{"text_format":"1","workbook":"xlsx","n_sheets":8,"sheets":["Home","Main Impact Map","ProRail","Infrabel","Data","SNCFR","SBB","ACF CFL"],"not_rendered":{"charts":0,"images":11,"macros":1,"external_links":6,"defined_names":61,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Home","index":0,"n_rows":5,"n_cols":15,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"! click icon to follow !"]

{"sheet":"Main Impact Map","index":1,"n_rows":15,"n_cols":14,"rows_kept":15,"cut":false,"hidden":false,"merged":[[45,5,46,7]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Main TCR for TT 2023 to TT 2025"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"03/08/2023 version 2"]
[null,null,null,null,null,null,null,null,null,null,null,null,"click on the comments for a direct link to TCR details"]

{"sheet":"ProRail","index":2,"n_rows":211,"n_cols":25,"rows_kept":211,"cut":false,"hidden":false,"merged":[[0,16,0,17],[0,3,0,4],[0,5,0,6],[0,7,0,8],[0,9,0,10],[0,11,0,12]]}
["IM","ID","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,"Description","IM\nProject ID\n(Optional)","Last updated","Classification","Deviation Location","Deviation Border","Status"]
[null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability "]
["ProRail","D003115-2301-00","< >","Deventer","Barneveld aansl.",2023,2023,12,13,"2023-03-25","00:30:00","2023-03-27","05:30:00",2,"continuous","Switch","T","LT+ST","Vernieuwen / Aanpassen wisselstraat, sporen op emplacement * More details: https://btd-planner.prorail.nl?taak=IO-D-003115-2301-00-2&doc=FOT (Register with ProRail)","D-003115","2022-11-23","Medium","00173","","Coordination"]
["ProRail","D003115-2302-00","< >","Deventer","Barneveld aansl.",2023,2023,20,20,"2023-05-18","01:00:00","2023-05-20","05:00:00",2,"continuous","Switch","T","LT+ST","Vernieuwen / Aanpassen wisselstraat, sporen op emplacement * More details: https://btd-planner.prorail.nl?taak=IO-D-003115-2302-00-2&doc=FOT (Register with ProRail)","D-003115","2022-12-07","Medium","00173","","Coordination"]
["ProRail","D003115-2303-00","< >","Deventer","Barneveld aansl.",2023,2023,29,32,"2023-07-22","01:00:00","2023-08-07","01:00:00",16,"continuous","Switch","T","LT+ST","Vernieuwen / Aanpassen wisselstraat, sporen op emplacement * More details: https://btd-planner.prorail.nl?taak=IO-D-003115-2303-00-1&doc=FOT (Register with ProRail)","D-003115","2022-11-15","High","00173","","Coordination"]
["ProRail","D003115-2304-00","< >","Deventer","Barneveld aansl.",2023,2023,44,45,"2023-11-04","01:00:00","2023-11-06","05:00:00",2,"continuous","Switch","T","LT+ST","Vernieuwen / Aanpassen wisselstraat, sporen op emplacement * More details: https://btd-planner.prorail.nl?taak=IO-D-003115-2304-00-1&doc=FOT (Register with ProRail)","D-003115","2022-11-15","Medium","00173","","Coordination"]
["ProRail","D003161-24B3-00","< >","Roosendaal","Goes",2024,2024,14,15,"2024-04-06","01:00:00","2024-04-08","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Saneren Dateq en realiseren DOSS 2.0 * More details: https://btd-planner.prorail.nl?taak=IO-D-003161-24B3-00-3&doc=FOT (Register with ProRail)","D-003161","2022-11-08","Medium","","","Coordination"]
["ProRail","D003183-2302-00","< >","Deventer","Apeldoorn",2023,2023,12,13,"2023-03-25","00:30:00","2023-03-27","05:30:00",2,"continuous","Catenary","T","LT+ST","BBV en EV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-D-003183-2302-00-2&doc=FOT (Register with ProRail)","D-003183","2022-11-23","Medium","00173","","Publication"]
["ProRail","D003183-2310-00","< >","Apeldoorn aansl.","Amersfoort aansl.",2023,2023,20,20,"2023-05-18","01:00:00","2023-05-20","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen spoorstaven, verwijderen NOBA's, aanbrengen RIP * More details: https://btd-planner.prorail.nl?taak=IO-D-003183-2310-00-4&doc=FOT (Register with ProRail)","D-003183","2022-11-30","Medium","00173, 00055","","Publication"]
["ProRail","D003183-2303-00","< >","Wierden","Apeldoorn aansl.",2023,2023,23,25,"2023-06-10","01:00:00","2023-06-19","05:00:00",9,"continuous","Switch","T","LT+ST","vernieuwen sporen en wissels * More details: https://btd-planner.prorail.nl?taak=IO-D-003183-2303-00-2&doc=FOT (Register with ProRail)","D-003183","2022-08-29","High","00173","00748","Publication"]
["ProRail","D003183-2304-00","< >","Apeldoorn","Amersfoort aansl.",2023,2023,44,45,"2023-11-04","01:00:00","2023-11-06","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen spoorstaven, verwijderen NABO's, aanleggen RIP * More details: https://btd-planner.prorail.nl?taak=IO-D-003183-2304-00-5&doc=FOT (Register with ProRail)","D-003183","2022-09-26","Medium","00173, 00055","","Publication"]
["ProRail","D003199-2405-00","< >","Deventer","Apeldoorn",2024,2024,6,7,"2024-02-10","01:00:00","2024-02-12","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-D-003199-2405-00-2&doc=FOT (Register with ProRail)","D-003199","2022-11-22","Medium","00173","","Publication"]
["ProRail","D003207-2401-00","< >","Zutphen Twentekanaal aansl.","Zutphen goed. empl. aansl.",2024,2024,15,16,"2024-04-13","01:00:00","2024-04-15","05:00:00",2,"continuous","Bridge","T","LT","Herstellen tuiconstructie stalen spoorbrug Eefde * More details: https://btd-planner.prorail.nl?taak=IO-D-003207-2401-00-3&doc=FOT (Register with ProRail)","D-003207","2022-12-14","Medium","00173","","Publication"]
["ProRail","D003207-2402-00","< >","Zutphen Twentekanaal aansl.","Zutphen goed. empl. aansl.",2024,2024,26,27,"2024-06-29","01:00:00","2024-07-01","05:00:00",2,"continuous","Bridge","T","LT","Herstellen tuiconstructie stalen spoorbrug Eefde * More details: https://btd-planner.prorail.nl?taak=IO-D-003207-2402-00-5&doc=FOT (Register with ProRail)","D-003207","2022-12-14","Medium","","","Publication"]
["ProRail","D003207-2403-00","< >","Zutphen Twentekanaal aansl.","Zutphen goed. empl. aansl.",2024,2024,36,37,"2024-09-07","01:00:00","2024-09-09","05:00:00",2,"continuous","Bridge","T","LT","Herstellen tuiconstructie stalen spoorbrug Eefde * More details: https://btd-planner.prorail.nl?taak=IO-D-003207-2403-00-2&doc=FOT (Register with ProRail)","D-003207","2022-12-07","Medium","00173","","Coordination"]
["ProRail","ER40204-2304-00","< >","Utrecht Centraal","Breukelen",2023,2023,26,27,"2023-07-01","01:00:00","2023-07-03","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","ervaringsrijden ERMTS * More details: https://btd-planner.prorail.nl?taak=IO-E-R40204-2304-00-1&doc=FOT (Register with ProRail)","E-R40204","2022-10-11","Medium","00129, 00621","","Publication"]
["ProRail","ER50008-2410-00","< >","Roosendaal","Roosendaal grens",2024,2024,35,36,"2024-08-31","01:00:00","2024-09-02","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Fase 0 ERTMS werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2410-00-2&doc=FOT (Register with ProRail)","E-R50008","2022-11-28","Medium","","","Coordination"]
["ProRail","ER50008-2409-00","< >","Lage Zwaluwe","Roosendaal",2024,2024,38,40,"2024-09-21","05:00:00","2024-09-30","05:00:00",9,"continuous","Miscellaneous","T","LT+ST","Fase 0 ERTMS werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2409-00-3&doc=FOT (Register with ProRail)","E-R50008","2022-11-10","High","00526","","Publication"]
["ProRail","ER50008-2412-00","< >","Breda aansl.","Roosendaal",2024,2024,41,42,"2024-10-12","05:00:00","2024-10-14","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Fase 0 ERTMS werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2412-00-2&doc=FOT (Register with ProRail)","E-R50008","2022-11-28","Medium","00129, 00055","","Coordination"]
["ProRail","ER50008-2411-00","< >","Roosendaal","Roosendaal grens",2024,2024,50,51,"2024-12-14","01:00:00","2024-12-16","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Fase 0 ERTMS werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2411-00-2&doc=FOT (Register with ProRail)","E-R50008","2022-12-07","Medium","","","Coordination"]
["ProRail","K006136-BWK3-00","< >","Zevenaar Betuweroute Aansl.","Kijfhoek zuid",2023,2023,15,16,"2023-04-15","00:00:00","2023-04-17","00:00:00",2,"continuous","Tunnel","T","LT+ST","BWK Sophiatunnel en Pankantunnel * More details: https://btd-planner.prorail.nl?taak=IO-K-006136-BWK3-00-2&doc=FOT (Register with ProRail)","K-006136","2022-11-09","Medium","99960, 00173","01331, 01254","Publication"]
["ProRail","K006310-2301-00","< >","Gouda Goverwelle","Moordrecht aansl. Zuid",2023,2023,29,30,"2023-07-22","01:00:00","2023-07-24","05:00:00",2,"continuous","Catenary","T","LT+ST","Het betreft het omleggen van IB kabels, EV kabels, telecom kabels, glasvezel kabels. * More details: https://btd-planner.prorail.nl?taak=IO-K-006310-2301-00-4&doc=FOT (Register with ProRail)","K-006310","2022-08-15","Medium","00173, 00055, 00747, 00530","","Coordination"]
["ProRail","K006310-2302-00","< >","Gouda Goverwelle","Moordrecht aansl. Zuid",2023,2023,33,34,"2023-08-19","01:00:00","2023-08-21","05:00:00",2,"continuous","Catenary","T","LT+ST","Het betreft het omleggen van IB kabels, EV kabels, telecom kabels, glasvezel kabels. * More details: https://btd-planner.prorail.nl?taak=IO-K-006310-2302-00-2&doc=FOT (Register with ProRail)","K-006310","2022-08-15","Medium","00173, 00055, 00747, 00530","","Coordination"]
["ProRail","K006310-2303-00","< >","Gouda Goverwelle","Moordrecht aansl. Zuid",2023,2023,37,38,"2023-09-16","01:00:00","2023-09-18","05:00:00",2,"continuous","Catenary","T","LT+ST","Het betreft het omleggen van IB kabels, EV kabels, telecom kabels, glasvezel kabels. * More details: https://btd-planner.prorail.nl?taak=IO-K-006310-2303-00-2&doc=FOT (Register with ProRail)","K-006310","2022-08-15","Medium","00173, 00055, 00747, 00530","","Coordination"]
["ProRail","K007022-2412-00","< >","Maasvlakte West","Maasvlakte Prinses Amaliahaven",2024,2024,50,50,"2024-12-13","23:00:00","2024-12-15","07:00:00",2,"continuous","Miscellaneous","T","LT+ST","Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2412-00-2&doc=FOT (Register with ProRail)","K-007022","2022-12-07","Medium","","","Coordination"]
["ProRail","K007022-2401-00","< >","Europoort","Maasvlakte aansl.",2024,2024,50,51,"2024-12-14","23:00:00","2024-12-16","07:00:00",2,"continuous","Miscellaneous","T","LT+ST","Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2401-00-4&doc=FOT (Register with ProRail)","K-007022","2022-12-06","Medium","","","Coordination"]
["ProRail","K007107-HY01-00","< >","Europoort West","Europoort West",2024,2024,5,6,"2024-02-03","23:00:00","2024-02-05","07:00:00",2,"continuous","Miscellaneous","T","ST","Spoorkruising met open ontgraving HY transport * More details: https://btd-planner.prorail.nl?taak=IO-K-007107-HY01-00-1&doc=FOT (Register with ProRail)","K-007107","2022-12-07","Medium","","","Coordination"]
["ProRail","K007207-02-00","< >","Kijfhoek zuid","Kijfhoek aansluiting noord",2023,2023,21,22,"2023-05-27","19:00:00","2023-05-29","23:00:00",2,"continuous","Miscellaneous","T","LT+ST","Aanleg pomp + 2x hydrant + 100m blusleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-007207-02-00-2&doc=FOT (Register with ProRail)","K-007207","2022-12-14","Medium","","","Publication"]
["ProRail","K007208-2305-00","< >","Geldermalsen","Oud Zaltbommel",2023,2023,28,29,"2023-07-15","05:00:00","2023-07-17","05:00:00",2,"continuous","Switch","T","LT+ST","Vervangen EBI-switches met NSE-stellers * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2305-00-2&doc=FOT (Register with ProRail)","K-007208","2022-02-21","Medium","99960, 00129, 00173","","Publication"]
["ProRail","K007208-2401-00","< >","Geldermalsen","Dordrecht",2024,2024,10,11,"2024-03-09","01:00:00","2024-03-11","09:00:00",2,"continuous","Switch","T","LT+ST","Vervangen EBI stellers 13, 33, 45, 53, 65, 73 en 85 door de NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2401-00-2&doc=FOT (Register with ProRail)","K-007208","2022-11-18","Medium","","","Publication"]
["ProRail","K007508-2303-00","< >","Barendrecht aansl.","Rotterdam Centraal",2023,2023,8,10,"2023-02-26","03:00:00","2023-03-06","05:00:00",8,"continuous","Track & Rail","T","LT+ST","Vernieuwing dwarsliggers spoor L en voor project K-007806 het vervangen van diverse LO's op empl. Rtd CS (gebied B en C) * More details: https://btd-planner.prorail.nl?taak=IO-K-007508-2303-00-7&doc=FOT (Register with ProRail)","K-007508","2022-10-27","High","","","Publication"]
["ProRail","K007508-2301-00","< >","Rotterdam Lombardijen","Rotterdam Centraal",2023,2023,30,32,"2023-07-30","03:00:00","2023-08-07","05:00:00",8,"continuous","Track & Rail","T","LT+ST","Vernieuwing dwarsliggers spoor J * More details: https://btd-planner.prorail.nl?taak=IO-K-007508-2301-00-6&doc=FOT (Register with ProRail)","K-007508","2022-07-19","High","","","Publication"]
["ProRail","K007802-2301-00","< >","Hoge Gouwebrug - bij Gouda","Den Haag Ypenburg",2023,2023,17,18,"2023-04-29","01:15:00","2023-05-04","05:15:00",5,"continuous","Miscellaneous","T","LT+ST","Slopen middels open ontgraving van historische duiker, en nieuwbouw van de duiker GEO107 KM9.785 met diverse risico's. * More details: https://btd-planner.prorail.nl?taak=IO-K-007802-2301-00-6&doc=FOT (Register with ProRail)","K-007802","2022-11-28","Medium","","","Publication"]
["ProRail","K007802-2302-00","< >","Hoge Gouwebrug - bij Gouda","Den Haag Ypenburg",2023,2023,29,29,"2023-07-17","01:00:00","2023-07-22","05:00:00",5,"continuous","Miscellaneous","T","LT+ST","Slopen middels open ontgraving van historische duikers, en nieuwbouw van duikers GEO107. * More details: https://btd-planner.prorail.nl?taak=IO-K-007802-2302-00-5&doc=FOT (Register with ProRail)","K-007802","2022-11-23","Medium","","","Publication"]
["ProRail","K007802-2303-00","< >","Hoge Gouwebrug - bij Gouda","Den Haag Ypenburg",2023,2023,33,33,"2023-08-14","01:00:00","2023-08-18","05:00:00",4,"continuous","Miscellaneous","T","LT+ST","Slopen middels open ontgraving van historische duikers, en nieuwbouw van duikers GEO107. * More details: https://btd-planner.prorail.nl?taak=IO-K-007802-2303-00-4&doc=FOT (Register with ProRail)","K-007802","2022-11-24","Medium","","","Publication"]
["ProRail","K007806-2413-00","< >","Sliedrecht","Rotterdam Lombardijen",2024,2024,10,11,"2024-03-09","01:00:00","2024-03-11","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Vervanging diverse LO's (ca. 14 sts) regio RZ ter hoogte van de perronsporen 1, 2, 15, 16, 20 en 21 op station Dordrecht * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2413-00-3&doc=FOT (Register with ProRail)","K-007806","2022-11-07","Medium","","","Publication"]
["ProRail","K007806-2414-00","< >","Kijfhoek aansl. Zuid","Willemsdorp",2024,2024,18,19,"2024-05-04","01:00:00","2024-05-06","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Vervanging diverse LO's (ca. 11 sts) regio RZ ter hoogte van de perronsporen 3, 4, 5 en 6 op station Dordrecht geo 542 * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2414-00-10&doc=FOT (Register with ProRail)","K-007806","2022-12-02","Medium","","","Publication"]
["ProRail","K007806-2427-00","< >","Zwijndrecht","Lage Zwaluwe",2024,2024,38,39,"2024-09-21","01:00:00","2024-09-23","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Vervanging diverse LO's (ca. 19 sts) regio RZ ter hoogte van de perronsporen 2, 3 en 4 op station Dordrecht geo 542 * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2427-00-8&doc=FOT (Register with ProRail)","K-007806","2022-11-07","Medium","00526, 00129","00748","Publication"]
["ProRail","K007810-1321-00","< >","Rotterdam Noord goed. Oost","Delfshaven Schiebrug aansl.",2023,2023,29,30,"2023-07-22","01:00:00","2023-07-24","05:00:00",2,"continuous","Bridge","T","LT+ST","Aanbrengen 204m ballastkeringen (km 50.238 - 50.829) nabij brug over de Rotte * More details: https://btd-planner.prorail.nl?taak=IO-K-007810-1321-00-3&doc=FOT (Register with ProRail)","K-007810","2022-01-13","Medium","00173, 00055, 00530","","Publication"]
["ProRail","K008109-TVP6-02","< >","Rail Service Center Waalhaven aansl.","Botlek",2024,2024,13,14,"2024-03-30","19:00:00","2024-04-02","00:00:00",3,"continuous","Switch","T","LT+ST","Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-TVP6-02-2&doc=FOT (Register with ProRail)","K-008109","2022-12-13","Medium","","","Publication"]
["ProRail","K008109-TVP5-00","< >","Waalhaven Zuid aansl Zuid","Pernis",2024,2024,13,14,"2024-03-30","19:00:00","2024-04-02","00:00:00",3,"continuous","Switch","T","LT+ST","Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-TVP5-00-4&doc=FOT (Register with ProRail)","K-008109","2022-12-12","Medium","","","Publication"]
["ProRail","K008109-TVP6-01","< >","Rail Service Center Waalhaven aansl.","Botlek",2024,2024,20,21,"2024-05-18","19:00:00","2024-05-20","23:00:00",2,"continuous","Switch","T","LT+ST","Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-TVP6-01-1&doc=FOT (Register with ProRail)","K-008109","2022-12-13","Medium","","","Publication"]
["ProRail","K008109-TVP8-00","< >","Waalhaven Zuid","Waalhaven Zuid",2024,2024,34,35,"2024-08-24","23:00:00","2024-08-26","07:00:00",2,"continuous","Switch","T","ST","Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-TVP8-00-2&doc=FOT (Register with ProRail)","K-008109","2022-12-13","Medium","","","Publication"]
["ProRail","K008110-2431-00","< >","Woerden","Gouda",2024,2024,40,41,"2024-10-05","01:00:00","2024-10-07","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-008110-2431-00-2&doc=FOT (Register with ProRail)","K-008110","2022-12-13","Medium","00173, 00055, 00747, 00530","","Publication"]
["ProRail","K008110-2421-00","< >","Leiden Centraal","Den Haag Mariahoeve",2024,2024,45,46,"2024-11-09","01:00:00","2024-11-11","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-008110-2421-00-1&doc=FOT (Register with ProRail)","K-008110","2022-12-13","Medium","","","Publication"]
["ProRail","KB17018-2301-00","< >","Zevenaar Betuweroute Aansl.","Betuweroute Valburg aansl. Oost",2023,2023,6,6,"2023-02-10","23:00:00","2023-02-12","23:00:00",2,"continuous","Tunnel","T","LT+ST","Pankantunnel en Zevenaartunnel.  jaarlijkse Tunnel Technische Installaties onderhoud * More details: https://btd-planner.prorail.nl?taak=IO-K-B17018-2301-00-2&doc=FOT (Register with ProRail)","K-B17018","2022-12-06","Medium","00173","01331, 01254","Publication"]
["ProRail","KX00006-2350-00","< >","Barendrecht Vork Aansl","Maasvlakte Prinses Amaliahaven",2023,2023,11,12,"2023-03-18","23:00:00","2023-03-20","07:00:00",2,"continuous","Catenary","T","LT+ST","Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2350-00-2&doc=FOT (Register with ProRail)","K-X00006","2022-11-09","Medium","","","Publication"]
["ProRail","KX00006-2351-00","< >","Barendrecht Vork Aansl","Maasvlakte Prinses Amaliahaven",2023,2023,14,15,"2023-04-08","19:00:00","2023-04-10","23:00:00",2,"continuous","Catenary","T","LT+ST","Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2351-00-2&doc=FOT (Register with ProRail)","K-X00006","2022-11-02","Medium","","","Publication"]
["ProRail","KX00006-2352-00","< >","Barendrecht Vork Aansl","Maasvlakte Prinses Amaliahaven",2023,2023,21,22,"2023-05-27","19:00:00","2023-05-29","23:00:00",2,"continuous","Catenary","T","LT+ST","Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2352-00-1&doc=FOT (Register with ProRail)","K-X00006","2022-12-14","Medium","","","Publication"]
["ProRail","KX00006-2353-00","< >","Barendrecht Vork Aansl","Maasvlakte Prinses Amaliahaven",2023,2023,26,27,"2023-07-01","23:00:00","2023-07-03","07:00:00",2,"continuous","Catenary","T","LT+ST","Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2353-00-1&doc=FOT (Register with ProRail)","K-X00006","2022-11-10","Medium","","","Publication"]
["ProRail","KX00006-2354-00","< >","Barendrecht Vork Aansl","Maasvlakte Prinses Amaliahaven",2023,2023,37,38,"2023-09-16","23:00:00","2023-09-18","07:00:00",2,"continuous","Catenary","T","LT+ST","Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2354-00-1&doc=FOT (Register with ProRail)","K-X00006","2022-11-10","Medium","","","Publication"]
["ProRail","KX00006-2355-00","< >","Barendrecht Vork Aansl","Maasvlakte Prinses Amaliahaven",2023,2023,47,48,"2023-11-25","23:00:00","2023-11-27","07:00:00",2,"continuous","Catenary","T","LT+ST","Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2355-00-1&doc=FOT (Register with ProRail)","K-X00006","2022-04-22","Medium","","","Publication"]
["ProRail","KX00015-2301-00","< >","Betuweroute Meteren","Kijfhoek zuid",2023,2023,6,7,"2023-02-11","01:00:00","2023-02-13","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","herstel actie van KW 40 * More details: https://btd-planner.prorail.nl?taak=IO-K-X00015-2301-00-2&doc=FOT (Register with ProRail)","K-X00015","2022-11-07","Medium","99960, 00173","01331","Publication"]
["ProRail","KX00015-2302-00","< >","Betuweroute Meteren","Kijfhoek zuid",2023,2023,7,8,"2023-02-18","01:00:00","2023-02-20","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","herstel actie van KW 40 * More details: https://btd-planner.prorail.nl?taak=IO-K-X00015-2302-00-2&doc=FOT (Register with ProRail)","K-X00015","2022-11-07","Medium","99960, 00173, 00055","01331","Publication"]
["ProRail","L005217-2301-00","< >","Houten Castellum","Geldermalsen",2023,2023,28,29,"2023-07-15","01:00:00","2023-07-17","05:00:00",2,"continuous","Bridge","T","LT+ST","conserveren lekbrug * More details: https://btd-planner.prorail.nl?taak=IO-L-005217-2301-00-1&doc=FOT (Register with ProRail)","L-005217","2022-02-04","Medium","00319, 00129, 00173","","Publication"]
["ProRail","L005217-2304-00","< >","Houten Castellum","Geldermalsen",2023,2023,29,29,"2023-07-17","05:00:00","2023-07-19","09:00:00",2,"continuous","Bridge","T","LT+ST","conserveren lekbrug * More details: https://btd-planner.prorail.nl?taak=IO-L-005217-2304-00-2&doc=FOT (Register with ProRail)","L-005217","2022-02-04","Medium","00319, 00129, 00173","","Publication"]
["ProRail","L005217-2305-00","< >","Houten Castellum","Geldermalsen",2023,2023,29,29,"2023-07-19","09:00:00","2023-07-21","13:00:00",2,"continuous","Bridge","T","LT+ST","conserveren lekbrug * More details: https://btd-planner.prorail.nl?taak=IO-L-005217-2305-00-2&doc=FOT (Register with ProRail)","L-005217","2022-10-14","Medium","00319, 00129, 00173","","Publication"]
["ProRail","L005222-2314-00","< >","Utrecht Centraal","Breukelen",2023,2023,26,27,"2023-07-01","01:00:00","2023-07-03","05:00:00",2,"continuous","Switch","T","LT+ST","Vervangen EBI-switches met NSE-stellers * More details: https://btd-planner.prorail.nl?taak=IO-L-005222-2314-00-3&doc=FOT (Register with ProRail)","L-005222","2022-08-23","Medium","00621","","Publication"]
["ProRail","L005222-2302-00","< >","Amsterdam Muiderpoort","Abcoude",2023,2023,44,45,"2023-11-04","01:00:00","2023-11-06","05:00:00",2,"continuous","Switch","T","LT+ST","Vervangen EBI-switches met NSE-stellers van 4 a 5 wissels * More details: https://btd-planner.prorail.nl?taak=IO-L-005222-2302-00-1&doc=FOT (Register with ProRail)","L-005222","2022-03-01","Medium","00173, 00055, 00747, 00621, 00530","","Publication"]
["ProRail","L005222-2306-00","< >","Amsterdam Transformatorweg aansl.","Amsterdam Riekerpolder aansl.",2023,2023,49,50,"2023-12-09","00:00:00","2023-12-11","04:00:00",2,"continuous","Switch","T","LT+ST","Vervangen van EBI-switches met NSE-stellers * More details: https://btd-planner.prorail.nl?taak=IO-L-005222-2306-00-1&doc=FOT (Register with ProRail)","L-005222","2022-02-07","Medium","00530","","Publication"]
["ProRail","L005222-2413-00","< >","Maarn goed. empl.","Utrecht Centraal",2024,2024,20,20,"2024-05-17","01:00:00","2024-05-19","05:00:00",2,"continuous","Switch","T","LT+ST","Vervangen EBI stellers 97, 101, 103, 105, 109 en 111 door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-L-005222-2413-00-3&doc=FOT (Register with ProRail)","L-005222","2022-12-01","Medium","","","Coordination"]
["ProRail","L005222-2414-00","< >","Maarn goed. empl.","Driebergen-Zeist",2024,2024,20,21,"2024-05-19","01:00:00","2024-05-21","05:00:00",2,"continuous","Switch","T","LT+ST","Vervangen EBI stellers * More details: https://btd-planner.prorail.nl?taak=IO-L-005222-2414-00-2&doc=FOT (Register with ProRail)","L-005222","2022-12-12","Medium","","","Publication"]
["ProRail","L005252-2317-00","< >","Breukelen aansluiting","Harmelen aansl.",2023,2023,8,9,"2023-02-25","01:00:00","2023-02-27","05:00:00",2,"continuous","Maintenance","T","LT+ST","BBV 2023 * More details: https://btd-planner.prorail.nl?taak=IO-L-005252-2317-00-2&doc=FOT (Register with ProRail)","L-005252","2022-10-27","Medium","00173, 00055, 00747, 00621, 00530","","Publication"]
["ProRail","L005252-2301-00","< >","Breukelen aansluiting","Harmelen aansl.",2023,2023,12,13,"2023-03-25","01:00:00","2023-03-27","06:00:00",2,"continuous","Maintenance","T","LT+ST","BBV 2023 * More details: https://btd-planner.prorail.nl?taak=IO-L-005252-2301-00-2&doc=FOT (Register with ProRail)","L-005252","2022-11-23","Medium","00173, 00055, 00747, 00530","","Publication"]
["ProRail","L005252-2315-00","< >","Breukelen aansluiting","Harmelen aansl.",2023,2023,23,24,"2023-06-10","01:00:00","2023-06-12","05:00:00",2,"continuous","Maintenance","T","LT+ST","BBV 2023 * More details: https://btd-planner.prorail.nl?taak=IO-L-005252-2315-00-1&doc=FOT (Register with ProRail)","L-005252","2022-02-14","Medium","00173, 00055, 00747, 00621, 00530","","Publication"]
["ProRail","L005252-2309-00","< >","Houten","Geldermalsen",2023,2023,28,29,"2023-07-15","01:00:00","2023-07-17","05:00:00",2,"continuous","Maintenance","T","LT+ST","BBV 2023 * More details: https://btd-planner.prorail.nl?taak=IO-L-005252-2309-00-2&doc=FOT (Register with ProRail)","L-005252","2021-11-15","Medium","00319, 00129, 00173","","Publication"]
["ProRail","L005252-2302-00","< >","Houten","Geldermalsen",2023,2023,29,29,"2023-07-17","01:00:00","2023-07-19","05:00:00",2,"continuous","Maintenance","T","LT+ST","BBV 2023 * More details: https://btd-planner.prorail.nl?taak=IO-L-005252-2302-00-2&doc=FOT (Register with ProRail)","L-005252","2021-11-17","Medium","00319, 00129, 00173","","Publication"]
["ProRail","L005252-2316-00","< >","Breukelen aansluiting","Harmelen aansl.",2023,2023,46,47,"2023-11-18","01:00:00","2023-11-20","05:00:00",2,"continuous","Maintenance","T","LT+ST","BBV 2023 * More details: https://btd-planner.prorail.nl?taak=IO-L-005252-2316-00-1&doc=FOT (Register with ProRail)","L-005252","2021-11-30","Medium","00173, 00055, 00747, 00621, 00530","","Publication"]
["ProRail","L005283-2391-00","< >","Amersfoort Centraal","Blauwkapel Oost aansl.",2023,2023,30,31,"2023-07-29","01:00:00","2023-08-01","05:00:00",3,"continuous","Switch","T","LT+ST","BBV werkzaamheden. Vervangen van wissels , spoorstaven, dwarsligger en ballast * More details: https://btd-planner.prorail.nl?taak=IO-L-005283-2391-00-1&doc=FOT (Register with ProRail)","L-005283","2022-12-08","Medium","00319, 00173","","Coordination"]
["ProRail","L005360-24IB-00","< >","Amsterdam Muiderpoort aansl.","Amsterdam Bijlmer ArenA",2024,2024,18,18,"2024-05-03","01:00:00","2024-05-05","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Conserveren kunstwerken * More details: https://btd-planner.prorail.nl?taak=IO-L-005360-24IB-00-2&doc=FOT (Register with ProRail)","L-005360","2022-11-25","Medium","99960, 00129, 00621, 00530","","Publication"]
["ProRail","L005360-24BB-00","< >","Amsterdam Muiderpoort","Amsterdam Bijlmer ArenA",2024,2024,18,18,"2024-05-01","01:00:00","2024-05-03","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Conserveren kunstwerken * More details: https://btd-planner.prorail.nl?taak=IO-L-005360-24BB-00-2&doc=FOT (Register with ProRail)","L-005360","2022-11-25","Medium","00621, 00530","","Publication"]
["ProRail","L005360-24CC-00","< >","Watergraafsmeer Oost aansl.","Amsterdam Muiderpoort West",2024,2024,24,25,"2024-06-15","01:00:00","2024-06-17","05:00:00",2,"continuous","Bridge","T","LT+ST","Conserveren brug Zuiderringvaart BS * More details: https://btd-planner.prorail.nl?taak=IO-L-005360-24CC-00-2&doc=FOT (Register with ProRail)","L-005360","2022-12-14","Medium","00173, 00530","","Coordination"]
["ProRail","L005383-2302-00","< >","Naarden-Bussum","Weesp",2023,2023,45,46,"2023-11-11","01:00:00","2023-11-13","05:00:00",2,"continuous","Tunnel","T","LT+ST","Vervangen spoorstaven, bevestigingsmiddelen en het vervangen ingegoten spoorstaaf ovw Keverdijk en tunneldek Gooiboog * More details: https://btd-planner.prorail.nl?taak=IO-L-005383-2302-00-1&doc=FOT (Register with ProRail)","L-005383","2022-02-21","Medium","00173, 00055, 00747, 00621","","Publication"]
["ProRail","L005383-2301-00","< >","Naarden-Bussum","Weesp",2023,2023,46,47,"2023-11-18","01:00:00","2023-11-20","05:00:00",2,"continuous","Tunnel","T","LT+ST","Vervangen spoorstaven, bevestigingsmiddelen en het vervangen ingegoten spoorstaaf ovw Keverdijk en tunneldek Gooiboog * More details: https://btd-planner.prorail.nl?taak=IO-L-005383-2301-00-3&doc=FOT (Register with ProRail)","L-005383","2022-02-11","Medium","00173, 00055, 00747, 00621","","Publication"]
["ProRail","L005387-2302-00","< >","Utrecht Centraal","Gouwebrug - bij Gouda",2023,2023,41,42,"2023-10-15","23:30:00","2023-10-21","06:00:00",6,"continuous","Signal","T","LT+ST","BBV, Saneren Oudewater / PHS seinoptimalisatie Gouda-Woerden * More details: https://btd-planner.prorail.nl?taak=IO-L-005387-2302-00-3&doc=FOT (Register with ProRail)","L-005387","2022-04-11","Medium","00129, 00173, 00055, 00747, 00530","","Publication"]
["ProRail","L005387-2401-00","< >","Woerden","Gouda Goverwelle",2024,2024,5,6,"2024-02-03","01:00:00","2024-02-05","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV logistiek, opladen / afvoeren materialen * More details: https://btd-planner.prorail.nl?taak=IO-L-005387-2401-00-2&doc=FOT (Register with ProRail)","L-005387","2022-11-18","Medium","00173, 00055, 00747, 00530","","Publication"]
["ProRail","L005430-2409-00","< >","Amsterdam Westhaven","Amsterdam Westhaven",2024,2024,15,16,"2024-04-14","01:00:00","2024-04-17","01:00:00",3,"continuous","Switch","T","ST","BBV, vernieuwen sporen en wissels. ingieten Harmelen ovw * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2409-00-2&doc=FOT (Register with ProRail)","L-005430","2022-12-02","Medium","","","Publication"]
["ProRail","L005442-2408-00","< >","Amersfoort Centraal","Hilversum",2024,2024,13,14,"2024-03-30","01:00:00","2024-04-01","06:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV  2024 * More details: https://btd-planner.prorail.nl?taak=IO-L-005442-2408-00-3&doc=FOT (Register with ProRail)","L-005442","2022-11-21","Medium","00319, 00173, 00055, 00747","","Publication"]
["ProRail","L005445-2402-00","< >","Amsterdam Transformatorweg aansl.","Amsterdam Riekerpolder aansl.",2024,2024,3,4,"2024-01-20","01:00:00","2024-01-22","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2402-00-1&doc=FOT (Register with ProRail)","L-005445","2022-10-14","Medium","00530","","Publication"]
["ProRail","L005445-2404-00","< >","Amsterdam Transformatorweg aansl.","Amsterdam Riekerpolder aansl.",2024,2024,5,6,"2024-02-03","01:00:00","2024-02-05","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2404-00-1&doc=FOT (Register with ProRail)","L-005445","2022-10-14","Medium","00530","","Publication"]
["ProRail","L005445-2403-00","< >","Amsterdam Transformatorweg aansl.","Amsterdam Riekerpolder aansl.",2024,2024,6,7,"2024-02-10","01:00:00","2024-02-12","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2403-00-1&doc=FOT (Register with ProRail)","L-005445","2022-10-21","Medium","00530","","Publication"]
["ProRail","L005445-2405-00","< >","Amsterdam Transformatorweg aansl.","Amsterdam Riekerpolder aansl.",2024,2024,9,10,"2024-03-02","01:00:00","2024-03-04","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2405-00-2&doc=FOT (Register with ProRail)","L-005445","2022-10-14","Medium","00530","","Publication"]
["ProRail","L005445-2406-00","< >","Amsterdam Transformatorweg aansl.","Amsterdam Riekerpolder aansl.",2024,2024,10,11,"2024-03-09","01:00:00","2024-03-11","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2406-00-2&doc=FOT (Register with ProRail)","L-005445","2022-10-14","Medium","00530","","Publication"]
["ProRail","L005445-2407-00","< >","Amsterdam Transformatorweg aansl.","Amsterdam Riekerpolder aansl.",2024,2024,12,13,"2024-03-23","01:00:00","2024-03-25","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2407-00-2&doc=FOT (Register with ProRail)","L-005445","2022-11-04","Medium","00530","","Publication"]
["ProRail","L005445-2408-00","< >","Amsterdam Transformatorweg aansl.","Amsterdam Riekerpolder aansl.",2024,2024,16,17,"2024-04-20","01:00:00","2024-04-22","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2408-00-2&doc=FOT (Register with ProRail)","L-005445","2022-10-24","Medium","00530","","Publication"]
["ProRail","L005445-2401-00","< >","Amsterdam Transformatorweg aansl.","Amsterdam Riekerpolder aansl.",2024,2024,21,22,"2024-05-25","01:00:00","2024-05-27","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2401-00-2&doc=FOT (Register with ProRail)","L-005445","2022-12-13","Medium","00530","","Coordination"]
["ProRail","M004042-2401-00","< >","Venlo grens","Tegelen",2024,2024,11,12,"2024-03-16","01:00:00","2024-03-18","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Het ombouwen van de resterende FTGS secties naar het nieuwe TCM100 * More details: https://btd-planner.prorail.nl?taak=IO-M-004042-2401-00-3&doc=FOT (Register with ProRail)","M-004042","2022-11-09","Medium","","00748","Publication"]
["ProRail","M004523-24B1-00","< >","Vught","Boxtel",2024,2024,27,28,"2024-07-01","01:00:00","2024-07-08","05:00:00",7,"continuous","Switch","T","LT","Saneren spoor en wissels, Toevoegen RIP en wissel. Bovenbouwvernieuwing * More details: https://btd-planner.prorail.nl?taak=IO-M-004523-24B1-00-2&doc=FOT (Register with ProRail)","M-004523","2022-12-09","High","","","Coordination"]
["ProRail","M004734-2202-00","< >","Roosendaal","Vlissingen Souburg",2023,2023,4,5,"2023-01-27","01:15:00","2023-01-30","05:15:00",3,"continuous","Maintenance","T","LT+ST","Saneren wissels * More details: https://btd-planner.prorail.nl?taak=IO-M-004734-2202-00-6&doc=FOT (Register with ProRail)","M-004734","2022-09-29","Medium","","","Publication"]
["ProRail","M004734-2301-00","< >","Lage Zwaluwe","Roosendaal",2023,2023,27,28,"2023-07-07","01:00:00","2023-07-10","05:00:00",3,"continuous","Maintenance","T","LT+ST","Saneren wissels en sporen in Oudenbosch en Zevenbergen * More details: https://btd-planner.prorail.nl?taak=IO-M-004734-2301-00-1&doc=FOT (Register with ProRail)","M-004734","2022-05-18","Medium","99960, 00526, 00055","","Publication"]
["ProRail","M004754-2301-00","< >","Bergen op Zoom","Kruiningen-Yerseke",2023,2023,4,5,"2023-01-28","01:15:00","2023-01-30","05:15:00",2,"continuous","Bridge","T","LT+ST","Conserveren Kreekrakbrug * More details: https://btd-planner.prorail.nl?taak=IO-M-004754-2301-00-6&doc=FOT (Register with ProRail)","M-004754","2022-09-29","Medium","","","Publication"]
["ProRail","M004754-2302-00","< >","Bergen op Zoom","Kruiningen-Yerseke",2023,2023,8,9,"2023-02-25","01:00:00","2023-02-27","05:00:00",2,"continuous","Bridge","T","LT+ST","Conserveren Kreekrakbrug * More details: https://btd-planner.prorail.nl?taak=IO-M-004754-2302-00-2&doc=FOT (Register with ProRail)","M-004754","2022-11-01","Medium","","","Publication"]
["ProRail","M004754-2303-00","< >","Bergen op Zoom","Goes",2023,2023,37,38,"2023-09-16","01:00:00","2023-09-18","05:00:00",2,"continuous","Bridge","T","LT+ST","Conserveren Kreekrakbrug * More details: https://btd-planner.prorail.nl?taak=IO-M-004754-2303-00-2&doc=FOT (Register with ProRail)","M-004754","2022-08-04","Medium","","","Publication"]
["ProRail","M004789-2301-00","< >","Helmond","Eindhoven Centraal",2023,2023,41,42,"2023-10-14","01:00:00","2023-10-18","01:00:00",4,"continuous","Bridge","T","LT+ST","conserveren brug De Kleine Dommel * More details: https://btd-planner.prorail.nl?taak=IO-M-004789-2301-00-4&doc=FOT (Register with ProRail)","M-004789","2022-02-28","Medium","","01331, 00748","Publication"]
["ProRail","M004791-2302-00","< >","Venlo","Roermond",2023,2023,41,42,"2023-10-14","01:00:00","2023-10-16","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen overwegen * More details: https://btd-planner.prorail.nl?taak=IO-M-004791-2302-00-3&doc=FOT (Register with ProRail)","M-004791","2022-08-04","Medium","","","Publication"]
["ProRail","M004792-2301-00","< >","Blerick","Eindhoven Centraal",2023,2023,41,43,"2023-10-14","01:00:00","2023-10-23","05:00:00",9,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004792-2301-00-10&doc=FOT (Register with ProRail)","M-004792","2022-02-28","High","","00748","Publication"]
["ProRail","M004796-2301-00","< >","Weert","Eindhoven Centraal",2023,2023,8,9,"2023-02-22","00:48:00","2023-03-03","04:48:00",9,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden en rijddraad vernieuwing * More details: https://btd-planner.prorail.nl?taak=IO-M-004796-2301-00-7&doc=FOT (Register with ProRail)","M-004796","2022-11-01","High","","","Publication"]
["ProRail","M004796-2306-00","< >","Maastricht","Eijsden grens",2023,2023,26,27,"2023-07-01","01:00:00","2023-07-03","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004796-2306-00-3&doc=FOT (Register with ProRail)","M-004796","2022-01-25","Medium","","","Publication"]
["ProRail","M004796-2302-00","< >","Weert","Eindhoven Centraal",2023,2023,33,34,"2023-08-19","01:00:00","2023-08-21","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden en rijddraad vernieuwing * More details: https://btd-planner.prorail.nl?taak=IO-M-004796-2302-00-5&doc=FOT (Register with ProRail)","M-004796","2022-02-11","Medium","","","Publication"]
["ProRail","M004796-2303-00","< >","Roermond","Roermond",2023,2023,39,40,"2023-09-30","01:00:00","2023-10-02","05:00:00",2,"continuous","Track & Rail","T","ST","BBV werkzaamheden spoor 3 * More details: https://btd-planner.prorail.nl?taak=IO-M-004796-2303-00-8&doc=FOT (Register with ProRail)","M-004796","2022-06-08","Medium","","","Publication"]
["ProRail","M004796-2304-00","< >","Sittard","Beatrixhaven aansl. (Maastricht)",2023,2023,46,47,"2023-11-18","05:00:00","2023-11-20","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004796-2304-00-3&doc=FOT (Register with ProRail)","M-004796","2022-01-31","Medium","","","Publication"]
["ProRail","M004811-2301-00","< >","Roermond","Eindhoven Centraal",2023,2023,31,34,"2023-08-05","05:00:00","2023-08-21","05:00:00",16,"continuous","Switch","T","LT+ST","saneren sporen/wissels en terugkoppelen spoor 12 * More details: https://btd-planner.prorail.nl?taak=IO-M-004811-2301-00-5&doc=FOT (Register with ProRail)","M-004811","2022-08-03","High","","","Publication"]
["ProRail","M004830-2401-00","< >","Tilburg Universiteit","Breda",2024,2024,10,11,"2024-03-09","01:00:00","2024-03-11","05:00:00",2,"continuous","Catenary","T","LT+ST","Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004830-2401-00-2&doc=FOT (Register with ProRail)","M-004830","2022-12-08","Medium","99960, 00129, 00055","00748","Coordination"]
["ProRail","M004830-2403-00","< >","Tilburg Universiteit","Breda",2024,2024,17,19,"2024-04-28","01:00:00","2024-05-10","01:00:00",12,"continuous","Catenary","T","LT+ST","Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004830-2403-00-2&doc=FOT (Register with ProRail)","M-004830","2022-11-14","High","99960, 00129, 00173, 00055, 00747","00748","Publication"]
["ProRail","M004830-2402-00","< >","Tilburg Universiteit","Breda",2024,2024,35,36,"2024-08-31","01:00:00","2024-09-02","05:00:00",2,"continuous","Catenary","T","LT+ST","Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004830-2402-00-3&doc=FOT (Register with ProRail)","M-004830","2022-12-09","Medium","99960, 00129, 00055","00748","Coordination"]
["ProRail","M004849-2306-00","< >","Oss","'s-Hertogenbosch",2023,2023,17,18,"2023-04-29","01:10:00","2023-05-01","05:10:00",2,"continuous","Track & Rail","T","LT+ST","Vernieuwen overweg Deken van Roestellaan in Rosmalen. * More details: https://btd-planner.prorail.nl?taak=IO-M-004849-2306-00-2&doc=FOT (Register with ProRail)","M-004849","2022-11-28","Medium","","","Publication"]
["ProRail","M004849-2301-00","< >","Roosendaal","Goes",2023,2023,20,21,"2023-05-20","01:00:00","2023-05-22","05:00:00",2,"continuous","Track & Rail","T","LT+ST","Diverse BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004849-2301-00-2&doc=FOT (Register with ProRail)","M-004849","2022-12-07","Medium","","","Publication"]
["ProRail","M004849-2302-00","< >","Roosendaal","Goes",2023,2023,23,24,"2023-06-09","01:00:00","2023-06-12","05:00:00",3,"continuous","Track & Rail","T","LT+ST","Diverse BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004849-2302-00-1&doc=FOT (Register with ProRail)","M-004849","2022-01-28","Medium","","","Publication"]
["ProRail","M004849-2305-00","< >","Goes","Vlissingen Souburg",2023,2023,37,38,"2023-09-16","01:00:00","2023-09-18","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV Werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004849-2305-00-2&doc=FOT (Register with ProRail)","M-004849","2022-08-03","Medium","","","Publication"]
["ProRail","M004849-2309-00","< >","Dordrecht","Roosendaal",2023,2023,39,41,"2023-09-30","05:00:00","2023-10-11","05:00:00",11,"continuous","Track & Rail","T","LT+ST","BBV Werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004849-2309-00-4&doc=FOT (Register with ProRail)","M-004849","2022-05-18","High","00526, 00129, 00055","00748","Publication"]
["ProRail","M004851-2301-00","< >","Roosendaal","Bergen op Zoom",2023,2023,20,21,"2023-05-20","01:00:00","2023-05-22","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV vernieuwingswerkzaamheden Roosendaal * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2301-00-5&doc=FOT (Register with ProRail)","M-004851","2022-12-07","Medium","","","Publication"]
["ProRail","M004851-2307-00","< >","Lage Zwaluwe","Moerdijk",2023,2023,32,33,"2023-08-12","01:00:00","2023-08-14","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden Lage Zwaluwe * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2307-00-4&doc=FOT (Register with ProRail)","M-004851","2022-08-01","Medium","","","Publication"]
["ProRail","M004851-2302-00","< >","Roosendaal","Bergen op Zoom",2023,2023,37,38,"2023-09-16","01:00:00","2023-09-18","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV vernieuwingswerkzaamheden Roosendaal * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2302-00-4&doc=FOT (Register with ProRail)","M-004851","2022-03-29","Medium","","","Publication"]
["ProRail","M004853-2311-00","< >","Sloehaven empl.","Sloe-Thermfos",2023,2023,12,13,"2023-03-25","01:00:00","2023-03-27","06:00:00",2,"continuous","Track & Rail","T","LT","BBV-werkzaamheden Stamlijn WTC * More details: https://btd-planner.prorail.nl?taak=IO-M-004853-2311-00-2&doc=FOT (Register with ProRail)","M-004853","2022-11-23","Medium","","","Publication"]
["ProRail","M004853-2304-00","< >","Sloehaven empl.","Sloe-Frankrijkweg",2023,2023,18,19,"2023-05-06","23:00:00","2023-05-08","07:00:00",2,"continuous","Track & Rail","T","LT","BBV-werkzaamheden Sloe Frankrijkweg * More details: https://btd-planner.prorail.nl?taak=IO-M-004853-2304-00-3&doc=FOT (Register with ProRail)","M-004853","2022-11-23","Medium","","","Publication"]
["ProRail","M004853-2301-00","< >","Terneuzen","Axel aansl.",2023,2023,36,37,"2023-09-09","01:00:00","2023-09-11","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV- en saneringswerkzaamheden Terneuzen en Sluiskil * More details: https://btd-planner.prorail.nl?taak=IO-M-004853-2301-00-6&doc=FOT (Register with ProRail)","M-004853","2022-01-17","Medium","","","Publication"]
["ProRail","M004853-2310-00","< >","Sloehaven empl.","Sloe-Thermfos",2023,2023,37,38,"2023-09-16","01:00:00","2023-09-18","05:00:00",2,"continuous","Track & Rail","T","LT","BBV-werkzaamheden Stamlijn WTC * More details: https://btd-planner.prorail.nl?taak=IO-M-004853-2310-00-2&doc=FOT (Register with ProRail)","M-004853","2022-04-08","Medium","","","Publication"]
["ProRail","M004853-2302-00","< >","Axel aansl.","Terneuzen Zuidzijde (racc.)",2023,2023,37,38,"2023-09-16","01:00:00","2023-09-18","05:00:00",2,"continuous","Track & Rail","T","LT","BBV- en saneringswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004853-2302-00-4&doc=FOT (Register with ProRail)","M-004853","2022-01-17","Medium","","","Publication"]
["ProRail","M004853-2303-00","< >","Sluiskil racc. Dow Chemical","Sas van Gent grens",2023,2023,38,39,"2023-09-23","01:00:00","2023-09-25","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV-werkzaamheden Sas van Gent * More details: https://btd-planner.prorail.nl?taak=IO-M-004853-2303-00-3&doc=FOT (Register with ProRail)","M-004853","2022-01-17","Medium","","","Publication"]
["ProRail","M004853-2306-00","< >","Lewedorp","Sloehaven empl.",2023,2023,39,40,"2023-09-30","23:00:00","2023-10-02","07:00:00",2,"continuous","Catenary","T","LT","rijdraadklemmen * More details: https://btd-planner.prorail.nl?taak=IO-M-004853-2306-00-2&doc=FOT (Register with ProRail)","M-004853","2022-04-08","Medium","","","Publication"]
["ProRail","M004853-2309-00","< >","Axel aansl.","Terneuzen Zuidzijde (racc.)",2023,2023,39,40,"2023-09-30","01:00:00","2023-10-02","05:00:00",2,"continuous","Track & Rail","T","LT","BBV- en saneringswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004853-2309-00-3&doc=FOT (Register with ProRail)","M-004853","2022-01-17","Medium","","","Publication"]
["ProRail","M004853-2305-00","< >","Sloehaven empl.","Sloe-Thermfos",2023,2023,40,41,"2023-10-07","01:00:00","2023-10-09","05:00:00",2,"continuous","Track & Rail","T","LT","BBV-werkzaamheden Stamlijn WTC * More details: https://btd-planner.prorail.nl?taak=IO-M-004853-2305-00-2&doc=FOT (Register with ProRail)","M-004853","2022-04-08","Medium","","","Publication"]
["ProRail","M004856-2401-00","< >","Meteren Betuweroute aansluiting Noord","'s-Hertogenbosch",2024,2024,43,44,"2024-10-26","01:00:00","2024-10-28","04:00:00",2,"continuous","Switch","T","LT+ST","Saneren 3de spoor en toe leidende wissels * More details: https://btd-planner.prorail.nl?taak=IO-M-004856-2401-00-3&doc=FOT (Register with ProRail)","M-004856","2022-11-11","Medium","99960, 00319, 00129, 00173, 00055","","Publication"]
["ProRail","M004864-2302-00","< >","Middelburg","Vlissingen",2023,2023,31,32,"2023-08-05","01:00:00","2023-08-07","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Vernieuwen waterleidingen * More details: https://btd-planner.prorail.nl?taak=IO-M-004864-2302-00-3&doc=FOT (Register with ProRail)","M-004864","2022-01-28","Medium","","","Publication"]
["ProRail","M004864-2301-00","< >","Middelburg","Vlissingen",2023,2023,37,38,"2023-09-16","01:00:00","2023-09-18","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Vernieuwen waterleidingen * More details: https://btd-planner.prorail.nl?taak=IO-M-004864-2301-00-3&doc=FOT (Register with ProRail)","M-004864","2022-03-24","Medium","","","Publication"]
["ProRail","M004886-2401-00","< >","Blerick","Eindhoven Centraal",2024,2024,10,12,"2024-03-09","01:00:00","2024-03-18","05:00:00",9,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004886-2401-00-3&doc=FOT (Register with ProRail)","M-004886","2022-11-09","High","","00748","Publication"]
["ProRail","M004886-2471-00","< >","Valkenburg","Maastricht",2024,2024,14,15,"2024-04-06","01:00:00","2024-04-08","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV Werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004886-2471-00-5&doc=FOT (Register with ProRail)","M-004886","2022-12-09","Medium","","","Coordination"]
["ProRail","M004896-2402-00","< >","Tilburg ind. terr.","Tilburg",2024,2024,22,23,"2024-06-01","01:00:00","2024-06-03","05:00:00",2,"continuous","Bridge","T","LT+ST","conserveren spoorbrug (stralen, ontroesten en 3 keer behandelen). * More details: https://btd-planner.prorail.nl?taak=IO-M-004896-2402-00-1&doc=FOT (Register with ProRail)","M-004896","2022-12-08","Medium","99960, 00055","","Coordination"]
["ProRail","M004896-2401-00","< >","Tilburg ind. terr.","Tilburg",2024,2024,32,33,"2024-08-10","01:00:00","2024-08-12","05:00:00",2,"continuous","Bridge","T","LT+ST","conserveren spoorbrug (stralen, ontroesten en 3 keer behandelen). * More details: https://btd-planner.prorail.nl?taak=IO-M-004896-2401-00-4&doc=FOT (Register with ProRail)","M-004896","2022-12-09","Medium","99960, 00055","","Coordination"]
["ProRail","M004896-2403-00","< >","Tilburg ind. terr.","Tilburg",2024,2024,44,45,"2024-11-02","01:00:00","2024-11-04","05:00:00",2,"continuous","Bridge","T","LT+ST","conserveren spoorbrug (stralen, ontroesten en 3 keer behandelen). * More details: https://btd-planner.prorail.nl?taak=IO-M-004896-2403-00-1&doc=FOT (Register with ProRail)","M-004896","2022-12-09","Medium","99960, 00055","","Coordination"]
["ProRail","M004898-2402-00","< >","Meteren Betuweroute aansluiting Zuid","'s-Hertogenbosch",2024,2024,43,44,"2024-10-26","01:00:00","2024-10-28","04:00:00",2,"continuous","Miscellaneous","T","LT+ST","Betreft spoorviaduct Zuider Waaldijk, herstellen lekkage vanuit bovendek * More details: https://btd-planner.prorail.nl?taak=IO-M-004898-2402-00-3&doc=FOT (Register with ProRail)","M-004898","2022-11-11","Medium","99960, 00319, 00129, 00173","","Publication"]
["ProRail","M004902-2406-00","< >","Breda aansl.","Roosendaal",2024,2024,9,10,"2024-03-02","01:00:00","2024-03-04","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2406-00-4&doc=FOT (Register with ProRail)","M-004902","2022-12-09","Medium","99960, 00055","","Coordination"]
["ProRail","M004902-2413-00","< >","Dordrecht","Roosendaal",2024,2024,11,12,"2024-03-16","01:00:00","2024-03-18","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2413-00-2&doc=FOT (Register with ProRail)","M-004902","2022-11-28","Medium","00526, 00129","00748","Coordination"]
["ProRail","M004902-2405-00","< >","Roosendaal","Goes",2024,2024,14,15,"2024-04-06","01:00:00","2024-04-08","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2405-00-4&doc=FOT (Register with ProRail)","M-004902","2022-11-08","Medium","","","Publication"]
["ProRail","M004902-2408-00","< >","Breda","Lage Zwaluwe",2024,2024,16,17,"2024-04-20","01:00:00","2024-04-22","05:00:00",2,"continuous","Switch","T","LT+ST","BBV werkzaamheden, vernieuwen wisselstellers en vervangen rijdraad * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2408-00-3&doc=FOT (Register with ProRail)","M-004902","2022-12-09","Medium","00129","00748","Coordination"]
["ProRail","M004902-2410-00","< >","Gilze-Rijen","Breda",2024,2024,18,19,"2024-05-04","01:00:00","2024-05-06","05:00:00",2,"continuous","Switch","T","LT","BBV werkzaamheden, vernieuwen wisselstellers en vervangen rijdraad * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2410-00-2&doc=FOT (Register with ProRail)","M-004902","2022-11-09","Medium","99960, 00129, 00055","00748","Publication"]
["ProRail","M004902-2412-00","< >","Dordrecht","Roosendaal",2024,2024,38,39,"2024-09-21","01:00:00","2024-09-23","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2412-00-2&doc=FOT (Register with ProRail)","M-004902","2022-11-10","Medium","00526, 00129","00748","Publication"]
["ProRail","M004902-2403-00","< >","Breda aansl.","Roosendaal",2024,2024,41,42,"2024-10-12","01:00:00","2024-10-14","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2403-00-2&doc=FOT (Register with ProRail)","M-004902","2022-11-28","Medium","99960, 00129, 00055","","Coordination"]
["ProRail","M004902-2409-00","< >","Breda","Lage Zwaluwe",2024,2024,41,42,"2024-10-12","01:00:00","2024-10-14","05:00:00",2,"continuous","Switch","T","LT+ST","BBV werkzaamheden, vernieuwen wisselstellers en vervangen rijdraad * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2409-00-3&doc=FOT (Register with ProRail)","M-004902","2022-12-08","Medium","00129","00748","Coordination"]
["ProRail","M004902-2407-00","< >","Breda","Roosendaal",2024,2024,42,43,"2024-10-19","01:00:00","2024-10-21","05:00:00",2,"continuous","Switch","T","LT+ST","BBV werkzaamheden, vernieuwen wisselstellers en vervangen rijdraad * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2407-00-4&doc=FOT (Register with ProRail)","M-004902","2022-12-09","Medium","","","Coordination"]
["ProRail","M004917-2401-00","< >","Lage Zwaluwe","Roosendaal",2024,2024,7,7,"2024-02-15","01:00:00","2024-02-17","05:00:00",2,"continuous","Catenary","T","LT+ST","Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2401-00-2&doc=FOT (Register with ProRail)","M-004917","2022-12-09","Medium","00526","","Coordination"]
["ProRail","M004917-2403-00","< >","Lage Zwaluwe","Roosendaal",2024,2024,11,13,"2024-03-16","05:00:00","2024-03-25","05:00:00",9,"continuous","Catenary","T","LT+ST","Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2403-00-3&doc=FOT (Register with ProRail)","M-004917","2022-11-28","High","00526","","Coordination"]
["ProRail","M004917-2402-00","< >","Lage Zwaluwe","Roosendaal",2024,2024,27,28,"2024-07-06","01:00:00","2024-07-08","05:00:00",2,"continuous","Catenary","T","LT+ST","Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2402-00-3&doc=FOT (Register with ProRail)","M-004917","2022-11-28","Medium","00526","","Coordination"]
["ProRail","M004917-2404-00","< >","Lage Zwaluwe","Roosendaal",2024,2024,38,40,"2024-09-21","05:00:00","2024-09-30","05:00:00",9,"continuous","Catenary","T","LT+ST","Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2404-00-4&doc=FOT (Register with ProRail)","M-004917","2022-11-10","High","00526","","Publication"]
["ProRail","M004937-2301-00","< >","Eindhoven Centraal","Acht",2024,2024,27,28,"2024-07-06","01:00:00","2024-07-08","05:00:00",2,"continuous","Tunnel","T","LT+ST","herstelwerkzaamheden aan kunstwerk * More details: https://btd-planner.prorail.nl?taak=IO-M-004937-2301-00-3&doc=FOT (Register with ProRail)","M-004937","2022-12-08","Medium","","00748","Coordination"]
["ProRail","M004942-2408-00","< >","Terneuzen","Sluiskil aansl.",2024,2024,10,11,"2024-03-09","01:00:00","2024-03-11","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004942-2408-00-3&doc=FOT (Register with ProRail)","M-004942","2022-11-08","Medium","","","Publication"]
["ProRail","M004942-2409-00","< >","Sluiskil racc. Dow Chemical","Sluiskil aansl.",2024,2024,11,12,"2024-03-16","01:00:00","2024-03-18","05:00:00",2,"continuous","Track & Rail","T","LT","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004942-2409-00-2&doc=FOT (Register with ProRail)","M-004942","2022-11-08","Medium","","","Publication"]
["ProRail","M004942-2411-00","< >","Sloehaven empl.","Sloe-Cobalfret",2024,2024,14,15,"2024-04-06","01:00:00","2024-04-08","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004942-2411-00-2&doc=FOT (Register with ProRail)","M-004942","2022-11-08","Medium","","","Publication"]
["ProRail","M004942-2410-00","< >","Moerdijk","Moerdijk",2024,2024,20,21,"2024-05-18","01:00:00","2024-05-20","05:00:00",2,"continuous","Track & Rail","T","ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004942-2410-00-2&doc=FOT (Register with ProRail)","M-004942","2022-11-25","Medium","","","Coordination"]
["ProRail","M004942-2416-00","< >","Vught aansl.","Tilburg",2024,2024,25,25,"2024-06-20","01:00:00","2024-06-22","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004942-2416-00-1&doc=FOT (Register with ProRail)","M-004942","2022-11-11","Medium","99960, 00055","","Publication"]
["ProRail","M004942-2401-00","< >","Vught aansl.","Boxtel",2024,2024,25,26,"2024-06-22","01:00:00","2024-06-24","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden. * More details: https://btd-planner.prorail.nl?taak=IO-M-004942-2401-00-2&doc=FOT (Register with ProRail)","M-004942","2022-11-11","Medium","00129","","Publication"]
["ProRail","M004942-2406-00","< >","Vught aansl.","Tilburg",2024,2024,25,26,"2024-06-22","01:00:00","2024-06-24","05:00:00",2,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004942-2406-00-7&doc=FOT (Register with ProRail)","M-004942","2022-11-11","Medium","99960, 00055","","Publication"]
["ProRail","M004942-2404-00","< >","Eindhoven Centraal","Boxtel",2024,2024,27,28,"2024-07-06","01:00:00","2024-07-09","05:00:00",3,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004942-2404-00-2&doc=FOT (Register with ProRail)","M-004942","2022-12-09","Medium","00129","01331, 00748","Coordination"]
["ProRail","M004943-2401-00","< >","Tilburg","Breda",2024,2024,17,20,"2024-04-28","01:00:00","2024-05-13","23:00:00",15,"continuous","Track & Rail","T","LT+ST","BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004943-2401-00-7&doc=FOT (Register with ProRail)","M-004943","2022-11-08","High","99960, 00129, 00055","00748","Publication"]
["ProRail","M004943-2402-00","< >","Boxtel","Tilburg aansl.",2024,2024,42,43,"2024-10-19","01:00:00","2024-10-26","09:00:00",7,"continuous","Track & Rail","T","LT+ST","BBV Werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004943-2402-00-4&doc=FOT (Register with ProRail)","M-004943","2022-11-15","High","00129","00748","Publication"]
["ProRail","R3AE009-2302-00","< >","Amsterdam Transformatorweg aansl.","Houtrakpolder aansl.(Amsterdam)",2023,2023,14,17,"2023-04-03","05:00:00","2023-04-26","09:00:00",23,"continuous","Miscellaneous","T","LT+ST","Aansluiten nieuw reizigersemplacement incl. derde spoor tbv het huidige goederenemplacement in de Amsterdamse Westhaven * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE009-2302-00-5&doc=FOT (Register with ProRail)","R-3AE009","2022-11-09","High","","","Publication"]
["ProRail","R3AE009-2303-00","< >","Singelgracht aansl.","Erasmusgracht aansl.",2023,2023,16,16,"2023-04-21","17:00:00","2023-04-23","01:00:00",2,"continuous","Miscellaneous","T","LT+ST","Aansluiten nieuw reizigersemplacement incl. derde spoor tbv het huidige goederenemplacement in de Amsterdamse Westhaven * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE009-2303-00-5&doc=FOT (Register with ProRail)","R-3AE009","2022-11-09","Medium","00530","","Publication"]
["ProRail","R3AE009-2304-00","< >","Amsterdam Centraal","Erasmusgracht aansl.",2023,2023,16,17,"2023-04-22","20:50:00","2023-04-24","04:50:00",2,"continuous","Miscellaneous","T","LT+ST","Aansluiten nieuw reizigersemplacement incl. derde spoor tbv het huidige goederenemplacement in de Amsterdamse Westhaven * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE009-2304-00-6&doc=FOT (Register with ProRail)","R-3AE009","2022-11-23","Medium","99960, 00129, 00173, 00621, 00530","","Publication"]
["ProRail","R3AE032-2401-00","< >","Dijksgracht Oostzijde (Amsterdam)","Overbrakerpolder aansl.",2024,2024,26,27,"2024-06-29","01:00:00","2024-07-02","05:00:00",3,"continuous","Miscellaneous","T","LT+ST","Stap 1i, buiten exploitatie nemen spoor 14+15 en indienststellen spoor 1 en 2a. * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE032-2401-00-6&doc=FOT (Register with ProRail)","R-3AE032","2022-10-24","Medium","99960, 00129, 00173, 00621, 00530, 00071","","Publication"]
["ProRail","R3BE001-2301-00","< >","Boxtel","Breda",2023,2023,32,33,"2023-08-07","01:00:00","2023-08-19","01:00:00",12,"continuous","Switch","T","LT+ST","Algehele functiewijziging empl. Tilburg (baan/spoor/bovenleiding/perron/K&L/wisselverwarming/beveiliging) * More details: https://btd-planner.prorail.nl?taak=IO-R-3BE001-2301-00-4&doc=FOT (Register with ProRail)","R-3BE001","2022-11-23","High","99960, 00129, 00055, 00747, 00071","01331, 00748","Publication"]
["ProRail","R3GZN02-2401-00","< >","Oss","Tilburg ind. terr.",2024,2024,25,26,"2024-06-18","01:00:00","2024-06-24","05:00:00",6,"continuous","Miscellaneous","T","LT+ST","PHS Den Bosch - Vught-uitvoering stap 0 saneren derde spoor * More details: https://btd-planner.prorail.nl?taak=IO-R-3GZN02-2401-00-2&doc=FOT (Register with ProRail)","R-3GZN02","2022-11-14","Medium","99960, 00129, 00173, 00055","00748","Publication"]
["ProRail","R3PB001-2318-00","< >","Sloehaven empl.","Sloehaven empl.",2023,2023,18,19,"2023-05-06","23:00:00","2023-05-08","07:00:00",2,"continuous","Miscellaneous","T","ST","Elektrificatie 2e spoorbundel Sloe * More details: https://btd-planner.prorail.nl?taak=IO-R-3PB001-2318-00-2&doc=FOT (Register with ProRail)","R-3PB001","2022-11-23","Medium","","","Publication"]
["ProRail","R3PB001-2320-00","< >","Lewedorp","Sloehaven empl.",2023,2023,20,21,"2023-05-20","01:00:00","2023-05-22","05:00:00",2,"continuous","Miscellaneous","T","LT","Elektrificatie 2e spoorbundel Sloe * More details: https://btd-planner.prorail.nl?taak=IO-R-3PB001-2320-00-2&doc=FOT (Register with ProRail)","R-3PB001","2022-12-07","Medium","","","Publication"]
["ProRail","R3PB001-2321-00","< >","Lewedorp","Sloehaven empl.",2023,2023,23,24,"2023-06-09","01:00:00","2023-06-12","05:00:00",3,"continuous","Miscellaneous","T","LT","Elektrificatie 2e spoorbundel Sloe * More details: https://btd-planner.prorail.nl?taak=IO-R-3PB001-2321-00-1&doc=FOT (Register with ProRail)","R-3PB001","2022-04-08","Medium","","","Publication"]
["ProRail","R3PB001-2322-00","< >","Lewedorp","Sloehaven empl.",2023,2023,24,25,"2023-06-17","23:00:00","2023-06-19","07:00:00",2,"continuous","Miscellaneous","T","LT","Elektrificatie 2e spoorbundel Sloe * More details: https://btd-planner.prorail.nl?taak=IO-R-3PB001-2322-00-1&doc=FOT (Register with ProRail)","R-3PB001","2022-04-08","Medium","","","Publication"]
["ProRail","R3PB001-2325-00","< >","Lewedorp","Sloehaven empl.",2023,2023,39,40,"2023-09-30","23:00:00","2023-10-02","07:00:00",2,"continuous","Catenary","T","LT","Aanleggen van BVL-Palen en Portalen en de voeding van het spoor wordt verzwaard. * More details: https://btd-planner.prorail.nl?taak=IO-R-3PB001-2325-00-1&doc=FOT (Register with ProRail)","R-3PB001","2022-04-08","Medium","","","Publication"]
["ProRail","R3PB001-2326-00","< >","Lewedorp","Sloehaven empl.",2023,2023,40,41,"2023-10-06","23:00:00","2023-10-09","07:00:00",3,"continuous","Miscellaneous","T","LT","Elektrificatie 2e spoorbundel Sloe * More details: https://btd-planner.prorail.nl?taak=IO-R-3PB001-2326-00-1&doc=FOT (Register with ProRail)","R-3PB001","2022-04-08","Medium","","","Publication"]
["ProRail","R429000-2301-00","< >","Duivendrecht aansluiting west","Amsterdam Riekerpolder aansl.",2023,2023,2,3,"2023-01-14","01:30:00","2023-01-16","05:30:00",2,"continuous","Miscellaneous","T","LT+ST","Aanbrengen damwand tussen M1 en T4 as 1-2 en as 4-5 * More details: https://btd-planner.prorail.nl?taak=IO-R-429000-2301-00-4&doc=FOT (Register with ProRail)","R-429000","2022-12-06","Medium","","","Publication"]
["ProRail","R429000-2306-00","< >","Duivendrecht aansluiting west","Amsterdam Riekerpolder aansl.",2023,2023,20,21,"2023-05-18","01:20:00","2023-05-22","05:20:00",4,"continuous","Miscellaneous","T","LT+ST","integrale projectwerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-R-429000-2306-00-3&doc=FOT (Register with ProRail)","R-429000","2022-12-07","Medium","00530","","Publication"]
["ProRail","R429000-2309-00","< >","Duivendrecht aansluiting west","Amsterdam Riekerpolder aansl.",2023,2023,26,27,"2023-07-01","01:00:00","2023-07-03","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Aanbrengen grondkeringen onderdeks BP-T4 t/m BP-M1. * More details: https://btd-planner.prorail.nl?taak=IO-R-429000-2309-00-2&doc=FOT (Register with ProRail)","R-429000","2021-11-08","Medium","00530","","Publication"]
["ProRail","R466300-2301-00","< >","Kragge aansl.","Kruiningen-Yerseke",2023,2023,23,24,"2023-06-09","01:00:00","2023-06-12","05:00:00",3,"continuous","Miscellaneous","T","LT+ST","GLS KM12.700-13.200. SPL werkplek A: 8672, 8674, 8676, 8700, 8718. SPL-B: 8672, 8674, 8675, 8677, 8700, 8701, 8717, 8718 * More details: https://btd-planner.prorail.nl?taak=IO-R-466300-2301-00-3&doc=FOT (Register with ProRail)","R-466300","2022-01-28","Medium","","","Publication"]
["ProRail","R472500-2401-00","< >","Blerick","Gekkengraaf West aansl.",2024,2024,10,11,"2024-03-09","01:00:00","2024-03-11","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Realiseren van een lift naar perron 1 en een lift naar perron 2. * More details: https://btd-planner.prorail.nl?taak=IO-R-472500-2401-00-2&doc=FOT (Register with ProRail)","R-472500","2022-11-07","Medium","","00748","Publication"]
["ProRail","R472500-2402-00","< >","Blerick","Gekkengraaf West aansl.",2024,2024,11,12,"2024-03-16","01:00:00","2024-03-18","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Realiseren van een lift naar perron 1 en een lift naar perron 2. plaatsen liftschachten * More details: https://btd-planner.prorail.nl?taak=IO-R-472500-2402-00-3&doc=FOT (Register with ProRail)","R-472500","2022-11-07","Medium","","00748","Publication"]
["ProRail","R472600-2401-00","< >","Venserpolder aansl.","Duivendrecht aansluiting west",2024,2024,43,44,"2024-10-26","01:00:00","2024-10-28","04:00:00",2,"continuous","Miscellaneous","T","LT+ST","Plaatsen liftschacht * More details: https://btd-planner.prorail.nl?taak=IO-R-472600-2401-00-2&doc=FOT (Register with ProRail)","R-472600","2022-11-09","Medium","00621","","Publication"]
["ProRail","R485230-2402-00","< >","Keverdijk","Watergraafsmeer Oost aansl.",2024,2024,1,2,"2024-01-06","01:00:00","2024-01-08","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","plaatsen geluidsschermen * More details: https://btd-planner.prorail.nl?taak=IO-R-485230-2402-00-1&doc=FOT (Register with ProRail)","R-485230","2022-11-07","Medium","00173, 00055, 00747, 00621","","Publication"]
["ProRail","R520020-2301-00","< >","Keverdijk","Amsterdam Riekerpolder aansl.",2023,2023,9,10,"2023-03-04","01:36:00","2023-03-06","05:36:00",2,"continuous","Tunnel","T","LT+ST","ODG Diemen. Verwijderen OVW 6.7 (incl.wijzigen EBP 1 & 5) * More details: https://btd-planner.prorail.nl?taak=IO-R-520020-2301-00-2&doc=FOT (Register with ProRail)","R-520020","2022-11-09","Medium","00173","","Publication"]
["ProRail","R520030-2301-00","< >","Venlo grens","Tegelen",2023,2023,41,42,"2023-10-14","01:00:00","2023-10-16","05:00:00",2,"continuous","Tunnel","T","LT+ST","Aanpassingen aan de OVW Vierpaardjes/Broekestraat * More details: https://btd-planner.prorail.nl?taak=IO-R-520030-2301-00-2&doc=FOT (Register with ProRail)","R-520030","2022-08-04","Medium","","00748","Publication"]
["ProRail","R540400-2301-00","< >","Gilze-Rijen","Breda",2023,2023,33,33,"2023-08-14","01:00:00","2023-08-18","05:00:00",4,"continuous","Miscellaneous","T","LT","Het inrijden of inschuiven van de voorgebouwde spoorkruisende tunnelmoot  ODG Oosterhoutseweg N631 * More details: https://btd-planner.prorail.nl?taak=IO-R-540400-2301-00-2&doc=FOT (Register with ProRail)","R-540400","2022-03-01","Medium","99960, 00129, 00173, 00055, 00747","00748","Publication"]
["ProRail","R540400-2401-00","< >","Tilburg Universiteit","Breda",2024,2024,35,36,"2024-08-31","01:00:00","2024-09-02","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Het definitief saneren van de tijdelijke  overweg Oosterhoutsweg N631 en het realiseren van een Railinzetplaats (RIP) * More details: https://btd-planner.prorail.nl?taak=IO-R-540400-2401-00-2&doc=FOT (Register with ProRail)","R-540400","2022-12-09","Medium","99960, 00129, 00055","00748","Coordination"]
["ProRail","R551400-2301-00","< >","Lage Zwaluwe","Moerdijk",2024,2024,31,32,"2024-08-03","01:00:00","2024-08-05","05:00:00",2,"continuous","Miscellaneous","T","LT","Aansluiten nieuwe opstelsporen inclusief inbouwen wissels * More details: https://btd-planner.prorail.nl?taak=IO-R-551400-2301-00-3&doc=FOT (Register with ProRail)","R-551400","2022-11-25","Medium","","","Coordination"]
["ProRail","R551400-2303-00","< >","Lage Zwaluwe","Moerdijk",2024,2024,34,35,"2024-08-24","01:00:00","2024-08-26","05:00:00",2,"continuous","Miscellaneous","T","LT","Aansluiten nieuwe opstelsporen en vernieuwen sporen * More details: https://btd-planner.prorail.nl?taak=IO-R-551400-2303-00-3&doc=FOT (Register with ProRail)","R-551400","2022-11-25","Medium","","","Coordination"]
["ProRail","R557700-2401-00","< >","Meteren Betuweroute aansluiting Noord","'s-Hertogenbosch",2024,2024,43,44,"2024-10-26","17:00:00","2024-10-28","04:00:00",2,"continuous","Miscellaneous","T","LT+ST","- Aanleggen Hoogspanningskabels - Plaatsen 4x bovenleidingsschakelaars - Aansluiten 4x pluskabels - Aansluiten minkabels * More details: https://btd-planner.prorail.nl?taak=IO-R-557700-2401-00-2&doc=FOT (Register with ProRail)","R-557700","2022-11-11","Medium","99960, 00319, 00129, 00173","","Publication"]
["ProRail","R557800-2401-00","< >","Boxtel","Tilburg aansl.",2024,2024,43,43,"2024-10-21","05:00:00","2024-10-23","09:00:00",2,"continuous","Miscellaneous","T","LT+ST","IO 1: aansluiten van het nieuwe OS Haaren afkoppelen van bestaand SS Haaren * More details: https://btd-planner.prorail.nl?taak=IO-R-557800-2401-00-2&doc=FOT (Register with ProRail)","R-557800","2022-09-23","Medium","00129","00748","Publication"]
["ProRail","R557800-2402-00","< >","Boxtel","Tilburg aansl.",2024,2024,43,43,"2024-10-23","09:00:00","2024-10-25","13:00:00",2,"continuous","Miscellaneous","T","LT+ST","Afvoeren van het oude schakelstation Haaren * More details: https://btd-planner.prorail.nl?taak=IO-R-557800-2402-00-2&doc=FOT (Register with ProRail)","R-557800","2022-09-23","Medium","00129","00748","Publication"]
["ProRail","R561400-2302-00","< >","Kragge aansl.","Goes",2023,2023,12,13,"2023-03-25","00:25:00","2023-03-27","05:25:00",2,"continuous","Miscellaneous","T","LT+ST","Het aanbrengen van assentellers * More details: https://btd-planner.prorail.nl?taak=IO-R-561400-2302-00-3&doc=FOT (Register with ProRail)","R-561400","2022-11-23","Medium","","","Publication"]
["ProRail","R561800-2350-00","< >","Amersfoort Centraal","Blauwkapel Oost aansl.",2023,2023,30,31,"2023-07-26","01:00:00","2023-07-31","05:00:00",5,"continuous","Miscellaneous","T","LT+ST","integraal onderhoud * More details: https://btd-planner.prorail.nl?taak=IO-R-561800-2350-00-2&doc=FOT (Register with ProRail)","R-561800","2022-12-13","Medium","00319, 00173","","Publication"]
["ProRail","R562500-2403-00","< >","Almelo","Nijverdal",2024,2024,39,40,"2024-09-28","01:00:00","2024-09-30","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Diverse wijzigen op het baanvak Zwolle-Wierden en emplacement Wierden t.b.v. versnellen IC Zl-Es * More details: https://btd-planner.prorail.nl?taak=IO-R-562500-2403-00-3&doc=FOT (Register with ProRail)","R-562500","2022-12-16","Medium","","00748","Publication"]
["ProRail","R562500-2405-00","< >","Raalte","Raalte",2024,2024,40,41,"2024-09-30","01:00:00","2024-10-09","05:00:00",9,"continuous","Miscellaneous","T","ST","Diverse wijzigen op het baanvak Zwolle-Wierden en emplacement Wierden t.b.v. versnellen IC Zl-Es * More details: https://btd-planner.prorail.nl?taak=IO-R-562500-2405-00-2&doc=FOT (Register with ProRail)","R-562500","2022-12-08","High","","","Coordination"]
["ProRail","R562500-2402-00","< >","Almelo","Nijverdal",2024,2024,40,41,"2024-09-30","01:00:00","2024-10-09","05:00:00",9,"continuous","Miscellaneous","T","LT+ST","Diverse wijzigen op het baanvak Zwolle-Wierden en emplacement Wierden t.b.v. versnellen IC Zl-Es * More details: https://btd-planner.prorail.nl?taak=IO-R-562500-2402-00-2&doc=FOT (Register with ProRail)","R-562500","2022-12-16","High","","00748","Publication"]
["ProRail","R562500-2404-00","< >","Almelo","Nijverdal",2024,2024,41,41,"2024-10-09","01:00:00","2024-10-11","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Diverse wijzigen op het baanvak Zwolle-Wierden en emplacement Wierden t.b.v. versnellen IC Zl-Es * More details: https://btd-planner.prorail.nl?taak=IO-R-562500-2404-00-1&doc=FOT (Register with ProRail)","R-562500","2022-12-16","Medium","","00748","Publication"]
["ProRail","R577100-2302-00","< >","Amsterdam Muiderpoort","Amsterdam Centraal",2023,2023,24,25,"2023-06-16","01:00:00","2023-06-19","05:00:00",3,"continuous","Miscellaneous","T","LT+ST","Aanbrengen Fietsonderdoorgang Kattenburg * More details: https://btd-planner.prorail.nl?taak=IO-R-577100-2302-00-2&doc=FOT (Register with ProRail)","R-577100","2022-04-11","Medium","99960, 00129, 00173, 00621, 00530","","Publication"]
["ProRail","R578800-BD01-00","< >","Europoort","Maasvlakte aansl.",2023,2023,11,12,"2023-03-18","23:00:00","2023-03-20","07:00:00",2,"continuous","Miscellaneous","T","LT+ST","K&L-strook Moezelweg * More details: https://btd-planner.prorail.nl?taak=IO-R-578800-BD01-00-2&doc=FOT (Register with ProRail)","R-578800","2022-11-21","Medium","","","Publication"]
["ProRail","R578800-BD02-00","< >","Europoort","Maasvlakte aansl.",2023,2023,14,15,"2023-04-08","19:00:00","2023-04-10","23:00:00",2,"continuous","Miscellaneous","T","LT+ST","K&L-strook Moezelweg * More details: https://btd-planner.prorail.nl?taak=IO-R-578800-BD02-00-2&doc=FOT (Register with ProRail)","R-578800","2022-11-21","Medium","","","Publication"]
["ProRail","R578800-BD03-00","< >","Europoort","Maasvlakte aansl.",2023,2023,21,22,"2023-05-27","19:00:00","2023-05-29","23:00:00",2,"continuous","Miscellaneous","T","LT+ST","K&L-strook Moezelweg * More details: https://btd-planner.prorail.nl?taak=IO-R-578800-BD03-00-1&doc=FOT (Register with ProRail)","R-578800","2022-12-14","Medium","","","Publication"]
["ProRail","R579600-2401-00","< >","Boxtel","Tilburg aansl.",2024,2024,42,43,"2024-10-19","01:00:00","2024-10-21","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","wijzigen overweg D'Ekker * More details: https://btd-planner.prorail.nl?taak=IO-R-579600-2401-00-2&doc=FOT (Register with ProRail)","R-579600","2022-09-23","Medium","00129","00748","Publication"]
["ProRail","R579600-2402-00","< >","Boxtel","Tilburg aansl.",2024,2024,43,43,"2024-10-21","05:00:00","2024-10-23","09:00:00",2,"continuous","Miscellaneous","T","LT+ST","wijzigen overweg Kapelweg * More details: https://btd-planner.prorail.nl?taak=IO-R-579600-2402-00-2&doc=FOT (Register with ProRail)","R-579600","2022-09-23","Medium","00129","00748","Publication"]
["ProRail","R583600-2301-00","< >","Oldenzaal Grens","Hengelo",2023,2023,44,45,"2023-11-04","02:00:00","2023-11-06","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Bouwen nieuw kopspoor op station Oldenzaal * More details: https://btd-planner.prorail.nl?taak=IO-R-583600-2301-00-2&doc=FOT (Register with ProRail)","R-583600","2022-11-28","Medium","","00748","Publication"]
["ProRail","R583600-2303-00","< >","Oldenzaal Grens","Hengelo",2023,2023,46,47,"2023-11-17","01:00:00","2023-11-20","05:00:00",3,"continuous","Miscellaneous","T","LT+ST","Bouwen nieuw kopspoor op station Oldenzaal * More details: https://btd-planner.prorail.nl?taak=IO-R-583600-2303-00-1&doc=FOT (Register with ProRail)","R-583600","2022-11-28","Medium","","00748","Publication"]
["ProRail","Z9ODB01-2301-00","< >","Zevenbergen inhaalsp.","Roosendaal",2023,2023,39,40,"2023-09-30","05:00:00","2023-10-02","09:00:00",2,"continuous","Miscellaneous","T","LT+ST","Oudenbosch vervangen keerwanden en straatwerk zij- en eilandperron * More details: https://btd-planner.prorail.nl?taak=IO-Z-9ODB01-2301-00-2&doc=FOT (Register with ProRail)","Z-9ODB01","2022-02-04","Medium","00526","","Publication"]
["ProRail","Z9ODB01-2302-00","< >","Zevenbergen inhaalsp.","Roosendaal",2023,2023,40,40,"2023-10-02","09:00:00","2023-10-04","13:00:00",2,"continuous","Miscellaneous","T","LT+ST","Oudenbosch vervangen keerwanden en straatwerk zij- en eilandperron * More details: https://btd-planner.prorail.nl?taak=IO-Z-9ODB01-2302-00-1&doc=FOT (Register with ProRail)","Z-9ODB01","2022-02-04","Medium","00526","","Publication"]
["ProRail","Z9ODB01-2303-00","< >","Zevenbergen inhaalsp.","Roosendaal",2023,2023,40,40,"2023-10-04","13:00:00","2023-10-06","17:00:00",2,"continuous","Miscellaneous","T","LT+ST","Oudenbosch vervangen keerwanden en straatwerk zij- en eilandperron * More details: https://btd-planner.prorail.nl?taak=IO-Z-9ODB01-2303-00-1&doc=FOT (Register with ProRail)","Z-9ODB01","2022-02-04","Medium","00526","","Publication"]
["ProRail","Z9TBR01-2302-00","< >","Tilburg","Gilze-Rijen",2023,2023,32,33,"2023-08-11","21:00:00","2023-08-14","01:00:00",3,"continuous","Miscellaneous","T","LT+ST","Aanpassing spoorligging t.p.v. de beide perrons zodat er toegankelijke instap ontstaat (P76) * More details: https://btd-planner.prorail.nl?taak=IO-Z-9TBR01-2302-00-1&doc=FOT (Register with ProRail)","Z-9TBR01","2022-02-15","Medium","99960, 00129, 00055","00748","Publication"]
["ProRail","Z9TBR01-2301-00","< >","Tilburg","Gilze-Rijen",2023,2023,32,32,"2023-08-09","21:00:00","2023-08-12","01:00:00",3,"continuous","Miscellaneous","T","LT+ST","Aanpassing spoorligging t.p.v. de beide perrons zodat er toegankelijke instap ontstaat (P76) * More details: https://btd-planner.prorail.nl?taak=IO-Z-9TBR01-2301-00-1&doc=FOT (Register with ProRail)","Z-9TBR01","2022-06-10","Medium","99960, 00129, 00055","00748","Publication"]
["ProRail","Z9TWL01-2414-00","< >","Deventer","Apeldoorn aansl.",2024,2024,6,7,"2024-02-10","01:00:00","2024-02-12","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Aanpassen perronhoogte, vernieuwen outillage en aanpassen hellingbaan N-zijde, * More details: https://btd-planner.prorail.nl?taak=IO-Z-9TWL01-2414-00-3&doc=FOT (Register with ProRail)","Z-9TWL01","2022-12-07","Medium","","","Coordination"]
["ProRail","Z180000-24A4-00","< >","Apeldoorn","Amersfoort aansl.",2024,2024,14,15,"2024-04-06","01:00:00","2024-04-08","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Saneren van de dateq in de kast en realiseren van DOSS 2.0 * More details: https://btd-planner.prorail.nl?taak=IO-Z-180000-24A4-00-3&doc=FOT (Register with ProRail)","Z-180000","2022-12-14","Medium","00173, 00055","","Publication"]
["ProRail","Z180000-24A3-00","< >","Wierden","Snippeling aansl.",2024,2024,41,41,"2024-10-09","01:00:00","2024-10-11","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","Saneren van de dateq in de kast en realiseren van DOSS 2.0 * More details: https://btd-planner.prorail.nl?taak=IO-Z-180000-24A3-00-2&doc=FOT (Register with ProRail)","Z-180000","2022-12-07","Medium","","00748","Coordination"]
["ProRail","Z180001-2301-00","< >","Rotterdam Stadion","Rotterdam Centraal",2023,2023,5,6,"2023-02-04","01:10:00","2023-02-06","05:10:00",2,"continuous","Miscellaneous","T","LT+ST","aanpassing besturings systeem Willemsspoortunnel * More details: https://btd-planner.prorail.nl?taak=IO-Z-180001-2301-00-2&doc=FOT (Register with ProRail)","Z-180001","2022-12-16","Medium","00173, 00055, 00747, 00530","","Publication"]
["ProRail","Z180023-s102-00","< >","Apeldoorn","Den Dolder",2024,2024,29,30,"2024-07-20","09:00:00","2024-07-24","05:00:00",4,"continuous","Miscellaneous","T","LT+ST","overnemen bestaande IXL naar nieuwe IXL, indienststellen nieuwe IXL * More details: https://btd-planner.prorail.nl?taak=IO-Z-180023-s102-00-5&doc=FOT (Register with ProRail)","Z-180023","2022-11-22","Medium","00319, 00173, 00747","","Publication"]
["ProRail","Z180023-s202-00","< >","Apeldoorn","Den Dolder",2024,2024,34,35,"2024-08-24","06:00:00","2024-08-26","02:00:00",2,"continuous","Miscellaneous","T","LT+ST","aansluiten spoor 1 t/m 6 conform eindsituatie. opbreken noodperron spoor 8. veegwerkzaamheden. * More details: https://btd-planner.prorail.nl?taak=IO-Z-180023-s202-00-4&doc=FOT (Register with ProRail)","Z-180023","2022-11-22","Medium","00319, 00173, 00747","","Publication"]
["ProRail","Z906258-2401-00","< >","Vught aansl.","Liempde",2024,2024,25,26,"2024-06-22","01:00:00","2024-06-24","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","onderhoudswerkzaamheden/ conserveren perronkap * More details: https://btd-planner.prorail.nl?taak=IO-Z-906258-2401-00-5&doc=FOT (Register with ProRail)","Z-906258","2022-11-11","Medium","00129","","Publication"]
["ProRail","Z906258-2402-00","< >","Liempde","Tilburg aansl.",2024,2024,42,43,"2024-10-19","01:00:00","2024-10-21","05:00:00",2,"continuous","Miscellaneous","T","LT+ST","onderhoudswerkzaamheden/ conserveren perronkap * More details: https://btd-planner.prorail.nl?taak=IO-Z-906258-2402-00-3&doc=FOT (Register with ProRail)","Z-906258","2022-11-11","Medium","","","Publication"]

{"sheet":"Infrabel","index":3,"n_rows":3468,"n_cols":18,"rows_kept":3468,"cut":false,"hidden":false,"merged":[]}
["date_begin","date_end","area","phase","line","tracks","section_from","section_to","period","period_type","Time Begin","Time End","description_of_works","impact","TCR Type","traffic_impact","Traffic Adaptation Freight","cou_id"]
["2023-09-02","2024-02-12","NW",1,"50A","*","AALTER","AALTER","AllWeek","Continuous","01:40","04:00","R-408245\r\nFasering Aalter spoor I aansluiting op L50D spoor B","Autre","Minor_AdHoc",null," ",46456]
["2023-09-04","2023-12-22","NE",1,"27A","*","ANTWERPEN-NOORD-INRIT C1","ANTWERPEN-NOORD-INRIT C1","AllWeek","Continuous","06:00","18:00","LANGE TLO 3weken: Vernieuwing wissels bundelkop C1 + verbinding tussen C1-C2.\r\nbuiten diensstelling tussen Antwerpen-noord uitrit C1 en  Antwerpen-noord Blok 9 rooster J\r\nWerkgroep wordt opgestart; zie dossier 20210203_2023 - L27A Antwerpen-Noord-C2-N_v","CTL","Major"," "," ",40219]
["2023-09-18","2023-12-18","SE",1,"162","A","LEIGNON","HAVERSIN","AllWeek","Continuous","06:00","05:00","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 10\r\nfinalisation des travaux","SAVU_CTRL","High","SAVU continu + CTL nuits: 23h15-04h50"," ",33286]
["2023-11-06","2023-12-20","SE",1,"162","A","MARLOIE","ROCHEFORT-JEMELLE","AllWeek","Continuous","04:00","04:20","Aménagement de la gare MARLOIE  - Phase 14: \t\r\nMHS de la voie A (voie II) en continu avec le cc 26259 + 26257 (placement de l’isolateur définitif pour le nouveau sectionnement au pied de la TJD 02AC/01BC)\r\nDépose des bordures et ripage de la voie II\r\nUP","SAVU_CTRL","High","La voie I en cds\r\nLa voie II hors service ."," ",51971]
["2023-12-04","2024-12-20","SE",1,"162","B","GRUPONT","HATRIVAL","AllWeek","Continuous","06:00","22:00","Grupont - Hatrival : phase 11\r\nVoie B HS= UPM 418401\r\nVoie A HS (CTL) = UPM : S 49/2023= 418414, S50/2023=418415, S51/2023= 418416, S52/2023=418418, S01/2024=418420, S02/2024=418421, S03/2024=418422,\r\nS04/2024=418423, S05/2024=418425, S06/2024=418426, S","SAVU_CTRL","High","CTL de 22h10 à 5h15"," ",19764]
["2023-12-04","2024-12-20","SE",1,"162","B","GRUPONT","HATRIVAL","AllWeek","Continuous","06:00","22:00","Grupont - Hatrival : phase 11\r\nVoie B HS= UPM 418401\r\nVoie A HS (CTL) = UPM : S 49/2023= 418414, S50/2023=418415, S51/2023= 418416, S52/2023=418418, S01/2024=418420, S02/2024=418421, S03/2024=418422,\r\nS04/2024=418423, S05/2024=418425, S06/2024=418426, S","SAVU_CTRL","High","CTL de 22h10 à 5h15"," ",19764]
["2023-12-11","2023-12-15","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Week","Night","23:50","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Minor_AdHoc","alternatief E1996-EM3372-E1972-E1995"," ",58205]
["2023-12-11","2023-12-15","NE",2,"53A","A+B","MECHELEN","MECHELEN","Week","Night","00:00","04:00","masterplan mechelen\r\nperronsporen 5+6 (met L27,L53)","CTL","Minor_AdHoc"," "," ",58277]
["2023-12-11","2023-12-15","NW",2,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","00:20","04:10","Linked to coupure nr 52895 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: R-405114\r\nMasterplan Gent\r\nStap 31: afbraak perronspoor 4 + 5\r\nL50E Y West Driehoek Ledeberg Niet inbegrepen, SP I tot VIII wel inbegrepen\r\nB/L50 FG","SAVU","Minor_AdHoc"," "," ",52895]
["2023-12-11","2023-12-15","NW",2,"50A/6","A+B","GENT-SINT-PIETERS","GENT-ROOSTER SNEPBRUG","Week","Night","00:20","04:10","Linked to coupure nr 52895 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: R-405114\r\nMasterplan Gent\r\nStap 31: afbraak perronspoor 4 + 5\r\nL50E Y West Driehoek Ledeberg Niet inbegrepen, SP I tot VIII wel inbegrepen\r\nB/L50 FG","CTL","Minor_AdHoc"," "," ",52895]
["2023-12-11","2023-12-15","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Week","Night","00:20","04:10","R-405114\r\nMasterplan Gent\r\nStap 31: afbraak perronspoor 4 + 5\r\nL50E Y West Driehoek Ledeberg Niet inbegrepen, SP I tot VIII wel inbegrepen\r\nB/L50 FGSP - Y West Driehoek Ledeberg vrij\r\nA/L50 tot AW 18BH vrij\r\nA+B/L50A6 FGSP - Y Snepbrug vrij\r\nA+B/L75 FGS","CTL","Minor_AdHoc",null," ",52895]
["2023-12-11","2023-12-15","NW",2,"75","A+B","GENT-SINT-PIETERS","DE PINTE","Week","Night","00:20","04:10","Linked to coupure nr 52895 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: R-405114\r\nMasterplan Gent\r\nStap 31: afbraak perronspoor 4 + 5\r\nL50E Y West Driehoek Ledeberg Niet inbegrepen, SP I tot VIII wel inbegrepen\r\nB/L50 FG","CTL","Minor_AdHoc"," "," ",52895]
["2023-12-11","2024-04-01","SW",1,"124","*","CHARLEROI-SUD","CHARLEROI-SUD","AllWeek","Continuous","06:00","06:00","Linked to coupure nr 27207 on line 130 tracks(s) * from CHARLEROI-SUD to CHARLEROI-SUD: CSV Charleroi - Phase 8\r\nVoies IV HS et voie III en CDS en continu - Période de travail:  08/01/24 - 17/03/24\r\nTravaux SNCB","Autre","Minor_AdHoc"," "," ",27207]
["2023-12-11","2024-04-01","SW",1,"130","*","CHARLEROI-SUD","CHARLEROI-SUD","AllWeek","Continuous","06:00","06:00","CSV Charleroi - Phase 8\r\nVoies IV HS et voie III en CDS en continu - Période de travail:  08/01/24 - 17/03/24\r\nTravaux SNCB","Autre","Minor_AdHoc",null," ",27207]
["2023-12-12","2023-12-15","NE",2,"53","A+B","MECHELEN","Y.HEIKE","Week","Night","00:05","04:00","masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6","CTL","Minor_AdHoc"," "," ",58315]
["2023-12-15","2023-12-18","NW",2,"75","A+B","DE PINTE","WAREGEM","Weekend","Continuous","20:00","04:10","IDS SIW  Deinze\r\ntestritten op zondag in overleg met regelaar\r\nuitwijk testloco in bundel Deinze","CTL","Medium"," "," ",49945]
["2023-12-16","2023-12-18","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:05","04:00","Linked to coupure nr 60341 on line 53 tracks(s) A+B from MECHELEN to Y.HEIKE: masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6","CTL","Medium"," "," ",60341]
["2023-12-16","2023-12-18","NE",2,"53","A+B","MECHELEN","Y.HEIKE","Weekend","Continuous","00:05","04:00","masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6","CTL","Medium"," "," ",60341]
["2023-12-16","2023-12-18","NE",2,"53A","A+B","MECHELEN","MECHELEN","Weekend","Continuous","00:00","04:00","masterplan mechelen\r\nperronsporen 5+6 (met L27,L53)","CTL","Medium"," "," ",58278]
["2023-12-16","2023-12-18","SW",1,"124","A+B","LUTTRE","ROUX","Weekend","Continuous","06:00","04:20","Aménagement de la transversale Sud de Luttre\r\nPose de grandes traverses + équipements\r\nWE 4 voies\r\nUPM : 417706","CTL","Medium","CTL L124 + L124A + voie 5 + CDS 164","HKM à adapter",50110]
["2023-12-16","2023-12-18","SW",1,"124A","A+B","ROUX","LUTTRE","Weekend","Continuous","06:00","04:20","Linked to coupure nr 50110 on line 124 tracks(s) A+B from LUTTRE to ROUX: Aménagement de la transversale Sud de Luttre\r\nPose de grandes traverses + équipements\r\nWE 4 voies\r\nUPM : 417706","CTL","Medium"," ","HKM à adapter",50110]
["2023-12-16","2023-12-17","SE",3,"161","A/B","NAMUR","RHISNES-SAS","Weekend","Day","08:00","16:00","Visite périodique + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","Savu alternatif VA/VB , de 8h à 16 h",null,46001]
["2023-12-17","2023-12-17","NW",2,"50","A+B","DENDERLEEUW","EREMBODEGEM","Weekend","Night","00:10","04:40","R-409627\r\nMasterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57734]
["2023-12-17","2023-12-17","NW",2,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Night","00:10","04:40","Linked to coupure nr 57734 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: R-409627\r\nMasterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57734]
["2023-12-17","2023-12-17","NW",2,"89","A+B","DENDERLEEUW","BURST","Weekend","Night","00:10","04:40","Linked to coupure nr 57734 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: R-409627\r\nMasterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57734]
["2023-12-18","2024-04-08","SE",1,"162","A","LEIGNON","HAVERSIN","AllWeek","Continuous","05:00","05:00","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 10\r\nfinalisation des travaux","SAVU_CTRL","High","SAVU continu + CTL nuits: 21:50-04:50"," ",58230]
["2024-01-01","2024-01-06","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59844]
["2024-01-01","2024-12-31","NE",1,"211C","S","Y.KROMMENHOEK","Y.ARENBERG","AllWeek","Continuous","00:05","23:55","Project Havenbedrijf: Westelijke ontsluiting (extra containercapaciteit Antwerpen).\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk\r\n\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinh","CTL","Major","herlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk\r\n\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","Info Racc",49860]
["2024-01-01","2024-12-31","NE",1,"211C","S","Y.KROMMENHOEK","Y.ARENBERG","AllWeek","Continuous","00:05","23:55","Project Havenbedrijf: Westelijke ontsluiting (extra containercapaciteit Antwerpen).\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk\r\n\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinh","CTL","Major","herlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk\r\n\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","Info Racc",49860]
["2024-01-03","2024-01-03","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60086]
["2024-01-03","2024-01-08","NW",1,"75","A+B","GENT-SINT-PIETERS","WAREGEM","AllWeek","Continuous","22:00","04:00","Backup IDS weekend\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\n\r\nFGSP NIET IN\r\nFVG bereikbaar kant Kortrijk","CTL","Medium",null," ",52980]
["2024-01-03","2024-01-08","NW",1,"86","A+B","GAVERE-ASPER","DE PINTE","AllWeek","Continuous","22:00","04:00","Linked to coupure nr 52980 on line 75 tracks(s) A+B from GENT-SINT-PIETERS to WAREGEM: Backup IDS weekend\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\n","CTL","Medium"," "," ",52980]
["2024-01-05","2024-01-08","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59550]
["2024-01-05","2024-01-08","NE",2,"34","A+B","GLONS","HASSELT","Weekend","Continuous","23:30","04:00","onderhoud +vernieuwen van OW\r\n+\r\nafschaffen 7 overwegen Bilzen\r\n\r\nUPM : 429154","CTL","Medium"," "," ",59351]
["2024-01-05","2024-01-08","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 min"," ",48629]
["2024-01-06","2024-01-06","SE",3,"130","A/B","FLAWINNE","MOUSTIER","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",37868]
["2024-01-06","2024-01-07","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60417]
["2024-01-06","2024-01-07","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60417 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60417]
["2024-01-06","2024-01-07","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60417 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60417]
["2024-01-06","2024-01-08","SE",2,"27","A+B","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL","Weekend","Continuous","06:00","04:00","migratie tunnelveiligheidstechnieken antw NZ","CTL","Medium"," "," ",59035]
["2024-01-06","2024-01-07","SE",3,"161","A/B","GEMBLOUX","RHISNES","Weekend","Day","08:00","16:00","Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49188]
["2024-01-07","2024-01-07","NW",2,"50","A+B","DENDERLEEUW","EREMBODEGEM","Weekend","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57735]
["2024-01-07","2024-01-07","NW",2,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Night","00:10","04:40","Linked to coupure nr 57735 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57735]
["2024-01-07","2024-01-07","NW",2,"89","A+B","DENDERLEEUW","BURST","Weekend","Night","00:10","04:40","Linked to coupure nr 57735 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57735]
["2024-01-07","2024-01-07","SE",3,"130","A/B","MOUSTIER","AUVELAIS","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",37876]
["2024-01-08","2024-01-12","CE",2,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","Week","Night","23:45","04:50","Onderhoudszone FBMZ_19, FBKI_03 en FH_06 Area CE volgens onderhoudskalender 2024\r\n\r\nSporen A en B 124 buiten dienst, inclusief L28/3","CTL","Minor_AdHoc",null," ",59509]
["2024-01-08","2024-01-13","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59845]
["2024-01-08","2024-01-13","NE",3,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","(vide)","(vide)","23:55","04:50","Linked to coupure nr 62632 on line 53 tracks(s) A+B from Y.HEIKE to MUIZEN: Rooster M+N. Werken ikv MP Mechelen.","CTL","Minor_AdHoc"," "," ",62632]
["2024-01-08","2024-01-13","NE",3,"53","A+B","Y.HEIKE","MUIZEN","(vide)","(vide)","23:55","04:50","Rooster M+N. Werken ikv MP Mechelen.","CTL","Minor_AdHoc","Laatste treinen L27 via L25"," ",62632]
["2024-01-08","2024-01-13","SW",1,"96","A+B","MONS","JURBISE","Week","Night","22:45","04:10","Réélectrification - Phase 9 - 2024 (suite planning 2023)\r\nPose des traverses entre 49/9B et 53/17B\r\n+ ETCS L2-IL_SO_P036_L96_L97_Jurbise - Mons - Saint Ghislain_ETCS\r\nETCS : Travaux extérieurs + chargements\r\nmeewerken mogelijk","CTL","Minor_AdHoc","MHS entre TX-F.27 (PK 49.645) et U-F.27 (PK 54.629) MHT cas 28323\r\nMHS entre T-F.27 (PK 49.645) et UX-F.27 (PK 54.629) MHT cas 28324"," ",49595]
["2024-01-08","2024-01-13","SW",2,"112","A+B","Y.SAINT-VAAST","LA LOUVIERE-CENTRE","Week","Night","23:30","05:20","Renouvellement des As 05AG/BG, 06AG/BG et 07XG\r\nfinitions","CTL","Minor_AdHoc","CTL L112 23h30 - 5h20\r\nL116 01h30 - 6h40 = dans l'amplitude après détournement des derniers HK venant de la L96 (Y La Paix et La Louvière centre inclus)\r\nART 2min"," ",40392]
["2024-01-08","2024-01-13","SW",2,"116","A","LA LOUVIERE-CENTRE","Y.LA PAIX","Week","Night","23:30","05:20","Linked to coupure nr 40392 on line 112 tracks(s) A+B from Y.SAINT-VAAST to LA LOUVIERE-CENTRE: Renouvellement des As 05AG/BG, 06AG/BG et 07XG\r\nfinitions","CTL","Minor_AdHoc"," "," ",40392]
["2024-01-08","2024-12-20","SE",2,"162","A+B","HAVERSIN","ROCHEFORT-JEMELLE","Week","Night","22:50","04:20","Travaux caténaire Axe 3 en gare de Marloie\r\n+ Travaux PLP BA Marloie-Jemelle","CTL","Minor_AdHoc",null," ",60133]
["2024-01-08","2024-12-15","SE",1,"161","A+B","GEMBLOUX","NAMUR","AllWeek","Night","22:50","04:30","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ Electrification (poteaux caténaires)","CTL","Minor_AdHoc","A partir de septembre 2021\r\nEn semaine.\r\n-        22h50 à 6h de nuit en semaine : SAVU\r\n-        CTL : de 22h50 à 4h30 en détournant les 2 derniers trains par la L144. \r\nLes weekends\r\n-        SAVU tous les weekends\r\n-        CTL de nuit : samedi à dima"," ",46352]
["2024-01-09","2024-01-12","NE",2,"53","A+B","MECHELEN","Y.HEIKE","Week","Night","00:05","04:00","masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6","CTL","Minor_AdHoc"," "," ",59816]
["2024-01-09","2024-01-13","NW",3,"50","A+B","Y.MELLE-WEST","GENT-SINT-PIETERS","Week","Night","00:20","06:00","Vernieuwen Y. Oost Driehoek Ledeberg \r\n\r\nR5/R6 L50 BD tot Buiten dienst stelling weekendTLO (R6 06.00u)","CTL","Minor_AdHoc",null," ",58172]
["2024-01-11","2024-01-11","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60102]
["2024-01-12","2024-01-14","SW",3,"90C","A+B","JURBISE","ATH","Weekend","Continuous","22:40","17:00","Maintenance Z7.53 + Z13.54","CTL","Medium","Brugelette non accessible (période non estivale)","HKM à adapter",58839]
["2024-01-12","2024-01-15","CE",2,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","Weekend","Continuous","23:45","04:50","Onderhoudszone FBMZ_19, FBKI_03 en FH_06 Area CE volgens onderhoudskalender 2024.\r\nSporen A en B 124 buiten dienst, inclusief L28/3\r\n\r\nPerrons en bundel Charleroi moeten vrijblijven (PHE)!!","CTL","Medium",null," ",58595]
["2024-01-12","2024-01-15","NW",2,"54","A+B","SINT-NIKLAAS","PUURS","Weekend","Continuous","23:40","04:00","onderhoud\r\n\r\nFSN - SP I + SP A inbegrepen\r\nFRP - wissel kant FSN inbegrepen + SP I inbegrepen","CTL","Medium"," "," ",60162]
["2024-01-12","2024-01-15","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 min","HKM à adapter",48627]
["2024-01-12","2024-01-15","SW",1,"130","A+B","TAMINES","CHATELET-GRIL OUEST","Weekend","Continuous","22:45","05:00","Maintenance Z15.51\r\nP4+\r\nReport 2023","CTL","Medium"," ","HKM à adapter",48508]
["2024-01-12","2024-01-15","SE",1,"161","B","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:45","WE SAVU RER Bakenbos-Ottignies\r\n+ Visite voies A/B + maintenance infrastructure + contrôles","SAVU_CTRL","Minor_AdHoc","ART maximum 2'"," ",49247]
["2024-01-13","2024-01-14","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61578]
["2024-01-13","2024-01-15","NE",1,"27","A+B","Y.DRABSTRAAT","Y.LIERSESTEENWEG","Weekend","Night","23:35","04:35","Linked to coupure nr 58093 on line 15 tracks(s) A+B from Y.AUBRY to Y.DRABSTRAAT: vernieuwing Y drabstraat\r\nlossen wissels","CTL","Minor_AdHoc"," "," ",58093]
["2024-01-13","2024-01-15","NE",2,"27","A+B","Y.BERCHEM-STADION","Y.LIERSESTEENWEG","Weekend","Night","23:35","04:35","Vernieuwing van de wissels Y-Drabstraat","CTL","Minor_AdHoc","Onderbreking van het verkeer op L27 tussen Y-Stadion en Y-Liersesteenweg\r\nOnderbreking van het verkeer op L15 tussen Y.Drabstraat en Y.Aubry\r\n\r\n\r\nLaatste reizigerstreinen kunnen niet stoppen in Mortsel"," ",33781]
["2024-01-13","2024-01-15","NW",1,"50","A+B","Y.MELLE-WEST","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","06:00","04:00","Linked to coupure nr 49435 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to MERELBEKE-ROOSTER S: Vernieuwen Y. Oost Driehoek Ledeberg \r\nFase 2 + 3\r\nWE1/3\r\n* aangepast naar 06.00u R6 >> geen CBP tijdens nacht R5/R6","CTL","Medium"," "," ",49435]
["2024-01-13","2024-01-15","NW",1,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","MERELBEKE-ROOSTER S","Weekend","Continuous","06:00","04:00","Vernieuwen Y. Oost Driehoek Ledeberg \r\nFase 2 + 3\r\nWE1/3\r\n* aangepast naar 06.00u R6 >> geen CBP tijdens nacht R5/R6","CTL","Medium","Geen verkeer tussen Y Melle West en Y West Driehoek Ledeberg"," ",49435]
["2024-01-13","2024-01-15","NW",1,"58(1)","A+B","Y.OOST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","06:00","04:00","Linked to coupure nr 49435 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to MERELBEKE-ROOSTER S: Vernieuwen Y. Oost Driehoek Ledeberg \r\nFase 2 + 3\r\nWE1/3\r\n* aangepast naar 06.00u R6 >> geen CBP tijdens nacht R5/R6","CTL","Medium"," "," ",49435]
["2024-01-13","2024-01-15","NW",2,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58745 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-tot AW 112BH vrij\r\nPerron I tem VI (geen continue buiten dienst ","SAVU","Minor_AdHoc"," "," ",58745]
["2024-01-13","2024-01-15","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-tot AW 112BH vrij\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)","CTL","Medium"," "," ",58745]
["2024-01-13","2024-01-15","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu"," ",47168]
["2024-01-14","2024-01-14","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61606]
["2024-01-14","2024-01-14","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59975]
["2024-01-14","2024-01-14","NW",2,"50","A+B","DENDERLEEUW","EREMBODEGEM","Weekend","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57736]
["2024-01-14","2024-01-14","NW",2,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Night","00:10","04:40","Linked to coupure nr 57736 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57736]
["2024-01-14","2024-01-14","NW",2,"89","A+B","DENDERLEEUW","BURST","Weekend","Night","00:10","04:40","Linked to coupure nr 57736 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57736]
["2024-01-15","2024-01-15","SE",3,"130","A/B","NAMUR","FLAWINNE","Week","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49045]
["2024-01-15","2024-01-19","NE",2,"53","A+B","MUIZEN-ROOSTER T","LEUVEN","Week","Night","23:20","05:00","herelectrificatie (bijkomend)","CTL","Minor_AdHoc","alternatief E2645-E2644"," ",60280]
["2024-01-15","2024-01-19","NE",3,"29","A+B","Y.KRUISBERG","TURNHOUT","Week","Night","23:00","04:40","omvormen 50 HZ SK naar TFSK\r\naanpassen treindetectiesysteem (moet voor 2025)\r\nvernieuwing signalisatie overwegen\r\nomvorming moet gebeuren voor uitrol ETCS L29","CTL","Minor_AdHoc","alternatief E3421"," ",60013]
["2024-01-15","2024-01-19","NW",3,"217","S","Y.NOORD EVERSTEIN","EVERGEM-OVERDAM","Week","Night","23:50","05:00","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Minor_AdHoc",null,"Info Racc.",58516]
["2024-01-15","2024-01-19","NW",3,"55A","S","Y.RINGVAART","LANGERBRUGGE","Week","Night","23:50","05:00","Linked to coupure nr 58516 on line 217 tracks(s) S from Y.NOORD EVERSTEIN to EVERGEM-OVERDAM: 227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Minor_AdHoc"," ","Info Racc.",58516]
["2024-01-15","2024-01-19","SW",2,"112","A+B","Y.SAINT-VAAST","LA LOUVIERE-CENTRE","Week","Night","23:30","05:20","Renouvellement des As 05AG/BG, 06AG/BG et 07XG\r\nfinitions","CTL","Minor_AdHoc","CTL L116 (Y La Paix et La Louvière centre inclus) 22:00-6:00"," ",60848]
["2024-01-15","2024-01-19","SW",2,"116","A","LA LOUVIERE-CENTRE","Y.LA PAIX","Week","Night","23:30","05:20","Linked to coupure nr 60848 on line 112 tracks(s) A+B from Y.SAINT-VAAST to LA LOUVIERE-CENTRE: Renouvellement des As 05AG/BG, 06AG/BG et 07XG\r\nfinitions","CTL","Minor_AdHoc"," "," ",60848]
["2024-01-15","2024-01-20","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59846]
["2024-01-15","2024-01-20","NW",3,"52","S","PUURS","BOOM","Week","Night","23:30","04:30","Onderhoud - Frank Matthys \r\nweek 3-16-42","CTL","Minor_AdHoc"," "," ",58795]
["2024-01-15","2024-01-20","SW",1,"78","A+B","SAINT-GHISLAIN","TOURNAI","Week","Night","22:55","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nTravaux préparatoires\r\n+ ETCS L2-IL_SO_P036_L96_L97_Jurbise - Mons - Saint Ghislain_ETCS\r\nTravaux extérieurs - Buitenwerken,","CTL","Minor_AdHoc",null," ",48725]
["2024-01-15","2024-01-29","NW",1,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","MERELBEKE-ROOSTER S","AllWeek","Continuous","04:00","04:00","BTS\r\nVernieuwen Y. Oost Driehoek Ledeberg","ART","Minor_AdHoc",null," ",60962]
["2024-01-15","2024-03-11","SW",1,"124A","A","LUTTRE","ROUX","AllWeek","Continuous","08:00","06:00","Linked to coupure nr 49461 on line 124A tracks(s) B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nCTL L117 de jour en semaine\r\nDossier de concertation validé le 28 octobre 2021","CTL","Major"," "," ",49461]
["2024-01-15","2024-03-11","SW",1,"124A","B","LUTTRE","ROUX","AllWeek","Continuous","08:00","06:00","Aménagement Gare de Luttre : Phase 1-2024\r\nCTL L117 de jour en semaine\r\nDossier de concertation validé le 28 octobre 2021","SAVU_CTRL","High","Voies IV et V en gare de Luttre inaccessible en continu\r\nFaisceau accessoire en gare de Luttre inaccessible en continu\r\nCTL L124A de jour en semaine (quais de Luttre inclu) : 08h30 - 15h30\r\nindisponibilité de la transversale Sud à partir du 09/02"," ",49461]
["2024-01-15","2024-03-15","SE",1,"154","B","DINANT","Y.NEFFE","AllWeek","Continuous","06:00","22:00","Suppression PN 115 bis et PN 116\r\nConstruction de deux couloirs sous-voies","SAVU","High","ART de protection (PN 115 bis)\r\nBK 90.050 à 90.150\r\nVitesse à 40 km/h\r\nPerte de temps HKV : 2 minutes / HKM : 2 minutes"," ",47498]
["2024-01-16","2024-01-19","NW",3,"50","A+B","Y.MELLE-WEST","GENT-SINT-PIETERS","Week","Night","00:20","04:30","Vernieuwen Y. Oost Driehoek Ledeberg \r\n\r\n*R5/R6 in weekend-TLO","CTL","Minor_AdHoc",null," ",58176]
["2024-01-16","2024-01-20","NW",3,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Week","Night","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Minor_AdHoc",null,"Info Racc",58698]
["2024-01-19","2024-01-22","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","23:30","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2 buiten dienst","CTL","Medium","geen verkeer sporen 1+2"," ",58130]
["2024-01-19","2024-01-22","NE",2,"53","A+B","MUIZEN-ROOSTER T","LEUVEN","Weekend","Continuous","23:20","05:00","herelectrificatie (bijkomend)","CTL","Medium","alternatief E2645-E2644"," ",60281]
["2024-01-19","2024-01-22","NW",2,"217","S","Y.NOORD EVERSTEIN","EVERGEM-OVERDAM","Weekend","Continuous","23:50","05:00","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Medium"," ","Info Racc.",58518]
["2024-01-19","2024-01-22","NW",2,"54","A+B","SINT-NIKLAAS","PUURS","Weekend","Continuous","23:40","04:00","Indienstname PLP\r\nL54-Temse\r\nFSN-FRP vrij\r\nTestritten op zondag tot in St Niklaas en Puurs in overleg met de regelaar","CTL","Medium"," "," ",57578]
["2024-01-19","2024-01-22","NW",2,"55A","S","Y.RINGVAART","LANGERBRUGGE","Weekend","Continuous","23:50","05:00","Linked to coupure nr 58518 on line 217 tracks(s) S from Y.NOORD EVERSTEIN to EVERGEM-OVERDAM: 227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Medium"," ","Info Racc.",58518]
["2024-01-19","2024-01-22","SW",1,"117","A+B","MANAGE","LUTTRE","Weekend","Continuous","23:20","04:40","Linked to coupure nr 49584 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 1/6\r\nDépose transversale caténaire\r\n+ Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52","CTL","Medium"," ","HKM à adapter",49584]
["2024-01-19","2024-01-22","SW",1,"118","A","MONS","HAVRE","Weekend","Continuous","23:30","04:30","Mise en sevice SIMIS-W entre Mons et Obourg (gare incluse).\r\nTravaux préparatoires","SAVU","Minor_AdHoc",null," ",49156]
["2024-01-19","2024-01-22","SW",1,"124","B","ROUX","OBAIX-BUZET","Weekend","Continuous","23:20","04:40","Linked to coupure nr 49584 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 1/6\r\nDépose transversale caténaire\r\n+ Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52","SAVU","Minor_AdHoc"," ","HKM à adapter",49584]
["2024-01-19","2024-01-22","SW",1,"124A","A+B","LUTTRE","ROUX","Weekend","Continuous","23:20","04:40","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 1/6\r\nDépose transversale caténaire\r\n+ Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52","CTL","Medium","Voies II, III, IV et V en gare de Luttre inaccessible en continu\r\nFaisceau accessoire en gare de Luttre inaccessible en continu\r\nLiaison 30AE/BE exploitable en L124\r\nDossier de concertation validé le 28 octobre 2021","HKM à adapter",49584]
["2024-01-20","2024-01-21","NW",3,"204","*","GENT-RODENHUIZE","GENT-RODENHUIZEDOK","Weekend","Continuous","22:00","14:00","Reservatie onderhoud, enkel bundel Mercator buiten dienst","CTL","Medium",null,"Info Racc",60413]
["2024-01-20","2024-01-21","SW",2,"96","A+B","Y.SOIGNIES","JURBISE","Weekend","Continuous","06:00","16:00","Maintenance Z4.53 \r\nMise HS P4","CTL","Medium",null,"HKM à adapter",48644]
["2024-01-20","2024-01-21","SW",3,"97","A+B","MONS","SAINT-GHISLAIN","Weekend","Continuous","06:00","16:00","Maintenance Z.12.53\r\nMise HS en P4","CTL","Medium"," "," ",48887]
["2024-01-20","2024-01-22","CE",2,"27D","A+B","SCHAERBEEK","SCHAERBEEK-GROUPE R","Weekend","Continuous","00:20","04:00","Onderhoudszone FSR_14/MTB_10 Area CE volgens onderhoudskalender 2024.\r\nOnderhoudswerken L27D en L27D/4 vanaf de perrons Schaarbeek tot en met de kopwissels van Groep R","CTL","Medium","Groep R en G en atelier NMBS enkel bereikbaar via Y Groep G en lokale manoeuvres.","HKM via L26",58570]
["2024-01-20","2024-01-22","CE",3,"27D","*","SCHAERBEEK","SCHAERBEEK-GROUPE R","Weekend","Continuous","00:20","04:00","P097314: Elektrificatie bundel OOP Schaarbeek-Vorming\r\n\r\nBijkomende goedkeuring te vragen aan NMBS door aanvrager voor installaties binnen domein NMBS.","Autre","Minor_AdHoc","L27D/5 Bundel V en DOP afgesloten kant FSR Reizigers.","Lokale omleiding in FSR",59014]
["2024-01-20","2024-01-22","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium",null," ",58000]
["2024-01-20","2024-01-22","NW",2,"50","A+B","Y.MELLE-WEST","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","01:00","04:00","Vernieuwen Y. Oost Driehoek Ledeberg \r\nWE2/3\r\n\r\nTLO L50+DOES L50E+DOES L58","CTL","Medium",null," ",58158]
["2024-01-20","2024-01-22","NW",2,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58757 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",58757]
["2024-01-20","2024-01-22","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)","CTL","Medium"," "," ",58757]
["2024-01-20","2024-01-22","NW",2,"50E","A+B","MERELBEKE-ROOSTER S","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58158 on line 50 tracks(s) A+B from Y.MELLE-WEST to Y.WEST DRIEHOEK LEDEBERG: Vernieuwen Y. Oost Driehoek Ledeberg \r\nWE2/3\r\n\r\nTLO L50+DOES L50E+DOES L58","SAVU","Minor_AdHoc"," "," ",58158]
["2024-01-20","2024-01-22","NW",2,"58(1)","A+B","Y.OOST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58158 on line 50 tracks(s) A+B from Y.MELLE-WEST to Y.WEST DRIEHOEK LEDEBERG: Vernieuwen Y. Oost Driehoek Ledeberg \r\nWE2/3\r\n\r\nTLO L50+DOES L50E+DOES L58","SAVU","Minor_AdHoc"," "," ",58158]
["2024-01-20","2024-01-22","NW",2,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58757 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",58757]
["2024-01-20","2024-01-22","SE",2,"27","A+B","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL","Weekend","Continuous","06:00","04:00","migratie tunnelveiligheidstechnieken antw NZ","CTL","Medium"," "," ",59036]
["2024-01-20","2024-01-22","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu"," ",47169]
["2024-01-20","2024-02-04","SW",1,"78","A/B","BLATON","Y.MAUBRAY","AllWeek","Continuous","06:00","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs","SAVU_CTRL","High","SAVU jour et CTL nuit (22h50-05h00) + CTL weekend\r\nART VA du 29/01 au 4/02 inclus\r\nART VB du 5/02 au 11/02 inclus\r\nART stabilisation 60 km/h : 5min"," ",48709]
["2024-01-20","2024-01-21","SE",3,"161","A/B","NAMUR","RHISNES-SAS","Weekend","Day","08:00","16:00","Visite périodique + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","Savu alternatif VA/VB , de 8h à 16 h"," ",49205]
["2024-01-21","2024-01-21","NE",1,"12/1","S","Y.DRIEHOEKSTRAAT","Y.SINT-MARIABURG","Weekend","Day","06:00","17:30","Linked to coupure nr 52761 on line 27A tracks(s) A+B from LUCHTBAL-ROOSTER S to ANTWERPEN-NOORD-INRIT C1: Oude Landen\r\nproject 304\r\n\r\nwerkvenster kan ingekort worden ,afhankelijk werken L59","CTL","Minor_AdHoc"," "," ",52761]
["2024-01-21","2024-01-21","NE",1,"27A","A+B","LUCHTBAL-ROOSTER S","ANTWERPEN-NOORD-INRIT C1","Weekend","Day","06:00","17:30","Oude Landen\r\nproject 304\r\n\r\nwerkvenster kan ingekort worden ,afhankelijk werken L59","CTL","Minor_AdHoc",null," ",52761]
["2024-01-21","2024-01-21","NW",2,"50","A+B","DENDERLEEUW","EREMBODEGEM","Weekend","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57722]
["2024-01-21","2024-01-21","NW",2,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Night","00:10","04:40","Linked to coupure nr 57722 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57722]
["2024-01-21","2024-01-21","NW",2,"89","A+B","DENDERLEEUW","BURST","Weekend","Night","00:10","04:40","Linked to coupure nr 57722 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57722]
["2024-01-21","2024-01-21","NW",3,"202B","S","Y.EIVOORDE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Day","10:00","18:00","R-419009-01\r\n\r\nonderhoud werkveld 3421-36\r\n\r\nAW 72R-73R-74R-74XR-75R-80R-82R-83R\r\n\r\nBundel Ramskapelle niet bereikbaar","CTL","Minor_AdHoc"," ","Info Racc",60367]
["2024-01-21","2024-01-22","NW",2,"50A/5","A+B","BRUGGE-ROOSTER E","BRUGGE","Weekend","Continuous","01:00","04:00","vervangen doorsteek Brugge kant Gent  I70-71-72 - 66 - 73 (vervangen ACEC) tot in Bundel A\r\nSP IX+X vrij\r\nSP I+II bereikbaar vanuit bundel B\r\nSP III-IV-V CDS kant Gent","CTL","Medium",null,null,58615]
["2024-01-21","2024-01-22","NW",2,"66","A+B","BRUGGE","BRUGGE-ROOSTER E","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58615 on line 50A/5 tracks(s) A+B from BRUGGE-ROOSTER E to BRUGGE: vervangen doorsteek Brugge kant Gent  I70-71-72 - 66 - 73 (vervangen ACEC) tot in Bundel A\r\nSP IX+X vrij\r\nSP I+II bereikbaar vanuit bundel B\r\nSP III-IV-V CDS kant Ge","CTL","Medium"," ",null,58615]
["2024-01-22","2024-01-26","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","23:50","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2"," ",58131]
["2024-01-22","2024-01-26","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Week","Night","23:50","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Minor_AdHoc"," "," ",58211]
["2024-01-22","2024-01-26","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59847]
["2024-01-22","2024-01-26","NE",3,"59","A+B","Y.OOST BERCHEM","Y.MELSELE","Week","Night","23:50","04:35","onderhoud SIG +onderhoud wissels en overwegen","CTL","Minor_AdHoc","alternatief E744"," ",60126]
["2024-01-22","2024-01-26","NW",3,"217","S","Y.NOORD EVERSTEIN","EVERGEM-OVERDAM","Week","Night","23:50","05:00","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Minor_AdHoc"," ","Info Racc.",58519]
["2024-01-22","2024-01-26","NW",3,"55A","S","Y.RINGVAART","LANGERBRUGGE","Week","Night","23:50","05:00","Linked to coupure nr 58519 on line 217 tracks(s) S from Y.NOORD EVERSTEIN to EVERGEM-OVERDAM: 227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Minor_AdHoc"," ","Info Racc.",58519]
["2024-01-22","2024-01-27","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Week","Night","23:55","05:20","Omvorming Y Jette Rooster R: voorbereidende nachten BVL","CTL","Minor_AdHoc","TLO L50 + L60"," ",53206]
["2024-01-22","2024-01-27","NW",1,"75","A+B","KORTRIJK","MOUSCRON","Week","Night","23:10","04:00","TLO-nachten voor TESTEN ETCS\r\n1 week aansluitend nachten in januari\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk","CTL","Minor_AdHoc"," "," ",47301]
["2024-01-22","2024-01-27","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","22:00","05:15","Travaux SNCF CHA24_0026001 \r\nLille Racc RougeBarre – Bif St André : REGE – RVB, RB/RT et RR\r\n+ Tirage de cable","CTL","Minor_AdHoc",null," ",57908]
["2024-01-23","2024-01-26","NW",3,"50","A+B","Y.MELLE-WEST","GENT-SINT-PIETERS","Week","Night","00:20","04:30","Vernieuwen Y. Oost Driehoek Ledeberg \r\n\r\n*R5/R6 in weekend-TLO","CTL","Minor_AdHoc",null," ",58177]
["2024-01-23","2024-01-26","NW",3,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Week","Night","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\n\r\nR5/56 in weekend TLO","CTL","Minor_AdHoc",null,"Info Racc",57794]
["2024-01-24","2024-01-24","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60087]
["2024-01-25","2024-01-25","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60103]
["2024-01-25","2024-01-25","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55941]
["2024-01-26","2024-01-29","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Weekend","Continuous","23:50","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Medium"," "," ",58206]
["2024-01-26","2024-01-29","NE",2,"52","A+B","PUURS","Y.ANTWERPEN-ZUID","Weekend","Continuous","23:50","04:30","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","CTL","Medium",null," ",59085]
["2024-01-26","2024-01-29","NE",2,"53A","A+B","MECHELEN","Y.MUIZEN","Weekend","Continuous","23:50","04:00","masterplan mechelen\r\nperronsporen 5+6 (met L27,L53)","CTL","Medium","spoor 5+6"," ",58279]
["2024-01-26","2024-01-29","NW",2,"217","S","Y.NOORD EVERSTEIN","EVERGEM-OVERDAM","Weekend","Continuous","23:50","05:00","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Medium"," ","Info Racc",58520]
["2024-01-26","2024-01-29","NW",2,"55A","S","Y.RINGVAART","LANGERBRUGGE","Weekend","Continuous","23:50","05:00","Linked to coupure nr 58520 on line 217 tracks(s) S from Y.NOORD EVERSTEIN to EVERGEM-OVERDAM: 227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Medium"," ","Info Racc",58520]
["2024-01-26","2024-01-29","SW",1,"117","A+B","MANAGE","LUTTRE","Weekend","Continuous","23:20","04:40","Linked to coupure nr 49462 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 2/6\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium"," "," ",49462]
["2024-01-26","2024-01-29","SW",1,"124","B","OBAIX-BUZET","ROUX","Weekend","Continuous","23:20","04:40","Linked to coupure nr 49462 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 2/6\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc"," "," ",49462]
["2024-01-26","2024-01-29","SW",1,"124A","A+B","LUTTRE","ROUX","Weekend","Continuous","23:20","04:40","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 2/6\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies II, III, IV et V en gare de Luttre inaccessible en continu\r\nFaisceau accessoire en gare de Luttre inaccessible en continu\r\n\r\nMise HS voie A L124A à partir de 18h00 pour permettre travaux ripage caténaire"," ",49462]
["2024-01-26","2024-01-29","SW",1,"78","A+B","BLATON","TOURNAI","Weekend","Continuous","22:30","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nWE 1/7","CTL","Medium",null," ",49403]
["2024-01-27","2024-01-27","SE",3,"139","A/B","WAVRE","OTTIGNIES","Weekend","Day","08:00","16:00","Visites des postes+ maintenances infrastructure et contrôles","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48866]
["2024-01-27","2024-01-28","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Night","00:30","06:00","Lossing wissels Muizen Rooster T - L53","CTL","Minor_AdHoc"," "," ",61503]
["2024-01-27","2024-01-28","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59433]
["2024-01-27","2024-01-28","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60409]
["2024-01-27","2024-01-28","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60409 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60409]
["2024-01-27","2024-01-28","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60409 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60409]
["2024-01-27","2024-01-28","SW",3,"130","B","CHATELET-GRIL EST","CHATELET-GRIL OUEST","Weekend","Continuous","22:00","22:00","Maintenance Z18. 51 (R6 22h - R7 22h)","Autre","Minor_AdHoc","Mise hors service en une zone (= Zone 18), voici les détails:\r\nL130, faisceau B\tVoie 353 + 354 + 355 + 356 + 357 + 358\tChâtelet\tChâtelet\t12J (ne)  &\t43AJ/44J (ne)\r\n\t\t\t\t+ 12J (ne)   &\t21AJ/22J (ne)"," ",55059]
["2024-01-27","2024-01-29","CE",2,"26","A+B","Y.RUE DE BRUEL","Y.CINQUANTENAIRE","Weekend","Continuous","06:10","04:00","P085306 BVL L26 Y Bruul - Y50.\r\nY Bruulstraat is niet inbegrepen.","CTL","Medium","TLO tussen Y Bruulstr en Y50","Info Racc",59645]
["2024-01-27","2024-01-29","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium",null," ",58001]
["2024-01-27","2024-01-29","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2 buiten dienst","CTL","Medium","geen verkeer sporen 1+2"," ",58132]
["2024-01-27","2024-01-29","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","migratie tunnelveiligheidstechnieken antwerpen NZ\r\nantwerpen centraal -Antwerpen luchtbal","CTL","Medium"," "," ",59038]
["2024-01-27","2024-01-29","NW",2,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58758 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",58758]
["2024-01-27","2024-01-29","NW",2,"50","B","Y.MELLE-WEST","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58157 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to MERELBEKE-ROOSTER S: Vernieuwen Y. Oost Driehoek Ledeberg \r\nWE3/3","SAVU","Minor_AdHoc"," "," ",58157]
["2024-01-27","2024-01-29","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)","CTL","Medium"," "," ",58758]
["2024-01-27","2024-01-29","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","MERELBEKE-ROOSTER S","Weekend","Continuous","01:00","04:00","Vernieuwen Y. Oost Driehoek Ledeberg \r\nWE3/3","CTL","Medium",null," ",58157]
["2024-01-27","2024-01-29","NW",2,"58(1)","A+B","Y.OOST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58157 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to MERELBEKE-ROOSTER S: Vernieuwen Y. Oost Driehoek Ledeberg \r\nWE3/3","CTL","Medium"," "," ",58157]
["2024-01-27","2024-01-29","NW",2,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58758 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",58758]
["2024-01-27","2024-01-29","NW",2,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Weekend","Continuous","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Medium",null,"Info Racc",57789]
["2024-01-27","2024-01-29","NW",2,"90","A+B","DENDERLEEUW","Y.NEDERBOELARE","Weekend","Continuous","06:00","04:20","Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P038_01_L90_Geraardsbergen - Ninove_IL\r\nETCS L2-IL_NW_P038_02_L90_Ninove_IL\r\nETCS L2-IL_NW_P038_03_L90_Ninove - Denderleeuw_IL\r\n\r\n*R6 06.00u - L90 niet in CBP","CTL","Medium",null,"Info Racc.",57527]
["2024-01-27","2024-01-29","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","05:00","Electrification 2 x 25 kV","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu"," ",47170]
["2024-01-27","2024-01-28","SE",3,"161","A/B","OTTIGNIES","GEMBLOUX","Weekend","Day","08:00","16:00","Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles + 1/2h sas Rhisnes","SAVU","Minor_AdHoc","SAVU alternatif entre 08h00 et 16h00"," ",48948]
["2024-01-28","2024-01-28","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59976]
["2024-01-28","2024-01-28","NW",2,"50","A+B","DENDERLEEUW","EREMBODEGEM","Weekend","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57723]
["2024-01-28","2024-01-28","NW",2,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Night","00:10","04:40","Linked to coupure nr 57723 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57723]
["2024-01-28","2024-01-28","NW",2,"89","A+B","DENDERLEEUW","BURST","Weekend","Night","00:10","04:40","Linked to coupure nr 57723 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57723]
["2024-01-28","2024-01-28","SE",3,"139","A/B","SINT-JORIS-WEERT","WAVRE","Weekend","Day","08:00","16:00","Visites des postes - maintenances diverses et révisions","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48876]
["2024-01-29","2024-02-02","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Week","Night","23:30","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3+4","CTL","Minor_AdHoc","sporen 3+4"," ",58190]
["2024-01-29","2024-02-02","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Week","Night","23:50","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Minor_AdHoc"," "," ",58210]
["2024-01-29","2024-02-02","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59848]
["2024-01-29","2024-02-02","NE",3,"59","A+B","Y.OOST BERCHEM","Y.MELSELE","Week","Night","23:50","04:35","onderhoud SIG +onderhoud wissels en overwegen","CTL","Minor_AdHoc","alternatief E744"," ",60127]
["2024-01-29","2024-02-03","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Week","Night","23:55","05:20","Omvorming Y Jette Rooster R: voorbereidende nachten BVL","CTL","Minor_AdHoc","TLO L50 + L60"," ",53207]
["2024-01-29","2024-02-03","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Linked to coupure nr 53207 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Omvorming Y Jette Rooster R: voorbereidende nachten BVL","CTL","Minor_AdHoc"," "," ",53207]
["2024-01-29","2024-02-03","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","22:00","05:15","Travaux SNCF CHA24_0026001 \r\nLille Racc RougeBarre – Bif St André : REGE – RVB, RB/RT et RR","CTL","Minor_AdHoc",null," ",57932]
["2024-01-29","2024-02-12","SW",1,"78","A/B","BLATON","Y.MAUBRAY","AllWeek","Continuous","06:00","05:00","ART\r\nBlaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs","ART","Minor_AdHoc","ART VA du 29/01 au 4/02 inclus\r\nART VB du 5/02 au 11/02 inclus\r\nART stabilisation 60 km/h: 5 min"," ",60885]
["2024-01-30","2024-02-02","NE",2,"53A","A+B","MECHELEN","Y.MUIZEN","Week","Night","00:00","04:00","masterplan mechelen\r\nperronsporen 5+6 (met L27,L53)","CTL","Minor_AdHoc","spoor 5+6"," ",58280]
["2024-01-30","2024-02-02","NW",3,"50","A+B","DENDERLEEUW","EREMBODEGEM","Week","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nBuiten dienst zonder impact HKV\r\nZone A + uitbreiding volledig rooster FDD kant Gent\r\nPerron 1-2-3-4-5-6-7-9 inbegrepen\r\nRooster FDD > L89 inbegrepen\r\nRooster FDD > L50A3 inbegrepen","CTL","Minor_AdHoc"," "," ",57717]
["2024-01-30","2024-02-02","NW",3,"50","A+B","Y.MELLE-WEST","GENT-SINT-PIETERS","Week","Night","00:20","04:30","Vernieuwen Y. Oost Driehoek Ledeberg \r\n\r\n*R5/R6 niet inbegrepen wegens weekend TLO MP FDD","CTL","Minor_AdHoc",null," ",58186]
["2024-01-30","2024-02-02","NW",3,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:10","04:40","Linked to coupure nr 57717 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nBuiten dienst zonder impact HKV\r\nZone A + uitbreiding volledig rooster FDD kant Gent\r\nPerron 1-2-3-4-5-6-7-9 inbegrepen\r\nR","CTL","Minor_AdHoc"," "," ",57717]
["2024-01-30","2024-02-02","NW",3,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Week","Night","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\n\r\n* R5/R6 in weekend-TLO","CTL","Minor_AdHoc",null,"Info Racc",57795]
["2024-01-30","2024-02-02","NW",3,"89","A+B","DENDERLEEUW","BURST","Week","Night","00:10","04:40","Linked to coupure nr 57717 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nBuiten dienst zonder impact HKV\r\nZone A + uitbreiding volledig rooster FDD kant Gent\r\nPerron 1-2-3-4-5-6-7-9 inbegrepen\r\nR","SAVU_CTRL","Minor_AdHoc"," "," ",57717]
["2024-02-02","2024-02-04","NW",2,"58","A+B","WONDELGEM","EEKLO","Weekend","Continuous","23:00","04:20","Vernieuwen houtstukken brug Schoonstraat Kp 15 078","CTL","Medium",null," ",59191]
["2024-02-02","2024-02-04","SW",2,"130C","A+B","COUILLET","CHATELET-GRIL OUEST","Weekend","Continuous","23:00","18:00","travaux préparatoire pour MES à la multimodale à Charleroi\r\nréglage CVs + transfert modules dans I34","CTL","Medium",null," ",55488]
["2024-02-02","2024-02-05","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Weekend","Continuous","23:50","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Medium"," "," ",58207]
["2024-02-02","2024-02-05","NE",2,"53A","A+B","MECHELEN","Y.MUIZEN","Weekend","Continuous","23:50","04:00","masterplan mechelen\r\nperronsporen 5+6 (met L27,L53)","CTL","Medium","spoor 5+6"," ",58281]
["2024-02-02","2024-02-05","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59895]
["2024-02-02","2024-02-05","SE",2,"162","A+B","LEIGNON","HAVERSIN-GARAGE","Weekend","Continuous","22:15","05:00","Travaux Axe 3:\r\nTravaux de traversée de voie + Massification OA","CTL","Medium","Suite arbitrage budgétaire - travaux effectués = Travaux de traversée de voie principalement \r\nART à déterminer"," ",47357]
["2024-02-02","2024-02-05","SW",1,"117","A+B","MANAGE","LUTTRE","Weekend","Continuous","18:00","04:40","Linked to coupure nr 49776 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 3/6\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium"," "," ",49776]
["2024-02-02","2024-02-05","SW",1,"118","B","MONS","HAVRE","Weekend","Continuous","23:30","04:30","Mise en sevice SIMIS-W entre Mons et Obourg (gare incluse).\r\nTravaux préparatoires","SAVU","Minor_AdHoc",null," ",49157]
["2024-02-02","2024-02-05","SW",1,"124","B","ROUX","OBAIX-BUZET","Weekend","Continuous","18:00","04:40","Linked to coupure nr 49776 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 3/6\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc"," "," ",49776]
["2024-02-02","2024-02-05","SW",1,"124A","A+B","LUTTRE","ROUX","Weekend","Continuous","18:00","04:40","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 3/6\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies II, III, IV et V en gare de Luttre inaccessible en continu\r\nFaisceau accessoire en gare de Luttre inaccessible en continu"," ",49776]
["2024-02-02","2024-02-05","SW",1,"78","A+B","BLATON","TOURNAI","Weekend","Continuous","22:30","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nWE 2/7","CTL","Medium",null," ",49405]
["2024-02-02","2024-02-05","SE",1,"161","A+B","OTTIGNIES","Y.LOUVAIN-LA-NEUVE","Weekend","Continuous","23:30","04:30","WE CTL RER Ottignies-Y.LLN","CTL","Medium","ART à définir, maximum 2'"," ",49260]
["2024-02-03","2024-02-04","SW",3,"124A","A+B","LUTTRE","MARCHIENNE-AU-PONT","Weekend","Continuous","06:00","17:00","Maintenance Z07.52","CTL","Medium","Quais III Luttre Inaccessible"," ",60790]
["2024-02-03","2024-02-04","SW",3,"90","A/B","GERAARDSBERGEN","ATH","Weekend","Continuous","06:00","18:00","PLP - SAVU de pré-réglage","SAVU","Minor_AdHoc","Samedi = SAVU VA\r\nDimanche = SAVU VB","HKM à adapter",57011]
["2024-02-03","2024-02-05","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58002]
["2024-02-03","2024-02-05","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","migratie tunnelveiligheidtechnieken Antw NZ\r\nantwerpen centraal -antwerpen luchtbal","CTL","Medium"," "," ",59047]
["2024-02-03","2024-02-05","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3+4","CTL","Medium","sporen 3+4"," ",58191]
["2024-02-03","2024-02-05","NW",2,"50","A+B","DENDERLEEUW","AALST","Weekend","Continuous","01:00","04:00","Omvorming rooster Denderleeuw volgens richtplan.\r\nBVL\r\nZone F\r\nSP I-II-III-IV-V + TLO L50 + DOES L50A3 SP B buiten dienst\r\ndoorsteek 75A/B-F-74A/B-F-73A/B-F-72A-F buiten dienst","CTL","Medium"," "," ",57716]
["2024-02-03","2024-02-05","NW",2,"50A/3","B","DENDERLEEUW","Y.WELLE","Weekend","Continuous","01:00","04:00","Linked to coupure nr 57716 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.\r\nBVL\r\nZone F\r\nSP I-II-III-IV-V + TLO L50 + DOES L50A3 SP B buiten dienst\r\ndoorsteek 75A/B-F-74A/B-F-73A/B-F-72A-F buiten dien","SAVU","Minor_AdHoc"," "," ",57716]
["2024-02-03","2024-02-05","NW",2,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Weekend","Continuous","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Medium",null,"Info Racc",57788]
["2024-02-03","2024-02-05","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu"," ",47171]
["2024-02-04","2024-02-04","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59783]
["2024-02-04","2024-02-04","NW",3,"51A","A","LISSEWEGE","ZEEBRUGGE-STRAND","Weekend","Day","14:00","22:00","R-419328-01\r\n\r\nReservering Onderhoud doorsteek bundel A-B Zone 107","SAVU","Minor_AdHoc"," "," ",60452]
["2024-02-05","2024-02-09","NE",1,"139","A+B","SINT-JORIS-WEERT","LEUVEN","Week","Night","22:50","05:15","Vernieuwing sporen.\r\n\r\nvoorbereidende werken massificatie met werken Waver-Ottignies\r\n\r\n+\r\nonderhoud","CTL","Minor_AdHoc","alternatief E5722",null,58898]
["2024-02-05","2024-02-09","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 5+6","CTL","Minor_AdHoc","sporen 5+6"," ",58192]
["2024-02-05","2024-02-09","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Week","Night","23:55","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Minor_AdHoc"," "," ",58212]
["2024-02-05","2024-02-09","NE",2,"53A","A+B","MECHELEN","Y.MUIZEN","Week","Night","23:50","04:00","masterplan mechelen\r\nperronsporen 5+6 (met L27,L53)","CTL","Minor_AdHoc","spoor 5+6"," ",58282]
["2024-02-05","2024-02-09","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59849]
["2024-02-05","2024-02-09","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58473]
["2024-02-05","2024-02-09","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58473 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58473]
["2024-02-05","2024-02-09","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58473 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58473]
["2024-02-05","2024-02-09","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58473 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58473]
["2024-02-05","2024-02-09","SE",2,"139","A+B","SINT-JORIS-WEERT","WAVRE","Week","Night","23:10","05:10","Renouvellement Traverses et Ballast \r\nC75 + P93 entre 12.100 et 19.285\r\nPréparations","CTL","Minor_AdHoc",null,"Nuits semaine 6 : via L165-166-154-130-124A-L124-L28(1) + 96- 28(1) (L130A non disponible)\r\nWE 6 : Athus-Anvers via bx/L130 (L130 fermée sam23h-dim15h)",59403]
["2024-02-05","2024-02-10","NE",2,"12","A+B","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL","Week","Night","22:45","04:55","onderhoud wissels en sporen te ANtwerpen Schijnpoort inrit bundel F inclusief bundelkoppen F, D","CTL","Minor_AdHoc","geen toegang tot bundel F \r\ngeen toegang bundel D kant Y luchtbal"," ",60215]
["2024-02-05","2024-02-10","SW",1,"130A","A+B","CHARLEROI-SUD","MARCHIENNE-ZONE","Week","Night","22:30","04:10","Livraison des AS Y LLS, à l'aide du train Kirow","CTL","Minor_AdHoc","L130A et L132 fermées","HKM à adapter\r\nInfoRacc",49495]
["2024-02-05","2024-02-10","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","22:00","05:15","Travaux SNCF CHA24_0026001 \r\nLille Racc RougeBarre – Bif St André : REGE – RVB, RB/RT et RR","CTL","Minor_AdHoc",null," ",57933]
["2024-02-05","2024-02-10","SW",1,"78","A+B","SAINT-GHISLAIN","TOURNAI","Week","Night","22:55","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nTravaux préparatoires\r\n+ Déchargement LRS train Robel","CTL","Minor_AdHoc",null," ",57918]
["2024-02-05","2024-04-14","SW",1,"96","A/B","MONS","JURBISE","AllWeek","Continuous","06:00","23:00","Réélectrification - Phases 1 et 2 - 2024","SAVU","High","SAVU dans le saisonnier","Inséré dans le saisonnier",47567]
["2024-02-05","2024-06-28","SE",2,"165","A/B","BERTRIX","FLORENVILLE","AllWeek","Continuous","09:00","16:00","ART 1 min\r\nRenouvellement des murs en aile du P.I. 92.674\r\nZone de chantier entre B.K. 92.645 à 92.705","ART","Minor_AdHoc","Seul un ART SANS MHS voie par voie \r\nDu 05/02 au 12/04 ART en VA\r\nDu 15/04 au 28/06 ART en VB\r\nART de protection\r\nlongueur de l’ART (avec BK si possible); 92.625 à 92.725 = 100m\r\nvitesse réduite: 60km/h\r\nperte de temps HKV: 1 \r\nperte de temps HKM: 1"," ",57824]
["2024-02-06","2024-02-09","NW",3,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Week","Night","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc",null,"Info Racc",57796]
["2024-02-06","2024-02-10","NW",3,"50","A+B","DENDERLEEUW","EREMBODEGEM","Week","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nBuiten dienst zonder impact HKV\r\nZone A + uitbreiding volledig rooster FDD kant Gent\r\nPerron 1-2-3-4-5-6-7-8-9 inbegrepen\r\nRooster FDD > L89 inbegrepen\r\nRooster FDD > L50A3 inbegrepen","CTL","Minor_AdHoc"," "," ",57719]
["2024-02-06","2024-02-10","NW",3,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:10","04:40","Linked to coupure nr 57719 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nBuiten dienst zonder impact HKV\r\nZone A + uitbreiding volledig rooster FDD kant Gent\r\nPerron 1-2-3-4-5-6-7-8-9 inbegrepen\r","CTL","Minor_AdHoc"," "," ",57719]
["2024-02-06","2024-02-10","NW",3,"89","A+B","DENDERLEEUW","BURST","Week","Night","00:10","04:40","Linked to coupure nr 57719 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nBuiten dienst zonder impact HKV\r\nZone A + uitbreiding volledig rooster FDD kant Gent\r\nPerron 1-2-3-4-5-6-7-8-9 inbegrepen\r","SAVU_CTRL","Minor_AdHoc"," "," ",57719]
["2024-02-09","2024-02-11","SE",3,"39","A+B","WELKENRAEDT","MONTZEN-GRIL Q","Weekend","Continuous","23:00","20:00","Linked to coupure nr 55128 on line 37 tracks(s) A+B from DOLHAIN-GILEPPE to Y.HAMMERBRUCKE: Maintenance\r\nEntretien manuel et mécanisés des AW de Welkenraedt 01K, 02K, 03AK, 05K/04BK, 07AK/06K, 04AK/24K, 16K/03BK, TO, 07BK, 25K\r\nEntretien manuel et mécan","CTL","Medium"," "," ",55128]
["2024-02-09","2024-02-12","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59555]
["2024-02-09","2024-02-12","CE",3,"96B","*","FOREST-VOITURES","FOREST-MIDI-VOIES 920/926","Weekend","Continuous","22:30","04:30","Onderhoudswerken volgens Onderhoudskalender Area CE, zone FBKI _16, Bundel D.","Autre","Minor_AdHoc","Bundel D volledig buiten dienst en buiten spanning"," ",58636]
["2024-02-09","2024-02-12","NE",1,"12/1","S","Y.DRIEHOEKSTRAAT","Y.SINT-MARIABURG","Weekend","Continuous","23:50","04:00","Linked to coupure nr 59012 on line 27A tracks(s) A+B from LUCHTBAL-ROOSTER S to ANTWERPEN-NOORD-INRIT C1: Oude Landen\r\nproject 304","CTL","Medium"," "," ",59012]
["2024-02-09","2024-02-12","NE",1,"27A","A+B","LUCHTBAL-ROOSTER S","ANTWERPEN-NOORD-INRIT C1","Weekend","Continuous","23:50","04:00","Oude Landen\r\nproject 304","CTL","Medium",null," ",59012]
["2024-02-09","2024-02-12","NE",2,"53A","A+B","MECHELEN","Y.MUIZEN","Weekend","Continuous","23:50","04:00","masterplan mechelen\r\nperronsporen 6 (met L27,L53)","CTL","Medium","spoor 6"," ",58283]
["2024-02-09","2024-02-12","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59896]
["2024-02-09","2024-02-12","SE",2,"162","B","LIBRAMONT","HATRIVAL","Weekend","Continuous","23:00","04:30","Linked to coupure nr 53437 on line 165(1) tracks(s) A+B from LIBRAMONT to BERTRIX: Réalisation de lame d'air et déplacement séparation de phase Rocogne L165(1) - L162","SAVU_CTRL","Minor_AdHoc"," "," ",53437]
["2024-02-09","2024-02-12","SE",2,"165(1)","A+B","LIBRAMONT","BERTRIX","Weekend","Continuous","23:00","04:30","Réalisation de lame d'air et déplacement séparation de phase Rocogne L165(1) - L162","CTL","Medium","L162 SAVU + CTL minimum 6h nuit\r\nCas caténaire: 26814, 815, 818, 820, 821, 822, 824,828, 830, 832,444, 445"," ",53437]
["2024-02-09","2024-02-12","SW",1,"118","A","MONS","Y.LA PAIX","Weekend","Continuous","23:30","04:30","Mise en sevice SIMIS-W entre Mons et Obourg (gare incluse).\r\nTravaux préparatoires","SAVU","Minor_AdHoc",null," ",49158]
["2024-02-09","2024-02-12","SW",2,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Weekend","Continuous","23:00","04:10","Maintenance Z2. 51  P4+\r\n+ Travaux Signalisation PN 107 108 109 114","CTL","Medium"," "," ",48246]
["2024-02-09","2024-02-19","SE",1,"139","A+B","SINT-JORIS-WEERT","WAVRE","AllWeek","Continuous","23:15","05:30","Renouvellement Traverses et Ballast \r\nC75 + P93 entre 12.100 et 19.285","CTL","High","ART de stabilisation à 40km/ du 19/02 au 24/02 (voir CoLT 49783)","Nuits semaine 7 : via L165-166-154-130-124A-L124-L28(1) + L28(1)-L96-ANE (L117 non disponible) + L130A-124A-124\r\nWE 6 : Flux Athus-Anvers via bx/L130 (L130 fermée sam 23h - Dim 15h)\r\nWE 7: via L96-90C-90 +130A-124A-124 + 165-130-124 + 165-130-117-96",47438]
["2024-02-09","2024-02-19","SW",2,"147","A","FLEURUS","AUVELAIS","AllWeek","Continuous","23:15","05:30","Maintenance L147\r\n+ Transfert interrupteurs n° 1 et 6 (PS Fleurus)","CTL","High","opportunité suite fermeture de L139\r\nen complément de la coupure 61108"," ",57931]
["2024-02-09","2024-02-12","CE",1,"161","A/B","WATERMAEL","BAKENBOS","Weekend","Continuous","23:30","04:50","WE SAVU RER Watermael-Bakenbos","SAVU_CTRL","Minor_AdHoc","ART à définir - maximum 2'"," ",49253]
["2024-02-10","2024-02-10","SE",3,"130","A/B","FLAWINNE","MOUSTIER","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49170]
["2024-02-10","2024-02-11","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61579]
["2024-02-10","2024-02-11","NE",3,"27A","A+B","Y.HOLLAND","ANTWERPEN-NOORDERDOKKEN","Weekend","Continuous","00:00","22:00","oosterweelverbinding R0\r\nanticiperende TLO,elke 3 maand \r\ndata zijn voorkeur doch flexibel\r\nvolledig weekend (zat 0h tot zondag 22h)flixebel in werkvenster\r\nsamenwerken met andere diensten mogelijk","CTL","Medium"," "," ",59048]
["2024-02-10","2024-02-11","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60418]
["2024-02-10","2024-02-11","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60418 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60418]
["2024-02-10","2024-02-11","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60418 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60418]
["2024-02-10","2024-02-11","SE",2,"130","A+B","NAMUR","AUVELAIS","Weekend","Continuous","23:40","14:50","Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+Visite de voies A et B Moustier/Auvelais + maintenance infrastructure + contrôles","CTL","Medium","SAVU le samedi en journée\r\nART protection et stabilisation:\r\nLongueur: 100 mètres \r\nVitesse réduite: 40 km/h\r\nDate de mise en vigueur: du 10 au 27/02 à minuit \r\nPerte de temps: \r\nHKV: 2'50\r\nHKM: 2,1"," ",50430]
["2024-02-10","2024-02-11","SE",2,"130/1","A","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Weekend","Continuous","23:40","14:50","Linked to coupure nr 50430 on line 130 tracks(s) A+B from NAMUR to AUVELAIS: Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+Visite de voies A et B Moustier/Auvelais + maintenance infrastructure + contrôles","CTL","Medium"," "," ",50430]
["2024-02-10","2024-02-11","SE",2,"144","A","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Weekend","Continuous","23:40","14:50","Linked to coupure nr 50430 on line 130 tracks(s) A+B from NAMUR to AUVELAIS: Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+Visite de voies A et B Moustier/Auvelais + maintenance infrastructure + contrôles","CTL","Medium"," "," ",50430]
["2024-02-10","2024-02-11","SE",3,"43","A+B","ANGLEUR","RIVAGE-MARCHANDISES","Weekend","Continuous","00:05","17:00","Entretien manuel et mécanisés des PN \r\nEntretien manuel et mécanisés des AW","CTL","Medium",null,"HKM à détourner via les L125A-125-130B-162",55083]
["2024-02-10","2024-02-11","SW",3,"130","A+B","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Weekend","Continuous","23:40","14:50","Maintenance Z19. 51\r\nMini CTL","CTL","Medium"," "," ",49164]
["2024-02-10","2024-02-12","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58003]
["2024-02-10","2024-02-12","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 5+6","CTL","Medium","sporen 5+6"," ",58193]
["2024-02-10","2024-02-12","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:05","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Medium"," "," ",58208]
["2024-02-10","2024-02-12","NE",2,"53","A+B","MECHELEN","Y.HEIKE","Weekend","Continuous","00:05","04:00","masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6","CTL","Medium"," "," ",58322]
["2024-02-10","2024-02-12","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Weekend","Continuous","01:00","04:00","Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\n*weekend 6: indienststelling Stuyvenberg - Bellem: mag niet verplaatst worden","CTL","Medium","TLO 50A+ 50A5+ 50A6 +50D",null,58472]
["2024-02-10","2024-02-12","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58472 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\n*weekend 6: indienststelling Stuyvenberg - Bellem: mag niet verplaatst worden","CTL","Medium"," ",null,58472]
["2024-02-10","2024-02-12","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58472 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\n*weekend 6: indienststelling Stuyvenberg - Bellem: mag niet verplaatst worden","CTL","Medium"," ",null,58472]
["2024-02-10","2024-02-12","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58472 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\n*weekend 6: indienststelling Stuyvenberg - Bellem: mag niet verplaatst worden","CTL","Medium"," ",null,58472]
["2024-02-10","2024-02-12","NW",2,"90","A+B","DENDERLEEUW","Y.NEDERBOELARE","Weekend","Continuous","00:10","04:20","Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P038_01_L90_Geraardsbergen - Ninove_IL\r\nETCS L2-IL_NW_P038_02_L90_Ninove_IL\r\nETCS L2-IL_NW_P038_03_L90_Ninove - Denderleeuw_IL","CTL","Medium",null,"Info Racc.",57545]
["2024-02-10","2024-02-12","SW",1,"78","A+B","BLATON","Y.MAUBRAY","Weekend","Night","23:40","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nTravaux préparatoires","CTL","Minor_AdHoc","Nuit sam/dim 23h40-6h20\r\nNuit dim/lun 23h40-5h"," ",61268]
["2024-02-10","2024-02-19","NE",1,"139","A+B","SINT-JORIS-WEERT","LEUVEN","AllWeek","Continuous","00:01","05:00","Vernieuwing sporen.\r\n\r\nBTS op deze werken ==> zie Colt ID 49890 (+4')","CTL","High",null,null,49889]
["2024-02-10","2024-02-19","NW",1,"53","A+B","LONDERZEEL","MECHELEN","AllWeek","Continuous","06:00","04:00","IDS ETCS - Mechelen-Londerzeel\r\n9 dagen TLO\r\n+\r\nonderhoud EDW\r\n\r\nMeewerken mogelijk zie mail Evelyn\r\n\r\n* Starten op zaterdag morgen CBP","CTL","High"," "," ",53185]
["2024-02-10","2024-02-19","NW",1,"54","A+B","Y.HEIKE","WILLEBROEK","AllWeek","Continuous","06:00","04:00","Linked to coupure nr 53185 on line 53 tracks(s) A+B from LONDERZEEL to MECHELEN: IDS ETCS - Mechelen-Londerzeel\r\n9 dagen TLO\r\n+\r\nonderhoud EDW\r\n\r\nMeewerken mogelijk zie mail Evelyn\r\n\r\n* Starten op zaterdag morgen CBP","CTL","High"," "," ",53185]
["2024-02-10","2024-02-26","SE",2,"130","A+B","NAMUR","AUVELAIS","Weekend","Continuous","23:40","05:00","ART 2min","ART","Minor_AdHoc","Perte de temps: \r\nHKV: 2'\r\nHKM: 2'"," ",58250]
["2024-02-11","2024-02-11","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61607]
["2024-02-11","2024-02-11","NW",2,"50","A+B","DENDERLEEUW","EREMBODEGEM","Weekend","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57724]
["2024-02-11","2024-02-11","NW",2,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Night","00:10","04:40","Linked to coupure nr 57724 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57724]
["2024-02-11","2024-02-11","NW",2,"89","A+B","DENDERLEEUW","BURST","Weekend","Night","00:10","04:40","Linked to coupure nr 57724 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57724]
["2024-02-11","2024-02-11","SE",2,"24","A+B","Y.GLONS","MONTZEN-FRONTIERE","Weekend","Day","06:00","15:45","testen ETCS L2-IL_SE_P030_L24_Glons - Montzen (without border)_ETCS\r\nmeewerken niet mogelijk","CTL","Minor_AdHoc","Pas de circulation possible entre Visé et DB\r\nPas de ciculation entre Longchamps vers DB"," ",61176]
["2024-02-11","2024-02-11","SE",2,"24/1","A+B","Y.LONGCHAMPS","Y.BERNEAU","Weekend","Day","06:00","15:45","Linked to coupure nr 61176 on line 24 tracks(s) A+B from Y.GLONS to MONTZEN-FRONTIERE: testen ETCS L2-IL_SE_P030_L24_Glons - Montzen (without border)_ETCS\r\nmeewerken niet mogelijk","CTL","Minor_AdHoc"," "," ",61176]
["2024-02-12","2024-02-16","CE",2,"26","A+B","Y.ENTREE GROUPE R","Y.NOORD HALLE","Week","Night","23:40","04:00","Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zijtakken: L26/5, L26/4, L26/3, L26/2, L26/1, L36/3, L36/1 en L36C/2","CTL","Minor_AdHoc","TLO L26","Info Racc",59506]
["2024-02-12","2024-02-16","CE",2,"26/1","A+B","Y.KEELBEEK","Y.MACHELEN","Week","Night","23:40","04:00","Linked to coupure nr 59506 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59506]
["2024-02-12","2024-02-16","CE",2,"26/2","A+B","ETTERBEEK","Y.ETTERBEEK","Week","Night","23:40","04:00","Linked to coupure nr 59506 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59506]
["2024-02-12","2024-02-16","CE",2,"26/3","A+B","Y.WATERMAEL","WATERMAEL","Week","Night","23:40","04:00","Linked to coupure nr 59506 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59506]
["2024-02-12","2024-02-16","CE",2,"26/4","A+B","ETTERBEEK","Y.BOONDAEL","Week","Night","23:40","04:00","Linked to coupure nr 59506 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59506]
["2024-02-12","2024-02-16","CE",2,"26/5","A+B","Y.LINKEBEEK-HALLE","Y.LINKEBEEK","Week","Night","23:40","04:00","Linked to coupure nr 59506 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59506]
["2024-02-12","2024-02-16","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","23:55","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2+3"," ",58133]
["2024-02-12","2024-02-16","NE",3,"29","A+B","Y.KRUISBERG","TURNHOUT","Week","Night","23:00","04:40","omvormen 50 HZ SK naar TFSK\r\naanpassen treindetectiesysteem (moet voor 2025)\r\nvernieuwing signalisatie overwegen\r\nomvorming moet gebeuren voor uitrol ETCS L29","CTL","Minor_AdHoc","alternatief E3421"," ",60012]
["2024-02-12","2024-02-16","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58474]
["2024-02-12","2024-02-16","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58474 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58474]
["2024-02-12","2024-02-16","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58474 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58474]
["2024-02-12","2024-02-16","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58474 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58474]
["2024-02-12","2024-02-16","SW",1,"78","A+B","SAINT-GHISLAIN","TOURNAI","Week","Night","22:55","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nTravaux préparatoires\r\n+ Maintenance Z.13.53 + Z4.54 en P3","CTL","Minor_AdHoc",null," ",61266]
["2024-02-12","2024-02-17","NE",3,"12","A+B","ANTWERPEN-NOORDERDOKKEN","Y.HOLLAND","Week","Night","23:25","04:00","onderheid SIG Y luchtbal en onderhoud wissel Y Antwerpen-luchtbal","CTL","Minor_AdHoc","alternatief E2573-E2594"," ",60119]
["2024-02-12","2024-02-17","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59850]
["2024-02-12","2024-02-17","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","22:00","05:15","Travaux SNCF CHA24_0026001 \r\nLille Racc RougeBarre – Bif St André : REGE – RVB, RB/RT et RR\r\n+ Tirage de cable","CTL","Minor_AdHoc",null," ",57934]
["2024-02-13","2024-02-16","NE",2,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Week","Night","00:00","05:00","masterplan Mechelen \r\nafbraak spoor 8\r\nL25+L25N","CTL","Minor_AdHoc","alternatief E2645+E3123+E2623"," ",58173]
["2024-02-13","2024-02-16","NW",3,"53","A+B","LONDERZEEL","DENDERMONDE","Week","Night","00:30","04:30","208312 waterhuishouding L53\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc",null," ",58438]
["2024-02-13","2024-02-17","NW",3,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Week","Night","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Minor_AdHoc",null,"Info Racc",58251]
["2024-02-14","2024-02-14","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60088]
["2024-02-15","2024-02-15","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60104]
["2024-02-16","2024-02-18","SW",2,"130C","A+B","COUILLET","CHATELET-GRIL OUEST","Weekend","Continuous","23:00","18:00","MES à la multimodale à Charleroi","CTL","Medium",null," ",55489]
["2024-02-16","2024-02-19","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59556]
["2024-02-16","2024-02-19","NE",2,"12","A+B","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Weekend","Continuous","23:30","04:00","onderhoud wissels Antwerpen-centraal\r\n\r\nvolledig verdiep +1 (perronsporen 1-6)\r\n\r\nsamen met werkaanvraag L12","CTL","Medium"," "," ",60085]
["2024-02-16","2024-02-19","NE",2,"59/1","A+B","ANTWERPEN-CENTRAAL","Y.NOORD BERCHEM","Weekend","Continuous","23:30","04:00","onderhoud wissels Antwerpen-centraal\r\n\r\nvolledig verdiep +1 (perronsporen 1-6)\r\n\r\nsamen met werkaanvraag L12","CTL","Medium"," "," ",60084]
["2024-02-16","2024-02-19","NE",3,"29","A+B","Y.KRUISBERG","TURNHOUT","Weekend","Continuous","23:00","04:40","omvormen 50 HZ SK naar TFSK\r\naanpassen treindetectiesysteem (moet voor 2025)\r\nvernieuwing signalisatie overwegen\r\nomvorming moet gebeuren voor uitrol ETCS L29","CTL","Medium","alternatief E3421"," ",60018]
["2024-02-16","2024-02-19","NW",3,"53","A+B","DENDERMONDE","LONDERZEEL","Weekend","Continuous","23:40","04:30","208312 waterhuishouding L53\r\n+\r\nonderhoud","CTL","Medium"," "," ",58431]
["2024-02-16","2024-02-19","SE",2,"162","A+B","LEIGNON","HAVERSIN-GARAGE","Weekend","Continuous","22:15","05:00","Travaux Axe 3:\r\nTravaux de traversée de voie + Massification OA","CTL","Medium","Suite arbitrage budgétaire - travaux effectués = Travaux de traversée de voie principalement \r\nART à déterminer"," ",47358]
["2024-02-16","2024-02-19","SW",1,"78","A+B","BLATON","TOURNAI","Weekend","Continuous","22:30","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nWE 3/7","CTL","Medium",null," ",49406]
["2024-02-16","2024-02-19","SE",3,"161","B","RHISNES","GEMBLOUX","Weekend","Continuous","23:00","05:00","réélectrification\r\n + Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","une voie en continu"," ",49708]
["2024-02-17","2024-02-18","SE",2,"24","A+B","VISE-HAUT","MONTZEN-FRONTIERE","Weekend","Continuous","08:00","21:00","Entretien manuel et mécanisés des AW de Y. Berneau, Fourons, Rémersdael, Montzen, Botzelaer\r\nEntretien manuel et mécanisés de la voie courante + Tunnel de Veurs","CTL","Medium","Pas de circulation possible entre Visé et DB\r\nPas de ciculation entre Longchamps vers DB"," ",55964]
["2024-02-17","2024-02-18","SE",2,"24/1","A+B","Y.LONGCHAMPS","Y.BERNEAU","Weekend","Continuous","08:00","21:00","Linked to coupure nr 55964 on line 24 tracks(s) A+B from VISE-HAUT to MONTZEN-FRONTIERE: Entretien manuel et mécanisés des AW de Y. Berneau, Fourons, Rémersdael, Montzen, Botzelaer\r\nEntretien manuel et mécanisés de la voie courante + Tunnel de Veurs","CTL","Medium"," "," ",55964]
["2024-02-17","2024-02-18","SW",2,"96","A+B","BRAINE-LE-COMTE","Y.SOIGNIES","Weekend","Continuous","06:00","16:00","Maintenance Z2.53\r\nMise HS P4","CTL","Medium",null,"HKM à adapter",48649]
["2024-02-17","2024-02-19","CE",2,"26","A+B","Y.RUE DE BRUEL","Y.NOORD HALLE","Weekend","Continuous","00:30","04:00","Massificatie: Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2023.\r\nSporen A en B L26 buiten dienst, inclusief alle zijtakken: L26/5, L26/4, L26/3, ","CTL","Medium","TLO L26 tussen Y Bruulstr en Y Nrd Halle","Info Racc",58564]
["2024-02-17","2024-02-19","CE",2,"26/1","A+B","Y.KEELBEEK","Y.MACHELEN","Weekend","Continuous","00:30","04:00","Linked to coupure nr 58564 on line 26 tracks(s) A+B from Y.RUE DE BRUEL to Y.NOORD HALLE: Massificatie: Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalend","CTL","Medium"," ","Info Racc",58564]
["2024-02-17","2024-02-19","CE",2,"26/2","A+B","ETTERBEEK","Y.ETTERBEEK","Weekend","Continuous","00:30","04:00","Linked to coupure nr 58564 on line 26 tracks(s) A+B from Y.RUE DE BRUEL to Y.NOORD HALLE: Massificatie: Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalend","CTL","Medium"," ","Info Racc",58564]
["2024-02-17","2024-02-19","CE",2,"26/3","A+B","Y.WATERMAEL","WATERMAEL","Weekend","Continuous","00:30","04:00","Linked to coupure nr 58564 on line 26 tracks(s) A+B from Y.RUE DE BRUEL to Y.NOORD HALLE: Massificatie: Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalend","CTL","Medium"," ","Info Racc",58564]
["2024-02-17","2024-02-19","CE",2,"26/4","A+B","ETTERBEEK","Y.BOONDAEL","Weekend","Continuous","00:30","04:00","Linked to coupure nr 58564 on line 26 tracks(s) A+B from Y.RUE DE BRUEL to Y.NOORD HALLE: Massificatie: Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalend","CTL","Medium"," ","Info Racc",58564]
["2024-02-17","2024-02-19","CE",2,"26/5","A+B","Y.LINKEBEEK-HALLE","Y.LINKEBEEK","Weekend","Continuous","00:30","04:00","Linked to coupure nr 58564 on line 26 tracks(s) A+B from Y.RUE DE BRUEL to Y.NOORD HALLE: Massificatie: Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalend","CTL","Medium"," ","Info Racc",58564]
["2024-02-17","2024-02-19","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58004]
["2024-02-17","2024-02-19","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Medium","geen verkeer sporen 1+2+3"," ",58139]
["2024-02-17","2024-02-19","NE",2,"25","A+B","Y.ABEELSTRAAT","MECHELEN","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58189 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, afbraak spoor 8\r\nL25+L25N","CTL","Medium"," "," ",58189]
["2024-02-17","2024-02-19","NE",2,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Weekend","Continuous","00:00","04:00","masterplan Mechelen \r\nafbraak spoor 8\r\nL25+L25N","CTL","Medium","alternatief E2645-E3123-E2623"," ",58174]
["2024-02-17","2024-02-19","NW",2,"123","A+B","GERAARDSBERGEN","ENGHIEN","Weekend","Continuous","00:10","04:20","Indienstname extra seinen voor masterplan ETCS\r\nBeide stations vrij\r\ntestritten op zondag tot FGRA en Edingen in overleg met de regelaars","CTL","Medium",null," ",57590]
["2024-02-17","2024-02-19","NW",2,"75","A+B","GENT-SINT-PIETERS","DEINZE","Weekend","Continuous","00:20","04:00","Buitenwerken\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL","CTL","Medium",null," ",57542]
["2024-02-17","2024-02-19","NW",2,"86","A+B","GAVERE-ASPER","DE PINTE","Weekend","Continuous","00:20","04:00","Linked to coupure nr 57542 on line 75 tracks(s) A+B from GENT-SINT-PIETERS to DEINZE: Buitenwerken\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL","CTL","Medium"," "," ",57542]
["2024-02-17","2024-02-19","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu"," ",47173]
["2024-02-18","2024-02-18","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59977]
["2024-02-18","2024-02-18","NW",2,"50","A+B","DENDERLEEUW","EREMBODEGEM","Weekend","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57725]
["2024-02-18","2024-02-18","NW",2,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Night","00:10","04:40","Linked to coupure nr 57725 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57725]
["2024-02-18","2024-02-18","NW",2,"89","A+B","DENDERLEEUW","BURST","Weekend","Night","00:10","04:40","Linked to coupure nr 57725 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57725]
["2024-02-19","2024-02-23","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Week","Night","23:55","05:20","Omvorming Y Jette Rooster S: voorbereidende nachten\r\nOmvorming Y Jette Rooster R: voorbereidende nachten BVL","CTL","Minor_AdHoc","TLO L50+L60."," ",58717]
["2024-02-19","2024-02-23","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Linked to coupure nr 58717 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Omvorming Y Jette Rooster S: voorbereidende nachten\r\nOmvorming Y Jette Rooster R: voorbereidende nachten BVL","CTL","Minor_AdHoc"," "," ",58717]
["2024-02-19","2024-02-23","NE",1,"139","A+B","SINT-JORIS-WEERT","LEUVEN","Week","Night","22:50","05:15","Vernieuwing sporen.\r\n\r\nvoorbereidende werken massificatie met werken Waver-Ottignies\r\n\r\n+\r\nonderhoud","CTL","Minor_AdHoc","alternatief E5722",null,59974]
["2024-02-19","2024-02-23","NE",2,"19","A+B","MOL","HAMONT","Week","Night","22:00","05:00","vernieuwen houtstukken brug kanaal Dessel-Kwaad Mechelen\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (colt 59851)","CTL","Minor_AdHoc","alternatief ER4321-Z4322-ZM4322"," ",58123]
["2024-02-19","2024-02-23","NE",2,"19","A+B","HAMONT","HAMONT-GRENS","Week","Night","22:00","05:00","Linked to coupure nr 58123 on line 19 tracks(s) A+B from MOL to HAMONT: vernieuwen houtstukken brug kanaal Dessel-Kwaad Mechelen\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (colt 59851)","CTL","Minor_AdHoc"," "," ",58123]
["2024-02-19","2024-02-23","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2+3"," ",58134]
["2024-02-19","2024-02-23","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Week","Night","23:50","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Minor_AdHoc"," "," ",58213]
["2024-02-19","2024-02-23","NE",2,"273","A+B","BALEN-WERKPLAATSEN","VERB.SIBELCO","Week","Night","22:00","05:00","Linked to coupure nr 58123 on line 19 tracks(s) A+B from MOL to HAMONT: vernieuwen houtstukken brug kanaal Dessel-Kwaad Mechelen\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (colt 59851)","CTL","Minor_AdHoc"," "," ",58123]
["2024-02-19","2024-02-24","NE",1,"139","A+B","LEUVEN","SINT-JORIS-WEERT","AllWeek","Continuous","05:30","16:00","BTS\r\nzie werken Colt ID 48989 (vernieuwen sporen)","ART","Minor_AdHoc",null," ",49890]
["2024-02-19","2024-02-24","NE",2,"12","A+B","ANTWERPEN-OOST","Y.HOLLAND","Week","Night","22:30","05:30","onderhoud wissels en sporen te Antwerpen Schijnpoort inrit bundel E inclusief bundelkoppen C,E","Autre","Minor_AdHoc","geen toegang tot bundel E\r\ngeen toegang bundel D kant Y antwerpen-Oost"," ",60218]
["2024-02-19","2024-02-24","SE",2,"139","A+B","SINT-JORIS-WEERT","WAVRE","Week","Night","23:10","05:10","Renouvellement Traverses et Ballast \r\nC75 + P93 entre 12.100 et 19.285\r\nFinitions","CTL","Minor_AdHoc",null,"via L165-166-154-130-124-L124-L28(1) + 96- 28(1) (L130A non disponible)",59404]
["2024-02-19","2024-02-24","SW",1,"78","A+B","SAINT-GHISLAIN","TOURNAI","Week","Night","22:55","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nTravaux préparatoires\r\n+ Déchargement LRS train Robel","CTL","Minor_AdHoc",null," ",61267]
["2024-02-19","2024-03-01","NW",3,"51A","S","ZEEBRUGGE-ROOSTER H","ZEEBRUGGE-STRAND","AllWeek","Continuous","08:00","16:00","Vervanging voegenspoor door LGS tussen AWT 63H en AWT 64H zone 120b","SAVU","High","perron Zeebrugge strand niet bereikbaar  ( Gecombineerd in weekend 9 werken te Brugge omdat Zeebrugge dan sowieso onbereikbaar is.)"," ",60870]
["2024-02-19","2024-03-02","SE",1,"139","A+B","SINT-JORIS-WEERT","WAVRE","AllWeek","Continuous","05:30","05:30","ART 3.2min\r\nstabilisation post-Renouvellement Traverses et Ballast (47438)","ART","Minor_AdHoc","ART de stabilisation 3.2 min"," ",49783]
["2024-02-20","2024-02-23","NW",3,"53","A+B","LONDERZEEL","DENDERMONDE","Week","Night","00:30","04:30","208312 waterhuishouding L53\r\n\r\nR5/R6 niet mogelijk wegens werken op L50","CTL","Minor_AdHoc",null," ",58437]
["2024-02-20","2024-02-24","NW",3,"50","A+B","DENDERLEEUW","EREMBODEGEM","Week","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57721]
["2024-02-20","2024-02-24","NW",3,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:10","04:40","Linked to coupure nr 57721 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57721]
["2024-02-20","2024-02-24","NW",3,"89","A+B","DENDERLEEUW","BURST","Week","Night","00:10","04:40","Linked to coupure nr 57721 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57721]
["2024-02-23","2024-02-26","CE",1,"50","A","JETTE","Y.BOCKSTAEL","Weekend","Continuous","23:55","05:20","Linked to coupure nr 50026 on line 50 tracks(s) A+B from JETTE to TERNAT: Omvorming Y Jette Rooster S","SAVU","Minor_AdHoc"," "," ",50026]
["2024-02-23","2024-02-26","CE",1,"50","A+B","JETTE","TERNAT","Weekend","Continuous","23:55","05:20","Omvorming Y Jette Rooster S","CTL","Medium","TLO L50 +  DOES L60"," ",50026]
["2024-02-23","2024-02-26","CE",1,"60","A","JETTE","ASSE","Weekend","Continuous","23:55","05:20","Linked to coupure nr 50026 on line 50 tracks(s) A+B from JETTE to TERNAT: Omvorming Y Jette Rooster S","SAVU","Minor_AdHoc"," "," ",50026]
["2024-02-23","2024-02-26","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59557]
["2024-02-23","2024-02-26","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","23:50","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Medium","geen verkeer sporen 1+2+3"," ",58140]
["2024-02-23","2024-02-26","NE",2,"53A","A+B","MECHELEN","Y.MUIZEN","Weekend","Continuous","23:50","04:00","masterplan mechelen\r\nperronsporen 5 (met L27,L53)","CTL","Medium","spoor 5"," ",58284]
["2024-02-23","2024-02-26","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59897]
["2024-02-23","2024-02-26","SE",2,"43","A+B","BOMAL","MARLOIE","Weekend","Continuous","23:30","05:00","TUC RAIL / Infrabel\r\ntravaux voies de dépose de l'AS 02i existant et remise en service de la VA exclusivement","CTL","Medium","plus de VB au niveau de Melreux durant une semaine pendant les congés de détente wallonie 2024 (du 26/2/24 au 8/3/24)"," ",59356]
["2024-02-23","2024-02-26","SW",1,"117","A+B","MANAGE","LUTTRE","Weekend","Continuous","23:20","04:40","Linked to coupure nr 49777 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 4/6\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium"," "," ",49777]
["2024-02-23","2024-02-26","SW",1,"124","B","ROUX","OBAIX-BUZET","Weekend","Continuous","23:20","04:40","Linked to coupure nr 49777 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 4/6\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc"," "," ",49777]
["2024-02-23","2024-02-26","SW",1,"124A","A+B","LUTTRE","ROUX","Weekend","Continuous","23:20","04:40","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 4/6\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies II, III, IV et V en gare de Luttre inaccessible en continu\r\nFaisceau accessoire en gare de Luttre inaccessible en continu"," ",49777]
["2024-02-24","2024-02-25","NW",2,"50","A+B","Y.OOST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Night","21:00","05:00","Vervangen isolatoren I102-103 (ombouw ACEC)\r\n\r\nY West volledig BD en BS voor 8uren\r\nL50+50E+58","CTL","Minor_AdHoc"," "," ",59221]
["2024-02-24","2024-02-25","NW",2,"50E","A+B","Y.OOST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Night","21:00","05:00","Linked to coupure nr 59221 on line 50 tracks(s) A+B from Y.OOST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Vervangen isolatoren I102-103 (ombouw ACEC)\r\n\r\nY West volledig BD en BS voor 8uren\r\nL50+50E+58","CTL","Minor_AdHoc"," "," ",59221]
["2024-02-24","2024-02-25","NW",2,"58/1","A+B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Night","21:00","05:00","Linked to coupure nr 59221 on line 50 tracks(s) A+B from Y.OOST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Vervangen isolatoren I102-103 (ombouw ACEC)\r\n\r\nY West volledig BD en BS voor 8uren\r\nL50+50E+58","CTL","Minor_AdHoc"," "," ",59221]
["2024-02-24","2024-02-25","SW",2,"96","A+B","MONS","QUEVY-FRONTIERE","Weekend","Continuous","23:30","17:00","Maintenance Z6.53 en P4\r\n+ Z.11.53","CTL","Medium","CTL L96 + L97\r\n1 voie Hs en gare de Mons les autres sont accessibles en CDS","L75 libre pour accéder à Gent",46911]
["2024-02-24","2024-02-25","SW",2,"97","A+B","MONS","SAINT-GHISLAIN","Weekend","Continuous","23:30","17:00","Linked to coupure nr 46911 on line 96 tracks(s) A+B from MONS to QUEVY-FRONTIERE: Maintenance Z6.53 en P4\r\n+ Z.11.53","CTL","Medium"," ","L75 libre pour accéder à Gent",46911]
["2024-02-24","2024-02-25","SW",3,"130","B","CHATELET-GRIL EST","CHATELET-GRIL OUEST","Weekend","Continuous","22:30","22:00","Maintenance Z17. 51\r\nFaisceau de Chatelet","SAVU","Minor_AdHoc","Mise hors service en une zone (= Zone 17), voici les détails:\r\n- L130 Voie B entre F4-I. 20 et DX-J. 20;\r\nM-I.20 + J-I.20 + PC-I. 20 (faisceau A); + voie 320\r\n- F6-L. 20 + FX5-I. 20 (L130C en gare de Châtelet);\r\n- GC353-J. 20 + GC354-J. 20 + GC355-J. 20","HKM à adapter",55053]
["2024-02-24","2024-02-26","NE",1,"12","A+B","ESSEN","KALMTHOUT","Weekend","Night","00:00","05:00","vernieuwen wissels Essen +onderhoud","CTL","Minor_AdHoc"," "," ",58780]
["2024-02-24","2024-02-26","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58005]
["2024-02-24","2024-02-26","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","onderhoud SIG+onderhoud wissels Y Arendstraat en Antwerpen Centraal -2\r\n\r\nbeveiliging L27 overdag door ATW-TX s'nachts buitendienststelling","CTL","Medium"," "," ",59707]
["2024-02-24","2024-02-26","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:00","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Medium"," "," ",58209]
["2024-02-24","2024-02-26","NE",3,"27","A+B","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL","Weekend","Night","00:40","04:20","onderhoud SIG + wissels Y arendstraat\r\n\r\nhangt samen met colt 59707 ===beveiliging werken L25","CTL","Minor_AdHoc","nog te bepalen"," ",59728]
["2024-02-24","2024-02-26","NW",1,"51","A+B","BRUGGE","Y.BLAUWE TOREN","Weekend","Continuous","01:00","04:00","plaatsen + overnemen seinkeet","CTL","Medium","TLO L51+51A\r\nGeen verkeer vanaf Brugge naar de Kust >> L50A wel vrij"," ",49530]
["2024-02-24","2024-02-26","NW",1,"51A","A+B","Y.BLAUWE TOREN","Y.TER DOEST","Weekend","Continuous","01:00","04:00","Linked to coupure nr 49530 on line 51 tracks(s) A+B from BRUGGE to Y.BLAUWE TOREN: plaatsen + overnemen seinkeet","CTL","Medium"," "," ",49530]
["2024-02-24","2024-02-26","NW",1,"51B","A+B","Y.DUDZELE","Y.BOUDEWIJNKANAAL","Weekend","Continuous","01:00","04:00","Linked to coupure nr 49530 on line 51 tracks(s) A+B from BRUGGE to Y.BLAUWE TOREN: plaatsen + overnemen seinkeet","CTL","Medium"," "," ",49530]
["2024-02-24","2024-02-26","NW",2,"51","*","BLANKENBERGE","Y.BLAUWE TOREN","Weekend","Continuous","01:00","04:00","Blankenberge station volledig BS en BS voor vervangen I10","CTL","Medium"," "," ",58616]
["2024-02-24","2024-02-26","NW",2,"51A","A+B","Y.BLAUWE TOREN","ZEEBRUGGE-ROOSTER H","Weekend","Continuous","01:00","04:00","Linked to coupure nr 60164 on line 51B tracks(s) A+B from Y.DUDZELE to KNOKKE: onderhoudsweekend\r\n(als gevolg van Renovatie brugdekken)\r\n+\r\nR7 14.00-22.00\r\n- Bundel Voorhaven West zone nr. 129: er worden max 3 sporen vrij gevraagd, overige sporen mogen ","CTL","Medium"," ","Info Racc",60164]
["2024-02-24","2024-02-26","NW",2,"51B","A+B","Y.DUDZELE","KNOKKE","Weekend","Continuous","01:00","04:00","onderhoudsweekend\r\n(als gevolg van Renovatie brugdekken)\r\n+\r\nR7 14.00-22.00\r\n- Bundel Voorhaven West zone nr. 129: er worden max 3 sporen vrij gevraagd, overige sporen mogen bezet blijven\r\n- Zeebrugge strand blijft bereikbaar","CTL","Medium",null,"Info Racc",60164]
["2024-02-24","2024-02-26","NW",2,"90","A+B","DENDERLEEUW","Y.NEDERBOELARE","Weekend","Continuous","00:10","04:20","Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P038_01_L90_Geraardsbergen - Ninove_IL\r\nETCS L2-IL_NW_P038_02_L90_Ninove_IL\r\nETCS L2-IL_NW_P038_03_L90_Ninove - Denderleeuw_IL\r\n\r\n*R6 06.00u - L90 niet in CBP","CTL","Medium",null,"Info Racc.",57546]
["2024-02-24","2024-02-26","SE",1,"24/1","A+B","VISE","Y.BERNEAU","Weekend","Continuous","00:20","04:40","Linked to coupure nr 55122 on line 40 tracks(s) A+B from FROIDMONT to VISE-FRONTIERE: Entretien manuel et mécanisés des AW Bressoux / Visé-Bas\r\nEntretien manuel et mécanisés de la voie courante","CTL","Medium"," "," ",55122]
["2024-02-24","2024-02-26","SE",1,"40","A+B","FROIDMONT","VISE-FRONTIERE","Weekend","Continuous","00:20","04:40","Entretien manuel et mécanisés des AW Bressoux / Visé-Bas\r\nEntretien manuel et mécanisés de la voie courante","CTL","Medium","L40 + L24/1"," ",55122]
["2024-02-24","2024-02-26","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu"," ",47174]
["2024-02-24","2024-03-11","SW",1,"78","A/B","BLATON","Y.MAUBRAY","AllWeek","Continuous","06:00","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs","SAVU_CTRL","High","SAVU jour et CTL nuit (22h50-05h00) + CTL weekend\r\nART VB du 4/03 au 10/03 inclus\r\nART VB du 11/03 au 17/03 inclus\r\nART stabilisation (40/60):\r\nHKV\t: 7.05/4.15\r\nHKM : 6.50/3.00"," ",57919]
["2024-02-24","2024-02-25","SE",3,"161","A/B","OTTIGNIES","GEMBLOUX","Weekend","Day","08:00","16:00","Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles + 1/2h sas Rhisnes","SAVU","Minor_AdHoc","SAVU alternatif entre 08h00 et 16h00"," ",48949]
["2024-02-25","2024-02-25","NE",1,"12/1","S","Y.DRIEHOEKSTRAAT","Y.SINT-MARIABURG","Weekend","Day","06:00","17:30","Linked to coupure nr 59011 on line 27A tracks(s) A+B from LUCHTBAL-ROOSTER S to ANTWERPEN-NOORD-INRIT C1: Oude Landen\r\nproject 304","CTL","Minor_AdHoc"," "," ",59011]
["2024-02-25","2024-02-25","NE",1,"27A","A+B","LUCHTBAL-ROOSTER S","ANTWERPEN-NOORD-INRIT C1","Weekend","Day","06:00","17:30","Oude Landen\r\nproject 304","CTL","Minor_AdHoc",null," ",59011]
["2024-02-25","2024-02-25","NW",2,"50","A+B","DENDERLEEUW","EREMBODEGEM","Weekend","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57726]
["2024-02-25","2024-02-25","NW",2,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Night","00:10","04:40","Linked to coupure nr 57726 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57726]
["2024-02-25","2024-02-25","NW",2,"89","A+B","DENDERLEEUW","BURST","Weekend","Night","00:10","04:40","Linked to coupure nr 57726 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57726]
["2024-02-25","2024-02-25","SE",2,"24","A+B","Y.GLONS","MONTZEN-FRONTIERE","Weekend","Day","06:00","15:45","testen ETCS L2-IL_SE_P030_L24_Glons - Montzen (without border)_ETCS\r\nmeewerken niet mogelijk","CTL","Minor_AdHoc","Pas de circulation possible entre Visé et DB\r\nPas de ciculation entre Longchamps vers DB"," ",61177]
["2024-02-25","2024-02-25","SE",2,"24/1","A+B","Y.LONGCHAMPS","Y.BERNEAU","Weekend","Day","06:00","15:45","Linked to coupure nr 61177 on line 24 tracks(s) A+B from Y.GLONS to MONTZEN-FRONTIERE: testen ETCS L2-IL_SE_P030_L24_Glons - Montzen (without border)_ETCS\r\nmeewerken niet mogelijk","CTL","Minor_AdHoc"," "," ",61177]
["2024-02-26","2024-02-26","SE",3,"130","A/B","NAMUR","FLAWINNE","Week","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49046]
["2024-02-26","2024-03-01","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Week","Night","23:55","05:20","Omvorming Y Jette Rooster S: voorbereidende nachten\r\nOmvorming Y Jette Rooster R: voorbereidende nachten BVL","CTL","Minor_AdHoc","TLO L50+L60."," ",50027]
["2024-02-26","2024-03-01","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Linked to coupure nr 50027 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Omvorming Y Jette Rooster S: voorbereidende nachten\r\nOmvorming Y Jette Rooster R: voorbereidende nachten BVL","CTL","Minor_AdHoc"," "," ",50027]
["2024-02-26","2024-03-01","NE",1,"139","A+B","SINT-JORIS-WEERT","LEUVEN","Week","Night","22:50","05:15","Vernieuwing sporen.\r\n\r\nafwerking  werken massificatie met werken Waver-Ottignies\r\n\r\n+\r\nonderhoud","CTL","Minor_AdHoc","alternatief E7572",null,58910]
["2024-02-26","2024-03-01","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2+3"," ",58135]
["2024-02-26","2024-03-02","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59852]
["2024-02-26","2024-03-02","SE",2,"139","A+B","SINT-JORIS-WEERT","WAVRE","Week","Night","23:10","05:10","Renouvellement Traverses et Ballast \r\nC75 + P93 entre 12.100 et 19.285\r\nFinitions","CTL","Minor_AdHoc",null,"Nuits semaine 9 : via L165-166-154-130-L124-L26 + 96- 26 + L130A",59405]
["2024-02-26","2024-03-09","CE",1,"50","A+B","JETTE","TERNAT","AllWeek","Continuous","05:20","05:20","Stabilisatie-BTS","ART","Minor_AdHoc","BTS 60 km/h: HKV=1,05' / HKM= 4'"," ",56099]
["2024-02-26","2024-03-09","SE",2,"43","A","BOMAL","MARLOIE","AllWeek","Continuous","05:00","05:00","ART de stabilisation à 60km/h en VA suite travaux voies de dépose de l'AS 02i \r\ncf. colt 59356","ART","Minor_AdHoc","HKM: 1'\r\nHKV: 1'"," ",63072]
["2024-02-26","2024-03-09","SE",2,"43","B","BOMAL","MARLOIE","AllWeek","Continuous","23:30","05:00","TUC RAIL / Infrabel\r\ntravaux voies de dépose de l'AS 02i existant et remise en service de la VA exclusivement\r\nRq 333 : A préciser\r\nCar voie unique entre Bomal - Marloie et pas de CTL demandée\r\nEst-ce uniquement la voie d'évitement de Melreux HS?\r\n+ ART","SAVU","High","plus de VB au niveau de Melreux durant une semaine pendant les congés de détente wallonie 2024 (du 26/2/24 au 8/3/24)"," ",59435]
["2024-02-27","2024-03-01","NE",2,"25","A+B","Y.ABEELSTRAAT","MECHELEN","Week","Night","00:00","05:00","Linked to coupure nr 58188 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, afbraak spoor 8\r\nL25+L25N","CTL","Minor_AdHoc"," ","Info Racc",58188]
["2024-02-27","2024-03-02","NE",2,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Week","Night","00:00","04:00","masterplan Mechelen \r\nafbraak spoor 8\r\nL25+L25N","CTL","Minor_AdHoc","alternatief E2645-E3123-E2623"," ",58175]
["2024-02-29","2024-02-29","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55942]
["2024-02-29","2024-03-04","SW",1,"118","A+B","MONS","Y.LA PAIX","Weekend","Continuous","23:30","04:30","Mise en service EBP/PLP - L118 Mons - Y LaPaix - WE 3jours\r\n+ préparation Mise en sevice SIMIS-W entre Mons et Obourg (gare incluse).\r\nTravaux préparatoires\r\nRq 333 : incompatible C75 L78\r\n+ 3 jours hors férié\r\nNT 10/03/22 : Géraldine me revient sur à m","CTL","Medium",null," ",49159]
["2024-03-01","2024-03-04","CE",1,"50","A","JETTE","Y.BOCKSTAEL","Weekend","Continuous","23:55","05:20","Linked to coupure nr 50025 on line 50 tracks(s) A+B from JETTE to TERNAT: Omvorming Y Jette Rooster S","SAVU","Minor_AdHoc"," "," ",50025]
["2024-03-01","2024-03-04","CE",1,"50","A+B","JETTE","TERNAT","Weekend","Continuous","23:55","05:20","Omvorming Y Jette Rooster S","CTL","Medium","TLO L50 +  DOES L60"," ",50025]
["2024-03-01","2024-03-04","CE",1,"60","A","JETTE","ASSE","Weekend","Continuous","23:55","05:20","Linked to coupure nr 50025 on line 50 tracks(s) A+B from JETTE to TERNAT: Omvorming Y Jette Rooster S","SAVU","Minor_AdHoc"," "," ",50025]
["2024-03-01","2024-03-04","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59558]
["2024-03-01","2024-03-04","CE",2,"96B","*","FOREST-VOITURES-QUAI SERVICE","FOREST-VOITURES","Weekend","Continuous","22:30","04:30","Onderhoudswerken volgen Onderhoudskalender Area CE, zone FBKI_13, Bundel Expo.\r\nVolledige bundel ter beschikking voor diverse onderhoudswerken.","Autre","Minor_AdHoc","Bundel Expo volledig buiten dienst","Néant",58630]
["2024-03-01","2024-03-04","NE",2,"10","A","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58673 on line 10 tracks(s) B from Y.KOESTRAAT to Y.HAZOP: aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc"," "," ",58673]
["2024-03-01","2024-03-04","NE",2,"10","B","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","CTL","Medium","DOES op spoor A L10 / bundel Zuid afgesloten"," ",58673]
["2024-03-01","2024-03-04","NW",1,"75","A+B","KORTRIJK","MOUSCRON","Weekend","Continuous","23:10","04:00","TLO-Weekend voor onderhouds werken","CTL","Medium",null," ",47299]
["2024-03-01","2024-03-04","NW",3,"50","A+B","DENDERLEEUW","JETTE","Weekend","Continuous","23:55","05:20","Onderhoudswerken (+ kleine vernieuwingswerken)","CTL","Medium",null," ",60810]
["2024-03-01","2024-03-04","NW",3,"60","A","JETTE","ASSE","Weekend","Continuous","23:55","05:20","Linked to coupure nr 60810 on line 50 tracks(s) A+B from DENDERLEEUW to JETTE: Onderhoudswerken (+ kleine vernieuwingswerken)","SAVU","Minor_AdHoc"," "," ",60810]
["2024-03-01","2024-03-04","SE",2,"165(1)","A+B","LIBRAMONT","BERTRIX","Weekend","Continuous","23:00","04:30","ETCS Libramont - Bertrix.","CTL","Medium","Pas de massification possible"," ",59115]
["2024-03-01","2024-03-04","SE",2,"166","A/B","HOUYET","BEAURAING","Weekend","Continuous","23:00","05:00","Massification travaux pour adaptation du tracé\r\nEntretien AS , traitement zone boueuse","CTL","Medium",null," ",57698]
["2024-03-01","2024-03-04","SE",2,"43","A+B","BOMAL","MARLOIE","Weekend","Continuous","23:30","05:00","TUC RAIL\r\ntravaux caténaire ZN Melreux\r\néquipement nouvelle VB\r\nenlèvement caténaire sur 02i ancien\r\nsignalisation 2 prestations pour règlage de CV et MES (dont une prestations seul)","CTL","Medium",null," ",59357]
["2024-03-01","2024-03-04","SE",2,"49","S","WELKENRAEDT","EUPEN","Weekend","Continuous","22:40","05:30","Renouvellement AS01R et adaptation du tracé","CTL","Medium","CTL L49 - WE n°1\r\nART stabilisation 1 minute jusqu'au 21/03"," ",47010]
["2024-03-01","2024-03-04","SW",1,"117","A+B","MANAGE","LUTTRE","Weekend","Continuous","23:20","04:40","Linked to coupure nr 49778 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 5/6\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium"," "," ",49778]
["2024-03-01","2024-03-04","SW",1,"124","B","ROUX","OBAIX-BUZET","Weekend","Continuous","23:20","04:40","Linked to coupure nr 49778 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 5/6\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc"," "," ",49778]
["2024-03-01","2024-03-04","SW",1,"124A","A+B","LUTTRE","ROUX","Weekend","Continuous","23:20","04:40","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 5/6\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies II, III, IV et V en gare de Luttre inaccessible en continu\r\nFaisceau accessoire en gare de Luttre inaccessible en continu"," ",49778]
["2024-03-01","2024-03-04","SW",1,"78","A+B","BLATON","TOURNAI","Weekend","Continuous","22:30","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nWE 5/7","CTL","Medium",null," ",49408]
["2024-03-01","2024-03-04","SW",2,"140","A+B","MARCINELLE","FLEURUS","Weekend","Continuous","23:00","05:00","Maintenance Z4. 51  P4+\r\n+ Renouvellement complet des PN\r\n+ Transfert interrupteurs 2, 3 et 4 (PS de Fleurus)","CTL","Medium",null,"HKM à adapter",49116]
["2024-03-01","2024-03-05","SE",2,"166","A","HOUYET","BEAURAING","Week","Continuous","05:00","05:00","Massification travaux pour adaptation du tracé pour augmenter la vitesse","SAVU","Minor_AdHoc","Voie A HS entre Houyet et Beauraing\r\nART de stabilisation d'1,5' vitesse 60km/h du 05/03/24 au 22/03/24"," ",60440]
["2024-03-01","2024-03-05","SE",2,"166","A+B","HOUYET","BEAURAING","Weekend","Continuous","05:00","05:00","CR L166 2024\r\nMassification travaux pour adaptation du tracé pour augmenter la vitesse","CTL","Medium",null," ",60551]
["2024-03-01","2024-03-04","SE",1,"161","A+B","BRUXELLES-LUXEMBOURG","OTTIGNIES","Weekend","Continuous","23:30","04:50","WE CTL RER Watermael - Ottignies\r\nLivraison Kirow\r\n+ Visite voies A/B + maintenance infrastructure + contrôles","CTL","Medium","ART maximum 2'"," ",49261]
["2024-03-02","2024-03-03","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59432]
["2024-03-02","2024-03-03","NW",2,"202B","S","Y.EIVOORDE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Night","23:45","07:00","Linked to coupure nr 60385 on line 202B/1 tracks(s) S from Y.PELIKAAN to ZEEBRUGGE-BUNDEL PELIKAAN: R-419030-01\r\n\r\nOnderhoud werkveld 3421-25\r\n\r\nBundel Pelikaan en Bundel Ramskapelle","CTL","Minor_AdHoc"," ","Info Racc",60385]
["2024-03-02","2024-03-03","NW",2,"202B/1","S","Y.PELIKAAN","ZEEBRUGGE-BUNDEL PELIKAAN","Weekend","Night","23:45","07:00","R-419030-01\r\n\r\nOnderhoud werkveld 3421-25\r\n\r\nBundel Pelikaan en Bundel Ramskapelle","CTL","Minor_AdHoc"," ","Info Racc",60385]
["2024-03-02","2024-03-03","NW",2,"202B/2","S","ZEEBRUGGE-BUNDEL PELIKAAN","ZEEBRUGGE-BUNDEL PELIKAAN","Weekend","Night","23:45","07:00","Linked to coupure nr 60385 on line 202B/1 tracks(s) S from Y.PELIKAAN to ZEEBRUGGE-BUNDEL PELIKAAN: R-419030-01\r\n\r\nOnderhoud werkveld 3421-25\r\n\r\nBundel Pelikaan en Bundel Ramskapelle","CTL","Minor_AdHoc"," ","Info Racc",60385]
["2024-03-02","2024-03-03","NW",2,"50","A+B","Y.OOST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Night","21:00","05:00","Vervangen isolatoren I104-105 (ombouw ACEC)\r\n+\r\noplossing dansende paal 54/38\r\n\r\n\r\nY West volledig BD en BS voor 8uren\r\nL50+50E+58","CTL","Minor_AdHoc"," "," ",59224]
["2024-03-02","2024-03-03","NW",2,"50E","A+B","Y.OOST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Night","21:00","05:00","Linked to coupure nr 59224 on line 50 tracks(s) A+B from Y.OOST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Vervangen isolatoren I104-105 (ombouw ACEC)\r\n+\r\noplossing dansende paal 54/38\r\n\r\n\r\nY West volledig BD en BS voor 8uren\r\nL50+50E+58","CTL","Minor_AdHoc"," "," ",59224]
["2024-03-02","2024-03-03","NW",2,"58/1","A+B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Night","21:00","05:00","Linked to coupure nr 59224 on line 50 tracks(s) A+B from Y.OOST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Vervangen isolatoren I104-105 (ombouw ACEC)\r\n+\r\noplossing dansende paal 54/38\r\n\r\n\r\nY West volledig BD en BS voor 8uren\r\nL50+50E+58","CTL","Minor_AdHoc"," "," ",59224]
["2024-03-02","2024-03-03","SE",3,"165","A+B","BERTRIX","FLORENVILLE","Weekend","Continuous","23:00","15:00","Interventions Programmées","CTL","Medium",null," ",46685]
["2024-03-02","2024-03-04","NE",1,"12","A+B","KAPELLEN","Y.LUCHTBAL","Weekend","Continuous","00:00","04:00","herelectrificatie","CTL","Medium"," "," ",58057]
["2024-03-02","2024-03-04","NE",1,"12","A+B","ESSEN-GRENS","Y.LUCHTBAL","Weekend","Continuous","01:00","04:30","VERNIEUWING WISSELS ESSEN\r\nWij voorzien voorjaar 2024 om niet in het vaarwater te zitten van de grote werken op het Duitse net (najaar 2024 tot voorjaar 2026).","CTL","Medium"," "," ",49862]
["2024-03-02","2024-03-04","NE",1,"12","A+B","ESSEN","KALMTHOUT","Weekend","Continuous","01:00","04:30","vernieuwen wissels Essen +onderhoud","CTL","Medium"," "," ",58781]
["2024-03-02","2024-03-04","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58006]
["2024-03-02","2024-03-04","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Medium","geen verkeer sporen 1+2+3"," ",58141]
["2024-03-02","2024-03-04","NW",1,"51","A+B","BRUGGE","Y.BLAUWE TOREN","Weekend","Continuous","01:00","04:00","R417944\r\nplaatsen + overnemen seinkeet","CTL","Medium","R417944\r\nTLO L51+51A\r\nGeen verkeer vanaf Brugge naar de Kust >> L50A wel vrij"," ",49531]
["2024-03-02","2024-03-04","NW",1,"51A","A+B","Y.BLAUWE TOREN","Y.TER DOEST","Weekend","Continuous","01:00","04:00","Linked to coupure nr 49531 on line 51 tracks(s) A+B from BRUGGE to Y.BLAUWE TOREN: R417944\r\nplaatsen + overnemen seinkeet","CTL","Medium"," "," ",49531]
["2024-03-02","2024-03-04","NW",1,"51B","A+B","Y.DUDZELE","Y.BOUDEWIJNKANAAL","Weekend","Continuous","01:00","04:00","Linked to coupure nr 49531 on line 51 tracks(s) A+B from BRUGGE to Y.BLAUWE TOREN: R417944\r\nplaatsen + overnemen seinkeet","CTL","Medium"," "," ",49531]
["2024-03-02","2024-03-04","NW",2,"122","A+B","Y.MELLE","ZOTTEGEM","Weekend","Continuous","00:10","04:50","Vernieuwen brug De Metstraat (Zottegem-Ymelle en Denderleeuw Zottegem)\r\n+\r\nOnderhoud Denderleeuw-Burst \r\n\r\nverplaatst wegens lange TLO FDD","CTL","Medium",null," ",59183]
["2024-03-02","2024-03-04","NW",2,"51","*","BLANKENBERGE","Y.BLAUWE TOREN","Weekend","Continuous","01:00","04:00","Blankenberge station volledig BS en BS voor vervangen I14","CTL","Medium"," "," ",58617]
["2024-03-02","2024-03-04","NW",2,"51A","A+B","Y.BLAUWE TOREN","ZEEBRUGGE-STRAND","Weekend","Continuous","01:00","04:00","Linked to coupure nr 60165 on line 51B tracks(s) A+B from Y.DUDZELE to KNOKKE: onderhoudsweekend\r\n(als gevolg van Renovatie brugdekken)","CTL","Medium"," ","Info Racc",60165]
["2024-03-02","2024-03-04","NW",2,"51B","A+B","Y.DUDZELE","KNOKKE","Weekend","Continuous","01:00","04:00","onderhoudsweekend\r\n(als gevolg van Renovatie brugdekken)","CTL","Medium",null,"Info Racc",60165]
["2024-03-02","2024-03-04","NW",2,"89","A+B","DENDERLEEUW","ZOTTEGEM","Weekend","Continuous","00:10","04:50","Linked to coupure nr 59183 on line 122 tracks(s) A+B from Y.MELLE to ZOTTEGEM: Vernieuwen brug De Metstraat (Zottegem-Ymelle en Denderleeuw Zottegem)\r\n+\r\nOnderhoud Denderleeuw-Burst \r\n\r\nverplaatst wegens lange TLO FDD","CTL","Medium"," "," ",59183]
["2024-03-03","2024-03-03","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59979]
["2024-03-03","2024-03-03","NW",2,"50","A+B","DENDERLEEUW","EREMBODEGEM","Weekend","Night","00:10","04:40","Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57727]
["2024-03-03","2024-03-03","NW",2,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Night","00:10","04:40","Linked to coupure nr 57727 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57727]
["2024-03-03","2024-03-03","NW",2,"89","A+B","DENDERLEEUW","BURST","Weekend","Night","00:10","04:40","Linked to coupure nr 57727 on line 50 tracks(s) A+B from DENDERLEEUW to EREMBODEGEM: Masterplan Denderleeuw - dienst bovenleiding\r\nZone E \r\nVolledig rooster FDD kant Gent\r\nStation + bundel buiten dienst + buiten spanning","CTL","Minor_AdHoc"," "," ",57727]
["2024-03-03","2024-03-03","SE",2,"24","A+B","Y.GLONS","MONTZEN-FRONTIERE","Weekend","Day","06:00","15:45","testen ETCS L2-IL_SE_P030_L24_Glons - Montzen (without border)_ETCS\r\nmeewerken niet mogelijk","CTL","Minor_AdHoc","Pas de circulation possible entre Visé et DB\r\nPas de ciculation entre Longchamps vers DB"," ",61178]
["2024-03-03","2024-03-03","SE",2,"24/1","A+B","Y.LONGCHAMPS","Y.BERNEAU","Weekend","Day","06:00","15:45","Linked to coupure nr 61178 on line 24 tracks(s) A+B from Y.GLONS to MONTZEN-FRONTIERE: testen ETCS L2-IL_SE_P030_L24_Glons - Montzen (without border)_ETCS\r\nmeewerken niet mogelijk","CTL","Minor_AdHoc"," "," ",61178]
["2024-03-04","2024-03-08","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2+3"," ",58136]
["2024-03-04","2024-03-08","NE",2,"27","A+B","Y.BERCHEM-STADION","Y.LIERSESTEENWEG","Week","Night","23:35","04:35","Vernieuwing van  Y-Drabstraat","CTL","Minor_AdHoc","Alternatief E2894-E1996-E1972"," ",58930]
["2024-03-04","2024-03-08","NE",3,"29","A+B","Y.KRUISBERG","TURNHOUT","Week","Night","23:00","04:40","omvormen 50 HZ SK naar TFSK\r\naanpassen treindetectiesysteem (moet voor 2025)\r\nvernieuwing signalisatie overwegen\r\nomvorming moet gebeuren voor uitrol ETCS L29","CTL","Minor_AdHoc","alternatief E3421"," ",60014]
["2024-03-04","2024-03-08","NW",3,"59B","*","GENT-ZEEHAVEN","GENT-ZEEHAVEN","Week","Continuous","05:00","21:00","Vernieuwen wissels Bundels Gent Zeehaven\r\nBundel E buiten dienst van SP 17 tot SP 24\r\nR5/R6 in weekend","Autre","Minor_AdHoc"," ","info rac",60479]
["2024-03-04","2024-03-09","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Week","Night","23:55","05:20","Omvorming Y Jette Rooster S: voorbereidende nachten\r\nOmvorming Y Jette Rooster R: voorbereidende nachten BVL","CTL","Minor_AdHoc","TLO L50+L60."," ",50029]
["2024-03-04","2024-03-09","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Linked to coupure nr 50029 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Omvorming Y Jette Rooster S: voorbereidende nachten\r\nOmvorming Y Jette Rooster R: voorbereidende nachten BVL","CTL","Minor_AdHoc"," "," ",50029]
["2024-03-04","2024-03-09","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59853]
["2024-03-04","2024-03-09","NW",1,"75","A+B","KORTRIJK","MOUSCRON","Week","Night","23:10","04:00","Afwerkingsnachten na TLO-Weekend voor onderhouds werken\r\nminimum van 2 weekends per jaar, 1 weekend maart/april + 1 weekend oktober/november\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken mogelijk","CTL","Minor_AdHoc"," "," ",47666]
["2024-03-04","2024-03-15","NW",3,"51A","*","ZEEBRUGGE-STRAND","ZEEBRUGGE-VOORHAVEN-WEST","AllWeek","Continuous","08:00","16:00","Sanering ballast sp 506 thv perron Zeebrugge strand  Zone 120","SAVU","High"," "," ",60591]
["2024-03-04","2024-03-18","SW",1,"78","A/B","BLATON","Y.MAUBRAY","AllWeek","Continuous","06:00","05:00","ART\r\nBlaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs","ART","Minor_AdHoc","ART VA du 4/03 au 10/03 inclus\r\nART VB du 11/03 au 17/03 inclus\r\nART stabilisation 60km/h : 5min"," ",61379]
["2024-03-04","2024-03-21","SE",2,"49","S","WELKENRAEDT","EUPEN","AllWeek","Continuous","05:30","05:30","ART 1min\r\nRenouvellement AS01R et adaptation du tracé","ART","Minor_AdHoc",null," ",61412]
["2024-03-05","2024-03-22","SE",2,"166","A+B","HOUYET","BEAURAING","AllWeek","Continuous","05:00","23:00","Massification travaux pour adaptation du tracé\r\nART 1.5min","ART","Minor_AdHoc","ART de stabilisation d'1,5' vitesse 60km/h du 05/03/24 au 22/03/24"," ",60550]
["2024-03-06","2024-03-06","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60089]
["2024-03-07","2024-03-07","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60105]
["2024-03-07","2024-03-08","NW",3,"50","B","DENDERLEEUW","AALST","Week","Night","23:45","04:45","Omvorming rooster Denderleeuw volgens richtplan.\r\nLossen Kirow\r\n\r\nBuiten dienst ; SP I tem VII  + 1ste doorsteek (AW75AF-74AF-75BF-73AF-74BF-72AF-73BF-71AF-72BF)\r\n\r\nDoorrit L90 via SP VIII+IX naar SP A L50\r\n\r\nR5/R6 in weekend TLO","SAVU","Minor_AdHoc"," "," ",60924]
["2024-03-08","2024-03-11","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59559]
["2024-03-08","2024-03-11","NE",1,"139","A+B","SINT-JORIS-WEERT","LEUVEN","Weekend","Continuous","23:55","05:00","Vernieuwing sporen.\r\n\r\n+\r\nonderhoud","CTL","Medium",null,null,58913]
["2024-03-08","2024-03-11","NE",1,"27","A+B","Y.BERCHEM-STADION","Y.LIERSESTEENWEG","Weekend","Continuous","23:35","04:35","Vernieuwing van de wissels Y-Drabstraat","CTL","Medium","Alternatief E2894-E1996-E1972"," ",33774]
["2024-03-08","2024-03-11","NE",2,"10","A","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58674 on line 10 tracks(s) B from Y.KOESTRAAT to Y.HAZOP: aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc"," "," ",58674]
["2024-03-08","2024-03-11","NE",2,"10","B","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc","DOES op spoor A L10 / bundel Zuid afgesloten"," ",58674]
["2024-03-08","2024-03-11","NW",2,"54","A+B","SINT-NIKLAAS","PUURS","Weekend","Continuous","23:40","04:00","onderhoud\r\n\r\nFSN - SP I + SP A inbegrepen\r\nFRP - wissel kant FSN inbegrepen + SP I inbegrepen","CTL","Medium"," "," ",60167]
["2024-03-08","2024-03-11","NW",2,"66","A+B","Y.KORTRIJK-WEST","LICHTERVELDE","Weekend","Continuous","23:50","05:00","Indienstname PLP \r\nLichtervelde - Roeselare\r\nStations niet inbegrepen\r\n\r\nTestritten op zondag tot op de perrons van Lichtervelde en Roeselare in overleg met regelaar\r\n\r\n+ Roeselare-Y West Kortrijk voor onderhoud","CTL","Medium"," "," ",57581]
["2024-03-08","2024-03-11","NW",3,"59B","*","GENT-ZEEHAVEN","GENT-ZEEHAVEN","Weekend","Continuous","21:00","05:00","Vernieuwen wissels Bundels Gent Zeehaven\r\nBundel E buiten dienst van SP 17 tot SP 32","Autre","Minor_AdHoc"," ","info rac",60480]
["2024-03-08","2024-03-11","SE",2,"162","A+B","HATRIVAL","MARBEHAN","Weekend","Continuous","23:00","05:00","Renforcement mur de soutènement VB 166.693 + renouvellement P.I. 166.698","CTL","Medium","VA=> ART de +- 2 semaines  sur 50 mètres à 60km/h\r\nVB=> ART de +- 6 semaines  sur 200 mètres à 60km/h","HKM à adapter",52541]
["2024-03-08","2024-03-11","SE",2,"162","B","LIBRAMONT","HATRIVAL","Weekend","Continuous","23:30","04:30","Linked to coupure nr 53438 on line 165(1) tracks(s) A+B from LIBRAMONT to BERTRIX: Réalisation de lame d'air et déplacement séparation de phase Rocogne L165(1) - L162","SAVU_CTRL","Minor_AdHoc"," "," ",53438]
["2024-03-08","2024-03-11","SE",2,"165(1)","A+B","LIBRAMONT","BERTRIX","Weekend","Continuous","23:30","04:30","Réalisation de lame d'air et déplacement séparation de phase Rocogne L165(1) - L162","CTL","Medium","Avec id 52541 = L162 CTL Hatrival - Marbehan\r\nCas caténaire: 26814, 815, 818, 820, 821, 822, 824,828, 830, 832,444, 445"," ",53438]
["2024-03-08","2024-03-11","SE",2,"43","A+B","BOMAL","MARLOIE","Weekend","Continuous","23:30","05:00","Travaux TUC RAIL/Infrabel","CTL","Medium"," ","HKM à adapter",59358]
["2024-03-08","2024-03-11","SW",1,"117","A+B","MANAGE","LUTTRE","Weekend","Continuous","23:20","04:40","Linked to coupure nr 49779 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 6/6\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium"," "," ",49779]
["2024-03-08","2024-03-11","SW",1,"124","B","ROUX","OBAIX-BUZET","Weekend","Continuous","23:20","04:40","Linked to coupure nr 49779 on line 124A tracks(s) A+B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 6/6\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc"," "," ",49779]
["2024-03-08","2024-03-11","SW",1,"124A","A+B","LUTTRE","ROUX","Weekend","Continuous","23:20","04:40","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 6/6\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies II, III, IV et V en gare de Luttre inaccessible en continu\r\nFaisceau accessoire en gare de Luttre inaccessible en continu\r\nART 3min"," ",49779]
["2024-03-08","2024-03-11","SW",1,"78","A+B","BLATON","TOURNAI","Weekend","Continuous","22:30","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nWE 6/7","CTL","Medium",null," ",49409]
["2024-03-08","2024-03-12","SE",2,"166","B","HOUYET","BEAURAING","Week","Continuous","06:00","04:30","CR L166 2024\r\nAdaptation du tracé entre 17200 et 19700 pour augmentation de vitesse","SAVU","Minor_AdHoc","Voie B HS entre Houyet et Beauraing"," ",60441]
["2024-03-09","2024-03-09","SE",3,"139","A/B","WAVRE","OTTIGNIES","Weekend","Day","08:00","16:00","Visites des postes+ maintenances infrastructure et contrôles","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48867]
["2024-03-09","2024-03-10","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61580]
["2024-03-09","2024-03-10","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60419]
["2024-03-09","2024-03-10","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60419 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60419]
["2024-03-09","2024-03-10","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60419 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60419]
["2024-03-09","2024-03-10","NW",3,"75","A","GENT-SINT-PIETERS","DEINZE","Weekend","Continuous","22:15","06:00","vervangen rijdraad SP A - JVO\r\nSPB bijkomend tijdens de nacht 00.20-05.15","SAVU_CTRL","Minor_AdHoc",null," ",58593]
["2024-03-09","2024-03-10","SW",3,"90","A/B","GERAARDSBERGEN","ATH","Weekend","Continuous","06:00","18:00","PLP - SAVU : Préparation MES PLP - réglage CV","SAVU","Minor_AdHoc"," ","HKM à adapter",57009]
["2024-03-09","2024-03-11","CE",2,"26","A+B","Y.RUE DE BRUEL","Y.CINQUANTENAIRE","Weekend","Continuous","06:10","04:00","P085306 BVL L26 Y Bruul - Y50.\r\nY Bruulstraat is niet inbegrepen.","CTL","Medium","TLO tussen Y Bruulstr en Y50","Info Racc",59646]
["2024-03-09","2024-03-11","NE",1,"12","A+B","KAPELLEN","Y.LUCHTBAL","Weekend","Continuous","00:00","04:00","herelectrificatie","CTL","Medium"," "," ",58640]
["2024-03-09","2024-03-11","NE",1,"12","A+B","ESSEN-GRENS","Y.LUCHTBAL","Weekend","Continuous","01:00","04:30","VERNIEUWING WISSELS ESSEN","CTL","Medium"," "," ",45916]
["2024-03-09","2024-03-11","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58007]
["2024-03-09","2024-03-11","NE",2,"19","A+B","MOL","HAMONT-GRENS","Weekend","Continuous","00:00","04:00","vernieuwen houtstukken brug kanaal Dessel-Kwaad Mechelen\r\n+\r\nvervolg railvernieuwing 2023\r\nsporen 493+494 in Neerpelt mee in BD (colt 58118)\r\nonderstopper van Mol naar Neerpelt","CTL","Medium"," "," ",58124]
["2024-03-09","2024-03-11","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Medium","geen verkeer sporen 1+2+3"," ",58142]
["2024-03-09","2024-03-11","NE",2,"273","A+B","BALEN-WERKPLAATSEN","VERB.SIBELCO","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58124 on line 19 tracks(s) A+B from MOL to HAMONT-GRENS: vernieuwen houtstukken brug kanaal Dessel-Kwaad Mechelen\r\n+\r\nvervolg railvernieuwing 2023\r\nsporen 493+494 in Neerpelt mee in BD (colt 58118)\r\nonderstopper van Mol naar Neerpel","CTL","Medium"," "," ",58124]
["2024-03-09","2024-03-11","NW",1,"50","A+B","DENDERLEEUW","AALST","Weekend","Continuous","01:00","04:00","Omvorming rooster Denderleeuw volgens richtplan.","CTL","Medium"," "," ",47671]
["2024-03-09","2024-03-11","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47671 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","CTL","Medium"," "," ",47671]
["2024-03-09","2024-03-11","NW",1,"89","B","DENDERLEEUW","BURST","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47671 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","SAVU_CTRL","Minor_AdHoc"," "," ",47671]
["2024-03-09","2024-03-11","SE",2,"166","A+B","HOUYET","BEAURAING","Weekend","Continuous","06:00","05:00","CR L166 2024\r\nAdaptation du tracé entre 17200 et 19700 pour augmentation de vitesse\r\nRipages caténaires suite adaptation du tracé 17200 -19700","CTL","Medium",null," ",60451]
["2024-03-09","2024-03-10","SE",3,"161","A/B","NAMUR","RHISNES-SAS","Weekend","Day","08:00","16:00","Visite périodique + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","Savu alternatif VA/VB , de 8h à 16 h"," ",49207]
["2024-03-10","2024-03-10","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61608]
["2024-03-10","2024-03-10","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59980]
["2024-03-10","2024-03-10","SE",2,"24","A+B","Y.GLONS","MONTZEN-FRONTIERE","Weekend","Day","06:00","15:45","testen ETCS L2-IL_SE_P030_L24_Glons - Montzen (without border)_ETCS\r\nmeewerken niet mogelijk","CTL","Minor_AdHoc","Pas de circulation possible entre Visé et DB\r\nPas de ciculation entre Longchamps vers DB"," ",61179]
["2024-03-10","2024-03-10","SE",2,"24/1","A+B","Y.LONGCHAMPS","Y.BERNEAU","Weekend","Day","06:00","15:45","Linked to coupure nr 61179 on line 24 tracks(s) A+B from Y.GLONS to MONTZEN-FRONTIERE: testen ETCS L2-IL_SE_P030_L24_Glons - Montzen (without border)_ETCS\r\nmeewerken niet mogelijk","CTL","Minor_AdHoc"," "," ",61179]
["2024-03-10","2024-03-10","SE",3,"139","A/B","SINT-JORIS-WEERT","WAVRE","Weekend","Day","08:00","16:00","Visites des postes - maintenances diverses et révisions","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48877]
["2024-03-11","2024-03-15","CE",2,"94","A+B","Y.NOORD HALLE","SAINTES","Week","Night","23:30","04:20","Onderhoudszone FH_10 Area CE volgens onderhoudskalender 2024\r\nOnderhoudswerken L94 tussen perrons Halle en Grens Vlaanderen-Wallonië.","CTL","Minor_AdHoc",null," ",59513]
["2024-03-11","2024-03-15","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2+3"," ",58137]
["2024-03-11","2024-03-15","NE",2,"27","A+B","Y.BERCHEM-STADION","Y.LIERSESTEENWEG","Week","Night","23:35","04:35","Vernieuwing van  Y-Drabstraat","CTL","Minor_AdHoc","Alternatief E2894-E1996-E1972"," ",58931]
["2024-03-11","2024-03-15","NE",2,"53","A+B","MECHELEN","Y.HEIKE","Week","Night","23:50","04:00","masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6","CTL","Minor_AdHoc"," "," ",58325]
["2024-03-11","2024-03-15","NE",2,"53A","A+B","MECHELEN","Y.MUIZEN","Week","Night","23:50","04:00","masterplan mechelen\r\nperronsporen 5 (met L27,L53)","CTL","Minor_AdHoc","spoor 5"," ",58285]
["2024-03-11","2024-03-15","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59854]
["2024-03-11","2024-03-15","NW",2,"54","A+B","PUURS","Y.HEIKE","Week","Night","23:40","04:30","Vernieuwen rails en dwarsliggers (Y-Heike-Puurs)","CTL","Minor_AdHoc",null," ",57829]
["2024-03-11","2024-03-15","NW",3,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58478]
["2024-03-11","2024-03-15","NW",3,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58478 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58478]
["2024-03-11","2024-03-15","NW",3,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58478 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58478]
["2024-03-11","2024-03-15","NW",3,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58478 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58478]
["2024-03-11","2024-03-15","NW",3,"59B","*","GENT-ZEEHAVEN","GENT-ZEEHAVEN","Week","Continuous","05:00","21:00","Vernieuwen wissels Bundels Gent Zeehaven\r\nBundel E buiten dienst van SP 17 tot SP 24\r\nR5/R6 in weekend","Autre","Minor_AdHoc"," ","info rac",60481]
["2024-03-11","2024-03-15","SW",1,"78","A+B","SAINT-GHISLAIN","TOURNAI","Week","Night","22:55","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nTravaux de finition","CTL","Minor_AdHoc",null," ",48727]
["2024-03-11","2024-03-16","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Week","Night","23:55","05:20","Omvorming Y Jette Rooster S: afwerking\r\nOmvorming Y Jette Rooster R: voorbereiding nachten BVL\r\n\r\nNacht 13/14-03 sp B vrij te houden voor US-trein en lichte aanpassing BDS voor sp A","CTL","Minor_AdHoc","TLO L50+L60.\r\n\r\nNacht 13/14-03 sp B vrij te houden voor US-trein en lichte aanpassing BDS voor sp A"," ",50030]
["2024-03-11","2024-03-16","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Linked to coupure nr 50030 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Omvorming Y Jette Rooster S: afwerking\r\nOmvorming Y Jette Rooster R: voorbereiding nachten BVL\r\n\r\nNacht 13/14-03 sp B vrij te houden voor US-trein en lichte aanpassing BDS voor","CTL","Minor_AdHoc"," "," ",50030]
["2024-03-11","2024-04-02","SW",1,"124","A","LUTTRE","ROUX","AllWeek","Continuous","06:00","06:00","Linked to coupure nr 49467 on line 124 tracks(s) B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 2-2024\r\nDossier de concertation validé le 28 octobre 2021","CTL","High"," "," ",49467]
["2024-03-11","2024-04-02","SW",1,"124","B","LUTTRE","ROUX","AllWeek","Continuous","06:00","06:00","Aménagement Gare de Luttre : Phase 2-2024\r\nDossier de concertation validé le 28 octobre 2021","SAVU_CTRL","High","Voies II en gare de Luttre inaccessible en continu\r\nFaisceau accessoire en gare de Luttre inaccessible en continu\r\nCTL L124 de nuit en semaine (quais de Luttre inclu) : 22h00 - 06h00\r\nIndisponibilité de la transversale Sud à partir du 09/02 (voie déviée"," ",49467]
["2024-03-11","2024-04-02","SW",1,"124A","A","LUTTRE","ROUX","AllWeek","Continuous","06:00","06:00","Linked to coupure nr 49467 on line 124 tracks(s) B from LUTTRE to ROUX: Aménagement Gare de Luttre : Phase 2-2024\r\nDossier de concertation validé le 28 octobre 2021","SAVU","High"," "," ",49467]
["2024-03-12","2024-03-15","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Week","Night","00:00","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Minor_AdHoc"," "," ",58214]
["2024-03-12","2024-03-15","NW",1,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53587]
["2024-03-12","2024-03-15","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 53587 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53587]
["2024-03-12","2024-03-15","NW",1,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 53587 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","SAVU","Minor_AdHoc"," "," ",53587]
["2024-03-12","2024-03-17","SE",2,"166","A","HOUYET","BEAURAING","AllWeek","Continuous","06:00","06:00","CR L166 2024\r\nAdaptation du tracé entre 17200 et 19700 pour augmentation de vitesse\r\nBourrage de révision, contraintes,...","SAVU","Minor_AdHoc","Voie A HS entre Houyet et Beauraing"," ",60442]
["2024-03-15","2024-03-18","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59560]
["2024-03-15","2024-03-18","CE",2,"94","A+B","Y.NOORD HALLE","SAINTES","Weekend","Continuous","23:30","04:20","Onderhoudswerken zone FH_10 volgens onderhoudskalender","CTL","Medium","TLO in continu\r\n2 Perronsporen in continu."," ",58597]
["2024-03-15","2024-03-18","NE",1,"27","A+B","Y.LIERSESTEENWEG","Y.BERCHEM-STADION","Weekend","Continuous","23:50","04:30","vernieuwing waterdichte rok van de kruisingsbrug BX15/L27A te Mortsel\r\nmeewerken met DVE Y Drabstraat","CTL","Medium"," "," ",58223]
["2024-03-15","2024-03-18","NE",1,"27","A+B","Y.BERCHEM-STADION","Y.LIERSESTEENWEG","Weekend","Continuous","23:35","04:35","Vernieuwing van de wissels Y-Drabstraat","CTL","Medium","Alternatief E2894-E1996-E1972"," ",33778]
["2024-03-15","2024-03-18","NE",1,"29","A+B","Y.KRUISBERG","TURNHOUT-BUNDEL","Weekend","Continuous","23:30","04:00","Linked to coupure nr 55026 on line 15 tracks(s) A+B from HERENTALS to GEEL: Etcs\r\n Meewerken mogelijk\r\n+\r\nwisselvernieuwing te Olen (58087)\r\n+\r\nvernieuwing OW en onderhoud (60061)","CTL","Medium"," "," ",55026]
["2024-03-15","2024-03-18","NE",2,"10","A","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58675 on line 10 tracks(s) B from Y.KOESTRAAT to Y.HAZOP: aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc"," "," ",58675]
["2024-03-15","2024-03-18","NE",2,"10","B","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","CTL","Medium","DOES op spoor A L10 / bundel Zuid afgesloten"," ",58675]
["2024-03-15","2024-03-18","NE",2,"19","A+B","BALEN-WERKPLAATSEN","HAMONT-GRENS","Weekend","Continuous","22:00","05:00","vervolg railvernieuwing 2023\r\nsporen 493+494 in Neerpelt mee in BD\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (colt 59898)","CTL","Medium","alternatief Z4321-Z4322-Z4324 R5"," ",58119]
["2024-03-15","2024-03-18","NE",2,"27","A+B","Y.HAREN-NORD","VILVOORDE","Weekend","Continuous","23:50","04:00","Werken Viaduct Vilvoorde (L27 = moot 18)","CTL","Medium"," "," ",58775]
["2024-03-15","2024-03-18","NE",2,"53A","A+B","Y.MUIZEN","MECHELEN","Weekend","Continuous","23:50","04:00","masterplan mechelen\r\nperronsporen 5 (met L27,L53)","CTL","Medium","spoor 5"," ",58286]
["2024-03-15","2024-03-18","NE",3,"230","A+B","Y.BOSDEL","ZUTENDAAL","Weekend","Continuous","23:00","05:00","Onderhoud","CTL","Medium"," "," ",59961]
["2024-03-15","2024-03-18","NW",2,"54","A+B","Y.HEIKE","PUURS","Weekend","Continuous","23:40","04:00","Vernieuwen rails en dwarsliggers (Y-Heike-Puurs)","CTL","Medium"," "," ",57828]
["2024-03-15","2024-03-18","NW",3,"59B","*","GENT-ZEEHAVEN","GENT-ZEEHAVEN","Weekend","Continuous","21:00","05:00","Vernieuwen wissels Bundels Gent Zeehaven\r\nBundel E buiten dienst van SP 17 tot SP 32","Autre","Minor_AdHoc"," ","info rac",60482]
["2024-03-15","2024-03-18","SE",2,"162","A+B","LIBRAMONT","HATRIVAL","Weekend","Continuous","23:00","04:30","Linked to coupure nr 53439 on line 165(1) tracks(s) A+B from LIBRAMONT to BERTRIX: Réalisation de lame d'air et déplacement séparation de phase Rocogne L165(1) - L162","CTL","Medium"," "," ",53439]
["2024-03-15","2024-03-18","SE",2,"165(1)","A+B","LIBRAMONT","BERTRIX","Weekend","Continuous","23:00","04:30","Réalisation de lame d'air et déplacement séparation de phase Rocogne L165(1) - L162","CTL","Medium","L162 Libramont Hatrival=> CTL du vend 23h au lund 05h\r\ncas caténaire: 26815 et 26817\r\nCas caténaire: 26814, 815, 818, 820, 821, 822, 824,828, 830, 832,444, 445"," ",53439]
["2024-03-15","2024-03-18","SE",2,"49","S","WELKENRAEDT","EUPEN","Weekend","Continuous","22:40","05:30","Renouvellement AS01R et adaptation du tracé\r\nBourrage de révision - contraintes et finitions","CTL","Medium","CTL L49 - WE 2\r\nART 1 min"," ",47011]
["2024-03-15","2024-03-18","SW",1,"118","*","OBOURG","OBOURG-MARCHANDISES","Weekend","Continuous","23:30","04:30","Mise en sevice SIMIS-W entre Mons et Obourg (gare incluse).\r\nTravaux préparatoires","SAVU","Minor_AdHoc","MHS des voies 483/484/485/486/487 en continu"," ",49160]
["2024-03-15","2024-03-18","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 2-2024\r\nWeek-end 1/3\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies I, II, III en gare de Luttre inaccessible en continu\r\nIndisponibilité de la transversale Sud à partir du 09/02 (voie déviée)"," ",49468]
["2024-03-15","2024-03-18","SW",1,"124A","A","LUTTRE","ROUX","Weekend","Continuous","23:30","04:40","Linked to coupure nr 49468 on line 124 tracks(s) A+B from LUTTRE to Y.NORD: Aménagement Gare de Luttre : Phase 2-2024\r\nWeek-end 1/3\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc"," "," ",49468]
["2024-03-15","2024-03-18","SW",1,"78","A+B","BLATON","Y.MAUBRAY","Weekend","Night","23:30","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nTravaux préparatoires","CTL","Minor_AdHoc","Nuit ven/sam 23h30 - 6h20\r\nsam/dim 23h40-6h20\r\nNuit dim/lun 23h40-5h"," ",61272]
["2024-03-15","2024-03-18","SW",2,"130","A+B","TAMINES","CHATELET-GRIL OUEST","Weekend","Continuous","22:45","05:00","Maintenance Z15.51\r\nP4+","CTL","Medium"," ","HKM à adapter",48833]
["2024-03-15","2024-03-18","SE",1,"161","B","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:45","WE SAVU RER Bakenbos-Ottignies","SAVU_CTRL","Minor_AdHoc","ART maximum 2'"," ",49248]
["2024-03-15","2024-03-18","SE",3,"154","A/B","JAMBES","YVOIR","Weekend","Continuous","23:30","05:00","Entretien AS , traitement zone boueuse\r\nRq 333 : Pas d'ART possible suite L154 renouvellement ballast déjà 3 min ART","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 18/03 au 21/03","HKM à adapter",57690]
["2024-03-16","2024-03-17","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59431]
["2024-03-16","2024-03-17","SW",3,"116","*","LA LOUVIERE-GARE INDUSTRIELLE","LA LOUVIERE-GARE INDUSTRIELLE","Weekend","Continuous","06:00","17:00","Maintenance Z17.52\r\nMise HS P4 - Zone 17 AI52","Autre","Minor_AdHoc","Mise HS des voies Accessoires du faisceau de GLI\r\nP4","InfoRacc",49155]
["2024-03-16","2024-03-17","SW",3,"90","A/B","GERAARDSBERGEN","ATH","Weekend","Continuous","06:00","18:00","PLP - SAVU : Préparation MES + réglage CV","SAVU","Minor_AdHoc"," ","HKM à adapter",57010]
["2024-03-16","2024-03-18","NE",1,"12","A+B","KAPELLEN","Y.LUCHTBAL","Weekend","Continuous","00:00","04:00","herelectrificatie","CTL","Medium"," "," ",58058]
["2024-03-16","2024-03-18","NE",1,"12","A+B","Y.LUCHTBAL","ESSEN-GRENS","Weekend","Continuous","01:00","04:30","VERNIEUWING WISSELS ESSEN","CTL","Medium"," "," ",45917]
["2024-03-16","2024-03-18","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58008]
["2024-03-16","2024-03-18","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:00","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Medium"," "," ",58217]
["2024-03-16","2024-03-18","NE",2,"53","A","MECHELEN","Y.HEIKE","Weekend","Continuous","00:00","04:00","masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6","CTL","Medium","SAVU L53 tussen Mechelen en Y.Heike (trapezium Mechelen)"," ",58326]
["2024-03-16","2024-03-18","NE",2,"53","A+B","MECHELEN","MUIZEN","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58326 on line 53 tracks(s) A from MECHELEN to Y.HEIKE: masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6","CTL","Medium"," "," ",58326]
["2024-03-16","2024-03-18","NE",3,"27","A+B","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL","Weekend","Night","00:40","04:20","onderhoud SIG + wissels Y arendstraat+onderhous wissel antwerpen centraal -1\r\n\r\nperronsporen 11-12-13-14","CTL","Minor_AdHoc","nog te bepalen"," ",59732]
["2024-03-16","2024-03-18","NW",1,"50","A+B","DENDERLEEUW","AALST","Weekend","Continuous","01:00","04:00","Omvorming rooster Denderleeuw volgens richtplan.","CTL","Medium"," "," ",47673]
["2024-03-16","2024-03-18","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47673 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","CTL","Medium"," "," ",47673]
["2024-03-16","2024-03-18","NW",1,"89","B","DENDERLEEUW","BURST","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47673 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","SAVU_CTRL","Minor_AdHoc"," "," ",47673]
["2024-03-16","2024-03-18","NW",2,"204","A+B","Y.BOMA","LIJN 204-KRUISING LIJN 58/2","Weekend","Night","00:10","04:00","Linked to coupure nr 57592 on line 58/2 tracks(s) A+B from GENT-ZEEHAVEN to Y.MUIDE: CoLT 57591: L204 Gent-Zeehaven - Gent-Noord:  indienstname PLP (masterplan ETCS) testritten op zondag in overleg met regelaar\r\nCoLT 57592: Tijdens de nacht uitbereiding","CTL","Minor_AdHoc"," ","Info Racc.",57592]
["2024-03-16","2024-03-18","NW",2,"204","A+B","LIJN 204-KRUISING LIJN 58/2","GENT-NOORD","Weekend","Continuous","00:10","04:00","CoLT 57591: L204 Gent-Zeehaven - Gent-Noord:  indienstname PLP (masterplan ETCS) testritten op zondag in overleg met regelaar\r\nCoLT 57592: Tijdens de nacht uitbereiding buitendienststelling met kruising tussen L58/2 en L204 tot Y Boma (tot sein DX-E.13 ","CTL","Medium",null,"Info Racc.",57591]
["2024-03-16","2024-03-18","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Weekend","Continuous","01:00","04:00","Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium",null,null,59184]
["2024-03-16","2024-03-18","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59184 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium"," ",null,59184]
["2024-03-16","2024-03-18","NW",2,"50A/6","A+B","Y.ASSELS","GENT-SINT-PIETERS","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59184 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium"," ",null,59184]
["2024-03-16","2024-03-18","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59184 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium"," ",null,59184]
["2024-03-16","2024-03-18","NW",2,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Night","00:10","04:00","CoLT 57591: L204 Gent-Zeehaven - Gent-Noord:  indienstname PLP (masterplan ETCS) testritten op zondag in overleg met regelaar\r\nCoLT 57592: Tijdens de nacht uitbereiding buitendienststelling met kruising tussen L58/2 en L204 tot Y Boma (tot sein DX-E.13 ","CTL","Minor_AdHoc",null,"Info Racc.",57592]
["2024-03-17","2024-03-17","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59981]
["2024-03-17","2024-03-22","SE",2,"166","B","HOUYET","BEAURAING","AllWeek","Continuous","06:00","06:00","Massification travaux pour adaptation du tracé\r\nAdaptation du tracé entre 17200 et 19700 pour augmentation de vitesse\r\nBourrage de révision, contraintes,...","SAVU","Minor_AdHoc","Voie B HS entre Houyet et Beauraing"," ",60443]
["2024-03-18","2024-03-22","NE",1,"27","A+B","Y.LIERSESTEENWEG","Y.BERCHEM-STADION","Week","Night","23:50","04:30","vernieuwing waterdichte rok van de kruisingsbrug BX15/L27A te Mortsel\r\nmeewerken met DVE Y Drabstraat\r\n+\r\nVernieuwing van  Y-Drabstraat (colt 58932)","CTL","Minor_AdHoc","Alternatief E2894-E1996-E1972"," ",58224]
["2024-03-18","2024-03-22","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 4+5+6 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 4+5+6"," ",58138]
["2024-03-18","2024-03-22","NE",2,"27","A+B","Y.BERCHEM-STADION","Y.LIERSESTEENWEG","Week","Night","23:35","04:35","Vernieuwing van  Y-Drabstraat","CTL","Minor_AdHoc","Alternatief E2894-E1996-E1972"," ",58932]
["2024-03-18","2024-03-22","NE",2,"27","A+B","Y.HAREN-NORD","VILVOORDE","Week","Night","23:50","04:00","Werken Viaduct Vilvoorde (L27 = moot 18)","CTL","Minor_AdHoc",null," ",58776]
["2024-03-18","2024-03-22","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59855]
["2024-03-18","2024-03-22","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Week","Night","23:40","04:00","Linked to coupure nr 59948 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59948]
["2024-03-18","2024-03-22","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Week","Night","23:40","04:00","Onderhoud","CTL","Minor_AdHoc"," "," ",59948]
["2024-03-18","2024-03-22","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Week","Night","23:40","04:00","Linked to coupure nr 59948 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59948]
["2024-03-18","2024-03-22","NW",2,"54","A+B","PUURS","Y.HEIKE","Week","Night","23:40","04:30","Vernieuwen rails en dwarsliggers (Y-Heike-Puurs)","CTL","Minor_AdHoc",null," ",57830]
["2024-03-18","2024-03-22","NW",3,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58480]
["2024-03-18","2024-03-22","NW",3,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58480 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc"," ",null,58480]
["2024-03-18","2024-03-22","NW",3,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58480 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc"," ",null,58480]
["2024-03-18","2024-03-22","NW",3,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58480 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc"," ",null,58480]
["2024-03-18","2024-03-22","NW",3,"59B","*","GENT-ZEEHAVEN","GENT-ZEEHAVEN","Week","Continuous","05:00","21:00","Vernieuwen wissels Bundels Gent Zeehaven\r\nBundel E buiten dienst van SP 17 tot SP 24\r\nR5/R6 in weekend","Autre","Minor_AdHoc"," ","info rac",60483]
["2024-03-18","2024-03-22","SW",1,"78","A+B","SAINT-GHISLAIN","TOURNAI","Week","Night","23:30","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nTravaux de finition (amplitude réduite suite TX L118)","CTL","Minor_AdHoc",null," ",61269]
["2024-03-18","2024-03-23","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Week","Night","23:55","05:20","Omvorming Y Jette Rooster S: afwerking\r\nOmvorming Y Jette Rooster R: voorbereiding nachten BVL","CTL","Minor_AdHoc","TLO L50+L60."," ",56098]
["2024-03-18","2024-03-23","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Linked to coupure nr 56098 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Omvorming Y Jette Rooster S: afwerking\r\nOmvorming Y Jette Rooster R: voorbereiding nachten BVL","CTL","Minor_AdHoc"," "," ",56098]
["2024-03-18","2024-03-23","NW",2,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","23:30","04:30","Linked to coupure nr 59242 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",59242]
["2024-03-18","2024-03-23","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","23:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)","CTL","Medium"," "," ",59242]
["2024-03-18","2024-03-23","NW",2,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","23:30","04:30","Linked to coupure nr 59242 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",59242]
["2024-03-18","2024-03-29","SE",3,"165(1)","B","LIBRAMONT","BERTRIX","Week","Day","08:00","16:00","Préparation reprise en PLP.","SAVU","Minor_AdHoc"," "," ",46753]
["2024-03-18","2024-03-21","SE",3,"154","A+B","JAMBES","YVOIR","Weekend","Continuous","05:00","05:00","ART 2min\r\nRq 333 : Pas d'ART possible suite L154 renouvellement ballast déjà 3 min ART","ART","Minor_AdHoc","ART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 18/03 au 21/03","HKM à adapter",58820]
["2024-03-18","2024-03-27","SE",1,"154","A","YVOIR","DINANT","AllWeek","Continuous","08:30","05:00","Renouvellement de Ballast (C75)","SAVU","High","ART de maximum 3,5 minutes id 49939"," ",49928]
["2024-03-18","2024-04-25","SE",1,"154","A/B","YVOIR","DINANT","AllWeek","Continuous","08:30","05:00","ART 3min\r\nRenouvellement de Ballast (C75)","ART","Minor_AdHoc",null," ",49939]
["2024-03-19","2024-03-22","NW",1,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53589]
["2024-03-19","2024-03-22","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 53589 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53589]
["2024-03-19","2024-03-22","NW",1,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 53589 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","SAVU","Minor_AdHoc"," "," ",53589]
["2024-03-22","2024-03-25","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59561]
["2024-03-22","2024-03-25","NE",1,"27","A+B","Y.LIERSESTEENWEG","Y.BERCHEM-STADION","Weekend","Continuous","23:35","04:35","vernieuwing waterdichte rok van de kruisingsbrug BX15/L27A te Mortsel\r\nmeewerken met DVE Y Drabstraat\r\n+\r\nvernieuwing waterdichte rok van de kruisingsbrug BX15/L27A te Mortsel\r\nmeewerken met DVE Y Drabstraat (colt33780)","CTL","Medium","Alternatief E2894-E1996-E1972"," ",58222]
["2024-03-22","2024-03-25","NE",1,"27","A+B","Y.BERCHEM-STADION","Y.LIERSESTEENWEG","Weekend","Continuous","23:35","04:35","Vernieuwing van de wissels Y-Drabstraat\r\n\r\nZIE COLT 58222","CTL","Medium","Alternatief E2894-E1996-E1972"," ",33780]
["2024-03-22","2024-03-25","NE",2,"10","A","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58676 on line 10 tracks(s) B from Y.KOESTRAAT to Y.HAZOP: aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc"," "," ",58676]
["2024-03-22","2024-03-25","NE",2,"10","B","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","CTL","Medium","DOES op spoor A L10 / bundel Zuid afgesloten"," ",58676]
["2024-03-22","2024-03-25","NE",2,"19","A+B","BALEN-WERKPLAATSEN","HAMONT-GRENS","Weekend","Continuous","23:00","04:00","vervolg railvernieuwing 2023\r\nsporen 493+494 in Neerpelt mee in BD\r\nonderstopper van Mol naar Neerpelt \r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (colt 59899)\r\n+\r\nvernieuwen houtstukken brug kanaal Dessel-Kwaad Mechelen (colt 58125)","CTL","Medium"," "," ",58120]
["2024-03-22","2024-03-25","NE",2,"27","A+B","ANTWERPEN-BERCHEM","Y.BERCHEM-STADION","Weekend","Continuous","23:50","04:30","onderhoud SIG Y stadion +Y noord Groenenhoek 4 nachten","CTL","Medium","Alternatief E2894-E1996-E1972"," ",59716]
["2024-03-22","2024-03-25","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Weekend","Continuous","23:40","04:00","Linked to coupure nr 59947 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Medium"," "," ",59947]
["2024-03-22","2024-03-25","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Weekend","Continuous","23:40","04:00","Onderhoud","CTL","Medium"," "," ",59947]
["2024-03-22","2024-03-25","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Weekend","Continuous","23:40","04:00","Linked to coupure nr 59947 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Medium"," "," ",59947]
["2024-03-22","2024-03-25","NW",2,"54","A+B","Y.HEIKE","PUURS","Weekend","Continuous","23:40","04:00","Vernieuwen rails en dwarsliggers (Y-Heike-Puurs)","CTL","Medium"," "," ",57831]
["2024-03-22","2024-03-25","NW",3,"59B","*","GENT-ZEEHAVEN","GENT-ZEEHAVEN","Weekend","Continuous","21:00","05:00","Vernieuwen wissels Bundels Gent Zeehaven\r\nBundel E buiten dienst van SP 17 tot SP 32","Autre","Minor_AdHoc"," ","info rac",60484]
["2024-03-22","2024-03-25","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 2-2024\r\nWeek-end 2/3\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies I, II, III en gare de Luttre inaccessible en continu\r\nIndisponibilité de la transversale Sud à partir du 09/02 (voie déviée)"," ",49780]
["2024-03-22","2024-03-25","SW",1,"124A","A","LUTTRE","ROUX","Weekend","Continuous","23:30","04:40","Linked to coupure nr 49780 on line 124 tracks(s) A+B from LUTTRE to Y.NORD: Aménagement Gare de Luttre : Phase 2-2024\r\nWeek-end 2/3\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc"," "," ",49780]
["2024-03-22","2024-03-25","SW",1,"78","A+B","BLATON","TOURNAI","Weekend","Continuous","22:30","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nWE Finitions\r\n+ Construction d'un couloir sous-voies au niveau du PN43 (L78…68.800) en vue de la suppression du PN.\r\nPhase 1 - fonçage de palplanches en VA et en VB.","CTL","Medium",null," ",49411]
["2024-03-22","2024-03-25","SW",2,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Maintenance Z3. 51  P4+\r\n+ Renouvellement complet des PN","CTL","Medium",null,"HKM à adapter",49113]
["2024-03-22","2024-03-25","SW",3,"90","A+B","GERAARDSBERGEN","ATH","Weekend","Continuous","22:10","04:30","PLP - Travaux d'intégration (préparatoires à la MES)\r\n + Maintenance Z12.54 + Z17.54\r\nGrammont - Ath","CTL","Medium",null,"InfoRacc",57021]
["2024-03-22","2024-03-25","SE",3,"161","B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","réélectrification\r\n+ Entretien des PN + maintenance planifiée","SAVU_CTRL","Minor_AdHoc","une voie en continu + CTL nuits classiques\r\nART stab 2 min 10jours","a déterminer",49706]
["2024-03-22","2024-03-25","SE",1,"154","A+B","YVOIR","DINANT","Weekend","Continuous","23:50","04:20","Renouvellement de Ballast (C75)\r\nWE 1/6","CTL","Medium",null,"HKM à adapter",49930]
["2024-03-23","2024-03-24","NE",2,"35","A+B","HASSELT","Y.DIEST","Weekend","Continuous","06:00","22:00","vernieuwen OW71A strall te Herk-de-Stad","CTL","Medium"," "," ",60023]
["2024-03-23","2024-03-24","NE",2,"52","A","PUURS","Y.ANTWERPEN-ZUID","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59089]
["2024-03-23","2024-03-24","NE",2,"59","A","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59088]
["2024-03-23","2024-03-24","SE",3,"43","A+B","ANGLEUR","RIVAGE-MARCHANDISES","Weekend","Continuous","00:05","17:00","Entretien manuel et mécanisés des PN \r\nEntretien manuel et mécanisés des AW","CTL","Medium",null,"HKM à détourner via les L125A-125-130B-162",55084]
["2024-03-23","2024-03-25","NE",1,"12","A+B","ESSEN-GRENS","Y.LUCHTBAL","Weekend","Continuous","01:00","04:30","VERNIEUWING WISSELS ESSEN\r\n+\r\nherelectrificatie kapellen - luchtbal Colt 58059","CTL","Medium","alternatief E2573-ER2020-ER2021-E2594"," ",45918]
["2024-03-23","2024-03-25","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58009]
["2024-03-23","2024-03-25","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Medium","geen verkeer sporen 1+2+3"," ",58144]
["2024-03-23","2024-03-25","NW",1,"50","A+B","DENDERLEEUW","AALST","Weekend","Continuous","01:00","04:00","Omvorming rooster Denderleeuw volgens richtplan.","CTL","Medium"," "," ",47674]
["2024-03-23","2024-03-25","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47674 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","CTL","Medium"," "," ",47674]
["2024-03-23","2024-03-25","NW",1,"89","B","DENDERLEEUW","BURST","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47674 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","SAVU_CTRL","Minor_AdHoc"," "," ",47674]
["2024-03-23","2024-03-25","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Weekend","Continuous","01:00","04:00","Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium",null,null,59185]
["2024-03-23","2024-03-25","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59185 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium"," ",null,59185]
["2024-03-23","2024-03-25","NW",2,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59185 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium"," ",null,59185]
["2024-03-23","2024-03-25","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59185 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium"," ",null,59185]
["2024-03-23","2024-03-25","SE",2,"139","A+B","WAVRE","OTTIGNIES","Weekend","Continuous","06:00","06:00","Entretien des PN + maintenance planifiée\r\nRq 333 : incompatible - à replanifier","CTL","Medium","ART protection et stabilisation:\r\nLongueur: 100 mètres \r\nVitesse réduite: 40 km/h\r\nDate de mise en vigueur: du 22/03 au 01/04 à minuit \r\nPerte de temps: \r\nHKV: 2'\r\nHKM: 1,9'"," ",50637]
["2024-03-23","2024-03-24","SE",3,"161","A/B","GEMBLOUX","RHISNES","Weekend","Day","08:00","16:00","Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49191]
["2024-03-24","2024-03-24","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59982]
["2024-03-25","2024-03-26","NE",1,"16","A+B","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT","Weekend","Night","23:00","04:30","levering wissels","CTL","Minor_AdHoc","alternatief E2922-E2943-E2872"," ",59694]
["2024-03-25","2024-03-27","NE",2,"12","*","Y.ANTWERPEN-SCHIJNPOORT","Y.ANTWERPEN-SCHIJNPOORT","Week","Day","08:30","15:30","onderhoud bundelkop bundel C wissels 35N-34BN-36N-34AN","Autre","Minor_AdHoc","werken  bundel C thv van sein RN.12-AN.12-PN.12"," ",60081]
["2024-03-25","2024-03-29","NE",2,"27","A+B","ANTWERPEN-BERCHEM","Y.LIERSESTEENWEG","Week","Night","23:35","04:35","Vernieuwing van  Y-Drabstraat\r\n+\r\nonderhoud SIG Y stadion +Y noord Groenenhoek 4 nachten (colt 59717)","CTL","Minor_AdHoc","Alternatief E2894-E1996-E1972"," ",58933]
["2024-03-25","2024-03-29","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59856]
["2024-03-25","2024-03-29","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Week","Night","23:40","04:00","Linked to coupure nr 59946 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59946]
["2024-03-25","2024-03-29","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Week","Night","23:40","04:00","Onderhoud","CTL","Minor_AdHoc"," "," ",59946]
["2024-03-25","2024-03-29","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Week","Night","23:40","04:00","Linked to coupure nr 59946 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59946]
["2024-03-25","2024-03-29","NW",2,"54","A+B","PUURS","Y.HEIKE","Week","Night","23:40","04:30","Vernieuwen rails en dwarsliggers (Y-Heike-Puurs)","CTL","Minor_AdHoc",null," ",57832]
["2024-03-25","2024-03-29","NW",3,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,59187]
["2024-03-25","2024-03-29","NW",3,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 59187 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc"," ",null,59187]
["2024-03-25","2024-03-29","NW",3,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 59187 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc"," ",null,59187]
["2024-03-25","2024-03-29","NW",3,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 59187 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc"," ",null,59187]
["2024-03-25","2024-03-29","SW",1,"78","A+B","SAINT-GHISLAIN","TOURNAI","Week","Night","22:55","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nTravaux de finition","CTL","Minor_AdHoc",null," ",61270]
["2024-03-25","2024-04-12","NE",3,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","AllWeek","Continuous","23:40","04:45","BTS van 40km/h tussen Y.Antwerpen-Zuid en Puurs +2'\r\n\r\nwerken onderhoud","ART","Minor_AdHoc"," "," ",60540]
["2024-03-25","2024-07-05","SE",1,"166","A","GENDRON-CELLES","HOUYET","AllWeek","Continuous","06:00","22:00","Massification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse \r\n+ Renouvellement tablier métallique PPI 13.808\r\nMise au gabarit pistes PI + sécurisation parois rocheuses + stabilisation talus","SAVU","High","ART de protection : BK 13.700 à 13.900 en voie A (longueur : 200 mètres)\r\nVitesse à 60 km/h. \r\nPerte de temps HKV : 2 minutes / HKM : 2 minutes\r\nART de stabilisation id 50023"," ",47500]
["2024-03-25","2024-03-26","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Week","Night","23:00","04:30","levering wissels\r\n\r\nhangt vast aan colt59694","CTL","Minor_AdHoc","alternatief E2943-E2922-E2872"," ",59698]
["2024-03-25","2024-03-25","SE",1,"154","A+B","YVOIR","DINANT","Week","Continuous","09:00","15:00","Renouvellement de Ballast (C75)\r\nWE 1/3 - CTL R1","CTL","Medium",null,"HKM à adapter",49931]
["2024-03-26","2024-03-27","NE",1,"16","A+B","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT","Week","Night","23:00","04:30","levering wissels","CTL","Minor_AdHoc","alternatief E2922-E2894-E2872"," ",59695]
["2024-03-26","2024-03-28","SE",3,"140","A+B","OTTIGNIES","OTTIGNIES","Week","Continuous","08:00","16:00","Entretien en gare d'Ottignies","Autre","Minor_AdHoc","Voie 10 + Voie 11 HS entre les AS 16AR/16BR et 10AR/OR.29\r\nService ES révision et Géométrie 09BR/10AR/12R/13BR"," ",51106]
["2024-03-26","2024-03-28","SE",3,"140","B","OTTIGNIES","CEROUX-MOUSTY","Week","Continuous","08:00","16:00","Linked to coupure nr 51106 on line 140 tracks(s) A+B from OTTIGNIES to OTTIGNIES: Entretien en gare d'Ottignies","SAVU","Minor_AdHoc"," "," ",51106]
["2024-03-26","2024-03-29","NW",1,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53590]
["2024-03-26","2024-03-29","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 53590 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53590]
["2024-03-26","2024-03-29","NW",1,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 53590 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","SAVU","Minor_AdHoc"," "," ",53590]
["2024-03-26","2024-03-27","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Week","Night","23:00","04:30","levering wissels","CTL","Minor_AdHoc","alternatief E2922-E2894-E2872"," ",59696]
["2024-03-27","2024-03-27","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60090]
["2024-03-27","2024-03-29","NE",2,"35","A+B","HASSELT","Y.DIEST","Week","Night","23:30","04:30","vernieuwen OW71A strall te Herk-de-Stad","CTL","Minor_AdHoc","alternatief E2622-E2743-E2221"," ",60024]
["2024-03-27","2024-04-08","SE",1,"154","B","YVOIR","DINANT","AllWeek","Continuous","09:00","15:00","Renouvellement de Ballast (C75)","SAVU","High","ART de maximum 3,5 minutes id 49939"," ",49929]
["2024-03-28","2024-03-28","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60106]
["2024-03-28","2024-03-28","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55943]
["2024-03-29","2024-04-01","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59562]
["2024-03-29","2024-04-01","NE",1,"27","A+B","ANTWERPEN-BERCHEM","Y.LIERSESTEENWEG","Weekend","Continuous","23:35","04:35","Vernieuwing van de wissels Y-Drabstraat\r\n+\r\nonderhoud SIG Y stadion +Y noord Groenenhoek (59718)","CTL","Medium","Alternatief E2894-E1996-E1972"," ",58934]
["2024-03-29","2024-04-01","NE",2,"19","A+B","BALEN-WERKPLAATSEN","HAMONT-GRENS","Weekend","Continuous","22:00","05:00","vervolg railvernieuwing 2023\r\nsporen 493+494 in Neerpelt mee in BD\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (59900)","CTL","Medium","alternatief Z4321-Z4322-Z4324 R5"," ",58121]
["2024-03-29","2024-04-01","NE",2,"27","A+B","ANTWERPEN-BERCHEM","Y.LIERSESTEENWEG","Weekend","Continuous","23:50","04:30","onderhoud SIG Y stadion +Y noord Groenenhoek 4 nachten\r\n\r\n===> zie colt 58934","CTL","Medium","Alternatief E2894-E1996-E1972"," ",59718]
["2024-03-29","2024-04-01","NW",2,"86","*","OUDENAARDE","LEUPEGEM-SEINEN SL9-TL9","Weekend","Continuous","23:40","04:50","buitenwerken \r\nVernieuwen SI te Oudenaarde - bundel Oudenaarde tss AW7AU niet inbegrepen tot AW11BU niet inbegrepen\r\n\r\n* In CoLT gekozen voor aanduiding Leupegem om zichtbaarheid op de assen te creëren","CTL","Medium","geen gebruik van de bundel mogelijk"," ",57571]
["2024-03-29","2024-04-01","SE",1,"130","A+B","MOUSTIER","Y.FLAWINNE","Weekend","Continuous","23:30","05:30","Aménagement gare de Floreffe\r\nC75 pour rectification tracé BK 68.300 à 69.500\r\nWE 1/6\r\nDossier de concertation validé le 26 octobre 2021\r\n+ Renouvellement PS BK 0.796","CTL","Medium",null," ",47406]
["2024-03-29","2024-04-01","SE",1,"130/1","S","ENTREE RACC.MOUSTIER-SOLVAY 1","MOUSTIER-GARAGE","Weekend","Continuous","23:30","05:30","Linked to coupure nr 47406 on line 130 tracks(s) A+B from MOUSTIER to Y.FLAWINNE: Aménagement gare de Floreffe\r\nC75 pour rectification tracé BK 68.300 à 69.500\r\nWE 1/6\r\nDossier de concertation validé le 26 octobre 2021\r\n+ Renouvellement PS BK 0.796","CTL","Medium"," "," ",47406]
["2024-03-29","2024-04-02","SE",2,"44","A+B","PEPINSTER-CITE","SPA-GERONSTERE","Weekend","Continuous","23:00","05:00","Renouvellement des équipements de signalisation des PNs 3, 4, 5 et 6 (Préparation et ou MES)\r\n+ Entretien manuel et mécanisés des AW \r\nEntretien manuel et mécanisés de la voie courante\r\nEntretien manuel et mécanisés des PN","CTL","Medium","WE 3 jours"," ",55095]
["2024-03-29","2024-04-02","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 2-2024\r\nWeek-end 3/3\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies I, II, III en gare de Luttre inaccessible en continu\r\nIndisponibilité de la transversale Sud à partir du 09/02 (voie déviée)"," ",49781]
["2024-03-29","2024-04-02","SW",1,"124A","A","LUTTRE","ROUX","Weekend","Continuous","23:30","04:40","Linked to coupure nr 49781 on line 124 tracks(s) A+B from LUTTRE to Y.NORD: Aménagement Gare de Luttre : Phase 2-2024\r\nWeek-end 3/3\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc"," "," ",49781]
["2024-03-29","2024-04-02","SW",1,"75","A+B","LAUWE","MOUSCRON-FRONTIERE","Weekend","Continuous","23:10","04:00","Mise en service ETCS\r\nWE 3jours","CTL","Medium","CTL L75+L75A \r\n+Impact gare de Mouscron\r\n\r\nbuiten dienst stelling station Moeskroen inbegrepen tot Lauwe\r\nsamenwerken NIET mogelijk","HKM à adapter \r\nNuit lundi/mardi iti via L130A-124A-124-26/3-26-26/1-27-27B-53-50A-75-73-66",55492]
["2024-03-29","2024-04-02","SW",1,"75A","A+B","MOUSCRON","FROYENNES","Weekend","Continuous","23:10","04:00","Linked to coupure nr 55492 on line 75 tracks(s) A+B from LAUWE to MOUSCRON-FRONTIERE: Mise en service ETCS\r\nWE 3jours","CTL","Medium"," ","HKM à adapter \r\nNuit lundi/mardi iti via L130A-124A-124-26/3-26-26/1-27-27B-53-50A-75-73-66",55492]
["2024-03-29","2024-04-08","SE",1,"161","A+B","BRUXELLES-LUXEMBOURG","OTTIGNIES","AllWeek","Continuous","23:50","04:40","RER\r\nTravaux plateformes, voies, signalisation et caténaires à Watermael et sur le tronçon Bakenbos-Ottignies","CTL","High"," "," ",46607]
["2024-03-29","2024-04-01","SE",1,"154","A+B","YVOIR","DINANT","Weekend","Continuous","23:50","04:20","Renouvellement de Ballast (C75)\r\nWE 2/6","CTL","Medium",null,"HKM à adapter",49932]
["2024-03-30","2024-03-30","SE",3,"130","A/B","FLAWINNE","MOUSTIER","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49172]
["2024-03-30","2024-03-31","NE",2,"35","A+B","HASSELT","Y.DIEST","Weekend","Continuous","06:00","22:00","vernieuwen OW71A strall te Herk-de-Stad","CTL","Medium"," "," ",60022]
["2024-03-30","2024-03-31","NE",2,"59","A","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59090]
["2024-03-30","2024-03-31","SW",3,"96","A+B","Y.JURBISE","MONS","Weekend","Continuous","06:00","17:00","Maintenance Z.5.53\r\nMise HS en P4","CTL","Medium"," ","HKM à adapter",48660]
["2024-03-30","2024-04-01","CE",2,"26","A+B","SCHAERBEEK-FORMATION","Y.RUE DE BRUEL","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58590 on line 26B(1) tracks(s) A+B from Y.RUE DE BRUEL to Y.HAREN-NORD: Onderhoudszone FSR_11-FSR_12-MTB_08 volgens onderhoudskalender Area CE.\r\n\r\nAfsluiting L26B (Y Bruulstraat) en bundelkoppen bundel G en R te FSR","CTL","Medium"," "," ",58590]
["2024-03-30","2024-04-01","CE",2,"26","A+B","Y.ENTREE GROUPE R","Y.KEELBEEK","Weekend","Continuous","00:20","04:00","P085306 BVL L26 Y Bruul - Y Keelbeek (Ni)","CTL","Medium","TLO L26 tussen Y Inrit Gr. R en Y Keelbeek (NI). Y Bruulstraat is dicht.\r\nGeen verkeer mogelijk tussen L27 en Schaarbeek Vorming\r\nBundel R en ateliers NMBS enkel toegankelijk kant Schaarbeek Vorming","HKM om te leiden via 26-26/1",59649]
["2024-03-30","2024-04-01","CE",2,"26A","A+B","SCHAERBEEK-ACC.FORMATION-L26A","Y.HAREN-NORD","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58590 on line 26B(1) tracks(s) A+B from Y.RUE DE BRUEL to Y.HAREN-NORD: Onderhoudszone FSR_11-FSR_12-MTB_08 volgens onderhoudskalender Area CE.\r\n\r\nAfsluiting L26B (Y Bruulstraat) en bundelkoppen bundel G en R te FSR","CTL","Medium"," "," ",58590]
["2024-03-30","2024-04-01","CE",2,"26A","A+B","SCHAERBEEK-ACC.FORMATION-L26A","Y.HAREN-NORD","Weekend","Continuous","00:20","04:00","Linked to coupure nr 59649 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.KEELBEEK: P085306 BVL L26 Y Bruul - Y Keelbeek (Ni)","CTL","Medium"," ","HKM om te leiden via 26-26/1",59649]
["2024-03-30","2024-04-01","CE",2,"26B(1)","A+B","Y.RUE DE BRUEL","Y.HAREN-NORD","Weekend","Continuous","00:20","04:00","Onderhoudszone FSR_11-FSR_12-MTB_08 volgens onderhoudskalender Area CE.\r\n\r\nAfsluiting L26B (Y Bruulstraat) en bundelkoppen bundel G en R te FSR","CTL","Medium","Geen verkeer mogelijk tussen L27 en Schaarbeek Vorming\r\nBundel R en ateliers NMBS enkel toegankelijk kant Schaarbeek Vorming"," ",58590]
["2024-03-30","2024-04-01","NE",1,"12","A+B","ESSEN","KALMTHOUT","Weekend","Night","00:00","05:00","vernieuwing wissels Essen +onderhoud","CTL","Minor_AdHoc"," "," ",58782]
["2024-03-30","2024-04-01","NE",2,"10","A","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:05","04:00","Linked to coupure nr 58677 on line 10 tracks(s) B from Y.KOESTRAAT to Y.HAZOP: aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc"," "," ",58677]
["2024-03-30","2024-04-01","NE",2,"10","B","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:05","04:00","aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc","DOES op spoor A L10 / bundel Zuid afgesloten"," ",58677]
["2024-03-30","2024-04-01","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58010]
["2024-03-30","2024-04-01","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Weekend","Continuous","01:00","04:00","Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium",null,null,59186]
["2024-03-30","2024-04-01","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59186 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium"," ",null,59186]
["2024-03-30","2024-04-01","NW",2,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59186 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium"," ",null,59186]
["2024-03-30","2024-04-01","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59186 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOptie 2: 3 weekends in combinatie met Masterplan Denderleeuw","CTL","Medium"," ",null,59186]
["2024-03-30","2024-04-01","NW",2,"55","A+B","WONDELGEM","ZELZATE-GRENS","Weekend","Continuous","05:00","05:00","L55 Wondelgem-Zelzate\r\nVernieuwing treindetectie\r\nTestritten op zondag tot op perrons te Wondelgem in overleg met de regelaar","CTL","Medium"," ","Info Racc",57579]
["2024-03-30","2024-04-02","SE",3,"162","A+B","BOIS D'AUSSE","BRAIBANT","Weekend","Continuous","00:30","04:20","Remplacement du PI à Florée au km 82,697\r\nBesoin d'une CTL de 3 jours complets","CTL","Medium","3 minutes ART 15 jour après le W-E de CTL","Détournement via L43",38672]
["2024-03-30","2024-04-15","NW",1,"50","A+B","DENDERLEEUW","AALST","AllWeek","Continuous","01:00","04:00","Omvorming rooster Denderleeuw volgens richtplan.\r\nSporen 2+3 Denderleeuw eveneens buiten dienst.\r\nSpoor 1 berijdbaar kant Liedekerke.\r\n\r\nVernieuwing brug over de Dender.\r\n\r\n* L89 overdag in dienst!","CTL","High"," "," ",47668]
["2024-03-30","2024-04-15","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","AllWeek","Continuous","01:00","04:00","Linked to coupure nr 47668 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.\r\nSporen 2+3 Denderleeuw eveneens buiten dienst.\r\nSpoor 1 berijdbaar kant Liedekerke.\r\n\r\nVernieuwing brug over de Dender.\r\n\r\n*","CTL","High"," "," ",47668]
["2024-03-30","2024-04-15","NW",1,"89","A+B","DENDERLEEUW","BURST","AllWeek","Continuous","01:00","04:00","Linked to coupure nr 47668 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.\r\nSporen 2+3 Denderleeuw eveneens buiten dienst.\r\nSpoor 1 berijdbaar kant Liedekerke.\r\n\r\nVernieuwing brug over de Dender.\r\n\r\n*","Autre","Minor_AdHoc"," "," ",47668]
["2024-03-30","2024-03-31","SE",3,"161","A/B","BAKENBOS","OTTIGNIES","Weekend","Day","08:00","16:00","Visite voies A/B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 08h00 et 16h00 le samedi et le dimanche,  avec adaptations trains"," ",48908]
["2024-03-31","2024-03-31","SE",3,"130","A/B","MOUSTIER","AUVELAIS","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49180]
["2024-04-01","2024-04-03","NE",2,"12","*","Y.ANTWERPEN-SCHIJNPOORT","Y.ANTWERPEN-SCHIJNPOORT","Week","Day","08:30","15:30","onderhoud bundelkop bundel C wissels 35N-34BN-36N-34AN","Autre","Minor_AdHoc","werken  bundel C thv van sein RN.12-AN.12-PN.12"," ",60080]
["2024-04-01","2024-04-05","NE",1,"27","A+B","Y.LIERSESTEENWEG","ANTWERPEN-BERCHEM","Week","Night","23:50","04:30","vernieuwing waterdichte rok van de kruisingsbrug BX15/L27A te Mortsel\r\nmeewerken met DVE Y Drabstraat\r\n+\r\nVernieuwing van  Y-Drabstraat (colt 58935)\r\n+\r\nonderhoud SIG Y stadion +Y noord Groenenhoek 4 nachten (colt 59719)","CTL","Minor_AdHoc","Alternatief E2894-E1996-E1972"," ",58225]
["2024-04-01","2024-04-05","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Week","Night","23:50","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3-9?","CTL","Minor_AdHoc","sporen3-9?"," ",58194]
["2024-04-01","2024-04-05","NE",2,"27","A+B","Y.BERCHEM-STADION","Y.LIERSESTEENWEG","Week","Night","23:35","04:35","Vernieuwing van  Y-Drabstraat\r\n\r\n====> zie Colt 58225","CTL","Minor_AdHoc","Alternatief E2894-E1996-E1972"," ",58935]
["2024-04-01","2024-04-05","NE",2,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","Week","Night","23:40","04:45","onderhoud TRA+SIG+OW \r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst","CTL","Minor_AdHoc"," "," ",60048]
["2024-04-01","2024-04-05","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59857]
["2024-04-01","2024-04-05","SE",1,"130","A","FRANIERE","Y.FLAWINNE","Week","Continuous","05:30","23:30","Aménagement gare de Floreffe \r\nSAVU voie B. Voie A HS\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc",null," ",47407]
["2024-04-01","2024-04-26","SE",1,"130","A+B","FLOREFFE","FLOREFFE","AllWeek","Continuous","04:30","05:00","ART de protection et de stabilisation lors de l'aménagement de la gare de Foreffe\r\nDossier de concertation validé le 26 octobre 2021","ART","Minor_AdHoc","ART de protection = ART de stabilisation à 40km/h pendant toute la durée du chantier\r\nPerte de temps de 2,25 min pour HKV et 3min pour HKM dans les 2 voies du premier WE jusqu'à une semaine après le dernier WE"," ",48753]
["2024-04-01","2024-06-09","SW",1,"140","A/B","LA ROCHE(BRABANT)","TILLY","AllWeek","Continuous","06:00","17:00","Sécurisation paroi rocheuse (400m)","SAVU","High",null," ",48256]
["2024-04-01","2024-12-08","SW",1,"124","*","CHARLEROI-SUD","CHARLEROI-SUD","AllWeek","Continuous","06:00","22:00","Linked to coupure nr 27208 on line 130C tracks(s) * from CHARLEROI-SUD to CHARLEROI-SUD: CSV Charleroi - Phases 9 + 10\r\nPhase 9 : Voie III HS et voie II en CDS en continu - Période de travail 01/04/24 - 30/06/24\r\nPhase 10 : Voie II HS et voie I en CDS e","Autre","Minor_AdHoc"," "," ",27208]
["2024-04-01","2024-12-08","SW",1,"130C","*","CHARLEROI-SUD","CHARLEROI-SUD","AllWeek","Continuous","06:00","22:00","CSV Charleroi - Phases 9 + 10\r\nPhase 9 : Voie III HS et voie II en CDS en continu - Période de travail 01/04/24 - 30/06/24\r\nPhase 10 : Voie II HS et voie I en CDS en continu - - Période de travail 05/08/24 - 03/11/24\r\nTravaux SNCB","Autre","Minor_AdHoc",null," ",27208]
["2024-04-01","2024-04-01","SE",1,"154","A+B","YVOIR","DINANT","Week","Continuous","09:00","15:00","Renouvellement de Ballast (C75)\r\nWE 2/3 CTL R1","CTL","Medium",null,"HKM à adapter",49937]
["2024-04-02","2024-04-05","SW",1,"78","A+B","SAINT-GHISLAIN","TOURNAI","Week","Night","22:55","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x8km) + traverses biblocs\r\nTravaux de finition","CTL","Minor_AdHoc",null," ",61271]
["2024-04-02","2024-04-06","NW",3,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,59188]
["2024-04-02","2024-04-06","NW",3,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 59188 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,59188]
["2024-04-02","2024-04-06","NW",3,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 59188 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,59188]
["2024-04-02","2024-04-06","NW",3,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 59188 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,59188]
["2024-04-02","2024-04-08","SW",1,"124","A","LUTTRE","ROUX","AllWeek","Continuous","06:00","06:00","Aménagement Gare de Luttre : Phase 3-2024\r\nDossier de concertation validé le 28 octobre 2021","SAVU_CTRL","Minor_AdHoc","Voies I en gare de Luttre inaccessible en continu\r\nCTL L124 de nuit en semaine (quais de Luttre inclu) : 22h00 - 06h00\r\nIndisponibilité de la transversale Sud à partir du 09/02 (voie déviée)\r\nL124 (A+B = 800m) : du 01/04/24 au 20/04/24 HKV : 2,56, HKM 4"," ",49471]
["2024-04-02","2024-04-17","SE",3,"162","A+B","BOIS D'AUSSE","BRAIBANT","AllWeek","Continuous","04:20","23:00","ART 3min\r\nRemplacement du PI à Florée au km 82,697","ART","Minor_AdHoc",null," ",59608]
["2024-04-03","2024-04-03","NW",3,"202B","S","Y.EIVOORDE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Day","10:00","18:00","R-419008-01\r\n\r\nonderhoud werkveld 3421-36\r\n\r\nAW 72R-73R-74R-74XR-75R-80R-82R-83R\r\n\r\nBundel Ramskapelle niet bereikbaar","Autre","Minor_AdHoc"," ","Info Racc.",60368]
["2024-04-03","2024-04-06","CE",1,"96","A+B","BRUXELLES-MIDI","Y.NOORD HALLE","Week","Night","00:40","04:40","Vernieuwen sp A L96: voorbereidende nachten Fase 2","CTL","Minor_AdHoc","TLO L96+96N tussen FBMZ en Halle."," ",50041]
["2024-04-05","2024-04-08","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59563]
["2024-04-05","2024-04-08","CE",2,"96B","*","FOREST-VOITURES-QUAI SERVICE","FOREST-MIDI-VOIES 920/926","Weekend","Continuous","22:30","04:00","Onderhoudswerken volgens onderhoudskalender Area CE, zone FBKI_15, bundel A en B","Autre","Minor_AdHoc","Bundel A en B buiten dienst voor onderhoudswerken"," ",58634]
["2024-04-05","2024-04-08","NE",2,"10","A","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58678 on line 10 tracks(s) B from Y.KOESTRAAT to Y.HAZOP: aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc"," "," ",58678]
["2024-04-05","2024-04-08","NE",2,"10","B","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc","DOES op spoor A L10 / bundel Zuid afgesloten"," ",58678]
["2024-04-05","2024-04-08","NE",2,"19","A+B","BALEN-WERKPLAATSEN","HAMONT-GRENS","Weekend","Continuous","23:50","04:00","vervolg railvernieuwing 2023\r\nsporen 493+494 in Neerpelt mee in BD\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (colt 59901)","CTL","Medium","alternatief Z4321-Z4322-Z4324 R5"," ",58122]
["2024-04-05","2024-04-08","SE",1,"130","A+B","MOUSTIER","Y.FLAWINNE","Weekend","Continuous","23:30","05:30","Aménagement gare de Floreffe\r\nWE 2/6\r\nDossier de concertation validé le 26 octobre 2021","CTL","Medium",null," ",47408]
["2024-04-05","2024-04-08","SE",1,"130/1","S","MOUSTIER-GARAGE","ENTREE RACC.MOUSTIER-SOLVAY 1","Weekend","Continuous","23:30","05:30","Linked to coupure nr 47408 on line 130 tracks(s) A+B from MOUSTIER to Y.FLAWINNE: Aménagement gare de Floreffe\r\nWE 2/6\r\nDossier de concertation validé le 26 octobre 2021","CTL","Medium"," "," ",47408]
["2024-04-05","2024-04-08","SE",1,"165","B","SAINT-VINCENT-BELLEFONTAINE","HALANZY","Weekend","Continuous","23:00","05:00","Renouvellement AS entrée de Virton : phase VB.","SAVU_CTRL","Minor_AdHoc","MHS limitée à Signeulx et non à Halanzy.\r\nCTL dans blanc fret (samedi 23h / dimanche 15h + nuit dimanche/lundi).\r\nLiaison 01 non parcourable entre les phases.\r\nPas d'ART car vitesse permanente = 50 km/h.\r\n/!\\ Selon plan d'aménagement, interversion des p"," ",47771]
["2024-04-05","2024-04-08","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 3-2024\r\nWeek-end 1/1\r\nIndisponibilité de la transversale Sud à partir du 09/02 (voie déviée)","CTL","Medium","Voies I, II, III en gare de Luttre inaccessible en continu\r\nIndisponibilité de la transversale Sud à partir du 09/02 (voie déviée)\r\nL124 (A+B = 800m) : du 01/04/24 au 20/04/24 HKV : 2,56, HKM 4,88"," ",49782]
["2024-04-05","2024-04-08","SW",1,"124A","A","LUTTRE","ROUX","Weekend","Continuous","23:30","04:40","Linked to coupure nr 49782 on line 124 tracks(s) A+B from LUTTRE to Y.NORD: Aménagement Gare de Luttre : Phase 3-2024\r\nWeek-end 1/1\r\nIndisponibilité de la transversale Sud à partir du 09/02 (voie déviée)","SAVU","Minor_AdHoc"," "," ",49782]
["2024-04-05","2024-04-08","SE",1,"154","A+B","YVOIR","DINANT","Weekend","Continuous","23:50","04:20","Renouvellement de Ballast (C75)\r\nWE 3/6","CTL","Medium","Chantier replanifié à la demande de la SNCB ou conséquence d’une replanification demandée par la SNCB. Voir réunion d'escalade du 17/02/2022 et accord de la SNCB du 18/02/2022","HKM à adapter",49933]
["2024-04-06","2024-04-07","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60420]
["2024-04-06","2024-04-07","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60420 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60420]
["2024-04-06","2024-04-07","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60420 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60420]
["2024-04-06","2024-04-07","NW",3,"75","B","GENT-SINT-PIETERS","DEINZE","Weekend","Night","22:15","06:00","vervangen rijdraad SP B - JVO\r\nSP A bijkomend tijdens de nacht 00.20-05.15","SAVU_CTRL","Minor_AdHoc",null," ",58594]
["2024-04-06","2024-04-07","SE",1,"165","B","SAINT-VINCENT-BELLEFONTAINE","HALANZY","Weekend","Continuous","23:00","15:00","Renouvellement AS entrée de Virton : phase VB.","CTL","Medium","MHS limitée à Signeulx et non à Halanzy.\r\nCTL dans blanc fret (samedi 23h / dimanche 15h + nuit dimanche/lundi).\r\nLiaison 01 non parcourable entre les phases.\r\nPas d'ART car vitesse permanente = 50 km/h"," ",59333]
["2024-04-06","2024-04-07","SE",3,"130","A+B","NAMUR","AUVELAIS","Weekend","Continuous","23:40","14:50","Mini CTL pour maintenance globale  L130  + L130/1 + L144","CTL","Medium",null," ",50426]
["2024-04-06","2024-04-07","SE",3,"130/1","A","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Weekend","Continuous","23:40","14:50","Linked to coupure nr 50426 on line 130 tracks(s) A+B from NAMUR to AUVELAIS: Mini CTL pour maintenance globale  L130  + L130/1 + L144","CTL","Medium"," "," ",50426]
["2024-04-06","2024-04-07","SE",3,"144","A","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Weekend","Continuous","23:40","14:50","Linked to coupure nr 50426 on line 130 tracks(s) A+B from NAMUR to AUVELAIS: Mini CTL pour maintenance globale  L130  + L130/1 + L144","CTL","Medium"," "," ",50426]
["2024-04-06","2024-04-07","SW",3,"130","A+B","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Weekend","Continuous","23:40","14:50","Maintenance Z19. 51\r\nMini CTL","CTL","Medium"," "," ",49165]
["2024-04-06","2024-04-07","SW",3,"90C","A+B","JURBISE","BRUGELETTE","Weekend","Continuous","06:00","17:00","Maintenance Z7.53","CTL","Medium",null,"HKM à adapter",55977]
["2024-04-06","2024-04-08","CE",1,"96","A+B","Y.RUISBROEK","Y.NOORD HALLE","Weekend","Continuous","00:45","04:45","Vernieuwing TB perron Lot met kraan. Fase 1 WE 1/3.","CTL","Medium","TLO L96+96E tussen Halle en Ruisbroek."," ",52947]
["2024-04-06","2024-04-08","CE",1,"96E","S","HALLE","LOT","Weekend","Continuous","00:45","04:45","Linked to coupure nr 52947 on line 96 tracks(s) A+B from Y.RUISBROEK to Y.NOORD HALLE: Vernieuwing TB perron Lot met kraan. Fase 1 WE 1/3.","CTL","Medium"," "," ",52947]
["2024-04-06","2024-04-08","NE",1,"12","A+B","ESSEN","KALMTHOUT","Weekend","Night","00:00","05:00","vernieuwing wissels Essen +onderhoud","CTL","Minor_AdHoc"," "," ",58783]
["2024-04-06","2024-04-08","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58011]
["2024-04-06","2024-04-08","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","migratie tunnelveiligheidtechnieken Antw NZ\r\nantwerpen centraal -antwerpen luchtbal","CTL","Medium"," "," ",59054]
["2024-04-06","2024-04-08","NE",2,"25","A+B","SCHAERBEEK","VILVOORDE","Weekend","Continuous","00:00","04:00","werken viaduct Vilvoorde --> door de werkvennootschap voor de werken aan de ring van Brussel\r\n\r\nDe demontage van deze stellingsmoten (moot 17+18 - hernummering tov vorig jaar !) dient te gebeuren in de periode tussen 01/02/2024 & 30/04/2024. \r\nIn deze p","CTL","Medium"," "," ",58770]
["2024-04-06","2024-04-08","NE",2,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","Weekend","Continuous","00:00","04:00","onderhoud TRA+SIG+OW \r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst\r\n+92\r\nwerken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren) colt 59092","CTL","Medium"," "," ",60055]
["2024-04-06","2024-04-08","NW",2,"59","A+B","LOKEREN","SINT-NIKLAAS","Weekend","Continuous","06:00","04:20","Onderhoud\r\n\r\n\r\n* Lokeren:\r\n- Rooster kant Antwerpen inbegrepen + SP IV\r\n- gevallen BVL perronsporen enkel tijdens de nacht\r\n* Sint Niklaas \r\n- Rooster kant Gent inbegrepen + SP IV en V\r\n- gevallen BVL perronsporen enkel tijdens de nacht","CTL","Medium"," "," ",60169]
["2024-04-07","2024-04-07","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59983]
["2024-04-07","2024-04-07","NW",3,"202B/1","S","Y.PELIKAAN","ZEEBRUGGE-BUNDEL PELIKAAN","Weekend","Day","06:00","22:00","R-419045-01\r\n\r\nOmvormen 51AR-51BR-52AR-54R-55R-56R-57R van He-H dmv voorgemonteerde panelen werkveld 3421-31\r\n\r\nBundel Pelikaan","CTL","Minor_AdHoc"," ","Info Racc",60381]
["2024-04-07","2024-04-07","NW",3,"202B/2","S","ZEEBRUGGE-BUNDEL PELIKAAN","Y.EIVOORDE","Weekend","Day","06:00","22:00","Linked to coupure nr 60381 on line 202B/1 tracks(s) S from Y.PELIKAAN to ZEEBRUGGE-BUNDEL PELIKAAN: R-419045-01\r\n\r\nOmvormen 51AR-51BR-52AR-54R-55R-56R-57R van He-H dmv voorgemonteerde panelen werkveld 3421-31\r\n\r\nBundel Pelikaan","CTL","Minor_AdHoc"," ","Info Racc",60381]
["2024-04-08","2024-04-08","SE",3,"130","A/B","NAMUR","FLAWINNE","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49047]
["2024-04-08","2024-04-10","NE",2,"12","*","Y.ANTWERPEN-SCHIJNPOORT","Y.ANTWERPEN-SCHIJNPOORT","Week","Day","08:30","15:30","onderhoud bundelkop bundel C wissels 33AN,33BN,3AN/32N,31BN,01Q,02Q,03Q","Autre","Minor_AdHoc","werken  bundel E -F thv van sein ON.12 en NN.12 en MN12 en TO.12"," ",60079]
["2024-04-08","2024-04-12","NE",2,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","Week","Night","23:40","04:45","onderhoud TRA+SIG+OW \r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst","CTL","Minor_AdHoc"," "," ",60049]
["2024-04-08","2024-04-12","NE",2,"53","A+B","MECHELEN","Y.HEIKE","Week","Night","23:50","04:00","masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6","CTL","Minor_AdHoc"," "," ",58327]
["2024-04-08","2024-04-12","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59858]
["2024-04-08","2024-04-12","SW",2,"112","A","LA LOUVIERE-CENTRE","LA LOUVIERE-CENTRE","Week","Night","23:30","05:15","Linked to coupure nr 53892 on line 116 tracks(s) A from Y.LA PAIX to LA LOUVIERE-GARE INDUSTRIELLE: Construction passerelle gare de LLV Centre. Réalilsation pieux coté L116","SAVU","Minor_AdHoc"," ","InfoRacc",53892]
["2024-04-08","2024-04-12","SW",2,"116","A","Y.LA PAIX","LA LOUVIERE-GARE INDUSTRIELLE","Week","Night","23:30","05:15","Construction passerelle gare de LLV Centre. Réalilsation pieux coté L116","CTL","Minor_AdHoc","MHS L116 + L112 VA de nuit. Circulation possible sur L112 VB","InfoRacc",53892]
["2024-04-08","2024-04-13","CE",1,"26","A+B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","Week","Night","23:30","04:00","Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1\r\nTLO-nachten voor plaatsen liggers en werken aan de brug.","CTL","Minor_AdHoc","TLO tussen Trapezium Linkebeek en Y Watermaal"," ",51880]
["2024-04-08","2024-04-13","NE",3,"27","A","ANTWERPEN-BERCHEM","Y.ARENDSTRAAT","Week","Night","23:30","04:30","L 27 spoor A onderhoud SIG schets \r\nY noord Berchem inbegrepen","SAVU","Minor_AdHoc",null," ",59720]
["2024-04-08","2024-04-13","NE",3,"59/1","B","ANTWERPEN-CENTRAAL","ANTWERPEN-BERCHEM","Week","Night","23:30","04:30","Linked to coupure nr 59720 on line 27 tracks(s) A from ANTWERPEN-BERCHEM to Y.ARENDSTRAAT: L 27 spoor A onderhoud SIG schets \r\nY noord Berchem inbegrepen","SAVU","Minor_AdHoc"," "," ",59720]
["2024-04-08","2024-04-19","SW",1,"124A","A+B","LUTTRE","ROUX","Week","Day","08:00","15:00","Aménagement Gare de Luttre : Phase 4-2024\r\nDossier de concertation validé le 28 octobre 2021","CTL","Minor_AdHoc","Voies IV et V en gare de Luttre inaccessible\r\nFaisceau accessoire en gare de Luttre inaccessible\r\nCTL L124A de jour en semaine (quais de Luttre inclu) : 08h00 - 15h00\r\nindisponibilité de la transversale Sud à partir du 09/02\r\nART de Stabilisation : 2,56"," ",49585]
["2024-04-08","2024-04-20","CE",1,"96","A+B","Y.RUISBROEK","Y.NOORD HALLE","AllWeek","Continuous","04:40","04:40","Stabilisatie-BTS Vernieuwing TB perron Lot met kraan.","ART","Minor_AdHoc","BTS"," ",56108]
["2024-04-08","2024-08-25","SE",1,"162","A","CINEY","HAVERSIN","AllWeek","Continuous","05:00","22:50","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 11\r\nciney-haversin","SAVU_CTRL","High","CTL de Nuit : Lu^Ma à Je^Ve :00:10–04:50, Ve^Sa 00:10–06:30, Sa^Di 23:10–06:30, Di^Lu 23:10–04:50\r\nvoies 1 et 2 en gare de Ciney en CDS"," ",47351]
["2024-04-08","2024-04-21","SE",1,"161","A+B","WATERMAEL","OTTIGNIES","AllWeek","Continuous","04:40","18:00","RER\r\nTravaux plateformes, voies, signalisation et caténaires à Watermael et sur le tronçon Bakenbos-Ottignies\r\nART 4 min","ART","Minor_AdHoc"," "," ",50022]
["2024-04-08","2024-04-08","SE",1,"154","A+B","YVOIR","DINANT","Week","Continuous","09:00","15:00","Renouvellement de Ballast (C75)\r\nWE 3/3 CTL R1","CTL","Medium",null,"HKM à adapter",49938]
["2024-04-09","2024-04-12","CE",1,"96","A+B","BRUXELLES-MIDI","Y.NOORD HALLE","Week","Night","00:40","04:40","Vernieuwen sp A L96: voorbereidende nachten Fase 2","CTL","Minor_AdHoc","TLO L96+96N tussen FBMZ en Halle."," ",50042]
["2024-04-09","2024-04-12","NE",1,"25","A+B","SCHAERBEEK","VILVOORDE","Week","Night","00:00","04:30","werken viaduct Vilvoorde --> door de werkvennootschap voor de werken aan de ring van Brussel\r\n\r\nDe demontage van deze stellingsmoten (moot 17+18 - hernummering tov vorig jaar !) dient te gebeuren in de periode tussen 01/02/2024 & 30/04/2024. \r\nIn deze p","CTL","Minor_AdHoc"," "," ",58771]
["2024-04-09","2024-04-12","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","afbraak trapkooien perrons 1+2 te Vilvoorde\r\n\r\nVilvoorde sporen 1+2+3","CTL","Minor_AdHoc","sporen1+2+3"," ",58195]
["2024-04-09","2024-04-12","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Week","Night","00:00","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Minor_AdHoc"," "," ",58215]
["2024-04-09","2024-04-12","NE",2,"53A","A+B","Y.MUIZEN","MECHELEN","Week","Night","00:00","04:00","masterplan mechelen\r\nperronsporen 6 (met L27,L53)","CTL","Minor_AdHoc","spoor 6"," ",58287]
["2024-04-11","2024-04-15","NE",3,"34","A+B","HASSELT","Y.GLONS","AllWeek","Continuous","01:00","04:00","IDS SW ETCS L2-IL_NO_P029_04-07_L34_Bilzen - Y Glons_IL","CTL","Medium"," ","Info Racc.",61996]
["2024-04-12","2024-04-14","SE",3,"125A","*","KINKEMPOIS-BLOCK 2","KINKEMPOIS-RELAIS","Weekend","Continuous","23:00","05:00","Z.20.41 P4+ Maintenance AI 41.","Autre","Minor_AdHoc"," "," ",57876]
["2024-04-12","2024-04-14","SW",2,"112","A/B","MARCHIENNE-AU-PONT","PIETON","Weekend","Continuous","23:30","16:00","Tir de fils de contacts avec autorail","SAVU","Minor_AdHoc"," "," ",53198]
["2024-04-12","2024-04-15","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59564]
["2024-04-12","2024-04-15","NE",2,"10","A","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58679 on line 10 tracks(s) B from Y.KOESTRAAT to Y.HAZOP: aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen do","SAVU","Minor_AdHoc"," "," ",58679]
["2024-04-12","2024-04-15","NE",2,"10","B","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","SAVU","Minor_AdHoc","DOES op spoor A L10 / bundel Zuid afgesloten\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk"," ",58679]
["2024-04-12","2024-04-15","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59902]
["2024-04-12","2024-04-15","SE",1,"130","A+B","MOUSTIER","Y.FLAWINNE","Weekend","Continuous","23:30","05:30","Aménagement gare de Floreffe\r\nWE 3/6\r\n+ Renouvellement PS BK 0.796","CTL","Medium",null," ",47411]
["2024-04-12","2024-04-15","SE",1,"130/1","A+B","ENTREE RACC.MOUSTIER-SOLVAY 1","MOUSTIER-GARAGE","Weekend","Continuous","23:30","05:30","Linked to coupure nr 47411 on line 130 tracks(s) A+B from MOUSTIER to Y.FLAWINNE: Aménagement gare de Floreffe\r\nWE 3/6\r\n+ Renouvellement PS BK 0.796","CTL","Medium"," "," ",47411]
["2024-04-12","2024-04-15","SE",1,"162","A+B","MARLOIE","MARLOIE","Weekend","Continuous","08:00","06:00","Pose AW 07AC","CTL","Medium","Voie A et B et la voie I (101) dans la gare Marloie\r\nVoie IV Marloie accessible \r\n+ Passage voies 105 et 106 possible",null,38734]
["2024-04-12","2024-04-15","SE",1,"165","A","SAINT-VINCENT-BELLEFONTAINE","VIRTON","Weekend","Continuous","23:00","05:00","Renouvellement AS entrée de Virton : phase VA.","SAVU_CTRL","Minor_AdHoc","MHS jusqu'en gare de Virton (voie 2 à quai incluse).\r\nCTL dans blanc fret (samedi 23h / dimanche 15h + nuit dimanche/lundi).\r\nLiaison 01 non parcourable entre les phases.\r\nPas d'ART car vitesse permanente = 50 km/h"," ",47772]
["2024-04-12","2024-04-15","SE",1,"43","A+B","MARLOIE","MARLOIE","Weekend","Continuous","08:00","06:00","Linked to coupure nr 38734 on line 162 tracks(s) A+B from MARLOIE to MARLOIE: Pose AW 07AC","CTL","Medium"," ",null,38734]
["2024-04-12","2024-04-15","SE",2,"166","A/B","ANSEREMME","HOUYET","Weekend","Continuous","23:00","05:00","Entretien AS , traitement zone boueuse","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 15/04 au 18/04 (fin probable)"," ",57697]
["2024-04-12","2024-04-15","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 min"," ",48630]
["2024-04-12","2024-04-15","SE",1,"161","A+B","BRUXELLES-LUXEMBOURG","OTTIGNIES","Weekend","Continuous","23:30","04:50","RER Watermael - Ottignies\r\nFinitions après semaine CTL de Pâques","CTL","Medium","ART id 50022"," ",49265]
["2024-04-12","2024-04-15","SE",3,"161","A+B","OTTIGNIES","BAKENBOS","Weekend","Continuous","23:00","05:00","Maintenance\r\nEntretien + Végétation","CTL","Medium","CTL en continu"," ",53057]
["2024-04-12","2024-04-15","SE",1,"154","A+B","YVOIR","DINANT","Weekend","Continuous","23:50","04:20","Renouvellement de Ballast (C75)\r\nWE 4/6","CTL","Medium",null,"HKM à adapter",49934]
["2024-04-13","2024-04-14","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61581]
["2024-04-13","2024-04-14","NW",3,"204","*","GENT-RODENHUIZE","GENT-RODENHUIZEDOK","Weekend","Continuous","22:00","14:00","Reservatie onderhoud, enkel bundel Mercator buiten dienst","CTL","Medium",null,"Info Racc",60414]
["2024-04-13","2024-04-14","SE",1,"165","A","SAINT-VINCENT-BELLEFONTAINE","VIRTON","Weekend","Continuous","23:00","15:00","Renouvellement AS entrée de Virton : phase VA.","CTL","Medium","MHS jusqu'en gare de Virton (voie 2 à quai incluse).\r\nCTL dans blanc fret (samedi 23h / dimanche 15h + nuit dimanche/lundi).\r\nLiaison 01 non parcourable entre les phases.\r\nPas d'ART car vitesse permanente = 50 km/h"," ",59334]
["2024-04-13","2024-04-14","SE",1,"166","A+B","ANSEREMME","HOUYET","Weekend","Continuous","23:00","15:00","Massification travaux OA tronçons Anseremme - Gendron et Gendron - Houyet (entretien tunnels, parois,...)","CTL","Medium","intervient avec le grand SAVU Houyet – Gendron ; pas d’ART supplémentaire !"," ",47504]
["2024-04-13","2024-04-14","SW",3,"130","A+B","CHARLEROI-SUD","COUILLET","Weekend","Continuous","06:00","17:00","Maintenance Z10. 51   P4+","CTL","Medium","Détails car sur plusieurs lignes:\r\nL130\tVoie B\tCharleroi-Sud\tChâtelet\tD08-G. 20   &\t FX3_I. 20\r\n\t        Voie A\t\t\t                        D09-G. 20    &  F4_I. 20\r\n\t\t\t\tE10_H. 20   &\tF4_I. 20\r\n\t\t\t\tE11_H. 20   &\tF4_I. 20\r\n\t\t\t\tE12_H. 20   &\tF4_I. 20"," ",48836]
["2024-04-13","2024-04-14","SW",3,"90C","A+B","ATH","BRUGELETTE","Weekend","Continuous","06:00","17:00","Maintenance Z13.54","CTL","Medium",null,"HKM à adapter",58838]
["2024-04-13","2024-04-15","CE",1,"96","A+B","BRUXELLES-MIDI","Y.NOORD HALLE","Weekend","Continuous","00:40","04:40","Vernieuwing TB perron Lot met kraan. Fase 1 WE 2/3 + voorbereidingsWE Fase 2","CTL","Medium","TLO L96 tussen FBMZ en Halle."," ",50040]
["2024-04-13","2024-04-15","CE",1,"96A","A+B","FOREST-MIDI","Y.RUISBROEK","Weekend","Continuous","00:40","04:40","Linked to coupure nr 50040 on line 96 tracks(s) A+B from BRUXELLES-MIDI to Y.NOORD HALLE: Vernieuwing TB perron Lot met kraan. Fase 1 WE 2/3 + voorbereidingsWE Fase 2","CTL","Medium"," "," ",50040]
["2024-04-13","2024-04-15","CE",1,"96E","S","Y.NOORD HALLE","LOT","Weekend","Continuous","00:40","04:40","Linked to coupure nr 50040 on line 96 tracks(s) A+B from BRUXELLES-MIDI to Y.NOORD HALLE: Vernieuwing TB perron Lot met kraan. Fase 1 WE 2/3 + voorbereidingsWE Fase 2","CTL","Medium"," "," ",50040]
["2024-04-13","2024-04-15","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","CTL","Medium","herlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk"," ",58012]
["2024-04-13","2024-04-15","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3+4+5+6","CTL","Medium","sporen3+4+5+6"," ",58197]
["2024-04-13","2024-04-15","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:00","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","CTL","Medium","herlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk"," ",58218]
["2024-04-13","2024-04-15","NE",2,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","Weekend","Continuous","00:00","04:00","onderhoud TRA+SIG+OW \r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst\r\n+\r\nwerken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren) colt 59091","CTL","Medium"," "," ",60056]
["2024-04-13","2024-04-15","NE",2,"53","A","MECHELEN","Y.HEIKE","Weekend","Continuous","00:00","04:00","masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","CTL","Medium","herlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk"," ",58328]
["2024-04-13","2024-04-15","NE",2,"53","A+B","MECHELEN","MUIZEN","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58328 on line 53 tracks(s) A from MECHELEN to Y.HEIKE: masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","CTL","Medium"," "," ",58328]
["2024-04-13","2024-04-15","NE",2,"53A","A+B","Y.MUIZEN","MECHELEN","Weekend","Continuous","00:00","04:00","masterplan mechelen\r\nperronsporen 6 (met L27,L53)\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","CTL","Medium","spoor 6\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk"," ",58288]
["2024-04-13","2024-04-15","NE",3,"12","A+B","Y.LUCHTBAL","Y.SINT-MARIABURG","Weekend","Continuous","06:00","04:10","Oude landen project 308+304\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","CTL","Medium","Aan deze werken is een R7 (van 06h00 tot 17h30) gekoppeld op L27A voor het spoorgedeelte Y.Laarsebeek - Y.Schijn!! (58226)\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk"," ",57552]
["2024-04-13","2024-04-15","SE",1,"166","A+B","ANSEREMME","HOUYET","Weekend","Continuous","06:00","04:30","CR L166 2024\r\nMassification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse","CTL","Medium","Pas d'ART après le WE","HKM à adapter",60552]
["2024-04-14","2024-04-14","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","LUCHTBAL-ROOSTER S","Weekend","Day","06:00","17:40","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat\r\n\r\ngekoppeld aan colt 57552","CTL","Minor_AdHoc"," "," ",58226]
["2024-04-14","2024-04-14","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61609]
["2024-04-14","2024-04-14","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59984]
["2024-04-15","2024-04-19","CE",2,"26","A+B","Y.ENTREE GROUPE R","Y.NOORD HALLE","Week","Night","23:40","04:00","Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zijtakken: L26/5, L26/4, L26/3, L26/2, L26/1, L36/3, L36/1 en L36C/2","CTL","Minor_AdHoc","TLO L26","Info Racc",59507]
["2024-04-15","2024-04-19","CE",2,"26/1","A+B","Y.KEELBEEK","Y.MACHELEN","Week","Night","23:40","04:00","Linked to coupure nr 59507 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59507]
["2024-04-15","2024-04-19","CE",2,"26/2","A+B","ETTERBEEK","Y.ETTERBEEK","Week","Night","23:40","04:00","Linked to coupure nr 59507 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59507]
["2024-04-15","2024-04-19","CE",2,"26/3","A+B","Y.WATERMAEL","WATERMAEL","Week","Night","23:40","04:00","Linked to coupure nr 59507 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59507]
["2024-04-15","2024-04-19","CE",2,"26/4","A+B","ETTERBEEK","Y.BOONDAEL","Week","Night","23:40","04:00","Linked to coupure nr 59507 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59507]
["2024-04-15","2024-04-19","CE",2,"26/5","A+B","Y.LINKEBEEK-HALLE","Y.LINKEBEEK","Week","Night","23:40","04:00","Linked to coupure nr 59507 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59507]
["2024-04-15","2024-04-19","NE",2,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","Week","Night","23:40","04:45","onderhoud TRA+SIG+OW \r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst\r\n\r\nNOG TE VERPLAATSEN","CTL","Minor_AdHoc"," "," ",60047]
["2024-04-15","2024-04-19","NE",2,"53","A+B","MECHELEN","Y.HEIKE","Week","Night","00:00","04:00","masterplan mechelen \r\ndeels met L27,L53A en sporen 5+6","CTL","Minor_AdHoc"," "," ",58329]
["2024-04-15","2024-04-19","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59859]
["2024-04-15","2024-04-19","NE",3,"59","A+B","Y.ANTWERPEN-ZUID","Y.MELSELE","Week","Night","23:50","04:35","onderhoud SIG,wissels en overwegen","CTL","Minor_AdHoc","alternatief E723-E744"," ",60211]
["2024-04-15","2024-04-20","CE",1,"26","A+B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","Week","Night","23:30","04:00","Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1\r\nTLO-nachten voor plaatsen liggers en werken aan de brug.","CTL","Minor_AdHoc","TLO tussen Trapezium Linkebeek en Y Watermaal"," ",51881]
["2024-04-15","2024-04-20","SW",2,"112","B","LA LOUVIERE-CENTRE","LA LOUVIERE-CENTRE","Week","Continuous","09:00","05:20","Construction passerelle gare de LLV Centre. Réalilsation micro-pieux quai central","SAVU_CTRL","Minor_AdHoc","L112 VB en continu = Voie 1 (AS ne)\r\nSAVU de jour (9h-15h) + CTL de nuit : 23:20 - 5:20\r\nMaintenir circulation aux heures de pointes pour éviter un dérouillage","HKM à adapter",53893]
["2024-04-15","2024-05-06","SE",1,"162","B","MARLOIE","MARLOIE","AllWeek","Continuous","06:00","06:00","Pose des nouvelles bordures de quai coté voie B\r\nDépose des bordures de quai cote voie IV,\r\nDépose et pose d’AW 08C + dépose d’AW 09 C et pose de la TJD MAR 6\r\nBourrage de la voie IV+ AW 08C, de la voie V +TJD MAR6\r\nPose des nouvelles bordures de quai c","SAVU_CTRL","High","La MHS + MHT des voies IV+V\r\nSAVU entre Haversin (liaison 34AK/34 BK 100.907) et Marloie (liaison 17AC/17BC BK 113.826)\r\nLa voie A en service avec réduction vitesse à 40km/h, HKV=3.55min, HKM=5.60 min\r\nLes voies à quais : \r\nvoie I  - pour le train venan"," ",51020]
["2024-04-15","2024-05-12","SE",1,"24","A","Y.GLONS","BASSENGE","AllWeek","Continuous","07:00","22:00","Sécurisation d'ouvrages et réfection de chapes d'étanchéité","SAVU","High","ART 6min"," ",50613]
["2024-04-15","2025-04-22","NW",1,"50","*","DENDERLEEUW","DENDERLEEUW","AllWeek","Continuous","04:00","04:00","Masterplan Denderleeuw (Project NMBS-Stations): SP IV en V buiten dienst buiten dienst","Autre","Minor_AdHoc"," "," ",48301]
["2024-04-15","2025-04-22","NW",1,"50","*","DENDERLEEUW","DENDERLEEUW","AllWeek","Continuous","04:00","04:00","Masterplan Denderleeuw (Project NMBS-Stations): SP IV en V buiten dienst buiten dienst","Autre","Minor_AdHoc"," "," ",48301]
["2024-04-16","2024-04-19","NE",2,"27","A+B","Y.WEERDE","MECHELEN-NEKKERSPOEL","Week","Night","00:00","04:00","masterplan Mechelen \r\ndeels met L53/53Asp 5+6","CTL","Minor_AdHoc"," "," ",58216]
["2024-04-16","2024-04-19","NE",2,"53A","A+B","Y.MUIZEN","MECHELEN","Week","Night","00:00","04:00","masterplan mechelen\r\nperronsporen 6 (met L27,L53)","CTL","Minor_AdHoc","spoor 6"," ",58289]
["2024-04-16","2024-04-19","NW",1,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53591]
["2024-04-16","2024-04-19","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 53591 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53591]
["2024-04-16","2024-04-19","NW",1,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 53591 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","SAVU","Minor_AdHoc"," "," ",53591]
["2024-04-17","2024-04-17","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60091]
["2024-04-18","2024-04-18","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60107]
["2024-04-19","2024-04-22","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59565]
["2024-04-19","2024-04-22","NE",1,"29","A+B","Y.KRUISBERG","TURNHOUT-BUNDEL","Weekend","Continuous","23:30","04:00","Linked to coupure nr 55027 on line 15 tracks(s) A+B from HERENTALS to GEEL: Etcs\r\n Meewerken mogelijk\r\n+\r\nbouw fietstunnel Geel aan OW 94 (RESERVE indien 2023 niet gehaald wordt) (58695)\r\n+\r\nwisselvernieuwing Olen (58092)","CTL","Medium"," "," ",55027]
["2024-04-19","2024-04-22","NE",2,"10","A","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58680 on line 10 tracks(s) B from Y.KOESTRAAT to Y.HAZOP: aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc"," "," ",58680]
["2024-04-19","2024-04-22","NE",2,"10","B","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc","DOES op spoor A L10 / bundel Zuid afgesloten"," ",58680]
["2024-04-19","2024-04-22","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59903]
["2024-04-19","2024-04-22","SE",1,"130","A+B","MOUSTIER","Y.FLAWINNE","Weekend","Continuous","23:30","05:30","Aménagement gare de Floreffe\r\nWE 4/6\r\nDossier de concertation validé le 26 octobre 2021","CTL","Medium",null,"L96 fermée nuit ven/sam - itinéraire via L130A-124A-117-96 + L75 + L130A-140-139 + 139-161-144-130-130A",48201]
["2024-04-19","2024-04-22","SE",1,"165","B","SAINT-VINCENT-BELLEFONTAINE","HALANZY","Weekend","Continuous","23:00","05:00","Renouvellement AS entrée de Virton : révision (1)","SAVU_CTRL","Minor_AdHoc","MHS limitée à Signeulx et non à Halanzy.\r\nCTL dans blanc fret (samedi 23h / dimanche 15h + nuit dimanche/lundi).\r\nPas d'ART car vitesse permanente = 50 km/h.\r\n/!\\ Selon plan d'aménagement, interversion des phases peut-être requise (VA avant ou après VB "," ",47773]
["2024-04-19","2024-04-22","SE",2,"162","A+B","LEIGNON","HAVERSIN-GARAGE","Weekend","Continuous","23:20","05:00","Travaux Axe 3:\r\nTravaux de traversée de voie + Massification OA","CTL","Medium","Suite arbitrage budgétaire - travaux effectués = Travaux de traversée de voie principalement \r\nART à déterminer","via L43",47359]
["2024-04-19","2024-04-22","SE",2,"40","A/B","BRESSOUX","VISE","Weekend","Continuous","23:30","05:00","Mise en servie EBP-PLP","SAVU_CTRL","Minor_AdHoc","SAVU VA HS le samedi\r\nCTL nuit sam/dim 23h30-5h\r\nSAVU VB HS le dimanche"," ",48400]
["2024-04-19","2024-04-22","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 5-2024\r\nWeek-end 1/1\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies I, II, III en gare de Luttre inaccessible en continu\r\nIndisponibilité de la transversale Sud à partir du 09/02 (voie déviée)\r\nL124 (A+B = 800m) : du 01/04/24 au 20/04/24 HKV : 2,56, HKM 4,88","L96 fermée nuit ven/sam - itinéraire via L130A-124A-117-96 + L75 + L130A-140-139 + 139-161-144-130-130A",49784]
["2024-04-19","2024-04-22","SW",1,"124A","A","LUTTRE","ROUX","Weekend","Continuous","23:30","04:40","Linked to coupure nr 49784 on line 124 tracks(s) A+B from LUTTRE to Y.NORD: Aménagement Gare de Luttre : Phase 5-2024\r\nWeek-end 1/1\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc"," ","L96 fermée nuit ven/sam - itinéraire via L130A-124A-117-96 + L75 + L130A-140-139 + 139-161-144-130-130A",49784]
["2024-04-19","2024-04-22","SW",2,"90","A+B","GERAARDSBERGEN","ATH","Weekend","Continuous","23:00","04:40","ETCS\r\nPLP - MES","CTL","Medium",null,"L96 fermée nuit ven/sam - itinéraire via L130A-124A-117-96 + L75 + L130A-140-139 + 139-161-144-130-130A\r\nInfoRacc",57449]
["2024-04-19","2024-04-27","CE",1,"124","B","BRUXELLES-MIDI","Y.FOREST-EST","AllWeek","Continuous","23:40","04:30","Linked to coupure nr 49980 on line 96 tracks(s) A from BRUXELLES-MIDI to Y.NOORD HALLE: Vernieuwen sp A L96 met P+C-trein. Fase 2.1 WE1-W1","SAVU","Minor_AdHoc"," "," ",49980]
["2024-04-19","2024-04-27","CE",1,"96","A","BRUXELLES-MIDI","Y.NOORD HALLE","AllWeek","Continuous","23:40","04:30","Vernieuwen sp A L96 met P+C-trein. Fase 2.1 WE1-W1","SAVU","Minor_AdHoc","DOES L96 tussen FBMZ en Halle.\r\nFBMZ Sp 19 BDS\r\nBijkomend sp B L124 tijdens werkperiode vernieuwingstreinen.\r\nBijkomend sp A L96N tijdens de nachten."," ",49980]
["2024-04-19","2024-04-22","SE",1,"154","A+B","YVOIR","DINANT","Weekend","Continuous","23:50","04:20","Renouvellement de Ballast (C75)\r\nWE 5/6","CTL","Medium",null,"HKM à adapter \r\nL96 fermée nuit ven/sam - itinéraire via L130A-124A-117-96 + L75 + L130A-140-139 + 139-161-144-130-130A",49935]
["2024-04-20","2024-04-21","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59430]
["2024-04-20","2024-04-21","NE",3,"27M/4","*","ANTWERPEN-NOORD-BUNDEL C1","ANTWERPEN-NOORD-BUNDEL C3","Weekend","Continuous","13:30","22:00","massificatiewerken C1/C2/C3","CTL","Medium","bundels C1-2-3 ontoegankelijk","Info Racc",60840]
["2024-04-20","2024-04-21","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60410]
["2024-04-20","2024-04-21","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60410 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60410]
["2024-04-20","2024-04-21","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60410 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60410]
["2024-04-20","2024-04-21","NW",3,"75","A","WAREGEM","KORTRIJK","Weekend","Night","22:15","06:00","vervangen rijdraad SP A - JVO\r\nSP B bijkomend tijdens de nacht 00.20-05.15","SAVU_CTRL","Minor_AdHoc",null," ",58599]
["2024-04-20","2024-04-21","SE",1,"165","B","SAINT-VINCENT-BELLEFONTAINE","HALANZY","Weekend","Continuous","23:00","15:00","Renouvellement AS entrée de Virton : révision (1)","CTL","Medium","MHS limitée à Signeulx et non à Halanzy.\r\nCTL dans blanc fret (samedi 23h / dimanche 15h + nuit dimanche/lundi).\r\nPas d'ART car vitesse permanente = 50 km/h.\r\n/!\\ Selon plan d'aménagement, interversion des phases peut-être requise (VA avant ou après VB "," ",59335]
["2024-04-20","2024-04-21","SW",2,"130","B","CHATELET-GRIL EST","CHATELET-GRIL OUEST","Weekend","Continuous","22:30","22:00","Maintenance Z17. 51 \r\nFaisceau de Chatelet","SAVU","Minor_AdHoc","Mise hors service en une zone (= Zone 17), voici les détails:\r\n- L130 Voie B entre F4-I. 20 et DX-J. 20;\r\nM-I.20 + J-I.20 + PC-I. 20 (faisceau A); + voie 320\r\n- F6-L. 20 + FX5-I. 20 (L130C en gare de Châtelet);\r\n- GC353-J. 20 + GC354-J. 20 + GC355-J. 20","HKM à adapter",55055]
["2024-04-20","2024-04-21","SW",3,"112","A+B","Y.SAINT-VAAST","LA LOUVIERE-CENTRE","Weekend","Continuous","06:00","17:00","Maintenance Z16.52","CTL","Medium"," "," ",60789]
["2024-04-20","2024-04-21","SW",3,"116","A+B","LA LOUVIERE-GARE INDUSTRIELLE","Y.LA PAIX","Weekend","Continuous","06:00","17:00","Linked to coupure nr 60789 on line 112 tracks(s) A+B from Y.SAINT-VAAST to LA LOUVIERE-CENTRE: Maintenance Z16.52","CTL","Medium"," "," ",60789]
["2024-04-20","2024-04-22","CE",1,"26","A+B","Y.RUE DE BRUEL","Y.NOORD HALLE","Weekend","Continuous","00:30","04:00","Massificatie: Carsoul - Onderhoud - BVL L26 P085306 - P103303 RER L124 Moensberg\r\n1) Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1 TLO-WE voor plaatsen liggers en werken aan de brug.\r\n2) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens","CTL","Medium","TLO tussen Y Bruulstr en Y Noord Halle","Info Racc",51875]
["2024-04-20","2024-04-22","CE",1,"26/1","A+B","Y.KEELBEEK","Y.MACHELEN","Weekend","Continuous","00:30","04:00","Linked to coupure nr 51875 on line 26 tracks(s) A+B from Y.RUE DE BRUEL to Y.NOORD HALLE: Massificatie: Carsoul - Onderhoud - BVL L26 P085306 - P103303 RER L124 Moensberg\r\n1) Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1 TLO-WE voor plaatsen liggers","CTL","Medium"," ","Info Racc",51875]
["2024-04-20","2024-04-22","CE",1,"26/2","A+B","ETTERBEEK","Y.ETTERBEEK","Weekend","Continuous","00:30","04:00","Linked to coupure nr 51875 on line 26 tracks(s) A+B from Y.RUE DE BRUEL to Y.NOORD HALLE: Massificatie: Carsoul - Onderhoud - BVL L26 P085306 - P103303 RER L124 Moensberg\r\n1) Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1 TLO-WE voor plaatsen liggers","CTL","Medium"," ","Info Racc",51875]
["2024-04-20","2024-04-22","CE",1,"26/3","A+B","Y.WATERMAEL","WATERMAEL","Weekend","Continuous","00:30","04:00","Linked to coupure nr 51875 on line 26 tracks(s) A+B from Y.RUE DE BRUEL to Y.NOORD HALLE: Massificatie: Carsoul - Onderhoud - BVL L26 P085306 - P103303 RER L124 Moensberg\r\n1) Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1 TLO-WE voor plaatsen liggers","CTL","Medium"," ","Info Racc",51875]
["2024-04-20","2024-04-22","CE",1,"26/4","A+B","ETTERBEEK","Y.BOONDAEL","Weekend","Continuous","00:30","04:00","Linked to coupure nr 51875 on line 26 tracks(s) A+B from Y.RUE DE BRUEL to Y.NOORD HALLE: Massificatie: Carsoul - Onderhoud - BVL L26 P085306 - P103303 RER L124 Moensberg\r\n1) Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1 TLO-WE voor plaatsen liggers","CTL","Medium"," ","Info Racc",51875]
["2024-04-20","2024-04-22","CE",1,"26/5","A+B","Y.LINKEBEEK-HALLE","Y.LINKEBEEK","Weekend","Continuous","00:30","04:00","Linked to coupure nr 51875 on line 26 tracks(s) A+B from Y.RUE DE BRUEL to Y.NOORD HALLE: Massificatie: Carsoul - Onderhoud - BVL L26 P085306 - P103303 RER L124 Moensberg\r\n1) Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1 TLO-WE voor plaatsen liggers","CTL","Medium"," ","Info Racc",51875]
["2024-04-20","2024-04-22","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58013]
["2024-04-20","2024-04-22","NE",2,"12","A+B","ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58246 on line 27A tracks(s) A from ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht\r\n\r\nTLO L12+27A SPa +bundelkop C","CTL","Medium"," "," ",58246]
["2024-04-20","2024-04-22","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3+4+5+6+7+8+9","CTL","Medium","Vilvoorde sporen 3+4+5+6+7+8+9"," ",58198]
["2024-04-20","2024-04-22","NE",2,"27A","A","ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht\r\n\r\nTLO L12+27A SPa +bundelkop C","SAVU","Minor_AdHoc","bundel kop bundel C +L12 TLO"," ",58246]
["2024-04-20","2024-04-22","NE",2,"27A/1","A+B","ANTWERPEN-NOORD-INRIT C1","ANTWERPEN-NOORD-INRIT C1","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58246 on line 27A tracks(s) A from ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht\r\n\r\nTLO L12+27A SPa +bundelkop C","CTL","Medium"," "," ",58246]
["2024-04-20","2024-04-22","NE",2,"59","A+B","Y.ANTWERPEN-ZUID","Y.MELSELE","Weekend","Continuous","01:00","04:30","Oosterweel (sloop brug, herpenduleren BVL,..) + duiker Sleedoornstraat\r\nTe herplannen?","CTL","Medium",null," ",59740]
["2024-04-20","2024-04-22","NE",3,"59","A+B","Y.ANTWERPEN-ZUID","Y.MELSELE","Weekend","Continuous","00:30","04:35","onderhoud SIG,wissels en overwegen","CTL","Medium","alternatief E723-E744"," ",60213]
["2024-04-20","2024-04-22","NW",1,"50","A+B","DENDERLEEUW","AALST","Weekend","Continuous","01:00","04:00","Omvorming rooster Denderleeuw volgens richtplan.\r\n+\r\nonderhoud Aalst - Denderleeuw","CTL","Medium"," "," ",47675]
["2024-04-20","2024-04-22","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47675 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.\r\n+\r\nonderhoud Aalst - Denderleeuw","CTL","Medium"," "," ",47675]
["2024-04-20","2024-04-22","NW",1,"89","B","DENDERLEEUW","BURST","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47675 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.\r\n+\r\nonderhoud Aalst - Denderleeuw","SAVU_CTRL","Minor_AdHoc"," "," ",47675]
["2024-04-20","2024-04-22","NW",2,"59","A+B","Y.MELSELE","SINT-NIKLAAS","Weekend","Continuous","00:30","04:40","P143: afschaffen overwegen NW afschaffen overweg 17 L59 - Haasdonkbaan, Beveren fietstunnel - BTS gedurende 1 week na inschuiven fietstunnel lente 2024 \r\n+\r\nOnderhoud Wissels Sint Niklaas \r\nperron IV-V inbegrepen + AW13L-11AL-15L-05L-03AL+ geval 29670\r\n","CTL","Medium","- Bouw Fietstunnel OW 12 L59 Gentstraat (Melsele/Beveren) (Ing Erik De Grove)\r\nMET BTS:\r\n•\tHKV : 1,92’\r\n•\tHKM : 4,42’\r\n\r\nDeze BTS is niet ter beveiliging maar wegens heraanleg spoor (stabilisatie).\r\nDeze zal van toepassing zijn van ma 18/09/2023 (na pla"," ",58415]
["2024-04-20","2024-04-21","SE",3,"161","A/B","OTTIGNIES","GEMBLOUX","Weekend","Day","08:00","16:00","Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles + 1/2h sas Rhisnes","SAVU","Minor_AdHoc","SAVU alternatif entre 08h00 et 16h00"," ",48950]
["2024-04-21","2024-04-21","NE",3,"27B","A+B","Y.WEERDE","Y.MUIZEN","Weekend","Night","00:30","06:00","Lossing wissels Muizen Rooster T - L27B\r\ndoodspoor 430 gaat mee BD + BS","CTL","Minor_AdHoc"," "," ",61501]
["2024-04-21","2024-04-21","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59985]
["2024-04-21","2024-04-21","NW",3,"202B","S","ZEEBRUGGE-BUNDEL RAMSKAPELLE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Day","08:00","16:00","R-419011-01\r\n\r\nOnderhoud werkveld 3421-46\r\n\r\nAW 21AR-22R-23R-24R-25R-26R-27R-28R-83R-84R-85R-86R-87R-88R-89R-90R-91BR-92R buiten dienst\r\nbundelsporen 16-15-14-13-12-11-10-9 buiten dienst","Autre","Minor_AdHoc"," ","Info Racc.",60374]
["2024-04-21","2024-04-22","NW",2,"75","*","KORTRIJK","KORTRIJK","Weekend","Continuous","01:00","04:30","April 2024: spoor IV en V buiten dienst voor 24u","Autre","Minor_AdHoc"," "," ",58529]
["2024-04-22","2024-04-26","NE",3,"27","B","ANTWERPEN-CENTRAAL","Y.NOORD GROENENHOEK","Week","Night","23:50","04:50","L 27 spoor B onderhoud SIG \r\nY noord Berchem inbegrepen\r\n+\r\nL59/1 spoor A onderhoud SIG","SAVU","Minor_AdHoc",null," ",59721]
["2024-04-22","2024-04-26","NE",3,"27/1","A+B","Y.NOORD BERCHEM","Y.ANTWERPEN-OOST","Week","Night","23:50","04:50","Linked to coupure nr 59721 on line 27 tracks(s) B from ANTWERPEN-CENTRAAL to Y.NOORD GROENENHOEK: L 27 spoor B onderhoud SIG \r\nY noord Berchem inbegrepen\r\n+\r\nL59/1 spoor A onderhoud SIG","CTL","Minor_AdHoc"," "," ",59721]
["2024-04-22","2024-04-26","NE",3,"29","A+B","Y.KRUISBERG","TURNHOUT","Week","Night","23:00","04:40","omvormen 50 HZ SK naar TFSK\r\naanpassen treindetectiesysteem (moet voor 2025)\r\nvernieuwing signalisatie overwegen\r\nomvorming moet gebeuren voor uitrol ETCS L29","CTL","Minor_AdHoc","alternatief E3421"," ",60015]
["2024-04-22","2024-04-26","NE",3,"59","A+B","Y.ANTWERPEN-ZUID","Y.MELSELE","Week","Night","23:50","04:35","onderhoud SIG,wissels en overwegen","CTL","Minor_AdHoc","alternatief E723-E744"," ",60212]
["2024-04-22","2024-04-26","NE",3,"59/1","A","ANTWERPEN-CENTRAAL","Y.ARENDSTRAAT","Week","Night","23:50","04:50","Linked to coupure nr 59721 on line 27 tracks(s) B from ANTWERPEN-CENTRAAL to Y.NOORD GROENENHOEK: L 27 spoor B onderhoud SIG \r\nY noord Berchem inbegrepen\r\n+\r\nL59/1 spoor A onderhoud SIG","SAVU","Minor_AdHoc"," "," ",59721]
["2024-04-22","2024-04-26","SW",1,"94","A/B","ENGHIEN","SAINTES","Week","Continuous","06:00","22:00","Enghien : Renouvellement de rails voies III & IV\r\nRq 333 : pas de MHT ou isolateur? \r\n+ Explication pourquoi pas en WE","CTL","Medium","1 voie HS en continu et l'autre hors heure de pointe (8h30 - 16h)\r\nART à 80 km/h -> 0,2 min de perte de temps"," ",48643]
["2024-04-22","2024-04-27","CE",1,"26","A+B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","Week","Night","23:30","04:00","Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1\r\nTLO-nachten voor plaatsen liggers en werken aan de brug.","CTL","Minor_AdHoc","TLO tussen Trapezium Linkebeek en Y Watermaal"," ",51882]
["2024-04-22","2024-04-27","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59860]
["2024-04-22","2024-04-27","SW",2,"112","B","LA LOUVIERE-CENTRE","LA LOUVIERE-CENTRE","Week","Continuous","09:00","05:20","Construction passerelle gare de LLV Centre. Réalilsation micro-pieux quai central","SAVU_CTRL","Minor_AdHoc","L112 VB en continu = Voie 1 (AS ne)\r\nSAVU de jour (9h-15h) + CTL de nuit : 23:20 - 5:20\r\nMaintenir circulation aux heures de pointes pour éviter un dérouillage","HKM à adapter",61383]
["2024-04-22","2024-04-29","NW",2,"59","A+B","Y.MELSELE","SINT-NIKLAAS","AllWeek","Continuous","04:40","04:40","BTS\r\nP143: afschaffen overwegen NW afschaffen overweg 17 L59 - Haasdonkbaan, Beveren fietstunnel","ART","Minor_AdHoc"," "," ",60941]
["2024-04-23","2024-04-26","NW",1,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53592]
["2024-04-23","2024-04-26","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 53592 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53592]
["2024-04-23","2024-04-26","NW",1,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 53592 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","SAVU","Minor_AdHoc"," "," ",53592]
["2024-04-25","2024-04-25","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55944]
["2024-04-26","2024-04-29","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59566]
["2024-04-26","2024-04-29","NE",1,"12","A+B","Y.SINT-MARIABURG","LUCHTBAL-ROOSTER S","Weekend","Continuous","23:50","04:00","304(statiestraat)+308 (herelectrificatie)\r\n\r\nAan deze werken is een R7 (van 06h00 tot 17h30) gekoppeld op L27A voor het spoorgedeelte Y.Laarsebeek - Y.Schijn!! (58227)","CTL","Medium","alternatief ER4521-ER2021-Er2020-E2573"," ",58064]
["2024-04-26","2024-04-29","SE",1,"165","A","SAINT-VINCENT-BELLEFONTAINE","VIRTON","Weekend","Continuous","23:00","05:00","Renouvellement AS entrée de Virton : révision (2)","SAVU_CTRL","Minor_AdHoc","MHS jusqu'en gare de Virton (voie 2 à quai incluse).\r\nCTL dans blanc fret (samedi 23h / dimanche 15h + nuit dimanche/lundi).\r\nPas d'ART car vitesse permanente = 50 km/h.\r\n/!\\ Selon plan d'aménagement, interversion des phases peut-être requise (VA avant "," ",47774]
["2024-04-26","2024-04-29","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 6-2024\r\nTravaux mur de soutènement - BOA\r\nWeek-end 1/5\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies I, II en gare de Luttre inaccessible en continu"," ",49586]
["2024-04-26","2024-05-11","CE",1,"96","A","BRUXELLES-MIDI","Y.NOORD HALLE","AllWeek","Continuous","23:40","04:30","Vernieuwen sp A L96 met P+C-trein. Fase 2 WE2-W2-WE3-W3","SAVU","High","DOES L96 tussen FBMZ en Halle.\r\nBijkomend tijdens de nachten sp B L96 + AL96N"," ",49981]
["2024-04-26","2024-05-11","CE",1,"96","B","Y.NOORD HALLE","Y.RUISBROEK","AllWeek","Continuous","23:40","04:30","Linked to coupure nr 49981 on line 96 tracks(s) A from BRUXELLES-MIDI to Y.NOORD HALLE: Vernieuwen sp A L96 met P+C-trein. Fase 2 WE2-W2-WE3-W3","SAVU","High"," "," ",49981]
["2024-04-26","2024-05-13","SE",1,"162","A+B","CINEY","MARLOIE","AllWeek","Continuous","22:15","05:00","Travaux en gare de d'Haversin :\r\npour renouvellement caténaire R3 mixte\r\n+  renouvellement du PS d’Haversin bK 102.161\r\n+ Pose TDJ 02AC/01BC\r\n+ Pose TDJ 03AC/02BC","CTL","High","Marloie :\r\nVoie I accessible - AS 01AC griffé en voie directe\r\nIsolateurs provisoires pour quais II + III + IV accessibles en CDS","via L162-43",47352]
["2024-04-26","2024-04-29","CE",1,"161","A/B","WATERMAEL","BAKENBOS","Weekend","Continuous","23:30","04:50","WE SAVU RER Watermael-Bakenbos","SAVU_CTRL","Minor_AdHoc","ART maximum 2'"," ",49254]
["2024-04-26","2024-04-29","SE",3,"161","A","RHISNES","GEMBLOUX","Weekend","Continuous","23:00","05:00","réélectrification","SAVU","Minor_AdHoc","une voie en continu"," ",49710]
["2024-04-26","2024-04-29","SE",1,"154","A+B","YVOIR","DINANT","Weekend","Continuous","23:50","04:20","Renouvellement de Ballast (C75)\r\nWE 6/6","CTL","Medium",null,"HKM à adapter - itinéraire via L130A ou L75",49936]
["2024-04-27","2024-04-27","SE",3,"139","A/B","WAVRE","OTTIGNIES","Weekend","Day","08:00","16:00","Visites des postes+ maintenances infrastructure et contrôles","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48868]
["2024-04-27","2024-04-28","NE",2,"52","A","PUURS","Y.ANTWERPEN-ZUID","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59094]
["2024-04-27","2024-04-28","NE",2,"59","A","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59093]
["2024-04-27","2024-04-28","SE",1,"165","A+B","BERTRIX","VIRTON","Weekend","Continuous","23:00","15:00","Renouvellement AS entrée de Virton : révision (2)","CTL","Medium","MHS jusqu'en gare de Virton (voie 2 à quai incluse).\r\nCTL dans blanc fret (samedi 23h / dimanche 15h + nuit dimanche/lundi).\r\nPas d'ART car vitesse permanente = 50 km/h."," ",59336]
["2024-04-27","2024-04-28","SE",3,"165","A+B","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE","Weekend","Continuous","23:00","15:00","Interventions Programmées","CTL","Medium","voie A du sa. 23h00 au di. 15h00\r\nvoie B du sa. 23h00 au di. 15h00"," ",46686]
["2024-04-27","2024-04-28","SW",3,"94","A+B","ENGHIEN","ATH","Weekend","Continuous","06:00","17:00","Maintenance Z16.54\r\n+ renouvellement rail Enghien","CTL","Medium",null," ",58071]
["2024-04-27","2024-04-28","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Weekend","Continuous","06:00","17:00","Maintenance Z6.53 en P4","CTL","Medium"," ","HKM à adapter",55957]
["2024-04-27","2024-04-29","CE",1,"26","A+B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","Weekend","Continuous","00:30","04:00","Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1\r\nTLO-WE voor plaatsen liggers en werken aan de brug.","CTL","Medium","TLO tussen Trapezium Linkebeek en Y Watermaal"," ",51876]
["2024-04-27","2024-04-29","CE",2,"26","A+B","Y.RUE DE BRUEL","Y.CINQUANTENAIRE","Weekend","Continuous","00:30","04:00","P085306 BVL L26 Y Bruul - Y50.\r\nY Bruulstraat is niet inbegrepen.","CTL","Medium","TLO tussen Y Bruulstr en Y50","Info Racc",59017]
["2024-04-27","2024-04-29","NE",2,"10","A","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58681 on line 10 tracks(s) B from Y.KOESTRAAT to Y.HAZOP: aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc"," "," ",58681]
["2024-04-27","2024-04-29","NE",2,"10","B","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc","DOES op spoor A L10 / bundel Zuid afgesloten"," ",58681]
["2024-04-27","2024-04-29","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58014]
["2024-04-27","2024-04-29","NE",2,"12","A+B","ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58247 on line 27A tracks(s) A from ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht\r\n\r\nhangt samen met colt 58047","CTL","Medium"," "," ",58247]
["2024-04-27","2024-04-29","NE",2,"12","A+B","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Engelse Leien vervolg vernieuwen wissels \r\nTLO L12+27A SPa +bundelkop C","CTL","Medium"," "," ",58047]
["2024-04-27","2024-04-29","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3+4+5+6+7+8+9","CTL","Medium","Vilvoorde sporen 3+4+5+6+7+8+9"," ",58199]
["2024-04-27","2024-04-29","NE",2,"27A","A","ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht\r\n\r\nhangt samen met colt 58047","SAVU","Minor_AdHoc","bundel kop bundel C +L12 TLO"," ",58247]
["2024-04-27","2024-04-29","NE",2,"27A","A","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58047 on line 12 tracks(s) A+B from Y.ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse Leien vervolg vernieuwen wissels \r\nTLO L12+27A SPa +bundelkop C","SAVU","Minor_AdHoc"," "," ",58047]
["2024-04-27","2024-04-29","NE",2,"27A/1","A+B","ANTWERPEN-NOORD-INRIT C1","ANTWERPEN-NOORD-INRIT C1","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58247 on line 27A tracks(s) A from ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht\r\n\r\nhangt samen met colt 58047","CTL","Medium"," "," ",58247]
["2024-04-27","2024-04-29","NW",1,"50","A+B","DENDERLEEUW","AALST","Weekend","Continuous","01:00","04:00","Omvorming rooster Denderleeuw volgens richtplan.","CTL","Medium"," "," ",47676]
["2024-04-27","2024-04-29","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47676 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","CTL","Medium"," "," ",47676]
["2024-04-27","2024-04-29","NW",1,"89","B","DENDERLEEUW","BURST","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47676 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","SAVU_CTRL","Minor_AdHoc"," "," ",47676]
["2024-04-27","2024-04-29","NW",3,"50A/6","A+B","GENT-SINT-PIETERS","GENT-ROOSTER SNEPBRUG","Weekend","Continuous","00:20","04:20","Linked to coupure nr 59050 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Gent Sint Pieters - Onderhoud \r\nY West vrij - FGSP SP I tem IV BD + verlengde op L50A6 - Bundel blijft bereikbaar","CTL","Medium"," ",null,59050]
["2024-04-27","2024-04-29","NW",3,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:20","04:20","Gent Sint Pieters - Onderhoud \r\nY West vrij - FGSP SP I tem IV BD + verlengde op L50A6 - Bundel blijft bereikbaar","CTL","Medium",null,null,59050]
["2024-04-27","2024-04-29","SE",1,"130","A+B","MOUSTIER","Y.FLAWINNE","Weekend","Night","23:40","05:00","Aménagement gare de Floreffe\r\nWE 5/6 - Nuits\r\nDossier de concertation validé le 26 octobre 2021","CTL","Minor_AdHoc","Nuit CTL R6^R7 23:40-6:20\r\nNuit CTL R7^R1 23:40-5:00"," ",52734]
["2024-04-27","2024-05-13","SW",1,"118","A+B","MONS","Y.LA PAIX","AllWeek","Continuous","00:30","04:30","Massification Tracks+OA+SI :\r\nProjet Holcim : nouveau branchement&liaison pour le raccordé à Obourg\r\nRenouvellement de la chape des PI km 34.175, 30.820, 30.800, 29.050 et 28.180 situé entre Y.St-Vaast et Obourg ;\r\nMise en service SIMIS-W entre Mons et ","CTL","High","CTL 14 jours\r\nART stabilisation"," ",45837]
["2024-04-27","2024-04-28","SE",3,"161","A/B","NAMUR","RHISNES-SAS","Weekend","Day","08:00","16:00","Visite périodique + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","Savu alternatif VA/VB , de 8h à 16 h"," ",49208]
["2024-04-28","2024-04-28","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","06:00","17:40","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58227]
["2024-04-28","2024-04-28","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59986]
["2024-04-28","2024-04-28","SE",3,"139","A/B","SINT-JORIS-WEERT","WAVRE","Weekend","Day","08:00","16:00","Visites des postes - maintenances diverses et révisions","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48878]
["2024-04-29","2024-05-03","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","Week","Night","23:50","04:30","Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers","CTL","Minor_AdHoc"," "," ",58963]
["2024-04-29","2024-05-03","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Week","Night","23:50","04:30","Linked to coupure nr 58963 on line 16 tracks(s) A+B from Y.OOST DRIEHOEK AARSCHOT to HEIST-OP-DEN-BERG: Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers","CTL","Minor_AdHoc"," "," ",58963]
["2024-04-29","2024-05-03","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Week","Night","23:40","04:00","Linked to coupure nr 59943 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59943]
["2024-04-29","2024-05-03","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Week","Night","23:40","04:00","Onderhoud","CTL","Minor_AdHoc"," "," ",59943]
["2024-04-29","2024-05-03","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Week","Night","23:40","04:00","Linked to coupure nr 59943 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59943]
["2024-04-29","2024-05-04","CE",1,"26","A+B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","Week","Night","23:30","04:00","Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 1\r\nTLO-nachten voor plaatsen liggers en werken aan de brug.","CTL","Minor_AdHoc","TLO tussen Trapezium Linkebeek en Y Watermaal"," ",51883]
["2024-04-29","2024-05-04","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59861]
["2024-04-29","2024-07-15","NE",2,"12","B","ANTWERPEN-CENTRAAL","ANTWERPEN-CENTRAAL","AllWeek","Continuous","00:00","04:00","Linked to coupure nr 58361 on line 59/1 tracks(s) A from ANTWERPEN-CENTRAAL to ANTWERPEN-CENTRAAL: Antwerpen-Centraal\r\nvernieuwen bevestigingen in beton en spoorstaven sporen 1 tot 6\r\ngefaseerd continue BD van twee perronsporen","CTL","Major"," "," ",58361]
["2024-04-29","2024-07-15","NE",2,"59/1","A","ANTWERPEN-CENTRAAL","ANTWERPEN-CENTRAAL","AllWeek","Continuous","00:00","04:00","Antwerpen-Centraal\r\nvernieuwen bevestigingen in beton en spoorstaven sporen 1 tot 6\r\ngefaseerd continue BD van twee perronsporen","CTL","Major","spoor 3 (L59/1 sp A) en spoor 4 (L12 sp B) continu BD"," ",58361]
["2024-04-30","2024-05-03","NW",1,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53593]
["2024-04-30","2024-05-03","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 53593 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","CTL","Minor_AdHoc"," "," ",53593]
["2024-04-30","2024-05-03","NW",1,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 53593 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan.","SAVU","Minor_AdHoc"," "," ",53593]
["2024-05-03","2024-05-06","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59567]
["2024-05-03","2024-05-06","NE",3,"139","A+B","LEUVEN","SINT-JORIS-WEERT","Weekend","Continuous","23:00","05:20","vernieuwing rails Harmelen OW2 L139 + rails steken 139/1 +DL","CTL","Medium","alternatief E5722"," ",60276]
["2024-05-03","2024-05-06","NE",3,"139/1","A+B","LEUVEN","Y.PARKBRUG","Weekend","Continuous","23:00","05:20","vernieuwing rails Harmelen OW2 L139+rails steken L139/1","CTL","Medium","alternatief E5722"," ",60277]
["2024-05-03","2024-05-06","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Weekend","Continuous","23:40","04:00","Linked to coupure nr 59944 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Medium"," "," ",59944]
["2024-05-03","2024-05-06","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Weekend","Continuous","23:40","04:00","Onderhoud","CTL","Medium"," "," ",59944]
["2024-05-03","2024-05-06","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Weekend","Continuous","23:40","04:00","Linked to coupure nr 59944 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Medium"," "," ",59944]
["2024-05-03","2024-05-06","SE",2,"139","A+B","OTTIGNIES","SINT-JORIS-WEERT","Weekend","Continuous","23:15","05:30","Mise en service modernisation PN34\r\nRq 333 : A replanifier - voir commentaire\r\nMinimum 3 sem avec L130\r\nDate à proposer pour L139 par I-CBE","CTL","Medium",null," ",57899]
["2024-05-03","2024-05-06","SE",2,"166","A/B","Y.NEFFE","ANSEREMME","Weekend","Continuous","23:00","05:00","Linked to coupure nr 57696 on line 154 tracks(s) A/B from DINANT to Y.NEFFE: Entretien AS , traitement zone boueuse","SAVU_CTRL","Minor_AdHoc"," "," ",57696]
["2024-05-03","2024-05-06","SE",2,"24/1","A+B","VISE","Y.LONGCHAMPS","Weekend","Continuous","23:00","05:00","Pose d'une nouvelle liaison - WE CTL n°1\r\nPose AS voie A","CTL","Medium","CTL L24/1 voies A et B\r\nVoie 554 HS\r\nVoie HS entre AS72K et 51AK"," ",57868]
["2024-05-03","2024-05-06","SE",3,"162","A+B","ARLON","STERPENICH-FRONTIERE","Weekend","Continuous","23:00","04:00","Travaux aux appareils d'Autelbas (traverses, rails)","CTL","Medium","ART stab 2min du 6/05 au 27/05","HKM à adapter",57815]
["2024-05-03","2024-05-06","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 6-2024\r\nTravaux mur de soutènement - BOA\r\nWeek-end 2/5\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies I, II en gare de Luttre inaccessible en continu"," ",49818]
["2024-05-03","2024-05-06","SW",1,"124A/1","A+B","LA SAMBRE","Y.LA SAMBRE","Weekend","Continuous","23:00","04:10","Linked to coupure nr 48247 on line 130A tracks(s) A+B from LA SAMBRE to ERQUELINNES-FRONTIERE: Maintenance Z2. 51  P4+\r\n+ Remplacement Loge PLP K6\r\n+ Travaux de remise en état du PS km 104,903\r\n + Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires ","CTL","Medium"," ","HKM à adapter",48247]
["2024-05-03","2024-05-06","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Weekend","Continuous","23:00","04:10","Maintenance Z2. 51  P4+\r\n+ Remplacement Loge PLP K6\r\n+ Travaux de remise en état du PS km 104,903\r\n + Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires caténaire (int. 99/4)","CTL","Medium","CTL L130A + SAVU Y. Nord - La Sambre VB HS : Entre 02K ne et Y.Nord - cas 27628 et 27624 et 27662 HT\r\n+ CTL L124A/1","HKM à adapter",48247]
["2024-05-03","2024-05-06","SW",1,"130A","B","Y.NORD","LA SAMBRE","Weekend","Continuous","23:00","04:10","Linked to coupure nr 48247 on line 130A tracks(s) A+B from LA SAMBRE to ERQUELINNES-FRONTIERE: Maintenance Z2. 51  P4+\r\n+ Remplacement Loge PLP K6\r\n+ Travaux de remise en état du PS km 104,903\r\n + Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires ","SAVU","Minor_AdHoc"," ","HKM à adapter",48247]
["2024-05-03","2024-05-06","SE",1,"161","A","OTTIGNIES","Y.LOUVAIN-LA-NEUVE","Weekend","Continuous","23:30","06:00","WE SAVU RER Ottignies-Y.LLN","SAVU_CTRL","Minor_AdHoc","ART maximum 2'"," ",49258]
["2024-05-03","2024-05-06","SE",2,"154","A/B","DINANT","Y.NEFFE","Weekend","Continuous","23:00","05:00","Entretien AS , traitement zone boueuse","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 06/05 au 09/05 (fin probable)"," ",57696]
["2024-05-04","2024-05-06","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","Weekend","Continuous","01:00","04:00","Voorbereidingsweekend  1/2 Vernieuwing Y.Noord-Driehoek-Aarschot + vernieuwen duikers\r\nPlaatsen nieuwe BVL-palen en voorbereidingswerken sporen\r\n\r\n\r\nOverlegdossier: 2024 - L16 Y.Oost Driehoek Aarschot-Heist od Berg - 211109","CTL","Medium"," "," ",52880]
["2024-05-04","2024-05-06","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Weekend","Continuous","01:00","04:00","Linked to coupure nr 52880 on line 16 tracks(s) A+B from Y.OOST DRIEHOEK AARSCHOT to HEIST-OP-DEN-BERG: Voorbereidingsweekend  1/2 Vernieuwing Y.Noord-Driehoek-Aarschot + vernieuwen duikers\r\nPlaatsen nieuwe BVL-palen en voorbereidingswerken sporen\r\n\r\n\r\n","CTL","Medium"," "," ",52880]
["2024-05-04","2024-05-04","SE",3,"130","A/B","FLAWINNE","MOUSTIER","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49171]
["2024-05-04","2024-05-05","NE",2,"52","A","PUURS","Y.ANTWERPEN-ZUID","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59096]
["2024-05-04","2024-05-05","NE",2,"59","A","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59095]
["2024-05-04","2024-05-05","NE",3,"10L/1","*","ANTWERPEN-W.H.-B.ZUID","ANTWERPEN-W.H.-B.ZUID","Weekend","Continuous","12:00","22:00","massificatiewerken","CTL","Medium","bundel Zuid WLH ontoegankelijk"," ",60821]
["2024-05-04","2024-05-05","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60421]
["2024-05-04","2024-05-05","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60421 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60421]
["2024-05-04","2024-05-05","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60421 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60421]
["2024-05-04","2024-05-06","NE",1,"29","A+B","Y.KRUISBERG","TURNHOUT-BUNDEL","Weekend","Continuous","00:00","04:00","Linked to coupure nr 59195 on line 15 tracks(s) A+B from Y.ALBERTKANAAL to OLEN: ETCS \r\nmeewerken niet mogelijk","CTL","Medium"," "," ",59195]
["2024-05-04","2024-05-06","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58015]
["2024-05-04","2024-05-06","NE",2,"12","A+B","ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58248 on line 27A tracks(s) A from ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht","CTL","Medium"," "," ",58248]
["2024-05-04","2024-05-06","NE",2,"12","A+B","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Engelse Leien vervolg vernieuwen wissels \r\nTLO L12+27A SPa +bundelkop C","CTL","Medium"," "," ",58048]
["2024-05-04","2024-05-06","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3+4+5+6+7+8+9","CTL","Medium","Vilvoorde sporen 3+4+5+6+7+8+9"," ",58200]
["2024-05-04","2024-05-06","NE",2,"27A","A","ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht","SAVU","Minor_AdHoc","bundel kop bundel C +L12 TLO"," ",58248]
["2024-05-04","2024-05-06","NE",2,"27A","A","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58048 on line 12 tracks(s) A+B from Y.ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse Leien vervolg vernieuwen wissels \r\nTLO L12+27A SPa +bundelkop C","SAVU","Minor_AdHoc"," "," ",58048]
["2024-05-04","2024-05-06","NE",2,"27A/1","A+B","ANTWERPEN-NOORD-INRIT C1","ANTWERPEN-NOORD-INRIT C1","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58248 on line 27A tracks(s) A from ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht","CTL","Medium"," "," ",58248]
["2024-05-04","2024-05-06","NW",1,"50","A+B","DENDERLEEUW","AALST","Weekend","Continuous","01:00","04:00","Omvorming rooster Denderleeuw volgens richtplan\r\n+\r\nONB over de Dender: afwerkingen KP 28.100-28.300 (Van Damme Bruno)","CTL","Medium"," "," ",47677]
["2024-05-04","2024-05-06","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47677 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan\r\n+\r\nONB over de Dender: afwerkingen KP 28.100-28.300 (Van Damme Bruno)","CTL","Medium"," "," ",47677]
["2024-05-04","2024-05-06","NW",1,"89","B","DENDERLEEUW","BURST","Weekend","Continuous","01:00","04:00","Linked to coupure nr 47677 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw volgens richtplan\r\n+\r\nONB over de Dender: afwerkingen KP 28.100-28.300 (Van Damme Bruno)","SAVU_CTRL","Minor_AdHoc"," "," ",47677]
["2024-05-04","2024-05-06","SE",1,"130","A+B","MOUSTIER","Y.FLAWINNE","Weekend","Night","23:40","05:00","Aménagement gare de Floreffe\r\nWE 6/6 Nuits\r\nDossier de concertation validé le 26 octobre 2021","CTL","Minor_AdHoc","Nuit CTL R6^R7 23:40-6:20\r\nNuit CTL R7^R1 23:40-5:00"," ",52735]
["2024-05-05","2024-05-05","NE",3,"27B","A+B","Y.WEERDE","Y.MUIZEN","Weekend","Night","00:30","06:00","Lossing wissels Muizen Rooster T - L27B\r\ndoodspoor 430 gaat mee BD + BS","CTL","Minor_AdHoc"," "," ",61502]
["2024-05-05","2024-05-05","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59987]
["2024-05-05","2024-05-05","NW",3,"202B/1","S","Y.PELIKAAN","ZEEBRUGGE-BUNDEL PELIKAAN","Weekend","Day","06:00","22:00","R-419053-01\r\n\r\nOmvormen 51AR-51BR-52AR-54R-55R-56R-57R van He-H dmv voorgemonteerde panelen werkveld 3421-31\r\n\r\nBundel Pelikaan niet bereikbaar","CTL","Minor_AdHoc"," ","Info Racc",60382]
["2024-05-05","2024-05-05","NW",3,"202B/2","S","ZEEBRUGGE-BUNDEL PELIKAAN","Y.EIVOORDE","Weekend","Day","06:00","22:00","Linked to coupure nr 60382 on line 202B/1 tracks(s) S from Y.PELIKAAN to ZEEBRUGGE-BUNDEL PELIKAAN: R-419053-01\r\n\r\nOmvormen 51AR-51BR-52AR-54R-55R-56R-57R van He-H dmv voorgemonteerde panelen werkveld 3421-31\r\n\r\nBundel Pelikaan niet bereikbaar","CTL","Minor_AdHoc"," ","Info Racc",60382]
["2024-05-05","2024-05-05","NW",3,"51A","*","ZEEBRUGGE-ROOSTER F","ZEEBRUGGE-ROOSTER G","Weekend","Day","14:00","(vide)","Reservering Onderhoud bundel Zwankendamme zone 108\r\n\r\nEnkel bundel Zwankendamme niet bereikbaar.\r\n\r\nAanduiding L51A enkel voor de visualisatie in Colt.geen beperkingen op L51A\r\n\r\nR-419352-01","Autre","Minor_AdHoc","bundel Zwakendamme niet bereikbaar"," ",60457]
["2024-05-05","2024-05-05","SE",3,"130","A/B","MOUSTIER","AUVELAIS","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49181]
["2024-05-06","2024-05-10","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","Week","Night","23:50","04:30","Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers\r\n\r\n+ 2 WE voorbereiding en 2 WE afwerking","CTL","Minor_AdHoc"," "," ",58970]
["2024-05-06","2024-05-10","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Week","Night","23:50","04:30","Linked to coupure nr 58970 on line 16 tracks(s) A+B from Y.OOST DRIEHOEK AARSCHOT to HEIST-OP-DEN-BERG: Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers\r\n\r\n+ 2 WE voorbereiding en 2 WE afwerking","CTL","Minor_AdHoc"," "," ",58970]
["2024-05-06","2024-05-08","SW",3,"130A","A+B","Y.NORD","ERQUELINNES-FRONTIERE","Week","Night","22:30","04:10","Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires caténaire (traverses)","CTL","Minor_AdHoc","1 semaines de CTL de nuit"," ",55938]
["2024-05-06","2024-05-10","CE",1,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Week","Night","23:50","04:30","P008 518: Op dubbel spoor brengen L161/1 fase 1: voorbereidende werken BVL + verplaatsen kabels","CTL","Minor_AdHoc","TLO L50 + L26B + L161/1"," ",59584]
["2024-05-06","2024-05-10","CE",1,"26B","B","Y.PONT-DE-LA-SENNE","SCHAERBEEK","Week","Night","23:50","04:30","Linked to coupure nr 59584 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Op dubbel spoor brengen L161/1 fase 1: voorbereidende werken BVL + verplaatsen kabels","CTL","Minor_AdHoc"," "," ",59584]
["2024-05-06","2024-05-10","CE",1,"50","A+B","BRUXELLES-NORD","Y.LAEKEN","Week","Night","23:50","04:30","Linked to coupure nr 59584 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Op dubbel spoor brengen L161/1 fase 1: voorbereidende werken BVL + verplaatsen kabels","CTL","Minor_AdHoc"," "," ",59584]
["2024-05-06","2024-05-10","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Week","Night","23:40","04:00","Linked to coupure nr 59945 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59945]
["2024-05-06","2024-05-10","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Week","Night","23:40","04:00","Onderhoud","CTL","Minor_AdHoc"," "," ",59945]
["2024-05-06","2024-05-10","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Week","Night","23:40","04:00","Linked to coupure nr 59945 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59945]
["2024-05-06","2024-05-10","NE",3,"35","A+B","LEUVEN","AARSCHOT","Week","Night","23:30","04:30","afschaffen OW 119 langestraat +verhogen perrons Wezemaal","CTL","Minor_AdHoc","alternatief E2622-E2743-E2221"," ",60036]
["2024-05-06","2024-05-10","SW",3,"94","A+B","ATH","TOURNAI","Week","Night","23:20","04:40","Renouvellement PN 70 et 80\r\n+ Renforcement de 7 PI entre les km 54.992 et 63.375 sur la L94\r\nPhase 1.1 : PI 1+2","CTL","Minor_AdHoc",null,"Info Racc : desserte d'Havinnes impossible",49150]
["2024-05-06","2024-05-11","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59862]
["2024-05-06","2024-05-27","SE",1,"165","A","SAINT-VINCENT-BELLEFONTAINE","VIRTON","AllWeek","Continuous","06:00","04:30","Chantier peignage paroi\r\nProjet pâturage chèvre\r\nRq 333 : demande EF's suite semestrielle : Pas de visites supplémentaire pendant ces TW sur L165-\r\nRep : L'impact sera minimisé au maximum\r\n+ Est-ce possible de déplacer e même temps id 46798?\r\n-> 51868 d","SAVU","High","entre les signaux TX-R.23 (BK 102945) au C-S 23 (BK 116920)\r\ncas 26465 et 26467 inclus."," ",51868]
["2024-05-06","2024-05-31","SE",2,"162","*","MARLOIE","MARLOIE","AllWeek","Continuous","06:00","16:00","Pose de la voie IX sur sa nouvelle position (renouvellement rails + traverses + ballast)\r\nLe raccord des aiguillages MAR 2 et MAR 3 (poses en 2023 et griffes sur la voie VII) \r\nPose des aiguillages MAR 4, Mar 5 et MAR 7+ l’aiguille déraillement MAR 8\r\nL","SAVU_CTRL","High","MHS des voies VII-XI  \r\nCas catenaire 26258 (si à cette date le cas est d’actualité pour les voies VII-XI les voies VII,VIII, IX et XI deviendrons des voies I-AM) \r\n\r\n-\tLa voie A et la voie B en service avec réduction vitesse à 60km/h, HKV=1.70min, HKM="," ",51021]
["2024-05-07","2024-05-07","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60108]
["2024-05-08","2024-05-08","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60092]
["2024-05-08","2024-05-13","SE",2,"44","A+B","PEPINSTER-CITE","SPA-GERONSTERE","AllWeek","Continuous","23:00","05:00","Renouvellement des équipements de signalisation des PNs 3, 4, 5 et 6 (Préparation et ou MES)\r\n+ Entretien manuel et mécanisés des AW \r\nEntretien manuel et mécanisés de la voie courante\r\nEntretien manuel et mécanisés des PN","CTL","Medium",null," ",56333]
["2024-05-09","2024-05-12","SE",1,"165","A+B","BERTRIX","VIRTON","AllWeek","Continuous","00:10","18:00","Renouvellement (démolition / reconstruction) et mise au gabarit des passages inférieurs suivants : \r\n- 97.285\r\n- 102.011","CTL","Medium","ART 3min20s, 15 jours après la remise en service du 12/05 au 26/05 (voir COLT 47846 modifié de 2023 à 2024)"," ",61620]
["2024-05-09","2024-05-13","NE",1,"29","A+B","Y.KRUISBERG","TURNHOUT-BUNDEL","Weekend","Continuous","04:00","04:00","Linked to coupure nr 49865 on line 15 tracks(s) A+B from Y.NAZARETH to GEEL: Indienstname ETCS\r\nBrugdag. Meewerken niet mogelijk\r\n+\r\nETCS (11-13/05)\r\nmeewerken niet mogelijk (59197)","CTL","Medium"," "," ",49865]
["2024-05-09","2024-05-13","NW",1,"75","A+B","GENT-SINT-PIETERS","DEINZE","Weekend","Continuous","00:30","04:00","IDS SIW L75-FGSP - De Pinte\r\nGEEN ANDERE WERKEN MOGELIJK","CTL","Medium"," "," ",53304]
["2024-05-09","2024-05-13","NW",1,"86","A+B","DE PINTE","GAVERE-ASPER","Weekend","Continuous","00:30","04:00","Linked to coupure nr 53304 on line 75 tracks(s) A+B from GENT-SINT-PIETERS to DEINZE: IDS SIW L75-FGSP - De Pinte\r\nGEEN ANDERE WERKEN MOGELIJK","CTL","Medium"," "," ",53304]
["2024-05-09","2024-05-12","SE",1,"154","A+B","NAMUR","LUSTIN","AllWeek","Continuous","00:10","18:00","Suppression PN 99 et 101 Jambes : pose de deux couloir sous-voies + extension quais gare de Jambes\r\nRemise en état pistes PI BK 63.100","CTL","Medium","ART 3min du 12/05 au 31/05"," ",47496]
["2024-05-10","2024-05-13","NE",2,"21C","S","Y.BOSDEL","Y.NIEUWDAK","Weekend","Continuous","23:40","04:00","Vervanging ONB Dominikanenlaan km 29.833\r\n\r\n\r\n\r\n\r\n\r\n\r\nR-431783-01","CTL","Medium","geen toegang tot L230"," ",61657]
["2024-05-10","2024-05-13","NE",2,"230","A+B","Y.BOSDEL","ZUTENDAAL","Weekend","Continuous","23:40","04:00","Linked to coupure nr 61657 on line 21C tracks(s) S from Y.BOSDEL to Y.NIEUWDAK: Vervanging ONB Dominikanenlaan km 29.833\r\n\r\n\r\n\r\n\r\n\r\n\r\nR-431783-01","CTL","Medium"," "," ",61657]
["2024-05-10","2024-05-13","NE",3,"139","A+B","LEUVEN","SINT-JORIS-WEERT","Weekend","Continuous","23:00","05:20","vernieuwing rails Harmelen OW2 L139 + rails steken 139/1 +DL\r\n\r\nof werken doorgaan dit weekend hangt af van massificatie onderhoud arr 44 (colt 50702)","CTL","Medium","alternatief E5722"," ",60278]
["2024-05-10","2024-05-13","NE",3,"139/1","A+B","LEUVEN","Y.PARKBRUG","Weekend","Continuous","23:00","05:20","vernieuwing rails Harmelen OW2 L139+rails steken L139/1\r\n\r\nof werken doorgaan dit weekend hangt af van massificatie onderhoud arr 44 (colt 50702","CTL","Medium","alternatief E5722"," ",60279]
["2024-05-10","2024-05-13","NE",3,"35","A+B","LEUVEN","AARSCHOT","Weekend","Continuous","23:30","04:30","afschaffen OW 119 langestraat +verhogen perrons Wezemaal","CTL","Medium","alternatief E2622-E2743-E2221"," ",60035]
["2024-05-10","2024-05-13","SE",2,"24/1","A+B","VISE","Y.LONGCHAMPS","Weekend","Continuous","23:00","06:00","Pose d'une nouvelle liaison - WE CTL n°2\r\nPose AS voie B","CTL","Medium","CTL L24/1 voies A et B\r\nVoie 554 HS\r\nVoie HS entre AS72K et 51AK"," ",57870]
["2024-05-10","2024-05-13","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 5-2024\r\nWeek-end 2/2\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies I, II, III en gare de Luttre inaccessible en continu\r\nIndisponibilité de la transversale Sud à partir du 09/02 (voie déviée)"," ",49787]
["2024-05-10","2024-05-13","SW",1,"124A","A","LUTTRE","ROUX","Weekend","Continuous","23:30","04:40","Linked to coupure nr 49787 on line 124 tracks(s) A+B from LUTTRE to Y.NORD: Aménagement Gare de Luttre : Phase 5-2024\r\nWeek-end 2/2\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc"," "," ",49787]
["2024-05-10","2024-05-13","SW",1,"94","A+B","ATH","TOURNAI","Weekend","Continuous","23:20","04:40","Renouvellement PN 70 et 80\r\n+ Renforcement de 7 PI entre les km 54.992 et 63.375 sur la L94\r\nPhase 1.2 : PI 1+2\r\nConstruction d'un PI dans le cadre de la suppression du PN30\r\nPhase 1.1 : Mise en œuvre de palplanches","CTL","Medium","ART 2 min","Info Racc : Havinnes inaccessible",49414]
["2024-05-10","2024-05-13","SW",3,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:30","05:00","Maintenance Z3. 51  P4+\r\n+ Renouvellement Pi métalliques 52.015 et 52.215","CTL","Medium","ART stab  2 min 3 semaines","HKM à adapter",49114]
["2024-05-10","2024-05-13","SW",3,"90","A+B","GERAARDSBERGEN","ATH","Weekend","Continuous","22:30","04:30","PLP - MES","CTL","Medium",null,"InfoRacc",57022]
["2024-05-10","2024-06-10","NE",1,"27A","*","ANTWERPEN-NOORD-INRIT C1","ANTWERPEN-NOORD-INRIT C1","AllWeek","Continuous","23:00","05:00","LANGE TLO 4 weken: Vernieuwing wissels bundelkop C1 + verbinding tussen C1-C2 --> Fase 2","CTL","High"," ","Info Racc",49859]
["2024-05-11","2024-05-13","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","Weekend","Continuous","01:00","04:00","Voorbereidingsweekend  2/2 Vernieuwing Y.Noord-Driehoek-Aarschot\r\nPlaatsen nieuwe BVL-palen en voorbereidingswerken sporen\r\nDossier: 2024 - L16 Y.Oost Driehoek Aarschot-Heist od Berg - 211109","CTL","Medium"," "," ",52879]
["2024-05-11","2024-05-13","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Weekend","Continuous","01:00","04:00","Linked to coupure nr 52879 on line 16 tracks(s) A+B from Y.OOST DRIEHOEK AARSCHOT to HEIST-OP-DEN-BERG: Voorbereidingsweekend  2/2 Vernieuwing Y.Noord-Driehoek-Aarschot\r\nPlaatsen nieuwe BVL-palen en voorbereidingswerken sporen\r\nDossier: 2024 - L16 Y.Oos","CTL","Medium"," "," ",52879]
["2024-05-11","2024-05-12","NE",2,"52","A","PUURS","Y.ANTWERPEN-ZUID","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59098]
["2024-05-11","2024-05-12","NE",2,"59","A","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59097]
["2024-05-11","2024-05-12","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61582]
["2024-05-11","2024-05-12","NW",3,"75","B","WAREGEM","KORTRIJK","Weekend","Night","22:15","06:00","vervangen rijdraad SP B- JVO\r\nSP A bijkomend tijdens de nacht 00.20-05.15","SAVU_CTRL","Minor_AdHoc",null," ",58600]
["2024-05-11","2024-05-12","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Weekend","Continuous","12:00","08:00","Travaux SNCF CHA24_0027268 \r\nLille Tourcoing : REGE - Remplacement du joint entre les deux tabliers TPE Pra km 5.921","CTL","Medium",null," ",57907]
["2024-05-11","2024-05-12","SW",3,"130","B","CHATELET-GRIL EST","CHATELET-GRIL OUEST","Weekend","Continuous","22:00","22:00","Maintenance Z18. 51 (R6 22h - R7 22h)","Autre","Minor_AdHoc","Mise hors service en une zone (= Zone 18), voici les détails:\r\nL130, faisceau B\tVoie 353 + 354 + 355 + 356 + 357 + 358\tChâtelet\tChâtelet\t12J (ne)  &\t43AJ/44J (ne)\r\n\t\t\t\t+ 12J (ne)   &\t21AJ/22J (ne)"," ",55060]
["2024-05-11","2024-05-13","CE",1,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","00:20","04:00","P008 518: Op dubbel spoor brengen L161/1: voorbereidend WE BVL","CTL","Medium","TLO L50 + L26B + L161/1"," ",58939]
["2024-05-11","2024-05-13","CE",1,"26B","B","Y.PONT-DE-LA-SENNE","SCHAERBEEK","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58939 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Op dubbel spoor brengen L161/1: voorbereidend WE BVL","CTL","Medium"," "," ",58939]
["2024-05-11","2024-05-13","CE",1,"50","A+B","BRUXELLES-NORD","Y.LAEKEN","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58939 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Op dubbel spoor brengen L161/1: voorbereidend WE BVL","CTL","Medium"," "," ",58939]
["2024-05-11","2024-05-13","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58406 on line 50 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.BOCKSTAEL: Onderhoudszone FBN_12/FSR_06 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling van L50 tussen FBN Rooster F (E/EX-F8) en Y Bockstael (niet inbe","CTL","Medium"," ","Omleiden via L26",58406]
["2024-05-11","2024-05-13","CE",2,"26B","A+B","Y.PONT-DE-LA-SENNE","SCHAERBEEK","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58406 on line 50 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.BOCKSTAEL: Onderhoudszone FBN_12/FSR_06 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling van L50 tussen FBN Rooster F (E/EX-F8) en Y Bockstael (niet inbe","CTL","Medium"," ","Omleiden via L26",58406]
["2024-05-11","2024-05-13","CE",2,"28(1)","A+B","Y.LAEKEN","Y.PANNENHUIS","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58406 on line 50 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.BOCKSTAEL: Onderhoudszone FBN_12/FSR_06 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling van L50 tussen FBN Rooster F (E/EX-F8) en Y Bockstael (niet inbe","CTL","Medium"," ","Omleiden via L26",58406]
["2024-05-11","2024-05-13","CE",2,"50","A+B","BRUXELLES-NORD-GRIL F","Y.BOCKSTAEL","Weekend","Continuous","00:20","04:00","Onderhoudszone FBN_12/FSR_06 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling van L50 tussen FBN Rooster F (E/EX-F8) en Y Bockstael (niet inbegrepen)\r\nBijkomend aftakkingen van L28(1) tussen Y Laken en Y Pannenhuis (niet inbegrepen) en v","CTL","Medium","Alle goederenverkeer langs L26","Omleiden via L26",58406]
["2024-05-11","2024-05-13","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58629]
["2024-05-11","2024-05-13","NE",2,"12","A+B","ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58249 on line 27A tracks(s) A from ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht","CTL","Medium"," "," ",58249]
["2024-05-11","2024-05-13","NE",2,"12","A+B","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Engelse Leien vervolg vernieuwen wissels \r\nTLO L12+27A SPa +bundelkop C","CTL","Medium"," "," ",58049]
["2024-05-11","2024-05-13","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3+4+5+6+7+8+9","CTL","Medium","Vilvoorde sporen 3+4+5+6+7+8+9"," ",58201]
["2024-05-11","2024-05-13","NE",2,"27A","A","ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht","SAVU","Minor_AdHoc","bundel kop bundel C +L12 TLO"," ",58249]
["2024-05-11","2024-05-13","NE",2,"27A","A","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58049 on line 12 tracks(s) A+B from Y.ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse Leien vervolg vernieuwen wissels \r\nTLO L12+27A SPa +bundelkop C","SAVU","Minor_AdHoc"," "," ",58049]
["2024-05-11","2024-05-13","NE",2,"27A/1","A+B","ANTWERPEN-NOORD-INRIT C1","ANTWERPEN-NOORD-INRIT C1","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58249 on line 27A tracks(s) A from ANTWERPEN-OOST to Y.ANTWERPEN-SCHIJNPOORT: Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht","CTL","Medium"," "," ",58249]
["2024-05-11","2024-05-21","CE",1,"96","A","BRUXELLES-MIDI","Y.NOORD HALLE","AllWeek","Continuous","04:40","04:30","Stabilisatie-BTS Vernieuwen sp A L96 met P+C-trein Fase 2","ART","Minor_AdHoc","BTS"," ",56110]
["2024-05-11","2024-05-12","SE",3,"161","A/B","BAKENBOS","OTTIGNIES","Weekend","Day","08:00","16:00","Visite voies A/B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 08h00 et 16h00 le samedi et le dimanche,  avec adaptations trains"," ",48909]
["2024-05-12","2024-05-12","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61610]
["2024-05-12","2024-05-12","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59988]
["2024-05-12","2024-05-12","NW",3,"202B","S","ZEEBRUGGE-BUNDEL RAMSKAPELLE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Day","08:00","16:00","R-419026-01\r\n\r\nOnderhoud 3421-56 \r\n\r\nAW 13R-14R-15R-16R-17R-18R-19R-21BR-75R-76R-77R-78R-79R-80R-81R-82R buiten dienst \r\nbundelsporen 1-2-3-4-5-6-7-8 buiten dienst","Autre","Minor_AdHoc"," ","Info Racc",60378]
["2024-05-12","2024-05-31","SE",1,"154","A+B","NAMUR","LUSTIN","AllWeek","Continuous","18:00","18:00","ART 5min\r\nSuppression PN 99 et 101 Jambes : pose de deux couloir sous-voies + extension quais gare de Jambes\r\nRemise en état pistes PI BK 63.100","ART","Minor_AdHoc","PN 99 : ART BK 63.900 à 64.100 en voies A et B. V 40 km/h. HKV : 2 min / HKM : 3 min du 12/05 au 31/05\r\nPN 101 : ART BK 65.400 à 65.500 en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 12/05 au 31/05"," ",48612]
["2024-05-13","2024-05-17","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","Week","Night","23:50","04:30","Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers","CTL","Minor_AdHoc"," "," ",58979]
["2024-05-13","2024-05-17","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Week","Night","23:50","04:30","Linked to coupure nr 58979 on line 16 tracks(s) A+B from Y.OOST DRIEHOEK AARSCHOT to HEIST-OP-DEN-BERG: Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers","CTL","Minor_AdHoc"," "," ",58979]
["2024-05-13","2024-05-17","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59863]
["2024-05-13","2024-05-17","NW",1,"53","A+B","LONDERZEEL","SCHELLEBELLE","Week","Continuous","23:30","04:30","PLP Dendermonde\r\nBeperkingen voor het treinverkeer.","Autre","Minor_AdHoc","Beperkingen voor het treinverkeer."," ",60253]
["2024-05-13","2024-05-17","NW",1,"60","A+B","DENDERMONDE","OPWIJK","Week","Continuous","23:30","04:30","Linked to coupure nr 60253 on line 53 tracks(s) A+B from LONDERZEEL to SCHELLEBELLE: PLP Dendermonde\r\nBeperkingen voor het treinverkeer.","Autre","Minor_AdHoc"," "," ",60253]
["2024-05-13","2024-05-17","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58475]
["2024-05-13","2024-05-17","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58475 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58475]
["2024-05-13","2024-05-17","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58475 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58475]
["2024-05-13","2024-05-17","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58475 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58475]
["2024-05-13","2024-05-17","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Week","Night","22:10","04:10","Renouvellement AS Y. La Sambre\r\nTravaux préparatoires caténaire\r\n+ Maintenance Z2. 51  P3 HKV\r\n+ Travaux voie A signalisation","CTL","Minor_AdHoc"," ","HKM adapter\r\nInfo racc - Solvay (Les Petons)",49238]
["2024-05-13","2024-05-18","NE",3,"35","A+B","LEUVEN","AARSCHOT","Week","Night","23:30","04:30","afschaffen OW 119 langestraat +verhogen perrons Wezemaal","CTL","Minor_AdHoc","alternatief E2622-E2743-E2221"," ",60037]
["2024-05-13","2024-05-18","NW",1,"75","A+B","KORTRIJK","MOUSCRON","Week","Night","23:10","04:00","TLO-nachten voor TESTEN ETCS\r\n2 weken aansluitend nachten in mei 2024\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk","CTL","Minor_AdHoc"," "," ",57127]
["2024-05-13","2024-05-18","SW",2,"112","B","LA LOUVIERE-CENTRE","LA LOUVIERE-CENTRE","Week","Continuous","09:00","05:20","Construction passerelle gare de LLV Centre. Réalilsation micro-pieux quai central","SAVU_CTRL","Minor_AdHoc","L112 VB en continu = Voie 1\r\nSAVU de jour (9h-15h) + CTL de nuit : 23:20 - 5:20\r\nMaintenir circulation aux heures de pointes pour éviter un dérouillage","HKM à adapter",53894]
["2024-05-13","2024-05-21","SW",1,"118","A+B","Y.LA PAIX","MONS","AllWeek","Continuous","04:30","04:00","ART 5 min\r\nMassification Tracks+OA+SI\r\nART de stabilisation après travaux","ART","Minor_AdHoc","ART de stabilisation : 5,04 min HKV du 13/5 au 21/5/2024 (km 28.100 au km 36.300)"," ",57258]
["2024-05-13","2024-05-24","SW",3,"94","A+B","LEUZE","TOURNAI","Week","Continuous","04:40","23:20","Renouvellement PN 70 et 80\r\nART","ART","Minor_AdHoc","ART stabilisation (40/60) : du 11/05 au 24/05 (fin probable)\r\nHKV\t: 2.52/1.44 - HKM : 3.4/1.76",null,49540]
["2024-05-13","2024-06-03","SW",3,"140","A+B","OTTIGNIES","FLEURUS","AllWeek","Continuous","05:00","05:00","ART 2min\r\nRenouvellement Pi métalliques 52.015 et 52.215","ART","Minor_AdHoc","ART stab  2 min 3 semaines","HKM à adapter",61375]
["2024-05-13","2024-06-09","SE",1,"24","B","Y.GLONS","BASSENGE","AllWeek","Continuous","07:00","22:00","Sécurisation d'ouvrages et réfection de chapes d'étanchéité","SAVU","High","ART 6min"," ",50614]
["2024-05-14","2024-05-14","NE",3,"25","A","ANTWERPEN-CENTRAAL","ANTWERPEN-CENTRAAL","Weekend","Day","10:00","15:00","onderhoud SIG L25Sp A (perron 21+22 antwerpen centraal -2)","SAVU","Minor_AdHoc"," "," ",59712]
["2024-05-14","2024-05-17","CE",1,"96","A+B","BRUXELLES-MIDI","Y.NOORD HALLE","Week","Night","00:40","04:40","Vernieuwen sp A L96: voorbereidende nachten Fase 2","CTL","Minor_AdHoc","TLO L96+96N tussen FBMZ en Halle."," ",50043]
["2024-05-17","2024-05-20","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59568]
["2024-05-17","2024-05-20","NE",2,"10","A","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58682 on line 10 tracks(s) B from Y.KOESTRAAT to Y.HAZOP: aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc"," "," ",58682]
["2024-05-17","2024-05-20","NE",2,"10","B","Y.KOESTRAAT","Y.HAZOP","Weekend","Continuous","00:00","04:00","aanleg extra klauw bundel zuid\r\n\r\nBD L10 spoor B+min 2 bundelsporen+bundelkoppen+bundel Zuid afgesloten","SAVU","Minor_AdHoc","DOES op spoor A L10 / bundel Zuid afgesloten"," ",58682]
["2024-05-17","2024-05-20","NE",2,"21C","S","Y.BOSDEL","Y.NIEUWDAK","Weekend","Continuous","23:40","04:00","Vervanging ONB Dominikanenlaan km 29.833\r\n\r\n\r\n\r\n\r\n\r\n\r\nR-431784-01","CTL","Medium","geen toegang tot L230"," ",61658]
["2024-05-17","2024-05-20","NE",2,"230","A+B","Y.BOSDEL","ZUTENDAAL","Weekend","Continuous","23:40","04:00","Linked to coupure nr 61658 on line 21C tracks(s) S from Y.BOSDEL to Y.NIEUWDAK: Vervanging ONB Dominikanenlaan km 29.833\r\n\r\n\r\n\r\n\r\n\r\n\r\nR-431784-01","CTL","Medium"," "," ",61658]
["2024-05-17","2024-05-20","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59904]
["2024-05-17","2024-05-20","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 6-2024\r\nTravaux mur de soutènement - BOA\r\nWeek-end 3/5\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies I, II en gare de Luttre inaccessible en continu"," ",49820]
["2024-05-17","2024-05-20","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 min","HKM à adapter",48631]
["2024-05-17","2024-05-21","NW",1,"53","A+B","LONDERZEEL","SCHELLEBELLE","Weekend","Continuous","23:30","04:30","L53 + Dendermonde:  indienstname PLP (masterplan ETCS)\r\nWE1/3\r\ntussen de weekends zijn er beperkingen  in de versporingen (meerdere wissels blijven geklauwd na WE1)","CTL","Medium"," "," ",47855]
["2024-05-17","2024-05-21","NW",1,"60","A+B","DENDERMONDE","OPWIJK","Weekend","Continuous","23:30","04:30","Linked to coupure nr 47855 on line 53 tracks(s) A+B from LONDERZEEL to SCHELLEBELLE: L53 + Dendermonde:  indienstname PLP (masterplan ETCS)\r\nWE1/3\r\ntussen de weekends zijn er beperkingen  in de versporingen (meerdere wissels blijven geklauwd na WE1)","CTL","Medium"," "," ",47855]
["2024-05-17","2024-05-21","SE",2,"44","A+B","PEPINSTER-CITE","SPA-GERONSTERE","Weekend","Continuous","23:00","05:00","Renouvellement des équipements de signalisation des PNs 3, 4, 5 et 6 (Préparation et ou MES)\r\n+ Entretien manuel et mécanisés des AW \r\nEntretien manuel et mécanisés de la voie courante\r\nEntretien manuel et mécanisés des PN","CTL","Medium","WE Pentecôte"," ",55096]
["2024-05-17","2024-05-21","SW",1,"118","A+B","MONS","Y.LA PAIX","Weekend","Continuous","23:30","04:30","Massification Tracks+OA+SI :\r\nProjet Holcim : nouveau branchement&liaison pour le raccordé à Obourg\r\nRenouvellement de la chape des PI km 29,050 et 28,180 situé entre Y.St-Vaast et Obourg ;\r\nMise en sevice SIMIS-W entre Mons et Obourg (gare incluse).\r\nT","CTL","Medium","CTL  WE 3jrs"," ",55217]
["2024-05-17","2024-05-20","SE",3,"161","A","RHISNES","GEMBLOUX","Weekend","Continuous","23:00","05:00","réélectrification","SAVU","Minor_AdHoc","une voie en continu"," ",49709]
["2024-05-17","2024-05-20","SE",2,"154","A/B","NAMUR","LUSTIN","Weekend","Continuous","23:00","05:00","Entretien AS , traitement zone boueuse","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 20/05 au 23/05 (fin probable)"," ",57688]
["2024-05-18","2024-05-27","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","AllWeek","Continuous","01:00","04:30","Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers\r\n\r\n+ 2 WE voorbereiding en 2 WE afwerking","CTL","High"," "," ",49873]
["2024-05-18","2024-05-27","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","AllWeek","Continuous","01:00","04:30","Linked to coupure nr 49873 on line 16 tracks(s) A+B from Y.OOST DRIEHOEK AARSCHOT to HEIST-OP-DEN-BERG: Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers\r\n\r\n+ 2 WE voorbereiding en 2 WE afwerking","CTL","High"," "," ",49873]
["2024-05-18","2024-05-19","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59429]
["2024-05-18","2024-05-19","SE",3,"165","A+B","SAINT-VINCENT-BELLEFONTAINE","VIRTON","Weekend","Continuous","23:00","15:00","Maintenance \r\nInterventions Programmées","CTL","Medium","CTL du sa. 23h00 au di. 15h00\r\nART 2 min"," ",46687]
["2024-05-18","2024-05-20","NE",1,"12","A+B","Y.SINT-MARIABURG","LUCHTBAL-ROOSTER S","Weekend","Continuous","00:00","04:00","304(statiestraat)+308 (herelectrificatie)","CTL","Medium","Aan deze werken is een R7 (van 06h00 tot 17h30) gekoppeld op L27A voor het spoorgedeelte Y.Laarsebeek - Y.Schijn!! (58228)"," ",58066]
["2024-05-18","2024-05-20","NE",1,"29","A+B","Y.KRUISBERG","TURNHOUT-BUNDEL","Weekend","Continuous","00:00","04:00","Linked to coupure nr 49866 on line 15 tracks(s) A+B from Y.NAZARETH to GEEL: Indienstname ETCS\r\n+ Brugdag. Meewerken niet mogelijk\r\n+\r\nETCS \r\nmeewerken niet mogelijk (59198)","CTL","Medium"," "," ",49866]
["2024-05-18","2024-05-20","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58016]
["2024-05-18","2024-05-20","NE",2,"12","A+B","ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","engelse leien vervolg vernieuwen wissels \r\nTLO L12 spa +bundelkop bundel C","CTL","Medium"," "," ",58050]
["2024-05-18","2024-05-20","NE",2,"34","A+B","GLONS","HASSELT","Weekend","Continuous","06:00","04:00","onderhoud +vernieuwen van OW\r\nUPM : 429156","CTL","Medium"," "," ",59349]
["2024-05-18","2024-05-20","NE",3,"25","A+B","Y.ARENDSTRAAT","KONTICH-LINT","Weekend","Continuous","00:30","04:00","onderhoud wissels Y Stadion","CTL","Medium","tijdens werken in de loop van de dag zal er beveiliging op L27 zijn door  ATW-TX"," ",59710]
["2024-05-18","2024-05-20","NE",3,"27","A+B","Y.LIERSESTEENWEG","ANTWERPEN-BERCHEM","Weekend","Night","00:30","04:00","onderhoud wissels Y Stadion , beveiliging L27\r\n\r\nhangt samen met colt 59710 L25","CTL","Minor_AdHoc"," "," ",59714]
["2024-05-18","2024-05-20","NW",2,"90","A+B","DENDERLEEUW","Y.NEDERBOELARE","Weekend","Continuous","06:00","04:20","Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P038_01_L90_Geraardsbergen - Ninove_IL\r\nETCS L2-IL_NW_P038_02_L90_Ninove_IL\r\nETCS L2-IL_NW_P038_03_L90_Ninove - Denderleeuw_IL\r\n\r\n*R6 06.00u - L90 niet in CBP","CTL","Medium",null,"Info Racc.",57547]
["2024-05-18","2024-05-20","SE",2,"24/1","A+B","VISE","Y.LONGCHAMPS","Weekend","Continuous","22:00","04:40","Pose d'une nouvelle liaison - WE finitions n°1\r\nBourrage de révision, contraintes et finitions","SAVU","Minor_AdHoc","SAVU R6 22h - R7 5h20\r\nCTL R7 5h20 - 15h20\r\nSAVU R7 15h20 - R1 4h40\r\nCTL L24/1 voies A et B\r\nVoie 554 HS\r\nVoie HS entre AS72K et 51AK"," ",57874]
["2024-05-18","2024-05-20","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu\r\nBertrix accessible (mais uniquement venant de Libramont)"," ",47172]
["2024-05-18","2024-05-21","CE",1,"96","A+B","Y.RUISBROEK","Y.NOORD HALLE","Weekend","Continuous","00:40","04:40","Vernieuwing met P+C-trein Fase 3 WE4","CTL","Medium","TLO L96+96E tussen Halle en Ruisbroek."," ",49982]
["2024-05-18","2024-05-21","CE",1,"96E","S","Y.NOORD HALLE","LOT","Weekend","Continuous","00:40","04:40","Linked to coupure nr 49982 on line 96 tracks(s) A+B from Y.RUISBROEK to Y.NOORD HALLE: Vernieuwing met P+C-trein Fase 3 WE4","CTL","Medium"," "," ",49982]
["2024-05-18","2024-05-19","SE",3,"161","A/B","GEMBLOUX","RHISNES","Weekend","Day","08:00","16:00","Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49196]
["2024-05-19","2024-05-19","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","08:00","18:00","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58228]
["2024-05-19","2024-05-19","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Continuous","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het werkvenster","CTL","Medium"," "," ",59810]
["2024-05-19","2024-05-20","NW",2,"75","*","KORTRIJK","KORTRIJK","Weekend","Continuous","01:00","04:30","Mei 2024: spoor II en III buiten dienst voor 24u","Autre","Minor_AdHoc"," "," ",58530]
["2024-05-20","2024-05-24","NE",3,"12","A+B","ANTWERPEN-NOORDERDOKKEN","Y.HOLLAND","Week","Night","23:25","04:00","onderheid SIG Y luchtbal en onderhoud wissel Y Antwerpen-luchtbal","CTL","Minor_AdHoc","alternatief E2573-E2594"," ",60120]
["2024-05-20","2024-05-24","NE",3,"139","A+B","LEUVEN","SINT-JORIS-WEERT","Week","Night","23:00","05:00","Onderhoud","CTL","Minor_AdHoc","alternatief E5722"," ",60243]
["2024-05-20","2024-05-24","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59864]
["2024-05-20","2024-05-24","NE",3,"29","A+B","Y.KRUISBERG","TURNHOUT","Week","Night","23:00","04:40","omvormen 50 HZ SK naar TFSK\r\naanpassen treindetectiesysteem (moet voor 2025)\r\nvernieuwing signalisatie overwegen\r\nomvorming moet gebeuren voor uitrol ETCS L29","CTL","Minor_AdHoc","alternatief E3421"," ",60016]
["2024-05-20","2024-05-24","SE",1,"130/1","A+B","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Week","Day","09:00","15:30","Linked to coupure nr 47280 on line 144 tracks(s) A+B from GEMBLOUX to JEMEPPE-SUR-SAMBRE: Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nPréparations","CTL","Minor_AdHoc"," ","Info Racc : raccordement inaccessible",47280]
["2024-05-20","2024-05-24","SE",1,"144","A+B","GEMBLOUX","JEMEPPE-SUR-SAMBRE","Week","Day","09:00","15:30","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nPréparations","CTL","Minor_AdHoc","Coupures de jour en semaine (minimum 6h)","Info Racc : raccordement inaccessible",47280]
["2024-05-20","2024-05-25","NW",1,"75","A+B","KORTRIJK","MOUSCRON","Week","Night","23:10","04:00","TLO-nachten voor TESTEN ETCS\r\n2 weken aansluitend nachten in mei 2024\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk","CTL","Minor_AdHoc"," "," ",57137]
["2024-05-20","2024-05-25","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58476]
["2024-05-20","2024-05-25","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58476 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58476]
["2024-05-20","2024-05-25","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58476 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58476]
["2024-05-20","2024-05-25","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58476 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58476]
["2024-05-20","2024-05-25","SW",1,"94","A+B","ATH","TOURNAI","Week","Night","23:20","04:40","Renouvellement PN 70 et 80","CTL","Minor_AdHoc",null,"Info Racc : desserte d'Havinnes impossible",49413]
["2024-05-20","2024-05-25","SW",2,"112","B","LA LOUVIERE-CENTRE","LA LOUVIERE-CENTRE","Week","Continuous","09:00","05:20","Construction passerelle gare de LLV Centre. Réalilsation micro-pieux quai central","SAVU_CTRL","Minor_AdHoc","L112 VB en continu = Voie 1\r\nSAVU de jour (9h-15h) + CTL de nuit : 23:20 - 5:20\r\nMaintenir circulation aux heures de pointes pour éviter un dérouillage","HKM à adapter",61384]
["2024-05-20","2024-06-02","SE",1,"43","A","TILFF","ESNEUX","AllWeek","Continuous","06:00","22:00","Renouvellement Mur de soutènement km 7.500 VA\r\nrq 333 : suite demande SNCB, possible de décaler pdt congés? vacances scolaires d'été? + Attention accés Plopsa Coo\r\n-> possibilité vacances Paques?\r\ndu lundi 29/04 au 12/05","SAVU_CTRL","High","Nuits de CTL de minimum 6h (23:00-5:00)\r\nART de protection VB à 60km/h (HKV: 0,5'  HKM: 1,7')\r\nART de stabilisation:\r\nVitesse réduite à 40km/h sur VA\r\nperte de temps HKV: 1,1'\r\nperte de temps HKM: 3,1'"," ",47307]
["2024-05-21","2024-05-24","NW",1,"53","A+B","LONDERZEEL","SCHELLEBELLE","Week","Continuous","04:30","23:30","PLP Dendermonde\r\nBeperkingen voor het treinverkeer.","Autre","Minor_AdHoc","Beperkingen voor het treinverkeer."," ",47856]
["2024-05-21","2024-05-24","NW",1,"60","A+B","DENDERMONDE","OPWIJK","Week","Continuous","04:30","23:30","Linked to coupure nr 47856 on line 53 tracks(s) A+B from LONDERZEEL to SCHELLEBELLE: PLP Dendermonde\r\nBeperkingen voor het treinverkeer.","Autre","Minor_AdHoc"," "," ",47856]
["2024-05-21","2024-05-24","NW",3,"89","A+B","DENDERLEEUW","ZOTTEGEM","Week","Night","00:40","04:20","Vernieuwen rails OW 34&36 (Harmelen)\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc",null," ",58588]
["2024-05-21","2024-06-01","CE",1,"96","A","Y.RUISBROEK","Y.NOORD HALLE","AllWeek","Continuous","04:40","04:40","Stabilisatie-BTS Vernieuwing met P+C-trein Fase 3 WE4","ART","Minor_AdHoc","BTS"," ",56111]
["2024-05-23","2024-05-23","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55945]
["2024-05-24","2024-05-27","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59569]
["2024-05-24","2024-05-27","NE",2,"21C","S","Y.BOSDEL","Y.NIEUWDAK","Weekend","Continuous","23:40","04:00","Vervanging ONB Dominikanenlaan km 29.833\r\nR-431785-01","CTL","Medium","geen toegang tot L230"," ",61659]
["2024-05-24","2024-05-27","NE",2,"230","A+B","Y.BOSDEL","ZUTENDAAL","Weekend","Continuous","23:40","04:00","Linked to coupure nr 61659 on line 21C tracks(s) S from Y.BOSDEL to Y.NIEUWDAK: Vervanging ONB Dominikanenlaan km 29.833\r\nR-431785-01","CTL","Medium"," "," ",61659]
["2024-05-24","2024-05-27","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59905]
["2024-05-24","2024-05-27","NE",3,"230","A+B","Y.BOSDEL","ZUTENDAAL","Weekend","Continuous","23:00","05:00","Onderhoud","CTL","Medium"," "," ",59969]
["2024-05-24","2024-05-27","NW",1,"53","A+B","LONDERZEEL","SCHELLEBELLE","Weekend","Continuous","23:30","04:30","L53/60 Dendermonde:  indienstname PLP (masterplan ETCS)\r\nWE2/3\r\ntussen de weekends zijn er beperkingen  in de versporingen (meerdere wissels blijven geklauwd na WE1)","CTL","Medium"," "," ",47859]
["2024-05-24","2024-05-27","NW",1,"60","A+B","DENDERMONDE","OPWIJK","Weekend","Continuous","23:30","04:30","Linked to coupure nr 47859 on line 53 tracks(s) A+B from LONDERZEEL to SCHELLEBELLE: L53/60 Dendermonde:  indienstname PLP (masterplan ETCS)\r\nWE2/3\r\ntussen de weekends zijn er beperkingen  in de versporingen (meerdere wissels blijven geklauwd na WE1)","CTL","Medium"," "," ",47859]
["2024-05-24","2024-05-27","SE",1,"130/1","A+B","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Weekend","Continuous","23:30","06:00","Linked to coupure nr 49893 on line 144 tracks(s) A+B from GEMBLOUX to JEMEPPE-SUR-SAMBRE: Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 1/4 (AS 21Q, 22Q)","CTL","Medium"," ","Info Racc : raccordement inaccessible",49893]
["2024-05-24","2024-05-27","SE",1,"144","A+B","GEMBLOUX","JEMEPPE-SUR-SAMBRE","Weekend","Continuous","23:30","06:00","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 1/4 (AS 21Q, 22Q)","CTL","Medium","Pas d'ART : L130/1 est à 40 km/h","Info Racc : raccordement inaccessible",49893]
["2024-05-24","2024-05-27","SE",2,"24/1","A+B","VISE","Y.LONGCHAMPS","Weekend","Night","23:00","05:00","Pose d'une nouvelle liaison - WE finitions n°2\r\nBourrage de révision, contraintes et finitions\r\nNuits min 06h","CTL","Minor_AdHoc","CTL L24/1 voies A et B\r\nVoie 554 HS\r\nVoie HS entre AS72K et 51AK\r\nNuits min 6h"," ",57875]
["2024-05-24","2024-05-27","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 6-2024\r\nTravaux mur de soutènement - BOA\r\nWeek-end 4/5\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies I, II en gare de Luttre inaccessible en continu"," ",49821]
["2024-05-24","2024-05-27","SE",1,"161","A","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:45","WE SAVU RER Bakenbos-Ottignies","SAVU_CTRL","Minor_AdHoc","ART à définir, maximum 2'"," ",49249]
["2024-05-25","2024-05-26","SE",1,"166","A+B","ANSEREMME","HOUYET","Weekend","Continuous","23:00","15:00","Massification travaux OA tronçons Anseremme - Gendron et Gendron - Houyet (entretien tunnels, parois,...)","CTL","Medium","intervient avec le grand SAVU Houyet – Gendron ; pas d’ART supplémentaire !"," ",47505]
["2024-05-25","2024-05-26","SE",3,"43","A+B","Y.AGUESSES","TILFF","Weekend","Continuous","06:00","17:00","Reprise en EBP-PLP du tronçon","CTL","Medium"," "," ",57856]
["2024-05-25","2024-05-26","SW",2,"96","A+B","LEMBEEK","BRAINE-LE-COMTE","Weekend","Continuous","06:00","16:00","Maintenance Z1.53 en P4","CTL","Medium",null,"itinéraire via L96-90C-90 ou via L130A-124A/1-L124A-L124",49537]
["2024-05-25","2024-05-26","SW",3,"112","A+B","PIETON","LA LOUVIERE-SUD","Weekend","Continuous","06:00","17:00","Maintenance Z15.52\r\nMise HS P4 - Zone 15 AI52","CTL","Medium","Mise HS des quais I, II, III et IV en gare de La Louvière y compris"," ",49630]
["2024-05-25","2024-05-26","SW",3,"130C","A+B","CHATELET","CHARLEROI-SUD","Weekend","Continuous","06:00","17:00","Maintenance Z13. 51 (P4+)","CTL","Medium","Mise hors service en une zone, voici les détails:\r\nL130C\tVoie A\tCharleroi-Sud\tChâtelet\tFX5-I. 20\tI-H. 20\r\n\t        Voie B\t\t\tFX6-I. 21\tIX-H. 20"," ",48838]
["2024-05-25","2024-05-26","SW",3,"97","A+B","SAINT-GHISLAIN","QUIEVRAIN","Weekend","Continuous","06:00","16:45","Maintenance Z.14.53 en P4","CTL","Medium","FGH : voie IV doit rester accessible (cas 28461 doit rester sous tension)"," ",56583]
["2024-05-25","2024-05-27","CE",1,"124","B","BRUXELLES-MIDI","Y.FOREST-EST","Weekend","Continuous","06:00","04:30","Linked to coupure nr 50044 on line 96 tracks(s) A from BRUXELLES-MIDI to Y.NOORD HALLE: Vernieuwen sp A L96: afwerkingsWE 1/2 Fase 2","SAVU","Minor_AdHoc"," "," ",50044]
["2024-05-25","2024-05-27","CE",1,"96","A","BRUXELLES-MIDI","Y.NOORD HALLE","Weekend","Continuous","06:00","04:30","Vernieuwen sp A L96: afwerkingsWE 1/2 Fase 2","SAVU","Minor_AdHoc","DOES L96 tussen FBMZ en Halle.\r\nBijkomend sp A L96N en BL124 tijdens de nachten."," ",50044]
["2024-05-25","2024-05-27","NE",1,"29","A+B","Y.KRUISBERG","TURNHOUT-BUNDEL","Weekend","Continuous","00:00","04:00","Linked to coupure nr 59199 on line 15 tracks(s) A+B from Y.ALBERTKANAAL to OLEN: ETCS \r\nmeewerken niet mogelijk","CTL","Medium"," "," ",59199]
["2024-05-25","2024-05-27","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58017]
["2024-05-25","2024-05-27","NE",2,"12","A+B","ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","00:00","04:00","engelse leien vervolg vernieuwen wissels \r\nTLO L12 spa +bundelkop bundel C","CTL","Medium"," "," ",58051]
["2024-05-25","2024-05-27","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3+4+5+6+7+8+9","CTL","Medium","Vilvoorde sporen 3+4+5+6+7+8+9"," ",58202]
["2024-05-25","2024-05-27","NE",3,"224","*","ANTWERPEN-D.S.-LILLO","ANTWERPEN-D.S.-LILLO","Weekend","Continuous","06:00","18:00","massificatiewerken","CTL","Medium"," "," ",60817]
["2024-05-25","2024-05-27","NW",2,"89","A+B","DENDERLEEUW","ZOTTEGEM","Weekend","Continuous","00:40","04:20","Buitenwerken\r\nvernieuwing SI te FDD-Burst / Burst inbegrepen\r\n+\r\nVernieuwen rails OW 34&36 (Harmelen)\r\n2 aparte weekends (wegens combinatie wegomlegging)","CTL","Medium",null," ",57555]
["2024-05-25","2024-05-27","SE",1,"166","A+B","ANSEREMME","HOUYET","Weekend","Continuous","06:00","04:30","Massification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse","CTL","Medium","Pas d'ART après le WE","HKM à adapter",60553]
["2024-05-25","2024-05-27","SE",3,"165(1)","A+B","LIBRAMONT","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2x25 kV Recogne - Bertrix + déplacement ZSP","CTL","Medium","nuit sa/di jusque 15h di + nuit di/lu"," ",47187]
["2024-05-25","2024-05-26","SE",1,"154","A+B","NAMUR","LUSTIN","Weekend","Continuous","06:00","18:00","Suppression PN 99 et 101 Jambes : finitions aux deux couloir sous-voies + extension quais gare de Jambes\r\nRemise en état pistes PI BK 63.100","CTL","Medium"," "," ",47497]
["2024-05-26","2024-05-26","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59989]
["2024-05-27","2024-05-31","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","Week","Night","23:50","04:30","Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers","CTL","Minor_AdHoc"," "," ",58981]
["2024-05-27","2024-05-31","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Week","Night","23:50","04:30","Linked to coupure nr 58981 on line 16 tracks(s) A+B from Y.OOST DRIEHOEK AARSCHOT to HEIST-OP-DEN-BERG: Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers","CTL","Minor_AdHoc"," "," ",58981]
["2024-05-27","2024-05-27","SE",3,"130","A/B","NAMUR","FLAWINNE","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49048]
["2024-05-27","2024-05-31","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59865]
["2024-05-27","2024-05-31","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:10","04:00","weeknachten als fase 3 in map 3","CTL","Minor_AdHoc"," "," ",60198]
["2024-05-27","2024-05-31","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:50","04:30","Onderhoud","CTL","Minor_AdHoc","te bepalen"," ",59735]
["2024-05-27","2024-05-31","NW",1,"53","A+B","LONDERZEEL","SCHELLEBELLE","Week","Continuous","04:30","23:30","PLP Dendermonde\r\nBeperkingen voor het treinverkeer.","Autre","Minor_AdHoc","Beperkingen voor het treinverkeer."," ",47857]
["2024-05-27","2024-05-31","NW",1,"60","A+B","DENDERMONDE","OPWIJK","Week","Continuous","04:30","23:30","Linked to coupure nr 47857 on line 53 tracks(s) A+B from LONDERZEEL to SCHELLEBELLE: PLP Dendermonde\r\nBeperkingen voor het treinverkeer.","Autre","Minor_AdHoc"," "," ",47857]
["2024-05-27","2024-05-31","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58481]
["2024-05-27","2024-05-31","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58481 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58481]
["2024-05-27","2024-05-31","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58481 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58481]
["2024-05-27","2024-05-31","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58481 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58481]
["2024-05-27","2024-05-31","NW",3,"122","A+B","ZOTTEGEM","Y.MELLE","Week","Night","23:50","05:10","Vernieuwen rails","CTL","Minor_AdHoc",null,null,57844]
["2024-05-27","2024-06-09","SE",1,"167","S","Y.AUTELBAS","ATHUS-LONGEAU","AllWeek","Continuous","08:00","16:00","Assainissement L167 - zone Messancy","CTL","High","ART réduit à 60KM/h jusqu'à une semaine après la fin des travaux"," ",46798]
["2024-05-28","2024-05-31","NW",3,"89","A+B","DENDERLEEUW","ZOTTEGEM","Week","Night","00:40","04:20","Vernieuwen rails OW 34&36 (Harmelen)\r\n\r\n* R5/R6 in weekend TLO","CTL","Minor_AdHoc",null," ",58589]
["2024-05-28","2024-06-01","CE",1,"96","A+B","BRUXELLES-MIDI","Y.NOORD HALLE","Week","Night","00:40","04:40","Vernieuwen sp A L96: afwerking nachten Fase 2","CTL","Minor_AdHoc","TLO L96+96N tussen FBMZ en Halle."," ",56106]
["2024-05-29","2024-05-29","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60093]
["2024-05-30","2024-05-30","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60109]
["2024-05-31","2024-06-03","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","Weekend","Continuous","23:50","04:00","Afwerkingsweekend 1/3 Vernieuwing Y.Noord-Driehoek-Aarschot+vernieuwen duikers\r\n\r\n\r\nDossier: 2024 - L16 Y.Oost Driehoek Aarschot-Heist od Berg - 211109","CTL","Medium"," "," ",53699]
["2024-05-31","2024-06-03","NE",3,"16","A+B","Y.NAZARETH","HEIST-OP-DEN-BERG","Weekend","Continuous","23:50","04:30","vernieuwen overwegen strail","CTL","Medium"," "," ",60231]
["2024-05-31","2024-06-03","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Weekend","Continuous","23:50","04:00","Linked to coupure nr 53699 on line 16 tracks(s) A+B from Y.OOST DRIEHOEK AARSCHOT to HEIST-OP-DEN-BERG: Afwerkingsweekend 1/3 Vernieuwing Y.Noord-Driehoek-Aarschot+vernieuwen duikers\r\n\r\n\r\nDossier: 2024 - L16 Y.Oost Driehoek Aarschot-Heist od Berg - 2111","CTL","Medium"," "," ",53699]
["2024-05-31","2024-06-02","SE",3,"43","A+B","BOMAL","MARLOIE","Weekend","Continuous","23:00","17:00","Chantier de maintenance","CTL","Medium"," "," ",57729]
["2024-05-31","2024-06-03","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59570]
["2024-05-31","2024-06-03","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59906]
["2024-05-31","2024-06-03","NW",2,"53","A+B","SCHELLEBELLE","LONDERZEEL","Weekend","Continuous","23:30","04:30","L53/60 Dendermonde:  indienstname PLP (masterplan ETCS)\r\nWE3/3\r\ntussen de weekends zijn er beperkingen  in de versporingen (meerdere wissels blijven geklauwd na WE1)\r\n+\r\nIDS - ETCS \r\nETCS_IL-SMI_NW_L53 FDR-B9\r\n\r\n\r\n*R6 06.00u - geen CBP L53","CTL","Medium"," "," ",57597]
["2024-05-31","2024-06-03","NW",2,"60","A+B","OPWIJK","DENDERMONDE","Weekend","Continuous","23:30","04:30","Linked to coupure nr 57597 on line 53 tracks(s) A+B from SCHELLEBELLE to LONDERZEEL: L53/60 Dendermonde:  indienstname PLP (masterplan ETCS)\r\nWE3/3\r\ntussen de weekends zijn er beperkingen  in de versporingen (meerdere wissels blijven geklauwd na WE1)\r\n+","CTL","Medium"," "," ",57597]
["2024-05-31","2024-06-03","NW",3,"219","S","GENT-KLUIZENDOK-ZUID","GENT-KLUIZENDOK-ZUID","Weekend","Continuous","22:00","06:00","Kluizendok Zuid, plaatsen wissel 701+702\r\nBD tss sein G-Q.13 tot doodspoor kluizendok zuid","CTL","Medium"," ","Info Racc",60732]
["2024-05-31","2024-06-03","NW",3,"59A","S","SINT-NIKLAAS","SINT-NIKLAAS-OOST","Weekend","Continuous","22:00","04:20","Vernieuwen wissels 27M-28M-29M\r\n\r\nGevallen 22871-22873-22875 van toepassing.","CTL","Medium","Geen verkeer mogelijk naar bundel Sint Niklaas Oost."," ",60562]
["2024-05-31","2024-06-03","SE",1,"130/1","A+B","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Weekend","Continuous","23:30","06:00","Linked to coupure nr 49894 on line 144 tracks(s) A+B from GEMBLOUX to JEMEPPE-SUR-SAMBRE: Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 2/4 (AS 19BQ, 18Q)","CTL","Medium"," ","Info Racc : raccordement inaccessible",49894]
["2024-05-31","2024-06-03","SE",1,"144","A+B","GEMBLOUX","JEMEPPE-SUR-SAMBRE","Weekend","Continuous","23:30","06:00","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 2/4 (AS 19BQ, 18Q)","CTL","Medium","ART de stabilisation VA à 60 km/h (longueur 110m, perte de temps HKV 0.44min, HKM 1.64min)\r\nDate Début : fin du WE 2/4\r\nDate Fin : fin du WE 4/4","Info Racc : raccordement inaccessible",49894]
["2024-05-31","2024-06-03","SE",2,"130","A+B","JEMEPPE-SUR-SAMBRE","NAMUR","Weekend","Continuous","23:30","05:00","Mise en service \"remontée en vitesse\".","CTL","Medium",null," ",57900]
["2024-05-31","2024-06-03","SE",2,"24/1","A+B","VISE","Y.LONGCHAMPS","Weekend","Night","23:00","05:00","Pose d'une nouvelle liaison - WE caténaire n°1\r\nBourrage de révision, contraintes et finitions\r\nNuits min 06h","CTL","Minor_AdHoc","CTL L24/1 voies A et B\r\nVoie 554 HS\r\nVoie HS entre AS72K et 51AK\r\nNuits min 6h"," ",57880]
["2024-05-31","2024-06-03","SW",1,"124","A+B","LUTTRE","Y.NORD","Weekend","Continuous","23:30","04:40","Aménagement Gare de Luttre : Phase 6-2024\r\nTravaux mur de soutènement - BOA\r\nWeek-end 5/5\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","Voies I, II en gare de Luttre inaccessible en continu"," ",49822]
["2024-06-01","2024-06-02","NE",3,"27M/2","*","ANTWERPEN-NOORD-BUNDEL B1","ANTWERPEN-NOORD-BUNDEL B2","Weekend","Continuous","13:30","22:00","massificatiewerken B1 + B2 (met Hugo Deckers tot zondag 22uur)","CTL","Medium","bundels B1-B2 ontoegankelijk\r\nwissels Hugo Deckers eveneens ontoegankelijk tot zondag 22uur","Info Racc",60838]
["2024-06-01","2024-06-02","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60422]
["2024-06-01","2024-06-02","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60422 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60422]
["2024-06-01","2024-06-02","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60422 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60422]
["2024-06-01","2024-06-02","SE",2,"130","A+B","NAMUR","AUVELAIS","Weekend","Continuous","23:40","14:50","Mini CTL pour maintenance globale  L130  + L130/1 + L144","CTL","Medium",null," ",50427]
["2024-06-01","2024-06-02","SE",2,"130/1","A","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Weekend","Continuous","23:40","14:50","Linked to coupure nr 50427 on line 130 tracks(s) A+B from NAMUR to AUVELAIS: Mini CTL pour maintenance globale  L130  + L130/1 + L144","CTL","Medium"," "," ",50427]
["2024-06-01","2024-06-02","SE",2,"144","A","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Weekend","Continuous","23:40","14:50","Linked to coupure nr 50427 on line 130 tracks(s) A+B from NAMUR to AUVELAIS: Mini CTL pour maintenance globale  L130  + L130/1 + L144","CTL","Medium"," "," ",50427]
["2024-06-01","2024-06-02","SW",2,"96","A+B","Y.SOIGNIES","JURBISE","Weekend","Continuous","06:00","16:00","Maintenance Z4.53 \r\nMise HS P4","CTL","Medium",null,"HKM à adapter",49499]
["2024-06-01","2024-06-02","SW",3,"130","A+B","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Weekend","Continuous","23:40","14:50","Maintenance Z19. 51\r\nMini CTL","CTL","Medium"," "," ",49166]
["2024-06-01","2024-06-03","CE",1,"96","A+B","Y.RUISBROEK","Y.NOORD HALLE","Weekend","Continuous","00:40","04:40","Vernieuwing TB perron Buizingen met kraan. Fase 1 WE 3/3.","CTL","Medium","TLO L96+96E tussen Halle en Ruisbroek."," ",50039]
["2024-06-01","2024-06-03","CE",1,"96E","S","HALLE","LOT","Weekend","Continuous","00:40","04:40","Linked to coupure nr 50039 on line 96 tracks(s) A+B from Y.RUISBROEK to Y.NOORD HALLE: Vernieuwing TB perron Buizingen met kraan. Fase 1 WE 3/3.","CTL","Medium"," "," ",50039]
["2024-06-01","2024-06-03","NE",1,"12","A+B","Y.SINT-MARIABURG","Y.LUCHTBAL","Weekend","Continuous","00:00","04:00","304(statiestraat)+308 (herelectrificatie) oude landen","CTL","Medium","Aan deze werken is een R7 (van 06h00 tot 17h30) gekoppeld op L27A voor het spoorgedeelte Y.Laarsebeek - Y.Schijn!! (58229)"," ",58067]
["2024-06-01","2024-06-03","NE",1,"29","A+B","Y.KRUISBERG","TURNHOUT-BUNDEL","Weekend","Continuous","00:00","04:00","Linked to coupure nr 59200 on line 15 tracks(s) A+B from Y.ALBERTKANAAL to OLEN: ETCS \r\nmeewerken niet mogelijk","CTL","Medium"," "," ",59200]
["2024-06-01","2024-06-03","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58018]
["2024-06-01","2024-06-03","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3+4+5+6+7+8+9","CTL","Medium","Vilvoorde sporen 3+4+5+6+7+8+9"," ",58203]
["2024-06-01","2024-06-03","NW",2,"89","A+B","DENDERLEEUW","ZOTTEGEM","Weekend","Continuous","00:40","04:20","Buitenwerken\r\nvernieuwing SI te FDD-Burst / Burst inbegrepen\r\n+\r\nVernieuwen rails OW 34&36 (Harmelen)\r\n2 aparte weekends (wegens combinatie wegomlegging)","CTL","Medium","in combi met L50A = IC23 niet omleiden wegens capaciteitsprobleem tussen FGSP-FD"," ",57557]
["2024-06-01","2024-06-03","SE",3,"165(1)","A+B","LIBRAMONT","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2x25 kV Recogne - Bertrix + déplacement ZSP","CTL","Medium","nuit sa/di jusque 15 h di + nuit di/lu"," ",47188]
["2024-06-01","2024-06-02","SE",3,"161","A/B","OTTIGNIES","GEMBLOUX","Weekend","Day","08:00","16:00","Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles + 1/2h sas Rhisnes","SAVU","Minor_AdHoc","SAVU alternatif entre 08h00 et 16h00"," ",48951]
["2024-06-02","2024-06-02","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","08:00","18:00","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58229]
["2024-06-02","2024-06-02","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Continuous","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\nwerken tijdens het werkvenster","CTL","Medium"," "," ",59811]
["2024-06-02","2024-06-02","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59990]
["2024-06-02","2024-06-02","NW",3,"202B/1","S","Y.PELIKAAN","ZEEBRUGGE-BUNDEL PELIKAAN","Weekend","Day","06:00","22:00","Omvormen 51AR-51BR-52AR-54R-55R-56R-57R van He-H dmv voorgemonteerde panelen werkveld 3421-31\r\n\r\nR-420934-01","CTL","Minor_AdHoc"," ","Info Racc",60383]
["2024-06-02","2024-06-02","NW",3,"202B/2","S","ZEEBRUGGE-BUNDEL PELIKAAN","Y.EIVOORDE","Weekend","Day","06:00","22:00","Linked to coupure nr 60383 on line 202B/1 tracks(s) S from Y.PELIKAAN to ZEEBRUGGE-BUNDEL PELIKAAN: Omvormen 51AR-51BR-52AR-54R-55R-56R-57R van He-H dmv voorgemonteerde panelen werkveld 3421-31\r\n\r\nR-420934-01","CTL","Minor_AdHoc"," ","Info Racc",60383]
["2024-06-03","2024-06-07","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","Week","Night","23:50","04:30","Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers","CTL","Minor_AdHoc"," "," ",58983]
["2024-06-03","2024-06-07","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59866]
["2024-06-03","2024-06-07","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:10","04:00","weeknachten als fase 3 in map 3","CTL","Minor_AdHoc"," "," ",60199]
["2024-06-03","2024-06-07","NE",3,"35","A+B","HASSELT","Y.HOLSBEEK","Week","Night","23:55","04:00","weeknachten als fase 3","CTL","Minor_AdHoc"," "," ",60205]
["2024-06-03","2024-06-07","NW",3,"122","A+B","ZOTTEGEM","Y.MELLE","Week","Night","23:50","05:10","Vernieuwen rails","CTL","Minor_AdHoc",null,null,57845]
["2024-06-03","2024-06-08","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58483]
["2024-06-03","2024-06-08","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58483 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58483]
["2024-06-03","2024-06-08","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58483 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58483]
["2024-06-03","2024-06-08","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58483 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58483]
["2024-06-03","2024-06-09","CE",1,"96","A","Y.RUISBROEK","Y.NOORD HALLE","AllWeek","Continuous","04:40","04:40","Stabilisatie-BTS Vernieuwing TB perron Buizingen met kraan. Fase 1 WE 3/3.","ART","Minor_AdHoc","BTS"," ",56112]
["2024-06-03","2024-06-16","NW",3,"204","*","GENT-RODENHUIZE","GENT-RODENHUIZEDOK","AllWeek","Continuous","07:00","21:00","Gent Coal Terminal buiten dienst\r\nAW08AK niet in, tot CDS GENT COAL","CTL","High",null,"Info Racc",60505]
["2024-06-04","2024-06-08","NW",3,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw \r\nAfwerking\r\n\r\n(TLO L89 ISM Tom Lannoo CoLT 58591)","CTL","Minor_AdHoc"," "," ",59040]
["2024-06-04","2024-06-08","NW",3,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 59040 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking\r\n\r\n(TLO L89 ISM Tom Lannoo CoLT 58591)","CTL","Minor_AdHoc"," "," ",59040]
["2024-06-04","2024-06-08","NW",3,"89","A+B","DENDERLEEUW","ZOTTEGEM","Week","Night","00:40","04:20","Vernieuwen rails OW 34&36 (Harmelen)\r\n\r\nJonas Van Wesemael werkt mee voor MP FDD","CTL","Minor_AdHoc",null," ",58591]
["2024-06-06","2024-06-06","NE",3,"27","A","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL","Week","Day","10:00","15:00","onderhoud SIG DOES","SAVU","Minor_AdHoc",null," ",59724]
["2024-06-06","2024-06-08","SW",2,"124A","B","LUTTRE","ROUX","Week","Continuous","06:00","06:00","Ré-électrification de la Gare de Luttre\r\nTravaux de pose caténaires L117 - L124A voie B\r\nentre R41/4 et R42/4","SAVU","Minor_AdHoc","Coupure de L124A voie B + Voie IV Gare de Luttre\r\nK-E.20 à DX-F.20\r\nMise hors tension des Cas TII : 27828, 27830,27832"," ",49311]
["2024-06-07","2024-06-09","SE",2,"162","A+B","ROCHEFORT-JEMELLE","HAVERSIN","Weekend","Continuous","23:55","16:00","Linked to coupure nr 40390 on line 43 tracks(s) A+B from BOMAL to MARLOIE: Mise en service PLP de la gare de Marloie.","CTL","Medium"," ","InfoRacc",40390]
["2024-06-07","2024-06-09","SE",2,"43","A+B","BOMAL","MARLOIE","Weekend","Continuous","23:55","16:00","Mise en service PLP de la gare de Marloie.","CTL","Medium","CTL L43 Bomal - Marloie + CTL L162 Jemelle - Haversin R5 23:55 - R7 16:00\r\n+ SAVU L162 Jemelle - Haversin  R7 16:00 - R1 6:00","InfoRacc",40390]
["2024-06-07","2024-06-09","SE",3,"125A","*","KINKEMPOIS-BLOCK 2","KINKEMPOIS-RELAIS","Weekend","Continuous","23:00","05:00","Z.26.41 P4+ - Maintenance AI 41.","Autre","Minor_AdHoc","Accès atelier doit se faire par la réception : adaptation rames à vide"," ",57883]
["2024-06-07","2024-06-09","SW",2,"112","A/B","MARCHIENNE-AU-PONT","PIETON","Weekend","Continuous","23:30","16:00","Tir de fils de contacts avec autorail","SAVU","Minor_AdHoc"," "," ",53200]
["2024-06-07","2024-06-10","CE",1,"96","A","BRUXELLES-MIDI","Y.NOORD HALLE","Weekend","Continuous","23:40","04:30","Vernieuwen sp A L96: afwerkingsWE 2/2 Fase 2","SAVU","Minor_AdHoc","DOES L96 tussen FBMZ en Halle.\r\nBijkomend tijdens de nachten sp B L96 + AL96N"," ",50045]
["2024-06-07","2024-06-10","CE",1,"96","B","Y.NOORD HALLE","Y.RUISBROEK","Weekend","Continuous","23:40","04:30","Linked to coupure nr 50045 on line 96 tracks(s) A from BRUXELLES-MIDI to Y.NOORD HALLE: Vernieuwen sp A L96: afwerkingsWE 2/2 Fase 2","SAVU","Minor_AdHoc"," "," ",50045]
["2024-06-07","2024-06-10","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59571]
["2024-06-07","2024-06-10","CE",2,"96B","*","FOREST-VOITURES-QUAI SERVICE","FOREST-MIDI-VOIES 920/926","Weekend","Continuous","22:30","04:00","Onderhoudswerken volgens onderhoudskalender Area CE, zone FBKI_14, bundel B en C","Autre","Minor_AdHoc","Bundel B en C buiten dienst voor onderhoudswerken"," ",58632]
["2024-06-07","2024-06-10","NE",3,"11A","A+B","ANTWERPEN-D.S.-ZANDVLIET","ANTWERPEN-D.S.-ZANDVLIET","AllWeek","Continuous","06:00","18:00","massificatiewerken","CTL","Medium","geen toegang tot bundels Zandvliet G+B en Stabroek A en Lillo"," ",60818]
["2024-06-07","2024-06-10","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59907]
["2024-06-07","2024-06-10","NE",3,"29","A+B","Y.KRUISBERG","TURNHOUT","Weekend","Continuous","23:00","04:40","omvormen 50 HZ SK naar TFSK\r\naanpassen treindetectiesysteem (moet voor 2025)\r\nvernieuwing signalisatie overwegen\r\nomvorming moet gebeuren voor uitrol ETCS L29\r\n\r\nmeewerken NIET mogelijk","CTL","Medium","alternatief E3421"," ",60019]
["2024-06-07","2024-06-10","NW",3,"122","A+B","Y.MELLE","ZOTTEGEM","Weekend","Continuous","23:50","05:00","Vernieuwen rails\r\nZottegem en Y Melle VRIJ\r\nL50A4 inbegrepen","CTL","Medium",null,null,57846]
["2024-06-07","2024-06-10","NW",3,"50A/4","A+B","Y.MELLE","Y.MEULEWIJK","Weekend","Continuous","23:50","05:00","Linked to coupure nr 57846 on line 122 tracks(s) A+B from Y.MELLE to ZOTTEGEM: Vernieuwen rails\r\nZottegem en Y Melle VRIJ\r\nL50A4 inbegrepen","CTL","Medium"," ",null,57846]
["2024-06-07","2024-06-10","NW",3,"59A","*","SINT-NIKLAAS-OOST","SINT-NIKLAAS-OOST","Weekend","Continuous","22:00","04:20","Vernieuwen wissels 23M-24M-25M\r\n\r\nGevallen  22873-22875\r\n\r\nSporen 505 tot en met 514 in bundel Sint -Niklaas Oost buiten dienst.","Autre","Minor_AdHoc"," "," ",60564]
["2024-06-07","2024-06-10","SE",1,"130/1","A+B","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Weekend","Continuous","23:30","06:00","Linked to coupure nr 49895 on line 144 tracks(s) A+B from GEMBLOUX to JEMEPPE-SUR-SAMBRE: Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 3/4 (AS 19AQ)","CTL","Medium"," ","Info Racc : raccordement inaccessible",49895]
["2024-06-07","2024-06-10","SE",1,"144","A+B","GEMBLOUX","JEMEPPE-SUR-SAMBRE","Weekend","Continuous","23:30","06:00","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 3/4 (AS 19AQ)","CTL","Medium","ART de stabilisation VA à 60 km/h (longueur 110m, perte de temps HKV 0.44min, HKM 1.64min)\r\nDate Début : fin du WE 3/4\r\nDate Fin : fin du WE 4/4","Info Racc : raccordement inaccessible",49895]
["2024-06-07","2024-06-10","SE",2,"24/1","A+B","VISE","Y.LONGCHAMPS","Weekend","Night","23:00","05:00","Pose d'une nouvelle liaison - WE caténaire n°2\r\nBourrage de révision, contraintes et finitions\r\nNuits min 06h","CTL","Minor_AdHoc","CTL L24/1 voies A et B\r\nVoie 554 HS\r\nVoie HS entre AS72K et 51AK\r\nNuits min 6h"," ",57882]
["2024-06-07","2024-06-10","SW",1,"96","A+B","BRAINE-LE-COMTE","HALLE","Weekend","Continuous","22:30","05:00","Renouvellement AS 07D+CDS 246, 14D,15D,16D,18D, 32D et 33D  Braine-le-Comte\r\nMaintenance Z1.53 (P4)","CTL","Medium","Faisceau indisponible 4 semaines\r\nART 2 minutes","HKM à adapter",38663]
["2024-06-07","2024-06-10","SW",3,"140","A+B","MARCINELLE","FLEURUS","Weekend","Continuous","23:40","05:00","Maintenance Z4. 51  P4+\r\n+ Renouvellement complet des PN","CTL","Medium",null,"HKM à adapter",49119]
["2024-06-07","2024-07-01","SW",1,"96","*","BRAINE-LE-COMTE","BRAINE-LE-COMTE","AllWeek","Continuous","22:30","05:00","Renouvellement AS 07D+CDS 246, 14D,15D,16D,18D, 32D et 33D  Braine-le-Comte","Autre","Minor_AdHoc","Faisceau indisponible 4 semaines"," ",9867]
["2024-06-07","2024-06-10","CE",1,"161","A/B","WATERMAEL","BAKENBOS","Weekend","Continuous","23:30","04:50","WE SAVU RER Watermael-Bakenbos","SAVU_CTRL","Minor_AdHoc","ART à définir - maximum 2'"," ",49255]
["2024-06-07","2024-06-10","SE",2,"154","A/B","LUSTIN","DINANT","Weekend","Continuous","23:00","05:00","Entretien AS , traitement zone boueuse","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 10/06 au 13/06 (fin probable)"," ",57692]
["2024-06-08","2024-06-10","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","Weekend","Continuous","01:00","04:00","Afwerkingsweekend 1/3 Vernieuwing Y.Noord-Driehoek-Aarschot +vernieuwen duikers\r\n\r\n\r\nDossier: 2024 - L16 Y.Oost Driehoek Aarschot-Heist od Berg - 211109","CTL","Medium"," "," ",58984]
["2024-06-08","2024-06-14","NE",3,"16","A+B","Y.NAZARETH","HEIST-OP-DEN-BERG","AllWeek","Night","23:50","04:30","vernieuwen overwegen strail\r\n\r\nnog te bepalen of werken doorgaan !!!","CTL","Minor_AdHoc"," "," ",60232]
["2024-06-08","2024-06-10","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58984 on line 16 tracks(s) A+B from Y.OOST DRIEHOEK AARSCHOT to HEIST-OP-DEN-BERG: Afwerkingsweekend 1/3 Vernieuwing Y.Noord-Driehoek-Aarschot +vernieuwen duikers\r\n\r\n\r\nDossier: 2024 - L16 Y.Oost Driehoek Aarschot-Heist od Berg - 211","CTL","Medium"," "," ",58984]
["2024-06-08","2024-06-08","SE",3,"139","A/B","WAVRE","OTTIGNIES","Weekend","Day","08:00","16:00","Visites des postes+ maintenances infrastructure et contrôles","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48870]
["2024-06-08","2024-06-09","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61583]
["2024-06-08","2024-06-09","NW",3,"75","A","WAREGEM","KORTRIJK","Weekend","Night","22:15","06:00","vervangen rijdraad SP A - JVO\r\nSP B bijkomend tijdens de nacht 00.20-05.15","SAVU_CTRL","Minor_AdHoc",null," ",58604]
["2024-06-08","2024-06-09","SW",2,"97","A+B","MONS","SAINT-GHISLAIN","Weekend","Continuous","06:00","17:00","Maintenance Z12.53 P4","CTL","Medium",null," ",49774]
["2024-06-08","2024-06-10","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58019]
["2024-06-08","2024-06-10","NE",2,"25","A+B","Y.ABEELSTRAAT","MECHELEN","Weekend","Continuous","00:00","04:00","Vierendeelbrug over de Vaart \r\nPERRONS mechelen INCLUSIEF \r\nL25N open","CTL","Medium","perrons mechelen inbegrepen"," ",58167]
["2024-06-08","2024-06-10","NE",2,"27","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","afbraak trapkooien perrons 3+4 te Vilvoorde\r\n\r\nVilvoorde sporen 3+4+5+6+7+8+9","CTL","Medium","Vilvoorde sporen 3+4+5+6+7+8+9"," ",58204]
["2024-06-08","2024-06-10","NE",2,"53","A+B","Y.HEIKE","MECHELEN","Weekend","Continuous","00:00","04:00","ETCS Mechelen Londerzeel\r\nmeewerken niet mogelijk \r\nCTL spoor A+B","CTL","Medium"," "," ",59361]
["2024-06-08","2024-06-10","NW",2,"204","A+B","Y.BOMA","LIJN 204-KRUISING LIJN 58/2","Weekend","Night","00:10","04:00","Linked to coupure nr 57594 on line 58/2 tracks(s) A+B from GENT-ZEEHAVEN to Y.MUIDE: CoLT 57593: L204 Gent-Zeehaven - Gent-Noord:  indienstname PLP (masterplan ETCS) testritten op zondag in overleg met regelaar\r\nCoLT 57594: Tijdens de nacht uitbereiding","CTL","Minor_AdHoc"," ","Info Racc.",57594]
["2024-06-08","2024-06-10","NW",2,"204","A+B","LIJN 204-KRUISING LIJN 58/2","GENT-NOORD","Weekend","Continuous","00:10","04:00","CoLT 57593: L204 Gent-Zeehaven - Gent-Noord:  indienstname PLP (masterplan ETCS) testritten op zondag in overleg met regelaar\r\nCoLT 57594: Tijdens de nacht uitbereiding buitendienststelling met kruising tussen L58/2 en L204 tot Y Boma (tot sein DX-E.13 ","CTL","Medium",null,"Info Racc.",57593]
["2024-06-08","2024-06-10","NW",2,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 59006 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",59006]
["2024-06-08","2024-06-10","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)","CTL","Medium"," "," ",59006]
["2024-06-08","2024-06-10","NW",2,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 59006 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",59006]
["2024-06-08","2024-06-10","NW",2,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Night","00:10","04:00","CoLT 57593: L204 Gent-Zeehaven - Gent-Noord:  indienstname PLP (masterplan ETCS) testritten op zondag in overleg met regelaar\r\nCoLT 57594: Tijdens de nacht uitbereiding buitendienststelling met kruising tussen L58/2 en L204 tot Y Boma (tot sein DX-E.13 ","CTL","Minor_AdHoc",null,"Info Racc.",57594]
["2024-06-08","2024-06-10","NW",3,"60","A+B","JETTE","DENDERMONDE","Weekend","Continuous","00:10","05:10","R409837\r\nOnderhoud - EDW","CTL","Medium"," ",null,59210]
["2024-06-08","2024-06-09","SE",3,"161","A/B","NAMUR","RHISNES-SAS","Weekend","Day","08:00","16:00","Visite périodique + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","Savu alternatif VA/VB , de 8h à 16 h"," ",49209]
["2024-06-09","2024-06-09","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61611]
["2024-06-09","2024-06-09","NW",3,"202B","S","Y.EIVOORDE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Day","10:00","18:00","R-419007-01\r\n\r\nonderhoud werkveld 3421-36\r\n\r\nAW 72R-73R-74R-74XR-75R-80R-82R-83R\r\n\r\nBundel Ramskapelle niet bereikbaar","CTL","Minor_AdHoc"," ","Info Racc.",60369]
["2024-06-09","2024-06-09","SE",3,"139","A/B","SINT-JORIS-WEERT","WAVRE","Weekend","Day","08:00","16:00","Visites des postes - maintenances diverses et révisions","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48879]
["2024-06-10","2024-06-14","NE",1,"16","A+B","Y.NOORD DRIEHOEK AARSCHOT","Y.OOST DRIEHOEK AARSCHOT","Week","Night","23:00","04:50","vervolg vernieuwing Y noord aarschot +vernieuwen duikers","CTL","Minor_AdHoc",null," ",58451]
["2024-06-10","2024-06-14","NE",1,"16","A+B","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG","Week","Night","23:50","04:30","Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers","CTL","Minor_AdHoc"," "," ",58985]
["2024-06-10","2024-06-14","NE",1,"16/1","A+B","Y.ZUID DRIEHOEK AARSCHOT","Y.NOORD DRIEHOEK AARSCHOT","Week","Night","23:50","04:30","Linked to coupure nr 58985 on line 16 tracks(s) A+B from Y.OOST DRIEHOEK AARSCHOT to HEIST-OP-DEN-BERG: Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers","CTL","Minor_AdHoc"," "," ",58985]
["2024-06-10","2024-06-14","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59867]
["2024-06-10","2024-06-14","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:10","04:00","weeknachten als fase 3 in map 3","CTL","Minor_AdHoc"," "," ",60200]
["2024-06-10","2024-06-14","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:50","04:30","onderhoud\r\n+\r\n\r\nafschaffen 7 overwegen Bilzen (COLT 59827)","CTL","Minor_AdHoc","te bepalen"," ",59736]
["2024-06-10","2024-06-14","NW",3,"122","A+B","ZOTTEGEM","Y.MELLE","Week","Night","23:50","05:10","Vernieuwen rails","CTL","Minor_AdHoc",null,null,57847]
["2024-06-10","2024-06-14","SW",2,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Week","Night","22:30","04:10","Renouvellement AS Y. La Sambre\r\nTravaux préparatoires caténaire\r\n+ Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux préparatoires caténaire (poteaux + traverses)","CTL","Minor_AdHoc",null," ",52989]
["2024-06-10","2024-06-14","SW",2,"94","A+B","HALLE","ENGHIEN","Week","Night","23:10","04:40","Nuits de préparation - Construction d'un CSV - PN18","CTL","Minor_AdHoc","CTL de nuits de semaine"," ",55575]
["2024-06-10","2024-06-15","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Week","Night","23:55","05:20","Omvorming Y Jette Rooster R: voorbereidende nachten","CTL","Minor_AdHoc","TLO L50 + L60"," ",50031]
["2024-06-10","2024-06-15","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Linked to coupure nr 50031 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Omvorming Y Jette Rooster R: voorbereidende nachten","CTL","Minor_AdHoc"," "," ",50031]
["2024-06-10","2024-06-15","NE",3,"35","A+B","HASSELT","Y.ZUID DRIEHOEK AARSCHOT","Week","Night","23:30","04:30","onderhoud arr 24\r\n+\r\nvervolg vernieuwingen Y Noord Aarschot ( colt 58252)","CTL","Minor_AdHoc","alternatief E2221-E2473-E2622"," ",60021]
["2024-06-10","2024-06-24","SW",1,"75","*","FRONT. FLANDRE-WALLONIE L75","MOUSCRON","AllWeek","Continuous","06:00","05:00","Gare de Mouscron : Renouvellement AS 12AK - 12BK - 11BK/11AK","Autre","Minor_AdHoc","1) CTL 7jours Voies I, II et III + weekend voie 4 HS en complément (Renouvellement) - Cas 28661 et 28662 restent sous tension\r\n2) CTL 1WE voies I, II, III et IV (finitions) - Cas 28661 et 28662 restent sous tension\r\nART stabilisation 40/60 : du 16/06 au"," ",48695]
["2024-06-11","2024-06-15","NW",3,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw \r\nAfwerking","CTL","Minor_AdHoc"," "," ",59041]
["2024-06-11","2024-06-15","NW",3,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 59041 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking","CTL","Minor_AdHoc"," "," ",59041]
["2024-06-11","2024-06-15","NW",3,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 59041 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking","SAVU","Minor_AdHoc"," "," ",59041]
["2024-06-12","2024-06-12","NE",3,"27","B","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL","Week","Day","10:00","15:00","onderhoud SIG DOES","SAVU","Minor_AdHoc",null," ",59725]
["2024-06-14","2024-06-17","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: voorbereidende werken","CTL","Medium","TLO L161/1"," ",59572]
["2024-06-14","2024-06-17","NE",1,"35","A+B","Y.ZUID DRIEHOEK AARSCHOT","DIEST","Weekend","Continuous","23:40","04:30","vervolg vernieuwingen Y Noord Aarschot","CTL","Medium","alternatief E2473-E2622"," ",58253]
["2024-06-14","2024-06-17","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:30","05:00","vernieuwen Muizen rooster T \r\n(samen met L27B)\r\n\r\nsecundair fietstunnel Willendries en ONB Willendriesbeek","CTL","Medium"," "," ",58334]
["2024-06-14","2024-06-17","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59908]
["2024-06-14","2024-06-17","NW",2,"217","S","Y.NOORD EVERSTEIN","EVERGEM-OVERDAM","Weekend","Continuous","23:50","05:00","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Medium"," ","Info Racc",58521]
["2024-06-14","2024-06-17","NW",2,"55A","S","Y.RINGVAART","LANGERBRUGGE","Weekend","Continuous","23:50","05:00","Linked to coupure nr 58521 on line 217 tracks(s) S from Y.NOORD EVERSTEIN to EVERGEM-OVERDAM: 227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Medium"," ","Info Racc",58521]
["2024-06-14","2024-06-17","NW",2,"86","A+B","GAVERE-ASPER","OUDENAARDE","Weekend","Continuous","23:40","05:00","Buitenwerken \r\nVernieuwen seininrichting Gavere-Asper - Oudenaarde\r\nBundel Oudenaarde inbegrepen\r\nRooster Oudenaarde inbegrepen tot aan seinen van perron III-IV-V, perrons zelf blijven beschikbaar\r\nRooster L89 blijft vrij","CTL","Medium",null," ",57566]
["2024-06-14","2024-06-17","NW",3,"122","A+B","Y.MELLE","ZOTTEGEM","Weekend","Continuous","23:50","05:00","Vernieuwen rails\r\nZottegem en Y Melle VRIJ\r\nL50A4 inbegrepen","CTL","Medium",null,null,57848]
["2024-06-14","2024-06-17","NW",3,"50A/4","A+B","Y.MELLE","Y.MEULEWIJK","Weekend","Continuous","23:50","05:00","Linked to coupure nr 57848 on line 122 tracks(s) A+B from Y.MELLE to ZOTTEGEM: Vernieuwen rails\r\nZottegem en Y Melle VRIJ\r\nL50A4 inbegrepen","CTL","Medium"," ",null,57848]
["2024-06-14","2024-06-17","NW",3,"59A","*","SINT-NIKLAAS-OOST","SINT-NIKLAAS-OOST","Weekend","Continuous","22:00","04:20","Vernieuwen wissels 21M-22M\r\n\r\nGevallen  22873-22875\r\n\r\nSporen 505 tot en met 514 in bundel Sint -Niklaas Oost buiten dienst.","Autre","Minor_AdHoc"," "," ",60566]
["2024-06-14","2024-06-17","SW",1,"117","A","BRAINE-LE-COMTE","BRAINE-LE-COMTE","Weekend","Continuous","22:30","05:00","Linked to coupure nr 38664 on line 96 tracks(s) A from BRAINE-LE-COMTE to HENNUYERES: Renouvellement AS 07D+CDS 246, 14D,15D,16D,18D, 32D et 33D  Braine-le-Comte","SAVU","Minor_AdHoc"," "," ",38664]
["2024-06-14","2024-06-17","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 min","HKM à adapter",48628]
["2024-06-14","2024-06-17","SW",1,"96","A","BRAINE-LE-COMTE","HENNUYERES","Weekend","Continuous","22:30","05:00","Renouvellement AS 07D+CDS 246, 14D,15D,16D,18D, 32D et 33D  Braine-le-Comte","SAVU","Minor_AdHoc","Faisceau indisponible 4 semaines\r\nVoie 229 inaccessible, mise HS et HT\r\nPlus portion de voie entre le 08D et la voie 229\r\nART 2 min"," ",38664]
["2024-06-14","2024-06-17","SW",2,"94","A/B","HALLE","SAINTES","Weekend","Continuous","23:10","05:00","Construction d'un CSV - PN18","SAVU","Minor_AdHoc","SAVU de préparation"," ",55573]
["2024-06-14","2024-07-15","SW",2,"94","A+B","HALLE","ENGHIEN","AllWeek","Continuous","23:10","04:20","ART 2 min \r\nConstruction d'un CSV - PN18","ART","Minor_AdHoc","ART pendant 21 jours après le WE"," ",59114]
["2024-06-14","2024-06-17","SE",1,"161","A+B","BRUXELLES-LUXEMBOURG","OTTIGNIES","Weekend","Continuous","23:30","04:50","WE CTL RER Watermael - Ottignies","CTL","Medium","ART à définir, maximum 2'"," ",49262]
["2024-06-15","2024-06-16","NE",3,"27M/4","*","ANTWERPEN-NOORD-BUNDEL C2","ANTWERPEN-NOORD-BUNDEL C3","Weekend","Continuous","13:30","22:00","massificatiewerken C2/C3","CTL","Medium","bundels C2-3 ontoegankelijk\r\n(omloopspoor lijn 27A/3 reeds terug in dienst op maandag om 2u)","Info Racc",60842]
["2024-06-15","2024-06-16","SE",2,"24","A+B","VISE-HAUT","MONTZEN-FRONTIERE","Weekend","Continuous","08:00","21:00","Entretien manuel et mécanisés des AW de Y. Berneau, Fourons, Rémersdael, Montzen, Botzelaer\r\nEntretien manuel et mécanisés de la voie courante + Tunnel de Veurs","CTL","Medium","Pas de circulation possible entre Visé et DB\r\nPas de ciculation entre Longchamps vers DB"," ",55965]
["2024-06-15","2024-06-16","SE",2,"24/1","A+B","Y.LONGCHAMPS","Y.BERNEAU","Weekend","Continuous","08:00","21:00","Linked to coupure nr 55965 on line 24 tracks(s) A+B from VISE-HAUT to MONTZEN-FRONTIERE: Entretien manuel et mécanisés des AW de Y. Berneau, Fourons, Rémersdael, Montzen, Botzelaer\r\nEntretien manuel et mécanisés de la voie courante + Tunnel de Veurs","CTL","Medium"," "," ",55965]
["2024-06-15","2024-06-16","SE",3,"165","A+B","VIRTON","AUBANGE","Weekend","Continuous","08:00","16:00","Pose de caniveaux drainant (boueux)","CTL","Medium",null," ",57838]
["2024-06-15","2024-06-16","SW",1,"130","A+B","AUVELAIS","CHATELET-GRIL OUEST","Weekend","Continuous","06:00","17:00","Maintenance Z15.51\r\nP4+","CTL","Medium"," ","HKM à adapter",48834]
["2024-06-15","2024-06-16","SW",3,"116","A+B","MANAGE","LA LOUVIERE-GARE INDUSTRIELLE","Weekend","Continuous","06:00","22:00","Maintenance Z10.52\r\nMise HS P4 - Zone 10 AI52\r\nRq 333 : demande SNCB replan le WE 26 ald 24 (possible WE 25 mais simultané Z9.52)","CTL","Medium"," ","InfoRacc",49152]
["2024-06-15","2024-06-16","SW",3,"116/1","A+B","Y.BOIS-D'HAINE","Y.FAMILLEUREUX","Weekend","Continuous","06:00","22:00","Linked to coupure nr 49152 on line 116 tracks(s) A+B from MANAGE to LA LOUVIERE-GARE INDUSTRIELLE: Maintenance Z10.52\r\nMise HS P4 - Zone 10 AI52\r\nRq 333 : demande SNCB replan le WE 26 ald 24 (possible WE 25 mais simultané Z9.52)","CTL","Medium"," ","InfoRacc",49152]
["2024-06-15","2024-06-17","CE",1,"96","A+B","Y.RUISBROEK","Y.NOORD HALLE","Weekend","Continuous","00:40","04:40","Vernieuwen sp A L96: afwerkingsWE Fase 3","CTL","Medium","TLO L96+96E tussen Halle en Ruisbroek."," ",50046]
["2024-06-15","2024-06-17","CE",1,"96E","S","HALLE","LOT","Weekend","Continuous","00:40","04:40","Linked to coupure nr 50046 on line 96 tracks(s) A+B from Y.RUISBROEK to Y.NOORD HALLE: Vernieuwen sp A L96: afwerkingsWE Fase 3","CTL","Medium"," "," ",50046]
["2024-06-15","2024-06-17","CE",2,"27D","A+B","SCHAERBEEK","SCHAERBEEK-GROUPE R","Weekend","Continuous","00:20","04:00","Onderhoudszone FSR_14/MTB_10 Area CE volgens onderhoudskalender 2023.\r\nOnderhoudswerken L27D en L27D/4 vanaf de perrons Schaarbeek tot en met de kopwissels van Groep R","CTL","Medium","Groep R en G en atelier NMBS enkel bereikbaar via Y Groep G en lokale manoeuvres.",null,58571]
["2024-06-15","2024-06-17","NE",1,"27B","A+B","Y.PRINSENHOEK","Y.MUIZEN","Weekend","Continuous","00:00","04:00","vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58352]
["2024-06-15","2024-06-17","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","06:00","04:00","Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nVoorbereidingsweekend 1/3\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINAL","CTL","Medium"," "," ",53691]
["2024-06-15","2024-06-17","NE",1,"53","A+B","Y.HEVER","MUIZEN","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58352 on line 27B tracks(s) A+B from Y.PRINSENHOEK to Y.MUIZEN: vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58352]
["2024-06-15","2024-06-17","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58020]
["2024-06-15","2024-06-17","NE",2,"53","A+B","Y.HEIKE","MECHELEN","Weekend","Continuous","00:00","04:00","ETCS Mechelen Londerzeel\r\nmeewerken niet mogelijk \r\nCTL spoor A+B","CTL","Medium"," "," ",59367]
["2024-06-15","2024-06-17","NE",3,"12","A+B","Y.LUCHTBAL","Y.SINT-MARIABURG","Weekend","Continuous","06:00","04:10","Oude landen project 308+304","CTL","Medium","Aan deze werken is een R7 (van 06h00 tot 17h30) gekoppeld op L27A voor het spoorgedeelte Y.Laarsebeek - Y.Schijn!! (58662)"," ",58641]
["2024-06-15","2024-06-17","NW",1,"50","A+B","Y.WEST DRIEHOEK LEDEBERG","SCHELLEBELLE","Weekend","Continuous","00:40","04:00","Onderhoud Y Melle + Wissels Rooster S L50+50E\r\n\r\nSchellebelle blijft toegankelijk\r\nInrit Merelbeke kant Gent vrij","CTL","Medium",null," ",52976]
["2024-06-15","2024-06-17","NW",1,"50E","A+B","Y.MELLE-WEST","MERELBEKE","Weekend","Continuous","00:40","04:00","Linked to coupure nr 52976 on line 50 tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to SCHELLEBELLE: Onderhoud Y Melle + Wissels Rooster S L50+50E\r\n\r\nSchellebelle blijft toegankelijk\r\nInrit Merelbeke kant Gent vrij","CTL","Medium"," "," ",52976]
["2024-06-15","2024-06-17","SW",3,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Weekend","Continuous","06:00","04:15","Travaux Signalisation PN 107 108 109 114\r\n+ ETCS LS Hourpes-Erquelinnes","CTL","Medium"," "," ",61814]
["2024-06-15","2024-06-16","SE",3,"161","A/B","BAKENBOS","OTTIGNIES","Weekend","Day","08:00","16:00","Visite voies A/B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 08h00 et 16h00 le samedi et le dimanche,  avec adaptations trains"," ",48910]
["2024-06-15","2024-06-17","SE",3,"154","A+B","JAMBES","Y.NEFFE","Weekend","Night","23:30","05:00","Travaux préparatoires pour passage futur en EBP-PLP : gare d'Yvoir + gare de Dinant + BA (Dinant-Anseremme) + Anseremme.","CTL","Minor_AdHoc","Nuit sam/dim 23h30 - 5h30\r\nNuit dim/lun 23h30 - 4h20"," ",57897]
["2024-06-16","2024-06-16","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","06:00","17:40","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58662]
["2024-06-16","2024-06-16","NW",2,"50A","A+B","OOSTENDE","Y.OOSTKAMP","Weekend","Night","00:45","06:00","IDS ETCS L2-IL_NW_P005_L50A_Oostende - Brugge_ETCS\r\nIDS ETCS L2-IL_NW_P013_L51_Brugge - Zeebrugge_ETCS","CTL","Minor_AdHoc"," ","Info Racc.",50487]
["2024-06-16","2024-06-16","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE","Weekend","Night","00:45","06:00","Linked to coupure nr 50487 on line 50A tracks(s) A+B from OOSTENDE to Y.OOSTKAMP: IDS ETCS L2-IL_NW_P005_L50A_Oostende - Brugge_ETCS\r\nIDS ETCS L2-IL_NW_P013_L51_Brugge - Zeebrugge_ETCS","CTL","Minor_AdHoc"," ","Info Racc.",50487]
["2024-06-16","2024-06-16","NW",2,"51","A+B","BRUGGE","BLANKENBERGE","Weekend","Night","00:45","06:00","Linked to coupure nr 50487 on line 50A tracks(s) A+B from OOSTENDE to Y.OOSTKAMP: IDS ETCS L2-IL_NW_P005_L50A_Oostende - Brugge_ETCS\r\nIDS ETCS L2-IL_NW_P013_L51_Brugge - Zeebrugge_ETCS","CTL","Minor_AdHoc"," ","Info Racc.",50487]
["2024-06-16","2024-06-16","NW",2,"51A","A+B","Y.BLAUWE TOREN","ZEEBRUGGE-VOORHAVEN-WEST","Weekend","Night","00:45","06:00","Linked to coupure nr 50487 on line 50A tracks(s) A+B from OOSTENDE to Y.OOSTKAMP: IDS ETCS L2-IL_NW_P005_L50A_Oostende - Brugge_ETCS\r\nIDS ETCS L2-IL_NW_P013_L51_Brugge - Zeebrugge_ETCS","CTL","Minor_AdHoc"," ","Info Racc.",50487]
["2024-06-16","2024-06-16","NW",2,"51A/1","A+B","ZEEBRUGGE-ROOSTER H","ZEEBRUGGE-DORP","Weekend","Night","00:45","06:00","Linked to coupure nr 50487 on line 50A tracks(s) A+B from OOSTENDE to Y.OOSTKAMP: IDS ETCS L2-IL_NW_P005_L50A_Oostende - Brugge_ETCS\r\nIDS ETCS L2-IL_NW_P013_L51_Brugge - Zeebrugge_ETCS","CTL","Minor_AdHoc"," ","Info Racc.",50487]
["2024-06-16","2024-06-16","NW",2,"51B","A+B","Y.DUDZELE","KNOKKE","Weekend","Night","00:45","06:00","Linked to coupure nr 50487 on line 50A tracks(s) A+B from OOSTENDE to Y.OOSTKAMP: IDS ETCS L2-IL_NW_P005_L50A_Oostende - Brugge_ETCS\r\nIDS ETCS L2-IL_NW_P013_L51_Brugge - Zeebrugge_ETCS","CTL","Minor_AdHoc"," ","Info Racc.",50487]
["2024-06-16","2024-06-16","NW",2,"51B/1","A+B","Y.TER DOEST","Y.BOUDEWIJNKANAAL","Weekend","Night","00:45","06:00","Linked to coupure nr 50487 on line 50A tracks(s) A+B from OOSTENDE to Y.OOSTKAMP: IDS ETCS L2-IL_NW_P005_L50A_Oostende - Brugge_ETCS\r\nIDS ETCS L2-IL_NW_P013_L51_Brugge - Zeebrugge_ETCS","CTL","Minor_AdHoc"," ","Info Racc.",50487]
["2024-06-16","2024-06-16","NW",2,"66","A+B","BRUGGE","ZEDELGEM","Weekend","Night","00:45","06:00","Linked to coupure nr 50487 on line 50A tracks(s) A+B from OOSTENDE to Y.OOSTKAMP: IDS ETCS L2-IL_NW_P005_L50A_Oostende - Brugge_ETCS\r\nIDS ETCS L2-IL_NW_P013_L51_Brugge - Zeebrugge_ETCS","CTL","Minor_AdHoc"," ","Info Racc.",50487]
["2024-06-16","2024-06-17","NW",2,"75","*","KORTRIJK","KORTRIJK","Weekend","Continuous","01:00","04:30","Juni 2024: spoor I en II buiten dienst voor 24u","Autre","Minor_AdHoc"," "," ",58531]
["2024-06-17","2024-06-21","NE",1,"16","A+B","Y.NOORD DRIEHOEK AARSCHOT","Y.OOST DRIEHOEK AARSCHOT","Week","Night","23:00","04:50","vervolg vernieuwing Y noord aarschot\r\n\r\n1WE L16 tussen vertakkingen + weeknachten ervoor en erna (WE incl L16+35)\r\n3WE L16+35 (incl weeknachten ervoor en erna)\r\n\r\ngeen fase 1","CTL","Minor_AdHoc",null," ",58453]
["2024-06-17","2024-06-21","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Week","Night","23:55","05:20","Omvorming Y Jette Rooster R: voorbereidende nachten","CTL","Minor_AdHoc","TLO L50 + L60"," ",50032]
["2024-06-17","2024-06-21","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Linked to coupure nr 50032 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Omvorming Y Jette Rooster R: voorbereidende nachten","CTL","Minor_AdHoc"," "," ",50032]
["2024-06-17","2024-06-21","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59868]
["2024-06-17","2024-06-21","NE",3,"29","A+B","Y.KRUISBERG","TURNHOUT","Week","Night","23:00","04:40","omvormen 50 HZ SK naar TFSK\r\naanpassen treindetectiesysteem (moet voor 2025)\r\nvernieuwing signalisatie overwegen\r\nomvorming moet gebeuren voor uitrol ETCS L29","CTL","Minor_AdHoc","alternatief E3421"," ",60017]
["2024-06-17","2024-06-21","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:10","04:00","weeknachten als fase 3 in map 3","CTL","Minor_AdHoc"," "," ",60201]
["2024-06-17","2024-06-21","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:50","04:30","onderhoud\r\n+\r\n afschaffen OW'en (colt 59828)","CTL","Minor_AdHoc","te bepalen"," ",59737]
["2024-06-17","2024-06-21","NW",3,"122","A+B","ZOTTEGEM","Y.MELLE","Week","Night","23:50","05:10","Vernieuwen rails","CTL","Minor_AdHoc",null,null,57849]
["2024-06-17","2024-06-21","NW",3,"59A","*","SINT-NIKLAAS-OOST","SINT-NIKLAAS-OOST","Week","Continuous","04:20","22:00","Sporen 505 tot 514 in bundel Sint Niklaas Oost niet bereikbaar kant Antwerpen","Autre","Minor_AdHoc"," "," ",60567]
["2024-06-17","2024-06-21","NW",3,"89","A+B","OUDENAARDE","Y.ZANDBERG","Week","Night","23:55","04:40","Vernieuwen overweg 91 (Harmelen)","CTL","Minor_AdHoc",null,"Info Racc.",57840]
["2024-06-17","2024-06-22","NE",3,"35","A+B","DIEST","AARSCHOT","Week","Night","23:40","04:40","onderhoudswerken A24\r\n+\r\nvervolg vernieuwingen Y Noord Aarschot (colt 58254)","CTL","Minor_AdHoc","alternatief E2622-E2743-E2872"," ",59972]
["2024-06-17","2024-06-22","SW",2,"94","A+B","HALLE","ATH","Week","Night","22:40","04:20","Nuits de préparation - Construction d'un CSV - PN18\r\n+ Maintenance Z9.54+Z10.54","CTL","Minor_AdHoc","CTL de nuits de semaine"," ",55574]
["2024-06-17","2024-06-23","SE",2,"165","B","HALANZY","AUBANGE","AllWeek","Continuous","08:00","16:00","Pose de caniveaux drainant (boueux)","SAVU","Minor_AdHoc"," "," ",57837]
["2024-06-18","2024-06-22","NW",3,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw \r\nAfwerking","CTL","Minor_AdHoc"," "," ",59042]
["2024-06-18","2024-06-22","NW",3,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 59042 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking","CTL","Minor_AdHoc"," "," ",59042]
["2024-06-18","2024-06-22","NW",3,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 59042 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking","SAVU","Minor_AdHoc"," "," ",59042]
["2024-06-19","2024-06-19","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60094]
["2024-06-20","2024-06-20","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60110]
["2024-06-20","2024-06-20","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",56276]
["2024-06-21","2024-06-24","NE",1,"16","A+B","Y.NOORD DRIEHOEK AARSCHOT","Y.OOST DRIEHOEK AARSCHOT","Weekend","Continuous","23:50","04:00","vervolg vernieuwing Y noord aarschot\r\n\r\n1WE L16 tussen vertakkingen + weeknachten ervoor en erna (WE incl L16+35)\r\n3WE L16+35 (incl weeknachten ervoor en erna)\r\n\r\ngeen fase 1","CTL","Medium",null," ",58454]
["2024-06-21","2024-06-24","CE",3,"96B","*","FOREST-VOITURES","FOREST-MIDI-VOIES 920/926","Weekend","Continuous","22:30","04:30","Onderhoudswerken volgens onderhoudskalender Area CE, zone FBKI_17.\r\nOnderhoud bundel IN+T","Autre","Minor_AdHoc","Volledige zone ter beschikking van I-AM"," ",58639]
["2024-06-21","2024-06-24","NE",1,"35","A+B","Y.ZUID DRIEHOEK AARSCHOT","DIEST","Weekend","Continuous","23:40","04:30","vervolg vernieuwingen Y Noord Aarschot \r\n\r\nreserve plaatsen fietstunnel OW opperstraat Aarschot","CTL","Medium",null," ",58255]
["2024-06-21","2024-06-24","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:30","05:00","vernieuwen Muizen rooster T \r\n(samen met L27B)\r\n\r\nsecundair fietstunnel Willendries en ONB Willendriesbeek","CTL","Medium"," "," ",58335]
["2024-06-21","2024-06-24","NE",2,"35","A+B","HASSELT","Y.ZUID DRIEHOEK AARSCHOT","Weekend","Continuous","23:50","04:00","onderhoud \r\n\r\ndata MOET nog wijzigen","CTL","Medium"," "," ",60176]
["2024-06-21","2024-06-24","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59909]
["2024-06-21","2024-06-24","NW",2,"217","S","Y.NOORD EVERSTEIN","EVERGEM-OVERDAM","Weekend","Continuous","23:50","05:00","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Medium"," ","Info Racc",58522]
["2024-06-21","2024-06-24","NW",2,"55A","S","Y.RINGVAART","LANGERBRUGGE","Weekend","Continuous","23:50","05:00","Linked to coupure nr 58522 on line 217 tracks(s) S from Y.NOORD EVERSTEIN to EVERGEM-OVERDAM: 227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Medium"," ","Info Racc",58522]
["2024-06-21","2024-06-24","NW",2,"86","S","RENAIX","OUDENAARDE","Weekend","Continuous","23:40","04:20","Linked to coupure nr 57839 on line 89 tracks(s) A+B from OUDENAARDE to Y.ZANDBERG: Vernieuwen overweg 91 (Harmelen)\r\n\r\n+\r\nBuitenwerken Oudenaarde \r\nbuitendienststelling rooster Oudenaarde L86+89 kant Ronse/Kortrijk + sp I + sp 781\r\nCoLT 57624 - tijdens ","CTL","Medium"," ","Info Racc.",57839]
["2024-06-21","2024-06-24","NW",2,"89","A+B","OUDENAARDE","Y.ZANDBERG","Weekend","Continuous","23:40","04:20","Vernieuwen overweg 91 (Harmelen)\r\n\r\n+\r\nBuitenwerken Oudenaarde \r\nbuitendienststelling rooster Oudenaarde L86+89 kant Ronse/Kortrijk + sp I + sp 781\r\nCoLT 57624 - tijdens de nacht buiten dienst stelling rooster Oudenaarde L86+89 kant Gent/Zottegem\r\n\r\n+\r\n","CTL","Medium",null,"Info Racc.",57839]
["2024-06-21","2024-06-24","NW",3,"122","A+B","Y.MELLE","ZOTTEGEM","Weekend","Continuous","23:50","05:00","Vernieuwen rails\r\nZottegem en Y Melle VRIJ","CTL","Medium",null,null,57850]
["2024-06-21","2024-06-24","NW",3,"50","A+B","DENDERLEEUW","JETTE","Weekend","Continuous","23:55","04:20","Onderhoudswerken + kleine vernieuwingswerken","CTL","Medium",null," ",60850]
["2024-06-21","2024-06-24","NW",3,"59A","*","SINT-NIKLAAS-OOST","SINT-NIKLAAS-OOST","Weekend","Continuous","22:00","04:20","Herzieningen en aansluiten bundelkoppen\r\nUitbraak 206 ABX.\r\nGevallen 22873+22875\r\nSporen 505 tot 514 buiten dienst","Autre","Minor_AdHoc"," "," ",60571]
["2024-06-21","2024-06-24","SE",1,"130/1","A+B","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Weekend","Continuous","23:30","06:00","Linked to coupure nr 49896 on line 144 tracks(s) A+B from GEMBLOUX to JEMEPPE-SUR-SAMBRE: Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 4/4 - Bourrage de révision et réglage des contraintes","CTL","Medium"," ","Info Racc : raccordement inaccessible",49896]
["2024-06-21","2024-06-24","SE",1,"144","A+B","GEMBLOUX","JEMEPPE-SUR-SAMBRE","Weekend","Continuous","23:30","06:00","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 4/4 - Bourrage de révision et réglage des contraintes","CTL","Medium","Fin des ART","Info Racc : raccordement inaccessible",49896]
["2024-06-21","2024-06-24","SE",1,"166","A+B","BEAURAING","BERTRIX","Weekend","Continuous","23:00","04:30","Renouvellement traverses (P93)","CTL","Medium","P93 entre BK 46180 et 48680\r\nART stabilisation v=60km/h , min retard = 3min\r\nDébut du chantier après le talon d'AW 06AO, l'entrée / sortie P93 occupe le cas caténaire 26433, en plus du 26437.\r\nLa MHS commencera à partir du signal EX-O23."," ",47740]
["2024-06-21","2024-06-24","SW",2,"78","A+B","SAINT-GHISLAIN","TOURNAI","Weekend","Continuous","23:30","05:00","Maintenance Z13.53 + Z4.54 P4\r\n+ Construction d'un couloir sous-voies au niveau du PN43 (L78…68.800) en vue de la suppression du PN.\r\nPhase 3 - ripage du CSV","CTL","Medium","ART stabilisation\r\nHKV : 160km/h→40km/h ; 100m ; retard = 2'38\"\r\nHKM : 120km/h→40km/h ; 100m ; retard = 5'37\""," ",56576]
["2024-06-21","2024-06-28","CE",1,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","AllWeek","Continuous","23:00","23:50","P008 518: Op dubbel spoor brengen L161/1 Fase 3: Ripage L161/1","CTL","Medium","TLO L161/1"," ",59583]
["2024-06-21","2024-07-01","SE",3,"40","*","VISE","VISE","AllWeek","Continuous","23:00","05:30","Dissociation TJD 34K/35K en 2 branchements simples.","Autre","Minor_AdHoc","La pose de la nouvelle liaison L24/1 est réalisée (CoLT id 57868 + 57870 + 57874 + 57875 + 57880 + 57882)\r\n\r\nFaisceau 56 et 57 inaccessibles côté Liège\r\nMHS depuis l'AS33K voie B L40 côté Liège jusqu'à la TJD52AK/60BK côté NL\r\n\r\nPour interventions catén"," ",57891]
["2024-06-21","2024-07-08","CE",1,"50","A+B","Y.LAEKEN","TERNAT","AllWeek","Continuous","23:55","05:20","Massificatie Omvorming Y Jette Rooster R + perrons Bockstael\r\n1) Omvorming Y Jette Rooster R (57157)\r\n2) P781301: Vernieuwing Bockstael perron 1+2 (50549-50550-50552)\r\nOnderling af te spreken met I-AM om steeds 1 spoor vrij te laten voor werfverkeer van","CTL","High","TLO L50 + L60"," ",57157]
["2024-06-21","2024-07-08","CE",1,"60","A+B","JETTE","ASSE","AllWeek","Continuous","23:55","05:20","Linked to coupure nr 57157 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Massificatie Omvorming Y Jette Rooster R + perrons Bockstael\r\n1) Omvorming Y Jette Rooster R (57157)\r\n2) P781301: Vernieuwing Bockstael perron 1+2 (50549-50550-50552)\r\nOnderlin","CTL","High"," "," ",57157]
["2024-06-22","2024-06-22","SE",3,"130","A/B","FLAWINNE","MOUSTIER","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49173]
["2024-06-22","2024-06-23","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59428]
["2024-06-22","2024-06-23","SE",3,"125A","S","Y.VAL-BENOIT","KINKEMPOIS-BLOCK 2","Weekend","Continuous","08:00","16:00","Linked to coupure nr 57778 on line 125B tracks(s) A+B from Y.GARDE-DIEU to KINKEMPOIS-BLOCK 2: Z.12.41 P4 Maintenance\r\nNivellement/Entretien TJD + Nivellement 125B VA & VB","CTL","Medium"," "," ",57778]
["2024-06-22","2024-06-23","SE",3,"125B","A+B","Y.GARDE-DIEU","KINKEMPOIS-BLOCK 2","Weekend","Continuous","08:00","16:00","Z.12.41 P4 Maintenance\r\nNivellement/Entretien TJD + Nivellement 125B VA & VB","CTL","Medium",null," ",57778]
["2024-06-22","2024-06-23","SE",3,"43","A+B","ANGLEUR","RIVAGE-MARCHANDISES","Weekend","Continuous","00:05","17:00","Entretien manuel et mécanisés des PN \r\nEntretien manuel et mécanisés des AW","CTL","Medium",null," ",55086]
["2024-06-22","2024-06-23","SW",2,"116/1","A+B","Y.FAMILLEUREUX","Y.BOIS-D'HAINE","Weekend","Continuous","06:00","17:00","Linked to coupure nr 56289 on line 117 tracks(s) A+B from BRAINE-LE-COMTE to MANAGE: Maintenance Z3.53 en P4\r\n+ Maintenance Zone Z09.52","CTL","Medium"," ","HKM à adapter",56289]
["2024-06-22","2024-06-23","SW",2,"117","A+B","BRAINE-LE-COMTE","MANAGE","Weekend","Continuous","06:00","17:00","Maintenance Z3.53 en P4\r\n+ Maintenance Zone Z09.52","CTL","Medium"," ","HKM à adapter",56289]
["2024-06-22","2024-06-24","NE",1,"27B","A+B","Y.PRINSENHOEK","Y.MUIZEN","Weekend","Continuous","00:00","04:00","vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58353]
["2024-06-22","2024-06-24","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","06:00","04:00","Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nVoorbereidingsweekend 2/3\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINAL","CTL","Medium"," "," ",53692]
["2024-06-22","2024-06-24","NE",1,"53","A+B","Y.HEVER","MUIZEN","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58353 on line 27B tracks(s) A+B from Y.PRINSENHOEK to Y.MUIZEN: vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58353]
["2024-06-22","2024-06-24","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58021]
["2024-06-22","2024-06-24","NE",2,"53","A+B","Y.HEIKE","MECHELEN","Weekend","Continuous","00:00","04:00","ETCS Mechelen Londerzeel\r\nmeewerken niet mogelijk \r\nCTL spoor A+B","CTL","Medium"," "," ",59368]
["2024-06-22","2024-06-24","NW",2,"86","A+B","OUDENAARDE","GAVERE-ASPER","Weekend","Night","00:05","04:20","Linked to coupure nr 57624 on line 89 tracks(s) A+B from OUDENAARDE to ZOTTEGEM: Buitenwerken Oudenaarde \r\nCoLT 57839- buitendienststelling rooster Oudenaarde L86+89 kant Ronse/Kortrijk + sp I + sp 781\r\nCoLT 57624 - tijdens de nacht buiten dienst stelli","CTL","Minor_AdHoc"," "," ",57624]
["2024-06-22","2024-06-24","NW",2,"89","A+B","OUDENAARDE","ZOTTEGEM","Weekend","Night","00:05","04:20","Buitenwerken Oudenaarde \r\nCoLT 57839- buitendienststelling rooster Oudenaarde L86+89 kant Ronse/Kortrijk + sp I + sp 781\r\nCoLT 57624 - tijdens de nacht buiten dienst stelling rooster Oudenaarde L86+89 kant Gent/Zottegem","CTL","Minor_AdHoc",null," ",57624]
["2024-06-22","2024-06-24","SW",2,"94","A+B","HALLE","ENGHIEN","Weekend","Continuous","00:30","04:20","Construction d'un CSV - PN18\r\n+ Maintenance Z15.54","CTL","Medium","WE de CTL du Vendredi soir au Lundi Matin\r\nART pendant 21 jours après le WE"," ",55576]
["2024-06-23","2024-06-23","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59991]
["2024-06-23","2024-06-23","SE",3,"130","A/B","MOUSTIER","AUVELAIS","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49182]
["2024-06-24","2024-06-28","NE",1,"16","A+B","Y.NOORD DRIEHOEK AARSCHOT","Y.OOST DRIEHOEK AARSCHOT","Week","Night","23:30","04:00","vervolg vernieuwing Y noord aarschot\r\n\r\n1WE L16 tussen vertakkingen + weeknachten ervoor en erna (WE incl L16+35)\r\n3WE L16+35 (incl weeknachten ervoor en erna)\r\n\r\ngeen fase 1","CTL","Minor_AdHoc",null," ",58455]
["2024-06-24","2024-06-27","NE",1,"35","A+B","Y.ZUID DRIEHOEK AARSCHOT","DIEST","Week","Night","23:50","04:40","vervolg vernieuwingen Y Noord Aarschot","CTL","Minor_AdHoc","alternatief E2622"," ",58256]
["2024-06-24","2024-06-28","NE",2,"53","A+B","MUIZEN-ROOSTER T","LEUVEN","Week","Night","23:20","05:00","herelectrificatie (bijkomend)","CTL","Minor_AdHoc","alternatief E2645-E2644"," ",60282]
["2024-06-24","2024-06-28","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59869]
["2024-06-24","2024-06-28","NW",3,"122","A+B","ZOTTEGEM","Y.MELLE","Week","Night","23:50","05:10","Vernieuwen rails","CTL","Minor_AdHoc",null,null,57851]
["2024-06-24","2024-06-28","NW",3,"59A","*","SINT-NIKLAAS-OOST","SINT-NIKLAAS-OOST","Week","Continuous","04:20","22:00","Sporen 505 tot 514 in bundel Sint Niklaas Oost niet bereikbaar kant Antwerpen","Autre","Minor_AdHoc"," "," ",60572]
["2024-06-24","2024-06-28","NW",3,"89","A+B","OUDENAARDE","Y.ZANDBERG","Week","Night","23:55","04:40","Vernieuwen overweg 91 (Harmelen)","CTL","Minor_AdHoc",null,"Info Racc.",57841]
["2024-06-24","2024-06-28","SE",1,"130/1","A+B","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Week","Day","09:00","15:30","Linked to coupure nr 49897 on line 144 tracks(s) A+B from GEMBLOUX to JEMEPPE-SUR-SAMBRE: Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nFinitions","CTL","Minor_AdHoc"," ","Info Racc : raccordement inaccessible",49897]
["2024-06-24","2024-06-28","SE",1,"144","A+B","GEMBLOUX","JEMEPPE-SUR-SAMBRE","Week","Day","09:00","15:30","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nFinitions","CTL","Minor_AdHoc","Coupures de jour en semaine (minimum 6h)","Info Racc : raccordement inaccessible",49897]
["2024-06-24","2024-06-28","SW",1,"90C","A","BRUGELETTE","BRUGELETTE","Week","Continuous","08:00","16:30","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette","SAVU","Minor_AdHoc","SAVU de jour en semaine sauf les mercredis"," ",49563]
["2024-06-24","2024-06-28","SW",1,"96","A+B","MONS","JURBISE","Week","Night","22:45","04:10","Maintenance Z.5.53 en P3\r\n+ Réélectrification - Phase 3 - 2024\r\nDépose anciennes traverses\r\n+ ETCS L2-IL_SO_P036_L96_L97_Jurbise - Mons - Saint Ghislain_ETCS\r\nETCS : Travaux extérieurs + chargements\r\nmeewerken mogelijk","CTL","Minor_AdHoc","4 nuits\r\nGroupe Pilote 6h",null,61224]
["2024-06-24","2024-06-29","CE",2,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","Week","Night","23:45","04:50","Onderhoudszone FBMZ_19, FBKI_03 en FH_06 Area CE volgens onderhoudskalender 2024\r\n\r\nSporen A en B 124 buiten dienst, inclusief L28/3","CTL","Minor_AdHoc",null," ",59512]
["2024-06-24","2024-07-08","SW",1,"90C","A+B","BRUGELETTE","BRUGELETTE","AllWeek","Continuous","22:10","05:10","ART 3min HKV / 5min HKM\r\nRenouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\nART de Stabilisation","ART","Minor_AdHoc","ART stabilisation (40/60) \r\nHKV\t: 3.04/1.52 - HKM : 5.32:3.00"," ",49539]
["2024-06-24","2024-07-12","SE",1,"166","A+B","BEAURAING","BERTRIX","AllWeek","Continuous","04:30","23:00","Renouvellement traverses (P93)\r\nART 3min","ART","Minor_AdHoc","ART stabilisation v=60km/h\r\n3 minutes"," ",54864]
["2024-06-24","2024-07-12","SW",1,"90C","A+B","JURBISE","ATH","Week","Night","22:10","05:10","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\n+ Maintenance Z7.53 +  Z13.54 en P3","CTL","Minor_AdHoc",null," ",48254]
["2024-06-25","2024-06-28","NE",3,"21D","A+B","Y.BOKSBERGHEIDE","GENK","Week","Night","23:20","04:40","Onderhoud","CTL","Minor_AdHoc"," "," ",59949]
["2024-06-25","2024-06-28","SW",2,"94","A+B","HALLE","ENGHIEN","Week","Night","00:20","04:20","Nuits de finitions - Construction d'un CSV - PN18","CTL","Minor_AdHoc","CTL de nuits de semaine"," ",55578]
["2024-06-28","2024-07-01","NE",1,"16","A+B","Y.NOORD DRIEHOEK AARSCHOT","Y.OOST DRIEHOEK AARSCHOT","Weekend","Continuous","23:30","04:00","vervolg vernieuwing Y noord aarschot","CTL","Medium",null," ",58456]
["2024-06-28","2024-06-30","SW",2,"112","A/B","MARCHIENNE-AU-PONT","PIETON","Weekend","Continuous","23:30","16:00","Tir de fils de contacts avec autorail","SAVU","Minor_AdHoc"," "," ",53199]
["2024-06-28","2024-06-30","SW",2,"287","A","ATH","GHISLENGHIEN","Weekend","Continuous","13:00","23:00","Transfert des PNs - Renouvellement des CVs et PNs","CTL","Medium",null," ",50568]
["2024-06-28","2024-07-01","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","23:30","04:00","Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nVoorbereidingsweekend 3/3\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINAL\r\n+\r\nherelectrificatie (bijkomend) colt 60283\r\n+\r\nvernieuwen Muizen rooster T \r\n(samen met L27B)\r\nsecundair f","CTL","Medium"," "," ",53693]
["2024-06-28","2024-07-01","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:30","05:00","vernieuwen Muizen rooster T \r\n(samen met L27B)\r\n\r\nsecundair fietstunnel Willendries en ONB Willendriesbeek","CTL","Medium"," "," ",58336]
["2024-06-28","2024-07-01","NE",2,"35","A+B","Y.ZUID DRIEHOEK AARSCHOT","DIEST","Weekend","Continuous","23:40","04:30","vervolg vernieuwingen Y Noord Aarschot \r\n+\r\nreserve plaatsen fietstunnel OW opperstraat Aarschot (59359)","CTL","Medium","alternatief E2473-E2622"," ",58257]
["2024-06-28","2024-07-01","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59910]
["2024-06-28","2024-07-01","NE",3,"21D","A+B","Y.BOKSBERGHEIDE","GENK","Weekend","Continuous","23:20","04:40","Onderhoud","CTL","Medium"," "," ",59950]
["2024-06-28","2024-07-01","NW",2,"86","A+B","GAVERE-ASPER","OUDENAARDE","Weekend","Continuous","23:40","05:00","Buitenwerken \r\nVernieuwen seininrichting Gavere-Asper - Oudenaarde\r\nBundel Oudenaarde inbegrepen\r\nRooster Oudenaarde inbegrepen tot aan seinen van perron III-IV-V, perrons zelf blijven beschikbaar\r\nRooster L89 blijft vrij","CTL","Medium",null," ",57567]
["2024-06-28","2024-07-01","NW",3,"122","A+B","Y.MELLE","ZOTTEGEM","Weekend","Continuous","23:50","05:00","Vernieuwen rails\r\nZottegem en Y Melle VRIJ","CTL","Medium",null,null,57852]
["2024-06-28","2024-07-01","NW",3,"59A","S","SINT-NIKLAAS","SINT-NIKLAAS-OOST","Weekend","Continuous","22:00","04:20","Vernieuwen wissels 30M-31AM-32BM\r\nGevallen 22871-22873-22875\r\nBundel Sint Niklaas Oost volledig buiten dienst \r\nBaantrein op spoor","CTL","Medium"," "," ",60573]
["2024-06-28","2024-07-01","SE",1,"166","A+B","BEAURAING","BERTRIX","Weekend","Continuous","23:00","04:30","Renouvellement traverses (P93)\r\nBourrage révision","CTL","Medium","P93 entre BK 46180 et 48680","HKM à adapter",46805]
["2024-06-28","2024-07-01","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 min","HKM à adapter",48632]
["2024-06-28","2024-07-01","SW",1,"90C","A+B","JURBISE","ATH","Weekend","Continuous","22:10","05:10","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\n+ Maintenance Z7.53 + Z13.54","CTL","Medium","Brugelette non accessible","HKM à adapter",48253]
["2024-06-28","2024-07-01","SW",2,"94","A/B","HALLE","SAINTES","Weekend","Continuous","23:10","05:00","Construction d'un CSV - PN18","SAVU","Minor_AdHoc","SAVU de finition"," ",55579]
["2024-06-28","2024-07-08","CE",1,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","AllWeek","Continuous","23:50","04:40","P008 518: Op dubbel spoor brengen L161/1","CTL","High","TLO L161/1 + 161/2 + 161\r\nDOES L26B op 29/06 vanaf 06u00\r\nTLO L26B tijdens de nachten vanaf 29/30-06 tem 5/6-07.\r\nContinue DOES L26B via sp A tijdens het WE 6+7/07."," ",49748]
["2024-06-28","2024-07-08","CE",1,"161/2","A+B","BRUXELLES-NORD-GRIL F","Y.JOSAPHAT","AllWeek","Continuous","23:50","04:40","Linked to coupure nr 49748 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Op dubbel spoor brengen L161/1","CTL","High"," "," ",49748]
["2024-06-28","2024-07-08","CE",1,"26B","B","Y.PONT-DE-LA-SENNE","SCHAERBEEK","AllWeek","Continuous","23:50","04:40","Linked to coupure nr 49748 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Op dubbel spoor brengen L161/1","CTL","High"," "," ",49748]
["2024-06-28","2024-07-01","SE",3,"161","B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","réélectrification","SAVU","Minor_AdHoc","une voie en continu"," ",49722]
["2024-06-28","2024-07-08","CE",1,"161","A+B","SCHAERBEEK","ROGIER","AllWeek","Continuous","23:50","04:40","Linked to coupure nr 49748 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Op dubbel spoor brengen L161/1","CTL","High"," "," ",49748]
["2024-06-29","2024-06-30","NW",3,"204","*","GENT-RODENHUIZE","GENT-RODENHUIZEDOK","Weekend","Continuous","22:00","14:00","Reservatie onderhoud, enkel bundel Mercator buiten dienst","CTL","Medium",null,"Info Racc",60415]
["2024-06-29","2024-06-30","SE",2,"125","A+B","FLEMALLE-HAUTE","HUY","Weekend","Continuous","00:40","18:00","WE n°1: Démolition passage supérieur BK 17.196 d'Engis - massification entretien OA et parois rocheuses","CTL","Medium"," "," ",47494]
["2024-06-29","2024-06-30","SW",3,"130","A+B","CHARLEROI-SUD","COUILLET","Weekend","Continuous","06:00","17:00","Maintenance Z10. 51   P4+","CTL","Medium","Détails car sur plusieurs lignes:\r\nL130\tVoie B\tCharleroi-Sud\tChâtelet\tD08-G. 20   &\t FX3_I. 20\r\n\t        Voie A\t\t\t                        D09-G. 20    &  F4_I. 20\r\n\t\t\t\tE10_H. 20   &\tF4_I. 20\r\n\t\t\t\tE11_H. 20   &\tF4_I. 20\r\n\t\t\t\tE12_H. 20   &\tF4_I. 20"," ",49372]
["2024-06-29","2024-07-01","NE",1,"27B","A+B","Y.PRINSENHOEK","Y.MUIZEN","Weekend","Continuous","00:00","04:00","vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58354]
["2024-06-29","2024-07-01","NE",1,"53","A+B","Y.HEVER","MUIZEN","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58354 on line 27B tracks(s) A+B from Y.PRINSENHOEK to Y.MUIZEN: vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58354]
["2024-06-29","2024-07-01","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58022]
["2024-06-29","2024-07-01","NE",2,"53","A+B","Y.HEIKE","MECHELEN","Weekend","Continuous","00:00","04:00","ETCS Mechelen Londerzeel\r\nmeewerken niet mogelijk \r\nCTL spoor A+B","CTL","Medium"," "," ",59369]
["2024-06-29","2024-07-01","NE",3,"12","A+B","Y.LUCHTBAL","Y.SINT-MARIABURG","Weekend","Continuous","06:00","04:10","Oude landen project 308+304","CTL","Medium","Aan deze werken is een R7 (van 06h00 tot 17h30) gekoppeld op L27A voor het spoorgedeelte Y.Laarsebeek - Y.Schijn!! (58663)"," ",58642]
["2024-06-29","2024-07-01","SE",1,"24/1","A+B","VISE","Y.BERNEAU","Weekend","Continuous","00:20","04:40","Linked to coupure nr 55123 on line 40 tracks(s) A+B from FROIDMONT to VISE-FRONTIERE: Entretien manuel et mécanisés des AW Bressoux / Visé-Bas\r\nEntretien manuel et mécanisés de la voie courante","CTL","Medium"," "," ",55123]
["2024-06-29","2024-07-01","SE",1,"40","A+B","FROIDMONT","VISE-FRONTIERE","Weekend","Continuous","00:20","04:40","Entretien manuel et mécanisés des AW Bressoux / Visé-Bas\r\nEntretien manuel et mécanisés de la voie courante","CTL","Medium","L40 + L24/1"," ",55123]
["2024-06-29","2024-08-26","SW",1,"124","A+B","BAULERS-GRIL D","NIVELLES","AllWeek","Continuous","06:00","04:50","RER Réaménagement des voies et aiguillages à Baulers vers Nivelles.\r\nPhase 3\r\nDossier de concertation validé","CTL","Major","PAS DE MARCHANDISE POSSIBLE car Rupture de charge !!!!!\r\nVoir SIRU à éditer"," ",21118]
["2024-06-29","2024-06-30","SE",3,"161","A/B","GEMBLOUX","RHISNES","Weekend","Day","08:00","16:00","Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49197]
["2024-06-30","2024-06-30","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","06:00","17:40","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58663]
["2024-06-30","2024-06-30","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59992]
["2024-07-01","2024-07-05","NE",1,"16","A+B","Y.NOORD DRIEHOEK AARSCHOT","Y.OOST DRIEHOEK AARSCHOT","Week","Night","23:30","04:00","vervolg vernieuwing Y noord aarschot","CTL","Minor_AdHoc",null," ",58457]
["2024-07-01","2024-07-02","SW",3,"130A","A","Y.NORD","LOBBES-GARAGE","Week","Continuous","22:30","15:30","Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires caténaire (int. 99/1)","SAVU","Minor_AdHoc","SAVU VA 16h min. en continu\r\nTravail à La Sambre mais cas 27631 HS --> SAVU jusque Lobbes-G.\r\nEntre 02K ne et Y.Nord\r\ncas  27629 et 27631\r\n\r\nLibéré une nuit sur P3 L96 Mons-Quévy Colt 55920\r\nVoir avec SAVU Z6.52 en L124A","HKM à adapter suite capacité insuffisante L130A en SAVU",61112]
["2024-07-01","2024-07-04","NE",1,"35","A+B","Y.ZUID DRIEHOEK AARSCHOT","DIEST","Week","Night","23:50","04:40","vervolg vernieuwingen Y Noord Aarschot","CTL","Minor_AdHoc","alternatief E2622"," ",58258]
["2024-07-01","2024-07-04","NE",3,"21D","A+B","Y.BOKSBERGHEIDE","GENK","Week","Night","23:20","04:40","Onderhoud","CTL","Minor_AdHoc"," "," ",59951]
["2024-07-01","2024-07-05","NE",2,"53","A+B","MUIZEN-ROOSTER T","LEUVEN","Week","Night","23:20","05:00","herelectrificatie (bijkomend)\r\n\r\nmogelijk conflict met vervolg vernieuwingen Y driehoek Aarschot","CTL","Minor_AdHoc","alternatief E2645-E2644"," ",60284]
["2024-07-01","2024-07-05","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59870]
["2024-07-01","2024-07-05","NW",3,"122","A+B","ZOTTEGEM","Y.MELLE","Week","Night","23:50","05:10","Vernieuwen rails","CTL","Minor_AdHoc",null,null,57853]
["2024-07-01","2024-07-05","NW",3,"58","A+B","WONDELGEM","SLEIDINGE","Week","Night","23:00","04:20","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nophoging spoor, afbreken bestaande brug, bouw nieuwe brug \r\n\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc"," "," ",58509]
["2024-07-01","2024-07-05","NW",3,"59A","*","SINT-NIKLAAS-OOST","SINT-NIKLAAS-OOST","Weekend","Continuous","04:20","22:00","Sporen 503 tot en met 514 niet toegankelijk kant Antwerpen","Autre","Minor_AdHoc"," "," ",60576]
["2024-07-01","2024-07-06","NW",3,"89","A+B","OUDENAARDE","Y.ZANDBERG","Week","Night","23:55","04:40","Vernieuwen overweg 91 (Harmelen)","CTL","Minor_AdHoc",null,"Info Racc.",57842]
["2024-07-01","2024-07-13","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","AllWeek","Continuous","04:40","04:40","Travaux RER\r\nART 2min","ART","Minor_AdHoc","ART stabilisation 2 min"," ",54877]
["2024-07-01","2024-07-13","SW",3,"94","A+B","HALLE","ENGHIEN","Week","Night","23:10","04:40","Nuits de finitions - Construction d'un CSV - PN18\r\nRQ 333 : incompatible Brugelette : 00h30-4h20","CTL","Minor_AdHoc","CTL de nuits de semaine"," ",55577]
["2024-07-01","2024-08-25","NW",3,"82","S","AALST","BURST","AllWeek","Continuous","08:00","18:00","Onderhoud","CTL","Major"," "," ",60868]
["2024-07-01","2032-09-01","NW",1,"66","*","KORTRIJK","KORTRIJK","AllWeek","Continuous","05:00","23:00","Linked to coupure nr 48302 on line 75 tracks(s) * from KORTRIJK to KORTRIJK: Kortrijk (Project NMBS-Stations): 2 sporen buiten dienst\r\n\r\ndd14/04/2022\r\n* Juli 2024: sporen VI en VII continu buiten dienst voor het afbreken van de perronluifel\r\n* Aansluite","Autre","Minor_AdHoc"," "," ",48302]
["2024-07-01","2032-09-01","NW",1,"75","*","KORTRIJK","KORTRIJK","AllWeek","Continuous","05:00","23:00","Kortrijk (Project NMBS-Stations): 2 sporen buiten dienst\r\n\r\ndd14/04/2022\r\n* Juli 2024: sporen VI en VII continu buiten dienst voor het afbreken van de perronluifel\r\n* Aansluitend augustus 2024 – januari 2026 sporen VII en VIII continu buiten dienst; uit","Autre","Minor_AdHoc"," "," ",48302]
["2024-07-01","2032-09-01","NW",1,"75C","*","KORTRIJK","KORTRIJK","AllWeek","Continuous","05:00","23:00","Linked to coupure nr 48302 on line 75 tracks(s) * from KORTRIJK to KORTRIJK: Kortrijk (Project NMBS-Stations): 2 sporen buiten dienst\r\n\r\ndd14/04/2022\r\n* Juli 2024: sporen VI en VII continu buiten dienst voor het afbreken van de perronluifel\r\n* Aansluite","Autre","Minor_AdHoc"," "," ",48302]
["2024-07-01","2032-09-01","NW",1,"66","*","KORTRIJK","KORTRIJK","AllWeek","Continuous","05:00","23:00","Linked to coupure nr 48302 on line 75 tracks(s) * from KORTRIJK to KORTRIJK: Kortrijk (Project NMBS-Stations): 2 sporen buiten dienst\r\n\r\ndd14/04/2022\r\n* Juli 2024: sporen VI en VII continu buiten dienst voor het afbreken van de perronluifel\r\n* Aansluite","Autre","Minor_AdHoc"," "," ",48302]
["2024-07-01","2032-09-01","NW",1,"75","*","KORTRIJK","KORTRIJK","AllWeek","Continuous","05:00","23:00","Kortrijk (Project NMBS-Stations): 2 sporen buiten dienst\r\n\r\ndd14/04/2022\r\n* Juli 2024: sporen VI en VII continu buiten dienst voor het afbreken van de perronluifel\r\n* Aansluitend augustus 2024 – januari 2026 sporen VII en VIII continu buiten dienst; uit","Autre","Minor_AdHoc"," "," ",48302]
["2024-07-01","2032-09-01","NW",1,"75C","*","KORTRIJK","KORTRIJK","AllWeek","Continuous","05:00","23:00","Linked to coupure nr 48302 on line 75 tracks(s) * from KORTRIJK to KORTRIJK: Kortrijk (Project NMBS-Stations): 2 sporen buiten dienst\r\n\r\ndd14/04/2022\r\n* Juli 2024: sporen VI en VII continu buiten dienst voor het afbreken van de perronluifel\r\n* Aansluite","Autre","Minor_AdHoc"," "," ",48302]
["2024-07-02","2024-07-06","NW",3,"59","A","SINT-NIKLAAS","Y.MELSELE","Week","Night","00:10","04:50","Vernieuwen wissels  Sint Niklaas Oost\r\n\r\nGevallen 22847 en 22871","SAVU","Minor_AdHoc","Gevallen 22847 en 22871 \r\nSporen 501-503-504 buiten dienst \r\nSporen 505 tot 514 niet bereikbaar"," ",60600]
["2024-07-05","2024-07-08","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59911]
["2024-07-05","2024-07-08","NW",2,"58","A+B","WONDELGEM","SLEIDINGE","Weekend","Continuous","23:00","05:00","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nophoging spoor, afbreken bestaande brug, bouw nieuwe brug","CTL","Medium",null," ",58506]
["2024-07-05","2024-07-08","NW",3,"122","A+B","Y.MELLE","ZOTTEGEM","Weekend","Continuous","23:50","05:00","Vernieuwen rails\r\nZottegem en Y Melle VRIJ","CTL","Medium",null,null,57843]
["2024-07-05","2024-07-08","NW",3,"59A","S","SINT-NIKLAAS","SINT-NIKLAAS-OOST","Weekend","Continuous","22:00","04:20","Vernieuwen wissels 33AM- 31BM\r\nGevallen 22871-22873-22875\r\nBundel Sint Niklaas Oost volledig buiten dienst","CTL","Medium"," "," ",60601]
["2024-07-05","2024-07-08","SE",1,"166","A+B","BEAURAING","BERTRIX","Weekend","Continuous","23:00","04:30","Renouvellement traverses (P93)","CTL","Medium","P93 de 51.180 à 53.680\r\nBourrage révision entre 48.680 et 51.180","HKM à adapter",46809]
["2024-07-05","2024-07-08","SW",1,"90C","A+B","ATH","JURBISE","Weekend","Continuous","22:10","05:10","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette","CTL","Medium","Brugelette non accessible","HKM à adapter",48252]
["2024-07-05","2024-07-31","SE",1,"166","A+B","GENDRON-CELLES","HOUYET","AllWeek","Continuous","22:00","22:00","Massification travaux\r\nART 3 minutes","ART","Minor_AdHoc","ART de stabilisation : BK 13.700 à 13.900 en voies A et B (longueur : 200 mètres). \r\nVitesse à 40 km/h. \r\nPerte de temps HKV : 3 minutes / HKM : 3 minutes. \r\nDate de début : 05/07 – date de fin probable : 31/07"," ",50023]
["2024-07-05","2024-07-08","SE",3,"161","B","RHISNES","GEMBLOUX","Weekend","Continuous","23:00","05:00","réélectrification","SAVU","Minor_AdHoc","une voie en continu"," ",49713]
["2024-07-06","2024-07-08","NE",1,"16","A+B","Y.NOORD DRIEHOEK AARSCHOT","Y.OOST DRIEHOEK AARSCHOT","Weekend","Continuous","00:00","04:00","vervolg vernieuwing Y noord aarschot","CTL","Medium",null," ",58452]
["2024-07-06","2024-07-07","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60423]
["2024-07-06","2024-07-07","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60423 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60423]
["2024-07-06","2024-07-07","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60423 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60423]
["2024-07-06","2024-07-07","SE",2,"125","A+B","FLEMALLE-HAUTE","HUY","Weekend","Continuous","00:40","18:00","WE n°2 :Démolition passage supérieur BK 17.196 d'Engis - massification entretien OA et parois rocheuses","CTL","Medium"," "," ",47495]
["2024-07-06","2024-07-07","SE",3,"34","A+B","HERSTAL","LIERS","Weekend","Continuous","08:00","17:00","Z17.41 P4+ - Maintenance AI 41.","CTL","Medium"," "," ",57873]
["2024-07-06","2024-07-08","CE",2,"96A/1","S","BRUXELLES-PETITE-ILE","FOREST-NORD","Weekend","Continuous","00:30","04:00","Linked to coupure nr 58622 on line 96B tracks(s) A+B from BRUXELLES-PETITE-ILE to FOREST-VOITURES: Onderhoudswerken Area CE zone FBKI 06\r\nL96B - Toegang Vorst","CTL","Medium"," ","Néant",58622]
["2024-07-06","2024-07-08","CE",2,"96B","A+B","BRUXELLES-PETITE-ILE","FOREST-VOITURES","Weekend","Continuous","00:30","04:00","Onderhoudswerken Area CE zone FBKI 06\r\nL96B - Toegang Vorst","CTL","Medium","Geen rechtstreekse toegang tot bundels Vorst.\r\nEnkel toegang via L96C en L96D","Néant",58622]
["2024-07-06","2024-07-08","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58023]
["2024-07-06","2024-07-08","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","migratie tunnelveiligheidtechnieken Antw NZ\r\nantwerpen centraal -antwerpen luchtbal","CTL","Medium"," "," ",59341]
["2024-07-06","2024-07-08","NW",2,"55","A+B","Y.RINGVAART","ZELZATE-GRENS","Weekend","Continuous","05:00","05:00","P227331 R4WO W8\r\nLangerbrugsestraat ecotunnel","CTL","Medium"," ","Info Racc",58505]
["2024-07-07","2024-07-07","CE",1,"25","A+B","BRUXELLES-NORD","VILVOORDE","Weekend","Night","00:30","05:00","Linked to coupure nr 56215 on line 28(1) tracks(s) A+B from Y.CUREGHEM to Y.LAEKEN: EBP-ETCS lading voor Jette en L161/1.\r\nGeen verkeer en geen werken mogelijk op L25-25N-26B-27-28-36-36N.","Autre","Minor_AdHoc"," "," ",56215]
["2024-07-07","2024-07-07","CE",1,"26B","A+B","Y.PONT-DE-LA-SENNE","SCHAERBEEK","Weekend","Night","00:30","05:00","Linked to coupure nr 56215 on line 28(1) tracks(s) A+B from Y.CUREGHEM to Y.LAEKEN: EBP-ETCS lading voor Jette en L161/1.\r\nGeen verkeer en geen werken mogelijk op L25-25N-26B-27-28-36-36N.","Autre","Minor_AdHoc"," "," ",56215]
["2024-07-07","2024-07-07","CE",1,"27","A+B","BRUXELLES-NORD","VILVOORDE","Weekend","Night","00:30","05:00","Linked to coupure nr 56215 on line 28(1) tracks(s) A+B from Y.CUREGHEM to Y.LAEKEN: EBP-ETCS lading voor Jette en L161/1.\r\nGeen verkeer en geen werken mogelijk op L25-25N-26B-27-28-36-36N.","Autre","Minor_AdHoc"," "," ",56215]
["2024-07-07","2024-07-07","CE",1,"28(1)","A+B","Y.CUREGHEM","Y.LAEKEN","Weekend","Night","00:30","05:00","EBP-ETCS lading voor Jette en L161/1.\r\nGeen verkeer en geen werken mogelijk op L25-25N-26B-27-28-36-36N.","Autre","Minor_AdHoc","Geen verkeer mogelijk op L25-25N-26B-27-28-36-36N"," ",56215]
["2024-07-07","2024-07-07","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59993]
["2024-07-07","2024-07-07","NW",3,"202B/1","S","Y.PELIKAAN","ZEEBRUGGE-BUNDEL PELIKAAN","Weekend","Day","06:00","22:00","R-419059-02\r\n\r\n\r\nOmvormen 51AR-51BR-52AR-54R-55R-56R-57R van He-H dmv voorgemonteerde panelen werkveld 3421-31\r\n\r\nBundel Pelikaan niet bereikbaar","CTL","Minor_AdHoc"," ","Info Racc",60384]
["2024-07-07","2024-07-07","NW",3,"202B/2","S","ZEEBRUGGE-BUNDEL PELIKAAN","Y.EIVOORDE","Weekend","Day","06:00","22:00","Linked to coupure nr 60384 on line 202B/1 tracks(s) S from Y.PELIKAAN to ZEEBRUGGE-BUNDEL PELIKAAN: R-419059-02\r\n\r\n\r\nOmvormen 51AR-51BR-52AR-54R-55R-56R-57R van He-H dmv voorgemonteerde panelen werkveld 3421-31\r\n\r\nBundel Pelikaan niet bereikbaar","CTL","Minor_AdHoc"," ","Info Racc",60384]
["2024-07-07","2024-07-07","NW",3,"51A","A","LISSEWEGE","ZEEBRUGGE-STRAND","Weekend","Day","14:00","22:00","Reservering Onderhoud doorsteek bundel A-B Zone 107\r\n\r\nR-419337-01","SAVU","Minor_AdHoc"," "," ",60453]
["2024-07-08","2024-07-08","SE",3,"130","A/B","NAMUR","FLAWINNE","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49056]
["2024-07-08","2024-07-12","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Week","Night","23:55","05:20","Omvorming Y Jette Rooster R: afwerking","CTL","Minor_AdHoc","TLO L50 + L60"," ",50033]
["2024-07-08","2024-07-12","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Linked to coupure nr 50033 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Omvorming Y Jette Rooster R: afwerking","CTL","Minor_AdHoc"," "," ",50033]
["2024-07-08","2024-07-12","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59871]
["2024-07-08","2024-07-12","SW",1,"90C","A","BRUGELETTE","BRUGELETTE","Week","Continuous","08:00","16:30","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette","SAVU","Minor_AdHoc","SAVU de jour en semaine sauf les mercredis"," ",56838]
["2024-07-08","2024-07-13","CE",1,"161","A+B","SCHAERBEEK","BRUXELLES-LUXEMBOURG","Week","Continuous","04:40","04:40","Linked to coupure nr 56103 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Stabilisatie-BTS","CTL","Medium"," "," ",56103]
["2024-07-08","2024-07-13","CE",1,"161","A+B","SCHAERBEEK","ROGIER","Week","Night","23:50","04:40","Linked to coupure nr 56799 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Op dubbel spoor brengen L161/1: Afwerking","CTL","Minor_AdHoc"," "," ",56799]
["2024-07-08","2024-07-13","CE",1,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Week","Continuous","04:40","04:40","P008 518: Stabilisatie-BTS","ART","Minor_AdHoc","BTS x km/h: HKV ="," ",56103]
["2024-07-08","2024-07-13","CE",1,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Week","Night","23:50","04:40","P008 518: Op dubbel spoor brengen L161/1: afwerking","CTL","Minor_AdHoc","TLO L161/1 + 161/2 + 161\r\nDOES L26B ??"," ",56799]
["2024-07-08","2024-07-13","CE",1,"161/2","A+B","BRUXELLES-NORD-GRIL F","Y.JOSAPHAT","Week","Continuous","04:40","04:40","Linked to coupure nr 56103 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Stabilisatie-BTS","CTL","Medium"," "," ",56103]
["2024-07-08","2024-07-13","CE",1,"161/2","A+B","BRUXELLES-NORD-GRIL F","Y.JOSAPHAT","Week","Night","23:50","04:40","Linked to coupure nr 56799 on line 161/1 tracks(s) S from Y.PONT-DE-LA-SENNE to Y.JOSAPHAT: P008 518: Op dubbel spoor brengen L161/1: Afwerking","CTL","Minor_AdHoc"," "," ",56799]
["2024-07-08","2024-07-13","NW",3,"122","A+B","ZOTTEGEM","Y.MELLE","Week","Night","23:50","05:10","Vernieuwen rails","CTL","Minor_AdHoc",null,null,57854]
["2024-07-08","2024-07-13","SW",1,"96","A+B","MONS","JURBISE","Week","Night","23:20","04:10","Réélectrification - Phase 3 - 2024\r\nDépose anciennes traverses\r\n+ ETCS L2-IL_SO_P036_L96_L97_Jurbise - Mons - Saint Ghislain_ETCS\r\nETCS : Travaux extérieurs + chargements\r\nmeewerken mogelijk","CTL","Minor_AdHoc",null,null,61225]
["2024-07-08","2024-07-15","CE",1,"50","A+B","Y.BOCKSTAEL","TERNAT","AllWeek","Continuous","05:20","05:20","Stabilisatie-BTS na omvorming rooster R","ART","Minor_AdHoc","BTS 60 km/h: HKV=2' / HKM= 4'"," ",56102]
["2024-07-08","2024-07-15","CE",1,"60","A+B","JETTE","ASSE","AllWeek","Continuous","05:20","05:20","Linked to coupure nr 56102 on line 50 tracks(s) A+B from Y.BOCKSTAEL to TERNAT: Stabilisatie-BTS na omvorming rooster R","Autre","Minor_AdHoc"," "," ",56102]
["2024-07-08","2024-07-22","NW",2,"55","A+B","Y.RINGVAART","ZELZATE-GRENS","AllWeek","Continuous","05:00","05:00","BTS\r\nP227331 R4WO W8\r\nLangerbrugsestraat ecotunnel","ART","Minor_AdHoc"," ","Info Racc",60961]
["2024-07-10","2024-07-10","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60095]
["2024-07-11","2024-07-11","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60111]
["2024-07-12","2024-07-15","CE",1,"50","A+B","Y.LAEKEN","TERNAT","Weekend","Continuous","23:55","05:20","Omvorming Y Jette Rooster R: afwerkingsWE, spanningsregeling, ...","CTL","Medium","TLO L50 + L60"," ",56097]
["2024-07-12","2024-07-15","CE",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:55","05:20","Linked to coupure nr 56097 on line 50 tracks(s) A+B from Y.LAEKEN to TERNAT: Omvorming Y Jette Rooster R: afwerkingsWE, spanningsregeling, ...","CTL","Medium"," "," ",56097]
["2024-07-12","2024-07-15","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: afwerking","CTL","Medium","TLO L161/1"," ",59574]
["2024-07-12","2024-07-15","CE",3,"96B","*","FOREST-VOITURES","FOREST-MIDI-VOIES 920/926","Weekend","Continuous","22:30","04:30","Onderhoudswerken volgens Onderhoudskalender Area CE, zone FBKI _16, Bundel D.","Autre","Minor_AdHoc","Bundel D volledig buiten dienst en buiten spanning"," ",58637]
["2024-07-12","2024-07-15","NE",2,"12","A+B","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL","Weekend","Continuous","22:45","04:55","onderhoud wissels en sporen te ANtwerpen Schijnpoort inrit bundel F inclusief bundelkoppen F, D","CTL","Medium","geen toegang tot bundel F \r\ngeen toegang bundel D kant Y luchtbal"," ",60217]
["2024-07-12","2024-07-15","NE",2,"35","A+B","AARSCHOT","LEUVEN","Weekend","Continuous","23:30","04:00","voor provinvie inschuiven tunnels,\r\nWIlsele L35 km 102.400\r\nWezemaal L35 km 97.400\r\n\r\nin totaal 3X TLO 52h (dicht bij elkaar)\r\n\r\nBTS 40km/h 2 weken vanaf middelste weekend voor elke tunnel\r\n+\r\n+ werken AWV: vervangen dekstenen en leuning op een brug Vun","CTL","Medium","alternatief E2943-E2622-E2872"," ",58671]
["2024-07-12","2024-07-15","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59912]
["2024-07-12","2024-07-15","SE",1,"166","A+B","BEAURAING","BERTRIX","Weekend","Continuous","23:00","04:30","Renouvellement traverses (P93)\r\nBourrage de révision","CTL","Medium","Bourrage de révision 51.180 - 53.680","HKM à adapter",46810]
["2024-07-12","2024-07-15","SE",3,"161","A","MONT-SAINT-GUIBERT","GEMBLOUX","Weekend","Continuous","23:00","05:00","réélectrification","SAVU","Minor_AdHoc","une voie en continu"," ",49717]
["2024-07-13","2024-07-14","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61584]
["2024-07-13","2024-07-14","SE",3,"161","A/B","OTTIGNIES","GEMBLOUX","Weekend","Day","08:00","16:00","Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles + 1/2h sas Rhisnes","SAVU","Minor_AdHoc","SAVU alternatif entre 08h00 et 16h00"," ",48952]
["2024-07-13","2024-07-14","SW",2,"96","A+B","Y.SOIGNIES","JURBISE","Weekend","Continuous","06:00","16:00","Maintenance Z4.53 \r\nMise HS P4","CTL","Medium",null," ",49500]
["2024-07-13","2024-07-14","SW",3,"112","A+B","MARCHIENNE-AU-PONT","PIETON","Weekend","Continuous","06:00","17:00","Maintenance Z13.52","CTL","Medium"," "," ",60787]
["2024-07-13","2024-07-14","SW",3,"124A","A+B","ROUX","Y.NORD","Weekend","Continuous","06:00","17:00","Linked to coupure nr 60787 on line 112 tracks(s) A+B from MARCHIENNE-AU-PONT to PIETON: Maintenance Z13.52","CTL","Medium"," "," ",60787]
["2024-07-13","2024-07-15","CE",2,"26","A+B","Y.RUE DE BRUEL","Y.CINQUANTENAIRE","Weekend","Continuous","00:30","04:00","P085306 BVL L26 Y Bruul - Y50.\r\nY Bruulstraat is niet inbegrepen.","CTL","Medium","TLO tussen Y Bruulstr en Y50","Info Racc",59647]
["2024-07-13","2024-07-15","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58024]
["2024-07-13","2024-07-15","NE",2,"34","A+B","Y.GLONS","HASSELT","Weekend","Continuous","06:00","04:30","onderhoud \r\n+\r\nvernieuwen en onderhoud OW'n","CTL","Medium"," "," ",63021]
["2024-07-14","2024-07-14","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61612]
["2024-07-14","2024-07-15","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","23:30","04:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het werkvenster","CTL","Minor_AdHoc"," "," ",59813]
["2024-07-15","2024-07-16","NE",3,"59/1","B","ANTWERPEN-CENTRAAL","Y.NOORD BERCHEM","Week","Day","10:00","15:00","spoor B onderhoud SIG\r\nsporen 1-2-3 antwerpen centraal inbegrepen","SAVU","Minor_AdHoc","Does op spoor A"," ",60223]
["2024-07-15","2024-07-19","SE",2,"40","*","VISE","VISE","Week","Day","06:00","22:00","Dissociation TJD 34K/35K en 2 branchements simples.\r\nBourrage de révision, finitions, contraintes,...","Autre","Minor_AdHoc","La pose de la nouvelle liaison L24/1 est réalisée (CoLT id 57868 + 57870 + 57874 + 57875 + 57880 + 57882)\r\n\r\nFaisceau 56 et 57 inaccessibles\r\nMHS depuis l'AS33K voie B L40 côté Liège jusqu'à la TJD52AK/60BK côté NL"," ",57892]
["2024-07-15","2024-07-20","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59872]
["2024-07-15","2024-07-20","NW",3,"58","A+B","WONDELGEM","SLEIDINGE","Week","Night","23:00","04:20","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nophoging spoor, afbreken bestaande brug, bouw nieuwe brug","CTL","Minor_AdHoc"," "," ",58510]
["2024-07-15","2024-07-20","SW",1,"96","*","BRAINE-LE-COMTE","BRAINE-LE-COMTE","AllWeek","Continuous","22:30","05:00","Renouvellement AS 07D+CDS 246, 14D,15D,16D,18D, 32D et 33D  Braine-le-Comte","Autre","Minor_AdHoc","Faisceau indisponible\r\nART 2min"," ",46943]
["2024-07-17","2024-07-19","NE",3,"59/1","A","ANTWERPEN-CENTRAAL","Y.NOORD BERCHEM","Week","Day","10:00","15:00","spoor A onderhoud SIG\r\nsporen 4-5-6 antwerpen centraal inbegrepen","SAVU","Minor_AdHoc","DOES op spoor B"," ",60224]
["2024-07-19","2024-07-21","SW",2,"96","A+B","Y.JURBISE","MONS","Weekend","Continuous","22:45","17:00","Maintenance Z5.53\r\nMise HS en P4","CTL","Medium"," ","HKM à adapter",49497]
["2024-07-19","2024-07-22","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: afwerking","CTL","Medium","TLO L161/1"," ",59575]
["2024-07-19","2024-07-22","NE",2,"35","A+B","AARSCHOT","LEUVEN","Weekend","Continuous","23:30","04:00","voor provinvie inschuiven tunnels,\r\nWIlsele L35 km 102.400\r\nWezemaal L35 km 97.400\r\n\r\nin totaal 3X TLO 52h (dicht bij elkaar)\r\n\r\nBTS 40km/h 2 weken vanaf middelste weekend voor elke tunnel\r\n+\r\n+ werken AWV: vervangen dekstenen en leuning op een brug Vun","CTL","Medium","alternatief E2943-E2622-E2872"," ",58672]
["2024-07-19","2024-07-22","SE",3,"161","A","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","réélectrification","SAVU","Minor_AdHoc","une voie en continu"," ",49721]
["2024-07-20","2024-07-20","SE",3,"139","A/B","WAVRE","OTTIGNIES","Weekend","Day","08:00","16:00","Visites des postes+ maintenances infrastructure et contrôles","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48871]
["2024-07-20","2024-07-21","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59427]
["2024-07-20","2024-07-21","SE",3,"161","A/B","NAMUR","RHISNES-SAS","Weekend","Day","08:00","16:00","Visite périodique + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","Savu alternatif VA/VB , de 8h à 16 h"," ",49210]
["2024-07-20","2024-07-22","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58025]
["2024-07-20","2024-07-22","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","migratie tunnelveiligheidtechnieken Antw NZ\r\nantwerpen centraal -antwerpen luchtbal","CTL","Medium"," "," ",59342]
["2024-07-20","2024-07-22","NE",3,"25","A+B","Y.ARENDSTRAAT","Y.BERCHEM-STADION","Weekend","Continuous","23:55","04:00","onderhoud wissels Y Noord Berchem","CTL","Medium"," "," ",59711]
["2024-07-21","2024-07-21","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59994]
["2024-07-21","2024-07-21","SE",3,"139","A/B","SINT-JORIS-WEERT","WAVRE","Weekend","Day","08:00","16:00","Visites des postes - maintenances diverses et révisions","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48880]
["2024-07-22","2024-07-27","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59873]
["2024-07-24","2024-07-24","NE",3,"25","B","ANTWERPEN-CENTRAAL","ANTWERPEN-CENTRAAL","Week","Day","10:00","15:00","onderhoud SIG L25Sp A (perron 23+24 antwerpen centraal -2)","SAVU","Minor_AdHoc"," "," ",59713]
["2024-07-25","2024-07-25","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55947]
["2024-07-26","2024-07-29","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: afwerking","CTL","Medium","TLO L161/1"," ",59576]
["2024-07-26","2024-07-29","NE",2,"35","A+B","AARSCHOT","LEUVEN","Weekend","Continuous","23:30","04:30","voor provinvie inschuiven tunnels,\r\nWIlsele L35 km 102.400\r\nWezemaal L35 km 97.400\r\n\r\n+\r\n\r\n+ werken AWV: vervangen dekstenen en leuning op een brug Vuntcomplex (L35 km 104.672)","CTL","Medium","alternatief E2943-E2622-E2872"," ",58670]
["2024-07-26","2024-07-29","NE",2,"53","A+B","MUIZEN-ROOSTER T","LEUVEN","Weekend","Continuous","23:20","05:00","herelectrificatie (bijkomend)\r\n\r\nsamen werken met colt 58336+58354","CTL","Medium","alternatief E2645-E2644"," ",60285]
["2024-07-26","2024-07-29","SE",3,"42","A+B","RIVAGE","AYWAILLE","Weekend","Continuous","23:50","04:50","Entretien manuel et mécanisés des AW de Rivage et Rivage Marchandise Entretien manuel et mécanisés des PN","CTL","Medium","Pas de circulation possible sur L43 depuis Tilff\r\nPas de circulation possible sur L42 depuis Tilff","HKM à adapter",55089]
["2024-07-26","2024-07-29","SE",3,"43","A+B","TILFF","BOMAL","Weekend","Continuous","23:50","04:50","Linked to coupure nr 55089 on line 42 tracks(s) A+B from RIVAGE to AYWAILLE: Entretien manuel et mécanisés des AW de Rivage et Rivage Marchandise Entretien manuel et mécanisés des PN","CTL","Medium"," ","HKM à adapter",55089]
["2024-07-27","2024-07-27","SE",3,"130","A/B","FLAWINNE","MOUSTIER","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49174]
["2024-07-27","2024-07-28","SE",3,"161","A/B","BAKENBOS","OTTIGNIES","Weekend","Day","08:00","16:00","Visite voies A/B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 08h00 et 16h00 le samedi et le dimanche,  avec adaptations trains"," ",48911]
["2024-07-27","2024-07-28","SW",2,"96","A+B","MONS","QUEVY-FRONTIERE","Weekend","Continuous","07:00","16:15","Maintenance  Z.11.53\r\nMise HS P4","CTL","Medium","CTL L96 + L97\r\n1 voie Hs en gare de Mons les autres sont accessibles en CDS","HKM à adapter",56798]
["2024-07-27","2024-07-28","SW",2,"97","A+B","SAINT-GHISLAIN","MONS","Weekend","Continuous","07:00","16:15","Linked to coupure nr 56798 on line 96 tracks(s) A+B from MONS to QUEVY-FRONTIERE: Maintenance  Z.11.53\r\nMise HS P4","CTL","Medium"," ","HKM à adapter",56798]
["2024-07-27","2024-07-29","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58026]
["2024-07-27","2024-07-29","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","migratie tunnelveiligheidtechnieken Antw NZ\r\nantwerpen centraal -antwerpen luchtbal","CTL","Medium"," "," ",59419]
["2024-07-28","2024-07-28","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","23:30","04:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nnog te bespreken of werken kunnen doorgaan","CTL","Minor_AdHoc"," "," ",59814]
["2024-07-28","2024-07-28","SE",3,"130","A/B","MOUSTIER","AUVELAIS","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49183]
["2024-07-28","2024-07-29","NW",3,"58","A+B","Y.NOORD DRIEHOEK LEDEBERG","GENT-DAMPOORT","Weekend","Continuous","00:50","04:00","Instandhouding Y Noord Driehoek Ledeberg\r\n2xTLO van 24u\r\nGent Dampoort perron vrij\r\nL50E vrij","CTL","Medium",null,null,60719]
["2024-07-28","2024-07-29","NW",3,"58(1)","A+B","Y.OOST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","00:50","04:00","Linked to coupure nr 60719 on line 58 tracks(s) A+B from Y.NOORD DRIEHOEK LEDEBERG to GENT-DAMPOORT: Instandhouding Y Noord Driehoek Ledeberg\r\n2xTLO van 24u\r\nGent Dampoort perron vrij\r\nL50E vrij","CTL","Medium"," ",null,60719]
["2024-07-28","2024-07-29","NW",3,"58/1","A+B","Y.NOORD DRIEHOEK LEDEBERG","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:50","04:00","Linked to coupure nr 60719 on line 58 tracks(s) A+B from Y.NOORD DRIEHOEK LEDEBERG to GENT-DAMPOORT: Instandhouding Y Noord Driehoek Ledeberg\r\n2xTLO van 24u\r\nGent Dampoort perron vrij\r\nL50E vrij","CTL","Medium"," ",null,60719]
["2024-07-29","2024-08-03","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59874]
["2024-07-31","2024-07-31","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60096]
["2024-08-01","2024-08-01","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60112]
["2024-08-02","2024-08-04","SE",3,"162","A+B","ROCHEFORT-JEMELLE","HATRIVAL","Weekend","Continuous","23:10","16:10","Rénovation Pont sur la Masblette (P.I.) bK 124.781","CTL","Medium","ART 1.2 min 2 semaines","Info Racc 5 : 1.N.101/1 (Lhoist Jemelle)",57383]
["2024-08-02","2024-08-04","SW",2,"96","A+B","BRAINE-LE-COMTE","Y.SOIGNIES","Weekend","Continuous","22:30","16:00","Maintenance Z2.53\r\nMise HS P4","CTL","Medium",null,"HKM à adapter",48650]
["2024-08-02","2024-08-05","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: afwerking","CTL","Medium","TLO L161/1"," ",59577]
["2024-08-02","2024-08-05","NE",2,"34","A+B","GLONS","HASSELT","Weekend","Continuous","23:30","04:00","onderhoud +vernieuwen van OW\r\n+\r\n\r\nafschaffen OW'en (colt 59815)","CTL","Medium"," "," ",59353]
["2024-08-02","2024-08-05","NE",3,"27","A+B","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL","Weekend","Night","23:50","04:00","onderhoud SIG + wissels Y arendstraat\r\n\r\nhangt samen met colt 59708","CTL","Minor_AdHoc","nog te bepalen"," ",59729]
["2024-08-02","2024-08-05","SE",3,"161","B","GEMBLOUX","RHISNES","Weekend","Continuous","23:00","05:00","réélectrification","SAVU","Minor_AdHoc","une voie en continu"," ",52664]
["2024-08-02","2024-08-05","SW",2,"94","A+B","ATH","LEUZE","Weekend","Continuous","23:20","04:40","Renforcement de 7 PI entre les km 54.992 et 63.375 sur la L94\r\nPhase 3.2 : PI 6+7","CTL","Medium","CTL de WE en continu"," ",57123]
["2024-08-03","2024-08-04","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60424]
["2024-08-03","2024-08-04","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60424 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60424]
["2024-08-03","2024-08-04","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60424 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60424]
["2024-08-03","2024-08-04","SE",2,"24","A+B","VISE-HAUT","MONTZEN-FRONTIERE","Weekend","Continuous","08:00","21:00","Entretien manuel et mécanisés des AW de Y. Berneau, Fourons, Rémersdael, Montzen, Botzelaer\r\nEntretien manuel et mécanisés de la voie courante + Tunnel de Veurs","CTL","Medium","Pas de circulation possible entre Visé et DB\r\nPas de ciculation entre Longchamps vers DB"," ",55966]
["2024-08-03","2024-08-04","SE",2,"24/1","A+B","Y.LONGCHAMPS","Y.BERNEAU","Weekend","Continuous","08:00","21:00","Linked to coupure nr 55966 on line 24 tracks(s) A+B from VISE-HAUT to MONTZEN-FRONTIERE: Entretien manuel et mécanisés des AW de Y. Berneau, Fourons, Rémersdael, Montzen, Botzelaer\r\nEntretien manuel et mécanisés de la voie courante + Tunnel de Veurs","CTL","Medium"," "," ",55966]
["2024-08-03","2024-08-04","SE",3,"161","A/B","GEMBLOUX","RHISNES","Weekend","Day","08:00","16:00","Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49198]
["2024-08-03","2024-08-04","SW",3,"112","A+B","LA LOUVIERE-SUD","LA LOUVIERE-CENTRE","Weekend","Continuous","06:00","17:00","Maintenance Z12.52","CTL","Medium"," "," ",60786]
["2024-08-03","2024-08-04","SW",3,"118","A","Y.LA PAIX","BRACQUEGNIES","Weekend","Continuous","06:00","17:00","Linked to coupure nr 60786 on line 112 tracks(s) A+B from LA LOUVIERE-SUD to LA LOUVIERE-CENTRE: Maintenance Z12.52","SAVU","Minor_AdHoc"," "," ",60786]
["2024-08-03","2024-08-04","SW",3,"118","A+B","Y.SAINT-VAAST","Y.LA PAIX","Weekend","Continuous","06:00","17:00","Linked to coupure nr 60786 on line 112 tracks(s) A+B from LA LOUVIERE-SUD to LA LOUVIERE-CENTRE: Maintenance Z12.52","CTL","Medium"," "," ",60786]
["2024-08-03","2024-08-05","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58027]
["2024-08-03","2024-08-05","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","migratie tunnelveiligheidtechnieken Antw NZ\r\nantwerpen centraal -antwerpen luchtbal","CTL","Medium"," "," ",59418]
["2024-08-03","2024-08-05","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","onderhoud SIG + onderhoud wissels Arendstraat  en Antwerpen centraal -2\r\n\r\nbeveiliging L27 s nachts door buitendienststelling overdag ATW-TX\r\n\r\nnog te bekijken","CTL","Medium"," "," ",59708]
["2024-08-03","2024-08-19","NE",1,"25","A+B","MECHELEN","Y.ABEELSTRAAT","AllWeek","Continuous","01:00","04:00","TLO lijn 25 van 16 dagen + 3 weekends van 3 dagen lijn 25N inbegrepen\r\nDit voor de ontmanteling Vierendeelbrug L25 over de vaart + inrijden nieuwe brug op dezelfde locatie\r\nZie goedgekeurd dossier: 2024 - L25 - 25N Mechelen-Y. Abeelstraat","CTL","High"," "," ",21754]
["2024-08-03","2024-08-19","NE",1,"25","A+B","VILVOORDE","Y.ABEELSTRAAT","AllWeek","Continuous","01:00","04:00","-TLO 2 weken continu (combinatie vierendeelbrug Leuvensevaart)\r\nRenovatie kruisingsbrug L27/L25 - geen impact L27\r\n\r\n-renovatie bruggen\r\n\r\n-vernieuwen waterdichte rok ONB Damstraat L25\r\nmeeliften met buitendienststellingen brug Leuvensevaart","CTL","High"," "," ",58517]
["2024-08-04","2024-08-05","NW",3,"58","A+B","Y.NOORD DRIEHOEK LEDEBERG","GENT-DAMPOORT","Weekend","Continuous","00:50","04:00","Instandhouding Y Noord Driehoek Ledeberg\r\n2xTLO van 24u\r\nGent Dampoort perron vrij\r\nL50E vrij","CTL","Medium",null,null,60718]
["2024-08-04","2024-08-05","NW",3,"58(1)","A+B","Y.OOST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","00:50","04:00","Linked to coupure nr 60718 on line 58 tracks(s) A+B from Y.NOORD DRIEHOEK LEDEBERG to GENT-DAMPOORT: Instandhouding Y Noord Driehoek Ledeberg\r\n2xTLO van 24u\r\nGent Dampoort perron vrij\r\nL50E vrij","CTL","Medium"," ",null,60718]
["2024-08-04","2024-08-05","NW",3,"58/1","A+B","Y.NOORD DRIEHOEK LEDEBERG","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:50","04:00","Linked to coupure nr 60718 on line 58 tracks(s) A+B from Y.NOORD DRIEHOEK LEDEBERG to GENT-DAMPOORT: Instandhouding Y Noord Driehoek Ledeberg\r\n2xTLO van 24u\r\nGent Dampoort perron vrij\r\nL50E vrij","CTL","Medium"," ",null,60718]
["2024-08-05","2024-08-09","NE",2,"53","A+B","MUIZEN-ROOSTER T","LEUVEN","Week","Night","23:20","05:00","herelectrificatie (bijkomend)","CTL","Minor_AdHoc","alternatief E2645-E2644"," ",60286]
["2024-08-05","2024-08-09","SW",2,"112","A+B","Y.MARTINET","LA LOUVIERE-SUD","Week","Night","22:50","04:40","Pose de murs de soutènements + pistes / caniveaux  + micro Pieux entre PN3 et PN5\r\n+  Renouvellement LRS Piéton -Y.Martinet\r\n+ Renouvellement AW LVRS côté Charleroi\r\nPréparations","CTL","Minor_AdHoc",null," ",59338]
["2024-08-05","2024-08-09","SW",2,"130A","A+B","Y.NORD","ERQUELINNES-FRONTIERE","Week","Night","22:30","04:10","Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires caténaire (transfert caténaires)\r\n+ Travaux signalisation PN 107, 108, 109 et 114\r\n+ Travaux voie A signalisation","CTL","Minor_AdHoc","la liaison 08AK/BK sera hors exploitation à partir du 8/08 à 4h JNA (2026)","HKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",55940]
["2024-08-05","2024-08-10","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59875]
["2024-08-05","2024-09-07","SW",1,"96","B","MONS","JURBISE","Week","Night","22:50","05:10","Réélectrification - Phase 5 - 2024\r\nDépose anciens poteaux","SAVU","Minor_AdHoc",null,"HKM à adapter",47570]
["2024-08-06","2024-08-10","NW",2,"58","A+B","GENT-DAMPOORT","Y.BOMA","Week","Night","00:30","04:30","Linked to coupure nr 59212 on line 59 tracks(s) A+B from Y.BERNADETTESTRAAT to GENT-DAMPOORT: Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I","CTL","Minor_AdHoc"," "," ",59212]
["2024-08-06","2024-08-10","NW",2,"59","A+B","Y.BERNADETTESTRAAT","GENT-DAMPOORT","Week","Night","00:30","04:30","Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I","CTL","Minor_AdHoc"," "," ",59212]
["2024-08-09","2024-08-12","CE",1,"27E","*","Y.SCHAERBEEK-GROUPE G","SCHAERBEEK-CUL DE SAC 814","Weekend","Continuous","23:50","04:30","Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","Autre","Minor_AdHoc","Sporen 705 tem 712 bundel G onbeschikbaar.\r\nGoederenas door FSR afgesloten."," ",56216]
["2024-08-09","2024-08-12","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-SAS K/C","Weekend","Continuous","23:50","04:30","Linked to coupure nr 56216 on line 27E tracks(s) * from Y.SCHAERBEEK-GROUPE G to SCHAERBEEK-CUL DE SAC 814: Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","CTL","Medium"," "," ",56216]
["2024-08-09","2024-08-12","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: afwerking","CTL","Medium","TLO L161/1"," ",59578]
["2024-08-09","2024-08-12","NE",2,"12","A+B","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-SCHIJNPOORT","Weekend","Continuous","22:30","05:30","onderhoud wissels en sporen te Antwerpen-Oost \r\nL27/1 tussen Antwerpen-Oost en Noord-Berchem eveneens BD\r\n\r\nHangt samen met COlt 60220 , werken onderhoud bundel E","CTL","Medium","geen verkeer L27/1 tss Noord-Berchem en Antwerpen-Oost"," ",60221]
["2024-08-09","2024-08-12","NE",2,"12","A+B","ANTWERPEN-OOST","Y.HOLLAND","Weekend","Continuous","22:30","05:30","onderhoud wissels en sporen te Antwerpen Schijnpoort inrit bundel E inclusief bundelkoppen C,E\r\n\r\nverlenging van BD stelling op 11/08  colt 60221 (tot Antwerpen-Centraal)","Autre","Minor_AdHoc","geen toegang tot bundel E\r\ngeen toegang bundel D kant Y antwerpen-Oost"," ",60220]
["2024-08-09","2024-08-12","NE",2,"21C","S","Y.BOSDEL","Y.NIEUWDAK","Weekend","Continuous","23:40","04:00","Vervanging ONB Dominikanenlaan km 29.833\r\n\r\n\r\n\r\n\r\n\r\n\r\nR-431786-01","CTL","Medium","geen toegang tot L230"," ",61660]
["2024-08-09","2024-08-12","NE",2,"230","A+B","Y.BOSDEL","ZUTENDAAL","Weekend","Continuous","23:40","04:00","Linked to coupure nr 61660 on line 21C tracks(s) S from Y.BOSDEL to Y.NIEUWDAK: Vervanging ONB Dominikanenlaan km 29.833\r\n\r\n\r\n\r\n\r\n\r\n\r\nR-431786-01","CTL","Medium"," "," ",61660]
["2024-08-09","2024-08-12","NE",2,"27/1","A+B","Y.NOORD BERCHEM","Y.ANTWERPEN-OOST","Weekend","Continuous","22:30","05:30","Linked to coupure nr 60221 on line 12 tracks(s) A+B from ANTWERPEN-CENTRAAL to Y.ANTWERPEN-SCHIJNPOORT: onderhoud wissels en sporen te Antwerpen-Oost \r\nL27/1 tussen Antwerpen-Oost en Noord-Berchem eveneens BD\r\n\r\nHangt samen met COlt 60220 , werken onder","CTL","Medium"," "," ",60221]
["2024-08-09","2024-08-12","SE",2,"42","A+B","TROIS-PONTS","GOUVY","Weekend","Continuous","23:50","05:00","Renouvellement liaison 31","CTL","Medium","CTL entre Trois-Ponts (non compris) et Gouvy (non compris)\r\nART 2.4 minutes du 12/08/24 au 21/08/24"," ",59318]
["2024-08-09","2024-08-12","SE",3,"130","A","HAM-SUR-SAMBRE","AUVELAIS","Weekend","Continuous","23:00","05:00","électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu","SAVU","Minor_AdHoc","une voie hors service en continu","HKM à adapter",47155]
["2024-08-09","2024-08-12","SE",3,"161","B","GEMBLOUX","RHISNES","Weekend","Continuous","23:00","05:00","réélectrification","SAVU","Minor_AdHoc","une voie en continu"," ",52665]
["2024-08-09","2024-08-12","SW",1,"130A","A+B","CHARLEROI-SUD","LA SAMBRE","Weekend","Continuous","23:00","04:10","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+L132","CTL","Medium","CTL L130A + L132","a déterminer",48245]
["2024-08-09","2024-08-12","SW",3,"90","A+B","GERAARDSBERGEN","ATH","Weekend","Continuous","22:30","04:30","ETCS\r\nRéglage de sécurité et CV","CTL","Medium","Coupure des signaux MX-F.37 à DX-M.37 et M-F.37 à E-M.37","InfoRacc",57450]
["2024-08-09","2024-08-19","CE",1,"161/2","*","BRUXELLES-NORD","BRUXELLES-NORD","AllWeek","Continuous","23:00","05:00","Vernieuwing perronboorden en perronverharding perron 8 FBN.","SAVU","High","Perronspoor 8 onbeschikbaar in continu.\r\nBijkomend tijdens de weekends perronspoor 9 en tijdens de nachten perronsporen 7 en 9."," ",49989]
["2024-08-09","2024-08-26","SW",1,"112","B","Y.MARTINET","LA LOUVIERE-SUD","AllWeek","Continuous","23:30","04:30","Pose de murs de soutènements + pistes / caniveaux  + micro Pieux entre PN3 et PN5\r\n+  Renouvellement LRS Piéton -Y.Martinet\r\n+ Renouvellement AW LVRS côté Charleroi","CTL","High","2 quais disponibles à La Louvière Sud\r\n+ ART stabilisation"," ",47791]
["2024-08-09","2024-08-26","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","AllWeek","Continuous","23:00","04:10","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nCTL 17 jours continu\r\n+ Travaux voie A signalisation","CTL","High","CTL L130A 17 jours\r\nDurant les WE CTL L130A+L132","HKM à adapter",48235]
["2024-08-09","2024-10-14","CE",1,"27E","*","SCHAERBEEK-GRIL G","SCHAERBEEK-CUL DE SAC 814","AllWeek","Continuous","23:00","04:30","Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712","Autre","Minor_AdHoc","Sporen 705 tem 712 bundel G onbeschikbaar.\r\nUitbreidingen tijdens de nachten en weekends."," ",49963]
["2024-08-09","2024-08-12","SE",2,"154","A/B","YVOIR","Y.NEFFE","Weekend","Continuous","23:00","05:00","Entretien AS , traitement zone boueuse","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 12/08 au 15/08 (fin probable)"," ",57694]
["2024-08-10","2024-08-11","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61586]
["2024-08-10","2024-08-11","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59426]
["2024-08-10","2024-08-11","SW",3,"124","A+B","NIVELLES","LUTTRE","Weekend","Continuous","06:00","17:00","Maintenance Z04.52","CTL","Medium","Voie VI Nivelles Inaccessible\r\nVoie I et II Luttre Inaccessible"," ",60785]
["2024-08-10","2024-08-12","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58028]
["2024-08-10","2024-08-12","NW",2,"204","A+B","GENT-ZEEHAVEN-SIFFERDOK","GENT-RODENHUIZE","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 07bis Piratenstraat; brug intern havenverkeer en fietsbrug","CTL","Medium",null,"Info Racc.",58491]
["2024-08-10","2024-08-12","NW",2,"59","A+B","LOKEREN","GENT-DAMPOORT","Weekend","Continuous","00:30","04:30","P143: afschaffen overwegen NW\r\nafschaffen overweg 58 L59 - Bormtestraat, Lokeren\r\nlangsweg\r\n\r\n*Lokeren\r\n- Inrit L57 naar SP A moet beschikbaar blijven\r\n- Rooster L59 kant Gent BD tot aan perronseinen - perron IV inbegrepen, overige perrons NIET IN\r\n- ge","CTL","Medium"," "," ",58416]
["2024-08-11","2024-08-11","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61613]
["2024-08-11","2024-08-11","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nnog te bespreken of werken kunnen doorgaan","CTL","Minor_AdHoc"," "," ",59995]
["2024-08-11","2024-08-11","NE",3,"59/1","A","ANTWERPEN-CENTRAAL","Y.NOORD BERCHEM","Weekend","Day","06:00","20:00","spoor A onderhoud SIG\r\nsamen met L12 \r\ntot perronkoppen 3-4-5-6","SAVU","Minor_AdHoc","DOES op spoor B"," ",60222]
["2024-08-12","2024-08-16","NE",2,"53","A+B","MUIZEN-ROOSTER T","LEUVEN","Week","Night","23:20","05:00","herelectrificatie (bijkomend)","CTL","Minor_AdHoc","alternatief E2645-E2644"," ",60287]
["2024-08-12","2024-08-16","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59876]
["2024-08-12","2024-08-17","SE",3,"42","A+B","TROIS-PONTS","GOUVY","Week","Night","23:30","05:00","Renouvellement liaison 31 - travaux de finitions","CTL","Minor_AdHoc","Trois-Ponts (non compris) et Gouvy (non compris)\r\nART 2.4 minutes du 12/08/24 au 21/08/24"," ",59319]
["2024-08-12","2024-08-21","SE",2,"42","A+B","TROIS-PONTS","GOUVY","AllWeek","Continuous","05:00","23:00","ART 2.4min\r\nRenouvellement liaison 31","ART","Minor_AdHoc",null," ",59605]
["2024-08-13","2024-08-16","NW",2,"58","A+B","GENT-DAMPOORT","Y.BOMA","Week","Night","00:30","04:30","Linked to coupure nr 59215 on line 59 tracks(s) A+B from Y.BERNADETTESTRAAT to GENT-DAMPOORT: Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I\r\n- R5/R6 in weekend TLO","CTL","Minor_AdHoc"," "," ",59215]
["2024-08-13","2024-08-16","NW",2,"59","A+B","Y.BERNADETTESTRAAT","GENT-DAMPOORT","Week","Night","00:30","04:30","Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I\r\n- R5/R6 in weekend TLO","CTL","Minor_AdHoc"," "," ",59215]
["2024-08-13","2024-08-16","NW",3,"204","A+B","GENT-ZEEHAVEN-SIFFERDOK","GENT-RODENHUIZE","Week","Night","00:10","04:00","227331 R4WO knooppunt 07bis Piratenstraat; brug intern havenverkeer en fietsbrug\r\n\r\n* R5/R6 in weekend TLO","CTL","Minor_AdHoc",null,"Info Racc.",58497]
["2024-08-14","2024-08-19","SE",3,"162","A+B","HAVERSIN","ROCHEFORT-JEMELLE","Weekend","Continuous","23:40","04:20","Travaux caténaire .\r\nmassifs / poteaux/ CDPA / feeder / R3 mixte / démontage caténaire existante","CTL","Medium","WE 4 jours (15/08 en R4)"," ",60136]
["2024-08-16","2024-08-19","CE",1,"27E","*","Y.SCHAERBEEK-GROUPE G","SCHAERBEEK-CUL DE SAC 814","Weekend","Continuous","23:50","04:30","Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","Autre","Minor_AdHoc","Sporen 705 tem 712 bundel G onbeschikbaar.\r\nGoederenas door FSR afgesloten."," ",56217]
["2024-08-16","2024-08-19","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-SAS K/C","Weekend","Continuous","23:50","04:30","Linked to coupure nr 56217 on line 27E tracks(s) * from Y.SCHAERBEEK-GROUPE G to SCHAERBEEK-CUL DE SAC 814: Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","CTL","Medium"," "," ",56217]
["2024-08-16","2024-08-19","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: afwerking","CTL","Medium","TLO L161/1"," ",59580]
["2024-08-16","2024-08-19","NE",1,"27A","A+B","ANTWERPEN-NOORDERDOKKEN","Y.DRIEHOEKSTRAAT","Weekend","Continuous","23:30","04:00","304 statiestraat tussen Y laarsebeek en Y schijn","CTL","Medium"," "," ",58232]
["2024-08-16","2024-08-19","NE",2,"35","A+B","HASSELT","Y.ZUID DRIEHOEK AARSCHOT","Weekend","Continuous","23:50","04:00","onderhoud \r\n\r\ndata kan nog wijzigen","CTL","Medium"," "," ",60178]
["2024-08-16","2024-08-19","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59913]
["2024-08-16","2024-08-19","NW",2,"59","A+B","LOKEREN","GENT-DAMPOORT","Weekend","Continuous","00:30","04:30","- brug station Beervelde\r\n+\r\n- onderhoud\r\n+\r\nFGDM - Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n\r\n*Lokeren\r\n- Inrit L57 naar SP A moet beschikbaar blijven\r\n- Rooster L59 kant Gent BD tot aan perronseinen - perron IV inbegrepen, overige perrons NIET IN\r\n","CTL","Medium"," "," ",57629]
["2024-08-16","2024-08-19","SE",1,"161","B","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:45","WE SAVU RER Bakenbos-Ottignies","SAVU_CTRL","Minor_AdHoc","ART à définir, maximum 2'"," ",49250]
["2024-08-16","2024-08-19","SE",3,"130","A","HAM-SUR-SAMBRE","AUVELAIS","Weekend","Continuous","23:00","05:00","électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu","SAVU","Minor_AdHoc","une voie hors service en continu","HKM à adapter",47156]
["2024-08-16","2024-08-19","SW",1,"130A","A+B","CHARLEROI-SUD","LA SAMBRE","AllWeek","Continuous","23:00","04:10","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+L132","CTL","Medium","CTL L130A + L132\r\nART de stabilisation Y La Sambre: 0,82min du 18/08/2024 au 15/09/2024","HKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",48244]
["2024-08-17","2024-08-18","SW",3,"116","A+B","MANAGE","LA LOUVIERE-GARE INDUSTRIELLE","Weekend","Continuous","06:00","22:00","Maintenance Z10.52\r\nMise HS P4 - Zone 10 AI52\r\nTravaux de maintenance pendant la fermeture NLMK\r\nRq 333 : HKV via L116-117 à laisser passer suite CTL L112\r\nRq EF's HKV à laisser passer suite CTL L112","CTL","Medium"," "," ",49151]
["2024-08-17","2024-08-18","SW",3,"116/1","A+B","Y.BOIS-D'HAINE","Y.FAMILLEUREUX","Weekend","Continuous","06:00","22:00","Linked to coupure nr 49151 on line 116 tracks(s) A+B from MANAGE to LA LOUVIERE-GARE INDUSTRIELLE: Maintenance Z10.52\r\nMise HS P4 - Zone 10 AI52\r\nTravaux de maintenance pendant la fermeture NLMK\r\nRq 333 : HKV via L116-117 à laisser passer suite CTL L112","CTL","Medium"," "," ",49151]
["2024-08-17","2024-08-19","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58029]
["2024-08-17","2024-08-19","NW",2,"204","A+B","GENT-ZEEHAVEN-SIFFERDOK","GENT-RODENHUIZE","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 07bis Piratenstraat; brug intern havenverkeer en fietsbrug","CTL","Medium",null,"Info Racc.",58492]
["2024-08-17","2024-08-19","NW",3,"123","A+B","FRONT. WALLONIE-FLANDRE L123","GERAARDSBERGEN","Weekend","Continuous","06:00","04:20","Linked to coupure nr 60172 on line 90 tracks(s) A+B from LESSINES to GERAARDSBERGEN: Onderhoud ABL\r\nperron I-II-III FGRA inbegrepen","CTL","Medium"," "," ",60172]
["2024-08-17","2024-08-19","NW",3,"90","A+B","LESSINES","GERAARDSBERGEN","Weekend","Continuous","06:00","04:20","Onderhoud ABL\r\nperron I-II-III FGRA inbegrepen","CTL","Medium",null," ",60172]
["2024-08-17","2024-08-26","CE",2,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","AllWeek","Continuous","06:00","04:50","Massificatie samen met lange TLO RER:\r\n1) Onderhoudszone FBMZ_19, FBKI_03 en FH_06 Area CE volgens onderhoudskalender 2024.\r\nSporen A en B 124 buiten dienst, inclusief L28/3\r\n2) Vernieuwing brug Brusselsestwg \r\n\r\nPerrons en bundel Charleroi moeten vrijb","CTL","High",null," ",58962]
["2024-08-17","2024-08-26","CE",2,"28/3","S","Y.FOREST-EST","Y.CUREGHEM","AllWeek","Continuous","06:00","04:50","Linked to coupure nr 58962 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: Massificatie samen met lange TLO RER:\r\n1) Onderhoudszone FBMZ_19, FBKI_03 en FH_06 Area CE volgens onderhoudskalender 2024.\r\nSporen A en B 124 buiten dienst, in","CTL","High"," "," ",58962]
["2024-08-17","2024-08-26","SW",1,"124","A+B","BAULERS-GRIL D","Y.FOREST-EST","AllWeek","Continuous","06:00","04:50","RER Réaménagement des voies et aiguillages à Baulers vers Nivelles.\r\nPhase 4\r\nDossier de concertation validé","CTL","High",null," ",52195]
["2024-08-18","2024-08-18","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59996]
["2024-08-19","2024-08-19","SE",3,"130","A/B","NAMUR","FLAWINNE","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49063]
["2024-08-19","2024-08-23","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:30","vernieuwen spoor L54,OW2 en AW01H","CTL","Minor_AdHoc"," "," ",58294]
["2024-08-19","2024-08-23","NE",3,"19","A+B","MOL","HAMONT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt\r\n+\r\nvernieuwing OW'en + onderhoud\r\n\r\nmeewerken met werken aanleg 2de spoor mogelijk (geen mogelijkheid tot werken tussen kp10 en kp 16) (colt 59929)","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59877]
["2024-08-19","2024-08-23","SW",1,"130A","B","Y.NORD","LA SAMBRE","AllWeek","Continuous","05:00","23:00","Renouvellement AS Y. La Sambre","SAVU","Minor_AdHoc","La VB L130A restera HS pour les travaux (en // L130A 48235) et (en // 59252 SAVU L132), mais il faut préciser que le tronçon entre K-K. 20 et E-G. 20 + les 2 voies L124A/1 seront HS toujours pour travaux.","InfoRacc\r\nAccès L132 vers Monceau impossible",59474]
["2024-08-19","2024-08-24","SE",3,"42","A+B","TROIS-PONTS","GOUVY","Week","Night","23:10","05:00","Renouvellement liaison 31 - travaux de finitions - bourrage de révision - incorporation des AS","CTL","Minor_AdHoc","CTL min 06h entre Trois-Ponts (non compris) et Gouvy (non compris)\r\nART 2.4 minutes du 12/08/24 au 21/08/24"," ",59320]
["2024-08-19","2024-09-02","NE",1,"53","A/B","HAACHT-WIJKSPOOR","LEUVEN","AllWeek","Continuous","23:30","04:30","Linked to coupure nr 49888 on line 53 tracks(s) A+B from MECHELEN to HAACHT: Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nTijdens de weekends uitbreiding tot Leuven\r\n\r\nvernieuwen Muizen rooster T ( ==> colt 58337)\r\n(samen met L27B","SAVU","High"," "," ",49888]
["2024-08-19","2024-09-02","NE",1,"53","A+B","MECHELEN","HAACHT","AllWeek","Continuous","23:30","04:30","Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nTijdens de weekends uitbreiding tot Leuven\r\n\r\nvernieuwen Muizen rooster T ( ==> colt 58337)\r\n(samen met L27B)(","CTL","High","Navettedienst op 1 spoor mogelijk tussen Haacht en Leuven"," ",49888]
["2024-08-20","2024-08-23","NW",2,"50A","A+B","Y.SINT-KATHERINA-LOMBEEK","GENT-SINT-PIETERS","Week","Night","00:30","04:30","Nieuwe Voetbrug  Wetteren KP39.100 - 39.300\r\n+\r\nFGSP SP X-XI-XII inbegrepen voor onderhoud wissels\r\n\r\n\r\n* R5/R6 in weekend TLO","CTL","Minor_AdHoc",null," ",58567]
["2024-08-20","2024-08-24","NW",2,"58","A+B","GENT-DAMPOORT","Y.BOMA","Week","Night","00:30","04:30","Linked to coupure nr 59216 on line 59 tracks(s) A+B from Y.BERNADETTESTRAAT to GENT-DAMPOORT: Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I","CTL","Minor_AdHoc"," "," ",59216]
["2024-08-20","2024-08-24","NW",2,"59","A+B","Y.BERNADETTESTRAAT","GENT-DAMPOORT","Week","Night","00:30","04:30","Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I","CTL","Minor_AdHoc"," "," ",59216]
["2024-08-21","2024-08-21","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60097]
["2024-08-22","2024-08-22","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc","eventueel beperkte indienstgave voor doorrit trein"," ",60113]
["2024-08-23","2024-08-26","CE",1,"27E","*","Y.SCHAERBEEK-GROUPE G","SCHAERBEEK-CUL DE SAC 814","Weekend","Continuous","23:50","04:30","Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","Autre","Minor_AdHoc","Sporen 705 tem 712 bundel G onbeschikbaar.\r\nGoederenas door FSR afgesloten."," ",56218]
["2024-08-23","2024-08-26","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-SAS K/C","Weekend","Continuous","23:50","04:30","Linked to coupure nr 56218 on line 27E tracks(s) * from Y.SCHAERBEEK-GROUPE G to SCHAERBEEK-CUL DE SAC 814: Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","CTL","Medium"," "," ",56218]
["2024-08-23","2024-08-26","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","21:30","05:50","P008 518: Op dubbel spoor brengen L161/1: afwerking","CTL","Medium","TLO L161/1"," ",59581]
["2024-08-23","2024-08-26","CE",2,"96B","*","FOREST-VOITURES-QUAI SERVICE","FOREST-VOITURES","Weekend","Continuous","22:30","04:30","Onderhoudswerken volgen Onderhoudskalender Area CE, zone FBKI_13, Bundel Expo.\r\nVolledige bundel ter beschikking voor diverse onderhoudswerken.","Autre","Minor_AdHoc","Bundel Expo volledig buiten dienst","Néant",58631]
["2024-08-23","2024-08-26","NE",2,"19","A+B","MOL","HAMONT","Weekend","Continuous","22:00","05:00","vernieuwing OW'en + onderhoud\r\n\r\nmeewerken met werken aanleg 2de spoor mogelijk (geen mogelijkheid tot werken tussen kp10 en kp 16)\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (colt 59914)","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59932]
["2024-08-23","2024-08-26","NE",3,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-BERCHEM","Weekend","Continuous","23:55","04:00","Lijn 27 sp. B samen met Lijn 59/1 sp. A, met een correcte beveiliging Indringing type II op L59/1 spoor B.\r\nL59/1 sp A: Y West Berchem J-F.12 tot Y West Berchem J-F.12\r\nL27 sp B: Y Noord Groenenhoek M-F.12 tot Y Arenstraat JX-G.12","CTL","Medium","Lijn 27 sp. B samen met Lijn 59/1 sp. A, met een correcte beveiliging Indringing type II op L59/1 spoor B.\r\nL59/1 sp A: Y West Berchem J-F.12 tot Y West Berchem J-F.12\r\nL27 sp B: Y Noord Groenenhoek M-F.12 tot Y Arenstraat JX-G.12"," ",59715]
["2024-08-23","2024-08-26","NE",3,"59/1","A","Y.ARENDSTRAAT","Y.WEST BERCHEM","Weekend","Continuous","23:55","04:00","Linked to coupure nr 59715 on line 27 tracks(s) A+B from Y.ARENDSTRAAT to ANTWERPEN-BERCHEM: Lijn 27 sp. B samen met Lijn 59/1 sp. A, met een correcte beveiliging Indringing type II op L59/1 spoor B.\r\nL59/1 sp A: Y West Berchem J-F.12 tot Y West Berchem","SAVU","Minor_AdHoc"," "," ",59715]
["2024-08-23","2024-08-26","SE",3,"130","A","HAM-SUR-SAMBRE","AUVELAIS","Weekend","Continuous","23:00","05:00","électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu","SAVU","Minor_AdHoc","une voie hors service en continu","HKM à adapter",47157]
["2024-08-23","2024-08-26","SW",1,"130A","A+B","CHARLEROI-SUD","LA SAMBRE","Weekend","Continuous","23:00","04:10","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+L132\r\n+ Renouvellement des as Y La Sambre \r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","CTL L130A + L132\r\nART de stabilisation Y La Sambre: 0,82min du 18/08/2024 au 15/09/2024","HKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",48243]
["2024-08-24","2024-08-25","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60411]
["2024-08-24","2024-08-25","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60411 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60411]
["2024-08-24","2024-08-25","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60411 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60411]
["2024-08-24","2024-08-25","SE",3,"161","A/B","OTTIGNIES","GEMBLOUX","Weekend","Day","08:00","16:00","Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles + 1/2h sas Rhisnes","SAVU","Minor_AdHoc","SAVU alternatif entre 08h00 et 16h00"," ",48953]
["2024-08-24","2024-08-25","SW",3,"116","*","LA LOUVIERE-GARE INDUSTRIELLE","LA LOUVIERE-GARE INDUSTRIELLE","Weekend","Continuous","06:00","17:00","Maintenance Z17.52\r\nMise HS P4 - Zone 17 AI52","Autre","Minor_AdHoc","Mise HS des voies Accessoires du faisceau de GLI\r\nP4","InfoRacc",49154]
["2024-08-24","2024-08-26","NE",1,"27B","A+B","Y.PRINSENHOEK","Y.MUIZEN","Weekend","Continuous","00:00","04:00","vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58355]
["2024-08-24","2024-08-26","NE",1,"53","A+B","Y.HEVER","MUIZEN","Weekend","Continuous","00:00","04:00","Linked to coupure nr 58355 on line 27B tracks(s) A+B from Y.PRINSENHOEK to Y.MUIZEN: vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58355]
["2024-08-24","2024-08-26","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58030]
["2024-08-24","2024-08-26","NE",3,"12","A+B","Y.LUCHTBAL","Y.SINT-MARIABURG","Weekend","Continuous","06:00","04:10","Oude landen project 308+304","CTL","Medium","Aan deze werken is een R7 (van 06h00 tot 17h30) gekoppeld op L27A voor het spoorgedeelte Y.Laarsebeek - Y.Schijn!! (58664)"," ",58643]
["2024-08-24","2024-08-26","NW",2,"50A","A+B","Y.SINT-KATHERINA-LOMBEEK","GENT-SINT-PIETERS","Weekend","Continuous","01:10","04:30","Onderhoud AW 23H-24AH-24BH-21BH-18AH-09AH-09BH-10AH-10BH-14G-15G-12AG-12BG-11AG-11BG+ Plaatsen bekabeling via aanneming \r\n\r\nFGSP SP X-XI-XII inbegrepen v","CTL","Medium",null," ",58565]
["2024-08-24","2024-08-26","NW",2,"50A/4","A+B","Y.MELLE","Y.MEULEWIJK","Weekend","Continuous","01:10","04:30","Linked to coupure nr 58565 on line 50A tracks(s) A+B from Y.SINT-KATHERINA-LOMBEEK to GENT-SINT-PIETERS: Onderhoud AW 23H-24AH-24BH-21BH-18AH-09AH-09BH-10AH-10BH-14G-15G-12AG-12BG-11AG-11BG+ Plaatsen bekabeling via aanneming \r\n\r\nFGSP SP X-XI-XII inbegre","CTL","Medium"," "," ",58565]
["2024-08-24","2024-08-26","SE",1,"24","A+B","Y.BERNEAU","MONTZEN-GRIL Q","Weekend","Continuous","00:40","04:00","Entretien manuel et mécanisé des AW de Fourons, Rémersdael, Y. Berneau\r\nEntretien manuel et mécanisés de la voie courante + Tunnel de Veurs","CTL","Medium","Pas de circulation possible entre Visé et Montzen"," ",55118]
["2024-08-24","2024-08-26","SE",1,"24/1","A+B","Y.LONGCHAMPS","Y.BERNEAU","Weekend","Continuous","00:40","04:00","Linked to coupure nr 55118 on line 24 tracks(s) A+B from Y.BERNEAU to MONTZEN-GRIL Q: Entretien manuel et mécanisé des AW de Fourons, Rémersdael, Y. Berneau\r\nEntretien manuel et mécanisés de la voie courante + Tunnel de Veurs","CTL","Medium"," "," ",55118]
["2024-08-25","2024-08-25","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","06:00","17:40","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58664]
["2024-08-25","2024-08-25","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59997]
["2024-08-25","2024-09-09","SE",1,"162","A","CINEY","HAVERSIN","AllWeek","Continuous","22:50","05:00","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 12 : SAVU VA HS continu (àld ART 5')","SAVU_CTRL","High",null," ",58231]
["2024-08-26","2024-08-29","NE",2,"53","A+B","MECHELEN","LONDERZEEL","Week","Night","23:50","04:00","vernieuwen spoor L54,OW2 en AW10H","CTL","Minor_AdHoc"," "," ",58313]
["2024-08-26","2024-08-30","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:00","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Minor_AdHoc"," "," ",58295]
["2024-08-26","2024-08-30","SW",1,"124","A+B","NIVELLES","Y.FOREST-EST","Week","Night","23:35","04:50","RER Réaménagement des voies et aiguillages à Baulers vers Nivelles.\r\nPhase 4bis\r\nDossier de concertation validé","CTL","Minor_AdHoc","Nuits CTL \r\n+ Restrictions en continu à Nivelles : 3 quais sur 4 disponibles"," ",53149]
["2024-08-26","2024-08-31","NE",2,"19","A+B","MOL","HAMONT","Week","Night","22:00","05:00","vernieuwing OW'en + onderhoud\r\n\r\nmeewerken met werken aanleg 2de spoor mogelijk (geen mogelijkheid tot werken tussen kp10 en kp 16)\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (Colt 59878)","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59930]
["2024-08-26","2024-08-31","NE",3,"12","A+B","ANTWERPEN-NOORDERDOKKEN","Y.HOLLAND","Week","Night","23:25","04:00","onderheid SIG Y luchtbal en onderhoud wissel Y Antwerpen-luchtbal","CTL","Minor_AdHoc","alternatief E2573-E2594"," ",60121]
["2024-08-26","2024-08-31","SW",1,"130A","A+B","CHARLEROI-SUD","ERQUELINNES-FRONTIERE","Week","Night","23:00","04:10","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nRenouvellement des AS de Y.La Sambre\r\nSem. nuits CTL L130A+132  Finitions","CTL","Minor_AdHoc","CTL L130A + L132","HKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",49237]
["2024-08-26","2024-08-31","SW",2,"112","B","Y.MARTINET","LA LOUVIERE-SUD","Week","Night","22:50","04:40","Pose de murs de soutènements + pistes / caniveaux  + micro Pieux entre PN3 et PN5\r\n+  Renouvellement LRS Piéton -Y.Martinet\r\n+ Renouvellement AW LVRS côté Charleroi\r\nFinitions","CTL","Minor_AdHoc",null," ",59339]
["2024-08-26","2024-09-07","CE",1,"124","A+B","BRUXELLES-MIDI","Y.LINKEBEEK","AllWeek","Continuous","04:00","04:00","BTS na werken Brusselsestwg","ART","Minor_AdHoc","BTS 60 km/h"," ",52881]
["2024-08-27","2024-08-30","NW",3,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Week","Night","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Minor_AdHoc",null,"Info Racc",57799]
["2024-08-27","2024-08-31","NW",2,"50A","A+B","Y.SINT-KATHERINA-LOMBEEK","GENT-SINT-PIETERS","Week","Night","00:30","04:30","Nieuwe Voetbrug  Wetteren KP39.100 - 39.300\r\n+\r\nFGSP SP X-XI-XII inbegrepen voor onderhoud wissels","CTL","Minor_AdHoc",null," ",58568]
["2024-08-27","2024-08-31","NW",2,"58","A+B","GENT-DAMPOORT","Y.BOMA","Week","Night","00:30","04:30","Linked to coupure nr 59217 on line 59 tracks(s) A+B from Y.BERNADETTESTRAAT to GENT-DAMPOORT: Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I","CTL","Minor_AdHoc"," "," ",59217]
["2024-08-27","2024-08-31","NW",2,"59","A+B","Y.BERNADETTESTRAAT","GENT-DAMPOORT","Week","Night","00:30","04:30","Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I","CTL","Minor_AdHoc"," "," ",59217]
["2024-08-29","2024-08-29","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55949]
["2024-08-30","2024-09-02","CE",1,"161","A/B","WATERMAEL","BAKENBOS","Weekend","Continuous","23:30","04:50","WE SAVU RER Watermael-Bakenbos","SAVU_CTRL","Minor_AdHoc","ART à définir - maximum 2'"," ",49256]
["2024-08-30","2024-09-02","NE",1,"27B","A+B","Y.PRINSENHOEK","Y.MUIZEN","Weekend","Continuous","23:30","04:00","vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58356]
["2024-08-30","2024-09-02","NE",1,"53","A+B","Y.HEVER","MUIZEN","Weekend","Continuous","23:30","04:00","Linked to coupure nr 58356 on line 27B tracks(s) A+B from Y.PRINSENHOEK to Y.MUIZEN: vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58356]
["2024-08-30","2024-09-02","NE",2,"19","A+B","MOL","HAMONT","Weekend","Continuous","22:00","05:00","vernieuwing OW'en + onderhoud\r\n\r\nmeewerken met werken aanleg 2de spoor mogelijk (geen mogelijkheid tot werken tussen kp10 en kp 16)\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (colt 59915)","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59933]
["2024-08-30","2024-09-02","NE",3,"230","A+B","Y.BOSDEL","ZUTENDAAL","Weekend","Continuous","23:00","05:00","Onderhoud","CTL","Medium"," "," ",59970]
["2024-08-30","2024-09-02","SE",1,"166","A+B","BEAURAING","BERTRIX","Weekend","Continuous","23:00","04:30","Renouvellement traverses (P93)","CTL","Medium","P93 entre 60.996-63.396"," ",47790]
["2024-08-30","2024-09-02","SW",1,"124","A+B","NIVELLES","Y.FOREST-EST","Weekend","Continuous","23:35","04:50","RER Réaménagement des voies et aiguillages à Baulers vers Nivelles.\r\nPhase 4 ter\r\nDossier de concertation validé","CTL","Medium",null," ",53150]
["2024-08-30","2024-09-02","SW",1,"130A","A+B","CHARLEROI-SUD","ERQUELINNES-FRONTIERE","Weekend","Continuous","23:00","04:10","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+132 Finitions\r\n+ Renouvellement des as Y La Sambre \r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","CTL L130A + L132\r\nART de stabilisation Y La Sambre: 0,82min du 18/08/2024 au 15/09/2024","HKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",48241]
["2024-08-30","2024-09-03","SE",1,"166","B","GENDRON-CELLES","HOUYET","AllWeek","Continuous","05:00","05:00","Massification travaux\r\nRenouvellement tablier métallique PI 13.808\r\nMise au gabarit pistes PI + sécurisation parois rocheuses + stabilisation talus\r\nMassification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse","SAVU","Minor_AdHoc","ART de protection : BK 13.700 à 13.900 en voie B (longueur : 200 mètres). \r\nVitesse à 60 km/h. \r\nPerte de temps HKV : 2 minutes / HKM : 2 minutes\r\n\r\nART de stabilisation id 50024"," ",47501]
["2024-08-31","2024-08-31","SE",3,"130","A/B","FLAWINNE","MOUSTIER","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49175]
["2024-08-31","2024-08-31","SE",3,"139","A/B","WAVRE","OTTIGNIES","Weekend","Day","08:00","16:00","Visites des postes+ maintenances infrastructure et contrôles","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48872]
["2024-08-31","2024-09-01","NE",3,"27M/2","*","ANTWERPEN-NOORD-BUNDEL B1","ANTWERPEN-NOORD-BUNDEL B2","Weekend","Continuous","13:30","22:00","massificatiewerken B1 + B2 (met Hugo Deckers tot zondag 22uur)","CTL","Medium","bundels B1-B2 ontoegankelijk\r\nwissels Hugo Deckers eveneens ontoegankelijk tot zondag 22uur","Info Racc",60839]
["2024-08-31","2024-09-01","SE",3,"161","A/B","NAMUR","RHISNES-SAS","Weekend","Day","08:00","16:00","Visite périodique + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","Savu alternatif VA/VB , de 8h à 16 h"," ",49211]
["2024-08-31","2024-09-01","SW",2,"118","A","OBOURG","MONS","Weekend","Continuous","07:00","18:00","Mise en sevice SIMIS-W entre Mons et Obourg (gare incluse).\r\nTravaux préparatoires","SAVU","Minor_AdHoc","Mise hors service entre signal DX-O.27 et signal D-K.27"," ",57004]
["2024-08-31","2024-09-02","CE",1,"26B","A+B","Y.PONT-DE-LA-SENNE","SCHAERBEEK","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58627 on line 27D tracks(s) A+B from BRUXELLES-NORD-GRIL F to SCHAERBEEK-QUAI A.T./D.-NOS: Vernieuwing spoorgedeelte L27D in rooster H te FSR","CTL","Medium"," "," ",58627]
["2024-08-31","2024-09-02","CE",1,"27D","A+B","BRUXELLES-NORD-GRIL F","SCHAERBEEK-QUAI A.T./D.-NOS","Weekend","Continuous","00:20","04:00","Vernieuwing spoorgedeelte L27D in rooster H te FSR","CTL","Medium","TLO L27D, TLO L26B\r\nTunnel T afgesloten, Doorsteken P en T afgesloten in FSR\r\nDOES L36N"," ",58627]
["2024-08-31","2024-09-02","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58031]
["2024-08-31","2024-09-02","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Weekend","Continuous","00:00","04:00","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Medium"," "," ",58296]
["2024-08-31","2024-09-02","NW",2,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58786 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",58786]
["2024-08-31","2024-09-02","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)","CTL","Medium"," "," ",58786]
["2024-08-31","2024-09-02","NW",2,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58786 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",58786]
["2024-08-31","2024-09-02","NW",2,"66","A+B","LICHTERVELDE","ROESELARE","Weekend","Continuous","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\n\r\nRMS THV DR-O.7+DRX-O.7\r\ngevallen 29352+29347 niet mogelijk!","CTL","Medium",null,"Info Racc",57793]
["2024-08-31","2024-09-02","NW",2,"90","A+B","DENDERLEEUW","Y.NEDERBOELARE","Weekend","Continuous","06:00","04:20","Onderhoud","CTL","Medium",null,"Info Racc",60173]
["2024-08-31","2024-09-02","SE",1,"166","A+B","ANSEREMME","HOUYET","Weekend","Continuous","06:00","04:30","Massification travaux OA tronçons Anseremme - Gendron et Gendron - Houyet (entretien tunnels, parois,...)\r\nMassification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse","CTL","Medium",null," ",47506]
["2024-09-01","2024-09-01","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59998]
["2024-09-01","2024-09-01","SE",3,"130","A/B","MOUSTIER","AUVELAIS","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49184]
["2024-09-01","2024-09-01","SE",3,"139","A/B","SINT-JORIS-WEERT","WAVRE","Weekend","Day","08:00","16:00","Visites des postes - maintenances diverses et révisions","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48881]
["2024-09-02","2024-09-06","CE",2,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","Week","Night","23:45","04:50","Onderhoudszone FBMZ_19, FBKI_03 en FH_06 Area CE volgens onderhoudskalender 2024\r\n\r\nSporen A en B 124 buiten dienst, inclusief L28/3","CTL","Minor_AdHoc",null," ",59511]
["2024-09-02","2024-09-06","NE",2,"19","A+B","MOL","HAMONT","Week","Night","22:00","05:00","vernieuwing OW'en + onderhoud\r\n\r\nmeewerken met werken aanleg 2de spoor mogelijk (geen mogelijkheid tot werken tussen kp10 en kp 16)\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (colt 59879)","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59931]
["2024-09-02","2024-09-06","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:30","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Minor_AdHoc"," "," ",58297]
["2024-09-02","2024-09-06","NE",3,"139","A+B","LEUVEN","SINT-JORIS-WEERT","Week","Night","23:00","05:00","Onderhoud","CTL","Minor_AdHoc","alternatief E5722"," ",60242]
["2024-09-02","2024-09-06","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59879]
["2024-09-02","2024-09-06","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Day","09:30","15:30","Travaux SNCF CHA24_0027238 \r\nLille Bif Wasquehal Tourcoing : REGE - Réfection et création de regard","CTL","Minor_AdHoc",null," ",57904]
["2024-09-02","2024-09-06","SW",1,"94","A+B","LEUZE","TOURNAI","Week","Night","23:20","04:40","Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH\r\nTravaux de préparation","CTL","Minor_AdHoc","L94 CTL + L78 SAVU [04H/05BH - 05AH/06BH]\r\n--> 1semaine CTL de nuit prépa\r\n--> 1semaine CTL de nuit finition","Info Racc : désertes Havinnes impossible",48772]
["2024-09-02","2024-09-13","SE",1,"166","A+B","BEAURAING","BERTRIX","AllWeek","Continuous","04:30","23:00","Renouvellement traverses (P93)\r\nART 3min","ART","Minor_AdHoc","ART stabilisation v=60km/h\r\n3 minutes"," ",54865]
["2024-09-02","2024-09-28","SW",1,"130","B","CHATELET-GRIL EST","CHATELET","Week","Night","23:00","05:00","Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.a\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc","Mise hors service Zone 17 :\r\nSAVU L130 FCL/Le Campinaire\r\n+ Faisceaux A et B en CDS côté Namur\r\n+Faisceaux K et D inaccessibles"," ",49110]
["2024-09-02","2024-09-28","SW",1,"130","B","CHATELET-GRIL EST","CHATELET-GRIL EST","Week","Night","23:00","05:00","Linked to coupure nr 49110 on line 130 tracks(s) B from CHATELET-GRIL EST to CHATELET: Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.a\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 ","SAVU","Minor_AdHoc"," "," ",49110]
["2024-09-02","2024-11-18","NE",1,"27A","A+B","Y.ANTWERPEN-OOST","Y.HOLLAND","AllWeek","Continuous","00:05","04:00","vernieuwing bundel Q\r\ncontinue TLO bundel Q +BD+BS L27A nodig\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","CTL","Major","continue TLO bundel Q +BD+BS L27A nodig\r\n\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk"," ",58245]
["2024-09-03","2024-09-06","NE",2,"25","A+B","Y.ABEELSTRAAT","MECHELEN","Week","Night","00:00","04:00","Vierendeelbrug over de Vaart \r\nPERRONS mechelen INCLUSIEF \r\nL25N open","CTL","Minor_AdHoc","perrons mechelen inbegrepen"," ",58170]
["2024-09-03","2024-09-06","NW",2,"204","A+B","GENT-RODENHUIZE","GENT-NOORD","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 05 Schuitstraat; ovonde boven het spoor\r\n\r\n* R5/R6 in weekend TLO","CTL","Medium",null,"Info Racc.",58503]
["2024-09-03","2024-09-06","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst\r\n\r\n\r\n* R5/R6 in weekend TLO","CTL","Minor_AdHoc",null,null,58778]
["2024-09-03","2024-09-06","NW",3,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Week","Night","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Minor_AdHoc",null,"Info Racc",57800]
["2024-09-03","2024-09-08","SE",1,"166","B","GENDRON-CELLES","HOUYET","AllWeek","Continuous","05:00","05:00","Massification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse","ART","Minor_AdHoc","ART 1’ voie B du 3/09 au 07/09/24 BK10600 – 12300",null,60556]
["2024-09-06","2024-09-09","CE",1,"27E","*","Y.SCHAERBEEK-GROUPE G","SCHAERBEEK-CUL DE SAC 814","Weekend","Continuous","23:50","04:30","Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","Autre","Minor_AdHoc","Sporen 705 tem 712 bundel G onbeschikbaar.\r\nGoederenas door FSR afgesloten."," ",56220]
["2024-09-06","2024-09-09","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-SAS K/C","Weekend","Continuous","23:50","04:30","Linked to coupure nr 56220 on line 27E tracks(s) * from Y.SCHAERBEEK-GROUPE G to SCHAERBEEK-CUL DE SAC 814: Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","CTL","Medium"," "," ",56220]
["2024-09-06","2024-09-09","CE",2,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","Weekend","Continuous","23:45","04:50","Onderhoudszone FBMZ_19, FBKI_03 en FH_06 Area CE volgens onderhoudskalender 2024.\r\nSporen A en B 124 buiten dienst, inclusief L28/3\r\n\r\nPerrons en bundel Charleroi moeten vrijblijven (PHE)!!","CTL","Medium",null," ",58596]
["2024-09-06","2024-09-09","CE",2,"28/3","S","Y.FOREST-EST","Y.CUREGHEM","Weekend","Continuous","23:45","04:50","Linked to coupure nr 58596 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: Onderhoudszone FBMZ_19, FBKI_03 en FH_06 Area CE volgens onderhoudskalender 2024.\r\nSporen A en B 124 buiten dienst, inclusief L28/3\r\n\r\nPerrons en bundel Charler","CTL","Medium"," "," ",58596]
["2024-09-06","2024-09-09","NE",1,"12","A+B","Y.LUCHTBAL","ESSEN","Weekend","Night","23:30","04:00","overwegen +onderhoud","CTL","Minor_AdHoc","geen verkeer L12"," ",58791]
["2024-09-06","2024-09-09","NE",1,"27B","A+B","Y.PRINSENHOEK","Y.MUIZEN","Weekend","Continuous","23:50","04:00","vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58357]
["2024-09-06","2024-09-09","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:50","04:00","Linked to coupure nr 58338 on line 53 tracks(s) A+B from MECHELEN to HAACHT: vernieuwen Muizen rooster T \r\n(samen met L27B)","CTL","Medium"," "," ",58338]
["2024-09-06","2024-09-09","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:50","04:00","vernieuwen Muizen rooster T \r\n(samen met L27B)","CTL","Medium"," "," ",58338]
["2024-09-06","2024-09-09","NE",1,"53","A+B","Y.HEVER","MUIZEN","Weekend","Continuous","23:50","04:00","Linked to coupure nr 58357 on line 27B tracks(s) A+B from Y.PRINSENHOEK to Y.MUIZEN: vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58357]
["2024-09-06","2024-09-09","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59916]
["2024-09-06","2024-09-09","SE",1,"161","A+B","OTTIGNIES","Y.LOUVAIN-LA-NEUVE","Weekend","Continuous","23:30","04:30","WE CTL RER Ottignies-Y.LLN","CTL","Medium","ART à définir, maximum 2'"," ",49259]
["2024-09-06","2024-09-09","SE",1,"166","A+B","BEAURAING","BERTRIX","Weekend","Continuous","23:00","04:30","Renouvellement traverses (P93)","CTL","Medium","P93 entre 63.396 - 65.800 + Bourrage de révision 60.996 - 63.396"," ",46811]
["2024-09-06","2024-09-09","SE",2,"161","A+B","OTTIGNIES","GEMBLOUX","Weekend","Continuous","23:00","05:00","Visite + Maintenance massifiée + entretien des PN+ travaux ES\r\n Rév et Géo 01AF/01BF/02AF/02BF/03AF/03BF/05F - 04AE/04BE","SAVU","Minor_AdHoc","SAVU VA du Ve 23H au Di 05H\r\nSAVU VB du Sa 23H au Lu 05H\r\nART protection et stabilisation:\r\nLongueur: 100 mètres \r\nVitesse réduite: 40 km/h\r\nDate de mise en vigueur: du 06/09 au 23/09 à minuit \r\nPerte de temps: \r\nHKV: 2'\r\nHKM: 1,9'"," ",50728]
["2024-09-06","2024-09-09","SE",3,"130","A","HAM-SUR-SAMBRE","AUVELAIS","Weekend","Continuous","23:00","05:00","électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu\r\nRq 333: déplacer - incompatible le WE 7-8/09","SAVU","Minor_AdHoc","une voie hors service en continu","HKM à adapter",47158]
["2024-09-06","2024-09-09","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 min","HKM à adapter",48633]
["2024-09-06","2024-09-09","SW",1,"130A","A+B","CHARLEROI-SUD","ERQUELINNES-FRONTIERE","Weekend","Continuous","23:00","04:10","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+132  Finitions\r\n+ Renouvellement des as Y La Sambre \r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","CTL L130A + L132\r\nART de stabilisation Y La Sambre: 0,82min du 18/08/2024 au 15/09/2024","HKM à adapter: via L75-59 + L96 + L96-117-124A-130-244/147-161-139\r\nAthus-Meuse + L94 fermées\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inaccessible",48242]
["2024-09-06","2024-09-09","SW",1,"78","B","TOURNAI","Y.MAUBRAY","Weekend","Continuous","23:20","04:40","Linked to coupure nr 48773 on line 94 tracks(s) A+B from LEUZE to TOURNAI: Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH","SAVU","Minor_AdHoc"," ","Info Racc : Havinnes inaccessible",48773]
["2024-09-06","2024-09-09","SW",1,"94","A+B","LEUZE","TOURNAI","Weekend","Continuous","23:20","04:40","Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH","CTL","Medium","L94 CTL + L78 SAVU [04H/05BH - 05AH/06BH]\r\nSeule la voie I est accessible pour le trafic de et vers Mons.","Info Racc : Havinnes inaccessible",48773]
["2024-09-06","2024-09-23","SE",2,"161","A+B","OTTIGNIES","GEMBLOUX","AllWeek","Continuous","23:00","05:00","ART 2 min\r\nMaintenance massifiée + entretien des PN+ travaux ES","ART","Minor_AdHoc","ART protection et stabilisation:\r\nLongueur: 100 mètres \r\nVitesse réduite: 40 km/h\r\nDate de mise en vigueur: du 06/09 au 23/09\r\nPerte de temps: \r\nHKV: 2'\r\nHKM: 1,9'"," ",59495]
["2024-09-07","2024-09-08","NE",3,"10L/1","*","ANTWERPEN-W.H.-B.ZUID","ANTWERPEN-W.H.-B.ZUID","Weekend","Continuous","12:00","22:00","massificatiewerken","CTL","Medium","bundel Zuid WLH ontoegankelijk"," ",60822]
["2024-09-07","2024-09-08","NW",2,"202B","S","Y.EIVOORDE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Night","23:15","07:00","Linked to coupure nr 60386 on line 202B/1 tracks(s) S from Y.PELIKAAN to ZEEBRUGGE-BUNDEL PELIKAAN: R-419041-01\r\n\r\nOnderhoud werkveld 3421-25\r\n\r\nBundel Pelikaan en Bundel Ramskapelle","CTL","Minor_AdHoc"," ","Info Racc.",60386]
["2024-09-07","2024-09-08","NW",2,"202B/1","S","Y.PELIKAAN","ZEEBRUGGE-BUNDEL PELIKAAN","Weekend","Night","23:15","07:00","R-419041-01\r\n\r\nOnderhoud werkveld 3421-25\r\n\r\nBundel Pelikaan en Bundel Ramskapelle","CTL","Minor_AdHoc"," ","Info Racc.",60386]
["2024-09-07","2024-09-08","NW",2,"202B/2","S","ZEEBRUGGE-BUNDEL PELIKAAN","ZEEBRUGGE-BUNDEL PELIKAAN","Weekend","Night","23:15","07:00","Linked to coupure nr 60386 on line 202B/1 tracks(s) S from Y.PELIKAAN to ZEEBRUGGE-BUNDEL PELIKAAN: R-419041-01\r\n\r\nOnderhoud werkveld 3421-25\r\n\r\nBundel Pelikaan en Bundel Ramskapelle","CTL","Minor_AdHoc"," ","Info Racc.",60386]
["2024-09-07","2024-09-08","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60425]
["2024-09-07","2024-09-08","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60425 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60425]
["2024-09-07","2024-09-08","NW",3,"51A","S","ZEEBRUGGE-VOORHAVEN-WEST","ZEEBRUGGE-BUNDEL DART-LINE","Weekend","Continuous","06:00","22:00","Sanering ballast AWT 897,AWT863B,AWT862 en AWT861 zone136","CTL","Medium"," ","Info Racc.",60587]
["2024-09-07","2024-09-08","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60425 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60425]
["2024-09-07","2024-09-08","NW",3,"75","B","WAREGEM","KORTRIJK","Weekend","Night","22:15","06:00","vervangen rijdraad SP B - JVO\r\nSP A bijkomend tijdens de nacht 00.20-05.15","SAVU_CTRL","Minor_AdHoc",null," ",58605]
["2024-09-07","2024-09-08","SW",2,"118","B","MONS","OBOURG","Weekend","Continuous","07:00","18:00","Mise en sevice SIMIS-W entre Mons et Obourg (gare incluse).\r\nTravaux préparatoires","SAVU","Minor_AdHoc","Mise hors entre signal K-O.27 et signal DX-K.27"," ",57005]
["2024-09-07","2024-09-08","SW",3,"130","B","CHATELET-GRIL EST","CHATELET-GRIL OUEST","Weekend","Continuous","22:30","22:00","Maintenance Z17. 51 \r\nFaisceau de Chatelet","SAVU","Minor_AdHoc","Mise hors service en une zone (= Zone 17), voici les détails:\r\n- L130 Voie B entre F4-I. 20 et DX-J. 20;\r\nM-I.20 + J-I.20 + PC-I. 20 (faisceau A); + voie 320\r\n- F6-L. 20 + FX5-I. 20 (L130C en gare de Châtelet);\r\n- GC353-J. 20 + GC354-J. 20 + GC355-J. 20","HKM à adapter",55056]
["2024-09-07","2024-09-09","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","06:00","04:00","Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nAfwerkingssweekend 1/4\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINAL","CTL","Medium"," "," ",53694]
["2024-09-07","2024-09-09","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58032]
["2024-09-07","2024-09-09","NE",2,"25","A+B","Y.ABEELSTRAAT","MECHELEN","Weekend","Continuous","00:00","04:00","Vierendeelbrug over de Vaart \r\nPERRONS mechelen INCLUSIEF \r\nL25N open","CTL","Medium","perrons mechelen inbegrepen"," ",58168]
["2024-09-07","2024-09-09","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Weekend","Continuous","00:00","04:00","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Medium","3weekends P op onze area (weekends liggen vast),dn verder naar NW\r\nNW vraagt ook dezelfde weekends op L54\r\n1weekend ook L53 thv Y Heike\r\nweekend TLO's zijn lange TLO's ,inclusief vrijdagnacht"," ",58298]
["2024-09-07","2024-09-09","NW",1,"50","A+B","Y.MELLE","AALST","Weekend","Continuous","00:40","04:00","Onderhoud Y Schellebelle + Wissels Rooster Schellebelle\r\n\r\nY Melle + Aalst NIET IN","CTL","Medium",null," ",52979]
["2024-09-07","2024-09-09","NW",1,"53","A+B","SCHELLEBELLE","DENDERMONDE","Weekend","Continuous","00:40","04:00","Linked to coupure nr 52979 on line 50 tracks(s) A+B from Y.MELLE to AALST: Onderhoud Y Schellebelle + Wissels Rooster Schellebelle\r\n\r\nY Melle + Aalst NIET IN","CTL","Medium"," "," ",52979]
["2024-09-07","2024-09-09","NW",2,"204","A+B","GENT-RODENHUIZE","GENT-NOORD","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 05 Schuitstraat; ovonde boven het spoor","CTL","Medium",null,"Info Racc.",58500]
["2024-09-07","2024-09-09","NW",2,"66","A+B","LICHTERVELDE","ROESELARE","Weekend","Continuous","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\n\r\n\r\nRMS THV DR-O.7+DRX-O.7\r\ngevallen 29352+29347 niet mogelijk!","CTL","Medium",null,"Info Racc",57792]
["2024-09-07","2024-09-09","SE",2,"24","*","MONTZEN-GRIL N","MONTZEN-EST","AllWeek","Continuous","06:00","16:00","Renouvellement des AS05N et 03N  WE n°1","Autre","Minor_AdHoc","Stand à gasoil inaccessible via les faisceaux, uniquement accessible via VP.\r\nPas d'impact direct en VP."," ",47022]
["2024-09-07","2024-09-09","SE",3,"154","A+B","JAMBES","Y.NEFFE","Weekend","Night","23:00","05:00","Travaux préparatoires pour passage futur en EBP-PLP : gare d'Yvoir + gare de Dinant + BA (Dinant-Anseremme) + Anseremme.","CTL","Minor_AdHoc",null," ",57898]
["2024-09-08","2024-09-13","SE",2,"166","B","GENDRON-CELLES","HOUYET","AllWeek","Continuous","05:00","06:00","Adaptation du tracé 10600 - 12300\r\nBourrage de révision, contraintes,...","SAVU","Minor_AdHoc","Voie B HS en continu"," ",60454]
["2024-09-09","2024-09-13","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:30","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Minor_AdHoc"," "," ",58300]
["2024-09-09","2024-09-13","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59880]
["2024-09-09","2024-09-13","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Week","Night","23:40","04:00","Linked to coupure nr 59937 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59937]
["2024-09-09","2024-09-13","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Week","Night","23:40","04:00","Onderhoud","CTL","Minor_AdHoc"," "," ",59937]
["2024-09-09","2024-09-13","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Week","Night","23:40","04:00","Linked to coupure nr 59937 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59937]
["2024-09-09","2024-09-13","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Day","09:30","15:30","Travaux SNCF CHA24_0027238 \r\nLille Bif Wasquehal Tourcoing : REGE - Réfection et création de regard","CTL","Minor_AdHoc",null," ",57905]
["2024-09-09","2024-09-13","SW",1,"90C","A","BRUGELETTE","BRUGELETTE","Week","Continuous","08:00","16:30","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette","SAVU","Minor_AdHoc","SAVU de jour en semaine sauf les mercredis"," ",56839]
["2024-09-09","2024-09-13","SW",1,"96","A+B","MONS","JURBISE","Week","Night","23:20","04:10","Réélectrification - Phase 3 - 2024\r\nDépose anciennes traverses\r\nRq 333 : 4 nuits conflit nuit ven/sam","CTL","Minor_AdHoc",null,null,61223]
["2024-09-09","2024-09-14","SW",1,"140","A/B","LA ROCHE(BRABANT)","TILLY","AllWeek","Continuous","06:00","06:00","Renouvellement des traverses P93","SAVU_CTRL","Minor_AdHoc","SAVU en continu + CTL de nuit (23:00-5:00)\r\n+ART de protection en voie B demandé 3 min àpd 12.09.2024"," ",61342]
["2024-09-09","2024-09-14","SW",1,"94","A+B","LEUZE","TOURNAI","Week","Night","23:20","04:40","Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH\r\nTravaux de finition","CTL","Minor_AdHoc","L94 CTL + L78 SAVU [04H/05BH - 05AH/06BH]\r\n--> 1semaine CTL de nuit prépa\r\n--> 1semaine CTL de nuit finition","Info Racc : désertes Havinnes impossible",49412]
["2024-09-09","2024-09-15","SW",1,"94","A+B","TOURNAI","TOURNAI","AllWeek","Continuous","04:40","23:30","Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH\r\nART","ART","Minor_AdHoc","ART stabilisation (40/60) : du 07/09 au 15/09/2024 (fin probable)\r\nHKV\t: 1.50/0.60 - HKM : 3.50/1.80",null,49541]
["2024-09-09","2024-09-23","SW",1,"90C","A+B","BRUGELETTE","BRUGELETTE","AllWeek","Continuous","22:10","05:10","ART 3min HKV / 5min HKM\r\nRenouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\nART de Stabilisation","ART","Minor_AdHoc","ART stabilisation (40/60)\r\nHKV\t: 3.04/1.52 - HKM : 5.32:3.00"," ",56842]
["2024-09-09","2024-09-27","SW",1,"90C","A+B","JURBISE","ATH","Week","Night","22:10","05:10","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\n+ Maintenance Z7.53 +  Z13.54 en P3","CTL","Minor_AdHoc",null," ",56844]
["2024-09-09","2024-09-30","NW",3,"59B","*","GENT-ZEEHAVEN","GENT-ZEEHAVEN","AllWeek","Continuous","05:00","05:00","Vernieuwen wissels Bundels Gent Zeehaven\r\nBundel E buiten dienst van SP 25 tot SP 32","Autre","Minor_AdHoc"," ","info rac",60485]
["2024-09-09","2024-12-13","SE",1,"162","B","CINEY","HAVERSIN","AllWeek","Continuous","05:00","22:50","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 13\r\nciney-haversin","SAVU_CTRL","High","CTL de Nuit : Lu^Ma à Je^Ve :00:10–04:50, Ve^Sa 00:10–06:30, Sa^Di 23:10–06:30, Di^Lu 23:10–04:50\r\nAS 34BK parcourable"," ",58234]
["2024-09-10","2024-09-13","NW",3,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Week","Night","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Minor_AdHoc",null,"Info Racc",57801]
["2024-09-10","2024-09-14","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst","CTL","Minor_AdHoc",null,null,58779]
["2024-09-12","2024-09-12","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60114]
["2024-09-12","2024-09-12","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55950]
["2024-09-13","2024-09-15","SW",2,"112","A/B","MARCHIENNE-AU-PONT","PIETON","Weekend","Continuous","23:30","16:00","Tir de fils de contacts avec autorail","SAVU","Minor_AdHoc"," "," ",53201]
["2024-09-13","2024-09-15","SW",2,"287","A","ATH","GHISLENGHIEN","Weekend","Continuous","13:00","23:00","Transfert des PNs - Renouvellement des CVs et PNs","CTL","Medium",null," ",50567]
["2024-09-13","2024-09-16","CE",1,"27E","*","Y.SCHAERBEEK-GROUPE G","SCHAERBEEK-CUL DE SAC 814","Weekend","Continuous","23:50","04:30","Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","Autre","Minor_AdHoc","Sporen 705 tem 712 bundel G onbeschikbaar.\r\nGoederenas door FSR afgesloten."," ",56221]
["2024-09-13","2024-09-16","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-SAS K/C","Weekend","Continuous","23:50","04:30","Linked to coupure nr 56221 on line 27E tracks(s) * from Y.SCHAERBEEK-GROUPE G to SCHAERBEEK-CUL DE SAC 814: Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","CTL","Medium"," "," ",56221]
["2024-09-13","2024-09-16","NE",1,"27B","A+B","Y.PRINSENHOEK","Y.MUIZEN","Weekend","Continuous","23:50","04:00","vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58358]
["2024-09-13","2024-09-16","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:40","04:00","vernieuwen Muizen rooster T \r\n(samen met L27B)","CTL","Medium"," "," ",58339]
["2024-09-13","2024-09-16","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:40","04:00","Linked to coupure nr 58339 on line 53 tracks(s) A+B from MECHELEN to HAACHT: vernieuwen Muizen rooster T \r\n(samen met L27B)","CTL","Medium"," "," ",58339]
["2024-09-13","2024-09-16","NE",1,"53","A+B","Y.HEVER","MUIZEN","Weekend","Continuous","23:50","04:00","Linked to coupure nr 58358 on line 27B tracks(s) A+B from Y.PRINSENHOEK to Y.MUIZEN: vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58358]
["2024-09-13","2024-09-16","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59917]
["2024-09-13","2024-09-16","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Weekend","Continuous","23:40","04:00","Linked to coupure nr 59938 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Medium"," "," ",59938]
["2024-09-13","2024-09-16","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Weekend","Continuous","23:40","04:00","Onderhoud","CTL","Medium"," "," ",59938]
["2024-09-13","2024-09-16","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Weekend","Continuous","23:40","04:00","Linked to coupure nr 59938 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Medium"," "," ",59938]
["2024-09-13","2024-09-16","NW",1,"75","A+B","KORTRIJK","MOUSCRON","Weekend","Continuous","23:10","04:00","TLO-weekend voor in dienst stellen ETCS\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk","CTL","Medium"," "," ",47303]
["2024-09-13","2024-09-16","NW",1,"75","A+B","Y.ZANDBERG","DEINZE","Weekend","Continuous","23:10","04:00","TLO-weekend voor in dienst stellen SIZ Deinze-Waregem","CTL","Medium"," "," ",62007]
["2024-09-13","2024-09-16","SE",1,"166","A+B","BEAURAING","BERTRIX","Weekend","Continuous","23:00","04:30","Renouvellement traverses(P93)\r\nBourrage de révision","CTL","Medium","Révisions entre 63.396 - 65.800"," ",47743]
["2024-09-13","2024-09-16","SE",2,"125","A+B","HUY","STATTE","Weekend","Continuous","23:30","05:30","Renouvellement voie 717 et 718 + Quais centraux 6/7 et 8/9","SAVU","Minor_AdHoc","ART de protection réduit à 40km/h sur les voies 716, 717, 718 \r\nperte de temps HKV= 3min\r\nperte de temps HKM= 3min\r\nART de stabilisation réduit à 40km/h sur les voies 716, 717, 718  du 13/09 au 19/10 en continu (date probable)\r\nperte de temps HKV= 3min\r"," ",47464]
["2024-09-13","2024-09-16","SE",3,"161","A+B","OTTIGNIES","BAKENBOS","Weekend","Continuous","23:00","05:00","Maintenance\r\nEntretien + Végétation","CTL","Medium","CTL en continu"," ",53058]
["2024-09-13","2024-09-16","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement des traverses P93\r\nPhase 1 WE 0/3","CTL","Medium",null," ",61290]
["2024-09-13","2024-09-16","SW",1,"90C","A+B","JURBISE","ATH","Weekend","Continuous","22:10","05:10","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette","CTL","Medium","Brugelette non accessible","HKM à adapter",48251]
["2024-09-14","2024-09-15","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61587]
["2024-09-14","2024-09-15","NW",3,"51A","S","ZEEBRUGGE-VOORHAVEN-WEST","ZEEBRUGGE-BUNDEL DART-LINE","Weekend","Continuous","06:00","22:00","Sanering ballast AWT 897,AWT863B,AWT862 en AWT861 zone136","CTL","Medium"," ","Info Racc.",60588]
["2024-09-14","2024-09-15","SE",2,"125","A+B","STATTE","NAMUR","Weekend","Continuous","00:10","18:00","Massification travaux OA \r\nrenouvellement quais - renouvellement passerelles - parois rocheuses","CTL","Medium"," "," ",47492]
["2024-09-14","2024-09-15","SE",3,"161","A/B","BAKENBOS","OTTIGNIES","Weekend","Day","08:00","16:00","Visite voies A/B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 08h00 et 16h00 le samedi et le dimanche,  avec adaptations trains"," ",48912]
["2024-09-14","2024-09-16","NE",1,"12","A+B","Y.LUCHTBAL","ESSEN","Weekend","Night","23:30","04:00","overwegen +onderhoud","CTL","Minor_AdHoc","geen verkeer L12"," ",58792]
["2024-09-14","2024-09-16","NE",1,"12","A+B","Y.SINT-MARIABURG","Y.LUCHTBAL","Weekend","Continuous","00:00","04:00","oude landen 301","CTL","Medium"," "," ",58052]
["2024-09-14","2024-09-16","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","06:00","04:00","Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nAfwerkingsweekend 2/4\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINAL","CTL","Medium"," "," ",53695]
["2024-09-14","2024-09-16","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58033]
["2024-09-14","2024-09-16","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Weekend","Continuous","00:00","04:00","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Medium"," "," ",58299]
["2024-09-14","2024-09-16","NE",3,"222","A+B","ANTWERPEN-D.S.-OORDEREN","ANTWERPEN-D.S.-OORDEREN","AllWeek","Continuous","06:00","18:00","massificatiewerken","CTL","Medium"," "," ",60816]
["2024-09-14","2024-09-16","NW",2,"90","A+B","DENDERLEEUW","Y.NEDERBOELARE","Weekend","Continuous","00:10","04:20","Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P038_01_L90_Geraardsbergen - Ninove_IL\r\nETCS L2-IL_NW_P038_02_L90_Ninove_IL\r\nETCS L2-IL_NW_P038_03_L90_Ninove - Denderleeuw_IL","CTL","Medium",null,"Info Racc.",57550]
["2024-09-14","2024-09-16","NW",3,"60","A+B","JETTE","DENDERMONDE","Weekend","Continuous","00:10","05:10","Onderhoud - EDW","CTL","Medium"," ",null,60174]
["2024-09-14","2024-09-16","SE",2,"24","*","MONTZEN-GRIL N","MONTZEN-EST","AllWeek","Continuous","06:00","16:00","Renouvellement des AS05N et 03N  WE n2","Autre","Minor_AdHoc","Stand à gasoil inaccessible via les faisceaux, uniquement accessible via VP.\r\nPas d'impact direct en VP."," ",47021]
["2024-09-14","2024-09-16","SW",1,"94","B","LEUZE","TOURNAI","Weekend","Continuous","05:00","05:00","Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH","SAVU_CTRL","Minor_AdHoc","[06AH/07BH - 07AH/08H]\r\n--> 1weekend L94 voie B + Voie IV, V, 311 à 318 en CDS"," ",48774]
["2024-09-14","2024-10-06","SW",1,"140","A/B","LA ROCHE(BRABANT)","TILLY","AllWeek","Continuous","06:00","16:00","Renouvellement des traverses P93","SAVU_CTRL","High","SAVU en continu + CTL de nuit (23:00-5:00)"," ",49375]
["2024-09-14","2024-09-15","SE",3,"154","A/B","DINANT","Y.NEFFE","Weekend","Day","07:00","16:00","Travaux caténaires\r\nDéroulage nouveaux câbles alimentations 3KV, interrupteurs T, retour courant de traction de sous-station de Neffe\r\nRemplacement des caniveaux","SAVU","Minor_AdHoc",null," ",61429]
["2024-09-15","2024-09-15","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61614]
["2024-09-15","2024-09-15","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",59999]
["2024-09-15","2024-09-15","NW",3,"202B","S","Y.EIVOORDE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Day","10:00","18:00","R-419006-01\r\n\r\nonderhoud werkveld 3421-36\r\n\r\nAW 72R-73R-74R-74XR-75R-80R-82R-83R\r\n\r\nBundel Ramskapelle niet bereikbaar","CTL","Minor_AdHoc"," ","Info Racc.",60370]
["2024-09-15","2024-10-21","SE",2,"125","A+B","STATTE","NAMUR","AllWeek","Continuous","18:00","05:00","ART 3min\r\nMassification travaux OA","ART","Minor_AdHoc"," "," ",59510]
["2024-09-16","2024-09-20","CE",2,"94","A+B","Y.NOORD HALLE","SAINTES","Week","Night","23:30","04:20","Massificatie:\r\n1) Onderhoudszone FH_10 Area CE volgens onderhoudskalender 2024\r\nOnderhoudswerken L94 tussen perrons Halle en Grens Vlaanderen-Wallonië.\r\n2) Voorbereidende werken afschaffen OW","CTL","Minor_AdHoc","TLO L94 samen met TLO L90C waardoor er geen mogelijkheid is om om te leiden via L96-96/2-90C. Busdienst te organiseren voor 3245."," ",59514]
["2024-09-16","2024-09-20","NE",2,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","Week","Night","23:40","04:45","onderhoud TRA+SIG+OW \r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst","CTL","Minor_AdHoc"," "," ",60050]
["2024-09-16","2024-09-20","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:30","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Minor_AdHoc"," "," ",58301]
["2024-09-16","2024-09-20","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59881]
["2024-09-16","2024-09-20","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Week","Night","23:40","04:00","Linked to coupure nr 59939 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59939]
["2024-09-16","2024-09-20","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Week","Night","23:40","04:00","Onderhoud","CTL","Minor_AdHoc"," "," ",59939]
["2024-09-16","2024-09-20","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Week","Night","23:40","04:00","Linked to coupure nr 59939 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59939]
["2024-09-16","2024-09-20","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Day","09:30","15:30","Travaux SNCF CHA24_0027238 \r\nLille Bif Wasquehal Tourcoing : REGE - Réfection et création de regard","CTL","Minor_AdHoc",null," ",57906]
["2024-09-16","2024-09-20","SW",1,"96","A+B","MONS","JURBISE","Week","Night","23:20","04:10","Réélectrification - Phase 3 - 2024\r\nDépose anciennes traverses\r\nRq 333 : 4 nuits conflit nuit ven/sam","CTL","Minor_AdHoc",null,null,47568]
["2024-09-17","2024-09-20","NE",2,"25","A+B","Y.ABEELSTRAAT","MECHELEN","Week","Night","00:00","04:00","Vierendeelbrug over de Vaart \r\nPERRONS mechelen INCLUSIEF \r\nL25N open","CTL","Minor_AdHoc","perrons mechelen inbegrepen"," ",58171]
["2024-09-17","2024-09-20","NW",3,"60","A+B","OPWIJK","DENDERMONDE","Week","Night","00:10","05:10","P143: afschaffen overwegen NW\r\nafschaffen overweg  29 L60 - Bolstraat, Opwijk\r\nfietstunnel\r\nBTS gedurende 1 week na inschuiven fietstunnel","CTL","Minor_AdHoc"," ",null,58683]
["2024-09-20","2024-09-23","CE",1,"27E","*","Y.SCHAERBEEK-GROUPE G","SCHAERBEEK-CUL DE SAC 814","Weekend","Continuous","23:50","04:30","Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","Autre","Minor_AdHoc","Sporen 705 tem 712 bundel G onbeschikbaar.\r\nGoederenas door FSR afgesloten."," ",56222]
["2024-09-20","2024-09-23","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-SAS K/C","Weekend","Continuous","23:50","04:30","Linked to coupure nr 56222 on line 27E tracks(s) * from Y.SCHAERBEEK-GROUPE G to SCHAERBEEK-CUL DE SAC 814: Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","CTL","Medium"," "," ",56222]
["2024-09-20","2024-09-23","CE",2,"94","A+B","Y.NOORD HALLE","SAINTES","Weekend","Continuous","23:30","04:20","Massificatie\r\n1) Onderhoudswerken zone FH_10 volgens onderhoudskalender(58598)\r\n2) Voorbereidende werken afschaffen OW (58601)","CTL","Medium","TLO L94 in continu\r\n2 Perronsporen in Halle continu.\r\nTLO L94 samen met TLO L90C waardoor er geen mogelijkheid is om om te leiden via L96-96/2-90C. Busdienst te organiseren voor IC06 (19xx) en S6 (155x)."," ",58598]
["2024-09-20","2024-09-23","NE",1,"27B","A+B","Y.PRINSENHOEK","Y.MUIZEN","Weekend","Continuous","23:50","04:00","vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58359]
["2024-09-20","2024-09-23","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:50","04:00","Linked to coupure nr 58340 on line 53 tracks(s) A+B from MECHELEN to HAACHT: vernieuwen Muizen rooster T \r\n(samen met L27B)","CTL","Medium"," "," ",58340]
["2024-09-20","2024-09-23","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:50","04:00","vernieuwen Muizen rooster T \r\n(samen met L27B)","CTL","Medium"," "," ",58340]
["2024-09-20","2024-09-23","NE",1,"53","A+B","Y.HEVER","MUIZEN","Weekend","Continuous","23:50","04:00","Linked to coupure nr 58359 on line 27B tracks(s) A+B from Y.PRINSENHOEK to Y.MUIZEN: vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58359]
["2024-09-20","2024-09-23","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59918]
["2024-09-20","2024-09-23","NE",3,"21","A+B","LANDEN","HASSELT","Weekend","Continuous","23:30","04:20","inschuiven tunnel Sint-Truiden km 10.550 OND","CTL","Medium"," "," ",59936]
["2024-09-20","2024-09-23","NW",2,"89","A+B","ZOTTEGEM","Y.ZANDBERG","Weekend","Continuous","23:40","04:50","Buitenwerken \r\nVernieuwen seininrichting Oudenaarde\r\nOudenaarde niet toegankelijk\r\n+\r\nRenovatie brug N60 door AWV thv L89 kp 38.377","CTL","Medium","Oudenaarde niet toegankelijk","Info Racc",57575]
["2024-09-20","2024-09-23","SE",2,"125","A+B","HUY","STATTE","Weekend","Continuous","23:30","05:30","Renouvellement voie 717 et 718 + Quais centraux 6/7 et 8/9","SAVU","Minor_AdHoc","ART de protection réduit à 40km/h sur les voies 716, 717, 718\r\nperte de temps HKV= 3min\r\nperte de temps HKM= 3min\r\n--> transformation CTL suite massification chantier Ch Javaux Andenne / Namur\r\n+ Mise HS de la voie 718 en continu du 16/09 au 18/10 pour "," ",47465]
["2024-09-20","2024-09-23","SE",2,"166","A/B","HOUYET","BEAURAING","Weekend","Continuous","23:00","05:00","Entretien AS , traitement zone boueuse","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 23/09 au 26/09 (fin probable)"," ",57699]
["2024-09-20","2024-09-23","SE",3,"130","B","HAM-SUR-SAMBRE","AUVELAIS","Weekend","Continuous","23:00","05:00","électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu","SAVU","Minor_AdHoc","une voie hors service en continu"," ",47161]
["2024-09-20","2024-09-23","SE",3,"161","A","GEMBLOUX","RHISNES","Weekend","Continuous","23:00","05:00","réélectrification","SAVU","Minor_AdHoc","une voie en continu"," ",52671]
["2024-09-20","2024-09-23","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement des traverses P93\r\nPhase 1 WE 1/3\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium",null," ",49545]
["2024-09-20","2024-09-23","SW",1,"90C","A+B","JURBISE","ATH","Weekend","Continuous","22:10","05:10","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\n+ Maintenance Z13.54 + Z7.53","CTL","Medium","Brugelette non accessible\r\nGare Jurbise (cf plan Z7.53)","HKM à adapter",48250]
["2024-09-20","2024-09-23","SW",2,"112","A+B","Y.SAINT-VAAST","LA LOUVIERE-CENTRE","Weekend","Continuous","23:30","05:15","Construction passerelle gare de LLV Centre. Pose passerelle","CTL","Medium","Gare La Louvière Centre inaccessible"," ",53896]
["2024-09-20","2024-09-23","SW",2,"116","A","LA LOUVIERE-GARE INDUSTRIELLE","Y.LA PAIX","Weekend","Continuous","23:30","05:15","Linked to coupure nr 53896 on line 112 tracks(s) A+B from Y.SAINT-VAAST to LA LOUVIERE-CENTRE: Construction passerelle gare de LLV Centre. Pose passerelle","CTL","Medium"," "," ",53896]
["2024-09-21","2024-09-22","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59425]
["2024-09-21","2024-09-22","NW",3,"51A","S","ZEEBRUGGE-VOORHAVEN-WEST","ZEEBRUGGE-BUNDEL DART-LINE","Weekend","Continuous","06:00","22:00","Sanering ballast AWT 897,AWT863B,AWT862 en AWT861 zone136","CTL","Medium"," ","Info Racc.",60589]
["2024-09-21","2024-09-22","SE",2,"125","A+B","STATTE","NAMUR","Weekend","Continuous","00:10","18:00","Massification travaux OA \r\nrenouvellement quais - renouvellement passerelles - parois rocheuses","CTL","Medium"," "," ",47493]
["2024-09-21","2024-09-22","SE",3,"161","A/B","GEMBLOUX","RHISNES","Weekend","Day","08:00","16:00","Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49199]
["2024-09-21","2024-09-22","SE",3,"165","A+B","VIRTON","AUBANGE","Weekend","Continuous","23:00","15:00","Maintenance\r\nInterventions Programmées","CTL","Medium",null," ",46688]
["2024-09-21","2024-09-22","SW",3,"130","A+B","CHARLEROI-SUD","COUILLET","Weekend","Continuous","06:00","17:00","Maintenance Z10. 51   P4+","CTL","Medium","Détails car sur plusieurs lignes:\r\nL130\tVoie B\tCharleroi-Sud\tChâtelet\tD08-G. 20   &\t FX3_I. 20\r\n\t        Voie A\t\t\t                        D09-G. 20    &  F4_I. 20\r\n\t\t\t\tE10_H. 20   &\tF4_I. 20\r\n\t\t\t\tE11_H. 20   &\tF4_I. 20\r\n\t\t\t\tE12_H. 20   &\tF4_I. 20"," ",48837]
["2024-09-21","2024-09-23","CE",2,"26","A+B","SCHAERBEEK-FORMATION","Y.RUE DE BRUEL","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58592 on line 26B(1) tracks(s) A+B from Y.RUE DE BRUEL to Y.HAREN-NORD: Onderhoudszone FSR_11-FSR_12-MTB_08 volgens onderhoudskalender Area CE.\r\n\r\nAfsluiting L26B (Y Bruulstraat) en bundelkoppen bundel G en R te FSR","CTL","Medium"," "," ",58592]
["2024-09-21","2024-09-23","CE",2,"26","A+B","Y.ENTREE GROUPE R","Y.KEELBEEK","Weekend","Continuous","00:20","04:00","P085306 BVL L26 Y Bruul - Y Keelbeek (Ni)","CTL","Medium","TLO L26 tussen Y Inrit Gr. R en Y Keelbeek (NI). Y Bruulstraat is dicht.\r\nGeen verkeer mogelijk tussen L27 en Schaarbeek Vorming\r\nBundel R en ateliers NMBS enkel toegankelijk kant Schaarbeek Vorming","HKM om te leiden via 26-26/1",59651]
["2024-09-21","2024-09-23","CE",2,"26A","A+B","SCHAERBEEK-ACC.FORMATION-L26A","Y.HAREN-NORD","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58592 on line 26B(1) tracks(s) A+B from Y.RUE DE BRUEL to Y.HAREN-NORD: Onderhoudszone FSR_11-FSR_12-MTB_08 volgens onderhoudskalender Area CE.\r\n\r\nAfsluiting L26B (Y Bruulstraat) en bundelkoppen bundel G en R te FSR","CTL","Medium"," "," ",58592]
["2024-09-21","2024-09-23","CE",2,"26A","A+B","SCHAERBEEK-ACC.FORMATION-L26A","Y.HAREN-NORD","Weekend","Continuous","00:20","04:00","Linked to coupure nr 59651 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.KEELBEEK: P085306 BVL L26 Y Bruul - Y Keelbeek (Ni)","CTL","Medium"," ","HKM om te leiden via 26-26/1",59651]
["2024-09-21","2024-09-23","CE",2,"26B(1)","A+B","Y.RUE DE BRUEL","Y.HAREN-NORD","Weekend","Continuous","00:20","04:00","Onderhoudszone FSR_11-FSR_12-MTB_08 volgens onderhoudskalender Area CE.\r\n\r\nAfsluiting L26B (Y Bruulstraat) en bundelkoppen bundel G en R te FSR","CTL","Medium","Geen verkeer mogelijk tussen L27 en Schaarbeek Vorming\r\nBundel R en ateliers NMBS enkel toegankelijk kant Schaarbeek Vorming"," ",58592]
["2024-09-21","2024-09-23","NE",1,"12","A+B","KAPELLEN","Y.LUCHTBAL","Weekend","Continuous","00:00","04:00","oude landen 301","CTL","Medium"," "," ",58061]
["2024-09-21","2024-09-23","NE",1,"12","A+B","ESSEN-GRENS","Y.LUCHTBAL","Weekend","Continuous","01:00","04:30","OVERWEGVERNIEUWING","CTL","Medium"," "," ",47393]
["2024-09-21","2024-09-23","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","00:10","04:00","Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nAfwerkingsweekend 3/4\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINAL","CTL","Medium"," "," ",53696]
["2024-09-21","2024-09-23","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58034]
["2024-09-21","2024-09-23","NE",2,"25","A+B","Y.ABEELSTRAAT","MECHELEN","Weekend","Continuous","00:00","04:00","Vierendeelbrug over de Vaart \r\nPERRONS mechelen INCLUSIEF \r\nL25N open","CTL","Medium","perrons mechelen inbegrepen"," ",58169]
["2024-09-21","2024-09-23","NE",2,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","Weekend","Continuous","00:00","04:00","onderhoud TRA+SIG+OW \r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst","CTL","Medium"," "," ",60053]
["2024-09-21","2024-09-23","NE",3,"27M/4","*","ANTWERPEN-NOORD-BUNDEL C1","ANTWERPEN-NOORD-BUNDEL C3","AllWeek","Continuous","13:30","14:00","massificatiewerken C1/C2/C3","CTL","Medium","bundels C1-2-3 ontoegankelijk\r\n(bundel C1 reeds terug in dienst op maandag om 12u)\r\n(omloopspoor lijn 27A/3 reeds terug in dienst op maandag om 2u)","Info Racc",60841]
["2024-09-21","2024-09-23","NW",3,"60","A+B","OPWIJK","DENDERMONDE","Weekend","Continuous","00:10","05:10","P143: afschaffen overwegen NW\r\nafschaffen overweg  29 L60 - Bolstraat, Opwijk\r\nfietstunnel\r\nBTS gedurende 1 week na inschuiven fietstunnel","CTL","Medium"," ",null,58418]
["2024-09-21","2024-09-23","SE",3,"43","A+B","ANGLEUR","RIVAGE-MARCHANDISES","Weekend","Continuous","00:05","05:10","Entretien manuel et mécanisés des PN \r\nEntretien manuel et mécanisés des AW","CTL","Medium","Remise d'une voie en service le dimanche à 17h pour les trains étudiants\r\nCTL classique nuit dim/lun"," ",55087]
["2024-09-22","2024-09-22","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","06:00","17:40","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58665]
["2024-09-22","2024-09-22","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",60000]
["2024-09-23","2024-09-27","CE",1,"50","A+B","Y.BOCKSTAEL","TERNAT","Week","Night","23:55","05:20","Linked to coupure nr 50036 on line 60 tracks(s) A+B from JETTE to ASSE: Omvorming Y Jette Rooster S: voorbereidende nachten.","CTL","Minor_AdHoc"," "," ",50036]
["2024-09-23","2024-09-27","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Omvorming Y Jette Rooster S: voorbereidende nachten.","CTL","Minor_AdHoc","TLO L60 + L50."," ",50036]
["2024-09-23","2024-09-27","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:30","vernieuwen spoor L54,OW2 en AW01H\r\n \r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Minor_AdHoc"," "," ",58302]
["2024-09-23","2024-09-27","NW",3,"58","A+B","WONDELGEM","SLEIDINGE","Week","Night","23:00","04:20","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nophoging spoor, afbreken bestaande brug, bouw nieuwe brug \r\n\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc"," "," ",58512]
["2024-09-23","2024-09-27","SW",1,"90C","A","BRUGELETTE","BRUGELETTE","Week","Continuous","08:00","16:30","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette","SAVU","Minor_AdHoc","SAVU de jour en semaine sauf les mercredis"," ",56840]
["2024-09-23","2024-09-28","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59882]
["2024-09-23","2024-09-28","SW",1,"130A","A+B","CHARLEROI-SUD","ERQUELINNES-FRONTIERE","Week","Night","23:00","04:10","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nRenouvellement des AS de Y.La Sambre\r\nSem. nuits CTL L130A+132  Finitions\r\n+ Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux préparatoires caténaire (poteaux","CTL","Minor_AdHoc","CTL L130A + L132","HKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",61262]
["2024-09-23","2024-09-28","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Week","Night","22:00","04:45","Travaux SNCF\r\nGare de Jeumont fermée","CTL","Minor_AdHoc",null," ",57901]
["2024-09-23","2024-09-30","NW",3,"60","A+B","OPWIJK","DENDERMONDE","AllWeek","Continuous","05:10","05:10","BTS \r\nP143: afschaffen overwegen NW\r\nafschaffen overweg  29 L60 - Bolstraat, Opwijk\r\nfietstunnel","ART","Minor_AdHoc"," ",null,60942]
["2024-09-23","2024-11-15","SW",1,"94","*","TOURNAI","TOURNAI","AllWeek","Continuous","06:00","22:00","Tournai: Renouvellement voies 313-314\r\nRq 333 : bien toujours sous tension - Pas de MHT faisceau?","Autre","Minor_AdHoc","--> voies 313-314 HS en continu 8 semaines\r\n--> voies 312 et 315 hs de 07h à 17h"," ",48775]
["2024-09-24","2024-09-28","NW",3,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw \r\nAfwerking","CTL","Minor_AdHoc"," "," ",59043]
["2024-09-24","2024-09-28","NW",3,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 59043 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking","CTL","Minor_AdHoc"," "," ",59043]
["2024-09-24","2024-09-28","NW",3,"60","A+B","OPWIJK","DENDERMONDE","Week","Night","00:10","05:10","P143: afschaffen overwegen NW\r\nafschaffen overweg  29 L60 - Bolstraat, Opwijk\r\nfietstunnel\r\nBTS gedurende 1 week na inschuiven fietstunnel","CTL","Minor_AdHoc"," ",null,58689]
["2024-09-24","2024-09-28","NW",3,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 59043 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking","SAVU","Minor_AdHoc"," "," ",59043]
["2024-09-27","2024-09-30","CE",1,"27E","*","Y.SCHAERBEEK-GROUPE G","SCHAERBEEK-CUL DE SAC 814","Weekend","Continuous","23:50","04:30","Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","Autre","Minor_AdHoc","Sporen 705 tem 712 bundel G onbeschikbaar.\r\nGoederenas door FSR afgesloten."," ",56223]
["2024-09-27","2024-09-30","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-SAS K/C","Weekend","Continuous","23:50","04:30","Linked to coupure nr 56223 on line 27E tracks(s) * from Y.SCHAERBEEK-GROUPE G to SCHAERBEEK-CUL DE SAC 814: Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","CTL","Medium"," "," ",56223]
["2024-09-27","2024-09-30","CE",1,"50","B","TERNAT","Y.BOCKSTAEL","Weekend","Continuous","23:55","05:20","Linked to coupure nr 50034 on line 60 tracks(s) A+B from JETTE to ASSE: Omvorming Y Jette Rooster S","SAVU","Minor_AdHoc"," "," ",50034]
["2024-09-27","2024-09-30","CE",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:55","05:20","Omvorming Y Jette Rooster S","CTL","Medium","TLO L60 +  DOES L50"," ",50034]
["2024-09-27","2024-09-30","CE",2,"96","B","BRUXELLES-MIDI","FOREST-MIDI","Weekend","Continuous","23:00","05:00","Linked to coupure nr 58619 on line 96D tracks(s) S from BRUXELLES-MIDI to FOREST-FAISCEAU M: onderhoudswerken volgens onderhoudskalender area CE\r\nonderhoudszone FBMZ_15-FBKI_12, L96D + Vorst Bundel M","SAVU","Minor_AdHoc"," "," ",58619]
["2024-09-27","2024-09-30","CE",2,"96D","S","BRUXELLES-MIDI","FOREST-FAISCEAU M","Weekend","Continuous","23:00","05:00","onderhoudswerken volgens onderhoudskalender area CE\r\nonderhoudszone FBMZ_15-FBKI_12, L96D + Vorst Bundel M","CTL","Medium","Geen verkeer mogelijk L96D en bundel M te Vorst.\r\nSp B L96 enkel tijdens de nacht."," ",58619]
["2024-09-27","2024-09-30","NE",1,"27B","A+B","Y.PRINSENHOEK","Y.MUIZEN","Weekend","Continuous","23:50","04:00","vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58360]
["2024-09-27","2024-09-30","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:30","04:00","Linked to coupure nr 58341 on line 53 tracks(s) A+B from MECHELEN to HAACHT: vernieuwen Muizen rooster T \r\n(samen met L27B)","CTL","Medium"," "," ",58341]
["2024-09-27","2024-09-30","NE",1,"53","A+B","MECHELEN","HAACHT","Weekend","Continuous","23:30","04:00","vernieuwen Muizen rooster T \r\n(samen met L27B)","CTL","Medium"," "," ",58341]
["2024-09-27","2024-09-30","NE",1,"53","A+B","Y.HEVER","MUIZEN","Weekend","Continuous","23:50","04:00","Linked to coupure nr 58360 on line 27B tracks(s) A+B from Y.PRINSENHOEK to Y.MUIZEN: vernieuwing Muizen Rooster T\r\n1 op 1 vernieuwing\r\n(samen met L53)","CTL","Medium"," "," ",58360]
["2024-09-27","2024-09-30","NE",3,"21","A+B","LANDEN","HASSELT","Weekend","Continuous","23:30","04:20","inschuiven tunnel Sint-Truiden km 10.550 OND","CTL","Medium"," "," ",59935]
["2024-09-27","2024-09-30","NE",3,"29","A+B","Y.KRUISBERG","TURNHOUT","Weekend","Continuous","23:00","04:40","omvormen 50 HZ SK naar TFSK\r\naanpassen treindetectiesysteem (moet voor 2025)\r\nvernieuwing signalisatie overwegen\r\nomvorming moet gebeuren voor uitrol ETCS L29\r\n\r\nmeewerken NIET mogelijk","CTL","Medium","alternatief E3421"," ",60020]
["2024-09-27","2024-09-30","NW",2,"58","A+B","WONDELGEM","SLEIDINGE","Weekend","Continuous","23:00","05:00","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nophoging spoor, afbreken bestaande brug, bouw nieuwe brug","CTL","Medium",null," ",58507]
["2024-09-27","2024-09-30","NW",2,"89","A+B","OUDENAARDE","Y.ZANDBERG","Weekend","Continuous","23:40","04:20","Renovatie brug N60 door AWV thv L89 kp 38.377\r\n+\r\nonderhoud","CTL","Medium",null,"Info Racc.",59253]
["2024-09-27","2024-09-30","SE",1,"161","A+B","BRUXELLES-LUXEMBOURG","OTTIGNIES","Weekend","Continuous","23:30","04:50","WE CTL RER Watermael - Ottignies","CTL","Medium","ART à définir, maximum 2'"," ",49263]
["2024-09-27","2024-09-30","SE",2,"125","A+B","HUY","STATTE","Weekend","Continuous","23:30","05:30","Renouvellement voie 717 et 718 + Quais centraux 6/7 et 8/9","SAVU","Minor_AdHoc","ART de protection réduit à 40km/h sur les voies 716, 717, 718 \r\nperte de temps HKV= 3min\r\nperte de temps HKM= 3min\r\n+ Mise HS de la voie 718 en continu du 16/09 au 18/10 pour aménagement quai\r\n--> transformation CTL suite massification chantier Ch Javau"," ",47467]
["2024-09-27","2024-09-30","SE",3,"130","B","HAM-SUR-SAMBRE","AUVELAIS","Weekend","Continuous","23:00","05:00","électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu","SAVU","Minor_AdHoc","une voie hors service en continu"," ",47162]
["2024-09-27","2024-09-30","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement des traverses P93\r\nPhase 1 WE 2/3\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium",null," ",49546]
["2024-09-27","2024-09-30","SW",1,"90C","A+B","JURBISE","ATH","Weekend","Continuous","22:10","05:10","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette","CTL","Medium",null,"HKM à adapter",56843]
["2024-09-27","2024-10-13","NE",3,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","AllWeek","Continuous","23:40","04:45","BTS van 40km/h tussen Y.Antwerpen-Zuid en Puurs +2'\r\n\r\nwerken onderhoud","ART","Minor_AdHoc"," "," ",60490]
["2024-09-28","2024-09-29","SE",2,"125","A+B","STATTE","NAMUR","Weekend","Continuous","00:10","18:00","Massification travaux OA \r\nrenouvellement quais - renouvellement passerelles - parois rocheuses","CTL","Medium"," "," ",47491]
["2024-09-28","2024-09-29","SW",2,"130A","A","LA SAMBRE","ERQUELINNES-FRONTIERE","Weekend","Continuous","06:00","17:00","Transfert CV jade et mise en service PN","CTL","Medium",null,"HKM à adapter",57251]
["2024-09-28","2024-09-30","NE",1,"12","A+B","KAPELLEN","Y.LUCHTBAL","Weekend","Continuous","00:00","04:00","oude landen 301","CTL","Medium"," "," ",58062]
["2024-09-28","2024-09-30","NE",1,"12","A+B","ESSEN-GRENS","Y.LUCHTBAL","Weekend","Continuous","01:00","04:30","Vernieuwen van overwegen","CTL","Medium"," "," ",47394]
["2024-09-28","2024-09-30","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","00:10","04:00","Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nAfwerkingsweekend 4/4\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINAL","CTL","Medium"," "," ",53697]
["2024-09-28","2024-09-30","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58035]
["2024-09-28","2024-09-30","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Weekend","Continuous","00:00","04:00","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Medium"," "," ",58303]
["2024-09-28","2024-09-30","NE",3,"226","*","ANTWERPEN-D.S.-BERENDRECHT","ANTWERPEN-D.S.-BERENDRECHT","AllWeek","Continuous","06:00","18:00","massificatiewerken","CTL","Medium"," "," ",60820]
["2024-09-28","2024-09-30","NW",2,"66","A+B","ROESELARE","KORTRIJK","Weekend","Continuous","00:40","04:00","Linked to coupure nr 57520 on line 75 tracks(s) A+B from Y.ZANDBERG to MOUSCRON-FRONTIERE: ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanv","CTL","Medium"," ","Info Racc",57520]
["2024-09-28","2024-09-30","NW",2,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Weekend","Continuous","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Medium",null,"Info Racc",57790]
["2024-09-28","2024-09-30","NW",2,"66/1","A+B","Y.BETHUNE","Y.LEIEBRUG","Weekend","Continuous","00:40","04:00","Linked to coupure nr 57520 on line 75 tracks(s) A+B from Y.ZANDBERG to MOUSCRON-FRONTIERE: ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanv","CTL","Medium"," ","Info Racc",57520]
["2024-09-28","2024-09-30","NW",2,"75","A+B","WAREGEM","KORTRIJK","Weekend","Continuous","00:40","04:00","Linked to coupure nr 57520 on line 75 tracks(s) A+B from Y.ZANDBERG to MOUSCRON-FRONTIERE: ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanv","CTL","Medium"," ","Info Racc",57520]
["2024-09-28","2024-09-30","NW",2,"75","A+B","Y.ZANDBERG","MOUSCRON-FRONTIERE","Weekend","Continuous","00:40","04:00","ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanvakken L89 FND - Y Zandberg + L69 Y West Kortrijk - Menen + L75 Y Zandberg - FVG + L66 Y Kor","CTL","Medium"," ","Info Racc",57520]
["2024-09-28","2024-09-30","NW",2,"89","A+B","Y.ZANDBERG","OUDENAARDE","Weekend","Continuous","00:40","04:00","Linked to coupure nr 57520 on line 75 tracks(s) A+B from Y.ZANDBERG to MOUSCRON-FRONTIERE: ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanv","CTL","Medium"," ","Info Racc",57520]
["2024-09-28","2024-09-30","SE",3,"165","A+B","BERTRIX","FLORENVILLE","Weekend","Continuous","23:00","04:30","Linked to coupure nr 47206 on line 166 tracks(s) A+B from GEDINNE to BERTRIX: Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix","CTL","Medium"," "," ",47206]
["2024-09-28","2024-09-30","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix","CTL","Medium","CTL sa soir à di 15h + nuit de di/lu"," ",47206]
["2024-09-28","2024-09-30","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Weekend","Continuous","17:15","05:15","Travaux SNCF\r\nGare de Jeumont fermée","CTL","Medium",null," ",57902]
["2024-09-28","2024-10-20","SW",1,"130","B","CHATELET-GRIL EST","CHATELET-GRIL EST","AllWeek","Continuous","05:00","05:00","Linked to coupure nr 49111 on line 130 tracks(s) * from CHATELET-GRIL EST to CHATELET: Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.b\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 ","SAVU","High"," "," ",49111]
["2024-09-28","2024-10-20","SW",1,"130","*","CHATELET-GRIL EST","CHATELET","AllWeek","Continuous","05:00","05:00","Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.b\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 octobre 2021","SAVU","High","Mise hors service Zone 17 :\r\nSAVU L130 FCL/Le Campinaire\r\n+ Faisceaux A et B en CDS côté Namur\r\n+Faisceaux K et D inaccessibles"," ",49111]
["2024-09-28","2024-09-30","SE",3,"154","A/B","DINANT","Y.NEFFE","Weekend","Continuous","07:00","04:20","Travaux caténaires\r\nDéroulage nouveaux câbles alimentations 3KV, interrupteurs T, retour courant de traction de sous-station de Neffe\r\nRemplacement des caniveaux\r\n+ Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble","SAVU_CTRL","Minor_AdHoc","CTL nuits dans BT\r\nNuit sam/dim 23h40-5h20\r\nNuit dim/lun 00h20-4h20","HKM à adapter",61428]
["2024-09-29","2024-09-29","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","06:00","17:40","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58666]
["2024-09-29","2024-09-29","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",60001]
["2024-09-30","2024-09-30","SE",3,"130","A/B","NAMUR","FLAWINNE","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49065]
["2024-09-30","2024-10-04","CE",1,"50","A+B","Y.BOCKSTAEL","TERNAT","Week","Night","23:55","05:20","Linked to coupure nr 50037 on line 60 tracks(s) A+B from JETTE to ASSE: Omvorming Y Jette Rooster S: voorbereidende nachten.","CTL","Minor_AdHoc"," "," ",50037]
["2024-09-30","2024-10-04","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Omvorming Y Jette Rooster S: voorbereidende nachten.","CTL","Minor_AdHoc","TLO L60 + L50."," ",50037]
["2024-09-30","2024-10-04","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:30","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Minor_AdHoc"," "," ",58304]
["2024-09-30","2024-10-04","SE",2,"125A","A","SERAING","FLEMALLE-ANNEXE","Week","Continuous","06:00","22:00","renouvellement des appareils de voie 20C et 21BC","SAVU_CTRL","Minor_AdHoc","SAVU flémalle-Annexe - Seraing\r\nCTL de nuit souhaitée de minimum 6h (Nuit LU-MA à Je-VE)\r\nVoies à 50km/H --> pas d'ART\r\nL285 inaccessible"," ",57015]
["2024-09-30","2024-10-04","SW",2,"112","A+B","Y.SAINT-VAAST","LA LOUVIERE-CENTRE","Week","Night","23:30","05:15","Construction passerelle gare de LLV Centre. Finitions + pose charpente métallique","CTL","Minor_AdHoc","Gare de La Louvière Centre inaccessible"," ",53897]
["2024-09-30","2024-10-04","SW",2,"116","A","LA LOUVIERE-GARE INDUSTRIELLE","Y.LA PAIX","Week","Night","23:30","05:15","Linked to coupure nr 53897 on line 112 tracks(s) A+B from Y.SAINT-VAAST to LA LOUVIERE-CENTRE: Construction passerelle gare de LLV Centre. Finitions + pose charpente métallique","CTL","Minor_AdHoc"," "," ",53897]
["2024-09-30","2024-10-05","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59883]
["2024-09-30","2024-10-05","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Week","Night","22:00","04:45","Travaux SNCF\r\nGare de Jeumont fermée","CTL","Minor_AdHoc",null," ",59245]
["2024-09-30","2024-10-12","CE",1,"60","A+B","JETTE","ASSE","AllWeek","Continuous","05:20","05:20","Stabilisatie-BTS","ART","Minor_AdHoc","BTS 60 km/h: HKV=0,76' / HKM= 1,76'"," ",56101]
["2024-09-30","2024-10-21","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","AllWeek","Continuous","06:00","04:00","aanleg 2de spoor (7,5km)","CTL","High"," "," ",59681]
["2024-09-30","2024-10-25","NW",3,"50L/3","*","OOSTENDE-BUNDEL A","OOSTENDE-BUNDEL A","AllWeek","Continuous","08:00","16:00","Spoor 412+413 Ononderbroken buiten dienst tussen ma 30/09/2024 08u  tot vr 25/10/2024 16u.\r\n+ \r\ncolt 60514\r\nSpoor 411 Dagelijks N67 BD van ma 30/09/2024 om 08u00 tem vr 25/10/2024 om 16u00. \r\nSpoor 409 is enkel kant FR bereikbaar, via AW30H.\r\nSpoor 414 ","Autre","Minor_AdHoc"," "," ",60513]
["2024-09-30","2024-10-25","NW",3,"50L/3","*","OOSTENDE-BUNDEL A","OOSTENDE-BUNDEL A","Week","Day","08:00","16:00","colt \r\nSpoor 411 Dagelijks N67 BD van ma 30/09/2024 om 08u00 tem vr 25/10/2024 om 16u00. \r\nSpoor 409 is enkel kant FR bereikbaar, via AW30H.\r\nSpoor 414 Dagelijks N67 BD van 08u00 tot 12u00 en van 12u30 tot 16u00 van ma 30/09/2024 tem vr 25/10/2024. Bedi","Autre","Minor_AdHoc"," "," ",60514]
["2024-10-01","2024-10-05","NW",3,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw \r\nAfwerking","CTL","Minor_AdHoc"," "," ",59044]
["2024-10-01","2024-10-05","NW",3,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 59044 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking","CTL","Minor_AdHoc"," "," ",59044]
["2024-10-01","2024-10-05","NW",3,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 59044 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking","SAVU","Minor_AdHoc"," "," ",59044]
["2024-10-03","2024-10-03","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60115]
["2024-10-04","2024-10-06","SE",3,"43","A+B","RIVAGE","BOMAL","Weekend","Continuous","23:00","17:00","Maintenance\r\nRq 333 : demande replan EF's pour trajet Kinkempois - Jemelle\r\nconflit L125 et L43 pour DB \r\nPropositions de WE pour replan L43 à faire par I-CBE","CTL","Medium"," "," ",57732]
["2024-10-04","2024-10-06","SW",2,"287","A","ATH","GHISLENGHIEN","Weekend","Continuous","13:00","23:00","Transfert des PNs - Renouvellement des CVs et PNs","CTL","Medium",null," ",50566]
["2024-10-04","2024-10-07","CE",1,"26","A+B","Y.LINKEBEEK-HALLE","Y.NOORD HALLE","Weekend","Continuous","23:30","04:10","Ziftwerf C75 WE 1/3","CTL","Medium","TLO"," ",52687]
["2024-10-04","2024-10-07","CE",1,"27E","*","Y.SCHAERBEEK-GROUPE G","SCHAERBEEK-CUL DE SAC 814","Weekend","Continuous","23:50","04:30","Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","Autre","Minor_AdHoc","Sporen 705 tem 712 bundel G onbeschikbaar.\r\nGoederenas door FSR afgesloten."," ",56224]
["2024-10-04","2024-10-07","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-SAS K/C","Weekend","Continuous","23:50","04:30","Linked to coupure nr 56224 on line 27E tracks(s) * from Y.SCHAERBEEK-GROUPE G to SCHAERBEEK-CUL DE SAC 814: Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","CTL","Medium"," "," ",56224]
["2024-10-04","2024-10-07","CE",1,"50","B","TERNAT","Y.BOCKSTAEL","Weekend","Continuous","23:55","05:20","Linked to coupure nr 50035 on line 60 tracks(s) A+B from JETTE to ASSE: Omvorming Y Jette Rooster S","SAVU","Minor_AdHoc"," "," ",50035]
["2024-10-04","2024-10-07","CE",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:55","05:20","Omvorming Y Jette Rooster S","CTL","Medium","TLO L60 +  DOES L50"," ",50035]
["2024-10-04","2024-10-07","NW",2,"89","A+B","Y.ZANDBERG","OUDENAARDE","Weekend","Continuous","23:40","04:50","Buitenwerken Oudenaarde \r\nCoLT 57620 - buitendienststelling rooster Oudenaarde L86+89 kant Ronse/Kortrijk + sp I + sp 781\r\nCoLT 57621 - tijdens de nacht buiten dienst stelling rooster Oudenaarde L86+89 kant Gent/Zottegem","CTL","Medium",null,"Info Racc",57620]
["2024-10-04","2024-10-07","SE",2,"125","A+B","HUY","STATTE","Weekend","Continuous","23:30","05:30","Renouvellement voie 717 et 718 + Quais centraux 6/7 et 8/9","SAVU","Minor_AdHoc","ART de protection réduit à 40km/h sur les voies 716, 717, 718\r\nperte de temps HKV= 3min\r\nperte de temps HKM= 3min\r\n+ Mise HS de la voie 718 en continu du 16/09 au 18/10 pour aménagement quai\r\n--> transformation CTL suite massification chantier Ch Javaux"," ",47461]
["2024-10-04","2024-10-07","SE",2,"125A","A+B","SERAING","FLEMALLE-ANNEXE","Weekend","Continuous","23:00","05:00","Renouvellement de l'appareil de voie  21AC + liaison","CTL","Medium","CTL L125A\r\nVoies à 50km/H --> pas d'ART\r\nL285 inaccessible\r\nliaison électriquement accessible dès le lundi matin"," ",57016]
["2024-10-04","2024-10-07","SE",3,"130","B","HAM-SUR-SAMBRE","AUVELAIS","Weekend","Continuous","23:00","05:00","électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu","SAVU","Minor_AdHoc","une voie hors service en continu"," ",47163]
["2024-10-04","2024-10-07","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement des traverses P93\r\nPhase 1 WE 1/3\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium","ART de stabilisation à 80 km/h : 2,5 minutes"," ",49547]
["2024-10-04","2024-10-08","SE",2,"166","B","GENDRON-CELLES","HOUYET","Week","Continuous","05:00","05:00","Massification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse","SAVU","Minor_AdHoc","Voie B HS en continu\r\nART 60km/h 1’ du 8/10 au 19/10/24 BK12300 - 13300"," ",60455]
["2024-10-05","2024-10-06","NE",2,"52","A","PUURS","Y.ANTWERPEN-ZUID","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59100]
["2024-10-05","2024-10-06","NE",2,"59","A","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59099]
["2024-10-05","2024-10-06","NW",3,"204","*","GENT-RODENHUIZE","GENT-RODENHUIZEDOK","Weekend","Continuous","22:00","14:00","Reservatie onderhoud, enkel bundel Mercator buiten dienst","CTL","Medium",null,"Info Racc",60416]
["2024-10-05","2024-10-06","NW",3,"75","A","WAREGEM","KORTRIJK","Weekend","Night","22:15","06:00","vervangen rijdraad SP A - JVO\r\nSP B bijkomend tijdens de nacht 00.20-05.15","SAVU_CTRL","Minor_AdHoc",null," ",58606]
["2024-10-05","2024-10-06","SE",2,"125","A+B","STATTE","NAMUR","Weekend","Continuous","00:10","18:00","Massification travaux OA \r\nrenouvellement quais - renouvellement passerelles - parois rocheuses","CTL","Medium"," "," ",55608]
["2024-10-05","2024-10-06","SE",3,"161","A/B","OTTIGNIES","GEMBLOUX","Weekend","Day","08:00","16:00","Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles + 1/2h sas Rhisnes","SAVU","Minor_AdHoc","SAVU alternatif entre 08h00 et 16h00"," ",48954]
["2024-10-05","2024-10-06","SW",2,"96","A+B","Y.JURBISE","MONS","Weekend","Continuous","06:00","17:00","Maintenance Z.5.53\r\nMise HS en P4","CTL","Medium"," ","HKM à adapter",48661]
["2024-10-05","2024-10-07","NE",1,"12","A+B","ESSEN","Y.LUCHTBAL","Weekend","Night","23:30","04:00","overwegen+onderhoud","CTL","Minor_AdHoc","geen verkeer"," ",58793]
["2024-10-05","2024-10-07","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58036]
["2024-10-05","2024-10-07","NE",2,"53","A+B","MECHELEN","LONDERZEEL","Weekend","Continuous","00:00","04:00","vernieuwen spoor L54,OW2 en AW10H\r\n\r\nBTS, beperkte hinder door BTS op L54","CTL","Medium"," "," ",58314]
["2024-10-05","2024-10-07","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Weekend","Continuous","00:00","04:00","vernieuwen spoor L54,OW2 en AW01H\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Medium"," "," ",58305]
["2024-10-05","2024-10-07","NW",2,"66","A+B","KORTRIJK","ROESELARE","Weekend","Continuous","00:40","04:00","Linked to coupure nr 57521 on line 75 tracks(s) A+B from Y.ZANDBERG to MOUSCRON-FRONTIERE: ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanv","CTL","Medium"," ","Info Racc",57521]
["2024-10-05","2024-10-07","NW",2,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Weekend","Continuous","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Medium",null,"Info Racc",57791]
["2024-10-05","2024-10-07","NW",2,"66/1","A+B","Y.BETHUNE","Y.LEIEBRUG","Weekend","Continuous","00:40","04:00","Linked to coupure nr 57521 on line 75 tracks(s) A+B from Y.ZANDBERG to MOUSCRON-FRONTIERE: ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanv","CTL","Medium"," ","Info Racc",57521]
["2024-10-05","2024-10-07","NW",2,"75","A+B","WAREGEM","KORTRIJK","Weekend","Continuous","00:40","04:00","Linked to coupure nr 57521 on line 75 tracks(s) A+B from Y.ZANDBERG to MOUSCRON-FRONTIERE: ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanv","CTL","Medium"," ","Info Racc",57521]
["2024-10-05","2024-10-07","NW",2,"75","A+B","Y.ZANDBERG","MOUSCRON-FRONTIERE","Weekend","Continuous","00:40","04:00","ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanvakken L89 FND - Y Zandberg + L69 Y West Kortrijk - Menen + L75 Y Zandberg - FVG + L66 Y Kor","CTL","Medium"," ","Info Racc",57521]
["2024-10-05","2024-10-07","NW",2,"89","A+B","OUDENAARDE","Y.ZANDBERG","Weekend","Continuous","00:40","04:00","Linked to coupure nr 57521 on line 75 tracks(s) A+B from Y.ZANDBERG to MOUSCRON-FRONTIERE: ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanv","CTL","Medium"," ","Info Racc",57521]
["2024-10-05","2024-10-07","NW",2,"89","A+B","OUDENAARDE","ZOTTEGEM","Weekend","Night","00:05","04:40","Buitenwerken Oudenaarde \r\nCoLT 57620 - buitendienststelling rooster Oudenaarde L86+89 kant Ronse/Kortrijk + sp I + sp 781\r\nCoLT 57621 - tijdens de nacht buiten dienst stelling rooster Oudenaarde L86+89 kant Gent/Zottegem","CTL","Minor_AdHoc",null," ",57621]
["2024-10-05","2024-10-07","SE",1,"166","A+B","ANSEREMME","HOUYET","Weekend","Continuous","06:00","04:30","Massification travaux OA tronçons Anseremme - Gendron et Gendron - Houyet (entretien tunnels, parois,...)\r\n+ Massification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse","CTL","Medium","ART 3min"," ",47507]
["2024-10-05","2024-10-07","SE",1,"24","A+B","MONTZEN-GRIL M","MONTZEN-FRONTIERE","Weekend","Continuous","00:40","04:00","Entretien manuel et mécanisés des AW de Montzen grills N et Q, Botzelaer\r\nEntretien manuel et mécanisés de la voie courante","CTL","Medium","Pas de circulation possible entre Montzen et DB\r\nVoie de passage Montzen doit rester dispo pour détournement depuis L37 - laisser un accès"," ",55121]
["2024-10-05","2024-10-07","SE",3,"165","A+B","BERTRIX","FLORENVILLE","Weekend","Continuous","23:00","04:30","Linked to coupure nr 47207 on line 166 tracks(s) A+B from GEDINNE to BERTRIX: Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix\r\nRq 333 : demande EF's suite semestrielle : Pas L166 en combin","CTL","Medium"," "," ",47207]
["2024-10-05","2024-10-07","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix\r\nRq 333 : demande EF's suite semestrielle : Pas L166 en combinaison avec les CTL Bertrix - Gedinne et Bertrix - Florenville\r\nReplan id 47207","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu"," ",47207]
["2024-10-06","2024-10-06","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",60002]
["2024-10-06","2024-10-06","NW",3,"202B","S","ZEEBRUGGE-BUNDEL RAMSKAPELLE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Day","08:00","16:00","R-419020-01\r\n\r\nOnderhoud werkveld 3421-46\r\n\r\nAW 21AR-22R-23R-24R-25R-26R-27R-28R-83R-84R-85R-86R-87R-88R-89R-90R-91BR-92R buiten dienst\r\nbundelsporen 16-15-14-13-12-11-10-9 buiten dienst \r\n\r\nAanduiding Y.Pelikaan-Zeebrugge bundel Pelikaan","Autre","Minor_AdHoc"," ","Info Racc.",60375]
["2024-10-06","2024-10-06","NW",3,"51A","*","ZEEBRUGGE-ROOSTER F","ZEEBRUGGE-ROOSTER G","Weekend","Day","14:00","22:00","Reservering Onderhoud bundel Zwankendamme zone 108\r\n\r\nEnkel bundel Zwankendamme niet bereikbaar.\r\n\r\nAanduiding L51A enkel voor de visualisatie in Colt.geen beperkingen op L51A\r\n\r\nR-419358-01","Autre","Minor_AdHoc","bundel Zwakendamme niet bereikbaar","Info Racc.",60458]
["2024-10-06","2024-10-20","CE",1,"26","A+B","Y.NOORD HALLE","Y.LINKEBEEK-HALLE","AllWeek","Continuous","22:00","23:00","StabilisatieBTS na ziftwerf\r\nBTS 60 km/u tussen 22.850 en 24.650","ART","Minor_AdHoc","BTS"," ",61208]
["2024-10-06","2024-10-20","SW",1,"140","A","LA ROCHE(BRABANT)","TILLY","AllWeek","Continuous","16:00","16:00","Renouvellement des traverses P93\r\nPhase 2 - ART de stabilisation","ART","Minor_AdHoc","ART de stabilisation à 60Km/h : 2,9 min HKV, 4 min HKM"," ",49549]
["2024-10-07","2024-10-11","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:30","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Minor_AdHoc"," "," ",58306]
["2024-10-07","2024-10-11","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59884]
["2024-10-07","2024-10-11","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:10","04:00","weeknachten als fase 3 in map 3","CTL","Minor_AdHoc"," "," ",60202]
["2024-10-07","2024-10-11","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:50","04:30","Onderhoud","CTL","Minor_AdHoc","te bepalen"," ",59738]
["2024-10-07","2024-10-11","NE",3,"35","A+B","HASSELT","Y.HOLSBEEK","Week","Night","23:55","04:00","weeknachten als fase 3","CTL","Minor_AdHoc"," "," ",60207]
["2024-10-07","2024-10-11","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58484]
["2024-10-07","2024-10-11","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58484 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58484]
["2024-10-07","2024-10-11","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58484 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58484]
["2024-10-07","2024-10-11","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58484 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58484]
["2024-10-07","2024-10-12","CE",1,"50","A+B","Y.BOCKSTAEL","TERNAT","Week","Night","23:55","05:20","Linked to coupure nr 50038 on line 60 tracks(s) A+B from JETTE to ASSE: Omvorming Y Jette Rooster S: voorbereidende nachten.","CTL","Minor_AdHoc"," "," ",50038]
["2024-10-07","2024-10-12","CE",1,"60","A+B","JETTE","ASSE","Week","Night","23:55","05:20","Omvorming Y Jette Rooster S: voorbereidende nachten.","CTL","Minor_AdHoc","TLO L60 + L50."," ",50038]
["2024-10-07","2024-10-12","NE",3,"35","A+B","DIEST","AARSCHOT","Week","Night","23:40","04:40","onderhoudswerken A24","CTL","Minor_AdHoc","alternatief E2622-E2743-E2872"," ",59973]
["2024-10-07","2024-10-12","NW",3,"58","A+B","WONDELGEM","SLEIDINGE","Week","Night","23:00","04:20","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nophoging spoor, afbreken bestaande brug, bouw nieuwe brug","CTL","Minor_AdHoc"," "," ",58513]
["2024-10-07","2024-10-12","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Week","Night","22:00","04:45","R-405368\r\n\r\nTravaux SNCF\r\nGare de Jeumont fermée","CTL","Minor_AdHoc",null," ",59246]
["2024-10-07","2024-10-28","SE",1,"165","B","Y.AUBANGE","HALANZY","AllWeek","Continuous","07:30","06:00","Renouvellement ballast par train C75 à Aix-sur-Cloie VB.\r\n+ ART 7' du 7/10 au 21/10/24","SAVU","High","Travail sans CTL (Athus-Meuse) --> ART de protection à 40 ; avec ART de stabilisation à 40 (deux semaines).\r\nDesserte raccordement Ecore d'Aix-sur-Cloie impossible.","restriction capacité importante -> Partie HKM dévies via ANE (impossible les nuits en sem 41)",47758]
["2024-10-07","2024-11-16","SW",1,"96","A","JURBISE","MONS","Week","Night","22:50","05:10","Réélectrification - Phase 4 - 2024\r\nDépose anciens poteaux","SAVU","Minor_AdHoc",null,"HKM à adapter",47569]
["2024-10-08","2024-10-12","NW",3,"50","A+B","DENDERLEEUW","AALST","Week","Night","00:05","04:40","Omvorming rooster Denderleeuw \r\nAfwerking","CTL","Minor_AdHoc"," "," ",59046]
["2024-10-08","2024-10-12","NW",3,"50A/3","A+B","DENDERLEEUW","Y.WELLE","Week","Night","00:05","04:40","Linked to coupure nr 59046 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking","CTL","Minor_AdHoc"," "," ",59046]
["2024-10-08","2024-10-12","NW",3,"89","B","DENDERLEEUW","BURST","Week","Night","00:05","04:40","Linked to coupure nr 59046 on line 50 tracks(s) A+B from DENDERLEEUW to AALST: Omvorming rooster Denderleeuw \r\nAfwerking","SAVU","Minor_AdHoc"," "," ",59046]
["2024-10-08","2024-10-14","SE",2,"166","B","GENDRON-CELLES","HOUYET","AllWeek","Continuous","05:00","05:00","Massification travaux pour adaptation du tracé pour augmenter la vitesse\r\nART 1min VB","ART","Minor_AdHoc","ART 60km/h 1’ BK12300 - 13300"," ",60558]
["2024-10-10","2024-10-10","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55951]
["2024-10-11","2024-10-13","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Weekend","Continuous","21:20","17:20","Travaux SNCF\r\nGare de Jeumont fermée","CTL","Medium",null," ",57903]
["2024-10-11","2024-10-14","CE",1,"26","A+B","Y.LINKEBEEK-HALLE","Y.NOORD HALLE","Weekend","Continuous","23:30","04:10","Ziftwerf C75 WE 2/3","CTL","Medium","TLO","Nuit 11^12/10 via Athus-Meuse-L130-144-161-139 + L96-90C-90 + L75 + L124-130-Athus-Meuse (L96 fermée)",52683]
["2024-10-11","2024-10-14","CE",1,"27E","*","Y.SCHAERBEEK-GROUPE G","SCHAERBEEK-CUL DE SAC 814","Weekend","Continuous","23:50","04:30","Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","Autre","Minor_AdHoc","Sporen 705 tem 712 bundel G onbeschikbaar.\r\nGoederenas door FSR afgesloten."," ",56225]
["2024-10-11","2024-10-14","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-SAS K/C","Weekend","Continuous","23:50","04:30","Linked to coupure nr 56225 on line 27E tracks(s) * from Y.SCHAERBEEK-GROUPE G to SCHAERBEEK-CUL DE SAC 814: Herinrichting FSR Bundel G Fase 4: sporen 705 tem 712\r\nUitbreidingen tijdens de nachten en weekends.","CTL","Medium"," "," ",56225]
["2024-10-11","2024-10-14","NE",1,"12","A+B","Y.SINT-MARIABURG","Y.LUCHTBAL","Weekend","Continuous","23:55","04:00","oude landen 301","CTL","Medium"," "," ",58053]
["2024-10-11","2024-10-14","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59919]
["2024-10-11","2024-10-14","NE",3,"21","A+B","LANDEN","HASSELT","Weekend","Continuous","23:30","04:20","inschuiven tunnel Sint-Truiden km 10.550 OND","CTL","Medium"," "," ",59934]
["2024-10-11","2024-10-14","NE",3,"230","A+B","Y.BOSDEL","ZUTENDAAL","Weekend","Continuous","23:00","05:00","Onderhoud","CTL","Medium"," "," ",59971]
["2024-10-11","2024-10-14","NW",2,"89","A+B","OUDENAARDE","ZOTTEGEM","Weekend","Continuous","23:40","04:50","Buitenwerken Oudenaarde \r\nCoLT 57617 - buiten dienst stelling rooster Oudenaarde L86+89 kant Gent/Zottegem + sp III + bundel\r\nCoLT 57619 - tijdens de nacht buiten dienst stelling rooster Oudenaarde L86+89 kant Ronse/Anzegem","CTL","Medium","Oudenaarde niet toegankelijk kant Gent of Zottegem"," ",57617]
["2024-10-11","2024-10-14","SE",1,"161","B","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:45","WE SAVU RER Bakenbos-Ottignies","SAVU_CTRL","Minor_AdHoc","ART à définir, maximum 2'"," ",49251]
["2024-10-11","2024-10-14","SE",2,"125","A","HUY","ANDENNE","Weekend","Continuous","23:30","05:30","Renouvellement voie 717 et 718 + Quais centraux 6/7 et 8/9\r\nRq 333 : question SNCB : Est-il possible de diminuer l'ART?\r\nSi 3 min nécessaires, planning visites et autres SAVU à décaler par rapport ART\r\nrép 12/10 : 3Min nécessaires - visites phase 4 sero","SAVU","Minor_AdHoc","ART de protection réduit à 40km/h sur les voies 716, 717, 718\r\nperte de temps HKV= 3min\r\nperte de temps HKM= 3min\r\n+ Mise HS de la voie 718 en continu du 16/09 au 18/10 pour aménagement quai\r\nART de stabilisation réduit à 40km/h sur les voies 716, 717, "," ",47462]
["2024-10-11","2024-10-14","SE",2,"42","A+B","TROIS-PONTS","GOUVY","Weekend","Continuous","23:40","05:00","MIse en service nouvelle technologie PN11","CTL","Medium","Mise hors service de la zone entre NV, OV et OXV45 BK 66153 (entrée Vielsalm côté Trois-Ponts, PN 11)"," ",49517]
["2024-10-11","2024-10-14","SE",3,"130","B","HAM-SUR-SAMBRE","AUVELAIS","Weekend","Continuous","23:00","05:00","électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu\r\nRq 333 : Incompatible L125 suite semestrielle - à replanifier ou contraintes L125 à diminuer (ART 3min + SAVU)\r\n-> Propositions SAVU WE L130 étalables début 2025 - premier semestre ma","SAVU","Minor_AdHoc","une voie hors service en continu"," ",47164]
["2024-10-11","2024-10-14","SE",3,"34","A+B","LIERS","Y.GLONS","Weekend","Continuous","23:00","05:00","Suppression PN19A","CTL","Medium","ART stab 2 min 10 jours"," ",47308]
["2024-10-11","2024-10-14","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement des traverses P93\r\nPhase 2 - WE 1/2\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium",null,"Nuit 11^12/10 via Athus-Meuse-L130-144-161-139 + L96-90C-90 + L75 + L124-130-Athus-Meuse (L96 fermée)",49544]
["2024-10-11","2024-10-14","SW",3,"78","A+B","BLATON","TOURNAI","Weekend","Continuous","23:30","05:00","Raccordement Holcim : MES signalisation","CTL","Medium","MHS entre Signaux Q et QX-J.27 de Maubray et Q-QX-H.37 de Tournai"," ",59190]
["2024-10-12","2024-10-12","SE",3,"139","A/B","WAVRE","OTTIGNIES","Weekend","Day","08:00","16:00","Visites des postes+ maintenances infrastructure et contrôles","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48873]
["2024-10-12","2024-10-13","NE",2,"35","A+B","DIEST","Y.OOST DRIEHOEK AARSCHOT","Weekend","Continuous","06:00","22:00","vernieuwen OW 94 strail  te Testelt","CTL","Medium"," "," ",60025]
["2024-10-12","2024-10-13","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61588]
["2024-10-12","2024-10-13","SE",3,"161","A/B","NAMUR","RHISNES-SAS","Weekend","Day","08:00","16:00","Visite périodique + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","Savu alternatif VA/VB , de 8h à 16 h"," ",49213]
["2024-10-12","2024-10-13","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Weekend","Continuous","07:00","17:00","Maintenance Z2. 51  P4+","CTL","Medium"," ","HKM à adapter",48249]
["2024-10-12","2024-10-13","SW",2,"118","A","BRACQUEGNIES","MONS","Weekend","Continuous","07:00","18:00","Mise en sevice SIMIS-W entre Mons et Obourg (gare incluse).\r\nTravaux préparatoires","SAVU","Minor_AdHoc","Mise hors service entre signal HX-E.11 et signal D-K.27"," ",57007]
["2024-10-12","2024-10-13","SW",3,"117","B","MANAGE","LUTTRE","Weekend","Continuous","06:00","17:00","Linked to coupure nr 60784 on line 124A tracks(s) B from LUTTRE to ROUX: Maintenance Z05.52","SAVU","Minor_AdHoc"," "," ",60784]
["2024-10-12","2024-10-13","SW",3,"124A","B","LUTTRE","ROUX","Weekend","Continuous","06:00","17:00","Maintenance Z05.52","SAVU","Minor_AdHoc"," "," ",60784]
["2024-10-12","2024-10-14","NE",1,"12","A+B","ESSEN","Y.LUCHTBAL","Weekend","Night","23:55","04:00","onderhoud enj overwegen","CTL","Minor_AdHoc",null," ",58794]
["2024-10-12","2024-10-14","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58037]
["2024-10-12","2024-10-14","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Weekend","Continuous","00:00","04:00","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Medium"," "," ",58307]
["2024-10-12","2024-10-14","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Weekend","Continuous","01:00","04:00","Aanleg 3de en 4de spoor L50D + massificatiewerken","CTL","Medium","TLO 50A+ 50A5+ 50A6 +50D",null,58485]
["2024-10-12","2024-10-14","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58485 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken","CTL","Medium"," ",null,58485]
["2024-10-12","2024-10-14","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58485 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken","CTL","Medium"," ",null,58485]
["2024-10-12","2024-10-14","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Weekend","Continuous","01:00","04:00","Linked to coupure nr 58485 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken","CTL","Medium"," ",null,58485]
["2024-10-12","2024-10-14","NW",2,"89","A+B","Y.ZANDBERG","OUDENAARDE","Weekend","Night","00:05","04:40","Buitenwerken Oudenaarde \r\nCoLT 57617 - buiten dienst stelling rooster Oudenaarde L86+89 kant Gent/Zottegem + sp III + bundel\r\nCoLT 57619 - tijdens de nacht buiten dienst stelling rooster Oudenaarde L86+89 kant Ronse/Anzegem","CTL","Minor_AdHoc",null,"Info Racc",57619]
["2024-10-12","2024-10-14","SE",3,"165","A+B","BERTRIX","FLORENVILLE","Weekend","Continuous","23:00","04:30","Linked to coupure nr 47210 on line 166 tracks(s) A+B from GEDINNE to BERTRIX: Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix","CTL","Medium"," "," ",47210]
["2024-10-12","2024-10-14","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu"," ",47210]
["2024-10-12","2024-10-13","SE",3,"154","A/B","DINANT","Y.NEFFE","Weekend","Day","07:00","16:00","Travaux caténaires\r\nDéroulage nouveaux câbles alimentations 3KV, interrupteurs T, retour courant de traction de sous-station de Neffe\r\nRemplacement des caniveaux","SAVU","Minor_AdHoc",null,"HKM à adapter",54832]
["2024-10-13","2024-10-13","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61615]
["2024-10-13","2024-10-13","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",60003]
["2024-10-13","2024-10-13","SE",3,"139","A/B","SINT-JORIS-WEERT","WAVRE","Weekend","Day","08:00","16:00","Visites des postes - maintenances diverses et révisions","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48882]
["2024-10-14","2024-10-18","CE",2,"26","A+B","Y.ENTREE GROUPE R","Y.NOORD HALLE","Week","Night","23:40","04:00","Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zijtakken: L26/5, L26/4, L26/3, L26/2, L26/1, L36/3, L36/1 en L36C/2","CTL","Minor_AdHoc","TLO L26","Info Racc",59508]
["2024-10-14","2024-10-18","CE",2,"26/1","A+B","Y.KEELBEEK","Y.MACHELEN","Week","Night","23:40","04:00","Linked to coupure nr 59508 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59508]
["2024-10-14","2024-10-18","CE",2,"26/2","A+B","ETTERBEEK","Y.ETTERBEEK","Week","Night","23:40","04:00","Linked to coupure nr 59508 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59508]
["2024-10-14","2024-10-18","CE",2,"26/3","A+B","Y.WATERMAEL","WATERMAEL","Week","Night","23:40","04:00","Linked to coupure nr 59508 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59508]
["2024-10-14","2024-10-18","CE",2,"26/4","A+B","ETTERBEEK","Y.BOONDAEL","Week","Night","23:40","04:00","Linked to coupure nr 59508 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59508]
["2024-10-14","2024-10-18","CE",2,"26/5","A+B","Y.LINKEBEEK-HALLE","Y.LINKEBEEK","Week","Night","23:40","04:00","Linked to coupure nr 59508 on line 26 tracks(s) A+B from Y.ENTREE GROUPE R to Y.NOORD HALLE: Massificatie: \r\n1) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2024. \r\nSporen A en B L26 buiten dienst, inclusief alle zij","CTL","Minor_AdHoc"," ","Info Racc",59508]
["2024-10-14","2024-10-18","NE",2,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","Week","Night","23:40","04:45","onderhoud TRA+SIG+OW \r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst","CTL","Minor_AdHoc"," "," ",60052]
["2024-10-14","2024-10-18","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:30","vernieuwen spoor L54,OW2 en AW01H","CTL","Minor_AdHoc"," "," ",58308]
["2024-10-14","2024-10-18","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59885]
["2024-10-14","2024-10-18","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:10","04:00","weeknachten als fase 3 in map 3","CTL","Minor_AdHoc"," "," ",60203]
["2024-10-14","2024-10-18","NE",3,"35","A+B","LEUVEN","DIEST","Week","Night","23:30","04:30","onderhoud\r\n+\r\nvernieuwen OW 94 strail  te Testelt (colt 60027)","CTL","Minor_AdHoc","alternatief E2622-E2743-E2221"," ",60032]
["2024-10-14","2024-10-18","SE",1,"42","A","RIVAGE","GOUVY","Week","Night","23:30","05:30","Criblage voie U \r\n+ Mise en service nouvelle technologie PN11\r\ntravaux préparatoires","CTL","Minor_AdHoc","Gare de Trois-Pont incluse"," ",47012]
["2024-10-14","2024-10-18","SE",2,"166","B","GENDRON-CELLES","HOUYET","AllWeek","Continuous","05:00","05:00","Massification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse\r\nBourrage de révision, contraintes,...","SAVU","Minor_AdHoc",null," ",60456]
["2024-10-14","2024-10-19","NE",3,"34","A+B","HASSELT","TONGEREN","Week","Night","23:30","04:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nnog te bespreken of werken kunnen doorgaan","CTL","Minor_AdHoc"," "," ",59831]
["2024-10-14","2024-10-19","NE",3,"59","A+B","ANTWERPEN-ZUID","Y.MELSELE","Week","Night","23:50","04:35","onderhoudsweek Kennedytunnel","CTL","Minor_AdHoc","alternatief E723-E744"," ",60210]
["2024-10-14","2024-10-19","NW",2,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:30","Linked to coupure nr 59243 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",59243]
["2024-10-14","2024-10-19","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58486]
["2024-10-14","2024-10-19","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58486 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58486]
["2024-10-14","2024-10-19","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58486 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58486]
["2024-10-14","2024-10-19","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58486 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58486]
["2024-10-14","2024-10-19","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Week","Night","23:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)","CTL","Minor_AdHoc"," "," ",59243]
["2024-10-14","2024-10-19","NW",2,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:30","Linked to coupure nr 59243 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",59243]
["2024-10-14","2024-10-19","SE",2,"125A","A+B","SERAING","FLEMALLE-ANNEXE","Week","Night","23:00","05:00","renouvellement des appareils de voie  21AC/21BC + 20C\r\nbourrage de révision\r\nréglage des contraintes\r\nfinitions","CTL","Minor_AdHoc","CTL L125A de minimum 6 heures\r\nVoies à 50km/H --> pas d'ART\r\nL285 inaccessible"," ",57017]
["2024-10-14","2024-10-19","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Week","Night","22:00","04:45","Travaux SNCF\r\nGare de Jeumont fermée","CTL","Minor_AdHoc",null," ",59247]
["2024-10-14","2024-10-19","SW",1,"94","A+B","Y.SILLY","ATH","Week","Night","23:30","05:00","Silly - Ath : Renouvellement de traverses\r\nTravaux de préparations","CTL","Minor_AdHoc","3 semaines CTL de nuit"," ",48768]
["2024-10-14","2024-10-25","SE",3,"34","A+B","LIERS","Y.GLONS","AllWeek","Continuous","23:00","22:00","ART 2min\r\nSuppression PN19A","ART","Minor_AdHoc",null," ",59515]
["2024-10-14","2025-05-12","CE",1,"26","A/B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","AllWeek","Continuous","04:00","04:00","Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 2\r\nAfwerking toegangstrappen, aanleg nieuwe perrons, toegangshellingen, RER Vélo.","SAVU","High","DOES tussen Trapezium Linkebeek en Y Watermaal, afwisselend spoor A of B naargelang evolutie van de Werf\r\nBIP op perrons St Job"," ",40264]
["2024-10-14","2025-05-12","CE",1,"26","A/B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","AllWeek","Continuous","04:00","04:00","Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 2\r\nAfwerking toegangstrappen, aanleg nieuwe perrons, toegangshellingen, RER Vélo.","SAVU","High","DOES tussen Trapezium Linkebeek en Y Watermaal, afwisselend spoor A of B naargelang evolutie van de Werf\r\nBIP op perrons St Job"," ",40264]
["2024-10-15","2024-10-18","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst\r\n\r\n\r\n* R5/R6 in weekend TLO","CTL","Minor_AdHoc",null,null,58578]
["2024-10-15","2024-10-18","NW",3,"51B","A","Y.PELIKAAN","KNOKKE","Week","Night","00:30","04:30","Fietstunnel sportcentra Heist KP 112.000-112.100\r\n\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc"," "," ",58549]
["2024-10-18","2024-10-21","CE",2,"96B","*","FOREST-VOITURES-QUAI SERVICE","FOREST-MIDI-VOIES 920/926","Weekend","Continuous","22:30","04:00","Onderhoudswerken volgens onderhoudskalender Area CE, zone FBKI_15, bundel A en B","Autre","Minor_AdHoc","Bundel A en B buiten dienst voor onderhoudswerken"," ",58635]
["2024-10-18","2024-10-21","NE",2,"35","A+B","HASSELT","Y.ZUID DRIEHOEK AARSCHOT","Weekend","Continuous","23:50","04:00","onderhoud \r\n\r\ndata kan nog wijzigen","CTL","Medium"," "," ",60179]
["2024-10-18","2024-10-21","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59920]
["2024-10-18","2024-10-21","NE",3,"35","A+B","LEUVEN","AARSCHOT","Weekend","Continuous","23:30","04:30","onderhoud\r\n+\r\nafschaffen OW 119 langestraat +verhogen perrons Wezemaal (colt 60034)","CTL","Medium","alternatief E2622-E2743-E2221"," ",60033]
["2024-10-18","2024-10-21","NW",2,"89","A+B","Y.ZANDBERG","ZOTTEGEM","Weekend","Continuous","23:40","04:50","Buitenwerken \r\nVernieuwen seininrichting Oudenaarde\r\nOudenaarde niet toegankelijk","CTL","Medium","Oudenaarde niet toegankelijk","Info Racc",57576]
["2024-10-18","2024-10-21","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 min","HKM à adapter",48634]
["2024-10-18","2024-10-21","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement des traverses P93\r\nPhase 2 - WE 2/2\r\nDossier de concertation validé le 28 octobre 2021","CTL","Medium",null," ",49548]
["2024-10-18","2024-10-28","SW",1,"140","A+B","OTTIGNIES","FLEURUS","AllWeek","Continuous","23:00","05:00","Renouvellement des Tabliers métalliques  + 5chapes \r\nTravaux RER Ottignies (CSV)\r\nCTL 9 jours continu","CTL","High",null,"HKM à adapter",56085]
["2024-10-18","2024-11-04","SE",1,"42","A+B","RIVAGE","GOUVY","AllWeek","Continuous","23:30","05:30","Criblage voie U \r\nRenouvellement RTB dans les voies A et B du tunnel de Trois-Ponts\r\n+ Préparation passage nouvelle technologie PNs 12, 18 et 19","CTL","High","Gare de Trois-Pont incluse\r\nCTL entre fin des quais de Trois-Ponts et Vielsalm\r\nART de stabilisation de bk 55223 à 55568 (350m) \r\nVitesse réduite à 60km/h \r\nperte de temps:\r\nHKV:1min\r\nHKM: 1min\r\nART de stabilisation du 4/11 au 15/11"," ",47014]
["2024-10-18","2024-10-21","SE",2,"154","A/B","NAMUR","LUSTIN","Weekend","Continuous","23:00","05:00","Entretien AS , traitement zone boueuse\r\nRq 333 : a déplacer","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 21/10 au 24/10 (fin probable)"," ",57689]
["2024-10-19","2024-10-19","SE",3,"130","A/B","FLAWINNE","MOUSTIER","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49176]
["2024-10-19","2024-10-20","NE",2,"35","A+B","DIEST","Y.OOST DRIEHOEK AARSCHOT","Weekend","Continuous","06:00","22:00","vernieuwen OW 94 strail  te Testelt","CTL","Medium"," "," ",60026]
["2024-10-19","2024-10-20","NE",2,"52","A","PUURS","Y.ANTWERPEN-ZUID","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59102]
["2024-10-19","2024-10-20","NE",2,"59","A","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59101]
["2024-10-19","2024-10-20","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59424]
["2024-10-19","2024-10-20","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60426]
["2024-10-19","2024-10-20","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60426 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60426]
["2024-10-19","2024-10-20","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60426 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60426]
["2024-10-19","2024-10-20","SE",2,"130","A+B","NAMUR","AUVELAIS","Weekend","Continuous","23:40","14:50","Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+ électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu VA + VB départ L144","CTL","Medium",null," ",50428]
["2024-10-19","2024-10-20","SE",2,"130/1","A","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Weekend","Continuous","23:40","14:50","Linked to coupure nr 50428 on line 130 tracks(s) A+B from NAMUR to AUVELAIS: Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+ électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu VA + VB départ L144","CTL","Medium"," "," ",50428]
["2024-10-19","2024-10-20","SE",2,"144","A","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Weekend","Continuous","23:40","14:50","Linked to coupure nr 50428 on line 130 tracks(s) A+B from NAMUR to AUVELAIS: Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+ électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu VA + VB départ L144","CTL","Medium"," "," ",50428]
["2024-10-19","2024-10-20","SW",2,"118","B","MONS","BRACQUEGNIES","Weekend","Continuous","07:00","18:00","Mise en sevice SIMIS-W entre Mons et Obourg (gare incluse).\r\nTravaux préparatoires","SAVU","Minor_AdHoc","Mise hors service entre signal DX-K.27 et signal H-E.11"," ",57006]
["2024-10-19","2024-10-20","SW",3,"130","A+B","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Weekend","Continuous","23:40","14:50","Maintenance Z19. 51\r\nMini CTL","CTL","Medium"," "," ",49167]
["2024-10-19","2024-10-21","CE",1,"26","A+B","Y.NOORD HALLE","Y.RUE DE BRUEL","Weekend","Continuous","00:30","03:15","Massificatie: Ziftwerf C75 - Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) TLO L26 voor C75 WE3/3 ( Colt 52684)\r\n2) Onderhoudszone MTB_04, MTB_06, MTB_07 en FH_01 Area CE volgens onderhoudskalender 2023. (Colt 58569)\r\nSporen A en","CTL","Medium","TLO L26","Info Racc",52684]
["2024-10-19","2024-10-21","CE",1,"26/1","A+B","Y.KEELBEEK","Y.MACHELEN","Weekend","Continuous","00:30","03:15","Linked to coupure nr 52684 on line 26 tracks(s) A+B from Y.NOORD HALLE to Y.RUE DE BRUEL: Massificatie: Ziftwerf C75 - Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) TLO L26 voor C75 WE3/3 ( Colt 52684)\r\n2) Onderhoudszone MTB_04, ","CTL","Medium"," ","Info Racc",52684]
["2024-10-19","2024-10-21","CE",1,"26/2","A+B","ETTERBEEK","Y.ETTERBEEK","Weekend","Continuous","00:30","03:15","Linked to coupure nr 52684 on line 26 tracks(s) A+B from Y.NOORD HALLE to Y.RUE DE BRUEL: Massificatie: Ziftwerf C75 - Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) TLO L26 voor C75 WE3/3 ( Colt 52684)\r\n2) Onderhoudszone MTB_04, ","CTL","Medium"," ","Info Racc",52684]
["2024-10-19","2024-10-21","CE",1,"26/3","A+B","Y.WATERMAEL","WATERMAEL","Weekend","Continuous","00:30","03:15","Linked to coupure nr 52684 on line 26 tracks(s) A+B from Y.NOORD HALLE to Y.RUE DE BRUEL: Massificatie: Ziftwerf C75 - Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) TLO L26 voor C75 WE3/3 ( Colt 52684)\r\n2) Onderhoudszone MTB_04, ","CTL","Medium"," ","Info Racc",52684]
["2024-10-19","2024-10-21","CE",1,"26/4","A+B","ETTERBEEK","Y.BOONDAEL","Weekend","Continuous","00:30","03:15","Linked to coupure nr 52684 on line 26 tracks(s) A+B from Y.NOORD HALLE to Y.RUE DE BRUEL: Massificatie: Ziftwerf C75 - Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) TLO L26 voor C75 WE3/3 ( Colt 52684)\r\n2) Onderhoudszone MTB_04, ","CTL","Medium"," ","Info Racc",52684]
["2024-10-19","2024-10-21","CE",1,"26/5","A+B","Y.LINKEBEEK-HALLE","Y.LINKEBEEK","Weekend","Continuous","00:30","03:15","Linked to coupure nr 52684 on line 26 tracks(s) A+B from Y.NOORD HALLE to Y.RUE DE BRUEL: Massificatie: Ziftwerf C75 - Onderhoud - Carsoul - BVL L26 P085306 - P103303 RER L26 Moensberg\r\n1) TLO L26 voor C75 WE3/3 ( Colt 52684)\r\n2) Onderhoudszone MTB_04, ","CTL","Medium"," ","Info Racc",52684]
["2024-10-19","2024-10-21","NE",1,"27A","A+B","LUCHTBAL-ROOSTER S","ANTWERPEN-NOORD-INRIT C1","Weekend","Continuous","00:00","04:00","304 statiestraat tussen Y laarsebeek en Y schijn","CTL","Medium"," "," ",58233]
["2024-10-19","2024-10-21","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58038]
["2024-10-19","2024-10-21","NE",2,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","Weekend","Continuous","00:00","04:00","onderhoud TRA+SIG+OW \r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst\r\n+\r\nOnderhoud NW Puurs - Y Sauvegarde","CTL","Medium"," "," ",60054]
["2024-10-19","2024-10-21","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Weekend","Continuous","00:00","04:00","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Medium"," "," ",58309]
["2024-10-19","2024-10-21","NW",2,"204","A+B","GENT-ZEEHAVEN-SIFFERDOK","GENT-RODENHUIZE","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 07bis Piratenstraat; brug intern havenverkeer en fietsbrug","CTL","Medium",null,"Info Racc.",58493]
["2024-10-19","2024-10-21","NW",2,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58787 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",58787]
["2024-10-19","2024-10-21","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)","CTL","Medium"," "," ",58787]
["2024-10-19","2024-10-21","NW",2,"51B","A","Y.PELIKAAN","KNOKKE","Weekend","Continuous","00:30","04:30","Fietstunnel sportcentra Heist KP 112.000-112.100","CTL","Medium"," "," ",58548]
["2024-10-19","2024-10-21","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Weekend","Continuous","00:10","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst","CTL","Medium",null,null,58572]
["2024-10-19","2024-10-21","NW",2,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58787 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",58787]
["2024-10-19","2024-10-21","NW",2,"90","A+B","DENDERLEEUW","Y.NEDERBOELARE","Weekend","Continuous","06:00","04:20","Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P038_01_L90_Geraardsbergen - Ninove_IL\r\nETCS L2-IL_NW_P038_02_L90_Ninove_IL\r\nETCS L2-IL_NW_P038_03_L90_Ninove - Denderleeuw_IL\r\n\r\n*R6 06.00u - L90 niet in CBP","CTL","Medium",null,"Info Racc.",57551]
["2024-10-19","2024-10-21","SE",3,"165","A+B","BERTRIX","FLORENVILLE","Weekend","Continuous","23:00","04:30","Linked to coupure nr 47211 on line 166 tracks(s) A+B from GEDINNE to BERTRIX: Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix","CTL","Medium"," "," ",47211]
["2024-10-19","2024-10-21","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu\r\nBertrix accessible (mais uniquement venant de Libramont)"," ",47211]
["2024-10-19","2024-10-21","SW",2,"94","A+B","ATH","HAVINNES","Weekend","Continuous","00:40","04:40","Renforcement de 7 PI entre les km 54.992 et 63.375 sur la L94\r\nPhase 2.2 : PI 3+4+5\r\nConstruction d'un PI dans le cadre de la suppression du PN30\r\nPhase 2 : Ripage du pont\r\nTravaux d'entretien au droit du PS 67.955 (pont Festu - travaux SPW)","CTL","Medium","CTL de WE en continu\r\nCalcul ART pour PN30 : \r\n- HKV : 140km/h→40km/h ; 100m ; retard = 2'08\"\r\n- HKM : 120km/h→40km/h ; 100m ; retard = 5'37\""," ",57122]
["2024-10-19","2024-10-20","SE",3,"154","A/B","DINANT","Y.NEFFE","Weekend","Day","07:00","16:00","Travaux caténaires\r\nDéroulage nouveaux câbles alimentations 3KV, interrupteurs T, retour courant de traction de sous-station de Neffe\r\nRemplacement des caniveaux","SAVU","Minor_AdHoc",null,"HKM à adapter",61430]
["2024-10-20","2024-10-20","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",60004]
["2024-10-20","2024-10-20","NW",3,"202B","S","ZEEBRUGGE-BUNDEL RAMSKAPELLE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Day","08:00","16:00","R-419022-01\r\n\r\nOnderhoud 3421-56 \r\n\r\nAW 13R-14R-15R-16R-17R-18R-19R-21BR-75R-76R-77R-78R-79R-80R-81R-82R buiten dienst \r\nbundelsporen 1-2-3-4-5-6-7-8 buiten dienst","Autre","Minor_AdHoc"," ","Info Racc",60379]
["2024-10-20","2024-11-04","SE",2,"130","A+B","NAMUR","AUVELAIS","AllWeek","Continuous","14:50","05:00","ART 2min\r\nsuite maintenance globale  L130  + L130/1 + L144","ART","Minor_AdHoc","ART protection et stabilisation:\r\nDate de mise en vigueur: du 20/10 au 4/11\r\nPerte de temps: \r\nHKV: 2'\r\nHKM: 2'"," ",59332]
["2024-10-21","2024-10-25","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2+3"," ",58148]
["2024-10-21","2024-10-25","NE",2,"52","A+B","Y.ANTWERPEN-ZUID","PUURS","Week","Night","23:40","04:45","onderhoud TRA+SIG+OW \r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst","CTL","Minor_AdHoc"," "," ",60051]
["2024-10-21","2024-10-25","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:30","vernieuwen spoor L54,OW2 en AW01H\r\n \r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Minor_AdHoc"," "," ",58310]
["2024-10-21","2024-10-25","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59886]
["2024-10-21","2024-10-25","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Week","Night","23:40","04:00","Linked to coupure nr 59940 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59940]
["2024-10-21","2024-10-25","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Week","Night","23:40","04:00","Onderhoud","CTL","Minor_AdHoc"," "," ",59940]
["2024-10-21","2024-10-25","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Week","Night","23:40","04:00","Linked to coupure nr 59940 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59940]
["2024-10-21","2024-10-25","NE",3,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Week","Night","23:50","04:20","onderhoud NZ verbinding (Antwerpen Centraal)\r\n\r\nhangt vast aan 61148 (L27)","CTL","Minor_AdHoc","alternatief E2573-E2594-E2021"," ",59706]
["2024-10-21","2024-10-25","NE",3,"34","A+B","HASSELT","GLONS","Week","Night","23:10","04:00","weeknachten als fase 3 in map 3","CTL","Minor_AdHoc"," "," ",60204]
["2024-10-21","2024-10-25","NE",3,"34","A+B","HASSELT","TONGEREN","Week","Night","23:30","04:00","afschaffen 7 overwegen Bilzen\r\n+\r\nonderhoud (59739)","CTL","Minor_AdHoc"," "," ",59834]
["2024-10-21","2024-10-25","NW",1,"50A/5","A+B","BRUGGE-ROOSTER E","BRUGGE","Week","Night","23:50","05:00","Vernieuwing wissels Brugge\r\nSporen 4,5, 6 en 7 Brugge buiten dienst.\r\nSporen 1 en 2 enkel bereikbaar via bundels.\r\nSpoor 3 doodspoor enkel bereikbaar kant kust.","CTL","Minor_AdHoc"," "," ",47707]
["2024-10-21","2024-10-25","NW",1,"66","A","BRUGGE","ZEDELGEM-ROOSTER E/G","Week","Night","23:50","05:00","Linked to coupure nr 47707 on line 50A/5 tracks(s) A+B from BRUGGE-ROOSTER E to BRUGGE: Vernieuwing wissels Brugge\r\nSporen 4,5, 6 en 7 Brugge buiten dienst.\r\nSporen 1 en 2 enkel bereikbaar via bundels.\r\nSpoor 3 doodspoor enkel bereikbaar kant kust.","SAVU","Minor_AdHoc"," "," ",47707]
["2024-10-21","2024-10-25","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58487]
["2024-10-21","2024-10-25","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58487 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58487]
["2024-10-21","2024-10-25","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58487 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58487]
["2024-10-21","2024-10-25","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58487 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge\r\n\r\n\r\n*R5/R6 in Weekend TLO","CTL","Minor_AdHoc"," ",null,58487]
["2024-10-21","2024-10-26","NE",3,"35","A+B","HASSELT","LEUVEN","Week","Night","23:55","04:00","weeknachten als fase 3\r\n+\r\nafschaffen OW 119 langestraat + verhogen van perrons Wezemaal (60030)","CTL","Minor_AdHoc"," "," ",60209]
["2024-10-21","2024-10-26","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Week","Night","22:00","04:45","Travaux SNCF\r\nGare de Jeumont fermée","CTL","Minor_AdHoc",null," ",59248]
["2024-10-21","2024-10-26","SW",1,"94","A+B","Y.SILLY","ATH","Week","Night","23:30","05:00","Silly - Ath : Renouvellement de traverses\r\nTravaux de préparations","CTL","Minor_AdHoc","3 semaines CTL de nuit"," ",59345]
["2024-10-21","2024-10-26","SW",2,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Week","Night","23:00","04:10","Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux préparatoires caténaire (poteaux + traverses)","CTL","Minor_AdHoc",null," ",59297]
["2024-10-21","2024-10-28","NW",3,"51B","A","Y.PELIKAAN","KNOKKE","AllWeek","Continuous","04:30","04:30","BTS\r\nFietstunnel sportcentra Heist KP 112.000-112.100","ART","Minor_AdHoc"," "," ",60940]
["2024-10-22","2024-10-25","NE",3,"27","A+B","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL","Week","Night","00:40","04:20","onderhoud NZ verbinding (Antwerpen Centraal)\r\n\r\nhangt samen met Colt 59706","CTL","Minor_AdHoc","alternatief E1972"," ",61148]
["2024-10-22","2024-10-25","NW",3,"204","A+B","GENT-ZEEHAVEN-SIFFERDOK","GENT-RODENHUIZE","Week","Night","00:10","04:00","227331 R4WO knooppunt 07bis Piratenstraat; brug intern havenverkeer en fietsbrug\r\n\r\n* R5/R6 in weekend TLO","CTL","Minor_AdHoc",null,"Info Racc.",58498]
["2024-10-22","2024-10-26","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst","CTL","Minor_AdHoc",null,null,58579]
["2024-10-22","2024-10-26","NW",3,"51B","A","Y.PELIKAAN","KNOKKE","Week","Night","00:30","04:30","Fietstunnel sportcentra Heist KP 112.000-112.100","CTL","Minor_AdHoc"," "," ",58550]
["2024-10-24","2024-10-24","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60116]
["2024-10-25","2024-10-27","SW",2,"112","A/B","MARCHIENNE-AU-PONT","PIETON","Weekend","Continuous","23:30","16:00","Tir de fils de contacts avec autorail","SAVU","Minor_AdHoc"," "," ",53202]
["2024-10-25","2024-10-28","CE",2,"96B","*","FOREST-VOITURES-QUAI SERVICE","FOREST-MIDI-VOIES 920/926","Weekend","Continuous","22:30","04:00","Onderhoudswerken volgens onderhoudskalender Area CE, zone FBKI_14, bundel B en C","Autre","Minor_AdHoc","Bundel B en C buiten dienst voor onderhoudswerken"," ",58633]
["2024-10-25","2024-10-28","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59921]
["2024-10-25","2024-10-28","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Weekend","Continuous","23:40","04:00","Linked to coupure nr 59941 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Medium"," "," ",59941]
["2024-10-25","2024-10-28","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Weekend","Continuous","23:40","04:00","Onderhoud","CTL","Medium"," "," ",59941]
["2024-10-25","2024-10-28","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Weekend","Continuous","23:40","04:00","Linked to coupure nr 59941 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Medium"," "," ",59941]
["2024-10-25","2024-11-04","NW",1,"50A/5","A+B","BRUGGE-ROOSTER E","BRUGGE","AllWeek","Continuous","23:50","05:00","Vernieuwing wissels Brugge\r\nSporen 4,5 ,6 en 7 Brugge buiten dienst.\r\nSpoor 3 doodspoor bereikbaar kant kust.\r\nSporen 1 en 2 enkel bereikbaar via bundels.","CTL","High"," "," ",47679]
["2024-10-25","2024-11-04","NW",1,"66","B","BRUGGE","ZEDELGEM-ROOSTER E/G","AllWeek","Continuous","23:50","05:00","Linked to coupure nr 47679 on line 50A/5 tracks(s) A+B from BRUGGE-ROOSTER E to BRUGGE: Vernieuwing wissels Brugge\r\nSporen 4,5 ,6 en 7 Brugge buiten dienst.\r\nSpoor 3 doodspoor bereikbaar kant kust.\r\nSporen 1 en 2 enkel bereikbaar via bundels.","SAVU","High"," "," ",47679]
["2024-10-26","2024-10-27","SE",3,"161","A/B","BAKENBOS","OTTIGNIES","Weekend","Day","08:00","16:00","Visite voies A/B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 08h00 et 16h00 le samedi et le dimanche,  avec adaptations trains"," ",48913]
["2024-10-26","2024-10-27","SW",2,"96","A+B","LEMBEEK","BRAINE-LE-COMTE","Weekend","Continuous","06:00","16:00","Maintenance Z1.53 en P4","CTL","Medium",null,"HKM à adapter",49538]
["2024-10-26","2024-10-27","SW",2,"97","A+B","MONS","SAINT-GHISLAIN","Weekend","Continuous","06:00","16:00","Maintenance Z.12.53\r\nMise HS en P4","CTL","Medium"," "," ",48890]
["2024-10-26","2024-10-28","CE",2,"96","A+B","Y.NOORD HALLE","TUBIZE","Weekend","Continuous","00:45","04:30","Onderhoudszone FH_11 volgens onderhoudskalender Area CE\r\n\r\nTLO op L96","CTL","Medium","TLO in continu"," ",58391]
["2024-10-26","2024-10-28","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)\r\n\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","CTL","Medium"," "," ",58039]
["2024-10-26","2024-10-28","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Medium","geen verkeer sporen 1+2+3"," ",58145]
["2024-10-26","2024-10-28","NE",2,"27","A+B","Y.HAREN-NORD","VILVOORDE","Weekend","Continuous","00:00","04:00","Werken werkvennootschap voor de werken aan de ring van Brussel --> viaduct Vilvoorde\r\n- Periode 27/11/2024 – 07/01/2025: 1 weekend volledige onderbreking (L27 – montage moot 18) \r\n- Periode 05/05/2025 – 03/06/2025: 1 weekend volledige onderbreking (L27 ","CTL","Medium"," "," ",58777]
["2024-10-26","2024-10-28","NW",2,"204","A+B","GENT-ZEEHAVEN-SIFFERDOK","GENT-RODENHUIZE","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 07bis Piratenstraat; brug intern havenverkeer en fietsbrug","CTL","Medium",null,"Info Racc.",58494]
["2024-10-26","2024-10-28","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Weekend","Continuous","00:10","04:30","Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOpgelet; verkeer moet op de werf zijn en blijven tijdens de duur van BDS ROCS (EBP buiten dienst)","CTL","Medium","TLO 50A+ 50A5+ 50A6 +50D",null,58488]
["2024-10-26","2024-10-28","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Weekend","Continuous","00:10","04:30","Linked to coupure nr 58488 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOpgelet; verkeer moet op de werf zijn en blijven tijdens de duur van BDS ROCS (EBP buiten dienst)","CTL","Medium"," ",null,58488]
["2024-10-26","2024-10-28","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Weekend","Continuous","00:10","04:30","Linked to coupure nr 58488 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOpgelet; verkeer moet op de werf zijn en blijven tijdens de duur van BDS ROCS (EBP buiten dienst)","CTL","Medium"," ",null,58488]
["2024-10-26","2024-10-28","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Weekend","Continuous","00:10","04:30","Linked to coupure nr 58488 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken\r\n\r\nOpgelet; verkeer moet op de werf zijn en blijven tijdens de duur van BDS ROCS (EBP buiten dienst)","CTL","Medium"," ",null,58488]
["2024-10-26","2024-10-28","SE",3,"165","A+B","BERTRIX","FLORENVILLE","Weekend","Continuous","23:00","04:30","Linked to coupure nr 47214 on line 166 tracks(s) A+B from GEDINNE to BERTRIX: Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix","CTL","Medium"," "," ",47214]
["2024-10-26","2024-10-28","SE",3,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","23:00","04:30","Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix","CTL","Medium","coupure nuit de sa à di 15h + nuit de di/lu\r\nBertrix accessible (mais uniquement venant de Libramont)"," ",47214]
["2024-10-26","2024-11-04","NW",1,"53","A+B","LONDERZEEL","MECHELEN","AllWeek","Continuous","00:30","04:00","IDS ETCS - Mechelen-Londerzeel\r\n9 dagen TLO\r\n\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","CTL","High","herlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk"," ",53177]
["2024-10-26","2024-11-04","NW",1,"54","A+B","Y.HEIKE","WILLEBROEK","AllWeek","Continuous","00:30","04:00","Linked to coupure nr 53177 on line 53 tracks(s) A+B from LONDERZEEL to MECHELEN: IDS ETCS - Mechelen-Londerzeel\r\n9 dagen TLO\r\n\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk","CTL","High"," "," ",53177]
["2024-10-26","2024-11-04","NW",1,"90","A+B","DENDERLEEUW","GERAARDSBERGEN","AllWeek","Continuous","00:10","04:20","IDS SIW Denderleeuw – Ninove\r\nIDS SIW Ninove\r\nIDS SIW Ninove – Geraardsbergen","CTL","High",null," ",52453]
["2024-10-26","2026-12-31","NW",1,"50L/1","A+B","Y.OOST DRIEHOEK LEDEBERG","MERELBEKE-ROOSTER S","AllWeek","Continuous","00:05","23:55","Merelbeke Bundel Centraal buiten spanning\r\n\r\nGeen impact op de lijn 50E  (zo in colt geprogrammeerd voor de zichtbaarheid)","Autre","Minor_AdHoc"," "," ",59256]
["2024-10-26","2026-12-31","NW",1,"50L/1","A+B","Y.OOST DRIEHOEK LEDEBERG","MERELBEKE-ROOSTER S","AllWeek","Continuous","00:05","23:55","Merelbeke Bundel Centraal buiten spanning\r\n\r\nGeen impact op de lijn 50E  (zo in colt geprogrammeerd voor de zichtbaarheid)","Autre","Minor_AdHoc"," "," ",59256]
["2024-10-26","2024-10-28","SE",2,"154","A/B","JAMBES","YVOIR","Weekend","Continuous","06:00","06:00","Mise en service EBP-PLP : gare d'Yvoir\r\nPrévoir 4 semaines MIN d'intervalles avec la MES Dinant + BA + Anseremme (COLT 57896 + 57935).","SAVU_CTRL","Minor_AdHoc","SAVU par la voie B du Sa 26/10 à 06h00 au Di 27/10 à 07H00\r\nCTL du Sa 26/10 à 23H00 au Di 27/10 à 07H00.\r\nSAVU par la voie A du Di 27/10 à 07h00 au Lu 28/10 à 07h00"," ",57894]
["2024-10-28","2024-10-31","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement des Tabliers métalliques  + 5chapes \r\nTravaux RER Ottignies (CSV)\r\n+ Maintenance Z3. 51  P3  HKV","CTL","Minor_AdHoc",null,"HKM à adapter",56086]
["2024-10-28","2024-10-31","SW",1,"147","A+B","AUVELAIS","FLEURUS","Week","Night","23:00","05:00","Linked to coupure nr 56086 on line 140 tracks(s) A+B from OTTIGNIES to FLEURUS: Renouvellement des Tabliers métalliques  + 5chapes \r\nTravaux RER Ottignies (CSV)\r\n+ Maintenance Z3. 51  P3  HKV","CTL","Minor_AdHoc"," ","HKM à adapter",56086]
["2024-10-28","2024-11-01","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2+3"," ",58149]
["2024-10-28","2024-11-01","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Week","Night","23:00","05:30","herlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk\r\n\r\n\r\nvernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Minor_AdHoc","herlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk"," ",58311]
["2024-10-28","2024-11-01","NE",3,"21A/1","A+B","Y.BOKSBERGHEIDE","Y.NIEUWDAK","Week","Night","23:40","04:00","Linked to coupure nr 59942 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59942]
["2024-10-28","2024-11-01","NE",3,"21C","A+B","GENK-GOEDEREN","Y.ROOIERWEG","Week","Night","23:40","04:00","Onderhoud","CTL","Minor_AdHoc"," "," ",59942]
["2024-10-28","2024-11-01","NE",3,"21L/1","A+B","GENK-ZUID-LO-INRIT NOORD FORD","GENK-ZUID-LO-INRIT ZUID FORD","Week","Night","23:40","04:00","Linked to coupure nr 59942 on line 21C tracks(s) A+B from GENK-GOEDEREN to Y.ROOIERWEG: onderhoud","CTL","Minor_AdHoc"," "," ",59942]
["2024-10-28","2024-11-02","NE",2,"53","A+B","MECHELEN","MUIZEN","Week","Night","23:50","04:00","Brug Leuvensesteenweg, voorbereiding BVL\r\n(rooster N niet beschikbaar L27)\r\ndeels samen met L27,L53","CTL","Minor_AdHoc"," "," ",58330]
["2024-10-28","2024-11-02","NE",3,"19","A+B","BALEN-WERKPLAATSEN","HAMONT-GRENS","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt\r\n+\r\nvernieuwen bevestiging spoorstaven aan brug kanaal Beverlo-Balen","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59887]
["2024-10-28","2024-11-02","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Week","Night","23:10","04:10","L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc","TLO 50A+ 50A5+ 50A6 +50D",null,58489]
["2024-10-28","2024-11-02","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Week","Night","23:10","04:10","Linked to coupure nr 58489 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58489]
["2024-10-28","2024-11-02","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Week","Night","23:10","04:10","Linked to coupure nr 58489 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58489]
["2024-10-28","2024-11-02","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Week","Night","23:10","04:10","Linked to coupure nr 58489 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: L50A aanleg derde/vierde spoor Gent > Brugge","CTL","Minor_AdHoc"," ",null,58489]
["2024-10-28","2024-11-02","SE",2,"53A","A+B","MECHELEN","Y.MUIZEN","Week","Night","23:50","04:00","Brug Leuvensesteenweg, voorbereiding BVL\r\n(rooster N blijft vrij L27)\r\ndeels samen met L27,L53","CTL","Minor_AdHoc"," "," ",58290]
["2024-10-28","2024-11-02","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Week","Night","22:00","04:45","Travaux SNCF\r\nGare de Jeumont fermée","CTL","Minor_AdHoc",null," ",59249]
["2024-10-28","2024-11-02","SW",1,"94","A+B","Y.SILLY","ATH","Week","Night","23:30","05:00","Silly - Ath : Renouvellement de traverses\r\nTravaux de préparations","CTL","Minor_AdHoc","3 semaines CTL de nuit"," ",59346]
["2024-10-28","2024-11-11","SW",1,"140","A+B","OTTIGNIES","FLEURUS","AllWeek","Continuous","05:00","05:00","ART 4 min\r\nRenouvellement des Tabliers métalliques  + 5chapes \r\nTravaux RER Ottignies (CSV)","ART","Minor_AdHoc","4min"," ",56089]
["2024-10-28","2024-11-18","SE",1,"165","B","Y.AUBANGE","HALANZY","AllWeek","Continuous","07:30","06:00","Révision suite renouvellement ballast par train C75 à Aix-sur-Cloie VB.","SAVU","High","Travail sans CTL (Athus-Meuse) --> ART de protection à 40.\r\nDesserte raccordement Ecore d'Aix-sur-Cloie impossible.","restriction capacité importante -> Partie HKM dévies via ANE",47761]
["2024-10-28","2024-11-22","NW",3,"50L/3","*","OOSTENDE-BUNDEL A","OOSTENDE-BUNDEL A","AllWeek","Day","08:00","16:00","Sp 412-413 en 414 buiten dienst vanaf  Ma 25/11/2024  tot en met 20/12/2024\r\n\r\n+\r\n\r\nColt 60524\r\n\r\nSpoor 415 Dagelijks N67 BD van 08u00 tot 12u00 en van 12u30 tot 16u00 van ma 25/11/2024 tem vr 20/12/2024. Het spoor mag bezet zijn tijdens de buitendienst","Autre","Minor_AdHoc"," "," ",60523]
["2024-10-28","2024-11-22","NW",3,"50L/3","*","OOSTENDE-BUNDEL A","OOSTENDE-BUNDEL A","Week","Continuous","08:00","16:00","Spoor 414 Dagelijks N67 BD van 08u00 tot 12u00 en van 12u30 tot 16u00 van ma 28/10/2024 tem vr 22/11/2024. Bediening door NMBS mogelijk over de middag.\r\nHet spoor mag bezet zijn tijdens de buitendienststelling","Autre","Minor_AdHoc"," "," ",60522]
["2024-10-28","2024-11-22","NW",3,"50L/3","*","OOSTENDE-BUNDEL A","OOSTENDE-BUNDEL A","Week","Day","08:00","16:00","Spoor 411-412 en 413 buiten dienst van  Ma 28/10/2024 tot en met Vr 22/11/2024\r\n\r\n+\r\n\r\nColt  60522\r\n\r\nSpoor 414 Dagelijks N67 BD van 08u00 tot 12u00 en van 12u30 tot 16u00 van ma 28/10/2024 tem vr 22/11/2024. Bediening door NMBS mogelijk over de middag.","Autre","Minor_AdHoc"," "," ",60521]
["2024-10-28","2024-11-22","NW",3,"50L/3","*","OOSTENDE-BUNDEL A","OOSTENDE-BUNDEL A","Week","Day","08:00","16:00","Spoor 415 Dagelijks N67 BD van 08u00 tot 12u00 en van 12u30 tot 16u00 van ma 25/11/2024 tem vr 20/12/2024. Het spoor mag bezet zijn tijdens de buitendienststelling\r\nBediening van de sporen 415 en 416  door NMBS mogelijk over de middag.","Autre","Minor_AdHoc"," "," ",60524]
["2024-10-28","2024-12-08","SW",1,"94","A/B","Y.SILLY","ATH","AllWeek","Continuous","06:00","05:00","ART 4.5 min\r\nSilly - Ath : Renouvellement de traverses\r\nP93 : 2x 10,5 km","ART","Minor_AdHoc","ART stabilisation (60 km/h): du 28/10 au 08/12/2024 - Dans une voie en alternance chaque semaine.\r\nHKV\t4.5 min"," ",60886]
["2024-10-29","2024-11-02","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst","CTL","Minor_AdHoc",null,null,58580]
["2024-10-31","2024-11-03","SE",2,"161","A+B","OTTIGNIES","GEMBLOUX","Weekend","Continuous","23:40","17:00","Maintenance massifiée + entretien des PN+ travaux ES \r\nRév et Géo 01AF/01BF/02AF/02BF/03AF/03BF/05F - 04AE/04BE","CTL","Medium","VA : de 29.875 E3 / D29 à 44.164 DX4 / F29\r\nVB : A'de 44000 D3/F29 à 29.882 EX2/D29\r\nART 2 min du 3/11 au 18/11"," ",50727]
["2024-10-31","2024-11-04","CE",1,"28(1)","B","BRUXELLES-MIDI","Y.CUREGHEM","Weekend","Continuous","23:30","04:30","Linked to coupure nr 52657 on line 28(1) tracks(s) * from BRUXELLES-MIDI to BRUXELLES-MIDI: Vernieuwing 45I/46BI-33XI-42AI/43I","SAVU","Minor_AdHoc"," "," ",52657]
["2024-10-31","2024-11-04","CE",1,"28(1)","*","BRUXELLES-MIDI","BRUXELLES-MIDI","Weekend","Continuous","23:30","04:30","Vernieuwing 45I/46BI-33XI-42AI/43I","Autre","Minor_AdHoc","Does op L28 en L50A.\r\nFBMZ sporen 9 en 11 BDS, sp 10 in cds.\r\nVerkeer van/naar Vorst via cds Cureghem."," ",52657]
["2024-10-31","2024-11-04","CE",1,"50A","A","BRUXELLES-MIDI","BRUXELLES-PETITE-ILE","Weekend","Continuous","23:30","04:30","Linked to coupure nr 52657 on line 28(1) tracks(s) * from BRUXELLES-MIDI to BRUXELLES-MIDI: Vernieuwing 45I/46BI-33XI-42AI/43I","SAVU","Minor_AdHoc"," "," ",52657]
["2024-10-31","2024-11-04","SE",2,"162","A+B","HAVERSIN","ROCHEFORT-JEMELLE","Weekend","Continuous","23:40","04:20","Travaux caténaire .\r\nmassifs / poteaux/ CDPA / feeder / R3 mixte / démontage caténaire existante\r\nRq 333 : rq suite semestrielle à replanifier (voir commentaire)\r\ndemande reporter vers décembre, mais pas pendant le WE de changement plan de transport-","CTL","Medium",null," ",60137]
["2024-10-31","2024-11-04","SE",2,"44","A+B","PEPINSTER-CITE","SPA-GERONSTERE","AllWeek","Continuous","23:00","05:00","Renouvellement des équipements de signalisation des PNs 3, 4, 5 et 6 (Préparation et ou MES)\r\n+ Entretien manuel et mécanisés des AW \r\nEntretien manuel et mécanisés de la voie courante\r\nEntretien manuel et mécanisés des PN","CTL","Medium",null," ",56332]
["2024-10-31","2024-11-04","SE",3,"130","B","HAM-SUR-SAMBRE","AUVELAIS","Weekend","Continuous","23:00","05:00","électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu\r\nRq 333 : incompatible id 50727 à arbitrer\r\nDates à proposer I-CBE - possible déborder premier semestre 2025","SAVU","Minor_AdHoc","une voie hors service en continu\r\nWE 3 jours","HKM à adapter",47160]
["2024-10-31","2024-11-04","SW",1,"118","A+B","BRACQUEGNIES","MONS","Weekend","Continuous","23:30","04:30","Massification L118 \r\nMES Simis-W L118 Mons-Obourg & Obourg","CTL","Medium","WE 3 jours"," ",52126]
["2024-10-31","2024-11-18","SE",2,"161","A+B","OTTIGNIES","GEMBLOUX","AllWeek","Continuous","23:40","04:30","ART 2min\r\nMaintenance massifiée + entretien des PN+ travaux ES","ART","Minor_AdHoc","ART protection et stabilisation:\r\nLongueur: 100 mètres \r\nVitesse réduite: 40 km/h\r\nDate de mise en vigueur: du 31/10 au 11/11\r\nPerte de temps: \r\nHKV: 2'\r\nHKM: 1,9'"," ",59496]
["2024-11-01","2024-11-03","SE",1,"165","A+B","FLORENVILLE","BERTRIX","AllWeek","Continuous","08:00","16:00","Linked to coupure nr 49597 on line 166 tracks(s) A+B from PALISEUL to BERTRIX: Mise en service PLP et modifications ETCS gare de Bertrix et bloc automatique Libramont - Bertrix.","CTL","Medium"," "," ",49597]
["2024-11-01","2024-11-03","SE",1,"165(1)","A+B","BERTRIX","LIBRAMONT","AllWeek","Continuous","08:00","16:00","Linked to coupure nr 49597 on line 166 tracks(s) A+B from PALISEUL to BERTRIX: Mise en service PLP et modifications ETCS gare de Bertrix et bloc automatique Libramont - Bertrix.","CTL","Medium"," "," ",49597]
["2024-11-01","2024-11-03","SE",1,"166","A+B","PALISEUL","BERTRIX","AllWeek","Continuous","08:00","16:00","Mise en service PLP et modifications ETCS gare de Bertrix et bloc automatique Libramont - Bertrix.","CTL","Medium"," "," ",49597]
["2024-11-01","2024-11-04","NE",1,"29","A+B","Y.KRUISBERG","TURNHOUT-BUNDEL","Weekend","Continuous","04:00","04:00","Linked to coupure nr 55023 on line 15 tracks(s) A+B from Y.NAZARETH to GEEL: Indienstname ETCS\r\n+Brugdag. Meewerken niet mogelijk\r\nBack-up","CTL","Medium"," "," ",55023]
["2024-11-01","2024-11-04","NE",2,"19","A+B","MOL","HAMONT","Weekend","Continuous","00:00","04:00","vernieuwen bevestiging spoorstaven aan brug kanaal Beverlo-Balen","CTL","Medium",null," ",58126]
["2024-11-01","2024-11-17","SE",1,"43","B","ANGLEUR","TILFF","AllWeek","Continuous","08:00","16:00","Criblage de Ballast (entre BK 500 et BK 2300)\r\nDe jours : ballastage, bourrage\r\nDe nuit : criblage dans la CTL\r\nDossier de concertation validé en octobre 2021\r\n+ Renouvellement pièces caténaire","SAVU_CTRL","High","CTL de nuits (Lu/Ma à Je/Ve) de minimum 6h00 (23:00-5:00)\r\nART de protection en voie A à 60km/h (3' HKV / 4' HKM)\r\n\r\nART de stabilisation en voie A à 40/60 km/h (dépend de la présence de la DGS ou non), \r\n*/ 40 km/h (2.8' HKV / 1,96' HKM)\r\n*/ 60 km/h (1"," ",47682]
["2024-11-01","2024-11-04","SE",2,"154","A/B","JAMBES","YVOIR","Weekend","Continuous","23:00","05:00","Entretien AS , traitement zone boueuse","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 04/11 au 07/11 (fin probable)"," ",57691]
["2024-11-02","2024-11-03","NW",3,"50","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Night","21:30","05:30","Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P008_L50A_Gent Sint Pieters_ETCS\r\nVolledige zone 8u buiten dienst\r\n-------------------\r\nIDS Gent Sint Pieters verplaatst naar 30/06/2025 Mail Laurent\r\nVolledige zone 8u buiten dienst","CTL","Minor_AdHoc","FGSP niet bereikbaar"," ",59039]
["2024-11-02","2024-11-03","NW",3,"50A","A+B","Y.ASSELS","Y.MEULEWIJK","Weekend","Night","21:30","05:30","Linked to coupure nr 59039 on line 50 tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P008_L50A_Gent Sint Pieters_ETCS\r\nVolledige zone 8u buiten dienst\r\n-------------------\r\nIDS Gent Sint ","CTL","Minor_AdHoc"," "," ",59039]
["2024-11-02","2024-11-03","NW",3,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Weekend","Night","21:30","05:30","Linked to coupure nr 59039 on line 50 tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P008_L50A_Gent Sint Pieters_ETCS\r\nVolledige zone 8u buiten dienst\r\n-------------------\r\nIDS Gent Sint ","CTL","Minor_AdHoc"," "," ",59039]
["2024-11-02","2024-11-03","NW",3,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Night","21:30","05:30","Linked to coupure nr 59039 on line 50 tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P008_L50A_Gent Sint Pieters_ETCS\r\nVolledige zone 8u buiten dienst\r\n-------------------\r\nIDS Gent Sint ","CTL","Minor_AdHoc"," "," ",59039]
["2024-11-02","2024-11-03","NW",3,"75","A+B","GENT-SINT-PIETERS","DE PINTE","Weekend","Night","21:30","05:30","Linked to coupure nr 59039 on line 50 tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Testen, meewerken niet mogelijk\r\nETCS L2-IL_NW_P008_L50A_Gent Sint Pieters_ETCS\r\nVolledige zone 8u buiten dienst\r\n-------------------\r\nIDS Gent Sint ","CTL","Minor_AdHoc"," "," ",59039]
["2024-11-02","2024-11-03","NW",3,"75","B","WAREGEM","KORTRIJK","Weekend","Night","22:15","06:00","vervangen rijdraad SP B - JVO\r\nSP A bijkomend tijdens de nacht 00.20-05.15","SAVU_CTRL","Minor_AdHoc",null," ",58608]
["2024-11-02","2024-11-03","SE",3,"161","A/B","OTTIGNIES","GEMBLOUX","Weekend","Day","08:00","16:00","Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles + 1/2h sas Rhisnes","SAVU","Minor_AdHoc","SAVU alternatif entre 08h00 et 16h00"," ",48955]
["2024-11-02","2024-11-03","SW",1,"130","B","CHATELET-GRIL EST","CHATELET","Weekend","Continuous","22:00","22:00","Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.c\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc","Mise hors service Zone 17 :\r\nSAVU L130 FCL/Le Campinaire\r\n+ Faisceaux A et B en CDS côté Namur\r\n+ Faisceaux K et D inaccessibles"," ",49320]
["2024-11-02","2024-11-03","SW",1,"130","B","CHATELET-GRIL EST","CHATELET-GRIL EST","Weekend","Continuous","22:00","22:00","Linked to coupure nr 49320 on line 130 tracks(s) B from CHATELET-GRIL EST to CHATELET: Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.c\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 ","SAVU","Minor_AdHoc"," "," ",49320]
["2024-11-02","2024-11-04","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58040]
["2024-11-02","2024-11-04","NE",2,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Weekend","Continuous","00:00","04:50","brug Leuvensesteenweg , voorbereiding lift\r\nX blijft open richting L27\r\nMechelen inclusief perrons\r\nL25N open","CTL","Medium","perrons mechelen inclusief BD"," ",58178]
["2024-11-02","2024-11-04","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Medium","geen verkeer sporen 1+2+3"," ",58146]
["2024-11-02","2024-11-04","NE",2,"54","A+B","Y.HEIKE","WILLEBROEK","Weekend","Continuous","00:00","04:00","vernieuwen spoor L54,OW2 en AW01H\r\n\r\n\r\nBTS tussen de weekends, vertraging afhankelijk van uitgevoerde zone en fasering werken \r\nmas op area NE, R+5'","CTL","Medium"," "," ",58312]
["2024-11-02","2024-12-05","SE",3,"154","A+B","YVOIR","Y.NEFFE","AllWeek","Continuous","04:30","23:00","ART 2min\r\nEntretien AS traitement zone boueuse","ART","Minor_AdHoc","ART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 02/12 au 05/12 (fin probable)"," ",61664]
["2024-11-03","2024-11-03","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",60005]
["2024-11-03","2024-11-03","SE",1,"162","B","LIBRAMONT","HATRIVAL","Weekend","Continuous","00:30","15:00","Mise en service PLP et modifications ETCS gare de Bertrix et bloc automatique Libramont - Bertrix et nouvelle ligne L162/1.\r\nMassifié avec MES Bertrix","SAVU","Minor_AdHoc",null," ",49601]
["2024-11-04","2024-11-08","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2+3"," ",58150]
["2024-11-04","2024-11-08","NE",2,"27","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Week","Night","23:50","04:00","Brug Leuvensesteenweg , voorbereiding BVL\r\nvanaf einde perrons 3+4 tot Mechelen -Dijkstraat\r\ndeels samen met L53A-L53","CTL","Minor_AdHoc"," "," ",58220]
["2024-11-04","2024-11-08","NE",2,"53","A+B","MECHELEN","MUIZEN","Week","Night","23:50","04:00","Brug Leuvensesteenweg, voorbereiding BVL\r\n(rooster N niet beschikbaar L27)\r\ndeels samen met L27,L53","CTL","Minor_AdHoc"," "," ",58331]
["2024-11-04","2024-11-08","NE",2,"53","A+B","HAMBOS","Y.DIJLEBRUG","Week","Night","23:20","05:00","railvernieuwing (nodig wegens veel railfouten)\r\n+\r\nherelectrificatie (bijkomend) zie colt 60288","CTL","Minor_AdHoc","alternatief E2645-E2644"," ",58342]
["2024-11-04","2024-11-08","NE",2,"53A","A+B","MECHELEN","Y.MUIZEN","Week","Night","23:50","04:00","Brug Leuvensesteenweg, voorbereiding BVL\r\n(rooster N blijft vrij L27)\r\ndeels samen met L27,L53\r\n\r\nnog te bepalen of/wanneer werken door gaan","CTL","Minor_AdHoc"," "," ",58291]
["2024-11-04","2024-11-08","NE",3,"19","A+B","BALEN-WERKPLAATSEN","HAMONT-GRENS","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt\r\n+\r\nvernieuwen bevestiging spoorstaven aan brug kanaal Beverlo-Balen","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59888]
["2024-11-04","2024-11-08","NW",1,"50A/5","A+B","BRUGGE-ROOSTER E","BRUGGE","Week","Night","23:50","05:00","Vernieuwing wissels Brugge\r\nSporen 4, 5, 6 en 7 Brugge buiten dienst.\r\nSpoor 3 doodspoor bereikbaar kant kust.\r\nSporen 1 en 2 enkel bereikbaar via bundels.","CTL","Minor_AdHoc"," "," ",47708]
["2024-11-04","2024-11-08","NW",1,"66","A","BRUGGE","ZEDELGEM-ROOSTER E/G","Week","Night","23:50","05:00","Linked to coupure nr 47708 on line 50A/5 tracks(s) A+B from BRUGGE-ROOSTER E to BRUGGE: Vernieuwing wissels Brugge\r\nSporen 4, 5, 6 en 7 Brugge buiten dienst.\r\nSpoor 3 doodspoor bereikbaar kant kust.\r\nSporen 1 en 2 enkel bereikbaar via bundels.","SAVU","Minor_AdHoc"," "," ",47708]
["2024-11-04","2024-11-08","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement des Tabliers métalliques  + 5chapes \r\nTravaux RER Ottignies (CSV)","CTL","Minor_AdHoc",null," ",56087]
["2024-11-04","2024-11-09","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Week","Night","22:00","04:45","Travaux SNCF\r\nGare de Jeumont fermée","CTL","Minor_AdHoc",null," ",59250]
["2024-11-04","2024-11-15","SE",1,"42","A+B","RIVAGE","GOUVY","AllWeek","Continuous","05:30","23:00","ART 1min\r\nCriblage voie U \r\nRenouvellement RTB dans les voies A et B du tunnel de Trois-Ponts","ART","Minor_AdHoc","ART de stabilisation de bk 55223 à 55568 (350m) \r\nVitesse réduite à 60km/h \r\nperte de temps:\r\nHKV:1min\r\nHKM: 1min\r\nART de stabilisation du 4/11 au 15/11"," ",59604]
["2024-11-04","2024-12-02","SW",1,"94","A/B","Y.SILLY","ATH","AllWeek","Continuous","06:00","05:00","Silly - Ath : Renouvellement de traverses\r\nP93 : 2x 10,5 km","SAVU_CTRL","High","4 semaines SAVU jour et CTL nuit (22h45-05h30) + CTL weekend\r\nART stabilisation (60 km/h): du 28/10 au 08/12/2024 - Dans une voie en alternance chaque semaine.\r\nHKV\t4.5 min"," ",48767]
["2024-11-05","2024-11-08","SE",2,"140","A+B","OTTIGNIES","OTTIGNIES","Week","Continuous","08:00","16:00","Entretien en gare d'Ottignies","Autre","Minor_AdHoc","Voie 10 + Voie 11 HS entre les AS 16AR/16BR et 10AR/OR.29\r\n-> une voie HS continu et l'autre de jour 8h-16h\r\nService ES révision et Géométrie 09BR/10AR/12R/13BR"," ",51112]
["2024-11-05","2024-11-08","SE",2,"140","B","OTTIGNIES","CEROUX-MOUSTY","Week","Continuous","08:00","16:00","Linked to coupure nr 51112 on line 140 tracks(s) A+B from OTTIGNIES to OTTIGNIES: Entretien en gare d'Ottignies","SAVU","Minor_AdHoc"," "," ",51112]
["2024-11-05","2024-11-09","NW",2,"53","B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels + Vernieuwen rails \r\n\r\nDOES wegens geen CBP - FDR SP IV tem IX mee buiten dienst, bundel toegankelijk kan FM, CDS 108 mee BD\r\n\r\nR5/R6 does mogelijk tot 06u","SAVU","Minor_AdHoc",null,null,58581]
["2024-11-07","2024-11-07","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55952]
["2024-11-08","2024-11-11","NE",1,"12","A+B","Y.SINT-MARIABURG","Y.LUCHTBAL","Weekend","Continuous","23:30","04:00","oude landen 301","CTL","Medium","geen verkeer L12 tussen Antwerpen luchtbal en Kapellen"," ",58054]
["2024-11-08","2024-11-11","SE",3,"161","A","GEMBLOUX","RHISNES","Weekend","Continuous","23:00","05:00","réélectrification","SAVU","Minor_AdHoc","une voie en continu"," ",52670]
["2024-11-08","2024-11-11","SE",3,"161","A+B","GEMBLOUX","NAMUR","Weekend","Continuous","23:00","05:00","Entretien des PN + massification maintenance + contrôles ES","SAVU","Minor_AdHoc","SAVU VA du Ve 22H au Di 06H\r\nSAVU VB du Sa 22H au Lu 06H\r\nMaximum 4 trains/h dans la voie en service\r\nART protection et stabilisation:\r\nLongueur: 100 mètres \r\nVitesse réduite: 40 km/h\r\nDate de mise en vigueur: du 13/09 au 07/10 à minuit \r\nPerte de temps"," ",51115]
["2024-11-08","2024-11-12","CE",1,"96B","A+B","BRUXELLES-MIDI","FOREST-MIDI-VOIES 920/926","Weekend","Continuous","(vide)","(vide)","Linked to coupure nr 52472 on line 96B tracks(s) * from FOREST-NORD to FOREST-MIDI-VOIES 920/926: Upgrade cabine Vorst met herparametrering ETCS","CTL","Medium"," "," ",52472]
["2024-11-08","2024-11-12","CE",1,"96B","*","FOREST-NORD","FOREST-MIDI-VOIES 920/926","Weekend","Continuous","(vide)","(vide)","Upgrade cabine Vorst met herparametrering ETCS","Autre","Minor_AdHoc","Vorst niet bereikbaar gedurende gans het weekend."," ",52472]
["2024-11-08","2024-11-12","CE",1,"96C","S","BRUXELLES-MIDI","FOREST-NORD","Weekend","Continuous","(vide)","(vide)","Linked to coupure nr 52472 on line 96B tracks(s) * from FOREST-NORD to FOREST-MIDI-VOIES 920/926: Upgrade cabine Vorst met herparametrering ETCS","CTL","Medium"," "," ",52472]
["2024-11-08","2024-11-12","CE",1,"96D","S","BRUXELLES-MIDI","FOREST-FAISCEAU M","Weekend","Continuous","(vide)","(vide)","Linked to coupure nr 52472 on line 96B tracks(s) * from FOREST-NORD to FOREST-MIDI-VOIES 920/926: Upgrade cabine Vorst met herparametrering ETCS","CTL","Medium"," "," ",52472]
["2024-11-08","2024-11-12","NE",2,"19","A+B","MOL","HAMONT","Weekend","Continuous","22:00","05:00","vernieuwen bevestiging spoorstaven aan de brug Kempisch kanaal\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt(59922)","CTL","Medium",null," ",58128]
["2024-11-08","2024-11-12","NW",1,"50A/5","A+B","BRUGGE-ROOSTER E","BRUGGE","Weekend","Continuous","23:00","05:00","Vernieuwing wissels Brugge\r\nSporen 4, 5, 6 en 7 Brugge buiten dienst.\r\nSpoor 3 doodspoor bereikbaar kant kust.\r\nSporen 1 en 2 enkel bereikbaar via bundels.","CTL","Medium"," "," ",47709]
["2024-11-08","2024-11-12","NW",1,"66","A","BRUGGE","ZEDELGEM-ROOSTER E/G","Weekend","Continuous","23:00","05:00","Linked to coupure nr 47709 on line 50A/5 tracks(s) A+B from BRUGGE-ROOSTER E to BRUGGE: Vernieuwing wissels Brugge\r\nSporen 4, 5, 6 en 7 Brugge buiten dienst.\r\nSpoor 3 doodspoor bereikbaar kant kust.\r\nSporen 1 en 2 enkel bereikbaar via bundels.","SAVU","Minor_AdHoc"," "," ",47709]
["2024-11-08","2024-11-12","SE",1,"162","A+B","GRUPONT","HATRIVAL","Weekend","Continuous","22:15","05:00","Travaux Axe 3 Grupont-Hatrival:\r\ntravaux OA","CTL","Medium"," "," ",47363]
["2024-11-08","2024-11-12","SE",2,"162","A+B","HAVERSIN","ROCHEFORT-JEMELLE","Weekend","Continuous","23:40","04:20","Travaux caténaire .\r\nmassifs / poteaux/ CDPA / feeder / R3 mixte / démontage caténaire existante\r\nRq 333 : rq suite semestrielle à replanifier (voir commentaire)\r\ndemande reporter vers décembre, mais pas pendant le WE de changement plan de transport-","CTL","Medium","A coordonner avec travaux OA prévu ce we-là sur Grupont-Hatrival du 8 au 12/11/24"," ",60138]
["2024-11-08","2024-11-12","SE",3,"44","A+B","PEPINSTER-CITE","SPA-GERONSTERE","AllWeek","Continuous","23:00","05:00","Entretien manuel et mécanisés des AW \r\nEntretien manuel et mécanisés de la voie courante\r\nEntretien manuel et mécanisés des PN","CTL","Medium",null," ",55097]
["2024-11-08","2024-11-12","SW",2,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement des Tabliers métalliques  + 5chapes \r\nWE 3 jrs de chapes\r\n+ Maintenance Z3. 51  P4+","CTL","Medium","CTL de WE\r\nART 2 semaines 2 min","HKM à adapter",55569]
["2024-11-08","2024-11-18","SE",1,"166","B","BEAURAING","VONECHE","AllWeek","Continuous","23:00","05:00","Renouvellement ballast par train C75 (phase 1 : VB).","SAVU","High",null,"restriction capacité importante -> Partie HKM dévies via ANE",47812]
["2024-11-09","2024-11-10","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61589]
["2024-11-09","2024-11-10","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60427]
["2024-11-09","2024-11-10","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60427 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60427]
["2024-11-09","2024-11-10","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60427 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60427]
["2024-11-09","2024-11-10","SE",3,"161","A/B","GEMBLOUX","RHISNES","Weekend","Day","08:00","16:00","Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49200]
["2024-11-09","2024-11-10","SW",1,"130","B","CHATELET-GRIL EST","CHATELET","Weekend","Continuous","22:00","22:00","Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.c\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 octobre 2021","SAVU","Minor_AdHoc","Mise hors service Zone 17 :\r\nSAVU L130 FCL/Le Campinaire\r\n+ Faisceaux A et B en CDS côté Namur\r\n+Faisceaux K et D inaccessibles"," ",49321]
["2024-11-09","2024-11-10","SW",1,"130","B","CHATELET-GRIL EST","CHATELET-GRIL EST","Weekend","Continuous","22:00","22:00","Linked to coupure nr 49321 on line 130 tracks(s) B from CHATELET-GRIL EST to CHATELET: Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.c\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 ","SAVU","Minor_AdHoc"," "," ",49321]
["2024-11-09","2024-11-10","SW",2,"117","A+B","MANAGE","LUTTRE","Weekend","Continuous","06:00","17:00","Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52","CTL","Medium","P4+"," ",46538]
["2024-11-09","2024-11-10","SW",3,"118","A+B","MONS","Y.SAINT-VAAST","Weekend","Continuous","06:00","16:00","Maintenance Z.8.53 + Z11.52 P4","CTL","Medium",null," ",56439]
["2024-11-09","2024-11-11","CE",2,"26","A+B","Y.RUE DE BRUEL","Y.CINQUANTENAIRE","Weekend","Continuous","06:00","22:00","P085306 BVL L26 Y Bruul - Y50.\r\nY Bruulstraat is niet inbegrepen.","CTL","Medium","TLO tussen Y Bruulstr en Y50","Info Racc",59648]
["2024-11-09","2024-11-11","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58041]
["2024-11-09","2024-11-11","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Medium","geen verkeer sporen 1+2+3"," ",58147]
["2024-11-09","2024-11-11","NE",2,"53","A+B","HAMBOS","Y.DIJLEBRUG","Weekend","Continuous","00:00","04:00","railvernieuwing nodig wegens veel railfouten)","CTL","Medium"," "," ",58343]
["2024-11-09","2024-11-11","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Weekend","Continuous","06:00","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst\r\n\r\nStart R6 wegens geen CBP mogelijk R5/R6\r\nR5/R6 DOES met CoLT 58581","CTL","Medium",null,null,58574]
["2024-11-10","2024-11-10","NE",3,"11","A+B","Y.SCHIJN","ANTWERPEN-D.S.-BASF","Weekend","Continuous","06:30","18:00","Onderhouswerken aan de sporen, wissels sienen, sk's, ...","CTL","Medium"," "," ",61616]
["2024-11-10","2024-11-10","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",60006]
["2024-11-11","2024-11-15","NE",2,"53","A+B","HAMBOS","Y.DIJLEBRUG","Week","Night","23:20","04:00","railvernieuwing (nodig wegens veel railfouten)","CTL","Minor_AdHoc"," "," ",58344]
["2024-11-11","2024-11-15","NE",3,"139","A+B","LEUVEN","SINT-JORIS-WEERT","Week","Night","23:00","05:00","Onderhoud","CTL","Minor_AdHoc","alternatief E5722"," ",60244]
["2024-11-11","2024-11-15","NE",3,"19","A+B","BALEN-WERKPLAATSEN","HAMONT-GRENS","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt\r\n+\r\nvernieuwen bevestiging spoorstaven aan brug kanaal Beverlo-Balen","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59889]
["2024-11-11","2024-11-16","SE",1,"42","A+B","RIVAGE","GOUVY","Week","Night","23:30","05:00","Criblage voie U \r\nRenouvellement RTB dans les voies A et B du tunnel de Trois-Ponts\r\nContraintes et finitions","CTL","Minor_AdHoc","Gare de Trois-Pont incluse\r\nCTL entre fin des quais de Trois-Ponts et Vielsalm\r\nART de stabilisation de bk 55223 à 55568 (350m) 3 minutes du 4/11 au 15/11"," ",47013]
["2024-11-11","2024-11-16","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Week","Night","22:00","04:45","Travaux SNCF\r\nGare de Jeumont fermée","CTL","Minor_AdHoc",null," ",59251]
["2024-11-12","2024-11-15","NE",2,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Week","Night","00:00","04:50","brug Leuvensesteenweg , voorbereiding lift\r\nX blijft open richting L27\r\nMechelen inclusief perrons\r\nL25N open","CTL","Minor_AdHoc","perrons mechelen inclusief BD\r\nalternatief E3323-E2644-E1794"," ",58182]
["2024-11-12","2024-11-15","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst\r\n\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc",null,null,58582]
["2024-11-12","2024-11-15","SE",3,"140","*","OTTIGNIES","OTTIGNIES","Week","Continuous","08:00","16:00","Maintenance voies 9 et 10 en gare d'Ottignies\r\nMHS zone voies 120,119,140,996 (Voie B L140): points de limites entre les OR- talon 12R / Talon 16AR-Talon 19BR","CTL","Medium","voies 9 et 10 HS entre les 19BR/16AR et OR/12R\r\n-> une voie HS continu et l'autre de jour 8h-16h"," ",51113]
["2024-11-12","2024-11-15","SW",2,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement des Tabliers métalliques  + 5chapes \r\nFinitions","CTL","Minor_AdHoc","CTL de nuit de semaine"," ",55568]
["2024-11-12","2024-11-25","SW",2,"140","A+B","OTTIGNIES","FLEURUS","AllWeek","Continuous","05:00","05:00","ART 2min\r\nRenouvellement des Tabliers métalliques  + 5chapes","ART","Minor_AdHoc","ART 2 semaines 2 min","HKM à adapter",61376]
["2024-11-13","2024-11-15","NW",3,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Week","Night","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Minor_AdHoc",null,"Info Racc",57802]
["2024-11-14","2024-11-14","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60117]
["2024-11-15","2024-11-17","SW",2,"287","A","ATH","GHISLENGHIEN","Weekend","Continuous","13:00","23:00","Mise en service - Renouvellement des CVs et PNs","CTL","Medium",null," ",50565]
["2024-11-15","2024-11-18","NE",2,"53","A+B","HAMBOS","Y.DIJLEBRUG","Weekend","Continuous","23:20","04:00","railvernieuwing  (nodig wegens veel railfouten)\r\n+\r\n \r\nherelectrificatie (bijkomend) colt 60289","CTL","Medium","alternatief E2645-E2644"," ",58345]
["2024-11-15","2024-11-18","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt\r\n\r\n+\r\nvernieuwen bevestiging spoorstaven aan brug kanaal Beverlo-Balen (58127)","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59923]
["2024-11-15","2024-11-18","NW",1,"75","A+B","Y.BETHUNE","MOUSCRON","Weekend","Continuous","23:10","04:00","TLO-Weekend voor onderhouds werken\r\nminimum van 2 weekends per jaar, 1 weekend maart/april + 1 weekend oktober/november\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken mogelijk\r\n\r\n\r\nIngekort tot Y-bethune door combinatie m","CTL","Medium"," "," ",47300]
["2024-11-15","2024-11-18","NW",2,"66","A+B","Y.KORTRIJK-WEST","LICHTERVELDE","Weekend","Continuous","23:50","05:00","Indienstname PLP \r\nLichtervelde - Roeselare\r\nStations niet inbegrepen\r\n\r\nTestritten op zondag tot op de perrons van Lichtervelde en Roeselare in overleg met regelaar","CTL","Medium"," "," ",57582]
["2024-11-15","2024-11-18","SE",1,"161","A+B","BRUXELLES-LUXEMBOURG","OTTIGNIES","Weekend","Continuous","23:30","04:50","WE CTL RER Watermael - Ottignies","CTL","Medium","ART à définir, maximum 2'","HKM à adapter",49264]
["2024-11-15","2024-11-18","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 min","HKM à adapter",48635]
["2024-11-15","2024-11-18","SW",1,"130","A+B","AUVELAIS","CHATELET-GRIL OUEST","Weekend","Continuous","23:40","05:00","Maintenance Z15. 51 P4+\r\n+ PS 87,100 - travaux en-dessous du tablier","CTL","Medium"," ","HKM à adapter",48835]
["2024-11-15","2024-11-18","SW",2,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Weekend","Continuous","23:00","05:40","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 1 - Nuits de préparation à la démolition\r\nPhase 1.1 - CTL de WE en continu pour travaux au niveau de la 1ère travée située au-dessus des L75 VA+L75 VB e","CTL","Medium","Les AW 03K, 04AK, 04BK/05AK, 10 AK, 11 AK restent parcourables"," ",57188]
["2024-11-15","2024-12-09","CE",1,"27D","*","Y.SCHAERBEEK-CARWASH","SCHAERBEEK-GROUPE R","AllWeek","Continuous","23:00","04:30","Herinrichting kop bundel R naast bundel V: sporen 745 tem 749","Autre","Minor_AdHoc","Sporen 745 tem 749 bundel R onbeschikbaar.\r\nUitbreidingen tijdens de nachten en weekends."," ",49964]
["2024-11-15","2024-11-18","SE",2,"154","A/B","LUSTIN","DINANT","Weekend","Continuous","23:00","05:00","Entretien AS , traitement zone boueuse\r\nRq 333 : Suite rq semestrielle : à replanifier hors période ART suite chantier\r\nART 50024 sera replan cf CR -> incompatibilité ne sera plus d'actualité","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 18/11 au 21/11 (fin probable)"," ",57693]
["2024-11-16","2024-11-17","NE",2,"52","A","PUURS","Y.ANTWERPEN-ZUID","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59104]
["2024-11-16","2024-11-17","NE",2,"59","A","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59103]
["2024-11-16","2024-11-17","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59423]
["2024-11-16","2024-11-17","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60412]
["2024-11-16","2024-11-17","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60412 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60412]
["2024-11-16","2024-11-17","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60412 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60412]
["2024-11-16","2024-11-17","SE",3,"165","A+B","HALANZY","Y.AUBANGE","Weekend","Continuous","23:00","15:00","Maintenance\r\nInterventions Programmées","CTL","Medium",null," ",46689]
["2024-11-16","2024-11-17","SE",3,"49","A+B","WELKENRAEDT","EUPEN","Weekend","Continuous","06:00","20:00","Linked to coupure nr 55131 on line 37 tracks(s) A+B from WELKENRAEDT to Y.HAMMERBRUCKE: Maintenance Z26.42\r\nEntretien manuel et mécanisés des AW de Welkenraedt 08BK, 09K, 10K, 11AK, 12K, 30AK, 14K, 15K\r\nEntretien manuel et mécanisés de la voie courante","CTL","Medium"," "," ",55131]
["2024-11-16","2024-11-17","SW",2,"90","A","LESSINES","GERAARDSBERGEN","Weekend","Continuous","07:00","18:00","Remplacement des CV50Hz par CV Jade","SAVU","Minor_AdHoc","Coupure des signaux MX-F.37 à P-M.2"," ",56835]
["2024-11-16","2024-11-18","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58042]
["2024-11-16","2024-11-18","NE",2,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Weekend","Continuous","00:00","04:50","brug Leuvensesteenweg , voorbereiding lift\r\nX blijft open richting L27\r\nMechelen inclusief perrons\r\nL25N open","CTL","Medium","perrons mechelen inclusief BD"," ",58179]
["2024-11-16","2024-11-18","NE",3,"27","A+B","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL","Weekend","Continuous","00:40","04:20","onderhoud SIG + wissels Y arendstraat+onderhous wissel antwerpen centraal -1\r\n\r\nperronsporen 11-12-13-14","CTL","Medium","nog te bepalen"," ",59731]
["2024-11-16","2024-11-18","NW",3,"50","A+B","DENDERLEEUW","AALST","Weekend","Continuous","01:00","04:00","onderhoud Aalst - Denderleeuw","CTL","Medium"," "," ",60813]
["2024-11-17","2024-11-17","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",60007]
["2024-11-17","2024-11-17","SE",2,"24","A+B","Y.GLONS","MONTZEN-FRONTIERE","Weekend","Day","06:00","15:45","MES ETCS L2-IL_SE_P030_L24_Glons - Montzen (without border)_ETCS\r\nmeewerken niet mogelijk","CTL","Minor_AdHoc","Pas de circulation possible entre Visé et DB\r\nPas de ciculation entre Longchamps vers DB"," ",61180]
["2024-11-17","2024-11-17","SE",2,"24/1","A+B","Y.LONGCHAMPS","Y.BERNEAU","Weekend","Day","06:00","15:45","Linked to coupure nr 61180 on line 24 tracks(s) A+B from Y.GLONS to MONTZEN-FRONTIERE: MES ETCS L2-IL_SE_P030_L24_Glons - Montzen (without border)_ETCS\r\nmeewerken niet mogelijk","CTL","Minor_AdHoc"," "," ",61180]
["2024-11-17","2024-11-18","NW",3,"66","*","KORTRIJK","Y.LEIEBRUG","Weekend","Continuous","00:30","04:00","Wisselverbindingen Kortrijk Kant Brugge: vernieuwen rijdraad en I's - JVS\r\ngeen verkeer kant Kust / Moeskroen\r\n\r\n* verplaatst naar WE46 om te combineren met PLP L66 + onderhoud L75","CTL","Medium",null," ",58769]
["2024-11-17","2024-11-18","NW",3,"75","A+B","KORTRIJK","Y.BETHUNE","Weekend","Continuous","00:30","04:00","Linked to coupure nr 58769 on line 66 tracks(s) * from KORTRIJK to Y.LEIEBRUG: Wisselverbindingen Kortrijk Kant Brugge: vernieuwen rijdraad en I's - JVS\r\ngeen verkeer kant Kust / Moeskroen\r\n\r\n* verplaatst naar WE46 om te combineren met PLP L66 + onderho","CTL","Medium"," "," ",58769]
["2024-11-17","2024-11-18","NW",3,"75C","A+B","Y.BETHUNE","KORTRIJK","Weekend","Continuous","00:30","04:00","Linked to coupure nr 58769 on line 66 tracks(s) * from KORTRIJK to Y.LEIEBRUG: Wisselverbindingen Kortrijk Kant Brugge: vernieuwen rijdraad en I's - JVS\r\ngeen verkeer kant Kust / Moeskroen\r\n\r\n* verplaatst naar WE46 om te combineren met PLP L66 + onderho","CTL","Medium"," "," ",58769]
["2024-11-17","2024-11-24","SE",1,"43","A","ANGLEUR","TILFF","AllWeek","Continuous","23:00","16:00","Criblage de Ballast (entre BK 500 et BK 2300)\r\nDe jours : ballastage, bourrage\r\nDe nuit : criblage dans la CTL\r\nDossier de concertation validé en octobre 2021","SAVU_CTRL","Minor_AdHoc","CTL de nuits (Lu/Ma à Je/Ve) de minimum 6h00 (23:00-5:00)\r\nART de protection/stabilisation en voie B à 60km/h (3' HKV / 4' HKM) du 17 au 29/11"," ",49911]
["2024-11-18","2024-11-18","SE",3,"130","A/B","NAMUR","FLAWINNE","Week","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49067]
["2024-11-18","2024-11-22","NE",2,"53","A+B","MUIZEN-ROOSTER T","LEUVEN","Week","Night","23:20","05:00","herelectrificatie (bijkomend)\r\n+\r\nrailvernieuwing  colt 58346?","CTL","Minor_AdHoc","alternatief E2645-E2644"," ",60290]
["2024-11-18","2024-11-22","NE",3,"12","A+B","ANTWERPEN-NOORDERDOKKEN","Y.HOLLAND","Week","Night","23:25","04:00","onderheid SIG Y luchtbal en onderhoud wissel Y Antwerpen-luchtbal","CTL","Minor_AdHoc","alternatief E2573-E2594"," ",60122]
["2024-11-18","2024-11-22","NE",3,"19","A+B","BALEN-WERKPLAATSEN","HAMONT-GRENS","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt\r\n+\r\nvernieuwen bevestiging spoorstaven aan brug kanaal Beverlo-Balen","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59890]
["2024-11-18","2024-11-22","NE",3,"59","A+B","Y.OOST BERCHEM","Y.MELSELE","Week","Night","23:50","04:35","onderhoud SIG +onderhoud wissels en overwegen","CTL","Minor_AdHoc","alternatief E744"," ",60129]
["2024-11-18","2024-11-22","SW",2,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement des Tabliers métalliques  + 5chapes \r\nCTL finition + levé ART","CTL","Minor_AdHoc","CTL de nuit de semaine"," ",55570]
["2024-11-18","2024-11-23","NW",1,"75","A+B","KORTRIJK","MOUSCRON","Week","Night","23:10","04:00","Afwerkingsnachten na TLO-Weekend voor onderhouds werken\r\nminimum van 2 weekends per jaar, 1 weekend maart/april + 1 weekend oktober/november\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken mogelijk","CTL","Minor_AdHoc"," "," ",47667]
["2024-11-18","2024-11-23","SE",1,"42","A+B","RIVAGE","GOUVY","Week","Night","23:30","05:00","Criblage voie U \r\nRenouvellement RTB dans les voies A et B du tunnel de Trois-Ponts\r\nContraintes et finitions","CTL","Minor_AdHoc","Gare de Trois-Pont incluse\r\nCTL entre fin des quais de Trois-Ponts et Vielsalm\r\nART de stabilisation de bk 55223 à 55568 (350m) 3 minutes du 4/11 au 15/11"," ",59437]
["2024-11-18","2024-11-29","SE",1,"165","B","Y.AUBANGE","HALANZY","Week","Day","07:30","16:00","Sécurisation des pistes suite renouvellement ballast par train C75 à Aix-sur-Cloie VB.","SAVU","Minor_AdHoc",null,"restriction capacité importante -> Partie HKM dévies via ANE",47763]
["2024-11-18","2024-12-16","SE",1,"166","B","BEAURAING","VONECHE","AllWeek","Continuous","05:00","05:00","ART stabilisation 5' \r\nRenouvellement ballast par train C75 (phase 1 : VB + phase 2: VA)","ART","Minor_AdHoc","Phase 1 : ART de stabilisation à 40 (trois semaines)\r\nPhase 2 : ART de stabilisation à 40 (trois semaines)  --- réutilisation des ART de la phase 1.",null,48259]
["2024-11-18","2024-12-16","SE",1,"166","B","BEAURAING","VONECHE","AllWeek","Continuous","05:00","05:00","ART stabilisation 5' \r\nRenouvellement ballast par train C75 (phase 1 : VB + phase 2: VA)","ART","Minor_AdHoc","Phase 1 : ART de stabilisation à 40 (trois semaines)\r\nPhase 2 : ART de stabilisation à 40 (trois semaines)  --- réutilisation des ART de la phase 1.",null,48259]
["2024-11-19","2024-11-22","NW",2,"53","B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels + Vernieuwen rails \r\n\r\nDOES wegens geen CBP - FDR SP IV tem IX mee buiten dienst, bundel toegankelijk kan FM, CDS 108 mee BD","SAVU","Minor_AdHoc",null,null,58583]
["2024-11-19","2024-11-22","NW",3,"51B","A","Y.PELIKAAN","KNOKKE","Week","Night","00:30","04:30","Fietstunnel sportcentra Heist KP 112.000-112.100\r\n\r\n\r\n*R5/R6 in weekend TLO","CTL","Minor_AdHoc"," "," ",58552]
["2024-11-19","2024-11-23","NW",3,"66","A+B","LICHTERVELDE","Y.KORTRIJK-WEST","Week","Night","00:10","04:30","Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497","CTL","Minor_AdHoc",null,"Info Racc",57803]
["2024-11-20","2024-11-20","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60098]
["2024-11-22","2024-11-25","CE",1,"161","A/B","WATERMAEL","BAKENBOS","Weekend","Continuous","23:30","04:50","WE SAVU RER Watermael-Bakenbos","SAVU_CTRL","Minor_AdHoc","ART à définir - maximum 2'"," ",49257]
["2024-11-22","2024-11-25","CE",2,"94","A+B","HALLE","SAINTES","Weekend","Continuous","23:30","04:20","Afschaffen OW L94 area CE","CTL","Medium","TLO in continu"," ",58603]
["2024-11-22","2024-11-25","NE",3,"21D","A+B","Y.BOKSBERGHEIDE","GENK","Weekend","Continuous","23:20","04:40","Onderhoud","CTL","Medium"," "," ",59952]
["2024-11-22","2024-11-25","SE",1,"166","A","BEAURAING","VONECHE","Weekend","Continuous","23:00","05:00","Renouvellement ballast par train C75 (phase 2 : VA).","SAVU","Minor_AdHoc",null,"restriction capacité importante -> Partie HKM dévies via ANE",47813]
["2024-11-22","2024-11-25","SE",2,"43","A+B","ANGLEUR","RIVAGE-MARCHANDISES","Weekend","Continuous","23:50","05:00","Modernisation de la signalisation en PLP du block automatique Angleur Tilff avec suppression PN 7 et 8\r\nMise en service","CTL","Medium",null,"HKM à adapter",46971]
["2024-11-22","2024-11-25","SE",2,"49","S","WELKENRAEDT","RAEREN","Weekend","Continuous","23:00","05:00","Entretien de PN","CTL","Medium","CTL entre Welkenraedt (talon AW 12K non engagé) et Eupen signal K-R.53"," ",56275]
["2024-11-22","2024-11-25","SE",3,"130","A","HAM-SUR-SAMBRE","AUVELAIS","Weekend","Continuous","23:00","05:00","électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu","SAVU","Minor_AdHoc","une voie hors service en continu","HKM à adapter",47159]
["2024-11-22","2024-11-25","SW",2,"140","A+B","MARCINELLE","FLEURUS","Weekend","Continuous","23:00","05:00","Maintenance Z4. 51  P4+\r\n+ Renouvellement complet des PN","CTL","Medium",null,"HKM à adapter",49117]
["2024-11-22","2024-11-25","SW",2,"94","A+B","TOURNAI","FROYENNES","Weekend","Continuous","23:20","04:40","PI situé au km 84.380 de la L94\r\nCTL de WE en continu pour le remplacement des appuis en acier noble","CTL","Medium","CTL de WE en continu"," ",57336]
["2024-11-23","2024-11-23","SE",3,"139","A/B","WAVRE","OTTIGNIES","Weekend","Day","08:00","16:00","Visites des postes+ maintenances infrastructure et contrôles","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48874]
["2024-11-23","2024-11-24","NE",2,"52","A","PUURS","Y.ANTWERPEN-ZUID","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59106]
["2024-11-23","2024-11-24","NE",2,"59","A","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59105]
["2024-11-23","2024-11-24","SE",3,"161","A/B","NAMUR","RHISNES-SAS","Weekend","Day","08:00","16:00","Visite périodique + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","Savu alternatif VA/VB , de 8h à 16 h"," ",49214]
["2024-11-23","2024-11-24","SW",2,"116/1","A+B","Y.FAMILLEUREUX","Y.BOIS-D'HAINE","Weekend","Continuous","06:00","17:00","Linked to coupure nr 56291 on line 117 tracks(s) A+B from BRAINE-LE-COMTE to MANAGE: Maintenance Z.3.53 en P4\r\n+ Maintenance Zone Z09.52","CTL","Medium"," "," ",56291]
["2024-11-23","2024-11-24","SW",2,"117","A+B","BRAINE-LE-COMTE","MANAGE","Weekend","Continuous","06:00","17:00","Maintenance Z.3.53 en P4\r\n+ Maintenance Zone Z09.52","CTL","Medium"," "," ",56291]
["2024-11-23","2024-11-24","SW",3,"130C","A+B","CHATELET","CHARLEROI-SUD","Weekend","Continuous","06:00","17:00","Maintenance Z13. 51 (P4+)","CTL","Medium","Mise hors service en une zone, voici les détails:\r\nL130C\tVoie A\tCharleroi-Sud\tChâtelet\tFX5-I. 20\tI-H. 20\r\n\t        Voie B\t\t\tFX6-I. 21\tIX-H. 20"," ",48839]
["2024-11-23","2024-11-25","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58043]
["2024-11-23","2024-11-25","NE",2,"19","A+B","MOL","HAMONT","Weekend","Continuous","00:00","04:00","vernieuwen bevestiging spoorstaven aan dde brug Kempisch kanaal\r\n\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk\r\n+\r\naanleg tweede spoor tussen Balen en werkplaatsen Neerpelt (colt59924)","CTL","Medium",null," ",58129]
["2024-11-23","2024-11-25","NE",2,"53","A+B","HAMBOS","Y.DIJLEBRUG","Weekend","Continuous","00:00","04:00","railvernieuwing (nodig wegens veel railfouten)","CTL","Medium"," "," ",58347]
["2024-11-23","2024-11-25","NW",2,"50A","A+B","GENT-SINT-PIETERS","BRUGGE","Weekend","Continuous","01:00","04:00","Aanleg 3de en 4de spoor L50D + massificatiewerken","CTL","Medium","TLO 50A+ 50A5+ 50A6 +50D",null,59007]
["2024-11-23","2024-11-25","NW",2,"50A/5","A+B","Y.OOSTKAMP","BRUGGE-ROOSTER E","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59007 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken","CTL","Medium"," ",null,59007]
["2024-11-23","2024-11-25","NW",2,"50A/6","A+B","GENT-ROOSTER SNEPBRUG","Y.ASSELS","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59007 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken","CTL","Medium"," ",null,59007]
["2024-11-23","2024-11-25","NW",2,"50D","A+B","Y.ASSELS","LANDEGEM-ROOSTER G/H/L","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59007 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to BRUGGE: Aanleg 3de en 4de spoor L50D + massificatiewerken","CTL","Medium"," ",null,59007]
["2024-11-23","2024-11-25","NW",2,"51B","A","Y.PELIKAAN","KNOKKE","Weekend","Continuous","00:30","04:30","Fietstunnel sportcentra Heist KP 112.000-112.100\r\nReserveweekend","CTL","Medium"," "," ",58551]
["2024-11-23","2024-11-25","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Weekend","Continuous","00:10","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst","CTL","Medium",null,null,58576]
["2024-11-23","2024-11-25","NW",2,"55","A+B","WONDELGEM","ZELZATE-GRENS","Weekend","Continuous","05:00","05:00","L55 Wondelgem-Zelzate\r\nVernieuwing treindetectie\r\nTestritten op zondag tot op perrons te Wondelgem in overleg met de regelaar","CTL","Medium"," ","Info Racc",57580]
["2024-11-23","2024-11-25","SE",2,"139","A+B","SINT-JORIS-WEERT","WAVRE","Weekend","Continuous","06:00","05:00","Entretien des PN + maintenance massifiée + Travaux ES","CTL","Medium","ART protection et stabilisation:\r\nLongueur: 100 mètres \r\nVitesse réduite: 40 km/h\r\nDate de mise en vigueur: à partir du 23/11 au 02/12 \r\nPerte de temps: \r\nHKV: 2'\r\nHKM: 1,9'","HKM à adapter",50638]
["2024-11-23","2024-11-25","SE",2,"154","A/B","YVOIR","Y.NEFFE","AllWeek","Continuous","06:00","07:00","Mise en service EBP-PLP : gare de Dinant + BA (Dinant-Anseremme) + Anseremme.","SAVU_CTRL","Minor_AdHoc","SAVU par la voie B du Sa 23/11 à 06h00 au Di 24/11 à 07H00\r\nCTL du Sa 23/11 à 23H00 au Di 24/11 à 07H00.\r\nSAVU par la voie A du Di 24/11 à 07h00 au Lu 25/11 à 07h00","HKM à adapter",57896]
["2024-11-24","2024-11-24","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","06:00","17:40","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58667]
["2024-11-24","2024-11-24","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",60008]
["2024-11-24","2024-11-24","SE",3,"139","A/B","SINT-JORIS-WEERT","WAVRE","Weekend","Day","08:00","16:00","Visites des postes - maintenances diverses et révisions","SAVU","Minor_AdHoc","SAVU alternatif voie A et voie B - 8h/16h","HKM à adapter",48883]
["2024-11-25","2024-11-25","NW",3,"50L/3","*","OOSTENDE-BUNDEL A","OOSTENDE-BUNDEL A","Week","Day","08:00","(vide)","Vernieuwing Bundelspoor","Autre","Minor_AdHoc","Sporen 409 en 411 buiten dienst van 08u tot 16u"," ",60871]
["2024-11-25","2024-11-29","NE",2,"12","A+B","ANTWERPEN-OOST","Y.HOLLAND","Week","Night","22:30","05:30","onderhoud wissels en sporen te Antwerpen Schijnpoort inrit bundel E inclusief bundelkoppen C,E","CTL","Minor_AdHoc","geen toegang tot bundel E\r\ngeen toegang bundel D kant Y antwerpen-Oost"," ",60219]
["2024-11-25","2024-11-29","NE",2,"53","A+B","HAMBOS","Y.DIJLEBRUG","Week","Night","23:20","04:00","railvernieuwing (nodig wegens veel railfouten)\r\n+\r\nherelectrificatie colt 60291","CTL","Minor_AdHoc","alternatief E2645-E2644"," ",58348]
["2024-11-25","2024-11-29","NE",3,"19","A+B","BALEN-WERKPLAATSEN","HAMONT-GRENS","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt\r\n+\r\nvernieuwen bevestiging spoorstaven aan brug kanaal Beverlo-Balen","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59891]
["2024-11-25","2024-11-29","NE",3,"21D","A+B","Y.BOKSBERGHEIDE","GENK","Week","Night","23:20","04:40","Onderhoud","CTL","Minor_AdHoc"," "," ",59953]
["2024-11-25","2024-11-29","SE",1,"42","A+B","RIVAGE","GOUVY","Week","Night","23:30","05:00","Criblage voie U \r\nRenouvellement RTB dans les voies A et B du tunnel de Trois-Ponts\r\nContraintes et finitions","CTL","Minor_AdHoc","Gare de Trois-Pont incluse\r\nCTL entre fin des quais de Trois-Ponts et Vielsalm\r\nART de stabilisation de bk 55223 à 55568 (350m) 3 minutes du 4/11 au 15/11"," ",59438]
["2024-11-25","2024-11-30","SW",2,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement des Tabliers métalliques  + 5chapes \r\nFinitions","CTL","Minor_AdHoc",null," ",55571]
["2024-11-25","2024-12-02","SE",2,"139","A+B","SINT-JORIS-WEERT","WAVRE","Weekend","Continuous","05:00","05:00","ART 2 min\r\nEntretien des PN + maintenance massifiée + Travaux ES","ART","Minor_AdHoc","ART protection et stabilisation:\r\nLongueur: 100 mètres \r\nVitesse réduite: 40 km/h\r\nDate de mise en vigueur: à partir du 23/11 au 02/12 \r\nPerte de temps: \r\nHKV: 2'\r\nHKM: 1,9'","HKM à adapter",59494]
["2024-11-25","2024-12-07","SE",1,"43","A+B","ANGLEUR","TILFF","Week","Night","23:00","05:00","Criblage de Ballast (entre BK 500 et BK 2300)\r\nFinitions\r\nDossier de concertation validé en octobre 2021","CTL","Minor_AdHoc",null," ",49912]
["2024-11-25","2024-12-09","SE",1,"43","A","ANGLEUR","TILFF","AllWeek","Continuous","23:00","05:00","ART 2min\r\nCriblage de Ballast (entre BK 500 et BK 2300)\r\nART de stabilisation\r\nDossier de concertation validé en octobre 2021","ART","Minor_AdHoc","ART 2'"," ",52733]
["2024-11-26","2024-11-29","NE",2,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Week","Night","00:00","04:00","brug Leuvensesteenweg , voorbereiding lift\r\nX blijft open richting L27\r\nMechelen inclusief perrons\r\nL25N open","CTL","Minor_AdHoc","perrons mechelen inclusief BD"," ",58183]
["2024-11-26","2024-11-29","NW",2,"53","B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels + Vernieuwen rails \r\n\r\nDOES wegens geen CBP - FDR SP IV tem IX mee buiten dienst, bundel toegankelijk kan FM, CDS 108 mee BD","SAVU","Minor_AdHoc",null,null,58584]
["2024-11-26","2024-11-30","NW",2,"50","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Week","Night","00:30","04:30","Linked to coupure nr 59240 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to Y.MEULEWIJK: Masterplan Gent Sint Pieters\r\nTLO L50A FGSP - Meulewijk\r\nDOES L50 SP A Y West - FGSP\r\nPerronsporen XII tem VII\r\n\r\n(alternatief stappenplan)","CTL","Minor_AdHoc"," "," ",59240]
["2024-11-26","2024-11-30","NW",2,"50A","A+B","GENT-SINT-PIETERS","Y.MEULEWIJK","Week","Night","00:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50A FGSP - Meulewijk\r\nDOES L50 SP A Y West - FGSP\r\nPerronsporen XII tem VII\r\n\r\n(alternatief stappenplan)","CTL","Minor_AdHoc"," "," ",59240]
["2024-11-26","2024-11-30","NW",2,"50E","A","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","00:30","04:30","Linked to coupure nr 59240 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to Y.MEULEWIJK: Masterplan Gent Sint Pieters\r\nTLO L50A FGSP - Meulewijk\r\nDOES L50 SP A Y West - FGSP\r\nPerronsporen XII tem VII\r\n\r\n(alternatief stappenplan)","SAVU","Minor_AdHoc"," "," ",59240]
["2024-11-26","2024-11-30","NW",3,"51B","A","Y.PELIKAAN","KNOKKE","Week","Night","00:30","04:30","Fietstunnel sportcentra Heist KP 112.000-112.100","CTL","Minor_AdHoc"," "," ",58554]
["2024-11-29","2024-12-02","NE",1,"12","A+B","Y.SINT-MARIABURG","Y.LUCHTBAL","Weekend","Continuous","23:30","04:00","oude landen 301","CTL","Medium","geen verkeer L12 tussen Antwerpen luchtbal en Kapellen"," ",58055]
["2024-11-29","2024-12-02","NE",2,"12","A+B","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Weekend","Continuous","23:30","04:00","onderhoud wissels Antwerpen-centraal\r\n\r\nvolledig verdiep +1 (perronsporen 1-6)\r\n\r\nsamen met werkaanvraag L59/1","CTL","Medium"," "," ",60083]
["2024-11-29","2024-12-02","NE",2,"59/1","A+B","ANTWERPEN-CENTRAAL","Y.NOORD BERCHEM","Weekend","Continuous","23:30","04:00","onderhoud wissels Antwerpen-centraal\r\n\r\nvolledig verdiep +1 (perronsporen 1-6)\r\n\r\nsamen met werkaanvraag L12","CTL","Medium"," "," ",60082]
["2024-11-29","2024-12-02","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59925]
["2024-11-29","2024-12-02","SE",1,"161","B","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:45","WE SAVU RER Bakenbos-Ottignies","SAVU_CTRL","Minor_AdHoc","ART à définir, maximum 2'"," ",49252]
["2024-11-29","2024-12-02","SE",1,"166","A","BEAURAING","VONECHE","AllWeek","Continuous","23:00","05:00","Renouvellement ballast par train C75 (phase 3 : révision VB).","SAVU","Minor_AdHoc",null,"restriction capacité importante -> Partie HKM dévies via ANE",47814]
["2024-11-29","2024-12-02","SE",3,"39","S","WELKENRAEDT","MONTZEN-GRIL Q","Weekend","Continuous","23:00","06:00","Entretien de PN","CTL","Medium","CTL entre Welkenraedt (talon AW 04AK non engagé) et Montzen (talon AW 07K non engagé)"," ",56274]
["2024-11-29","2024-12-02","SE",3,"154","A/B","YVOIR","Y.NEFFE","Weekend","Continuous","23:00","04:30","Entretien AS traitement zone boueuse","SAVU_CTRL","Minor_AdHoc","SAVU EN CONTINU AVEC LES CTL/NUIT CLASSIQUE sam/dim et dim/lun\r\nART  en voies A et B. V 40 km/h. HKV : 2 minutes / HKM : 2 minutes du 02/12 au 05/12 (fin probable)"," ",57695]
["2024-11-30","2024-12-01","NE",2,"52","A","PUURS","Y.ANTWERPEN-ZUID","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59108]
["2024-11-30","2024-12-01","NE",2,"59","A","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM","Weekend","Continuous","06:00","22:00","werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)","SAVU","Minor_AdHoc",null," ",59107]
["2024-11-30","2024-12-01","SW",1,"130","A+B","AUVELAIS","CHATELET-GRIL OUEST","Weekend","Continuous","06:00","17:00","Maintenance Z15.51\r\nP4+","CTL","Medium"," ","HKM à adapter",48832]
["2024-11-30","2024-12-01","SW",2,"90","B","LESSINES","GERAARDSBERGEN","Weekend","Continuous","07:00","18:00","Remplacement des CV50Hz par CV Jade","SAVU","Minor_AdHoc","Coupure des signaux M-F.37 à PX-M.2"," ",56836]
["2024-11-30","2024-12-01","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Weekend","Continuous","06:00","17:00","Maintenance Z6.53 en P4","CTL","Medium"," ","HKM à adapter",55976]
["2024-11-30","2024-12-02","CE",2,"161/1","S","Y.PONT-DE-LA-SENNE","Y.JOSAPHAT","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58407 on line 50 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.BOCKSTAEL: Onderhoudszone FBN_12/FSR_06 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling van L50 tussen FBN Rooster F (E/EX-F8) en Y Bockstael (niet inbe","CTL","Medium"," ","Omleiden via L26",58407]
["2024-11-30","2024-12-02","CE",2,"26B","A+B","Y.PONT-DE-LA-SENNE","SCHAERBEEK","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58407 on line 50 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.BOCKSTAEL: Onderhoudszone FBN_12/FSR_06 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling van L50 tussen FBN Rooster F (E/EX-F8) en Y Bockstael (niet inbe","CTL","Medium"," ","Omleiden via L26",58407]
["2024-11-30","2024-12-02","CE",2,"28(1)","A+B","Y.LAEKEN","Y.PANNENHUIS","Weekend","Continuous","00:20","04:00","Linked to coupure nr 58407 on line 50 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.BOCKSTAEL: Onderhoudszone FBN_12/FSR_06 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling van L50 tussen FBN Rooster F (E/EX-F8) en Y Bockstael (niet inbe","CTL","Medium"," ","Omleiden via L26",58407]
["2024-11-30","2024-12-02","CE",2,"50","A+B","BRUXELLES-NORD-GRIL F","Y.BOCKSTAEL","Weekend","Continuous","00:20","04:00","Onderhoudszone FBN_12/FSR_06 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling van L50 tussen FBN Rooster F (E/EX-F8) en Y Bockstael (niet inbegrepen)\r\nBijkomend aftakkingen van L28(1) tussen Y Laken en Y Pannenhuis (niet inbegrepen) en v","CTL","Medium","Alle goederenverkeer langs L26","Omleiden via L26",58407]
["2024-11-30","2024-12-02","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58044]
["2024-11-30","2024-12-02","NE",2,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Weekend","Continuous","00:00","04:00","brug Leuvensesteenweg , voorbereiding lift\r\nX blijft open richting L27\r\nMechelen inclusief perrons\r\nL25N open","CTL","Medium","perrons mechelen inclusief BD\r\nalternatief E3323-E2644-E1794"," ",58180]
["2024-11-30","2024-12-02","NE",2,"53","A+B","HAMBOS","Y.DIJLEBRUG","Weekend","Continuous","00:00","04:00","railvernieuwing spoor A (nodig wegens veel railfouten)\r\n+\r\nherelectrificatie (bijkomend) colt 60292","CTL","Medium","alternatief E2645-E2644"," ",58349]
["2024-11-30","2024-12-02","NW",2,"204","A+B","GENT-RODENHUIZE","GENT-NOORD","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 05 Schuitstraat; ovonde boven het spoor","CTL","Medium",null,"Info Racc.",58501]
["2024-11-30","2024-12-02","NW",2,"204","A+B","GENT-ZEEHAVEN-SIFFERDOK","GENT-RODENHUIZE","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 07bis Piratenstraat; brug intern havenverkeer en fietsbrug","CTL","Medium",null,"Info Racc.",58495]
["2024-11-30","2024-12-02","NW",2,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58789 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",58789]
["2024-11-30","2024-12-02","NW",2,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)","CTL","Medium"," "," ",58789]
["2024-11-30","2024-12-02","NW",2,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58789 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten ","SAVU","Minor_AdHoc"," "," ",58789]
["2024-11-30","2024-12-02","NW",2,"89","A+B","DENDERLEEUW","ZOTTEGEM","Weekend","Continuous","00:10","04:50","Onderhoud Denderleeuw-Zottegem","CTL","Medium",null," ",60869]
["2024-12-01","2024-12-01","CE",2,"25","A+B","SCHAERBEEK","VILVOORDE","Weekend","Night","01:20","04:30","Linked to coupure nr 58625 on line 36N tracks(s) A+B from Y.PONT ALBERT to Y.DIEGEM: Indienststelling zone N FSR: upgrade SI","CTL","Minor_AdHoc"," ","HKM om te leiden.",58625]
["2024-12-01","2024-12-01","CE",2,"27","A+B","SCHAERBEEK","Y.HAREN-NORD","Weekend","Night","01:20","04:30","Linked to coupure nr 58625 on line 36N tracks(s) A+B from Y.PONT ALBERT to Y.DIEGEM: Indienststelling zone N FSR: upgrade SI","CTL","Minor_AdHoc"," ","HKM om te leiden.",58625]
["2024-12-01","2024-12-01","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","06:00","17:40","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58668]
["2024-12-01","2024-12-01","NE",3,"34","A+B","HASSELT","TONGEREN","Weekend","Night","00:30","05:00","afschaffen 7 overwegen Bilzen\r\n\r\n\r\nwerken tijdens het voorziene werkvenster","CTL","Minor_AdHoc"," "," ",60009]
["2024-12-02","2024-12-06","NE",2,"12","A+B","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL","Week","Night","22:45","04:45","onderhoud wissels en sporen te ANtwerpen Schijnpoort inrit bundel F inclusief bundelkoppen F, D","CTL","Minor_AdHoc","geen toegang tot bundel F \r\ngeen toegang bundel D kant Y luchtbal"," ",60216]
["2024-12-02","2024-12-06","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","23:50","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2+3"," ",58151]
["2024-12-02","2024-12-06","NE",2,"53","A+B","HAMBOS","Y.DIJLEBRUG","Week","Night","23:30","04:00","railvernieuwing (nodig wegens veel railfouten)","CTL","Minor_AdHoc"," "," ",58350]
["2024-12-02","2024-12-06","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59892]
["2024-12-02","2024-12-06","SW",1,"94","A+B","Y.SILLY","ATH","Week","Night","23:30","05:00","Silly - Ath : Renouvellement de traverses\r\nTravaux de finition","CTL","Minor_AdHoc","3 semaines CTL de nuit"," ",48769]
["2024-12-03","2024-12-06","NE",2,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Week","Night","00:00","04:50","brug Leuvensesteenweg , voorbereiding lift\r\nX blijft open richting L27\r\nMechelen inclusief perrons\r\nL25N open","CTL","Minor_AdHoc","perrons mechelen inclusief BD"," ",58184]
["2024-12-03","2024-12-06","NW",2,"204","A+B","GENT-RODENHUIZE","GENT-NOORD","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 05 Schuitstraat; ovonde boven het spoor\r\n\r\n* R5/R6 in weekend TLO","CTL","Medium",null,"Info Racc.",58504]
["2024-12-03","2024-12-06","NW",3,"204","A+B","GENT-ZEEHAVEN-SIFFERDOK","GENT-RODENHUIZE","Week","Night","00:10","04:00","227331 R4WO knooppunt 07bis Piratenstraat; brug intern havenverkeer en fietsbrug\r\n\r\n* R5/R6 in weekend TLO","CTL","Minor_AdHoc",null,"Info Racc.",58499]
["2024-12-03","2024-12-07","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst","CTL","Minor_AdHoc",null,null,58585]
["2024-12-05","2024-12-05","SW",3,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Day","09:30","15:50","Maintenance Z.6.53\r\nMise HS en P2","CTL","Minor_AdHoc"," ","HKM à adapter",55953]
["2024-12-06","2024-12-09","NE",1,"12","A+B","Y.SINT-MARIABURG","Y.LUCHTBAL","Weekend","Continuous","23:55","04:00","oude landen 301","CTL","Medium","geen verkeer tussen Antwerpen luchtbal en Kapellen"," ",58056]
["2024-12-06","2024-12-09","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59926]
["2024-12-06","2024-12-09","NW",2,"217","S","Y.NOORD EVERSTEIN","EVERGEM-OVERDAM","Weekend","Continuous","23:50","05:00","227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Medium"," ","Info Racc",58523]
["2024-12-06","2024-12-09","NW",2,"55A","S","Y.RINGVAART","LANGERBRUGGE","Weekend","Continuous","23:50","05:00","Linked to coupure nr 58523 on line 217 tracks(s) S from Y.NOORD EVERSTEIN to EVERGEM-OVERDAM: 227331: R4WO W9 Zeeschipstraat - Evergemsestwg\r\nringvaartbruggen - vernieuwde tunnel","CTL","Medium"," ","Info Racc",58523]
["2024-12-06","2024-12-09","SE",1,"166","A","BEAURAING","VONECHE","AllWeek","Continuous","23:00","05:00","Renouvellement ballast par train C75 (phase 4 : révision VA).","SAVU","Minor_AdHoc","Athus-Meuse = pas de CTL -> travail en journée avec ART de protection.\r\nART de protection à 40.","restriction capacité importante -> Partie HKM dévies via ANE",47815]
["2024-12-06","2024-12-09","SE",3,"42","A+B","TROIS-PONTS","VIELSALM","Weekend","Continuous","23:50","05:00","Entretien manuel et mécanisés des PN","CTL","Medium","La limite de MHS du côté Vielsalm sera un SMA au droit du signal OX-V.45 (BK 66.153) pour traiter le PN 11 à la BK 65.580"," ",55082]
["2024-12-06","2024-12-09","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 min","HKM à adapter",48636]
["2024-12-06","2024-12-09","SW",1,"94","A+B","Y.SILLY","ATH","Weekend","Continuous","23:30","05:00","Silly - Ath : Renouvellement de traverses\r\nTravaux de finition","CTL","Medium","1 weekend CTL (7-8/12)"," ",59337]
["2024-12-07","2024-12-07","SE",3,"130","A/B","FLAWINNE","MOUSTIER","Weekend","Day","08:00","16:00","Visite de voies A et B + maintenance infrastructure + contrôles","SAVU","Minor_AdHoc","SAVU alternatif 8h/16h"," ",49177]
["2024-12-07","2024-12-08","NW",3,"204","A+B","GENT-NOORD","LIJN 204-KRUISING LIJN 58/2","Weekend","Continuous","22:00","14:00","Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium",null,"Info Racc",60428]
["2024-12-07","2024-12-08","NW",3,"204/1","A+B","GENT-ZEEHAVEN","Y.FARMANSTRAAT","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60428 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60428]
["2024-12-07","2024-12-08","NW",3,"58/2","A+B","GENT-ZEEHAVEN","Y.MUIDE","Weekend","Continuous","22:00","14:00","Linked to coupure nr 60428 on line 204 tracks(s) A+B from GENT-NOORD to LIJN 204-KRUISING LIJN 58/2: Reservatie onderhoud\r\nVan Gent-Zeehaven BT 18BF & BT 20F tot Gent-Noord uitritseinen bundel Kennedy","CTL","Medium"," ","Info Racc",60428]
["2024-12-07","2024-12-08","SE",2,"130","A+B","NAMUR","AUVELAIS","Weekend","Continuous","23:40","14:50","Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+ électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu VA + VB départ L144","CTL","Medium",null," ",50429]
["2024-12-07","2024-12-08","SE",2,"130/1","A","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Weekend","Continuous","23:40","14:50","Linked to coupure nr 50429 on line 130 tracks(s) A+B from NAMUR to AUVELAIS: Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+ électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu VA + VB départ L144","CTL","Medium"," "," ",50429]
["2024-12-07","2024-12-08","SE",2,"144","A","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Weekend","Continuous","23:40","14:50","Linked to coupure nr 50429 on line 130 tracks(s) A+B from NAMUR to AUVELAIS: Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+ électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu VA + VB départ L144","CTL","Medium"," "," ",50429]
["2024-12-07","2024-12-08","SW",2,"130","A+B","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Weekend","Continuous","23:40","14:50","Maintenance Z19. 51\r\nMini CTL","CTL","Medium"," "," ",49168]
["2024-12-07","2024-12-08","SW",3,"116","A+B","MANAGE","LA LOUVIERE-GARE INDUSTRIELLE","Weekend","Continuous","06:00","22:00","Maintenance Z10.52\r\nMise HS P4 - Zone 10 AI52","CTL","Medium"," ","InfoRacc",49153]
["2024-12-07","2024-12-08","SW",3,"116/1","A+B","Y.BOIS-D'HAINE","Y.FAMILLEUREUX","Weekend","Continuous","06:00","22:00","Linked to coupure nr 49153 on line 116 tracks(s) A+B from MANAGE to LA LOUVIERE-GARE INDUSTRIELLE: Maintenance Z10.52\r\nMise HS P4 - Zone 10 AI52","CTL","Medium"," ","InfoRacc",49153]
["2024-12-07","2024-12-09","NE",2,"11","A+B","Y.STABROEK","ANTWERPEN-D.S.-BASF","Weekend","Continuous","00:00","04:00","aanleg 2de spoor (7,5km)","CTL","Medium"," "," ",58045]
["2024-12-07","2024-12-09","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Medium","geen verkeer sporen 1+2+3"," ",58154]
["2024-12-07","2024-12-09","NE",2,"53","A+B","HAMBOS","Y.DIJLEBRUG","Weekend","Continuous","00:00","04:00","railvernieuwing (nodig wegens veel railfouten)","CTL","Medium"," "," ",58351]
["2024-12-07","2024-12-09","NW",2,"204","A+B","GENT-RODENHUIZE","GENT-NOORD","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 05 Schuitstraat; ovonde boven het spoor","CTL","Medium",null,"Info Racc.",58502]
["2024-12-07","2024-12-09","NW",2,"204","A+B","GENT-ZEEHAVEN-SIFFERDOK","GENT-RODENHUIZE","Weekend","Continuous","00:10","04:00","227331 R4WO knooppunt 07bis Piratenstraat; brug intern havenverkeer en fietsbrug","CTL","Medium",null,"Info Racc.",58496]
["2024-12-07","2024-12-09","NW",2,"50","A","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:30","04:30","Linked to coupure nr 58790 on line 50A tracks(s) A+B from GENT-SINT-PIETERS to Y.MEULEWIJK: Masterplan Gent Sint Pieters\r\nTLO L50A FGSP - Meulewijk\r\nDOES L50 SP A Y West - FGSP\r\nPerronsporen XII tem VII\r\n\r\n(alternatief stappenplan)","SAVU","Minor_AdHoc"," "," ",58790]
["2024-12-07","2024-12-09","NW",2,"50A","A+B","GENT-SINT-PIETERS","Y.MEULEWIJK","Weekend","Continuous","00:30","04:30","Masterplan Gent Sint Pieters\r\nTLO L50A FGSP - Meulewijk\r\nDOES L50 SP A Y West - FGSP\r\nPerronsporen XII tem VII\r\n\r\n(alternatief stappenplan)","CTL","Medium"," "," ",58790]
["2024-12-07","2024-12-09","NW",2,"53","A+B","DENDERMONDE","LONDERZEEL","Weekend","Continuous","00:20","04:30","Indienstname PLP\r\nL53 Dendermonde-Londerzeel\r\nStations beide beschikbaar\r\nTestritten op zondag tot op de perrons van Dendermonde en Londerzeel in overleg met de regelaar\r\n+\r\nIDS - ETCS \r\nETCS_IL-SMI_NW_L53 FDR-FZL","CTL","Medium"," "," ",57577]
["2024-12-08","2024-12-08","NE",1,"12/1","A+B","Y.DRIEHOEKSTRAAT","Y.SINT-MARIABURG","Weekend","Day","06:00","17:40","Linked to coupure nr 58669 on line 27A tracks(s) A+B from Y.DRIEHOEKSTRAAT to ANTWERPEN-LUCHTBAL: 304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58669]
["2024-12-08","2024-12-08","NE",1,"27A","A+B","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL","Weekend","Day","06:00","17:40","304 statiestraat , tussen Y laarsebeek en Y driehoekstraat","CTL","Minor_AdHoc"," "," ",58669]
["2024-12-08","2024-12-08","NW",3,"202B","S","Y.EIVOORDE","ZEEBRUGGE-BUNDEL RAMSKAPELLE","Weekend","Day","10:00","18:00","R-419005-01\r\n\r\nonderhoud werkveld 3421-36\r\n\r\nAW 72R-73R-74R-74XR-75R-80R-82R-83R\r\n\r\nBundel Ramskapelle niet bereikbaar","Autre","Minor_AdHoc"," ","Info Racc.",60371]
["2024-12-09","2024-12-13","NE",2,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Week","Night","23:50","04:00","brug Leuvensesteenweg , voorbereiding lift\r\nX blijft open richting L27\r\nMechelen inclusief perrons\r\nL25N open","CTL","Minor_AdHoc","perrons mechelen inclusief BD\r\nalternatief E3123-E2644"," ",58185]
["2024-12-09","2024-12-13","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Week","Night","00:00","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Minor_AdHoc","geen verkeer sporen 1+2+3"," ",58152]
["2024-12-09","2024-12-13","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Week","Night","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Minor_AdHoc","alternatief Z4321-Z4322-Z4324"," ",59893]
["2024-12-09","2024-12-14","SW",1,"94","A+B","Y.SILLY","ATH","Week","Night","23:30","05:00","Silly - Ath : Renouvellement de traverses\r\nTravaux de finition","CTL","Minor_AdHoc","3 semaines CTL de nuit"," ",59347]
["2024-12-10","2024-12-14","NW",2,"53","A+B","SCHELLEBELLE","DENDERMONDE","Week","Night","00:10","04:45","Vernieuwen wissels 01AD,01BD,02BD,02AD,03AD,03BD,04AD,04BD + Vernieuwen rails KP 9 553 - Kp 11 605\r\nPerron I-II-III-IV buiten dienst\r\nCDS 108 buiten dienst","CTL","Minor_AdHoc",null,null,59192]
["2024-12-11","2024-12-11","NE",2,"12","A","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn","SAVU","Minor_AdHoc","L12 spoor A +perronsporen 4-5-6"," ",60099]
["2024-12-12","2024-12-12","NE",2,"27","A+B","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL","Week","Day","09:30","15:00","onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12-13-14 buiten dienst","CTL","Minor_AdHoc"," "," ",60118]
["2024-12-13","2024-12-16","NE",2,"25","A+B","VILVOORDE","VILVOORDE","Weekend","Continuous","23:55","04:00","sporen 1+2 (+3) \r\nafbraak trapkooien perrons 1-2-3 Vilvoorde\r\n\r\n==>sporen 1+2+3 buiten dienst","CTL","Medium","geen verkeer sporen 1+2+3"," ",58155]
["2024-12-13","2024-12-16","NE",3,"19","A+B","BALEN-WERKPLAATSEN","NEERPELT","Weekend","Continuous","22:00","05:00","aanleg tweede spoor tussen Balen en werkplaatsen Neerpelt","CTL","Medium","alternatief Z4321-Z4322-Z4324"," ",59927]
["2024-12-13","2025-01-20","SE",1,"162","B","CINEY","HAVERSIN","AllWeek","Continuous","22:50","05:00","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 13\r\nciney-haversin\r\nTravaux effectués = Travaux caténaires et GC linéaire + début des travaux de quai à Leignon et Chapois","SAVU_CTRL","High","CTL de Nuit : Lu^Ma à Je^Ve :00:10–04:50, Ve^Sa 00:10–06:30, Sa^Di 23:10–06:30, Di^Lu 23:10–04:50\r\nAS 34BK parcourable\r\nSAVU prolongé jusqu'en mai suite arbitrage budgétaire"," ",62769]
["2024-12-13","2025-01-20","SE",1,"162","B","CINEY","HAVERSIN","AllWeek","Continuous","22:50","05:00","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 13\r\nciney-haversin\r\nTravaux effectués = Travaux caténaires et GC linéaire + début des travaux de quai à Leignon et Chapois","SAVU_CTRL","High","CTL de Nuit : Lu^Ma à Je^Ve :00:10–04:50, Ve^Sa 00:10–06:30, Sa^Di 23:10–06:30, Di^Lu 23:10–04:50\r\nAS 34BK parcourable\r\nSAVU prolongé jusqu'en mai suite arbitrage budgétaire"," ",62769]
["2024-12-14","2024-12-15","NE",3,"10","A+B","Y.ZWIJNDRECHT-FORT","Y.WALENHOEK","Weekend","Continuous","22:00","14:00","Onderhoudswerken aan wissels, puntstukken, seinen, sk's,;;;;","CTL","Medium"," "," ",61590]
["2024-12-14","2024-12-15","NE",3,"10","A+B","Y.HAZOP","Y.WALENHOEK","Weekend","Night","22:00","06:00","onderhoud antigoontunnel (contractueel vastgelegd)","CTL","Minor_AdHoc"," "," ",59422]
["2024-12-14","2024-12-15","SE",2,"24","A+B","VISE-HAUT","MONTZEN-FRONTIERE","Weekend","Continuous","08:00","21:00","Entretien manuel et mécanisés des AW de Y. Berneau, Fourons, Rémersdael, Montzen, Botzelaer\r\nEntretien manuel et mécanisés de la voie courante + Tunnel de Veurs","CTL","Medium","Pas de circulation possible entre Visé et DB\r\nPas de ciculation entre Longchamps vers DB"," ",55968]
["2024-12-14","2024-12-15","SE",2,"24/1","A+B","Y.LONGCHAMPS","Y.BERNEAU","Weekend","Continuous","08:00","21:00","Linked to coupure nr 55968 on line 24 tracks(s) A+B from VISE-HAUT to MONTZEN-FRONTIERE: Entretien manuel et mécanisés des AW de Y. Berneau, Fourons, Rémersdael, Montzen, Botzelaer\r\nEntretien manuel et mécanisés de la voie courante + Tunnel de Veurs","CTL","Medium"," "," ",55968]
["2024-12-14","2024-12-16","NE",1,"12","A+B","ESSEN","ESSEN-GRENS","Weekend","Continuous","00:01","04:00","travaux ProRail","CTL","Medium","geen verkeer","Via L24/34/35",63069]
["2024-12-14","2024-12-16","NE",2,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Weekend","Continuous","00:00","04:00","brug Leuvensesteenweg , voorbereiding lift\r\nX blijft open richting L27\r\nMechelen inclusief perrons\r\nL25N open","CTL","Medium","perrons mechelen inclusief BD\r\nalternatief E3323-E2644-E1794"," ",58181]
["2024-12-14","2024-12-16","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","migratie tunnelveiligheidtechnieken Antw NZ\r\nantwerpen centraal -antwerpen luchtbal","CTL","Medium"," "," ",59343]
["2024-12-14","2024-12-16","NE",2,"25","A+B","Y.NOORD BERCHEM","Y.LUCHTBAL","Weekend","Continuous","06:00","04:00","onderhoud SIG + onderhoud wissels Arendstraat  en Antwerpen centraal -2\r\n\r\nbeveiliging L27 s nachts door buitendienststelling overdag ATW-TX\r\n\r\nnog te bekijken","CTL","Medium"," "," ",59709]
["2024-12-14","2024-12-16","NE",3,"27","A+B","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL","Weekend","Night","00:40","04:20","onderhoud SIG + wissels Y arendstraat\r\n\r\nbeveiliging werken L25","CTL","Minor_AdHoc","nog te bepalen"," ",59730]
["2024-12-14","2024-12-16","NE",1,"12","A+B","ESSEN","ESSEN-GRENS","Weekend","Continuous","00:01","04:00","travaux ProRail","CTL","Medium","geen verkeer","Via L24/34/35",63069]
["2024-12-16","2024-12-21","SW",1,"94","A+B","Y.SILLY","ATH","Week","Night","23:30","05:00","Silly - Ath : Renouvellement de traverses\r\nTravaux de finition","CTL","Minor_AdHoc","3 semaines CTL de nuit"," ",59348]
["2024-12-16","2025-12-12","SW",1,"124","*","BAULERS-GRIL D","NIVELLES","AllWeek","Continuous","06:00","18:00","RER renouvellement voies + quai en voie 3 (ou voie 4 en fonction de l'avancement du chantier)","Autre","Minor_AdHoc","MHS et quai de la voie 3 (ou voie 4)"," ",54492]
["2024-12-16","2025-12-13","CE",1,"96B","A","BRUXELLES-MIDI","BRUXELLES-MIDI","AllWeek","Continuous","00:05","23:55","FBMZ Sp 15+16: Perronvernieuwing - Overkapping - Lot Q","CTL","Major","Perronsporen 15+16 continu BDS."," ",39794]
["2024-12-16","2025-12-20","SE",1,"161","A/B","GEMBLOUX","RHISNES","AllWeek","Night","06:00","22:00","Modernisation Axe 3","SAVU_CTRL","Minor_AdHoc","SAVU Nuits 7h amplitude\r\nCTL Nuits 5h amplitude"," ",53859]
["2024-12-16","2025-12-20","SE",1,"161","A/B","RHISNES","NAMUR","AllWeek","Continuous","06:00","22:00","Modernisation Axe 3","SAVU_CTRL","High","Alternance de simple et double cas +  alternance VA/VB sur le tronçon en SAVU de jour\r\n+ CTL nuits prolongée\r\nART à déterminer"," ",19215]
["2024-12-20","2025-01-20","SE",1,"162","B","GRUPONT","HATRIVAL","AllWeek","Continuous","22:00","05:00","Grupont - Hatrival : phase 12 = ART de stabilisation (post criblage)\r\nSAVU","SAVU_CTRL","High","SAVU VB HS suite ART contraignant 7min"," ",19763]
["2025-01-01","2025-04-27","NW",1,"53","A+B","DENDERMONDE","DENDERMONDE","AllWeek","Continuous","00:00","00:00","Masterplan Dendermonde \r\nVernieuwen perron","Autre","Minor_AdHoc"," "," ",59380]
["2025-01-01","2025-04-28","NW",1,"53","A+B","DENDERMONDE","DENDERMONDE","AllWeek","Continuous","00:00","04:00","Perronspoor 4 en 5 buiten dienst te Dendermonde","Autre","Minor_AdHoc"," "," ",58626]
["2025-01-01","2025-12-31","NE",1,"211C","S","Y.KROMMENHOEK","Y.ARENBERG","AllWeek","Continuous","00:05","23:55","Project Havenbedrijf: \r\nECA - Westelijke Ontsluiting (extra containercapaciteit Antwerpen).","CTL","Major","Aansluiting Rubis-Zuid bereikbaar."," ",57825]
["2025-01-01","2025-12-31","NW",1,"50L/1","A+B","MERELBEKE-ROOSTER S","Y.OOST DRIEHOEK LEDEBERG","AllWeek","Continuous","00:00","23:55","Merelbeke Bundel Centraal sporen 5 tot en met 9 buiten dienst voor heraanleg\r\n\r\nSporen 1 tot en met 4  in dienst maar buiten spanning.\r\n\r\nGeen invloed op de lijn 50E ( zo ingevoerd in colt voor de zichtbaarheid)","Autre","Minor_AdHoc"," "," ",59257]
["2025-01-01","2025-12-31","NW",1,"50L/1","S","Y.OOST DRIEHOEK LEDEBERG","MERELBEKE-ROOSTER S","AllWeek","Continuous","00:00","23:55","Linked to coupure nr 59257 on line 50L/1 tracks(s) A+B from MERELBEKE-ROOSTER S to Y.OOST DRIEHOEK LEDEBERG: Merelbeke Bundel Centraal sporen 5 tot en met 9 buiten dienst voor heraanleg\r\n\r\nSporen 1 tot en met 4  in dienst maar buiten spanning.\r\n\r\nGeen i","Autre","Minor_AdHoc"," "," ",59257]
["2025-01-01","2025-12-31","SE",1,"139L/2","A+B","Y.OTTIGNIES-RELAIS","OTTIGNIES","AllWeek","Continuous","00:01","23:55","Travaux RER","CTL","Major","voies 6 et 7 à quai HS en continu\r\nvoies 143 et 144 du faisceau relais HS. Passage L161 --> L139 Ok via voie 142 en service\r\nSuppression du faisceau Entretien et impact probable sur faisceau manage\r\nMise HS de nuit en gare"," ",58404]
["2025-01-04","2025-01-05","SW",1,"90C","A+B","JURBISE","BRUGELETTE","Weekend","Continuous","06:00","17:00","Maintenance Z.7.53 P4","CTL","Medium",null," ",56573]
["2025-01-06","2025-01-10","CE",1,"96","A+B","Y.RUISBROEK","Y.NOORD HALLE","Week","Night","23:40","04:30","Vernieuwen BVL L96+L96E zone A4-B4-A5-B5: voorbereiding","CTL","Minor_AdHoc","TLO L96 + L96E",null,59691]
["2025-01-06","2025-01-10","CE",1,"96E","S","Y.NOORD HALLE","LOT","Week","Night","23:40","04:30","Linked to coupure nr 59691 on line 96 tracks(s) A+B from Y.RUISBROEK to Y.NOORD HALLE: Vernieuwen BVL L96+L96E zone A4-B4-A5-B5: voorbereiding","CTL","Minor_AdHoc"," ",null,59691]
["2025-01-06","2025-01-20","NE",1,"52","A/B","Y.ANTWERPEN-ZUID","HOBOKEN-POLDER","AllWeek","Continuous","06:00","05:00","Stationsproject Antwerpen-Zuid voor B-Stations:\r\n\r\nBrugdek + bovenleidingswerken boven L52","SAVU","High","DOES L52 periode van 2 weken"," ",60158]
["2025-01-06","2025-02-22","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n1- Réalisation de massifs et pose de poteaux","SAVU","Minor_AdHoc","7 semaines SAVU de nuits en semaine + CTL dans les blancs travaux"," ",56440]
["2025-01-06","2025-05-03","CE",1,"96C","*","BRUXELLES-MIDI","BRUXELLES-MIDI","AllWeek","Continuous","07:00","04:30","Gedurende de ganse periode sporen 502-503-504 buiten dienst voor stockage en premontage wissels, tijdens de aanvoer bijkomend spoor 505 buiten dienst","Autre","Minor_AdHoc","Gedurende de ganse periode sporen 502-503-504 buiten dienst voor stockage en premontage wissel, tijdens de aanvoer bijkomend spoor 505 buiten dienst",null,59744]
["2025-01-06","2025-12-22","SE",1,"162","B","MARLOIE","MARLOIE","AllWeek","Continuous","06:00","06:00","Travaux en gare de Marloie","Autre","Minor_AdHoc","3 quais toujours disponibles en gare de Marloie\r\nPhases ponctuelles + contraignantes suivant phasage à préciser"," ",62779]
["2025-01-10","2025-01-13","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers","Autre","Minor_AdHoc","sp 3 cont BDS"," ",59754]
["2025-01-10","2025-01-13","CE",1,"96","A+B","Y.RUISBROEK","Y.NOORD HALLE","Weekend","Continuous","23:40","04:30","Vernieuwen BVL L96+L96E zone A4-B4-A5-B5","CTL","Medium","TLO L96 + L96E",null,59690]
["2025-01-10","2025-01-13","CE",1,"96E","S","Y.NOORD HALLE","LOT","Weekend","Continuous","23:40","04:30","Linked to coupure nr 59690 on line 96 tracks(s) A+B from Y.RUISBROEK to Y.NOORD HALLE: Vernieuwen BVL L96+L96E zone A4-B4-A5-B5","CTL","Medium"," ",null,59690]
["2025-01-10","2025-01-13","SE",1,"130","A/B","AUVELAIS","MOUSTIER","Weekend","Night","23:00","05:00","Electrification Gare de Jemeppe Sur Sambre\r\nPose portiques Moustier- Auvelais","CTL","Minor_AdHoc",null," ",59468]
["2025-01-11","2025-01-13","CE",1,"26","A+B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","Weekend","Continuous","00:30","04:00","Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 2\r\nTLO-WE voor afbraak brug","CTL","Medium","TLO tussen Trapezium Linkebeek en Y Watermaal"," ",59726]
["2025-01-13","2025-01-17","CE",1,"50C","A","BRUXELLES-MIDI","ANDERLECHT-GRIL EST","Week","Night","23:40","04:30","Vernieuwen aw's 29BJ-35BJ/28AJ: voorbereidende werken\r\nVan de perrons 15-16-17 dwars over rooster FBMZ tot inritseinen AL50C, L96D en BL96. \r\nTijdens de nachten uitbreiding naar bundel Gent","Autre","Minor_AdHoc","Van de perrons 15-16-17 dwars over rooster FBMZ tot inritseinen AL50C, L96D en BL96. \r\nTijdens de nachten uitbreiding naar bundel Gent",null,59703]
["2025-01-13","2025-01-18","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59308 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen ","SAVU","Minor_AdHoc"," "," ",59308]
["2025-01-13","2025-01-18","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe","CTL","Minor_AdHoc"," "," ",59308]
["2025-01-13","2025-01-18","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","GENTBRUGGE-PERRON C.W.","Week","Night","23:30","04:20","Linked to coupure nr 59308 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen ","SAVU","Minor_AdHoc"," "," ",59308]
["2025-01-13","2025-02-03","CE",1,"27F","*","SCHAERBEEK","SCHAERBEEK","AllWeek","Continuous","07:00","04:00","Vernieuwing volledige bundel L","Autre","Minor_AdHoc","FSR bundel L continu BDS"," ",59450]
["2025-01-13","2025-04-18","SW",1,"130","A/B","LE CAMPINAIRE","CHATELET","Week","Night","23:10","05:10","Réélectrification L130","SAVU","Minor_AdHoc","Du Campinaire à Châtelet\r\nSAVU en nuit de semaine voie A du 13/01/2025 au 28/02/2025  (7 semaines)\r\nSAVU en nuit de semaine voie B du 03/03/2025 au 18/04/2025 (7 semaines)"," ",54818]
["2025-01-14","2025-01-17","NE",1,"53","A+B","MECHELEN","MUIZEN","Week","Night","00:01","04:00","Vernieuwing Vierendeelbrug Leuvensesteenweg\r\nVoorbereiding","CTL","Minor_AdHoc","(rooster N L27 beschikbaar)"," ",58399]
["2025-01-14","2025-01-17","NE",1,"53A","A+B","Y.MUIZEN","MECHELEN","Week","Night","00:01","04:00","Linked to coupure nr 58399 on line 53 tracks(s) A+B from MECHELEN to MUIZEN: Vernieuwing Vierendeelbrug Leuvensesteenweg\r\nVoorbereiding","CTL","Minor_AdHoc"," "," ",58399]
["2025-01-17","2025-01-20","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers","Autre","Minor_AdHoc","sp 3 cont BDS"," ",59755]
["2025-01-17","2025-01-20","CE",1,"50C","A","BRUXELLES-MIDI","ANDERLECHT-GRIL EST","Weekend","Continuous","23:40","04:30","Vernieuwen aw's 28BJ-20BJ/29AJ\r\nVan de perrons 15-16-17 dwars over rooster FBMZ tot inritseinen AL50C, L96D en BL96. \r\nTijdens de nachten uitbreiding naar bundel Gent","Autre","Minor_AdHoc","Van de perrons 15-16-17 dwars over rooster FBMZ tot inritseinen AL50C, L96D en BL96. \r\nTijdens de nachten uitbreiding naar bundel Gent",null,59700]
["2025-01-17","2025-01-20","SE",1,"130","A/B","AUVELAIS","MOUSTIER","Weekend","Night","23:00","05:00","Electrification Gare de Jemeppe Sur Sambre\r\nPose portiques Moustier- Auvelais","CTL","Minor_AdHoc",null," ",59470]
["2025-01-17","2025-01-20","SW",1,"78","A+B","BLATON","TOURNAI","Weekend","Continuous","23:30","05:00","Renouvellement AS 15H à l'entrée de la gare de Tournai","CTL","Medium","Voies 1, 2, A et B HS\r\nART stab 2 min"," ",53243]
["2025-01-18","2025-01-19","NW",1,"50","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Night","23:30","04:20","Linked to coupure nr 59312 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen ","CTL","Minor_AdHoc"," "," ",59312]
["2025-01-18","2025-01-19","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Night","23:30","04:20","Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nTLO L 50 tussen Gent Sint Pieters en Y. West Driehoek Le","CTL","Minor_AdHoc"," "," ",59312]
["2025-01-18","2025-01-19","NW",1,"58/1","A+B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Night","23:30","04:20","Linked to coupure nr 59312 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen ","CTL","Minor_AdHoc"," "," ",59312]
["2025-01-18","2025-01-20","CE",1,"26","A+B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","Weekend","Continuous","00:30","04:00","Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 2\r\nTLO-WE voor afbraak brug","CTL","Medium","TLO tussen Trapezium Linkebeek en Y Watermaal"," ",59727]
["2025-01-18","2025-01-20","NE",1,"53","A+B","MECHELEN","MUIZEN","Weekend","Continuous","00:01","04:00","Vernieuwing Vierendeelbrug Leuvensesteenweg\r\nVoorbereiding","CTL","Medium","(rooster N L27 beschikbaar)"," ",58401]
["2025-01-18","2025-01-20","NE",1,"53A","A+B","Y.MUIZEN","MECHELEN","Weekend","Continuous","00:01","04:00","Linked to coupure nr 58401 on line 53 tracks(s) A+B from MECHELEN to MUIZEN: Vernieuwing Vierendeelbrug Leuvensesteenweg\r\nVoorbereiding","CTL","Medium"," "," ",58401]
["2025-01-20","2025-01-24","CE",1,"50C","A","BRUXELLES-MIDI","ANDERLECHT-GRIL EST","Week","Night","23:40","04:30","Vernieuwen aw's 29BJ-35BJ/28AJ: voorbereidende werken\r\nVan de perrons 15-16-17 dwars over rooster FBMZ tot inritseinen AL50C, L96D en BL96. \r\nTijdens de nachten uitbreiding naar bundel Gent","Autre","Minor_AdHoc","Van de perrons 15-16-17 dwars over rooster FBMZ tot inritseinen AL50C, L96D en BL96. \r\nTijdens de nachten uitbreiding naar bundel Gent",null,59704]
["2025-01-20","2025-01-25","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59309 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen ","SAVU","Minor_AdHoc"," "," ",59309]
["2025-01-20","2025-01-25","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe","CTL","Minor_AdHoc"," "," ",59309]
["2025-01-20","2025-01-25","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59309 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen ","SAVU","Minor_AdHoc"," "," ",59309]
["2025-01-20","2025-02-02","SE",1,"162","B","NEUFCHATEAU","LAVAUX","AllWeek","Continuous","07:30","16:00","Renouvellement LRS Longlier-Lavaux\r\nRéunion 12/05/2022 : A placer début 2025 (Attente confirmation Daniel)","SAVU_CTRL","High"," "," ",38358]
["2025-01-20","2025-12-12","SW",1,"96","A/B","LEMBEEK","BRAINE-LE-COMTE","Week","Night","23:10","05:10","Réélectrification L96","SAVU","Minor_AdHoc","SAVU de nuit"," ",54473]
["2025-01-24","2025-01-27","CE",1,"161","A/B","WATERMAEL","BAKENBOS","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59172]
["2025-01-24","2025-01-27","CE",1,"161","A+B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers","CTL","Medium","sp 3 +4 cont BDS"," ",59756]
["2025-01-24","2025-01-27","CE",1,"50C","A","BRUXELLES-MIDI","ANDERLECHT-GRIL EST","Weekend","Continuous","23:40","04:30","Vernieuwen aw's 29BJ-35BJ/28AJ\r\nVan de perrons 15-16-17 dwars over rooster FBMZ tot inritseinen AL50C, L96D en BL96. \r\nTijdens de nachten uitbreiding naar bundel Gent","Autre","Minor_AdHoc","Van de perrons 15-16-17 dwars over rooster FBMZ tot inritseinen AL50C, L96D en BL96. \r\nTijdens de nachten uitbreiding naar bundel Gent",null,59701]
["2025-01-24","2025-01-27","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 minutes"," ",54938]
["2025-01-24","2025-01-27","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Weekend","Continuous","23:00","04:10","Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation","CTL","Medium",null,"HKM à adapter",56545]
["2025-01-24","2025-04-07","SE",1,"130","A/B","AUVELAIS","MOUSTIER","Weekend","Continuous","23:00","05:00","Electrification Gare de Jemeppe Sur Sambre\r\nDéroulage Moustier- Auvelais","SAVU_CTRL","Minor_AdHoc","12 we en continu de SAVU vend 23h au lun 05h + CTL dans les blancs travaux"," ",59469]
["2025-01-25","2025-01-26","NW",1,"50","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Night","23:30","04:20","Linked to coupure nr 59313 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen ","CTL","Minor_AdHoc"," "," ",59313]
["2025-01-25","2025-01-26","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Night","23:30","04:20","Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nTLO L 50 tussen Gent Sint Pieters en Y. West Driehoek Le","CTL","Minor_AdHoc"," "," ",59313]
["2025-01-25","2025-01-26","NW",1,"58/1","A+B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Night","23:30","04:20","Linked to coupure nr 59313 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen ","CTL","Minor_AdHoc"," "," ",59313]
["2025-01-25","2025-01-27","NE",1,"25","A+B","SCHAERBEEK","VILVOORDE","Weekend","Continuous","00:01","04:00","Werken Viaduct Vilvoorde (AWV)","CTL","Medium"," "," ",58703]
["2025-01-27","2025-01-31","CE",1,"124","A+B","BRUXELLES-MIDI","Y.FOREST-EST","Week","Night","23:40","04:30","Linked to coupure nr 59699 on line 96 tracks(s) A+B from BRUXELLES-MIDI to Y.RUISBROEK: Vernieuwen aw 37AJ/46BJ: voorbereidende werken\r\nFBMZ sp 17-18 tot Y Ruisbroek\r\nTijdens de nachten uitbreiding naar L124 en bundel Charleroi","Autre","Minor_AdHoc"," ",null,59699]
["2025-01-27","2025-01-31","CE",1,"96","A+B","BRUXELLES-MIDI","Y.RUISBROEK","Week","Night","23:40","04:30","Vernieuwen aw 37AJ/46BJ: voorbereidende werken\r\nFBMZ sp 17-18 tot Y Ruisbroek\r\nTijdens de nachten uitbreiding naar L124 en bundel Charleroi","CTL","Minor_AdHoc","TLO L96 + bypass + l124 + bundel Charleroi\r\nFBMZ sp 17+18",null,59699]
["2025-01-27","2025-02-01","CE",1,"50C","A","BRUXELLES-MIDI","ANDERLECHT-GRIL EST","Week","Night","23:40","04:30","Vernieuwen aw's 29BJ-35BJ/28AJ: afwerking\r\nVan de perrons 15-16-17 dwars over rooster FBMZ tot inritseinen AL50C, L96D en BL96. \r\nTijdens de nachten uitbreiding naar bundel Gent","Autre","Minor_AdHoc","Van de perrons 15-16-17 dwars over rooster FBMZ tot inritseinen AL50C, L96D en BL96. \r\nTijdens de nachten uitbreiding naar bundel Gent",null,59705]
["2025-01-27","2025-02-01","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59310 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen ","SAVU","Minor_AdHoc"," "," ",59310]
["2025-01-27","2025-02-01","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\n Spoor B L 50 tussen Gent Sint Pieters en Y. West Drieho","CTL","Minor_AdHoc"," "," ",59310]
["2025-01-27","2025-02-01","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59310 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen ","SAVU","Minor_AdHoc"," "," ",59310]
["2025-01-27","2025-02-01","SW",1,"78","A+B","BLATON","TOURNAI","Week","Night","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) + traverses biblocs\r\nTravaux préparatoires (2 semaines)\r\n+ Renouvellement AS 15H à l'entrée de la gare de Tournai\r\nTravaux de finition\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Voies 1, 2, A et B HS\r\nART 2 min"," ",53246]
["2025-01-27","2025-02-01","SW",1,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Night","22:30","05:00","Aménagement de Quévy\r\nTravaux préparatoires - déchargement LRS","CTL","Minor_AdHoc","CTL de nuit"," ",53239]
["2025-01-28","2025-01-31","CE",1,"94","A+B","Y.NOORD HALLE","SAINTES","Week","Night","00:45","04:30","Linked to coupure nr 59689 on line 96 tracks(s) A+B from Y.NOORD HALLE to TUBIZE: Vernieuwen BVL L96 + aw's 96/94 kant Lembeek zone A12-A13","CTL","Minor_AdHoc"," ",null,59689]
["2025-01-28","2025-01-31","CE",1,"96","A+B","Y.NOORD HALLE","TUBIZE","Week","Night","00:45","04:30","Vernieuwen BVL L96 + aw's 96/94 kant Lembeek zone A12-A13","CTL","Minor_AdHoc","TLO L96 + L94\r\nStation Halle afgesloten",null,59689]
["2025-01-28","2025-01-31","NE",1,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Week","Night","00:01","04:00","Linked to coupure nr 58400 on line 53 tracks(s) A+B from MECHELEN to MUIZEN: Vernieuwing Vierendeelbrug Leuvensesteenweg\r\nVoorbereiding","CTL","Minor_AdHoc"," "," ",58400]
["2025-01-28","2025-01-31","NE",1,"53","A+B","MECHELEN","MUIZEN","Week","Night","00:01","04:00","Vernieuwing Vierendeelbrug Leuvensesteenweg\r\nVoorbereiding","CTL","Minor_AdHoc"," "," ",58400]
["2025-01-28","2025-01-31","NE",1,"53A","A+B","Y.MUIZEN","MECHELEN","Week","Night","00:01","04:00","Linked to coupure nr 58400 on line 53 tracks(s) A+B from MECHELEN to MUIZEN: Vernieuwing Vierendeelbrug Leuvensesteenweg\r\nVoorbereiding","CTL","Minor_AdHoc"," "," ",58400]
["2025-01-31","2025-02-03","CE",1,"124","A+B","BRUXELLES-MIDI","Y.FOREST-EST","Weekend","Continuous","23:40","04:30","Linked to coupure nr 59697 on line 96 tracks(s) A+B from BRUXELLES-MIDI to Y.RUISBROEK: Vernieuwen aw 37AJ/46BJ\r\nFBMZ sp 17-18 tot Y Ruisbroek\r\nTijdens de nachten uitbreiding naar L124 en bundel Charleroi","Autre","Minor_AdHoc"," ",null,59697]
["2025-01-31","2025-02-03","CE",1,"161","A+B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers","CTL","Medium","sp 3 +4 cont BDS"," ",59757]
["2025-01-31","2025-02-03","CE",1,"96","A+B","BRUXELLES-MIDI","Y.RUISBROEK","Weekend","Continuous","23:40","04:30","Vernieuwen aw 37AJ/46BJ\r\nFBMZ sp 17-18 tot Y Ruisbroek\r\nTijdens de nachten uitbreiding naar L124 en bundel Charleroi","CTL","Medium","TLO L96 + bypass\r\nFBMZ sp 17+18 in cds",null,59697]
["2025-02-01","2025-02-02","NW",1,"50","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Night","23:30","04:20","Linked to coupure nr 59314 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen ","CTL","Minor_AdHoc"," "," ",59314]
["2025-02-01","2025-02-02","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Night","23:30","04:20","Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nTLO L 50 tussen Gent Sint Pieters en Y. West Driehoek Le","CTL","Minor_AdHoc"," "," ",59314]
["2025-02-01","2025-02-02","NW",1,"58/1","A+B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Night","23:30","04:20","Linked to coupure nr 59314 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen ","CTL","Minor_AdHoc"," "," ",59314]
["2025-02-01","2025-02-02","SW",1,"130","A+B","TAMINES","CHATELET-GRIL OUEST","Weekend","Continuous","06:00","17:00","Maintenance Z15. 51 P4+","CTL","Medium"," ","HKM à adapter",53523]
["2025-02-01","2025-02-03","CE",1,"94","A+B","Y.NOORD HALLE","SAINTES","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59680 on line 96 tracks(s) A+B from Y.NOORD HALLE to TUBIZE: Vernieuwen BVL L96 + aw's 96/94 kant Lembeek zone A12-A13","CTL","Medium"," ",null,59680]
["2025-02-01","2025-02-03","CE",1,"96","A+B","Y.NOORD HALLE","TUBIZE","Weekend","Continuous","00:45","04:30","Vernieuwen BVL L96 + aw's 96/94 kant Lembeek zone A12-A13","CTL","Medium","TLO L96 + L94\r\nStation Halle afgesloten",null,59680]
["2025-02-01","2025-02-03","NE",1,"27","A+B","MECHELEN","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:00","04:30","Linked to coupure nr 58392 on line 25N tracks(s) A from MECHELEN to MECHELEN-NEKKERSPOEL: Vierendeelbrug Leuvensesteenweg L25 over L53-L53A  (liften brug)\r\nIn combinatie met COLT 57998\r\n\r\nMasterplan Mechelen\r\nrooster N geblokkeerd perrons 1,2,3,4,5 en 6","CTL","Medium"," "," ",58392]
["2025-02-01","2025-02-24","NE",1,"53","A+B","MECHELEN","MUIZEN-ROOSTER T","AllWeek","Continuous","00:01","04:00","Herelectrificatie L53","CTL","High"," "," ",57997]
["2025-02-03","2025-02-07","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Week","Night","23:00","04:10","Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation","CTL","Minor_AdHoc",null,"HKM à adapter",56485]
["2025-02-03","2025-02-07","SW",1,"78","A+B","BLATON","TOURNAI","Week","Night","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) + traverses biblocs\r\nTravaux préparatoires (2 semaines)\r\n+ Renouvellement AS 15H à l'entrée de la gare de Tournai\r\nTravaux de finition\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Voies 1, 2, A et B HS\r\nART 2 min"," ",61815]
["2025-02-03","2025-02-08","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59218 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen ","SAVU","Minor_AdHoc"," "," ",59218]
["2025-02-03","2025-02-08","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\n Spoor B L 50 tussen Gent Sint Pieters en Y. West Drieho","CTL","Minor_AdHoc"," "," ",59218]
["2025-02-03","2025-02-17","SE",1,"162","A","ROCHEFORT-JEMELLE","GRUPONT","AllWeek","Continuous","07:30","06:00","Renouvellement rails Forrières VA.\r\nRéunion 12/05/2022 : A placer début 2025 (Attente confirmation Daniel)","SAVU_CTRL","High","CTL nocturnes de 7 heures requises."," ",47717]
["2025-02-03","2025-03-01","SW",1,"94","*","TOURNAI","TOURNAI","AllWeek","Continuous","06:00","04:30","Renouvellement des voies 315 et 316 en gare de Tournai","Autre","Minor_AdHoc","Voies 314 à 318 HS en continu\r\nCas électrique 28643 en continu\r\n+Cas électrique 28637 de jour (7h-17h)"," ",53245]
["2025-02-03","2025-03-08","SW",1,"140","A/B","OTTIGNIES","LA ROCHE(BRABANT)","AllWeek","Continuous","06:00","06:00","Renouvellement des traverses P93","SAVU_CTRL","High","5 semaines SAVU en continu + CTL de nuit (23:00-5:00)\r\nART 3 min"," ",53251]
["2025-02-03","2025-04-07","CE",1,"161","*","SCHAERBEEK","SCHAERBEEK","AllWeek","Continuous","07:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers","Autre","Minor_AdHoc"," "," ",50050]
["2025-02-03","2025-12-12","SE",1,"24","A/B","REMERSDAAL","MONTZEN-GRIL M","AllWeek","Continuous","06:00","22:00","Réfection de la voûte du tunnel de la Galoppe (bK 33.658 - 34.455)\r\nRenouvellement de la chape d'étanchéité du viaduc de la Galoppe (32.701 - 33.023)","SAVU","High","+ Toutes les CTL possibles (tous les blancs travaux + autant de lundi que possible)\r\nART de la BK 33.658 à 34.455 - HKV: 1.8  HKM:2.4\r\nDurant la 1ère semaine qui suivra le changement de côté du SAVU, l'ART sera prolongé depuis bK 32.701 jusqu'à bK 34.45"," ",55983]
["2025-02-07","2025-02-10","CE",1,"25","A+B","BRUXELLES-NORD","SCHAERBEEK","Weekend","Continuous","23:50","04:30","Linked to coupure nr 59122 on line 0/5 tracks(s) A+B from BRUXELLES-CHAPELLE to BRUXELLES-NORD: Vernieuwing C-sporen (C11+C12): koker 3 verlengd tot de perrons 5 en 6 van FSR.\r\nFBN sp 10 vanaf uitrit koker als bescherming, sp 10 bruikbaar in cds.","CTL","Medium"," "," ",59122]
["2025-02-07","2025-02-10","SE",1,"161","A","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59164]
["2025-02-07","2025-02-10","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Weekend","Continuous","23:00","04:10","Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation\r\n+ Maintenance Z2. 51  P4+","CTL","Medium",null,"HKM à adapter",56487]
["2025-02-07","2025-02-10","SW",1,"78","A/B","BLATON","TOURNAI","Weekend","Continuous","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) - Phase 1\r\nDossier de concertation validé en octobre 2022","CTL","Medium","4 semaines SAVU jour et CTL nuit (22h50-05h00) + CTL weekend\r\nART stabilisation (60) : du 17/02 5h au 24/02 5h VB + du 24/02 5h au 3/03 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",59444]
["2025-02-10","2025-02-15","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59219 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen ","SAVU","Minor_AdHoc"," "," ",59219]
["2025-02-10","2025-02-15","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nDoes Spoor A L 50 tussen Gent Sint Pieters en Y. West Dr","CTL","Minor_AdHoc"," "," ",59219]
["2025-02-10","2025-02-15","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","23:00","05:45","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 1 - Nuits de préparation à la démolition\r\nPhase 1.1 - travaux au niveau de la 1ère travée située au-dessus des L75 VA+L75 VB et de la pile centrale (L75","CTL","Minor_AdHoc","Phase 1.1 – CTL L75 + SAVU L75A de nuit de semaine\r\nLes AW 03K, 04AK, 04BK/05AK, 10 AK, 11 AK restent parcourables"," ",55843]
["2025-02-10","2025-02-15","SW",1,"75A","A/B","MOUSCRON","MOUSCRON","Week","Night","23:00","05:45","Linked to coupure nr 55843 on line 75 tracks(s) A+B from MOUSCRON to MOUSCRON-FRONTIERE: Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 1 - Nuits de préparation à la démolition\r\nPhase 1.1 - travaux a","SAVU","Minor_AdHoc"," "," ",55843]
["2025-02-10","2025-02-15","SW",1,"96","A+B","MONS","QUEVY-FRONTIERE","Week","Night","22:30","05:00","Aménagement de Quévy\r\nTravaux préparatoires - déchargement LRS","CTL","Minor_AdHoc","CTL de nuit"," ",53240]
["2025-02-10","2025-02-21","SW",1,"78","A/B","BLATON","Y.MAUBRAY","AllWeek","Continuous","05:00","22:50","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) - Phase 1\r\nDossier de concertation validé en octobre 2022","SAVU_CTRL","High","SAVU et CTL nuit (22h50-05h00) + CTL weekend\r\nVB HS du 10/02 5h au 17/02 5h\r\nVA HS du 14/02 22h50 au 24/02 5h\r\nART stabilisation (60) : du 17/02 5h au 24/02 VB + du 24/02 5h au 3/03 VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",53247]
["2025-02-14","2025-02-17","CE",1,"25","A+B","BRUXELLES-NORD","SCHAERBEEK","Weekend","Continuous","23:50","04:30","Linked to coupure nr 59123 on line 0/5 tracks(s) A+B from BRUXELLES-CHAPELLE to BRUXELLES-NORD: Vernieuwing C-sporen (C11+C12): koker 3 verlengd tot de perrons 5 en 6 van FSR.\r\nFBN sp 10 vanaf uitrit koker als bescherming, sp 10 bruikbaar in cds.","CTL","Medium"," "," ",59123]
["2025-02-14","2025-02-17","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Weekend","Continuous","23:00","04:10","Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation\r\n+ Maintenance Z2. 51  P4+","CTL","Medium",null,"HKM à adapter",56488]
["2025-02-14","2025-02-17","SW",1,"140","A/B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement des traverses P93","CTL","Medium",null," ",59516]
["2025-02-14","2025-02-17","SW",1,"78","A/B","BLATON","TOURNAI","Weekend","Continuous","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) - Phase 1\r\nDossier de concertation validé en octobre 2022","CTL","Medium","ART stabilisation (60) : du 17/02 au 24/02 VB + du 24/02 au 3/03 VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",59445]
["2025-02-15","2025-02-17","NE",1,"27","A+B","MECHELEN","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:00","04:00","Masterplan Mechelen\r\nrooster N geblokkeerd perrons 1,2,3,4,5 en 6 bereikbaar vanuit rooster M.\r\n\r\ngecombineerd met COLT 57998 + nachten L25N","CTL","Medium"," "," ",58449]
["2025-02-17","2025-02-21","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Week","Night","23:00","04:10","Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation","CTL","Minor_AdHoc",null,"HKM à adapter",56486]
["2025-02-17","2025-02-21","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","22:30","04:10","Linked to coupure nr 55844 on line 75A tracks(s) A+B from MOUSCRON to HERSEAUX: Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 1 - Nuits de préparation à la démolition\r\nPhase 1.2 - travaux au niveau ","CTL","Minor_AdHoc"," "," ",55844]
["2025-02-17","2025-02-21","SW",1,"75A","A+B","MOUSCRON","HERSEAUX","Week","Night","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 1 - Nuits de préparation à la démolition\r\nPhase 1.2 - travaux au niveau de la 2ère travée située au-dessus des L75A VB +L75A VA et de la pile centrale (","CTL","Minor_AdHoc","Phase 1.2 – CTL L75+L75A de nuit de semaine​"," ",55844]
["2025-02-17","2025-03-03","SW",1,"78","A+B","BLATON","TOURNAI","AllWeek","Continuous","05:00","05:00","ART 4min \r\nBlaton - Y.Maubray : Renouvellement ballast C75 (2x7km) - Phase 1\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART stabilisation (60) : du 17/02 5h au 24/02 5h VB + du 24/02 5h au 3/03 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",61817]
["2025-02-17","2025-05-18","SE",1,"166","B","GENDRON-CELLES","HOUYET","AllWeek","Continuous","06:00","16:00","Mise au gabarit des pistes de circulation\r\nSécurisation des parois rocheuses \r\nRenouvellement PI BK 13808","SAVU","High","+ CTL weekends du samedi 23h00 au dimanche 15h00"," ",46317]
["2025-02-17","2025-06-02","SE",1,"162","A","GRUPONT","HATRIVAL","AllWeek","Continuous","06:00","05:00","Grupont - Hatrival : phase 13","SAVU_CTRL","High","CTL de 22h10 à 5h15"," ",33295]
["2025-02-17","2025-06-02","SE",1,"162","B","CINEY","HAVERSIN","AllWeek","Continuous","06:00","05:00","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 13\r\nciney-haversin\r\nTravaux effectués = Travaux caténaires et GC linéaire + début des travaux de quai à Leignon et Chapois","SAVU_CTRL","High","CTL de Nuit : Lu^Ma à Je^Ve :00:10–04:50, Ve^Sa 00:10–06:30, Sa^Di 23:10–06:30, Di^Lu 23:10–04:50\r\nAS 34BK parcourable\r\nSAVU prolongé jusqu'en mai suite arbitrage budgétaire"," ",62770]
["2025-02-18","2025-02-22","NW",1,"50A","A+B","BRUGGE","OOSTENDE","Week","Night","00:30","04:30","Afbraak van de ONB over het nieuwe kanaal Plassendale-Nieuwpoort \r\n\r\nVoorbereidende nachten \r\n\r\nW1 van 2","CTL","Minor_AdHoc"," "," ",59390]
["2025-02-21","2025-02-24","SE",1,"161","A+B","WATERMAEL","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER","CTL","Medium","ART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59159]
["2025-02-21","2025-02-24","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 minutes"," ",54939]
["2025-02-21","2025-02-24","SW",1,"140","A/B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement des traverses P93","CTL","Medium",null," ",59517]
["2025-02-21","2025-02-24","SW",1,"78","A/B","BLATON","TOURNAI","Weekend","Continuous","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) - Phase 1\r\nDossier de concertation validé en octobre 2022","CTL","Medium","ART stabilisation (60) : du 17/02 5h au 24/02 5h VB + du 24/02 5h au 3/03 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",59446]
["2025-02-21","2025-02-25","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","AllWeek","Continuous","23:00","22:30","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 2 - CTL en continu pour la démolition des tabliers et de la pile centrale\r\nPhase 2.1 - travaux au niveau de la 1ère travée située au-dessus des L75 VA+L","CTL","Medium","Phase 2.1 – CTL L75 + SAVU L75A 5 jours en continu​\r\nLes AW 03K, 04AK, 04BK/05AK, 10 AK, 11 AK restent parcourables"," ",55845]
["2025-02-21","2025-02-25","SW",1,"75A","*","MOUSCRON","MOUSCRON","AllWeek","Continuous","23:00","22:30","Linked to coupure nr 55845 on line 75 tracks(s) A+B from MOUSCRON to MOUSCRON-FRONTIERE: Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 2 - CTL en continu pour la démolition des tabliers et de la pil","SAVU","Minor_AdHoc"," "," ",55845]
["2025-02-21","2025-03-10","SE",1,"162","A+B","HAVERSIN","ROCHEFORT-JEMELLE","AllWeek","Continuous","23:40","04:20","Travaux caténaire et quais en gare de Marloie.\r\nmassifs / poteaux/ CDPA / feeder / R3 mixte / démontage caténaire existante\r\nrehaussement et allongement des quais en gare\r\ntravaux PMR pour SNCB probables","CTL","High",null," ",60135]
["2025-02-22","2025-02-24","NE",1,"27","A+B","MECHELEN","MECHELEN-NEKKERSPOEL","Weekend","Night","00:00","04:30","Linked to coupure nr 58395 on line 25N tracks(s) A from MECHELEN to MECHELEN-NEKKERSPOEL: Vierendeelbrug Leuvensesteenweg L25 over L53-L53A  (liften brug)\r\nIn combinatie met COLT 57998\r\n3 nachten\r\n\r\nMasterplan Mechelen\r\nL27: rooster N geblokkeerd perron","CTL","Minor_AdHoc"," "," ",58395]
["2025-02-22","2025-02-24","NE",1,"52","A/B","Y.ANTWERPEN-ZUID","HOBOKEN-POLDER","Weekend","Continuous","06:00","05:00","Stationsproject Antwerpen-Zuid voor B-Stations:\r\n\r\nTrapconstructie op perron","SAVU","Minor_AdHoc","DOES L52 periode van 2 weken"," ",60184]
["2025-02-24","2025-02-28","SW",1,"117","B","MANAGE","LUTTRE","Week","Day","08:30","15:30","Aménagement de Luttre - phase 2025\r\nentre  IX-E.20 > quai IV\r\nTravaux ES + Préparations caténaires, \r\n(réalisation de massifs en tête de faisceau)\r\n+ révision à mi-vie caténaire L117, entre IX-E.20 > T-H.11","SAVU","Minor_AdHoc","SAVU, de jour en semaine, entre T-H.11 et K-E.20 + voies 152/153 de Luttre\r\nvoie IV de Luttre en garage, entrée et sortie vers Charleroi\r\n!!! sectionnement caténaire créé en 2023 entre la transversale nord et le quai de Luttre"," ",56182]
["2025-02-24","2025-03-01","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58726]
["2025-02-24","2025-03-01","SW",1,"78","A+B","BLATON","TOURNAI","Week","Night","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) + traverses biblocs - Phase 1\r\nTravaux finition (2 semaines)\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","ART stabilisation (60) : du 17/02 5h au 24/02 5h VB + du 24/02 5h au 3/03 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",56094]
["2025-02-24","2025-03-10","SW",1,"96","A+B","MONS","QUEVY-FRONTIERE","AllWeek","Continuous","06:00","04:30","Aménagement de Quévy - Phase 1\r\n+ Travaux OA : Chape PI 71.240 du 03 au 07/03 + Chantier SPW Entretien ou Renouvellement PS 65.090","CTL","High","CTL de 14 jours (congés scolaires FWB)\r\nART OA 60km/h 2min ajouté en plus de l'ART V -> voir si 2 ART séparé ou 1 allongé","HKM à adapter",53237]
["2025-02-24","2025-03-16","SE",1,"130","B","MOUSTIER","FRANIERE","AllWeek","Continuous","07:00","16:00","Renouvellement du système de drainage (caniveaux) dans le bois de Soye\r\nDossier de concertation validé en octobre 2022","SAVU","High","1 prestation en 8h00 – 16h00 (heures exactes à déterminer en concertation en fonction des pointes de trafic). Pas de limitation du nombre de trains durant cette prestation. ​\r\n1 prestation en 22h00 – 6h00. Maximum 4 trains/heure durant cette prestation "," ",56183]
["2025-02-24","2025-03-24","SW",1,"96","A+B","QUEVY","QUEVY-FRONTIERE","AllWeek","Continuous","06:00","04:30","Aménagement de Quévy - Phase 2","CTL","High","Prolongation de 14 jours de la CTL entre Mons et Quévy-Fr.\r\nART stab","HKM à adapter",53236]
["2025-02-25","2025-02-28","NW",1,"50A","A+B","BRUGGE","OOSTENDE","Week","Night","00:30","04:30","Afbraak van de ONB over het nieuwe kanaal Plassendale-Nieuwpoort \r\n\r\nVoorbereidende nachten \r\n\r\nW2 van 2\r\n\r\nN R5/R6 opgenomen in weekend-TLO","CTL","Minor_AdHoc"," "," ",59399]
["2025-02-25","2025-03-03","SW",1,"75","A","MOUSCRON-FRONTIERE","MOUSCRON","AllWeek","Continuous","22:30","04:10","Linked to coupure nr 55846 on line 75A tracks(s) A+B from MOUSCRON to HERSEAUX: Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 2 - CTL en continu pour la démolition des tabliers et de la pile central","CTL","Medium"," "," ",55846]
["2025-02-25","2025-03-03","SW",1,"75A","A+B","MOUSCRON","HERSEAUX","AllWeek","Continuous","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 2 - CTL en continu pour la démolition des tabliers et de la pile centrale\r\nPhase 2.2 - travaux au niveau de la 2è travée\r\nDossier de concertation validé","CTL","Medium","Phase 2.2 – CTL L75+L75A 5 jours en continu​"," ",55846]
["2025-02-27","2025-02-28","SE",1,"139","A","SINT-JORIS-WEERT","WAVRE","Week","Continuous","08:00","23:00","Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre - travaux préparatoires","SAVU","Minor_AdHoc","Voie A HS entre SJW et Wavre"," ",55769]
["2025-02-28","2025-03-03","SE",1,"161","A/B","NAMUR","GEMBLOUX","AllWeek","Continuous","23:00","05:00","Travaux caténaires\r\n2- Déroulage Rhisnes- Mont St Guibert","SAVU_CTRL","Minor_AdHoc","1 we en continu de SAVU vend 23h au lun 05h + CTL de nuit"," ",59616]
["2025-02-28","2025-03-03","SE",1,"161","A+B","OTTIGNIES","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER\r\nGare Ottignies","Autre","Minor_AdHoc","voies 4 et 5 à quai HS\r\n+ Voie 3 à quai inaccessible côté Bruxelles\r\nVoie 142 HS \r\nPas de lien L161-L139 et L161-L140. PED SNCB inaccessible. Circulation L161 vers Namur à contrevoie en gare"," ",59176]
["2025-02-28","2025-03-05","NW",1,"50A","A+B","BRUGGE","OOSTENDE","AllWeek","Continuous","23:55","04:00","Afbraak van de ONB over het nieuwe kanaal Plassendale - Nieuwpoort","CTL","Medium"," "," ",58385]
["2025-02-28","2025-03-10","SE",1,"139","A+B","SINT-JORIS-WEERT","Y.OTTIGNIES-RELAIS","AllWeek","Continuous","23:00","05:00","Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre\r\nRenouvellement de rails entre SJW et Y Ottignies Relais","CTL","High","Congés scolaires\r\nART stab 4'"," ",55770]
["2025-03-01","2025-03-10","CE",1,"26","A+B","Y.KEELBEEK","EVERE","AllWeek","Continuous","00:20","04:00","Werken MIVB: versterking brug aansluiting Haachtsesteenweg\r\n\r\nSamen met BVL-werken","CTL","High","TLO L26 tussen Evere en Y Keelbeek"," ",59146]
["2025-03-01","2025-04-21","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET","Weekend","Night","23:10","05:10","Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses","CTL","Minor_AdHoc",null," ",54819]
["2025-03-03","2025-03-07","SW",1,"117","A","MANAGE","LUTTRE","Week","Day","08:30","15:30","Aménagement de Luttre - phase 2025\r\nPréparations caténaires, I-E.20 > quai III\r\n+ révision à mi-vie caténaire L117, I-E.20 > TX-H.11","SAVU","Minor_AdHoc","SAVU, de jour en semaine, entre TX-H.11 et KX-E.20\r\nvoie III de Luttre en garage, entrée et sortie vers Charleroi\r\n!!! sectionnement caténaire créé en 2023 entre la transversale nord et le quai de Luttre"," ",56116]
["2025-03-03","2025-03-07","SW",1,"75","B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Day","06:00","16:00","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pour la réalisation des fondat","SAVU","Minor_AdHoc","Phase 3.1 – SAVU L75 de jour pendant 4 sem.​\r\nTravaux de jour en semaine 10, 14, 17, 19 et 21 entre 6h et 16h​"," ",55866]
["2025-03-03","2025-03-08","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58727]
["2025-03-03","2025-03-08","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n3 - Réalisation de massifs et pose de poteaux","SAVU_CTRL","Minor_AdHoc","1 semaine de SAVU de nuits en semaine + CTL dans les blancs travaux"," ",59617]
["2025-03-03","2025-03-08","SW",1,"78","A+B","BLATON","TOURNAI","Week","Night","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) + traverses biblocs - Phase 1\r\nTravaux finition (2 semaines)\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","ART stabilisation (60) : du 17/02 5h au 24/02 5h VB + du 24/02 5h au 3/03 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",61816]
["2025-03-03","2025-03-28","SE",1,"162","B","ARLON","Y.AUTELBAS","AllWeek","Continuous","06:00","16:00","Assainissement Voie B","SAVU_CTRL","High","AS 41AL non engagé\r\nCTL nocturnes 22:30-4:30 (pas d'accès routier : il faut des HKC sur la VA).\r\nART 2' du 28/03 au 9/04"," ",56546]
["2025-03-03","2025-04-06","SE",1,"154","A/B","YVOIR","YVOIR","AllWeek","Continuous","06:00","22:00","Travaux SNCB\r\nNouveaux ascenseurs+ Finitions des quais en gare d'Yvoir","SAVU","High","Voie 3 HS et HT 5 jours en continu\r\nVoie 2 HS 21 jours en continu\r\nVoie 1 HS et HT 5 jours de jour (6h d'amplitude min) \r\nContact SNCB pour détails: Laurence Daras"," ",56451]
["2025-03-04","2025-03-07","NE",1,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Week","Night","00:00","04:30","Brug Leuvensesteenweg L25 over L53-L53A\r\nweeknachten","CTL","Minor_AdHoc"," "," ",58410]
["2025-03-04","2025-03-08","CE",1,"26","A+B","Y.NOORD HALLE","Y.LINKEBEEK-HALLE","Week","Night","00:20","04:00","Verbreding ONB Spoorwegstraat: voorbereiding","CTL","Minor_AdHoc","TLO L26 tussen Halle en Y Linkebeek/Halle"," ",59455]
["2025-03-07","2025-03-10","SE",1,"162","A+B","Y.AUTELBAS","STERPENICH-FRONTIERE","Weekend","Continuous","18:00","06:00","Renouvellement du PN163 de Sterpenich (BK 206600 à 206700) avec pose d'un CSV avec ripage caténaire.","CTL","Medium","Minimum 60h de CTL en continu\r\nART de stabilisation à 40km/h VA+ VB entre BK 206600 à 206700 pendant 2 semaines  (date probable)\r\nPerte de temps HKV: 1,92min\r\nPerte de temps HKM:1,89min"," ",56446]
["2025-03-08","2025-03-10","NE",1,"12","A+B","ESSEN-GRENS","Y.LUCHTBAL","Weekend","Continuous","01:00","04:00","Onderhoud","CTL","Medium","Geen verkeer mogelijk van/naar Roosendaal"," ",56123]
["2025-03-08","2025-03-10","NE",1,"12/1","A+B","Y.DRIEHOEKSTRAAT","Y.SINT-MARIABURG","Weekend","Continuous","01:00","04:00","Linked to coupure nr 56123 on line 12 tracks(s) A+B from ESSEN-GRENS to Y.LUCHTBAL: Onderhoud","CTL","Medium"," "," ",56123]
["2025-03-08","2025-03-10","NE",1,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Weekend","Continuous","00:00","04:30","Brug Leuvensesteenweg L25 over L53-L53A\r\nweekend TLO","CTL","Medium"," "," ",58412]
["2025-03-08","2025-03-10","NE",1,"52","A/B","Y.ANTWERPEN-ZUID","HOBOKEN-POLDER","Weekend","Continuous","06:00","05:00","Stationsproject Antwerpen-Zuid voor B-Stations:\r\n\r\nTrapconstructie op perron","SAVU","Minor_AdHoc","DOES L52 periode van 2 weken"," ",60185]
["2025-03-08","2025-03-10","NW",1,"51","A+B","BRUGGE","Y.BLAUWE TOREN","Weekend","Continuous","06:00","04:30","Levering en inbouw van de wissel 15U met Kirow Kraan","CTL","Medium"," "," ",59193]
["2025-03-08","2025-03-24","SW",1,"124","A","ROUX","MARCHIENNE-AU-PONT","AllWeek","Continuous","09:00","04:40","Rénovation et sécurisation des murs de soutènement voie A entre la BK 49.050 et la BK 29.300","SAVU_CTRL","High",null," ",55544]
["2025-03-10","2025-03-11","SE",1,"139","A","SINT-JORIS-WEERT","WAVRE","Week","Continuous","08:00","23:00","Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre - travaux pour remise en service","SAVU","Minor_AdHoc","Voie A HS entre SJW et Wavre"," ",55768]
["2025-03-10","2025-03-14","NW",1,"50","A+B","SCHELLEBELLE","Y.OOST DRIEHOEK LEDEBERG","Week","Night","23:55","04:30","Vernieuwen Y Melle\r\n\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc","geen verkeer mogelijk tss Schellebelle en Gent.\r\ngeen verkeer L50 tussen Denderleeuw en Gent.\r\ngeen verkeer naar L122.\r\nBundel polyvalente werkplaats Melle en bundel Merelbeke Centraal niet bereikbaar Kant Y Melle West."," ",30831]
["2025-03-10","2025-03-14","NW",1,"50A/4","A+B","Y.MEULEWIJK","Y.MELLE","Week","Night","23:55","04:30","Linked to coupure nr 30831 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y Melle\r\n\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc"," "," ",30831]
["2025-03-10","2025-03-14","NW",1,"50E","A+B","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG","Week","Night","23:55","04:30","Linked to coupure nr 30831 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y Melle\r\n\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc"," "," ",30831]
["2025-03-10","2025-03-14","SW",1,"117","B","MANAGE","LUTTRE","Week","Day","08:30","15:30","Aménagement de Luttre - phase 2025\r\nPréparations caténaires, IX-E.20 > quai IV\r\n+ révision à mi-vie caténaire L117, IX-E.20 > T-H.11","SAVU","Minor_AdHoc","SAVU, de jour en semaine, entre T-H.11 et K-E.20\r\nvoie IV de Luttre en garage, entrée et sortie vers Charleroi\r\n!!! sectionnement caténaire créé en 2023 entre la transversale nord et le quai de Luttre"," ",56117]
["2025-03-10","2025-03-14","SW",1,"75A","A+B","MOUSCRON","MOUSCRON","Week","Day","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.2 - Construction des nouvelles culées et fondations​\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Phase 3.2 – MHS du faisceau de jour​\r\nTravaux de jour en semaine 11, 13, 16, 18 et 20 entre 8h et 16h"," ",55860]
["2025-03-10","2025-03-15","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58728]
["2025-03-10","2025-03-15","NE",1,"27","A+B","MECHELEN","MECHELEN-NEKKERSPOEL","Week","Night","23:00","04:00","Masterplan Mechelen\r\nrooster N geblokkeerd perrons 1,2,3,4,5 en 6 bereikbaar vanuit rooster M.","CTL","Minor_AdHoc"," "," ",58450]
["2025-03-10","2025-03-24","SE",1,"139","A+B","SINT-JORIS-WEERT","Y.OTTIGNIES-RELAIS","AllWeek","Continuous","05:00","05:00","ART 4min\r\nRenouvellement de traverses par train P93 de la voie A entre SJW et Wavre\r\nRenouvellement de rails entre SJW et Y Ottignies Relais","ART","Minor_AdHoc",null," ",59522]
["2025-03-10","2025-03-24","SE",1,"162","A+B","Y.AUTELBAS","STERPENICH-FRONTIERE","Weekend","Continuous","18:00","06:00","ART 2min\r\nRenouvellement du PN163 de Sterpenich (BK 206600 à 206700) avec pose d'un CSV avec ripage caténaire.","ART","Minor_AdHoc","ART de stabilisation à 40km/h VA+ VB entre BK 206600 à 206700 pendant 2 semaines  (date probable)\r\nPerte de temps HKV: 1,92min\r\nPerte de temps HKM:1,89min"," ",59586]
["2025-03-10","2025-11-15","SW",1,"96","A+B","QUEVY-FRONTIERE","QUEVY","Week","Night","23:00","04:00","Travaux SNCF\r\nV RM 14h00","CTL","Minor_AdHoc",null," ",62954]
["2025-03-11","2025-03-15","NE",1,"53","A+B","MECHELEN","MUIZEN","Week","Night","00:01","04:00","Vernieuwing Vierendeelbrug Leuvensesteenweg","CTL","Minor_AdHoc","(rooster N L27 beschikbaar)"," ",58408]
["2025-03-11","2025-03-15","NE",1,"53A","A+B","Y.MUIZEN","MECHELEN","Week","Night","00:01","04:00","Linked to coupure nr 58408 on line 53 tracks(s) A+B from MECHELEN to MUIZEN: Vernieuwing Vierendeelbrug Leuvensesteenweg","CTL","Minor_AdHoc"," "," ",58408]
["2025-03-11","2025-03-15","NW",1,"50A","A+B","BRUGGE","OOSTENDE","Week","Night","00:30","04:30","Afbraak van de ONB over het nieuwe kanaal Plassendale-Nieuwpoort \r\n\r\nAfwerkingsnachten \r\n\r\nW1 van 2","CTL","Minor_AdHoc"," "," ",59400]
["2025-03-14","2025-03-17","NW",1,"50","A+B","SCHELLEBELLE","Y.OOST DRIEHOEK LEDEBERG","Weekend","Continuous","23:55","04:30","Vernieuwen Y Melle \r\n\r\n* uitgesteld naar 2025","CTL","Medium","geen verkeer mogelijk tss Schellebelle en Gent.\r\ngeen verkeer L50 tussen Denderleeuw en Gent.\r\ngeen verkeer naar L122.\r\nBundel polyvalente werkplaats Melle en bundel Merelbeke Centraal niet bereikbaar Kant Y Melle West.\r\nGevallen 29129-29131-29128-29130"," ",30829]
["2025-03-14","2025-03-17","NW",1,"50A/4","A+B","Y.MEULEWIJK","Y.MELLE","Weekend","Continuous","23:55","04:30","Linked to coupure nr 30829 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y Melle \r\n\r\n* uitgesteld naar 2025","CTL","Medium"," "," ",30829]
["2025-03-14","2025-03-17","NW",1,"50E","A+B","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG","Weekend","Continuous","23:55","04:30","Linked to coupure nr 30829 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y Melle \r\n\r\n* uitgesteld naar 2025","CTL","Medium"," "," ",30829]
["2025-03-14","2025-03-17","SE",1,"161","A","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59165]
["2025-03-14","2025-03-17","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n4- Déroulage Rhisnes- Mont St Guibert","SAVU_CTRL","Minor_AdHoc","1 we en continu de SAVU vend 23h au lun 05h + CTL de nuit"," ",59618]
["2025-03-14","2025-03-31","SE",1,"43","A/B","ANGLEUR","TILFF","AllWeek","Continuous","23:00","05:00","Criblage","SAVU_CTRL","High","CTL de nuit min 6h\r\nVoie A HS du 14/03 au 24/03\r\nVB HS du 21/03 au 31/03\r\nART 2 min"," ",55764]
["2025-03-14","2025-04-14","SE",1,"43","A/B","ANGLEUR","TILFF","AllWeek","Continuous","23:00","05:00","ART 2min\r\nCriblage","ART","Minor_AdHoc",null," ",59548]
["2025-03-15","2025-03-17","SE",1,"139","A+B","SINT-JORIS-WEERT","WAVRE","Weekend","Night","23:00","05:00","Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre - contraintes, finitions (1)","CTL","Minor_AdHoc",null," ",55767]
["2025-03-17","2025-03-21","NW",1,"50","A+B","SCHELLEBELLE","Y.OOST DRIEHOEK LEDEBERG","Week","Night","23:55","04:30","Vernieuwen Y. Melle \r\n\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc","geen verkeer mogelijk tss Schellebelle en Gent.\r\ngeen verkeer L50 tussen Denderleeuw en Gent.\r\ngeen verkeer naar L122.\r\nBundel polyvalente werkplaats Melle en bundel Merelbeke Centraal niet bereikbaar Kant Y Melle West."," ",30839]
["2025-03-17","2025-03-21","NW",1,"50A/4","A+B","Y.MEULEWIJK","Y.MELLE","Week","Night","23:55","04:30","Linked to coupure nr 30839 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y. Melle \r\n\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc"," "," ",30839]
["2025-03-17","2025-03-21","NW",1,"50E","A+B","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG","Week","Night","23:55","04:30","Linked to coupure nr 30839 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y. Melle \r\n\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc"," "," ",30839]
["2025-03-17","2025-03-22","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58729]
["2025-03-17","2025-04-05","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n5 - Réalisation de massifs et pose de poteaux","SAVU_CTRL","Minor_AdHoc","3 semaines SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 4)"," ",59620]
["2025-03-17","2025-04-06","SE",1,"130","A","MOUSTIER","FRANIERE","AllWeek","Continuous","07:00","16:00","Renouvellement du système de drainage (caniveaux) dans le bois de Soye\r\nDossier de concertation validé en ocotbre 2022","SAVU","High","1 prestation en 8h00 – 16h00 (heures exactes à déterminer en concertation en fonction des pointes de trafic). Pas de limitation du nombre de trains durant cette prestation. ​\r\n1 prestation en 22h00 – 6h00. Maximum 4 trains/heure durant cette prestation "," ",56184]
["2025-03-17","2025-04-12","SW",1,"140","A/B","OTTIGNIES","LA ROCHE(BRABANT)","AllWeek","Continuous","06:00","06:00","Renouvellement des traverses P93","SAVU_CTRL","High","4 semaines SAVU en continu + CTL de nuit (23:00-5:00)\r\nART 3min"," ",53252]
["2025-03-18","2025-03-22","NE",1,"25","A+B","MECHELEN","MECHELEN-DIJKSTRAAT","Week","Night","00:00","04:30","Brug Leuvensesteenweg L25 over L53-L53A\r\nweeknachten","CTL","Minor_AdHoc"," "," ",58411]
["2025-03-18","2025-03-22","NW",1,"50A","A+B","BRUGGE","OOSTENDE","Week","Night","00:30","04:30","Afbraak van de ONB over het nieuwe kanaal Plassendale-Nieuwpoort \r\n\r\nAfwerkingsnachten \r\n\r\nW2 van 2","CTL","Minor_AdHoc"," "," ",59401]
["2025-03-21","2025-03-24","NW",1,"50","A+B","SCHELLEBELLE","Y.OOST DRIEHOEK LEDEBERG","Weekend","Continuous","23:55","04:30","Vernieuwen Y Melle\r\n\r\n* uitgesteld naar 2025","CTL","Medium","geen verkeer mogelijk tss Schellebelle en Gent.\r\ngeen verkeer L50 tussen Denderleeuw en Gent.\r\ngeen verkeer naar L122.\r\nBundel polyvalente werkplaats Melle en bundel Merelbeke Centraal niet bereikbaar Kant Y Melle West."," ",30830]
["2025-03-21","2025-03-24","NW",1,"50A/4","A+B","Y.MEULEWIJK","Y.MELLE","Weekend","Continuous","23:55","04:30","Linked to coupure nr 30830 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y Melle\r\n\r\n* uitgesteld naar 2025","CTL","Medium"," "," ",30830]
["2025-03-21","2025-03-24","NW",1,"50E","A+B","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG","Weekend","Continuous","23:55","04:30","Linked to coupure nr 30830 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y Melle\r\n\r\n* uitgesteld naar 2025","CTL","Medium"," "," ",30830]
["2025-03-21","2025-03-24","SE",1,"43","B","ANGLEUR","TILFF","Weekend","Continuous","23:00","05:00","Criblage","CTL","Medium",null," ",55765]
["2025-03-21","2025-03-24","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 minutes"," ",54941]
["2025-03-22","2025-03-24","SE",1,"139","A+B","SINT-JORIS-WEERT","WAVRE","Weekend","Night","23:00","05:00","Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre \r\ncontraintes, finitions (2) suppression ART","CTL","Minor_AdHoc",null," ",55771]
["2025-03-24","2025-03-28","NW",1,"50","A+B","SCHELLEBELLE","Y.OOST DRIEHOEK LEDEBERG","Week","Night","23:55","04:30","Vernieuwen Y Melle\r\n\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc","geen verkeer mogelijk tss Schellebelle en Gent.\r\ngeen verkeer L50 tussen Denderleeuw en Gent.\r\ngeen verkeer naar L122.\r\nBundel polyvalente werkplaats Melle en bundel Merelbeke Centraal niet bereikbaar Kant Y Melle West."," ",30840]
["2025-03-24","2025-03-28","NW",1,"50A/4","A+B","Y.MEULEWIJK","Y.MELLE","Week","Night","23:55","04:30","Linked to coupure nr 30840 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y Melle\r\n\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc"," "," ",30840]
["2025-03-24","2025-03-28","NW",1,"50E","A+B","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG","Week","Night","23:55","04:30","Linked to coupure nr 30840 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y Melle\r\n\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc"," "," ",30840]
["2025-03-24","2025-03-28","SW",1,"75A","A+B","MOUSCRON","MOUSCRON","Week","Day","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.2 - Construction des nouvelles culées et fondations​\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Phase 3.2 – MHS du faisceau de jour​\r\nTravaux de jour en semaine 11, 13, 16, 18 et 20 entre 8h et 16h"," ",61846]
["2025-03-24","2025-03-29","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58730]
["2025-03-24","2025-03-29","SW",1,"117","A+B","MANAGE","LUTTRE","Week","Continuous","08:30","05:00","Aménagement de Luttre - Phase 2025\r\nPréparations","SAVU_CTRL","Minor_AdHoc","CTL Nuits 21:50 - 5:00 SAVU de jour en semaine, \r\n3 jours entre TX-H.11 et KX-E.20\r\n2 jours entre T-H.11 et K-E.20\r\nvoie III ou IV de Luttre en garage, entrée et sortie vers Charleroi"," ",53223]
["2025-03-24","2025-04-04","CE",1,"96B","*","FOREST-NORD","FOREST-MIDI-VOIES 920/926","AllWeek","Continuous","23:30","23:30","Premontage van de wissels 12F-11F-10F en 08F in de bundel A te Vorst.","Autre","Minor_AdHoc","Bundel A sporen 414 tem 416 en sp 961 continu BDS."," ",59157]
["2025-03-28","2025-03-31","SE",1,"24","A+B","Y.GLONS","MONTZEN-FRONTIERE","Weekend","Continuous","23:00","05:00","Entretien","CTL","Medium","ART 2'"," ",51835]
["2025-03-28","2025-04-09","SE",1,"162","B","ARLON","Y.AUTELBAS","AllWeek","Continuous","16:00","16:00","ART 2min\r\nAssainissement Voie B","ART","Minor_AdHoc",null," ",59587]
["2025-03-29","2025-03-31","SE",1,"139","A+B","SINT-JORIS-WEERT","WAVRE","Weekend","Night","23:00","05:00","Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre \r\ncontraintes, finitions (3) suppression ART","CTL","Minor_AdHoc",null," ",55772]
["2025-03-31","2025-04-04","NW",1,"50","A+B","SCHELLEBELLE","Y.OOST DRIEHOEK LEDEBERG","Week","Night","23:55","04:30","Vernieuwen Y Melle\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc","geen verkeer mogelijk tss Schellebelle en Gent.\r\ngeen verkeer L50 tussen Denderleeuw en Gent.\r\ngeen verkeer naar L122.\r\nBundel polyvalente werkplaats Melle en bundel Merelbeke Centraal niet bereikbaar Kant Y Melle West."," ",47436]
["2025-03-31","2025-04-04","NW",1,"50A/4","A+B","Y.MEULEWIJK","Y.MELLE","Week","Night","23:55","04:30","Linked to coupure nr 47436 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y Melle\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc"," "," ",47436]
["2025-03-31","2025-04-04","NW",1,"50E","A+B","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG","Week","Night","23:55","04:30","Linked to coupure nr 47436 on line 50 tracks(s) A+B from SCHELLEBELLE to Y.OOST DRIEHOEK LEDEBERG: Vernieuwen Y Melle\r\n* uitgesteld naar 2025","CTL","Minor_AdHoc"," "," ",47436]
["2025-03-31","2025-04-04","SW",1,"75","B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Day","06:00","16:00","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pour la réalisation des fondat","SAVU","Minor_AdHoc","Phase 3.1 – SAVU L75 de jour pendant 4 sem.​\r\nTravaux de jour en semaine 10, 14, 17, 19 et 21 entre 6h et 16h​"," ",61842]
["2025-03-31","2025-04-05","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58731]
["2025-03-31","2025-04-07","SW",1,"96","A+B","MONS","QUEVY-FRONTIERE","AllWeek","Continuous","06:00","04:30","Aménagement de Quévy + OA Chape 71.240 + Chantier SPW Entretien ou Renouvellement PS 65.090\r\nTravaux de finition","CTL","Medium","CTL de 7 jours\r\nLevée de l'ART OA 71.240"," ",53238]
["2025-03-31","2025-04-28","SE",1,"43","A+B","ANGLEUR","TILFF","AllWeek","Night","23:00","05:30","Criblage - contraintes et finitions","CTL","Minor_AdHoc","CTL de nuit min 6h"," ",55766]
["2025-04-04","2025-04-07","SE",1,"24","A+B","Y.GLONS","MONTZEN-FRONTIERE","Weekend","Continuous","23:00","05:00","Entretien","CTL","Medium","ART 2'"," ",51836]
["2025-04-04","2025-04-21","CE",1,"96B","*","FOREST-NORD","FOREST-MIDI-VOIES 920/926","AllWeek","Continuous","23:30","04:00","Vernieuwing van de wissels 12F-11F-10F en 08F in de bundel A te Vorst.\r\nVernieuwing van de sporen 415 en 961 in de bundel A te Vorst.","Autre","Minor_AdHoc","Bundel A sporen 409 tem 416 en sp 961 continu BDS.\r\nTijdens de nachten telkens verlenging van BDS tot sein N941F.II"," ",59156]
["2025-04-04","2025-04-21","NW",1,"50A/3","A+B","DENDERLEEUW","Y.WELLE","AllWeek","Continuous","23:00","04:00","Linked to coupure nr 58620 on line 89 tracks(s) A+B from DENDERLEEUW to BURST: Masterplan Denderleeuw","CTL","High"," "," ",58620]
["2025-04-04","2025-04-21","NW",1,"89","A+B","DENDERLEEUW","BURST","AllWeek","Continuous","23:00","04:00","Masterplan Denderleeuw","CTL","High","Perronsporen IV,V en VI buiten dienst \r\nPerronsporen III,VII en VIII doodsporen \r\nBundel enkel bereikbaar via kant Geraardsbergen \r\n\r\nTijdens de nacht tussen de laatste en eerste reiziergstrein bijkomende TLO L 50"," ",58620]
["2025-04-04","2025-04-28","SE",1,"167","A","Y.AUTELBAS","Y.ATHUS-NORD","AllWeek","Continuous","23:00","05:30","Criblage Autelbas - Athus (y compris)","CTL","High","CTL L167 Autelbas - Athus\r\nVoie A HS en gare d'Athus\r\nART 5 min"," ",55774]
["2025-04-05","2025-04-07","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Weekend","Continuous","05:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\nWEEKEND","CTL","Medium","geen impact L25N!"," ",58738]
["2025-04-05","2025-04-07","SE",1,"139","A+B","SINT-JORIS-WEERT","WAVRE","Weekend","Night","23:00","05:00","Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre \r\ncontraintes, finitions (4)","CTL","Minor_AdHoc",null," ",55773]
["2025-04-07","2025-04-11","SW",1,"117","B","MANAGE","LUTTRE","Week","Day","08:30","15:30","Aménagement de Luttre - phase 2025\r\nPréparations caténaires, T-H.11 > quai IV\r\npose de consoles en tête de faisceau + transfert de la caténaire\r\n+ révision à mi-vie","SAVU","Minor_AdHoc","Le 7/04 + 10-11/04 : VB HS + voie IV de Luttre en garage, entrée et sortie vers Charleroi\r\nLes 8-9/04: VA HS + voie III de Luttre en garage, entrée et sortie vers Charleroi\r\nsectionnement caténaire créé en 2023 entre la transversale nord et le quai de L"," ",56175]
["2025-04-07","2025-04-11","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Week","Night","23:00","04:10","Second tabliers ponts 7,8 et 9 + Renouvellement AS de Lobbes-Garage & Hourpes\r\nNuits de préparation","CTL","Minor_AdHoc",null,"HKM à adapter",56490]
["2025-04-07","2025-04-12","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58732]
["2025-04-07","2025-04-12","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement de chapes – Phase 1 - 39.681 39.749 40.133\r\nPréparations","CTL","Minor_AdHoc",null," ",55511]
["2025-04-07","2025-04-14","SE",1,"161","A/B","NAMUR","GEMBLOUX","AllWeek","Night","23:00","05:00","Travaux caténaires\r\n6- Déroulage Liaisons Namur- Gembloux","CTL","Minor_AdHoc","8 nuits CTL dont 2 nuits de WE de 6h minimum (après point 5)"," ",59619]
["2025-04-07","2025-07-12","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","AllWeek","Night","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers","Autre","Minor_AdHoc","sp 3 BDS"," ",59758]
["2025-04-07","2025-08-24","CE",1,"161","*","SCHAERBEEK","SCHAERBEEK","AllWeek","Continuous","(vide)","(vide)","P149301: Renovatiewerken perron 3 Schaarbeek Reizigers\r\nPerron 3 BDS maar HK kunnen rijden.","Autre","Minor_AdHoc"," "," ",58785]
["2025-04-11","2025-04-14","SW",1,"117","A+B","MANAGE","LUTTRE","Weekend","Continuous","21:50","05:30","Aménagement de Luttre - Phase 2025\r\nWE 1","CTL","Medium","CTL en continu entre TX-H.11 et T-H.11 et K-E.20/KX.E.20 + voies 152/153\r\npossibilité voie III / IV / V en garage\r\nART 3 min"," ",53222]
["2025-04-11","2025-05-19","SE",1,"130","A/B","AUVELAIS","MOUSTIER","Weekend","Night","23:00","05:00","Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais","CTL","Minor_AdHoc","6 we de nuit en CTL minimum 6h"," ",59471]
["2025-04-12","2025-04-14","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Weekend","Continuous","05:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\nWEEKEND","CTL","Medium","geen impact L25N!"," ",58739]
["2025-04-14","2025-04-18","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement de chapes – Phase 1-  39.681 39.749 40.133\r\nPréparations","CTL","Minor_AdHoc",null," ",55512]
["2025-04-14","2025-04-18","SW",1,"75A","A+B","MOUSCRON","MOUSCRON","Week","Day","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.2 - Construction des nouvelles culées et fondations​\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Phase 3.2 – MHS du faisceau de jour​\r\nTravaux de jour en semaine 11, 13, 16, 18 et 20 entre 8h et 16h"," ",61847]
["2025-04-14","2025-04-19","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58733]
["2025-04-14","2025-04-19","SW",1,"117","A+B","MANAGE","LUTTRE","Week","Night","21:50","05:30","Aménagement de Luttre - Phase 2025\r\nNuits préparatoires","CTL","Minor_AdHoc","CTL de nuit"," ",53224]
["2025-04-14","2025-05-23","SW",1,"140","A","LA ROCHE(BRABANT)","TILLY","AllWeek","Continuous","06:00","16:00","Sécurisation des Parois Rocheuses entre La Roche et Tilly (2 parois)","SAVU","High",null," ",55589]
["2025-04-18","2025-04-21","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n7 - Déroulage Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","1 we en continu de SAVU vend 23h au lun 05h + CTL de nuit (après le point 6)"," ",59621]
["2025-04-18","2025-04-22","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","RER - Travaux OA pour la suppression du PN de Lillois\r\nWE de 3jrs en CTL en continu","CTL","Medium","WE de 3jrs en CTL en continu\r\nART à prévoir 6min"," ",54494]
["2025-04-18","2025-04-22","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement de chapes – Phase 1 - 39.681 39.749 40.133","CTL","Medium","ART 2 min pendant 3 semaines"," ",55514]
["2025-04-19","2025-04-20","SW",1,"90C","A+B","JURBISE","BRUGELETTE","Weekend","Continuous","06:00","17:00","Maintenance Z.7.53 P4","CTL","Medium",null," ",56574]
["2025-04-19","2025-04-21","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Weekend","Continuous","05:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\nWEEKEND","CTL","Medium","geen impact L25N!"," ",59311]
["2025-04-21","2025-04-25","CE",1,"50C","A","BRUXELLES-MIDI","ANDERLECHT-GRIL EST","Week","Night","23:40","04:30","Vernieuwen aw 01BJ: voorbereidende werken\r\nVan de perrons 13-14-15 tot inritseinen AL50C en helft buitenrooster\r\nTijdens de nachten uitbreiding naar bundel Gent en 1 sp van L96B","Autre","Minor_AdHoc","Van de perrons 13-14-15 tot inritseinen AL50C en helft buitenrooster\r\nTijdens de nachten uitbreiding naar bundel Gent en 1 sp van L96B",null,59742]
["2025-04-21","2025-04-25","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Week","Night","23:00","04:10","Second tabliers ponts 7,8 et 9 + Renouvellement AS de Lobbes-Garage & Hourpes\r\nNuits de préparation","CTL","Minor_AdHoc",null,"HKM à adapter",53455]
["2025-04-21","2025-04-25","SW",1,"75","B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Day","06:00","16:00","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pour la réalisation des fondat","SAVU","Minor_AdHoc","Phase 3.1 – SAVU L75 de jour pendant 4 sem.​\r\nTravaux de jour en semaine 10, 14, 17, 19 et 21 entre 6h et 16h​"," ",61843]
["2025-04-21","2025-04-25","SW",1,"94","A+B","ATH","LEUZE","Week","Night","22:30","04:30","Travaux de construction d'un PI au droit du km 53.560 en vue de la suppression du PN30 + renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\nNuits de préparation pour le ripage du pont-cadre + le renforcement des P","CTL","Minor_AdHoc"," "," ",55546]
["2025-04-21","2025-04-25","SW",1,"94","A+B","TOURNAI","BLANDAIN-FRONTIERE","Week","Night","22:40","05:50","Travaux de renouvellement du PI 87.005 et de suppression du PN2 par la construction d'un nouveau pont-cadre.\r\nNuits de préparation","CTL","Minor_AdHoc"," "," ",55550]
["2025-04-21","2025-04-26","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58734]
["2025-04-21","2025-05-03","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n8 - Réalisation de massifs et pose de poteaux\r\n9 - Pose de traverses Namur -Gembloux","SAVU_CTRL","Minor_AdHoc","1 semaines SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 7)\r\n1semaines SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 8)"," ",59622]
["2025-04-22","2025-04-26","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement de chapes – Phase 1 - 39.681 39.749 40.133\r\nCTL nuit soudures","CTL","Minor_AdHoc",null," ",55515]
["2025-04-22","2025-05-12","SW",1,"140","A+B","OTTIGNIES","FLEURUS","AllWeek","Continuous","23:00","05:00","ART 2 min\r\nRenouvellement de chapes – Phase 1-  39.681 39.749 40.133","ART","Minor_AdHoc",null," ",59518]
["2025-04-25","2025-04-26","SE",1,"166","A/B","VONECHE","PALISEUL","Week","Day","06:00","06:00","Renouvellement de traverses par P93 - Phase 1 - WE 1\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu ven 25/04 6h00 au sam 26/04 06h00 (avec max 4 trains/h)","HKM à adapter",56524]
["2025-04-25","2025-04-28","CE",1,"50C","A","BRUXELLES-MIDI","ANDERLECHT-GRIL EST","Weekend","Continuous","23:40","04:30","Vernieuwen aw 01BJ\r\nVan de perrons 13-14-15 tot inritseinen AL50C en helft buitenrooster\r\nTijdens de nachten uitbreiding naar bundel Gent en 1 sp van L96B","Autre","Minor_AdHoc","Van de perrons 13-14-15 tot inritseinen AL50C en helft buitenrooster\r\nTijdens de nachten uitbreiding naar bundel Gent en 1 sp van L96B",null,59741]
["2025-04-25","2025-04-28","SW",1,"130","A/B","LE CAMPINAIRE","CHATELET","Weekend","Continuous","23:10","05:10","Réélectrification L130\r\nTir caténaires","SAVU","Minor_AdHoc","SAVU de Weekend en continu voie A/B"," ",54820]
["2025-04-25","2025-04-28","SW",1,"94","A+B","ATH","LEUZE","Weekend","Continuous","22:30","04:30","Travaux de construction d'un PI au droit du km 53.560 en vue de la suppression du PN30 + renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\nCTL de WE en continu pour le ripage du pont-cadre + le renforcement des P","CTL","Medium"," "," ",55542]
["2025-04-25","2025-04-28","SW",1,"94","A+B","TOURNAI","BLANDAIN-FRONTIERE","Weekend","Continuous","22:00","06:00","Travaux de renouvellement du PI 87.005 et de suppression du PN2 par la construction d'un nouveau pont-cadre.\r\nCTL de WE en continu pour le ripage du pont-cadre.","CTL","Medium"," "," ",55556]
["2025-04-25","2025-05-05","SE",1,"161","A+B","OTTIGNIES","WATERMAEL","AllWeek","Continuous","23:30","04:50","Travaux RER\r\nDossier de concertation validé en octobre 2022","CTL","High","ART 4' pdt 1sem après la fin des travaux"," ",56444]
["2025-04-25","2025-05-12","NW",1,"59","A+B","Y.BERNADETTESTRAAT","GENT-DAMPOORT","AllWeek","Continuous","23:00","04:00","Werken in bundelkop bundel E\r\n\r\nVoor de zichtbaarheid ingegeven  op lijn 59.\r\n\r\nDe hinder beperkt zich echter tot de bundelkop van bundel E","Autre","Minor_AdHoc"," "," ",58623]
["2025-04-25","2025-05-12","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","AllWeek","Continuous","23:00","04:10","Rnvlt AS Lobbes-Garage : Construction MDS + élargissement plateforme\r\nSecond tabliers ponts 7,8 et 9\r\nCTL 17 jours continu","CTL","High","CTL L130A 17 jours (congés scolaires FWB)\r\nART stabilisation 5 minutes","HKM à adapter",53234]
["2025-04-25","2025-05-28","SE",1,"166","A+B","VONECHE","PALISEUL","AllWeek","Continuous","08:30","22:00","ART 5'\r\nRenouvellement de traverses par P93","ART","Minor_AdHoc","ART de stabilisation en voie B - vitesse 80 km/h\r\nBK45680 à 53690\r\nMise en vigueur: 25/04/25\r\nFin probable: 28/05/25",null,59612]
["2025-04-26","2025-04-28","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","00:01","04:00","Vernieuwing Ballast & Dwaarsliggers","CTL","Medium","BTS 40km/h -  wordt nog berekend."," ",57974]
["2025-04-26","2025-04-28","SE",1,"166","A+B","VONECHE","PALISEUL","Weekend","Continuous","06:00","04:30","Renouvellement de traverses par P93 - Phase 1 - WE 1\r\nDossier de concertation octobre 2022","CTL","Medium",null,"HKM à adapter",56520]
["2025-04-27","2025-05-05","SW",1,"118","A+B","MONS","Y.LA PAIX","AllWeek","Continuous","04:00","04:30","Mise en service SIMIS-W entre Mons et Obourg (gare incluse).","CTL","High","CTL 7 jours"," ",61394]
["2025-04-28","2025-04-28","SE",1,"166","A/B","VONECHE","PALISEUL","Week","Day","04:30","16:30","Renouvellement de traverses par P93 - Phase 1 - WE 1\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu lun 28/04 04h30 à 16h30 (avec max 4 trains/h)","HKM à adapter",61879]
["2025-04-28","2025-05-02","SW",1,"75A","A+B","MOUSCRON","MOUSCRON","Week","Day","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.2 - Construction des nouvelles culées et fondations​\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Phase 3.2 – MHS du faisceau de jour​\r\nTravaux de jour en semaine 11, 13, 16, 18 et 20 entre 8h et 16h"," ",61848]
["2025-04-28","2025-05-03","CE",1,"50C","A","BRUXELLES-MIDI","ANDERLECHT-GRIL EST","Week","Night","23:40","04:30","Vernieuwen aw 01BJ: voorbereidende werken\r\nVan de perrons 13-14-15 tot inritseinen AL50C en helft buitenrooster\r\nTijdens de nachten uitbreiding naar bundel Gent en 1 sp van L96B","Autre","Minor_AdHoc","Van de perrons 13-14-15 tot inritseinen AL50C en helft buitenrooster\r\nTijdens de nachten uitbreiding naar bundel Gent en 1 sp van L96B",null,59743]
["2025-04-28","2025-05-03","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58735]
["2025-04-28","2025-05-03","SW",1,"78","A+B","BLATON","TOURNAI","Week","Night","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) + traverses biblocs - Phase 2\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc",null," ",53248]
["2025-04-28","2025-05-03","SW",1,"94","A+B","ATH","LEUZE","Week","Night","22:30","04:30","Travaux de construction d'un PI au droit du km 53.560 en vue de la suppression du PN30 + renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\nNuits de finitions","CTL","Minor_AdHoc"," "," ",55547]
["2025-04-28","2025-05-03","SW",1,"94","A+B","TOURNAI","BLANDAIN-FRONTIERE","Week","Night","22:40","05:50","Travaux de renouvellement du PI 87.005 et de suppression du PN2 par la construction d'un nouveau pont-cadre.\r\nNuits de finitions suite au ripage du pont-cadre","CTL","Minor_AdHoc","ART 2 min"," ",55551]
["2025-04-28","2025-05-09","SE",1,"125A","A/B","FLEMALLE-ANNEXE","SERAING","AllWeek","Continuous","06:00","22:00","Renouvellement de traverses","SAVU","High","Du 28/04 au 5/05 : Voie A HS - en gare de Flémalle Annexe y compris\r\nDu 1/05 au 9/05 : Voie B HS - en gare de Flémalle Annexe y compris\r\nCTL du 1 au 5 mai (id 55797)\r\nART 1min"," ",55796]
["2025-04-30","2025-05-05","SE",1,"165","A+B","Y.AUBANGE","ATHUS","AllWeek","Continuous","23:00","05:00","Linked to coupure nr 56495 on line 167 tracks(s) A+B from Y.AUTELBAS to ATHUS-FRONTIERE: Massification\r\nOA: Renouvellement PS bK 213.548 - commun avec L165 - bK 141.744","CTL","Medium"," ","HKM à adapter",56495]
["2025-04-30","2025-05-05","SE",1,"167","A+B","Y.AUTELBAS","ATHUS-FRONTIERE","AllWeek","Continuous","23:00","05:00","Massification\r\nOA: Renouvellement PS bK 213.548 - commun avec L165 - bK 141.744","CTL","Medium","Gare d'Athus incluse\r\n+ L165 fermée en gare d'Athus\r\nOA a besoin de 4 jours CTL continu obligatoires\r\nSignalling: réalisation de traversée de voie et implantation des signaux pour reprise en PLP (besoin de 7jours en continu) mais pas besosin de la gare ","HKM à adapter",56495]
["2025-05-01","2025-05-05","SE",1,"125A","B","FLEMALLE-ANNEXE","SERAING","AllWeek","Continuous","06:00","05:00","Renouvellement de traverses\r\nRq 333 : rq suite semestrielle \r\nReplan hors CTL L36 NE","CTL","Medium",null," ",55797]
["2025-05-02","2025-05-03","SE",1,"166","A/B","VONECHE","PALISEUL","Week","Day","06:00","06:00","Renouvellement de traverses par P93 - Phase 1 - WE 2\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu ven 02/05 6h00 au sam 03/05 06h (avec max 4 trains/h)​","HKM à adapter",56523]
["2025-05-02","2025-05-05","NW",1,"75","A+B","Y.BETHUNE","MOUSCRON","Weekend","Continuous","23:10","04:00","Onderhoud","CTL","Medium"," "," ",59352]
["2025-05-02","2025-05-05","SE",1,"167","A","Y.AUTELBAS","Y.ATHUS-NORD","Weekend","Continuous","23:00","05:30","Criblage Autelbas - Athus (y compris) - Contraintes finitions","CTL","Medium","CTL L167 Autelbas - Athus\r\nVoie A HS en gare d'Athus"," ",55775]
["2025-05-02","2025-05-05","SW",1,"130","A/B","LE CAMPINAIRE","CHATELET","Weekend","Continuous","23:10","05:10","Réélectrification L130\r\nTir caténaires","SAVU","Minor_AdHoc",null," ",54821]
["2025-05-03","2025-05-05","NE",1,"25","A","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Weekend","Continuous","05:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nenkel sp A --> Mechelen perronspoor A tot Mechelen Dijkstraat --> invloed L25N --> komt op 1 spoor te Nekkerspoel\r\nzie schets 'expl A-L25' (tabblad schet","CTL","Medium","impact L25N ? --> komt op 1 spoor te Nekkerspoel"," ",58740]
["2025-05-03","2025-05-05","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","00:01","04:00","Vernieuwing Ballast & Dwaarsliggers","CTL","Medium","BTS 40km/h -  wordt nog berekend."," ",57975]
["2025-05-03","2025-05-05","SE",1,"166","A+B","VONECHE","PALISEUL","Weekend","Continuous","06:00","04:30","Renouvellement de traverses par P93 - Phase 1 - WE 2\r\nDossier de concertation octobre 2022","CTL","Medium",null,"HKM à adapter",56521]
["2025-05-05","2025-05-05","SE",1,"166","A/B","VONECHE","PALISEUL","Week","Day","04:30","16:30","Renouvellement de traverses par P93 - Phase 1 - WE 2\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu lun 28/04 04h30 à 16h30 (avec max 4 trains/h)","HKM à adapter",56522]
["2025-05-05","2025-05-09","SW",1,"130","A+B","AISEAU","CHATELET-GRIL EST","Week","Night","22:30","05:00","Semaines de nuits de préparations - démolition 85.708","CTL","Minor_AdHoc"," "," ",55905]
["2025-05-05","2025-05-09","SW",1,"75","B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Day","06:00","16:00","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pour la réalisation des fondat","SAVU","Minor_AdHoc","Phase 3.1 – SAVU L75 de jour pendant 4 sem.​\r\nTravaux de jour en semaine 10, 14, 17, 19 et 21 entre 6h et 16h​"," ",61844]
["2025-05-05","2025-05-09","SW",1,"78","A+B","BLATON","TOURNAI","Week","Night","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) + traverses biblocs - Phase 2\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc",null," ",61835]
["2025-05-05","2025-05-10","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58736]
["2025-05-05","2025-05-10","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement de chapes – Phase 1 - 39.681 39.749 40.133\r\nfinitions","CTL","Minor_AdHoc",null," ",55521]
["2025-05-05","2025-05-10","SW",1,"94","A+B","ATH","LEUZE","Week","Night","22:30","04:30","Travaux de construction d'un PI au droit du km 53.560 en vue de la suppression du PN30 + renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\nNuits de finitions + enlèvement de l'ART","CTL","Minor_AdHoc"," "," ",55548]
["2025-05-05","2025-05-10","SW",1,"94","A+B","TOURNAI","BLANDAIN-FRONTIERE","Week","Night","22:40","05:50","Travaux de renouvellement du PI 87.005 et de suppression du PN2 par la construction d'un nouveau pont-cadre.\r\nNuits de finitions suite au ripage du pont-cadre","CTL","Minor_AdHoc","ART 2 min"," ",55552]
["2025-05-05","2025-05-12","SE",1,"161","A+B","WATERMAEL","OTTIGNIES","AllWeek","Continuous","04:50","05:00","ART stab 4min\r\nTravaux RER\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","Stabilisation suite CTL"," ",58405]
["2025-05-05","2025-05-28","CE",1,"27","A","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 59746 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: voorbereidende werken afbraak deel 3+4","SAVU","Minor_AdHoc"," "," ",59746]
["2025-05-05","2025-05-28","CE",1,"27D","S","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 59746 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: voorbereidende werken afbraak deel 3+4","CTL","Minor_AdHoc"," "," ",59746]
["2025-05-05","2025-05-28","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","Week","Night","23:40","04:30","Linked to coupure nr 59746 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: voorbereidende werken afbraak deel 3+4","CTL","Minor_AdHoc"," "," ",59746]
["2025-05-05","2025-05-30","SW",1,"94","*","Y.LE COUCOU","ATH","AllWeek","Continuous","06:00","16:00","Renouvellement des AS à Ath dans le faisceau","Autre","Minor_AdHoc","Voie 207 à 211 HS en continu\r\nVoies 5 et 6 en protection (28535-539-543)\r\nde 7h à 17h"," ",53242]
["2025-05-09","2025-05-10","SE",1,"166","A/B","VONECHE","PALISEUL","Week","Day","06:00","06:00","Renouvellement de traverses par P93 - Phase 1 - WE 3\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu ven 09/05 6h00 au sam 10/05 06h (avec max 4 trains/h)","HKM à adapter",56527]
["2025-05-09","2025-05-12","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Night","23:00","05:00","Travaux caténaires\r\n10 - Déroulage liaisons Namur- Gembloux","CTL","Minor_AdHoc","3 nuits de CTL Ven^sam sam^dim et dim^lun (minimum 6h d'amplitude) (après le point 09)"," ",59623]
["2025-05-09","2025-05-12","SE",1,"161","A+B","WATERMAEL","OTTIGNIES","AllWeek","Continuous","23:30","05:00","Travaux RER: WE Finitions \r\nDossier de concertation validé en octobre 2022","CTL","Medium","ART de stabilisation de 2' : 12/05 - 19/05"," ",58403]
["2025-05-09","2025-05-12","SE",1,"167","A","Y.AUTELBAS","Y.ATHUS-NORD","Weekend","Continuous","23:00","05:30","Criblage Autelbas - Athus (y compris) - Contraintes finitions","CTL","Medium","CTL L167 Autelbas - Athus\r\nVoie A HS en gare d'Athus"," ",55776]
["2025-05-09","2025-05-12","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER\r\nRq 333 : Rq Ef's suite semestrielle : Nok in combinatie met werken L36 en L12\r\nRéunion 27/09 : WE à proposer par I-CBE","CTL","Medium","ART stabilisation 2 minutes"," ",54942]
["2025-05-09","2025-05-12","SW",1,"130","A/B","LE CAMPINAIRE","CHATELET","Weekend","Continuous","23:10","05:10","Réélectrification L130\r\nTir caténaires","SAVU","Minor_AdHoc",null," ",54822]
["2025-05-09","2025-05-12","SW",1,"78","A/B","SAINT-GHISLAIN","TOURNAI","Weekend","Continuous","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) - Phase 2\r\nDossier de concertation validé en octobre 2022","CTL","Medium","ART stabilisation (60) : du 19/05/25 5h au 26/05 5H VB + du 26/05 5h au 02/06/2025 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",59447]
["2025-05-09","2025-06-23","SW",1,"97","A+B","SAINT-GHISLAIN","QUIEVRAIN","Weekend","Continuous","22:30","04:30","Renouvellement des AS de Saint-Ghislain/Quiévrain + PN 127&128 + Travaux OA Chape PI 55.405 (durant WE 31/5-1/6 + préparations et finitions)","CTL","Minor_AdHoc","5 WE en CTL (10-11/5, 17-18/5, 31-1/6, 7-8/6, 21-22/6)\r\nSemaine de nuit en CTL : 12-16/5, 26-30/5, 2-6/6 et 16-20/6.\r\nAccès aux voies en gare possible en cul de sac\r\nAccès faisceau Saint Ghislain impossible durant du 09/05 au 19/05 (côté Quiévrain)\r\nART"," ",53258]
["2025-05-10","2025-05-12","NE",1,"12","A+B","ESSEN-GRENS","Y.LUCHTBAL","Weekend","Continuous","01:00","04:00","Onderhoud\r\n\r\nweekend verplaatst door trilateraal overleg","CTL","Medium","Geen verkeer mogen van/naar Roosendaal"," ",59607]
["2025-05-10","2025-05-12","NE",1,"12/1","A+B","Y.DRIEHOEKSTRAAT","Y.SINT-MARIABURG","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59607 on line 12 tracks(s) A+B from ESSEN-GRENS to Y.LUCHTBAL: Onderhoud\r\n\r\nweekend verplaatst door trilateraal overleg","CTL","Medium"," "," ",59607]
["2025-05-10","2025-05-12","NE",1,"25","A","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Weekend","Continuous","05:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nenkel sp A --> Mechelen perronspoor A tot Mechelen Dijkstraat --> invloed L25N --> komt op 1 spoor te Nekkerspoel\r\nzie schets 'expl A-L25' (tabblad schet","CTL","Medium","impact L25N ? --> komt op 1 spoor te Nekkerspoel"," ",58741]
["2025-05-10","2025-05-12","NE",1,"27","A+B","Y.HAREN-NORD","VILVOORDE","Weekend","Continuous","00:01","04:00","Werken Viaduct Vilvoorde (AWV)","CTL","Medium"," "," ",58706]
["2025-05-10","2025-05-12","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","00:01","04:00","Vernieuwing Ballast & Dwaarsliggers","CTL","Medium","BTS 40km/h -  wordt nog berekend."," ",57976]
["2025-05-10","2025-05-12","NW",1,"51","A+B","BRUGGE","Y.BLAUWE TOREN","Weekend","Continuous","06:00","04:00","Plaatsen nieuwe brugdekvoeg en steunmuur Brug Blankenbergsesteenweg \r\nVerhoogd talud bouwen thv KP 96.400","CTL","Medium","Geen verkeer richting Knokke-Blankenberge en Zeebrugge mogelijk","Info Racc.",56100]
["2025-05-10","2025-05-12","SE",1,"166","A+B","VONECHE","PALISEUL","Weekend","Continuous","06:00","04:30","Renouvellement de traverses par P93 - Phase 1 - WE 3\r\nDossier de concertation octobre 2022","CTL","Medium",null,"HKM à adapter",56525]
["2025-05-12","2025-05-12","SE",1,"166","A/B","VONECHE","PALISEUL","Week","Day","04:30","16:30","Renouvellement de traverses par P93 - Phase 1 - WE 3\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu lun 12/05 04h30 à 16h30 (avec max 4 trains/h)","HKM à adapter",56537]
["2025-05-12","2025-05-16","SE",1,"125A","A/B","FLEMALLE-ANNEXE","SERAING","Week","Day","08:00","05:00","Renouvellement de traverses \r\nContraintes et finitions","SAVU","Minor_AdHoc","Voie en gare de Flémalle Annexe y compris"," ",55798]
["2025-05-12","2025-05-16","SW",1,"117","A+B","MANAGE","LUTTRE","Week","Night","21:50","05:30","Aménagement de Luttre - Phase 2025\r\nNuits préparatoires","CTL","Minor_AdHoc","CTL de nuit"," ",53225]
["2025-05-12","2025-05-16","SW",1,"130","A+B","AISEAU","CHATELET-GRIL EST","Week","Night","22:30","05:00","Semaines de nuits de préparations - démolition 85.708","CTL","Minor_AdHoc"," "," ",55902]
["2025-05-12","2025-05-16","SW",1,"75A","A+B","MOUSCRON","MOUSCRON","Week","Day","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.2 - Construction des nouvelles culées et fondations​\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Phase 3.2 – MHS du faisceau de jour​\r\nTravaux de jour en semaine 11, 13, 16, 18 et 20 entre 8h et 16h"," ",61849]
["2025-05-12","2025-05-17","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58737]
["2025-05-12","2025-05-17","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n11 - Pose de traverses Namur -Gembloux","SAVU_CTRL","Minor_AdHoc","1 semaines SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 10)"," ",59624]
["2025-05-12","2025-05-17","SE",1,"40A","A+B","Y.GARDE-DIEU","Y.VAL-BENOIT","Week","Night","22:00","05:00","Linked to coupure nr 60141 on line 37 tracks(s) A+B from ANGLEUR to LIEGE-GUILLEMINS: Criblage du ballast entre Y Val Benoît et Y Aguesses\r\nBourrage de révision, finitions,... de la voie A\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc"," ","via NK",60141]
["2025-05-12","2025-05-19","CE",1,"26","B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","AllWeek","Continuous","04:00","04:00","BTS bij indienstname sp B na Fase 2.","ART","Minor_AdHoc","BTS"," ",51878]
["2025-05-12","2025-05-19","SE",1,"161","A+B","OTTIGNIES","WATERMAEL","AllWeek","Continuous","05:00","05:00","ART 2min\r\nTravaux RER\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc"," "," ",56445]
["2025-05-12","2025-05-23","SW",1,"78","A/B","BLATON","Y.MAUBRAY","AllWeek","Continuous","05:00","22:50","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) - Phase 2\r\nDossier de concertation validé en octobre 2022","SAVU_CTRL","High","SAVU + CTL nuit (22h50-05h00) + CTL weekend\r\nVB HS du 12/05 5h au 19/05 5h\r\nVA HS du 19/05 5h au 26/05 5h\r\nART stabilisation (60) : du 19/05/25 5h au 26/05 5H VB + du 26/05 5h au 02/06/2025 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",56093]
["2025-05-12","2025-06-30","CE",1,"26","A/B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","AllWeek","Continuous","04:00","04:00","Nieuwe brug thv de Carsoelstraat te Ukkel: Fase 3\r\nAfwerking toegangstrappen, aanleg nieuwe perrons, toegangshellingen.","SAVU","High","DOES tussen Trapezium Linkebeek en Y Watermaal, afwisselend spoor A of B naargelang evolutie van de Werf\r\nBIP op perrons St Job"," ",51877]
["2025-05-16","2025-05-17","SE",1,"166","A/B","VONECHE","PALISEUL","Week","Day","06:00","06:00","Renouvellement de traverses par P93 - Phase 1 - WE 4\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu ven 16/05 6h00 au sam 17/05 06h (avec max 4 trains/h)","HKM à adapter",56528]
["2025-05-16","2025-05-19","SE",1,"166","A+B","Y.NEFFE","GENDRON-CELLES","Weekend","Continuous","23:00","04:30","Maintenance, renouvellement de traverses au niveau du viaduc d’Anseremme.","CTL","Medium","CTL entre Dinant (Sg MX-W.30/M-W.30)  et Gendron\r\nART de stabilisation de 5 jours (date de fin probable le 24/5).\r\nART de 3 minutes","HKM à adapter",56544]
["2025-05-16","2025-05-19","SE",1,"167","A","Y.AUTELBAS","Y.ATHUS-NORD","Weekend","Continuous","23:00","05:30","Criblage Autelbas - Athus (y compris) - Contraintes finitions","CTL","Medium","CTL L167 Autelbas - Athus\r\nVoie A HS en gare d'Athus"," ",55777]
["2025-05-16","2025-05-19","SE",1,"24","A+B","Y.GLONS","Y.VISE-HAUT","Weekend","Continuous","23:00","05:00","Linked to coupure nr 55214 on line 34 tracks(s) A+B from TONGEREN to GLONS: Entretien manuel et mécanisés des AW de Y. Glons, Bassenge, Visé-Haut \r\nEntretien manuel et mécanisés de la voie courante","CTL","Medium"," "," ",55214]
["2025-05-16","2025-05-19","SE",1,"24/2","A+B","VISE-HAUT","Y.LONGCHAMPS","Weekend","Continuous","23:00","05:00","Linked to coupure nr 55214 on line 34 tracks(s) A+B from TONGEREN to GLONS: Entretien manuel et mécanisés des AW de Y. Glons, Bassenge, Visé-Haut \r\nEntretien manuel et mécanisés de la voie courante","CTL","Medium"," "," ",55214]
["2025-05-16","2025-05-19","SE",1,"34","A+B","TONGEREN","GLONS","Weekend","Continuous","23:00","05:00","Entretien manuel et mécanisés des AW de Y. Glons, Bassenge, Visé-Haut \r\nEntretien manuel et mécanisés de la voie courante","CTL","Medium","L24 + L24/2 + L34"," ",55214]
["2025-05-16","2025-05-19","SW",1,"117","A+B","MANAGE","LUTTRE","Weekend","Continuous","21:50","05:30","Aménagement de Luttre - Phase 2025\r\nWE 2","CTL","Medium","CTL en continu"," ",53228]
["2025-05-16","2025-05-19","SW",1,"130","A/B","LE CAMPINAIRE","CHATELET","Weekend","Continuous","23:10","05:10","Réélectrification L130\r\nTir caténaires","SAVU","Minor_AdHoc",null," ",54823]
["2025-05-16","2025-05-19","SW",1,"130","A+B","TAMINES","CHATELET-GRIL OUEST","Weekend","Continuous","23:00","05:00","Maintenance Z15. 51 P4+\r\n+ Démolition 85.708","CTL","Medium","ART stab 2 min"," ",53524]
["2025-05-16","2025-05-19","SW",1,"78","A/B","SAINT-GHISLAIN","TOURNAI","Weekend","Continuous","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) - Phase 2\r\nDossier de concertation validé en octobre 2022","CTL","Medium","ART stabilisation (60) : du 19/05/25 5h au 26/05 5H VB + du 26/05 5h au 02/06/2025 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",59448]
["2025-05-17","2025-05-19","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","00:01","04:00","Vernieuwing Ballast & Dwaarsliggers","CTL","Medium","BTS 40km/h -  wordt nog berekend."," ",57977]
["2025-05-17","2025-05-19","SE",1,"166","A+B","VONECHE","PALISEUL","Weekend","Continuous","06:00","04:30","Renouvellement de traverses par P93 - Phase 1 - WE 4\r\nDossier de concertation octobre 2022","CTL","Medium",null,"HKM à adapter",56526]
["2025-05-19","2025-05-19","SE",1,"166","A/B","VONECHE","PALISEUL","Week","Day","04:30","16:30","Renouvellement de traverses par P93 - Phase 1 - WE 4\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu lun 19/05 04h30 à 16h30 (avec max 4 trains/h)","HKM à adapter",56538]
["2025-05-19","2025-05-23","SW",1,"75","B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Day","06:00","16:00","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pour la réalisation des fondat","SAVU","Minor_AdHoc","Phase 3.1 – SAVU L75 de jour pendant 4 sem.​\r\nTravaux de jour en semaine 10, 14, 17, 19 et 21 entre 6h et 16h​"," ",61845]
["2025-05-19","2025-05-24","SE",1,"40A","A+B","Y.GARDE-DIEU","Y.VAL-BENOIT","Week","Night","22:00","05:00","Linked to coupure nr 60142 on line 37 tracks(s) A+B from LIEGE-GUILLEMINS to ANGLEUR: Criblage du ballast entre Y Val Benoît et Y Aguesses\r\nBourrage de révision, finitions,... de la voie B\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc"," ","via NK",60142]
["2025-05-19","2025-05-24","SW",1,"117","A+B","MANAGE","LUTTRE","Week","Night","21:50","05:30","Aménagement de Luttre - Phase 2025\r\nNuits préparatoires","CTL","Minor_AdHoc","CTL de nuit"," ",53226]
["2025-05-19","2025-05-24","SW",1,"90C","A+B","JURBISE","Y.LENS","AllWeek","Continuous","09:00","05:00","Jurbise - Voies III - IV -V + appareils -  bourrage de révisions et contraintes","CTL","Medium"," "," ",39087]
["2025-05-19","2025-06-02","SW",1,"130","A+B","TAMINES","CHATELET-GRIL OUEST","AllWeek","Continuous","05:00","05:00","ART 2 min","ART","Minor_AdHoc","ART stab 2 min"," ",59462]
["2025-05-19","2025-06-02","SW",1,"78","A/B","BLATON","TOURNAI","AllWeek","Continuous","05:00","05:00","ART 4 min\r\nBlaton - Y.Maubray : Renouvellement ballast C75 (2x7km) - Phase 2\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART stabilisation (60) : du 19/05/25 5h au 26/05 5H VB + du 26/05 5h au 02/06/2025 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",61837]
["2025-05-19","2025-07-05","SE",1,"130","A/B","AUVELAIS","MOUSTIER","Week","Night","23:00","05:00","Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais","SAVU","Minor_AdHoc","7 semaines de nuit en SAVU"," ",59472]
["2025-05-20","2025-05-24","SE",1,"166","A/B","VONECHE","PALISEUL","Week","Night","23:00","05:30","Renouvellement de traverses par P93 - Phase 1 - Finitions\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu de nuits en semaine de 23h00 à 05h30 du 20 au 24/05"," ",56038]
["2025-05-23","2025-05-26","CE",1,"161","A/B","WATERMAEL","BAKENBOS","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59173]
["2025-05-23","2025-05-26","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Night","23:00","05:00","Travaux caténaires\r\n12 - Déroulage liaisons Namur- Gembloux","CTL","Minor_AdHoc","3 nuits de CTL Ven^sam sam^dim et dim^lun (minimum 6h d'amplitude) (après le point 11)"," ",59625]
["2025-05-23","2025-05-26","SE",1,"161","A+B","OTTIGNIES","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER\r\nGare Ottignies","Autre","Minor_AdHoc","voies 4 et 5 à quai HS\r\n+ Voie 3 à quai inaccessible côté Bruxelles\r\nVoie 142 HS \r\nPas de lien L161-L139 et L161-L140. PED SNCB inaccessible. Circulation L161 vers Namur à contrevoie en gare"," ",59177]
["2025-05-23","2025-05-26","SE",1,"167","A","Y.AUTELBAS","Y.ATHUS-NORD","Weekend","Continuous","23:00","05:30","Criblage Autelbas - Athus (y compris) - Contraintes finitions","CTL","Medium","CTL L167 Autelbas - Athus\r\nVoie A HS en gare d'Athus"," ",55778]
["2025-05-23","2025-05-26","SW",1,"78","A/B","SAINT-GHISLAIN","TOURNAI","Weekend","Continuous","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) - Phase 2\r\nDossier de concertation validé en octobre 2022","CTL","Medium","ART stabilisation (60) : du 19/05/25 5h au 26/05 5H VB + du 26/05 5h au 02/06/2025 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",59449]
["2025-05-24","2025-05-26","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","00:01","04:00","Vernieuwing Ballast & Dwaarsliggers","CTL","Medium","BTS 40km/h -  wordt nog berekend."," ",57978]
["2025-05-26","2025-05-31","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Week","Night","23:00","05:00","Linked to coupure nr 58428 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\n(zie ook schets 'expl L25&L25N')","CTL","Minor_AdHoc"," "," ",58428]
["2025-05-26","2025-05-31","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n13 - Pose métalliques","CTL","Minor_AdHoc","1 semaine SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 12)"," ",59626]
["2025-05-26","2025-05-31","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement de chapes - 36.363 38.279\r\nPréparations","CTL","Minor_AdHoc",null," ",55523]
["2025-05-26","2025-05-31","SW",1,"78","A+B","BLATON","TOURNAI","Week","Night","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) + traverses biblocs - Phase 2\r\nTravaux finition (2 semaines)\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","ART stabilisation (60) : du 19/05/25 5h au 26/05 5H VB + du 26/05 5h au 02/06/2025 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",56095]
["2025-05-26","2025-05-31","SW",1,"94","A+B","HALLE","ENGHIEN","Week","Night","23:10","04:40","Nuits de préparation - Construction d'un PI - PN16","CTL","Minor_AdHoc","CTL de nuits de semaine"," ",55581]
["2025-05-26","2025-06-02","SW",1,"117","A+B","MANAGE","LUTTRE","AllWeek","Continuous","06:00","05:00","Aménagement de Luttre - Phase 2025\r\nCTL 1 semaine","CTL","Medium","CTL en continu\r\nART stab 3 min"," ",54153]
["2025-05-26","2025-06-07","SW",1,"130","A","LE CAMPINAIRE","CHATELET-GRIL OUEST","Week","Night","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Coupure type 10 - voir dossier\r\nAmplitude 6h\r\nSAVU VA HS","Aperam accéssible uniquement en diesel coté Charleroi",55166]
["2025-05-28","2025-05-31","CE",1,"26B","B","Y.PONT-DE-LA-SENNE","SCHAERBEEK","AllWeek","Continuous","23:40","04:30","Linked to coupure nr 50120 on line 36N tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.DIEGEM: Vernieuwing Albertbrug fase 1.1: afbraak brugdeel 3 + Vervangen assentellersysteem zone H","SAVU","Minor_AdHoc"," "," ",50120]
["2025-05-29","2025-06-02","CE",1,"25","A+B","BRUXELLES-NORD","VILVOORDE","AllWeek","Continuous","00:15","04:00","Linked to coupure nr 59140 on line 36N tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.DIEGEM: Vervangen assentellersysteem zone H FSR.","Autre","Minor_AdHoc"," "," ",59140]
["2025-05-29","2025-06-02","CE",1,"27","A+B","BRUXELLES-NORD-GRIL F","VILVOORDE","AllWeek","Continuous","00:15","04:00","Linked to coupure nr 59140 on line 36N tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.DIEGEM: Vervangen assentellersysteem zone H FSR.","Autre","Minor_AdHoc"," "," ",59140]
["2025-05-29","2025-06-02","CE",1,"27D","A+B","BRUXELLES-NORD-GRIL F","Y.SCHAERBEEK-CARWASH","AllWeek","Continuous","00:15","04:00","Linked to coupure nr 59140 on line 36N tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.DIEGEM: Vervangen assentellersysteem zone H FSR.","Autre","Minor_AdHoc"," "," ",59140]
["2025-05-29","2025-06-02","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","AllWeek","Continuous","00:15","04:00","Linked to coupure nr 59140 on line 36N tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.DIEGEM: Vervangen assentellersysteem zone H FSR.","Autre","Minor_AdHoc"," "," ",59140]
["2025-05-30","2025-06-02","SE",1,"161","B","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59166]
["2025-05-30","2025-06-02","SE",1,"167","A","Y.AUTELBAS","Y.ATHUS-NORD","Weekend","Continuous","23:00","05:30","Criblage Autelbas - Athus (y compris) - Contraintes finitions","CTL","Medium","CTL L167 Autelbas - Athus\r\nVoie A HS en gare d'Athus"," ",56489]
["2025-05-30","2025-06-10","NW",1,"90","A+B","DENDERLEEUW","Y.NEDERBOELARE","AllWeek","Continuous","23:30","04:20","ETCS L2 -IL_ NW_P038_01_L90_Geraardsbergen-Ninove_IL \r\nIndienststelling, meewerken niet mogelijk","CTL","High"," "," ",56107]
["2025-05-31","2025-06-02","CE",1,"26B","B","Y.PONT-DE-LA-SENNE","SCHAERBEEK","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59132 on line 36 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.DIEGEM: Vernieuwing Albertbrug fase 1.2: afbraak brugdeel 4 boven L27D/L27F/L36/AL27 + Vervangen assentellersysteem zone H","SAVU","Minor_AdHoc"," "," ",59132]
["2025-05-31","2025-06-02","CE",1,"27","A","BRUXELLES-NORD-GRIL F","Y.SCHAERBEEK-GROUPE G","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59132 on line 36 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.DIEGEM: Vernieuwing Albertbrug fase 1.2: afbraak brugdeel 4 boven L27D/L27F/L36/AL27 + Vervangen assentellersysteem zone H","SAVU","Minor_AdHoc"," "," ",59132]
["2025-05-31","2025-06-02","CE",1,"27D","A+B","BRUXELLES-NORD-GRIL F","Y.SCHAERBEEK-CARWASH","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59132 on line 36 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.DIEGEM: Vernieuwing Albertbrug fase 1.2: afbraak brugdeel 4 boven L27D/L27F/L36/AL27 + Vervangen assentellersysteem zone H","CTL","Medium"," "," ",59132]
["2025-05-31","2025-06-02","CE",1,"27D/4","A+B","SCHAERBEEK","Y.SCHAERBEEK-CARWASH","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59132 on line 36 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.DIEGEM: Vernieuwing Albertbrug fase 1.2: afbraak brugdeel 4 boven L27D/L27F/L36/AL27 + Vervangen assentellersysteem zone H","CTL","Medium"," "," ",59132]
["2025-05-31","2025-06-02","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59132 on line 36 tracks(s) A+B from BRUXELLES-NORD-GRIL F to Y.DIEGEM: Vernieuwing Albertbrug fase 1.2: afbraak brugdeel 4 boven L27D/L27F/L36/AL27 + Vervangen assentellersysteem zone H","CTL","Medium"," "," ",59132]
["2025-05-31","2025-06-02","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","00:01","04:00","Vernieuwing Ballast & Dwaarsliggers","CTL","Medium","BTS 40km/h -  wordt nog berekend."," ",57979]
["2025-06-02","2025-06-06","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Week","Night","23:00","04:10","Second tabliers ponts 7,8 et 9 + Renouvellement AS de Lobbes-Garage & Hourpes\r\nNuits de finition","CTL","Minor_AdHoc",null,"HKM à adapter",53457]
["2025-06-02","2025-06-06","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement de chapes – Phase 2- 36.363 38.279\r\nPréparations","CTL","Minor_AdHoc",null," ",55525]
["2025-06-02","2025-06-06","SW",1,"94","A+B","HALLE","ENGHIEN","Week","Night","23:10","04:40","Nuits de préparation - Construction d'un PI - PN16","CTL","Minor_AdHoc","CTL de nuits de semaine"," ",55580]
["2025-06-02","2025-06-07","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Week","Night","23:00","05:00","Linked to coupure nr 58429 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\n(zie ook schets 'expl L25&L25N')","CTL","Minor_AdHoc"," "," ",58429]
["2025-06-02","2025-06-07","SW",1,"130","A+B","AISEAU","CHATELET-GRIL EST","Week","Night","22:30","05:00","Semaines de nuits de finitions - démolition 85.708","CTL","Minor_AdHoc"," "," ",55903]
["2025-06-02","2025-06-07","SW",1,"78","A+B","BLATON","TOURNAI","Week","Night","22:50","05:00","Blaton - Y.Maubray : Renouvellement ballast C75 (2x7km) + traverses biblocs - Phase 2\r\nTravaux finition (2 semaines)\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","ART stabilisation (60) : du 19/05/25 5h au 26/05 5H VB + du 26/05 5h au 02/06/2025 5h VA\r\nHKV\t: 4min.\r\nHKM : 2min."," ",61841]
["2025-06-02","2025-06-13","SE",1,"165","B","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE","AllWeek","Continuous","06:00","06:00","Criblage 102500-98200\r\nDossier de concertation validé en octobre 2022","SAVU","High","ART protection (voie A) 60 km/h: V: 4' - M: 5' du 02 au 13 juin. \r\nART à 60km/h = MAX 4 train/heure\r\nARt de stabilisation cf CoLT 56496"," ",55799]
["2025-06-02","2025-06-14","CE",1,"27","A","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 62032 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerkenwerken afbraak deel 3+4","SAVU","Minor_AdHoc"," "," ",62032]
["2025-06-02","2025-06-14","CE",1,"27D","S","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 62032 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerkenwerken afbraak deel 3+4","CTL","Minor_AdHoc"," "," ",62032]
["2025-06-02","2025-06-14","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","Week","Night","23:40","04:30","Linked to coupure nr 62032 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerkenwerken afbraak deel 3+4","CTL","Minor_AdHoc"," "," ",62032]
["2025-06-02","2025-06-16","SE",1,"162","A","POIX-SAINT-HUBERT","HATRIVAL","AllWeek","Continuous","05:00","05:00","Grupont - Hatrival : phase 14 = ART VA\r\nDeux voies passantes","ART","Minor_AdHoc","ART 4min (à préciser)"," ",33296]
["2025-06-02","2025-06-16","SE",1,"162","B","CINEY","HAVERSIN","AllWeek","Continuous","06:00","05:00","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 14 - ART\r\nciney-haversin\r\nTravaux effectués = Travaux caténaires et GC linéaire + début des travaux de quai à Leignon et Chapois","ART","Minor_AdHoc","Phase ART stabilisation\r\nEstimation en cours (environ 5min - à confirmer)"," ",62771]
["2025-06-02","2025-07-07","SE",1,"154","A","DINANT","YVOIR","AllWeek","Continuous","08:00","16:00","Remise en peinture viaduc de Houx\r\nMise au gabarit pistes de circulation\r\nPhase 1","SAVU","High","ART 2min"," ",46309]
["2025-06-06","2025-06-09","SE",1,"154","A+B","YVOIR","DINANT","Weekend","Continuous","23:50","04:20","Remplacement de rails dans le PN114 à Dinant","CTL","Medium","La gare de Dinant reste accessible côté L166 \r\nVoie 3 HS\r\nLa gare d'Yvoir reste accessible côté Namur"," ",56494]
["2025-06-06","2025-06-09","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n14 - Déroulage Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","3 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 13)"," ",59627]
["2025-06-06","2025-06-09","SE",1,"24/1","A","VISE","Y.BERNEAU","Weekend","Continuous","23:00","05:00","Linked to coupure nr 55215 on line 40 tracks(s) A+B from VISE to VISE-FRONTIERE: Entretien mécanisé et manuel des AS du grill Nord de Visé-Bas\r\nEntretien mécanisé du PN 28\r\nRq 333 : Rq Ef's suite semestrielle : attention lever CTL L37\r\nRéunion 12/10 : P","SAVU","Minor_AdHoc"," "," ",55215]
["2025-06-06","2025-06-09","SE",1,"40","A+B","VISE","VISE-FRONTIERE","Weekend","Continuous","23:00","05:00","Entretien mécanisé et manuel des AS du grill Nord de Visé-Bas\r\nEntretien mécanisé du PN 28\r\nRq 333 : Rq Ef's suite semestrielle : attention lever CTL L37\r\nRéunion 12/10 : Propo à faire pour L37 (au plus proche)","CTL","Medium","Quai de la voie I de Visé accessible vers Liège\r\nQuai de la voie II HS\r\nVA de la 24/1 HS"," ",55215]
["2025-06-06","2025-06-10","SW",1,"117","A+B","MANAGE","LUTTRE","Weekend","Continuous","23:30","04:30","Aménagement de Luttre - Phase 2025\r\nWE 3 (3jrs)","CTL","Medium","CTL en continu"," ",53229]
["2025-06-06","2025-06-10","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement de chapes – Phase 2- 36.363 38.279","CTL","Medium","CTL de WE avec jour férié \r\nART 2 min pendant 3 semaines"," ",55529]
["2025-06-06","2025-06-10","SW",1,"94","A+B","HALLE","ENGHIEN","Weekend","Continuous","23:10","04:40","Construction d'un PI - PN16","CTL","Medium","WE de CTL du Vendredi soir au Lundi Matin\r\nART pendant 14 jours après le WE"," ",55582]
["2025-06-07","2025-06-09","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","00:01","04:00","Vernieuwing Ballast & Dwaarsliggers","CTL","Medium","BTS 40km/h -  wordt nog berekend."," ",57980]
["2025-06-07","2025-06-09","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Weekend","Night","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Coupure type 9\r\nVoies principales en CTL\r\nFaisceau A accessible uniquement coté Charleroi\r\nFaisceau K inacessible \r\nFaisceau D : uniquement voies 360-361 en CDS accessibles coté Namur\r\nFaisceau B+C : uniquement accessible coté Namur","InfoRacc",55168]
["2025-06-07","2025-06-10","CE",1,"26","A+B","Y.NOORD HALLE","Y.LINKEBEEK-HALLE","Weekend","Continuous","00:20","04:00","Verbreding ONB Spoorwegstraat","CTL","Medium","TLO L26 tussen Halle en Y Linkebeek/Halle"," ",59453]
["2025-06-07","2025-12-06","NW",1,"50","*","GENT-SINT-PIETERS","GENT-SINT-PIETERS","AllWeek","Continuous","00:00","(vide)","Masterplan Gent Sint Pieters Stap 33\r\n\r\nSpoor III doodspoor","Autre","Minor_AdHoc"," "," ",59413]
["2025-06-09","2025-06-14","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:20","Linked to coupure nr 59220 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: inkorten bovenleiding spoor III\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. West Driehoek Ledeberg \r\nSP B L 50 G","SAVU","Minor_AdHoc"," "," ",59220]
["2025-06-09","2025-06-14","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:20","04:20","Linked to coupure nr 59220 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: inkorten bovenleiding spoor III\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. West Driehoek Ledeberg \r\nSP B L 50 G","CTL","Minor_AdHoc"," "," ",59220]
["2025-06-09","2025-06-14","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:20","Stap 33: inkorten bovenleiding spoor III\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. West Driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters -Y. West Driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels\r\nSP B L 75 Gent Sin","CTL","Minor_AdHoc"," "," ",59220]
["2025-06-09","2025-06-14","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:20","04:20","Linked to coupure nr 59220 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: inkorten bovenleiding spoor III\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. West Driehoek Ledeberg \r\nSP B L 50 G","SAVU","Minor_AdHoc"," "," ",59220]
["2025-06-09","2025-06-14","NW",1,"75","B","GENT-SINT-PIETERS","DE PINTE","Week","Night","23:20","04:20","Linked to coupure nr 59220 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: inkorten bovenleiding spoor III\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. West Driehoek Ledeberg \r\nSP B L 50 G","SAVU","Minor_AdHoc"," "," ",59220]
["2025-06-09","2025-06-21","SW",1,"130","B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Week","Night","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Coupure type 8\r\nSAVU VB HS\r\nFaisceau A accessible uniquement coté Charleroi\r\nFaisceau K inacessible \r\nFaisceau D : uniquement voies 360-361 en CDS accessibles coté Namur\r\nFaisceau B : uniquement accessible coté Namur","A déterminer",55171]
["2025-06-10","2025-06-14","SW",1,"117","A+B","MANAGE","LUTTRE","Week","Night","22:30","04:30","Aménagement de Luttre - Phase 2025\r\nNuits de finition","CTL","Minor_AdHoc","CTL de nuit"," ",53227]
["2025-06-10","2025-06-14","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement de chapes – Phase 2 - 36.363 38.279\r\nNuit pour soudures","CTL","Minor_AdHoc",null," ",55530]
["2025-06-10","2025-06-14","SW",1,"94","A+B","HALLE","ENGHIEN","Week","Night","23:10","04:40","Nuits de finition - Construction d'un PI - PN16","CTL","Minor_AdHoc","CTL de nuits de semaine"," ",55583]
["2025-06-10","2025-06-25","SW",1,"94","A+B","HALLE","ENGHIEN","AllWeek","Continuous","04:40","04:40","ART 2 min\r\nConstruction d'un PI - PN16","ART","Minor_AdHoc","ART pendant 14 jours après le WE"," ",59440]
["2025-06-10","2025-06-30","SW",1,"140","A+B","OTTIGNIES","FLEURUS","AllWeek","Continuous","05:00","05:00","ART 2min\r\nRenouvellement de chapes – Phase 2- 36.363 38.279","ART","Minor_AdHoc",null," ",59519]
["2025-06-11","2025-06-14","CE",1,"26","A+B","Y.NOORD HALLE","Y.LINKEBEEK-HALLE","Week","Night","00:20","04:00","Verbreding ONB Spoorwegstraat: afwerking","CTL","Minor_AdHoc","TLO L26 tussen Halle en Y Linkebeek/Halle"," ",59454]
["2025-06-13","2025-06-16","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n14 - Déroulage Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","3 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 13)"," ",59628]
["2025-06-13","2025-06-16","SE",1,"161","A+B","WATERMAEL","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER\r\n Rq 333 : demande EF's suite semestrielle :  Laisser L36+139 Libre pour déviations et pas de travaux simultanés sur la L140.-","CTL","Medium","ART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59160]
["2025-06-13","2025-06-19","SE",1,"165","B","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE","Weekend","Continuous","06:00","06:00","ART 4min/5min\r\nde stabilisation en voie B post-Criblage 102500-98200\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART stabilisation à 60km/h : V: 4' M:5'","HKM à adapter",56496]
["2025-06-14","2025-06-16","NW",1,"50","A+B","Y.MELLE","AALST","Weekend","Continuous","00:40","04:00","Instandhouding  Y Schellebelle + Wissels Rooster Schellebelle\r\n\r\nY Melle + Aalst NIET IN","CTL","Medium",null," ",59340]
["2025-06-14","2025-06-16","NW",1,"53","A+B","SCHELLEBELLE","DENDERMONDE","Weekend","Continuous","00:40","04:00","Linked to coupure nr 59340 on line 50 tracks(s) A+B from Y.MELLE to AALST: Instandhouding  Y Schellebelle + Wissels Rooster Schellebelle\r\n\r\nY Melle + Aalst NIET IN","CTL","Medium"," "," ",59340]
["2025-06-14","2025-06-23","SW",1,"124","A+B","ROUX","MARCHIENNE-AU-PONT","AllWeek","Night","23:00","05:00","Rénovation et sécurisation des murs de soutènement voie A entre la BK 49.050 et la BK 29.300","CTL","Minor_AdHoc"," "," ",55545]
["2025-06-16","2025-06-17","SE",1,"165","B","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE","Week","Day","08:00","16:00","Criblage - bourrage de révision\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc",null,"HKM à adapter",56504]
["2025-06-16","2025-06-20","SW",1,"130A","A+B","LA SAMBRE","ERQUELINNES-FRONTIERE","Week","Night","23:00","04:10","Second tabliers ponts 7,8 et 9 + Renouvellement AS de Lobbes-Garage & Hourpes\r\nNuits de finition","CTL","Minor_AdHoc",null,"HKM à adapter",56491]
["2025-06-16","2025-06-21","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59222 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59222]
["2025-06-16","2025-06-21","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59222 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59222]
["2025-06-16","2025-06-21","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59222]
["2025-06-16","2025-06-21","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59222 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59222]
["2025-06-16","2025-06-21","SW",1,"94","A+B","HALLE","ENGHIEN","Week","Night","23:10","04:40","Nuits de finition - Construction d'un PI - PN16","CTL","Minor_AdHoc","CTL de nuits de semaine"," ",57064]
["2025-06-16","2025-06-27","SW",1,"117","A/B","BRAINE-LE-COMTE","Y.ECAUSSINNES","Week","Day","09:00","15:00","Programme de révision caténaire - Phase 1","SAVU","Minor_AdHoc","SAVU Voie A/B\r\nCoupures de jour (9h-15h) limitées à une seule voie sur le tronçon entre B-L-C et Manage."," ",56178]
["2025-06-16","2025-09-29","SE",1,"162","A","CINEY","HAVERSIN","AllWeek","Continuous","05:00","05:00","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 15\r\nciney-haversin\r\nTravaux effectués = Travaux caténaires et GC linéaire + début des travaux de quai à Leignon et Chapois","SAVU_CTRL","High","CTL de Nuit : Lu^Ma à Je^Ve :00:10–04:50, Ve^Sa 00:10–06:30, Sa^Di 23:10–06:30, Di^Lu 23:10–04:50\r\nAS 34BK parcourable\r\nSAVU prolongé dans le tronçon suite arbitrage budgétaire"," ",62773]
["2025-06-16","2025-12-13","SE",1,"162","A","GRUPONT","HATRIVAL","AllWeek","Continuous","05:00","23:50","Grupont - Hatrival : phase 15\r\nFinitions","SAVU_CTRL","High","CTL de 22h10 à 5h15"," ",62777]
["2025-06-20","2025-06-21","SE",1,"166","A/B","GEDINNE","PALISEUL","Week","Day","06:00","06:00","Renouvellement de traverses par P93 - Phase 2 - WE 1\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu ven 20/06 au sam 21/06 06h (avec max 4 trains/h)","HKM à adapter",56529]
["2025-06-20","2025-06-23","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n14 - Déroulage Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","3 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 13)"," ",59629]
["2025-06-20","2025-06-23","SW",1,"94","A+B","BLANDAIN-FRONTIERE","FROYENNES","Weekend","Continuous","23:00","04:30","Modernisation de la signalisation des PN entre Y. Froyennes et la Fr. Française","CTL","Medium","CTL WE en continu"," ",53443]
["2025-06-20","2025-06-28","SE",1,"165","B","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE","AllWeek","Continuous","06:00","06:00","Criblage 98200-95100\r\nDossier de concertation validé en octobre 2022","SAVU","High","ART protection (voie A) 60 km/h: V: 3' - M: 4' du 19 juin au 04 juillet.\r\nART à 60km/h = MAX 4 trains/heure\r\nART de stabilisation cf CoLT 59609","HKM à adapter",56497]
["2025-06-20","2025-07-27","SE",1,"166","A+B","GEDINNE","PALISEUL","AllWeek","Continuous","06:00","04:30","ART\r\nRenouvellement de traverses par P93 - Phase 2","ART","Minor_AdHoc","ART de stabilisation en voie B - vitesse 80 km/h - 3'\r\nBK53870 à 60960\r\nMise en vigueur: 20/06/25\r\nFin probable: 25/07/25",null,61880]
["2025-06-21","2025-06-23","SE",1,"166","A+B","GEDINNE","PALISEUL","Weekend","Continuous","06:00","04:30","Renouvellement de traverses par P93 - Phase 2 - WE 1\r\nDossier de concertation octobre 2022","CTL","Medium",null,"HKM à adapter",56533]
["2025-06-23","2025-06-23","SE",1,"166","A/B","GEDINNE","PALISEUL","Week","Day","04:30","16:30","Renouvellement de traverses par P93 - Phase 2 - WE 1\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu lun 23/06 04h30 à 16h30 (avec max 4 trains/h)","HKM à adapter",56539]
["2025-06-23","2025-06-28","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59223 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59223]
["2025-06-23","2025-06-28","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59223 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59223]
["2025-06-23","2025-06-28","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59223]
["2025-06-23","2025-06-28","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59223 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59223]
["2025-06-23","2025-06-28","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n15 - Pose métalliques","SAVU_CTRL","Minor_AdHoc","1 semaine SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 14)"," ",59630]
["2025-06-23","2025-06-28","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Week","Continuous","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Coupure type 1 \r\nEn continu : \r\nFaisceau A HS (stand gazoil uniquement accessible en diesel coté Charleroi)\r\ncas 27331 HT\r\nFaisceau B accessible uniquement coté Campinaire\r\nFaisceau D : voies 360-361 exploitables\r\nFaisceau K inaccessible","to be defined",55174]
["2025-06-23","2025-06-28","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Week","Night","23:00","05:00","Renouvellement de chapes – Phase 2 - 36.363 38.279\r\nfinitions","CTL","Minor_AdHoc",null," ",55531]
["2025-06-23","2025-06-28","SW",1,"94","A+B","HALLE","ENGHIEN","Week","Night","23:10","04:40","Nuits de finition - Construction d'un PI - PN16","CTL","Minor_AdHoc","CTL de nuits de semaine"," ",57065]
["2025-06-27","2025-06-28","SE",1,"166","A/B","GEDINNE","PALISEUL","Week","Day","06:00","06:00","Renouvellement de traverses par P93 - Phase 2 - WE 2\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu ven 27/06 au sam 28/06 06h (avec max 4 trains/h)","HKM à adapter",56530]
["2025-06-27","2025-06-30","CE",1,"96B","A+B","BRUXELLES-MIDI","FOREST-MIDI-VOIES 920/926","Weekend","Continuous","23:50","04:00","Indienstname ETCS bundels Vorst","Autre","Minor_AdHoc","Bundels Vorst volledig afgesloten."," ",59139]
["2025-06-27","2025-06-30","SE",1,"161","B","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59167]
["2025-06-27","2025-06-30","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 minutes"," ",54943]
["2025-06-27","2025-06-30","SW",1,"130A","A+B","ERQUELINNES","ERQUELINNES-FRONTIERE","Weekend","Continuous","23:50","04:00","Travaux SNCF\r\nPMR Maubeuge 48h00","CTL","Medium",null," ",62944]
["2025-06-27","2025-06-30","SW",1,"75A","A+B","MOUSCRON","FROYENNES","Weekend","Continuous","22:30","04:10","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nCTL en continu pour ripage du CSV.\r\nRq 333 : rq Ef's suite semestrielle : déplacé WE 26","CTL","Medium","ART  40km/h : 2,13 min voyageurs; 5,62 min marchandises pendant 14 jours après la CTL"," ",39541]
["2025-06-28","2025-06-29","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Weekend","Night","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Coupure type 9\r\nVoies principales en CTL\r\nFaisceau A accessible uniquement coté Charleroi\r\nFaisceau K inacessible \r\nFaisceau D : uniquement voies 360-361 en CDS accessibles coté Namur\r\nFaisceau B+C : uniquement accessible coté Namur","InfoRacc",55170]
["2025-06-28","2025-06-29","SW",1,"130C","A+B","CHATELET-GRIL EST","CHATELET-GRIL OUEST","Weekend","Night","23:00","05:00","Linked to coupure nr 55170 on line 130 tracks(s) A+B from LE CAMPINAIRE to CHATELET-GRIL OUEST: Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc"," ","InfoRacc",55170]
["2025-06-28","2025-06-29","SW",1,"90C","A+B","JURBISE","BRUGELETTE","Weekend","Continuous","06:00","17:00","Maintenance Z.7.53 P4","CTL","Medium",null," ",56575]
["2025-06-28","2025-06-30","NE",1,"25","A+B","SCHAERBEEK","VILVOORDE","Weekend","Continuous","00:01","04:00","Werken Viaduct Vilvoorde (AWV)","CTL","Medium"," "," ",58704]
["2025-06-28","2025-06-30","SE",1,"166","A+B","GEDINNE","PALISEUL","Weekend","Continuous","06:00","04:30","Renouvellement de traverses par P93 - Phase 2 - WE 2\r\nDossier de concertation octobre 2022","CTL","Medium",null,"HKM à adapter",56534]
["2025-06-28","2025-07-04","SE",1,"165","B","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE","AllWeek","Continuous","06:00","22:00","ART stabilisation en voie B post-criblage 98200 - 95100\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART stabilisation 60 km/h V: 3' M: 4'\r\n95100 - 102500"," ",59609]
["2025-06-29","2025-06-30","SW",1,"130","B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Weekend","Night","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Coupure type 8\r\nSAVU VB HS\r\nFaisceau A accessible uniquement coté Charleroi\r\nFaisceau K inacessible \r\nFaisceau D : uniquement voies 360-361 en CDS accessibles coté Namur\r\nFaisceau B : uniquement accessible coté Namur","A déterminer",55172]
["2025-06-30","2025-06-30","SE",1,"166","A/B","GEDINNE","PALISEUL","Week","Day","04:30","16:30","Renouvellement de traverses par P93 - Phase 2 - WE 2\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu lun 30/06 04h30 à 16h30 (avec max 4 trains/h)","HKM à adapter",56540]
["2025-06-30","2025-07-04","CE",1,"96","A+B","Y.RUISBROEK","Y.NOORD HALLE","Week","Night","23:40","04:30","Vernieuwen BVL L96+L96E zone A4-B4-A5-B5: voorbereiding","CTL","Minor_AdHoc","TLO L96 + L96E",null,59693]
["2025-06-30","2025-07-04","CE",1,"96E","S","Y.NOORD HALLE","LOT","Week","Night","23:40","04:30","Linked to coupure nr 59693 on line 96 tracks(s) A+B from Y.RUISBROEK to Y.NOORD HALLE: Vernieuwen BVL L96+L96E zone A4-B4-A5-B5: voorbereiding","CTL","Minor_AdHoc"," ",null,59693]
["2025-06-30","2025-07-05","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59225 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59225]
["2025-06-30","2025-07-05","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59225 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59225]
["2025-06-30","2025-07-05","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59225]
["2025-06-30","2025-07-05","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59225 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59225]
["2025-06-30","2025-07-05","SW",1,"130","A+B","CHATELET-GRIL EST","CHATELET-GRIL OUEST","Week","Night","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Coupure type 7\r\nFaisceau A HS \r\ncas 27320+ 27322 HT","to be defined",55178]
["2025-06-30","2025-07-07","CE",1,"26","B","Y.WATERMAEL","Y.LINKEBEEK-HALLE","AllWeek","Continuous","04:00","04:00","BTS bij indienstname sp A na Fase 3.","ART","Minor_AdHoc","BTS"," ",51879]
["2025-06-30","2025-07-14","SW",1,"75A","A+B","MOUSCRON","FROYENNES","AllWeek","Continuous","04:10","04:10","ART\r\nConstruction passage inférieur + couloir-sous-voie pour la suppression du PN4","ART","Minor_AdHoc","ART  40km/h : 2,13 min voyageurs; 5,62 min marchandises pendant 14 jours après la CTL"," ",59458]
["2025-06-30","2025-09-05","SW",1,"117","A/B","MANAGE","Y.FELUY","Week","Day","15:00","15:00","Programme de révision caténaire - Phase 1","SAVU","Minor_AdHoc","SAVU Voie A/B\r\nCoupures de jour (9h-15h) limitées à une seule voie sur le tronçon entre B-L-C et Manage."," ",56092]
["2025-07-01","2025-07-02","SE",1,"165","B","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE","Week","Day","08:00","16:00","Criblage: bourrage de révision\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc",null,"HKM à adapter",56498]
["2025-07-04","2025-07-05","SE",1,"166","A/B","GEDINNE","PALISEUL","Week","Day","06:00","06:00","Renouvellement de traverses par P93 - Phase 2 - WE 3\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu ven 04/07 au sam 05/07 06h (avec max 4 trains/h)","HKM à adapter",56531]
["2025-07-04","2025-07-07","CE",1,"96","A+B","Y.RUISBROEK","Y.NOORD HALLE","Weekend","Continuous","23:40","04:30","Vernieuwen BVL L96+L96E zone A4-B4-A5-B5","CTL","Medium","TLO L96 + L96E",null,59692]
["2025-07-04","2025-07-07","CE",1,"96E","S","Y.NOORD HALLE","LOT","Weekend","Continuous","23:40","04:30","Linked to coupure nr 59692 on line 96 tracks(s) A+B from Y.RUISBROEK to Y.NOORD HALLE: Vernieuwen BVL L96+L96E zone A4-B4-A5-B5","CTL","Medium"," ",null,59692]
["2025-07-04","2025-07-07","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n16 - Déroulage Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","2 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 15)"," ",59631]
["2025-07-05","2025-07-07","SE",1,"166","A+B","GEDINNE","PALISEUL","Weekend","Continuous","06:00","04:30","Renouvellement de traverses par P93 - Phase 2 - WE 3\r\nDossier de concertation octobre 2022","CTL","Medium",null,"HKM à adapter",56535]
["2025-07-05","2025-07-07","SW",1,"130","B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Weekend","Night","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Coupure type 8\r\nSAVU VB HS\r\nFaisceau A accessible uniquement coté Charleroi\r\nFaisceau K inacessible \r\nFaisceau D : uniquement voies 360-361 en CDS accessibles coté Namur\r\nFaisceau B : uniquement accessible coté Namur","A déterminer",55173]
["2025-07-07","2025-07-07","SE",1,"166","A/B","GEDINNE","PALISEUL","Week","Day","04:30","16:30","Renouvellement de traverses par P93 - Phase 2 - WE 3\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu lun 07/07 04h30 à 16h30 (avec max 4 trains/h)","HKM à adapter",56541]
["2025-07-07","2025-07-11","SE",1,"165","B","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE","Week","Day","06:00","22:00","Criblage: bourrage et finitions\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc",null,"HKM à adapter",56499]
["2025-07-07","2025-07-12","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59226 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59226]
["2025-07-07","2025-07-12","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59226 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59226]
["2025-07-07","2025-07-12","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59226]
["2025-07-07","2025-07-12","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59226 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59226]
["2025-07-07","2025-08-24","SE",1,"34","A+B","LIEGE-GUILLEMINS","HERSTAL","AllWeek","Continuous","23:55","22:00","Massification:\r\nRé-électrification du tunnel de Gt Gilles\r\nEntretien général des installations caténaires\r\nRenouvellement de fils de contact\r\nRectification du profil en long V pour drainage et renouvellement du soutènement VB\r\nDossier de concertation oc","CTL","Major","ART: \r\n1 mois 40km/h entre env. km 5.500 et 5.900 VA et VB\r\nVitesse réduite HKM: 1.4 et HKV: 2.2"," ",55923]
["2025-07-08","2025-07-11","CE",1,"94","A+B","Y.NOORD HALLE","SAINTES","Week","Night","00:45","04:30","Linked to coupure nr 59688 on line 96 tracks(s) A+B from Y.NOORD HALLE to TUBIZE: Vernieuwen BVL L96 + aw's 96/94 kant Lembeek zone A12-A13","CTL","Minor_AdHoc"," ",null,59688]
["2025-07-08","2025-07-11","CE",1,"96","A+B","Y.NOORD HALLE","TUBIZE","Week","Night","00:45","04:30","Vernieuwen BVL L96 + aw's 96/94 kant Lembeek zone A12-A13","CTL","Minor_AdHoc","TLO L96 + L94\r\nStation Halle afgesloten",null,59688]
["2025-07-11","2025-07-11","SE",1,"166","A/B","GEDINNE","PALISEUL","Week","Day","06:00","06:00","Renouvellement de traverses par P93 - Phase 2 - WE 4\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu ven 11/07 au sam 12/07 06h (avec max 4 trains/h)","HKM à adapter",56532]
["2025-07-11","2025-07-14","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n16 - Déroulage Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","2 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 15)"," ",59633]
["2025-07-12","2025-07-13","SW",1,"96","A+B","MONS","QUEVY-FRONTIERE","Weekend","Continuous","06:00","17:00","Maintenance Z.6.53 en P4","CTL","Medium"," "," ",53501]
["2025-07-12","2025-07-14","CE",1,"94","A+B","Y.NOORD HALLE","SAINTES","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59687 on line 96 tracks(s) A+B from Y.NOORD HALLE to TUBIZE: Vernieuwen BVL L96 + aw's 96/94 kant Lembeek zone A12-A13","CTL","Medium"," ",null,59687]
["2025-07-12","2025-07-14","CE",1,"96","A+B","Y.NOORD HALLE","TUBIZE","Weekend","Continuous","00:45","04:30","Vernieuwen BVL L96 + aw's 96/94 kant Lembeek zone A12-A13","CTL","Medium","TLO L96 + L94\r\nStation Halle afgesloten",null,59687]
["2025-07-12","2025-07-14","SE",1,"166","A+B","GEDINNE","PALISEUL","Weekend","Continuous","06:00","04:30","Renouvellement de traverses par P93 - Phase 2 - WE 4\r\nDossier de concertation octobre 2022","CTL","Medium",null,"HKM à adapter",56536]
["2025-07-14","2025-07-14","SE",1,"166","A/B","GEDINNE","PALISEUL","Week","Day","04:30","16:30","Renouvellement de traverses par P93 - Phase 2 - WE 4\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu lun 14/07 04h30 à 16h30 (avec max 4 trains/h)","HKM à adapter",56542]
["2025-07-14","2025-07-18","SE",1,"165","B","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE","Week","Day","06:00","22:00","Criblage: bourrage et finitions\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc",null,"HKM à adapter",56500]
["2025-07-14","2025-07-19","CE",1,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","Week","Night","23:45","04:50","Voorbereidende werken /opmetingen lange TLO oktober\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit FBMZ verlengde L124","CTL","Minor_AdHoc","TLO L124"," ",61834]
["2025-07-14","2025-07-19","CE",1,"28/3","S","Y.FOREST-EST","Y.CUREGHEM","Week","Night","23:45","04:50","Linked to coupure nr 61834 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: Voorbereidende werken /opmetingen lange TLO oktober\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissel","CTL","Minor_AdHoc"," "," ",61834]
["2025-07-14","2025-07-25","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","Week","Night","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL","Autre","Minor_AdHoc","sp 3 BDS"," ",59762]
["2025-07-15","2025-07-28","SE",1,"166","A/B","GEDINNE","PALISEUL","Week","Night","23:00","05:30","Renouvellement de traverses par P93 - Phase 2 - Finitions\r\nDossier de concertation octobre 2022","SAVU","Minor_AdHoc","Savu de nuits en semaine de 23h00 à 05h30 du 15 au 28/07"," ",56056]
["2025-07-18","2025-07-21","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL","Autre","Minor_AdHoc","sp 3 BDS"," ",59763]
["2025-07-25","2025-07-28","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL","Autre","Minor_AdHoc","sp 3 BDS"," ",59764]
["2025-07-26","2025-07-27","SW",1,"96","A+B","MONS","QUEVY-FRONTIERE","Weekend","Continuous","06:00","17:00","Maintenance Z.6.53 en P4","CTL","Medium"," "," ",53499]
["2025-07-28","2025-08-16","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","Week","Night","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL","Autre","Minor_AdHoc","sp 3 BDS"," ",59765]
["2025-08-01","2025-08-04","CE",1,"161","A+B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL","CTL","Medium","sp 3 +4 BDS"," ",59767]
["2025-08-01","2025-08-25","CE",1,"28/1","A+B","Y.BOCKSTAEL","Y.PANNENHUIS","AllWeek","Continuous","23:30","04:00","L28/1 spuitbeton: herstellen beton tunnel Bockstaelplein","CTL","High","TLO L28/1"," ",59145]
["2025-08-02","2025-08-03","SW",1,"130","B","CHATELET","LE CAMPINAIRE","Weekend","Night","22:30","05:30","Livraison LRS via T-Portique\r\n\r\nMHS : Cul sac 317 + signal DX6-I. 20 + signal D5-I. 20 + GC-J. 20 + e359-j. 20\r\n+ L130 VB entre DX4-I. 20 et signal C-J. 20\r\nMHT cas 27331 + 324 + 333","SAVU","Minor_AdHoc","Faisceau A inaccessible côté Namur\r\nFaisceau K fermé\r\nFaisceau B & D inaccessible côté Charleroi"," ",61827]
["2025-08-04","2025-08-08","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","22:30","04:30","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 4  - Pose du nouveau tablier (préparations et CTL en continu pour la pose)​\r\nPhase 4.1 – CTL L75+75A+Faisceau de nuit","CTL","Minor_AdHoc","Phase 4.1 – CTL L75+75A+Faisceau de nuit​\r\nTravaux de de nuit du 4/08 au 8/08/2025 entre 22h30 et 4h30"," ",55877]
["2025-08-04","2025-08-08","SW",1,"75A","B","MOUSCRON","FROYENNES","Week","Night","22:30","04:30","Linked to coupure nr 55877 on line 75 tracks(s) A+B from MOUSCRON to MOUSCRON-FRONTIERE: Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 4  - Pose du nouveau tablier (préparations et CTL en continu po","CTL","Minor_AdHoc"," "," ",55877]
["2025-08-04","2025-08-09","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n17 - Dépose traverses Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","1 semaines SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 16)"," ",59632]
["2025-08-04","2025-08-09","SW",1,"90C","A+B","JURBISE","ATH","Week","Night","23:00","05:00","Travaux de construction d'un PI au droit du km 51.775 en vue de la suppression du PN5\r\nNuits de préparation","CTL","Minor_AdHoc"," "," ",55538]
["2025-08-04","2025-08-25","SE",1,"43","A","MARLOIE","BOMAL","AllWeek","Continuous","05:00","05:00","Travaux Axe 3\r\nAdaptation pour 25kV:\r\nAbaissement de la voie sous le PS 60.070\r\nTravaux caténaire","CTL","High","Congés scolaires FWB"," ",54058]
["2025-08-04","2025-08-30","SW",1,"130A","A/B","LOBBES","ERQUELINNES-VILLAGE","AllWeek","Night","06:00","15:30","Renouvellement AS Lobbes-Garage : préparation caténaire","SAVU","Minor_AdHoc"," "," ",56336]
["2025-08-04","2025-09-08","SE",1,"154","B","DINANT","YVOIR","AllWeek","Continuous","08:00","08:00","Remise en peinture viaduc de Houx\r\nMise au gabarit pistes de circulation \r\nPhase 2","SAVU","High","ART 2min"," ",46303]
["2025-08-08","2025-08-11","CE",1,"161","A+B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL","CTL","Medium","sp 3 +4 BDS"," ",59768]
["2025-08-08","2025-08-11","SE",1,"161","A","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59168]
["2025-08-08","2025-08-11","SW",1,"75","A","MOUSCRON-FRONTIERE","MOUSCRON","Weekend","Continuous","23:00","04:30","Linked to coupure nr 55879 on line 75A tracks(s) A+B from MOUSCRON to FROYENNES: Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 4  - Pose du nouveau tablier (préparations et CTL en continu pour la po","CTL","Medium"," "," ",55879]
["2025-08-08","2025-08-11","SW",1,"75A","A+B","MOUSCRON","FROYENNES","Weekend","Continuous","23:00","04:30","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 4  - Pose du nouveau tablier (préparations et CTL en continu pour la pose)\r\nPhase 4.2 – CTL L75+75A+Faisceau en continu\r\nDossier de concertation validé ","CTL","Medium","Phase 4.2 – CTL L75+75A+Faisceau en continu\r\nTravaux en continu du 8/08 à 23h00 au 11/08/2025 à 4h30"," ",55879]
["2025-08-08","2025-08-15","SW",1,"112","A+B","MARCHIENNE-AU-PONT","LA LOUVIERE-SUD","AllWeek","Night","22:50","04:40","Renouvellement chapes PI 13.823 + 14.636 + 17.664. \r\nNuits de préparation","CTL","Minor_AdHoc"," "," ",55513]
["2025-08-08","2025-08-25","SE",1,"42","A","AYWAILLE","TROIS-PONTS","AllWeek","Continuous","23:00","05:00","Criblage de ballsast","CTL","High","CTL Aywaille Trois-Ponts (aywaille HT)\r\nART stabilisation voir Colt 59540","détournés via les L162-125-125A",55813]
["2025-08-09","2025-08-10","SW",1,"96","A+B","MONS","QUEVY-FRONTIERE","Weekend","Continuous","06:00","17:00","Maintenance Z.6.53 en P4","CTL","Medium"," "," ",53500]
["2025-08-09","2025-08-11","NE",1,"25","A+B","MECHELEN","Y.ABEELSTRAAT","Weekend","Continuous","01:00","04:00","bijkomende aanvraag renovatie Vaartbrug  ipv vernieuwing\r\n\r\n\r\nTLO lijn 25 gedurende 7 weken. Impact deels icm CoLT 58490 (renovatie kruisingsbrug 2 weken september 2025)\r\n\r\nZie goedgekeurd dossier: 2024 - L25 - Mechelen-Y. Abeelstraat","CTL","Medium","TLO L25 A+B tijdens weekends van Y.Abeelstraat tot Mechelen inbegrepen.\r\nTLO L25 A+B tijdens weeknachten van Mechelen tot Mechelen."," ",59456]
["2025-08-09","2025-11-10","SE",1,"166","A+B","GEDINNE","BERTRIX","Weekend","Continuous","06:00","06:00","Travaux caténaires\r\nRq 333 : Pas le we 27-28/09 (réunion 17/10)","CTL","Minor_AdHoc","1) Bertrix exclus\r\n11 we du sam 23 au dim 15h+ nuit dim^lun de 23h à 05h\r\n2) Gedinne- Bertix inclus\r\n3we nuit sam^dim et dim^lun 23h à 05h"," ",56493]
["2025-08-09","2025-12-19","SE",1,"167","A","Y.AUTELBAS","ATHUS-FRONTIERE","AllWeek","Night","06:00","22:00","Nouvelle électrification faisceau A","SAVU","Minor_AdHoc","Gare d'Athus comprise\r\nImpact voie 705, 706, 707, 708, 709, 710, 711, 712+ VA L167\r\nnécessité d'avoir 60 prestations de 8h"," ",56492]
["2025-08-11","2025-08-15","SE",1,"130/1","A+B","JEMEPPE-FROIDMONT","MOUSTIER-GARAGE","Week","Day","09:00","15:00","Linked to coupure nr 59473 on line 144 tracks(s) A/B from GEMBLOUX to JEMEPPE-SUR-SAMBRE-MARCHANDISE: Electrification Gare de Jemeppe Sur Sambre\r\nTransfert L130/1 du cas 26690","CTL","Minor_AdHoc"," "," ",59473]
["2025-08-11","2025-08-15","SE",1,"144","A/B","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE","Week","Day","09:00","15:00","Electrification Gare de Jemeppe Sur Sambre\r\nTransfert L130/1 du cas 26690","CTL","Minor_AdHoc","5 jours (en 9h-15h) L130/1 et L144"," ",59473]
["2025-08-11","2025-08-16","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u\r\n\r\nnog te bepalen of/wanneer werken door gaan","CTL","Minor_AdHoc","geen impact L25N!"," ",58744]
["2025-08-11","2025-08-16","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","23:00","05:45","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 5 -Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architectonique\r\nPhase 5.1 – CTL L75 de","CTL","Minor_AdHoc","Travaux de nuit  du 11/08 au 23/08/2025 de 23h à 5h45​"," ",55882]
["2025-08-11","2025-09-27","NE",1,"25","A+B","MECHELEN","MECHELEN","AllWeek","Continuous","04:00","01:00","bijkomende aanvraag renovatie Vaartbrug  ipv vernieuwing\r\n\r\n\r\nTLO lijn 25 gedurende 7 weken. Impact deels icm CoLT 58490 (renovatie kruisingsbrug 2 weken september 2025)\r\n\r\nZie goedgekeurd dossier: 2024 - L25 - Mechelen-Y. Abeelstraat","CTL","Major","TLO L25 A+B in continu van Mechelen tot Mechelen\r\nTLO L25 A+B uitbreiding tijdens weekends van Y.Abeelstraat tot Mechelen inbegrepen."," ",62721]
["2025-08-14","2025-08-18","SE",1,"161","A+B","OTTIGNIES","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER\r\nGare Ottignies","Autre","Minor_AdHoc","voies 4 et 5 à quai HS\r\n+ Voie 3 à quai inaccessible côté Bruxelles\r\nVoie 142 HS \r\nPas de lien L161-L139 et L161-L140. PED SNCB inaccessible. Circulation L161 vers Namur à contrevoie en gare"," ",59180]
["2025-08-15","2025-08-18","CE",1,"161","A+B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL","CTL","Medium","sp 3 +4 BDS"," ",59769]
["2025-08-15","2025-08-18","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n18 - Déroulage Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","1 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 17)"," ",59634]
["2025-08-15","2025-08-18","SW",1,"112","A+B","MARCHIENNE-AU-PONT","LA LOUVIERE-SUD","AllWeek","Continuous","09:30","04:40","Renouvellement chapes PI 13.823 + 14.636 + 17.664","CTL","Medium","ART 40km/h pendant 14 jours après CTL.\r\nHKV : + 2min12s"," ",55510]
["2025-08-16","2025-08-18","NE",1,"25","A+B","MECHELEN","Y.ABEELSTRAAT","Weekend","Continuous","01:00","04:00","bijkomende aanvraag renovatie Vaartbrug  ipv vernieuwing\r\n\r\n\r\nTLO lijn 25 gedurende 7 weken. Impact deels icm CoLT 58490 (renovatie kruisingsbrug 2 weken september 2025)\r\n\r\nZie goedgekeurd dossier: 2024 - L25 - Mechelen-Y. Abeelstraat","CTL","Medium","TLO L25 A+B tijdens weekends van Y.Abeelstraat tot Mechelen inbegrepen.\r\nTLO L25 A+B tijdens weeknachten van Mechelen tot Mechelen."," ",62703]
["2025-08-16","2025-08-18","NE",1,"27B","A+B","Y.WEERDE","MUIZEN-ROOSTER T","Weekend","Continuous","00:01","04:00","Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek","CTL","Medium","BTS vanaf eerste weekend tem laatste weekend na lange TLO:\r\nHKV:4'\r\nHKM: 8'"," ",57971]
["2025-08-16","2025-08-18","NE",1,"27B/1","A+B","Y.PRINSENHOEK","Y.HEVER","Weekend","Continuous","00:01","04:00","Linked to coupure nr 57971 on line 27B tracks(s) A+B from Y.WEERDE to MUIZEN-ROOSTER T: Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek","CTL","Medium"," "," ",57971]
["2025-08-18","2025-08-20","SW",1,"112","A+B","MARCHIENNE-AU-PONT","LA LOUVIERE-SUD","Week","Night","22:50","04:40","Renouvellement chapes PI 13.823 + 14.636 + 17.664. \r\nNuits de finition soudures","CTL","Minor_AdHoc"," "," ",55516]
["2025-08-18","2025-08-22","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","Week","Night","23:00","05:00","P723301: Renovatiewerken perron 3 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL","Autre","Minor_AdHoc","sp 3 BDS"," ",59770]
["2025-08-18","2025-08-23","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58746]
["2025-08-18","2025-08-23","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59227 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59227]
["2025-08-18","2025-08-23","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59227 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59227]
["2025-08-18","2025-08-23","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59227]
["2025-08-18","2025-08-23","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59227 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59227]
["2025-08-18","2025-08-23","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n19 - Dépose traverses Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","1 semaine SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 18)"," ",59635]
["2025-08-18","2025-08-23","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","23:00","05:45","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 5 -Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architectonique\r\nPhase 5.1 – CTL L75 de","CTL","Minor_AdHoc","Travaux de nuit  du 11/08 au 23/08/2025 de 23h à 5h45​"," ",61850]
["2025-08-18","2025-08-31","SW",1,"75A","A","MOUSCRON","FROYENNES","AllWeek","Day","09:00","15:00","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4.","SAVU","Minor_AdHoc","SAVU + S460 travaux de piste"," ",39589]
["2025-08-18","2025-09-01","SW",1,"112","A+B","MARCHIENNE-AU-PONT","LA LOUVIERE-SUD","AllWeek","Continuous","04:40","05:00","ART 40km/h\r\nRenouvellement chapes PI 13.823 + 14.636 + 17.664","ART","Minor_AdHoc","ART 40km/h pendant 14 jours après CTL.\r\nHKV : + 2min12s"," ",59439]
["2025-08-22","2025-08-25","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:30","04:30","Linked to coupure nr 59771 on line 25 tracks(s) B from SCHAERBEEK to SCHAERBEEK: P723301: Renovatiewerken perron 4 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL en sp B L25 tss 26AH en 50XL","Autre","Minor_AdHoc"," "," ",59771]
["2025-08-22","2025-08-25","CE",1,"25","B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:30","04:30","P723301: Renovatiewerken perron 4 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL en sp B L25 tss 26AH en 50XL","SAVU","Minor_AdHoc","sp B L25 BDS - FSR sporen 4+5 BDS"," ",59771]
["2025-08-23","2025-08-24","SW",1,"130","A+B","TAMINES","CHATELET-GRIL OUEST","Weekend","Continuous","06:00","17:00","Maintenance Z15. 51 P4+","CTL","Medium"," "," ",53525]
["2025-08-23","2025-08-25","NE",1,"25","A+B","MECHELEN","Y.ABEELSTRAAT","Weekend","Continuous","01:00","04:00","bijkomende aanvraag renovatie Vaartbrug  ipv vernieuwing\r\n\r\n\r\nTLO lijn 25 gedurende 7 weken. Impact deels icm CoLT 58490 (renovatie kruisingsbrug 2 weken september 2025)\r\n\r\nZie goedgekeurd dossier: 2024 - L25 - Mechelen-Y. Abeelstraat","CTL","Medium","TLO L25 A+B tijdens weekends van Y.Abeelstraat tot Mechelen inbegrepen.\r\nTLO L25 A+B tijdens weeknachten van Mechelen tot Mechelen."," ",62704]
["2025-08-23","2025-09-01","NE",1,"27B","A+B","Y.WEERDE","MUIZEN-ROOSTER T","AllWeek","Continuous","00:10","04:00","Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek\r\n+ BVL Y Weerde - Y Prinsenhoek \r\n+ RTB L27B/1","CTL","High","HKV:4'\r\nHKM: 8'"," ",57970]
["2025-08-23","2025-09-01","NE",1,"27B/1","A+B","Y.PRINSENHOEK","Y.HEVER","AllWeek","Continuous","00:10","04:00","Linked to coupure nr 57970 on line 27B tracks(s) A+B from Y.WEERDE to MUIZEN-ROOSTER T: Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek\r\n+ BVL Y Weerde - Y Prinsenhoek \r\n+ RTB L27B/1","CTL","High"," "," ",57970]
["2025-08-24","2025-09-28","SE",1,"34","A+B","LIEGE-GUILLEMINS","HERSTAL","AllWeek","Continuous","22:00","22:00","ART\r\nMassification L34\r\nDossier de concertation octobre 2022","ART","Minor_AdHoc","1 mois 40km/h entre env. km 5.500 et 5.900 VA et VB\r\nVitesse réduite HKM: 3.2 et HKV: 1.2"," ",59531]
["2025-08-25","2025-08-29","SW",1,"75A","A+B","MOUSCRON","FROYENNES","Week","Night","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 5 - Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architectonique\r\nPhase 5.2 – CTL L75A+","CTL","Minor_AdHoc","Phase 5.2 – CTL L75A+Faisceau de nuit de semaine\r\nTravaux de nuit du 25/08 au 06/09/2025 de 22h30 à 4h10​"," ",39558]
["2025-08-25","2025-08-30","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58747]
["2025-08-25","2025-08-30","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59228 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59228]
["2025-08-25","2025-08-30","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59228 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59228]
["2025-08-25","2025-08-30","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59228]
["2025-08-25","2025-08-30","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59228 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59228]
["2025-08-25","2025-09-01","SW",1,"112","A+B","MARCHIENNE-AU-PONT","LA LOUVIERE-SUD","AllWeek","Night","22:50","04:40","Renouvellement chapes PI 13.823 + 14.636 + 17.664. \r\nNuits de finition: révision, régulations, finitions, enlèvement ART","CTL","Minor_AdHoc"," "," ",55528]
["2025-08-25","2025-09-07","SE",1,"42","S","AYWAILLE","STOUMONT","AllWeek","Continuous","05:00","05:00","ART 3min\r\nCriblage de ballast\r\nART de stabilisation","ART","Minor_AdHoc","Perte de temps HKV : 3'"," ",59540]
["2025-08-25","2025-09-20","SE",1,"42","A+B","AYWAILLE","TROIS-PONTS","AllWeek","Night","23:00","05:00","Criblage: bourrage, contraintes et finitions","CTL","Minor_AdHoc",null," ",55814]
["2025-08-25","2025-09-20","SW",1,"75A","*","HERSEAUX","MOUSCRON","Week","Day","06:00","16:00","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 5 - Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architectonique\r\nPhase 5.3 –MHS du fai","Autre","Minor_AdHoc","Phase 5.3 – MHS du faisceau de jour\r\nTravaux de jour  du 25/08 au 20/09/2025 de 6h à 16h"," ",55885]
["2025-08-29","2025-09-01","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:30","04:30","Linked to coupure nr 59772 on line 25 tracks(s) B from SCHAERBEEK to SCHAERBEEK: P723301: Renovatiewerken perron 4 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL en sp B L25 tss 26AH en 50XL","Autre","Minor_AdHoc"," "," ",59772]
["2025-08-29","2025-09-01","CE",1,"25","B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:30","04:30","P723301: Renovatiewerken perron 4 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL en sp B L25 tss 26AH en 50XL","SAVU","Minor_AdHoc","sp B L25 BDS - FSR sporen 4+5 BDS"," ",59772]
["2025-08-29","2025-09-01","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n20 - Déroulage Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","1 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 19)"," ",59636]
["2025-08-29","2025-09-01","SE",1,"42","A+B","RIVAGE","AYWAILLE","Weekend","Continuous","23:55","05:00","Entretien manuel et mécanisés des AW de Rivage et Rivage Marchandise\r\nEntretien manuel et mécanisés des PN","CTL","Medium","L42 + L43"," ",55081]
["2025-08-29","2025-09-01","SE",1,"43","A+B","TILFF","BOMAL","Weekend","Continuous","23:55","05:00","Linked to coupure nr 55081 on line 42 tracks(s) A+B from RIVAGE to AYWAILLE: Entretien manuel et mécanisés des AW de Rivage et Rivage Marchandise\r\nEntretien manuel et mécanisés des PN","CTL","Medium"," "," ",55081]
["2025-08-29","2025-09-01","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 minutes"," ",54944]
["2025-08-30","2025-08-31","SW",1,"130A","A+B","ERQUELINNES-FRONTIERE","LA SAMBRE","Weekend","Continuous","06:00","17:00","Maintenance Z2. 51  P4+","CTL","Medium"," "," ",53534]
["2025-08-30","2025-09-01","NE",1,"25","A+B","MECHELEN","Y.ABEELSTRAAT","Weekend","Continuous","01:00","04:00","bijkomende aanvraag renovatie Vaartbrug  ipv vernieuwing\r\n\r\n\r\nTLO lijn 25 gedurende 7 weken. Impact deels icm CoLT 58490 (renovatie kruisingsbrug 2 weken september 2025)\r\n\r\nZie goedgekeurd dossier: 2024 - L25 - Mechelen-Y. Abeelstraat","CTL","Medium","TLO L25 A+B tijdens weekends van Y.Abeelstraat tot Mechelen inbegrepen.\r\nTLO L25 A+B tijdens weeknachten van Mechelen tot Mechelen."," ",62705]
["2025-09-01","2025-09-04","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Week","Night","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Coupure type 3​\r\nSem 36: 1^2 – 2^3 - 3^4/09/2025 de 23h à 5h + voie du Car wash"," ",54838]
["2025-09-01","2025-09-05","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58748]
["2025-09-01","2025-09-05","SW",1,"90C","A+B","JURBISE","ATH","Week","Night","23:00","05:00","Travaux de construction d'un PI au droit du km 51.775 en vue de la suppression du PN5 + renouvellement de l'étanchéité des PI 52.279 et 58.656\r\nNuits de préparation","CTL","Minor_AdHoc"," "," ",55539]
["2025-09-01","2025-09-06","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59230 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59230]
["2025-09-01","2025-09-06","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59230 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59230]
["2025-09-01","2025-09-06","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59230]
["2025-09-01","2025-09-06","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59230 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59230]
["2025-09-01","2025-09-06","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n21 - Dépose traverses Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","1 semaines SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 20)"," ",59637]
["2025-09-01","2025-09-06","SW",1,"75A","A+B","MOUSCRON","FROYENNES","Week","Night","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 5 - Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architectonique\r\nPhase 5.2 – CTL L75A+","CTL","Minor_AdHoc","Phase 5.2 – CTL L75A+Faisceau de nuit de semaine\r\nTravaux de nuit du 25/08 au 06/09/2025 de 22h30 à 4h10​"," ",61851]
["2025-09-01","2025-09-19","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET","AllWeek","Continuous","06:00","23:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Coupure type 1 \r\nEn continu : \r\nFaisceau A HS (stand gazoil uniquement accessible en diesel coté Charleroi)\r\ncas 27331 HT\r\nFaisceau B accessible uniquement coté Campinaire\r\nFaisceau D : voies 360-361 exploitables\r\nFaisceau K inaccessible\r\nART L130 VA+B "," ",53233]
["2025-09-01","2025-09-20","SW",1,"94","A+B","HALLE","ENGHIEN","Week","Night","22:30","04:40","Renouvellement des traverses P93 entre Enghien et Halle\r\nTravaux préparatoires","CTL","Minor_AdHoc","CTL de nuit"," ",53254]
["2025-09-01","2025-09-29","SE",1,"162","A","HATRIVAL","LIBRAMONT","AllWeek","Continuous","06:00","05:00","Remplacement de filet de sécurisation sur parois rocheuses (Galva --> Inox)","SAVU","High"," "," ",55279]
["2025-09-01","2025-10-04","SW",1,"130","A+B","CHATELET-GRIL EST","CHATELET","AllWeek","Continuous","06:00","23:00","ART 1/3min\r\nAménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART de stabilisation en VB L130 & protection en VA L130 (HKV: 0,78min & HKM: 2,67min) du 1/09 au 4/10"," ",61860]
["2025-09-01","2026-03-31","NW",1,"75","*","KORTRIJK","KORTRIJK","AllWeek","Continuous","00:00","00:00","Vernieuwen by-pass tussen wissel 20AC/21BC en wissel 12C","Autre","Minor_AdHoc"," "," ",60387]
["2025-09-02","2025-09-27","SW",1,"130","A+B","CHATELET","CHATELET","AllWeek","Continuous","05:00","23:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","liaisons 36AI - 37AI - 36BI - 38 AI - 37BI du 02/09 à 5h jusqu'au 27/09 à 23h"," ",54844]
["2025-09-04","2025-09-16","SW",1,"130","B","LE CAMPINAIRE","CHATELET-GRIL OUEST","AllWeek","Night","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Complément 53233\r\nCoupure Type 2\r\nSAVU VB HS"," ",54840]
["2025-09-05","2025-09-08","CE",1,"161","B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:30","04:30","Linked to coupure nr 59773 on line 25 tracks(s) A+B from SCHAERBEEK to SCHAERBEEK: P723301: Renovatiewerken perron 4 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL, sp A L25 tss 27AH en 49XL,  en sp B L25 tss 26AH en 50XL","Autre","Minor_AdHoc"," "," ",59773]
["2025-09-05","2025-09-08","CE",1,"25","A+B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:30","04:30","P723301: Renovatiewerken perron 4 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL, sp A L25 tss 27AH en 49XL,  en sp B L25 tss 26AH en 50XL","Autre","Minor_AdHoc","sp A en B L25 BDS - FSR sporen 4+5+6 BDS"," ",59773]
["2025-09-05","2025-09-08","SE",1,"161","A","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER\r\n Rq 333 : demande EF's suite semestrielle :  5 SAVU et une CTL sur une relation, replan à prévoir\r\nRéunion 17/10 : analyse par I-CBE pour proposer un autre WE","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59169]
["2025-09-05","2025-09-08","SE",1,"161","A+B","GEMBLOUX","NAMUR","Weekend","Continuous","23:50","04:30","Criblage du ballast (C75)\r\n Rq 333 : demande EF's suite semestrielle :  demande déplacer pendant les vacances d'été + pas de contrainte L130/144","CTL","Medium","ART :  3min VA : du 05/09/25 au 17/09/25 entre Bk 53.800 et 55.500\r\nART : 3 min VB du 12/09/25 au 24/09/23 entre Bk 53.800 et 55.430"," ",56447]
["2025-09-05","2025-09-08","SW",1,"90C","A+B","JURBISE","ATH","Weekend","Continuous","23:00","05:00","Travaux de construction d'un PI au droit du km 51.775 en vue de la suppression du PN5 + renouvellement de l'étanchéité des PI 52.279 et 58.656\r\nCTL de WE en continu pour le ripage du pont-cadre + le renouvellement de l'étanchéité des 2 PI.\r\nRq 333 : dem","CTL","Medium"," "," ",55558]
["2025-09-05","2025-09-22","SW",1,"97","*","Y.CRIQUELION","SAINT-GHISLAIN","AllWeek","Continuous","22:30","04:30","Renouvellement des AS tête de faisceau de triage","Autre","Minor_AdHoc","Fermeture en continu de l'accès côté Quiévrain (pas d'accès via L78 - voie 208 HS)\r\nCirculation réduite dans le faisceau\r\nMise HT des cas 28727-725-723"," ",53256]
["2025-09-05","2025-09-24","SE",1,"161","A+B","GEMBLOUX","NAMUR","AllWeek","Continuous","23:50","04:30","ART 3min\r\nCriblage du ballast (C75) - bourrage de révision, contraintes fintions,..","CTL","High","ART :  3min VA : du 05/09/25 au 17/09/25 entre Bk 53.800 et 55.500\r\nART : 3 min VB du 12/09/25 au 24/09/23 entre Bk 53.800 et 55.430"," ",59644]
["2025-09-06","2025-09-08","NE",1,"25","A","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nenkel sp A --> Mechelen perronspoor A tot Mechelen Dijkstraat --> invloed L25N --> komt op 1 spoor te Nekkerspoel\r\nzie schets 'expl A-L25' (tabblad schet","CTL","Medium","impact L25N ? --> komt op 1 spoor te Nekkerspoel"," ",58759]
["2025-09-06","2025-09-08","NE",1,"25","A+B","MECHELEN","Y.ABEELSTRAAT","Weekend","Continuous","01:00","04:00","bijkomende aanvraag renovatie Vaartbrug  ipv vernieuwing\r\n\r\n\r\nTLO lijn 25 gedurende 7 weken. Impact deels icm CoLT 58490 (renovatie kruisingsbrug 2 weken september 2025)\r\n\r\nZie goedgekeurd dossier: 2024 - L25 - Mechelen-Y. Abeelstraat","CTL","Medium","TLO L25 A+B tijdens weekends van Y.Abeelstraat tot Mechelen inbegrepen.\r\nTLO L25 A+B tijdens weeknachten van Mechelen tot Mechelen."," ",62707]
["2025-09-06","2025-09-08","NE",1,"27B","A+B","Y.WEERDE","MUIZEN-ROOSTER T","Weekend","Continuous","00:01","04:00","Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek","CTL","Medium","BTS vanaf eerste weekend tem laatste weekend na lange TLO:\r\nHKV:4'\r\nHKM: 8'"," ",57972]
["2025-09-06","2025-09-08","NE",1,"27B/1","A+B","Y.PRINSENHOEK","Y.HEVER","Weekend","Continuous","00:01","04:00","Linked to coupure nr 57972 on line 27B tracks(s) A+B from Y.WEERDE to MUIZEN-ROOSTER T: Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek","CTL","Medium"," "," ",57972]
["2025-09-06","2025-09-22","NW",1,"59","A+B","SINT-NIKLAAS","SINT-NIKLAAS-OOST","AllWeek","Continuous","06:00","04:00","Vernieuwen bundelkop Sint Niklaas Oost \r\nvoor de zichtbaarheid ingepland op L59 \r\nDe impact van de werken beperkt zich enkel tot de bundel Sint Niklaas-Oost\r\n\r\nI-AM bekijkt of het mogelijk is om deze werken gefaseerd uit te voeren.","Autre","Minor_AdHoc"," "," ",58624]
["2025-09-08","2025-09-12","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58749]
["2025-09-08","2025-09-13","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59232 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59232]
["2025-09-08","2025-09-13","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59232 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59232]
["2025-09-08","2025-09-13","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59232]
["2025-09-08","2025-09-13","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59232 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59232]
["2025-09-08","2025-09-13","SW",1,"116/1","A+B","Y.FAMILLEUREUX","Y.BOIS-D'HAINE","Week","Night","23:10","05:30","Linked to coupure nr 56120 on line 117 tracks(s) A+B from BRAINE-LE-COMTE to MANAGE: Programme de révision caténaire","CTL","Minor_AdHoc"," "," ",56120]
["2025-09-08","2025-09-13","SW",1,"117","A+B","BRAINE-LE-COMTE","MANAGE","Week","Night","23:10","05:30","Programme de révision caténaire","CTL","Minor_AdHoc","CTL de nuit - Amplitude élargie"," ",56120]
["2025-09-08","2025-09-13","SW",1,"140","A+B","OTTIGNIES","LODELINSART","Week","Night","23:00","05:00","Renouvellement Pi métalliques 52.015 et 52.215\r\nPréparations","CTL","Minor_AdHoc","Gare de Fleurus incluse"," ",55532]
["2025-09-08","2025-09-13","SW",1,"90C","A+B","JURBISE","ATH","Week","Night","23:00","05:00","Travaux de construction d'un PI au droit du km 51.775 en vue de la suppression du PN5 + renouvellement de l'étanchéité des PI 52.279 et 58.656\r\nNuits de finitions","CTL","Minor_AdHoc"," "," ",55540]
["2025-09-08","2025-09-26","CE",1,"96","B","BRUXELLES-MIDI","LOT","Week","Night","23:30","05:00","Linked to coupure nr 58369 on line 96N tracks(s) B from Y.NOORD HALLE to BRUXELLES-MIDI: Y.Ruisbroek - Renouvellement Aiguillages - Phase 2\r\nPréparation","SAVU","Minor_AdHoc"," "," ",58369]
["2025-09-08","2025-09-26","CE",1,"96N","B","Y.NOORD HALLE","BRUXELLES-MIDI","Week","Night","23:30","05:00","Y.Ruisbroek - Renouvellement Aiguillages - Phase 2\r\nPréparation","SAVU","Minor_AdHoc"," "," ",58369]
["2025-09-08","2025-12-12","SW",1,"117","A/B","Y.FELUY","Y.ECAUSSINNES","Week","Day","09:00","15:00","Programme de révision caténaire - Phase 2","SAVU","Minor_AdHoc","SAVU Voie A/B\r\nCoupures de jour (9h-15h) limitées à une seule voie sur le tronçon entre B-L-C et Manage."," ",56177]
["2025-09-12","2025-09-15","CE",1,"161","A","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:30","04:30","Linked to coupure nr 59774 on line 25 tracks(s) A+B from SCHAERBEEK to SCHAERBEEK: P723301: Renovatiewerken perron 4 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL, sp A L25 tss 27AH en 49XL,  en sp B L25 tss 26AH en 50XL","Autre","Minor_AdHoc"," "," ",59774]
["2025-09-12","2025-09-15","CE",1,"25","A+B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","23:30","04:30","P723301: Renovatiewerken perron 4 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL, sp A L25 tss 27AH en 49XL,  en sp B L25 tss 26AH en 50XL","Autre","Minor_AdHoc","sp A en B L25 BDS - FSR sporen 4+5+6 BDS"," ",59774]
["2025-09-12","2025-09-15","SE",1,"161","A+B","GEMBLOUX","NAMUR","Weekend","Continuous","23:50","04:30","Criblage du ballast (C75)","CTL","Medium","ART :  3min VA : du 05/09/25 au 17/09/25 entre Bk 53.800 et 55.500\r\nART : 3 min VB du 12/09/25 au 24/09/23 entre Bk 53.800 et 55.430"," ",56448]
["2025-09-12","2025-09-15","SE",1,"161","A+B","OTTIGNIES","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER\r\nGare Ottignies","Autre","Minor_AdHoc","voies 4 et 5 à quai HS\r\n+ Voie 3 à quai inaccessible côté Bruxelles\r\nVoie 142 HS \r\nPas de lien L161-L139 et L161-L140. PED SNCB inaccessible. Circulation L161 vers Namur à contrevoie en gare"," ",59178]
["2025-09-12","2025-09-15","SE",1,"166","A+B","HOUYET","BEAURAING","Weekend","Continuous","23:00","04:30","Assainissement bk 16.200\r\nDossier concertation octobre 2022","CTL","Medium","ART de stabilisation de 5 jours (date de fin probable le 20/9).\r\nART de 3 minutes inclus id 55572","HKM à adapter",56543]
["2025-09-13","2025-09-15","NE",1,"21","A+B","HASSELT","ALKEN","Weekend","Continuous","00:01","04:00","Linked to coupure nr 57990 on line 34 tracks(s) A+B from HASSELT to Y.ROOIERWEG: Vernieuwing 4 wissels L34/L21 (02AU; 02BU; 01AU; 01BU)","CTL","Medium"," ","BTS van 3' voor HKM",57990]
["2025-09-13","2025-09-15","NE",1,"25","A","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:01","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nenkel sp A --> Mechelen perronspoor A tot Mechelen Dijkstraat --> invloed L25N --> komt op 1 spoor te Nekkerspoel\r\nzie schets 'expl A-L25' (tabblad schet","CTL","Medium","impact L25N ? --> komt op 1 spoor te Nekkerspoel"," ",58760]
["2025-09-13","2025-09-15","NE",1,"25","A+B","MECHELEN","Y.ABEELSTRAAT","Weekend","Continuous","01:00","04:00","bijkomende aanvraag renovatie Vaartbrug  ipv vernieuwing\r\n\r\n\r\nTLO lijn 25 gedurende 7 weken. Impact deels icm CoLT 58490 (renovatie kruisingsbrug 2 weken september 2025)\r\n\r\nZie goedgekeurd dossier: 2024 - L25 - Mechelen-Y. Abeelstraat","CTL","Medium","TLO L25 A+B tijdens weekends van Y.Abeelstraat tot Mechelen inbegrepen.\r\nTLO L25 A+B tijdens weeknachten van Mechelen tot Mechelen."," ",62709]
["2025-09-13","2025-09-15","NE",1,"27B/1","A+B","Y.PRINSENHOEK","Y.HEVER","Weekend","Continuous","00:00","04:00","Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek","CTL","Medium","Inclusief L53 !\r\n\r\nIndien volledig apart weekend --> aparte BTS, anders BTS mee in lange TLO BTS\r\naparte BTS tot weekend na de werken:\r\nHKV: 1,5'\r\nHKM: 3,5'"," ",57973]
["2025-09-13","2025-09-15","NE",1,"34","A+B","HASSELT","Y.ROOIERWEG","Weekend","Continuous","00:01","04:00","Vernieuwing 4 wissels L34/L21 (02AU; 02BU; 01AU; 01BU)","CTL","Medium","BTS: Wisselzone is al 40k/u, dus enkel misschien BTS L34 sp A (afhankelijk van de werken): 90 km/u naar 40km/u: HKV: 1,2 min; HKM, 3,2 min in week tussen grote TLO en herziening.","BTS van 3' voor HKM",57990]
["2025-09-13","2025-09-15","NE",1,"53","A+B","MECHELEN","LEUVEN","Weekend","Continuous","00:00","04:00","Linked to coupure nr 57973 on line 27B/1 tracks(s) A+B from Y.PRINSENHOEK to Y.HEVER: Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek","CTL","Medium"," "," ",57973]
["2025-09-13","2025-09-29","NE",1,"25","A+B","VILVOORDE","Y.ABEELSTRAAT","AllWeek","Continuous","00:00","04:00","TLO 2 weken continu (wegens geschrapt in 2024\r\nRenovatie kruisingsbrug L27/L25 - geen impact L27","CTL","High"," "," ",58490]
["2025-09-15","2025-09-18","SE",1,"130","A","FRANIERE","MOUSTIER","Week","Night","23:00","05:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Il faut limiter le nombre de trains par heure à 4 maximum :​\r\nnuits 15-16, 16-17 et 17-18/09​ + du 18/9 23h00 au 23/09 5h00"," ",61864]
["2025-09-15","2025-09-19","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58750]
["2025-09-15","2025-09-19","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60983]
["2025-09-15","2025-09-19","SW",1,"140","A+B","OTTIGNIES","LODELINSART","Week","Night","23:00","05:00","Renouvellement Pi métalliques 52.015 et 52.215\r\nPréparations","CTL","Minor_AdHoc","Gare de Fleurus incluse"," ",55533]
["2025-09-15","2025-09-20","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59233 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59233]
["2025-09-15","2025-09-20","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59233 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59233]
["2025-09-15","2025-09-20","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59233]
["2025-09-15","2025-09-20","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59233 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59233]
["2025-09-15","2025-09-20","SE",1,"161","A+B","GEMBLOUX","NAMUR","Week","Night","23:50","04:30","Criblage du ballast (C75) - bourrage de révision, contraintes fintions,..","CTL","Minor_AdHoc","ART :  3min VA : du 05/09/25 au 17/09/25 entre Bk 53.800 et 55.500\r\nART : 3 min VB du 12/09/25 au 24/09/23 entre Bk 53.800 et 55.430"," ",56449]
["2025-09-15","2025-09-20","SW",1,"116/1","A+B","Y.FAMILLEUREUX","Y.BOIS-D'HAINE","Week","Night","23:10","05:30","Linked to coupure nr 56121 on line 117 tracks(s) A+B from BRAINE-LE-COMTE to MANAGE: Programme de révision caténaire","CTL","Minor_AdHoc"," "," ",56121]
["2025-09-15","2025-09-20","SW",1,"117","A+B","BRAINE-LE-COMTE","MANAGE","Week","Night","23:10","05:30","Programme de révision caténaire","CTL","Minor_AdHoc","CTL de nuit - Amplitude élargie"," ",56121]
["2025-09-15","2025-09-20","SW",1,"90C","A+B","JURBISE","ATH","Week","Night","22:00","06:00","Travaux de construction d'un PI au droit du km 51.775 en vue de la suppression du PN5 + renouvellement de l'étanchéité des PI 52.279 et 58.656\r\nNuits de finitions et enlèvement ART","CTL","Minor_AdHoc"," "," ",55541]
["2025-09-15","2025-11-09","CE",1,"161","*","SCHAERBEEK","SCHAERBEEK","AllWeek","Continuous","(vide)","(vide)","P149301: Renovatiewerken perron 4 Schaarbeek Reizigers","Autre","Minor_AdHoc"," "," ",50051]
["2025-09-15","2025-11-24","SE",1,"166","A/B","HOUYET","BEAURAING","AllWeek","Continuous","08:00","06:00","Assainissement bk 16.200.\r\nDossier concertation octobre 2022","SAVU","High","Voie A  5 semaines (15/09 au 19/10)\r\nVoie B 5 semaines (20/10 au 24/11)\r\nTous les WE : CTL  nuit sam^dim et dim^lun 23h à 05h\r\nART protection 3min"," ",55572]
["2025-09-16","2025-09-19","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Week","Night","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Coupure type 3​\r\nSem 38: 16^17 – 17^18 - 18^19/09/2025 de 23h à 5h"," ",54839]
["2025-09-18","2025-09-23","SE",1,"130","A","FRANIERE","MOUSTIER","AllWeek","Continuous","23:00","05:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","ART 1 à 60Km/h (suite Stabilisatrice) de 3’ HKV et 2’ HKM VA + VB du 18/09 23h00 au lundi 29/09 à 05h00​\r\nPour travailler avec un ART de protection à 60km/h, il faut limiter le nombre de trains par heure à 4 maximum :​\r\nnuits 15-16, 16-17 et 17-18/09​\r\n"," ",55833]
["2025-09-18","2025-09-29","SE",1,"130","B","FLAWINNE","MOUSTIER","AllWeek","Continuous","23:00","05:00","ART 3min\r\nCriblage voie B Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART 1 à 60Km/h (suite Stabilisatrice) de 3’ HKV et 2’ HKM VA + VB du 18/09 23h00 au lundi 29/09 à 05h00​\r\nPour travailler avec un ART de protection à 60km/h, il faut limiter le nombre de trains par heure à 4 maximum :​\r\nnuits 15-16, 16-17 et 17-18/09​\r\n"," ",59615]
["2025-09-19","2025-09-22","CE",1,"96","B","BRUXELLES-MIDI","LOT","Weekend","Continuous","23:30","05:00","Linked to coupure nr 58367 on line 96N tracks(s) B from Y.NOORD HALLE to BRUXELLES-MIDI: Y.Ruisbroek - Renouvellement Aiguillages - Phase 2\r\nWE 1/2 Travaux","SAVU","Minor_AdHoc"," "," ",58367]
["2025-09-19","2025-09-22","CE",1,"96N","B","Y.NOORD HALLE","BRUXELLES-MIDI","Weekend","Continuous","23:30","05:00","Y.Ruisbroek - Renouvellement Aiguillages - Phase 2\r\nWE 1/2 Travaux","SAVU","Minor_AdHoc"," "," ",58367]
["2025-09-19","2025-09-22","SE",1,"130","A","FLAWINNE","MOUSTIER","Weekend","Continuous","23:00","05:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","CTL","Medium",null," ",56354]
["2025-09-19","2025-09-22","SE",1,"161","A+B","WATERMAEL","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER\r\n Rq 333 : demande EF's suite semestrielle : Rien d'autre L161","CTL","Medium","ART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59161]
["2025-09-19","2025-09-22","SW",1,"130","A+B","TAMINES","CHATELET-GRIL OUEST","Weekend","Continuous","23:00","05:00","Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022","CTL","Medium","A la remise en service, liaisons 36AI - 37AI - 36BI - 38 AI - 37BI du 02/09 à 5h jusqu'au 27/09 à 23h"," ",54841]
["2025-09-19","2025-09-22","SW",1,"140","A+B","OTTIGNIES","FLEURUS","Weekend","Continuous","23:00","05:00","Renouvellement Pi métalliques 52.015 et 52.215\r\nCTL WE","CTL","Medium","ART 2 min pendant 3 semaines\r\nCas 27243-244 HT"," ",55534]
["2025-09-20","2025-09-22","NE",1,"25","A","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:01","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nenkel sp A --> Mechelen perronspoor A tot Mechelen Dijkstraat --> invloed L25N --> komt op 1 spoor te Nekkerspoel\r\nzie schets 'expl A-L25' (tabblad schet","CTL","Medium","impact L25N ? --> komt op 1 spoor te Nekkerspoel"," ",58761]
["2025-09-20","2025-09-22","NE",1,"25","A+B","MECHELEN","Y.ABEELSTRAAT","Weekend","Continuous","01:00","04:00","bijkomende aanvraag renovatie Vaartbrug  ipv vernieuwing\r\n\r\n\r\nTLO lijn 25 gedurende 7 weken. Impact deels icm CoLT 58490 (renovatie kruisingsbrug 2 weken september 2025)\r\n\r\nZie goedgekeurd dossier: 2024 - L25 - Mechelen-Y. Abeelstraat","CTL","Medium"," "," ",62710]
["2025-09-22","2025-09-26","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60984]
["2025-09-22","2025-09-27","CE",1,"25","B","SCHAERBEEK","VILVOORDE","Week","Night","23:00","05:00","Vernieuwing Albertbrug fase 2: voorbereidende werken afbraak brugdeel 6","CTL","Minor_AdHoc","DOES L25"," ",62036]
["2025-09-22","2025-09-27","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58751]
["2025-09-22","2025-09-27","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59234 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: R-384580\r\n\r\nStap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 5","SAVU","Minor_AdHoc"," "," ",59234]
["2025-09-22","2025-09-27","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59234 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: R-384580\r\n\r\nStap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 5","CTL","Minor_AdHoc"," "," ",59234]
["2025-09-22","2025-09-27","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","R-384580\r\n\r\nStap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59234]
["2025-09-22","2025-09-27","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59234 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: R-384580\r\n\r\nStap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 5","SAVU","Minor_AdHoc"," "," ",59234]
["2025-09-22","2025-09-27","SE",1,"161","A+B","GEMBLOUX","NAMUR","Week","Night","23:50","04:30","Criblage du ballast (C75) - bourrage de révision, contraintes fintions,..","CTL","Minor_AdHoc","ART :  3min VA : du 05/09/25 au 17/09/25 entre Bk 53.800 et 55.500\r\nART : 3 min VB du 12/09/25 au 24/09/23 entre Bk 53.800 et 55.430"," ",56450]
["2025-09-22","2025-09-27","SW",1,"116/1","A+B","Y.FAMILLEUREUX","Y.BOIS-D'HAINE","Week","Night","23:10","05:30","Linked to coupure nr 56122 on line 117 tracks(s) A+B from BRAINE-LE-COMTE to MANAGE: Programme de révision caténaire\r\nRq 333 : rq Ef's suite semestrielle : Niet ok in combinatie met werken L117 Braine-Le Comte-Manage én L124 Y.Forest-Est Nivelles én L13","CTL","Minor_AdHoc"," "," ",56122]
["2025-09-22","2025-09-27","SW",1,"117","A+B","BRAINE-LE-COMTE","MANAGE","Week","Night","23:10","05:30","Programme de révision caténaire\r\nRq 333 : rq Ef's suite semestrielle : Niet ok in combinatie met werken L117 Braine-Le Comte-Manage én L124 Y.Forest-Est Nivelles én L130 Moustier -Flawinnes","CTL","Minor_AdHoc","CTL de nuit - Amplitude élargie"," ",56122]
["2025-09-22","2025-09-27","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Week","Night","23:00","05:00","Aménagement Châtelet - Phase 4\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Coupure type 3 + * Voie du car wash en complément​\r\nSem 39: Toutes les nuits 22^23 au 26^27/09/2025 de 23h à 5h"," ",54842]
["2025-09-22","2025-09-27","SW",1,"140","A+B","OTTIGNIES","LODELINSART","Week","Night","23:00","05:00","Renouvellement Pi métalliques 52.015 et 52.215\r\nNuit pour soudures","CTL","Minor_AdHoc","Gare de Fleurus incluse"," ",55535]
["2025-09-22","2025-10-03","CE",1,"96","B","Y.RUISBROEK","Y.RUISBROEK","AllWeek","Continuous","05:00","06:00","Y.Ruisbroek - Renouvellement Aiguillages - Phase 2\r\nART 60km/h","ART","Minor_AdHoc","Perte de temps : 2.12 min"," ",58371]
["2025-09-22","2025-10-03","SW",1,"130A","A+B","ERQUELINNES-FRONTIERE","LA SAMBRE","Week","Night","23:00","05:00","Renouvellement PS bk 118.788  + 104.903 - préparation démolition","CTL","Minor_AdHoc"," "," ",56482]
["2025-09-22","2025-10-13","SW",1,"140","A+B","OTTIGNIES","FLEURUS","AllWeek","Continuous","05:00","05:00","ART 2 min\r\nRenouvellement Pi métalliques 52.015 et 52.215","ART","Minor_AdHoc",null," ",59520]
["2025-09-22","2025-10-13","SW",1,"94","A/B","HALLE","ENGHIEN","AllWeek","Continuous","06:00","04:20","Renouvellement des traverses P93 entre Enghien et Halle","SAVU_CTRL","High","SAVU en continu + CTL de nuit\r\n3 WE en CTL pendant le SAVU\r\nART 40/60/80 km/h pendant le SAVU - 5min"," ",53253]
["2025-09-22","2025-10-20","SW",1,"94","A/B","HALLE","ENGHIEN","AllWeek","Continuous","06:00","04:20","ART 5min \r\nRenouvellement des traverses P93 entre Enghien et Halle","ART","Minor_AdHoc","ART 40/60/80 km/h - 5min"," ",61855]
["2025-09-22","2025-10-24","SW",1,"75A","A+B","MOUSCRON","FROYENNES","AllWeek","Night","22:30","04:10","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nCTL de nuit pour préparation et finition des travaux de ripage du PI.","CTL","Minor_AdHoc",null," ",39577]
["2025-09-22","2026-04-27","CE",1,"161","*","SCHAERBEEK","SCHAERBEEK","AllWeek","Continuous","22:00","06:00","Bundel M in FSR continu buiten dienst voor de vernieuwing van de Albertbrug Fase 2.0\r\nBijkomend tijdens de nachten sp B L25","CTL","Major","FSR Bundel M BDS: P-treinen uitwijken naar FSR Groep G of R"," ",32341]
["2025-09-22","2026-04-27","CE",1,"25","B","SCHAERBEEK","BUDA","AllWeek","Continuous","22:00","06:00","Linked to coupure nr 32341 on line 161 tracks(s) * from SCHAERBEEK to SCHAERBEEK: Bundel M in FSR continu buiten dienst voor de vernieuwing van de Albertbrug Fase 2.0\r\nBijkomend tijdens de nachten sp B L25","SAVU","High"," "," ",32341]
["2025-09-24","2025-09-25","SE",1,"130","A","FRANIERE","FLAWINNE","Week","Night","23:00","05:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Il faut limiter le nombre de trains par heure à 4 maximum :​\r\nla nuit du 24-25/09​\r\ndu 25/9 23h00 au 30/09 5h00"," ",61867]
["2025-09-25","2025-09-26","SE",1,"130","A","FRANIERE","FLAWINNE","AllWeek","Continuous","23:00","23:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc",null," ",56349]
["2025-09-26","2025-09-29","CE",1,"96","B","BRUXELLES-MIDI","LOT","Weekend","Continuous","23:30","05:00","Linked to coupure nr 58368 on line 96N tracks(s) B from Y.NOORD HALLE to BRUXELLES-MIDI: Y.Ruisbroek - Renouvellement Aiguillages - Phase 2\r\nWE 2/2 Travaux","SAVU","Minor_AdHoc"," "," ",58368]
["2025-09-26","2025-09-29","CE",1,"96N","B","Y.NOORD HALLE","BRUXELLES-MIDI","Weekend","Continuous","23:30","05:00","Y.Ruisbroek - Renouvellement Aiguillages - Phase 2\r\nWE 2/2 Travaux","SAVU","Minor_AdHoc"," "," ",58368]
["2025-09-26","2025-09-29","SE",1,"130","A","FLAWINNE","MOUSTIER","Weekend","Continuous","23:00","05:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","CTL","Medium",null," ",56355]
["2025-09-26","2025-09-29","SE",1,"166","A+B","ANSEREMME","GENDRON-CELLES","Weekend","Continuous","23:00","04:30","Mise en service CV Jade","CTL","Medium"," "," ",47338]
["2025-09-26","2025-09-29","SE",1,"24","A+B","Y.GLONS","MONTZEN-FRONTIERE","Weekend","Continuous","23:00","05:00","Entretien","CTL","Medium","ART 2'"," ",51839]
["2025-09-26","2025-09-29","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER","CTL","Medium","ART stabilisation 2 minutes"," ",54946]
["2025-09-26","2025-09-29","SW",1,"94","A/B","HALLE","ENGHIEN","Weekend","Continuous","22:30","04:40","Renouvellement des traverses P93 entre Enghien et Halle","CTL","Medium",null," ",59441]
["2025-09-27","2025-09-28","NW",1,"66","A+B","KORTRIJK","ROESELARE","Weekend","Continuous","22:00","06:00","IDS, BDS, meewerken niet mogelijk\r\nETCS1-FS_NW_L75 Kortrijk + grid Kortrijk\r\n1 za -zo weekendnacht 8u CTL spoor A+B","CTL","Medium"," "," ",57822]
["2025-09-27","2025-09-28","NW",1,"75","A+B","WAREGEM","FRONT. FLANDRE-WALLONIE L75","Weekend","Continuous","22:00","06:00","Linked to coupure nr 57822 on line 66 tracks(s) A+B from KORTRIJK to ROESELARE: IDS, BDS, meewerken niet mogelijk\r\nETCS1-FS_NW_L75 Kortrijk + grid Kortrijk\r\n1 za -zo weekendnacht 8u CTL spoor A+B","CTL","Medium"," "," ",57822]
["2025-09-27","2025-09-28","NW",1,"89","A+B","Y.ZANDBERG","OUDENAARDE","Weekend","Continuous","22:00","06:00","Linked to coupure nr 57822 on line 66 tracks(s) A+B from KORTRIJK to ROESELARE: IDS, BDS, meewerken niet mogelijk\r\nETCS1-FS_NW_L75 Kortrijk + grid Kortrijk\r\n1 za -zo weekendnacht 8u CTL spoor A+B","CTL","Medium"," "," ",57822]
["2025-09-27","2025-09-29","NE",1,"21","A+B","HASSELT","ALKEN","Weekend","Continuous","00:01","04:00","Linked to coupure nr 57987 on line 34 tracks(s) A+B from HASSELT to Y.ROOIERWEG: Vernieuwing 4 wissels L34/L21 (02AU; 02BU; 01AU; 01BU)","CTL","Medium"," ","BTS van 3' voor HKM",57987]
["2025-09-27","2025-09-29","NE",1,"25","A+B","MECHELEN","Y.ABEELSTRAAT","Weekend","Continuous","01:00","04:00","bijkomende aanvraag renovatie Vaartbrug  ipv vernieuwing\r\n\r\n\r\nTLO lijn 25 gedurende 7 weken. Impact deels icm CoLT 58490 (renovatie kruisingsbrug 2 weken september 2025)\r\n\r\nZie goedgekeurd dossier: 2024 - L25 - Mechelen-Y. Abeelstraat","CTL","Medium","TLO L25 A+B tijdens weekends van Y.Abeelstraat tot Mechelen inbegrepen.\r\nTLO L25 A+B tijdens weeknachten van Mechelen tot Mechelen."," ",62711]
["2025-09-27","2025-09-29","NE",1,"34","A+B","HASSELT","Y.ROOIERWEG","Weekend","Continuous","00:01","04:00","Vernieuwing 4 wissels L34/L21 (02AU; 02BU; 01AU; 01BU)","CTL","Medium","BTS: Wisselzone is al 40k/u, dus enkel misschien BTS L34 sp A (afhankelijk van de werken): 90 km/u naar 40km/u: HKV: 1,2 min; HKM, 3,2 min in week tussen grote TLO en herziening.","BTS van 3' voor HKM",57987]
["2025-09-29","2025-09-30","SE",1,"130","B","FRANIERE","FLAWINNE","Week","Continuous","05:00","05:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc",null," ",61866]
["2025-09-29","2025-10-03","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58752]
["2025-09-29","2025-10-03","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60985]
["2025-09-29","2025-10-04","CE",1,"25","B","SCHAERBEEK","VILVOORDE","Week","Night","23:00","05:00","Vernieuwing Albertbrug fase 2: werken afbraak brugdeel 6","CTL","Minor_AdHoc","DOES L25"," ",62037]
["2025-09-29","2025-10-04","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59235 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59235]
["2025-09-29","2025-10-04","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59235 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59235]
["2025-09-29","2025-10-04","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59235]
["2025-09-29","2025-10-04","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59235 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59235]
["2025-09-29","2025-10-04","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Week","Night","23:00","05:00","Aménagement Châtelet - Phase 5\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Coupure type 3​\r\nSem 40: Toutes les nuits 29^30/09 au 3^4/10/2025 de 23h à 5h"," ",61861]
["2025-09-29","2025-10-04","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","23:00","05:45","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 6 - finitions\r\nPhase 6.1 – CTL L75 de nuit de semaine\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Phase 6.1 – CTL L75 de nuit de semaine\r\nTravaux de nuit en semaine 40 et 43 de 23h à 5h45"," ",55883]
["2025-09-29","2025-10-10","CE",1,"96","A+B","BRUXELLES-MIDI","LOT","Week","Night","23:30","05:00","Linked to coupure nr 58374 on line 96N tracks(s) A+B from Y.NOORD HALLE to BRUXELLES-MIDI: Y.Ruisbroek - Renouvellement Aiguillages - Phase 2\r\nFinitions\r\nY.Ruisbroek - Renouvellement Aiguillages - Phase 3\r\nPréparations","CTL","Minor_AdHoc"," "," ",58374]
["2025-09-29","2025-10-10","CE",1,"96N","A+B","Y.NOORD HALLE","BRUXELLES-MIDI","Week","Night","23:30","05:00","Y.Ruisbroek - Renouvellement Aiguillages - Phase 2\r\nFinitions\r\nY.Ruisbroek - Renouvellement Aiguillages - Phase 3\r\nPréparations","CTL","Minor_AdHoc"," "," ",58374]
["2025-09-29","2025-10-13","SE",1,"130","B","FLAWINNE","MOUSTIER","AllWeek","Continuous","05:00","05:00","ART 3min\r\nCriblage voie B Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART 2 à 60Km/h (suite Stabilisatrice) de 3’ HKV et 2’ HKM VA + VB du lundi 29/09 05h00 au lundi 13/10 à 05h00​\r\nPour travailler avec un ART de protection à 60km/h, il faut limiter le nombre de trains par heure à 4 maximum :​\r\n- les nuits du 24-25/09​ + "," ",61865]
["2025-09-29","2025-10-13","SE",1,"162","A","CINEY","HAVERSIN","AllWeek","Continuous","05:00","05:00","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 16 - ART\r\nciney-haversin\r\nTravaux effectués = Travaux caténaires et GC linéaire + début des travaux de quai à Leignon et Chapois","ART","Minor_AdHoc","Phase ART stabilisation\r\nEstimation en cours (environ 5min - à confirmer)"," ",62774]
["2025-09-29","2025-10-18","CE",1,"25","A+B","BRUXELLES-NORD","VILVOORDE","Week","Night","23:30","04:30","Vernieuwing Albertbrug fase 2: nachtwerken afbraak brugdeel 5","CTL","Minor_AdHoc","TLO L25 + L27 + BL36"," ",62038]
["2025-09-29","2025-10-18","CE",1,"27","A+B","BRUXELLES-NORD-GRIL F","Y.SCHAERBEEK-GROUPE G","Week","Night","23:30","04:30","Linked to coupure nr 62038 on line 25 tracks(s) A+B from BRUXELLES-NORD to VILVOORDE: Vernieuwing Albertbrug fase 2: nachtwerken afbraak brugdeel 5","CTL","Minor_AdHoc"," "," ",62038]
["2025-09-29","2025-11-03","CE",1,"124","*","BRUXELLES-MIDI","BRUXELLES-MIDI","AllWeek","Continuous","07:00","04:40","Bundel Charleroi continu BDS voor premontage wissels","Autre","Minor_AdHoc","bundel Charleroi ontoegankelijk"," ",59148]
["2025-09-30","2025-10-27","CE",1,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","AllWeek","Night","00:45","04:30","Voorbereidende nachten + Uitbreiding tijdens de nachten van de Massificatie-TLO:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit FBMZ verlengde L124","CTL","Minor_AdHoc","TLO L124 \r\nL96 sp A + Bypass BDS\r\nFBMZ perron sp 20+21 BDS,  verlengd tot in koker 3 seinen E5/EX-6\r\nFBMZ sp 18-19-20-21 ontoegankelijk"," ",61836]
["2025-09-30","2025-10-27","CE",1,"28/3","S","Y.FOREST-EST","Y.CUREGHEM","AllWeek","Night","00:45","04:30","Linked to coupure nr 61836 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: Voorbereidende nachten + Uitbreiding tijdens de nachten van de Massificatie-TLO:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlo","CTL","Minor_AdHoc"," "," ",61836]
["2025-09-30","2025-10-27","CE",1,"96","A","BRUXELLES-MIDI","Y.RUISBROEK","AllWeek","Night","00:45","04:30","Linked to coupure nr 61836 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: Voorbereidende nachten + Uitbreiding tijdens de nachten van de Massificatie-TLO:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlo","SAVU","Minor_AdHoc"," "," ",61836]
["2025-10-01","2025-10-02","SE",1,"130","B","FRANIERE","FLAWINNE","Week","Night","23:00","05:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Il faut limiter le nombre de trains par heure à 4 maximum :​\r\n- la nuit 1-2/10​\r\n- du 2/10 23h00 au 7/10 5h00"," ",61869]
["2025-10-02","2025-10-07","SE",1,"130","B","FRANIERE","FLAWINNE","AllWeek","Continuous","05:00","05:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc",null," ",61868]
["2025-10-03","2025-10-06","CE",1,"96","A","BRUXELLES-MIDI","LOT","Weekend","Continuous","23:30","05:00","Linked to coupure nr 58372 on line 96N tracks(s) A from Y.NOORD HALLE to BRUXELLES-MIDI: Y.Ruisbroek - Renouvellement Aiguillages - Phase 3\r\nWE 1/2 Travaux","SAVU","Minor_AdHoc"," "," ",58372]
["2025-10-03","2025-10-06","CE",1,"96N","A","Y.NOORD HALLE","BRUXELLES-MIDI","Weekend","Continuous","23:30","05:00","Y.Ruisbroek - Renouvellement Aiguillages - Phase 3\r\nWE 1/2 Travaux","SAVU","Minor_AdHoc"," "," ",58372]
["2025-10-03","2025-10-06","SE",1,"130","B","FLAWINNE","MOUSTIER","Weekend","Continuous","23:00","05:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","CTL","Medium",null," ",56357]
["2025-10-03","2025-10-06","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n22 - Déroulage Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","1 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 21)"," ",59638]
["2025-10-03","2025-10-06","SE",1,"161","B","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59170]
["2025-10-03","2025-10-06","SE",1,"24","A+B","Y.GLONS","MONTZEN-FRONTIERE","Weekend","Continuous","23:00","05:00","Entretien","CTL","Medium","ART 2'"," ",51838]
["2025-10-03","2025-10-06","SW",1,"130A","A+B","ERQUELINNES-FRONTIERE","LA SAMBRE","Weekend","Continuous","23:00","04:10","Renouvellement PS bk 118.788  + 104.903 - préparation démolition","CTL","Medium"," "," ",56479]
["2025-10-03","2025-10-06","SW",1,"75A","A+B","MOUSCRON","FROYENNES","Weekend","Continuous","22:30","04:10","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nCTL en continu pour ripage du PI.","CTL","Medium","ART  40km/h : 2,13 min voyageurs; 5,62 min marchandises pendant 14 jours après la CTL"," ",39546]
["2025-10-03","2025-10-06","SW",1,"94","A/B","HALLE","ENGHIEN","Weekend","Continuous","22:30","04:40","Renouvellement des traverses P93 entre Enghien et Halle","CTL","Medium",null," ",59442]
["2025-10-04","2025-10-06","CE",1,"161","A+B","SCHAERBEEK","Y.JOSAPHAT","Weekend","Continuous","00:20","04:30","Linked to coupure nr 59135 on line 25 tracks(s) A+B from SCHAERBEEK to VILVOORDE: Vernieuwing Albertbrug fase 2.1: Afbraak brugdeel 5 gedeelte boven L25/L27/BL36","CTL","Medium"," "," ",59135]
["2025-10-04","2025-10-06","CE",1,"25","A+B","SCHAERBEEK","VILVOORDE","Weekend","Continuous","00:20","04:30","Vernieuwing Albertbrug fase 2.1: Afbraak brugdeel 5 gedeelte boven L25/L27/BL36","CTL","Medium","TLO L25 + sp B L27 afgesloten, BL36 en AL27 lokaal in FSR BDS+BSS\r\nFSR sp 3/4/5/6/7/9/11 BDS+BSS. FSR sp 8 en 10 in cds."," ",59135]
["2025-10-04","2025-10-06","CE",1,"27","A","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","00:20","04:30","Linked to coupure nr 59135 on line 25 tracks(s) A+B from SCHAERBEEK to VILVOORDE: Vernieuwing Albertbrug fase 2.1: Afbraak brugdeel 5 gedeelte boven L25/L27/BL36","Autre","Minor_AdHoc"," "," ",59135]
["2025-10-04","2025-10-06","CE",1,"27","B","SCHAERBEEK","SCHAERBEEK","Weekend","Continuous","00:20","04:30","Linked to coupure nr 59135 on line 25 tracks(s) A+B from SCHAERBEEK to VILVOORDE: Vernieuwing Albertbrug fase 2.1: Afbraak brugdeel 5 gedeelte boven L25/L27/BL36","SAVU","Minor_AdHoc"," "," ",59135]
["2025-10-04","2025-10-06","NE",1,"25","A","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:01","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nenkel sp A --> Mechelen perronspoor A tot Mechelen Dijkstraat --> invloed L25N --> komt op 1 spoor te Nekkerspoel\r\nzie schets 'expl A-L25' (tabblad schet","CTL","Medium","impact L25N ? --> komt op 1 spoor te Nekkerspoel"," ",58762]
["2025-10-04","2025-10-13","NE",1,"21","A+B","HASSELT","ALKEN","AllWeek","Continuous","00:01","04:00","Linked to coupure nr 57986 on line 34 tracks(s) A+B from HASSELT to Y.ROOIERWEG: Vernieuwing 4 wissels L34/L21 (02AU; 02BU; 01AU; 01BU)","CTL","High"," ","BTS van 3' voor HKM",57986]
["2025-10-04","2025-10-13","NE",1,"34","A+B","HASSELT","Y.ROOIERWEG","AllWeek","Continuous","00:01","04:00","Vernieuwing 4 wissels L34/L21 (02AU; 02BU; 01AU; 01BU)","CTL","High"," ","BTS van 3' voor HKM",57986]
["2025-10-06","2025-10-10","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60986]
["2025-10-06","2025-10-11","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58753]
["2025-10-06","2025-10-11","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59281 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59281]
["2025-10-06","2025-10-11","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:20","04:30","Linked to coupure nr 59281 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","CTL","Minor_AdHoc"," "," ",59281]
["2025-10-06","2025-10-11","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg\r\nTLO L50A/6 Gent Sint Pieters-","CTL","Minor_AdHoc"," "," ",59281]
["2025-10-06","2025-10-11","NW",1,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59281 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59281]
["2025-10-06","2025-10-11","NW",1,"75","B","GENT-SINT-PIETERS","DE PINTE","Week","Night","23:20","04:30","Linked to coupure nr 59281 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59281]
["2025-10-06","2025-10-11","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n23- Dépose poteaux+ finitions","SAVU_CTRL","Minor_AdHoc","1 semaine SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 22)"," ",59639]
["2025-10-06","2025-10-11","SW",1,"140","A+B","OTTIGNIES","LODELINSART","Week","Night","23:00","05:00","Renouvellement Pi métalliques 52.015 et 52.215\r\nNuits finitions","CTL","Minor_AdHoc","Gare de Fleurus incluse"," ",55537]
["2025-10-06","2025-10-11","SW",1,"75A","A+B","MOUSCRON","FROYENNES","Week","Night","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 6 - finitions\r\nPhase 6.2 – CTL L75A+Faisceau de nuit de semaine​\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Phase 6.2 – CTL L75A+Faisceau de nuit de semaine​\r\nTravaux de nuit en semaine 41 et 44 de 22h30 à 4h10"," ",55887]
["2025-10-06","2025-10-17","CE",1,"96","A","Y.RUISBROEK","Y.RUISBROEK","AllWeek","Continuous","05:00","06:00","Y.Ruisbroek - Renouvellement Aiguillages - Phase 3\r\nART 60 km/h","ART","Minor_AdHoc","Perte de temps : 2.12 min"," ",58525]
["2025-10-06","2025-10-18","SE",1,"130","A/B","FLAWINNE","MOUSTIER","Week","Night","23:00","05:00","Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","SAVU Voie A ou Voie B hors service tronçons Flawinne – Franière ou Franière – Moustier de nuit les 6-7, 7-8, 8-9 ,9-10 ,10-11, 13-14, 14-15, 15-16, 16-17, 17-18 octobre"," ",61870]
["2025-10-06","2025-10-19","SW",1,"75A","A+B","MOUSCRON","FROYENNES","AllWeek","Continuous","05:20","22:00","ART \r\nConstruction passage inférieur + couloir-sous-voie pour la suppression du PN4.","ART","Minor_AdHoc","ART  40km/h : 2,13 min voyageurs; 5,62 min marchandises"," ",53174]
["2025-10-06","2025-10-25","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET","AllWeek","Continuous","06:00","06:00","Aménagement Châtelet - Phase 6\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Coupure type 4\r\nSem 41-42-43: En continu du 6/10 à 6h jusqu’au 25/10/2025 à 6h (3 semaines)​\r\n\r\n​"," ",54846]
["2025-10-06","2025-10-25","SW",1,"130","B","LE CAMPINAIRE","CHATELET-GRIL OUEST","AllWeek","Night","23:00","05:00","Aménagement Châtelet - Phase 6\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Coupure type 5​\r\nSem 41-42-43 + WE 41-42: Toutes les nuits 6^7 au 24^25/10/2025​\r\nComplément 54846"," ",54847]
["2025-10-10","2025-10-13","CE",1,"96","A","BRUXELLES-MIDI","LOT","Weekend","Continuous","23:30","05:00","Linked to coupure nr 58373 on line 96N tracks(s) A from Y.NOORD HALLE to BRUXELLES-MIDI: Y.Ruisbroek - Renouvellement Aiguillages - Phase 3\r\nWE 2/2 Travaux","SAVU","Minor_AdHoc"," "," ",58373]
["2025-10-10","2025-10-13","CE",1,"96N","A","Y.NOORD HALLE","BRUXELLES-MIDI","Weekend","Continuous","23:30","05:00","Y.Ruisbroek - Renouvellement Aiguillages - Phase 3\r\nWE 2/2 Travaux","SAVU","Minor_AdHoc"," "," ",58373]
["2025-10-10","2025-10-13","NW",1,"51","A+B","BRUGGE","Y.BLAUWE TOREN","Weekend","Continuous","22:00","04:00","Plaatsen nieuwe brugdekvoeg en steunmuur Brug Blankenbergsesteenweg \r\nVerhoogd talud bouwen thv KP 96.400","CTL","Medium","Geen verkeer richting Knokke-Blankenberge en Zeebrugge mogelijk","Info Racc.",56104]
["2025-10-10","2025-10-14","SW",1,"94","A/B","HALLE","ENGHIEN","Weekend","Continuous","22:30","04:40","Renouvellement des traverses P93 entre Enghien et Halle","CTL","Medium",null," ",59443]
["2025-10-11","2025-10-13","CE",1,"27","A","SCHAERBEEK","Y.SCHAERBEEK-GROUPE G","Weekend","Continuous","00:45","04:30","Linked to coupure nr 62041 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1.5: verstevigen pijlers brugdeel 4","SAVU","Minor_AdHoc"," "," ",62041]
["2025-10-11","2025-10-13","CE",1,"27D","A+B","SCHAERBEEK","Y.SCHAERBEEK-CARWASH","Weekend","Continuous","00:45","04:30","Linked to coupure nr 62041 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1.5: verstevigen pijlers brugdeel 4","CTL","Medium"," "," ",62041]
["2025-10-11","2025-10-13","CE",1,"27D/4","A+B","SCHAERBEEK","SCHAERBEEK-GROUPE R","Weekend","Continuous","00:45","04:30","Linked to coupure nr 62041 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1.5: verstevigen pijlers brugdeel 4","CTL","Medium"," "," ",62041]
["2025-10-11","2025-10-13","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","Weekend","Continuous","00:45","04:30","Linked to coupure nr 62041 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1.5: verstevigen pijlers brugdeel 4","CTL","Medium"," "," ",62041]
["2025-10-11","2025-10-13","NE",1,"12","A+B","ESSEN-GRENS","Y.LUCHTBAL","Weekend","Continuous","01:00","04:00","Massificatie","CTL","Medium","Geen verkeer mogelijk van/naar Roosendaal"," ",59606]
["2025-10-11","2025-10-13","NE",1,"12/1","A+B","Y.DRIEHOEKSTRAAT","Y.SINT-MARIABURG","Weekend","Continuous","01:00","04:00","Linked to coupure nr 59606 on line 12 tracks(s) A+B from ESSEN-GRENS to Y.LUCHTBAL: Massificatie","CTL","Medium"," "," ",59606]
["2025-10-11","2025-10-13","NE",1,"25","A+B","SCHAERBEEK","VILVOORDE","Weekend","Continuous","00:01","04:00","Werken Viaduct Vilvoorde (AWV)","CTL","Medium"," "," ",58705]
["2025-10-11","2025-10-13","SE",1,"130","A+B","FLAWINNE","MOUSTIER","Weekend","Night","23:00","05:00","Criblage voie B Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","CTL de nuit (Sam/dim et dim/lun – 6h. Min.) de WE Flawinne – Moustier"," ",56362]
["2025-10-13","2025-10-17","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60987]
["2025-10-13","2025-10-17","SW",1,"118","A+B","BRACQUEGNIES","MONS","Week","Night","22:30","04:30","Renouvellement des chapes d'étanchéité des PI 30.800, 30.820 et 34.175 + pose de passerelles de service sur le PI 34.175\r\nNuits de préparations","CTL","Minor_AdHoc",null," ",55634]
["2025-10-13","2025-10-17","SW",1,"75A","*","MOUSCRON","HERSEAUX","Week","Day","06:00","16:00","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 6 - finitions\r\nPhase 6.3 - MHS du faisceau de jour\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Phase 6.3 - MHS du faisceau de jour\r\nTravaux de jour en semaine 42 et 45 de 6h à 16h​"," ",55890]
["2025-10-13","2025-10-18","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59236 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59236]
["2025-10-13","2025-10-18","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59236 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59236]
["2025-10-13","2025-10-18","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59236]
["2025-10-13","2025-10-18","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59236 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59236]
["2025-10-13","2025-10-25","CE",1,"96","A","BRUXELLES-MIDI","LOT","Week","Night","23:30","05:00","Linked to coupure nr 58375 on line 96N tracks(s) A from Y.NOORD HALLE to BRUXELLES-MIDI: Y.Ruisbroek - Renouvellement Aiguillages - Phase 3\r\nFinitions","SAVU","Minor_AdHoc"," "," ",58375]
["2025-10-13","2025-10-25","CE",1,"96N","A","Y.NOORD HALLE","BRUXELLES-MIDI","Week","Night","23:30","05:00","Y.Ruisbroek - Renouvellement Aiguillages - Phase 3\r\nFinitions","SAVU","Minor_AdHoc"," "," ",58375]
["2025-10-13","2025-11-01","SW",1,"94","A+B","HALLE","ENGHIEN","Week","Night","22:30","04:40","Renouvellement des traverses P93 entre Enghien et Halle\r\nTravaux de finition","CTL","Minor_AdHoc","CTL de nuit\r\nART 40/60/80 se poursuit pendant la 1ère semaine"," ",53255]
["2025-10-13","2025-12-12","NW",1,"60","A+B","JETTE","ASSE","AllWeek","Continuous","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","ART","Minor_AdHoc",null," ",60996]
["2025-10-13","2025-12-13","SE",1,"162","A/B","CINEY","HAVERSIN","AllWeek","Continuous","05:00","23:50","SIRU_2019_L162_Ciney: Gare, LRS, ré-électrification_V12\r\nPhase 17\r\nciney-haversin\r\nTravaux effectués = Travaux caténaires et GC linéaire + début des travaux de quai à Leignon et Chapois","SAVU_CTRL","High","CTL de Nuit : Lu^Ma à Je^Ve :00:10–04:50, Ve^Sa 00:10–06:30, Sa^Di 23:10–06:30, Di^Lu 23:10–04:50\r\nAS 34BK parcourable\r\nSAVU prolongé dans le tronçon suite arbitrage budgétaire"," ",62775]
["2025-10-17","2025-10-20","CE",1,"161","A+B","WATERMAEL","BAKENBOS","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon).\r\nLivraison KIROW! besoin de garder la date fixe"," ",59174]
["2025-10-17","2025-10-20","NW",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Medium",null," ",60975]
["2025-10-17","2025-10-20","NW",1,"75","A+B","Y.BETHUNE","MOUSCRON","Weekend","Continuous","23:10","04:00","Onderhoud","CTL","Medium"," "," ",59355]
["2025-10-17","2025-10-20","SE",1,"130","A+B","FLAWINNE","MOUSTIER","Weekend","Night","23:00","05:00","Criblage voie B Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","CTL de nuit (Sam/dim et dim/lun – 6h. Min.) de WE Flawinne – Moustier"," ",56361]
["2025-10-17","2025-10-20","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n24 - Déroulage Namur- Gembloux","SAVU_CTRL","Minor_AdHoc","1 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 23)"," ",59640]
["2025-10-17","2025-10-20","SW",1,"130A","A+B","ERQUELINNES-FRONTIERE","LA SAMBRE","Weekend","Continuous","23:00","04:10","Renouvellement PS bk 118.788  + 104.903 - préparation démolition","CTL","Medium"," "," ",56480]
["2025-10-17","2025-10-27","CE",1,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","AllWeek","Continuous","23:45","04:50","Massificatie:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit FBMZ verlengde L124","CTL","High","TLO L124 in continu\r\nL96 sp A continu BDS in buitenrooster tot aw 52J(NI): lokale omleiding via Bypass\r\nFBMZ perron sp 20+21 continu BDS, tijdens de WE 18+19/10 verlengd tot in koker 3 seinen E5/EX-6"," ",59147]
["2025-10-17","2025-10-27","CE",1,"28/3","S","Y.FOREST-EST","Y.CUREGHEM","AllWeek","Continuous","23:45","04:50","Linked to coupure nr 59147 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: Massificatie:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit FBMZ verlengde L124","CTL","High"," "," ",59147]
["2025-10-17","2025-10-27","CE",1,"96","A","BRUXELLES-MIDI","LIGNE 96-BYPASS","AllWeek","Continuous","23:45","04:50","Linked to coupure nr 59147 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: Massificatie:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit FBMZ verlengde L124","SAVU","High"," "," ",59147]
["2025-10-17","2025-10-27","SE",1,"140","A+B","OTTIGNIES","FLEURUS","AllWeek","Continuous","23:30","04:50","Suppression du PN 45 à Ottignies et remplacement par un CSV.\r\nRq 333 : demande EF's suite semestrielle : Pas ensemble avec TW L124. Est-il possible de massifier sur les congés de détente RWB 2025 => du 23/02 au 09/03/2025","CTL","High","ART de 2min pendant 1 semaine après la CTL de 10 jours"," ",59181]
["2025-10-17","2025-10-27","SE",1,"43","A","BOMAL","MARLOIE","AllWeek","Continuous","23:00","05:00","Criblage","CTL","High","Congés scolaires FWB"," ",55900]
["2025-10-17","2025-10-27","SW",1,"124","A+B","NIVELLES","Y.FOREST-EST","AllWeek","Continuous","23:30","04:40","RER Achèvement 4 voies Waterloo-Braine-Alliance","CTL","High","CTL 9jrs en continu (congés scolaires FWB)\r\nART stabilisation 4’ pendant 14jrs à la fin des travaux"," ",54936]
["2025-10-17","2025-11-02","SW",1,"118","A+B","BRACQUEGNIES","MONS","AllWeek","Continuous","23:00","04:00","Renouvellement des chapes d'étanchéité des PI 30.800, 30.820 et 34.175 + pose de passerelles de service sur le PI 34.175","CTL","High","CTL continu de 14 jours (congés scolaires FWB)\r\n2 ART à 60km/h : 1 pour les 30.800 et 30.820 + 1 pour le 34.175 : 4 minutes"," ",55623]
["2025-10-17","2025-11-03","SW",1,"78","A+B","SAINT-GHISLAIN","BLATON","Weekend","Continuous","22:30","04:30","Linked to coupure nr 53249 on line 97 tracks(s) A+B from MONS to SAINT-GHISLAIN: Renouvellement LRS + Chantier SPW Entretien ou Renouvellement PS 42.944\r\nRq 333 : rq EF's suite semestrielle: L97+78 tronçon trop long - possible de scincder?","CTL","Minor_AdHoc"," "," ",53249]
["2025-10-17","2025-11-03","SW",1,"97","A+B","MONS","SAINT-GHISLAIN","Weekend","Continuous","22:30","04:30","Renouvellement LRS + Chantier SPW Entretien ou Renouvellement PS 42.944\r\nRq 333 : rq EF's suite semestrielle: L97+78 tronçon trop long - possible de scincder?","CTL","Minor_AdHoc","3 WE de CTL + CTL de nuit du 20/10 au 24/10/2025"," ",53249]
["2025-10-18","2025-10-19","NW",1,"204","A+B","Y.BOMA","GENT-NOORD","Weekend","Night","22:00","06:00","ETCS1-FS_NW_L204 \r\nIDS Meewerken niet mogelijk","CTL","Minor_AdHoc"," ","Info Racc.",55185]
["2025-10-18","2025-10-20","NE",1,"21","A+B","HASSELT","ALKEN","Weekend","Continuous","00:01","04:00","Linked to coupure nr 57988 on line 34 tracks(s) A+B from HASSELT to Y.ROOIERWEG: Vernieuwing 4 wissels L34/L21 (02AU; 02BU; 01AU; 01BU)","CTL","Medium"," ","BTS van 3' voor HKM",57988]
["2025-10-18","2025-10-20","NE",1,"25","A","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Weekend","Continuous","00:01","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nenkel sp A --> Mechelen perronspoor A tot Mechelen Dijkstraat --> invloed L25N --> komt op 1 spoor te Nekkerspoel\r\nzie schets 'expl A-L25' (tabblad schet","CTL","Medium","impact L25N ? --> komt op 1 spoor te Nekkerspoel"," ",58763]
["2025-10-18","2025-10-20","NE",1,"27","A+B","Y.HAREN-NORD","VILVOORDE","Weekend","Continuous","00:01","04:00","Werken Viaduct Vilvoorde (AWV)","CTL","Medium"," "," ",58707]
["2025-10-18","2025-10-20","NE",1,"34","A+B","HASSELT","Y.ROOIERWEG","Weekend","Continuous","00:01","04:00","Vernieuwing 4 wissels L34/L21 (02AU; 02BU; 01AU; 01BU)","CTL","Medium"," ","BTS van 3' voor HKM",57988]
["2025-10-20","2025-10-24","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60988]
["2025-10-20","2025-10-25","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58754]
["2025-10-20","2025-10-25","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59237 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59237]
["2025-10-20","2025-10-25","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59237 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59237]
["2025-10-20","2025-10-25","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59237]
["2025-10-20","2025-10-25","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59237 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59237]
["2025-10-20","2025-10-25","SW",1,"75","A+B","MOUSCRON","MOUSCRON-FRONTIERE","Week","Night","23:00","05:45","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 6 - finitions\r\nPhase 6.1 – CTL L75 de nuit de semaine\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Phase 6.1 – CTL L75 de nuit de semaine\r\nTravaux de nuit en semaine 40 et 43 de 23h à 5h45"," ",61852]
["2025-10-20","2025-10-31","SW",1,"130A","A+B","ERQUELINNES-FRONTIERE","LA SAMBRE","Week","Night","23:00","05:00","Renouvellement PS bk 118.788  + 104.903 - préparation démolition","CTL","Minor_AdHoc"," "," ",56483]
["2025-10-20","2025-11-08","SE",1,"161","A/B","NAMUR","GEMBLOUX","Week","Night","23:00","05:00","Travaux caténaires\r\n25 - Dépose poteaux+ finitions","SAVU_CTRL","Minor_AdHoc","3 semaines SAVU de nuits en semaine + CTL dans les blancs travaux (après le point 24)"," ",59641]
["2025-10-24","2025-10-27","NW",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Medium",null," ",60976]
["2025-10-24","2025-10-27","NW",1,"75","A+B","KORTRIJK","DEINZE","Weekend","Continuous","23:30","04:00","Station Kortrijk buiten dienst voor het leveren en inbouwen van wissels rooster kant Gent.\r\n\r\n(TUC-rail werkt nog een detailstudie uit)","CTL","Medium"," "," ",58628]
["2025-10-24","2025-10-27","NW",1,"75","A+B","KORTRIJK","MOUSCRON","Weekend","Continuous","23:30","04:00","Linked to coupure nr 58628 on line 75 tracks(s) A+B from KORTRIJK to DEINZE: Station Kortrijk buiten dienst voor het leveren en inbouwen van wissels rooster kant Gent.\r\n\r\n(TUC-rail werkt nog een detailstudie uit)","CTL","Medium"," "," ",58628]
["2025-10-24","2025-10-27","NW",1,"89","A+B","Y.ZANDBERG","OUDENAARDE","Weekend","Continuous","23:30","04:00","Linked to coupure nr 58628 on line 75 tracks(s) A+B from KORTRIJK to DEINZE: Station Kortrijk buiten dienst voor het leveren en inbouwen van wissels rooster kant Gent.\r\n\r\n(TUC-rail werkt nog een detailstudie uit)","CTL","Medium"," "," ",58628]
["2025-10-24","2025-10-27","SW",1,"130A","A+B","ERQUELINNES-FRONTIERE","LA SAMBRE","Weekend","Continuous","23:00","04:10","Renouvellement PS bk 118.788  + 104.903 - préparation démolition","CTL","Medium"," "," ",56481]
["2025-10-25","2025-10-27","NE",1,"12","A+B","ESSEN-GRENS","Y.LUCHTBAL","Weekend","Continuous","01:00","04:00","Massificatie","CTL","Medium","Geen verkeer mogelijk van/naar Roosendaal"," ",56124]
["2025-10-25","2025-10-27","NE",1,"12/1","A+B","Y.DRIEHOEKSTRAAT","Y.SINT-MARIABURG","Weekend","Continuous","01:00","04:00","Linked to coupure nr 56124 on line 12 tracks(s) A+B from ESSEN-GRENS to Y.LUCHTBAL: Massificatie","CTL","Medium"," "," ",56124]
["2025-10-25","2025-10-27","NE",1,"21","A+B","HASSELT","ALKEN","Weekend","Continuous","00:01","04:00","Linked to coupure nr 57989 on line 34 tracks(s) A+B from HASSELT to Y.ROOIERWEG: Vernieuwing 4 wissels L34/L21 (02AU; 02BU; 01AU; 01BU)","CTL","Medium"," ","BTS van 3' voor HKM",57989]
["2025-10-25","2025-10-27","NE",1,"34","A+B","HASSELT","Y.ROOIERWEG","Weekend","Continuous","00:01","04:00","Vernieuwing 4 wissels L34/L21 (02AU; 02BU; 01AU; 01BU)","CTL","Medium"," ","BTS van 3' voor HKM",57989]
["2025-10-27","2025-10-31","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60989]
["2025-10-27","2025-11-01","CE",1,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","Week","Continuous","04:50","04:50","Stabilisatie-BTS na Vernieuwen brug Guldenkasteelstraat","ART","Minor_AdHoc","BTS"," ",59152]
["2025-10-27","2025-11-01","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58755]
["2025-10-27","2025-11-01","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59305 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59305]
["2025-10-27","2025-11-01","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:20","04:30","Linked to coupure nr 59305 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","CTL","Minor_AdHoc"," "," ",59305]
["2025-10-27","2025-11-01","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg\r\nTLO L50A/6 Gent Sint Pieters-","CTL","Minor_AdHoc"," "," ",59305]
["2025-10-27","2025-11-01","NW",1,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59305 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59305]
["2025-10-27","2025-11-01","NW",1,"75","B","GENT-SINT-PIETERS","DE PINTE","Week","Night","23:20","04:30","Linked to coupure nr 59305 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59305]
["2025-10-27","2025-11-01","SW",1,"75A","A+B","MOUSCRON","FROYENNES","Week","Night","22:30","04:10","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 6 - finitions\r\nPhase 6.2 – CTL L75A+Faisceau de nuit de semaine​\r\nDossier de concertation validé en octobre 2022","CTL","Minor_AdHoc","Phase 6.2 – CTL L75A+Faisceau de nuit de semaine​\r\nTravaux de nuit en semaine 41 et 44 de 22h30 à 4h10"," ",61853]
["2025-10-27","2025-11-02","SE",1,"165","A","VIRTON","HALANZY","AllWeek","Continuous","06:00","06:00","Criblage - Phase 1\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","ART voie B : protection 3’ HKV 5’ HKM du lun. 27 oct 6h00 au dim. 2 nov 06h​\r\nMax 4 trains/h entre 6h00 et 22h00 pour ART 60 km/h​"," ",56308]
["2025-10-27","2025-11-03","SE",1,"140","A+B","OTTIGNIES","FLEURUS","AllWeek","Continuous","04:50","05:00","ART 2min\r\nSuppression du PN 45 à Ottignies et remplacement par un CSV.","CTL","Medium",null," ",59521]
["2025-10-27","2025-11-07","CE",1,"27","A","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 59747 on line 36 tracks(s) A from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: voorbereidende werken heropbouw brugdeel 4","SAVU","Minor_AdHoc"," "," ",59747]
["2025-10-27","2025-11-07","CE",1,"27D","S","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 59747 on line 36 tracks(s) A from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: voorbereidende werken heropbouw brugdeel 4","CTL","Minor_AdHoc"," "," ",59747]
["2025-10-27","2025-11-07","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","Week","Night","23:40","04:30","Linked to coupure nr 59747 on line 36 tracks(s) A from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: voorbereidende werken heropbouw brugdeel 4","CTL","Minor_AdHoc"," "," ",59747]
["2025-10-27","2025-11-09","SW",1,"75A","B","MOUSCRON","HERSEAUX","AllWeek","Day","09:00","15:00","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4.","SAVU","Minor_AdHoc","SAVU + S460 travaux de piste"," ",39587]
["2025-10-27","2025-11-17","SE",1,"43","A","BOMAL","MARLOIE","AllWeek","Continuous","05:00","05:00","ART 2min\r\nCriblage","ART","Minor_AdHoc",null," ",59544]
["2025-10-28","2025-10-28","SE",1,"165","A","Y.AUBANGE","VIRTON","Week","Day","06:00","22:00","Criblage - Phase 1\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Le 28 oct: extension côté bif Aubange 06h-22h​\r\nlie id 56308","HKM à adapter",56511]
["2025-10-28","2025-11-03","CE",1,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","AllWeek","Night","00:45","04:30","Afwerkingsnachten van de Massificatie-TLO:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit FBMZ verlengde L124","CTL","Minor_AdHoc","TLO L124 + FBMZ sp 20+21\r\nUitbreiding later te verkrijgen: 00u45-04u30\r\nL96 sp A + Bypass BDS\r\nFBMZ perron sp 20+21 verlengd tot in koker 3 seinen E5/EX-6\r\nFBMZ sp 18-19-20-21 ontoegankelijk"," ",61838]
["2025-10-28","2025-11-03","CE",1,"28/3","S","Y.FOREST-EST","Y.CUREGHEM","AllWeek","Night","00:45","04:30","Linked to coupure nr 61838 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: Afwerkingsnachten van de Massificatie-TLO:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit F","CTL","Minor_AdHoc"," "," ",61838]
["2025-10-28","2025-11-03","CE",1,"96","A","BRUXELLES-MIDI","Y.RUISBROEK","AllWeek","Night","00:45","04:30","Linked to coupure nr 61838 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: Afwerkingsnachten van de Massificatie-TLO:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit F","SAVU","Minor_AdHoc"," "," ",61838]
["2025-10-29","2025-11-02","SE",1,"167","A+B","Y.AUTELBAS","ATHUS","Week","Continuous","09:00","16:00","Mise en service de la PLP\r\nréglage des CV","CTL","Medium","L162 et L167 entre Athus et Rodange accessibles"," ",56263]
["2025-10-31","2025-11-03","CE",1,"124","A+B","BRUXELLES-MIDI","BRAINE-L'ALLEUD","Weekend","Continuous","23:45","04:30","AfwerkingsWE van de Massificatie-TLO:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit FBMZ verlengde L124","CTL","Medium","In continu TLO L124 + FBMZ sp 20+21\r\nL96 sp A continu BDS in buitenrooster tot aw 52J(NI): lokale omleiding via Bypass"," ",61839]
["2025-10-31","2025-11-03","CE",1,"28/3","S","Y.FOREST-EST","Y.CUREGHEM","Weekend","Continuous","23:45","04:30","Linked to coupure nr 61839 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: AfwerkingsWE van de Massificatie-TLO:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit FBMZ v","CTL","Medium"," "," ",61839]
["2025-10-31","2025-11-03","CE",1,"96","A","BRUXELLES-MIDI","Y.RUISBROEK","Weekend","Continuous","23:45","04:30","Linked to coupure nr 61839 on line 124 tracks(s) A+B from BRUXELLES-MIDI to BRAINE-L'ALLEUD: AfwerkingsWE van de Massificatie-TLO:\r\n1) Vernieuwen brug Guldenkasteelstraat\r\n2) Onderhoudswerken overbrugging Merlostraat\r\n3) Vernieuwing wissels inrit FBMZ v","SAVU","Minor_AdHoc"," "," ",61839]
["2025-10-31","2025-11-03","NW",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Medium",null," ",60977]
["2025-10-31","2025-11-03","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER - WE de finition suite CTL en continu","CTL","Medium","ART à prévoir - estim 6 min"," ",54491]
["2025-11-01","2025-11-02","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Weekend","Continuous","22:00","22:00","Aménagement Châtelet - Phase 7\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Coupure Type 5\r\nSAVU VB HS \r\ncas 27331 - 27323 HT\r\nFaisceau B et D HS + HT\r\nFaisceau K innaccessible\r\nFaisceau A accessible uniquement coté Charleroi"," ",54848]
["2025-11-01","2025-11-03","NW",1,"50","A+B","Y.MELLE","AALST","Weekend","Continuous","00:40","04:00","Instandhouding  Y Schellebelle + Wissels Rooster Schellebelle\r\n\r\nY Melle + Aalst NIET IN","CTL","Medium",null," ",59350]
["2025-11-01","2025-11-03","NW",1,"53","A+B","SCHELLEBELLE","DENDERMONDE","Weekend","Continuous","00:40","04:00","Linked to coupure nr 59350 on line 50 tracks(s) A+B from Y.MELLE to AALST: Instandhouding  Y Schellebelle + Wissels Rooster Schellebelle\r\n\r\nY Melle + Aalst NIET IN","CTL","Medium"," "," ",59350]
["2025-11-02","2025-11-07","SE",1,"165","A","VIRTON","HALANZY","AllWeek","Continuous","06:00","06:00","ART stab 3' HKV / 5' HKM\r\nCriblage Phase 1\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART voie A: stabilisation 3’ HKV, 5’ HKM du dim. 2 nov 06h au ven. 7 nov 6h00"," ",59610]
["2025-11-03","2025-11-07","CE",1,"96","B","BRUXELLES-MIDI","LOT","Week","Night","23:30","04:30","Linked to coupure nr 58376 on line 96N tracks(s) A+B from Y.NOORD HALLE to BRUXELLES-MIDI: Renouvellement Caténaires - Zone B2\r\nPréparations","SAVU","Minor_AdHoc"," "," ",58376]
["2025-11-03","2025-11-07","CE",1,"96N","A+B","Y.NOORD HALLE","BRUXELLES-MIDI","Week","Night","23:30","04:30","Renouvellement Caténaires - Zone B2\r\nPréparations","CTL","Minor_AdHoc"," "," ",58376]
["2025-11-03","2025-11-07","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Week","Night","23:00","05:00","Linked to coupure nr 58441 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nweeknachten min 6u\r\n(zie ook schets 'expl L25&L25N')","CTL","Minor_AdHoc"," "," ",58441]
["2025-11-03","2025-11-07","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60990]
["2025-11-03","2025-11-07","SW",1,"75A","*","MOUSCRON","HERSEAUX","Week","Day","06:00","16:00","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 6 - finitions\r\nPhase 6.3 - MHS du faisceau de jour\r\nDossier de concertation validé en octobre 2022","Autre","Minor_AdHoc","Phase 6.3 - MHS du faisceau de jour\r\nTravaux de jour en semaine 42 et 45 de 6h à 16h​"," ",61854]
["2025-11-03","2025-11-08","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59304 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59304]
["2025-11-03","2025-11-08","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:20","04:30","Linked to coupure nr 59304 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","CTL","Minor_AdHoc"," "," ",59304]
["2025-11-03","2025-11-08","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg\r\nTLO L50A/6 Gent Sint Pieters-","CTL","Minor_AdHoc"," "," ",59304]
["2025-11-03","2025-11-08","NW",1,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59304 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59304]
["2025-11-03","2025-11-08","NW",1,"75","B","GENT-SINT-PIETERS","DE PINTE","Week","Night","23:20","04:30","Linked to coupure nr 59304 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59304]
["2025-11-03","2025-11-17","SE",1,"43","A","BOMAL","MARLOIE","AllWeek","Night","23:00","05:00","Criblage: bourrage de révision, contraintes et finitions","CTL","Minor_AdHoc"," "," ",55901]
["2025-11-04","2025-11-08","CE",1,"124","A+B","BRUXELLES-MIDI","Y.FOREST-EST","Week","Night","00:45","04:30","Afwerkingsnachten Vernieuwing wissels inrit FBMZ verlengde L124","CTL","Minor_AdHoc","TLO L124 + FBMZ sp 20+21\r\nL96 sp A + Bypass BDS\r\nFBMZ perron sp 20+21 verlengd tot in koker 3 seinen E5/EX-6\r\nFBMZ sp 18-19-20-21 ontoegankelijk"," ",61840]
["2025-11-04","2025-11-08","CE",1,"28/3","S","Y.FOREST-EST","Y.CUREGHEM","Week","Night","00:45","04:30","Linked to coupure nr 61840 on line 124 tracks(s) A+B from BRUXELLES-MIDI to Y.FOREST-EST: Afwerkingsnachten Vernieuwing wissels inrit FBMZ verlengde L124","CTL","Minor_AdHoc"," "," ",61840]
["2025-11-04","2025-11-08","CE",1,"96","A","BRUXELLES-MIDI","Y.RUISBROEK","Week","Night","00:45","04:30","Linked to coupure nr 61840 on line 124 tracks(s) A+B from BRUXELLES-MIDI to Y.FOREST-EST: Afwerkingsnachten Vernieuwing wissels inrit FBMZ verlengde L124","SAVU","Minor_AdHoc"," "," ",61840]
["2025-11-05","2025-11-05","SE",1,"165","A","VIRTON","HALANZY","Week","Day","06:00","22:00","Criblage - Phase 1\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","​Bourrage de Révision​\r\n5 nov Voie A HS entre Virton et Halanzy 6h00-22h00","HKM à adapter",56508]
["2025-11-05","2025-11-12","SE",1,"165","A","HALANZY","VIRTON","AllWeek","Continuous","06:00","22:00","Criblage - Phase 2\r\nDossier de concertation validé en octobre 2022","SAVU","High","ART voie B : protection 3’ HKV, 5’ HKM du ven. 7 nov 6h00 au mer. 12 nov 6h00\r\nMax 4 trains/h entre 06h et 22h pour ART 60 km/h"," ",56316]
["2025-11-07","2025-11-10","CE",1,"96","B","BRUXELLES-MIDI","LOT","Weekend","Continuous","23:30","04:30","Linked to coupure nr 58377 on line 96N tracks(s) A+B from Y.NOORD HALLE to BRUXELLES-MIDI: Renouvellement Caténaires - Zone B2\r\nTravaux","SAVU","Minor_AdHoc"," "," ",58377]
["2025-11-07","2025-11-10","CE",1,"96N","A+B","Y.NOORD HALLE","BRUXELLES-MIDI","Weekend","Continuous","23:30","04:30","Renouvellement Caténaires - Zone B2\r\nTravaux","CTL","Medium"," "," ",58377]
["2025-11-07","2025-11-10","NW",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Medium",null," ",60978]
["2025-11-07","2025-11-10","SE",1,"161","B","BAKENBOS","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59171]
["2025-11-08","2025-11-09","SW",1,"130","A+B","LE CAMPINAIRE","CHATELET-GRIL OUEST","Weekend","Continuous","22:00","22:00","Aménagement Châtelet - Phase 7\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Coupure Type 5\r\nSAVU VB HS \r\ncas 27331 - 27323 HT\r\nFaisceau B et D HS + HT\r\nFaisceau K innaccessible\r\nFaisceau A accessible uniquement coté Charleroi"," ",54849]
["2025-11-08","2025-11-09","SW",1,"130","A+B","TAMINES","CHATELET-GRIL OUEST","Weekend","Continuous","06:00","17:00","Maintenance Z15. 51 P4+","CTL","Medium"," "," ",53522]
["2025-11-08","2025-11-10","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Weekend","Continuous","23:00","05:00","Linked to coupure nr 58445 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nTLO weekend vanaf nacht vrij/zat\r\n(zie ook schets 'expl L25&L25N')","CTL","Medium"," "," ",58445]
["2025-11-08","2025-11-10","SW",1,"96","A+B","QUEVY-FRONTIERE","QUEVY","Weekend","Continuous","06:00","04:00","Travaux SNCF\r\nV RM 14h00","CTL","Medium",null," ",62951]
["2025-11-10","2025-11-14","CE",1,"96","A","BRUXELLES-MIDI","LOT","Week","Night","23:30","04:30","Linked to coupure nr 58379 on line 96N tracks(s) A+B from Y.NOORD HALLE to BRUXELLES-MIDI: Renouvellement Caténaires - Zone A2-A3\r\nPréparations","SAVU","Minor_AdHoc"," "," ",58379]
["2025-11-10","2025-11-14","CE",1,"96N","A+B","Y.NOORD HALLE","BRUXELLES-MIDI","Week","Night","23:30","04:30","Renouvellement Caténaires - Zone A2-A3\r\nPréparations","CTL","Minor_AdHoc"," "," ",58379]
["2025-11-10","2025-11-14","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Week","Night","23:00","05:00","Linked to coupure nr 58442 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nweeknachten min 6u\r\n\r\n(zie ook schets 'expl L25&L25N')","CTL","Minor_AdHoc"," "," ",58442]
["2025-11-10","2025-11-14","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60991]
["2025-11-10","2025-11-14","SW",1,"124","A+B","Y.NORD","CHARLEROI-SUD","Week","Night","23:30","04:30","Aménagement Grill Charleroi-Sud - Phase 1.1","CTL","Minor_AdHoc","MHS en continu L124 Voie A+B  + L124A VA + faisceau A\r\nCoupure Type 1"," ",54813]
["2025-11-10","2025-11-14","SW",1,"124A","A","CHARLEROI-SUD","Y.NORD","Week","Night","23:30","04:30","Linked to coupure nr 54813 on line 124 tracks(s) A+B from Y.NORD to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.1","SAVU","Minor_AdHoc"," "," ",54813]
["2025-11-10","2025-11-14","SW",1,"94","A+B","TOURNAI","BLANDAIN-FRONTIERE","Week","Night","22:45","04:10","Travaux de renouvellement du PI 87.005 et de suppression du PN2 par la construction d'un nouveau pont-cadre.\r\nNuits de préparation à la démolition du PI 87.005","CTL","Minor_AdHoc"," "," ",55553]
["2025-11-10","2025-11-15","CE",1,"27","A","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 62034 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerken heropbouw brugdeel 3 en brugdeel 4","SAVU","Minor_AdHoc"," "," ",62034]
["2025-11-10","2025-11-15","CE",1,"27D","S","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 62034 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerken heropbouw brugdeel 3 en brugdeel 4","CTL","Minor_AdHoc"," "," ",62034]
["2025-11-10","2025-11-15","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","Week","Night","23:40","04:30","Linked to coupure nr 62034 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerken heropbouw brugdeel 3 en brugdeel 4","CTL","Minor_AdHoc"," "," ",62034]
["2025-11-10","2025-11-15","SW",1,"118","A+B","BRACQUEGNIES","MONS","Week","Night","22:30","04:30","Renouvellement des chapes d'étanchéité des PI 30.800, 30.820 et 34.175 + pose de passerelles de service sur le PI 34.175\r\nNuits de finitions","CTL","Minor_AdHoc",null," ",55625]
["2025-11-10","2025-11-15","SW",1,"75A","A+B","MOUSCRON","HERSEAUX","Week","Night","22:00","06:00","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 6 - finitions\r\nPhase 6.2 - travaux au-dessus des voies de la L75A + faisceau","CTL","Minor_AdHoc",null," ",55888]
["2025-11-10","2025-11-21","CE",1,"27","A","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 59748 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: voorbereidende werken heropbouw brugdeel 3 en afwerking brugdeel 4","SAVU","Minor_AdHoc"," "," ",59748]
["2025-11-10","2025-11-21","CE",1,"27D","S","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 59748 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: voorbereidende werken heropbouw brugdeel 3 en afwerking brugdeel 4","CTL","Minor_AdHoc"," "," ",59748]
["2025-11-10","2025-11-21","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","Week","Night","23:40","04:30","Linked to coupure nr 59748 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: voorbereidende werken heropbouw brugdeel 3 en afwerking brugdeel 4","CTL","Minor_AdHoc"," "," ",59748]
["2025-11-10","2025-12-01","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-GROUPE R","AllWeek","Continuous","07:00","04:00","Vernieuwing wissels 60G-61G-62G-63G","Autre","Minor_AdHoc","FSR bundel R sp 741 tem 744 continu BDS\r\nUitbreiding tijdens de nachten: sp 740+745 en bundelkoppen aan beide zijden: geen verkeer mogelijktussen groep G en groep R (bundel R in cds kant FVV."," ",59451]
["2025-11-10","2025-12-28","CE",1,"161","*","SCHAERBEEK","SCHAERBEEK","AllWeek","Continuous","(vide)","(vide)","P149301: Renovatiewerken perron 4 Schaarbeek Reizigers\r\nPerron 4 BDS maar HK kunnen rijden.","Autre","Minor_AdHoc","HK kunnen niet stoppen."," ",58784]
["2025-11-10","2025-12-31","CE",1,"161","B","SCHAERBEEK","SCHAERBEEK","Week","Night","23:00","05:00","P723301: Renovatiewerken perron 4 Schaarbeek Reizigers\r\nBDS tss 05J en 51L/52AL","Autre","Minor_AdHoc","FSR sporen 4 BDS"," ",59775]
["2025-11-12","2025-11-15","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59303 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59303]
["2025-11-12","2025-11-15","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:20","04:30","Linked to coupure nr 59303 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","CTL","Minor_AdHoc"," "," ",59303]
["2025-11-12","2025-11-15","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg\r\nTLO L50A/6 Gent Sint Pieters-","CTL","Minor_AdHoc"," "," ",59303]
["2025-11-12","2025-11-15","NW",1,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59303 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59303]
["2025-11-12","2025-11-15","NW",1,"75","B","GENT-SINT-PIETERS","DE PINTE","Week","Night","23:20","04:30","Linked to coupure nr 59303 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59303]
["2025-11-12","2025-11-18","SE",1,"165","A","HALANZY","VIRTON","AllWeek","Continuous","06:00","06:00","ART 3’ HKV,  5’ HKM\r\nCriblage - Phase 2\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART voie A : stabilisation 3’ HKV,  5’ HKM du mer. 12 nov 6h00 au mar. 18 nov 06h00"," ",59611]
["2025-11-14","2025-11-17","CE",1,"96","A","BRUXELLES-MIDI","LOT","Weekend","Continuous","23:30","05:00","Linked to coupure nr 58378 on line 96N tracks(s) A+B from Y.NOORD HALLE to BRUXELLES-MIDI: Renouvellement Caténaires - Zone A2+A3\r\nTravaux","SAVU","Minor_AdHoc"," "," ",58378]
["2025-11-14","2025-11-17","CE",1,"96N","A+B","Y.NOORD HALLE","BRUXELLES-MIDI","Weekend","Continuous","23:30","05:00","Renouvellement Caténaires - Zone A2+A3\r\nTravaux","CTL","Medium"," "," ",58378]
["2025-11-14","2025-11-17","NW",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Medium",null," ",60979]
["2025-11-14","2025-11-17","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n26 - Déroulage Rhisnes- Mont ST Guibert","SAVU_CTRL","Minor_AdHoc","2 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 25)"," ",59642]
["2025-11-14","2025-11-17","SE",1,"161","A+B","OTTIGNIES","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER\r\nGare Ottignies","Autre","Minor_AdHoc","voies 4 et 5 à quai HS\r\n+ Voie 3 à quai inaccessible côté Bruxelles\r\nVoie 142 HS \r\nPas de lien L161-L139 et L161-L140. PED SNCB inaccessible. Circulation L161 vers Namur à contrevoie en gare"," ",59179]
["2025-11-14","2025-11-17","SW",1,"124","A+B","MARCHIENNE-AU-PONT","CHARLEROI-SUD","Weekend","Continuous","23:30","04:30","Aménagement Grill Charleroi-Sud - Phase 1.1\r\nRq 333 : demande EF's suite semestrielle : Pas de TW supplémentaire en L112 et L124 côté nord","CTL","Medium","MHS en continu L124 Voie A+B  + L124A VA + faisceau A\r\nExtension nuits ven^sa - sa^dim L124 Y.Nord - Marchienne-au-Pont  (liaison L140 - L130A inaccessible)\r\nCoupure Type 1\r\n\r\n+ MHS tronçon entre 36G - 38BG HS du 17/11 au 31/11 (id 54812)"," ",53230]
["2025-11-14","2025-11-17","SW",1,"124A","A","CHARLEROI-SUD","Y.NORD","Weekend","Continuous","23:30","04:30","Linked to coupure nr 53230 on line 124 tracks(s) A+B from MARCHIENNE-AU-PONT to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.1\r\nRq 333 : demande EF's suite semestrielle : Pas de TW supplémentaire en L112 et L124 côté nord","SAVU","Minor_AdHoc"," "," ",53230]
["2025-11-14","2025-11-17","SW",1,"94","A+B","TOURNAI","BLANDAIN-FRONTIERE","Weekend","Continuous","22:45","04:10","Travaux de renouvellement du PI 87.005 et de suppression du PN2 par la construction d'un nouveau pont-cadre.\r\nCTL de WE en continu pour la démolition du PI 87.005","CTL","Medium","ART stabilisation 2 min"," ",55557]
["2025-11-15","2025-11-15","SE",1,"165","A","VIRTON","HALANZY","Week","Day","06:00","22:00","Criblage - Phase 2\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Bourrage de révision​\r\n15 nov Voie A HS entre Virton et Halanzy 6h00-22h00","HKM à adapter",56516]
["2025-11-15","2025-11-17","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Weekend","Continuous","23:00","05:00","Linked to coupure nr 58446 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nTLO weekend vanaf nacht vrij/zat\r\n(zie ook schets 'expl L25&L25N')","CTL","Medium"," "," ",58446]
["2025-11-15","2025-11-17","SW",1,"96","A+B","QUEVY-FRONTIERE","QUEVY","Weekend","Continuous","06:00","04:00","Travaux SNCF\r\nV RM 14h00","CTL","Medium",null," ",62950]
["2025-11-17","2025-11-21","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59238 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59238]
["2025-11-17","2025-11-21","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59238 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59238]
["2025-11-17","2025-11-21","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59238]
["2025-11-17","2025-11-21","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59238 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59238]
["2025-11-17","2025-11-21","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60992]
["2025-11-17","2025-11-21","SW",1,"124","A","Y.NORD","CHARLEROI-SUD","Week","Night","23:30","04:30","Aménagement Grill Charleroi-Sud - Phase 1.2","SAVU","Minor_AdHoc","MHS L124 Voie A +L140 VA + L140/1 + faisceau A\r\nCoupure Type 2\r\nliaison 37AG – 37BG, HS à partir de la nuit 17^18/11/2025 (et ce jusqu’au 24/11/2025)"," ",54815]
["2025-11-17","2025-11-21","SW",1,"124","A+B","CHARLEROI-SUD","Y.NORD","Week","Continuous","04:30","23:30","Aménagement Grill Charleroi-Sud - Phase 2.1","Autre","Minor_AdHoc","MHS tronçon entre 36G - 38BG HS du 17/11 au 21/11 (id 54812)"," ",54812]
["2025-11-17","2025-11-21","SW",1,"140","A","CHARLEROI-OUEST","Y.NORD","Week","Night","23:30","04:30","Linked to coupure nr 54815 on line 124 tracks(s) A from Y.NORD to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.2","SAVU","Minor_AdHoc"," "," ",54815]
["2025-11-17","2025-11-21","SW",1,"140/1","S","CHARLEROI-OUEST","CHARLEROI-SUD","Week","Night","23:30","04:30","Linked to coupure nr 54815 on line 124 tracks(s) A from Y.NORD to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.2","CTL","Minor_AdHoc"," "," ",54815]
["2025-11-17","2025-11-21","SW",1,"75A","A","MOUSCRON","HERSEAUX","Week","Day","06:00","16:00","Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nPhase 6 - finitions\r\nPhase 6.3 - travaux au-dessus des voies du faisceau","SAVU","Minor_AdHoc","MHS des voies de faisceau au niveau du km 54.663 de la gare de Mouscron"," ",55891]
["2025-11-17","2025-11-22","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-NEKKERSPOEL","Week","Night","23:00","05:00","Masterplan Mechelen:\r\nspoor 9 +10 Mechelen , afbraak en opbouw beddingen , nieuwe BVL-constructies\r\nwissels 33N + 34N niet in\r\nzie schets 'expl L25' (tabblad schetsen Mechelen)\r\n5 weeknachten: min 6u","CTL","Minor_AdHoc","geen impact L25N!"," ",58764]
["2025-11-17","2025-11-22","SW",1,"130A","A+B","ERQUELINNES-FRONTIERE","LA SAMBRE","Week","Night","23:00","04:10","Renouvellement PS bk 118.788  + 104.903 - préparation démolition","CTL","Minor_AdHoc"," "," ",56484]
["2025-11-17","2025-11-22","SW",1,"94","A+B","TOURNAI","BLANDAIN-FRONTIERE","Week","Night","22:45","04:10","Travaux de renouvellement du PI 87.005 et de suppression du PN2 par la construction d'un nouveau pont-cadre.\r\nNuits de finitions suite à la démolition du PI 87.005","CTL","Minor_AdHoc"," "," ",55554]
["2025-11-17","2025-11-29","CE",1,"27","A","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 62033 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerken heropbouw brugdeel 3 en brugdeel 4","SAVU","Minor_AdHoc"," "," ",62033]
["2025-11-17","2025-11-29","CE",1,"27D","S","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 62033 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerken heropbouw brugdeel 3 en brugdeel 4","CTL","Minor_AdHoc"," "," ",62033]
["2025-11-17","2025-11-29","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","Week","Night","23:40","04:30","Linked to coupure nr 62033 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerken heropbouw brugdeel 3 en brugdeel 4","CTL","Minor_AdHoc"," "," ",62033]
["2025-11-20","2025-11-26","SE",1,"165","A","Y.AUBANGE","HALANZY","AllWeek","Continuous","06:00","06:00","Criblage - Phase 3\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","ART voie B : protection 3’ HKV,  6’ HKM du jeu. 20 nov 6h00 au mer. 26 nov 6h00.\r\nMax 4 trains/h entre 6h00 et 22h00 pour ART 60 km/h","HKM à adapter",56505]
["2025-11-21","2025-11-21","SE",1,"165","A+B","Y.AUBANGE","VIRTON","Week","Day","06:00","22:00","Criblage - Phase 3\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Ven. 21 nov extension côté Virton 6h00-22h00 \r\nlié id 56505","HKM à adapter",56510]
["2025-11-21","2025-11-24","NW",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Medium",null," ",60980]
["2025-11-21","2025-11-24","SE",1,"161","A/B","NAMUR","GEMBLOUX","Weekend","Continuous","23:00","05:00","Travaux caténaires\r\n26 - Déroulage Rhisnes- Mont ST Guibert","SAVU_CTRL","Minor_AdHoc","2 we en continu de SAVU du vend 22h au lun 05h + CTL de nuits (après le point 25)"," ",59643]
["2025-11-21","2025-11-24","SE",1,"161","A+B","WATERMAEL","OTTIGNIES","Weekend","Continuous","23:30","04:50","Travaux RER","CTL","Medium","ART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59162]
["2025-11-21","2025-11-24","SW",1,"124","A","Y.NORD","CHARLEROI-SUD","Weekend","Continuous","23:30","04:30","Aménagement Grill Charleroi-Sud - Phase 1.2","SAVU","Minor_AdHoc","MHS L124 Voie A +L140 VA + L140/1 + faisceau A\r\nCoupure Type 2"," ",53231]
["2025-11-21","2025-11-24","SW",1,"140","A","CHARLEROI-OUEST","Y.NORD","Weekend","Continuous","23:30","04:30","Linked to coupure nr 53231 on line 124 tracks(s) A from Y.NORD to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.2","SAVU","Minor_AdHoc"," "," ",53231]
["2025-11-21","2025-11-24","SW",1,"140/1","S","CHARLEROI-OUEST","CHARLEROI-SUD","Weekend","Continuous","23:30","04:30","Linked to coupure nr 53231 on line 124 tracks(s) A from Y.NORD to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.2","CTL","Medium"," "," ",53231]
["2025-11-22","2025-11-24","CE",1,"27","A","SCHAERBEEK","Y.SCHAERBEEK-GROUPE G","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59133 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1.3: plaatsing brugdeel 4 gedeelte boven L27D/L27F/L36/AL27","SAVU","Minor_AdHoc"," "," ",59133]
["2025-11-22","2025-11-24","CE",1,"27D","A+B","SCHAERBEEK","Y.SCHAERBEEK-CARWASH","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59133 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1.3: plaatsing brugdeel 4 gedeelte boven L27D/L27F/L36/AL27","CTL","Medium"," "," ",59133]
["2025-11-22","2025-11-24","CE",1,"27D/4","A+B","SCHAERBEEK","SCHAERBEEK-GROUPE R","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59133 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1.3: plaatsing brugdeel 4 gedeelte boven L27D/L27F/L36/AL27","CTL","Medium"," "," ",59133]
["2025-11-22","2025-11-24","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","Weekend","Continuous","00:45","04:30","Linked to coupure nr 59133 on line 36 tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1.3: plaatsing brugdeel 4 gedeelte boven L27D/L27F/L36/AL27","CTL","Medium"," "," ",59133]
["2025-11-22","2025-11-24","CE",1,"27F","*","SCHAERBEEK-GROUPE R","SCHAERBEEK-GROUPE R","Weekend","Continuous","00:30","04:00","Vernieuwing wissels 60G-61G-62G-63G","Autre","Minor_AdHoc","FSR bundel R sp 741 tem 744 continu BDS\r\nSp 740+745 en bundelkoppen aan beide zijden BDS: geen verkeer mogelijk tussen groep G en groep R (bundel R in cds kant FVV."," ",59452]
["2025-11-22","2025-11-24","SW",1,"96","A+B","QUEVY-FRONTIERE","QUEVY","Weekend","Continuous","06:00","04:00","Travaux SNCF\r\nV RM 14h00","CTL","Medium",null," ",62949]
["2025-11-24","2025-11-28","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Week","Night","23:00","05:00","Linked to coupure nr 58443 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nweeknachten min 6u\r\n\r\n(zie ook schets 'expl L25&L25N')","CTL","Minor_AdHoc"," "," ",58443]
["2025-11-24","2025-11-28","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59239 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59239]
["2025-11-24","2025-11-28","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:30","04:20","Linked to coupure nr 59239 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","CTL","Minor_AdHoc"," "," ",59239]
["2025-11-24","2025-11-28","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels","CTL","Minor_AdHoc"," "," ",59239]
["2025-11-24","2025-11-28","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:30","04:20","Linked to coupure nr 59239 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint ","SAVU","Minor_AdHoc"," "," ",59239]
["2025-11-24","2025-11-28","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60993]
["2025-11-24","2025-11-28","SW",1,"124A","B","Y.NORD","CHARLEROI-SUD","Week","Night","23:30","04:30","Aménagement Grill Charleroi-Sud - Phase 1.3","SAVU","Minor_AdHoc","MHS L124A Voie B + L130A + voies en gare + Faisceau C\r\nCoupure Type 3\r\nliaison 28AG - 28BG HS à partir du 24/11/2025 (et ce JNA)\r\nliaison 31G – 32G, HS à partir du 24/11/2025 (et ce JNA)"," ",54817]
["2025-11-24","2025-11-28","SW",1,"130A","A+B","CHARLEROI-SUD","Y.NORD","Week","Night","23:30","04:30","Linked to coupure nr 54817 on line 124A tracks(s) B from Y.NORD to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.3","CTL","Minor_AdHoc"," "," ",54817]
["2025-11-24","2025-11-29","SW",1,"94","A+B","TOURNAI","BLANDAIN-FRONTIERE","Week","Night","22:45","04:10","Travaux de renouvellement du PI 87.005 et de suppression du PN2 par la construction d'un nouveau pont-cadre.\r\nNuits de finitions suite à la démolition du PI 87.005","CTL","Minor_AdHoc","ART 2min"," ",55555]
["2025-11-24","2025-12-05","CE",1,"94","A+B","Y.NOORD HALLE","HALLE","Week","Night","23:30","04:30","Linked to coupure nr 58382 on line 96 tracks(s) A+B from HALLE to LOT: Renouvellement Caténaires - Zones Z.A7-Z.A8-Z.B7-Z.B8\r\nPréparations","CTL","Minor_AdHoc"," "," ",58382]
["2025-11-24","2025-12-05","CE",1,"96","A+B","HALLE","LOT","Week","Night","23:30","04:30","Renouvellement Caténaires - Zones Z.A7-Z.A8-Z.B7-Z.B8\r\nPréparations","CTL","Minor_AdHoc"," "," ",58382]
["2025-11-24","2025-12-05","CE",1,"96N","B","BRUXELLES-MIDI","Y.NOORD HALLE","Week","Night","23:30","04:30","Linked to coupure nr 58382 on line 96 tracks(s) A+B from HALLE to LOT: Renouvellement Caténaires - Zones Z.A7-Z.A8-Z.B7-Z.B8\r\nPréparations","SAVU","Minor_AdHoc"," "," ",58382]
["2025-11-24","2025-12-08","SE",1,"166","B","HOUYET","BEAURAING","AllWeek","Continuous","06:00","06:00","ART stab 3min\r\nAssainissement bk 16.200.\r\nDossier concertation octobre 2022","ART","Minor_AdHoc","ART 3 minutes pendants 12 semaines du 15/09 au 08/12 (10 semaines protection  de chantier+ 2 semaines pour fin stabilisation post chantier)"," ",59614]
["2025-11-26","2025-11-29","SE",1,"165","A","Y.AUBANGE","HALANZY","AllWeek","Continuous","06:00","06:00","ART 3min/6min\r\nCriblage - Phase 3\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART voie A: stabilisation 3’ HKV, 6’ HKM du mer. 26 nov 6h00 au sam. 29 nov 6h00","HKM à adapter",56506]
["2025-11-28","2025-11-28","SE",1,"165","A","Y.AUBANGE","HALANZY","Week","Day","06:00","22:00","Criblage - Phase 3\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Bourrage de révision:​\r\nVen. 28 nov. voie A entre Halanzy et Y Aubange 6h00-22h00","HKM à adapter",56509]
["2025-11-28","2025-12-01","CE",1,"94","A","Y.NOORD HALLE","HALLE","Weekend","Continuous","23:30","04:30","Linked to coupure nr 58380 on line 96 tracks(s) A+B from HALLE to LOT: Renouvellement Caténaires - Zones Z.A7-Z.A8-Z.B7-Z.B8\r\nTravaux WE 1/2","SAVU","Minor_AdHoc"," "," ",58380]
["2025-11-28","2025-12-01","CE",1,"96","A+B","HALLE","LOT","Weekend","Continuous","23:30","04:30","Renouvellement Caténaires - Zones Z.A7-Z.A8-Z.B7-Z.B8\r\nTravaux WE 1/2","CTL","Medium"," "," ",58380]
["2025-11-28","2025-12-01","CE",1,"96N","B","BRUXELLES-MIDI","Y.NOORD HALLE","Weekend","Continuous","23:30","04:30","Linked to coupure nr 58380 on line 96 tracks(s) A+B from HALLE to LOT: Renouvellement Caténaires - Zones Z.A7-Z.A8-Z.B7-Z.B8\r\nTravaux WE 1/2","SAVU","Minor_AdHoc"," "," ",58380]
["2025-11-28","2025-12-01","NW",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Medium",null," ",60981]
["2025-11-28","2025-12-01","SE",1,"42","A+B","TROIS-PONTS","VIELSALM","Weekend","Continuous","23:40","05:00","Entretien manuel et mécanisés des PN","CTL","Medium","La limite de MHS du côté Vielsalm sera un SMA au droit du signal OX-V.45 (BK 66.153) pour traiter le PN 11 à la BK 65.580"," ",55078]
["2025-11-28","2025-12-01","SW",1,"124","A+B","Y.FOREST-EST","BAULERS-GRIL D","Weekend","Continuous","23:30","04:40","Travaux RER - WE de finition suite CTL en continu","CTL","Medium","ART à prévoir"," ",54947]
["2025-11-28","2025-12-01","SW",1,"124A","B","Y.NORD","CHARLEROI-SUD","Weekend","Continuous","23:30","04:30","Aménagement Grill Charleroi-Sud - Phase 1.3","SAVU","Minor_AdHoc","MHS L124A Voie B + L130A + voies en gare + Faisceau C\r\nCoupure Type 3"," ",53232]
["2025-11-28","2025-12-01","SW",1,"130A","A+B","CHARLEROI-SUD","Y.NORD","Weekend","Continuous","23:30","04:30","Linked to coupure nr 53232 on line 124A tracks(s) B from Y.NORD to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.3","CTL","Medium"," "," ",53232]
["2025-11-29","2025-11-30","SW",1,"130A","A+B","ERQUELINNES-FRONTIERE","LA SAMBRE","Weekend","Continuous","06:00","17:00","Maintenance Z2. 51  P4+","CTL","Medium"," "," ",53533]
["2025-11-29","2025-12-01","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Weekend","Continuous","23:00","05:00","Linked to coupure nr 58447 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nTLO weekend vanaf nacht vrij/zat\r\nL27 sp B - wissels L53/L53A beschikbaar -->W05M - L53 ni\r\n\r\n(zie ook schets 'ex","CTL","Medium"," "," ",58447]
["2025-11-29","2025-12-01","NE",1,"27","B","Y.WEERDE","MECHELEN","Weekend","Continuous","23:00","05:00","Linked to coupure nr 58447 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nTLO weekend vanaf nacht vrij/zat\r\nL27 sp B - wissels L53/L53A beschikbaar -->W05M - L53 ni\r\n\r\n(zie ook schets 'ex","SAVU","Minor_AdHoc"," "," ",58447]
["2025-11-29","2025-12-01","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 59241 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters stap 33 : Indienststelling perronsporen IV+V\r\n\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. W","SAVU","Minor_AdHoc"," "," ",59241]
["2025-11-29","2025-12-01","NW",1,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:30","04:30","Masterplan Gent Sint Pieters stap 33 : Indienststelling perronsporen IV+V\r\n\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. West Driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters -Y West Driehoek Ledeberg","CTL","Medium"," "," ",59241]
["2025-11-29","2025-12-01","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 59241 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters stap 33 : Indienststelling perronsporen IV+V\r\n\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. W","SAVU","Minor_AdHoc"," "," ",59241]
["2025-11-29","2025-12-05","SE",1,"165","A","Y.AUBANGE","HALANZY","AllWeek","Continuous","06:00","06:00","Criblage - Phase 4\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","ART voie B : protection 3’ HKV,  6’ HKM du sam. 29 nov 6h00 au mer. 05 déc 06h00​\r\nMax 4 trains/h entre 6h00 et 22h00 pour ART 60 km/h","HKM à adapter",56507]
["2025-12-01","2025-12-05","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60994]
["2025-12-01","2025-12-06","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59302 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59302]
["2025-12-01","2025-12-06","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:20","04:30","Linked to coupure nr 59302 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","CTL","Minor_AdHoc"," "," ",59302]
["2025-12-01","2025-12-06","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg\r\nTLO L50A/6 Gent Sint Pieters-","CTL","Minor_AdHoc"," "," ",59302]
["2025-12-01","2025-12-06","NW",1,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59302 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59302]
["2025-12-01","2025-12-06","NW",1,"75","B","GENT-SINT-PIETERS","DE PINTE","Week","Night","23:20","04:30","Linked to coupure nr 59302 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59302]
["2025-12-01","2025-12-06","SW",1,"118","A+B","BRACQUEGNIES","MONS","Week","Night","22:30","04:30","Renouvellement des chapes d'étanchéité des PI 30.800, 30.820 et 34.175 + pose de passerelles de service sur le PI 34.175\r\nNuits de finitions","CTL","Minor_AdHoc",null," ",55624]
["2025-12-01","2025-12-06","SW",1,"124","A+B","Y.NORD","CHARLEROI-SUD","Week","Night","23:30","04:30","Aménagement Grill Charleroi-Sud - Phase 1.3","CTL","Minor_AdHoc","MHS en continu L124 Voie A+B  + L124A VA + faisceau A\r\nCoupure Type 1"," ",54814]
["2025-12-01","2025-12-06","SW",1,"124A","A","CHARLEROI-SUD","Y.NORD","Week","Night","23:30","04:30","Linked to coupure nr 54814 on line 124 tracks(s) A+B from Y.NORD to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.3","SAVU","Minor_AdHoc"," "," ",54814]
["2025-12-01","2025-12-12","CE",1,"25","A+B","SCHAERBEEK","VILVOORDE","Week","Night","23:50","04:30","Vernieuwing Albertbrug fase 2: voorbereiding plaatsing brugdeel 4 gedeelte boven L25/L27/BL36","CTL","Minor_AdHoc","L25/BL36/BL27 afgesloten"," ",59750]
["2025-12-01","2025-12-12","CE",1,"27","B","SCHAERBEEK","Y.SCHAERBEEK-GROUPE G","Week","Night","23:50","04:30","Linked to coupure nr 59750 on line 25 tracks(s) A+B from SCHAERBEEK to VILVOORDE: Vernieuwing Albertbrug fase 2: voorbereiding plaatsing brugdeel 4 gedeelte boven L25/L27/BL36","SAVU","Minor_AdHoc"," "," ",59750]
["2025-12-01","2025-12-13","CE",1,"27","A","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 62035 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerken heropbouw brugdeel 3","SAVU","Minor_AdHoc"," "," ",62035]
["2025-12-01","2025-12-13","CE",1,"27D","S","BRUXELLES-NORD-GRIL F","SCHAERBEEK","Week","Night","23:40","04:30","Linked to coupure nr 62035 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerken heropbouw brugdeel 3","CTL","Minor_AdHoc"," "," ",62035]
["2025-12-01","2025-12-13","CE",1,"27F","S","SCHAERBEEK","SCHAERBEEK-GRIL N","Week","Night","23:40","04:30","Linked to coupure nr 62035 on line 36N tracks(s) A+B from SCHAERBEEK to Y.DIEGEM: Vernieuwing Albertbrug fase 1: nachtwerken heropbouw brugdeel 3","CTL","Minor_AdHoc"," "," ",62035]
["2025-12-02","2025-12-02","SE",1,"165","A","VIRTON","Y.AUBANGE","Week","Day","06:00","22:00","Criblage - Phase 4\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","2 déc extension côté Y aubange-Virton 6h00-22h00\r\nlié id 56507","HKM à adapter",56518]
["2025-12-05","2025-12-08","CE",1,"161","A/B","WATERMAEL","BAKENBOS","Weekend","Continuous","23:30","04:50","Travaux RER","SAVU_CTRL","Minor_AdHoc","CTL de nuit de WE sam/dim et dim/lun (BT)\r\nART 2’ pendant une semaine après ce WE (à inclure au temps tampon)."," ",59175]
["2025-12-05","2025-12-08","CE",1,"94","A","Y.NOORD HALLE","HALLE","Weekend","Continuous","23:30","04:30","Linked to coupure nr 58381 on line 96 tracks(s) A+B from HALLE to LOT: Renouvellement Caténaires - Zones Z.A7-Z.A8-Z.B7-Z.B8\r\nTravaux WE 2/2","SAVU","Minor_AdHoc"," "," ",58381]
["2025-12-05","2025-12-08","CE",1,"96","A+B","HALLE","LOT","Weekend","Continuous","23:30","04:30","Renouvellement Caténaires - Zones Z.A7-Z.A8-Z.B7-Z.B8\r\nTravaux WE 2/2","CTL","Medium"," "," ",58381]
["2025-12-05","2025-12-08","CE",1,"96N","B","BRUXELLES-MIDI","Y.NOORD HALLE","Weekend","Continuous","23:30","04:30","Linked to coupure nr 58381 on line 96 tracks(s) A+B from HALLE to LOT: Renouvellement Caténaires - Zones Z.A7-Z.A8-Z.B7-Z.B8\r\nTravaux WE 2/2","SAVU","Minor_AdHoc"," "," ",58381]
["2025-12-05","2025-12-08","NW",1,"60","A+B","JETTE","ASSE","Weekend","Continuous","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Medium",null," ",60982]
["2025-12-05","2025-12-10","SE",1,"165","A","Y.AUBANGE","HALANZY","AllWeek","Continuous","06:00","06:00","ART 3min/6min\r\nCriblage - Phase 4\r\nDossier de concertation validé en octobre 2022","ART","Minor_AdHoc","ART voie A : stabilisation 3’ HKV, 6’ HKM du 05 déc 6h00 au 10 déc 6h00","HKM à adapter",56513]
["2025-12-06","2025-12-08","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 59259 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters stap 33 : Indienststelling perronsporen IV+V\r\n\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. W","SAVU","Minor_AdHoc"," "," ",59259]
["2025-12-06","2025-12-08","NW",1,"50E","A+B","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS","Weekend","Continuous","00:30","04:30","Masterplan Gent Sint Pieters stap 33 : Indienststelling perronsporen IV+V\r\n\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. West Driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters -Y West Driehoek Ledeberg","CTL","Medium"," "," ",59259]
["2025-12-06","2025-12-08","NW",1,"58/1","A","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Weekend","Continuous","00:30","04:30","Linked to coupure nr 59259 on line 50E tracks(s) A+B from Y.WEST DRIEHOEK LEDEBERG to GENT-SINT-PIETERS: Masterplan Gent Sint Pieters stap 33 : Indienststelling perronsporen IV+V\r\n\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. W","SAVU","Minor_AdHoc"," "," ",59259]
["2025-12-08","2025-12-08","SE",1,"165","A","Y.AUBANGE","HALANZY","Week","Day","06:00","22:00","Criblage - Phase 4\r\nDossier de concertation validé en octobre 2022","SAVU","Minor_AdHoc","Bourrage de revision:​\r\n8 déc Voie A entre Halanzy et Y Aubange 06h-22h","HKM à adapter",56517]
["2025-12-08","2025-12-12","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Week","Night","23:00","05:00","Linked to coupure nr 58444 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nweeknachten min 6u\r\nL27 sp B - wissels L53/L53A beschikbaar -->W05M - L53 ni\r\n\r\n\r\n(zie ook schets 'expl L25&L25N ","CTL","Minor_AdHoc"," "," ",58444]
["2025-12-08","2025-12-12","NE",1,"27","B","Y.WEERDE","MECHELEN","Week","Night","23:00","05:00","Linked to coupure nr 58444 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nweeknachten min 6u\r\nL27 sp B - wissels L53/L53A beschikbaar -->W05M - L53 ni\r\n\r\n\r\n(zie ook schets 'expl L25&L25N ","SAVU","Minor_AdHoc"," "," ",58444]
["2025-12-08","2025-12-12","NW",1,"50","B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59301 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59301]
["2025-12-08","2025-12-12","NW",1,"50A/6","A+B","GENT-SINT-PIETERS","Y.ASSELS","Week","Night","23:20","04:30","Linked to coupure nr 59301 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","CTL","Minor_AdHoc"," "," ",59301]
["2025-12-08","2025-12-12","NW",1,"50E","A+B","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg\r\nTLO L50A/6 Gent Sint Pieters-","CTL","Minor_AdHoc"," "," ",59301]
["2025-12-08","2025-12-12","NW",1,"58/1","B","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG","Week","Night","23:20","04:30","Linked to coupure nr 59301 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59301]
["2025-12-08","2025-12-12","NW",1,"60","A+B","JETTE","ASSE","Week","Night","23:50","05:20","Vernieuwing ballast, dwarsliggers en spoorstaven.","CTL","Minor_AdHoc",null," ",60995]
["2025-12-08","2025-12-12","NW",1,"75","B","GENT-SINT-PIETERS","DE PINTE","Week","Night","23:20","04:30","Linked to coupure nr 59301 on line 50E tracks(s) A+B from GENT-SINT-PIETERS to Y.WEST DRIEHOEK LEDEBERG: Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West ","SAVU","Minor_AdHoc"," "," ",59301]
["2025-12-08","2025-12-13","SW",1,"124","A","Y.NORD","CHARLEROI-SUD","Week","Night","23:30","04:30","Aménagement Grill Charleroi-Sud - Phase 1.3","SAVU","Minor_AdHoc","MHS L124 Voie A +L140 VA + L140/1 + faisceau A\r\nCoupure Type 2"," ",54816]
["2025-12-08","2025-12-13","SW",1,"140","A","CHARLEROI-OUEST","Y.NORD","Week","Night","23:30","04:30","Linked to coupure nr 54816 on line 124 tracks(s) A from Y.NORD to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.3","SAVU","Minor_AdHoc"," "," ",54816]
["2025-12-08","2025-12-13","SW",1,"140/1","S","CHARLEROI-OUEST","CHARLEROI-SUD","Week","Night","23:30","04:30","Linked to coupure nr 54816 on line 124 tracks(s) A from Y.NORD to CHARLEROI-SUD: Aménagement Grill Charleroi-Sud - Phase 1.3","CTL","Minor_AdHoc"," "," ",54816]
["2025-12-13","2025-12-15","NE",1,"25","A+B","Y.ABEELSTRAAT","MECHELEN-DIJKSTRAAT","Weekend","Continuous","23:00","05:00","Linked to coupure nr 58448 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nTLO weekend vanaf nacht vrij/zat\r\nL27 sp B - wissels L53/L53A beschikbaar -->W05M - L53 ni\r\n\r\n(zie ook schets 'ex","CTL","Medium"," "," ",58448]
["2025-12-13","2025-12-15","NE",1,"27","B","Y.WEERDE","MECHELEN","Weekend","Continuous","23:00","05:00","Linked to coupure nr 58448 on line 25N tracks(s) A+B from Y.ABEELSTRAAT to MECHELEN-NEKKERSPOEL: masterplan mechelen, spoor 9+10\r\nL25+L25N\r\nTLO weekend vanaf nacht vrij/zat\r\nL27 sp B - wissels L53/L53A beschikbaar -->W05M - L53 ni\r\n\r\n(zie ook schets 'ex","SAVU","Minor_AdHoc"," "," ",58448]

{"sheet":"Data","index":4,"n_rows":24,"n_cols":7,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction"]
["SNCF R",87,"Boulogne-Calais",1,"All day",10868,"Signal work"]
[null,null,"Calais-Dunkerque-Hazebrouck",2,"Day",null,"Switch work"]
[null,null,"Calais-Lille-Aulnoye",3,"Night",null,"Catenary work"]
[null,null,"Hazebrouck-Lens-Aulnoye",4,null,null,"Track work"]
[null,null,"Amiens-Douai",5,null,null,"Rail work"]
[null,null,"Paris-Amiens",6,null,null,"Tunnel work"]
[null,null,"Paris-Busigny",7,null,null,"Bridge work"]
[null,null,"Aulnoye-Longuyon",8,null,null,"Misc. Work"]
[null,null,"Longuyon-Metz-Sarrebourg",9,null,null,"Maintanance"]
[null,null,"Longuyon-Nancy-Sarrebourg",10]
[null,null,"Lerouville-Metz",11]
[null,null,"Lerouville-Nancy",12]
[null,null,"Sarrebourg-Basel",13]
[null,null,"Dijon-Toul",14]
[null,null,"Dijon-Lyon",15]
[null,null,"Dijon-Amberieu-Lyon",16]
[null,null,"Lyon-Valence",17]
[null,null,"Valence - Avignon",18]
[null,null,"Avignon-Miramasparouest",19]
[null,null,"Avignon-Miramasparest",20]
[null,null,"Miramas-Marseille",21]
[null,null,"Miramas-Fos-Marseille",22]
[null,null,"Aulnoye-Feignies-Jeumont",23]

{"sheet":"SNCFR","index":5,"n_rows":1898,"n_cols":21,"rows_kept":1898,"cut":false,"hidden":false,"merged":[[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Time \nof day","Reason for \nrestriction","Description","Last update","Classification","Weekdays","Status"]
[null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to"]
["SNCF-R","3C_HAU_008","LilleBifJustice","< >","Lille-Flandres - Bât Voyageurs","Lille-St-Sauveur - E/S Faisceaux",2023,2023,14,15,"2023-04-09","14:00:00","2023-04-10","10:00:00","periodical","Miscellaneous","Cap, 0,1,AM,DM,N,SA,V1,V2, 20:00, Passe-minuit, DI/LU","2022-01-07","unclassified","1, 7","publication"]
["SNCF-R","3C_HAU_019","LilleBifJustice","< >","Lille-Flandres - Bât Voyageurs","Lille-St-Sauveur - E/S Faisceaux",2023,2023,36,38,"2023-09-09","20:00:00","2023-09-24","11:00:00","periodical","Miscellaneous","Cap, 0,1,AM,DM,N,SA,V1,V2, 15:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_LE_002","LilleFlandres","< >","Lille-Flandres - Bif Verte-Rue","Lille-Flandres - Bif Verte-Rue",2023,2023,9,9,"2023-03-04","15:20:00","2023-03-05","15:21:00","continuous","Miscellaneous","Cap, RB1,RB2,V1,V2, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_LE_003","LilleFlandres","< >","Lille-Flandres - Bif Verte-Rue","Lille-Flandres - Bif Verte-Rue",2023,2023,28,29,"2023-07-14","05:00:00","2023-07-17","05:00:00","continuous","Miscellaneous","Cap, RB1,RB2,V1,V2, 72:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3C_LE_004","LilleFlandres","< >","Lille-Flandres - Bif Verte-Rue","Lille-Flandres - Bif Verte-Rue",2023,2023,32,33,"2023-08-12","14:20:00","2023-08-15","14:20:00","continuous","Miscellaneous","Cap, RB1,RB2,V1,V2, 72:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication"]
["SNCF-R","3C_LE_013","LilleFlandres","< >","Lille-Flandres - Ent/Sort VA TGV","Lille-Flandres - Jonct V2/V1",2023,2023,14,15,"2023-04-09","14:00:00","2023-04-10","10:00:00","periodical","Miscellaneous","Cap, 2,V1,V1,V2,V2, 20:00, Passe-minuit, DI/LU","2022-01-07","unclassified","1, 7","publication"]
["SNCF-R","3C_LE_032","LilleFlandres","< >","Lille-Flandres - Ent/Sort VA TGV","Lille-Flandres - Bât Voyageurs",2023,2023,36,38,"2023-09-09","20:00:00","2023-09-24","11:00:00","periodical","Miscellaneous","Cap, 2,V1,V2, 15:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_ORM-LWP_2","Ormoy-Longueil","< >","Verberie - Bif d'Ageux","Longueil-Ste-Marie - Bif Rivecourt",2023,2023,12,27,"2023-03-24","23:35:00","2023-07-03","04:30:00","continuous","Miscellaneous","Cap, VR1,VR2,VU, 52:55, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3D_ORM-LWP_2","Ormoy-Longueil","< >","Ormoy-Villiers","Estrées-St-Denis - Bât Voyageurs",2023,2023,12,27,"2023-03-24","23:35:00","2023-07-03","04:30:00","continuous","Maintenance","Def, V1,V2, 2V/2, 52:55, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3C_LWP-TGR_1","Longueil Ste Marie-Tergnier",">","Compiègne - ITE Nourylande","Compiègne - Garage Impair",2023,2023,12,45,"2023-03-24","23:39:00","2023-11-06","23:39:00","continuous","Maintenance","Cap, 3,5,7,9, 53:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3C_LWP-TGR_2","Longueil Ste Marie-Tergnier",">","Compiègne - ITE Nourylande","Compiègne - Garage Impair",2023,2023,13,15,"2023-03-31","23:39:00","2023-04-10","23:39:00","continuous","Maintenance","Cap, 5,7,9, 53:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3C_LWP-TGR_3","Longueil Ste Marie-Tergnier",">","Compiègne - ITE Nourylande","Compiègne - Garage Impair",2023,2023,15,28,"2023-04-14","23:39:00","2023-07-10","23:39:00","continuous","Maintenance","Cap, 3,9, 53:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3D_LWP-TGR_2","Longueil Ste Marie-Tergnier","< >","Compiègne - ITE Nourylande","Compiègne - Garage Impair",2023,2023,15,28,"2023-04-14","23:39:00","2023-07-10","23:39:00","continuous","Maintenance","Def, V1,V2, , 53:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3C_TGR1_002","Tergnier(242000)","<","Tergnier - Bât Voyageurs","Ternier - Triage",2023,2023,12,"12","2023-03-25","21:00:00","2023-03-26","14:00:00","continuous","Miscellaneous","Cap, 4,6, 17:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_TGR1_003","Tergnier(242000)","<","Tergnier - Bât Voyageurs","Ternier - Triage",2023,2023,14,15,"2023-04-08","01:00:00","2023-04-10","01:00:00","continuous","Miscellaneous","Cap, 4,6, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3C_TGR1_004","Tergnier(242000)","<","Tergnier - Bât Voyageurs","Ternier - Triage",2023,2023,15,19,"2023-04-15","15:00:00","2023-05-14","15:01:00","continuous","Miscellaneous","Cap, 4,6, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_TGR1_005","Tergnier(242000)","<","Tergnier - Bât Voyageurs","Ternier - Triage",2023,2023,16,16,"2023-04-22","00:40:00","2023-04-23","16:40:00","continuous","Miscellaneous","Cap, 4,6, 40:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_TGR1_006","Tergnier(242000)","<","Tergnier - Bât Voyageurs","Ternier - Triage",2023,2023,17,17,"2023-04-29","10:50:00","2023-04-30","16:50:00","continuous","Miscellaneous","Cap, 4,6, 30:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_TGR2_003","Tergnier(261000)","<","Tergnier - Accès Nord","Fargniers-Garage - ITE ALB",2023,2023,14,15,"2023-04-08","01:00:00","2023-04-10","01:00:00","continuous","Miscellaneous","Cap, 12,V1,V2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3D_TGR-LAO_2","Ternier-Laon","< >","Tergnier - Bât Voyageurs","Laon - Bât Voyageurs",2023,2023,12,12,"2023-03-25","21:00:00","2023-03-26","14:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 17:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_TGR-LAO_3","Ternier-Laon","< >","Tergnier - Bât Voyageurs","Laon - Bât Voyageurs",2023,2023,14,15,"2023-04-08","01:00:00","2023-04-10","01:00:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3D_TGR-LAO_4","Ternier-Laon","< >","Tergnier - Bât Voyageurs","Laon - Bât Voyageurs",2023,2023,15,19,"2023-04-15","15:00:00","2023-05-14","15:01:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_TGR-LAO_5","Ternier-Laon","< >","Tergnier - Bât Voyageurs","Laon - Bât Voyageurs",2023,2023,16,16,"2023-04-22","00:40:00","2023-04-23","16:40:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 40:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_TGR-LAO_6","Ternier-Laon","< >","Tergnier - Bât Voyageurs","Laon - Bât Voyageurs",2023,2023,17,17,"2023-04-29","10:50:00","2023-04-30","16:50:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 30:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_TGR-LAO_10","Ternier-Laon","< >","Fargniers-Garage - ITE ALB","Laon - Bât Voyageurs",2023,2023,28,29,"2023-07-13","22:45:00","2023-07-17","04:45:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 78:00, Continu, LU,JE,VE,SA,DI","2022-01-07","unclassified","1, 4, 5, 6, 7","publication"]
["SNCF-R","3D_TGR-LAO_11","Ternier-Laon","< >","Fargniers-Garage - ITE ALB","Laon - Bât Voyageurs",2023,2023,32,33,"2023-08-11","22:20:00","2023-08-15","12:20:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 86:00, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication"]
["SNCF-R","3C_AYE1_002","Aulnoye(242000)","< >","Aulnoye-Aymeries - Poste 1","Aulnoye-Aymeries - Poste 3",2023,2023,32,33,"2023-08-12","23:30:00","2023-08-14","03:30:00","continuous","Miscellaneous","Cap, 10,4,6,8,B,C,D1,D3,DM,E,F,K,L2,L4,O,P,R,V1,V2, 28:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3D_RNG-BE_3","Rang-Boulogne","< >","Conchil-le-Temple","Boulogne-Ville - Bif d'Outreau",2023,2023,39,39,"2023-09-29","22:00:00","2023-10-01","18:00:00","continuous","Miscellaneous","Def, 3,4,V1,V2, 2V/2, 44:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_BE-MRX_3","Boulogne-Marquise","< >","Boulogne-Tintelleries","Marquise-Rinxent",2023,2023,8,9,"2023-02-24","23:00:00","2023-02-27","03:00:00","continuous","Miscellaneous","Def, V1,V2, , 52:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3C_MRX-CS_3","Marquise-Calais","<","Wimille-Wimereux","Le Haut-Banc",2023,2023,8,9,"2023-02-24","23:00:00","2023-02-27","03:00:00","continuous","Miscellaneous","Cap, 4, 52:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3C_MRX-CS_4","Marquise-Calais","<","Wimille-Wimereux","Le Haut-Banc",2023,2023,9,13,"2023-03-04","17:55:00","2023-04-02","15:55:00","periodical","Miscellaneous","Cap, 4, 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_MRX-CS_5","Marquise-Calais","<","Wimille-Wimereux","Le Haut-Banc",2023,2023,11,11,"2023-03-18","20:20:00","2023-03-19","10:20:00","periodical","Miscellaneous","Cap, 4, 14:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_MRX-CS_7","Marquise-Calais","<","Wimille-Wimereux","Le Haut-Banc",2023,2023,14,15,"2023-04-08","17:55:00","2023-04-16","15:55:00","periodical","Miscellaneous","Cap, 4, 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_MRX-CS_4","Marquise-Calais","< >","Wimille-Wimereux","Calais-Fréthun - C102/204",2023,2023,9,13,"2023-03-04","17:55:00","2023-04-02","15:55:00","periodical","Miscellaneous","Def, V1,V2, , 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_MRX-CS_5","Marquise-Calais","< >","Wimille-Wimereux","Calais-Fréthun - C102/205",2023,2023,11,11,"2023-03-18","20:20:00","2023-03-19","10:20:00","periodical","Miscellaneous","Def, V1,V2, , 14:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_MRX-CS_7","Marquise-Calais","< >","Wimille-Wimereux","Caffiers - Bât Voyageurs",2023,2023,14,15,"2023-04-08","17:55:00","2023-04-16","15:55:00","periodical","Miscellaneous","Def, V1,V2, , 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_CS_019","Calais","< >","Calais-Ville - Bât Voyageurs","Calais-Ville - Bât Voyageurs",2023,2023,43,44,"2023-10-28","04:00:00","2023-10-31","22:00:00","continuous","Miscellaneous","Cap, A,B,C,D,V1,V2, 90:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication"]
["SNCF-R","3D_SRO-ABB_2","StRoch-Abbeville","< >","St-Roch (Somme) - Bif et Poste 1","Abbeville",2023,2023,19,19,"2023-05-12","23:00:00","2023-05-14","23:00:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 48:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_ABB-RDF_3","Abbeville-Rang","< >","Abbeville","Rang-du-Fliers-Verton",2023,2023,20,20,"2023-05-17","23:30:00","2023-05-21","23:30:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 96:00, Continu, ME,JE,VE,SA,DI","2022-01-07","unclassified","3, 4, 5, 6, 7","publication"]
["SNCF-R","3C_AS_007","Amiens","< >","Amiens - Poste 1","Longueau - E/S Tergnier",2023,2023,21,21,"2023-05-27","23:00:00","2023-05-28","11:00:00","periodical","Miscellaneous","Cap, CIC,V1,V2, 12:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_LUA-AS_9","Longueau-Amiens","< >","Longueau - Bât Voyageurs","Amiens - Poste 1",2023,2023,21,21,"2023-05-27","23:00:00","2023-05-28","11:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 12:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_LUA-BFY_5","Longueau-BifAgnyExclue",">","Albert","Achiet",2023,2023,21,22,"2023-05-26","23:50:00","2023-05-30","03:50:00","continuous","Miscellaneous","Def, V1, 1V/2, 76:00, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication"]
["SNCF-R","3D_LUA-BFR_5","Longueau-Bif de l'arbre Robert exclue","<","Albert","Achiet",2023,2023,21,22,"2023-05-26","23:50:00","2023-05-30","03:50:00","continuous","Miscellaneous","Def, V2, 1V/2, 76:00, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication"]
["SNCF-R","3C_BE_004","Boulogne   ",">","Boulogne-Ville - Bât Voyageurs","Boulogne-Tintelleries",2023,2023,9,13,"2023-03-04","17:55:00","2023-04-02","17:55:00","periodical","Miscellaneous","Cap, V1, 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_BE_005","Boulogne   ",">","Boulogne-Ville - Bât Voyageurs","Boulogne-Tintelleries",2023,2023,11,11,"2023-03-18","20:20:00","2023-03-19","10:20:00","periodical","Miscellaneous","Cap, V1, 14:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_BE_007","Boulogne   ",">","Boulogne-Ville - Bât Voyageurs","Boulogne-Tintelleries",2023,2023,14,15,"2023-04-08","17:55:00","2023-04-16","15:55:00","periodical","Miscellaneous","Cap, V1, 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_LNS_001","Lens",">","Lens - Poste 3","Lens - Poste 4",2023,2023,29,29,"2023-07-17","08:00:00","2023-07-23","17:00:00","continuous","Miscellaneous","Cap, 5, 153:00, Continu, LU,MA,ME,JE,VE,SA,DI","2022-01-07","unclassified","1, 2, 3, 4, 5, 6, 7","publication"]
["SNCF-R","3C_LNS-HZK_2","Lens-Hazebrouck",">","Béthune - E/S Béthune","Béthune - Poste 2",2023,2023,17,19,"2023-04-29","13:10:00","2023-05-08","17:10:00","continuous","Miscellaneous","Cap, 3,5, 52:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3C_LNS-HZK_3","Lens-Hazebrouck",">","Béthune - E/S Béthune","Béthune - Poste 2",2023,2023,19,19,"2023-05-13","10:30:00","2023-05-14","16:30:00","continuous","Miscellaneous","Cap, 3,5, 30:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_LNS-HZK_2","Lens-Hazebrouck","< >","Noeudx-les-Mines","Fouquereuil - Bât Voyageurs",2023,2023,17,19,"2023-04-29","13:10:00","2023-05-08","17:10:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 52:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3D_LNS-HZK_3","Lens-Hazebrouck","< >","Noeudx-les-Mines","Fouquereuil - Bât Voyageurs",2023,2023,19,19,"2023-05-13","10:30:00","2023-05-14","16:30:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 30:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_HZK_002","Hazebrouck","< >","Hazebrouck - Bif Haute Loge","Ebblighem",2023,2023,16,17,"2023-04-22","06:30:00","2023-04-30","12:30:00","periodical","Miscellaneous","Cap, V1,V2, 30:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_HZK_004","Hazebrouck",">","Hazebrouck - Bif Haute Loge","Ebblighem",2023,2023,22,22,"2023-06-03","00:30:00","2023-06-04","12:30:00","periodical","Miscellaneous","Cap, V1, 36:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_HZK_005","Hazebrouck","< >","Hazebrouck - Bif Haute Loge","Ebblighem",2023,2023,18,18,"2023-05-06","00:30:00","2023-05-07","12:30:00","periodical","Miscellaneous","Cap, V1,V2, 36:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_DO-OIC_6","Douai-Ostricourt","< >","Douai - Aig Km 218,5","Triangle d'Ostricourt - Bif Harponlieu",2023,2023,16,31,"2023-04-21","22:30:00","2023-08-06","22:30:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 48:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3C_DO_018","Douai   ","< >","Douai - Acc Marchandise","Pont-de-la-Deule",2023,2023,16,31,"2023-04-21","22:30:00","2023-08-06","22:30:00","continuous","Miscellaneous","Cap, 3,4,5,6,7,9,A,B,K,V1,V1,V2,V2, 48:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3C_SOM1_004","Somain(262000)","<","Somain - Aig Km 230,5","Somain - ITE EDF",2022,2022,50,51,"2022-12-17","05:20:00","2022-12-19","05:20:00","continuous","Miscellaneous","Cap, V2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3C_SOM1_005","Somain(262000)","<","Somain - Aig Km 230,5","Somain - ITE EDF",2023,2023,32,33,"2023-08-12","01:20:00","2023-08-16","05:20:00","continuous","Miscellaneous","Cap, V2, 100:00, Continu, LU,MA,ME,SA,DI","2022-01-07","unclassified","1, 2, 3, 6, 7","publication"]
["SNCF-R","3D_SOM-VS_2","Somain-Valenciennes","< >","Somain - Aig Km 230,5","Beuvrages",2023,2023,50,51,"2022-12-17","05:20:00","2022-12-19","05:20:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3D_SOM-VS_3","Somain-Valenciennes","< >","Somain - Aig Km 230,5","Beuvrages",2023,2023,32,33,"2023-08-12","01:20:00","2023-08-16","05:20:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 100:00, Continu, LU,MA,ME,SA,DI","2022-01-07","unclassified","1, 2, 3, 6, 7","publication"]
["SNCF-R","3C_VS_002","Valenciennes","< >","Raismes (Nord)","Valenciennes - Poste 1",2022,2022,50,51,"2022-12-17","05:20:00","2022-12-19","05:20:00","continuous","Miscellaneous","Cap, UNIQUE,V1,V2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3C_VS_003","Valenciennes","< >","Raismes (Nord)","Valenciennes - Poste 1",2023,2023,32,33,"2023-08-12","01:20:00","2023-08-16","05:20:00","continuous","Miscellaneous","Cap, UNIQUE,V1,V2, 100:00, Continu, LU,MA,ME,SA,DI","2022-01-07","unclassified","1, 2, 3, 6, 7","publication"]
["SNCF-R","3D_LZP_002","Lille-Lambersart","< >","Lille-Flandres - Jonct Lion d'Or","Lambersart - Bif 4 Maisons",2023,2023,9,9,"2023-03-04","15:20:00","2023-03-05","15:21:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_LZP_003","Lille-Lambersart","< >","Lille-Flandres - Jonct Lion d'Or","Lambersart - Bif 4 Maisons",2023,2023,28,29,"2023-07-14","05:00:00","2023-07-17","05:00:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 72:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3D_LZP_004","Lille-Lambersart","< >","Lille-Flandres - Jonct Lion d'Or","Lambersart - Bif 4 Maisons",2023,2023,32,33,"2023-08-12","14:20:00","2023-08-15","14:20:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 72:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication"]
["SNCF-R","3C_AYE_002","Aulnoye(267000)","< >","Aulnoye-Aymeries - Poste 1","Aulnoye-Aymeries - Bif de Leval",2023,2023,32,33,"2023-08-12","23:30:00","2023-08-14","03:30:00","continuous","Miscellaneous","Cap, V1,V1,V2,V2, 28:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3D_AYE-HI_2","Aulnoye-Hirson","< >","Leval","Fourmies",2023,2023,13,14,"2023-04-01","06:30:00","2023-04-03","06:30:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3D_AYE-HI_3","Aulnoye-Hirson","< >","Leval","Hirson-Écoles",2023,2023,14,15,"2023-04-08","06:30:00","2023-04-11","12:30:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 78:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication"]
["SNCF-R","3D_AYE-HI_4","Aulnoye-Hirson","< >","Leval","Hirson-Écoles",2023,2023,17,22,"2023-04-29","06:30:00","2023-05-30","06:30:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 72:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication"]
["SNCF-R","3D_AYE-HI_6","Aulnoye-Hirson","< >","Leval","Fourmies",2023,2023,32,33,"2023-08-12","06:30:00","2023-08-18","06:30:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 150:00, Continu, LU,MA,ME,JE,VE,SA,DI","2022-01-07","unclassified","1, 2, 3, 4, 5, 6, 7","publication"]
["SNCF-R","3D_AYE-HI_7","Aulnoye-Hirson","< >","Leval","Fourmies",2023,2023,32,33,"2023-08-12","19:00:00","2023-08-14","19:00:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication"]
["SNCF-R","3D_SED-LGN_2","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,31,31,"2023-08-04","20:25:00","2023-08-06","18:20:00","continuous","Miscellaneous","Def, V1,V2, , 45:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_SED-LGN_3","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,32,33,"2023-08-11","20:25:00","2023-08-15","18:20:00","continuous","Miscellaneous","Def, V1,V2, , 93:55, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication"]
["SNCF-R","3D_SED-LGN_5","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,31,31,"2023-08-04","20:25:00","2023-08-06","18:20:00","continuous","Miscellaneous","Def, V1,V2, , 45:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_SED-LGN_6","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,32,33,"2023-08-11","20:25:00","2023-08-15","18:20:00","continuous","Miscellaneous","Def, V1,V2, , 93:55, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication"]
["SNCF-R","3D_SED-LGN_8","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,31,31,"2023-08-04","20:25:00","2023-08-06","18:20:00","continuous","Miscellaneous","Def, V1,V2, , 45:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_SED-LGN_9","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,32,33,"2023-08-11","20:25:00","2023-08-15","18:20:00","continuous","Miscellaneous","Def, V1,V2, , 93:55, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication"]
["SNCF-R","3D_SED-LGN_11","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,31,31,"2023-08-04","20:25:00","2023-08-06","18:20:00","continuous","Miscellaneous","Def, V1,V2, , 45:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_SED-LGN_12","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,32,33,"2023-08-11","20:25:00","2023-08-15","18:20:00","continuous","Miscellaneous","Def, V1,V2, , 93:55, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication"]
["SNCF-R","3C_EPR_010","Epernay","< >","Épernay - Bât Voyageurs","Épernay - Bif L1/22 5",2023,2023,10,15,"2023-03-10","23:30:00","2023-04-16","11:30:00","continuous","Miscellaneous","Cap, 1B-2B,V1, 36:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_CM-BIM_008","Chalons-Blesme Haussignemont","< >","Vitry-le-François - Bât Voyageurs","Blesme-Haussignemont - Bât Voyageurs",2023,2023,15,15,"2023-04-14","23:35:00","2023-04-16","11:30:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 35:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3C_BIM1_005","Blesme Haussignemont(070000)","< >","Vitry-le-François - Aig Est-V Bis","Pargny-sur-Saulx",2023,2023,15,15,"2023-04-14","23:35:00","2023-04-16","11:30:00","continuous","Miscellaneous","Cap, V1,V2, 35:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3C_BIM1_007","Blesme Haussignemont(070000)","< >","Vitry-le-François - Aig Est-V Bis","Pargny-sur-Saulx",2023,2023,15,15,"2023-04-14","23:35:00","2023-04-16","11:30:00","continuous","Miscellaneous","Cap, V1,V2, 35:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_BIM-BLD_2","Blesme Haussignemont-Bar le Duc","< >","Revigny - Aig Km 235,8","Revigny - Aig Km 239,3",2023,2023,18,19,"2023-05-07","09:00:00","2023-05-08","10:30:00","continuous","Miscellaneous","Def, 2BIS,V1, 2V/4, 25:30, Continu, LU,DI","2022-01-07","unclassified","1, 7","publication"]
["SNCF-R","3D_BIM-BLD_018","Blesme Haussignemont-Bar le Duc","<","Vitry-le-François - Aig Est-V Bis","Blesme-Haussignemont - Aiguille L1/L10",2023,2023,15,15,"2023-04-14","23:35:00","2023-04-16","11:30:00","continuous","Miscellaneous","Def, V2, 1V/2, 35:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_BIM-BLD_020","Blesme Haussignemont-Bar le Duc","<","Vitry-le-François - Aig Est-V Bis","Blesme-Haussignemont - Aiguille L1/L10",2023,2023,15,15,"2023-04-14","23:35:00","2023-04-16","11:30:00","continuous","Miscellaneous","Def, V2, 1V/2, 35:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3C_BLD_004","Bar le Duc",">","Bar-le-Duc - Bât Voyageurs","Nançois-Tronville - Aig Km 263,4",2023,2023,7,7,"2023-02-18","16:00:00","2023-02-19","16:01:00","continuous","Miscellaneous","Cap, 1BIS,V1, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_BLD-LER_4","Bar le Duc-Lerouville",">","Bar-le-Duc - Bât Voyageurs","Nançois-Tronville - Aig Km 263,4",2023,2023,7,7,"2023-02-18","16:00:00","2023-02-19","16:01:00","continuous","Miscellaneous","Def, V1, 2V/4, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_EPR-RE_1","Epernay-Reims","< >","Germaine - Sortie Paire","Germaine - Sortie Impaire",2023,2023,23,24,"2023-06-05","09:25:00","2023-06-14","15:59:00","continuous","Miscellaneous","Def, UNIQUE, 1V/1, 54:34, Continu, LU,MA,ME","2022-01-07","unclassified","1, 2, 3","publication"]
["SNCF-R","3D_EPR-RE_15","Epernay-Reims","< >","Germaine - Sortie Paire","Germaine - Sortie Impaire",2023,2023,22,22,"2023-05-30","09:25:00","2023-05-31","15:59:00","continuous","Miscellaneous","Def, UNIQUE, 1V/1, 30:34, Continu, MA,ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3C_LEW-FFT_5","LilleEurope-Calais","< >","Lille-Europe - Poste 41","Lambersart - Rac de Lille",2023,2023,28,28,"2023-07-14","23:30:00","2023-07-15","05:00:00","continuous","Miscellaneous","Cap, 43,44,45,46, 05:30, Passe-minuit, VE/SA","2022-01-07","unclassified","5, 6","publication"]
["SNCF-R","3D_CHM-CY_003","Chaumont-Culmont","< >","Grandpuits - Poste 4","Vesoul - Poste C",2023,2023,16,16,"2023-04-21","23:30:00","2023-04-23","05:30:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 30:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_CHM-CY_004","Chaumont-Culmont","< >","Grandpuits - Poste 4","Vesoul - Poste C",2023,2023,17,18,"2023-04-28","21:40:00","2023-05-01","17:00:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 67:20, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3D_CHM-CY_005","Chaumont-Culmont","< >","Grandpuits - Poste 4","Vesoul - Poste C",2023,2023,20,20,"2023-05-18","11:40:00","2023-05-21","07:28:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 67:48, Continu, JE,VE,SA,DI","2022-01-07","unclassified","4, 5, 6, 7","publication"]
["SNCF-R","3C_SDZ_001","StDizier","< >","Villiers-en-Lieu","St-Dizier - ITE Tréfilunion",2023,2023,15,16,"2023-04-14","22:00:00","2023-04-23","20:55:00","continuous","Miscellaneous","Cap, 1B-2B,1T-2T,V1,V2, 46:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3C_SDZ_009","StDizier","< >","Villiers-en-Lieu","St-Dizier - ITE Tréfilunion",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","20:55:00","continuous","Miscellaneous","Cap, 1B-2B,1T-2T,V1,V2, 70:55, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication"]
["SNCF-R","3D_RDG-SNE20","Reding-Saverne","<","Arzviller - IPCS","Lutzelbourg - IPCS",2022,2022,50,50,"2022-12-11","00:01:00","2022-12-12","05:30:00","continuous","Miscellaneous","Def, V2, 1V/2, 29:29, Continu, LU,DI","2022-01-07","unclassified","1, 7","publication"]
["SNCF-R","3C_VHM-HN_7","Vendenheim-Hausbergen","< >","Hausbergen-Triage - Aiguille 496,9","Hausbergen-Triage - Relais Pairs",2023,2023,9,9,"2023-03-04","13:00:00","2023-03-05","09:00:00","periodical","Miscellaneous","Cap, 1M,2M, 20:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_PMO_002","Pagny sur Moselle","< >","Raccordement Pagny-Vandières - RAC côté Paris","Pagny-sur-Moselle - Bât Voyageurs",2023,2023,32,33,"2023-08-12","12:30:00","2023-08-15","12:30:00","continuous","Miscellaneous","Cap, R2,V1,V2, 72:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication"]
["SNCF-R","3D_THL-AP_008","Thionville-Apach","< >","Thionville - Poste 3","Apach (Moselle) - Frontière Fr-Al",2023,2023,47,48,"2023-11-25","04:00:00","2023-11-27","05:00:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 49:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication"]
["SNCF-R","3D_THL-ZOU17","Thionville-Zoufftgen","< >","Thionville - Poste 2","Zoufftgen (IE) - Frontière Fr-Lu",2023,2023,47,48,"2023-11-25","04:00:00","2023-11-27","05:00:00","continuous","Miscellaneous","Def, V1,V2, 2V/2, 49:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication"]
["SNCF-R","3D_HGD-UCK_8","Hagondange-Uckange","< >","Hagondange - Bât Voyageurs","Uckange - Ano Km 181,3",2023,2023,47,48,"2023-11-25","04:00:00","2023-11-27","05:00:00","continuous","Miscellaneous","Def, V1,V1BIS,V2,V2BIS, 4V/4, 49:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication"]
["SNCF-R","3D_UCK-THL14","Uckange-Thionville","< >","Uckange - Poste 2","Ébange - Jonction Nord",2023,2023,47,48,"2023-11-25","04:00:00","2023-11-27","05:00:00","continuous","Miscellaneous","Def, V1,V1BIS,V2,V2BIS, 4V/4, 49:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication"]
["SNCF-R","3D_CY-NCH_007","Culmont-NeufChateau","< >","Bourmont","Neufchâteau - CV 254",2023,2023,16,17,"2023-04-22","06:00:00","2023-04-24","06:00:00","continuous","Miscellaneous","Def, 1BIS,2BIS,V2, 3V/4, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication"]
["SNCF-R","3D_NCH-TL_005","NeufChateau-Toul","<","Neufchâteau - Bât Voyageurs","Soulosse",2023,2023,16,17,"2023-04-22","06:00:00","2023-04-24","06:00:00","continuous","Miscellaneous","Def, V2, 1V/2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication"]
["SNCF-R","3D_LE-TG_003","Lille-Tourcoing","< >","La Madeleine (Nord) - PI","Tourcoing - XB",2023,2023,13,13,"2023-03-29","09:00:00","2023-03-31","14:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 05:30, Jour, ME,JE,VE","2022-01-07","unclassified","3, 4, 5","publication"]
["SNCF-R","3F_LE-TG_001","Lille-Tourcoing",">","La Madeleine (Nord) - PI","Tourcoing - XB",2023,2023,10,49,"2023-03-06","09:25:00","2023-12-08","13:25:00","periodical","Miscellaneous","Gen, V1, 1V/2, 04:00, Jour, LU,MA,ME,JE,VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3F_LE-TG_002","Lille-Tourcoing","<","La Madeleine (Nord) - PI","Tourcoing - XB",2023,2023,10,49,"2023-03-06","09:40:00","2023-12-08","13:40:00","periodical","Miscellaneous","Gen, V2, 1V/2, 04:00, Jour, LU,MA,ME,JE,VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_001","Reding-Saverne","< >","Réding - FP","Hommarting - IPCS",2023,2023,21,24,"2023-05-22","22:00:00","2023-06-16","04:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_002","Reding-Saverne","< >","Réding - FP","Hommarting - IPCS",2023,2023,21,21,"2023-05-27","21:05:00","2023-05-28","06:05:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 09:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RDG-SNE_003","Reding-Saverne","< >","Réding - FP","Hommarting - IPCS",2023,2023,22,22,"2023-05-29","22:00:00","2023-05-30","05:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 07:00, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3D_RDG-SNE_004","Reding-Saverne","< >","Stambach ","Saverne - AE",2023,2023,16,16,"2023-04-17","23:30:00","2023-04-20","04:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_005","Reding-Saverne","< >","Stambach ","Saverne - AE",2023,2023,15,15,"2023-04-15","22:50:00","2023-04-16","04:50:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 06:00, Passe-minuit, SA/DI,DI/LU","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RDG-SNE_006","Reding-Saverne","<","Stambach ","Saverne - AE",2023,2023,16,16,"2023-04-22","22:00:00","2023-04-23","04:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, SA/DI,DI/LU","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RDG-SNE_007","Reding-Saverne","<","Stambach ","Saverne - AE",2023,2023,17,17,"2023-04-24","23:30:00","2023-04-27","04:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_008","Reding-Saverne","< >","Réding - AE","Saverne  ",2023,2023,21,23,"2023-05-22","23:30:00","2023-06-09","03:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_009","Reding-Saverne","< >","Arzviller - IPCS","Lutzelbourg - IPCS",2023,2023,27,30,"2023-07-03","22:50:00","2023-07-28","04:50:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_010","Reding-Saverne","< >","Arzviller - IPCS","Lutzelbourg - IPCS",2023,2023,27,28,"2023-07-08","21:20:00","2023-07-15","06:20:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 09:00, Passe-minuit, SA/DI","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_011","Reding-Saverne",">","Réding - AE","Saverne  ",2023,2023,34,41,"2023-08-21","22:50:00","2023-10-13","04:50:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_012","Reding-Saverne","<","Réding - AE","Saverne  ",2023,2023,34,41,"2023-08-21","23:30:00","2023-10-13","04:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_013","Reding-Saverne","<","Réding - AE","Saverne  ",2023,2023,42,49,"2023-10-16","22:50:00","2023-12-08","04:50:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_014","Reding-Saverne",">","Réding - AE","Saverne  ",2023,2023,42,49,"2023-10-16","23:30:00","2023-12-08","04:00:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_015","Reding-Saverne","< >","Réding - FP","Hommarting - IPCS",2023,2023,21,22,"2023-05-28","20:30:00","2023-05-29","05:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 09:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RDG-SNE_016","Reding-Saverne","< >","Arzviller - IPCS","Lutzelbourg - IPCS",2023,2023,27,28,"2023-07-09","20:30:00","2023-07-16","05:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 09:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RDG-SNE_017","Reding-Saverne","< >","Réding - AE","Saverne  ",2023,2023,7,19,"2023-02-13","23:30:00","2023-05-12","04:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_018","Reding-Saverne",">","Arzviller - IPCS","Lutzelbourg - IPCS",2023,2023,26,31,"2023-06-26","22:50:00","2023-08-04","04:50:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_019","Reding-Saverne","<","Arzviller - IPCS","Lutzelbourg - IPCS",2023,2023,26,31,"2023-06-26","23:30:00","2023-08-04","04:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_021","Reding-Saverne","< >","Arzviller - Bât Voyageurs","Stambach",2023,2023,12,12,"2023-03-22","23:30:00","2023-03-23","04:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Passe-minuit, ME/JE,JE/VE","2022-01-07","unclassified","3, 4","publication"]
["SNCF-R","3D_RDG-SNE_022","Reding-Saverne",">","Arzviller - IPCS","Lutzelbourg - IPCS",2022,2022,50,50,"2022-12-11","21:50:00","2022-12-12","05:45:00","periodical","Miscellaneous","Def, V1, 1V/2, 07:55, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RDG-SNE_023","Reding-Saverne","<","Arzviller - IPCS","Lutzelbourg - IPCS",2022,2022,50,50,"2022-12-12","21:50:00","2022-12-14","05:50:00","periodical","Miscellaneous","Def, V2, 1V/2, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_024","Reding-Saverne",">","Arzviller - IPCS","Lutzelbourg - IPCS",2022,2022,50,50,"2022-12-12","23:00:00","2022-12-14","05:00:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_025","Reding-Saverne","< >","Arzviller - IPCS","Lutzelbourg - IPCS",2022,2022,50,50,"2022-12-17","21:55:00","2022-12-18","05:40:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 07:45, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RDG-SNE_026","Reding-Saverne","< >","Arzviller - IPCS","Lutzelbourg - IPCS",2022,2022,50,51,"2022-12-18","21:50:00","2022-12-19","05:10:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 07:20, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RDG-SNE_027","Reding-Saverne","<","Arzviller - IPCS","Lutzelbourg - IPCS",2022,2022,51,51,"2022-12-19","22:35:00","2022-12-21","04:35:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_028","Reding-Saverne",">","Arzviller - IPCS","Lutzelbourg - IPCS",2022,2022,51,51,"2022-12-19","23:40:00","2022-12-21","03:40:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:00, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_029","Reding-Saverne","<","Réding - AE","Saverne  ",2022,2022,50,50,"2022-12-17","21:40:00","2022-12-18","05:05:00","periodical","Miscellaneous","Def, V2, 1V/2, 07:25, Passe-minuit, SA/DI,DI/LU","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RDG-SNE_030","Reding-Saverne","< >","Réding - AE","Saverne  ",2022,2022,50,50,"2022-12-11","21:46:00","2022-12-12","05:05:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 07:19, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RDG-SNE_031","Reding-Saverne","<","Réding - AE","Saverne  ",2022,2022,50,50,"2022-12-12","21:50:00","2022-12-14","05:50:00","periodical","Miscellaneous","Def, V2, 1V/2, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_032","Reding-Saverne",">","Réding - AE","Saverne  ",2022,2022,50,50,"2022-12-12","23:00:00","2022-12-14","05:00:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_RDG-SNE_033","Reding-Saverne","< >","Réding - AE","Saverne  ",2022,2022,50,50,"2022-12-15","23:30:00","2022-12-16","04:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Passe-minuit, JE/VE,VE/SA","2022-01-07","unclassified","4, 5","publication"]
["SNCF-R","3D_RDG-SNE_034","Reding-Saverne",">","Réding - AE","Saverne  ",2022,2022,50,50,"2022-12-17","23:15:00","2022-12-18","05:15:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:00, Passe-minuit, SA/DI,DI/LU","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RDG-SNE_035","Reding-Saverne","<","Réding - AE","Saverne  ",2022,2022,50,50,"2022-12-11","00:01:00","2022-12-11","04:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 03:59, Nuit non passe-minuit, DI","2022-01-07","unclassified",7,"publication"]
["SNCF-R","3F_RDG-SNE_001","Reding-Saverne","< >","Réding - FP","Saverne - AE",2023,2023,10,39,"2023-03-06","22:57:00","2023-09-29","04:45:00","periodical","Miscellaneous","Gen, V1,V2, 1V/2, 05:48, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_SNE_001","Saverne","< >","Stambach ","Saverne - AE",2023,2023,15,15,"2023-04-15","22:50:00","2023-04-16","04:50:00","periodical","Miscellaneous","Cap, 1B-2B, 06:00, Passe-minuit, SA/DI,DI/LU","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_SNE_002","Saverne","< >","Stambach ","Saverne - AE",2023,2023,16,16,"2023-04-17","23:30:00","2023-04-20","04:00:00","periodical","Miscellaneous","Cap, 1B-2B, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_SNE_003","Saverne","< >","Stambach ","Saverne - AE",2023,2023,16,16,"2023-04-22","22:00:00","2023-04-23","04:00:00","periodical","Miscellaneous","Cap, 1B-2B,4, 06:00, Passe-minuit, SA/DI,DI/LU","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_SNE_004","Saverne","< >","Stambach ","Saverne - AE",2023,2023,17,17,"2023-04-24","23:30:00","2023-04-27","04:00:00","periodical","Miscellaneous","Cap, 1B-2B,4, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_SNE_005","Saverne","< >","Stambach ","Saverne - AE",2023,2023,16,16,"2023-04-17","10:30:00","2023-04-21","15:00:00","periodical","Miscellaneous","Cap, 1B-2B, 04:30, Jour, LU,MA,ME,JE,VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_001","Saverne-Vendenheim",">","Saverne - AE","Vendenheim",2023,2023,26,32,"2023-06-26","22:10:00","2023-08-09","05:10:00","periodical","Miscellaneous","Def, V1, 1V/2, 07:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_002","Saverne-Vendenheim","<","Saverne - AE","Vendenheim",2023,2023,26,32,"2023-06-26","23:00:00","2023-08-09","03:45:00","periodical","Miscellaneous","Def, V2, 1V/2, 04:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_003","Saverne-Vendenheim","<","Saverne - AE","Vendenheim",2023,2023,32,38,"2023-08-10","22:10:00","2023-09-22","05:10:00","periodical","Miscellaneous","Def, V2, 1V/2, 07:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_004","Saverne-Vendenheim",">","Saverne - AE","Vendenheim",2023,2023,32,38,"2023-08-10","23:00:00","2023-09-22","03:45:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_005","Saverne-Vendenheim","<","Saverne - AE","Vendenheim",2023,2023,27,30,"2023-07-03","22:40:00","2023-07-28","04:30:00","periodical","Miscellaneous","Def, V2, 1V/2, 05:50, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_006","Saverne-Vendenheim","<","Schwindratzheim","Brumath - Bât Voyageurs",2023,2023,26,26,"2023-06-30","23:30:00","2023-07-01","04:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 04:30, Passe-minuit, VE/SA","2022-01-07","unclassified","5, 6","publication"]
["SNCF-R","3D_SNE-VHM_007","Saverne-Vendenheim","<","Schwindratzheim","Brumath - Bât Voyageurs",2023,2023,27,27,"2023-07-03","23:00:00","2023-07-06","05:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_008","Saverne-Vendenheim","<","Schwindratzheim","Brumath - Bât Voyageurs",2023,2023,26,29,"2023-07-01","22:55:00","2023-07-22","06:55:00","periodical","Miscellaneous","Def, V2, 1V/2, 08:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_SNE-VHM_009","Saverne-Vendenheim","<","Schwindratzheim","Brumath - Bât Voyageurs",2023,2023,26,29,"2023-07-02","21:15:00","2023-07-23","05:15:00","periodical","Miscellaneous","Def, V2, 1V/2, 08:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_SNE-VHM_010","Saverne-Vendenheim","<","Schwindratzheim","Brumath - Bât Voyageurs",2023,2023,35,35,"2023-09-01","23:00:00","2023-09-02","05:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, VE/SA,SA/DI","2022-01-07","unclassified","5, 6, 7","publication"]
["SNCF-R","3D_SNE-VHM_011","Saverne-Vendenheim",">","Schwindratzheim","Brumath - Bât Voyageurs",2023,2023,23,25,"2023-06-05","23:00:00","2023-06-23","03:30:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_012","Saverne-Vendenheim","<","Mommenheim - AE","Vendenheim",2023,2023,23,25,"2023-06-05","22:15:00","2023-06-23","04:15:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_013","Saverne-Vendenheim","< >","Mommenheim ","Vendenheim",2023,2023,23,23,"2023-06-05","23:00:00","2023-06-08","03:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_015","Saverne-Vendenheim","< >","Mommenheim - AE","Vendenheim",2023,2023,12,12,"2023-03-20","23:30:00","2023-03-21","04:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3D_SNE-VHM_016","Saverne-Vendenheim","< >","Saverne - AE","Mommenheim - AE",2023,2023,12,12,"2023-03-21","23:30:00","2023-03-22","04:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Passe-minuit, MA/ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3D_SNE-VHM_017","Saverne-Vendenheim",">","Mommenheim - AE","Vendenheim",2023,2023,39,41,"2023-09-25","23:30:00","2023-10-13","04:00:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_018","Saverne-Vendenheim","<","Mommenheim - AE","Vendenheim",2023,2023,39,41,"2023-09-25","22:45:00","2023-10-13","04:45:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_SNE-VHM_019","Saverne-Vendenheim","< >","Mommenheim ","Vendenheim",2023,2023,39,39,"2023-09-25","23:30:00","2023-09-28","04:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3F_SNE-VHM_001","Saverne-Vendenheim","< >","Saverne ","Vendenheim",2023,2023,7,43,"2023-02-13","23:12:00","2023-10-27","04:57:00","periodical","Miscellaneous","Gen, V1,V2, 1V/2, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM_001","Vendenheim ",">","Vendenheim","Mundolsheim",2023,2023,12,12,"2023-03-20","22:55:00","2023-03-23","04:40:00","periodical","Miscellaneous","Cap, V1,V2, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM_002","Vendenheim ","<","Vendenheim - JN","Mundolsheim",2023,2023,38,38,"2023-09-21","23:30:00","2023-09-22","04:30:00","periodical","Miscellaneous","Cap, V1,V2, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM_003","Vendenheim ","< >","Vendenheim","Vendenheim - JN",2023,2023,38,38,"2023-09-22","00:01:00","2023-09-22","05:00:00","periodical","Miscellaneous","Cap, V1,V2, 05:00, Passe-minuit, JE/VE","2022-01-07","unclassified","4, 5","publication"]
["SNCF-R","3C_VHM_004","Vendenheim ","<","Vendenheim","Mundolsheim",2023,2023,38,39,"2023-09-22","23:35:00","2023-09-25","04:35:00","periodical","Miscellaneous","Cap, V2, 04:59, Nuit non passe-minuit, VE","2022-01-07","unclassified",5,"publication"]
["SNCF-R","3C_VHM_005","Vendenheim ","< >","Vendenheim","Vendenheim - JN",2023,2023,38,38,"2023-09-23","00:01:00","2023-09-23","05:00:00","periodical","Miscellaneous","Cap, V1,V2, 05:00, Passe-minuit, LU/MA,VE/SA","2022-01-07","unclassified","1, 2, 5, 6","publication"]
["SNCF-R","3C_VHM_006","Vendenheim ","< >","Vendenheim","Mundolsheim",2023,2023,12,12,"2023-03-24","23:40:00","2023-03-25","04:40:00","periodical","Miscellaneous","Cap, V1, 04:59, Nuit non passe-minuit, SA","2022-01-07","unclassified",6,"publication"]
["SNCF-R","3C_VHM_016","Vendenheim ","< >","Stephansfeld","Mundolsheim",2023,2023,35,35,"2023-08-28","23:00:00","2023-08-29","03:30:00","periodical","Miscellaneous","Cap, V1,V2, 05:00, Passe-minuit, VE/SA","2022-01-07","unclassified","5, 6","publication"]
["SNCF-R","3C_VHM_017","Vendenheim ","< >","Stephansfeld","Mundolsheim",2023,2023,35,35,"2023-08-31","23:00:00","2023-09-01","03:30:00","periodical","Miscellaneous","Cap, V1, 04:30, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3C_VHM_018","Vendenheim ","< >","Stephansfeld","Mundolsheim",2023,2023,35,35,"2023-08-29","23:00:00","2023-08-30","03:30:00","periodical","Miscellaneous","Cap, V2, 04:30, Passe-minuit, JE/VE","2022-01-07","unclassified","4, 5","publication"]
["SNCF-R","3C_VHM-HN_001","Vendenheim-Hausbergen",">","Vendenheim","Vendenheim - JN",2023,2023,39,39,"2023-09-26","00:01:00","2023-09-26","05:00:00","periodical","Miscellaneous","Cap, V1BIS, 04:59, Nuit non passe-minuit, MA","2022-01-07","unclassified",2,"publication"]
["SNCF-R","3C_VHM-HN_002","Vendenheim-Hausbergen","<","Hausbergen-Triage - A5","Hausbergen-Triage - PU",2023,2023,3,3,"2023-01-16","10:00:00","2023-01-18","15:00:00","periodical","Miscellaneous","Cap, 2BIS, 05:00, Jour, LU,MA,ME","2022-01-07","unclassified","1, 2, 3","publication"]
["SNCF-R","3C_VHM-HN_003","Vendenheim-Hausbergen","< >","Hausbergen-Triage - A3","Hausbergen-Triage - RP",2023,2023,6,6,"2023-02-06","10:00:00","2023-02-10","15:00:00","periodical","Miscellaneous","Cap, 1M,2M, 05:00, Jour, LU,MA,ME,JE,VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM-HN_004","Vendenheim-Hausbergen","<","Hausbergen-Triage - A5","Hausbergen-Triage - PU",2023,2023,8,10,"2023-02-20","23:00:00","2023-03-10","04:00:00","periodical","Miscellaneous","Cap, 2BIS, 05:00, Passe-minuit, LU/MA,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM-HN_005","Vendenheim-Hausbergen","< >","Hausbergen-Triage - A3","Hausbergen-Triage - RP",2023,2023,8,10,"2023-02-20","21:00:00","2023-03-07","05:00:00","periodical","Miscellaneous","Cap, 1M,2M, 08:00, Passe-minuit, LU/MA,MA/ME","2022-01-07","unclassified","1, 2, 3","publication"]
["SNCF-R","3C_VHM-HN_006","Vendenheim-Hausbergen",">","Hausbergen-Triage - A1","Hausbergen-Triage - A3",2023,2023,9,9,"2023-02-27","08:00:00","2023-03-03","16:00:00","periodical","Miscellaneous","Cap, 1TER, 08:00, Jour, LU,MA,ME,JE,VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM-HN_008","Vendenheim-Hausbergen",">","Hausbergen-Triage - A3","Hausbergen-Triage - A5",2023,2023,9,9,"2023-03-04","13:30:00","2023-03-04","18:30:00","periodical","Miscellaneous","Cap, V1BIS, 05:00, Jour, SA","2022-01-07","unclassified",6,"publication"]
["SNCF-R","3C_VHM-HN_009","Vendenheim-Hausbergen","< >","Hausbergen-Triage - 21","Hausbergen-Triage - FD",2023,2023,10,10,"2023-03-06","21:00:00","2023-03-06","05:00:00","periodical","Miscellaneous","Cap, 1M,1TER,2M, 08:00, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3C_VHM-HN_010","Vendenheim-Hausbergen","< >","Hausbergen-Triage - 21","Hausbergen-Triage - FD",2023,2023,10,10,"2023-03-07","23:00:00","2023-03-09","04:00:00","periodical","Miscellaneous","Cap, 1M,1TER,2M, 05:00, Passe-minuit, MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM-HN_011","Vendenheim-Hausbergen","< >","Hausbergen-Triage - A5","Hausbergen-Triage - PU",2023,2023,10,10,"2023-03-07","21:00:00","2023-03-07","05:00:00","periodical","Miscellaneous","Cap, 1M,2BIS, 08:00, Passe-minuit, MA/ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3C_VHM-HN_012","Vendenheim-Hausbergen","< >","Hausbergen-Triage - A3","Hausbergen-Triage - PU",2023,2023,10,10,"2023-03-08","23:00:00","2023-03-10","04:00:00","periodical","Miscellaneous","Cap, 1M,2M, 05:00, Passe-minuit, ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","3, 4, 5, 6","publication"]
["SNCF-R","3C_VHM-HN_013","Vendenheim-Hausbergen",">","Hausbergen-Triage - FS","Strasbourg-Cronenbourg - AS",2023,2023,10,11,"2023-03-12","21:00:00","2023-03-13","05:00:00","periodical","Miscellaneous","Cap, 1M,V1BIS, 08:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_VHM-HN_014","Vendenheim-Hausbergen",">","Hausbergen-Triage - FS","Strasbourg-Cronenbourg - AS",2023,2023,11,18,"2023-03-13","23:00:00","2023-05-01","04:00:00","periodical","Miscellaneous","Cap, 1M,V1BIS, 05:00, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3C_VHM-HN_015","Vendenheim-Hausbergen",">","Hausbergen-Triage - A1","Hausbergen-Triage - A3",2023,2023,11,11,"2023-03-13","21:00:00","2023-03-16","05:00:00","periodical","Miscellaneous","Cap, 1TER, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM-HN_016","Vendenheim-Hausbergen","< >","Hausbergen-Triage - FD","Hausbergen-Triage - PU",2023,2023,12,12,"2023-03-20","21:00:00","2023-04-21","05:00:00","periodical","Miscellaneous","Cap, 1M,2BIS,2M, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM-HN_017","Vendenheim-Hausbergen","< >","Hausbergen-Triage - FF","Hausbergen-Triage - RP",2023,2023,12,16,"2023-03-23","21:00:00","2023-04-18","05:00:00","periodical","Miscellaneous","Cap, 1M,2M, 08:00, Passe-minuit, LU/MA,MA/ME,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM-HN_018","Vendenheim-Hausbergen","< >","Hausbergen-Triage - FD","Hausbergen-Triage - RP",2023,2023,13,14,"2023-03-29","21:00:00","2023-04-07","05:00:00","periodical","Miscellaneous","Cap, 1M,2M, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM-HN_019","Vendenheim-Hausbergen","<","Hausbergen-Triage - FD","Hausbergen-Triage - RP",2023,2023,17,17,"2023-04-25","23:00:00","2023-04-28","04:00:00","periodical","Miscellaneous","Cap, 1M,2M, 05:00, Passe-minuit, MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM-HN_020","Vendenheim-Hausbergen","< >","Hausbergen-Triage - FF","Hausbergen-Triage - PF",2023,2023,17,17,"2023-04-24","21:00:00","2023-04-25","05:00:00","periodical","Miscellaneous","Cap, 2M, 08:00, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3C_VHM-HN_021","Vendenheim-Hausbergen","< >","Hausbergen-Triage - A1","Hausbergen-Triage - PU",2023,2023,18,18,"2023-05-02","23:00:00","2023-05-05","04:00:00","periodical","Miscellaneous","Cap, 1M,1TER,2BIS,2M, 05:00, Passe-minuit, MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3C_VHM-HN_024","Vendenheim-Hausbergen",">","Vendenheim - JN","Strasbourg-Ville - QM",2023,2023,14,14,"2023-04-03","23:12:00","2023-04-04","05:12:00","periodical","Miscellaneous","Cap, V1, 06:00, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3C_VHM-HN_025","Vendenheim-Hausbergen","<","Vendenheim - JN","Strasbourg-Ville - QM",2023,2023,14,14,"2023-04-04","22:40:00","2023-04-05","04:40:00","periodical","Miscellaneous","Cap, V2, 06:00, Passe-minuit, MA/ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3C_VHM-HN_026","Vendenheim-Hausbergen","< >","Hausbergen-Triage - FN","Hausbergen-Triage - RI",2023,2023,14,14,"2023-04-05","23:12:00","2023-04-06","03:12:00","periodical","Miscellaneous","Cap, VD, 04:00, Passe-minuit, ME/JE","2022-01-07","unclassified","3, 4","publication"]
["SNCF-R","3C_VHM-HN_027","Vendenheim-Hausbergen","< >","Hausbergen-Triage - A3","Hausbergen-Triage - A5",2023,2023,8,8,"2023-02-25","08:00:00","2023-02-25","16:00:00","periodical","Miscellaneous","Cap, 1M,2M,V1BIS, 08:00, Jour, SA","2022-01-07","unclassified",6,"publication"]
["SNCF-R","3C_VHM-HN_028","Vendenheim-Hausbergen",">","Hausbergen-Triage - A1","Hausbergen-Triage - A3",2023,2023,8,8,"2023-02-26","08:00:00","2023-02-26","16:00:00","periodical","Miscellaneous","Cap, 1TER, 08:00, Jour, DI","2022-01-07","unclassified",7,"publication"]
["SNCF-R","3C_SG_001","Strasbourg","< >","Strasbourg-Koenigshoffen - RN","Strasbourg-Koenigshoffen - Poste 1",2023,2023,7,27,"2023-02-13","21:00:00","2023-07-04","02:00:00","periodical","Miscellaneous","Cap, 1S-2S,V1L,V2L, 05:00, Passe-minuit, LU/MA,MA/ME","2022-01-07","unclassified","1, 2, 3","publication"]
["SNCF-R","3C_SG_002","Strasbourg","< >","Strasbourg-Koenigshoffen - RS","Strasbourg-Koenigshoffen - Poste 1",2023,2023,7,27,"2023-02-13","21:00:00","2023-07-07","05:00:00","periodical","Miscellaneous","Cap, V1L,V2L, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_SG_003","Strasbourg","< >","Strasbourg-Koenigshoffen - RN","Strasbourg-Koenigshoffen - Poste 1",2023,2023,8,26,"2023-02-22","21:00:00","2023-06-30","05:00:00","periodical","Miscellaneous","Cap, 1S-2S,V1L,V2L, 08:00, Passe-minuit, ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","3, 4, 5, 6","publication"]
["SNCF-R","3C_SG_004","Strasbourg","< >","Strasbourg-Koenigshoffen - RS","Strasbourg-Koenigshoffen - Poste 1",2023,2023,7,7,"2023-02-15","21:00:00","2023-02-17","05:00:00","periodical","Miscellaneous","Cap, V1L,V1N,V1N,V1R,V2L,V2N,V2N,V2R, 08:00, Passe-minuit, ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","3, 4, 5, 6","publication"]
["SNCF-R","3C_SG_005","Strasbourg","< >","Strasbourg-Koenigshoffen - RC","Strasbourg-Koenigshoffen - Poste 1",2023,2023,8,26,"2023-02-23","21:00:00","2023-06-30","05:00:00","periodical","Miscellaneous","Cap, V1N,V1N,V1R,V2N,V2N,V2R, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_SG_008","Strasbourg",">","Strasbourg-Ville - J1","Strasbourg-Neudorf - LA",2023,2023,19,19,"2023-05-10","00:25:00","2023-05-10","04:25:00","periodical","Miscellaneous","Cap, V1, 04:00, Nuit non passe-minuit, ME","2022-01-07","unclassified",3,"publication"]
["SNCF-R","3C_SG_009","Strasbourg","<","Strasbourg-Ville - J1","Strasbourg-Neudorf - LA",2023,2023,19,19,"2023-05-11","00:25:00","2023-05-11","04:25:00","periodical","Miscellaneous","Cap, V2, 04:00, Nuit non passe-minuit, JE","2022-01-07","unclassified",4,"publication"]
["SNCF-R","3C_SG_010","Strasbourg",">","Graffenstaden - RC","Strasbourg-Neudorf - RG",2023,2023,14,14,"2023-04-06","21:00:00","2023-04-06","02:00:00","periodical","Miscellaneous","Cap, V1R, 05:00, Passe-minuit, JE/VE","2022-01-07","unclassified","4, 5","publication"]
["SNCF-R","3C_SG_011","Strasbourg","<","Graffenstaden - RC","Strasbourg-Neudorf - RG",2023,2023,14,14,"2023-04-07","21:00:00","2023-04-07","02:00:00","periodical","Miscellaneous","Cap, V2R, 05:00, Passe-minuit, VE/SA","2022-01-07","unclassified","5, 6","publication"]
["SNCF-R","3C_SG_012","Strasbourg","< >","Strasbourg-Neudorf - Bât Voyageurs","Strasbourg-Port-du-Rhin - JN",2022,2022,50,49,"2022-12-11","22:00:00","2022-12-16","06:00:00","periodical","Miscellaneous","Cap, 3, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_SG_013","Strasbourg","< >","Strasbourg-Ville - J1","Strasbourg-Neudorf - LA",2023,2023,36,49,"2023-09-04","22:40:00","2023-12-08","04:40:00","periodical","Miscellaneous","Cap, V1,V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_SG_014","Strasbourg",">","Graffenstaden - RC","Strasbourg-Neudorf - RG",2023,2023,19,19,"2023-05-09","23:30:00","2023-05-11","04:00:00","periodical","Miscellaneous","Cap, V1R, 04:30, Passe-minuit, MA/ME,ME/JE","2022-01-07","unclassified","2, 3, 4","publication"]
["SNCF-R","3C_SG_015","Strasbourg","<","Graffenstaden - RC","Strasbourg-Neudorf - RG",2023,2023,19,19,"2023-05-11","21:00:00","2023-05-13","00:30:00","periodical","Miscellaneous","Cap, V2R, 03:30, Passe-minuit, JE/VE,VE/SA","2022-01-07","unclassified","4, 5, 6","publication"]
["SNCF-R","3C_SG_016","Strasbourg","< > ","Graffenstaden - RC","Strasbourg-Koenigshoffen - Poste 1",2023,2023,12,17,"2023-03-20","21:00:00","2023-04-27","01:30:00","periodical","Miscellaneous","Cap, V1N,V1N,V1R,V2N,V2N,V2R, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_SG_017","Strasbourg",">","Strasbourg-Neudorf - RG","Strasbourg-Koenigshoffen - Poste 1",2023,2023,20,20,"2023-05-15","21:00:00","2023-05-16","01:30:00","periodical","Miscellaneous","Cap, V1N,V1N, 04:30, Passe-minuit, LU/MA,MA/ME","2022-01-07","unclassified","1, 2, 3","publication"]
["SNCF-R","3C_SG_018","Strasbourg","<","Strasbourg-Neudorf - RG","Strasbourg-Koenigshoffen - Poste 1",2023,2023,20,20,"2023-05-17","21:00:00","2023-05-18","01:30:00","periodical","Miscellaneous","Cap, V2N, 04:30, Passe-minuit, ME/JE,JE/VE","2022-01-07","unclassified","3, 4, 5","publication"]
["SNCF-R","3C_SG_019","Strasbourg",">","Strasbourg-Ville - J1","Strasbourg-Neudorf - LA",2023,2023,9,9,"2023-02-28","00:15:00","2023-03-03","06:05:00","periodical","Miscellaneous","Cap, V1, 05:45, Nuit non passe-minuit, MA,ME,JE,VE","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3C_SG_020","Strasbourg","<","Strasbourg-Ville - J1","Strasbourg-Neudorf - LA",2023,2023,10,10,"2023-03-06","22:55:00","2023-03-09","04:20:00","periodical","Miscellaneous","Cap, V2, 05:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_SG_021","Strasbourg","< > ","Strasbourg-Ville - J1","Strasbourg-Neudorf - LA",2023,2023,11,11,"2023-03-14","00:15:00","2023-03-17","04:20:00","periodical","Miscellaneous","Cap, V1,V2, 04:05, Nuit non passe-minuit, MA,ME,JE,VE","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3C_SG_022","Strasbourg","< > ","Strasbourg-Neudorf - RN","Strasbourg-Koenigshoffen - Poste 1",2023,2023,21,23,"2023-05-22","21:00:00","2023-06-09","05:00:00","periodical","Miscellaneous","Cap, 1S-2S,V1L,V2L, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_SG_023","Strasbourg","< > ","Strasbourg-Neudorf - RS","Strasbourg-Koenigshoffen - Poste 1",2023,2023,22,24,"2023-05-30","21:00:00","2023-06-16","05:00:00","periodical","Miscellaneous","Cap, V1L,V2L, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_HN2GRF_001","Hausbergen-Graffenstaden (via Koenigshoffen)","< > ","Graffenstaden - BF","Hausbergen-Triage - AC",2023,2023,7,27,"2023-02-13","21:00:00","2023-07-04","02:00:00","periodical","Miscellaneous","Cap, V1BIS,V2BIS, 05:00, Passe-minuit, LU/MA,MA/ME","2022-01-07","unclassified","1, 2, 3","publication"]
["SNCF-R","3C_HN2GRF_002","Hausbergen-Graffenstaden (via Koenigshoffen)","< > ","Graffenstaden - BF","Hausbergen-Triage - AC",2023,2023,8,26,"2023-02-22","21:00:00","2023-06-30","05:00:00","periodical","Miscellaneous","Cap, V1BIS,V2BIS, 08:00, Passe-minuit, ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","3, 4, 5, 6","publication"]
["SNCF-R","3C_HN2GRF_003","Hausbergen-Graffenstaden (via Koenigshoffen)",">","Graffenstaden - BF","Hausbergen-Triage - AC",2023,2023,18,18,"2023-05-02","23:30:00","2023-05-03","04:00:00","periodical","Miscellaneous","Cap, V1BIS, 04:30, Passe-minuit, MA/ME,ME/JE","2022-01-07","unclassified","2, 3, 4","publication"]
["SNCF-R","3C_HN2GRF_004","Hausbergen-Graffenstaden (via Koenigshoffen)","<","Graffenstaden - BF","Hausbergen-Triage - AC",2023,2023,18,18,"2023-05-04","22:20:00","2023-05-05","02:50:00","periodical","Miscellaneous","Cap, V2BIS, 04:30, Passe-minuit, JE/VE,VE/SA","2022-01-07","unclassified","4, 5, 6","publication"]
["SNCF-R","3C_HN2GRF_005","Hausbergen-Graffenstaden (via Koenigshoffen)","< > ","Graffenstaden - BF","Hausbergen-Triage - AC",2023,2023,21,23,"2023-05-22","21:00:00","2023-06-09","05:00:00","periodical","Miscellaneous","Cap, V1BIS,V2BIS, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_HN1GRF_001","Hausbergen-Graffenstaden (via Strasbourg)","< > ","Strasbourg-Ville - AM","Graffenstaden - BF",2023,2023,36,36,"2023-09-10","00:30:00","2023-09-10","04:30:00","periodical","Miscellaneous","Cap, V1,V2, 04:00, Nuit non passe-minuit, DI","2022-01-07","unclassified",7,"publication"]
["SNCF-R","3C_HN1GRF_002","Hausbergen-Graffenstaden (via Strasbourg)","< > ","Strasbourg-Ville - AM","Graffenstaden - BF",2023,2023,14,14,"2023-04-04","00:45:00","2023-04-05","05:00:00","periodical","Miscellaneous","Cap, V1,V2, 04:15, Nuit non passe-minuit, MA,ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3C_GRF_001","Graffenstaden","< > ","Strasbourg-Ville - AM","Geipolsheim",2023,2023,36,36,"2023-09-10","00:30:00","2023-09-10","04:30:00","periodical","Miscellaneous","Cap, V1,V2, 04:00, Nuit non passe-minuit, DI","2022-01-07","unclassified",7,"publication"]
["SNCF-R","3C_GRF_003","Graffenstaden",">","Strasbourg-Ville - AM","Graffenstaden - Bât Voyageurs",2023,2023,14,14,"2023-04-05","23:30:00","2023-04-06","04:30:00","periodical","Miscellaneous","Cap, V1, 05:00, Passe-minuit, ME/JE","2022-01-07","unclassified","3, 4","publication"]
["SNCF-R","3C_GRF_004","Graffenstaden","<","Strasbourg-Ville - AM","Geipolsheim",2023,2023,15,15,"2023-04-12","00:45:00","2023-04-12","05:00:00","periodical","Miscellaneous","Cap, V2, 04:15, Nuit non passe-minuit, ME","2022-01-07","unclassified",3,"publication"]
["SNCF-R","3C_GRF_005","Graffenstaden","< > ","Strasbourg-Ville - AM","Geipolsheim",2023,2023,15,15,"2023-04-13","00:45:00","2023-04-13","05:00:00","periodical","Miscellaneous","Cap, V1,V2, 04:15, Nuit non passe-minuit, JE","2022-01-07","unclassified",4,"publication"]
["SNCF-R","3C_GRF_006","Graffenstaden",">","Strasbourg-Ville - AM","Graffenstaden - Bât Voyageurs",2023,2023,18,19,"2023-05-02","23:30:00","2023-05-10","04:00:00","periodical","Miscellaneous","Cap, V1, 04:30, Passe-minuit, MA/ME,ME/JE","2022-01-07","unclassified","2, 3, 4","publication"]
["SNCF-R","3C_GRF_007","Graffenstaden",">","Strasbourg-Ville - AM","Graffenstaden - Bât Voyageurs",2023,2023,36,44,"2023-09-04","23:25:00","2023-11-02","05:02:00","periodical","Miscellaneous","Cap, V1, 05:37, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_GRF_008","Graffenstaden","<","Strasbourg-Ville - AM","Geipolsheim",2023,2023,22,28,"2023-05-29","23:23:00","2023-07-13","05:04:00","periodical","Miscellaneous","Cap, V2, 05:41, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_GRF-STT_001","Graffenstaden-Selestat","<","Fegersheim-Lipsheim - E4","Erstein - E2",2023,2023,16,16,"2023-04-17","23:00:00","2023-04-18","05:00:00","periodical","Miscellaneous","Cap, 2BIS, 06:00, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3C_GRF-STT_002","Graffenstaden-Selestat",">","Erstein - E1","Benfeld - E3",2023,2023,16,16,"2023-04-20","23:00:00","2023-04-21","05:00:00","periodical","Miscellaneous","Cap, 1TER, 06:00, Passe-minuit, JE/VE","2022-01-07","unclassified","4, 5","publication"]
["SNCF-R","3C_GRF-STT_003","Graffenstaden-Selestat","<","Benfeld - E3","Kogenheim - Bât Voyageurs",2023,2023,17,17,"2023-04-25","23:00:00","2023-04-26","05:00:00","periodical","Miscellaneous","Cap, 2BIS, 06:00, Passe-minuit, MA/ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3D_GRF-STT_001","Graffenstaden-Selestat","<","Kogenheim - Bât Voyageurs","St-Hyppolyte (Haut-Rhin)",2023,2023,4,5,"2023-01-23","23:55:00","2023-02-03","04:55:00","periodical","Miscellaneous","Def, V2, 1V/2, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_GRF-STT_002","Graffenstaden-Selestat",">","Kogenheim - Bât Voyageurs","St-Hyppolyte (Haut-Rhin)",2023,2023,6,7,"2023-02-06","23:55:00","2023-02-17","04:55:00","periodical","Miscellaneous","Def, V1, 1V/2, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_GRF-STT_003","Graffenstaden-Selestat","< >","Graffensatden - RC","St-Hyppolyte (Haut-Rhin)",2023,2023,36,36,"2023-09-10","00:30:00","2023-09-10","04:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:00, Nuit non passe-minuit, DI","2022-01-07","unclassified",7,"publication"]
["SNCF-R","3D_GRF-STT_004","Graffenstaden-Selestat",">","Benfeld - Bât Voyageurs","Sélestat",2022,2022,49,50,"2022-12-11","23:23:00","2022-12-16","05:04:00","periodical","Miscellaneous","Def, V1, 1V/2, 05:41, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_GRF-STT_005","Graffenstaden-Selestat","<","Ebersheim","Sélestat",2023,2023,9,9,"2023-03-01","21:50:00","2023-03-02","05:05:00","periodical","Miscellaneous","Def, V2, 1V/2, 07:15, Passe-minuit, ME/JE","2022-01-07","unclassified","3, 4","publication"]
["SNCF-R","3D_GRF-STT_006","Graffenstaden-Selestat","<","Ebersheim","Sélestat",2023,2023,9,9,"2023-03-02","00:15:00","2023-03-02","05:00:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:45, Nuit non passe-minuit, JE","2022-01-07","unclassified",4,"publication"]
["SNCF-R","3D_GRF-STT_007","Graffenstaden-Selestat","<","Limersheim ","Erstein - C2",2023,2023,9,9,"2023-03-02","22:05:00","2023-03-03","05:20:00","periodical","Miscellaneous","Def, V1, 1V/2, 07:15, Passe-minuit, JE/VE","2022-01-07","unclassified","4, 5","publication"]
["SNCF-R","3D_GRF-STT_008","Graffenstaden-Selestat","<","Limersheim ","Erstein - E2",2023,2023,9,9,"2023-03-03","00:30:00","2023-03-03","05:20:00","periodical","Miscellaneous","Def, V2, 1V/2, 04:50, Nuit non passe-minuit, VE","2022-01-07","unclassified",5,"publication"]
["SNCF-R","3D_GRF-STT_009","Graffenstaden-Selestat",">","Benfeld - Bât Voyageurs","Kogenheim - Bât Voyageurs",2023,2023,9,9,"2023-03-03","23:00:00","2023-03-04","05:30:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:30, Passe-minuit, VE/SA","2022-01-07","unclassified","5, 6","publication"]
["SNCF-R","3D_GRF-STT_010","Graffenstaden-Selestat","<","Benfeld - Bât Voyageurs","Kogenheim - Bât Voyageurs",2023,2023,9,9,"2023-03-04","00:25:00","2023-03-04","05:25:00","periodical","Miscellaneous","Def, V2, 1V/2, 05:00, Nuit non passe-minuit, SA","2022-01-07","unclassified",6,"publication"]
["SNCF-R","3D_GRF-STT_018","Graffenstaden-Selestat","< >","Kogenheim - Bât Voyageurs","Sélestat",2023,2023,15,15,"2023-04-12","00:20:00","2023-04-15","04:50:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, ME,JE,VE,SA","2022-01-07","unclassified","3, 4, 5, 6","publication"]
["SNCF-R","3D_GRF-STT_019","Graffenstaden-Selestat","< >","Graffensatden - RC","Kogenheim - EV",2023,2023,29,30,"2023-07-18","00:45:00","2023-07-28","04:55:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:10, Nuit non passe-minuit, MA,ME,JE,VE","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3D_GRF-STT_020","Graffenstaden-Selestat","< >","Ebersheim","St-Hyppolyte (Haut-Rhin)",2023,2023,19,19,"2023-05-11","00:20:00","2023-05-11","04:50:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, JE","2022-01-07","unclassified",4,"publication"]
["SNCF-R","3D_GRF-STT_021","Graffenstaden-Selestat",">","Graffensatden - RC","St-Hyppolyte (Haut-Rhin)",2023,2023,44,44,"2023-11-01","23:23:00","2023-11-02","05:04:00","periodical","Miscellaneous","Def, V1, 1V/2, 05:41, Passe-minuit, ME/JE","2022-01-07","unclassified","3, 4","publication"]
["SNCF-R","3F_GRF-STT_006","Graffenstaden-Selestat","< >","Graffensatden - RC","St-Hyppolyte (Haut-Rhin)",2023,2023,9,44,"2023-02-27","23:23:00","2023-11-02","05:04:00","periodical","Miscellaneous","Gen, V1,V2, 1V/2, 05:41, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_STT_001","Selestat","<","Ebersheim","St-Hyppolyte (Haut-Rhin)",2023,2023,4,5,"2023-01-23","23:55:00","2023-02-03","04:55:00","periodical","Miscellaneous","Cap, 2BIS,C, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_STT_002","Selestat",">","Ebersheim","St-Hyppolyte (Haut-Rhin)",2023,2023,6,7,"2023-02-06","23:55:00","2023-02-17","04:55:00","periodical","Miscellaneous","Cap, 1BIS, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_STT_003","Selestat","< >","Ebersheim","St-Hyppolyte (Haut-Rhin)",2023,2023,19,19,"2023-05-11","00:20:00","2023-05-11","04:50:00","periodical","Miscellaneous","Cap, 1BIS,2BIS,C, 04:30, Nuit non passe-minuit, JE","2022-01-07","unclassified",4,"publication"]
["SNCF-R","3D_STT-CMR_001","Selestat-Colmar","< >","Sélestat","Colmar - AN",2023,2023,22,26,"2023-05-30","00:20:00","2023-07-01","04:50:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, MA,ME,JE,VE,SA","2022-01-07","unclassified","2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_STT-CMR_002","Selestat-Colmar","< >","Sélestat","Colmar - AN",2023,2023,27,30,"2023-07-03","23:10:00","2023-07-28","05:10:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_STT-CMR_003","Selestat-Colmar","<","Sélestat","Ribeauvillé - C1",2023,2023,4,5,"2023-01-23","23:55:00","2023-02-03","04:55:00","periodical","Miscellaneous","Def, V2, 1V/2, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_STT-CMR_004","Selestat-Colmar",">","Sélestat","Ribeauvillé - 1B",2023,2023,6,7,"2023-02-06","23:55:00","2023-02-17","04:55:00","periodical","Miscellaneous","Def, V1, 1V/2, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_STT-CMR_005","Selestat-Colmar","< >","Sélestat","Colmar - AN",2023,2023,36,36,"2023-09-10","00:30:00","2023-09-10","04:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:00, Nuit non passe-minuit, DI","2022-01-07","unclassified",7,"publication"]
["SNCF-R","3D_STT-CMR_006","Selestat-Colmar","<","Sélestat","Ribeauvillé - 2B",2023,2023,25,25,"2023-06-19","23:00:00","2023-06-23","05:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_STT-CMR_007","Selestat-Colmar",">","Sélestat","Ribeauvillé - 1B",2023,2023,25,25,"2023-06-20","00:20:00","2023-06-24","04:50:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:30, Nuit non passe-minuit, MA,ME,JE,VE,SA","2022-01-07","unclassified","2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_STT-CMR_008","Selestat-Colmar","< >","Sélestat","Ribeauvillé - 2B",2023,2023,27,27,"2023-07-03","21:50:00","2023-07-04","05:20:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 07:30, Passe-minuit, LU/MA,MA/ME","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3D_STT-CMR_009","Selestat-Colmar","< >","Sélestat","Ribeauvillé - 2B",2023,2023,27,28,"2023-07-05","21:50:00","2023-07-14","05:20:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 07:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3D_STT-CMR_010","Selestat-Colmar","<","Sélestat","Ribeauvillé - 2B",2023,2023,31,31,"2023-08-03","23:00:00","2023-08-04","05:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, JE/VE,VE/SA","2022-01-07","unclassified","5, 6","publication"]
["SNCF-R","3D_STT-CMR_011","Selestat-Colmar",">","Sélestat","Ribeauvillé - 2B",2023,2023,31,31,"2023-08-04","00:20:00","2023-08-05","04:50:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:30, Nuit non passe-minuit, VE,SA","2022-01-07","unclassified","5, 6","publication"]
["SNCF-R","3D_STT-CMR_012","Selestat-Colmar",">","Ribeauvillé - 1B","Ostheim-Beblenheim",2023,2023,9,9,"2023-03-01","00:15:00","2023-03-01","05:20:00","periodical","Miscellaneous","Def, V1, 1V/2, 05:05, Nuit non passe-minuit, ME","2022-01-07","unclassified",3,"publication"]
["SNCF-R","3D_STT-CMR_013","Selestat-Colmar",">","Ribeauvillé - 1B","Ostheim-Beblenheim",2023,2023,9,9,"2023-02-28","21:45:00","2023-02-28","05:20:00","periodical","Miscellaneous","Def, V2, 1V/2, 07:35, Passe-minuit, MA/ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3D_STT-CMR_014","Selestat-Colmar","<","Colmar - ZI","Colmar - AN",2023,2023,39,39,"2023-09-27","22:35:00","2023-09-27","05:05:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:30, Passe-minuit, ME/JE","2022-01-07","unclassified","3, 4","publication"]
["SNCF-R","3D_STT-CMR_015","Selestat-Colmar","<","Ribeauvillé - 2B","Colmar - AN",2023,2023,39,39,"2023-09-28","00:05:00","2023-09-28","05:05:00","periodical","Miscellaneous","Def, V1, 1V/2, 05:00, Nuit non passe-minuit, JE","2022-01-07","unclassified",4,"publication"]
["SNCF-R","3D_STT-CMR_018","Selestat-Colmar","< >","Colmar - ZI","Colmar - AN",2023,2023,16,16,"2023-04-18","00:20:00","2023-04-19","04:50:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, MA,ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3D_STT-CMR_019","Selestat-Colmar","<","Colmar - ZI","Colmar - AN",2023,2023,17,18,"2023-04-27","00:05:00","2023-05-04","03:05:00","periodical","Miscellaneous","Def, V2, 1V/2, 03:00, Nuit non passe-minuit, ME,JE,VE","2022-01-07","unclassified","3, 4, 5","publication"]
["SNCF-R","3D_STT-CMR_020","Selestat-Colmar","< >","Sélestat","Ribeauvillé - 2B",2023,2023,29,29,"2023-07-17","22:00:00","2023-07-19","05:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 07:30, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_STT-CMR_021","Selestat-Colmar",">","Colmar - ZI","Colmar - AN",2023,2023,16,17,"2023-04-20","00:20:00","2023-04-26","03:20:00","periodical","Miscellaneous","Def, V1, 1V/2, 03:00, Nuit non passe-minuit, MA,ME,JE,VE","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3D_STT-CMR_022","Selestat-Colmar","< >","Sélestat","Colmar - AN",2023,2023,15,15,"2023-04-12","00:20:00","2023-04-15","04:50:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, ME,JE,VE,SA","2022-01-07","unclassified","3, 4, 5, 6","publication"]
["SNCF-R","3F_STT-CMR_008","Selestat-Colmar","< >","Sélestat","Colmar - AN",2023,2023,12,42,"2023-03-20","23:00:00","2023-10-20","05:00:00","periodical","Miscellaneous","Gen, V1,V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_CMR_001","Colmar","< >","Colmar - ZI","Colmar - ES",2023,2023,36,36,"2023-09-10","00:30:00","2023-09-10","04:30:00","periodical","Miscellaneous","Cap, V1,V2, 04:00, Nuit non passe-minuit, DI","2022-01-07","unclassified","1, 2, 3, 4, 5, 7","publication"]
["SNCF-R","3C_CMR_002","Colmar","<","Colmar - FM","Colmar - ES",2023,2023,26,31,"2023-06-26","23:00:00","2023-07-31","05:00:00","periodical","Miscellaneous","Cap, V2, 06:00, Passe-minuit, LU/MA,MA/ME","2022-01-07","unclassified","1, 2, 3","publication"]
["SNCF-R","3C_CMR_003","Colmar",">","Coilmar - AS","Colmar - ES",2023,2023,26,31,"2023-06-27","00:20:00","2023-08-01","04:50:00","periodical","Miscellaneous","Cap, V1, 04:30, Nuit non passe-minuit, MA,ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3C_CMR_004","Colmar","< >","Colmar - FM","Colmar - ES",2023,2023,29,29,"2023-07-17","22:00:00","2023-07-19","05:30:00","periodical","Miscellaneous","Cap, V1,V2, 07:30, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3C_CMR_005","Colmar",">","Colmar - FM","Colmar - ES",2023,2023,39,39,"2023-09-28","22:40:00","2023-09-28","05:10:00","periodical","Miscellaneous","Cap, V1, 06:30, Passe-minuit, JE/VE","2022-01-07","unclassified","4, 5","publication"]
["SNCF-R","3C_CMR_006","Colmar","<","Colmar - FM","Colmar - ES",2023,2023,39,39,"2023-09-29","00:10:00","2023-09-29","05:10:00","periodical","Miscellaneous","Cap, V2, 05:00, Nuit non passe-minuit, VE","2022-01-07","unclassified",5,"publication"]
["SNCF-R","3C_CMR_008","Colmar","<","Colmar - ZI","Colmar - Bât Voyageurs",2023,2023,17,18,"2023-04-27","00:05:00","2023-05-04","03:05:00","periodical","Miscellaneous","Cap, V2, 03:00, Nuit non passe-minuit, ME,JE,VE","2022-01-07","unclassified","3, 4, 5","publication"]
["SNCF-R","3C_CMR_009","Colmar",">","Colmar - ZI","Colmar - FM",2023,2023,34,34,"2023-08-21","23:00:00","2023-08-21","05:00:00","periodical","Miscellaneous","Cap, V1, 06:00, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3C_CMR-LUT_001","Colmar-Lutterbach","<","Rouffach","Rouffach - V4",2023,2023,41,44,"2023-10-10","00:15:00","2023-11-02","04:45:00","periodical","Miscellaneous","Cap, 2BIS, 04:30, Nuit non passe-minuit, MA,ME,JE,VE,SA","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3C_CMR-LUT_002","Colmar-Lutterbach","<","Rouffach","Rouffach - V4",2023,2023,43,43,"2023-10-29","22:30:00","2023-10-29","04:30:00","periodical","Miscellaneous","Cap, 2BIS, 06:00, Passe-minuit, DI/LU","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_CMR-LUT_003","Colmar-Lutterbach","<","Rouffach","Rouffach - V4",2023,2023,44,44,"2023-10-30","22:30:00","2023-10-30","04:30:00","periodical","Miscellaneous","Cap, 2BIS, 06:00, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3D_CMR-LUT_001","Colmar-Lutterbach","< >","Colmar - AS","Lutterbach (Haut-Rhin) - Bât Voyageurs",2023,2023,36,36,"2023-09-10","00:30:00","2023-09-10","04:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:00, Nuit non passe-minuit, DI","2022-01-07","unclassified",7,"publication"]
["SNCF-R","3D_CMR-LUT_002","Colmar-Lutterbach","<","Colmar - AS","Rouffach - C1",2023,2023,26,31,"2023-06-26","23:00:00","2023-07-31","05:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME","2022-01-07","unclassified","1, 2, 3","publication"]
["SNCF-R","3D_CMR-LUT_003","Colmar-Lutterbach",">","Colmar - AS","Rouffach- V3",2023,2023,26,31,"2023-06-27","00:20:00","2023-08-01","04:50:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:30, Nuit non passe-minuit, MA,ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3D_CMR-LUT_004","Colmar-Lutterbach","<","Colmar - ES","Rouffach - C1",2023,2023,26,31,"2023-06-28","23:00:00","2023-08-02","05:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:00, Passe-minuit, MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_CMR-LUT_005","Colmar-Lutterbach",">","Colmar - ES","Rouffach- V3",2023,2023,26,31,"2023-06-29","00:20:00","2023-08-03","04:50:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:30, Nuit non passe-minuit, ME,JE,VE,SA","2022-01-07","unclassified","3, 4, 5, 6","publication"]
["SNCF-R","3D_CMR-LUT_006","Colmar-Lutterbach","< >","Colmar - AS","Rouffach - C1",2023,2023,29,29,"2023-07-17","22:00:00","2023-07-19","05:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 07:30, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_CMR-LUT_007","Colmar-Lutterbach","< >","Colmar - ES","Rouffach - C1",2023,2023,29,30,"2023-07-20","22:00:00","2023-07-28","05:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 07:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6 ","publication"]
["SNCF-R","3D_CMR-LUT_008","Colmar-Lutterbach","< >","Rouffach- V3","Rouffach - V4",2023,2023,41,44,"2023-10-10","00:15:00","2023-11-02","04:45:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, MA,ME,JE,VE,SA","2022-01-07","unclassified","2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_CMR-LUT_009","Colmar-Lutterbach","<","Rouffach- V3","Rouffach - V4",2023,2023,42,43,"2023-10-17","00:15:00","2023-10-27","04:45:00","periodical","Miscellaneous","Def, V2, 1V/2, 04:30, Nuit non passe-minuit, MA,ME,JE,VE,SA","2022-01-07","unclassified","2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_CMR-LUT_010","Colmar-Lutterbach","< >","Rouffach- V3","Rouffach - V4",2023,2023,43,43,"2023-10-29","22:30:00","2023-10-29","04:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 06:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_CMR-LUT_011","Colmar-Lutterbach","< >","Rouffach- V3","Rouffach - V4",2023,2023,44,44,"2023-10-30","22:30:00","2023-10-30","04:30:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3D_CMR-LUT_012","Colmar-Lutterbach",">","Colmar - AS","Herrlisheim-près-Colmar ",2023,2023,39,39,"2023-09-28","22:40:00","2023-09-28","05:10:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:30, Passe-minuit, JE/VE","2022-01-07","unclassified","4, 5","publication"]
["SNCF-R","3D_CMR-LUT_013","Colmar-Lutterbach","< >","Rouffach - C2","Merxheim",2023,2023,9,9,"2023-02-28","00:15:00","2023-02-28","04:45:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, MA","2022-01-07","unclassified",2,"publication"]
["SNCF-R","3D_CMR-LUT_014","Colmar-Lutterbach","<","Colmar - AS","Rouffach - C1",2023,2023,39,39,"2023-09-29","00:10:00","2023-09-29","05:10:00","periodical","Miscellaneous","Def, V2, 1V/2, 05:00, Nuit non passe-minuit, VE","2022-01-07","unclassified",5,"publication"]
["SNCF-R","3D_CMR-LUT_015","Colmar-Lutterbach","<","Bollwiller - Bât Voyageurs","Staffelfelden",2023,2023,39,39,"2023-09-29","23:00:00","2023-09-29","04:35:00","periodical","Miscellaneous","Def, V2, 1V/2, 05:35, Passe-minuit, VE/SA","2022-01-07","unclassified","5, 6","publication"]
["SNCF-R","3D_CMR-LUT_016","Colmar-Lutterbach",">","Raedersheim","Staffelfelden",2023,2023,39,39,"2023-09-30","00:30:00","2023-09-30","04:30:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:00, Nuit non passe-minuit, SA","2022-01-07","unclassified",6,"publication"]
["SNCF-R","3D_CMR-LUT_020","Colmar-Lutterbach","< >","Bollwiller - EV","Lutterbach (Haut-Rhin) - Bât Voyageurs",2023,2023,37,37,"2023-09-12","00:25:00","2023-09-15","04:55:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, MA,ME,JE,VE","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3D_CMR-LUT_021","Colmar-Lutterbach","< >","Colmar - AS","Rouffach - V4",2023,2023,16,16,"2023-04-18","00:20:00","2023-04-19","04:50:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, MA,ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3F_CMR-LUT_005","Colmar-Lutterbach","< >","Colmar - AS","Lutterbach (Haut-Rhin) - Bât Voyageurs",2023,2023,11,41,"2023-03-13","23:16:00","2023-10-13","05:01:00","periodical","Miscellaneous","Gen, V1,V2, 1V/2, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6 ","publication"]
["SNCF-R","3C_LUT_001","Lutterbach","<","Richwiller - FP","Mulhouse-Musées",2023,2023,4,6,"2023-01-29","20:00:00","2023-02-12","04:55:00","periodical","Miscellaneous","Cap, V2, 08:55, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_LUT_002","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,4,6,"2023-01-29","22:00:00","2023-02-12","04:30:00","periodical","Miscellaneous","Cap, V1, 06:30, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_LUT_003","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,5,8,"2023-02-05","20:05:00","2023-02-26","05:00:00","periodical","Miscellaneous","Cap, V1, 08:55, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_LUT_004","Lutterbach","<","Richwiller - FP","Mulhouse-Musées",2023,2023,5,8,"2023-02-05","22:00:00","2023-02-26","04:30:00","periodical","Miscellaneous","Cap, V2, 06:30, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_LUT_005","Lutterbach","<","Richwiller - FP","Mulhouse-Musées",2023,2023,5,7,"2023-01-30","23:01:00","2023-02-15","05:01:00","periodical","Miscellaneous","Cap, V2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3C_LUT_006","Lutterbach","<","Richwiller - FP","Mulhouse-Musées",2023,2023,4,4,"2023-01-24","00:30:00","2023-01-26","03:30:00","periodical","Miscellaneous","Cap, V2, 03:00, Nuit non passe-minuit, MA,ME,JE","2022-01-07","unclassified","2, 3, 4","publication"]
["SNCF-R","3C_LUT_007","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,7,7,"2023-02-15","00:20:00","2023-02-15","04:50:00","periodical","Miscellaneous","Cap, V1, 04:30, Nuit non passe-minuit, MA,ME,JE","2022-01-07","unclassified","2, 3, 4","publication"]
["SNCF-R","3C_LUT_008","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,4,9,"2023-01-24","23:01:00","2023-02-28","05:01:00","periodical","Miscellaneous","Cap, V1, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3C_LUT_009","Lutterbach","<","Richwiller - FP","Mulhouse-Musées",2023,2023,8,9,"2023-02-21","00:20:00","2023-03-02","04:50:00","periodical","Miscellaneous","Cap, V2, 04:30, Nuit non passe-minuit, MA,ME,JE","2022-01-07","unclassified","2, 3, 4","publication"]
["SNCF-R","3C_LUT_010","Lutterbach","< >","Richwiller - FP","Mulhouse-Musées",2023,2023,36,36,"2023-09-10","00:30:00","2023-09-10","04:30:00","periodical","Miscellaneous","Cap, V1,V2, 04:00, Nuit non passe-minuit, DI","2022-01-07","unclassified",7,"publication"]
["SNCF-R","3C_LUT_012","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,36,36,"2023-09-04","23:20:00","2023-09-07","04:43:00","periodical","Miscellaneous","Cap, V1, 05:23, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_LUT_013","Lutterbach","< >","Richwiller - FP","Mulhouse-Musées",2023,2023,37,37,"2023-09-12","00:25:00","2023-09-15","04:45:00","periodical","Miscellaneous","Cap, V1,V2, 04:20, Nuit non passe-minuit, MA,ME,JE,VE","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3C_LUT_014","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,23,23,"2023-06-06","00:25:00","2023-06-06","04:45:00","periodical","Miscellaneous","Cap, V1, 04:20, Nuit non passe-minuit, MA","2022-01-07","unclassified",2,"publication"]
["SNCF-R","3C_LUT_015","Lutterbach","<","Richwiller - FP","Mulhouse-Musées",2023,2023,23,23,"2023-06-07","00:25:00","2023-06-07","04:55:00","periodical","Miscellaneous","Cap, V2, 04:30, Nuit non passe-minuit, ME","2022-01-07","unclassified",3,"publication"]
["SNCF-R","3C_LUT_016","Lutterbach","<","Richwiller - FP","Mulhouse-Musées",2023,2023,4,6,"2023-01-28","21:00:00","2023-02-11","06:00:00","periodical","Miscellaneous","Cap, V2, 09:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_LUT_017","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,4,6,"2023-01-28","22:10:00","2023-02-11","04:40:00","periodical","Miscellaneous","Cap, V1, 06:30, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_LUT_018","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,7,8,"2023-02-18","21:00:00","2023-02-25","06:00:00","periodical","Miscellaneous","Cap, V1, 09:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_LUT_019","Lutterbach","<","Richwiller - FP","Mulhouse-Musées",2023,2023,7,8,"2023-02-18","22:10:00","2023-02-25","04:40:00","periodical","Miscellaneous","Cap, V2, 06:30, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_LUT_020","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,4,9,"2023-01-23","23:01:00","2023-03-01","04:46:00","periodical","Miscellaneous","Cap, V1, 05:44, Passe-minuit, LU/MA,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3C_LUT_021","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,5,6,"2023-01-30","23:40:00","2023-02-08","04:40:00","periodical","Miscellaneous","Cap, V1, 05:00, Passe-minuit, LU/MA,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3C_LUT_022","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,5,6,"2023-01-31","23:40:00","2023-02-07","04:50:00","periodical","Miscellaneous","Cap, V1, 05:10, Passe-minuit, MA/ME,ME/JE","2022-01-07","unclassified","2, 3, 4","publication"]
["SNCF-R","3C_LUT_023","Lutterbach","<","Richwiller - FP","Mulhouse-Musées",2023,2023,6,6,"2023-02-06","23:40:00","2023-02-06","04:40:00","periodical","Miscellaneous","Cap, V2, 05:00, Passe-minuit, LU/MA,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3C_LUT_024","Lutterbach",">","Richwiller - FP","Mulhouse-Musées",2023,2023,7,7,"2023-02-14","00:20:00","2023-02-16","04:40:00","periodical","Miscellaneous","Cap, V1, 04:20, Nuit non passe-minuit, MA,JE","2022-01-07","unclassified","2, 4","publication"]
["SNCF-R","3C_LUT1RHE_001","Lutterbach-Rixheim (via Mulhouse Nord)","< > ","Mulhouse-Nord - ZP","Rixheim - BF",2023,2023,36,36,"2023-09-05","00:10:00","2023-09-06","04:40:00","periodical","Miscellaneous","Cap, V1M,V2M, 04:30, Nuit non passe-minuit, MA,ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3C_LUT1RHE_002","Lutterbach-Rixheim (via Mulhouse Nord)","< > ","Mulhouse-Nord - ZP","Rixheim - BF",2023,2023,40,43,"2023-10-02","22:35:00","2023-10-25","05:05:00","periodical","Miscellaneous","Cap, V1M,V2M, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3C_LUT1RHE_003","Lutterbach-Rixheim (via Mulhouse Nord)","< > ","Mulhouse-Nord - ZP","Rixheim - BF",2023,2023,39,42,"2023-09-30","21:10:00","2023-10-21","06:10:00","periodical","Miscellaneous","Cap, V1M,V2M, 09:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_LUT1RHE_004","Lutterbach-Rixheim (via Mulhouse Nord)","< > ","Lutterbach (Haut-Rhin) - BF","Rixheim - BF",2023,2023,47,47,"2023-11-26","23:20:00","2023-11-26","03:20:00","periodical","Miscellaneous","Cap, C,V1M,V2M, 04:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_LUT1RHE_005","Lutterbach-Rixheim (via Mulhouse Nord)","< > ","Mulhouse-Nord - A3","Rixheim - BF",2023,2023,12,13,"2023-03-23","05:05:00","2023-03-27","21:00:00","periodical","Miscellaneous","Cap, V1M,V2M, 111:55, Continu, LU,JE,VE,SA,DI","2022-01-07","unclassified","1, 4, 5, 6, 7","publication"]
["SNCF-R","3C_LUT1RHE_006","Lutterbach-Rixheim (via Mulhouse Nord)","< > ","Lutterbach (Haut-Rhin) - BF","Rixheim - BF",2023,2023,23,23,"2023-06-08","00:30:00","2023-06-08","04:30:00","periodical","Miscellaneous","Cap, V1M,V2M, 04:00, Nuit non passe-minuit, JE","2022-01-07","unclassified",4,"publication"]
["SNCF-R","3C_LUT1RHE_007","Lutterbach-Rixheim (via Mulhouse Nord)","< > ","Mulhouse-Nord - ZP","Rixheim - BF",2023,2023,39,42,"2023-10-01","20:20:00","2023-10-22","05:20:00","periodical","Miscellaneous","Cap, V1M,V2M, 09:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_LUT2RHE_001","Lutterbach-Rixheim-viaSud","< > ","Mulhouse-Dornach - J2","Mulhouse-Ville - FM",2023,2023,2,47,"2023-01-09","23:45:00","2023-11-24","04:15:00","periodical","Miscellaneous","Cap, 1,3,S1,V1,V2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_LUT2RHE_002","Lutterbach-Rixheim-viaSud",">","Mulhouse-Ville - AM","Mulhouse-Ville - FM",2023,2023,15,44,"2023-04-11","23:45:00","2023-11-03","04:15:00","periodical","Miscellaneous","Cap, 3,S3,V1, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_LUT2RHE_003","Lutterbach-Rixheim-viaSud","< > ","Mulhouse-Ville - FM","Rixheim - BF",2023,2023,17,37,"2023-04-24","23:30:00","2023-09-15","04:30:00","periodical","Miscellaneous","Cap, 1BIS3,2BIS3,V1,V2, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_LUT2RHE_004","Lutterbach-Rixheim-viaSud","<","Lutterbach (Haut-Rhin) - BF","Mulhouse-Dornach - J2",2023,2023,4,40,"2023-10-02","23:40:00","2023-10-02","04:50:00","periodical","Miscellaneous","Cap, V2, 05:10, Passe-minuit, LU/MA","2022-01-07","unclassified","1, 2","publication"]
["SNCF-R","3C_LUT2RHE_005","Lutterbach-Rixheim-viaSud","< >","Mulhouse-Ville - AM","Mulhouse-Ville - FM",2023,2023,2,47,"2023-01-09","23:45:00","2023-11-24","04:15:00","periodical","Miscellaneous","Cap, 1M,2M,6,8, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_LUT2RHE_006","Lutterbach-Rixheim-viaSud",">","Mulhouse-Ville - AM","Mulhouse-Ville - FM",2023,2023,15,44,"2023-04-11","23:45:00","2023-11-03","04:00:00","periodical","Miscellaneous","Cap, 1,V2, 04:15, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_LUT2RHE_007","Lutterbach-Rixheim-viaSud","< >","Mulhouse-Ville - AM","Mulhouse-Ville - FM",2023,2023,15,44,"2023-04-11","23:45:00","2023-11-03","04:15:00","periodical","Miscellaneous","Cap, 1BIS3,2BIS3,6,8, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_LUT2RHE_008","Lutterbach-Rixheim-viaSud","< >","Mulhouse-Ville - AM","Mulhouse-Ville - FM",2023,2023,15,44,"2023-04-11","22:00:00","2023-11-03","04:15:00","periodical","Miscellaneous","Cap, 1BIS3,1M,2BIS3,2M, 06:15, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_LUT2RHE_009","Lutterbach-Rixheim-viaSud","< >","Mulhouse-Ville - Bât Voyageurs","Mulhouse-Ville - FM",2023,2023,12,15,"2023-03-20","22:00:00","2023-04-14","04:30:00","periodical","Miscellaneous","Cap, V1,V2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_LUT2RHE_010","Lutterbach-Rixheim-viaSud","< >","Mulhouse-Ville - FM","Rixheim - BF",2023,2023,15,16,"2023-04-11","22:20:00","2023-04-21","04:30:00","periodical","Miscellaneous","Cap, V1,V2, 06:10, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_LUT2RHE_011","Lutterbach-Rixheim-viaSud","< >","Lutterbach (Haut-Rhin) - BF","Mulhouse-Dornach - J2",2023,2023,36,36,"2023-09-10","00:30:00","2023-09-10","04:30:00","periodical","Miscellaneous","Cap, V1,V2, 04:00, Nuit non passe-minuit, DI","2022-01-07","unclassified",7,"publication"]
["SNCF-R","3C_LUT2RHE_012","Lutterbach-Rixheim-viaSud","< >","Mulhouse-Dornach ","Mulhouse-Ville - Bât Voyageurs",2023,2023,8,8,"2023-02-24","00:25:00","2023-02-24","04:55:00","periodical","Miscellaneous","Cap, V1,V2, 04:30, Nuit non passe-minuit, VE","2022-01-07","unclassified",5,"publication"]
["SNCF-R","3C_LUT2RHE_013","Lutterbach-Rixheim-viaSud",">","Lutterbach (Haut-Rhin) - BF","Mulhouse-Dornach - J2",2023,2023,40,40,"2023-10-03","00:25:00","2023-10-03","05:25:00","periodical","Miscellaneous","Cap, V1, 05:00, Nuit non passe-minuit, MA","2022-01-07","unclassified",2,"publication"]
["SNCF-R","3C_LUT2RHE_014","Lutterbach-Rixheim-viaSud","< >","Mulhouse-Ville - FM","Rixheim - BF",2023,2023,40,40,"2023-10-03","23:15:00","2023-10-04","04:40:00","periodical","Miscellaneous","Cap, V1,V2, 05:25, Passe-minuit, MA/ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3C_LUT2RHE_017","Lutterbach-Rixheim-viaSud",">","Lutterbach (Haut-Rhin) - BF","Mulhouse-Dornach - J2",2023,2023,36,36,"2023-09-04","23:22:00","2023-09-07","04:45:00","periodical","Miscellaneous","Cap, V1, 05:22, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_LUT2RHE_018","Lutterbach-Rixheim-viaSud","< >","Lutterbach (Haut-Rhin) - BF","Mulhouse-Dornach - J2",2023,2023,37,37,"2023-09-12","00:25:00","2023-09-15","04:55:00","periodical","Miscellaneous","Cap, V1,V2, 04:30, Nuit non passe-minuit, MA,ME,JE,VE","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3C_LUT2RHE_019","Lutterbach-Rixheim-viaSud","< >","Mulhouse-Ville - AS","Rixheim - BF",2023,2023,38,43,"2023-09-18","23:45:00","2023-10-26","04:15:00","periodical","Miscellaneous","Cap, V1,V2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5","publication"]
["SNCF-R","3C_LUT2RHE_020","Lutterbach-Rixheim-viaSud","< >","Mulhouse-Dornach - J1","Rixheim - BF",2023,2023,29,29,"2023-07-20","00:30:00","2023-07-20","04:30:00","periodical","Miscellaneous","Cap, 1,3,V1,V2, 04:00, Nuit non passe-minuit, JE","2022-01-07","unclassified",4,"publication"]
["SNCF-R","3C_LUT2RHE_023","Lutterbach-Rixheim-viaSud","< >","Mulhouse-Ville - AM","Mulhouse-Ville - FM",2023,2023,42,42,"2023-10-16","23:15:00","2023-10-20","04:15:00","periodical","Miscellaneous","Cap, 1M,2M,6,8, 05:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_LUT2RHE_024","Lutterbach-Rixheim-viaSud","< >","Lutterbach (Haut-Rhin) - BF","Mulhouse-Dornach - J2",2023,2023,23,23,"2023-06-08","00:30:00","2023-06-08","04:30:00","periodical","Miscellaneous","Cap, V1,V2, 04:00, Nuit non passe-minuit, JE","2022-01-07","unclassified",4,"publication"]
["SNCF-R","3C_RHE_001","Rixheim","< >","Rixheim - BF","Habsheim - Bât Voyageurs",2023,2023,36,36,"2023-09-05","00:10:00","2023-09-06","04:40:00","periodical","Miscellaneous","Cap, V1,V2, 04:30, Nuit non passe-minuit, MA,ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3C_RHE_002","Rixheim","<","Rixheim - BF","Habsheim - Bât Voyageurs",2023,2023,39,42,"2023-09-30","21:10:00","2023-10-21","06:10:00","periodical","Miscellaneous","Cap, V2, 08:55, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_RHE_003","Rixheim",">","Rixheim - BF","Habsheim - Bât Voyageurs",2023,2023,39,42,"2023-09-30","22:30:00","2023-10-21","05:00:00","periodical","Miscellaneous","Cap, V1, 06:30, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_RHE_004","Rixheim","<","Rixheim - BF","Habsheim - Bât Voyageurs",2023,2023,40,43,"2023-10-02","22:35:00","2023-10-25","05:05:00","periodical","Miscellaneous","Cap, V2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3C_RHE_005","Rixheim",">","Rixheim - BF","Habsheim - Bât Voyageurs",2023,2023,40,43,"2023-10-02","23:59:00","2023-10-25","04:30:00","periodical","Miscellaneous","Cap, V1, 04:31, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3C_RHE_006","Rixheim","<","Mulhouse-Ville - AS","Habsheim - Bât Voyageurs",2023,2023,36,36,"2023-09-05","00:10:00","2023-09-06","04:40:00","periodical","Miscellaneous","Cap, V2, 04:30, Nuit non passe-minuit, MA,ME","2022-01-07","unclassified","2, 3","publication"]
["SNCF-R","3C_RHE_007","Rixheim","<","Mulhouse-Ville - AS","Habsheim - Bât Voyageurs",2023,2023,40,43,"2023-10-02","22:35:00","2023-10-25","05:05:00","periodical","Miscellaneous","Cap, V2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3C_RHE_008","Rixheim","<","Mulhouse-Ville - AS","Habsheim - Bât Voyageurs",2023,2023,39,42,"2023-09-30","21:10:00","2023-10-21","06:10:00","periodical","Miscellaneous","Cap, V2, 09:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3C_RHE_009","Rixheim",">","Rixheim - BF","Habsheim - Bât Voyageurs",2023,2023,39,42,"2023-10-01","22:15:00","2023-10-22","04:45:00","periodical","Miscellaneous","Cap, V1, 06:30, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_RHE_010","Rixheim",">","Rixheim - BF","Habsheim - Bât Voyageurs",2023,2023,4,5,"2023-01-23","23:05:00","2023-02-03","04:50:00","periodical","Miscellaneous","Cap, V1, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_RHE_011","Rixheim","<","Rixheim - BF","Habsheim - Bât Voyageurs",2023,2023,6,7,"2023-02-06","23:07:00","2023-02-17","04:52:00","periodical","Miscellaneous","Cap, V2, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_RHE_012","Rixheim","< >","Mulhouse-Ville - AS","Habsheim - Bât Voyageurs",2023,2023,47,47,"2023-11-26","23:20:00","2023-11-26","03:20:00","periodical","Miscellaneous","Cap, V1,V2, 04:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_RHE_016","Rixheim",">","Mulhouse-Ville - AS","Habsheim - Bât Voyageurs",2022,2022,50,50,"2022-12-12","23:20:00","2022-12-13","03:50:00","periodical","Miscellaneous","Cap, V1, 04:30, Passe-minuit, LU/MA,MA/ME","2022-01-07","unclassified","1, 2, 3","publication"]
["SNCF-R","3C_RHE_017","Rixheim","<","Mulhouse-Ville - AS","Habsheim - Bât Voyageurs",2022,2022,50,50,"2022-12-14","23:20:00","2022-12-15","03:50:00","periodical","Miscellaneous","Cap, V2, 04:30, Passe-minuit, ME/JE,JE/VE","2022-01-07","unclassified","3, 4, 5","publication"]
["SNCF-R","3C_RHE_018","Rixheim","<","Rixheim - BF","Habsheim - Bât Voyageurs",2023,2023,39,42,"2023-10-01","20:20:00","2023-10-22","05:20:00","periodical","Miscellaneous","Cap, V2, 09:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_RHE_019","Rixheim","<","Mulhouse-Ville - AS","Habsheim - Bât Voyageurs",2023,2023,39,42,"2023-10-01","20:20:00","2023-10-22","05:20:00","periodical","Miscellaneous","Cap, V2, 09:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3C_RHE_020","Rixheim",">","Mulhouse-Ville - AS","Habsheim - Bât Voyageurs",2023,2023,4,4,"2023-01-23","23:05:00","2023-01-23","01:05:00","periodical","Miscellaneous","Cap, V1, 02:00, Passe-minuit, LU/MA,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_001","Rixheim-StLouis","< >","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,36,36,"2023-09-05","00:10:00","2023-09-06","04:40:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, MA,ME","2022-01-07","unclassified",2.2999999999999998,"publication"]
["SNCF-R","3D_RHE-STL_002","Rixheim-StLouis","<","St-Louis (Haut-Rhin) - FM","St-Louis (Haut-Rhin) - XS",2023,2023,36,37,"2023-09-06","22:50:00","2023-09-12","05:20:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_RHE-STL_003","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,37,37,"2023-09-13","01:00:00","2023-09-13","04:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 03:00, Nuit non passe-minuit, ME","2022-01-07","unclassified",3,"publication"]
["SNCF-R","3D_RHE-STL_004","Rixheim-StLouis","< >","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,37,37,"2023-09-13","23:50:00","2023-09-13","04:20:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Passe-minuit, ME/JE","2022-01-07","unclassified","3, 4","publication"]
["SNCF-R","3D_RHE-STL_005","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,38,39,"2023-09-18","23:59:00","2023-09-27","04:30:00","periodical","Miscellaneous","Def, V2, 1V/2, 04:31, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_006","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,38,39,"2023-09-18","22:35:00","2023-09-27","05:05:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_007","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,37,38,"2023-09-16","22:30:00","2023-09-23","05:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:30, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RHE-STL_008","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,37,38,"2023-09-16","21:00:00","2023-09-23","06:00:00","periodical","Miscellaneous","Def, V1, 1V/2, 09:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RHE-STL_009","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,39,42,"2023-09-30","21:10:00","2023-10-21","06:10:00","periodical","Miscellaneous","Def, V2, 1V/2, 09:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RHE-STL_010","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,39,42,"2023-09-30","22:30:00","2023-10-21","05:00:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:30, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RHE-STL_011","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,40,43,"2023-10-02","22:35:00","2023-10-25","05:05:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_012","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,40,43,"2023-10-02","23:59:00","2023-10-25","04:30:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:31, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_013","Rixheim-StLouis","<","St-Louis (Haut-Rhin) - FM","St-Louis (Haut-Rhin) - XS",2023,2023,43,46,"2023-10-28","21:00:00","2023-11-18","06:00:00","periodical","Miscellaneous","Def, V2, 1V/2, 09:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RHE-STL_014","Rixheim-StLouis",">","St-Louis (Haut-Rhin) - FM","St-Louis (Haut-Rhin) - XS",2023,2023,43,46,"2023-10-28","22:45:00","2023-11-18","05:15:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:30, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RHE-STL_015","Rixheim-StLouis","<","St-Louis (Haut-Rhin) - FM","St-Louis (Haut-Rhin) - XS",2023,2023,44,46,"2023-10-30","21:00:00","2023-11-14","05:40:00","periodical","Miscellaneous","Def, V2, 1V/2, 08:40, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_016","Rixheim-StLouis",">","St-Louis (Haut-Rhin) - FM","St-Louis (Haut-Rhin) - XS",2023,2023,45,47,"2023-11-08","23:50:00","2023-11-22","04:20:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:30, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_017","Rixheim-StLouis","<","St-Louis (Haut-Rhin) - FM","St-Louis (Haut-Rhin) - XS",2023,2023,45,47,"2023-11-08","22:40:00","2023-11-22","05:10:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_018","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,47,47,"2023-11-25","21:05:00","2023-11-26","06:05:00","periodical","Miscellaneous","Def, V2, 1V/2, 09:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RHE-STL_019","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,47,47,"2023-11-25","22:35:00","2023-11-26","05:05:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:30, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication"]
["SNCF-R","3D_RHE-STL_020","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,47,47,"2023-11-26","21:40:00","2023-11-27","04:10:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:30, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RHE-STL_021","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,47,47,"2023-11-26","20:20:00","2023-11-27","05:20:00","periodical","Miscellaneous","Def, V1, 1V/2, 09:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RHE-STL_022","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,48,49,"2023-11-27","23:59:00","2023-12-08","04:30:00","periodical","Miscellaneous","Def, V2, 1V/2, 04:31, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_RHE-STL_023","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,48,49,"2023-11-27","22:35:00","2023-12-08","05:05:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_RHE-STL_024","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,48,48,"2023-11-28","23:10:00","2023-11-29","05:40:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:30, Passe-minuit, MA/ME,ME/JE","2022-01-07","unclassified","2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_025","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,48,48,"2023-11-28","23:59:00","2023-11-29","04:30:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:31, Passe-minuit, MA/ME,ME/JE","2022-01-07","unclassified","2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_026","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,37,38,"2023-09-17","21:40:00","2023-09-24","04:10:00","periodical","Miscellaneous","Def, V2, 1V/2, 06:30, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RHE-STL_027","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,39,42,"2023-10-01","21:40:00","2023-10-22","04:10:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:30, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RHE-STL_028","Rixheim-StLouis",">","St-Louis (Haut-Rhin) - FM","St-Louis (Haut-Rhin) - XS",2023,2023,43,46,"2023-10-29","21:40:00","2023-11-19","04:10:00","periodical","Miscellaneous","Def, V1, 1V/2, 06:30, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RHE-STL_029","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - XS",2023,2023,4,5,"2023-01-23","23:05:00","2023-02-03","04:50:00","periodical","Miscellaneous","Def, V1, 1V/2, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_RHE-STL_030","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - XS",2023,2023,6,7,"2023-02-06","23:05:00","2023-02-17","04:50:00","periodical","Miscellaneous","Def, V2, 1V/2, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_RHE-STL_031","Rixheim-StLouis","< >","St-Louis-la-Chaussée","St-Louis (Haut-Rhin) - XS",2023,2023,19,20,"2023-05-08","23:05:00","2023-05-19","04:50:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_RHE-STL_032","Rixheim-StLouis","< >","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - XS",2023,2023,47,47,"2023-11-26","23:20:00","2023-11-27","03:20:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RHE-STL_033","Rixheim-StLouis",">","St-Louis (Haut-Rhin) - FM","St-Louis (Haut-Rhin) - XS",2023,2023,44,46,"2023-10-30","22:35:00","2023-11-14","03:10:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:35, Passe-minuit, LU/MA,MA/ME,ME/JE","2022-01-07","unclassified","1, 2, 3, 4","publication"]
["SNCF-R","3D_RHE-STL_034","Rixheim-StLouis","< >","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - FM",2023,2023,7,7,"2023-02-19","23:15:00","2023-02-19","04:45:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 05:30, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RHE-STL_037","Rixheim-StLouis","< >","St-Louis-la-Chaussée","St-Louis (Haut-Rhin) - XS",2023,2023,29,29,"2023-07-19","00:05:00","2023-07-19","04:35:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:30, Nuit non passe-minuit, ME","2022-01-07","unclassified",3,"publication"]
["SNCF-R","3D_RHE-STL_038","Rixheim-StLouis","<","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,39,42,"2023-10-01","20:20:00","2023-10-22","05:20:00","periodical","Miscellaneous","Def, V2, 1V/2, 09:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RHE-STL_039","Rixheim-StLouis","<","St-Louis (Haut-Rhin) - FM","St-Louis (Haut-Rhin) - XS",2023,2023,43,46,"2023-10-29","20:20:00","2023-11-19","05:20:00","periodical","Miscellaneous","Def, V2, 1V/2, 09:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3D_RHE-STL_040","Rixheim-StLouis",">","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - P1",2023,2023,37,38,"2023-09-17","20:20:00","2023-09-24","05:20:00","periodical","Miscellaneous","Def, V1, 1V/2, 09:00, Passe-minuit, DI/LU","2022-01-07","unclassified","7, 1","publication"]
["SNCF-R","3F_RHE-STL_007","Rixheim-StLouis","< >","Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - XS",2023,2023,12,42,"2023-03-20","23:05:00","2023-10-20","04:50:00","periodical","Miscellaneous","Gen, V1,V2, 1V/2, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_STL_001","StLouis","<","St-Louis (Haut-Rhin) - P2","St-Louis (Haut-Rhin) - P3",2023,2023,36,37,"2023-09-06","22:50:00","2023-09-12","05:20:00","periodical","Miscellaneous","Cap, 2BIS, 06:30, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_STL_002","StLouis","<","St-Louis (Haut-Rhin) - P2","St-Louis (Haut-Rhin) - P3",2023,2023,6,7,"2023-02-06","23:05:00","2023-02-17","04:50:00","periodical","Miscellaneous","Cap, 2BIS, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_STL_003","StLouis",">","St-Louis (Haut-Rhin) - P2","St-Louis (Haut-Rhin) - P3",2023,2023,4,5,"2023-01-23","23:05:00","2023-02-03","04:50:00","periodical","Miscellaneous","Cap, 1BIS, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3C_STL_004","StLouis","< >","St-Louis (Haut-Rhin) - P2","St-Louis (Haut-Rhin) - P3",2023,2023,19,20,"2023-05-08","23:05:00","2023-05-19","04:50:00","periodical","Miscellaneous","Cap, 1BIS,2BIS, 05:45, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_SG-KE_001","Strasbourg-Kehl","< >","Strasbourg-Ville - J1","Strasbourg-Port-du-Rhin - JN",2023,2023,36,37,"2023-09-04","22:40:00","2023-09-15","04:40:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_SG-KE_002","Strasbourg-Kehl","< >","Strasbourg-Ville - J1","Strasbourg-Neudorf - JE",2023,2023,38,43,"2023-09-18","22:40:00","2023-10-23","04:40:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_SG-KE_003","Strasbourg-Kehl","< >","Strasbourg-Ville - J1","Krimmeri-Meinau",2023,2023,43,48,"2023-10-24","22:40:00","2023-11-28","04:40:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_SG-KE_004","Strasbourg-Kehl","< >","Strasbourg-Neudorf - Bât Voyageurs","Strasbourg-Port-du-Rhin - JN",2023,2023,43,48,"2023-10-24","21:40:00","2023-11-28","05:40:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_SG-KE_005","Strasbourg-Kehl","< >","Strasbourg-Ville - J1","Strasbourg-Port-du-Rhin - JN",2023,2023,48,49,"2023-11-29","22:40:00","2023-12-08","04:40:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_SG-KE_006","Strasbourg-Kehl",">","Strasbourg-Ville - J1","Strasbourg-Port-du-Rhin - XD",2023,2023,9,9,"2023-02-28","00:15:00","2023-03-03","06:05:00","periodical","Miscellaneous","Def, V1, 1V/2, 05:50, Nuit non passe-minuit, MA,ME,JE,VE","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3D_SG-KE_007","Strasbourg-Kehl","< >","Strasbourg-Neudorf - Bât Voyageurs","Strasbourg-Port-du-Rhin ",2022,2022,50,50,"2022-12-12","22:00:00","2022-12-16","06:00:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 08:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_SG-KE_008","Strasbourg-Kehl","<","Strasbourg-Ville - J1","Strasbourg-Port-du-Rhin - XD",2023,2023,10,10,"2023-03-06","22:55:00","2023-03-09","04:20:00","periodical","Miscellaneous","Def, V2, 1V/2, 05:25, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3D_SG-KE_009","Strasbourg-Kehl","< >","Strasbourg-Ville - J1","Strasbourg-Port-du-Rhin - XD",2023,2023,11,11,"2023-03-14","00:15:00","2023-03-17","04:20:00","periodical","Miscellaneous","Def, V1,V2, 2V/2, 04:05, Nuit non passe-minuit, MA,ME,JE,VE","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","3D_SG-KE_010","Strasbourg-Kehl","<","Strasbourg-Ville - J1","Strasbourg-Port-du-Rhin - XD",2023,2023,18,18,"2023-05-06","00:05:00","2023-05-06","04:05:00","periodical","Miscellaneous","Def, V2, 1V/2, 04:00, Nuit non passe-minuit, SA","2022-01-07","unclassified",6,"publication"]
["SNCF-R","3D_SG-KE_011","Strasbourg-Kehl",">","Strasbourg-Ville - J1","Strasbourg-Port-du-Rhin - XD",2023,2023,18,18,"2023-05-05","00:20:00","2023-05-05","04:20:00","periodical","Miscellaneous","Def, V1, 1V/2, 04:00, Nuit non passe-minuit, VE","2022-01-07","unclassified",5,"publication"]
["SNCF-R","3F_SG-KE_001","Strasbourg-Kehl","<","Strasbourg-Ville - J1","Strasbourg-Port-du-Rhin - XD",2023,2023,13,42,"2023-03-27","22:40:00","2023-10-20","04:40:00","periodical","Miscellaneous","Gen, V2, 1V/2, 06:00, Passe-minuit, LU/MA,MA/ME,ME/JE,JE/VE,VE/SA","2022-01-07","unclassified","1, 2, 3, 4, 5, 6","publication"]
["SNCF-R","3F_SG-KE_004","Strasbourg-Kehl",">","Strasbourg-Ville - J1","Strasbourg-Port-du-Rhin - XD",2023,2023,13,42,"2023-03-27","00:15:00","2023-10-20","06:05:00","periodical","Miscellaneous","Gen, V1, 1V/2, 05:50, Nuit non passe-minuit, MA,ME,JE,VE,SA","2022-01-07","unclassified","2, 3, 4, 5","publication"]
["SNCF-R","R22718c",null,"< >","Reding-Remilly","Reding-Remilly",2025,2025,39,50,null,null,null,null,"continuous","Maintenance","30 Sarraltroff - Berthelming: HS: V1 : 3,855 km de RR et V2 : 5,11 km de RRN_1F","2022-10-06","High",12,"Planned"]
["SNCF-R",null,null,"< >","Frouard-Pagny","Frouard-Pagny",2025,2025,26,34,null,null,null,null,"continuous","Maintenance","140 Dieulouard - Pont-à-Mousson RR ","2022-10-06","High",9,"Planned"]
["SNCF-R","R20536y",null,"< >","Pagny-Noveant ","Pagny-Noveant ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","145.1 Création d'un atelier TER en I-LOR","2022-10-06",null,null,"Planned"]
["SNCF-R","R20536y",null,"< >","Lerouville-Noveant","Lerouville-Noveant",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","145.2 Création d'un atelier TER en I-LOR","2022-10-06",null,null,"Planned"]
["SNCF-R","R24725q",null,"< >","Noveant-Metz ","Noveant-Metz ",2025,2025,11,15,null,null,null,null,"continuous","Maintenance","151.2 RAV Metz Sablon","2022-10-06","High",5,"Planned"]
["SNCF-R","R21788j",null,"< >","Reding-Remilly","Reding-Remilly",2025,2025,5,9,null,null,null,null,"continuous","Maintenance","152.1  Bénestroff - Metz : RVB HS voies 1 et 2 de 9 zones courtes (TB éxo) pour une longueur total de 1697m.","2022-10-06","High",5,"Planned"]
["SNCF-R","R21788j",null,"< >","Remilly-Metz","Remilly-Metz",2025,2025,10,13,null,null,null,null,"continuous","Maintenance","152.2  Bénestroff - Metz : RVB HS voies 1 et 2 de 9 zones courtes (TB éxo) pour une longueur total de 1697m.","2022-10-06","High",4,"Planned"]
["SNCF-R","R22699y",null,"< >","Reding-Remilly","Reding-Remilly",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","153.1 Bénestroff - Metz-Ville: HS: V2 : 11,507 km de RR et 3,342 km de RRN_1F et V1 : 6,731 km de RR et 0,98 km de RRN_1F","2022-10-06","High",null,"Planned"]
["SNCF-R","R22699y",null,"< >","Remilly-Metz","Remilly-Metz",2025,2025,46,51,null,null,null,null,"continuous","Maintenance","153.2 Bénestroff - Metz-Ville: HS: V2 : 11,507 km de RR et 3,342 km de RRN_1F et V1 : 6,731 km de RR et 0,98 km de RRN_1F","2022-10-06","High",6,"Planned"]
["SNCF-R","R24727y",null,"< >","Lerouville-Noveant","Lerouville-Noveant",2025,2025,11,15,null,null,null,null,"continuous","Maintenance","158.2 RAV Lérouville ","2022-10-06","Major",null,"Planned"]
["SNCF-R","R24793y",null,"< >","Remilly-Metz","Remilly-Metz",2025,2025,11,15,null,null,null,null,"continuous","Maintenance","167.1 RVB HS, ligne 140 et 172, Rémilly Faulquemont.","2022-10-06",null,5,"Planned"]
["SNCF-R","R10318p",null,"< >","Remilly-Metz ","Remilly-Metz ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","264.7 Corridors européens ETCS niveau1, Corridor 2 - Axe Longuyon - Bettembourg Bâle. PHASE 1 à 5","2022-10-06","High",null,"Planned"]
["SNCF-R","R27356w",null,"< >","Creil-LongueilSteMarie ","Creil-LongueilSteMarie ",2025,2025,38,47,null,null,null,null,"continuous","Maintenance","Simplification en gare de Pont Sainte Maxence (8 AdV)\nVérifier compatibilités axes alternatifs FRET","2022-10-06","High",10,"Planned"]
["SNCF-R","R23175n",null,"< >","Longueil Ste Marie-Tergnier ","Longueil Ste Marie-Tergnier ",2025,2025,2,50,null,null,null,null,"periodical","Maintenance","Travaux du BV de Compiègne","2022-10-06","High",22,"Planned"]
["SNCF-R","R01709q",null,"< >","Longueil Ste Marie-Tergnier ","Longueil Ste Marie-Tergnier ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","PRa Margny les compiègne (Elargissement ? Création ? Réhaussement ?)","2022-10-06","High",null,"Planned"]
["SNCF-R","R20537q",null,"< >","Hagondange","Hagondange",2025,2025,2,9,null,null,null,null,"continuous","Maintenance","25 Création SST Richemont","2022-10-06","High",9,"Planned"]
["SNCF-R","R11993z",null,"< >","Maubeuge","Maubeuge",2025,2025,2,50,null,null,null,null,"continuous","Maintenance","73 PMR Maubeuge","2022-10-06","Major",49,"Planned"]
["SNCF-R","R16036p",null,"< >","Aulnoye","Aulnoye",2025,2025,2,50,null,null,null,null,"continuous","Maintenance","78 Aulnoye PMR","2022-10-06","Major",49,"Planned"]
["SNCF-R","R14872b",null,"< >","Uckange","Uckange",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","134.1 Uckange - poste 1 : 11;12; 13/14; 15/16; 17/18; 18; 19; 20; 21; 22/23 - Aiguilles équipées de réchauffeurs gaz . A équiper avec des réchauffeurs électriques.","2022-10-06",null,null,"Planned"]
["SNCF-R","R14873t",null,"< >","Uckange","Uckange",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","134.2 Uckange - poste 2 : 15/16; 17/18; 19/20; 21/22; 23/116; 114; 118; 115; 117 - Aiguilles équipées de réchauffeurs gaz . A équiper avec des réchauffeurs électriques.","2022-10-06",null,null,"Planned"]
["SNCF-R","R20516q",null,"< >","Mohon-Sedan\n\n***","Mohon-Sedan\n\n***",2025,2025,21,30,null,null,null,null,"continuous","Maintenance","144 Gare de Lumes  :  4 RAV (530, 531A, 531B, 523/522) et Gare de Margut-Fromy  :  3 SUPPR (Aig C- Aig G - TO XB","2022-10-06","Major",10,"Planned"]
["SNCF-R","R20516q",null,"< >","Sedan-Longuyon\n\n***","Sedan-Longuyon\n\n***",2025,2025,26,32,null,null,null,null,"continuous","Maintenance","144 Gare de Lumes  :  4 RAV (530, 531A, 531B, 523/522) et Gare de Margut-Fromy  :  3 SUPPR (Aig C- Aig G - TO XB","2022-10-06","Major",7,"Planned"]
["SNCF-R","R22914u",null,"< >","Longuyon-Thionville","Longuyon-Thionville",2025,2025,15,18,null,null,null,null,"continuous","Maintenance","156 Remplacement de deux TM du PRA sur RD 653, Terville, ligne 204 000, de Thionville à Mohon.","2022-10-06","Major",4,"Planned"]
["SNCF-R","R24793y",null,"< >","Remilly-Bening","Remilly-Bening",2025,2025,16,20,null,null,null,null,"continuous","Maintenance","167.2 RVB HS, ligne 140 et 172, Rémilly Faulquemont.","2022-10-06","High",5,"Planned"]
["SNCF-R","R26291q",null,"< >","Mohon-Sedan","Mohon-Sedan",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","174.2 UP SES Charleville : Éradication de CDV de type monorail/ancien","2022-10-06",null,null,"Planned"]
["SNCF-R","R26739u",null,"< >","Sedan-Longuyon","Sedan-Longuyon",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","178 Confortement Remblai Villecloye   L204000 km 210+762,","2022-10-06",null,null,"Planned"]
["SNCF-R","R07181c",null,"< >","Tergnier-StQuentin","Tergnier-StQuentin",2025,2025,2,15,null,null,null,null,"periodical","Maintenance","213.1 PMR Saint Quentin","2022-10-06","Major",7,"Planned"]
["SNCF-R","R07181c",null,"< >","StQuentin-Busigny","StQuentin-Busigny",2025,2025,2,15,null,null,null,null,"periodical","Maintenance","213.2 PMR Saint Quentin","2022-10-06","Major",7,"Planned"]
["SNCF-R","R12336k",null,"< >","StQuentin-Busigny","StQuentin-Busigny",2025,2025,21,25,null,null,null,null,"continuous","Maintenance","218 Régé Potences signaux C106 et C110/112 Busigny","2022-10-06","High",5,"Planned"]
["SNCF-R","R16040f",null,"< >","StQuentin-Busigny","StQuentin-Busigny",2025,2025,35,41,null,null,null,null,"continuous","Maintenance","221.1 Gare de Busigny :  3 RAV (3 BS) et 2 RB (2 BS) + FEM 13974 RVB voie 3 et 5 en gare de Busigny","2022-10-06","Major",7,"Planned"]
["SNCF-R","R18929f",null,"< >","VilliersLeBel-Vemars\n","VilliersLeBel-Vemars\n",2025,2025,2,50,null,null,null,null,"continuous","Maintenance","224.1 Liaison ferroviaire Roissy-I-HP - Partie Infrapôle Nord Européen","2022-10-06","Major",49,"Planned"]
["SNCF-R","R18929f",null,"< >","Vemars-Sainghin\n","Vemars-Sainghin\n",2025,2025,2,50,null,null,null,null,"continuous","Maintenance","224.2 Liaison ferroviaire Roissy-I-HP - Partie Infrapôle Nord Européen","2022-10-06","Major",49,"Planned"]
["SNCF-R","R24970y",null,"< >","Vemars-Sainghin","Vemars-Sainghin",2025,2025,3,27,null,null,null,null,"continuous","Maintenance","237 Réfection des collecteurs drainant de la gare Haute I-HP","2022-10-06","Major",26,"Planned"]
["SNCF-R","R24971q",null,"< >","VilliersLeBel-Vemars\n","VilliersLeBel-Vemars\n",2025,2025,2,8,null,null,null,null,"continuous","Maintenance","238.2 LN3 2025 - Remplacement de 5 AD (2 AD Interco LN3 à Ourcq – 2 AD Interco LN1 et 1 AD au Km 4 (226 000) )","2022-10-06","Major",8,"Planned"]
["SNCF-R","R25608n",null,"< >","StQuentin-Busigny","StQuentin-Busigny",2025,2025,35,41,null,null,null,null,"continuous","Maintenance","241.1 RVB Gare de Busigny voie 3 et voie 5\njumelée avec le F49036 dossier FIC commun","2022-10-06","Major",7,"Planned"]
["SNCF-R","R30274v",null,"< >","LilleEurope-Calais","LilleEurope-Calais",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","258 Régénération des DBC (4 => 4 bis) PRCI 45 et 46","2022-10-06","High",null,"Planned"]
["SNCF-R","R25610w",null,"< >","Tergnier-StQuentin ","Tergnier-StQuentin ",2025,2025,39,41,null,null,null,null,"continuous","Maintenance","284 Simplification du Brt 2 de MONTESCOURT","2022-10-06","High",3,"Planned"]
["SNCF-R","R00148e",null,"< >","Aulnoye","Aulnoye",2025,2025,39,48,null,null,null,null,"continuous","Maintenance","298 - RVB Vois RM Aulnoye","2022-10-06","High",10,"Planned"]
["SNCF-R","R31151t",null,"< >","Vemars-Sainghin","Vemars-Sainghin",2025,2025,32,50,null,null,null,null,"continuous","Maintenance","313 - RAV PRCI 26 IZEL Pk 165+000 -169+500  - (4 AdV 1/46)","2022-10-06","Major",19,"Planned"]
["SNCF-R",null,null,"< >","Tergnier-StQuentin ","Tergnier-StQuentin ",2025,2025,3,25,null,null,null,null,"periodical","Maintenance","314 - Travaux d'artère câble et passage câble St Quentin Tergnier","2022-10-06","High",9,"Planned"]
["SNCF-R","?",null,"< >","Tergnier","Tergnier",2025,2025,2,39,null,null,null,null,"periodical","Maintenance","331.1 - Passerelle de Tergnier - Démolition","2022-10-06","Major",19,"Planned"]
["SNCF-R",null,null,"< >","Longuyon-Thionville","Longuyon-Thionville",2025,2025,8,39,null,null,null,null,"periodical","Development","339.1 CCR Thionville ","2022-10-06","High",5,"Planned"]
["SNCF-R",null,null,"< >","Uckange-Thionville","Uckange-Thionville",2025,2025,6,39,null,null,null,null,"periodical","Development","339.2 CCR Thionville ","2022-10-06","High",4,"Planned"]
["SNCF-R",null,null,"< >","Thionville-Apach","Thionville-Apach",2025,2025,4,39,null,null,null,null,"periodical","Development","339.3 CCR Thionville ","2022-10-06","High",6,"Planned"]
["SNCF-R",null,null,"< >","Thionville-Zoufftgen","Thionville-Zoufftgen",2025,2025,7,39,null,null,null,null,"periodical","Development","339.5 CCR Thionville ","2022-10-06","High",4,"Planned"]
["SNCF-R","??",null,"< >","Mohon-Mohon\n\n***","Mohon-Mohon\n\n***",2025,2025,36,42,null,null,null,null,"periodical","Maintenance","344.1 OGE RR File Haute ","2022-10-06","High",4,"Planned"]
["SNCF-R",0,null,"< >","Paris-Stade de France ","Paris-Stade de France ",2025,2025,13,23,null,null,null,null,"continuous","Maintenance","NExTEO BD - Nord : Phase 2a : Prédisposition des installations  de sécurité (P30+P31+P44+P47+P6)\nCréation du STD NExTEO et du réseau radio\nGare du Nord Sout à Stade de France St Denis sur voies RO et DO","2022-10-06","High",11,"Planned"]
["SNCF-R","R28557g",null,"< >","Paris-Stade de France ","Paris-Stade de France ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","Déplacement de la section de séparation de Paris Gare du Nord souterraine (uniquement RER B pour adaptation MR MING ?)","2022-10-06","High",null,"Planned"]
["SNCF-R",0,null,"< >","ParisNord-Bif de Pierrefitte ","ParisNord-Bif de Pierrefitte ",2025,2025,4,45,null,null,null,null,"continuous","Maintenance","Réfection des quais de la gare du Nord de surface","2022-10-06","High",41,"Planned"]
["SNCF-R","R27716w",null,"< >","Paris-Stade de France ","Paris-Stade de France ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","Fontis Gare du Nord","2022-10-06","High",null,"Planned"]
["SNCF-R","R27333n",null,"< >","Paris-Stade de France ","Paris-Stade de France ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","RR industrialisé BOA entre Paris et Epinay\nVoies DM et RM du pk 1 au pk 6\nA faire en 2025","2022-10-06","High",null,"Planned"]
["SNCF-R","R19150h",null,"< >","ParisNord-Bif de Pierrefitte ","ParisNord-Bif de Pierrefitte ",2025,2025,22,50,null,null,null,null,"periodical","Maintenance","Franchissement urbain Pleyel (FUP) : phase 2\nVoir pour déverinage en semaine au lieu des WE","2022-10-06","Major",17,"Planned"]
["SNCF-R","R27367e",null,"< >","SaintDenis-VilliersLeBel ","SaintDenis-VilliersLeBel ",2025,2025,8,13,null,null,null,null,"continuous","Maintenance","RVB HS à Joncherolles (RJ)\nVoir pour décaler d'une semaine cause TX SDM Combs Melun (WE 09/10 et 10/11)","2022-10-06","Major",6,"Planned"]
["SNCF-R","R19252v",null,"< >","SaintDenis-VilliersLeBel ","SaintDenis-VilliersLeBel ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","SMGL Grand Joncherolles: Pivos + Syprai","2022-10-06","High",null,"Planned"]
["SNCF-R","R23785e",null,"< >","SaintDenis-VilliersLeBel ","SaintDenis-VilliersLeBel ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","SMGL Grand Joncherolles adaptation au RER NG","2022-10-06","Major",null,"Planned"]
["SNCF-R","R25348s",null,"< >","SaintDenis-VilliersLeBel ","SaintDenis-VilliersLeBel ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","Régé 2 tabliers à poutres jumelles PRA de Pierrefitte (petit ouvrage accolé au PRa 4 voies GL+RER)\nITC côté 272000","2022-10-06","High",null,"Planned"]
["SNCF-R","R04320n",null,"< >","SaintDenis-VilliersLeBel ","SaintDenis-VilliersLeBel ",2025,2025,47,49,null,null,null,null,"continuous","Maintenance","SDA PMR de niveau 4 de la gare de Villiers le Bel (notamment passerelle traversante ville-ville)","2022-10-06","Major",3,"Planned"]
["SNCF-R","R31061f",null,"< >","Villiers le Bel-Goussainville ","Villiers le Bel-Goussainville ",2025,2025,38,51,null,null,null,null,"continuous","Maintenance","RVB SR Villiers Orry Chantilly Creil à la place d'Epinay Meru\nV1D du 15+085 au 19+120 soit 4135 ml\nV1D du 33+250 au 41+300 soit 7400 ml\nV1D du 45+950 au 48+000 soit 2050 ml\nV1D du 49+400 au 49+830 soit 430 ml\nV2D du 14+090 au 19+231 soit 5141 ml\nV2D du 45+950 au 48+000 soit 2050 ml\nVM du 36+000 au 41+190 soit 5190 ml","2022-10-06","High",14,"Planned"]
["SNCF-R","R30494m",null,"< >","Goussainville-Orry ","Goussainville-Orry ",2025,2025,26,30,null,null,null,null,"continuous","Maintenance","Déblai de Marly la Ville & Remblai de Louvres-Marlot - amélioration du drainage - Ligne 272 000 km 24+900 à 27+160","2022-10-06","High",5,"Planned"]
["SNCF-R","R28647u",null,"< >","Goussainville-Orry ","Goussainville-Orry ",2025,2025,2,50,null,null,null,null,"continuous","Maintenance","Roissy Picardie : Block Survilliers (dont Goussainville) : saut de mouton + création 2 voies et quais + impacts sig + Ecopont de Chantilly","2022-10-06","Major",49,"Planned"]
["SNCF-R","R13458r",null,"< >","Goussainville-Orry ","Goussainville-Orry ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","Renouvellement des 10 interrupteurs 25 kV du poste de traction électrique de Marly-la-Ville","2022-10-06","High",null,"Planned"]
["SNCF-R","R14111f",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","CPER P 2015 2020 - Creil - aménagement du pôle Gare","2022-10-06","High",null,"Planned"]
["SNCF-R","R18200t",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,2,50,null,null,null,null,"continuous","Maintenance","Modernisation du noeud ferroviaire de Creil - Phase 2 (lié Roissy Picardie)","2022-10-06","Major",49,"Planned"]
["SNCF-R","R27364e",null,"< >","Creil-Longueau ","Creil-Longueau ",2025,2025,39,49,null,null,null,null,"continuous","Maintenance","4 RAV  + du RVB Clermont de l'Oise\n1718a & 1718ac/bd & 1728a et 1728b\nen même temps que St Just","2022-10-06","High",11,"Planned"]
["SNCF-R","R03930u",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,2,50,null,null,null,null,"continuous","Maintenance","G&C : PMR Chantilly : phase 2 (notamment PaSo)\nMise en œuvre de Tabliers Auxiliaires\nVersion initiale","2022-10-06","Major",49,"Planned"]
["SNCF-R","R03930u",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","G&C : PMR Chantilly : phase 2 (notamment PaSo)\nMise en œuvre d'un cadre préfabriqué sur une OCP de 100h\nVersion initiale","2022-10-06","Major",null,"Planned"]
["SNCF-R","R03930u",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","G&C : PMR Chantilly : phase 2 (notamment PaSo)\nMise en œuvre de Tabliers Auxiliaires\nVersion validée","2022-10-06","Major",null,"Planned"]
["SNCF-R","R03930u",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,39,49,null,null,null,null,"continuous","Maintenance","G&C : PMR Chantilly : phase 2 (notamment PaSo)\nMise en œuvre d'un cadre préfabriqué sur une OCP de 100h\nVersion validée","2022-10-06","Major",11,"Planned"]
["SNCF-R","R03838y",null,"< >","Creil-Longueau ","Creil-Longueau ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","VIGIRAIL 2025 - St Just en Chaussée: \nRAV 1803 & 1805 & 1819b et Simplif du Waa+ Simplif du Brt Za de Gannes\nEn même temps que Clermont et attention à l'accès base de St Just pour Roissy Picardie","2022-10-06","High",null,"Planned"]
["SNCF-R",0,null,"< >","Paris-Stade de France ","Paris-Stade de France ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","Suppression des zones neutres des portiques souples des quais de la Gare du Nord","2022-10-06","High",null,"Planned"]
["SNCF-R","R06869w\n",null,"< >","Arras-Lens ","Arras-Lens ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","72 Déblai de FARBUS au km 202,100 côté V1 et V2: Travaux de reconnaissance et injection","2022-10-06","High",null,"Planned"]
["SNCF-R","R25632n",null,"< >","Longueau-Bif d'Agny exclue ","Longueau-Bif d'Agny exclue ",2025,2025,6,9,null,null,null,null,"continuous","Maintenance","105 LONGUEAU - RAV Brt 2700","2022-10-06","High",4,"Planned"]
["SNCF-R","R01584g",null,"< >","Creil-Longueau","Creil-Longueau",2025,2025,14,48,null,null,null,null,"periodical","Maintenance","124.1 SR ZD Ailly Sur Noye Miraumont \nHSI V80 HP\n\n","2022-10-06","Major",23,"Planned"]
["SNCF-R","R01584g",null,"< >","Longueau-Bif d'Agny exclue","Longueau-Bif d'Agny exclue",2025,2025,14,48,null,null,null,null,"periodical","Maintenance","124.2 SR ZD Ailly Sur Noye Miraumont  \nHSI V80 HP\nLIGNE PARIS/LILLE - RB/RT SR 2018 (Lot 4) DU PK 115.287 AU PK 165.930 VOIE 1 ET 2","2022-10-06","Major",23,"Planned"]
["SNCF-R","R01584g",null,"< >","Longueau-Bif de l'arbre Robert exclue ","Longueau-Bif de l'arbre Robert exclue ",2025,2025,14,48,null,null,null,null,"periodical","Maintenance","124.3 SR ZD Ailly Sur Noye Miraumont\nHSI V80 HP\n LIGNE PARIS/LILLE - RB/RT SR 2018 (Lot 4) DU PK 115.287 AU PK 165.930 VOIE 1 ET 2","2022-10-06","Major",23,"Planned"]
["SNCF-R","R00157e",null,"< >","Longueau-Bif d'Agny exclue","Longueau-Bif d'Agny exclue",2025,2025,19,46,null,null,null,null,"periodical","Maintenance","210 .1 ACHIET-Renouvel. Partie 25 kV","2022-10-06","High",8,"Planned"]
["SNCF-R","R00157e",null,"< >","Longueau-Bif de l'arbre Robert exclue ","Longueau-Bif de l'arbre Robert exclue ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","210.2 ACHIET-Renouvel. Partie 25 kV","2022-10-06","High",null,"Planned"]
["SNCF-R","R18462k",null,"< >","Ostricourt-Lille","Ostricourt-Lille",2025,2025,13,21,null,null,null,null,"continuous","Maintenance","223.1 RR 16 585m - V1 233,180 à 235,765 - V2 233,220 à 238,470 - V2 238,590 à 239,470 - V2 239,630 à 247,500 + Voie 2 du 171,950 au 173,450","2022-10-06","High",9,"Planned"]
["SNCF-R","R19153h",null,"< >","Hazebrouck-Dunkerque\n\n*","Hazebrouck-Dunkerque\n\n*",2025,2025,4,44,null,null,null,null,"periodical","Maintenance","226 Gare de Dunkerque : RVB Voie 1 à quai (304ml), Voie 2 à quai (304ml), Voie 3 à quai (298ml), Voie 4 à quai (273ml) - RB+RT du 302,350 au 304,497 - RVB sur 1299m - RB+RT sur 3826m - B sur 23m + Reliquat RVB HS 301000 2016 (F50005)","2022-10-06","Major",25,"Planned"]
["SNCF-R","R21349s",null,"< >","Lens-Hazebrouck","Lens-Hazebrouck",2025,2025,23,30,null,null,null,null,"continuous","Maintenance","227 RVB Voie D Bully","2022-10-06","High",8,"Planned"]
["SNCF-R","R21846n",null,"< >","Arras-Lens","Arras-Lens",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","230 Régénération Poste EALE Bailleul Sir Berthoult","2022-10-06","High",null,"Planned"]
["SNCF-R","R24692c",null,"< >","Arras-Douai","Arras-Douai",2025,2025,26,33,null,null,null,null,"continuous","Maintenance","232.1 Gare d'Arras: RAV Brt 40 et 41 + RVB Voie K du 190,270 au 190,292 et du 190,320 au 190,340 - RAV Brt 208 + RVB Voie 9 du 191,820 au 192,360 (avec mise en LRS) + RAV Brt 126 + Simplif des Brt 131 et TO 2 +Voie SN/SL + 400 ml de RVB","2022-10-06","Major",8,"Planned"]
["SNCF-R","R24692c",null,"< >","Arras-Bif d'Agny\nArras-Bif de l'arbre Robert","Arras-Bif d'Agny\nArras-Bif de l'arbre Robert",2025,2025,26,33,null,null,null,null,"continuous","Maintenance","232.2 Gare d'Arras: RAV Brt 40 et 41 + RVB Voie K du 190,270 au 190,292 et du 190,320 au 190,340 - RAV Brt 208 + RVB Voie 9 du 191,820 au 192,360 (avec mise en LRS) + RAV Brt 126 + Simplif des Brt 131 et TO 2 +Voie SN/SL + 400 ml de RVB","2022-10-06","Major",8,"Planned"]
["SNCF-R","R24721y",null,"< >","Lens-Hazebrouck","Lens-Hazebrouck",2025,2025,24,31,null,null,null,null,"continuous","Maintenance","233 Gare de Béthune: RVB V5 du Pk 229+700 au 229+800 et du Pk 230+200 au 230+250 - RB/RR V5 du Pk 229+800 au 230+200 avec Rt partiel de 189 Tba - RVB Voie 3 du Pk 229+720 au 230+210 - RR Voie 3 du Pk 230+210 au 230+300","2022-10-06","High",8,"Planned"]
["SNCF-R","R24927g",null,"< >","Aulnoye-Hirson\n\n**","Aulnoye-Hirson\n\n**",2025,2025,22,31,null,null,null,null,"continuous","Maintenance","235 SR CAT Fives Hirson phase 2/6","2022-10-06","Major",10,"Planned"]
["SNCF-R","R25761a",null,"< >","Lille-Tourcoing","Lille-Tourcoing",2025,2025,17,31,null,null,null,null,"continuous","Maintenance","245.1 Fives Mouscron - Reliquats: RVB Voie 1 du 2,580 au 2,985 - RVB Voie M1/P1 du 0,000 au 0,500 (Becquerel) - RVB Voie M1/P1 du 1,300 au 2,100 - RVB Voies 1+2 suite RAV Bif Lion d'Op 2018 (2x100m)","2022-10-06","Major",15,"Planned"]
["SNCF-R","R25761a",null,"< >","Lille-Hazebrouck","Lille-Hazebrouck",2025,2025,17,31,null,null,null,null,"continuous","Maintenance","245.2 Fives Mouscron - Reliquats: RVB Voie 1 du 2,580 au 2,985 - RVB Voie M1/P1 du 0,000 au 0,500 (Becquerel) - RVB Voie M1/P1 du 1,300 au 2,100 - RVB Voies 1+2 suite RAV Bif Lion d'Op 2018 (2x100m)","2022-10-06","Major",15,"Planned"]
["SNCF-R","R29722s",null,"< >","Valenciennes-Aulnoye","Valenciennes-Aulnoye",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","257 Redécoupage de la zone Z562 - ligne 267000","2022-10-06","High",null,"Planned"]
["SNCF-R","R30473m",null,"< >","Creil-Longueau","Creil-Longueau",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","259.1 Remplacement FC 2025 IHP","2022-10-06",null,null,"Planned"]
["SNCF-R","R30473m",null,"< >","Longueau-Bif d'Agny exclue","Longueau-Bif d'Agny exclue",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","259.2 Remplacement FC 2025 IHP","2022-10-06",null,null,"Planned"]
["SNCF-R","R30473m",null,"< >","Longueau-Bif de l'arbre Robert exclue ","Longueau-Bif de l'arbre Robert exclue ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","259.3 Remplacement FC 2025 IHP","2022-10-06",null,null,"Planned"]
["SNCF-R",null,null,"< >","Hazebrouck-Dunkerque\n\n*","Hazebrouck-Dunkerque\n\n*",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","270 Meulage 2024 sur SA 2025","2022-10-06","High",null,"Planned"]
["SNCF-R","R25715j",null,"< >","Lille-Hazebrouck","Lille-Hazebrouck",2025,2025,7,16,null,null,null,null,"continuous","Maintenance","281 RRI  Nieppe Hazebrouck","2022-10-06","High",10,"Planned"]
["SNCF-R","R24718y",null,"< >","Hazebrouck-Dunkerque\n\n*","Hazebrouck-Dunkerque\n\n*",2025,2025,33,47,null,null,null,null,"periodical","Maintenance","286 Dunkerque RAV TJ10/11, RAV brt46b (incorpo?), RVB 115ml talon brt 31","2022-10-06","High",6,"Planned"]
["SNCF-R",null,null,"< >","Hazebrouck-Dunkerque\n\n*","Hazebrouck-Dunkerque\n\n*",2025,2025,15,48,null,null,null,null,"periodical","Maintenance","293 - Maintenance Hazebrouck Dunkerque ","2022-10-06","High",8,"Planned"]
["SNCF-R","R05089l",null,"< >","Lille-Valenciennes","Lille-Valenciennes",2025,2025,7,10,null,null,null,null,"continuous","Maintenance","306 - PRO CNV contournement Nord Valenciennes PK 42,673 ","2022-10-06","High",4,"Planned"]
["SNCF-R",null,null,"< >","Aulnoye-Hirson\n\n**","Aulnoye-Hirson\n\n**",2025,2025,24,30,null,null,null,null,"continuous","Maintenance","317- suppression du PN95 à Avesnelles","2022-10-06","High",7,"Planned"]
["SNCF-R","?",null,"< >","Longueau-Bif de l'arbre Robert exclue ","Longueau-Bif de l'arbre Robert exclue ",2025,2025,15,18,null,null,null,null,"continuous","Maintenance","336 - OGE Etanchéité PRA","2022-10-06","High",4,"Planned"]
["SNCF-R","R18871b",null,"< >","St clair-Ambérieu ","St clair-Ambérieu ",2025,2025,null,null,null,null,null,null,"continuous","Maintenance","101 Création Sous Station de Miribel dans le cadre de la convention robustesse","2022-10-06","High",null,"Planned"]
["SNCF-R","?",null,"< >","Tergnier-StQuentin","Tergnier-StQuentin",2025,2025,21,25,null,null,null,null,"continuous","Maintenance","335.1 - OGE Etancheite PRA","2022-10-06","High",5,"Planned"]
["SNCF-R","13673380261",null,"< >","Noisy-le-Sec - Bif Impaire O","Noisy-le-Sec - Bât Voyageurs",2024,2024,14,37,"2024-04-01","12:00:00","2024-09-13","15:00:00","Periodical",null,"De ZEP 770 à ZEP 776 2B4/2EO + ZEP 782 2B1 Reconduction DETC20_02242   ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15002468261",null,"< >","Bondy - Bât Voyageurs","Bondy - Bât Voyageurs",2024,2024,10,12,"2024-03-08","23:30:00","2024-03-18","04:30:00","Periodical",null,"Zone 2               ",null,"High","1,5,6,7","Planned"]
["SNCF-R","14998835161",null,"< >","Bondy - Bât Voyageurs","Bondy - Bât Voyageurs",2024,2024,8,13,"2024-02-20","23:00:00","2024-03-28","05:00:00","Periodical",null,"Zone 2              ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13997810061",null,"< >","Bondy - Bât Voyageurs","Bondy - Bât Voyageurs",2024,2024,8,13,"2024-02-20","23:00:00","2024-03-28","05:00:00","Periodical",null,"Zone 1  ZEP 610+776+774+772+770+782+780+736  ZEP 620+784+788+786  ZEP 810+812                  ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15002437261",null,"< >","Bondy - Bât Voyageurs","Bondy - Bât Voyageurs",2024,2024,10,12,"2024-03-08","23:30:00","2024-03-18","04:30:00","Periodical",null,"Zone 1                   ",null,"High","1,5,6,7","Planned"]
["SNCF-R","13673378661",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,24,24,"2024-06-10","10:00:00","2024-06-14","15:00:00","Periodical",null,"Schéma 18 ZEP 627+751+753   ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-02-12","23:30:00","2024-05-16","04:30:00","Periodical",null,"Toutes ZEP CHL     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673379461",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,15,15,"2024-04-08","10:00:00","2024-04-12","15:00:00","Periodical",null,"Schéma 19 De ZEP 633 à ZEP 775 1B1   ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15070155261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,18,18,"2024-04-29","22:30:00","2024-05-02","04:30:00","Periodical",null,"Toutes ZEP CHL     ",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-03-25","23:30:00","2024-03-28","04:30:00","Periodical",null,"Toutes ZEP CHL     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-12","04:30:00","Periodical",null,"Toutes ZEP CHL     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13797360761",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,30,36,"2024-07-22","01:30:00","2024-09-06","04:30:00","Periodical",null,"Toutes ZEP CHL     ",null,"High","2,3,4,5,6","Planned"]
["SNCF-R","13673388861",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,3,17,"2024-01-15","23:00:00","2024-04-25","04:30:00","Periodical",null,"Toutes ZEP CHL     ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14998706761",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,6,13,"2024-02-05","23:00:00","2024-03-28","05:00:00","Periodical",null,"Voie 1B4+1L1+1B1 zone 2   Zone 2535a sur ZEP 633 libre pour circulation sur aig 2535a vers 2535b       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15002413361",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,7,9,"2024-02-16","23:30:00","2024-02-26","04:30:00","Periodical",null,"Voie 1B4+1L1+1B1 zone 2   Zone 2535a sur ZEP 633 libre pour circulation sur aig 2535a vers 2535b       ",null,"High","1,5,6,7","Planned"]
["SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-01-01","23:30:00","2024-10-11","04:30:00","Periodical",null,"Toutes ZEP CHL     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-01-01","23:30:00","2024-11-21","04:30:00","Periodical",null,"Toutes ZEP CHL     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-05-13","23:30:00","2024-12-06","04:30:00","Periodical",null,"Toutes ZEP CHL     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13836398261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,48,"2023-12-17","23:50:00","2024-12-01","04:40:00","Periodical",null,"Toutes ZEP CHL     ",null,"Major","7","Planned"]
["SNCF-R","13836363461",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2023-12-16","23:15:00","2024-12-14","05:15:00","Periodical",null,"Toutes ZEP CHL     ",null,"Major","6","Planned"]
["SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-01-05","23:30:00","2024-12-13","04:30:00","Periodical",null,"Toutes ZEP CHL     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673386061",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,38,38,"2024-09-21","12:16:00","2024-09-21","12:16:00","Periodical",null,"DFV sur ZEP type G ensemble des ZEP du poste CHL et les ZEP encadrantes de chaque poste Ligne 1 jusqu´avant les quais de Gagny Ligne 4 jusqu´avant les quais de Nogent         ",null,"Medium","6,7","Planned"]
["SNCF-R","13673387461",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,17,17,"2024-04-27","20:00:00","2024-04-27","08:00:00","Periodical",null,"DFV sur ZEP type G ensemble des ZEP du poste CHL et les ZEP encadrantes de chaque poste Ligne 1 jusqu´avant les quais de Gagny Ligne 4 jusqu´avant les quais de Nogent         ",null,"Medium","6","Planned"]
["SNCF-R","13673341061",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,15,15,"2024-04-08","13:30:00","2024-04-12","15:15:00","Periodical",null,"1TER : ZEP 789 CHL  Sans impact",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13673326261",null,"< >","Bondy - Bât Voyageurs","Le Raincy-Villemomble-Montferm",2024,2024,40,40,"2024-09-30","12:50:00","2024-10-02","14:48:00","Periodical",null,"2L1 : ZEP 742,744 CHL (aig. 2660a,2664b,2745a)   ",null,"Medium","1,2,3","Planned"]
["SNCF-R","13673325461",null,"< >","Bondy - Bât Voyageurs","Le Raincy-Villemomble-Montferm",2024,2024,40,40,"2024-10-03","11:09:00","2024-10-04","12:57:00","Periodical",null,"1L1 : ZEP 761 CHL (aig. 2743b,2745b) ",null,"Medium","4,5","Planned"]
["SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2024-04-15","23:30:00","2024-04-19","04:45:00","Periodical",null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2024-03-04","23:30:00","2024-03-08","04:45:00","Periodical",null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2024-02-12","23:30:00","2024-10-10","04:45:00","Periodical",null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15304959061",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,40,40,"2024-09-30","22:30:00","2024-10-02","04:30:00","Periodical",null,"Ombre de la DEF MEGA ZEP                       ",null,"Medium","1,3","Planned"]
["SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-12","04:45:00","Periodical",null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2024-03-11","23:30:00","2024-05-03","04:45:00","Periodical",null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14000040161",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,16,16,"2024-04-19","23:30:00","2024-04-21","16:40:00","Periodical",null,"TOUT VAIRES P5   Restitution 16h40 pour TER 839165 acté en Conciliation N°3 Désaccords RP0 2024",null,"Medium","5,6,7","Planned"]
["SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-13","04:45:00","Periodical",null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15358183661",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Aig V2Bis/V2Ter",2024,2024,40,40,"2024-10-03","22:30:00","2024-10-03","04:30:00","Periodical",null,"6h                       ",null,"Medium","4","Planned"]
["SNCF-R","13673398061",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Aig V2Bis/V2Ter",2024,2024,8,8,"2024-02-19","13:40:00","2024-02-19","16:00:00","Periodical",null,"2TER : ZEP 1732,1736 GN (aig. 2905b,2913a)           ",null,"Medium","1","Planned"]
["SNCF-R","13673317561",null,"< >","Noisy-le-Sec - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,28,36,"2024-07-08","01:20:00","2024-09-08","04:25:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13673322561",null,"< >","Noisy-le-Sec - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,8,50,"2024-02-19","01:14:00","2024-12-09","04:23:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13673320961",null,"< >","Noisy-le-Sec - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,8,50,"2024-02-19","01:10:00","2024-12-09","04:17:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13673318361",null,"< >","Noisy-le-Sec - Bif Impaire O","Gagny - Aig V2Bis/V2Ter",2024,2024,28,36,"2024-07-08","01:30:00","2024-09-08","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","15358105961",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2024,2024,40,40,"2024-10-01","22:35:00","2024-10-01","04:35:00","Periodical",null,"",null,"Medium","2","Planned"]
["SNCF-R","14119814861",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2024,2024,15,16,"2024-04-08","08:00:00","2024-04-21","17:00:00","continuous",null,"",null,"High","","Planned"]
["SNCF-R","13673398861",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2024,2024,11,40,"2024-03-11","22:55:00","2024-05-03","04:55:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673398861",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2024,2024,11,40,"2024-04-22","22:55:00","2024-10-06","04:55:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673319361",null,"< >","Noisy-le-Sec - Bif Impaire O","Gagny - Bât Voyageurs",2024,2024,28,36,"2024-07-08","01:00:00","2024-09-08","03:55:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13673320161",null,"< >","Noisy-le-Sec - Bif Impaire O","Gagny - Bât Voyageurs",2024,2024,8,50,"2024-02-19","01:07:00","2024-12-09","04:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13673321761",null,"< >","Noisy-le-Sec - Bif Impaire O","Gagny - Bât Voyageurs",2024,2024,8,50,"2024-02-19","01:10:00","2024-12-09","04:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","14484681361",null,"< >","Meaux - Aig Km 41,7-Ã‰v","Meaux - Bât Voyageurs",2024,2024,42,50,"2024-10-14","08:00:00","2024-12-14","04:00:00","continuous",null,"",null,"Major","","Planned"]
["SNCF-R","13673407261",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,40,50,"2024-09-30","23:10:00","2024-12-13","04:10:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673408861",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,46,48,"2024-11-15","23:10:00","2024-11-25","04:10:00","Periodical",null,"",null,"High","1,5,6,7","Planned"]
["SNCF-R","13884886761",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,48,48,"2024-11-29","23:10:00","2024-12-01","16:00:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","13872234161",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,45,46,"2024-11-08","23:10:00","2024-11-11","16:00:00","Periodical",null,"",null,"Medium","1,5,6,7","Planned"]
["SNCF-R","15733405461",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,43,43,"2024-10-27","21:30:00","2024-10-27","04:10:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","15614938461",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,44,45,"2024-10-31","23:10:00","2024-11-04","04:10:00","Periodical",null,"",null,"Medium","1,4,5,6,7","Planned"]
["SNCF-R","15733367261",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,43,43,"2024-10-25","23:10:00","2024-10-27","18:00:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","13673432661",null,"< >","Vaires-Torcy - Aig Km 21,0","Vaires-Torcy - Bât Voyageurs",2024,2024,5,27,"2024-02-01","12:40:00","2024-07-05","15:00:00","Periodical",null,"2B1/2A2 : ZEP 1336 VAI (aig. 3314a,3314b)     ",null,"Medium","4,5","Planned"]
["SNCF-R","13673431861",null,"< >","Vaires-Torcy - Poste 4","Vaires-Torcy - Bât Voyageurs",2024,2024,5,5,"2024-01-30","14:00:00","2024-01-30","15:20:00","Periodical",null,"2B1/2A4 : ZEP 1334 VAI (aig. 3320)   ",null,"Medium","2","Planned"]
["SNCF-R","13673435361",null,"< >","Vaires-Torcy - Bât Voyageurs","Vaires-Torcy - ITE EDF",2024,2024,5,5,"2024-01-30","11:00:00","2024-01-30","12:15:00","Periodical",null,"1B1 : ZEP 1333 EDF (aig. 3365a)           ",null,"Medium","2","Planned"]
["SNCF-R","13673436161",null,"< >","Vaires-Torcy - Bât Voyageurs","Lagny-Thorigny",2024,2024,27,27,"2024-07-04","13:37:00","2024-07-05","15:02:00","Periodical",null,"2B1 : ZEP 1330 VAI (aig. 4E2)       ",null,"Medium","4,5","Planned"]
["SNCF-R","13673438361",null,"< >","Vaires-Torcy - Bât Voyageurs","Lagny-Thorigny",2024,2024,27,27,"2024-07-03","09:30:00","2024-07-03","11:51:00","Periodical",null,"1B1 : ZEP 1333 EDF (aig. 3365a+3365b)       ",null,"Medium","3","Planned"]
["SNCF-R","13673434561",null,"< >","Vaires-Torcy - ITE EDF","Lagny-Thorigny",2024,2024,5,27,"2024-01-30","09:10:00","2024-07-04","10:30:00","Periodical",null,"1L1 : ZEP 1111 LGY (aig. 3915a)         ",null,"Medium","2,4","Planned"]
["SNCF-R","13673433761",null,"< >","Vaires-Torcy - Poste 4","Lagny-Thorigny",2024,2024,5,5,"2024-01-31","13:00:00","2024-01-31","15:20:00","Periodical",null,"2B1 : ZEP 1330+1332+1350 EDF (aig. 2E1,4E2)         ",null,"Medium","3","Planned"]
["SNCF-R","13673368261",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-10-22","23:55:00","2024-10-25","04:55:00","Periodical",null,"Ombre générique Lagny Meaux ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673369061",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-10-22","23:35:00","2024-10-25","04:10:00","Periodical",null,"Ombre fenêtrre generique Lagny Meaux ZEP 1106+1104 Vaires 5VP SEL 24 SSr Pomponne Dampmart V2",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673368261",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-02-26","23:55:00","2024-10-10","04:55:00","Periodical",null,"Ombre générique Lagny Meaux ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673369061",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-02-26","23:35:00","2024-10-10","04:10:00","Periodical",null,"Ombre fenêtrre generique Lagny Meaux ZEP 1106+1104 Vaires 5VP SEL 24 SSr Pomponne Dampmart V2",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673371061",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,5,27,"2024-01-29","09:30:00","2024-07-02","12:30:00","Periodical",null,"1B1 : ZEP 1209 (1103 + 1141 + 1143) LGY (aig. 3915b,3923a)     ",null,"Medium","1,2","Planned"]
["SNCF-R","13673369061",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-05-20","23:35:00","2024-10-20","04:10:00","Periodical",null,"Ombre fenêtrre generique Lagny Meaux ZEP 1106+1104 Vaires 5VP SEL 24 SSr Pomponne Dampmart V2",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673368261",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-05-20","23:55:00","2024-10-20","04:55:00","Periodical",null,"Ombre générique Lagny Meaux ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673368261",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-03-19","23:55:00","2024-03-22","04:55:00","Periodical",null,"Ombre générique Lagny Meaux ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673369061",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-03-19","23:35:00","2024-03-22","04:10:00","Periodical",null,"Ombre fenêtrre generique Lagny Meaux ZEP 1106+1104 Vaires 5VP SEL 24 SSr Pomponne Dampmart V2",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673422261",null,"< >","Vaires-Torcy - Aig Km 21,0","Lagny-Thorigny - Tiroir 3",2024,2024,35,35,"2024-08-27","00:45:00","2024-08-31","05:00:00","Periodical",null,"",null,"Medium","2,3,4,5,6","Planned"]
["SNCF-R","13673436961",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,50,50,"2024-02-19","23:30:00","2024-02-23","04:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673423061",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,35,35,"2024-08-26","22:50:00","2024-08-30","04:25:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13673423861",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,35,35,"2024-08-27","01:18:00","2024-08-31","05:48:00","Periodical",null,"",null,"Medium","2,3,4,5,6","Planned"]
["SNCF-R","13673421461",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,35,35,"2024-08-26","22:45:00","2024-08-30","04:20:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13673436961",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,50,50,"2024-10-22","23:30:00","2024-10-31","04:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673436961",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,50,50,"2024-02-12","23:30:00","2024-10-10","04:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673436961",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,50,50,"2024-03-19","23:30:00","2024-09-13","04:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673436961",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,50,50,"2024-03-11","23:30:00","2024-05-03","04:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14000076761",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,16,16,"2024-04-19","23:30:00","2024-04-21","16:40:00","Periodical",null,"TOUT VAIRES P5   Restitution 16h40 pour TER 839165 acté en Conciliation N°3 Désaccords RP0 2024",null,"Medium","5,6,7","Planned"]
["SNCF-R","13673431061",null,"< >","Vaires-Torcy - ITE EDF","Lagny-Thorigny - Tiroir 3",2024,2024,5,27,"2024-01-29","09:30:00","2024-07-02","12:30:00","Periodical",null,"1B1 : ZEP 1209 (1103 + 1141 + 1143) LGY (aig. 3915b,3923a)   ",null,"Medium","1,2","Planned"]
["SNCF-R","13673370061",null,"< >","Lagny-Thorigny","Esbly",2024,2024,5,5,"2024-01-29","14:00:00","2024-01-29","15:15:00","Periodical",null,"3+T3 : ZEP 1205 (1143 + 1145 + 1147) LGY (aig. 3944b)     ",null,"Medium","1","Planned"]
["SNCF-R","14724329261",null,"< >","Lagny-Thorigny","Esbly",2024,2024,41,41,"2024-10-10","22:35:00","2024-10-11","04:35:00","Periodical",null,"",null,"Medium","4,5","Planned"]
["SNCF-R","15050524861",null,"< >","Lagny-Thorigny","Esbly",2024,2024,43,43,"2024-10-25","23:30:00","2024-10-27","18:00:00","Periodical",null,"WE de Maintenance type CASTOR  Aligné sur CHA19_0026052 RAV Meaux    ",null,"Medium","5,6,7","Planned"]
["SNCF-R","13673371861",null,"< >","Lagny-Thorigny","Esbly",2024,2024,48,48,"2024-11-25","23:30:00","2024-11-29","04:30:00","Periodical",null,"Ombre Mega ZEP ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1 ZEP 1106+1104 Vaires 5VP SEL 24 SSr Pomponne Dampmart V2     ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14610328761",null,"< >","Lagny-Thorigny","Esbly",2024,2024,16,16,"2024-04-19","23:30:00","2024-04-21","16:40:00","Periodical",null,"TOUT VAIRES P5  Restitution 16h40 pour TER 839165 acté en Conciliation N°3 Désaccords RP0 2024",null,"Medium","5,6,7","Planned"]
["SNCF-R","13673365461",null,"< >","Trilport - Bât Voyageurs","Trilport - Bif de Germigny",2024,2024,5,45,"2024-01-29","13:31:00","2024-11-10","14:16:00","Periodical",null,"Tournée M03 - Courbe de Trilport ZEP 205 V1 TO 117275 / TF 117133 ZEP 205 V1 ",null,"Medium","2","Planned"]
["SNCF-R","13673363061",null,"< >","Meaux - Bât Voyageurs","Trilport - Bât Voyageurs",2024,2024,4,44,"2024-01-22","13:24:00","2024-11-03","14:17:00","Periodical",null,"Tournée M02 - Courbe Saint Faron ZEP MT01",null,"Medium","2","Planned"]
["SNCF-R","13673363861",null,"< >","Meaux - Bât Voyageurs","Trilport - Bât Voyageurs",2024,2024,4,44,"2024-01-22","13:45:00","2024-11-03","14:25:00","Periodical",null,"Tournée M02 - Courbe Saint Faron ZEP TM 04  Train fermant 117278 Passage Trilport 14h30  ",null,"Medium","2","Planned"]
["SNCF-R","15029512061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,2,9,"2024-01-08","23:40:00","2024-03-01","04:40:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14754152461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,1,"2023-12-11","22:40:00","2024-01-05","04:40:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15700763161",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,1,1,"2024-01-01","23:30:00","2024-01-01","04:40:00","Periodical",null,"Variante réduite JF pour TER",null,"Medium","1","Planned"]
["SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-03-25","23:10:00","2024-09-06","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-03-25","23:10:00","2024-09-06","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-07-01","23:10:00","2024-11-10","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-07-01","23:10:00","2024-11-10","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-05-27","23:10:00","2024-05-31","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-05-27","23:10:00","2024-05-31","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-02-27","23:10:00","2024-03-08","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-02-27","23:10:00","2024-03-08","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13872239561",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,45,46,"2024-11-08","23:10:00","2024-11-11","16:00:00","Periodical",null,"",null,"Medium","1,5,6,7","Planned"]
["SNCF-R","14484765361",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,40,50,"2024-09-30","23:10:00","2024-12-13","04:10:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673366261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,46,48,"2024-11-15","23:10:00","2024-11-25","04:10:00","Periodical",null,"",null,"High","1,5,6,7","Planned"]
["SNCF-R","13884889461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,48,48,"2024-11-29","23:10:00","2024-12-01","16:00:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","15614946061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,44,45,"2024-10-31","23:10:00","2024-11-04","04:10:00","Periodical",null,"",null,"Medium","1,4,5,6,7","Planned"]
["SNCF-R","15733370361",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,43,43,"2024-10-25","23:10:00","2024-10-27","18:00:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","15733412561",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,43,43,"2024-10-27","21:30:00","2024-10-27","04:10:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","13673359661",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,50,"2023-12-11","13:43:00","2024-12-13","14:27:00","Periodical",null,"Train ouvrant: 117144  Train fermant: 117278",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673358861",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,50,"2023-12-11","09:23:00","2024-12-13","10:20:00","Periodical",null,"Train ouvrant: 117267  Trin fermant: 117117",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-03-04","23:10:00","2024-10-20","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673360461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,50,"2023-12-11","00:40:00","2024-12-09","03:32:00","Periodical",null,"",null,"Major","1","Planned"]
["SNCF-R","13673361261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,50,"2023-12-11","00:31:00","2024-12-09","03:39:00","Periodical",null,"03/02/2023 : DECC24_00077 pour circulation sillon JO.",null,"Major","1","Planned"]
["SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-03-04","23:10:00","2024-10-20","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14716575461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,37,42,"2024-10-14","23:10:00","2024-10-15","05:00:00","Periodical",null,"TO 795631",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14716575461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,37,42,"2024-09-09","23:10:00","2024-09-18","05:00:00","Periodical",null,"TO 795631",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-04-22","23:10:00","2024-04-26","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-04-22","23:10:00","2024-04-26","04:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15029512061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,2,9,"2024-01-08","23:40:00","2024-01-26","04:40:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14754152461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,1,"2024-01-01","22:40:00","2024-01-05","04:40:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14754070361",null,"< >","Trilport - ITE CCI de Meau","Trilport - Aig Év Germigny",2024,2024,6,6,"2024-02-05","21:40:00","2024-02-09","04:40:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13673364661",null,"< >","Trilport - ITE CCI de Meau","Trilport - Aig Év Germigny",2024,2024,5,45,"2024-01-29","13:40:00","2024-11-10","14:24:00","Periodical",null,"Tournée M03 - Courbe de Trilport ZEP 33002 (202+204+206+208+210+212+214+216) V2 TO 117144 / TF 117278   ",null,"Medium","2","Planned"]
["SNCF-R","13672978261",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Troyes - Aig OE-Preize",2024,2024,5,41,"2024-01-30","00:15:00","2024-04-20","05:13:00","Periodical",null,"Fenêtre Courte                                                                     ",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13672978261",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Troyes - Aig OE-Preize",2024,2024,5,41,"2024-03-12","00:15:00","2024-10-12","05:13:00","Periodical",null,"Fenêtre Courte                                                                     ",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13672979261",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Troyes - Aig OE-Preize",2024,2024,15,24,"2024-04-08","00:00:00","2024-06-10","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13672978261",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Troyes - Aig OE-Preize",2024,2024,5,41,"2024-02-13","00:15:00","2024-02-24","05:13:00","Periodical",null,"Fenêtre Courte                                                                     ",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13672977461",null,"< >","Romilly-sur-Seine - Bât Voyageurs","Troyes - Aig Ouest-V C",2024,2024,50,50,"2023-12-11","12:40:00","2024-12-13","13:25:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13672975061",null,"< >","Romilly-sur-Seine - Bât Voyageurs","Troyes - Aig Ouest-V C",2024,2024,50,50,"2023-12-11","11:12:00","2024-12-13","12:28:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13672976661",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Troyes - FSC St-Luc",2024,2024,15,24,"2024-04-08","01:30:00","2024-06-10","06:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13672975861",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Romilly-sur-Seine - Bât Voyageurs",2024,2024,50,49,"2023-12-11","12:57:00","2024-12-06","13:40:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13672980061",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Romilly-sur-Seine - Bât Voyageurs",2024,2024,50,49,"2023-12-11","10:54:00","2024-12-06","12:12:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14462280261",null,"< >","Thionville - Bif L3/L7","Thionville - Bât Voyageurs",2024,2024,35,35,"2024-08-27","10:00:00","2024-08-28","11:30:00","Periodical",null,"Essais ETCS_C1 - Cap 1h30 jour, zep 854, Voie 2M",null,"Medium","2","Planned"]
["SNCF-R","15120760061",null,"< >","Thionville - Bât Voyageurs","Thionville - ITE EDF/Catteno",2024,2024,23,24,"2024-06-03","23:45:00","2024-06-14","05:25:00","Periodical",null," Cap 5h40, 1L3+2L3 coté Nord, Accès FLUX interdit, Avec 4F_THL-ZOU_001 et _002.     ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14462099361",null,"< >","Thionville - FSC Luxembourg","Thionville - ITE EDF/Catteno",2024,2024,31,31,"2024-08-02","10:15:00","2024-08-03","11:45:00","Periodical",null,"Essais ETCS_C1 - Cap 1h30 jour, zep 932, Voie 2L3",null,"Medium","5","Planned"]
["SNCF-R","15050429661",null,"< >","Thionville - ITE EDF/Catteno","Thionville - ITE EDF/Catteno",2024,2024,27,27,"2024-07-07","00:10:00","2024-07-08","04:40:00","Periodical",null,"PTE Thionville Nord - TT Domaine revendiqué: Ssr Thionville-Yutz + Feeder R du Ssr Thionville côté P1 + Ssr Thionville côté BV (simultanée)  V1B+V2B+A+B+C+D+1Bis+2bis+M interdites. Accès L177,178,180N interdit. FLUX interdit.",null,"Medium","7","Planned"]
["SNCF-R","14132220461",null,"< >","Thionville - ITE EDF/Catteno","Thionville - ITE EDF/Catteno",2024,2024,27,27,"2024-07-07","23:45:00","2024-07-08","04:15:00","Periodical",null,"PTE Thionville Nord - TT Domaine revendiqué: Ssr Thionville-Yutz + Feeder R du Ssr Thionville côté P1 + Ssr Thionville côté BV (simultanée)  V1B+V2B+A+B+C+D+1Bis+2bis+M interdites. Accès L177,178,180N interdit. FLUX interdit.",null,"Medium","7","Planned"]
["SNCF-R","15121565761",null,"< >","Thionville - ITE EDF/Catteno","Thionville - ITE EDF/Catteno",2024,2024,35,36,"2024-08-27","00:10:00","2024-09-07","03:40:00","Periodical",null,"Cap 3h30 nuit, 1L3+2L3+1L7.3+2L7.3+1L37.7+2L37.7+1Bis+2Bis+M+FAE+FLUX+DP accès Nord + B,C,D,E,F,1M,2M coté Nord. Avec 4D_THL-ZOU_010 , 4D_THL-HGT_019 et 4D_THL-AP_025.       ",null,"High","2,3,4,5,6","Planned"]
["SNCF-R","14132538861",null,"< >","Thionville - Jonctions Nord","Thionville - ITE EDF/Catteno",2024,2024,20,22,"2024-05-13","23:55:00","2024-05-31","05:15:00","Periodical",null,"Sél 47+48+49+50+51+52 du SSr Thionville côté BV. Accès L180N de/vers Bettembourg interdit. FLUX inacessible.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14135869261",null,"< >","Thionville - Jonctions Nord","Thionville - ITE EDF/Catteno",2024,2024,10,10,"2024-03-04","23:45:00","2024-03-08","05:45:00","Periodical",null,"Cap 6h nuit, 1L3+2L3+1L37,7+2L37,7+1L7,3+2L7,3+1Bis+2Bis+M+Accès FAE Nord+Accès FLUX Nord. Accès L177,178,180N interdit.",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13675990061",null,"< >","Ebange - Faisceau","Thionville - FSC Luxembourg",2024,2024,44,44,"2024-11-02","08:00:00","2024-11-03","15:00:00","Periodical",null,"Cap 7h SA, V1B+V2B. Accès Ebange AN interdit. Report des circulations sur V1/V2 entre THL et UCK. Voies A+B+C interdites.",null,"Medium","6","Planned"]
["SNCF-R","14457938661",null,"< >","Thionville - Bât Voyageurs","Thionville - FSC Luxembourg",2024,2024,17,17,"2024-04-22","10:00:00","2024-04-23","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 895, Voie C",null,"Medium","1","Planned"]
["SNCF-R","14457794361",null,"< >","Thionville - Bât Voyageurs","Thionville - FSC Luxembourg",2024,2024,16,16,"2024-04-19","10:00:00","2024-04-20","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 896, Voie B",null,"Medium","5","Planned"]
["SNCF-R","14457962261",null,"< >","Thionville - Bât Voyageurs","Thionville - FSC Luxembourg",2024,2024,17,17,"2024-04-23","10:00:00","2024-04-24","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 893, Voie D",null,"Medium","2","Planned"]
["SNCF-R","14461812861",null,"< >","Thionville - Bât Voyageurs","Thionville - FSC Luxembourg",2024,2024,29,29,"2024-07-15","10:00:00","2024-07-16","11:20:00","Periodical",null,"Essais ETCS_C1 - Cap 1h20 jour, zep 895+897, Voie 1L3+2L3/C",null,"Medium","1","Planned"]
["SNCF-R","14132586861",null,"< >","Thionville - FSC Luxembourg","Thionville - FSC Luxembourg",2024,2024,25,25,"2024-06-17","23:40:00","2024-06-21","05:25:00","Periodical",null,"Sél 44+46+48+56+58 du SSr Thionville côté BV. Voie C+D interdites. Accès L180N restreint.",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15120971561",null,"< >","Thionville - FSC Luxembourg","Thionville - FSC Luxembourg",2024,2024,25,28,"2024-06-17","10:30:00","2024-07-12","14:30:00","Periodical",null,"Cap 4h jour, 1Bis+2Bis+M+FAE+DP accès Nord + D,E,F,1M,2M coté Nord.Avec 4D_THL-HGT_018 et 4D_THL-AP_024.       ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14461678761",null,"< >","Thionville - FSC Luxembourg","Thionville - FSC Luxembourg",2024,2024,28,28,"2024-07-10","10:00:00","2024-07-12","11:55:00","Periodical",null,"Essais ETCS_C1 - Cap 1h55 jour, zep 942, Voie 2L3",null,"Medium","3,5","Planned"]
["SNCF-R","14549694761",null,"< >","Ebange - Faisceau","Thionville - Bif L3/L7",2024,2024,8,8,"2024-02-20","11:30:00","2024-02-23","15:30:00","Periodical",null,"Cap 4h jour, V1+V2 à Thionville, MA à VE. Avec 4F_UCK-THL_001, 4F_UCK-THL_002 et 4D_UCK_034 qui reprend les conséquences circulations. (zep 811,803,801,802)",null,"Medium","2,3,4,5","Planned"]
["SNCF-R","14549526361",null,"< >","Ebange - Faisceau","Thionville - Bif L3/L7",2024,2024,8,8,"2024-02-19","09:30:00","2024-02-20","15:30:00","Periodical",null,"Cap 6h jour, V1+V2 à Thionville, LU. Avec 4F_UCK-THL_005, 4F_UCK-THL_006 et 4D_UCK_033 qui reprend les conséquences circulations. (zep 811,803,801,802)",null,"Medium","1","Planned"]
["SNCF-R","14457677361",null,"< >","Ebange - Jonction Nord","Thionville - Bif L3/L7",2024,2024,16,16,"2024-04-16","10:00:00","2024-04-17","12:00:00","Periodical",null,"Essais ETCS_C2 - Cap 2h jour, zep 811+814, Voies 1+2B",null,"Medium","2","Planned"]
["SNCF-R","13676085461",null,"< >","Thionville - Bât Voyageurs","Thionville - Ac Nord FSC Lux",2024,2024,32,35,"2024-08-05","08:00:00","2024-08-30","14:00:00","Periodical",null,"Cap 6h, Faisceau Luxembourg Thionville (V15 à 29). DP S9C: zep 913,915,917,919,921,923,925,927,929,905,902. DP S11: Sél 340,315,317,319,321,323,325,327,329,330 du SSr Thionville Faisceau Luxembourg.   ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14132577061",null,"< >","Thionville - Bif L3/L7","Thionville - Ac Nord FSC Lux",2024,2024,23,24,"2024-06-03","23:40:00","2024-06-14","05:25:00","Periodical",null,"Sél 44+46+47+145+147 du SSr Thionville côté BV. B+C interdites. Accès L180N de/vers Bettembourg interdit. FLUX inacessible.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14461796661",null,"< >","Thionville - FSC Luxembourg","Thionville - Ac Nord FSC Lux",2024,2024,28,28,"2024-07-11","09:30:00","2024-07-12","11:20:00","Periodical",null,"Essais ETCS_C1 - Cap 1h50 jour, zep 941, Voie 1L3",null,"Medium","4","Planned"]
["SNCF-R","14462305561",null,"< >","Thionville - Jonctions Nord","Thionville - Ac Nord FSC Lux",2024,2024,35,35,"2024-08-29","10:00:00","2024-08-30","12:00:00","Periodical",null,"Essais ETCS_C1 - Cap 2h jour, zep 905+913, FLUX",null,"Medium","4,5","Planned"]
["SNCF-R","14457838361",null,"< >","Ebange - Accès Sud","Ebange - Aig VL90",2024,2024,16,16,"2024-04-17","10:00:00","2024-04-18","11:30:00","Periodical",null,"Essais ETCS_C2 - Déf 1h30 jour, zep 156 d'Uckange, V2B",null,"Medium","3","Planned"]
["SNCF-R","13676550061",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,4,42,"2024-01-22","09:30:00","2024-10-14","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                       ",null,"Medium","1","Planned"]
["SNCF-R","13676553561",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,50,50,"2023-12-11","09:09:00","2024-12-13","10:07:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676546061",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,4,42,"2024-01-23","11:30:00","2024-10-18","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                             ",null,"High","2,3,4,5","Planned"]
["SNCF-R","13676554361",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,50,50,"2023-12-11","11:37:00","2024-12-13","12:44:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676546861",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,8,46,"2024-02-20","11:30:00","2024-11-15","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)         ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676546861",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,8,46,"2024-02-20","11:30:00","2024-02-23","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)         ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676547661",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,8,45,"2024-02-19","09:30:00","2024-11-04","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                               ",null,"Medium","1","Planned"]
["SNCF-R","13676547661",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,8,45,"2024-02-19","09:30:00","2024-02-19","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                               ",null,"Medium","1","Planned"]
["SNCF-R","14458025261",null,"< >","Ebange - Aig VL90","Ebange - Accès Nord",2024,2024,22,22,"2024-05-27","10:00:00","2024-05-28","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 802, Voie 2",null,"Medium","1","Planned"]
["SNCF-R","14000156161",null,"< >","Ebange - Faisceau","Ebange - Accès Nord",2024,2024,6,6,"2024-02-07","11:30:00","2024-02-08","15:30:00","Periodical",null,"Cap V1B+V2B Thionville. Avec 4D_UCK-THL_005.       ",null,"Medium","3,4","Planned"]
["SNCF-R","14000107561",null,"< >","Ebange - Faisceau","Ebange - Accès Nord",2024,2024,6,6,"2024-02-05","11:30:00","2024-02-06","15:30:00","Periodical",null,"Cap V1+V2 Thionville. Avec 4D_UCK-THL_005.       ",null,"Medium","1,2","Planned"]
["SNCF-R","14131497161",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,10,15,"2024-03-10","23:50:00","2024-04-14","03:20:00","Periodical",null,"Avec 4C_THL_100 qui reprend les conséquences circulations.",null,"Medium","7","Planned"]
["SNCF-R","13676573761",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,8,45,"2024-02-19","09:30:00","2024-11-04","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                             ",null,"Medium","1","Planned"]
["SNCF-R","13676577761",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,50,50,"2023-12-11","09:10:00","2024-12-13","10:08:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676579361",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,50,50,"2023-12-11","13:50:00","2024-12-13","14:52:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676580161",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,6,50,"2024-02-05","00:00:00","2024-12-09","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13676576161",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,50,50,"2023-12-11","11:35:00","2024-12-13","12:38:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676575361",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,8,45,"2024-02-19","09:30:00","2024-11-04","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)         ",null,"Medium","1","Planned"]
["SNCF-R","14925047961",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,4,42,"2024-01-23","11:30:00","2024-10-18","15:30:00","Periodical",null,"V1B+V2B à Uckange, MA ME JE VE. Avec 4F_UCK-THL_003 et 4F_UCK-THL_004.  Ne pas activer la Déf quand générique activée sur la L204000 (LGN-THL)                       ",null,"High","2,3,4,5","Planned"]
["SNCF-R","14924978961",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,8,46,"2024-02-20","11:30:00","2024-11-15","15:30:00","Periodical",null,"V1+V2 à Uckange, MA ME JE VE. Accès Faisceau Uckange et Rac d'Uckange interdit. Avec 4F_UCK-THL_001 et 4F_UCK-THL_002.  Déf à activer quand générique activée sur la L204000 (LGN-THL)",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676574561",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,4,42,"2024-01-22","09:30:00","2024-10-14","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                           ",null,"Medium","1","Planned"]
["SNCF-R","13676576961",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,50,45,"2023-12-11","00:00:00","2024-11-04","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13676578561",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,6,50,"2024-02-05","00:00:00","2024-12-09","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","14000730661",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,7,35,"2024-02-18","23:55:00","2024-09-01","01:55:00","Periodical",null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,"Medium","7","Planned"]
["SNCF-R","15126004861",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,13,49,"2024-03-30","04:00:00","2024-12-02","05:00:00","Periodical",null,"Mise en service CCR secteur Thionville    Les objets travaux placés sur les WE S13+21+40+48 ne seront pas tous utilisés (WE de secours selon avancement du projet CCR), il est demandé à la DAC de tracer les sillons dans les objets travaux au lot 1 avec la ",null,"High","1,6,7","Planned"]
["SNCF-R","15126494561",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,9,36,"2024-03-03","23:00:00","2024-09-08","05:00:00","Periodical",null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,"Medium","7","Planned"]
["SNCF-R","15088062761",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,32,32,"2024-08-11","21:30:00","2024-08-12","05:30:00","Periodical",null,"Déf 27678, 8h nuit, V1+V1B+V2 à Uckange P2. Avec 4D_UCK-THL_030 et 4D_HGD-UCK_022 qui reprend les conséquences circulations.",null,"Medium","7","Planned"]
["SNCF-R","15088333061",null,"< >","Uckange - Poste 2","Ebange - Accès Sud",2024,2024,37,40,"2024-09-09","08:30:00","2024-10-04","17:00:00","Periodical",null,"Déf 27678, 8h30 jour, V1B (correspond à la zep 157) à Uckange. Avec 4D_UCK_039 et 4D_HGD-UCK_023 qui reprend les conséquences circulations.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15088083761",null,"< >","Uckange - Poste 2","Ebange - Accès Sud",2024,2024,32,32,"2024-08-11","21:30:00","2024-08-12","05:30:00","Periodical",null,"Déf 27678, 8h nuit, V1B (correspond à la zep 157) à Uckange. Avec 4D_UCK_038 et 4D_HGD-UCK_022 qui reprend les conséquences circulations.",null,"Medium","7","Planned"]
["SNCF-R","14000079461",null,"< >","Ebange - Accès Sud","Ebange - Jonction Nord",2024,2024,6,6,"2024-02-07","11:30:00","2024-02-08","15:30:00","Periodical",null,"Déf V1B+V2B entre Thionville et Uckange. Avec 4C_THL_098.",null,"Medium","3,4","Planned"]
["SNCF-R","14458010161",null,"< >","Ebange - Faisceau","Ebange - Jonction Nord",2024,2024,17,17,"2024-04-26","10:00:00","2024-04-27","12:30:00","Periodical",null,"Essais ETCS_C2 - Cap 2h30 jour, zep 804, Voie 2Bis",null,"Medium","5","Planned"]
["SNCF-R","13999992261",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,6,6,"2024-02-05","11:30:00","2024-02-06","15:30:00","Periodical",null,"Déf V1+V2 entre Thionville et Uckange. Avec 4C_THL_097.",null,"Medium","1,2","Planned"]
["SNCF-R","14458115561",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,22,22,"2024-05-31","10:00:00","2024-06-01","11:30:00","Periodical",null,"Essais ETCS_C2 - Déf 1h30 jour, zep 162 d'Uckange, V2",null,"Medium","5","Planned"]
["SNCF-R","13676552461",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,50,50,"2023-12-11","13:51:00","2024-12-13","14:53:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676544461",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,8,46,"2024-02-20","11:30:00","2024-11-15","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                               ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676544461",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,8,46,"2024-02-20","11:30:00","2024-02-23","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                               ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676548461",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,8,45,"2024-02-19","09:30:00","2024-11-04","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                     ",null,"Medium","1","Planned"]
["SNCF-R","13676548461",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,8,45,"2024-02-19","09:30:00","2024-02-19","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                     ",null,"Medium","1","Planned"]
["SNCF-R","14000754761",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,7,35,"2024-02-18","23:55:00","2024-09-01","01:55:00","Periodical",null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,"Medium","7","Planned"]
["SNCF-R","14462777561",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,13,49,"2024-03-30","04:00:00","2024-12-02","05:00:00","Periodical",null,"Mise en service CCR secteur Thionville    Les objets travaux placés sur les WE S13+21+40+48 ne seront pas tous utilisés (WE de secours selon avancement du projet CCR), il est demandé à la DAC de tracer les sillons dans les objets travaux au lot 1 avec la ",null,"High","1,6,7","Planned"]
["SNCF-R","15126500861",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,9,36,"2024-03-03","23:00:00","2024-09-08","05:00:00","Periodical",null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,"Medium","7","Planned"]
["SNCF-R","13676551661",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,50,50,"2023-12-11","14:15:00","2024-12-13","15:05:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676549261",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,4,42,"2024-01-23","11:30:00","2024-10-18","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                       ",null,"High","2,3,4,5","Planned"]
["SNCF-R","13676545261",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,4,42,"2024-01-22","09:30:00","2024-10-14","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                             ",null,"Medium","1","Planned"]
["SNCF-R","13676550861",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,50,45,"2023-12-11","00:00:00","2024-11-04","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","14131541961",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,10,16,"2024-03-10","23:50:00","2024-04-21","03:20:00","Periodical",null,"Avec 4C_THL_100 qui reprend les conséquences circulations.",null,"Medium","7","Planned"]
["SNCF-R","13676236861",null,"< >","Metz-Nord - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,46,46,"2024-11-16","08:00:00","2024-11-16","15:00:00","Periodical",null,"Déf. 7h00 sur les voies rapides entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_001 + 4D_MMZ-HGD_001 + 4D_HGD2_002. Report circulation sur voies BIS entre UCK ou THL et WPY BV. Entrée WPY par voie 1M interdite => report via FO",null,"Medium","6,7","Planned"]
["SNCF-R","13676229661",null,"< >","Metz-Nord - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                         ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676224061",null,"< >","Metz-Nord - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                           ",null,"High","1","Planned"]
["SNCF-R","13676232861",null,"< >","Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2024,2024,6,50,"2024-01-30","00:00:00","2024-12-09","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13676232061",null,"< >","Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,46,"2023-12-11","13:38:00","2024-11-15","14:41:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676231261",null,"< >","Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,34,"2023-12-11","09:21:00","2024-08-23","10:19:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676233661",null,"< >","Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2024,2024,6,50,"2024-01-30","00:00:00","2024-12-09","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13676242461",null,"< >","Woippy - Aig ITE","Maizières-lès-Metz - Bât Voyageurs",2024,2024,8,8,"2024-02-24","22:30:00","2024-02-25","05:30:00","Periodical",null,"Déf 11822, 7h nuits SaDi+DiLu, V1+V2 à Woippy AN (zep 45,41,39,26,30). Avec 4D_MMZ-HGD_016. Report des circulations V1B/V2B entre Hagondange et Woippy BV.",null,"Medium","6,7","Planned"]
["SNCF-R","14550724661",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,9,9,"2024-03-03","08:00:00","2024-03-03","15:00:00","Periodical",null,"Déf. 7h00 DI sur voies Bis entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_012 + 4D_MMZ-HGD_018 + 4D_HGD2_014 + 4D_HGD-UCK_021 + 4D_UCK_035. Report circulation sur voies rapides entre UCK ou THL et WPY BV. Faisceau départ WPY côté Nord + Faisceau et",null,"Medium","7","Planned"]
["SNCF-R","13676228061",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                     ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676227261",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                               ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676226461",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                   ",null,"High","1","Planned"]
["SNCF-R","13676225661",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                           ",null,"High","1","Planned"]
["SNCF-R","13676234461",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,45,"2023-12-11","00:00:00","2024-11-04","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13676236061",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,45,"2023-12-11","00:00:00","2024-11-04","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13676230461",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,50,"2023-12-11","11:23:00","2024-12-13","12:27:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676235261",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,50,"2023-12-11","14:30:00","2024-12-13","15:25:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676224861",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                   ",null,"High","1","Planned"]
["SNCF-R","13676239661",null,"< >","Woippy - CV 188","Maizières-lès-Metz - Bât Voyageurs",2024,2024,46,46,"2024-11-17","08:00:00","2024-11-17","15:00:00","Periodical",null,"Déf. 7h00 les DI sur voies 1+2Bis entre Woippy et Hagondange. Simultanément 4D_WPY-MMZ_004 + 4D_MMZ-HGD_003 + 4D_HGD2_003. Report circulation sur voie 1Bis d'UCK ou THL à WPY AS, report sur voie 2 de WPY BV à UCK ou THL. Départ WPY côté Nord interdit => s",null,"Medium","7","Planned"]
["SNCF-R","14550411661",null,"< >","Woippy - FSC Départ","Maizières-lès-Metz - Bât Voyageurs",2024,2024,9,9,"2024-02-26","09:30:00","2024-02-29","15:30:00","Periodical",null,"Déf 11822, 6h jour, LU MA ME JE, V1B+V2B à Woippy AN (zep 91,89,84,86,90,92,96). Avec 4D_MMZ-HGD_017. Report des circulations V1/V2 entre Hagondange et Woippy BV. Sortie FD et FRE Woippy vers V2B interdit. Accès ITE Euromoselle interdit. Accès HGD Faiscea",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","14550971561",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,9,9,"2024-03-03","08:00:00","2024-03-03","15:00:00","Periodical",null,"Déf. 7h00 les DI sur voies Bis entre Hagondange et Thionville. Simultanément: 4D_WPY-MMZ_012 + 4D_MMZ-HGD_018 + 4D_HGD2_014 + 4D_HGD-UCK_021 + 4D_UCK_035.",null,"Medium","7","Planned"]
["SNCF-R","13676476761",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,7,35,"2024-02-18","23:55:00","2024-09-01","01:55:00","Periodical",null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,"Medium","7","Planned"]
["SNCF-R","15126490961",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,9,36,"2024-03-03","23:00:00","2024-09-08","05:00:00","Periodical",null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,"Medium","7","Planned"]
["SNCF-R","13676460961",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676458561",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"High","1","Planned"]
["SNCF-R","13676457761",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676456961",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"High","1","Planned"]
["SNCF-R","13676463561",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,50,50,"2023-12-11","11:30:00","2024-12-13","12:34:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676465961",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,50,50,"2023-12-11","14:20:00","2024-12-13","15:15:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14131583461",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,10,16,"2024-03-10","23:50:00","2024-04-21","03:20:00","Periodical",null,"Avec 4C_THL_100 qui reprend les conséquences circulations.",null,"Medium","7","Planned"]
["SNCF-R","13676460161",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy B)",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676459361",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676461761",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"High","1","Planned"]
["SNCF-R","13676462561",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"High","1","Planned"]
["SNCF-R","13676465161",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,50,46,"2023-12-11","13:45:00","2024-11-15","14:49:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676464361",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,50,34,"2023-12-11","09:15:00","2024-08-23","10:11:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14550923461",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,9,9,"2024-03-03","08:00:00","2024-03-04","15:00:00","Periodical",null,"Déf. 7h00 sur voies Bis entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_012 + 4D_MMZ-HGD_018 + 4D_HGD2_014 + 4D_HGD-UCK_021 + 4D_UCK_035.",null,"Medium","7","Planned"]
["SNCF-R","13676496461",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,46,46,"2024-11-16","08:00:00","2024-11-17","15:00:00","Periodical",null,"Déf. 7h00 sur les voies rapides entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_001 + 4D_MMZ-HGD_001 + 4D_HGD2_002. Report circulation sur voies BIS entre UCK ou THL et WPY BV. Entrée WPY par voie 1M interdite => report via FO",null,"Medium","6,7","Planned"]
["SNCF-R","13676497261",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,46,46,"2024-11-17","08:00:00","2024-11-18","15:00:00","Periodical",null,"Déf. 7h00 les DI sur voies 1+2Bis entre Woippy et Hagondange. Simultanément 4D_WPY-MMZ_004 + 4D_MMZ-HGD_003 + 4D_HGD2_003. Report circulation sur voie 1Bis d'UCK ou THL à WPY AS, report sur voie 2 de WPY BV à UCK ou THL. Départ WPY côté Nord interdit => s",null,"Medium","7","Planned"]
["SNCF-R","13676498261",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,10,16,"2024-03-10","23:50:00","2024-04-21","03:20:00","Periodical",null,"Avec 4C_THL_100 qui reprend les conséquences circulations.",null,"Medium","7","Planned"]
["SNCF-R","13676491461",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                     ",null,"High","1","Planned"]
["SNCF-R","13676490361",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV       ",null,"High","1","Planned"]
["SNCF-R","13676492261",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                       ",null,"High","1","Planned"]
["SNCF-R","13676494661",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,50,50,"2023-12-11","11:28:00","2024-12-13","12:29:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676493061",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,50,50,"2023-12-11","14:11:00","2024-12-13","15:09:00","Periodical",null,"Modifiée suite main courante pour le SA2023",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676493861",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,50,34,"2023-12-11","09:17:00","2024-08-23","10:14:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676387261",null,"< >","Woippy - Accès Nord","Hagondange - ITE Richemont",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                           ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676389661",null,"< >","Woippy - Accès Nord","Hagondange - ITE Richemont",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                   ",null,"High","1","Planned"]
["SNCF-R","13676393661",null,"< >","Woippy - Accès Nord","Hagondange - ITE Richemont",2024,2024,50,46,"2023-12-11","13:41:00","2024-11-15","14:44:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676396061",null,"< >","Woippy - Accès Nord","Hagondange - ITE Richemont",2024,2024,46,46,"2024-11-16","08:00:00","2024-11-16","15:00:00","Periodical",null,"Déf. 7h00 sur les voies rapides entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_001 + 4D_MMZ-HGD_001 + 4D_HGD2_002. Report circulation sur voies BIS entre UCK ou THL et WPY BV. Entrée WPY par voie 1M interdite => report via FO",null,"Medium","6,7","Planned"]
["SNCF-R","14550504661",null,"< >","Walibi-Lorraine","Hagondange - Faisceau",2024,2024,9,9,"2024-02-26","09:30:00","2024-02-29","15:30:00","Periodical",null,"Déf 11822, 6h jour, LU MA ME JE, V1B+V2B entre Woippy AN et Hagondange  (zep type L entre WPY et HGD). Avec 4D_WPY-MMZ_011 qui reprend les conséquences circulations.",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","13676390461",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                     ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676392061",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                             ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676388861",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                               ",null,"High","1","Planned"]
["SNCF-R","13676391261",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)         ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676386461",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                             ",null,"High","1","Planned"]
["SNCF-R","13676388061",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                     ",null,"High","1","Planned"]
["SNCF-R","13676395261",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,50,50,"2023-12-11","11:27:00","2024-12-13","12:28:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676392861",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,50,50,"2023-12-11","14:25:00","2024-12-13","15:21:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676394461",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,50,34,"2023-12-11","09:19:00","2024-08-23","10:17:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676398061",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,46,46,"2024-11-17","08:00:00","2024-11-17","15:00:00","Periodical",null,"Déf. 7h00 les DI sur voies 1+2Bis entre Woippy et Hagondange. Simultanément 4D_WPY-MMZ_004 + 4D_MMZ-HGD_003 + 4D_HGD2_003. Report circulation sur voie 1Bis d'UCK ou THL à WPY AS, report sur voie 2 de WPY BV à UCK ou THL. Départ WPY côté Nord interdit => s",null,"Medium","7","Planned"]
["SNCF-R","14550857361",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,9,9,"2024-03-03","08:00:00","2024-03-03","15:00:00","Periodical",null,"Déf. 7h00 sur voies Bis entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_012 + 4D_MMZ-HGD_018 + 4D_HGD2_014 + 4D_HGD-UCK_021 + 4D_UCK_035.",null,"Medium","7","Planned"]
["SNCF-R","13676572961",null,"< >","Uckange - Ano Km 181,3","Uckange - Faisceau",2024,2024,4,42,"2024-01-22","09:30:00","2024-10-14","15:30:00","Periodical",null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                           ",null,"Medium","1","Planned"]
["SNCF-R","15088080861",null,"< >","Uckange - Ano Km 181,3","Uckange - Faisceau",2024,2024,37,40,"2024-09-09","08:30:00","2024-10-04","17:00:00","Periodical",null,"Déf 27678, 8h30 jour, V1B+V2B à Uckange P2. Avec 4D_UCK-THL_031 et 4D_HGD-UCK_023 qui reprend les conséquences circulations.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14550983561",null,"< >","Uckange - Ano Km 181,3","Uckange - Faisceau",2024,2024,9,9,"2024-03-03","08:00:00","2024-03-03","15:00:00","Periodical",null,"Déf. 7h00 les DI sur voies Bis entre Hagondange et Uckange. Simultanément: 4D_WPY-MMZ_012 + 4D_MMZ-HGD_018 + 4D_HGD2_014 + 4D_HGD-UCK_021 + 4D_UCK_035.",null,"Medium","7","Planned"]
["SNCF-R","15088121161",null,"< >","Hagondange - Aig ITE","Uckange - Ano Km 181,3",2024,2024,37,40,"2024-09-09","08:30:00","2024-10-04","17:00:00","Periodical",null,"Déf 27678, 8h30 jour, V1B+V2B entre Hagondange et Uckange P2. Avec 4D_UCK_039 et 4D_UCK-THL_031.   Report circulations sur V1+V2 entre Hagondange et Thionville.  Rac Mondelange interdit (Thionville, Ebange <-->Rac<-->Conflans interdit).   Accès Ebange via",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14462859561",null,"< >","Hagondange - ITE Richemont","Uckange - Ano Km 181,3",2024,2024,13,49,"2024-03-30","04:00:00","2024-12-02","05:00:00","Periodical",null,"Mise en service CCR secteur Thionville    Les objets travaux placés sur les WE S13+21+40+48 ne seront pas tous utilisés (WE de secours selon avancement du projet CCR), il est demandé à la DAC de tracer les sillons dans les objets travaux au lot 1 avec la ",null,"High","1,6,7","Planned"]
["SNCF-R","15087968861",null,"< >","Hagondange - ITE Richemont","Uckange - Ano Km 181,3",2024,2024,32,32,"2024-08-11","21:30:00","2024-08-12","05:30:00","Periodical",null,"Déf 27678, 8h nuit, V1+V1B+V2B entre Hagondange et Uckange P2. Avec 4D_UCK_038 et 4D_UCK-THL_030.   Trafic Impair Thionville-->Uckange-->Hagondange INTERDIT.   Report circulations paires sur V2. Rac Mondelange interdit (Thionville, Ebange <-->Rac<-->Confl",null,"Medium","7","Planned"]
["SNCF-R","14462011761",null,"< >","Thionville - Ac Nord FSC Lux","Hettange-Grande",2024,2024,31,31,"2024-07-29","10:15:00","2024-07-30","11:50:00","Periodical",null,"Essais ETCS_C1 - Cap 1h35 jour, zep 934",null,"Medium","1,2","Planned"]
["SNCF-R","14461983661",null,"< >","Thionville - Ac Nord FSC Lux","Hettange-Grande",2024,2024,30,30,"2024-07-26","10:15:00","2024-07-26","12:10:00","Periodical",null,"Essais ETCS_C1 - Cap 1h55 jour, zep 934",null,"Medium","5","Planned"]
["SNCF-R","14000425461",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,7,7,"2024-02-14","10:25:00","2024-02-15","14:10:00","Periodical",null,"Déf 3h45 jour, V1+V2 entre Thionville et Bettembourg.",null,"Medium","3,4","Planned"]
["SNCF-R","15126429461",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,9,36,"2024-03-03","23:00:00","2024-09-08","05:00:00","Periodical",null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,"Medium","7","Planned"]
["SNCF-R","15121690461",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,35,36,"2024-08-27","00:10:00","2024-09-07","03:40:00","Periodical",null,"Déf 3h30, V1+V2 entre Thionville et Zoufftgen. Avec 4D_THL-HGT_019, 4D_THL-AP_025 et 4C_THL_153.",null,"High","2,3,4,5,6","Planned"]
["SNCF-R","14462092361",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,13,49,"2024-03-30","04:00:00","2024-12-02","05:00:00","Periodical",null,"Mise en service CCR secteur Thionville    Les objets travaux placés sur les WE S13+21+40+48 ne seront pas tous utilisés (WE de secours selon avancement du projet CCR), il est demandé à la DAC de tracer les sillons dans les objets travaux au lot 1 avec la ",null,"High","1,6,7","Planned"]
["SNCF-R","14132534061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,30,30,"2024-07-25","11:30:00","2024-07-25","14:15:00","Periodical",null,"Essais ETCS_C1 - Cap 2h45 jour, DFV-L BTG-THL V1",null,"Medium","4","Planned"]
["SNCF-R","14000728161",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,7,35,"2024-02-18","23:55:00","2024-09-01","01:55:00","Periodical",null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,"Medium","7","Planned"]
["SNCF-R","13676094461",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,50,50,"2023-12-11","09:03:00","2024-12-13","09:55:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676093661",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,50,50,"2023-12-11","14:00:00","2024-12-13","15:07:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14128639961",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,10,16,"2024-03-10","23:50:00","2024-04-21","03:20:00","Periodical",null,"Avec 4C_THL_100 qui reprend les conséquences circulations.",null,"Medium","7","Planned"]
["SNCF-R","13676092061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-01-08","23:27:00","2024-06-14","05:27:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676092061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-06-03","23:27:00","2024-06-07","05:27:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676092061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-10-28","23:27:00","2024-11-08","05:27:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676092061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-01-22","23:27:00","2024-12-06","05:27:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676092061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-06-24","23:27:00","2024-06-28","05:27:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676092861",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-01-08","23:43:00","2024-06-14","05:29:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676092861",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-06-03","23:43:00","2024-06-07","05:29:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676092861",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-10-28","23:43:00","2024-11-08","05:29:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676092861",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-01-22","23:43:00","2024-12-06","05:29:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676092861",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-06-24","23:43:00","2024-06-28","05:29:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14462084061",null,"< >","Thionville - ITE EDF/Catteno","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,31,31,"2024-07-31","10:15:00","2024-08-01","11:50:00","Periodical",null,"Essais ETCS_C1 - Cap 1h35 jour, zep 936",null,"Medium","3,4","Planned"]
["SNCF-R","13676665261",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2024,2024,50,50,"2023-12-11","10:48:00","2024-12-13","11:55:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676666861",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2024,2024,50,50,"2023-12-11","14:11:00","2024-12-13","15:05:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676664461",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2024,2024,50,50,"2023-12-11","09:20:00","2024-12-13","10:15:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676668461",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2024,2024,5,50,"2024-01-29","00:00:00","2024-12-09","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13676660861",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,11,50,"2024-03-11","23:00:00","2024-12-13","05:45:00","Periodical",null,"Modification le 07/02/2019 : X voies sur Y passé de \"\"2V/2\"\" à \"\"2V/4\"\", et Typologie schématisée passée de \"\"Simultanée\"\" à \"\"Autre\"\"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676661861",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,8,48,"2024-02-19","23:00:00","2024-11-29","05:45:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676666061",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,50,40,"2023-12-11","00:00:00","2024-10-06","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13676667661",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,5,50,"2024-01-29","00:00:00","2024-12-09","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13676661861",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,8,48,"2024-04-22","23:00:00","2024-11-22","05:45:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676695161",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,11,46,"2024-03-16","23:45:00","2024-11-17","04:15:00","Periodical",null,"Def 4 voies entre Novéant et Metz",null,"High","6,7","Planned"]
["SNCF-R","13676660861",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,11,50,"2024-08-12","23:00:00","2024-12-13","05:45:00","Periodical",null,"Modification le 07/02/2019 : X voies sur Y passé de \"\"2V/2\"\" à \"\"2V/4\"\", et Typologie schématisée passée de \"\"Simultanée\"\" à \"\"Autre\"\"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676693761",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,42,45,"2024-10-14","23:00:00","2024-11-08","05:00:00","Periodical",null,"Déf V2B entre Metz-Sablon et Novéant.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13910915161",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,45,47,"2024-11-09","23:30:00","2024-11-24","04:00:00","Periodical",null,"Déf V1+V2+V1B+V2B entre Novéant et Metz-Sablon.",null,"Medium","6,7","Planned"]
["SNCF-R","14548405761",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,39,41,"2024-09-28","21:30:00","2024-10-13","05:00:00","Periodical",null,"Déf V2B entre Metz-Sablon et Novéant.",null,"Medium","6,7","Planned"]
["SNCF-R","13676670261",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,3,42,"2024-01-21","23:25:00","2024-10-20","03:30:00","Periodical",null,"04h05 simultanées nuit de DI/LU durant 2 WE. Re-paramétrage Mistral CCR Lorraine. Interdiction de circulation dans la zone d´action des PAI de Pagny et Metz. Décalage horaire. Fenêtres déformées simultanément sur lignes 89000 + 95000 + 140000 + 180000 + 1",null,"Medium","7","Planned"]
["SNCF-R","13971963961",null,"< >","Ancy-sur-Moselle","Metz-Sablon - Montigny AT",2024,2024,46,47,"2024-11-12","23:30:00","2024-11-22","05:30:00","Periodical",null,"Avec 4D_MZS-WPY_002 et 4C_MZ_003 qui reprend les conséquences circulations.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13972521061",null,"< >","Ancy-sur-Moselle","Metz-Sablon - Montigny AT",2024,2024,45,46,"2024-11-09","08:00:00","2024-11-12","05:00:00","Periodical",null,"Avec 4D_MZS-WPY_003 et 4C_MZ_004 qui reprend les conséquences circulations.",null,"Medium","1,2,6,7","Planned"]
["SNCF-R","13972581861",null,"< >","Ancy-sur-Moselle","Metz-Sablon - Montigny AT",2024,2024,46,46,"2024-11-16","08:00:00","2024-11-16","20:00:00","Periodical",null,"Avec 4D_MZS-WPY_004 et 4C_MZ_005 qui reprend les conséquences circulations.",null,"Medium","6","Planned"]
["SNCF-R","14705658161",null,"< >","Ancy-sur-Moselle","Metz-Sablon - Montigny AT",2024,2024,44,45,"2024-10-28","23:30:00","2024-11-07","05:30:00","Periodical",null,"Avec 4D_MZS-WPY_006 et 4C_MZ_018 qui reprend les conséquences circulations.",null,"High","1,2,3,4","Planned"]
["SNCF-R","13676663661",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Montigny AT",2024,2024,50,50,"2023-12-11","14:09:00","2024-12-13","15:17:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676662861",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Montigny AT",2024,2024,50,40,"2023-12-11","00:00:00","2024-10-06","03:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","14528331061",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Montigny AT",2024,2024,47,48,"2024-11-18","23:00:00","2024-11-29","05:00:00","Periodical",null,"Déf V1B entre Novéant et Metz-Sablon. Report des trafics V1. Accès faisceau Montigny en venant de Novéant interdit.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13676157261",null,"< >","Woippy - Faisceau Début","Woippy - Aig Km 165,3",2024,2024,20,39,"2024-05-13","08:00:00","2024-09-27","14:30:00","Periodical",null,"Cap 6h30, voie FO Woippy. DP S9C: Zep 291. DP S11: Sél 156 du SSr Woippy Triage Départ à concerter car impact sur la liaison FRE<-->Faisceau Départ.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13676238861",null,"< >","Woippy - Bât Voyageurs","Woippy - Aig V1M",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00","Periodical",null,"Se substitue à la FEN20_Woippy-Maizières_009 pour adaptation au PK 164+650 (au lieu du PK 167+169 interdisant la sortie AFPL du RE de Woippy). Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uc",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13676162061",null,"< >","Woippy - FSC Arrivée","Woippy - Aig V1M",2024,2024,20,39,"2024-05-13","08:00:00","2024-09-27","14:30:00","Periodical",null,"Cap 6h30, FRE Woippy. DP S9C: zep 672, 673, 676, 757 à 764, 956, 955, 953. DP S11: sel 157,161,170 du SSr Woippy Triage Départ.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13676154261",null,"< >","Metz-Nord - Bât Voyageurs","Woippy - AccÃ¨s Sud",2024,2024,11,41,"2024-03-11","23:30:00","2024-10-11","05:30:00","Periodical",null,"CAP 6h00 de nuit voies 1 + 2 au niveau de Woippy BV. Simultanément avec 4F_MZ-WPY_001. Report circulation sur voies BIS entre MZS AO et WPY AN. Entrée WPY par voie 1M libre. Permet de travailler sur la jonction Bis/Rapides au BV. Prévoir un renfort au fai",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676628961",null,"< >","Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2024,2024,3,42,"2024-01-21","23:25:00","2024-10-20","03:30:00","Periodical",null,"04h05 simultanées nuit de DI/LU durant 2 WE. Re-paramétrage Mistral CCR Lorraine. Interdiction de circulation dans la zone d´action des PAI de Pagny et Metz. Décalage horaire. Fenêtres déformées simultanément sur lignes 89000 + 95000 + 140000 + 180000 + 1",null,"Medium","7","Planned"]
["SNCF-R","13676631961",null,"< >","Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2024,2024,21,27,"2024-05-21","23:35:00","2024-07-05","05:05:00","Periodical",null,"Avec 4C_MZ_014 qui reprend les conséquences circulations.",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676629961",null,"< >","Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2024,2024,43,44,"2024-10-27","23:40:00","2024-11-03","04:50:00","Periodical",null,"Fenêtre déformée 5h10 nuit DI/LU sur voies V1+V2+1M+2M, simultanément lignes 180000+191300. Maintenance annuelle ADV au nord de MZV. Accès Metz-Ville côté Woippy interdit. Détournements via MZ DLP avec rebroussement à Metz Sablon pour les trains de/vers N",null,"Medium","7","Planned"]
["SNCF-R","13676624761",null,"< >","Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2024,2024,11,41,"2024-03-11","23:30:00","2024-10-11","05:30:00","Periodical",null,"SA2019 Modif des horaires suite à la demande de la MC 144  SA2023 Modification des horaires par main courante (passage de 23h26 - 05h26 à 23h30 - 05h30)",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676627361",null,"< >","Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2024,2024,50,50,"2023-12-11","13:35:00","2024-12-13","14:38:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676628161",null,"< >","Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2024,2024,50,50,"2023-12-11","09:25:00","2024-12-13","10:22:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13676626561",null,"< >","Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2024,2024,49,43,"2023-12-10","23:56:00","2024-11-02","02:56:00","Periodical",null,"",null,"High","7","Planned"]
["SNCF-R","13676625761",null,"< >","Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2024,2024,49,43,"2023-12-10","23:56:00","2024-11-02","02:56:00","Periodical",null,"",null,"High","7","Planned"]
["SNCF-R","13676158061",null,"< >","Woippy - FSC Arrivée","Woippy - Faisceau Relais",2024,2024,20,40,"2024-05-13","08:00:00","2024-10-04","14:30:00","Periodical",null,"Cap 6h30, voie DO Woippy. DP S9C: Zep 282. DP S11: Sél 256 du SSr Woippy Triage Reception.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14513391661",null,"< >","Gagny Raccordement - Bif Nord","Gagny Raccordement - Bif Est",2024,2024,2,47,"2024-01-08","08:30:00","2024-11-24","12:30:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14513391661",null,"< >","Gagny Raccordement - Bif Nord","Gagny Raccordement - Bif Est",2024,2024,2,47,"2024-01-08","08:30:00","2024-11-24","12:30:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14513947061",null,"< >","Gagny Raccordement - Bif Nord","Gagny Raccordement - Bif Est",2024,2024,50,47,"2023-12-16","08:30:00","2024-11-18","12:00:00","Periodical",null,"",null,"Medium","1,6,7","Planned"]
["SNCF-R","13703676461",null,"< >","Stade-de-France-St-Denis","St-Denis - Pk 6,8",2024,2024,50,50,"2023-12-11","00:30:00","2024-12-14","04:25:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703678061",null,"< >","Stade-de-France-St-Denis","St-Denis - Pk 6,8",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703678061",null,"< >","Stade-de-France-St-Denis","St-Denis - Pk 6,8",2024,2024,1,50,"2024-01-08","23:35:00","2024-01-28","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703673861",null,"< >","St-Denis - Garages Impairs","St-Denis - Pk 6,8",2024,2024,50,50,"2023-12-11","00:35:00","2024-12-14","04:45:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703675661",null,"< >","St-Denis - Garages Impairs","St-Denis - Pk 6,8",2024,2024,50,50,"2023-12-11","01:00:00","2024-12-14","05:20:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703679061",null,"< >","St-Denis - Garages Impairs","St-Denis - Pk 6,8",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13875734061",null,"< >","St-Denis - Garages Impairs","St-Denis - Pk 6,8",2024,2024,1,49,"2024-01-02","10:10:00","2024-12-06","12:40:00","Periodical",null,"maintenance de jour DV/RV",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703619661",null,"< >","Paris-Landy - Pleyel","St-Denis - Garages Pairs",2024,2024,1,50,"2024-01-08","23:35:00","2024-01-28","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703619661",null,"< >","Paris-Landy - Pleyel","St-Denis - Garages Pairs",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13875530761",null,"< >","Paris-Landy - Pleyel","St-Denis - Garages Pairs",2024,2024,1,49,"2024-01-02","10:10:00","2024-12-06","12:40:00","Periodical",null,"maintenance de jour DV/RV",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14351655161",null,"< >","Paris-Landy - Pleyel","St-Denis - Garages Pairs",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-09","04:30:00","Periodical",null,"",null,"Major","1","Planned"]
["SNCF-R","13703682061",null,"< >","St-Ouen - Bât Voyageurs","Épinay-sur-Seine",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-14","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703683061",null,"< >","St-Ouen - Bât Voyageurs","Épinay-sur-Seine",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC industrielles",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14352010261",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-09","04:30:00","Periodical",null,"",null,"Major","1","Planned"]
["SNCF-R","13875665461",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,1,49,"2024-01-02","10:10:00","2024-12-06","12:40:00","Periodical",null,"maintenance de jour DV/RV",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703610261",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2024-07-09","00:30:00","2024-08-04","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703612861",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,1,50,"2024-03-04","23:35:00","2024-07-07","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703611061",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2024-07-09","01:05:00","2024-08-04","05:15:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703611861",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703612861",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703609461",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","01:05:00","2024-12-14","05:05:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703608661",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","00:25:00","2024-12-14","04:25:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703611061",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","01:05:00","2024-12-14","05:15:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703610261",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","00:30:00","2024-12-14","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","14351779361",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-09","04:30:00","Periodical",null,"",null,"Major","1","Planned"]
["SNCF-R","14329448361",null,"< >","St-Denis - Pk 6,8","La Barre-Ormesson",2024,2024,38,39,"2024-09-20","23:35:00","2024-09-27","04:30:00","Periodical",null,"",null,"Medium","5","Planned"]
["SNCF-R","14869513161",null,"< >","St-Denis - Pk 6,8","La Barre-Ormesson",2024,2024,38,40,"2024-09-22","01:30:00","2024-09-30","04:30:00","Periodical",null,"",null,"Medium","1,7","Planned"]
["SNCF-R","14630498761",null,"< >","St-Denis - Pk 6,8","La Barre-Ormesson",2024,2024,23,24,"2024-06-07","23:35:00","2024-06-10","04:30:00","Periodical",null,"",null,"Medium","1,5,6,7","Planned"]
["SNCF-R","13703670661",null,"< >","Paris-La Chapelle - Jonct Km 3,4","St-Ouen-les-Docks - Garage Centraux",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-14","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703671661",null,"< >","Paris-La Chapelle - Poste E","St-Ouen-les-Docks - Garage Centraux",2024,2024,1,49,"2024-01-02","23:35:00","2024-12-06","04:30:00","Periodical",null,"ITC INDUSTRIELLE (fermeture gare sout) ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703635061",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703635061",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,1,50,"2024-03-04","23:35:00","2024-07-07","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703634261",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,50,50,"2024-07-09","00:55:00","2024-08-04","05:25:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703630661",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,50,50,"2024-07-09","00:30:00","2024-08-04","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","14630464561",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,23,24,"2024-06-07","23:35:00","2024-06-10","04:30:00","Periodical",null,"",null,"Medium","1,5,6,7","Planned"]
["SNCF-R","13703635061",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,1,50,"2024-09-30","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703630661",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,50,50,"2023-12-11","00:30:00","2024-12-14","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703634261",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,50,50,"2023-12-11","00:55:00","2024-12-14","05:25:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","14352949461",null,"< >","Ermont-Eaubonne - Poste 1","Ermont-Eaubonne - Bât Voyageurs",2024,2024,46,48,"2024-11-15","23:35:00","2024-11-25","04:30:00","Periodical",null,"",null,"High","1,5,6,7","Planned"]
["SNCF-R","13703592861",null,"< >","Gennevilliers - Garages","Ermont-Eaubonne - Bât Voyageurs",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-14","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703654261",null,"< >","Champ-de-Courses-d'Enghien","Ermont-Eaubonne - Garage Pair",2024,2024,50,50,"2023-12-12","01:30:00","2024-12-14","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703656461",null,"< >","Champ-de-Courses-d'Enghien","Ermont-Eaubonne - Garage Pair",2024,2024,1,50,"2024-09-30","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC industrielles     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703656461",null,"< >","Champ-de-Courses-d'Enghien","Ermont-Eaubonne - Garage Pair",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC industrielles     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14137283861",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Ermont-Eaubonne - Garage Pair",2024,2024,1,50,"2024-09-30","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC INDUS",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14352976161",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Ermont-Eaubonne - Garage Pair",2024,2024,46,48,"2024-11-15","23:35:00","2024-11-25","04:30:00","Periodical",null,"",null,"High","1,5,6,7","Planned"]
["SNCF-R","14137283861",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Ermont-Eaubonne - Garage Pair",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC INDUS",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14352960361",null,"< >","Ermont-Eaubonne - Poste 1","Ermont-Eaubonne - Garage Pair",2024,2024,46,48,"2024-11-15","23:35:00","2024-11-25","04:30:00","Periodical",null,"",null,"High","1,5,6,7","Planned"]
["SNCF-R","13703651861",null,"< >","Ermont-Eaubonne - Garages Impairs","Cernay (Val-d'Oise)",2024,2024,1,50,"2024-09-30","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14352987061",null,"< >","Ermont-Eaubonne - Garages Impairs","Cernay (Val-d'Oise)",2024,2024,46,48,"2024-11-15","23:35:00","2024-11-25","04:30:00","Periodical",null,"",null,"High","1,5,6,7","Planned"]
["SNCF-R","13703651861",null,"< >","Ermont-Eaubonne - Garages Impairs","Cernay (Val-d'Oise)",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703650861",null,"< >","Ermont-Eaubonne - Garages Impairs","Cernay (Val-d'Oise)",2024,2024,50,50,"2023-12-12","01:30:00","2024-12-14","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703602661",null,"< >","Franconville-Plessis-Bouchard","Montigny-Beauchamp - Tiroir",2024,2024,7,50,"2024-02-13","01:30:00","2024-12-14","04:30:00","Periodical",null,"",null,"High","2,3,4,5,6","Planned"]
["SNCF-R","15338387961",null,"< >","St-Ouen-l'Aumône","St-Ouen-l'Aumône",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00","continuous",null,"",null,"High","","Planned"]
["SNCF-R","13703587861",null,"< >","St-Ouen-l'Aumône","St-Ouen-l'Aumône",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14339216561",null,"< >","St-Ouen-l'Aumône","St-Ouen-l'Aumône",2024,2024,2,50,"2024-01-08","23:35:00","2024-12-13","04:30:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14345094961",null,"< >","St-Ouen-l'Aumône","St-Ouen-l'Aumône",2024,2024,50,50,"2023-12-12","01:45:00","2024-12-14","04:15:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","14345153161",null,"< >","St-Ouen-l'Aumône","St-Ouen-l'Aumône",2024,2024,51,36,"2023-12-19","01:45:00","2024-09-07","04:15:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703604261",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703603461",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2024,2024,50,50,"2023-12-12","01:30:00","2024-12-14","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703601861",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2024,2024,50,36,"2023-12-12","00:30:00","2024-09-08","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703604261",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2024,2024,1,50,"2024-09-30","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14352999361",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2024,2024,46,48,"2024-11-15","23:35:00","2024-11-25","04:30:00","Periodical",null,"",null,"High","1,5,6,7","Planned"]
["SNCF-R","13703648061",null,"< >","Pontoise - Bif de Liesse","Pontoise - Bif de Liesse",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703646061",null,"< >","Pontoise - Bif de Liesse","Pontoise - Bif de Liesse",2024,2024,50,50,"2023-12-12","01:30:00","2024-12-14","04:00:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","15338885561",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,28,35,"2024-07-08","22:25:00","2024-08-30","05:10:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15338907561",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,28,35,"2024-07-08","22:25:00","2024-08-30","05:10:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15338334161",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00","continuous",null,"",null,"High","","Planned"]
["SNCF-R","15338321361",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00","continuous",null,"",null,"High","","Planned"]
["SNCF-R","15338430561",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00","continuous",null,"",null,"High","","Planned"]
["SNCF-R","15338423761",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00","continuous",null,"",null,"High","","Planned"]
["SNCF-R","15338413761",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00","continuous",null,"",null,"High","","Planned"]
["SNCF-R","15338888761",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,28,35,"2024-07-08","22:25:00","2024-08-30","05:10:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15338846061",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,28,35,"2024-07-08","22:25:00","2024-08-30","05:10:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15338195361",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00","continuous",null,"",null,"High","","Planned"]
["SNCF-R","13703586861",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,2,50,"2024-01-08","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC Industrielles ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14345221361",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,51,36,"2023-12-19","01:45:00","2024-09-07","04:15:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703644061",null,"< >","Pontoise - Bif de Liesse","Pontoise - Bât Voyageurs",2024,2024,50,50,"2023-12-12","00:00:00","2024-12-14","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","14894106361",null,"< >","Paris-La Chapelle - Poste E","Paris-La Chapelle - Jonct Km 3,4",2024,2024,28,34,"2024-07-12","23:30:00","2024-08-19","04:30:00","continuous",null,"",null,"Major","","Planned"]
["SNCF-R","13687363461",null,"< >","Berre","Vitrolles-Aéroport-Marseille-P",2024,2024,50,40,"2023-12-12","22:35:00","2024-10-04","05:30:00","Periodical",null,"CCR OUEST P. -Etape1- : CAP V2EVIT Berre + V4G RGC (06h55 du Ma/Me au Ve/Sa)  Domaine S9, V2 EVIT Berre : ZEP G 862  Domaine S9, V4G RGC : ZEP G 28+34  Nota : Les autres voies côté Pair de Berre et de Rognac ne peuvent pas être réservées dans TCAP, elles ",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13687360661",null,"< >","Miramas - Aig Km 818,2","Vitrolles-Aéroport-Marseille-P",2024,2024,50,40,"2023-12-11","22:35:00","2024-10-04","05:30:00","Periodical",null,"CCR OUEST P. -Etape1- : CAP V1Bis Berre +1 Bis de RGC + Voie circ. Aix à RGC de 06h55  Domaine S9, V1Bis Berre : ZEP G 861+863+867   Domaine S9, V1 Bis RGC : ZEPG 29+31+49+27  Domaine S9, VU Aix-Rgc 33+29+89  Nota : les ZEPs de Berre 865 (V3+V5) ne peuven",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687355661",null,"< >","Miramas - Bât Voyageurs","Vitrolles-Aéroport-Marseille-P",2024,2024,8,24,"2024-05-28","00:00:00","2024-06-15","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13687355661",null,"< >","Miramas - Bât Voyageurs","Vitrolles-Aéroport-Marseille-P",2024,2024,8,24,"2024-02-20","00:00:00","2024-03-16","04:30:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13687372061",null,"< >","Miramas - Bât Voyageurs","Vitrolles-Aéroport-Marseille-P",2024,2024,50,40,"2023-12-11","22:35:00","2024-10-04","05:30:00","Periodical",null,"CCR OUEST P. : DEF V1 de MAS à RGC (inclus jusqu'au C3 de RGC Km 835,940) de 06h55  Etendue S9 : V1 du C653 Km 810,004 de Mas au C3 Km 835,940 de Rognac (+ du C3 Km 835,940 à la PATC Km 837,500 de Rognac = ZEP 27+85)  Domaine S9 : ZEP G Mas 99 + Les Roque",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687377261",null,"< >","Miramas - Bât Voyageurs","Vitrolles-Aéroport-Marseille-P",2024,2024,50,40,"2023-12-12","22:35:00","2024-10-03","05:30:00","Periodical",null,"CCR OUEST P. -Etape1- : DEF V2 de RGC à MAS (depuis le JI Z14/16B de RGC Km 835,940 jusqu'au C 651 de MAS Km 810,004) de 06h55 (depuis le C4 de RGC Km 836,421 au Km 835,940 JI z14/z6B)  Etendue S9 : V2 depuis le JI Z14/16B de RGC Km 835,940 au C 653 Km 81",null,"Major","2,3,4,5","Planned"]
["SNCF-R","13687374261",null,"< >","Miramas - Bât Voyageurs","Vitrolles-Aéroport-Marseille-P",2024,2024,50,40,"2023-12-11","23:45:00","2024-10-04","05:30:00","Periodical",null,"CCR OUEST P. -Etape1- : DEF V2 de RGC à MAS (depuis le JI Z14/16B de RGC Km 835,940 jusqu'au C 651 de MAS Km 810,004) de 05h45 (depuis le C4 de RGC Km 836,421 au Km 835,940 JI z14/z6B)  Etendue S9 : V2 depuis le JI Z14/16B de RGC Km 835,940 au C 653 Km 81",null,"Major","1,3,5","Planned"]
["SNCF-R","13687195461",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,50,50,"2023-12-11","10:22:00","2024-12-13","10:55:00","Periodical",null,"MC19-0027 pour calage entre 879606 et 879654 Modif par la main courante 2020 Maj-570-871 2021_SE_58 : décalage de -40mn pour avoir 879662 en SO(train rapide) et 879622 en SF (train lent), aligné V2 de Miramas à Avignon, le 19/11/2019 2022_SE_15 : vibratio",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687198661",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,9,11,"2024-02-26","09:17:00","2024-03-15","14:47:00","Periodical",null,"2024_SE_74 : vibration de +7' pour avoir FRET LDMC17 en SO (vibration imposée aussi sur 4D_AFT-CVN_009 pour maintenir l'alignement)   RPU Maintenance Voie BML VC avec B1N+Régaleuse :  Format Générique + 1h30= 09h10 /14h40 soit 05h30   Domaine S9 : DFV L C",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14696392861",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,17,48,"2024-04-27","22:10:00","2024-11-30","06:10:00","Periodical",null,"SA2024, Maint, DEF 08h00, L925 V1+V2+V1S+V2S+1Racct+2Racct, du Sa 22h10 au Di 06h10 (du 30/03 au 31/03 + 23/11 au 24/11 + 30/11 au 01/12 ) :  Etendue S9 : V1 de la PATC de CAV Km 38,695 au C507 Km 66,880 jusqu'au JI Z605/617 Km 68,130 (V1S) / V2 du C24 de",null,"Medium","6","Planned"]
["SNCF-R","13687209461",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,44,47,"2024-10-28","08:25:00","2024-11-22","16:55:00","Periodical",null,"Tvx Ppx 08h30 -de S44 à 47 - Avignon Fontcouverte exclu à Miramas exclu -  :  Tvx PPx V1+V2 (de S44 à S47), -Avignon Fontcouverte exclu à Miramas exclu- et à prendre avec 4D_AFT-CVN_028  :  Etendue S9 : V1 de la PATC Km 4,283 au C507 au Km 66,880 de Mas /",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13836688561",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,48,50,"2024-11-25","08:25:00","2024-12-13","16:55:00","Periodical",null,"Tvx PPx V1+V2 (de S48+49+50 SA2024 et 51 de 2024 sur SA2025) -Avignon Fontcouverte inclus à Miramas exclu-, à prendre avec 4C_AV_068+4C_CVN_010+4C_AFT-CVN_002+4D_AFT-CVN_029 :    Etendue S9 : V1 du Km 0+730 (Cv105 d'AFT) au Km 66+880 (C507 de Mas) et V2 a",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14737175761",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,37,43,"2024-09-09","08:35:00","2024-10-25","17:15:00","Periodical",null,"Tvx Préparatoires, Principaux, ou Finitions 08h40 -Miramas inclus à Cavaillon exclu - S37+38+S39 LU, MA+S40 JE, VE+S41 ET S39 ME, JE, VE+S40 LU, MA, ME ET S42+43 :  Etendue S9 : V1 de la PATC Km 38,695 au C507 au Km 66,880 => JI Z 605/617 km 67.837 de Mas",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14644009261",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,26,36,"2024-06-24","08:35:00","2024-09-06","16:35:00","Periodical",null,"SR Voie AMS, de S26 à S36,Tvx connexes et hors suite et S37 Tvx Préparatoires , -Cavaillon exclu à Miramas exclu- DEF de 08h00 :  Etendue S9 : V1 de la PATC Km 38,695 au C507 au Km 66,880 / V2 de la PATC Km 65,976 au C24 Km 34,100  Domaine S9 : DFV L CAV-",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687197061",null,"< >","Cavaillon - Bif ChevalBlanc","Miramas ITE SMEA",2024,2024,50,50,"2023-12-11","13:42:00","2024-12-13","15:07:00","Periodical",null,"2024_SE_16 : vibration de +7' pour avoir TER 879632 en SO  2021_SE_113 : décalage de quelques minutes pour avoir 879636 en SO et 879671 en SF et FEN21_Avignon-Cavaillon_002 à avancer pour avoir 879636 en SO pour aligner les surveillances sur l'axe  Décala",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13541700461",null,"< >","Parthenay - Bât Voyageurs","Niort - Bif de Thouars",2024,2024,50,50,"2023-12-11","12:45:00","2024-12-13","13:45:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13541701261",null,"< >","Parthenay - Bât Voyageurs","Niort - Bif de Thouars",2024,2024,20,38,"2024-05-13","07:00:00","2024-09-20","12:00:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13576578461",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:05:00","2024-12-13","11:10:00","Periodical",null,"Mise en qualité Refonte 2022",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13576579261",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:15:00","2024-12-13","11:05:00","Periodical",null,"Mise en qualité Refonte 2022",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13576580861",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,49,45,"2023-12-10","22:30:00","2024-11-07","03:50:00","Periodical",null,"Mise en qualité Refonte 2022",null,"Major","1,2,3,4,7","Planned"]
["SNCF-R","13576576861",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,49,45,"2023-12-10","23:50:00","2024-11-07","04:30:00","Periodical",null,"Mise en qualité Refonte 2022",null,"Major","1,2,3,4,7","Planned"]
["SNCF-R","14394943861",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,5,8,"2024-02-04","22:25:00","2024-02-22","04:00:00","Periodical",null,"capacités de nuit SIM V1+ V2 entre La Touche et Lusignan  Demande 2022 UTM Partie Ouest IPPC  ",null,"High","1,2,3,4,7","Planned"]
["SNCF-R","14394548061",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,2,50,"2024-01-08","09:50:00","2024-12-12","14:50:00","Periodical",null,"capacités de jour monovoie Voie 1 entre La Touche et Lusignan  Demande 2022 UTM Partie Ouest IPPC",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14394701561",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,9,40,"2024-02-26","10:05:00","2024-10-03","14:55:00","Periodical",null,"capacités de jour monovoie Voie 2 entre La Touche et Lusignan  Demande 2022 UTM Partie Ouest IPPC",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14689751061",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,40,42,"2024-10-05","23:00:00","2024-10-19","06:30:00","Periodical",null,"Nuit de sa/di besoin de maintenance",null,"Medium","6","Planned"]
["SNCF-R","15125792461",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,5,8,"2024-02-04","21:40:00","2024-02-22","04:40:00","Periodical",null,"capacités de nuit monovoie V1 ou V2 entre La Touche et Lusignan  Demande 2022 UTM Ouest IPPC  ",null,"High","1,2,3,4,7","Planned"]
["SNCF-R","13576579261",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,50,50,"2024-03-07","10:15:00","2024-03-13","11:05:00","Periodical",null,"Mise en qualité Refonte 2022",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13576578461",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,50,50,"2024-03-07","10:05:00","2024-03-13","11:10:00","Periodical",null,"Mise en qualité Refonte 2022",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15310152661",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,15,24,"2024-04-08","22:20:00","2024-06-13","05:10:00","Periodical",null,"RR + relevage  SIM V1+V2  Zep 8383 V1 et 702 V2 + Sr Mezeau Lusignan V1 + V2",null,"High","1,2,3,4","Planned"]
["SNCF-R","13886927061",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,14,24,"2024-04-07","22:25:00","2024-06-16","05:25:00","Periodical",null,"RR + relevage  SIM V1+V2  Zep 8383 V1 et 702 V2 + Sr Mezeau Lusignan V1 + V2",null,"Medium","7","Planned"]
["SNCF-R","14376091661",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","23:20:00","2024-12-13","04:55:00","Periodical",null,"JUVISY C102  à  CHOISY LE ROI C528",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14376033161",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","22:45:00","2024-12-13","05:50:00","Periodical",null,"JUVISY C104 15.905 21:10 05:50 à  PAZ(CLR) C728 10,320 21:10 05:50",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14719463761",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,3,42,"2024-01-19","23:20:00","2024-10-14","04:55:00","Periodical",null,"",null,"Major","1,5,6,7","Planned"]
["SNCF-R","13575986361",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,21,41,"2024-05-26","23:30:00","2024-10-13","05:00:00","Periodical",null,"JY C104 A PAZ C728     ",null,"Medium","6,7","Planned"]
["SNCF-R","14719475461",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,21,41,"2024-05-25","10:15:00","2024-10-13","15:15:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","15133556461",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,18,44,"2024-04-30","23:20:00","2024-10-31","04:25:00","Periodical",null,"JUVISY C102  à  CHOISY LE ROI C528",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14376091661",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2024-11-13","23:20:00","2024-11-14","04:55:00","Periodical",null,"JUVISY C102  à  CHOISY LE ROI C528",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13575966361",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","00:10:00","2024-12-09","03:55:00","Periodical",null,"",null,"Major","1","Planned"]
["SNCF-R","13575964761",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","00:25:00","2024-12-09","04:25:00","Periodical",null,"",null,"Major","1","Planned"]
["SNCF-R","14700315261",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,36,42,"2024-09-08","23:45:00","2024-10-20","05:00:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","13575967961",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2024-09-27","23:13:00","2024-09-27","05:10:00","Periodical",null,"6h par voie sur V1 et V2 dont min 3h10 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy) 3690 ouvrant 142144 (ou 141142) et 143844 (ou 141844) circulent V2bis                    ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13575986361",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,21,41,"2024-09-28","23:30:00","2024-09-29","05:00:00","Periodical",null,"JY C104 A PAZ C728     ",null,"Medium","6,7","Planned"]
["SNCF-R","14717993961",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,39,39,"2024-09-29","00:05:00","2024-09-29","04:30:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","14651501661",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2024-09-27","23:20:00","2024-09-27","05:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14651501661",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","23:20:00","2024-12-13","05:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13575967961",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","23:13:00","2024-12-13","05:10:00","Periodical",null,"6h par voie sur V1 et V2 dont min 3h10 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy) 3690 ouvrant 142144 (ou 141142) et 143844 (ou 141844) circulent V2bis                    ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13575968761",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,51,36,"2023-12-19","00:10:00","2024-09-07","04:20:00","Periodical",null,"6h 2V/4 dont 4h de sim. et Incompatible avec fenêtre longue voies dir sur Choisy<->Juvisy(Choisy-Juvisy)                                               ",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","14651501661",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2024-04-24","23:20:00","2024-04-29","05:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13575967961",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2024-04-24","23:13:00","2024-04-30","05:10:00","Periodical",null,"6h par voie sur V1 et V2 dont min 3h10 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy) 3690 ouvrant 142144 (ou 141142) et 143844 (ou 141844) circulent V2bis                    ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14561746161",null,"< >","Choisy-le-Roi - Bât Voyageurs","Villeneuve-le-Roi",2024,2024,50,50,"2023-12-12","08:44:00","2024-12-10","09:44:00","Periodical",null,"PAZ(CLR) C727  à  PAZ(CLR) S10,7",null,"Major","2","Planned"]
["SNCF-R","14376274561",null,"< >","Choisy-le-Roi - E/S V1V","Villeneuve-le-Roi",2024,2024,50,50,"2023-12-11","23:18:00","2024-12-13","05:25:00","Periodical",null,"CHOISY LE ROI JIZ 241/245  à  PANCARTE ARRET 10.728",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14375806461",null,"< >","Choisy-le-Roi - E/S V1V","Villeneuve-le-Roi",2024,2024,50,50,"2023-12-11","22:45:00","2024-12-13","05:47:00","Periodical",null,"PAZ(CLR) C725 à  PANCARTE ARRET 10.728",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14761032761",null,"< >","Choisy-le-Roi - E/S V1V","Villeneuve-le-Roi",2024,2024,10,11,"2024-03-08","23:20:00","2024-03-11","05:20:00","Periodical",null,"CHOISY LE ROI JIZ 241/245 à  PAZ (CLR) PATC",null,"Medium","1,5,6,7","Planned"]
["SNCF-R","15133515261",null,"< >","Choisy-le-Roi - E/S V1V","Villeneuve-le-Roi",2024,2024,18,44,"2024-04-30","23:15:00","2024-10-31","05:05:00","Periodical",null,"CHOISY LE ROI JIZ 241/245  à  PANCARTE ARRET 10.728",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14725523361",null,"< >","Choisy-le-Roi - E/S V1V","Choisy-le-Roi - Déviation Sud",2024,2024,22,47,"2024-06-01","00:00:00","2024-11-18","05:30:00","Periodical",null,"PAZ(CLR) C725 à  PAZ(CLR) C727",null,"High","1,6,7","Planned"]
["SNCF-R","14481961961",null,"< >","Corbeil-Essonnes - Bif Km 33","Essonnes-Robinson",2024,2024,50,27,"2023-12-11","23:10:00","2024-07-05","04:30:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14482116961",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,2,18,"2024-01-08","21:15:00","2024-05-03","05:45:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14483016661",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,4,10,"2024-01-22","08:42:00","2024-03-08","17:17:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14482973261",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,19,25,"2024-05-06","08:42:00","2024-06-21","17:17:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14482340961",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,28,31,"2024-07-08","23:10:00","2024-08-02","04:30:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14482271061",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,26,27,"2024-06-24","22:00:00","2024-07-05","05:40:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14481897861",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,50,51,"2023-12-11","21:45:00","2023-12-22","05:41:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14552785561",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,37,38,"2024-09-13","23:00:00","2024-09-20","05:40:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14392325361",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,49,49,"2024-12-02","22:00:00","2024-12-08","03:45:00","Periodical",null,"",null,"Medium","6","Planned"]
["SNCF-R","14392347461",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,49,49,"2024-12-02","23:00:00","2024-12-08","04:00:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","13690608761",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,50,49,"2024-07-08","23:45:00","2024-08-23","04:25:00","Periodical",null,"Modification horaire du 1er train au départ de COE 129600 (04h25)",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690608761",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,50,49,"2024-09-20","23:45:00","2024-12-06","04:25:00","Periodical",null,"Modification horaire du 1er train au départ de COE 129600 (04h25)",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15242625161",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,42,43,"2024-10-18","23:45:00","2024-10-21","04:25:00","Periodical",null,"",null,"Medium","1,5,6,7","Planned"]
["SNCF-R","13690608761",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,50,49,"2023-12-11","23:45:00","2024-12-08","04:25:00","Periodical",null,"Modification horaire du 1er train au départ de COE 129600 (04h25)",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14868014661",null,"< >","Villeneuve-St-Georges-Triage - Poste 3","Villeneuve-St-Georges-Triage - Carré 11",2024,2024,22,23,"2024-05-31","23:15:00","2024-06-03","04:00:00","Periodical",null,"",null,"Medium","1,5,6,7","Planned"]
["SNCF-R","13690515961",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - Panneau 19",2024,2024,1,49,"2024-01-02","10:35:00","2024-12-04","11:20:00","Periodical",null,"Gpt: 9928 ",null,"High","2,3","Planned"]
["SNCF-R","15289056861",null,"< >","Villeneuve-St-Georges-Triage - FSC Réception","Villeneuve-St-Georges-Triage - Atelier Mat",2024,2024,22,23,"2024-05-27","10:00:00","2024-06-07","14:00:00","Periodical",null,"ZEP 176 de VTRP3",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15231590661",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - Bif Km 8,9/9,1",2024,2024,12,12,"2024-03-18","21:55:00","2024-03-18","04:40:00","Periodical",null,"",null,"Medium","1","Planned"]
["SNCF-R","13690517761",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - Carré 55",2024,2024,5,45,"2024-02-01","10:35:00","2024-11-07","11:20:00","Periodical",null,"Gpt: 9933   ",null,"Medium","2,4","Planned"]
["SNCF-R","14680188361",null,"< >","Villeneuve-St-Georges-Triage - Bif Km 8,9/9,1","Villeneuve-St-Georges-Triage - Carré 55",2024,2024,2,5,"2024-01-08","23:15:00","2024-02-02","04:40:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13690513361",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - FSC Départ Nord",2024,2024,52,36,"2024-07-08","23:30:00","2024-09-06","04:50:00","Periodical",null,"s30:ve26/sa27 juillet + s31: lu29/ma30 à ve02/sa03 août + s32: lu05/ma06 à ve09/sa10 août + s35:lu26/ma27 à ve30/sa31 août + s36: lu02/ma03 à ve06/sa07 septembre  En cas de nécessité pour TN ou impératif pour assurer la sécurité technique des installation",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690513361",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - FSC Départ Nord",2024,2024,52,36,"2023-12-26","23:30:00","2024-01-05","04:50:00","Periodical",null,"s30:ve26/sa27 juillet + s31: lu29/ma30 à ve02/sa03 août + s32: lu05/ma06 à ve09/sa10 août + s35:lu26/ma27 à ve30/sa31 août + s36: lu02/ma03 à ve06/sa07 septembre  En cas de nécessité pour TN ou impératif pour assurer la sécurité technique des installation",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14861863261",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,3,46,"2024-01-20","23:20:00","2024-11-16","04:40:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","14862348261",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,11,16,"2024-03-15","23:15:00","2024-04-21","13:15:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","14862449961",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,21,24,"2024-05-25","23:20:00","2024-06-15","04:40:00","Periodical",null,"",null,"Medium","6","Planned"]
["SNCF-R","15281827561",null,"< >","Villeneuve-St-Georges-Triage - Atelier Mat","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,16,17,"2024-04-15","09:35:00","2024-04-26","15:05:00","Periodical",null,"ZEP 156+158",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14778744361",null,"< >","Villeneuve-St-Georges-Triage - Bif Km 8,9/9,1","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,41,43,"2024-10-12","22:00:00","2024-10-21","04:40:00","Periodical",null,"",null,"Medium","1,6,7","Planned"]
["SNCF-R","14778631061",null,"< >","Villeneuve-St-Georges-Triage - FSC Débranche","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,39,43,"2024-09-23","23:15:00","2024-10-25","04:40:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14778707861",null,"< >","Villeneuve-St-Georges-Triage - FSC Débranche","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,40,41,"2024-10-04","23:15:00","2024-10-07","04:40:00","Periodical",null,"",null,"Medium","1,5,6,7","Planned"]
["SNCF-R","15243804161",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 15,9",2024,2024,10,11,"2024-03-08","23:15:00","2024-03-11","04:40:00","Periodical",null,"",null,"Medium","1,5,6,7","Planned"]
["SNCF-R","13690593961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,4,50,"2024-09-23","23:15:00","2024-10-11","04:40:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690593961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,4,50,"2024-01-22","23:15:00","2024-12-13","04:40:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690593961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,4,50,"2024-01-22","23:15:00","2024-12-13","04:40:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14862365361",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,11,16,"2024-03-15","23:15:00","2024-04-21","13:15:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","14861910061",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,3,46,"2024-01-20","23:20:00","2024-11-16","04:40:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","14862454961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,21,24,"2024-05-25","23:20:00","2024-06-15","04:40:00","Periodical",null,"",null,"Medium","6","Planned"]
["SNCF-R","14517655461",null,"< >","Villeneuve-St-Georges - Bât Voyageurs","Montgeron-Crosne",2024,2024,43,45,"2024-10-21","21:50:00","2024-11-08","05:40:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13690597761",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,1,34,"2024-07-08","23:15:00","2024-08-23","04:40:00","Periodical",null,"S1/2023",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15702660161",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,39,39,"2024-09-27","23:15:00","2024-09-27","04:40:00","Periodical",null,"",null,"Medium","3,5","Planned"]
["SNCF-R","13690590761",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,50,49,"2023-12-11","23:15:00","2024-12-08","04:40:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690591961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,3,38,"2024-01-15","23:15:00","2024-09-22","04:40:00","Periodical",null,"ZEP 665 libre",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690597761",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,1,34,"2024-01-02","23:15:00","2024-01-05","04:40:00","Periodical",null,"S1/2023",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13690590761",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,50,49,"2023-12-11","23:15:00","2024-12-06","04:40:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690591961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,3,38,"2024-01-15","23:15:00","2024-09-20","04:40:00","Periodical",null,"ZEP 665 libre",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14467346161",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,24,27,"2024-06-10","01:00:00","2024-07-01","03:00:00","Periodical",null,"",null,"Medium","1,7","Planned"]
["SNCF-R","13690526361",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,39,47,"2024-11-04","10:26:00","2024-11-22","15:30:00","Periodical",null,"Du 151427 au 151554. ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14517858761",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,48,50,"2024-11-25","21:30:00","2024-12-13","05:30:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14482200561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,2,3,"2024-01-08","22:30:00","2024-01-19","05:30:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14482256661",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,11,16,"2024-03-11","21:15:00","2024-04-18","05:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14481956861",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,18,"2023-12-11","23:15:00","2024-05-03","05:30:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14552666061",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,37,37,"2024-09-11","22:25:00","2024-09-12","05:25:00","Periodical",null,"",null,"Medium","3,4","Planned"]
["SNCF-R","13690524561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,50,"2024-01-17","23:30:00","2024-11-01","05:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690526361",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,39,47,"2024-09-23","10:26:00","2024-09-27","15:30:00","Periodical",null,"Du 151427 au 151554. ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690523761",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,49,"2023-12-11","13:05:00","2024-12-06","13:30:00","Periodical",null,"11401806 fenêtre intercaler entre 151536 et 151538                   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690525561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,49,"2023-12-11","11:50:00","2024-12-06","13:26:00","Periodical",null,"11401805 MC18-255 pour sillon cadre PNSO05 le 18/11/16                     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690527361",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,49,21,"2023-12-10","23:45:00","2024-05-26","05:10:00","Periodical",null,"Plage corrective en nuit de di/lu ",null,"High","7","Planned"]
["SNCF-R","13690524561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-13","05:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690526361",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,39,47,"2024-09-23","10:26:00","2024-11-24","15:30:00","Periodical",null,"Du 151427 au 151554. ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690524561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-13","05:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13690524561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,50,"2024-07-08","23:30:00","2024-07-23","05:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689816861",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-03-11","09:45:00","2024-10-18","15:45:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15196873161",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,10,13,"2024-03-04","08:00:00","2024-03-22","16:00:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15196897061",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,10,13,"2024-03-04","10:00:00","2024-03-22","13:35:00","Periodical",null,"Avec le 1610",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689815261",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-03-11","08:45:00","2024-10-18","14:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15867245361",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,38,38,"2024-09-16","22:00:00","2024-09-19","04:00:00","Periodical",null,"",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","13689816061",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-10-14","08:45:00","2024-10-18","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689814461",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-10-14","10:00:00","2024-10-18","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15867293561",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,38,42,"2024-09-22","22:00:00","2024-10-20","04:00:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","13689816861",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-01-29","09:45:00","2024-10-20","15:45:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15196873161",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,10,13,"2024-03-04","08:00:00","2024-03-31","16:00:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689815261",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-20","14:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15196897061",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,10,13,"2024-03-04","10:00:00","2024-03-31","13:35:00","Periodical",null,"Avec le 1610",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689816061",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-20","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689814461",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-01-29","10:00:00","2024-10-20","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15236674761",null,"< >","Sens - Poste 2","Sens - ITE ZI",2024,2024,38,38,"2024-09-16","23:00:00","2024-09-19","05:00:00","Periodical",null,"",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","14687105161",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","10:00:00","2024-03-29","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14687095061",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","08:00:00","2024-03-29","16:00:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15200936961",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,11,11,"2024-03-16","08:55:00","2024-03-17","16:30:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","14687118361",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,11,12,"2024-03-16","08:55:00","2024-03-18","06:00:00","Periodical",null,"",null,"Medium","1,6,7","Planned"]
["SNCF-R","15200952361",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,11,11,"2024-03-17","19:10:00","2024-03-17","06:00:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","13689801861",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,50,44,"2023-12-11","02:32:00","2024-11-03","05:47:00","Periodical",null,"2V/4 => 1 voie dans chaque sens Modification le 05/02/2019 : Typologie passée de Jour à Nuit non passe-minuit",null,"High","1","Planned"]
["SNCF-R","13689797861",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,51,45,"2023-12-18","02:32:00","2024-11-10","05:47:00","Periodical",null,"2V/4 => 1 voie dans chaque sens Modification le 05/02/2019 : Typologie passée de Jour à Nuit non passe-minuit",null,"High","1","Planned"]
["SNCF-R","13689800261",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,52,50,"2023-12-26","08:51:00","2024-12-13","14:51:00","Periodical",null,"Prise de voie V1   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689798661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,50,49,"2023-12-11","08:51:00","2024-12-08","14:51:00","Periodical",null,"Prise de voie V1bis ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689803461",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-20","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689809261",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,20,43,"2024-05-19","23:00:00","2024-10-26","05:00:00","Periodical",null,"",null,"High","1,2,3,4,7","Planned"]
["SNCF-R","14687105161",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","10:00:00","2024-03-31","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689807661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,19,48,"2024-05-12","23:00:00","2024-11-29","05:00:00","Periodical",null,"",null,"High","1,2,3,4,5,7","Planned"]
["SNCF-R","13689802661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-01-29","10:00:00","2024-10-20","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14687095061",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","08:00:00","2024-03-31","16:00:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689806861",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,16,16,"2024-04-15","09:30:00","2024-04-21","15:30:00","Periodical",null,"Besoins Caténaires : - Secteur Laroche Voie de service Impair - Secteur Cezy Laroche voie 1bis   Besoins ZEP : - Toutes les ZEP du faisceau Bourgogne Impair et Accès  - Toutes les ZEP du faisceau de Préblin + ZEP 481 et Accès par bourgogne faisceau impair",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15202273861",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,33,49,"2024-08-12","10:00:00","2024-12-06","16:31:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689803461",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-09-09","08:45:00","2024-10-18","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15645800061",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,38,45,"2024-09-16","10:00:00","2024-11-08","16:31:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689802661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-09-09","10:00:00","2024-10-18","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689806861",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,16,16,"2024-04-15","09:30:00","2024-04-19","15:30:00","Periodical",null,"Besoins Caténaires : - Secteur Laroche Voie de service Impair - Secteur Cezy Laroche voie 1bis   Besoins ZEP : - Toutes les ZEP du faisceau Bourgogne Impair et Accès  - Toutes les ZEP du faisceau de Préblin + ZEP 481 et Accès par bourgogne faisceau impair",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13689798661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,50,49,"2024-04-22","08:51:00","2024-04-26","14:51:00","Periodical",null,"Prise de voie V1bis ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14687095061",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","08:00:00","2024-03-22","16:00:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14687105161",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","10:00:00","2024-03-22","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689800261",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,52,50,"2024-01-22","08:51:00","2024-02-23","14:51:00","Periodical",null,"Prise de voie V1   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689803461",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-18","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689802661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-01-29","10:00:00","2024-10-18","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689807661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,19,48,"2024-09-16","23:00:00","2024-09-19","05:00:00","Periodical",null,"",null,"High","1,2,3,4,5,7","Planned"]
["SNCF-R","13689798661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,50,49,"2024-05-06","08:51:00","2024-07-14","14:51:00","Periodical",null,"Prise de voie V1bis ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689799461",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,51,45,"2023-12-18","00:37:00","2024-11-10","03:20:00","Periodical",null,"2V/4 => 1 voie dans chaque sens Modification le 05/02/2019 : Typologie passée de Jour à Nuit non passe-minuit",null,"High","1","Planned"]
["SNCF-R","13689797061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,50,50,"2023-12-11","08:51:00","2024-12-13","14:51:00","Periodical",null,"Prise de voie V2bis ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689804261",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-20","14:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689810061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,20,43,"2024-05-19","22:00:00","2024-10-26","04:00:00","Periodical",null,"",null,"High","1,2,3,4,7","Planned"]
["SNCF-R","13689806061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,17,17,"2024-04-22","09:30:00","2024-04-28","15:30:00","Periodical",null,"Besoins Caténaires : - Secteur Laroche Voie de service Pair - Secteur Laroche Cezy voie 2bis - Sel 2320 bis du Secteur Laroche St Florentin Voie 2bis (Voie 2 Racco) - Sel 2321bis +131 du Secteur  Laroche St Florentin Voie 1bis (Voie 1 Racco + Voie A Racco",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15201970961",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,38,45,"2024-09-21","01:00:00","2024-11-04","04:00:00","Periodical",null,"",null,"High","1,6,7","Planned"]
["SNCF-R","13689804261",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,5,42,"2024-09-09","08:45:00","2024-10-18","14:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15652881061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,33,49,"2024-08-18","22:00:00","2024-12-08","04:00:00","Periodical",null,"",null,"High","7","Planned"]
["SNCF-R","13689804261",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-18","14:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689806061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,17,17,"2024-04-22","09:30:00","2024-04-26","15:30:00","Periodical",null,"Besoins Caténaires : - Secteur Laroche Voie de service Pair - Secteur Laroche Cezy voie 2bis - Sel 2320 bis du Secteur Laroche St Florentin Voie 2bis (Voie 2 Racco) - Sel 2321bis +131 du Secteur  Laroche St Florentin Voie 1bis (Voie 1 Racco + Voie A Racco",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15238035061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,4,8,"2024-01-22","10:45:00","2024-02-23","11:05:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15238038761",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,4,8,"2024-01-22","12:45:00","2024-02-23","13:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15201970961",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,38,45,"2024-09-21","01:00:00","2024-10-21","04:00:00","Periodical",null,"",null,"High","1,6,7","Planned"]
["SNCF-R","13689797061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,50,50,"2024-04-15","08:51:00","2024-04-19","14:51:00","Periodical",null,"Prise de voie V2bis ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689797061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,50,50,"2024-05-06","08:51:00","2024-07-14","14:51:00","Periodical",null,"Prise de voie V2bis ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689931461",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 165,9",2024,2024,50,32,"2024-03-27","08:51:00","2024-04-19","14:51:00","Periodical",null,"1 voie par sens Prise de voie V1bis       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689925661",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 165,9",2024,2024,51,49,"2023-12-18","02:47:00","2024-12-02","06:00:00","Periodical",null,"2V/4 => 1 voie dans chaque sens               ",null,"High","1","Planned"]
["SNCF-R","13689931461",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 165,9",2024,2024,50,32,"2023-12-11","08:51:00","2024-08-11","14:51:00","Periodical",null,"1 voie par sens Prise de voie V1bis       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689923061",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 165,9",2024,2024,46,46,"2024-11-14","12:55:00","2024-11-15","14:10:00","Periodical",null,"11401052 Incompatible avec Fenêtre générique V1 pour eviter la sim de 1h                             ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13689935461",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 165,9",2024,2024,20,43,"2024-05-19","23:00:00","2024-10-26","05:00:00","Periodical",null,"",null,"High","1,2,3,4,7","Planned"]
["SNCF-R","13689922261",null,"< >","Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,1,30,"2024-03-25","08:51:00","2024-03-26","14:51:00","Periodical",null,"1 voie par sens Prise de voie V2                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689933061",null,"< >","Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,50,48,"2023-12-11","00:19:00","2024-12-01","03:05:00","Periodical",null,"2V/4 => 1 voie dans chaque sens               ",null,"High","1","Planned"]
["SNCF-R","13689922261",null,"< >","Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,1,30,"2024-01-02","08:51:00","2024-07-28","14:51:00","Periodical",null,"1 voie par sens Prise de voie V2                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689924661",null,"< >","Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,1,7,"2024-01-02","09:53:00","2024-02-18","13:45:00","Periodical",null,"V2 + V2BIS dans l'ombre de la fenêtre générique St Florenton tonnerre => Décision N2 du 02/10/2015 TO 891352 / TF 891354 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689928061",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,50,32,"2024-03-27","08:51:00","2024-04-19","14:51:00","Periodical",null,"1 voie par sens Prise de voie V2bis                                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14552356561",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,35,35,"2024-08-26","08:15:00","2024-08-30","16:15:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13689926461",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,51,49,"2023-12-18","00:19:00","2024-12-02","03:05:00","Periodical",null,"2V/4 => 1 voie dans chaque sens             ",null,"High","1","Planned"]
["SNCF-R","13689928061",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,50,32,"2023-12-11","08:51:00","2024-08-11","14:51:00","Periodical",null,"1 voie par sens Prise de voie V2bis                                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689936261",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,20,43,"2024-05-19","22:00:00","2024-10-26","04:00:00","Periodical",null,"",null,"High","1,2,3,4,7","Planned"]
["SNCF-R","13689934661",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,19,41,"2024-05-12","22:00:00","2024-10-10","04:00:00","Periodical",null,"",null,"High","1,2,3,4,7","Planned"]
["SNCF-R","13689927261",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,46,46,"2024-11-14","12:20:00","2024-11-17","13:05:00","Periodical",null,"11401082  Incompatible avec Fenêtre générique V2 pour eviter la sim de 1h                           ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13689929661",null,"< >","Laroche-Migennes - Voies 4 Ã  10","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,46,46,"2024-11-12","12:20:00","2024-11-13","13:05:00","Periodical",null,"11401054 Incompatible avec Fenêtre générique V2BIS pour eviter la sim de 1h                               ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15222684661",null,"< >","Brienon","St-Florentin-Vergigny - Bât Voyageurs",2024,2024,36,36,"2024-09-02","10:00:00","2024-09-03","16:00:00","Periodical",null,"",null,"Medium","1,2","Planned"]
["SNCF-R","13689928861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bât Voyageurs",2024,2024,46,46,"2024-11-12","12:55:00","2024-11-13","14:10:00","Periodical",null,"11401026 Incompatible avec Fenêtre générique V1BIS pour eviter la sim de 1h                                     ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14552398361",null,"< >","Brienon","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,35,35,"2024-08-26","08:15:00","2024-08-30","16:15:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14390397161",null,"< >","Brienon","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,49,37,"2023-12-10","23:10:00","2024-09-14","04:50:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","14606420461",null,"< >","Brienon","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,45,45,"2024-11-10","22:10:00","2024-11-10","04:50:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","14390276661",null,"< >","Brienon","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,49,49,"2023-12-10","00:00:00","2023-12-10","04:50:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","14552276461",null,"< >","Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,34,34,"2024-08-19","08:15:00","2024-08-23","16:15:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15195439161",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,19,45,"2024-09-30","10:00:00","2024-10-31","17:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195341161",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,17,50,"2024-04-22","10:00:00","2024-12-06","16:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689923861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,1,30,"2024-03-25","08:51:00","2024-03-26","14:51:00","Periodical",null,"1 voie par sens Prise de voie V1   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689923861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,1,30,"2024-03-11","08:51:00","2024-03-18","14:51:00","Periodical",null,"1 voie par sens Prise de voie V1   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15202374061",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,39,39,"2024-09-28","08:00:00","2024-09-29","18:00:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","13689932261",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,50,48,"2023-12-11","02:47:00","2024-12-01","06:00:00","Periodical",null,"2V/4 => 1 voie dans chaque sens             ",null,"High","1","Planned"]
["SNCF-R","13689923861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,1,30,"2024-01-02","08:51:00","2024-07-28","14:51:00","Periodical",null,"1 voie par sens Prise de voie V1   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689930461",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,1,7,"2024-01-02","09:16:00","2024-02-18","13:26:00","Periodical",null,"V1 + V1BIS  dans l'ombre de la fenêtre générique St Florenton tonnerre => Décision N2 du 02/10/2015 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195341161",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,17,50,"2024-04-22","10:00:00","2024-12-13","16:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195439161",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,19,45,"2024-05-06","10:00:00","2024-11-07","17:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689941861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,18,37,"2024-05-05","23:05:00","2024-09-15","04:45:00","Periodical",null,"Entre 5789 et 5790 ",null,"High","7","Planned"]
["SNCF-R","13689933861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,19,41,"2024-05-12","23:00:00","2024-10-10","05:00:00","Periodical",null,"Accord derrière 5789",null,"High","1,2,3,4,7","Planned"]
["SNCF-R","14552340761",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,34,34,"2024-08-19","08:15:00","2024-08-23","16:15:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14390402661",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","St-Florentin-Vergigny - Voie 3 Garage",2024,2024,49,37,"2023-12-10","23:10:00","2024-09-14","04:50:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","14606741261",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","St-Florentin-Vergigny - Voie 3 Garage",2024,2024,11,12,"2024-03-14","08:51:00","2024-03-21","14:51:00","Periodical",null,"",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","14390257261",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","St-Florentin-Vergigny - Voie 3 Garage",2024,2024,49,49,"2023-12-10","00:00:00","2023-12-10","04:50:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","14606406461",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","St-Florentin-Vergigny - Voie 3 Garage",2024,2024,45,45,"2024-11-10","22:10:00","2024-11-10","04:50:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","14606711861",null,"< >","Brienon","St-Florentin-Vergigny - Voie 4 Garage",2024,2024,11,12,"2024-03-12","08:51:00","2024-03-20","14:51:00","Periodical",null,"",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","15222787761",null,"< >","Brienon","St-Florentin-Vergigny - Voie 4 Garage",2024,2024,36,36,"2024-09-02","10:00:00","2024-09-03","16:00:00","Periodical",null,"",null,"Medium","1,2","Planned"]
["SNCF-R","15237953161",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Toucy-Ville - Bât Voyageurs",2024,2024,19,19,"2024-05-06","23:20:00","2024-05-10","05:40:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15231606061",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Toucy-Ville - Bât Voyageurs",2024,2024,12,12,"2024-03-19","23:20:00","2024-03-21","05:40:00","Periodical",null,"",null,"Medium","2,3,4","Planned"]
["SNCF-R","15195840061",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,8,16,"2024-02-19","09:45:00","2024-04-21","15:45:00","Periodical",null,"Voie 1 OU voie 2  - Passage possible en bana du 199 au 212, en dehors du domaine de  la SR Cat",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195882861",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,17,18,"2024-04-22","09:45:00","2024-05-05","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15195891061",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,19,27,"2024-05-06","09:45:00","2024-07-07","16:50:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195910761",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,33,47,"2024-08-12","09:36:00","2024-11-24","16:25:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195918761",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,38,45,"2024-09-16","09:36:00","2024-11-07","17:25:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195882861",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,17,18,"2024-04-22","09:45:00","2024-05-03","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15195918761",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,38,45,"2024-09-30","09:36:00","2024-10-31","17:25:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195840061",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,8,16,"2024-04-15","09:45:00","2024-04-19","15:45:00","Periodical",null,"Voie 1 OU voie 2  - Passage possible en bana du 199 au 212, en dehors du domaine de  la SR Cat",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195910761",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,33,47,"2024-10-04","09:36:00","2024-11-01","16:25:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689881261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00","Periodical",null,"Coupure de 06h00 IHM1 pendant la Mise En Service",null,"Medium","6","Planned"]
["SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2024-01-15","10:35:00","2024-02-02","14:35:00","Periodical",null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14127821161",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,38,45,"2024-09-16","09:30:00","2024-11-07","17:30:00","Periodical",null,"TO: 9261     TF: 17764",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14382904161",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,33,50,"2024-08-13","09:50:00","2024-12-13","15:50:00","Periodical",null,"TO: 17756   TF: Sans",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14382883761",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,35,49,"2024-08-26","09:50:00","2024-12-06","16:50:00","Periodical",null,"TO: 17756    TF: Sans",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14997595861",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,38,45,"2024-09-20","09:30:00","2024-11-08","17:00:00","Periodical",null,"TO: 9261     TF: 6706",null,"High","5","Planned"]
["SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2024-08-12","10:35:00","2024-08-12","14:35:00","Periodical",null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2024-10-23","10:35:00","2024-10-24","14:35:00","Periodical",null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2024-06-17","10:35:00","2024-06-21","14:35:00","Periodical",null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13861527461",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,14,14,"2024-04-02","10:35:00","2024-04-05","14:35:00","Periodical",null,"Utilisation des 4 Pas au lieu des 2 autorisés par la 4F_BSB-DN_001  Circulation des trains en bana sur la voie non utilisée par les travaux.  Croisement possible à Malain et Plombières",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14127821161",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,38,45,"2024-09-30","09:30:00","2024-10-10","17:30:00","Periodical",null,"TO: 9261     TF: 17764",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14382883761",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,35,49,"2024-11-25","09:50:00","2024-11-29","16:50:00","Periodical",null,"TO: 17756    TF: Sans",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15111243161",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,9,9,"2024-02-26","13:25:00","2024-02-29","14:25:00","Periodical",null,"TO: 891907    TF: 9268",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","13689877261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,11,11,"2024-03-16","12:00:00","2024-03-16","11:40:00","Periodical",null,"   T0: 9211 du Sa        TF: 9211 du Di  (Amplitude initiale Coupure de 24h00  Abaisser à 23h40 pour le SA2023   )",null,"Medium","6","Planned"]
["SNCF-R","15111256061",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,9,17,"2024-02-26","11:10:00","2024-04-25","12:15:00","Periodical",null,"TO: 6703     TF: 891904",null,"High","1,2,3,4","Planned"]
["SNCF-R","15111252961",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,13,13,"2024-03-25","10:20:00","2024-03-28","12:00:00","Periodical",null,"TO: 9206   TF: 9210",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","15138737861",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,15,16,"2024-04-13","23:50:00","2024-04-21","04:40:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","14928112061",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,44,44,"2024-11-02","19:50:00","2024-11-02","13:10:00","Periodical",null,"Voie 1 + 2  TO: 17766    TF: 891375/6704",null,"Medium","6","Planned"]
["SNCF-R","14997595861",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,38,45,"2024-10-04","09:30:00","2024-10-11","17:00:00","Periodical",null,"TO: 9261     TF: 6706",null,"High","5","Planned"]
["SNCF-R","15138724361",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,15,16,"2024-04-13","00:45:00","2024-04-20","04:30:00","Periodical",null,"",null,"Medium","6","Planned"]
["SNCF-R","14642076061",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,"Medium","1","Planned"]
["SNCF-R","13689879261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00","Periodical",null,"Maintenance IHM 1 ",null,"Medium","1","Planned"]
["SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2024-04-08","10:35:00","2024-04-26","14:35:00","Periodical",null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14366709061",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00","Periodical",null,"MES LGV+",null,"Medium","7","Planned"]
["SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2023-12-11","10:35:00","2024-12-13","14:35:00","Periodical",null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689868661",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,33,"2023-12-17","00:05:00","2024-08-18","02:45:00","Periodical",null,"11401110 Corrective activable en même temps que sur la V1, a condition que la simultanée n'impacte pas de sillon                  ",null,"High","7","Planned"]
["SNCF-R","13689871261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,52,34,"2023-12-27","11:17:00","2024-08-23","12:01:00","Periodical",null,"11401058 Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689869461",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,52,34,"2023-12-26","10:41:00","2024-08-23","11:53:00","Periodical",null,"11401030 Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689872061",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,51,34,"2023-12-18","02:07:00","2024-08-19","05:21:00","Periodical",null,"11401109 Corrective activable en même temps que sur la V2, a condition que la simultanée n'impacte pas de sillon                             ",null,"High","1","Planned"]
["SNCF-R","14753954761",null,"< >","Dijon-Ville - C4104","Dijon-Ville - Aiguilles Nord",2024,2024,26,26,"2024-06-24","10:40:00","2024-06-28","15:15:00","Periodical",null,"En complément de la 4C_DN_194",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14753882061",null,"< >","Dijon-Ville - C4104","Dijon-Ville - Aiguilles Nord",2024,2024,10,10,"2024-03-10","22:15:00","2024-03-10","04:30:00","Periodical",null,"En complément de la 4C_DN_183",null,"Medium","7","Planned"]
["SNCF-R","13794550361",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00","Periodical",null,"Coupure de 06h00 IHM1 pendant la Mise En Service",null,"Medium","6","Planned"]
["SNCF-R","14382966161",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,33,50,"2024-08-13","08:00:00","2024-12-13","17:00:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14389425161",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,35,49,"2024-08-26","08:00:00","2024-12-06","18:30:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689873861",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00","Periodical",null,"Maintenace IHM 04h00   ",null,"Medium","1","Planned"]
["SNCF-R","14642192761",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   ",null,"Medium","1","Planned"]
["SNCF-R","14366977261",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00","Periodical",null,"MES LGV+",null,"Medium","7","Planned"]
["SNCF-R","14863521761",null,"< >","Plombières - Evit Plombières","Dijon-Ville - Aiguilles Nord",2024,2024,11,11,"2024-03-17","05:00:00","2024-03-17","11:15:00","Periodical",null,"Ombre de la coupure de 24h     En simultanée avec 4C_DN_240",null,"Medium","7","Planned"]
["SNCF-R","14863542061",null,"< >","Plombières - Evit Plombières","Dijon-Ville - Aiguilles Nord",2024,2024,12,12,"2024-03-18","00:00:00","2024-03-18","05:00:00","Periodical",null,"En simultanée avec 4C_DN_241",null,"Medium","1","Planned"]
["SNCF-R","14754012061",null,"< >","Plombières - Pt Changt Voie","Dijon-Ville - Aiguilles Nord",2024,2024,44,44,"2024-11-02","19:40:00","2024-11-02","13:10:00","Periodical",null,"En complément de la 4C_DN_196  ",null,"Medium","6","Planned"]
["SNCF-R","14753922261",null,"< >","Plombières - Pt Changt Voie","Dijon-Ville - Aiguilles Nord",2024,2024,11,11,"2024-03-16","17:00:00","2024-03-16","05:00:00","Periodical",null,"En complément de la 4C_DN_190",null,"Medium","6","Planned"]
["SNCF-R","14928571161",null,"< >","Blaisy-Bas","Mâlain - Bât Voyageurs",2024,2024,15,15,"2024-04-08","10:50:00","2024-04-08","12:40:00","Periodical",null,"TO: 6703   TF: 6705",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","13854459661",null,"< >","Blaisy-Bas","Mâlain - Bât Voyageurs",2024,2024,43,43,"2024-10-21","10:15:00","2024-10-22","12:40:00","Periodical",null,"TO: 17753   TF: 6705",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13854283861",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,43,43,"2024-10-21","10:00:00","2024-10-22","12:40:00","Periodical",null,"En Simultanée avec la 4F_LLA-BSB_001  TO: 17753   TF: 6705",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13689818461",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-03-04","09:00:00","2024-04-05","14:45:00","Periodical",null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689818461",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-01-22","09:00:00","2024-02-02","14:45:00","Periodical",null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689818461",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-04-04","09:00:00","2024-04-26","14:45:00","Periodical",null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689819261",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,2,34,"2024-01-08","12:32:00","2024-08-23","13:10:00","Periodical",null,"11401061 Incompatible avec les Fenêtre générique et surveillance V2, pour eviter la sim de 1h                                             ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689818461",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-01-22","09:00:00","2024-12-06","14:45:00","Periodical",null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689824861",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,2,34,"2024-01-08","00:20:00","2024-08-19","03:05:00","Periodical",null,"11401123",null,"Medium","1","Planned"]
["SNCF-R","13689818461",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-09-02","09:00:00","2024-10-04","14:45:00","Periodical",null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689820861",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,50,50,"2024-03-25","09:10:00","2024-03-29","15:30:00","Periodical",null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689831461",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,8,14,"2024-02-19","09:10:00","2024-04-05","15:30:00","Periodical",null,"Voie 1 OU 1 Bis  La voie sera déterminée par le plateau commun lors des \"\"réunions des Pas\"\"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689830061",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,11,11,"2024-03-16","11:45:00","2024-03-16","11:25:00","Periodical",null,"",null,"Medium","6","Planned"]
["SNCF-R","13689820861",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,50,50,"2024-01-15","09:10:00","2024-01-19","15:30:00","Periodical",null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689820861",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,50,50,"2024-03-27","09:10:00","2024-03-28","15:30:00","Periodical",null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689820861",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,50,50,"2023-12-11","09:10:00","2024-12-13","15:30:00","Periodical",null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689823261",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,51,31,"2023-12-18","10:27:00","2024-08-02","11:40:00","Periodical",null,"11401032  Incompatible avec les Fenêtre générique et surveillance V1BIS, pour eviter la sim de 1h                                                     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689824061",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,51,31,"2023-12-18","01:51:00","2024-07-29","05:07:00","Periodical",null,"11401118",null,"High","1","Planned"]
["SNCF-R","14615040761",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,35,39,"2024-08-26","10:15:00","2024-09-27","16:30:00","Periodical",null,"En complément de la 4D_AIY-LLA_020 et de la 4C_LLA_004",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689820861",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,50,50,"2024-10-07","09:10:00","2024-10-22","15:30:00","Periodical",null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14366467161",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","14641237561",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,"Medium","6","Planned"]
["SNCF-R","13689828061",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00","Periodical",null,"Maintenance IHM ",null,"Medium","1","Planned"]
["SNCF-R","14641889261",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,"Medium","1","Planned"]
["SNCF-R","13793938961",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00","Periodical",null,"Plage modifiée le 01/12/2022 suite report de la MES",null,"Medium","6","Planned"]
["SNCF-R","15169803561",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,48,48,"2024-11-25","10:25:00","2024-11-29","16:25:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15138662161",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,15,16,"2024-04-13","00:25:00","2024-04-20","04:50:00","Periodical",null,"",null,"Medium","6","Planned"]
["SNCF-R","15138700361",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,15,16,"2024-04-13","23:30:00","2024-04-21","04:55:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","15110090561",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,9,17,"2024-02-26","10:50:00","2024-04-25","12:30:00","Periodical",null,"TO: 6703   TF 891907",null,"High","1,2,3,4","Planned"]
["SNCF-R","15110333561",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,40,41,"2024-09-30","10:00:00","2024-10-11","16:00:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689829061",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,9,9,"2024-02-26","13:10:00","2024-02-29","14:35:00","Periodical",null,"TO: 891904   TF: 9268",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","13689830061",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,11,11,"2024-03-16","11:45:00","2024-03-16","11:25:00","Periodical",null,"",null,"Medium","6","Planned"]
["SNCF-R","15169834761",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,44,44,"2024-11-02","20:10:00","2024-11-02","12:50:00","Periodical",null,"",null,"Medium","6","Planned"]
["SNCF-R","13689832461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,10,11,"2024-03-04","10:55:00","2024-03-14","14:55:00","Periodical",null,"TO: 6703   TF: 891377",null,"High","1,2,3,4","Planned"]
["SNCF-R","14466406361",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,12,13,"2024-03-18","09:25:00","2024-03-28","12:25:00","Periodical",null,"TO: 9261     TF:6705",null,"High","1,2,3,4","Planned"]
["SNCF-R","14466406361",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,12,13,"2024-03-25","09:25:00","2024-03-28","12:25:00","Periodical",null,"TO: 9261     TF:6705",null,"High","1,2,3,4","Planned"]
["SNCF-R","13689826461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-01-22","09:10:00","2024-02-02","15:30:00","Periodical",null,"voie par sens. Accord pour 10 semaines suite à revue de cloture d'ordonnancement PCAST                                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689826461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-04-02","09:10:00","2024-04-26","15:30:00","Periodical",null,"voie par sens. Accord pour 10 semaines suite à revue de cloture d'ordonnancement PCAST                                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689826461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-01-22","09:10:00","2024-12-06","15:30:00","Periodical",null,"voie par sens. Accord pour 10 semaines suite à revue de cloture d'ordonnancement PCAST                                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689821661",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,2,34,"2024-01-08","13:29:00","2024-08-23","14:42:00","Periodical",null,"Incompatible avec les Fenêtre générique et surveillance V1, pour eviter la sim de 1h                                                                   ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689827261",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,2,34,"2024-01-08","01:51:00","2024-08-19","05:07:00","Periodical",null,"11401119",null,"Medium","1","Planned"]
["SNCF-R","13689826461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-09-02","09:10:00","2024-10-04","15:30:00","Periodical",null,"voie par sens. Accord pour 10 semaines suite à revue de cloture d'ordonnancement PCAST                                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15109773161",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,13,13,"2024-03-25","10:35:00","2024-03-28","12:15:00","Periodical",null,"TO: 9206  TF: 9210",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","13794225461",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00","Periodical",null,"Coupure de 06h00 IHM1 pendant la Mise En Service",null,"Medium","6","Planned"]
["SNCF-R","13689967861",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,"Medium","1","Planned"]
["SNCF-R","14858721861",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,"Medium","1","Planned"]
["SNCF-R","13855620061",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,15,43,"2024-04-09","10:20:00","2024-04-10","12:10:00","Periodical",null,"TO: 9206  TF: 9210  Correspond aux Zeps 304 + 308 + 308 + 310 Voie 2 et 2Bis de BSB",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14408975661",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,33,50,"2024-08-13","09:50:00","2024-12-13","15:50:00","Periodical",null,"TO: 17756  TF: Sans  En complément de la 4D_BSB-DN_011",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14409036161",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,35,49,"2024-08-26","09:50:00","2024-12-06","16:50:00","Periodical",null,"TO: 17756 TF: Sans  En complément de la 4D_BSB-DN_010",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14409052361",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,38,45,"2024-09-16","09:30:00","2024-11-07","17:30:00","Periodical",null,"TO: 9261  TF:17764   En complément de la 4D_BSB-DN_008",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14997524361",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,38,45,"2024-09-20","09:30:00","2024-11-08","17:00:00","Periodical",null,"TO: 9261  TF: 6706   En complément de la 4D_BSB-DN_029",null,"High","5","Planned"]
["SNCF-R","13855620061",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,15,43,"2024-10-23","10:20:00","2024-10-24","12:10:00","Periodical",null,"TO: 9206  TF: 9210  Correspond aux Zeps 304 + 308 + 308 + 310 Voie 2 et 2Bis de BSB",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13689820061",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,50,50,"2024-02-19","09:00:00","2024-04-03","14:45:00","Periodical",null,"1 voie par sens.                                                                                   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689820061",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,50,50,"2024-01-15","09:00:00","2024-01-19","14:45:00","Periodical",null,"1 voie par sens.                                                                                   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689820061",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,50,50,"2024-03-29","09:00:00","2024-04-03","14:45:00","Periodical",null,"1 voie par sens.                                                                                   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689820061",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,50,50,"2023-12-11","09:00:00","2024-12-13","14:45:00","Periodical",null,"1 voie par sens.                                                                                   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689825661",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,51,31,"2023-12-18","00:20:00","2024-07-29","03:05:00","Periodical",null,"11401122",null,"High","1","Planned"]
["SNCF-R","13689822461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,51,31,"2023-12-18","11:23:00","2024-08-02","12:05:00","Periodical",null,"11401061 Incompatible avec les Fenêtre générique et surveillance V2BIS, pour eviter la sim de 1h                               ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689820061",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,50,50,"2024-10-23","09:00:00","2024-11-08","14:45:00","Periodical",null,"1 voie par sens.                                                                                   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14334121761",null,"< >","Les Laumes-Alésia - Côté NO","Les Laumes-Alésia - Bif Km 259",2024,2024,15,15,"2024-04-10","09:00:00","2024-04-11","13:00:00","Periodical",null,"Entrée et Sortie coté Pair du Fx Escale est Impossible",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13793849461",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00","Periodical",null,"Plage modifiée le 01/12/2022 suite report de la MES.",null,"Medium","6","Planned"]
["SNCF-R","14366445261",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00","Periodical",null,"MES LGV+",null,"Medium","7","Planned"]
["SNCF-R","14641192261",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard  les zones devront être au blanc.",null,"Medium","6","Planned"]
["SNCF-R","14641865161",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard  les zones devront être au blanc.",null,"Medium","1","Planned"]
["SNCF-R","13689834461",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00","Periodical",null,"Maintenance IHM, les zones devront être au blanc.",null,"Medium","1","Planned"]
["SNCF-R","14333663161",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,35,39,"2024-08-26","10:15:00","2024-09-27","16:30:00","Periodical",null,"En complement de la 4D_AIY-LLA_021",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14011720261",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,15,16,"2024-04-13","23:30:00","2024-04-21","05:10:00","Periodical",null,"Prépa MES LGV+",null,"Medium","6,7","Planned"]
["SNCF-R","14011357761",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,15,16,"2024-04-13","00:05:00","2024-04-20","05:10:00","Periodical",null,"Prépa MES LGV+",null,"Medium","6","Planned"]
["SNCF-R","13689838461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,50,50,"2024-04-04","10:15:00","2024-04-12","14:15:00","Periodical",null,"Aiguille d'accès LGV Aisy GV libre Accord en CODAB le 26/09/2016 pour 35 semaines     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689838461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:15:00","2024-12-13","14:15:00","Periodical",null,"Aiguille d'accès LGV Aisy GV libre Accord en CODAB le 26/09/2016 pour 35 semaines     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689839461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,51,34,"2023-12-18","11:42:00","2024-08-23","12:30:00","Periodical",null,"11401060",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689836861",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,31,34,"2024-07-29","00:34:00","2024-08-19","03:20:00","Periodical",null,"11401135",null,"Medium","1","Planned"]
["SNCF-R","13689838461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,50,50,"2024-12-09","10:15:00","2024-12-13","14:15:00","Periodical",null,"Aiguille d'accès LGV Aisy GV libre Accord en CODAB le 26/09/2016 pour 35 semaines     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14472116761",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,43,43,"2024-10-21","10:10:00","2024-10-24","16:00:00","Periodical",null,"TO: 9264     TF: 17762",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","14504405361",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,43,43,"2024-10-25","10:10:00","2024-10-25","15:45:00","Periodical",null,"TO: 9264     TF: 6743",null,"Medium","5","Planned"]
["SNCF-R","15109488761",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,40,41,"2024-09-30","10:00:00","2024-10-11","16:00:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15109430361",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,13,13,"2024-03-25","10:45:00","2024-03-28","12:15:00","Periodical",null,"TO: 9206   TF: 6705",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","15169710861",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,44,44,"2024-11-02","20:20:00","2024-11-02","12:40:00","Periodical",null,"Voie 1 + 2",null,"Medium","6","Planned"]
["SNCF-R","14446457961",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,9,11,"2024-02-26","10:45:00","2024-02-29","14:45:00","Periodical",null,"",null,"High","1,2,3,4","Planned"]
["SNCF-R","14446660561",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,16,17,"2024-04-15","10:45:00","2024-04-25","13:45:00","Periodical",null,"",null,"High","1,2,3,4","Planned"]
["SNCF-R","15169740761",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,48,48,"2024-11-25","10:25:00","2024-11-29","16:25:00","Periodical",null,"Voie 1 + 2",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13689844061",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,11,11,"2024-03-16","11:30:00","2024-03-16","11:15:00","Periodical",null,"TO: 9211 du Samedi   TF: 9211 du Dimanche",null,"Medium","6","Planned"]
["SNCF-R","13689845061",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00","Periodical",null,"Plage modifiée le 01/12/2022  suite report de la MES.  ",null,"Medium","6","Planned"]
["SNCF-R","13689842061",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00","Periodical",null,"Maintenance IHM   ",null,"Medium","1","Planned"]
["SNCF-R","14641083161",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,"Medium","6","Planned"]
["SNCF-R","14641811661",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,"Medium","1","Planned"]
["SNCF-R","14446385761",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,7,11,"2024-02-12","10:45:00","2024-03-14","16:25:00","Periodical",null,"Circulation des trains par la voie 1 de Les Laumes à Aisy.",null,"High","1,2,3,4","Planned"]
["SNCF-R","14446457961",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,9,11,"2024-02-26","10:45:00","2024-03-14","14:45:00","Periodical",null,"",null,"High","1,2,3,4","Planned"]
["SNCF-R","14446660561",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,16,17,"2024-04-15","10:45:00","2024-04-25","13:45:00","Periodical",null,"",null,"High","1,2,3,4","Planned"]
["SNCF-R","13689838461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,50,50,"2024-01-26","10:15:00","2024-07-05","14:15:00","Periodical",null,"Aiguille d'accès LGV Aisy GV libre Accord en CODAB le 26/09/2016 pour 35 semaines     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689844061",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,11,11,"2024-03-16","11:30:00","2024-03-16","11:15:00","Periodical",null,"TO: 9211 du Samedi   TF: 9211 du Dimanche",null,"Medium","6","Planned"]
["SNCF-R","14366427461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00","Periodical",null,"MES LGV+",null,"Medium","7","Planned"]
["SNCF-R","13689838461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,50,50,"2024-01-15","10:15:00","2024-02-02","14:15:00","Periodical",null,"Aiguille d'accès LGV Aisy GV libre Accord en CODAB le 26/09/2016 pour 35 semaines     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14333732961",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Bât Voyageurs",2024,2024,13,14,"2024-03-29","10:10:00","2024-04-03","14:10:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14333883161",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bât Voyageurs",2024,2024,14,15,"2024-04-04","10:36:00","2024-04-08","12:20:00","Periodical",null,"TO: 6703    TF: 6705  Accès Entrée Nord (par Voie 1) du Fx Impaire Impossible",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14334347461",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bât Voyageurs",2024,2024,15,15,"2024-04-10","10:35:00","2024-04-11","12:25:00","Periodical",null,"TO: 9206    TF: 9210",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14615000261",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bât Voyageurs",2024,2024,35,39,"2024-08-26","10:15:00","2024-09-27","16:30:00","Periodical",null,"TO: 9264   TF: 891379",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14333627861",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Faisceau Impair",2024,2024,13,13,"2024-03-27","09:10:00","2024-03-28","14:20:00","Periodical",null,"TO: 9261  TF: 5763  Accès Fx Impaire Impossible  ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14333518961",null,"< >","Aisy - évitement Pair","Montbard - Bât Voyageurs",2024,2024,13,13,"2024-03-25","09:05:00","2024-03-27","11:10:00","Periodical",null,"TO: 9261    TF: 9211",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14325172061",null,"< >","Aisy - évitement Pair","Montbard - Bât Voyageurs",2024,2024,33,33,"2024-08-12","09:25:00","2024-08-15","16:30:00","Periodical",null,"En Complément de la 4D_RAI_005",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14768809361",null,"< >","Aisy - évitement Pair","Montbard - Bât Voyageurs",2024,2024,27,27,"2024-07-01","09:50:00","2024-07-05","16:50:00","Periodical",null,"En Complément de la 4D_RAI_013",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14640921261",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard  Maintenance IHM1",null,"Medium","5","Planned"]
["SNCF-R","14641724661",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard  Maintenance IHM1",null,"Medium","1","Planned"]
["SNCF-R","14641059261",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard  Maintenance IHM1",null,"Medium","6","Planned"]
["SNCF-R","13884217661",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00","Periodical",null,"MES LGV+",null,"Medium","7","Planned"]
["SNCF-R","14472142061",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,43,43,"2024-10-21","09:45:00","2024-10-25","15:45:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13689955461",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00","Periodical",null,"Plage modifiée le 01/12/2022 suite report de la MES.",null,"Medium","6","Planned"]
["SNCF-R","14011324961",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,15,16,"2024-04-13","00:05:00","2024-04-20","05:10:00","Periodical",null,"Prépa MES LGV+",null,"Medium","6","Planned"]
["SNCF-R","14011795461",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,15,16,"2024-04-13","23:30:00","2024-04-21","05:10:00","Periodical",null,"Prépa MES LGV+",null,"Medium","6,7","Planned"]
["SNCF-R","14448448461",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,6,6,"2024-02-05","09:10:00","2024-02-08","15:10:00","Periodical",null,"En complément de la 4D_AIY-LLA_014   Voie 1",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","14448496861",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,9,10,"2024-02-26","10:40:00","2024-03-05","16:40:00","Periodical",null,"En complément de la 4D_AIY-LLA_017  Voie 1",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","13851162261",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,3,47,"2024-01-16","09:45:00","2024-01-16","15:45:00","Periodical",null,"NUR Voie 1Bis OU Voie A de NUR  En SIM avec la 4D_TNE-AIY_014 (= Voie 1 OU Voie 2)  Si Tx sont : - Voie 1 alors se sera V1Bis                   - Voie 2 alors se sera Voie A                                Accès Faisceau Impair IMPOSSIBLE lorsqu'il s'agit ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14640886061",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   Les zones doivent etre au blanc",null,"Medium","5","Planned"]
["SNCF-R","14641049261",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   Les zones doivent etre au blanc",null,"Medium","6","Planned"]
["SNCF-R","14641658861",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   Les zones doivent etre au blanc",null,"Medium","1","Planned"]
["SNCF-R","13689906661",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00","Periodical",null,"Maintenance IHM1 Les zones doivent etre au blanc ",null,"Medium","1","Planned"]
["SNCF-R","13793246461",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00","Periodical",null,"Plage Modifiée le 01/12/2022 suite report de la MES",null,"Medium","6","Planned"]
["SNCF-R","13851162261",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,3,47,"2024-02-19","09:45:00","2024-11-22","15:45:00","Periodical",null,"NUR Voie 1Bis OU Voie A de NUR  En SIM avec la 4D_TNE-AIY_014 (= Voie 1 OU Voie 2)  Si Tx sont : - Voie 1 alors se sera V1Bis                   - Voie 2 alors se sera Voie A                                Accès Faisceau Impair IMPOSSIBLE lorsqu'il s'agit ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689907861",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00","Periodical",null,"   ",null,"Medium","7","Planned"]
["SNCF-R","13851162261",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,3,47,"2024-01-15","09:45:00","2024-04-26","15:45:00","Periodical",null,"NUR Voie 1Bis OU Voie A de NUR  En SIM avec la 4D_TNE-AIY_014 (= Voie 1 OU Voie 2)  Si Tx sont : - Voie 1 alors se sera V1Bis                   - Voie 2 alors se sera Voie A                                Accès Faisceau Impair IMPOSSIBLE lorsqu'il s'agit ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13851215761",null,"< >","Lézinnes","Aisy - Bât Voyageurs",2024,2024,8,47,"2024-02-19","09:30:00","2024-11-22","16:00:00","Periodical",null,"Voie A de Pacy ET Voie 4 Garage  de NUR  En SIM avec la 4D_TNE-AIY_014  ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13835715861",null,"< >","Lézinnes","Aisy - Bât Voyageurs",2024,2024,17,44,"2024-04-22","09:00:00","2024-10-31","16:45:00","Periodical",null,"Correspond aux voies 1Bis + 4G + A de Nuits sous Ravières et Voie A de Pacy  Pour TTX caténaire.",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689910061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,17,44,"2024-10-21","09:45:00","2024-10-25","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13850875061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,3,47,"2024-01-16","09:45:00","2024-01-16","15:45:00","Periodical",null,"Il s'agit des pas 2 + 3 + 4 Voie 1 OU voie 2  - Passage possible en bana du 207 au 241  - Croisement possible en gare de NUR (Voie 1Bis ou Voie A) .",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13850875061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,3,47,"2024-03-25","09:45:00","2024-03-29","15:45:00","Periodical",null,"Il s'agit des pas 2 + 3 + 4 Voie 1 OU voie 2  - Passage possible en bana du 207 au 241  - Croisement possible en gare de NUR (Voie 1Bis ou Voie A) .",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689910061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,17,44,"2024-04-22","09:45:00","2024-10-31","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13850875061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,3,47,"2024-02-19","09:45:00","2024-11-22","15:45:00","Periodical",null,"Il s'agit des pas 2 + 3 + 4 Voie 1 OU voie 2  - Passage possible en bana du 207 au 241  - Croisement possible en gare de NUR (Voie 1Bis ou Voie A) .",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13971950761",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,33,41,"2024-08-12","09:25:00","2024-10-11","16:30:00","Periodical",null,"TO: 891352   TF: 891379",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14768769161",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,19,27,"2024-05-06","09:50:00","2024-07-05","16:50:00","Periodical",null,"TO: 17753   TF: Sans",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14768769161",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,19,27,"2024-06-03","09:50:00","2024-06-28","16:50:00","Periodical",null,"TO: 17753   TF: Sans",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13971950761",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,33,41,"2024-09-30","09:25:00","2024-10-11","16:30:00","Periodical",null,"TO: 891352   TF: 891379",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13850875061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,3,47,"2024-01-15","09:45:00","2024-04-26","15:45:00","Periodical",null,"Il s'agit des pas 2 + 3 + 4 Voie 1 OU voie 2  - Passage possible en bana du 207 au 241  - Croisement possible en gare de NUR (Voie 1Bis ou Voie A) .",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689910061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,17,44,"2024-04-29","09:45:00","2024-05-03","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14768769161",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,19,27,"2024-05-06","09:50:00","2024-07-05","16:50:00","Periodical",null,"TO: 17753   TF: Sans",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15108831461",null,"< >","LEZINNES POINT DE CHANGEMENT DE VOIE","Aisy - Rac LGV",2024,2024,16,48,"2024-04-15","10:40:00","2024-11-29","13:40:00","Periodical",null,"Voie 1 + 2",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15169707761",null,"< >","LEZINNES POINT DE CHANGEMENT DE VOIE","Aisy - Rac LGV",2024,2024,44,44,"2024-11-02","20:40:00","2024-11-02","12:20:00","Periodical",null,"Voie 1 + 2",null,"Medium","6","Planned"]
["SNCF-R","14011430261",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,15,16,"2024-04-13","23:30:00","2024-04-21","05:10:00","Periodical",null,"Prépa MES LGV +",null,"Medium","6,7","Planned"]
["SNCF-R","14011302061",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,15,16,"2024-04-13","00:05:00","2024-04-20","05:10:00","Periodical",null,"",null,"Medium","6","Planned"]
["SNCF-R","13836175461",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,17,44,"2024-04-22","09:45:00","2024-10-31","15:45:00","Periodical",null,"En SIM avec la 4D_TNE-AIY_002  L'aig 1722 est dégagée. La sortie des TGV est possible.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13851395361",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,8,47,"2024-02-19","09:45:00","2024-11-22","15:45:00","Periodical",null,"En SIM avec la 4D_TNE-AIY_014",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13972261361",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,33,41,"2024-08-12","09:25:00","2024-10-11","16:30:00","Periodical",null,"En SIM avec la 4D_TNE-AIY_016  L'aig 1722 est dégagée. La sortie des TGV est possible.",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14768798861",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,19,27,"2024-05-06","09:50:00","2024-07-05","16:50:00","Periodical",null,"En SIM avec la 4D_TNE-AIY_021  L'aig 1722 est dégagée. La sortie des TGV est possible.",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689917461",null,"< >","Port-Sec-de-Pacy","Aisy - Rac LGV",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00","Periodical",null,"Maintenance IHM 1 ",null,"Medium","1","Planned"]
["SNCF-R","13689920461",null,"< >","Port-Sec-de-Pacy","Aisy - Rac LGV",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,"Medium","5","Planned"]
["SNCF-R","13689918461",null,"< >","Port-Sec-de-Pacy","Aisy - Rac LGV",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00","Periodical",null,"Plage modifiée le 01/12/2022 suite report de la MES",null,"Medium","6","Planned"]
["SNCF-R","13884171661",null,"< >","Port-Sec-de-Pacy","Aisy - Rac LGV",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00","Periodical",null,"MES LGV+",null,"Medium","7","Planned"]
["SNCF-R","13689902261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,50,"2023-12-11","10:15:00","2024-12-13","14:15:00","Periodical",null,"Aiguille d'accès LGV Aisy GV libre       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689903261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,46,"2023-12-18","10:10:00","2024-08-23","11:30:00","Periodical",null,"11401033",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689905861",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,46,"2023-12-18","11:55:00","2024-08-23","12:35:00","Periodical",null,"11401059",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689905061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,49,"2023-12-18","01:11:00","2024-08-12","04:36:00","Periodical",null,"11300364",null,"High","1","Planned"]
["SNCF-R","13689904061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,1,20,"2024-02-26","10:10:00","2024-05-17","13:00:00","Periodical",null,"Fenêtre activable lorsque FEN19_StFlorentin-Tonnerre_001 et FEN19_StFlorentin-Tonnerre_003 sont activées. Sans impact sillons           ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689901461",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,48,"2024-01-08","00:50:00","2024-08-19","03:31:00","Periodical",null,"11401132",null,"High","1","Planned"]
["SNCF-R","13689902261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,50,"2024-01-15","10:15:00","2024-02-02","14:15:00","Periodical",null,"Aiguille d'accès LGV Aisy GV libre       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689901461",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,48,"2023-12-11","00:50:00","2024-12-01","03:31:00","Periodical",null,"11401132",null,"High","1","Planned"]
["SNCF-R","13689905061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,49,"2023-12-18","01:11:00","2024-12-02","04:36:00","Periodical",null,"11300364",null,"High","1","Planned"]
["SNCF-R","13689911061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,18,37,"2024-05-05","23:30:00","2024-09-15","04:15:00","Periodical",null,"Entre 5789 et 5790 ",null,"High","7","Planned"]
["SNCF-R","13689904061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,1,20,"2024-01-02","10:10:00","2024-02-18","13:00:00","Periodical",null,"Fenêtre activable lorsque FEN19_StFlorentin-Tonnerre_001 et FEN19_StFlorentin-Tonnerre_003 sont activées. Sans impact sillons           ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689902261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,50,"2023-12-11","10:15:00","2024-08-11","14:15:00","Periodical",null,"Aiguille d'accès LGV Aisy GV libre       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689903261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,46,"2024-11-12","10:10:00","2024-11-17","11:30:00","Periodical",null,"11401033",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689905861",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,46,"2024-11-12","11:55:00","2024-11-17","12:35:00","Periodical",null,"11401059",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689902261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,50,"2023-12-11","10:15:00","2023-12-15","14:15:00","Periodical",null,"Aiguille d'accès LGV Aisy GV libre       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689909061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,11,11,"2024-03-16","11:20:00","2024-03-16","11:15:00","Periodical",null,"TO: SANS    TF: 17757    ",null,"Medium","6","Planned"]
["SNCF-R","13689902261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,50,"2024-01-19","10:15:00","2024-04-12","14:15:00","Periodical",null,"Aiguille d'accès LGV Aisy GV libre       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14439111461",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,9,15,"2024-02-26","10:00:00","2024-04-11","13:00:00","Periodical",null,"Voie 1 + 2",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689909061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,11,11,"2024-03-16","11:20:00","2024-03-16","11:15:00","Periodical",null,"TO: SANS    TF: 17757    ",null,"Medium","6","Planned"]
["SNCF-R","15195958761",null,"< >","Tonnerre - Bât Voyageurs","Nuits-sous-Ravières",2024,2024,48,50,"2024-11-25","09:36:00","2024-12-13","16:25:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15195746261",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,38,45,"2024-09-30","09:45:00","2024-10-31","17:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195715761",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,17,50,"2024-04-22","09:45:00","2024-12-06","16:13:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689890661",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,50,16,"2024-03-25","10:50:00","2024-04-19","12:30:00","Periodical",null,"Derrière 17756 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15202406561",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,39,39,"2024-09-28","08:00:00","2024-09-29","18:00:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","13689883861",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,50,49,"2023-12-11","00:10:00","2024-12-02","03:00:00","Periodical",null,"",null,"Major","1","Planned"]
["SNCF-R","13689890661",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,50,16,"2023-12-11","10:50:00","2024-04-19","12:30:00","Periodical",null,"Derrière 17756 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195746261",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,38,45,"2024-09-16","09:45:00","2024-11-07","17:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689888861",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,12,37,"2024-03-24","23:15:00","2024-09-15","04:35:00","Periodical",null,"Entre 5789 et 5790 ",null,"High","7","Planned"]
["SNCF-R","13689884661",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,1,32,"2024-01-02","09:46:00","2024-08-11","13:26:00","Periodical",null,"3h45 à 3h54 en sim 5J/7 MC17-0131 pour 891352 (ouvrant) et le 891354 (fermant)                                                                                     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15195715761",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,17,50,"2024-04-22","09:45:00","2024-12-13","16:13:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689889861",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tanlay",2024,2024,50,16,"2024-03-25","11:25:00","2024-04-19","13:10:00","Periodical",null,"Derrière 17757 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689885461",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tanlay",2024,2024,50,49,"2023-12-11","03:00:00","2024-12-02","06:10:00","Periodical",null,"",null,"Major","1","Planned"]
["SNCF-R","13689889861",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tanlay",2024,2024,50,16,"2023-12-11","11:25:00","2024-04-19","13:10:00","Periodical",null,"Derrière 17757 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689883061",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tanlay",2024,2024,1,32,"2024-01-02","09:26:00","2024-08-11","13:37:00","Periodical",null,"3h45 à 3h54 en sim 5J/7                                                               ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689887061",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tonnerre - Bât Voyageurs",2024,2024,46,46,"2024-11-12","12:25:00","2024-11-17","13:35:00","Periodical",null,"11401034",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13689886261",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tonnerre - Bât Voyageurs",2024,2024,46,46,"2024-11-12","12:05:00","2024-11-17","12:55:00","Periodical",null,"11401062",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15202420661",null,"< >","Brienon","Flogny",2024,2024,39,39,"2024-09-28","08:00:00","2024-09-29","18:00:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","15179391861",null,"< >","Vienne - Poste","Vaugris",2024,2024,40,40,"2024-09-30","23:00:00","2024-10-04","05:00:00","Periodical",null,"Créée Pour  - Maintenance voie ou SeG avec engins spéciaux  ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14623761961",null,"< >","Vienne - Voie 2Bis","Salaise",2024,2024,7,48,"2024-02-12","22:30:00","2024-11-29","06:00:00","Periodical",null,"Créé pour CHA24_0026549 ADAP PEAGE ROUSSILLON  Travaux de préparations  - Travaux Génie civil - Grutage ascenseur  DFV Type L VIENNE - St RAMBERT voie 1 de la gare de VIENNE   DFV Type L PSt RAMBERT - VIENNE voie 2 de la gare de St RAMBERT - Secteur CLONA",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688243461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2024-09-23","22:24:00","2024-09-26","06:40:00","Periodical",null,"4h26 de sim. partielle déduite. derrière 9847 SA2018 => SF ME 9/05, ME 31/10 2022_SE_09: vibration <10mn pour avoir 9846/7 en SO     ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688240261",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2024-09-23","23:17:00","2024-09-26","05:17:00","Periodical",null,"4h30 de sim. partielle déduite. sauf jours typé VE SA2018 => SF ME 9/05, ME 31/10 Modification le 05/02/2019 : inversion Heure Début PK Début et Heure Début PK Fin, et Heure Fin PK Début et Heure Fin PK Fin ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","14886083461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00","Periodical",null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00  ",null,"Medium","1,2,3,5,6,7","Planned"]
["SNCF-R","13688242661",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-11","13:01:00","2024-12-13","13:19:00","Periodical",null,"10700733",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688244261",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-11","13:46:00","2024-12-13","15:26:00","Periodical",null,"10700732 2021_SE_106 + 2021_SE_107 + 2021_SE_108 + 2021_SE_109 + 2021_SE_110 + 2021_SE_111 : décalage de quelques minutes pour avoir 6615 en SO et 6617 en SF                                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688243461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-11","22:24:00","2024-12-12","06:40:00","Periodical",null,"4h26 de sim. partielle déduite. derrière 9847 SA2018 => SF ME 9/05, ME 31/10 2022_SE_09: vibration <10mn pour avoir 9846/7 en SO     ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688240261",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-11","23:17:00","2024-12-12","05:17:00","Periodical",null,"4h30 de sim. partielle déduite. sauf jours typé VE SA2018 => SF ME 9/05, ME 31/10 Modification le 05/02/2019 : inversion Heure Début PK Début et Heure Début PK Fin, et Heure Fin PK Début et Heure Fin PK Fin ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688246061",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,52,46,"2023-12-25","23:35:00","2024-11-11","06:00:00","Periodical",null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022   ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688247061",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,52,46,"2023-12-26","00:05:00","2024-11-12","05:20:00","Periodical",null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022 ",null,"High","2,3,4,5,6","Planned"]
["SNCF-R","13688241061",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-15","23:25:00","2024-12-13","05:17:00","Periodical",null,"TGV ouvrant 6672 TGV fermant 999614 VE/SA + jours typé VE SA2018 => + ME 9/05 + ME 31/10       ",null,"Major","3,5","Planned"]
["SNCF-R","13688241861",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-15","22:55:00","2024-12-13","06:37:00","Periodical",null,"TGV ouvrant 6635, TGV fermant 999611 VE/SA + jours typé VE SA2018 => + ME 9/05 + ME 31/10       ",null,"Major","3,5","Planned"]
["SNCF-R","13688250461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,15,49,"2024-04-13","23:05:00","2024-12-07","05:35:00","Periodical",null,"fenêtre applicable sa/di lorsque ne circule pas 9098 train ouvrant 9847 et 6442, train fermant 999614 ",null,"Major","6","Planned"]
["SNCF-R","13688252461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,49,49,"2023-12-10","23:55:00","2024-12-08","05:25:00","Periodical",null,"fenêtre applicable di/lu train ouvrant 6208, train fermant 999614 ",null,"Major","7","Planned"]
["SNCF-R","13688249461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,14,"2023-12-17","00:10:00","2024-04-07","05:35:00","Periodical",null,"fenêtre applicable sa/di lorsque circule 9098 avancé  train ouvrant 9098, train fermant 999614  ",null,"High","7","Planned"]
["SNCF-R","13688250461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,15,49,"2024-09-28","23:05:00","2024-09-28","05:35:00","Periodical",null,"fenêtre applicable sa/di lorsque ne circule pas 9098 train ouvrant 9847 et 6442, train fermant 999614 ",null,"Major","6","Planned"]
["SNCF-R","14643893861",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Culoz - Bif de Genève",2024,2024,33,50,"2024-08-18","22:20:00","2024-12-12","05:20:00","Periodical",null,"Interception Gare de Culoz:  Voie CG+ VU(raccordement)  Domaine S9 :  Zep 432 (V CG)  Zep 436(VRacco)     ",null,"Major","1,2,3,4,7","Planned"]
["SNCF-R","14926727161",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Vions-Chanaz",2024,2024,16,16,"2024-04-16","22:20:00","2024-04-18","05:00:00","Periodical",null,"Interception Gare de Culoz: BML Appareil  Voies 1M et 2M et Racco  Domaine S9:(CCTT)   ZEP 436+437+438+439+440  ",null,"Medium","2,3,4","Planned"]
["SNCF-R","14958334961",null,"< >","Marseille-Maritime-Arenc - Fsc Sud","Marseille-St-Charles - Marchandises",2024,2024,2,3,"2024-01-08","23:20:00","2024-01-19","05:00:00","Periodical",null,"LNPCA, Bloc Ouest Voie N :  Domaine S9 : ZEP G 5430+5432+5433 (du Cv304 Km 861,539 au Cv349 Km 861,689)   Domaine S11 : Sél 316 (du Km 861,539 au Km 861,810)",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14976487661",null,"< >","Marseille-St-Charles - Marchandises","Marseille-St-Charles - Marchandises",2024,2024,36,50,"2024-09-02","00:00:00","2024-12-14","23:59:00","continuous",null,"LNPCA : Libération Abeilles : travaux VS, prise des voies 19 à 23 uniquement, SA 2024 de septembre (S36) à décembre 2024 (S50) - démolition bâtiments le long de la voie A.",null,"Major","","Planned"]
["SNCF-R","14975654261",null,"< >","Marseille-St-Charles - Marchandises","Marseille-St-Charles - Marchandises",2024,2024,20,24,"2024-05-18","06:00:00","2024-06-16","22:00:00","Periodical",null,"SA2024 : Déménagement CSS Marseille, gare des Pierres uniquement sf voies 87 :  1 OCP WE S20 40h (MES : du Sa 18/05 à 06h00 au Di 19/05 22h00) + 1 OCP 40h secours S24 40h (MES : du Sa 15/06 06h00 au Di 16/06 22h00)  Nota : les travaux sur l'intégralité du",null,"Medium","6,7","Planned"]
["SNCF-R","14340433861",null,"< >","L'Estaque - Bif Mourepiane","L'Estaque - Bif Mourepiane",2024,2024,45,45,"2024-11-10","22:35:00","2024-11-10","05:35:00","Periodical",null,"CHA24_0026458, OCP 7h00, 1 nuit du Di/Lu 10-11/11/24 (de 22h35 à 05h35), mise en service \"\"LGV +\"\" sur l'interface de la zone télécommandée de l'IHM1 de Mistral P1 de Marseille)  Conditions de réalisation : toute la zone d'action du poste de l'IHM1 de Mar",null,"Medium","7","Planned"]
["SNCF-R","14340932761",null,"< >","L'Estaque - Bif Mourepiane","L'Estaque - Bif Mourepiane",2024,2024,3,37,"2024-01-20","23:59:00","2024-09-14","04:40:00","Periodical",null,"CHA20_0018098 \"\"Augmentation débit LGV\"\" : OCP 4h41,  1 nuit du Sa/Di de S3 (20-21/01/24) + 1 nuit du Sa/Di de S25 ( 22-23/06/24 de 23h59 à 04h40 opérations sur l´IHM1 Mistral au P1 de Marseille) et 1 nuit du Sa/Di de S37 pour essai complet de montée en c",null,"Medium","6","Planned"]
["SNCF-R","13686953261",null,"< >","Martigues - Aig Rac La Mède","L'Estaque - Bât Voyageurs",2024,2024,11,41,"2024-03-11","09:20:00","2024-10-11","13:20:00","Periodical",null,"MC19-0025 le 19/09/17 pour décalage pour passage du 879728.",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14537771861",null,"< >","Martigues - Aig Rac La Mède","L'Estaque - Bât Voyageurs",2024,2024,8,38,"2024-02-19","22:30:00","2024-09-20","04:30:00","Periodical",null,"SA2024, UP SES Avi :  Domaine S9 : ZEP 33+40+46(V4)+75(Sortie VS 3 à 11) ou ZEP 35+38 ou ZEP 42(V4G)+74",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13686955061",null,"< >","Martigues - CV 878","L'Estaque - Bât Voyageurs",2024,2024,50,50,"2023-12-11","09:38:00","2024-12-13","10:06:00","Periodical",null,"2024_SE_10 : vibration de +5' pour avoir TER 879716 en SO  2021_SE_52 : décalage de +35mn pour avoir 879716 en SO, aligné V2 de l'Estaque à Miramas, le 19/11/2019  MC19-0020 pour caler la plage entre 879716 et 879720  Modification le 05/02/2019 : inversio",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687217861",null,"< >","Pas-des-Lanciers - Bât Voyageurs","L'Estaque - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:56:00","2024-12-13","12:00:00","Periodical",null,"2024_SE_30 : vibration de -10' pour avoir TER 17701 en SO et TER 886565 en SF  MC19-0149 Calage entre 879653 et 879655 Modif main courante 2020 Maj-550_871   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687217061",null,"< >","Pas-des-Lanciers - Bât Voyageurs","L'Estaque - Bât Voyageurs",2024,2024,50,50,"2023-12-11","09:56:00","2024-12-13","10:50:00","Periodical",null,"Annulation Décalage MC17-0226 pour 879610 le 21/10/15 2021_SE_68 : décalage de +30mn pour avoir 879518 en SO et 879522 en SF, aligné V2 de St Louis à Tarascon, le 19/11/2019",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14340826861",null,"< >","Vitrolles-Aéroport-Marseille-P","L'Estaque - Bât Voyageurs",2024,2024,3,37,"2024-01-20","23:59:00","2024-09-14","04:40:00","Periodical",null,"CHA20_0018098 \"\"Augmentation débit LGV\"\" : OCP 4h41,  1 nuit du Sa/Di de S3 (20-21/01/24) + 1 nuit du Sa/Di de S25 ( 22-23/06/24 de 23h59 à 04h41 opérations sur l´IHM1 Mistral au P1 de Marseille) et 1 nuit du Sa/Di de S37 pour essai complet de montée en c",null,"Medium","6","Planned"]
["SNCF-R","14340241361",null,"< >","Vitrolles-Aéroport-Marseille-P","L'Estaque - Bât Voyageurs",2024,2024,45,45,"2024-11-10","22:35:00","2024-11-10","05:35:00","Periodical",null,"CHA24_0026458, OCP 7h00, 1 nuit du Di/Lu 10-11/11/24 (de 22h35 à 05h35), mise en service \"\"LGV +\"\" sur l'interface de la zone télécommandée de l'IHM1 de Mistral P1 de Marseille)  Conditions de réalisation : toute la zone d'action du poste de l'IHM1 de Mar",null,"Medium","7","Planned"]
["SNCF-R","13686954261",null,"< >","Martigues - Aig Rac La Mède","L'Estaque - Panneau 901",2024,2024,50,50,"2023-12-11","15:26:00","2024-12-13","16:54:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14340462561",null,"< >","Pas-des-Lanciers - V 4 Garage","Séon-St-Henry",2024,2024,45,45,"2024-11-10","22:35:00","2024-11-10","05:35:00","Periodical",null,"CHA24_0026458, OCP 7h00, 1 nuit du Di/Lu 10-11/11/24 (de 22h35 à 05h35), mise en service \"\"LGV +\"\" sur l'interface de la zone télécommandée de l'IHM1 de Mistral P1 de Marseille)  Conditions de réalisation : toute la zone d'action du poste de l'IHM1 de Mar",null,"Medium","7","Planned"]
["SNCF-R","14958206361",null,"< >","Séon-St-Henry","St-Louis-les-Aygalades - Km 857,206",2024,2024,8,11,"2024-02-24","01:00:00","2024-03-16","04:30:00","Periodical",null,"LNPCA - Marseille Nord (St Louis les Aygualades) L830 tunnel Delorme, nuit courte VE/SA (SA) :  Domaine S9 : M1 ZEP 5111 (du C716 Km 855,709 au C723 Km 856,633) et M2 ZEP 5110 (du C714 Km 855,709 au C721 Km 856,633)  Domaine S11 : M1 Sél 2915 (du Km 854,4",null,"Medium","6","Planned"]
["SNCF-R","14958157661",null,"< >","Séon-St-Henry","St-Louis-les-Aygalades - Km 857,206",2024,2024,8,11,"2024-02-20","00:05:00","2024-03-15","04:30:00","Periodical",null,"LNPCA - Marseille Nord (St Louis les Aygualades) L830 tunnel Delorme :  Domaine S9 : M1 ZEP 5111 (du C716 Km 855,709 au C723 Km 856,633) et M2 ZEP 5110 (du C714 Km 855,709 au C721 Km 856,633)  Domaine S11 : M1 Sél 2915 (du Km 854,422 au Km 856,868) et M2 ",null,"High","2,3,4,5","Planned"]
["SNCF-R","14845750361",null,"< >","Marseille-St-Charles - Remisage TER","La Pomme",2024,2024,43,45,"2024-10-21","23:19:00","2024-11-08","05:35:00","Periodical",null,"Meuleur SA2024, S43, V1+V2",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15224237461",null,"< >","La Barasse","Aubagne",2024,2024,35,50,"2024-09-01","22:50:00","2024-12-12","05:35:00","Periodical",null,"Portiques souples Aubagne, reprise travaux sur SA2024 :   Domaine S9 :  V.D : zep 3617+3619+3621  V.1/VC : zep 3601+3603+3605+3607+3609+3611+3613+3615  MV2/VB : zep 3600+3602+3604+3606+3608+3610+3612+3614  MV3/VA : zep 3616+3618+3620+3622+3624+3626  VE : ",null,"Major","1,2,3,4,7","Planned"]
["SNCF-R","15446138061",null,"< >","La Barasse","Aubagne",2024,2024,41,41,"2024-10-12","00:01:00","2024-10-12","12:01:00","Periodical",null,"OCP 12h, sur S41 (sur le même We que le CHA24_0026522 Aqueducs Km 26,242) :  Portiques souples Aubagne, reprise travaux sur SA2024 à l'ombre de l'OCP 28h du CHA24_0026522) :   Domaine S9 :  V.D : zep 3617+3619+3621  V.1/VC : zep 3601+3603+3605+3607+3609+3",null,"Medium","6","Planned"]
["SNCF-R","14340744061",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,3,37,"2024-01-20","23:59:00","2024-09-14","04:40:00","Periodical",null,"CHA20_0018098 \"\"Augmentation débit LGV\"\" : OCP 4h41,  1 nuit du Sa/Di de S3 (20-21/01/24) + 1 nuit du Sa/Di de S25 ( 22-23/06/24 de 23h59 à 04h40 opérations sur l´IHM1 Mistral au P1 de Marseille) et 1 nuit du Sa/Di de S37 pour essai complet de montée en c",null,"Medium","6","Planned"]
["SNCF-R","13689508961",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,50,50,"2024-10-28","23:19:00","2024-12-06","05:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689508961",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,50,50,"2024-09-30","23:19:00","2024-11-15","05:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689508961",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,50,50,"2023-12-11","23:19:00","2024-12-13","05:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689508161",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,50,50,"2023-12-11","08:38:00","2024-12-13","09:45:00","Periodical",null,"MC19-0062 entre 6805 et 17475 2021_SE_87 + 2021_SE_88 + 2021_SE_89 : décalage pour avoir 881611 en SF   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14340542561",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,45,45,"2024-11-10","22:35:00","2024-11-10","05:35:00","Periodical",null,"CHA24_0026458, OCP 7h00, 1 nuit du Di/Lu 10-11/11/24 (de 22h35 à 05h35), mise en service \"\"LGV +\"\" sur l'interface de la zone télécommandée de l'IHM1 de Mistral P1 de Marseille)  Conditions de réalisation : toute la zone d'action du poste de l'IHM1 de Mar",null,"Medium","7","Planned"]
["SNCF-R","13689508961",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,50,50,"2024-03-18","23:19:00","2024-03-29","05:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689510161",null,"< >","Marseille-Blancarde - Jonction 1","Aubagne",2024,2024,50,50,"2023-12-11","11:20:00","2024-12-13","12:12:00","Periodical",null,"MC19-0071 avoir une heure de surveillance pleine de 1h00 2021_SE_81 + 2021_SE_82 + 2021_SE_83 : décalage de quelques minutes pour avoir 881426 en SO   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689510961",null,"< >","Marseille-Blancarde - Jonction 1","Aubagne",2024,2024,50,50,"2023-12-11","11:10:00","2024-12-13","12:10:00","Periodical",null,"Décalage MC18-0207 passage entre 881034 et 881036 2021_SE_79 : décalage de quelques minutes pour avoir 881037 et 881036 en SO",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14411818061",null,"< >","Marseille-Maritime-Arenc - Fsc Sud","Marseille-Maritime-Arenc - Fsc Sud",2024,2024,17,24,"2024-04-22","21:20:00","2024-06-14","04:55:00","Periodical",null,"Le Canet - Fermeture du chantier puis cession de terrain à partir de S17 jusqu´à S24, DEF 07h35 - (Rac Canet et Rac Arenc reliant de part et d'autre le chantier du Canet avec neutralisation aiguilles 313ac/314bd sur Bif Rac. Arenc et VA Circulation P1 Are",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15445950461",null,"< >","Marseille-Maritime-Arenc - Fsc Sud","Marseille-Maritime-Arenc - Fsc Sud",2024,2024,20,21,"2024-05-18","19:00:00","2024-05-20","07:00:00","Periodical",null,"Fermeture du Canet -Fermeture du chantier, cession du terrain- , OCP 36h  => We S20/21, du Sa 18/05 à 19h00 au Lu 20/05 à 07h00 : remplacement des ADV 203aV et 205aV par de la voie courante, dépose de l´ADV 203b et remplacement de la TJD 313ac/314bd par B",null,"Medium","1,6,7","Planned"]
["SNCF-R","13686989661",null,"< >","L'Estaque - BÃ¢t Voyageurs","Marseille-Maritime-Arenc - Bif Rac Canet",2024,2024,17,24,"2024-04-22","21:20:00","2024-06-14","04:55:00","Periodical",null,"Le Canet - Fermeture du chantier puis cession de terrain à partir de S17 jusqu´à S24, DEF 07h35 - (Rac Canet et Rac Arenc reliant de part et d'autre le chantier du Canet avec neutralisation aiguilles 313ac/314bd sur Bif Rac. Arenc et VA Circulation P1 Are",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15445947261",null,"< >","L'Estaque - Point Km","Marseille-Maritime-Arenc - Bif Rac Canet",2024,2024,20,21,"2024-05-18","19:00:00","2024-05-20","07:00:00","Periodical",null,"Fermeture du Canet -Fermeture du chantier, cession du terrain- , OCP 36h  => We S20/21, du Sa 18/05 à 19h00 au Lu 20/05 à 07h00 : remplacement des ADV 203aV et 205aV par de la voie courante, dépose de l´ADV 203b et remplacement de la TJD 313ac/314bd par B",null,"Medium","1,6,7","Planned"]
["SNCF-R","13686977861",null,"< >","L'Estaque - Point Km","Marseille-Maritime-Arenc - Bif Rac Canet",2024,2024,41,50,"2024-10-07","21:20:00","2024-12-13","04:55:00","Periodical",null,"Raccordement Mourepiane, pose de la nouvelle Com Tg 0.085 (Voie et caténaire) et modification platelage PN2 :  Etendue S9 MM1 / MM2 : MM1 du C944 à revers Km 853,154 au C946 à revers Km 854,559 / MM2 du C201 à revers Km 856,051 au C942 km 853,154  Domaine",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13686979861",null,"< >","L'Estaque - Point Km","Marseille-Maritime-Arenc - Bif Rac Canet",2024,2024,41,50,"2024-10-07","21:20:00","2024-12-13","04:55:00","Periodical",null,"Raccordement Mourepiane, Entrées/ Sorties de trains travaux vers le S9A3 => depuis MM1 vers le tunnel de Soulat (via Aig 947 neut.D) :  1 Nuit de 7h30 sur MM1 LU/MA et puis une sur VE/SA toutes les semaines de octobre (S41) à déc. 2024 (S49).  Etendue S9 ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14737169161",null,"< >","Avignon - Bif Cavaillon","Miramas - Bât Voyageurs",2024,2024,39,40,"2024-09-25","08:37:00","2024-10-02","17:15:00","Periodical",null,"Tvx Principaux 08h40 -Miramas inclus à Cavaillon exclu - Ppx : S39 ME+JE+VE et S40 LU+MA+ME- :  Etendue S9 : V1 de la PATC Km 38,695 au C507 au Km 66,880 => JI Z 605/617 km 67.837 de Mas / V2 Du Cv 607 km 67,860 => à la PATC Km 65,976 au C24 Km 34,100    ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14596796961",null,"< >","Miramas - Relais La Crau","Miramas - Bât Voyageurs",2024,2024,50,25,"2023-12-11","14:00:00","2024-06-21","22:00:00","Periodical",null,"La réservation capacitaire de l'outil TCAP sur les VS de Miramas ne nous permet pas de réservation voie par voie (à voir les nouvelles données prévues pour fin juin, fin de campagne RP0, si elles nous permettront ou pas une réservation plus précise : ici ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14535706861",null,"< >","Miramas - Relais La Crau","Miramas - Bât Voyageurs",2024,2024,10,10,"2024-03-04","23:59:00","2024-03-08","03:30:00","Periodical",null,"SA2024, UP SES Avi (V3G) :  Etendue S9 : L925 V1+V3G (du V1 Cv517 Km 67,251 au C627 Km 68,512+ V3G+ VS E/S dépôt)/L925 V2 du C619 Km 68,100 au C612 Km 68,220 / V1 L830 du C603 Km 808,585 au Cv610 Km 808,947    Domaine S9 :  L925 V1 173+175+177+190+179+137",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14696449561",null,"< >","Salon","Miramas - Bât Voyageurs",2024,2024,9,11,"2024-02-26","11:35:00","2024-03-15","13:44:00","Periodical",null,"SA2024, Maint, de 11h35 à 13h44, V1S+V2S+1Racct+2Racct, entre les circulaztions de l'ITE SMEA :  Etendue S9 : V1S du C507 Km 66,880 au JI Z605/617 Km 68,130 / V2 de la PATC Km 65,976 au C607 Km 67,860 /Racct 1 de l'Aig 505 Km au C420 Km ,595  /Racct 2 de ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14696432461",null,"< >","Salon","Miramas - Bât Voyageurs",2024,2024,17,48,"2024-04-27","22:10:00","2024-11-30","06:10:00","Periodical",null,"SA2024, Maint, DEF 08h00, L925 V1+V2+V1S+V2S+1Racct+2Racct, du Sa 22h10 au Di 06h10 (du 30/03 au 31/03 + 23/11 au 24/11 + 30/11 au 01/12 ) :  Etendue S9 : V1 de la PATC de CAV Km 38,695 au C507 Km 66,880 jusqu'au JI Z605/617 Km 68,130 (V1S) / V2 du C24 de",null,"Medium","6","Planned"]
["SNCF-R","16633986861",null,"< >","Salon","Miramas - Bât Voyageurs",2024,2024,38,41,"2024-09-16","09:55:00","2024-10-11","17:45:00","Periodical",null,"Tvx Prépa/Confortatifs ou Principaux 07h20 -Miramas inclus à Cavaillon exclu - S37+S38(Prépa/Conf.) et S39 LU+MA (Ppx)+S40 JE+VE (Ppx)+S41(Ppx)+S42(finitions)+43 (finitions)- :  Etendue S9 : V1 de la PATC Km 38,695 au C507 au Km 66,880 => JI Z 605/617 km ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14646586861",null,"< >","Salon","Miramas - Bât Voyageurs",2024,2024,37,43,"2024-09-09","09:55:00","2024-10-25","17:15:00","Periodical",null,"Tvx Prépa/Confortatifs ou Principaux 07h20 -Miramas inclus à Cavaillon exclu - S37+S38(Prépa/Conf.) et S39 LU+MA (Ppx)+S40 JE+VE (Ppx)+S41(Ppx)+S42(finitions)+43 (finitions)- :  Etendue S9 : V1 de la PATC Km 38,695 au C507 au Km 66,880 => JI Z 605/617 km ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14570436061",null,"< >","Salon","Miramas - Bât Voyageurs",2024,2024,24,24,"2024-06-15","17:00:00","2024-06-15","11:00:00","Periodical",null,"SA2024, CCR OP1, OCP 4 V1S+V2S+1Racct+2Racct, OCP4 18h du Sa 17h00 au Di 11h00 (du 15/06 au 16/06), pendant la fermeture ITE SMEA :  Etendue S9 : V1S du C507 Km 66,880 au JI Z605/617 Km 68,130 / V2 de la PATC Km 65,976 au C607 Km 67,860 /Racct 1 de l'Aig ",null,"Medium","6","Planned"]
["SNCF-R","14535482661",null,"< >","Miramas - Triage PC","Miramas - Faisceau Départ",2024,2024,23,36,"2024-06-03","23:59:00","2024-09-06","03:30:00","Periodical",null,"SA 2024, UP SES Avi :  Etendue S9 : sortie F.Tri V51 à V74 (du Km 807,680 au C1 Km 807,736)  Domaine S9 : uniquement ZEPG 660+661+662+664 (Poste C)     Nota : révision SIPH/VS TCAP faites au 23-07-22",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14535505361",null,"< >","Miramas - Triage PC","Miramas - Faisceau Départ",2024,2024,24,37,"2024-06-10","23:59:00","2024-09-13","03:30:00","Periodical",null,"SA 2024, UP SES Avi :  Etendue S9 : sortie F.Tri V31 à V50 (du Km 807,614 au Km 807,875)  Domaine S9 : uniquement ZEPG 304+647+658+659+663    Nota : révision SIPH/VS TCAP faites au 23-07-22",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14535532461",null,"< >","Miramas - Triage PC","Miramas - Faisceau Départ",2024,2024,25,25,"2024-06-17","23:59:00","2024-06-19","03:30:00","Periodical",null,"SA2024, UP SES Avi :  Etendue S9 : du 29C Km 807,568 (F. Relais)  au C9C Km 807,746 (Voie SAS Mach.)   Domaine S9 : ZEPG 313+315+300    Nota : révision SIPH/VS TCAP faites au 23-07-22  ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13687303261",null,"< >","Miramas - Aig Km 805,1","Miramas - FSC réception",2024,2024,50,39,"2023-12-11","22:07:00","2024-09-27","05:01:00","Periodical",null,"CCR OUEST P. -Etape1- : DEF V1+V2 de St Martin de Crau à Mas (exclus) de 06h57, à prendre avec 3D_TCN-MAS_011 :  Etendue S9 : V1 du C 1 Km 791,183 de SMA au C 603 Km 808,585 de MAS / V2 du GF Aig 301 (V2/V2Bis) Km 805,980 de MAS à la PATC du Km 791,250 de",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14463937161",null,"< >","Miramas - FSC réception","Miramas - Triage PC",2024,2024,42,48,"2024-10-15","05:05:00","2024-11-30","05:05:00","continuous",null,"RAV Mas, F. Triage, réservation des voies 27+28+29 pour Base arrière du Ma 15/10 à 05h05 de S42 au Sa 30/11 à 05h05 de S48 :  Domaine S9 : 527+526+529  Domaine S11 : néant",null,"Major","","Planned"]
["SNCF-R","14462347061",null,"< >","Miramas - Triage PC","Miramas - Triage PC",2024,2024,42,48,"2024-10-14","23:05:00","2024-11-29","05:05:00","Periodical",null,"Extension du domaine fermée, depuis le domaine de base vers le faisceau Relais, de S42 à S48 :  Etendue S9 : du Km 806,688 au Km 807,566 pour les V153 et 154 et limitée au Km 807,509 pour les V150 à 152    Domaine S9 : 184+313+315+753+754+757+758  Etendue",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14462594961",null,"< >","Miramas - Triage PC","Miramas - Triage PC",2024,2024,44,46,"2024-11-01","05:01:00","2024-11-12","05:01:00","Periodical",null,"Extension du domaine fermée, depuis le domaine de base vers le faisceau Relais, pdt tte l'OCP 72h,  WE(s) S44/45 + S45/46 :  Etendue S9 : du Km 806,766 au Km 807,509 pour les V153 et 154 et limitée au Km 807,509 pour les V150 à 152  Domaine S9 : 184+313+3",null,"High","1,2,3,4,5,6,7","Planned"]
["SNCF-R","14462981961",null,"< >","Miramas - Triage PC","Miramas - Triage PC",2024,2024,40,49,"2024-10-01","05:05:00","2024-12-07","05:05:00","continuous",null,"Fermeture continue de la V154 sur le F. Relais, aire de montage des APvs, du Ma 01/10 à 05h05 de S40 à Sa 07/12 à 05h05 de S49 :   Etendue S9 : du Km 806,766 au Km 807,509   Domaine S9 : ZEPG 754 (V154)   Etendue S11 : du Km 806,766 au Km 807,509, CBT S11",null,"Major","","Planned"]
["SNCF-R","14463434861",null,"< >","Miramas - Triage PC","Miramas - Triage PC",2024,2024,40,49,"2024-09-30","23:05:00","2024-12-06","05:05:00","Periodical",null,"Mise en application de la CBT S11 sur 154 ( mise en place et retrait) , besoin de consigner la Sél 134, F. relais inexploitable sur 2 jours (Lu/Ma et Ma/Me) de la S40 et 2 jrs sur la S49 :  Etendue S9 : du Km 806,670 au Km 807,509 pour les V153 et 154 et ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13687299461",null,"< >","Miramas - Bif Km 67","Miramas - Panneau 601",2024,2024,8,48,"2024-02-19","09:55:00","2024-11-29","15:40:00","Periodical",null,"SA 2024, Famille B, Maintenance massifiée sur ADV AMS, raccord et entrée sortie Dépot :   ZEP : 154+156+161+163+117+145+147+149+183+185+174+176+178+180+182+184+168  Nota : étapes de réunion avec la DT  ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14573175261",null,"< >","Miramas - Relais La Crau","Miramas - Panneau 601",2024,2024,19,19,"2024-05-08","12:10:00","2024-05-10","00:10:00","Periodical",null,"CCR OP1, OCP3 36h, We S19, de Me 08/05 à 12h10 au  VE 10/05 à 00h10 :  Etendue S9 : Racc 1 jusqu'au Cv510 Km 67,270 + Racc 2 Jusqu'au C508 Km 67,391 + V1TER C403 Km 807,317 au Pte Ag 410 Km 808,109 + V2TER/VB Circ du C401 Km 807,317 au C601 Km 808,650 + V",null,"Medium","3,4,5,6","Planned"]
["SNCF-R","14542959461",null,"< >","Salon","Miramas - V 3 garage",2024,2024,21,40,"2024-05-25","23:00:00","2024-10-05","06:00:00","Periodical",null,"SA2024, UP Voie SES Avi, OCP 7h00 We SA/DI cause Ite SMEA :   Etendue S9 : L925 : V1S du C507 Km 66,880 au Cv 514 Km 67,231 / V2S de la PATC km 65,976 au JI Z506/512 Km 67,200 / V3G de la Butte Km 67,174 au Cv 504 Km 67,259  Domaine S9 : ZEPG 96+158+160+1",null,"Medium","6","Planned"]
["SNCF-R","14110119961",null,"< >","Miramas - Aig Km 805,1","St-Chamas",2024,2024,13,13,"2024-03-30","00:00:00","2024-03-31","12:00:00","Periodical",null,"CCR OP1, OCP2 36h We S13/14, V2+V2Bis+VBCirc/VB+Tête de voies F. Départ :  Etendue S9 : V2 du Cv647 Km 809,384 au C204 Km 805,240 et V2Bis TTes Zeps / VBCirc=>VB du C601 Km 808,650 au C639 Km 809,349 / F.Départ du des GF Km 808,750 au Km 808,887   Domaine",null,"Medium","6,7","Planned"]
["SNCF-R","14552158561",null,"< >","Miramas - Bât Voyageurs","St-Chamas",2024,2024,12,12,"2024-03-20","00:10:00","2024-03-23","05:10:00","Periodical",null,"SA2024, Tir823/08  : DEF V1+V2 de MAS à RGC de 05h00  Etendue S9 : V1 du C653 Km 810,004 de Mas au C1 Km 834,933 de Rognac+ V2 depuis PATC de RGC Km 834,175 au C 651 Km 810,004 de Mas  Domaine S9 : V1 ZEP G Mas 99 + Les Roques ZEP G 801+821+841 + Berre ZE",null,"Medium","3,4,5,6","Planned"]
["SNCF-R","14012551761",null,"< >","Miramas - Relais La Crau","St-Chamas",2024,2024,4,4,"2024-01-27","00:15:00","2024-01-28","12:15:00","Periodical",null,"OCP1 36h, WE S04/05, sur VC, VD, V1MRS (passage par A circ+1Ter+B Circ+AM) :  Etendue S9 : 1S=>VD du JI Z605/617 Km 68,120 au C 627 Km 68,512 + 2S=>VC du Cv 615 Km 68,000 au C 625 Km 68,564 / V1Mrs du C 603 Km 808,585 au C 623 Km 68,564/809,312  Domaine S",null,"Medium","6,7","Planned"]
["SNCF-R","13687356661",null,"< >","Miramas - Bât Voyageurs","Berre",2024,2024,50,50,"2023-12-11","10:35:00","2024-12-13","11:46:00","Periodical",null,"2024_SE_27 : vibration de -5' pour avoir TER 17701 en SO et TER 886565 en SF  MC19-0146 Passage entre 879653 et 87655 Modif suite main courante 2020 Min-547-871    ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687357461",null,"< >","Miramas - Bât Voyageurs","Berre",2024,2024,50,50,"2023-12-11","10:20:00","2024-12-13","11:08:00","Periodical",null,"Annulation Décalage MC17-0229 pour 879610 le 21/10/15 2021_SE_65 décalage de + 40mn pour avoir 879518 en SO et 879522 en SF, aligné V2 de St Louis à Tarascon, le 19/11/2019",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687359061",null,"< >","Berre","Rognac - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:46:00","2024-12-13","11:49:00","Periodical",null,"2024_SE_28 : vibration de -10' pour avoir TER 17701 en SO et TER 886565 en SF  MC19-0032 le 19/09/17 pour alignement sur 9F_MAS-RGC_002 MC19-0147 le 10/11/17 calage entre 879653 et 879655 Modif main courante 2020 Maj-548-871     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687359861",null,"< >","Berre","Rognac - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:08:00","2024-12-13","11:05:00","Periodical",null,"Annulation Décalage MC17-0228 pour 879610 2021_SE_66 : décalage de +40mn pour avoir 879518 en SO et 879522 en SF, aligné V2 de St Louis à Tarascon, le 19/11/2019",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13686995261",null,"< >","Miramas - Bât Voyageurs","Fos-sur-Mer - ITE Lafarge",2024,2024,10,50,"2024-04-08","22:30:00","2024-04-19","04:30:00","Periodical",null,"Demande EF d'avancer les fenêtres génériques Miramas - Lavalduc, Lavalduc - Fos et Lavalduc - Martigues d'une heure. Validation lors de la Concertation SE-NEN du 25/11/2014.   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14113365161",null,"< >","Miramas - Bât Voyageurs","Fos-sur-Mer - ITE Lafarge",2024,2024,21,40,"2024-05-21","22:00:00","2024-10-04","05:30:00","Periodical",null,"CCR OP1, DEF 07h30 MAS<=>LVU",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13686995261",null,"< >","Miramas - Bât Voyageurs","Fos-sur-Mer - ITE Lafarge",2024,2024,10,50,"2024-03-04","22:30:00","2024-12-13","04:30:00","Periodical",null,"Demande EF d'avancer les fenêtres génériques Miramas - Lavalduc, Lavalduc - Fos et Lavalduc - Martigues d'une heure. Validation lors de la Concertation SE-NEN du 25/11/2014.   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13686993661",null,"< >","Miramas - Bif Km 811,8","Fos-sur-Mer - ITE Lafarge",2024,2024,50,50,"2023-12-11","14:51:00","2024-12-13","16:06:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687470661",null,"< >","Rassuen","Fos-sur-Mer - ITE Lafarge",2024,2024,15,17,"2024-04-08","22:30:00","2024-04-28","04:30:00","Periodical",null,"SA2024, UP SES Voie Avignon, CAP 6H V2 LVU PRA LAVALDUC coté PdB, à prendre avec 4F_MAS-LVU_001 et 4C_LVU_005   Domaine S9 : ZEP 2+4+6+8+10          ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15183724661",null,"< >","Croix-Sainte","Martigues - Bât Voyageurs",2024,2024,10,48,"2024-03-04","22:30:00","2024-11-29","04:30:00","Periodical",null,"SM+Télécommande Pont de Caronte, sans aménagement d'ouverture de Pont : PORT DE BOUC - MARTIGUES (MIRAMAS - MARSEILLE-ST CH (PORT DE BOUC) MARSEILLE-MARITIME SUD DE MIRAMAS)        Ouvertures et fermetures liées à la manoeuvre du viaduc de Caronte  Etendu",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14537508361",null,"< >","Croix-Sainte","Martigues - CV 878",2024,2024,8,38,"2024-02-19","22:30:00","2024-09-22","04:30:00","Periodical",null,"SA2024, UP SES Avi :  Domaine S9 : ZEP 33+40+46(V4)+75(Sortie VS 3 à 11) ou ZEP 35+38 ou ZEP 42(V4G)+74 ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13836777961",null,"< >","L'Isle-Fontaine-de-Vaucluse","Orgon",2024,2024,44,47,"2024-10-28","08:25:00","2024-11-22","16:55:00","Periodical",null,"Tvx PPx V1+V2 (de S44 à S47), -Avignon Fontcouverte exclu à Miramas exclu- et à prendre avec 4D_AFT-CVN_028  :  Etendue S9 : V1 de la PATC Km 4,283 au C507 au Km 66,880 de Mas / V2 De la PATC Km 65,976 au C88 Km 3,645   Domaine S9 : DFV L CAV-MAS V1/ V2+ ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13836727061",null,"< >","L'Isle-Fontaine-de-Vaucluse","Orgon",2024,2024,48,50,"2024-11-25","08:25:00","2024-12-13","16:55:00","Periodical",null,"Tvx PPx V1+V2 (de S48+49+50 SA2024 et 51 de 2024 sur SA2025) -Avignon Fontcouverte inclus à Miramas exclu-, à prendre avec 4C_AV_068 +4C_AFT-CVN_002+4D_AFT-CVN_029+4D_CVN-MAS_014 :    Etendue S9 : V1 du Km 0+730 (Cv105 d'AFT) au Km 66+880 (C507 de Mas) et",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689385561",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2024-09-16","23:30:00","2024-10-31","04:55:00","Periodical",null,"Modification de la fenêtre pour le passage du TGV 6129 (avec marge pour anticiper le décalage du sillon lié à des LTV) en sillon ouvrant et TER 8810402 en sillon fermant (avec marge pour anticiper le décalage du sillon lié à des LTV). La forme en trapèze ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13886949661",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,41,41,"2024-10-12","00:01:00","2024-10-13","04:01:00","Periodical",null,"Réfection aqueduc Km 26,242 OCP 28h We S41 :  Domaine S9 : V1 DFV L AUB-CIS + ZEPG CIS 21 / V2 ZEP G CIS 22 + DFV L CIS-AUB  Domaine S11 : Sél ou Ssr correspondant  Nota : VS impaires prises ZEP 23  ",null,"Medium","6,7","Planned"]
["SNCF-R","13689388961",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2023-12-11","11:10:00","2024-12-13","11:26:00","Periodical",null,"MC19-0070 pour augmentation de l'amplitude horaire à 1h00 2021_SE_81 + 2021_SE_82 + 2021_SE_83 : décalage de quelques minutes pour avoir 881426 en SO",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689384761",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2023-12-11","08:48:00","2024-12-13","10:29:00","Periodical",null,"decalage MC18-0281 pour Thello 145  2021_SE_87 + 2021_SE_88 + 2021_SE_89 : décalage pour avoir 881611 en SF",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689385561",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-13","04:55:00","Periodical",null,"Modification de la fenêtre pour le passage du TGV 6129 (avec marge pour anticiper le décalage du sillon lié à des LTV) en sillon ouvrant et TER 8810402 en sillon fermant (avec marge pour anticiper le décalage du sillon lié à des LTV). La forme en trapèze ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689385561",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2024-09-30","23:30:00","2024-12-06","04:55:00","Periodical",null,"Modification de la fenêtre pour le passage du TGV 6129 (avec marge pour anticiper le décalage du sillon lié à des LTV) en sillon ouvrant et TER 8810402 en sillon fermant (avec marge pour anticiper le décalage du sillon lié à des LTV). La forme en trapèze ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689385561",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2024-12-02","23:30:00","2024-12-13","04:55:00","Periodical",null,"Modification de la fenêtre pour le passage du TGV 6129 (avec marge pour anticiper le décalage du sillon lié à des LTV) en sillon ouvrant et TER 8810402 en sillon fermant (avec marge pour anticiper le décalage du sillon lié à des LTV). La forme en trapèze ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689385561",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2024-09-30","23:30:00","2024-11-15","04:55:00","Periodical",null,"Modification de la fenêtre pour le passage du TGV 6129 (avec marge pour anticiper le décalage du sillon lié à des LTV) en sillon ouvrant et TER 8810402 en sillon fermant (avec marge pour anticiper le décalage du sillon lié à des LTV). La forme en trapèze ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13886964061",null,"< >","La Ciotat","La Seyne-Tamaris-sur-Mer - Aig Km 59,9 PA",2024,2024,50,13,"2023-12-11","22:25:00","2024-03-28","05:25:00","Periodical",null,"Tranchée Rocheuse du PRo Reynaud, DEF 07h00, de S50 à S13 de 2024 :  Etendue S9 : V1 du C201 SNA Km 39,820 au C73 Km 59,771 LSM et V2 du C 203 Km 39,820 SNA au C 59 Km 59,690  Domaine S9 : ZEP G 41+42 + DFV L SNA-LSM V1/V2  Etendue S11 : V1 Si Sél du Km 4",null,"Major","1,2,3,4,7","Planned"]
["SNCF-R","13908516961",null,"< >","Les Arcs-Draguignan - V 3 de Garage","St-Raphaël-Valescure - Bât Voyageurs",2024,2024,45,50,"2024-11-10","22:44:00","2024-12-12","05:12:00","Periodical",null,"HS Fréjus-Nice - zone Fréjus- :  Etendue S9 : V1 du C30 Km 136,335 au C17 Km 160,238 et V2 du C22 Km 136,335 au C14 Km 160,694  Domaine S9 : V1 Groupement de ZEP type L Les Arcs Saint Raphaël V1 et ZEP 101+103+105+107+109 de SRV et V2 ZEP de SRV ZEP 118+1",null,"High","1,2,3,4,7","Planned"]
["SNCF-R","13689487961",null,"< >","Les Arcs-Draguignan","Boulouris-sur-Mer",2024,2024,50,50,"2023-12-11","10:02:00","2024-12-13","11:16:00","Periodical",null,"decalage MC18-0284 pour Thello 145 2021_SE_90 : décalage pour avoir 881267 en SF",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13910981761",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,47,48,"2024-11-24","21:35:00","2024-11-28","05:50:00","Periodical",null,"HS Fréjus-Nice - zone Fréjus +TTes Zones- :  ",null,"Medium","1,2,3,4,7","Planned"]
["SNCF-R","13689488761",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,50,50,"2024-10-05","00:03:00","2024-11-16","06:15:00","Periodical",null,"31/07/2019:décalage de la fenêtre pour avoir le TGV 6187 sillon ouvrant le soir positionnement horaire pour ne pas créer d'autres trains dans l'espace libéré, cet espace est prévu pour le décalage du 6187 impacté par des LTV",null,"Major","3,4,5,6","Planned"]
["SNCF-R","13689486961",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,50,50,"2024-09-30","22:44:00","2024-11-14","05:12:00","Periodical",null,"modif 2020: Maj-461-690              ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13689486161",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,50,50,"2023-12-11","13:33:00","2024-12-13","14:16:00","Periodical",null,"Modif horaire via MC 429 MC19-0068 calage pour 17478 2021_SE_76 + 2021_SE_77 + 2021_SE_78 : décalage de quelques minutes pour avoir 17484 en SF (ISO 2020) ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689488761",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,50,50,"2023-12-16","00:03:00","2024-12-14","06:15:00","Periodical",null,"31/07/2019:décalage de la fenêtre pour avoir le TGV 6187 sillon ouvrant le soir positionnement horaire pour ne pas créer d'autres trains dans l'espace libéré, cet espace est prévu pour le décalage du 6187 impacté par des LTV",null,"Major","3,4,5,6","Planned"]
["SNCF-R","13689486961",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,50,50,"2023-12-11","22:44:00","2024-12-12","05:12:00","Periodical",null,"modif 2020: Maj-461-690              ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","14600494561",null,"< >","Picon-Busserine","Picon-Busserine",2024,2024,4,9,"2024-01-22","23:00:00","2024-03-01","05:00:00","Periodical",null,"Tvx préparatoires et finitions du RAV MSC de 2024 de S04 DEF de 06h00 (yc S4 pose de LTV et S9 dépose de LTV) : L930 VA, VB/MV4 à VC/MV3, MV1+MV2 => Sr2 Km 1,060 , sur L830 D à J en passant pas C/D/E/F Circ. => jusqu'au Km 857,206(C723)/859,625 (Aig 102bV",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688630261",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","Valence - Bif Cagnard",2024,2024,51,33,"2023-12-18","12:57:00","2024-08-14","13:29:00","Periodical",null,"11401066 FEN22_StRambert-BifduCagnard(RG)_004(2F_SRA-VCE_004) :  o Heure Fin PK Fin : 13h29 au lieu de 13h32 ,  o TRAIN FERMANT 886184.                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14629399561",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,27,43,"2024-07-01","22:35:00","2024-10-24","05:35:00","Periodical",null,"Créé pour CHA 24_006301 RR double File entre SRA et VCE BOA 34100 ml - Travaux Préparatoires et Finitions  ZEP L St Rambert Valence V1 + ZEP 413+415+417 de St Rambert d´Albon - ZEP L Valence - St Rambert V2 + ZEP 402+404 et 420+422+424 ZEP 418+PP de St Ra",null,"Major","1,2,3,4","Planned"]
["SNCF-R","14633816961",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,33,41,"2024-08-12","21:35:00","2024-10-11","05:35:00","Periodical",null,"Créé pour CHA 24_006301 RR double File entre SRA et VCE BOA 34100 ml - Travaux Principaux  ZEP L St Rambert Valence V1 + ZEP 413+415+417 de St Rambert d´Albon - ZEP L Valence - St Rambert V2 + ZEP 402+404 et 420+422+424 ZEP 418+PP de St Rambert d´Albon  S",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","16030874661",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,27,43,"2024-07-05","23:30:00","2024-10-25","06:15:00","Periodical",null,"Créé pour CHA 24_006301 RR double File entre SRA et VCE BOA 34100 ml - Travaux Préparatoires et Finitions  ZEP L St Rambert Valence V1 + ZEP 413+415+417 de St Rambert d´Albon - ZEP L Valence - St Rambert V2 + ZEP 402+404 et 420+422+424 ZEP 418+PP de St Ra",null,"High","5","Planned"]
["SNCF-R","13688626261",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,23,34,"2024-06-03","10:05:00","2024-08-23","15:20:00","Periodical",null,"4h06 à 4h59 en sim 5J/7 SA2017 => TO 17709 / TF 886127 FEN22_StRambert-BifduCagnard(RG)_001(2F_SRA-VCE_001) :  o Heure Début PK Début : 10h05 au lieu de 09h59 ,  o Heure Fin PK Début : 14h56 au lieu de 14h59,  o Heure Début PK Fin : 10h32 au lieu de 10h24",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688628661",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,35,48,"2024-08-26","12:02:00","2024-11-29","13:28:00","Periodical",null,"11401037 A vigiler passage du 886185 (demande TER en RP0 RAA du 14/06/2017 sur CHA17_0016613) à h+29 à VCE BG dans la trame 2h SA2019 (passage à 13h26 dans le préconstruit 2018). Sinon réduire fin de plage PKfin à 13h25.                    ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688627061",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,21,47,"2024-05-26","23:12:00","2024-11-24","02:51:00","Periodical",null,"10800589",null,"High","7","Planned"]
["SNCF-R","13688625461",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","Valence - Bât Voyageurs",2024,2024,23,34,"2024-06-03","10:01:00","2024-08-23","14:29:00","Periodical",null,"4h06 à 4h59 en sim 5J SA2017 => TO 17706 / TF 886118 Décalage MC18-0157 MC18-0160 réduction pour 886118                       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688631861",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bât Voyageurs",2024,2024,4,41,"2024-01-22","22:40:00","2024-10-11","04:30:00","Periodical",null,"Créée initialement  pour chantier de Maintenance (Engins,... )  Toutes ZEP et S.él de SRA à VCE (Bif du Cagnard)",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15036019061",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bât Voyageurs",2024,2024,45,45,"2024-11-10","22:15:00","2024-11-10","05:15:00","Periodical",null,"Créée initialement pour CHA26_0026458 - HPGV SE MeS  ------------------ ATTENTION -----------------  Coupure IHM3 CCSL  --------------------------------------------------",null,"Medium","7","Planned"]
["SNCF-R","14970478761",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bât Voyageurs",2024,2024,15,37,"2024-04-13","22:35:00","2024-09-14","05:55:00","Periodical",null,"Créé Pour CHA20_0018098 HPGV SE   Essais Poste à poste et essais en long IHM : Poste 51 Alixan / P10 Chateauneuf sur Isère / P60 St Marcel les Valences +  PCD Moirans / SAE LGV SE / IHM3 CCSL (A globaliser avec demande sur IFP ALPES  Toutes ZEP et Sel ent",null,"Medium","6","Planned"]
["SNCF-R","13688631061",null,"< >","Valence - ITE Km 611,695","Valence - Bât Voyageurs",2024,2024,51,48,"2023-12-18","12:17:00","2024-11-29","13:17:00","Periodical",null,"2024_SE_21 : vibration de +3mn pour avoir Fret PNBP07 en SO   2021_SE_26 : décalage de -25mn alignement avec 1F_POR-LIV_004 pour croisement entre 96634 et 17576 en fin de fenêtre + 17574 en IPCS de Valence à Bif du Cagnard, le 14/11/2019  11401077  MC18-0",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688627861",null,"< >","Valence - ITE Km 611,695","Valence - Bât Voyageurs",2024,2024,22,48,"2024-05-27","02:10:00","2024-11-25","05:10:00","Periodical",null,"11401131",null,"High","1","Planned"]
["SNCF-R","13688591261",null,"< >","Vienne - Bât Voyageurs","St-Rambert-d'Albon - Voie 12 Garage",2024,2024,23,27,"2024-06-03","09:43:00","2024-07-05","14:55:00","Periodical",null,"4h22 à 4h59 en sim 5J/7 SA2017 => TO 17709 / TF 886127 A vigiler passage du TO 17709 (demande TER en RP0 RAA du 14/06/2017 sur CHA17_0016613) à h+42 à VIE dans la trame 2h SA2019 (passage à 9h41 dans le préconstruit 2018). Plage décalée à 9h43/14h43 PK dé",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688592061",null,"< >","Vienne - Bât Voyageurs","St-Rambert-d'Albon - Bif Km 570,2",2024,2024,23,27,"2024-06-03","10:21:00","2024-07-05","14:55:00","Periodical",null,"4h22 à 4h59 en sim 5J/7 SA2017 => TO 17706 / TF 886118 Décalage MC18-0158 MC18-0160 : Réduction 886118                                 ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15092851861",null,"< >","Vienne - Bât Voyageurs","St-Rambert-d'Albon - Bât Voyageurs",2024,2024,7,45,"2024-02-12","22:40:00","2024-11-10","04:30:00","Periodical",null,"Créée Pour Maintenance spécialisée avec Engins lourds (Entreprises...)  ZEP et Sel de Vienne à Sra  ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14671255261",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","Andancette - Bât Voyageurs",2024,2024,22,30,"2024-05-27","22:35:00","2024-07-28","05:35:00","Periodical",null,"Créé pour CHA 24_0026405 RAG De St-Rambert-D'Albons  Sél 8+10 Sr Champ Rolland St Rambert V1",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14569321061",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Andancette - Bât Voyageurs",2024,2024,6,49,"2024-02-05","22:10:00","2024-12-05","05:15:00","Periodical",null,"Créée pour CHA 24_0026620 - CCR Tx SeG : Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles VT + Essais Poste 58  CCTT Toutes  ZEP de SRA - Sr Champ Rolland St Rambert voie - Sr Peyraud Champ Rolland St Rambert V2",null,"Major","1,2,3,4","Planned"]
["SNCF-R","14984882661",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Andancette - Bât Voyageurs",2024,2024,6,49,"2024-02-05","23:05:00","2024-12-08","06:15:00","Periodical",null,"Créée pour CHA 24_0026620 - CCR Tx SeG : Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles VT + Essais Poste 58  CCTT Toutes  ZEP de SRA - Sr Champ Rolland St Rambert voie - Sr Peyraud Champ Rolland St Rambert V2",null,"Major","5","Planned"]
["SNCF-R","14669234461",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Andancette - Bât Voyageurs",2024,2024,19,33,"2024-05-06","22:35:00","2024-08-18","05:35:00","Periodical",null,"Créée pour CHA 24_0026405- RAG de SRA :   Sél  9 drSr Champ Rolland St Rambert voie 1 ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14568473161",null,"< >","St-Vallier-sur-Rhône - Voie 4 Garage","St-Vallier-sur-Rhône - Voie 5 Garage",2024,2024,12,46,"2024-03-18","22:25:00","2024-11-14","05:00:00","Periodical",null,"Créée pour CHA 24_0026620 -  CCR 5 - Travaux SeG SAINT VALLIER :  Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58   ZEP L St-Rambert St-Vallier  V1 - ZEP 201+203+205 de St Vallier  - ZEP L St-Vallier Tain Voie 1 - Secteurs St",null,"Major","1,2,3,4","Planned"]
["SNCF-R","14558253561",null,"< >","St-Vallier-sur-Rhône - Voie 4 Garage","St-Vallier-sur-Rhône - Voie 5 Garage",2024,2024,4,11,"2024-01-22","21:35:00","2024-03-15","05:20:00","Periodical",null,"Créée pour CHA 24_0026620 -  CCR 5 - Travaux Voie SAINT VALLIER KM 583 au KM 585+200 + Tx SeG :  Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58   ZEP L St-Rambert St-Vallier  V1 - ZEP 201+203+205 de St Vallier  - ZEP L St-Va",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15036569261",null,"< >","St-Vallier-sur-Rhône - Voie 4 Garage","St-Vallier-sur-Rhône - Voie 5 Garage",2024,2024,45,45,"2024-11-10","22:15:00","2024-11-10","05:15:00","Periodical",null,"Créée initialement pour CHA26_0026458 - HPGV SE MeS  Report des mesures de protections sur les postes encadrants.  ------------------ ATTENTION -----------------  Coupure IHM3 CCSL  --------------------------------------------------",null,"Medium","7","Planned"]
["SNCF-R","14970519361",null,"< >","St-Vallier-sur-Rhône - Voie 4 Garage","St-Vallier-sur-Rhône - Voie 5 Garage",2024,2024,15,37,"2024-04-13","22:35:00","2024-09-14","05:55:00","Periodical",null,"Créée pour CHA20_0018098 HPGVSE  Essais Poste à poste et essais en long IHM : Poste 51 Alixan / P10 Chateauneuf sur Isère / P60 St Marcel les Valence +  PCD Moirans / SAE LGV SE / IHM3 CCSL (A globaliser avec demande sur IFP ALPES)  Toutes ZEP et Sel de S",null,"Medium","6","Planned"]
["SNCF-R","14568462161",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","La Roche-de-Glun - Bât Voyageurs",2024,2024,12,46,"2024-03-18","22:25:00","2024-11-14","05:00:00","Periodical",null,"Créée pour CCR 5 -  Tx SeG Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58  ZEP L St-Rambert Vallier Voie 1 - ZEP L St Vallier St Rambert V2 - ZEP 201+203+205 ZEP 202+204+206+208 -  ZEP L St Vallier Tain Voie 1 - ZEP L Tain S",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14562487861",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","La Roche-de-Glun - Bât Voyageurs",2024,2024,6,8,"2024-02-05","21:35:00","2024-02-23","05:20:00","Periodical",null,"Créée pour CCR 5 - Travaux Voie SAINT VALLIER KM 583 au KM 585+200 + Tx SeG ravaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58  ZEP L St-Rambert Vallier Voie 1 - ZEP L St Vallier St Rambert V2 - ZEP 201+203+205 ZEP 202+204+206+20",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14985061761",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","La Roche-de-Glun - Bât Voyageurs",2024,2024,4,11,"2024-01-22","22:10:00","2024-03-17","05:45:00","Periodical",null,"Créée pour CCR 5 - Travaux Voie SAINT VALLIER KM 583 au KM 585+200 + Tx SeG ravaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58  ZEP L St-Rambert Vallier Voie 1 - ZEP L St Vallier St Rambert V2 - ZEP 201+203+205 ZEP 202+204+206+20",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14985100761",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","La Roche-de-Glun - Bât Voyageurs",2024,2024,12,46,"2024-03-18","23:30:00","2024-11-17","06:00:00","Periodical",null,"Créée pour CCR 5 -  Tx SeG Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58  ZEP L St-Rambert Vallier Voie 1 - ZEP L St Vallier St Rambert V2 - ZEP 201+203+205 ZEP 202+204+206+208 -  ZEP L St Vallier Tain Voie 1 - ZEP L Tain S",null,"High","5","Planned"]
["SNCF-R","14714567061",null,"< >","Condrieu","Sarras",2024,2024,12,21,"2024-03-18","07:45:00","2024-05-24","15:45:00","Periodical",null,"Créé pour CHA24_0025937 RVB PEY  Toutes ZEP de Peyraud P1 - + Zep 426  438  442 de St Rambert - + ZEP type L Entre PEY et LVO V1 et V2  Sr Limony - Peyraud V1   Sr Limony - Peyraud V2  Sr. Peyraud - Ozon V1  Sr. Peyraud - Ozon V2   S.El 18P S.El 20P du Se",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688229461",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Montanay-Bif",2024,2024,50,50,"2023-12-11","12:21:00","2024-12-13","13:11:00","Periodical",null,"10700733",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688230261",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Montanay-Bif",2024,2024,50,50,"2023-12-11","14:33:00","2024-12-13","15:44:00","Periodical",null,"10700732 2021_SE_106 + 2021_SE_107 + 2021_SE_108 + 2021_SE_109 + 2021_SE_110 + 2021_SE_111 : décalage de quelques minutes pour avoir 6615 en SO et 6617 en SF",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688383661",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-15","22:10:00","2024-12-13","05:18:00","Periodical",null,"7h18 de sim. partielle déduite. SA2018 => + ME 9/05 + ME 31/10                            ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688385261",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-15","23:21:00","2024-12-13","05:52:00","Periodical",null,"6h21 de sim. partielle déduite SA2018 => + ME 9/05 + ME 31/10            ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688388061",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,49,"2023-12-16","23:20:00","2024-12-07","07:25:00","Periodical",null,"fenêtre applicable sa/di  train ouvrant  9098 quand il circule, train fermant 6136",null,"Major","6","Planned"]
["SNCF-R","13688389061",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,49,49,"2023-12-10","23:30:00","2024-12-08","06:10:00","Periodical",null,"fenêtre applicable di/lu train ouvrant 6137, train fermant 6900",null,"Major","7","Planned"]
["SNCF-R","13688382861",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-11","12:11:00","2024-12-13","13:03:00","Periodical",null,"10701424",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688384461",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-11","14:44:00","2024-12-13","15:50:00","Periodical",null,"10701421",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688381261",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-11","22:23:00","2024-12-09","05:45:00","Periodical",null,"6h50 de sim. partielle déduite. Pour SA2018 => LU/MA + jours typés LU : MA/ME 26-27/12, MA/ME 02-03/01, MA/ME 03-04/04, ME/JE 02-03/05, MA/ME 22-23/05         ",null,"Major","1,2,3","Planned"]
["SNCF-R","13688380461",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-12","22:10:00","2024-12-12","05:45:00","Periodical",null,"7h15 de sim. partielle déduite. Sauf jours particulier TGV typé LU ou VE  SA2018 => SF ME 9/05 + ME 31/10      ",null,"Major","2,3,4","Planned"]
["SNCF-R","13688386061",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,52,46,"2023-12-25","23:40:00","2024-11-11","06:00:00","Periodical",null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022       ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688382061",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-11","21:48:00","2024-12-12","05:17:00","Periodical",null,"7h18 de sim. partielle déduite. Sauf jours typés VE  sur le calendrier TGV SA2018 => SF ME 9/05 + ME 31/10                       ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688387061",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,52,46,"2023-12-25","23:00:00","2024-11-11","06:00:00","Periodical",null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14629096761",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 44 Grenay - Transition TVM",2024,2024,3,5,"2024-01-20","00:15:00","2024-02-03","05:30:00","Periodical",null,"Plage créée pour le CHA20_0018098, essai de poste à poste avec l'infrapôle Rhodanien  Toute la zone du poste 44 de Grenay est concernée  Plage sans impact pour les circulations.",null,"Medium","5,6","Planned"]
["SNCF-R","14628965661",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,3,5,"2024-01-20","00:15:00","2024-02-03","05:30:00","Periodical",null,"Plage créée pour le CHA20_0018098, essai de poste à poste avec l'infrapôle Rhodanien  Toute la zone du poste 44 est concernée  Plage sans impact pour les circulations.",null,"Medium","5,6","Planned"]
["SNCF-R","14418916661",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-09-02","22:45:00","2024-10-21","06:15:00","Periodical",null,"Notion V1 ou V2 en grand lu/ma et jours en lu/ma  (en raison du 6131 circulant dans sa variante du lundi) Pour le CHA24_0026280 Cas V2 sim lu/ma lorsque DEF24_MXO-GNA_006 est prise sur V1 Cas V1 sim lu/ma lorsque DEF24_MXO-GNA_007 est prise sur V2  Pour l",null,"Major","1,2","Planned"]
["SNCF-R","14419102261",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-09-03","22:35:00","2024-10-24","06:15:00","Periodical",null,"Notion V1 ou V2 en grand ma/me à me/je:  Pour le CHA24_0026280 Cas V2 sim ma/me à me/je lorsque DEF24_MXO-GNA_006 est prise sur V1 Cas V1 sim ma/me à me/je lorsque DEF24_MXO-GNA_007 est prise sur V2  Pour le CHA24_0026378 Cas V2 sim ma/me à me/je lorsque ",null,"Major","2,3,4","Planned"]
["SNCF-R","14975846361",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,36,43,"2024-09-02","21:20:00","2024-10-24","06:20:00","Periodical",null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_MXO-GNA_008 lu/ma ou DEF24_MXO-GNA_009 du ma/me à je/ve  sur V2  V1 derrière 6225 jusqu'au 999603 + 25 minutes Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571 + 745 + 4771 + 747",null,"Major","1,2,3,4","Planned"]
["SNCF-R","14418774961",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-09-02","21:05:00","2024-10-24","06:15:00","Periodical",null,"Notion V1 ou V2 en grand, cas V2 en grand lu/ma à je/ve, la prise de cette DEF rend applicable DEF24_MXO-GNA_008 lu/ma ou DEF24_MXO-GNA_009 ma/me à je/ve sur V1 V2 derrière 6260 jusqu'au 999600 + 10 Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 + ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","14418916661",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-01-08","22:45:00","2024-06-24","06:15:00","Periodical",null,"Notion V1 ou V2 en grand lu/ma et jours en lu/ma  (en raison du 6131 circulant dans sa variante du lundi) Pour le CHA24_0026280 Cas V2 sim lu/ma lorsque DEF24_MXO-GNA_006 est prise sur V1 Cas V1 sim lu/ma lorsque DEF24_MXO-GNA_007 est prise sur V2  Pour l",null,"Major","1,2","Planned"]
["SNCF-R","14419143661",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,26,"2024-01-12","21:50:00","2024-06-28","06:20:00","Periodical",null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_MXO-GNA_012 le ve/sa sur V2  V1 derrière 6129 et 6953  jusqu'au 999603 + 25 minutes  Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571 + 745 + 4771 + 747  Consignation C: Sr Grena",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14419182161",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,26,"2024-01-12","22:05:00","2024-06-28","06:15:00","Periodical",null,"Notion V1 ou V2 en grand, cas V2 en grand rend applicable DEF24_MXO-GNA_012 le ve/sa sur V1 V2 derrière 6206 jusqu'au 999600 + 10  Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 + 4472 + 4474 + 843   Consignation C: Sr Grenay DV2 + SEL 1002 Sr Cham",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14419210161",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,26,"2024-01-12","23:50:00","2024-06-28","06:15:00","Periodical",null,"Notion V1 ou V2 en grand le ve/sa  Cas V2 sim ve/sa lorsque DEF24_MXO-GNA_010 est prise sur V1 Cas V1 sim ve/sa lorsque DEF24_MXO-GNA_011 est prise sur V2   Derrière 6137  jusqu'au 999603 + 25 minutes ou 999600 + 10   Zeps V1:  743 + 4471 + 4473 + 4475 + ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14419334061",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,14,21,"2024-04-01","22:45:00","2024-05-20","06:20:00","Periodical",null,"Notion V1 ou V2 en grand, cas V1 en grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05 rend applicable en sim DEF24_MXO-GNA_015  sur V2  V1 derrière 6131  jusqu'au 999603 + 25 minutes  Zeps V1 : 743 + 4471 + 4473 ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14419483361",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,14,21,"2024-04-01","23:50:00","2024-05-20","06:15:00","Periodical",null,"Notion V1 ou V2 en grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05 Cas V2 sim ve/sa lorsque DEF24_MXO-GNA_013 est prise sur V1 Cas V1 sim ve/sa lorsque DEF24_MXO-GNA_014 est prise sur V2   Derrière 6137  jusqu'",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14413142561",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,26,"2024-01-08","20:55:00","2024-06-27","06:20:00","Periodical",null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_MXO-GNA_008 lu/ma ou DEF24_MXO-GNA_009 du ma/me à je/ve  sur V2  V1 derrière 6225 moins 25 minutes jusqu'au 999603 + 25 minutes Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571 +",null,"Major","1,2,3,4","Planned"]
["SNCF-R","14419414161",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,14,21,"2024-04-01","22:50:00","2024-05-20","06:15:00","Periodical",null,"Notion V1 ou V2 en grand, cas V2 en grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05, rend applicable DEF24_MXO-GNA_015 sur V1 V2 derrière 6186 jusqu'au 999600 + 10 Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 457",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14418774961",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-01-08","21:05:00","2024-06-27","06:15:00","Periodical",null,"Notion V1 ou V2 en grand, cas V2 en grand lu/ma à je/ve, la prise de cette DEF rend applicable DEF24_MXO-GNA_008 lu/ma ou DEF24_MXO-GNA_009 ma/me à je/ve sur V1 V2 derrière 6260 jusqu'au 999600 + 10 Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 + ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","14419102261",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-01-09","22:35:00","2024-06-27","06:15:00","Periodical",null,"Notion V1 ou V2 en grand ma/me à me/je:  Pour le CHA24_0026280 Cas V2 sim ma/me à me/je lorsque DEF24_MXO-GNA_006 est prise sur V1 Cas V1 sim ma/me à me/je lorsque DEF24_MXO-GNA_007 est prise sur V2  Pour le CHA24_0026378 Cas V2 sim ma/me à me/je lorsque ",null,"Major","2,3,4","Planned"]
["SNCF-R","14886304761",null,"< >","Montanay-Bif","Grenay-PRG - Rep4431-Pk419,4",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00","Periodical",null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00",null,"Medium","1,2,3,5,6,7","Planned"]
["SNCF-R","13688213261",null,"< >","Poste 44 Grenay - Bif de Lyon","Valence-TGV - Bif de Valence",2024,2024,50,50,"2023-12-11","14:50:00","2024-12-13","16:09:00","Periodical",null,"10701426",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688214861",null,"< >","Poste 44 Grenay - Bif de Lyon","Valence-TGV - Bif de Valence",2024,2024,50,50,"2023-12-11","12:07:00","2024-12-13","12:46:00","Periodical",null,"10701429",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14545016661",null,"< >","Avignon - Bif Rac","L'Ardoise - Voie 2Bis",2024,2024,15,15,"2024-04-12","22:35:00","2024-04-12","03:05:00","Periodical",null,"SA2024, UP SES Avignon :   Etendue S9 : V1 du C103 Km 740,569 au Ji Z106/112 Km 740,700 +V2 du C102 Km 740,790 au C101 Km 740,597 L830 Avi Nord    Domaine S9 : ZEP 507+510+511+512",null,"Medium","5","Planned"]
["SNCF-R","14545251861",null,"< >","Avignon - Bif Cavaillon","Avignon - Bât Voyageurs",2024,2024,14,14,"2024-04-02","22:35:00","2024-04-05","03:05:00","Periodical",null,"SA 2024, UP SEs Avignon :  Etendue S9 : L830 V1 du Cv115 Km 740,895 (GF Aig 108) au+V2 du Cv 113 Km 740,895 au (C110 Km 741,130)=>VA/B/C C118 à 112 Km 741,107 -559 non prise cause It Alternatif-   Domaine S9 : ZEP 521+522+523+524+525+529+531+533+535+539 -",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14544875661",null,"< >","Avignon - Bif Cavaillon","Avignon - Bât Voyageurs",2024,2024,15,15,"2024-04-10","09:10:00","2024-04-11","13:10:00","Periodical",null,"SA2024, UP Voie Avignon :  Etendue S9 : L925, V2 AMS du C 68 Km 0,860 au JI Z117/401 Km0,547 + L830, V1Bis du Km 740,800 au Km 741,102  Domaine S9 : ZEP 509+554+556+560+562+563",null,"Medium","3,4","Planned"]
["SNCF-R","14473742261",null,"< >","Avignon - Bif Cavaillon","Avignon - Bât Voyageurs",2024,2024,2,2,"2024-01-08","21:50:00","2024-01-12","03:10:00","Periodical",null,"SA 2024, Famille B de 05h20 :    étendue du domaine : L925 V1 du Km 0,547 à la Pte de l'Aig 5  Km 2+244/ V2 du Km 0,547 au Cv48 Km 2,227 et V1Bis+V2Bis du 740,598/7 jusqu'au Km 741,180 et V2Bis Km 741,093.  Domaine S9 :  V1bis/V1 L925, 563+556+509  /  V2B",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15036281461",null,"< >","Avignon - Bif Rac","Avignon - Bât Voyageurs",2024,2024,14,15,"2024-04-02","21:50:00","2024-04-12","03:10:00","Periodical",null,"SA 2024, Famille B de 05h20 :    étendue du domaine : V1 du JI Z4/5 Km 739,850 au GF Aig. 113 Km 740,950 /V2 du C2 Km 739, 768 au C113 Km 740,895  Domaine S9 : ZEP V1  505+507+511+513+521+523 / V2  508+510+512+514+520 d'Avignon  Domaine S11 : Sel 2093 SR ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13687134661",null,"< >","Villeneuve-lès-Avignon - Bif de Nîmes","Avignon - Bât Voyageurs",2024,2024,10,11,"2024-03-04","09:57:00","2024-03-17","14:49:00","Periodical",null,"RPU Fam B, AVIGNON  :   Etendue S9 : Voie 1+2 VAV + V102 ZEP (V1/V2 VAV V2 de la pointe de l'aig 405 Km 2,135 (C401) à la pointe AIG 189 Km 4,087+ V1 de la pointe de AIG 190 Km 3,690 à la pointe de l'aig 407 Km 2,125 et voie 102 de la pointe de l'AIG 190 ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13836845561",null,"< >","Avignon - Bif Cavaillon","Avignon-Fontcouverte - Fais Réc Impair",2024,2024,48,50,"2024-11-25","08:25:00","2024-12-13","16:55:00","Periodical",null,"Tvx PPx V1+V2 (de S48+49+50 du SA2024 et S51 de 2024 sur SA2025) -Avignon Fontcouverte inclus à Miramas exclu-, à prendre avec 4D_AFT-CVN_029  :  Etendue S9 : V1 du Km 0+730 (Cv105 d'AFT) au Km 66+880 (C507 de Mas) et V2 au Km 65+976 (PATC de Mas) au Km 0",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13687153661",null,"< >","AVIGNON - ENT DEPOT","Avignon-Fontcouverte - Fais Réc Impair",2024,2024,16,39,"2024-04-15","09:10:00","2024-09-27","14:10:00","Periodical",null,"RPU Maintenance, épuration, Voie AVI (ESV méca) S16+17 et S38+39 (SR Voie sur zone de l'ITE SMEA de S38 à S43) :  Etendue S9 : AMS V2 du C88 Km 3,645 au Cv48 Km 2,227 / AMS V1 du ZI z127/129 Km 2,244 à la PATC Km 4,283   Domaine S9 : AMS V2 (ZEP G 927+918",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13687038861",null,"< >","Avignon-Fontcouverte - Chantier TAC","Avignon-Fontcouverte - Fais Récep Pair",2024,2024,42,50,"2024-10-14","09:10:00","2024-12-13","13:10:00","Periodical",null,"PRO RD907 PK 2,247 (mise en peinture)-bout de S11 V1AMS- :   Etendue S9 : du JI z121/123 Km 2,092 au Cv64 V5à11 Km 2,341 + Cv65 V15à27 Km 2,341 / de la butte Km 1,846 au Cv47 Km 2,255 /V1 AMS du C35 Km 1,902 au Cv62 Km 2,427 / V2 AMS du Cv37 Km 2,048 au C",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687038061",null,"< >","Avignon-Fontcouverte - Chantier TAC","Avignon-Fontcouverte - Fais Récep Pair",2024,2024,37,41,"2024-09-09","09:10:00","2024-10-11","15:50:00","Periodical",null,"PRO RD907 PK 2,247 (mise en peinture)-bout de S11 V1AMS- :   Etendue S9 : du JI z121/123 Km 2,092 au Cv64 V5à11 Km 2,341 + Cv65 V15à27 Km 2,341 / de la butte Km 1,846 au Cv47 Km 2,255 /V1 AMS du C35 Km 1,902 au Cv62 Km 2,427 / V2 AMS du Cv37 Km 2,048 au C",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14559555261",null,"< >","Avignon - Bif Cavaillon","Avignon-Champfleury - Aig Km 743,5",2024,2024,38,39,"2024-09-16","22:17:00","2024-09-29","01:55:00","Periodical",null,"Lot G C SUD, AVI, VTE+RFC :   Etendue S9 : V1 du C163 Km 741,604 au C255 m 743,417  + vers tête des voies VA , VB, VC   Domaine S9 Depuis A/B/C vers V1: ZEP G AVI 597(VA)+573(VB)+575(VC)+586+584+582+588+590+594+596+598   Etendue S11 Depuis A/B/C/D/E vers ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14560456661",null,"< >","Avignon - Bât Voyageurs","Avignon-Champfleury - FSC Réception",2024,2024,13,14,"2024-03-25","22:05:00","2024-04-05","01:55:00","Periodical",null,"SA 2024, VG, Avi Lot 4  :  Etendue S9 : V2 du Cv148 Km 741,773 au C164 Km 741,910   Domaine S9 : 576+594  Etendue S11 : V2 du Km 741,663 au Km 742,550  Domaine S11 : Sel 2098 Sr Foncouverte Champfleury V2",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14557402061",null,"< >","Avignon - Bif Rac","Avignon-Champfleury - FSC Réception",2024,2024,38,39,"2024-09-16","22:17:00","2024-09-27","01:55:00","Periodical",null,"Lot G C SUD, AVI, VTE+RFC à prendre avec 4C_AV_086 :   Etendue S9 : V2 du GF Aig 101 Km 740,655 du C176 Km 742,286    Domaine S9 V2 : ZEP G AVI V2 512+514+520+522+524+570+572+574+576+594+596+598  Etendue S11 V2 : du Km 740,719 au Km 741,604    Domaine S11",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14553510361",null,"< >","Avignon - Bât Voyageurs","Avignon-Champfleury - Aig Km 744,4",2024,2024,13,13,"2024-03-25","23:15:00","2024-03-29","04:45:00","Periodical",null,"AVI Voie 1+1 Gare,VTE+RFC, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870, équivalent Gén, à prendre avec 4D_AF-TCN_016 et 4C_TCN_013 :  Etendue S9 : V1 Côté TCN, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870  Domaine S9 : ZEP G 705+703+701 Ete",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14550052061",null,"< >","Avignon-Champfleury - Chant Multitech","Avignon-Champfleury - Aig Km 744,4",2024,2024,17,17,"2024-04-22","23:15:00","2024-04-24","04:45:00","Periodical",null,"Tir 744/15A, SA2024 (à prendre avec 4D_AF-TCN_014)  :  Domaine S9 : V1 ZEP 701+703+705 / V2 ZEP 706+704+702 +DFL Avi/TCN V1+V2 (jusqu'au V1 C601/V2 603 Km 759,095)    Etendue S11 : V1 du Km 742,441 au Km 759,179 / V2 du Km 758,757 au Km 742,573  Domaine S",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","14548126061",null,"< >","Avignon-Champfleury - Aig Km 743,9","Barbentane-Rognonas",2024,2024,18,18,"2024-04-29","23:15:00","2024-04-30","04:55:00","Periodical",null,"SA2024, UP SES Avignon :   Etendue S9 : V2 du C306 km 744,730 au C260 Km 744,165   Domaine S9 : 702+712",null,"Medium","1,2","Planned"]
["SNCF-R","14548162161",null,"< >","Avignon-Champfleury - Aig Km 743,9","Barbentane-Rognonas",2024,2024,18,18,"2024-05-02","23:15:00","2024-05-03","04:55:00","Periodical",null,"SA2024, UP SES Avignon :   Etendue S9 : V1 du C304 km 744,730 au C307 Km 744,405   Domaine S9 : 705",null,"Medium","4,5","Planned"]
["SNCF-R","14553757061",null,"< >","Avignon-Champfleury - Chant Multitech","Barbentane-Rognonas",2024,2024,14,15,"2024-04-03","00:00:00","2024-04-13","02:00:00","Periodical",null,"AVI Voie C Circ+V2Courtine+V1Courtine+HCourtine+A/B Courtine, VTE+RFC, du C154 Km 741,629 au C306 Km 744,730, à prendre avec 4C_AF-TCN_017 + 4C_AV_083 :  Etendue S9 : depuis V1Bis/2bis vers VC Circ. + VCirc du C154 Km 741,629 au C305 Km 743,974 (et du C30",null,"High","2,3,4,5,6","Planned"]
["SNCF-R","14549427561",null,"< >","Avignon-Champfleury - Chant Multitech","Barbentane-Rognonas",2024,2024,16,16,"2024-04-18","23:15:00","2024-04-19","04:45:00","Periodical",null," Tir 742/3077 (V2 à prendre avec 4C_AV_078+4D_AF-TCN_013) :  Domaine S9 : ZEP600+620+624+706+704+702+ +DFV L Avi/TCN V2 (Jusqu'au C603 Km 759,095)    Etendue S11 : du Km 758,757 au Km 742,573  Domaine S11 :  Sel 2112+2114 SR Champfleury/les Olivettes voie",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14553592661",null,"< >","Graveson-Maillane","Tarascon - Bif Rac Nord",2024,2024,13,13,"2024-03-25","23:15:00","2024-03-29","04:45:00","Periodical",null,"AVI Voie 1+1 Gare,VTE+RFC, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870, équivalent Gén, à prendre avec 4D_AF-TCN_0016 et 4C_AV_082 :  Etendue S9 : V1 Côté TCN, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870  Domaine S9 : ZEP G 705+703+701 Ete",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14551601361",null,"< >","Graveson-Maillane","Tarascon - Voies 6 Ã  10",2024,2024,15,15,"2024-04-08","23:15:00","2024-04-12","04:45:00","Periodical",null,"SA2024, Tir 714/16 + 752/11 (àprendre avec 4D_AF-TCN_015+4D_TCN-MAS_037)  :  Etendue S9 : V1 du C 304 Km 744,730 (Avignon) à la PATC Km 767+009 (Tarascon) / V2 du C 306  Km 744,730 (Avignon) au C22 Km 766,134 (Tarascon)   Domaine S9 : V1 ZEP L Avi-TCN + Z",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13836835461",null,"< >","Le Thor","L'Isle-Fontaine-de-Vaucluse",2024,2024,48,50,"2024-11-25","08:25:00","2024-12-13","16:55:00","Periodical",null,"Tvx PPx V1+V2 (de S48 à S50 du SA2024 et S51 2024 sur SA2025) - VA L'Isle-Fontaine - (de Avignon Fontcouverte inclus à Miramas exclu), à prendre avec  :    Etendue S9 : V1 du Km 0+730 (Cv105 d'AFT) au Km 66+880 (C507 de Mas) et V2 au Km 65+976 (PATC de Ma",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13809744261",null,"< >","Le Thor","L'Isle-Fontaine-de-Vaucluse",2024,2024,26,37,"2024-06-24","08:35:00","2024-09-15","16:35:00","Periodical",null,"SR Voie AMS, de S26 à S36,Tvx connexes et hors suite et S37 Tvx Préparatoires - VA L'Isle-Fontaine - Avignon  Fontcouverte exclu à Cavaillon exclu - DEF de 08h00 :  Etendue S9 : V1 de la PATC Km 4,283 (AFT) au C1 Km 32,188 / V2 de la PATC km 32,167 (CAV) ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13836816961",null,"< >","Avignon-Fontcouverte - Aig Km 3,383","Cavaillon - Bât Voyageurs",2024,2024,44,47,"2024-10-28","08:25:00","2024-11-22","16:55:00","Periodical",null,"Tvx PPx V1+V2 (de S44 à S47), -Avignon Fontcouverte exclu à Miramas exclu- et à prendre avec 4D_AFT-CVN_028  :  Etendue S9 : V1 de la PATC Km 4,283 au C507 au Km 66,880 de Mas / V2 De la PATC Km 65,976 au C88 Km 3,645   Domaine S9 : DFV L CAV-MAS V1/ V2+ ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14644066861",null,"< >","Avignon-Fontcouverte - Aig Km 3,383","Cavaillon - Bât Voyageurs",2024,2024,26,37,"2024-06-24","08:35:00","2024-09-15","16:35:00","Periodical",null,"SR Voie AMS, de S26 à S36,Tvx connexes et hors suite  et S37 Tvx Préparatoires -Avignon Fontcouverte exclu Cavaillon exclu- DEF de 08h00 :  Etendue S9 : V1 de la PATC Km 4,283 (AFT) au C1 Km 32,188 / V2 de la PATC km 32,167 (CAV) au C88 Km 3,645  Domaine ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687026661",null,"< >","Avignon-Fontcouverte - Chantier TAC","Cavaillon - Bât Voyageurs",2024,2024,50,50,"2023-12-11","13:03:00","2024-12-13","14:33:00","Periodical",null,"2024_SE_15 : vibration de +13mn pour avoir TER 879632 en SO  2021_SE_113 : décalage de quelques minutes pour avoir 879636 en SO et 879671 en SF et FEN21_Avignon-Cavaillon_002 à avancer pour avoir 879636 en SO pour aligner les surveillances sur l'axe  Déca",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687036061",null,"< >","Avignon-Fontcouverte - Fais Réc Impair","Cavaillon - Bât Voyageurs",2024,2024,9,11,"2024-02-26","09:17:00","2024-03-15","14:47:00","Periodical",null,"RPU Maintenance Voie BML VC avec B1N+Régaleuse : Format Générique + 1h30= 09h10 /14h40 soit 05h30  Domaine S9 : DFV L CAV-AFT V1+ V2 Domaine S11 : néant TO : 50541/879650 TF :",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13687027461",null,"< >","Avignon-Fontcouverte - Fais Réc Impair","Cavaillon - Bât Voyageurs",2024,2024,50,50,"2023-12-11","11:00:00","2024-12-13","11:30:00","Periodical",null,"SA2023/Main Courante PCO_SE/demande n°75 : vibration <10mn pour passage 879688 (SO 879622/SF 879688)  Décalage mineure MC17-0060 pour 879608 ouvrant et 879610  Main courante MAJ 224 pour train 879660 le 14/10/15  2021_SE_56 : décalage de +01h pour avoir 8",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13836831161",null,"< >","Avignon-Fontcouverte - Fais Récep Pair","Cavaillon - Bât Voyageurs",2024,2024,48,50,"2024-11-25","08:25:00","2024-12-13","16:55:00","Periodical",null,"Tvx PPx V1+V2 (de S48+49+50 SA2024 et 51 de 2024 sur SA2025) -Avignon Fontcouverte inclus à Miramas exclu-, à prendre avec 4C_AV_068+4C_CVN_010 :    Etendue S9 : V1 du Km 0+730 (Cv105 d'AFT) au Km 66+880 (C507 de Mas) et V2 au Km 65+976 (PATC de Mas) au K",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13687110261",null,"< >","Villeneuve-lès-Avignon - Rac Nord","Villeneuve-lès-Avignon - Rac Nord",2024,2024,18,18,"2024-04-29","09:57:00","2024-05-03","14:49:00","Periodical",null,"Lot Avi RVLA/VLA, Fenêtre capacitaire voie 1 et 2 de Villeneuve les Avignon à Avignon pour Révision Périodique (VTE+RFC) de 4h52 V2, (Semaine 18, à rendre avec 4C_VAV_001).  Etendue de la plage: du C412 et PATC 748+886 (coté Nimes) vers C171 ( voie1 et 2 ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13687017861",null,"< >","Villeneuve-lès-Avignon - Bif de Nîmes","Villeneuve-lès-Avignon - Rac Nord",2024,2024,18,18,"2024-04-29","09:57:00","2024-05-03","14:49:00","Periodical",null,"Lot AVI RVLA+VLA, VTE+RFC AVI, à prendre avec 4C_AV_003 :  Etendue S9 : VLA 1 => Rac Sud V2 du Ji Z350/414 km 2,845 à la Pte Aig 407 Km 2,125 + Racc VLA1 du Ji 412/410b Km 2,850 au C406 Km 0,203 (V2 RAC)/0,0028(Rac Sud V2) jusqu'au Rac sud V2 C 406 Km 0,2",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14657670361",null,"< >","Poste 14 Vaumort","Pasilly - Km 160,2",2024,2024,14,15,"2024-04-07","23:55:00","2024-04-14","04:50:00","Periodical",null,"CHA23_0024712, zone st florentin vergigny, postes 15 et 16   Train ouvrant 6442  ",null,"Medium","6,7","Planned"]
["SNCF-R","13688331461",null,"< >","Poste 14 Vaumort","Pasilly - Km 160,2",2024,2024,14,37,"2024-04-06","23:30:00","2024-09-14","04:50:00","Periodical",null,"CHA23_0024712, zone st florentin vergigny, postes 15 et 16   Train ouvrant 9784   ",null,"Medium","6","Planned"]
["SNCF-R","14340811761",null,"< >","Aubagne - Jonction 3","ITE Camp-Militaire-Carpiagne",2024,2024,3,37,"2024-01-20","23:59:00","2024-09-14","04:40:00","Periodical",null,"CHA20_0018098 \"\"Augmentation débit LGV\"\" : OCP 4h41,  1 nuit du Sa/Di de S3 (20-21/01/24) + 1 nuit du Sa/Di de S25 ( 22-23/06/24 de 23h59 à 04h40 opérations sur l´IHM1 Mistral au P1 de Marseille) et 1 nuit du Sa/Di de S37 pour essai complet de montée en c",null,"Medium","6","Planned"]
["SNCF-R","14845641261",null,"< >","Aubagne - Jonction 3","ITE Camp-Militaire-Carpiagne",2024,2024,43,45,"2024-10-21","23:30:00","2024-11-08","04:55:00","Periodical",null,"Meuleur SA2024, S43, AUB V1+V2+Générique AUB-TLN",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14340560461",null,"< >","Aubagne - Jonction 3","ITE Camp-Militaire-Carpiagne",2024,2024,45,45,"2024-11-10","22:35:00","2024-11-10","05:35:00","Periodical",null,"CHA24_0026458, OCP 7h00, 1 nuit du Di/Lu 10-11/11/24 (de 22h35 à 05h35), mise en service \"\"LGV +\"\" sur l'interface de la zone télécommandée de l'IHM1 de Mistral P1 de Marseille)  Conditions de réalisation : toute la zone d'action du poste de l'IHM1 de Mar",null,"Medium","7","Planned"]
["SNCF-R","15224291261",null,"< >","Aubagne - Jonction 3","ITE Camp-Militaire-Carpiagne",2024,2024,35,50,"2024-09-01","22:50:00","2024-12-12","05:35:00","Periodical",null,"Portiques souples Aubagne, reprise travaux sur SA2024 :   Domaine S9 :  V.D : zep 3617+3619+3621  V.1/VC : zep 3601+3603+3605+3607+3609+3611+3613+3615  MV2/VB : zep 3600+3602+3604+3606+3608+3610+3612+3614  MV3/VA : zep 3616+3618+3620+3622+3624+3626  VE : ",null,"Major","1,2,3,4,7","Planned"]
["SNCF-R","15446184461",null,"< >","Aubagne - Jonction 3","ITE Camp-Militaire-Carpiagne",2024,2024,41,41,"2024-10-12","00:01:00","2024-10-12","12:01:00","Periodical",null,"OCP 12h, sur S41 (sur le même We que le CHA24_0026522 Aqueducs Km 26,242) :  Portiques souples Aubagne, reprise travaux sur SA2024 à l'ombre de l'OCP 28h du CHA24_0026522) :   Domaine S9 :  V.D : zep 3617+3619+3621  V.1/VC : zep 3601+3603+3605+3607+3609+3",null,"Medium","6","Planned"]
["SNCF-R","13686996261",null,"< >","Miramas - Bif Km 811,8","Lavalduc - Bif Km823,3 V2B",2024,2024,50,50,"2023-12-11","10:13:00","2024-12-13","11:03:00","Periodical",null,"2024_SE_12 : vibration de +8' pour avoir TER 879716 en SO  2021_SE_54 : décalage de +35mn pour avoir 879716 en SO, aligné V2 de l'Estaque à Miramas, le 19/11/2019  MC19-0022 pour caler la plage entre 879716 et 879720  Modification le 05/02/2019 : inversio",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14484261261",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,19,33,"2024-05-10","23:25:00","2024-08-16","04:45:00","Periodical",null,"",null,"Medium","1,3,4,5","Planned"]
["SNCF-R","14483605961",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,25,25,"2024-06-21","21:30:00","2024-06-23","12:00:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","14713557161",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,49,49,"2024-12-04","00:35:00","2024-12-04","04:35:00","Periodical",null,"",null,"Medium","3","Planned"]
["SNCF-R","14713837161",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,13,13,"2024-03-29","23:20:00","2024-03-29","04:40:00","Periodical",null,"ZEP38117+38124",null,"Medium","5","Planned"]
["SNCF-R","14119230261",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,44,49,"2024-10-28","22:55:00","2024-12-06","05:20:00","Periodical",null,"ZEP38117+38124",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14119239461",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,46,48,"2024-11-11","21:30:00","2024-11-27","05:30:00","Periodical",null,"ZEP38117+38124",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14471018661",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,38,38,"2024-09-16","23:35:00","2024-09-20","04:35:00","Periodical",null,"ZEP425+443",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14471328561",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,39,41,"2024-09-23","22:00:00","2024-10-11","05:00:00","Periodical",null,"ZEP423+425+427+443",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14471413861",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,39,41,"2024-09-23","23:35:00","2024-10-12","04:35:00","continuous",null,"ZEP443",null,"High",null,"Planned"]
["SNCF-R","14509562861",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,8,8,"2024-02-19","23:35:00","2024-02-19","04:35:00","Periodical",null,"ZEP443+449",null,"Medium","1","Planned"]
["SNCF-R","15102547461",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,12,12,"2024-03-21","21:15:00","2024-03-21","23:00:00","Periodical",null,"ZEP441",null,"Medium","4","Planned"]
["SNCF-R","14657724161",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,11,11,"2024-03-13","21:15:00","2024-03-13","05:00:00","Periodical",null,"ZEP441",null,"Medium","3","Planned"]
["SNCF-R","15102549761",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,12,12,"2024-03-21","23:40:00","2024-03-21","04:50:00","Periodical",null,"ZEP441",null,"Medium","4","Planned"]
["SNCF-R","15102552261",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,12,12,"2024-03-22","23:50:00","2024-03-22","05:00:00","Periodical",null,"ZEP441",null,"Medium","5","Planned"]
["SNCF-R","15102556261",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,12,12,"2024-03-22","21:00:00","2024-03-22","05:10:00","Periodical",null,"ZEP443",null,"Medium","5","Planned"]
["SNCF-R","14657832461",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,11,11,"2024-03-14","21:00:00","2024-03-14","05:15:00","Periodical",null,"ZEP443",null,"Medium","4","Planned"]
["SNCF-R","14713724861",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,49,49,"2024-12-05","00:35:00","2024-12-06","04:35:00","Periodical",null,"",null,"Medium","4,5","Planned"]
["SNCF-R","13673354461",null,"< >","Chézy-sur-Marne","Mézy - Poste U",2024,2024,42,43,"2024-10-18","23:00:00","2024-10-25","04:40:00","Periodical",null,"ZEP de type G 201 + 202 + 203 + 204 + 205 + 207 + 209 + 210 + 211 + 212 + 213 + 214 + 216 + 222 + 224 + 226 + 301 + 309 + 311 + 313 + 315 + 317 Château Thierry   ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2024-07-16","22:15:00","2024-07-25","05:09:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2023-12-11","22:15:00","2023-12-15","05:09:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2023-12-11","22:15:00","2024-06-14","05:09:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15088750061",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,22,22,"2024-05-31","23:42:00","2024-06-02","16:05:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","14766708361",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,4,4,"2024-01-26","21:25:00","2024-01-28","10:40:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","14762533061",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,4,4,"2024-01-26","23:42:00","2024-01-28","12:30:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","15295774761",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,23,23,"2024-06-06","12:25:00","2024-06-07","14:05:00","Periodical",null,"Pour enrobés V2 entre 839410 et 839508",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15088752461",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,22,22,"2024-05-31","21:25:00","2024-06-02","15:35:00","Periodical",null,"",null,"Medium","5,6,7","Planned"]
["SNCF-R","15295736661",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,23,23,"2024-06-06","10:45:00","2024-06-07","12:25:00","Periodical",null,"Pour enrobés V1 entre 839403 et 839584/5",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14670005261",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,14,38,"2024-04-02","22:15:00","2024-09-20","04:45:00","Periodical",null,"Aménagement aires de mise en voie / Pose auvents Marnay, Pont sur Seine, Romilly, Barberey  La ZEP 603 est inclue dans le domaine intercepté",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14670147761",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,14,38,"2024-04-02","21:30:00","2024-09-20","04:55:00","Periodical",null,"Aménagement aires de mise en voie / Pose de auvents Marnay, Pont sur Seine, Romilly, Troyes Barberey  ZEP 606 inclue dans le domaine intercepté",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2024-02-19","22:15:00","2024-11-15","05:09:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2023-12-18","22:15:00","2024-01-12","05:09:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2024-08-19","22:15:00","2024-10-18","05:09:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15298773061",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,37,41,"2024-09-13","23:45:00","2024-10-13","16:05:00","Periodical",null,"",null,"High","5,6,7","Planned"]
["SNCF-R","15298807361",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,37,41,"2024-09-13","21:25:00","2024-10-13","15:35:00","Periodical",null,"",null,"High","5,6,7","Planned"]
["SNCF-R","14550032461",null,"< >","Woippy - Accès Nord","Hagondange - Poste 3",2024,2024,8,8,"2024-02-24","22:30:00","2024-02-25","05:30:00","Periodical",null,"Déf 11822, 7h nuits SaDi+DiLu, V1+V2 entre Woippy AN et Hagondange  (zep type L entre WPY et HGD). Avec 4D_WPY-MMZ_007 qui reprend les conséquences circulations.",null,"Medium","6,7","Planned"]
["SNCF-R","14867464261",null,"< >","Claveyson-Bren","Poste 52 Upie",2024,2024,6,37,"2024-02-10","23:10:00","2024-09-14","05:55:00","Periodical",null,"Plage créée pour le CHA20_0018098, essai de poste à poste avec l'infrapôle Alpes le SA/DI  Toute la zone du poste 51 d'Alixan TGV est concernée  Plage sans impact pour les circulations.",null,"Medium","6","Planned"]
["SNCF-R","14867374861",null,"< >","Claveyson-Bren","Poste 52 Upie",2024,2024,6,7,"2024-02-09","23:55:00","2024-02-16","05:30:00","Periodical",null,"Plage créée pour le CHA20_0018098, essai de poste à poste avec l'infrapôle Alpes le VE/SA  Toute la zone du poste 51 d'Alixan TGV est concernée  Plage sans impact pour les circulations.",null,"Medium","5","Planned"]
["SNCF-R","14867534561",null,"< >","Claveyson-Bren","Poste 52 Upie",2024,2024,6,7,"2024-02-11","23:55:00","2024-02-18","05:35:00","Periodical",null,"Plage créée pour le CHA20_0018098, essai de poste à poste avec l'infrapôle Alpes le DI/LU  Toute la zone du poste 51 d'Alixan TGV est concernée  Plage sans impact pour les circulations.",null,"Medium","7","Planned"]
["SNCF-R","13688214061",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,50,"2023-12-15","23:47:00","2024-12-13","06:18:00","Periodical",null,"5h20 de sim. partielle déduite. Pour SA2018 => VE/SA + jours typés VE : + ME 9/05 + ME 31/10  derrière le 5137 en DI     ",null,"Major","3,5","Planned"]
["SNCF-R","13688212461",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,50,"2023-12-15","23:12:00","2024-12-13","04:48:00","Periodical",null,"Modification main courante majeure MC565 SA2018 => + ME 9/05 + ME 31/10              ",null,"Major","3,5","Planned"]
["SNCF-R","13688218061",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,49,"2023-12-16","23:00:00","2024-12-07","05:55:00","Periodical",null,"ouvrant 6131, fermant 999603 ",null,"Major","6","Planned"]
["SNCF-R","13688219061",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,49,49,"2023-12-10","23:50:00","2024-12-08","05:55:00","Periodical",null,"ouvrant 6137, fermant 999600  ",null,"Major","7","Planned"]
["SNCF-R","14886336461",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00","Periodical",null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00",null,"Medium","1,2,3,5,6,7","Planned"]
["SNCF-R","13688215661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,50,"2023-12-11","22:36:00","2024-12-09","06:19:00","Periodical",null,"6h25 de sim. partielle déduite. Pour SA2018 => LU/MA + jours typés LU : MA/ME 26-27/12, MA/ME 02-03/01, MA/ME 03-04/04, ME/JE 02-03/05, MA/ME 22-23/05     ",null,"Major","1,2,3","Planned"]
["SNCF-R","13688211661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,50,"2023-12-12","22:24:00","2024-12-12","06:18:00","Periodical",null,"6h36 de sim. partielle déduite. Sauf jours particulier TGV typé LU VE SA2018 => SF ME 9/05, ME 31/10 MA/ME 26-27/12, MA/ME 02-03/01, MA/ME 03-04/04, ME/JE 02-03/05, MA/ME 22-23/05   ",null,"Major","2,3,4","Planned"]
["SNCF-R","13688216461",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,52,46,"2023-12-25","23:50:00","2024-11-11","05:50:00","Periodical",null,"Variante Gen pour VF,F et LDF         ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688210861",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,50,"2023-12-11","22:00:00","2024-12-12","04:50:00","Periodical",null,"6h32 de sim. partielle déduite. Sauf jours typés VE sur le calendrier TGV SA2018 => SF ME 9/05 + ME 31/10         ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688217261",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,52,46,"2023-12-25","23:05:00","2024-11-11","06:00:00","Periodical",null,"Variante Gen pour VF,F et LDF         ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13703631461",null,"< >","Enghien-les-Bains","Ermont-Eaubonne - Poste 1",2024,2024,50,36,"2024-07-09","01:05:00","2024-08-04","05:25:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13703631461",null,"< >","Enghien-les-Bains","Ermont-Eaubonne - Poste 1",2024,2024,50,36,"2023-12-11","01:05:00","2024-09-08","05:25:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","14329314461",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Poste 1",2024,2024,38,39,"2024-09-20","23:35:00","2024-09-27","04:30:00","Periodical",null,"",null,"Medium","5","Planned"]
["SNCF-R","14869528861",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Poste 1",2024,2024,38,40,"2024-09-22","01:30:00","2024-09-30","04:30:00","Periodical",null,"",null,"Medium","1,7","Planned"]
["SNCF-R","13688339061",null,"< >","Poste 56 Lapalud - Rac d'Avignon","Poste 61 Roquemaure",2024,2024,50,50,"2023-12-11","15:33:00","2024-12-13","16:42:00","Periodical",null,"10701436",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688338261",null,"< >","Poste 56 Lapalud - Rac d'Avignon","Poste 61 Roquemaure",2024,2024,50,50,"2023-12-11","11:23:00","2024-12-13","12:15:00","Periodical",null,"10701439 2021_SE_48 : décalage de -5mn pour avoir 9710 en SF, le 19/11/2019",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14376128961",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Poste B",2024,2024,50,28,"2023-12-11","22:45:00","2024-07-12","05:47:00","Periodical",null,"PAZ(CLR) Jiz 273/285  à  JUVISY C203",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14375958861",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,28,"2023-12-11","23:18:00","2024-07-12","05:35:00","Periodical",null,"CHOISY LE ROI JIZ 241/245  à  JUVISY C205 16,590",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14719451261",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,3,42,"2024-01-19","23:18:00","2024-10-14","05:30:00","Periodical",null,"",null,"Major","1,5,6,7","Planned"]
["SNCF-R","14719469761",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,21,41,"2024-05-25","09:50:00","2024-10-13","14:52:00","Periodical",null,"",null,"Medium","6,7","Planned"]
["SNCF-R","14719484861",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,21,41,"2024-05-26","23:20:00","2024-10-13","05:15:00","Periodical",null,"",null,"Medium","7","Planned"]
["SNCF-R","15133680161",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,18,44,"2024-04-30","23:20:00","2024-10-31","05:10:00","Periodical",null,"CHOISY LE ROI JIZ 241/245  à  JUVISY C205 16,590",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15535469261",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,9,11,"2024-03-02","00:00:00","2024-03-11","05:30:00","Periodical",null,"PAZ(CLR) C725 à  JUVISY C203",null,"Medium","1,6,7","Planned"]
["SNCF-R","16273658561",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,3,7,"2024-01-19","23:25:00","2024-02-18","05:30:00","Periodical",null,"",null,"High","5,7","Planned"]
["SNCF-R","16273788261",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,3,7,"2024-01-21","00:40:00","2024-02-18","05:00:00","Periodical",null,"PAZ(CLR) C725 à  JUVISY C203",null,"Medium","7","Planned"]
["SNCF-R","13575965561",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2023-12-11","01:05:00","2024-12-09","05:05:00","Periodical",null,"",null,"Major","1","Planned"]
["SNCF-R","13575967161",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2023-12-11","00:25:00","2024-12-09","04:25:00","Periodical",null,"",null,"Major","1","Planned"]
["SNCF-R","13575971961",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2023-12-11","23:23:00","2024-12-13","05:29:00","Periodical",null,"6h par voie V1 et V2 avec min 3h10 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy)               ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14651543761",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2023-12-11","23:15:00","2024-12-13","05:10:00","Periodical",null,"",null,"Major","1,2,3,4,5,6","Planned"]
["SNCF-R","13575970361",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,51,37,"2023-12-19","01:00:00","2024-09-11","05:10:00","Periodical",null,"6h par voie V1 et V2 dont min 3h10 de sim 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy)                   ",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13575971961",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2024-04-22","23:23:00","2024-04-30","05:29:00","Periodical",null,"6h par voie V1 et V2 avec min 3h10 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy)               ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14651543761",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2024-04-25","23:15:00","2024-04-30","05:10:00","Periodical",null,"",null,"Major","1,2,3,4,5,6","Planned"]
["SNCF-R","15289086361",null,"< >","Villeneuve-St-Georges-Triage - FSC Débranche","Villeneuve-St-Georges-Triage - Poste 2",2024,2024,20,21,"2024-05-13","10:00:00","2024-05-24","14:00:00","Periodical",null,"ZEP 459+462 de VTRP2",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15230590561",null,"< >","Villeneuve-St-Georges - Bât Voyageurs","Villeneuve-St-Georges - Point X",2024,2024,7,7,"2024-02-17","21:55:00","2024-02-17","04:40:00","Periodical",null,"",null,"Medium","6","Planned"]
["SNCF-R","13690650761",null,"< >","Lieusaint-Moissy - ITE EPAMS","Melun - Poste 1",2024,2024,14,49,"2024-05-06","23:35:00","2024-05-10","05:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689805061",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 1",2024,2024,12,42,"2024-09-09","10:00:00","2024-10-18","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689805061",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 1",2024,2024,12,42,"2024-03-18","10:00:00","2024-03-22","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689801061",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,50,44,"2023-12-11","00:37:00","2024-11-03","03:20:00","Periodical",null,"2V/4 => 1 voie dans chaque sens Modification le 05/02/2019 : Typologie passée de Jour à Nuit non passe-minuit ",null,"High","1","Planned"]
["SNCF-R","13689810861",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,5,42,"2024-01-29","09:45:00","2024-10-20","15:45:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689796261",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,52,30,"2023-12-26","08:51:00","2024-07-28","14:51:00","Periodical",null,"Prise de voie V2   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689808461",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,19,48,"2024-05-12","22:00:00","2024-11-29","04:00:00","Periodical",null,"",null,"High","1,2,3,4,5,7","Planned"]
["SNCF-R","15202008861",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,38,45,"2024-09-21","07:00:00","2024-11-04","04:00:00","Periodical",null,"",null,"High","1,6,7","Planned"]
["SNCF-R","15652915361",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,34,50,"2024-08-19","00:50:00","2024-12-09","04:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","13689810861",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,5,42,"2024-09-09","09:45:00","2024-10-18","15:45:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15652335461",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,46,46,"2024-11-11","00:50:00","2024-11-11","04:00:00","Periodical",null,"",null,"Medium","1","Planned"]
["SNCF-R","13689810861",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,5,42,"2024-01-29","09:45:00","2024-10-18","15:45:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689796261",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,52,30,"2024-01-22","08:51:00","2024-02-23","14:51:00","Periodical",null,"Prise de voie V2   ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689808461",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,19,48,"2024-09-16","22:00:00","2024-09-19","04:00:00","Periodical",null,"",null,"High","1,2,3,4,5,7","Planned"]
["SNCF-R","15202008861",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,38,45,"2024-09-21","07:00:00","2024-10-21","04:00:00","Periodical",null,"",null,"High","1,6,7","Planned"]
["SNCF-R","15652558361",null,"< >","Laroche-Migennes - Poste 1","Laroche-Migennes - Poste 2",2024,2024,40,42,"2024-10-03","10:00:00","2024-10-14","04:00:00","Periodical",null,"",null,"High","1,4,5,6,7","Planned"]
["SNCF-R","13689851461",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 2",2024,2024,5,42,"2024-03-18","10:00:00","2024-03-22","13:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689851461",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 2",2024,2024,5,42,"2024-01-29","10:00:00","2024-03-31","13:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689851461",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 2",2024,2024,5,42,"2024-09-09","10:00:00","2024-10-18","13:35:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15202283661",null,"< >","Laroche-Migennes - BÃ¢t Voyageurs","Laroche-Migennes - Poste 4",2024,2024,37,42,"2024-09-09","10:00:00","2024-10-18","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689848861",null,"< >","Laroche-Migennes - CarrÃ© Violet 12","Laroche-Migennes - Poste 4",2024,2024,17,17,"2024-04-22","09:30:00","2024-04-28","15:30:00","Periodical",null,"Besoins Caténaires : - Secteur Laroche Voie de service Pair - Secteur Laroche Cezy voie 2bis - Sel 2320 bis du Secteur Laroche St Florentin Voie 2bis (Voie 2 Racco) - Sel 2321bis +131 du Secteur  Laroche St Florentin Voie 1bis (Voie 1 Racco + Voie A Racco",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15652718461",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-16","10:00:00","2024-11-08","18:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15652473261",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,37,42,"2024-09-09","08:45:00","2024-10-18","14:00:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15202029761",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-21","07:00:00","2024-11-04","04:00:00","Periodical",null,"",null,"High","1,6,7","Planned"]
["SNCF-R","15201913561",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-16","10:00:00","2024-11-08","18:00:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15201830661",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,37,42,"2024-09-09","09:45:00","2024-10-18","15:45:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","15654108661",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,34,50,"2024-08-19","00:50:00","2024-12-09","04:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","15202297561",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,33,46,"2024-08-12","00:50:00","2024-11-11","04:00:00","Periodical",null,"",null,"Medium","1","Planned"]
["SNCF-R","15645809461",null,"< >","Laroche-Migennes - Poste 1","Laroche-Migennes - Poste 4",2024,2024,37,42,"2024-09-09","08:45:00","2024-10-18","13:35:00","Periodical",null,"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13689849661",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,16,16,"2024-04-15","09:30:00","2024-04-21","15:30:00","Periodical",null,"Besoins Caténaires : - Secteur Laroche Voie de service Impair - Secteur Cezy Laroche voie 1bis Besoins ZEP : - Toutes les ZEP du faisceau Bourgogne Impair et Accès  - Toutes les ZEP du faisceau de Préblin + ZEP 481 et Accès par bourgogne faisceau impair  ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","15202016261",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-21","07:00:00","2024-11-04","04:00:00","Periodical",null,"",null,"High","1,6,7","Planned"]
["SNCF-R","15201727861",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,33,49,"2024-08-12","10:00:00","2024-12-08","16:31:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15652676761",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-16","10:00:00","2024-11-08","16:31:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15654038861",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,34,50,"2024-08-19","00:50:00","2024-12-09","04:00:00","Periodical",null,"",null,"High","1","Planned"]
["SNCF-R","15201987861",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-21","01:00:00","2024-11-04","04:00:00","Periodical",null,"",null,"High","1,6,7","Planned"]
["SNCF-R","15201892561",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,33,49,"2024-08-12","10:00:00","2024-12-08","11:50:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","15652892461",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,33,49,"2024-08-18","22:00:00","2024-12-08","04:00:00","Periodical",null,"",null,"High","7","Planned"]
["SNCF-R","15652809261",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,46,46,"2024-11-11","00:50:00","2024-11-11","04:00:00","Periodical",null,"",null,"Medium","1","Planned"]
["SNCF-R","14437994361",null,"< >","Marquixanes","St-Antoine (M) Poste 1",2024,2024,38,50,"2024-09-22","23:20:00","2024-12-12","05:30:00","Periodical",null,"Confortement mur +OT des Cuettes :   Etendue S9 : V1 du C104 (Cassis) Km 26,744 au C201(SNA) Km 39,820 / V2 du C102 Km 26,787 au C203 (SNA) Km 39,820  Domaine S9 : ZEP 31 / ZEP 32  Etendue S11 : V1 du Km 28,849 au Km 40,110 /V2 du Km au Km 40,110  Domaine",null,"Major","1,2,3,4,7","Planned"]
["SNCF-R","14551847761",null,"< >","Miramas - Bât Voyageurs","Rognac - Poste A",2024,2024,12,12,"2024-03-20","00:10:00","2024-03-23","05:10:00","Periodical",null,"SA2024, Tir823/08  : DEF V1+V2 de MAS à RGC de 05h00  Etendue S9 : V1 du C653 Km 810,004 de Mas au C1 Km 834,933 de Rognac+ V2 depuis PATC de RGC Km 834,175 au C 651 Km 810,004 de Mas  Domaine S9 : V1 ZEP G Mas 99 + Les Roques ZEP G 801+821+841 + Berre ZE",null,"Medium","3,4,5,6","Planned"]
["SNCF-R","14472067061",null,"< >","Fos-Coussoul - Poste 1","Fos-Viguerat - Poste 1",2024,2024,10,49,"2024-04-29","22:40:00","2024-05-05","04:10:00","Periodical",null,"SA2024, Epurations, UP Voie Avignon :  Domaine S9 : ZEP L FOS-VIG V1 (étendue V1 PATC de FOC Km 6,015 au C303 Viguerat au Km 11,215) + ZEP L VIG-FOC V2 (étendue Du C8 Km 4,945 à la PATC de VIG Km 10,379) Domaine S11 : sans  ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14472067061",null,"< >","Fos-Coussoul - Poste 1","Fos-Viguerat - Poste 1",2024,2024,10,49,"2024-03-04","22:40:00","2024-12-06","04:10:00","Periodical",null,"SA2024, Epurations, UP Voie Avignon :  Domaine S9 : ZEP L FOS-VIG V1 (étendue V1 PATC de FOC Km 6,015 au C303 Viguerat au Km 11,215) + ZEP L VIG-FOC V2 (étendue Du C8 Km 4,945 à la PATC de VIG Km 10,379) Domaine S11 : sans  ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688228661",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,50,50,"2023-12-11","22:50:00","2024-12-12","05:28:00","Periodical",null,"derrière le 6672 le VE/SA",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688233661",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,52,46,"2023-12-25","23:25:00","2024-11-11","05:10:00","Periodical",null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022 ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688231861",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,50,50,"2023-12-11","23:05:00","2024-12-12","05:28:00","Periodical",null,"derrière 9847 SA2018 => SF  ME 9/05 + ME 31/10       ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","14886193561",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00","Periodical",null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00           ",null,"Medium","1,2,3,5,6,7","Planned"]
["SNCF-R","13688228661",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,50,50,"2023-12-15","22:50:00","2024-12-13","05:28:00","Periodical",null,"derrière le 6672 le VE/SA",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688231061",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,50,50,"2023-12-15","23:35:00","2024-12-13","05:42:00","Periodical",null,"Derrière le 6635 SA2018 => + ME 9/05 + ME 31/10",null,"Major","3,5","Planned"]
["SNCF-R","13688237261",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,49,49,"2023-12-10","23:45:00","2024-12-08","05:10:00","Periodical",null,"fenêtre applicable di/lu train ouvrant 6635, train fermant 999614     ",null,"Major","7","Planned"]
["SNCF-R","14995596061",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,6,25,"2024-02-09","23:55:00","2024-06-21","05:15:00","Periodical",null,"Plage pour le CHA20-0018098, essais avec l'infrapôle Rhodanien  Toutes les ZEP des postes 27 et 40  TO 6635, TF 999614            ",null,"Medium","5","Planned"]
["SNCF-R","13688236261",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,50,49,"2023-12-16","23:30:00","2024-12-07","05:20:00","Periodical",null,"fenêtre applicable sa/di train ouvrant 9847 , train fermant 999614     ",null,"Major","6","Planned"]
["SNCF-R","14995298761",null,"< >","Poste 27 Cesseins","Miribel-LGV",2024,2024,3,13,"2024-01-19","23:55:00","2024-03-29","05:20:00","Periodical",null,"Plage pour le CHA20-0018098, essais avec l'infrapôle Rhodanien  Toutes les ZEP du poste 40  TO 6635, TF 999614            ",null,"High","5","Planned"]
["SNCF-R","14995157061",null,"< >","Poste 27 Cesseins","Miribel-LGV",2024,2024,3,13,"2024-01-15","23:30:00","2024-03-28","05:20:00","Periodical",null,"Plage pour le CHA20-0018098, essais avec l'infrapôle Rhodanien  Toutes les ZEP du poste 40  TO 9847, TF 999614            ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688220861",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-09-02","21:05:00","2024-10-24","06:15:00","Periodical",null,"Notion V1 ou V2 en grand, cas V2 en grand lu/ma à je/ve, la prise de cette DEF rend applicable DEF24_GNA-VXN_007 lu/ma ou DEF24_GNA-VXN_008 ma/me à je/ve sur V1  V2 derrière 6260 jusqu'au 999600 +10   Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688221661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-09-02","22:45:00","2024-10-21","06:15:00","Periodical",null,"Notion V1 ou V2 en grand lu/ma et jours en lu/ma  (en raison du 6131 circulant dans sa variante du lundi)  CHA24_0026280:   Cas V2 sim lu/ma lorsque DEF24_GNA-VXN_005 est prise sur V1  Cas V1 sim lu/ma lorsque DEF24_GNA-VXN_006 est prise sur V2  CHA24_002",null,"Major","1,2","Planned"]
["SNCF-R","13688222661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-09-03","22:35:00","2024-10-24","06:15:00","Periodical",null,"Notion V1 ou V2 en grand ma/me à je/ve  CHA24_0026280:   Cas V2 sim ma/me à je/ve lorsque DEF24_GNA-VXN_005 est prise sur V1  Cas V1 sim ma/me à je/ve lorsque DEF24_GNA-VXN_006 est prise sur V2  CHA24_0026378:   Cas V2 sim ma/me à je/ve lorsque DEF24_GNA-",null,"Major","2,3,4","Planned"]
["SNCF-R","14976483561",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,36,43,"2024-09-02","21:20:00","2024-10-24","06:20:00","Periodical",null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_GNA-VXN_007 lu/ma ou DEF24_GNA_VXN_008 du ma/me à je/ve  sur V2   V1 derrière 6225  jusqu'au 999603 + 25 minutes  Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571 + 745 + 4771 + ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688223661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,26,"2024-01-12","21:50:00","2024-06-28","06:20:00","Periodical",null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_GNA-VXN_011 le ve/sa  sur V2   V1 derrière 6129 et 6953  jusqu'au 999603 + 25 minutes  Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571 + 745 + 4771 + 747    Consignation C: Sr G",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688224461",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,26,"2024-01-12","22:05:00","2024-06-28","06:15:00","Periodical",null,"Notion V1 ou V2 en grand, cas V2 en grand rend applicable DEF24_GNA-VXN_011 le ve/sa sur V1   V2 derrière 6206 jusqu'au 999600 + 10     Zeps V2: 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 + 4472 + 4474 + 843   Consignation C: Sr Grenay DV2 + SEL 1002 Sr ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688225261",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,26,"2024-01-12","23:50:00","2024-06-28","06:15:00","Periodical",null,"Notion V1 ou V2 en grand le ve/sa   Cas V2 sim ve/sa lorsque DEF24_GNA-VXN_009 est prise sur V1   Cas V1 sim ve/sa lorsque DEF24_GNA-VXN_010 est prise sur V2  Derrière 6137  jusqu'au  999603 + 25 minutes ou 999600 + 10   Zeps V1:  743 + 4471 + 4473 + 4475",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688226261",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,14,21,"2024-04-01","22:45:00","2024-05-20","06:20:00","Periodical",null,"Notion V1 ou V2 en grand, cas voie 1 en Grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05, rend applicable en sim DEF24_GNA-VXN_014    V1 derrière 6131  jusqu'au 999603 + 25  Zeps V1 : 743 + 4471 + 4473 + 4475 + ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14409893561",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,14,21,"2024-04-01","23:50:00","2024-05-20","06:15:00","Periodical",null,"Notion V1 ou V2 en grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05   Cas V2 sim ve/sa lorsque DEF24_GNA-VXN_012 est prise sur V1   Cas V1 sim ve/sa lorsque DEF24_GNA-VXN_013 est prise sur V2  Derrière 6137  jus",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13688221661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-01-08","22:45:00","2024-06-24","06:15:00","Periodical",null,"Notion V1 ou V2 en grand lu/ma et jours en lu/ma  (en raison du 6131 circulant dans sa variante du lundi)  CHA24_0026280:   Cas V2 sim lu/ma lorsque DEF24_GNA-VXN_005 est prise sur V1  Cas V1 sim lu/ma lorsque DEF24_GNA-VXN_006 est prise sur V2  CHA24_002",null,"Major","1,2","Planned"]
["SNCF-R","13688220861",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-01-08","21:05:00","2024-06-27","06:15:00","Periodical",null,"Notion V1 ou V2 en grand, cas V2 en grand lu/ma à je/ve, la prise de cette DEF rend applicable DEF24_GNA-VXN_007 lu/ma ou DEF24_GNA-VXN_008 ma/me à je/ve sur V1  V2 derrière 6260 jusqu'au 999600 +10   Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688220061",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,26,"2024-01-08","20:55:00","2024-06-27","06:20:00","Periodical",null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_GNA-VXN_007 lu/ma ou DEF24_GNA_VXN_008 du ma/me à je/ve  sur V2   V1 derrière 6225 moins 25 minutes jusqu'au 999603 + 25 minutes  Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688227061",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,14,21,"2024-04-01","22:50:00","2024-05-20","06:15:00","Periodical",null,"Notion V1 ou V2 en grand, cas voie 2 en Grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05, rend applicable en sim DEF24_GNA-VXN_014   V2 derrière 6206 jusqu'au 999600 + 10    Zeps V2: 847 + 4772 + 4774 + 845 + 45",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13688222661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-01-09","22:35:00","2024-06-27","06:15:00","Periodical",null,"Notion V1 ou V2 en grand ma/me à je/ve  CHA24_0026280:   Cas V2 sim ma/me à je/ve lorsque DEF24_GNA-VXN_005 est prise sur V1  Cas V1 sim ma/me à je/ve lorsque DEF24_GNA-VXN_006 est prise sur V2  CHA24_0026378:   Cas V2 sim ma/me à je/ve lorsque DEF24_GNA-",null,"Major","2,3,4","Planned"]
["SNCF-R","13687480061",null,"< >","Avignon-Champfleury - Aig Km 743,9","Tarascon - Poste Km 759,1",2024,2024,50,50,"2023-12-11","14:00:00","2024-12-13","15:01:00","Periodical",null,"2024_SE_59 : décalage et réduction pour avoir TER 886569 en SO et TER 17709 en SF  2021_SE_47 : décalage de -10mn avec 879531 en SO et 879535 en SF, aligné V1 d'Avignon à St Louis, le 19/11/2019  Main courante MC20-0317 pour le passage du FBCE22, le 06/11",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687476661",null,"< >","Avignon-Champfleury - Aig Km 743,9","Tarascon - Poste Km 759,1",2024,2024,8,11,"2024-02-19","23:10:00","2024-03-15","05:04:00","Periodical",null,"Gen, V1, 1V/2, 5h54 Nuit en sim partielle, LU/MA->VE/SA (sim 2V/2 avec 1F_AF-TCN_002 / FEN21_Avignon-Tarascon_002) 2h en sim 5N/7 Modification le 11/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13687478261",null,"< >","Avignon-Champfleury - Aig Km 743,9","Tarascon - Poste Km 759,1",2024,2024,8,11,"2024-02-20","00:00:00","2024-03-16","02:00:00","Periodical",null,"",null,"High","2,3,4,5,6","Planned"]
["SNCF-R","14553555461",null,"< >","Avignon-Champfleury - Aig Km 743,9","Tarascon - Poste Km 759,1",2024,2024,13,13,"2024-03-25","23:15:00","2024-03-29","04:45:00","Periodical",null,"AVI Voie 1+1 Gare,VTE+RFC, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870, équivalent Gén, à prendre avec 4D_AV_082 et 2C_TCN_013 :  Etendue S9 : V1 Côté TCN, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870  Domaine S9 : ZEP G 705+703+701 Etendue",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14550034061",null,"< >","Avignon-Champfleury - Aig Km 743,9","Tarascon - Poste Km 759,1",2024,2024,17,17,"2024-04-22","23:15:00","2024-04-24","04:45:00","Periodical",null,"Tir 744/15A, SA2024, à prendre avec 4C_AV_080  :  Domaine S9 : V1 ZEP 701+703+705 / V2 ZEP 706+704+702 +DFL Avi/TCN V1+V2 (jusqu'au V1 C601/V2 603 Km 759,095)   Etendue S11 : V1 du Km 742,441 au Km 759,179 / V2 du Km 758,757 au Km 742,573  Domaine S11 : V",null,"Medium","1,2,3","Planned"]
["SNCF-R","13687479261",null,"< >","Avignon-Champfleury - Aig Km 744,5","Tarascon - Poste Km 759,1",2024,2024,50,50,"2023-12-11","10:23:00","2024-12-13","11:15:00","Periodical",null,"2024_SE_20 : vibration de +5mn pour avoir Fret PNBP07 en SO  2021_SE_125 : gros décalage pour TER 876416 tout en conservant l'alignement avec les surveillances V2 Avignon-Pierrelatte pour minimiser l'impact sur les flux fret (report de la contrainte sur T",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14586018461",null,"< >","Avignon-Champfleury - Aig Km 744,5","Tarascon - Poste Km 759,1",2024,2024,14,15,"2024-04-03","00:00:00","2024-04-13","02:00:00","Periodical",null,"VI Voie C Circ+V2Courtine+V1Courtine+HCourtine+A/B Courtine, VTE+RFC, du C154 Km 741,629 au C306 Km 744,730, à prendre avec 4C_AV_083+4C_AV_084 :  Etendue S9 : depuis V1Bis/2bis vers VC Circ. + VCirc du C154 Km 741,629 au C305 Km 743,974 (et du C305 Km 74",null,"High","2,3,4,5,6","Planned"]
["SNCF-R","14551529261",null,"< >","Avignon-Champfleury - Aig Km 744,5","Tarascon - Poste Km 759,1",2024,2024,15,15,"2024-04-08","23:15:00","2024-04-12","04:45:00","Periodical",null,"SA2024, Tir 714/16 + 752/11 (à prendre avec 4C_TCN_012+4D_TCN-MAS_037)  :  Etendue S9 : V1 du C 304 Km 744,730 (Avignon) à la PATC Km 767+009 (Tarascon) / V2 du C 306  Km 744,730 (Avignon) au C22 Km 766,134 (Tarascon)   Domaine S9 : V1 ZEP L Avi-TCN + ZEP",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14549525861",null,"< >","Avignon-Champfleury - Aig Km 744,5","Tarascon - Poste Km 759,1",2024,2024,16,16,"2024-04-17","23:15:00","2024-04-18","04:45:00","Periodical",null,"Tir 742/3077 (V2 à prendre avec 4C_AV_079+078) :  Domaine S9 : ZEP600+620+624+706+704+702+DFV L Avi/TCN V2 (Jusqu'au C603 Km 759,095)   Etendue S11 : du Km 758,757 au Km 742,573  Domaine S11 :  Sel 2112+2114 SR Champfleury/les Olivettes voie2",null,"Medium","3,4","Planned"]
["SNCF-R","14705167261",null,"< >","Poste 66 Crisenoy","Poste 11 Le ChÃ¢telet",2024,2024,16,40,"2024-04-15","00:00:00","2024-09-30","05:00:00","Periodical",null,"Pour  le CHA23-0024712 (PSE)   Zone du Poste 66 Crisenoy, TO 6928                             ",null,"Medium","1","Planned"]
["SNCF-R","14704969461",null,"< >","Poste 66 Crisenoy","Poste 11 Le ChÃ¢telet",2024,2024,15,39,"2024-04-12","23:55:00","2024-09-27","05:20:00","Periodical",null,"Pour  le CHA23-0024712 (PSE)   Zone du Poste 66 Crisenoy, TO 6676                             ",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14705160661",null,"< >","Poste 66 Crisenoy","Poste 11 Le ChÃ¢telet",2024,2024,15,39,"2024-04-13","23:45:00","2024-09-28","05:00:00","Periodical",null,"Pour  le CHA23-0024712 (PSE)   Zone du Poste 66 Crisenoy, TO 6442                             ",null,"Medium","6","Planned"]
["SNCF-R","13688436261",null,"< >","Poste 66 Crisenoy - Bif","Poste 14 Vaumort",2024,2024,2,3,"2024-01-12","23:50:00","2024-01-19","05:20:00","Periodical",null,"Pour  le CHA23-0024712 (PSE)   après 6672 jusqu'au 999611                              ",null,"Medium","5","Planned"]
["SNCF-R","13688437261",null,"< >","Poste 14 Vaumort","Poste 15 Vergigny",2024,2024,14,37,"2024-04-06","23:30:00","2024-09-14","04:50:00","Periodical",null,"CHA23_0024712, zone st florentin vergigny, postes 15 à 16    Train ouvrant le 9784",null,"Medium","6","Planned"]
["SNCF-R","14657634061",null,"< >","Poste 14 Vaumort","Poste 15 Vergigny",2024,2024,14,15,"2024-04-07","23:55:00","2024-04-14","04:50:00","Periodical",null,"CHA23_0024712, zone st florentin vergigny, postes 15 à 16    Train ouvrant le 6442",null,"Medium","5,6,7","Planned"]
["SNCF-R","13688403261",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2024-09-16","22:30:00","2024-09-19","05:33:00","Periodical",null,"5h10 de sim. partielle déduite. SA2018 => VE/SA non activé du début du service au 30/03 pour circulation de l'Eurostar 9097 => Variante plus courte FEN17 Crisnoy-Vergigny 005 s'applique       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688406461",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2024-09-16","23:37:00","2024-09-19","05:37:00","Periodical",null,"5h20 de sim. partielle déduite. SA2018 => SF ME 9/05, ME 31/10 Modification le 05/02/2019 : inversion Heure Début PK Début et Heure Début PK Fin, et Heure Fin PK Début et Heure Fin PK Fin   ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688424061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard  Train ouvrant  6144, train fermant  999611",null,"Medium","1","Planned"]
["SNCF-R","13688423061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00","Periodical",null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard  Train ouvrant le 6676 et  train fermant le 999611",null,"Medium","5","Planned"]
["SNCF-R","13688420061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00","Periodical",null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard  Train ouvrant  6144, train fermant  999611",null,"Medium","6","Planned"]
["SNCF-R","13688421061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00","Periodical",null,"                                 ",null,"Medium","1","Planned"]
["SNCF-R","13688416061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,2,49,"2024-09-28","23:30:00","2024-09-28","05:35:00","Periodical",null,"Pour le CHA20-0018098 LGV + et le CHA23-0024712 (PSE)  après 9784 jusqu'au 999611 +  15                             ",null,"Major","6","Planned"]
["SNCF-R","13688403261",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2024-04-12","22:30:00","2024-12-13","05:33:00","Periodical",null,"5h10 de sim. partielle déduite. SA2018 => VE/SA non activé du début du service au 30/03 pour circulation de l'Eurostar 9097 => Variante plus courte FEN17 Crisnoy-Vergigny 005 s'applique       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688407261",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,14,"2023-12-15","23:36:00","2024-04-05","05:54:00","Periodical",null,"5h10 de sim. partielle déduite. sim. partielle déduite. SA2018 => VE/SA activé du début du service au 30/03 pour circulation de l'Eurostar 9097/6                     ",null,"High","5","Planned"]
["SNCF-R","13688404061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2023-12-15","23:50:00","2024-12-13","05:37:00","Periodical",null,"TGV ouvrant 6672 ",null,"Major","5","Planned"]
["SNCF-R","13688416061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,2,49,"2024-04-13","23:30:00","2024-12-07","05:35:00","Periodical",null,"Pour le CHA20-0018098 LGV + et le CHA23-0024712 (PSE)  après 9784 jusqu'au 999611 +  15                             ",null,"Major","6","Planned"]
["SNCF-R","13688418061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2023-12-11","00:10:00","2024-12-09","05:35:00","Periodical",null,"Pour le CHA20-0018098 LGV + et le CHA23-0024712 (PSE) après 6144 jusqu'au 999611 retardé +15'                             ",null,"Major","1","Planned"]
["SNCF-R","13688415061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,14,"2023-12-17","00:45:00","2024-04-07","05:35:00","Periodical",null,"applicable lorsque circule 9098  9098 avancé ouvrant, 999611 retardé + 15 fermant                          ",null,"High","7","Planned"]
["SNCF-R","13688406461",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2023-12-11","23:37:00","2024-12-12","05:37:00","Periodical",null,"5h20 de sim. partielle déduite. SA2018 => SF ME 9/05, ME 31/10 Modification le 05/02/2019 : inversion Heure Début PK Début et Heure Début PK Fin, et Heure Fin PK Début et Heure Fin PK Fin   ",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688413461",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,52,46,"2023-12-25","22:40:00","2024-11-11","05:15:00","Periodical",null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022                     ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688414261",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,52,46,"2023-12-26","00:35:00","2024-11-12","06:00:00","Periodical",null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022                     ",null,"High","2,3,4,5,6","Planned"]
["SNCF-R","13688403261",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2023-12-11","22:30:00","2024-12-12","05:33:00","Periodical",null,"5h10 de sim. partielle déduite. SA2018 => VE/SA non activé du début du service au 30/03 pour circulation de l'Eurostar 9097 => Variante plus courte FEN17 Crisnoy-Vergigny 005 s'applique       ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688418061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2024-01-15","00:10:00","2024-01-22","05:35:00","Periodical",null,"Pour le CHA20-0018098 LGV + et le CHA23-0024712 (PSE) après 6144 jusqu'au 999611 retardé +15'                             ",null,"Major","1","Planned"]
["SNCF-R","13688416061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,2,49,"2024-01-13","23:30:00","2024-01-20","05:35:00","Periodical",null,"Pour le CHA20-0018098 LGV + et le CHA23-0024712 (PSE)  après 9784 jusqu'au 999611 +  15                             ",null,"Major","6","Planned"]
["SNCF-R","13688422061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00","Periodical",null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00",null,"Medium","1,2,3,5,6,7","Planned"]
["SNCF-R","13688404861",null,"< >","Poste 66 Crisenoy - Bif","Poste 15 Vergigny",2024,2024,50,50,"2023-12-11","13:13:00","2024-12-13","14:32:00","Periodical",null,"10700732 2021_SE_106 + 2021_SE_107 + 2021_SE_108 + 2021_SE_109 + 2021_SE_110 + 2021_SE_111 : décalage de quelques minutes pour avoir 6615 en SO et 6617 en SF                                                             ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688405661",null,"< >","Poste 66 Crisenoy - Bif","Poste 15 Vergigny",2024,2024,50,50,"2023-12-11","13:34:00","2024-12-13","14:11:00","Periodical",null,"10700733",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688297861",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-11","13:11:00","2024-12-13","14:01:00","Periodical",null,"10700733",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688296261",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-11","13:35:00","2024-12-13","14:44:00","Periodical",null,"10700732 2021_SE_106 + 2021_SE_107 + 2021_SE_108 + 2021_SE_109 + 2021_SE_110 + 2021_SE_111 : décalage de quelques minutes pour avoir 6615 en SO et 6617 en SF                                           ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688307461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,52,46,"2023-12-26","00:15:00","2024-11-12","06:00:00","Periodical",null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022                   ",null,"High","2,3,4,5,6","Planned"]
["SNCF-R","13688295461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-11","22:50:00","2024-12-12","06:07:00","Periodical",null,"5h52 de sim. partielle déduite. derrière 6635 les VE/SA SA2018 => VE/SA non activé du début du service au 30/03 pour circulation de l'Eurostar 9097                     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688306461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,52,46,"2023-12-25","22:50:00","2024-11-11","05:50:00","Periodical",null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022                   ",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13688299461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-11","23:10:00","2024-12-12","05:57:00","Periodical",null,"sauf jours typé VE SA2018 => SF ME 9/05, ME 31/10 Modification le 05/02/2019 : inversion Heure Début PK Début et Heure Début PK Fin",null,"Major","1,2,3,4","Planned"]
["SNCF-R","13688295461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2024-04-12","22:50:00","2024-12-13","06:07:00","Periodical",null,"5h52 de sim. partielle déduite. derrière 6635 les VE/SA SA2018 => VE/SA non activé du début du service au 30/03 pour circulation de l'Eurostar 9097                     ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13688298661",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-15","23:30:00","2024-12-13","05:57:00","Periodical",null,"TGV ouvrant 6672 VE/SA + jours typé VE SA2018 => + ME 9/05 + ME 31/10                       ",null,"Major","3,5","Planned"]
["SNCF-R","13688308461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,14,"2023-12-17","00:20:00","2024-04-07","06:15:00","Periodical",null,"TGV ouvrant 9098 avancé train fermant 999611 retardé +15'                   ",null,"High","7","Planned"]
["SNCF-R","13688311461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-11","00:10:00","2024-12-09","06:00:00","Periodical",null,"fenêtre applicable di/lu train ouvrant 6208 train fermant 999611 retardé +15                   ",null,"Major","1","Planned"]
["SNCF-R","13688297061",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,14,"2023-12-15","23:57:00","2024-04-05","06:07:00","Periodical",null,"sim. partielle déduite. SA2018 => VE/SA activé du début du service au 30/03 pour circulation de l'Eurostar 9097/6                     ",null,"High","5","Planned"]
["SNCF-R","13688309461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,15,49,"2024-04-13","23:10:00","2024-12-07","06:15:00","Periodical",null,"fenêtre applicable sa/di lorsque circule ne circule ni 6442 ni 9098. train ouvrant 9784 jusqu'au 999611 + 15                               ",null,"Major","6","Planned"]
["SNCF-R","13688305461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00","Periodical",null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00                             ",null,"Medium","1,2,3,5,6,7","Planned"]
["SNCF-R","13688320661",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00","Periodical",null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard   Train ouvrant: 6676    train fermant: 999611  ",null,"Medium","5","Planned"]
["SNCF-R","13688321661",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00","Periodical",null,"",null,"Medium","1","Planned"]
["SNCF-R","14636816861",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00","Periodical",null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard.",null,"Medium","6","Planned"]
["SNCF-R","13688304461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard  Train ouvrant  6144, train fermant  999611",null,"Medium","1","Planned"]
["SNCF-R","13688309461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,15,49,"2024-09-28","23:10:00","2024-09-28","06:15:00","Periodical",null,"fenêtre applicable sa/di lorsque circule ne circule ni 6442 ni 9098. train ouvrant 9784 jusqu'au 999611 + 15                               ",null,"Major","6","Planned"]
["SNCF-R","13688264261",null,"< >","Pasilly - Poste 17","Poste 19 Lacour-d'Arcenay",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00","Periodical",null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard   Train ouvrant: 6676    train fermant: 999611   ",null,"Medium","5","Planned"]
["SNCF-R","13688245061",null,"< >","Pasilly - Poste 17","Poste 19 Lacour-d'Arcenay",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard  Train ouvrant  6144, train fermant  999611",null,"Medium","1","Planned"]
["SNCF-R","13688265261",null,"< >","Pasilly - Poste 17","Poste 19 Lacour-d'Arcenay",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00","Periodical",null,"",null,"Medium","1","Planned"]
["SNCF-R","14637203161",null,"< >","Pasilly - Poste 17","Poste 19 Lacour-d'Arcenay",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00","Periodical",null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard",null,"Medium","6","Planned"]
["SNCF-R","13688288661",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Poste 27 Cesseins",2024,2024,2,2,"2024-01-08","23:40:00","2024-01-09","05:30:00","Periodical",null,"Essais limitrophes avec infrapôle Alpes la Semaine2, nuit du lu/ma à ma/me avec plage 4C_RPV_004   ZEP 257, 250, 260 et 261 du Poste 25 (MLH) en protection du rac de Pont de Veyle, TO 6635 TF 999614",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13687541061",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,50,"2023-12-11","10:56:00","2024-12-13","12:02:00","Periodical",null,"2024_SE_43 :vibration de -3' pour avoir TER 86985 en SF  le 15/19/17 MC19-0007 pour passage entre 4761 et 86985  MC19-0073 pour calage entre 4761 et 86985 (50minutes)  Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687539261",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,50,"2023-12-11","10:03:00","2024-12-13","10:48:00","Periodical",null,"MC19-0074 calage entre 9708 et 4654 Main courante 2020 Maj-565-871              ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687538461",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,49,"2023-12-11","00:35:00","2024-12-02","03:31:00","Periodical",null,"Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,"Major","1","Planned"]
["SNCF-R","13687540061",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,50,"2023-12-12","00:15:00","2024-12-14","05:25:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13687537661",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,49,"2023-12-11","01:33:00","2024-12-02","04:43:00","Periodical",null,"Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,"Major","1","Planned"]
["SNCF-R","13687540061",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,50,"2024-12-03","00:15:00","2024-12-07","05:25:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","13687540061",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,50,"2024-04-03","00:15:00","2024-04-27","05:25:00","Periodical",null,"",null,"Major","2,3,4,5,6","Planned"]
["SNCF-R","14535938661",null,"< >","Rassuen","Lavalduc - Bif RN Poste",2024,2024,15,16,"2024-04-08","22:30:00","2024-04-21","04:30:00","Periodical",null,"SA2024, UP SES AVI :  V2Bis avec Générique de nuit   Doamine S9 : ZEPG à LVU sur les deux semaines soit : ZEP 1+10+30 ou ZEP 6+7+8+9+13+24+26 ou ZEP 2+4+11",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","13576554061",null,"< >","St-Benoît (Vienne) - Bât Voyageurs","Coulombiers - Bif Coulombiers",2024,2024,50,50,"2023-12-11","12:40:00","2024-12-13","13:47:00","Periodical",null,"Mise en qualité Refonte 2022                                ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13576553261",null,"< >","St-Benoît (Vienne) - Bât Voyageurs","Coulombiers - Bif Coulombiers",2024,2024,50,50,"2023-12-11","10:30:00","2024-12-13","11:15:00","Periodical",null,"Mise en qualité Refonte 2022                          ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13576555661",null,"< >","St-Benoît (Vienne) - Bât Voyageurs","Coulombiers - Bif Coulombiers",2024,2024,50,45,"2023-12-11","23:50:00","2024-11-07","04:30:00","Periodical",null,"Mise en qualité Refonte 2022                                                              ",null,"Major","1,2,3,4,7","Planned"]
["SNCF-R","13576554861",null,"< >","St-Benoît (Vienne) - Bât Voyageurs","Coulombiers - Bif Coulombiers",2024,2024,50,45,"2023-12-11","23:00:00","2024-11-07","04:05:00","Periodical",null,"                                             ",null,"Major","1,2,3,4,7","Planned"]
["SNCF-R","14458077361",null,"< >","Ebange - Accès Nord","Thionville - Dépôt",2024,2024,22,22,"2024-05-30","10:00:00","2024-05-31","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 815+846, Voie B+1B / Accès VA interdit",null,"Medium","4","Planned"]
["SNCF-R","14457558961",null,"< >","Ebange - Accès Nord","Thionville - Dépôt",2024,2024,16,16,"2024-04-15","10:00:00","2024-04-16","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 817, Voie 1+2L7",null,"Medium","1","Planned"]
["SNCF-R","14457539261",null,"< >","Ebange - Accès Nord","Thionville - Dépôt",2024,2024,15,15,"2024-04-12","10:00:00","2024-04-13","12:30:00","Periodical",null,"Essais ETCS_C2 - Cap 2h30 jour, zep 818, Voie 2Bis",null,"Medium","5","Planned"]
["SNCF-R","13676310561",null,"< >","Metz-Ville - Quai Est","Metz-Ville - Poste 66 CTN1",2024,2024,11,49,"2024-03-11","23:35:00","2024-12-06","05:05:00","Periodical",null,"Cap 5h30 simultanées voies 1 + 2 lignes 3 + 11 de nuit entre Metz Ville et MZ-AM + MZS-AO + MZS-AE avec voies 1T + 2T. Accès Metz Ville et dépôt côté BV interdits. Suppression TER. Détournement FRET via Metz Marchandises ou Metz-Devant-les-Ponts. Attentio",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14544446561",null,"< >","Avignon - Bif Cavaillon","Avignon - Ent Dépôt",2024,2024,15,15,"2024-04-08","09:10:00","2024-04-09","13:10:00","Periodical",null,"SA2024, UP SES Voie Avignon :  Etendue S9 : Avi V2 AMS du C61 Km 1,490 au C68 Km 0,860 et V1 AMS du  du C66 Km 0,841 au C35 Km 1,902  Domaine S9 : 528+530+532+534+538+540 + 569+571",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-04-15","09:53:00","2024-05-10","15:25:00","Periodical",null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687342261",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,50,50,"2023-12-11","11:52:00","2024-12-13","13:08:00","Periodical",null,"recréation de 0F_VAV-SIZ_011 suite disparition après le redécoupage des sections CNM pour le SA 2020  2021_SE_100 + 2021_SE_101 + 2021_SE_102 + 2021_SE_103 : décalage de -02h dans un créneau offrant 01h d'amplitude pour la surveillance et permettre le tra",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-01-29","09:53:00","2024-11-15","15:25:00","Periodical",null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-01-29","09:53:00","2024-02-09","15:25:00","Periodical",null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-03-11","09:53:00","2024-09-20","15:25:00","Periodical",null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-03-04","09:53:00","2024-11-15","15:25:00","Periodical",null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-08-26","09:53:00","2024-10-04","15:25:00","Periodical",null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687343061",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,5,46,"2024-04-15","10:00:00","2024-05-10","14:45:00","Periodical",null,"recréation de 0F_VAV-SIZ_010 suite disparition après le redécoupage des sections CNM pour le SA 2020 2021_SE_45 : décalage de +50mn pour Corridor PNMD05, le 14/11/2019",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687343061",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,5,46,"2024-01-29","10:00:00","2024-11-15","14:45:00","Periodical",null,"recréation de 0F_VAV-SIZ_010 suite disparition après le redécoupage des sections CNM pour le SA 2020 2021_SE_45 : décalage de +50mn pour Corridor PNMD05, le 14/11/2019",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687343861",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,50,50,"2023-12-11","10:33:00","2024-12-13","11:06:00","Periodical",null,"recréation de 0F_VAV-SIZ_012 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687343061",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,5,46,"2024-01-29","10:00:00","2024-02-09","14:45:00","Periodical",null,"recréation de 0F_VAV-SIZ_010 suite disparition après le redécoupage des sections CNM pour le SA 2020 2021_SE_45 : décalage de +50mn pour Corridor PNMD05, le 14/11/2019",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687343061",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,5,46,"2024-03-04","10:00:00","2024-11-15","14:45:00","Periodical",null,"recréation de 0F_VAV-SIZ_010 suite disparition après le redécoupage des sections CNM pour le SA 2020 2021_SE_45 : décalage de +50mn pour Corridor PNMD05, le 14/11/2019",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13687343061",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,5,46,"2024-08-26","10:00:00","2024-10-04","14:45:00","Periodical",null,"recréation de 0F_VAV-SIZ_010 suite disparition après le redécoupage des sections CNM pour le SA 2020 2021_SE_45 : décalage de +50mn pour Corridor PNMD05, le 14/11/2019",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14699475061",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","Valence - ITE Km 611,695",2024,2024,20,30,"2024-05-13","21:40:00","2024-07-26","05:20:00","Periodical",null,"Créé pour CHA 24_0026011 - Eradication de Zones Bois RVB Andancette Portes  ZEP St Rambert Tain V1 - ZEP Tain St Rambert V2 - Sr. Saint Rambert-St Vallier V1 et Sr. Saint Rambert-St Vallier V2 - Sr. St Valliers - Serves V1 -  Sr. St Valliers - Serves V2 -",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13665563561",null,"< >","Serqueux - CV9105","Serqueux - C9144",2024,2024,3,50,"2024-03-04","13:11:00","2024-11-29","17:11:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13665563561",null,"< >","Serqueux - CV9105","Serqueux - C9144",2024,2024,3,50,"2024-01-15","13:11:00","2024-12-10","17:11:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13665563561",null,"< >","Serqueux - CV9105","Serqueux - C9144",2024,2024,3,50,"2024-02-05","13:11:00","2024-11-24","17:11:00","Periodical",null,"",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13703595461",null,"< >","Gennevilliers - Ent/Sort Sud","Gennevilliers - Ent/Sort Sud",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00","Periodical",null,"ITC industrielle",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14011400361",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,15,16,"2024-04-13","00:05:00","2024-04-20","05:10:00","Periodical",null,"Prépa MES LGV+ Les zones doivent être au blanc.  ",null,"Medium","6","Planned"]
["SNCF-R","14011804961",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,10,21,"2024-04-13","23:10:00","2024-04-21","05:10:00","Periodical",null,"Prépa MES LGV+ Les zones doivent être au blanc.  ",null,"Medium","6,7","Planned"]
["SNCF-R","14333548561",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,13,13,"2024-03-25","09:00:00","2024-03-28","14:15:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14333698361",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,13,14,"2024-03-29","10:00:00","2024-04-03","14:10:00","Periodical",null,"",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13793479061",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00","Periodical",null," Plage modifiée le 01/12/2022 suite report de la MES",null,"Medium","6","Planned"]
["SNCF-R","13689841061",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00","Periodical",null,"Maintenance IHM 1 Les zones doivent etre au blanc.   ",null,"Medium","1","Planned"]
["SNCF-R","14641848161",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   Les zones doivent etre au blanc.",null,"Medium","1","Planned"]
["SNCF-R","14011804961",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,10,21,"2024-03-09","23:10:00","2024-05-25","05:10:00","Periodical",null,"Prépa MES LGV+ Les zones doivent être au blanc.  ",null,"Medium","6,7","Planned"]
["SNCF-R","14640970761",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00","Periodical",null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   Les zones doivent etre au blanc.",null,"Medium","5","Planned"]
["SNCF-R","14365016761",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,4,17,"2024-01-22","10:10:00","2024-04-25","16:00:00","Periodical",null,"Voie A OU Voie B (Evitement de Nogent)  Complément de la 4D_AIY-LLA_012 (Voie 1 OU Voie 2).  Si Voie 1 alors Voie A  Si Voie 2 alors Voie B",null,"High","1,2,3,4","Planned"]
["SNCF-R","14365140761",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,4,27,"2024-01-26","10:15:00","2024-07-05","14:15:00","Periodical",null,"Voie A OU Voie B  (Evit. Nogent)  En complément de la 4F_AIY-LLA_001 (Voie 1 OU Voie 2)  Si Voie 1 alors Voie A  Si voie 2 alors Voie B",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14446758361",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,9,11,"2024-02-26","10:40:00","2024-03-14","14:45:00","Periodical",null,"En complément de la 4D_AIY-LLA_016   Voie 1 + 2",null,"High","1,2,3,4","Planned"]
["SNCF-R","14446852061",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,16,17,"2024-04-15","10:45:00","2024-04-25","13:45:00","Periodical",null,"En complément de la 4D_AIY-LLA_018   Voie 1 + 2",null,"High","1,2,3,4","Planned"]
["SNCF-R","14446684161",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,6,6,"2024-02-05","09:10:00","2024-02-08","15:10:00","Periodical",null,"En complément de la 4D_AIY-LLA_014 (Voie 1)",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","14446706161",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,7,11,"2024-02-12","10:45:00","2024-03-14","16:25:00","Periodical",null,"En complément de la 4D_AIY-LLA_015   Voie 2",null,"High","1,2,3,4","Planned"]
["SNCF-R","14446812161",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,9,10,"2024-02-26","14:40:00","2024-03-05","16:40:00","Periodical",null,"",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","14447001961",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,11,11,"2024-03-16","11:30:00","2024-03-16","11:15:00","Periodical",null,"En complément de la 4D_AIY-LLA_003  OCP de 24h Voie 1 + 2",null,"Medium","6","Planned"]
["SNCF-R","14366366361",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00","Periodical",null,"MES LGV+ Les zones doivent être au blanc.",null,"Medium","7","Planned"]
["SNCF-R","13690516761",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - Remisage Nord",2024,2024,1,49,"2024-01-02","13:50:00","2024-12-04","15:05:00","Periodical",null,"Gpt: 9933 891022 & 151954 circulent 2/2bis à LIU  ",null,"High","2,3","Planned"]
["SNCF-R","14365081161",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Côté NO",2024,2024,4,17,"2024-01-22","10:10:00","2024-04-25","16:00:00","Periodical",null,"Voie 1 OU Voie 2  Complété par la 4C_AIY-LLA_007 (Evit. Nogent)",null,"High","1,2,3,4","Planned"]
["SNCF-R","14333562061",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Côté NO",2024,2024,13,13,"2024-03-25","09:05:00","2024-03-28","14:10:00","Periodical",null,"TO: 9261   TF: 5763",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","13689840261",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Côté NO",2024,2024,51,34,"2023-12-18","10:20:00","2024-08-23","11:27:00","Periodical",null,"11401031",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","13689837661",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Côté NO",2024,2024,51,30,"2023-12-18","01:36:00","2024-07-22","04:50:00","Periodical",null,"11401136",null,"High","1","Planned"]
["SNCF-R","14446602061",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Côté NO",2024,2024,9,10,"2024-02-26","10:40:00","2024-03-05","16:40:00","Periodical",null,"Circulation des trains par la voie 2 de Aisy à Les Laumes",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","14446336661",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Côté NO",2024,2024,6,6,"2024-02-05","09:10:00","2024-02-08","15:10:00","Periodical",null,"Passage des trains en Bana par la voie 2 depuis Aisy à LLA.  TO: 9261     TF: 9215",null,"Medium","1,2,3,4","Planned"]
["SNCF-R","14978218061",null,"< >","Marseille-Blancarde - Bif Km 2,0 V B","Marseille-Blancarde - Technicentre",2024,2024,18,26,"2024-04-29","22:50:00","2024-06-28","04:50:00","Periodical",null,"PMR Blancarde, rallongement du quai de MV1 sur 100 mètres :  Domaine S9 : MV1, ZEP G 5813+5811 (Du JI Z429/423 Km 2,550 au C 407 + du C407 Km 2,767 au C500 Km 3,333)  Domaine S11 Sél 2759 (du Km 2,550 au Km 3,335)  ",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14952641261",null,"< >","Marseille-Blancarde - Technicentre","Marseille-Blancarde - Technicentre",2024,2024,36,50,"2024-09-02","00:00:00","2024-12-14","23:59:00","continuous",null,"LNPCA -Remisage TC Blancarde- Dépose d'installations et Fermeture en continue de 4 VS grill Electrique (de VS37 à 43). La capacité réservée dans l'outil TCAP ne nous permet pas cette précision apportée ci-après :  déposes d'installations sur le site du TC",null,"Major","","Planned"]
["SNCF-R","14609810461",null,"< >","Marseille-St-Charles - E/S Gare","Marseille-St-Charles - Remisage TER",2024,2024,6,6,"2024-02-05","21:00:00","2024-02-06","05:00:00","Periodical",null,"Tvx RAV MSC de 2024, zone E Circ de S06, L930, Traversée depuis Abeille vers zone E Circ. : MV1+MV2+MV3+MV4+GCirc du P3 0,820 => jusqu'au Sr2 Km 1,060 , Sur L830 depuis P3 Km 861,305 (C et D Circ.) => jusqu'au Km 857,206(C723)/859,625 (Aig 102bV) (MV1/MV2",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14346157561",null,"< >","Marseille-St-Charles - Remisage TER","Marseille-St-Charles - Remisage TER",2024,2024,1,15,"2024-01-02","23:20:00","2024-04-11","05:00:00","Periodical",null,"Tvx préparatoires et finitions du RAV MSC de 2024 de S01 à S03 et de S14 à S15, de 23h20 à 05h00 (du Lu/Ma à Je/Ve) : L930 VA, VB/MV4 à VC/MV3, MV1+MV2 => Sr2 Km 1,060 , sur L830 D à J en passant pas C/D/E/F Circ. => jusqu'au Km 860,187 (M1) et Km 860,113",null,"High","1,2,3,4","Planned"]
["SNCF-R","14621277961",null,"< >","Marseille-St-Charles - Remisage TER","Marseille-St-Charles - Remisage TER",2024,2024,4,4,"2024-01-22","23:00:00","2024-01-26","05:00:00","Periodical",null,"Tvx préparatoires et finitions du RAV MSC de 2024 de S04, (06h00 du Lu/Ma à Ve/Sa) : L930 VA, VB/MV4 à VC/MV3, MV1+MV2 +VG Circ.=> Sr2 Km 1,060 , sur L830 D à J en passant pas C/D/E/F Circ. => jusqu'au Km 860,113 (MV1+MV2) et jusqu'au  Km 860,257  (VE Cir",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14894397161",null,"< >","Marseille-St-Charles - Remisage TER","Marseille-St-Charles - Remisage TER",2024,2024,1,15,"2024-01-05","23:35:00","2024-04-12","05:15:00","Periodical",null,"Tvx préparatoires et finitions du RAV MSC de 2024 de S01 à S03 et 14 à 15, de 23h35 à 05h15 (nuit Ve/Sa) : L930 VA, VB/MV4 à VC/MV3, MV1+MV2 => Sr2 Km 1,060 , sur L830 D à J en passant pas C/D/E/F Circ. => jusqu'au Km 860,187 (M1) et Km 860,113 (M2) et ju",null,"Medium","5","Planned"]
["SNCF-R","14571039661",null,"< >","Salon","Miramas - ITE ZRA ETAMAT",2024,2024,24,24,"2024-06-15","17:00:00","2024-06-15","11:00:00","Periodical",null,"SA2024, CCR OP1, OCP 4 V1S+V2S+1Racct+2Racct, OCP4 18h du Sa 17h00 au Di 11h00 (du 01/06 au 02/06) :  Etendue S9 : V1S du C507 Km 66,880 au JI Z605/617 Km 68,130 / V2 de la PATC Km 65,976 au C607 Km 67,860 /Racct 1 de l'Aig 505 Km au C420 Km ,595  /Racct ",null,"Medium","6","Planned"]
["SNCF-R","14535645861",null,"< >","Miramas - Aig Km 808,5","Miramas - Dépôt",2024,2024,10,10,"2024-03-04","23:59:00","2024-03-08","03:30:00","Periodical",null,"SA2024, UP SES Avi :  Etendue S9 : L925 V1+V3G (du V1 Cv517 Km 67,251 au C627 Km 68,512+ V3G+ VS E/S dépôt)/L925 V2 du C619 Km 68,100 au C612 Km 68,220 / V1 L830 du C603 Km 808,585 au Cv610 Km 808,947    Domaine S9 :  L925 V1 173+175+177+190+179+137(VS)+1",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14012586261",null,"< >","Miramas - Aig Km 808,5","Miramas - Dépôt",2024,2024,4,4,"2024-01-27","00:15:00","2024-01-28","12:15:00","Periodical",null,"OCP1 36h, WE S04/05, sur VC, VD, V1MRS (passage par A circ+1Ter+B Circ+AM) :  Etendue S9 : 1S=>VD du JI Z605/617 Km 68,120 au C 627 Km 68,512 + 2S=>VC du Cv 615 Km 68,000 au C 625 Km 68,564 / V1Mrs du C 603 Km 808,585 au C 623 Km 68,564/809,312  Domaine S",null,"Medium","6,7","Planned"]
["SNCF-R","14114692761",null,"< >","Miramas - Relais La Crau","Miramas - Dépôt",2024,2024,40,49,"2024-09-30","23:05:00","2024-12-07","05:05:00","Periodical",null,"RAV MAS, CAP 06h00, Domaine de base :  Etendue S9 : V1TER C306 Km 806,814 au Pte Ag 410 Km 808,109 + V2TER/VB Circ du C308 Km 806,814 au GF Aig 603v Km 808,764 + VRacc. Triage du Pte Aig 421 Km 808,197 au C416 Km 808,369 +Racc V1 (du Cv 510 Km 67,270 à la",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14115493161",null,"< >","Miramas - Relais La Crau","Miramas - Dépôt",2024,2024,44,46,"2024-11-01","05:01:00","2024-11-12","05:01:00","Periodical",null,"RAV MAS, OCP 72h00, WE(s) S44/45 + S45/46, Domaine de base :  Etendue S9 : V1TER C306 Km 806,814 au Pte Ag 410 Km 808,109 + V2TER/VB Circ du C308 Km 806,814 au GF 603v Km 808,764 + VRacc. Triage du Pte Aig 421 Km 808,197 au C416 Km 808,369 +Racc V1 (du Cv",null,"High","1,2,3,4,5,6,7","Planned"]
["SNCF-R","14535551661",null,"< >","Miramas - Relais La Crau","Miramas - Dépôt",2024,2024,10,10,"2024-03-04","23:59:00","2024-03-08","03:30:00","Periodical",null,"SA2024, UP SES Avi :  Etendue S9 : L925 V1+V3G (du V1 Cv517 Km 67,251 au C627 Km 68,512+ V3G+ VS E/S dépôt)/L925 V2 du C619 Km 68,100 au C612 Km 68,220 / V1 L830 du C603 Km 808,585 au Cv610 Km 808,947    Domaine S9 :  L925 V1 173+175+177+190+179+137(VS)+1",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14114692761",null,"< >","Miramas - Relais La Crau","Miramas - Dépôt",2024,2024,40,49,"2024-09-30","23:05:00","2024-12-06","05:05:00","Periodical",null,"RAV MAS, CAP 06h00, Domaine de base :  Etendue S9 : V1TER C306 Km 806,814 au Pte Ag 410 Km 808,109 + V2TER/VB Circ du C308 Km 806,814 au GF Aig 603v Km 808,764 + VRacc. Triage du Pte Aig 421 Km 808,197 au C416 Km 808,369 +Racc V1 (du Cv 510 Km 67,270 à la",null,"Major","1,2,3,4,5","Planned"]
["SNCF-R","14545600461",null,"< >","Avignon - Bât Voyageurs","Avignon-Champfleury - Cv 2A",2024,2024,13,13,"2024-03-25","22:35:00","2024-03-27","03:05:00","Periodical",null,"SA2024, UP voie Avignon, à prendre avec 4C_AV_074 :  Etendue S9 : V1 du C162 Km 741,862 vers V à quais au Km 741,604  Domaine S9 : ZEP 595+599+621",null,"Medium","1,2,3","Planned"]
["SNCF-R","14545565861",null,"< >","Avignon - Bât Voyageurs","Avignon-Champfleury - Cv 2A",2024,2024,13,13,"2024-03-25","22:35:00","2024-03-29","03:05:00","Periodical",null,"SA2024, UP SES Avignon :  Etendue : depuis V A/B/C/D/E des C163 à 151 Km 741,604 vers Cv162 V1 Km 741,862 et Cv148 V2 Km 741,773  Domaine S9 : ZEP (V2 : 572+574=>4C_AV_076)+582+584+586+588+590+592 (+V1 : ZEP 595+599+621 =>4C_AV_075)",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14545613861",null,"< >","Avignon - Bât Voyageurs","Avignon-Champfleury - Cv 2A",2024,2024,13,13,"2024-03-25","22:35:00","2024-03-29","01:55:00","Periodical",null,"SA2024, UP SES Avignon :  Etendue : depuis V 2 du C 151 Km 741,604 vers Cv148 V2 Km 741,773  Domaine S9 : ZEP 572+574+(582+584+586+588+590+592=> 4C_AV_074) (+ ZEP 595+599+621 =>4C_AV_075)",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14558703661",null,"< >","Avignon - Bif Cavaillon","Avignon-Champfleury - Cv 2A",2024,2024,38,39,"2024-09-16","22:17:00","2024-09-29","01:55:00","Periodical",null,"Lot G C SUD, AVI, VTE+RFC à prendre avec 4C_AV_085 :   Etendue S9 : V2 du C176 Km 742,286 au Km 741,604 tête des voies VA , VB, VC   Domaine S9 Depuis A/B/C vers V2: ZEP G AVI 597(VA)+573(VB)+575(VC)+586+584+582+588+590+594+596+598   Etendue S11 Depuis A/",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14553194261",null,"< >","Avignon - Bif Rac","Avignon-Champfleury - Cv 2A",2024,2024,19,20,"2024-05-06","22:05:00","2024-05-17","03:05:00","Periodical",null,"AVI Voie 1+1 Gare,VTE+RFC, du C1 Km 739,706 au C163 Km 741,604, à prendre avec 4D_SCP-AVI_012 : Etendue S9 : PLM du C1 Km 739,706 au C 163 Km 741,604 Domaine S9 : ZEP G AVI 501+505+507+511+513+521+523+525+527 Etendue S11 : du Km 740,038 au Km 741,643 Doma",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14560316161",null,"< >","Avignon - Bif Rac","Avignon-Champfleury - Cv 2A",2024,2024,13,14,"2024-03-25","22:05:00","2024-04-05","01:55:00","Periodical",null,"SA 2024, VG, Avi Lot 4 à prendre avec 4D_SCP-AV_013 :  Etendue S9 : de la PATC Km 737,920 au Cv148 Km 741,773  Domaine S9 : 502+504+508+510+512+514+520+522+524+570+572+574  Etendue S11 : du Km 739,702 au Km 741,663  Domaine S11 : Sel 2092+2094+2096 Sr Fon",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14462167361",null,"< >","Ebange - Accès Nord","Thionville - Jonctions Nord",2024,2024,32,32,"2024-08-08","10:00:00","2024-08-09","11:30:00","Periodical",null,"Essais ETCS_C1 - Cap 1h30 jour, zep 843+817, Voie D+1 - Accès L204 interdit (vers 2L7)",null,"Medium","4","Planned"]
["SNCF-R","13676084061",null,"< >","Ebange - Faisceau","Thionville - Jonctions Nord",2024,2024,44,44,"2024-11-03","08:00:00","2024-11-04","15:00:00","Periodical",null,"Cap 7h DI, V1+V2B+VD+VC. Report des circulations V1B/V2 entre THL et UCK. Accès 204000 sens THL-->LGN(2L7) interdit. Voies C+D interdites. ",null,"Medium","7","Planned"]
["SNCF-R","15120169561",null,"< >","Ebange - Faisceau","Thionville - Jonctions Nord",2024,2024,14,16,"2024-04-01","23:55:00","2024-04-19","04:25:00","Periodical",null,"Cap 4h30 nuit, V1B+V2B+A+B+C, Thionville côté Sud.",null,"High","1,2,3,4,5","Planned"]
["SNCF-R","14457991961",null,"< >","Thionville - Bât Voyageurs","Thionville - Jonctions Nord",2024,2024,17,17,"2024-04-24","10:00:00","2024-04-25","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 891, Voie E",null,"Medium","3","Planned"]
["SNCF-R","14457507261",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,15,15,"2024-04-10","10:00:00","2024-04-11","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 862, Voie C",null,"Medium","3","Planned"]
["SNCF-R","14457335561",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,14,14,"2024-04-03","10:00:00","2024-04-04","12:30:00","Periodical",null,"Essais ETCS_C2 - Cap 2h30 jour, zep 863, Voie B",null,"Medium","3","Planned"]
["SNCF-R","14458001961",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,17,17,"2024-04-25","10:00:00","2024-04-26","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 856, Voie F",null,"Medium","4","Planned"]
["SNCF-R","14457362761",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,14,14,"2024-04-05","10:00:00","2024-04-06","12:00:00","Periodical",null,"Essais ETCS_C2 - Cap 2h jour, zep 861, Voie D",null,"Medium","5","Planned"]
["SNCF-R","14457726661",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,16,16,"2024-04-18","10:00:00","2024-04-19","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 853, Voie 1M",null,"Medium","4","Planned"]
["SNCF-R","14457380761",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,15,15,"2024-04-08","10:00:00","2024-04-09","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 859, Voie E",null,"Medium","1","Planned"]
["SNCF-R","14461835561",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,29,29,"2024-07-18","10:00:00","2024-07-19","12:30:00","Periodical",null,"Essais ETCS_C1 - Cap 2h30 jour, zep 861, Voie D",null,"Medium","4","Planned"]
["SNCF-R","14457525761",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,15,15,"2024-04-11","10:00:00","2024-04-12","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 861, Voie D",null,"Medium","4","Planned"]
["SNCF-R","14462275061",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,35,35,"2024-08-26","10:00:00","2024-08-27","11:30:00","Periodical",null,"Essais ETCS_C1 - Cap 1h30 jour, zep 856, Voie F",null,"Medium","1","Planned"]
["SNCF-R","14461831961",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,29,29,"2024-07-16","10:00:00","2024-07-17","12:30:00","Periodical",null,"Essais ETCS_C1 - Cap 2h30 jour, zep 863, Voie B",null,"Medium","2","Planned"]
["SNCF-R","14457478061",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,15,15,"2024-04-09","10:00:00","2024-04-10","12:00:00","Periodical",null,"Essais ETCS_C2 - Cap 2h jour, zep 861, Voie D",null,"Medium","2","Planned"]
["SNCF-R","14458059461",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,22,22,"2024-05-29","10:00:00","2024-05-30","11:30:00","Periodical",null,"Essais ETCS_C2 - Cap 1h30 jour, zep 843, Voie D+1",null,"Medium","3","Planned"]
["SNCF-R","14457353561",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,14,14,"2024-04-04","10:00:00","2024-04-05","12:30:00","Periodical",null,"Essais ETCS_C2 - Cap 2h30 jour, zep 862, Voie C",null,"Medium","4","Planned"]
["SNCF-R","14461833761",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,29,29,"2024-07-17","10:00:00","2024-07-18","12:30:00","Periodical",null,"Essais ETCS_C1 - Cap 2h30 jour, zep 862, Voie C",null,"Medium","3","Planned"]
["SNCF-R","14462225261",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,32,32,"2024-08-09","10:00:00","2024-08-10","11:30:00","Periodical",null,"Essais ETCS_C1 - Cap 1h30 jour, zep 859, Voie E",null,"Medium","5","Planned"]
["SNCF-R","14132606061",null,"< >","Thionville - Jonctions Nord","Thionville - Jonctions Nord",2024,2024,26,26,"2024-06-24","23:40:00","2024-06-28","05:25:00","Periodical",null,"Sél 56+58 du SSr Thionville côté BV, sél 29+31 du SSr Thionville côté P1, sél 60+63 du SSr Thionville Yutz. D+E+F+1Bis+2Bis interdites. Accès L177,178 restreint.",null,"Medium","1,2,3,4,5","Planned"]
["SNCF-R","14858632261",null,"< >","AISY ENTREE SORTIE LGV","Montbard - Point Changement de Voie",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00","Periodical",null,"Maintenance IHM",null,"Medium","1","Planned"]

{"sheet":"SBB","index":6,"n_rows":19,"n_cols":27,"rows_kept":19,"cut":false,"hidden":false,"merged":[[0,21,0,25],[0,3,0,4],[0,5,0,6],[0,7,0,8],[0,9,0,10],[0,11,0,12],[0,16,0,20]]}
["IM","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description"]
[null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["SBB Infra","Bellegarde-La Plaine-Genève La Praille","<> ","LPFR","GEPR/GE",2023,2023,8,49,"2023-02-19","22:00:00","2023-12-08","05:00:00","Week","night","track works ",null,"x",null,null,null,"x",null,"x","x",null,"Pose diagonales Satigny / nuit "]
["SBB Infra","Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,9,9,"2023-03-03","22:45:00","2023-03-06","05:00:00","Weekend","continuous","track works ","x",null,null,null,null,null,"x",null,null,null,"Total closure "]
["SBB Infra","Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,10,10,"2023-03-10","22:45:00","2023-03-12","22:00:00","Weekend","continuous","track works ","x",null,null,null,null,null,"x",null,null,null,"Total closure "]
["SBB Infra","Bellegarde-La Plaine-Genève La Praille","<> ","LPFR","GEPR/GE",2023,2023,25,30,"2023-06-16",null,"2023-07-24",null,"6 weeks","continuous","track works ",null,"x",null,null,null,"x",null,"x","x",null,"Permanentes 680/580 pose diagonales Satigny"]
["SBB Infra","Basel RB","<","BSRB",null,2023,2023,31,33,"2023-08-05","09:00:00","2023-08-21","06:00:00","Weekend Sa-Mo","continuous","track works ",null,"x",null,null,null,"x","x","x","x",null,"Trains S-N re-routing, no buffering possibilities BSRB"]
["SBB Infra","Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,39,39,"2023-09-29","22:45:00","2023-10-02","05:00:00","Weekend","continuous","track works ","x",null,null,null,null,null,"x",null,null,null,"Total closure "]
["SBB Infra","Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,40,40,"2023-10-06","22:45:00","2023-10-09","05:00:00","Weekend","continuous","track works ","x",null,null,null,null,null,"x",null,null,null,"Total closure "]
["SBB Infra","Bellegarde-La Plaine-Genève La Praille","<>","LPFR","GEPR/GE",2023,2023,41,42,"2023-10-13",null,"2023-10-23",null,"2 weekends","continuous","track works ","x","x",null,null,null,"x",null,"x",null,null,"Total closure 2 weekends / Friday 22:00-Monday 05:00"]
["SBB Infra","Bellegarde-La Plaine-Genève La Praille","< >","LPFR","GEPR/GE",2024,2024,1,46,"2024-01-01",null,"2024-11-15",null,"10 months","continuous","Platform and track works ",null,"x",null,null,null,"x",null,"x","x",null,"Total closures may be possible"]
["SBB Infra","Basel RB","< >","BSGB","BSRB",2024,2024,26,37,"2024-06-29","14:00:00","2024-09-09","02:00:00","Weekend Sa-Mo","continuous","track works ",null,"x",null,null,null,null,null,null,"x",null,"only one track available"]
["SBB Infra","Basel SBB","< >","BS",null,2024,2024,39,null,"2024-09-28","19:00:00","2024-09-30","05:00:00","Saturday-Monday","2x 10h shift","track works ",null,"x",null,null,null,"x",null,null,"x",null,"Reduced Track Availability "]
["SBB Infra","Basel St.Johann","< >","BSSJ",null,2024,2024,41,null,"2024-10-13","23:00:00","2024-10-14","05:00:00","Sunday-Monday","continuous","signal box replacement","x",null,null,null,null,null,null,null,null,null,"Total closure "]
["SBB Infra","Basel SBB","< >","BS",null,2024,2024,48,null,"2024-11-30","19:00:00","2024-12-02","05:00:00","Saturday-Monday","2x 10h shift","track works ",null,"x",null,null,null,"x",null,null,"x",null,"Reduced Track Availability "]
["SBB Infra","Basel St.Johann","< >","BSSJ",null,2024,2024,49,50,"2024-12-02",null,"2024-12-13",null,"Monday-Sunday","shifts","track works ","x","x",null,null,null,null,null,null,null,null,"Only garage installation affected"]
["SBB Infra","Bellegarde-La Plaine-Genève La Praille","<>","LPFR","GEPR/GE",2025,2025,1,49,"2025-01-01",null,"2025-12-10",null,"12 months","continuous","Platform and track works ",null,"x",null,null,null,"x",null,"x","x",null,"Total closures may be possible / interdictions permanentes voies 584/684"]
["SBB Infra","Bellegarde-La Plaine-Genève La Praille","<>","LPFR","GEPR/GE",2025,2025,32,34,"2025-08-11",null,"2025-08-25",null,"2 weeks","continuous","track works ","x",null,null,null,null,"x",null,null,null,null,"Total closure "]
["SBB Infra","Bellegarde-La Plaine-Genève La Praille","<>","SY","VMC",2026,2026,28,34,"2026-07-06",null,"xx.08.2026",null,"7 weeks","continuous","track works ",null,"x",null,null,null,"x",null,"x",null,null,"Interdiction permanenete voie 680"]

{"sheet":"ACF CFL","index":7,"n_rows":121,"n_cols":31,"rows_kept":121,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["ACF/CFL","ACF102","Luxembourg-Bettembourg",">","Luxembourg","Berchem",2023,2023,1,2,"2023-01-08","01:00:00","2023-01-09","04:00:00","1 day","Night/Day","renewal of the line","x","x",null,null,null,null,"x",null,null,"x","continious restriction",null,"no"]
["ACF/CFL","ACF103","Luxembourg-Bettembourg",">","Luxembourg","Berchem",2023,2023,2,3,"2023-01-15","01:00:00","2023-01-16","04:00:00","1 day","Night/Day","renewal of the line","x","x",null,null,null,null,"x",null,null,"x","continious restriction",null,"no"]
["ACF/CFL","ACF165","Rodange - Bettembourg","< >","Esch/Alzette","Differdange",2023,2023,7,7,"2023-02-13","22:00:00","2023-02-17","04:00:00","4 nights","mo/tu-th/fr","Maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF104","Luxembourg-Bettembourg","< >","Luxembourg","Fentange",2023,2023,7,8,"2023-02-18","01:00:00","2023-02-20","04:00:00","2 days","Night/Day","renewal of the line",null,null,null,null,null,null,"x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF105","Luxembourg-Bettembourg","< >","Luxembourg","Fentange",2023,2023,8,9,"2023-02-25","01:00:00","2023-02-27","04:00:00","2 days","Night/Day","renewal of the line",null,null,null,null,null,null,"x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF166","Rodange - Bettembourg","< >","Luxembourg","Berchem",2023,2023,9,10,"2023-03-04","01:30:00","2023-03-06","04:00:00","2 days","Night/Day","new line","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF167","Rodange - Bettembourg","< >","Luxembourg","Berchem",2023,2023,10,11,"2023-03-11","01:30:00","2023-03-13","04:00:00","2 days","Night/Day","new line","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF168","Rodange - Bettembourg","< >","Berchem","Bettembourg",2023,2023,11,12,"2023-03-18","01:30:00","2023-03-20","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF107","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2023,13,15,"2023-04-01","01:00:00","2023-04-17","04:00:00","16 days","Night/Day","Track maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF169","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,13,14,"2023-04-01","22:00:00","2023-04-03","04:00:00","2 nights","sa/su-su/mo","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF179","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,14,14,"2023-04-03","22:00:00","2023-04-06","04:00:00","3 nights","mo/tu-we/je","Catenary work",null,"x"]
["ACF/CFL","ACF170","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,14,15,"2023-04-08","22:00:00","2023-04-10","04:00:00","2 nights","sa/su-su/mo","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF180","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,15,15,"2023-04-10","22:00:00","2023-04-13","04:00:00","3 nights","mo/tu-we/je","Catenary work",null,"x"]
["ACF/CFL","ACF171","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,15,16,"2023-04-15","22:00:00","2023-04-17","04:00:00","2 nights","sa/su-su/mo","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF181","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,16,16,"2023-04-17","22:00:00","2023-04-20","04:00:00","3 nights","mo/tu-we/je","Catenary work",null,"x"]
["ACF/CFL","ACF109","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,16,17,"2023-04-22","01:00:00","2023-04-24","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF172","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,16,17,"2023-04-22","22:00:00","2023-04-24","04:00:00","2 nights","sa/su-su/mo","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF110","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2023,2023,17,18,"2023-04-29","01:00:00","2023-05-02","04:00:00","3 days","Night/Day","plattform renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF173","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,17,18,"2023-04-29","22:00:00","2023-05-01","04:00:00","2 nights","sa/su-su/mo","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF113","Rodange - Bettembourg","< >","Bettembourg","Esch/Alzette",2023,2023,18,19,"2023-05-06","01:00:00","2023-05-08","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF174","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,18,19,"2023-05-06","22:00:00","2023-05-08","04:00:00","2 nights","sa/su-su/mo","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF182","Rodange - Bettembourg","< >","Esch/Alzette","Differdange",2023,2023,19,19,"2023-05-08","22:00:00","2023-05-12","04:00:00","4 nights","mo/tu-th/fr","Maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF129","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2023,2023,19,20,"2023-05-13","01:00:00","2023-05-15","04:00:00","2 days","Night/Day","plattform renewal"]
["ACF/CFL","ACF175","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,19,20,"2023-05-13","22:00:00","2023-05-15","04:00:00","2 nights","sa/su-su/mo","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF176","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,20,21,"2023-05-20","22:00:00","2023-05-22","04:00:00","2 nights","sa/su-su/mo","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF189","Rodange - Bettembourg","< >","Rodange","Rodange",2023,2023,21,21,"2023-05-22","22:00:00","2023-05-25","04:00:00","3 nights","mo/tu-we/je","Catenary work",null,"x"]
["ACF/CFL","ACF112","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2023,2023,21,23,"2023-05-27","01:00:00","2023-06-05","04:00:00","9 days","Night/Day","Track and plattform maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF177","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,21,22,"2023-05-27","22:00:00","2023-05-29","04:00:00","2 nights","sa/su-su/mo","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF190","Rodange - Bettembourg","< >","Rodange","Rodange",2023,2023,22,22,"2023-05-29","22:00:00","2023-06-01","04:00:00","3 nights","mo/tu-we/je","Catenary work",null,"x"]
["ACF/CFL","ACF178","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,22,23,"2023-06-03","22:00:00","2023-06-04","04:00:00","2 nights","sa/su-su/mo","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF191","Rodange - Bettembourg","< >","Rodange","Rodange",2023,2023,23,23,"2023-06-05","22:00:00","2023-06-08","04:00:00","3 nights","mo/tu-we/je","Catenary work",null,"x"]
["ACF/CFL","ACF186","Rodange - Bettembourg","< >","Rodange-frontière","Rodange",2023,2023,23,25,"2023-06-10","01:00:00","2023-06-25","22:00:00","2 weeks","Night/Day","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF187","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,23,25,"2023-06-10","22:00:00","2023-06-25","04:00:00","2 weeks","Night","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF114","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2023,24,25,"2023-06-17","01:00:00","2023-06-19","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF183","Rodange - Bettembourg","< >","Berchem","Bettembourg",2023,2023,24,25,"2023-06-17","01:30:00","2023-06-19","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF115","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2022,25,26,"2023-06-24","02:00:00","2023-06-26","02:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF184","Rodange - Bettembourg","< >","Berchem","Bettembourg",2023,2023,25,26,"2023-06-24","01:30:00","2023-06-26","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF188","Rodange - Bettembourg","< >","Bascharage/Sanem","Dippach/Reckange",2023,2023,25,26,"2023-06-25","22:00:00","2023-06-30","04:00:00","5 nights","su/mo-je/ve","Maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF130","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,26,26,"2023-07-01","06:00:00","2023-07-02","21:00:00","2 days","Night/Day","plattform renewal"]
["ACF/CFL","ACF185","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2023,26,27,"2023-07-01","02:00:00","2023-07-03","02:00:00","2 days","Night/Day","Maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF194","Rodange - Bettembourg","< >","Esch/Alzette","Differdange",2023,2023,27,27,"2023-07-03","22:00:00","2023-07-07","04:00:00","4 nights","Night","Maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF131","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,27,28,"2023-07-08","06:00:00","2023-07-10","04:00:00","2 days","Night/Day","plattform renewal"]
["ACF/CFL","ACF132","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,28,29,"2023-07-15","06:00:00","2023-07-17","04:00:00","2 days","Night/Day","plattform renewal"]
["ACF/CFL","ACF192","Rodange - Bettembourg","< >","Pétange","Dippach/Reckange",2023,2023,29,29,"2023-07-17","22:00:00","2023-07-21","04:00:00","4 nights","mo/tu-th/fr","Maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF133","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,29,30,"2023-07-22","06:00:00","2023-07-24","04:00:00","2 days","Night/Day","plattform renewal"]
["ACF/CFL","ACF193","Rodange - Bettembourg","< >","Luxembourg","Berchem",2023,2023,29,30,"2023-07-22","01:30:00","2023-07-24","04:00:00","2 days","Night/Day","new line",null,"x",null,null,null,null,"x",null,"x"]
["ACF/CFL","ACF195","Rodange - Bettembourg","< >","Berchem","Bettembourg",2023,2023,34,35,"2023-08-26","01:30:00","2023-08-28","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF196","Rodange - Bettembourg","< >","Rodange","Rodange",2023,2023,37,38,"2023-09-15","22:00:00","2023-09-18","04:00:00","3 nights","fr/sa-di/lu","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF134","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,37,38,"2023-09-16","01:00:00","2023-09-18","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF200","Rodange - Bettembourg","< >","Rodange","Rodange",2023,2023,38,38,"2023-09-18","22:00:00","2023-09-21","04:00:00","3 nights","mo/tu-we/je","Catenary work",null,"x"]
["ACF/CFL","ACF197","Rodange - Bettembourg","< >","Rodange","Rodange",2023,2023,38,39,"2023-09-22","22:00:00","2023-09-25","04:00:00","3 nights","fr/sa-di/lu","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF135","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,38,39,"2023-09-23","01:00:00","2023-09-25","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF201","Rodange - Bettembourg","< >","Rodange","Rodange",2023,2023,39,39,"2023-09-25","22:00:00","2023-09-28","04:00:00","3 nights","mo/tu-we/je","Catenary work",null,"x"]
["ACF/CFL","ACF198","Rodange - Bettembourg","< >","Rodange","Rodange",2023,2023,39,40,"2023-09-29","22:00:00","2023-10-02","04:00:00","3 nights","fr/sa-di/lu","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF136","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,39,40,"2023-09-30","01:00:00","2023-10-02","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF202","Rodange - Bettembourg","< >","Rodange","Rodange",2023,2023,40,40,"2023-10-02","22:00:00","2023-10-05","04:00:00","3 nights","mo/tu-we/je","Catenary work",null,"x"]
["ACF/CFL","ACF199","Rodange - Bettembourg","< >","Rodange","Rodange",2023,2023,40,41,"2023-10-06","22:00:00","2023-10-09","04:00:00","3 nights","fr/sa-di/lu","Catenary work","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF137","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,40,41,"2023-10-07","01:00:00","2023-10-09","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF138","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,41,42,"2023-10-14","01:00:00","2023-10-16","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF139","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,42,43,"2023-10-21","01:00:00","2023-10-23","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF122","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2023,2023,43,45,"2023-10-28","01:00:00","2023-11-06","04:00:00","9 days","Night/Day","Track and plattform maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF141","Rodange - Bettembourg","< >","Luxembourg","Bettembourg",2023,2023,45,46,"2023-11-11","01:00:00","2023-11-13","04:00:00","2 days","Night/Day","new line"]
["ACF/CFL","ACF147","Rodange - Bettembourg","< >","Luxembourg","Dippach/Reckange",2023,2023,45,46,"2023-11-11","01:00:00","2023-11-13","04:00:00","2 days","Night/Day","elimination railway crossing"]
["ACF/CFL","ACF148","Rodange - Bettembourg","< >","Luxembourg","Pétange",2023,2023,47,48,"2023-11-25","01:00:00","2023-11-27","04:00:00","2 days","Night/Day","catenary & track maintenance"]
["ACF/CFL","ACF144","Rodange - Bettembourg","< >","Luxembourg","Bettembourg",2023,2023,48,49,"2023-12-02","01:00:00","2023-12-04","04:00:00","2 days","Night/Day","new line"]
["ACF/CFL","ACF146","Rodange - Bettembourg","< >","Luxembourg","Bettembourg",2023,2023,50,51,"2023-12-16","01:00:00","2023-12-18","04:00:00","2 days","Night/Day","new line"]
["ACF/CFL","ACF203","Rodange-Bettembourg","< >","Bascharage/Sanem","Dippach/Reckange",2024,2024,4,5,"2024-01-27","01:00:00","2024-01-29","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF204","Rodange-Bettembourg","< >","Bettembourg","Bettembourg",2024,2024,6,7,"2024-02-10","01:00:00","2024-02-12","04:00:00","2 days","Night/Day","Public road works",null,"x",null,null,null,null,"x"]
["ACF/CFL","ACF206","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2024,2024,6,7,"2024-02-10","01:00:00","2024-02-12","04:00:00","2 days","Night/Day","Maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF207","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2024,2024,7,8,"2024-02-17","01:00:00","2024-02-19","04:00:00","2 days","Night/Day","Maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF208","Rodange-Bettembourg","< >","Bascharage/Sanem","Dippach/Reckange",2024,2024,7,8,"2024-02-17","01:00:00","2024-02-19","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF205","Rodange-Bettembourg","< >","Bettembourg","Bettembourg",2024,2024,8,9,"2024-02-24","01:00:00","2024-02-26","04:00:00","2 days","Night/Day","Public road works",null,"x",null,null,null,null,"x"]
["ACF/CFL","ACF209","Rodange-Bettembourg","< >","Bascharage/Sanem","Dippach/Reckange",2024,2024,9,10,"2024-03-02","01:00:00","2024-03-04","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF210","Rodange-Bettembourg","< >","Bascharage/Sanem","Dippach/Reckange",2024,2024,11,12,"2024-03-16","01:00:00","2024-03-18","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF149","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2024,2024,13,16,"2024-03-30","01:00:00","2024-04-15","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF150","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2024,2024,16,17,"2024-04-20","01:00:00","2024-04-22","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF151","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2024,2024,17,18,"2024-04-27","01:00:00","2024-04-29","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF152","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2024,2024,18,19,"2024-05-04","01:00:00","2024-05-06","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF153","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2024,2024,19,20,"2024-05-11","01:00:00","2024-05-13","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF154","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2024,2024,20,21,"2024-05-18","01:00:00","2024-05-20","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF155","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2024,2024,21,23,"2024-05-25","01:00:00","2024-06-03","04:00:00","1 week","Night/Day","Infrastructure maintenance"]
["ACF/CFL","ACF211","Rodange-Bettembourg","< >","Bascharage/Sanem","Dippach/Reckange",2024,2024,22,23,"2024-06-01","01:00:00","2024-06-03","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF156","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2024,2024,26,27,"2024-06-29","01:00:00","2024-07-01","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF157","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2024,2024,27,28,"2024-07-06","01:00:00","2024-07-08","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF212","Rodange-Bettembourg","< >","Bascharage/Sanem","Dippach/Reckange",2024,2024,27,28,"2024-07-06","01:00:00","2024-07-08","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF158","Rodange-Bettembourg","< >","Luxembourg","Berchem",2024,2024,29,33,"2024-07-16","01:00:00","2024-08-12","04:00:00","4 weeks","Night/Day","new line"]
["ACF/CFL","ACF159","Rodange-Bettembourg","< >","Berchem","Bettembourg",2024,2024,33,38,"2024-08-12","04:00:00","2024-09-16","04:00:00","5 weeks","Night/Day","new line"]
["ACF/CFL","ACF160","Rodange-Athus","< >","Rodange","Athus",2024,2024,34,38,"2024-08-24","01:00:00","2024-09-16","04:00:00","4 weeks","Night/Day","Maintenance"]
["ACF/CFL","ACF213","Rodange-Mont St.Martin","< >","Rodange","Mont St.Martin",2024,2024,36,37,"2024-09-06","22:00:00","2024-09-09","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF214","Rodange-Mont St.Martin","< >","Rodange","Mont St.Martin",2024,2024,37,38,"2024-09-13","22:00:00","2024-09-16","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF161","Rodange-Bettembourg","< >","Berchem","Bettembourg",2024,2024,38,39,"2024-09-21","01:00:00","2024-09-23","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF215","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2024,2024,39,40,"2024-09-28","01:00:00","2024-09-30","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF216","Rodange-Bettembourg","< >","Bascharage/Sanem","Dippach/Reckange",2024,2024,39,40,"2024-09-28","01:00:00","2024-09-30","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF217","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2024,2024,40,41,"2024-10-05","01:00:00","2024-10-07","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF218","Rodange-Bettembourg","< >","Bascharage/Sanem","Dippach/Reckange",2024,2024,40,41,"2024-10-05","01:00:00","2024-10-07","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF162","Rodange-Bettembourg","< >","Luxembourg","Berchem",2024,2024,40,41,"2024-10-06","01:00:00","2024-10-07","04:00:00","1 day","Night/Day","Maintenance"]
["ACF/CFL","ACF219","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2024,2024,41,42,"2024-10-12","01:00:00","2024-10-14","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF163","Rodange-Bettembourg","< >","Luxembourg","Berchem",2024,2024,41,42,"2024-10-13","01:00:00","2024-10-14","04:00:00","1 day","Night/Day","Maintenance"]
["ACF/CFL","ACF220","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2024,2024,42,43,"2024-10-19","01:00:00","2024-10-21","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF164","Rodange-Bettembourg","< >","Luxembourg","Berchem",2024,2024,42,43,"2024-10-20","01:00:00","2024-10-21","04:00:00","1 day","Night/Day","Maintenance"]
["ACF/CFL","ACF221","Rodange-Bettembourg","< >","Hollerich","Dippach/Reckange",2024,2024,44,45,"2024-11-01","01:00:00","2024-11-04","04:00:00","3 days","Night/Day","elimination railway crossing","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF222","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2024,2024,45,46,"2024-11-09","01:00:00","2024-11-11","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF223","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2024,2024,45,46,"2024-11-09","01:00:00","2024-11-11","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF224","Rodange-Bettembourg","< >","Hollerich","Pétange",2024,2024,46,47,"2024-11-16","01:00:00","2024-11-18","04:00:00","2 days","Night/Day","elimination railway crossing","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF225","Rodange-Bettembourg","< >","Bascharage/Sanem","Dippach/Reckange",2024,2024,47,48,"2024-11-23","01:00:00","2024-11-25","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF226","Rodange-Bettembourg","< >","Berchem","Bettembourg",2024,2024,50,51,"2024-12-14","01:00:00","2024-12-16","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF227","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,2,3,"2025-01-11","01:00:00","2024-01-13","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF228","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,7,9,"2025-02-15","01:00:00","2025-02-24","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF229","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,10,11,"2025-03-08","01:00:00","2025-03-10","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF230","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,12,13,"2025-03-22","01:00:00","2025-03-24","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF231","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2025,2025,14,17,"2025-04-05","01:00:00","2025-04-22","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF232","Rodange-Bettembourg","< >","Berchem","Bettembourg",2025,2025,14,17,"2025-04-05","01:00:00","2025-04-22","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF233","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,17,18,"2025-04-26","01:00:00","2025-04-28","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF234","Rodange-Bettembourg","< >","Bettembourg","Esch/Alzette",2025,2025,21,23,"2025-05-24","01:00:00","2025-06-02","04:00:00","1 week","Night/Day","track renewal","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF235","Rodange-Bettembourg","< >","Berchem","Bettembourg",2025,2025,26,27,"2025-06-28","01:00:00","2025-06-30","04:00:00","2 days","Night/Day","new line","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF236","Rodange-Bettembourg","< >","Berchem","Bettembourg",2025,2025,27,28,"2025-07-05","01:00:00","2025-07-07","04:00:00","2 days","Night/Day","new line","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF237","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,29,38,"2025-07-16","01:00:00","2025-09-15","04:00:00","2 months","Night/Day","new line","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF238","Rodange-Bettembourg","< >","Luxembourg","Pétange",2025,2025,43,45,"2025-10-25","01:00:00","2025-11-03","04:00:00","1 week","Night/Day","new line","x",null,null,null,null,"x","x"]
["ACF/CFL","ACF239","Rodange-Bettembourg","< >","Hollerich","Dippach/Reckange",2025,2025,47,48,"2025-11-22","01:00:00","2025-11-24","04:00:00","2 days","Night/Day","elimination railway crossing","x",null,null,null,null,"x","x"]