{"text_format":"1","workbook":"xlsx","n_sheets":8,"sheets":["Home","Main Impact Map","ProRail","Infrabel","Data","SNCFR","SBB","ACF CFL"],"not_rendered":{"charts":0,"images":11,"macros":1,"external_links":8,"defined_names":63,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Home","index":0,"n_rows":18,"n_cols":15,"rows_kept":18,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"! click icon to follow !"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["                              version 14 September 2020"]

{"sheet":"Main Impact Map","index":1,"n_rows":15,"n_cols":14,"rows_kept":15,"cut":false,"hidden":false,"merged":[[45,5,46,7]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Main TCR for TT 2020 to TT 2022"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"2019-09-14"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"click on              for detailed TCR information"]

{"sheet":"ProRail","index":2,"n_rows":374,"n_cols":31,"rows_kept":374,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
["ProRail","IO-K-005836-FH19-00",".",">","Maasvlakte aansl.","Maasvlakte empl. West west",2020,2020,4,4,"2020-01-26","07:00:00","2020-01-26","23:00:00","16:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Plaatsen lichtmast 2, herstellen lichtmast 1 Groep 1770",null,"N","K-005836"]
["ProRail","IO-K-006000-2001-00",".","< >","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2020,2020,45,47,"2020-11-07","01:00:00","2020-11-16","05:00:00","220:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Saneren van wissels 101A/B, 123A/B, 141A/B, 143A/B, 255, 253 A/B, 163A/B, 959A/B, 983A/B, 985A/B + 975/977, 901AB/917AB",null,"Y","K-006000"]
["ProRail","IO-K-006000-2102-00",".",">","IJsselmonde","Willemstunnel Zuid",2021,2021,9,10,"2021-03-06","01:25:00","2021-03-08","05:25:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"BBV werkzaamheden",null,"Y","K-006000"]
["ProRail","IO-K-006000-2101-00",".",">","Barendrecht","Zwijndrecht",2021,2021,13,14,"2021-04-03","01:10:00","2021-04-05","05:10:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"Wissels 873A, 873B symm en 875 + spoor 1264 + KG/KF + wissel 969 Spoor LJ ca. 5 km sps (kijfhoek)",null,"Y","K-006000"]
["ProRail","IO-K-006000-2103-00",".",">","IJsselmonde","Rotterdam Stadion",2021,2021,20,21,"2021-05-22","01:30:00","2021-05-24","05:30:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"BBV werkzaamheden",null,"Y","K-006000"]
["ProRail","IO-K-006000-2105-00",".",">","Kijfhoek aansl. Zuid","Zwijndrecht",2021,2021,44,45,"2021-11-06","01:00:00","2021-11-08","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"Sporen HR, 67 en 68 kijfhoek",null,"Y","K-006000"]
["ProRail","IO-K-006002-GK03-00",".",">","Kijfhoek aansluiting noord","Kijfhoek zuid",2020,2020,12,13,"2020-03-21","02:00:00","2020-03-23","22:00:00","68:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Kijfhoef vervanging W03",null,"N","K-006002"]
["ProRail","IO-K-006002-2001-00",".",">","Kijfhoek aansluiting noord","Kijfhoek zuid",2020,2020,15,16,"2020-04-11","23:00:00","2020-04-14","03:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"werkplek 7: Vernieuwen wissels 2353A vernieuwen spoor tussen vk wissel 3759 en vk wissel 3781A rechtzetten 4 stuks BVL portalen",null,"N","K-006002"]
["ProRail","IO-K-006002-W07-00",".",">","Kijfhoek aansluiting noord","Kijfhoek zuid",2020,2020,15,16,"2020-04-11","19:00:00","2020-04-13","23:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"werkplek 7: Vernieuwen wissels 2353A vernieuwen spoor tussen vk wissel 3759 en vk wissel 3781A rechtzetten 4 stuks BVL portalen",null,"Y","K-006002"]
["ProRail","IO-K-006005-2001-00",".",">","Capelle Schollevaar","Rotterdam Noord goed. West",2020,2020,37,38,"2020-09-12","00:00:00","2020-09-14","04:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Spoorvernieuwing Rtd-Gd",null,"N","K-006005"]
["ProRail","IO-K-006017-1906-00",".",">","Gouda","Gouda Goverwelle",2020,2020,11,12,"2020-03-14","01:00:00","2020-03-16","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"reconstructie kabeltracé, verwijderen kabelkokers.",null,"Y","K-006017"]
["ProRail","IO-K-006017-1908-00",".",">","Gouda","Gouda",2020,2020,25,26,"2020-06-20","01:00:00","2020-06-22","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"reconstructie kabeltracé, verwijderen kabelkokers.",null,"Y","K-006017"]
["ProRail","IO-K-006017-2001-00",".",">","Gouda","Moordrecht overloopw.",2020,2020,37,38,"2020-09-11","00:00:00","2020-09-14","04:00:00","76:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"BBV Gouda",null,"Y","K-006017"]
["ProRail","IO-K-006021-RTD2-00",".",">","Delfshaven Schiebrug aansl.","Willemstunnel Zuid",2020,2020,13,14,"2020-03-28","00:40:00","2020-03-30","05:40:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"BBV RTD - Vernieuwen sporen 1M, 2M, 3M, wissels 231, 233, 341, 347",null,"Y","K-006021"]
["ProRail","IO-K-006021-RTD4-00",".",">","Delfshavense Schie, brug o/d - bij Schiedam","Willemstunnel Zuid",2020,2020,46,47,"2020-11-13","01:00:00","2020-11-16","05:00:00","76:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"BBV RTD - Vernieuwen sporen 1M, 2M, 3M, wissels 231, 233, 341, 347",null,"Y","K-006021"]
["ProRail","IO-K-006031-2002-00",".",">","Dordrecht","Dordrecht",2020,2020,15,15,"2020-04-06","01:00:00","2020-04-11","01:00:00","120:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Ontvangst en boorput ivm gestuurde boring km 29.490, boring uitvoeren, drainage spoor 21 aanleggen en meer",null,"Y","K-006031"]
["ProRail","IO-K-006031-2003-00",".",">","Dordrecht","Dordrecht",2020,2020,15,16,"2020-04-11","01:00:00","2020-04-13","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Ontvangst en boorput ivm gestuurde boring km 29.490, boring uitvoeren, drainage spoor 21 aanleggen en meer",null,"Y","K-006031"]
["ProRail","IO-K-006031-2004-00",".",">","Dordrecht","Dordrecht",2020,2020,16,16,"2020-04-13","05:00:00","2020-04-15","05:00:00","48:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Ontvangst en boorput ivm gestuurde boring km 29.490, boring uitvoeren, drainage spoor 21 aanleggen en meer",null,"Y","K-006031"]
["ProRail","IO-K-006305-2101-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"werkzaamheden Calandbrug",null,"Y","K-006305"]
["ProRail","IO-K-006305-2102-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,20,21,"2021-05-22","19:00:00","2021-05-24","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"werkzaamheden Calandbrug",null,"Y","K-006305"]
["ProRail","IO-K-006308-2001-00",".","< >","Gouda","Moordrecht overloopw.",2021,2021,6,7,"2021-02-13","01:15:00","2021-02-15","05:15:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"groot onderhoud aan brug",null,"Y","K-006308"]
["ProRail","IO-K-006308-2101-00",".",">","Gouda","Moordrecht overloopw.",2021,2021,10,11,"2021-03-13","01:15:00","2021-03-15","05:15:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"groot onderhoud aan brug",null,"Y","K-006308"]
["ProRail","IO-K-006308-2003-00",".",">","Gouda","Moordrecht aansl.",2021,2021,14,15,"2021-04-10","01:00:00","2021-04-12","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Groot Onderhoud Hef- en Draaibrug te Gouda",null,"Y","K-006308"]
["ProRail","IO-K-006310-2101-00",".","< >","Gouda","Moordrecht overloopw.",2021,2021,6,7,"2021-02-13","01:15:00","2021-02-15","05:15:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"omlassen kabeltrace's, werkzaamheden relaishuis 10 Gd.",null,"Y","K-006310"]
["ProRail","IO-K-006310-2102-00",".",">","Gouda","Moordrecht overloopw.",2021,2021,10,11,"2021-03-13","01:15:00","2021-03-15","04:15:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"omlassen kabeltrace's, werkzaamheden relaishuis 10 Gd.",null,"Y","K-006310"]
["ProRail","IO-K-006357-2017-00",".",">","Barendrecht","Willemstunnel Zuid",2020,2020,35,35,"2020-08-27","02:00:00","2020-08-28","00:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Balken verhogen spoor KJ en LJ. Monteren 1 overspanningsafleider km 43",null,"Y","K-006357"]
["ProRail","IO-K-006357-2018-00",".",">","Barendrecht","Rotterdam Stadion",2020,2020,35,35,"2020-08-28","00:00:00","2020-08-28","22:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Ophogen balken sporen BG, HJ en JJ onder kunstwerken.",null,"Y","K-006357"]
["ProRail","IO-K-006357-2014-00",".","< >","Barendrecht","Rotterdam Stadion",2020,2020,40,41,"2020-10-03","00:00:00","2020-10-05","04:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Wijzigingen draagconstructie Munnikensteeg Plaatsen van 4 overspanningsbeveiligingen",null,"Y","K-006357"]
["ProRail","IO-K-006357-2019-00",".",">","Barendrecht","Rotterdam Stadion",2020,2020,46,46,"2020-11-14","00:00:00","2020-11-14","22:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Ophogen balken sporen BG, HJ en JJ onder kunstwerken.",null,"Y","K-006357"]
["ProRail","IO-K-006357-2020-00",".",">","Barendrecht","Willemstunnel Zuid",2020,2020,46,46,"2020-11-15","00:00:00","2020-11-15","22:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Balken verhogen spoor KJ en LJ. Monteren 1 overspanningsafleider km 43",null,"Y","K-006357"]
["ProRail","IO-K-006608-2003-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,13,14,"2020-03-28","01:09:00","2020-03-30","05:09:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afronden vluchtpadverlichting HJ",null,"Y","K-006608"]
["ProRail","IO-K-006608-2004-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,18,19,"2020-05-02","01:10:00","2020-05-04","04:10:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afronden vluchtpadverlichting HJ",null,"Y","K-006608"]
["ProRail","IO-K-006608-2002-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,36,37,"2020-09-05","00:00:00","2020-09-07","03:00:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afronden vluchtpadverlichting KL",null,"Y","K-006608"]
["ProRail","IO-K-006608-2001-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,42,43,"2020-10-17","00:00:00","2020-10-19","03:00:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afronden vluchtpadverlichting KL",null,"Y","K-006608"]
["ProRail","IO-K-006608-2005-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,46,47,"2020-11-14","00:00:00","2020-11-16","03:00:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afronden vluchtpadverlichting HJ",null,"Y","K-006608"]
["ProRail","IO-K-006610-2057-00",".",">","Dordrecht","Dordrecht",2020,2020,14,15,"2020-04-04","01:00:00","2020-04-06","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"wissel 1241 spoor 21;20; 43b",null,"Y","K-006610"]
["ProRail","IO-K-006610-2053-00",".",">","Dordrecht","Dordrecht",2020,2020,40,41,"2020-10-03","01:00:00","2020-10-05","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"wissels: - 1175 - 1185 - 1183A - 1183B - 1177B",null,"Y","K-006610"]
["ProRail","IO-K-006610-2059-00",".",">","Dordrecht","Dordrecht",2020,2020,40,40,"2020-09-29","08:00:00","2020-10-01","20:00:00","60:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"43b",null,"Y","K-006610"]
["ProRail","IO-K-006610-2056-00",".","< >","Dordrecht","Dordrecht",2020,2020,43,44,"2020-10-24","01:00:00","2020-10-26","04:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"R",null,null,null,"wissels: -1145A -1145B -1165",null,"Y","K-006610"]
["ProRail","IO-K-006613-1901-00",".",">","Barendrecht","Rotterdam Stadion",2022,2022,14,15,"2022-04-09","00:00:00","2022-04-11","04:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Aanpassen besturing in 5 tunnelbuizen (NS-reisigers, Goederen en HSL) en Dive Under HSL.",null,"N","K-006613"]
["ProRail","IO-K-006630-1915-03",".",">","Europoort","Suurhoffbrug o/h Hartelkanaal",2020,2020,9,10,"2020-02-29","23:00:00","2020-03-02","07:00:00","32:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"vernieuwen spoor en wissels",null,"N","K-006630"]
["ProRail","IO-K-006630-2009-01",".",">","Botlek","Botlek",2020,2020,15,16,"2020-04-11","19:00:00","2020-04-13","23:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen spoor, spoorstaven en overwegbevloeringen.",null,"Y","K-006630"]
["ProRail","IO-K-006630-2019-00",".",">","Maasvlakte","Maasvlakte",2020,2020,16,16,"2020-04-13","23:00:00","2020-04-18","05:00:00","102:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen dwarsliggers en ballast in diverse sporen",null,"Y","K-006630"]
["ProRail","IO-K-006630-2003-00",".",">","Pernis","Pernis",2020,2020,20,21,"2020-05-16","07:00:00","2020-05-18","07:00:00","48:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoor, dwarsliggers en saneren wissels",null,"Y","K-006630"]
["ProRail","IO-K-006630-2009-02",".",">","Botlek","Botlek",2020,2020,22,23,"2020-05-30","19:00:00","2020-06-01","23:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen spoor, spoorstaven en overwegbevloeringen.",null,"Y","K-006630"]
["ProRail","IO-K-006630-2004-00",".",">","Pernis","Pernis",2020,2020,24,24,"2020-06-12","16:00:00","2020-06-14","04:00:00","36:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen wissel en overwegbevloering",null,"Y","K-006630"]
["ProRail","IO-K-006630-2005-00",".",">","Pernis","Pernis",2020,2020,24,25,"2020-06-14","04:00:00","2020-06-15","08:00:00","28:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen wissel 328",null,"Y","K-006630"]
["ProRail","IO-K-006630-2006-00",".",">","Botlek","Botlek",2020,2020,25,26,"2020-06-20","12:00:00","2020-06-22","07:00:00","43:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoor en wissels en saneren van een wissel",null,"Y","K-006630"]
["ProRail","IO-K-006630-2007-00",".",">","Botlek","Botlek",2020,2020,27,28,"2020-07-05","22:10:00","2020-07-08","02:10:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoor en wissels",null,"Y","K-006630"]
["ProRail","IO-K-006630-2011-01",".",">","Europoort","Europoort",2020,2020,29,29,"2020-07-18","23:00:00","2020-07-19","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen sporen, wissels en wisselliggers.",null,"Y","K-006630"]
["ProRail","IO-K-006630-2011-02",".",">","Europoort","Europoort",2020,2020,30,30,"2020-07-25","23:00:00","2020-07-26","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen sporen, wissels en wisselliggers.",null,"Y","K-006630"]
["ProRail","IO-K-006630-2011-03",".",">","Europoort","Europoort",2020,2020,31,31,"2020-08-01","23:00:00","2020-08-02","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen sporen, wissels en wisselliggers.",null,"Y","K-006630"]
["ProRail","IO-K-006630-2010-01",".","< >","Botlek","Pernis",2020,2020,39,40,"2020-09-26","23:00:00","2020-09-28","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen wissel, spoor en dwarsliggers",null,"Y","K-006630"]
["ProRail","IO-K-006630-2017-03",".","< >","Europoort","Suurhoffbrug o/h Hartelkanaal",2020,2020,39,40,"2020-09-26","23:00:00","2020-09-28","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen spoor en wissels",null,"Y","K-006630"]
["ProRail","IO-K-006630-2002-00",".",">","Waalhaven Zuid","Waalhaven Zuid aansl. Noord",2020,2020,45,46,"2020-11-08","15:00:00","2020-11-09","07:00:00","16:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen dwarsliggers en ballast",null,"N","K-006630"]
["ProRail","IO-K-006630-2001-00",".","< >","Barendrecht aansl.","Kijfhoek zuid",2020,2020,46,46,"2020-11-14","23:00:00","2020-11-15","15:00:00","16:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen dwarsliggers",null,"Y","K-006630"]
["ProRail","IO-K-006630-2010-02",".","< >","Botlek","Pernis",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen wissel, spoor en dwarsliggers",null,"Y","K-006630"]
["ProRail","IO-K-006630-2013-00",".",">","Europoort","Europoort West",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"vernieuwen sporen, wissels en wisselliggers.",null,"Y","K-006630"]
["ProRail","IO-K-006630-2017-01",".",">","Europoort","Suurhoffbrug o/h Hartelkanaal",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"vernieuwen spoor en wissels",null,"N","K-006630"]
["ProRail","IO-K-006630-2008-00",".","< >","Botlek","Botlek",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoor en overwegen",null,"Y","K-006630"]
["ProRail","IO-K-006630-2018-00",".","< >","Europoort West","Suurhoffbrug o/h Hartelkanaal",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vernieuwen wissels",null,"Y","K-006630"]
["ProRail","IO-K-006630-2014-00",".",">","Europoort","Europoort",2021,2021,20,21,"2021-05-22","23:00:00","2021-05-24","23:00:00","48:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen spoorstaven en ballast en saneren wissel 960",null,"Y","K-006630"]
["ProRail","IO-K-006631-IO01-00",".",">","Pernis","Waalhaven Zuid aansl Zuid",2020,2020,34,34,"2020-08-22","23:00:00","2020-08-23","23:00:00","24:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen dwarsliggers geo 950 sporen: -sp 473(RC) km 7.803-7.973 -sp 479AV (PC) km 7.859-8.027",null,"Y","K-006631"]
["ProRail","IO-K-006631-IO04-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,35,36,"2020-08-27","23:00:00","2020-08-31","03:00:00","76:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"verniewen wsl 670, 671, 669A/669B, 665",null,"Y","K-006631"]
["ProRail","IO-K-006631-2001-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,36,36,"2020-09-05","23:00:00","2020-09-06","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen wissel 129",null,"Y","K-006631"]
["ProRail","IO-K-006631-2002-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,38,38,"2020-09-19","23:00:00","2020-09-20","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen wissel 133",null,"Y","K-006631"]
["ProRail","IO-K-006631-IO2B-00",".","< >","Waalhaven Zuid","Waalhaven Zuid",2020,2020,41,42,"2020-10-10","07:00:00","2020-10-12","11:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"",null,null,null,"-Vernieuwen wsl 609 -Vernieuwen spoortak 609R (301B)- vern ovw bevl 609R (301B)",null,"Y","K-006631"]
["ProRail","IO-K-006631-IO09-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,46,46,"2020-11-14","23:00:00","2020-11-15","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen wsl 117",null,"Y","K-006631"]
["ProRail","IO-K-006631-IO08-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen wissel 129, 133",null,"N","K-006631"]
["ProRail","IO-K-007019-0001-00",".",">","Grote Draaibrug o/d Oude Maas - bij Dordrecht","Zwijndrecht",2020,2020,40,41,"2020-10-03","00:00:00","2020-10-05","00:00:00","48:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vervangen van de lagers van twee stuks omloopwielen van de Brug over de Oude Maas.",null,"Y","K-007019"]
["ProRail","IO-K-B17018-00pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,2,2,"2020-01-06","07:00:00","2020-01-10","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,2,2,"2020-01-06","07:00:00","2020-01-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,2,2,"2020-01-06","07:00:00","2020-01-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,2,2,"2020-01-06","07:00:00","2020-01-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-01b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,3,3,"2020-01-13","07:00:00","2020-01-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-01b2-00",".",">","Botlek","Botlek",2020,2020,3,3,"2020-01-13","07:00:00","2020-01-18","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,3,3,"2020-01-13","07:00:00","2020-01-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,3,3,"2020-01-13","07:00:00","2020-01-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,3,3,"2020-01-13","07:00:00","2020-01-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-01eu-00",".",">","Europoort","Europoort West",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-24","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-01m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-24","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-F38H-00",".",">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2020,2020,4,5,"2020-01-25","23:00:00","2020-01-27","07:00:00","32:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Uitgraven klappers bij wissels Mvtyn",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij02-00",".",">","IJsselmonde","IJsselmonde",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-24","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-01wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,5,5,"2020-01-27","07:00:00","2020-01-31","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,5,5,"2020-01-27","07:00:00","2020-02-01","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,5,5,"2020-01-27","07:00:00","2020-02-01","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,5,5,"2020-01-27","07:00:00","2020-02-01","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo02-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,5,5,"2020-01-27","07:00:00","2020-01-31","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww02-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,5,5,"2020-01-27","07:00:00","2020-01-31","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-01pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,6,6,"2020-02-03","07:00:00","2020-02-07","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,6,6,"2020-02-03","07:00:00","2020-02-08","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,6,6,"2020-02-03","07:00:00","2020-02-08","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,6,6,"2020-02-03","07:00:00","2020-02-08","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-02b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,7,7,"2020-02-10","07:00:00","2020-02-15","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-02b2-00",".",">","Botlek","Botlek",2020,2020,7,7,"2020-02-10","07:00:00","2020-02-15","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,7,7,"2020-02-10","07:00:00","2020-02-15","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,7,7,"2020-02-10","07:00:00","2020-02-15","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,7,7,"2020-02-10","07:00:00","2020-02-15","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-02eu-00",".",">","Europoort","Europoort West",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-21","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-02m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-21","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-22","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-22","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-22","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij03-00",".",">","IJsselmonde","IJsselmonde",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-21","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-02wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-28","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-29","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-29","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-29","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo03-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-28","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww03-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-28","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-02pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,10,10,"2020-03-02","07:00:00","2020-03-06","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,10,10,"2020-03-02","07:00:00","2020-03-07","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,10,10,"2020-03-02","07:00:00","2020-03-07","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,10,10,"2020-03-02","07:00:00","2020-03-07","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,11,11,"2020-03-09","07:00:00","2020-03-14","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03b2-00",".",">","Botlek","Botlek",2020,2020,11,11,"2020-03-09","07:00:00","2020-03-14","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,11,11,"2020-03-09","07:00:00","2020-03-14","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,11,11,"2020-03-09","07:00:00","2020-03-14","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,11,11,"2020-03-09","07:00:00","2020-03-14","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03eu-00",".",">","Europoort","Europoort West",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-20","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-20","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-13m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-21","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-13m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-21","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-13th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-21","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij04-00",".",">","IJsselmonde","IJsselmonde",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-20","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-27","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-14m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-28","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-14m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-28","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-14th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-28","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo04-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-27","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww04-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-27","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,14,14,"2020-03-30","07:00:00","2020-04-03","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-15m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,14,14,"2020-03-30","07:00:00","2020-04-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-15m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,14,14,"2020-03-30","07:00:00","2020-04-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-15th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,14,14,"2020-03-30","07:00:00","2020-04-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,15,15,"2020-04-06","07:00:00","2020-04-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04b2-00",".",">","Botlek","Botlek",2020,2020,15,15,"2020-04-06","07:00:00","2020-04-11","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-16m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,15,15,"2020-04-06","07:00:00","2020-04-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-16m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,15,15,"2020-04-06","07:00:00","2020-04-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-16th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,15,15,"2020-04-06","07:00:00","2020-04-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04eu-00",".",">","Europoort","Europoort West",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-17","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-17","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-17m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-17m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-17th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij05-00",".",">","IJsselmonde","IJsselmonde",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-17","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-24","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-18m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-18m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-18th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo05-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-24","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww05-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-24","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,18,18,"2020-04-27","07:00:00","2020-05-01","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-19m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,18,18,"2020-04-27","07:00:00","2020-05-02","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-19m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,18,18,"2020-04-27","07:00:00","2020-05-02","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-19th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,18,18,"2020-04-27","07:00:00","2020-05-02","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,19,19,"2020-05-04","07:00:00","2020-05-09","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05b2-00",".",">","Botlek","Botlek",2020,2020,19,19,"2020-05-04","07:00:00","2020-05-09","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-20m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,19,19,"2020-05-04","07:00:00","2020-05-09","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-20m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,19,19,"2020-05-04","07:00:00","2020-05-09","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-20th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,19,19,"2020-05-04","07:00:00","2020-05-09","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05eu-00",".",">","Europoort","Europoort West",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-15","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-15","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-21m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-16","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-21m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-16","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-21th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-16","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij06-00",".",">","IJsselmonde","IJsselmonde",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-15","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-22","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-22m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-23","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-22m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-23","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-22th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-23","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo06-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-22","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww06-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-22","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,22,22,"2020-05-25","07:00:00","2020-05-29","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-23m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,22,22,"2020-05-25","07:00:00","2020-05-30","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-23m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,22,22,"2020-05-25","07:00:00","2020-05-30","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-23th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,22,22,"2020-05-25","07:00:00","2020-05-30","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,23,23,"2020-06-01","07:00:00","2020-06-06","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06b2-00",".",">","Botlek","Botlek",2020,2020,23,23,"2020-06-01","07:00:00","2020-06-06","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-24m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,23,23,"2020-06-01","07:00:00","2020-06-06","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-24m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,23,23,"2020-06-01","07:00:00","2020-06-06","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-24th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,23,23,"2020-06-01","07:00:00","2020-06-06","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06eu-00",".",">","Europoort","Europoort West",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-12","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-12","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-25m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-13","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-25m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-13","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-25th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-13","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij07-00",".",">","IJsselmonde","IJsselmonde",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-12","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-19","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-26m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-20","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-26m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-20","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-26th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-20","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo07-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-19","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww07-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-19","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,26,26,"2020-06-22","07:00:00","2020-06-26","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-27m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,26,26,"2020-06-22","07:00:00","2020-06-27","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-27m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,26,26,"2020-06-22","07:00:00","2020-06-27","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-27th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,26,26,"2020-06-22","07:00:00","2020-06-27","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,27,27,"2020-06-29","07:00:00","2020-07-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07b2-00",".",">","Botlek","Botlek",2020,2020,27,27,"2020-06-29","07:00:00","2020-07-04","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-28m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,27,27,"2020-06-29","07:00:00","2020-07-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-28m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,27,27,"2020-06-29","07:00:00","2020-07-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-28th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,27,27,"2020-06-29","07:00:00","2020-07-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij08-00",".",">","IJsselmonde","IJsselmonde",2020,2020,28,28,"2020-07-06","07:00:00","2020-07-10","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,29,29,"2020-07-13","07:00:00","2020-07-17","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo08-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,29,29,"2020-07-13","07:00:00","2020-07-17","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww08-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,29,29,"2020-07-13","07:00:00","2020-07-17","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,30,30,"2020-07-20","07:00:00","2020-07-24","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,31,31,"2020-07-27","07:00:00","2020-08-01","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08b2-00",".",">","Botlek","Botlek",2020,2020,31,31,"2020-07-27","07:00:00","2020-08-01","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09ij-00",".",">","IJsselmonde","IJsselmonde",2020,2020,32,32,"2020-08-03","07:00:00","2020-08-07","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,33,33,"2020-08-10","07:00:00","2020-08-14","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo09-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,33,33,"2020-08-10","07:00:00","2020-08-14","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww09-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,33,33,"2020-08-10","07:00:00","2020-08-14","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,34,34,"2020-08-17","07:00:00","2020-08-21","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,35,35,"2020-08-24","07:00:00","2020-08-29","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09b2-00",".",">","Botlek","Botlek",2020,2020,35,35,"2020-08-24","07:00:00","2020-08-29","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij10-00",".",">","IJsselmonde","IJsselmonde",2020,2020,36,36,"2020-08-31","07:00:00","2020-09-04","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,37,37,"2020-09-07","07:00:00","2020-09-11","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo10-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,37,37,"2020-09-07","07:00:00","2020-09-11","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww10-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,37,37,"2020-09-07","07:00:00","2020-09-11","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,38,38,"2020-09-14","07:00:00","2020-09-18","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,39,39,"2020-09-21","07:00:00","2020-09-26","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10b2-00",".",">","Botlek","Botlek",2020,2020,39,39,"2020-09-21","07:00:00","2020-09-26","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij11-00",".",">","IJsselmonde","IJsselmonde",2020,2020,40,40,"2020-09-28","07:00:00","2020-10-02","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,41,41,"2020-10-05","07:00:00","2020-10-09","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo11-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,41,41,"2020-10-05","07:00:00","2020-10-09","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww11-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,41,41,"2020-10-05","07:00:00","2020-10-09","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,42,42,"2020-10-12","07:00:00","2020-10-16","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,43,43,"2020-10-19","07:00:00","2020-10-24","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11b2-00",".",">","Botlek","Botlek",2020,2020,43,43,"2020-10-19","07:00:00","2020-10-24","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij12-00",".",">","IJsselmonde","IJsselmonde",2020,2020,44,44,"2020-10-26","07:00:00","2020-10-30","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,45,45,"2020-11-02","07:00:00","2020-11-06","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo12-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,45,45,"2020-11-02","07:00:00","2020-11-06","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww12-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,45,45,"2020-11-02","07:00:00","2020-11-06","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,46,46,"2020-11-09","07:00:00","2020-11-13","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,47,47,"2020-11-16","07:00:00","2020-11-21","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12b2-00",".",">","Botlek","Botlek",2020,2020,47,47,"2020-11-16","07:00:00","2020-11-21","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij13-00",".",">","IJsselmonde","IJsselmonde",2020,2020,48,48,"2020-11-23","07:00:00","2020-11-27","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,49,49,"2020-11-30","07:00:00","2020-12-04","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo13-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,49,49,"2020-11-30","07:00:00","2020-12-04","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww13-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,49,49,"2020-11-30","07:00:00","2020-12-04","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,50,50,"2020-12-07","07:00:00","2020-12-11","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-l-005011-POA3-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,8,9,"2020-02-21","19:00:00","2020-02-24","05:00:00","58:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Asfalteerwerkzaamheden Vlothavenweg - Amsterdam Westhaven",null,"N","l-005011"]
["ProRail","IO-l-005011-POA4-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,9,10,"2020-02-28","19:00:00","2020-03-02","05:00:00","58:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Asfalteerwerkzaamheden Vlothavenweg - Amsterdam Westhaven",null,"N","l-005011"]
["ProRail","IO-L-005089-2103-00",".",">","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2021,2021,13,14,"2021-04-04","01:00:00","2021-04-05","05:00:00","28:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vervangen huidige Centrale buis wisselverwarming voor elektrische wisselverwarming",null,"Y","L-005089"]
["ProRail","IO-L-005092-2003-00",".",">","Amsterdam Centraal","Singelgrachtbrug",2020,2020,13,13,"2020-03-28","02:00:00","2020-03-29","00:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Uitvoeren taludverbetering",null,"Y","L-005092"]
["ProRail","IO-L-005092-2001-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,14,14,"2020-04-04","02:00:00","2020-04-05","10:00:00","32:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen schouwpaden",null,"N","L-005092"]
["ProRail","IO-L-005092-2002-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven West",2020,2020,23,23,"2020-06-07","00:00:00","2020-06-07","14:00:00","14:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen schouwpaden",null,"Y","L-005092"]
["ProRail","IO-L-005095-2010-00",".",">","Amsterdam Amstel","Watergraafsmeer Oost aansl.",2020,2020,2,2,"2020-01-11","07:00:00","2020-01-12","23:00:00","40:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"LDV balken 2/79-2/80, 2/101-2/102-2/103, 2/113-2/114+ verv balk 2/127-2/128 + noodmaatregel balk 2/92 PVE-8",null,"Y","L-005095"]
["ProRail","IO-L-005113-2002-00",".",">","Harmelen aansl.","Vleuten",2020,2020,31,32,"2020-08-02","07:00:00","2020-08-03","05:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vervangen ledseinen en matrixsignaalgever",null,"Y","L-005113"]
["ProRail","IO-L-005113-2003-00",".","< >","Harmelen aansl.","Woerden Overloop",2020,2020,50,51,"2020-12-12","02:00:00","2020-12-14","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen ledseinen en matrixsignaalgever",null,"Y","L-005113"]
["ProRail","IO-L-005121-2101-00",".","< >","Amsterdam Amstel","Watergraafsmeer West aansl.",2021,2021,2,3,"2021-01-16","02:00:00","2021-01-18","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleidingbalken portaal 3/28-3/29-3/30, portaal 3/31-3/32(-3/33)_PVE-5",null,"Y","L-005121"]
["ProRail","IO-L-005121-2103-00",".","< >","Amsterdam Centraal","Watergraafsmeer West aansl.",2021,2021,40,41,"2021-10-10","01:00:00","2021-10-11","05:00:00","28:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleidingbalk 2/129-130 en 4/7-8 Dgr_PVE-5",null,"Y","L-005121"]
["ProRail","IO-L-005121-2102-00",".","< >","Amsterdam Amstel","Duivendrecht",2021,2021,44,45,"2021-11-07","01:00:00","2021-11-08","05:00:00","28:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleidingbalken portaal 3/3-3/4, 3/11-3/12 en portaal 3/15-3/16 Dmn-Asdm_PVE-5",null,"Y","L-005121"]
["ProRail","IO-L-005124-2102-00",".","< >","Amsterdam Amstel","Watergraafsmeer West aansl.",2021,2021,2,3,"2021-01-16","01:00:00","2021-01-18","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-2",null,"Y","L-005124"]
["ProRail","IO-L-005124-2106-00",".","< >","Amsterdam Muiderpoort","Dijksgracht Westzijde (Amsterdam)",2021,2021,2,2,"2021-01-16","00:00:00","2021-01-16","20:00:00","20:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-2 deel E",null,"Y","L-005124"]
["ProRail","IO-L-005124-2104-00",".","< >","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2021,2021,40,40,"2021-10-09","01:00:00","2021-10-10","00:50:00","23:50","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-1 deel A en B",null,"Y","L-005124"]
["ProRail","IO-L-005124-2105-00",".","< >","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2021,2021,44,44,"2021-11-06","01:00:00","2021-11-07","00:50:00","23:50","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-1 deel D1",null,"Y","L-005124"]
["ProRail","IO-L-005124-2107-00",".","< >","Amsterdam Amstel","Watergraafsmeer West aansl.",2021,2021,44,44,"2021-11-06","02:00:00","2021-11-07","01:50:00","23:50","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-2 deel F",null,"Y","L-005124"]
["ProRail","IO-L-005189-2001-00",".",">","Amsterdam Transformatorweg aansl.","Amsterdam Zaanstraat",2020,2020,14,15,"2020-04-04","01:20:00","2020-04-06","05:20:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen wisselliggers en vernieuwen dwarsliggers Zaanstraat.",null,"Y","L-005189"]
["ProRail","IO-L-005189-2008-00",".",">","Abcoude","Maarssen",2020,2020,29,29,"2020-07-16","01:00:00","2020-07-17","05:00:00","28:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen dwarsliggers op diverse locaties en aanbrengen railframe",null,"Y","L-005189"]
["ProRail","IO-L-005189-2007-00",".",">","Abcoude","Maarssen",2020,2020,32,33,"2020-08-09","01:00:00","2020-08-10","05:00:00","28:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen dwarsliggers, aanbrengen railframe op diverse locaties",null,"Y","L-005189"]
["ProRail","IO-L-005189-2009-00",".",">","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2020,2020,37,38,"2020-09-12","02:00:00","2020-09-14","04:00:00","50:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen wisselliggers en ballast van diverse wissels en vernieuwen dwarsliggers en ballast in diverse sporen.",null,"Y","L-005189"]
["ProRail","IO-L-005189-2022-00",".","< >","Erasmusgracht aansl.","Amsterdam Sloterdijk",2020,2020,40,40,"2020-10-03","02:00:00","2020-10-04","18:00:00","40:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen spoorstaven en dwarsliggers.",null,"Y","L-005189"]
["ProRail","IO-L-005189-2016-00",".","< >","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2020,2020,42,43,"2020-10-17","02:00:00","2020-10-19","06:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen dwarsliggers,blokjesspoor, compensatielassen en spoorstaven",null,"Y","L-005189"]
["ProRail","IO-L-005189-2012-00",".",">","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2020,2020,49,50,"2020-12-05","02:00:00","2020-12-07","04:00:00","50:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen wisselliggers en ballast van diverse wissels en dwarsliggers en ballast in diverse sporen vernieuwen.",null,"Y","L-005189"]
["ProRail","IO-L-005189-2019-00",".","< >","Erasmusgracht aansl.","Zaandam",2021,2021,5,6,"2021-02-06","02:20:00","2021-02-08","05:20:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen dwarsliggers en spoorstaven in diverse sporen",null,"Y","L-005189"]
["ProRail","IO-L-005191-2004-00",".",">","Harmelen aansl.","Vleuten",2020,2020,37,38,"2020-09-12","01:00:00","2020-09-14","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"Vernieuwen regelbare sps bev en verwijderen CL rondom kunstwerk",null,"Y","L-005191"]
["ProRail","IO-L-005211-2104-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2021,2021,13,14,"2021-04-04","01:00:00","2021-04-06","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoorstaven ballast en dwarsliggers spoor 8812, 8813,8815,4225,4540,4742,4645 spoorbegrenzers, wissel 49 en bediening wissel 91 en 39, saneren wissel 93, vernieuwen wissels 102A/B,118,87,89.",null,"Y","L-005211"]
["ProRail","IO-L-005211-2107-00",".","< >","Houtrakpolder (Amsterdam)","Houtrakpolder aansl.(Amsterdam)",2021,2021,27,27,"2021-07-05","07:00:00","2021-07-09","07:00:00","96:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vernieuwen wissels 115, 106 en 112 en ballast spoor 5250 en 5350 Vernieuwen wissels 109, ballast spoor 5165 en 5454, spoorstaven spoor 5165, 5252 en 5454 en spoortak spoor 5165 en 5352",null,"Y","L-005211"]
["ProRail","IO-L-005211-2103-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2021,2021,34,34,"2021-08-23","00:00:00","2021-08-25","04:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoorstaven en dwarsliggers spoor 6101, 6103 en 6203 en wissel 19",null,"N","L-005211"]
["ProRail","IO-L-005211-2108-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2021,2021,34,34,"2021-08-23","00:00:00","2021-08-26","04:00:00","76:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen sporen wissels en overwegen",null,"Y","L-005211"]
["ProRail","IO-L-005211-2102-00",".","< >","Amsterdam Sloterdijk","Spaarnebrug - bij Haarlem",2021,2021,40,41,"2021-10-09","01:35:00","2021-10-11","05:35:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen spoorstaven en dwarsliggers spoor SJ en spoorstaven spoor 602",null,"Y","L-005211"]
["ProRail","IO-L-005231-2001-00",".","< >","Oudewater overloopw.","Woerden Overloop",2020,2020,37,38,"2020-09-12","02:00:00","2020-09-14","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Aanleggen RIP KM 21.200 dubbelsporig",null,"Y","L-005231"]
["ProRail","IO-L-005233-2001-00",".","< >","Erasmusgracht aansl.","Amsterdam Sloterdijk",2020,2020,40,41,"2020-10-03","02:00:00","2020-10-05","04:00:00","50:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Herstellen betonschade opstortblokken van viaduct te Amsterdam Sloterdijk.",null,"Y","L-005233"]
["ProRail","IO-M-004551-2105-00",".","< >","Roosendaal grens","Roosendaal grens",2021,2021,10,11,"2021-03-13","01:00:00","2021-03-15","05:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"R",null,null,null,"BBV Rsd",null,"Y","M-004551"]
["ProRail","IO-M-004551-2104-00",".","< >","Roosendaal grens","Roosendaal grens",2021,2021,20,21,"2021-05-22","01:00:00","2021-05-25","05:00:00","76:00","continuous","Miscellaneous","T","ST",null,null,null,null,"R",null,null,null,"BBV Rsd",null,"Y","M-004551"]
["ProRail","IO-M-004551-2101-00",".","< >","Markbrug - tussen Zevenbergen en Oudenbosch","Zevenbergen inhaalsp.",2021,2021,29,32,"2021-07-24","01:25:00","2021-08-09","05:25:00","388:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"PSS + BBV",null,"Y","M-004551"]
["ProRail","IO-M-004551-2106-00",".","< >","Bergen op Zoom","Roosendaal",2021,2021,39,40,"2021-10-02","03:00:00","2021-10-04","03:00:00","48:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"BBV Rsd",null,"Y","M-004551"]
["ProRail","IO-R-2AE001-2102-00",".",">","Amsterdam Amstel","Duivendrecht",2021,2021,2,3,"2021-01-16","01:00:00","2021-01-18","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afbouw nieuw stijgpunt met tunnel in het eerste perron van station Amsterdam Amstel",null,"Y","R-2AE001"]
["ProRail","IO-R-3AE001-2106-00",".",">","Amsterdam Centraal","Singelgracht aansl.",2021,2021,5,6,"2021-02-06","01:00:00","2021-02-08","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Tijdelijk wegnemen van sporen en/of perrondelen voor bouwkundig onderzoek naar de onderliggende constructie.",null,"Y","R-3AE001"]
["ProRail","IO-R-3AE001-2107-00",".",">","Amsterdam Centraal","Amsterdam Centraal",2021,2021,11,12,"2021-03-20","01:00:00","2021-03-22","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Tijdelijk wegnemen van sporen en/of perrondelen voor bouwkundig onderzoek naar de onderliggende constructie.",null,"N","R-3AE001"]
["ProRail","IO-R-3AE001-2109-00",".",">","Amsterdam Centraal","Singelgracht aansl.",2021,2021,15,16,"2021-04-17","01:00:00","2021-04-19","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Aanpassen IJ-Tram Kunstwerk",null,"Y","R-3AE001"]
["ProRail","IO-R-3AE001-2101-00",".",">","Amsterdam Centraal","Amsterdam Centraal",2021,2021,37,38,"2021-09-18","01:00:00","2021-09-20","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Verstevigen IJ-Tram kunstwerk",null,"N","R-3AE001"]
["ProRail","IO-R-3AE001-2108-00",".",">","Amsterdam Centraal","Amsterdam Centraal",2021,2021,39,40,"2021-10-02","01:00:00","2021-10-04","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Tijdelijk wegnemen van sporen en/of perrondelen voor bouwkundig onderzoek naar de onderliggende constructie.",null,"N","R-3AE001"]
["ProRail","IO-R-3AE001-2103-00",".","< >","Amsterdam Amstel","Amsterdam Zaanstraat",2021,2021,40,41,"2021-10-09","01:00:00","2021-10-11","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Leeghalen Dijksgracht",null,"Y","R-3AE001"]
["ProRail","IO-R-3AE001-2104-00",".","< >","Amsterdam Amstel","Amsterdam Zaanstraat",2021,2021,44,45,"2021-11-06","01:00:00","2021-11-08","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Saneren wissels 1e perronbak.",null,"Y","R-3AE001"]
["ProRail","IO-R-3AE001-2102-00",".",">","Amsterdam Centraal","Singelgracht aansl.",2021,2021,45,46,"2021-11-13","01:00:00","2021-11-15","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Aanpassen IJ-Tram Kunstwerk",null,"Y","R-3AE001"]
["ProRail","IO-R-3AE009-2001-00",".",">","Amsterdam Transformatorweg aansl.","Amsterdam Zaanstraat",2020,2020,14,15,"2020-04-04","01:20:00","2020-04-06","05:20:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Diverse werkzaamheden Westhaven Amsterdam. Verwijzing van de werkzaamheden, zie TVP aanvraagformulier 1.",null,"Y","R-3AE009"]
["ProRail","IO-R-3AE009-2016-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,14,14,"2020-04-01","08:00:00","2020-04-04","01:00:00","65:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Verlengen Spoor 2264 en verplaatsen inrit.",null,"N","R-3AE009"]
["ProRail","IO-R-3AE009-2017-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,15,20,"2020-04-06","07:00:00","2020-05-11","07:00:00","840:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Voorbereidende werkzaamheden voor het verplaatsen Loc/Opstel Sporen.",null,"N","R-3AE009"]
["ProRail","IO-R-3AE009-2018-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,20,23,"2020-05-11","07:00:00","2020-06-06","01:00:00","618:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Voorbereidende werkzaamheden voor het verplaatsen Loc/Opstel Sporen.",null,"N","R-3AE009"]
["ProRail","IO-R-3AE011-2101-00",".","< >","Amsterdam Sloterdijk","Singelgracht aansl.",2021,2021,40,41,"2021-10-09","01:35:00","2021-10-11","05:35:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Perron verlenging Amsterdam zijde (optioneel inkortte perron andere zijde) Verwijderen van OTC's Aanpassen bovenleiding",null,"Y","R-3AE011"]
["ProRail","IO-R-3AE011-2102-00",".","< >","Amsterdam Sloterdijk","Singelgracht aansl.",2021,2021,44,45,"2021-11-06","05:35:00","2021-11-08","05:35:00","48:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Bouwstap aannemer, Aanbrengen RH - Wissels - Kabelkruizingen",null,"Y","R-3AE011"]
["ProRail","IO-R-3AE011-2103-00",".","< >","Amsterdam Sloterdijk","Singelgracht aansl.",2022,2022,18,19,"2022-05-07","00:00:00","2022-05-09","04:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Eulynx voorbereidingen, plaatsen objectcontrolers en realiseren glasvezelnetwerk. Eventueel al een gedeeltelijke voortest.",null,"Y","R-3AE011"]
["ProRail","IO-R-403700-2099-00",".",">","Botlek","Waalhaven Zuid aansl Zuid",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Indienststellen nieuwe Botlekbrug (stap 200 )",null,"Y","R-403700"]
["ProRail","IO-R-403700-2051-00",".",">","Botlek","Pernis",2020,2020,47,47,"2020-11-21","15:00:00","2020-11-22","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"N","R-403700"]
["ProRail","IO-R-403700-2052-00",".",">","Botlek","Pernis",2020,2020,48,48,"2020-11-28","15:00:00","2020-11-29","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-403700-2053-00",".",">","Botlek","Pernis",2020,2020,50,50,"2020-12-12","15:00:00","2020-12-13","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"N","R-403700"]
["ProRail","IO-R-403700-2154-00",".",">","Botlek","Pernis",2021,2021,1,1,"2021-01-09","15:00:00","2021-01-10","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-403700-2155-00",".",">","Botlek","Pernis",2021,2021,3,3,"2021-01-23","15:00:00","2021-01-24","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-403700-2156-00",".",">","Botlek","Pernis",2021,2021,4,4,"2021-01-30","15:00:00","2021-01-31","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-403700-2157-00",".",">","Botlek","Pernis",2021,2021,6,6,"2021-02-13","15:00:00","2021-02-14","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-403700-2158-00",".",">","Botlek","Pernis",2021,2021,7,7,"2021-02-20","15:00:00","2021-02-21","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-403700-2159-00",".",">","Botlek","Pernis",2021,2021,9,9,"2021-03-06","15:00:00","2021-03-07","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-403700-2160-00",".",">","Botlek","Pernis",2021,2021,10,10,"2021-03-13","15:00:00","2021-03-14","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-403700-2101-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Indienststellen nieuwe Botlekbrug (stap 200 )",null,"Y","R-403700"]
["ProRail","IO-R-404600-1970-00",".",">","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2020,2020,11,12,"2020-03-14","01:00:00","2020-03-16","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"upgrade Rotterdam Noord",null,"N","R-404600"]
["ProRail","IO-R-465700-IO01-00",".",">","Rail Service Center Waalhaven","Rail Service Center Waalhaven aansl.",2020,2020,18,19,"2020-05-02","15:00:00","2020-05-04","15:00:00","48:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Westzijde RSC terminal sp 401/402 aanpassen door verplaatsen wsl 803A/803B naar het oosten, meer info zie werkplek A",null,"Y","R-465700"]
["ProRail","IO-R-474300-2002-00",".","< >","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2020,2020,47,49,"2020-11-21","00:00:00","2020-11-30","00:00:00","216:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Wijzigen en testen EBS i.v.m. goederen overdrachtspoor",null,"Y","R-474300"]
["ProRail","IO-R-474300-2101-00",".","< >","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2021,2021,28,30,"2021-07-17","01:00:00","2021-07-26","01:00:00","216:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Wijzigen en testen EBS i.v.m. goederen overdrachtspoor",null,"Y","R-474300"]
["ProRail","IO-R-485000.01-Hbg1-00",".","< >","Erasmusgracht aansl.","Radarweg aansl.",2021,2021,5,6,"2021-02-06","02:00:00","2021-02-08","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Ass Hemboog spoorwerk, lichten-schiften, reguleren Bvl Sporen 9 en 10",null,"Y","R-485000.01"]
["ProRail","IO-R-485000.01-Hbg2-00",".","< >","Erasmusgracht aansl.","Radarweg aansl.",2021,2021,35,36,"2021-09-04","02:00:00","2021-09-06","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Ass Hemboog spoorwerk, lichten-schiften, reguleren Bvl Sporen 9 en 10",null,"Y","R-485000.01"]
["ProRail","IO-R-485000.02-Rt01-00",".",">","Rotterdam Centraal","Rotterdam Centraal",2021,2021,15,16,"2021-04-17","01:15:00","2021-04-19","05:15:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"spoor op hoogte P76 brengen",null,"Y","R-485000.02"]
["ProRail","IO-R-485000.02-Rt02-00",".",">","Rotterdam Centraal","Rotterdam Centraal",2021,2021,17,18,"2021-05-01","01:05:00","2021-05-03","05:05:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"spoor op hoogte P76 brengen",null,"Y","R-485000.02"]
["ProRail","IO-R-485000.02-Rt03-00",".",">","Rotterdam Centraal","Rotterdam Centraal",2021,2021,19,20,"2021-05-15","01:15:00","2021-05-17","05:15:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"spoor op hoogte P76 brengen",null,"Y","R-485000.02"]
["ProRail","IO-R-485000.02-Rt04-00",".",">","Rotterdam Centraal","Rotterdam Centraal",2021,2021,21,22,"2021-05-29","02:00:00","2021-05-31","06:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"spoor op hoogte P76 brengen",null,"Y","R-485000.02"]
["ProRail","IO-R-485000.02-Rt05-00",".",">","Rotterdam Centraal","Rotterdam Centraal",2021,2021,23,24,"2021-06-12","01:05:00","2021-06-14","05:05:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"spoor op hoogte P76 brengen",null,"Y","R-485000.02"]
["ProRail","IO-R-493300-1961-00",".",">","Gouda","Moordrecht aansl.",2020,2020,37,38,"2020-09-12","00:00:00","2020-09-14","04:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Bouw van een nieuw service- en opstelterrein voor de treindienst Gd-Apn",null,"Y","R-493300"]
["ProRail","IO-R-493300-1963-00",".",">","Gouda","Gouda",2020,2020,37,43,"2020-09-07","08:00:00","2020-10-19","08:00:00","1008:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Bouw van een nieuw service- en opstelterrein voor de treindienst Gd-Apn",null,"Y","R-493300"]
["ProRail","IO-R-493300-1962-00",".",">","Gouda","Moordrecht aansl.",2020,2020,41,42,"2020-10-10","00:00:00","2020-10-12","04:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Bouw van een nieuw service- en opstelterrein voor de treindienst Gd-Apn",null,"Y","R-493300"]
["ProRail","IO-R-497500-2007-00",".",">","Botlek racc.Theemsweg","Botlek Theemsweg aansl.",2020,2020,8,9,"2020-02-22","23:00:00","2020-02-25","03:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Werkzaamheden onderbouw aannemer (Save). Aanbrengen damwanden en fundaties. Zo nodig spooronderhoud.",null,"N","R-497500"]
["ProRail","IO-R-497500-2009-00",".",">","Botlek racc.Theemsweg","Botlek Theemsweg aansl.",2020,2020,14,15,"2020-04-04","01:00:00","2020-04-06","09:00:00","56:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Werkzaamheden onderbouw aannemer (Save). Aanbrengen damwanden en fundaties. Zo nodig spooronderhoud.",null,"N","R-497500"]
["ProRail","IO-R-497500-2011-00",".",">","Botlek racc.Theemsweg","Botlek Theemsweg aansl.",2020,2020,44,44,"2020-10-31","12:00:00","2020-11-01","20:00:00","32:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Werkzaamheden onderbouw aannemer (Save). Aanbrengen damwanden en fundaties. Zo nodig spooronderhoud.",null,"Y","R-497500"]
["ProRail","IO-R-497500-2004-00",".","< >","Botlek racc.Theemsweg","Europoort",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Werkzaamheden aan / tbv de onderbouw van het nieuwe Theemswegtracé.",null,"Y","R-497500"]
["ProRail","IO-R-497500-2102-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-497500-2101-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,20,21,"2021-05-22","19:00:00","2021-05-24","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-497500-2103-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,36,37,"2021-09-11","23:00:00","2021-09-13","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-497500-2104-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,39,40,"2021-10-02","23:00:00","2021-10-04","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-497500-2105-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,44,45,"2021-11-02","05:00:00","2021-11-08","05:00:00","144:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-505000-EV02-00",".",">","Dordrecht","Zwijndrecht",2020,2020,15,16,"2020-04-11","01:00:00","2020-04-13","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"Saneren kruiswissel 1195A/B-1197A/B te Dordrecht Saneren wisseloverlopen 1335A/B en 1347A/B",null,"Y","R-505000"]
["ProRail","IO-R-520045-2013-00",".",">","Oudenbosch","Oudenbosch",2020,2020,13,13,"2020-03-28","00:00:00","2020-03-28","22:00:00","22:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Aanpassen overweg 15.4 binnen bevloering",null,"N","R-520045"]
["ProRail","IO-R-523400-2002-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,39,40,"2020-09-26","23:00:00","2020-09-28","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Bouw kunstwerken over spoor tbv aanleg CER.",null,"Y","R-523400"]
["ProRail","IO-R-523400-2006-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"- Saneren Overweg 300.3 - Saneren Overweg 303.5 - Nieuwe wegaansluiting overweg 3.2",null,"Y","R-523400"]
["ProRail","IO-R-523400-2101-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"- Saneren Overweg 300.3 - Saneren Overweg 303.5",null,"Y","R-523400"]
["ProRail","IO-R-539100-2001-00",".",">","Gouda","Gouda",2020,2020,14,15,"2020-04-05","00:00:00","2020-04-06","00:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"aanbrengen zettingsvrije plaat.",null,"N","R-539100"]
["ProRail","IO-R-546200-2101-01",".","< >","Europoort West","Maasvlakte aansl.",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"weggedeelte suurhofbrug vervangen",null,"Y","R-546200"]
["ProRail","IO-R-546200-2101-02",".","< >","Europoort West","Maasvlakte aansl.",2021,2021,20,21,"2021-05-22","19:00:00","2021-05-24","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"weggedeelte suurhofbrug vervangen",null,"Y","R-546200"]
["ProRail","IO-R-550080-2001-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2020,2020,40,41,"2020-10-03","19:00:00","2020-10-05","05:00:00","34:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Plaatsen van damwanden.",null,"Y","R-550080"]
["ProRail","IO-R-550080-TAC1-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2021,2021,13,14,"2021-04-04","00:55:00","2021-04-06","04:55:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Plaatsen van damwanden.",null,"Y","R-550080"]
["ProRail","IO-R-550080-TAC2-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2021,2021,23,23,"2021-06-07","01:15:00","2021-06-11","05:15:00","100:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Plaatsen van onderdoorgang, zeer sterke voorkeur voor pasen ivm andere planning",null,"Y","R-550080"]
["ProRail","IO-R-552700-2101-00",".","< >","Moerdijk","Lage Zwaluwe",2021,2021,13,14,"2021-04-04","01:00:00","2021-04-05","05:00:00","28:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Bouwen van een overweg",null,"Y","R-552700"]
["ProRail","IO-R-FI0000-1994-00",".",">","Gouda","Moordrecht overloopw.",2020,2020,10,11,"2020-03-07","01:00:00","2020-03-09","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"bouwen fietsenstalling",null,"Y","R-FI0000"]
["ProRail","IO-Z-180000-2003-00",".","< >","Breda aansl.","Roosendaal racc. Philips",2020,2020,43,43,"2020-10-24","05:00:00","2020-10-25","04:00:00","24:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen Dateq voor DOSS",null,"Y","Z-180000"]
["ProRail","IO-Z-180001-1901-00",".","< >","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,46,47,"2020-11-14","00:00:00","2020-11-16","03:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"aanpassing besturings systeem Willemsspoortunnel",null,"Y","Z-180001"]
["ProRail","IO-Z-906057-RSD3-02",".",">","Roosendaal","Roosendaal",2020,2020,5,6,"2020-02-01","01:20:00","2020-02-03","05:20:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden van perron 4",null,"Y","Z-906057"]
["ProRail","IO-Z-906057-RSD3-01",".",">","Roosendaal","Roosendaal",2020,2020,10,11,"2020-03-07","01:20:00","2020-03-09","05:20:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden van perron 4",null,"Y","Z-906057"]
["ProRail","IO-Z-906057-RSD2-01",".",">","Roosendaal","Roosendaal",2020,2020,17,18,"2020-04-25","01:10:00","2020-04-27","05:10:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden van perron 3",null,"Y","Z-906057"]
["ProRail","IO-Z-906057-RSD1-02",".",">","Roosendaal","Roosendaal",2020,2020,37,38,"2020-09-12","01:00:00","2020-09-14","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden",null,"Y","Z-906057"]
["ProRail","IO-Z-906057-RSD2-02",".",">","Roosendaal","Roosendaal",2020,2020,38,39,"2020-09-19","01:00:00","2020-09-21","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden van perron 3",null,"Y","Z-906057"]
["ProRail","IO-Z-906057-RSD1-01",".",">","Roosendaal","Roosendaal",2020,2020,41,42,"2020-10-10","01:00:00","2020-10-12","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden",null,"Y","Z-906057"]
["ProRail","IO-Z-906096-wd01-00",".","< >","Woerden","Woerden Overloop",2020,2020,37,38,"2020-09-12","02:00:00","2020-09-14","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Conserveren traverse.",null,"Y","Z-906096"]
["ProRail","IO-Z-906096-ass1-00",".","< >","Erasmusgracht aansl.","Amsterdam Sloterdijk",2020,2020,40,41,"2020-10-03","00:00:00","2020-10-05","02:00:00","50:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Conserveren hout- en staalwerk tubes perron sp 11-12",null,"Y","Z-906096"]
["ProRail","IO-Z-906096-2119-00",".",">","Breukelen aansluiting","Maarssen",2021,2021,17,18,"2021-05-01","01:00:00","2021-05-04","05:00:00","76:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Schilderen staalconstructie en dakbeschot perronkap station Maarssen",null,"Y","Z-906096"]
["ProRail","IO-Z-906106-LZ02-01",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,29,30,"2021-07-24","01:25:00","2021-07-26","05:25:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-Z-906106-LZ02-02",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,30,31,"2021-07-31","01:25:00","2021-08-02","05:25:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-Z-906106-LZ03-01",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,34,35,"2021-08-28","01:30:00","2021-08-30","05:30:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-Z-906106-LZ03-02",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,38,39,"2021-09-25","01:30:00","2021-09-27","05:30:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-Z-906107-2102-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2021,2021,9,10,"2021-03-06","01:20:00","2021-03-08","04:20:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"vervangen liften Blaak",null,"Y","Z-906107"]
["ProRail","IO-Z-906107-2101-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2021,2021,13,14,"2021-04-03","01:20:00","2021-04-05","04:20:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"vervangen liften Blaak",null,"Y","Z-906107"]
["ProRail","IO-Z-906107-DVD2-00",".","< >","Duivendrecht aansluiting west","Venserpolder aansl.",2021,2021,37,38,"2021-09-18","02:15:00","2021-09-20","05:15:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen roltrap nivo 1-2. Aanvoeren en afvoeren roltrappen via spoor Gdpa-Asra op nivo 1.",null,"Y","Z-906107"]
["ProRail","IO-Z-906107-DVD5-00",".","< >","Duivendrecht aansluiting west","Venserpolder aansl.",2021,2021,42,43,"2021-10-23","02:15:00","2021-10-25","05:15:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen roltrap nivo 1-2.",null,"Y","Z-906107"]
["ProRail","IO-Z-906237-ddr1-00",".",">","Dordrecht","Dordrecht",2020,2020,31,32,"2020-08-01","01:00:00","2020-08-03","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vervangen dakbedekking, bakgoten en verrot dakbeschot van de perronkap tussen spoor 2 en 3 te Dordrecht.",null,"Y","Z-906237"]
["ProRail","IO-Z-906237-ddr2-00",".",">","Dordrecht","Dordrecht",2020,2020,33,33,"2020-08-10","01:00:00","2020-08-12","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vervangen dakbedekking, bakgoten en verrot dakbeschot van de perronkap tussen spoor 2 en 3 te Dordrecht.",null,"Y","Z-906237"]
["ProRail","IO-Z-906237-2101-00",".",">","Dordrecht","Dordrecht",2021,2021,34,35,"2021-08-28","00:00:00","2021-08-30","04:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vervangen dakbedekking, bakgoten en verrot dakbeschot van de perronkap tussen spoor 2 en 3 te Dordrecht.",null,"Y","Z-906237"]
["ProRail","IO-Z-906237-2102-00",".",">","Dordrecht","Dordrecht",2021,2021,38,39,"2021-09-25","00:00:00","2021-09-27","04:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vervangen dakbedekking, bakgoten en verrot dakbeschot van de perronkap tussen spoor 2 en 3 te Dordrecht.",null,"Y","Z-906237"]
["ProRail","IO-Z-906310-I200-00",".",">","Roosendaal","Roosendaal",2020,2020,5,5,"2020-01-27","08:00:00","2020-01-31","16:00:00","104:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Oversteken van materieel en materiaal naar perron 2 t.b.v. renovatie werkzaamheden van Abri's, wachtruimtes e.d..",null,"N","Z-906310"]
["ProRail","IO-Z-906310-I201-00",".",">","Roosendaal","Roosendaal",2020,2020,6,6,"2020-02-03","08:00:00","2020-02-07","16:00:00","104:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Oversteken van materieel en materiaal naar perron 2 t.b.v. renovatie werkzaamheden van Abri's, wachtruimtes e.d..",null,"N","Z-906310"]
[null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]

{"sheet":"Infrabel","index":3,"n_rows":711,"n_cols":31,"rows_kept":711,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["Infrabel","10281","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2021,2021,43,46,"2021-10-22",43810.958333333336,"2021-11-08",43810.208333333336,"17d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9 \n ",null,null,10281]
["Infrabel","30557","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,26,29,"2022-06-25",43810.958333333336,"2022-07-10",43810.208333333336,"15d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"CTL pour la pose du second tablier sur les ponts 10 et 11 \n ",null,null,30557]
["Infrabel","16116","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2020,2021,45,10,"2020-11-06",43810.958333333336,"2021-03-01",43810.208333333336,"115d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.3 : Mise en service nouveau tracé L165/1 \nproposition détournement via SNCF (L165/2) ou tête à queue à Athus",null,null,16116]
["Infrabel","16118","Athus - Meuse",">","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,20,24,"2021-05-14",43810.958333333336,"2021-06-07",43810.208333333336,"24d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.5 : Pose AS sur VA de L165/2. ",null,null,16118]
["Infrabel","22224","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2021,2021,9,10,"2021-02-26",43810.958333333336,"2021-03-01",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.3 : Electrification L165/1 ",null,null,22224]
["Infrabel","22225","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2021,2021,8,9,"2021-02-19",43810.958333333336,"2021-02-22",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.3 : Electrification L165/1",null,null,22225]
["Infrabel","22226","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2021,2021,11,12,"2021-03-12",43810.958333333336,"2021-03-15",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.4 : Désélectrification L167 ",null,null,22226]
["Infrabel","22227","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2021,2021,10,11,"2021-03-05",43810.958333333336,"2021-03-08",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.4 : Désélectrification L167",null,null,22227]
["Infrabel","22228","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2021,2021,16,17,"2021-04-16",43810.958333333336,"2021-04-19",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.4 : électrification L167",null,null,22228]
["Infrabel","22231","Athus - Meuse","< >","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,20,21,"2021-05-14",43810.958333333336,"2021-05-17",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.5 : désélectrification L165/2",null,null,22231]
["Infrabel","22232","Athus - Meuse","< >","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,23,24,"2021-06-04",43810.958333333336,"2021-06-07",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.5 : électrification L165/2 ",null,null,22232]
["Infrabel","22233","Athus - Meuse","< >","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,22,23,"2021-05-28",43810.958333333336,"2021-05-31",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.5 : électrification L165/2",null,null,22233]
["Infrabel","26987","Athus - Meuse",">","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,31,33,"2021-07-26",43810.958333333336,"2021-08-09",43810.208333333336,"14d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.6 : Pose AS sur VB de L165/2",null,null,26987]
["Infrabel","26988","Athus - Meuse","< >","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,32,33,"2021-08-07",43810.958333333336,"2021-08-08",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.6 : Pose AS sur VB de L165/2",null,null,26988]
["Infrabel","10355","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,14,17,"2021-04-03",43810.25,"2021-04-19",43810.166666666664,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nTrafic HKM à détourner",null,null,10355]
["Infrabel","20460","Namur - Antwerpen","< >","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,7,9,"2021-02-12",43810.989583333336,"2021-02-22",43810.166666666664,"10d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER CTL : \r\n+ assainissement de plateformess \r\n+ pose 5 AW\r\n+ Ripage\r\n+ tvx CAT & sign\r\n+ renovation pont (av des Combattants)",null,null,20460]
["Infrabel","29278","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2022,2022,34,37,"2022-08-20",43810.333333333336,"2022-09-05",43810.25,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses avec train P93\r\nRenouvellement PI",null,null,29278]
["Infrabel","29293","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,37,37,"2022-09-09",44061.333333333336,"2022-09-09",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,29293]
["Infrabel","30903","Athus - Meuse",">","VIRTON","AUBANGE",2022,2022,37,40,"2022-09-09",44061.333333333336,"2022-09-26",44061.666666666664,"17d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,30903]
["Infrabel","35126","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,37,38,"2022-09-10",44061.25,"2022-09-12",44061.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35126]
["Infrabel","35120","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,38,38,"2022-09-16",44061.25,"2022-09-16",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35120]
["Infrabel","35127","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,38,39,"2022-09-17",44061.25,"2022-09-19",44061.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35127]
["Infrabel","35121","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,39,39,"2022-09-23",44061.25,"2022-09-23",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35121]
["Infrabel","35128","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,39,40,"2022-09-24",44061.25,"2022-09-26",44061.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35128]
["Infrabel","29295","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,41,41,"2022-10-07",44061.333333333336,"2022-10-07",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage + tx finitions \n ",null,null,29295]
["Infrabel","35130","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,41,42,"2022-10-08",44061.25,"2022-10-10",44061.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35130]
["Infrabel","30904","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,42,42,"2022-10-14",44061.333333333336,"2022-10-14",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage + tx finitions \n ",null,null,30904]
["Infrabel","35131","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,42,43,"2022-10-15",44061.583333333336,"2022-10-17",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35131]
["Infrabel","30905","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,43,43,"2022-10-17",44061.333333333336,"2022-10-17",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage + tx finitions \n ",null,null,30905]
["Infrabel","35122","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,43,43,"2022-10-21",44061.333333333336,"2022-10-21",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage + tx finitions \n ",null,null,35122]
["Infrabel","35132","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,43,44,"2022-10-22",44061.583333333336,"2022-10-24",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35132]
["Infrabel","35124","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,44,44,"2022-10-24",44061.333333333336,"2022-10-24",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage + tx finitions \n ",null,null,35124]
["Infrabel","35125","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,44,44,"2022-10-28",44061.333333333336,"2022-10-28",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage + tx finitions \n ",null,null,35125]
["Infrabel","35133","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,44,45,"2022-10-29",44061.583333333336,"2022-10-31",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35133]
["Infrabel","29949","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,37,37,"2022-09-09",44061.333333333336,"2022-09-09",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,29949]
["Infrabel","30908","Athus - Meuse",">","GEDINNE","PALISEUL",2022,2022,37,40,"2022-09-09",44061.333333333336,"2022-09-26",44061.666666666664,"17d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,30908]
["Infrabel","35134","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,37,38,"2022-09-10",44061.25,"2022-09-12",44061.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35134]
["Infrabel","35135","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,38,38,"2022-09-16",44061.333333333336,"2022-09-16",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35135]
["Infrabel","35136","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,38,39,"2022-09-17",44061.25,"2022-09-19",44061.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35136]
["Infrabel","35137","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,39,39,"2022-09-23",44061.333333333336,"2022-09-23",44061.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35137]
["Infrabel","35138","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,39,40,"2022-09-24",44061.25,"2022-09-26",44061.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35138]
["Infrabel","29953","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,41,42,"2022-10-08",44061.583333333336,"2022-10-10",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,29953]
["Infrabel","29955","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,42,43,"2022-10-15",44061.583333333336,"2022-10-17",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,29955]
["Infrabel","35139","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,43,44,"2022-10-22",44061.583333333336,"2022-10-24",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35139]
["Infrabel","26709","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,2,2,"2021-01-05",44061.010416666664,"2021-01-08",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg\r\n\r\n27/05/20 Aangepast voor Lichtfestival Gent \n ",null,null,26709]
["Infrabel","33971","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2021,2021,2,2,"2021-01-05",44061.010416666664,"2021-01-08",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud\r\n\r\n27/05/20 Aangepast voor Lichtfestival Gent \n ",null,null,33971]
["Infrabel","33976","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,2,2,"2021-01-05",44061.010416666664,"2021-01-08",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud\r\n\r\n27/05/20 Aangepast voor Lichtfestival Gent \n ",null,null,33976]
["Infrabel","34002","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,2,2,"2021-01-05",44061.003472222219,"2021-01-08",44061.180555555555,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud\r\n\r\n27/05/20 Aangepast voor Lichtfestival Gent \n ",null,null,34002]
["Infrabel","32474","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,2,2,"2021-01-09",44061.010416666664,"2021-01-09",44061.21875,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg\r\n\r\n27/05/20 Aangepast voor Lichtfestival Gent \n ",null,null,32474]
["Infrabel","34097","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,2,2,"2021-01-09",44061.010416666664,"2021-01-09",44061.21875,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud\r\n\r\n27/05/20 Aangepast voor Lichtfestival Gent \n ",null,null,34097]
["Infrabel","34098","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2021,2021,2,2,"2021-01-09",44061.010416666664,"2021-01-09",44061.21875,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud\r\n\r\n27/05/20 Aangepast voor Lichtfestival Gent \n ",null,null,34098]
["Infrabel","26454","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,3,7,"2021-01-10",44061.951388888891,"2021-02-13",44061.229166666664,"34d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"RER : \r\nSAVU DE NUIT en semaine 22:50-05:30\r\net CTL nuit les weekend samedi a dimanche 00:30-05:30 (blanc travaux)\r\nTravaux préparatoires de la renovation de la Y.LLN \n",null,null,26454]
["Infrabel","21104","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,3,3,"2021-01-11",44061.958333333336,"2021-01-15",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PS 51.035 et du pont du canal - Travaux SPW \n ",null,null,21104]
["Infrabel","22563","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,3,3,"2021-01-11",44061.958333333336,"2021-01-16",44061.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk. \n ",null,null,22563]
["Infrabel","24784","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,3,3,"2021-01-12",44061.010416666664,"2021-01-15",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,24784]
["Infrabel","26414","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,3,4,"2021-01-16",44061.25,"2021-01-17",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52 \n ",null,null,26414]
["Infrabel","24600","Lille - Charleroi","< >","Y.FAMILLEUREUX","LUTTRE",2021,2021,3,4,"2021-01-16",44061.25,"2021-01-17",44061.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Préparation MES EBP/PLP\r\nCV jade\r\n+ Préparation chantier Manage \n ",null,null,24600]
["Infrabel","30996","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,4,4,"2021-01-18",44061.958333333336,"2021-01-23",44061.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk. \n ",null,null,30996]
["Infrabel","31456","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2021,2021,4,5,"2021-01-21",44061.979166666664,"2021-01-24",44061.1875,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z7. 51   P3 HKV \r\n\r\nDétails car sur plusieurs lignes:\r\nL130A\tVoie B\tMarchienne-au-Pont\tCharleroi-Sud\tCX-K. 20\tK-G. 20\r\nL124A\tVoie B\t\t\tRX-F. 20\tI-G. 20\r\n\t        Voie A\t\t\tR-F. 20\tJ-G. 20 \n ",null,null,31456]
["Infrabel","26994","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,4,5,"2021-01-23",44061.944444444445,"2021-01-24",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P4+ \n ",null,null,26994]
["Infrabel","34229","Lille - Charleroi","< >","Y.SOIGNIES","BRAINE-LE-COMTE",2021,2021,4,5,"2021-01-23",44061.270833333336,"2021-01-24",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P4+ \n ",null,null,34229]
["Infrabel","30997","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,5,5,"2021-01-25",44061.958333333336,"2021-01-29",44061.166666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk. \n ",null,null,30997]
["Infrabel","32285","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,5,5,"2021-01-25",44061.979166666664,"2021-01-30",44061.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,32285]
["Infrabel","32283","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,5,5,"2021-01-25",44061.986111111109,"2021-01-30",44061.236111111109,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P3 HKV - Zone 3 AI53 \n ",null,null,32283]
["Infrabel","26420","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,5,5,"2021-01-25",44061.944444444445,"2021-01-30",44061.236111111109,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P3 HKV - Zone 9 AI52 \n ",null,null,26420]
["Infrabel","32288","Lille - Charleroi","< >","ATH","TOURNAI",2021,2021,5,5,"2021-01-25",44061.940972222219,"2021-01-30",44061.190972222219,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5.54 \n ",null,null,32288]
["Infrabel","21103","Lille - Charleroi","< >","ATH","ENGHIEN",2021,2021,5,6,"2021-01-29",44061.958333333336,"2021-01-31",44061.75,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"MES en EBP/PLP \n ",null,null,21103]
["Infrabel","31004","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,5,6,"2021-01-30",44061,"2021-02-01",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk. \n ",null,null,31004]
["Infrabel","23501","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2021,2021,6,6,"2021-02-01",44061.958333333336,"2021-02-06",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoudswerken \n ",null,null,23501]
["Infrabel","20862","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2021,2021,6,6,"2021-02-01",44061.979166666664,"2021-02-06",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L140 BK 58.475 : Rnvlt des passerelles/trottoirs du PS\r\nTravaux de finition suite CTL du 13 au 16 novembre 2020 (UPM A-078998) \n ",null,null,20862]
["Infrabel","32979","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","KORTRIJK",2021,2021,6,6,"2021-02-01",44061.951388888891,"2021-02-06",44061.236111111109,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.54\r\nP3 HKV\r\nUPM 109515 \nA déterminer",null,null,32979]
["Infrabel","21655","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,6,7,"2021-02-05",44061.993055555555,"2021-02-08",44061.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen. \n ",null,null,21655]
["Infrabel","30408","Namur - Antwerpen","< >","AUVELAIS","TAMINES",2021,2021,6,23,"2021-02-06",44061.979166666664,"2021-05-31",44061.208333333336,"114d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"ETCS L130 CTL nuits weekends \n ",null,null,30408]
["Infrabel","25665","Lille - Charleroi",">","LUTTRE","Y.NORD",2021,2021,7,10,"2021-02-08",44061.958333333336,"2021-02-28",44061.208333333336,"20d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A \n ",null,null,25665]
["Infrabel","27224","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,7,7,"2021-02-08",44061.9375,"2021-02-13",44061.170138888891,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51    P3 HKV \n ",null,null,27224]
["Infrabel","31390","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,7,7,"2021-02-08",44061.993055555555,"2021-02-12",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31390]
["Infrabel","20390","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2021,2021,7,8,"2021-02-12",44061.979166666664,"2021-02-15",44061.708333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement 2 PS rue Baudoux et rue du gros chêne\r\npose des nouveaux tabliers \n ",null,null,20390]
["Infrabel","21656","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,7,8,"2021-02-12",44061.993055555555,"2021-02-15",44061.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen. \n ",null,null,21656]
["Infrabel","21652","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,7,9,"2021-02-13",44061.027777777781,"2021-02-22",44061.177083333336,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"- Omvorming stopplaats Zwijndrecht (FASE 2)\r\n- Verhogen veiligheid Kennedytunnel \n ",null,null,21652]
["Infrabel","29277","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,7,9,"2021-02-13",44061.027777777781,"2021-02-22",44061.177083333336,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 PLP SI\r\nL59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel \n ",null,null,29277]
["Infrabel","31483","Erquelinnes - Montzen","< >","CHARLEROI-SUD","MARCHIENNE-ZONE",2021,2021,7,8,"2021-02-13",44061.25,"2021-02-14",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5. 51\r\nP4+ \n ",null,null,31483]
["Infrabel","32295","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,8,8,"2021-02-15",44061.979166666664,"2021-02-20",44061.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,32295]
["Infrabel","33034","Lille - Charleroi","< >","TOURNAI","FROYENNES",2021,2021,8,8,"2021-02-15",44061.9375,"2021-02-20",44061.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.54 \n ",null,null,33034]
["Infrabel","28212","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,8,8,"2021-02-15",44061.944444444445,"2021-02-20",44061.236111111109,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nP3 HKM 2 nuits\r\nP3 HKV 3 nuits \n ",null,null,28212]
["Infrabel","32299","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","BLANDAIN-FRONTIERE",2021,2021,8,8,"2021-02-15",44061.944444444445,"2021-02-20",44061.243055555555,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z7.54 \n ",null,null,32299]
["Infrabel","20456","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2021,2021,8,9,"2021-02-19",44061.979166666664,"2021-02-21",44061.708333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement 2 PS rue Baudoux et rue du gros chêne\r\npose des nouveaux tabliers \n ",null,null,20456]
["Infrabel","21657","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,8,9,"2021-02-19",44061.993055555555,"2021-02-22",44061.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen. \n ",null,null,21657]
["Infrabel","32297","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,8,9,"2021-02-20",44061.3125,"2021-02-21",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 - P4 \n ",null,null,32297]
["Infrabel","22929","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,9,16,"2021-02-21",44061.951388888891,"2021-04-11",44061.229166666664,"49d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"RER : \r\nSAVU DE NUIT en semaine 22:50-05:30\r\net CTL nuit les weekend samedi a dimanche 00:30-05:30\r\nTravaux préparatoires de la renovation de la Y.LLN \n ",null,null,22929]
["Infrabel","27228","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,9,9,"2021-02-22",44061.972222222219,"2021-02-26",44061.222222222219,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P3 HKV \n ",null,null,27228]
["Infrabel","33547","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","Y.VAL-SAINT-LAMBERT",2021,2021,9,9,"2021-02-22",44061.965277777781,"2021-02-27",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Z.19.41 - Maintenance P3 \n ",null,null,33547]
["Infrabel","24633","Lille - Charleroi",">","MANAGE","LUTTRE",2021,2021,9,9,"2021-02-22",44061.986111111109,"2021-02-27",44061.208333333336,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"essai de sécurité avant mise en service EBP/PLP \n ",null,null,24633]
["Infrabel","27503","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2021,2021,9,10,"2021-02-26",44061.993055555555,"2021-03-01",44061.197916666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER CTL déviation voie B de Watermael \n ",null,null,27503]
["Infrabel","21658","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,9,10,"2021-02-26",44061.993055555555,"2021-03-01",44061.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen. \n ",null,null,21658]
["Infrabel","22211","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,9,10,"2021-02-27",44061.958333333336,"2021-02-28",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22211]
["Infrabel","26877","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,9,10,"2021-02-27",44061.958333333336,"2021-02-28",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nP4+ Mini CTL \n ",null,null,26877]
["Infrabel","27226","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,9,10,"2021-02-27",44061.222222222219,"2021-02-28",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P4+ \n ",null,null,27226]
["Infrabel","30110","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,10,10,"2021-02-28",44061.25,"2021-02-28",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,30110]
["Infrabel","33289","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2021,2021,10,10,"2021-02-28",44061.270833333336,"2021-02-28",44061.625,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Massification \r\nCTL dimanche \n ",null,null,33289]
["Infrabel","30998","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,10,10,"2021-03-01",44061.958333333336,"2021-03-06",44061.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk. \n ",null,null,30998]
["Infrabel","25184","Lille - Charleroi",">","MARCHIENNE-AU-PONT","ROUX",2021,2021,10,13,"2021-03-01",44061.958333333336,"2021-03-26",44061.958333333336,"25d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Travaux de Réélectrification L. 124A voie B (Roux - Marchienne-au-Pont) \n ",null,null,25184]
["Infrabel","24636","Lille - Charleroi",">","MANAGE","LUTTRE",2021,2021,10,10,"2021-03-01",44061.986111111109,"2021-03-06",44061.208333333336,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"essai de sécurité avant mise en service EBP/PLP \n ",null,null,24636]
["Infrabel","20865","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,10,10,"2021-03-01",44061.993055555555,"2021-03-06",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,20865]
["Infrabel","26714","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,10,10,"2021-03-02",44061.010416666664,"2021-03-05",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,26714]
["Infrabel","33977","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2021,2021,10,10,"2021-03-02",44061.010416666664,"2021-03-05",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,33977]
["Infrabel","34045","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,10,10,"2021-03-02",44061.010416666664,"2021-03-05",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,34045]
["Infrabel","33974","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,10,10,"2021-03-02",44061.003472222219,"2021-03-05",44061.180555555555,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,33974]
["Infrabel","21659","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,10,11,"2021-03-05",44061.993055555555,"2021-03-08",44061.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen. \n ",null,null,21659]
["Infrabel","36824","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,10,11,"2021-03-06",44061.958333333336,"2021-03-07",44061.208333333336,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk. \n ",null,null,36824]
["Infrabel","37195","Lille - Charleroi","< >","MANAGE","MANAGE",2021,2021,10,11,"2021-03-06",44061.958333333336,"2021-03-07",44061.291666666664,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Déchargement LRS en L117 pour le chantier de Manage 2021 \n ",null,null,37195]
["Infrabel","17019","Namur - Antwerpen","< >","AISEAU","FARCIENNES",2021,2021,10,11,"2021-03-06",44061.208333333336,"2021-03-08",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,17019]
["Infrabel","26422","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,10,11,"2021-03-06",44061.291666666664,"2021-03-07",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P4+  - Zone 9 AI52 \n ",null,null,26422]
["Infrabel","26991","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,10,11,"2021-03-06",44061.291666666664,"2021-03-07",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P4+\r\nZone 3 AI 53 \n ",null,null,26991]
["Infrabel","26869","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2021,2021,10,11,"2021-03-06",44061.25,"2021-03-07",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP4+ \n ",null,null,26869]
["Infrabel","30999","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,11,11,"2021-03-08",44061.958333333336,"2021-03-12",44061.166666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk. \n ",null,null,30999]
["Infrabel","31593","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2021,2021,11,11,"2021-03-08",44061.972222222219,"2021-03-13",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z7.52\r\nMise HS P3 HKM - Zone 7 AI52 \n ",null,null,31593]
["Infrabel","26870","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2021,2021,11,11,"2021-03-08",44061.993055555555,"2021-03-12",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP3HKM \n ",null,null,26870]
["Infrabel","31391","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,11,11,"2021-03-08",44061.993055555555,"2021-03-12",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31391]
["Infrabel","26715","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,11,11,"2021-03-09",44061.010416666664,"2021-03-12",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,26715]
["Infrabel","33978","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2021,2021,11,11,"2021-03-09",44061.010416666664,"2021-03-12",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,33978]
["Infrabel","34046","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,11,11,"2021-03-09",44061.010416666664,"2021-03-12",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,34046]
["Infrabel","34001","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,11,11,"2021-03-09",44061.003472222219,"2021-03-12",44061.180555555555,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,34001]
["Infrabel","24610","Lille - Charleroi",">","MANAGE","LUTTRE",2021,2021,11,11,"2021-03-10",44061.986111111109,"2021-03-13",44061.006944444445,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"placement CV Jade en VB avant mise en service EBP/PLP \n ",null,null,24610]
["Infrabel","21660","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,11,12,"2021-03-12",44061.993055555555,"2021-03-15",44061.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen. \n ",null,null,21660]
["Infrabel","24596","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,11,12,"2021-03-13",44061.006944444445,"2021-03-14",44061.916666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"MES EBP/PLP \n ",null,null,24596]
["Infrabel","22780","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,11,12,"2021-03-13",44061,"2021-03-15",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk. \n ",null,null,22780]
["Infrabel","32482","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,11,11,"2021-03-13",44061.010416666664,"2021-03-13",44061.21875,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,32482]
["Infrabel","34062","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,11,11,"2021-03-13",44061.010416666664,"2021-03-13",44061.21875,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,34062]
["Infrabel","34083","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2021,2021,11,11,"2021-03-13",44061.010416666664,"2021-03-13",44061.21875,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,34083]
["Infrabel","34082","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,11,11,"2021-03-13",44061.003472222219,"2021-03-13",44061.180555555555,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,34082]
["Infrabel","31820","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2021,2021,12,12,"2021-03-15",44061.979166666664,"2021-03-20",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z10. 51   P3 HKV \n ",null,null,31820]
["Infrabel","34238","Lille - Charleroi","< >","Y.SOIGNIES","BRAINE-LE-COMTE",2021,2021,12,12,"2021-03-15",44061.979166666664,"2021-03-20",44061.1875,"5d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P3 HKV \n ",null,null,34238]
["Infrabel","31392","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,12,12,"2021-03-15",44061.993055555555,"2021-03-20",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31392]
["Infrabel","26982","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,12,12,"2021-03-15",44061.982638888891,"2021-03-20",44061.177083333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P3 5 HKV \n ",null,null,26982]
["Infrabel","31498","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE-WIJKSPOREN",2021,2021,12,12,"2021-03-16",44061.010416666664,"2021-03-19",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"aanleg kabel: ETCS L2+IL P014b_01 Gent-Sint Pieters - De Pinte \n ",null,null,31498]
["Infrabel","33979","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2021,2021,12,12,"2021-03-16",44061.010416666664,"2021-03-19",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,33979]
["Infrabel","34034","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,12,12,"2021-03-16",44061.010416666664,"2021-03-19",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,34034]
["Infrabel","34047","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,12,12,"2021-03-16",44061.010416666664,"2021-03-19",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,34047]
["Infrabel","34005","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,12,12,"2021-03-16",44061.003472222219,"2021-03-19",44061.180555555555,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,34005]
["Infrabel","22691","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,12,13,"2021-03-19",44061.993055555555,"2021-03-22",44061.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen. \n ",null,null,22691]
["Infrabel","31728","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2021,2021,12,13,"2021-03-20",44061.208333333336,"2021-03-21",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z10. 51   P4+ \n ",null,null,31728]
["Infrabel","34242","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,12,13,"2021-03-20",44061.944444444445,"2021-03-21",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P4+ \n ",null,null,34242]
["Infrabel","34243","Lille - Charleroi","< >","Y.SOIGNIES","BRAINE-LE-COMTE",2021,2021,12,13,"2021-03-20",44061.270833333336,"2021-03-21",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P4+ \n ",null,null,34243]
["Infrabel","29870","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,13,13,"2021-03-21",44061.25,"2021-03-21",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29870]
["Infrabel","17001","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,13,13,"2021-03-22",44061.958333333336,"2021-03-27",44061.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,17001]
["Infrabel","32998","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,13,13,"2021-03-22",44061.979166666664,"2021-03-27",44061.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,32998]
["Infrabel","31596","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2021,2021,13,14,"2021-03-27",44061.958333333336,"2021-03-28",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z7.52\r\nMise HS P4+ - Zone 7 AI52 \n ",null,null,31596]
["Infrabel","22212","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,13,14,"2021-03-27",44061.958333333336,"2021-03-28",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22212]
["Infrabel","30587","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE-MARCHANDISE","TAMINES",2021,2021,13,14,"2021-03-27",44061.958333333336,"2021-03-28",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nP4+ Mini CTL \n ",null,null,30587]
["Infrabel","32293","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,13,14,"2021-03-27",44061.25,"2021-03-28",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Z13.54/Z7.53 pour SI\r\nRéglage CV entre Brugelette et Ath \nDétournements à prévoir",null,null,32293]
["Infrabel","32260","Lille - Charleroi",">","LUTTRE","Y.NORD",2021,2021,14,17,"2021-03-28",44061.958333333336,"2021-04-19",44061.25,"22d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Travaux de Réélectrification L. 124A voie A \n ",null,null,32260]
["Infrabel","29871","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,14,14,"2021-03-28",44061.25,"2021-03-28",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29871]
["Infrabel","33300","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2021,2021,14,14,"2021-03-28",44061.270833333336,"2021-03-28",44061.625,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Massification \r\nCTL dimanche \n ",null,null,33300]
["Infrabel","31449","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,14,14,"2021-03-29",44061.958333333336,"2021-04-02",44061.229166666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,31449]
["Infrabel","31609","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2021,2021,14,14,"2021-03-29",44061.979166666664,"2021-04-03",44061.1875,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.52\r\nMise HS P3 - Zone 13 AI52 \n ",null,null,31609]
["Infrabel","31486","Erquelinnes - Montzen","< >","CHARLEROI-SUD","LA SAMBRE",2021,2021,14,14,"2021-03-29",44061.902777777781,"2021-04-03",44061.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5. 51\r\nP3  HKV \n ",null,null,31486]
["Infrabel","33008","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2021,2021,14,14,"2021-03-29",44061.375,"2021-04-02",44061.666666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.54 (avec travaux SNCF-Réseau) \nDétournements suivant SNCF-Réseau",null,null,33008]
["Infrabel","23972","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE-WIJKSPOREN",2021,2021,14,14,"2021-03-30",44061.010416666664,"2021-04-02",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"aanleg kabel: ETCS L2+IL P014b_01 Gent-Sint Pieters - De Pinte \n ",null,null,23972]
["Infrabel","17039","Athus - Meuse",">","JAMBES","LUSTIN",2021,2021,14,17,"2021-03-31",44061.333333333336,"2021-04-18",44061.666666666664,"18d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast (C75) \nHKM A ADAPTER",null,null,17039]
["Infrabel","18399","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,14,17,"2021-04-02",44061.958333333336,"2021-04-19",44061.166666666664,"17d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN45 et PN46 \n ",null,null,18399]
["Infrabel","19893","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,14,15,"2021-04-03",44061.958333333336,"2021-04-04",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 11 \nHKM A ADAPTER",null,null,19893]
["Infrabel","26244","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","Y.RENORY",2021,2021,14,15,"2021-04-03",44061.333333333336,"2021-04-04",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z.21.41 P4+ \nPas d'accès possible au port de Rénory\r\nDétournement via formation et réception",null,null,26244]
["Infrabel","19269","Lille - Antwerpen","< >","Y.BETHUNE","KORTRIJK",2021,2021,14,17,"2021-04-03",44061,"2021-04-19",44061.166666666664,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Bouwen van een tunnel (met open sleuf) \n",null,null,19269]
["Infrabel","22322","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,14,17,"2021-04-03",44061,"2021-04-19",44061.166666666664,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Nieuwe ondertunneling Kortrijk. \n ",null,null,22322]
["Infrabel","19892","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,14,15,"2021-04-03",44061.25,"2021-04-05",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 11 \n ",null,null,19892]
["Infrabel","35730","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","Y.RENORY",2021,2021,15,15,"2021-04-05",44061.965277777781,"2021-04-10",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z.21.41 P3 \nAccès port Rénory Impossible",null,null,35730]
["Infrabel","31222","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,15,15,"2021-04-06",44061.9375,"2021-04-10",44061.170138888891,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51    P3 HKV \n ",null,null,31222]
["Infrabel","26720","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,15,15,"2021-04-06",44061.010416666664,"2021-04-09",44061.135416666664,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg\r\n*Vroeger in dienst wegens aanvoer materieel voor Kortrijk (Langdurige TLO) \n ",null,null,26720]
["Infrabel","19895","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,15,16,"2021-04-10",44061.958333333336,"2021-04-11",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 11 \n ",null,null,19895]
["Infrabel","16761","Erquelinnes - Montzen","< >","LOBBES","ERQUELINNES",2021,2021,15,16,"2021-04-10",44061.333333333336,"2021-04-11",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement As 04AL & 04BL & 09AL & 09BL & 10AL & 10BL \n ",null,null,16761]
["Infrabel","19894","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,15,16,"2021-04-10",44061.25,"2021-04-12",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 11 \n ",null,null,19894]
["Infrabel","23934","Lille - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG",2021,2021,15,16,"2021-04-10",44061.0625,"2021-04-12",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Werken TUC P198361 - sporen A+B BD \r\nmaken doorsteken - plaatsen en verwijderen T & TS- schakelaars\r\nBDS:\r\nL50E F-S.6 tot AW 72AH vrij en AW 72BH vrij tot EX-S.6\r\nL58 C-C.13 tot AW 01XR vrij en AW 02R vrij tot CX-C.13\r\nL58/1 AW 11O vrij tot AW 03Q vrij  \n",null,null,23934]
["Infrabel","27236","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,15,16,"2021-04-10",44061.170138888891,"2021-04-11",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51  P4+ \n ",null,null,27236]
["Infrabel","31495","Erquelinnes - Montzen","< >","CHARLEROI-SUD","MARCHIENNE-ZONE",2021,2021,15,16,"2021-04-10",44061.170138888891,"2021-04-11",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5. 51\r\nP4+\r\nmassifié Z1.51 \n ",null,null,31495]
["Infrabel","19896","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,16,16,"2021-04-12",44061.375,"2021-04-12",44061.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 11 - asphaltage \n ",null,null,19896]
["Infrabel","19897","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,16,16,"2021-04-13",44061.333333333336,"2021-04-13",44061.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 11 - asphaltage \n ",null,null,19897]
["Infrabel","29435","Namur - Antwerpen","< >","CHATELET-GRIL EST","CHATELET-GRIL EST",2021,2021,16,17,"2021-04-17",44061.916666666664,"2021-04-18",44061.916666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z17. 51 (P4+) \n ",null,null,29435]
["Infrabel","37088","Athus - Meuse","< >","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,16,17,"2021-04-17",44061.961805555555,"2021-04-18",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 104.150 à Bk 104.190 \nHKM A ADAPTER",null,null,37088]
["Infrabel","16993","Namur - Antwerpen",">","TILLY","LA ROCHE(BRABANT)",2021,2021,17,17,"2021-04-19",44061.958333333336,"2021-04-23",44061.229166666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,16993]
["Infrabel","33012","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,17,17,"2021-04-19",44061.979166666664,"2021-04-24",44061.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,33012]
["Infrabel","20466","Athus - Meuse",">","JAMBES","LUSTIN",2021,2021,17,20,"2021-04-19",44061.916666666664,"2021-05-09",44061.75,"20d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement traverses et ballast dans le tunnel de Lustin \nHKM A ADAPTER",null,null,20466]
["Infrabel","20955","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,17,18,"2021-04-19",44061.986111111109,"2021-04-30",44061.229166666664,"11d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Démolition du PS 42.810 \n ",null,null,20955]
["Infrabel","10038","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,17,18,"2021-04-19",44061.986111111109,"2021-05-01",44061.229166666664,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,10038]
["Infrabel","26417","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,17,17,"2021-04-19",44061.944444444445,"2021-04-24",44061.243055555555,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P3 HKV - Zone 8 AI52 \n ",null,null,26417]
["Infrabel","33013","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","BLANDAIN-FRONTIERE",2021,2021,17,17,"2021-04-19",44061.944444444445,"2021-04-24",44061.243055555555,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z7.54 \n ",null,null,33013]
["Infrabel","22787","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,17,17,"2021-04-19",44061.993055555555,"2021-04-23",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Afwerking: Nieuwe ondertunneling Kortrijk. \n ",null,null,22787]
["Infrabel","26724","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,17,17,"2021-04-20",44061.010416666664,"2021-04-23",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,26724]
["Infrabel","21355","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,17,18,"2021-04-23",44061.986111111109,"2021-04-26",44061.194444444445,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,21355]
["Infrabel","21094","Lille - Charleroi",">","Y.FAMILLEUREUX","MANAGE",2021,2021,17,17,"2021-04-23",44061.75,"2021-04-24",44061.013888888891,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Démolition du PS 42.810\r\nEn massification avec la coupure 21360 \nVoir coupure 21360",null,null,21094]
["Infrabel","22791","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,17,18,"2021-04-24",44061,"2021-04-26",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Afwerking: Nieuwe ondertunneling Kortrijk. \n ",null,null,22791]
["Infrabel","21105","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,17,18,"2021-04-24",44061.965277777781,"2021-04-26",44061.201388888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PS 51.035 et du pont du canal - Travaux SPW \n ",null,null,21105]
["Infrabel","22794","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,18,18,"2021-04-26",44061.993055555555,"2021-04-30",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwwerking Nieuwe ondertunneling Kortrijk. \n ",null,null,22794]
["Infrabel","21318","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,18,18,"2021-04-26",44061.375,"2021-04-26",44061.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 104.150 à Bk 104.190 - Bourrage vitesse normale \nHKM A ADAPTER",null,null,21318]
["Infrabel","21319","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,18,18,"2021-04-27",44061.333333333336,"2021-04-27",44061.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 104.150 à Bk 104.190 - Réglage des contraintes \n ",null,null,21319]
["Infrabel","26725","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,18,18,"2021-04-27",44061.010416666664,"2021-04-30",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,26725]
["Infrabel","21360","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,18,19,"2021-04-30",44061.986111111109,"2021-05-03",44061.194444444445,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,21360]
["Infrabel","26691","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,18,19,"2021-05-01",44061,"2021-05-03",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Afwerking: Nieuwe ondertunneling Kortrijk. \n ",null,null,26691]
["Infrabel","29876","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,19,19,"2021-05-02",44061.25,"2021-05-02",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29876]
["Infrabel","33292","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2021,2021,19,19,"2021-05-02",44061.270833333336,"2021-05-02",44061.625,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Massification \r\nCTL dimanche \n ",null,null,33292]
["Infrabel","20857","Namur - Antwerpen",">","TILLY","LA ROCHE(BRABANT)",2021,2021,19,19,"2021-05-03",44061.958333333336,"2021-05-08",44061.208333333336,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,20857]
["Infrabel","21095","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,19,19,"2021-05-03",44061.986111111109,"2021-05-08",44061.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Démolition du PS 42.810 \n ",null,null,21095]
["Infrabel","30992","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,19,19,"2021-05-03",44061.986111111109,"2021-05-08",44061.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,30992]
["Infrabel","32947","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2021,2021,19,19,"2021-05-03",44061.993055555555,"2021-05-07",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51 P3 HKM \n ",null,null,32947]
["Infrabel","33020","Lille - Charleroi","< >","ATH","TOURNAI",2021,2021,19,19,"2021-05-03",44061.940972222219,"2021-05-08",44061.190972222219,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5.54 \n ",null,null,33020]
["Infrabel","26726","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,19,19,"2021-05-04",44061.010416666664,"2021-05-07",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,26726]
["Infrabel","21358","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,19,20,"2021-05-07",44061.986111111109,"2021-05-10",44061.194444444445,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,21358]
["Infrabel","29878","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,20,20,"2021-05-09",44061.25,"2021-05-09",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29878]
["Infrabel","18076","Athus - Meuse",">","PALISEUL","BERTRIX",2021,2021,20,26,"2021-05-10",44061.333333333336,"2021-06-25",44061.666666666664,"46d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Assainissement à la grue (71410-72140)\r\nCas 26441 reste sous tension pour utilisation de la liaison 02BQ/02AQ \n ",null,null,18076]
["Infrabel","31207","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,20,21,"2021-05-10",44061.951388888891,"2021-05-21",44061.229166666664,"11d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"RER : \r\nSAVU DE NUIT en semaine 22:50-05:30\r\net CTL nuit les weekend samedi a dimanche 00:30-05:30\r\nTravaux préparatoires de la renovation de la Y.LLN \n ",null,null,31207]
["Infrabel","30993","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,20,27,"2021-05-10",44061.986111111109,"2021-07-02",44061.229166666664,"53d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,30993]
["Infrabel","21359","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,20,21,"2021-05-12",44061.986111111109,"2021-05-17",44061.194444444445,"5d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,21359]
["Infrabel","20690","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2021,2021,20,21,"2021-05-14",44061.993055555555,"2021-05-17",44061.197916666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"CTL RER \n ",null,null,20690]
["Infrabel","20180","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,20,21,"2021-05-15",44061.013888888891,"2021-05-17",44061.25,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord \n ",null,null,20180]
["Infrabel","26439","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,20,21,"2021-05-15",44061.013888888891,"2021-05-17",44061.25,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement PN 28\r\nMassifiée avec CTL (id 20180) \n ",null,null,26439]
["Infrabel","29879","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,21,21,"2021-05-16",44061.25,"2021-05-16",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29879]
["Infrabel","20179","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,21,21,"2021-05-17",44061.958333333336,"2021-05-22",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord \n ",null,null,20179]
["Infrabel","22210","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2021,2021,21,21,"2021-05-17",44061.965277777781,"2021-05-21",44061.236111111109,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme), \r\ntravaux préparatoires (dépose caténaire existante, pose panneaux ART, préparation panneaux d'appareils de voie,...) \n ",null,null,22210]
["Infrabel","33027","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","BLANDAIN-FRONTIERE",2021,2021,21,21,"2021-05-17",44061.944444444445,"2021-05-22",44061.243055555555,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z7.54 \n ",null,null,33027]
["Infrabel","20869","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,21,21,"2021-05-17",44061.993055555555,"2021-05-21",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,20869]
["Infrabel","31000","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,21,21,"2021-05-18",44061.020833333336,"2021-05-22",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwwerking Nieuwe ondertunneling Kortrijk. \n ",null,null,31000]
["Infrabel","30107","Namur - Antwerpen",">","CHATELET","LE CAMPINAIRE",2021,2021,21,22,"2021-05-21",44061.9375,"2021-05-25",44061.229166666664,"4d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Phase 2.2 : Renouvellement Rails-Traverses-Ballast du Trapèze de la voie d'évitement (W-e 3 jours) \n ",null,null,30107]
["Infrabel","20189","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2021,2021,21,22,"2021-05-21",44061.965277777781,"2021-05-25",44061.236111111109,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS \n ",null,null,20189]
["Infrabel","20455","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2021,2021,21,22,"2021-05-21",44061.986111111109,"2021-05-24",44061.708333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Démolition PS Ponlot \n ",null,null,20455]
["Infrabel","21357","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,21,22,"2021-05-21",44061.986111111109,"2021-05-25",44061.194444444445,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,21357]
["Infrabel","23104","Athus - Meuse","< >","HALANZY","AUBANGE",2021,2021,21,22,"2021-05-22",44061.25,"2021-05-23",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 138.830 à 138.870 (PN41) \n ",null,null,23104]
["Infrabel","21323","Athus - Meuse",">","HALANZY","AUBANGE",2021,2021,21,22,"2021-05-22",44061.25,"2021-05-24",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 138.830 à 138.870 (PN41) \n ",null,null,21323]
["Infrabel","20182","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2021,2021,22,22,"2021-05-24",44061.916666666664,"2021-05-28",44061.25,"4d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Dépose caténaire voie 553 \n ",null,null,20182]
["Infrabel","31001","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,22,22,"2021-05-24",44061.993055555555,"2021-05-28",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwwerking Nieuwe ondertunneling Kortrijk. \n ",null,null,31001]
["Infrabel","33028","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,22,22,"2021-05-25",44061.979166666664,"2021-05-29",44061.166666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,33028]
["Infrabel","20868","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,22,22,"2021-05-25",44061.993055555555,"2021-05-29",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \nAdaptations",null,null,20868]
["Infrabel","26731","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,22,22,"2021-05-26",44061.010416666664,"2021-05-28",44061.177083333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg\r\n(aanvang na Pinksterweekend wegens TLO L59) \n ",null,null,26731]
["Infrabel","21155","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2021,2021,22,23,"2021-05-28",44061.965277777781,"2021-05-31",44061.236111111109,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS \n ",null,null,21155]
["Infrabel","21354","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,22,23,"2021-05-28",44061.986111111109,"2021-05-31",44061.194444444445,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,21354]
["Infrabel","22213","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,22,23,"2021-05-29",44061.958333333336,"2021-05-30",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22213]
["Infrabel","30588","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,22,23,"2021-05-29",44061.958333333336,"2021-05-30",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nP4+ Mini CTL \n ",null,null,30588]
["Infrabel","31190","Athus - Meuse",">","HALANZY","AUBANGE",2021,2021,22,23,"2021-05-29",44061.958333333336,"2021-05-30",44061.625,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 138.830 à 138.870 (PN41) - pose revêtement routier / bourrage vitesse normale / réglage contraintes \n ",null,null,31190]
["Infrabel","21324","Athus - Meuse",">","HALANZY","AUBANGE",2021,2021,22,23,"2021-05-29",44061.25,"2021-05-30",44061.208333333336,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 138.830 à 138.870 (PN41) - pose revêtement routier / bourrage vitesse normale / réglage contraintes \n ",null,null,21324]
["Infrabel","30252","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,22,23,"2021-05-29",44061.072916666664,"2021-05-31",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Bundelkop Bundel Luchtbal\r\nWE 1 \n ",null,null,30252]
["Infrabel","22614","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,23,23,"2021-05-30",44061.03125,"2021-05-30",44061.25,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,22614]
["Infrabel","34839","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,23,23,"2021-05-31",44061.03125,"2021-05-31",44061.208333333336,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,34839]
["Infrabel","31490","Erquelinnes - Montzen","< >","CHARLEROI-SUD","LA SAMBRE",2021,2021,23,23,"2021-05-31",44061.9375,"2021-06-05",44061.170138888891,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5. 51\r\nP3  HKV \n ",null,null,31490]
["Infrabel","21321","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,23,23,"2021-05-31",44061.375,"2021-05-31",44061.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 116.150 à Bk 116.180 & renouvellement étanchéité PI - Bourrage vitesse normale \nHKM A ADAPTER",null,null,21321]
["Infrabel","18109","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,23,23,"2021-06-01",44061.020833333336,"2021-06-05",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,18109]
["Infrabel","26729","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,23,23,"2021-06-01",44061.010416666664,"2021-06-04",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,26729]
["Infrabel","21322","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,23,23,"2021-06-01",44061.375,"2021-06-01",44061.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 116.150 à Bk 116.180 & renouvellement étanchéité PI - Réglage des contraintes \nHKM A ADAPTER",null,null,21322]
["Infrabel","20190","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2021,2021,23,24,"2021-06-04",44061.965277777781,"2021-06-07",44061.236111111109,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS \n ",null,null,20190]
["Infrabel","18107","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,23,24,"2021-06-05",44061.020833333336,"2021-06-07",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,18107]
["Infrabel","31095","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,23,24,"2021-06-05",44061.013888888891,"2021-06-07",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"In dienst name van Piloot 3 van de inklinking SIW \n ",null,null,31095]
["Infrabel","23133","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,23,24,"2021-06-05",44061.072916666664,"2021-06-07",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nWE 1 TLO \n ",null,null,23133]
["Infrabel","30242","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,23,24,"2021-06-05",44061.072916666664,"2021-06-07",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Bundelkop Bundel Luchtbal\r\nWE 2 TLO \n ",null,null,30242]
["Infrabel","22209","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2021,2021,24,24,"2021-06-07",44061.965277777781,"2021-06-11",44061.236111111109,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme), suite phase 2\r\ntravaux divers en voie A (bourrage de révision, réglage des contraintes, retrait ART, toilette de la voie...) \n ",null,null,22209]
["Infrabel","27796","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,24,24,"2021-06-08",44061.020833333336,"2021-06-12",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,27796]
["Infrabel","18093","Lille - Charleroi","< >","NEUFVILLES","MASNUY-SAINT-PIERRE",2021,2021,24,24,"2021-06-08",44061.020833333336,"2021-06-12",44061.177083333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL de nuit étendues. Rejointoiement et réfection de maçonnerie en voûte (PS 42.540) \n ",null,null,18093]
["Infrabel","34248","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,24,24,"2021-06-08",44061.020833333336,"2021-06-12",44061.177083333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P3 HKM \n ",null,null,34248]
["Infrabel","26740","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,24,24,"2021-06-08",44061.010416666664,"2021-06-11",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,26740]
["Infrabel","20451","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2021,2021,24,25,"2021-06-12",44061.027777777781,"2021-06-13",44061.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA + voies tronçon Andenne - Namur (renouvellement de rails suite défaut US entre BK 56500 et BK 58000) \n ",null,null,20451]
["Infrabel","25447","Lille - Charleroi","< >","Y.LENS","ATH",2021,2021,24,25,"2021-06-12",44061.319444444445,"2021-06-14",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise en service de la seconde phase de la L90C BA Brugelette/Ath \n ",null,null,25447]
["Infrabel","36416","Lille - Charleroi","< >","Y.LENS","JURBISE",2021,2021,24,25,"2021-06-12",44061.319444444445,"2021-06-14",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS 49.000\r\nRenforcement culées \n ",null,null,36416]
["Infrabel","25361","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,24,25,"2021-06-12",44061.072916666664,"2021-06-14",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nWE 2 TLO \n ",null,null,25361]
["Infrabel","30244","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,24,25,"2021-06-12",44061.072916666664,"2021-06-14",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Bundelkop Bundel Luchtbal\r\nWE 3 TLO \n ",null,null,30244]
["Infrabel","22978","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,25,25,"2021-06-14",44061.958333333336,"2021-06-18",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord - bourrage de revision, finitions \n ",null,null,22978]
["Infrabel","28722","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,25,25,"2021-06-14",44061.958333333336,"2021-06-18",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux PN28 DT 143100 \n ",null,null,28722]
["Infrabel","21035","Lille - Charleroi","< >","ATH","ATH",2021,2021,25,25,"2021-06-14",44061.979166666664,"2021-06-18",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Péparartion renouvellement 34AF/34BF + 42F \n ",null,null,21035]
["Infrabel","30109","Namur - Antwerpen",">","CHATELET","LE CAMPINAIRE",2021,2021,25,25,"2021-06-15",44061.9375,"2021-06-19",44061.229166666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Phase 2.3 : Bourrage de révision, nettoyage + réglage de joints \n ",null,null,30109]
["Infrabel","27797","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,25,25,"2021-06-15",44061.020833333336,"2021-06-19",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,27797]
["Infrabel","23980","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE-WIJKSPOREN",2021,2021,25,25,"2021-06-15",44061.010416666664,"2021-06-18",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"aanleg kabel: ETCS L2+IL P014b_01 Gent-Sint Pieters - De Pinte \n ",null,null,23980]
["Infrabel","21036","Lille - Charleroi","< >","ATH","LEUZE",2021,2021,25,26,"2021-06-18",44061.979166666664,"2021-06-21",44061.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 34AF/34BF + 42F \n ",null,null,21036]
["Infrabel","20432","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2021,2021,25,26,"2021-06-19",44061.027777777781,"2021-06-20",44061.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur (renouvellement de quais - renouvellement passerelles - parois rocheuses - ...) \n ",null,null,20432]
["Infrabel","25357","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,26,26,"2021-06-20",44061.03125,"2021-06-20",44061.25,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,25357]
["Infrabel","29884","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,26,26,"2021-06-20",44061.25,"2021-06-20",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29884]
["Infrabel","31696","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,26,26,"2021-06-21",44061.958333333336,"2021-06-25",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord - bourrage de revision, finitions \n ",null,null,31696]
["Infrabel","36562","Lille - Charleroi","< >","ATH","ATH",2021,2021,26,26,"2021-06-21",44061.979166666664,"2021-06-26",44061.1875,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Péparartion renouvellement 34AF/34BF + 42F \n ",null,null,36562]
["Infrabel","34840","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,26,26,"2021-06-21",44061.03125,"2021-06-21",44061.208333333336,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,34840]
["Infrabel","26421","Lille - Charleroi",">","ECAUSSINNES","MANAGE",2021,2021,26,26,"2021-06-21",44061.986111111109,"2021-06-26",44061.194444444445,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS SAVU P3 HKV - Zone 9 AI52\r\nincompatible chantier de Manage - SAVU possible pour trafic NMLK + HKV \n ",null,null,26421]
["Infrabel","33337","Lille - Charleroi",">","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,26,26,"2021-06-21",44061.986111111109,"2021-06-26",44061.194444444445,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS SAVU P3 HKM\r\n incompatible chantier de Manage - SAVU possible pour trafic NMLK + HKV \n ",null,null,33337]
["Infrabel","27798","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,26,26,"2021-06-22",44061.020833333336,"2021-06-26",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,27798]
["Infrabel","25131","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2021,2021,26,26,"2021-06-23",44061.958333333336,"2021-06-25",44061.21875,"2d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Préparation Criblage WE 26 - 27 juin\r\nSAVU nuit \n ",null,null,25131]
["Infrabel","22214","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,26,27,"2021-06-26",44061.958333333336,"2021-06-27",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22214]
["Infrabel","36014","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,26,27,"2021-06-26",44061.958333333336,"2021-06-27",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nP4+ Mini CTL \n ",null,null,36014]
["Infrabel","18007","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,26,27,"2021-06-26",44061.006944444445,"2021-06-28",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast avec C75:\r\n- en voie B entre 69.500 et 70.390 (900m) \r\n- en voie A entre 67.700 et 68.500 (800m) + entre 70.000 et 70.390 (390m) \nA determiner",null,null,18007]
["Infrabel","18108","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,26,27,"2021-06-26",44061.020833333336,"2021-06-28",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies\r\nA réanalyser suite rencontre EF 12/12/19 : conflit avec CTL L130 \n ",null,null,18108]
["Infrabel","29886","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,27,27,"2021-06-27",44061.25,"2021-06-27",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29886]
["Infrabel","33298","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2021,2021,27,27,"2021-06-27",44061.270833333336,"2021-06-27",44061.625,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Massification \r\nCTL dimanche \n ",null,null,33298]
["Infrabel","25132","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2021,2021,27,27,"2021-06-28",44061.958333333336,"2021-07-02",44061.21875,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Réalisation piste + bourrage de révision \n ",null,null,25132]
["Infrabel","27799","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,27,27,"2021-06-29",44061.020833333336,"2021-07-03",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,27799]
["Infrabel","24814","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,27,27,"2021-06-29",44061.010416666664,"2021-07-01",44061.177083333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwerking en  opkuis  ETCS L2+IL P014_07 Waregem Y Zandberg\r\nNacht R4 op R5 niet wegens nachttreinen Werchter \n ",null,null,24814]
["Infrabel","23039","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,27,28,"2021-07-03",44061.006944444445,"2021-07-05",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast avec C75:\r\n- en voie B entre 71.200 et 74.200 (3000m) + quais de Franière Voie B \nA determiner",null,null,23039]
["Infrabel","30994","Lille - Charleroi","< >","ATH","LEUZE",2021,2021,27,28,"2021-07-03",44061.020833333336,"2021-07-05",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 34AF/34BF + 42F \n ",null,null,30994]
["Infrabel","29887","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,28,28,"2021-07-04",44061.25,"2021-07-04",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29887]
["Infrabel","25138","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,28,28,"2021-07-05",44061.958333333336,"2021-07-08",44061.21875,"3d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"pistes + contraintes Voie B + reconstruction quai Franière Voie B \n ",null,null,25138]
["Infrabel","33331","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,28,28,"2021-07-05",44061.979166666664,"2021-07-10",44061.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,33331]
["Infrabel","27800","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,28,28,"2021-07-06",44061.020833333336,"2021-07-10",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,27800]
["Infrabel","24815","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,28,28,"2021-07-06",44061.010416666664,"2021-07-08",44061.177083333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwerking en  opkuis  ETCS L2+IL P014_07 Waregem Y Zandberg\r\nNacht R4 op R5 niet wegens nachttreinen Werchter \n ",null,null,24815]
["Infrabel","33995","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2021,2021,28,28,"2021-07-06",44061.010416666664,"2021-07-09",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,33995]
["Infrabel","25139","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,28,28,"2021-07-08",44061.958333333336,"2021-07-09",44061.21875,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Préparation criblage voie A + début démolition quai Franière voie A \n ",null,null,25139]
["Infrabel","27802","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,28,29,"2021-07-10",44061.006944444445,"2021-07-12",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast avec C75:\r\n- en voie B entre 71.200 et 74.200 (3000m) + quais de Franière Voie B \nA determiner",null,null,27802]
["Infrabel","30995","Lille - Charleroi","< >","ATH","LEUZE",2021,2021,28,29,"2021-07-10",44061.020833333336,"2021-07-12",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 34AF/34BF + 42F \n ",null,null,30995]
["Infrabel","29888","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,29,29,"2021-07-11",44061.25,"2021-07-11",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29888]
["Infrabel","25143","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,29,29,"2021-07-12",44061.958333333336,"2021-07-16",44061.21875,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Pistes + contraintes voie A + reconstruction quai Franière voie A \n ",null,null,25143]
["Infrabel","33342","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","KORTRIJK",2021,2021,29,29,"2021-07-12",44061.951388888891,"2021-07-17",44061.236111111109,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.54\r\nP3 HKV\r\nUPM 109515 \nA déterminer",null,null,33342]
["Infrabel","25137","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,29,30,"2021-07-17",44061.006944444445,"2021-07-19",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage ballast voie B entre Bk 66.100 et 68.500 (2400M) \nA determiner",null,null,25137]
["Infrabel","29897","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,30,30,"2021-07-18",44061.25,"2021-07-18",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29897]
["Infrabel","25146","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,30,30,"2021-07-19",44061.958333333336,"2021-07-22",44061.21875,"3d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"pistes + contraintes Voie B + reconstruction quai Franière Voie B \n ",null,null,25146]
["Infrabel","25148","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,30,30,"2021-07-22",44061.958333333336,"2021-07-23",44061.21875,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Pistes + contraintes voie A + reconstruction quai Franière voie A \n ",null,null,25148]
["Infrabel","25149","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,30,31,"2021-07-24",44061.006944444445,"2021-07-26",44061.208333333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage révision \nA determiner",null,null,25149]
["Infrabel","30582","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2021,2021,30,31,"2021-07-24",44061.25,"2021-07-25",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP4+ \n ",null,null,30582]
["Infrabel","26997","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,30,31,"2021-07-24",44061.3125,"2021-07-25",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P4 \r\nZone 3 AI 53 \n ",null,null,26997]
["Infrabel","29898","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,31,31,"2021-07-25",44061.25,"2021-07-25",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29898]
["Infrabel","25150","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2021,2021,31,31,"2021-07-26",44061.958333333336,"2021-07-31",44061.21875,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Pistes + Contraintes\r\nSAVU nuit \n ",null,null,25150]
["Infrabel","27237","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,31,32,"2021-07-31",44061.25,"2021-08-01",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51  P4+ \n ",null,null,27237]
["Infrabel","29899","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,32,32,"2021-08-01",44061.25,"2021-08-01",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29899]
["Infrabel","23258","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,32,32,"2021-08-02",44061.958333333336,"2021-08-07",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,23258]
["Infrabel","31208","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,32,33,"2021-08-02",44061.951388888891,"2021-08-08",44061.229166666664,"6d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"RER : \r\nSAVU DE NUIT en semaine 22:50-05:30\r\net CTL nuit les weekend samedi a dimanche 00:30-05:30\r\nTravaux préparatoires de la renovation de la Y.LLN \n ",null,null,31208]
["Infrabel","22215","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,32,33,"2021-08-07",44061.958333333336,"2021-08-08",44061.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22215]
["Infrabel","21325","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,32,33,"2021-08-07",44061.958333333336,"2021-08-08",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,21325]
["Infrabel","23105","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,32,33,"2021-08-07",44061.25,"2021-08-09",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,23105]
["Infrabel","29900","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,33,33,"2021-08-08",44061.25,"2021-08-08",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29900]
["Infrabel","32084","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,33,33,"2021-08-09",44061.958333333336,"2021-08-13",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,32084]
["Infrabel","31393","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,33,33,"2021-08-09",44061.993055555555,"2021-08-14",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31393]
["Infrabel","21326","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,33,34,"2021-08-14",44061.958333333336,"2021-08-15",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,21326]
["Infrabel","19881","Athus - Meuse","< >","BERTRIX","GEDINNE",2021,2021,33,34,"2021-08-14",44061.958333333336,"2021-08-15",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 4 ( double cas nécessaire à la demande de Mr Depierreux)\r\nCTL du samedi 23h au dimanche 15h\r\net du dimanche 23h au lundi 5h \n ",null,null,19881]
["Infrabel","23106","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,33,34,"2021-08-14",44061.25,"2021-08-16",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,23106]
["Infrabel","22856","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,33,34,"2021-08-14",44061.079861111109,"2021-08-16",44061.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22856]
["Infrabel","30105","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,34,34,"2021-08-16",44061.875,"2021-08-20",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \n ",null,null,30105]
["Infrabel","36274","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE-WIJKSPOREN",2021,2021,34,34,"2021-08-17",44061.010416666664,"2021-08-20",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud sporen en wissels. \n ",null,null,36274]
["Infrabel","19971","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2021,2021,34,37,"2021-08-18",44061.333333333336,"2021-09-06",44061.243055555555,"19d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Cribleuse L144 entre Bk 0.400 et 13.500 \n ",null,null,19971]
["Infrabel","23489","Lille - Antwerpen","< >","Y.BETHUNE","LAUWE",2021,2021,34,35,"2021-08-20",44061.979166666664,"2021-08-23",44061.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Sanering thv ex stopplaats Lauwe \n ",null,null,23489]
["Infrabel","19872","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,34,35,"2021-08-20",44061.875,"2021-08-23",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \nDétournement via L130A",null,null,19872]
["Infrabel","21330","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,34,35,"2021-08-21",44061.958333333336,"2021-08-22",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,21330]
["Infrabel","19885","Athus - Meuse","< >","GEDINNE","BERTRIX",2021,2021,34,35,"2021-08-21",44061.958333333336,"2021-08-22",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 4\r\nCTL du samedi 23h au dimanche 15h\r\net du dimanche 23h au lundi 5h \n ",null,null,19885]
["Infrabel","35582","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.HOLLAND",2021,2021,34,44,"2021-08-21",44061,"2021-10-28",44061.996527777781,"68d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwing spoortoestellen Bundel Q Antwerpen-Schijnpoort \n ",null,null,35582]
["Infrabel","26416","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,34,35,"2021-08-21",44061.25,"2021-08-22",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52 \n ",null,null,26416]
["Infrabel","23107","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,34,35,"2021-08-21",44061.25,"2021-08-23",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,23107]
["Infrabel","19884","Athus - Meuse",">","BERTRIX","GEDINNE",2021,2021,34,35,"2021-08-21",44061.25,"2021-08-23",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 4 \n ",null,null,19884]
["Infrabel","22857","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,34,35,"2021-08-21",44061.079861111109,"2021-08-23",44061.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59\r\nRelatie S32",null,null,22857]
["Infrabel","21333","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,35,35,"2021-08-23",44061.333333333336,"2021-08-27",44061.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations \n ",null,null,21333]
["Infrabel","30151","Namur - Antwerpen",">","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,35,35,"2021-08-23",44061.291666666664,"2021-08-25",44061.958333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réglage des CV pour préparer la MES PLP\r\nEssais de sécurité \n ",null,null,30151]
["Infrabel","19875","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,35,35,"2021-08-23",44061.875,"2021-08-27",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \n ",null,null,19875]
["Infrabel","33353","Lille - Charleroi","< >","ATH","TOURNAI",2021,2021,35,35,"2021-08-23",44061.940972222219,"2021-08-28",44061.190972222219,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5.54 \n ",null,null,33353]
["Infrabel","19883","Athus - Meuse",">","PALISEUL","GEDINNE",2021,2021,35,35,"2021-08-24",44061.333333333336,"2021-08-24",44061.666666666664,"0d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 4 - asphaltage \n ",null,null,19883]
["Infrabel","30152","Namur - Antwerpen",">","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,35,35,"2021-08-25",44061.958333333336,"2021-08-28",44061.958333333336,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réglage des CV pour préparer la MES PLP\r\nEssais de sécurité \r\nPas d'autres services dans la coupure \n ",null,null,30152]
["Infrabel","36405","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,35,36,"2021-08-27",44061.875,"2021-08-30",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \nDétournement via L130A",null,null,36405]
["Infrabel","21327","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,35,36,"2021-08-28",44061.958333333336,"2021-08-29",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,21327]
["Infrabel","23108","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,35,36,"2021-08-28",44061.25,"2021-08-30",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,23108]
["Infrabel","32690","Lille - Antwerpen","< >","WAREGEM","KORTRIJK",2021,2021,35,36,"2021-08-28",44061.010416666664,"2021-08-30",44061.177083333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen voegen brug Kanaal Bossuit \n ",null,null,32690]
["Infrabel","25360","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,36,36,"2021-08-29",44061.03125,"2021-08-29",44061.25,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,25360]
["Infrabel","29903","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,36,36,"2021-08-29",44061.25,"2021-08-29",44061.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29903]
["Infrabel","21334","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,36,36,"2021-08-30",44061.333333333336,"2021-09-03",44061.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations \n ",null,null,21334]
["Infrabel","34841","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,36,36,"2021-08-30",44061.03125,"2021-08-30",44061.208333333336,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,34841]
["Infrabel","27252","Lille - Charleroi","< >","LUTTRE","MANAGE",2021,2021,36,36,"2021-08-30",44061.986111111109,"2021-09-04",44061.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5.52\r\nMise HS P3 HKM - Zone 5 AI52 (Luttre-Manage) \n ",null,null,27252]
["Infrabel","21106","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,36,37,"2021-08-30",44061.986111111109,"2021-09-05",44061.194444444445,"6d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PS 51.035 et du pont du canal - Travaux SPW \n ",null,null,21106]
["Infrabel","17962","Lille - Charleroi","< >","FROYENNES","MOUSCRON",2021,2021,36,50,"2021-08-30",44061.25,"2021-12-06",44061.208333333336,"98d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"-\tRenouvellement de traverses, Rails, passages à niveau\r\n-\tSuppression de passages à niveau\r\n-\tAssainissement\r\n-\tRéalisation de travaux divers aux abords clôture, débroussaillage,… afin de sécuriser notre domaine aux points sensibles (HOT SPOT)\r\n-\tRenou \nomleidingen te specifiëren per week",null,null,17962]
["Infrabel","36407","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,36,36,"2021-08-30",44061.875,"2021-09-04",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \n ",null,null,36407]
["Infrabel","27000","Lille - Charleroi","< >","JURBISE","MONS",2021,2021,36,37,"2021-09-04",44061.25,"2021-09-05",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5.53\r\nMise HS P4 \r\nZone 5 AI 53 \n ",null,null,27000]
["Infrabel","22848","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,36,37,"2021-09-04",44061.079861111109,"2021-09-06",44061.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22848]
["Infrabel","23135","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,36,37,"2021-09-04",44061.072916666664,"2021-09-06",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nTLO WE 1 \n ",null,null,23135]
["Infrabel","20960","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,37,37,"2021-09-06",44061.958333333336,"2021-09-11",44061.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20960]
["Infrabel","23091","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,37,37,"2021-09-06",44061.958333333336,"2021-09-11",44061.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,23091]
["Infrabel","21331","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,37,37,"2021-09-06",44061.333333333336,"2021-09-10",44061.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations\r\nVoie A HS les Lu-Ma-Me-Je-Ve de 08h à 16h\r\nModification faite des dates à la demande de Mr Hennecart (mail Grignard du 20/02/20) \n ",null,null,21331]
["Infrabel","34250","Lille - Charleroi","< >","Y.SOIGNIES","BRAINE-LE-COMTE",2021,2021,37,37,"2021-09-06",44061.979166666664,"2021-09-11",44061.1875,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P3 HKV \n ",null,null,34250]
["Infrabel","27254","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,37,37,"2021-09-06",44061.972222222219,"2021-09-10",44061.222222222219,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P3 HKV \n ",null,null,27254]
["Infrabel","34249","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,37,37,"2021-09-06",44061.982638888891,"2021-09-11",44061.177083333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P3 HKV \n ",null,null,34249]
["Infrabel","34571","Lille - Charleroi","< >","NEUFVILLES","MASNUY-SAINT-PIERRE",2021,2021,37,37,"2021-09-06",44061.982638888891,"2021-09-11",44061.177083333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL de nuit étendues. Rejointoiement et réfection de maçonnerie en voûte (PS 42.540) \n ",null,null,34571]
["Infrabel","21328","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,37,37,"2021-09-11",44061.333333333336,"2021-09-11",44061.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 - Bourrage vitesse normale\r\nModification faite des dates à la demande de Mr Hennecart (mail Grignard du 20/02/20) \nHKM A ADAPTER",null,null,21328]
["Infrabel","22553","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,37,38,"2021-09-11",44061.96875,"2021-09-12",44061.208333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. \n ",null,null,22553]
["Infrabel","34251","Lille - Charleroi","< >","Y.SOIGNIES","BRAINE-LE-COMTE",2021,2021,37,38,"2021-09-11",44061.270833333336,"2021-09-12",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P4+ \n ",null,null,34251]
["Infrabel","27253","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,37,38,"2021-09-11",44061.222222222219,"2021-09-12",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P4+ \n ",null,null,27253]
["Infrabel","24712","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,37,38,"2021-09-11",44061.072916666664,"2021-09-13",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nTLO WE 1 \n ",null,null,24712]
["Infrabel","21329","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,38,38,"2021-09-12",44061.333333333336,"2021-09-12",44061.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 - Réglage des contraintes\r\nModification faite des dates à la demande de Mr Hennecart (mail Grignard du 20/02/20) \nHKM A ADAPTER",null,null,21329]
["Infrabel","22556","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,38,38,"2021-09-12",44061.96875,"2021-09-13",44061.208333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. \n ",null,null,22556]
["Infrabel","20859","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,38,38,"2021-09-13",44061.958333333336,"2021-09-18",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \n",null,null,20859]
["Infrabel","21332","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,38,38,"2021-09-13",44061.333333333336,"2021-09-17",44061.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations\r\nModification faite des dates à la demande de Mr Hennecart (mail Grignard du 20/02/20) \n ",null,null,21332]
["Infrabel","19890","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,38,39,"2021-09-18",44061.958333333336,"2021-09-19",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,19890]
["Infrabel","32378","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,38,39,"2021-09-18",44061.333333333336,"2021-09-20",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,32378]
["Infrabel","22619","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,39,39,"2021-09-19",44061.03125,"2021-09-19",44061.25,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,22619]
["Infrabel","22557","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,39,39,"2021-09-19",44061.96875,"2021-09-20",44061.208333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. \n ",null,null,22557]
["Infrabel","31785","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,39,39,"2021-09-20",44061.958333333336,"2021-09-25",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,31785]
["Infrabel","20860","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,39,39,"2021-09-20",44061.958333333336,"2021-09-25",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nPas de traffic supplémentaire les nuits de CTL. (Doc envoyé le 12/03/18)",null,null,20860]
["Infrabel","21402","Athus - Meuse",">","VONECHE","BEAURAING",2021,2021,39,42,"2021-09-20",44061.333333333336,"2021-10-15",44061.666666666664,"25d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Pose de caniveaux piste\r\nTravail en double prestations \n ",null,null,21402]
["Infrabel","34842","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,39,39,"2021-09-20",44061.03125,"2021-09-20",44061.208333333336,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,34842]
["Infrabel","22216","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,39,40,"2021-09-25",44061.958333333336,"2021-09-26",44061.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22216]
["Infrabel","26879","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,39,40,"2021-09-25",44061.958333333336,"2021-09-26",44061.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nMini CTL \n ",null,null,26879]
["Infrabel","22558","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,39,40,"2021-09-25",44061.96875,"2021-09-26",44061.208333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. \n ",null,null,22558]
["Infrabel","19887","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,39,40,"2021-09-25",44061.25,"2021-09-26",44061.208333333336,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,19887]
["Infrabel","33293","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2021,2021,40,40,"2021-09-26",44061.270833333336,"2021-09-26",44061.625,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Massification \r\nCTL dimanche \n ",null,null,33293]
["Infrabel","30103","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,40,40,"2021-09-27",44061.9375,"2021-10-01",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy - Préparations \n ",null,null,30103]
["Infrabel","31394","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,40,40,"2021-09-27",44061.993055555555,"2021-10-01",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31394]
["Infrabel","31395","Namur - Antwerpen","< >","AISEAU","FARCIENNES",2021,2021,40,41,"2021-10-01",44061.958333333336,"2021-10-04",44061.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31395]
["Infrabel","20268","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2021,2021,40,41,"2021-10-01",44061.979166666664,"2021-10-04",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Démolition PS Norbert Ponlot \n ",null,null,20268]
["Infrabel","18104","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,40,41,"2021-10-01",44061.9375,"2021-10-04",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy \n ",null,null,18104]
["Infrabel","21065","Athus - Meuse","< >","HALANZY","VIRTON",2021,2021,40,41,"2021-10-02",44061.96875,"2021-10-03",44061.208333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement de Virton\r\nBourrage de révision \n ",null,null,21065]
["Infrabel","34254","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,40,41,"2021-10-02",44061.944444444445,"2021-10-03",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P4+ - MINI CTL \n ",null,null,34254]
["Infrabel","10165","Lille - Charleroi","< >","Y.LA SAMBRE","Y.NORD",2021,2021,40,41,"2021-10-02",44061.930555555555,"2021-10-09",44061.194444444445,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,10165]
["Infrabel","19888","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,40,41,"2021-10-02",44061.25,"2021-10-04",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,19888]
["Infrabel","22858","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,40,41,"2021-10-02",44061.079861111109,"2021-10-04",44061.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22858]
["Infrabel","24637","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,40,41,"2021-10-02",44061.079861111109,"2021-10-04",44061.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,24637]
["Infrabel","25829","Lille - Charleroi",">","LUTTRE","MARCHIENNE-AU-PONT",2021,2021,41,44,"2021-10-04",44061.979166666664,"2021-10-25",44061.166666666664,"21d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A\r\n- Coupures L124A voie A\r\n- De nuit uniquement. \n ",null,null,25829]
["Infrabel","9917","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,41,41,"2021-10-04",44061.9375,"2021-10-08",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy \n ",null,null,9917]
["Infrabel","30147","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,41,42,"2021-10-08",44061.958333333336,"2021-10-11",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Reprise en EBP-PLP des installations de Tamines et Auvelais.\r\nPas d'autres services dans la coupure (sauf train d'essais ES et ETCS). \n ",null,null,30147]
["Infrabel","20391","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2021,2021,41,42,"2021-10-08",44061.979166666664,"2021-10-11",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Démolition PS Norbert Ponlot \n ",null,null,20391]
["Infrabel","18105","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,41,42,"2021-10-08",44061.9375,"2021-10-11",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy \n ",null,null,18105]
["Infrabel","20962","Namur - Antwerpen",">","COURT-SAINT-ETIENNE","FAUX",2021,2021,41,42,"2021-10-09",44061.25,"2021-10-10",44061.916666666664,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20962]
["Infrabel","34264","Lille - Charleroi","< >","Y.SOIGNIES","BRAINE-LE-COMTE",2021,2021,42,42,"2021-10-11",44061.979166666664,"2021-10-16",44061.1875,"5d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P3 HKV \n ",null,null,34264]
["Infrabel","30104","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,42,42,"2021-10-11",44061.9375,"2021-10-15",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy - finitions \n ",null,null,30104]
["Infrabel","31397","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,42,42,"2021-10-11",44061.993055555555,"2021-10-16",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31397]
["Infrabel","20963","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,42,43,"2021-10-11",44061.375,"2021-10-17",44061.666666666664,"6d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20963]
["Infrabel","30150","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,42,43,"2021-10-15",44061.958333333336,"2021-10-18",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Reprise en EBP-PLP des installations de Tamines et Auvelais.\r\nPas d'autres services dans la coupure (sauf train d'essais ES et ETCS). \n ",null,null,30150]
["Infrabel","27542","Athus - Meuse","< >","BERTRIX","SAINT-VINCENT-BELLEFONTAINE",2021,2021,42,43,"2021-10-16",44061.958333333336,"2021-10-17",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27542]
["Infrabel","20055","Athus - Meuse",">","BERTRIX","SAINT-VINCENT-BELLEFONTAINE",2021,2021,42,43,"2021-10-16",44061.333333333336,"2021-10-18",44061.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,20055]
["Infrabel","34263","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,42,43,"2021-10-16",44061.944444444445,"2021-10-17",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P4+ \n ",null,null,34263]
["Infrabel","20671","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,43,43,"2021-10-18",44061.958333333336,"2021-10-23",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,20671]
["Infrabel","18077","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,43,44,"2021-10-18",44061.333333333336,"2021-10-27",44061.666666666664,"9d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des traverses (P93) \n ",null,null,18077]
["Infrabel","21236","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2021,2021,43,46,"2021-10-22",44061.958333333336,"2021-11-08",44061.208333333336,"17d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement As 04AL & 04BL & 09AL & 09BL & 10AL & 10BL \nWE 23-24/10/21 - CTL L124-124A -> détournement via L94-96-28 uniquement possible.\r\nWE 30-31/10/21 – CTL L96 -> Détournement via L124-28/3 ou L75 possible\r\nWE 6-7/11/21 - CTL L96 -> Détournement via L75 uniquement possible",null,null,21236]
["Infrabel","27543","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2021,2021,43,44,"2021-10-23",44061.958333333336,"2021-10-24",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27543]
["Infrabel","20449","Erquelinnes - Montzen","< >","HUY","ANDENNE",2021,2021,43,44,"2021-10-23",44061.027777777781,"2021-10-24",44061.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification : renouvellement de rails suite défaut US entre BK 31400 et BK 32000, ... \n ",null,null,20449]
["Infrabel","20959","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,44,44,"2021-10-25",44061.958333333336,"2021-10-29",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20959]
["Infrabel","25831","Lille - Charleroi",">","ROUX","MARCHIENNE-AU-PONT",2021,2021,44,47,"2021-10-25",44061.958333333336,"2021-11-15",44061.25,"21d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A \n ",null,null,25831]
["Infrabel","22733","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,44,45,"2021-10-29",44061.996527777781,"2021-11-01",44061.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,22733]
["Infrabel","27505","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,44,46,"2021-10-30",44061.027777777781,"2021-11-08",44061.177083333336,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 2)\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) \n ",null,null,27505]
["Infrabel","29288","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,44,46,"2021-10-30",44061.020833333336,"2021-11-08",44061.1875,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 PLP SI\r\nL59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel \n ",null,null,29288]
["Infrabel","29605","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,44,46,"2021-10-30",44061.020833333336,"2021-11-08",44061.1875,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"- Omvorming stopplaats Zwijndrecht (FASE 3)\r\n- Verhogen veiligheid Kennedytunnel\r\n- L59 PLP SI \n ",null,null,29605]
["Infrabel","30583","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2021,2021,45,45,"2021-11-02",44061.993055555555,"2021-11-05",44061.208333333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP3HKM \n ",null,null,30583]
["Infrabel","31396","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,45,45,"2021-11-02",44061.993055555555,"2021-11-05",44061.208333333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31396]
["Infrabel","19033","Lille - Charleroi","< >","Y.RUISBROEK","TUBIZE",2021,2021,45,46,"2021-11-06",44061.03125,"2021-11-08",44061.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Overname Halle Fase PLP3.2 \nHKM om te leiden.",null,null,19033]
["Infrabel","29437","Namur - Antwerpen","< >","CHATELET-GRIL EST","CHATELET-GRIL EST",2021,2021,45,46,"2021-11-06",44061.916666666664,"2021-11-07",44061.916666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z17. 51 (P4+)\r\n\r\nMise hors service en une zone (= Zone 17), voici les détails:\r\n- L130 Voie B entre F4-I. 20 et DX-J. 20;\r\nM-I.20 + J-I.20 + PC-I. 20 (faisceau A);\r\n- F6-L. 20 + FX5-I. 20 (L130C en gare de Châtelet);\r\n- GC353-J. 20 + GC354-J \n ",null,null,29437]
["Infrabel","27301","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,45,46,"2021-11-06",44061.291666666664,"2021-11-07",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P4+ \n ",null,null,27301]
["Infrabel","32036","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,45,46,"2021-11-06",44061.25,"2021-11-07",44061.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance  AI 44 (PN + AW) \n ",null,null,32036]
["Infrabel","18079","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,46,48,"2021-11-08",44061.333333333336,"2021-11-21",44061.625,"13d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement de rails \n ",null,null,18079]
["Infrabel","33736","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,46,46,"2021-11-08",44061.979166666664,"2021-11-13",44061.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,33736]
["Infrabel","27302","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,46,46,"2021-11-08",44061.972222222219,"2021-11-13",44061.222222222219,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P3 HKV \n ",null,null,27302]
["Infrabel","31846","Lille - Charleroi","< >","BRUGELETTE","MEVERGNIES-ATTRE",2021,2021,46,46,"2021-11-08",44061.9375,"2021-11-12",44061.201388888891,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTLs de nuit pour préparation renouvellement de l'Aqueduc BK 59.050 \n ",null,null,31846]
["Infrabel","17963","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2021,2021,46,50,"2021-11-08",44061.25,"2021-12-06",44061.208333333336,"28d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"-Renouvellement de traverses,\r\n-Renouvellement des quais de Froyennes\r\n-Renouvellement de chape d’étanchéité\r\n-Renouvellement d’aiguillages\r\n-Renouvellement de rails\r\n-Réalisation de travaux divers aux abords clôture, débroussaillage,… afin de sécuriser \nomleidingen te specifiëren per week",null,null,17963]
["Infrabel","36841","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,46,46,"2021-11-09",44061.006944444445,"2021-11-13",44061.194444444445,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P3 HKM - Zone 9 AI52 \n ",null,null,36841]
["Infrabel","26992","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,46,46,"2021-11-09",44061.006944444445,"2021-11-13",44061.243055555555,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P3 HKM\r\nZone 3 AI 53 \n ",null,null,26992]
["Infrabel","31845","Lille - Charleroi","< >","BRUGELETTE","MEVERGNIES-ATTRE",2021,2021,46,47,"2021-11-12",44061.895833333336,"2021-11-15",44061.229166666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"CTL pour renouvellement complet de l'Aqueduc BK 59.050 \n ",null,null,31845]
["Infrabel","22217","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,46,47,"2021-11-13",44061.958333333336,"2021-11-14",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22217]
["Infrabel","33882","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,46,47,"2021-11-13",44061.958333333336,"2021-11-14",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nP4+ Mini CTL \n ",null,null,33882]
["Infrabel","27545","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,46,47,"2021-11-13",44061.958333333336,"2021-11-14",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27545]
["Infrabel","31876","Lille - Charleroi","< >","LENS","ATH",2021,2021,46,47,"2021-11-13",44061.25,"2021-11-14",44061.916666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réglage CV Brugelette-ATH \n ",null,null,31876]
["Infrabel","37196","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","Y.VAL-SAINT-LAMBERT",2021,2021,47,47,"2021-11-15",44061.965277777781,"2021-11-20",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Z.19.41 - Maintenance P3\r\nCTL en conflit avec travaux L36 \n ",null,null,37196]
["Infrabel","31851","Lille - Charleroi","< >","BRUGELETTE","MEVERGNIES-ATTRE",2021,2021,47,48,"2021-11-19",44061.9375,"2021-11-26",44061.201388888891,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTLs de nuit pour finitions du renouvellement de l'Aqueduc BK 59.050 \n ",null,null,31851]
["Infrabel","31877","Lille - Charleroi","< >","LENS","ATH",2021,2021,47,48,"2021-11-19",44061.993055555555,"2021-11-21",44061.888888888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise en service BA Brugelette/Ath \n ",null,null,31877]
["Infrabel","27547","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,47,48,"2021-11-20",44061.958333333336,"2021-11-21",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27547]
["Infrabel","27804","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,47,48,"2021-11-20",44061.013888888891,"2021-11-22",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"In dienst name van Piloot 3 van de inklinking SIW. Deinze niet bereikbaar vanuit Lichtervelde !! \n ",null,null,27804]
["Infrabel","21039","Lille - Charleroi","< >","Y.LENS","ATH",2021,2021,48,48,"2021-11-22",44061.9375,"2021-11-27",44061.201388888891,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \r\nDéchargement des appareils \n ",null,null,21039]
["Infrabel","33779","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,48,48,"2021-11-22",44061.9375,"2021-11-27",44061.201388888891,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,33779]
["Infrabel","31399","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,48,48,"2021-11-22",44061.993055555555,"2021-11-27",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31399]
["Infrabel","20965","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,48,49,"2021-11-22",44061.375,"2021-11-28",44061.666666666664,"6d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20965]
["Infrabel","30584","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2021,2021,48,49,"2021-11-27",44061.958333333336,"2021-11-28",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nMini CTL \n ",null,null,30584]
["Infrabel","33294","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2021,2021,49,49,"2021-11-28",44061.270833333336,"2021-11-28",44061.625,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Massification \r\nCTL dimanche \n ",null,null,33294]
["Infrabel","26418","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,49,49,"2021-11-29",44061.944444444445,"2021-12-04",44061.243055555555,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P3 HKV - Zone 8 AI52 \n ",null,null,26418]
["Infrabel","31398","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,49,49,"2021-11-29",44061.993055555555,"2021-12-04",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31398]
["Infrabel","22218","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,49,50,"2021-12-04",44061.958333333336,"2021-12-05",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22218]
["Infrabel","26880","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,49,50,"2021-12-04",44061.958333333336,"2021-12-05",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nP4+ Mini CTL \n ",null,null,26880]
["Infrabel","21168","Lille - Charleroi","< >","Y.LA SAMBRE","Y.NORD",2021,2021,49,50,"2021-12-04",44061.972222222219,"2021-12-09",44061.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,21168]
["Infrabel","26423","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,49,50,"2021-12-04",44061.3125,"2021-12-05",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P4+  - Zone 9 AI52 \n ",null,null,26423]
["Infrabel","33773","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,49,50,"2021-12-04",44061.3125,"2021-12-05",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P4 \r\nZone 3 AI 53 \n ",null,null,33773]
["Infrabel","20674","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,50,50,"2021-12-06",44061.958333333336,"2021-12-11",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,20674]
["Infrabel","27247","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,50,50,"2021-12-06",44061.9375,"2021-12-11",44061.170138888891,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51    P3 HKV \n ",null,null,27247]
["Infrabel","23259","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,51,51,"2021-12-13",44061.958333333336,"2021-12-18",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,23259]
["Infrabel","33784","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","KORTRIJK",2021,2021,51,51,"2021-12-13",44061.951388888891,"2021-12-17",44061.236111111109,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.54\r\nP3 HKV\r\nUPM 109515 \nA déterminer",null,null,33784]
["Infrabel","32289","Lille - Charleroi",">","LUTTRE","ROUX",2021,2021,51,52,"2021-12-13",44061.25,"2021-12-20",44061.25,"7d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124-124A FLU-FMR \n ",null,null,32289]
["Infrabel","36273","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE-WIJKSPOREN",2021,2021,51,51,"2021-12-14",44061.010416666664,"2021-12-17",44061.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud sporen en wissels. \n ",null,null,36273]
["Infrabel","32291","Lille - Charleroi",">","ROUX","MARCHIENNE-AU-PONT",2021,2021,52,52,"2021-12-20",44061.25,"2021-12-24",44061.666666666664,"4d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124-124A FLU-FMR \n ",null,null,32291]
["Infrabel","22864","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,52,53,"2021-12-25",44061.079861111109,"2021-12-27",44061.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22864]
["Infrabel","27403","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2022,2022,3,17,"2022-01-10",44061.25,"2022-04-22",44061.625,"102d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réalisation d'une dalle en béton armé pour l'étanchéité de la culée-voûte à la bk 8,509 - côté voie B \nA prévoir au saisonnier\r\n+ ART à prendre en considération",null,null,27403]
["Infrabel","28137","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,4,5,"2022-01-22",44061.979166666664,"2022-01-24",44061.229166666664,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire - Phase 2 : Intervention caténaire \n ",null,null,28137]
["Infrabel","25715","Namur - Antwerpen",">","TAMINES","CHATELET-GRIL EST",2022,2022,6,11,"2022-01-31",44061.9375,"2022-03-12",44061.229166666664,"40d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire - Phase 3 \n ",null,null,25715]
["Infrabel","38790","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,6,16,"2022-02-01",44061.003472222219,"2022-04-11",44061.003472222219,"69d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"L12 Engelselei – waterdichte rokken vervangen\r\nSpoor A L27A eveneens continu buitendienst ( zie andere locaties ) \n ",null,null,38790]
["Infrabel","38961","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,6,7,"2022-02-05",44061.25,"2022-02-07",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - voorbereidende werken\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) -> L59 bijkomende isolatoren te plaatsen + DOES L52 \n ",null,null,38961]
["Infrabel","43958","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,7,7,"2022-02-06",44061.041666666664,"2022-02-06",44061.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,43958]
["Infrabel","28769","Lille - Charleroi","< >","LEUZE","TOURNAI",2022,2022,7,8,"2022-02-11",44061.958333333336,"2022-02-14",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 76 \n ",null,null,28769]
["Infrabel","38962","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,7,8,"2022-02-12",44061.041666666664,"2022-02-14",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - voorbereidende werken\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) -> L59 nog bijkomende isolatoren te plaatsen\r\nDoes op L52 ( zie andere locaties ) \n ",null,null,38962]
["Infrabel","30777","Lille - Charleroi","< >","MONS","QUEVY",2022,2022,7,8,"2022-02-12",44061.003472222219,"2022-02-13",44061.996527777781,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise HS pour finitions chantier P 93 + entreiten \n ",null,null,30777]
["Infrabel","32067","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,7,8,"2022-02-12",44061.079861111109,"2022-02-14",44061.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,32067]
["Infrabel","38942","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,8,8,"2022-02-13",44061.041666666664,"2022-02-13",44061.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38942]
["Infrabel","40680","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,8,8,"2022-02-15",44061.083333333336,"2022-02-19",44061.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,40680]
["Infrabel","22729","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,8,9,"2022-02-18",44061.958333333336,"2022-02-21",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,22729]
["Infrabel","38963","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,8,9,"2022-02-19",44061.041666666664,"2022-02-21",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - voorbereidende werken\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) -> L59 bijkomende isolatoren te plaatsen\r\nDoes L52 \n ",null,null,38963]
["Infrabel","30778","Lille - Charleroi","< >","MONS","QUEVY",2022,2022,8,9,"2022-02-19",44061.003472222219,"2022-02-20",44061.996527777781,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise HS pour finitions chantier P 93 + entreiten \n ",null,null,30778]
["Infrabel","38943","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,9,9,"2022-02-20",44061.041666666664,"2022-02-20",44061.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38943]
["Infrabel","28770","Lille - Charleroi","< >","LEUZE","TOURNAI",2022,2022,9,9,"2022-02-21",44061.958333333336,"2022-02-26",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 76\r\nBourrage de révision\r\nAsphaltage\r\nfinitions \n ",null,null,28770]
["Infrabel","29978","Athus - Meuse","< >","Y.NEFFE","HOUYET",2022,2022,9,10,"2022-02-26",44061.25,"2022-02-28",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses à la grue dans 3 tunnels entre BK 8900 et 12100\r\nIncompatible avec Travaux L130 \n ",null,null,29978]
["Infrabel","29933","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,9,11,"2022-02-26",44061.25,"2022-03-06",44061.708333333336,"8d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29933]
["Infrabel","21753","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,9,11,"2022-02-26",44061.041666666664,"2022-03-07",44061.166666666664,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"- Omvorming stopplaats Zwijndrecht (FASE 4)\r\n- Verhogen veiligheid Kennedytunnel\r\n- Bouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) \n ",null,null,21753]
["Infrabel","30754","Lille - Charleroi","< >","MONS","QUEVY",2022,2022,9,10,"2022-02-26",44061.003472222219,"2022-02-27",44061.996527777781,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise HS pour finitions chantier P 93 + entreiten \n ",null,null,30754]
["Infrabel","38944","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,10,10,"2022-02-27",44061.041666666664,"2022-02-27",44061.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38944]
["Infrabel","33011","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2022,2022,10,10,"2022-02-28",44061.041666666664,"2022-03-05",44061.208333333336,"5d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen wissels Y.Parkbrug (in combinatie met langdurige buitendienststelling tussen Ottignie en Sint-Joris-Weert).\r\nStation Heverlee (B-ST): Vernieuwing perronluifel (Annick Locquet) \nOp zesmaandelijkse van 12/12/2019 vragen goederenoperatoren de lijnen 75 en 59 bijkomend open te houden.",null,null,33011]
["Infrabel","40681","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,10,10,"2022-03-01",44061.083333333336,"2022-03-05",44061.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,40681]
["Infrabel","30906","Athus - Meuse","< >","Y.NEFFE","HOUYET",2022,2022,10,11,"2022-03-05",44061.25,"2022-03-07",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses à la grue dans 3 tunnels entre BK 8900 et 12100\r\nIncompatible avec Travaux L130 \n ",null,null,30906]
["Infrabel","30838","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,10,11,"2022-03-05",44061.25,"2022-03-07",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,30838]
["Infrabel","38945","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,11,11,"2022-03-06",44061.041666666664,"2022-03-06",44061.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38945]
["Infrabel","29935","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,11,11,"2022-03-07",44061.916666666664,"2022-03-11",44061.25,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29935]
["Infrabel","40682","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,11,11,"2022-03-08",44061.083333333336,"2022-03-12",44061.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,40682]
["Infrabel","30891","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,11,12,"2022-03-11",44061.979166666664,"2022-03-14",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,30891]
["Infrabel","28760","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,11,12,"2022-03-12",44061.25,"2022-03-14",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28760]
["Infrabel","30907","Athus - Meuse","< >","Y.NEFFE","HOUYET",2022,2022,11,12,"2022-03-12",44061.25,"2022-03-14",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de boueux et entretiens d'appareils de voies (bourrage, nivellement,...) \n ",null,null,30907]
["Infrabel","38946","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,12,12,"2022-03-13",44061.041666666664,"2022-03-13",44061.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38946]
["Infrabel","14729","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,12,15,"2022-03-14",44061.979166666664,"2022-04-08",44061.1875,"25d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs P93\r\nPréparations/finitions \n ",null,null,14729]
["Infrabel","25727","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,12,13,"2022-03-14",44061.9375,"2022-03-25",44061.229166666664,"11d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire Phase 4 : Travaux Voie sur CTL de nuits semaine\r\nPréparation plateforme 64BJ + drainage, etc.\r\nCTL de nuits en semaine, les nuits en 22h30/05h30 :\r\nVB + VA L130 entre les signaux DX-J.20 + J2-M.20 + D-J. 20 et JX1-M. 20 (en une \n ",null,null,25727]
["Infrabel","29936","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,12,12,"2022-03-14",44061.916666666664,"2022-03-18",44061.25,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29936]
["Infrabel","28762","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,12,13,"2022-03-19",44061.25,"2022-03-21",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780\r\nIncompatible avec travaux Marchienne-au-Pont \n ",null,null,28762]
["Infrabel","38967","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,12,13,"2022-03-19",44061.25,"2022-03-21",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - afwerking\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) +\r\nDoes L52 \n ",null,null,38967]
["Infrabel","22854","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,12,13,"2022-03-19",44061.041666666664,"2022-03-21",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22854]
["Infrabel","41769","Lille - Antwerpen","< >","DEINZE","GENT-SINT-PIETERS",2022,2022,12,13,"2022-03-19",44061.083333333336,"2022-03-21",44061.125,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Wissels FGSP+De Pinte (FGSP SpIV+SpV -Deinze) \n ",null,null,41769]
["Infrabel","14725","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,12,13,"2022-03-19",44061.034722222219,"2022-03-21",44061.173611111109,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs L 96 avec P93 \n ",null,null,14725]
["Infrabel","38947","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,13,13,"2022-03-20",44061.041666666664,"2022-03-20",44061.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38947]
["Infrabel","39304","Lille - Antwerpen",">","MOUSCRON","KORTRIJK",2022,2022,13,13,"2022-03-21",44061.951388888891,"2022-03-26",44061.236111111109,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 1 – Fondations\r\nPhase 1.2. Forage des pieux dans le quai II-III \nA adapter",null,null,39304]
["Infrabel","29937","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,13,13,"2022-03-21",44061.916666666664,"2022-03-25",44061.25,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29937]
["Infrabel","30892","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,13,14,"2022-03-25",44061.979166666664,"2022-03-28",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,30892]
["Infrabel","25730","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,13,14,"2022-03-25",44061.979166666664,"2022-03-28",44061.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire Phase 5 : Week-end n°1\r\nPose nouveau 64BJ en site propre + voies L130vB.\r\nVB + VA L130 entre les signaux DX-J.20 + J2-M.20 + D-J. 20 et JX1-M. 20 (en une zone de mise HS).\r\nMise hors tension cas 27442, 27440, 27438,27436, 27443 \n ",null,null,25730]
["Infrabel","37623","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2022,2022,13,14,"2022-03-26",44061.25,"2022-03-27",44061.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Spanningsregeling, herziening, ...: Vernieuwen wissels Y.Parkbrug\r\nStation Heverlee (B-ST): Vernieuwing perronluifel (Annick Locquet) \n",null,null,37623]
["Infrabel","28785","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,13,14,"2022-03-26",44061.25,"2022-03-28",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28785]
["Infrabel","41865","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2022,2022,13,14,"2022-03-26",44061.083333333336,"2022-03-28",44061.125,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud (Deinze-Kortrijk) \n ",null,null,41865]
["Infrabel","14726","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,13,14,"2022-03-26",44061.034722222219,"2022-03-28",44061.173611111109,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs L 96 avec P93 \n ",null,null,14726]
["Infrabel","32072","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,13,14,"2022-03-26",44061.079861111109,"2022-03-28",44061.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,32072]
["Infrabel","38948","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,14,14,"2022-03-27",44061.041666666664,"2022-03-27",44061.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38948]
["Infrabel","30780","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,14,14,"2022-03-28",44061.9375,"2022-04-01",44061.229166666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 6 : Travaux Voie sur CTL de nuits semaine\r\nPréparation plateforme 64BJ + drainage, etc….\r\nCTL de nuits en semaine, les nuits en 22h30/05h30\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hors tensio \n ",null,null,30780]
["Infrabel","29938","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,14,14,"2022-03-28",44061.916666666664,"2022-04-01",44061.25,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29938]
["Infrabel","30781","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,14,15,"2022-04-01",44061.979166666664,"2022-04-04",44061.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 7 : Week-end n°2\r\nMise en place de la voie B / L130 et renouvellement.\r\nCTL WE n°2, du vendredi 25/03/2022 à 22h30 en continu jusqu’au lundi 28/03/2022 à 05h :\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ. \n ",null,null,30781]
["Infrabel","28790","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,14,15,"2022-04-02",44061.25,"2022-04-04",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28790]
["Infrabel","22849","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,14,15,"2022-04-02",44061.041666666664,"2022-04-04",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22849]
["Infrabel","24634","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,14,15,"2022-04-02",44061.041666666664,"2022-04-04",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,24634]
["Infrabel","30303","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,14,15,"2022-04-02",44061.041666666664,"2022-04-04",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30303]
["Infrabel","14727","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,14,15,"2022-04-02",44061.034722222219,"2022-04-04",44061.173611111109,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs P93\r\nContraintes \n ",null,null,14727]
["Infrabel","43959","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,15,15,"2022-04-03",44061.041666666664,"2022-04-03",44061.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,43959]
["Infrabel","30785","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,15,15,"2022-04-04",44061.9375,"2022-04-09",44061.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 8 : Travaux Voie sur CTL de nuits semaine\r\nFinition W-e 2 + drainage, etc….\r\nCTL de nuits en semaine, les nuits en 22h30/05h30 :\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hors tension cas 27319 \n ",null,null,30785]
["Infrabel","28955","Lille - Charleroi","< >","Y.LA SAMBRE","Y.NORD",2022,2022,15,16,"2022-04-09",44061.930555555555,"2022-04-16",44061.194444444445,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,28955]
["Infrabel","28794","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,15,16,"2022-04-09",44061.25,"2022-04-11",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28794]
["Infrabel","43960","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,16,16,"2022-04-10",44061.041666666664,"2022-04-10",44061.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,43960]
["Infrabel","38666","Lille - Charleroi","< >","MARCHIENNE-AU-PONT","Y.NORD",2022,2022,16,17,"2022-04-11",44061.979166666664,"2022-04-22",44061.1875,"11d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 2bis \n ",null,null,38666]
["Infrabel","39393","Lille - Antwerpen",">","MOUSCRON","KORTRIJK",2022,2022,16,16,"2022-04-11",44061.951388888891,"2022-04-16",44061.236111111109,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 2 – Fondations\r\nPhase 2.1. Dalle quai II-III \nA adapter",null,null,39393]
["Infrabel","28146","Namur - Antwerpen",">","TAMINES","CHATELET-GRIL EST",2022,2022,16,17,"2022-04-11",44061.9375,"2022-04-23",44061.229166666664,"12d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 9 : Semaines de finition Caténaire, E&S et Voie\r\nFinition Caténaire, E&S et Voie en voie 382 / B L130.\r\nSAVU de semaine, les nuits en 22h30/05h30 :\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hor \n ",null,null,28146]
["Infrabel","34344","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,16,25,"2022-04-11",44061.003472222219,"2022-06-12",44061.003472222219,"62d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 Engelselei – waterdichte rokken vervangen \n ",null,null,34344]
["Infrabel","30846","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,16,16,"2022-04-12",44061.083333333336,"2022-04-16",44061.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,30846]
["Infrabel","20723","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2022,2022,16,17,"2022-04-15",44061.979166666664,"2022-04-18",44061.243055555555,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER Weekend Paques \n ",null,null,20723]
["Infrabel","22853","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,16,17,"2022-04-16",44061.041666666664,"2022-04-18",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22853]
["Infrabel","30305","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,16,17,"2022-04-16",44061.041666666664,"2022-04-19",44061.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\n\r\n+ Paasmaandag \nVia Montzen",null,null,30305]
["Infrabel","38951","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,17,17,"2022-04-17",44061,"2022-04-18",44061.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38951]
["Infrabel","39944","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,17,17,"2022-04-19",44061.958333333336,"2022-04-22",44061.208333333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - nuits préparation \n ",null,null,39944]
["Infrabel","39947","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,17,18,"2022-04-22",44061.958333333336,"2022-04-25",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - renouvellement \n ",null,null,39947]
["Infrabel","30791","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,17,18,"2022-04-23",44061.020833333336,"2022-04-25",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Y La Sambre - 4 AS - 17AF/BF (simpl), 19AF/BF, 20F, 18F + quai Marchienne \n ",null,null,30791]
["Infrabel","22852","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,17,18,"2022-04-23",44061.041666666664,"2022-04-25",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22852]
["Infrabel","30306","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,17,18,"2022-04-23",44061.041666666664,"2022-04-25",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30306]
["Infrabel","38952","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,18,18,"2022-04-24",44061,"2022-04-25",44061.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38952]
["Infrabel","27245","Athus - Meuse",">","HOUYET","BEAURAING",2022,2022,18,24,"2022-04-25",44061.333333333336,"2022-06-05",44061.75,"41d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing \n ",null,null,27245]
["Infrabel","38904","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,18,23,"2022-04-25",44061.923611111109,"2022-05-30",44061.215277777781,"35d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,38904]
["Infrabel","29920","Erquelinnes - Montzen","< >","STATTE","JAVA",2022,2022,18,19,"2022-04-29",44061.958333333336,"2022-05-02",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte \n ",null,null,29920]
["Infrabel","29026","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,18,19,"2022-04-29",44061.944444444445,"2022-05-02",44061.222222222219,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \n",null,null,29026]
["Infrabel","30861","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,18,19,"2022-04-29",44061.923611111109,"2022-05-02",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,30861]
["Infrabel","33946","Athus - Meuse","< >","HOUYET","BEAURAING",2022,2022,18,19,"2022-04-30",44061.958333333336,"2022-05-01",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing \n ",null,null,33946]
["Infrabel","30793","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,18,19,"2022-04-30",44061.020833333336,"2022-05-02",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 3 - WE 1/4 \n ",null,null,30793]
["Infrabel","41301","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,18,19,"2022-04-30",44061.25,"2022-05-02",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - renouvellement \n ",null,null,41301]
["Infrabel","22851","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,18,19,"2022-04-30",44061.041666666664,"2022-05-02",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22851]
["Infrabel","30308","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,18,19,"2022-04-30",44061.041666666664,"2022-05-02",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30308]
["Infrabel","38953","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,19,19,"2022-05-01",44061,"2022-05-02",44061.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38953]
["Infrabel","31685","Lille - Charleroi","< >","LOT","HALLE",2022,2022,19,19,"2022-05-02"," ","2022-05-07"," ","5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,31685]
["Infrabel","30849","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,19,20,"2022-05-02",44061.958333333336,"2022-05-14",44061.208333333336,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL toutes les nuits de semaine pour travaux préparatoires - Pose 2nd tablier des ponts 10&11 \n ",null,null,30849]
["Infrabel","32061","Athus - Meuse",">","BERTRIX","FLORENVILLE",2022,2022,19,20,"2022-05-02",44061.333333333336,"2022-05-09",44061.208333333336,"7d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réglages des contraintes des rails (LRS) mises en voie B en novembre 2021, entre km 82050-89480 \n ",null,null,32061]
["Infrabel","30855","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,19,19,"2022-05-02",44061.979166666664,"2022-05-07",44061.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 10 : Travaux Voie sur CTL de nuits semaine\r\nBourrage révision, contrainte, pose caniveaux pistes, finitions chantier….\r\nCTL de nuits en semaine, les nuits en 22h30/05h30 :\r\n\r\n-\tVoie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\t \n ",null,null,30855]
["Infrabel","38376","Lille - Charleroi","< >","MEVERGNIES-ATTRE","ATH",2022,2022,19,19,"2022-05-02",44061.923611111109,"2022-05-07",44061.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux de préparation pour la construction de passerelles en VA et VB au droit du PI 61.597. Nuits de préparation. \n ",null,null,38376]
["Infrabel","30913","Erquelinnes - Montzen","< >","STATTE","JAVA",2022,2022,19,20,"2022-05-06",44061.958333333336,"2022-05-09",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte \n ",null,null,30913]
["Infrabel","30860","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,19,20,"2022-05-06",44061.923611111109,"2022-05-09",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,30860]
["Infrabel","39107","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,19,20,"2022-05-07",44061.020833333336,"2022-05-09",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 3 - WE 2/4 \n ",null,null,39107]
["Infrabel","37677","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,19,20,"2022-05-07",44061.041666666664,"2022-05-09",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,37677]
["Infrabel","38954","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,20,20,"2022-05-08",44061,"2022-05-09",44061.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38954]
["Infrabel","43615","Lille - Charleroi","< >","LOT","HALLE",2022,2022,20,20,"2022-05-09"," ","2022-05-14"," ","5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,43615]
["Infrabel","30783","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,20,21,"2022-05-09",44061.9375,"2022-05-21",44061.229166666664,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 10 : Travaux Voie sur CTL de nuits semaine\r\nBourrage révision, contrainte, pose caniveaux pistes, finitions chantier….\r\nCTL de nuits en semaine, les nuits en 22h30/05h30\r\n\r\n-\tVoie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMi \n ",null,null,30783]
["Infrabel","38375","Lille - Charleroi","< >","MEVERGNIES-ATTRE","ATH",2022,2022,20,20,"2022-05-09",44061.923611111109,"2022-05-13",44061.215277777781,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux de renouvellement des chapes d'étanchéité des PI 61.597 et 64.126 + construction de passerelles en VA et VB au droit du PI 61.597.\r\nNuits de préparation. \n ",null,null,38375]
["Infrabel","28105","Lille - Charleroi","< >","LUTTRE","Y.NORD",2022,2022,20,21,"2022-05-13",44061.958333333336,"2022-05-16",44061.25,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L. 124A \r\nWeekend en CTL 4 voies en continu\r\nMassifié avec Léoskool \n ",null,null,28105]
["Infrabel","30859","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,20,21,"2022-05-13",44061.923611111109,"2022-05-16",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,30859]
["Infrabel","38379","Lille - Charleroi","< >","MEVERGNIES-ATTRE","ATH",2022,2022,20,21,"2022-05-13",44061.923611111109,"2022-05-16",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux de renouvellement des chapes d'étanchéité des PI 61.597 et 64.126 + construction de passerelles en VA et VB au droit du PI 61.597.\r\nCTL de we pour la réalisation des travaux. \n ",null,null,38379]
["Infrabel","33944","Athus - Meuse","< >","HOUYET","BEAURAING",2022,2022,20,21,"2022-05-14",44061.958333333336,"2022-05-15",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing \n ",null,null,33944]
["Infrabel","39310","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,20,21,"2022-05-14",44061.958333333336,"2022-05-16",44061.208333333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 3 – Pose des Piles \n ",null,null,39310]
["Infrabel","39108","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,20,21,"2022-05-14",44061.020833333336,"2022-05-16",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 3 - WE 3/4 \n ",null,null,39108]
["Infrabel","37678","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,20,21,"2022-05-14",44061.041666666664,"2022-05-16",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,37678]
["Infrabel","38955","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,21,21,"2022-05-15",44061,"2022-05-16",44061.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38955]
["Infrabel","43616","Lille - Charleroi","< >","LOT","HALLE",2022,2022,21,21,"2022-05-16"," ","2022-05-20"," ","4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,43616]
["Infrabel","30914","Erquelinnes - Montzen","< >","STATTE","JAVA",2022,2022,21,21,"2022-05-16",44061.958333333336,"2022-05-21",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte\r\nBourrage + tx finition \n ",null,null,30914]
["Infrabel","38377","Lille - Charleroi","< >","MEVERGNIES-ATTRE","ATH",2022,2022,21,21,"2022-05-16",44061.923611111109,"2022-05-21",44061.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux de renouvellement des chapes d'étanchéité des PI 61.597 et 64.126 + construction de passerelles en VA et VB au droit du PI 61.597. Nuits de finitions. \n ",null,null,38377]
["Infrabel","30858","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,21,22,"2022-05-20",44061.923611111109,"2022-05-23",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,30858]
["Infrabel","39311","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,21,22,"2022-05-21",44061.958333333336,"2022-05-23",44061.208333333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 3 – Pose des Piles \n ",null,null,39311]
["Infrabel","39109","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,21,22,"2022-05-21",44061.020833333336,"2022-05-23",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 3 - WE 4/4 \n ",null,null,39109]
["Infrabel","37679","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,21,22,"2022-05-21",44061.041666666664,"2022-05-23",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,37679]
["Infrabel","38956","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,22,22,"2022-05-22",44061,"2022-05-23",44061.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38956]
["Infrabel","38378","Lille - Charleroi","< >","MEVERGNIES-ATTRE","ATH",2022,2022,22,22,"2022-05-23",44061.923611111109,"2022-05-28",44061.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux de renouvellement des chapes d'étanchéité des PI 61.597 et 64.126 + construction de passerelles en VA et VB au droit du PI 61.597. Nuits de finitions. \n ",null,null,38378]
["Infrabel","21040","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,22,23,"2022-05-27",44061.923611111109,"2022-05-30",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,21040]
["Infrabel","33945","Athus - Meuse","< >","HOUYET","BEAURAING",2022,2022,22,23,"2022-05-28",44061.958333333336,"2022-05-29",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing \n ",null,null,33945]
["Infrabel","38957","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,23,23,"2022-05-29",44061,"2022-05-30",44061.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38957]
["Infrabel","30847","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,23,23,"2022-05-31",44061.083333333336,"2022-06-04",44061.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,30847]
["Infrabel","39397","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,23,24,"2022-06-04",44061.958333333336,"2022-06-06",44061.208333333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 4 – Pose des tabliers \n ",null,null,39397]
["Infrabel","41717","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,23,24,"2022-06-04",44061.25,"2022-06-07",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nDétournement via L130A",null,null,41717]
["Infrabel","39395","Lille - Antwerpen",">","KORTRIJK","MOUSCRON",2022,2022,23,23,"2022-06-04",44061.583333333336,"2022-06-04",44061.958333333336,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 4 – Pose des tabliers \nFaisceau Mouscron inaccessible",null,null,39395]
["Infrabel","38958","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,24,24,"2022-06-05",44061,"2022-06-06",44061.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38958]
["Infrabel","31686","Lille - Charleroi","< >","LOT","HALLE",2022,2022,24,24,"2022-06-06"," ","2022-06-11"," ","5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,31686]
["Infrabel","41718","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,24,24,"2022-06-07",44061.208333333336,"2022-06-07",44061.666666666664,"0d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",null,null,41718]
["Infrabel","39113","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,24,25,"2022-06-11",44061.020833333336,"2022-06-13",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 4 - WE 1/5 \nA détourner",null,null,39113]
["Infrabel","39023","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,24,25,"2022-06-11",44061.25,"2022-06-13",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nDétournement via L130A",null,null,39023]
["Infrabel","28811","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,24,25,"2022-06-11",44061.25,"2022-06-13",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28811]
["Infrabel","43617","Lille - Charleroi","< >","LOT","HALLE",2022,2022,25,25,"2022-06-13"," ","2022-06-18"," ","5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,43617]
["Infrabel","30845","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,25,25,"2022-06-13",44061.958333333336,"2022-06-18",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL toutes les nuits de semaine pour travaux préparatoires - Pose 2nd tablier des ponts 10&11 \n ",null,null,30845]
["Infrabel","39990","Namur - Antwerpen",">","FLEURUS","TILLY",2022,2022,25,28,"2022-06-13",44061.333333333336,"2022-07-03",44061.708333333336,"20d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Chantier 1 - Renouvellement de traverses P93 - Fleurus-Tilly \n ",null,null,39990]
["Infrabel","39024","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,25,25,"2022-06-13",44061.208333333336,"2022-06-13",44061.666666666664,"0d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",null,null,39024]
["Infrabel","39994","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,25,26,"2022-06-17",44061.979166666664,"2022-06-20",44061.229166666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 1 - Renouvellement de traverses P93 - Fleurus-Tilly\r\nWE 1/4 \n ",null,null,39994]
["Infrabel","39022","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,25,26,"2022-06-17",44061.916666666664,"2022-06-20",44061.666666666664,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",null,null,39022]
["Infrabel","39114","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,25,26,"2022-06-18",44061.020833333336,"2022-06-20",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 4 - WE 2/5 \nA détourner",null,null,39114]
["Infrabel","29298","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,25,26,"2022-06-18",44061.25,"2022-06-20",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nDétournement via L130A",null,null,29298]
["Infrabel","28895","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,25,26,"2022-06-18",44061.25,"2022-06-20",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28895]
["Infrabel","39954","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,25,26,"2022-06-18",44061.25,"2022-06-20",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"PN123 - renouvellement \n ",null,null,39954]
["Infrabel","43618","Lille - Charleroi","< >","LOT","HALLE",2022,2022,26,26,"2022-06-20"," ","2022-06-24"," ","4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,43618]
["Infrabel","41465","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,26,26,"2022-06-20",44061.958333333336,"2022-06-25",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL toutes les nuits de semaine pour travaux préparatoires - Pose 2nd tablier des ponts 10&11 \n ",null,null,41465]
["Infrabel","28896","Athus - Meuse",">","FLORENVILLE","BERTRIX",2022,2022,26,26,"2022-06-20",44061.333333333336,"2022-06-21",44061.666666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28896]
["Infrabel","39995","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,26,27,"2022-06-24",44061.958333333336,"2022-06-27",44061.229166666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 1 - Renouvellement de traverses P93 - Fleurus-Tilly\r\nWE 2/4 \n ",null,null,39995]
["Infrabel","28899","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2022,2022,26,27,"2022-06-25",44061.958333333336,"2022-06-26",44061.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28899]
["Infrabel","39115","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,26,27,"2022-06-25",44061.020833333336,"2022-06-27",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 4 - WE 3/5 \nA détourner",null,null,39115]
["Infrabel","39945","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,27,27,"2022-06-27",44061.958333333336,"2022-07-01",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - nuits préparation \n ",null,null,39945]
["Infrabel","39955","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,27,27,"2022-06-27",44061.958333333336,"2022-07-01",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN123 \n ",null,null,39955]
["Infrabel","40684","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,27,27,"2022-06-28",44061.083333333336,"2022-07-02",44061.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,40684]
["Infrabel","31886","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,27,28,"2022-07-01",44061.958333333336,"2022-07-04",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,31886]
["Infrabel","39026","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,27,28,"2022-07-01",44061.916666666664,"2022-07-04",44061.666666666664,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",null,null,39026]
["Infrabel","39116","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,27,28,"2022-07-02",44061.020833333336,"2022-07-04",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 4 - WE 4/5 \nA détourner",null,null,39116]
["Infrabel","30901","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,27,28,"2022-07-02",44061.25,"2022-07-04",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,30901]
["Infrabel","41313","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,27,28,"2022-07-02",44061.25,"2022-07-04",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - renouvellement \n ",null,null,41313]
["Infrabel","39027","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,28,29,"2022-07-08",44061.916666666664,"2022-07-11",44061.666666666664,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",null,null,39027]
["Infrabel","39110","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,28,29,"2022-07-09",44061.020833333336,"2022-07-11",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 4 - WE 5/5 \nA détourner",null,null,39110]
["Infrabel","30902","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,28,29,"2022-07-09",44061.25,"2022-07-11",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,30902]
["Infrabel","41314","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,28,29,"2022-07-09",44061.25,"2022-07-11",44061.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - renouvellement \n ",null,null,41314]
["Infrabel","31887","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,29,30,"2022-07-15",44061.958333333336,"2022-07-18",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,31887]
["Infrabel","29749","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2022,2022,32,33,"2022-08-05",44061.979166666664,"2022-08-08",44061.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre \nHKM détourné via :\r\n- Athus-Meuse - L161\r\n- L144 - L130 - L130A",null,null,29749]
["Infrabel","33931","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,32,33,"2022-08-06",44061.958333333336,"2022-08-07",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \n ",null,null,33931]
["Infrabel","28909","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,32,35,"2022-08-06",44061.958333333336,"2022-08-21",44061.666666666664,"15d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \n ",null,null,28909]
["Infrabel","30893","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2022,2022,33,34,"2022-08-12",44061.979166666664,"2022-08-16",44061.1875,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre \nHKM détourné via :\r\n- Athus-Meuse - L161\r\n- L144 - L130 - L130A",null,null,30893]
["Infrabel","31902","Namur - Antwerpen","< >","Y.HOLLAND","Y.DRIEHOEKSTRAAT",2022,2022,34,34,"2022-08-14",44061.041666666664,"2022-08-16",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Project Oude Landen \n ",null,null,31902]
["Infrabel","29430","Namur - Antwerpen",">","CHATELET","CHATELET-GRIL EST",2022,2022,34,34,"2022-08-15",44061.993055555555,"2022-08-19",44061.208333333336,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Aménagement Châtelet – Phase 1 : \r\nRenouvellement des AS 03BJ, 10J, 12J et 13J\r\nPréparations \nFaisceaux B, D, K inaccessible",null,null,29430]
["Infrabel","33932","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,34,35,"2022-08-20",44061.958333333336,"2022-08-21",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \n ",null,null,33932]
["Infrabel","30894","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2022,2022,34,35,"2022-08-20",44061.958333333336,"2022-08-21",44061.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre \n ",null,null,30894]
["Infrabel","27273","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2022,2022,34,35,"2022-08-20",44061.333333333336,"2022-08-22",44061.25,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L144 BK1.100 PS Rue combattant \n ",null,null,27273]
["Infrabel","28910","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,35,36,"2022-08-27",44061.958333333336,"2022-08-28",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \n ",null,null,28910]
["Infrabel","29363","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,36,38,"2022-09-01",44061.989583333336,"2022-09-16",44061.197916666664,"15d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"SAVU de NUIT : travaux préparatoire  grande coupure Grill coté LLN\r\net CTL les NUITs de Weekend \n ",null,null,29363]
["Infrabel","39996","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,36,37,"2022-09-03",44061.25,"2022-09-05",44061.229166666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 1 - Renouvellement de traverses P93 - Fleurus-Tilly\r\nWE 3/4 \n ",null,null,39996]
["Infrabel","30851","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,37,38,"2022-09-05",44061.958333333336,"2022-09-17",44061.208333333336,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL de nuit pour les travaux de finition du second tablier sur les ponts 10 et 11 \n ",null,null,30851]
["Infrabel","36087","Erquelinnes - Montzen",">","BRESSOUX","VISE",2022,2022,37,40,"2022-09-05",44061.291666666664,"2022-09-25",44061.916666666664,"20d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Entretien OA + sécurisation pistes \n ",null,null,36087]
["Infrabel","27248","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,37,38,"2022-09-09",44061.958333333336,"2022-09-12",44061.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD \n ",null,null,27248]
["Infrabel","41340","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,37,38,"2022-09-09",44061.923611111109,"2022-09-12",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 \n ",null,null,41340]
["Infrabel","30890","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,37,53,"2022-09-10",44061,"2022-12-31",44061.25,"112d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes \n ",null,null,30890]
["Infrabel","39997","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,37,38,"2022-09-10",44061.25,"2022-09-12",44061.229166666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 1 - Renouvellement de traverses P93 - Fleurus-Tilly\r\nWE 4/4 \n ",null,null,39997]
["Infrabel","30915","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,38,39,"2022-09-16",44061.958333333336,"2022-09-19",44061.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD \n ",null,null,30915]
["Infrabel","30866","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,38,39,"2022-09-16",44061.923611111109,"2022-09-19",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 \n ",null,null,30866]
["Infrabel","41868","Lille - Antwerpen","< >","DE PINTE","Y.ZANDBERG",2022,2022,38,39,"2022-09-17",44061.25,"2022-09-19",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Indienstname SIW in Deinze(I-Build ETCS)  - Waregem \n ",null,null,41868]
["Infrabel","44093","Namur - Antwerpen","< >","Y.HOLLAND","Y.DRIEHOEKSTRAAT",2022,2022,38,38,"2022-09-17",44061.041666666664,"2022-09-17",44061.166666666664,"0d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Project Oude Landen \n ",null,null,44093]
["Infrabel","37680","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,38,39,"2022-09-17",44061.041666666664,"2022-09-19",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,37680]
["Infrabel","29364","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,39,39,"2022-09-19",44061.989583333336,"2022-09-24",44061.197916666664,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"SAVU de NUIT : travaux préparatoire  grande coupure Grill coté LLN\r\net CTL les NUITs de Weekend \n ",null,null,29364]
["Infrabel","30916","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,39,40,"2022-09-23",44061.958333333336,"2022-09-26",44061.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD \n ",null,null,30916]
["Infrabel","41341","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,39,40,"2022-09-23",44061.923611111109,"2022-09-26",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 \n ",null,null,41341]
["Infrabel","30315","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,39,40,"2022-09-24",44061.041666666664,"2022-09-26",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30315]
["Infrabel","30567","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,39,40,"2022-09-24",44061.041666666664,"2022-09-26",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30567]
["Infrabel","36089","Erquelinnes - Montzen",">","BRESSOUX","VISE",2022,2022,40,43,"2022-09-26",44061.291666666664,"2022-10-16",44061.916666666664,"20d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Entretien OA \n ",null,null,36089]
["Infrabel","20891","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,40,41,"2022-09-30",44061.989583333336,"2022-10-08",44061.197916666664,"8d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"SAVU de NUIT : travaux préparatoire  grande coupure Grill coté LLN\r\net CTL les NUITs de Weekend \n ",null,null,20891]
["Infrabel","41342","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,40,41,"2022-09-30",44061.923611111109,"2022-10-03",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 \n ",null,null,41342]
["Infrabel","22850","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,40,41,"2022-10-01",44061.041666666664,"2022-10-03",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22850]
["Infrabel","30318","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,40,41,"2022-10-01",44061.041666666664,"2022-10-03",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30318]
["Infrabel","38869","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,41,41,"2022-10-03",44061.958333333336,"2022-10-08",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart \n ",null,null,38869]
["Infrabel","28779","Lille - Charleroi","< >","FROYENNES","BLANDAIN-FRONTIERE",2022,2022,41,42,"2022-10-07",44061.958333333336,"2022-10-10",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 2 - 8 - 10 \n ",null,null,28779]
["Infrabel","38892","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,41,42,"2022-10-07",44061.979166666664,"2022-10-10",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 1/4 \n ",null,null,38892]
["Infrabel","33949","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,41,42,"2022-10-08",44061.958333333336,"2022-10-09",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,33949]
["Infrabel","30311","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,41,42,"2022-10-08",44061.041666666664,"2022-10-10",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30311]
["Infrabel","30563","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,41,42,"2022-10-08",44061.041666666664,"2022-10-10",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30563]
["Infrabel","17167","Namur - Antwerpen","< >","TILLY","FLEURUS",2022,2022,42,42,"2022-10-10",44061.958333333336,"2022-10-14",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Nuits pour travaux préparatoires Rnvlt du Tablier métallique situé Bk 47.290 \n ",null,null,17167]
["Infrabel","38871","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,42,42,"2022-10-10",44061.958333333336,"2022-10-15",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart \n ",null,null,38871]
["Infrabel","31904","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,42,43,"2022-10-14",44061.958333333336,"2022-10-17",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,31904]
["Infrabel","38901","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,42,43,"2022-10-14",44061.979166666664,"2022-10-17",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 2/4 \n ",null,null,38901]
["Infrabel","33950","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,42,43,"2022-10-15",44061.958333333336,"2022-10-16",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,33950]
["Infrabel","28780","Lille - Charleroi","< >","FROYENNES","BLANDAIN-FRONTIERE",2022,2022,43,43,"2022-10-17",44061.958333333336,"2022-10-22",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 2 - 8 - 10\r\nBourrage de révision\r\nAsphaltage\r\nFinitions \n ",null,null,28780]
["Infrabel","27256","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,43,47,"2022-10-17",44061.333333333336,"2022-11-13",44061.333333333336,"27d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement quais de Lustin + sécurisation paroi Godinne \n ",null,null,27256]
["Infrabel","29368","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,43,45,"2022-10-17",44061.989583333336,"2022-10-30",44061.197916666664,"13d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"SAVU de NUIT : travaux préparatoire  grande coupure Grill coté LLN\r\net CTL les NUITS S/D, D/L dans les blancs travaux \n ",null,null,29368]
["Infrabel","17166","Namur - Antwerpen","< >","TILLY","FLEURUS",2022,2022,43,44,"2022-10-21",44061.958333333336,"2022-10-24",44061.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du Tablier métallique situé Bk 47.290 \n ",null,null,17166]
["Infrabel","33951","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,43,44,"2022-10-22",44061.958333333336,"2022-10-23",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,33951]
["Infrabel","28915","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,43,47,"2022-10-22",44061.958333333336,"2022-11-14",44061.208333333336,"23d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,28915]
["Infrabel","30312","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,43,44,"2022-10-22",44061.041666666664,"2022-10-24",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30312]
["Infrabel","30564","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,43,44,"2022-10-22",44061.041666666664,"2022-10-24",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30564]
["Infrabel","38876","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,44,44,"2022-10-24",44061.9375,"2022-10-29",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart \n ",null,null,38876]
["Infrabel","30853","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,44,44,"2022-10-25",44061.083333333336,"2022-10-29",44061.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,30853]
["Infrabel","38902","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,44,45,"2022-10-28",44061.979166666664,"2022-10-31",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 3/4 \n ",null,null,38902]
["Infrabel","20717","Namur - Antwerpen","< >","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,44,46,"2022-10-28",44061.989583333336,"2022-11-07",44061.197916666664,"10d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER CTL : grill coté LLN \r\nachèvement de Y.LLN et MES des voies latérales \r\n+ assainissement de plateformess \r\n+ pose 5 AW\r\n+ Ripage\r\n+ tvx CAT & sign \n ",null,null,20717]
["Infrabel","33948","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,44,45,"2022-10-29",44061.958333333336,"2022-10-30",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,33948]
["Infrabel","30313","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,44,45,"2022-10-29",44061.041666666664,"2022-10-31",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30313]
["Infrabel","30565","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,44,45,"2022-10-29",44061.041666666664,"2022-10-31",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30565]
["Infrabel","29276","Athus - Meuse","< >","Y.NEFFE","BEAURAING",2022,2022,44,45,"2022-10-29",44061.583333333336,"2022-10-31",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de boueux et entretiens d'appareils de voies (bourrage, nivellement,...) \n ",null,null,29276]
["Infrabel","39946","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,45,45,"2022-10-31",44061.958333333336,"2022-11-04",44061.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - nuits préparation \n ",null,null,39946]
["Infrabel","17168","Namur - Antwerpen","< >","TILLY","FLEURUS",2022,2022,45,46,"2022-10-31",44061.958333333336,"2022-11-07",44061.166666666664,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Nuits pour travaux de finitions Rnvlt du Tablier métallique situé Bk 47.290 \n ",null,null,17168]
["Infrabel","38875","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,45,45,"2022-10-31",44061.9375,"2022-11-05",44061.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart \n ",null,null,38875]
["Infrabel","40685","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,45,45,"2022-11-03",44061.083333333336,"2022-11-05",44061.125,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,40685]
["Infrabel","41319","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,45,46,"2022-11-04",44061.958333333336,"2022-11-07",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - renouvellement \n ",null,null,41319]
["Infrabel","38903","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,45,46,"2022-11-04",44061.979166666664,"2022-11-07",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 4/4 \n ",null,null,38903]
["Infrabel","30848","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,45,46,"2022-11-05",44061.25,"2022-11-07",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,30848]
["Infrabel","41869","Lille - Antwerpen","< >","DE PINTE","Y.ZANDBERG",2022,2022,45,46,"2022-11-05",44061.25,"2022-11-07",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Indienstname SIW in Deinze(I-Build ETCS)  - Waregem \n ",null,null,41869]
["Infrabel","30314","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,45,46,"2022-11-05",44061.041666666664,"2022-11-07",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30314]
["Infrabel","30566","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,45,46,"2022-11-05",44061.041666666664,"2022-11-07",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30566]
["Infrabel","41320","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,46,47,"2022-11-11",44061.25,"2022-11-14",44061.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - renouvellement \n ",null,null,41320]
["Infrabel","41346","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,46,47,"2022-11-11",44061.25,"2022-11-14",44061.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93\r\nFinitions \n ",null,null,41346]
["Infrabel","27255","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,47,50,"2022-11-14",44061.333333333336,"2022-12-09",44061.333333333336,"25d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement quais de Lustin + mise au gabarit pistes Godinne \n ",null,null,27255]
["Infrabel","30850","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,47,47,"2022-11-14",44061.996527777781,"2022-11-18",44061.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,30850]
["Infrabel","28916","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,47,48,"2022-11-19",44061.958333333336,"2022-11-20",44061.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,28916]
["Infrabel","44160","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2022,2022,47,48,"2022-11-19",44061.25,"2022-11-21",44061.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réserve maintenance \n",null,null,44160]
["Infrabel","30316","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,48,49,"2022-11-26",44061.041666666664,"2022-11-28",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30316]
["Infrabel","30568","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,48,49,"2022-11-26",44061.041666666664,"2022-11-28",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30568]
["Infrabel","30317","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,49,50,"2022-12-03",44061.041666666664,"2022-12-05",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30317]
["Infrabel","30569","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,49,50,"2022-12-03",44061.041666666664,"2022-12-05",44061.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30569]
["Infrabel","31304","Lille - Charleroi","< >","LUTTRE","ROUX",2022,2023,50,5,"2022-12-05",44061.291666666664,"2023-01-29",44061.666666666664,"55d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du ballast L124A (C75) \n ",null,null,31304]

{"sheet":"Data","index":4,"n_rows":24,"n_cols":7,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction"]
["SNCF R",87,"Boulogne-Calais",1,"All day",10868,"Signal work"]
[null,null,"Calais-Dunkerque-Hazebrouck",2,"Day",null,"Switch work"]
[null,null,"Calais-Lille-Aulnoye",3,"Night",null,"Catenary work"]
[null,null,"Hazebrouck-Lens-Aulnoye",4,null,null,"Track work"]
[null,null,"Amiens-Douai",5,null,null,"Rail work"]
[null,null,"Paris-Amiens",6,null,null,"Tunnel work"]
[null,null,"Paris-Busigny",7,null,null,"Bridge work"]
[null,null,"Aulnoye-Longuyon",8,null,null,"Misc. Work"]
[null,null,"Longuyon-Metz-Sarrebourg",9,null,null,"Maintanance"]
[null,null,"Longuyon-Nancy-Sarrebourg",10]
[null,null,"Lerouville-Metz",11]
[null,null,"Lerouville-Nancy",12]
[null,null,"Sarrebourg-Basel",13]
[null,null,"Dijon-Toul",14]
[null,null,"Dijon-Lyon",15]
[null,null,"Dijon-Amberieu-Lyon",16]
[null,null,"Lyon-Valence",17]
[null,null,"Valence - Avignon",18]
[null,null,"Avignon-Miramasparouest",19]
[null,null,"Avignon-Miramasparest",20]
[null,null,"Miramas-Marseille",21]
[null,null,"Miramas-Fos-Marseille",22]
[null,null,"Aulnoye-Feignies-Jeumont",23]

{"sheet":"SNCFR","index":5,"n_rows":725,"n_cols":31,"rows_kept":725,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["SNCF Réseau","6650255761_6650161361","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T12:45:00","12:45","2020-12-11T14:15:00","14:15",3421,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","6650255761_6650159761","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2020,9,42,"2020-02-24T09:15:00","09:15","2020-10-16T13:30:00","13:30",868,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","6650255761_6650163761","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2020,1,49,"2020-01-05T23:00:00","23:00","2020-12-06T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","6650255761_6650162161","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T12:45:00","12:45","2020-12-11T13:30:00","13:30",3375,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255761_6650158161","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2020,9,42,"2020-02-24T10:15:00","10:15","2020-10-16T16:00:00","16:00",1029,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","6650255761_6650157361","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T00:10:00","00:10","2020-12-07T03:10:00","03:10",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6650255761_6650156561","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T13:15:00","13:15","2020-12-11T13:45:00","13:45",3300,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","6650255761_6650162961","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2020,1,49,"2020-01-05T23:00:00","23:00","2020-12-06T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","6650255761_6650160561","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T00:10:00","00:10","2020-12-07T03:10:00","03:10",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6650255761_6650158961","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T13:00:00","13:00","2020-12-11T14:15:00","14:15",3563,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650256861_6650095561","Calais-Lille-Aulnoye",">","Lille Lambersart",null,2019,2020,51,50,"2019-12-16T10:19:00","10:19","2020-12-11T11:15:00","11:15",2813,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650256861_6650094761","Calais-Lille-Aulnoye",">","Lille Lambersart",null,2019,2020,51,50,"2019-12-16T11:05:00","11:05","2020-12-11T12:00:00","12:00",3000,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650256261_6650180161","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2019,2020,51,50,"2019-12-16T13:45:00","13:45","2020-12-11T14:18:00","14:18",3575,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650256261_6650177761","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2019,2020,51,49,"2019-12-22T23:00:00","23:00","2020-12-06T02:28:00","02:28",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","6650256261_6650176961","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2020,10,42,"2020-03-02T10:21:00","10:21","2020-10-16T15:14:00","15:14",431,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","6650256261_6650180961","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2019,2020,51,50,"2019-12-16T01:10:00","01:10","2020-12-07T03:45:00","03:45",193,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","6650256261_6650178561","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2020,10,42,"2020-03-02T08:50:00","08:50","2020-10-16T15:05:00","15:05",428,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","6650256261_6650179361","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2019,2020,51,50,"2019-12-16T10:37:00","10:37","2020-12-11T12:05:00","12:05",3022,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255361_6650153961","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2020,11,39,"2020-03-09T23:04:00","23:04","2020-09-25T04:23:00","04:23",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"90 jours dans le régime binaire"]
["SNCF Réseau","6650255361_6650151561","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2019,2020,51,50,"2019-12-16T13:43:00","13:43","2020-12-11T14:09:00","14:09",3537,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255361_6650152361","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2019,2020,51,50,"2019-12-16T10:15:00","10:15","2020-12-11T11:50:00","11:50",2959,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255361_6650153161","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2019,2020,52,42,"2019-12-29T23:00:00","23:00","2020-10-18T02:32:00","02:32",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6650255361_6650154761","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2019,2020,51,43,"2019-12-16T01:36:00","01:36","2020-10-19T04:13:00","04:13",70,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6650255361_6650150761","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2020,11,39,"2020-03-09T22:21:00","22:21","2020-09-25T05:35:00","05:35",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"90 jours dans le régime binaire"]
["SNCF Réseau","6650256761_6650065761","Aulnoye-Longuyon",">","Hirson","Liart",2019,2020,51,50,"2019-12-16T11:45:00","11:45","2020-12-11T13:05:00","13:05",3272,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650256761_6650064161","Aulnoye-Longuyon",">","Hirson","Liart",2020,2020,9,44,"2020-02-24T09:10:00","09:10","2020-10-30T14:35:00","14:35",938,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","6650256761_6650061761","Aulnoye-Longuyon",">","Hirson","Liart",2019,2020,51,50,"2019-12-16T00:30:00","00:30","2020-12-07T03:15:00","03:15",162,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6650256761_6650064961","Aulnoye-Longuyon",">","Hirson","Liart",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:20:00","03:20",166,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6650256761_6650062561","Aulnoye-Longuyon",">","Hirson","Liart",2020,2020,9,44,"2020-02-24T09:30:00","09:30","2020-10-30T14:37:00","14:37",940,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","6650256761_6650063361","Aulnoye-Longuyon",">","Hirson","Liart",2019,2020,51,50,"2019-12-16T14:25:00","14:25","2020-12-11T15:00:00","15:00",3750,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255061_6650134761","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,50,"2019-12-16T10:38:00","10:38","2020-12-11T11:48:00","11:48",2951,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255061_6650135561","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,49,"2019-12-22T00:15:00","00:15","2020-12-06T02:45:00","02:45",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","6650255061_6650137961","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,50,"2019-12-16T13:27:00","13:27","2020-12-11T14:19:00","14:19",3580,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255061_6650136361","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,50,"2019-12-16T10:11:00","10:11","2020-12-11T11:38:00","11:38",2909,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255061_6650133961","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,49,"2019-12-22T23:50:00","23:50","2020-12-06T03:15:00","03:15",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","6650255061_6650132961","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2020,7,47,"2020-02-10T23:00:00","23:00","2020-11-20T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","6650255061_6650137161","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,50,"2019-12-16T13:51:00","13:51","2020-12-11T14:27:00","14:27",3613,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255961_6650058561","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2020,2020,9,49,"2020-02-24T23:00:00","23:00","2020-12-04T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","6650255961_6650056961","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2019,2020,51,50,"2019-12-16T13:57:00","13:57","2020-12-11T14:37:00","14:37",3654,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255961_6650057761","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2019,2020,52,50,"2019-12-23","00:00","2020-12-07T03:10:00","03:10",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6650255961_6650060361","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2019,2020,52,50,"2019-12-23","00:00","2020-12-07T03:00:00","03:00",54,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6650255961_6650059561","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2019,2020,51,50,"2019-12-16T14:30:00","14:30","2020-12-11T15:50:00","15:50",3959,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255561_6650141761","Aulnoye-Longuyon",">","Aulnoye","Hirson",2019,2020,51,50,"2019-12-16T13:15:00","13:15","2020-12-11T13:45:00","13:45",3438,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255561_6650139361","Aulnoye-Longuyon",">","Aulnoye","Hirson",2019,2020,51,50,"2019-12-16T00:55:00","00:55","2020-12-07T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","6650255561_6650143361","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2020,10,44,"2020-03-02T09:14:00","09:14","2020-10-30T15:44:00","15:44",447,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","6650255561_6650142561","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2020,10,44,"2020-03-02T09:59:00","09:59","2020-10-30T15:25:00","15:25",437,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","6650255561_6650140161","Aulnoye-Longuyon",">","Aulnoye","Hirson",2019,2020,51,49,"2019-12-22T23:30:00","23:30","2020-12-06T03:00:00","03:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","6650255561_6650140961","Aulnoye-Longuyon",">","Aulnoye","Hirson",2019,2020,51,50,"2019-12-16T11:20:00","11:20","2020-12-11T12:32:00","12:32",3134,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255561_6650144161","Aulnoye-Longuyon",">","Aulnoye","Hirson",2019,2020,51,50,"2019-12-16T10:59:00","10:59","2020-12-11T12:20:00","12:20",3084,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650256461_6650169361","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2020,2020,15,49,"2020-04-06T23:05:00","23:05","2020-12-04T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"42 jours dans le régime binaire"]
["SNCF Réseau","6650256461_6650170361","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2019,2020,51,50,"2019-12-16T11:22:00","11:22","2020-12-11T12:48:00","12:48",3201,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650256461_6650167761","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2019,2020,51,50,"2019-12-16T10:30:00","10:30","2020-12-11T11:05:00","11:05",2771,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650256461_6650168561","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2019,2020,51,50,"2019-12-16T00:20:00","00:20","2020-12-07T03:20:00","03:20",173,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","6650256461_6650171161","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2019,2020,51,50,"2019-12-16T01:10:00","01:10","2020-12-07T04:10:00","04:10",215,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","6650255461_6650175761","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2019,2020,51,50,"2019-12-16T14:15:00","14:15","2020-12-11T15:20:00","15:20",3834,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255461_6650174761","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2020,2020,14,50,"2020-03-30T23:30:00","23:30","2020-12-11T05:15:00","05:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","6650255461_6650173161","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2019,2020,51,50,"2019-12-16T14:04:00","14:04","2020-12-11T14:55:00","14:55",3730,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650255461_6650173961","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2020,2020,7,49,"2020-02-10","00:00","2020-11-30T03:00:00","03:00",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6650255461_6650172361","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2020,2020,7,49,"2020-02-10","00:00","2020-11-30T03:10:00","03:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6650255861_6650120361","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,1,49,"2020-01-05T23:40:00","23:40","2020-12-06T02:40:00","02:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","6650255861_6650114761","Aulnoye-Longuyon",">","Mohon","Sedan",2019,2020,51,50,"2019-12-16T13:24:00","13:24","2020-12-11T14:11:00","14:11",3404,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","6650255861_6650119561","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,9,42,"2020-02-24T10:07:00","10:07","2020-10-16T14:15:00","14:15",702,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6650255861_6650117961","Aulnoye-Longuyon",">","Mohon","Sedan",2019,2020,51,50,"2019-12-16T13:25:00","13:25","2020-12-11T14:24:00","14:24",3456,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","6650255861_6650113961","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,1,49,"2020-01-05T23:50:00","23:50","2020-12-06T02:50:00","02:50",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","6650255861_6650115561","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,1,49,"2020-01-05T23:40:00","23:40","2020-12-06T02:40:00","02:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","6650255861_6650118761","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,1,49,"2020-01-05T23:50:00","23:50","2020-12-06T02:50:00","02:50",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","6650255861_6650116361","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,9,42,"2020-02-24T10:25:00","10:25","2020-10-16T14:15:00","14:15",702,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6650255861_6650117161","Aulnoye-Longuyon",">","Mohon","Sedan",2019,2020,51,50,"2019-12-16T13:36:00","13:36","2020-12-11T14:51:00","14:51",3565,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","6650256661_6650200361","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2019,2020,51,50,"2019-12-16T09:52:00","09:52","2020-12-11T11:00:00","11:00",2751,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650256661_6650202761","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2019,2020,51,41,"2019-12-16T00:20:00","00:20","2020-10-05T03:00:00","03:00",41,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","6650256661_6650201961","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2019,2020,51,50,"2019-12-16T14:25:00","14:25","2020-12-11T15:08:00","15:08",3784,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650256661_6650199361","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2020,2020,12,50,"2020-03-16T22:43:00","22:43","2020-12-11T04:43:00","04:43",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","6650256661_6650201161","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2019,2020,51,41,"2019-12-16T01:00:00","01:00","2020-10-05T04:00:00","04:00",55,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","6650257061_6650190161","Aulnoye-Longuyon",">","Tournes","Charleville",2019,2020,51,50,"2019-12-16T13:35:00","13:35","2020-12-11T14:40:00","14:40",3521,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","6650257061_6650188561","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2020,1,49,"2020-01-05T23:00:00","23:00","2020-12-06T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","6650257061_6650191761","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2020,9,44,"2020-02-24T09:15:00","09:15","2020-10-30T14:20:00","14:20",779,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
["SNCF Réseau","6650257061_6650190961","Aulnoye-Longuyon",">","Tournes","Charleville",2019,2020,51,50,"2019-12-16T12:25:00","12:25","2020-12-11T13:21:00","13:21",3204,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","6650257061_6650189361","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2020,1,49,"2020-01-05T23:55:00","23:55","2020-12-06T02:55:00","02:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","6650257061_6650187761","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2020,9,44,"2020-02-24T10:00:00","10:00","2020-10-30T14:54:00","14:54",809,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
["SNCF Réseau","6650257261_6650185761","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2019,2020,51,50,"2019-12-16T10:12:00","10:12","2020-12-11T10:53:00","10:53",2721,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650257261_6650183361","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2019,2020,51,43,"2019-12-16T01:00:00","01:00","2020-10-19T03:30:00","03:30",58,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6650257261_6650184161","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2019,2020,51,43,"2019-12-16T00:06:00","00:06","2020-10-19T03:30:00","03:30",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6650257261_6650186561","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2019,2020,51,50,"2019-12-16T11:02:00","11:02","2020-12-11T12:25:00","12:25",3105,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6650257261_6650182561","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2020,11,42,"2020-03-09T22:45:00","22:45","2020-10-16T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"56 jours dans le régime binaire"]
["SNCF Réseau","6650257261_6650184961","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2020,11,42,"2020-03-09T22:12:00","22:12","2020-10-16T04:40:00","04:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"56 jours dans le régime binaire"]
["SNCF Réseau","6650257561_6650089961","Aulnoye-Longuyon",">","Liart","Tournes",2019,2020,51,50,"2019-12-16T14:00:00","14:00","2020-12-11T14:40:00","14:40",3520,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","6650257561_6650091561","Aulnoye-Longuyon",">","Liart","Tournes",2020,2020,9,44,"2020-02-24T09:35:00","09:35","2020-10-30T14:54:00","14:54",809,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
["SNCF Réseau","6650257561_6650089161","Aulnoye-Longuyon",">","Liart","Tournes",2020,2020,1,49,"2020-01-05T23:00:00","23:00","2020-12-06T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","6650257561_6650090761","Aulnoye-Longuyon",">","Liart","Tournes",2020,2020,9,44,"2020-02-24T09:37:00","09:37","2020-10-30T14:20:00","14:20",778,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
["SNCF Réseau","6650257561_6650092361","Aulnoye-Longuyon",">","Liart","Tournes",2019,2020,51,50,"2019-12-16T12:05:00","12:05","2020-12-11T13:21:00","13:21",3205,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","6650257561_6650093161","Aulnoye-Longuyon",">","Liart","Tournes",2020,2020,1,49,"2020-01-05T23:55:00","23:55","2020-12-06T02:55:00","02:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","6648554861_6647973161","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2020,2,36,"2020-01-06T00:25:00","00:25","2020-08-31T03:50:00","03:50",37,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","6648554861_6647969761","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2019,2020,51,50,"2019-12-16T14:00:00","14:00","2020-12-11T15:20:00","15:20",3804,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6648554861_6647974761","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2019,2020,51,50,"2019-12-16T14:17:00","14:17","2020-12-11T15:28:00","15:28",3836,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6648554861_6647970561","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2020,2,36,"2020-01-06T00:50:00","00:50","2020-08-31T03:25:00","03:25",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","6648554861_6647976361","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2020,2,36,"2020-01-06","00:00","2020-08-31T03:00:00","03:00",30,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","6648554861_6647972161","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2020,11,47,"2020-03-09T10:12:00","10:12","2020-11-20T16:12:00","16:12",1253,"DAY",null,null,null,null,null,null,null,null,null,null,null,"78 jours dans le régime binaire"]
["SNCF Réseau","6648554861_6647971361","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2020,1,35,"2020-01-05T23:43:00","23:43","2020-08-30T02:23:00","02:23",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6648554861_6647973961","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2019,2020,51,50,"2019-12-16T10:55:00","10:55","2020-12-11T11:50:00","11:50",2935,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6648554861_6647975561","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2019,2020,51,50,"2019-12-16T11:15:00","11:15","2020-12-11T11:55:00","11:55",2956,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648303961","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,3,44,"2020-01-13T09:30:00","09:30","2020-10-26T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648296761","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2019,2020,51,46,"2019-12-16T14:15:00","14:15","2020-11-13T15:05:00","15:05",2368,"DAY",null,null,null,null,null,null,null,null,null,null,null,"158 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648303161","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,18,48,"2020-04-28T11:30:00","11:30","2020-11-27T15:30:00","15:30",515,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648298361","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,2,50,"2020-01-06","00:00","2020-12-07T03:00:00","03:00",36,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648300761","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2019,2020,51,50,"2019-12-16T13:51:00","13:51","2020-12-11T14:53:00","14:53",2040,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648299961","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,3,44,"2020-01-14T11:30:00","11:30","2020-10-30T15:30:00","15:30",608,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648306361","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2019,2020,51,50,"2019-12-16T09:09:00","09:09","2020-12-11T10:07:00","10:07",1730,"DAY",null,null,null,null,null,null,null,null,null,null,null,"172 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648299161","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2019,2020,51,46,"2019-12-16T11:37:00","11:37","2020-11-13T12:44:00","12:44",2000,"DAY",null,null,null,null,null,null,null,null,null,null,null,"158 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648297561","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,3,44,"2020-01-14T11:30:00","11:30","2020-10-30T15:30:00","15:30",608,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648305561","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,19,48,"2020-05-04T09:30:00","09:30","2020-11-23T15:30:00","15:30",114,"DAY",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648302361","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,3,44,"2020-01-13T09:30:00","09:30","2020-10-26T15:30:00","15:30",68,"DAY",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648301561","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,19,48,"2020-05-04T09:30:00","09:30","2020-11-23T15:30:00","15:30",114,"DAY",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","6648554561_6648304761","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,18,48,"2020-04-28T11:30:00","11:30","2020-11-27T15:30:00","15:30",515,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","6648554961_6648355961","Lerouville-Metz",">","Lerouville","Noveant",2020,2020,9,46,"2020-02-24T23:00:00","23:00","2020-11-13T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6648554961_6648356961","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,51,50,"2019-12-16T10:42:00","10:42","2020-12-11T11:16:00","11:16",2817,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648554961_6648358561","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,51,50,"2019-12-16T14:02:00","14:02","2020-12-11T15:08:00","15:08",3784,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648554961_6648355161","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,52,1,"2019-12-29T22:38:00","22:38","2020-01-05T01:02:00","01:02",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"3 jours dans le régime binaire"]
["SNCF Réseau","6648554961_6648357761","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,51,50,"2019-12-16T10:16:00","10:16","2020-12-11T11:05:00","11:05",2771,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648554961_6648360161","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,51,50,"2019-12-16T13:35:00","13:35","2020-12-11T15:02:00","15:02",3759,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648554961_6648359361","Lerouville-Metz",">","Lerouville","Noveant",2019,2019,52,52,"2019-12-29T23:27:00","23:27","2019-12-29T02:59:00","02:59",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","6648555361_6648148161","Lerouville-Metz",">","Noveant","Metz",2020,2020,12,46,"2020-03-17T23:00:00","23:00","2020-11-13T05:45:00","05:45",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"37 jours dans le régime binaire"]
["SNCF Réseau","6648555361_6648147361","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,50,"2019-12-16T09:20:00","09:20","2020-12-11T10:15:00","10:15",2563,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648555361_6648144961","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,50,"2019-12-16T14:11:00","14:11","2020-12-11T15:05:00","15:05",3771,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648555361_6648145761","Lerouville-Metz",">","Noveant","Metz",2020,2020,4,32,"2020-01-20","00:00","2020-08-03T03:00:00","03:00",30,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","6648555361_6648141761","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,36,"2019-12-16","00:00","2020-08-31T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6648555361_6648144161","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,36,"2019-12-16","00:00","2020-08-31T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6648555361_6648146561","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,50,"2019-12-16T10:48:00","10:48","2020-12-11T11:55:00","11:55",2980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648555361_6648142561","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,50,"2019-12-16T14:09:00","14:09","2020-12-11T15:17:00","15:17",3821,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648555361_6648143361","Lerouville-Metz",">","Noveant","Metz",2020,2020,4,32,"2020-01-20","00:00","2020-08-03T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6648555361_6648149161","Lerouville-Metz",">","Noveant","Metz",2020,2020,11,45,"2020-03-09T22:55:00","22:55","2020-11-06T05:40:00","05:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","6648554061_6648028961","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2020,2,38,"2020-01-06T23:09:00","23:09","2020-09-18T04:35:00","04:35",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"88 jours dans le régime binaire"]
["SNCF Réseau","6648554061_6648028161","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,50,"2019-12-16T14:25:00","14:25","2020-12-11T15:10:00","15:10",3716,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6648554061_6648026561","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,4,"2019-12-16T00:20:00","00:20","2020-01-20T03:50:00","03:50",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","6648554061_6648024161","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,50,"2019-12-16T14:10:00","14:10","2020-12-11T15:00:00","15:00",3675,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6648554061_6648027361","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,3,"2019-12-22T22:40:00","22:40","2020-01-19T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","6648554061_6648024961","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,50,"2019-12-16T09:47:00","09:47","2020-12-11T11:00:00","11:00",2696,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6648554061_6648025761","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,50,"2019-12-16T09:33:00","09:33","2020-12-11T10:47:00","10:47",2643,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6648554061_6648023361","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2020,2,38,"2020-01-06T23:46:00","23:46","2020-09-18T06:20:00","06:20",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"88 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647988561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2019,2020,51,50,"2019-12-16T13:41:00","13:41","2020-12-11T14:44:00","14:44",2004,"DAY",null,null,null,null,null,null,null,null,null,null,null,"137 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647987761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",531,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647989361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,5,46,"2020-01-28T11:30:00","11:30","2020-11-13T15:30:00","15:30",391,"DAY",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647991761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,5,46,"2020-01-28T11:30:00","11:30","2020-11-13T15:30:00","15:30",469,"DAY",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647986961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647986161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2019,2020,51,50,"2019-12-16T09:19:00","09:19","2020-12-11T10:17:00","10:17",2201,"DAY",null,null,null,null,null,null,null,null,null,null,null,"215 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647982961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2019,2020,51,46,"2019-12-16T14:25:00","14:25","2020-11-13T15:21:00","15:21",2318,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647983761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2019,2020,51,46,"2019-12-16T11:27:00","11:27","2020-11-13T12:28:00","12:28",1883,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647990961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",68,"DAY",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647990161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647984561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",469,"DAY",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","6648554361_6647985361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6648554761_6648124361","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T13:25:00","13:25","2020-12-11T14:48:00","14:48",3701,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648554761_6648123561","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T00:27:00","00:27","2020-12-07T03:05:00","03:05",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6648554761_6648122761","Dijon-Toul",">","Culmont","NeufChateau",2020,2020,7,11,"2020-02-10T13:26:00","13:26","2020-03-12T19:14:00","19:14",371,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6648554761_6648125961","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T01:25:00","01:25","2020-12-07T04:51:00","04:51",81,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6648554761_6648119561","Dijon-Toul",">","Culmont","NeufChateau",2020,2020,7,11,"2020-02-10T10:05:00","10:05","2020-03-13T13:48:00","13:48",334,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","6648554761_6648126761","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T13:48:00","13:48","2020-12-11T15:15:00","15:15",3813,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648554761_6648121161","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T10:55:00","10:55","2020-12-11T11:37:00","11:37",2904,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648554761_6648121961","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T01:03:00","01:03","2020-12-07T04:25:00","04:25",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6648554761_6648120361","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,49,"2019-12-22T00:05:00","00:05","2020-12-06T02:37:00","02:37",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6648554761_6648125161","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T10:37:00","10:37","2020-12-11T11:08:00","11:08",2783,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648554261_6648075961","Lerouville-Nancy",">","Toul","Frouard",2020,2020,6,42,"2020-02-03T23:00:00","23:00","2020-10-16T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6648554261_6648078561","Lerouville-Nancy",">","Toul","Frouard",2020,2020,2,3,"2020-01-12T22:55:00","22:55","2020-01-19T02:06:00","02:06",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","6648554261_6648075161","Lerouville-Nancy",">","Toul","Frouard",2019,2020,51,50,"2019-12-16T14:59:00","14:59","2020-12-11T15:42:00","15:42",3784,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","6648554261_6648076961","Lerouville-Nancy",">","Toul","Frouard",2020,2020,2,3,"2020-01-12T22:54:00","22:54","2020-01-19T01:40:00","01:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","6648554261_6648077761","Lerouville-Nancy",">","Toul","Frouard",2019,2020,51,50,"2019-12-16T08:58:00","08:58","2020-12-11T10:16:00","10:16",2567,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648555061_6648169961","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2020,2020,2,36,"2020-01-06","00:00","2020-08-31T03:00:00","03:00",30,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","6648555061_6648172561","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2019,2020,51,50,"2019-12-16T12:17:00","12:17","2020-12-11T12:49:00","12:49",3179,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6648555061_6648171561","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2020,2020,11,47,"2020-03-09T10:10:00","10:10","2020-11-20T16:10:00","16:10",1073,"DAY",null,null,null,null,null,null,null,null,null,null,null,"67 jours dans le régime binaire"]
["SNCF Réseau","6648555061_6648170761","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2019,2020,51,50,"2019-12-16T14:05:00","14:05","2020-12-11T15:32:00","15:32",3853,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6648555061_6648173361","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2020,2020,2,36,"2020-01-06T00:30:00","00:30","2020-08-31T03:30:00","03:30",34,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","6648559161_6648032761","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2020,3,36,"2020-01-13","00:00","2020-08-31T03:24:00","03:24",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648559161_6648031961","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2019,2020,51,50,"2019-12-16T14:32:00","14:32","2020-12-11T15:16:00","15:16",3817,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648559161_6648035361","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2020,3,36,"2020-01-13T00:25:00","00:25","2020-08-31T03:03:00","03:03",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648559161_6648034561","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2019,2020,51,50,"2019-12-16T10:26:00","10:26","2020-12-11T11:42:00","11:42",2926,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648559161_6648033561","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2020,2,37,"2020-01-06T23:35:00","23:35","2020-09-11T05:35:00","05:35",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","6648555861_6648177961","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2019,2020,51,3,"2019-12-22T23:56:00","23:56","2020-01-19T02:56:00","02:56",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","6648555861_6648175361","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2020,2020,6,37,"2020-02-03T23:26:00","23:26","2020-09-11T05:26:00","05:26",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","6648555861_6648176361","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2019,2020,51,50,"2019-12-16T13:35:00","13:35","2020-12-11T14:38:00","14:38",2766,"DAY",null,null,null,null,null,null,null,null,null,null,null,"190 jours dans le régime binaire"]
["SNCF Réseau","6648555861_6648174561","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2019,2020,51,3,"2019-12-22T23:56:00","23:56","2020-01-19T02:56:00","02:56",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","6648555861_6648177161","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2019,2020,51,50,"2019-12-16T09:25:00","09:25","2020-12-11T10:22:00","10:22",2260,"DAY",null,null,null,null,null,null,null,null,null,null,null,"219 jours dans le régime binaire"]
["SNCF Réseau","6648556761_6648377761","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2019,2020,1,32,"2019-12-30T00:15:00","00:15","2020-08-03T03:00:00","03:00",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648556761_6648375361","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2019,2020,52,31,"2019-12-29T22:45:00","22:45","2020-08-02T02:01:00","02:01",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648556761_6648376961","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2019,2020,51,50,"2019-12-16T14:07:00","14:07","2020-12-11T15:17:00","15:17",3791,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6648556761_6648376161","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2019,2020,51,50,"2019-12-16T10:51:00","10:51","2020-12-11T11:41:00","11:41",2092,"DAY",null,null,null,null,null,null,null,null,null,null,null,"180 jours dans le régime binaire"]
["SNCF Réseau","6648556761_6648374361","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2020,2020,9,42,"2020-02-24T23:00:00","23:00","2020-10-16T05:40:00","05:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"54 jours dans le régime binaire"]
["SNCF Réseau","6648559761_6648251961","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2019,2020,51,50,"2019-12-16T13:20:00","13:20","2020-12-11T13:40:00","13:40",3416,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648559761_6648251161","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2019,2019,51,52,"2019-12-22T23:00:00","23:00","2019-12-29T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"3 jours dans le régime binaire"]
["SNCF Réseau","6648559761_6648252761","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2019,2020,51,50,"2019-12-16T11:30:00","11:30","2020-12-11T13:15:00","13:15",3314,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648559761_6648253561","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2020,2020,8,39,"2020-02-17T10:30:00","10:30","2020-09-25T16:30:00","16:30",1144,"DAY",null,null,null,null,null,null,null,null,null,null,null,"70 jours dans le régime binaire"]
["SNCF Réseau","6648559761_6648250361","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2019,2019,51,52,"2019-12-22T23:00:00","23:00","2019-12-29T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"3 jours dans le régime binaire"]
["SNCF Réseau","6648558461_6648046961","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2020,2020,2,38,"2020-01-06T23:10:00","23:10","2020-09-18T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"81 jours dans le régime binaire"]
["SNCF Réseau","6648558461_6648045361","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2020,2020,2,38,"2020-01-06T23:41:00","23:41","2020-09-18T05:46:00","05:46",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"80 jours dans le régime binaire"]
["SNCF Réseau","6648558461_6648046161","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2019,2020,51,50,"2019-12-16T09:44:00","09:44","2020-12-11T10:50:00","10:50",2709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648558461_6648047761","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2019,2020,51,50,"2019-12-16T14:25:00","14:25","2020-12-11T15:20:00","15:20",3834,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648559561_6648246361","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2020,2020,2,38,"2020-01-06T23:14:00","23:14","2020-09-18T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"85 jours dans le régime binaire"]
["SNCF Réseau","6648559561_6648247361","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2019,2020,51,50,"2019-12-16T14:26:00","14:26","2020-12-11T15:23:00","15:23",3846,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648559561_6648248161","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2019,2020,51,50,"2019-12-16T09:46:00","09:46","2020-12-11T10:44:00","10:44",2684,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648557061_6647998961","Lerouville-Nancy",">","Frouard","Jarville",2020,2020,2,38,"2020-01-06T23:05:00","23:05","2020-09-18T05:16:00","05:16",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"86 jours dans le régime binaire"]
["SNCF Réseau","6648557061_6647999761","Lerouville-Nancy",">","Frouard","Jarville",2020,2020,2,38,"2020-01-06T23:11:00","23:11","2020-09-18T05:07:00","05:07",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"86 jours dans le régime binaire"]
["SNCF Réseau","6648557761_6648181161","Longuyon-Metz-Sarrebourg","<","Metz sablon via MetzVille",null,2020,2020,4,37,"2020-01-20T23:30:00","23:30","2020-09-09T05:30:00","05:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","6648558961_6648113361","Dijon-Toul",">","Dijon","Is sur Tille",2019,2020,51,50,"2019-12-16T01:10:00","01:10","2020-12-07T03:55:00","03:55",194,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6648558961_6648111361","Dijon-Toul",">","Dijon","Is sur Tille",2019,2020,51,50,"2019-12-16T12:35:00","12:35","2020-12-11T14:01:00","14:01",2272,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","6648558961_6648110361","Dijon-Toul",">","Dijon","Is sur Tille",2019,2020,51,50,"2019-12-16T00:05:00","00:05","2020-12-07T03:29:00","03:29",174,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6648558961_6648112361","Dijon-Toul",">","Dijon","Is sur Tille",2020,2020,9,48,"2020-02-24T12:28:00","12:28","2020-11-27T16:48:00","16:48",1415,"DAY",null,null,null,null,null,null,null,null,null,null,null,"85 jours dans le régime binaire"]
["SNCF Réseau","6648558961_6648109361","Dijon-Toul",">","Dijon","Is sur Tille",2019,2020,51,50,"2019-12-16T11:14:00","11:14","2020-12-11T12:35:00","12:35",2039,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","6648558961_6648114361","Dijon-Toul",">","Dijon","Is sur Tille",2020,2020,12,48,"2020-03-16T11:30:00","11:30","2020-11-27T15:00:00","15:00",738,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6648558061_6648131761","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2020,2020,6,26,"2020-02-03T23:27:00","23:27","2020-06-26T05:37:00","05:37",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","6648558061_6648130961","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2019,2020,51,50,"2019-12-16T09:03:00","09:03","2020-12-11T09:55:00","09:55",2162,"DAY",null,null,null,null,null,null,null,null,null,null,null,"219 jours dans le régime binaire"]
["SNCF Réseau","6648558061_6648132561","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2019,2020,51,50,"2019-12-16T13:55:00","13:55","2020-12-11T15:05:00","15:05",3741,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6648558061_6648133361","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2020,2020,6,47,"2020-02-03T23:43:00","23:43","2020-11-20T05:29:00","05:29",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"66 jours dans le régime binaire"]
["SNCF Réseau","6648558761_6648053561","Longuyon-Metz-Sarrebourg","<","Uckange",null,2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","6648558761_6648051961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2020,3,44,"2020-01-13T09:30:00","09:30","2020-10-26T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","6648558761_6648054361","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2020,3,44,"2020-01-13T09:30:00","09:30","2020-10-26T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","6648558761_6648051161","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2020,2,36,"2020-01-06","00:00","2020-08-31T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6648558761_6648052761","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2020,10,39,"2020-03-02T09:30:00","09:30","2020-09-21T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648558761_6648050361","Longuyon-Metz-Sarrebourg","<","Uckange",null,2019,2020,51,50,"2019-12-16T13:50:00","13:50","2020-12-11T14:52:00","14:52",2037,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
["SNCF Réseau","6648558761_6648055961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2019,2020,51,50,"2019-12-16T09:10:00","09:10","2020-12-11T10:08:00","10:08",2139,"DAY",null,null,null,null,null,null,null,null,null,null,null,"212 jours dans le régime binaire"]
["SNCF Réseau","6648558761_6648055161","Longuyon-Metz-Sarrebourg","<","Uckange",null,2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","6648558761_6648049561","Longuyon-Metz-Sarrebourg","<","Uckange",null,2019,2020,51,46,"2019-12-16T11:35:00","11:35","2020-11-13T12:38:00","12:38",1984,"DAY",null,null,null,null,null,null,null,null,null,null,null,"158 jours dans le régime binaire"]
["SNCF Réseau","6648558761_6648056761","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2020,10,39,"2020-03-02T09:30:00","09:30","2020-09-21T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648557861_6648369161","Dijon-Toul",">","IsSurTille","Culmont",2019,2020,51,50,"2019-12-16T11:08:00","11:08","2020-12-11T11:38:00","11:38",1768,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
["SNCF Réseau","6648557861_6648370761","Dijon-Toul",">","IsSurTille","Culmont",2020,2020,13,48,"2020-03-23T12:50:00","12:50","2020-11-27T17:23:00","17:23",734,"DAY",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","6648557861_6648367561","Dijon-Toul",">","IsSurTille","Culmont",2019,2020,51,50,"2019-12-16T13:01:00","13:01","2020-12-11T14:22:00","14:22",2185,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
["SNCF Réseau","6648557861_6648369961","Dijon-Toul",">","IsSurTille","Culmont",2019,2020,51,50,"2019-12-16T00:54:00","00:54","2020-12-07T03:29:00","03:29",169,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","6648557861_6648371561","Dijon-Toul",">","IsSurTille","Culmont",2019,2020,51,50,"2019-12-16T00:29:00","00:29","2020-12-07T04:03:00","04:03",197,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","6648557861_6648368361","Dijon-Toul",">","IsSurTille","Culmont",2020,2020,12,48,"2020-03-16T10:58:00","10:58","2020-11-27T14:28:00","14:28",755,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","6648556561_6648273161","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2020,11,47,"2020-03-09T10:00:00","10:00","2020-11-20T15:30:00","15:30",1059,"DAY",null,null,null,null,null,null,null,null,null,null,null,"69 jours dans le régime binaire"]
["SNCF Réseau","6648556561_6648271561","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2020,1,35,"2020-01-05T23:00:00","23:00","2020-08-30T02:30:00","02:30",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6648556561_6648272361","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2019,2020,51,50,"2019-12-16T11:52:00","11:52","2020-12-11T12:15:00","12:15",3038,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6648556561_6648273961","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2020,11,47,"2020-03-09T09:40:00","09:40","2020-11-20T16:10:00","16:10",1105,"DAY",null,null,null,null,null,null,null,null,null,null,null,"69 jours dans le régime binaire"]
["SNCF Réseau","6648556561_6648270761","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2020,2,36,"2020-01-06T02:08:00","02:08","2020-08-31T04:31:00","04:31",43,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","6648556561_6648274761","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2019,2020,51,50,"2019-12-16T13:35:00","13:35","2020-12-11T15:05:00","15:05",3742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6648557661_6648166961","Lerouville-Nancy",">","Lerouville","Toul",2020,2020,4,48,"2020-01-20T23:00:00","23:00","2020-11-27T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"103 jours dans le régime binaire"]
["SNCF Réseau","6648557661_6648166161","Lerouville-Nancy",">","Lerouville","Toul",2019,2020,51,50,"2019-12-16T10:40:00","10:40","2020-12-11T11:56:00","11:56",2984,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648557661_6648167961","Lerouville-Nancy",">","Lerouville","Toul",2019,2020,51,50,"2019-12-16T15:15:00","15:15","2020-12-11T16:00:00","16:00",3856,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","6648557661_6648168761","Lerouville-Nancy",">","Lerouville","Toul",2019,2019,51,52,"2019-12-16T00:40:00","00:40","2019-12-23T03:20:00","03:20",6,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","6648557661_6648165361","Lerouville-Nancy",">","Lerouville","Toul",2019,2019,51,51,"2019-12-22T22:40:00","22:40","2019-12-22T02:01:00","02:01",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","6648558661_6648015361","Dijon-Toul",">","NeufChateau","Toul",2019,2020,51,49,"2019-12-22T23:52:00","23:52","2020-12-06T01:34:00","01:34",23,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6648558661_6648016161","Dijon-Toul",">","NeufChateau","Toul",2019,2020,51,50,"2019-12-16T01:46:00","01:46","2020-12-07T05:12:00","05:12",86,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6648558661_6648014561","Dijon-Toul",">","NeufChateau","Toul",2019,2020,51,50,"2019-12-16T10:08:00","10:08","2020-12-11T10:34:00","10:34",2642,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648558661_6648013761","Dijon-Toul",">","NeufChateau","Toul",2020,2020,8,11,"2020-02-17T14:15:00","14:15","2020-03-13T19:41:00","19:41",379,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6648558661_6648012961","Dijon-Toul",">","NeufChateau","Toul",2020,2020,8,11,"2020-02-17T09:17:00","09:17","2020-03-13T13:15:00","13:15",255,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6648558661_6648016961","Dijon-Toul",">","NeufChateau","Toul",2019,2020,51,50,"2019-12-16T14:15:00","14:15","2020-12-11T15:44:00","15:44",3934,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648559861_6648007961","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2019,2020,51,50,"2019-12-16T14:16:00","14:16","2020-12-11T15:11:00","15:11",3796,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648559861_6648005761","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2020,3,36,"2020-01-13T00:24:00","00:24","2020-08-31T03:30:00","03:30",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648559861_6648004961","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2020,3,36,"2020-01-13T00:03:00","00:03","2020-08-31T03:00:00","03:00",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648559861_6648006561","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2020,6,37,"2020-02-03T23:45:00","23:45","2020-09-11T05:45:00","05:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"38 jours dans le régime binaire"]
["SNCF Réseau","6648559861_6648008761","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2019,2020,51,50,"2019-12-16T10:45:00","10:45","2020-12-11T11:47:00","11:47",2946,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648557161_6647919161","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2019,2020,51,50,"2019-12-16T11:30:00","11:30","2020-12-11T12:10:00","12:10",3042,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648557161_6647918361","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2019,2020,51,50,"2019-12-16T00:30:00","00:30","2020-12-07T03:50:00","03:50",99,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","6648557161_6647916761","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2019,2020,51,50,"2019-12-16T14:05:00","14:05","2020-12-11T15:25:00","15:25",3855,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648557161_6647917561","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2019,2020,51,50,"2019-12-16T00:50:00","00:50","2020-12-07T03:30:00","03:30",90,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","6648557161_6647915761","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2020,2020,12,44,"2020-03-16T10:15:00","10:15","2020-10-30T16:00:00","16:00",1157,"DAY",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648094361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2019,2020,51,46,"2019-12-16T14:20:00","14:20","2020-11-13T15:15:00","15:15",2303,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648099961","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",453,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648096761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,3,46,"2020-01-13T09:30:00","09:30","2020-11-09T15:30:00","15:30",254,"DAY",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648101561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,5,46,"2020-01-28T11:30:00","11:30","2020-11-13T15:30:00","15:30",484,"DAY",null,null,null,null,null,null,null,null,null,null,null,"32 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648102361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",453,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648095161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2019,2020,51,50,"2019-12-16T13:45:00","13:45","2020-12-11T14:49:00","14:49",2016,"DAY",null,null,null,null,null,null,null,null,null,null,null,"137 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648099161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2019,2020,51,50,"2019-12-16T09:15:00","09:15","2020-12-11T10:11:00","10:11",2180,"DAY",null,null,null,null,null,null,null,null,null,null,null,"215 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648100761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,5,46,"2020-01-28T11:30:00","11:30","2020-11-13T15:30:00","15:30",469,"DAY",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648095961","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,3,46,"2020-01-13T09:30:00","09:30","2020-11-09T15:30:00","15:30",254,"DAY",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648103161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648098361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2019,2020,51,46,"2019-12-16T11:30:00","11:30","2020-11-13T12:34:00","12:34",1898,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
["SNCF Réseau","6648560161_6648097561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","6648557961_6648265161","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2019,2020,51,4,"2019-12-16","00:00","2020-01-20T03:20:00","03:20",13,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","6648557961_6648262761","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2019,2020,51,50,"2019-12-16T09:36:00","09:36","2020-12-11T10:37:00","10:37",2655,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6648557961_6648263561","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2019,2020,51,3,"2019-12-22T23:04:00","23:04","2020-01-19T01:55:00","01:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","6648557961_6648266761","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2019,2020,51,50,"2019-12-16T14:36:00","14:36","2020-12-11T15:26:00","15:26",3720,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","6648557961_6648265961","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2020,2,38,"2020-01-06T23:05:00","23:05","2020-09-18T04:55:00","04:55",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"62 jours dans le régime binaire"]
["SNCF Réseau","6648557961_6648264361","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2020,2,38,"2020-01-06T23:20:00","23:20","2020-09-18T05:30:00","05:30",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"62 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648331161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",407,"DAY",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648336761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648331961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,46,"2019-12-16T11:23:00","11:23","2020-11-13T12:27:00","12:27",1893,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648332761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648334361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648339961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,2,36,"2020-01-06","00:00","2020-08-31T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648337561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,5,46,"2020-01-28T11:30:00","11:30","2020-11-13T15:30:00","15:30",624,"DAY",null,null,null,null,null,null,null,null,null,null,null,"41 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648340761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648335961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648333561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,2,36,"2020-01-06","00:00","2020-08-31T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648341561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",391,"DAY",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648338361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,46,"2019-12-16T14:30:00","14:30","2020-11-13T15:25:00","15:25",2344,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648335161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648339161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,50,"2019-12-16T13:38:00","13:38","2020-12-11T14:41:00","14:41",2012,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
["SNCF Réseau","6648558261_6648330361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,50,"2019-12-16T09:21:00","09:21","2020-12-11T10:19:00","10:19",2219,"DAY",null,null,null,null,null,null,null,null,null,null,null,"216 jours dans le régime binaire"]
["SNCF Réseau","6648556361_6648235361","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
["SNCF Réseau","6648556361_6648233761","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
["SNCF Réseau","6648556361_6648237761","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6648556361_6648234561","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2019,2020,51,46,"2019-12-16T14:21:00","14:21","2020-11-13T15:20:00","15:20",2331,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
["SNCF Réseau","6648556361_6648236961","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2019,2020,51,46,"2019-12-16T11:28:00","11:28","2020-11-13T12:29:00","12:29",1898,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
["SNCF Réseau","6648556361_6648236161","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2019,2020,51,50,"2019-12-16T09:17:00","09:17","2020-12-11T10:14:00","10:14",2201,"DAY",null,null,null,null,null,null,null,null,null,null,null,"216 jours dans le régime binaire"]
["SNCF Réseau","6648558561_6648365361","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2019,2020,51,50,"2019-12-16T11:30:00","11:30","2020-12-11T11:55:00","11:55",2133,"DAY",null,null,null,null,null,null,null,null,null,null,null,"180 jours dans le régime binaire"]
["SNCF Réseau","6648558561_6648363761","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2020,2020,9,48,"2020-02-24T23:40:00","23:40","2020-11-27T05:10:00","05:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"75 jours dans le régime binaire"]
["SNCF Réseau","6648558561_6648364561","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2019,2020,51,50,"2019-12-16T14:05:00","14:05","2020-12-11T15:55:00","15:55",2850,"DAY",null,null,null,null,null,null,null,null,null,null,null,"180 jours dans le régime binaire"]
["SNCF Réseau","6648558561_6648362961","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2020,2020,9,48,"2020-02-24T22:55:00","22:55","2020-11-27T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"72 jours dans le régime binaire"]
["SNCF Réseau","6658927861_6665963261","Paris-Busigny",">","Aulnay","Mitry",2020,2020,4,42,"2020-01-20T23:20:00","23:20","2020-10-16T04:40:00","04:40",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6658927861_6665968861","Paris-Busigny",">","Aulnay","Mitry",2019,2020,51,50,"2019-12-16T23:20:00","23:20","2020-12-11T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
["SNCF Réseau","6658927861_6665952961","Paris-Busigny",">","Aulnay","Mitry",2020,2020,4,42,"2020-01-21T01:30:00","01:30","2020-10-17T04:40:00","04:40",301,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","6658927861_6665935161","Paris-Busigny",">","Aulnay","Mitry",2019,2020,51,50,"2019-12-17T01:30:00","01:30","2020-12-11T04:40:00","04:40",726,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"156 jours dans le régime binaire"]
["SNCF Réseau","6651778261_6651676961","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-16T01:35:00","01:35","2020-12-07T04:35:00","04:35",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651778261_6651677761","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-16T23:50:00","23:50","2020-12-11T04:50:00","04:50",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
["SNCF Réseau","6651778261_6651676161","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-17T00:15:00","00:15","2020-12-12T04:45:00","04:45",664,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"140 jours dans le régime binaire"]
["SNCF Réseau","6651778261_6651679361","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-16T01:40:00","01:40","2020-12-07T04:40:00","04:40",236,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651778261_6651678561","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-17T01:20:00","01:20","2020-12-12T04:50:00","04:50",675,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"140 jours dans le régime binaire"]
["SNCF Réseau","6651778261_6651675361","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-16T23:40:00","23:40","2020-12-11T04:35:00","04:35",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
["SNCF Réseau","6651778561_6651705561","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2020,2,50,"2020-01-07T00:30:00","00:30","2020-12-12T04:55:00","04:55",1204,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"245 jours dans le régime binaire"]
["SNCF Réseau","6651778561_6651703961","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2020,2,50,"2020-01-07T01:05:00","01:05","2020-12-12T04:50:00","04:50",1183,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"245 jours dans le régime binaire"]
["SNCF Réseau","6651778561_6651704761","Paris-Amiens",">","SaintDenis","VilliersLeBel",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651778561_6651702361","Paris-Amiens",">","SaintDenis","VilliersLeBel",2019,2020,51,50,"2019-12-16T23:35:00","23:35","2020-12-11T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","6651778561_6651703161","Paris-Amiens",">","SaintDenis","VilliersLeBel",2019,2020,51,50,"2019-12-16T23:55:00","23:55","2020-12-11T04:50:00","04:50",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651778561_6651701561","Paris-Amiens",">","SaintDenis","VilliersLeBel",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651778361_6651730361","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2019,2020,51,50,"2019-12-16T01:45:00","01:45","2020-12-07T04:45:00","04:45",240,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651778361_6651731161","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2019,2020,51,50,"2019-12-17","00:00","2020-12-12T05:00:00","05:00",1285,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"257 jours dans le régime binaire"]
["SNCF Réseau","6651778361_6651729561","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651779161_6651689961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-17T01:00:00","01:00","2020-12-12T04:50:00","04:50",1202,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6651779161_6651690961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-17T00:35:00","00:35","2020-12-12T05:05:00","05:05",1265,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6651779161_6651687961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651779161_6651686961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-16T23:25:00","23:25","2020-12-11T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6651779161_6651691961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651779161_6651688961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-16","00:00","2020-12-11T05:05:00","05:05",-5,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","6651778961_6651740961","Paris-Amiens",">","Orry","Creil",2020,2020,7,48,"2020-02-11T01:04:00","01:04","2020-11-28T05:20:00","05:20",398,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"75 jours dans le régime binaire"]
["SNCF Réseau","6651778961_6651741761","Paris-Amiens",">","Orry","Creil",2019,2020,52,50,"2019-12-23T01:30:00","01:30","2020-12-07T04:30:00","04:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","6651778961_6651738561","Paris-Amiens",">","Orry","Creil",2020,2020,9,27,"2020-02-24T23:49:00","23:49","2020-07-03T04:54:00","04:54",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","6651778961_6651742561","Paris-Amiens",">","Orry","Creil",2019,2020,52,50,"2019-12-23T01:51:00","01:51","2020-12-07T04:51:00","04:51",70,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","6651778961_6651739361","Paris-Amiens",">","Orry","Creil",2020,2020,7,48,"2020-02-10T23:53:00","23:53","2020-11-27T04:42:00","04:42",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"75 jours dans le régime binaire"]
["SNCF Réseau","6651778961_6651740161","Paris-Amiens",">","Orry","Creil",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","6651777861_6651683361","Paris-Amiens",">","Villiers le Bel","Goussainville",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651777861_6651684161","Paris-Amiens",">","Villiers le Bel","Goussainville",2020,2020,6,50,"2020-02-04T01:14:00","01:14","2020-12-12T04:50:00","04:50",433,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"90 jours dans le régime binaire"]
["SNCF Réseau","6651777861_6651684961","Paris-Amiens",">","Villiers le Bel","Goussainville",2019,2020,51,50,"2019-12-16T23:45:00","23:45","2020-12-11T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
["SNCF Réseau","6651777861_6651680961","Paris-Amiens",">","Villiers le Bel","Goussainville",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651777861_6651681761","Paris-Amiens",">","Villiers le Bel","Goussainville",2019,2020,51,50,"2019-12-17T00:20:00","00:20","2020-12-12T04:50:00","04:50",676,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"140 jours dans le régime binaire"]
["SNCF Réseau","6651777861_6651682561","Paris-Amiens",">","Villiers le Bel","Goussainville",2019,2020,51,50,"2019-12-16T23:46:00","23:46","2020-12-11T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
["SNCF Réseau","6651777961_6651693761","Paris-Busigny",">","Mitry","Ormoy",2019,2020,51,45,"2019-12-17","00:00","2020-11-07T04:45:00","04:45",831,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"175 jours dans le régime binaire"]
["SNCF Réseau","6651778061_6651734361","Paris-Amiens",">","Bif de Pierrefitte","Orry",2019,2020,52,50,"2019-12-23T01:45:00","01:45","2020-12-07T04:45:00","04:45",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","6651778061_6651735161","Paris-Amiens",">","Bif de Pierrefitte","Orry",2019,2020,52,50,"2019-12-23T01:30:00","01:30","2020-12-07T04:30:00","04:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","6651778061_6651735961","Paris-Amiens",">","Bif de Pierrefitte","Orry",2020,2020,7,48,"2020-02-11","00:00","2020-11-28T05:00:00","05:00",375,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"75 jours dans le régime binaire"]
["SNCF Réseau","6651778061_6651733561","Paris-Amiens",">","Bif de Pierrefitte","Orry",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",142,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"32 jours dans le régime binaire"]
["SNCF Réseau","6645025761_6644811661","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2020,3,42,"2020-01-13T01:07:00","01:07","2020-10-12T04:40:00","04:40",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","6645025761_6644809261","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2020,3,44,"2020-01-13T23:05:00","23:05","2020-10-28T05:57:00","05:57",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"127 jours dans le régime binaire"]
["SNCF Réseau","6645025761_6644812461","Dijon-Lyon",">","Chalon sur Saone","Macon",2019,2020,51,50,"2019-12-16T13:25:00","13:25","2020-12-11T14:56:00","14:56",3734,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645025761_6644810061","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2020,3,44,"2020-01-13T23:58:00","23:58","2020-10-28T05:18:00","05:18",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"122 jours dans le régime binaire"]
["SNCF Réseau","6645025761_6644810861","Dijon-Lyon",">","Chalon sur Saone","Macon",2019,2020,51,50,"2019-12-16T11:37:00","11:37","2020-12-11T12:06:00","12:06",3025,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645025761_6644813261","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2020,2,41,"2020-01-12T00:03:00","00:03","2020-10-11T02:30:00","02:30",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","6645025961_6644853861","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2020,7,25,"2020-02-10T13:08:00","13:08","2020-06-19T16:28:00","16:28",678,"DAY",null,null,null,null,null,null,null,null,null,null,null,"42 jours dans le régime binaire"]
["SNCF Réseau","6645025961_6644858861","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2019,2020,51,34,"2019-12-16T11:45:00","11:45","2020-08-21T13:15:00","13:15",1445,"DAY",null,null,null,null,null,null,null,null,null,null,null,"110 jours dans le régime binaire"]
["SNCF Réseau","6645025961_6644854661","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2020,4,36,"2020-01-26T22:10:00","22:10","2020-09-06T01:30:00","01:30",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6645025961_6644855461","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2020,7,25,"2020-02-10T08:49:00","08:49","2020-06-19T13:22:00","13:22",552,"DAY",null,null,null,null,null,null,null,null,null,null,null,"42 jours dans le régime binaire"]
["SNCF Réseau","6645025961_6644858061","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2020,5,37,"2020-01-27T02:56:00","02:56","2020-09-07T05:30:00","05:30",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6645025961_6644857261","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2019,2020,51,34,"2019-12-16T13:30:00","13:30","2020-08-21T13:48:00","13:48",1504,"DAY",null,null,null,null,null,null,null,null,null,null,null,"110 jours dans le régime binaire"]
["SNCF Réseau","6645025961_6644856261","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2020,8,49,"2020-02-17T10:22:00","10:22","2020-12-04T16:22:00","16:22",1446,"DAY",null,null,null,null,null,null,null,null,null,null,null,"89 jours dans le régime binaire"]
["SNCF Réseau","6645025361_6644862861","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T22:58:00","22:58","2020-12-11T04:37:00","04:37",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
["SNCF Réseau","6645025361_6644864461","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T10:30:00","10:30","2020-12-11T11:24:00","11:24",2702,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","6645025361_6644862061","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-07T00:20:00","00:20","2020-12-12T06:24:00","06:24",620,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
["SNCF Réseau","6645025361_6644861261","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T14:28:00","14:28","2020-12-11T15:35:00","15:35",3694,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","6645025361_6644863661","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T14:28:00","14:28","2020-12-11T15:35:00","15:35",3694,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","6645025361_6644866061","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T10:30:00","10:30","2020-12-11T11:24:00","11:24",2702,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","6645025361_6644860461","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-07T00:20:00","00:20","2020-12-12T06:24:00","06:24",620,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
["SNCF Réseau","6645025361_6644865261","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T22:58:00","22:58","2020-12-11T04:37:00","04:37",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
["SNCF Réseau","6645025861_6644871061","Dijon-Lyon",">","Macon","Saint Germain",2020,2020,3,44,"2020-01-13T23:25:00","23:25","2020-10-28T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"98 jours dans le régime binaire"]
["SNCF Réseau","6645025861_6644868661","Dijon-Lyon",">","Macon","Saint Germain",2020,2020,3,44,"2020-01-13T23:45:00","23:45","2020-10-28T06:20:00","06:20",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"98 jours dans le régime binaire"]
["SNCF Réseau","6645025861_6644871861","Dijon-Lyon",">","Macon","Saint Germain",2019,2020,51,50,"2019-12-16T11:03:00","11:03","2020-12-11T11:33:00","11:33",2888,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645025861_6644870261","Dijon-Lyon",">","Macon","Saint Germain",2020,2020,3,42,"2020-01-13T01:45:00","01:45","2020-10-12T05:04:00","05:04",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","6645025861_6644872661","Dijon-Lyon",">","Macon","Saint Germain",2020,2020,2,41,"2020-01-12T22:50:00","22:50","2020-10-11T01:30:00","01:30",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","6645025861_6644869461","Dijon-Lyon",">","Macon","Saint Germain",2019,2020,51,50,"2019-12-16T13:57:00","13:57","2020-12-11T15:28:00","15:28",3868,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645024661_6644934861","Dijon-Lyon",">","Dijon","Chagny",2020,2020,3,42,"2020-01-13T00:25:00","00:25","2020-10-12T03:11:00","03:11",44,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","6645024661_6644935661","Dijon-Lyon",">","Dijon","Chagny",2020,2020,3,44,"2020-01-13T22:29:00","22:29","2020-10-28T04:55:00","04:55",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"108 jours dans le régime binaire"]
["SNCF Réseau","6645024661_6644936461","Dijon-Lyon",">","Dijon","Chagny",2020,2020,3,42,"2020-01-13T00:45:00","00:45","2020-10-12T04:00:00","04:00",55,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","6645024661_6644937261","Dijon-Lyon",">","Dijon","Chagny",2019,2020,51,50,"2019-12-16T12:42:00","12:42","2020-12-11T14:13:00","14:13",3555,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645024661_6644938861","Dijon-Lyon",">","Dijon","Chagny",2019,2020,51,50,"2019-12-16T12:16:00","12:16","2020-12-11T12:44:00","12:44",3183,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645024661_6644938061","Dijon-Lyon",">","Dijon","Chagny",2020,2020,3,44,"2020-01-14T00:34:00","00:34","2020-10-29T05:57:00","05:57",695,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"117 jours dans le régime binaire"]
["SNCF Réseau","6645024361_6644953061","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2020,19,49,"2020-05-04T14:15:00","14:15","2020-12-04T16:15:00","16:15",700,"DAY",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","6645024361_6644952261","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2019,2020,51,50,"2019-12-16T11:34:00","11:34","2020-12-11T12:14:00","12:14",3059,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645024361_6644954861","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2019,2020,51,50,"2019-12-16T14:16:00","14:16","2020-12-11T15:29:00","15:29",3872,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645024361_6644954061","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2019,2020,1,50,"2019-12-30T01:32:00","01:32","2020-12-07T04:15:00","04:15",100,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","6645024361_6644951461","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2019,2020,52,49,"2019-12-29T23:22:00","23:22","2020-12-06T02:39:00","02:39",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","6645024361_6644955661","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2020,11,49,"2020-03-09T10:15:00","10:15","2020-12-04T16:15:00","16:15",802,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6645025661_6644918861","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2019,2020,51,50,"2019-12-16T12:58:00","12:58","2020-12-11T14:20:00","14:20",3584,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645025661_6644917261","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2020,4,36,"2020-01-26T23:44:00","23:44","2020-09-06T02:29:00","02:29",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645025661_6644918061","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2019,2020,51,50,"2019-12-16T12:00:00","12:00","2020-12-11T12:50:00","12:50",3209,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645025661_6644920661","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2020,5,37,"2020-01-27T01:52:00","01:52","2020-09-07T04:32:00","04:32",52,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","6645025661_6644919661","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2020,2,50,"2020-01-07T10:43:00","10:43","2020-12-11T16:43:00","16:43",1794,"DAY",null,null,null,null,null,null,null,null,null,null,null,"108 jours dans le régime binaire"]
["SNCF Réseau","6645025661_6644921461","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2020,2,50,"2020-01-07T11:00:00","11:00","2020-12-11T13:00:00","13:00",1393,"DAY",null,null,null,null,null,null,null,null,null,null,null,"108 jours dans le régime binaire"]
["SNCF Réseau","6645025461_6644891061","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2019,2020,51,50,"2019-12-16T00:05:00","00:05","2020-12-07T03:20:00","03:20",166,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6645025461_6644888661","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2019,2020,51,50,"2019-12-16T15:05:00","15:05","2020-12-11T15:48:00","15:48",3950,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645025461_6644890261","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2019,2020,51,50,"2019-12-16T00:25:00","00:25","2020-12-07T03:10:00","03:10",157,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6645025461_6644889461","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2019,2020,51,50,"2019-12-16T14:31:00","14:31","2020-12-11T15:48:00","15:48",3951,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645025461_6644887661","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2020,2020,3,50,"2020-01-13T23:40:00","23:40","2020-12-11T05:40:00","05:40",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","6645024161_6644916061","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2020,6,25,"2020-02-03T09:15:00","09:15","2020-06-19T13:45:00","13:45",458,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","6645024161_6644914461","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2020,6,25,"2020-02-03T12:35:00","12:35","2020-06-19T16:15:00","16:15",539,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","6645024161_6644911861","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2020,8,47,"2020-02-17T10:15:00","10:15","2020-11-20T16:15:00","16:15",786,"DAY",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","6645024161_6644912861","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2020,5,37,"2020-01-27T02:30:00","02:30","2020-09-07T04:52:00","04:52",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6645024161_6644913661","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2019,2020,51,42,"2019-12-16T12:15:00","12:15","2020-10-16T13:58:00","13:58",1915,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
["SNCF Réseau","6645024161_6644915261","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2020,4,36,"2020-01-26T22:31:00","22:31","2020-09-06T02:02:00","02:02",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6645024161_6644911061","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2019,2020,51,42,"2019-12-16T12:58:00","12:58","2020-10-16T13:10:00","13:10",1804,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
["SNCF Réseau","6645025561_6644876261","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2020,3,44,"2020-01-15T23:00:00","23:00","2020-10-28T05:11:00","05:11",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"96 jours dans le régime binaire"]
["SNCF Réseau","6645025561_6644880261","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2020,3,44,"2020-01-15T00:07:00","00:07","2020-10-28T05:55:00","05:55",-5,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"89 jours dans le régime binaire"]
["SNCF Réseau","6645025561_6644879461","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2020,3,42,"2020-01-13T00:10:00","00:10","2020-10-12T03:05:00","03:05",43,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","6645025561_6644877061","Dijon-Lyon",">","Chagny","Chalon sur Saone",2019,2020,51,50,"2019-12-16T13:13:00","13:13","2020-12-11T14:26:00","14:26",3609,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645025561_6644878661","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2020,3,42,"2020-01-13T01:00:00","01:00","2020-10-12T04:05:00","04:05",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","6645025561_6644877861","Dijon-Lyon",">","Chagny","Chalon sur Saone",2019,2020,51,50,"2019-12-16T11:46:00","11:46","2020-12-11T12:35:00","12:35",3146,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6645023961_6644896261","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2020,8,49,"2020-02-17T22:18:00","22:18","2020-12-03T04:40:00","04:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","6645023961_6644899461","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2019,2020,51,50,"2019-12-16T11:44:00","11:44","2020-12-11T12:08:00","12:08",2985,"DAY",null,null,null,null,null,null,null,null,null,null,null,"247 jours dans le régime binaire"]
["SNCF Réseau","6645023961_6644897061","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2020,7,37,"2020-02-10T03:06:00","03:06","2020-09-07T05:32:00","05:32",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","6645023961_6644900261","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2020,1,50,"2020-01-05T23:30:00","23:30","2020-12-10T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"41 jours dans le régime binaire"]
["SNCF Réseau","6645023961_6644898661","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2019,2020,51,50,"2019-12-16T10:42:00","10:42","2020-12-11T12:01:00","12:01",2957,"DAY",null,null,null,null,null,null,null,null,null,null,null,"247 jours dans le régime binaire"]
["SNCF Réseau","6645023961_6644897861","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2020,7,37,"2020-02-10T00:24:00","00:24","2020-09-07T03:47:00","03:47",45,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","6652285361_6652238261","Paris-Amiens",">","StadeDeFrance","StDenis",2019,2020,51,50,"2019-12-17T01:00:00","01:00","2020-12-12T05:20:00","05:20",1359,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"255 jours dans le régime binaire"]
["SNCF Réseau","6652285361_6652237461","Paris-Amiens",">","StadeDeFrance","StDenis",2019,2020,51,50,"2019-12-17T01:00:00","01:00","2020-12-12T05:05:00","05:05",1295,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"255 jours dans le régime binaire"]
["SNCF Réseau","6652285361_6652235661","Paris-Amiens",">","StadeDeFrance","StDenis",2019,2020,51,50,"2019-12-17T00:35:00","00:35","2020-12-12T04:45:00","04:45",1210,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"255 jours dans le régime binaire"]
["SNCF Réseau","6652285361_6652234861","Paris-Amiens",">","StadeDeFrance","StDenis",2019,2020,51,50,"2019-12-17T00:30:00","00:30","2020-12-12T04:25:00","04:25",1125,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"255 jours dans le régime binaire"]
["SNCF Réseau","6652285361_6652236461","Paris-Amiens",">","StadeDeFrance","StDenis",2020,2020,15,49,"2020-04-06T23:55:00","23:55","2020-12-04T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"32 jours dans le régime binaire"]
["SNCF Réseau","6652754861_6652623761","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2020,2020,6,48,"2020-02-03T20:25:00","20:25","2020-11-27T04:55:00","04:55",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"125 jours dans le régime binaire"]
["SNCF Réseau","6652754861_6652625361","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2019,2020,51,50,"2019-12-16T13:45:00","13:45","2020-12-11T14:55:00","14:55",3730,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6652756461_6652670361","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2020,2020,6,48,"2020-02-03T21:03:00","21:03","2020-11-27T05:20:00","05:20",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"133 jours dans le régime binaire"]
["SNCF Réseau","6652756461_6652668361","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2019,2020,51,50,"2019-12-16T13:50:00","13:50","2020-12-11T16:50:00","16:50",4211,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6652756461_6652669361","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2020,2020,7,44,"2020-02-10T10:00:00","10:00","2020-10-29T17:00:00","17:00",194,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","6652759861_6652673161","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2019,2020,51,50,"2019-12-16T10:11:00","10:11","2020-12-11T13:00:00","13:00",3252,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6652759861_6652672161","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2020,2020,16,45,"2020-04-14T10:00:00","10:00","2020-11-06T15:00:00","15:00",275,"DAY",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6652753761_6652685161","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2020,7,44,"2020-02-10T10:05:00","10:05","2020-10-30T17:00:00","17:00",329,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6652753761_6652686961","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2019,2020,51,50,"2019-12-16T13:50:00","13:50","2020-12-11T16:50:00","16:50",4211,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6652753761_6652683561","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2019,2020,51,50,"2019-12-17T13:50:00","13:50","2020-12-11T16:50:00","16:50",2527,"DAY",null,null,null,null,null,null,null,null,null,null,null,"151 jours dans le régime binaire"]
["SNCF Réseau","6652753761_6652682761","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2019,2020,51,50,"2019-12-16T13:50:00","13:50","2020-12-09T15:35:00","15:35",1528,"DAY",null,null,null,null,null,null,null,null,null,null,null,"99 jours dans le régime binaire"]
["SNCF Réseau","6652753761_6652685961","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2020,6,48,"2020-02-03T21:03:00","21:03","2020-11-27T05:20:00","05:20",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"113 jours dans le régime binaire"]
["SNCF Réseau","6652753761_6652684361","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2020,7,44,"2020-02-10T11:40:00","11:40","2020-10-30T17:00:00","17:00",328,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6652756661_6652629561","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2019,2020,51,50,"2019-12-16T09:35:00","09:35","2020-12-11T10:35:00","10:35",2742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","6652756661_6652631161","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2020,2020,6,48,"2020-02-03T22:00:00","22:00","2020-11-27T04:00:00","04:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"130 jours dans le régime binaire"]
["SNCF Réseau","6652756661_6652630361","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2019,2020,51,50,"2019-12-21T09:00:00","09:00","2020-12-12T10:35:00","10:35",1091,"DAY",null,null,null,null,null,null,null,null,null,null,null,"104 jours dans le régime binaire"]
["SNCF Réseau","6652757561_6652607561","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2020,2020,6,49,"2020-02-03T21:45:00","21:45","2020-12-04T05:25:00","05:25",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"139 jours dans le régime binaire"]
["SNCF Réseau","6652757561_6652609361","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2019,2020,51,50,"2019-12-16T13:50:00","13:50","2020-12-11T14:50:00","14:50",3709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6652757561_6652608561","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2019,2020,51,50,"2019-12-16T09:54:00","09:54","2020-12-11T10:54:00","10:54",2726,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651859761_6651792261","Sarrebourg-Basel",">","Reding","Saverne",2019,2020,51,50,"2019-12-16T13:21:00","13:21","2020-12-11T14:36:00","14:36",3403,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","6651859761_6651791461","Sarrebourg-Basel",">","Reding","Saverne",2019,2020,51,50,"2019-12-16T14:00:00","14:00","2020-12-11T14:45:00","14:45",2759,"DAY",null,null,null,null,null,null,null,null,null,null,null,"188 jours dans le régime binaire"]
["SNCF Réseau","6651859761_6651790461","Sarrebourg-Basel",">","Reding","Saverne",2020,2020,9,50,"2020-02-24T22:45:00","22:45","2020-12-10T04:57:00","04:57",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"101 jours dans le régime binaire"]
["SNCF Réseau","6651860261_6651804861","Sarrebourg-Basel",">","Graffenstaden","Selestat",2019,2020,51,50,"2019-12-16T13:55:00","13:55","2020-12-11T15:08:00","15:08",3391,"DAY",null,null,null,null,null,null,null,null,null,null,null,"225 jours dans le régime binaire"]
["SNCF Réseau","6651860261_6651802461","Sarrebourg-Basel",">","Graffenstaden","Selestat",2020,2020,8,42,"2020-02-17T23:25:00","23:25","2020-10-16T05:35:00","05:35",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","6651860261_6651803261","Sarrebourg-Basel",">","Graffenstaden","Selestat",2020,2020,9,45,"2020-02-24T23:23:00","23:23","2020-11-03T05:04:00","05:04",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6651860261_6651804061","Sarrebourg-Basel",">","Graffenstaden","Selestat",2019,2020,51,50,"2019-12-16T10:33:00","10:33","2020-12-11T11:19:00","11:19",2773,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6651859661_6651796661","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2020,9,47,"2020-02-24T22:50:00","22:50","2020-11-19T05:05:00","05:05",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","6651859661_6651795061","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2019,2020,51,50,"2019-12-16T09:29:00","09:29","2020-12-11T10:26:00","10:26",2557,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6651859661_6651795861","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2019,2020,51,50,"2019-12-16T09:40:00","09:40","2020-12-11T10:30:00","10:30",2573,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6651859661_6651793461","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2020,12,48,"2020-03-16T23:05:00","23:05","2020-11-26T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651859661_6651797461","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2019,2020,51,50,"2019-12-16T14:50:00","14:50","2020-12-11T16:00:00","16:00",3921,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6651859661_6651794261","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2019,2020,51,50,"2019-12-16T15:01:00","15:01","2020-12-11T16:04:00","16:04",3937,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6651860061_6651818461","Sarrebourg-Basel",">","Saverne","Vendenheim",2019,2020,51,50,"2019-12-16T13:35:00","13:35","2020-12-11T14:26:00","14:26",2699,"DAY",null,null,null,null,null,null,null,null,null,null,null,"188 jours dans le régime binaire"]
["SNCF Réseau","6651860061_6651817661","Sarrebourg-Basel",">","Saverne","Vendenheim",2019,2020,51,50,"2019-12-16T13:49:00","13:49","2020-12-11T14:57:00","14:57",3484,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","6651860061_6651816861","Sarrebourg-Basel",">","Saverne","Vendenheim",2019,2020,51,50,"2019-12-16T13:45:00","13:45","2020-12-11T14:34:00","14:34",2724,"DAY",null,null,null,null,null,null,null,null,null,null,null,"188 jours dans le régime binaire"]
["SNCF Réseau","6651860061_6651819261","Sarrebourg-Basel",">","Saverne","Vendenheim",2019,2020,51,50,"2019-12-16T13:36:00","13:36","2020-12-11T14:50:00","14:50",3635,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6651860061_6651815861","Sarrebourg-Basel",">","Saverne","Vendenheim",2019,2020,51,50,"2019-12-16T22:57:00","22:57","2020-12-10T05:12:00","05:12",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"76 jours dans le régime binaire"]
["SNCF Réseau","6651861361_6651835861","Sarrebourg-Basel",">","Colmar","Lutterbach",2020,2020,9,45,"2020-02-24T23:01:00","23:01","2020-11-05T05:16:00","05:16",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","6651861361_6651835061","Sarrebourg-Basel",">","Colmar","Lutterbach",2019,2020,51,50,"2019-12-16T10:03:00","10:03","2020-12-11T10:50:00","10:50",2654,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6651861361_6651834261","Sarrebourg-Basel",">","Colmar","Lutterbach",2020,2020,8,48,"2020-02-17T23:15:00","23:15","2020-11-26T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","6651861361_6651836661","Sarrebourg-Basel",">","Colmar","Lutterbach",2019,2020,51,50,"2019-12-16T14:25:00","14:25","2020-12-11T15:39:00","15:39",3835,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6651859461_6651826061","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2019,2020,51,50,"2019-12-16T10:17:00","10:17","2020-12-11T11:09:00","11:09",2732,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6651859461_6651830061","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2020,24,47,"2020-06-08T22:52:00","22:52","2020-11-20T04:58:00","04:58",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","6651859461_6651827661","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2019,2020,51,50,"2019-12-16T14:10:00","14:10","2020-12-11T15:19:00","15:19",3432,"DAY",null,null,null,null,null,null,null,null,null,null,null,"225 jours dans le régime binaire"]
["SNCF Réseau","6651859461_6651829261","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2020,19,50,"2020-05-04T23:26:00","23:26","2020-12-11T05:18:00","05:18",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","6644750761_6644545161","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2020,2020,27,50,"2020-06-29T08:22:00","08:22","2020-12-11T09:57:00","09:57",1165,"DAY",null,null,null,null,null,null,null,null,null,null,null,"118 jours dans le régime binaire"]
["SNCF Réseau","6644750761_6644544361","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2020,2020,27,50,"2020-06-29T15:26:00","15:26","2020-12-11T16:54:00","16:54",1978,"DAY",null,null,null,null,null,null,null,null,null,null,null,"118 jours dans le régime binaire"]
["SNCF Réseau","6644750761_6644543361","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2020,2020,42,47,"2020-10-12T09:20:00","09:20","2020-11-20T13:20:00","13:20",377,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","6644748461_6644599361","Avignon-Miramasparouest",">","Avignon","Tarascon",2019,2020,51,50,"2019-12-16T14:17:00","14:17","2020-12-11T15:10:00","15:10",3686,"DAY",null,null,null,null,null,null,null,null,null,null,null,"244 jours dans le régime binaire"]
["SNCF Réseau","6644748461_6644594361","Avignon-Miramasparouest",">","Avignon","Tarascon",2019,2020,51,50,"2019-12-16T10:35:00","10:35","2020-12-11T11:41:00","11:41",2653,"DAY",null,null,null,null,null,null,null,null,null,null,null,"228 jours dans le régime binaire"]
["SNCF Réseau","6644748461_6644596961","Avignon-Miramasparouest",">","Avignon","Tarascon",2019,2020,52,49,"2019-12-23T01:20:00","01:20","2020-11-30T04:15:00","04:15",100,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","6644748461_6644597761","Avignon-Miramasparouest",">","Avignon","Tarascon",2019,2020,52,49,"2019-12-23T01:05:00","01:05","2020-11-30T04:10:00","04:10",98,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","6644748461_6644595161","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2020,5,47,"2020-01-27T23:10:00","23:10","2020-11-20T05:04:00","05:04",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6644748461_6644598561","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2020,13,48,"2020-03-23T23:15:00","23:15","2020-11-27T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","6644748461_6644595961","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2020,10,48,"2020-03-03","00:00","2020-11-28T02:00:00","02:00",148,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
["SNCF Réseau","6644751161_6644631961","Miramas-Marseille",">","Miramas","Rognac",2019,2020,51,50,"2019-12-16T10:39:00","10:39","2020-12-11T11:51:00","11:51",2963,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644751161_6644632761","Miramas-Marseille",">","Miramas","Rognac",2019,2020,51,50,"2019-12-16T10:21:00","10:21","2020-12-11T11:08:00","11:08",2661,"DAY",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","6644751161_6644629561","Miramas-Marseille",">","Miramas","Rognac",2019,2020,51,50,"2019-12-16T10:08:00","10:08","2020-12-11T11:06:00","11:06",2775,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644751161_6644628561","Miramas-Marseille",">","Miramas","Rognac",2020,2020,6,48,"2020-02-04","00:00","2020-11-28T04:30:00","04:30",445,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"99 jours dans le régime binaire"]
["SNCF Réseau","6644751161_6644630361","Miramas-Marseille",">","Miramas","Rognac",2019,2020,51,21,"2019-12-16T01:00:00","01:00","2020-05-18T03:55:00","03:55",46,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","6644751161_6644631161","Miramas-Marseille",">","Miramas","Rognac",2019,2020,51,50,"2019-12-16T10:51:00","10:51","2020-12-11T11:55:00","11:55",2980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644750061_6644584961","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2019,2020,51,50,"2019-12-16T11:11:00","11:11","2020-12-11T12:13:00","12:13",3055,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644750061_6644583161","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2019,2020,51,50,"2019-12-16T09:50:00","09:50","2020-12-11T10:47:00","10:47",2535,"DAY",null,null,null,null,null,null,null,null,null,null,null,"236 jours dans le régime binaire"]
["SNCF Réseau","6644750061_6644583961","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2020,2020,10,43,"2020-03-03","00:00","2020-10-24T04:30:00","04:30",288,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","6644748861_6644581961","Avignon-Miramasparest",">","Cavaillon","Miramas",2019,2020,51,50,"2019-12-16T10:52:00","10:52","2020-12-11T11:25:00","11:25",2854,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644748861_6644579361","Avignon-Miramasparest",">","Cavaillon","Miramas",2020,2020,14,47,"2020-03-30T09:08:00","09:08","2020-11-20T13:08:00","13:08",752,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","6644748861_6644578561","Avignon-Miramasparest",">","Cavaillon","Miramas",2019,2020,51,50,"2019-12-16T14:08:00","14:08","2020-12-11T15:33:00","15:33",3888,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644749061_6644538361","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2020,10,43,"2020-03-02T22:30:00","22:30","2020-10-23T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","6644749061_6644537561","Miramas-Fos-Marseille",">","Lavalduc","Fos",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",153,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6644749061_6644536761","Miramas-Fos-Marseille",">","Lavalduc","Fos",2019,2020,51,50,"2019-12-16T08:45:00","08:45","2020-12-11T09:45:00","09:45",2438,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644749061_6644535961","Miramas-Fos-Marseille",">","Lavalduc","Fos",2019,2020,51,50,"2019-12-16T08:45:00","08:45","2020-12-11T09:45:00","09:45",2438,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644749061_6644540161","Miramas-Fos-Marseille",">","Lavalduc","Fos",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","6644749061_6644539161","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2020,13,47,"2020-03-23T22:30:00","22:30","2020-11-20T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","6644748561_6644563561","Miramas-Marseille",">","Rognac","L'Estaque",2019,2020,51,50,"2019-12-16T11:05:00","11:05","2020-12-11T12:10:00","12:10",3042,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644748561_6644561761","Miramas-Marseille",">","Rognac","L'Estaque",2019,2020,51,50,"2019-12-16T10:56:00","10:56","2020-12-11T12:04:00","12:04",3017,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644748561_6644562561","Miramas-Marseille",">","Rognac","L'Estaque",2019,2020,51,50,"2019-12-17","00:00","2020-12-12T04:30:00","04:30",661,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"147 jours dans le régime binaire"]
["SNCF Réseau","6644748561_6644560961","Miramas-Marseille",">","Rognac","L'Estaque",2019,2020,51,50,"2019-12-16T09:55:00","09:55","2020-12-11T10:50:00","10:50",2709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644748561_6644564361","Miramas-Marseille",">","Rognac","L'Estaque",2019,2020,51,50,"2019-12-16T09:55:00","09:55","2020-12-11T11:03:00","11:03",2763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644748661_6644618561","Avignon-Miramasparouest",">","Tarascon","Miramas",2019,2020,51,50,"2019-12-16T10:23:00","10:23","2020-12-11T11:01:00","11:01",2754,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644748661_6644619361","Avignon-Miramasparouest",">","Tarascon","Miramas",2019,2020,52,49,"2019-12-23T00:30:00","00:30","2020-11-30T03:28:00","03:28",82,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","6644748661_6644620161","Avignon-Miramasparouest",">","Tarascon","Miramas",2019,2020,51,50,"2019-12-16T10:30:00","10:30","2020-12-11T11:57:00","11:57",2929,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","6644748661_6644621761","Avignon-Miramasparouest",">","Tarascon","Miramas",2020,2020,2,49,"2020-01-06T23:15:00","23:15","2020-12-04T05:13:00","05:13",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"167 jours dans le régime binaire"]
["SNCF Réseau","6644748661_6644620961","Avignon-Miramasparouest",">","Tarascon","Miramas",2019,2020,52,49,"2019-12-23T01:43:00","01:43","2020-11-30T04:45:00","04:45",112,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","6644748761_6644532761","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2019,2020,51,50,"2019-12-16T09:23:00","09:23","2020-12-11T10:40:00","10:40",2667,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644748761_6644533561","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2019,2020,51,50,"2019-12-16T15:06:00","15:06","2020-12-11T16:23:00","16:23",4097,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644748761_6644531761","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2020,2020,10,44,"2020-03-02T22:30:00","22:30","2020-10-30T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"104 jours dans le régime binaire"]
["SNCF Réseau","6644748961_6644548961","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2020,2020,10,44,"2020-03-02T22:30:00","22:30","2020-10-30T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"104 jours dans le régime binaire"]
["SNCF Réseau","6644748961_6644551561","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2019,2020,51,50,"2019-12-16T09:20:00","09:20","2020-12-11T10:38:00","10:38",2659,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644748961_6644549961","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",153,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6644748961_6644550761","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",153,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6644748961_6644552361","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2019,2020,51,50,"2019-12-16T14:51:00","14:51","2020-12-11T16:06:00","16:06",4026,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644749861_6644603561","Avignon-Miramasparest",">","Avignon","Cavaillon",2020,2020,14,47,"2020-03-30T09:08:00","09:08","2020-11-20T13:08:00","13:08",765,"DAY",null,null,null,null,null,null,null,null,null,null,null,"59 jours dans le régime binaire"]
["SNCF Réseau","6644749861_6644601161","Avignon-Miramasparest",">","Avignon","Cavaillon",2019,2020,51,50,"2019-12-16T11:20:00","11:20","2020-12-11T11:52:00","11:52",2967,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6644749861_6644604561","Avignon-Miramasparest",">","Avignon","Cavaillon",2019,2020,51,50,"2019-12-16T13:37:00","13:37","2020-12-11T15:07:00","15:07",3780,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651389161_6651240861","Amiens-Douai",">","Arras","Douai",2020,2020,9,42,"2020-02-24T23:00:00","23:00","2020-10-16T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"28 jours dans le régime binaire"]
["SNCF Réseau","6651389161_6651239261","Amiens-Douai",">","Arras","Douai",2019,2020,51,50,"2019-12-16T09:50:00","09:50","2020-12-11T10:56:00","10:56",2734,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651389161_6651242461","Amiens-Douai",">","Arras","Douai",2019,2020,52,38,"2019-12-23T01:30:00","01:30","2020-09-14T04:30:00","04:30",25,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6651389161_6651243261","Amiens-Douai",">","Arras","Douai",2019,2020,51,50,"2019-12-16T14:29:00","14:29","2020-12-11T15:20:00","15:20",3834,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651389161_6651241661","Amiens-Douai",">","Arras","Douai",2019,2020,52,38,"2019-12-23T00:35:00","00:35","2020-09-14T03:20:00","03:20",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6651389161_6651240061","Amiens-Douai",">","Arras","Douai",2020,2020,9,42,"2020-02-24T22:50:00","22:50","2020-10-16T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"28 jours dans le régime binaire"]
["SNCF Réseau","6651388861_6651205661","Paris-Busigny",">","Ormoy","Longueil",2019,2020,51,50,"2019-12-16T14:12:00","14:12","2020-12-11T15:52:00","15:52",3968,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651388861_6651204661","Paris-Busigny",">","Ormoy","Longueil",2019,2020,51,50,"2019-12-16T23:22:00","23:22","2020-12-11T05:10:00","05:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"180 jours dans le régime binaire"]
["SNCF Réseau","6651388861_6651203861","Paris-Busigny",">","Ormoy","Longueil",2019,2020,51,50,"2019-12-16T10:57:00","10:57","2020-12-11T12:33:00","12:33",3139,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651258461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T10:05:00","10:05","2020-12-11T11:20:00","11:20",2857,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651265661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T13:55:00","13:55","2020-12-11T14:38:00","14:38",3044,"DAY",null,null,null,null,null,null,null,null,null,null,null,"209 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651260061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T01:20:00","01:20","2020-11-30T04:05:00","04:05",72,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651264061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T10:25:00","10:25","2020-12-11T11:37:00","11:37",2905,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651256661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,1,50,"2019-12-30T23:39:00","23:39","2020-12-11T04:59:00","04:59",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"134 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651264861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T01:30:00","01:30","2020-11-30T04:25:00","04:25",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651261661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T00:10:00","00:10","2020-11-30T03:20:00","03:20",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651255861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T13:38:00","13:38","2020-12-11T14:27:00","14:27",3613,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651262461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T00:35:00","00:35","2020-11-30T03:20:00","03:20",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651260861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T13:55:00","13:55","2020-12-11T14:38:00","14:38",3673,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651263261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T00:05:00","00:05","2020-11-30T03:10:00","03:10",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651257661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T09:58:00","09:58","2020-12-11T11:05:00","11:05",2783,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","6651388961_6651259261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T00:20:00","00:20","2020-11-30T03:30:00","03:30",62,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6651389561_6651207061","Boulogne-Calais",">","Marquise","Calais",2020,2020,2,50,"2020-01-06T23:08:00","23:08","2020-12-11T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651389561_6651209461","Boulogne-Calais",">","Marquise","Calais",2019,2020,51,50,"2019-12-16T14:20:00","14:20","2020-12-11T15:30:00","15:30",3876,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651389561_6651208661","Boulogne-Calais",">","Marquise","Calais",2020,2020,2,50,"2020-01-06T23:08:00","23:08","2020-12-11T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651389561_6651207861","Boulogne-Calais",">","Marquise","Calais",2019,2020,51,50,"2019-12-16T11:00:00","11:00","2020-12-11T11:55:00","11:55",2980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651389561_6651211061","Boulogne-Calais",">","Marquise","Calais",2019,2020,51,41,"2019-12-16","00:00","2020-10-05T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6651389561_6651210261","Boulogne-Calais",">","Marquise","Calais",2019,2020,51,41,"2019-12-16","00:00","2020-10-05T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6651386561_6651323061","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2019,2020,51,50,"2019-12-16T13:30:00","13:30","2020-12-11T14:24:00","14:24",3600,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651386561_6651325461","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2019,2020,51,50,"2019-12-16T00:30:00","00:30","2020-12-07T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","6651386561_6651324661","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2020,2020,7,48,"2020-02-10T11:00:00","11:00","2020-11-27T15:00:00","15:00",424,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","6651386561_6651323861","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2019,2020,51,50,"2019-12-16T11:30:00","11:30","2020-12-11T12:37:00","12:37",3155,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651386561_6651326461","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2020,2020,7,48,"2020-02-10T11:00:00","11:00","2020-11-27T15:00:00","15:00",424,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","6651385361_6651363061","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2019,2020,51,50,"2019-12-16T09:08:00","09:08","2020-12-11T10:40:00","10:40",2668,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651385361_6651360661","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2020,2020,5,5,"2020-01-27T09:30:00","09:30","2020-01-31T13:30:00","13:30",58,"DAY",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
["SNCF Réseau","6651385361_6651362261","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2019,2020,51,50,"2019-12-16T09:40:00","09:40","2020-12-11T10:44:00","10:44",2684,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651385361_6651361461","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2019,2020,52,50,"2019-12-23T01:35:00","01:35","2020-12-07T05:10:00","05:10",81,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","6651385661_6651369261","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2019,2020,51,37,"2019-12-22T23:00:00","23:00","2020-09-13T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6651385661_6651371861","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2019,2020,51,50,"2019-12-16T09:55:00","09:55","2020-12-11T11:05:00","11:05",2772,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651385661_6651370861","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2020,2020,7,48,"2020-02-10T22:30:00","22:30","2020-11-27T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","6651385661_6651372661","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2019,2020,51,50,"2019-12-16T14:06:00","14:06","2020-12-11T14:56:00","14:56",3734,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651385661_6651370061","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2019,2020,52,38,"2019-12-23","00:00","2020-09-14T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6651386461_6651364661","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2020,2020,4,42,"2020-01-20T22:58:00","22:58","2020-10-16T04:58:00","04:58",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"94 jours dans le régime binaire"]
["SNCF Réseau","6651386461_6651365661","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2019,2020,52,50,"2019-12-23T01:35:00","01:35","2020-12-07T04:55:00","04:55",111,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","6651386461_6651368061","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2019,2020,51,50,"2019-12-16T10:02:00","10:02","2020-12-11T11:12:00","11:12",2801,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651386461_6651366461","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2019,2020,51,50,"2019-12-16T14:14:00","14:14","2020-12-11T14:58:00","14:58",3742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651386461_6651367261","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2019,2020,52,50,"2019-12-23","00:00","2020-12-07T03:00:00","03:00",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","6651387761_6651185661","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2019,2020,51,50,"2019-12-16T13:16:00","13:16","2020-12-11T14:08:00","14:08",3534,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387761_6651183061","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2019,2020,51,50,"2019-12-16T00:30:00","00:30","2020-12-07T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","6651387761_6651184061","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2020,2020,7,48,"2020-02-10T11:00:00","11:00","2020-11-27T15:00:00","15:00",424,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","6651387761_6651186461","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2019,2020,51,50,"2019-12-16T11:23:00","11:23","2020-12-11T12:30:00","12:30",3126,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387761_6651184861","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2020,2020,7,48,"2020-02-10T11:00:00","11:00","2020-11-27T15:00:00","15:00",424,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","6651386761_6651354261","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2019,2020,52,44,"2019-12-29T23:35:00","23:35","2020-11-01T02:45:00","02:45",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651386761_6651356061","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2019,2020,51,50,"2019-12-16T13:48:00","13:48","2020-12-11T15:10:00","15:10",3793,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651386761_6651353461","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2019,2020,52,44,"2019-12-29T23:15:00","23:15","2020-11-01T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651386761_6651355061","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2019,2020,51,49,"2019-12-16T22:50:00","22:50","2020-12-04T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","6651386761_6651352661","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2019,2020,51,50,"2019-12-16T09:55:00","09:55","2020-12-11T10:43:00","10:43",2679,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384861_6651155461","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2019,2020,52,44,"2019-12-29T22:50:00","22:50","2020-11-01T01:40:00","01:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651384861_6651157861","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2019,2020,52,44,"2019-12-29T23:10:00","23:10","2020-11-01T02:20:00","02:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651384861_6651158661","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2020,19,38,"2020-05-04T22:50:00","22:50","2020-09-18T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651384861_6651157061","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2019,2020,51,50,"2019-12-16T14:21:00","14:21","2020-12-11T15:26:00","15:26",3859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384861_6651159461","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2019,2020,51,50,"2019-12-16T10:37:00","10:37","2020-12-11T11:31:00","11:31",2880,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384861_6651156261","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2020,19,38,"2020-05-04T22:50:00","22:50","2020-09-18T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651388161_6651251061","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2019,2020,51,50,"2019-12-16T00:46:00","00:46","2020-12-07T04:00:00","04:00",203,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651388161_6651249461","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2020,15,50,"2020-04-06T11:09:00","11:09","2020-12-11T14:58:00","14:58",482,"DAY",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","6651388161_6651252661","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2019,2020,51,50,"2019-12-16T11:02:00","11:02","2020-12-11T12:20:00","12:20",3084,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651388161_6651251861","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2019,2020,51,50,"2019-12-16T14:10:00","14:10","2020-12-11T14:54:00","14:54",3725,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651388161_6651248661","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2019,2020,51,50,"2019-12-16T00:25:00","00:25","2020-12-07T03:00:00","03:00",152,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651388161_6651250261","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2020,15,50,"2020-04-06T10:47:00","10:47","2020-12-11T14:58:00","14:58",483,"DAY",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","6651384561_6651247461","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2019,2020,51,50,"2019-12-16T15:47:00","15:47","2020-12-11T16:21:00","16:21",4088,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384561_6651246661","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2020,2020,6,6,"2020-02-03T09:30:00","09:30","2020-02-07T13:30:00","13:30",58,"DAY",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
["SNCF Réseau","6651384561_6651245061","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2019,2020,52,50,"2019-12-23T00:30:00","00:30","2020-12-07T03:30:00","03:30",55,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","6651384561_6651245861","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2019,2020,51,50,"2019-12-16T15:21:00","15:21","2020-12-11T16:12:00","16:12",4050,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651231661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16T00:30:00","00:30","2020-11-30T03:30:00","03:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651230661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2020,4,49,"2020-01-20T23:17:00","23:17","2020-12-04T05:15:00","05:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651237261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,50,"2019-12-16T14:51:00","14:51","2020-12-11T15:44:00","15:44",3934,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651234861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,50,"2019-12-16T14:34:00","14:34","2020-12-11T15:24:00","15:24",3850,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651235661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16T00:30:00","00:30","2020-11-30T03:30:00","03:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651236461","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,50,"2019-12-16T11:10:00","11:10","2020-12-11T12:21:00","12:21",3088,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651229061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,50,"2019-12-16T13:30:00","13:30","2020-12-11T14:50:00","14:50",3709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651233261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,50,"2019-12-16T14:24:00","14:24","2020-12-11T15:19:00","15:19",3830,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651238061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16T00:35:00","00:35","2020-11-30T03:15:00","03:15",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651234061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16T00:30:00","00:30","2020-11-30T03:30:00","03:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651229861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16","00:00","2020-11-30T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651387561_6651232461","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16T00:30:00","00:30","2020-11-30T03:30:00","03:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651387061_6651180661","Paris-Busigny",">","Creil","LongueilSteMarie",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:10:00","03:10",164,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","6651387061_6651178861","Paris-Busigny",">","Creil","LongueilSteMarie",2019,2020,1,50,"2019-12-31","00:00","2020-12-12T05:05:00","05:05",1092,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"215 jours dans le régime binaire"]
["SNCF Réseau","6651387061_6651178061","Paris-Busigny",">","Creil","LongueilSteMarie",2019,2020,51,50,"2019-12-16T14:17:00","14:17","2020-12-11T15:02:00","15:02",3759,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387061_6651179861","Paris-Busigny",">","Creil","LongueilSteMarie",2019,2020,51,50,"2019-12-16T09:46:00","09:46","2020-12-11T10:57:00","10:57",2738,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387061_6651181461","Paris-Busigny",">","Creil","LongueilSteMarie",2019,2020,51,50,"2019-12-16T01:35:00","01:35","2020-12-07T04:20:00","04:20",223,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","6651386861_6651284061","Amiens-Douai","<","Arras","Bif de l'arbre Robert",2019,2020,51,50,"2019-12-16T15:15:00","15:15","2020-12-11T16:12:00","16:12",4050,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384961_6651381661","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,52,42,"2019-12-29T21:28:00","21:28","2020-10-18T01:08:00","01:08",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6651384961_6651375061","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,52,42,"2019-12-29T21:27:00","21:27","2020-10-18T23:57:00","23:57",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6651384961_6651380861","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T09:32:00","09:32","2020-12-11T10:17:00","10:17",2571,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384961_6651380061","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T11:15:00","11:15","2020-12-11T12:25:00","12:25",3105,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384961_6651379261","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T09:00:00","09:00","2020-12-11T09:46:00","09:46",2442,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384961_6651374261","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T10:50:00","10:50","2020-12-11T12:00:00","12:00",3001,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384961_6651378461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T11:00:00","11:00","2020-12-11T12:15:00","12:15",3063,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384961_6651382461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T09:17:00","09:17","2020-12-11T10:00:00","10:00",2500,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384961_6651375861","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2020,10,42,"2020-03-02T10:00:00","10:00","2020-10-16T14:00:00","14:00",270,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6651387361_6651294861","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2019,2020,51,45,"2019-12-16","00:00","2020-11-02T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651387361_6651296461","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2019,2020,51,45,"2019-12-16","00:00","2020-11-02T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","6651387361_6651295661","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2019,2020,51,50,"2019-12-16T09:36:00","09:36","2020-12-11T10:43:00","10:43",2680,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651387361_6651298061","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2020,2020,17,49,"2020-04-20T22:50:00","22:50","2020-12-04T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","6651387361_6651297261","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2019,2020,51,50,"2019-12-16T14:20:00","14:20","2020-12-11T15:09:00","15:09",3788,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651386661_6651301861","Amiens-Douai",">","Arras","Bif d'Agny",2019,2020,51,50,"2019-12-16T09:46:00","09:46","2020-12-11T10:50:00","10:50",2709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384761_6651314661","Paris-Amiens",">","Creil","Longueau",2019,2020,52,50,"2019-12-23T01:45:00","01:45","2020-12-07T04:20:00","04:20",76,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6651384761_6651319461","Paris-Amiens",">","Creil","Longueau",2019,2020,52,50,"2019-12-23T01:45:00","01:45","2020-12-07T05:15:00","05:15",92,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6651384761_6651316261","Paris-Amiens",">","Creil","Longueau",2020,2020,7,48,"2020-02-10T22:55:00","22:55","2020-11-27T04:15:00","04:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"110 jours dans le régime binaire"]
["SNCF Réseau","6651384761_6651321861","Paris-Amiens",">","Creil","Longueau",2019,2020,52,50,"2019-12-23T02:15:00","02:15","2020-12-07T05:40:00","05:40",99,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6651384761_6651317861","Paris-Amiens",">","Creil","Longueau",2019,2020,51,50,"2019-12-16T12:35:00","12:35","2020-12-11T13:56:00","13:56",3484,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384761_6651320261","Paris-Amiens",">","Creil","Longueau",2019,2020,51,50,"2019-12-16T10:50:00","10:50","2020-12-11T11:30:00","11:30",2875,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384761_6651317061","Paris-Amiens",">","Creil","Longueau",2019,2020,51,50,"2019-12-16T14:58:00","14:58","2020-12-11T16:03:00","16:03",4013,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384761_6651318661","Paris-Amiens",">","Creil","Longueau",2019,2020,52,50,"2019-12-23T01:20:00","01:20","2020-12-07T04:05:00","04:05",72,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6651384761_6651315461","Paris-Amiens",">","Creil","Longueau",2019,2020,51,50,"2019-12-16T11:04:00","11:04","2020-12-11T11:51:00","11:51",2963,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651384761_6651321061","Paris-Amiens",">","Creil","Longueau",2020,2020,7,48,"2020-02-10T23:10:00","23:10","2020-11-27T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"110 jours dans le régime binaire"]
["SNCF Réseau","6651385761_6651338461","Boulogne-Calais",">","Boulogne","Marquise",2019,2020,51,41,"2019-12-16","00:00","2020-10-05T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6651385761_6651336061","Boulogne-Calais",">","Boulogne","Marquise",2020,2020,2,50,"2020-01-06T22:15:00","22:15","2020-12-11T04:19:00","04:19",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651385761_6651337661","Boulogne-Calais",">","Boulogne","Marquise",2020,2020,2,50,"2020-01-06T22:03:00","22:03","2020-12-11T04:38:00","04:38",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
["SNCF Réseau","6651385761_6651339261","Boulogne-Calais",">","Boulogne","Marquise",2019,2020,51,50,"2019-12-16T14:15:00","14:15","2020-12-11T15:35:00","15:35",3897,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651385761_6651336861","Boulogne-Calais",">","Boulogne","Marquise",2019,2020,51,50,"2019-12-16T11:05:00","11:05","2020-12-11T11:55:00","11:55",2979,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","6651385761_6651340061","Boulogne-Calais",">","Boulogne","Marquise",2019,2020,51,41,"2019-12-16","00:00","2020-10-05T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","6645698661_6645593361","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2019,2020,51,50,"2019-12-16T13:26:00","13:26","2020-12-11T14:19:00","14:19",2950,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
["SNCF Réseau","6645698661_6645591761","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2020,2,43,"2020-01-12T23:06:00","23:06","2020-10-25T02:12:00","02:12",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645698661_6645592561","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2020,3,44,"2020-01-13T02:57:00","02:57","2020-10-26T05:47:00","05:47",72,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645698661_6645594961","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2020,21,24,"2020-05-18T10:26:00","10:26","2020-06-12T15:16:00","15:16",264,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6645698661_6645590961","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2020,21,24,"2020-05-18T09:34:00","09:34","2020-06-12T14:36:00","14:36",253,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6645698661_6645594161","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2019,2020,51,50,"2019-12-16T11:32:00","11:32","2020-12-11T12:38:00","12:38",2603,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
["SNCF Réseau","6645698761_6645550761","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,36,49,"2020-08-31T09:47:00","09:47","2020-12-04T15:47:00","15:47",1079,"DAY",null,null,null,null,null,null,null,null,null,null,null,"69 jours dans le régime binaire"]
["SNCF Réseau","6645698761_6645552561","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,25,35,"2020-06-15T11:00:00","11:00","2020-08-28T11:22:00","11:22",375,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","6645698761_6645555761","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,4,42,"2020-01-20T02:49:00","02:49","2020-10-12T04:59:00","04:59",52,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6645698761_6645551761","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,1,50,"2020-01-02T11:55:00","11:55","2020-12-11T12:00:00","12:00",1488,"DAY",null,null,null,null,null,null,null,null,null,null,null,"125 jours dans le régime binaire"]
["SNCF Réseau","6645698761_6645554961","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,4,42,"2020-01-20T00:05:00","00:05","2020-10-12T03:32:00","03:32",38,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6645698761_6645549961","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,25,35,"2020-06-15T13:30:00","13:30","2020-08-28T15:05:00","15:05",499,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","6645698761_6645556561","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,1,50,"2020-01-02T12:40:00","12:40","2020-12-11T14:30:00","14:30",1741,"DAY",null,null,null,null,null,null,null,null,null,null,null,"121 jours dans le régime binaire"]
["SNCF Réseau","6645699161_6645583961","Valence - Avignon",">","Sorgues","Avignon",2020,2020,4,37,"2020-01-20T01:05:00","01:05","2020-09-07T04:12:00","04:12",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","6645699161_6645579961","Valence - Avignon",">","Sorgues","Avignon",2019,2020,51,50,"2019-12-16T10:43:00","10:43","2020-12-11T11:36:00","11:36",2402,"DAY",null,null,null,null,null,null,null,null,null,null,null,"208 jours dans le régime binaire"]
["SNCF Réseau","6645699161_6645581561","Valence - Avignon",">","Sorgues","Avignon",2020,2020,31,34,"2020-07-27T08:16:00","08:16","2020-08-21T12:50:00","12:50",248,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6645699161_6645580761","Valence - Avignon",">","Sorgues","Avignon",2020,2020,4,37,"2020-01-20T01:17:00","01:17","2020-09-07T04:10:00","04:10",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","6645699161_6645583161","Valence - Avignon",">","Sorgues","Avignon",2019,2020,51,50,"2019-12-16T13:52:00","13:52","2020-12-11T15:02:00","15:02",3113,"DAY",null,null,null,null,null,null,null,null,null,null,null,"208 jours dans le régime binaire"]
["SNCF Réseau","6645698061_6645575561","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2019,2020,51,50,"2019-12-16T12:57:00","12:57","2020-12-11T13:32:00","13:32",2788,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
["SNCF Réseau","6645698061_6645574761","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2020,23,24,"2020-06-02T09:59:00","09:59","2020-06-12T15:24:00","15:24",128,"DAY",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
["SNCF Réseau","6645698061_6645573961","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2020,3,44,"2020-01-13T02:34:00","02:34","2020-10-26T05:10:00","05:10",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645698061_6645572361","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2019,2020,51,50,"2019-12-16T12:34:00","12:34","2020-12-11T13:33:00","13:33",2453,"DAY",null,null,null,null,null,null,null,null,null,null,null,"182 jours dans le régime binaire"]
["SNCF Réseau","6645698061_6645577161","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2019,2020,51,50,"2019-12-16T11:59:00","11:59","2020-12-11T13:28:00","13:28",2748,"DAY",null,null,null,null,null,null,null,null,null,null,null,"205 jours dans le régime binaire"]
["SNCF Réseau","6645698061_6645576361","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2020,3,44,"2020-01-13T02:10:00","02:10","2020-10-26T05:10:00","05:10",65,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645698061_6645577961","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2020,2,43,"2020-01-12T23:12:00","23:12","2020-10-25T02:51:00","02:51",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645698561_6645567361","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2020,1,50,"2020-01-02T13:28:00","13:28","2020-12-11T13:50:00","13:50",1950,"DAY",null,null,null,null,null,null,null,null,null,null,null,"142 jours dans le régime binaire"]
["SNCF Réseau","6645698561_6645569161","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2020,1,50,"2020-01-02T11:15:00","11:15","2020-12-11T12:48:00","12:48",1806,"DAY",null,null,null,null,null,null,null,null,null,null,null,"142 jours dans le régime binaire"]
["SNCF Réseau","6645698561_6645568161","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2020,13,44,"2020-03-23T09:15:00","09:15","2020-10-30T15:15:00","15:15",600,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","6645698561_6645570761","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2020,4,42,"2020-01-20T04:05:00","04:05","2020-10-12T06:35:00","06:35",68,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6645698561_6645569961","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2020,3,41,"2020-01-19T21:50:00","21:50","2020-10-11T01:20:00","01:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6645697761_6645561361","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2020,3,44,"2020-01-13T02:55:00","02:55","2020-10-26T05:35:00","05:35",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645697761_6645562961","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2020,2,43,"2020-01-12T23:00:00","23:00","2020-10-25T02:20:00","02:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645697761_6645563761","Lyon-Valence",">","Vienne","St Rambert (par RG)",2019,2020,51,50,"2019-12-16T11:40:00","11:40","2020-12-11T12:58:00","12:58",2672,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
["SNCF Réseau","6645697761_6645560561","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2020,21,24,"2020-05-18T10:21:00","10:21","2020-06-12T14:55:00","14:55",258,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6645697761_6645559761","Lyon-Valence",">","Vienne","St Rambert (par RG)",2019,2020,51,50,"2019-12-16T13:18:00","13:18","2020-12-11T14:00:00","14:00",2884,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
["SNCF Réseau","6645697761_6645562161","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2020,21,24,"2020-05-18T09:43:00","09:43","2020-06-12T14:59:00","14:59",259,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","6645698961_6645654361","Valence - Avignon",">","Portes","Livron (par RG)",2019,2020,51,50,"2019-12-16T12:34:00","12:34","2020-12-11T13:40:00","13:40",2816,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
["SNCF Réseau","6645698961_6645658361","Valence - Avignon",">","Portes","Livron (par RG)",2020,2020,3,44,"2020-01-13T01:55:00","01:55","2020-10-26T04:45:00","04:45",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645698961_6645657561","Valence - Avignon",">","Portes","Livron (par RG)",2019,2020,51,50,"2019-12-16T12:05:00","12:05","2020-12-11T12:55:00","12:55",2661,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
["SNCF Réseau","6645698961_6645655161","Valence - Avignon",">","Portes","Livron (par RG)",2020,2020,2,43,"2020-01-12T23:54:00","23:54","2020-10-25T03:07:00","03:07",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645697961_6645639761","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2020,4,37,"2020-01-20T01:35:00","01:35","2020-09-07T04:17:00","04:17",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","6645697961_6645636561","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2020,4,37,"2020-01-20T00:40:00","00:40","2020-09-07T04:05:00","04:05",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","6645697961_6645638961","Valence - Avignon",">","Pierrelatte","Sorgues",2019,2020,51,50,"2019-12-16T11:17:00","11:17","2020-12-11T11:43:00","11:43",2425,"DAY",null,null,null,null,null,null,null,null,null,null,null,"208 jours dans le régime binaire"]
["SNCF Réseau","6645697961_6645638161","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2020,31,34,"2020-07-27T08:32:00","08:32","2020-08-21T12:50:00","12:50",248,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6645697961_6645637361","Valence - Avignon",">","Pierrelatte","Sorgues",2019,2020,51,50,"2019-12-16T13:13:00","13:13","2020-12-11T14:48:00","14:48",3065,"DAY",null,null,null,null,null,null,null,null,null,null,null,"208 jours dans le régime binaire"]
["SNCF Réseau","6645699661_6645510561","Valence - Avignon",">","Raccordement de Livron","LaVoulte",2020,2020,5,9,"2020-01-30T08:08:00","08:08","2020-02-28T09:38:00","09:38",49,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","6645699661_6645512361","Valence - Avignon",">","Raccordement de Livron","LaVoulte",2020,2020,10,44,"2020-03-02T10:32:00","10:32","2020-10-30T15:32:00","15:32",300,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6645699361_6645523561","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2020,10,44,"2020-03-02T08:36:00","08:36","2020-10-30T14:36:00","14:36",1086,"DAY",null,null,null,null,null,null,null,null,null,null,null,"75 jours dans le régime binaire"]
["SNCF Réseau","6645699361_6645524561","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2020,1,50,"2020-01-02T12:50:00","12:50","2020-12-11T13:00:00","13:00",1118,"DAY",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
["SNCF Réseau","6645699361_6645526161","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2020,3,41,"2020-01-19T22:20:00","22:20","2020-10-11T02:00:00","02:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6645699361_6645522761","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2020,1,50,"2020-01-02T11:48:00","11:48","2020-12-11T13:34:00","13:34",1168,"DAY",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
["SNCF Réseau","6645699361_6645525361","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2020,4,42,"2020-01-20T03:35:00","03:35","2020-10-12T05:55:00","05:55",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","6645698261_6645505161","Lyon-Valence",">","RaccPeyraud","St Rambert",2020,2020,10,44,"2020-03-02T09:58:00","09:58","2020-10-30T14:58:00","14:58",289,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","6645699761_6645543961","Valence - Avignon",">","Livron","Pierrelatte",2020,2020,3,44,"2020-01-13T00:10:00","00:10","2020-10-26T03:40:00","03:40",47,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645699761_6645542361","Valence - Avignon",">","Livron","Pierrelatte",2020,2020,3,44,"2020-01-13T02:05:00","02:05","2020-10-26T04:35:00","04:35",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","6645699761_6645541561","Valence - Avignon",">","Livron","Pierrelatte",2020,2020,16,50,"2020-04-14T11:52:00","11:52","2020-12-11T12:20:00","12:20",1221,"DAY",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
["SNCF Réseau","6645699761_6645543161","Valence - Avignon",">","Livron","Pierrelatte",2020,2020,16,50,"2020-04-14T12:41:00","12:41","2020-12-11T14:11:00","14:11",1405,"DAY",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
["SNCF Réseau","6648859661_6648654361","Longuyon-Metz-Sarrebourg",">","Hauconcourt","Woippy",2020,2020,8,47,"2020-02-17T10:00:00","10:00","2020-11-20T18:00:00","18:00",170,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","6648863061_6648722761","Sarrebourg-Basel",">","Mulhouse","Chalampe",2019,2020,51,50,"2019-12-17T08:52:00","08:52","2020-12-11T09:52:00","09:52",1392,"DAY",null,null,null,null,null,null,null,null,null,null,null,"142 jours dans le régime binaire"]
["SNCF Réseau","6648863061_6648723561","Sarrebourg-Basel",">","Mulhouse","Chalampe",2020,2020,17,43,"2020-04-20T22:00:00","22:00","2020-10-23T04:00:00","04:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","6648854861_6648622361","Longuyon-Metz-Sarrebourg",">","Longwy","Saulnes",2020,2020,31,31,"2020-07-27T08:00:00","08:00","2020-07-31T16:00:00","16:00",0,"ALL DAY",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
["SNCF Réseau","6648854761_6648652161","Sarrebourg-Basel",">","Colmar","NeufBrisach",2020,2020,36,37,"2020-09-04T11:40:00","11:40","2020-09-11T15:40:00","15:40",19,"DAY",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","6648854761_6648653161","Sarrebourg-Basel",">","Colmar","NeufBrisach",2020,2020,36,37,"2020-08-31T12:00:00","12:00","2020-09-10T20:00:00","20:00",148,"DAY",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","10295929061_10295502561","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295929061_10295503361","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","10295929061_10295499361","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295926061_10295532761","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2022,2022,9,48,"2022-02-28T10:10:00","10:10","2022-12-02T16:10:00","16:10",976,"DAY",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","10295928561_10295667761","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2022,2022,13,37,"2022-03-28T10:30:00","10:30","2022-09-16T16:30:00","16:30",633,"DAY",null,null,null,null,null,null,null,null,null,null,null,"39 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295508961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,8,48,"2022-02-22T11:30:00","11:30","2022-12-02T15:30:00","15:30",810,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295509761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",856,"DAY",null,null,null,null,null,null,null,null,null,null,null,"56 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295516161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,8,48,"2022-02-22T11:30:00","11:30","2022-12-02T15:30:00","15:30",810,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295517761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295516961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295512161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",856,"DAY",null,null,null,null,null,null,null,null,null,null,null,"56 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295511361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295510561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295563161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",856,"DAY",null,null,null,null,null,null,null,null,null,null,null,"56 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295571161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295562361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",856,"DAY",null,null,null,null,null,null,null,null,null,null,null,"56 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295570361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,8,48,"2022-02-22T11:30:00","11:30","2022-12-02T15:30:00","15:30",810,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295565561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,8,48,"2022-02-22T11:30:00","11:30","2022-12-02T15:30:00","15:30",810,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295567161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295566361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295564761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295771961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2022,2022,7,40,"2022-02-14T09:30:00","09:30","2022-10-03T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","10295924961_10295458761","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2022,2022,9,48,"2022-02-28T10:12:00","10:12","2022-12-02T16:12:00","16:12",977,"DAY",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295645561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295650361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",856,"DAY",null,null,null,null,null,null,null,null,null,null,null,"56 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295643961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295644761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",856,"DAY",null,null,null,null,null,null,null,null,null,null,null,"56 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295649561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295639961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295638361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,8,48,"2022-02-22T11:30:00","11:30","2022-12-02T15:30:00","15:30",810,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295928061_10295555561","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2022,2022,9,48,"2022-02-28T09:40:00","09:40","2022-12-02T16:10:00","16:10",976,"DAY",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","10295928061_10295557161","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2022,2022,9,48,"2022-02-28T10:00:00","10:00","2022-12-02T15:30:00","15:30",935,"DAY",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]

{"sheet":"SBB","index":6,"n_rows":11,"n_cols":31,"rows_kept":11,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["SBB Infra",6553,"Basel St. Johann","< >","BSSJ","BSSJ",2021,2021,null,null,"2021-02-26",null,"2021-07-30",null,null,"Night","Signal box works","x",null,null,null,null,"x","x",null,"x",null,"Totalclosure 8 nights for 4 hours. Exactlly dasy tbd"]
["SBB Infra",1872,"Basel RB","< >","BSGB","BSRB",2021,2021,null,null,"2021-03-09",null,"2021-04-27",null,null,null,"Switch works","x",null,null,null,null,"x","x",null,"x",null,"Nordkopf 100er Weichen (Zulauf Basel GB - RB eingeschränkt), 6 WE Sa/Su - Su/Mo (11.04-12.04 02 am to 04 am totalclosure, 17.04-19.04 10.00 am - 04.00am totalclosure). Trains direction SNCF  with delay till15 Min"]
["SBB Infra",29170,"Muttenz","< >","BSGB","BSRB",2021,2021,null,null,"2021-01-01",null,"2021-12-31",null,null,"continuous","Catenary works",null,"x",null,null,null,null,"x",null,"x",null,"16-18.10, 22-24.10, 30.10.-01-11, 6-8.11 Line Basel - Muttenz totalclosure. Trains direction SNCF via  Basel GB - Basel RB"]
["SBB Infra",1899,"Basel GB - Basel RB","< >","BS","BSRB",2021,2021,null,null,"2019-10-13",null,"2019-11-22",null,null,null,"Switch works",null,null,null,null,null,null,null,null,"x",null,"Trains direction SNCF  with delay till15 Min"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille ","< >","LPFR","GEPR",2021,2021,null,null,null,null,null,null,"4 weeks","continuous","Platform works ",null,"x",null,null,null,null,null,null,"x",null,"Approx. 4 weeks/exact date unknown. Total closures may be possible"]
["SBB Infra",null,"Basel PB","< >","BSPB","BSPB",2022,2022,null,null,"2022-01-01",null,"2022-12-31",null,null,"continuous",null,null,"x"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<>","LPFR","GEPR",2023,2023,null,null,"2023-01-15",null,"2023-12-15",null,"11 months","continuous",null,null,"x",null,null,null,"x",null,null,"x",null,"Total closures may be possible"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"."]

{"sheet":"ACF CFL","index":7,"n_rows":89,"n_cols":31,"rows_kept":89,"cut":false,"hidden":false,"merged":[[0,17,0,21],[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["ACF/CFL","ACF27","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,23,24,"2021-06-12","01:30:00","2021-06-14","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF28","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,24,25,"2021-06-19","01:30:00","2021-06-21","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF29","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,25,26,"2021-06-26","01:30:00","2021-06-28","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF30","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,26,27,"2021-07-03","01:30:00","2021-07-05","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF33","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,27,28,"2021-07-10","01:30:00","2021-07-12","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF38","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,34,37,"2021-08-23","00:00:00","2021-09-13","04:00:00","22 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF58","Rodange-Bettembourg","< >","Rodange","Lamadelaine",2022,2022,34,37,"2022-08-27","01:00:00","2022-09-12","04:00:00","16 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF70","Rodange-Bettembourg","< >","Rodange","Aubange & Athus",2022,2022,47,48,"2022-11-21","00:00:00","2022-12-04","00:00:00","14 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF11","Rodange-Athus","< >","Rodange","Athus",2021,2021,7,8,"2021-02-20","04:00:00","2021-02-22","04:00:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF13","Rodange-Athus","< >","Rodange","Athus",2021,2021,8,9,"2021-02-27","04:00:00","2021-03-01","04:00:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF17","Rodange-Aubange","< >","Rodange","Aubange",2021,2021,15,15,"2021-04-17","01:00:00","2021-04-18","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF18","Rodange-Aubange","< >","Rodange","Aubange",2021,2021,16,16,"2021-04-24","01:00:00","2021-04-25","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF20","Rodange-Aubange/Athus","< >","Rodange","Aubange/Athus",2021,2021,17,17,"2021-05-01","01:00:00","2021-05-02","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF22","Rodange-Aubange/Athus","< >","Rodange","Aubange/Athus",2021,2021,18,18,"2021-04-24","01:00:00","2021-05-09","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF5","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2020,2020,38,39,"2020-09-19","01:30:00","2020-09-21","04:00:00","2 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF6","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2020,2020,43,44,"2020-10-24","01:30:00","2020-10-26","04:00:00","2 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF7","Rodange-Bettembourg","< >","Belval-Usines","Differdange",2020,2020,44,46,"2020-10-31","01:00:00","2020-11-09","04:00:00","9 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF8","Luxembourg-Kleinbettingen","< >","Bertrange","Kleinbettingen",2020,2020,44,46,"2020-10-31","01:00:00","2020-11-09","01:00:00","9 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF9","Rodange-Aubange","< >","Rodange","Aubange",2020,2021,45,8,"2020-11-06","01:00:00","2021-03-01","23:59:00","16 weeks","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF10","Luxembourg-Pétange","< >","Dippach","Luxembourg",2021,2021,6,7,"2021-02-13","01:30:00","2021-02-15","04:00:00","2 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF12","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2021,2021,7,8,"2021-02-16","01:00:00","2021-02-22","04:00:00","6 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF14","Rodange-Athus","< >","Rodange","Athus",2021,2021,9,16,"2021-03-05","00:00:00","2021-04-25","23:59:00","8 weeks","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF15","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,12,13,"2021-03-27","01:00:00","2021-03-29","04:00:00","3 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF16","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,13,16,"2021-04-03","04:00:00","2021-04-19","04:00:00","16 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF19","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,16,17,"2021-04-24","04:00:00","2021-04-26","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF21","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,17,18,"2021-05-01","04:00:00","2021-05-03","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF23","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,18,19,"2021-05-08","04:00:00","2021-05-10","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF24","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,19,20,"2021-05-15","04:00:00","2021-05-17","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF25","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2021,2021,20,21,"2021-05-22","01:00:00","2021-05-25","04:00:00","3 days","Night/Day","underpass renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF26","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,22,23,"2021-06-05","04:00:00","2021-06-07","04:00:00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF31","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,26,27,"2021-07-03","01:30:00","2021-07-05","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF32","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,27,28,"2021-07-10","01:30:00","2021-07-12","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF34","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,28,29,"2021-07-17","04:00:00","2021-07-19","04:00:00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF35","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,29,30,"2021-07-24","04:00:00","2021-07-26","04:00:00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF36","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,31,32,"2021-08-07","04:00:00","2021-08-08","04:00:00","1 day","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF37","Rodange-Bettembourg","< >","Esch/Alzette","Noertzange",2021,2021,34,37,"2021-08-28","00:00:00","2021-09-13","04:00:00","17 days","Night/Day","bridge maintenance/renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF39","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,37,38,"2021-09-18","04:00:00","2021-09-20","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF40","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,38,39,"2021-09-25","04:00:00","2021-09-27","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF41","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,39,40,"2021-10-02","01:30:00","2021-10-04","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF42","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,40,41,"2021-10-09","01:30:00","2021-10-11","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF43","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,41,42,"2021-10-16","04:00:00","2021-10-18","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF44","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,42,43,"2021-10-23","04:00:00","2021-10-25","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF45","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2021,2021,43,45,"2021-06-19","00:00:00","2021-06-21","04:00:00","3 days","Night/Day","bridge maintenance/renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF46","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2021,2021,43,45,"2021-10-30","00:00:00","2021-11-08","04:00:00","9 days","Night/Day","switch renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF47","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2021,2021,43,44,"2021-10-30","00:00:00","2021-11-02","04:00:00","3 days","Night/Day","underpass renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF78","Rodange-Bettembourg","< >","Belval-Lycée","Esch/Alzette",2022,2022,1,26,"2022-01-03","00:10:00","2022-06-30","04:45:00","172 days","Night","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"from Monday to Friday",null,"no"]
["ACF/CFL","ACF79","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,5,8,"2022-01-31","01:20:00","2020-02-25","04:10:00","26 days","Night","station renewal","x",null,null,null,null,"x","x",null,null,null,"from Monday to Friday",null,"no"]
["ACF/CFL","ACF48","Rodange-Bettembourg","< >","Noertzange","Esch/Alzette",2022,2022,8,9,"2022-02-26","01:00:00","2022-02-28","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF49","Rodange-Bettembourg","< >","Noertzange","Esch/Alzette",2022,2022,9,10,"2022-03-05","01:00:00","2022-03-07","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF80","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,11,12,"2022-03-19","01:00:00","2022-03-21","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF81","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,12,13,"2022-03-26","01:00:00","2022-03-28","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF82","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,16,17,"2022-04-23","01:00:00","2022-04-25","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF83","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,17,18,"2022-04-30","01:00:00","2022-05-02","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF50","Rodange-Bettembourg","< >","Differdange","Belval-Lycée",2022,2022,18,19,"2022-05-07","01:00:00","2022-05-10","04:00:00","3 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF84","Rodange-Bettembourg","< >","Differdange","Belval-Lycée",2022,2022,19,20,"2022-05-14","01:00:00","2022-05-16","04:00:00","3 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF51","Rodange-Bettembourg","< >","Belval-Usines","Esch/Alzette",2022,2022,20,22,"2022-05-21","01:00:00","2022-05-30","04:00:00","9 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF52","Rodange-Bettembourg","< >","Differdange","Belval-Lycée",2022,2022,22,23,"2022-06-04","01:00:00","2022-06-07","04:00:00","3 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF53","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,23,24,"2022-06-11","01:00:00","2022-06-13","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF54","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,24,25,"2022-06-18","01:00:00","2022-06-20","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF55","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,25,26,"2022-06-25","01:00:00","2022-06-27","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF56","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,26,27,"2022-07-02","01:00:00","2022-07-04","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF85","Rodange-Bettembourg","< >","Differdange","Belval-Lycée",2022,2022,27,28,"2022-07-09","01:00:00","2022-07-11","04:00:00","3 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF57","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,34,37,"2022-08-22","01:00:00","2022-09-12","04:00:00","22 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF86","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,34,37,"2022-08-27","01:00:00","2022-09-12","04:00:00","17 days","Night/Day","renewal station","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF59","Luxembourg-Bettembourg",">","Luxembourg","Bettembourg",2022,2022,36,37,"2022-09-09","23:30:00","2022-09-12","05:00:00","2 days","Night/Day","renewal of the line",null,"x",null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF60","Luxembourg-Bettembourg",">","Luxembourg","Bettembourg",2022,2022,37,38,"2022-09-16","23:30:00","2022-09-19","05:00:00","2 days","Night/Day","renewal of the line",null,"x",null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF87","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,37,38,"2022-09-17","01:00:00","2022-09-19","04:00:00","2 days","Night/Day","renewal station","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF61","Rodange-Bettembourg","< >","Belval-Usines","Pétange",2022,2022,38,39,"2022-09-24","01:00:00","2022-09-26","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF62","Rodange-Bettembourg","< >","Belval-Usines","Pétange",2022,2022,39,40,"2022-10-01","01:00:00","2022-10-03","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF63","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,40,41,"2022-10-08","01:00:00","2022-10-10","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF64","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,41,42,"2022-10-15","01:00:00","2022-10-17","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF65","Luxembourg-Bettembourg",">","Luxembourg","Bettembourg",2022,2022,42,43,"2022-10-22","23:30:00","2022-10-24","05:00:00","2 days","Night/Day","renewal of the line",null,"x",null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF66","Rodange-Bettembourg","< >","Belval-Usines","Pétange",2022,2022,42,43,"2022-10-22","01:00:00","2022-10-24","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF67","Luxembourg-Bettembourg","< >","Luxembourg-triage","Berchem",2022,2022,43,44,"2022-10-29","01:00:00","2022-10-31","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF68","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,45,46,"2022-11-12","01:00:00","2022-11-14","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF69","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,46,47,"2022-11-19","01:00:00","2022-11-21","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF88","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,48,49,"2022-11-21","01:00:00","2022-12-04","04:00:00","14 days","Night/day","renewal of station","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF71","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,47,48,"2022-11-26","01:00:00","2022-11-28","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF72","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,48,49,"2022-12-02","01:00:00","2022-12-04","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF73","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,49,50,"2022-12-10","01:00:00","2022-12-12","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF89","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,49,50,"2022-12-10","01:00:00","2022-12-12","04:00:00","14 days","Night/day","renewal of station","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF74","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,50,51,"2022-12-17","01:00:00","2022-12-19","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF75","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2021,2021,45,46,"2021-11-13","04:00:00","2021-11-15","04:00:00","2 days","Night/Day","bridge maintenance/renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF76","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,49,50,"2021-12-11","04:00:00","2021-12-13","04:00:00","2 days","Night/Day","project Howald","x",null,null,null,null,"x","x",null,null,null,"continious restriction"]
["ACF/CFL","ACF77","Luxembourg-Bettembourg","< >","Luxembourg","Bettemboourg",2021,2021,50,51,"2021-12-18","04:00:00","2021-12-20","04:00:00","2 days","Night/Day","project Howald","x",null,null,null,null,"x","x",null,null,null,"continious restriction"]
[]
["HIGHTLIGHTS --> TOTAL CLOSURE OF THE CORRIDOR RFC NSM"]