{"text_format":"1","workbook":"xlsx","n_sheets":8,"sheets":["Home","Main Impact Map","ProRail","Infrabel","Data","SNCFR","SBB","ACF CFL"],"not_rendered":{"charts":0,"images":13,"macros":1,"external_links":6,"defined_names":61,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Home","index":0,"n_rows":15,"n_cols":15,"rows_kept":15,"cut":false,"hidden":false,"merged":[[14,0,14,5]]}
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"! click icon to follow !"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["version 28 June 2019"]

{"sheet":"Main Impact Map","index":1,"n_rows":12,"n_cols":14,"rows_kept":12,"cut":false,"hidden":false,"merged":[[45,5,46,7]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Main TCR for TT 2020"]

{"sheet":"ProRail","index":2,"n_rows":46,"n_cols":16,"rows_kept":46,"cut":false,"hidden":false,"merged":[]}
[2020]
["Week","Project","Kenmerk","In Cluster (combi)","Hindercategorie","Duur ","Dag begin","Datum begin","Tijd begin","Dag einde","Datum einde","Tijd einde","Locatie","Deelcorridor","Werkzaamheden","Afspraken uit overleg"]
["05, 06","Z-906106","LZ01-01","C-000278","R",2.1666666666666665,"Zaterdag","2020-02-01","01:00:00","Maandag","2020-02-03","05:00:00"," Mdbz, Zlw","Ddr-Bd,Ddr-Rsd,Ddr-Zlw,Zlw-Bd,Zlw-Rsd","Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.","LPO 354 d.d. 10-01-19 Kader vastgesteld\nVoorlopig vastgesteld RGO Zd 2018-48. Akkoord indien meelift  met Zwaluwe-Roosendaal."]
["05, 06","K-006610","2055-00","-","R",2.1666666666666665,"Zaterdag","2020-02-01","01:00:00","Maandag","2020-02-03","05:00:00"," Ddr, Ddrs","Ddr-Bd,Ddr-Gdm,Ddr-Rsd,Ddr-Zlw","wissels:\n-1169\n-1173B\n-1155A\n-1115B","LPO 360: meelifter met K-006000 2001. kader vastgesteld met disclaimer: verdere de risico-inventarisatie moet inzicht geven op daadwerkelijke mogelijkheid tot uitvoeren in week 34&#x2F;35\nLPO 357 dd 21-02-2019: Kader vastgesteld"]
["05, 06","M-004701","2001-00","C-000278","R",2.1666666666666665,"Zaterdag","2020-02-01","01:00:00","Maandag","2020-02-03","05:00:00"," Mabr, Odb, Zlw, Zvb, Zvbi","Ddr-Rsd,Zlw-Rsd","Vervangen e-componenten Markbrug","WO&#x27;s verwijderen baanvak Bd-Rsd, en op empl. Rsd, empl Bd en empl. Zwaluwe, AM akkoord tijdens overleg NSR-Arriva-AM-CV dd 19 feb 2019 m.u.v. alle WO’s te Rsd (nog overleg AM en CV).\nLPO 354 d.d. 10-01-19 Kader vastgesteld\nVoorlopig vastgesteld in RGO Zd 2018-46."]
[9,"V-L00116","2001-00","-","R","04:20:00","Zaterdag","2020-02-29","01:00:00","Zaterdag","2020-02-29","05:20:00"," Abr, Arn, Bd, Bda, Bdpb, Bgn, Bgnphm, Bzl, Ddr, Ddzd, Esn, Etn, Gs, Gz, Gzve, Gzvea, Ha, Hzl, Kbd, Krag, Kraga, Krg, Lwd, Mabr, Mdb, Mdbz, Mdk, Nvbro, Odb, Otw, Rb, Rsd, Rsdg, Rsdphi, Sloe, Vlk, Vs, Vss, Wld, Zha, Zlw, Zvb, Zvbi","Bda-Hsbda,Bd-Rsd,Bd-Tb,Ddr-Bd,Ddr-Rsd,Ddr-Zlw,Esn-Rsd,Gs-Rsd,Gs-Sloe,Gs-Vs,Kraga-Krag,Lwd-Sloe,Rsd-Bd,Rsd-Esn,Rsd-Gs,Rtd-Bd,Sloe-Gs,Tb-Bd,Zlw-Bd,Zlw-Mdk,Zlw-Otw,Zlw-Rsd","uitwijkoefening VL-post ","Vastgesteld (LPO) in RGO Zuid 2019-20\nVoorlopig vastgesteld in RGO Zd 2018-46. Verzoek NSR om andere nachten dan vr&#x2F;za en za&#x2F;zo. Conform regulier proces mogen geen treinbewegingen in TVP plaatsvinden en dienen meelift werkzaamheden afgestemd te worden met betreffende LWB-er. DBC akkoord per mail."]
[9,"V-L00116","2002-00","-","R","04:20:00","Zondag","2020-03-01","01:00:00","Zondag","2020-03-01","05:20:00"," Abr, Arn, Bd, Bda, Bdpb, Bgn, Bgnphm, Bzl, Ddr, Ddzd, Esn, Etn, Gs, Gz, Gzve, Gzvea, Ha, Hzl, Kbd, Krag, Kraga, Krg, Lwd, Mabr, Mdb, Mdbz, Mdk, Nvbro, Odb, Otw, Rb, Rsd, Rsdg, Rsdphi, Sloe, Vlk, Vs, Vss, Wld, Zha, Zlw, Zvb, Zvbi","Bda-Hsbda,Bd-Rsd,Bd-Tb,Ddr-Bd,Ddr-Rsd,Ddr-Zlw,Esn-Rsd,Gs-Rsd,Gs-Sloe,Gs-Vs,Kraga-Krag,Lwd-Sloe,Rsd-Bd,Rsd-Esn,Rsd-Gs,Rtd-Bd,Sloe-Gs,Tb-Bd,Zlw-Bd,Zlw-Mdk,Zlw-Otw,Zlw-Rsd","uitwijkoefening VL-post ","Vastgesteld (LPO) in RGO Zuid 2019-20\nVoorlopig vastgesteld in RGO Zd 2018-46. Verzoek NSR om andere nachten dan vr&#x2F;za en za&#x2F;zo. Conform regulier proces mogen geen treinbewegingen in TVP plaatsvinden en dienen meelift werkzaamheden afgestemd te worden met betreffende LWB-er. DBC akkoord per mail."]
["10, 11","M-004701","2002-00","C-000279","R",2.1666666666666665,"Zaterdag","2020-03-07","01:00:00","Maandag","2020-03-09","05:00:00"," Mabr, Odb, Zlw, Zvb, Zvbi","Ddr-Rsd,Zlw-Rsd","Vervangen e-componenten Markbrug","WO&#x27;s verwijderen baanvak Bd-Rsd, en op empl. Rsd, empl Bd en empl. Zwaluwe, AM akkoord tijdens overleg NSR-Arriva-AM-CV dd 19 feb 2019 m.u.v. alle WO’s te Rsd (nog overleg AM en CV).\nLPO 354 d.d. 10-01-19 Kader vastgesteld\nVoorlopig vastgesteld in RGO Zd 2018-46."]
["10, 11","Z-906106","LZ01-02","C-000279","R",2.1666666666666665,"Zaterdag","2020-03-07","01:00:00","Maandag","2020-03-09","05:00:00"," Mdbz, Zlw","Ddr-Bd,Ddr-Rsd,Ddr-Zlw,Zlw-Bd,Zlw-Rsd","Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.","LPO 354 d.d. 10-01-19 Kader vastgesteld\nVoorlopig vastgesteld RGO Zd 2018-48. Akkoord indien meelift  met Zwaluwe-Roosendaal."]
[12,"K-006021","RTD6-00","-","R","09:00:00","Zondag","2020-03-22","00:00:00","Zondag","2020-03-22","09:00:00"," Dhsa, Rhsla, Rmoa, Rtb, Rtd, Rtst, Rtz, Wiltn, Wiltz, Wsba, Wspl","Gv-Rtd,Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Gv,Rtd-Kfhn,Rtd-Kfhz,Rtd-Rlb,Shl-Rtd","BBV RTD - Rijdraavernieuwing Draad 29 &amp; 96","omrijdroute van IO-B EM013+014+01; Edwin checkt met OSS\n"]
["13, 14","K-006608","2003-00","C-000339-1","R",2.125,"Zaterdag","2020-03-28","00:00:00","Maandag","2020-03-30","04:00:00"," Rtb, Rtd, Rtst, Rtz, Wiltn, Wiltz","Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb","Afronden vluchtpadverlichting HJ","LPO 354 d.d. 10-01-19 Kader vastgesteld\nVoorkeur in combinatie met HSL-zuid"]
["15, 16","K-006031","2003-00","-","R",2.1666666666666665,"Zaterdag","2020-04-11","01:00:00","Maandag","2020-04-13","05:00:00"," Ddr","Brdv-Ddr,Kfhn-Ddr,Rtd-Ddr","Ontvangst en boorput ivm gestuurde boring km 29.490, boring uitvoeren, drainage spoor 21 aanleggen en meer","LPO 358 d.d. 07-03-2019: Kader vastgesteld. "]
["15, 16","K-006610","2051-00","-","U",3.1666666666666665,"Zaterdag","2020-04-11","01:00:00","Dinsdag","2020-04-14","05:00:00"," Ddr, Ddzd, Mdbz, Wld","Ddr-Bd,Ddr-Rsd,Ddr-Zlw","wissels:\n-121A\n-121B\n-123A\n-123B\n-spoor 34,35,36","LPO 357 dd 21-02-2019: Kader vastgesteld."]
["15, 16","R-505000","EV02-00","-","R",2.1666666666666665,"Zaterdag","2020-04-11","01:00:00","Maandag","2020-04-13","05:00:00"," Ddr, Grbr, Kfhaz, Kfhz, Zwd","Brdv-Ddr,Ddr-Bd,Ddr-Gdm,Ddr-Rsd,Ddr-Zlw,Kfhn-Ddr,Rtd-Ddr","Saneren kruiswissel 1195A&#x2F;B-1197A&#x2F;B te Dordrecht\nSaneren wisseloverlopen 1335A&#x2F;B en 1347A&#x2F;B","LPO 359 d.d. 21-03-19 Kader vastgesteld"]
["15, 16","Z-906106","LZ04-01","-","R",2.1666666666666665,"Zaterdag","2020-04-11","01:00:00","Maandag","2020-04-13","05:00:00"," Mdbz, Zlw","Ddr-Bd,Ddr-Rsd,Ddr-Zlw,Zlw-Bd,Zlw-Mdk,Zlw-Otw,Zlw-Rsd","Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.","LPO 357 dd 21-02-2019: Kader vastgesteld. Actie af.\nLPO 356 dd 07-02-2019: Actie handhaven\nLPO 355: actie handhaven\nLPO 354: kader nog niet vaststellen. Lift mee met K-006610. Zodra K-006610 is vastgesteld, kan deze ook vastgesteld.\n\nVoorlopig vastgesteld RGO Zd 2018-48. Wordt gezocht naar combi met 2x 52 uur Dordrecht-Zwaluwe. Indien mogelijk 1x 76 uur, indien niet dan 2x 52 uur weekend."]
["18, 19","K-006608","2004-00","-","R",2.125,"Zaterdag","2020-05-02","00:00:00","Maandag","2020-05-04","03:00:00"," Rtb, Rtd, Rtst, Rtz, Wiltn, Wiltz","Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb","Afronden vluchtpadverlichting HJ","LPO 354 d.d. 10-01-19 Kader vastgesteld\nVoorkeur in combinatie met HSL-zuid"]
[21,"Z-187002","RTD8-00","-","R","03:20:00","Zondag","2020-05-24","01:00:00","Zondag","2020-05-24","04:20:00"," Az, Brd, Cps, Dhs, Dhsa, Dtz, Dtzo, Hfdm, Hlba, Hsbrdo, Hsghtn, Hsghtz, Hshfdo, Hshmdo, Hsrtdt, Hsrtdv, Hsvbw, IJsm, Kfhaz, Nwk, Nwki, Rhsla, Rlb, Rmoa, Rta, Rtb, Rtd, Rtn, Rtng, Rtngo, Rtngw, Rtst, Rtz, Sdm, Wiltn, Wiltz, Wsba, Wspl","Brdv-Rlb,Dhsa-Wspl,Gd-Rtd,Gv-Rtd,Kfhz-Rtd,Rlb-Ndkp,Rtd-Bd,Rtd-Ddr,Rtd-Gd,Rtd-Gv,Rtd-Kfhn,Rtd-Rlb,Rtngw-Rtngo,Rtst-Kfhan,Sdm-Vdgvch,Shl-Rtd","Onderhoud (jaarlijks) aan de EBS installatie door Siemens","vastgesteld (LPO) in RGO-RZ 1920"]
[21,"K-006610","2052-00","-","U",3.1666666666666665,"Donderdag","2020-05-21","01:00:00","Zondag","2020-05-24","05:00:00"," Ddr, Ddzd, Mdbz, Wld","Ddr-Bd,Ddr-Rsd,Ddr-Zlw","wissels:\n1113A\n1113B\n1111","LPO 360 d.d. 04-04-2019. Kader vastgesteld in week 21\nLPO 355 24-01-2019:Kader vastgesteld. "]
["22, 23","Z-906106","LZ04-02","-","R",2.1666666666666665,"Zaterdag","2020-05-30","01:00:00","Maandag","2020-06-01","05:00:00"," Mdbz, Zlw","Ddr-Bd,Ddr-Rsd,Ddr-Zlw,Zlw-Bd,Zlw-Mdk,Zlw-Otw,Zlw-Rsd","Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.","LPO 355 24-01-2019:Kader vastgesteld. \nLPO 354: meelifter met K-006610. Kader vaststellen zodra 6610 ook geprogrammeerd is in week 22.\n\nVoorlopig vastgesteld RGO Zd 2018-48. Wordt gezocht naar combi met 2x 52 uur Dordrecht-Zwaluwe. Indien mogelijk 1x 76 uur, indien niet dan 2x 52 uur weekend."]
["22, 23","R-485800","2001-00","-","R",2.1666666666666665,"Zaterdag","2020-05-30","01:00:00","Maandag","2020-06-01","05:00:00"," Mdk, Zlw","Zlw-Mdk","Aanpassen overwegen  Moerdijk A, B en C","LPO 356 dd 07-02-2019: Kader vastgesteld.\nVoorlopig vastgesteld in RGO Zd 2018-50. Is in opdracht van het havenbedrijf. Voorlopige vaststelling wordt doorgestuurd naar het havenbedrijf. Kan niet korter in duur vanwege bouw gehele overweg."]
["24, 25","K-006610","2058-00","-","R",2.1666666666666665,"Zaterdag","2020-06-13","01:00:00","Maandag","2020-06-15","05:00:00"," Ddr","Ddr-Bd,Ddr-Gdm,Ddr-Rsd,Ddr-Zlw","wissels:\n1163\n1155A\n1153A","LPO 359 d.d. 21-03-19 Kader vastgesteld"]
["25, 26, 27","R-474300","2001-00","C-000347-1","R",9,"Zaterdag","2020-06-20","00:00:00","Maandag","2020-06-29","00:00:00"," Az, Dhsa, Dtzo, Hlba, Hsrtdt, IJsm, Rhsla, Rlb, Rmoa, Rtb, Rtd, Rtn, Rtng, Rtngo, Rtngw, Rtst, Rtz, Sdm, Wiltn, Wiltz, Wsba, Wspl","Brdv-Rlb,Brdv-Rtd,Ddr-Rtd,Dhsa-Wspl,Gd-Rtd,Gv-Rtd,Kfhz-Rtd,Rlb-Ndkp,Rtd-Bd,Rtd-Ddr,Rtd-Gd,Rtd-Gv,Rtd-Kfhn,Rtd-Kfhz,Rtd-Rlb,Rtngw-Rtngo,Rtst-Kfhan,Sdm-Vdgvch,Shl-Rtd","Wijzigen en testen EBS i.v.m. goederen overdrachtspoor","LPO 359 d.d. 21-03-19 Kader vastgesteld\nLPO 358: kader conflicteert met omleidingsroute agv Gdm. Verzoek aan AM andere datum\nLPO 357: kader is een meelifter met R-3HRB01 2002 PHS Rijswijk Rotterdam.\nR-3HRB01-2002 conflicteert met R-550020-2001. Eerst conflict oplossen, pas daarna R-3HRB01-2002 en R474300 2001 vaststellen.\nActie: 1 AM onderzoekt mogelijkheden voor andere datum. Actie 2:hoeveel goederentreinen worden geraakt? Actie 3: biedt de route via Hvs voor goederen een alternatief? Actie 4: is het mogelijk voor goederen vanuit Beverwijk om een weekend niet te rijden? Actie 2 t&#x2F;m 4 CV.\nRGO 1906:\n- uiterlijk moet in week 12-2020 bekend zijn of deze IO uitgevoerd wordt, anders komt deze te vervallen.\n- Indien deze IO uitgevoerd wordt, komt IO R-464300 2002 (week 47) te vervallen"]
["34, 35","K-006610","2054-00","-","U",7,"Maandag","2020-08-17","05:00:00","Maandag","2020-08-24","05:00:00"," Ddr","Ddr-Bd,Ddr-Gdm,Ddr-Rsd,Ddr-Zlw","wissels:\n1159\n1171B &#x2F; 1177A\n1167 &#x2F; 1171A\n1155B\n1151&#x2F;1153A\n1153B\n1163\n1155A\n1173A","LPO 357 dd 21-02-2019: Kader vastgesteld."]
["34, 35, 36","K-006000","2001-00","C-000358-1-Leidend","U",9.1666666666666661,"Zaterdag","2020-08-22","01:00:00","Maandag","2020-08-31","05:00:00"," Az, Brd, Brda, Cps, Dhs, Dhsa, Dt, Dtz, Dtzo, Hlba, IJsm, IJsma, Mdo, Nwk, Nwki, Rhsla, Rlb, Rmoa, Rta, Rtb, Rtd, Rtn, Rtng, Rtngo, Rtngw, Rtst, Rtz, Sdm, Wiltn, Wiltz, Wsba, Wspl","Kfhz-Rtd,Rlb-Ndkp,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb,Rtst-Kfhan","Saneren van wissels 101A&#x2F;B, 123A&#x2F;B, 141A&#x2F;B, 143A&#x2F;B, 255, 253 A&#x2F;B, 163A&#x2F;B, 959A&#x2F;B, 983A&#x2F;B, 985A&#x2F;B + 975&#x2F;977, 901AB&#x2F;917AB","LPO 360: kader vastgesteld met disclaimer: verdere de risico-inventarisatie miet inzicht geven op daadwerkelijke mogelijkheid tot uitvoeren in week 34&#x2F;35\nLPO 359: kader nog niet vaststellen. programmering week 45 niet mogelijk ivm onmogelijkheden om te verbussen.\nVerzoek AM nieuwe datum.\nLPO 358: actie handhaven\nLPO 357: actie handhaven\nLPO 356 dd 07-02-2019: kader nog niet vaststellen. Nog geen zekerheid over programmering in week 45. Zie tevens actielijst LPO 356.\nVerkeersanalyse als de combinaties met andere IO’s bekend zijn"]
[35,"K-006357","2017-00","C-000358-1","R","22:00:00","Donderdag","2020-08-27","02:00:00","Vrijdag","2020-08-28","00:00:00"," Brd, Kfhaz, Rlb, Rtb, Rtd, Rtst, Rtz, Wiltn, Wiltz","Brdv-Rtd,Ddr-Rtd,Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb,Rtst-Kfhan","Balken verhogen spoor KJ en LJ.\nMonteren 1 overspanningsafleider km 43","LPO 360: kader vastgesteld met disclaimer: verdere de risico-inventarisatie miet inzicht geven op daadwerkelijke mogelijkheid tot uitvoeren in week 34&#x2F;35\nLPO 360: kader verplaatst hoogstwaarschijnlijk mee met kader IJsselmonde K-0060000 2001. Met Am afgesproken kader op aanpassen IO totdat er duidelijkheid is\nLPO 359: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001\nLPO 358: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001\nrandvoorwaarde: niet in combinatie met HSL-zuid"]
[35,"K-006357","2018-00","C-000358-1","R","22:00:00","Vrijdag","2020-08-28","00:00:00","Vrijdag","2020-08-28","22:00:00"," Brd, IJsm, Kfhaz, Rlb, Rtst","Ddr-Rtd,Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb,Rtst-Kfhan","Ophogen balken sporen BG, HJ en JJ onder kunstwerken.\n","LPO 360: kader vastgesteld met disclaimer: verdere de risico-inventarisatie miet inzicht geven op daadwerkelijke mogelijkheid tot uitvoeren in week 34&#x2F;35\nLPO 360: kader verplaatst hoogstwaarschijnlijk mee met kader IJsselmonde K-0060000 2001. Met Am afgesproken kader op aanpassen IO totdat er duidelijkheid is\nLPO 359: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001\nLPO 358: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001"]
["36, 37","K-006608","2002-00","-","R",2.125,"Zaterdag","2020-09-05","00:00:00","Maandag","2020-09-07","03:00:00"," Rtb, Rtd, Rtst, Rtz, Wiltn, Wiltz","Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb","Afronden vluchtpadverlichting KL","LPO 355 24-01-2019:Kader vastgesteld. \nVoorkeur in combinatie met HSL-zuid"]
["38, 39","Z-180000","2002-00","C-000283-1","R",1.3333333333333333,"Zaterdag","2020-09-19","21:00:00","Maandag","2020-09-21","05:00:00"," Bgn, Bgnphm, Bzl, Gs, Kbd, Kraga, Krg, Rb, Rsd, Vlk","Esn-Rsd,Gs-Rsd,Gs-Sloe,Gs-Vs,Kraga-Krag,Rsd-Bd,Rsd-Esn,Rsd-Gs,Sloe-Gs","Dateq vervangen voor DOSS","LPO 355 dd 24-01-2019: Kader vastgesteld. \nVoorlopig vastgesteld RGO Zd 2018-42. DB-C: graag za&#x2F;zo - zo&#x2F;ma\nFOT is aangepast vanwege niet bereden sporen.\n"]
[40,"K-006357","2013-00","-","R","10:00:00","Zondag","2020-10-04","01:20:00","Zondag","2020-10-04","11:20:00"," Grbr, Kfhaz, Zwd","Brdv-Ddr,Kfhn-Ddr,Rtd-Ddr","Geo 116 01-02 1 balk en 2 palen ophalen\nGeo 116 01 plaatsen overspanningsbeveiligingen","LPO 357 dd 21-02-2019: Kader vastgesteld. \nniet in combinatie met HSL-zuid"]
["40, 41","K-006357","2014-00","-","R",2.1666666666666665,"Zaterdag","2020-10-03","00:00:00","Maandag","2020-10-05","04:00:00"," Brd, Kfhaz, Rlb, Rtst","Rtd-Ddr","Wijzigingen draagconstructie Munnikensteeg\nPlaatsen van 4 overspanningsbeveiligingen","LPO 355 dd 24-01-2019: Kader vastgesteld. \nrandvoorwaarde: niet in combinatie met HSL-zuid"]
["42, 43","K-006608","2001-00","-","R",2.125,"Zaterdag","2020-10-17","00:00:00","Maandag","2020-10-19","03:00:00"," Rtb, Rtd, Rtst, Rtz, Wiltn, Wiltz","Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb","Afronden vluchtpadverlichting KL","LPO 356 dd 07-02-2019: Kader vastgesteld.\nLPO 354: conflict met Gdm (ivm omleidingsroute). Verzoek aan AM nieuwe datum.\nVoorkeur in combinatie met HSL-zuid"]
["43, 44","K-006610","2056-00","-","R",2.1666666666666665,"Zaterdag","2020-10-24","01:00:00","Maandag","2020-10-26","04:00:00"," Ddr","Ddr-Bd,Ddr-Gdm,Ddr-Rsd,Ddr-Zlw","wissels:\n-1145A\n-1145B\n-1165","LPO 359 d.d. 21-03-19 Kader vastgesteld. "]
[46,"K-006357","2019-00","C-000360-1","R","22:00:00","Zaterdag","2020-11-14","00:00:00","Zaterdag","2020-11-14","22:00:00"," Brd, IJsm, Kfhaz, Rlb, Rtst","Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb,Rtst-Kfhan","Ophogen balken sporen BG, HJ en JJ onder kunstwerken.\n","LPO 360 d.d. 04-04-2019: Kader vastgesteld in week 46\nLPO 359: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001\nLPO 358: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001"]
[46,"K-006357","2020-00","C-000360-1","R","22:00:00","Zondag","2020-11-15","00:00:00","Zondag","2020-11-15","22:00:00"," Brd, Kfhaz, Rlb, Rtb, Rtd, Rtst, Rtz, Wiltn, Wiltz","Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb,Rtst-Kfhan","Balken verhogen spoor KJ en LJ.\nMonteren 1 overspanningsafleider km 43","LPO 360 d.d. 04-04-2019: Kader vastgesteld in week 46\nLPO 359: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001\nLPO 358: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001\nrandvoorwaarde: niet in combinatie met HSL-zuid\n"]
["46, 47","Z-180001","1901-00","C-000360-1-Leidend","R",2.125,"Zaterdag","2020-11-14","00:00:00","Maandag","2020-11-16","03:00:00"," Rtb, Rtd, Rtst, Rtz, Wiltn, Wiltz","Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb","aanpassing besturings systeem Willemsspoortunnel","LPO 360 d.d. 04-04-2019: Kader vastgesteld in week 46\nLPO 359: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001\nLPO 358: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001\nLPO 357: kader vaststellen zodra K-006000 2001 (IJsselmonde) is geprogrammeerd (in afwachting van programmering IJsselmonde)\n\nlift mee met kader IJsm (K-006000)"]
["46, 47","K-006608","2005-00","C-000360-1","R",2.125,"Zaterdag","2020-11-14","00:00:00","Maandag","2020-11-16","03:00:00"," Rtb, Rtd, Rtst, Rtz, Wiltn, Wiltz","Kfhz-Rtd,Rtd-Bd,Rtd-Ddr,Rtd-Kfhz,Rtd-Rlb","Afronden vluchtpadverlichting HJ","LPO 360 d.d. 04-04-2019: Kader vastgesteld in week 46\nLPO 359: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001\nLPO 358: kader nog niet vaststellen totdat er duidelijkheid is omtrent programmering IJsselmonde K-006000 2001\nLPO 357: kader vaststellen zodra K-006000 2001 (IJsselmonde) is geprogrammeerd (in afwachting van programmering IJsselmonde)\nVoorkeur in combinatie met HSL-zuid"]
["47, 48, 49","R-474300","2002-00","C-000357-1","R",9,"Zaterdag","2020-11-21","00:00:00","Maandag","2020-11-30","00:00:00"," Az, Dhsa, Dtzo, Hlba, Hsrtdt, IJsm, Rhsla, Rlb, Rmoa, Rtb, Rtd, Rtn, Rtng, Rtngo, Rtngw, Rtst, Rtz, Sdm, Wiltn, Wiltz, Wsba, Wspl","Brdv-Rlb,Brdv-Rtd,Ddr-Rtd,Dhsa-Wspl,Gd-Rtd,Gv-Rtd,Kfhz-Rtd,Rlb-Ndkp,Rtd-Bd,Rtd-Ddr,Rtd-Gd,Rtd-Gv,Rtd-Kfhn,Rtd-Kfhz,Rtd-Rlb,Rtngw-Rtngo,Rtst-Kfhan,Sdm-Vdgvch,Shl-Rtd","Wijzigen en testen EBS i.v.m. goederen overdrachtspoor","LPO 358 d.d. 07-03-2019: Kader vastgesteld. \nRGO 1906:\n- deze IO vervalt indien R-74300 2001 in week 29-2020 uitgevoerd wordt.\n- uiterlijk moet in week 30-2020 bekend zijn of deze IO uitgevoerd wordt, anders komt deze te vervallen."]
[]
[2021]
["Rtd-Zwd-Rsd grens"]
["Projectnummer","Projectomschrijving","Locatie","TVP - R (12-52 uur)","TVP - U (>52 uur)"]
["K-006000","Zwijndrecht-Ijsselmonde, Uitvoeringsscope inclusief FIS","Rtd-Brd","5*","1* tussen 4-9 dgn",null,"50% treinverkeer mogelijk"]
["K-006613","TTI, Barendrecht vervangen Scada","Rtd-Brd","1*",null,"Risico planning 2020 afhankelijk van pilot moederspec wspt","Maatgevend"]
["M-004551","BBV regio Zuid 2021","Zlw-Rsd",null,"1*16 dagen of 2*9 dagen","In 2022 ook nog 1*9 dagen nodig (facultatief),","Maatgevend"]
["M-004763","Vervangen GP portalen ZD 2021","Zlw-Rsd",null,"1*9 dagen","Alternatief: 6*52 uur Meeliften met BBV en rest in lange nachten? Voorwaarde: BBV logistiek via Zlw vooralsnog gewoon opnemen","Meeliften met BBV"]
["M-004551","BBV Regio Zuid 2021","Rsd-Rsdg","1*",null,null,"Meeliften met BBV Rsd-Vs"]

{"sheet":"Infrabel","index":3,"n_rows":245,"n_cols":31,"rows_kept":245,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
["map:",null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[]
["Infrabel",10037,"Lille - Charleroi","<>","Braine-le-Comte","Ecaussines",{"$f":"YEAR(K4)","v":2020},{"$f":"YEAR(M4)","v":2020},32,35,"2020-08-07","23:00:00","2020-08-24","05:00:00","15d","All day","Viaduc Renewal","T",null,null,null,null,null,"R",null,null,null,"Re-routing"]
["Infrabel",12506,"Lille - Antwerpen","<>","Y.Melsele","Antwerpen",{"$f":"YEAR(K5)","v":2020},{"$f":"YEAR(M5)","v":2020},37,38,"2020-09-12","00:15:00",{"$f":"K5+1","v":"2020-09-13"},"04:10:00","2d","All day","Massification Works","T",null,null,null,null,null,"R",null,null,null,"Re-routing via Line 10"]
["Infrabel",12507,"Lille - Antwerpen","<>","Y.Melsele","Antwerpen",2020,2020,38,39,"2020-09-19","00:15:00","2020-09-20","04:10:00","2d","All day","Massification Works","T",null,null,null,null,null,"R",null,null,null,"Re-routing via Line 10"]
["Infrabel",12508,"Lille - Antwerpen","<>","Y.Melsele","Antwerpen",2020,2020,39,40,"2020-09-26","00:15:00","2020-09-27","04:10:00","2d","All day","Massification Works","T",null,null,null,null,null,"R",null,null,null,"Re-routing via Line 10"]
["Infrabel",12509,"Lille - Antwerpen","<>","Y.Melsele","Antwerpen",2020,2020,40,41,"2020-10-03","00:15:00","2020-10-04","04:10:00","2d","All day","Massification Works","T",null,null,null,null,null,"R",null,null,null,"Re-routing via Line 10"]
["Infrabel",12510,"Lille - Antwerpen","<>","Y.Melsele","Antwerpen",2020,2020,41,42,"2020-10-10","00:15:00","2020-10-11","04:10:00","2d","All day","Massification Works","T",null,null,null,null,null,"R",null,null,null,"Re-routing via Line 10"]
["Infrabel",12512,"Lille - Antwerpen","<>","Y.Melsele","Antwerpen",2020,2020,43,44,"2020-10-24","00:15:00","2020-10-25","04:10:00","2d","All day","Massification Works","T",null,null,null,null,null,"R",null,null,null,"Re-routing via Line 10"]
["Infrabel",12514,"Lille - Antwerpen","<>","Y.Melsele","Antwerpen",2020,2020,44,45,"2020-10-31","00:15:00","2020-11-01","04:10:00","2d","All day","Massification Works","T",null,null,null,null,null,"R",null,null,null,"Re-routing via Line 10"]
["Infrabel",12521,"Lille - Antwerpen","<>","Y.Melsele","Antwerpen",2020,2020,45,46,"2020-11-07","00:15:00","2020-11-08","04:10:00","2d","All day","Massification Works","T",null,null,null,null,null,"R",null,null,null,"Re-routing via Line 10"]
["Infrabel",12522,"Lille - Antwerpen","<>","Y.Melsele","Antwerpen",2020,2020,46,47,"2020-11-14","00:15:00","2020-11-15","04:10:00","2d","All day","Massification Works","T",null,null,null,null,null,"R",null,null,null,"Re-routing via Line 10"]
[null,21795,"Lille - Charleroi","<>","ECAUSSINNES","Y.FELUY",2020,2020,40,41,"2020-09-27","23:30:00","2020-10-04","04:30:00","7d","Nights","Viaduc Renewal","T",null,null,null,null,null,"R",null,null,null,"Re-routing"]
["Infrabel",10378,"Lille - Charleroi","<>","Neufvilles","Jurbise",2020,2020,40,41,"2020-10-03","00:40:00","2020-10-05","04:30:00","2d","All day","Road crossing renewal","T",null,null,null,null,null,"R",null,null,null,"Re-routing"]
["Infrabel",10379,"Lille - Charleroi","<>","Neufvilles","Jurbise",2020,2020,42,43,"2020-10-17","00:40:00","2020-10-19","04:30:00","2d","All day","Road crossing renewal","T",null,null,null,null,null,"R",null,null,null,"Re-routing"]
["Infrabel",15709,"Lille - Charleroi","<>","BRAINE-LE-COMTE","SOIGNIES",2020,2020,13,15,"2020-03-24","00:30:00","2020-04-10","04:30:00","17d","Nights","Renouvellement traverses P93 - préparations et finitions (pistes)","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",15713,"Lille - Charleroi","<>","BRAINE-LE-COMTE","SOIGNIES",2020,2020,13,14,"2020-03-28","00:30:00","2020-03-30","04:30:00","2d","All day","Renouvellement traverses P93","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",21860,"Lille - Antwerpen","<>","DEINZE","KORTRIJK",2020,2020,3,3,"2020-01-13","00:15:00","2020-01-17","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21517,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,3,3,"2020-01-13","23:00:00","2020-01-16","05:40:00","5d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"omleidingen via alternatieve reiswegen"]
["Infrabel",21447,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,3,4,"2020-01-18","00:00:00","2020-01-19","06:00:00","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21861,"Lille - Antwerpen","<>","DEINZE","KORTRIJK",2020,2020,4,4,"2020-01-20","00:15:00","2020-01-24","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21677,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,4,4,"2020-01-20","23:00:00","2020-01-23","05:00:00","5d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"omleidingen via alternatieve reiswegen"]
["Infrabel",13192,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,4,5,"2020-01-25"," ","2020-01-26"," ","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via Quévy/L96/28-1/28/50/26A/27"]
["Infrabel",21862,"Lille - Antwerpen","<>","DEINZE","KORTRIJK",2020,2020,5,5,"2020-01-27","00:15:00","2020-01-31","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21678,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,5,5,"2020-01-27","23:00:00","2020-01-30","05:00:00","5d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"omleidingen via alternatieve reiswegen"]
["Infrabel",21683,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,5,5,"2020-01-27","23:10:00","2020-01-31","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",13193,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,5,6,"2020-02-01"," ","2020-02-02"," ","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via Quévy/L96/28-1/28/50/26A/27"]
["Infrabel",21863,"Lille - Antwerpen","<>","DEINZE","KORTRIJK",2020,2020,6,6,"2020-02-03","00:15:00","2020-02-07","04:10:00","4d","Night","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21679,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,6,6,"2020-02-03","23:00:00","2020-02-06","05:00:00","5d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"omleidingen via alternatieve reiswegen"]
["Infrabel",21684,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,6,6,"2020-02-03","23:10:00","2020-02-07","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",13190,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,6,7,"2020-02-08"," ","2020-02-09"," ","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via Quévy/L96/28-1/28/50/26A/27"]
["Infrabel",21876,"Lille - Antwerpen","<>","GENT-SINT-PIETERS","KORTRIJK",2020,2020,7,7,"2020-02-10","00:15:00","2020-02-14","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21685,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,7,7,"2020-02-10","23:10:00","2020-02-14","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",13191,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,7,8,"2020-02-15"," ","2020-02-16"," ","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via Quévy/L96/28-1/28/50/26A/27"]
["Infrabel",21867,"Lille - Antwerpen","<>","DEINZE","Y.ZANDBERG",2020,2020,8,8,"2020-02-17","00:15:00","2020-02-21","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21686,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,8,8,"2020-02-17","23:10:00","2020-02-21","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",21868,"Lille - Antwerpen","<>","DEINZE","Y.ZANDBERG",2020,2020,9,9,"2020-02-24","00:15:00","2020-02-28","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21687,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,9,9,"2020-02-24","23:10:00","2020-02-27","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",16641,"Lille - Antwerpen","<>","KORTRIJK","Y.ZANDBERG",2020,2020,9,10,"2020-02-29"," ","2020-03-01"," ","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM tussen Kortrijk en Gent om te leiden via L66 - Brugge - stuurpostwissel - L50A.\nOF via L96"]
["Infrabel",21882,"Lille - Antwerpen","<>","GENT-SINT-PIETERS","Y.ZANDBERG",2020,2020,10,10,"2020-03-02","00:15:00","2020-03-06","04:10:00","5d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21688,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,10,10,"2020-03-02","23:10:00","2020-03-05","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",16642,"Lille - Antwerpen","<>","KORTRIJK","Y.ZANDBERG",2020,2020,10,11,"2020-03-07"," ","2020-03-08"," ","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM tussen Kortrijk en Gent om te leiden via L66 - Brugge - stuurpostwissel - L50A.\nOF via L96"]
["Infrabel",21869,"Lille - Antwerpen","<>","DEINZE","Y.ZANDBERG",2020,2020,11,11,"2020-03-09","00:15:00","2020-03-13","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21689,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,11,11,"2020-03-09","23:10:00","2020-03-12","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",16643,"Lille - Antwerpen","<>","KORTRIJK","Y.ZANDBERG",2020,2020,11,12,"2020-03-14"," ","2020-03-15"," ","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM tussen Kortrijk en Gent om te leiden via L66 - Brugge - stuurpostwissel - L50A.\nOF via L96"]
["Infrabel",21690,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,12,12,"2020-03-16","23:10:00","2020-03-20","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",21691,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,14,14,"2020-03-30","23:10:00","2020-04-03","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",16613,"Lille - Antwerpen","<>","KORTRIJK","Y.ZANDBERG",2020,2020,14,15,"2020-04-04"," ","2020-04-05"," ","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM tussen Kortrijk en Gent om te leiden via L66 - Brugge - stuurpostwissel - L50A.\nOF via L96"]
["Infrabel",21692,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,15,15,"2020-04-06","23:10:00","2020-04-09","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",16644,"Lille - Antwerpen","<>","KORTRIJK","Y.ZANDBERG",2020,2020,15,16,"2020-04-11"," ","2020-04-12"," ","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM tussen Kortrijk en Gent om te leiden via L66 - Brugge - stuurpostwissel - L50A.\nOF via L96"]
["Infrabel",21870,"Lille - Antwerpen","<>","DEINZE","Y.ZANDBERG",2020,2020,16,16,"2020-04-13","00:15:00","2020-04-17","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21693,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,16,16,"2020-04-13","23:10:00","2020-04-16","04:10:00","4d","Night","Preparation track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",16645,"Lille - Antwerpen","<>","KORTRIJK","Y.ZANDBERG",2020,2020,16,17,"2020-04-18"," ","2020-04-19"," ","2d","All day","Track Renewal","T",null,null,null,null,null,"R",null,null,null,"HKM tussen Kortrijk en Gent om te leiden via L66 - Brugge - stuurpostwissel - L50A."]
["Infrabel",21871,"Lille - Antwerpen","<>","DEINZE","Y.ZANDBERG",2020,2020,17,17,"2020-04-20","00:15:00","2020-04-24","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21694,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,17,17,"2020-04-20","23:10:00","2020-04-24","04:10:00","4d","Night","Finishes track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",21872,"Lille - Antwerpen","<>","DEINZE","Y.ZANDBERG",2020,2020,18,18,"2020-04-27","00:15:00","2020-05-01","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21695,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,18,18,"2020-04-27","23:10:00","2020-05-01","04:10:00","4d","Night","Finishes track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",21680,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,19,19,"2020-05-04","23:00:00","2020-05-08","05:00:00","5d","Night","Finishes track renewal","T",null,null,null,null,null,"R",null,null,null,"omleidingen via alternatieve reiswegen"]
["Infrabel",21696,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,19,19,"2020-05-04","23:10:00","2020-05-08","04:10:00","4d","Night","Finishes track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",21873,"Lille - Antwerpen","<>","DEINZE","Y.ZANDBERG",2020,2020,20,20,"2020-05-11","00:15:00","2020-05-15","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21697,"Lille - Antwerpen","<>","Y.ZANDBERG","KORTRIJK",2020,2020,20,20,"2020-05-11","23:10:00","2020-05-15","04:10:00","4d","Night","Finishes track renewal","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via L66-FR-rondzetten HL-L50A\nOF via L96"]
["Infrabel",21874,"Lille - Antwerpen","<>","DEINZE","Y.ZANDBERG",2020,2020,25,25,"2020-06-15","00:15:00","2020-06-19","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21877,"Lille - Antwerpen","<>","GENT-SINT-PIETERS","KORTRIJK",2020,2020,28,28,"2020-07-06","00:15:00","2020-07-10","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21878,"Lille - Antwerpen","<>","GENT-SINT-PIETERS","KORTRIJK",2020,2020,30,30,"2020-07-20","00:15:00","2020-07-24","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21864,"Lille - Antwerpen","<>","DEINZE","KORTRIJK",2020,2020,31,31,"2020-07-27","00:15:00","2020-07-31","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21879,"Lille - Antwerpen","<>","GENT-SINT-PIETERS","KORTRIJK",2020,2020,32,32,"2020-08-03","00:15:00","2020-08-07","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21880,"Lille - Antwerpen","<>","GENT-SINT-PIETERS","KORTRIJK",2020,2020,33,33,"2020-08-10","00:15:00","2020-08-14","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21681,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,33,33,"2020-08-10","23:00:00","2020-08-14","05:00:00","5d","All day","Finishes track renewal","T",null,null,null,null,null,"R",null,null,null,"omleidingen via alternatieve reiswegen"]
["Infrabel",21881,"Lille - Antwerpen","<>","GENT-SINT-PIETERS","KORTRIJK",2020,2020,34,34,"2020-08-17","00:15:00","2020-08-21","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21682,"Lille - Antwerpen","<>","KORTRIJK","MOUSCRON",2020,2020,34,34,"2020-08-17","23:00:00","2020-08-21","05:00:00","5d","All day","Finishes track renewal","T",null,null,null,null,null,"R",null,null,null,"omleidingen via alternatieve reiswegen"]
["Infrabel",21865,"Lille - Antwerpen","<>","DEINZE","KORTRIJK",2020,2020,35,35,"2020-08-24","00:15:00","2020-08-28","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",21866,"Lille - Antwerpen","<>","DEINZE","KORTRIJK",2020,2020,49,49,"2020-11-30","00:15:00","2020-12-04","04:10:00","4d","Night","Massification Works","T",null,null,null,null,null,"R",null,null,null,"HKM om te leiden via alternatieve reiswegen"]
["Infrabel",19508,"Athus - Meuse",">","DINANT","DINANT",2019,2020,49,9,"2019-12-02","05:00:00","2020-02-28","16:00:00","88d","All day","Gare de Dinant - Phase 1.5 - Renouvellement quai I",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",16551,"Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2020,2020,10,27,"2020-03-02"," ","2020-06-29"," ","119d","All day","PI BK 8500 - 7450 + pistes + parois rocheuses + tx divers",null,"ST",null,null,null,null,null,null,null,null,"adaptations service des trains"]
["Infrabel",21800,"Athus - Meuse","<>","VIRTON","HALANZY",2020,2020,10,11,"2020-03-07","23:00:00","2020-03-09","05:00:00","2d","All day","Traitement zone boueuse (bk126100): assainissement et drainage","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",21804,"Athus - Meuse",">","VIRTON","HALANZY",2020,2020,10,13,"2020-03-07","23:00:00","2020-03-22","15:00:00","15d","All day","Traitement zone boueuse (bk 103290) : assainissement et abaissement de piste",null,"ST",null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",19637,"Athus - Meuse","<>","ANSEREMME","GENDRON-CELLES",2020,2020,11,12,"2020-03-14","08:00:00","2020-03-15","15:00:00","1d","All day","PI BK 8500 - 7450 + pistes + parois rocheuses + tx divers","T",null,null,null,null,null,null,null,null,null,"adaptations service des trains"]
["Infrabel",21801,"Athus - Meuse","<>","VIRTON","HALANZY",2020,2020,11,12,"2020-03-14","10:00:00","2020-03-16","05:00:00","2d","All day","Traitement zone boueuse (bk126100): assainissement et drainage","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",21802,"Athus - Meuse","<>","VIRTON","HALANZY",2020,2020,12,13,"2020-03-21","23:00:00","2020-03-22","15:00:00","1d","All day","Traitement zone boueuse (bk126100): assainissement et drainage","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",21803,"Athus - Meuse","<>","VIRTON","HALANZY",2020,2020,13,14,"2020-03-28","23:00:00","2020-03-29","15:00:00","1d","All day","Traitement zone boueuse (bk126100): assainissement et drainage","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",21805,"Athus - Meuse","<>","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2020,2020,14,15,"2020-04-04","23:00:00","2020-04-05","16:00:00","1d","All day","Traitement zone boueuse (bk 103290) : assainissement et abaissement de piste","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",21799,"Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2020,2020,14,16,"2020-04-04","23:00:00","2020-04-14","05:00:00","10d","All day","Traitement zone boueuse (bk 103290) : assainissement et abaissement de piste",null,"ST",null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",21806,"Athus - Meuse","<>","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2020,2020,15,16,"2020-04-11","23:00:00","2020-04-12","16:00:00","1d","All day","Traitement zone boueuse (bk 103290) : assainissement et abaissement de piste","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",21807,"Athus - Meuse","<>","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2020,2020,16,17,"2020-04-18","23:00:00","2020-04-19","16:00:00","1d","All day","Traitement zone boueuse (bk 103290) : assainissement et abaissement de piste","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",19638,"Athus - Meuse","<>","ANSEREMME","GENDRON-CELLES",2020,2020,18,19,"2020-05-02","08:00:00","2020-05-03","15:00:00","1d","All day","PI BK 8500 - 7450 + pistes + parois rocheuses + tx divers","T",null,null,null,null,null,null,null,null,null,"adaptations service des trains"]
["Infrabel",21808,"Athus - Meuse","<>","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2020,2020,18,19,"2020-05-02","10:00:00","2020-05-04","05:00:00","2d","All day","Traitement zone boueuse (BK : 95.140) assainissement & abaissement de la piste","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",21809,"Athus - Meuse","<>","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2020,2020,19,20,"2020-05-09","23:00:00","2020-05-11","05:00:00","2d","All day","Traitement zone boueuse (BK : 95.140) assainissement & abaissement de la piste","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",21810,"Athus - Meuse","<>","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2020,2020,20,21,"2020-05-16","23:00:00","2020-05-17","15:00:00","1d","All day","Traitement zone boueuse (BK : 95.140) assainissement & abaissement de la piste","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",21811,"Athus - Meuse","<>","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2020,2020,20,21,"2020-05-16","23:00:00","2020-05-18","05:00:00","2d","All day","Traitement zone boueuse (BK : 95.140) assainissement & abaissement de la piste","T",null,null,null,null,null,null,null,null,null,"A déterminer"]
["Infrabel",16116,"Athus - Meuse","<>","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2020,2021,32,10,"2020-08-08"," ","2021-02-28"," ","204d","All day","Terminal Athus - Phase 5.3 : Mise en service nouveau tracé L165/1","T",null,null,null,null,null,null,null,null,null,"proposition détournement via SNCF (L165/2) ou tête à queue à Athus"]
["Infrabel",16565,"Athus - Meuse",">","LUSTIN","YVOIR",2020,2020,36,41,"2020-09-05","06:00:00","2020-10-05","04:00:00","30d","All day","Renouvellement quais Yvoir + CSV : Phase 1/3",null,"ST",null,null,null,null,null,null,null,null,"HKM à adapter"]
["Infrabel",13615,"Athus - Meuse",">","BEAURAING","HOUYET",2020,2020,40,50,"2020-09-28"," ","2020-12-11"," ","74d","All day","Assainissement Beauraing - Houyet - Vonêche",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",19618,"Athus - Meuse",">","LUSTIN","YVOIR",2020,2020,46,50,"2020-11-09","05:00:00","2020-12-07","04:00:00","28d","All day","Renouvellement quais Yvoir + CSV : Phase 3/3",null,"ST",null,null,null,null,null,null,null,null,"HKM à adapter"]
["Infrabel",14741,"Erquelinnes - Montzen",">","MOUSTIER-GARAGE","MOUSTIER-GARAGE",2020,2020,4,9,"2020-01-20"," ","2020-02-23"," ","34d","All day","Aménagement Moustier - Phase 5",null,"ST",null,null,null,null,null,null,null,null,"Adaptations par BNX"]
["Infrabel",16684,"Erquelinnes - Montzen",">","BASSENGE","VISE-HAUT",2020,2020,8,20,"2020-02-16"," ","2020-05-16"," ","90d","All day","Mise sur ballast du pont sur canal + peinture",null,"ST",null,null,null,null,null,null,null,null,"pas de croisement entre Bassenge-visé (service saisonnier)"]
["Infrabel",18961,"Erquelinnes - Montzen","<>","Y.GLONS","VISE-HAUT",2020,2020,11,12,"2020-03-14"," ","2020-03-15"," ","2d","All day","Mise en service bloc automatique","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",17966,"Erquelinnes - Montzen","<>","TAMINES","AISEAU",2020,2020,13,27,"2020-03-27","23:40:00","2020-06-29","04:40:00",null,"nights","Peinture Pont BK 83413\nCTL les nuits de WE ven/sam sam/dim dim/lun","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",16655,"Erquelinnes - Montzen","<>","ANDENNE","MARCHE-LES-DAMES-MARCHANDISES",2020,2020,16,17,"2020-04-17","23:45:00","2020-04-20","04:30:00","2d","All day","PN 83-84 + AS Château de Seilles (raccordement Carmeuse)","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20077,"Erquelinnes - Montzen","<>","ANDENNE","MARCHE-LES-DAMES-MARCHANDISES",2020,2020,17,18,"2020-04-24","23:45:00","2020-04-27","04:30:00","2d","All day","PN 83-84 + AS Château de Seilles (raccordement Carmeuse)","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",18963,"Erquelinnes - Montzen",">","VISE-HAUT","MONTZEN-GRIL M",2020,2020,20,21,"2020-05-16","06:00:00","2020-05-17","18:00:00","2d","All day","Mise en service bloc automatique",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20078,"Erquelinnes - Montzen",">","AMAY","HUY",2020,2020,21,25,"2020-05-18","22:00:00","2020-06-20","06:00:00",null,"Nights","Renouvellement Appareils\nSAVU les nuits",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",18967,"Erquelinnes - Montzen",">","VISE-HAUT","MONTZEN-GRIL M",2020,2020,21,21,"2020-05-18","08:00:00","2020-05-22","17:00:00","5d","All day","Mise en service bloc automatique",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",16651,"Erquelinnes - Montzen","<>","FLEMALLE-HAUTE","STATTE",2020,2020,21,22,"2020-05-21","00:40:00","2020-05-25","04:30:00","3d","All day","Renouvellement AS 1A, 1B, 2A, 2B, 4A","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",18964,"Erquelinnes - Montzen","<>","VISE-HAUT","MONTZEN-GRIL M",2020,2020,21,22,"2020-05-23","06:30:00","2020-05-24","06:30:00","2d","All day","Mise en service bloc automatique","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",18968,"Erquelinnes - Montzen",">","VISE-HAUT","MONTZEN-GRIL M",2020,2020,22,22,"2020-05-25","08:00:00","2020-05-29","17:00:00","5d","All day","Mise en service bloc automatique",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",16652,"Erquelinnes - Montzen","<>","FLEMALLE-HAUTE","STATTE",2020,2020,22,23,"2020-05-30","00:40:00","2020-06-01","04:30:00","2d","All day","Renouvellement AS 1A, 1B, 2A, 2B, 4A","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",18965,"Erquelinnes - Montzen","<>","VISE-HAUT","MONTZEN-GRIL M",2020,2020,23,23,"2020-05-31","06:30:00","2020-05-31","15:00:00","0d","All day","Mise en service bloc automatique","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",19652,"Erquelinnes - Montzen",">","BASSENGE","VISE-HAUT",2020,2020,23,36,"2020-06-01"," ","2020-08-30"," ","90d","All day","Mise sur ballast du pont sur canal + peinture",null,"ST",null,null,null,null,null,null,null,null,"pas de croisement entre Bassenge-visé (service saisonnier)"]
["Infrabel",16653,"Erquelinnes - Montzen","<>","FLEMALLE-HAUTE","STATTE",2020,2020,23,24,"2020-06-06","00:40:00","2020-06-08","04:40:00","2d","All day","Renouvellement AS 1A, 1B, 2A, 2B, 4A","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",16654,"Erquelinnes - Montzen","<>","FLEMALLE-HAUTE","STATTE",2020,2020,24,25,"2020-06-13","00:40:00","2020-06-15","04:30:00","2d","All day","Renouvellement AS 1A, 1B, 2A, 2B, 4A","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20011,"Erquelinnes - Montzen",">","Y.FLAWINNE","FRANIERE",2020,2020,32,37,"2020-08-07","23:30:00","2020-09-07","05:00:00","31d","All day","Franière 2020\nPhase 1.1\nVoie B HS en continu",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20017,"Erquelinnes - Montzen","<>","Y.FLAWINNE","MOUSTIER-GARAGE",2020,2020,35,36,"2020-08-28","23:30:00","2020-08-31","05:00:00","3d","All day","Franière 2020\nPhase 1.2\nWE de CTL en continu","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20683,"Erquelinnes - Montzen","<>","HOURPES","LOBBES",2020,2020,36,36,"2020-08-31","22:00:00","2020-09-05","04:25:00","5d","Night","Renouvellement des ponts  10 + 11: Nuits préparatoires\nCTL de nuit","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20018,"Erquelinnes - Montzen","<>","Y.FLAWINNE","MOUSTIER-GARAGE",2020,2020,36,37,"2020-09-04","23:30:00","2020-09-07","05:00:00","3d","All day","Franière 2020\nPhase 1.2\nWE de CTL en continu","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",21796,"Erquelinnes - Montzen","<>","HOURPES","LOBBES",2020,2020,37,37,"2020-09-07","22:00:00","2020-09-11","04:25:00","4d","All day","Renouvellement des ponts  10 + 11: Nuits préparatoires\nCTL de nuit","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20016,"Erquelinnes - Montzen",">","Y.FLAWINNE","FRANIERE",2020,2020,37,39,"2020-09-07","05:00:00","2020-09-25","23:00:00","18d","All day","Franière 2020\nPhase 2.1\nVoie A HS en continu",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20019,"Erquelinnes - Montzen","<>","Y.FLAWINNE","MOUSTIER-GARAGE",2020,2020,40,41,"2020-10-02","23:30:00","2020-10-05","05:00:00","3d","All day","Franière 2020\nPhase 3.2\nWE de CTL en continu","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",16236,"Erquelinnes - Montzen","<>","JEMEPPE-SUR-SAMBRE-MARCHANDISE","LE CAMPINAIRE",2020,2020,40,41,"2020-10-02","23:40:00","2020-10-05","05:00:00","3d","All day","Démolition PS renouvellement de chape d'étanchéité et pose de passerelles, BK 78.887 et 86.825","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",19242,"Erquelinnes - Montzen",">","VISE-HAUT","MONTZEN-GRIL M",2020,2020,40,41,"2020-10-03","06:30:00","2020-10-04","15:00:00","1d","All day","Mise en service bloc automatique",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20684,"Erquelinnes - Montzen","<>","HOURPES","LOBBES",2020,2020,41,43,"2020-10-05","22:00:00","2020-10-23","04:25:00","18d","Nights","Renouvellement des ponts  10 + 11: Nuits préparatoires\nCTL de nuit en semaine","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",19243,"Erquelinnes - Montzen",">","VISE-HAUT","MONTZEN-GRIL M",2020,2020,41,42,"2020-10-10","06:30:00","2020-10-11","15:00:00","1d","All day","Mise en service bloc automatique",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20079,"Erquelinnes - Montzen",">","MARCHE-LES-DAMES-MARCHANDISES","NAMUR-HERBATTE",2020,2020,43,48,"2020-10-19","22:00:00","2020-11-28","06:00:00","40d","Night","Renouvellement As de Beez\nSAVU de nuit",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",10285,"Erquelinnes - Montzen","<>","LA SAMBRE","ERQUELINNES",2020,2020,43,46,"2020-10-23","22:00:00","2020-11-09","04:25:00","17d","All day","Renouvellement des ponts  10 + 11\nCTL en continu","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20080,"Erquelinnes - Montzen","<>","STATTE","NAMUR-HERBATTE",2020,2020,43,44,"2020-10-23","23:30:00","2020-10-26","04:30:00","3d","All day","Renouvellement AS Beez + massification travaux","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20081,"Erquelinnes - Montzen","<>","STATTE","NAMUR-HERBATTE",2020,2020,44,45,"2020-10-30","23:30:00","2020-11-02","04:30:00","3d","All day","Renouvellement AS Beez + massification travaux","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20082,"Erquelinnes - Montzen","<>","STATTE","NAMUR-HERBATTE",2020,2020,46,47,"2020-11-13","23:30:00","2020-11-16","04:30:00","3d","All day","Renouvellement AS Beez + massification travaux","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20685,"Erquelinnes - Montzen","<>","HOURPES","LOBBES",2020,2020,46,48,"2020-11-14","22:00:00","2020-11-22","04:25:00","8d","Nights","Renouvellement des ponts  10 + 11: Nuits de finitions\nCTL de nuit en semaine","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20083,"Erquelinnes - Montzen","<>","STATTE","NAMUR-HERBATTE",2020,2020,47,48,"2020-11-20","23:30:00","2020-11-23","04:30:00","3d","All day","Renouvellement AS Beez + massification travaux","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",10263,"Erquelinnes - Montzen","<>","LOBBES-GARAGE","ERQUELINNES",2020,2020,48,49,"2020-11-27","22:00:00","2020-11-30","04:30:00","3d","All day","Renouvellement tablier pont BK 125.363","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20686,"Erquelinnes - Montzen","<>","HOURPES","LOBBES",2020,2020,51,51,"2020-12-14","22:00:00","2020-12-19","04:25:00","5d","Nights","Renouvellement des ponts  10 + 11: Nuits de finitions\nCTL de nuit","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",21773,"Namur-Antwerpen","<>","LEUVEN","WAVRE",2020,2020,5,5,"2020-01-26"," ","2020-01-26"," ","0d","All day","Werken L139","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",21779,"Namur-Antwerpen","<>","LEUVEN","SINT-JORIS-WEERT",2020,2020,8,9,"2020-02-22"," ","2020-02-23"," ","1d","All day","Werken L139","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",21774,"Namur-Antwerpen","<>","LEUVEN","WAVRE",2020,2020,12,12,"2020-03-15"," ","2020-03-15"," ","0d","All day","Werken L139","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",21775,"Namur-Antwerpen","<>","LEUVEN","WAVRE",2020,2020,19,19,"2020-05-03"," ","2020-05-03"," ","0d","All day","Werken L139","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20659,"Namur-Antwerpen","<>","OTTIGNIES","LA ROCHE(BRABANT)",2020,2020,37,38,"2020-09-07","23:00:00","2020-09-13","05:20:00","6d","Nights","Travaux d'investissement du PS 32.576 ","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",21776,"Namur-Antwerpen","<>","LEUVEN","WAVRE",2020,2020,39,39,"2020-09-20"," ","2020-09-20"," ","0d","All day","Werken L139","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",21777,"Namur-Antwerpen","<>","LEUVEN","WAVRE",2020,2020,41,41,"2020-10-04"," ","2020-10-04"," ","0d","All day","Werken L139","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20660,"Namur-Antwerpen","<>","OTTIGNIES","LA ROCHE(BRABANT)",2020,2020,41,42,"2020-10-05","23:00:00","2020-10-11","05:20:00","6d","Nights","Travaux d'investissement du PS 32.576 ","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20662,"Namur-Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2020,2020,41,41,"2020-10-05","09:00:00","2020-10-09","15:00:00","4d","day","Travaux d'investissement du PS 32.576 ",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20664,"Namur-Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2020,2020,42,42,"2020-10-12","09:00:00","2020-10-16","15:00:00","4d","day","Travaux d'investissement du PS 32.576 ",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20656,"Namur-Antwerpen","<>","OTTIGNIES","LA ROCHE(BRABANT)",2020,2020,44,45,"2020-10-30","23:30:00","2020-11-02","05:00:00","3d","All day","Renouvellement du tablier métallique L140 BK29.453 par des ponts bacs BP et passerelles ","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",21798,"Namur-Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2020,2020,44,45,"2020-10-31","23:30:00","2020-11-01","15:00:00","1d","All day","Travaux CSV Florival",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",18390,"Namur-Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2020,2020,45,45,"2020-11-02","05:30:00","2020-11-06","23:30:00","4d","All day","Travaux CSV Florival",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",21797,"Namur-Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2020,2020,45,46,"2020-11-06","23:30:00","2020-11-09","05:00:00","3d","All day","Travaux CSV Florival",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",18398,"Namur-Antwerpen","<>","OTTIGNIES","LA ROCHE(BRABANT)",2020,2020,45,46,"2020-11-06","23:30:00","2020-11-09","05:00:00","3d","All day","Renouvellement du tablier métallique L140 BK29.453 par des ponts bacs BP et passerelles ","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20661,"Namur-Antwerpen","<>","OTTIGNIES","LA ROCHE(BRABANT)",2020,2020,46,47,"2020-11-09","23:00:00","2020-11-15","05:20:00","6d","Nights","Travaux d'investissement du PS 32.576 Rue Defalque ","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20663,"Namur-Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2020,2020,46,46,"2020-11-09","09:00:00","2020-11-13","15:00:00","4d","day","Travaux d'investissement du PS 32.576 Rue Defalque ",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20665,"Namur-Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2020,2020,47,47,"2020-11-16","09:00:00","2020-11-20","15:00:00","4d","day","Travaux d'investissement du PS 32.576 Rue Defalque ",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",21778,"Namur-Antwerpen","<>","LEUVEN","WAVRE",2020,2020,49,49,"2020-11-29"," ","2020-11-29"," ","0d","All day","Werken L139","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",10389,"Lille - Charleroi","<>","LEUZE","TOURNAI",2020,2020,38,41,"2020-09-14","23:30:00","2020-10-10","04:30:00","26d","Nights","renouvellement rails (Leuze-Barry)\nCTL de nuit en semaine","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",18044,"Lille - Charleroi","<>","LEUZE","TOURNAI",2020,2020,38,39,"2020-09-18","23:30:00","2020-09-21","04:30:00","3d","All day","renouvellement rails (Leuze-Barry)","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",18045,"Lille - Charleroi","<>","LEUZE","TOURNAI",2020,2020,39,40,"2020-09-25","23:30:00","2020-09-28","04:30:00","3d","All day","renouvellement rails (Leuze-Barry)","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20858,"Lille - Charleroi","<>","ATH","TOURNAI",2020,2020,40,41,"2020-10-02","23:40:00","2020-10-05","04:30:00","3d","All day","renouvellement rails (Leuze-Barry)","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20863,"Lille - Charleroi","<>","ATH","TOURNAI",2020,2020,41,42,"2020-10-09","23:40:00","2020-10-12","04:30:00","3d","All day","renouvellement rails (Leuze-Barry)","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",10388,"Lille - Charleroi",">","Y.LENS","BRUGELETTE",2020,2020,46,47,"2020-11-09","06:00:00","2020-11-18","06:00:00","9d","All day","Renouvellement de traverses entre Ath et Lens",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",10393,"Lille - Charleroi","<>","Y.LENS","ATH",2020,2020,46,47,"2020-11-13","22:40:00","2020-11-16","05:40:00","3d","All day","Renouvellement de traverses entre Ath et Lens","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",10390,"Lille - Charleroi",">","BRUGELETTE","ATH",2020,2020,47,50,"2020-11-18","06:00:00","2020-12-11","06:00:00","23d","All day","Renouvellement de traverses entre Ath et Lens",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",10394,"Lille - Charleroi","<>","Y.LENS","ATH",2020,2020,47,48,"2020-11-20","22:40:00","2020-11-23","05:40:00","3d","All day","Renouvellement de traverses entre Ath et Lens","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",17021,"Lille - Charleroi","<>","Y.LENS","ATH",2020,2020,48,49,"2020-11-27","22:40:00","2020-11-30","05:40:00","3d","All day","Renouvellement de traverses entre Ath et Lens","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",17022,"Lille - Charleroi","<>","Y.LENS","ATH",2020,2020,49,50,"2020-12-04","22:40:00","2020-12-07","05:40:00","3d","All day","Renouvellement de traverses entre Ath et Lens","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",19811,"Lille - Charleroi","<>","LUTTRE","MANAGE",2020,2020,40,40,"2020-09-28","00:05:00","2020-10-02","05:50:00","4d","Nights","Préparation/finition P93","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",10050,"Lille - Charleroi","<>","LUTTRE","MANAGE",2020,2020,40,41,"2020-10-02","23:20:00","2020-10-05","05:50:00","3d","All day","P93 ","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",10052,"Lille - Charleroi",">","LUTTRE","MANAGE",2020,2020,40,42,"2020-10-02","22:50:00","2020-10-12","05:50:00","10d","All day","P93 ",null,"ST",null,null,null,null,null,null,null,null," "]
["Infrabel",10427,"Lille - Charleroi","<>","LUTTRE","MANAGE",2020,2020,41,45,"2020-10-05","00:05:00","2020-11-06","05:50:00","32d","Nights","Préparation/finition P93","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",10051,"Lille - Charleroi","<>","LUTTRE","MANAGE",2020,2020,41,42,"2020-10-09","23:20:00","2020-10-12","05:50:00","3d","All day","P93 ","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",19220,"Lille - Charleroi","<>","LUTTRE","MANAGE",2020,2020,42,43,"2020-10-16","23:20:00","2020-10-19","05:50:00","3d","All day","P93 ","T",null,null,null,null,null,null,null,null,null," "]
["Infrabel",20359,"Erquelinnes - Montzen",">","FOURON-SAINT-MARTIN","REMERSDAAL",2021,2021,3,17,"2021-01-11",null,"2021-04-18",null,"97d","All day","Travaux V + OA + ECFM tunnel de Veurs (phase I)","","ST",null,null,null,null,null,null,null,null,"saisonnier"]
["Infrabel",19886,"Athus - Meuse",">","VONECHE","BEAURAING",2021,2021,5,13,"2021-01-25",null,"2021-03-21",null,"55d","All day","Pose de caniveaux piste\r\nTravail en double prestations","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",19213,"Namur-Antwerpen",">","Y.LOUVAIN-LA-NEUVE","MONT-SAINT-GUIBERT",2021,2021,6,50,"2021-02-01",null,"2021-12-11",null,"313d","All day","Modernisation Axe 3\r","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",16761,"Erquelinnes - Montzen","<>","LOBBES","ERQUELINNES",2021,2021,7,8,"2021-02-13",null,"2021-02-14",null,"1d","All day","Renouvellement As 04AL & 04BL & 09AL & 09BL & 10AL & 10BL","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20864,"Erquelinnes - Montzen","<>","AISEAU","LE CAMPINAIRE",2021,2021,10,10,"2021-03-01",null,"2021-03-06",null,"5d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20865,"Erquelinnes - Montzen","<>","AISEAU","LE CAMPINAIRE",2021,2021,11,11,"2021-03-08",null,"2021-03-13",null,"5d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20866,"Erquelinnes - Montzen","<>","AISEAU","LE CAMPINAIRE",2021,2021,12,12,"2021-03-15",null,"2021-03-20",null,"5d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",17001,"Namur-Antwerpen","<>","TILLY","LA ROCHE(BRABANT)",2021,2021,13,14,"2021-03-22",null,"2021-04-02",null,"11d","All day","- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement","T","",null,null,null,null,null,null,null,null,"Détournements à prévoir"]
["Infrabel",20867,"Erquelinnes - Montzen","<>","AISEAU","LE CAMPINAIRE",2021,2021,13,13,"2021-03-22",null,"2021-03-27",null,"5d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",17039,"Athus - Meuse",">","JAMBES","LUSTIN",2021,2021,14,17,"2021-03-31",null,"2021-04-18",null,"18d","All day","Criblage du ballast (C75)","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",10355,"Namur-Antwerpen","<>","TILLY","LA ROCHE(BRABANT)",2021,2021,14,17,"2021-04-02",null,"2021-04-19",null,"17d","All day","- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement","T","",null,null,null,null,null,null,null,null,"Trafic HKM à détourner"]
["Infrabel",21105,"Lille - Charleroi","<>","MANAGE","LUTTRE",2021,2021,15,16,"2021-04-10",null,"2021-04-12",null,"2d","All day","Renouvellement du PS 51.035 et du pont du canal - Travaux SPW","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",10038,"Lille - Charleroi","<>","Y.FAMILLEUREUX","MANAGE",2021,2021,16,26,"2021-04-12",null,"2021-06-25",null,"74d","All day","Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21354,"Lille - Charleroi","<>","Y.FAMILLEUREUX","MANAGE",2021,2021,16,17,"2021-04-16",null,"2021-04-19",null,"3d","All day","Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21317,"Athus - Meuse","<>","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,16,17,"2021-04-17",null,"2021-04-19",null,"2d","All day","Traitement de zone boueuse Bk 104.150 à Bk 104.190","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",18071,"Athus - Meuse",">","BEAURAING","BEAURAING",2021,2021,16,17,"2021-04-17",null,"2021-04-19",null,"2d","All day","Renouvellement de traverses à la grue (24080-24700)\r\nRenouvellement des traverses à la grue (14790-15230)","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",16993,"Namur-Antwerpen","<>","TILLY","LA ROCHE(BRABANT)",2021,2021,17,18,"2021-04-19",null,"2021-04-30",null,"11d","All day","- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement","T","",null,null,null,null,null,null,null,null,"Détournements à prévoir"]
["Infrabel",21355,"Lille - Charleroi","<>","Y.FAMILLEUREUX","MANAGE",2021,2021,17,18,"2021-04-23",null,"2021-04-26",null,"3d","All day","Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",18072,"Athus - Meuse",">","HOUYET","VONECHE",2021,2021,17,18,"2021-04-24",null,"2021-04-26",null,"2d","All day","Renouvellement des traverses à la grue (24080-24700)\r\nRenouvellement des traverses à la grue (14790-15230)","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",21320,"Athus - Meuse","<>","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,18,19,"2021-05-01",null,"2021-05-03",null,"2d","All day","Traitement de zone boueuse Bk 116.150 à Bk 116.180 & renouvellement étanchéité PI","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21323,"Athus - Meuse","<>","HALANZY","AUBANGE",2021,2021,18,19,"2021-05-01",null,"2021-05-03",null,"2d","All day","Traitement de zone boueuse Bk 138.830 à 138.870 (PN41)","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21401,"Athus - Meuse",">","HOUYET","VONECHE",2021,2021,18,19,"2021-05-01",null,"2021-05-03",null,"2d","All day","Renouvellement des traverses à la grue (24080-24700)\r\nRenouvellement des traverses à la grue (14790-15230)","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20857,"Namur-Antwerpen","<>","TILLY","LA ROCHE(BRABANT)",2021,2021,19,19,"2021-05-03",null,"2021-05-08",null,"5d","All day","- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement","T","",null,null,null,null,null,null,null,null,"Détournements à prévoir"]
["Infrabel",21358,"Lille - Charleroi","<>","Y.FAMILLEUREUX","MANAGE",2021,2021,19,20,"2021-05-07",null,"2021-05-10",null,"3d","All day","Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",18076,"Athus - Meuse",">","PALISEUL","BERTRIX",2021,2021,20,27,"2021-05-10",null,"2021-06-27",null,"48d","All day","Assainissement à la grue (71410-72140)","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20868,"Erquelinnes - Montzen","<>","AISEAU","LE CAMPINAIRE",2021,2021,20,20,"2021-05-10",null,"2021-05-15",null,"5d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21359,"Lille - Charleroi","<>","Y.FAMILLEUREUX","MANAGE",2021,2021,20,21,"2021-05-12",null,"2021-05-17",null,"5d","All day","Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21035,"Lille - Charleroi","<>","ATH","LEUZE",2021,2021,21,22,"2021-05-17",null,"2021-05-28",null,"11d","All day","Péparartion renouvellement 34AF/34BF + 42F","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20869,"Erquelinnes - Montzen","<>","AISEAU","LE CAMPINAIRE",2021,2021,21,21,"2021-05-17",null,"2021-05-22",null,"5d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20189,"Erquelinnes - Montzen","<>","HUY","FLEMALLE-HAUTE",2021,2021,21,22,"2021-05-21",null,"2021-05-25",null,"4d","All day","Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21357,"Lille - Charleroi","<>","Y.FAMILLEUREUX","MANAGE",2021,2021,21,22,"2021-05-21",null,"2021-05-25",null,"4d","All day","Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21036,"Lille - Charleroi","<>","ATH","LEUZE",2021,2021,21,22,"2021-05-21",null,"2021-05-25",null,"4d","All day","Renouvellement des AS 34AF/34BF + 42F","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20859,"Namur-Antwerpen","<>","TILLY","LA ROCHE(BRABANT)",2021,2021,22,22,"2021-05-24",null,"2021-05-29",null,"5d","All day","- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement","T","",null,null,null,null,null,null,null,null,"Pas de traffic supplémentaire les nuits de CTL. (Doc envoyé le 12/03/18)"]
["Infrabel",20671,"Erquelinnes - Montzen","<>","HOURPES","LOBBES",2021,2021,22,25,"2021-05-24",null,"2021-06-18",null,"25d","All day","Renouvellement du pont 9","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",10281,"Erquelinnes - Montzen","<>","LOBBES","HOURPES",2021,2021,25,28,"2021-06-18",null,"2021-07-05",null,"17d","All day","Renouvellement du pont 9","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21155,"Erquelinnes - Montzen","<>","FLEMALLE-HAUTE","HUY",2021,2021,22,23,"2021-05-28",null,"2021-05-31",null,"3d","All day","Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20860,"Namur-Antwerpen","<>","TILLY","LA ROCHE(BRABANT)",2021,2021,23,23,"2021-05-31",null,"2021-06-05",null,"5d","All day","- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement","T","",null,null,null,null,null,null,null,null,"Pas de traffic supplémentaire les nuits de CTL. (Doc envoyé le 12/03/18)"]
["Infrabel",20190,"Erquelinnes - Montzen","<>","FLEMALLE-HAUTE","HUY",2021,2021,23,24,"2021-06-04",null,"2021-06-07",null,"3d","All day","Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",18107,"Lille - Charleroi","<>","BRAINE-LE-COMTE","SOIGNIES",2021,2021,23,24,"2021-06-05",null,"2021-06-07",null,"2d","All day","P93 - Renouvellement des traverses Braine-Soignies","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20451,"Erquelinnes - Montzen","<>","ANDENNE","NAMUR",2021,2021,24,25,"2021-06-12",null,"2021-06-13",null,"1d","All day","Massification travaux OA + voies tronçon Andenne - Namur (renouvellement de rails suite défaut US entre BK 56500 et BK 58000)","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",16855,"Erquelinnes - Montzen","<>","JEMEPPE-SUR-SAMBRE","LE CAMPINAIRE",2021,2021,25,26,"2021-06-18",null,"2021-06-21",null,"3d","All day","Reprise en EBP-PLP des installations de Tamines et Auvelais. (Attention rework ETCS sur Auvelais en même temps).\r\nPas d'autres services dans la coupure (sauf train d'essais ES et ETCS).","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20432,"Erquelinnes - Montzen","<>","ANDENNE","NAMUR",2021,2021,26,27,"2021-06-26",null,"2021-06-27",null,"1d","All day","Massification travaux OA tronçon Andenne - Namur (renouvellement de quais - renouvellement passerelles - parois rocheuses - ...)","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20674,"Erquelinnes - Montzen","<>","HOURPES","LOBBES",2021,2021,32,33,"2021-08-02",null,"2021-08-09",null,"7d","All day","Renouvellement du pont 9","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",19971,"Namur-Antwerpen","<>","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2021,2021,32,34,"2021-08-02",null,"2021-08-16",null,"14d","All day","Cribleuse L144 entre Bk 0.400 et 13.500","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21325,"Athus - Meuse","<>","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,32,33,"2021-08-07",null,"2021-08-09",null,"2d","All day","Traitement de zone boueuse Bk 94.440 à 94.780","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21238,"Erquelinnes - Montzen","<>","LA SAMBRE","HOURPES",2021,2021,33,34,"2021-08-09",null,"2021-08-15",null,"6d","All day","Renouvellement As 04AL & 04BL & 09AL & 09BL & 10AL & 10BL","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21331,"Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,33,33,"2021-08-09",null,"2021-08-13",null,"4d","All day","Peignage de rochers et coupe des végétations","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20360,"Erquelinnes - Montzen",">","FOURON-SAINT-MARTIN","REMERSDAAL",2021,2021,33,45,"2021-08-09",null,"2021-10-31",null,"83d","All day","Travaux Cat + OA + ECFM tunnel de Veurs (phase II)","","ST",null,null,null,null,null,null,null,null,"saisonnier"]
["Infrabel",21326,"Athus - Meuse","<>","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,33,34,"2021-08-14",null,"2021-08-16",null,"2d","All day","Traitement de zone boueuse Bk 94.440 à 94.780","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21332,"Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,34,34,"2021-08-16",null,"2021-08-20",null,"4d","All day","Peignage de rochers et coupe des végétations","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",21330,"Athus - Meuse","<>","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,34,35,"2021-08-21",null,"2021-08-23",null,"2d","All day","Traitement de zone boueuse Bk 94.440 à 94.780","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21333,"Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,35,35,"2021-08-23",null,"2021-08-27",null,"4d","All day","Peignage de rochers et coupe des végétations","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",21327,"Athus - Meuse","<>","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,35,36,"2021-08-28",null,"2021-08-30",null,"2d","All day","Traitement de zone boueuse Bk 94.440 à 94.780","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21334,"Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,36,36,"2021-08-30",null,"2021-09-03",null,"4d","All day","Peignage de rochers et coupe des végétations","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20055,"Athus - Meuse",">","BERTRIX","SAINT-VINCENT-BELLEFONTAINE",2021,2021,37,38,"2021-09-11",null,"2021-09-13",null,"2d","All day","Pose traverse entre BK92800-93565 P93","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",18077,"Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,38,39,"2021-09-13",null,"2021-09-22",null,"9d","All day","Renouvellement des traverses (P93)","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20104,"Erquelinnes - Montzen",">","FRANIERE","FLAWINNE",2021,2021,38,44,"2021-09-13",null,"2021-10-24",null,"41d","All day","Rectification du tracé à Floreffe pour Voie 3 et passage à 120km/h + renouvellement des quais","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20871,"Erquelinnes - Montzen","<>","AISEAU","LE CAMPINAIRE",2021,2021,40,40,"2021-09-27",null,"2021-10-01",null,"4d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20853,"Erquelinnes - Montzen","<>","AISEAU","FARCIENNES",2021,2021,40,41,"2021-10-01",null,"2021-10-04",null,"3d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21390,"Erquelinnes - Montzen","<>","AISEAU","FARCIENNES",2021,2021,40,41,"2021-10-01",null,"2021-10-04",null,"3d","Night","Renouvellement AS 64BJ","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",18079,"Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,41,43,"2021-10-04",null,"2021-10-17",null,"13d","All day","Renouvellement de rails","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20872,"Erquelinnes - Montzen","<>","AISEAU","LE CAMPINAIRE",2021,2021,41,41,"2021-10-04",null,"2021-10-09",null,"5d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20873,"Erquelinnes - Montzen","<>","AISEAU","LE CAMPINAIRE",2021,2021,42,42,"2021-10-11",null,"2021-10-16",null,"5d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20194,"Athus - Meuse",">","GEDINNE","PALISEUL",2021,2021,43,46,"2021-10-18",null,"2021-11-12",null,"25d","All day","Pose de drains","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20959,"Namur-Antwerpen","<>","COURT-SAINT-ETIENNE","FAUX",2021,2021,43,45,"2021-10-22",null,"2021-11-01",null,"10d","All day","Entretien PS Defalque 32.576","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20111,"Erquelinnes - Montzen","<>","FRANIERE","FLAWINNE",2021,2021,43,44,"2021-10-22",null,"2021-10-25",null,"3d","All day","Rectification du tracé à Floreffe pour Voie 3 et passage à 120km/h + renouvellement des quais","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20105,"Erquelinnes - Montzen",">","FRANIERE","FLAWINNE",2021,2021,44,50,"2021-10-25",null,"2021-12-05",null,"41d","All day","Rectification du tracé à Floreffe pour Voie 3 et passage à 120km/h + renouvellement des quais","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20112,"Erquelinnes - Montzen","<>","FRANIERE","FLAWINNE",2021,2021,44,45,"2021-10-29",null,"2021-11-01",null,"3d","All day","Rectification du tracé à Floreffe pour Voie 3 et passage à 120km/h + renouvellement des quais","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20113,"Erquelinnes - Montzen","<>","FRANIERE","FLAWINNE",2021,2021,45,46,"2021-11-05",null,"2021-11-08",null,"3d","All day","Rectification du tracé à Floreffe pour Voie 3 et passage à 120km/h + renouvellement des quais","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",17963,"Lille - Charleroi","<>","TOURNAI","BLANDAIN-FRONTIERE",2021,2021,46,50,"2021-11-08",null,"2021-12-11",null,"33d","All day","-Renouvellement de traverses,\r\n-Renouvellement des quais de Froyennes\r\n-Renouvellement de chape d’étanchéité\r\n-Renouvellement d’aiguillages\r\n-Renouvellement de rails\r\n-Réalisation de travaux divers aux abords clôture, débroussaillage,… afin de sécuriser","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20114,"Erquelinnes - Montzen","<>","FRANIERE","FLAWINNE",2021,2021,46,47,"2021-11-12",null,"2021-11-15",null,"3d","All day","Rectification du tracé à Floreffe pour Voie 3 et passage à 120km/h + renouvellement des quais","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20964,"Namur-Antwerpen","<>","COURT-SAINT-ETIENNE","FAUX",2021,2021,47,48,"2021-11-14",null,"2021-11-21",null,"7d","All day","Entretien PS Defalque 32.576","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",21402,"Athus - Meuse",">","VONECHE","BEAURAING",2021,2021,47,50,"2021-11-15",null,"2021-12-10",null,"25d","All day","Pose de caniveaux piste\r\nTravail en double prestations","","ST",null,null,null,null,null,null,null,null," "]
["Infrabel",20875,"Erquelinnes - Montzen","<>","AISEAU","LE CAMPINAIRE",2021,2021,47,47,"2021-11-15",null,"2021-11-20",null,"5d","Night","Renouvellement passages supérieurs BK 85.708 et 84.625","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20115,"Erquelinnes - Montzen","<>","FRANIERE","FLAWINNE",2021,2021,47,48,"2021-11-19",null,"2021-11-22",null,"3d","All day","Rectification du tracé à Floreffe pour Voie 3 et passage à 120km/h + renouvellement des quais","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20116,"Erquelinnes - Montzen","<>","FRANIERE","FLAWINNE",2021,2021,48,49,"2021-11-26",null,"2021-11-29",null,"3d","All day","Rectification du tracé à Floreffe pour Voie 3 et passage à 120km/h + renouvellement des quais","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",20118,"Erquelinnes - Montzen","<>","FRANIERE","FLAWINNE",2021,2021,49,50,"2021-12-03",null,"2021-12-06",null,"3d","All day","Rectification du tracé à Floreffe pour Voie 3 et passage à 120km/h + renouvellement des quais","T","",null,null,null,null,null,null,null,null," "]
["Infrabel",17019,null,"<>","AISEAU","FARCIENNES",2021,2021,11,12,"2021-03-12","23:00:00","2021-03-15","04:00:00","3d","All day","Renouvellement passages supérieurs BK 85.708 et 84.625","T",null,null,null,null,null,null,null,null,null," "]

{"sheet":"Data","index":4,"n_rows":24,"n_cols":7,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction"]
["SNCF R",87,"Boulogne-Calais",1,"All day",10868,"Signal work"]
[null,null,"Calais-Dunkerque-Hazebrouck",2,"Day",null,"Switch work"]
[null,null,"Calais-Lille-Aulnoye",3,"Night",null,"Catenary work"]
[null,null,"Hazebrouck-Lens-Aulnoye",4,null,null,"Track work"]
[null,null,"Amiens-Douai",5,null,null,"Rail work"]
[null,null,"Paris-Amiens",6,null,null,"Tunnel work"]
[null,null,"Paris-Busigny",7,null,null,"Bridge work"]
[null,null,"Aulnoye-Longuyon",8,null,null,"Misc. Work"]
[null,null,"Longuyon-Metz-Sarrebourg",9,null,null,"Maintanance"]
[null,null,"Longuyon-Nancy-Sarrebourg",10]
[null,null,"Lerouville-Metz",11]
[null,null,"Lerouville-Nancy",12]
[null,null,"Sarrebourg-Basel",13]
[null,null,"Dijon-Toul",14]
[null,null,"Dijon-Lyon",15]
[null,null,"Dijon-Amberieu-Lyon",16]
[null,null,"Lyon-Valence",17]
[null,null,"Valence - Avignon",18]
[null,null,"Avignon-Miramasparouest",19]
[null,null,"Avignon-Miramasparest",20]
[null,null,"Miramas-Marseille",21]
[null,null,"Miramas-Fos-Marseille",22]
[null,null,"Aulnoye-Feignies-Jeumont",23]

{"sheet":"SNCFR","index":5,"n_rows":701,"n_cols":32,"rows_kept":701,"cut":false,"hidden":false,"merged":[[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]]}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"SNCF Réseau","6652754861_6652623761","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2020,2020,6,48,"2020-02-03T20:25:00","20:25","2020-11-27T04:55:00","04:55",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"125 jours dans le régime binaire"]
[null,"SNCF Réseau","6652754861_6652625361","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2019,2020,51,50,"2019-12-16T13:45:00","13:45","2020-12-11T14:55:00","14:55",3730,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6652756661_6652629561","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2019,2020,51,50,"2019-12-16T09:35:00","09:35","2020-12-11T10:35:00","10:35",2742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
[null,"SNCF Réseau","6652756661_6652630361","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2019,2020,51,50,"2019-12-21T09:00:00","09:00","2020-12-12T10:35:00","10:35",1091,"DAY",null,null,null,null,null,null,null,null,null,null,null,"104 jours dans le régime binaire"]
[null,"SNCF Réseau","6652756661_6652631161","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2020,2020,6,48,"2020-02-03T22:00:00","22:00","2020-11-27T04:00:00","04:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"130 jours dans le régime binaire"]
[null,"SNCF Réseau","6652757561_6652607561","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2020,2020,6,49,"2020-02-03T21:45:00","21:45","2020-12-04T05:25:00","05:25",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"140 jours dans le régime binaire"]
[null,"SNCF Réseau","6652757561_6652609361","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2019,2020,51,50,"2019-12-16T14:00:00","14:00","2020-12-11T15:00:00","15:00",3751,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6652757561_6652608561","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2019,2020,51,50,"2019-12-16T09:54:00","09:54","2020-12-11T10:54:00","10:54",2726,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6652756461_6652669361","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2020,2020,7,44,"2020-02-10T10:00:00","10:00","2020-10-30T17:00:00","17:00",330,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
[null,"SNCF Réseau","6652756461_6652668361","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2019,2020,51,50,"2019-12-16T13:50:00","13:50","2020-12-11T16:50:00","16:50",4211,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6652756461_6652670361","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2020,2020,6,48,"2020-02-03T21:03:00","21:03","2020-11-27T05:20:00","05:20",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"135 jours dans le régime binaire"]
[null,"SNCF Réseau","6652759861_6652673161","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2019,2020,51,50,"2019-12-16T10:11:00","10:11","2020-12-11T13:00:00","13:00",3252,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6652759861_6652672161","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2020,2020,16,45,"2020-04-14T10:00:00","10:00","2020-11-06T15:00:00","15:00",275,"DAY",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6652753761_6652686961","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2019,2020,51,50,"2019-12-16T13:50:00","13:50","2020-12-11T16:50:00","16:50",4211,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6652753761_6652682761","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2019,2020,51,50,"2019-12-16T13:50:00","13:50","2020-12-09T15:35:00","15:35",1528,"DAY",null,null,null,null,null,null,null,null,null,null,null,"99 jours dans le régime binaire"]
[null,"SNCF Réseau","6652753761_6652685161","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2020,7,44,"2020-02-10T10:05:00","10:05","2020-10-30T17:00:00","17:00",329,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
[null,"SNCF Réseau","6652753761_6652684361","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2020,7,44,"2020-02-10T12:25:00","12:25","2020-10-30T17:00:00","17:00",327,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
[null,"SNCF Réseau","6652753761_6652685961","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2020,6,48,"2020-02-03T21:03:00","21:03","2020-11-27T05:20:00","05:20",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"115 jours dans le régime binaire"]
[null,"SNCF Réseau","6652753761_6652683561","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2019,2020,51,50,"2019-12-17T13:50:00","13:50","2020-12-11T16:50:00","16:50",2527,"DAY",null,null,null,null,null,null,null,null,null,null,null,"151 jours dans le régime binaire"]
[null,"SNCF Réseau","6652285361_6652234861","Paris-Amiens",">","StadeDeFrance","StDenis",2019,2020,51,50,"2019-12-17T00:30:00","00:30","2020-12-12T04:25:00","04:25",1125,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"255 jours dans le régime binaire"]
[null,"SNCF Réseau","6652285361_6652237461","Paris-Amiens",">","StadeDeFrance","StDenis",2019,2020,51,50,"2019-12-17T01:00:00","01:00","2020-12-12T05:05:00","05:05",1295,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"255 jours dans le régime binaire"]
[null,"SNCF Réseau","6652285361_6652235661","Paris-Amiens",">","StadeDeFrance","StDenis",2019,2020,51,50,"2019-12-17T00:35:00","00:35","2020-12-12T04:45:00","04:45",1210,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"255 jours dans le régime binaire"]
[null,"SNCF Réseau","6652285361_6652238261","Paris-Amiens",">","StadeDeFrance","StDenis",2019,2020,51,50,"2019-12-17T01:00:00","01:00","2020-12-12T05:20:00","05:20",1359,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"255 jours dans le régime binaire"]
[null,"SNCF Réseau","6652285361_6652236461","Paris-Amiens",">","StadeDeFrance","StDenis",2020,2020,15,49,"2020-04-06T23:55:00","23:55","2020-12-04T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"32 jours dans le régime binaire"]
[null,"SNCF Réseau","6651860261_6651804861","Sarrebourg-Basel",">","Graffenstaden","Selestat",2019,2020,51,50,"2019-12-16T13:55:00","13:55","2020-12-11T15:08:00","15:08",3708,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651860261_6651804061","Sarrebourg-Basel",">","Graffenstaden","Selestat",2019,2020,51,50,"2019-12-16T10:33:00","10:33","2020-12-11T11:19:00","11:19",2773,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651860261_6651803261","Sarrebourg-Basel",">","Graffenstaden","Selestat",2020,2020,9,43,"2020-02-24T23:23:00","23:23","2020-10-23T05:04:00","05:04",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6651860261_6651802461","Sarrebourg-Basel",">","Graffenstaden","Selestat",2020,2020,8,42,"2020-02-17T23:25:00","23:25","2020-10-16T05:35:00","05:35",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"54 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859661_6651796661","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2020,9,47,"2020-02-24T22:50:00","22:50","2020-11-19T05:05:00","05:05",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859661_6651793461","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2020,12,48,"2020-03-16T23:05:00","23:05","2020-11-26T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859661_6651797461","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2019,2020,51,50,"2019-12-16T14:50:00","14:50","2020-12-11T16:00:00","16:00",3921,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859661_6651795861","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2019,2020,51,50,"2019-12-16T09:40:00","09:40","2020-12-11T10:30:00","10:30",2573,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859661_6651795061","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2019,2020,51,50,"2019-12-16T09:29:00","09:29","2020-12-11T10:26:00","10:26",2557,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859661_6651794261","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2019,2020,51,50,"2019-12-16T15:01:00","15:01","2020-12-11T16:04:00","16:04",3937,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651861361_6651835861","Sarrebourg-Basel",">","Colmar","Lutterbach",2020,2020,7,45,"2020-02-10T23:01:00","23:01","2020-11-05T05:16:00","05:16",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
[null,"SNCF Réseau","6651861361_6651835061","Sarrebourg-Basel",">","Colmar","Lutterbach",2019,2020,51,50,"2019-12-16T10:03:00","10:03","2020-12-11T10:50:00","10:50",2654,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651861361_6651836661","Sarrebourg-Basel",">","Colmar","Lutterbach",2019,2020,51,50,"2019-12-16T14:25:00","14:25","2020-12-11T15:39:00","15:39",3835,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651861361_6651834261","Sarrebourg-Basel",">","Colmar","Lutterbach",2020,2020,8,48,"2020-02-17T23:15:00","23:15","2020-11-26T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6651860061_6651816861","Sarrebourg-Basel",">","Saverne","Vendenheim",2019,2020,51,50,"2019-12-16T13:45:00","13:45","2020-12-11T14:34:00","14:34",3569,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651860061_6651815861","Sarrebourg-Basel",">","Saverne","Vendenheim",2019,2020,51,50,"2019-12-16T22:57:00","22:57","2020-12-10T05:12:00","05:12",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"79 jours dans le régime binaire"]
[null,"SNCF Réseau","6651860061_6651819261","Sarrebourg-Basel",">","Saverne","Vendenheim",2019,2020,51,50,"2019-12-16T13:36:00","13:36","2020-12-11T14:50:00","14:50",3635,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651860061_6651818461","Sarrebourg-Basel",">","Saverne","Vendenheim",2019,2020,51,50,"2019-12-16T13:35:00","13:35","2020-12-11T14:26:00","14:26",3537,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651860061_6651817661","Sarrebourg-Basel",">","Saverne","Vendenheim",2019,2020,51,50,"2019-12-16T13:49:00","13:49","2020-12-11T14:57:00","14:57",3663,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859761_6651791461","Sarrebourg-Basel",">","Reding","Saverne",2019,2020,51,50,"2019-12-16T14:00:00","14:00","2020-12-11T14:45:00","14:45",3614,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859761_6651792261","Sarrebourg-Basel",">","Reding","Saverne",2019,2020,51,50,"2019-12-16T13:21:00","13:21","2020-12-11T14:36:00","14:36",3578,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859761_6651790461","Sarrebourg-Basel",">","Reding","Saverne",2020,2020,9,50,"2020-02-24T22:45:00","22:45","2020-12-10T04:57:00","04:57",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"106 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859461_6651826061","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2019,2020,51,50,"2019-12-16T10:17:00","10:17","2020-12-11T11:09:00","11:09",2732,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859461_6651830061","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2020,18,47,"2020-04-27T22:52:00","22:52","2020-11-20T04:58:00","04:58",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859461_6651827661","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2019,2020,51,50,"2019-12-16T14:10:00","14:10","2020-12-11T15:19:00","15:19",3753,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6651859461_6651829261","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2020,10,50,"2020-03-03T23:26:00","23:26","2020-12-11T05:18:00","05:18",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"54 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778361_6651731161","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2019,2020,51,50,"2019-12-17","00:00","2020-12-12T05:00:00","05:00",1285,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"257 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778361_6651729561","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778361_6651730361","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2019,2020,51,50,"2019-12-16T01:45:00","01:45","2020-12-07T04:45:00","04:45",240,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651777861_6651680961","Paris-Amiens",">","Villiers le Bel","Goussainville",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651777861_6651683361","Paris-Amiens",">","Villiers le Bel","Goussainville",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651777861_6651684161","Paris-Amiens",">","Villiers le Bel","Goussainville",2020,2020,6,50,"2020-02-04T01:14:00","01:14","2020-12-12T04:50:00","04:50",433,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"90 jours dans le régime binaire"]
[null,"SNCF Réseau","6651777861_6651681761","Paris-Amiens",">","Villiers le Bel","Goussainville",2019,2020,51,50,"2019-12-17T00:20:00","00:20","2020-12-12T04:50:00","04:50",676,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"140 jours dans le régime binaire"]
[null,"SNCF Réseau","6651777861_6651682561","Paris-Amiens",">","Villiers le Bel","Goussainville",2019,2020,51,50,"2019-12-16T23:46:00","23:46","2020-12-11T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
[null,"SNCF Réseau","6651777861_6651684961","Paris-Amiens",">","Villiers le Bel","Goussainville",2019,2020,51,50,"2019-12-16T23:45:00","23:45","2020-12-11T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778961_6651740961","Paris-Amiens",">","Orry","Creil",2020,2020,7,48,"2020-02-11T01:10:00","01:10","2020-11-28T05:26:00","05:26",406,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"75 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778961_6651738561","Paris-Amiens",">","Orry","Creil",2020,2020,9,27,"2020-02-24T23:49:00","23:49","2020-07-03T04:54:00","04:54",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778961_6651741761","Paris-Amiens",">","Orry","Creil",2019,2020,52,50,"2019-12-23T01:30:00","01:30","2020-12-07T04:30:00","04:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778961_6651742561","Paris-Amiens",">","Orry","Creil",2019,2020,52,50,"2019-12-23T01:51:00","01:51","2020-12-07T04:51:00","04:51",70,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778961_6651740161","Paris-Amiens",">","Orry","Creil",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778961_6651739361","Paris-Amiens",">","Orry","Creil",2020,2020,7,48,"2020-02-10T23:53:00","23:53","2020-11-27T04:42:00","04:42",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"75 jours dans le régime binaire"]
[null,"SNCF Réseau","6658927861_6665963261","Paris-Busigny",">","Aulnay","Mitry",2020,2020,4,42,"2020-01-20T23:20:00","23:20","2020-10-16T04:40:00","04:40",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6658927861_6665952961","Paris-Busigny",">","Aulnay","Mitry",2020,2020,4,42,"2020-01-21T01:30:00","01:30","2020-10-17T04:40:00","04:40",301,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
[null,"SNCF Réseau","6658927861_6665968861","Paris-Busigny",">","Aulnay","Mitry",2019,2020,51,50,"2019-12-16T23:20:00","23:20","2020-12-11T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
[null,"SNCF Réseau","6658927861_6665935161","Paris-Busigny",">","Aulnay","Mitry",2019,2020,51,50,"2019-12-17T01:30:00","01:30","2020-12-11T04:40:00","04:40",735,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"158 jours dans le régime binaire"]
[null,"SNCF Réseau","6651777961_6651693761","Paris-Busigny",">","Mitry","Ormoy",2019,2020,51,45,"2019-12-17","00:00","2020-11-07T04:45:00","04:45",831,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"175 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778261_6651676961","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-16T01:35:00","01:35","2020-12-07T04:35:00","04:35",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778261_6651677761","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-16T23:50:00","23:50","2020-12-11T04:50:00","04:50",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778261_6651675361","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-16T23:40:00","23:40","2020-12-11T04:35:00","04:35",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778261_6651678561","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-17T01:20:00","01:20","2020-12-12T04:50:00","04:50",675,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"140 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778261_6651679361","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-16T01:40:00","01:40","2020-12-07T04:40:00","04:40",236,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778261_6651676161","Paris-Amiens",">","Goussainville","Orry",2019,2020,51,50,"2019-12-17T00:15:00","00:15","2020-12-12T04:45:00","04:45",664,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"140 jours dans le régime binaire"]
[null,"SNCF Réseau","6651779161_6651689961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-17T01:00:00","01:00","2020-12-12T04:50:00","04:50",1202,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6651779161_6651687961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651779161_6651690961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-17T00:35:00","00:35","2020-12-12T05:05:00","05:05",1265,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6651779161_6651688961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-16","00:00","2020-12-11T05:05:00","05:05",-5,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6651779161_6651691961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651779161_6651686961","Paris-Amiens",">","Stade de France","SaintDenis",2019,2020,51,50,"2019-12-16T23:25:00","23:25","2020-12-11T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778061_6651735961","Paris-Amiens",">","Bif de Pierrefitte","Orry",2020,2020,7,48,"2020-02-11","00:00","2020-11-28T05:00:00","05:00",375,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"75 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778061_6651733561","Paris-Amiens",">","Bif de Pierrefitte","Orry",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",142,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"32 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778061_6651734361","Paris-Amiens",">","Bif de Pierrefitte","Orry",2019,2020,52,50,"2019-12-23T01:45:00","01:45","2020-12-07T04:45:00","04:45",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778061_6651735161","Paris-Amiens",">","Bif de Pierrefitte","Orry",2019,2020,52,50,"2019-12-23T01:30:00","01:30","2020-12-07T04:30:00","04:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778561_6651703161","Paris-Amiens",">","SaintDenis","VilliersLeBel",2019,2020,51,50,"2019-12-16T23:55:00","23:55","2020-12-11T04:50:00","04:50",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778561_6651705561","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2020,2,50,"2020-01-07T00:30:00","00:30","2020-12-12T04:55:00","04:55",1204,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"245 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778561_6651703961","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2020,2,50,"2020-01-07T01:05:00","01:05","2020-12-12T04:50:00","04:50",1183,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"245 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778561_6651701561","Paris-Amiens",">","SaintDenis","VilliersLeBel",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778561_6651702361","Paris-Amiens",">","SaintDenis","VilliersLeBel",2019,2020,51,50,"2019-12-16T23:35:00","23:35","2020-12-11T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
[null,"SNCF Réseau","6651778561_6651704761","Paris-Amiens",">","SaintDenis","VilliersLeBel",2019,2020,51,50,"2019-12-16T01:30:00","01:30","2020-12-07T04:30:00","04:30",228,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386461_6651365661","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2019,2020,52,50,"2019-12-23T01:35:00","01:35","2020-12-07T04:55:00","04:55",111,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386461_6651368061","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2019,2020,51,50,"2019-12-16T10:02:00","10:02","2020-12-11T11:12:00","11:12",2801,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386461_6651366461","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2019,2020,51,50,"2019-12-16T14:14:00","14:14","2020-12-11T14:58:00","14:58",3742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386461_6651364661","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2020,2020,3,42,"2020-01-13T22:58:00","22:58","2020-10-16T04:58:00","04:58",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"104 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386461_6651367261","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2019,2020,52,50,"2019-12-23","00:00","2020-12-07T03:00:00","03:00",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384761_6651316261","Paris-Amiens",">","Creil","Longueau",2020,2020,7,48,"2020-02-10T22:55:00","22:55","2020-11-27T04:15:00","04:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"110 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384761_6651314661","Paris-Amiens",">","Creil","Longueau",2019,2020,52,50,"2019-12-23T01:45:00","01:45","2020-12-07T04:20:00","04:20",76,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384761_6651318661","Paris-Amiens",">","Creil","Longueau",2019,2020,52,50,"2019-12-23T01:20:00","01:20","2020-12-07T04:05:00","04:05",72,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384761_6651321861","Paris-Amiens",">","Creil","Longueau",2019,2020,52,50,"2019-12-23T02:15:00","02:15","2020-12-07T05:40:00","05:40",99,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384761_6651315461","Paris-Amiens",">","Creil","Longueau",2019,2020,51,50,"2019-12-16T11:04:00","11:04","2020-12-11T11:51:00","11:51",2963,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384761_6651321061","Paris-Amiens",">","Creil","Longueau",2020,2020,7,48,"2020-02-10T23:10:00","23:10","2020-11-27T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"110 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384761_6651319461","Paris-Amiens",">","Creil","Longueau",2019,2020,52,50,"2019-12-23T01:45:00","01:45","2020-12-07T05:15:00","05:15",92,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384761_6651317861","Paris-Amiens",">","Creil","Longueau",2019,2020,51,50,"2019-12-16T12:35:00","12:35","2020-12-11T13:56:00","13:56",3484,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384761_6651320261","Paris-Amiens",">","Creil","Longueau",2019,2020,51,50,"2019-12-16T10:50:00","10:50","2020-12-11T11:30:00","11:30",2875,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384761_6651317061","Paris-Amiens",">","Creil","Longueau",2019,2020,51,50,"2019-12-16T14:58:00","14:58","2020-12-11T16:03:00","16:03",4013,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384561_6651247461","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2019,2020,51,50,"2019-12-16T15:47:00","15:47","2020-12-11T16:21:00","16:21",4088,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384561_6651245061","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2019,2020,52,50,"2019-12-23T00:30:00","00:30","2020-12-07T03:30:00","03:30",55,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384561_6651246661","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2020,2020,6,6,"2020-02-03T09:30:00","09:30","2020-02-07T13:30:00","13:30",58,"DAY",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384561_6651245861","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2019,2020,51,50,"2019-12-16T15:26:00","15:26","2020-12-11T16:17:00","16:17",4071,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386561_6651323861","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2019,2020,51,50,"2019-12-16T11:30:00","11:30","2020-12-11T12:37:00","12:37",3155,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386561_6651323061","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2019,2020,51,50,"2019-12-16T13:30:00","13:30","2020-12-11T14:24:00","14:24",3600,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386561_6651325461","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2019,2020,51,50,"2019-12-16T00:30:00","00:30","2020-12-07T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386561_6651326461","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2020,2020,7,48,"2020-02-10T11:00:00","11:00","2020-11-27T15:00:00","15:00",424,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386561_6651324661","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2020,2020,7,48,"2020-02-10T11:00:00","11:00","2020-11-27T15:00:00","15:00",424,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384861_6651157861","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2019,2020,52,44,"2019-12-29T23:10:00","23:10","2020-11-01T02:20:00","02:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384861_6651155461","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2019,2020,52,44,"2019-12-29T22:50:00","22:50","2020-11-01T01:40:00","01:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384861_6651158661","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2020,17,49,"2020-04-20T22:50:00","22:50","2020-12-04T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"81 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384861_6651157061","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2019,2020,51,50,"2019-12-16T14:21:00","14:21","2020-12-11T15:26:00","15:26",3859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384861_6651159461","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2019,2020,51,50,"2019-12-16T10:37:00","10:37","2020-12-11T11:31:00","11:31",2880,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384861_6651156261","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2020,17,49,"2020-04-20T22:50:00","22:50","2020-12-04T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"81 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651265661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T13:55:00","13:55","2020-12-11T14:38:00","14:38",3688,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651258461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T10:05:00","10:05","2020-12-11T11:20:00","11:20",2857,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651263261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T00:05:00","00:05","2020-11-30T03:10:00","03:10",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651264861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T01:30:00","01:30","2020-11-30T04:25:00","04:25",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651255861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T13:38:00","13:38","2020-12-11T14:27:00","14:27",3613,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651261661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T00:10:00","00:10","2020-11-30T03:20:00","03:20",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651260061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T01:20:00","01:20","2020-11-30T04:05:00","04:05",72,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651264061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T10:25:00","10:25","2020-12-11T11:37:00","11:37",2905,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651262461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T00:35:00","00:35","2020-11-30T03:20:00","03:20",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651256661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,1,50,"2019-12-30T23:39:00","23:39","2020-12-11T04:59:00","04:59",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"140 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651259261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,49,"2019-12-16T00:20:00","00:20","2020-11-30T03:30:00","03:30",62,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651260861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T13:55:00","13:55","2020-12-11T14:38:00","14:38",3673,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388961_6651257661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2019,2020,51,50,"2019-12-16T09:58:00","09:58","2020-12-11T11:05:00","11:05",2783,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387061_6651180661","Paris-Busigny",">","Creil","LongueilSteMarie",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:10:00","03:10",164,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387061_6651178861","Paris-Busigny",">","Creil","LongueilSteMarie",2019,2020,1,50,"2019-12-31","00:00","2020-12-12T05:05:00","05:05",1092,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"215 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387061_6651181461","Paris-Busigny",">","Creil","LongueilSteMarie",2019,2020,51,50,"2019-12-16T01:35:00","01:35","2020-12-07T04:20:00","04:20",223,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387061_6651178061","Paris-Busigny",">","Creil","LongueilSteMarie",2019,2020,51,50,"2019-12-16T14:17:00","14:17","2020-12-11T15:02:00","15:02",3759,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387061_6651179861","Paris-Busigny",">","Creil","LongueilSteMarie",2019,2020,51,50,"2019-12-16T09:46:00","09:46","2020-12-11T10:57:00","10:57",2738,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385661_6651372661","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2019,2020,51,50,"2019-12-16T14:06:00","14:06","2020-12-11T14:56:00","14:56",3734,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385661_6651369261","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2019,2020,51,37,"2019-12-22T23:00:00","23:00","2020-09-13T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385661_6651371861","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2019,2020,51,50,"2019-12-16T09:55:00","09:55","2020-12-11T11:05:00","11:05",2772,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385661_6651370061","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2019,2020,52,38,"2019-12-23","00:00","2020-09-14T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385661_6651370861","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2020,2020,7,48,"2020-02-10T22:30:00","22:30","2020-11-27T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388861_6651204661","Paris-Busigny",">","Ormoy","Longueil",2019,2020,51,50,"2019-12-16T23:22:00","23:22","2020-12-11T05:10:00","05:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"180 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388861_6651203861","Paris-Busigny",">","Ormoy","Longueil",2019,2020,51,50,"2019-12-16T10:57:00","10:57","2020-12-11T12:33:00","12:33",3139,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388861_6651205661","Paris-Busigny",">","Ormoy","Longueil",2019,2020,51,50,"2019-12-16T14:20:00","14:20","2020-12-11T16:00:00","16:00",4001,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388161_6651249461","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2020,15,50,"2020-04-06T11:09:00","11:09","2020-12-11T14:58:00","14:58",482,"DAY",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388161_6651252661","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2019,2020,51,50,"2019-12-16T11:02:00","11:02","2020-12-11T12:20:00","12:20",3084,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388161_6651251061","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2019,2020,51,50,"2019-12-16T00:46:00","00:46","2020-12-07T04:00:00","04:00",203,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388161_6651251861","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2019,2020,51,50,"2019-12-16T14:10:00","14:10","2020-12-11T14:54:00","14:54",3725,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388161_6651250261","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2020,15,50,"2020-04-06T10:47:00","10:47","2020-12-11T14:58:00","14:58",483,"DAY",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
[null,"SNCF Réseau","6651388161_6651248661","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2019,2020,51,50,"2019-12-16T00:25:00","00:25","2020-12-07T03:00:00","03:00",152,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386661_6651301861","Amiens-Douai",">","Arras","Bif d'Agny",2019,2020,51,50,"2019-12-16T09:46:00","09:46","2020-12-11T10:50:00","10:50",2709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385361_6651360661","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2020,2020,5,5,"2020-01-27T09:30:00","09:30","2020-01-31T13:30:00","13:30",58,"DAY",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385361_6651361461","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2019,2020,52,50,"2019-12-23T01:35:00","01:35","2020-12-07T05:10:00","05:10",81,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385361_6651363061","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2019,2020,51,50,"2019-12-16T09:08:00","09:08","2020-12-11T10:40:00","10:40",2668,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385361_6651362261","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2019,2020,51,50,"2019-12-16T09:40:00","09:40","2020-12-11T10:44:00","10:44",2684,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387761_6651186461","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2019,2020,51,50,"2019-12-16T11:23:00","11:23","2020-12-11T12:30:00","12:30",3126,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387761_6651183061","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2019,2020,51,50,"2019-12-16T00:30:00","00:30","2020-12-07T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387761_6651185661","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2019,2020,51,50,"2019-12-16T13:16:00","13:16","2020-12-11T14:08:00","14:08",3534,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387761_6651184061","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2020,2020,7,48,"2020-02-10T11:00:00","11:00","2020-11-27T15:00:00","15:00",424,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387761_6651184861","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2020,2020,7,48,"2020-02-10T11:00:00","11:00","2020-11-27T15:00:00","15:00",424,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389561_6651209461","Boulogne-Calais",">","Marquise","Calais",2019,2020,51,50,"2019-12-16T14:20:00","14:20","2020-12-11T15:30:00","15:30",3876,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389561_6651207061","Boulogne-Calais",">","Marquise","Calais",2020,2020,2,50,"2020-01-06T23:08:00","23:08","2020-12-11T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389561_6651208661","Boulogne-Calais",">","Marquise","Calais",2020,2020,2,50,"2020-01-06T23:08:00","23:08","2020-12-11T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389561_6651210261","Boulogne-Calais",">","Marquise","Calais",2019,2020,51,41,"2019-12-16","00:00","2020-10-05T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389561_6651207861","Boulogne-Calais",">","Marquise","Calais",2019,2020,51,50,"2019-12-16T11:00:00","11:00","2020-12-11T11:55:00","11:55",2980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389561_6651211061","Boulogne-Calais",">","Marquise","Calais",2019,2020,51,41,"2019-12-16","00:00","2020-10-05T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651234861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,50,"2019-12-16T14:34:00","14:34","2020-12-11T15:24:00","15:24",3850,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651230661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2020,4,49,"2020-01-20T23:17:00","23:17","2020-12-04T05:15:00","05:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651233261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,50,"2019-12-16T14:24:00","14:24","2020-12-11T15:19:00","15:19",3830,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651231661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16T00:30:00","00:30","2020-11-30T03:30:00","03:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651238061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16T00:35:00","00:35","2020-11-30T03:15:00","03:15",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651229861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16","00:00","2020-11-30T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651237261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,50,"2019-12-16T14:51:00","14:51","2020-12-11T15:44:00","15:44",3934,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651229061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,50,"2019-12-16T13:30:00","13:30","2020-12-11T14:50:00","14:50",3709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651235661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16T00:30:00","00:30","2020-11-30T03:30:00","03:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651234061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16T00:30:00","00:30","2020-11-30T03:30:00","03:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651236461","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,50,"2019-12-16T11:10:00","11:10","2020-12-11T12:21:00","12:21",3088,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387561_6651232461","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2019,2020,51,49,"2019-12-16T00:30:00","00:30","2020-11-30T03:30:00","03:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386761_6651354261","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2019,2020,52,44,"2019-12-29T23:35:00","23:35","2020-11-01T02:45:00","02:45",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386761_6651356061","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2019,2020,51,50,"2019-12-16T13:48:00","13:48","2020-12-11T15:10:00","15:10",3793,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386761_6651355061","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2019,2020,51,49,"2019-12-16T22:50:00","22:50","2020-12-04T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386761_6651353461","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2019,2020,52,44,"2019-12-29T23:15:00","23:15","2020-11-01T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386761_6651352661","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2019,2020,51,50,"2019-12-16T09:55:00","09:55","2020-12-11T10:43:00","10:43",2679,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385761_6651337661","Boulogne-Calais",">","Boulogne","Marquise",2020,2020,2,50,"2020-01-06T22:03:00","22:03","2020-12-11T04:38:00","04:38",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385761_6651340061","Boulogne-Calais",">","Boulogne","Marquise",2019,2020,51,41,"2019-12-16","00:00","2020-10-05T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385761_6651338461","Boulogne-Calais",">","Boulogne","Marquise",2019,2020,51,41,"2019-12-16","00:00","2020-10-05T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385761_6651336061","Boulogne-Calais",">","Boulogne","Marquise",2020,2020,2,50,"2020-01-06T22:15:00","22:15","2020-12-11T04:19:00","04:19",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385761_6651339261","Boulogne-Calais",">","Boulogne","Marquise",2019,2020,51,50,"2019-12-16T14:15:00","14:15","2020-12-11T15:35:00","15:35",3897,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651385761_6651336861","Boulogne-Calais",">","Boulogne","Marquise",2019,2020,51,50,"2019-12-16T11:05:00","11:05","2020-12-11T11:55:00","11:55",2979,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384961_6651381661","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,52,42,"2019-12-29T21:28:00","21:28","2020-10-18T01:08:00","01:08",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384961_6651379261","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T09:00:00","09:00","2020-12-11T09:46:00","09:46",2442,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384961_6651382461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T09:17:00","09:17","2020-12-11T10:00:00","10:00",2500,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384961_6651378461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T11:00:00","11:00","2020-12-11T12:15:00","12:15",3063,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384961_6651380861","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T09:32:00","09:32","2020-12-11T10:17:00","10:17",2571,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384961_6651375061","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,52,42,"2019-12-29T21:27:00","21:27","2020-10-18T23:57:00","23:57",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384961_6651380061","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T11:15:00","11:15","2020-12-11T12:25:00","12:25",3105,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384961_6651375861","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2020,10,42,"2020-03-02T10:00:00","10:00","2020-10-16T14:00:00","14:00",270,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
[null,"SNCF Réseau","6651384961_6651374261","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2019,2020,51,50,"2019-12-16T10:50:00","10:50","2020-12-11T12:00:00","12:00",3001,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389161_6651239261","Amiens-Douai",">","Arras","Douai",2019,2020,51,50,"2019-12-16T09:50:00","09:50","2020-12-11T10:56:00","10:56",2734,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389161_6651240861","Amiens-Douai",">","Arras","Douai",2020,2020,9,42,"2020-02-24T23:00:00","23:00","2020-10-16T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"28 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389161_6651242461","Amiens-Douai",">","Arras","Douai",2019,2020,52,38,"2019-12-23T01:30:00","01:30","2020-09-14T04:30:00","04:30",25,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389161_6651243261","Amiens-Douai",">","Arras","Douai",2019,2020,51,50,"2019-12-16T14:29:00","14:29","2020-12-11T15:20:00","15:20",3834,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389161_6651241661","Amiens-Douai",">","Arras","Douai",2019,2020,52,38,"2019-12-23T00:35:00","00:35","2020-09-14T03:20:00","03:20",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6651389161_6651240061","Amiens-Douai",">","Arras","Douai",2020,2020,9,42,"2020-02-24T22:50:00","22:50","2020-10-16T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"28 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387361_6651294861","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2019,2020,51,45,"2019-12-16","00:00","2020-11-02T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387361_6651296461","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2019,2020,51,45,"2019-12-16","00:00","2020-11-02T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387361_6651298061","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2020,2020,17,49,"2020-04-20T22:50:00","22:50","2020-12-04T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387361_6651295661","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2019,2020,51,50,"2019-12-16T09:36:00","09:36","2020-12-11T10:43:00","10:43",2680,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651387361_6651297261","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2019,2020,51,50,"2019-12-16T14:20:00","14:20","2020-12-11T15:09:00","15:09",3788,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6651386861_6651284061","Amiens-Douai","<","Arras","Bif de l'arbre Robert",2019,2020,51,50,"2019-12-16T15:20:00","15:20","2020-12-11T16:17:00","16:17",4071,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256861_6650095561","Calais-Lille-Aulnoye",">","Lille Lambersart",null,2019,2020,51,50,"2019-12-16T10:19:00","10:19","2020-12-11T11:15:00","11:15",2813,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256861_6650094761","Calais-Lille-Aulnoye",">","Lille Lambersart",null,2019,2020,51,50,"2019-12-16T11:05:00","11:05","2020-12-11T12:00:00","12:00",3000,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256461_6650167761","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2019,2020,51,50,"2019-12-16T11:36:00","11:36","2020-12-11T12:13:00","12:13",3054,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256461_6650170361","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2019,2020,51,50,"2019-12-16T11:22:00","11:22","2020-12-11T12:48:00","12:48",3201,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256461_6650169361","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2020,2020,15,49,"2020-04-06T23:05:00","23:05","2020-12-04T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"42 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256461_6650171161","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2019,2020,51,50,"2019-12-16T01:10:00","01:10","2020-12-07T04:10:00","04:10",215,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256461_6650168561","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",156,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257261_6650182561","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2020,11,42,"2020-03-09T22:45:00","22:45","2020-10-16T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257261_6650183361","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2019,2020,51,43,"2019-12-16T01:00:00","01:00","2020-10-19T03:30:00","03:30",58,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257261_6650185761","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2019,2020,51,50,"2019-12-16T10:12:00","10:12","2020-12-11T10:53:00","10:53",2721,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257261_6650186561","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2019,2020,51,50,"2019-12-16T11:05:00","11:05","2020-12-11T12:28:00","12:28",3118,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257261_6650184961","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2020,11,42,"2020-03-09T22:12:00","22:12","2020-10-16T04:40:00","04:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257261_6650184161","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2019,2020,51,43,"2019-12-16T00:06:00","00:06","2020-10-19T03:30:00","03:30",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255361_6650151561","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2019,2020,51,50,"2019-12-16T13:43:00","13:43","2020-12-11T14:09:00","14:09",3537,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255361_6650153961","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2020,11,42,"2020-03-09T23:04:00","23:04","2020-10-16T04:23:00","04:23",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"107 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255361_6650152361","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2019,2020,51,50,"2019-12-16T10:15:00","10:15","2020-12-11T11:50:00","11:50",2959,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255361_6650153161","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2019,2020,52,42,"2019-12-29T23:00:00","23:00","2020-10-18T02:32:00","02:32",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255361_6650154761","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2019,2020,51,43,"2019-12-16T01:36:00","01:36","2020-10-19T04:13:00","04:13",70,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255361_6650150761","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2020,11,42,"2020-03-09T22:21:00","22:21","2020-10-16T05:35:00","05:35",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"107 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256261_6650180161","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2019,2020,51,50,"2019-12-16T13:45:00","13:45","2020-12-11T14:18:00","14:18",3575,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256261_6650176961","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2020,10,42,"2020-03-02T10:21:00","10:21","2020-10-16T15:14:00","15:14",431,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256261_6650180961","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2019,2020,51,50,"2019-12-16T01:10:00","01:10","2020-12-07T03:45:00","03:45",193,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256261_6650178561","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2020,10,42,"2020-03-02T08:50:00","08:50","2020-10-16T15:05:00","15:05",428,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256261_6650177761","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2019,2020,51,49,"2019-12-22T23:00:00","23:00","2020-12-06T02:28:00","02:28",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256261_6650179361","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2019,2020,51,50,"2019-12-16T10:37:00","10:37","2020-12-11T12:05:00","12:05",3022,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255961_6650060361","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2019,2020,52,50,"2019-12-23","00:00","2020-12-07T03:00:00","03:00",54,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255961_6650056961","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2019,2020,51,50,"2019-12-16T13:57:00","13:57","2020-12-11T14:37:00","14:37",3654,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255961_6650058561","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2020,2020,9,49,"2020-02-24T23:00:00","23:00","2020-12-04T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255961_6650057761","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2019,2020,52,50,"2019-12-23","00:00","2020-12-07T03:10:00","03:10",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255961_6650059561","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2019,2020,51,50,"2019-12-16T14:30:00","14:30","2020-12-11T15:50:00","15:50",3959,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255861_6650120361","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,1,49,"2020-01-05T23:40:00","23:40","2020-12-06T02:40:00","02:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255861_6650118761","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,1,49,"2020-01-05T23:50:00","23:50","2020-12-06T02:50:00","02:50",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255861_6650113961","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,1,49,"2020-01-05T23:50:00","23:50","2020-12-06T02:50:00","02:50",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255861_6650114761","Aulnoye-Longuyon",">","Mohon","Sedan",2019,2020,51,50,"2019-12-16T13:24:00","13:24","2020-12-11T14:11:00","14:11",3404,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255861_6650116361","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,9,42,"2020-02-24T10:25:00","10:25","2020-10-16T14:15:00","14:15",702,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255861_6650115561","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,1,49,"2020-01-05T23:40:00","23:40","2020-12-06T02:40:00","02:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255861_6650117161","Aulnoye-Longuyon",">","Mohon","Sedan",2019,2020,51,50,"2019-12-16T13:36:00","13:36","2020-12-11T14:51:00","14:51",3565,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255861_6650117961","Aulnoye-Longuyon",">","Mohon","Sedan",2019,2020,51,50,"2019-12-16T13:25:00","13:25","2020-12-11T14:24:00","14:24",3456,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255861_6650119561","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2020,9,42,"2020-02-24T10:07:00","10:07","2020-10-16T14:15:00","14:15",702,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255761_6650163761","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2020,1,49,"2020-01-05T23:00:00","23:00","2020-12-06T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255761_6650156561","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T13:15:00","13:15","2020-12-11T13:45:00","13:45",3300,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255761_6650162961","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2020,1,49,"2020-01-05T23:00:00","23:00","2020-12-06T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255761_6650159761","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2020,9,42,"2020-02-24T09:15:00","09:15","2020-10-16T13:30:00","13:30",868,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255761_6650158161","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2020,9,42,"2020-02-24T10:15:00","10:15","2020-10-16T16:00:00","16:00",1029,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255761_6650161361","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T12:45:00","12:45","2020-12-11T14:15:00","14:15",3421,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255761_6650157361","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T00:10:00","00:10","2020-12-07T03:10:00","03:10",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255761_6650162161","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T12:45:00","12:45","2020-12-11T13:30:00","13:30",3375,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255761_6650160561","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T00:10:00","00:10","2020-12-07T03:10:00","03:10",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255761_6650158961","Aulnoye-Longuyon",">","Sedan","Longuyon",2019,2020,51,50,"2019-12-16T13:00:00","13:00","2020-12-11T14:15:00","14:15",3563,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257061_6650190161","Aulnoye-Longuyon",">","Tournes","Charleville",2019,2020,51,50,"2019-12-16T13:35:00","13:35","2020-12-11T14:40:00","14:40",3521,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257061_6650189361","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2020,1,49,"2020-01-05T23:55:00","23:55","2020-12-06T02:55:00","02:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257061_6650188561","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2020,1,49,"2020-01-05T23:00:00","23:00","2020-12-06T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257061_6650187761","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2020,9,44,"2020-02-24T10:00:00","10:00","2020-10-30T14:54:00","14:54",809,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257061_6650191761","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2020,9,44,"2020-02-24T09:15:00","09:15","2020-10-30T14:20:00","14:20",779,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257061_6650190961","Aulnoye-Longuyon",">","Tournes","Charleville",2019,2020,51,50,"2019-12-16T12:25:00","12:25","2020-12-11T13:21:00","13:21",3204,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255061_6650134761","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,50,"2019-12-16T10:38:00","10:38","2020-12-11T11:48:00","11:48",2951,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255061_6650132961","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2020,7,48,"2020-02-10T23:00:00","23:00","2020-11-27T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255061_6650137961","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,50,"2019-12-16T13:07:00","13:07","2020-12-11T13:57:00","13:57",3488,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255061_6650133961","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,49,"2019-12-22T23:50:00","23:50","2020-12-06T03:15:00","03:15",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255061_6650135561","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,49,"2019-12-22T00:15:00","00:15","2020-12-06T02:45:00","02:45",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255061_6650136361","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,50,"2019-12-16T10:11:00","10:11","2020-12-11T11:38:00","11:38",2909,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255061_6650137161","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2019,2020,51,50,"2019-12-16T13:51:00","13:51","2020-12-11T14:27:00","14:27",3613,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256761_6650065761","Aulnoye-Longuyon",">","Hirson","Liart",2019,2020,51,50,"2019-12-16T11:45:00","11:45","2020-12-11T13:05:00","13:05",3272,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256761_6650064161","Aulnoye-Longuyon",">","Hirson","Liart",2020,2020,9,44,"2020-02-24T09:10:00","09:10","2020-10-30T14:35:00","14:35",938,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256761_6650064961","Aulnoye-Longuyon",">","Hirson","Liart",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:20:00","03:20",173,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256761_6650061761","Aulnoye-Longuyon",">","Hirson","Liart",2019,2020,51,50,"2019-12-16T00:30:00","00:30","2020-12-07T03:15:00","03:15",168,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256761_6650062561","Aulnoye-Longuyon",">","Hirson","Liart",2020,2020,9,44,"2020-02-24T09:30:00","09:30","2020-10-30T14:37:00","14:37",940,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256761_6650063361","Aulnoye-Longuyon",">","Hirson","Liart",2019,2020,51,50,"2019-12-16T14:25:00","14:25","2020-12-11T15:00:00","15:00",3750,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255561_6650140161","Aulnoye-Longuyon",">","Aulnoye","Hirson",2019,2020,51,49,"2019-12-22T23:30:00","23:30","2020-12-06T03:00:00","03:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255561_6650141761","Aulnoye-Longuyon",">","Aulnoye","Hirson",2019,2020,51,50,"2019-12-16T13:15:00","13:15","2020-12-11T13:45:00","13:45",3438,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255561_6650139361","Aulnoye-Longuyon",">","Aulnoye","Hirson",2019,2020,51,50,"2019-12-16T00:55:00","00:55","2020-12-07T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255561_6650142561","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2020,10,44,"2020-03-02T09:59:00","09:59","2020-10-30T15:25:00","15:25",437,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255561_6650143361","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2020,10,44,"2020-03-02T09:14:00","09:14","2020-10-30T15:54:00","15:54",451,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255561_6650144161","Aulnoye-Longuyon",">","Aulnoye","Hirson",2019,2020,51,50,"2019-12-16T10:59:00","10:59","2020-12-11T12:20:00","12:20",3084,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255561_6650140961","Aulnoye-Longuyon",">","Aulnoye","Hirson",2019,2020,51,50,"2019-12-16T11:20:00","11:20","2020-12-11T12:32:00","12:32",3134,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255461_6650175761","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2019,2020,51,50,"2019-12-16T14:20:00","14:20","2020-12-11T15:25:00","15:25",3855,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255461_6650172361","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2020,2020,7,49,"2020-02-10","00:00","2020-11-30T03:10:00","03:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255461_6650173161","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2019,2020,51,50,"2019-12-16T14:04:00","14:04","2020-12-11T14:55:00","14:55",3730,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255461_6650174761","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2020,2020,14,50,"2020-03-30T23:30:00","23:30","2020-12-11T05:15:00","05:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
[null,"SNCF Réseau","6650255461_6650173961","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2020,2020,7,49,"2020-02-10","00:00","2020-11-30T03:00:00","03:00",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257561_6650089961","Aulnoye-Longuyon",">","Liart","Tournes",2019,2020,51,50,"2019-12-16T14:00:00","14:00","2020-12-11T14:40:00","14:40",3520,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257561_6650093161","Aulnoye-Longuyon",">","Liart","Tournes",2020,2020,1,49,"2020-01-05T23:55:00","23:55","2020-12-06T02:55:00","02:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257561_6650090761","Aulnoye-Longuyon",">","Liart","Tournes",2020,2020,9,44,"2020-02-24T09:37:00","09:37","2020-10-30T14:20:00","14:20",778,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257561_6650091561","Aulnoye-Longuyon",">","Liart","Tournes",2020,2020,9,44,"2020-02-24T09:35:00","09:35","2020-10-30T14:54:00","14:54",809,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257561_6650089161","Aulnoye-Longuyon",">","Liart","Tournes",2020,2020,1,49,"2020-01-05T23:00:00","23:00","2020-12-06T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
[null,"SNCF Réseau","6650257561_6650092361","Aulnoye-Longuyon",">","Liart","Tournes",2019,2020,51,50,"2019-12-16T12:05:00","12:05","2020-12-11T13:21:00","13:21",3205,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256661_6650200361","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2019,2020,51,50,"2019-12-16T09:52:00","09:52","2020-12-11T11:00:00","11:00",2751,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256661_6650201961","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2019,2020,51,50,"2019-12-16T14:25:00","14:25","2020-12-11T15:08:00","15:08",3784,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256661_6650202761","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2019,2020,51,41,"2019-12-16T00:20:00","00:20","2020-10-05T03:00:00","03:00",41,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256661_6650199361","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2020,2020,12,50,"2020-03-16T22:43:00","22:43","2020-12-11T04:43:00","04:43",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
[null,"SNCF Réseau","6650256661_6650201161","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2019,2020,51,41,"2019-12-16T01:00:00","01:00","2020-10-05T04:00:00","04:00",55,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6648859661_6648654361","Longuyon-Metz-Sarrebourg",">","Hauconcourt","Woippy",2020,2020,8,47,"2020-02-17T10:00:00","10:00","2020-11-20T18:00:00","18:00",170,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
[null,"SNCF Réseau","6648854861_6648622361","Longuyon-Metz-Sarrebourg",">","Longwy","Saulnes",2020,2020,31,31,"2020-07-27T08:00:00","08:00","2020-07-31T16:00:00","16:00",0,"ALL DAY",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
[null,"SNCF Réseau","6648854761_6648652161","Sarrebourg-Basel",">","Colmar","NeufBrisach",2020,2020,36,37,"2020-09-04T11:40:00","11:40","2020-09-11T15:40:00","15:40",19,"DAY",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
[null,"SNCF Réseau","6648854761_6648653161","Sarrebourg-Basel",">","Colmar","NeufBrisach",2020,2020,36,37,"2020-08-31T12:00:00","12:00","2020-09-10T20:00:00","20:00",148,"DAY",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
[null,"SNCF Réseau","6648863061_6648722761","Sarrebourg-Basel",">","Mulhouse","Chalampe",2019,2020,51,50,"2019-12-16T08:52:00","08:52","2020-12-11T09:52:00","09:52",2319,"DAY",null,null,null,null,null,null,null,null,null,null,null,"236 jours dans le régime binaire"]
[null,"SNCF Réseau","6648863061_6648723561","Sarrebourg-Basel",">","Mulhouse","Chalampe",2020,2020,17,43,"2020-04-20T22:00:00","22:00","2020-10-23T04:00:00","04:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556361_6648235361","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556361_6648233761","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556361_6648236961","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2019,2020,51,46,"2019-12-16T11:28:00","11:28","2020-11-13T12:29:00","12:29",1898,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556361_6648236161","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2019,2020,51,50,"2019-12-16T09:17:00","09:17","2020-12-11T10:14:00","10:14",2201,"DAY",null,null,null,null,null,null,null,null,null,null,null,"216 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556361_6648237761","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556361_6648234561","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2019,2020,51,46,"2019-12-16T14:21:00","14:21","2020-11-13T15:20:00","15:20",2331,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558961_6648113361","Dijon-Toul",">","Dijon","Is sur Tille",2019,2020,51,50,"2019-12-16T01:10:00","01:10","2020-12-07T03:55:00","03:55",194,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558961_6648111361","Dijon-Toul",">","Dijon","Is sur Tille",2019,2020,51,50,"2019-12-16T12:35:00","12:35","2020-12-11T14:01:00","14:01",2272,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558961_6648110361","Dijon-Toul",">","Dijon","Is sur Tille",2019,2020,51,50,"2019-12-16T00:05:00","00:05","2020-12-07T03:29:00","03:29",174,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558961_6648112361","Dijon-Toul",">","Dijon","Is sur Tille",2020,2020,9,48,"2020-02-24T12:28:00","12:28","2020-11-27T16:48:00","16:48",1465,"DAY",null,null,null,null,null,null,null,null,null,null,null,"88 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558961_6648109361","Dijon-Toul",">","Dijon","Is sur Tille",2019,2020,51,50,"2019-12-16T11:14:00","11:14","2020-12-11T12:35:00","12:35",2039,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558961_6648114361","Dijon-Toul",">","Dijon","Is sur Tille",2020,2020,9,48,"2020-02-24T11:26:00","11:26","2020-11-27T14:58:00","14:58",1305,"DAY",null,null,null,null,null,null,null,null,null,null,null,"88 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555861_6648175361","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2020,2020,6,37,"2020-02-03T23:26:00","23:26","2020-09-11T05:26:00","05:26",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555861_6648177961","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2019,2020,51,3,"2019-12-22T23:56:00","23:56","2020-01-19T02:56:00","02:56",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555861_6648176361","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2019,2020,51,50,"2019-12-16T13:35:00","13:35","2020-12-11T14:38:00","14:38",3630,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555861_6648174561","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2019,2020,51,3,"2019-12-22T23:56:00","23:56","2020-01-19T02:56:00","02:56",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555861_6648177161","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2019,2020,51,50,"2019-12-16T09:25:00","09:25","2020-12-11T10:22:00","10:22",2571,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555061_6648169961","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2020,2020,2,36,"2020-01-06","00:00","2020-08-31T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555061_6648171561","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2020,2020,11,47,"2020-03-09T10:10:00","10:10","2020-11-20T16:10:00","16:10",1105,"DAY",null,null,null,null,null,null,null,null,null,null,null,"69 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555061_6648172561","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2019,2020,51,50,"2019-12-16T12:17:00","12:17","2020-12-11T12:49:00","12:49",3179,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555061_6648173361","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2020,2020,2,36,"2020-01-06T00:30:00","00:30","2020-08-31T03:30:00","03:30",38,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555061_6648170761","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2019,2020,51,50,"2019-12-16T14:05:00","14:05","2020-12-11T15:32:00","15:32",3853,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556761_6648377761","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2019,2020,1,32,"2019-12-30T00:15:00","00:15","2020-08-03T03:00:00","03:00",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556761_6648376161","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2019,2020,51,50,"2019-12-16T10:51:00","10:51","2020-12-11T11:41:00","11:41",2898,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556761_6648375361","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2019,2020,52,31,"2019-12-29T22:45:00","22:45","2020-08-02T02:01:00","02:01",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556761_6648376961","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2019,2020,51,50,"2019-12-16T14:07:00","14:07","2020-12-11T15:17:00","15:17",3791,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556761_6648374361","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2020,2020,9,42,"2020-02-24T23:00:00","23:00","2020-10-16T05:40:00","05:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"54 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557661_6648166961","Lerouville-Nancy",">","Lerouville","Toul",2020,2020,4,48,"2020-01-20T23:00:00","23:00","2020-11-27T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"104 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557661_6648166161","Lerouville-Nancy",">","Lerouville","Toul",2019,2020,51,50,"2019-12-16T10:40:00","10:40","2020-12-11T11:56:00","11:56",2984,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557661_6648167961","Lerouville-Nancy",">","Lerouville","Toul",2019,2020,51,50,"2019-12-16T15:15:00","15:15","2020-12-11T16:00:00","16:00",4000,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557661_6648168761","Lerouville-Nancy",">","Lerouville","Toul",2019,2019,51,52,"2019-12-16T00:40:00","00:40","2019-12-23T03:20:00","03:20",6,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557661_6648165361","Lerouville-Nancy",">","Lerouville","Toul",2019,2019,51,51,"2019-12-22T22:40:00","22:40","2019-12-22T02:01:00","02:01",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557761_6648181161","Longuyon-Metz-Sarrebourg","<","Metz sablon via MetzVille",null,2020,2020,4,37,"2020-01-20T23:30:00","23:30","2020-09-11T05:30:00","05:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648303161","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,9,48,"2020-02-25T11:30:00","11:30","2020-11-27T15:30:00","15:30",639,"DAY",null,null,null,null,null,null,null,null,null,null,null,"42 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648296761","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2019,2020,51,46,"2019-12-16T14:15:00","14:15","2020-11-13T15:05:00","15:05",2368,"DAY",null,null,null,null,null,null,null,null,null,null,null,"158 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648303961","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,3,44,"2020-01-13T09:30:00","09:30","2020-10-26T15:30:00","15:30",130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648299161","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2019,2020,51,46,"2019-12-16T11:37:00","11:37","2020-11-13T12:44:00","12:44",2000,"DAY",null,null,null,null,null,null,null,null,null,null,null,"158 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648299961","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,3,44,"2020-01-14T11:30:00","11:30","2020-10-30T15:30:00","15:30",608,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648306361","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2019,2020,51,50,"2019-12-16T09:09:00","09:09","2020-12-11T10:07:00","10:07",1730,"DAY",null,null,null,null,null,null,null,null,null,null,null,"172 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648300761","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2019,2020,51,50,"2019-12-16T13:51:00","13:51","2020-12-11T14:53:00","14:53",2040,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648298361","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,2,50,"2020-01-06","00:00","2020-12-07T03:00:00","03:00",36,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648297561","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,3,44,"2020-01-14T11:30:00","11:30","2020-10-30T15:30:00","15:30",608,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648304761","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,9,48,"2020-02-25T11:30:00","11:30","2020-11-27T15:30:00","15:30",639,"DAY",null,null,null,null,null,null,null,null,null,null,null,"42 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648301561","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,9,48,"2020-02-24T09:30:00","09:30","2020-11-23T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648305561","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,9,48,"2020-02-24T09:30:00","09:30","2020-11-23T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554561_6648302361","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2020,3,44,"2020-01-13T09:30:00","09:30","2020-10-26T15:30:00","15:30",130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648331161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",531,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648336761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648340761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648335961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648334361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648339161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,50,"2019-12-16T13:38:00","13:38","2020-12-11T14:41:00","14:41",2012,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648331961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,46,"2019-12-16T11:23:00","11:23","2020-11-13T12:27:00","12:27",1893,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648341561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",531,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648338361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,46,"2019-12-16T14:30:00","14:30","2020-11-13T15:25:00","15:25",2344,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648337561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,5,46,"2020-01-28T11:30:00","11:30","2020-11-13T15:30:00","15:30",670,"DAY",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648332761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648339961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,2,36,"2020-01-06","00:00","2020-08-31T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648333561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,2,36,"2020-01-06","00:00","2020-08-31T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648335161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558261_6648330361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2019,2020,51,50,"2019-12-16T09:21:00","09:21","2020-12-11T10:19:00","10:19",2219,"DAY",null,null,null,null,null,null,null,null,null,null,null,"216 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557961_6648265961","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2020,2,38,"2020-01-06T23:05:00","23:05","2020-09-18T04:55:00","04:55",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557961_6648263561","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2019,2020,51,3,"2019-12-22T23:04:00","23:04","2020-01-19T01:55:00","01:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557961_6648265161","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2019,2020,51,4,"2019-12-16","00:00","2020-01-20T03:20:00","03:20",13,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557961_6648266761","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2019,2020,51,50,"2019-12-16T14:36:00","14:36","2020-12-11T15:26:00","15:26",3859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557961_6648264361","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2020,2,38,"2020-01-06T23:20:00","23:20","2020-09-18T05:30:00","05:30",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557961_6648262761","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2019,2020,51,50,"2019-12-16T09:36:00","09:36","2020-12-11T10:37:00","10:37",2655,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554261_6648075961","Lerouville-Nancy",">","Toul","Frouard",2020,2020,6,42,"2020-02-03T23:00:00","23:00","2020-10-16T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554261_6648078561","Lerouville-Nancy",">","Toul","Frouard",2020,2020,2,3,"2020-01-12T22:55:00","22:55","2020-01-19T02:06:00","02:06",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554261_6648075161","Lerouville-Nancy",">","Toul","Frouard",2019,2020,51,50,"2019-12-16T14:59:00","14:59","2020-12-11T15:42:00","15:42",3925,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554261_6648077761","Lerouville-Nancy",">","Toul","Frouard",2019,2020,51,50,"2019-12-16T08:58:00","08:58","2020-12-11T10:16:00","10:16",2567,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554261_6648076961","Lerouville-Nancy",">","Toul","Frouard",2020,2020,2,3,"2020-01-12T22:54:00","22:54","2020-01-19T01:40:00","01:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558661_6648015361","Dijon-Toul",">","NeufChateau","Toul",2019,2020,51,49,"2019-12-22T23:52:00","23:52","2020-12-06T01:34:00","01:34",23,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558661_6648016161","Dijon-Toul",">","NeufChateau","Toul",2019,2020,51,50,"2019-12-16T01:46:00","01:46","2020-12-07T05:12:00","05:12",91,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558661_6648012961","Dijon-Toul",">","NeufChateau","Toul",2020,2020,7,11,"2020-02-10T09:17:00","09:17","2020-03-13T13:15:00","13:15",321,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558661_6648016961","Dijon-Toul",">","NeufChateau","Toul",2019,2020,51,50,"2019-12-16T14:15:00","14:15","2020-12-11T15:44:00","15:44",3934,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558661_6648014561","Dijon-Toul",">","NeufChateau","Toul",2019,2020,51,50,"2019-12-16T10:08:00","10:08","2020-12-11T10:34:00","10:34",2642,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558661_6648013761","Dijon-Toul",">","NeufChateau","Toul",2020,2020,7,11,"2020-02-10T14:15:00","14:15","2020-03-13T19:41:00","19:41",477,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558561_6648362961","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2020,2020,9,48,"2020-02-24T22:55:00","22:55","2020-11-27T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"121 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558561_6648363761","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2020,2020,9,48,"2020-02-24T23:40:00","23:40","2020-11-27T05:10:00","05:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"121 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558561_6648364561","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2019,2020,51,50,"2019-12-16T14:05:00","14:05","2020-12-11T15:55:00","15:55",3949,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558561_6648365361","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2019,2020,51,50,"2019-12-16T11:30:00","11:30","2020-12-11T11:55:00","11:55",2955,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648099961","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",531,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648094361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2019,2020,51,46,"2019-12-16T14:20:00","14:20","2020-11-13T15:15:00","15:15",2303,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648099161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2019,2020,51,50,"2019-12-16T09:15:00","09:15","2020-12-11T10:11:00","10:11",2180,"DAY",null,null,null,null,null,null,null,null,null,null,null,"215 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648096761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,3,46,"2020-01-13T09:30:00","09:30","2020-11-09T15:30:00","15:30",254,"DAY",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648095961","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,3,46,"2020-01-13T09:30:00","09:30","2020-11-09T15:30:00","15:30",254,"DAY",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648095161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2019,2020,51,50,"2019-12-16T13:45:00","13:45","2020-12-11T14:49:00","14:49",2016,"DAY",null,null,null,null,null,null,null,null,null,null,null,"137 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648100761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,5,46,"2020-01-28T11:30:00","11:30","2020-11-13T15:30:00","15:30",500,"DAY",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648101561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,5,46,"2020-01-28T11:30:00","11:30","2020-11-13T15:30:00","15:30",500,"DAY",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648103161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648102361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",531,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648097561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
[null,"SNCF Réseau","6648560161_6648098361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2019,2020,51,46,"2019-12-16T11:30:00","11:30","2020-11-13T12:34:00","12:34",1898,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559761_6648251161","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2019,2019,51,52,"2019-12-22T23:00:00","23:00","2019-12-29T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"3 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559761_6648251961","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2019,2020,51,50,"2019-12-16T13:20:00","13:20","2020-12-11T13:40:00","13:40",3416,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559761_6648253561","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2020,2020,8,39,"2020-02-17T10:30:00","10:30","2020-09-25T16:30:00","16:30",1144,"DAY",null,null,null,null,null,null,null,null,null,null,null,"70 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559761_6648250361","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2019,2019,51,52,"2019-12-22T23:00:00","23:00","2019-12-29T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"3 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559761_6648252761","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2019,2020,51,50,"2019-12-16T11:30:00","11:30","2020-12-11T13:15:00","13:15",3314,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559861_6648005761","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2020,3,36,"2020-01-13T00:24:00","00:24","2020-08-31T03:30:00","03:30",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559861_6648004961","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2020,3,36,"2020-01-13T00:03:00","00:03","2020-08-31T03:00:00","03:00",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559861_6648007961","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2019,2020,51,50,"2019-12-16T14:16:00","14:16","2020-12-11T15:11:00","15:11",3796,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559861_6648006561","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2020,2,37,"2020-01-06T23:45:00","23:45","2020-09-11T05:45:00","05:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559861_6648008761","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2019,2020,51,50,"2019-12-16T10:45:00","10:45","2020-12-11T11:47:00","11:47",2946,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557161_6647916761","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2019,2020,51,50,"2019-12-16T13:36:00","13:36","2020-12-11T14:56:00","14:56",3734,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557161_6647919161","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2019,2020,51,50,"2019-12-16T11:30:00","11:30","2020-12-11T12:10:00","12:10",3042,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557161_6647918361","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2019,2020,51,50,"2019-12-16T00:30:00","00:30","2020-12-07T03:50:00","03:50",99,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557161_6647917561","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2019,2020,51,50,"2019-12-16T00:50:00","00:50","2020-12-07T03:30:00","03:30",90,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557161_6647915761","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2020,2020,12,44,"2020-03-16T10:15:00","10:15","2020-10-30T16:00:00","16:00",1157,"DAY",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556561_6648273161","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2020,11,47,"2020-03-09T10:00:00","10:00","2020-11-20T15:30:00","15:30",1059,"DAY",null,null,null,null,null,null,null,null,null,null,null,"69 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556561_6648271561","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2020,1,35,"2020-01-05T23:00:00","23:00","2020-08-30T02:30:00","02:30",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556561_6648274761","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2019,2020,51,50,"2019-12-16T13:35:00","13:35","2020-12-11T15:05:00","15:05",3742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556561_6648273961","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2020,11,47,"2020-03-09T09:40:00","09:40","2020-11-20T16:10:00","16:10",1105,"DAY",null,null,null,null,null,null,null,null,null,null,null,"69 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556561_6648272361","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2019,2020,51,50,"2019-12-16T11:52:00","11:52","2020-12-11T12:15:00","12:15",3038,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648556561_6648270761","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2020,2,36,"2020-01-06T02:08:00","02:08","2020-08-31T04:31:00","04:31",47,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554761_6648124361","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T13:25:00","13:25","2020-12-11T14:48:00","14:48",3701,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554761_6648121961","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T01:03:00","01:03","2020-12-07T04:25:00","04:25",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554761_6648123561","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T00:27:00","00:27","2020-12-07T03:05:00","03:05",55,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554761_6648121161","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T10:55:00","10:55","2020-12-11T11:37:00","11:37",2904,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554761_6648120361","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,49,"2019-12-22T00:05:00","00:05","2020-12-06T02:37:00","02:37",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554761_6648125161","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T10:37:00","10:37","2020-12-11T11:08:00","11:08",2783,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554761_6648125961","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T01:25:00","01:25","2020-12-07T04:51:00","04:51",85,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554761_6648119561","Dijon-Toul",">","Culmont","NeufChateau",2020,2020,7,11,"2020-02-10T10:05:00","10:05","2020-03-13T13:48:00","13:48",334,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554761_6648126761","Dijon-Toul",">","Culmont","NeufChateau",2019,2020,51,50,"2019-12-16T13:48:00","13:48","2020-12-11T15:15:00","15:15",3813,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554761_6648122761","Dijon-Toul",">","Culmont","NeufChateau",2020,2020,7,11,"2020-02-10T13:26:00","13:26","2020-03-13T19:14:00","19:14",467,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559561_6648246361","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2020,2020,2,38,"2020-01-06T23:14:00","23:14","2020-09-18T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"86 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559561_6648247361","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2019,2020,51,50,"2019-12-16T14:26:00","14:26","2020-12-11T15:23:00","15:23",3846,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559561_6648248161","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2019,2020,51,50,"2019-12-16T09:46:00","09:46","2020-12-11T10:44:00","10:44",2684,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557861_6648369161","Dijon-Toul",">","IsSurTille","Culmont",2019,2020,51,50,"2019-12-16T11:08:00","11:08","2020-12-11T11:38:00","11:38",1768,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557861_6648369961","Dijon-Toul",">","IsSurTille","Culmont",2019,2020,51,50,"2019-12-16T00:54:00","00:54","2020-12-07T03:29:00","03:29",173,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557861_6648370761","Dijon-Toul",">","IsSurTille","Culmont",2020,2020,7,48,"2020-02-10T12:50:00","12:50","2020-11-27T17:23:00","17:23",1673,"DAY",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557861_6648371561","Dijon-Toul",">","IsSurTille","Culmont",2019,2020,51,50,"2019-12-16T00:29:00","00:29","2020-12-07T04:03:00","04:03",202,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557861_6648368361","Dijon-Toul",">","IsSurTille","Culmont",2020,2020,7,48,"2020-02-10T10:58:00","10:58","2020-11-27T14:28:00","14:28",1392,"DAY",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557861_6648367561","Dijon-Toul",">","IsSurTille","Culmont",2019,2020,51,50,"2019-12-16T13:01:00","13:01","2020-12-11T14:22:00","14:22",2185,"DAY",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557061_6647998961","Lerouville-Nancy",">","Frouard","Jarville",2020,2020,2,38,"2020-01-06T23:05:00","23:05","2020-09-18T05:16:00","05:16",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"86 jours dans le régime binaire"]
[null,"SNCF Réseau","6648557061_6647999761","Lerouville-Nancy",">","Frouard","Jarville",2020,2020,2,38,"2020-01-06T23:11:00","23:11","2020-09-18T05:07:00","05:07",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"86 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554961_6648355961","Lerouville-Metz",">","Lerouville","Noveant",2020,2020,9,46,"2020-02-24T23:00:00","23:00","2020-11-13T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554961_6648355161","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,52,1,"2019-12-29T22:38:00","22:38","2020-01-05T01:02:00","01:02",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"3 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554961_6648356961","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,51,50,"2019-12-16T10:42:00","10:42","2020-12-11T11:16:00","11:16",2817,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554961_6648358561","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,51,50,"2019-12-16T14:02:00","14:02","2020-12-11T15:08:00","15:08",3784,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554961_6648357761","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,51,50,"2019-12-16T10:16:00","10:16","2020-12-11T11:05:00","11:05",2771,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554961_6648360161","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,51,50,"2019-12-16T13:35:00","13:35","2020-12-11T15:02:00","15:02",3759,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554961_6648359361","Lerouville-Metz",">","Lerouville","Noveant",2019,2020,52,1,"2019-12-29T23:27:00","23:27","2020-01-05T02:59:00","02:59",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"3 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558761_6648051961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2020,3,44,"2020-01-13T09:30:00","09:30","2020-10-26T15:30:00","15:30",130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558761_6648051161","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2020,2,36,"2020-01-06","00:00","2020-08-31T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558761_6648053561","Longuyon-Metz-Sarrebourg","<","Uckange",null,2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558761_6648054361","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2020,3,44,"2020-01-13T09:30:00","09:30","2020-10-26T15:30:00","15:30",130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558761_6648052761","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2020,9,39,"2020-02-24T09:30:00","09:30","2020-09-21T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558761_6648055961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2019,2020,51,50,"2019-12-16T09:10:00","09:10","2020-12-11T10:08:00","10:08",2139,"DAY",null,null,null,null,null,null,null,null,null,null,null,"212 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558761_6648050361","Longuyon-Metz-Sarrebourg","<","Uckange",null,2019,2020,51,50,"2019-12-16T13:50:00","13:50","2020-12-11T14:52:00","14:52",2037,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558761_6648055161","Longuyon-Metz-Sarrebourg","<","Uckange",null,2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558761_6648049561","Longuyon-Metz-Sarrebourg","<","Uckange",null,2019,2020,51,46,"2019-12-16T11:35:00","11:35","2020-11-13T12:38:00","12:38",1984,"DAY",null,null,null,null,null,null,null,null,null,null,null,"158 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558761_6648056761","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2020,9,39,"2020-02-24T09:30:00","09:30","2020-09-21T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558461_6648045361","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2020,2020,2,38,"2020-01-06T23:41:00","23:41","2020-09-18T05:46:00","05:46",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"91 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558461_6648047761","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2019,2020,51,50,"2019-12-16T14:25:00","14:25","2020-12-11T15:20:00","15:20",3834,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558461_6648046961","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2020,2020,2,38,"2020-01-06T23:10:00","23:10","2020-09-18T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"91 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558461_6648046161","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2019,2020,51,50,"2019-12-16T09:44:00","09:44","2020-12-11T10:50:00","10:50",2709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555361_6648148161","Lerouville-Metz",">","Noveant","Metz",2020,2020,12,46,"2020-03-16T23:00:00","23:00","2020-11-13T05:45:00","05:45",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555361_6648147361","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,50,"2019-12-16T09:20:00","09:20","2020-12-11T10:15:00","10:15",2563,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555361_6648144961","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,50,"2019-12-16T14:11:00","14:11","2020-12-11T15:05:00","15:05",3771,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555361_6648145761","Lerouville-Metz",">","Noveant","Metz",2020,2020,4,32,"2020-01-20","00:00","2020-08-03T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555361_6648142561","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,50,"2019-12-16T14:09:00","14:09","2020-12-11T15:17:00","15:17",3821,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555361_6648141761","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,36,"2019-12-16","00:00","2020-08-31T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555361_6648143361","Lerouville-Metz",">","Noveant","Metz",2020,2020,4,32,"2020-01-20","00:00","2020-08-03T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555361_6648149161","Lerouville-Metz",">","Noveant","Metz",2020,2020,11,45,"2020-03-09T22:55:00","22:55","2020-11-06T05:40:00","05:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555361_6648146561","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,50,"2019-12-16T10:48:00","10:48","2020-12-11T11:55:00","11:55",2980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648555361_6648144161","Lerouville-Metz",">","Noveant","Metz",2019,2020,51,36,"2019-12-16","00:00","2020-08-31T03:00:00","03:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558061_6648133361","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2020,2020,6,47,"2020-02-03T23:43:00","23:43","2020-11-20T05:29:00","05:29",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"68 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558061_6648130961","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2019,2020,51,50,"2019-12-16T09:03:00","09:03","2020-12-11T09:55:00","09:55",2460,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558061_6648131761","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2020,2020,6,26,"2020-02-03T23:27:00","23:27","2020-06-26T05:37:00","05:37",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
[null,"SNCF Réseau","6648558061_6648132561","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2019,2020,51,50,"2019-12-16T13:57:00","13:57","2020-12-11T15:07:00","15:07",3750,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554861_6647969761","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2019,2020,51,50,"2019-12-16T14:00:00","14:00","2020-12-11T15:20:00","15:20",3804,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554861_6647973161","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2020,2,36,"2020-01-06T00:25:00","00:25","2020-08-31T03:50:00","03:50",41,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554861_6647973961","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2019,2020,51,50,"2019-12-16T10:55:00","10:55","2020-12-11T11:50:00","11:50",2935,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554861_6647975561","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2019,2020,51,50,"2019-12-16T11:15:00","11:15","2020-12-11T11:55:00","11:55",2956,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554861_6647970561","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2020,2,36,"2020-01-06T00:50:00","00:50","2020-08-31T03:25:00","03:25",36,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554861_6647976361","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2020,2,36,"2020-01-06","00:00","2020-08-31T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554861_6647974761","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2019,2020,51,50,"2019-12-16T14:17:00","14:17","2020-12-11T15:28:00","15:28",3836,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554861_6647972161","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2020,11,47,"2020-03-09T10:12:00","10:12","2020-11-20T16:12:00","16:12",1253,"DAY",null,null,null,null,null,null,null,null,null,null,null,"78 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554861_6647971361","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2020,1,35,"2020-01-05T23:43:00","23:43","2020-08-30T02:23:00","02:23",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647988561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2019,2020,51,50,"2019-12-16T13:41:00","13:41","2020-12-11T14:44:00","14:44",2004,"DAY",null,null,null,null,null,null,null,null,null,null,null,"137 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647986961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647991761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,5,46,"2020-01-28T11:30:00","11:30","2020-11-13T15:30:00","15:30",686,"DAY",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647987761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",531,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647989361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,5,46,"2020-01-28T11:30:00","11:30","2020-11-13T15:30:00","15:30",670,"DAY",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647986161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2019,2020,51,50,"2019-12-16T09:19:00","09:19","2020-12-11T10:17:00","10:17",2201,"DAY",null,null,null,null,null,null,null,null,null,null,null,"215 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647984561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,7,50,"2020-02-11T11:30:00","11:30","2020-12-11T15:30:00","15:30",531,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647990961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647982961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2019,2020,51,46,"2019-12-16T14:25:00","14:25","2020-11-13T15:21:00","15:21",2318,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647990161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,7,50,"2020-02-10T09:30:00","09:30","2020-12-07T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647983761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2019,2020,51,46,"2019-12-16T11:27:00","11:27","2020-11-13T12:28:00","12:28",1883,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554361_6647985361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2020,5,46,"2020-01-27T09:30:00","09:30","2020-11-09T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559161_6648031961","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2019,2020,51,50,"2019-12-16T14:32:00","14:32","2020-12-11T15:16:00","15:16",3817,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559161_6648032761","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2020,3,36,"2020-01-13","00:00","2020-08-31T03:24:00","03:24",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559161_6648035361","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2020,3,36,"2020-01-13T00:25:00","00:25","2020-08-31T03:03:00","03:03",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559161_6648033561","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2020,2,37,"2020-01-06T23:35:00","23:35","2020-09-11T05:35:00","05:35",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
[null,"SNCF Réseau","6648559161_6648034561","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2019,2020,51,50,"2019-12-16T10:26:00","10:26","2020-12-11T11:42:00","11:42",2926,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554061_6648028161","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,50,"2019-12-16T14:25:00","14:25","2020-12-11T15:10:00","15:10",3716,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554061_6648028961","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2020,2,38,"2020-01-06T23:09:00","23:09","2020-09-18T04:35:00","04:35",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554061_6648026561","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,4,"2019-12-16T00:20:00","00:20","2020-01-20T03:50:00","03:50",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554061_6648024161","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,50,"2019-12-16T14:10:00","14:10","2020-12-11T15:00:00","15:00",3675,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554061_6648024961","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,50,"2019-12-16T09:47:00","09:47","2020-12-11T11:00:00","11:00",2696,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554061_6648027361","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,3,"2019-12-22T22:40:00","22:40","2020-01-19T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554061_6648023361","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2020,2,38,"2020-01-06T23:46:00","23:46","2020-09-18T06:20:00","06:20",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
[null,"SNCF Réseau","6648554061_6648025761","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2019,2020,51,50,"2019-12-16T09:33:00","09:33","2020-12-11T10:47:00","10:47",2643,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699361_6645523561","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2020,10,44,"2020-03-02T08:36:00","08:36","2020-10-30T14:36:00","14:36",1086,"DAY",null,null,null,null,null,null,null,null,null,null,null,"75 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699361_6645522761","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2020,1,50,"2020-01-02T11:48:00","11:48","2020-12-11T13:34:00","13:34",1168,"DAY",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699361_6645524561","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2020,1,50,"2020-01-02T12:50:00","12:50","2020-12-11T13:00:00","13:00",1118,"DAY",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699361_6645526161","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2020,3,41,"2020-01-19T22:20:00","22:20","2020-10-11T02:00:00","02:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699361_6645525361","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2020,4,42,"2020-01-20T03:35:00","03:35","2020-10-12T05:55:00","05:55",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697961_6645639761","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2020,4,37,"2020-01-20T01:35:00","01:35","2020-09-07T04:17:00","04:17",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697961_6645640561","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2020,21,34,"2020-05-18T11:00:00","11:00","2020-08-21T16:35:00","16:35",619,"DAY",null,null,null,null,null,null,null,null,null,null,null,"38 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697961_6645638961","Valence - Avignon",">","Pierrelatte","Sorgues",2019,2020,51,50,"2019-12-16T11:17:00","11:17","2020-12-11T11:43:00","11:43",2425,"DAY",null,null,null,null,null,null,null,null,null,null,null,"208 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697961_6645636561","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2020,4,37,"2020-01-20T00:40:00","00:40","2020-09-07T04:05:00","04:05",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697961_6645638161","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2020,21,34,"2020-05-18T08:32:00","08:32","2020-08-21T12:50:00","12:50",479,"DAY",null,null,null,null,null,null,null,null,null,null,null,"38 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697961_6645637361","Valence - Avignon",">","Pierrelatte","Sorgues",2019,2020,51,50,"2019-12-16T13:13:00","13:13","2020-12-11T14:48:00","14:48",3065,"DAY",null,null,null,null,null,null,null,null,null,null,null,"208 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699161_6645583961","Valence - Avignon",">","Sorgues","Avignon",2020,2020,4,37,"2020-01-20T01:05:00","01:05","2020-09-07T04:12:00","04:12",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699161_6645582361","Valence - Avignon",">","Sorgues","Avignon",2020,2020,21,34,"2020-05-18T11:40:00","11:40","2020-08-21T16:23:00","16:23",610,"DAY",null,null,null,null,null,null,null,null,null,null,null,"38 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699161_6645579961","Valence - Avignon",">","Sorgues","Avignon",2019,2020,51,50,"2019-12-16T10:43:00","10:43","2020-12-11T11:36:00","11:36",2402,"DAY",null,null,null,null,null,null,null,null,null,null,null,"208 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699161_6645581561","Valence - Avignon",">","Sorgues","Avignon",2020,2020,21,34,"2020-05-18T08:16:00","08:16","2020-08-21T12:50:00","12:50",479,"DAY",null,null,null,null,null,null,null,null,null,null,null,"38 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699161_6645583161","Valence - Avignon",">","Sorgues","Avignon",2019,2020,51,50,"2019-12-16T14:04:00","14:04","2020-12-11T15:12:00","15:12",3147,"DAY",null,null,null,null,null,null,null,null,null,null,null,"208 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699161_6645580761","Valence - Avignon",">","Sorgues","Avignon",2020,2020,4,37,"2020-01-20T01:17:00","01:17","2020-09-07T04:10:00","04:10",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697761_6645561361","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2020,3,44,"2020-01-13T02:55:00","02:55","2020-10-26T05:35:00","05:35",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697761_6645560561","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2020,21,24,"2020-05-18T10:21:00","10:21","2020-06-12T14:55:00","14:55",258,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697761_6645559761","Lyon-Valence",">","Vienne","St Rambert (par RG)",2019,2020,51,50,"2019-12-16T13:18:00","13:18","2020-12-11T14:00:00","14:00",2884,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697761_6645562161","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2020,21,24,"2020-05-18T09:43:00","09:43","2020-06-12T14:59:00","14:59",259,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697761_6645563761","Lyon-Valence",">","Vienne","St Rambert (par RG)",2019,2020,51,50,"2019-12-16T11:40:00","11:40","2020-12-11T12:58:00","12:58",2672,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
[null,"SNCF Réseau","6645697761_6645562961","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2020,2,43,"2020-01-12T23:00:00","23:00","2020-10-25T02:20:00","02:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698561_6645568161","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2020,10,44,"2020-03-02T09:15:00","09:15","2020-10-30T15:15:00","15:15",829,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698561_6645569161","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2020,1,50,"2020-01-02T11:15:00","11:15","2020-12-11T12:48:00","12:48",1806,"DAY",null,null,null,null,null,null,null,null,null,null,null,"142 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698561_6645567361","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2020,1,50,"2020-01-02T13:28:00","13:28","2020-12-11T13:50:00","13:50",1950,"DAY",null,null,null,null,null,null,null,null,null,null,null,"142 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698561_6645569961","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2020,3,41,"2020-01-19T21:50:00","21:50","2020-10-11T01:20:00","01:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698561_6645570761","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2020,4,42,"2020-01-20T04:05:00","04:05","2020-10-12T06:35:00","06:35",68,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698961_6645654361","Valence - Avignon",">","Portes","Livron (par RG)",2019,2020,51,50,"2019-12-16T12:34:00","12:34","2020-12-11T13:40:00","13:40",2816,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698961_6645658361","Valence - Avignon",">","Portes","Livron (par RG)",2020,2020,3,44,"2020-01-13T01:55:00","01:55","2020-10-26T04:45:00","04:45",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698961_6645657561","Valence - Avignon",">","Portes","Livron (par RG)",2019,2020,51,50,"2019-12-16T12:05:00","12:05","2020-12-11T12:55:00","12:55",2661,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698961_6645655161","Valence - Avignon",">","Portes","Livron (par RG)",2020,2020,2,43,"2020-01-12T23:54:00","23:54","2020-10-25T03:07:00","03:07",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698661_6645590961","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2020,21,24,"2020-05-18T09:34:00","09:34","2020-06-12T14:36:00","14:36",253,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698661_6645591761","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2020,2,43,"2020-01-12T23:06:00","23:06","2020-10-25T02:12:00","02:12",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698661_6645593361","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2019,2020,51,50,"2019-12-16T13:26:00","13:26","2020-12-11T14:19:00","14:19",2950,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698661_6645592561","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2020,3,44,"2020-01-13T02:57:00","02:57","2020-10-26T05:47:00","05:47",72,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698661_6645594961","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2020,21,24,"2020-05-18T10:26:00","10:26","2020-06-12T15:16:00","15:16",264,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698661_6645594161","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2019,2020,51,50,"2019-12-16T11:32:00","11:32","2020-12-11T12:38:00","12:38",2603,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698061_6645572361","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2019,2020,51,50,"2019-12-16T12:34:00","12:34","2020-12-11T13:33:00","13:33",2453,"DAY",null,null,null,null,null,null,null,null,null,null,null,"182 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698061_6645573961","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2020,3,44,"2020-01-13T02:34:00","02:34","2020-10-26T05:10:00","05:10",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698061_6645577161","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2019,2020,51,50,"2019-12-16T11:59:00","11:59","2020-12-11T13:28:00","13:28",2748,"DAY",null,null,null,null,null,null,null,null,null,null,null,"205 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698061_6645574761","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2020,21,24,"2020-05-18T09:59:00","09:59","2020-06-12T15:24:00","15:24",267,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698061_6645575561","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2019,2020,51,50,"2019-12-16T12:57:00","12:57","2020-12-11T13:32:00","13:32",2788,"DAY",null,null,null,null,null,null,null,null,null,null,null,"207 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698061_6645577961","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2020,2,43,"2020-01-12T23:12:00","23:12","2020-10-25T02:51:00","02:51",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698061_6645576361","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2020,3,44,"2020-01-13T02:10:00","02:10","2020-10-26T05:10:00","05:10",65,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699661_6645512361","Valence - Avignon",">","Raccordement de Livron","LaVoulte",2020,2020,10,44,"2020-03-02T10:32:00","10:32","2020-10-30T15:32:00","15:32",300,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699661_6645510561","Valence - Avignon",">","Raccordement de Livron","LaVoulte",2020,2020,5,9,"2020-01-30T08:08:00","08:08","2020-02-28T09:38:00","09:38",49,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698261_6645505161","Lyon-Valence",">","RaccPeyraud","St Rambert",2020,2020,10,44,"2020-03-02T09:58:00","09:58","2020-10-30T14:58:00","14:58",289,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699761_6645543961","Valence - Avignon",">","Livron","Pierrelatte",2020,2020,3,44,"2020-01-13T00:10:00","00:10","2020-10-26T03:40:00","03:40",47,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699761_6645543161","Valence - Avignon",">","Livron","Pierrelatte",2020,2020,16,50,"2020-04-14T12:41:00","12:41","2020-12-11T14:11:00","14:11",1405,"DAY",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699761_6645541561","Valence - Avignon",">","Livron","Pierrelatte",2020,2020,16,50,"2020-04-14T11:52:00","11:52","2020-12-11T12:20:00","12:20",1221,"DAY",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699761_6645542361","Valence - Avignon",">","Livron","Pierrelatte",2020,2020,3,44,"2020-01-13T02:05:00","02:05","2020-10-26T04:35:00","04:35",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645699761_6645544761","Valence - Avignon",">","Livron","Pierrelatte",2020,2020,21,24,"2020-05-18T10:37:00","10:37","2020-06-12T16:02:00","16:02",277,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698761_6645552561","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,25,35,"2020-06-15T11:00:00","11:00","2020-08-28T11:22:00","11:22",375,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698761_6645550761","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,6,49,"2020-02-03T09:47:00","09:47","2020-12-04T15:47:00","15:47",1237,"DAY",null,null,null,null,null,null,null,null,null,null,null,"79 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698761_6645554961","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,4,42,"2020-01-20T00:05:00","00:05","2020-10-12T03:32:00","03:32",38,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698761_6645555761","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,4,42,"2020-01-20T02:49:00","02:49","2020-10-12T04:59:00","04:59",52,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698761_6645551761","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,1,50,"2020-01-02T11:55:00","11:55","2020-12-11T12:00:00","12:00",1488,"DAY",null,null,null,null,null,null,null,null,null,null,null,"125 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698761_6645549961","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,25,35,"2020-06-15T13:30:00","13:30","2020-08-28T15:05:00","15:05",499,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
[null,"SNCF Réseau","6645698761_6645556561","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2020,1,50,"2020-01-02T12:40:00","12:40","2020-12-11T14:30:00","14:30",1741,"DAY",null,null,null,null,null,null,null,null,null,null,null,"121 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024661_6644936461","Dijon-Lyon",">","Dijon","Chagny",2020,2020,3,42,"2020-01-13T00:45:00","00:45","2020-10-12T04:00:00","04:00",55,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024661_6644937261","Dijon-Lyon",">","Dijon","Chagny",2019,2020,51,50,"2019-12-16T12:42:00","12:42","2020-12-11T14:13:00","14:13",3555,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024661_6644935661","Dijon-Lyon",">","Dijon","Chagny",2019,2020,51,44,"2019-12-16T22:29:00","22:29","2020-10-28T04:55:00","04:55",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"137 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024661_6644934861","Dijon-Lyon",">","Dijon","Chagny",2020,2020,3,42,"2020-01-13T00:25:00","00:25","2020-10-12T03:11:00","03:11",44,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024661_6644938861","Dijon-Lyon",">","Dijon","Chagny",2019,2020,51,50,"2019-12-16T12:16:00","12:16","2020-12-11T12:44:00","12:44",3183,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024661_6644938061","Dijon-Lyon",">","Dijon","Chagny",2019,2020,51,44,"2019-12-17T00:34:00","00:34","2020-10-29T05:57:00","05:57",814,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"137 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024361_6644954861","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2019,2020,51,50,"2019-12-16T13:09:00","13:09","2020-12-11T14:22:00","14:22",3607,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024361_6644954061","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2019,2020,1,50,"2019-12-30T01:32:00","01:32","2020-12-07T04:15:00","04:15",100,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024361_6644951461","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2019,2020,52,49,"2019-12-29T23:22:00","23:22","2020-12-06T02:39:00","02:39",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024361_6644952261","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2019,2020,51,50,"2019-12-16T11:34:00","11:34","2020-12-11T12:14:00","12:14",3059,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024361_6644955661","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2020,3,49,"2020-01-13T10:15:00","10:15","2020-12-04T16:15:00","16:15",1501,"DAY",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024361_6644953061","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2020,3,49,"2020-01-13T14:15:00","14:15","2020-12-04T16:15:00","16:15",1497,"DAY",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025561_6644876261","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2020,3,44,"2020-01-13T23:00:00","23:00","2020-10-28T05:11:00","05:11",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"117 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025561_6644879461","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2020,3,42,"2020-01-13T00:10:00","00:10","2020-10-12T03:05:00","03:05",43,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025561_6644877061","Dijon-Lyon",">","Chagny","Chalon sur Saone",2019,2020,51,50,"2019-12-16T13:13:00","13:13","2020-12-11T14:26:00","14:26",3609,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025561_6644877861","Dijon-Lyon",">","Chagny","Chalon sur Saone",2019,2020,51,50,"2019-12-16T11:46:00","11:46","2020-12-11T12:35:00","12:35",3146,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025561_6644880261","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2020,3,44,"2020-01-13T00:07:00","00:07","2020-10-28T05:55:00","05:55",-5,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"116 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025561_6644878661","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2020,3,42,"2020-01-13T01:00:00","01:00","2020-10-12T04:05:00","04:05",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025761_6644812461","Dijon-Lyon",">","Chalon sur Saone","Macon",2019,2020,51,50,"2019-12-16T13:25:00","13:25","2020-12-11T14:56:00","14:56",3734,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025761_6644813261","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2020,2,41,"2020-01-12T00:03:00","00:03","2020-10-11T02:30:00","02:30",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025761_6644810061","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2020,3,44,"2020-01-13T23:58:00","23:58","2020-10-28T05:18:00","05:18",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"117 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025761_6644811661","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2020,3,42,"2020-01-13T01:07:00","01:07","2020-10-12T04:40:00","04:40",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025761_6644809261","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2020,3,44,"2020-01-13T23:05:00","23:05","2020-10-28T05:57:00","05:57",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"117 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025761_6644810861","Dijon-Lyon",">","Chalon sur Saone","Macon",2019,2020,51,50,"2019-12-16T11:37:00","11:37","2020-12-11T12:06:00","12:06",3025,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025661_6644918861","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2019,2020,51,50,"2019-12-16T12:49:00","12:49","2020-12-11T14:05:00","14:05",3522,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025661_6644920661","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2020,5,37,"2020-01-27T01:52:00","01:52","2020-09-07T04:32:00","04:32",52,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025661_6644917261","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2020,4,36,"2020-01-26T23:44:00","23:44","2020-09-06T02:29:00","02:29",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025661_6644921461","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2020,2,50,"2020-01-06T11:00:00","11:00","2020-12-11T13:00:00","13:00",1406,"DAY",null,null,null,null,null,null,null,null,null,null,null,"109 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025661_6644918061","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2019,2020,51,50,"2019-12-16T12:00:00","12:00","2020-12-11T12:50:00","12:50",3209,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025661_6644919661","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2020,2,50,"2020-01-06T10:43:00","10:43","2020-12-11T16:43:00","16:43",1811,"DAY",null,null,null,null,null,null,null,null,null,null,null,"109 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025961_6644854661","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2020,4,36,"2020-01-26T22:10:00","22:10","2020-09-06T01:30:00","01:30",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025961_6644853861","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2020,7,25,"2020-02-10T13:08:00","13:08","2020-06-19T16:28:00","16:28",760,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025961_6644855461","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2020,7,25,"2020-02-10T08:49:00","08:49","2020-06-19T13:22:00","13:22",619,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025961_6644858861","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2019,2020,51,34,"2019-12-16T11:27:00","11:27","2020-08-21T13:05:00","13:05",1427,"DAY",null,null,null,null,null,null,null,null,null,null,null,"110 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025961_6644857261","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2019,2020,51,34,"2019-12-16T13:30:00","13:30","2020-08-21T13:48:00","13:48",1504,"DAY",null,null,null,null,null,null,null,null,null,null,null,"110 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025961_6644858061","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2020,5,37,"2020-01-27T02:56:00","02:56","2020-09-07T05:30:00","05:30",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025961_6644856261","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2020,8,49,"2020-02-17T10:22:00","10:22","2020-12-04T16:22:00","16:22",1446,"DAY",null,null,null,null,null,null,null,null,null,null,null,"89 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025461_6644888661","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2019,2020,51,50,"2019-12-16T15:05:00","15:05","2020-12-11T15:48:00","15:48",3950,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025461_6644887661","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2019,2020,51,50,"2019-12-16T23:40:00","23:40","2020-12-11T05:40:00","05:40",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"219 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025461_6644890261","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2019,2020,51,50,"2019-12-16T00:25:00","00:25","2020-12-07T03:10:00","03:10",157,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025461_6644889461","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2019,2020,51,50,"2019-12-16T14:31:00","14:31","2020-12-11T15:48:00","15:48",3951,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025461_6644891061","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2019,2020,51,50,"2019-12-16T00:05:00","00:05","2020-12-07T03:20:00","03:20",166,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025361_6644863661","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T14:28:00","14:28","2020-12-11T15:35:00","15:35",3694,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025361_6644866061","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T10:30:00","10:30","2020-12-11T11:24:00","11:24",2702,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025361_6644864461","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T10:30:00","10:30","2020-12-11T11:24:00","11:24",2702,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025361_6644860461","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-07T00:20:00","00:20","2020-12-12T06:24:00","06:24",620,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025361_6644862061","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-07T00:20:00","00:20","2020-12-12T06:24:00","06:24",620,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025361_6644865261","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T22:58:00","22:58","2020-12-11T04:37:00","04:37",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025361_6644861261","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T14:28:00","14:28","2020-12-11T15:35:00","15:35",3694,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025361_6644862861","Dijon-Lyon",">","StGermain","Collonges",2020,2020,2,50,"2020-01-06T22:58:00","22:58","2020-12-11T04:37:00","04:37",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024161_6644914461","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2020,6,25,"2020-02-03T12:35:00","12:35","2020-06-19T16:15:00","16:15",783,"DAY",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024161_6644911861","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2020,8,47,"2020-02-17T10:15:00","10:15","2020-11-20T16:15:00","16:15",786,"DAY",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024161_6644911061","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2019,2020,51,42,"2019-12-16T12:58:00","12:58","2020-10-16T13:10:00","13:10",1804,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024161_6644912861","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2020,5,37,"2020-01-27T02:30:00","02:30","2020-09-07T04:52:00","04:52",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024161_6644915261","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2020,4,36,"2020-01-26T22:31:00","22:31","2020-09-06T02:02:00","02:02",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024161_6644916061","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2020,6,25,"2020-02-03T09:15:00","09:15","2020-06-19T13:45:00","13:45",664,"DAY",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
[null,"SNCF Réseau","6645024161_6644913661","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2019,2020,51,42,"2019-12-16T12:05:00","12:05","2020-10-16T13:48:00","13:48",1892,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
[null,"SNCF Réseau","6645023961_6644899461","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2019,2020,51,50,"2019-12-16T11:44:00","11:44","2020-12-11T12:08:00","12:08",2985,"DAY",null,null,null,null,null,null,null,null,null,null,null,"247 jours dans le régime binaire"]
[null,"SNCF Réseau","6645023961_6644896261","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2020,8,49,"2020-02-17T22:18:00","22:18","2020-12-03T04:40:00","04:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
[null,"SNCF Réseau","6645023961_6644897861","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2020,7,37,"2020-02-10T00:24:00","00:24","2020-09-07T03:47:00","03:47",52,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6645023961_6644898661","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2019,2020,51,50,"2019-12-16T10:42:00","10:42","2020-12-11T12:01:00","12:01",2957,"DAY",null,null,null,null,null,null,null,null,null,null,null,"247 jours dans le régime binaire"]
[null,"SNCF Réseau","6645023961_6644897061","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2020,7,37,"2020-02-10T03:06:00","03:06","2020-09-07T05:32:00","05:32",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6645023961_6644900261","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2020,1,50,"2020-01-05T23:30:00","23:30","2020-12-10T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"41 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025861_6644872661","Dijon-Lyon",">","Macon","Saint Germain",2020,2020,2,41,"2020-01-12T22:50:00","22:50","2020-10-11T01:30:00","01:30",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025861_6644869461","Dijon-Lyon",">","Macon","Saint Germain",2019,2020,51,50,"2019-12-16T13:57:00","13:57","2020-12-11T15:28:00","15:28",3868,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025861_6644871861","Dijon-Lyon",">","Macon","Saint Germain",2019,2020,51,50,"2019-12-16T11:03:00","11:03","2020-12-11T11:33:00","11:33",2888,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025861_6644871061","Dijon-Lyon",">","Macon","Saint Germain",2020,2020,3,44,"2020-01-13T23:25:00","23:25","2020-10-28T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"98 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025861_6644870261","Dijon-Lyon",">","Macon","Saint Germain",2020,2020,3,42,"2020-01-13T01:45:00","01:45","2020-10-12T05:04:00","05:04",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
[null,"SNCF Réseau","6645025861_6644868661","Dijon-Lyon",">","Macon","Saint Germain",2020,2020,3,44,"2020-01-13T23:45:00","23:45","2020-10-28T06:20:00","06:20",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"98 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749061_6644538361","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2020,6,43,"2020-02-03T22:30:00","22:30","2020-10-23T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749061_6644535961","Miramas-Fos-Marseille",">","Lavalduc","Fos",2019,2020,51,50,"2019-12-16T08:45:00","08:45","2020-12-11T09:45:00","09:45",2438,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749061_6644537561","Miramas-Fos-Marseille",">","Lavalduc","Fos",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",153,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749061_6644540161","Miramas-Fos-Marseille",">","Lavalduc","Fos",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749061_6644539161","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2020,13,47,"2020-03-23T22:30:00","22:30","2020-11-20T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749061_6644536761","Miramas-Fos-Marseille",">","Lavalduc","Fos",2019,2020,51,50,"2019-12-16T08:45:00","08:45","2020-12-11T09:45:00","09:45",2438,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748561_6644560961","Miramas-Marseille",">","Rognac","L'Estaque",2019,2020,51,50,"2019-12-16T09:55:00","09:55","2020-12-11T10:50:00","10:50",2709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748561_6644561761","Miramas-Marseille",">","Rognac","L'Estaque",2019,2020,51,50,"2019-12-16T10:56:00","10:56","2020-12-11T12:04:00","12:04",3017,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748561_6644562561","Miramas-Marseille",">","Rognac","L'Estaque",2019,2020,51,50,"2019-12-17","00:00","2020-12-12T04:30:00","04:30",688,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"153 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748561_6644563561","Miramas-Marseille",">","Rognac","L'Estaque",2019,2020,51,50,"2019-12-16T11:05:00","11:05","2020-12-11T12:10:00","12:10",3042,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748561_6644564361","Miramas-Marseille",">","Rognac","L'Estaque",2019,2020,51,50,"2019-12-16T09:55:00","09:55","2020-12-11T11:03:00","11:03",2763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644750761_6644544361","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2020,2020,27,50,"2020-06-29T15:26:00","15:26","2020-12-11T16:54:00","16:54",1978,"DAY",null,null,null,null,null,null,null,null,null,null,null,"118 jours dans le régime binaire"]
[null,"SNCF Réseau","6644750761_6644543361","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2020,2020,42,47,"2020-10-12T09:20:00","09:20","2020-11-20T13:20:00","13:20",377,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
[null,"SNCF Réseau","6644750761_6644545161","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2020,2020,27,50,"2020-06-29T08:22:00","08:22","2020-12-11T09:57:00","09:57",1165,"DAY",null,null,null,null,null,null,null,null,null,null,null,"118 jours dans le régime binaire"]
[null,"SNCF Réseau","6644750061_6644584961","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2019,2020,51,50,"2019-12-16T11:11:00","11:11","2020-12-11T12:13:00","12:13",3055,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644750061_6644583961","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2020,2020,10,43,"2020-03-03","00:00","2020-10-24T04:30:00","04:30",292,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
[null,"SNCF Réseau","6644750061_6644583161","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2019,2020,51,50,"2019-12-16T09:50:00","09:50","2020-12-11T10:47:00","10:47",2696,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748861_6644581161","Avignon-Miramasparest",">","Cavaillon","Miramas",2019,2020,51,50,"2019-12-16T00:55:00","00:55","2020-12-07T04:28:00","04:28",110,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748861_6644580361","Avignon-Miramasparest",">","Cavaillon","Miramas",2019,2020,51,50,"2019-12-16T01:16:00","01:16","2020-12-07T03:35:00","03:35",91,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748861_6644581961","Avignon-Miramasparest",">","Cavaillon","Miramas",2019,2020,51,50,"2019-12-16T10:52:00","10:52","2020-12-11T11:25:00","11:25",2854,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748861_6644578561","Avignon-Miramasparest",">","Cavaillon","Miramas",2019,2020,51,50,"2019-12-16T14:08:00","14:08","2020-12-11T15:33:00","15:33",3888,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748861_6644579361","Avignon-Miramasparest",">","Cavaillon","Miramas",2020,2020,14,47,"2020-03-30T09:08:00","09:08","2020-11-20T13:08:00","13:08",752,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748461_6644596961","Avignon-Miramasparouest",">","Avignon","Tarascon",2019,2020,52,49,"2019-12-23T01:20:00","01:20","2020-11-30T04:15:00","04:15",100,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748461_6644595961","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2020,10,48,"2020-03-03","00:00","2020-11-28T02:00:00","02:00",148,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748461_6644598561","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2020,13,48,"2020-03-23T23:15:00","23:15","2020-11-27T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748461_6644594361","Avignon-Miramasparouest",">","Avignon","Tarascon",2019,2020,51,50,"2019-12-16T10:41:00","10:41","2020-12-11T11:47:00","11:47",2946,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748461_6644597761","Avignon-Miramasparouest",">","Avignon","Tarascon",2019,2020,52,49,"2019-12-23T01:05:00","01:05","2020-11-30T04:10:00","04:10",98,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748461_6644599361","Avignon-Miramasparouest",">","Avignon","Tarascon",2019,2020,51,50,"2019-12-16T14:17:00","14:17","2020-12-11T15:10:00","15:10",3792,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748461_6644595161","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2020,2,47,"2020-01-06T23:10:00","23:10","2020-11-20T05:04:00","05:04",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749861_6644602761","Avignon-Miramasparest",">","Avignon","Cavaillon",2019,2020,51,50,"2019-12-16T01:45:00","01:45","2020-12-07T04:16:00","04:16",104,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749861_6644603561","Avignon-Miramasparest",">","Avignon","Cavaillon",2020,2020,14,47,"2020-03-30T09:08:00","09:08","2020-11-20T13:08:00","13:08",765,"DAY",null,null,null,null,null,null,null,null,null,null,null,"59 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749861_6644601161","Avignon-Miramasparest",">","Avignon","Cavaillon",2019,2020,51,50,"2019-12-16T11:20:00","11:20","2020-12-11T11:52:00","11:52",2967,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749861_6644601961","Avignon-Miramasparest",">","Avignon","Cavaillon",2019,2020,51,50,"2019-12-16T00:32:00","00:32","2020-12-07T03:55:00","03:55",97,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
[null,"SNCF Réseau","6644749861_6644604561","Avignon-Miramasparest",">","Avignon","Cavaillon",2019,2020,51,50,"2019-12-16T13:37:00","13:37","2020-12-11T15:07:00","15:07",3780,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748761_6644533561","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2019,2020,51,50,"2019-12-16T15:06:00","15:06","2020-12-11T16:23:00","16:23",4097,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748761_6644531761","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2020,2020,10,44,"2020-03-02T22:30:00","22:30","2020-10-30T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748761_6644532761","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2019,2020,51,50,"2019-12-16T09:23:00","09:23","2020-12-11T10:40:00","10:40",2667,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644751161_6644631161","Miramas-Marseille",">","Miramas","Rognac",2019,2020,51,50,"2019-12-16T10:51:00","10:51","2020-12-11T11:55:00","11:55",2980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644751161_6644632761","Miramas-Marseille",">","Miramas","Rognac",2019,2020,51,50,"2019-12-16T10:21:00","10:21","2020-12-11T11:08:00","11:08",2784,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644751161_6644631961","Miramas-Marseille",">","Miramas","Rognac",2019,2020,51,50,"2019-12-16T10:39:00","10:39","2020-12-11T11:51:00","11:51",2963,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644751161_6644629561","Miramas-Marseille",">","Miramas","Rognac",2019,2020,51,50,"2019-12-16T10:08:00","10:08","2020-12-11T11:06:00","11:06",2775,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644751161_6644628561","Miramas-Marseille",">","Miramas","Rognac",2020,2020,6,48,"2020-02-04","00:00","2020-11-28T04:30:00","04:30",450,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
[null,"SNCF Réseau","6644751161_6644630361","Miramas-Marseille",">","Miramas","Rognac",2019,2020,51,50,"2019-12-16T01:00:00","01:00","2020-12-07T03:55:00","03:55",198,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748961_6644548961","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2020,2020,10,44,"2020-03-02T22:30:00","22:30","2020-10-30T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"69 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748961_6644549961","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",153,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748961_6644552361","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2019,2020,51,50,"2019-12-16T14:51:00","14:51","2020-12-11T16:06:00","16:06",4026,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748961_6644551561","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2019,2020,51,50,"2019-12-16T09:20:00","09:20","2020-12-11T10:38:00","10:38",2659,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748961_6644550761","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2019,2020,51,50,"2019-12-16","00:00","2020-12-07T03:00:00","03:00",153,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"51 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748661_6644618561","Avignon-Miramasparouest",">","Tarascon","Miramas",2019,2020,51,50,"2019-12-16T10:23:00","10:23","2020-12-11T11:01:00","11:01",2754,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748661_6644619361","Avignon-Miramasparouest",">","Tarascon","Miramas",2019,2020,52,49,"2019-12-23T00:30:00","00:30","2020-11-30T03:28:00","03:28",82,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748661_6644620161","Avignon-Miramasparouest",">","Tarascon","Miramas",2019,2020,51,50,"2019-12-16T10:30:00","10:30","2020-12-11T11:57:00","11:57",2988,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748661_6644621761","Avignon-Miramasparouest",">","Tarascon","Miramas",2020,2020,2,49,"2020-01-06T23:15:00","23:15","2020-12-04T05:13:00","05:13",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"212 jours dans le régime binaire"]
[null,"SNCF Réseau","6644748661_6644620961","Avignon-Miramasparouest",">","Tarascon","Miramas",2019,2020,52,49,"2019-12-23T01:43:00","01:43","2020-11-30T04:45:00","04:45",112,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]

{"sheet":"SBB","index":6,"n_rows":12,"n_cols":31,"rows_kept":12,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["SBB Infra","AD305","Basel Bad - Basel PB","< >","BSGB","BS",2019,2019,48,49,"2019-11-30",null,"2019-12-02",null,null,"Night and Day","Track renewal","x",null,null,null,null,"x",null,null,"x",null,"Sa/Mo 30.11 - 02.12.2019, 7.12 - 9.11.2019,  Totalclosure from 04:00 - 04:00, delays till 15 Min direction SNCF"]
["SBB Infra",null,"Basel GB - Basel PB","< >","BSGB","BS",2020,2020,2,5,"2020-01-06",null,"2020-01-31",null,null,"Night and Day","Track renewal",null,"x","x",null,null,null,null,null,"x",null,"Works with single track from 06.01 - 17.01, 27.01. - 31.01.2020, 16 - 26.03.20 delays till 15Min direction SNCF"]
["SBB Infra",6553,"Basel St. Johann",null,"BSSJ","BSSJ",2021,2021,null,null,"2020-05-01",null,"2021-09-22",null,null,"Night","Signal box works","x",null,null,null,null,"x",null,null,"x",null,"Totalclosure 8 nights for 4 hours"]
["SBB Infra",null,"Basel PB - Basel St. Johann","< >","BS ","BSSJ",2020,2020,31,40,"2020-08-01",null,"2020-09-20",null,null,"Night","Signal box works","x",null,null,null,null,"x",null,null,"x",null,"So/Mo 20/21.06, 05/06.07, 12/13.07, 01-03.08.2020 Totalclosure from 00:40 - 04:40, no trains direction SNCF"]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"."]

{"sheet":"ACF CFL","index":7,"n_rows":53,"n_cols":31,"rows_kept":53,"cut":false,"hidden":false,"merged":[[3,17,3,21],[3,22,3,26],[3,4,3,5],[3,6,3,7],[3,8,3,9],[3,10,3,11],[3,12,3,13]]}
[]
[null,null,"Works Luxembourg 2020 Map",null,null,"Works Luxembourg 2020 Map"]
[]
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["ACF/CFL","ACF1","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2019,2019,28,30,"2019-07-13","01:20:00","2019-07-22","04:00:00","9 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF2","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2019,2019,33,34,"2019-08-17","01:20:00","2019-08-23","04:00:00","6 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF3","Rodange-Bettembourg","< >","Pétange","Esch/Alzette",2019,2019,43,44,"2019-10-26","00:30:00","2019-11-04","04:00:00","9 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF4","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2019,2019,41,42,"2019-10-12","01:20:00","2019-10-14","04:00:00","3 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF5","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2019,2019,42,43,"2019-10-19","01:20:00","2019-10-21","04:00:00","3 days ","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF6","Luxembourg-Bettembourg","< >","Luxembourg","Berchem",2020,2020,18,19,"2020-05-01","00:00:00","2020-05-04","04:00:00","4 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF7","Rodange-Bettembourg","< >","Belval-Usines","Differdange",2020,2020,22,24,"2020-05-30","00:00:00","2020-06-08","04:00:00","10 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF8","Luxembourg-Kleinbettingen","< >","Bertrange","Kleinbettingen",2020,2020,28,30,"2019-07-11","01:00:00","2019-07-27","01:00:00","16 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF9","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2020,2020,31,32,"2020-08-02","00:00:00","2020-08-03","00:00:00","1 day","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF10","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2020,2020,32,33,"2020-08-09","00:00:00","2020-08-10","00:00:00","1 day","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF11","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2020,2020,33,34,"2020-08-15","00:00:00","2020-08-17","00:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF12","Luxembourg-Bettembourg","< >","Luxembourg","Berchem",2020,2020,36,37,"2020-09-05","00:00:00","2020-09-07","00:00:00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF13","Luxembourg-Bettembourg","< >","Luxembourg","Berchem",2020,2020,37,38,"2020-09-12","00:00:00","2020-09-14","00:00:00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF14","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2020,2020,38,39,"2020-09-19","01:30:00","2020-09-21","04:00:00","2 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF15","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2020,2020,43,44,"2020-10-24","01:30:00","2020-10-26","04:00:00","2 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF16","Rodange-Bettembourg","< >","Belval-Usines","Pétange",2020,2020,44,46,"2020-10-31","01:00:00","2020-11-09","04:00:00","9 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF17","Luxembourg-Kleinbettingen","< >","Bertrange","Kleinbettingen",2020,2020,44,46,"2020-10-31","01:00:00","2020-11-09","01:00:00","9 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF18","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2021,2021,6,8,"2021-02-13","04:00:00","2021-02-22","04:00:00","9 days","Night/Day","new line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF19","Luxembourg-Bettembourg","< >","Luxembourg-Hollerich","Luxembourg-triage",2021,2021,9,10,"2021-03-07","00:00:00","2021-03-08","04:00:00","28 hours","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF20","Luxembourg-Bettembourg","< >","Luxembourg-Hollerich","Luxembourg-triage",2021,2021,10,11,"2021-03-14","00:00:00","2021-03-15","04:00:00","28 hours","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF21","Luxembourg-Bettembourg","< >","Luxembourg-Hollerich","Luxembourg-triage",2021,2021,11,12,"2021-03-21","00:00:00","2021-03-22","04:00:00","28 hours","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF22","Luxembourg-Bettembourg","< >","Luxembourg-Hollerich","Luxembourg-triage",2021,2021,12,13,"2021-03-28","00:00:00","2021-03-29","04:00:00","28 hours","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF23","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,13,16,"2021-04-03","04:00:00","2021-04-19","04:00:00","9 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF24","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,16,17,"2021-04-24","04:00:00","2021-04-26","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF25","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,17,18,"2021-05-01","04:00:00","2021-05-03","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF26","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,18,19,"2021-05-08","04:00:00","2021-05-10","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF27","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,19,20,"2021-05-15","04:00:00","2021-05-17","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF28","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2021,2021,20,21,"2021-05-22","01:00:00","2021-05-25","04:00:00","3 days","Night/Day","underpass renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF29","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,22,23,"2021-06-05","04:00:00","2021-06-07","04/00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF30","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,23,24,"2021-06-12","01:30:00","2021-06-14","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF31","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,24,25,"2021-06-19","01:30:00","2021-06-21","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF32","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,25,26,"2021-06-26","01:30:00","2021-06-28","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF33","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,26,27,"2021-07-03","01:30:00","2021-07-05","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF34","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,26,27,"2021-07-03","01:30:00","2021-07-05","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF35","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,27,28,"2021-07-10","01:30:00","2021-07-12","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF36","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,27,28,"2021-07-10","01:30:00","2021-07-12","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF37","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,28,29,"2021-07-17","04:00:00","2021-07-19","04/00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF38","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,29,30,"2021-07-24","04:00:00","2021-07-26","04/00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF39","Rodange-Bettembourg","< >","Esch/Alzette","Noertzange",2021,2021,34,37,"2021-08-28","00:00:00","2021-09-13","04:00:00","17 days","Night/Day","brigde maintenance/renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF40","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,34,37,"2021-08-28","00:00:00","2021-09-13","04:00:00","17 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF41","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,37,38,"2021-09-18","04:00:00","2021-09-20","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF42","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,38,39,"2021-09-25","04:00:00","2021-09-27","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF43","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,39,40,"2021-10-02","01:30:00","2021-10-04","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF44","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,40,41,"2021-10-09","01:30:00","2021-10-11","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF45","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,41,42,"2021-10-16","04:00:00","2021-10-18","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF46","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,42,43,"2021-10-23","04:00:00","2021-10-25","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF47","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2021,2021,43,45,"2021-10-30","00:00:00","2021-11-08","04:00:00","9 days","Night/Day","switch renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF48","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2021,2021,43,44,"2021-10-30","00:00:00","2021-11-02","04:00:00","3 days","Night/Day","underpass renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]