{"text_format":"1","workbook":"xlsx","n_sheets":8,"sheets":["Home","Main Impact Map","ProRail","Infrabel","Data","SNCFR","SBB","ACF CFL"],"not_rendered":{"charts":0,"images":11,"macros":1,"external_links":7,"defined_names":63,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Home","index":0,"n_rows":18,"n_cols":15,"rows_kept":18,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"! click icon to follow !"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["                              version 17 December 2019"]

{"sheet":"Main Impact Map","index":1,"n_rows":15,"n_cols":14,"rows_kept":15,"cut":false,"hidden":false,"merged":[[45,5,46,7]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Main TCR for TT 2020 to TT 2022"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"2019-12-17"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"click on              for detailed TCR information"]

{"sheet":"ProRail","index":2,"n_rows":416,"n_cols":31,"rows_kept":416,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["ProRail","IO-K-006631-wk01-00",".","< >","Waalhaven Zuid","Waalhaven Zuid",2020,2020,1,2,"2020-01-02","23:00:00","2020-01-07","23:00:00","120:00","continuous","Miscellaneous","T","ST",null,null,null,null,"",null,null,null,"Vernieuwen KRSWL Waalhaven",null,"N","K-006631"]
["ProRail","IO-K-B17018-00pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,2,2,"2020-01-06","07:00:00","2020-01-10","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,2,2,"2020-01-06","07:00:00","2020-01-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,2,2,"2020-01-06","07:00:00","2020-01-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,2,2,"2020-01-06","07:00:00","2020-01-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-L-005095-2010-00",".",">","Amsterdam Amstel","Watergraafsmeer Oost aansl.",2020,2020,2,2,"2020-01-11","07:00:00","2020-01-12","23:00:00","40:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"LDV balken 2/79-2/80, 2/101-2/102-2/103, 2/113-2/114+ verv balk 2/127-2/128 + noodmaatregel balk 2/92 PVE-8",null,"Y","L-005095"]
["ProRail","IO-K-B17018-2001-00",".","< >","Betuweroute Giessendam","Kijfhoek zuid",2020,2020,3,4,"2020-01-18","02:00:00","2020-01-22","02:00:00","96:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Sophia tunnel",null,"Y","K-B17018"]
["ProRail","IO-K-B17018-01b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,3,3,"2020-01-13","07:00:00","2020-01-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-01b2-00",".",">","Botlek","Botlek",2020,2020,3,3,"2020-01-13","07:00:00","2020-01-18","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,3,3,"2020-01-13","07:00:00","2020-01-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,3,3,"2020-01-13","07:00:00","2020-01-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,3,3,"2020-01-13","07:00:00","2020-01-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-497500-2003-00",".","< >","Botlek","Europoort",2020,2020,4,5,"2020-01-25","23:00:00","2020-01-27","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Werkzaamheden aan / tbv de onderbouw van het nieuwe Theemswegtracé.",null,"Y","R-497500"]
["ProRail","IO-R-497500-2006-00",".","< >","Botlek racc.Theemsweg","Botlek Theemsweg aansl.",2020,2020,4,5,"2020-01-25","23:00:00","2020-01-28","03:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Werkzaamheden onderbouw aannemer (Save). Aanbrengen damwanden en fundaties. Zo nodig spooronderhoud.",null,"Y","R-497500"]
["ProRail","IO-R-523400-2001-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,4,5,"2020-01-25","23:00:00","2020-01-27","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Bouw kunstwerken over spoor tbv aanleg CER.",null,"Y","R-523400"]
["ProRail","IO-K-005836-FH19-00",".",">","Maasvlakte aansl.","Maasvlakte empl. West west",2020,2020,4,4,"2020-01-26","07:00:00","2020-01-26","23:00:00","16:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Plaatsen lichtmast 2, herstellen lichtmast 1 Groep 1770",null,"N","K-005836"]
["ProRail","IO-K-B17018-01eu-00",".",">","Europoort","Europoort West",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-24","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-01m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-24","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-F38H-00",".",">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2020,2020,4,5,"2020-01-25","23:00:00","2020-01-27","07:00:00","32:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Uitgraven klappers bij wissels Mvtyn",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij02-00",".",">","IJsselmonde","IJsselmonde",2020,2020,4,4,"2020-01-20","07:00:00","2020-01-24","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-006610-2055-00",".","< >","Baanhoekbrug o/d Beneden-Merwede - bij Sliedrecht","Wantijbrug - bij Dordrecht",2020,2020,5,6,"2020-02-01","01:05:00","2020-02-03","05:05:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"wissels: -1169 -1173B -1155A -1115B",null,"Y","K-006610"]
["ProRail","IO-M-004701-2001-00",".","< >","Markbrug - tussen Zevenbergen en Oudenbosch","Zevenbergen inhaalsp.",2020,2020,5,6,"2020-02-01","01:20:00","2020-02-03","05:20:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen e-componenten Markbrug",null,"Y","M-004701"]
["ProRail","IO-Z-906106-LZ01-01",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2020,2020,5,6,"2020-02-01","01:20:00","2020-02-03","05:20:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-K-B17018-01wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,5,5,"2020-01-27","07:00:00","2020-01-31","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,5,5,"2020-01-27","07:00:00","2020-02-01","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,5,5,"2020-01-27","07:00:00","2020-02-01","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,5,5,"2020-01-27","07:00:00","2020-02-01","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo02-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,5,5,"2020-01-27","07:00:00","2020-01-31","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww02-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,5,5,"2020-01-27","07:00:00","2020-01-31","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-Z-906057-RSD3-02",".",">","Roosendaal","Roosendaal",2020,2020,5,6,"2020-02-01","01:20:00","2020-02-03","05:20:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden van perron 4",null,"Y","Z-906057"]
["ProRail","IO-Z-906310-I200-00",".",">","Roosendaal","Roosendaal",2020,2020,5,5,"2020-01-27","08:00:00","2020-01-31","16:00:00","104:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Oversteken van materieel en materiaal naar perron 2 t.b.v. renovatie werkzaamheden van Abri's, wachtruimtes e.d..",null,"N","Z-906310"]
["ProRail","IO-K-B17018-01pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,6,6,"2020-02-03","07:00:00","2020-02-07","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,6,6,"2020-02-03","07:00:00","2020-02-08","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,6,6,"2020-02-03","07:00:00","2020-02-08","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,6,6,"2020-02-03","07:00:00","2020-02-08","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-Z-906310-I201-00",".",">","Roosendaal","Roosendaal",2020,2020,6,6,"2020-02-03","08:00:00","2020-02-07","16:00:00","104:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Oversteken van materieel en materiaal naar perron 2 t.b.v. renovatie werkzaamheden van Abri's, wachtruimtes e.d..",null,"N","Z-906310"]
["ProRail","IO-K-B17018-02b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,7,7,"2020-02-10","07:00:00","2020-02-15","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-02b2-00",".",">","Botlek","Botlek",2020,2020,7,7,"2020-02-10","07:00:00","2020-02-15","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,7,7,"2020-02-10","07:00:00","2020-02-15","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,7,7,"2020-02-10","07:00:00","2020-02-15","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,7,7,"2020-02-10","07:00:00","2020-02-15","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-02eu-00",".",">","Europoort","Europoort West",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-21","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-02m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-21","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-22","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-22","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-22","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij03-00",".",">","IJsselmonde","IJsselmonde",2020,2020,8,8,"2020-02-17","07:00:00","2020-02-21","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-l-005011-POA3-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,8,9,"2020-02-21","19:00:00","2020-02-24","05:00:00","58:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Asfalteerwerkzaamheden Vlothavenweg - Amsterdam Westhaven",null,"N","l-005011"]
["ProRail","IO-R-497500-2007-00",".",">","Botlek racc.Theemsweg","Botlek Theemsweg aansl.",2020,2020,8,9,"2020-02-22","23:00:00","2020-02-25","03:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Werkzaamheden onderbouw aannemer (Save). Aanbrengen damwanden en fundaties. Zo nodig spooronderhoud.",null,"N","R-497500"]
["ProRail","IO-K-006630-1915-03",".",">","Europoort","Suurhoffbrug o/h Hartelkanaal",2020,2020,9,10,"2020-02-29","23:00:00","2020-03-02","07:00:00","32:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"vernieuwen spoor en wissels",null,"N","K-006630"]
["ProRail","IO-K-B17018-02wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-28","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-29","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-29","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-29","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo03-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-28","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww03-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,9,9,"2020-02-24","07:00:00","2020-02-28","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-l-005011-POA4-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,9,10,"2020-02-28","19:00:00","2020-03-02","05:00:00","58:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Asfalteerwerkzaamheden Vlothavenweg - Amsterdam Westhaven",null,"N","l-005011"]
["ProRail","IO-M-004701-2002-00",".","< >","Markbrug - tussen Zevenbergen en Oudenbosch","Zevenbergen inhaalsp.",2020,2020,10,11,"2020-03-07","01:20:00","2020-03-09","05:20:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen e-componenten Markbrug",null,"Y","M-004701"]
["ProRail","IO-Z-906106-LZ01-02",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2020,2020,10,11,"2020-03-07","01:20:00","2020-03-09","05:20:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-K-B17018-02pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,10,10,"2020-03-02","07:00:00","2020-03-06","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,10,10,"2020-03-02","07:00:00","2020-03-07","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,10,10,"2020-03-02","07:00:00","2020-03-07","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,10,10,"2020-03-02","07:00:00","2020-03-07","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-FI0000-1994-00",".",">","Gouda","Moordrecht overloopw.",2020,2020,10,11,"2020-03-07","01:00:00","2020-03-09","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"bouwen fietsenstalling",null,"Y","R-FI0000"]
["ProRail","IO-Z-906057-RSD3-01",".",">","Roosendaal","Roosendaal",2020,2020,10,11,"2020-03-07","01:20:00","2020-03-09","05:20:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden van perron 4",null,"Y","Z-906057"]
["ProRail","IO-K-006017-1906-00",".",">","Gouda","Gouda Goverwelle",2020,2020,11,12,"2020-03-14","01:00:00","2020-03-16","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"reconstructie kabeltracé, verwijderen kabelkokers.",null,"Y","K-006017"]
["ProRail","IO-K-B17018-03b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,11,11,"2020-03-09","07:00:00","2020-03-14","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03b2-00",".",">","Botlek","Botlek",2020,2020,11,11,"2020-03-09","07:00:00","2020-03-14","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,11,11,"2020-03-09","07:00:00","2020-03-14","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,11,11,"2020-03-09","07:00:00","2020-03-14","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,11,11,"2020-03-09","07:00:00","2020-03-14","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-404600-1970-00",".",">","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2020,2020,11,12,"2020-03-14","01:00:00","2020-03-16","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"upgrade Rotterdam Noord",null,"N","R-404600"]
["ProRail","IO-R-497500-2008-00",".","< >","Botlek racc.Theemsweg","Botlek Theemsweg aansl.",2020,2020,12,12,"2020-03-21","12:00:00","2020-03-22","20:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Werkzaamheden onderbouw aannemer (Save). Aanbrengen damwanden en fundaties. Zo nodig spooronderhoud.",null,"Y","R-497500"]
["ProRail","IO-K-006002-GK03-00",".",">","Kijfhoek aansluiting noord","Kijfhoek zuid",2020,2020,12,13,"2020-03-21","02:00:00","2020-03-23","22:00:00","68:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Kijfhoef vervanging W03",null,"N","K-006002"]
["ProRail","IO-K-B17018-03eu-00",".",">","Europoort","Europoort West",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-20","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-03m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-20","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-13m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-21","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-13m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-21","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-13th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-21","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij04-00",".",">","IJsselmonde","IJsselmonde",2020,2020,12,12,"2020-03-16","07:00:00","2020-03-20","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-006021-RTD2-00",".",">","Delfshaven Schiebrug aansl.","Willemstunnel Zuid",2020,2020,13,14,"2020-03-28","00:40:00","2020-03-30","05:40:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"BBV RTD - Vernieuwen sporen 1M, 2M, 3M, wissels 231, 233, 341, 347",null,"Y","K-006021"]
["ProRail","IO-K-006608-2003-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,13,14,"2020-03-28","01:09:00","2020-03-30","05:09:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afronden vluchtpadverlichting HJ",null,"Y","K-006608"]
["ProRail","IO-K-B17018-03wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-27","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-14m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-28","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-14m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-28","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-14th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-28","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo04-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-27","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww04-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,13,13,"2020-03-23","07:00:00","2020-03-27","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-L-005092-2003-00",".",">","Amsterdam Centraal","Singelgrachtbrug",2020,2020,13,13,"2020-03-28","02:00:00","2020-03-29","00:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Uitvoeren taludverbetering",null,"Y","L-005092"]
["ProRail","IO-R-520045-2013-00",".",">","Oudenbosch","Oudenbosch",2020,2020,13,13,"2020-03-28","00:00:00","2020-03-28","22:00:00","22:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Aanpassen overweg 15.4 binnen bevloering",null,"N","R-520045"]
["ProRail","IO-K-006610-2057-00",".",">","Dordrecht","Dordrecht",2020,2020,14,15,"2020-04-04","01:00:00","2020-04-06","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"wissel 1241 spoor 21;20; 43b",null,"Y","K-006610"]
["ProRail","IO-K-B17018-03pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,14,14,"2020-03-30","07:00:00","2020-04-03","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-15m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,14,14,"2020-03-30","07:00:00","2020-04-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-15m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,14,14,"2020-03-30","07:00:00","2020-04-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-15th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,14,14,"2020-03-30","07:00:00","2020-04-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-L-005092-2001-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,14,14,"2020-04-04","02:00:00","2020-04-05","10:00:00","32:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen schouwpaden",null,"N","L-005092"]
["ProRail","IO-L-005189-2001-00",".",">","Amsterdam Transformatorweg aansl.","Amsterdam Zaanstraat",2020,2020,14,15,"2020-04-04","01:20:00","2020-04-06","05:20:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen wisselliggers en vernieuwen dwarsliggers Zaanstraat.",null,"Y","L-005189"]
["ProRail","IO-R-3AE009-2001-00",".",">","Amsterdam Transformatorweg aansl.","Amsterdam Zaanstraat",2020,2020,14,15,"2020-04-04","01:20:00","2020-04-06","05:20:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Diverse werkzaamheden Westhaven Amsterdam. Verwijzing van de werkzaamheden, zie TVP aanvraagformulier 1.",null,"Y","R-3AE009"]
["ProRail","IO-R-3AE009-2016-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,14,14,"2020-04-01","08:00:00","2020-04-04","01:00:00","65:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Verlengen Spoor 2264 en verplaatsen inrit.",null,"N","R-3AE009"]
["ProRail","IO-R-497500-2009-00",".",">","Botlek racc.Theemsweg","Botlek Theemsweg aansl.",2020,2020,14,15,"2020-04-04","01:00:00","2020-04-06","09:00:00","56:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Werkzaamheden onderbouw aannemer (Save). Aanbrengen damwanden en fundaties. Zo nodig spooronderhoud.",null,"N","R-497500"]
["ProRail","IO-R-539100-2001-00",".",">","Gouda","Gouda",2020,2020,14,15,"2020-04-05","00:00:00","2020-04-06","00:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"aanbrengen zettingsvrije plaat.",null,"N","R-539100"]
["ProRail","IO-K-006305-2001-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2020,2020,15,16,"2020-04-11","19:00:00","2020-04-13","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"werzaamheden Calandbrug",null,"Y","K-006305"]
["ProRail","IO-K-006610-2051-00",".","< >","Dordrecht","Willemsdorp",2020,2020,15,16,"2020-04-11","01:35:00","2020-04-14","05:35:00","76:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"wissels: -121A -121B -123A -123B -spoor 34,35,36",null,"Y","K-006610"]
["ProRail","IO-K-006630-2020-00",".","< >","Europoort West","Suurhoffbrug o/h Hartelkanaal",2020,2020,15,16,"2020-04-11","19:00:00","2020-04-13","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vernieuwen wissels en sporen",null,"Y","K-006630"]
["ProRail","IO-K-B17018-2005-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2020,2020,15,15,"2020-04-11","23:00:00","2020-04-12","23:00:00","24:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"TTI Botlektunnel",null,"Y","K-B17018"]
["ProRail","IO-L-005189-2018-00",".","< >","Erasmusgracht aansl.","Zaandam",2020,2020,15,16,"2020-04-11","02:20:00","2020-04-13","05:20:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen dwarsliggers en spoorstaven in diverse sporen",null,"Y","L-005189"]
["ProRail","IO-R-464700-Mv01-00",".","< >","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,15,16,"2020-04-11","19:00:00","2020-04-13","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"30 lichtmasten voorzien van nieuwe armaturen",null,"Y","R-464700"]
["ProRail","IO-R-497500-2001-00",".","< >","Botlek","Europoort",2020,2020,15,16,"2020-04-11","19:00:00","2020-04-13","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Werkzaamheden aan / tbv de onderbouw van het nieuwe Theemswegtracé.",null,"Y","R-497500"]
["ProRail","IO-R-523400-2004-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,15,16,"2020-04-11","19:00:00","2020-04-13","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Bouw kunstwerken over spoor tbv aanleg CER.",null,"Y","R-523400"]
["ProRail","IO-Z-906106-LZ04-01",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2020,2020,15,16,"2020-04-11","01:00:00","2020-04-13","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-K-006002-2001-00",".",">","Kijfhoek aansluiting noord","Kijfhoek zuid",2020,2020,15,16,"2020-04-11","23:00:00","2020-04-14","03:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"werkplek 7: Vernieuwen wissels 2353A vernieuwen spoor tussen vk wissel 3759 en vk wissel 3781A rechtzetten 4 stuks BVL portalen",null,"N","K-006002"]
["ProRail","IO-K-006002-W07-00",".",">","Kijfhoek aansluiting noord","Kijfhoek zuid",2020,2020,15,16,"2020-04-11","19:00:00","2020-04-13","23:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"werkplek 7: Vernieuwen wissels 2353A vernieuwen spoor tussen vk wissel 3759 en vk wissel 3781A rechtzetten 4 stuks BVL portalen",null,"Y","K-006002"]
["ProRail","IO-K-006031-2002-00",".",">","Dordrecht","Dordrecht",2020,2020,15,15,"2020-04-06","01:00:00","2020-04-11","01:00:00","120:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Ontvangst en boorput ivm gestuurde boring km 29.490, boring uitvoeren, drainage spoor 21 aanleggen en meer",null,"Y","K-006031"]
["ProRail","IO-K-006031-2003-00",".",">","Dordrecht","Dordrecht",2020,2020,15,16,"2020-04-11","01:00:00","2020-04-13","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Ontvangst en boorput ivm gestuurde boring km 29.490, boring uitvoeren, drainage spoor 21 aanleggen en meer",null,"Y","K-006031"]
["ProRail","IO-K-006630-2009-01",".",">","Botlek","Botlek",2020,2020,15,16,"2020-04-11","19:00:00","2020-04-13","23:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen spoor, spoorstaven en overwegbevloeringen.",null,"Y","K-006630"]
["ProRail","IO-K-B17018-04b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,15,15,"2020-04-06","07:00:00","2020-04-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04b2-00",".",">","Botlek","Botlek",2020,2020,15,15,"2020-04-06","07:00:00","2020-04-11","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-16m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,15,15,"2020-04-06","07:00:00","2020-04-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-16m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,15,15,"2020-04-06","07:00:00","2020-04-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-16th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,15,15,"2020-04-06","07:00:00","2020-04-11","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-3AE009-2017-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,15,20,"2020-04-06","07:00:00","2020-05-11","07:00:00","840:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Voorbereidende werkzaamheden voor het verplaatsen Loc/Opstel Sporen.",null,"N","R-3AE009"]
["ProRail","IO-R-505000-EV02-00",".",">","Dordrecht","Zwijndrecht",2020,2020,15,16,"2020-04-11","01:00:00","2020-04-13","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"Saneren kruiswissel 1195A/B-1197A/B te Dordrecht Saneren wisseloverlopen 1335A/B en 1347A/B",null,"Y","R-505000"]
["ProRail","IO-K-006031-2004-00",".",">","Dordrecht","Dordrecht",2020,2020,16,16,"2020-04-13","05:00:00","2020-04-15","05:00:00","48:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Ontvangst en boorput ivm gestuurde boring km 29.490, boring uitvoeren, drainage spoor 21 aanleggen en meer",null,"Y","K-006031"]
["ProRail","IO-K-006630-2019-00",".",">","Maasvlakte","Maasvlakte",2020,2020,16,16,"2020-04-13","23:00:00","2020-04-18","05:00:00","102:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen dwarsliggers en ballast in diverse sporen",null,"Y","K-006630"]
["ProRail","IO-K-B17018-04eu-00",".",">","Europoort","Europoort West",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-17","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-17","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-17m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-17m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-17th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-18","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij05-00",".",">","IJsselmonde","IJsselmonde",2020,2020,16,16,"2020-04-13","07:00:00","2020-04-17","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-04wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-24","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-18m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-18m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-18th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-25","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo05-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-24","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww05-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,17,17,"2020-04-20","07:00:00","2020-04-24","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-Z-906057-RSD2-01",".",">","Roosendaal","Roosendaal",2020,2020,17,18,"2020-04-25","01:10:00","2020-04-27","05:10:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden van perron 3",null,"Y","Z-906057"]
["ProRail","IO-K-006608-2004-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,18,19,"2020-05-02","01:10:00","2020-05-04","04:10:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afronden vluchtpadverlichting HJ",null,"Y","K-006608"]
["ProRail","IO-K-B17018-04pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,18,18,"2020-04-27","07:00:00","2020-05-01","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-19m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,18,18,"2020-04-27","07:00:00","2020-05-02","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-19m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,18,18,"2020-04-27","07:00:00","2020-05-02","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-19th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,18,18,"2020-04-27","07:00:00","2020-05-02","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-465700-IO01-00",".",">","Rail Service Center Waalhaven","Rail Service Center Waalhaven aansl.",2020,2020,18,19,"2020-05-02","15:00:00","2020-05-04","15:00:00","48:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Westzijde RSC terminal sp 401/402 aanpassen door verplaatsen wsl 803A/803B naar het oosten, meer info zie werkplek A",null,"Y","R-465700"]
["ProRail","IO-K-B17018-05b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,19,19,"2020-05-04","07:00:00","2020-05-09","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05b2-00",".",">","Botlek","Botlek",2020,2020,19,19,"2020-05-04","07:00:00","2020-05-09","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-20m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,19,19,"2020-05-04","07:00:00","2020-05-09","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-20m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,19,19,"2020-05-04","07:00:00","2020-05-09","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-20th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,19,19,"2020-05-04","07:00:00","2020-05-09","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-006630-2003-00",".",">","Pernis","Pernis",2020,2020,20,21,"2020-05-16","07:00:00","2020-05-18","07:00:00","48:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoor, dwarsliggers en saneren wissels",null,"Y","K-006630"]
["ProRail","IO-K-B17018-05eu-00",".",">","Europoort","Europoort West",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-15","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-05m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-15","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-21m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-16","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-21m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-16","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-21th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-16","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij06-00",".",">","IJsselmonde","IJsselmonde",2020,2020,20,20,"2020-05-11","07:00:00","2020-05-15","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-3AE009-2018-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,20,23,"2020-05-11","07:00:00","2020-06-06","01:00:00","618:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Voorbereidende werkzaamheden voor het verplaatsen Loc/Opstel Sporen.",null,"N","R-3AE009"]
["ProRail","IO-K-006610-2052-00",".","< >","Dordrecht","Willemsdorp",2020,2020,21,21,"2020-05-21","01:20:00","2020-05-24","05:20:00","76:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"wissels: 1113A 1113B 1111",null,"Y","K-006610"]
["ProRail","IO-K-B17018-05wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-22","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-22m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-23","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-22m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-23","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-22th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-23","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo06-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-22","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww06-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,21,21,"2020-05-18","07:00:00","2020-05-22","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-006305-2002-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2020,2020,22,23,"2020-05-30","19:00:00","2020-06-01","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"werzaamheden Calandbrug",null,"Y","K-006305"]
["ProRail","IO-K-006630-2016-00",".","< >","Europoort","Suurhoffbrug o/h Hartelkanaal",2020,2020,22,23,"2020-05-30","19:00:00","2020-06-01","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen spoor en wissels",null,"Y","K-006630"]
["ProRail","IO-R-464700-Mv02-00",".","< >","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,22,23,"2020-05-30","19:00:00","2020-06-01","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"30 lichtmasten voorzien van nieuwe armaturen",null,"Y","R-464700"]
["ProRail","IO-R-485800-2001-00",".","< >","Moerdijk","Lage Zwaluwe",2020,2020,22,23,"2020-05-30","01:00:00","2020-06-01","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Aanpassen overwegen  Moerdijk A, B en C",null,"Y","R-485800"]
["ProRail","IO-R-497500-2002-00",".","< >","Botlek","Europoort",2020,2020,22,23,"2020-05-30","19:00:00","2020-06-01","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Werkzaamheden aan / tbv de onderbouw van het nieuwe Theemswegtracé.",null,"Y","R-497500"]
["ProRail","IO-R-523400-2003-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,22,23,"2020-05-30","19:00:00","2020-06-01","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Bouw kunstwerken over spoor tbv aanleg CER.",null,"Y","R-523400"]
["ProRail","IO-Z-906106-LZ04-02",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2020,2020,22,23,"2020-05-30","01:15:00","2020-06-01","05:15:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-K-006630-2009-02",".",">","Botlek","Botlek",2020,2020,22,23,"2020-05-30","19:00:00","2020-06-01","23:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen spoor, spoorstaven en overwegbevloeringen.",null,"Y","K-006630"]
["ProRail","IO-K-B17018-05pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,22,22,"2020-05-25","07:00:00","2020-05-29","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-23m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,22,22,"2020-05-25","07:00:00","2020-05-30","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-23m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,22,22,"2020-05-25","07:00:00","2020-05-30","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-23th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,22,22,"2020-05-25","07:00:00","2020-05-30","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-L-005189-2002-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Zaanstraat",2020,2020,23,24,"2020-06-06","01:00:00","2020-06-08","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vernieuwen wisselliggers: wissel 987, 986, 985, 983, 979.",null,"Y","L-005189"]
["ProRail","IO-L-005189-2003-00",".","< >","Amsterdam Westhaven","Amsterdam Westhaven",2020,2020,23,24,"2020-06-06","01:00:00","2020-06-08","05:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"",null,null,null,"Vernieuwen wisselliggers wissel 60",null,"Y","L-005189"]
["ProRail","IO-R-3AE009-2002-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Zaanstraat",2020,2020,23,24,"2020-06-06","01:00:00","2020-06-08","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Diverse werkzaamheden Westhaven Amsterdam. Verwijzing van de werkzaamheden, zie TVP aanvraagformulier 2.",null,"Y","R-3AE009"]
["ProRail","IO-K-B17018-06b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,23,23,"2020-06-01","07:00:00","2020-06-06","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06b2-00",".",">","Botlek","Botlek",2020,2020,23,23,"2020-06-01","07:00:00","2020-06-06","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-24m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,23,23,"2020-06-01","07:00:00","2020-06-06","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-24m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,23,23,"2020-06-01","07:00:00","2020-06-06","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-24th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,23,23,"2020-06-01","07:00:00","2020-06-06","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-L-005092-2002-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven West",2020,2020,23,23,"2020-06-07","00:00:00","2020-06-07","14:00:00","14:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen schouwpaden",null,"Y","L-005092"]
["ProRail","IO-K-006610-2058-00",".","< >","Dordrecht","Dordrecht",2020,2020,24,25,"2020-06-13","01:10:00","2020-06-15","05:10:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"R",null,null,null,"wissels: 1163 1155A 1153A",null,"Y","K-006610"]
["ProRail","IO-K-006630-2004-00",".",">","Pernis","Pernis",2020,2020,24,24,"2020-06-12","16:00:00","2020-06-14","04:00:00","36:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen wissel en overwegbevloering",null,"Y","K-006630"]
["ProRail","IO-K-006630-2005-00",".",">","Pernis","Pernis",2020,2020,24,25,"2020-06-14","04:00:00","2020-06-15","08:00:00","28:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen wissel 328",null,"Y","K-006630"]
["ProRail","IO-K-B17018-06eu-00",".",">","Europoort","Europoort West",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-12","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Europoort  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06m1-00",".",">","Maasvlakte","Maasvlakte Europahaven zuid",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-12","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Maasvlakte  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-25m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-13","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-25m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-13","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-25th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-13","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij07-00",".",">","IJsselmonde","IJsselmonde",2020,2020,24,24,"2020-06-08","07:00:00","2020-06-12","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-474300-2001-00",".","< >","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2020,2020,25,27,"2020-06-20","00:00:00","2020-06-29","00:00:00","216:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Wijzigen en testen EBS i.v.m. goederen overdrachtspoor",null,"Y","R-474300"]
["ProRail","IO-K-006017-1908-00",".",">","Gouda","Gouda",2020,2020,25,26,"2020-06-20","01:00:00","2020-06-22","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"reconstructie kabeltracé, verwijderen kabelkokers.",null,"Y","K-006017"]
["ProRail","IO-K-006630-2006-00",".",">","Botlek","Botlek",2020,2020,25,26,"2020-06-20","12:00:00","2020-06-22","07:00:00","43:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoor en wissels en saneren van een wissel",null,"Y","K-006630"]
["ProRail","IO-K-B17018-06wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-19","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-26m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-20","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-26m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-20","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-26th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-20","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo07-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-19","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww07-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,25,25,"2020-06-15","07:00:00","2020-06-19","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-06pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,26,26,"2020-06-22","07:00:00","2020-06-26","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-27m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,26,26,"2020-06-22","07:00:00","2020-06-27","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-27m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,26,26,"2020-06-22","07:00:00","2020-06-27","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-27th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,26,26,"2020-06-22","07:00:00","2020-06-27","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-006630-2007-00",".",">","Botlek","Botlek",2020,2020,27,28,"2020-07-05","22:10:00","2020-07-08","02:10:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoor en wissels",null,"Y","K-006630"]
["ProRail","IO-K-B17018-07b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,27,27,"2020-06-29","07:00:00","2020-07-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-07b2-00",".",">","Botlek","Botlek",2020,2020,27,27,"2020-06-29","07:00:00","2020-07-04","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-28m2-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,27,27,"2020-06-29","07:00:00","2020-07-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM Aanleg Cer-Route - Kunstwerk West WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-28m3-00",".",">","Maasvlakte Prinses Amaliahaven","Maasvlakte West terminal Noord",2020,2020,27,27,"2020-06-29","07:00:00","2020-07-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM WBI Aanleg Cer-Route - Kunstwerk Noord en Zuid WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-28th-00",".",">","Botlek","Botlek Theemsweg aansl.",2020,2020,27,27,"2020-06-29","07:00:00","2020-07-04","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Theemsweg WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij08-00",".",">","IJsselmonde","IJsselmonde",2020,2020,28,28,"2020-07-06","07:00:00","2020-07-10","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-2AE001-2001-00",".","< >","Amsterdam Amstel","Duivendrecht",2020,2020,29,31,"2020-07-14","00:00:00","2020-07-30","04:00:00","388:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Realiseren nieuw stijgpunt met tunnel in het eerste perron van station Amsterdam Amstel.",null,"Y","R-2AE001"]
["ProRail","IO-R-3AE009-2003-00",".","< >","Abcoude","Watergraafsmeer West aansl.",2020,2020,29,30,"2020-07-14","02:00:00","2020-07-26","02:00:00","288:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Diverse werkzaamheden PHS Amsterdam Muiderpoort.",null,"Y","R-3AE009"]
["ProRail","IO-R-550020-2001-00",".","< >","Amsterdam Amstel","Duivendrecht",2020,2020,29,31,"2020-07-14","00:00:00","2020-07-30","04:00:00","388:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Verw. bovenbouw, verschuiven bvl, aanbrengen grondkeringen, terugbouwen bovenbouw/hermonteren BVL, inschuiven dek.",null,"Y","R-550020"]
["ProRail","IO-K-006630-2011-01",".",">","Europoort","Europoort",2020,2020,29,29,"2020-07-18","23:00:00","2020-07-19","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen sporen, wissels en wisselliggers.",null,"Y","K-006630"]
["ProRail","IO-K-B17018-07wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,29,29,"2020-07-13","07:00:00","2020-07-17","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo08-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,29,29,"2020-07-13","07:00:00","2020-07-17","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww08-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,29,29,"2020-07-13","07:00:00","2020-07-17","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-L-005189-2008-00",".",">","Abcoude","Maarssen",2020,2020,29,29,"2020-07-16","01:00:00","2020-07-17","05:00:00","28:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen dwarsliggers op diverse locaties en aanbrengen railframe",null,"Y","L-005189"]
["ProRail","IO-L-005189-2005-00",".","< >","Amsterdam Amstel","Duivendrecht",2020,2020,30,30,"2020-07-22","00:00:00","2020-07-23","16:00:00","40:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen brugdwarslliggers+regelbaar op 2 kunstwerken op beiden sporen en dwarsliggers in spoor UB",null,"Y","L-005189"]
["ProRail","IO-K-006630-2011-02",".",">","Europoort","Europoort",2020,2020,30,30,"2020-07-25","23:00:00","2020-07-26","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen sporen, wissels en wisselliggers.",null,"Y","K-006630"]
["ProRail","IO-K-B17018-07pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,30,30,"2020-07-20","07:00:00","2020-07-24","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-006630-2011-03",".",">","Europoort","Europoort",2020,2020,31,31,"2020-08-01","23:00:00","2020-08-02","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen sporen, wissels en wisselliggers.",null,"Y","K-006630"]
["ProRail","IO-K-B17018-08b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,31,31,"2020-07-27","07:00:00","2020-08-01","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-08b2-00",".",">","Botlek","Botlek",2020,2020,31,31,"2020-07-27","07:00:00","2020-08-01","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-L-005113-2002-00",".",">","Harmelen aansl.","Vleuten",2020,2020,31,32,"2020-08-02","07:00:00","2020-08-03","05:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vervangen ledseinen en matrixsignaalgever",null,"Y","L-005113"]
["ProRail","IO-Z-906237-ddr1-00",".",">","Dordrecht","Dordrecht",2020,2020,31,32,"2020-08-01","01:00:00","2020-08-03","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vervangen dakbedekking, bakgoten en verrot dakbeschot van de perronkap tussen spoor 2 en 3 te Dordrecht.",null,"Y","Z-906237"]
["ProRail","IO-K-B17018-09ij-00",".",">","IJsselmonde","IJsselmonde",2020,2020,32,32,"2020-08-03","07:00:00","2020-08-07","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-L-005189-2007-00",".",">","Abcoude","Maarssen",2020,2020,32,33,"2020-08-09","01:00:00","2020-08-10","05:00:00","28:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen dwarsliggers, aanbrengen railframe op diverse locaties",null,"Y","L-005189"]
["ProRail","IO-R-497500-2010-00",".","< >","Botlek racc.Theemsweg","Botlek Theemsweg aansl.",2020,2020,33,34,"2020-08-15","23:00:00","2020-08-18","03:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Werkzaamheden onderbouw aannemer (Save). Aanbrengen damwanden en fundaties. Zo nodig spooronderhoud.",null,"Y","R-497500"]
["ProRail","IO-K-B17018-08wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,33,33,"2020-08-10","07:00:00","2020-08-14","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo09-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,33,33,"2020-08-10","07:00:00","2020-08-14","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww09-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,33,33,"2020-08-10","07:00:00","2020-08-14","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-Z-906237-ddr2-00",".",">","Dordrecht","Dordrecht",2020,2020,33,33,"2020-08-10","01:00:00","2020-08-12","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vervangen dakbedekking, bakgoten en verrot dakbeschot van de perronkap tussen spoor 2 en 3 te Dordrecht.",null,"Y","Z-906237"]
["ProRail","IO-K-006305-2003-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2020,2020,34,35,"2020-08-22","23:00:00","2020-08-24","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"werzaamheden Calandbrug",null,"Y","K-006305"]
["ProRail","IO-K-006610-2054-00",".","< >","Dordrecht","Dordrecht",2020,2020,34,35,"2020-08-17","05:00:00","2020-08-24","05:00:00","168:00","continuous","Miscellaneous","T","ST",null,null,null,null,"",null,null,null,"wissels: 1159 1171B / 1177A 1167 / 1171A 1155B 1151/1153A 1153B 1163 1155A 1173A",null,"Y","K-006610"]
["ProRail","IO-K-006630-2017-02",".","< >","Europoort","Suurhoffbrug o/h Hartelkanaal",2020,2020,34,35,"2020-08-22","23:00:00","2020-08-24","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen spoor en wissels",null,"Y","K-006630"]
["ProRail","IO-R-523400-2005-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,34,35,"2020-08-22","23:00:00","2020-08-24","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"- Saneren Overweg 300.3 - Saneren Overweg 303.5 - Nieuwe wegaansluiting overweg 3.2",null,"Y","R-523400"]
["ProRail","IO-K-006631-IO01-00",".",">","Pernis","Waalhaven Zuid aansl Zuid",2020,2020,34,34,"2020-08-22","23:00:00","2020-08-23","23:00:00","24:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen dwarsliggers geo 950 sporen: -sp 473(RC) km 7.803-7.973 -sp 479AV (PC) km 7.859-8.027",null,"Y","K-006631"]
["ProRail","IO-K-B17018-08pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,34,34,"2020-08-17","07:00:00","2020-08-21","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-006357-2017-00",".",">","Barendrecht","Willemstunnel Zuid",2020,2020,35,35,"2020-08-27","02:00:00","2020-08-28","00:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Balken verhogen spoor KJ en LJ. Monteren 1 overspanningsafleider km 43",null,"Y","K-006357"]
["ProRail","IO-K-006357-2018-00",".",">","Barendrecht","Rotterdam Stadion",2020,2020,35,35,"2020-08-28","00:00:00","2020-08-28","22:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Ophogen balken sporen BG, HJ en JJ onder kunstwerken.",null,"Y","K-006357"]
["ProRail","IO-K-006631-IO04-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,35,36,"2020-08-27","23:00:00","2020-08-31","03:00:00","76:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"verniewen wsl 670, 671, 669A/669B, 665",null,"Y","K-006631"]
["ProRail","IO-K-B17018-09b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,35,35,"2020-08-24","07:00:00","2020-08-29","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-09b2-00",".",">","Botlek","Botlek",2020,2020,35,35,"2020-08-24","07:00:00","2020-08-29","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-006608-2002-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,36,37,"2020-09-05","00:00:00","2020-09-07","03:00:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afronden vluchtpadverlichting KL",null,"Y","K-006608"]
["ProRail","IO-K-006631-2001-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,36,36,"2020-09-05","23:00:00","2020-09-06","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen wissel 129",null,"Y","K-006631"]
["ProRail","IO-K-B17018-ij10-00",".",">","IJsselmonde","IJsselmonde",2020,2020,36,36,"2020-08-31","07:00:00","2020-09-04","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-L-005231-2001-00",".","< >","Oudewater overloopw.","Woerden Overloop",2020,2020,37,38,"2020-09-12","02:00:00","2020-09-14","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Aanleggen RIP KM 21.200 dubbelsporig",null,"Y","L-005231"]
["ProRail","IO-Z-906096-wd01-00",".","< >","Woerden","Woerden Overloop",2020,2020,37,38,"2020-09-12","02:00:00","2020-09-14","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Conserveren traverse.",null,"Y","Z-906096"]
["ProRail","IO-K-006005-2001-00",".",">","Capelle Schollevaar","Rotterdam Noord goed. West",2020,2020,37,38,"2020-09-12","00:00:00","2020-09-14","04:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Spoorvernieuwing Rtd-Gd",null,"N","K-006005"]
["ProRail","IO-K-006017-2001-00",".",">","Gouda","Moordrecht overloopw.",2020,2020,37,38,"2020-09-11","00:00:00","2020-09-14","04:00:00","76:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"BBV Gouda",null,"Y","K-006017"]
["ProRail","IO-K-B17018-09wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,37,37,"2020-09-07","07:00:00","2020-09-11","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo10-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,37,37,"2020-09-07","07:00:00","2020-09-11","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww10-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,37,37,"2020-09-07","07:00:00","2020-09-11","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-L-005189-2009-00",".",">","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2020,2020,37,38,"2020-09-12","02:00:00","2020-09-14","04:00:00","50:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen wisselliggers en ballast van diverse wissels en vernieuwen dwarsliggers en ballast in diverse sporen.",null,"Y","L-005189"]
["ProRail","IO-L-005191-2004-00",".",">","Harmelen aansl.","Vleuten",2020,2020,37,38,"2020-09-12","01:00:00","2020-09-14","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"Vernieuwen regelbare sps bev en verwijderen CL rondom kunstwerk",null,"Y","L-005191"]
["ProRail","IO-R-493300-1961-00",".",">","Gouda","Moordrecht aansl.",2020,2020,37,38,"2020-09-12","00:00:00","2020-09-14","04:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Bouw van een nieuw service- en opstelterrein voor de treindienst Gd-Apn",null,"Y","R-493300"]
["ProRail","IO-R-493300-1963-00",".",">","Gouda","Gouda",2020,2020,37,43,"2020-09-07","08:00:00","2020-10-19","08:00:00","1008:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Bouw van een nieuw service- en opstelterrein voor de treindienst Gd-Apn",null,"Y","R-493300"]
["ProRail","IO-Z-906057-RSD1-02",".",">","Roosendaal","Roosendaal",2020,2020,37,38,"2020-09-12","01:00:00","2020-09-14","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden",null,"Y","Z-906057"]
["ProRail","IO-K-006631-2002-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,38,38,"2020-09-19","23:00:00","2020-09-20","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen wissel 133",null,"Y","K-006631"]
["ProRail","IO-K-B17018-09pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,38,38,"2020-09-14","07:00:00","2020-09-18","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-Z-906057-RSD2-02",".",">","Roosendaal","Roosendaal",2020,2020,38,39,"2020-09-19","01:00:00","2020-09-21","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden van perron 3",null,"Y","Z-906057"]
["ProRail","IO-K-006630-2010-01",".","< >","Botlek","Pernis",2020,2020,39,40,"2020-09-26","23:00:00","2020-09-28","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen wissel, spoor en dwarsliggers",null,"Y","K-006630"]
["ProRail","IO-K-006630-2017-03",".","< >","Europoort","Suurhoffbrug o/h Hartelkanaal",2020,2020,39,40,"2020-09-26","23:00:00","2020-09-28","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen spoor en wissels",null,"Y","K-006630"]
["ProRail","IO-R-523400-2002-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,39,40,"2020-09-26","23:00:00","2020-09-28","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Bouw kunstwerken over spoor tbv aanleg CER.",null,"Y","R-523400"]
["ProRail","IO-K-B17018-10b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,39,39,"2020-09-21","07:00:00","2020-09-26","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-10b2-00",".",">","Botlek","Botlek",2020,2020,39,39,"2020-09-21","07:00:00","2020-09-26","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-006357-2014-00",".","< >","Barendrecht","Rotterdam Stadion",2020,2020,40,41,"2020-10-03","00:00:00","2020-10-05","04:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Wijzigingen draagconstructie Munnikensteeg Plaatsen van 4 overspanningsbeveiligingen",null,"Y","K-006357"]
["ProRail","IO-L-005189-2022-00",".","< >","Erasmusgracht aansl.","Amsterdam Sloterdijk",2020,2020,40,40,"2020-10-03","02:00:00","2020-10-04","18:00:00","40:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen spoorstaven en dwarsliggers.",null,"Y","L-005189"]
["ProRail","IO-L-005233-2001-00",".","< >","Erasmusgracht aansl.","Amsterdam Sloterdijk",2020,2020,40,41,"2020-10-03","02:00:00","2020-10-05","04:00:00","50:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Herstellen betonschade opstortblokken van viaduct te Amsterdam Sloterdijk.",null,"Y","L-005233"]
["ProRail","IO-R-550080-2001-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2020,2020,40,41,"2020-10-03","19:00:00","2020-10-05","05:00:00","34:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Plaatsen van damwanden.",null,"Y","R-550080"]
["ProRail","IO-Z-906096-ass1-00",".","< >","Erasmusgracht aansl.","Amsterdam Sloterdijk",2020,2020,40,41,"2020-10-03","00:00:00","2020-10-05","02:00:00","50:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Conserveren hout- en staalwerk tubes perron sp 11-12",null,"Y","Z-906096"]
["ProRail","IO-K-006610-2053-00",".",">","Dordrecht","Dordrecht",2020,2020,40,41,"2020-10-03","01:00:00","2020-10-05","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"wissels: - 1175 - 1185 - 1183A - 1183B - 1177B",null,"Y","K-006610"]
["ProRail","IO-K-006610-2059-00",".",">","Dordrecht","Dordrecht",2020,2020,40,40,"2020-09-29","08:00:00","2020-10-01","20:00:00","60:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"43b",null,"Y","K-006610"]
["ProRail","IO-K-007019-0001-00",".",">","Grote Draaibrug o/d Oude Maas - bij Dordrecht","Zwijndrecht",2020,2020,40,41,"2020-10-03","00:00:00","2020-10-05","00:00:00","48:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vervangen van de lagers van twee stuks omloopwielen van de Brug over de Oude Maas.",null,"Y","K-007019"]
["ProRail","IO-K-B17018-ij11-00",".",">","IJsselmonde","IJsselmonde",2020,2020,40,40,"2020-09-28","07:00:00","2020-10-02","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-006631-IO2B-00",".","< >","Waalhaven Zuid","Waalhaven Zuid",2020,2020,41,42,"2020-10-10","07:00:00","2020-10-12","11:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"",null,null,null,"-Vernieuwen wsl 609 -Vernieuwen spoortak 609R (301B)- vern ovw bevl 609R (301B)",null,"Y","K-006631"]
["ProRail","IO-K-B17018-10wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,41,41,"2020-10-05","07:00:00","2020-10-09","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo11-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,41,41,"2020-10-05","07:00:00","2020-10-09","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww11-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,41,41,"2020-10-05","07:00:00","2020-10-09","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-493300-1962-00",".",">","Gouda","Moordrecht aansl.",2020,2020,41,42,"2020-10-10","00:00:00","2020-10-12","04:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Bouw van een nieuw service- en opstelterrein voor de treindienst Gd-Apn",null,"Y","R-493300"]
["ProRail","IO-Z-906057-RSD1-01",".",">","Roosendaal","Roosendaal",2020,2020,41,42,"2020-10-10","01:00:00","2020-10-12","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Herstelwerkzaamheden aan de keerwanden",null,"Y","Z-906057"]
["ProRail","IO-L-005189-2016-00",".","< >","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2020,2020,42,43,"2020-10-17","02:00:00","2020-10-19","06:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen dwarsliggers,blokjesspoor, compensatielassen en spoorstaven",null,"Y","L-005189"]
["ProRail","IO-K-006608-2001-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,42,43,"2020-10-17","00:00:00","2020-10-19","03:00:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afronden vluchtpadverlichting KL",null,"Y","K-006608"]
["ProRail","IO-K-B17018-10pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,42,42,"2020-10-12","07:00:00","2020-10-16","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-006610-2056-00",".","< >","Dordrecht","Dordrecht",2020,2020,43,44,"2020-10-24","01:00:00","2020-10-26","04:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"R",null,null,null,"wissels: -1145A -1145B -1165",null,"Y","K-006610"]
["ProRail","IO-Z-180000-2003-00",".","< >","Breda aansl.","Roosendaal racc. Philips",2020,2020,43,43,"2020-10-24","05:00:00","2020-10-25","04:00:00","24:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen Dateq voor DOSS",null,"Y","Z-180000"]
["ProRail","IO-K-B17018-11b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,43,43,"2020-10-19","07:00:00","2020-10-24","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-11b2-00",".",">","Botlek","Botlek",2020,2020,43,43,"2020-10-19","07:00:00","2020-10-24","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ij12-00",".",">","IJsselmonde","IJsselmonde",2020,2020,44,44,"2020-10-26","07:00:00","2020-10-30","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-497500-2011-00",".",">","Botlek racc.Theemsweg","Botlek Theemsweg aansl.",2020,2020,44,44,"2020-10-31","12:00:00","2020-11-01","20:00:00","32:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Werkzaamheden onderbouw aannemer (Save). Aanbrengen damwanden en fundaties. Zo nodig spooronderhoud.",null,"Y","R-497500"]
["ProRail","IO-K-006000-2001-00",".","< >","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2020,2020,45,47,"2020-11-07","01:00:00","2020-11-16","05:00:00","220:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Saneren van wissels 101A/B, 123A/B, 141A/B, 143A/B, 255, 253 A/B, 163A/B, 959A/B, 983A/B, 985A/B + 975/977, 901AB/917AB",null,"Y","K-006000"]
["ProRail","IO-K-006630-2002-00",".",">","Waalhaven Zuid","Waalhaven Zuid aansl. Noord",2020,2020,45,46,"2020-11-08","15:00:00","2020-11-09","07:00:00","16:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen dwarsliggers en ballast",null,"N","K-006630"]
["ProRail","IO-K-B17018-11wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,45,45,"2020-11-02","07:00:00","2020-11-06","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo12-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,45,45,"2020-11-02","07:00:00","2020-11-06","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww12-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,45,45,"2020-11-02","07:00:00","2020-11-06","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-006630-2001-00",".","< >","Barendrecht aansl.","Kijfhoek zuid",2020,2020,46,46,"2020-11-14","23:00:00","2020-11-15","15:00:00","16:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen dwarsliggers",null,"Y","K-006630"]
["ProRail","IO-K-006630-2010-02",".","< >","Botlek","Pernis",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen wissel, spoor en dwarsliggers",null,"Y","K-006630"]
["ProRail","IO-R-497500-2004-00",".","< >","Botlek racc.Theemsweg","Europoort",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Werkzaamheden aan / tbv de onderbouw van het nieuwe Theemswegtracé.",null,"Y","R-497500"]
["ProRail","IO-R-523400-2006-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"- Saneren Overweg 300.3 - Saneren Overweg 303.5 - Nieuwe wegaansluiting overweg 3.2",null,"Y","R-523400"]
["ProRail","IO-Z-180001-1901-00",".","< >","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,46,47,"2020-11-14","00:00:00","2020-11-16","03:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"aanpassing besturings systeem Willemsspoortunnel",null,"Y","Z-180001"]
["ProRail","IO-K-006021-RTD4-00",".",">","Delfshavense Schie, brug o/d - bij Schiedam","Willemstunnel Zuid",2020,2020,46,47,"2020-11-13","01:00:00","2020-11-16","05:00:00","76:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"BBV RTD - Vernieuwen sporen 1M, 2M, 3M, wissels 231, 233, 341, 347",null,"Y","K-006021"]
["ProRail","IO-K-006357-2019-00",".",">","Barendrecht","Rotterdam Stadion",2020,2020,46,46,"2020-11-14","00:00:00","2020-11-14","22:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Ophogen balken sporen BG, HJ en JJ onder kunstwerken.",null,"Y","K-006357"]
["ProRail","IO-K-006357-2020-00",".",">","Barendrecht","Willemstunnel Zuid",2020,2020,46,46,"2020-11-15","00:00:00","2020-11-15","22:00:00","22:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Balken verhogen spoor KJ en LJ. Monteren 1 overspanningsafleider km 43",null,"Y","K-006357"]
["ProRail","IO-K-006608-2005-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,46,47,"2020-11-14","00:00:00","2020-11-16","03:00:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afronden vluchtpadverlichting HJ",null,"Y","K-006608"]
["ProRail","IO-K-006630-2013-00",".",">","Europoort","Europoort West",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"vernieuwen sporen, wissels en wisselliggers.",null,"Y","K-006630"]
["ProRail","IO-K-006630-2017-01",".",">","Europoort","Suurhoffbrug o/h Hartelkanaal",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"vernieuwen spoor en wissels",null,"N","K-006630"]
["ProRail","IO-K-006631-IO09-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,46,46,"2020-11-14","23:00:00","2020-11-15","23:00:00","24:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen wsl 117",null,"Y","K-006631"]
["ProRail","IO-K-B17018-11pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,46,46,"2020-11-09","07:00:00","2020-11-13","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-403700-2099-00",".",">","Botlek","Waalhaven Zuid aansl Zuid",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Indienststellen nieuwe Botlekbrug (stap 200 )",null,"Y","R-403700"]
["ProRail","IO-R-474300-2002-00",".","< >","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2020,2020,47,49,"2020-11-21","00:00:00","2020-11-30","00:00:00","216:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Wijzigen en testen EBS i.v.m. goederen overdrachtspoor",null,"Y","R-474300"]
["ProRail","IO-K-B17018-12b1-00",".",">","Botlek","Botlek Tunnel",2020,2020,47,47,"2020-11-16","07:00:00","2020-11-21","23:00:00","136:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 1",null,"N","K-B17018"]
["ProRail","IO-K-B17018-12b2-00",".",">","Botlek","Botlek",2020,2020,47,47,"2020-11-16","07:00:00","2020-11-21","23:00:00","136:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCBG Botlek 2",null,"N","K-B17018"]
["ProRail","IO-R-403700-2051-00",".",">","Botlek","Pernis",2020,2020,47,47,"2020-11-21","15:00:00","2020-11-22","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"N","R-403700"]
["ProRail","IO-K-B17018-ij13-00",".",">","IJsselmonde","IJsselmonde",2020,2020,48,48,"2020-11-23","07:00:00","2020-11-27","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB IJsselmonde  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-403700-2052-00",".",">","Botlek","Pernis",2020,2020,48,48,"2020-11-28","15:00:00","2020-11-29","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-K-B17018-12wz-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,49,49,"2020-11-30","07:00:00","2020-12-04","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Zuid  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-wo13-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,49,49,"2020-11-30","07:00:00","2020-12-04","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven Oost  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-K-B17018-ww13-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2020,2020,49,49,"2020-11-30","07:00:00","2020-12-04","16:00:00","105:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"IOM NCGB Waalhaven West  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-L-005189-2012-00",".",">","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2020,2020,49,50,"2020-12-05","02:00:00","2020-12-07","04:00:00","50:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vernieuwen wisselliggers en ballast van diverse wissels en dwarsliggers en ballast in diverse sporen vernieuwen.",null,"Y","L-005189"]
["ProRail","IO-L-005113-2003-00",".","< >","Harmelen aansl.","Woerden Overloop",2020,2020,50,51,"2020-12-12","02:00:00","2020-12-14","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen ledseinen en matrixsignaalgever",null,"Y","L-005113"]
["ProRail","IO-K-B17018-12pe-00",".",">","Pernis","Rail Service Center Waalhaven aansl.",2020,2020,50,50,"2020-12-07","07:00:00","2020-12-11","16:00:00","105:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"IOM NCGB Pernis  WO RZR202-0094",null,"N","K-B17018"]
["ProRail","IO-R-403700-2053-00",".",">","Botlek","Pernis",2020,2020,50,50,"2020-12-12","15:00:00","2020-12-13","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"N","R-403700"]
["ProRail","IO-R-403700-2154-00",".",">","Botlek","Pernis",2021,2021,1,1,"2021-01-09","15:00:00","2021-01-10","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-L-005121-2101-00",".","< >","Amsterdam Amstel","Watergraafsmeer West aansl.",2021,2021,2,3,"2021-01-16","02:00:00","2021-01-18","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleidingbalken portaal 3/28-3/29-3/30, portaal 3/31-3/32(-3/33)_PVE-5",null,"Y","L-005121"]
["ProRail","IO-L-005124-2102-00",".","< >","Amsterdam Amstel","Watergraafsmeer West aansl.",2021,2021,2,3,"2021-01-16","01:00:00","2021-01-18","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-2",null,"Y","L-005124"]
["ProRail","IO-L-005124-2106-00",".","< >","Amsterdam Muiderpoort","Dijksgracht Westzijde (Amsterdam)",2021,2021,2,2,"2021-01-16","00:00:00","2021-01-16","20:00:00","20:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-2 deel E",null,"Y","L-005124"]
["ProRail","IO-R-2AE001-2102-00",".",">","Amsterdam Amstel","Duivendrecht",2021,2021,2,3,"2021-01-16","01:00:00","2021-01-18","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Afbouw nieuw stijgpunt met tunnel in het eerste perron van station Amsterdam Amstel",null,"Y","R-2AE001"]
["ProRail","IO-R-403700-2155-00",".",">","Botlek","Pernis",2021,2021,3,3,"2021-01-23","15:00:00","2021-01-24","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-403700-2156-00",".",">","Botlek","Pernis",2021,2021,4,4,"2021-01-30","15:00:00","2021-01-31","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-L-005189-2019-00",".","< >","Erasmusgracht aansl.","Zaandam",2021,2021,5,6,"2021-02-06","02:20:00","2021-02-08","05:20:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen dwarsliggers en spoorstaven in diverse sporen",null,"Y","L-005189"]
["ProRail","IO-R-485000.01-Hbg1-00",".","< >","Erasmusgracht aansl.","Radarweg aansl.",2021,2021,5,6,"2021-02-06","02:00:00","2021-02-08","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Ass Hemboog spoorwerk, lichten-schiften, reguleren Bvl Sporen 9 en 10",null,"Y","R-485000.01"]
["ProRail","IO-R-3AE001-2106-00",".",">","Amsterdam Centraal","Singelgracht aansl.",2021,2021,5,6,"2021-02-06","01:00:00","2021-02-08","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Tijdelijk wegnemen van sporen en/of perrondelen voor bouwkundig onderzoek naar de onderliggende constructie.",null,"Y","R-3AE001"]
["ProRail","IO-K-006308-2001-00",".","< >","Gouda","Moordrecht overloopw.",2021,2021,6,7,"2021-02-13","01:15:00","2021-02-15","05:15:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"groot onderhoud aan brug",null,"Y","K-006308"]
["ProRail","IO-K-006310-2101-00",".","< >","Gouda","Moordrecht overloopw.",2021,2021,6,7,"2021-02-13","01:15:00","2021-02-15","05:15:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"omlassen kabeltrace's, werkzaamheden relaishuis 10 Gd.",null,"Y","K-006310"]
["ProRail","IO-R-403700-2157-00",".",">","Botlek","Pernis",2021,2021,6,6,"2021-02-13","15:00:00","2021-02-14","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-403700-2158-00",".",">","Botlek","Pernis",2021,2021,7,7,"2021-02-20","15:00:00","2021-02-21","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-K-006000-2102-00",".",">","IJsselmonde","Willemstunnel Zuid",2021,2021,9,10,"2021-03-06","01:25:00","2021-03-08","05:25:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"BBV werkzaamheden",null,"Y","K-006000"]
["ProRail","IO-R-403700-2159-00",".",">","Botlek","Pernis",2021,2021,9,9,"2021-03-06","15:00:00","2021-03-07","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-Z-906107-2102-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2021,2021,9,10,"2021-03-06","01:20:00","2021-03-08","04:20:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"vervangen liften Blaak",null,"Y","Z-906107"]
["ProRail","IO-M-004551-2105-00",".","< >","Roosendaal grens","Roosendaal grens",2021,2021,10,11,"2021-03-13","01:00:00","2021-03-15","05:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"R",null,null,null,"BBV Rsd",null,"Y","M-004551"]
["ProRail","IO-K-006308-2101-00",".",">","Gouda","Moordrecht overloopw.",2021,2021,10,11,"2021-03-13","01:15:00","2021-03-15","05:15:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"groot onderhoud aan brug",null,"Y","K-006308"]
["ProRail","IO-K-006310-2102-00",".",">","Gouda","Moordrecht overloopw.",2021,2021,10,11,"2021-03-13","01:15:00","2021-03-15","04:15:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"omlassen kabeltrace's, werkzaamheden relaishuis 10 Gd.",null,"Y","K-006310"]
["ProRail","IO-R-403700-2160-00",".",">","Botlek","Pernis",2021,2021,10,10,"2021-03-13","15:00:00","2021-03-14","12:00:00","21:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"testbedrijf nieuwe Botlekbrug",null,"Y","R-403700"]
["ProRail","IO-R-3AE001-2107-00",".",">","Amsterdam Centraal","Amsterdam Centraal",2021,2021,11,12,"2021-03-20","01:00:00","2021-03-22","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Tijdelijk wegnemen van sporen en/of perrondelen voor bouwkundig onderzoek naar de onderliggende constructie.",null,"N","R-3AE001"]
["ProRail","IO-K-006305-2101-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"werkzaamheden Calandbrug",null,"Y","K-006305"]
["ProRail","IO-K-006630-2008-00",".","< >","Botlek","Botlek",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoor en overwegen",null,"Y","K-006630"]
["ProRail","IO-K-006630-2018-00",".","< >","Europoort West","Suurhoffbrug o/h Hartelkanaal",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vernieuwen wissels",null,"Y","K-006630"]
["ProRail","IO-R-403700-2101-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Indienststellen nieuwe Botlekbrug (stap 200 )",null,"Y","R-403700"]
["ProRail","IO-R-497500-2102-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-523400-2101-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"- Saneren Overweg 300.3 - Saneren Overweg 303.5",null,"Y","R-523400"]
["ProRail","IO-R-546200-2101-01",".","< >","Europoort West","Maasvlakte aansl.",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"weggedeelte suurhofbrug vervangen",null,"Y","R-546200"]
["ProRail","IO-R-550080-TAC1-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2021,2021,13,14,"2021-04-04","00:55:00","2021-04-06","04:55:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Plaatsen van damwanden.",null,"Y","R-550080"]
["ProRail","IO-R-552700-2101-00",".","< >","Moerdijk","Lage Zwaluwe",2021,2021,13,14,"2021-04-04","01:00:00","2021-04-05","05:00:00","28:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Bouwen van een overweg",null,"Y","R-552700"]
["ProRail","IO-K-006000-2101-00",".",">","Barendrecht","Zwijndrecht",2021,2021,13,14,"2021-04-03","01:10:00","2021-04-05","05:10:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"Wissels 873A, 873B symm en 875 + spoor 1264 + KG/KF + wissel 969 Spoor LJ ca. 5 km sps (kijfhoek)",null,"Y","K-006000"]
["ProRail","IO-K-006631-IO08-00",".",">","Waalhaven Zuid","Waalhaven Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen wissel 129, 133",null,"N","K-006631"]
["ProRail","IO-L-005089-2103-00",".",">","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2021,2021,13,14,"2021-04-04","01:00:00","2021-04-05","05:00:00","28:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Vervangen huidige Centrale buis wisselverwarming voor elektrische wisselverwarming",null,"Y","L-005089"]
["ProRail","IO-L-005211-2104-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2021,2021,13,14,"2021-04-04","01:00:00","2021-04-06","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoorstaven ballast en dwarsliggers spoor 8812, 8813,8815,4225,4540,4742,4645 spoorbegrenzers, wissel 49 en bediening wissel 91 en 39, saneren wissel 93, vernieuwen wissels 102A/B,118,87,89.",null,"Y","L-005211"]
["ProRail","IO-Z-906107-2101-00",".",">","Rotterdam Blaak","Willemstunnel Zuid",2021,2021,13,14,"2021-04-03","01:20:00","2021-04-05","04:20:00","51:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"vervangen liften Blaak",null,"Y","Z-906107"]
["ProRail","IO-K-006308-2003-00",".",">","Gouda","Moordrecht aansl.",2021,2021,14,15,"2021-04-10","01:00:00","2021-04-12","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Groot Onderhoud Hef- en Draaibrug te Gouda",null,"Y","K-006308"]
["ProRail","IO-R-3AE001-2109-00",".",">","Amsterdam Centraal","Singelgracht aansl.",2021,2021,15,16,"2021-04-17","01:00:00","2021-04-19","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Aanpassen IJ-Tram Kunstwerk",null,"Y","R-3AE001"]
["ProRail","IO-R-485000.02-Rt01-00",".",">","Rotterdam Centraal","Rotterdam Centraal",2021,2021,15,16,"2021-04-17","01:15:00","2021-04-19","05:15:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"spoor op hoogte P76 brengen",null,"Y","R-485000.02"]
["ProRail","IO-R-485000.02-Rt02-00",".",">","Rotterdam Centraal","Rotterdam Centraal",2021,2021,17,18,"2021-05-01","01:05:00","2021-05-03","05:05:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"spoor op hoogte P76 brengen",null,"Y","R-485000.02"]
["ProRail","IO-Z-906096-2119-00",".",">","Breukelen aansluiting","Maarssen",2021,2021,17,18,"2021-05-01","01:00:00","2021-05-04","05:00:00","76:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Schilderen staalconstructie en dakbeschot perronkap station Maarssen",null,"Y","Z-906096"]
["ProRail","IO-R-485000.02-Rt03-00",".",">","Rotterdam Centraal","Rotterdam Centraal",2021,2021,19,20,"2021-05-15","01:15:00","2021-05-17","05:15:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"spoor op hoogte P76 brengen",null,"Y","R-485000.02"]
["ProRail","IO-K-006305-2102-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,20,21,"2021-05-22","19:00:00","2021-05-24","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"werkzaamheden Calandbrug",null,"Y","K-006305"]
["ProRail","IO-M-004551-2104-00",".","< >","Roosendaal grens","Roosendaal grens",2021,2021,20,21,"2021-05-22","01:00:00","2021-05-25","05:00:00","76:00","continuous","Miscellaneous","T","ST",null,null,null,null,"R",null,null,null,"BBV Rsd",null,"Y","M-004551"]
["ProRail","IO-R-497500-2101-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,20,21,"2021-05-22","19:00:00","2021-05-24","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-546200-2101-02",".","< >","Europoort West","Maasvlakte aansl.",2021,2021,20,21,"2021-05-22","19:00:00","2021-05-24","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"weggedeelte suurhofbrug vervangen",null,"Y","R-546200"]
["ProRail","IO-K-006000-2103-00",".",">","IJsselmonde","Rotterdam Stadion",2021,2021,20,21,"2021-05-22","01:30:00","2021-05-24","05:30:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"BBV werkzaamheden",null,"Y","K-006000"]
["ProRail","IO-K-006630-2014-00",".",">","Europoort","Europoort",2021,2021,20,21,"2021-05-22","23:00:00","2021-05-24","23:00:00","48:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"vernieuwen spoorstaven en ballast en saneren wissel 960",null,"Y","K-006630"]
["ProRail","IO-R-485000.02-Rt04-00",".",">","Rotterdam Centraal","Rotterdam Centraal",2021,2021,21,22,"2021-05-29","02:00:00","2021-05-31","06:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"spoor op hoogte P76 brengen",null,"Y","R-485000.02"]
["ProRail","IO-R-550080-TAC2-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2021,2021,23,23,"2021-06-07","01:15:00","2021-06-11","05:15:00","100:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Plaatsen van onderdoorgang, zeer sterke voorkeur voor pasen ivm andere planning",null,"Y","R-550080"]
["ProRail","IO-R-485000.02-Rt05-00",".",">","Rotterdam Centraal","Rotterdam Centraal",2021,2021,23,24,"2021-06-12","01:05:00","2021-06-14","05:05:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"spoor op hoogte P76 brengen",null,"Y","R-485000.02"]
["ProRail","IO-L-005211-2107-00",".","< >","Houtrakpolder (Amsterdam)","Houtrakpolder aansl.(Amsterdam)",2021,2021,27,27,"2021-07-05","07:00:00","2021-07-09","07:00:00","96:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vernieuwen wissels 115, 106 en 112 en ballast spoor 5250 en 5350 Vernieuwen wissels 109, ballast spoor 5165 en 5454, spoorstaven spoor 5165, 5252 en 5454 en spoortak spoor 5165 en 5352",null,"Y","L-005211"]
["ProRail","IO-R-474300-2101-00",".","< >","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2021,2021,28,30,"2021-07-17","01:00:00","2021-07-26","01:00:00","216:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Wijzigen en testen EBS i.v.m. goederen overdrachtspoor",null,"Y","R-474300"]
["ProRail","IO-M-004551-2101-00",".","< >","Markbrug - tussen Zevenbergen en Oudenbosch","Zevenbergen inhaalsp.",2021,2021,29,32,"2021-07-24","01:25:00","2021-08-09","05:25:00","388:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"PSS + BBV",null,"Y","M-004551"]
["ProRail","IO-Z-906106-LZ02-01",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,29,30,"2021-07-24","01:25:00","2021-07-26","05:25:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-Z-906106-LZ02-02",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,30,31,"2021-07-31","01:25:00","2021-08-02","05:25:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-Z-906106-LZ03-01",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,34,35,"2021-08-28","01:30:00","2021-08-30","05:30:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-L-005211-2103-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2021,2021,34,34,"2021-08-23","00:00:00","2021-08-25","04:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoorstaven en dwarsliggers spoor 6101, 6103 en 6203 en wissel 19",null,"N","L-005211"]
["ProRail","IO-L-005211-2108-00",".",">","Amsterdam Westhaven","Amsterdam Westhaven",2021,2021,34,34,"2021-08-23","00:00:00","2021-08-26","04:00:00","76:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vernieuwen sporen wissels en overwegen",null,"Y","L-005211"]
["ProRail","IO-Z-906237-2101-00",".",">","Dordrecht","Dordrecht",2021,2021,34,35,"2021-08-28","00:00:00","2021-08-30","04:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vervangen dakbedekking, bakgoten en verrot dakbeschot van de perronkap tussen spoor 2 en 3 te Dordrecht.",null,"Y","Z-906237"]
["ProRail","IO-R-485000.01-Hbg2-00",".","< >","Erasmusgracht aansl.","Radarweg aansl.",2021,2021,35,36,"2021-09-04","02:00:00","2021-09-06","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Ass Hemboog spoorwerk, lichten-schiften, reguleren Bvl Sporen 9 en 10",null,"Y","R-485000.01"]
["ProRail","IO-R-497500-2103-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,36,37,"2021-09-11","23:00:00","2021-09-13","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Theemsweg",null,"Y","R-497500"]
["ProRail","IO-Z-906107-DVD2-00",".","< >","Duivendrecht aansluiting west","Venserpolder aansl.",2021,2021,37,38,"2021-09-18","02:15:00","2021-09-20","05:15:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen roltrap nivo 1-2. Aanvoeren en afvoeren roltrappen via spoor Gdpa-Asra op nivo 1.",null,"Y","Z-906107"]
["ProRail","IO-R-3AE001-2101-00",".",">","Amsterdam Centraal","Amsterdam Centraal",2021,2021,37,38,"2021-09-18","01:00:00","2021-09-20","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Verstevigen IJ-Tram kunstwerk",null,"N","R-3AE001"]
["ProRail","IO-Z-906106-LZ03-02",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,38,39,"2021-09-25","01:30:00","2021-09-27","05:30:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-Z-906237-2102-00",".",">","Dordrecht","Dordrecht",2021,2021,38,39,"2021-09-25","00:00:00","2021-09-27","04:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Vervangen dakbedekking, bakgoten en verrot dakbeschot van de perronkap tussen spoor 2 en 3 te Dordrecht.",null,"Y","Z-906237"]
["ProRail","IO-M-004551-2106-00",".","< >","Bergen op Zoom","Roosendaal",2021,2021,39,40,"2021-10-02","03:00:00","2021-10-04","03:00:00","48:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"BBV Rsd",null,"Y","M-004551"]
["ProRail","IO-R-497500-2104-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,39,40,"2021-10-02","23:00:00","2021-10-04","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-3AE001-2108-00",".",">","Amsterdam Centraal","Amsterdam Centraal",2021,2021,39,40,"2021-10-02","01:00:00","2021-10-04","05:00:00","52:00","continuous","Miscellaneous","","ST",null,null,null,null,"",null,null,null,"Tijdelijk wegnemen van sporen en/of perrondelen voor bouwkundig onderzoek naar de onderliggende constructie.",null,"N","R-3AE001"]
["ProRail","IO-L-005121-2103-00",".","< >","Amsterdam Centraal","Watergraafsmeer West aansl.",2021,2021,40,41,"2021-10-10","01:00:00","2021-10-11","05:00:00","28:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleidingbalk 2/129-130 en 4/7-8 Dgr_PVE-5",null,"Y","L-005121"]
["ProRail","IO-L-005124-2104-00",".","< >","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2021,2021,40,40,"2021-10-09","01:00:00","2021-10-10","00:50:00","23:50","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-1 deel A en B",null,"Y","L-005124"]
["ProRail","IO-L-005211-2102-00",".","< >","Amsterdam Sloterdijk","Spaarnebrug - bij Haarlem",2021,2021,40,41,"2021-10-09","01:35:00","2021-10-11","05:35:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen spoorstaven en dwarsliggers spoor SJ en spoorstaven spoor 602",null,"Y","L-005211"]
["ProRail","IO-R-3AE001-2103-00",".","< >","Amsterdam Amstel","Amsterdam Zaanstraat",2021,2021,40,41,"2021-10-09","01:00:00","2021-10-11","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Leeghalen Dijksgracht",null,"Y","R-3AE001"]
["ProRail","IO-R-3AE011-2101-00",".","< >","Amsterdam Sloterdijk","Singelgracht aansl.",2021,2021,40,41,"2021-10-09","01:35:00","2021-10-11","05:35:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Perron verlenging Amsterdam zijde (optioneel inkortte perron andere zijde) Verwijderen van OTC's Aanpassen bovenleiding",null,"Y","R-3AE011"]
["ProRail","IO-Z-906107-DVD5-00",".","< >","Duivendrecht aansluiting west","Venserpolder aansl.",2021,2021,42,43,"2021-10-23","02:15:00","2021-10-25","05:15:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen roltrap nivo 1-2.",null,"Y","Z-906107"]
["ProRail","IO-L-005121-2102-00",".","< >","Amsterdam Amstel","Duivendrecht",2021,2021,44,45,"2021-11-07","01:00:00","2021-11-08","05:00:00","28:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleidingbalken portaal 3/3-3/4, 3/11-3/12 en portaal 3/15-3/16 Dmn-Asdm_PVE-5",null,"Y","L-005121"]
["ProRail","IO-L-005124-2105-00",".","< >","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2021,2021,44,44,"2021-11-06","01:00:00","2021-11-07","00:50:00","23:50","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-1 deel D1",null,"Y","L-005124"]
["ProRail","IO-L-005124-2107-00",".","< >","Amsterdam Amstel","Watergraafsmeer West aansl.",2021,2021,44,44,"2021-11-06","02:00:00","2021-11-07","01:50:00","23:50","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-2 deel F",null,"Y","L-005124"]
["ProRail","IO-R-3AE001-2104-00",".","< >","Amsterdam Amstel","Amsterdam Zaanstraat",2021,2021,44,45,"2021-11-06","01:00:00","2021-11-08","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Saneren wissels 1e perronbak.",null,"Y","R-3AE001"]
["ProRail","IO-R-3AE011-2102-00",".","< >","Amsterdam Sloterdijk","Singelgracht aansl.",2021,2021,44,45,"2021-11-06","05:35:00","2021-11-08","05:35:00","48:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Bouwstap aannemer, Aanbrengen RH - Wissels - Kabelkruizingen",null,"Y","R-3AE011"]
["ProRail","IO-R-497500-2105-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,44,45,"2021-11-02","05:00:00","2021-11-08","05:00:00","144:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-K-006000-2105-00",".",">","Kijfhoek aansl. Zuid","Zwijndrecht",2021,2021,44,45,"2021-11-06","01:00:00","2021-11-08","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"R",null,null,null,"Sporen HR, 67 en 68 kijfhoek",null,"Y","K-006000"]
["ProRail","IO-R-3AE001-2102-00",".",">","Amsterdam Centraal","Singelgracht aansl.",2021,2021,45,46,"2021-11-13","01:00:00","2021-11-15","05:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Aanpassen IJ-Tram Kunstwerk",null,"Y","R-3AE001"]
["ProRail","IO-K-006613-1901-00",".",">","Barendrecht","Rotterdam Stadion",2022,2022,14,15,"2022-04-09","00:00:00","2022-04-11","04:00:00","52:00","continuous","Miscellaneous","","LT",null,null,null,null,"",null,null,null,"Aanpassen besturing in 5 tunnelbuizen (NS-reisigers, Goederen en HSL) en Dive Under HSL.",null,"N","K-006613"]
["ProRail","IO-R-3AE011-2103-00",".","< >","Amsterdam Sloterdijk","Singelgracht aansl.",2022,2022,18,19,"2022-05-07","00:00:00","2022-05-09","04:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Eulynx voorbereidingen, plaatsen objectcontrolers en realiseren glasvezelnetwerk. Eventueel al een gedeeltelijke voortest.",null,"Y","R-3AE011"]

{"sheet":"Infrabel","index":3,"n_rows":540,"n_cols":31,"rows_kept":540,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["Infrabel","10281","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2021,2021,43,46,"2021-10-22",43810.958333333336,"2021-11-08",43810.208333333336,"17d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9 \n ",null,null,10281]
["Infrabel","30557","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,26,29,"2022-06-25",43810.958333333336,"2022-07-10",43810.208333333336,"15d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"CTL pour la pose du second tablier sur les ponts 10 et 11 \n ",null,null,30557]
["Infrabel","16116","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2020,2021,45,10,"2020-11-06",43810.958333333336,"2021-03-01",43810.208333333336,"115d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.3 : Mise en service nouveau tracé L165/1 \nproposition détournement via SNCF (L165/2) ou tête à queue à Athus",null,null,16116]
["Infrabel","16118","Athus - Meuse",">","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,20,24,"2021-05-14",43810.958333333336,"2021-06-07",43810.208333333336,"24d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.5 : Pose AS sur VA de L165/2. ",null,null,16118]
["Infrabel","22224","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2021,2021,9,10,"2021-02-26",43810.958333333336,"2021-03-01",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.3 : Electrification L165/1 ",null,null,22224]
["Infrabel","22225","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2021,2021,8,9,"2021-02-19",43810.958333333336,"2021-02-22",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.3 : Electrification L165/1",null,null,22225]
["Infrabel","22226","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2021,2021,11,12,"2021-03-12",43810.958333333336,"2021-03-15",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.4 : Désélectrification L167 ",null,null,22226]
["Infrabel","22227","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2021,2021,10,11,"2021-03-05",43810.958333333336,"2021-03-08",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.4 : Désélectrification L167",null,null,22227]
["Infrabel","22228","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-LUXEMBOURG",2021,2021,16,17,"2021-04-16",43810.958333333336,"2021-04-19",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.4 : électrification L167",null,null,22228]
["Infrabel","22231","Athus - Meuse","< >","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,20,21,"2021-05-14",43810.958333333336,"2021-05-17",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.5 : désélectrification L165/2",null,null,22231]
["Infrabel","22232","Athus - Meuse","< >","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,23,24,"2021-06-04",43810.958333333336,"2021-06-07",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.5 : électrification L165/2 ",null,null,22232]
["Infrabel","22233","Athus - Meuse","< >","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,22,23,"2021-05-28",43810.958333333336,"2021-05-31",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.5 : électrification L165/2",null,null,22233]
["Infrabel","26987","Athus - Meuse",">","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,31,33,"2021-07-26",43810.958333333336,"2021-08-09",43810.208333333336,"14d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.6 : Pose AS sur VB de L165/2",null,null,26987]
["Infrabel","26988","Athus - Meuse","< >","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,32,33,"2021-08-07",43810.958333333336,"2021-08-08",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.6 : Pose AS sur VB de L165/2",null,null,26988]
["Infrabel","10038","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,17,18,"2021-04-19",43810.986111111109,"2021-05-01",43810.194444444445,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141",null,null,10038]
["Infrabel","10165","Lille - Charleroi","< >","MARCHIENNE-AU-PONT","Y.NORD",2021,2021,40,41,"2021-10-02",43810.930555555555,"2021-10-09",43810.194444444445,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,10165]
["Infrabel","10166","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2021,2021,42,43,"2021-10-15",43810.972222222219,"2021-10-18",43810.194444444445,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,10166]
["Infrabel","11183","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,12,13,"2022-03-19",43810.041666666664,"2022-03-21",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,11183]
["Infrabel","14725","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,41,42,"2022-10-08",43810.034722222219,"2022-10-10",43810.173611111109,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs L 96 avec P 93 \n ",null,null,14725]
["Infrabel","14726","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,42,43,"2022-10-15",43810.034722222219,"2022-10-17",43810.173611111109,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs L 96 avec P93 \n ",null,null,14726]
["Infrabel","14727","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,43,44,"2022-10-22",43810.034722222219,"2022-10-24",43810.173611111109,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs L 96 contraintes P93 \n ",null,null,14727]
["Infrabel","14728","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,44,45,"2022-10-29",43810.034722222219,"2022-10-31",43810.173611111109,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs L 96 contraintes P93 \n ",null,null,14728]
["Infrabel","14729","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,41,44,"2022-10-03",43810.979166666664,"2022-10-28",43810.1875,"25d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs L 96 préparations/finitions P93 \n ",null,null,14729]
["Infrabel","16761","Erquelinnes - Montzen","< >","LOBBES","ERQUELINNES",2021,2021,15,16,"2021-04-10",43810.333333333336,"2021-04-11",43810.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement As 04AL & 04BL & 09AL & 09BL & 10AL & 10BL ",null,null,16761]
["Infrabel","16993","Namur - Antwerpen",">","TILLY","LA ROCHE(BRABANT)",2021,2021,17,17,"2021-04-19",43810.958333333336,"2021-04-23",43810.229166666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,16993]
["Infrabel","17001","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,13,13,"2021-03-22",43810.958333333336,"2021-03-27",43810.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,17001]
["Infrabel","17019","Namur - Antwerpen","< >","AISEAU","FARCIENNES",2021,2021,10,11,"2021-03-05",43810.958333333336,"2021-03-08",43810.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,17019]
["Infrabel","17039","Athus - Meuse",">","JAMBES","LUSTIN",2021,2021,14,17,"2021-03-31",43810.333333333336,"2021-04-18",43810.666666666664,"18d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast (C75)",null,null,17039]
["Infrabel","17040","Athus - Meuse",">","HOUYET","BEAURAING",2021,2021,13,14,"2021-03-22",43810.333333333336,"2021-03-30",43810.666666666664,"8d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast (C75) \n ",null,null,17040]
["Infrabel","17962","Lille - Charleroi","< >","FROYENNES","MOUSCRON",2021,2021,36,50,"2021-08-30",43810.25,"2021-12-06",43810.208333333336,"98d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"-\tRenouvellement de traverses, Rails, passages à niveau\r\n-\tSuppression de passages à niveau\r\n-\tAssainissement\r\n-\tRéalisation de travaux divers aux abords clôture, débroussaillage,… afin de sécuriser notre domaine aux points sensibles (HOT SPOT)\r\n-\tRenou \n ",null,null,17962]
["Infrabel","17963","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2021,2021,46,50,"2021-11-08",43810.25,"2021-12-06",43810.208333333336,"28d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"-Renouvellement de traverses,\r\n-Renouvellement des quais de Froyennes\r\n-Renouvellement de chape d’étanchéité\r\n-Renouvellement d’aiguillages\r\n-Renouvellement de rails\r\n-Réalisation de travaux divers aux abords clôture, débroussaillage,… afin de sécuriser \nBijkomende omleidingen Moeskroen - Gent als L75 Deinze - Waregem buiten dienst is via L66/1 - L66 - frontwissel Brugge - L50A - Gent",null,null,17963]
["Infrabel","18007","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,26,27,"2021-06-26",43810.006944444445,"2021-06-28",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast avec C75:\r\n- en voie B entre 69.500 et 70.390 (900m) \r\n- en voie A entre 67.700 et 68.500 (800m) + entre 70.000 et 70.390 (390m) \nA determiner",null,null,18007]
["Infrabel","18071","Athus - Meuse",">","BEAURAING","BEAURAING",2021,2021,16,17,"2021-04-17",43810.25,"2021-04-19",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement de traverses à la grue (24080-24700)\r\nRenouvellement des traverses à la grue (14790-15230)",null,null,18071]
["Infrabel","18072","Athus - Meuse",">","HOUYET","VONECHE",2021,2021,17,18,"2021-04-24",43810.25,"2021-04-26",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des traverses à la grue (24080-24700)\r\nRenouvellement des traverses à la grue (14790-15230) \n ",null,null,18072]
["Infrabel","18076","Athus - Meuse",">","PALISEUL","BERTRIX",2021,2021,20,26,"2021-05-10",43810.333333333336,"2021-06-25",43810.666666666664,"46d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Assainissement à la grue (71410-72140) \n ",null,null,18076]
["Infrabel","18077","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,43,44,"2021-10-18",43810.333333333336,"2021-10-27",43810.666666666664,"9d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des traverses (P93) \n ",null,null,18077]
["Infrabel","18079","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,46,48,"2021-11-08",43810.333333333336,"2021-11-21",43810.625,"13d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement de rails \n ",null,null,18079]
["Infrabel","18104","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,40,41,"2021-10-01",43810.958333333336,"2021-10-04",43810.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy \n ",null,null,18104]
["Infrabel","18105","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,41,42,"2021-10-08",43810.958333333336,"2021-10-11",43810.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy \n ",null,null,18105]
["Infrabel","18107","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,23,24,"2021-06-05",43810.020833333336,"2021-06-07",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies ",null,null,18107]
["Infrabel","18108","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,26,27,"2021-06-26",43810.020833333336,"2021-06-28",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,18108]
["Infrabel","18399","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,14,17,"2021-04-02",43810.958333333336,"2021-04-19",43810.166666666664,"17d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN45 et PN46",null,null,18399]
["Infrabel","18675","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2022,2022,19,20,"2022-05-07",43810.041666666664,"2022-05-09",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwing waterdichte rok van de onderbruggingen langsheen de Engelse lei (incl. opbraak en heraanleg spoor)\r\n\r\nOpgelet nevenliggend spoor A van L27A dient eveneens uit dienst te zijn begin en einde coupure !! \nDienst op enkel spoor tussen Y.Z. Groenenhoek en Y.Holland",null,null,18675]
["Infrabel","18677","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2022,2022,22,23,"2022-05-28",43810.041666666664,"2022-05-30",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwing waterdichte rok van de onderbruggingen langsheen de Engelse lei (incl. opbraak en heraanleg spoor)\r\n\r\nOpgelet nevenliggend spoor A van L27A dient eveneens uit dienst te zijn begin en einde coupure !! \nDienst op enkel spoor tussen Y.Z. Groenenhoek en Y.Holland",null,null,18677]
["Infrabel","19033","Lille - Charleroi","< >","Y.RUISBROEK","TUBIZE",2021,2021,45,46,"2021-11-05",43810.979166666664,"2021-11-08",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Overname Halle Fase PLP3.2 \n ",null,null,19033]
["Infrabel","19269","Lille - Antwerpen","< >","KORTRIJK-RINGLAAN","KORTRIJK",2021,2021,14,17,"2021-04-03",43810,"2021-04-19",43810.166666666664,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Bouwen van een tunnel (met open sleuf)",null,null,19269]
["Infrabel","19872","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,48,49,"2021-11-27",43810.020833333336,"2021-11-29",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \nDétournement via L130A",null,null,19872]
["Infrabel","19875","Lille - Charleroi",">","MONS","QUEVY",2021,2021,49,49,"2021-11-29",43810.833333333336,"2021-12-03",43810.208333333336,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \n ",null,null,19875]
["Infrabel","19880","Athus - Meuse",">","GEDINNE","PALISEUL",2021,2021,33,34,"2021-08-14",43810.25,"2021-08-16",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 4",null,null,19880]
["Infrabel","19881","Athus - Meuse","< >","BERTRIX","GEDINNE",2021,2021,33,34,"2021-08-14",43810.958333333336,"2021-08-15",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 4\r\nCTL du samedi 23h au dimanche 15h\r\net du dimanche 23h au lundi 5h",null,null,19881]
["Infrabel","19882","Athus - Meuse",">","GEDINNE","PALISEUL",2021,2021,35,35,"2021-08-23",43810.333333333336,"2021-08-23",43810.666666666664,"0d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 4 - asphaltage ",null,null,19882]
["Infrabel","19883","Athus - Meuse",">","PALISEUL","GEDINNE",2021,2021,35,35,"2021-08-24",43810.333333333336,"2021-08-24",43810.666666666664,"0d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 4 - asphaltage \n ",null,null,19883]
["Infrabel","19884","Athus - Meuse",">","BERTRIX","GEDINNE",2021,2021,34,35,"2021-08-21",43810.25,"2021-08-23",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 4 \n ",null,null,19884]
["Infrabel","19885","Athus - Meuse","< >","GEDINNE","BERTRIX",2021,2021,34,35,"2021-08-21",43810.958333333336,"2021-08-22",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 4\r\nCTL du samedi 23h au dimanche 15h\r\net du dimanche 23h au lundi 5h \n ",null,null,19885]
["Infrabel","19886","Athus - Meuse",">","VONECHE","BEAURAING",2021,2021,5,13,"2021-01-25",43810.333333333336,"2021-03-21",43810.666666666664,"55d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Pose de caniveaux piste\r\nTravail en double prestations",null,null,19886]
["Infrabel","19887","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,39,40,"2021-09-25",43810.25,"2021-09-26",43810.208333333336,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,19887]
["Infrabel","19888","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,40,41,"2021-10-02",43810.25,"2021-10-04",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,19888]
["Infrabel","19890","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,38,39,"2021-09-18",43810.958333333336,"2021-09-19",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,19890]
["Infrabel","19892","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,14,15,"2021-04-03",43810.25,"2021-04-05",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 11",null,null,19892]
["Infrabel","19893","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,14,15,"2021-04-03",43810.958333333336,"2021-04-04",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 11 ",null,null,19893]
["Infrabel","19894","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,15,16,"2021-04-10",43810.25,"2021-04-12",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 11 ",null,null,19894]
["Infrabel","19895","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,15,16,"2021-04-10",43810.958333333336,"2021-04-11",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 11",null,null,19895]
["Infrabel","19896","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,16,16,"2021-04-12",43810.333333333336,"2021-04-12",43810.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 11 - asphaltage",null,null,19896]
["Infrabel","19897","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,16,16,"2021-04-13",43810.333333333336,"2021-04-13",43810.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 11 - asphaltage",null,null,19897]
["Infrabel","19971","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2021,2021,34,37,"2021-08-18",43810.333333333336,"2021-09-06",43810.243055555555,"19d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Cribleuse L144 entre Bk 0.400 et 13.500 \n ",null,null,19971]
["Infrabel","20055","Athus - Meuse",">","BERTRIX","SAINT-VINCENT-BELLEFONTAINE",2021,2021,42,43,"2021-10-16",43810.333333333336,"2021-10-18",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,20055]
["Infrabel","20179","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,9,9,"2021-02-22",43810.958333333336,"2021-02-27",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord",null,null,20179]
["Infrabel","20180","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,8,9,"2021-02-20",43810.013888888891,"2021-02-22",43810.25,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord",null,null,20180]
["Infrabel","20182","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2021,2021,10,10,"2021-03-01",43810.916666666664,"2021-03-05",43810.25,"4d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Dépose caténaire voie 553",null,null,20182]
["Infrabel","20189","Erquelinnes - Montzen","< >","HUY","FLEMALLE-HAUTE",2021,2021,21,22,"2021-05-21",43810.965277777781,"2021-05-25",43810.236111111109,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS",null,null,20189]
["Infrabel","20190","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","HUY",2021,2021,23,24,"2021-06-04",43810.965277777781,"2021-06-07",43810.236111111109,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS ",null,null,20190]
["Infrabel","20195","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","HALANZY",2021,2021,18,19,"2021-05-01",43810.958333333336,"2021-05-02",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Virton: rechargements EBP/PLP+ETCS, essais et parcours des nouvelles voies et de la nouvelle signalisation\r\nRechargement le 01:05/21 à 1h, \r\nParcours le 02/05/21 jusqu'à 14h, pour remise en service des voies I, II et III (vIII si  liaison vers vB déjà é \n ",null,null,20195]
["Infrabel","20268","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2021,2021,40,41,"2021-10-01",43810.979166666664,"2021-10-04",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Démolition PS Norbert Ponlot \n ",null,null,20268]
["Infrabel","20390","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2021,2021,7,8,"2021-02-12",43810.979166666664,"2021-02-15",43810.708333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement 2 PS rue Baudoux et rue du gros chêne\r\npose des nouveaux tabliers",null,null,20390]
["Infrabel","20391","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2021,2021,41,42,"2021-10-08",43810.979166666664,"2021-10-11",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Démolition PS Norbert Ponlot \n ",null,null,20391]
["Infrabel","20432","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2021,2021,25,26,"2021-06-19",43810.027777777781,"2021-06-20",43810.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur (renouvellement de quais - renouvellement passerelles - parois rocheuses - ...)",null,null,20432]
["Infrabel","20449","Erquelinnes - Montzen","< >","HUY","ANDENNE",2021,2021,43,44,"2021-10-23",43810.027777777781,"2021-10-24",43810.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification : renouvellement de rails suite défaut US entre BK 31400 et BK 32000, ... \n ",null,null,20449]
["Infrabel","20451","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2021,2021,24,25,"2021-06-12",43810.027777777781,"2021-06-13",43810.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA + voies tronçon Andenne - Namur (renouvellement de rails suite défaut US entre BK 56500 et BK 58000) ",null,null,20451]
["Infrabel","20455","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2021,2021,21,22,"2021-05-21",43810.986111111109,"2021-05-24",43810.708333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Démolition PS Ponlot",null,null,20455]
["Infrabel","20456","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2021,2021,8,9,"2021-02-19",43810.979166666664,"2021-02-21",43810.708333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement 2 PS rue Baudoux et rue du gros chêne\r\npose des nouveaux tabliers",null,null,20456]
["Infrabel","20466","Athus - Meuse",">","JAMBES","LUSTIN",2021,2021,17,20,"2021-04-19",43810.916666666664,"2021-05-09",43810.75,"20d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement traverses et ballast dans le tunnel de Lustin",null,null,20466]
["Infrabel","20671","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,43,43,"2021-10-18",43810.958333333336,"2021-10-22",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,20671]
["Infrabel","20674","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,50,50,"2021-12-06",43810.958333333336,"2021-12-11",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,20674]
["Infrabel","20690","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2021,2021,20,21,"2021-05-14",43810.993055555555,"2021-05-17",43810.243055555555,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"CTL RER \n ",null,null,20690]
["Infrabel","20717","Namur - Antwerpen","< >","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,44,46,"2022-10-28",43810.989583333336,"2022-11-07",43810.197916666664,"10d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER CTL : grill coté LLN \r\nachèvement de Y.LLN et MES des voies latérales \r\n+ assainissement de plateformess \r\n+ pose 5 AW\r\n+ Ripage\r\n+ tvx CAT & sign \n ",null,null,20717]
["Infrabel","20718","Namur - Antwerpen","< >","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,46,47,"2022-11-11",43810.989583333336,"2022-11-14",43810.197916666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER CTL : grill coté LLN\r\n+ assainissement de plateformess \r\n+ pose 5 AW\r\n+ Ripage\r\n+ tvx CAT & sign\n ",null,null,20718]
["Infrabel","20723","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2022,2022,16,17,"2022-04-15",43810.979166666664,"2022-04-18",43810.243055555555,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER Weekend Paques \n ",null,null,20723]
["Infrabel","20857","Namur - Antwerpen",">","TILLY","LA ROCHE(BRABANT)",2021,2021,19,19,"2021-05-03",43810.958333333336,"2021-05-08",43810.208333333336,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,20857]
["Infrabel","20859","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,38,38,"2021-09-13",43810.958333333336,"2021-09-18",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \n",null,null,20859]
["Infrabel","20860","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,39,39,"2021-09-20",43810.958333333336,"2021-09-25",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nPas de traffic supplémentaire les nuits de CTL. (Doc envoyé le 12/03/18)",null,null,20860]
["Infrabel","20862","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2021,2021,6,6,"2021-02-01",43810.958333333336,"2021-02-06",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L140 BK 58.475 : Rnvlt des passerelles/trottoirs du PS\r\nTravaux de finition suite CTL du 13 au 16 novembre 2020 (UPM A-078998)",null,null,20862]
["Infrabel","20865","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,10,10,"2021-03-01",43810.993055555555,"2021-03-06",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,20865]
["Infrabel","20868","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,22,22,"2021-05-25",43810.993055555555,"2021-05-29",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 ",null,null,20868]
["Infrabel","20869","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,21,21,"2021-05-17",43810.993055555555,"2021-05-22",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,20869]
["Infrabel","20955","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,17,18,"2021-04-19",43810.916666666664,"2021-04-30",43810.25,"11d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Démolition du PS 42.810",null,null,20955]
["Infrabel","20959","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,44,44,"2021-10-25",43810.958333333336,"2021-10-29",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20959]
["Infrabel","20960","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,37,37,"2021-09-06",43810.958333333336,"2021-09-11",43810.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20960]
["Infrabel","20962","Namur - Antwerpen",">","COURT-SAINT-ETIENNE","FAUX",2021,2021,41,42,"2021-10-09",43810.25,"2021-10-10",43810.916666666664,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20962]
["Infrabel","20963","Namur - Antwerpen",">","COURT-SAINT-ETIENNE","FAUX",2021,2021,42,43,"2021-10-11",43810.375,"2021-10-17",43810.666666666664,"6d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20963]
["Infrabel","20965","Namur - Antwerpen",">","COURT-SAINT-ETIENNE","FAUX",2021,2021,48,49,"2021-11-22",43810.375,"2021-11-28",43810.666666666664,"6d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20965]
["Infrabel","20967","Namur - Antwerpen",">","COURT-SAINT-ETIENNE","FAUX",2021,2021,47,48,"2021-11-20",43810.25,"2021-11-21",43810.916666666664,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20967]
["Infrabel","20979","Lille - Charleroi","< >","JURBISE","JURBISE",2021,2021,11,11,"2021-03-08",43810.916666666664,"2021-03-12",43810.25,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS 49.000\r\npréparation caténaires : 4 nuits 22-6",null,null,20979]
["Infrabel","21035","Lille - Charleroi","< >","ATH","LEUZE",2021,2021,25,26,"2021-06-14",43810.979166666664,"2021-06-26",43810.1875,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Péparartion renouvellement 34AF/34BF + 42F",null,null,21035]
["Infrabel","21036","Lille - Charleroi","< >","ATH","LEUZE",2021,2021,25,26,"2021-06-19",43810.020833333336,"2021-06-21",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 34AF/34BF + 42F",null,null,21036]
["Infrabel","21039","Lille - Charleroi","< >","Y.LENS","ATH",2021,2021,50,50,"2021-12-06",43810.9375,"2021-12-11",43810.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \r\nDéchargement des appareils \n ",null,null,21039]
["Infrabel","21040","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,10,11,"2022-03-04",43810.923611111109,"2022-03-07",43810.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,21040]
["Infrabel","21065","Athus - Meuse",">","HALANZY","VIRTON",2021,2021,19,20,"2021-05-08",43810.333333333336,"2021-05-09",43810.958333333336,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Phase 2 (demande A171 : A-107273-01) : \r\no   Dépose de l’ancien 14BS et pose de voie courante. \n ",null,null,21065]
["Infrabel","21094","Lille - Charleroi",">","Y.FAMILLEUREUX","MANAGE",2021,2021,17,17,"2021-04-23",43810.75,"2021-04-24",43810.013888888891,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Démolition du PS 42.810\r\nEn massification avec la coupure 21360 \nVoir coupure 21360",null,null,21094]
["Infrabel","21095","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,19,19,"2021-05-03",43810.986111111109,"2021-05-08",43810.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Démolition du PS 42.810 \n ",null,null,21095]
["Infrabel","21104","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,3,3,"2021-01-11",43810.958333333336,"2021-01-15",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PS 51.035 et du pont du canal - Travaux SPW",null,null,21104]
["Infrabel","21105","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,17,18,"2021-04-24",43810.965277777781,"2021-04-26",43810.201388888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PS 51.035 et du pont du canal - Travaux SPW \n ",null,null,21105]
["Infrabel","21106","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,36,37,"2021-08-30",43810.986111111109,"2021-09-05",43810.194444444445,"6d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PS 51.035 et du pont du canal - Travaux SPW \n ",null,null,21106]
["Infrabel","21155","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","HUY",2021,2021,22,23,"2021-05-28",43810.965277777781,"2021-05-31",43810.236111111109,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS ",null,null,21155]
["Infrabel","21168","Lille - Charleroi","< >","Y.LA SAMBRE","Y.NORD",2021,2021,49,50,"2021-12-04",43810.972222222219,"2021-12-09",43810.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,21168]
["Infrabel","21236","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2021,2021,43,46,"2021-10-22",43810.958333333336,"2021-11-08",43810.208333333336,"17d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement As 04AL & 04BL & 09AL & 09BL & 10AL & 10BL \n ",null,null,21236]
["Infrabel","21238","Erquelinnes - Montzen","< >","LA SAMBRE","HOURPES",2021,2021,51,51,"2021-12-13",43810.958333333336,"2021-12-18",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement As 04AL & 04BL & 09AL & 09BL & 10AL & 10BL\r\nCTL toutes les nuits \n ",null,null,21238]
["Infrabel","21317","Athus - Meuse","< >","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,16,17,"2021-04-17",43810.25,"2021-04-18",43810.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 104.150 à Bk 104.190",null,null,21317]
["Infrabel","21318","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,18,18,"2021-04-26",43810.333333333336,"2021-04-26",43810.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 104.150 à Bk 104.190 - Bourrage vitesse normale \n ",null,null,21318]
["Infrabel","21319","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,18,18,"2021-04-27",43810.333333333336,"2021-04-27",43810.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 104.150 à Bk 104.190 - Réglage des contraintes \n ",null,null,21319]
["Infrabel","21320","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,20,21,"2021-05-15",43810.25,"2021-05-17",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 116.150 à Bk 116.180 & renouvellement étanchéité PI",null,null,21320]
["Infrabel","21321","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,21,21,"2021-05-17",43810.333333333336,"2021-05-17",43810.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 116.150 à Bk 116.180 & renouvellement étanchéité PI - Bourrage vitesse normale ",null,null,21321]
["Infrabel","21322","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,21,21,"2021-05-18",43810.333333333336,"2021-05-18",43810.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 116.150 à Bk 116.180 & renouvellement étanchéité PI - Réglage des contraintes",null,null,21322]
["Infrabel","21323","Athus - Meuse",">","HALANZY","AUBANGE",2021,2021,20,21,"2021-05-15",43810.25,"2021-05-17",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 138.830 à 138.870 (PN41)",null,null,21323]
["Infrabel","21324","Athus - Meuse",">","HALANZY","AUBANGE",2021,2021,21,22,"2021-05-22",43810.25,"2021-05-23",43810.208333333336,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 138.830 à 138.870 (PN41) - pose revêtement routier / bourrage vitesse normale / réglage contraintes",null,null,21324]
["Infrabel","21325","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,32,33,"2021-08-07",43810.958333333336,"2021-08-08",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780",null,null,21325]
["Infrabel","21326","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,33,34,"2021-08-14",43810.958333333336,"2021-08-15",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780",null,null,21326]
["Infrabel","21327","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,35,36,"2021-08-28",43810.958333333336,"2021-08-29",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,21327]
["Infrabel","21328","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,37,37,"2021-09-06",43810.333333333336,"2021-09-06",43810.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 - Bourrage vitesse normale \n ",null,null,21328]
["Infrabel","21329","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,37,37,"2021-09-07",43810.333333333336,"2021-09-07",43810.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 - Réglage des contraintes \n ",null,null,21329]
["Infrabel","21330","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,34,35,"2021-08-21",43810.958333333336,"2021-08-22",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,21330]
["Infrabel","21331","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,33,33,"2021-08-09",43810.333333333336,"2021-08-13",43810.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations\r\nVoie A HS les Lu-Ma-Me-Je-Ve de 08h à 16h",null,null,21331]
["Infrabel","21332","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,34,34,"2021-08-16",43810.333333333336,"2021-08-20",43810.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations \n ",null,null,21332]
["Infrabel","21333","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,35,35,"2021-08-23",43810.333333333336,"2021-08-27",43810.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations",null,null,21333]
["Infrabel","21334","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,36,36,"2021-08-30",43810.333333333336,"2021-09-03",43810.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations \n ",null,null,21334]
["Infrabel","21338","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2021,2021,20,21,"2021-05-15",43810.25,"2021-05-16",43810.229166666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Etanchéité PI bk 116158 + assainissement \n",null,null,21338]
["Infrabel","21354","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,22,23,"2021-05-28",43810.986111111109,"2021-05-31",43810.194444444445,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141",null,null,21354]
["Infrabel","21355","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,17,18,"2021-04-23",43810.986111111109,"2021-04-26",43810.194444444445,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 ",null,null,21355]
["Infrabel","21357","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,21,22,"2021-05-21",43810.986111111109,"2021-05-25",43810.194444444445,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141",null,null,21357]
["Infrabel","21358","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,19,20,"2021-05-07",43810.986111111109,"2021-05-10",43810.194444444445,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,21358]
["Infrabel","21359","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,20,21,"2021-05-12",43810.986111111109,"2021-05-17",43810.194444444445,"5d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,21359]
["Infrabel","21360","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,18,19,"2021-04-30",43810.986111111109,"2021-05-03",43810.194444444445,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141 \n ",null,null,21360]
["Infrabel","21370","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2021,2021,43,44,"2021-10-22",43810.944444444445,"2021-10-25",43810.222222222219,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \n",null,null,21370]
["Infrabel","21401","Athus - Meuse",">","HOUYET","VONECHE",2021,2021,18,19,"2021-05-01",43810.25,"2021-05-03",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des traverses à la grue (24080-24700)\r\nRenouvellement des traverses à la grue (14790-15230) \n ",null,null,21401]
["Infrabel","21402","Athus - Meuse",">","VONECHE","BEAURAING",2021,2021,39,42,"2021-09-20",43810.333333333336,"2021-10-15",43810.666666666664,"25d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Pose de caniveaux piste\r\nTravail en double prestations \n ",null,null,21402]
["Infrabel","21652","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,7,9,"2021-02-13",43810.027777777781,"2021-02-22",43810.177083333336,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 2)",null,null,21652]
["Infrabel","21654","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,5,6,"2021-01-29",43810.993055555555,"2021-02-01",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen. ",null,null,21654]
["Infrabel","21655","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,6,7,"2021-02-05",43810.993055555555,"2021-02-08",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen.",null,null,21655]
["Infrabel","21656","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,7,8,"2021-02-12",43810.993055555555,"2021-02-15",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen ",null,null,21656]
["Infrabel","21657","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,8,9,"2021-02-19",43810.993055555555,"2021-02-22",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen",null,null,21657]
["Infrabel","21658","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,9,10,"2021-02-26",43810.993055555555,"2021-03-01",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen",null,null,21658]
["Infrabel","21659","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,10,11,"2021-03-05",43810.993055555555,"2021-03-08",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen",null,null,21659]
["Infrabel","21660","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,11,12,"2021-03-12",43810.993055555555,"2021-03-15",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen ",null,null,21660]
["Infrabel","21731","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2022,2022,19,22,"2022-05-07",43810,"2022-05-23",43810.166666666664,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 Engelselei – waterdichte rokken vervangen\t\t\t\teerste fase TLO 16 dagen\r\nvan een 70-tal gewelfstructuren \n ",null,null,21731]
["Infrabel","21753","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,9,11,"2022-02-26",43810.041666666664,"2022-03-07",43810.166666666664,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) \n ",null,null,21753]
["Infrabel","22209","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","HUY",2021,2021,24,24,"2021-06-07",43810.965277777781,"2021-06-11",43810.236111111109,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme), suite phase 2\r\ntravaux divers en voie A (bourrage de révision, réglage des contraintes, retrait ART, toilette de la voie...) ",null,null,22209]
["Infrabel","22210","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","HUY",2021,2021,21,21,"2021-05-17",43810.965277777781,"2021-05-21",43810.236111111109,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme), \r\ntravaux préparatoires (dépose caténaire existante, pose panneaux ART, préparation panneaux d'appareils de voie,...)",null,null,22210]
["Infrabel","22211","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,9,10,"2021-02-27",43810.958333333336,"2021-02-28",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130",null,null,22211]
["Infrabel","22212","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,14,15,"2021-04-03",43810.958333333336,"2021-04-04",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130",null,null,22212]
["Infrabel","22213","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,22,23,"2021-05-29",43810.958333333336,"2021-05-30",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 ",null,null,22213]
["Infrabel","22214","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,26,27,"2021-06-26",43810.958333333336,"2021-06-27",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130",null,null,22214]
["Infrabel","22215","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,32,33,"2021-08-07",43810.958333333336,"2021-08-08",43810.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130",null,null,22215]
["Infrabel","22216","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,39,40,"2021-09-25",43810.958333333336,"2021-09-26",43810.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22216]
["Infrabel","22217","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,44,45,"2021-10-30",43810.958333333336,"2021-10-31",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22217]
["Infrabel","22218","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,49,50,"2021-12-04",43810.958333333336,"2021-12-05",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22218]
["Infrabel","22322","Lille - Antwerpen","< >","KORTRIJK","KORTRIJK-RINGLAAN",2021,2021,14,17,"2021-04-03",43810,"2021-04-19",43810.166666666664,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Nieuwe ondertunneling Kortrijk",null,null,22322]
["Infrabel","22553","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,15,16,"2021-04-10",43810.958333333336,"2021-04-11",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. ",null,null,22553]
["Infrabel","22555","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,17,18,"2021-04-24",43810.958333333336,"2021-04-25",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. \n ",null,null,22555]
["Infrabel","22556","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,16,16,"2021-04-11",43810.958333333336,"2021-04-12",43810.229166666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. ",null,null,22556]
["Infrabel","22557","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,17,17,"2021-04-18",43810.958333333336,"2021-04-19",43810.229166666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S",null,null,22557]
["Infrabel","22558","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,17,18,"2021-04-24",43810.958333333336,"2021-04-25",43810.229166666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. \n ",null,null,22558]
["Infrabel","22559","Athus - Meuse",">","HALANZY","VIRTON",2021,2021,19,20,"2021-05-08",43810.25,"2021-05-10",43810.25,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nDépose de l'ancien 14BS et pose de voie courante. \n ",null,null,22559]
["Infrabel","22560","Athus - Meuse","< >","HALANZY","VIRTON",2021,2021,20,21,"2021-05-15",43810.958333333336,"2021-05-16",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nbourrage de révision, contraintes et finitions. \n ",null,null,22560]
["Infrabel","22563","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,3,3,"2021-01-11",43810.958333333336,"2021-01-15",43810.166666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk",null,null,22563]
["Infrabel","22614","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,23,23,"2021-05-30",43810.03125,"2021-05-31",43810.166666666664,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten ",null,null,22614]
["Infrabel","22619","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,39,39,"2021-09-19",43810.03125,"2021-09-20",43810.166666666664,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,22619]
["Infrabel","22632","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,4,4,"2021-01-18",43810.993055555555,"2021-01-22",43810.159722222219,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereidende weeknachten Y Holland L12-27A - vernieuwing spoortoestellen",null,null,22632]
["Infrabel","22691","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,12,13,"2021-03-19",43810.993055555555,"2021-03-22",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen",null,null,22691]
["Infrabel","22727","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,25,26,"2022-06-17",43810.958333333336,"2022-06-20",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,22727]
["Infrabel","22729","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,8,9,"2022-02-18",43810.958333333336,"2022-02-21",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,22729]
["Infrabel","22733","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,44,45,"2021-10-29",43810.996527777781,"2021-11-01",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,22733]
["Infrabel","22734","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,49,50,"2021-12-03",43810.996527777781,"2021-12-06",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,22734]
["Infrabel","22780","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,11,12,"2021-03-13",43810,"2021-03-15",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk",null,null,22780]
["Infrabel","22787","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,17,17,"2021-04-19",43810.993055555555,"2021-04-23",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Afwerking: Nieuwe ondertunneling Kortrijk",null,null,22787]
["Infrabel","22791","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,17,18,"2021-04-24",43810,"2021-04-26",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Afwerking: Nieuwe ondertunneling Kortrijk. \n ",null,null,22791]
["Infrabel","22794","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,18,18,"2021-04-26",43810.993055555555,"2021-04-30",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwwerking Nieuwe ondertunneling Kortrijk. \n ",null,null,22794]
["Infrabel","22848","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,36,37,"2021-09-04",43810.079861111109,"2021-09-06",43810.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22848]
["Infrabel","22849","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,14,15,"2022-04-02",43810.041666666664,"2022-04-04",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22849]
["Infrabel","22850","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,40,41,"2022-10-01",43810.041666666664,"2022-10-03",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22850]
["Infrabel","22851","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,18,19,"2022-04-30",43810.041666666664,"2022-05-02",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22851]
["Infrabel","22852","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,17,18,"2022-04-23",43810.041666666664,"2022-04-25",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22852]
["Infrabel","22853","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,16,17,"2022-04-16",43810.041666666664,"2022-04-18",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22853]
["Infrabel","22854","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,12,13,"2022-03-19",43810.041666666664,"2022-03-21",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22854]
["Infrabel","22856","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,33,34,"2021-08-14",43810.079861111109,"2021-08-16",43810.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22856]
["Infrabel","22857","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,34,35,"2021-08-21",43810.079861111109,"2021-08-23",43810.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59\r\nRelatie S32",null,null,22857]
["Infrabel","22858","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,40,41,"2021-10-02",43810.079861111109,"2021-10-04",43810.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22858]
["Infrabel","22864","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,52,53,"2021-12-25",43810.079861111109,"2021-12-27",43810.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22864]
["Infrabel","22879","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-DAM",2021,2021,4,5,"2021-01-22",43810.993055555555,"2021-01-25",43810.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Y Holland L12-27A – vernieuwing spoortoestellen\r\nDe spoortoestellen van Y Holland zullen vernieuwd worden in combinatie met de omvorming van de bundelkop van bundel Q kant Essen.",null,null,22879]
["Infrabel","22929","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,9,16,"2021-02-21",43810.951388888891,"2021-04-11",43810.229166666664,"49d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"RER : \r\nSAVU DE NUIT en semaine 22:50-05:30\r\net CTL nuit les weekend samedi a dimanche 00:30-05:30\r\nTravaux préparatoires de la renovation de la Y.LLN",null,null,22929]
["Infrabel","22978","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,14,14,"2021-03-29",43810.958333333336,"2021-04-02",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord - bourrage de revision, finitions",null,null,22978]
["Infrabel","23039","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,27,28,"2021-07-03",43810.006944444445,"2021-07-05",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast avec C75:\r\n- en voie B entre 71.200 et 74.200 (3000m) + quais de Franière Voie B \nA determiner",null,null,23039]
["Infrabel","23091","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,37,37,"2021-09-06",43810.958333333336,"2021-09-11",43810.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,23091]
["Infrabel","23103","Athus - Meuse","< >","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,20,21,"2021-05-15",43810.25,"2021-05-16",43810.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 116.150 à Bk 116.180 & renouvellement étanchéité PI \n ",null,null,23103]
["Infrabel","23104","Athus - Meuse","< >","HALANZY","AUBANGE",2021,2021,20,21,"2021-05-15",43810.25,"2021-05-16",43810.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 138.830 à 138.870 (PN41) \n ",null,null,23104]
["Infrabel","23105","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,32,33,"2021-08-07",43810.25,"2021-08-09",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780",null,null,23105]
["Infrabel","23106","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,33,34,"2021-08-14",43810.25,"2021-08-16",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780",null,null,23106]
["Infrabel","23107","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,34,35,"2021-08-21",43810.25,"2021-08-23",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,23107]
["Infrabel","23108","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,35,36,"2021-08-28",43810.25,"2021-08-30",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,23108]
["Infrabel","23113","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,16,17,"2021-04-17",43810.25,"2021-04-19",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 104.150 à Bk 104.190",null,null,23113]
["Infrabel","23133","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,23,24,"2021-06-05",43810.072916666664,"2021-06-07",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nWE 1 TLO ",null,null,23133]
["Infrabel","23135","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,36,37,"2021-09-04",43810.072916666664,"2021-09-06",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nTLO WE 1 \n ",null,null,23135]
["Infrabel","23258","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,32,32,"2021-08-02",43810.958333333336,"2021-08-07",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits",null,null,23258]
["Infrabel","23259","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,51,51,"2021-12-13",43810.958333333336,"2021-12-18",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,23259]
["Infrabel","23934","Lille - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG",2021,2021,15,16,"2021-04-10",43810.0625,"2021-04-12",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Werken TUC P198361 - sporen A+B BD \r\nmaken doorsteken - plaatsen en verwijderen T & TS- schakelaars\r\nBDS:\r\nL50E F-S.6 tot AW 72AH vrij en AW 72BH vrij tot EX-S.6\r\nL58 C-C.13 tot AW 01XR vrij en AW 02R vrij tot CX-C.13\r\nL58/1 AW 11O vrij tot AW 03Q vrij  ",null,null,23934]
["Infrabel","24596","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,11,12,"2021-03-13",43810.25,"2021-03-14",43810.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"MES EBP/PLP",null,null,24596]
["Infrabel","24600","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,10,11,"2021-03-06",43810.25,"2021-03-07",43810.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Préparation MES EBP/PLP\r\nCV jade",null,null,24600]
["Infrabel","24610","Lille - Charleroi",">","MANAGE","LUTTRE",2021,2021,11,11,"2021-03-10",43810.986111111109,"2021-03-12",43810.979166666664,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"placement CV Jade en VB avant mise en service EBP/PLP",null,null,24610]
["Infrabel","24633","Lille - Charleroi",">","MANAGE","LUTTRE",2021,2021,9,9,"2021-02-22",43810.986111111109,"2021-02-27",43810.208333333336,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"essai de sécurité avant mise en service EBP/PLP",null,null,24633]
["Infrabel","24634","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,14,15,"2022-04-02",43810.041666666664,"2022-04-04",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,24634]
["Infrabel","24636","Lille - Charleroi",">","MANAGE","LUTTRE",2021,2021,10,10,"2021-03-01",43810.986111111109,"2021-03-06",43810.208333333336,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"essai de sécurité avant mise en service EBP/PLP",null,null,24636]
["Infrabel","24637","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,40,41,"2021-10-02",43810.079861111109,"2021-10-04",43810.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,24637]
["Infrabel","24712","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,37,38,"2021-09-11",43810.072916666664,"2021-09-13",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nTLO WE 1 \n ",null,null,24712]
["Infrabel","25015","Namur - Antwerpen","< >","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,48,49,"2022-11-25",43810.989583333336,"2022-11-28",43810.197916666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER CTL : grill coté LLN\r\n+ assainissement de plateformess \r\n+ pose 5 AW\r\n+ Ripage\r\n+ tvx CAT & sign",null,null,25015]
["Infrabel","25131","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2021,2021,26,26,"2021-06-23",43810.958333333336,"2021-06-25",43810.21875,"2d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Préparation Criblage WE 26 - 27 juin\r\nSAVU nuit",null,null,25131]
["Infrabel","25132","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2021,2021,27,27,"2021-06-28",43810.958333333336,"2021-07-02",43810.21875,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Réalisation piste + bourrage de révision",null,null,25132]
["Infrabel","25137","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,29,30,"2021-07-17",43810.006944444445,"2021-07-19",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage ballast voie B entre Bk 66.100 et 68.500 (2400M) \nA determiner",null,null,25137]
["Infrabel","25138","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,28,28,"2021-07-05",43810.958333333336,"2021-07-08",43810.21875,"3d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"pistes + contraintes Voie B + reconstruction quai Franière Voie B",null,null,25138]
["Infrabel","25139","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,28,28,"2021-07-08",43810.958333333336,"2021-07-09",43810.21875,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Préparation criblage voie A + début démolition quai Franière voie A",null,null,25139]
["Infrabel","25143","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,29,29,"2021-07-12",43810.958333333336,"2021-07-16",43810.21875,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Pistes + contraintes voie A + reconstruction quai Franière voie A",null,null,25143]
["Infrabel","25146","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,30,30,"2021-07-19",43810.958333333336,"2021-07-22",43810.21875,"3d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"pistes + contraintes Voie B + reconstruction quai Franière Voie B ",null,null,25146]
["Infrabel","25148","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,30,30,"2021-07-22",43810.958333333336,"2021-07-23",43810.21875,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Pistes + contraintes voie A + reconstruction quai Franière voie A ",null,null,25148]
["Infrabel","25149","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,30,31,"2021-07-24",43810.006944444445,"2021-07-26",43810.208333333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage révision \nA determiner",null,null,25149]
["Infrabel","25150","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2021,2021,31,31,"2021-07-26",43810.958333333336,"2021-07-31",43810.21875,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Pistes + Contraintes\r\nSAVU nuit ",null,null,25150]
["Infrabel","25184","Lille - Charleroi",">","LUTTRE","Y.NORD",2021,2021,10,14,"2021-03-01",43810.958333333336,"2021-03-28",43810.958333333336,"27d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Travaux de Réélectrification L. 124A voie B",null,null,25184]
["Infrabel","25193","Lille - Charleroi",">","LUTTRE","MARCHIENNE-AU-PONT",2021,2021,26,27,"2021-06-25",43810.958333333336,"2021-06-28",43810.25,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Travaux de Réélectrification L. 124A voie B",null,null,25193]
["Infrabel","25357","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,26,26,"2021-06-20",43810.03125,"2021-06-21",43810.166666666664,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten",null,null,25357]
["Infrabel","25360","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,36,36,"2021-08-29",43810.03125,"2021-08-30",43810.166666666664,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,25360]
["Infrabel","25361","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,24,25,"2021-06-12",43810.072916666664,"2021-06-14",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nWE 2 TLO ",null,null,25361]
["Infrabel","25423","Erquelinnes - Montzen","< >","LA SAMBRE","HOURPES",2021,2021,39,39,"2021-09-20",43810.958333333336,"2021-09-25",43810.173611111109,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement 09AL & 09BL & 10AL & 10BL \n ",null,null,25423]
["Infrabel","25447","Lille - Charleroi","< >","Y.LENS","ATH",2021,2021,24,25,"2021-06-11",43810.979166666664,"2021-06-14",43810.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise en service de la seconde phase de la L90C BA Brugelette/Ath ",null,null,25447]
["Infrabel","25665","Lille - Charleroi",">","LUTTRE","Y.NORD",2021,2021,7,10,"2021-02-08",43810.958333333336,"2021-02-28",43810.208333333336,"20d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A\r\n- Coupures L124A voie A. De nuit uniquement.",null,null,25665]
["Infrabel","25666","Lille - Charleroi","< >","LUTTRE","Y.NORD",2021,2021,10,14,"2021-03-01",43810.958333333336,"2021-03-29",43810.25,"28d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A",null,null,25666]
["Infrabel","25715","Namur - Antwerpen",">","TAMINES","CHATELET-GRIL EST",2022,2022,5,10,"2022-01-24",43810.9375,"2022-03-05",43810.229166666664,"40d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire - Phase 3 \n ",null,null,25715]
["Infrabel","25727","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,11,12,"2022-03-07",43810.9375,"2022-03-19",43810.229166666664,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire Phase 4 : Travaux Voie sur CTL de nuits semaine\r\nPréparation plateforme 64BJ + drainage, etc.\r\nCTL de nuits en semaine, les nuits en 22h30/05h30 :\r\nVB + VA L130 entre les signaux DX-J.20 + J2-M.20 + D-J. 20 et JX1-M. 20 (en une \n ",null,null,25727]
["Infrabel","25730","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,12,13,"2022-03-18",43810.979166666664,"2022-03-21",43810.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire Phase 5 : Week-end n°1\r\nPose nouveau 64BJ en site propre + voies L130vB.\r\nVB + VA L130 entre les signaux DX-J.20 + J2-M.20 + D-J. 20 et JX1-M. 20 (en une zone de mise HS).\r\nMise hors tension cas 27442, 27440, 27438,27436, 27443 \n ",null,null,25730]
["Infrabel","25829","Lille - Charleroi",">","LUTTRE","Y.NORD",2021,2021,40,44,"2021-10-01",43810.958333333336,"2021-10-25",43810.25,"24d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A\r\n- Coupures L124A voie A\r\n- De nuit uniquement. \n ",null,null,25829]
["Infrabel","25831","Lille - Charleroi",">","LUTTRE","MARCHIENNE-AU-PONT",2021,2021,44,47,"2021-10-25",43810.958333333336,"2021-11-15",43810.25,"21d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A \n ",null,null,25831]
["Infrabel","26176","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2023,37,50,"2022-09-04",43810,"2023-12-15",43810.25,"467d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes \n ",null,null,26176]
["Infrabel","26334","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,8,14,"2022-02-14",43810.923611111109,"2022-03-27",43810.215277777781,"41d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,26334]
["Infrabel","26414","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,3,4,"2021-01-16",43810.25,"2021-01-17",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52",null,null,26414]
["Infrabel","26415","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,25,26,"2021-06-19",43810.25,"2021-06-20",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52",null,null,26415]
["Infrabel","26416","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,34,35,"2021-08-21",43810.25,"2021-08-22",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52 \n ",null,null,26416]
["Infrabel","26417","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,17,17,"2021-04-19",43810.944444444445,"2021-04-24",43810.243055555555,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P3 HKV - Zone 8 AI52 ",null,null,26417]
["Infrabel","26418","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,48,48,"2021-11-22",43810.944444444445,"2021-11-27",43810.243055555555,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P3 HKV - Zone 8 AI52 \n ",null,null,26418]
["Infrabel","26420","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,4,4,"2021-01-18",43810.944444444445,"2021-01-23",43810.236111111109,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P3 HKV - Zone 9 AI52",null,null,26420]
["Infrabel","26421","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,26,26,"2021-06-21",43810.986111111109,"2021-06-26",43810.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P3 HKV - Zone 9 AI52",null,null,26421]
["Infrabel","26422","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,10,11,"2021-03-06",43810.291666666664,"2021-03-07",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P4+  - Zone 9 AI52",null,null,26422]
["Infrabel","26423","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,49,50,"2021-12-04",43810.916666666664,"2021-12-05",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P4+  - Zone 9 AI52 \n ",null,null,26423]
["Infrabel","26427","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,36,37,"2021-09-04",43810.916666666664,"2021-09-05",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P4+ - Zone 9 AI52 \n ",null,null,26427]
["Infrabel","26439","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,8,9,"2021-02-20",43810.013888888891,"2021-02-22",43810.25,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement PN 28\r\n\r\nLa coordination internationale est terminée -> à massifier avec CTL existantes (id 20180)",null,null,26439]
["Infrabel","26454","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,3,7,"2021-01-10",43810.951388888891,"2021-02-13",43810.229166666664,"34d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"RER : \rSAVU DE NUIT en semaine 22:50-05:30\r\net CTL nuit les weekend samedi a dimanche 00:30-05:30 (blanc travaux)\r\nTravaux préparatoires de la renovation de la Y.LLN ",null,null,26454]
["Infrabel","26691","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,18,19,"2021-05-01",43810,"2021-05-03",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Afwerking: Nieuwe ondertunneling Kortrijk. \n ",null,null,26691]
["Infrabel","26877","Namur - Antwerpen","< >","AUVELAIS","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,9,10,"2021-02-27",43810.958333333336,"2021-02-28",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z16. 51\r\nP4+ Mini CTL",null,null,26877]
["Infrabel","26879","Namur - Antwerpen","< >","AUVELAIS","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,39,40,"2021-09-25",43810.958333333336,"2021-09-26",43810.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z16. 51\r\nP4+ \n ",null,null,26879]
["Infrabel","26880","Namur - Antwerpen","< >","AUVELAIS","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,49,50,"2021-12-04",43810.958333333336,"2021-12-05",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z16. 51\r\nP4+ Mini CTL \n ",null,null,26880]
["Infrabel","26981","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,39,40,"2021-09-25",43810.25,"2021-09-26",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P4\r\nZone 2 AI 53 \n ",null,null,26981]
["Infrabel","26982","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,12,12,"2021-03-15",43810.940972222219,"2021-03-20",43810.177083333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P3 5 HKV\r\nZone 2 AI 53",null,null,26982]
["Infrabel","26991","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,10,11,"2021-03-06",43810.291666666664,"2021-03-07",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P4+\r\nZone 3 AI 53",null,null,26991]
["Infrabel","26992","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,49,49,"2021-11-29",43810.006944444445,"2021-12-04",43810.243055555555,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P3 HKM\r\nZone 3 AI 53 \n ",null,null,26992]
["Infrabel","26994","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,4,5,"2021-01-23",43810.25,"2021-01-24",43810.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P4+one 2 AI 53 ",null,null,26994]
["Infrabel","26995","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,12,13,"2021-03-20",43810.25,"2021-03-21",43810.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P4+ \r\nZone 2 AI 53",null,null,26995]
["Infrabel","26998","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,48,49,"2021-11-27",43810.25,"2021-11-28",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P4 \r\nZone 3 AI 53 \n ",null,null,26998]
["Infrabel","27000","Lille - Charleroi","< >","JURBISE","MONS",2021,2021,36,37,"2021-09-04",43810.25,"2021-09-05",43810.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5.53\r\nMise HS P4 \r\nZone 5 AI 53 \n ",null,null,27000]
["Infrabel","27224","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,7,7,"2021-02-08",43810.881944444445,"2021-02-12",43810.173611111109,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51    P3 HKV",null,null,27224]
["Infrabel","27226","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,9,10,"2021-02-27",43810.25,"2021-02-28",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P4+",null,null,27226]
["Infrabel","27228","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,9,9,"2021-02-22",43810.972222222219,"2021-02-26",43810.222222222219,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P3 HKV ",null,null,27228]
["Infrabel","27236","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,24,25,"2021-06-12",43810.25,"2021-06-13",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51  P4+ ",null,null,27236]
["Infrabel","27237","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,31,32,"2021-07-31",43810.25,"2021-08-01",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51  P4+ ",null,null,27237]
["Infrabel","27245","Athus - Meuse",">","HOUYET","BEAURAING",2022,2022,19,27,"2022-05-02",43810.333333333336,"2022-07-01",43810.75,"60d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\n\r\nMassification de travaux sur le tronçon Houyet Beauraing \n ",null,null,27245]
["Infrabel","27247","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,50,50,"2021-12-06",43810.881944444445,"2021-12-10",43810.173611111109,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51    P3 HKV \n ",null,null,27247]
["Infrabel","27248","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,24,25,"2022-06-11",43810,"2022-06-13",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD \n ",null,null,27248]
["Infrabel","27253","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,37,38,"2021-09-11",43810.25,"2021-09-12",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P4+ \n ",null,null,27253]
["Infrabel","27255","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,47,50,"2022-11-14",43810.333333333336,"2022-12-09",43810.333333333336,"25d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement quais de Lustin + mise au gabarit pistes Godinne",null,null,27255]
["Infrabel","27256","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,43,47,"2022-10-17",43810.333333333336,"2022-11-13",43810.333333333336,"27d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement quais de Lustin + sécurisation paroi Godinne \n ",null,null,27256]
["Infrabel","27273","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2022,2022,34,35,"2022-08-20",43810.333333333336,"2022-08-22",43810.25,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L144 BK1.100 PS Rue combattant \n ",null,null,27273]
["Infrabel","27301","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,46,47,"2021-11-13",43810.25,"2021-11-14",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P4+ \n ",null,null,27301]
["Infrabel","27302","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,46,46,"2021-11-08",43810.923611111109,"2021-11-12",43810.222222222219,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P3 HKV \n ",null,null,27302]
["Infrabel","27403","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2022,2022,3,18,"2022-01-10"," ","2022-04-30",43810.625,"110d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réalisation d'une dalle en béton armé pour l'étanchéité de la culée-voûte à la bk 8,509 - côté voie B \n ",null,null,27403]
["Infrabel","27503","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2021,2021,9,10,"2021-02-26",43810.993055555555,"2021-03-01",43810.243055555555,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER CTL déviation voie B de Watermael",null,null,27503]
["Infrabel","27505","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,44,46,"2021-10-30",43810.027777777781,"2021-11-08",43810.177083333336,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 2) \n ",null,null,27505]
["Infrabel","27542","Athus - Meuse","< >","BERTRIX","SAINT-VINCENT-BELLEFONTAINE",2021,2021,42,43,"2021-10-16",43810.958333333336,"2021-10-17",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27542]
["Infrabel","27543","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2021,2021,43,44,"2021-10-23",43810.958333333336,"2021-10-24",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27543]
["Infrabel","27545","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,46,47,"2021-11-13",43810.958333333336,"2021-11-14",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27545]
["Infrabel","27547","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,47,48,"2021-11-20",43810.958333333336,"2021-11-21",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27547]
["Infrabel","27796","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,24,24,"2021-06-08",43810.020833333336,"2021-06-12",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies ",null,null,27796]
["Infrabel","27797","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,25,25,"2021-06-15",43810.020833333336,"2021-06-19",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies",null,null,27797]
["Infrabel","27798","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,26,26,"2021-06-22",43810.020833333336,"2021-06-26",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies",null,null,27798]
["Infrabel","27799","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,27,27,"2021-06-29",43810.020833333336,"2021-07-03",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies",null,null,27799]
["Infrabel","27800","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,28,28,"2021-07-06",43810.020833333336,"2021-07-10",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies",null,null,27800]
["Infrabel","27802","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,28,29,"2021-07-10",43810.006944444445,"2021-07-12",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast avec C75:\r\n- en voie B entre 71.200 et 74.200 (3000m) + quais de Franière Voie B \nA determiner",null,null,27802]
["Infrabel","27804","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,47,48,"2021-11-20",43810.013888888891,"2021-11-22",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"In dienst name van Piloot 3 van de inklinking SIW. Deinze niet bereikbaar vanuit Lichtervelde !! \n ",null,null,27804]
["Infrabel","28105","Lille - Charleroi","< >","LUTTRE","Y.NORD",2022,2022,20,21,"2022-05-13",43810.958333333336,"2022-05-16",43810.25,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L. 124A \r\nWeekend en CTL 4 voies en continu\r\nMassifié avec Léoskool \n ",null,null,28105]
["Infrabel","28137","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,4,5,"2022-01-22",43810.9375,"2022-01-24",43810.229166666664,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire - Phase 2 : Intervention caténaire \n ",null,null,28137]
["Infrabel","28146","Namur - Antwerpen",">","TAMINES","CHATELET-GRIL EST",2022,2022,15,16,"2022-04-04",43810.9375,"2022-04-16",43810.229166666664,"12d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Phase 9 : Semaines de finition Caténaire, E&S et Voie\r\nFinition Caténaire, E&S et Voie en voie 382 / B L130.\r\nSAVU de semaine, les nuits en 22h30/05h30 :\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hors tension cas 27319 + 321.\r \n ",null,null,28146]
["Infrabel","28212","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,8,8,"2021-02-15",43810.944444444445,"2021-02-20",43810.236111111109,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nP3 HKM 2 nuits\r\nP3 HKV 3 nuits",null,null,28212]
["Infrabel","28267","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2021,2021,37,51,"2021-09-06",43810.951388888891,"2021-12-18",43810.1875,"103d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes \n ",null,null,28267]
["Infrabel","28760","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,11,12,"2022-03-12",43810.25,"2022-03-14",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28760]
["Infrabel","28762","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,12,13,"2022-03-19",43810.25,"2022-03-21",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28762]
["Infrabel","28769","Lille - Charleroi","< >","LEUZE","TOURNAI",2022,2022,24,25,"2022-06-10",43810.958333333336,"2022-06-13",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 76 \n ",null,null,28769]
["Infrabel","28770","Lille - Charleroi","< >","LEUZE","TOURNAI",2022,2022,27,27,"2022-06-27",43810.958333333336,"2022-07-01",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 76\r\nBourrage de révision\r\nAsphaltage\r\nfinitions \n ",null,null,28770]
["Infrabel","28779","Lille - Charleroi","< >","FROYENNES","BLANDAIN-FRONTIERE",2022,2022,36,37,"2022-09-02",43810.958333333336,"2022-09-05",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 2 - 8 - 10 \n ",null,null,28779]
["Infrabel","28780","Lille - Charleroi","< >","FROYENNES","BLANDAIN-FRONTIERE",2022,2022,38,39,"2022-09-12",43810.958333333336,"2022-09-18",43810.208333333336,"6d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 2 - 8 - 10\r\nBourrage de révision\r\nAsphaltage\r\nFinitions \n ",null,null,28780]
["Infrabel","28785","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,13,14,"2022-03-26",43810.25,"2022-03-28",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28785]
["Infrabel","28790","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,14,15,"2022-04-02",43810.25,"2022-04-04",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28790]
["Infrabel","28791","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,46,47,"2022-11-11",43810.923611111109,"2022-11-14",43810.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 ",null,null,28791]
["Infrabel","28794","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,15,16,"2022-04-09",43810.25,"2022-04-11",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28794]
["Infrabel","28796","Lille - Charleroi",">","Y.LENS","BRUGELETTE",2022,2022,47,48,"2022-11-14",43810.166666666664,"2022-11-21",43810.173611111109,"7d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"renouvellement de traverses entre Ath et Lens ",null,null,28796]
["Infrabel","28811","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,24,25,"2022-06-11",43810.25,"2022-06-13",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28811]
["Infrabel","28895","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,25,26,"2022-06-18",43810.25,"2022-06-20",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28895]
["Infrabel","28899","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2022,2022,26,27,"2022-06-25",43810.958333333336,"2022-06-26",43810.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28899]
["Infrabel","28909","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,17,20,"2022-04-23",43810.958333333336,"2022-05-08",43810.666666666664,"15d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \n ",null,null,28909]
["Infrabel","28910","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,20,21,"2022-05-14",43810.958333333336,"2022-05-16",43810.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 ",null,null,28910]
["Infrabel","28915","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,42,46,"2022-10-15",43810.958333333336,"2022-11-07",43810.208333333336,"23d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,28915]
["Infrabel","28916","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,46,47,"2022-11-12",43810.958333333336,"2022-11-13",43810.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500",null,null,28916]
["Infrabel","28947","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,11,13,"2022-03-11",43810.958333333336,"2022-03-21",43810.208333333336,"10d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron (Pieux)\r\nCTLs de nuit \n ",null,null,28947]
["Infrabel","28955","Lille - Charleroi","< >","MARCHIENNE-AU-PONT","Y.NORD",2022,2022,15,16,"2022-04-09",43810.930555555555,"2022-04-16",43810.194444444445,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,28955]
["Infrabel","29026","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,18,19,"2022-04-29",43810.944444444445,"2022-05-02",43810.222222222219,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \n",null,null,29026]
["Infrabel","29035","Lille - Charleroi","< >","MARCHIENNE-AU-PONT","Y.NORD",2022,2022,24,25,"2022-06-11",43810.972222222219,"2022-06-16",43810.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,29035]
["Infrabel","29044","Lille - Charleroi","< >","Y.LA SAMBRE","MARCHIENNE-AU-PONT",2021,2021,49,50,"2021-12-04",43810.972222222219,"2021-12-09",43810.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,29044]
["Infrabel","29276","Athus - Meuse","< >","Y.NEFFE","BEAURAING",2022,2022,37,38,"2022-09-09",43810.916666666664,"2022-09-12",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de boueux et entretiens d'appareils de voies (bourrage, nivellement,...) \n ",null,null,29276]
["Infrabel","29277","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,7,9,"2021-02-13",43810.027777777781,"2021-02-22",43810.177083333336,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 PLP SI\r\nL59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel",null,null,29277]
["Infrabel","29288","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,44,46,"2021-10-30",43810.020833333336,"2021-11-08",43810.1875,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 PLP SI\r\nL59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel \n ",null,null,29288]
["Infrabel","29298","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,25,26,"2022-06-17",43810.958333333336,"2022-06-20",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \n ",null,null,29298]
["Infrabel","29368","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,43,45,"2022-10-17",43810.989583333336,"2022-10-30",43810.197916666664,"13d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"SAVU de NUIT : travaux préparatoire  grande coupure Grill coté LLN\r\net CTL les NUITs de Weekend \n ",null,null,29368]
["Infrabel","29396","Namur - Antwerpen",">","FLEURUS","TILLY",2022,2022,19,23,"2022-05-02",43810.3125,"2022-06-03",43810.645833333336,"32d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des traverses à l'aide du train P93 entre Fleurus et Tilly en voie A (entre 15BN et 04BO).\r\nL140 Voie A, HS en continu entre le 5/09/2022 jusqu'au 27/11/2022.\r\n+ mises hors services les nuits & certains WE \n ",null,null,29396]
["Infrabel","29397","Namur - Antwerpen","< >","FLEURUS","TILLY",2022,2022,17,17,"2022-04-19",43810.958333333336,"2022-04-23",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Phase 2: Renouvellement des traverses à l'aide du train P entre Fleurus et Tilly en voie A (entre 15BN et 04BO).\r\nL140 Voie B, HS toutes les nuits en semaine durant la période allant du 5^6/09/2022 jusqu'au 25^26/11/2022.\r\n\r\nART à 60km/H sur toute la zo \n ",null,null,29397]
["Infrabel","29401","Namur - Antwerpen","< >","FLEURUS","TILLY",2022,2022,21,22,"2022-05-20",43810.979166666664,"2022-05-23",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Phase 3: Assainissement Ligny (suite P93)\r\nL140 Voie B (en // de la voie A), WE de CTL du 16/09/2022 à 22h jusqu'au 19/09/2022 à 06h. \n ",null,null,29401]
["Infrabel","29435","Namur - Antwerpen","< >","CHATELET-GRIL EST","CHATELET-GRIL EST",2021,2021,16,17,"2021-04-17",43810.916666666664,"2021-04-18",43810.916666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z17. 51 (P4+)",null,null,29435]
["Infrabel","29605","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,44,46,"2021-10-30",43810.020833333336,"2021-11-08",43810.1875,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel \r\nL59 PLP SI \n ",null,null,29605]
["Infrabel","29749","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2022,2022,37,38,"2022-09-09",43810.979166666664,"2022-09-12",43810.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre \n ",null,null,29749]
["Infrabel","29870","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,13,13,"2021-03-21",43810.25,"2021-03-21",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor",null,null,29870]
["Infrabel","29871","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,14,14,"2021-03-28",43810.25,"2021-03-28",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29871]
["Infrabel","29876","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,19,19,"2021-05-02",43810.25,"2021-05-02",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29876]
["Infrabel","29878","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,20,20,"2021-05-09",43810.25,"2021-05-09",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29878]
["Infrabel","29879","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,21,21,"2021-05-16",43810.25,"2021-05-16",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor",null,null,29879]
["Infrabel","29884","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,26,26,"2021-06-20",43810.25,"2021-06-20",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor",null,null,29884]
["Infrabel","29886","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,27,27,"2021-06-27",43810.25,"2021-06-27",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29886]
["Infrabel","29887","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,28,28,"2021-07-04",43810.25,"2021-07-04",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor",null,null,29887]
["Infrabel","29888","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,29,29,"2021-07-11",43810.25,"2021-07-11",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29888]
["Infrabel","29897","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,30,30,"2021-07-18",43810.25,"2021-07-18",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor ",null,null,29897]
["Infrabel","29898","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,31,31,"2021-07-25",43810.25,"2021-07-25",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor",null,null,29898]
["Infrabel","29899","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,32,32,"2021-08-01",43810.25,"2021-08-01",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor ",null,null,29899]
["Infrabel","29900","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,33,33,"2021-08-08",43810.25,"2021-08-08",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor",null,null,29900]
["Infrabel","29903","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,36,36,"2021-08-29",43810.25,"2021-08-29",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29903]
["Infrabel","29920","Erquelinnes - Montzen","< >","STATTE","JAVA",2022,2022,11,12,"2022-03-11",43810.958333333336,"2022-03-14",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte \n ",null,null,29920]
["Infrabel","29933","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,9,11,"2022-02-26",43810.25,"2022-03-06",43810.708333333336,"8d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29933]
["Infrabel","29935","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,11,11,"2022-03-07",43810.916666666664,"2022-03-11",43810.25,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29935]
["Infrabel","29936","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,12,12,"2022-03-14",43810.916666666664,"2022-03-18",43810.25,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29936]
["Infrabel","29937","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,13,13,"2022-03-21",43810.916666666664,"2022-03-25",43810.25,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29937]
["Infrabel","29938","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,14,14,"2022-03-28",43810.916666666664,"2022-04-01",43810.25,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29938]
["Infrabel","29978","Athus - Meuse","< >","Y.NEFFE","HOUYET",2022,2022,13,14,"2022-03-25",43810.979166666664,"2022-03-28",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses à la grue dans 3 tunnels entre BK 8900 et 12100 \n ",null,null,29978]
["Infrabel","30103","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,40,40,"2021-09-27",43810.958333333336,"2021-10-01",43810.166666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy - Préparations \n ",null,null,30103]
["Infrabel","30104","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,42,42,"2021-10-11",43810.958333333336,"2021-10-15",43810.166666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy - finitions \n ",null,null,30104]
["Infrabel","30105","Lille - Charleroi",">","MONS","QUEVY",2021,2021,48,48,"2021-11-22",43810.833333333336,"2021-11-26",43810.208333333336,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \n ",null,null,30105]
["Infrabel","30107","Namur - Antwerpen",">","CHATELET","LE CAMPINAIRE",2021,2021,21,22,"2021-05-21",43810.9375,"2021-05-25",43810.229166666664,"4d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Phase 2.2 : Renouvellement Rails-Traverses-Ballast du Trapèze de la voie d'évitement (W-e 3 jours)",null,null,30107]
["Infrabel","30109","Namur - Antwerpen",">","CHATELET","LE CAMPINAIRE",2021,2021,25,25,"2021-06-15",43810.9375,"2021-06-19",43810.229166666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Phase 2.3 : Bourrage de révision, nettoyage + réglage de joints",null,null,30109]
["Infrabel","30110","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,10,10,"2021-02-28",43810.25,"2021-02-28",43810.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor",null,null,30110]
["Infrabel","30147","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,41,42,"2021-10-08",43810.958333333336,"2021-10-11",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Reprise en EBP-PLP des installations de Tamines et Auvelais.\r\nPas d'autres services dans la coupure (sauf train d'essais ES et ETCS). \n ",null,null,30147]
["Infrabel","30150","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,42,43,"2021-10-15",43810.958333333336,"2021-10-18",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Reprise en EBP-PLP des installations de Tamines et Auvelais.\r\nPas d'autres services dans la coupure (sauf train d'essais ES et ETCS). \n ",null,null,30150]
["Infrabel","30151","Namur - Antwerpen",">","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,35,35,"2021-08-23",43810.291666666664,"2021-08-25",43810.958333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réglage des CV pour préparer la MES PLP\r\nEssais de sécurité \n ",null,null,30151]
["Infrabel","30152","Namur - Antwerpen",">","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,35,35,"2021-08-25",43810.958333333336,"2021-08-28",43810.958333333336,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réglage des CV pour préparer la MES PLP\r\nEssais de sécurité \r\nPas d'autres services dans la coupure \n ",null,null,30152]
["Infrabel","30170","Namur - Antwerpen",">","CHATELET","LE CAMPINAIRE",2021,2021,25,26,"2021-06-19",43810.916666666664,"2021-06-21",43810.25,"2d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Phase 1.5 : Réalisation des contraintes & finitions",null,null,30170]
["Infrabel","30242","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,23,24,"2021-06-05",43810.072916666664,"2021-06-07",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Bundelkop Bundel Luchtbal\r\nWE 2 TLO ",null,null,30242]
["Infrabel","30244","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,24,25,"2021-06-12",43810.072916666664,"2021-06-14",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Bundelkop Bundel Luchtbal\r\nWE 3 TLO",null,null,30244]
["Infrabel","30252","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,22,23,"2021-05-29",43810.072916666664,"2021-05-31",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Bundelkop Bundel Luchtbal\r\nWE 1 ",null,null,30252]
["Infrabel","30302","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,13,14,"2022-03-26",43810.041666666664,"2022-03-28",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30302]
["Infrabel","30303","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,14,15,"2022-04-02",43810.041666666664,"2022-04-04",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30303]
["Infrabel","30305","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,16,17,"2022-04-16",43810.041666666664,"2022-04-18",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30305]
["Infrabel","30306","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,17,18,"2022-04-23",43810.041666666664,"2022-04-25",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30306]
["Infrabel","30308","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,18,19,"2022-04-30",43810.041666666664,"2022-05-02",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30308]
["Infrabel","30311","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,41,42,"2022-10-08",43810.041666666664,"2022-10-10",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30311]
["Infrabel","30312","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,43,44,"2022-10-22",43810.041666666664,"2022-10-24",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30312]
["Infrabel","30313","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,44,45,"2022-10-29",43810.041666666664,"2022-10-31",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30313]
["Infrabel","30314","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,45,46,"2022-11-05",43810.041666666664,"2022-11-07",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30314]
["Infrabel","30315","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,39,40,"2022-09-24",43810.041666666664,"2022-09-26",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30315]
["Infrabel","30316","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,48,49,"2022-11-26",43810.041666666664,"2022-11-28",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30316]
["Infrabel","30317","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,49,50,"2022-12-03",43810.041666666664,"2022-12-05",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30317]
["Infrabel","30318","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,40,41,"2022-10-01",43810.041666666664,"2022-10-03",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30318]
["Infrabel","30319","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2022,2022,20,21,"2022-05-14",43810.041666666664,"2022-05-16",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwing waterdichte rok van de onderbruggingen langsheen de Engelse lei (incl. opbraak en heraanleg spoor)\nOpgelet nevenliggend spoor A van L27A dient eveneens uit dienst te zijn begin en einde coupure !! \nDienst op enkel spoor tussen Y.Z. Groenenhoek en Y.Holland",null,null,30319]
["Infrabel","30320","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2022,2022,21,22,"2022-05-21",43810.041666666664,"2022-05-23",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwing waterdichte rok van de onderbruggingen langsheen de Engelse lei (incl. opbraak en heraanleg spoor)\r\n\r\nOpgelet nevenliggend spoor A van L27A dient eveneens uit dienst te zijn begin en einde coupure !! \nDienst op enkel spoor tussen Y.Z. Groenenhoek en Y.Holland",null,null,30320]
["Infrabel","30563","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,41,42,"2022-10-08",43810.041666666664,"2022-10-10",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30563]
["Infrabel","30564","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,43,44,"2022-10-22",43810.041666666664,"2022-10-24",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30564]
["Infrabel","30565","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,44,45,"2022-10-29",43810.041666666664,"2022-10-31",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30565]
["Infrabel","30566","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,45,46,"2022-11-05",43810.041666666664,"2022-11-07",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30566]
["Infrabel","30567","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,39,40,"2022-09-24",43810.041666666664,"2022-09-26",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30567]
["Infrabel","30568","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,48,49,"2022-11-26",43810.041666666664,"2022-11-28",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30568]
["Infrabel","30569","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,49,50,"2022-12-03",43810.041666666664,"2022-12-05",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,30569]
["Infrabel","30580","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2021,2021,23,23,"2021-05-31",43810.993055555555,"2021-06-05",43810.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP3HKV ",null,null,30580]
["Infrabel","30582","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2021,2021,23,24,"2021-06-05",43810.958333333336,"2021-06-06",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP4+ ",null,null,30582]
["Infrabel","30583","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2021,2021,48,48,"2021-11-22",43810.993055555555,"2021-11-27",43810.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP3HKM",null,null,30583]
["Infrabel","30584","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2021,2021,48,49,"2021-11-27",43810.25,"2021-11-28",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP4+",null,null,30584]
["Infrabel","30587","Namur - Antwerpen","< >","AUVELAIS","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,14,15,"2021-04-03",43810.958333333336,"2021-04-04",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z16. 51\r\nP4+ Mini CTL ",null,null,30587]
["Infrabel","30588","Namur - Antwerpen","< >","AUVELAIS","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,22,23,"2021-05-29",43810.958333333336,"2021-05-30",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z16. 51\r\nP4+ Mini CTL ",null,null,30588]
["Infrabel","30754","Lille - Charleroi","< >","MONS","QUEVY",2022,2022,6,7,"2022-02-05",43810.003472222219,"2022-02-06",43810.996527777781,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise HS pour finitions chantier P 93 + entreiten",null,null,30754]
["Infrabel","30758","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2021,2021,26,29,"2021-06-25",43810.958333333336,"2021-07-12",43810.25,"17d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A\r\n- Coupures L124A voie B \r\n- De nuit uniquement",null,null,30758]
["Infrabel","30777","Lille - Charleroi","< >","MONS","QUEVY",2022,2022,7,8,"2022-02-12",43810.003472222219,"2022-02-13",43810.996527777781,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise HS pour finitions chantier P 93 + entreiten",null,null,30777]
["Infrabel","30778","Lille - Charleroi","< >","MONS","QUEVY",2022,2022,8,9,"2022-02-19",43810.003472222219,"2022-02-20",43810.996527777781,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise HS pour finitions chantier P 93 + entreiten",null,null,30778]
["Infrabel","30780","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,13,13,"2022-03-21",43810.9375,"2022-03-25",43810.229166666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Phase 6 : Travaux Voie sur CTL de nuits semaine\r\nPréparation plateforme 64BJ + drainage, etc….\r\nCTL de nuits en semaine, les nuits en 22h30/05h30\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hors tension cas 27319 + 321.\r\n-\tVB  ",null,null,30780]
["Infrabel","30781","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,13,14,"2022-03-25",43810.979166666664,"2022-03-28",43810.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Phase 7 : Week-end n°2\r\nMise en place de la voie B / L130 et renouvellement.\r\nCTL WE n°2, du vendredi 25/03/2022 à 22h30 en continu jusqu’au lundi 28/03/2022 à 05h :\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hors tension cas 2",null,null,30781]
["Infrabel","30783","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,33,34,"2022-08-08",43810.9375,"2022-08-20",43810.229166666664,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Phase 10 : Travaux Voie sur CTL de nuits semaine\r\nBourrage révision, contrainte, pose caniveaux pistes, finitions chantier….\r\nCTL de nuits en semaine, les nuits en 22h30/05h30\r\n\r\n-\tVoie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hors tension cas 27319 +",null,null,30783]
["Infrabel","30785","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,14,14,"2022-03-28",43810.9375,"2022-04-02",43810.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Phase 8 : Travaux Voie sur CTL de nuits semaine\r\nFinition W-e 2 + drainage, etc….\r\nCTL de nuits en semaine, les nuits en 22h30/05h30 :\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hors tension cas 27319 + 321.\r\n-\tVB + VA L130 etn",null,null,30785]
["Infrabel","30790","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,16,17,"2022-04-16",43810.020833333336,"2022-04-19",43810.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Y La Sambre - 4 AS - 17AF/BF (simpl), 19AF/BF, 20F, 18F + quai Marchienne",null,null,30790]
["Infrabel","30791","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,17,18,"2022-04-23",43810.020833333336,"2022-04-25",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Y La Sambre - 4 AS - 17AF/BF (simpl), 19AF/BF, 20F, 18F + quai Marchienne",null,null,30791]
["Infrabel","30793","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,18,19,"2022-04-30",43810.020833333336,"2022-05-02",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Y La Sambre - 4 AS - 17AF/BF (simpl), 19AF/BF, 20F, 18F + quai Marchienne",null,null,30793]
["Infrabel","30794","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,19,20,"2022-05-07",43810.020833333336,"2022-05-09",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Y La Sambre - 4 AS - 17AF/BF (simpl), 19AF/BF, 20F, 18F + quai Marchienne",null,null,30794]
["Infrabel","30802","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,20,21,"2022-05-14",43810.020833333336,"2022-05-16",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Y La Sambre - 4 AS - 17AF/BF (simpl), 19AF/BF, 20F, 18F + quai Marchienne\r\nMassifié avec Lowijck",null,null,30802]
["Infrabel","30803","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,21,22,"2022-05-21",43810.020833333336,"2022-05-23",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Y La Sambre - 4 AS - 17AF/BF (simpl), 19AF/BF, 20F, 18F + quai Marchienne",null,null,30803]
["Infrabel","30804","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,22,23,"2022-05-28",43810.020833333336,"2022-05-30",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Y La Sambre - 4 AS - 17AF/BF (simpl), 19AF/BF, 20F, 18F + quai Marchienne",null,null,30804]
["Infrabel","30806","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,23,24,"2022-06-04",43810.020833333336,"2022-06-07",43810.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Y La Sambre - 4 AS - 17AF/BF (simpl), 19AF/BF, 20F, 18F + quai Marchienne",null,null,30806]
["Infrabel","30838","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,12,13,"2022-03-19",43810.041666666664,"2022-03-21",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november",null,null,30838]
["Infrabel","30845","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,25,26,"2022-06-13",43810.958333333336,"2022-06-25",43810.208333333336,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL toutes les nuits de semaine pour travaux préparatoires - Pose 2nd tablier des ponts 10&11",null,null,30845]
["Infrabel","30846","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,12,12,"2022-03-14",43810.996527777781,"2022-03-18",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november ",null,null,30846]
["Infrabel","30847","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,23,23,"2022-05-30",43810.996527777781,"2022-06-03",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november",null,null,30847]
["Infrabel","30848","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,34,35,"2022-08-20",43810.003472222219,"2022-08-22",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november ",null,null,30848]
["Infrabel","30849","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,19,20,"2022-05-02",43810.958333333336,"2022-05-14",43810.208333333336,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL toutes les nuits de semaine pour travaux préparatoires - Pose 2nd tablier des ponts 10&11",null,null,30849]
["Infrabel","30850","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,47,47,"2022-11-14",43810.996527777781,"2022-11-18",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november",null,null,30850]
["Infrabel","30851","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,37,38,"2022-09-05",43810.958333333336,"2022-09-17",43810.208333333336,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL de nuit pour les travaux de finition du second tablier sur les ponts 10 et 11",null,null,30851]
["Infrabel","30853","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,34,34,"2022-08-15",43810.996527777781,"2022-08-19",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november ",null,null,30853]
["Infrabel","30854","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,46,46,"2022-11-07",43810.989583333336,"2022-11-11",43810.197916666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"SAVU de NUIT : travaux préparatoire  grande coupure Grill coté LLN\r\net CTL les NUITs de Weekend\r\ntravaux compatible avec les CTL de nuits de la L124 (car SAVU de nuit de semaine)",null,null,30854]
["Infrabel","30855","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,18,18,"2022-04-25",43810.979166666664,"2022-04-30",43810.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Phase 10 : Travaux Voie sur CTL de nuits semaine\r\nBourrage révision, contrainte, pose caniveaux pistes, finitions chantier….\r\nCTL de nuits en semaine, les nuits en 22h30/05h30 :\r\n\r\n-\tVoie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hors tension cas 27319",null,null,30855]
["Infrabel","30856","Namur - Antwerpen","< >","FLEURUS","TILLY",2022,2022,19,23,"2022-05-02",43810.958333333336,"2022-06-04",43810.208333333336,"33d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Phase 2: Renouvellement des traverses à l'aide du train P entre Fleurus et Tilly en voie A (entre 15BN et 04BO).\r\nL140 Voie B, HS toutes les nuits en semaine durant la période allant du 5^6/09/2022 jusqu'au 25^26/11/2022.\r\n\rART à 60km/H sur toute la zo",null,null,30856]
["Infrabel","30857","Namur - Antwerpen","< >","FLEURUS","TILLY",2022,2022,25,26,"2022-06-13",43810.958333333336,"2022-06-25",43810.208333333336,"12d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses à l'aide du train P entre Fleurus et Tilly en voie A (entre 15BN et 04BO).\r\nL140 Voie B, HS toutes les nuits en semaine durant la période allant du 5^6/09/2022 jusqu'au 25^26/11/2022\r\nART à 60km/H sur toute la zone du cha",null,null,30857]
["Infrabel","30858","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,9,10,"2022-02-25",43810.923611111109,"2022-02-28",43810.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF",null,null,30858]
["Infrabel","30859","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,8,9,"2022-02-18",43810.923611111109,"2022-02-21",43810.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF",null,null,30859]
["Infrabel","30860","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,12,13,"2022-03-18",43810.923611111109,"2022-03-21",43810.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF",null,null,30860]
["Infrabel","30861","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,11,12,"2022-03-11",43810.923611111109,"2022-03-14",43810.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF",null,null,30861]
["Infrabel","30862","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,43,43,"2022-10-17",43810.923611111109,"2022-10-22",43810.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparation renouvellement de traverses entre Ath et Lens ",null,null,30862]
["Infrabel","30863","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,44,44,"2022-10-24",43810.923611111109,"2022-10-29",43810.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparation renouvellement de traverses entre Ath et Lens ",null,null,30863]
["Infrabel","30865","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,45,45,"2022-10-31",43810.923611111109,"2022-11-05",43810.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparation renouvellement de traverses entre Ath et Lens ",null,null,30865]
["Infrabel","30866","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,47,48,"2022-11-18",43810.9375,"2022-11-21",43810.229166666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 ",null,null,30866]
["Infrabel","30867","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,48,49,"2022-11-25",43810.9375,"2022-11-28",43810.229166666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93",null,null,30867]
["Infrabel","30868","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,49,50,"2022-12-02",43810.9375,"2022-12-05",43810.229166666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 ",null,null,30868]
["Infrabel","30876","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,15,17,"2022-04-08",43810.958333333336,"2022-04-19",43810.208333333336,"11d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron (Pieux)\r\nCTLs de nuit",null,null,30876]
["Infrabel","30877","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,22,23,"2022-05-28",43810.958333333336,"2022-06-03",43810.208333333336,"6d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Préparation pour renouvellement du PI métallique 53.680 + construction passerelle en gare de Mouscron\r\nCTLs de nuit",null,null,30877]
["Infrabel","30878","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,23,24,"2022-06-03",43810.958333333336,"2022-06-07",43810.208333333336,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PI métallique 53.680 (3 ponts bacs + 2 passerelles) + construction passerelle en gare de Mouscron\r\nCTL en continu de 3 jours nécessaire",null,null,30878]
["Infrabel","30879","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,24,24,"2022-06-07",43810.958333333336,"2022-06-09",43810.208333333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Finitions pour renouvellement du PI métallique 53.680\r\nCTLs de nuit",null,null,30879]
["Infrabel","30880","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,25,26,"2022-06-16",43810.958333333336,"2022-06-23",43810.208333333336,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Finitions pour renouvellement du PI métallique 53.680 (bourrage, régulation contraintes, enlèvement ART, ...) + construction passerelle en gare de Mouscron\r\nCTLs de nuit",null,null,30880]
["Infrabel","30881","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,27,28,"2022-07-01",43810.958333333336,"2022-07-04",43810.208333333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Finitions pour renouvellement du PI métallique 53.680 (bourrage, régulation contraintes, enlèvement ART, ...) + construction passerelle en gare de Mouscron\r\nCTLs de nuit",null,null,30881]
["Infrabel","30882","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,34,35,"2022-08-19",43810.958333333336,"2022-08-22",43810.208333333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Finitions pour renouvellement du PI métallique 53.680 (bourrage, régulation contraintes, enlèvement ART, ...) + construction passerelle en gare de Mouscron\r\nCTLs de nuit",null,null,30882]
["Infrabel","30883","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2022,2022,40,41,"2022-09-30",43810.958333333336,"2022-10-03",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 123 Harmelen",null,null,30883]
["Infrabel","30884","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2022,2022,42,43,"2022-10-10",43810.958333333336,"2022-10-16",43810.208333333336,"6d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 123 Harmelen\r\nBourrage de révision\r\nAsphatage\r\nFinitions",null,null,30884]
["Infrabel","30890","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,1,34,"2022-01-01",43810,"2022-08-20",43810.25,"231d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes",null,null,30890]
["Infrabel","30891","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,11,12,"2022-03-11",43810.979166666664,"2022-03-14",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36",null,null,30891]
["Infrabel","30892","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,13,14,"2022-03-25",43810.979166666664,"2022-03-28",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36",null,null,30892]
["Infrabel","30893","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2022,2022,38,39,"2022-09-16",43810.979166666664,"2022-09-19",43810.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre",null,null,30893]
["Infrabel","30894","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2022,2022,39,40,"2022-09-24",43810.958333333336,"2022-09-25",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre",null,null,30894]
["Infrabel","30900","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,26,27,"2022-06-24",43810.958333333336,"2022-06-27",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye",null,null,30900]
["Infrabel","30901","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,27,28,"2022-07-01",43810.958333333336,"2022-07-04",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast",null,null,30901]
["Infrabel","30902","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,28,29,"2022-07-08",43810.958333333336,"2022-07-11",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast",null,null,30902]
["Infrabel","30906","Athus - Meuse","< >","Y.NEFFE","HOUYET",2022,2022,14,15,"2022-04-01",43810.979166666664,"2022-04-04",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses à la grue dans 3 tunnels entre BK 8900 et 12100",null,null,30906]
["Infrabel","30907","Athus - Meuse","< >","Y.NEFFE","HOUYET",2022,2022,15,16,"2022-04-08",43810.979166666664,"2022-04-11",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de boueux et entretiens d'appareils de voies (bourrage, nivellement,...)",null,null,30907]
["Infrabel","30913","Erquelinnes - Montzen","< >","STATTE","JAVA",2022,2022,12,13,"2022-03-18",43810.958333333336,"2022-03-21",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte",null,null,30913]
["Infrabel","30914","Erquelinnes - Montzen","< >","STATTE","JAVA",2022,2022,14,14,"2022-03-28",43810.958333333336,"2022-04-02",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte\r\nBourrage + tx finition",null,null,30914]
["Infrabel","30915","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,25,26,"2022-06-18",43810,"2022-06-20",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD ",null,null,30915]
["Infrabel","30916","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,26,27,"2022-06-25",43810,"2022-06-27",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD",null,null,30916]
["Infrabel","30992","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,19,19,"2021-05-03",43810.986111111109,"2021-05-08",43810.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141",null,null,30992]
["Infrabel","30993","Lille - Charleroi","< >","Y.FAMILLEUREUX","MANAGE",2021,2021,20,27,"2021-05-10",43810.986111111109,"2021-07-03",43810.194444444445,"54d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS Manage  12AI/12BI-14AI/15BI-14BI-15AI/16BI-16AI/17BI-37I\r\nSimplification AS 24B-13A/13B-23A/23B et CDS N35 L141",null,null,30993]
["Infrabel","30994","Lille - Charleroi","< >","ATH","LEUZE",2021,2021,27,28,"2021-07-03",43810.020833333336,"2021-07-05",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 34AF/34BF + 42F",null,null,30994]
["Infrabel","30995","Lille - Charleroi","< >","ATH","LEUZE",2021,2021,28,29,"2021-07-10",43810.020833333336,"2021-07-12",43810.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 34AF/34BF + 42F",null,null,30995]
["Infrabel","30996","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,4,4,"2021-01-18",43810.958333333336,"2021-01-22",43810.166666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk",null,null,30996]
["Infrabel","31000","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,21,21,"2021-05-18",43810.020833333336,"2021-05-22",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwwerking Nieuwe ondertunneling Kortrijk",null,null,31000]
["Infrabel","31001","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,22,22,"2021-05-24",43810.993055555555,"2021-05-28",43810.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwwerking Nieuwe ondertunneling Kortrijk",null,null,31001]
["Infrabel","31004","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,5,6,"2021-01-30",43810,"2021-02-01",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk.",null,null,31004]
["Infrabel","31007","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,14,14,"2021-03-28",43810.0625,"2021-03-28",43810.204861111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk",null,null,31007]
["Infrabel","31095","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,23,24,"2021-06-05",43810.013888888891,"2021-06-07",43810.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"In dienst name van Piloot 3 van de inklinking SIW ",null,null,31095]
["Infrabel","31189","Athus - Meuse","< >","HALANZY","VIRTON",2021,2021,19,20,"2021-05-08",43810.958333333336,"2021-05-09",43810.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nDépose de l'ancien 14BS et pose de voie courante ",null,null,31189]
["Infrabel","31190","Athus - Meuse",">","HALANZY","AUBANGE",2021,2021,21,22,"2021-05-22",43810.958333333336,"2021-05-23",43810.625,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 138.830 à 138.870 (PN41) - pose revêtement routier / bourrage vitesse normale / réglage contraintes",null,null,31190]
["Infrabel","31207","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,20,21,"2021-05-10",43810.951388888891,"2021-05-21",43810.229166666664,"11d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"RER : \r\nSAVU DE NUIT en semaine 22:50-05:30\r\net CTL nuit les weekend samedi a dimanche 00:30-05:30\r\nTravaux préparatoires de la renovation de la Y.LLN",null,null,31207]
["Infrabel","31208","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,32,34,"2021-08-02",43810.951388888891,"2021-08-18",43810.229166666664,"16d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"RER : \r\nSAVU DE NUIT en semaine 22:50-05:30\r\net CTL nuit les weekend samedi a dimanche 00:30-05:30\r\nTravaux préparatoires de la renovation de la Y.LLN",null,null,31208]
["Infrabel","31390","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,7,7,"2021-02-08",43810.993055555555,"2021-02-12",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,31390]
["Infrabel","31391","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,11,11,"2021-03-08",43810.993055555555,"2021-03-13",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,31391]
["Infrabel","31392","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,12,12,"2021-03-15",43810.993055555555,"2021-03-20",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,31392]
["Infrabel","31393","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,33,33,"2021-08-09",43810.993055555555,"2021-08-14",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,31393]
["Infrabel","31394","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,40,40,"2021-09-27",43810.993055555555,"2021-10-01",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,31394]
["Infrabel","31395","Namur - Antwerpen","< >","AISEAU","FARCIENNES",2021,2021,40,41,"2021-10-01",43810.958333333336,"2021-10-04",43810.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,31395]
["Infrabel","31396","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,43,43,"2021-10-18",43810.993055555555,"2021-10-23",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,31396]
["Infrabel","31397","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,42,42,"2021-10-11",43810.993055555555,"2021-10-16",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,31397]
["Infrabel","31398","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,49,49,"2021-11-29",43810.993055555555,"2021-12-04",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,31398]
["Infrabel","31399","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,48,48,"2021-11-22",43810.993055555555,"2021-11-27",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625",null,null,31399]
["Infrabel","31449","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,14,14,"2021-03-29",43810.958333333336,"2021-04-02",43810.229166666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,31449]
["Infrabel","31462","Lille - Charleroi","< >","LUTTRE","Y.NORD",2021,2021,20,21,"2021-05-15",43810.958333333336,"2021-05-17",43810.25,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A\r\n- Coupures L124A voie A \r\n- De nuit uniquement.\r\namplitude 5 h samedi et 4 h le dimanche \n ",null,null,31462]
["Infrabel","31483","Erquelinnes - Montzen","< >","CHARLEROI-SUD","MARCHIENNE-ZONE",2021,2021,11,12,"2021-03-13",43810.170138888891,"2021-03-14",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5. 51\r\nP4+",null,null,31483]
["Infrabel","31486","Erquelinnes - Montzen","< >","CHARLEROI-SUD","MARCHIENNE-ZONE",2021,2021,11,11,"2021-03-08",43810.902777777781,"2021-03-13",43810.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5. 51\r\nP3  HKV",null,null,31486]
["Infrabel","31685","Lille - Charleroi","< >","LOT","HALLE",2022,2022,18,21,"2022-04-25"," ","2022-05-21"," ","26d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B",null,null,31685]
["Infrabel","31686","Lille - Charleroi","< >","LOT","HALLE",2022,2022,23,26,"2022-05-30"," ","2022-06-25"," ","26d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B",null,null,31686]
["Infrabel","31696","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,15,15,"2021-04-05",43810.958333333336,"2021-04-09",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord - bourrage de revision, finitions",null,null,31696]
["Infrabel","31728","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2021,2021,12,13,"2021-03-20",43810.208333333336,"2021-03-21",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z10. 51   P4+",null,null,31728]
["Infrabel","31785","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,39,39,"2021-09-20",43810.958333333336,"2021-09-25",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits",null,null,31785]
["Infrabel","31786","Erquelinnes - Montzen","< >","LA SAMBRE","HOURPES",2021,2021,43,43,"2021-10-18",43810.958333333336,"2021-10-23",43810.173611111109,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement 09AL & 09BL & 10AL & 10BL",null,null,31786]
["Infrabel","31820","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2021,2021,12,12,"2021-03-15",43810.979166666664,"2021-03-20",43810.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z10. 51   P3 HKV",null,null,31820]
["Infrabel","31876","Lille - Charleroi","< >","LENS","ATH",2021,2021,46,47,"2021-11-13",43810.25,"2021-11-14",43810.916666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réglage CV Brugelette-ATH ",null,null,31876]
["Infrabel","31877","Lille - Charleroi","< >","LENS","ATH",2021,2021,47,48,"2021-11-19",43810.916666666664,"2021-11-21",43810.916666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise en service BA Brugelette/Ath ",null,null,31877]
["Infrabel","31886","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,27,28,"2022-07-01",43810.958333333336,"2022-07-04",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor ",null,null,31886]
["Infrabel","31887","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,29,30,"2022-07-15",43810.958333333336,"2022-07-18",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor",null,null,31887]
["Infrabel","31888","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,46,46,"2022-11-07",43810.923611111109,"2022-11-12",43810.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparation renouvellement de traverses entre Ath et Lens ",null,null,31888]
["Infrabel","31889","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2022,2022,47,47,"2022-11-14",43810.923611111109,"2022-11-19",43810.215277777781,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Travaux préparation renouvellement de traverses entre Ath et Lens",null,null,31889]
["Infrabel","31890","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,48,48,"2022-11-21",43810.923611111109,"2022-11-26",43810.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparation renouvellement de traverses entre Ath et Lens",null,null,31890]
["Infrabel","31891","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,49,49,"2022-11-28",43810.923611111109,"2022-12-03",43810.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparation renouvellement de traverses entre Ath et Lens",null,null,31891]
["Infrabel","31892","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,50,50,"2022-12-05",43810.923611111109,"2022-12-10",43810.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparation renouvellement de traverses entre Ath et Lens ",null,null,31892]
["Infrabel","31893","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,51,51,"2022-12-12",43810.923611111109,"2022-12-17",43810.215277777781,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparation renouvellement de traverses entre Ath et Lens ",null,null,31893]
["Infrabel","31902","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,33,34,"2022-08-12",43810.958333333336,"2022-08-15",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor ",null,null,31902]
["Infrabel","31903","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,34,35,"2022-08-19",43810.958333333336,"2022-08-22",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor ",null,null,31903]
["Infrabel","31904","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,42,43,"2022-10-14",43810.958333333336,"2022-10-17",43810.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor",null,null,31904]
["Infrabel","32067","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,7,8,"2022-02-12",43810.079861111109,"2022-02-14",43810.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,32067]
["Infrabel","32072","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,13,14,"2022-03-26",43810.079861111109,"2022-03-28",43810.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,32072]
["Infrabel","32084","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,33,33,"2021-08-09",43810.958333333336,"2021-08-13",43810.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits",null,null,32084]
["Infrabel","32260","Lille - Charleroi",">","LUTTRE","Y.NORD",2021,2021,13,17,"2021-03-27",43810.958333333336,"2021-04-19",43810.25,"23d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Travaux de Réélectrification L. 124A voie A",null,null,32260]
["Infrabel","32276","Lille - Charleroi",">","BRUGELETTE","ATH",2022,2022,48,49,"2022-11-21",43810.166666666664,"2022-12-02",43810.996527777781,"11d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"renouvellement de traverses entre Ath et Lens",null,null,32276]
["Infrabel","32283","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,4,4,"2021-01-18",43810.944444444445,"2021-01-23",43810.236111111109,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P3 HKV - Zone 3 AI53",null,null,32283]
["Infrabel","32285","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,4,4,"2021-01-18",43810.979166666664,"2021-01-23",43810.166666666664,"5d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53",null,null,32285]
["Infrabel","32289","Lille - Charleroi",">","LUTTRE","ROUX",2021,2021,51,52,"2021-12-13",43810.25,"2021-12-20",43810.25,"7d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124-124A FLU-FMR ",null,null,32289]
["Infrabel","32291","Lille - Charleroi",">","ROUX","MARCHIENNE-AU-PONT",2021,2021,52,52,"2021-12-20",43810.25,"2021-12-24",43810.666666666664,"4d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124-124A FLU-FMR ",null,null,32291]
["Infrabel","32295","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,8,8,"2021-02-15",43810.979166666664,"2021-02-20",43810.166666666664,"5d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53",null,null,32295]
["Infrabel","32297","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,8,9,"2021-02-20",43810.3125,"2021-02-21",43810.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 - P4",null,null,32297]
["Infrabel","32299","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","BLANDAIN-FRONTIERE",2021,2021,8,8,"2021-02-15",43810.944444444445,"2021-02-20",43810.243055555555,"5d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z7.54",null,null,32299]
["Infrabel","32378","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,38,39,"2021-09-18",43810.333333333336,"2021-09-20",43810.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q",null,null,32378]
["Infrabel","9917","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,41,41,"2021-10-04",43810.958333333336,"2021-10-08",43810.166666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy ",null,null,9917]
["Infrabel","10355","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,14,17,"2021-04-02",43810.958333333336,"2021-04-19",43810.166666666664,"17d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nTrafic HKM à détourner",null,null,10355]
["Infrabel","20460","Namur - Antwerpen","< >","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,7,9,"2021-02-12",43810.989583333336,"2021-02-22",43810.166666666664,"10d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER CTL : \r\n+ assainissement de plateformess \r\n+ pose 5 AW\r\n+ Ripage\r\n+ tvx CAT & sign\r\n+ renovation pont (av des Combattants)",null,null,20460]
["Infrabel","29278","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2022,2022,34,37,"2022-08-20",43810.333333333336,"2022-09-05",43810.25,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses avec train P93\r\nRenouvellement PI",null,null,29278]
["Infrabel","29293","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,37,39,"2022-09-05",43810.333333333336,"2022-09-19",43810.25,"14d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast",null,null,29293]
["Infrabel","29295","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,40,40,"2022-09-26",43810.333333333336,"2022-09-30",43810.666666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage + tx finitions",null,null,29295]
["Infrabel","30903","Athus - Meuse",">","VIRTON","AUBANGE",2022,2022,37,39,"2022-09-05",43810.333333333336,"2022-09-19",43810.25,"14d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast",null,null,30903]
["Infrabel","30904","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,41,41,"2022-10-03",43810.333333333336,"2022-10-07",43810.666666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage + tx finitions",null,null,30904]
["Infrabel","30905","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,42,42,"2022-10-10",43810.333333333336,"2022-10-14",43810.666666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage + tx finitions",null,null,30905]
["Infrabel","30908","Athus - Meuse",">","GEDINNE","PALISEUL",2022,2022,37,39,"2022-09-05",43810.333333333336,"2022-09-19",43810.25,"14d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Assainissement de la voie A",null,null,30908]
["Infrabel","29949","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,37,39,"2022-09-05","06:00:00","2022-09-19","22:00:00","14d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A",null,null,29949]
["Infrabel","29953","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,40,40,"2022-09-26",43810.333333333336,"2022-09-30",43810.666666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A",null,null,29953]
["Infrabel","29955","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,42,42,"2022-10-10",43810.333333333336,"2022-10-14",43810.666666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A",null,null,29955]

{"sheet":"Data","index":4,"n_rows":24,"n_cols":7,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction"]
["SNCF R",87,"Boulogne-Calais",1,"All day",10868,"Signal work"]
[null,null,"Calais-Dunkerque-Hazebrouck",2,"Day",null,"Switch work"]
[null,null,"Calais-Lille-Aulnoye",3,"Night",null,"Catenary work"]
[null,null,"Hazebrouck-Lens-Aulnoye",4,null,null,"Track work"]
[null,null,"Amiens-Douai",5,null,null,"Rail work"]
[null,null,"Paris-Amiens",6,null,null,"Tunnel work"]
[null,null,"Paris-Busigny",7,null,null,"Bridge work"]
[null,null,"Aulnoye-Longuyon",8,null,null,"Misc. Work"]
[null,null,"Longuyon-Metz-Sarrebourg",9,null,null,"Maintanance"]
[null,null,"Longuyon-Nancy-Sarrebourg",10]
[null,null,"Lerouville-Metz",11]
[null,null,"Lerouville-Nancy",12]
[null,null,"Sarrebourg-Basel",13]
[null,null,"Dijon-Toul",14]
[null,null,"Dijon-Lyon",15]
[null,null,"Dijon-Amberieu-Lyon",16]
[null,null,"Lyon-Valence",17]
[null,null,"Valence - Avignon",18]
[null,null,"Avignon-Miramasparouest",19]
[null,null,"Avignon-Miramasparest",20]
[null,null,"Miramas-Marseille",21]
[null,null,"Miramas-Fos-Marseille",22]
[null,null,"Aulnoye-Feignies-Jeumont",23]

{"sheet":"SNCFR","index":5,"n_rows":715,"n_cols":31,"rows_kept":715,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["SNCF Réseau","8290981661_8290799961","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2021,2021,7,45,"2021-02-15","00:00","2021-11-08T03:00:00","03:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","8290981661_8290798161","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2021,2021,10,43,"2021-03-08T23:30:00","23:30","2021-10-29T05:15:00","05:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","8290981661_8290799161","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2021,2021,7,45,"2021-02-15","00:00","2021-11-08T03:10:00","03:10",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","8290981661_8290796561","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2020,2021,51,49,"2020-12-14T14:04:00","14:04","2021-12-10T14:55:00","14:55",3730,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290981661_8290797361","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2020,2021,51,49,"2020-12-14T14:20:00","14:20","2021-12-10T15:25:00","15:25",3855,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290911761","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,49,"2020-12-14T13:36:00","13:36","2021-12-10T14:51:00","14:51",3580,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290908561","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,48,"2020-12-20T23:50:00","23:50","2021-12-05T02:50:00","02:50",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290906961","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2021,7,40,"2021-02-15T10:40:00","10:40","2021-10-08T14:30:00","14:30",931,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290910161","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,48,"2020-12-20T23:50:00","23:50","2021-12-05T02:50:00","02:50",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290906161","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,48,"2020-12-20T23:40:00","23:40","2021-12-05T02:40:00","02:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290910961","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2021,7,40,"2021-02-15T10:07:00","10:07","2021-10-08T14:15:00","14:15",916,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290907761","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,48,"2020-12-20T23:40:00","23:40","2021-12-05T02:40:00","02:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290912561","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,49,"2020-12-14T13:25:00","13:25","2021-12-10T14:24:00","14:24",3485,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290909361","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,49,"2020-12-14T13:24:00","13:24","2021-12-10T14:11:00","14:11",3433,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290980361_8290900561","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2020,2021,51,49,"2020-12-14T13:57:00","13:57","2021-12-10T14:37:00","14:37",3654,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290980361_8290903961","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2020,2021,52,48,"2020-12-21","00:00","2021-11-29T03:10:00","03:10",60,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8290980361_8290901361","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2021,2021,6,44,"2021-02-08T23:00:00","23:00","2021-11-05T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"77 jours dans le régime binaire"]
["SNCF Réseau","8290980361_8290903161","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2020,2021,51,49,"2020-12-14T14:30:00","14:30","2021-12-10T15:50:00","15:50",3959,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290980361_8290902361","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2020,2021,52,48,"2020-12-21","00:00","2021-11-29T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290843961","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2021,51,49,"2020-12-14T10:15:00","10:15","2021-12-10T11:50:00","11:50",2971,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290847161","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2021,2021,12,47,"2021-03-22T22:21:00","22:21","2021-11-26T05:35:00","05:35",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290845561","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2021,2021,12,47,"2021-03-22T23:04:00","23:04","2021-11-26T04:23:00","04:23",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290844761","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2021,52,48,"2020-12-27T23:00:00","23:00","2021-12-05T02:32:00","02:32",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290846361","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2021,51,49,"2020-12-14T13:43:00","13:43","2021-12-10T14:09:00","14:09",3552,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290843161","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2021,51,49,"2020-12-14T01:36:00","01:36","2021-12-06T04:13:00","04:13",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290825961","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,49,"2020-12-14T10:38:00","10:38","2021-12-10T11:48:00","11:48",2962,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290829361","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,49,"2020-12-14T13:07:00","13:07","2021-12-10T13:57:00","13:57",3502,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290826761","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,47,"2020-12-20T23:50:00","23:50","2021-11-28T03:15:00","03:15",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290830161","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,49,"2020-12-14T10:11:00","10:11","2021-12-10T11:38:00","11:38",2921,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290825161","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,49,"2020-12-14T13:51:00","13:51","2021-12-10T14:27:00","14:27",3627,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290828561","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,47,"2020-12-20T00:15:00","00:15","2021-11-28T02:45:00","02:45",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290886161","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2021,51,49,"2020-12-14T13:45:00","13:45","2021-12-10T14:18:00","14:18",3589,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290886961","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:28:00","02:28",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290888561","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2021,51,49,"2020-12-14T01:10:00","01:10","2021-12-06T03:45:00","03:45",193,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290887761","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2021,51,49,"2020-12-14T10:37:00","10:37","2021-12-10T12:05:00","12:05",3034,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290884561","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2021,2021,10,40,"2021-03-08T10:21:00","10:21","2021-10-08T15:14:00","15:14",446,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290885361","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2021,2021,10,40,"2021-03-08T08:50:00","08:50","2021-10-08T15:05:00","15:05",443,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","8290981261_8290802761","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2020,2021,51,49,"2020-12-14T11:22:00","11:22","2021-12-10T12:48:00","12:48",3214,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981261_8290804561","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8290981261_8290801161","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2020,2021,51,49,"2020-12-14T01:10:00","01:10","2021-12-06T04:10:00","04:10",203,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8290981261_8290803561","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2021,2021,5,47,"2021-02-01T23:05:00","23:05","2021-11-26T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","8290981261_8290801961","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2020,2021,51,49,"2020-12-14T10:30:00","10:30","2021-12-10T11:05:00","11:05",2782,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980261_8290883361","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2020,2021,51,49,"2020-12-14T14:25:00","14:25","2021-12-10T15:08:00","15:08",3784,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290980261_8290879961","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2021,2021,2,46,"2021-01-11T22:43:00","22:43","2021-11-19T04:43:00","04:43",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8290980261_8290881761","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2020,2021,51,49,"2020-12-14T09:52:00","09:52","2021-12-10T11:00:00","11:00",2751,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290980261_8290882561","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2020,2021,51,41,"2020-12-14T00:20:00","00:20","2021-10-11T03:00:00","03:00",38,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8290980261_8290880961","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2020,2021,51,41,"2020-12-14T01:00:00","01:00","2021-10-11T04:00:00","04:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8290981561_8290890161","Calais-Lille-Aulnoye",">","Lille Lambersart",null,2020,2021,51,49,"2020-12-14T10:19:00","10:19","2021-12-10T11:15:00","11:15",2824,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981561_8290890961","Calais-Lille-Aulnoye",">","Lille Lambersart",null,2020,2021,51,49,"2020-12-14T11:05:00","11:05","2021-12-10T12:00:00","12:00",3012,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290789761","Aulnoye-Longuyon",">","Hirson","Liart",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:20:00","03:20",173,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290788161","Aulnoye-Longuyon",">","Hirson","Liart",2021,2021,7,40,"2021-02-15T09:30:00","09:30","2021-10-08T14:37:00","14:37",648,"DAY",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290790561","Aulnoye-Longuyon",">","Hirson","Liart",2020,2021,51,49,"2020-12-14T14:25:00","14:25","2021-12-10T15:00:00","15:00",3765,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290786561","Aulnoye-Longuyon",">","Hirson","Liart",2020,2021,51,49,"2020-12-14T11:45:00","11:45","2021-12-10T13:05:00","13:05",3285,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290788961","Aulnoye-Longuyon",">","Hirson","Liart",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:15:00","03:15",168,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290787361","Aulnoye-Longuyon",">","Hirson","Liart",2021,2021,7,40,"2021-02-15T09:10:00","09:10","2021-10-08T14:35:00","14:35",647,"DAY",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290896161","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2021,51,49,"2020-12-14T10:12:00","10:12","2021-12-10T10:53:00","10:53",2732,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290895361","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2021,2021,12,49,"2021-03-22T22:45:00","22:45","2021-12-10T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290896961","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2021,2021,12,49,"2021-03-22T22:12:00","22:12","2021-12-10T04:40:00","04:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290898561","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2021,51,49,"2020-12-14T11:05:00","11:05","2021-12-10T12:28:00","12:28",3130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290897761","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2021,51,49,"2020-12-14T01:00:00","01:00","2021-12-06T03:30:00","03:30",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290899361","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2021,51,49,"2020-12-14T00:06:00","00:06","2021-12-06T03:30:00","03:30",52,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290835961","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290832761","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T13:15:00","13:15","2021-12-10T13:45:00","13:45",3314,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290831961","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T12:45:00","12:45","2021-12-10T13:30:00","13:30",3389,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290839161","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T00:10:00","00:10","2021-12-06T03:10:00","03:10",151,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290834361","Aulnoye-Longuyon",">","Sedan","Longuyon",2021,2021,7,49,"2021-02-15T10:15:00","10:15","2021-12-10T16:00:00","16:00",1109,"DAY",null,null,null,null,null,null,null,null,null,null,null,"70 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290837561","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290835161","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T12:45:00","12:45","2021-12-10T14:15:00","14:15",3435,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290836761","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T13:00:00","13:00","2021-12-10T14:15:00","14:15",3578,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290833561","Aulnoye-Longuyon",">","Sedan","Longuyon",2021,2021,7,49,"2021-02-15T09:15:00","09:15","2021-12-10T13:30:00","13:30",935,"DAY",null,null,null,null,null,null,null,null,null,null,null,"70 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290838361","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T00:10:00","00:10","2021-12-06T03:10:00","03:10",151,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290779761","Aulnoye-Longuyon",">","Liart","Tournes",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290781361","Aulnoye-Longuyon",">","Liart","Tournes",2020,2021,51,49,"2020-12-14T14:00:00","14:00","2021-12-10T14:40:00","14:40",3550,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290778161","Aulnoye-Longuyon",">","Liart","Tournes",2020,2021,51,49,"2020-12-14T12:05:00","12:05","2021-12-10T13:21:00","13:21",3231,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290778961","Aulnoye-Longuyon",">","Liart","Tournes",2020,2021,51,48,"2020-12-20T23:55:00","23:55","2021-12-05T02:55:00","02:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290777361","Aulnoye-Longuyon",">","Liart","Tournes",2021,2021,7,40,"2021-02-15T09:37:00","09:37","2021-10-08T14:20:00","14:20",635,"DAY",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290780561","Aulnoye-Longuyon",">","Liart","Tournes",2021,2021,7,40,"2021-02-15T09:35:00","09:35","2021-10-08T14:54:00","14:54",660,"DAY",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290926761","Aulnoye-Longuyon",">","Aulnoye","Hirson",2021,2021,10,40,"2021-03-08T09:20:00","09:20","2021-10-08T16:00:00","16:00",630,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290923561","Aulnoye-Longuyon",">","Aulnoye","Hirson",2021,2021,10,40,"2021-03-08T09:59:00","09:59","2021-10-08T15:25:00","15:25",606,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290922761","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2021,51,49,"2020-12-14T11:18:00","11:18","2021-12-10T12:30:00","12:30",3138,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290924361","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2021,51,49,"2020-12-14T00:55:00","00:55","2021-12-06T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290921961","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2021,51,49,"2020-12-14T13:15:00","13:15","2021-12-10T13:45:00","13:45",3451,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290925161","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2021,51,49,"2020-12-14T10:57:00","10:57","2021-12-10T12:18:00","12:18",3088,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290925961","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2021,51,48,"2020-12-20T23:30:00","23:30","2021-12-05T03:00:00","03:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290855961","Aulnoye-Longuyon",">","Tournes","Charleville",2021,2021,7,40,"2021-02-15T09:15:00","09:15","2021-10-08T14:20:00","14:20",850,"DAY",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290852761","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2021,51,49,"2020-12-14T13:35:00","13:35","2021-12-10T14:40:00","14:40",3550,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290856761","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2021,51,49,"2020-12-14T12:25:00","12:25","2021-12-10T13:21:00","13:21",3231,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290853561","Aulnoye-Longuyon",">","Tournes","Charleville",2021,2021,7,40,"2021-02-15T10:00:00","10:00","2021-10-08T14:54:00","14:54",884,"DAY",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290854361","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2021,51,48,"2020-12-20T23:55:00","23:55","2021-12-05T02:55:00","02:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290855161","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8345420561_8345380561","Paris-Amiens",">","StadeDeFrance","StDenis",2020,2021,51,49,"2020-12-15T01:00:00","01:00","2021-12-11T05:05:00","05:05",1168,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"230 jours dans le régime binaire"]
["SNCF Réseau","8345420561_8345379761","Paris-Amiens",">","StadeDeFrance","StDenis",2020,2021,51,49,"2020-12-15T00:30:00","00:30","2021-12-11T04:25:00","04:25",1015,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"230 jours dans le régime binaire"]
["SNCF Réseau","8345420561_8345381361","Paris-Amiens",">","StadeDeFrance","StDenis",2020,2021,51,49,"2020-12-15T01:00:00","01:00","2021-12-11T05:20:00","05:20",1279,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","8345420561_8345378961","Paris-Amiens",">","StadeDeFrance","StDenis",2020,2021,51,49,"2020-12-15T00:35:00","00:35","2021-12-11T04:45:00","04:45",1139,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","8345420561_8345382161","Paris-Amiens",">","StadeDeFrance","StDenis",2021,2021,44,44,"2021-11-02T23:55:00","23:55","2021-11-05T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8344690361_8344442061","Sarrebourg-Basel",">","Mulhouse","Chalampe",2020,2021,51,49,"2020-12-14T08:52:00","08:52","2021-12-10T09:52:00","09:52",2349,"DAY",null,null,null,null,null,null,null,null,null,null,null,"239 jours dans le régime binaire"]
["SNCF Réseau","8344690361_8344443661","Sarrebourg-Basel",">","Mulhouse","Chalampe",2021,2021,11,41,"2021-03-15T22:00:00","22:00","2021-10-15T04:00:00","04:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8344680761_8344430461","Sarrebourg-Basel",">","Colmar","NeufBrisach",2021,2021,23,24,"2021-06-11T11:40:00","11:40","2021-06-18T15:40:00","15:40",19,"DAY",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","8344680761_8344429461","Sarrebourg-Basel",">","Colmar","NeufBrisach",2021,2021,16,24,"2021-04-19T12:00:00","12:00","2021-06-17T20:00:00","20:00",208,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8344681061_8344424661","Longuyon-Metz-Sarrebourg",">","Hauconcourt","Woippy",2021,2021,17,46,"2021-04-26T10:00:00","10:00","2021-11-19T18:00:00","18:00",440,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8344683761_8344407661","Longuyon-Metz-Sarrebourg",">","Longwy","Saulnes",2021,2021,30,30,"2021-07-26T08:00:00","08:00","2021-07-30T16:00:00","16:00",0,"ALL DAY",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
["SNCF Réseau","8328470961_8328403961","Lyon-Valence",">","Givors","Peyraud (par RD)",2021,2021,8,49,"2021-02-22T09:15:00","09:15","2021-12-10T15:15:00","15:15",1256,"DAY",null,null,null,null,null,null,null,null,null,null,null,"83 jours dans le régime binaire"]
["SNCF Réseau","8328470961_8328403161","Lyon-Valence",">","Givors","Peyraud (par RD)",2021,2021,3,45,"2021-01-24T21:50:00","21:50","2021-11-14T01:20:00","01:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328470961_8328406561","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2021,51,35,"2020-12-14T11:15:00","11:15","2021-09-03T12:48:00","12:48",2049,"DAY",null,null,null,null,null,null,null,null,null,null,null,"161 jours dans le régime binaire"]
["SNCF Réseau","8328470961_8328405761","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2021,51,35,"2020-12-14T13:28:00","13:28","2021-09-03T13:50:00","13:50",2075,"DAY",null,null,null,null,null,null,null,null,null,null,null,"151 jours dans le régime binaire"]
["SNCF Réseau","8328470961_8328404961","Lyon-Valence",">","Givors","Peyraud (par RD)",2021,2021,3,45,"2021-01-18T04:05:00","04:05","2021-11-08T06:35:00","06:35",134,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8328471061_8328268561","Lyon-Valence",">","RaccPeyraud","St Rambert",2021,2021,9,10,"2021-03-01T09:58:00","09:58","2021-03-12T14:58:00","14:58",139,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328355361","Valence - Avignon",">","Sorgues","Avignon",2020,2021,51,49,"2020-12-14T10:43:00","10:43","2021-12-10T11:37:00","11:37",2800,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328352961","Valence - Avignon",">","Sorgues","Avignon",2021,2021,12,13,"2021-03-22T11:40:00","11:40","2021-04-02T16:23:00","16:23",152,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328356161","Valence - Avignon",">","Sorgues","Avignon",2021,2021,12,13,"2021-03-22T08:16:00","08:16","2021-04-02T12:50:00","12:50",120,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328352161","Valence - Avignon",">","Sorgues","Avignon",2021,2021,2,41,"2021-01-11T01:05:00","01:05","2021-10-11T04:12:00","04:12",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328354561","Valence - Avignon",">","Sorgues","Avignon",2020,2021,51,49,"2020-12-14T13:48:00","13:48","2021-12-10T14:55:00","14:55",3596,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328353761","Valence - Avignon",">","Sorgues","Avignon",2021,2021,2,41,"2021-01-11T01:17:00","01:17","2021-10-11T04:10:00","04:10",7,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328281361","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:20:00","02:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328283761","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2021,51,49,"2020-12-14T02:55:00","02:55","2021-12-06T05:35:00","05:35",170,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328280561","Lyon-Valence",">","Vienne","St Rambert (par RG)",2021,2021,12,14,"2021-03-22T09:43:00","09:43","2021-04-09T14:59:00","14:59",200,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328282161","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2021,51,49,"2020-12-14T11:40:00","11:40","2021-12-10T12:58:00","12:58",2828,"DAY",null,null,null,null,null,null,null,null,null,null,null,"219 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328282961","Lyon-Valence",">","Vienne","St Rambert (par RG)",2021,2021,12,14,"2021-03-22T10:21:00","10:21","2021-04-09T14:55:00","14:55",198,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328284561","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2021,52,49,"2020-12-21T13:18:00","13:18","2021-12-10T14:00:00","14:00",2982,"DAY",null,null,null,null,null,null,null,null,null,null,null,"214 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328386961","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2021,52,49,"2020-12-21T13:26:00","13:26","2021-12-10T14:19:00","14:19",3050,"DAY",null,null,null,null,null,null,null,null,null,null,null,"214 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328388561","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2021,2021,12,14,"2021-03-22T10:26:00","10:26","2021-04-09T15:16:00","15:16",203,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328386161","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2021,2021,12,14,"2021-03-22T09:34:00","09:34","2021-04-09T14:36:00","14:36",194,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328389361","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2021,51,48,"2020-12-20T23:06:00","23:06","2021-12-05T02:12:00","02:12",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328390161","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2021,52,49,"2020-12-21T11:32:00","11:32","2021-12-10T12:38:00","12:38",2692,"DAY",null,null,null,null,null,null,null,null,null,null,null,"214 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328387761","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2021,51,49,"2020-12-14T02:57:00","02:57","2021-12-06T05:47:00","05:47",176,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328471561_8328382761","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2021,51,49,"2020-12-14T12:50:00","12:50","2021-12-10T13:00:00","13:00",2405,"DAY",null,null,null,null,null,null,null,null,null,null,null,"186 jours dans le régime binaire"]
["SNCF Réseau","8328471561_8328381161","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2021,2021,3,46,"2021-01-24T22:20:00","22:20","2021-11-21T02:00:00","02:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8328471561_8328384561","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2021,51,49,"2020-12-14T11:48:00","11:48","2021-12-10T13:34:00","13:34",2511,"DAY",null,null,null,null,null,null,null,null,null,null,null,"186 jours dans le régime binaire"]
["SNCF Réseau","8328471561_8328381961","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2021,2021,4,47,"2021-01-25T03:35:00","03:35","2021-11-22T05:55:00","05:55",108,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8328471561_8328383561","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2021,2021,7,38,"2021-02-15T08:36:00","08:36","2021-09-24T14:36:00","14:36",706,"DAY",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328287561","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2021,51,49,"2020-12-14T13:13:00","13:13","2021-12-10T14:48:00","14:48",3568,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328286761","Valence - Avignon",">","Pierrelatte","Sorgues",2021,2021,2,41,"2021-01-11T01:35:00","01:35","2021-10-11T04:17:00","04:17",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328289961","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2021,51,49,"2020-12-14T11:17:00","11:17","2021-12-10T11:43:00","11:43",2824,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328290761","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2021,51,49,"2020-12-14T00:40:00","00:40","2021-12-06T04:05:00","04:05",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328288361","Valence - Avignon",">","Pierrelatte","Sorgues",2021,2021,12,13,"2021-03-22T11:00:00","11:00","2021-04-02T16:35:00","16:35",154,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328289161","Valence - Avignon",">","Pierrelatte","Sorgues",2021,2021,12,13,"2021-03-22T08:32:00","08:32","2021-04-02T12:50:00","12:50",119,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328344161","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2021,4,47,"2021-01-25T02:49:00","02:49","2021-11-22T04:59:00","04:59",91,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328347561","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2021,51,49,"2020-12-14T11:55:00","11:55","2021-12-10T12:00:00","12:00",2496,"DAY",null,null,null,null,null,null,null,null,null,null,null,"209 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328344961","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2021,51,49,"2020-12-14T12:40:00","12:40","2021-12-10T14:30:00","14:30",3017,"DAY",null,null,null,null,null,null,null,null,null,null,null,"209 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328341761","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2021,4,47,"2021-01-25T00:05:00","00:05","2021-11-22T03:32:00","03:32",67,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328342561","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2021,3,46,"2021-01-24T23:05:00","23:05","2021-11-21T02:55:00","02:55",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328346561","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2021,2,45,"2021-01-11T09:47:00","09:47","2021-11-12T15:47:00","15:47",1821,"DAY",null,null,null,null,null,null,null,null,null,null,null,"116 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328379561","Valence - Avignon",">","Portes","Livron (par RG)",2020,2021,51,49,"2020-12-14T12:05:00","12:05","2021-12-10T12:55:00","12:55",3010,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328377961","Valence - Avignon",">","Portes","Livron (par RG)",2021,2021,12,14,"2021-03-22T10:32:00","10:32","2021-04-09T15:37:00","15:37",208,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328377161","Valence - Avignon",">","Portes","Livron (par RG)",2021,2021,12,14,"2021-03-22T08:56:00","08:56","2021-04-09T13:37:00","13:37",181,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328378761","Valence - Avignon",">","Portes","Livron (par RG)",2020,2021,51,49,"2020-12-14T01:55:00","01:55","2021-12-06T04:45:00","04:45",135,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328376361","Valence - Avignon",">","Portes","Livron (par RG)",2020,2021,51,49,"2020-12-14T12:34:00","12:34","2021-12-10T13:40:00","13:40",3185,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328375561","Valence - Avignon",">","Portes","Livron (par RG)",2020,2021,51,48,"2020-12-20T23:54:00","23:54","2021-12-05T03:07:00","03:07",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328323161","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2021,51,48,"2020-12-20T23:12:00","23:12","2021-12-05T02:51:00","02:51",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"28 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328319161","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2021,51,49,"2020-12-14T02:10:00","02:10","2021-12-06T05:10:00","05:10",142,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"28 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328318361","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2021,51,49,"2020-12-14T12:57:00","12:57","2021-12-10T13:32:00","13:32",3153,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328321561","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2021,12,14,"2021-03-22T09:59:00","09:59","2021-04-09T15:24:00","15:24",205,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328319961","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2021,12,14,"2021-03-22T10:01:00","10:01","2021-04-09T14:29:00","14:29",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328320761","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2021,51,49,"2020-12-14T02:34:00","02:34","2021-12-06T05:10:00","05:10",142,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"28 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328322361","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2021,51,49,"2020-12-14T12:10:00","12:10","2021-12-10T13:10:00","13:10",3068,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328317561","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2021,51,49,"2020-12-14T11:59:00","11:59","2021-12-10T13:28:00","13:28",3139,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328327361","Valence - Avignon",">","Livron","Pierrelatte",2021,2021,12,13,"2021-03-22T08:49:00","08:49","2021-04-02T13:17:00","13:17",124,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328325761","Valence - Avignon",">","Livron","Pierrelatte",2020,2021,51,49,"2020-12-14T11:52:00","11:52","2021-12-10T12:20:00","12:20",2763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"225 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328328161","Valence - Avignon",">","Livron","Pierrelatte",2020,2021,51,49,"2020-12-14T02:05:00","02:05","2021-12-06T04:35:00","04:35",135,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328328961","Valence - Avignon",">","Livron","Pierrelatte",2021,2021,12,13,"2021-03-22T10:37:00","10:37","2021-04-02T16:02:00","16:02",149,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328324961","Valence - Avignon",">","Livron","Pierrelatte",2020,2021,51,49,"2020-12-14T12:41:00","12:41","2021-12-10T14:11:00","14:11",3178,"DAY",null,null,null,null,null,null,null,null,null,null,null,"225 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328326561","Valence - Avignon",">","Livron","Pierrelatte",2020,2021,51,49,"2020-12-14T00:10:00","00:10","2021-12-06T03:40:00","03:40",109,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","8328473061_8328259961","Valence - Avignon",">","Raccordement de Livron","LaVoulte",2021,2021,6,38,"2021-02-08T10:32:00","10:32","2021-09-24T15:32:00","15:32",377,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8328473061_8328261761","Valence - Avignon",">","Raccordement de Livron","LaVoulte",2021,2021,9,42,"2021-03-01T08:08:00","08:08","2021-10-22T09:38:00","09:38",377,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","8345623561_8345518761","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2021,2021,4,47,"2021-01-25T21:45:00","21:45","2021-11-26T05:25:00","05:25",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"151 jours dans le régime binaire"]
["SNCF Réseau","8345623561_8345519761","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2020,2021,51,49,"2020-12-14T09:54:00","09:54","2021-12-10T10:54:00","10:54",2736,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345623561_8345517961","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2020,2021,51,49,"2020-12-14T14:00:00","14:00","2021-12-10T15:00:00","15:00",3766,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345624861_10318794261","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2020,2021,51,49,"2020-12-14T11:20:00","11:20","2021-12-10T13:20:00","13:20",3348,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345624861_8345493761","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2021,2021,6,49,"2021-02-08T10:00:00","10:00","2021-12-10T15:00:00","15:00",650,"DAY",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","8345624861_8345494761","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2020,2021,51,49,"2020-12-14T10:00:00","10:00","2021-12-10T12:30:00","12:30",3140,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345545361","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2021,2021,14,44,"2021-04-06T10:05:00","10:05","2021-11-05T17:00:00","17:00",890,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345546161","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2021,51,49,"2020-12-14T13:50:00","13:50","2021-12-10T16:50:00","16:50",4228,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345546961","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2021,51,49,"2020-12-14T13:50:00","13:50","2021-12-08T15:35:00","15:35",1544,"DAY",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345549561","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2021,51,49,"2020-12-15T13:50:00","13:50","2021-12-10T16:50:00","16:50",2544,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345548561","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2021,2021,5,47,"2021-02-01T21:03:00","21:03","2021-11-26T05:20:00","05:20",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"126 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345547761","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2021,2021,14,44,"2021-04-06T12:25:00","12:25","2021-11-05T17:00:00","17:00",888,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","8345625061_8345490961","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2021,2021,14,44,"2021-04-06T10:00:00","10:00","2021-11-05T17:00:00","17:00",891,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","8345625061_8345489961","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2020,2021,51,49,"2020-12-14T13:50:00","13:50","2021-12-10T16:50:00","16:50",4228,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345625061_8345491961","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2021,2021,5,47,"2021-02-01T21:03:00","21:03","2021-11-26T05:20:00","05:20",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"142 jours dans le régime binaire"]
["SNCF Réseau","8345624161_8345505161","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2020,2021,51,49,"2020-12-19T09:00:00","09:00","2021-12-11T10:35:00","10:35",1091,"DAY",null,null,null,null,null,null,null,null,null,null,null,"104 jours dans le régime binaire"]
["SNCF Réseau","8345624161_8345504361","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2020,2021,51,49,"2020-12-14T09:35:00","09:35","2021-12-10T10:35:00","10:35",2742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","8345624161_8345505961","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2021,2021,5,47,"2021-02-01T22:00:00","22:00","2021-11-26T04:00:00","04:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"147 jours dans le régime binaire"]
["SNCF Réseau","8345626461_8345598961","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2021,2021,5,47,"2021-02-01T20:25:00","20:25","2021-11-26T04:55:00","04:55",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"127 jours dans le régime binaire"]
["SNCF Réseau","8345626461_8345598161","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2021,2021,14,44,"2021-04-06T08:00:00","08:00","2021-11-05T16:00:00","16:00",280,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8345626461_8345597361","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2020,2021,51,49,"2020-12-14T13:45:00","13:45","2021-12-10T14:55:00","14:55",3745,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344319961","Paris-Amiens",">","Orry","Creil",2020,2021,51,49,"2020-12-14T01:51:00","01:51","2021-12-06T04:51:00","04:51",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344317961","Paris-Amiens",">","Orry","Creil",2021,2021,5,49,"2021-02-01T23:49:00","23:49","2021-12-10T04:54:00","04:54",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"114 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344319161","Paris-Amiens",">","Orry","Creil",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",115,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344322361","Paris-Amiens",">","Orry","Creil",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344321561","Paris-Amiens",">","Orry","Creil",2021,2021,5,49,"2021-02-02T01:10:00","01:10","2021-12-11T05:26:00","05:26",618,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"114 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344320761","Paris-Amiens",">","Orry","Creil",2021,2021,5,49,"2021-02-01T23:53:00","23:53","2021-12-10T04:42:00","04:42",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"114 jours dans le régime binaire"]
["SNCF Réseau","8344371661_8344280361","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2020,2021,51,49,"2020-12-14T01:45:00","01:45","2021-12-06T04:45:00","04:45",245,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344371661_8344279561","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344371661_8344278561","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2020,2021,51,49,"2020-12-15","00:00","2021-12-11T05:00:00","05:00",1300,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344325161","Paris-Amiens",">","Stade de France","SaintDenis",2021,2021,1,46,"2021-01-04","00:00","2021-11-19T05:05:00","05:05",-5,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"150 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344326161","Paris-Amiens",">","Stade de France","SaintDenis",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344328161","Paris-Amiens",">","Stade de France","SaintDenis",2020,2021,51,49,"2020-12-15T00:35:00","00:35","2021-12-11T05:05:00","05:05",1310,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"258 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344327161","Paris-Amiens",">","Stade de France","SaintDenis",2021,2021,1,46,"2021-01-04T23:25:00","23:25","2021-11-19T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"150 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344330161","Paris-Amiens",">","Stade de France","SaintDenis",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344329161","Paris-Amiens",">","Stade de France","SaintDenis",2020,2021,51,49,"2020-12-15T01:00:00","01:00","2021-12-11T04:50:00","04:50",1246,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"258 jours dans le régime binaire"]
["SNCF Réseau","8344372261_8344284361","Paris-Amiens",">","Bif de Pierrefitte","Orry",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344372261_8344285161","Paris-Amiens",">","Bif de Pierrefitte","Orry",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",115,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8344372261_8344283161","Paris-Amiens",">","Bif de Pierrefitte","Orry",2021,2021,5,49,"2021-02-02","00:00","2021-12-11T05:00:00","05:00",570,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"114 jours dans le régime binaire"]
["SNCF Réseau","8344372261_8344282361","Paris-Amiens",">","Bif de Pierrefitte","Orry",2020,2021,51,49,"2020-12-14T01:45:00","01:45","2021-12-06T04:45:00","04:45",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344291161","Paris-Amiens",">","SaintDenis","VilliersLeBel",2021,2021,1,46,"2021-01-04T23:35:00","23:35","2021-11-19T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344287961","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2021,51,49,"2020-12-15T00:30:00","00:30","2021-12-11T04:55:00","04:55",1248,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344289561","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344290361","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2021,51,49,"2020-12-15T01:05:00","01:05","2021-12-11T04:50:00","04:50",1226,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344288761","Paris-Amiens",">","SaintDenis","VilliersLeBel",2021,2021,1,46,"2021-01-04T23:55:00","23:55","2021-11-19T04:50:00","04:50",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344291961","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344251961","Paris-Amiens",">","Villiers le Bel","Goussainville",2021,2021,1,46,"2021-01-04T23:46:00","23:46","2021-11-19T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344248761","Paris-Amiens",">","Villiers le Bel","Goussainville",2021,2021,1,46,"2021-01-04T23:45:00","23:45","2021-11-19T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344247961","Paris-Amiens",">","Villiers le Bel","Goussainville",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344249561","Paris-Amiens",">","Villiers le Bel","Goussainville",2020,2021,51,49,"2020-12-15T00:20:00","00:20","2021-12-11T04:50:00","04:50",1203,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344251161","Paris-Amiens",">","Villiers le Bel","Goussainville",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344250361","Paris-Amiens",">","Villiers le Bel","Goussainville",2020,2021,51,49,"2020-12-15T01:14:00","01:14","2021-12-11T04:50:00","04:50",1202,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344256561","Paris-Amiens",">","Goussainville","Orry",2020,2021,51,49,"2020-12-14T01:35:00","01:35","2021-12-06T04:35:00","04:35",236,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344254161","Paris-Amiens",">","Goussainville","Orry",2020,2021,51,49,"2020-12-15T01:20:00","01:20","2021-12-11T04:50:00","04:50",1202,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344257361","Paris-Amiens",">","Goussainville","Orry",2021,2021,1,46,"2021-01-04T23:40:00","23:40","2021-11-19T04:35:00","04:35",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344253361","Paris-Amiens",">","Goussainville","Orry",2021,2021,1,46,"2021-01-04T23:50:00","23:50","2021-11-19T04:50:00","04:50",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344255761","Paris-Amiens",">","Goussainville","Orry",2020,2021,51,49,"2020-12-14T01:40:00","01:40","2021-12-06T04:40:00","04:40",241,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344254961","Paris-Amiens",">","Goussainville","Orry",2020,2021,51,49,"2020-12-15T00:15:00","00:15","2021-12-11T04:45:00","04:45",1182,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342261761","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2021,2021,6,49,"2021-02-08T23:20:00","23:20","2021-12-10T05:30:00","05:30",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342258561","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2021,51,49,"2020-12-14T09:36:00","09:36","2021-12-10T10:37:00","10:37",2665,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342260161","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2021,51,49,"2020-12-14T14:36:00","14:36","2021-12-10T15:26:00","15:26",3874,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342259361","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2021,51,48,"2020-12-20T23:04:00","23:04","2021-12-05T01:55:00","01:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342262561","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:20:00","03:20",116,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342260961","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2021,2021,6,49,"2021-02-08T23:05:00","23:05","2021-12-10T04:55:00","04:55",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342650861_8342402361","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2021,2021,5,49,"2021-02-01T23:27:00","23:27","2021-12-10T05:27:00","05:27",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"78 jours dans le régime binaire"]
["SNCF Réseau","8342650861_8342400761","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2020,2021,51,49,"2020-12-14T09:03:00","09:03","2021-12-10T09:55:00","09:55",2470,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8342650861_8342399961","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2021,2021,5,49,"2021-02-01T23:43:00","23:43","2021-12-10T05:29:00","05:29",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"78 jours dans le régime binaire"]
["SNCF Réseau","8342650861_8342401561","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2020,2021,51,49,"2020-12-14T13:57:00","13:57","2021-12-10T15:07:00","15:07",3765,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8342651361_8342209061","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2020,2021,51,49,"2020-12-14T09:25:00","09:25","2021-12-10T10:22:00","10:22",2602,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651361_8342207461","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2020,2021,51,48,"2020-12-20T23:56:00","23:56","2021-12-05T02:56:00","02:56",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342651361_8342205661","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2021,2021,1,37,"2021-01-04T23:26:00","23:26","2021-09-17T05:26:00","05:26",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8342651361_8342208261","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2020,2021,51,48,"2020-12-20T23:56:00","23:56","2021-12-05T02:56:00","02:56",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342651361_8342206661","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2020,2021,51,49,"2020-12-14T13:35:00","13:35","2021-12-10T14:38:00","14:38",3674,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342281761","Dijon-Toul",">","Dijon","Is sur Tille",2021,2021,4,45,"2021-01-25T11:26:00","11:26","2021-11-12T14:58:00","14:58",1290,"DAY",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342282761","Dijon-Toul",">","Dijon","Is sur Tille",2021,2021,4,45,"2021-01-25T12:28:00","12:28","2021-11-12T16:48:00","16:48",1449,"DAY",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342280761","Dijon-Toul",">","Dijon","Is sur Tille",2020,2021,51,48,"2020-12-14T11:35:00","11:35","2021-12-03T12:14:00","12:14",2006,"DAY",null,null,null,null,null,null,null,null,null,null,null,"165 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342277761","Dijon-Toul",">","Dijon","Is sur Tille",2021,2021,1,48,"2021-01-04T01:10:00","01:10","2021-11-29T03:55:00","03:55",179,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342278761","Dijon-Toul",">","Dijon","Is sur Tille",2020,2021,51,48,"2020-12-14T12:35:00","12:35","2021-12-03T14:01:00","14:01",2300,"DAY",null,null,null,null,null,null,null,null,null,null,null,"165 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342279761","Dijon-Toul",">","Dijon","Is sur Tille",2021,2021,1,48,"2021-01-04T00:05:00","00:05","2021-11-29T03:29:00","03:29",160,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342240361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,4,41,"2021-01-26T11:30:00","11:30","2021-10-15T15:30:00","15:30",763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342238761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342234761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342241161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,51,49,"2020-12-15T09:21:00","09:21","2021-12-10T10:19:00","10:19",2053,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342229961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,6,49,"2021-02-08T13:38:00","13:38","2021-12-10T14:41:00","14:41",838,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342237961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,51,46,"2020-12-14T11:23:00","11:23","2021-11-19T12:27:00","12:27",2366,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342232361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342233961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,51,43,"2020-12-14","00:00","2021-10-25T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342233161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342235561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,51,43,"2020-12-14","00:00","2021-10-25T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342241961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,4,49,"2021-01-25","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342239561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,51,46,"2020-12-14T14:30:00","14:30","2021-11-19T15:25:00","15:25",2930,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342231561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342230761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342236361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,4,49,"2021-01-25","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342651461_8342193661","Lerouville-Nancy",">","Lerouville","Toul",2021,2021,3,48,"2021-01-24T22:40:00","22:40","2021-12-05T02:01:00","02:01",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8342651461_8342194461","Lerouville-Nancy",">","Lerouville","Toul",2021,2021,4,49,"2021-01-25T00:40:00","00:40","2021-12-06T03:20:00","03:20",32,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8342651461_8342191861","Lerouville-Nancy",">","Lerouville","Toul",2021,2021,9,49,"2021-03-01T23:00:00","23:00","2021-12-10T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"57 jours dans le régime binaire"]
["SNCF Réseau","8342651461_8342191061","Lerouville-Nancy",">","Lerouville","Toul",2020,2021,51,49,"2020-12-14T10:40:00","10:40","2021-12-10T11:56:00","11:56",2996,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651461_8342192861","Lerouville-Nancy",">","Lerouville","Toul",2020,2021,51,49,"2020-12-14T15:15:00","15:15","2021-12-10T16:00:00","16:00",4016,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649361_8342189661","Longuyon-Metz-Sarrebourg","<","Metz sablon via MetzVille",null,2021,2021,14,47,"2021-04-05T23:30:00","23:30","2021-11-26T05:30:00","05:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342467161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342464761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342460761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342459161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2021,51,49,"2020-12-15T09:19:00","09:19","2021-12-10T10:17:00","10:17",2047,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342465561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342463161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,4,41,"2021-01-26T11:30:00","11:30","2021-10-15T15:30:00","15:30",763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342461561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,6,49,"2021-02-08T13:41:00","13:41","2021-12-10T14:44:00","14:44",840,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342463961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342466361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2021,51,46,"2020-12-14T11:27:00","11:27","2021-11-19T12:28:00","12:28",2369,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342462361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,4,41,"2021-01-26T11:30:00","11:30","2021-10-15T15:30:00","15:30",763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342459961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342467961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2021,51,46,"2020-12-14T14:25:00","14:25","2021-11-19T15:21:00","15:21",2917,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342649461_8342381761","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2020,2021,51,49,"2020-12-14T13:20:00","13:20","2021-12-10T13:40:00","13:40",3430,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649461_8342380161","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2020,2021,51,49,"2020-12-14T11:30:00","11:30","2021-12-10T13:15:00","13:15",3327,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649461_8342382561","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2020,2021,51,42,"2020-12-20T23:00:00","23:00","2021-10-24T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8342649461_8342380961","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2020,2021,51,42,"2020-12-20T23:00:00","23:00","2021-10-24T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8342649461_8342383361","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2021,2021,12,38,"2021-03-22T10:30:00","10:30","2021-09-24T16:30:00","16:30",550,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","8342651761_8342374561","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2021,2021,6,49,"2021-02-08T23:10:00","23:10","2021-12-10T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342651761_8342376961","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2021,2021,6,40,"2021-02-08T23:41:00","23:41","2021-10-08T05:46:00","05:46",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
["SNCF Réseau","8342651761_8342375361","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2020,2021,51,49,"2020-12-14T14:25:00","14:25","2021-12-10T15:20:00","15:20",3849,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651761_8342376161","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2020,2021,51,49,"2020-12-14T09:44:00","09:44","2021-12-10T10:50:00","10:50",2720,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342222061","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,51,49,"2020-12-14T10:55:00","10:55","2021-12-10T11:37:00","11:37",2916,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342218061","Dijon-Toul",">","Culmont","NeufChateau",2021,2021,9,29,"2021-03-01T10:05:00","10:05","2021-07-23T13:48:00","13:48",334,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342218861","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,51,49,"2020-12-14T13:48:00","13:48","2021-12-10T15:15:00","15:15",3829,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342221261","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,51,49,"2020-12-14T10:37:00","10:37","2021-12-10T11:08:00","11:08",2794,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342220461","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,52,49,"2020-12-21T01:25:00","01:25","2021-12-06T04:51:00","04:51",226,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342216461","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,52,49,"2020-12-21T01:03:00","01:03","2021-12-06T04:25:00","04:25",206,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342214861","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,51,49,"2020-12-14T13:25:00","13:25","2021-12-10T14:48:00","14:48",3716,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342215661","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,52,49,"2020-12-21T00:27:00","00:27","2021-12-06T03:05:00","03:05",144,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342217261","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,51,48,"2020-12-20T00:05:00","00:05","2021-12-05T02:37:00","02:37",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342219661","Dijon-Toul",">","Culmont","NeufChateau",2021,2021,9,29,"2021-03-01T13:26:00","13:26","2021-07-23T19:14:00","19:14",467,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8342651861_8342183461","Lerouville-Nancy",">","Toul","Frouard",2020,2021,51,49,"2020-12-14T08:58:00","08:58","2021-12-10T10:16:00","10:16",2578,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651861_8342184261","Lerouville-Nancy",">","Toul","Frouard",2020,2021,51,45,"2020-12-20T22:54:00","22:54","2021-11-14T01:40:00","01:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8342651861_8342181661","Lerouville-Nancy",">","Toul","Frouard",2020,2021,51,45,"2020-12-20T22:55:00","22:55","2021-11-14T02:06:00","02:06",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8342651861_8342185061","Lerouville-Nancy",">","Toul","Frouard",2020,2021,51,49,"2020-12-14T14:59:00","14:59","2021-12-10T15:42:00","15:42",3941,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651861_8342182461","Lerouville-Nancy",">","Toul","Frouard",2021,2021,6,42,"2021-02-08T23:00:00","23:00","2021-10-22T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342395961","Dijon-Toul",">","NeufChateau","Toul",2020,2021,51,49,"2020-12-14T14:15:00","14:15","2021-12-10T15:44:00","15:44",3808,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342393561","Dijon-Toul",">","NeufChateau","Toul",2020,2021,52,49,"2020-12-21T01:46:00","01:46","2021-12-06T05:12:00","05:12",242,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342396761","Dijon-Toul",">","NeufChateau","Toul",2020,2021,51,49,"2020-12-14T10:08:00","10:08","2021-12-10T10:34:00","10:34",2557,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342392761","Dijon-Toul",">","NeufChateau","Toul",2020,2021,51,48,"2020-12-20T23:52:00","23:52","2021-12-05T01:34:00","01:34",23,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342395161","Dijon-Toul",">","NeufChateau","Toul",2021,2021,9,29,"2021-03-01T14:15:00","14:15","2021-07-23T19:41:00","19:41",654,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342394361","Dijon-Toul",">","NeufChateau","Toul",2021,2021,9,29,"2021-03-01T09:17:00","09:17","2021-07-23T13:15:00","13:15",441,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","8342649561_8342251561","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2021,51,46,"2020-12-14T00:24:00","00:24","2021-11-15T03:30:00","03:30",38,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342649561_8342253961","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2021,2021,6,42,"2021-02-08T23:45:00","23:45","2021-10-22T05:45:00","05:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8342649561_8342252361","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2021,51,49,"2020-12-14T14:16:00","14:16","2021-12-10T15:11:00","15:11",3811,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649561_8342253161","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2021,51,46,"2020-12-14T00:03:00","00:03","2021-11-15T03:00:00","03:00",32,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342649561_8342255361","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2021,51,49,"2020-12-14T10:45:00","10:45","2021-12-10T11:47:00","11:47",2958,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649761_8342111261","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2020,2021,51,49,"2020-12-14T14:07:00","14:07","2021-12-10T15:17:00","15:17",3822,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8342649761_8342109461","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2021,2021,10,45,"2021-03-08T23:00:00","23:00","2021-11-10T05:40:00","05:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8342649761_8342110461","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2021,2021,30,45,"2021-07-26T00:15:00","00:15","2021-11-08T03:00:00","03:00",11,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8342649761_8342112861","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2020,2021,51,49,"2020-12-14T10:51:00","10:51","2021-12-10T11:41:00","11:41",2921,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8342649761_8342112061","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2021,2021,29,44,"2021-07-25T22:45:00","22:45","2021-11-07T02:01:00","02:01",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342306561","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,4,45,"2021-01-25T09:30:00","09:30","2021-11-08T15:30:00","15:30",223,"DAY",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342308161","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2021,51,43,"2020-12-14","00:00","2021-10-25T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342302561","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2021,51,46,"2020-12-14T11:35:00","11:35","2021-11-19T12:38:00","12:38",2388,"DAY",null,null,null,null,null,null,null,null,null,null,null,"190 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342309761","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,6,49,"2021-02-08T13:50:00","13:50","2021-12-10T14:52:00","14:52",863,"DAY",null,null,null,null,null,null,null,null,null,null,null,"59 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342305761","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,4,45,"2021-01-25T09:30:00","09:30","2021-11-08T15:30:00","15:30",223,"DAY",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342308961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342304961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2021,51,43,"2020-12-14","00:00","2021-10-25T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342303361","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342304161","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,4,49,"2021-01-25","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342307361","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2021,51,49,"2020-12-15T09:10:00","09:10","2021-12-10T10:08:00","10:08",2017,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","8342647661_8342140861","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2020,2021,51,49,"2020-12-14T14:05:00","14:05","2021-12-10T15:32:00","15:32",3900,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647661_8342140061","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2021,2021,24,49,"2021-06-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",55,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8342647661_8342138261","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2021,2021,24,49,"2021-06-14","00:00","2021-12-06T03:00:00","03:00",48,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8342647661_8342141661","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2020,2021,51,49,"2020-12-14T12:17:00","12:17","2021-12-10T12:49:00","12:49",3217,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647661_8342139061","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2021,2021,7,49,"2021-02-15T10:10:00","10:10","2021-12-10T16:10:00","16:10",1574,"DAY",null,null,null,null,null,null,null,null,null,null,null,"98 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342150661","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,11,46,"2021-03-15T09:30:00","09:30","2021-11-15T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342149861","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,11,46,"2021-03-16T11:30:00","11:30","2021-11-19T15:30:00","15:30",407,"DAY",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342145861","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2021,53,49,"2020-12-28T14:15:00","14:15","2021-12-10T15:05:00","15:05",2942,"DAY",null,null,null,null,null,null,null,null,null,null,null,"196 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342153061","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,11,46,"2021-03-15T09:30:00","09:30","2021-11-15T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342145061","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,11,46,"2021-03-16T11:30:00","11:30","2021-11-19T15:30:00","15:30",407,"DAY",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342148261","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2021,53,49,"2020-12-28T11:37:00","11:37","2021-12-10T12:44:00","12:44",2547,"DAY",null,null,null,null,null,null,null,null,null,null,null,"201 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342147461","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2021,51,49,"2020-12-14T09:09:00","09:09","2021-12-10T10:07:00","10:07",2044,"DAY",null,null,null,null,null,null,null,null,null,null,null,"203 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342149061","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,2,45,"2021-01-11T09:30:00","09:30","2021-11-08T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342146661","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,2,45,"2021-01-11T09:30:00","09:30","2021-11-08T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342151461","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,4,49,"2021-01-25","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342153861","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2021,51,46,"2020-12-14T13:51:00","13:51","2021-11-19T14:53:00","14:53",685,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342152261","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,2,45,"2021-01-12T11:30:00","11:30","2021-11-10T15:30:00","15:30",391,"DAY",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342144261","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,2,45,"2021-01-12T11:30:00","11:30","2021-11-10T15:30:00","15:30",391,"DAY",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342335561","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342334761","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342338961","Lerouville-Metz",">","Noveant","Metz",2021,2021,1,47,"2021-01-04","00:00","2021-11-22T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342337161","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14T14:11:00","14:11","2021-12-10T15:05:00","15:05",3786,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342337961","Lerouville-Metz",">","Noveant","Metz",2021,2021,5,44,"2021-02-01T23:00:00","23:00","2021-11-05T05:45:00","05:45",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342339761","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14T10:48:00","10:48","2021-12-10T11:55:00","11:55",2992,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342341561","Lerouville-Metz",">","Noveant","Metz",2021,2021,1,47,"2021-01-04","00:00","2021-11-22T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342336361","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14T09:20:00","09:20","2021-12-10T10:15:00","10:15",2573,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342340561","Lerouville-Metz",">","Noveant","Metz",2021,2021,4,38,"2021-01-25T23:00:00","23:00","2021-09-24T05:45:00","05:45",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342342361","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14T14:09:00","14:09","2021-12-10T15:17:00","15:17",3837,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342293161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342294761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342287561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2021,51,46,"2020-12-14T11:30:00","11:30","2021-11-19T12:34:00","12:34",2388,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342289961","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,6,49,"2021-02-08T13:45:00","13:45","2021-12-10T14:49:00","14:49",845,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342291561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,4,41,"2021-01-26T11:30:00","11:30","2021-10-15T15:30:00","15:30",763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342296361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342295561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342288361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2021,51,46,"2020-12-14T14:20:00","14:20","2021-11-19T15:15:00","15:15",2898,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342293961","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2021,51,49,"2020-12-15T09:15:00","09:15","2021-12-10T10:11:00","10:11",2027,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342292361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,4,41,"2021-01-26T11:30:00","11:30","2021-10-15T15:30:00","15:30",763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342289161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342290761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342316961","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2021,2021,24,49,"2021-06-14T02:08:00","02:08","2021-12-06T04:31:00","04:31",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342319361","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2021,51,49,"2020-12-14T11:52:00","11:52","2021-12-10T12:15:00","12:15",3075,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342317761","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2021,2021,7,49,"2021-02-15T09:40:00","09:40","2021-12-10T16:10:00","16:10",1170,"DAY",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342316161","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2021,2021,7,49,"2021-02-15T10:00:00","10:00","2021-12-10T15:30:00","15:30",1121,"DAY",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342318561","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2021,51,49,"2020-12-14T13:35:00","13:35","2021-12-10T15:05:00","15:05",3787,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342315361","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2021,2021,23,48,"2021-06-13T23:00:00","23:00","2021-12-05T02:30:00","02:30",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342269361","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2021,51,46,"2020-12-14T14:21:00","14:21","2021-11-19T15:20:00","15:20",2914,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342266961","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2021,51,46,"2020-12-14T11:28:00","11:28","2021-11-19T12:29:00","12:29",2372,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342267761","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342270161","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2021,51,49,"2020-12-15T09:17:00","09:17","2021-12-10T10:14:00","10:14",2037,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342268561","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342270961","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342648361_8342249161","Lerouville-Nancy",">","Frouard","Jarville",2021,2021,6,49,"2021-02-08T23:05:00","23:05","2021-12-10T05:16:00","05:16",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
["SNCF Réseau","8342648361_8342249961","Lerouville-Nancy",">","Frouard","Jarville",2021,2021,6,49,"2021-02-08T23:11:00","23:11","2021-12-10T05:07:00","05:07",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
["SNCF Réseau","8342650061_8342359161","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2021,2021,18,18,"2021-05-03T23:14:00","23:14","2021-05-07T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
["SNCF Réseau","8342650061_8342360161","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2021,2021,1,49,"2021-01-04T09:46:00","09:46","2021-12-10T10:44:00","10:44",2555,"DAY",null,null,null,null,null,null,null,null,null,null,null,"239 jours dans le régime binaire"]
["SNCF Réseau","8342650061_8342358161","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2021,2021,6,49,"2021-02-08T23:14:00","23:14","2021-12-10T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342650061_8342360961","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2021,2021,1,49,"2021-01-04T14:26:00","14:26","2021-12-10T15:23:00","15:23",3662,"DAY",null,null,null,null,null,null,null,null,null,null,null,"239 jours dans le régime binaire"]
["SNCF Réseau","8342646561_8342366961","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2021,51,46,"2020-12-14","00:00","2021-11-15T03:24:00","03:24",37,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342646561_8342367761","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2021,51,49,"2020-12-14T14:32:00","14:32","2021-12-10T15:16:00","15:16",3832,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342646561_8342368561","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2021,51,46,"2020-12-14T00:25:00","00:25","2021-11-15T03:03:00","03:03",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342646561_8342369361","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2021,2021,6,42,"2021-02-08T23:35:00","23:35","2021-10-22T05:35:00","05:35",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8342646561_8342370361","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2021,51,49,"2020-12-14T10:26:00","10:26","2021-12-10T11:42:00","11:42",2937,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342646661_8342121461","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2021,2021,10,45,"2021-03-08T23:40:00","23:40","2021-11-10T05:10:00","05:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"79 jours dans le régime binaire"]
["SNCF Réseau","8342646661_8342122261","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2020,2021,51,49,"2020-12-14T11:30:00","11:30","2021-12-10T11:55:00","11:55",2979,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8342646661_8342120661","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2020,2021,51,49,"2020-12-14T14:05:00","14:05","2021-12-10T15:55:00","15:55",3949,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8342646661_8342119861","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2021,2021,10,45,"2021-03-08T22:55:00","22:55","2021-11-10T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"79 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342480161","Dijon-Toul",">","IsSurTille","Culmont",2020,2021,51,49,"2020-12-14T11:08:00","11:08","2021-12-10T11:38:00","11:38",2920,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342481761","Dijon-Toul",">","IsSurTille","Culmont",2020,2021,51,49,"2020-12-14T00:29:00","00:29","2021-12-06T04:03:00","04:03",202,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342483361","Dijon-Toul",">","IsSurTille","Culmont",2020,2021,51,49,"2020-12-14T00:54:00","00:54","2021-12-06T03:29:00","03:29",173,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342480961","Dijon-Toul",">","IsSurTille","Culmont",2021,2021,4,45,"2021-01-25T12:50:00","12:50","2021-11-12T17:23:00","17:23",1412,"DAY",null,null,null,null,null,null,null,null,null,null,null,"82 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342479361","Dijon-Toul",">","IsSurTille","Culmont",2021,2021,4,45,"2021-01-25T10:58:00","10:58","2021-11-12T14:28:00","14:28",1175,"DAY",null,null,null,null,null,null,null,null,null,null,null,"82 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342482561","Dijon-Toul",">","IsSurTille","Culmont",2020,2021,51,49,"2020-12-14T13:01:00","13:01","2021-12-10T14:22:00","14:22",3607,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342356561","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,49,"2020-12-14T09:47:00","09:47","2021-12-10T11:00:00","11:00",2762,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342354161","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,49,"2020-12-14T09:33:00","09:33","2021-12-10T10:47:00","10:47",2707,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342353361","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,49,"2020-12-14T14:10:00","14:10","2021-12-10T15:00:00","15:00",3765,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342352561","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,49,"2020-12-14T14:25:00","14:25","2021-12-10T15:10:00","15:10",3807,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342354961","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,48,"2020-12-20T22:40:00","22:40","2021-12-05T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342350961","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,49,"2020-12-14T00:20:00","00:20","2021-12-06T03:50:00","03:50",133,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342355761","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2021,2021,6,49,"2021-02-08T23:46:00","23:46","2021-12-10T06:20:00","06:20",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342351761","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2021,2021,6,49,"2021-02-08T23:09:00","23:09","2021-12-10T04:35:00","04:35",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342197461","Lerouville-Metz",">","Lerouville","Noveant",2021,2021,3,45,"2021-01-18T23:00:00","23:00","2021-11-12T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342200861","Lerouville-Metz",">","Lerouville","Noveant",2020,2021,51,49,"2020-12-14T10:42:00","10:42","2021-12-10T11:16:00","11:16",2828,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342200061","Lerouville-Metz",">","Lerouville","Noveant",2021,2021,4,42,"2021-01-31T23:27:00","23:27","2021-10-24T02:59:00","02:59",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342199261","Lerouville-Metz",">","Lerouville","Noveant",2020,2021,51,49,"2020-12-14T13:35:00","13:35","2021-12-10T15:02:00","15:02",3774,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342202461","Lerouville-Metz",">","Lerouville","Noveant",2021,2021,4,42,"2021-01-31T22:38:00","22:38","2021-10-24T01:02:00","01:02",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342198461","Lerouville-Metz",">","Lerouville","Noveant",2020,2021,51,49,"2020-12-14T14:02:00","14:02","2021-12-10T15:08:00","15:08",3799,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342201661","Lerouville-Metz",">","Lerouville","Noveant",2020,2021,51,49,"2020-12-14T10:16:00","10:16","2021-12-10T11:05:00","11:05",2782,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342062261","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2021,51,49,"2020-12-14T14:00:00","14:00","2021-12-10T15:20:00","15:20",3850,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342066461","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2021,2021,23,48,"2021-06-13T23:43:00","23:43","2021-12-05T02:23:00","02:23",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342065661","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2021,2021,24,49,"2021-06-14","00:00","2021-12-06T03:00:00","03:00",42,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342063861","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2021,51,49,"2020-12-14T14:17:00","14:17","2021-12-10T15:28:00","15:28",3883,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342067261","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2021,51,49,"2020-12-14T10:55:00","10:55","2021-12-10T11:50:00","11:50",2971,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342061461","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2021,2021,24,49,"2021-06-14T00:25:00","00:25","2021-12-06T03:50:00","03:50",53,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342064661","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2021,2021,8,49,"2021-02-22T10:12:00","10:12","2021-12-10T16:12:00","16:12",1010,"DAY",null,null,null,null,null,null,null,null,null,null,null,"63 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342060661","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2021,51,49,"2020-12-14T11:15:00","11:15","2021-12-10T11:55:00","11:55",2991,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342063061","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2021,2021,24,49,"2021-06-14T00:50:00","00:50","2021-12-06T03:25:00","03:25",46,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8342646361_8342095261","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2020,2021,51,49,"2020-12-14T00:50:00","00:50","2021-12-06T03:30:00","03:30",114,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","8342646361_8342096061","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2021,2021,9,48,"2021-03-01T10:15:00","10:15","2021-12-03T16:00:00","16:00",1029,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","8342646361_8342092861","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2020,2021,51,49,"2020-12-14T11:30:00","11:30","2021-12-10T12:10:00","12:10",3054,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342646361_8342094461","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2020,2021,51,49,"2020-12-14T14:05:00","14:05","2021-12-10T15:25:00","15:25",3870,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342646361_8342093661","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:50:00","03:50",126,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327859361","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2021,51,49,"2020-12-14T00:10:00","00:10","2021-12-06T03:05:00","03:05",55,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327860161","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2021,51,49,"2020-12-14T01:00:00","01:00","2021-12-06T04:05:00","04:05",72,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327861761","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2021,51,49,"2020-12-14T11:46:00","11:46","2021-12-10T12:35:00","12:35",3159,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327860961","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2021,51,49,"2020-12-14T13:13:00","13:13","2021-12-10T14:26:00","14:26",3623,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327858561","Dijon-Lyon",">","Chagny","Chalon sur Saone",2021,2021,11,44,"2021-03-15T23:00:00","23:00","2021-11-05T05:11:00","05:11",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"66 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327857761","Dijon-Lyon",">","Chagny","Chalon sur Saone",2021,2021,11,44,"2021-03-15T00:07:00","00:07","2021-11-05T05:55:00","05:55",-5,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"66 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327908761","Dijon-Lyon",">","Dijon","Chagny",2020,2021,51,49,"2020-12-14T00:25:00","00:25","2021-12-06T03:11:00","03:11",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327907961","Dijon-Lyon",">","Dijon","Chagny",2020,2021,51,49,"2020-12-14T12:42:00","12:42","2021-12-10T14:13:00","14:13",3569,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327906361","Dijon-Lyon",">","Dijon","Chagny",2020,2021,51,49,"2020-12-14T00:45:00","00:45","2021-12-06T04:00:00","04:00",71,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327904761","Dijon-Lyon",">","Dijon","Chagny",2021,2021,12,49,"2021-03-23T00:34:00","00:34","2021-12-11T05:57:00","05:57",558,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"94 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327907161","Dijon-Lyon",">","Dijon","Chagny",2020,2021,51,49,"2020-12-14T12:16:00","12:16","2021-12-10T12:44:00","12:44",3196,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327905561","Dijon-Lyon",">","Dijon","Chagny",2021,2021,12,45,"2021-03-22T22:29:00","22:29","2021-11-10T04:55:00","04:55",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"83 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327946961","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2021,51,49,"2020-12-14T11:37:00","11:37","2021-12-10T12:06:00","12:06",3037,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327945361","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2021,9,49,"2021-03-05T23:05:00","23:05","2021-12-10T05:57:00","05:57",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"133 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327942961","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2021,9,49,"2021-03-01T23:58:00","23:58","2021-12-10T05:18:00","05:18",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"136 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327946161","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2021,51,41,"2020-12-20T00:03:00","00:03","2021-10-17T02:30:00","02:30",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327943761","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2021,51,49,"2020-12-14T13:25:00","13:25","2021-12-10T14:56:00","14:56",3749,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327944561","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2021,51,49,"2020-12-14T01:07:00","01:07","2021-12-06T04:40:00","04:40",82,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327889561","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2021,51,47,"2020-12-14T10:43:00","10:43","2021-11-26T16:43:00","16:43",1694,"DAY",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327887161","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2021,51,49,"2020-12-14T12:00:00","12:00","2021-12-10T12:50:00","12:50",3222,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327888761","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2021,2021,13,45,"2021-04-04T23:44:00","23:44","2021-11-14T02:29:00","02:29",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327891561","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2021,2021,13,45,"2021-03-29T01:52:00","01:52","2021-11-08T04:32:00","04:32",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327890561","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2021,51,47,"2020-12-14T11:00:00","11:00","2021-11-26T13:00:00","13:00",1211,"DAY",null,null,null,null,null,null,null,null,null,null,null,"94 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327887961","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2021,51,49,"2020-12-14T12:49:00","12:49","2021-12-10T14:05:00","14:05",3536,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8328000161","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2021,51,47,"2020-12-14T14:15:00","14:15","2021-11-26T16:15:00","16:15",1432,"DAY",null,null,null,null,null,null,null,null,null,null,null,"89 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8327999361","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2021,2021,53,47,"2021-01-03T23:22:00","23:22","2021-11-28T02:39:00","02:39",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8328001961","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2021,51,49,"2020-12-14T13:09:00","13:09","2021-12-10T14:22:00","14:22",2400,"DAY",null,null,null,null,null,null,null,null,null,null,null,"168 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8328002761","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2021,51,47,"2020-12-14T10:15:00","10:15","2021-11-26T16:15:00","16:15",1436,"DAY",null,null,null,null,null,null,null,null,null,null,null,"89 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8328001161","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2021,51,49,"2020-12-14T11:49:00","11:49","2021-12-10T12:29:00","12:29",2085,"DAY",null,null,null,null,null,null,null,null,null,null,null,"168 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327960961","Dijon-Lyon",">","Macon","Saint Germain",2021,2021,8,48,"2021-02-28T22:50:00","22:50","2021-12-05T01:30:00","01:30",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327961761","Dijon-Lyon",">","Macon","Saint Germain",2020,2021,51,49,"2020-12-14T01:45:00","01:45","2021-12-06T05:04:00","05:04",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327964961","Dijon-Lyon",">","Macon","Saint Germain",2021,2021,9,49,"2021-03-01T23:43:00","23:43","2021-12-10T06:18:00","06:18",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"127 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327964161","Dijon-Lyon",">","Macon","Saint Germain",2020,2021,51,49,"2020-12-14T11:03:00","11:03","2021-12-10T11:33:00","11:33",2888,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327963361","Dijon-Lyon",">","Macon","Saint Germain",2020,2021,51,49,"2020-12-14T13:57:00","13:57","2021-12-10T15:28:00","15:28",3868,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327962561","Dijon-Lyon",">","Macon","Saint Germain",2021,2021,9,48,"2021-03-01T23:25:00","23:25","2021-12-03T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"144 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327867361","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2021,51,47,"2020-12-14T23:30:00","23:30","2021-11-25T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327864161","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2021,2021,23,44,"2021-06-07T03:06:00","03:06","2021-11-01T05:32:00","05:32",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327866561","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2021,2021,23,44,"2021-06-07T00:24:00","00:24","2021-11-01T03:47:00","03:47",14,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327865761","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2021,51,49,"2020-12-14T10:42:00","10:42","2021-12-10T12:01:00","12:01",2969,"DAY",null,null,null,null,null,null,null,null,null,null,null,"248 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327864961","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2021,51,49,"2020-12-14T11:44:00","11:44","2021-12-10T12:08:00","12:08",2997,"DAY",null,null,null,null,null,null,null,null,null,null,null,"248 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327863361","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2021,51,47,"2020-12-14T22:18:00","22:18","2021-11-25T04:40:00","04:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327938561","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2021,2021,13,45,"2021-03-29T02:30:00","02:30","2021-11-08T04:52:00","04:52",65,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327935361","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2021,2021,9,48,"2021-03-01T12:35:00","12:35","2021-12-03T16:15:00","16:15",588,"DAY",null,null,null,null,null,null,null,null,null,null,null,"37 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327936161","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2021,2021,9,48,"2021-03-01T09:15:00","09:15","2021-12-03T13:45:00","13:45",499,"DAY",null,null,null,null,null,null,null,null,null,null,null,"37 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327936961","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2021,2021,13,45,"2021-04-04T22:31:00","22:31","2021-11-14T02:02:00","02:02",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327939361","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2021,2021,5,47,"2021-02-01T10:15:00","10:15","2021-11-26T16:15:00","16:15",1127,"DAY",null,null,null,null,null,null,null,null,null,null,null,"70 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327937761","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2021,51,44,"2020-12-14T12:05:00","12:05","2021-11-05T13:48:00","13:48",2237,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327940361","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2021,51,44,"2020-12-14T12:58:00","12:58","2021-11-05T13:10:00","13:10",2133,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","8328066961_8327876161","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2020,2021,51,49,"2020-12-14T15:05:00","15:05","2021-12-10T15:48:00","15:48",3966,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328066961_8327877761","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2021,2021,1,47,"2021-01-04T00:05:00","00:05","2021-11-22T03:20:00","03:20",146,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","8328066961_8327878561","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2020,2021,51,49,"2020-12-14T14:31:00","14:31","2021-12-10T15:48:00","15:48",3967,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328066961_8327876961","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2021,2021,1,47,"2021-01-04T00:25:00","00:25","2021-11-22T03:10:00","03:10",138,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","8328066961_8327879361","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2020,2021,51,49,"2020-12-14T23:40:00","23:40","2021-12-10T05:40:00","05:40",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"212 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327955761","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2021,51,48,"2020-12-14T13:08:00","13:08","2021-12-03T16:28:00","16:28",546,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327957361","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2021,2021,7,47,"2021-02-15T10:22:00","10:22","2021-11-26T16:22:00","16:22",889,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327956561","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2021,51,48,"2020-12-14T08:40:00","08:40","2021-12-03T13:15:00","13:15",441,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327954961","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2021,51,44,"2020-12-14T13:30:00","13:30","2021-11-05T13:48:00","13:48",2235,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327953361","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2021,2021,13,45,"2021-04-04T22:10:00","22:10","2021-11-14T01:30:00","01:30",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327958361","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2021,2021,13,45,"2021-03-29T02:56:00","02:56","2021-11-08T05:30:00","05:30",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327954161","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2021,51,44,"2020-12-14T11:27:00","11:27","2021-11-05T13:05:00","13:05",2121,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327901561","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-14T14:28:00","14:28","2021-12-10T15:35:00","15:35",3538,"DAY",null,null,null,null,null,null,null,null,null,null,null,"228 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327899961","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-14T10:30:00","10:30","2021-12-10T11:24:00","11:24",2588,"DAY",null,null,null,null,null,null,null,null,null,null,null,"228 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327897561","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-14T10:30:00","10:30","2021-12-10T11:24:00","11:24",2588,"DAY",null,null,null,null,null,null,null,null,null,null,null,"228 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327902361","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-14T14:28:00","14:28","2021-12-10T15:35:00","15:35",3538,"DAY",null,null,null,null,null,null,null,null,null,null,null,"228 jours dans le régime binaire"]
["SNCF Réseau","8291617261_8291581861","Sarrebourg-Basel",">","Graffenstaden","Selestat",2020,2021,51,49,"2020-12-14T13:55:00","13:55","2021-12-10T15:08:00","15:08",3754,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291617261_8291579461","Sarrebourg-Basel",">","Graffenstaden","Selestat",2020,2021,51,49,"2020-12-14T10:33:00","10:33","2021-12-10T11:19:00","11:19",2807,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291617261_8341950861","Sarrebourg-Basel",">","Graffenstaden","Selestat",2021,2021,8,47,"2021-02-22T23:04:00","23:04","2021-11-25T05:23:00","05:23",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","8291617561_8291584261","Sarrebourg-Basel",">","Reding","Saverne",2020,2021,51,49,"2020-12-14T14:00:00","14:00","2021-12-10T14:45:00","14:45",3658,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291617561_8291585061","Sarrebourg-Basel",">","Reding","Saverne",2020,2021,51,49,"2020-12-14T13:21:00","13:21","2021-12-10T14:36:00","14:36",3622,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291617561_8291583261","Sarrebourg-Basel",">","Reding","Saverne",2021,2021,11,46,"2021-03-15T22:45:00","22:45","2021-11-19T04:57:00","04:57",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"105 jours dans le régime binaire"]
["SNCF Réseau","8291618161_8291571061","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2021,51,49,"2020-12-14T09:40:00","09:40","2021-12-10T10:30:00","10:30",2604,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618161_8291572661","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2021,51,49,"2020-12-14T09:29:00","09:29","2021-12-10T10:26:00","10:26",2588,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618161_8291573461","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2021,51,49,"2020-12-14T14:50:00","14:50","2021-12-10T16:00:00","16:00",3969,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618161_8291574261","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2021,51,49,"2020-12-14T15:01:00","15:01","2021-12-10T16:04:00","16:04",3985,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618161_8341841461","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2021,2021,15,48,"2021-04-12T22:50:00","22:50","2021-12-01T05:05:00","05:05",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"86 jours dans le régime binaire"]
["SNCF Réseau","8291618961_8291554261","Sarrebourg-Basel",">","Colmar","Lutterbach",2020,2021,51,49,"2020-12-14T14:25:00","14:25","2021-12-10T15:39:00","15:39",3882,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618961_8291555061","Sarrebourg-Basel",">","Colmar","Lutterbach",2020,2021,51,49,"2020-12-14T10:03:00","10:03","2021-12-10T10:50:00","10:50",2687,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618961_8342031061","Sarrebourg-Basel",">","Colmar","Lutterbach",2021,2021,7,48,"2021-02-15T23:01:00","23:01","2021-12-02T05:16:00","05:16",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"96 jours dans le régime binaire"]
["SNCF Réseau","8291618261_8291593861","Sarrebourg-Basel",">","Saverne","Vendenheim",2020,2021,51,49,"2020-12-14T13:45:00","13:45","2021-12-10T14:34:00","14:34",3627,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8291618261_8291592261","Sarrebourg-Basel",">","Saverne","Vendenheim",2020,2021,51,49,"2020-12-14T13:35:00","13:35","2021-12-10T14:26:00","14:26",3594,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8291618261_8291590461","Sarrebourg-Basel",">","Saverne","Vendenheim",2020,2021,51,49,"2020-12-14T13:36:00","13:36","2021-12-10T14:50:00","14:50",3694,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8291618261_8291591261","Sarrebourg-Basel",">","Saverne","Vendenheim",2021,2021,12,49,"2021-03-22T22:57:00","22:57","2021-12-09T05:12:00","05:12",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"79 jours dans le régime binaire"]
["SNCF Réseau","8291618261_8291593061","Sarrebourg-Basel",">","Saverne","Vendenheim",2020,2021,51,49,"2020-12-14T13:49:00","13:49","2021-12-10T14:57:00","14:57",3723,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8291618361_8345442361","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2021,2021,6,48,"2021-02-08T22:52:00","22:52","2021-12-03T05:00:00","05:00",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8291618361_8291549061","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2021,51,49,"2020-12-14T14:10:00","14:10","2021-12-10T15:19:00","15:19",3799,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618361_8291548261","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2021,51,49,"2020-12-14T10:17:00","10:17","2021-12-10T11:09:00","11:09",2766,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618361_8291549861","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2021,51,49,"2020-12-14T10:09:00","10:09","2021-12-10T11:01:00","11:01",2733,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618361_8291551461","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2021,51,49,"2020-12-14T14:19:00","14:19","2021-12-10T15:27:00","15:27",3832,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344015261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T11:10:00","11:10","2021-12-10T12:21:00","12:21",3088,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344024261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344021861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",60,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344018661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",73,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344021061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344023461","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",73,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344022661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T14:34:00","14:34","2021-12-10T15:24:00","15:24",3850,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344019461","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T00:35:00","00:35","2021-12-06T03:15:00","03:15",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344016061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2021,2021,10,44,"2021-03-08T23:17:00","23:17","2021-11-05T05:15:00","05:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344020261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T14:24:00","14:24","2021-12-10T15:19:00","15:19",3830,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344017861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T13:30:00","13:30","2021-12-10T14:50:00","14:50",3709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344017061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T14:51:00","14:51","2021-12-10T15:44:00","15:44",3934,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344225461_8343933661","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2020,2021,51,49,"2020-12-14T11:23:00","11:23","2021-12-10T12:30:00","12:30",3138,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225461_8343931861","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2021,2021,16,43,"2021-04-19T11:00:00","11:00","2021-10-29T15:00:00","15:00",859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8344225461_8343931061","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2020,2021,51,49,"2020-12-14T13:16:00","13:16","2021-12-10T14:08:00","14:08",3548,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225461_8343932661","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344225461_8343934461","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2021,2021,16,43,"2021-04-19T11:00:00","11:00","2021-10-29T15:00:00","15:00",859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8343996861","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2021,2021,18,42,"2021-05-03T11:09:00","11:09","2021-10-22T14:58:00","14:58",632,"DAY",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8344000861","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2021,2021,18,42,"2021-05-03T10:47:00","10:47","2021-10-22T14:58:00","14:58",632,"DAY",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8343998461","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2021,51,49,"2020-12-14T00:25:00","00:25","2021-12-06T03:00:00","03:00",155,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8343999261","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2021,51,49,"2020-12-14T11:02:00","11:02","2021-12-10T12:20:00","12:20",3084,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8343997661","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2021,51,49,"2020-12-14T00:46:00","00:46","2021-12-06T04:00:00","04:00",207,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8344000061","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2021,51,49,"2020-12-14T14:10:00","14:10","2021-12-10T14:54:00","14:54",3725,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224461_8344102261","Amiens-Douai",">","Arras","Bif d'Agny",2020,2021,51,49,"2020-12-14T09:46:00","09:46","2021-12-10T10:50:00","10:50",2720,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344224961_8344095661","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2020,2021,52,48,"2020-12-21T00:30:00","00:30","2021-11-29T03:30:00","03:30",45,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344224961_8344094861","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2020,2021,51,49,"2020-12-14T14:46:00","14:46","2021-12-10T15:37:00","15:37",3920,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344224961_8344096461","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2021,2021,11,44,"2021-03-15T09:30:00","09:30","2021-11-05T13:30:00","13:30",247,"DAY",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8344224961_8344094061","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2020,2021,51,49,"2020-12-14T15:07:00","15:07","2021-12-10T15:41:00","15:41",3937,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344112061","Boulogne-Calais",">","Boulogne","Marquise",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344112861","Boulogne-Calais",">","Boulogne","Marquise",2021,2021,1,39,"2021-01-04T22:03:00","22:03","2021-10-01T04:38:00","04:38",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344115661","Boulogne-Calais",">","Boulogne","Marquise",2020,2021,51,49,"2020-12-14T14:15:00","14:15","2021-12-10T15:35:00","15:35",3912,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344114861","Boulogne-Calais",">","Boulogne","Marquise",2020,2021,51,49,"2020-12-14T09:48:00","09:48","2021-12-10T10:38:00","10:38",2669,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344116461","Boulogne-Calais",">","Boulogne","Marquise",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344113661","Boulogne-Calais",">","Boulogne","Marquise",2021,2021,1,39,"2021-01-04T22:15:00","22:15","2021-10-01T04:19:00","04:19",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
["SNCF Réseau","8344225561_8344110261","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2020,2021,51,49,"2020-12-14T09:08:00","09:08","2021-12-10T10:40:00","10:40",2678,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225561_8344107861","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2020,2021,52,48,"2020-12-21T01:35:00","01:35","2021-11-29T05:10:00","05:10",65,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344225561_8344108661","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2021,2021,10,43,"2021-03-08T09:30:00","09:30","2021-10-29T13:30:00","13:30",260,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344225561_8344109461","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2020,2021,51,49,"2020-12-14T09:40:00","09:40","2021-12-10T10:44:00","10:44",2695,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343984861","Paris-Amiens",">","Creil","Longueau",2021,2021,5,49,"2021-02-01T22:55:00","22:55","2021-12-10T04:15:00","04:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"115 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343980861","Paris-Amiens",">","Creil","Longueau",2020,2021,51,49,"2020-12-14T12:35:00","12:35","2021-12-10T13:56:00","13:56",3498,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343981661","Paris-Amiens",">","Creil","Longueau",2020,2021,52,48,"2020-12-21T01:45:00","01:45","2021-11-29T04:20:00","04:20",54,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343986461","Paris-Amiens",">","Creil","Longueau",2020,2021,52,48,"2020-12-21T01:45:00","01:45","2021-11-29T05:15:00","05:15",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343983261","Paris-Amiens",">","Creil","Longueau",2021,2021,5,49,"2021-02-01T23:10:00","23:10","2021-12-10T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"115 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343984061","Paris-Amiens",">","Creil","Longueau",2020,2021,51,49,"2020-12-14T10:50:00","10:50","2021-12-10T11:30:00","11:30",2887,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343985661","Paris-Amiens",">","Creil","Longueau",2020,2021,51,49,"2020-12-14T14:58:00","14:58","2021-12-10T16:03:00","16:03",4029,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343982461","Paris-Amiens",">","Creil","Longueau",2020,2021,51,49,"2020-12-14T11:04:00","11:04","2021-12-10T11:51:00","11:51",2975,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343988061","Paris-Amiens",">","Creil","Longueau",2020,2021,52,48,"2020-12-21T02:15:00","02:15","2021-11-29T05:40:00","05:40",71,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343987261","Paris-Amiens",">","Creil","Longueau",2020,2021,52,48,"2020-12-21T01:20:00","01:20","2021-11-29T04:05:00","04:05",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344056461","Amiens-Douai",">","Arras","Douai",2020,2021,51,49,"2020-12-14T14:29:00","14:29","2021-12-10T15:20:00","15:20",3834,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344055661","Amiens-Douai",">","Arras","Douai",2020,2021,52,48,"2020-12-21T00:35:00","00:35","2021-11-29T03:20:00","03:20",26,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344054061","Amiens-Douai",">","Arras","Douai",2021,2021,20,49,"2021-05-17T22:50:00","22:50","2021-12-10T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"39 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344052461","Amiens-Douai",">","Arras","Douai",2020,2021,52,48,"2020-12-21T01:30:00","01:30","2021-11-29T04:30:00","04:30",34,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344054861","Amiens-Douai",">","Arras","Douai",2021,2021,20,49,"2021-05-17T23:00:00","23:00","2021-12-10T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"39 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344053261","Amiens-Douai",">","Arras","Douai",2020,2021,51,49,"2020-12-14T09:50:00","09:50","2021-12-10T10:56:00","10:56",2734,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344227161_8343951261","Paris-Busigny",">","Ormoy","Longueil",2020,2021,51,44,"2020-12-14T23:22:00","23:22","2021-11-05T05:10:00","05:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"145 jours dans le régime binaire"]
["SNCF Réseau","8344227161_8343953061","Paris-Busigny",">","Ormoy","Longueil",2020,2021,51,49,"2020-12-14T14:20:00","14:20","2021-12-10T16:00:00","16:00",4017,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227161_8343952261","Paris-Busigny",">","Ormoy","Longueil",2020,2021,51,49,"2020-12-14T10:57:00","10:57","2021-12-10T12:33:00","12:33",3151,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344119661","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2021,51,49,"2020-12-14T10:37:00","10:37","2021-12-10T11:31:00","11:31",2891,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344118861","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2021,2021,10,49,"2021-03-08T22:50:00","22:50","2021-12-10T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344118061","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2021,51,49,"2020-12-14T14:21:00","14:21","2021-12-10T15:26:00","15:26",3874,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344122061","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2021,2021,10,49,"2021-03-08T22:50:00","22:50","2021-12-10T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344121261","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2021,52,40,"2020-12-27T22:50:00","22:50","2021-10-10T01:40:00","01:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344120461","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2021,52,40,"2020-12-27T23:10:00","23:10","2021-10-10T02:20:00","02:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344013461","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T01:00:00","01:00","2021-12-06T03:54:00","03:54",77,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344007061","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T00:37:00","00:37","2021-12-06T03:45:00","03:45",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344010661","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T10:50:00","10:50","2021-12-10T12:05:00","12:05",3010,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344006261","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T00:54:00","00:54","2021-12-06T03:45:00","03:45",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344007861","Paris-Busigny",">","StQuentin","Busigny",2021,2021,10,43,"2021-03-08T23:46:00","23:46","2021-10-29T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344011861","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T14:09:00","14:09","2021-12-10T14:55:00","14:55",3715,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344009061","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T10:50:00","10:50","2021-12-10T12:05:00","12:05",3010,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344009861","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:37:00","03:37",71,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344012661","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T14:09:00","14:09","2021-12-10T14:55:00","14:55",3715,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344089661","Boulogne-Calais",">","Marquise","Calais",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344088061","Boulogne-Calais",">","Marquise","Calais",2021,2021,1,39,"2021-01-04T23:08:00","23:08","2021-10-01T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344090661","Boulogne-Calais",">","Marquise","Calais",2020,2021,51,49,"2020-12-14T14:27:00","14:27","2021-12-10T15:37:00","15:37",3920,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344091461","Boulogne-Calais",">","Marquise","Calais",2020,2021,51,49,"2020-12-14T09:40:00","09:40","2021-12-10T10:35:00","10:35",2657,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344092261","Boulogne-Calais",">","Marquise","Calais",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344088861","Boulogne-Calais",">","Marquise","Calais",2021,2021,1,39,"2021-01-04T23:08:00","23:08","2021-10-01T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
["SNCF Réseau","8344228061_8344125461","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2020,2021,52,48,"2020-12-21","00:00","2021-11-29T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344228061_8344126261","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2020,2021,52,48,"2020-12-21T01:35:00","01:35","2021-11-29T04:55:00","04:55",106,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344228061_8344127861","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2021,2021,2,46,"2021-01-11T22:58:00","22:58","2021-11-19T04:58:00","04:58",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"79 jours dans le régime binaire"]
["SNCF Réseau","8344228061_8344124661","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2020,2021,51,49,"2020-12-14T14:14:00","14:14","2021-12-10T14:58:00","14:58",3742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344228061_8344127061","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2020,2021,51,49,"2020-12-14T10:02:00","10:02","2021-12-10T11:12:00","11:12",2801,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343916261","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T01:00:00","01:00","2021-12-06T03:54:00","03:54",77,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343913861","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T10:40:00","10:40","2021-12-10T11:55:00","11:55",2968,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343912261","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T10:37:00","10:37","2021-12-10T11:50:00","11:50",2947,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343914661","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T13:58:00","13:58","2021-12-10T14:44:00","14:44",3669,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343915461","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T00:54:00","00:54","2021-12-06T03:45:00","03:45",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343911461","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:37:00","03:37",71,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343910661","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T13:56:00","13:56","2021-12-10T14:46:00","14:46",3677,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343917061","Paris-Busigny",">","Tergnier","StQuentin",2021,2021,1,43,"2021-01-04T23:26:00","23:26","2021-10-29T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"85 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343913061","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T00:37:00","00:37","2021-12-06T03:45:00","03:45",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228261_8344060661","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2020,2021,51,49,"2020-12-14T09:36:00","09:36","2021-12-10T10:43:00","10:43",2691,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228261_8344058861","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2021,2021,3,44,"2021-01-18T22:50:00","22:50","2021-11-05T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","8344228261_8344058061","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2020,2021,51,41,"2020-12-14","00:00","2021-10-11T03:00:00","03:00",42,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344228261_8344059861","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2020,2021,51,41,"2020-12-14","00:00","2021-10-11T03:00:00","03:00",42,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344228261_8344061461","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2020,2021,51,49,"2020-12-14T14:20:00","14:20","2021-12-10T15:09:00","15:09",3803,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344226061_8343893861","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2020,2021,51,49,"2020-12-14T10:02:00","10:02","2021-12-10T10:52:00","10:52",2728,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344226061_8343891461","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2021,2021,3,43,"2021-01-18T09:40:00","09:40","2021-10-29T13:25:00","13:25",1090,"DAY",null,null,null,null,null,null,null,null,null,null,null,"82 jours dans le régime binaire"]
["SNCF Réseau","8344226061_8343893061","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2020,2021,51,49,"2020-12-14T14:34:00","14:34","2021-12-10T15:44:00","15:44",3950,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344226061_8343892261","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2021,2021,3,43,"2021-01-18T09:25:00","09:25","2021-10-29T13:40:00","13:40",1111,"DAY",null,null,null,null,null,null,null,null,null,null,null,"82 jours dans le régime binaire"]
["SNCF Réseau","8344228561_8344097861","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2020,2021,52,40,"2020-12-27T23:15:00","23:15","2021-10-10T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344228561_8344098661","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2020,2021,51,49,"2020-12-14T09:55:00","09:55","2021-12-10T10:43:00","10:43",2690,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228561_8344100261","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2021,2021,3,49,"2021-01-18T22:50:00","22:50","2021-12-08T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8344228561_8344101261","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2020,2021,51,49,"2020-12-14T13:48:00","13:48","2021-12-10T15:10:00","15:10",3808,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228561_8344099461","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2020,2021,52,40,"2020-12-27T23:35:00","23:35","2021-10-10T02:45:00","02:45",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343972661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T00:05:00","00:05","2021-12-06T03:10:00","03:10",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343974261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T00:20:00","00:20","2021-12-06T03:30:00","03:30",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343965261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T14:20:00","14:20","2021-12-10T15:15:00","15:15",3828,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343964461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T00:35:00","00:35","2021-12-06T03:20:00","03:20",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343973461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:25:00","04:25",86,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343967661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T14:18:00","14:18","2021-12-10T15:03:00","15:03",3778,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343969261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T14:05:00","14:05","2021-12-10T14:55:00","14:55",3744,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343971861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T10:05:00","10:05","2021-12-10T11:20:00","11:20",2845,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343970061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,44,"2020-12-14T23:39:00","23:39","2021-11-05T04:59:00","04:59",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"145 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343968461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T00:10:00","00:10","2021-12-06T03:20:00","03:20",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343966861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T09:58:00","09:58","2021-12-10T11:05:00","11:05",2783,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343966061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T01:20:00","01:20","2021-12-06T04:05:00","04:05",80,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343971061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T10:25:00","10:25","2021-12-10T11:37:00","11:37",2916,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227361_8344106861","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2020,2021,51,49,"2020-12-14T11:30:00","11:30","2021-12-10T12:37:00","12:37",3167,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227361_8344105261","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2021,2021,16,43,"2021-04-19T11:00:00","11:00","2021-10-29T15:00:00","15:00",859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8344227361_8344104461","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2021,2021,16,43,"2021-04-19T11:00:00","11:00","2021-10-29T15:00:00","15:00",859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8344227361_8344103461","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344227361_8344106061","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2020,2021,51,49,"2020-12-14T13:30:00","13:30","2021-12-10T14:24:00","14:24",3615,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225961_8344067461","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2020,2021,52,38,"2020-12-21","00:00","2021-09-20T03:00:00","03:00",24,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","8344225961_8344064861","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2020,2021,51,49,"2020-12-14T09:55:00","09:55","2021-12-10T11:05:00","11:05",2783,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225961_8344065661","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2021,2021,6,49,"2021-02-08T22:30:00","22:30","2021-12-10T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
["SNCF Réseau","8344225961_8344066661","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2020,2021,51,49,"2020-12-14T14:02:00","14:02","2021-12-10T14:52:00","14:52",3732,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225961_8344068261","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2020,2021,51,37,"2020-12-20T23:00:00","23:00","2021-09-19T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343903861","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,47,"2020-12-20T21:28:00","21:28","2021-11-28T01:08:00","01:08",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343904661","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T11:00:00","11:00","2021-12-10T12:15:00","12:15",3076,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343906261","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2021,27,32,"2021-07-05T10:45:00","10:45","2021-08-13T15:35:00","15:35",207,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343905461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T11:15:00","11:15","2021-12-10T12:25:00","12:25",3117,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343900661","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T09:17:00","09:17","2021-12-10T10:00:00","10:00",2510,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343899061","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T09:32:00","09:32","2021-12-10T10:17:00","10:17",2581,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343901461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T10:50:00","10:50","2021-12-10T12:00:00","12:00",3013,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343899861","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,47,"2020-12-20T21:27:00","21:27","2021-11-28T23:57:00","23:57",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343907261","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2021,2,49,"2021-01-11T10:00:00","10:00","2021-12-10T14:00:00","14:00",536,"DAY",null,null,null,null,null,null,null,null,null,null,null,"39 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343903061","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T09:00:00","09:00","2021-12-10T09:46:00","09:46",2452,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227761_8344003861","Amiens-Douai","<","Arras","Bif de l'arbre Robert",2020,2021,51,49,"2020-12-14T14:40:00","14:40","2021-12-10T15:37:00","15:37",3920,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344226361_8344028661","Paris-Busigny",">","Creil","LongueilSteMarie",2020,2021,51,49,"2020-12-15","00:00","2021-12-11T05:05:00","05:05",1321,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","8344226361_8344027061","Paris-Busigny",">","Creil","LongueilSteMarie",2020,2021,51,49,"2020-12-14T14:35:00","14:35","2021-12-10T15:20:00","15:20",3849,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344226361_8344027861","Paris-Busigny",">","Creil","LongueilSteMarie",2020,2021,51,49,"2020-12-14T09:46:00","09:46","2021-12-10T10:57:00","10:57",2749,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344226361_8344029661","Paris-Busigny",">","Creil","LongueilSteMarie",2020,2021,51,49,"2020-12-14T01:35:00","01:35","2021-12-06T04:20:00","04:20",223,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344226361_8344026261","Paris-Busigny",">","Creil","LongueilSteMarie",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:10:00","03:10",164,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8327805661_8327641461","Avignon-Miramasparest",">","Avignon","Cavaillon",2020,2021,51,49,"2020-12-14T11:04:00","11:04","2021-12-10T11:33:00","11:33",2899,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805661_8327640461","Avignon-Miramasparest",">","Avignon","Cavaillon",2021,2021,14,48,"2021-04-06T09:10:00","09:10","2021-12-03T13:10:00","13:10",372,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","8327805661_8327639661","Avignon-Miramasparest",">","Avignon","Cavaillon",2021,2021,2,48,"2021-01-11T01:45:00","01:45","2021-11-29T04:16:00","04:16",92,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8327805661_8327642261","Avignon-Miramasparest",">","Avignon","Cavaillon",2020,2021,51,49,"2020-12-14T13:37:00","13:37","2021-12-10T15:07:00","15:07",3795,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805661_8327643061","Avignon-Miramasparest",">","Avignon","Cavaillon",2021,2021,2,48,"2021-01-11T00:32:00","00:32","2021-11-29T03:55:00","03:55",85,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8327807561_8327691461","Miramas-Marseille",">","Rognac","L'Estaque",2020,2021,51,49,"2020-12-14T10:56:00","10:56","2021-12-10T12:04:00","12:04",3029,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327807561_8327692261","Miramas-Marseille",">","Rognac","L'Estaque",2020,2021,51,49,"2020-12-14T11:05:00","11:05","2021-12-10T12:10:00","12:10",3054,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327807561_8327689861","Miramas-Marseille",">","Rognac","L'Estaque",2020,2021,51,49,"2020-12-14T10:02:00","10:02","2021-12-10T10:56:00","10:56",2745,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327807561_8327690661","Miramas-Marseille",">","Rognac","L'Estaque",2020,2021,51,49,"2020-12-14T09:56:00","09:56","2021-12-10T10:50:00","10:50",2720,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805761_8327734461","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2020,2021,51,49,"2020-12-14T09:53:00","09:53","2021-12-10T10:38:00","10:38",2669,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805761_8327735261","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2020,2021,51,49,"2020-12-14T15:06:00","15:06","2021-12-10T16:23:00","16:23",4113,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805761_8327736061","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2021,2021,1,49,"2021-01-04T22:30:00","22:30","2021-12-10T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"123 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327682261","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,49,"2020-12-14T10:51:00","10:51","2021-12-10T11:55:00","11:55",2992,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327678061","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,49,"2020-12-14T10:08:00","10:08","2021-12-10T11:05:00","11:05",2782,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327678861","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,49,"2020-12-14T01:00:00","01:00","2021-12-06T03:55:00","03:55",190,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327679661","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,49,"2020-12-14T10:20:00","10:20","2021-12-10T11:08:00","11:08",2795,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327680461","Miramas-Marseille",">","Miramas","Rognac",2021,2021,7,48,"2021-02-16","00:00","2021-12-04T04:30:00","04:30",576,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"128 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327681461","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,49,"2020-12-14T10:39:00","10:39","2021-12-10T11:51:00","11:51",2975,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806461_8327684661","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2020,2021,51,49,"2020-12-14T15:26:00","15:26","2021-12-10T16:54:00","16:54",4243,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806461_8327685461","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2021,2021,12,15,"2021-03-22T09:20:00","09:20","2021-04-16T13:20:00","13:20",244,"DAY",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8327806461_8327686461","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2020,2021,51,49,"2020-12-14T09:33:00","09:33","2021-12-10T10:01:00","10:01",2514,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806361_8327674261","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8327806361_8327670861","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2021,2021,5,43,"2021-02-01T22:30:00","22:30","2021-10-29T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"122 jours dans le régime binaire"]
["SNCF Réseau","8327806361_8327672661","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2020,2021,51,49,"2020-12-14T14:51:00","14:51","2021-12-10T16:06:00","16:06",4042,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806361_8327673461","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8327806361_8327671861","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2020,2021,51,49,"2020-12-14T10:06:00","10:06","2021-12-10T10:55:00","10:55",2740,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806761_8327585061","Avignon-Miramasparest",">","Cavaillon","Miramas",2021,2021,12,48,"2021-03-22T09:10:00","09:10","2021-12-03T13:10:00","13:10",385,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","8327806761_8327586061","Avignon-Miramasparest",">","Cavaillon","Miramas",2020,2021,51,49,"2020-12-14T10:14:00","10:14","2021-12-10T10:51:00","10:51",2723,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806761_8327587661","Avignon-Miramasparest",">","Cavaillon","Miramas",2020,2021,51,49,"2020-12-14T14:08:00","14:08","2021-12-10T15:33:00","15:33",3904,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806761_8327588461","Avignon-Miramasparest",">","Cavaillon","Miramas",2021,2021,2,48,"2021-01-11T00:55:00","00:55","2021-11-29T04:28:00","04:28",97,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8327806761_8327586861","Avignon-Miramasparest",">","Cavaillon","Miramas",2021,2021,2,48,"2021-01-11T01:16:00","01:16","2021-11-29T03:35:00","03:35",77,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8327804961_8327632461","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2021,2021,5,42,"2021-02-02","00:00","2021-10-23T04:30:00","04:30",445,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"99 jours dans le régime binaire"]
["SNCF Réseau","8327804961_8327630861","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2020,2021,51,49,"2020-12-14T11:11:00","11:11","2021-12-10T12:13:00","12:13",3067,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327804961_8327631661","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2020,2021,51,49,"2020-12-14T09:49:00","09:49","2021-12-10T10:46:00","10:46",2703,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327569661","Miramas-Fos-Marseille",">","Lavalduc","Fos",2021,2021,10,43,"2021-03-08T22:30:00","22:30","2021-10-29T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327570461","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327571261","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327573861","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2021,51,49,"2020-12-14T08:45:00","08:45","2021-12-10T09:45:00","09:45",2448,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327573061","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2021,51,49,"2020-12-14T08:45:00","08:45","2021-12-10T09:45:00","09:45",2448,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327572061","Miramas-Fos-Marseille",">","Lavalduc","Fos",2021,2021,13,48,"2021-03-29T22:30:00","22:30","2021-12-03T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327594661","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2021,51,37,"2020-12-14T23:15:00","23:15","2021-09-17T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327592061","Avignon-Miramasparouest",">","Avignon","Tarascon",2021,2021,1,42,"2021-01-04T23:10:00","23:10","2021-10-22T05:04:00","05:04",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327593661","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2021,51,47,"2020-12-15","00:00","2021-11-27T02:00:00","02:00",298,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"149 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327591261","Avignon-Miramasparouest",">","Avignon","Tarascon",2021,2021,1,49,"2021-01-04T01:05:00","01:05","2021-12-06T04:10:00","04:10",98,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327589661","Avignon-Miramasparouest",">","Avignon","Tarascon",2021,2021,1,49,"2021-01-04T01:20:00","01:20","2021-12-06T04:15:00","04:15",100,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327590461","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2021,51,49,"2020-12-14T10:01:00","10:01","2021-12-10T11:08:00","11:08",2795,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327592861","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2021,51,49,"2020-12-14T15:01:00","15:01","2021-12-10T15:51:00","15:51",3979,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327807161_8327724861","Avignon-Miramasparouest",">","Tarascon","Miramas",2021,2021,1,49,"2021-01-04T01:43:00","01:43","2021-12-06T04:45:00","04:45",112,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8327807161_8327722261","Avignon-Miramasparouest",">","Tarascon","Miramas",2021,2021,8,48,"2021-02-22T23:15:00","23:15","2021-12-03T05:13:00","05:13",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"139 jours dans le régime binaire"]
["SNCF Réseau","8327807161_8327721461","Avignon-Miramasparouest",">","Tarascon","Miramas",2021,2021,1,49,"2021-01-04T00:30:00","00:30","2021-12-06T03:28:00","03:28",82,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8327807161_8327723261","Avignon-Miramasparouest",">","Tarascon","Miramas",2020,2021,51,49,"2020-12-14T10:52:00","10:52","2021-12-10T11:25:00","11:25",2866,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327807161_8327724061","Avignon-Miramasparouest",">","Tarascon","Miramas",2020,2021,51,49,"2020-12-14T10:08:00","10:08","2021-12-10T11:34:00","11:34",2904,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]

{"sheet":"SBB","index":6,"n_rows":11,"n_cols":31,"rows_kept":11,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["SBB Infra",4715,"Basel GB - Basel RB","< >",null,null,2020,2020,null,null,"2020-08-21",null,"2020-08-31",null,null,null,"Brigde works","x",null,null,null,null,"x","x",null,"x",null,"Fr/Mo  21.08-24.08.2020, 28.08-31.08.2020 Totalclosure from 21:00 - 06.00. Trains direction SNCF Basel passenger station. Delay till 15 Min"]
["SBB Infra",6553,"Basel St. Johann","< >","BSSJ","BSSJ",2021,2021,null,null,"2021-02-26",null,"2021-07-30",null,null,"Night","Signal box works","x",null,null,null,null,"x","x",null,"x",null,"Totalclosure 8 nights for 4 hours. Exactlly dasy tbd"]
["SBB Infra",1872,"Basel RB","< >","BSGB","BSRB",2021,2021,null,null,"2021-03-09",null,"2021-04-27",null,null,null,"Switch works","x",null,null,null,null,"x","x",null,"x",null,"Nordkopf 100er Weichen (Zulauf Basel GB - RB eingeschränkt), 6 WE Sa/Su - Su/Mo (11.04-12.04 02 am to 04 am totalclosure, 17.04-19.04 10.00 am - 04.00am totalclosure). Trains direction SNCF  with delay till15 Min"]
["SBB Infra",29170,"Muttenz","< >","BSGB","BSRB",2021,2021,null,null,null,null,null,null,null,null,"Catenary works",null,"x",null,null,null,null,"x",null,"x",null,"16-18.10, 22-24.10, 30.10.-01-11, 6-8.11 Line Basel - Muttenz totalclosure. Trains direction SNCF via  Basel GB - Basel RB"]
[]
["SBB Infra",1899,"Basel GB - Basel RB","< >","BS","BSRB",2021,2021,null,null,"2019-10-13",null,"2019-11-22",null,null,null,"Switch works",null,null,null,null,null,null,null,null,"x",null,"Trains direction SNCF  with delay till15 Min"]
["SBB Infra",null,"Belgarde-La Plaine-Genève La Praille ","< >","LPFR","GEPR",2021,2021,null,null,null,null,null,null,null,null,"Platform works ",null,"x",null,null,null,null,null,null,"x",null,"Totalclosures may be possible"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"."]

{"sheet":"ACF CFL","index":7,"n_rows":79,"n_cols":31,"rows_kept":79,"cut":false,"hidden":false,"merged":[[0,17,0,21],[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["ACF/CFL","ACF27","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,23,24,"2021-06-12","01:30:00","2021-06-14","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF28","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,24,25,"2021-06-19","01:30:00","2021-06-21","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF29","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,25,26,"2021-06-26","01:30:00","2021-06-28","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF30","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,26,27,"2021-07-03","01:30:00","2021-07-05","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF33","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,27,28,"2021-07-10","01:30:00","2021-07-12","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF38","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,34,37,"2021-08-28","00:00:00","2021-09-13","04:00:00","17 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF58","Rodange-Bettembourg","< >","Rodange","Lamadelaine",2022,2022,34,37,"2022-08-27","01:00:00","2022-09-12","04:00:00","16 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF70","Rodange-Bettembourg","< >","Rodange","Aubange & Athus",2022,2022,47,48,"2022-11-21","00:00:00","2022-12-04","00:00:00","14 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF11","Rodange-Athus","< >","Rodange","Athus",2021,2021,7,8,"2021-02-20","04:00:00","2021-02-22","04:00:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF13","Rodange-Athus","< >","Rodange","Athus",2021,2021,8,9,"2021-02-27","04:00:00","2021-03-01","04:00:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF17","Rodange-Aubange","< >","Rodange","Aubange",2021,2021,15,15,"2021-04-17","01:00:00","2021-04-18","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF18","Rodange-Aubange","< >","Rodange","Aubange",2021,2021,16,16,"2021-04-24","01:00:00","2021-04-25","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF20","Rodange-Aubange/Athus","< >","Rodange","Aubange/Athus",2021,2021,17,17,"2021-05-01","01:00:00","2021-05-02","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF22","Rodange-Aubange/Athus","< >","Rodange","Aubange/Athus",2021,2021,18,18,"2021-04-24","01:00:00","2021-05-09","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF1","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2020,2020,20,21,"2020-05-16","01:30:00","2020-05-18","04:00:00","3 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF2","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2020,2020,21,22,"2020-05-23","01:30:00","2020-05-25","04:00:00","3 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF3","Rodange-Bettembourg","< >","Belval-Usines","Differdange",2020,2020,22,24,"2020-05-30","00:00:00","2020-06-08","04:00:00","10 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF4","Luxembourg-Kleinbettingen","< >","Bertrange","Kleinbettingen",2020,2020,28,30,"2020-07-11","01:00:00","2020-07-27","01:00:00","16 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF5","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2020,2020,38,39,"2020-09-19","01:30:00","2020-09-21","04:00:00","2 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF6","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2020,2020,43,44,"2020-10-24","01:30:00","2020-10-26","04:00:00","2 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF7","Rodange-Bettembourg","< >","Belval-Usines","Differdange",2020,2020,44,46,"2020-10-31","01:00:00","2020-11-09","04:00:00","9 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF8","Luxembourg-Kleinbettingen","< >","Bertrange","Kleinbettingen",2020,2020,44,46,"2020-10-31","01:00:00","2020-11-09","01:00:00","9 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF9","Rodange-Aubange","< >","Rodange","Aubange",2020,2021,45,8,"2020-11-06","01:00:00","2021-03-01","23:59:00","16 weeks","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF10","Luxembourg-Pétange","< >","Dippach","Luxembourg",2021,2021,6,7,"2021-02-13","01:30:00","2021-02-15","04:00:00","2 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF12","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2021,2021,7,8,"2021-02-16","01:00:00","2021-02-21","04:00:00","6 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF14","Rodange-Athus","< >","Rodange","Athus",2021,2021,9,16,"2021-03-05","00:00:00","2021-04-25","23:59:00","8 weeks","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF15","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,12,13,"2021-03-27","01:00:00","2021-03-29","04:00:00","6 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF16","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,13,16,"2021-04-03","04:00:00","2021-04-19","04:00:00","16 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF19","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,16,17,"2021-04-24","04:00:00","2021-04-26","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF21","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,17,18,"2021-05-01","04:00:00","2021-05-03","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF23","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,18,19,"2021-05-08","04:00:00","2021-05-10","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF24","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,19,20,"2021-05-15","04:00:00","2021-05-17","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF25","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2021,2021,20,21,"2021-05-22","01:00:00","2021-05-25","04:00:00","3 days","Night/Day","underpass renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF26","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,22,23,"2021-06-05","04:00:00","2021-06-07","04:00:00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF31","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,26,27,"2021-07-03","01:30:00","2021-07-05","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF32","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,27,28,"2021-07-10","01:30:00","2021-07-12","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF34","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,28,29,"2021-07-17","04:00:00","2021-07-19","04:00:00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF35","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,29,30,"2021-07-24","04:00:00","2021-07-26","04:00:00","2 days","Night/Day","new bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF36","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,31,32,"2021-08-07","04:00:00","2021-08-08","04:00:00","1 day","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF37","Rodange-Bettembourg","< >","Esch/Alzette","Noertzange",2021,2021,34,37,"2021-08-28","00:00:00","2021-09-13","04:00:00","17 days","Night/Day","brigde maintenance/renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF39","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,37,38,"2021-09-18","04:00:00","2021-09-20","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF40","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,38,39,"2021-09-25","04:00:00","2021-09-27","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF41","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,39,40,"2021-10-02","01:30:00","2021-10-04","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF42","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,40,41,"2021-10-09","01:30:00","2021-10-11","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF43","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,41,42,"2021-10-16","04:00:00","2021-10-18","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF44","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,42,43,"2021-10-23","04:00:00","2021-10-25","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF45","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2021,2021,43,45,"2021-06-19","00:00:00","2021-06-21","04:00:00","3 days","Night/Day","switch renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF46","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2021,2021,43,45,"2021-10-30","00:00:00","2021-11-08","04:00:00","9 days","Night/Day","switch renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF47","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2021,2021,43,44,"2021-10-30","00:00:00","2021-11-02","04:00:00","3 days","Night/Day","underpass renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF48","Rodange-Bettembourg","< >","Belval-Lycée","Esch/Alzette",2022,2022,8,9,"2022-02-26","01:00:00","2022-02-28","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF49","Rodange-Bettembourg","< >","Belval-Lycée","Esch/Alzette",2022,2022,9,10,"2022-03-05","01:00:00","2022-03-07","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF50","Rodange-Bettembourg","< >","Oberkorn","Belval-Lycée",2022,2022,18,19,"2022-05-07","01:00:00","2022-05-10","04:00:00","3 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF51","Rodange-Bettembourg","< >","Belval-Usines","Esch/Alzette",2022,2022,20,22,"2022-05-21","01:00:00","2022-05-30","04:00:00","9 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF52","Rodange-Bettembourg","< >","Oberkorn","Belval-Lycée",2022,2022,22,23,"2022-06-04","01:00:00","2022-06-07","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF53","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,23,24,"2022-06-11","01:00:00","2022-06-13","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF54","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,24,25,"2022-06-18","01:00:00","2022-06-20","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF55","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,25,26,"2022-06-25","01:00:00","2022-06-27","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF56","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,26,27,"2022-07-02","01:00:00","2022-07-04","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF57","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,28,36,"2022-07-16","01:00:00","2022-09-05","04:00:00","51 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF59","Luxembourg-Bettembourg",">","Luxembourg","Bettembourg",2022,2022,36,37,"2022-09-09","23:30:00","2022-09-12","05:00:00","2 days","Night/Day","renewal of the line",null,"x",null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF60","Luxembourg-Bettembourg",">","Luxembourg","Bettembourg",2022,2022,37,38,"2022-09-16","23:30:00","2022-09-19","05:00:00","2 days","Night/Day","renewal of the line",null,"x",null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF61","Rodange-Bettembourg","< >","Belval-Usines","Obercorn",2022,2022,38,39,"2022-09-24","01:00:00","2022-09-26","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF62","Rodange-Bettembourg","< >","Belval-Usines","Obercorn",2022,2022,39,40,"2022-10-01","01:00:00","2022-10-03","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF63","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,40,41,"2022-10-08","01:00:00","2022-10-10","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF64","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,41,42,"2022-10-15","01:00:00","2022-10-17","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF65","Luxembourg-Bettembourg",">","Luxembourg","Bettembourg",2022,2022,42,43,"2022-10-22","23:30:00","2022-10-24","05:00:00","2 days","Night/Day","renewal of the line",null,"x",null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF66","Rodange-Bettembourg","< >","Belval-Usines","Obercorn",2022,2022,42,43,"2022-10-22","01:00:00","2022-10-24","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF67","Luxembourg-Bettembourg","< >","Luxembourg-triage","Berchem",2022,2022,43,52,"2022-10-29","01:00:00","2022-12-31","04:00:00","9 weeks","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF68","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,45,46,"2022-11-12","01:00:00","2022-11-14","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF69","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,46,47,"2022-11-19","01:00:00","2022-11-21","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF71","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,47,48,"2022-11-26","01:00:00","2022-11-28","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF72","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,48,49,"2022-12-03","01:00:00","2022-12-05","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF73","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,49,50,"2022-12-10","01:00:00","2022-12-12","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF74","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,50,51,"2022-12-17","01:00:00","2022-12-19","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
[]
[]
["HIGHTLIGHTS --> TOTAL CLOSURE OF THE CORRIDOR RFC NSM"]