{"text_format":"1","workbook":"xlsx","n_sheets":8,"sheets":["Home","Main Impact Map","ProRail","Infrabel","Data","SNCFR","SBB","ACF CFL"],"not_rendered":{"charts":0,"images":11,"macros":1,"external_links":8,"defined_names":60,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Home","index":0,"n_rows":18,"n_cols":15,"rows_kept":18,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"! click icon to follow !"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["                              version 14 September 2020"]

{"sheet":"Main Impact Map","index":1,"n_rows":30,"n_cols":14,"rows_kept":30,"cut":false,"hidden":false,"merged":[[45,5,46,7]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Main TCR for TT 2020 to TT 2023"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-02-02"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"click on              for detailed TCR information"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,"Plaine d'Alsace"]

{"sheet":"ProRail","index":2,"n_rows":102,"n_cols":31,"rows_kept":102,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
["ProRail","IO-L-005231-2001-00",".","< >","Oudewater overloopw.","Woerden Overloop",2020,2020,37,38,"2020-09-12","02:00:00","2020-09-14","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Aanleggen RIP KM 21.200 dubbelsporig",null,"Y","L-005231"]
["ProRail","IO-Z-906096-wd01-00",".","< >","Woerden","Woerden Overloop",2020,2020,37,38,"2020-09-12","02:00:00","2020-09-14","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Conserveren traverse.",null,"Y","Z-906096"]
["ProRail","IO-K-006630-2010-01",".","< >","Botlek","Pernis",2020,2020,39,40,"2020-09-26","23:00:00","2020-09-28","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen wissel, spoor en dwarsliggers",null,"Y","K-006630"]
["ProRail","IO-K-006630-2017-03",".","< >","Europoort","Suurhoffbrug o/h Hartelkanaal",2020,2020,39,40,"2020-09-26","23:00:00","2020-09-28","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen spoor en wissels",null,"Y","K-006630"]
["ProRail","IO-R-523400-2002-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,39,40,"2020-09-26","23:00:00","2020-09-28","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Bouw kunstwerken over spoor tbv aanleg CER.",null,"Y","R-523400"]
["ProRail","IO-K-006357-2014-00",".","< >","Barendrecht","Rotterdam Stadion",2020,2020,40,41,"2020-10-03","00:00:00","2020-10-05","04:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Wijzigingen draagconstructie Munnikensteeg Plaatsen van 4 overspanningsbeveiligingen",null,"Y","K-006357"]
["ProRail","IO-L-005189-2022-00",".","< >","Erasmusgracht aansl.","Amsterdam Sloterdijk",2020,2020,40,40,"2020-10-03","02:00:00","2020-10-04","18:00:00","40:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen spoorstaven en dwarsliggers.",null,"Y","L-005189"]
["ProRail","IO-L-005233-2001-00",".","< >","Erasmusgracht aansl.","Amsterdam Sloterdijk",2020,2020,40,41,"2020-10-03","02:00:00","2020-10-05","04:00:00","50:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Herstellen betonschade opstortblokken van viaduct te Amsterdam Sloterdijk.",null,"Y","L-005233"]
["ProRail","IO-R-550080-2001-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2020,2020,40,41,"2020-10-03","19:00:00","2020-10-05","05:00:00","34:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Plaatsen van damwanden.",null,"Y","R-550080"]
["ProRail","IO-Z-906096-ass1-00",".","< >","Erasmusgracht aansl.","Amsterdam Sloterdijk",2020,2020,40,41,"2020-10-03","00:00:00","2020-10-05","02:00:00","50:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Conserveren hout- en staalwerk tubes perron sp 11-12",null,"Y","Z-906096"]
["ProRail","IO-K-006631-IO2B-00",".","< >","Waalhaven Zuid","Waalhaven Zuid",2020,2020,41,42,"2020-10-10","07:00:00","2020-10-12","11:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"",null,null,null,"-Vernieuwen wsl 609 -Vernieuwen spoortak 609R (301B)- vern ovw bevl 609R (301B)",null,"Y","K-006631"]
["ProRail","IO-L-005189-2016-00",".","< >","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2020,2020,42,43,"2020-10-17","02:00:00","2020-10-19","06:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen dwarsliggers,blokjesspoor, compensatielassen en spoorstaven",null,"Y","L-005189"]
["ProRail","IO-K-006610-2056-00",".","< >","Dordrecht","Dordrecht",2020,2020,43,44,"2020-10-24","01:00:00","2020-10-26","04:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"R",null,null,null,"wissels: -1145A -1145B -1165",null,"Y","K-006610"]
["ProRail","IO-Z-180000-2003-00",".","< >","Breda aansl.","Roosendaal racc. Philips",2020,2020,43,43,"2020-10-24","05:00:00","2020-10-25","04:00:00","24:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen Dateq voor DOSS",null,"Y","Z-180000"]
["ProRail","IO-K-006000-2001-00",".","< >","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2020,2020,45,47,"2020-11-07","01:00:00","2020-11-16","05:00:00","220:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Saneren van wissels 101A/B, 123A/B, 141A/B, 143A/B, 255, 253 A/B, 163A/B, 959A/B, 983A/B, 985A/B + 975/977, 901AB/917AB",null,"Y","K-006000"]
["ProRail","IO-K-006630-2001-00",".","< >","Barendrecht aansl.","Kijfhoek zuid",2020,2020,46,46,"2020-11-14","23:00:00","2020-11-15","15:00:00","16:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen dwarsliggers",null,"Y","K-006630"]
["ProRail","IO-K-006630-2010-02",".","< >","Botlek","Pernis",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"vernieuwen wissel, spoor en dwarsliggers",null,"Y","K-006630"]
["ProRail","IO-R-497500-2004-00",".","< >","Botlek racc.Theemsweg","Europoort",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Werkzaamheden aan / tbv de onderbouw van het nieuwe Theemswegtracé.",null,"Y","R-497500"]
["ProRail","IO-R-523400-2006-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2020,2020,46,47,"2020-11-14","23:00:00","2020-11-16","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"- Saneren Overweg 300.3 - Saneren Overweg 303.5 - Nieuwe wegaansluiting overweg 3.2",null,"Y","R-523400"]
["ProRail","IO-Z-180001-1901-00",".","< >","Rotterdam Blaak","Willemstunnel Zuid",2020,2020,46,47,"2020-11-14","00:00:00","2020-11-16","03:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"aanpassing besturings systeem Willemsspoortunnel",null,"Y","Z-180001"]
["ProRail","IO-R-474300-2002-00",".","< >","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2020,2020,47,49,"2020-11-21","00:00:00","2020-11-30","00:00:00","216:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Wijzigen en testen EBS i.v.m. goederen overdrachtspoor",null,"Y","R-474300"]
["ProRail","IO-L-005113-2003-00",".","< >","Harmelen aansl.","Woerden Overloop",2020,2020,50,51,"2020-12-12","02:00:00","2020-12-14","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen ledseinen en matrixsignaalgever",null,"Y","L-005113"]
["ProRail","IO-L-005121-2101-00",".","< >","Amsterdam Amstel","Watergraafsmeer West aansl.",2021,2021,2,3,"2021-01-16","02:00:00","2021-01-18","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleidingbalken portaal 3/28-3/29-3/30, portaal 3/31-3/32(-3/33)_PVE-5",null,"Y","L-005121"]
["ProRail","IO-L-005124-2102-00",".","< >","Amsterdam Amstel","Watergraafsmeer West aansl.",2021,2021,2,3,"2021-01-16","01:00:00","2021-01-18","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-2",null,"Y","L-005124"]
["ProRail","IO-L-005124-2106-00",".","< >","Amsterdam Muiderpoort","Dijksgracht Westzijde (Amsterdam)",2021,2021,2,2,"2021-01-16","00:00:00","2021-01-16","20:00:00","20:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-2 deel E",null,"Y","L-005124"]
["ProRail","IO-L-005189-2019-00",".","< >","Erasmusgracht aansl.","Zaandam",2021,2021,5,6,"2021-02-06","02:20:00","2021-02-08","05:20:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen dwarsliggers en spoorstaven in diverse sporen",null,"Y","L-005189"]
["ProRail","IO-R-485000.01-Hbg1-00",".","< >","Erasmusgracht aansl.","Radarweg aansl.",2021,2021,5,6,"2021-02-06","02:00:00","2021-02-08","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Ass Hemboog spoorwerk, lichten-schiften, reguleren Bvl Sporen 9 en 10",null,"Y","R-485000.01"]
["ProRail","IO-K-006308-2001-00",".","< >","Gouda","Moordrecht overloopw.",2021,2021,6,7,"2021-02-13","01:15:00","2021-02-15","05:15:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"groot onderhoud aan brug",null,"Y","K-006308"]
["ProRail","IO-K-006310-2101-00",".","< >","Gouda","Moordrecht overloopw.",2021,2021,6,7,"2021-02-13","01:15:00","2021-02-15","05:15:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"omlassen kabeltrace's, werkzaamheden relaishuis 10 Gd.",null,"Y","K-006310"]
["ProRail","IO-M-004551-2105-00",".","< >","Roosendaal grens","Roosendaal grens",2021,2021,10,11,"2021-03-13","01:00:00","2021-03-15","05:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"R",null,null,null,"BBV Rsd",null,"Y","M-004551"]
["ProRail","IO-K-006305-2101-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"werkzaamheden Calandbrug",null,"Y","K-006305"]
["ProRail","IO-K-006630-2008-00",".","< >","Botlek","Botlek",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","ST",null,null,null,null,"",null,null,null,"Vernieuwen spoor en overwegen",null,"Y","K-006630"]
["ProRail","IO-K-006630-2018-00",".","< >","Europoort West","Suurhoffbrug o/h Hartelkanaal",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vernieuwen wissels",null,"Y","K-006630"]
["ProRail","IO-R-403700-2101-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Indienststellen nieuwe Botlekbrug (stap 200 )",null,"Y","R-403700"]
["ProRail","IO-R-497500-2102-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-523400-2101-00",".","< >","Maasvlakte Prinses Amaliahaven","Maasvlakte Yangtzehaven Noord",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"- Saneren Overweg 300.3 - Saneren Overweg 303.5",null,"Y","R-523400"]
["ProRail","IO-R-546200-2101-01",".","< >","Europoort West","Maasvlakte aansl.",2021,2021,13,14,"2021-04-03","19:00:00","2021-04-05","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"weggedeelte suurhofbrug vervangen",null,"Y","R-546200"]
["ProRail","IO-R-550080-TAC1-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2021,2021,13,14,"2021-04-04","00:55:00","2021-04-06","04:55:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Plaatsen van damwanden.",null,"Y","R-550080"]
["ProRail","IO-R-552700-2101-00",".","< >","Moerdijk","Lage Zwaluwe",2021,2021,13,14,"2021-04-04","01:00:00","2021-04-05","05:00:00","28:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Bouwen van een overweg",null,"Y","R-552700"]
["ProRail","IO-K-006305-2102-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,20,21,"2021-05-22","19:00:00","2021-05-24","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"werkzaamheden Calandbrug",null,"Y","K-006305"]
["ProRail","IO-M-004551-2104-00",".","< >","Roosendaal grens","Roosendaal grens",2021,2021,20,21,"2021-05-22","01:00:00","2021-05-25","05:00:00","76:00","continuous","Miscellaneous","T","ST",null,null,null,null,"R",null,null,null,"BBV Rsd",null,"Y","M-004551"]
["ProRail","IO-R-497500-2101-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,20,21,"2021-05-22","19:00:00","2021-05-24","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-546200-2101-02",".","< >","Europoort West","Maasvlakte aansl.",2021,2021,20,21,"2021-05-22","19:00:00","2021-05-24","23:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"weggedeelte suurhofbrug vervangen",null,"Y","R-546200"]
["ProRail","IO-R-550080-TAC2-00",".","< >","Amsterdam Transformatorweg aansl.","Amsterdam Westhaven",2021,2021,23,23,"2021-06-07","01:15:00","2021-06-11","05:15:00","100:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Plaatsen van onderdoorgang, zeer sterke voorkeur voor pasen ivm andere planning",null,"Y","R-550080"]
["ProRail","IO-L-005211-2107-00",".","< >","Houtrakpolder (Amsterdam)","Houtrakpolder aansl.(Amsterdam)",2021,2021,27,27,"2021-07-05","07:00:00","2021-07-09","07:00:00","96:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vernieuwen wissels 115, 106 en 112 en ballast spoor 5250 en 5350 Vernieuwen wissels 109, ballast spoor 5165 en 5454, spoorstaven spoor 5165, 5252 en 5454 en spoortak spoor 5165 en 5352",null,"Y","L-005211"]
["ProRail","IO-R-474300-2101-00",".","< >","Rotterdam Aansl Zuid","Rotterdam Westelijke Splitsing",2021,2021,28,30,"2021-07-17","01:00:00","2021-07-26","01:00:00","216:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Wijzigen en testen EBS i.v.m. goederen overdrachtspoor",null,"Y","R-474300"]
["ProRail","IO-M-004551-2101-00",".","< >","Markbrug - tussen Zevenbergen en Oudenbosch","Zevenbergen inhaalsp.",2021,2021,29,32,"2021-07-24","01:25:00","2021-08-09","05:25:00","388:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"PSS + BBV",null,"Y","M-004551"]
["ProRail","IO-Z-906106-LZ02-01",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,29,30,"2021-07-24","01:25:00","2021-07-26","05:25:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-Z-906106-LZ02-02",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,30,31,"2021-07-31","01:25:00","2021-08-02","05:25:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-Z-906106-LZ03-01",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,34,35,"2021-08-28","01:30:00","2021-08-30","05:30:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-R-485000.01-Hbg2-00",".","< >","Erasmusgracht aansl.","Radarweg aansl.",2021,2021,35,36,"2021-09-04","02:00:00","2021-09-06","05:00:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Ass Hemboog spoorwerk, lichten-schiften, reguleren Bvl Sporen 9 en 10",null,"Y","R-485000.01"]
["ProRail","IO-R-497500-2103-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,36,37,"2021-09-11","23:00:00","2021-09-13","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Theemsweg",null,"Y","R-497500"]
["ProRail","IO-Z-906107-DVD2-00",".","< >","Duivendrecht aansluiting west","Venserpolder aansl.",2021,2021,37,38,"2021-09-18","02:15:00","2021-09-20","05:15:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen roltrap nivo 1-2. Aanvoeren en afvoeren roltrappen via spoor Gdpa-Asra op nivo 1.",null,"Y","Z-906107"]
["ProRail","IO-Z-906106-LZ03-02",".","< >","Moerdijkbrug Zuid aansl.","Lage Zwaluwe",2021,2021,38,39,"2021-09-25","01:30:00","2021-09-27","05:30:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen en vernieuwen perronkeerwanden met bijbehorende werkzaamheden aan perronbestratingen en geleidelijnen.",null,"Y","Z-906106"]
["ProRail","IO-M-004551-2106-00",".","< >","Bergen op Zoom","Roosendaal",2021,2021,39,40,"2021-10-02","03:00:00","2021-10-04","03:00:00","48:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"BBV Rsd",null,"Y","M-004551"]
["ProRail","IO-R-497500-2104-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,39,40,"2021-10-02","23:00:00","2021-10-04","07:00:00","32:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-L-005121-2103-00",".","< >","Amsterdam Centraal","Watergraafsmeer West aansl.",2021,2021,40,41,"2021-10-10","01:00:00","2021-10-11","05:00:00","28:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleidingbalk 2/129-130 en 4/7-8 Dgr_PVE-5",null,"Y","L-005121"]
["ProRail","IO-L-005124-2104-00",".","< >","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2021,2021,40,40,"2021-10-09","01:00:00","2021-10-10","00:50:00","23:50","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-1 deel A en B",null,"Y","L-005124"]
["ProRail","IO-L-005211-2102-00",".","< >","Amsterdam Sloterdijk","Spaarnebrug - bij Haarlem",2021,2021,40,41,"2021-10-09","01:35:00","2021-10-11","05:35:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vernieuwen spoorstaven en dwarsliggers spoor SJ en spoorstaven spoor 602",null,"Y","L-005211"]
["ProRail","IO-R-3AE001-2103-00",".","< >","Amsterdam Amstel","Amsterdam Zaanstraat",2021,2021,40,41,"2021-10-09","01:00:00","2021-10-11","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Leeghalen Dijksgracht",null,"Y","R-3AE001"]
["ProRail","IO-R-3AE011-2101-00",".","< >","Amsterdam Sloterdijk","Singelgracht aansl.",2021,2021,40,41,"2021-10-09","01:35:00","2021-10-11","05:35:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Perron verlenging Amsterdam zijde (optioneel inkortte perron andere zijde) Verwijderen van OTC's Aanpassen bovenleiding",null,"Y","R-3AE011"]
["ProRail","IO-Z-906107-DVD5-00",".","< >","Duivendrecht aansluiting west","Venserpolder aansl.",2021,2021,42,43,"2021-10-23","02:15:00","2021-10-25","05:15:00","51:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"Vervangen roltrap nivo 1-2.",null,"Y","Z-906107"]
["ProRail","IO-L-005121-2102-00",".","< >","Amsterdam Amstel","Duivendrecht",2021,2021,44,45,"2021-11-07","01:00:00","2021-11-08","05:00:00","28:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleidingbalken portaal 3/3-3/4, 3/11-3/12 en portaal 3/15-3/16 Dmn-Asdm_PVE-5",null,"Y","L-005121"]
["ProRail","IO-L-005124-2105-00",".","< >","Amsterdam Muiderpoort","Watergraafsmeer West aansl.",2021,2021,44,44,"2021-11-06","01:00:00","2021-11-07","00:50:00","23:50","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-1 deel D1",null,"Y","L-005124"]
["ProRail","IO-L-005124-2107-00",".","< >","Amsterdam Amstel","Watergraafsmeer West aansl.",2021,2021,44,44,"2021-11-06","02:00:00","2021-11-07","01:50:00","23:50","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Vervangen bovenleiding-draagconstructie PVE-2 deel F",null,"Y","L-005124"]
["ProRail","IO-R-3AE001-2104-00",".","< >","Amsterdam Amstel","Amsterdam Zaanstraat",2021,2021,44,45,"2021-11-06","01:00:00","2021-11-08","05:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Saneren wissels 1e perronbak.",null,"Y","R-3AE001"]
["ProRail","IO-R-3AE011-2102-00",".","< >","Amsterdam Sloterdijk","Singelgracht aansl.",2021,2021,44,45,"2021-11-06","05:35:00","2021-11-08","05:35:00","48:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Bouwstap aannemer, Aanbrengen RH - Wissels - Kabelkruizingen",null,"Y","R-3AE011"]
["ProRail","IO-R-497500-2105-00",".","< >","Botlek","Waalhaven Zuid aansl Zuid",2021,2021,44,45,"2021-11-02","05:00:00","2021-11-08","05:00:00","144:00","continuous","Miscellaneous","T","LT",null,null,null,null,"",null,null,null,"theemsweg",null,"Y","R-497500"]
["ProRail","IO-R-3AE011-2103-00",".","< >","Amsterdam Sloterdijk","Singelgracht aansl.",2022,2022,18,19,"2022-05-07","00:00:00","2022-05-09","04:00:00","52:00","continuous","Miscellaneous","T","LT",null,null,null,null,"R",null,null,null,"Eulynx voorbereidingen, plaatsen objectcontrolers en realiseren glasvezelnetwerk. Eventueel al een gedeeltelijke voortest.",null,"Y","R-3AE011"]
["ProRail","0084-Z906141-2206-00",".","< >","Watergraafsmeer Oost aansl. (NL-1347)","Dijksgracht Westzijde (Amsterdam) (NL-1115)",null,null,null,null,"2022-04-02","01:00:00","2022-04-04T05:00:00","05:00:00",null,"continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-01",".","< >","Watergraafsmeer Oost aansl. (NL-1347)","Dijksgracht Westzijde (Amsterdam) (NL-1115)",null,null,null,null,"2022-02-12T01:00:00","01:00:00","2022-02-14T05:00:00","05:00:00",null,"continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-02",".","< >","Watergraafsmeer Oost aansl. (NL-1347)","Dijksgracht Westzijde (Amsterdam) (NL-1115)",null,null,null,null,"2022-01-08T01:00:00","01:00:00","2022-01-10T05:00:00","05:00:00",null,"continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-03",".","< >","Dordrecht (NL-180)","Moerdijkbrug Zuid aansl. (NL-1238)",null,null,null,null,"2022-10-20","00:00:00","2022-11-01T03:00:00","03:00:00",null,"continuous","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-04",".","< >","Dordrecht (NL-180)","Moerdijkbrug Zuid aansl. (NL-1238)",null,null,null,null,"2022-07-10","00:00:00","2022-07-11T05:00:00","05:00:00",null,"continuous","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-05",".","< >","De Diem overloopw. (NL-1101)","Oosterdoksdoorvaart (NL-1259)",null,null,null,null,"2022-10-08T01:00:00","01:00:00","2022-10-10T05:00:00","05:00:00",null,"continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-06",".","< >","Dordrecht (NL-180)","Dordrecht (NL-180)",null,null,null,null,"2022-10-26T08:00:00","08:00:00","2022-10-28T12:00:00","12:00:00",null,"continuous","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-07",".","< >","Dordrecht (NL-180)","Dordrecht (NL-180)",null,null,null,null,"2022-10-28T12:00:00","12:00:00","2022-10-30T15:00:00","15:00:00",null,"continuous","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-08",".","< >","Dordrecht (NL-180)","Dordrecht (NL-180)",null,null,null,null,"2022-10-24T04:00:00","04:00:00","2022-10-26T08:00:00","08:00:00",null,"continuous","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-09",".","< >","Dordrecht (NL-180)","Dordrecht (NL-180)",null,null,null,null,"2022-10-22","00:00:00","2022-10-24T04:00:00","04:00:00",null,"continuous","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-10",".","< >","Dijksgracht Westzijde (Amsterdam) (NL-1115)","Amsterdam Bijlmer ArenA (NL-74)",null,null,null,null,"2022-10-01T01:00:00","01:00:00","2022-10-03T05:00:00","05:00:00",null,"continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-11",".","< >","Dijksgracht Westzijde (Amsterdam) (NL-1115)","Amsterdam Bijlmer ArenA (NL-74)",null,null,null,null,"2022-06-26T01:00:00","01:00:00","2022-06-27T05:00:00","05:00:00",null,"continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-12",".","< >","Dijksgracht Westzijde (Amsterdam) (NL-1115)","Amsterdam Bijlmer ArenA (NL-74)",null,null,null,null,"2022-04-02T01:00:00","01:00:00","2022-04-04T05:00:00","05:00:00",null,"continuous","Miscellaneous",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-13",".","< >","Singelgrachtbrug (NL-1291)","Haarlem (NL-285)",null,null,null,null,"2022-10-18T21:00:00","21:00:00","2022-10-24T05:00:00","05:00:00",null,"continuous","Switch","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-14",".","< >","Singelgracht aansl. (NL-1290)","Halfweg (NL-1153)",null,null,null,null,"2022-04-23T01:00:00","01:00:00","2022-04-25T05:00:00","05:00:00",null,"continuous","Catenary","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-15",".","< >","Singelgracht aansl. (NL-1290)","Haarlem (NL-285)",null,null,null,null,"2022-01-15T01:00:00","01:00:00","2022-01-17T05:00:00","05:00:00",null,"continuous","Catenary","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-16",".","< >","Amsterdam Transformatorweg aansl. (NL-1051)","Amsterdam Westhaven (NL-64)",null,null,null,null,"2022-07-16T05:00:00","05:00:00","2022-07-18T05:00:00","05:00:00",null,"continuous","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-17",".","< >","Amsterdam Westhaven (NL-64)","Amsterdam Westhaven (NL-64)",null,null,null,null,"2022-01-30T05:00:00","05:00:00","2022-01-31T04:50:00","04:50:00",null,"continuous","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-18",".","< >","Dijksgracht Oostzijde (Amsterdam) (NL-1114)","Overbrakerpolder aansl. (NL-1265)",null,null,null,null,"2022-11-05T01:00:00","01:00:00","2022-11-07T05:00:00","05:00:00",null,"continuous","Switch","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-19",".","< >","Dijksgracht Oostzijde (Amsterdam) (NL-1114)","Overbrakerpolder aansl. (NL-1265)",null,null,null,null,"2022-06-25T01:00:00","01:00:00","2022-06-27T05:00:00","05:00:00",null,"continuous","Tunnel","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-20",".","< >","Dijksgracht Oostzijde (Amsterdam) (NL-1114)","Amsterdam Centraal (NL-58)",null,null,null,null,"2022-04-02T01:00:00","01:00:00","2022-04-04T05:00:00","05:00:00",null,"continuous","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-21",".","< >","Abcoude (NL-47)","Breukelen aansluiting (NL-1091)",null,null,null,null,"2022-10-02T01:00:00","01:00:00","2022-10-03T05:00:00","05:00:00",null,"continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-22",".","< >","Amsterdam Centraal (NL-58)","Singelgrachtbrug (NL-1291)",null,null,null,null,"2022-10-23T05:00:00","05:00:00","2022-10-24T04:55:00","04:55:00",null,"continuous","Track and Rail",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-23",".","< >","Amsterdam Centraal (NL-58)","Singelgracht aansl. (NL-1290)",null,null,null,null,"2022-10-09T01:00:00","01:00:00","2022-10-10T05:00:00","05:00:00",null,"continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-24",".","< >","Amsterdam Muiderpoort (NL-60)","Breukelen aansluiting (NL-1091)",null,null,null,null,"2022-10-01T02:00:00","02:00:00","2022-10-03T05:00:00","05:00:00",null,"continuous","Switch","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-25",".","< >","Venserpolder aansl. (NL-1332)","Abcoude overloop (NL-1031)",null,null,null,null,"2022-07-09T01:00:00","01:00:00","2022-07-09T17:00:00","17:00:00",null,"continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-26",".","< >","Abcoude (NL-47)","Maarssen (NL-419)",null,null,null,null,"2022-07-10T01:00:00","01:00:00","2022-07-10T17:00:00","17:00:00",null,"continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-27",".","< >","Amsterdam Westhaven (NL-64)","Amsterdam Westhaven (NL-64)",null,null,null,null,"2022-02-05T01:00:00","01:00:00","2022-02-07T05:00:00","05:00:00",null,"continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-28",".","< >","Utrecht aansl. Maarssen (NL-1313)","Breukelen (NL-133)",null,null,null,null,"2022-10-01T01:00:00","01:00:00","2022-10-03T05:00:00","05:00:00",null,"continuous","Signal",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-29",".","< >","Amsterdam Westhaven (NL-64)","Amsterdam Westhaven (NL-64)",null,null,null,null,"2022-07-08T01:00:00","01:00:00","2022-07-11T05:00:00","05:00:00",null,"continuous","Switch","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-Z906141-2206-30",".","< >","Watergraafsmeer Oost aansl. (NL-1347)","Dijksgracht Westzijde (Amsterdam) (NL-1115)",null,null,null,null,"2022-02-12T01:00:00","01:00:00","2022-02-14T05:00:00","05:00:00",null,"continuous","Switch","T","LT",null,null,null,null,null,null,null,null,null,null,"Y"]
["ProRail","0084-L005077-2201-00",".","< >","Amsterdam Centraal (NL-58)","Singelgracht aansl. (NL-1290)",null,null,null,null,"2022-06-26T05:00:00","05:00:00","2022-06-27T04:55:00","04:55:00",null,"continuous","Switch",null,"LT",null,null,null,null,null,null,null,null,null,null,"Y"]

{"sheet":"Infrabel","index":3,"n_rows":540,"n_cols":31,"rows_kept":540,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["Infrabel","32482","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,11,11,"2021-03-13",44172.010416666664,"2021-03-13",44172.21875,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,32482]
["Infrabel","33292","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2021,2021,19,19,"2021-05-02",44172.270833333336,"2021-05-02",44172.625,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Massification \r\nCTL dimanche \n ",null,null,33292]
["Infrabel","22614","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,23,23,"2021-05-30",44172.03125,"2021-05-30",44172.25,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,22614]
["Infrabel","34839","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,23,23,"2021-05-31",44172.03125,"2021-05-31",44172.208333333336,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,34839]
["Infrabel","21322","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2021,2021,23,23,"2021-06-01",44172.375,"2021-06-01",44172.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 116.150 à Bk 116.180 & renouvellement étanchéité PI - Réglage des contraintes \nHKM A ADAPTER",null,null,21322]
["Infrabel","25357","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,26,26,"2021-06-20",44172.03125,"2021-06-20",44172.25,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,25357]
["Infrabel","29884","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,26,26,"2021-06-20",44172.25,"2021-06-20",44172.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29884]
["Infrabel","34840","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,26,26,"2021-06-21",44172.03125,"2021-06-21",44172.208333333336,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,34840]
["Infrabel","29886","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,27,27,"2021-06-27",44172.25,"2021-06-27",44172.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29886]
["Infrabel","33298","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2021,2021,27,27,"2021-06-27",44172.270833333336,"2021-06-27",44172.625,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Massification \r\nCTL dimanche \n ",null,null,33298]
["Infrabel","29887","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,28,28,"2021-07-04",44172.25,"2021-07-04",44172.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29887]
["Infrabel","29888","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,29,29,"2021-07-11",44172.25,"2021-07-11",44172.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29888]
["Infrabel","29897","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,30,30,"2021-07-18",44172.25,"2021-07-18",44172.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29897]
["Infrabel","29898","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,31,31,"2021-07-25",44172.25,"2021-07-25",44172.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29898]
["Infrabel","29899","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,32,32,"2021-08-01",44172.25,"2021-08-01",44172.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29899]
["Infrabel","29900","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,33,33,"2021-08-08",44172.25,"2021-08-08",44172.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29900]
["Infrabel","19882","Athus - Meuse",">","GEDINNE","PALISEUL",2021,2021,35,35,"2021-08-23",44172.333333333336,"2021-08-23",44172.666666666664,"0d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 4 - asphaltage \n ",null,null,19882]
["Infrabel","19883","Athus - Meuse",">","PALISEUL","GEDINNE",2021,2021,35,35,"2021-08-24",44172.333333333336,"2021-08-24",44172.666666666664,"0d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 4 - asphaltage \n ",null,null,19883]
["Infrabel","25360","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,36,36,"2021-08-29",44172.03125,"2021-08-29",44172.25,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,25360]
["Infrabel","29903","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,36,36,"2021-08-29",44172.25,"2021-08-29",44172.736111111109,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,29903]
["Infrabel","34841","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,36,36,"2021-08-30",44172.03125,"2021-08-30",44172.208333333336,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,34841]
["Infrabel","21328","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,37,37,"2021-09-11",44172.333333333336,"2021-09-11",44172.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 - Bourrage vitesse normale\r\nModification faite des dates à la demande de Mr Hennecart (mail Grignard du 20/02/20) \nHKM A ADAPTER",null,null,21328]
["Infrabel","21329","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,38,38,"2021-09-12",44172.333333333336,"2021-09-12",44172.666666666664,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 - Réglage des contraintes\r\nModification faite des dates à la demande de Mr Hennecart (mail Grignard du 20/02/20) \nHKM A ADAPTER",null,null,21329]
["Infrabel","22619","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,39,39,"2021-09-19",44172.03125,"2021-09-19",44172.25,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,22619]
["Infrabel","34842","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,39,39,"2021-09-20",44172.03125,"2021-09-20",44172.208333333336,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\n(MA-DO Voorbereidende weeknachten weekend1) --> vervangen door 2 weekendnachten\r\n\r\n(MA-DO Voorbereidende weeknachten weekend 2) --> niet mogelijk\r\n(MA-DO Nazorg) --> vervangen door 2 weekendnachten \n ",null,null,34842]
["Infrabel","33293","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2021,2021,40,40,"2021-09-26",44172.270833333336,"2021-09-26",44172.625,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Massification \r\nCTL dimanche \n ",null,null,33293]
["Infrabel","33294","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2021,2021,49,49,"2021-11-28",44172.270833333336,"2021-11-28",44172.625,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Massification \r\nCTL dimanche \n ",null,null,33294]
["Infrabel","43958","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,7,7,"2022-02-06",44172.041666666664,"2022-02-06",44172.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,43958]
["Infrabel","38942","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,8,8,"2022-02-13",44172.041666666664,"2022-02-13",44172.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38942]
["Infrabel","38943","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,9,9,"2022-02-20",44172.041666666664,"2022-02-20",44172.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38943]
["Infrabel","38944","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,10,10,"2022-02-27",44172.041666666664,"2022-02-27",44172.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38944]
["Infrabel","38945","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,11,11,"2022-03-06",44172.041666666664,"2022-03-06",44172.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38945]
["Infrabel","38946","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,12,12,"2022-03-13",44172.041666666664,"2022-03-13",44172.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38946]
["Infrabel","38947","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,13,13,"2022-03-20",44172.041666666664,"2022-03-20",44172.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38947]
["Infrabel","38948","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,14,14,"2022-03-27",44172.041666666664,"2022-03-27",44172.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,38948]
["Infrabel","43959","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,15,15,"2022-04-03",44172.041666666664,"2022-04-03",44172.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,43959]
["Infrabel","43960","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,16,16,"2022-04-10",44172.041666666664,"2022-04-10",44172.75,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"fase I : vernieuwing Engelse Leien \n ",null,null,43960]
["Infrabel","39395","Lille - Antwerpen",">","KORTRIJK","MOUSCRON",2022,2022,23,23,"2022-06-04",44172.583333333336,"2022-06-04",44172.958333333336,"0d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 4 – Pose des tabliers \nFaisceau Mouscron inaccessible",null,null,39395]
["Infrabel","29293","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,37,37,"2022-09-09",44172.333333333336,"2022-09-09",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,29293]
["Infrabel","29949","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,37,37,"2022-09-09",44172.333333333336,"2022-09-09",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,29949]
["Infrabel","35135","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,38,38,"2022-09-16",44172.333333333336,"2022-09-16",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35135]
["Infrabel","35120","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,38,38,"2022-09-16",44172.25,"2022-09-16",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35120]
["Infrabel","44093","Namur - Antwerpen","< >","Y.HOLLAND","Y.DRIEHOEKSTRAAT",2022,2022,38,38,"2022-09-17",44172.041666666664,"2022-09-17",44172.166666666664,"0d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Project Oude Landen \n ",null,null,44093]
["Infrabel","35121","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,39,39,"2022-09-23",44172.333333333336,"2022-09-23",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35121]
["Infrabel","35137","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,39,39,"2022-09-23",44172.333333333336,"2022-09-23",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35137]
["Infrabel","29295","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,41,41,"2022-10-07",44172.333333333336,"2022-10-07",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast\r\nBourrage + tx finitions \n ",null,null,29295]
["Infrabel","30904","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,42,42,"2022-10-14",44172.333333333336,"2022-10-14",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast\r\nBourrage + tx finitions \n ",null,null,30904]
["Infrabel","30905","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,43,43,"2022-10-17",44172.333333333336,"2022-10-17",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast\r\nBourrage + tx finitions \n ",null,null,30905]
["Infrabel","35122","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,43,43,"2022-10-21",44172.333333333336,"2022-10-21",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast\r\nBourrage + tx finitions \n ",null,null,35122]
["Infrabel","35124","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,44,44,"2022-10-24",44172.333333333336,"2022-10-24",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast\r\nBourrage + tx finitions \n ",null,null,35124]
["Infrabel","35125","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,44,44,"2022-10-28",44172.333333333336,"2022-10-28",44172.666666666664,"0d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast\r\nBourrage + tx finitions \n ",null,null,35125]
["Infrabel","27403","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2022,2022,3,17,"2022-01-10",44172.25,"2022-04-22",44172.625,"102d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réalisation d'une dalle en béton armé pour l'étanchéité de la culée-voûte à la bk 8,509 - côté voie B \nA prévoir au saisonnier\r\n+ ART à prendre en considération",null,null,27403]
["Infrabel","20717","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2022,2022,44,46,"2022-10-28",44172.989583333336,"2022-11-07",44172.197916666664,"10d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER CTL : grill coté LLN \r\nachèvement de Y.LLN et MES des voies latérales \r\nAssainissement de plateformess \r\nPose 5 AW\r\nRipage\r\ntvx CAT & sign\r\n\r\n+ Renouvellement de la passerelle BK36.635 à Mont-Saint-Guibert\r\nEntretien des ouvrages du tronçon Ottignie \n ",null,null,20717]
["Infrabel","25727","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,12,13,"2022-03-14",44172.944444444445,"2022-03-25",44172.208333333336,"11d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire Phase 4 : Travaux Voie sur CTL de nuits semaine \n ",null,null,25727]
["Infrabel","38666","Lille - Charleroi","< >","MARCHIENNE-AU-PONT","Y.NORD",2022,2022,16,17,"2022-04-11",44172.979166666664,"2022-04-22",44172.180555555555,"11d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 2bis \n ",null,null,38666]
["Infrabel","28146","Namur - Antwerpen",">","TAMINES","CHATELET-GRIL EST",2022,2022,16,17,"2022-04-11",44172.9375,"2022-04-23",44172.229166666664,"12d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 9 : Semaines de finition Caténaire, E&S et Voie\r\nFinition Caténaire, E&S et Voie en voie 382 / B L130.\r\nSAVU de semaine, les nuits en 22h30/05h30 :\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hor \n ",null,null,28146]
["Infrabel","18079","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,46,48,"2021-11-08",44172.333333333336,"2021-11-21",44172.625,"13d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement de rails \n ",null,null,18079]
["Infrabel","29368","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,43,45,"2022-10-17",44172.989583333336,"2022-10-30",44172.197916666664,"13d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Travaux préparatoires  CTL Grill coté LLN \n ",null,null,29368]
["Infrabel","26987","Athus - Meuse",">","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,31,33,"2021-07-26",44172.958333333336,"2021-08-09",44172.208333333336,"14d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.6 : Pose AS sur VB de L165/2. \n ",null,null,26987]
["Infrabel","30557","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2022,2022,26,29,"2022-06-25",44172.958333333336,"2022-07-10",44172.208333333336,"15d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose seconds tabliers ponts 10 et 11\r\n+ Massification maintenance AI51 \nA déterminer",null,null,30557]
["Infrabel","28909","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,32,35,"2022-08-06",44172.958333333336,"2022-08-21",44172.666666666664,"15d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \n ",null,null,28909]
["Infrabel","29363","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,36,38,"2022-09-01",44172.989583333336,"2022-09-16",44172.197916666664,"15d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Travaux préparatoire Grill coté LLN \n ",null,null,29363]
["Infrabel","19269","Lille - Antwerpen","< >","Y.BETHUNE","KORTRIJK",2021,2021,14,17,"2021-04-03",44172,"2021-04-19",44172.166666666664,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Bouwen van een tunnel (met open sleuf) \n",null,null,19269]
["Infrabel","22322","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,14,17,"2021-04-03",44172,"2021-04-19",44172.166666666664,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Nieuwe ondertunneling Kortrijk. \n ",null,null,22322]
["Infrabel","10281","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2021,2021,43,46,"2021-10-23",44172.208333333336,"2021-11-08",44172.208333333336,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9 \nWE 23-24/10/21 - CTL L124-124A -> détournement via L94-96-28 uniquement possible.\r\nWE 30-31/10/21 – CTL L96 -> Détournement via L124-28/3 ou L75 possible\r\nWE 6-7/11/21 - CTL L96 -> Détournement via L75 uniquement possible",null,null,10281]
["Infrabel","29278","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2022,2022,34,37,"2022-08-20",44172.333333333336,"2022-09-05",44172.25,"16d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses avec train P93\r\nRenouvellement PI\r\n+ Renouvellement PS Rue combattant BK1.100 \n ",null,null,29278]
["Infrabel","21236","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2021,2021,43,46,"2021-10-22",44172.958333333336,"2021-11-08",44172.208333333336,"17d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement As 04AL & 04BL & 09AL & 09BL & 10AL & 10BL \nWE 23-24/10/21 - CTL L124-124A -> détournement via L94-96-28 uniquement possible.\r\nWE 30-31/10/21 – CTL L96 -> Détournement via L124-28/3 ou L75 possible\r\nWE 6-7/11/21 - CTL L96 -> Détournement via L75 uniquement possible",null,null,21236]
["Infrabel","30903","Athus - Meuse",">","VIRTON","AUBANGE",2022,2022,37,40,"2022-09-09",44172.333333333336,"2022-09-26",44172.666666666664,"17d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,30903]
["Infrabel","30908","Athus - Meuse",">","GEDINNE","PALISEUL",2022,2022,37,40,"2022-09-09",44172.333333333336,"2022-09-26",44172.666666666664,"17d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,30908]
["Infrabel","19971","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2021,2021,34,37,"2021-08-18",44172.333333333336,"2021-09-06",44172.243055555555,"19d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Cribleuse L144 entre Bk 0.400 et 13.500 \n ",null,null,19971]
["Infrabel","20451","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2021,2021,24,25,"2021-06-12",44172.027777777781,"2021-06-13",44172.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA + voies tronçon Andenne - Namur (renouvellement de rails suite défaut US entre BK 56500 et BK 58000) \n ",null,null,20451]
["Infrabel","20432","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2021,2021,25,26,"2021-06-19",44172.027777777781,"2021-06-20",44172.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur (renouvellement de quais - renouvellement passerelles - parois rocheuses - ...) \n ",null,null,20432]
["Infrabel","22214","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,26,27,"2021-06-26",44172.958333333336,"2021-06-27",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22214]
["Infrabel","36014","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,26,27,"2021-06-26",44172.958333333336,"2021-06-27",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nP4+ Mini CTL \n ",null,null,36014]
["Infrabel","25139","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,28,28,"2021-07-08",44172.958333333336,"2021-07-09",44172.21875,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Préparation criblage voie A + début démolition quai Franière voie A \n ",null,null,25139]
["Infrabel","25148","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,30,30,"2021-07-22",44172.958333333336,"2021-07-23",44172.21875,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Pistes + contraintes voie A + reconstruction quai Franière voie A \n ",null,null,25148]
["Infrabel","30582","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2021,2021,30,31,"2021-07-24",44172.25,"2021-07-25",44172.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP4+ \n ",null,null,30582]
["Infrabel","26997","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,30,31,"2021-07-24",44172.3125,"2021-07-25",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P4 \r\nZone 3 AI 53 \n ",null,null,26997]
["Infrabel","27237","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,31,32,"2021-07-31",44172.25,"2021-08-01",44172.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51  P4+ \n ",null,null,27237]
["Infrabel","22215","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,32,33,"2021-08-07",44172.958333333336,"2021-08-08",44172.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22215]
["Infrabel","21325","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,32,33,"2021-08-07",44172.958333333336,"2021-08-08",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,21325]
["Infrabel","26988","Athus - Meuse","< >","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,32,33,"2021-08-07",44172.958333333336,"2021-08-08",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.6 : Pose AS sur VB de L165/2. \n ",null,null,26988]
["Infrabel","21326","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,33,34,"2021-08-14",44172.958333333336,"2021-08-15",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,21326]
["Infrabel","19881","Athus - Meuse","< >","BERTRIX","GEDINNE",2021,2021,33,34,"2021-08-14",44172.958333333336,"2021-08-15",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 4 ( double cas nécessaire à la demande de Mr Depierreux)\r\nCTL du samedi 23h au dimanche 15h\r\net du dimanche 23h au lundi 5h \n ",null,null,19881]
["Infrabel","21330","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,34,35,"2021-08-21",44172.958333333336,"2021-08-22",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,21330]
["Infrabel","19885","Athus - Meuse","< >","GEDINNE","BERTRIX",2021,2021,34,35,"2021-08-21",44172.958333333336,"2021-08-22",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 4\r\nCTL du samedi 23h au dimanche 15h\r\net du dimanche 23h au lundi 5h \n ",null,null,19885]
["Infrabel","26416","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,34,35,"2021-08-21",44172.25,"2021-08-22",44172.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52 \n ",null,null,26416]
["Infrabel","21327","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,35,36,"2021-08-28",44172.958333333336,"2021-08-29",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,21327]
["Infrabel","27000","Lille - Charleroi","< >","JURBISE","MONS",2021,2021,36,37,"2021-09-04",44172.25,"2021-09-05",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5.53\r\nMise HS P4 \r\nZone 5 AI 53 \n ",null,null,27000]
["Infrabel","22553","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,37,38,"2021-09-11",44172.96875,"2021-09-12",44172.208333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. \n ",null,null,22553]
["Infrabel","34251","Lille - Charleroi","< >","Y.SOIGNIES","BRAINE-LE-COMTE",2021,2021,37,38,"2021-09-11",44172.270833333336,"2021-09-12",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P4+ \n ",null,null,34251]
["Infrabel","27253","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,37,38,"2021-09-11",44172.222222222219,"2021-09-12",44172.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P4+ \n ",null,null,27253]
["Infrabel","22556","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,38,38,"2021-09-12",44172.96875,"2021-09-13",44172.208333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. \n ",null,null,22556]
["Infrabel","19890","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,38,39,"2021-09-18",44172.958333333336,"2021-09-19",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,19890]
["Infrabel","22557","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,39,39,"2021-09-19",44172.96875,"2021-09-20",44172.208333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. \n ",null,null,22557]
["Infrabel","22216","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,39,40,"2021-09-25",44172.958333333336,"2021-09-26",44172.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22216]
["Infrabel","26879","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,39,40,"2021-09-25",44172.958333333336,"2021-09-26",44172.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nMini CTL \n ",null,null,26879]
["Infrabel","22558","Athus - Meuse","< >","VIRTON","HALANZY",2021,2021,39,40,"2021-09-25",44172.96875,"2021-09-26",44172.208333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L165 Virton - aménagement de la gare :\r\nRenouvellement de l'AW 11S par une nouvelle TAD ;\r\nDépose de la TJD 14AS/13S et pose du nouveau AW 13 à sa position ;\r\nPose de voie entre le nouveau AW 14S et le nouveau AW 13S. \n ",null,null,22558]
["Infrabel","19887","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,39,40,"2021-09-25",44172.25,"2021-09-26",44172.208333333336,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,19887]
["Infrabel","21065","Athus - Meuse","< >","HALANZY","VIRTON",2021,2021,40,41,"2021-10-02",44172.96875,"2021-10-03",44172.208333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement de Virton\r\nBourrage de révision \n ",null,null,21065]
["Infrabel","34254","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,40,41,"2021-10-02",44172.944444444445,"2021-10-03",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P4+ - MINI CTL \n ",null,null,34254]
["Infrabel","20962","Namur - Antwerpen",">","COURT-SAINT-ETIENNE","FAUX",2021,2021,41,42,"2021-10-09",44172.25,"2021-10-10",44172.916666666664,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20962]
["Infrabel","27542","Athus - Meuse","< >","BERTRIX","SAINT-VINCENT-BELLEFONTAINE",2021,2021,42,43,"2021-10-16",44172.958333333336,"2021-10-17",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27542]
["Infrabel","34263","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,42,43,"2021-10-16",44172.944444444445,"2021-10-17",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P4+ \n ",null,null,34263]
["Infrabel","27543","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2021,2021,43,44,"2021-10-23",44172.958333333336,"2021-10-24",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27543]
["Infrabel","20449","Erquelinnes - Montzen","< >","HUY","ANDENNE",2021,2021,43,44,"2021-10-23",44172.027777777781,"2021-10-24",44172.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification : renouvellement de rails suite défaut US entre BK 31400 et BK 32000, ... \n ",null,null,20449]
["Infrabel","29437","Namur - Antwerpen","< >","CHATELET-GRIL EST","CHATELET-GRIL EST",2021,2021,45,46,"2021-11-06",44172.916666666664,"2021-11-07",44172.916666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z17. 51 (P4+)\r\n\r\nMise hors service en une zone (= Zone 17), voici les détails:\r\n- L130 Voie B entre F4-I. 20 et DX-J. 20;\r\nM-I.20 + J-I.20 + PC-I. 20 (faisceau A);\r\n- F6-L. 20 + FX5-I. 20 (L130C en gare de Châtelet);\r\n- GC353-J. 20 + GC354-J \n ",null,null,29437]
["Infrabel","27301","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,45,46,"2021-11-06",44172.291666666664,"2021-11-07",44172.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P4+ \n ",null,null,27301]
["Infrabel","32036","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,45,46,"2021-11-06",44172.25,"2021-11-07",44172.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance  AI 44 (PN + AW) \n ",null,null,32036]
["Infrabel","22217","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,46,47,"2021-11-13",44172.958333333336,"2021-11-14",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22217]
["Infrabel","33882","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,46,47,"2021-11-13",44172.958333333336,"2021-11-14",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nP4+ Mini CTL \n ",null,null,33882]
["Infrabel","27545","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,46,47,"2021-11-13",44172.958333333336,"2021-11-14",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27545]
["Infrabel","31876","Lille - Charleroi","< >","LENS","ATH",2021,2021,46,47,"2021-11-13",44172.25,"2021-11-14",44172.916666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réglage CV Brugelette-ATH \n ",null,null,31876]
["Infrabel","27547","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2021,2021,47,48,"2021-11-20",44172.958333333336,"2021-11-21",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,27547]
["Infrabel","30584","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2021,2021,48,49,"2021-11-27",44172.958333333336,"2021-11-28",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nMini CTL \n ",null,null,30584]
["Infrabel","22218","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2021,2021,49,50,"2021-12-04",44172.958333333336,"2021-12-05",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mini CTL pour maintenance globale L 130 \n ",null,null,22218]
["Infrabel","26880","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2021,2021,49,50,"2021-12-04",44172.958333333336,"2021-12-05",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nP4+ Mini CTL \n ",null,null,26880]
["Infrabel","26423","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,49,50,"2021-12-04",44172.3125,"2021-12-05",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P4+  - Zone 9 AI52 \n ",null,null,26423]
["Infrabel","33773","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,49,50,"2021-12-04",44172.3125,"2021-12-05",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P4 \r\nZone 3 AI 53 \n ",null,null,33773]
["Infrabel","45601","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,6,7,"2022-02-05",44172.958333333336,"2022-02-06",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Straimont \n ",null,null,45601]
["Infrabel","30777","Lille - Charleroi","< >","MONS","QUEVY",2022,2022,7,8,"2022-02-12",44172.003472222219,"2022-02-13",44172.996527777781,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise HS pour finitions chantier P 93 + entreiten \n ",null,null,30777]
["Infrabel","45600","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,8,9,"2022-02-19",44172.958333333336,"2022-02-20",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",null,null,45600]
["Infrabel","30778","Lille - Charleroi","< >","MONS","QUEVY",2022,2022,8,9,"2022-02-19",44172.003472222219,"2022-02-20",44172.996527777781,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise HS pour finitions chantier P 93 + entreiten \n ",null,null,30778]
["Infrabel","44119","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,10,11,"2022-03-05",44172.958333333336,"2022-03-06",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",null,null,44119]
["Infrabel","44115","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,12,13,"2022-03-19",44172.958333333336,"2022-03-20",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Straimont \n ",null,null,44115]
["Infrabel","44116","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,13,14,"2022-03-26",44172.958333333336,"2022-03-27",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Straimont\r\nEn massification avec id 28785 \n ",null,null,44116]
["Infrabel","37623","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2022,2022,13,14,"2022-03-26",44172.25,"2022-03-27",44172.75,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Spanningsregeling, herziening, ...: Vernieuwen wissels Y.Parkbrug\r\nStation Heverlee (B-ST): Vernieuwing perronluifel (Annick Locquet) \n",null,null,37623]
["Infrabel","44901","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,14,15,"2022-04-02",44172.958333333336,"2022-04-03",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,44901]
["Infrabel","44117","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,14,15,"2022-04-02",44172.958333333336,"2022-04-03",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Straimont \n ",null,null,44117]
["Infrabel","40513","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,16,17,"2022-04-16",44172.958333333336,"2022-04-17",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",null,null,40513]
["Infrabel","38951","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,17,17,"2022-04-17",44172,"2022-04-18",44172.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38951]
["Infrabel","44118","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,17,18,"2022-04-23",44172.958333333336,"2022-04-24",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",null,null,44118]
["Infrabel","38952","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,18,18,"2022-04-24",44172,"2022-04-25",44172.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38952]
["Infrabel","40518","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,18,19,"2022-04-30",44172.958333333336,"2022-05-01",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Straimont \nSans impact",null,null,40518]
["Infrabel","33946","Athus - Meuse","< >","HOUYET","BEAURAING",2022,2022,18,19,"2022-04-30",44172.958333333336,"2022-05-01",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing \n ",null,null,33946]
["Infrabel","38953","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,19,19,"2022-05-01",44172,"2022-05-02",44172.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38953]
["Infrabel","40516","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,19,20,"2022-05-07",44172.958333333336,"2022-05-08",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Straimont \n ",null,null,40516]
["Infrabel","38954","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,20,20,"2022-05-08",44172,"2022-05-09",44172.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38954]
["Infrabel","33944","Athus - Meuse","< >","HOUYET","BEAURAING",2022,2022,20,21,"2022-05-14",44172.958333333336,"2022-05-15",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing \n ",null,null,33944]
["Infrabel","38955","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,21,21,"2022-05-15",44172,"2022-05-16",44172.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38955]
["Infrabel","38956","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,22,22,"2022-05-22",44172,"2022-05-23",44172.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38956]
["Infrabel","37805","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,22,23,"2022-05-28",44172.958333333336,"2022-05-29",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",null,null,37805]
["Infrabel","33945","Athus - Meuse","< >","HOUYET","BEAURAING",2022,2022,22,23,"2022-05-28",44172.958333333336,"2022-05-29",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing \n ",null,null,33945]
["Infrabel","38957","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,23,23,"2022-05-29",44172,"2022-05-30",44172.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38957]
["Infrabel","38958","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,24,24,"2022-06-05",44172,"2022-06-06",44172.166666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"fase II : vernieuwing Engelse Leien \n ",null,null,38958]
["Infrabel","40523","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,25,26,"2022-06-18",44172.958333333336,"2022-06-19",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux de finition des nouvelles liaisons de Straimont \n ",null,null,40523]
["Infrabel","39994","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,25,26,"2022-06-18",44172.25,"2022-06-19",44172.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance\r\nP3 Z3. 51 \n ",null,null,39994]
["Infrabel","28896","Athus - Meuse",">","FLORENVILLE","BERTRIX",2022,2022,26,26,"2022-06-20",44172.333333333336,"2022-06-21",44172.666666666664,"1d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28896]
["Infrabel","40525","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,26,27,"2022-06-25",44172.958333333336,"2022-06-26",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux de finition des nouvelles liaisons de Straimont \n ",null,null,40525]
["Infrabel","28899","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2022,2022,26,27,"2022-06-25",44172.958333333336,"2022-06-26",44172.625,"1d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28899]
["Infrabel","45664","Athus - Meuse",">","VIRTON","HALANZY",2022,2022,27,28,"2022-07-02",44172.958333333336,"2022-07-03",44172.625,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",null,null,45664]
["Infrabel","45666","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,27,28,"2022-07-02",44172.958333333336,"2022-07-03",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",null,null,45666]
["Infrabel","45667","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,28,29,"2022-07-09",44172.958333333336,"2022-07-10",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",null,null,45667]
["Infrabel","33931","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,32,33,"2022-08-06",44172.958333333336,"2022-08-07",44172.25,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",null,null,33931]
["Infrabel","45579","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,33,34,"2022-08-13",44172.958333333336,"2022-08-14",44172.25,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",null,null,45579]
["Infrabel","45580","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,34,34,"2022-08-14",44172.958333333336,"2022-08-15",44172.25,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",null,null,45580]
["Infrabel","33932","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,34,35,"2022-08-20",44172.958333333336,"2022-08-21",44172.25,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",null,null,33932]
["Infrabel","30894","Namur - Antwerpen","< >","AUVELAIS","NAMUR",2022,2022,34,35,"2022-08-20",44172.958333333336,"2022-08-21",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre \n ",null,null,30894]
["Infrabel","45581","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,35,36,"2022-08-27",44172.958333333336,"2022-08-28",44172.25,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",null,null,45581]
["Infrabel","29443","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET",2022,2022,35,36,"2022-08-27",44172.25,"2022-08-28",44172.75,"1d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Maintenance Z17. 51 (P4+)\r\n+ Impact faisceaux Chatelet \nFaisceaux B, D, K inaccessibles",null,null,29443]
["Infrabel","45392","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,36,37,"2022-09-03",44172.958333333336,"2022-09-04",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux de finition des nouvelles liaisons de Straimont \n ",null,null,45392]
["Infrabel","39996","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,36,37,"2022-09-03",44172.25,"2022-09-04",44172.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance\r\nP4 Z3.51 \n ",null,null,39996]
["Infrabel","39997","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,37,38,"2022-09-10",44172.25,"2022-09-11",44172.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance P4 Z3.51\r\n+ Entretien des PN + massification maintenance+ travaux ES \n ",null,null,39997]
["Infrabel","45539","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,40,41,"2022-10-01",44172.958333333336,"2022-10-02",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Travaux de finition des nouvelles liaisons de Straimont \n ",null,null,45539]
["Infrabel","33949","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,41,42,"2022-10-08",44172.958333333336,"2022-10-09",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,33949]
["Infrabel","33950","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,42,43,"2022-10-15",44172.958333333336,"2022-10-16",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,33950]
["Infrabel","33951","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,43,44,"2022-10-22",44172.958333333336,"2022-10-23",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,33951]
["Infrabel","33948","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,44,45,"2022-10-29",44172.958333333336,"2022-10-30",44172.666666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,33948]
["Infrabel","28916","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,47,48,"2022-11-19",44172.958333333336,"2022-11-20",44172.541666666664,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,28916]
["Infrabel","41434","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,47,48,"2022-11-19",44172.958333333336,"2022-11-20",44172.625,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Trapèze de Straimont : travaux Signalling (MES) \n ",null,null,41434]
["Infrabel","45386","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,49,50,"2022-12-03",44172.25,"2022-12-04",44172.708333333336,"1d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93\r\nFinitions \n ",null,null,45386]
["Infrabel","36087","Erquelinnes - Montzen",">","BRESSOUX","VISE",2022,2022,37,40,"2022-09-05",44172.291666666664,"2022-09-25",44172.916666666664,"20d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Entretien OA + sécurisation pistes \n ",null,null,36087]
["Infrabel","36089","Erquelinnes - Montzen",">","BRESSOUX","VISE",2022,2022,40,43,"2022-09-26",44172.291666666664,"2022-10-16",44172.916666666664,"20d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Entretien OA \n ",null,null,36089]
["Infrabel","25829","Lille - Charleroi",">","LUTTRE","MARCHIENNE-AU-PONT",2021,2021,41,44,"2021-10-04",44172.979166666664,"2021-10-25",44172.166666666664,"21d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A\r\n- Coupures L124A voie A\r\n- De nuit uniquement. \n ",null,null,25829]
["Infrabel","25831","Lille - Charleroi",">","ROUX","MARCHIENNE-AU-PONT",2021,2021,44,47,"2021-10-25",44172.958333333336,"2021-11-15",44172.25,"21d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L124A \n ",null,null,25831]
["Infrabel","44802","Lille - Charleroi",">","ROUX","Y.NORD",2022,2022,5,8,"2022-01-24",44172.25,"2022-02-14",44172.25,"21d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L. 124A \n ",null,null,44802]
["Infrabel","28915","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,43,47,"2022-10-22",44172.958333333336,"2022-11-14",44172.208333333336,"23d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",null,null,28915]
["Infrabel","21402","Athus - Meuse",">","VONECHE","BEAURAING",2021,2021,39,42,"2021-09-20",44172.333333333336,"2021-10-15",44172.666666666664,"25d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Pose de caniveaux piste\r\nTravail en double prestations \n ",null,null,21402]
["Infrabel","14729","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,12,15,"2022-03-14",44172.979166666664,"2022-04-08",44172.1875,"25d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs P93\r\nPréparations/finitions \n ",null,null,14729]
["Infrabel","27255","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,47,50,"2022-11-14",44172.333333333336,"2022-12-09",44172.333333333336,"25d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement quais de Lustin + mise au gabarit pistes Godinne \n ",null,null,27255]
["Infrabel","27256","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,43,47,"2022-10-17",44172.333333333336,"2022-11-13",44172.333333333336,"27d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement quais de Lustin + sécurisation paroi Godinne \n ",null,null,27256]
["Infrabel","17963","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2021,2021,46,50,"2021-11-08",44172.25,"2021-12-06",44172.208333333336,"28d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"-Renouvellement de traverses,\r\n-Renouvellement des quais de Froyennes\r\n-Renouvellement de chape d’étanchéité\r\n-Renouvellement d’aiguillages\r\n-Renouvellement de rails\r\n-Réalisation de travaux divers aux abords clôture, débroussaillage,… afin de sécuriser \nomleidingen te specifiëren per week",null,null,17963]
["Infrabel","38904","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,18,22,"2022-04-25",44172.923611111109,"2022-05-23",44172.215277777781,"28d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nDémontage Signalisation suite au passage en PLP\r\nTravaux de préparation pour la construction de passerelles au droit du PI 61.597 \n ",null,null,38904]
["Infrabel","23934","Lille - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","Y.NOORD DRIEHOEK LEDEBERG",2021,2021,15,16,"2021-04-10",44172.0625,"2021-04-12",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Werken TUC P198361 - sporen A+B BD \r\nmaken doorsteken - plaatsen en verwijderen T & TS- schakelaars\r\nBDS:\r\nL50E F-S.6 tot AW 72AH vrij en AW 72BH vrij tot EX-S.6\r\nL58 C-C.13 tot AW 01XR vrij en AW 02R vrij tot CX-C.13\r\nL58/1 AW 11O vrij tot AW 03Q vrij  \n",null,null,23934]
["Infrabel","26691","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,18,19,"2021-05-01",44172,"2021-05-03",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Afwerking: Nieuwe ondertunneling Kortrijk. \n ",null,null,26691]
["Infrabel","20180","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,20,21,"2021-05-15",44172.013888888891,"2021-05-17",44172.25,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord \n ",null,null,20180]
["Infrabel","26439","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,20,21,"2021-05-15",44172.013888888891,"2021-05-17",44172.25,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement PN 28\r\nMassifiée avec CTL (id 20180) \n ",null,null,26439]
["Infrabel","26731","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,22,22,"2021-05-26",44172.010416666664,"2021-05-28",44172.177083333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg\r\n(aanvang na Pinksterweekend wegens TLO L59) \n ",null,null,26731]
["Infrabel","30252","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,22,23,"2021-05-29",44172.072916666664,"2021-05-31",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Bundelkop Bundel Luchtbal\r\nWE 1 \n ",null,null,30252]
["Infrabel","18107","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,23,24,"2021-06-05",44172.020833333336,"2021-06-07",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,18107]
["Infrabel","31095","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,23,24,"2021-06-05",44172.013888888891,"2021-06-07",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"In dienst name van Piloot 3 van de inklinking SIW \n ",null,null,31095]
["Infrabel","23133","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,23,24,"2021-06-05",44172.072916666664,"2021-06-07",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nWE 1 TLO \n ",null,null,23133]
["Infrabel","30242","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,23,24,"2021-06-05",44172.072916666664,"2021-06-07",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Bundelkop Bundel Luchtbal\r\nWE 2 TLO \n ",null,null,30242]
["Infrabel","25447","Lille - Charleroi","< >","Y.LENS","ATH",2021,2021,24,25,"2021-06-12",44172.319444444445,"2021-06-14",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise en service de la seconde phase de la L90C BA Brugelette/Ath \n ",null,null,25447]
["Infrabel","36416","Lille - Charleroi","< >","Y.LENS","JURBISE",2021,2021,24,25,"2021-06-12",44172.319444444445,"2021-06-14",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS 49.000\r\nRenforcement culées \n ",null,null,36416]
["Infrabel","25361","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,24,25,"2021-06-12",44172.072916666664,"2021-06-14",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nWE 2 TLO \n ",null,null,25361]
["Infrabel","30244","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,24,25,"2021-06-12",44172.072916666664,"2021-06-14",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Bundelkop Bundel Luchtbal\r\nWE 3 TLO \n ",null,null,30244]
["Infrabel","25131","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2021,2021,26,26,"2021-06-23",44172.958333333336,"2021-06-25",44172.21875,"2d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Préparation Criblage WE 26 - 27 juin\r\nSAVU nuit \n ",null,null,25131]
["Infrabel","18007","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,26,27,"2021-06-26",44172.006944444445,"2021-06-28",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast avec C75:\r\n- en voie B entre 69.500 et 70.390 (900m) \r\n- en voie A entre 67.700 et 68.500 (800m) + entre 70.000 et 70.390 (390m) \nA determiner",null,null,18007]
["Infrabel","18108","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,26,27,"2021-06-26",44172.020833333336,"2021-06-28",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies\r\nA réanalyser suite rencontre EF 12/12/19 : conflit avec CTL L130 \n ",null,null,18108]
["Infrabel","24814","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,27,27,"2021-06-29",44172.010416666664,"2021-07-01",44172.177083333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwerking en  opkuis  ETCS L2+IL P014_07 Waregem Y Zandberg\r\nNacht R4 op R5 niet wegens nachttreinen Werchter \n ",null,null,24814]
["Infrabel","23039","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,27,28,"2021-07-03",44172.006944444445,"2021-07-05",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast avec C75:\r\n- en voie B entre 71.200 et 74.200 (3000m) + quais de Franière Voie B \nA determiner",null,null,23039]
["Infrabel","30994","Lille - Charleroi","< >","ATH","LEUZE",2021,2021,27,28,"2021-07-03",44172.020833333336,"2021-07-05",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 34AF/34BF + 42F \n ",null,null,30994]
["Infrabel","24815","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,28,28,"2021-07-06",44172.010416666664,"2021-07-08",44172.177083333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwerking en  opkuis  ETCS L2+IL P014_07 Waregem Y Zandberg\r\nNacht R4 op R5 niet wegens nachttreinen Werchter \n ",null,null,24815]
["Infrabel","27802","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,28,29,"2021-07-10",44172.006944444445,"2021-07-12",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast avec C75:\r\n- en voie B entre 71.200 et 74.200 (3000m) + quais de Franière Voie B \nA determiner",null,null,27802]
["Infrabel","30995","Lille - Charleroi","< >","ATH","LEUZE",2021,2021,28,29,"2021-07-10",44172.020833333336,"2021-07-12",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 34AF/34BF + 42F \n ",null,null,30995]
["Infrabel","25137","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,29,30,"2021-07-17",44172.006944444445,"2021-07-19",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage ballast voie B entre Bk 66.100 et 68.500 (2400M) \nA determiner",null,null,25137]
["Infrabel","25149","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2021,2021,30,31,"2021-07-24",44172.006944444445,"2021-07-26",44172.208333333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Bourrage révision \nA determiner",null,null,25149]
["Infrabel","23105","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,32,33,"2021-08-07",44172.25,"2021-08-09",44172.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,23105]
["Infrabel","23106","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,33,34,"2021-08-14",44172.25,"2021-08-16",44172.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,23106]
["Infrabel","19880","Athus - Meuse",">","GEDINNE","PALISEUL",2021,2021,33,34,"2021-08-14",44172.25,"2021-08-16",44172.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 4 \n ",null,null,19880]
["Infrabel","22856","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,33,34,"2021-08-14",44172.079861111109,"2021-08-16",44172.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22856]
["Infrabel","23107","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,34,35,"2021-08-21",44172.25,"2021-08-23",44172.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,23107]
["Infrabel","19884","Athus - Meuse",">","BERTRIX","GEDINNE",2021,2021,34,35,"2021-08-21",44172.25,"2021-08-23",44172.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PN 4 \n ",null,null,19884]
["Infrabel","22857","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,34,35,"2021-08-21",44172.079861111109,"2021-08-23",44172.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59\r\nRelatie S32",null,null,22857]
["Infrabel","30151","Namur - Antwerpen",">","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,35,35,"2021-08-23",44172.291666666664,"2021-08-25",44172.958333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réglage des CV pour préparer la MES PLP\r\nEssais de sécurité \n ",null,null,30151]
["Infrabel","23108","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2021,2021,35,36,"2021-08-28",44172.25,"2021-08-30",44172.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Traitement de zone boueuse Bk 94.440 à 94.780 \n ",null,null,23108]
["Infrabel","32690","Lille - Antwerpen","< >","WAREGEM","KORTRIJK",2021,2021,35,36,"2021-08-28",44172.010416666664,"2021-08-30",44172.177083333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen voegen brug Kanaal Bossuit \n ",null,null,32690]
["Infrabel","22848","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,36,37,"2021-09-04",44172.079861111109,"2021-09-06",44172.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22848]
["Infrabel","23135","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,36,37,"2021-09-04",44172.072916666664,"2021-09-06",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nTLO WE 1 \n ",null,null,23135]
["Infrabel","24712","Namur - Antwerpen","< >","ESSEN","SINT-MARIABURG",2021,2021,37,38,"2021-09-11",44172.072916666664,"2021-09-13",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 - Vernieuwing overwegen \r\nTLO WE 1 \n ",null,null,24712]
["Infrabel","32378","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,38,39,"2021-09-18",44172.333333333336,"2021-09-20",44172.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,32378]
["Infrabel","19888","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,40,41,"2021-10-02",44172.25,"2021-10-04",44172.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement AS 30Q \n ",null,null,19888]
["Infrabel","22858","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,40,41,"2021-10-02",44172.079861111109,"2021-10-04",44172.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22858]
["Infrabel","24637","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,40,41,"2021-10-02",44172.079861111109,"2021-10-04",44172.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,24637]
["Infrabel","20055","Athus - Meuse",">","BERTRIX","SAINT-VINCENT-BELLEFONTAINE",2021,2021,42,43,"2021-10-16",44172.333333333336,"2021-10-18",44172.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Pose traverse entre BK92800-93565 P93 \n ",null,null,20055]
["Infrabel","19033","Lille - Charleroi","< >","Y.RUISBROEK","TUBIZE",2021,2021,45,46,"2021-11-06",44172.03125,"2021-11-08",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Overname Halle Fase PLP3.2 \nHKM om te leiden.",null,null,19033]
["Infrabel","31877","Lille - Charleroi","< >","LENS","ATH",2021,2021,47,48,"2021-11-19",44172.993055555555,"2021-11-21",44172.888888888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Mise en service BA Brugelette/Ath \n ",null,null,31877]
["Infrabel","27804","Lille - Antwerpen","< >","DEINZE","WAREGEM",2021,2021,47,48,"2021-11-20",44172.013888888891,"2021-11-22",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"In dienst name van Piloot 3 van de inklinking SIW. Deinze niet bereikbaar vanuit Lichtervelde !! \n ",null,null,27804]
["Infrabel","22864","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2021,2021,52,53,"2021-12-25",44172.079861111109,"2021-12-27",44172.170138888891,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \nOMLEIDING 1: LIJN 12-12/1-FRONTVERANDERING HAVEN ANTWERPEN - 27A\r\nOMLEIDING 2: LIJN 12 - 12/1 - 11 - 10 - 59",null,null,22864]
["Infrabel","28137","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,4,5,"2022-01-22",44172.979166666664,"2022-01-24",44172.201388888891,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire - Phase 2 : Intervention caténaire\r\nCTL de nuit sans impact \n ",null,null,28137]
["Infrabel","38961","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,6,7,"2022-02-05",44172.25,"2022-02-07",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - voorbereidende werken\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) -> L59 bijkomende isolatoren te plaatsen + DOES L52\r\nWerken Kennedytunnel (Sam De Raeve) (kom \n ",null,null,38961]
["Infrabel","38962","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,7,8,"2022-02-12",44172.041666666664,"2022-02-14",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - voorbereidende werken\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) -> L59 nog bijkomende isolatoren te plaatsen\r\nDoes op L52 ( zie andere locaties ) \n ",null,null,38962]
["Infrabel","29978","Athus - Meuse","< >","Y.NEFFE","HOUYET",2022,2022,9,10,"2022-02-26",44172.25,"2022-02-28",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses à la grue dans 3 tunnels entre BK 8900 et 12100 \n ",null,null,29978]
["Infrabel","44164","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2022,2022,9,10,"2022-02-26",44172.25,"2022-02-28",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réserve maintenance \n",null,null,44164]
["Infrabel","30906","Athus - Meuse","< >","Y.NEFFE","HOUYET",2022,2022,10,11,"2022-03-05",44172.25,"2022-03-07",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses à la grue dans 3 tunnels entre BK 8900 et 12100 \n ",null,null,30906]
["Infrabel","28760","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,11,12,"2022-03-12",44172.25,"2022-03-14",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28760]
["Infrabel","30907","Athus - Meuse","< >","Y.NEFFE","HOUYET",2022,2022,11,12,"2022-03-12",44172.25,"2022-03-14",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de boueux et entretiens d'appareils de voies (bourrage, nivellement,...) \n ",null,null,30907]
["Infrabel","28762","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,12,13,"2022-03-19",44172.25,"2022-03-21",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780\r\nIncompatible avec travaux Marchienne-au-Pont \n ",null,null,28762]
["Infrabel","38967","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,12,13,"2022-03-19",44172.25,"2022-03-21",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - afwerking\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) +\r\nDoes L52 \n ",null,null,38967]
["Infrabel","37678","Namur - Antwerpen","< >","EKEREN","ESSEN",2022,2022,12,13,"2022-03-19",44172.041666666664,"2022-03-21",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen\r\nIn combinatie met TLO lijn 35. Zo gepland wegens lijn 12 niet verenigbaar met langdurige TLO op lijn 24 Duitse net (vervangen brug).",null,null,37678]
["Infrabel","14725","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,12,13,"2022-03-19",44172.034722222219,"2022-03-21",44172.173611111109,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs L 96 avec P93 \n ",null,null,14725]
["Infrabel","28785","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,13,14,"2022-03-26",44172.25,"2022-03-28",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28785]
["Infrabel","38963","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,13,14,"2022-03-26",44172.25,"2022-03-28",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - voorbereidende werken\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) -> L59 bijkomende isolatoren te plaatsen\r\nDoes L52 \n ",null,null,38963]
["Infrabel","37679","Namur - Antwerpen","< >","EKEREN","ESSEN",2022,2022,13,14,"2022-03-26",44172.041666666664,"2022-03-28",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen\r\nIn combinatie met TLO lijn 35. Zo gepland wegens lijn 12 niet verenigbaar met langdurige TLO op lijn 24 Duitse net (vervangen brug).",null,null,37679]
["Infrabel","14726","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,13,14,"2022-03-26",44172.034722222219,"2022-03-28",44172.173611111109,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs L 96 avec P93\r\n + Maintenance Z.5.53\r\nMise HS en P4 \n ",null,null,14726]
["Infrabel","30303","Namur - Antwerpen","< >","EKEREN","ESSEN",2022,2022,14,15,"2022-04-02",44172.041666666664,"2022-04-04",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30303]
["Infrabel","14727","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,14,15,"2022-04-02",44172.034722222219,"2022-04-04",44172.173611111109,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des traverses Bi-blocs P93\r\nContraintes\r\n+ Maintenance Z.5.53\r\nMise HS en P4 \n ",null,null,14727]
["Infrabel","28794","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,15,16,"2022-04-09",44172.25,"2022-04-11",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 94.440 à Bk 94.780 \n ",null,null,28794]
["Infrabel","30306","Namur - Antwerpen","< >","EKEREN","ESSEN",2022,2022,17,18,"2022-04-23",44172.041666666664,"2022-04-25",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30306]
["Infrabel","30793","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,18,19,"2022-04-30",44172.020833333336,"2022-05-02",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 3 - WE 1/4 \n ",null,null,30793]
["Infrabel","41301","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,18,19,"2022-04-30",44172.25,"2022-05-02",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - renouvellement\r\n+ 385335 PLP \n ",null,null,41301]
["Infrabel","30308","Namur - Antwerpen","< >","EKEREN","ESSEN",2022,2022,18,19,"2022-04-30",44172.041666666664,"2022-05-02",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30308]
["Infrabel","39107","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,19,20,"2022-05-07",44172.020833333336,"2022-05-09",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 3 - WE 2/4 \n ",null,null,39107]
["Infrabel","37677","Namur - Antwerpen","< >","EKEREN","ESSEN",2022,2022,19,20,"2022-05-07",44172.041666666664,"2022-05-09",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,37677]
["Infrabel","39310","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,20,21,"2022-05-14",44172.958333333336,"2022-05-16",44172.208333333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 3 – Pose des Piles \n ",null,null,39310]
["Infrabel","39108","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,20,21,"2022-05-14",44172.020833333336,"2022-05-16",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 3 - WE 3/4 \n ",null,null,39108]
["Infrabel","28105","Lille - Charleroi","< >","LUTTRE","Y.LA SAMBRE",2022,2022,20,21,"2022-05-14",44172.583333333336,"2022-05-16",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réélectrification L. 124+L. 124A \r\nWeekend en CTL 4 voies en continu \n ",null,null,28105]
["Infrabel","39311","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,21,22,"2022-05-21",44172.958333333336,"2022-05-23",44172.208333333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 3 – Pose des Piles \n ",null,null,39311]
["Infrabel","39109","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,21,22,"2022-05-21",44172.020833333336,"2022-05-23",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 3 - WE 4/4 \n ",null,null,39109]
["Infrabel","39397","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,23,24,"2022-06-04",44172.958333333336,"2022-06-06",44172.208333333336,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 4 – Pose des tabliers \n ",null,null,39397]
["Infrabel","39113","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,24,25,"2022-06-11",44172.020833333336,"2022-06-13",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 4 - WE 1/5 \nA détourner",null,null,39113]
["Infrabel","28811","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,24,25,"2022-06-11",44172.25,"2022-06-13",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28811]
["Infrabel","44163","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2022,2022,24,25,"2022-06-11",44172.25,"2022-06-13",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réserve maintenance \n",null,null,44163]
["Infrabel","39023","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,24,25,"2022-06-11",44172.25,"2022-06-13",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nDétournement via L130A",null,null,39023]
["Infrabel","39114","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,25,26,"2022-06-18",44172.020833333336,"2022-06-20",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 4 - WE 2/5 \nA détourner",null,null,39114]
["Infrabel","28895","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,25,26,"2022-06-18",44172.25,"2022-06-20",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",null,null,28895]
["Infrabel","39954","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,25,26,"2022-06-18",44172.25,"2022-06-20",44172.208333333336,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"PN123 - renouvellement\r\n+ 385335 PLP \n ",null,null,39954]
["Infrabel","29298","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,25,26,"2022-06-18",44172.25,"2022-06-20",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nDétournement via L130A",null,null,29298]
["Infrabel","39115","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,26,27,"2022-06-25",44172.020833333336,"2022-06-27",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 4 - WE 3/5 \nA détourner",null,null,39115]
["Infrabel","39116","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,27,28,"2022-07-02",44172.020833333336,"2022-07-04",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 4 - WE 4/5 \nA détourner",null,null,39116]
["Infrabel","30901","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,27,28,"2022-07-02",44172.25,"2022-07-04",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,30901]
["Infrabel","45668","Athus - Meuse",">","VIRTON","HALANZY",2022,2022,28,29,"2022-07-09",44172.958333333336,"2022-07-11",44172.625,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",null,null,45668]
["Infrabel","39110","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,28,29,"2022-07-09",44172.020833333336,"2022-07-11",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Marchienne-au-Pont - Phase 4 - WE 5/5 \nA détourner",null,null,39110]
["Infrabel","30902","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,28,29,"2022-07-09",44172.25,"2022-07-11",44172.180555555555,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,30902]
["Infrabel","31902","Namur - Antwerpen","< >","Y.HOLLAND","Y.DRIEHOEKSTRAAT",2022,2022,34,34,"2022-08-14",44172.041666666664,"2022-08-16",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Project Oude Landen \n ",null,null,31902]
["Infrabel","44162","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2022,2022,34,35,"2022-08-20",44172.25,"2022-08-22",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réserve maintenance\r\n(in combinatie met TLO Sittard - Roermand, besproken op trilaterale) \n",null,null,44162]
["Infrabel","28910","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,35,36,"2022-08-27",44172.958333333336,"2022-08-29",44172.208333333336,"2d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",null,null,28910]
["Infrabel","35126","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,37,38,"2022-09-10",44172.25,"2022-09-12",44172.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35126]
["Infrabel","35134","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,37,38,"2022-09-10",44172.25,"2022-09-12",44172.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35134]
["Infrabel","35127","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,38,39,"2022-09-17",44172.25,"2022-09-19",44172.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35127]
["Infrabel","35136","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,38,39,"2022-09-17",44172.25,"2022-09-19",44172.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35136]
["Infrabel","35128","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,39,40,"2022-09-24",44172.25,"2022-09-26",44172.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast \n ",null,null,35128]
["Infrabel","35138","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,39,40,"2022-09-24",44172.25,"2022-09-26",44172.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35138]
["Infrabel","22850","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,40,41,"2022-10-01",44172.041666666664,"2022-10-03",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",null,null,22850]
["Infrabel","30318","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,40,41,"2022-10-01",44172.041666666664,"2022-10-03",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30318]
["Infrabel","35130","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,41,42,"2022-10-08",44172.25,"2022-10-10",44172.666666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast\r\nBourrage + tx finitions \n ",null,null,35130]
["Infrabel","30311","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,41,42,"2022-10-08",44172.041666666664,"2022-10-10",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30311]
["Infrabel","30563","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,41,42,"2022-10-08",44172.041666666664,"2022-10-10",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",null,null,30563]
["Infrabel","29953","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,41,42,"2022-10-08",44172.583333333336,"2022-10-10",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,29953]
["Infrabel","30315","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,42,43,"2022-10-15",44172.041666666664,"2022-10-17",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30315]
["Infrabel","35131","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,42,43,"2022-10-15",44172.583333333336,"2022-10-17",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast\r\nBourrage + tx finitions \n ",null,null,35131]
["Infrabel","29955","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,42,43,"2022-10-15",44172.583333333336,"2022-10-17",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,29955]
["Infrabel","41868","Lille - Antwerpen","< >","DE PINTE","Y.ZANDBERG",2022,2022,43,44,"2022-10-22",44172.25,"2022-10-24",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"CoLT 41868 An Van Den Abeele - Indienstname SIW in Deinze(I-Build ETCS)  - Waregem\r\nCoLT 42137 Eric Denolin - ETCS L2-IL_NW_P014_05_L75_Deinze - Waregem_IL\r\nCoLT 42130 Eric Denolin - ETCS L2-IL_NW_P014_04_L75_Deinze_IL\r\nCoLT 41866 Dieter Opsomer - Onder \n ",null,null,41868]
["Infrabel","30312","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,43,44,"2022-10-22",44172.041666666664,"2022-10-24",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30312]
["Infrabel","30564","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,43,44,"2022-10-22",44172.041666666664,"2022-10-24",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",null,null,30564]
["Infrabel","35132","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,43,44,"2022-10-22",44172.583333333336,"2022-10-24",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast\r\nBourrage + tx finitions \n ",null,null,35132]
["Infrabel","35139","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,43,44,"2022-10-22",44172.583333333336,"2022-10-24",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Assainissement de la voie A \n ",null,null,35139]
["Infrabel","41346","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,44,45,"2022-10-29",44172.25,"2022-10-31",44172.215277777781,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93\r\nFinitions \n ",null,null,41346]
["Infrabel","30313","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,44,45,"2022-10-29",44172.041666666664,"2022-10-31",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30313]
["Infrabel","30565","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,44,45,"2022-10-29",44172.041666666664,"2022-10-31",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",null,null,30565]
["Infrabel","29276","Athus - Meuse","< >","Y.NEFFE","BEAURAING",2022,2022,44,45,"2022-10-29",44172.583333333336,"2022-10-31",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Traitement de boueux et entretiens d'appareils de voies (bourrage, nivellement,...) \n ",null,null,29276]
["Infrabel","35133","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,44,45,"2022-10-29",44172.583333333336,"2022-10-31",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast\r\nBourrage + tx finitions \n ",null,null,35133]
["Infrabel","40685","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,45,45,"2022-11-03",44172.083333333336,"2022-11-05",44172.125,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,40685]
["Infrabel","41869","Lille - Antwerpen","< >","DE PINTE","Y.ZANDBERG",2022,2022,45,46,"2022-11-05",44172.25,"2022-11-07",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"CoLT 41869 An Van Den Abeele - Indienstname SIW in Deinze(I-Build ETCS)  - Waregem \r\nCoLT 42138 Eric Denolin - ETCS L2-IL_NW_P014_05_L75_Deinze - Waregem_IL\r\nCoLT 42131 Eric Denolin - ETCS L2-IL_NW_P014_04_L75_Deinze_IL \n ",null,null,41869]
["Infrabel","30314","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,45,46,"2022-11-05",44172.041666666664,"2022-11-07",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30314]
["Infrabel","30566","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,45,46,"2022-11-05",44172.041666666664,"2022-11-07",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",null,null,30566]
["Infrabel","45146","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,46,47,"2022-11-12",44172.951388888891,"2022-11-14",44172.1875,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45146]
["Infrabel","45385","Namur - Antwerpen","< >","TILLY","FLEURUS",2022,2022,47,48,"2022-11-19",44172.958333333336,"2022-11-21",44172.166666666664,"2d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Nuits pour travaux de finitions Rnvlt du Tablier métallique situé Bk 47.290 \n ",null,null,45385]
["Infrabel","44160","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2022,2022,47,48,"2022-11-19",44172.25,"2022-11-21",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Réserve maintenance\r\n(in combinatie met TLO Sittard - Maastricht, besproken op trilaterale) \n",null,null,44160]
["Infrabel","30316","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,48,49,"2022-11-26",44172.041666666664,"2022-11-28",44172.1875,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30316]
["Infrabel","30568","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,48,49,"2022-11-26",44172.041666666664,"2022-11-28",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",null,null,30568]
["Infrabel","30317","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,49,50,"2022-12-03",44172.041666666664,"2022-12-05",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout \nVia Montzen",null,null,30317]
["Infrabel","30569","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,49,50,"2022-12-03",44172.041666666664,"2022-12-05",44172.166666666664,"2d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",null,null,30569]
["Infrabel","26726","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,19,19,"2021-05-04",44172.010416666664,"2021-05-07",44172.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,26726]
["Infrabel","20690","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2021,2021,20,21,"2021-05-14",44172.993055555555,"2021-05-17",44172.197916666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"CTL RER \n ",null,null,20690]
["Infrabel","21155","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2021,2021,22,23,"2021-05-28",44172.965277777781,"2021-05-31",44172.236111111109,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS \n ",null,null,21155]
["Infrabel","26729","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,23,23,"2021-06-01",44172.010416666664,"2021-06-04",44172.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,26729]
["Infrabel","22232","Athus - Meuse","< >","AUBANGE-GRIL E","AUBANGE-FRONTIERE-FRANCE",2021,2021,23,24,"2021-06-04",44172.958333333336,"2021-06-07",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Terminal Athus - Phase 5.5 : électrification L165/2 \n ",null,null,22232]
["Infrabel","20190","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2021,2021,23,24,"2021-06-04",44172.965277777781,"2021-06-07",44172.236111111109,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme) \r\nRenouvellement PN 35 - 37\r\nRenouvellement des AS de Amay - 01AS, 01BS, 02AS, 02BS \n ",null,null,20190]
["Infrabel","26740","Lille - Antwerpen","< >","WAREGEM","Y.ZANDBERG",2021,2021,24,24,"2021-06-08",44172.010416666664,"2021-06-11",44172.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"graven grachten en of plaatsen sleuven ETCS L2+IL P014_07 Waregem Y Zandberg \n ",null,null,26740]
["Infrabel","23980","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE-WIJKSPOREN",2021,2021,25,25,"2021-06-15",44172.010416666664,"2021-06-18",44172.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"aanleg kabel: ETCS L2+IL P014b_01 Gent-Sint Pieters - De Pinte \n ",null,null,23980]
["Infrabel","21036","Lille - Charleroi","< >","ATH","LEUZE",2021,2021,25,26,"2021-06-18",44172.979166666664,"2021-06-21",44172.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 34AF/34BF + 42F \n ",null,null,21036]
["Infrabel","25138","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,28,28,"2021-07-05",44172.958333333336,"2021-07-08",44172.21875,"3d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"pistes + contraintes Voie B + reconstruction quai Franière Voie B \n ",null,null,25138]
["Infrabel","33995","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2021,2021,28,28,"2021-07-06",44172.010416666664,"2021-07-09",44172.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"onderhoud \n ",null,null,33995]
["Infrabel","25146","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,30,30,"2021-07-19",44172.958333333336,"2021-07-22",44172.21875,"3d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"pistes + contraintes Voie B + reconstruction quai Franière Voie B \n ",null,null,25146]
["Infrabel","36274","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE-WIJKSPOREN",2021,2021,34,34,"2021-08-17",44172.010416666664,"2021-08-20",44172.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud sporen en wissels. \n ",null,null,36274]
["Infrabel","23489","Lille - Antwerpen","< >","Y.BETHUNE","LAUWE",2021,2021,34,35,"2021-08-20",44172.979166666664,"2021-08-23",44172.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Sanering thv ex stopplaats Lauwe \n ",null,null,23489]
["Infrabel","19872","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,34,35,"2021-08-20",44172.875,"2021-08-23",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \nDétournement via L130A",null,null,19872]
["Infrabel","30152","Namur - Antwerpen",">","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,35,35,"2021-08-25",44172.958333333336,"2021-08-28",44172.958333333336,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réglage des CV pour préparer la MES PLP\r\nEssais de sécurité \r\nPas d'autres services dans la coupure \n ",null,null,30152]
["Infrabel","36405","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,35,36,"2021-08-27",44172.875,"2021-08-30",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \nDétournement via L130A",null,null,36405]
["Infrabel","31395","Namur - Antwerpen","< >","AISEAU","FARCIENNES",2021,2021,40,41,"2021-10-01",44172.958333333336,"2021-10-04",44172.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31395]
["Infrabel","20268","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2021,2021,40,41,"2021-10-01",44172.979166666664,"2021-10-04",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Démolition PS Norbert Ponlot \n ",null,null,20268]
["Infrabel","18104","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,40,41,"2021-10-01",44172.9375,"2021-10-04",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy \n ",null,null,18104]
["Infrabel","30147","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,41,42,"2021-10-08",44172.958333333336,"2021-10-11",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Reprise en EBP-PLP des installations de Tamines et Auvelais.\r\nPas d'autres services dans la coupure (sauf train d'essais ES et ETCS). \n ",null,null,30147]
["Infrabel","20391","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2021,2021,41,42,"2021-10-08",44172.979166666664,"2021-10-11",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Démolition PS Norbert Ponlot \n ",null,null,20391]
["Infrabel","18105","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,41,42,"2021-10-08",44172.9375,"2021-10-11",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy \n ",null,null,18105]
["Infrabel","30150","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","CHATELET-GRIL EST",2021,2021,42,43,"2021-10-15",44172.958333333336,"2021-10-18",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Reprise en EBP-PLP des installations de Tamines et Auvelais.\r\nPas d'autres services dans la coupure (sauf train d'essais ES et ETCS). \n ",null,null,30150]
["Infrabel","22733","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2021,2021,44,45,"2021-10-29",44172.996527777781,"2021-11-01",44172.159722222219,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"TLO-wknds : zondagen voorbereidende werken voor de weekend TLO's:\r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor \n ",null,null,22733]
["Infrabel","30583","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2021,2021,45,45,"2021-11-02",44172.993055555555,"2021-11-05",44172.208333333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP3HKM \n ",null,null,30583]
["Infrabel","31396","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,45,45,"2021-11-02",44172.993055555555,"2021-11-05",44172.208333333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31396]
["Infrabel","31845","Lille - Charleroi","< >","BRUGELETTE","MEVERGNIES-ATTRE",2021,2021,46,47,"2021-11-12",44172.895833333336,"2021-11-15",44172.229166666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"CTL pour renouvellement complet de l'Aqueduc BK 59.050 \n ",null,null,31845]
["Infrabel","36273","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE-WIJKSPOREN",2021,2021,51,51,"2021-12-14",44172.010416666664,"2021-12-17",44172.177083333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud sporen en wissels. \n ",null,null,36273]
["Infrabel","30891","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,11,12,"2022-03-11",44172.979166666664,"2022-03-14",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36\r\n+ Renouvellement des quais VA de Florival\r\nElargissement des pistes de circulation et pose de passerelles \n ",null,null,30891]
["Infrabel","30892","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,13,14,"2022-03-25",44172.979166666664,"2022-03-28",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36\r\n+ Renouvellement des quais VA de Florival\r\nElargissement des pistes de circulation et pose de passerelles \n ",null,null,30892]
["Infrabel","25730","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,13,14,"2022-03-25",44172.979166666664,"2022-03-28",44172.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire Phase 5 : Week-end n°1\r\nPose nouveau 64BJ en site propre + voies L130vB.\r\nVB + VA L130 entre les signaux DX-J.20 + J2-M.20 + D-J. 20 et JX1-M. 20 (en une zone de mise HS).\r\nMise hors tension cas 27442, 27440, 27438,27436, 27443 \n ",null,null,25730]
["Infrabel","30781","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,14,15,"2022-04-01",44172.979166666664,"2022-04-04",44172.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 7 : Week-end n°2\r\nMise en place de la voie B / L130 et renouvellement.\r\nCTL WE n°2, du vendredi 25/03/2022 à 22h30 en continu jusqu’au lundi 28/03/2022 à 05h :\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ. \n ",null,null,30781]
["Infrabel","20723","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2022,2022,16,17,"2022-04-15",44172.979166666664,"2022-04-18",44172.243055555555,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"RER Weekend Paques \n ",null,null,20723]
["Infrabel","30305","Namur - Antwerpen","< >","EKEREN","ESSEN",2022,2022,16,17,"2022-04-16",44172.041666666664,"2022-04-19",44172.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\n\r\n+ Paasmaandag \nVia Montzen",null,null,30305]
["Infrabel","39944","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,17,17,"2022-04-19",44172.958333333336,"2022-04-22",44172.208333333336,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - nuits préparation \n ",null,null,39944]
["Infrabel","39947","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,17,18,"2022-04-22",44172.958333333336,"2022-04-25",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - renouvellement\r\n+ 385335 PLP \n ",null,null,39947]
["Infrabel","29026","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,18,19,"2022-04-29",44172.944444444445,"2022-05-02",44172.222222222219,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \n",null,null,29026]
["Infrabel","29920","Erquelinnes - Montzen","< >","STATTE","JAVA",2022,2022,18,19,"2022-04-29",44172.993055555555,"2022-05-02",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte \n ",null,null,29920]
["Infrabel","30861","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,18,19,"2022-04-29",44172.923611111109,"2022-05-02",44172.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,30861]
["Infrabel","30913","Erquelinnes - Montzen","< >","STATTE","JAVA",2022,2022,19,20,"2022-05-06",44172.993055555555,"2022-05-09",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte \n ",null,null,30913]
["Infrabel","30860","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,19,20,"2022-05-06",44172.923611111109,"2022-05-09",44172.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,30860]
["Infrabel","30859","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,20,21,"2022-05-13",44172.923611111109,"2022-05-16",44172.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nTravaux de renouvellement des chapes d'étanchéité des PI 61.597 et 64.126 + construction de passerelles au droit du PI 61.597 \n ",null,null,30859]
["Infrabel","43616","Lille - Charleroi","< >","LOT","HALLE",2022,2022,21,21,"2022-05-17",44172.083333333336,"2022-05-20",44172.125,"3d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,43616]
["Infrabel","30858","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,21,22,"2022-05-20",44172.923611111109,"2022-05-23",44172.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,30858]
["Infrabel","21040","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,22,23,"2022-05-27",44172.923611111109,"2022-05-30",44172.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \n ",null,null,21040]
["Infrabel","28769","Lille - Charleroi","< >","LEUZE","TOURNAI",2022,2022,23,24,"2022-06-03",44172.996527777781,"2022-06-06",44172.194444444445,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 76 \n ",null,null,28769]
["Infrabel","41865","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2022,2022,23,24,"2022-06-04",44172.006944444445,"2022-06-07",44172.173611111109,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"CoLT 41865: Dieter Opsomer- Onderhoud (Deinze-Kortrijk) *pinkstermaandag inbegrepen \n ",null,null,41865]
["Infrabel","38488","Athus - Meuse","< >","BERTRIX","HALANZY",2022,2022,23,24,"2022-06-04",44172.25,"2022-06-07",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Pose des nouveaux trapezes de Signeulx et Straimont \n ",null,null,38488]
["Infrabel","41717","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,23,24,"2022-06-04",44172.25,"2022-06-07",44172.180555555555,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nDétournement via L130A",null,null,41717]
["Infrabel","39024","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,24,25,"2022-06-10",44172.979166666664,"2022-06-13",44172.666666666664,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",null,null,39024]
["Infrabel","39022","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,25,26,"2022-06-17",44172.979166666664,"2022-06-20",44172.666666666664,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",null,null,39022]
["Infrabel","39026","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,27,28,"2022-07-01",44172.979166666664,"2022-07-04",44172.666666666664,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",null,null,39026]
["Infrabel","39027","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,28,29,"2022-07-08",44172.979166666664,"2022-07-11",44172.666666666664,"3d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",null,null,39027]
["Infrabel","29749","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER-GARAGE",2022,2022,32,33,"2022-08-05",44172.979166666664,"2022-08-08",44172.1875,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre \nHKM détourné via :\r\n- Athus-Meuse - L161\r\n- L144 - L130 - L130A",null,null,29749]
["Infrabel","27248","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,37,38,"2022-09-09",44172.958333333336,"2022-09-12",44172.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD \n ",null,null,27248]
["Infrabel","41340","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,37,38,"2022-09-09",44172.923611111109,"2022-09-12",44172.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 \n ",null,null,41340]
["Infrabel","30915","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,38,39,"2022-09-16",44172.958333333336,"2022-09-19",44172.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD \n ",null,null,30915]
["Infrabel","30866","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,38,39,"2022-09-16",44172.923611111109,"2022-09-19",44172.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 \n ",null,null,30866]
["Infrabel","30916","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,39,40,"2022-09-23",44172.958333333336,"2022-09-26",44172.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD \n ",null,null,30916]
["Infrabel","41341","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,39,40,"2022-09-23",44172.923611111109,"2022-09-26",44172.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 \n ",null,null,41341]
["Infrabel","41342","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,40,41,"2022-09-30",44172.923611111109,"2022-10-03",44172.215277777781,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement de traverses entre Ath et Lens P93 \n ",null,null,41342]
["Infrabel","28779","Lille - Charleroi","< >","FROYENNES","BLANDAIN-FRONTIERE",2022,2022,41,42,"2022-10-07",44172.958333333336,"2022-10-10",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 2 - 8 - 10 \n ",null,null,28779]
["Infrabel","38892","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,41,42,"2022-10-07",44172.979166666664,"2022-10-10",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 1/4 \n ",null,null,38892]
["Infrabel","38901","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,42,43,"2022-10-14",44172.979166666664,"2022-10-17",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 2/4 \n ",null,null,38901]
["Infrabel","17166","Namur - Antwerpen","< >","TILLY","FLEURUS",2022,2022,43,44,"2022-10-21",44172.958333333336,"2022-10-24",44172.166666666664,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du Tablier métallique situé Bk 47.290 \n ",null,null,17166]
["Infrabel","38902","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,44,45,"2022-10-28",44172.979166666664,"2022-10-31",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 3/4 \n ",null,null,38902]
["Infrabel","41319","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,45,46,"2022-11-04",44172.958333333336,"2022-11-07",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - renouvellement \n ",null,null,41319]
["Infrabel","38903","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,45,46,"2022-11-04",44172.979166666664,"2022-11-07",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 4/4 \n ",null,null,38903]
["Infrabel","41320","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,46,47,"2022-11-11",44172.25,"2022-11-14",44172.208333333336,"3d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"P93 - renouvellement \n ",null,null,41320]
["Infrabel","25715","Namur - Antwerpen",">","TAMINES","CHATELET-GRIL EST",2022,2022,6,11,"2022-01-31",44172.9375,"2022-03-12",44172.229166666664,"40d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire - Phase 3 \n ",null,null,25715]
["Infrabel","27245","Athus - Meuse",">","HOUYET","BEAURAING",2022,2022,18,24,"2022-04-25",44172.333333333336,"2022-06-05",44172.75,"41d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing \n ",null,null,27245]
["Infrabel","18076","Athus - Meuse",">","PALISEUL","BERTRIX",2021,2021,20,26,"2021-05-10",44172.333333333336,"2021-06-25",44172.666666666664,"46d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Assainissement à la grue (71410-72140)\r\nCas 26441 reste sous tension pour utilisation de la liaison 02BQ/02AQ \n ",null,null,18076]
["Infrabel","30999","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,11,11,"2021-03-08",44172.958333333336,"2021-03-12",44172.166666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Voorbereiding: Nieuwe ondertunneling Kortrijk. \nL75, richting Moeskroen, DOES via sp B L75C.\r\nL50A/BRUGGE/66/66-1",null,null,30999]
["Infrabel","31000","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,21,21,"2021-05-18",44172.020833333336,"2021-05-22",44172.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwwerking Nieuwe ondertunneling Kortrijk. \n ",null,null,31000]
["Infrabel","20182","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2021,2021,22,22,"2021-05-24",44172.916666666664,"2021-05-28",44172.25,"4d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Dépose caténaire voie 553 \n ",null,null,20182]
["Infrabel","31001","Lille - Antwerpen","< >","KORTRIJK","Y.BETHUNE",2021,2021,22,22,"2021-05-24",44172.993055555555,"2021-05-28",44172.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"afwwerking Nieuwe ondertunneling Kortrijk. \n ",null,null,31001]
["Infrabel","18109","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,23,23,"2021-06-01",44172.020833333336,"2021-06-05",44172.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies\r\nUPM 181991 \nHKM à adapter L117 - L124A - 124A/1 - 130A",null,null,18109]
["Infrabel","22209","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2021,2021,24,24,"2021-06-07",44172.965277777781,"2021-06-11",44172.236111111109,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 01AU/01BU/02U à Flémalle_Haute (avec plateforme), suite phase 2\r\ntravaux divers en voie A (bourrage de révision, réglage des contraintes, retrait ART, toilette de la voie...) \n ",null,null,22209]
["Infrabel","27796","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,24,24,"2021-06-08",44172.020833333336,"2021-06-12",44172.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,27796]
["Infrabel","18093","Lille - Charleroi","< >","NEUFVILLES","MASNUY-SAINT-PIERRE",2021,2021,24,24,"2021-06-08",44172.020833333336,"2021-06-12",44172.177083333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL de nuit étendues. Rejointoiement et réfection de maçonnerie en voûte (PS 42.540) \n ",null,null,18093]
["Infrabel","34248","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,24,24,"2021-06-08",44172.020833333336,"2021-06-12",44172.177083333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P3 HKM \n ",null,null,34248]
["Infrabel","22978","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,25,25,"2021-06-14",44172.958333333336,"2021-06-18",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord - bourrage de revision, finitions \n ",null,null,22978]
["Infrabel","28722","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,25,25,"2021-06-14",44172.958333333336,"2021-06-18",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux PN28 DT 143100 \n ",null,null,28722]
["Infrabel","21035","Lille - Charleroi","< >","ATH","ATH",2021,2021,25,25,"2021-06-14",44172.979166666664,"2021-06-18",44172.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Péparartion renouvellement 34AF/34BF + 42F \n ",null,null,21035]
["Infrabel","30109","Namur - Antwerpen",">","CHATELET","LE CAMPINAIRE",2021,2021,25,25,"2021-06-15",44172.9375,"2021-06-19",44172.229166666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Phase 2.3 : Bourrage de révision, nettoyage + réglage de joints \n ",null,null,30109]
["Infrabel","27797","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,25,25,"2021-06-15",44172.020833333336,"2021-06-19",44172.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,27797]
["Infrabel","31696","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,26,26,"2021-06-21",44172.958333333336,"2021-06-25",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord - bourrage de revision, finitions \n ",null,null,31696]
["Infrabel","27798","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,26,26,"2021-06-22",44172.020833333336,"2021-06-26",44172.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,27798]
["Infrabel","25132","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2021,2021,27,27,"2021-06-28",44172.958333333336,"2021-07-02",44172.21875,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Réalisation piste + bourrage de révision \n ",null,null,25132]
["Infrabel","27799","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,27,27,"2021-06-29",44172.020833333336,"2021-07-03",44172.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,27799]
["Infrabel","27800","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2021,2021,28,28,"2021-07-06",44172.020833333336,"2021-07-10",44172.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement des traverses Braine-Soignies \n ",null,null,27800]
["Infrabel","25143","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2021,2021,29,29,"2021-07-12",44172.958333333336,"2021-07-16",44172.21875,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Pistes + contraintes voie A + reconstruction quai Franière voie A \n ",null,null,25143]
["Infrabel","32084","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,33,33,"2021-08-09",44172.958333333336,"2021-08-13",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,32084]
["Infrabel","30105","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,34,34,"2021-08-16",44172.875,"2021-08-20",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \n ",null,null,30105]
["Infrabel","21333","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,35,35,"2021-08-23",44172.333333333336,"2021-08-27",44172.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations \n ",null,null,21333]
["Infrabel","19875","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,35,35,"2021-08-23",44172.875,"2021-08-27",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \n ",null,null,19875]
["Infrabel","21334","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,36,36,"2021-08-30",44172.333333333336,"2021-09-03",44172.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations \n ",null,null,21334]
["Infrabel","21331","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,37,37,"2021-09-06",44172.333333333336,"2021-09-10",44172.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations\r\nVoie A HS les Lu-Ma-Me-Je-Ve de 08h à 16h\r\nModification faite des dates à la demande de Mr Hennecart (mail Grignard du 20/02/20) \n ",null,null,21331]
["Infrabel","27254","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,37,37,"2021-09-06",44172.972222222219,"2021-09-10",44172.222222222219,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P3 HKV \n ",null,null,27254]
["Infrabel","21332","Athus - Meuse",">","BERTRIX","FLORENVILLE",2021,2021,38,38,"2021-09-13",44172.333333333336,"2021-09-17",44172.666666666664,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Peignage de rochers et coupe des végétations\r\nModification faite des dates à la demande de Mr Hennecart (mail Grignard du 20/02/20) \n ",null,null,21332]
["Infrabel","30103","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,40,40,"2021-09-27",44172.9375,"2021-10-01",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy - Préparations \n ",null,null,30103]
["Infrabel","31394","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,40,40,"2021-09-27",44172.993055555555,"2021-10-01",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31394]
["Infrabel","9917","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,41,41,"2021-10-04",44172.9375,"2021-10-08",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy \n ",null,null,9917]
["Infrabel","30104","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,42,42,"2021-10-11",44172.9375,"2021-10-15",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - Renouvellement Traverses Mons-Quévy - finitions \n ",null,null,30104]
["Infrabel","20959","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,44,44,"2021-10-25",44172.958333333336,"2021-10-29",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20959]
["Infrabel","31846","Lille - Charleroi","< >","BRUGELETTE","MEVERGNIES-ATTRE",2021,2021,46,46,"2021-11-08",44172.9375,"2021-11-12",44172.201388888891,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTLs de nuit pour préparation renouvellement de l'Aqueduc BK 59.050 \n ",null,null,31846]
["Infrabel","36841","Lille - Charleroi","< >","ECAUSSINNES","MANAGE",2021,2021,46,46,"2021-11-09",44172.006944444445,"2021-11-13",44172.194444444445,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS P3 HKM - Zone 9 AI52 \n ",null,null,36841]
["Infrabel","26992","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,46,46,"2021-11-09",44172.006944444445,"2021-11-13",44172.243055555555,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS P3 HKM\r\nZone 3 AI 53 \n ",null,null,26992]
["Infrabel","32291","Lille - Charleroi",">","ROUX","MARCHIENNE-AU-PONT",2021,2021,52,52,"2021-12-20",44172.25,"2021-12-24",44172.666666666664,"4d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124-124A FLU-FMR \n ",null,null,32291]
["Infrabel","40680","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,8,8,"2022-02-15",44172.083333333336,"2022-02-19",44172.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,40680]
["Infrabel","40681","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,10,10,"2022-03-01",44172.083333333336,"2022-03-05",44172.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,40681]
["Infrabel","29935","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,11,11,"2022-03-07",44172.972222222219,"2022-03-11",44172.222222222219,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29935]
["Infrabel","40682","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,11,11,"2022-03-08",44172.083333333336,"2022-03-12",44172.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,40682]
["Infrabel","29936","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,12,12,"2022-03-14",44172.972222222219,"2022-03-18",44172.222222222219,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29936]
["Infrabel","29937","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,13,13,"2022-03-21",44172.972222222219,"2022-03-25",44172.222222222219,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29937]
["Infrabel","29938","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,14,14,"2022-03-28",44172.972222222219,"2022-04-01",44172.222222222219,"4d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36 \n ",null,null,29938]
["Infrabel","30780","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,14,14,"2022-03-28",44172.944444444445,"2022-04-01",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 6 : Travaux Voie sur CTL de nuits semaine\r\nPréparation plateforme 64BJ + drainage, etc….\r\nCTL de nuits en semaine, les nuits en 22h30/05h30\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hors tensio \n ",null,null,30780]
["Infrabel","30846","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,16,16,"2022-04-12",44172.083333333336,"2022-04-16",44172.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,30846]
["Infrabel","29450","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2022,2022,16,17,"2022-04-15",44172.958333333336,"2022-04-19",44172.166666666664,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51  P4+ \n ",null,null,29450]
["Infrabel","31685","Lille - Charleroi","< >","LOT","HALLE",2022,2022,19,19,"2022-05-03",44172.083333333336,"2022-05-07",44172.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,31685]
["Infrabel","43615","Lille - Charleroi","< >","LOT","HALLE",2022,2022,20,20,"2022-05-10",44172.083333333336,"2022-05-14",44172.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,43615]
["Infrabel","30847","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,23,23,"2022-05-31",44172.083333333336,"2022-06-04",44172.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,30847]
["Infrabel","41718","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,23,24,"2022-06-03",44172.979166666664,"2022-06-07",44172.666666666664,"4d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",null,null,41718]
["Infrabel","31686","Lille - Charleroi","< >","LOT","HALLE",2022,2022,24,24,"2022-06-07"," ","2022-06-11"," ","4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,31686]
["Infrabel","45060","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,24,24,"2022-06-07",44172.958333333336,"2022-06-11",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose seconds tabliers ponts 10 et 11\r\nTravaux préparatoires \n ",null,null,45060]
["Infrabel","43618","Lille - Charleroi","< >","LOT","HALLE",2022,2022,26,26,"2022-06-20"," ","2022-06-24"," ","4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,43618]
["Infrabel","39945","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,27,27,"2022-06-27",44172.958333333336,"2022-07-01",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - nuits préparation \n ",null,null,39945]
["Infrabel","39955","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,27,27,"2022-06-27",44172.958333333336,"2022-07-01",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN123 \n ",null,null,39955]
["Infrabel","40684","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,27,27,"2022-06-28",44172.083333333336,"2022-07-02",44172.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,40684]
["Infrabel","30893","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER-GARAGE",2022,2022,33,34,"2022-08-12",44172.979166666664,"2022-08-16",44172.1875,"4d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre \nHKM détourné via :\r\n- Athus-Meuse - L161\r\n- L144 - L130 - L130A",null,null,30893]
["Infrabel","17168","Namur - Antwerpen","< >","TILLY","FLEURUS",2022,2022,44,44,"2022-10-24",44172.958333333336,"2022-10-28",44172.166666666664,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Nuits pour travaux de finitions Rnvlt du Tablier métallique situé Bk 47.290 \n ",null,null,17168]
["Infrabel","30853","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,44,44,"2022-10-25",44172.083333333336,"2022-10-29",44172.125,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",null,null,30853]
["Infrabel","39946","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,45,45,"2022-10-31",44172.958333333336,"2022-11-04",44172.208333333336,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"P93 - nuits préparation \n ",null,null,39946]
["Infrabel","45521","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,50,50,"2022-12-05",44172.951388888891,"2022-12-09",44172.1875,"4d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45521]
["Infrabel","31304","Lille - Charleroi","< >","LUTTRE","ROUX",2022,2023,50,5,"2022-12-05",44172.291666666664,"2023-01-29",44172.666666666664,"55d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du ballast L124A (C75) \n ",null,null,31304]
["Infrabel","20179","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2021,2021,21,21,"2021-05-17",44172.958333333336,"2021-05-22",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose de 3 AS - grill nord \n ",null,null,20179]
["Infrabel","36562","Lille - Charleroi","< >","ATH","ATH",2021,2021,26,26,"2021-06-21",44172.979166666664,"2021-06-26",44172.1875,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Péparartion renouvellement 34AF/34BF + 42F \n ",null,null,36562]
["Infrabel","26421","Lille - Charleroi",">","ECAUSSINNES","MANAGE",2021,2021,26,26,"2021-06-21",44172.986111111109,"2021-06-26",44172.194444444445,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Maintenance Z9.52\r\nMise HS SAVU P3 HKV - Zone 9 AI52\r\nincompatible chantier de Manage - SAVU possible pour trafic NMLK + HKV \n ",null,null,26421]
["Infrabel","33337","Lille - Charleroi",">","BRAINE-LE-COMTE","ECAUSSINNES",2021,2021,26,26,"2021-06-21",44172.986111111109,"2021-06-26",44172.194444444445,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Maintenance Z3.53\r\nMise HS SAVU P3 HKM\r\n incompatible chantier de Manage - SAVU possible pour trafic NMLK + HKV \n ",null,null,33337]
["Infrabel","33331","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,28,28,"2021-07-05",44172.979166666664,"2021-07-10",44172.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,33331]
["Infrabel","25150","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2021,2021,31,31,"2021-07-26",44172.958333333336,"2021-07-31",44172.21875,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Pistes + Contraintes\r\nSAVU nuit \n ",null,null,25150]
["Infrabel","23258","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,32,32,"2021-08-02",44172.958333333336,"2021-08-07",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,23258]
["Infrabel","31393","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,33,33,"2021-08-09",44172.993055555555,"2021-08-14",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31393]
["Infrabel","27252","Lille - Charleroi","< >","LUTTRE","MANAGE",2021,2021,36,36,"2021-08-30",44172.986111111109,"2021-09-04",44172.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z5.52\r\nMise HS P3 HKM - Zone 5 AI52 (Luttre-Manage) \n ",null,null,27252]
["Infrabel","36407","Lille - Charleroi","< >","MONS","QUEVY",2021,2021,36,36,"2021-08-30",44172.875,"2021-09-04",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PN 110 + 108  de Frameries \n ",null,null,36407]
["Infrabel","20960","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,37,37,"2021-09-06",44172.958333333336,"2021-09-11",44172.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20960]
["Infrabel","23091","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,37,37,"2021-09-06",44172.958333333336,"2021-09-11",44172.229166666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nDétournements à prévoir",null,null,23091]
["Infrabel","34250","Lille - Charleroi","< >","Y.SOIGNIES","BRAINE-LE-COMTE",2021,2021,37,37,"2021-09-06",44172.979166666664,"2021-09-11",44172.1875,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P3 HKV \n ",null,null,34250]
["Infrabel","34249","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2021,2021,37,37,"2021-09-06",44172.982638888891,"2021-09-11",44172.177083333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z4.53\r\nMise HS P3 HKV \n ",null,null,34249]
["Infrabel","34571","Lille - Charleroi","< >","NEUFVILLES","MASNUY-SAINT-PIERRE",2021,2021,37,37,"2021-09-06",44172.982638888891,"2021-09-11",44172.177083333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTL de nuit étendues. Rejointoiement et réfection de maçonnerie en voûte (PS 42.540) \n ",null,null,34571]
["Infrabel","20859","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,38,38,"2021-09-13",44172.958333333336,"2021-09-18",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \n",null,null,20859]
["Infrabel","31785","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,39,39,"2021-09-20",44172.958333333336,"2021-09-25",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,31785]
["Infrabel","20860","Namur - Antwerpen","< >","TILLY","LA ROCHE(BRABANT)",2021,2021,39,39,"2021-09-20",44172.958333333336,"2021-09-25",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"- Renouvellement chapes Villers-la-Ville\r\n- Pose de passerelles sur 2 PI\r\n- Construction d'un mur de soutènement \nPas de traffic supplémentaire les nuits de CTL. (Doc envoyé le 12/03/18)",null,null,20860]
["Infrabel","34264","Lille - Charleroi","< >","Y.SOIGNIES","BRAINE-LE-COMTE",2021,2021,42,42,"2021-10-11",44172.979166666664,"2021-10-16",44172.1875,"5d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2.53\r\nMise HS P3 HKV \n ",null,null,34264]
["Infrabel","31397","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,42,42,"2021-10-11",44172.993055555555,"2021-10-16",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31397]
["Infrabel","20671","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,43,43,"2021-10-18",44172.958333333336,"2021-10-23",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,20671]
["Infrabel","33736","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,46,46,"2021-11-08",44172.979166666664,"2021-11-13",44172.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,33736]
["Infrabel","27302","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2021,2021,46,46,"2021-11-08",44172.972222222219,"2021-11-13",44172.222222222219,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z3. 51   P3 HKV \n ",null,null,27302]
["Infrabel","37196","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","Y.VAL-SAINT-LAMBERT",2021,2021,47,47,"2021-11-15",44172.965277777781,"2021-11-20",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Z.19.41 - Maintenance P3\r\nCTL en conflit avec travaux L36 \n ",null,null,37196]
["Infrabel","21039","Lille - Charleroi","< >","Y.LENS","ATH",2021,2021,48,48,"2021-11-22",44172.9375,"2021-11-27",44172.201388888891,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF \r\nDéchargement des appareils \n ",null,null,21039]
["Infrabel","33779","Lille - Charleroi","< >","JURBISE","ATH",2021,2021,48,48,"2021-11-22",44172.9375,"2021-11-27",44172.201388888891,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 \n ",null,null,33779]
["Infrabel","31399","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,48,48,"2021-11-22",44172.993055555555,"2021-11-27",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31399]
["Infrabel","26418","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,49,49,"2021-11-29",44172.944444444445,"2021-12-04",44172.243055555555,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z8.52\r\nMise HS P3 HKV - Zone 8 AI52 \n ",null,null,26418]
["Infrabel","31398","Namur - Antwerpen","< >","AISEAU","LE CAMPINAIRE",2021,2021,49,49,"2021-11-29",44172.993055555555,"2021-12-04",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement passages supérieurs BK 85.708 et 84.625 \n ",null,null,31398]
["Infrabel","21168","Lille - Charleroi","< >","Y.LA SAMBRE","Y.NORD",2021,2021,49,50,"2021-12-04",44172.972222222219,"2021-12-09",44172.194444444445,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,21168]
["Infrabel","20674","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,50,50,"2021-12-06",44172.958333333336,"2021-12-11",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,20674]
["Infrabel","27247","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2021,2021,50,50,"2021-12-06",44172.9375,"2021-12-11",44172.170138888891,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Maintenance Z2. 51    P3 HKV \n ",null,null,27247]
["Infrabel","23259","Erquelinnes - Montzen","< >","HOURPES","LOBBES",2021,2021,51,51,"2021-12-13",44172.958333333336,"2021-12-18",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du pont 9\r\nCTL toutes les nuits \n ",null,null,23259]
["Infrabel","33011","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2022,2022,10,10,"2022-02-28",44172.041666666664,"2022-03-05",44172.208333333336,"5d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen wissels Y.Parkbrug (in combinatie met langdurige buitendienststelling tussen Ottignie en Sint-Joris-Weert).\r\nStation Heverlee (B-ST): Vernieuwing perronluifel (Annick Locquet) \nOp zesmaandelijkse van 12/12/2019 vragen goederenoperatoren de lijnen 75 en 59 bijkomend open te houden.",null,null,33011]
["Infrabel","39304","Lille - Antwerpen",">","MOUSCRON","KORTRIJK",2022,2022,13,13,"2022-03-21",44172.951388888891,"2022-03-26",44172.236111111109,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 1 – Fondations\r\nPhase 1.2. Forage des pieux dans le quai II-III \nA adapter",null,null,39304]
["Infrabel","30785","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,15,15,"2022-04-04",44172.944444444445,"2022-04-09",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 8 : Travaux Voie sur CTL de nuits semaine\r\nFinition W-e 2 + drainage, etc….\r\nCTL de nuits en semaine, les nuits en 22h30/05h30 :\r\n\r\n-\tHS en continu : Voie 382 entre l’AS 61AJ et l’As 64 BJ.\r\n\tMise hors tension cas 27319 \n ",null,null,30785]
["Infrabel","39393","Lille - Antwerpen",">","MOUSCRON","KORTRIJK",2022,2022,16,16,"2022-04-11",44172.951388888891,"2022-04-16",44172.236111111109,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Construction passerelle en gare de Mouscron\r\nPhase 2 – Fondations\r\nPhase 2.1. Dalle quai II-III \nA adapter",null,null,39393]
["Infrabel","30855","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,19,19,"2022-05-02",44172.944444444445,"2022-05-07",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 10 : Travaux Voie sur CTL de nuits semaine\r\nBourrage révision, contrainte, pose caniveaux pistes, finitions chantier…. \n ",null,null,30855]
["Infrabel","30783","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,20,20,"2022-05-09",44172.944444444445,"2022-05-14",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 10 : Travaux Voie sur CTL de nuits semaine\r\nBourrage révision, contrainte, pose caniveaux pistes, finitions chantier…. \n ",null,null,30783]
["Infrabel","45106","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,21,21,"2022-05-16",44172.944444444445,"2022-05-21",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Aménagement Le Campinaire\r\nPhase 10 : Travaux Voie sur CTL de nuits semaine\r\nBourrage révision, contrainte, pose caniveaux pistes, finitions chantier…. \n ",null,null,45106]
["Infrabel","30914","Erquelinnes - Montzen","< >","STATTE","JAVA",2022,2022,21,21,"2022-05-16",44172.993055555555,"2022-05-21",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte\r\nBourrage + tx finition \n ",null,null,30914]
["Infrabel","30849","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,23,23,"2022-05-30",44172.958333333336,"2022-06-04",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose seconds tabliers ponts 10 et 11\r\nTravaux préparatoires \n ",null,null,30849]
["Infrabel","43617","Lille - Charleroi","< >","LOT","HALLE",2022,2022,25,25,"2022-06-13"," ","2022-06-18"," ","5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's L96N sp B \n ",null,null,43617]
["Infrabel","30845","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,25,25,"2022-06-13",44172.958333333336,"2022-06-18",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose seconds tabliers ponts 10 et 11\r\nTravaux préparatoires \n ",null,null,30845]
["Infrabel","41465","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,26,26,"2022-06-20",44172.958333333336,"2022-06-25",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose seconds tabliers ponts 10 et 11\r\nTravaux préparatoires \n ",null,null,41465]
["Infrabel","30851","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,37,37,"2022-09-04",44172.958333333336,"2022-09-09",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose seconds tabliers ponts 10 et 11\r\nTravaux de finition \n ",null,null,30851]
["Infrabel","29364","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,39,39,"2022-09-19",44172.989583333336,"2022-09-24",44172.197916666664,"5d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Travaux préparatoires  CTL Grill coté LLN \n ",null,null,29364]
["Infrabel","45130","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,40,40,"2022-09-26",44172.951388888891,"2022-10-01",44172.1875,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45130]
["Infrabel","38869","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,41,41,"2022-10-03",44172.958333333336,"2022-10-08",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart \n ",null,null,38869]
["Infrabel","45061","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2022,2022,41,41,"2022-10-03",44172.9375,"2022-10-08",44172.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Pose seconds tabliers ponts 10 et 11 - Travaux de finition\r\n+ Travaux de préparation pour le renouvellement des tabliers du pont BK 125.363\r\n+ Travaux de préparation pour renouvellement chape d'étanchéité PI km 106,769 \n ",null,null,45061]
["Infrabel","38871","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,42,42,"2022-10-10",44172.958333333336,"2022-10-15",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart \n ",null,null,38871]
["Infrabel","28780","Lille - Charleroi","< >","FROYENNES","BLANDAIN-FRONTIERE",2022,2022,42,42,"2022-10-10",44172.958333333336,"2022-10-15",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PN 2 - 8 - 10\r\nBourrage de révision\r\nAsphaltage\r\nFinitions \n ",null,null,28780]
["Infrabel","30753","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2022,2022,42,42,"2022-10-10",44172.9375,"2022-10-15",44172.166666666664,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Travaux de préparation pour renouvellement chape d'étanchéité PI km 106,769\r\n+ Travaux de préparation pour le renouvellement des tabliers du pont BK 125.363 \n ",null,null,30753]
["Infrabel","17167","Namur - Antwerpen","< >","TILLY","FLEURUS",2022,2022,42,43,"2022-10-12",44172.958333333336,"2022-10-17",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Nuits pour travaux préparatoires Rnvlt du Tablier métallique situé Bk 47.290 \n ",null,null,17167]
["Infrabel","38876","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,44,44,"2022-10-24",44172.9375,"2022-10-29",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart \n ",null,null,38876]
["Infrabel","38875","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,45,45,"2022-10-31",44172.9375,"2022-11-05",44172.208333333336,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart \n ",null,null,38875]
["Infrabel","45514","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,47,47,"2022-11-14",44172.951388888891,"2022-11-19",44172.1875,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45514]
["Infrabel","45517","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,48,48,"2022-11-21",44172.951388888891,"2022-11-26",44172.1875,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45517]
["Infrabel","45518","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,49,49,"2022-11-28",44172.951388888891,"2022-12-03",44172.1875,"5d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45518]
["Infrabel","34344","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,16,25,"2022-04-11",44172.003472222219,"2022-06-12",44172.003472222219,"62d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L12 Engelselei – waterdichte rokken vervangen \n ",null,null,34344]
["Infrabel","35582","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.HOLLAND",2021,2021,34,44,"2021-08-21",44172,"2021-10-28",44172.996527777781,"68d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Vernieuwing spoortoestellen Bundel Q Antwerpen-Schijnpoort\r\n\r\nUPM: A-248867 \n ",null,null,35582]
["Infrabel","38790","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,6,16,"2022-02-01",44172.003472222219,"2022-04-11",44172.003472222219,"69d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"L12 Engelselei – waterdichte rokken vervangen\r\nSpoor A L27A eveneens continu buitendienst ( zie andere locaties ) \n ",null,null,38790]
["Infrabel","31208","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2021,2021,32,33,"2021-08-02",44172.951388888891,"2021-08-08",44172.229166666664,"6d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"RER : \r\nSAVU DE NUIT en semaine 22:50-05:30\r\net CTL nuit les weekend samedi a dimanche 00:30-05:30\r\nTravaux préparatoires de la renovation de la Y.LLN \n ",null,null,31208]
["Infrabel","21106","Lille - Charleroi","< >","MANAGE","LUTTRE",2021,2021,36,37,"2021-08-30",44172.986111111109,"2021-09-05",44172.194444444445,"6d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement du PS 51.035 et du pont du canal - Travaux SPW \n ",null,null,21106]
["Infrabel","20963","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,42,43,"2021-10-11",44172.375,"2021-10-17",44172.666666666664,"6d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20963]
["Infrabel","20965","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2021,2021,48,49,"2021-11-22",44172.375,"2021-11-28",44172.666666666664,"6d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Entretien PS Defalque 32.576 \n ",null,null,20965]
["Infrabel","10165","Lille - Charleroi","< >","Y.LA SAMBRE","Y.NORD",2021,2021,40,41,"2021-10-02",44172.930555555555,"2021-10-09",44172.194444444445,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,10165]
["Infrabel","31851","Lille - Charleroi","< >","BRUGELETTE","MEVERGNIES-ATTRE",2021,2021,47,48,"2021-11-19",44172.9375,"2021-11-26",44172.201388888891,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"CTLs de nuit pour finitions du renouvellement de l'Aqueduc BK 59.050 \n ",null,null,31851]
["Infrabel","32289","Lille - Charleroi",">","LUTTRE","ROUX",2021,2021,51,52,"2021-12-13",44172.25,"2021-12-20",44172.25,"7d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réélectrification L. 124-124A FLU-FMR \n ",null,null,32289]
["Infrabel","28955","Lille - Charleroi","< >","Y.LA SAMBRE","Y.NORD",2022,2022,16,17,"2022-04-11",44172.930555555555,"2022-04-18",44172.194444444445,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement PS BK 54.263 Marchienne Est \nHKM à adapter",null,null,28955]
["Infrabel","32061","Athus - Meuse",">","BERTRIX","FLORENVILLE",2022,2022,19,20,"2022-05-02",44172.333333333336,"2022-05-09",44172.208333333336,"7d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Réglages des contraintes des rails (LRS) entre km 82050-89480\r\nFinition chantier 2021 \n ",null,null,32061]
["Infrabel","45107","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,22,23,"2022-05-23",44172.923611111109,"2022-05-30",44172.215277777781,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nTravaux de renouvellement des chapes d'étanchéité des PI 61.597 et 64.126 + construction de passerelles en VA et VB au droit du PI 61.597. \n ",null,null,45107]
["Infrabel","45122","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,37,38,"2022-09-05",44172.951388888891,"2022-09-12",44172.1875,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n + dépose traverses \n ",null,null,45122]
["Infrabel","45125","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,38,39,"2022-09-12",44172.951388888891,"2022-09-19",44172.1875,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45125]
["Infrabel","45128","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,39,40,"2022-09-19",44172.951388888891,"2022-09-26",44172.1875,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45128]
["Infrabel","45132","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,41,42,"2022-10-03",44172.951388888891,"2022-10-10",44172.1875,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45132]
["Infrabel","45136","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,42,43,"2022-10-10",44172.951388888891,"2022-10-17",44172.1875,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45136]
["Infrabel","45139","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,43,44,"2022-10-17",44172.951388888891,"2022-10-24",44172.1875,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45139]
["Infrabel","45141","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,44,45,"2022-10-24",44172.951388888891,"2022-10-31",44172.1875,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45141]
["Infrabel","45140","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,45,46,"2022-10-31",44172.951388888891,"2022-11-07",44172.1875,"7d","Periodical",null,"T","",null,null,null,null,null,null,null,null,"Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",null,null,45140]
["Infrabel","20891","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,40,41,"2022-09-30",44172.989583333336,"2022-10-08",44172.197916666664,"8d","Periodical",null,"","ST",null,null,null,null,null,null,null,null,"Travaux préparatoires  CTL Grill coté LLN \n ",null,null,20891]
["Infrabel","17962","Lille - Charleroi","< >","FROYENNES","MOUSCRON",2021,2021,36,50,"2021-08-30",44172.25,"2021-12-06",44172.208333333336,"98d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"-\tRenouvellement de traverses, Rails, passages à niveau\r\n-\tSuppression de passages à niveau\r\n-\tAssainissement\r\n-\tRéalisation de travaux divers aux abords clôture, débroussaillage,… afin de sécuriser notre domaine aux points sensibles (HOT SPOT)\r\n-\tRenou \nomleidingen te specifiëren per week",null,null,17962]
["Infrabel","18077","Athus - Meuse",">","FLORENVILLE","BERTRIX",2021,2021,43,44,"2021-10-18",44172.333333333336,"2021-10-27",44172.666666666664,"9d","Continuous",null,"","ST",null,null,null,null,null,null,null,null,"Renouvellement des traverses (P93) \n ",null,null,18077]
["Infrabel","27505","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,44,46,"2021-10-30",44172.027777777781,"2021-11-08",44172.177083333336,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 2)\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) \n ",null,null,27505]
["Infrabel","29288","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,44,46,"2021-10-30",44172.020833333336,"2021-11-08",44172.1875,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"L59 PLP SI\r\nL59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel \n ",null,null,29288]
["Infrabel","29605","Lille - Antwerpen","< >","Y.MELSELE","Y.ANTWERPEN-ZUID",2021,2021,44,46,"2021-10-30",44172.020833333336,"2021-11-08",44172.1875,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"- Omvorming stopplaats Zwijndrecht (FASE 3)\r\n- Verhogen veiligheid Kennedytunnel\r\n- L59 PLP SI \n ",null,null,29605]
["Infrabel","29933","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,9,11,"2022-02-26",44172.25,"2022-03-07",44172.208333333336,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36\r\n+ Renouvellement des quais VA de Florival\r\nElargissement des pistes de circulation et pose de passerelles\r\n+ Entretien massi \nWE 5-6/03/22 - L96 fermée -> détournements via L130A ou via L90C-90",null,null,29933]
["Infrabel","21753","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,9,11,"2022-02-26",44172.041666666664,"2022-03-07",44172.166666666664,"9d","Continuous",null,"T","",null,null,null,null,null,null,null,null,"- Omvorming stopplaats Zwijndrecht (FASE 4)\r\n- Verhogen veiligheid Kennedytunnel\r\n- Bouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) \n ",null,null,21753]

{"sheet":"Data","index":4,"n_rows":24,"n_cols":7,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction"]
["SNCF R",87,"Boulogne-Calais",1,"All day",10868,"Signal work"]
[null,null,"Calais-Dunkerque-Hazebrouck",2,"Day",null,"Switch work"]
[null,null,"Calais-Lille-Aulnoye",3,"Night",null,"Catenary work"]
[null,null,"Hazebrouck-Lens-Aulnoye",4,null,null,"Track work"]
[null,null,"Amiens-Douai",5,null,null,"Rail work"]
[null,null,"Paris-Amiens",6,null,null,"Tunnel work"]
[null,null,"Paris-Busigny",7,null,null,"Bridge work"]
[null,null,"Aulnoye-Longuyon",8,null,null,"Misc. Work"]
[null,null,"Longuyon-Metz-Sarrebourg",9,null,null,"Maintanance"]
[null,null,"Longuyon-Nancy-Sarrebourg",10]
[null,null,"Lerouville-Metz",11]
[null,null,"Lerouville-Nancy",12]
[null,null,"Sarrebourg-Basel",13]
[null,null,"Dijon-Toul",14]
[null,null,"Dijon-Lyon",15]
[null,null,"Dijon-Amberieu-Lyon",16]
[null,null,"Lyon-Valence",17]
[null,null,"Valence - Avignon",18]
[null,null,"Avignon-Miramasparouest",19]
[null,null,"Avignon-Miramasparest",20]
[null,null,"Miramas-Marseille",21]
[null,null,"Miramas-Fos-Marseille",22]
[null,null,"Aulnoye-Feignies-Jeumont",23]

{"sheet":"SNCFR","index":5,"n_rows":1393,"n_cols":31,"rows_kept":1393,"cut":false,"hidden":false,"merged":[[0,17,0,21],[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["SNCF Réseau","8344680761_8344430461","Sarrebourg-Basel",">","Colmar","NeufBrisach",2021,2021,23,24,"2021-06-11T11:40:00","11:40","2021-06-18T15:40:00","15:40",19,"DAY",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","8344680761_8344429461","Sarrebourg-Basel",">","Colmar","NeufBrisach",2021,2021,16,24,"2021-04-19T12:00:00","12:00","2021-06-17T20:00:00","20:00",208,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8344690361_8344442061","Sarrebourg-Basel",">","Mulhouse","Chalampe",2020,2021,51,49,"2020-12-14T08:52:00","08:52","2021-12-10T09:52:00","09:52",2349,"DAY",null,null,null,null,null,null,null,null,null,null,null,"239 jours dans le régime binaire"]
["SNCF Réseau","8344690361_8344443661","Sarrebourg-Basel",">","Mulhouse","Chalampe",2021,2021,11,41,"2021-03-15T22:00:00","22:00","2021-10-15T04:00:00","04:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344327161","Paris-Amiens",">","Stade de France","SaintDenis",2021,2021,1,46,"2021-01-04T23:25:00","23:25","2021-11-19T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"150 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344329161","Paris-Amiens",">","Stade de France","SaintDenis",2020,2021,51,49,"2020-12-15T01:00:00","01:00","2021-12-11T04:50:00","04:50",1246,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"258 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344330161","Paris-Amiens",">","Stade de France","SaintDenis",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344326161","Paris-Amiens",">","Stade de France","SaintDenis",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344325161","Paris-Amiens",">","Stade de France","SaintDenis",2021,2021,1,46,"2021-01-04","00:00","2021-11-19T05:05:00","05:05",-5,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"150 jours dans le régime binaire"]
["SNCF Réseau","8344372661_8344328161","Paris-Amiens",">","Stade de France","SaintDenis",2020,2021,51,49,"2020-12-15T00:35:00","00:35","2021-12-11T05:05:00","05:05",1305,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"257 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344247961","Paris-Amiens",">","Villiers le Bel","Goussainville",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344251961","Paris-Amiens",">","Villiers le Bel","Goussainville",2021,2021,1,46,"2021-01-04T23:46:00","23:46","2021-11-19T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344251161","Paris-Amiens",">","Villiers le Bel","Goussainville",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344249561","Paris-Amiens",">","Villiers le Bel","Goussainville",2020,2021,51,49,"2020-12-15T00:20:00","00:20","2021-12-11T04:50:00","04:50",1198,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"248 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344248761","Paris-Amiens",">","Villiers le Bel","Goussainville",2021,2021,1,46,"2021-01-04T23:45:00","23:45","2021-11-19T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","8344372461_8344250361","Paris-Amiens",">","Villiers le Bel","Goussainville",2020,2021,51,49,"2020-12-15T01:14:00","01:14","2021-12-11T04:50:00","04:50",1202,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344287961","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2021,51,49,"2020-12-15T00:30:00","00:30","2021-12-11T04:55:00","04:55",1243,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344288761","Paris-Amiens",">","SaintDenis","VilliersLeBel",2021,2021,1,46,"2021-01-04T23:55:00","23:55","2021-11-19T04:50:00","04:50",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344291161","Paris-Amiens",">","SaintDenis","VilliersLeBel",2021,2021,1,46,"2021-01-04T23:35:00","23:35","2021-11-19T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344289561","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344291961","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344371761_8344290361","Paris-Amiens",">","SaintDenis","VilliersLeBel",2020,2021,51,49,"2020-12-15T01:05:00","01:05","2021-12-11T04:50:00","04:50",1226,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"254 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344322361","Paris-Amiens",">","Orry","Creil",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344319961","Paris-Amiens",">","Orry","Creil",2020,2021,51,49,"2020-12-14T01:51:00","01:51","2021-12-06T04:51:00","04:51",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344319161","Paris-Amiens",">","Orry","Creil",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",115,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344321561","Paris-Amiens",">","Orry","Creil",2021,2021,5,49,"2021-02-02T01:10:00","01:10","2021-12-11T05:26:00","05:26",618,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"114 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344317961","Paris-Amiens",">","Orry","Creil",2021,2021,5,49,"2021-02-01T23:49:00","23:49","2021-12-10T04:54:00","04:54",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"114 jours dans le régime binaire"]
["SNCF Réseau","8344371561_8344320761","Paris-Amiens",">","Orry","Creil",2021,2021,5,49,"2021-02-01T23:53:00","23:53","2021-12-10T04:42:00","04:42",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"114 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344254961","Paris-Amiens",">","Goussainville","Orry",2020,2021,51,49,"2020-12-15T00:15:00","00:15","2021-12-11T04:45:00","04:45",1177,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"248 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344255761","Paris-Amiens",">","Goussainville","Orry",2020,2021,51,49,"2020-12-14T01:40:00","01:40","2021-12-06T04:40:00","04:40",241,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344256561","Paris-Amiens",">","Goussainville","Orry",2020,2021,51,49,"2020-12-14T01:35:00","01:35","2021-12-06T04:35:00","04:35",236,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344257361","Paris-Amiens",">","Goussainville","Orry",2021,2021,1,46,"2021-01-04T23:40:00","23:40","2021-11-19T04:35:00","04:35",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344253361","Paris-Amiens",">","Goussainville","Orry",2021,2021,1,46,"2021-01-04T23:50:00","23:50","2021-11-19T04:50:00","04:50",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","8344372861_8344254161","Paris-Amiens",">","Goussainville","Orry",2020,2021,51,49,"2020-12-15T01:20:00","01:20","2021-12-11T04:50:00","04:50",1197,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"248 jours dans le régime binaire"]
["SNCF Réseau","8344372261_8344282361","Paris-Amiens",">","Bif de Pierrefitte","Orry",2020,2021,51,49,"2020-12-14T01:45:00","01:45","2021-12-06T04:45:00","04:45",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344372261_8344285161","Paris-Amiens",">","Bif de Pierrefitte","Orry",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",115,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8344372261_8344284361","Paris-Amiens",">","Bif de Pierrefitte","Orry",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344372261_8344283161","Paris-Amiens",">","Bif de Pierrefitte","Orry",2021,2021,5,49,"2021-02-02","00:00","2021-12-11T05:00:00","05:00",455,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"91 jours dans le régime binaire"]
["SNCF Réseau","8344371661_8344280361","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2020,2021,51,49,"2020-12-14T01:45:00","01:45","2021-12-06T04:45:00","04:45",245,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344371661_8344279561","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:30:00","04:30",232,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344371661_8344278561","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2020,2021,51,49,"2020-12-15","00:00","2021-12-11T05:00:00","05:00",1040,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"208 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327591261","Avignon-Miramasparouest",">","Avignon","Tarascon",2021,2021,1,48,"2021-01-04T01:05:00","01:05","2021-11-29T04:10:00","04:10",90,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327593661","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2021,51,47,"2020-12-15","00:00","2021-11-27T02:00:00","02:00",298,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"149 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327589661","Avignon-Miramasparouest",">","Avignon","Tarascon",2021,2021,1,48,"2021-01-04T01:20:00","01:20","2021-11-29T04:15:00","04:15",92,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327592061","Avignon-Miramasparouest",">","Avignon","Tarascon",2021,2021,1,42,"2021-01-04T23:10:00","23:10","2021-10-22T05:04:00","05:04",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327592861","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2021,51,49,"2020-12-14T10:24:00","10:24","2021-12-10T11:15:00","11:15",2824,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327590461","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2021,51,49,"2020-12-14T14:00:00","14:00","2021-12-10T15:09:00","15:09",3803,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805161_8327594661","Avignon-Miramasparouest",">","Avignon","Tarascon",2020,2021,51,47,"2020-12-14T23:15:00","23:15","2021-11-26T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","8327806461_8327684661","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2020,2021,51,49,"2020-12-14T15:26:00","15:26","2021-12-10T16:54:00","16:54",4243,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806461_8327685461","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2021,2021,12,15,"2021-03-22T09:20:00","09:20","2021-04-16T13:20:00","13:20",244,"DAY",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8327806461_8327686461","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2020,2021,51,49,"2020-12-14T09:33:00","09:33","2021-12-10T10:01:00","10:01",2514,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327804961_8327630861","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2020,2021,51,49,"2020-12-14T11:11:00","11:11","2021-12-10T12:13:00","12:13",3067,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327804961_8327631661","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2020,2021,51,49,"2020-12-14T09:49:00","09:49","2021-12-10T10:46:00","10:46",2703,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327804961_8327632461","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2020,2021,51,48,"2020-12-15","00:00","2021-12-04T04:30:00","04:30",1111,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"247 jours dans le régime binaire"]
["SNCF Réseau","8327807561_8327690661","Miramas-Marseille",">","Rognac","L'Estaque",2020,2021,51,49,"2020-12-14T09:56:00","09:56","2021-12-10T10:50:00","10:50",2720,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327807561_8327692261","Miramas-Marseille",">","Rognac","L'Estaque",2020,2021,51,49,"2020-12-14T11:05:00","11:05","2021-12-10T12:10:00","12:10",3054,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327807561_8327689861","Miramas-Marseille",">","Rognac","L'Estaque",2020,2021,51,49,"2020-12-14T10:02:00","10:02","2021-12-10T10:56:00","10:56",2745,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327807561_8327693061","Miramas-Marseille",">","Rognac","L'Estaque",2020,2021,51,48,"2020-12-15","00:00","2021-12-04T04:30:00","04:30",1111,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"247 jours dans le régime binaire"]
["SNCF Réseau","8327807561_8327691461","Miramas-Marseille",">","Rognac","L'Estaque",2020,2021,51,49,"2020-12-14T10:56:00","10:56","2021-12-10T12:04:00","12:04",3029,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805761_8327734461","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2020,2021,51,49,"2020-12-14T09:53:00","09:53","2021-12-10T10:38:00","10:38",2669,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805761_8327735261","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2020,2021,51,49,"2020-12-14T15:06:00","15:06","2021-12-10T16:23:00","16:23",4113,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805761_8327736061","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2021,2021,12,49,"2021-03-22T22:30:00","22:30","2021-12-10T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"118 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327573061","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2021,51,49,"2020-12-14T09:20:00","09:20","2021-12-10T10:20:00","10:20",2594,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327572061","Miramas-Fos-Marseille",">","Lavalduc","Fos",2021,2021,13,48,"2021-03-29T22:30:00","22:30","2021-12-03T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327570461","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327571261","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327569661","Miramas-Fos-Marseille",">","Lavalduc","Fos",2021,2021,10,43,"2021-03-08T22:30:00","22:30","2021-10-29T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","8327805061_8327573861","Miramas-Fos-Marseille",">","Lavalduc","Fos",2020,2021,51,49,"2020-12-14T09:20:00","09:20","2021-12-10T10:20:00","10:20",2594,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327807161_8327724061","Avignon-Miramasparouest",">","Tarascon","Miramas",2020,2021,51,49,"2020-12-14T10:08:00","10:08","2021-12-10T11:34:00","11:34",2904,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327807161_8327721461","Avignon-Miramasparouest",">","Tarascon","Miramas",2021,2021,1,48,"2021-01-04T00:30:00","00:30","2021-11-29T03:28:00","03:28",75,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8327807161_8327722261","Avignon-Miramasparouest",">","Tarascon","Miramas",2021,2021,8,48,"2021-02-22T23:15:00","23:15","2021-12-03T05:13:00","05:13",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"88 jours dans le régime binaire"]
["SNCF Réseau","8327807161_8327724861","Avignon-Miramasparouest",">","Tarascon","Miramas",2021,2021,1,48,"2021-01-04T01:43:00","01:43","2021-11-29T04:45:00","04:45",102,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8327807161_8327723261","Avignon-Miramasparouest",">","Tarascon","Miramas",2020,2021,51,49,"2020-12-14T10:52:00","10:52","2021-12-10T11:25:00","11:25",2866,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805661_8327643061","Avignon-Miramasparest",">","Avignon","Cavaillon",2020,2021,51,49,"2020-12-14T00:32:00","00:32","2021-12-06T03:55:00","03:55",97,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8327805661_8327640461","Avignon-Miramasparest",">","Avignon","Cavaillon",2021,2021,14,48,"2021-04-06T09:10:00","09:10","2021-12-03T13:10:00","13:10",372,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","8327805661_8327639661","Avignon-Miramasparest",">","Avignon","Cavaillon",2020,2021,51,49,"2020-12-14T01:45:00","01:45","2021-12-06T04:16:00","04:16",104,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8327805661_8327641461","Avignon-Miramasparest",">","Avignon","Cavaillon",2020,2021,51,49,"2020-12-14T11:04:00","11:04","2021-12-10T11:33:00","11:33",2899,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327805661_8327642261","Avignon-Miramasparest",">","Avignon","Cavaillon",2020,2021,51,49,"2020-12-14T12:50:00","12:50","2021-12-10T14:21:00","14:21",3603,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806761_8327587661","Avignon-Miramasparest",">","Cavaillon","Miramas",2020,2021,51,49,"2020-12-14T13:37:00","13:37","2021-12-10T15:00:00","15:00",3766,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806761_8327588461","Avignon-Miramasparest",">","Cavaillon","Miramas",2020,2021,51,49,"2020-12-14T00:55:00","00:55","2021-12-06T04:28:00","04:28",110,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8327806761_8327586061","Avignon-Miramasparest",">","Cavaillon","Miramas",2020,2021,51,49,"2020-12-14T10:14:00","10:14","2021-12-10T10:51:00","10:51",2723,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806761_8327585061","Avignon-Miramasparest",">","Cavaillon","Miramas",2021,2021,14,48,"2021-04-06T09:10:00","09:10","2021-12-03T13:10:00","13:10",372,"DAY",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","8327806761_8327586861","Avignon-Miramasparest",">","Cavaillon","Miramas",2020,2021,51,49,"2020-12-14T01:16:00","01:16","2021-12-06T03:35:00","03:35",88,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8327806361_8327673461","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8327806361_8327672661","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2020,2021,51,49,"2020-12-14T14:51:00","14:51","2021-12-10T16:06:00","16:06",4042,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806361_8327671861","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2020,2021,51,49,"2020-12-14T10:06:00","10:06","2021-12-10T10:55:00","10:55",2740,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806361_8327674261","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8327806361_8327670861","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2021,2021,5,43,"2021-02-01T22:30:00","22:30","2021-10-29T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"122 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327679661","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,49,"2020-12-14T10:20:00","10:20","2021-12-10T11:08:00","11:08",2795,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327682261","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,49,"2020-12-14T10:51:00","10:51","2021-12-10T11:55:00","11:55",2992,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327678861","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,49,"2020-12-14T01:00:00","01:00","2021-12-06T03:55:00","03:55",190,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327681461","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,49,"2020-12-14T10:39:00","10:39","2021-12-10T11:51:00","11:51",2975,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327680461","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,48,"2020-12-15","00:00","2021-12-04T04:30:00","04:30",1116,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"248 jours dans le régime binaire"]
["SNCF Réseau","8327806161_8327678061","Miramas-Marseille",">","Miramas","Rognac",2020,2021,51,49,"2020-12-14T10:08:00","10:08","2021-12-10T11:05:00","11:05",2782,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345623561_8345519761","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2020,2021,51,49,"2020-12-14T09:54:00","09:54","2021-12-10T10:54:00","10:54",2736,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345623561_8345517961","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2020,2021,51,49,"2020-12-14T14:00:00","14:00","2021-12-10T15:00:00","15:00",3766,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345623561_8345518761","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2021,2021,4,47,"2021-01-25T21:45:00","21:45","2021-11-26T05:25:00","05:25",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"151 jours dans le régime binaire"]
["SNCF Réseau","8345624861_8345494761","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2020,2021,51,49,"2020-12-14T10:00:00","10:00","2021-12-10T12:30:00","12:30",3140,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345624861_8345493761","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2021,2021,6,49,"2021-02-08T10:00:00","10:00","2021-12-10T15:00:00","15:00",650,"DAY",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","8345624861_10318794261","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2020,2021,51,49,"2020-12-14T11:20:00","11:20","2021-12-10T13:20:00","13:20",3348,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345625061_8345490961","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2021,2021,17,43,"2021-04-26T10:00:00","10:00","2021-10-29T17:00:00","17:00",296,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8345625061_8345491961","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2021,2021,5,47,"2021-02-01T21:03:00","21:03","2021-11-26T05:20:00","05:20",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"140 jours dans le régime binaire"]
["SNCF Réseau","8345625061_8345489961","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2020,2021,51,49,"2020-12-14T13:50:00","13:50","2021-12-10T16:50:00","16:50",4228,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345547761","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2021,2021,17,43,"2021-04-26T12:25:00","12:25","2021-10-29T17:00:00","17:00",293,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345546161","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2021,51,49,"2020-12-14T13:50:00","13:50","2021-12-10T16:50:00","16:50",4228,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345548561","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2021,2021,5,47,"2021-02-01T21:03:00","21:03","2021-11-26T05:20:00","05:20",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"125 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345549561","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2021,51,49,"2020-12-15T13:50:00","13:50","2021-12-10T16:50:00","16:50",2544,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345545361","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2021,2021,17,43,"2021-04-26T10:05:00","10:05","2021-10-29T17:00:00","17:00",295,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8345623961_8345546961","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2020,2021,51,49,"2020-12-14T13:50:00","13:50","2021-12-08T15:35:00","15:35",1544,"DAY",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
["SNCF Réseau","8345624161_8345504361","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2020,2021,51,49,"2020-12-14T09:35:00","09:35","2021-12-10T10:35:00","10:35",2742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","8345624161_8345505961","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2021,2021,5,47,"2021-02-01T22:00:00","22:00","2021-11-26T04:00:00","04:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"147 jours dans le régime binaire"]
["SNCF Réseau","8345624161_8345505161","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2020,2021,51,49,"2020-12-19T09:00:00","09:00","2021-12-11T10:35:00","10:35",1091,"DAY",null,null,null,null,null,null,null,null,null,null,null,"104 jours dans le régime binaire"]
["SNCF Réseau","8345626461_8345598161","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2021,2021,42,43,"2021-10-18T08:20:00","08:20","2021-10-29T16:20:00","16:20",154,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8345626461_8345597361","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2020,2021,51,49,"2020-12-14T15:25:00","15:25","2021-12-10T16:35:00","16:35",4163,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8345626461_8345598961","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2021,2021,5,47,"2021-02-01T20:25:00","20:25","2021-11-26T04:55:00","04:55",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"127 jours dans le régime binaire"]
["SNCF Réseau","8344228561_8344101261","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2020,2021,51,49,"2020-12-14T13:48:00","13:48","2021-12-10T15:10:00","15:10",3808,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228561_8344098661","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2020,2021,51,49,"2020-12-14T09:55:00","09:55","2021-12-10T10:43:00","10:43",2690,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228561_8344097861","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2020,2021,52,40,"2020-12-27T23:15:00","23:15","2021-10-10T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344228561_8344100261","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2021,2021,3,49,"2021-01-18T22:50:00","22:50","2021-12-08T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8344228561_8344099461","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2020,2021,52,40,"2020-12-27T23:35:00","23:35","2021-10-10T02:45:00","02:45",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344052461","Amiens-Douai",">","Arras","Douai",2020,2021,52,48,"2020-12-21T01:30:00","01:30","2021-11-29T04:30:00","04:30",34,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344053261","Amiens-Douai",">","Arras","Douai",2020,2021,51,49,"2020-12-14T09:50:00","09:50","2021-12-10T10:56:00","10:56",2734,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344055661","Amiens-Douai",">","Arras","Douai",2020,2021,52,48,"2020-12-21T00:35:00","00:35","2021-11-29T03:20:00","03:20",26,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344056461","Amiens-Douai",">","Arras","Douai",2020,2021,51,49,"2020-12-14T14:29:00","14:29","2021-12-10T15:20:00","15:20",3834,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344054861","Amiens-Douai",">","Arras","Douai",2021,2021,20,49,"2021-05-17T23:00:00","23:00","2021-12-10T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"39 jours dans le régime binaire"]
["SNCF Réseau","8344229061_8344054061","Amiens-Douai",">","Arras","Douai",2021,2021,20,49,"2021-05-17T22:50:00","22:50","2021-12-10T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"39 jours dans le régime binaire"]
["SNCF Réseau","8344227761_8344003861","Amiens-Douai","<","Arras","Bif de l'arbre Robert",2020,2021,51,49,"2020-12-14T14:40:00","14:40","2021-12-10T15:37:00","15:37",3920,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344122061","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2021,2021,10,49,"2021-03-08T22:50:00","22:50","2021-12-10T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344121261","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2021,52,40,"2020-12-27T22:50:00","22:50","2021-10-10T01:40:00","01:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344120461","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2021,52,40,"2020-12-27T23:10:00","23:10","2021-10-10T02:20:00","02:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344118061","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2021,51,49,"2020-12-14T14:21:00","14:21","2021-12-10T15:26:00","15:26",3874,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344119661","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2020,2021,51,49,"2020-12-14T10:37:00","10:37","2021-12-10T11:31:00","11:31",2891,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228161_8344118861","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2021,2021,10,49,"2021-03-08T22:50:00","22:50","2021-12-10T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343971861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T10:05:00","10:05","2021-12-10T11:20:00","11:20",2845,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343966861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T09:58:00","09:58","2021-12-10T11:05:00","11:05",2783,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343968461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T00:10:00","00:10","2021-12-06T03:20:00","03:20",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343969261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T14:05:00","14:05","2021-12-10T14:55:00","14:55",3744,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343973461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T01:30:00","01:30","2021-12-06T04:25:00","04:25",86,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343965261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T14:20:00","14:20","2021-12-10T15:15:00","15:15",3828,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343972661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T00:05:00","00:05","2021-12-06T03:10:00","03:10",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343964461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T00:35:00","00:35","2021-12-06T03:20:00","03:20",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343967661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T14:18:00","14:18","2021-12-10T15:03:00","15:03",3778,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343974261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T00:20:00","00:20","2021-12-06T03:30:00","03:30",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343966061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T01:20:00","01:20","2021-12-06T04:05:00","04:05",80,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343970061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,44,"2020-12-14T23:39:00","23:39","2021-11-05T04:59:00","04:59",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"140 jours dans le régime binaire"]
["SNCF Réseau","8344228661_8343971061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2020,2021,51,49,"2020-12-14T10:15:00","10:15","2021-12-10T11:27:00","11:27",2875,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227361_8344103461","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344227361_8344106061","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2020,2021,51,49,"2020-12-14T13:30:00","13:30","2021-12-10T14:24:00","14:24",3615,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227361_8344105261","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2021,2021,16,43,"2021-04-19T11:00:00","11:00","2021-10-29T15:00:00","15:00",859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8344227361_8344106861","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2020,2021,51,49,"2020-12-14T11:30:00","11:30","2021-12-10T12:37:00","12:37",3167,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227361_8344104461","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2021,2021,16,43,"2021-04-19T11:00:00","11:00","2021-10-29T15:00:00","15:00",859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8344226061_8343892261","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2021,2021,3,43,"2021-01-18T09:25:00","09:25","2021-10-29T13:40:00","13:40",1111,"DAY",null,null,null,null,null,null,null,null,null,null,null,"82 jours dans le régime binaire"]
["SNCF Réseau","8344226061_8343893061","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2020,2021,51,49,"2020-12-14T14:34:00","14:34","2021-12-10T15:44:00","15:44",3950,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344226061_8343891461","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2021,2021,3,43,"2021-01-18T09:40:00","09:40","2021-10-29T13:25:00","13:25",1010,"DAY",null,null,null,null,null,null,null,null,null,null,null,"76 jours dans le régime binaire"]
["SNCF Réseau","8344226061_8343893861","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2020,2021,51,49,"2020-12-14T10:02:00","10:02","2021-12-10T10:52:00","10:52",2728,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228261_8344061461","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2020,2021,51,49,"2020-12-14T14:20:00","14:20","2021-12-10T15:09:00","15:09",3803,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228261_8344058061","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2020,2021,51,41,"2020-12-14","00:00","2021-10-11T03:00:00","03:00",42,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344228261_8344058861","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2021,2021,3,44,"2021-01-18T22:50:00","22:50","2021-11-05T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","8344228261_8344060661","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2020,2021,51,49,"2020-12-14T09:36:00","09:36","2021-12-10T10:43:00","10:43",2691,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228261_8344059861","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2020,2021,51,41,"2020-12-14","00:00","2021-10-11T03:00:00","03:00",42,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344226361_8344029661","Paris-Busigny",">","Creil","LongueilSteMarie",2020,2021,51,49,"2020-12-14T01:35:00","01:35","2021-12-06T04:20:00","04:20",223,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344226361_8344026261","Paris-Busigny",">","Creil","LongueilSteMarie",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:10:00","03:10",164,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344226361_8344027061","Paris-Busigny",">","Creil","LongueilSteMarie",2020,2021,51,49,"2020-12-14T14:35:00","14:35","2021-12-10T15:20:00","15:20",3849,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344226361_8344027861","Paris-Busigny",">","Creil","LongueilSteMarie",2020,2021,51,49,"2020-12-14T09:46:00","09:46","2021-12-10T10:57:00","10:57",2749,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227161_8343952261","Paris-Busigny",">","Ormoy","Longueil",2020,2021,51,49,"2020-12-14T10:57:00","10:57","2021-12-10T12:33:00","12:33",3151,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227161_8343953061","Paris-Busigny",">","Ormoy","Longueil",2020,2021,51,49,"2020-12-14T14:20:00","14:20","2021-12-10T16:00:00","16:00",4017,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227161_8343951261","Paris-Busigny",">","Ormoy","Longueil",2020,2021,51,44,"2020-12-14T23:22:00","23:22","2021-11-05T05:10:00","05:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"145 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343903061","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T09:00:00","09:00","2021-12-10T09:46:00","09:46",2452,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343899061","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T09:32:00","09:32","2021-12-10T10:17:00","10:17",2581,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343899861","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,47,"2020-12-20T21:27:00","21:27","2021-11-28T23:57:00","23:57",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343901461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T10:50:00","10:50","2021-12-10T12:00:00","12:00",3013,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343905461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T11:15:00","11:15","2021-12-10T12:25:00","12:25",3117,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343900661","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T09:17:00","09:17","2021-12-10T10:00:00","10:00",2510,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343907261","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2021,2,49,"2021-01-11T10:00:00","10:00","2021-12-10T14:00:00","14:00",536,"DAY",null,null,null,null,null,null,null,null,null,null,null,"39 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343904661","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,49,"2020-12-14T11:00:00","11:00","2021-12-10T12:15:00","12:15",3076,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343903861","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2020,2021,51,47,"2020-12-20T21:28:00","21:28","2021-11-28T01:08:00","01:08",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8344227961_8343906261","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2021,27,32,"2021-07-05T10:45:00","10:45","2021-08-13T15:35:00","15:35",207,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344009861","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:37:00","03:37",71,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344009061","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T10:50:00","10:50","2021-12-10T12:05:00","12:05",3010,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344012661","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T14:09:00","14:09","2021-12-10T14:55:00","14:55",3715,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344011861","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T14:09:00","14:09","2021-12-10T14:55:00","14:55",3715,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344007861","Paris-Busigny",">","StQuentin","Busigny",2021,2021,10,43,"2021-03-08T23:46:00","23:46","2021-10-29T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344013461","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T01:00:00","01:00","2021-12-06T03:54:00","03:54",77,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344006261","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T00:54:00","00:54","2021-12-06T03:45:00","03:45",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344007061","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T00:37:00","00:37","2021-12-06T03:45:00","03:45",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344227261_8344010661","Paris-Busigny",">","StQuentin","Busigny",2020,2021,51,49,"2020-12-14T10:50:00","10:50","2021-12-10T12:05:00","12:05",3010,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344228061_8344127061","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2020,2021,51,49,"2020-12-14T10:02:00","10:02","2021-12-10T11:12:00","11:12",2801,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344228061_8344126261","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2020,2021,52,48,"2020-12-21T01:35:00","01:35","2021-11-29T04:55:00","04:55",106,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344228061_8344124661","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2020,2021,51,49,"2020-12-14T14:14:00","14:14","2021-12-10T14:58:00","14:58",3742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344228061_8344127861","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2021,2021,2,46,"2021-01-11T22:58:00","22:58","2021-11-19T04:58:00","04:58",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"79 jours dans le régime binaire"]
["SNCF Réseau","8344228061_8344125461","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2020,2021,52,48,"2020-12-21","00:00","2021-11-29T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344088861","Boulogne-Calais",">","Marquise","Calais",2021,2021,1,39,"2021-01-04T23:08:00","23:08","2021-10-01T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344092261","Boulogne-Calais",">","Marquise","Calais",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344090661","Boulogne-Calais",">","Marquise","Calais",2020,2021,51,49,"2020-12-14T14:27:00","14:27","2021-12-10T15:37:00","15:37",3920,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344089661","Boulogne-Calais",">","Marquise","Calais",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344091461","Boulogne-Calais",">","Marquise","Calais",2020,2021,51,49,"2020-12-14T09:40:00","09:40","2021-12-10T10:35:00","10:35",2657,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344228361_8344088061","Boulogne-Calais",">","Marquise","Calais",2021,2021,1,39,"2021-01-04T23:08:00","23:08","2021-10-01T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343913061","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T00:37:00","00:37","2021-12-06T03:45:00","03:45",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343917061","Paris-Busigny",">","Tergnier","StQuentin",2021,2021,1,43,"2021-01-04T23:26:00","23:26","2021-10-29T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"85 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343910661","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T13:56:00","13:56","2021-12-10T14:46:00","14:46",3677,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343912261","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T10:37:00","10:37","2021-12-10T11:50:00","11:50",2947,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343911461","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:37:00","03:37",71,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343915461","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T00:54:00","00:54","2021-12-06T03:45:00","03:45",74,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343916261","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,51,49,"2020-12-14T01:00:00","01:00","2021-12-06T03:54:00","03:54",77,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343913861","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,53,49,"2020-12-28T10:30:00","10:30","2021-12-10T11:39:00","11:39",2797,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","8344229261_8343914661","Paris-Busigny",">","Tergnier","StQuentin",2020,2021,53,49,"2020-12-28T13:58:00","13:58","2021-12-10T14:44:00","14:44",3536,"DAY",null,null,null,null,null,null,null,null,null,null,null,"241 jours dans le régime binaire"]
["SNCF Réseau","8344225961_8344066661","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2020,2021,51,49,"2020-12-14T14:02:00","14:02","2021-12-10T14:52:00","14:52",3732,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225961_8344068261","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2020,2021,51,37,"2020-12-20T23:00:00","23:00","2021-09-19T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
["SNCF Réseau","8344225961_8344065661","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2021,2021,6,49,"2021-02-08T22:30:00","22:30","2021-12-10T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","8344225961_8344064861","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2020,2021,51,49,"2020-12-14T09:55:00","09:55","2021-12-10T11:05:00","11:05",2783,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225961_8344067461","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2020,2021,52,38,"2020-12-21","00:00","2021-09-20T03:00:00","03:00",24,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","8344225561_8344109461","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2020,2021,51,49,"2020-12-14T09:40:00","09:40","2021-12-10T10:44:00","10:44",2695,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225561_8344108661","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2021,2021,10,43,"2021-03-08T09:30:00","09:30","2021-10-29T13:30:00","13:30",260,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344225561_8344110261","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2020,2021,51,49,"2020-12-14T09:08:00","09:08","2021-12-10T10:40:00","10:40",2678,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225561_8344107861","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2020,2021,52,48,"2020-12-21T01:35:00","01:35","2021-11-29T05:10:00","05:10",65,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344114861","Boulogne-Calais",">","Boulogne","Marquise",2020,2021,51,49,"2020-12-14T09:48:00","09:48","2021-12-10T10:38:00","10:38",2669,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344116461","Boulogne-Calais",">","Boulogne","Marquise",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344115661","Boulogne-Calais",">","Boulogne","Marquise",2020,2021,51,49,"2020-12-14T14:15:00","14:15","2021-12-10T15:35:00","15:35",3912,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344113661","Boulogne-Calais",">","Boulogne","Marquise",2021,2021,1,39,"2021-01-04T22:15:00","22:15","2021-10-01T04:19:00","04:19",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344112061","Boulogne-Calais",">","Boulogne","Marquise",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8344225261_8344112861","Boulogne-Calais",">","Boulogne","Marquise",2021,2021,1,39,"2021-01-04T22:03:00","22:03","2021-10-01T04:38:00","04:38",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8343998461","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2021,51,49,"2020-12-14T00:25:00","00:25","2021-12-06T03:00:00","03:00",155,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8343997661","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2021,51,49,"2020-12-14T00:46:00","00:46","2021-12-06T04:00:00","04:00",207,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8344000061","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2021,51,49,"2020-12-14T14:10:00","14:10","2021-12-10T14:54:00","14:54",3725,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8343999261","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2020,2021,51,49,"2020-12-14T11:02:00","11:02","2021-12-10T12:20:00","12:20",3084,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8343996861","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2021,2021,18,42,"2021-05-03T11:09:00","11:09","2021-10-22T14:58:00","14:58",632,"DAY",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","8344224761_8344000861","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2021,2021,18,42,"2021-05-03T10:47:00","10:47","2021-10-22T14:58:00","14:58",632,"DAY",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","8344225461_8343932661","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8344225461_8343931061","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2020,2021,51,49,"2020-12-14T13:16:00","13:16","2021-12-10T14:08:00","14:08",3548,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225461_8343933661","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2020,2021,51,49,"2020-12-14T11:23:00","11:23","2021-12-10T12:30:00","12:30",3138,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225461_8343931861","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2021,2021,16,43,"2021-04-19T11:00:00","11:00","2021-10-29T15:00:00","15:00",859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8344225461_8343934461","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2021,2021,16,43,"2021-04-19T11:00:00","11:00","2021-10-29T15:00:00","15:00",859,"DAY",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","8344224961_8344094861","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2020,2021,51,49,"2020-12-14T14:46:00","14:46","2021-12-10T15:37:00","15:37",3920,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344224961_8344096461","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2021,2021,11,44,"2021-03-15T09:30:00","09:30","2021-11-05T13:30:00","13:30",247,"DAY",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8344224961_8344095661","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2020,2021,52,48,"2020-12-21T00:30:00","00:30","2021-11-29T03:30:00","03:30",45,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344224961_8344094061","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2020,2021,51,49,"2020-12-14T15:07:00","15:07","2021-12-10T15:41:00","15:41",3937,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343985661","Paris-Amiens",">","Creil","Longueau",2020,2021,51,49,"2020-12-14T14:58:00","14:58","2021-12-10T16:03:00","16:03",4029,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343981661","Paris-Amiens",">","Creil","Longueau",2020,2021,52,48,"2020-12-21T01:45:00","01:45","2021-11-29T04:20:00","04:20",54,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343987261","Paris-Amiens",">","Creil","Longueau",2020,2021,52,48,"2020-12-21T01:20:00","01:20","2021-11-29T04:05:00","04:05",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343980861","Paris-Amiens",">","Creil","Longueau",2020,2021,51,49,"2020-12-14T12:35:00","12:35","2021-12-10T13:56:00","13:56",3498,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343982461","Paris-Amiens",">","Creil","Longueau",2020,2021,51,49,"2020-12-14T11:04:00","11:04","2021-12-10T11:51:00","11:51",2975,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343984061","Paris-Amiens",">","Creil","Longueau",2020,2021,51,49,"2020-12-14T10:50:00","10:50","2021-12-10T11:30:00","11:30",2887,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343986461","Paris-Amiens",">","Creil","Longueau",2020,2021,52,48,"2020-12-21T01:45:00","01:45","2021-11-29T05:15:00","05:15",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343988061","Paris-Amiens",">","Creil","Longueau",2020,2021,52,48,"2020-12-21T02:15:00","02:15","2021-11-29T05:40:00","05:40",71,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343984861","Paris-Amiens",">","Creil","Longueau",2021,2021,5,49,"2021-02-01T22:55:00","22:55","2021-12-10T04:15:00","04:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"115 jours dans le régime binaire"]
["SNCF Réseau","8344225061_8343983261","Paris-Amiens",">","Creil","Longueau",2021,2021,5,49,"2021-02-01T23:10:00","23:10","2021-12-10T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"115 jours dans le régime binaire"]
["SNCF Réseau","8344224461_8344102261","Amiens-Douai",">","Arras","Bif d'Agny",2020,2021,51,49,"2020-12-14T09:46:00","09:46","2021-12-10T10:50:00","10:50",2720,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344021861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",60,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344017861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T13:30:00","13:30","2021-12-10T14:50:00","14:50",3709,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344018661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",73,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344017061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T14:51:00","14:51","2021-12-10T15:44:00","15:44",3934,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344021061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344022661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T14:34:00","14:34","2021-12-10T15:24:00","15:24",3850,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344020261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T14:24:00","14:24","2021-12-10T15:19:00","15:19",3830,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344019461","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T00:35:00","00:35","2021-12-06T03:15:00","03:15",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344023461","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",73,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344015261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T11:10:00","11:10","2021-12-10T12:21:00","12:21",3088,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344024261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8344224561_8344016061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2021,2021,10,44,"2021-03-08T23:17:00","23:17","2021-11-05T05:15:00","05:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"57 jours dans le régime binaire"]
["SNCF Réseau","8328473061_8328261761","Valence - Avignon",">","Raccordement de Livron","LaVoulte",2021,2021,9,42,"2021-03-01T08:40:00","08:40","2021-10-22T10:10:00","10:10",397,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","8328473061_8328259961","Valence - Avignon",">","Raccordement de Livron","LaVoulte",2021,2021,6,38,"2021-02-08T10:32:00","10:32","2021-09-24T15:32:00","15:32",377,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328376361","Valence - Avignon",">","Portes","Livron (par RG)",2020,2021,51,49,"2020-12-14T12:34:00","12:34","2021-12-10T13:40:00","13:40",3185,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328375561","Valence - Avignon",">","Portes","Livron (par RG)",2021,2021,53,47,"2021-01-03T23:54:00","23:54","2021-11-28T03:07:00","03:07",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328377161","Valence - Avignon",">","Portes","Livron (par RG)",2021,2021,12,14,"2021-03-22T08:56:00","08:56","2021-04-09T13:37:00","13:37",181,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328377961","Valence - Avignon",">","Portes","Livron (par RG)",2021,2021,12,14,"2021-03-22T10:43:00","10:43","2021-04-09T15:37:00","15:37",207,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328379561","Valence - Avignon",">","Portes","Livron (par RG)",2020,2021,51,49,"2020-12-14T12:05:00","12:05","2021-12-10T12:55:00","12:55",3010,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","8328472561_8328378761","Valence - Avignon",">","Portes","Livron (par RG)",2021,2021,1,48,"2021-01-04T01:55:00","01:55","2021-11-29T04:45:00","04:45",93,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328290761","Valence - Avignon",">","Pierrelatte","Sorgues",2021,2021,1,48,"2021-01-04T00:40:00","00:40","2021-11-29T04:05:00","04:05",89,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328286761","Valence - Avignon",">","Pierrelatte","Sorgues",2021,2021,1,48,"2021-01-04T01:35:00","01:35","2021-11-29T04:17:00","04:17",92,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328289961","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2021,51,49,"2020-12-14T11:17:00","11:17","2021-12-10T11:43:00","11:43",2777,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328289161","Valence - Avignon",">","Pierrelatte","Sorgues",2021,2021,12,14,"2021-03-22T08:32:00","08:32","2021-04-09T12:50:00","12:50",171,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328288361","Valence - Avignon",">","Pierrelatte","Sorgues",2021,2021,12,14,"2021-03-22T11:20:00","11:20","2021-04-09T16:35:00","16:35",220,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472161_8328287561","Valence - Avignon",">","Pierrelatte","Sorgues",2020,2021,51,49,"2020-12-14T13:13:00","13:13","2021-12-10T14:48:00","14:48",3509,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","8328470961_8328404961","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2021,51,49,"2020-12-14T04:05:00","04:05","2021-12-06T06:35:00","06:35",160,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8328470961_8328403161","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2021,51,48,"2020-12-20T21:50:00","21:50","2021-12-05T01:20:00","01:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8328470961_8328405761","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2021,51,35,"2020-12-14T13:28:00","13:28","2021-09-03T13:50:00","13:50",2075,"DAY",null,null,null,null,null,null,null,null,null,null,null,"151 jours dans le régime binaire"]
["SNCF Réseau","8328470961_8328406561","Lyon-Valence",">","Givors","Peyraud (par RD)",2020,2021,51,35,"2020-12-14T11:15:00","11:15","2021-09-03T12:48:00","12:48",2049,"DAY",null,null,null,null,null,null,null,null,null,null,null,"161 jours dans le régime binaire"]
["SNCF Réseau","8328470961_8328403961","Lyon-Valence",">","Givors","Peyraud (par RD)",2021,2021,8,49,"2021-02-22T09:15:00","09:15","2021-12-10T15:15:00","15:15",1256,"DAY",null,null,null,null,null,null,null,null,null,null,null,"83 jours dans le régime binaire"]
["SNCF Réseau","8328471561_8328382761","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2021,51,49,"2020-12-14T12:50:00","12:50","2021-12-10T13:00:00","13:00",2405,"DAY",null,null,null,null,null,null,null,null,null,null,null,"186 jours dans le régime binaire"]
["SNCF Réseau","8328471561_8328381961","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2021,2021,4,43,"2021-01-25T03:35:00","03:35","2021-10-25T05:55:00","05:55",85,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8328471561_8328383561","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2021,2021,7,38,"2021-02-15T08:36:00","08:36","2021-09-24T14:36:00","14:36",706,"DAY",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8328471561_8328384561","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2021,51,49,"2020-12-14T11:49:00","11:49","2021-12-10T13:30:00","13:30",2499,"DAY",null,null,null,null,null,null,null,null,null,null,null,"186 jours dans le régime binaire"]
["SNCF Réseau","8328471561_8328381161","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2020,2021,52,48,"2020-12-27T22:20:00","22:20","2021-12-05T02:00:00","02:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328320761","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2021,1,48,"2021-01-04T02:34:00","02:34","2021-11-29T05:10:00","05:10",111,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328319961","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2021,12,14,"2021-03-22T10:01:00","10:01","2021-04-09T14:29:00","14:29",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328317561","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2021,51,49,"2020-12-14T11:59:00","11:59","2021-12-10T13:28:00","13:28",3139,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328318361","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2021,51,49,"2020-12-14T12:57:00","12:57","2021-12-10T13:32:00","13:32",3153,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328319161","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2021,1,48,"2021-01-04T02:10:00","02:10","2021-11-29T05:10:00","05:10",101,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328321561","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2021,12,14,"2021-03-22T10:05:00","10:05","2021-04-09T15:20:00","15:20",204,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328323161","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2021,53,47,"2021-01-03T23:12:00","23:12","2021-11-28T02:51:00","02:51",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8328472361_8328322361","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2020,2021,51,49,"2020-12-14T12:10:00","12:10","2021-12-10T13:10:00","13:10",3068,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328324961","Valence - Avignon",">","Livron","Pierrelatte",2020,2021,51,49,"2020-12-14T12:41:00","12:41","2021-12-10T14:11:00","14:11",3178,"DAY",null,null,null,null,null,null,null,null,null,null,null,"225 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328327361","Valence - Avignon",">","Livron","Pierrelatte",2021,2021,12,13,"2021-03-22T08:49:00","08:49","2021-04-02T13:17:00","13:17",124,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328326561","Valence - Avignon",">","Livron","Pierrelatte",2021,2021,1,48,"2021-01-04T00:10:00","00:10","2021-11-29T03:40:00","03:40",80,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328325761","Valence - Avignon",">","Livron","Pierrelatte",2020,2021,51,49,"2020-12-14T11:52:00","11:52","2021-12-10T12:20:00","12:20",2763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"225 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328328161","Valence - Avignon",">","Livron","Pierrelatte",2021,2021,1,48,"2021-01-04T02:05:00","02:05","2021-11-29T04:35:00","04:35",89,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328472661_8328328961","Valence - Avignon",">","Livron","Pierrelatte",2021,2021,12,13,"2021-03-22T10:44:00","10:44","2021-04-02T16:02:00","16:02",149,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328353761","Valence - Avignon",">","Sorgues","Avignon",2021,2021,1,48,"2021-01-04T01:17:00","01:17","2021-11-29T04:10:00","04:10",73,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328354561","Valence - Avignon",">","Sorgues","Avignon",2020,2021,51,49,"2020-12-14T13:48:00","13:48","2021-12-10T14:55:00","14:55",3536,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328352161","Valence - Avignon",">","Sorgues","Avignon",2021,2021,1,48,"2021-01-04T01:05:00","01:05","2021-11-29T04:12:00","04:12",91,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328355361","Valence - Avignon",">","Sorgues","Avignon",2020,2021,51,49,"2020-12-14T10:43:00","10:43","2021-12-10T11:37:00","11:37",2754,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328356161","Valence - Avignon",">","Sorgues","Avignon",2021,2021,12,14,"2021-03-22T08:16:00","08:16","2021-04-09T12:50:00","12:50",171,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328471161_8328352961","Valence - Avignon",">","Sorgues","Avignon",2021,2021,12,14,"2021-03-22T11:44:00","11:44","2021-04-09T16:23:00","16:23",217,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328344161","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2021,51,49,"2020-12-14T02:49:00","02:49","2021-12-06T04:59:00","04:59",121,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328344961","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2021,51,49,"2020-12-14T12:33:00","12:33","2021-12-10T14:16:00","14:16",2969,"DAY",null,null,null,null,null,null,null,null,null,null,null,"209 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328343361","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2021,51,49,"2020-12-14T13:16:00","13:16","2021-12-06T14:46:00","14:46",3648,"DAY",null,null,null,null,null,null,null,null,null,null,null,"248 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328340961","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2021,51,49,"2020-12-14T01:59:00","01:59","2021-12-06T04:22:00","04:22",107,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328342561","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2021,51,48,"2020-12-20T23:05:00","23:05","2021-12-05T02:55:00","02:55",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328341761","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2021,51,49,"2020-12-14T00:05:00","00:05","2021-12-06T03:32:00","03:32",84,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328345761","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2021,51,49,"2020-12-14T11:00:00","11:00","2021-12-10T11:22:00","11:22",2853,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328347561","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2020,2021,51,49,"2020-12-14T11:55:00","11:55","2021-12-10T12:00:00","12:00",2496,"DAY",null,null,null,null,null,null,null,null,null,null,null,"209 jours dans le régime binaire"]
["SNCF Réseau","8328472061_8328346561","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2021,2,45,"2021-01-11T09:47:00","09:47","2021-11-12T15:47:00","15:47",1821,"DAY",null,null,null,null,null,null,null,null,null,null,null,"116 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328282161","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2021,51,49,"2020-12-14T11:40:00","11:40","2021-12-10T12:58:00","12:58",2828,"DAY",null,null,null,null,null,null,null,null,null,null,null,"219 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328281361","Lyon-Valence",">","Vienne","St Rambert (par RG)",2021,2021,53,47,"2021-01-03T23:00:00","23:00","2021-11-28T02:20:00","02:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328282961","Lyon-Valence",">","Vienne","St Rambert (par RG)",2021,2021,12,14,"2021-03-22T10:21:00","10:21","2021-04-09T14:55:00","14:55",198,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328284561","Lyon-Valence",">","Vienne","St Rambert (par RG)",2020,2021,52,49,"2020-12-21T13:18:00","13:18","2021-12-10T14:00:00","14:00",2982,"DAY",null,null,null,null,null,null,null,null,null,null,null,"214 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328280561","Lyon-Valence",">","Vienne","St Rambert (par RG)",2021,2021,12,14,"2021-03-22T09:43:00","09:43","2021-04-09T14:55:00","14:55",199,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328471361_8328283761","Lyon-Valence",">","Vienne","St Rambert (par RG)",2021,2021,1,48,"2021-01-04T02:55:00","02:55","2021-11-29T05:35:00","05:35",108,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328387761","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2021,2021,1,48,"2021-01-04T02:57:00","02:57","2021-11-29T05:47:00","05:47",106,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328386161","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2021,2021,12,14,"2021-03-22T09:34:00","09:34","2021-04-09T14:36:00","14:36",194,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328388561","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2021,2021,12,14,"2021-03-22T10:26:00","10:26","2021-04-09T15:16:00","15:16",203,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328389361","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2021,2021,53,47,"2021-01-03T23:06:00","23:06","2021-11-28T02:12:00","02:12",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328386961","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2021,52,49,"2020-12-21T13:26:00","13:26","2021-12-10T14:19:00","14:19",3050,"DAY",null,null,null,null,null,null,null,null,null,null,null,"214 jours dans le régime binaire"]
["SNCF Réseau","8328471461_8328390161","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2020,2021,52,49,"2020-12-21T11:32:00","11:32","2021-12-10T12:38:00","12:38",2692,"DAY",null,null,null,null,null,null,null,null,null,null,null,"214 jours dans le régime binaire"]
["SNCF Réseau","8328471061_8328268561","Lyon-Valence",">","RaccPeyraud","St Rambert",2021,2021,9,10,"2021-03-01T09:58:00","09:58","2021-03-12T14:58:00","14:58",139,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290925961","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2021,51,48,"2020-12-20T23:30:00","23:30","2021-12-05T03:00:00","03:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290921961","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2021,51,49,"2020-12-14T13:15:00","13:15","2021-12-10T13:45:00","13:45",3451,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290925161","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2021,51,49,"2020-12-14T10:57:00","10:57","2021-12-10T12:18:00","12:18",3088,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290923561","Aulnoye-Longuyon",">","Aulnoye","Hirson",2021,2021,10,40,"2021-03-08T09:59:00","09:59","2021-10-08T15:25:00","15:25",606,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290922761","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2021,51,49,"2020-12-14T11:18:00","11:18","2021-12-10T12:30:00","12:30",3138,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290924361","Aulnoye-Longuyon",">","Aulnoye","Hirson",2020,2021,51,49,"2020-12-14T00:55:00","00:55","2021-12-06T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8290982661_8290926761","Aulnoye-Longuyon",">","Aulnoye","Hirson",2021,2021,10,40,"2021-03-08T09:20:00","09:20","2021-10-08T16:00:00","16:00",630,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290787361","Aulnoye-Longuyon",">","Hirson","Liart",2021,2021,7,40,"2021-02-15T09:10:00","09:10","2021-10-08T14:35:00","14:35",647,"DAY",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290786561","Aulnoye-Longuyon",">","Hirson","Liart",2020,2021,51,49,"2020-12-14T11:45:00","11:45","2021-12-10T13:05:00","13:05",3285,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290788961","Aulnoye-Longuyon",">","Hirson","Liart",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:15:00","03:15",168,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290788161","Aulnoye-Longuyon",">","Hirson","Liart",2021,2021,7,40,"2021-02-15T09:30:00","09:30","2021-10-08T14:37:00","14:37",648,"DAY",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290789761","Aulnoye-Longuyon",">","Hirson","Liart",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:20:00","03:20",173,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8290980461_8290790561","Aulnoye-Longuyon",">","Hirson","Liart",2020,2021,51,49,"2020-12-14T14:25:00","14:25","2021-12-10T15:00:00","15:00",3765,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290907761","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,48,"2020-12-20T23:40:00","23:40","2021-12-05T02:40:00","02:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290909361","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,49,"2020-12-14T13:24:00","13:24","2021-12-10T14:11:00","14:11",3433,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290910961","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2021,7,40,"2021-02-15T10:07:00","10:07","2021-10-08T14:15:00","14:15",916,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290906161","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,48,"2020-12-20T23:40:00","23:40","2021-12-05T02:40:00","02:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290912561","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,49,"2020-12-14T13:25:00","13:25","2021-12-10T14:24:00","14:24",3485,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290908561","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,48,"2020-12-20T23:50:00","23:50","2021-12-05T02:50:00","02:50",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290906961","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2021,7,40,"2021-02-15T10:40:00","10:40","2021-10-08T14:30:00","14:30",931,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290910161","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,48,"2020-12-20T23:50:00","23:50","2021-12-05T02:50:00","02:50",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290981761_8290911761","Aulnoye-Longuyon",">","Mohon","Sedan",2020,2021,51,49,"2020-12-14T13:36:00","13:36","2021-12-10T14:51:00","14:51",3580,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290846361","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2021,51,49,"2020-12-14T13:43:00","13:43","2021-12-10T14:09:00","14:09",3552,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290845561","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2021,2021,12,47,"2021-03-22T23:04:00","23:04","2021-11-26T04:23:00","04:23",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290843961","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2021,51,49,"2020-12-14T10:15:00","10:15","2021-12-10T11:50:00","11:50",2971,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290844761","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2021,52,48,"2020-12-27T23:00:00","23:00","2021-12-05T02:32:00","02:32",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290843161","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2020,2021,51,49,"2020-12-14T01:36:00","01:36","2021-12-06T04:13:00","04:13",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8290981361_8290847161","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2021,2021,12,47,"2021-03-22T22:21:00","22:21","2021-11-26T05:35:00","05:35",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"100 jours dans le régime binaire"]
["SNCF Réseau","8290980361_8290903161","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2020,2021,51,49,"2020-12-14T14:30:00","14:30","2021-12-10T15:50:00","15:50",3959,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290980361_8290900561","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2020,2021,51,49,"2020-12-14T13:57:00","13:57","2021-12-10T14:37:00","14:37",3654,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290980361_8290903961","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2020,2021,52,48,"2020-12-21","00:00","2021-11-29T03:10:00","03:10",60,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8290980361_8290902361","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2020,2021,52,48,"2020-12-21","00:00","2021-11-29T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8290980361_8290901361","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2021,2021,7,44,"2021-02-15T23:00:00","23:00","2021-11-05T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8290981261_8290801961","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2020,2021,51,49,"2020-12-14T10:30:00","10:30","2021-12-10T11:05:00","11:05",2782,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981261_8290803561","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2021,2021,5,47,"2021-02-01T23:05:00","23:05","2021-11-26T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","8290981261_8290804561","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8290981261_8290802761","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2020,2021,51,49,"2020-12-14T11:22:00","11:22","2021-12-10T12:48:00","12:48",3214,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981261_8290801161","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2020,2021,51,49,"2020-12-14T01:10:00","01:10","2021-12-06T04:10:00","04:10",203,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8290980261_8290880961","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2020,2021,51,41,"2020-12-14T01:00:00","01:00","2021-10-11T04:00:00","04:00",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8290980261_8290879961","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2021,2021,2,46,"2021-01-11T22:43:00","22:43","2021-11-19T04:43:00","04:43",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8290980261_8290881761","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2020,2021,51,49,"2020-12-14T09:52:00","09:52","2021-12-10T11:00:00","11:00",2751,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290980261_8290882561","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2020,2021,51,41,"2020-12-14T00:20:00","00:20","2021-10-11T03:00:00","03:00",38,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8290980261_8290883361","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2020,2021,51,49,"2020-12-14T14:25:00","14:25","2021-12-10T15:08:00","15:08",3784,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290981661_8290797361","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2020,2021,51,49,"2020-12-14T14:20:00","14:20","2021-12-10T15:25:00","15:25",3855,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290981661_8290796561","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2020,2021,51,49,"2020-12-14T14:04:00","14:04","2021-12-10T14:55:00","14:55",3730,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8290981661_8290799961","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2021,2021,7,45,"2021-02-15","00:00","2021-11-08T03:00:00","03:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","8290981661_8290799161","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2021,2021,7,45,"2021-02-15","00:00","2021-11-08T03:10:00","03:10",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","8290981661_8290798161","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2021,2021,10,43,"2021-03-08T23:30:00","23:30","2021-10-29T05:15:00","05:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290825161","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,49,"2020-12-14T13:51:00","13:51","2021-12-10T14:40:00","14:40",3682,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290826761","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,47,"2020-12-20T23:50:00","23:50","2021-11-28T03:15:00","03:15",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290825961","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,49,"2020-12-14T10:38:00","10:38","2021-12-10T11:48:00","11:48",2962,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290829361","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,49,"2020-12-14T13:07:00","13:07","2021-12-10T13:57:00","13:57",3502,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290828561","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,47,"2020-12-20T00:15:00","00:15","2021-11-28T02:45:00","02:45",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290827561","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2021,2021,8,48,"2021-02-22T23:00:00","23:00","2021-12-03T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","8290980761_8290830161","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2020,2021,51,49,"2020-12-14T10:11:00","10:11","2021-12-10T11:24:00","11:24",2862,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290884561","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2021,2021,10,40,"2021-03-08T10:21:00","10:21","2021-10-08T15:14:00","15:14",446,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290888561","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2021,51,49,"2020-12-14T01:10:00","01:10","2021-12-06T03:45:00","03:45",193,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290886961","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:28:00","02:28",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290885361","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2021,2021,10,40,"2021-03-08T08:50:00","08:50","2021-10-08T15:05:00","15:05",443,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290886161","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2021,51,49,"2020-12-14T13:45:00","13:45","2021-12-10T14:18:00","14:18",3589,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981161_8290887761","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2020,2021,51,49,"2020-12-14T10:37:00","10:37","2021-12-10T12:05:00","12:05",3034,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981561_8290890961","Calais-Lille-Aulnoye",">","Lille Lambersart",null,2020,2021,51,49,"2020-12-14T11:05:00","11:05","2021-12-10T12:00:00","12:00",3012,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981561_8290890161","Calais-Lille-Aulnoye",">","Lille Lambersart",null,2020,2021,51,49,"2020-12-14T10:19:00","10:19","2021-12-10T11:15:00","11:15",2824,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290895361","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2021,2021,12,49,"2021-03-22T22:45:00","22:45","2021-12-10T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290899361","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2021,51,49,"2020-12-14T00:06:00","00:06","2021-12-06T03:30:00","03:30",52,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290898561","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2021,51,49,"2020-12-14T11:05:00","11:05","2021-12-10T12:28:00","12:28",3130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290897761","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2021,51,49,"2020-12-14T01:00:00","01:00","2021-12-06T03:30:00","03:30",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290896161","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2020,2021,51,49,"2020-12-14T10:12:00","10:12","2021-12-10T10:53:00","10:53",2732,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290981461_8290896961","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2021,2021,12,49,"2021-03-22T22:12:00","22:12","2021-12-10T04:40:00","04:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290780561","Aulnoye-Longuyon",">","Liart","Tournes",2021,2021,7,40,"2021-02-15T09:35:00","09:35","2021-10-08T14:54:00","14:54",660,"DAY",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290777361","Aulnoye-Longuyon",">","Liart","Tournes",2021,2021,7,40,"2021-02-15T09:37:00","09:37","2021-10-08T14:20:00","14:20",635,"DAY",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290779761","Aulnoye-Longuyon",">","Liart","Tournes",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290778161","Aulnoye-Longuyon",">","Liart","Tournes",2020,2021,51,49,"2020-12-14T12:05:00","12:05","2021-12-10T13:21:00","13:21",3231,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290778961","Aulnoye-Longuyon",">","Liart","Tournes",2020,2021,51,48,"2020-12-20T23:55:00","23:55","2021-12-05T02:55:00","02:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290982961_8290781361","Aulnoye-Longuyon",">","Liart","Tournes",2020,2021,51,49,"2020-12-14T14:00:00","14:00","2021-12-10T14:40:00","14:40",3550,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290855161","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290853561","Aulnoye-Longuyon",">","Tournes","Charleville",2021,2021,7,40,"2021-02-15T10:00:00","10:00","2021-10-08T14:54:00","14:54",884,"DAY",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290856761","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2021,51,49,"2020-12-14T12:25:00","12:25","2021-12-10T13:21:00","13:21",3231,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290852761","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2021,51,49,"2020-12-14T13:35:00","13:35","2021-12-10T14:40:00","14:40",3550,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290855961","Aulnoye-Longuyon",">","Tournes","Charleville",2021,2021,7,40,"2021-02-15T09:15:00","09:15","2021-10-08T14:20:00","14:20",850,"DAY",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8290982361_8290854361","Aulnoye-Longuyon",">","Tournes","Charleville",2020,2021,51,48,"2020-12-20T23:55:00","23:55","2021-12-05T02:55:00","02:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290835161","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T12:45:00","12:45","2021-12-10T14:15:00","14:15",3435,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290836761","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T13:00:00","13:00","2021-12-10T14:15:00","14:15",3578,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290833561","Aulnoye-Longuyon",">","Sedan","Longuyon",2021,2021,7,49,"2021-02-15T09:15:00","09:15","2021-12-10T13:30:00","13:30",935,"DAY",null,null,null,null,null,null,null,null,null,null,null,"70 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290839161","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T00:10:00","00:10","2021-12-06T03:10:00","03:10",151,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290838361","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T00:10:00","00:10","2021-12-06T03:10:00","03:10",151,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290835961","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290832761","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T13:15:00","13:15","2021-12-10T13:45:00","13:45",3314,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290831961","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,49,"2020-12-14T12:45:00","12:45","2021-12-10T13:30:00","13:30",3389,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290837561","Aulnoye-Longuyon",">","Sedan","Longuyon",2020,2021,51,48,"2020-12-20T23:00:00","23:00","2021-12-05T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8290982761_8290834361","Aulnoye-Longuyon",">","Sedan","Longuyon",2021,2021,7,49,"2021-02-15T10:15:00","10:15","2021-12-10T16:00:00","16:00",1109,"DAY",null,null,null,null,null,null,null,null,null,null,null,"70 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342201661","Lerouville-Metz",">","Lerouville","Noveant",2020,2021,51,49,"2020-12-14T10:16:00","10:16","2021-12-10T11:05:00","11:05",2782,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342202461","Lerouville-Metz",">","Lerouville","Noveant",2021,2021,4,42,"2021-01-31T22:38:00","22:38","2021-10-24T01:02:00","01:02",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342199261","Lerouville-Metz",">","Lerouville","Noveant",2020,2021,51,49,"2020-12-14T13:35:00","13:35","2021-12-10T15:02:00","15:02",3774,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342200861","Lerouville-Metz",">","Lerouville","Noveant",2020,2021,51,49,"2020-12-14T10:42:00","10:42","2021-12-10T11:16:00","11:16",2828,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342198461","Lerouville-Metz",">","Lerouville","Noveant",2020,2021,51,49,"2020-12-14T14:02:00","14:02","2021-12-10T15:08:00","15:08",3799,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342200061","Lerouville-Metz",">","Lerouville","Noveant",2021,2021,4,42,"2021-01-31T23:27:00","23:27","2021-10-24T02:59:00","02:59",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","8342647361_8342197461","Lerouville-Metz",">","Lerouville","Noveant",2021,2021,3,45,"2021-01-18T23:00:00","23:00","2021-11-12T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342292361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,4,41,"2021-01-26T11:30:00","11:30","2021-10-15T15:30:00","15:30",763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342295561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342290761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342288361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2021,51,46,"2020-12-14T14:20:00","14:20","2021-11-19T15:15:00","15:15",2791,"DAY",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342294761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342289961","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2021,53,49,"2020-12-28T13:45:00","13:45","2021-12-10T14:49:00","14:49",2534,"DAY",null,null,null,null,null,null,null,null,null,null,null,"172 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342291561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,4,41,"2021-01-26T11:30:00","11:30","2021-10-15T15:30:00","15:30",763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342293161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342296361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342289161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342287561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2021,51,46,"2020-12-14T11:30:00","11:30","2021-11-19T12:34:00","12:34",2300,"DAY",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","8342650161_8342293961","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2020,2021,51,46,"2020-12-15T09:15:00","09:15","2021-11-19T10:11:00","10:11",1019,"DAY",null,null,null,null,null,null,null,null,null,null,null,"101 jours dans le régime binaire"]
["SNCF Réseau","8342648361_8342249961","Lerouville-Nancy",">","Frouard","Jarville",2021,2021,6,49,"2021-02-08T23:11:00","23:11","2021-12-10T05:07:00","05:07",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
["SNCF Réseau","8342648361_8342249161","Lerouville-Nancy",">","Frouard","Jarville",2021,2021,6,49,"2021-02-08T23:05:00","23:05","2021-12-10T05:16:00","05:16",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342270961","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342268561","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342267761","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342269361","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2021,51,46,"2020-12-14T14:05:00","14:05","2021-11-19T15:05:00","15:05",2761,"DAY",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342270161","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2021,51,46,"2020-12-15T09:17:00","09:17","2021-11-19T10:14:00","10:14",1044,"DAY",null,null,null,null,null,null,null,null,null,null,null,"103 jours dans le régime binaire"]
["SNCF Réseau","8342652061_8342266961","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2020,2021,51,46,"2020-12-14T11:28:00","11:28","2021-11-19T12:29:00","12:29",2285,"DAY",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","8342646661_8342120661","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2020,2021,51,49,"2020-12-14T14:05:00","14:05","2021-12-10T15:55:00","15:55",3949,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8342646661_8342121461","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2021,2021,10,45,"2021-03-08T23:40:00","23:40","2021-11-10T05:10:00","05:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
["SNCF Réseau","8342646661_8342119861","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2021,2021,10,45,"2021-03-08T22:55:00","22:55","2021-11-10T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"74 jours dans le régime binaire"]
["SNCF Réseau","8342646661_8342122261","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2020,2021,51,49,"2020-12-14T11:42:00","11:42","2021-12-10T12:07:00","12:07",3029,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8342647661_8342139061","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2021,2021,7,49,"2021-02-15T10:10:00","10:10","2021-12-10T16:10:00","16:10",1574,"DAY",null,null,null,null,null,null,null,null,null,null,null,"98 jours dans le régime binaire"]
["SNCF Réseau","8342647661_8342140061","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2021,2021,24,49,"2021-06-14T00:30:00","00:30","2021-12-06T03:30:00","03:30",55,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8342647661_8342138261","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2021,2021,24,49,"2021-06-14","00:00","2021-12-06T03:00:00","03:00",48,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8342647661_8342141661","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2020,2021,51,49,"2020-12-14T12:17:00","12:17","2021-12-10T12:49:00","12:49",3217,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647661_8342140861","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2020,2021,51,49,"2020-12-14T14:05:00","14:05","2021-12-10T15:32:00","15:32",3900,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342394361","Dijon-Toul",">","NeufChateau","Toul",2021,2021,9,29,"2021-03-01T09:17:00","09:17","2021-07-23T13:15:00","13:15",441,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342395161","Dijon-Toul",">","NeufChateau","Toul",2021,2021,9,29,"2021-03-01T14:15:00","14:15","2021-07-23T19:41:00","19:41",654,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342393561","Dijon-Toul",">","NeufChateau","Toul",2020,2021,52,49,"2020-12-21T01:46:00","01:46","2021-12-06T05:12:00","05:12",242,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342396761","Dijon-Toul",">","NeufChateau","Toul",2020,2021,51,49,"2020-12-14T10:08:00","10:08","2021-12-10T10:34:00","10:34",2557,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342392761","Dijon-Toul",">","NeufChateau","Toul",2020,2021,51,48,"2020-12-20T23:52:00","23:52","2021-12-05T01:34:00","01:34",23,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342648961_8342395961","Dijon-Toul",">","NeufChateau","Toul",2020,2021,51,49,"2020-12-14T14:15:00","14:15","2021-12-10T15:44:00","15:44",3808,"DAY",null,null,null,null,null,null,null,null,null,null,null,"243 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342064661","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2021,2021,7,49,"2021-02-15T10:12:00","10:12","2021-12-10T16:12:00","16:12",1172,"DAY",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342063061","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2021,2021,24,49,"2021-06-14T00:50:00","00:50","2021-12-06T03:25:00","03:25",53,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342061461","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2021,2021,24,49,"2021-06-14T00:25:00","00:25","2021-12-06T03:50:00","03:50",60,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342060661","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2021,51,49,"2020-12-14T11:15:00","11:15","2021-12-10T11:55:00","11:55",2991,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342065661","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2021,2021,24,49,"2021-06-14","00:00","2021-12-06T03:00:00","03:00",48,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342062261","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2021,51,49,"2020-12-14T14:00:00","14:00","2021-12-10T15:20:00","15:20",3850,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342063861","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2021,51,49,"2020-12-14T14:17:00","14:17","2021-12-10T15:28:00","15:28",3883,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342066461","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2021,2021,23,48,"2021-06-13T23:43:00","23:43","2021-12-05T02:23:00","02:23",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8342647561_8342067261","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2020,2021,51,49,"2020-12-14T10:55:00","10:55","2021-12-10T11:50:00","11:50",2971,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649561_8342255361","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2021,51,49,"2020-12-14T10:45:00","10:45","2021-12-10T11:47:00","11:47",2958,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649561_8342253161","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2021,51,46,"2020-12-14T00:03:00","00:03","2021-11-15T03:00:00","03:00",32,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342649561_8342252361","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2021,51,49,"2020-12-14T14:16:00","14:16","2021-12-10T15:11:00","15:11",3811,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649561_8342253961","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2021,2021,6,41,"2021-02-08T23:45:00","23:45","2021-10-15T05:45:00","05:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342649561_8342251561","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2020,2021,51,46,"2020-12-14T00:24:00","00:24","2021-11-15T03:30:00","03:30",38,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342316161","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2021,2021,7,49,"2021-02-15T10:00:00","10:00","2021-12-10T15:30:00","15:30",1121,"DAY",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342317761","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2021,2021,7,49,"2021-02-15T09:40:00","09:40","2021-12-10T16:10:00","16:10",1170,"DAY",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342318561","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2021,51,49,"2020-12-14T13:35:00","13:35","2021-12-10T15:05:00","15:05",3787,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342316961","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2021,2021,24,49,"2021-06-14T02:08:00","02:08","2021-12-06T04:31:00","04:31",70,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342319361","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2020,2021,51,49,"2020-12-14T11:52:00","11:52","2021-12-10T12:15:00","12:15",3075,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647761_8342315361","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2021,2021,23,48,"2021-06-13T23:00:00","23:00","2021-12-05T02:30:00","02:30",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342355761","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2021,2021,6,49,"2021-02-08T23:46:00","23:46","2021-12-10T06:20:00","06:20",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342350961","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,49,"2020-12-14T00:20:00","00:20","2021-12-06T03:50:00","03:50",133,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342354961","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,48,"2020-12-20T22:40:00","22:40","2021-12-05T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342356561","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,49,"2020-12-14T09:47:00","09:47","2021-12-10T11:00:00","11:00",2762,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342354161","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,49,"2020-12-14T09:33:00","09:33","2021-12-10T10:47:00","10:47",2707,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342351761","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2021,2021,6,49,"2021-02-08T23:09:00","23:09","2021-12-10T04:35:00","04:35",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342353361","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,49,"2020-12-14T14:10:00","14:10","2021-12-10T15:00:00","15:00",3765,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647061_8342352561","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2020,2021,51,49,"2020-12-14T14:25:00","14:25","2021-12-10T15:10:00","15:10",3807,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650861_8342402361","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2021,2021,13,49,"2021-03-29T23:27:00","23:27","2021-12-10T05:27:00","05:27",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342650861_8342400761","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2020,2021,51,49,"2020-12-14T09:03:00","09:03","2021-12-10T09:55:00","09:55",2470,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8342650861_8342399961","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2021,2021,13,49,"2021-03-29T23:43:00","23:43","2021-12-10T05:29:00","05:29",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"63 jours dans le régime binaire"]
["SNCF Réseau","8342650861_8342401561","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2020,2021,51,49,"2020-12-14T14:00:00","14:00","2021-12-10T15:05:00","15:05",3756,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8342651861_8342185061","Lerouville-Nancy",">","Toul","Frouard",2020,2021,51,49,"2020-12-14T14:59:00","14:59","2021-12-10T15:42:00","15:42",3941,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651861_8342183461","Lerouville-Nancy",">","Toul","Frouard",2020,2021,51,49,"2020-12-14T08:58:00","08:58","2021-12-10T10:16:00","10:16",2578,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651861_8342182461","Lerouville-Nancy",">","Toul","Frouard",2021,2021,6,42,"2021-02-08T23:00:00","23:00","2021-10-22T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","8342651861_8342184261","Lerouville-Nancy",">","Toul","Frouard",2020,2021,51,45,"2020-12-20T22:54:00","22:54","2021-11-14T01:40:00","01:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8342651861_8342181661","Lerouville-Nancy",">","Toul","Frouard",2020,2021,51,45,"2020-12-20T22:55:00","22:55","2021-11-14T02:06:00","02:06",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8342649761_8342112061","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2021,2021,29,44,"2021-07-25T22:45:00","22:45","2021-11-07T02:01:00","02:01",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8342649761_8342112861","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2020,2021,51,49,"2020-12-14T10:51:00","10:51","2021-12-10T11:41:00","11:41",2921,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8342649761_8342110461","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2021,2021,30,45,"2021-07-26T00:15:00","00:15","2021-11-08T03:00:00","03:00",11,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8342649761_8342109461","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2021,2021,10,45,"2021-03-08T23:00:00","23:00","2021-11-10T05:40:00","05:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8342649761_8342111261","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2020,2021,51,49,"2020-12-14T14:07:00","14:07","2021-12-10T15:17:00","15:17",3822,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8342651361_8342206661","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2020,2021,51,49,"2020-12-14T13:35:00","13:35","2021-12-10T14:38:00","14:38",3674,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651361_8342207461","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2020,2021,51,48,"2020-12-20T23:56:00","23:56","2021-12-05T02:56:00","02:56",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342651361_8342208261","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2020,2021,51,48,"2020-12-20T23:56:00","23:56","2021-12-05T02:56:00","02:56",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342651361_8342209061","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2020,2021,51,49,"2020-12-14T09:25:00","09:25","2021-12-10T10:22:00","10:22",2602,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651361_8342205661","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2021,2021,6,37,"2021-02-08T23:26:00","23:26","2021-09-17T05:26:00","05:26",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342307361","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2021,51,49,"2020-12-14T09:10:00","09:10","2021-12-10T10:08:00","10:08",1865,"DAY",null,null,null,null,null,null,null,null,null,null,null,"185 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342304161","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,4,49,"2021-01-25","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342303361","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,11,46,"2021-03-15T09:30:00","09:30","2021-11-15T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342308961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,11,46,"2021-03-15T09:30:00","09:30","2021-11-15T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342308161","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2021,51,43,"2020-12-14","00:00","2021-10-25T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342304961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2021,51,43,"2020-12-14","00:00","2021-10-25T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342302561","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2021,51,45,"2020-12-14T11:35:00","11:35","2021-11-12T12:38:00","12:38",2009,"DAY",null,null,null,null,null,null,null,null,null,null,null,"160 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342309761","Longuyon-Metz-Sarrebourg","<","Uckange",null,2020,2021,51,49,"2020-12-14T13:50:00","13:50","2021-12-10T14:52:00","14:52",2498,"DAY",null,null,null,null,null,null,null,null,null,null,null,"169 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342306561","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,16,45,"2021-04-19T09:30:00","09:30","2021-11-08T15:30:00","15:30",52,"DAY",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8342651261_8342305761","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2021,16,45,"2021-04-19T09:30:00","09:30","2021-11-08T15:30:00","15:30",52,"DAY",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342153861","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2021,51,49,"2020-12-14T13:51:00","13:51","2021-12-10T14:53:00","14:53",3215,"DAY",null,null,null,null,null,null,null,null,null,null,null,"217 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342145061","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,11,46,"2021-03-16T11:30:00","11:30","2021-11-19T15:30:00","15:30",407,"DAY",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342149861","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,11,46,"2021-03-16T11:30:00","11:30","2021-11-19T15:30:00","15:30",407,"DAY",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342150661","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,11,46,"2021-03-15T09:30:00","09:30","2021-11-15T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342151461","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,4,49,"2021-01-25","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342153061","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,11,46,"2021-03-15T09:30:00","09:30","2021-11-15T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342145861","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2021,53,49,"2020-12-28T14:15:00","14:15","2021-12-10T15:05:00","15:05",3092,"DAY",null,null,null,null,null,null,null,null,null,null,null,"206 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342148261","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2021,53,49,"2020-12-28T11:37:00","11:37","2021-12-10T12:44:00","12:44",2611,"DAY",null,null,null,null,null,null,null,null,null,null,null,"206 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342147461","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2020,2021,51,49,"2020-12-14T09:09:00","09:09","2021-12-10T10:07:00","10:07",1842,"DAY",null,null,null,null,null,null,null,null,null,null,null,"183 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342152261","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,16,45,"2021-04-20T11:30:00","11:30","2021-11-10T15:30:00","15:30",267,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342144261","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,16,45,"2021-04-20T11:30:00","11:30","2021-11-10T15:30:00","15:30",267,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342146661","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,16,45,"2021-04-19T09:30:00","09:30","2021-11-08T15:30:00","15:30",52,"DAY",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8342651561_8342149061","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2021,16,45,"2021-04-19T09:30:00","09:30","2021-11-08T15:30:00","15:30",52,"DAY",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342215661","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,52,49,"2020-12-21T00:27:00","00:27","2021-12-06T03:05:00","03:05",144,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342216461","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,52,49,"2020-12-21T01:03:00","01:03","2021-12-06T04:25:00","04:25",206,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342221261","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,51,49,"2020-12-14T10:37:00","10:37","2021-12-10T11:08:00","11:08",2794,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342214861","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,51,49,"2020-12-14T13:25:00","13:25","2021-12-10T14:48:00","14:48",3716,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342217261","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,51,48,"2020-12-20T00:05:00","00:05","2021-12-05T02:37:00","02:37",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342218861","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,51,49,"2020-12-14T13:48:00","13:48","2021-12-10T15:15:00","15:15",3829,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342218061","Dijon-Toul",">","Culmont","NeufChateau",2021,2021,9,29,"2021-03-01T10:05:00","10:05","2021-07-23T13:48:00","13:48",334,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342219661","Dijon-Toul",">","Culmont","NeufChateau",2021,2021,9,29,"2021-03-01T13:26:00","13:26","2021-07-22T19:14:00","19:14",371,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342220461","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,52,49,"2020-12-21T01:25:00","01:25","2021-12-06T04:51:00","04:51",226,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650261_8342222061","Dijon-Toul",">","Culmont","NeufChateau",2020,2021,51,49,"2020-12-14T10:55:00","10:55","2021-12-10T11:37:00","11:37",2916,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651761_8342376161","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2020,2021,51,49,"2020-12-14T09:44:00","09:44","2021-12-10T10:50:00","10:50",2720,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651761_8342376961","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2021,2021,6,40,"2021-02-08T23:34:00","23:34","2021-10-08T05:39:00","05:39",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
["SNCF Réseau","8342651761_8342374561","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2021,2021,6,49,"2021-02-08T23:10:00","23:10","2021-12-10T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342651761_8342375361","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2020,2021,51,49,"2020-12-14T14:31:00","14:31","2021-12-10T15:26:00","15:26",3874,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649461_8342380161","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2020,2021,51,49,"2020-12-14T11:30:00","11:30","2021-12-10T13:15:00","13:15",3327,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649461_8342382561","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2020,2021,51,42,"2020-12-20T23:00:00","23:00","2021-10-24T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8342649461_8342381761","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2020,2021,51,49,"2020-12-14T13:20:00","13:20","2021-12-10T13:40:00","13:40",3430,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649461_8342383361","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2021,2021,12,38,"2021-03-22T10:30:00","10:30","2021-09-24T16:30:00","16:30",550,"DAY",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","8342649461_8342380961","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2020,2021,51,42,"2020-12-20T23:00:00","23:00","2021-10-24T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342260961","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2021,2021,6,49,"2021-02-08T23:05:00","23:05","2021-12-10T04:55:00","04:55",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342258561","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2021,51,49,"2020-12-14T09:36:00","09:36","2021-12-10T10:37:00","10:37",2665,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342261761","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2021,2021,6,49,"2021-02-08T23:20:00","23:20","2021-12-10T05:30:00","05:30",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342259361","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2021,51,48,"2020-12-20T23:04:00","23:04","2021-12-05T01:55:00","01:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342262561","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:20:00","03:20",116,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","8342650461_8342260161","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2020,2021,51,49,"2020-12-14T14:36:00","14:36","2021-12-10T15:26:00","15:26",3874,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651461_8342192861","Lerouville-Nancy",">","Lerouville","Toul",2020,2021,51,49,"2020-12-14T15:15:00","15:15","2021-12-10T16:00:00","16:00",4016,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651461_8342194461","Lerouville-Nancy",">","Lerouville","Toul",2021,2021,4,49,"2021-01-25T00:40:00","00:40","2021-12-06T03:20:00","03:20",32,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8342651461_8342191061","Lerouville-Nancy",">","Lerouville","Toul",2020,2021,51,49,"2020-12-14T10:40:00","10:40","2021-12-10T11:56:00","11:56",2996,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342651461_8342193661","Lerouville-Nancy",">","Lerouville","Toul",2021,2021,3,48,"2021-01-24T22:40:00","22:40","2021-12-05T02:01:00","02:01",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","8342651461_8342191861","Lerouville-Nancy",">","Lerouville","Toul",2021,2021,9,49,"2021-03-01T23:00:00","23:00","2021-12-10T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"57 jours dans le régime binaire"]
["SNCF Réseau","8342646361_8342096061","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2021,2021,9,48,"2021-03-01T10:15:00","10:15","2021-12-03T16:00:00","16:00",1029,"DAY",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","8342646361_8342093661","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2020,2021,51,49,"2020-12-14T00:30:00","00:30","2021-12-06T03:50:00","03:50",126,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","8342646361_8342092861","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2020,2021,51,49,"2020-12-14T11:30:00","11:30","2021-12-10T12:10:00","12:10",3054,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342646361_8342094461","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2020,2021,51,49,"2020-12-14T14:05:00","14:05","2021-12-10T15:25:00","15:25",3870,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342646361_8342095261","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2020,2021,51,49,"2020-12-14T00:50:00","00:50","2021-12-06T03:30:00","03:30",114,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342342361","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14T14:09:00","14:09","2021-12-10T15:17:00","15:17",3837,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342340561","Lerouville-Metz",">","Noveant","Metz",2021,2021,4,49,"2021-01-25T23:00:00","23:00","2021-12-10T05:45:00","05:45",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342341561","Lerouville-Metz",">","Noveant","Metz",2021,2021,1,47,"2021-01-04","00:00","2021-11-22T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342337161","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14T14:11:00","14:11","2021-12-10T15:05:00","15:05",3786,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342339761","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14T10:48:00","10:48","2021-12-10T11:55:00","11:55",2992,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342337961","Lerouville-Metz",">","Noveant","Metz",2021,2021,5,44,"2021-02-01T23:00:00","23:00","2021-11-05T05:45:00","05:45",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342338961","Lerouville-Metz",">","Noveant","Metz",2021,2021,1,47,"2021-01-04","00:00","2021-11-22T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342334761","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342336361","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14T09:20:00","09:20","2021-12-10T10:15:00","10:15",2573,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342649261_8342335561","Lerouville-Metz",">","Noveant","Metz",2020,2021,51,49,"2020-12-14","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342480961","Dijon-Toul",">","IsSurTille","Culmont",2021,2021,4,45,"2021-01-25T12:22:00","12:22","2021-11-10T16:50:00","16:50",1351,"DAY",null,null,null,null,null,null,null,null,null,null,null,"81 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342481761","Dijon-Toul",">","IsSurTille","Culmont",2020,2021,51,49,"2020-12-14T00:29:00","00:29","2021-12-06T04:03:00","04:03",202,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342483361","Dijon-Toul",">","IsSurTille","Culmont",2020,2021,51,49,"2020-12-14T00:54:00","00:54","2021-12-06T03:29:00","03:29",173,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342482561","Dijon-Toul",">","IsSurTille","Culmont",2020,2021,51,49,"2020-12-14T13:01:00","13:01","2021-12-10T14:22:00","14:22",3607,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342479361","Dijon-Toul",">","IsSurTille","Culmont",2021,2021,4,45,"2021-01-25T10:58:00","10:58","2021-11-10T14:28:00","14:28",1160,"DAY",null,null,null,null,null,null,null,null,null,null,null,"81 jours dans le régime binaire"]
["SNCF Réseau","8342647461_8342480161","Dijon-Toul",">","IsSurTille","Culmont",2020,2021,51,49,"2020-12-14T11:08:00","11:08","2021-12-10T11:38:00","11:38",2920,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342230761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342233961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,51,43,"2020-12-14","00:00","2021-10-25T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342231561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342241161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,51,46,"2020-12-15T09:21:00","09:21","2021-11-19T10:19:00","10:19",1063,"DAY",null,null,null,null,null,null,null,null,null,null,null,"104 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342241961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,4,49,"2021-01-25","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342237961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,51,46,"2020-12-14T11:23:00","11:23","2021-11-19T12:27:00","12:27",2366,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342239561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,51,46,"2020-12-14T14:30:00","14:30","2021-11-19T15:25:00","15:25",2930,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342232361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342236361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,4,49,"2021-01-25","00:00","2021-12-06T03:00:00","03:00",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"26 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342234761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342229961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,53,49,"2020-12-28T13:38:00","13:38","2021-12-10T14:41:00","14:41",2585,"DAY",null,null,null,null,null,null,null,null,null,null,null,"177 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342235561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2020,2021,51,43,"2020-12-14","00:00","2021-10-25T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342233161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,5,41,"2021-02-01T09:30:00","09:30","2021-10-11T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342240361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,5,41,"2021-02-02T11:30:00","11:30","2021-10-15T15:30:00","15:30",701,"DAY",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","8342648461_8342238761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2021,5,41,"2021-02-01T09:30:00","09:30","2021-10-11T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","8342646561_8342368561","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2021,51,46,"2020-12-14T00:25:00","00:25","2021-11-15T03:03:00","03:03",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342646561_8342370361","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2021,51,49,"2020-12-14T10:26:00","10:26","2021-12-10T11:42:00","11:42",2937,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342646561_8342367761","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2021,51,49,"2020-12-14T14:32:00","14:32","2021-12-10T15:16:00","15:16",3832,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8342646561_8342369361","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2021,2021,6,41,"2021-02-08T23:35:00","23:35","2021-10-15T05:35:00","05:35",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342646561_8342366961","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2020,2021,51,46,"2020-12-14","00:00","2021-11-15T03:24:00","03:24",37,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342650061_8342360161","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2021,2021,1,49,"2021-01-04T09:46:00","09:46","2021-12-10T10:44:00","10:44",2555,"DAY",null,null,null,null,null,null,null,null,null,null,null,"239 jours dans le régime binaire"]
["SNCF Réseau","8342650061_8342358161","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2021,2021,6,49,"2021-02-08T23:14:00","23:14","2021-12-10T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"102 jours dans le régime binaire"]
["SNCF Réseau","8342650061_8342359161","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2021,2021,18,18,"2021-05-03T23:14:00","23:14","2021-05-07T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"5 jours dans le régime binaire"]
["SNCF Réseau","8342650061_8342360961","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2021,2021,1,49,"2021-01-04T14:26:00","14:26","2021-12-10T15:23:00","15:23",3662,"DAY",null,null,null,null,null,null,null,null,null,null,null,"239 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342279761","Dijon-Toul",">","Dijon","Is sur Tille",2021,2021,1,48,"2021-01-04T00:05:00","00:05","2021-11-29T03:29:00","03:29",160,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342278761","Dijon-Toul",">","Dijon","Is sur Tille",2020,2021,51,48,"2020-12-14T12:35:00","12:35","2021-12-03T14:01:00","14:01",2300,"DAY",null,null,null,null,null,null,null,null,null,null,null,"165 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342280761","Dijon-Toul",">","Dijon","Is sur Tille",2020,2021,51,48,"2020-12-14T11:35:00","11:35","2021-12-03T12:14:00","12:14",2006,"DAY",null,null,null,null,null,null,null,null,null,null,null,"165 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342277761","Dijon-Toul",">","Dijon","Is sur Tille",2021,2021,1,48,"2021-01-04T01:10:00","01:10","2021-11-29T03:55:00","03:55",179,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342281761","Dijon-Toul",">","Dijon","Is sur Tille",2021,2021,4,45,"2021-01-25T11:26:00","11:26","2021-11-12T14:58:00","14:58",1290,"DAY",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
["SNCF Réseau","8342648561_8342282761","Dijon-Toul",">","Dijon","Is sur Tille",2021,2021,4,45,"2021-01-25T12:00:00","12:00","2021-11-12T16:22:00","16:22",1411,"DAY",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
["SNCF Réseau","8342649361_8342189661","Longuyon-Metz-Sarrebourg","<","Metz sablon via MetzVille",null,2021,2021,14,47,"2021-04-05T23:30:00","23:30","2021-11-26T05:30:00","05:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342467961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2021,51,46,"2020-12-14T14:25:00","14:25","2021-11-19T15:21:00","15:21",2917,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342466361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2021,51,46,"2020-12-14T11:27:00","11:27","2021-11-19T12:28:00","12:28",2369,"DAY",null,null,null,null,null,null,null,null,null,null,null,"191 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342461561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2021,53,49,"2020-12-28T13:41:00","13:41","2021-12-10T14:44:00","14:44",2594,"DAY",null,null,null,null,null,null,null,null,null,null,null,"177 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342459161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2020,2021,51,46,"2020-12-15T09:19:00","09:19","2021-11-19T10:17:00","10:17",1049,"DAY",null,null,null,null,null,null,null,null,null,null,null,"103 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342465561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342459961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,4,41,"2021-01-25T09:30:00","09:30","2021-10-11T15:30:00","15:30",192,"DAY",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342463961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342460761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342464761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,6,49,"2021-02-09T11:30:00","11:30","2021-12-10T15:30:00","15:30",717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342467161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,6,49,"2021-02-08T09:30:00","09:30","2021-12-06T15:30:00","15:30",161,"DAY",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342463161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,4,41,"2021-01-26T11:30:00","11:30","2021-10-15T15:30:00","15:30",763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8342650961_8342462361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2021,4,41,"2021-01-26T11:30:00","11:30","2021-10-15T15:30:00","15:30",763,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","8345420561_8345381361","Paris-Amiens",">","StadeDeFrance","StDenis",2020,2021,51,49,"2020-12-15T01:00:00","01:00","2021-12-11T05:20:00","05:20",1273,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"239 jours dans le régime binaire"]
["SNCF Réseau","8345420561_8345380561","Paris-Amiens",">","StadeDeFrance","StDenis",2020,2021,51,49,"2020-12-15T01:00:00","01:00","2021-12-11T05:05:00","05:05",1163,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"229 jours dans le régime binaire"]
["SNCF Réseau","8345420561_8345382161","Paris-Amiens",">","StadeDeFrance","StDenis",2021,2021,44,44,"2021-11-02T23:55:00","23:55","2021-11-05T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","8345420561_8345379761","Paris-Amiens",">","StadeDeFrance","StDenis",2020,2021,51,49,"2020-12-15T00:30:00","00:30","2021-12-11T04:25:00","04:25",1015,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"230 jours dans le régime binaire"]
["SNCF Réseau","8345420561_8345378961","Paris-Amiens",">","StadeDeFrance","StDenis",2020,2021,51,49,"2020-12-15T00:35:00","00:35","2021-12-11T04:45:00","04:45",1139,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327964161","Dijon-Lyon",">","Macon","Saint Germain",2020,2021,51,49,"2020-12-14T11:03:00","11:03","2021-12-10T11:33:00","11:33",2888,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327961761","Dijon-Lyon",">","Macon","Saint Germain",2021,2021,9,49,"2021-03-01T01:45:00","01:45","2021-12-06T05:04:00","05:04",99,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327962561","Dijon-Lyon",">","Macon","Saint Germain",2021,2021,9,48,"2021-03-01T23:25:00","23:25","2021-12-03T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"144 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327963361","Dijon-Lyon",">","Macon","Saint Germain",2020,2021,51,49,"2020-12-14T13:57:00","13:57","2021-12-10T15:28:00","15:28",3868,"DAY",null,null,null,null,null,null,null,null,null,null,null,"251 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327960961","Dijon-Lyon",">","Macon","Saint Germain",2021,2021,8,48,"2021-02-28T22:50:00","22:50","2021-12-05T01:30:00","01:30",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","8328066861_8327964961","Dijon-Lyon",">","Macon","Saint Germain",2021,2021,9,49,"2021-03-01T23:43:00","23:43","2021-12-10T06:18:00","06:18",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"127 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327901561","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-14T14:28:00","14:28","2021-12-10T15:35:00","15:35",3538,"DAY",null,null,null,null,null,null,null,null,null,null,null,"228 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327899961","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-14T10:30:00","10:30","2021-12-10T11:24:00","11:24",2588,"DAY",null,null,null,null,null,null,null,null,null,null,null,"228 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327896761","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-14T22:58:00","22:58","2021-12-10T04:37:00","04:37",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"94 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327900761","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-14T22:58:00","22:58","2021-12-10T04:37:00","04:37",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"65 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327898361","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-15T00:20:00","00:20","2021-12-11T06:24:00","06:24",351,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327897561","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-14T10:30:00","10:30","2021-12-10T11:24:00","11:24",2588,"DAY",null,null,null,null,null,null,null,null,null,null,null,"228 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327902361","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-14T14:28:00","14:28","2021-12-10T15:35:00","15:35",3538,"DAY",null,null,null,null,null,null,null,null,null,null,null,"228 jours dans le régime binaire"]
["SNCF Réseau","8328065361_8327899161","Dijon-Lyon",">","StGermain","Collonges",2020,2021,51,49,"2020-12-15T00:20:00","00:20","2021-12-10T06:24:00","06:24",537,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"84 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327944561","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2021,9,49,"2021-03-01T01:07:00","01:07","2021-12-06T04:40:00","04:40",92,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327942961","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2021,9,49,"2021-03-01T23:58:00","23:58","2021-12-10T05:18:00","05:18",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"141 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327943761","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2021,51,49,"2020-12-14T13:25:00","13:25","2021-12-10T14:56:00","14:56",3749,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327946161","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2021,8,48,"2021-02-28T00:03:00","00:03","2021-12-05T02:30:00","02:30",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327946961","Dijon-Lyon",">","Chalon sur Saone","Macon",2020,2021,51,49,"2020-12-14T11:37:00","11:37","2021-12-10T12:06:00","12:06",3037,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065861_8327945361","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2021,9,49,"2021-03-05T23:05:00","23:05","2021-12-10T05:57:00","05:57",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"129 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327857761","Dijon-Lyon",">","Chagny","Chalon sur Saone",2021,2021,11,44,"2021-03-15T00:07:00","00:07","2021-11-05T05:55:00","05:55",-5,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"63 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327860161","Dijon-Lyon",">","Chagny","Chalon sur Saone",2021,2021,9,49,"2021-03-01T01:00:00","01:00","2021-12-06T04:05:00","04:05",80,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327858561","Dijon-Lyon",">","Chagny","Chalon sur Saone",2021,2021,11,44,"2021-03-15T23:00:00","23:00","2021-11-05T05:11:00","05:11",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"63 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327860961","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2021,51,49,"2020-12-14T13:13:00","13:13","2021-12-10T14:26:00","14:26",3623,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327861761","Dijon-Lyon",">","Chagny","Chalon sur Saone",2020,2021,51,49,"2020-12-14T11:46:00","11:46","2021-12-10T12:35:00","12:35",3159,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065761_8327859361","Dijon-Lyon",">","Chagny","Chalon sur Saone",2021,2021,9,49,"2021-03-01T00:10:00","00:10","2021-12-06T03:05:00","03:05",61,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327957361","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2021,2021,7,47,"2021-02-15T10:22:00","10:22","2021-11-26T16:22:00","16:22",889,"DAY",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327958361","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2021,51,48,"2020-12-14T02:56:00","02:56","2021-11-29T05:30:00","05:30",167,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327955761","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2021,51,48,"2020-12-14T13:08:00","13:08","2021-12-03T16:28:00","16:28",530,"DAY",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327956561","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2021,51,48,"2020-12-14T08:53:00","08:53","2021-12-03T13:22:00","13:22",432,"DAY",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327954161","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2021,51,44,"2020-12-14T11:27:00","11:27","2021-11-05T13:05:00","13:05",2121,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327954961","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2021,51,44,"2020-12-14T13:30:00","13:30","2021-11-05T13:48:00","13:48",2235,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","8328065461_8327953361","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2020,2021,51,47,"2020-12-20T22:10:00","22:10","2021-11-28T01:30:00","01:30",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327863361","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2021,51,47,"2020-12-14T22:18:00","22:18","2021-11-25T04:40:00","04:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"38 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327864161","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2021,51,48,"2020-12-14T03:06:00","03:06","2021-11-29T05:32:00","05:32",168,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327866561","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2021,51,48,"2020-12-14T00:24:00","00:24","2021-11-29T03:47:00","03:47",116,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327865761","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2021,51,49,"2020-12-14T10:42:00","10:42","2021-12-10T12:01:00","12:01",2969,"DAY",null,null,null,null,null,null,null,null,null,null,null,"248 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327864961","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2021,51,49,"2020-12-14T11:44:00","11:44","2021-12-10T12:08:00","12:08",2997,"DAY",null,null,null,null,null,null,null,null,null,null,null,"248 jours dans le régime binaire"]
["SNCF Réseau","8328066661_8327867361","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2020,2021,51,47,"2020-12-14T23:30:00","23:30","2021-11-25T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"38 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327887961","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2021,51,49,"2020-12-14T12:17:00","12:17","2021-12-10T13:37:00","13:37",3391,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327888761","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2021,51,47,"2020-12-20T23:44:00","23:44","2021-11-28T02:29:00","02:29",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327891561","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2021,51,48,"2020-12-14T01:52:00","01:52","2021-11-29T04:32:00","04:32",138,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327887161","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2021,51,49,"2020-12-14T12:00:00","12:00","2021-12-10T12:50:00","12:50",3196,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327889561","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2021,51,47,"2020-12-14T10:43:00","10:43","2021-11-26T16:43:00","16:43",1443,"DAY",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
["SNCF Réseau","8328066361_8327890561","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2020,2021,51,47,"2020-12-14T11:00:00","11:00","2021-11-26T13:00:00","13:00",912,"DAY",null,null,null,null,null,null,null,null,null,null,null,"71 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8328001961","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2021,51,49,"2020-12-14T13:09:00","13:09","2021-12-10T14:22:00","14:22",2371,"DAY",null,null,null,null,null,null,null,null,null,null,null,"166 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8328003761","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2021,51,48,"2020-12-14T01:32:00","01:32","2021-11-29T04:15:00","04:15",125,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8328001161","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2021,51,49,"2020-12-14T11:49:00","11:49","2021-12-10T12:29:00","12:29",2060,"DAY",null,null,null,null,null,null,null,null,null,null,null,"166 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8327999361","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2020,2021,51,47,"2020-12-20T23:22:00","23:22","2021-11-28T02:39:00","02:39",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8328002761","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2021,2021,1,47,"2021-01-04T10:15:00","10:15","2021-11-26T16:15:00","16:15",964,"DAY",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8328066461_8328000161","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2021,2021,1,47,"2021-01-04T14:15:00","14:15","2021-11-26T16:15:00","16:15",895,"DAY",null,null,null,null,null,null,null,null,null,null,null,"56 jours dans le régime binaire"]
["SNCF Réseau","8328066961_8327876961","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2021,2021,1,47,"2021-01-04T00:25:00","00:25","2021-11-22T03:10:00","03:10",138,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","8328066961_8327876161","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2020,2021,51,49,"2020-12-14T15:05:00","15:05","2021-12-10T15:48:00","15:48",3966,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328066961_8327877761","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2021,2021,1,47,"2021-01-04T00:05:00","00:05","2021-11-22T03:20:00","03:20",146,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","8328066961_8327878561","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2020,2021,51,49,"2020-12-14T14:31:00","14:31","2021-12-10T15:48:00","15:48",3967,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328066961_8327879361","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2020,2021,51,49,"2020-12-14T23:40:00","23:40","2021-12-10T05:40:00","05:40",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327907161","Dijon-Lyon",">","Dijon","Chagny",2020,2021,51,49,"2020-12-14T12:16:00","12:16","2021-12-10T12:44:00","12:44",3196,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327906361","Dijon-Lyon",">","Dijon","Chagny",2021,2021,9,49,"2021-03-01T00:45:00","00:45","2021-12-06T04:00:00","04:00",79,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327905561","Dijon-Lyon",">","Dijon","Chagny",2021,2021,9,45,"2021-03-01T22:29:00","22:29","2021-11-10T04:55:00","04:55",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"85 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327904761","Dijon-Lyon",">","Dijon","Chagny",2021,2021,9,49,"2021-03-02T00:34:00","00:34","2021-12-11T05:57:00","05:57",564,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"95 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327908761","Dijon-Lyon",">","Dijon","Chagny",2021,2021,9,49,"2021-03-01T00:25:00","00:25","2021-12-06T03:11:00","03:11",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","8328065961_8327907961","Dijon-Lyon",">","Dijon","Chagny",2020,2021,51,49,"2020-12-14T12:42:00","12:42","2021-12-10T14:13:00","14:13",3569,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327938561","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2021,51,48,"2020-12-14T02:30:00","02:30","2021-11-29T04:52:00","04:52",148,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327940361","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2021,51,44,"2020-12-14T12:58:00","12:58","2021-11-05T13:10:00","13:10",2133,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327936961","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2021,51,47,"2020-12-20T22:31:00","22:31","2021-11-28T02:02:00","02:02",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"31 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327937761","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2020,2021,51,44,"2020-12-14T12:05:00","12:05","2021-11-05T13:48:00","13:48",2237,"DAY",null,null,null,null,null,null,null,null,null,null,null,"163 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327935361","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2021,2021,9,48,"2021-03-01T12:35:00","12:35","2021-12-03T16:15:00","16:15",572,"DAY",null,null,null,null,null,null,null,null,null,null,null,"36 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327939361","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2021,2021,5,47,"2021-02-01T10:15:00","10:15","2021-11-26T16:15:00","16:15",1127,"DAY",null,null,null,null,null,null,null,null,null,null,null,"70 jours dans le régime binaire"]
["SNCF Réseau","8328067061_8327936161","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2021,2021,9,48,"2021-03-01T09:15:00","09:15","2021-12-03T13:45:00","13:45",485,"DAY",null,null,null,null,null,null,null,null,null,null,null,"36 jours dans le régime binaire"]
["SNCF Réseau","8291618961_8291555061","Sarrebourg-Basel",">","Colmar","Lutterbach",2020,2021,51,49,"2020-12-14T10:03:00","10:03","2021-12-10T10:50:00","10:50",2687,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618961_8342031061","Sarrebourg-Basel",">","Colmar","Lutterbach",2021,2021,7,48,"2021-02-15T23:01:00","23:01","2021-12-02T05:16:00","05:16",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"96 jours dans le régime binaire"]
["SNCF Réseau","8291618961_8291554261","Sarrebourg-Basel",">","Colmar","Lutterbach",2020,2021,51,49,"2020-12-14T14:25:00","14:25","2021-12-10T15:39:00","15:39",3882,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618361_8291549061","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2021,51,49,"2020-12-14T14:10:00","14:10","2021-12-10T15:19:00","15:19",3799,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618361_8291549861","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2021,51,49,"2020-12-14T10:09:00","10:09","2021-12-10T11:01:00","11:01",2733,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618361_8291548261","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2021,51,49,"2020-12-14T10:17:00","10:17","2021-12-10T11:09:00","11:09",2766,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618361_8291551461","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2020,2021,51,49,"2020-12-14T14:19:00","14:19","2021-12-10T15:27:00","15:27",3832,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618361_8345442361","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2021,2021,6,48,"2021-02-08T22:52:00","22:52","2021-12-03T05:00:00","05:00",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","8291617261_8291581861","Sarrebourg-Basel",">","Graffenstaden","Selestat",2020,2021,51,49,"2020-12-14T13:55:00","13:55","2021-12-10T15:08:00","15:08",3754,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291617261_8291579461","Sarrebourg-Basel",">","Graffenstaden","Selestat",2020,2021,51,49,"2020-12-14T10:33:00","10:33","2021-12-10T11:19:00","11:19",2807,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291617261_8341950861","Sarrebourg-Basel",">","Graffenstaden","Selestat",2021,2021,8,47,"2021-02-22T23:04:00","23:04","2021-11-25T05:23:00","05:23",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"72 jours dans le régime binaire"]
["SNCF Réseau","8291618261_8291591261","Sarrebourg-Basel",">","Saverne","Vendenheim",2021,2021,12,49,"2021-03-22T22:57:00","22:57","2021-12-09T05:12:00","05:12",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"79 jours dans le régime binaire"]
["SNCF Réseau","8291618161_8291573461","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2021,51,49,"2020-12-14T14:50:00","14:50","2021-12-10T16:00:00","16:00",3969,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618161_8291572661","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2021,51,49,"2020-12-14T09:29:00","09:29","2021-12-10T10:26:00","10:26",2588,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618161_8291571061","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2021,51,49,"2020-12-14T09:40:00","09:40","2021-12-10T10:30:00","10:30",2604,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618161_8291574261","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2020,2021,51,49,"2020-12-14T15:01:00","15:01","2021-12-10T16:04:00","16:04",3985,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","8291618161_8341841461","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2021,2021,15,48,"2021-04-12T22:50:00","22:50","2021-12-01T05:05:00","05:05",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"86 jours dans le régime binaire"]
["SNCF Réseau","8291617561_8291583261","Sarrebourg-Basel",">","Reding","Saverne",2021,2021,11,46,"2021-03-15T22:45:00","22:45","2021-11-19T04:57:00","04:57",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"105 jours dans le régime binaire"]
["SNCF Réseau","10315306761_10315192761","Paris-Amiens",">","StadeDeFrance","StDenis",2021,2022,50,49,"2021-12-14T01:00:00","01:00","2022-12-10T05:05:00","05:05",1320,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","10315306761_10315191961","Paris-Amiens",">","StadeDeFrance","StDenis",2021,2022,50,49,"2021-12-14T01:00:00","01:00","2022-12-10T05:20:00","05:20",1380,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"259 jours dans le régime binaire"]
["SNCF Réseau","10315306761_10315190361","Paris-Amiens",">","StadeDeFrance","StDenis",2021,2022,50,49,"2021-12-14T00:30:00","00:30","2022-12-10T04:25:00","04:25",1147,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","10315306761_10315191161","Paris-Amiens",">","StadeDeFrance","StDenis",2021,2022,50,49,"2021-12-14T00:35:00","00:35","2022-12-10T04:45:00","04:45",1229,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"259 jours dans le régime binaire"]
["SNCF Réseau","10302001861_10301949961","Paris-Amiens",">","Bif de Pierrefitte","Orry",2021,2022,50,48,"2021-12-13T01:30:00","01:30","2022-11-28T04:30:00","04:30",43,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","10302001861_10301951561","Paris-Amiens",">","Bif de Pierrefitte","Orry",2021,2022,50,48,"2021-12-13T01:45:00","01:45","2022-11-28T04:45:00","04:45",45,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","10302001861_10301950761","Paris-Amiens",">","Bif de Pierrefitte","Orry",2021,2022,50,49,"2021-12-13T01:30:00","01:30","2022-12-05T04:30:00","04:30",210,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10302001861_10301948761","Paris-Amiens",">","Bif de Pierrefitte","Orry",2021,2022,50,49,"2021-12-14","00:00","2022-12-10T05:00:00","05:00",670,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"134 jours dans le régime binaire"]
["SNCF Réseau","10302001461_10301885961","Paris-Amiens",">","Goussainville","Orry",2021,2022,50,46,"2021-12-14T01:20:00","01:20","2022-11-19T04:50:00","04:50",742,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"154 jours dans le régime binaire"]
["SNCF Réseau","10302001461_10301886761","Paris-Amiens",">","Goussainville","Orry",2021,2022,50,46,"2021-12-14T00:15:00","00:15","2022-11-19T04:45:00","04:45",731,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"154 jours dans le régime binaire"]
["SNCF Réseau","10302001461_10301884361","Paris-Amiens",">","Goussainville","Orry",2022,2022,6,49,"2022-02-07T23:40:00","23:40","2022-12-09T04:35:00","04:35",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","10302001461_10301883561","Paris-Amiens",">","Goussainville","Orry",2022,2022,6,49,"2022-02-07T23:50:00","23:50","2022-12-09T04:50:00","04:50",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","10302000661_10301890361","Paris-Amiens",">","Villiers le Bel","Goussainville",2021,2022,50,46,"2021-12-14T00:20:00","00:20","2022-11-19T04:50:00","04:50",743,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"154 jours dans le régime binaire"]
["SNCF Réseau","10302000661_10301891961","Paris-Amiens",">","Villiers le Bel","Goussainville",2022,2022,6,49,"2022-02-07T23:45:00","23:45","2022-12-09T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","10302000661_10301889561","Paris-Amiens",">","Villiers le Bel","Goussainville",2021,2022,50,46,"2021-12-14T01:14:00","01:14","2022-11-19T04:50:00","04:50",743,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"154 jours dans le régime binaire"]
["SNCF Réseau","10302000661_10301891161","Paris-Amiens",">","Villiers le Bel","Goussainville",2022,2022,6,49,"2022-02-07T23:46:00","23:46","2022-12-09T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","10302001661_10301917161","Paris-Amiens",">","Orry","Creil",2021,2022,51,49,"2021-12-20T23:49:00","23:49","2022-12-09T04:54:00","04:54",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"68 jours dans le régime binaire"]
["SNCF Réseau","10302001661_10301915561","Paris-Amiens",">","Orry","Creil",2021,2022,50,48,"2021-12-13T01:30:00","01:30","2022-11-28T04:30:00","04:30",43,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","10302001661_10301913961","Paris-Amiens",">","Orry","Creil",2021,2022,50,48,"2021-12-13T01:51:00","01:51","2022-11-28T04:51:00","04:51",46,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","10302001661_10301913161","Paris-Amiens",">","Orry","Creil",2021,2022,50,49,"2021-12-13T01:30:00","01:30","2022-12-05T04:30:00","04:30",210,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10302001661_10301914761","Paris-Amiens",">","Orry","Creil",2021,2022,51,49,"2021-12-20T23:53:00","23:53","2022-12-09T04:42:00","04:42",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"68 jours dans le régime binaire"]
["SNCF Réseau","10302001661_10301916361","Paris-Amiens",">","Orry","Creil",2021,2022,51,49,"2021-12-21T01:10:00","01:10","2022-12-10T05:26:00","05:26",368,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"68 jours dans le régime binaire"]
["SNCF Réseau","10302000961_10301896561","Paris-Amiens",">","ParisNord","Bif de Pierrefitte",2021,2022,50,49,"2021-12-14","00:00","2022-12-10T05:00:00","05:00",1300,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","10302000761_10301964761","Paris-Busigny",">","Mitry","Ormoy",2022,2022,1,46,"2022-01-04","00:00","2022-11-19T04:45:00","04:45",593,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"125 jours dans le régime binaire"]
["SNCF Réseau","10302000561_10301957961","Paris-Amiens",">","Stade de France","SaintDenis",2022,2022,14,32,"2022-04-04","00:00","2022-08-12T05:05:00","05:05",-5,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10302000561_10301958961","Paris-Amiens",">","Stade de France","SaintDenis",2021,2022,50,49,"2021-12-14T00:35:00","00:35","2022-12-10T05:05:00","05:05",1316,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"259 jours dans le régime binaire"]
["SNCF Réseau","10302000561_10301959961","Paris-Amiens",">","Stade de France","SaintDenis",2021,2022,50,49,"2021-12-14T01:00:00","01:00","2022-12-10T04:50:00","04:50",1250,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"259 jours dans le régime binaire"]
["SNCF Réseau","10302000561_10301962961","Paris-Amiens",">","Stade de France","SaintDenis",2022,2022,14,32,"2022-04-04T23:25:00","23:25","2022-08-12T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10302002161_10301910961","Paris-Amiens",">","SaintDenis","VilliersLeBel",2022,2022,21,39,"2022-05-23T23:35:00","23:35","2022-09-30T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"79 jours dans le régime binaire"]
["SNCF Réseau","10302002161_10301907761","Paris-Amiens",">","SaintDenis","VilliersLeBel",2021,2022,50,49,"2021-12-14T01:05:00","01:05","2022-12-10T04:50:00","04:50",1250,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"259 jours dans le régime binaire"]
["SNCF Réseau","10302002161_10301910161","Paris-Amiens",">","SaintDenis","VilliersLeBel",2022,2022,21,39,"2022-05-23T23:55:00","23:55","2022-09-30T04:50:00","04:50",20,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"79 jours dans le régime binaire"]
["SNCF Réseau","10302002161_10301909361","Paris-Amiens",">","SaintDenis","VilliersLeBel",2021,2022,50,49,"2021-12-14T00:30:00","00:30","2022-12-10T04:55:00","04:55",1272,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"259 jours dans le régime binaire"]
["SNCF Réseau","10302076661_10302055661","Sarrebourg-Basel",">","Reding","Saverne",2021,2022,50,49,"2021-12-13T13:26:00","13:26","2022-12-09T14:41:00","14:41",3642,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076661_10302054861","Sarrebourg-Basel",">","Reding","Saverne",2021,2022,50,49,"2021-12-13T14:00:00","14:00","2022-12-09T14:45:00","14:45",3658,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076661_10302053861","Sarrebourg-Basel",">","Reding","Saverne",2022,2022,7,37,"2022-02-14T22:57:00","22:57","2022-09-16T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"37 jours dans le régime binaire"]
["SNCF Réseau","10302075461_10302071261","Sarrebourg-Basel",">","Saverne","Vendenheim",2021,2022,50,49,"2021-12-13T13:42:00","13:42","2022-12-09T14:55:00","14:55",3700,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302075461_10302073861","Sarrebourg-Basel",">","Saverne","Vendenheim",2021,2022,50,49,"2021-12-13T13:55:00","13:55","2022-12-09T15:03:00","15:03",3733,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302075461_10302072861","Sarrebourg-Basel",">","Saverne","Vendenheim",2022,2022,9,47,"2022-02-28T23:12:00","23:12","2022-11-25T04:57:00","04:57",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"41 jours dans le régime binaire"]
["SNCF Réseau","10302075461_10302070461","Sarrebourg-Basel",">","Saverne","Vendenheim",2021,2022,50,49,"2021-12-13T13:45:00","13:45","2022-12-09T14:34:00","14:34",3613,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302075461_10302072061","Sarrebourg-Basel",">","Saverne","Vendenheim",2021,2022,50,49,"2021-12-13T13:35:00","13:35","2022-12-09T14:26:00","14:26",3580,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302077161_10302044661","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2021,2022,50,49,"2021-12-13T15:01:00","15:01","2022-12-09T16:04:00","16:04",3985,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302077161_10302043661","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2022,2022,5,46,"2022-01-31T23:05:00","23:05","2022-11-14T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"80 jours dans le régime binaire"]
["SNCF Réseau","10302077161_10302045461","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2021,2022,50,49,"2021-12-13T09:29:00","09:29","2022-12-09T10:26:00","10:26",2588,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302077161_10302047061","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2021,2022,50,49,"2021-12-13T09:40:00","09:40","2022-12-09T10:30:00","10:30",2604,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302077161_10302046261","Sarrebourg-Basel",">","Rixheim","StLouisFrontiere",2021,2022,50,49,"2021-12-13T14:50:00","14:50","2022-12-09T16:00:00","16:00",3969,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076861_10302052461","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2021,2022,50,49,"2021-12-13T10:09:00","10:09","2022-12-09T11:01:00","11:01",2733,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076861_10302049061","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2022,2022,4,48,"2022-01-24T23:00:00","23:00","2022-12-02T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"90 jours dans le régime binaire"]
["SNCF Réseau","10302076861_10302050861","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2021,2022,50,49,"2021-12-13T10:17:00","10:17","2022-12-09T11:09:00","11:09",2766,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076861_10302051661","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2021,2022,50,49,"2021-12-13T14:10:00","14:10","2022-12-09T15:19:00","15:19",3799,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076861_10302050061","Sarrebourg-Basel",">","Selestat","Colmar(115000)",2021,2022,50,49,"2021-12-13T14:19:00","14:19","2022-12-09T15:27:00","15:27",3832,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076261_10302066461","Sarrebourg-Basel",">","Graffenstaden","Selestat",2021,2022,50,49,"2021-12-13T13:55:00","13:55","2022-12-09T15:08:00","15:08",3754,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076261_10302067261","Sarrebourg-Basel",">","Graffenstaden","Selestat",2021,2022,50,49,"2021-12-13T10:33:00","10:33","2022-12-09T11:19:00","11:19",2807,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076261_10302068061","Sarrebourg-Basel",">","Graffenstaden","Selestat",2022,2022,7,49,"2022-02-17T23:23:00","23:23","2022-12-09T05:04:00","05:04",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"87 jours dans le régime binaire"]
["SNCF Réseau","10302076461_10302061661","Sarrebourg-Basel",">","Colmar","Lutterbach",2021,2022,50,49,"2021-12-13T14:25:00","14:25","2022-12-09T15:39:00","15:39",3882,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076461_10302062461","Sarrebourg-Basel",">","Colmar","Lutterbach",2021,2022,50,49,"2021-12-13T10:03:00","10:03","2022-12-09T10:50:00","10:50",2687,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10302076461_10302063261","Sarrebourg-Basel",">","Colmar","Lutterbach",2022,2022,7,47,"2022-02-14T23:16:00","23:16","2022-11-25T05:01:00","05:01",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"82 jours dans le régime binaire"]
["SNCF Réseau","10301683561_10301395461","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2021,2022,50,49,"2021-12-13T13:16:00","13:16","2022-12-09T14:08:00","14:08",3562,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301683561_10301396261","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2021,2022,50,49,"2021-12-13T00:30:00","00:30","2022-12-05T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10301683561_10301394661","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2022,2022,6,49,"2022-02-07T11:00:00","11:00","2022-12-09T15:00:00","15:00",439,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","10301683561_10301393861","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2021,2022,50,49,"2021-12-13T11:30:00","11:30","2022-12-09T12:37:00","12:37",3180,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301683561_10301393061","Aulnoye-Feignies-Jeumont",">","Aulnoye","Maubeuge",2022,2022,6,49,"2022-02-07T11:00:00","11:00","2022-12-09T15:00:00","15:00",439,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301451061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2022,2022,2,46,"2022-01-10T23:17:00","23:17","2022-11-18T05:15:00","05:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"78 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301445461","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2022,2022,1,49,"2022-01-03T00:30:00","00:30","2022-12-05T03:30:00","03:30",73,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301447861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2021,2022,50,49,"2021-12-13T14:51:00","14:51","2022-12-09T15:44:00","15:44",3965,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301452861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2021,2022,50,49,"2021-12-13T14:24:00","14:24","2022-12-09T15:19:00","15:19",3860,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301452061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2022,2022,1,49,"2022-01-03T00:30:00","00:30","2022-12-05T03:30:00","03:30",73,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301449461","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2021,2022,50,49,"2021-12-13T10:50:00","10:50","2022-12-09T12:10:00","12:10",3067,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301450261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2022,2022,1,49,"2022-01-03","00:00","2022-12-05T03:00:00","03:00",63,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301444661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2021,2022,50,49,"2021-12-13T11:10:00","11:10","2022-12-09T12:21:00","12:21",3113,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301446261","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2021,2022,50,49,"2021-12-13T14:34:00","14:34","2022-12-09T15:24:00","15:24",3881,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301448661","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2022,2022,1,49,"2022-01-03T00:30:00","00:30","2022-12-05T03:30:00","03:30",73,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301443861","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2022,2022,1,49,"2022-01-03T00:30:00","00:30","2022-12-05T03:30:00","03:30",73,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","10301688661_10301447061","Hazebrouck-Lens-Aulnoye",">","Busigny","Somain",2022,2022,1,49,"2022-01-03T00:35:00","00:35","2022-12-05T03:15:00","03:15",67,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"21 jours dans le régime binaire"]
["SNCF Réseau","10301687961_10301378661","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2021,2022,50,49,"2021-12-13T08:56:00","08:56","2022-12-09T10:18:00","10:18",2596,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301687961_10301377861","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2021,2022,50,48,"2021-12-13T01:35:00","01:35","2022-11-28T05:10:00","05:10",60,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10301687961_10301380261","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2022,2022,15,44,"2022-04-11T09:30:00","09:30","2022-11-04T13:30:00","13:30",233,"DAY",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301687961_10301379461","Amiens-Douai",">","Longueau","Bif d'Agny exclue",2021,2022,50,49,"2021-12-13T09:18:00","09:18","2022-12-09T10:22:00","10:22",2613,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688361_10301391861","Amiens-Douai","<","Arras","Bif de l'arbre Robert",2021,2022,50,49,"2021-12-13T14:37:00","14:37","2022-12-09T15:34:00","15:34",3923,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301687161_10301572661","Paris-Busigny",">","StQuentin","Busigny",2021,2022,50,49,"2021-12-13T14:09:00","14:09","2022-12-09T14:55:00","14:55",3759,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301687161_10301568261","Paris-Busigny",">","StQuentin","Busigny",2022,2022,1,49,"2022-01-03T00:54:00","00:54","2022-12-05T03:45:00","03:45",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301687161_10301571861","Paris-Busigny",">","StQuentin","Busigny",2021,2022,50,49,"2021-12-13T10:50:00","10:50","2022-12-09T12:05:00","12:05",3046,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301687161_10301573461","Paris-Busigny",">","StQuentin","Busigny",2022,2022,1,49,"2022-01-03T00:30:00","00:30","2022-12-05T03:37:00","03:37",64,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301687161_10301570661","Paris-Busigny",">","StQuentin","Busigny",2022,2022,1,46,"2022-01-03T23:46:00","23:46","2022-11-18T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10301687861_10301436661","Paris-Busigny",">","Tergnier","StQuentin",2022,2022,1,49,"2022-01-03T00:54:00","00:54","2022-12-05T03:45:00","03:45",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301687861_10301435861","Paris-Busigny",">","Tergnier","StQuentin",2022,2022,1,49,"2022-01-03T00:37:00","00:37","2022-12-05T03:45:00","03:45",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301687861_10301435061","Paris-Busigny",">","Tergnier","StQuentin",2021,2022,50,49,"2021-12-13T10:50:00","10:50","2022-12-09T12:05:00","12:05",3046,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301687861_10301440661","Paris-Busigny",">","Tergnier","StQuentin",2022,2022,1,46,"2022-01-03T23:26:00","23:26","2022-11-18T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"57 jours dans le régime binaire"]
["SNCF Réseau","10301687861_10301437461","Paris-Busigny",">","Tergnier","StQuentin",2021,2022,50,49,"2021-12-13T14:25:00","14:25","2022-12-09T14:45:00","14:45",3717,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301686661_10301386261","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2021,2022,50,49,"2021-12-13T13:48:00","13:48","2022-12-09T15:10:00","15:10",3823,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301686661_10301382861","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2021,2022,50,40,"2021-12-19T23:35:00","23:35","2022-10-09T02:45:00","02:45",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10301686661_10301384461","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2022,2022,3,49,"2022-01-17T22:50:00","22:50","2022-12-09T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"60 jours dans le régime binaire"]
["SNCF Réseau","10301686661_10301385461","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2021,2022,50,40,"2021-12-19T23:15:00","23:15","2022-10-09T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10301686661_10301383661","Hazebrouck-Lens-Aulnoye",">","Lens","DonSainghin",2021,2022,50,49,"2021-12-13T09:55:00","09:55","2022-12-09T10:43:00","10:43",2701,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301687561_10301522261","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2021,2022,50,46,"2021-12-13T01:35:00","01:35","2022-11-14T04:55:00","04:55",106,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","10301687561_10301519861","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2021,2022,50,49,"2021-12-13T14:14:00","14:14","2022-12-09T14:58:00","14:58",3772,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301687561_10301520661","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2021,2022,50,46,"2021-12-13","00:00","2022-11-14T03:00:00","03:00",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"22 jours dans le régime binaire"]
["SNCF Réseau","10301687561_10301518861","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2022,2022,2,48,"2022-01-10T22:58:00","22:58","2022-12-02T04:58:00","04:58",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"72 jours dans le régime binaire"]
["SNCF Réseau","10301687561_10301521461","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Lille",2021,2022,50,49,"2021-12-13T09:52:00","09:52","2022-12-09T11:02:00","11:02",2781,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688061_10301500061","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2021,2022,51,41,"2021-12-20","00:00","2022-10-10T03:00:00","03:00",54,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301688061_10301496661","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2021,2022,51,41,"2021-12-20","00:00","2022-10-10T03:00:00","03:00",54,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301688061_10301499261","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2021,2022,50,49,"2021-12-13T14:20:00","14:20","2022-12-09T15:09:00","15:09",3818,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688061_10301497461","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2022,2022,12,49,"2022-03-21T22:50:00","22:50","2022-12-09T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
["SNCF Réseau","10301688061_10301498461","Hazebrouck-Lens-Aulnoye",">","Haubourdin","DonSainghin",2021,2022,50,49,"2021-12-13T09:36:00","09:36","2022-12-09T10:43:00","10:43",2701,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301686561_10301406861","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2021,2022,50,49,"2021-12-13T14:21:00","14:21","2022-12-09T15:26:00","15:26",3890,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301686561_10301403661","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2022,2022,15,36,"2022-04-11T22:50:00","22:50","2022-09-09T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","10301686561_10301404461","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2021,2022,50,49,"2021-12-13T10:41:00","10:41","2022-12-09T11:35:00","11:35",2919,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301686561_10301405261","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2021,2022,50,40,"2021-12-19T22:50:00","22:50","2022-10-09T01:40:00","01:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10301686561_10301407661","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2021,2022,50,40,"2021-12-19T23:10:00","23:10","2022-10-09T02:20:00","02:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10301686561_10301406061","Hazebrouck-Lens-Aulnoye",">","Justice Haubourdin",null,2022,2022,15,36,"2022-04-11T22:50:00","22:50","2022-09-09T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"29 jours dans le régime binaire"]
["SNCF Réseau","10301683861_10301425661","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2022,2022,8,47,"2022-02-21T11:09:00","11:09","2022-11-25T14:58:00","14:58",437,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","10301683861_10301428861","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2021,2022,50,49,"2021-12-13T14:10:00","14:10","2022-12-09T14:54:00","14:54",3755,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301683861_10301426461","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2022,2022,8,47,"2022-02-21T10:47:00","10:47","2022-11-25T14:58:00","14:58",438,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","10301683861_10301427261","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2021,2022,50,49,"2021-12-13T00:46:00","00:46","2022-12-05T04:00:00","04:00",207,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10301683861_10301429661","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2021,2022,50,49,"2021-12-13T11:02:00","11:02","2022-12-09T12:20:00","12:20",3109,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301683861_10301428061","Hazebrouck-Lens-Aulnoye",">","Busigny","Aulnoye",2021,2022,50,49,"2021-12-13T00:25:00","00:25","2022-12-05T03:00:00","03:00",155,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10301685461_10301353661","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2021,2022,50,49,"2021-12-13T10:02:00","10:02","2022-12-09T10:52:00","10:52",2739,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301685461_10301354461","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2022,2022,5,39,"2022-01-31T09:25:00","09:25","2022-09-30T13:40:00","13:40",673,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","10301685461_10301356061","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2021,2022,50,49,"2021-12-13T14:34:00","14:34","2022-12-09T15:44:00","15:44",3965,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301685461_10301355261","Calais-Lille-Aulnoye",">","Lille","Tourcoing",2022,2022,5,39,"2022-01-31T09:40:00","09:40","2022-09-30T13:25:00","13:25",661,"DAY",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","10301688161_10301537261","Paris-Busigny",">","Creil","LongueilSteMarie",2022,2022,1,46,"2022-01-04","00:00","2022-11-19T05:05:00","05:05",686,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"135 jours dans le régime binaire"]
["SNCF Réseau","10301688161_10301538261","Paris-Busigny",">","Creil","LongueilSteMarie",2021,2022,50,49,"2021-12-13T09:46:00","09:46","2022-12-09T10:57:00","10:57",2760,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688161_10301539861","Paris-Busigny",">","Creil","LongueilSteMarie",2021,2022,50,49,"2021-12-13","00:00","2022-12-05T03:10:00","03:10",148,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10301688161_10301539061","Paris-Busigny",">","Creil","LongueilSteMarie",2021,2022,50,49,"2021-12-13T14:35:00","14:35","2022-12-09T15:20:00","15:20",3864,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688161_10301540661","Paris-Busigny",">","Creil","LongueilSteMarie",2021,2022,50,49,"2021-12-13T01:35:00","01:35","2022-12-05T04:20:00","04:20",202,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10301686161_10301554261","Paris-Amiens",">","Creil","Longueau",2021,2022,50,49,"2021-12-13T12:35:00","12:35","2022-12-09T13:56:00","13:56",3512,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301686161_10301555861","Paris-Amiens",">","Creil","Longueau",2021,2022,50,49,"2021-12-13T10:50:00","10:50","2022-12-09T11:30:00","11:30",2898,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301686161_10301553461","Paris-Amiens",">","Creil","Longueau",2021,2022,50,49,"2021-12-13T14:49:00","14:49","2022-12-09T15:54:00","15:54",4007,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301686161_10301551861","Paris-Amiens",">","Creil","Longueau",2021,2022,50,48,"2021-12-13T01:45:00","01:45","2022-11-28T05:15:00","05:15",45,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
["SNCF Réseau","10301686161_10301552661","Paris-Amiens",">","Creil","Longueau",2021,2022,50,49,"2021-12-13T11:04:00","11:04","2022-12-09T11:51:00","11:51",2986,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301686161_10301555061","Paris-Amiens",">","Creil","Longueau",2021,2022,50,48,"2021-12-13T01:45:00","01:45","2022-11-28T04:20:00","04:20",37,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
["SNCF Réseau","10301686161_10301549461","Paris-Amiens",">","Creil","Longueau",2021,2022,50,49,"2021-12-13T23:10:00","23:10","2022-12-09T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"135 jours dans le régime binaire"]
["SNCF Réseau","10301686161_10301550261","Paris-Amiens",">","Creil","Longueau",2021,2022,50,48,"2021-12-13T02:15:00","02:15","2022-11-28T05:40:00","05:40",48,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
["SNCF Réseau","10301686161_10301556661","Paris-Amiens",">","Creil","Longueau",2021,2022,50,48,"2021-12-13T01:20:00","01:20","2022-11-28T04:05:00","04:05",35,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"9 jours dans le régime binaire"]
["SNCF Réseau","10301686161_10301551061","Paris-Amiens",">","Creil","Longueau",2021,2022,50,49,"2021-12-13T22:55:00","22:55","2022-12-09T04:15:00","04:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"135 jours dans le régime binaire"]
["SNCF Réseau","10301687661_10301511461","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2021,2022,51,35,"2021-12-26T23:00:00","23:00","2022-09-04T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","10301687661_10301508061","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2021,2022,50,36,"2021-12-13","00:00","2022-09-05T03:00:00","03:00",42,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","10301687661_10301508861","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2021,2022,50,49,"2021-12-13T09:55:00","09:55","2022-12-09T11:05:00","11:05",2794,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301687661_10301509661","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2022,2022,2,37,"2022-01-10T22:30:00","22:30","2022-09-16T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","10301687661_10301510661","Hazebrouck-Lens-Aulnoye",">","Arras","Lens",2021,2022,50,49,"2021-12-13T14:02:00","14:02","2022-12-09T14:52:00","14:52",3747,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684561_10301360661","Boulogne-Calais",">","Marquise","Calais",2022,2022,5,49,"2022-01-31T23:08:00","23:08","2022-12-09T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"76 jours dans le régime binaire"]
["SNCF Réseau","10301684561_10301361461","Boulogne-Calais",">","Marquise","Calais",2021,2022,51,49,"2021-12-20","00:00","2022-12-05T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10301684561_10301357461","Boulogne-Calais",">","Marquise","Calais",2022,2022,5,49,"2022-01-31T23:08:00","23:08","2022-12-09T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"76 jours dans le régime binaire"]
["SNCF Réseau","10301684561_10301359861","Boulogne-Calais",">","Marquise","Calais",2021,2022,50,49,"2021-12-13T14:25:00","14:25","2022-12-09T15:35:00","15:35",3928,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684561_10301359061","Boulogne-Calais",">","Marquise","Calais",2021,2022,50,49,"2021-12-13T11:00:00","11:00","2022-12-09T11:55:00","11:55",3003,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684561_10301358261","Boulogne-Calais",">","Marquise","Calais",2021,2022,51,49,"2021-12-20","00:00","2022-12-05T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10301688761_10301364261","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2021,2022,50,49,"2021-12-13T11:33:00","11:33","2022-12-09T12:40:00","12:40",3193,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688761_10301365061","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2021,2022,50,49,"2021-12-13T13:30:00","13:30","2022-12-09T14:24:00","14:24",3629,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688761_10301365861","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2021,2022,50,49,"2021-12-13T00:30:00","00:30","2022-12-05T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10301688761_10301363461","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2022,2022,6,49,"2022-02-07T11:00:00","11:00","2022-12-09T15:00:00","15:00",589,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","10301688761_10301362661","Aulnoye-Feignies-Jeumont",">","Maubeuge","Jeumont",2022,2022,6,49,"2022-02-07T11:00:00","11:00","2022-12-09T15:00:00","15:00",589,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","10301684261_10301454861","Amiens-Douai",">","Arras","Douai",2021,2022,50,26,"2021-12-13T00:35:00","00:35","2022-06-27T03:20:00","03:20",26,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","10301684261_10301457261","Amiens-Douai",">","Arras","Douai",2021,2022,50,26,"2021-12-13T01:30:00","01:30","2022-06-27T04:30:00","04:30",34,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","10301684261_10301455661","Amiens-Douai",">","Arras","Douai",2022,2022,6,37,"2022-02-07T22:50:00","22:50","2022-09-16T04:50:00","04:50",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","10301684261_10301458061","Amiens-Douai",">","Arras","Douai",2021,2022,50,49,"2021-12-13T09:34:00","09:34","2022-12-09T10:40:00","10:40",2689,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684261_10301456461","Amiens-Douai",">","Arras","Douai",2022,2022,6,37,"2022-02-07T23:00:00","23:00","2022-09-16T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","10301684261_10301454061","Amiens-Douai",">","Arras","Douai",2021,2022,50,49,"2021-12-13T14:29:00","14:29","2022-12-09T15:20:00","15:20",3864,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301686061_10301486661","Amiens-Douai",">","Arras","Bif d'Agny",2021,2022,50,49,"2021-12-13T09:24:00","09:24","2022-12-09T10:26:00","10:26",2630,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301685961_10301525861","Paris-Busigny",">","Ormoy","Longueil",2021,2022,50,49,"2021-12-13T10:57:00","10:57","2022-12-09T12:33:00","12:33",3164,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301685961_10301524061","Paris-Busigny",">","Ormoy","Longueil",2022,2022,1,46,"2022-01-03T23:22:00","23:22","2022-11-18T05:10:00","05:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"125 jours dans le régime binaire"]
["SNCF Réseau","10301685961_10301525061","Paris-Busigny",">","Ormoy","Longueil",2021,2022,50,49,"2021-12-13T14:20:00","14:20","2022-12-09T16:00:00","16:00",4033,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301685061_10301560861","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2021,2022,50,49,"2021-12-13T15:07:00","15:07","2022-12-09T15:44:00","15:44",3965,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301685061_10301559261","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2021,2022,50,49,"2021-12-13T14:44:00","14:44","2022-12-09T15:37:00","15:37",3936,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301685061_10301558461","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2022,2022,17,46,"2022-04-25T09:30:00","09:30","2022-11-18T13:30:00","13:30",247,"DAY",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10301685061_10301560061","Amiens-Douai",">","Longueau","Bif de l'arbre Robert exclue",2021,2022,50,48,"2021-12-13T00:30:00","00:30","2022-11-28T03:30:00","03:30",41,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10301688961_10301415061","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2022,50,49,"2021-12-13T11:00:00","11:00","2022-12-09T12:15:00","12:15",3088,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688961_10301419261","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2022,50,49,"2021-12-13T09:32:00","09:32","2022-12-09T10:17:00","10:17",2592,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688961_10301422461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2022,50,49,"2021-12-13T09:17:00","09:17","2022-12-09T10:00:00","10:00",2520,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688961_10301418461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2022,50,49,"2021-12-13T10:50:00","10:50","2022-12-09T12:00:00","12:00",3025,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688961_10301420861","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2022,50,49,"2021-12-13T11:15:00","11:15","2022-12-09T12:25:00","12:25",3130,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688961_10301415861","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2022,51,47,"2021-12-26T21:28:00","21:28","2022-11-27T01:08:00","01:08",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","10301688961_10301421661","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2022,50,49,"2021-12-13T09:00:00","09:00","2022-12-09T09:46:00","09:46",2461,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301688961_10301420061","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2021,2022,51,47,"2021-12-26T21:27:00","21:27","2022-11-27T23:57:00","23:57",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","10301688961_10301417461","Calais-Lille-Aulnoye",">","Hazebrouck","Calais",2022,2022,4,37,"2022-01-24T10:00:00","10:00","2022-09-16T14:00:00","14:00",536,"DAY",null,null,null,null,null,null,null,null,null,null,null,"39 jours dans le régime binaire"]
["SNCF Réseau","10301684961_10301564461","Boulogne-Calais",">","Boulogne","Marquise",2022,2022,5,49,"2022-01-31T22:15:00","22:15","2022-12-09T04:19:00","04:19",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"108 jours dans le régime binaire"]
["SNCF Réseau","10301684961_10301563661","Boulogne-Calais",">","Boulogne","Marquise",2021,2022,50,49,"2021-12-13T11:05:00","11:05","2022-12-09T11:55:00","11:55",3003,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684961_10301566061","Boulogne-Calais",">","Boulogne","Marquise",2021,2022,50,49,"2021-12-13T14:15:00","14:15","2022-12-09T15:35:00","15:35",3928,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684961_10301562861","Boulogne-Calais",">","Boulogne","Marquise",2022,2022,5,49,"2022-01-31T22:03:00","22:03","2022-12-09T04:38:00","04:38",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"105 jours dans le régime binaire"]
["SNCF Réseau","10301684961_10301562061","Boulogne-Calais",">","Boulogne","Marquise",2021,2022,51,49,"2021-12-20","00:00","2022-12-05T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10301684961_10301565261","Boulogne-Calais",">","Boulogne","Marquise",2021,2022,51,49,"2021-12-20","00:00","2022-12-05T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301475461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2021,2022,50,49,"2021-12-13T09:58:00","09:58","2022-12-09T11:05:00","11:05",2794,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301469061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2021,2022,50,49,"2021-12-13T14:18:00","14:18","2022-12-09T15:03:00","15:03",3793,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301474661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2022,2022,1,49,"2022-01-03T00:10:00","00:10","2022-12-05T03:20:00","03:20",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301471461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2022,2022,1,49,"2022-01-03T01:30:00","01:30","2022-12-05T04:25:00","04:25",78,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301473061","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2021,2022,50,49,"2021-12-13T10:25:00","10:25","2022-12-09T11:37:00","11:37",2928,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301469861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2022,2022,1,49,"2022-01-03T00:20:00","00:20","2022-12-05T03:30:00","03:30",62,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301467461","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2021,2022,50,49,"2021-12-13T14:20:00","14:20","2022-12-09T15:15:00","15:15",3843,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301472261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2021,2022,50,49,"2021-12-13T14:05:00","14:05","2022-12-09T14:55:00","14:55",3759,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301470661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2022,2022,1,49,"2022-01-03T00:35:00","00:35","2022-12-05T03:20:00","03:20",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301465661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2022,2022,1,46,"2022-01-03T23:39:00","23:39","2022-11-18T04:59:00","04:59",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"125 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301466661","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2022,2022,1,49,"2022-01-03T01:20:00","01:20","2022-12-05T04:05:00","04:05",72,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301468261","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2022,2022,1,49,"2022-01-03T00:05:00","00:05","2022-12-05T03:10:00","03:10",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10301684361_10301473861","Paris-Busigny",">","Longueil Ste Marie","Tergnier",2021,2022,50,49,"2021-12-13T10:05:00","10:05","2022-12-09T11:20:00","11:20",2857,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10314846061_10314629061","Sarrebourg-Basel",">","Colmar","NeufBrisach",2022,2022,35,36,"2022-09-02T11:40:00","11:40","2022-09-09T15:40:00","15:40",19,"DAY",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","10314846061_10314630061","Sarrebourg-Basel",">","Colmar","NeufBrisach",2022,2022,35,36,"2022-08-29T12:00:00","12:00","2022-09-08T20:00:00","20:00",148,"DAY",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","10314849461_10314621061","Longuyon-Metz-Sarrebourg",">","Hauconcourt","Woippy",2022,2022,8,47,"2022-02-21T10:00:00","10:00","2022-11-25T18:00:00","18:00",260,"DAY",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10314841461_10314825661","Sarrebourg-Basel",">","Mulhouse","Chalampe",2022,2022,40,41,"2022-10-03T22:00:00","22:00","2022-10-13T04:00:00","04:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","10314841461_10314827261","Sarrebourg-Basel",">","Mulhouse","Chalampe",2021,2022,50,49,"2021-12-14T08:52:00","08:52","2022-12-09T09:52:00","09:52",1461,"DAY",null,null,null,null,null,null,null,null,null,null,null,"149 jours dans le régime binaire"]
["SNCF Réseau","10293429161_10293289661","Valence - Avignon",">","Portes","Livron (par RG)",2021,2022,50,49,"2021-12-13T01:55:00","01:55","2022-12-05T04:45:00","04:45",88,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293429161_10293292861","Valence - Avignon",">","Portes","Livron (par RG)",2022,2022,7,40,"2022-02-14T10:43:00","10:43","2022-10-07T15:37:00","15:37",535,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293429161_10293292061","Valence - Avignon",">","Portes","Livron (par RG)",2022,2022,7,40,"2022-02-14T08:56:00","08:56","2022-10-07T13:37:00","13:37",467,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293429161_10293290461","Valence - Avignon",">","Portes","Livron (par RG)",2021,2022,50,49,"2021-12-13T12:34:00","12:34","2022-12-09T13:40:00","13:40",2720,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","10293429161_10293291261","Valence - Avignon",">","Portes","Livron (par RG)",2021,2022,50,49,"2021-12-13T12:05:00","12:05","2022-12-09T12:55:00","12:55",2571,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","10293429161_10293293661","Valence - Avignon",">","Portes","Livron (par RG)",2022,2022,1,48,"2022-01-09T23:54:00","23:54","2022-12-04T03:07:00","03:07",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293429761_10293393061","Valence - Avignon",">","Livron","Pierrelatte",2022,2022,7,40,"2022-02-14T10:44:00","10:44","2022-10-07T16:02:00","16:02",550,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293429761_10293391461","Valence - Avignon",">","Livron","Pierrelatte",2022,2022,7,40,"2022-02-14T08:49:00","08:49","2022-10-07T13:17:00","13:17",456,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293429761_10293390661","Valence - Avignon",">","Livron","Pierrelatte",2021,2022,50,49,"2021-12-13T11:52:00","11:52","2022-12-09T12:20:00","12:20",2479,"DAY",null,null,null,null,null,null,null,null,null,null,null,"202 jours dans le régime binaire"]
["SNCF Réseau","10293429761_10293393861","Valence - Avignon",">","Livron","Pierrelatte",2021,2022,50,49,"2021-12-13T12:41:00","12:41","2022-12-09T14:11:00","14:11",2852,"DAY",null,null,null,null,null,null,null,null,null,null,null,"202 jours dans le régime binaire"]
["SNCF Réseau","10293429761_10293392261","Valence - Avignon",">","Livron","Pierrelatte",2021,2022,50,49,"2021-12-13T00:10:00","00:10","2022-12-05T03:40:00","03:40",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293429761_10293389861","Valence - Avignon",">","Livron","Pierrelatte",2021,2022,50,49,"2021-12-13T02:05:00","02:05","2022-12-05T04:35:00","04:35",85,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293429561_10293296461","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2022,50,42,"2021-12-13T11:55:00","11:55","2022-10-21T12:00:00","12:00",1644,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
["SNCF Réseau","10293429561_10293299661","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2022,50,42,"2021-12-13T11:00:00","11:00","2022-10-21T11:22:00","11:22",1557,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
["SNCF Réseau","10293429561_10293302261","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2022,2022,37,44,"2022-09-12T01:59:00","01:59","2022-10-31T04:22:00","04:22",15,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"4 jours dans le régime binaire"]
["SNCF Réseau","10293429561_10293298861","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2022,50,42,"2021-12-13T12:33:00","12:33","2022-10-21T14:16:00","14:16",1956,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
["SNCF Réseau","10293429561_10293301261","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2022,2022,10,49,"2022-03-07T09:47:00","09:47","2022-12-09T15:47:00","15:47",1757,"DAY",null,null,null,null,null,null,null,null,null,null,null,"112 jours dans le régime binaire"]
["SNCF Réseau","10293429561_10293297261","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2022,50,47,"2021-12-19T23:05:00","23:05","2022-11-27T02:55:00","02:55",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293429561_10293295661","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2022,51,48,"2021-12-20T00:05:00","00:05","2022-11-28T03:32:00","03:32",67,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293429561_10293298061","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2022,50,42,"2021-12-13T13:16:00","13:16","2022-10-21T14:46:00","14:46",2024,"DAY",null,null,null,null,null,null,null,null,null,null,null,"138 jours dans le régime binaire"]
["SNCF Réseau","10293429561_10293300461","Valence - Avignon",">","La Voulte","VilleneuvelesA. (par RD)",2021,2022,51,48,"2021-12-20T02:49:00","02:49","2022-11-28T04:59:00","04:59",91,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293427961_10293408861","Lyon-Valence",">","Vienne","St Rambert (par RG)",2022,2022,7,40,"2022-02-14T10:21:00","10:21","2022-10-07T14:55:00","14:55",511,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293427961_10293406461","Lyon-Valence",">","Vienne","St Rambert (par RG)",2021,2022,50,49,"2021-12-13T11:40:00","11:40","2022-12-09T12:58:00","12:58",2581,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","10293427961_10293407261","Lyon-Valence",">","Vienne","St Rambert (par RG)",2022,2022,1,48,"2022-01-09T23:00:00","23:00","2022-12-04T02:20:00","02:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293427961_10293410461","Lyon-Valence",">","Vienne","St Rambert (par RG)",2021,2022,50,49,"2021-12-13T13:18:00","13:18","2022-12-09T14:00:00","14:00",2786,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","10293427961_10293408061","Lyon-Valence",">","Vienne","St Rambert (par RG)",2021,2022,50,49,"2021-12-13T02:55:00","02:55","2022-12-05T05:35:00","05:35",103,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293427961_10293409661","Lyon-Valence",">","Vienne","St Rambert (par RG)",2022,2022,7,40,"2022-02-14T09:43:00","09:43","2022-10-07T14:55:00","14:55",512,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293429261_10293272861","Lyon-Valence",">","RaccPeyraud","St Rambert",2022,2022,11,46,"2022-03-14T09:58:00","09:58","2022-11-18T14:58:00","14:58",289,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10293427861_10293334061","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2022,2022,7,40,"2022-02-14T10:05:00","10:05","2022-10-07T15:20:00","15:20",526,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293427861_10293330861","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2022,2022,7,40,"2022-02-14T10:01:00","10:01","2022-10-07T14:29:00","14:29",496,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293427861_10293334861","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2022,50,49,"2021-12-13T12:57:00","12:57","2022-12-09T13:29:00","13:29",2683,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","10293427861_10293335661","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2022,50,49,"2021-12-13T11:59:00","11:59","2022-12-09T13:28:00","13:28",2681,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","10293427861_10293331661","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2022,50,49,"2021-12-13T12:10:00","12:10","2022-12-09T13:10:00","13:10",2621,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","10293427861_10293332461","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2022,2022,1,48,"2022-01-09T23:12:00","23:12","2022-12-04T02:51:00","02:51",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293427861_10293330061","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2022,50,49,"2021-12-13T02:34:00","02:34","2022-12-05T05:10:00","05:10",95,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293427861_10293333261","Lyon-Valence",">","St Rambert","Bif du Cagnard (par RG)",2021,2022,50,49,"2021-12-13T02:10:00","02:10","2022-12-05T05:10:00","05:10",96,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293428861_10293339861","Valence - Avignon",">","Pierrelatte","Sorgues",2022,2022,7,40,"2022-02-14T08:32:00","08:32","2022-10-07T12:50:00","12:50",440,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293428861_10293341461","Valence - Avignon",">","Pierrelatte","Sorgues",2022,2022,7,49,"2022-02-14T11:00:00","11:00","2022-12-09T16:35:00","16:35",652,"DAY",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","10293428861_10293338261","Valence - Avignon",">","Pierrelatte","Sorgues",2021,2022,50,48,"2021-12-13T13:13:00","13:13","2022-12-02T14:48:00","14:48",3139,"DAY",null,null,null,null,null,null,null,null,null,null,null,"213 jours dans le régime binaire"]
["SNCF Réseau","10293428861_10293340661","Valence - Avignon",">","Pierrelatte","Sorgues",2021,2022,50,48,"2021-12-13T11:17:00","11:17","2022-12-02T11:43:00","11:43",2425,"DAY",null,null,null,null,null,null,null,null,null,null,null,"208 jours dans le régime binaire"]
["SNCF Réseau","10293428661_10293303861","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2022,2022,10,49,"2022-03-07T08:36:00","08:36","2022-12-09T14:36:00","14:36",692,"DAY",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","10293428661_10293305661","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2021,2022,50,42,"2021-12-13T11:49:00","11:49","2022-10-21T13:30:00","13:30",2283,"DAY",null,null,null,null,null,null,null,null,null,null,null,"170 jours dans le régime binaire"]
["SNCF Réseau","10293428661_10293307261","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2021,2022,50,42,"2021-12-13T12:50:00","12:50","2022-10-21T13:00:00","13:00",2197,"DAY",null,null,null,null,null,null,null,null,null,null,null,"170 jours dans le régime binaire"]
["SNCF Réseau","10293428661_10293304861","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2021,2022,50,47,"2021-12-19T22:20:00","22:20","2022-11-27T02:00:00","02:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293428661_10293306461","Lyon-Valence",">","Peyraud","LaVoulte (par RD)",2021,2022,51,48,"2021-12-20T03:35:00","03:35","2022-11-28T05:55:00","05:55",108,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293428561_10293326061","Valence - Avignon",">","Sorgues","Avignon",2022,2022,7,40,"2022-02-14T11:40:00","11:40","2022-10-07T16:23:00","16:23",561,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293428561_10293326861","Valence - Avignon",">","Sorgues","Avignon",2021,2022,50,49,"2021-12-13T13:45:00","13:45","2022-12-09T14:49:00","14:49",2919,"DAY",null,null,null,null,null,null,null,null,null,null,null,"198 jours dans le régime binaire"]
["SNCF Réseau","10293428561_10293325261","Valence - Avignon",">","Sorgues","Avignon",2021,2022,50,49,"2021-12-13T10:43:00","10:43","2022-12-09T11:37:00","11:37",2289,"DAY",null,null,null,null,null,null,null,null,null,null,null,"198 jours dans le régime binaire"]
["SNCF Réseau","10293428561_10293328461","Valence - Avignon",">","Sorgues","Avignon",2022,2022,7,40,"2022-02-14T08:16:00","08:16","2022-10-07T12:50:00","12:50",440,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293429361_10293400861","Lyon-Valence",">","Givors","Peyraud (par RD)",2021,2022,50,44,"2021-12-13T11:15:00","11:15","2022-11-04T12:48:00","12:48",2215,"DAY",null,null,null,null,null,null,null,null,null,null,null,"174 jours dans le régime binaire"]
["SNCF Réseau","10293429361_10293403461","Lyon-Valence",">","Givors","Peyraud (par RD)",2021,2022,50,44,"2021-12-13T13:28:00","13:28","2022-11-04T13:50:00","13:50",2393,"DAY",null,null,null,null,null,null,null,null,null,null,null,"174 jours dans le régime binaire"]
["SNCF Réseau","10293429361_10293404261","Lyon-Valence",">","Givors","Peyraud (par RD)",2021,2022,51,48,"2021-12-20T04:05:00","04:05","2022-11-28T06:35:00","06:35",121,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293429361_10293402661","Lyon-Valence",">","Givors","Peyraud (par RD)",2021,2022,50,47,"2021-12-19T21:50:00","21:50","2022-11-27T01:20:00","01:20",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293429361_10293401661","Lyon-Valence",">","Givors","Peyraud (par RD)",2022,2022,10,47,"2022-03-07T09:15:00","09:15","2022-11-25T15:15:00","15:15",524,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293428961_10293395461","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2021,2022,50,49,"2021-12-13T13:26:00","13:26","2022-12-09T14:19:00","14:19",2849,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","10293428961_10293399461","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2022,2022,1,48,"2022-01-09T23:06:00","23:06","2022-12-04T02:12:00","02:12",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293428961_10293398661","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2021,2022,50,49,"2021-12-13T02:57:00","02:57","2022-12-05T05:47:00","05:47",106,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10293428961_10293397061","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2022,2022,7,40,"2022-02-14T09:34:00","09:34","2022-10-07T14:36:00","14:36",501,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293428961_10293397861","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2022,2022,7,40,"2022-02-14T10:26:00","10:26","2022-10-07T15:16:00","15:16",523,"DAY",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10293428961_10293396261","Lyon-Valence",">","Chasse/R.","Vienne (par RG)",2021,2022,50,49,"2021-12-13T11:32:00","11:32","2022-12-09T12:38:00","12:38",2515,"DAY",null,null,null,null,null,null,null,null,null,null,null,"200 jours dans le régime binaire"]
["SNCF Réseau","10293428161_10293280061","Valence - Avignon",">","Raccordement de Livron","LaVoulte",2022,2022,11,46,"2022-03-14T10:32:00","10:32","2022-11-18T15:32:00","15:32",300,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10292128961_10291948761","Avignon-Miramasparest",">","Cavaillon","Miramas",2021,2022,50,49,"2021-12-13T13:37:00","13:37","2022-12-09T15:00:00","15:00",3781,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128961_10291946961","Avignon-Miramasparest",">","Cavaillon","Miramas",2021,2022,50,49,"2021-12-13T10:22:00","10:22","2022-12-09T10:55:00","10:55",2751,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128961_10291947761","Avignon-Miramasparest",">","Cavaillon","Miramas",2022,2022,7,49,"2022-02-14T09:10:00","09:10","2022-12-09T13:10:00","13:10",1044,"DAY",null,null,null,null,null,null,null,null,null,null,null,"80 jours dans le régime binaire"]
["SNCF Réseau","10292128861_10292009761","Miramas-Marseille",">","Rognac","L'Estaque",2021,2022,50,49,"2021-12-13T11:05:00","11:05","2022-12-09T12:10:00","12:10",3067,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128861_10292007161","Miramas-Marseille",">","Rognac","L'Estaque",2021,2022,50,49,"2021-12-13T10:02:00","10:02","2022-12-09T10:56:00","10:56",2756,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128861_10292008761","Miramas-Marseille",">","Rognac","L'Estaque",2022,2022,13,49,"2022-03-29","00:00","2022-12-10T04:30:00","04:30",562,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"125 jours dans le régime binaire"]
["SNCF Réseau","10292128861_10292010561","Miramas-Marseille",">","Rognac","L'Estaque",2021,2022,50,49,"2021-12-13T09:56:00","09:56","2022-12-09T10:50:00","10:50",2730,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128861_10292007961","Miramas-Marseille",">","Rognac","L'Estaque",2021,2022,50,49,"2021-12-13T10:56:00","10:56","2022-12-09T12:04:00","12:04",3041,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292130461_10291875561","Avignon-Miramasparest",">","Avignon","Cavaillon",2021,2022,50,49,"2021-12-13T12:50:00","12:50","2022-12-09T14:21:00","14:21",3617,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292130461_10291872961","Avignon-Miramasparest",">","Avignon","Cavaillon",2022,2022,7,49,"2022-02-14T09:10:00","09:10","2022-12-09T13:10:00","13:10",1044,"DAY",null,null,null,null,null,null,null,null,null,null,null,"80 jours dans le régime binaire"]
["SNCF Réseau","10292130461_10291873961","Avignon-Miramasparest",">","Avignon","Cavaillon",2021,2022,50,49,"2021-12-13T11:04:00","11:04","2022-12-09T11:33:00","11:33",2911,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128061_10291931761","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2022,2022,10,49,"2022-03-08","00:00","2022-12-10T04:30:00","04:30",486,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"108 jours dans le régime binaire"]
["SNCF Réseau","10292128061_10291930961","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2021,2022,50,49,"2021-12-13T09:49:00","09:49","2022-12-09T10:46:00","10:46",2714,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128061_10291933161","Miramas-Marseille",">","L'Estaque","Marseille via PLM",2021,2022,50,49,"2021-12-13T11:11:00","11:11","2022-12-09T12:13:00","12:13",3079,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292130161_10291967161","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2022,2022,8,45,"2022-02-21T22:30:00","22:30","2022-11-11T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"80 jours dans le régime binaire"]
["SNCF Réseau","10292130161_10291968161","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2021,2022,50,49,"2021-12-13T10:06:00","10:06","2022-12-09T10:55:00","10:55",2751,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292130161_10291966361","Miramas-Fos-Marseille",">","Miramas","Lavalduc",2021,2022,50,49,"2021-12-13T14:51:00","14:51","2022-12-09T16:06:00","16:06",4058,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128761_10291822761","Avignon-Miramasparouest",">","Avignon","Tarascon",2022,2022,7,48,"2022-02-14T23:10:00","23:10","2022-12-02T05:04:00","05:04",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","10292128761_10291823561","Avignon-Miramasparouest",">","Avignon","Tarascon",2022,2022,14,49,"2022-04-04T23:15:00","23:15","2022-12-09T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","10292128761_10291826161","Avignon-Miramasparouest",">","Avignon","Tarascon",2021,2022,50,49,"2021-12-13T14:00:00","14:00","2022-12-09T15:06:00","15:06",3806,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128761_10291824361","Avignon-Miramasparouest",">","Avignon","Tarascon",2022,2022,7,49,"2022-02-15","00:00","2022-12-10T02:00:00","02:00",180,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"90 jours dans le régime binaire"]
["SNCF Réseau","10292128761_10291827761","Avignon-Miramasparouest",">","Avignon","Tarascon",2021,2022,50,49,"2021-12-13T10:21:00","10:21","2022-12-09T11:13:00","11:13",2827,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292127961_10291869761","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2021,2022,50,49,"2021-12-13T15:26:00","15:26","2022-12-09T16:54:00","16:54",4243,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","10292127961_10291868961","Miramas-Fos-Marseille",">","Martigues","L'Estaque",2021,2022,50,49,"2021-12-13T09:33:00","09:33","2022-12-09T10:01:00","10:01",2514,"DAY",null,null,null,null,null,null,null,null,null,null,null,"252 jours dans le régime binaire"]
["SNCF Réseau","10292130261_10291794161","Avignon-Miramasparouest",">","Tarascon","Miramas",2021,2022,50,49,"2021-12-13T10:08:00","10:08","2022-12-09T11:34:00","11:34",2916,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292130261_10291795761","Avignon-Miramasparouest",">","Tarascon","Miramas",2021,2022,50,49,"2021-12-13T23:15:00","23:15","2022-12-09T05:13:00","05:13",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"194 jours dans le régime binaire"]
["SNCF Réseau","10292130261_10291794961","Avignon-Miramasparouest",">","Tarascon","Miramas",2021,2022,50,49,"2021-12-13T10:52:00","10:52","2022-12-09T11:25:00","11:25",2877,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292129161_10291943961","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2021,2022,50,49,"2021-12-13T15:06:00","15:06","2022-12-09T16:23:00","16:23",4129,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292129161_10291945561","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2021,2022,50,45,"2021-12-13T22:30:00","22:30","2022-11-11T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"85 jours dans le régime binaire"]
["SNCF Réseau","10292129161_10291944761","Miramas-Fos-Marseille",">","Lavalduc","Martigues",2021,2022,50,49,"2021-12-13T09:53:00","09:53","2022-12-09T10:38:00","10:38",2680,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128261_10291781361","Miramas-Fos-Marseille",">","Lavalduc","Fos",2021,2022,50,49,"2021-12-13T15:16:00","15:16","2022-12-09T16:16:00","16:16",4100,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128261_10291784561","Miramas-Fos-Marseille",">","Lavalduc","Fos",2021,2022,50,49,"2021-12-13T09:48:00","09:48","2022-12-09T10:48:00","10:48",2722,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128661_10291810961","Miramas-Marseille",">","Miramas","Rognac",2022,2022,13,49,"2022-03-29","00:00","2022-12-10T04:30:00","04:30",558,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"124 jours dans le régime binaire"]
["SNCF Réseau","10292128661_10291808561","Miramas-Marseille",">","Miramas","Rognac",2021,2022,50,49,"2021-12-13T10:20:00","10:20","2022-12-09T11:08:00","11:08",2806,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128661_10291811961","Miramas-Marseille",">","Miramas","Rognac",2021,2022,50,49,"2021-12-13T10:39:00","10:39","2022-12-09T11:51:00","11:51",2987,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128661_10291809361","Miramas-Marseille",">","Miramas","Rognac",2021,2022,50,49,"2021-12-13T10:51:00","10:51","2022-12-09T11:55:00","11:55",3004,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292128661_10291807761","Miramas-Marseille",">","Miramas","Rognac",2021,2022,50,49,"2021-12-13T10:08:00","10:08","2022-12-09T11:05:00","11:05",2793,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10319363361_10319193161","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2021,2022,50,49,"2021-12-13T15:25:00","15:25","2022-12-09T16:35:00","16:35",4180,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10319363361_10319192361","Hazebrouck-Lens-Aulnoye",">","Fouquereuil","StPolTernoise",2022,2022,6,49,"2022-02-07T20:25:00","20:25","2022-12-09T04:55:00","04:55",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"142 jours dans le régime binaire"]
["SNCF Réseau","10319361561_10319256761","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2021,2022,50,49,"2021-12-13T09:54:00","09:54","2022-12-09T10:54:00","10:54",2747,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10319361561_10319254961","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2021,2022,50,49,"2021-12-13T14:00:00","14:00","2022-12-09T15:00:00","15:00",3781,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10319361561_10319255761","Hazebrouck-Lens-Aulnoye",">","DonSainghin","Bethune",2022,2022,4,49,"2022-01-24T21:45:00","21:45","2022-12-09T05:25:00","05:25",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"169 jours dans le régime binaire"]
["SNCF Réseau","10319359661_10319264761","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2022,2022,10,39,"2022-03-07T21:03:00","21:03","2022-09-30T05:20:00","05:20",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"45 jours dans le régime binaire"]
["SNCF Réseau","10319359661_10319262361","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2021,2022,50,49,"2021-12-13T13:50:00","13:50","2022-12-07T15:35:00","15:35",1560,"DAY",null,null,null,null,null,null,null,null,null,null,null,"101 jours dans le régime binaire"]
["SNCF Réseau","10319359661_10319263961","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2021,2022,50,49,"2021-12-14T13:50:00","13:50","2022-12-09T16:50:00","16:50",2544,"DAY",null,null,null,null,null,null,null,null,null,null,null,"152 jours dans le régime binaire"]
["SNCF Réseau","10319359661_10319263161","Hazebrouck-Lens-Aulnoye",">","Trith","Valenciennes",2021,2022,50,49,"2021-12-13T13:50:00","13:50","2022-12-09T16:50:00","16:50",4245,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10319363061_10319238361","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2022,2022,2,40,"2022-01-10T21:03:00","21:03","2022-10-07T05:20:00","05:20",16,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"62 jours dans le régime binaire"]
["SNCF Réseau","10319363061_10319236361","Hazebrouck-Lens-Aulnoye",">","Lourches","Trith",2021,2022,50,49,"2021-12-13T13:50:00","13:50","2022-12-09T16:50:00","16:50",4245,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10319360861_10319241761","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2022,2022,2,45,"2022-01-10T10:00:00","10:00","2022-11-11T15:00:00","15:00",440,"DAY",null,null,null,null,null,null,null,null,null,null,null,"30 jours dans le régime binaire"]
["SNCF Réseau","10319360861_10319240961","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2021,2022,50,49,"2021-12-13T10:00:00","10:00","2022-12-09T12:30:00","12:30",3152,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10319360861_10319240161","Aulnoye-Feignies-Jeumont",">","Hautmont","Feignies",2021,2022,50,49,"2021-12-13T11:20:00","11:20","2022-12-09T13:20:00","13:20",3362,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10319365361_10319232361","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2022,2022,7,49,"2022-02-14T22:00:00","22:00","2022-12-09T04:00:00","04:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"28 jours dans le régime binaire"]
["SNCF Réseau","10319365361_10319231561","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2021,2022,50,49,"2021-12-13T09:35:00","09:35","2022-12-09T10:35:00","10:35",2742,"DAY",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","10319365361_10319233161","Calais-Dunkerque-Hazebrouck",">","Puythouck","Fontinettes",2021,2022,50,49,"2021-12-18T09:00:00","09:00","2022-12-10T10:35:00","10:35",1081,"DAY",null,null,null,null,null,null,null,null,null,null,null,"103 jours dans le régime binaire"]
["SNCF Réseau","10299952161_10299824661","Aulnoye-Longuyon",">","Tournes","Charleville",2021,2022,50,49,"2021-12-13T12:25:00","12:25","2022-12-09T13:21:00","13:21",3271,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","10299952161_10299825461","Aulnoye-Longuyon",">","Tournes","Charleville",2021,2022,50,49,"2021-12-13T13:35:00","13:35","2022-12-09T14:40:00","14:40",3594,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","10299952161_10299823061","Aulnoye-Longuyon",">","Tournes","Charleville",2021,2022,50,48,"2021-12-19T23:55:00","23:55","2022-12-04T02:55:00","02:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10299952161_10299823861","Aulnoye-Longuyon",">","Tournes","Charleville",2022,2022,3,43,"2022-01-17T10:00:00","10:00","2022-10-28T14:54:00","14:54",943,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10299952161_10299827061","Aulnoye-Longuyon",">","Tournes","Charleville",2021,2022,50,48,"2021-12-19T23:00:00","23:00","2022-12-04T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10299952161_10299826261","Aulnoye-Longuyon",">","Tournes","Charleville",2022,2022,3,43,"2022-01-17T09:15:00","09:15","2022-10-28T14:20:00","14:20",908,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10299951961_10299778061","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2021,2022,50,49,"2021-12-13T10:15:00","10:15","2022-12-09T11:50:00","11:50",2983,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951961_10299778861","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2021,2022,50,49,"2021-12-13T13:43:00","13:43","2022-12-09T14:09:00","14:09",3566,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951961_10299775661","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2021,2022,51,40,"2021-12-20T01:36:00","01:36","2022-10-03T04:13:00","04:13",53,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"13 jours dans le régime binaire"]
["SNCF Réseau","10299951961_10299774861","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2022,2022,8,39,"2022-02-21T22:21:00","22:21","2022-09-30T05:35:00","05:35",17,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"95 jours dans le régime binaire"]
["SNCF Réseau","10299951961_10299776461","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2021,2022,50,39,"2021-12-19T23:00:00","23:00","2022-10-02T02:32:00","02:32",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","10299951961_10299777261","Calais-Lille-Aulnoye",">","Lille","Valenciennes",2022,2022,8,39,"2022-02-21T23:04:00","23:04","2022-09-30T04:23:00","04:23",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"95 jours dans le régime binaire"]
["SNCF Réseau","10299951461_10299831661","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2021,2022,50,49,"2021-12-13T14:30:00","14:30","2022-12-09T15:50:00","15:50",3991,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951461_10299830861","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2021,2022,50,49,"2021-12-13T13:57:00","13:57","2022-12-09T14:37:00","14:37",3684,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951461_10299828261","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2021,2022,50,46,"2021-12-13","00:00","2022-11-14T03:00:00","03:00",69,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","10299951461_10299829061","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2021,2022,50,46,"2021-12-13","00:00","2022-11-14T03:10:00","03:10",72,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","10299951461_10299829861","Hazebrouck-Lens-Aulnoye",">","Somain","Valenciennes",2022,2022,3,49,"2022-01-17T23:00:00","23:00","2022-12-09T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"73 jours dans le régime binaire"]
["SNCF Réseau","10299950961_10299867461","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2021,2022,50,49,"2021-12-13T13:51:00","13:51","2022-12-09T14:40:00","14:40",3696,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950961_10299865061","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2021,2022,50,49,"2021-12-13T13:07:00","13:07","2022-12-09T13:57:00","13:57",3516,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950961_10299866661","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2021,2022,50,49,"2021-12-13T10:11:00","10:11","2022-12-09T11:38:00","11:38",2933,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950961_10299862461","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2021,2022,51,45,"2021-12-26T00:15:00","00:15","2022-11-13T02:45:00","02:45",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","10299950961_11420236161","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2021,2022,50,49,"2021-12-13T13:40:00","13:40","2022-12-09T14:28:00","14:28",3646,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950961_10299865861","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2021,2022,51,45,"2021-12-26T23:50:00","23:50","2022-11-13T03:15:00","03:15",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"24 jours dans le régime binaire"]
["SNCF Réseau","10299950961_10299863261","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2022,2022,4,49,"2022-01-24T23:00:00","23:00","2022-12-09T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","10299950961_10299864261","Hazebrouck-Lens-Aulnoye",">","Lens","Hazebrouck",2021,2022,50,49,"2021-12-13T10:38:00","10:38","2022-12-09T11:48:00","11:48",2974,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951561_10299835461","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2021,2022,51,41,"2021-12-20T00:20:00","00:20","2022-10-10T03:00:00","03:00",44,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10299951561_10299836261","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2021,2022,51,41,"2021-12-20T01:00:00","01:00","2022-10-10T04:00:00","04:00",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10299951561_10299832861","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2021,2022,50,49,"2021-12-13T14:25:00","14:25","2022-12-09T15:08:00","15:08",3814,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951561_10299833661","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2021,2022,50,49,"2021-12-13T09:46:00","09:46","2022-12-09T10:54:00","10:54",2747,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951561_10299834461","Hazebrouck-Lens-Aulnoye",">","Ostricourt","Douai",2022,2022,9,49,"2022-02-28T22:43:00","22:43","2022-12-09T04:43:00","04:43",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10299950461_10299805661","Calais-Lille-Aulnoye",">","Lille Lambersart",null,2021,2022,50,49,"2021-12-13T11:05:00","11:05","2022-12-09T12:00:00","12:00",3024,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950461_10299804861","Calais-Lille-Aulnoye",">","Lille Lambersart",null,2021,2022,50,49,"2021-12-13T10:19:00","10:19","2022-12-09T11:15:00","11:15",2835,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951061_10299732461","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2021,2022,50,49,"2021-12-13T01:10:00","01:10","2022-12-05T04:10:00","04:10",215,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10299951061_10299735861","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2021,2022,50,49,"2021-12-13T10:30:00","10:30","2022-12-09T11:05:00","11:05",2793,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951061_10299734861","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2022,2022,2,41,"2022-01-10T23:05:00","23:05","2022-10-14T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"55 jours dans le régime binaire"]
["SNCF Réseau","10299951061_10299733261","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2021,2022,50,49,"2021-12-13","00:00","2022-12-05T03:00:00","03:00",156,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10299951061_10299734061","Calais-Dunkerque-Hazebrouck",">","Hazebrouck","Dunkerque",2021,2022,50,49,"2021-12-13T11:12:00","11:12","2022-12-09T12:38:00","12:38",3185,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299949961_10299792861","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2022,50,48,"2021-12-19T23:40:00","23:40","2022-12-04T02:40:00","02:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10299949961_10299793661","Aulnoye-Longuyon",">","Mohon","Sedan",2022,2022,3,46,"2022-01-17T10:07:00","10:07","2022-11-18T14:15:00","14:15",1072,"DAY",null,null,null,null,null,null,null,null,null,null,null,"76 jours dans le régime binaire"]
["SNCF Réseau","10299949961_10299790461","Aulnoye-Longuyon",">","Mohon","Sedan",2022,2022,3,46,"2022-01-17T10:40:00","10:40","2022-11-18T14:30:00","14:30",1091,"DAY",null,null,null,null,null,null,null,null,null,null,null,"76 jours dans le régime binaire"]
["SNCF Réseau","10299949961_10299792061","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2022,50,49,"2021-12-13T13:25:00","13:25","2022-12-09T14:24:00","14:24",3586,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10299949961_10299794461","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2022,50,48,"2021-12-19T23:40:00","23:40","2022-12-04T02:40:00","02:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10299949961_10299788861","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2022,50,49,"2021-12-13T13:36:00","13:36","2022-12-09T14:51:00","14:51",3698,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10299949961_10299795261","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2022,50,49,"2021-12-13T13:24:00","13:24","2022-12-09T14:11:00","14:11",3532,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10299949961_10299791261","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2022,50,48,"2021-12-19T23:50:00","23:50","2022-12-04T02:50:00","02:50",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10299949961_10299789661","Aulnoye-Longuyon",">","Mohon","Sedan",2021,2022,50,48,"2021-12-19T23:50:00","23:50","2022-12-04T02:50:00","02:50",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10299950561_10299786661","Aulnoye-Longuyon",">","Liart","Tournes",2022,2022,3,43,"2022-01-17T09:35:00","09:35","2022-10-28T14:54:00","14:54",944,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10299950561_10299785861","Aulnoye-Longuyon",">","Liart","Tournes",2022,2022,3,43,"2022-01-17T09:37:00","09:37","2022-10-28T14:20:00","14:20",907,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10299950561_10299782661","Aulnoye-Longuyon",">","Liart","Tournes",2021,2022,50,49,"2021-12-13T14:00:00","14:00","2022-12-09T14:40:00","14:40",3564,"DAY",null,null,null,null,null,null,null,null,null,null,null,"244 jours dans le régime binaire"]
["SNCF Réseau","10299950561_10299784261","Aulnoye-Longuyon",">","Liart","Tournes",2021,2022,50,49,"2021-12-13T12:05:00","12:05","2022-12-09T13:21:00","13:21",3245,"DAY",null,null,null,null,null,null,null,null,null,null,null,"244 jours dans le régime binaire"]
["SNCF Réseau","10299950561_10299783461","Aulnoye-Longuyon",">","Liart","Tournes",2021,2022,50,48,"2021-12-19T23:00:00","23:00","2022-12-04T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10299950561_10299785061","Aulnoye-Longuyon",">","Liart","Tournes",2021,2022,50,48,"2021-12-19T23:55:00","23:55","2022-12-04T02:55:00","02:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10299950661_10299744061","Aulnoye-Longuyon",">","Aulnoye","Hirson",2021,2022,50,49,"2021-12-13T10:54:00","10:54","2022-12-09T12:15:00","12:15",3088,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950661_10299740861","Aulnoye-Longuyon",">","Aulnoye","Hirson",2021,2022,50,49,"2021-12-13T11:16:00","11:16","2022-12-09T12:28:00","12:28",3142,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950661_10299744861","Aulnoye-Longuyon",">","Aulnoye","Hirson",2021,2022,50,48,"2021-12-19T23:30:00","23:30","2022-12-04T03:00:00","03:00",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10299950661_10299740061","Aulnoye-Longuyon",">","Aulnoye","Hirson",2022,2022,4,48,"2022-01-24T09:20:00","09:20","2022-12-02T16:00:00","16:00",726,"DAY",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","10299950661_10299743261","Aulnoye-Longuyon",">","Aulnoye","Hirson",2021,2022,50,49,"2021-12-13T13:12:00","13:12","2022-12-09T13:42:00","13:42",3452,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950661_10299741661","Aulnoye-Longuyon",">","Aulnoye","Hirson",2021,2022,50,49,"2021-12-13T00:55:00","00:55","2022-12-05T03:30:00","03:30",181,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10299950661_10299742461","Aulnoye-Longuyon",">","Aulnoye","Hirson",2022,2022,4,48,"2022-01-24T09:59:00","09:59","2022-12-02T15:25:00","15:25",699,"DAY",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","10299950161_10299750861","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2021,2022,50,49,"2021-12-13T10:52:00","10:52","2022-12-09T12:20:00","12:20",3109,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950161_10299751661","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2021,2022,50,49,"2021-12-13T13:45:00","13:45","2022-12-09T14:18:00","14:18",3604,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950161_10299753261","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2021,2022,50,49,"2021-12-13T01:10:00","01:10","2022-12-05T03:45:00","03:45",193,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10299950161_10299754061","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2022,2022,14,47,"2022-04-04T08:55:00","08:55","2022-11-23T15:10:00","15:10",688,"DAY",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","10299950161_10299754861","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2021,2022,50,48,"2021-12-19T23:00:00","23:00","2022-12-04T02:28:00","02:28",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10299950161_10299752461","Calais-Lille-Aulnoye",">","Valenciennes","Aulnoye",2022,2022,14,47,"2022-04-04T10:21:00","10:21","2022-11-23T15:14:00","15:14",690,"DAY",null,null,null,null,null,null,null,null,null,null,null,"46 jours dans le régime binaire"]
["SNCF Réseau","10299951361_10299837461","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2022,2022,5,49,"2022-01-31","00:00","2022-12-05T03:10:00","03:10",34,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","10299951361_10299838261","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2022,2022,5,49,"2022-01-31","00:00","2022-12-05T03:00:00","03:00",33,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"11 jours dans le régime binaire"]
["SNCF Réseau","10299951361_10299840061","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2021,2022,50,49,"2021-12-13T14:04:00","14:04","2022-12-09T14:55:00","14:55",3759,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951361_10299840861","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2021,2022,50,49,"2021-12-13T14:20:00","14:20","2022-12-09T15:25:00","15:25",3886,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299951361_10299839061","Hazebrouck-Lens-Aulnoye",">","Douai","Somain",2022,2022,3,46,"2022-01-17T23:30:00","23:30","2022-11-18T05:15:00","05:15",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"41 jours dans le régime binaire"]
["SNCF Réseau","10299950861_10299882261","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2021,2022,51,39,"2021-12-20T01:00:00","01:00","2022-09-26T03:30:00","03:30",41,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10299950861_10299879861","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2022,2022,2,40,"2022-01-10T22:45:00","22:45","2022-10-07T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","10299950861_10299879061","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2021,2022,50,49,"2021-12-13T10:12:00","10:12","2022-12-09T10:53:00","10:53",2743,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950861_10299880661","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2022,2022,2,40,"2022-01-10T22:12:00","22:12","2022-10-07T04:40:00","04:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","10299950861_10299881461","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2021,2022,50,49,"2021-12-13T11:05:00","11:05","2022-12-09T12:28:00","12:28",3142,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299950861_10299883061","Calais-Lille-Aulnoye",">","Lille","Hazebrouck",2021,2022,51,39,"2021-12-20T00:06:00","00:06","2022-09-26T03:30:00","03:30",41,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10299952361_10299771461","Aulnoye-Longuyon",">","Sedan","Longuyon",2021,2022,50,49,"2021-12-13T12:45:00","12:45","2022-12-09T14:15:00","14:15",3492,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","10299952361_10299770661","Aulnoye-Longuyon",">","Sedan","Longuyon",2022,2022,1,49,"2022-01-03T13:00:00","13:00","2022-12-09T14:15:00","14:15",3335,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10299952361_10299769061","Aulnoye-Longuyon",">","Sedan","Longuyon",2022,2022,1,49,"2022-01-03T12:45:00","12:45","2022-12-09T13:30:00","13:30",3159,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10299952361_10299773061","Aulnoye-Longuyon",">","Sedan","Longuyon",2021,2022,50,49,"2021-12-13T00:10:00","00:10","2022-12-05T03:10:00","03:10",148,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10299952361_10299765861","Aulnoye-Longuyon",">","Sedan","Longuyon",2022,2022,3,47,"2022-01-17T10:15:00","10:15","2022-11-25T16:00:00","16:00",1573,"DAY",null,null,null,null,null,null,null,null,null,null,null,"99 jours dans le régime binaire"]
["SNCF Réseau","10299952361_10299767461","Aulnoye-Longuyon",">","Sedan","Longuyon",2021,2022,50,49,"2021-12-13T13:15:00","13:15","2022-12-09T13:45:00","13:45",3369,"DAY",null,null,null,null,null,null,null,null,null,null,null,"246 jours dans le régime binaire"]
["SNCF Réseau","10299952361_10299768261","Aulnoye-Longuyon",">","Sedan","Longuyon",2021,2022,50,48,"2021-12-19T23:00:00","23:00","2022-12-04T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10299952361_10299769861","Aulnoye-Longuyon",">","Sedan","Longuyon",2021,2022,50,48,"2021-12-19T23:00:00","23:00","2022-12-04T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10299952361_10299766661","Aulnoye-Longuyon",">","Sedan","Longuyon",2021,2022,50,49,"2021-12-13T00:10:00","00:10","2022-12-05T03:10:00","03:10",148,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10299952361_10299772261","Aulnoye-Longuyon",">","Sedan","Longuyon",2022,2022,3,47,"2022-01-17T09:15:00","09:15","2022-11-25T13:30:00","13:30",1327,"DAY",null,null,null,null,null,null,null,null,null,null,null,"99 jours dans le régime binaire"]
["SNCF Réseau","10299952561_10299763261","Aulnoye-Longuyon",">","Hirson","Liart",2022,2022,3,48,"2022-01-17T09:10:00","09:10","2022-12-02T14:35:00","14:35",1405,"DAY",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
["SNCF Réseau","10299952561_10299761661","Aulnoye-Longuyon",">","Hirson","Liart",2022,2022,3,48,"2022-01-17T09:30:00","09:30","2022-12-02T14:37:00","14:37",1408,"DAY",null,null,null,null,null,null,null,null,null,null,null,"97 jours dans le régime binaire"]
["SNCF Réseau","10299952561_10299760061","Aulnoye-Longuyon",">","Hirson","Liart",2021,2022,50,49,"2021-12-13T14:25:00","14:25","2022-12-09T15:00:00","15:00",3780,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299952561_10299764061","Aulnoye-Longuyon",">","Hirson","Liart",2021,2022,50,49,"2021-12-13T11:45:00","11:45","2022-12-09T13:05:00","13:05",3298,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10299952561_10299760861","Aulnoye-Longuyon",">","Hirson","Liart",2021,2022,50,49,"2021-12-13","00:00","2022-12-05T03:20:00","03:20",173,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10299952561_10299762461","Aulnoye-Longuyon",">","Hirson","Liart",2021,2022,50,49,"2021-12-13T00:30:00","00:30","2022-12-05T03:15:00","03:15",168,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"52 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295640761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2022,50,49,"2021-12-13T13:38:00","13:38","2022-12-09T14:41:00","14:41",2688,"DAY",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295650361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295646361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2022,50,49,"2021-12-13T11:23:00","11:23","2022-12-09T12:27:00","12:27",2105,"DAY",null,null,null,null,null,null,null,null,null,null,null,"170 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295649561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",223,"DAY",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295647161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2022,50,49,"2021-12-13","00:00","2022-12-05T03:00:00","03:00",81,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295645561","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",223,"DAY",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295648761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2022,50,49,"2021-12-13T14:30:00","14:30","2022-12-09T15:25:00","15:25",2606,"DAY",null,null,null,null,null,null,null,null,null,null,null,"170 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295644761","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295639161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2022,50,49,"2021-12-14T09:21:00","09:21","2022-12-09T10:19:00","10:19",857,"DAY",null,null,null,null,null,null,null,null,null,null,null,"84 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295642361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,3,43,"2022-01-17","00:00","2022-10-24T03:00:00","03:00",54,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295639961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295643161","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2021,2022,50,49,"2021-12-13","00:00","2022-12-05T03:00:00","03:00",81,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295643961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295647961","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,3,43,"2022-01-17","00:00","2022-10-24T03:00:00","03:00",54,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"18 jours dans le régime binaire"]
["SNCF Réseau","10295927861_10295638361","Longuyon-Metz-Sarrebourg","<","Woippy","Maizières",2022,2022,8,48,"2022-02-22T11:30:00","11:30","2022-12-02T15:30:00","15:30",810,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295925461_10295628561","Dijon-Toul",">","Dijon","Is sur Tille",2021,2022,50,49,"2021-12-13T11:35:00","11:35","2022-12-09T12:14:00","12:14",1909,"DAY",null,null,null,null,null,null,null,null,null,null,null,"157 jours dans le régime binaire"]
["SNCF Réseau","10295925461_10295630561","Dijon-Toul",">","Dijon","Is sur Tille",2021,2022,50,49,"2021-12-13T01:10:00","01:10","2022-12-05T03:55:00","03:55",186,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","10295925461_10295633561","Dijon-Toul",">","Dijon","Is sur Tille",2021,2022,50,49,"2021-12-13T00:05:00","00:05","2022-12-05T03:29:00","03:29",167,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","10295925461_10295632561","Dijon-Toul",">","Dijon","Is sur Tille",2021,2022,50,49,"2021-12-13T12:35:00","12:35","2022-12-09T14:01:00","14:01",2188,"DAY",null,null,null,null,null,null,null,null,null,null,null,"157 jours dans le régime binaire"]
["SNCF Réseau","10295925461_10295629561","Dijon-Toul",">","Dijon","Is sur Tille",2022,2022,9,46,"2022-02-28T12:18:00","12:18","2022-11-18T16:40:00","16:40",1537,"DAY",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
["SNCF Réseau","10295925461_10295631561","Dijon-Toul",">","Dijon","Is sur Tille",2022,2022,9,46,"2022-02-28T11:26:00","11:26","2022-11-18T14:58:00","14:58",1380,"DAY",null,null,null,null,null,null,null,null,null,null,null,"93 jours dans le régime binaire"]
["SNCF Réseau","10295924961_10295457961","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2022,2022,3,44,"2022-01-17","00:00","2022-10-31T03:00:00","03:00",60,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10295924961_10295458761","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2022,2022,9,48,"2022-02-28T10:12:00","10:12","2022-12-02T16:12:00","16:12",977,"DAY",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","10295924961_10295455561","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2022,2022,1,49,"2022-01-03T10:55:00","10:55","2022-12-09T11:50:00","11:50",2769,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295924961_10295454761","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2022,2022,1,49,"2022-01-03T14:00:00","14:00","2022-12-09T15:20:00","15:20",3589,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295924961_10295459761","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2022,2022,1,49,"2022-01-03T11:15:00","11:15","2022-12-09T11:55:00","11:55",2789,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295924961_10295457161","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2022,2022,3,44,"2022-01-17T00:25:00","00:25","2022-10-31T03:50:00","03:50",76,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10295924961_10295453961","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2022,2022,2,43,"2022-01-16T23:43:00","23:43","2022-10-30T02:23:00","02:23",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10295924961_10295456361","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2022,2022,1,49,"2022-01-03T14:17:00","14:17","2022-12-09T15:28:00","15:28",3620,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295924961_10295460561","Longuyon-Nancy-Sarrebourg","<","Conflans","Pagny",2022,2022,3,44,"2022-01-17T00:50:00","00:50","2022-10-31T03:25:00","03:25",67,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10295929661_10295697561","Lerouville-Nancy",">","Frouard","Jarville",2022,2022,6,40,"2022-02-07T23:11:00","23:11","2022-10-05T05:07:00","05:07",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10295929661_10295696761","Lerouville-Nancy",">","Frouard","Jarville",2022,2022,6,40,"2022-02-07T23:13:00","23:13","2022-10-05T05:20:00","05:20",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10295928061_10295557961","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2022,2022,1,49,"2022-01-03T11:52:00","11:52","2022-12-09T12:15:00","12:15",2866,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295928061_10295557161","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2022,2022,9,48,"2022-02-28T10:00:00","10:00","2022-12-02T15:30:00","15:30",935,"DAY",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","10295928061_10295558761","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2022,2022,2,43,"2022-01-16T23:00:00","23:00","2022-10-30T02:30:00","02:30",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10295928061_10295555561","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2022,2022,9,48,"2022-02-28T09:40:00","09:40","2022-12-02T16:10:00","16:10",976,"DAY",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","10295928061_10295554761","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2022,2022,1,49,"2022-01-03T13:35:00","13:35","2022-12-09T15:05:00","15:05",3531,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295928061_10295556361","Longuyon-Nancy-Sarrebourg","<","Longuyon","Conflans",2022,2022,3,44,"2022-01-17T02:08:00","02:08","2022-10-31T04:31:00","04:31",88,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10295927261_10295485561","Lerouville-Metz",">","Noveant","Metz",2021,2022,50,41,"2021-12-13","00:00","2022-10-10T03:00:00","03:00",60,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10295927261_10295484761","Lerouville-Metz",">","Noveant","Metz",2022,2022,7,41,"2022-02-14T09:20:00","09:20","2022-10-14T10:15:00","10:15",1097,"DAY",null,null,null,null,null,null,null,null,null,null,null,"108 jours dans le régime binaire"]
["SNCF Réseau","10295927261_10295486361","Lerouville-Metz",">","Noveant","Metz",2022,2022,1,49,"2022-01-03","00:00","2022-12-05T03:00:00","03:00",81,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","10295927261_10295483961","Lerouville-Metz",">","Noveant","Metz",2022,2022,1,49,"2022-01-03","00:00","2022-12-05T03:00:00","03:00",81,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","10295927261_10295490561","Lerouville-Metz",">","Noveant","Metz",2022,2022,10,47,"2022-03-07T23:00:00","23:00","2022-11-25T05:45:00","05:45",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","10295927261_10295487161","Lerouville-Metz",">","Noveant","Metz",2021,2022,50,41,"2021-12-13","00:00","2022-10-10T03:00:00","03:00",60,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10295927261_10295491561","Lerouville-Metz",">","Noveant","Metz",2022,2022,7,41,"2022-02-14T14:09:00","14:09","2022-10-14T15:17:00","15:17",1636,"DAY",null,null,null,null,null,null,null,null,null,null,null,"108 jours dans le régime binaire"]
["SNCF Réseau","10295927261_10295488761","Lerouville-Metz",">","Noveant","Metz",2022,2022,16,43,"2022-04-19T23:00:00","23:00","2022-10-28T05:45:00","05:45",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10295927261_10295489761","Lerouville-Metz",">","Noveant","Metz",2022,2022,1,49,"2022-01-03T10:48:00","10:48","2022-12-09T11:55:00","11:55",1502,"DAY",null,null,null,null,null,null,null,null,null,null,null,"127 jours dans le régime binaire"]
["SNCF Réseau","10295927261_10295487961","Lerouville-Metz",">","Noveant","Metz",2022,2022,1,49,"2022-01-03T14:11:00","14:11","2022-12-09T15:05:00","15:05",1901,"DAY",null,null,null,null,null,null,null,null,null,null,null,"127 jours dans le régime binaire"]
["SNCF Réseau","10295927961_10295589361","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2022,2022,6,40,"2022-02-07T23:14:00","23:14","2022-10-05T05:14:00","05:14",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","10295927961_10295590361","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2022,2022,1,49,"2022-01-03T09:46:00","09:46","2022-12-09T10:44:00","10:44",2512,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295927961_10295591161","Longuyon-Nancy-Sarrebourg",">","Rosieres","Blainville",2022,2022,1,49,"2022-01-03T14:26:00","14:26","2022-12-09T15:23:00","15:23",3600,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295928161_10295719161","Dijon-Toul",">","NeufChateau","Toul",2022,2022,14,15,"2022-04-04T09:17:00","09:17","2022-04-15T13:15:00","13:15",123,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","10295928161_10295715961","Dijon-Toul",">","NeufChateau","Toul",2022,2022,1,49,"2022-01-03T14:15:00","14:15","2022-12-09T15:44:00","15:44",3683,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295928161_10295718361","Dijon-Toul",">","NeufChateau","Toul",2022,2022,14,15,"2022-04-04T14:15:00","14:15","2022-04-15T19:41:00","19:41",182,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","10295928161_10295716761","Dijon-Toul",">","NeufChateau","Toul",2022,2022,1,49,"2022-01-03T01:46:00","01:46","2022-12-05T05:12:00","05:12",227,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10295928161_10295717561","Dijon-Toul",">","NeufChateau","Toul",2022,2022,1,49,"2022-01-03T10:08:00","10:08","2022-12-09T10:34:00","10:34",2473,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295928161_10295715161","Dijon-Toul",">","NeufChateau","Toul",2022,2022,52,48,"2022-01-02T23:52:00","23:52","2022-12-04T01:34:00","01:34",23,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295569561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2022,50,49,"2021-12-14T09:15:00","09:15","2022-12-09T10:11:00","10:11",846,"DAY",null,null,null,null,null,null,null,null,null,null,null,"84 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295562361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295563961","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2022,50,49,"2021-12-13T14:20:00","14:20","2022-12-09T15:15:00","15:15",2578,"DAY",null,null,null,null,null,null,null,null,null,null,null,"170 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295565561","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,8,48,"2022-02-22T11:30:00","11:30","2022-12-02T15:30:00","15:30",810,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295568761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2022,50,49,"2021-12-13T11:30:00","11:30","2022-12-09T12:34:00","12:34",2124,"DAY",null,null,null,null,null,null,null,null,null,null,null,"170 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295570361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,8,48,"2022-02-22T11:30:00","11:30","2022-12-02T15:30:00","15:30",810,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295567961","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2021,2022,50,49,"2021-12-13T13:45:00","13:45","2022-12-09T14:49:00","14:49",2712,"DAY",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295563161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295571161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295567161","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",223,"DAY",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295564761","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",223,"DAY",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10295927361_10295566361","Longuyon-Metz-Sarrebourg","<","Hagondange","Uckange",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295928361_10295582361","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2022,2022,3,49,"2022-01-17T23:40:00","23:40","2022-12-09T05:10:00","05:10",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"112 jours dans le régime binaire"]
["SNCF Réseau","10295928361_10295583961","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2022,2022,3,49,"2022-01-17T22:55:00","22:55","2022-12-09T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"105 jours dans le régime binaire"]
["SNCF Réseau","10295928361_10295583161","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2021,2022,50,49,"2021-12-13T14:05:00","14:05","2022-12-09T15:55:00","15:55",3949,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10295928361_10295581561","Longuyon-Metz-Sarrebourg","<","Reding","Remilly",2021,2022,50,49,"2021-12-13T11:42:00","11:42","2022-12-09T12:07:00","12:07",3005,"DAY",null,null,null,null,null,null,null,null,null,null,null,"249 jours dans le régime binaire"]
["SNCF Réseau","10295929761_10295690961","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2022,2022,8,40,"2022-02-21T23:26:00","23:26","2022-10-07T05:26:00","05:26",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"40 jours dans le régime binaire"]
["SNCF Réseau","10295929761_10295692761","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2022,2022,4,48,"2022-01-30T23:56:00","23:56","2022-12-04T02:56:00","02:56",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","10295929761_10295691961","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2022,2022,1,49,"2022-01-03T09:25:00","09:25","2022-12-09T10:22:00","10:22",2426,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295929761_10295694361","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2022,2022,1,49,"2022-01-03T13:35:00","13:35","2022-12-09T14:38:00","14:38",3425,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295929761_10295693561","Longuyon-Metz-Sarrebourg","<","MetzAM","Woippy",2022,2022,4,48,"2022-01-30T23:56:00","23:56","2022-12-04T02:56:00","02:56",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","10295929261_10295524961","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2021,2022,52,49,"2021-12-27T09:36:00","09:36","2022-12-09T10:37:00","10:37",2538,"DAY",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","10295929261_10295525761","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2022,2022,5,49,"2022-01-31","00:00","2022-12-05T03:20:00","03:20",76,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","10295929261_10295526561","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2022,2022,4,48,"2022-01-30T23:04:00","23:04","2022-12-04T01:55:00","01:55",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","10295929261_10295524161","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2021,2022,52,49,"2021-12-27T14:36:00","14:36","2022-12-09T15:26:00","15:26",3689,"DAY",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","10295929261_10295527361","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2022,2022,6,40,"2022-02-07T23:05:00","23:05","2022-10-05T04:55:00","04:55",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"59 jours dans le régime binaire"]
["SNCF Réseau","10295929261_10295523361","Longuyon-Nancy-Sarrebourg",">","Jarville","Rosieres",2022,2022,6,40,"2022-02-07T23:15:00","23:15","2022-10-05T05:25:00","05:25",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"59 jours dans le régime binaire"]
["SNCF Réseau","10295927161_10295611961","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2022,2022,4,48,"2022-01-30T22:40:00","22:40","2022-12-04T04:30:00","04:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","10295927161_10295607961","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2022,2022,6,42,"2022-02-07T23:09:00","23:09","2022-10-21T04:35:00","04:35",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"59 jours dans le régime binaire"]
["SNCF Réseau","10295927161_10295609561","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2021,2022,52,49,"2021-12-27T09:33:00","09:33","2022-12-09T10:47:00","10:47",2578,"DAY",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","10295927161_10295613561","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2022,2022,6,42,"2022-02-07T23:46:00","23:46","2022-10-21T06:20:00","06:20",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"59 jours dans le régime binaire"]
["SNCF Réseau","10295927161_10295612761","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2022,2022,5,49,"2022-01-31T00:20:00","00:20","2022-12-05T03:50:00","03:50",87,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"23 jours dans le régime binaire"]
["SNCF Réseau","10295927161_10295608761","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2021,2022,50,49,"2021-12-13T09:47:00","09:47","2022-12-09T11:00:00","11:00",2740,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10295927161_10295610361","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2021,2022,52,49,"2021-12-27T14:23:00","14:23","2022-12-09T15:10:00","15:10",3625,"DAY",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","10295927161_10295611161","Longuyon-Nancy-Sarrebourg",">","Luneville","Reding",2021,2022,50,49,"2021-12-13T14:10:00","14:10","2022-12-09T15:00:00","15:00",3735,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10295929061_10295500161","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2021,2022,50,49,"2021-12-13T14:11:00","14:11","2022-12-09T15:10:00","15:10",2564,"DAY",null,null,null,null,null,null,null,null,null,null,null,"170 jours dans le régime binaire"]
["SNCF Réseau","10295929061_10295500961","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2021,2022,50,49,"2021-12-14T09:17:00","09:17","2022-12-09T10:14:00","10:14",850,"DAY",null,null,null,null,null,null,null,null,null,null,null,"84 jours dans le régime binaire"]
["SNCF Réseau","10295929061_10295501761","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2021,2022,50,49,"2021-12-13T11:28:00","11:28","2022-12-09T12:29:00","12:29",2110,"DAY",null,null,null,null,null,null,null,null,null,null,null,"170 jours dans le régime binaire"]
["SNCF Réseau","10295929061_10295499361","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295929061_10295503361","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",207,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","10295929061_10295502561","Longuyon-Metz-Sarrebourg","<","Hagondange",null,2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295925161_10295705161","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2022,2022,5,49,"2022-01-31T00:03:00","00:03","2022-12-05T03:00:00","03:00",50,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","10295925161_10295703561","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2022,2022,5,49,"2022-01-31T00:24:00","00:24","2022-12-05T03:30:00","03:30",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","10295925161_10295702161","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2022,2022,29,38,"2022-07-18T23:45:00","23:45","2022-09-23T05:45:00","05:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","10295925161_10295705961","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2021,2022,52,49,"2021-12-27T10:45:00","10:45","2022-12-09T11:47:00","11:47",2793,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","10295925161_10295704361","Longuyon-Nancy-Sarrebourg",">","Pagny","Noveant",2021,2022,52,49,"2021-12-27T14:16:00","14:16","2022-12-09T15:11:00","15:11",3599,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295776761","Longuyon-Metz-Sarrebourg","<","Uckange",null,2022,2022,3,43,"2022-01-17","00:00","2022-10-24T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295772761","Longuyon-Metz-Sarrebourg","<","Uckange",null,2022,2022,5,46,"2022-01-31T09:30:00","09:30","2022-11-14T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295773561","Longuyon-Metz-Sarrebourg","<","Uckange",null,2022,2022,7,40,"2022-02-14T09:30:00","09:30","2022-10-03T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295775961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2022,50,49,"2021-12-13T09:10:00","09:10","2022-12-09T10:08:00","10:08",1865,"DAY",null,null,null,null,null,null,null,null,null,null,null,"185 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295771961","Longuyon-Metz-Sarrebourg","<","Uckange",null,2022,2022,7,40,"2022-02-14T09:30:00","09:30","2022-10-03T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295771161","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2022,50,49,"2021-12-13","00:00","2022-12-05T03:00:00","03:00",81,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295774361","Longuyon-Metz-Sarrebourg","<","Uckange",null,2022,2022,5,46,"2022-01-31T09:30:00","09:30","2022-11-14T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295775161","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2022,50,49,"2021-12-13T13:50:00","13:50","2022-12-09T14:52:00","14:52",3256,"DAY",null,null,null,null,null,null,null,null,null,null,null,"220 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295769561","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2022,50,49,"2021-12-13T11:35:00","11:35","2022-12-09T12:38:00","12:38",2691,"DAY",null,null,null,null,null,null,null,null,null,null,null,"214 jours dans le régime binaire"]
["SNCF Réseau","10295930861_10295770361","Longuyon-Metz-Sarrebourg","<","Uckange",null,2021,2022,50,49,"2021-12-13","00:00","2022-12-05T03:00:00","03:00",81,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","10295928561_10295667761","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2022,2022,13,37,"2022-03-28T10:30:00","10:30","2022-09-16T16:30:00","16:30",864,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295928561_10295666161","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2022,2022,1,49,"2022-01-03T13:20:00","13:20","2022-12-09T13:40:00","13:40",3198,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295928561_10295665361","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2021,2022,50,48,"2021-12-19T23:00:00","23:00","2022-12-04T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","10295928561_10295666961","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2022,2022,1,49,"2022-01-03T11:30:00","11:30","2022-12-09T13:15:00","13:15",3102,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295928561_10295668761","Longuyon-Metz-Sarrebourg",">","Longuyon","Thionville",2021,2022,50,48,"2021-12-19T23:00:00","23:00","2022-12-04T02:00:00","02:00",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"27 jours dans le régime binaire"]
["SNCF Réseau","10295930461_10295619361","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2022,2022,10,43,"2022-03-07T23:00:00","23:00","2022-10-28T05:40:00","05:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"58 jours dans le régime binaire"]
["SNCF Réseau","10295930461_10295622761","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2021,2022,50,41,"2021-12-19T22:45:00","22:45","2022-10-16T02:01:00","02:01",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10295930461_10295621161","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2021,2022,52,49,"2021-12-27T10:51:00","10:51","2022-12-09T11:41:00","11:41",2769,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","10295930461_10295621961","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2021,2022,52,49,"2021-12-27T14:07:00","14:07","2022-12-09T15:17:00","15:17",3623,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","10295930461_10295620361","Longuyon-Metz-Sarrebourg","<","Remilly","Metz",2021,2022,51,42,"2021-12-20T00:15:00","00:15","2022-10-17T03:00:00","03:00",59,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10295930161_10295595161","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2022,2022,29,38,"2022-07-18T23:35:00","23:35","2022-09-23T05:35:00","05:35",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"43 jours dans le régime binaire"]
["SNCF Réseau","10295930161_10295597761","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2021,2022,52,49,"2021-12-27T10:26:00","10:26","2022-12-09T11:42:00","11:42",2774,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","10295930161_10295596961","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2021,2022,52,49,"2021-12-27T14:32:00","14:32","2022-12-09T15:16:00","15:16",3618,"DAY",null,null,null,null,null,null,null,null,null,null,null,"238 jours dans le régime binaire"]
["SNCF Réseau","10295930161_10295594361","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2022,2022,5,49,"2022-01-31","00:00","2022-12-05T03:24:00","03:24",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","10295930161_10295596161","Longuyon-Nancy-Sarrebourg",">","Frouard","Pagny",2022,2022,5,49,"2022-01-31T00:25:00","00:25","2022-12-05T03:03:00","03:03",51,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","10295927061_10295757561","Dijon-Toul",">","Culmont","NeufChateau",2022,2022,1,49,"2022-01-03T10:55:00","10:55","2022-12-09T11:37:00","11:37",2719,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295927061_10295763161","Dijon-Toul",">","Culmont","NeufChateau",2021,2022,50,49,"2021-12-13T01:03:00","01:03","2022-12-05T04:25:00","04:25",206,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10295927061_10295762361","Dijon-Toul",">","Culmont","NeufChateau",2021,2022,50,49,"2021-12-13T01:25:00","01:25","2022-12-05T04:51:00","04:51",226,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10295927061_10295759161","Dijon-Toul",">","Culmont","NeufChateau",2022,2022,1,49,"2022-01-03T10:37:00","10:37","2022-12-09T11:08:00","11:08",2605,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295927061_10295759961","Dijon-Toul",">","Culmont","NeufChateau",2022,2022,1,49,"2022-01-03T13:48:00","13:48","2022-12-09T15:15:00","15:15",3569,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295927061_10295758361","Dijon-Toul",">","Culmont","NeufChateau",2021,2022,50,48,"2021-12-19T00:05:00","00:05","2022-12-04T02:37:00","02:37",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10295927061_10295760761","Dijon-Toul",">","Culmont","NeufChateau",2022,2022,14,15,"2022-04-04T10:05:00","10:05","2022-04-15T13:48:00","13:48",127,"DAY",null,null,null,null,null,null,null,null,null,null,null,"10 jours dans le régime binaire"]
["SNCF Réseau","10295927061_10295763961","Dijon-Toul",">","Culmont","NeufChateau",2021,2022,50,49,"2021-12-13T00:27:00","00:27","2022-12-05T03:05:00","03:05",144,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10295927061_10295764761","Dijon-Toul",">","Culmont","NeufChateau",2022,2022,14,15,"2022-04-04T13:26:00","13:26","2022-04-14T19:14:00","19:14",140,"DAY",null,null,null,null,null,null,null,null,null,null,null,"8 jours dans le régime binaire"]
["SNCF Réseau","10295927061_11729704861","Dijon-Toul",">","Culmont","NeufChateau",2022,2022,14,15,"2022-04-08T13:26:00","13:26","2022-04-15T19:00:00","19:00",24,"DAY",null,null,null,null,null,null,null,null,null,null,null,"2 jours dans le régime binaire"]
["SNCF Réseau","10295927061_10295761561","Dijon-Toul",">","Culmont","NeufChateau",2022,2022,1,49,"2022-01-03T13:25:00","13:25","2022-12-09T14:48:00","14:48",3464,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295925761_10295790361","Lerouville-Nancy",">","Lerouville","Toul",2022,2022,1,49,"2022-01-03T15:15:00","15:15","2022-12-09T16:00:00","16:00",3744,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295925761_10295788761","Lerouville-Nancy",">","Lerouville","Toul",2022,2022,10,38,"2022-03-07T00:40:00","00:40","2022-09-19T03:20:00","03:20",49,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10295925761_10295789561","Lerouville-Nancy",">","Lerouville","Toul",2022,2022,9,37,"2022-03-06T22:40:00","22:40","2022-09-18T02:01:00","02:01",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10295925761_10295787961","Lerouville-Nancy",">","Lerouville","Toul",2022,2022,1,49,"2022-01-03T10:40:00","10:40","2022-12-09T11:56:00","11:56",2793,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295925761_10295791161","Lerouville-Nancy",">","Lerouville","Toul",2022,2022,9,46,"2022-02-28T23:00:00","23:00","2022-11-18T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"47 jours dans le régime binaire"]
["SNCF Réseau","10295925061_10295577961","Lerouville-Nancy",">","Toul","Frouard",2022,2022,4,48,"2022-01-30T22:54:00","22:54","2022-12-04T01:40:00","01:40",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","10295925061_10295577161","Lerouville-Nancy",">","Toul","Frouard",2022,2022,4,48,"2022-01-30T22:55:00","22:55","2022-12-04T02:06:00","02:06",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","10295925061_10295579561","Lerouville-Nancy",">","Toul","Frouard",2022,2022,12,43,"2022-03-21T23:00:00","23:00","2022-10-28T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","10295925061_10295576361","Lerouville-Nancy",">","Toul","Frouard",2021,2022,52,49,"2021-12-27T08:58:00","08:58","2022-12-09T10:16:00","10:16",2455,"DAY",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","10295925061_10295578761","Lerouville-Nancy",">","Toul","Frouard",2021,2022,52,49,"2021-12-27T14:59:00","14:59","2022-12-09T15:42:00","15:42",3753,"DAY",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","10295926461_10295725361","Lerouville-Metz",">","Lerouville","Noveant",2022,2022,1,49,"2022-01-03T14:02:00","14:02","2022-12-09T15:08:00","15:08",3542,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295926461_10295726961","Lerouville-Metz",">","Lerouville","Noveant",2022,2022,1,49,"2022-01-03T10:16:00","10:16","2022-12-09T11:05:00","11:05",2594,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295926461_10295724561","Lerouville-Metz",">","Lerouville","Noveant",2021,2022,50,41,"2021-12-19T23:27:00","23:27","2022-10-16T02:59:00","02:59",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","10295926461_10295723761","Lerouville-Metz",">","Lerouville","Noveant",2022,2022,1,49,"2022-01-03T10:42:00","10:42","2022-12-09T11:16:00","11:16",2636,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295926461_10295721961","Lerouville-Metz",">","Lerouville","Noveant",2022,2022,1,49,"2022-01-03T13:35:00","13:35","2022-12-09T15:02:00","15:02",3519,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295926461_10295726161","Lerouville-Metz",">","Lerouville","Noveant",2021,2022,50,41,"2021-12-19T22:38:00","22:38","2022-10-16T01:02:00","01:02",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"16 jours dans le régime binaire"]
["SNCF Réseau","10295926461_10295722761","Lerouville-Metz",">","Lerouville","Noveant",2022,2022,16,42,"2022-04-19T23:00:00","23:00","2022-10-21T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"44 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295512961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2022,50,49,"2021-12-14T09:19:00","09:19","2022-12-09T10:17:00","10:17",854,"DAY",null,null,null,null,null,null,null,null,null,null,null,"84 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295509761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295515361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2022,50,49,"2021-12-13T14:25:00","14:25","2022-12-09T15:21:00","15:21",2595,"DAY",null,null,null,null,null,null,null,null,null,null,null,"170 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295516161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,8,48,"2022-02-22T11:30:00","11:30","2022-12-02T15:30:00","15:30",810,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295514561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2022,50,49,"2021-12-13T11:27:00","11:27","2022-12-09T12:28:00","12:28",2107,"DAY",null,null,null,null,null,null,null,null,null,null,null,"170 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295516961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",207,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295513761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2021,2022,50,49,"2021-12-13T13:41:00","13:41","2022-12-09T14:44:00","14:44",2697,"DAY",null,null,null,null,null,null,null,null,null,null,null,"184 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295512161","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,9,47,"2022-03-01T11:30:00","11:30","2022-11-25T15:30:00","15:30",980,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295508961","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,8,48,"2022-02-22T11:30:00","11:30","2022-12-02T15:30:00","15:30",810,"DAY",null,null,null,null,null,null,null,null,null,null,null,"53 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295510561","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295511361","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,9,47,"2022-02-28T09:30:00","09:30","2022-11-21T15:30:00","15:30",207,"DAY",null,null,null,null,null,null,null,null,null,null,null,"14 jours dans le régime binaire"]
["SNCF Réseau","10295929361_10295517761","Longuyon-Metz-Sarrebourg","<","Maizières","Hagondange",2022,2022,8,48,"2022-02-21T09:30:00","09:30","2022-11-28T15:30:00","15:30",176,"DAY",null,null,null,null,null,null,null,null,null,null,null,"12 jours dans le régime binaire"]
["SNCF Réseau","10295928961_10295780961","Dijon-Toul",">","IsSurTille","Culmont",2021,2022,50,49,"2021-12-13T00:29:00","00:29","2022-12-05T04:03:00","04:03",197,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","10295928961_10295784161","Dijon-Toul",">","IsSurTille","Culmont",2021,2022,50,49,"2021-12-13T00:54:00","00:54","2022-12-05T03:29:00","03:29",169,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","10295928961_10295783361","Dijon-Toul",">","IsSurTille","Culmont",2021,2022,50,49,"2021-12-13T11:08:00","11:08","2022-12-09T11:38:00","11:38",2897,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10295928961_10295784961","Dijon-Toul",">","IsSurTille","Culmont",2022,2022,9,46,"2022-02-28T10:58:00","10:58","2022-11-18T14:28:00","14:28",1479,"DAY",null,null,null,null,null,null,null,null,null,null,null,"103 jours dans le régime binaire"]
["SNCF Réseau","10295928961_10295781761","Dijon-Toul",">","IsSurTille","Culmont",2022,2022,9,46,"2022-02-28T12:40:00","12:40","2022-11-18T17:08:00","17:08",1752,"DAY",null,null,null,null,null,null,null,null,null,null,null,"103 jours dans le régime binaire"]
["SNCF Réseau","10295928961_10295782561","Dijon-Toul",">","IsSurTille","Culmont",2021,2022,50,49,"2021-12-13T13:01:00","13:01","2022-12-09T14:22:00","14:22",3578,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10295926361_10295476161","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2022,2022,1,49,"2022-01-03T14:05:00","14:05","2022-12-09T15:25:00","15:25",3608,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295926361_10295475361","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2022,2022,1,49,"2022-01-03T11:30:00","11:30","2022-12-09T12:10:00","12:10",2847,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295926361_10295474361","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2022,2022,2,47,"2022-01-10T10:15:00","10:15","2022-11-25T16:00:00","16:00",1013,"DAY",null,null,null,null,null,null,null,null,null,null,null,"64 jours dans le régime binaire"]
["SNCF Réseau","10295926361_10295473561","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2021,2022,50,49,"2021-12-13T00:50:00","00:50","2022-12-05T03:30:00","03:30",167,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","10295926361_10295476961","Longuyon-Metz-Sarrebourg",">","Longuyon","MontStMartin",2021,2022,50,49,"2021-12-13T00:30:00","00:30","2022-12-05T03:50:00","03:50",183,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","10295929461_10295478161","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2022,2022,10,49,"2022-03-07T23:43:00","23:43","2022-12-09T05:29:00","05:29",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"183 jours dans le régime binaire"]
["SNCF Réseau","10295929461_10295478961","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2022,2022,1,49,"2022-01-03T09:03:00","09:03","2022-12-09T09:55:00","09:55",2311,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","10295929461_10295479761","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2022,2022,10,49,"2022-03-07T23:27:00","23:27","2022-12-09T05:27:00","05:27",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"183 jours dans le régime binaire"]
["SNCF Réseau","10295929461_10295480561","Longuyon-Metz-Sarrebourg","<","Thionville","Zoufftgen",2022,2022,1,49,"2022-01-03T14:00:00","14:00","2022-12-09T15:07:00","15:07",3523,"DAY",null,null,null,null,null,null,null,null,null,null,null,"234 jours dans le régime binaire"]
["SNCF Réseau","10295926061_10295531961","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2022,2022,1,49,"2022-01-03T12:17:00","12:17","2022-12-09T12:49:00","12:49",2999,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295926061_10295531161","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2022,2022,3,49,"2022-01-17T00:30:00","00:30","2022-12-05T03:30:00","03:30",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10295926061_10295530361","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2022,2022,3,49,"2022-01-17","00:00","2022-12-05T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10295926061_10295529561","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2022,2022,1,49,"2022-01-03T14:05:00","14:05","2022-12-09T15:32:00","15:32",3636,"DAY",null,null,null,null,null,null,null,null,null,null,null,"235 jours dans le régime binaire"]
["SNCF Réseau","10295926061_10295532761","Longuyon-Nancy-Sarrebourg",">","Conflans","Hagondange",2022,2022,9,48,"2022-02-28T10:10:00","10:10","2022-12-02T16:10:00","16:10",976,"DAY",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","10295929561_10295786561","Longuyon-Metz-Sarrebourg","<","Metz sablon via MetzVille",null,2022,2022,13,47,"2022-03-28T23:30:00","23:30","2022-11-25T05:30:00","05:30",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"49 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295747761","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2022,50,49,"2021-12-13T09:09:00","09:09","2022-12-09T10:07:00","10:07",1862,"DAY",null,null,null,null,null,null,null,null,null,null,null,"185 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295745361","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2022,2022,5,46,"2022-02-01T11:30:00","11:30","2022-11-18T15:30:00","15:30",422,"DAY",null,null,null,null,null,null,null,null,null,null,null,"28 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295742961","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2022,50,49,"2021-12-13T11:37:00","11:37","2022-12-09T12:44:00","12:44",2713,"DAY",null,null,null,null,null,null,null,null,null,null,null,"214 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295752561","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2022,2022,7,40,"2022-02-15T11:30:00","11:30","2022-10-07T15:30:00","15:30",298,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295750961","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2022,2022,3,43,"2022-01-17","00:00","2022-10-24T03:00:00","03:00",57,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"19 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295751761","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2022,2022,7,40,"2022-02-15T11:30:00","11:30","2022-10-07T15:30:00","15:30",298,"DAY",null,null,null,null,null,null,null,null,null,null,null,"20 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295750161","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2022,50,49,"2021-12-13T13:51:00","13:51","2022-12-09T14:53:00","14:53",3260,"DAY",null,null,null,null,null,null,null,null,null,null,null,"220 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295744561","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2022,2022,5,46,"2022-02-01T11:30:00","11:30","2022-11-18T15:30:00","15:30",422,"DAY",null,null,null,null,null,null,null,null,null,null,null,"28 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295748561","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2022,2022,7,40,"2022-02-14T09:30:00","09:30","2022-10-03T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295746961","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2021,2022,50,49,"2021-12-13T14:15:00","14:15","2022-12-09T15:05:00","15:05",3213,"DAY",null,null,null,null,null,null,null,null,null,null,null,"214 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295743761","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2022,2022,5,46,"2022-01-31T09:30:00","09:30","2022-11-14T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295746161","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2022,2022,5,46,"2022-01-31T09:30:00","09:30","2022-11-14T15:30:00","15:30",99,"DAY",null,null,null,null,null,null,null,null,null,null,null,"7 jours dans le régime binaire"]
["SNCF Réseau","10295928761_10295749361","Longuyon-Metz-Sarrebourg","<","Uckange","Thionville",2022,2022,7,40,"2022-02-14T09:30:00","09:30","2022-10-03T15:30:00","15:30",83,"DAY",null,null,null,null,null,null,null,null,null,null,null,"6 jours dans le régime binaire"]
["SNCF Réseau","10295926261_10295660561","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2022,2022,6,40,"2022-02-07T23:10:00","23:10","2022-10-05T05:05:00","05:05",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","10295926261_10295661361","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2021,2022,52,49,"2021-12-27T09:44:00","09:44","2022-12-09T10:50:00","10:50",2590,"DAY",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","10295926261_10295658961","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2022,2022,6,40,"2022-02-07T23:41:00","23:41","2022-10-05T05:46:00","05:46",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"50 jours dans le régime binaire"]
["SNCF Réseau","10295926261_10295659761","Longuyon-Nancy-Sarrebourg",">","Blainville","Luneville",2021,2022,52,49,"2021-12-27T14:28:00","14:28","2022-12-09T15:23:00","15:23",3677,"DAY",null,null,null,null,null,null,null,null,null,null,null,"240 jours dans le régime binaire"]
["SNCF Réseau","10292743561_10292524061","Dijon-Lyon",">","Chagny","Chalon sur Saone",2022,2022,1,49,"2022-01-03T23:00:00","23:00","2022-12-09T05:11:00","05:11",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"151 jours dans le régime binaire"]
["SNCF Réseau","10292743561_10292520061","Dijon-Lyon",">","Chagny","Chalon sur Saone",2022,2022,1,49,"2022-01-03T00:07:00","00:07","2022-12-09T05:55:00","05:55",-5,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"159 jours dans le régime binaire"]
["SNCF Réseau","10292743561_10292522461","Dijon-Lyon",">","Chagny","Chalon sur Saone",2021,2022,50,49,"2021-12-13T11:46:00","11:46","2022-12-09T12:35:00","12:35",3134,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10292743561_10292520861","Dijon-Lyon",">","Chagny","Chalon sur Saone",2021,2022,50,49,"2021-12-13T13:13:00","13:13","2022-12-09T14:26:00","14:26",3595,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10292743561_10292523261","Dijon-Lyon",">","Chagny","Chalon sur Saone",2021,2022,50,48,"2021-12-13T01:00:00","01:00","2022-11-28T04:05:00","04:05",133,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","10292743561_10292521661","Dijon-Lyon",">","Chagny","Chalon sur Saone",2021,2022,50,48,"2021-12-13T00:10:00","00:10","2022-11-28T03:05:00","03:05",101,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","10292743961_10292586061","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2022,2022,4,48,"2022-01-24T10:22:00","10:22","2022-12-02T16:22:00","16:22",1233,"DAY",null,null,null,null,null,null,null,null,null,null,null,"76 jours dans le régime binaire"]
["SNCF Réseau","10292743961_10292585261","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2021,2022,50,49,"2021-12-13T13:30:00","13:30","2022-12-09T13:48:00","13:48",2732,"DAY",null,null,null,null,null,null,null,null,null,null,null,"199 jours dans le régime binaire"]
["SNCF Réseau","10292743961_10292584461","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2022,2022,35,39,"2022-08-29T08:40:00","08:40","2022-09-30T13:15:00","13:15",322,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","10292743961_10292587861","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2021,2022,50,49,"2021-12-13T11:27:00","11:27","2022-12-09T13:05:00","13:05",2592,"DAY",null,null,null,null,null,null,null,null,null,null,null,"199 jours dans le régime binaire"]
["SNCF Réseau","10292743961_10292588661","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2022,2022,1,44,"2022-01-09T22:10:00","22:10","2022-11-06T01:30:00","01:30",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","10292743961_10292583661","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2022,2022,1,49,"2022-01-03T02:56:00","02:56","2022-12-05T05:30:00","05:30",79,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10292743961_10292587061","Dijon-Amberieu-Lyon",">","Dijon","Seurre",2022,2022,35,39,"2022-08-29T13:08:00","13:08","2022-09-30T16:28:00","16:28",398,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","10292743161_10292607861","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2021,2022,50,48,"2021-12-19T22:18:00","22:18","2022-12-01T04:40:00","04:40",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"63 jours dans le régime binaire"]
["SNCF Réseau","10292743161_10292604661","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2021,2022,50,48,"2021-12-19T23:30:00","23:30","2022-12-01T05:00:00","05:00",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"63 jours dans le régime binaire"]
["SNCF Réseau","10292743161_10292605461","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2021,2022,50,49,"2021-12-13T11:44:00","11:44","2022-12-09T12:08:00","12:08",3058,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292743161_10292607061","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2021,2022,50,49,"2021-12-13T10:42:00","10:42","2022-12-09T12:01:00","12:01",2897,"DAY",null,null,null,null,null,null,null,null,null,null,null,"242 jours dans le régime binaire"]
["SNCF Réseau","10292743161_10292603861","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2022,2022,1,49,"2022-01-03T00:24:00","00:24","2022-12-05T03:47:00","03:47",56,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10292743161_10292606261","Dijon-Amberieu-Lyon",">","Lyon","Amberieu",2022,2022,1,49,"2022-01-03T03:06:00","03:06","2022-12-05T05:32:00","05:32",79,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10292742161_10292627461","Dijon-Lyon",">","Dijon","Chagny",2021,2022,50,44,"2021-12-13T22:29:00","22:29","2022-11-04T04:55:00","04:55",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"113 jours dans le régime binaire"]
["SNCF Réseau","10292742161_10292626661","Dijon-Lyon",">","Dijon","Chagny",2021,2022,50,49,"2021-12-13T12:42:00","12:42","2022-12-09T14:13:00","14:13",3541,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10292742161_10292629061","Dijon-Lyon",">","Dijon","Chagny",2021,2022,50,48,"2021-12-13T00:25:00","00:25","2022-11-28T03:11:00","03:11",107,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","10292742161_10292628261","Dijon-Lyon",">","Dijon","Chagny",2021,2022,50,44,"2021-12-14T00:34:00","00:34","2022-11-04T05:57:00","05:57",671,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"113 jours dans le régime binaire"]
["SNCF Réseau","10292742161_10292630661","Dijon-Lyon",">","Dijon","Chagny",2021,2022,50,49,"2021-12-13T12:16:00","12:16","2022-12-09T12:44:00","12:44",3171,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10292742161_10292629861","Dijon-Lyon",">","Dijon","Chagny",2021,2022,50,48,"2021-12-13T00:45:00","00:45","2022-11-28T04:00:00","04:00",135,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"34 jours dans le régime binaire"]
["SNCF Réseau","10292742461_10292618861","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2021,2022,50,48,"2021-12-13T10:15:00","10:15","2022-12-02T16:15:00","16:15",1484,"DAY",null,null,null,null,null,null,null,null,null,null,null,"92 jours dans le régime binaire"]
["SNCF Réseau","10292742461_10292617861","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2021,2022,50,48,"2021-12-13T14:15:00","14:15","2022-12-02T16:15:00","16:15",1480,"DAY",null,null,null,null,null,null,null,null,null,null,null,"92 jours dans le régime binaire"]
["SNCF Réseau","10292742461_10292620661","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2021,2022,50,49,"2021-12-13T11:49:00","11:49","2022-12-09T12:29:00","12:29",2235,"DAY",null,null,null,null,null,null,null,null,null,null,null,"180 jours dans le régime binaire"]
["SNCF Réseau","10292742461_10292619861","Dijon-Amberieu-Lyon",">","BourgEnBresse","Amberieu",2021,2022,50,49,"2021-12-13T13:09:00","13:09","2022-12-09T14:22:00","14:22",2572,"DAY",null,null,null,null,null,null,null,null,null,null,null,"180 jours dans le régime binaire"]
["SNCF Réseau","10292743661_10292563461","Dijon-Lyon",">","Macon","Saint Germain",2021,2022,50,49,"2021-12-13T23:43:00","23:43","2022-12-09T06:18:00","06:18",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"175 jours dans le régime binaire"]
["SNCF Réseau","10292743661_10292564261","Dijon-Lyon",">","Macon","Saint Germain",2021,2022,50,49,"2021-12-13T23:25:00","23:25","2022-12-09T04:45:00","04:45",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"175 jours dans le régime binaire"]
["SNCF Réseau","10292743661_10292565861","Dijon-Lyon",">","Macon","Saint Germain",2021,2022,50,49,"2021-12-13T11:03:00","11:03","2022-12-09T11:33:00","11:33",2911,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292743661_10292565061","Dijon-Lyon",">","Macon","Saint Germain",2021,2022,50,49,"2021-12-13T13:57:00","13:57","2022-12-09T15:28:00","15:28",3899,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292743461_10292457461","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2022,50,49,"2021-12-13T13:25:00","13:25","2022-12-09T14:56:00","14:56",3719,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10292743461_10292459861","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2022,50,49,"2021-12-13T11:37:00","11:37","2022-12-09T12:06:00","12:06",3013,"DAY",null,null,null,null,null,null,null,null,null,null,null,"250 jours dans le régime binaire"]
["SNCF Réseau","10292743461_10292459061","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2022,50,48,"2021-12-19T00:03:00","00:03","2022-12-04T02:30:00","02:30",-2,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"35 jours dans le régime binaire"]
["SNCF Réseau","10292743461_10292456661","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2022,50,49,"2021-12-13T23:05:00","23:05","2022-12-09T05:57:00","05:57",18,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"164 jours dans le régime binaire"]
["SNCF Réseau","10292743461_10292460661","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2022,50,48,"2021-12-13T01:07:00","01:07","2022-11-28T04:40:00","04:40",152,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"33 jours dans le régime binaire"]
["SNCF Réseau","10292743461_10292458261","Dijon-Lyon",">","Chalon sur Saone","Macon",2021,2022,50,49,"2021-12-13T23:58:00","23:58","2022-12-09T05:18:00","05:18",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"168 jours dans le régime binaire"]
["SNCF Réseau","10292742061_10292572461","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2021,2022,50,49,"2021-12-13T14:31:00","14:31","2022-12-09T15:48:00","15:48",4093,"DAY",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","10292742061_10292569061","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2021,2022,50,49,"2021-12-13T15:05:00","15:05","2022-12-09T15:48:00","15:48",4092,"DAY",null,null,null,null,null,null,null,null,null,null,null,"260 jours dans le régime binaire"]
["SNCF Réseau","10292742061_10292571661","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2021,2022,50,49,"2021-12-13T00:25:00","00:25","2022-12-05T03:10:00","03:10",151,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","10292742061_10292569861","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2021,2022,50,49,"2021-12-13T00:05:00","00:05","2022-12-05T03:20:00","03:20",159,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"48 jours dans le régime binaire"]
["SNCF Réseau","10292742061_10292570661","Dijon-Amberieu-Lyon",">","Macon","Bourg en Bresse",2021,2022,50,49,"2021-12-13T23:40:00","23:40","2022-12-09T05:40:00","05:40",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"222 jours dans le régime binaire"]
["SNCF Réseau","10292742361_10292643061","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2021,2022,50,49,"2021-12-13T12:58:00","12:58","2022-12-09T13:10:00","13:10",2567,"DAY",null,null,null,null,null,null,null,null,null,null,null,"196 jours dans le régime binaire"]
["SNCF Réseau","10292742361_10292643861","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2022,2022,1,44,"2022-01-09T22:31:00","22:31","2022-11-06T02:02:00","02:02",21,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","10292742361_10292641461","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2022,2022,35,39,"2022-08-29T09:15:00","09:15","2022-09-30T13:45:00","13:45",334,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","10292742361_10292640461","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2022,2022,7,48,"2022-02-14T10:15:00","10:15","2022-12-02T16:15:00","16:15",981,"DAY",null,null,null,null,null,null,null,null,null,null,null,"61 jours dans le régime binaire"]
["SNCF Réseau","10292742361_10292639661","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2022,2022,1,49,"2022-01-03T02:30:00","02:30","2022-12-05T04:52:00","04:52",70,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10292742361_10292638861","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2022,2022,35,39,"2022-08-29T12:35:00","12:35","2022-09-30T16:15:00","16:15",393,"DAY",null,null,null,null,null,null,null,null,null,null,null,"25 jours dans le régime binaire"]
["SNCF Réseau","10292742361_10292642261","Dijon-Amberieu-Lyon",">","Seurre","StAmour",2021,2022,50,49,"2021-12-13T12:05:00","12:05","2022-12-09T13:48:00","13:48",2692,"DAY",null,null,null,null,null,null,null,null,null,null,null,"196 jours dans le régime binaire"]
["SNCF Réseau","10292741861_10292485261","Dijon-Lyon",">","StGermain","Collonges",2021,2022,50,48,"2021-12-13T22:58:00","22:58","2022-12-02T04:37:00","04:37",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"123 jours dans le régime binaire"]
["SNCF Réseau","10292741861_10292486061","Dijon-Lyon",">","StGermain","Collonges",2021,2022,50,49,"2021-12-13T14:28:00","14:28","2022-12-09T15:35:00","15:35",3928,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292741861_10292482861","Dijon-Lyon",">","StGermain","Collonges",2021,2022,50,49,"2021-12-13T14:28:00","14:28","2022-12-09T15:35:00","15:35",3928,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292741861_10292488461","Dijon-Lyon",">","StGermain","Collonges",2021,2022,50,48,"2021-12-13T22:58:00","22:58","2022-12-02T04:37:00","04:37",19,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"98 jours dans le régime binaire"]
["SNCF Réseau","10292741861_10292484461","Dijon-Lyon",">","StGermain","Collonges",2021,2022,50,49,"2021-12-13T10:30:00","10:30","2022-12-09T11:24:00","11:24",2873,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292741861_10292487661","Dijon-Lyon",">","StGermain","Collonges",2021,2022,50,49,"2021-12-13T10:30:00","10:30","2022-12-09T11:24:00","11:24",2873,"DAY",null,null,null,null,null,null,null,null,null,null,null,"253 jours dans le régime binaire"]
["SNCF Réseau","10292741861_10292486861","Dijon-Lyon",">","StGermain","Collonges",2021,2022,50,48,"2021-12-14T00:20:00","00:20","2022-12-03T06:24:00","06:24",582,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"91 jours dans le régime binaire"]
["SNCF Réseau","10292741861_10292483661","Dijon-Lyon",">","StGermain","Collonges",2021,2022,50,48,"2021-12-14T00:20:00","00:20","2022-12-03T06:24:00","06:24",774,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"121 jours dans le régime binaire"]
["SNCF Réseau","10292742961_10292536261","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2021,2022,50,49,"2021-12-13T12:49:00","12:49","2022-12-09T14:05:00","14:05",2832,"DAY",null,null,null,null,null,null,null,null,null,null,null,"202 jours dans le régime binaire"]
["SNCF Réseau","10292742961_10292533661","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2021,2022,50,49,"2021-12-13T12:00:00","12:00","2022-12-09T12:50:00","12:50",2580,"DAY",null,null,null,null,null,null,null,null,null,null,null,"202 jours dans le régime binaire"]
["SNCF Réseau","10292742961_10292532861","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2022,2022,1,49,"2022-01-03T01:52:00","01:52","2022-12-05T04:32:00","04:32",66,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"15 jours dans le régime binaire"]
["SNCF Réseau","10292742961_10292531861","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2021,2022,50,48,"2021-12-13T10:43:00","10:43","2022-12-02T16:43:00","16:43",1527,"DAY",null,null,null,null,null,null,null,null,null,null,null,"92 jours dans le régime binaire"]
["SNCF Réseau","10292742961_10292534461","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2022,2022,1,44,"2022-01-09T23:44:00","23:44","2022-11-06T02:29:00","02:29",22,"NIGHT",null,null,null,null,null,null,null,null,null,null,null,"17 jours dans le régime binaire"]
["SNCF Réseau","10292742961_10292535261","Dijon-Amberieu-Lyon",">","StAmour","Bourg en Bresse",2021,2022,50,48,"2021-12-13T11:00:00","11:00","2022-12-02T13:00:00","13:00",1185,"DAY",null,null,null,null,null,null,null,null,null,null,null,"92 jours dans le régime binaire"]
[]
["More data on SNCF-R TCR 2023 will follow soon"]

{"sheet":"SBB","index":6,"n_rows":11,"n_cols":31,"rows_kept":11,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["SBB Infra",6553,"Basel St. Johann","< >","BSSJ","BSSJ",2021,2021,null,null,"2021-02-26",null,"2021-07-30",null,null,"Night","Signal box works","x",null,null,null,null,"x","x",null,"x",null,"Totalclosure 8 nights for 4 hours. Exactlly dasy tbd"]
["SBB Infra",1872,"Basel RB","< >","BSGB","BSRB",2021,2021,null,null,"2021-03-01",null,"2021-04-19",null,null,"continuous","Switch and track works","x",null,null,null,null,"x","x",null,"x",null,"Nordkopf 100er Weichen (Zulauf Basel GB - RB eingeschränkt), 6 WE Sa/Su - Su/Mo (11.04-12.04 02 am to 04 am totalclosure, 17.04-19.04 10.00 am - 04.00am totalclosure). Trains direction SNCF  with delay till15 Min"]
["SBB Infra",29170,"Muttenz","< >","BSGB","BSRB",2021,2021,null,null,"2021-01-01",null,"2021-12-31",null,null,"continuous","Catenary works",null,"x",null,null,null,null,"x",null,"x",null,"16-18.10, 22-24.10, 30.10.-01-11, 6-8.11 Line Basel - Muttenz totalclosure. Trains direction SNCF via  Basel GB - Basel RB"]
["SBB Infra",1899,"Basel GB - Basel RB","< >","BS","BSRB",2021,2021,null,null,"2021-10-13",null,"2021-11-22",null,null,"continuous","Switch works",null,null,null,null,null,null,null,null,"x",null,"Trains direction SNCF  with delay till15 Min"]
["SBB Infra",54018,"Bellegarde-La Plaine-Genève La Praille ","< >","LPFR","GEPR",2021,2021,null,null,"2021-04-09",null,"2021-04-20",null,null,"continuous","Platform works ",null,"x",null,null,null,null,null,null,"x",null,"Approx. 4 weeks/exact date unknown. Total closures may be possible"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille ","<>","LPFR","GEPR",2021,2021,null,null,"2021-10-14",null,"2021-10-29",null,null,"continuous"]
["SBB Infra","Div.","Basel PB","< >","BSPB","BSPB",2022,2022,null,null,"2022-01-01",null,"2022-12-31",null,null,"continuous",null,null,"x"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","< >","LPFR","GEPR",2023,2023,null,null,"2023-01-15",null,"2023-12-15",null,"11 months","continuous",null,null,"x",null,null,null,"x",null,null,"x",null,"Total closures may be possible"]
["SBB Infra","Div.","Basel PB","< >","BSPB","BSPB",2023,2023,null,null,"2023-01-01",null,"2023-12-31"]

{"sheet":"ACF CFL","index":7,"n_rows":95,"n_cols":31,"rows_kept":95,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["ACF/CFL","ACF10","Luxembourg-Pétange","< >","Dippach","Luxembourg",2021,2021,6,7,"2021-02-13","01:30:00","2021-02-15","04:00:00","2 days","Night/Day","maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF12","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,7,8,"2021-02-16","01:00:00","2021-02-22","04:00:00","6 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF11","Rodange-Athus","< >","Rodange","Athus",2021,2021,7,8,"2021-02-20","04:00:00","2021-02-22","04:00:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF13","Rodange-Athus","< >","Rodange","Athus",2021,2021,8,9,"2021-02-27","04:00:00","2021-03-01","04:00:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF14","Rodange-Athus","< >","Rodange","Athus",2021,2021,9,16,"2021-03-05","00:00:00","2021-04-25","23:59:00","8 weeks","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF15","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2021,2021,12,13,"2021-03-27","01:00:00","2021-03-29","04:00:00","3 days","Night/Day","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF16","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,13,16,"2021-04-03","00:30:00","2021-04-19","04:00:00","16 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF17","Rodange-Aubange","< >","Rodange","Aubange",2021,2021,15,15,"2021-04-17","01:00:00","2021-04-18","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF22","Rodange-Aubange/Athus","< >","Rodange","Aubange/Athus",2021,2021,18,18,"2021-04-24","01:00:00","2021-05-09","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF19","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,16,17,"2021-04-24","04:00:00","2021-04-26","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF18","Rodange-Aubange","< >","Rodange","Aubange",2021,2021,16,16,"2021-04-24","01:00:00","2021-04-25","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF20","Rodange-Aubange/Athus","< >","Rodange","Aubange/Athus",2021,2021,17,17,"2021-05-01","01:00:00","2021-05-02","23:59:00","2 days","Night/Day","INFRABEL - Terminal Athus","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF25","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2021,2021,20,21,"2021-05-22","00:30:00","2021-05-25","04:20:00","3 days","Night/Day","underpass renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF27","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,23,24,"2021-06-12","01:30:00","2021-06-14","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF45","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2021,2021,43,45,"2021-06-19","00:30:00","2021-06-21","04:00:00","3 days","Night/Day","bridge maintenance/renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF28","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,24,25,"2021-06-19","01:30:00","2021-06-21","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF29","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,25,26,"2021-06-26","01:30:00","2021-06-28","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF31","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,26,27,"2021-07-03","01:30:00","2021-07-05","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF30","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,26,27,"2021-07-03","01:30:00","2021-07-05","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF33","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,27,28,"2021-07-10","01:30:00","2021-07-12","04:00:00","2 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF32","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,27,28,"2021-07-10","01:30:00","2021-07-12","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF90","Luxembourg-Bettembourg","< >","Berchem","Bettembourg-M",2021,2021,31,32,"2021-08-08","01:00:00","2021-08-09","04:00:00","1 day","Night/Day","renewal train station","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF91","Luxembourg-Bettembourg","< >","Berchem","Bettembourg-M",2021,2021,32,33,"2021-08-15","01:00:00","2021-08-16","04:00:00","1 day","Night/Day","renewal train station","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF92","Luxembourg-Bettembourg","< >","Berchem","Bettembourg-M",2021,2021,32,33,"2021-08-21","01:00:00","2021-08-23","04:00:00","2 days","Night/Day","renewal train station","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF93","Rodange-Bettembourg","< >","Noertzange","Bettembourg-M",2021,2021,33,33,"2021-08-23","00:00:00","2021-08-23","03:00:00","3 hours","Night","external works (public electricity supplier)","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF38","Rodange-Bettembourg","< >","Rodange","Pétange",2021,2021,34,37,"2021-08-23","00:00:00","2021-09-13","04:00:00","22 days","Night/Day","catenary renewal/train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF37","Rodange-Bettembourg","< >","Esch/Alzette","Noertzange",2021,2021,34,37,"2021-08-28","00:00:00","2021-09-13","04:00:00","17 days","Night/Day","bridge maintenance/renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF41","Luxembourg-Pétange","< >","Dippach","Luxembourg ",2021,2021,39,40,"2021-10-02","01:30:00","2021-10-04","04:00:00","2 days","Night/Day","supppression railway crossing","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF42","Luxembourg-Pétange","< >","Pétange","Luxembourg ",2021,2021,40,41,"2021-10-09","05:00:00","2021-10-11","04:00:00","2 days","Night/Day","external works (public electricity supplier)","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF43","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,41,42,"2021-10-16","04:00:00","2021-10-18","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF44","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,42,43,"2021-10-23","04:00:00","2021-10-25","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF47","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2021,2021,43,44,"2021-10-30","00:00:00","2021-11-02","04:00:00","3 days","Night/Day","underpass renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF46","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2021,2021,43,45,"2021-10-30","00:00:00","2021-11-08","04:00:00","9 days","Night/Day","switch renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF75","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2021,2021,45,46,"2021-11-13","04:00:00","2021-11-15","04:00:00","2 days","Night/Day","bridge maintenance/renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF76","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2021,2021,49,50,"2021-12-11","04:00:00","2021-12-13","04:00:00","2 days","Night/Day","project Howald","x",null,null,null,null,"x","x",null,null,null,"continious restriction"]
["ACF/CFL","ACF77","Luxembourg-Bettembourg","< >","Luxembourg","Bettemboourg",2021,2021,50,51,"2021-12-18","04:00:00","2021-12-20","04:00:00","2 days","Night/Day","project Howald","x",null,null,null,null,"x","x",null,null,null,"continious restriction"]
["ACF/CFL","ACF78","Rodange-Bettembourg","< >","Belval-Lycée","Esch/Alzette",2022,2022,1,26,"2022-01-03","00:10:00","2022-06-30","04:45:00","172 days","Night","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"from Monday to Friday",null,"no"]
["ACF/CFL","ACF94","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,4,5,"2022-01-29","01:00:00","2022-01-31","04:00:00","2 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF79","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,5,8,"2022-01-31","01:20:00","2022-02-25","04:10:00","26 days","Night","station renewal","x",null,null,null,null,"x",null,null,null,null,"from Monday to Friday",null,"no"]
["ACF/CFL","ACF95","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,5,6,"2022-02-05","01:00:00","2022-02-07","04:00:00","2 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF96","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,6,7,"2022-02-12","01:00:00","2022-02-14","04:00:00","2 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF97","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,7,8,"2022-02-19","01:00:00","2022-02-21","04:00:00","2 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF48","Rodange-Bettembourg","< >","Noertzange","Esch/Alzette",2022,2022,7,8,"2022-02-19","01:00:00","2022-02-21","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF49","Rodange-Bettembourg","< >","Noertzange","Esch/Alzette",2022,2022,9,10,"2022-03-05","01:00:00","2022-03-07","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF98","Rodange - Bettembourg","< >","Pétange","Luxembourg",2022,2022,10,11,"2022-03-12","01:00:00","2022-03-14","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF99","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2022,2022,13,15,"2022-04-02","01:00:00","2022-04-10","23:59:00","9 days","Night/Day","catenary & track maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF100","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2022,2022,15,16,"2022-04-11","01:00:00","2022-04-18","04:00:00","7 days","Night/Day","catenary & track maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF82","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,16,17,"2022-04-23","01:00:00","2022-04-25","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF83","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,17,18,"2022-04-30","01:00:00","2022-05-02","04:00:00","3 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF50","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2022,2022,18,19,"2022-05-07","01:00:00","2022-05-10","04:00:00","3 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF84","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2022,2022,19,20,"2022-05-14","01:00:00","2022-05-16","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF51","Rodange-Bettembourg","< >","Belvaux-Soleuvre","Esch/Alzette",2022,2022,20,22,"2022-05-21","01:00:00","2022-05-30","04:00:00","9 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF52","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2022,2022,22,23,"2022-06-04","01:00:00","2022-06-07","04:00:00","3 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF53","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,23,24,"2022-06-11","01:20:00","2022-06-13","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF54","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,24,25,"2022-06-18","01:20:00","2022-06-20","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF55","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,25,26,"2022-06-25","01:20:00","2022-06-27","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF56","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,26,27,"2022-07-02","01:00:00","2022-07-04","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF85","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2022,2022,27,28,"2022-07-09","01:00:00","2022-07-11","04:00:00","3 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF101","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2022,2022,29,31,"2022-07-16","01:20:00","2022-07-31","23:59:00","16 days","Night/Day","new line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF58","Rodange-Bettembourg","< >","Rodange","Lamadelaine",2022,2022,34,37,"2022-08-20","01:00:00","2022-09-05","04:00:00","16 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF60","Luxembourg-Bettembourg",">","Luxembourg","Bettembourg",2022,2022,37,38,"2022-09-16","23:30:00","2022-09-19","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF87","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,37,38,"2022-09-17","01:00:00","2022-09-19","04:00:00","2 days","Night/Day","renewal station","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF61","Rodange-Bettembourg","< >","Belval-Usines","Pétange",2022,2022,38,39,"2022-09-24","01:00:00","2022-09-26","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF62","Rodange-Bettembourg","< >","Belval-Usines","Pétange",2022,2022,39,40,"2022-10-01","01:00:00","2022-10-03","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF66","Rodange-Bettembourg","< >","Belval-Usines","Pétange",2022,2022,42,43,"2022-10-22","01:00:00","2022-10-24","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF69","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,46,47,"2022-11-19","01:00:00","2022-11-21","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF72","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,47,48,"2022-11-21","01:00:00","2022-12-04","23:59:00","14 days","Night/Day","Construction new hangar","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF73","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,49,50,"2022-12-10","04:00:00","2022-12-12","01:00:00","2 days","Night/Day","Construction new hangar","x",null,null,null,null,"x",null,null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF74","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,50,51,"2022-12-17","01:00:00","2022-12-19","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF102","Luxembourg-Bettembourg",">","Luxembourg","Berchem",2023,2023,1,2,"2023-01-08","01:00:00","2023-01-09","04:00:00","1 day","Night/Day","renewal of the line","x","x",null,null,null,null,"x",null,null,"x","continious restriction",null,"no"]
["ACF/CFL","ACF103","Luxembourg-Bettembourg",">","Luxembourg","Berchem",2023,2023,2,3,"2023-01-15","01:00:00","2023-01-16","04:00:00","1 day","Night/Day","renewal of the line","x","x",null,null,null,null,"x",null,null,"x","continious restriction",null,"no"]
["ACF/CFL","ACF104","Luxembourg-Bettembourg","< >","Luxembourg","Fentange",2023,2023,7,8,"2023-02-18","01:00:00","2023-02-20","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF105","Luxembourg-Bettembourg","< >","Luxembourg","Fentange",2023,2023,8,9,"2023-02-25","01:00:00","2023-02-27","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF106","Luxembourg-Bettembourg","< >","Luxembourg","Berchem",2023,2023,9,14,"2023-03-01","22:00:00","2023-04-08","04:00:00","39 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF107","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2023,13,15,"2023-04-01","01:00:00","2023-04-17","04:00:00","16 days","Night/Day","Track maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF108","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2023,2023,14,15,"2023-04-08","01:00:00","2023-04-11","04:00:00","3 days","Night/Day","plattform renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF109","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,16,17,"2023-04-22","01:00:00","2023-04-24","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF110","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2023,2023,17,18,"2023-04-29","01:00:00","2023-05-02","04:00:00","3 days","Night/Day","plattform renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF113","Rodange - Bettembourg","< >","Bettembourg","Esch/Alzette",2023,2023,18,19,"2023-05-06","01:00:00","2023-05-08","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF112","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2023,2023,21,23,"2023-05-27","01:00:00","2023-06-05","04:00:00","9 days","Night/Day","Track and plattform maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF111","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2023,2023,21,22,"2023-05-27","01:00:00","2023-05-30","04:00:00","3 days","Night/Day","plattform renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF117","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,24,25,"2023-06-17","01:00:00","2023-06-19","04:00:00","2 days","Night/Day","renewal aqueducs","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF114","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2023,24,25,"2023-06-17","01:00:00","2023-06-19","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF118","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,25,26,"2023-06-24","01:00:00","2023-06-26","04:00:00","2 days","Night/Day","renewal aqueducs","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF115","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2022,25,26,"2023-06-24","01:00:00","2023-06-26","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF119","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,26,27,"2023-07-01","01:00:00","2023-07-03","04:00:00","2 days","Night/Day","renewal aqueducs","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF116","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2023,26,27,"2023-07-01","01:00:00","2023-07-03","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF120","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,27,28,"2023-07-08","01:00:00","2023-07-10","04:00:00","2 days","Night/Day","renewal aqueducs","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF121","Luxembourg-Bettembourg",">","Luxembourg","Berchem",2023,2023,29,36,"2023-07-14","22:00:00","2023-09-11","04:00:00","58 days","Night/Day","renewal of the line",null,"x","x",null,null,"x","x",null,null,"x","continious restriction",null,"no"]
["ACF/CFL","ACF122","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2023,2023,43,45,"2023-10-28","01:00:00","2023-11-06","04:00:00","9 days","Night/Day","Track and plattform maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF123","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,45,46,"2023-11-11","01:00:00","2023-11-13","04:00:00","2 days","Night/Day","renewal aqueducs","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF124","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,46,47,"2023-11-18","01:00:00","2023-11-20","04:00:00","2 days","Night/Day","renewal aqueducs","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]
["ACF/CFL","ACF125","Rodange-Luxembourg","< >","Pétange","Luxembourg",2023,2023,47,48,"2023-11-25","01:00:00","2023-11-27","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction",null,"no"]