{"text_format":"1","workbook":"xlsx","n_sheets":8,"sheets":["Home","Main Impact Map","ProRail","Infrabel","Data","SNCFR","SBB","ACF CFL"],"not_rendered":{"charts":0,"images":11,"macros":1,"external_links":6,"defined_names":61,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Home","index":0,"n_rows":5,"n_cols":15,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"! click icon to follow !"]

{"sheet":"Main Impact Map","index":1,"n_rows":30,"n_cols":14,"rows_kept":30,"cut":false,"hidden":false,"merged":[[45,5,46,7]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Main TCR for TT 2022 to TT 2024"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"01/02/2022 version 2"]
[null,null,null,null,null,null,null,null,null,null,null,null,"click on the comments for a direct link to TCR details"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,"Plaine d'Alsace"]

{"sheet":"ProRail","index":2,"n_rows":82,"n_cols":22,"rows_kept":82,"cut":false,"hidden":false,"merged":[[0,15,0,16],[0,3,0,4],[0,5,0,6],[0,7,0,8],[0,9,0,10],[0,11,0,12]]}
["IM","ID","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Type of TCR","Reason for \nrestriction","Traffic impact",null,"Description","IM\nProject ID\n(Optional)","Last update","Classification","Deviation location"]
[null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,"Total Closure","Reduced Track Availability "]
["ProRail","D003161-23A5-00","< >","Roosendaal","Goes",2023,2023,23,23,"2023-06-09","01:00:00","2023-06-11","05:00:00","continuous","Miscellaneous","T","LT+ST","Saneren Dateq en realiseren DOSS 2.0 * More details: https://btd-planner.prorail.nl?taak=IO-D-003161-23A5-00-2&doc=FOT (Register with ProRail)","D-003161","2021-12-02","Medium",""]
["ProRail","K005837-26ZB-02","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2021,2021,49,49,"2021-12-12","01:20:00","2021-12-12","06:50:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP B van 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZB-02-2&doc=FOT (Register with ProRail)","K-005837","2021-10-22","Minor",""]
["ProRail","K005837-26ZC-02","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,2,2,"2022-01-16","01:20:00","2022-01-16","06:57:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP C 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZC-02-2&doc=FOT (Register with ProRail)","K-005837","2021-09-15","Minor",""]
["ProRail","K005837-26ZB-04","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,6,6,"2022-02-13","01:20:00","2022-02-13","06:50:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP B van 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZB-04-2&doc=FOT (Register with ProRail)","K-005837","2021-12-08","Minor",""]
["ProRail","K005837-26ZC-05","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,10,10,"2022-03-13","01:20:00","2022-03-13","06:57:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP C 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZC-05-2&doc=FOT (Register with ProRail)","K-005837","2021-11-18","Minor",""]
["ProRail","K005837-26ZB-06","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,14,14,"2022-04-10","01:20:00","2022-04-10","06:50:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP B van 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZB-06-3&doc=FOT (Register with ProRail)","K-005837","2021-12-08","Minor",""]
["ProRail","K005837-26ZC-04","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,18,18,"2022-05-08","01:20:00","2022-05-08","06:57:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP C 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZC-04-3&doc=FOT (Register with ProRail)","K-005837","2021-12-15","Minor",""]
["ProRail","K005837-26ZC-01","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,24,24,"2022-06-19","01:20:00","2022-06-19","06:57:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP C 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZC-01-1&doc=FOT (Register with ProRail)","K-005837","2021-12-15","Minor",""]
["ProRail","K005837-26ZB-05","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,28,28,"2022-07-17","01:20:00","2022-07-17","06:50:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP B van 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZB-05-1&doc=FOT (Register with ProRail)","K-005837","2021-10-29","Minor",""]
["ProRail","K005837-26ZC-07","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,30,30,"2022-07-31","01:20:00","2022-07-31","06:57:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP C 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZC-07-1&doc=FOT (Register with ProRail)","K-005837","2021-12-15","Minor",""]
["ProRail","K005837-26ZB-01","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,31,31,"2022-08-07","01:20:00","2022-08-07","06:50:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP B van 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZB-01-1&doc=FOT (Register with ProRail)","K-005837","2021-11-19","Minor",""]
["ProRail","K005837-26ZC-03","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,36,36,"2022-09-11","01:20:00","2022-09-11","06:57:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP C 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZC-03-1&doc=FOT (Register with ProRail)","K-005837","2021-12-15","Minor",""]
["ProRail","K005837-26ZB-03","< >","Kijfhoek zuid","Moerdijkbrug Zuid aansl.",2022,2022,40,40,"2022-10-09","01:20:00","2022-10-09","06:50:00","continuous","Maintenance","T","LT+ST","WOAA RZR2022604 (WP B van 604 vrij van mat) PCA werkzaamheden AR Zlw-Khaz, za/zo nachten. RZR2022601, 604, 605 en 685. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-26ZB-03-1&doc=FOT (Register with ProRail)","K-005837","2021-10-29","Minor",""]
["ProRail","K006000-IJW5-00","< >","Kijfhoek aansl. Zuid","Rotterdam Stadion",2022,2022,15,15,"2022-04-17","01:10:00","2022-04-17","11:10:00","continuous","Catenary","T","LT+ST","Saneren oude BVL draden * More details: https://btd-planner.prorail.nl?taak=IO-K-006000-IJW5-00-3&doc=FOT (Register with ProRail)","K-006000","2021-12-23","Minor",""]
["ProRail","K006136-Z603-00","< >","Kijfhoek aansl. Zuid","Kijfhoek aansluiting noord",2022,2022,12,12,"2022-03-27","00:00:00","2022-03-27","07:00:00","continuous","Miscellaneous","T","LT+ST","PCA werkzaamheden ZZR202-2605, ZZR202-2603, ZZR202-2602 Aparte IO ivm ingang Zomertijd * More details: https://btd-planner.prorail.nl?taak=IO-K-006136-Z603-00-2&doc=FOT (Register with ProRail)","K-006136","2021-11-25","Minor",""]
["ProRail","K006609-2311-00",">","Kijfhoek Noord","Kijfhoek Noord",2023,2023,5,7,"2023-02-04","00:00:00","2023-02-16","00:00:00","continuous","Switch","","ST","Cluster 07 Vernieuwen wisselliggers kruiscomplexen 341K, 349K en 357K  inclusief aansluitende wissels * More details: https://btd-planner.prorail.nl?taak=IO-K-006609-2311-00-1&doc=FOT (Register with ProRail)","K-006609","2021-11-02","High",""]
["ProRail","K006609-2309-00",">","Kijfhoek zuid","Kijfhoek aansluiting noord",2023,2023,14,15,"2023-04-05","23:00:00","2023-04-10","23:00:00","continuous","Switch","","LT+ST","Cluster 11 Vernieuwen wissel 3735, 3737, 3739, 3741, 3743 en 3747 * More details: https://btd-planner.prorail.nl?taak=IO-K-006609-2309-00-5&doc=FOT (Register with ProRail)","K-006609","2021-12-01","Medium",""]
["ProRail","K006613-2022-00","< >","Kijfhoek aansl. Zuid","Rotterdam Stadion",2022,2022,3,4,"2022-01-22","02:10:00","2022-01-24","05:10:00","continuous","Tunnel","T","LT+ST","Aanpassen besturing in 5 tunnelbuizen (NS-reisigers, ) * More details: https://btd-planner.prorail.nl?taak=IO-K-006613-2022-00-6&doc=FOT (Register with ProRail)","K-006613","2021-12-06","Medium",""]
["ProRail","K006613-1903-00","< >","Kijfhoek aansl. Zuid","Rotterdam Stadion",2022,2022,21,22,"2022-05-28","01:25:00","2022-05-30","05:25:00","continuous","Tunnel","T","LT+ST","Aanpassen besturing in 5 tunnelbuizen (NS-reisigers, Goederen en HSL) en de Dive Under HSL * More details: https://btd-planner.prorail.nl?taak=IO-K-006613-1903-00-8&doc=FOT (Register with ProRail)","K-006613","2021-12-22","Medium","00129, 00173, 00055, 00747"]
["ProRail","K006613-1904-00","< >","Kijfhoek aansl. Zuid","Rotterdam Stadion",2022,2022,32,33,"2022-08-13","01:00:00","2022-08-15","05:00:00","continuous","Tunnel","T","LT+ST","Aanpassen besturing in 5 tunnelbuizen (NS-reisigers, Goederen en HSL) en Dive Under HSL. * More details: https://btd-planner.prorail.nl?taak=IO-K-006613-1904-00-8&doc=FOT (Register with ProRail)","K-006613","2021-12-14","Medium","00129, 00173, 00055, 00747"]
["ProRail","K007202-01-00",">","Kijfhoek zuid","Kijfhoek Noord",2023,2023,25,26,"2023-06-24","10:00:00","2023-06-26","14:00:00","continuous","Miscellaneous","","LT","- Herconfigureren MSR 32 - Testen of bundel 3-1 juist in dienst blijft - Veilig buiten gebruik nemen bundels 6-4 * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-01-00-2&doc=FOT (Register with ProRail)","K-007202","2021-11-02","Medium",""]
["ProRail","K007202-02-00",">","Kijfhoek zuid","Kijfhoek Noord",2023,2024,26,12,"2023-06-26","14:00:00","2024-03-18","14:00:00","continuous","Track & Rail","","LT","Vernieuwen van Heuvelsysteem + BBV op bundels 6-4 * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-02-00-2&doc=FOT (Register with ProRail)","K-007202","2021-11-25","Major",""]
["ProRail","K007207-03-00",">","Kijfhoek zuid","Kijfhoek aansluiting noord",2023,2023,19,20,"2023-05-13","01:00:00","2023-05-20","01:00:00","continuous","Miscellaneous","","LT+ST","Aanleg weg aankomstsporen + kruisende blusleidingen * More details: https://btd-planner.prorail.nl?taak=IO-K-007207-03-00-2&doc=FOT (Register with ProRail)","K-007207","2021-12-09","Medium",""]
["ProRail","K007207-02-00","< >","Kijfhoek zuid","Kijfhoek aansluiting noord",2023,2023,21,22,"2023-05-27","19:00:00","2023-05-29","23:00:00","continuous","Miscellaneous","T","LT+ST","Aanleg pomp + 2x hydrant + 100m blusleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-007207-02-00-2&doc=FOT (Register with ProRail)","K-007207","2021-12-03","Medium",""]
["ProRail","K007207-04-00",">","Kijfhoek Noord","Kijfhoek Noord",2023,2023,23,24,"2023-06-05","01:00:00","2023-06-12","01:00:00","continuous","Miscellaneous","","ST","Asfalteren middenweg + vernieuwen hydranten * More details: https://btd-planner.prorail.nl?taak=IO-K-007207-04-00-2&doc=FOT (Register with ProRail)","K-007207","2021-12-20","Medium",""]
["ProRail","K007207-01-00",">","Kijfhoek aansl. Zuid","Kijfhoek zuid",2023,2024,26,12,"2023-06-26","14:00:00","2024-03-18","13:00:00","continuous","Miscellaneous","","LT","Aanleg calamiteitenweg spoor 135 + gedeelte overwegen zuidzijde * More details: https://btd-planner.prorail.nl?taak=IO-K-007207-01-00-3&doc=FOT (Register with ProRail)","K-007207","2021-12-03","Major",""]
["ProRail","KX00005-2202-00",">","Waalhaven Zuid aansl. Noord","Pernis",2022,2022,15,16,"2022-04-16","19:00:00","2022-04-18","23:00:00","continuous","Switch","","LT+ST","Cluster WE-33 Vernieuwen wissel 473, 475A, 475B, 479A en 479B * More details: https://btd-planner.prorail.nl?taak=IO-K-X00005-2202-00-3&doc=FOT (Register with ProRail)","K-X00005","2021-04-01","Medium",""]
["ProRail","KX00005-TVP3-00",">","Pernis","Botlek Theemsweg aansl.",2022,2022,15,16,"2022-04-16","19:00:00","2022-04-20","10:00:00","continuous","Track & Rail","","LT+ST","infra op orde * More details: https://btd-planner.prorail.nl?taak=IO-K-X00005-TVP3-00-3&doc=FOT (Register with ProRail)","K-X00005","2021-11-17","Medium",""]
["ProRail","KX00005-TVP9-00",">","Pernis","Botlek Theemsweg aansl.",2022,2022,22,24,"2022-06-04","15:00:00","2022-06-14","18:00:00","continuous","Track & Rail","","LT+ST","combi TVP 4 en 5 * More details: https://btd-planner.prorail.nl?taak=IO-K-X00005-TVP9-00-3&doc=FOT (Register with ProRail)","K-X00005","2021-04-01","High",""]
["ProRail","KX00005-2203-00",">","Rail Service Center Waalhaven aansl.","Botlek",2022,2022,27,28,"2022-07-09","23:00:00","2022-07-11","07:00:00","continuous","Track & Rail","","LT+ST","Cluster PE-04 Railinzetplaats spoor 243R, 861V en 851AL * More details: https://btd-planner.prorail.nl?taak=IO-K-X00005-2203-00-3&doc=FOT (Register with ProRail)","K-X00005","2021-04-01","Medium",""]
["ProRail","KX00005-2210-00",">","Rail Service Center Waalhaven aansl.","Botlek",2022,2022,38,39,"2022-09-24","23:00:00","2022-09-26","07:00:00","continuous","Track & Rail","","LT+ST","Cluster PE-04 Railinzetplaats spoor 243R, 861V en 851AL * More details: https://btd-planner.prorail.nl?taak=IO-K-X00005-2210-00-2&doc=FOT (Register with ProRail)","K-X00005","2021-04-01","Medium",""]
["ProRail","KX00006-2308-00",">","Waalhaven Zuid","Waalhaven Zuid",2023,2023,7,8,"2023-02-18","01:00:00","2023-02-20","05:00:00","continuous","Track & Rail","","ST","Cluster WE-27 (3x 1:9 GW en ca. 136m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2308-00-2&doc=FOT (Register with ProRail)","K-X00006","2021-11-25","Medium",""]
["ProRail","KX00006-2306-00",">","Waalhaven Zuid","Waalhaven Zuid",2023,2023,8,9,"2023-02-25","01:00:00","2023-02-28","17:00:00","continuous","Track & Rail","","ST","Cluster WE-15 (2x 1:9 GW en ca. 1131m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2306-00-4&doc=FOT (Register with ProRail)","K-X00006","2021-11-25","Medium",""]
["ProRail","KX00006-2307-00",">","Waalhaven Zuid","Waalhaven Zuid",2023,2023,9,10,"2023-03-04","01:00:00","2023-03-06","05:00:00","continuous","Track & Rail","","ST","Cluster WE-25 + WE-26 (ca. 645m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2307-00-2&doc=FOT (Register with ProRail)","K-X00006","2021-11-25","Medium",""]
["ProRail","KX00006-2324-00",">","Europoort","Europoort West",2023,2023,14,15,"2023-04-08","19:00:00","2023-04-10","23:00:00","continuous","Track & Rail","","LT","Cluster EE-05 (2x 1:9 GW en ca. 29m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2324-00-1&doc=FOT (Register with ProRail)","K-X00006","2021-12-20","Medium",""]
["ProRail","KX00006-2323-00",">","Botlek Theemsweg aansl.","Europoort West",2023,2023,14,15,"2023-04-08","23:00:00","2023-04-12","03:00:00","continuous","Track & Rail","","LT+ST","Cluster EE-02 + EE-05 (2x 1:9 GW, 2x 1:9 W en ca. 307m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2323-00-1&doc=FOT (Register with ProRail)","K-X00006","2021-12-03","Medium",""]
["ProRail","KX00006-2304-00",">","Waalhaven Zuid aansl. Noord","Waalhaven Zuid",2023,2023,18,18,"2023-05-01","07:00:00","2023-05-04","01:00:00","continuous","Track & Rail","","LT","Cluster WE-14 (ca. 1029m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2304-00-4&doc=FOT (Register with ProRail)","K-X00006","2021-12-03","Medium",""]
["ProRail","KX00006-2309-00",">","Waalhaven Zuid","Waalhaven Zuid",2023,2023,21,22,"2023-05-27","19:00:00","2023-05-29","23:00:00","continuous","Track & Rail","","ST","Cluster WE-29 (1x 1:9 GW, 1x 1:9 EW en ca. 130m spoor) Cluster WR-12 (1x 26m OVW en ca 48m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2309-00-4&doc=FOT (Register with ProRail)","K-X00006","2021-12-03","Medium",""]
["ProRail","KX00006-2314-00","< >","Pernis","Botlek",2023,2023,26,27,"2023-07-01","23:00:00","2023-07-03","07:00:00","continuous","Track & Rail","T","LT+ST","Cluster BE-04 (240m sps) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2314-00-1&doc=FOT (Register with ProRail)","K-X00006","2021-09-28","Medium",""]
["ProRail","KX00006-2310-00",">","Waalhaven Zuid","Waalhaven Zuid",2023,2023,42,43,"2023-10-21","01:00:00","2023-10-25","01:00:00","continuous","Track & Rail","","ST","Cluster WR-04 + WR-05 (2x 1:9 GW, 2x 28m OVW en ca. 702m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-2310-00-1&doc=FOT (Register with ProRail)","K-X00006","2021-12-06","Medium",""]
["ProRail","M004547-29Z4-03","< >","Lage Zwaluwe","Lage Zwaluwe",2022,2022,4,4,"2022-01-27","08:30:00","2022-01-27","13:25:00","continuous","Maintenance","T","ST","WOAA ZDR2022985, 29Z4, Zlw Do. * More details: https://btd-planner.prorail.nl?taak=IO-M-004547-29Z4-03-2&doc=FOT (Register with ProRail)","M-004547","2021-10-08","Minor",""]
["ProRail","M004547-ZLD4-00","< >","Roosendaal","Roosendaal",2022,2022,4,4,"2022-01-29","23:10:00","2022-01-30","07:10:00","continuous","Maintenance","T","ST","ZLD4, Roosendaal, Herstel gebreken tbv oplevering PGO contract. * More details: https://btd-planner.prorail.nl?taak=IO-M-004547-ZLD4-00-4&doc=FOT (Register with ProRail)","M-004547","2021-09-29","Minor",""]
["ProRail","M004547-ZLD3-00","< >","Roosendaal","Roosendaal",2022,2022,5,5,"2022-02-05","23:45:00","2022-02-06","07:45:00","continuous","Maintenance","T","ST","ZLD3, Roosendaal, Herstel gebreken tbv oplevering PGO contract. * More details: https://btd-planner.prorail.nl?taak=IO-M-004547-ZLD3-00-5&doc=FOT (Register with ProRail)","M-004547","2021-10-13","Minor",""]
["ProRail","M004547-ZLD1-00","< >","Lage Zwaluwe","Moerdijk",2022,2022,7,7,"2022-02-19","23:00:00","2022-02-20","07:00:00","continuous","Maintenance","T","LT+ST","ZLD1, Zwaluwe, Herstel gebreken tbv oplevering PGO contract. * More details: https://btd-planner.prorail.nl?taak=IO-M-004547-ZLD1-00-2&doc=FOT (Register with ProRail)","M-004547","2021-09-22","Minor",""]
["ProRail","M004547-29Z4-02","< >","Lage Zwaluwe","Lage Zwaluwe",2022,2022,12,12,"2022-03-24","08:30:00","2022-03-24","13:25:00","continuous","Maintenance","T","ST","WOAA ZDR2022985, 29Z4, Zlw Do. * More details: https://btd-planner.prorail.nl?taak=IO-M-004547-29Z4-02-2&doc=FOT (Register with ProRail)","M-004547","2021-12-10","Minor",""]
["ProRail","M004547-ZLD8-00","< >","Roosendaal","Bergen op Zoom",2022,2022,16,16,"2022-04-23","01:10:00","2022-04-23","13:10:00","continuous","Maintenance","T","LT+ST","ZLD8, Rsd-Bgn, Herstel gebreken tbv oplevering PGO contract * More details: https://btd-planner.prorail.nl?taak=IO-M-004547-ZLD8-00-2&doc=FOT (Register with ProRail)","M-004547","2021-12-10","Minor",""]
["ProRail","M004547-29Z4-04","< >","Lage Zwaluwe","Lage Zwaluwe",2022,2022,20,20,"2022-05-19","08:30:00","2022-05-19","13:25:00","continuous","Maintenance","T","ST","WOAA ZDR2022985, 29Z4, Zlw Do. * More details: https://btd-planner.prorail.nl?taak=IO-M-004547-29Z4-04-2&doc=FOT (Register with ProRail)","M-004547","2021-12-10","Minor",""]
["ProRail","M004547-29Z4-01","< >","Lage Zwaluwe","Lage Zwaluwe",2022,2022,24,24,"2022-06-16","08:30:00","2022-06-16","13:25:00","continuous","Maintenance","T","ST","WOAA ZDR2022985, 29Z4, Zlw Do. * More details: https://btd-planner.prorail.nl?taak=IO-M-004547-29Z4-01-1&doc=FOT (Register with ProRail)","M-004547","2021-09-14","Minor",""]
["ProRail","M004547-29Z4-06","< >","Lage Zwaluwe","Lage Zwaluwe",2022,2022,36,36,"2022-09-08","08:30:00","2022-09-08","13:25:00","continuous","Maintenance","T","ST","WOAA ZDR2022985, 29Z4, Zlw Do. * More details: https://btd-planner.prorail.nl?taak=IO-M-004547-29Z4-06-1&doc=FOT (Register with ProRail)","M-004547","2021-09-17","Minor",""]
["ProRail","M004547-29Z4-05","< >","Lage Zwaluwe","Lage Zwaluwe",2022,2022,44,44,"2022-11-03","08:30:00","2022-11-03","13:25:00","continuous","Maintenance","T","ST","WOAA ZDR2022985, 29Z4, Zlw Do. * More details: https://btd-planner.prorail.nl?taak=IO-M-004547-29Z4-05-1&doc=FOT (Register with ProRail)","M-004547","2021-09-17","Minor",""]
["ProRail","M004701-2202-00","< >","Lage Zwaluwe","Oudenbosch",2022,2022,48,49,"2022-12-03","01:00:00","2022-12-05","05:00:00","continuous","Bridge","T","LT+ST","Vervangen e-componenten Markbrug * More details: https://btd-planner.prorail.nl?taak=IO-M-004701-2202-00-2&doc=FOT (Register with ProRail)","M-004701","2021-04-19","Medium","00526"]
["ProRail","M004734-2203-00","< >","Oudenbosch","Roosendaal",2022,2022,48,49,"2022-12-03","01:00:00","2022-12-05","05:00:00","continuous","Maintenance","T","LT","Saneren wissels * More details: https://btd-planner.prorail.nl?taak=IO-M-004734-2203-00-2&doc=FOT (Register with ProRail)","M-004734","2021-04-19","Medium","00526"]
["ProRail","M004734-2202-00","< >","Roosendaal","Vlissingen Souburg",2023,2023,4,5,"2023-01-27","01:00:00","2023-01-30","05:00:00","continuous","Maintenance","T","LT+ST","Saneren wissels * More details: https://btd-planner.prorail.nl?taak=IO-M-004734-2202-00-5&doc=FOT (Register with ProRail)","M-004734","2021-11-30","Medium",""]
["ProRail","M004734-2301-00","< >","Lage Zwaluwe","Roosendaal",2023,2023,27,28,"2023-07-07","01:00:00","2023-07-10","05:00:00","continuous","Maintenance","T","LT+ST","Saneren wissels en sporen in Oudenbosch en Zevenbergen * More details: https://btd-planner.prorail.nl?taak=IO-M-004734-2301-00-1&doc=FOT (Register with ProRail)","M-004734","2021-11-09","Medium","99960, 00526, 00055"]
["ProRail","M004735-2209-01","< >","Lage Zwaluwe","Moerdijk",2022,2022,9,10,"2022-03-05","23:00:00","2022-03-07","07:00:00","continuous","Switch","T","LT","vernieuwen wissel 901, 902, 919, 905, 926, 927, 928. 4114 meter spoor, 3 overpaden en 3884 meter inspectiepaden. * More details: https://btd-planner.prorail.nl?taak=IO-M-004735-2209-01-6&doc=FOT (Register with ProRail)","M-004735","2021-11-24","Medium",""]
["ProRail","M004735-2208-01","< >","Lage Zwaluwe","Moerdijk",2022,2022,15,16,"2022-04-16","23:00:00","2022-04-19","03:00:00","continuous","Switch","T","LT","vernieuwen wissel 901, 902, 919, 905, 926, 927, 928. 4114 meter spoor, 3 overpaden en 3884 meter inspectiepaden. * More details: https://btd-planner.prorail.nl?taak=IO-M-004735-2208-01-4&doc=FOT (Register with ProRail)","M-004735","2021-11-15","Medium",""]
["ProRail","M004735-2208-02","< >","Lage Zwaluwe","Moerdijk",2022,2022,22,23,"2022-06-04","23:00:00","2022-06-07","03:00:00","continuous","Switch","T","LT","vernieuwen wissel 901, 902, 919, 905, 926, 927, 928. 4114 meter spoor, 3 overpaden en 3884 meter inspectiepaden. * More details: https://btd-planner.prorail.nl?taak=IO-M-004735-2208-02-4&doc=FOT (Register with ProRail)","M-004735","2021-12-22","Medium",""]
["ProRail","M004735-2209-02","< >","Lage Zwaluwe","Moerdijk",2022,2022,27,28,"2022-07-09","23:00:00","2022-07-11","07:00:00","continuous","Switch","T","LT","vernieuwen wissel 901, 902, 919, 905, 926, 927, 928. 4114 meter spoor, 3 overpaden en 3884 meter inspectiepaden. * More details: https://btd-planner.prorail.nl?taak=IO-M-004735-2209-02-3&doc=FOT (Register with ProRail)","M-004735","2021-11-22","Medium",""]
["ProRail","M004735-2209-03","< >","Lage Zwaluwe","Moerdijk",2022,2022,38,39,"2022-09-24","23:00:00","2022-09-26","07:00:00","continuous","Switch","T","LT","vernieuwen wissel 901, 902, 919, 905, 926, 927, 928. 4114 meter spoor, 3 overpaden en 3884 meter inspectiepaden. * More details: https://btd-planner.prorail.nl?taak=IO-M-004735-2209-03-3&doc=FOT (Register with ProRail)","M-004735","2021-11-22","Medium",""]
["ProRail","M004735-2209-04","< >","Lage Zwaluwe","Moerdijk",2022,2022,44,45,"2022-11-05","23:00:00","2022-11-07","07:00:00","continuous","Switch","T","LT","vernieuwen wissel 901, 902, 919, 905, 926, 927, 928. 4114 meter spoor, 3 overpaden en 3884 meter inspectiepaden. * More details: https://btd-planner.prorail.nl?taak=IO-M-004735-2209-04-4&doc=FOT (Register with ProRail)","M-004735","2021-11-22","Medium",""]
["ProRail","M004793-2204-01","< >","Breda aansl.","Roosendaal",2022,2022,13,14,"2022-04-02","01:15:00","2022-04-04","05:15:00","continuous","Track & Rail","T","LT+ST","BBV Vernieuwen van harmelen overwegen. * More details: https://btd-planner.prorail.nl?taak=IO-M-004793-2204-01-4&doc=FOT (Register with ProRail)","M-004793","2021-12-08","Medium","99960, 00129, 00055"]
["ProRail","M004793-2204-02","< >","Breda aansl.","Roosendaal",2022,2022,19,20,"2022-05-14","01:15:00","2022-05-16","05:15:00","continuous","Track & Rail","T","LT+ST","BBV Vernieuwen van harmelen overwegen. * More details: https://btd-planner.prorail.nl?taak=IO-M-004793-2204-02-3&doc=FOT (Register with ProRail)","M-004793","2021-12-10","Medium","99960, 00129, 00055"]
["ProRail","M004849-2301-00","< >","Roosendaal","Goes",2023,2023,19,20,"2023-05-13","01:00:00","2023-05-15","05:00:00","continuous","Track & Rail","T","LT+ST","Diverse BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004849-2301-00-1&doc=FOT (Register with ProRail)","M-004849","2021-12-02","Medium",""]
["ProRail","M004849-2302-00","< >","Roosendaal","Goes",2023,2023,23,24,"2023-06-09","01:00:00","2023-06-12","05:00:00","continuous","Track & Rail","T","LT+ST","Diverse BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004849-2302-00-1&doc=FOT (Register with ProRail)","M-004849","2021-12-02","Medium",""]
["ProRail","M004851-2302-00","< >","Roosendaal","Bergen op Zoom",2023,2023,9,51,"00:00:00","00:00:00","00:00:00","00:00:00","continuous","Track & Rail","T","LT+ST","BBV vernieuwingswerkzaamheden Roosendaal * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2302-00-4&doc=FOT (Register with ProRail)","M-004851","2021-12-07","Medium",""]
["ProRail","M004851-2310-00","< >","Moerdijk","Moerdijk",2023,2023,11,12,"2023-03-18","05:00:00","2023-03-20","09:00:00","continuous","Track & Rail","T","ST","BBV vernieuwingswerkzaamheden Moerdijk Zuidelijke Randweg * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2310-00-3&doc=FOT (Register with ProRail)","M-004851","2021-12-02","Medium",""]
["ProRail","M004851-2309-00","< >","Moerdijk","Moerdijk",2023,2023,14,15,"2023-04-08","19:00:00","2023-04-10","23:00:00","continuous","Track & Rail","T","ST","BBV vernieuwingswerkzaamheden Moerdijk Zuidelijke Randweg * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2309-00-3&doc=FOT (Register with ProRail)","M-004851","2021-12-02","Medium",""]
["ProRail","M004851-2301-00","< >","Roosendaal","Bergen op Zoom",2023,2023,20,21,"2023-05-20","01:00:00","2023-05-22","05:00:00","continuous","Track & Rail","T","LT+ST","BBV vernieuwingswerkzaamheden Roosendaal * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2301-00-4&doc=FOT (Register with ProRail)","M-004851","2021-12-17","Medium",""]
["ProRail","M004851-2304-00","< >","Moerdijk","Moerdijk",2023,2023,21,22,"2023-05-26","11:30:00","2023-05-29","10:00:00","continuous","Track & Rail","T","ST","BBV vernieuwingswerkzaamheden Moerdijk Middenweg * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2304-00-4&doc=FOT (Register with ProRail)","M-004851","2021-12-09","Medium",""]
["ProRail","M004851-2305-00","< >","Moerdijk","Moerdijk",2023,2023,26,27,"2023-07-01","05:00:00","2023-07-03","09:00:00","continuous","Track & Rail","T","ST","BBV wekzaamheden Moerdijk Oostelijke Randweg en Vlasweg * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2305-00-3&doc=FOT (Register with ProRail)","M-004851","2021-12-02","Medium",""]
["ProRail","M004851-2307-00","< >","Lage Zwaluwe","Moerdijk",2023,2023,32,33,"2023-08-12","01:00:00","2023-08-14","05:00:00","continuous","Track & Rail","T","LT+ST","BBV werkzaamheden Lage Zwaluwe * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2307-00-4&doc=FOT (Register with ProRail)","M-004851","2021-12-21","Medium",""]
["ProRail","M004851-2311-00","< >","Moerdijk","Moerdijk",2023,2023,37,38,"2023-09-16","05:00:00","2023-09-18","09:00:00","continuous","Track & Rail","T","ST","BBV wekzaamheden Moerdijk Oostelijke Randweg en Vlasweg * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2311-00-2&doc=FOT (Register with ProRail)","M-004851","2021-12-03","Medium",""]
["ProRail","M004851-2312-00","< >","Oudenbosch","Roosendaal",2023,2023,39,39,"2023-09-30","23:00:00","2023-10-01","09:00:00","continuous","Track & Rail","T","LT","BBV vernieuwingswerkzaamheden Roosendaal * More details: https://btd-planner.prorail.nl?taak=IO-M-004851-2312-00-2&doc=FOT (Register with ProRail)","M-004851","2021-12-05","Minor","00526"]
["ProRail","R465700-LALO-00",">","Waalhaven Zuid","Waalhaven Zuid",2023,2023,48,50,"2023-11-27","08:00:00","2023-12-13","00:00:00","continuous","Miscellaneous","","ST","Realisatie nieuwe Lalo WhZ * More details: https://btd-planner.prorail.nl?taak=IO-R-465700-LALO-00-2&doc=FOT (Register with ProRail)","R-465700","2021-11-15","High",""]
["ProRail","Z9ODB01-2301-00","< >","Zevenbergen inhaalsp.","Roosendaal",2023,2023,39,40,"2023-09-30","05:00:00","2023-10-02","09:00:00","continuous","Miscellaneous","T","LT+ST","Oudenbosch vervangen keerwanden en straatwerk zij- en eilandperron * More details: https://btd-planner.prorail.nl?taak=IO-Z-9ODB01-2301-00-2&doc=FOT (Register with ProRail)","Z-9ODB01","2021-11-25","Medium","00526"]
["ProRail","Z9ODB01-2302-00","< >","Zevenbergen inhaalsp.","Roosendaal",2023,2023,40,40,"2023-10-02","09:00:00","2023-10-04","13:00:00","continuous","Miscellaneous","T","LT+ST","Oudenbosch vervangen keerwanden en straatwerk zij- en eilandperron * More details: https://btd-planner.prorail.nl?taak=IO-Z-9ODB01-2302-00-1&doc=FOT (Register with ProRail)","Z-9ODB01","2021-12-09","Medium","00526"]
["ProRail","Z9ODB01-2303-00","< >","Zevenbergen inhaalsp.","Roosendaal",2023,2023,40,40,"2023-10-04","13:00:00","2023-10-06","17:00:00","continuous","Miscellaneous","T","LT+ST","Oudenbosch vervangen keerwanden en straatwerk zij- en eilandperron * More details: https://btd-planner.prorail.nl?taak=IO-Z-9ODB01-2303-00-1&doc=FOT (Register with ProRail)","Z-9ODB01","2021-11-25","Medium","00526"]
["ProRail","Z207002-2206-00",">","Kijfhoek aansl. Zuid","Rotterdam Centraal",2022,2022,4,4,"2022-01-30","02:15:00","2022-01-30","05:15:00","continuous","Miscellaneous","","LT+ST","jaarlijks EBS onderhoud * More details: https://btd-planner.prorail.nl?taak=IO-Z-207002-2206-00-2&doc=FOT (Register with ProRail)","Z-207002","2021-09-29","Minor",""]
["ProRail","Z222601-2056-00","< >","Roosendaal","Bergen op Zoom",2022,2022,41,41,"2022-10-16","01:20:00","2022-10-16","06:35:00","continuous","Miscellaneous","T","LT+ST","Slijpen VB * More details: https://btd-planner.prorail.nl?taak=IO-Z-222601-2056-00-4&doc=FOT (Register with ProRail)","Z-222601","2021-09-14","Minor",""]
["ProRail","Z222601-2057-00","< >","Roosendaal","Rilland-Bath",2022,2022,42,42,"2022-10-17","00:30:00","2022-10-17","05:30:00","continuous","Miscellaneous","T","LT+ST","Slijpen VB * More details: https://btd-planner.prorail.nl?taak=IO-Z-222601-2057-00-4&doc=FOT (Register with ProRail)","Z-222601","2021-09-14","Minor",""]

{"sheet":"Infrabel","index":3,"n_rows":819,"n_cols":21,"rows_kept":819,"cut":false,"hidden":false,"merged":[[0,17,0,18],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,"Description","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability "]
["Infrabel","13823","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2022,2022,16,17,"2022-04-16",44568.173611111109,"2022-04-19",44568.166666666664,"3d","Continuous",null,"T","","Rnvlt chapes + construction passerelles PI 121,475 ;\r\nRnvlt chapes PI 120,998 et PS 108,062.\r\n+ Maintenance Z2. 51  P4+\r\nUPM 278773 \nHKM à adapter\r\nVia L117 - 124 - 90 - 90C - 96",13823]
["Infrabel","14725","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,12,13,"2022-03-19",44568.034722222219,"2022-03-21",44568.173611111109,"2d","Continuous",null,"T","","Renouvellement des traverses Bi-blocs L 96 avec P93\r\nUPM 278676 \nHKM à adapter\r\nVia L116 - 117 - 118 - 130A",14725]
["Infrabel","14726","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,13,14,"2022-03-26",44568.034722222219,"2022-03-28",44568.173611111109,"2d","Continuous",null,"T","","Renouvellement des traverses Bi-blocs L 96 avec P93\r\n + Maintenance Z.5.53\r\nMise HS en P4\r\nUPM 278682 \nHKM à adapter\r\nVia L116 - 117 - 118 - 124A - 130A",14726]
["Infrabel","14727","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,14,15,"2022-04-02",44568.034722222219,"2022-04-04",44568.173611111109,"2d","Continuous",null,"T","","Renouvellement des traverses Bi-blocs P93\r\nContraintes\r\n+ Maintenance Z.5.53\r\nMise HS en P4\r\nUPM 278684 \nHKM à adapter \r\nVia L116 - 117 - 118 - 124A - 130A",14727]
["Infrabel","14729","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,12,12,"2022-03-14",44568.979166666664,"2022-03-18",44568.177083333336,"4d","Periodical",null,"T","","Renouvellement des traverses Bi-blocs P93\r\nPréparations/finitions\r\nUPM 278586 \nHKM à adapter\r\nVia L116 - 117 - 118 - 130A",14729]
["Infrabel","17166","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2022,2022,43,44,"2022-10-21",44568.965277777781,"2022-10-24",44568.166666666664,"3d","Continuous",null,"T","","Renouvellement du Tablier métallique situé Bk 47.290\r\n+ Tir FDC n° 21/22-22/24-24/25 \n ",17166]
["Infrabel","17167","Namur - Antwerpen","< >","TILLY","FLEURUS",2022,2022,42,43,"2022-10-12",44568.958333333336,"2022-10-17",44568.208333333336,"5d","Periodical",null,"T","","Nuits pour travaux préparatoires Rnvlt du Tablier métallique situé Bk 47.290 \n ",17167]
["Infrabel","17168","Namur - Antwerpen","< >","TILLY","FLEURUS",2022,2022,44,44,"2022-10-24",44568.958333333336,"2022-10-28",44568.166666666664,"4d","Periodical",null,"T","","Nuits pour travaux de finitions Rnvlt du Tablier métallique situé Bk 47.290 \n ",17168]
["Infrabel","20717","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2022,2022,44,46,"2022-10-28",44568.989583333336,"2022-11-07",44568.197916666664,"10d","Continuous",null,"T","","RER CTL : grill coté LLN \r\nachèvement de Y.LLN et MES des voies latérales \r\nAssainissement de plateformess \r\nPose 5 AW\r\nRipage\r\ntvx CAT & sign\r\n\r\n+ Renouvellement de la passerelle BK36.635 à Mont-Saint-Guibert\r\nEntretien des ouvrages du tronçon Ottignie \n ",20717]
["Infrabel","20723","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2022,2022,16,17,"2022-04-15",44568.989583333336,"2022-04-18",44568.232638888891,"3d","Continuous",null,"T","","RER Weekend Paques\r\n\r\nR-300528 \n ",20723]
["Infrabel","20891","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,40,41,"2022-09-30",44568.989583333336,"2022-10-08",44568.197916666664,"8d","Periodical",null,"","ST","Travaux préparatoires  CTL Grill coté LLN \n ",20891]
["Infrabel","21040","Lille - Charleroi","< >","BRUGELETTE","ATH",2022,2022,22,23,"2022-05-27",44568.9375,"2022-05-30",44568.215277777781,"3d","Continuous",null,"T","","Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nUPM 291745 \nHKM à adapter\r\nVia 117 - 124 - 130A - 94",21040]
["Infrabel","21753","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,9,11,"2022-02-26",44568.041666666664,"2022-03-07",44568.166666666664,"9d","Continuous",null,"T","","- Omvorming stopplaats Zwijndrecht (FASE 4)\r\n- Verhogen veiligheid Kennedytunnel\r\n- Bouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet)\r\nTCR 277956 \nHKM om te leiden.",21753]
["Infrabel","22850","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,40,41,"2022-10-01",44568.041666666664,"2022-10-03",44568.1875,"2d","Continuous",null,"T","","project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",22850]
["Infrabel","25715","Namur - Antwerpen",">","TAMINES","CHATELET-GRIL EST",2022,2022,6,11,"2022-01-31",44568.944444444445,"2022-03-12",44568.222222222219,"40d","Periodical",null,"","ST","Aménagement Le Campinaire - Phase 3\r\nUPM : 288847 \n ",25715]
["Infrabel","25727","Namur - Antwerpen","< >","TAMINES","CHATELET",2022,2022,13,13,"2022-03-21",44568.944444444445,"2022-03-25",44568.208333333336,"4d","Periodical",null,"T","","Aménagement Le Campinaire Phase 4 : Travaux Voie sur CTL de nuits semaine\r\n+ Peinture pont métallique L130…83.413.\r\n+ Buitenwerken ETCS (Mathilde Wallez)\r\nUPM 289189 \nHKM à adapter",25727]
["Infrabel","25730","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2022,2022,13,14,"2022-03-25",44568.979166666664,"2022-03-28",44568.1875,"3d","Continuous",null,"T","","Aménagement Le Campinaire Phase 5 : Week-end n°1\r\n+ Renouvellement passages supérieurs BK 85.708 et 84.625\r\n+ Peinture pont métallique (Cleremans Mathieu)\r\n+ Maintenance Z15.51\r\nUPM289194 \nHKM à adapter\r\nVia L117 - 124A - 130 - 140 - 96",25730]
["Infrabel","27245","Athus - Meuse",">","HOUYET","BEAURAING",2022,2022,18,24,"2022-04-25",44568.333333333336,"2022-06-05",44568.75,"41d","Continuous",null,"","ST","Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing\r\n+ visite et interventions diverses le 26 \nHKM à adapter",27245]
["Infrabel","27248","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,37,38,"2022-09-09",44568.986111111109,"2022-09-12",44568.208333333336,"3d","Continuous",null,"T","","Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD\r\nMassification avec travaux :Marche-les-Dames Phase2: Assainissement voie B (part 1/2); Rectification de tracé en voie B; Renouvelle \n ",27248]
["Infrabel","27255","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,48,51,"2022-11-21",44568.333333333336,"2022-12-16",44568.666666666664,"25d","Continuous",null,"","ST","Renouvellement quais de Lustin + mise au gabarit pistes Godinne\r\n+ visites 30/11 (G.G.) \n ",27255]
["Infrabel","27256","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,43,47,"2022-10-18",44568.333333333336,"2022-11-13",44568.333333333336,"26d","Continuous",null,"","ST","Renouvellement quais de Lustin + sécurisation paroi Godinne\r\n+ visites le 18/10 (G. G.) \n",27256]
["Infrabel","27403","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2022,2022,3,7,"2022-01-12",44568.25,"2022-02-11",44568.708333333336,"30d","Continuous",null,"","ST","Réalisation d'une dalle en béton armé pour l'étanchéité de la culée-voûte à la bk 8,509 - côté voie B\r\nSécurisation parois rocheuses du 10.01 8:00 au 1.04 18:00 (Javaux)\r\nUPM 275642 \nPas de croisement prévu au saionnier",27403]
["Infrabel","27924","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2022,2022,10,11,"2022-03-05",44568.958333333336,"2022-03-06",44568.625,"1d","Continuous",null,"T","","Mini CTL pour maintenance globale L 130\r\nUPM: 279839 \nHKM à adapter\r\nInfo Racc 45 : 1.N.112/1 (Inovyn)\r\nInfo Racc 46 : 1.N.112/2 (Inovyn 1)\r\nInfo Racc 47 : 1.N.112/3 (Inovyn 2)",27924]
["Infrabel","27927","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2023,2023,2,3,"2023-01-14",44568.986111111109,"2023-01-15",44568.618055555555,"1d","Continuous",null,"T","","Mini CTL pour maintenance globale L 130 + L144 + L130/1\r\nService ES Révision 36AQ/36BQ\r\nUPM : 335293 \n ",27927]
["Infrabel","27970","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2022,2022,13,14,"2022-03-26",44568.25,"2022-03-27",44568.916666666664,"1d","Continuous",null,"T","","Entretien des PN + maintenance massifiée + Travaux ES\r\nEn massification avec les travaux de Wavre\r\nUPM: 279899 \nHKM à adapter",27970]
["Infrabel","28105","Lille - Charleroi","< >","LUTTRE","Y.LA SAMBRE",2022,2022,20,21,"2022-05-14",44568.583333333336,"2022-05-16",44568.180555555555,"2d","Continuous",null,"T","","Réélectrification L. 124+L. 124A \r\nWeekend en CTL 4 voies en continu\r\nUPM 280877 \nHKM à adapter",28105]
["Infrabel","28137","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,4,5,"2022-01-22",44568.979166666664,"2022-01-24",44568.201388888891,"2d","Periodical",null,"T","","Aménagement Le Campinaire - Phase 2 : Intervention caténaire\r\nCTL de nuit sans impact\r\nUPM 288833 \n ",28137]
["Infrabel","28146","Namur - Antwerpen",">","TAMINES","CHATELET-GRIL EST",2022,2022,16,16,"2022-04-11",44568.944444444445,"2022-04-16",44568.229166666664,"5d","Periodical",null,"","ST","Aménagement Le Campinaire Phase 9\r\nUPM 288881 \nHKM à adapter",28146]
["Infrabel","28278","Namur - Antwerpen","< >","AUVELAIS","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2022,2022,10,11,"2022-03-05",44568.958333333336,"2022-03-06",44568.625,"1d","Continuous",null,"T","","Maintenance Z19. 51\r\nMini CTL\r\nUPM 286510 \nHKM à adapter\r\nInfo Racc : CARMEUSE",28278]
["Infrabel","28280","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2022,2022,12,12,"2022-03-14",44568.944444444445,"2022-03-19",44568.208333333336,"5d","Periodical",null,"T","","Maintenance Z15. 51   P3HKV\r\n+ Peinture pont métallique L130…83.413.\r\n+ Aménagement Le Campinaire Phase 4 : Travaux Voie sur CTL de nuits semaine\r\n+ Buitenwerken ETCS (Wallez Mathilde)\r\nUPM 289186 \nHKM à adapter\r\nVia L117 - 124A - 130 - 130C - 140 - 147 - 96",28280]
["Infrabel","28283","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2022,2022,30,31,"2022-07-23",44568.25,"2022-07-24",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z15. 51\r\nP4+ \n ",28283]
["Infrabel","28284","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2022,2022,40,40,"2022-09-26",44568.979166666664,"2022-10-01",44568.1875,"5d","Periodical",null,"T","","Maintenance Z15. 51\r\nP3 \n ",28284]
["Infrabel","28285","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2022,2022,34,35,"2022-08-20",44568.958333333336,"2022-08-21",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z19. 51\r\nMini CTL\r\n+ Travaux de finitions - Renouvellement de la chape d'étanchéité du PI 78.887 \n ",28285]
["Infrabel","28288","Namur - Antwerpen","< >","AUVELAIS","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2022,2022,46,47,"2022-11-12",44568.958333333336,"2022-11-13",44568.625,"1d","Continuous",null,"T","","Maintenance Z19. 51\r\nMini CTL \n ",28288]
["Infrabel","28289","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2022,2022,48,49,"2022-11-26",44568.25,"2022-11-28",44568.166666666664,"2d","Continuous",null,"T","","Renouvellement du PS 85.708 - WE CTL du samedi matin au lundi matin\r\n+ Maintenance Z15. 51\r\nP4+ \n ",28289]
["Infrabel","28760","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2022,2022,11,12,"2022-03-12",44568.25,"2022-03-14",44568.208333333336,"2d","Continuous",null,"T","","Traitement zone boueuse Bk 94.440 à Bk 94.780\r\nUPM: 279586 \nHKM à adapter",28760]
["Infrabel","28762","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,12,13,"2022-03-19",44568.25,"2022-03-21",44568.208333333336,"2d","Continuous",null,"T","","Traitement zone boueuse Bk 94.440 à Bk 94.780\r\nUPM: 279593 \nHKM à adapter",28762]
["Infrabel","28769","Lille - Charleroi","< >","LEUZE","TOURNAI",2022,2022,23,24,"2022-06-03",44568.996527777781,"2022-06-06",44568.194444444445,"3d","Continuous",null,"T","","Renouvellement du PN 76\r\nUPM 291292\r\n\r\nA mettre en conformité avec Colt FTY non inclus \nHKM à adapter\r\nInfo racc - CCB",28769]
["Infrabel","28770","Lille - Charleroi","< >","LEUZE","TOURNAI",2022,2022,25,25,"2022-06-13",44568.979166666664,"2022-06-18",44568.1875,"5d","Periodical",null,"T","","Renouvellement du PN 76\r\nBourrage de révision\r\nAsphaltage\r\nfinitions\r\nUPM 296701\r\nA mettre en conformité avec Colt FTY non inclus. \nNéant\r\nInfo racc - CCB",28770]
["Infrabel","28785","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,13,14,"2022-03-26",44568.25,"2022-03-28",44568.208333333336,"2d","Continuous",null,"T","","Traitement zone boueuse\r\nUPM: 279595 \nHKM à adapter",28785]
["Infrabel","28794","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,15,16,"2022-04-09",44568.25,"2022-04-11",44568.208333333336,"2d","Continuous",null,"T","","Traitement zone boueuse Bk 94.440 à Bk 94.780\r\nUPM: 279605 \nHKM à adapter",28794]
["Infrabel","28811","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,24,25,"2022-06-11",44568.25,"2022-06-13",44568.208333333336,"2d","Continuous",null,"T","","Traitement zone boueuse Bk 91.050 à Bk 91.130 VB\r\n280129 \n ",28811]
["Infrabel","28895","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,25,26,"2022-06-18",44568.25,"2022-06-20",44568.208333333336,"2d","Continuous",null,"T","","Traitement zone boueuse Bk 91.050 à Bk 91.130 VB \n ",28895]
["Infrabel","28896","Athus - Meuse",">","FLORENVILLE","BERTRIX",2022,2022,26,26,"2022-06-20",44568.333333333336,"2022-06-21",44568.666666666664,"1d","Periodical",null,"","ST","Traitement zone boueuse Bk 91.050 à Bk 91.130 VB\r\n280366 \n ",28896]
["Infrabel","28899","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2022,2022,26,27,"2022-06-25",44568.958333333336,"2022-06-26",44568.625,"1d","Continuous",null,"T","","Traitement zone boueuse Bk 91.050 à Bk 91.130 VB\r\n280310 \n ",28899]
["Infrabel","28909","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,32,35,"2022-08-06",44568.958333333336,"2022-08-21",44568.666666666664,"15d","Continuous",null,"","ST","traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \n ",28909]
["Infrabel","28910","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,35,36,"2022-08-27",44568.958333333336,"2022-08-29",44568.208333333336,"2d","Continuous",null,"","ST","traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",28910]
["Infrabel","28915","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,43,47,"2022-10-22",44568.958333333336,"2022-11-14",44568.208333333336,"23d","Continuous",null,"","ST","traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",28915]
["Infrabel","28916","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,47,48,"2022-11-19",44568.958333333336,"2022-11-20",44568.541666666664,"1d","Continuous",null,"T","","traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",28916]
["Infrabel","28923","Athus - Meuse",">","FLORENVILLE","BERTRIX",2022,2022,48,49,"2022-11-22",44568.333333333336,"2022-12-02",44568.666666666664,"10d","Periodical",null,"","ST","peignage de parois rocheuses\r\n+ visites le 22/11 \n ",28923]
["Infrabel","28955","Lille - Charleroi","< >","Y.LA SAMBRE","Y.NORD",2022,2022,16,17,"2022-04-11",44568.979166666664,"2022-04-18",44568.1875,"7d","Periodical",null,"T","","Renouvellement PS BK 54.263 Marchienne Est\r\nUPM 278595 \nHKM à adapter",28955]
["Infrabel","29026","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,18,19,"2022-04-29",44568.944444444445,"2022-05-02",44568.180555555555,"3d","Continuous",null,"","ST","Renouvellement PS BK 54.263 Marchienne Est\r\nUPM 278602 \nHKM à adapter",29026]
["Infrabel","29274","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2022,2022,24,25,"2022-06-11",44568.013888888891,"2022-06-13",44568.1875,"2d","Continuous",null,"T","","Renouvellement AS liaison 28 à Tilleur\r\n272856 \n ",29274]
["Infrabel","29276","Athus - Meuse","< >","Y.NEFFE","BEAURAING",2022,2022,44,45,"2022-10-29",44568.583333333336,"2022-10-31",44568.1875,"2d","Continuous",null,"T","","Traitement de boueux et entretiens d'appareils de voies (bourrage, nivellement,...) \n ",29276]
["Infrabel","29278","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2022,2022,34,37,"2022-08-20",44568.333333333336,"2022-09-05",44568.25,"16d","Continuous",null,"T","","Renouvellement des traverses avec train C75\r\nRenouvellement PI\r\n+ Renouvellement PS Rue combattant BK1.100 \nInfo Racc : Solvay inaccessible via L144, uniquement via L130/1",29278]
["Infrabel","29293","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,37,37,"2022-09-09",44568.333333333336,"2022-09-09",44568.666666666664,"0d","Periodical",null,"T","","Criblage du ballast \n ",29293]
["Infrabel","29295","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,41,41,"2022-10-07",44568.333333333336,"2022-10-07",44568.666666666664,"0d","Periodical",null,"T","","Criblage du ballast\r\nBourrage + tx finitions \n ",29295]
["Infrabel","29298","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,25,26,"2022-06-18",44568.25,"2022-06-20",44568.180555555555,"2d","Continuous",null,"T","","Criblage du ballast + rails/traverses dans tunnel Fidevoye\r\n278960 \nDétournement via L130A",29298]
["Infrabel","29302","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2022,2022,22,23,"2022-05-28",44568.291666666664,"2022-05-29",44568.666666666664,"1d","Continuous",null,"T","","Massification travaux entretien voies et signalisation\r\nUPM: 280221 \nHKM à adapter\r\nInfo Racc 72 : 1.L.L125/2 (Prayon)\r\nInfo Racc ??? : 1.L.L125/4 (Dumont-Wautier 1)\r\nInfo Racc 77 : 1.L.L125/5 (Dumont-Wautier 2)\r\nInfo Racc 78 : 1.L.L125/6 (Raffinerie Tirlemontoise)",29302]
["Infrabel","29363","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,36,38,"2022-09-01",44568.989583333336,"2022-09-16",44568.197916666664,"15d","Periodical",null,"","ST","Travaux préparatoire Grill coté LLN \n ",29363]
["Infrabel","29364","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,39,39,"2022-09-19",44568.989583333336,"2022-09-24",44568.197916666664,"5d","Periodical",null,"","ST","Travaux préparatoires  CTL Grill coté LLN \n ",29364]
["Infrabel","29368","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2022,2022,43,45,"2022-10-17",44568.989583333336,"2022-10-30",44568.197916666664,"13d","Periodical",null,"","ST","Travaux préparatoires  CTL Grill coté LLN \n ",29368]
["Infrabel","29443","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET",2022,2022,35,36,"2022-08-27",44568.9375,"2022-08-28",44568.916666666664,"1d","Continuous",null,"","ST","Maintenance Z17. 51 (P4+)\r\n+ Impact faisceaux Chatelet \nFaisceaux B, D, K inaccessibles",29443]
["Infrabel","29453","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2023,2023,5,6,"2023-02-04",44568.25,"2023-02-05",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z2. 51  P4+ \n ",29453]
["Infrabel","29454","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2022,2022,16,16,"2022-04-11",44568.916666666664,"2022-04-16",44568.173611111109,"5d","Periodical",null,"T","","Maintenance Z2. 51    P3 HKV \nHKM à adapter",29454]
["Infrabel","29459","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2022,2022,44,44,"2022-10-24",44568.881944444445,"2022-10-29",44568.173611111109,"5d","Periodical",null,"T","","Maintenance Z2. 51    P3 HKV\r\n+ Renouvellement des tabliers du pont BK 125.363 - finitions \n ",29459]
["Infrabel","29461","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2023,2023,6,6,"2023-02-06",44568.881944444445,"2023-02-11",44568.173611111109,"5d","Periodical",null,"T","","Maintenance Z2. 51    P3 HKV \n ",29461]
["Infrabel","29749","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER-GARAGE",2022,2022,32,33,"2022-08-05",44568.979166666664,"2022-08-08",44568.1875,"3d","Continuous",null,"T","","Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre \nHKM détourné via :\r\n- Athus-Meuse - L161\r\n- L144 - L130 - L130A",29749]
["Infrabel","29920","Erquelinnes - Montzen","< >","HUY","JAVA",2022,2022,18,19,"2022-04-29",44568.993055555555,"2022-05-02",44568.208333333336,"3d","Continuous",null,"T","","Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte\r\nRenouvellement des quais de Bas-Oha\r\nUPM: 272540 \nHKM à adapter\r\nInfo Racc 78 : 1.L.L125/6 (Raffinerie Tirlemontoise)",29920]
["Infrabel","29933","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,9,11,"2022-02-26",44568.25,"2022-03-07",44568.208333333336,"9d","Continuous",null,"T","","Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36\r\n+ Renouvellement des quais VA de Florival\r\nElargissement des pistes de circulation et pose de passerelles\r\n+ Entretien massi \nWE 5-6/03/22 - L96 fermée -> détournements via L130A ou via L90C-90",29933]
["Infrabel","29935","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,11,11,"2022-03-07",44568.972222222219,"2022-03-11",44568.222222222219,"4d","Periodical",null,"","ST","Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36\r\nUPM: 277299\r\n\r\nART entre Basse-Wavre (bk 22490) et Bierges (bk 24000) VA+ VB réduit à 40km/h. Mise en vigueur le 07/03 fin p \nHKM à adapter",29935]
["Infrabel","29936","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,12,12,"2022-03-14",44568.972222222219,"2022-03-18",44568.222222222219,"4d","Periodical",null,"","ST","Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36\r\nUPM: 277901 \nHKM à adapter",29936]
["Infrabel","29937","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,13,13,"2022-03-21",44568.972222222219,"2022-03-25",44568.222222222219,"4d","Periodical",null,"","ST","Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36\r\nUPM: 278066 \nHKM à adapter",29937]
["Infrabel","29938","Namur - Antwerpen",">","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,14,14,"2022-03-28",44568.972222222219,"2022-04-01",44568.222222222219,"4d","Periodical",null,"","ST","Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36\r\nUPM: 278086 \nHKM à adapter",29938]
["Infrabel","29949","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,37,37,"2022-09-09",44568.333333333336,"2022-09-09",44568.666666666664,"0d","Periodical",null,"T","","Assainissement de la voie A \n ",29949]
["Infrabel","29953","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,41,42,"2022-10-08",44568.583333333336,"2022-10-10",44568.166666666664,"2d","Continuous",null,"T","","Assainissement de la voie A \n ",29953]
["Infrabel","29955","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,42,43,"2022-10-15",44568.583333333336,"2022-10-17",44568.166666666664,"2d","Continuous",null,"T","","Assainissement de la voie A \n ",29955]
["Infrabel","29978","Athus - Meuse","< >","Y.NEFFE","HOUYET",2022,2022,9,10,"2022-02-26",44568.25,"2022-02-28",44568.208333333336,"2d","Continuous",null,"T","","Renouvellement de traverses à la grue dans 2 tunnels entre BK 8900 et 12100\r\nUPM: 278989 \nHKM à adapter",29978]
["Infrabel","30293","Lille - Antwerpen","< >","Y.MELSELE","ANTWERPEN-BERCHEM",2022,2022,9,10,"2022-02-26",44568.25,"2022-02-28",44568.166666666664,"2d","Continuous",null,"T","","Massificatieprogramma lijn 59\r\n+ Kennedytunnel (Cornelis Bram)\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) -> bijkomende isolatoren te plaatsen ( Deraeve S. )\r\nTCR 277976 \nHKM om te leiden.",30293]
["Infrabel","30295","Lille - Antwerpen","< >","Y.MELSELE","ANTWERPEN-BERCHEM",2022,2022,10,11,"2022-03-05",44568.25,"2022-03-07",44568.166666666664,"2d","Continuous",null,"T","","Massificatieprogramma lijn 59\r\n+ Kennedytunnel (Cornelis Bram)\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) - Deraeve Sam\r\nTCR 278243 \nHKM om te leiden.",30295]
["Infrabel","30303","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,14,15,"2022-04-02",44568.041666666664,"2022-04-04",44568.1875,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278246 \nVia Montzen",30303]
["Infrabel","30305","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,16,17,"2022-04-16",44568.041666666664,"2022-04-19",44568.166666666664,"3d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\n\r\n+ Paasmaandag\r\nR-278249 \nVia Montzen",30305]
["Infrabel","30306","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,17,18,"2022-04-23",44568.041666666664,"2022-04-25",44568.1875,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278251 \nVia Montzen",30306]
["Infrabel","30308","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,18,19,"2022-04-30",44568.041666666664,"2022-05-02",44568.1875,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278253 \nVia Montzen",30308]
["Infrabel","30311","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,41,42,"2022-10-08",44568.041666666664,"2022-10-10",44568.166666666664,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278262 \nVia Montzen",30311]
["Infrabel","30312","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,43,44,"2022-10-22",44568.041666666664,"2022-10-24",44568.1875,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278264 \nVia Montzen",30312]
["Infrabel","30313","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,44,45,"2022-10-29",44568.041666666664,"2022-10-31",44568.1875,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278265 \nVia Montzen",30313]
["Infrabel","30314","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,45,46,"2022-11-05",44568.041666666664,"2022-11-07",44568.166666666664,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278268 \nVia Montzen",30314]
["Infrabel","30315","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,42,43,"2022-10-15",44568.041666666664,"2022-10-17",44568.166666666664,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278269 \nVia Montzen",30315]
["Infrabel","30316","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,48,49,"2022-11-26",44568.041666666664,"2022-11-28",44568.1875,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278270 \nVia Montzen",30316]
["Infrabel","30317","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,49,50,"2022-12-03",44568.041666666664,"2022-12-05",44568.166666666664,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278271 \nVia Montzen",30317]
["Infrabel","30318","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,40,41,"2022-10-01",44568.041666666664,"2022-10-03",44568.1875,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278272 \nVia Montzen",30318]
["Infrabel","30507","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2022,2022,34,35,"2022-08-20",44568.583333333336,"2022-08-22",44568.25,"2d","Continuous",null,"T","","Réélectrification L. 124+L. 124A \r\nCTL L124A\r\n+ Préparation travaux ES en vue des VAE Manage \nMonceau inaccessible via L124A",30507]
["Infrabel","30557","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2022,2022,26,29,"2022-06-25",44568.25,"2022-07-11",44568.208333333336,"16d","Continuous",null,"T","","Pose seconds tabliers ponts 10 et 11\r\nRenouvellement des tabliers métalliques L130A 125.363\r\n+ Massification maintenance AI51\r\nUPM 278860 \nHKM à adapter\r\nVia L117 - 124 - 130 - 90C - 96",30557]
["Infrabel","30563","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,41,42,"2022-10-08",44568.041666666664,"2022-10-10",44568.166666666664,"2d","Continuous",null,"T","","project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",30563]
["Infrabel","30564","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,43,44,"2022-10-22",44568.041666666664,"2022-10-24",44568.166666666664,"2d","Continuous",null,"T","","project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",30564]
["Infrabel","30565","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,44,45,"2022-10-29",44568.041666666664,"2022-10-31",44568.166666666664,"2d","Continuous",null,"T","","project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",30565]
["Infrabel","30566","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,45,46,"2022-11-05",44568.041666666664,"2022-11-07",44568.166666666664,"2d","Continuous",null,"T","","project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",30566]
["Infrabel","30568","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,48,49,"2022-11-26",44568.041666666664,"2022-11-28",44568.166666666664,"2d","Continuous",null,"T","","project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",30568]
["Infrabel","30569","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2022,2022,49,50,"2022-12-03",44568.041666666664,"2022-12-05",44568.166666666664,"2d","Continuous",null,"T","","project Oude Landen : TLO's:\r\n- afbraak verbindingspoor 2\r\n- aanleg noodzakelijke tijdelijke verbinding naar bundel Luchtbal\r\n- aanpassingswerken BVL L12 van voor station Noorderdokken tot na St Mariaburg\r\n- schuiven koker onder de L12 \n",30569]
["Infrabel","30753","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2022,2022,42,42,"2022-10-11",44568.083333333336,"2022-10-15",44568.125,"4d","Periodical",null,"T","","Travaux de préparation pour renouvellement chape d'étanchéité PI km 106,769\r\n+ Travaux de préparation pour le renouvellement des tabliers du pont BK 125.363 \n ",30753]
["Infrabel","30778","Lille - Charleroi","< >","MONS","QUEVY",2022,2022,8,9,"2022-02-19",44568.25,"2022-02-20",44568.996527777781,"1d","Continuous",null,"T","","Mise HS pour finitions chantier P 93 + entreiten\r\nUPM 278330 \nHKM à adapter \r\nVia L130A",30778]
["Infrabel","30780","Namur - Antwerpen","< >","TAMINES","CHATELET",2022,2022,14,14,"2022-03-28",44568.944444444445,"2022-04-01",44568.208333333336,"4d","Periodical",null,"T","","Aménagement Le Campinaire - Phase 6 \r\n+ Peinture pont métallique L130…83.413.\r\n+ Diagno 2022: L130 Partie 2 \r\n+ Buitenwerken ETCS (Mathilde Wallez)\r\nUPM 286276 \nHKM à adapter\r\nVia L117 - 124A - 130 - 140 147 - 96",30780]
["Infrabel","30781","Namur - Antwerpen","< >","TAMINES","CHATELET",2022,2022,14,15,"2022-04-01",44568.989583333336,"2022-04-04",44568.1875,"3d","Continuous",null,"T","","Aménagement Le Campinaire - Phase 7 : Week-end n°2\r\n+ Peinture pont métallique\r\nUPM 288856 \nHKM à adapter\r\nVia L117 - 124A - 130 - 140 - 147 - 96",30781]
["Infrabel","30783","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,20,20,"2022-05-09",44568.947916666664,"2022-05-14",44568.208333333336,"5d","Periodical",null,"T","","Aménagement Le Campinaire - Phase 10 :\r\nBourrage révision, contrainte, pose caniveaux pistes, finitions chantier….\r\n+ Diagno 2022: L130 Partie 2 \r\n+ Buitenwerken ETCS\r\nUPM 286302 \nHKM à adapter\r\nVia 117 - 124 - 130 - 140 - 147",30783]
["Infrabel","30785","Namur - Antwerpen","< >","TAMINES","CHATELET",2022,2022,15,15,"2022-04-04",44568.965277777781,"2022-04-09",44568.208333333336,"5d","Periodical",null,"T","","Aménagement Le Campinaire - Phase 8\r\n+ Peinture pont métallique L130…83.413.\r\n+ Buitenwerken ETCS (Mathilde Wallez)\r\nUPM 288861 \nHKM à adapter\r\nVia L124 - 130 - 140 - 144 - 147",30785]
["Infrabel","30793","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,18,19,"2022-04-30",44568.020833333336,"2022-05-02",44568.180555555555,"2d","Continuous",null,"T","","Maintenance AI52\r\n+ Travaux OA\r\nUPM 294968 \nHKM à adapter",30793]
["Infrabel","30845","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,25,25,"2022-06-13",44568.923611111109,"2022-06-18",44568.166666666664,"5d","Periodical",null,"T","","Pose seconds tabliers ponts 10 et 11\r\nTravaux préparatoires\r\nUPM 278785 \nHKM à adapter\r\nVia L117 - 124 - 96",30845]
["Infrabel","30846","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,16,16,"2022-04-12",44568.083333333336,"2022-04-16",44568.125,"4d","Periodical",null,"T","","Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november.\r\n294524 \nNéant",30846]
["Infrabel","30847","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,23,23,"2022-05-31",44568.083333333336,"2022-06-04",44568.125,"4d","Periodical",null,"T","","Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",30847]
["Infrabel","30849","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,23,23,"2022-05-30",44568.923611111109,"2022-06-04",44568.166666666664,"5d","Periodical",null,"T","","Pose seconds tabliers ponts 10 et 11\r\nTravaux préparatoires\r\nUPM 278776 \nHKM à adapter",30849]
["Infrabel","30851","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,37,37,"2022-09-04",44568.923611111109,"2022-09-09",44568.166666666664,"5d","Periodical",null,"T","","Pose seconds tabliers ponts 10 et 11\r\nTravaux de finition \n ",30851]
["Infrabel","30853","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,44,44,"2022-10-25",44568.083333333336,"2022-10-29",44568.125,"4d","Periodical",null,"T","","Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",30853]
["Infrabel","30855","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,19,19,"2022-05-02",44568.947916666664,"2022-05-07",44568.208333333336,"5d","Periodical",null,"T","","Aménagement Le Campinaire - Phase 10 \r\nBourrage révision, contrainte, pose caniveaux pistes, finitions chantier….\r\n+ Peinture pont métallique L130…83.413. Phase de déplacement du caisson.\r\n+ Buitenwerken ETCS (Mathilde Wallez)\r\nUPM 289174\r\nART 2' \nHKM à adapter\r\nVia L117 - 124 - 130  - 130C - 140 - 147 - 94 - 96",30855]
["Infrabel","30858","Lille - Charleroi","< >","BRUGELETTE","ATH",2022,2022,21,22,"2022-05-20",44568.9375,"2022-05-23",44568.215277777781,"3d","Continuous",null,"T","","Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nUPM 291740 \nHKM à adapter\r\nVia 117 - 124 - 130A - 94 - 130",30858]
["Infrabel","30859","Lille - Charleroi","< >","BRUGELETTE","ATH",2022,2022,20,21,"2022-05-13",44568.9375,"2022-05-16",44568.215277777781,"3d","Continuous",null,"T","","Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nTravaux de renouvellement des chapes d'étanchéité des PI 61.597 et 64.126 + construction de passerelles au droit du PI 61.597\r\nUPM 291704 \nHKM à adapter\r\nVia 117 - 124 - 130A - 94 - 90 - 96",30859]
["Infrabel","30860","Lille - Charleroi","< >","BRUGELETTE","ATH",2022,2022,19,20,"2022-05-06",44568.9375,"2022-05-09",44568.215277777781,"3d","Continuous",null,"T","","Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nUPM 291700 \nHKM à adapter\r\nVia 117 - 124 - 130A - 94",30860]
["Infrabel","30861","Lille - Charleroi","< >","BRUGELETTE","ATH",2022,2022,18,19,"2022-04-29",44568.934027777781,"2022-05-02",44568.215277777781,"3d","Continuous",null,"T","","Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nUPM 291690 \nHKM à adapter\r\nVia 117 - 124 - 130A - 90 - 94 - 96",30861]
["Infrabel","30866","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,38,39,"2022-09-16",44568.923611111109,"2022-09-19",44568.215277777781,"3d","Continuous",null,"T","","Renouvellement de traverses entre Ath et Lens P93 \n ",30866]
["Infrabel","30891","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,11,12,"2022-03-11",44568.979166666664,"2022-03-14",44568.208333333336,"3d","Continuous",null,"T","","Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36\r\n+ Renouvellement des quais VA de Florival\r\nElargissement des pistes de circulation et pose de passerelles\r\nUPM: 278022 \nHKM à adapter",30891]
["Infrabel","30892","Namur - Antwerpen","< >","OTTIGNIES","SINT-JORIS-WEERT",2022,2022,13,14,"2022-03-25",44568.979166666664,"2022-03-28",44568.208333333336,"3d","Continuous",null,"T","","Renouvellement des appareils 66AR, 66BR, 67R, 68R, 69AR, 69BR à Wavre\r\nRenouvellement des quais\r\nRenouvellement des PN 34 et 36\r\n+ Renouvellement des quais VA de Florival\r\nElargissement des pistes de circulation et pose de passerelles\r\nUPM: 278084 \nHKM à adapter",30892]
["Infrabel","30893","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER-GARAGE",2022,2022,33,34,"2022-08-12",44568.979166666664,"2022-08-16",44568.1875,"4d","Continuous",null,"T","","Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre \nHKM détourné via :\r\n- Athus-Meuse - L161\r\n- L144 - L130 - L130A",30893]
["Infrabel","30894","Namur - Antwerpen","< >","AUVELAIS","NAMUR",2022,2022,34,35,"2022-08-20",44568.958333333336,"2022-08-21",44568.625,"1d","Continuous",null,"T","","Renouvellement des TJD 12BQ/13AQ et 13BQ/14AQ à Jemeppe-sur-Sambre\r\nMini CTL\r\n+ visites \n ",30894]
["Infrabel","30901","Athus - Meuse","< >","NAMUR","YVOIR",2022,2022,27,28,"2022-07-02",44568.25,"2022-07-04",44568.180555555555,"2d","Continuous",null,"T","","Criblage du ballast\r\n + Renouvellement rails dans les PN , entretien AS en gare de Jambes , traitement zone boueuse\r\n278963 \n ",30901]
["Infrabel","30902","Athus - Meuse","< >","NAMUR","YVOIR",2022,2022,28,29,"2022-07-09",44568.25,"2022-07-11",44568.180555555555,"2d","Continuous",null,"T","","Criblage du ballast + Renouvel rails dans les PN , entretien AS en gare de Jambes , traitement zone boueuse \n ",30902]
["Infrabel","30903","Athus - Meuse",">","VIRTON","AUBANGE",2022,2022,37,40,"2022-09-09",44568.333333333336,"2022-09-26",44568.666666666664,"17d","Continuous",null,"","ST","Criblage du ballast \nINFO RACC",30903]
["Infrabel","30904","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,42,42,"2022-10-14",44568.333333333336,"2022-10-14",44568.666666666664,"0d","Periodical",null,"T","","Criblage du ballast\r\nBourrage + tx finitions \n ",30904]
["Infrabel","30905","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,43,43,"2022-10-17",44568.333333333336,"2022-10-17",44568.666666666664,"0d","Periodical",null,"T","","Criblage du ballast\r\nBourrage + tx finitions \n ",30905]
["Infrabel","30906","Athus - Meuse","< >","ANSEREMME","HOUYET",2022,2022,10,11,"2022-03-05",44568.25,"2022-03-07",44568.208333333336,"2d","Continuous",null,"T","","Renouvellement de traverses à la grue dans 3 tunnels entre BK 8900 et 12100\r\nUPM: 278999 \nHKM à adapter",30906]
["Infrabel","30907","Athus - Meuse","< >","ANSEREMME","HOUYET",2022,2022,11,12,"2022-03-12",44568.25,"2022-03-14",44568.208333333336,"2d","Continuous",null,"T","","Traitement de boueux et entretiens d'appareils de voies (bourrage, nivellement,...)\r\nUPM: 279001 \nHKM à adapter",30907]
["Infrabel","30908","Athus - Meuse",">","GEDINNE","PALISEUL",2022,2022,37,40,"2022-09-09",44568.333333333336,"2022-09-26",44568.666666666664,"17d","Continuous",null,"","ST","Assainissement de la voie A\r\nVisites de voie \nPriorité aux relations voyageurs durant les heures de pointe",30908]
["Infrabel","30913","Erquelinnes - Montzen","< >","HUY","JAVA",2022,2022,19,20,"2022-05-06",44568.993055555555,"2022-05-09",44568.208333333336,"3d","Continuous",null,"T","","Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte\r\nRenouvellement des quais de Bas-Oha\r\nUPM: 272541 \nHKM à adapter\r\nInfo Racc 78 : 1.L.L125/6 (Raffinerie Tirlemontoise)",30913]
["Infrabel","30914","Erquelinnes - Montzen","< >","HUY","JAVA",2022,2022,21,21,"2022-05-16",44568.993055555555,"2022-05-21",44568.208333333336,"5d","Periodical",null,"T","","Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte\r\nRenouvellement des quais de Bas-Oha\r\nBourrage + tx finition\r\nUPM: 272501 \nHKM à adapter\r\nInfo Racc 78 : 1.L.L125/6 (Raffinerie Tirlemontoise)",30914]
["Infrabel","30915","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,38,39,"2022-09-16",44568.986111111109,"2022-09-19",44568.208333333336,"3d","Continuous",null,"T","","Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD\r\nMassifié avec travaux :Marche-les-Dames Phase3 : Assainissement voie B (part 2/2) + Drainage; Renouvellement des AS 13AN/13BN; Remi \n ",30915]
["Infrabel","30916","Erquelinnes - Montzen","< >","ANDENNE","NAMUR",2022,2022,39,40,"2022-09-23",44568.986111111109,"2022-09-26",44568.208333333336,"3d","Continuous",null,"T","","Massification travaux OA tronçon Andenne - Namur - Renouvellement quais PANG + Renouvellement AS 13AN, 13BN, 14AN de MLD\r\n+ Marche-les-Dames Phase 4.2: Pose des bordures de quais voie B prioritaire; Fin assainissement voie A (en fonction des travaux aux \n ",30916]
["Infrabel","31304","Lille - Charleroi","< >","LUTTRE","ROUX",2022,2023,50,5,"2022-12-05",44568.291666666664,"2023-01-29",44568.666666666664,"55d","Continuous",null,"T","","Renouvellement du ballast L124A (C75) \n ",31304]
["Infrabel","31675","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","Y.DRIEHOEKSTRAAT",2022,2022,38,39,"2022-09-17",44568.25,"2022-09-19",44568.166666666664,"2d","Continuous",null,"T","","TLO-wknds : \r\n- afbraak verbindingspoor 2\r\n- inkorten perrons Noorderdokken\r\n- aanleg tijdelijke werfoverweg\r\n- plaatsen L-profielen langs L27A ter bescherming van werfverkeer\r\n- aanleg werkspoor\r\n\r\nde werken in op L27A mogen maar om 06:00 beginnen wege \n ",31675]
["Infrabel","31685","Lille - Charleroi","< >","LOT","HALLE",2022,2022,19,19,"2022-05-03",44568.027777777781,"2022-05-07",44568.197916666664,"4d","Periodical",null,"T","","Vernieuwen BVL L96 + aw's L96N sp B.\r\nSp AL96 tss H-N1 en NX-D1 / BL96 tss GX-N1 en aw 43BE en zonder 21888. \n ",31685]
["Infrabel","31686","Lille - Charleroi","< >","LOT","HALLE",2022,2022,24,24,"2022-06-08",44568.027777777781,"2022-06-11",44568.194444444445,"3d","Periodical",null,"T","","Vernieuwen BVL L96 + aw's L96N sp B\r\nSp A L96 tss H-N1 en NX-D1 / BL96 tss GX-N1 en O-D1 en zonder 21888. \n ",31686]
["Infrabel","31902","Namur - Antwerpen",">","Y.HOLLAND","Y.SCHIJN",2022,2022,34,34,"2022-08-14",44568.041666666664,"2022-08-16",44568.166666666664,"2d","Continuous",null,"","ST","Project Oude Landen CR 068 tot Y Schijn \nVanuit Nederland met  frontwissel in bundel Q naar de haven",31902]
["Infrabel","31911","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2022,2022,47,48,"2022-11-19",44568.875,"2022-11-21",44568.208333333336,"2d","Continuous",null,"T","","Travaux SNCF CHA22_0022621\r\n76 Gare de Tourcoing: RAV U50 BOIS : Bt 102, Bt 107, Bt 108, Bt 109 - RAV UIC 60 Béton\r\n+ P93 - renouvellement\r\n+ 385335 PLP Massification travaux Infrabel L75 \n ",31911]
["Infrabel","32061","Athus - Meuse",">","BERTRIX","FLORENVILLE",2022,2022,19,20,"2022-05-02",44568.333333333336,"2022-05-09",44568.208333333336,"7d","Continuous",null,"","ST","Réglages des contraintes des rails (LRS) entre km 82050-89480\r\nFinition chantier 2021\r\n275441 \n ",32061]
["Infrabel","33011","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2022,2022,10,10,"2022-02-28",44568.041666666664,"2022-03-05",44568.208333333336,"5d","Continuous",null,"T","","Vernieuwen wissels Y.Parkbrug (in combinatie met langdurige buitendienststelling tussen Ottignie en Sint-Joris-Weert).\r\nStation Heverlee (B-ST): Vernieuwing perronluifel (Annick Locquet) + BVL\r\nTCR 278168 \nOp zesmaandelijkse van 12/12/2019 vragen goederenoperatoren de lijnen 75 en 59 bijkomend open te houden.\r\nHKM om te leiden.",33011]
["Infrabel","33120","Erquelinnes - Montzen","< >","LOBBES-GARAGE","ERQUELINNES",2022,2022,43,43,"2022-10-18",44568.083333333336,"2022-10-22",44568.125,"4d","Periodical",null,"T","","Renouvellement des tabliers du pont BK 125.363\r\nNuits finitions \n ",33120]
["Infrabel","33885","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES",2022,2022,8,8,"2022-02-14",44568.923611111109,"2022-02-19",44568.166666666664,"5d","Periodical",null,"T","","OA - Rnvlt chapes PI 120,998, PI 121,475, 106,769 et PS 108,062 ;\r\n+ AI51 - Maintenance\r\nUPM 278727 \nHKM à adapter",33885]
["Infrabel","33886","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES",2022,2022,9,9,"2022-02-21",44568.923611111109,"2022-02-26",44568.166666666664,"5d","Periodical",null,"T","","OA - Rnvlt chapes PI 120,998, PI 121,475, 106,769 et PS 108,062 ;\r\n+ AI51 - Maintenance\r\nUPM 278736 \nHKM à adapter",33886]
["Infrabel","33887","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES",2022,2022,11,11,"2022-03-07",44568.923611111109,"2022-03-12",44568.166666666664,"5d","Periodical",null,"T","","OA - Rnvlt chapes PI 120,998, PI 121,475, 106,769 et PS 108,062 ;\r\n+ AI51 - Maintenance\r\nUPM 278771 \nHKM à adapter",33887]
["Infrabel","33931","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,32,33,"2022-08-06",44568.958333333336,"2022-08-07",44568.25,"1d","Periodical",null,"T","","traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",33931]
["Infrabel","33932","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,34,35,"2022-08-20",44568.958333333336,"2022-08-21",44568.25,"1d","Periodical",null,"T","","traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",33932]
["Infrabel","33944","Athus - Meuse","< >","HOUYET","BEAURAING",2022,2022,20,21,"2022-05-14",44568.958333333336,"2022-05-15",44568.625,"1d","Continuous",null,"T","","Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing\r\nUPM: 274920 \nNéant",33944]
["Infrabel","33945","Athus - Meuse","< >","Y.NEFFE","BEAURAING",2022,2022,22,23,"2022-05-28",44568.958333333336,"2022-05-29",44568.625,"1d","Continuous",null,"T","","Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing\r\n+ Visites/Maintenance\r\nUPM: 274921 \nNéant",33945]
["Infrabel","33946","Athus - Meuse","< >","HOUYET","BEAURAING",2022,2022,18,19,"2022-04-30",44568.958333333336,"2022-05-01",44568.625,"1d","Continuous",null,"T","","Renouvellement des murs de soutènement de Houyet - sécurisation des parois rocheuses de Houyet - mise au gabarit des pistes du tronçon Houyet - Beauraing\r\nMassification de travaux sur le tronçon Houyet Beauraing\r\nUPM: 274919 \nHKM à adapter",33946]
["Infrabel","33948","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,44,45,"2022-10-29",44568.958333333336,"2022-10-30",44568.666666666664,"1d","Continuous",null,"T","","traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",33948]
["Infrabel","33949","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,41,42,"2022-10-08",44568.958333333336,"2022-10-09",44568.666666666664,"1d","Continuous",null,"T","","traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",33949]
["Infrabel","33950","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2022,2022,42,43,"2022-10-15",44568.958333333336,"2022-10-16",44568.666666666664,"1d","Continuous",null,"T","","traitement de zone boueuse, voie B, entre Bk 115.280 à Bk 115.500 \n ",33950]
["Infrabel","34344","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2023,2023,14,24,"2023-04-03",44568.003472222219,"2023-06-12",44568.1875,"70d","Continuous",null,"T","","L12 Engelselei – waterdichte rokken vervangen \n ",34344]
["Infrabel","34426","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2022,2022,3,4,"2022-01-15",44568.958333333336,"2022-01-16",44568.625,"1d","Continuous",null,"T","","Maintenance Z15. 51\r\nMini CTL\r\nUPM 286342 \n ",34426]
["Infrabel","35120","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,38,38,"2022-09-16",44568.25,"2022-09-16",44568.666666666664,"0d","Periodical",null,"T","","Criblage du ballast \n ",35120]
["Infrabel","35121","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,39,39,"2022-09-23",44568.333333333336,"2022-09-23",44568.666666666664,"0d","Periodical",null,"T","","Criblage du ballast \n ",35121]
["Infrabel","35122","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,43,43,"2022-10-21",44568.333333333336,"2022-10-21",44568.666666666664,"0d","Periodical",null,"T","","Criblage du ballast\r\nBourrage + tx finitions \n ",35122]
["Infrabel","35124","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,44,44,"2022-10-24",44568.333333333336,"2022-10-24",44568.666666666664,"0d","Periodical",null,"T","","Criblage du ballast\r\nBourrage + tx finitions \n ",35124]
["Infrabel","35125","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,44,44,"2022-10-28",44568.333333333336,"2022-10-28",44568.666666666664,"0d","Periodical",null,"T","","Criblage du ballast\r\nBourrage + tx finitions \n ",35125]
["Infrabel","35126","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,37,38,"2022-09-10",44568.25,"2022-09-12",44568.666666666664,"2d","Continuous",null,"T","","Criblage du ballast \n ",35126]
["Infrabel","35127","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,38,39,"2022-09-17",44568.25,"2022-09-19",44568.666666666664,"2d","Continuous",null,"T","","Criblage du ballast \n ",35127]
["Infrabel","35128","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,39,40,"2022-09-24",44568.25,"2022-09-26",44568.666666666664,"2d","Continuous",null,"T","","Criblage du ballast \n ",35128]
["Infrabel","35130","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,41,42,"2022-10-08",44568.25,"2022-10-10",44568.666666666664,"2d","Continuous",null,"T","","Criblage du ballast\r\nBourrage + tx finitions \n ",35130]
["Infrabel","35131","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,42,43,"2022-10-15",44568.583333333336,"2022-10-17",44568.166666666664,"2d","Continuous",null,"T","","Criblage du ballast\r\nBourrage + tx finitions \n ",35131]
["Infrabel","35132","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,43,44,"2022-10-22",44568.583333333336,"2022-10-24",44568.166666666664,"2d","Continuous",null,"T","","Criblage du ballast\r\nBourrage + tx finitions \n ",35132]
["Infrabel","35133","Athus - Meuse","< >","VIRTON","AUBANGE",2022,2022,44,45,"2022-10-29",44568.583333333336,"2022-10-31",44568.166666666664,"2d","Continuous",null,"T","","Criblage du ballast\r\nBourrage + tx finitions\r\nTrapèze de Signeulx : travaux Signalling (MES) \n ",35133]
["Infrabel","35134","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,37,38,"2022-09-10",44568.25,"2022-09-12",44568.666666666664,"2d","Continuous",null,"T","","Assainissement de la voie A \n ",35134]
["Infrabel","35135","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,38,38,"2022-09-16",44568.333333333336,"2022-09-16",44568.666666666664,"0d","Periodical",null,"T","","Assainissement de la voie A \n ",35135]
["Infrabel","35136","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,38,39,"2022-09-17",44568.25,"2022-09-19",44568.666666666664,"2d","Continuous",null,"T","","Assainissement de la voie A \n ",35136]
["Infrabel","35137","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,39,39,"2022-09-23",44568.333333333336,"2022-09-23",44568.666666666664,"0d","Periodical",null,"T","","Assainissement de la voie A \n ",35137]
["Infrabel","35138","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,39,40,"2022-09-24",44568.25,"2022-09-26",44568.666666666664,"2d","Continuous",null,"T","","Assainissement de la voie A \n ",35138]
["Infrabel","35139","Athus - Meuse","< >","GEDINNE","PALISEUL",2022,2022,43,44,"2022-10-22",44568.583333333336,"2022-10-24",44568.166666666664,"2d","Continuous",null,"T","","Assainissement de la voie A \n ",35139]
["Infrabel","35872","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","HALANZY",2022,2022,48,49,"2022-11-26",44568.333333333336,"2022-11-27",44568.666666666664,"1d","Continuous",null,"T","","Mise en service EBP-PLP nouveaux aiguillages gare de Virton et rework ETCS.\r\n+ visites Virton/Halanzy \n ",35872]
["Infrabel","36087","Erquelinnes - Montzen",">","BRESSOUX","VISE",2022,2022,37,40,"2022-09-05",44568.291666666664,"2022-09-25",44568.583333333336,"20d","Continuous",null,"","ST","Entretien OA + sécurisation pistes \n ",36087]
["Infrabel","36089","Erquelinnes - Montzen",">","BRESSOUX","VISE",2022,2022,40,43,"2022-09-26",44568.5,"2022-10-16",44568.916666666664,"20d","Continuous",null,"","ST","Entretien OA\r\n+ Visites 27/09 \n ",36089]
["Infrabel","37623","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2022,2022,13,14,"2022-03-26",44568.25,"2022-03-27",44568.75,"1d","Continuous",null,"T","","Spanningsregeling, herziening, ...: Vernieuwen wissels Y.Parkbrug\r\nStation Heverlee (B-ST): Vernieuwing perronluifel (Annick Locquet)\r\nR-278366 \nHKM om te leiden.",37623]
["Infrabel","37677","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN",2022,2022,19,20,"2022-05-07",44568.041666666664,"2022-05-09",44568.1875,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278461 \nVia Montzen",37677]
["Infrabel","37678","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,12,13,"2022-03-19",44568.041666666664,"2022-03-21",44568.1875,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nTCR 278464 \nVia Montzen\r\nIn combinatie met TLO lijn 35. Zo gepland wegens lijn 12 niet verenigbaar met langdurige TLO op lijn 24 Duitse net (vervangen brug).",37678]
["Infrabel","37679","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2022,2022,13,14,"2022-03-26",44568.041666666664,"2022-03-28",44568.1875,"2d","Continuous",null,"T","","P93 (dwarsliggers) + C75 (ziftwerf)\r\nRailvernieuwing spoor A Kapellen - Kalmthout\r\nR-278580 \nVia Montzen\r\nIn combinatie met TLO lijn 35. Zo gepland wegens lijn 12 niet verenigbaar met langdurige TLO op lijn 24 Duitse net (vervangen brug).",37679]
["Infrabel","37805","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,22,23,"2022-05-28",44568.958333333336,"2022-05-29",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Signeulx\r\nUPM: 275981 \nNéant",37805]
["Infrabel","37877","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2023,2023,16,17,"2023-04-22",44568.986111111109,"2023-04-23",44568.618055555555,"1d","Continuous",null,"T","","Mini CTL pour maintenance globale  L130  + L130/1 + L144 \n ",37877]
["Infrabel","37878","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2023,2023,7,8,"2023-02-18",44568.986111111109,"2023-02-19",44568.618055555555,"1d","Continuous",null,"T","","Mini CTL pour maintenance globale  L130  + L130/1 + L144 \n ",37878]
["Infrabel","37879","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2023,2023,31,32,"2023-08-05",44568.986111111109,"2023-08-06",44568.618055555555,"1d","Continuous",null,"T","","Mini CTL pour maintenance globale  L130  + L130/1 + L144 \n ",37879]
["Infrabel","37880","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2023,2023,46,47,"2023-11-18",44568.986111111109,"2023-11-19",44568.618055555555,"1d","Continuous",null,"T","","Mini CTL pour maintenance globale  L130  + L130/1 + L144 \n ",37880]
["Infrabel","38052","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2023,2023,47,48,"2023-11-25",44568.25,"2023-11-26",44568.916666666664,"1d","Continuous",null,"T","","Entretien des PN + maintenance massifiée + Travaux ES \n ",38052]
["Infrabel","38219","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","ERQUELINNES",2022,2022,6,6,"2022-01-31",44568.958333333336,"2022-02-05",44568.208333333336,"5d","Periodical",null,"T","","Travaux SNCF\r\nCHA22_0023253 \n ",38219]
["Infrabel","38298","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON",2023,2023,26,31,"2023-07-01",44568.25,"2023-07-30",44568.916666666664,"29d","Continuous",null,"T","","Remise en peinture  + chape d'étancheité des tabliers du PI 53.680. \n ",38298]
["Infrabel","38306","Erquelinnes - Montzen","< >","HUY","FLEMALLE-HAUTE",2023,2023,19,20,"2023-05-13",44568.020833333336,"2023-05-14",44568.708333333336,"1d","Continuous",null,"T","","Renouvellement des appareils de voies d'Engis\r\nPhase 2 - WE 1/3 - Renouvellement AS 05AT / 05BT(+  plateforme) \n ",38306]
["Infrabel","38317","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,20,21,"2023-05-18",44568.003472222219,"2023-05-21",44568.666666666664,"3d","Continuous",null,"T","","Renouvellement (démolition / reconstruction) et mise au gabarit des passages inférieurs suivants : \r\n- 97.285\r\n- 102.011\r\n+ Électrification liaisons Straimont (Delooz Michel - ancien COLT 38563) \n ",38317]
["Infrabel","38344","Erquelinnes - Montzen","< >","FLEMALLE-ANNEXE","Y.RENORY",2023,2023,42,43,"2023-10-20",44568.916666666664,"2023-10-23",44568.25,"3d","Continuous",null,"T","","Renouvellement des appareils de voie 01AD/01BD à Seraing \n ",38344]
["Infrabel","38381","Erquelinnes - Montzen","< >","Y.RENORY","FLEMALLE-ANNEXE",2023,2023,43,43,"2023-10-26",44568.916666666664,"2023-10-27",44568.208333333336,"1d","Periodical",null,"T","","Renouvellement des appareils de voie à Seraing\r\nBourrage de révision \n ",38381]
["Infrabel","38488","Athus - Meuse","< >","BERTRIX","HALANZY",2022,2022,23,24,"2022-06-04",44568.25,"2022-06-07",44568.208333333336,"3d","Continuous",null,"T","","Pose des nouveaux trapezes de Signeulx et Straimont\r\n276000 \n ",38488]
["Infrabel","38551","Athus - Meuse","< >","VIRTON","BERTRIX",2023,2023,7,8,"2023-02-18",44568.958333333336,"2023-02-19",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont\r\n+ interventions de maintenance \n ",38551]
["Infrabel","38552","Athus - Meuse","< >","VIRTON","BERTRIX",2023,2023,9,10,"2023-03-04",44568.958333333336,"2023-03-05",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont \n ",38552]
["Infrabel","38553","Athus - Meuse","< >","VIRTON","BERTRIX",2023,2023,10,11,"2023-03-11",44568.958333333336,"2023-03-12",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont \n ",38553]
["Infrabel","38555","Athus - Meuse","< >","VIRTON","BERTRIX",2023,2023,12,13,"2023-03-25",44568.958333333336,"2023-03-26",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont \n ",38555]
["Infrabel","38557","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,14,15,"2023-04-08",44568.958333333336,"2023-04-09",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont \n ",38557]
["Infrabel","38558","Athus - Meuse","< >","VIRTON","BERTRIX",2023,2023,15,16,"2023-04-15",44568.958333333336,"2023-04-16",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont \n ",38558]
["Infrabel","38559","Athus - Meuse","< >","VIRTON","BERTRIX",2023,2023,16,17,"2023-04-22",44568.958333333336,"2023-04-23",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont\r\n+ interventions de maintenance \n ",38559]
["Infrabel","38560","Athus - Meuse","< >","VIRTON","BERTRIX",2023,2023,17,18,"2023-04-29",44568.958333333336,"2023-04-30",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont \n ",38560]
["Infrabel","38561","Athus - Meuse","< >","VIRTON","BERTRIX",2023,2023,18,19,"2023-05-06",44568.958333333336,"2023-05-07",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont \n ",38561]
["Infrabel","38564","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2023,2023,21,22,"2023-05-27",44568.958333333336,"2023-05-28",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont \n ",38564]
["Infrabel","38565","Athus - Meuse","< >","FLORENVILLE","BERTRIX",2023,2023,22,23,"2023-06-03",44568.958333333336,"2023-06-04",44568.625,"1d","Continuous",null,"T","","Electrification liaisons Straimont \n ",38565]
["Infrabel","38589","Athus - Meuse","< >","VIRTON","HALANZY",2023,2023,39,40,"2023-09-29",44568.916666666664,"2023-10-02",44568.666666666664,"3d","Continuous",null,"T","","Renouvellement ballast Halanzy : C75 (Musson) --- Phase 1.1. WE 1 \n ",38589]
["Infrabel","38656","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2023,2023,41,42,"2023-10-14",44568.25,"2023-10-16",44568.208333333336,"2d","Continuous",null,"T","","Pose du nouveau PS L144 bk0.776 \n ",38656]
["Infrabel","38659","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2023,2023,34,35,"2023-08-25",44568.958333333336,"2023-08-28",44568.208333333336,"3d","Periodical",null,"T","","Démolition tablier du PS L144 bk0.776 \n ",38659]
["Infrabel","38666","Lille - Charleroi","< >","MARCHIENNE-AU-PONT","Y.NORD",2022,2022,16,16,"2022-04-11",44568.979166666664,"2022-04-16",44568.180555555555,"5d","Periodical",null,"T","","Maintenance AI52\r\nUPM 294964 \nHKM à adapter",38666]
["Infrabel","38669","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2023,2023,23,28,"2023-06-05",44568.333333333336,"2023-07-10",44568.208333333336,"35d","Continuous",null,"","ST","Remplacement d'un tablier métallique à pose directe VA à la bk 7,591 \n ",38669]
[null,"38726","Athus - Meuse","< >","ANSEREMME","HOUYET",2023,2023,23,24,"2023-06-10",44568.25,"2023-06-12",44568.166666666664,"2d","Continuous",null,"T","","Renouvellement traverses KM 8930-9420 Grue \n ",38726]
["Infrabel","38742","Erquelinnes - Montzen","< >","Y.RENORY","OUGREE-GRIL F/K",2022,2022,18,19,"2022-04-30",44568.25,"2022-05-01",44568.916666666664,"1d","Continuous",null,"T","","Entretien tunnel d'Ougrée\r\nUPM: 275402\r\n+UPM303962/colt41226 \nHKM à adapter\r\nInfo Racc ??? : Port de Renory",38742]
["Infrabel","38743","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","OUGREE-GRIL F/K",2022,2022,19,20,"2022-05-07",44568.25,"2022-05-08",44568.916666666664,"1d","Continuous",null,"T","","Entretien tunnel d'Ougrée\r\nUPM: 275420 \nHKM à adapter\r\nInfo Racc ??? : Port de Renory",38743]
["Infrabel","38763","Athus - Meuse","< >","YVOIR","Y.NEFFE",2023,2023,20,21,"2023-05-19",44568.003472222219,"2023-05-21",44568.708333333336,"2d","Continuous",null,"T","","Renouvellement passage inférieur de Bouvignes BK 87.543 \n ",38763]
["Infrabel","38765","Athus - Meuse","< >","JAMBES","LUSTIN",2023,2023,20,21,"2023-05-18",44568.003472222219,"2023-05-21",44568.708333333336,"3d","Continuous",null,"T","","Poussage passage inférieur BK 65.900 en vue de la suppression du PN 101 \n ",38765]
["Infrabel","38766","Erquelinnes - Montzen","< >","STATTE","NAMUR",2023,2023,36,37,"2023-09-09",44568.006944444445,"2023-09-11",44568.166666666664,"2d","Continuous",null,"T","","Massification travaux :\r\n- 2 liaisons de Andenne\r\n- Poste de sectionnement Andenne + adaptation CAT\r\n- Passage supérieur Andenne\r\n- Quais de Sclaigneaux\r\n- Couloir sous-voies en vue de la suppression des PN 75-76-77-78 \n ",38766]
["Infrabel","38787","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2023,2023,43,44,"2023-10-27",44568.958333333336,"2023-10-30",44568.208333333336,"3d","Continuous",null,"T","","Pose du nouveau PS L144 bk0.776 \n ",38787]
["Infrabel","38790","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2023,2023,6,14,"2023-02-06",44568.003472222219,"2023-04-03",44568.003472222219,"56d","Continuous",null,"","ST","L12 Engelselei – waterdichte rokken vervangen\r\nSpoor A L27A eveneens continu buitendienst ( zie andere locaties ) \n ",38790]
["Infrabel","38796","Athus - Meuse","< >","YVOIR","Y.NEFFE",2023,2023,22,23,"2023-06-03",44568.003472222219,"2023-06-04",44568.708333333336,"1d","Continuous",null,"T","","Renouvellement passage inférieur de Bouvignes BK 87.543\r\n+ massification Renouvel rails dans les PN 114,... entretien AS en gare de Dinant \n ",38796]
["Infrabel","38827","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,30,31,"2023-07-29",44568.25,"2023-07-30",44568.625,"1d","Continuous",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°8.\r\nRéglage des contraintes \n ",38827]
["Infrabel","38842","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2022,2022,33,34,"2022-08-13",44568.583333333336,"2022-08-16",44568.25,"3d","Continuous",null,"T","","Réélectrification L. 124+L. 124A \r\nCTL L124A\r\n+ Préparation travaux ES en vue des VAE Manage \nMonceau inaccessible via L124A",38842]
["Infrabel","38871","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,42,42,"2022-10-10",44568.958333333336,"2022-10-14",44568.208333333336,"4d","Periodical",null,"T","","Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart \n ",38871]
["Infrabel","38875","Namur - Antwerpen","< >","FLEURUS","MARCINELLE",2022,2022,45,45,"2022-10-31",44568.9375,"2022-11-04",44568.208333333336,"4d","Periodical",null,"T","","Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\n+ Maintenance Z4. 51 P3HKV \n ",38875]
["Infrabel","38876","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,44,44,"2022-10-24",44568.9375,"2022-10-28",44568.208333333336,"4d","Periodical",null,"T","","Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart \n ",38876]
["Infrabel","38885","Athus - Meuse","< >","VIRTON","HALANZY",2023,2023,40,41,"2023-10-06",44568.916666666664,"2023-10-09",44568.666666666664,"3d","Continuous",null,"T","","Renouvellement ballast Halanzy : C75 (Musson) --- Phase 1.1. WE 2 \n ",38885]
["Infrabel","38892","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,41,42,"2022-10-07",44568.979166666664,"2022-10-10",44568.208333333336,"3d","Continuous",null,"T","","Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 1/4 \n ",38892]
["Infrabel","38894","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2022,2022,46,47,"2022-11-12",44568.958333333336,"2022-11-13",44568.625,"1d","Continuous",null,"T","","Mini CTL pour maintenance globale \n ",38894]
["Infrabel","38901","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,42,43,"2022-10-14",44568.979166666664,"2022-10-17",44568.208333333336,"3d","Continuous",null,"T","","Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 2/4\r\n+ Diagno 2022: L140 Partie 2 \n ",38901]
["Infrabel","38903","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2022,2022,45,46,"2022-11-04",44568.979166666664,"2022-11-07",44568.208333333336,"3d","Continuous",null,"T","","Chantier 2 - Renouvellement de traverses P93 - Fleurus-Lodelinsart\r\nWE 4/4 \n ",38903]
["Infrabel","38904","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,18,18,"2022-04-25",44568.934027777781,"2022-04-30",44568.215277777781,"5d","Periodical",null,"T","","Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nDémontage Signalisation suite au passage en PLP\r\nTravaux de préparation pour la construction de passerelles au droit du PI 61.597\r\nUPM 291688 \nHKM à adapter\r\nVia 117 - 124 - 130A - 90 - 94 - 96",38904]
["Infrabel","38905","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2022,2022,10,10,"2022-02-28",44568.986111111109,"2022-03-05",44568.229166666664,"5d","Periodical",null,"T","","Maintenance Z9.52 + Z3.53\r\nMise HS P3 HKM - Zone 9 AI52\r\nUPM 289100 - 290457 \nHKM à adapter",38905]
["Infrabel","38921","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2023,2023,11,14,"2023-03-18",44568.333333333336,"2023-04-03",44568.229166666664,"16d","Continuous",null,"T","","Renouvellement Traverses et Ballast\r\n(+/- 2,9 Km entre Lodelinsart et Charleroi-Ouest) \n ",38921]
["Infrabel","38926","Athus - Meuse","< >","VIRTON","HALANZY",2023,2023,46,47,"2023-11-18",44568.25,"2023-11-19",44568.625,"1d","Continuous",null,"T","","Renouvellement ballast Halanzy : C75 (Musson) --- Phase 1.2. WE 8\r\nRéglage des contraintes \n ",38926]
["Infrabel","38927","Athus - Meuse","< >","VIRTON","HALANZY",2023,2023,45,46,"2023-11-11",44568.25,"2023-11-12",44568.625,"1d","Continuous",null,"T","","Renouvellement ballast Halanzy : C75 (Musson) --- Phase 1.2. WE 7\r\nRéglage des contraintes \n ",38927]
["Infrabel","38928","Athus - Meuse","< >","Y.AUBANGE","HALANZY",2023,2023,42,43,"2023-10-20",44568.916666666664,"2023-10-23",44568.666666666664,"3d","Continuous",null,"T","","Renouvellement ballast Halanzy : C75(Aix-sur-Cloie) --- Phase 2.1. WE 4 \n ",38928]
["Infrabel","38929","Athus - Meuse","< >","Y.AUBANGE","HALANZY",2023,2023,43,44,"2023-10-27",44568.916666666664,"2023-10-30",44568.666666666664,"3d","Continuous",null,"T","","Renouvellement ballast Halanzy : C75 (Aix-sur-Cloie) --- Phase 2.1. WE 5 \n ",38929]
["Infrabel","38930","Athus - Meuse","< >","Y.AUBANGE","HALANZY",2023,2023,47,48,"2023-11-25",44568.25,"2023-11-26",44568.625,"1d","Continuous",null,"T","","Renouvellement ballast Halanzy : C75 (Aix-sur-Cloie) --- Phase 2.2. WE 9\r\nRéglage des contraintes \n ",38930]
["Infrabel","38931","Athus - Meuse","< >","Y.AUBANGE","HALANZY",2023,2023,48,49,"2023-12-02",44568.25,"2023-12-03",44568.625,"1d","Continuous",null,"T","","Renouvellement ballast Halanzy : C75 (Aix-sur-Cloie) --- Phase 2.2. WE 10\r\nRéglage des contraintes \n ",38931]
["Infrabel","38934","Athus - Meuse","< >","ANSEREMME","HOUYET",2023,2023,24,25,"2023-06-17",44568.25,"2023-06-19",44568.166666666664,"2d","Continuous",null,"T","","Renouvellement traverses KM 8930-9420 Grue \n ",38934]
["Infrabel","38935","Athus - Meuse","< >","ANSEREMME","HOUYET",2023,2023,25,26,"2023-06-24",44568.25,"2023-06-26",44568.166666666664,"2d","Continuous",null,"T","","Renouvellement traverses KM 8930-9420 Grue \n ",38935]
["Infrabel","38936","Athus - Meuse","< >","ANSEREMME","HOUYET",2023,2023,26,27,"2023-07-01",44568.25,"2023-07-03",44568.166666666664,"2d","Continuous",null,"T","","Renouvellement traverses KM 8930-9420 Grue \n ",38936]
["Infrabel","38937","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2023,2023,14,15,"2023-04-07",44568.930555555555,"2023-04-10",44568.222222222219,"3d","Continuous",null,"T","","Renouvellement Traverses et Ballast - WE 1/4\r\n(+/- 2,9 Km entre Lodelinsart et Charleroi-Ouest) \n ",38937]
["Infrabel","38938","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2023,2023,15,16,"2023-04-14",44568.930555555555,"2023-04-17",44568.222222222219,"3d","Continuous",null,"T","","Renouvellement Traverses et Ballast - WE 2/4\r\n(+/- 2,9 Km entre Lodelinsart et Charleroi-Ouest) \n ",38938]
["Infrabel","38939","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2023,2023,18,19,"2023-05-05",44568.930555555555,"2023-05-08",44568.222222222219,"3d","Continuous",null,"T","","Renouvellement Traverses et Ballast - WE 3/4\r\n(+/- 2,9 Km entre Lodelinsart et Charleroi-Ouest) \n ",38939]
["Infrabel","38940","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2023,2023,19,20,"2023-05-12",44568.930555555555,"2023-05-15",44568.222222222219,"3d","Continuous",null,"T","","Renouvellement Traverses et Ballast - WE 4/4\r\n(+/- 2,9 Km entre Lodelinsart et Charleroi-Ouest) \n ",38940]
["Infrabel","38961","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,6,7,"2022-02-05",44568.25,"2022-02-07",44568.166666666664,"2d","Continuous",null,"T","","L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - voorbereidende werken\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) -> L59 bijkomende isolatoren te plaatsen + DOES L52\r\nWerken Kennedytunnel (Sam De Raeve) (kom \nHKM om te leiden.",38961]
["Infrabel","38962","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,7,8,"2022-02-12",44568.041666666664,"2022-02-14",44568.166666666664,"2d","Continuous",null,"T","","L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - voorbereidende werken\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) -> L59 nog bijkomende isolatoren te plaatsen\r\nDoes op L52 ( zie andere locaties ) \nHKM om te leiden.",38962]
["Infrabel","38963","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,13,14,"2022-03-26",44568.25,"2022-03-28",44568.166666666664,"2d","Continuous",null,"T","","L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - voorbereidende werken\r\nR-278956 \nHKM om te leiden.",38963]
["Infrabel","38967","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2022,2022,12,13,"2022-03-19",44568.25,"2022-03-21",44568.166666666664,"2d","Continuous",null,"T","","L59 Zwijndrecht  - Y-West Berchem incl. Kennedytunnel (FASE 4) - afwerking\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) +\r\nDoes L52\r\nTCR 278984 \nHKM om te leiden.",38967]
["Infrabel","39021","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2022,2022,25,26,"2022-06-18",44568.013888888891,"2022-06-20",44568.1875,"2d","Continuous",null,"T","","Renouvellement AS liaison 28 à Tilleur\r\n272861 \n ",39021]
["Infrabel","39022","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,25,26,"2022-06-17",44568.979166666664,"2022-06-20",44568.666666666664,"3d","Continuous",null,"","ST","Criblage du ballast + rails/traverses dans tunnel Fidevoye\r\n278959 \nHKM à adapter",39022]
["Infrabel","39023","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,24,25,"2022-06-11",44568.25,"2022-06-13",44568.180555555555,"2d","Continuous",null,"T","","Criblage du ballast + rails/traverses dans tunnel Fidevoye\r\n+visites\r\n278957 \nDétournement via L130A",39023]
["Infrabel","39024","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,24,25,"2022-06-10",44568.979166666664,"2022-06-13",44568.666666666664,"3d","Continuous",null,"","ST","Criblage du ballast + rails/traverses dans tunnel Fidevoye\r\n278954 \nHKM à adapter",39024]
["Infrabel","39026","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,27,28,"2022-07-01",44568.979166666664,"2022-07-04",44568.666666666664,"3d","Continuous",null,"","ST","Criblage du ballast + rails/traverses dans tunnel Fidevoye\r\n278961 \nHKM à adapter",39026]
["Infrabel","39027","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,28,29,"2022-07-08",44568.979166666664,"2022-07-11",44568.666666666664,"3d","Continuous",null,"","ST","Criblage du ballast + rails/traverses dans tunnel Fidevoye \nHKM à adapter",39027]
["Infrabel","39080","Erquelinnes - Montzen","< >","SCLESSIN","LIEGE-GUILLEMINS",2022,2022,48,48,"2022-11-22",44568.972222222219,"2022-11-26",44568.1875,"4d","Periodical",null,"T","","Entretien des liaisons \n ",39080]
["Infrabel","39113","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,24,25,"2022-06-11",44568.020833333336,"2022-06-13",44568.180555555555,"2d","Continuous",null,"T","","Maintenance AI52 \nA détourner",39113]
["Infrabel","39116","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,27,28,"2022-07-02",44568.020833333336,"2022-07-04",44568.180555555555,"2d","Continuous",null,"T","","Aménagement Marchienne-au-Pont - Phase 4 - WE 4/5 \nA détourner",39116]
["Infrabel","39123","Lille - Charleroi","< >","ATH","LEUZE",2023,2023,34,34,"2023-08-21",44568.961805555555,"2023-08-26",44568.1875,"5d","Periodical",null,"T","","Criblage de ballast - C75 nuits prépa \n ",39123]
["Infrabel","39136","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2023,2023,18,18,"2023-05-02",44568.930555555555,"2023-05-05",44568.222222222219,"3d","Periodical",null,"T","","Renouvellement Traverses et Ballast - Sem. 1\r\nBourrage et contrainte  + drainage \n ",39136]
["Infrabel","39137","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2023,2023,19,19,"2023-05-08",44568.930555555555,"2023-05-12",44568.222222222219,"4d","Periodical",null,"T","","Renouvellement Traverses et Ballast - Sem. 2\r\nBourrage et contrainte  + drainage \n ",39137]
["Infrabel","39209","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON",2023,2023,47,48,"2023-11-24",44568.993055555555,"2023-11-27",44568.208333333336,"3d","Continuous",null,"T","","Onderhoud met impact internationaal.\r\n+ Buitenwerken IL For ETCS_IL-SML_SO_L75_Mouscron (Mee werken  mogelijk) \n ",39209]
["Infrabel","39230","Lille - Antwerpen","< >","Y.BETHUNE","FRONT. FLANDRE-WALLONIE L75",2023,2023,13,13,"2023-03-27",44568.993055555555,"2023-04-01",44568.208333333336,"5d","Periodical",null,"T","","Onderhoud met impact internationaal. \n ",39230]
["Infrabel","39231","Lille - Antwerpen","< >","Y.BETHUNE","FRONT. FLANDRE-WALLONIE L75",2023,2023,36,36,"2023-09-04",44568.993055555555,"2023-09-09",44568.208333333336,"5d","Periodical",null,"T","","Onderhoud met impact internationaal. \n ",39231]
["Infrabel","39304","Lille - Antwerpen",">","MOUSCRON","KORTRIJK",2022,2022,13,13,"2022-03-21",44568.9375,"2022-03-26",44568.222222222219,"5d","Periodical",null,"","ST","Construction passerelle en gare de Mouscron\r\nPhase 1 – Fondations\r\nPhase 1.2. Forage des pieux dans le quai II-III\r\nUPM 278543\r\nNuits de semaine 22h30 - 05h20 \r\nNuit R5/R6 22h50 - 05h40 \nHKM à adapter",39304]
["Infrabel","39310","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,20,21,"2022-05-14",44568.958333333336,"2022-05-16",44568.208333333336,"2d","Periodical",null,"T","","Construction passerelle en gare de Mouscron\r\nPhase 3 – Pose des Piles\r\nUPM 278550 \nNéant",39310]
["Infrabel","39311","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,21,22,"2022-05-21",44568.958333333336,"2022-05-23",44568.208333333336,"2d","Periodical",null,"T","","Construction passerelle en gare de Mouscron\r\nPhase 3 – Pose des Piles\r\nUPM 278553 \nNéant",39311]
["Infrabel","39393","Lille - Antwerpen",">","MOUSCRON","KORTRIJK",2022,2022,16,16,"2022-04-11",44568.951388888891,"2022-04-16",44568.236111111109,"5d","Periodical",null,"","ST","Construction passerelle en gare de Mouscron\r\nPhase 2 – Fondations\r\nPhase 2.1. Dalle quai II-III\r\nUPM 278548 \nHKM A ADAPTER",39393]
["Infrabel","39395","Lille - Antwerpen",">","KORTRIJK","MOUSCRON",2022,2022,23,23,"2022-06-04",44568.583333333336,"2022-06-04",44568.958333333336,"0d","Periodical",null,"","ST","Construction passerelle en gare de Mouscron\r\nPhase 4 – Pose des tabliers\r\nUPM 278557 \nHKM à adapter\r\nFaisceau Mouscron inaccessible",39395]
["Infrabel","39397","Lille - Antwerpen","< >","MOUSCRON","LAUWE",2022,2022,23,24,"2022-06-04",44568.958333333336,"2022-06-06",44568.208333333336,"2d","Periodical",null,"T","","Construction passerelle en gare de Mouscron\r\nPhase 4 – Pose des tabliers\r\nUPM 278565 \nHKM à adapter",39397]
["Infrabel","39512","Namur - Antwerpen","< >","NAMUR","RONET",2022,2022,35,35,"2022-08-21",44568.003472222219,"2022-08-21",44568.21875,"0d","Periodical",null,"T","","Maintenance AW et interventions diverses en gare de Namur (ZONE 6) \n ",39512]
["Infrabel","39514","Namur - Antwerpen","< >","NAMUR","RONET",2022,2022,47,47,"2022-11-13",44568.003472222219,"2022-11-13",44568.21875,"0d","Periodical",null,"T","","Maintenance AW et interventions diverses en gare de Namur (ZONE 6) \n ",39514]
["Infrabel","39541","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2024,2024,20,21,"2024-05-17","2022-01-07T22:20:00","2024-05-20","2022-01-07T05:20:00","3d","Continuous",null,"T","","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nCTL en continu pour ripage du CSV. \n ",39541]
["Infrabel","39546","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2024,2024,40,41,"2024-10-04","2022-01-07T22:20:00","2024-10-07","2022-01-07T05:20:00","3d","Continuous",null,"T","","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nCTL en continu pour ripage du PI. \n ",39546]
["Infrabel","39558","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2024,2024,20,23,"2024-05-13","2022-01-07T22:20:00","2024-06-07","2022-01-07T04:20:00","25d","Periodical",null,"T","","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\npréparation ripage du CSV \n ",39558]
["Infrabel","39577","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2024,2024,39,43,"2024-09-23","2022-01-07T22:20:00","2024-10-25","2022-01-07T05:20:00","32d","Periodical",null,"T","","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nPréparation ripage du PI. \n ",39577]
["Infrabel","39587","Lille - Charleroi",">","MOUSCRON","HERSEAUX",2024,2024,44,46,"2024-10-28","2022-01-07T09:00:00","2024-11-10","2022-01-07T15:00:00","13d","Periodical",null,"","ST","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nSAVU + S460 travaux de piste \n ",39587]
["Infrabel","39589","Lille - Charleroi",">","MOUSCRON","FROYENNES",2024,2024,34,36,"2024-08-19","2022-01-07T09:00:00","2024-09-01","2022-01-07T15:00:00","13d","Periodical",null,"","ST","Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nSAVU + S460 travaux de piste \n ",39589]
["Infrabel","39701","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES",2023,2023,25,28,"2023-06-24",44568.958333333336,"2023-07-10",44568.208333333336,"16d","Continuous",null,"T","","CTL pour la pose du second tablier sur les ponts 7&8\r\n+ Maintenance AI51 \r\n+ Renouvellement de la chape du PI 121.475 (Préparation + renouvellement)\r\n+ Renouvellement As Erquelinnes \n ",39701]
["Infrabel","39710","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2023,2023,23,23,"2023-06-05",44568.923611111109,"2023-06-09",44568.173611111109,"4d","Periodical",null,"T","","CTL toutes les nuits de semaine pour travaux préparatoires - Pose 2nd tablier des ponts 7&8 \n ",39710]
["Infrabel","39723","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2023,2023,18,18,"2023-05-02",44568.923611111109,"2023-05-06",44568.173611111109,"4d","Periodical",null,"T","","CTL toutes les nuits de semaine pour travaux préparatoires - Pose 2nd tablier des ponts 7&8 \n ",39723]
["Infrabel","39724","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2023,2023,32,32,"2023-08-07",44568.923611111109,"2023-08-11",44568.173611111109,"4d","Periodical",null,"T","","CTL toutes les nuits de semaine pour travaux de finition - Pose 2nd tablier des ponts 7&8 \n ",39724]
["Infrabel","39726","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2023,2023,15,15,"2023-04-11",44568.881944444445,"2023-04-15",44568.173611111109,"4d","Periodical",null,"T","","CTL de nuit pour réalisation de blindage au droit des PS km 104.903 et 118.788\r\n+ Maintenance Z2. 51  P3 HKV \n ",39726]
["Infrabel","39773","Erquelinnes - Montzen","< >","MARCHIENNE-ZONE","ERQUELINNES-FRONTIERE",2023,2023,48,49,"2023-12-01",44568.958333333336,"2023-12-04",44568.208333333336,"3d","Continuous",null,"T","","CTL pour travaux de finition (démontage coffrage, garde-corps,...) des PS km 104.903 et 118.788 \n ",39773]
["Infrabel","39804","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2023,2023,16,16,"2023-04-17",44568.947916666664,"2023-04-22",44568.173611111109,"5d","Periodical",null,"T","","Renouvellement des AS Y. Froyennes\r\nUPM : 317283 \n ",39804]
["Infrabel","39805","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2023,2023,14,16,"2023-04-03",44568.25,"2023-04-17",44568.208333333336,"14d","Continuous",null,"T","","Renouvellement des AS Y. Froyennes\r\n\r\nUPM : 317247 \n",39805]
["Infrabel","39812","Lille - Charleroi","< >","ATH","LEUZE",2023,2023,40,40,"2023-10-02",44568.961805555555,"2023-10-07",44568.1875,"5d","Periodical",null,"T","","Criblage de ballast - C75 nuits finitions \n ",39812]
["Infrabel","39813","Lille - Charleroi","< >","ATH","LEUZE",2023,2023,37,38,"2023-09-15",44568.961805555555,"2023-09-18",44568.1875,"3d","Continuous",null,"T","","Criblage de ballast - C75 \n ",39813]
["Infrabel","39814","Lille - Charleroi","< >","ATH","LEUZE",2023,2023,38,39,"2023-09-22",44568.961805555555,"2023-09-25",44568.1875,"3d","Continuous",null,"T","","Criblage de ballast - C75 nuits renouvellement \n ",39814]
["Infrabel","39815","Lille - Charleroi","< >","ATH","LEUZE",2023,2023,39,40,"2023-09-29",44568.961805555555,"2023-10-02",44568.194444444445,"3d","Continuous",null,"T","","Criblage de ballast - C75 nuits renouvellement \n ",39815]
["Infrabel","39816","Lille - Charleroi","< >","ATH","LEUZE",2023,2023,40,41,"2023-10-07",44568.1875,"2023-10-09",44568.1875,"2d","Continuous",null,"T","","Criblage de ballast - C75 \n ",39816]
["Infrabel","39944","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,17,17,"2022-04-19",44568.958333333336,"2022-04-22",44568.208333333336,"3d","Periodical",null,"T","","P93 - nuits préparation\r\n+ 385335 PLP\r\nUPM 298281 \nHKM à adapter",39944]
["Infrabel","39945","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,27,27,"2022-06-27",44568.958333333336,"2022-07-01",44568.208333333336,"4d","Periodical",null,"T","","P93 - nuits préparation\r\n+ Renouvellement PN123\r\n+ Massification Mathilde Wallez : 385335 PLP\r\nUPM 298287 \nHKM à adapter",39945]
["Infrabel","39946","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,45,45,"2022-10-31",44568.958333333336,"2022-11-04",44568.208333333336,"4d","Periodical",null,"T","","P93 - nuits préparation\r\n+ 385335 PLP \n ",39946]
["Infrabel","39947","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,17,18,"2022-04-22",44568.958333333336,"2022-04-25",44568.208333333336,"3d","Continuous",null,"T","","P93 - renouvellement\r\n+ 385335 PLP\r\nUPM 298283 \nHKM à adapter",39947]
["Infrabel","39954","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,25,26,"2022-06-18",44568.25,"2022-06-20",44568.208333333336,"2d","Continuous",null,"T","","PN123 - renouvellement\r\n+ 385335 PLP\r\nUPM 298286 \nHKM à adapter",39954]
["Infrabel","39982","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2022,2022,17,17,"2022-04-20",44568.041666666664,"2022-04-23",44568.229166666664,"3d","Periodical",null,"T","","Maintenance Z.3.53\r\nMise HS en P3 HKM zone 3 AI Mons\r\nUPM 290460 \nHKM à adapter",39982]
["Infrabel","39983","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.ECAUSSINNES",2022,2022,28,28,"2022-07-04",44568.965277777781,"2022-07-09",44568.236111111109,"5d","Periodical",null,"T","","Maintenance Z.3.53\r\nMise HS en P3 HKV zone 3 AI Mons \n ",39983]
["Infrabel","39984","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2022,2022,45,45,"2022-11-03",44568.083333333336,"2022-11-05",44568.125,"2d","Periodical",null,"T","","Maintenance Z.3.53\r\nMise HS en P3 HKM zone 3 AI Mons \n ",39984]
["Infrabel","39987","Lille - Charleroi","< >","BRAINE-LE-COMTE","ECAUSSINNES",2022,2022,29,30,"2022-07-16",44568.25,"2022-07-17",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z.3.53 + Révision AS 42D-43D et 39BD\r\nMise HS en P4 \n ",39987]
["Infrabel","39994","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,25,26,"2022-06-18",44568.222222222219,"2022-06-19",44568.708333333336,"1d","Continuous",null,"T","","Maintenance\r\nP4 Z3. 51\r\nUPM 297207 \nHKM à adapter",39994]
["Infrabel","39996","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,36,37,"2022-09-03",44568.25,"2022-09-05",44568.208333333336,"2d","Continuous",null,"T","","Chantier 1 - Renouvellement de traverses P93 - Tilly-La Roche   (Bourrage - Contrainte - Pistes - Finitions - ART)\r\n+ Maintenance\r\nP4 Z3.51 \n ",39996]
["Infrabel","39997","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,37,38,"2022-09-10",44568.25,"2022-09-12",44568.208333333336,"2d","Continuous",null,"T","","Chantier 1 - Renouvellement de traverses P93 - Tilly-La Roche   (Contrainte - Pistes - Finitions - ART)\r\n+ Maintenance P4 Z3.51\r\n+ Entretien des PN + massification maintenance+ travaux ES \n ",39997]
["Infrabel","40003","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2022,2022,45,46,"2022-11-04",44568.979166666664,"2022-11-07",44568.1875,"3d","Continuous",null,"T","","Renouvellement des PDB du pont canal L117 voies A et B \r\n+ Maintenance AI53 Z3.53\r\n+ Maintenance AI52 Z9.52 \n ",40003]
["Infrabel","40015","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2022,2022,7,8,"2022-02-12",44568.986111111109,"2022-02-14",44568.177083333336,"2d","Periodical",null,"T","","Maintenance Z4.53 \r\nMise HS nuit de we\r\nUPM 278081 \nHKM à adapter",40015]
["Infrabel","40016","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2023,2023,23,24,"2023-06-09",44568.958333333336,"2023-06-12",44568.208333333336,"3d","Continuous",null,"T","","Renouvellement des Tabliers métalliques situés Bk 43.660 et Bk 48.720\r\n+ Maintenance Z3. 51  P4+\r\n+ Diagno 2023: L140 Partie 1\r\n+ Massification des travaux de maintenance AI 44   \r\n+ Service ES révision et Géométrie 09BR/10AR/12R/13BR/19AR/19BR\r\n+ Renou \n ",40016]
["Infrabel","40017","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2023,2023,23,23,"2023-06-05",44568.958333333336,"2023-06-09",44568.208333333336,"4d","Periodical",null,"T","","Renouvellement des Tabliers métalliques situés Bk 43.660 et Bk 48.720\r\nPréparations \n ",40017]
["Infrabel","40021","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2023,2023,26,27,"2023-06-30",44568.958333333336,"2023-07-03",44568.208333333336,"3d","Periodical",null,"T","","Renouvellement des Tabliers métalliques situés Bk 43.660 et Bk 48.720 \n ",40021]
["Infrabel","40028","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.SOIGNIES",2022,2022,15,16,"2022-04-09",44568.25,"2022-04-10",44568.666666666664,"1d","Continuous",null,"T","","Maintenance Z2.53\r\nMise HS P4\r\nUPM 278070 \nHKM à adapter\r\nVia 117 - 124A - 130A - 90 - 90C",40028]
["Infrabel","40219","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","ANTWERPEN-NOORD-INRIT C1",2023,2023,36,39,"2023-09-04",44568.958333333336,"2023-09-24",44568.208333333336,"20d","Continuous",null,"T","","LANGE TLO 3weken: Vernieuwing wissels bundelkop C1 + verbinding tussen C1-C2.\r\nWerkgroep wordt opgestart; zie dossier 20210203_2023 - L27A Antwerpen-Noord-C2-N_v4 \n ",40219]
["Infrabel","40229","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2023,2023,6,7,"2023-02-11",44568.041666666664,"2023-02-13",44568.1875,"2d","Continuous",null,"T","","WE OVERWEGVERNIEUWING: Weekend TLO.\r\nTotaal: 4 nachten + 2WE + 4nachten.\r\n+\r\nOude Landen project 308 \n ",40229]
["Infrabel","40230","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2023,2023,7,8,"2023-02-18",44568.041666666664,"2023-02-20",44568.1875,"2d","Continuous",null,"T","","WE OVERWEGVERNIEUWING: Weekend TLO.\r\nTotaal: 4 nachten + 2WE + 4nachten.\r\n+\r\nOude Landen project 308 \n ",40230]
["Infrabel","40243","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2023,2023,21,22,"2023-05-27",44568.041666666664,"2023-05-30",44568.166666666664,"3d","Continuous",null,"T","","Weekend OHH + Pinksterweekend: sanering 'Bommenspoor' Wildert + OW32 Harmelen + vernieuwing wissel Essen\r\n(beperkter alternatief voor week TLO - risico gezien aard der werken)\r\nBTS voor OW + bommenspoor tot minimaal 1 week na de werken.\r\n+\r\nOude Landen  \n ",40243]
["Infrabel","40247","Erquelinnes - Montzen","< >","HUY","JAVA",2022,2022,18,18,"2022-04-26",44568.003472222219,"2022-04-29",44568.208333333336,"3d","Periodical",null,"T","","Renouvellement des appareils 02AR, 02BR/03R et 04AR à Statte\r\nRenouvellement des quais de Bas-Oha\r\nPréparation\r\nUPM: 272539 \nHKM à adapter",40247]
["Infrabel","40435","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2023,2023,20,21,"2023-05-18",44568.041666666664,"2023-05-22",44568.166666666664,"4d","Continuous",null,"T","","Weekend OHH + Pinksterweekend: sanering 'Bommenspoor' Wildert + OW32 Harmelen + vernieuwing wissel Essen\r\n(beperkter alternatief voor week TLO - risico gezien aard der werken)\r\nBTS voor OW + bommenspoor tot minimaal 1 week na de werken.\r\n+\r\nOude Landen  \n ",40435]
["Infrabel","40446","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2023,2023,7,9,"2023-02-18",44568.041666666664,"2023-02-27",44568.166666666664,"9d","Continuous",null,"T","","Bouwen van een nieuwe brug over station Antwerpen-Zuid\r\n+\r\nOnderhoud wissels\r\n+\r\nTunnelveiligheid  Kennedytunnel \n ",40446]
["Infrabel","40447","Lille - Antwerpen","< >","Y.WEST BERCHEM","Y.MELSELE",2023,2023,7,8,"2023-02-18",44568.25,"2023-02-20",44568.166666666664,"2d","Continuous",null,"T","","Bouwen van een nieuwe brug over station Antwerpen-Zuid\r\n+\r\nOnderhoud \n ",40447]
["Infrabel","40448","Lille - Antwerpen","< >","Y.WEST BERCHEM","Y.MELSELE",2023,2023,8,9,"2023-02-25",44568.25,"2023-02-27",44568.166666666664,"2d","Continuous",null,"T","","Bouwen van een nieuwe brug over station Antwerpen-Zuid \n ",40448]
["Infrabel","40479","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2022,2022,48,49,"2022-11-26",44568.916666666664,"2022-11-27",44568.666666666664,"1d","Continuous",null,"T","","Maintenance Z4.53 + Révision 01AE + 12BE\r\nMise HS P4 R6 22h - R7 16h \n ",40479]
["Infrabel","40489","Lille - Charleroi","< >","JURBISE","BRUGELETTE",2022,2022,20,20,"2022-05-09",44568.9375,"2022-05-14",44568.215277777781,"5d","Periodical",null,"T","","Maintenance Z.7.53\r\nMise HS en P3\r\nUPM 277059 \nHKM à adapter",40489]
["Infrabel","40490","Lille - Charleroi","< >","JURBISE","BRUGELETTE",2022,2022,21,22,"2022-05-21",44568.25,"2022-05-22",44568.666666666664,"1d","Continuous",null,"T","","Maintenance Z.7.53 + Révision As 09AF - 09BF\r\nMise HS en P4\r\nUPM 277080 \nHKM à adapter\r\nVia 117 - 124 - 130A - 94",40490]
["Infrabel","40491","Lille - Charleroi","< >","JURBISE","BRUGELETTE",2022,2022,44,45,"2022-10-29",44568.25,"2022-10-30",44568.666666666664,"1d","Continuous",null,"T","","Maintenance Z.7.53 \r\nMise HS en P4 \n ",40491]
["Infrabel","40492","Lille - Charleroi","< >","JURBISE","BRUGELETTE",2022,2022,40,41,"2022-10-01",44568.25,"2022-10-02",44568.666666666664,"1d","Continuous",null,"T","","Maintenance Z.7.53 \r\nMise HS en P4 \n ",40492]
["Infrabel","40513","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,16,17,"2022-04-16",44568.958333333336,"2022-04-17",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Signeulx\r\nUPM: 275969 \nHKM à adapter",40513]
["Infrabel","40516","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,19,20,"2022-05-07",44568.958333333336,"2022-05-08",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Straimont\r\nUPM: 275976 \n ",40516]
["Infrabel","40518","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,18,19,"2022-04-30",44568.958333333336,"2022-05-01",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Straimont\r\nUPM: 275974 \nHKM à adapter",40518]
["Infrabel","40523","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,25,26,"2022-06-18",44568.958333333336,"2022-06-20",44568.208333333336,"2d","Continuous",null,"T","","Travaux de finition des nouvelles liaisons de Straimont\r\n276004 \n ",40523]
["Infrabel","40525","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,26,27,"2022-06-25",44568.958333333336,"2022-06-27",44568.208333333336,"2d","Continuous",null,"T","","Travaux de finition des nouvelles liaisons de Straimont\r\n276025 \n ",40525]
["Infrabel","40680","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,8,8,"2022-02-15",44568.083333333336,"2022-02-19",44568.125,"4d","Periodical",null,"T","","Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november.\r\nR-284335-01 \nNéant",40680]
["Infrabel","40681","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,10,10,"2022-03-01",44568.951388888891,"2022-03-05",44568.239583333336,"4d","Periodical",null,"T","","Onderhoud + ETCS\r\nR-294464\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \nNéant",40681]
["Infrabel","40682","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,11,11,"2022-03-07",44568.951388888891,"2022-03-12",44568.239583333336,"5d","Periodical",null,"T","","Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november.\r\nR-294520 \nINFO RACC",40682]
["Infrabel","40683","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,17,17,"2022-04-20",44568.083333333336,"2022-04-23",44568.125,"3d","Periodical",null,"T","","Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november.\r\n\r\nPaasmaandag niet inbegrepen \n ",40683]
["Infrabel","40684","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,27,27,"2022-06-28",44568.083333333336,"2022-07-02",44568.125,"4d","Periodical",null,"T","","Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",40684]
["Infrabel","40685","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2022,2022,45,45,"2022-11-03",44568.083333333336,"2022-11-05",44568.125,"2d","Periodical",null,"T","","Onderhoud + ETCS\r\n\r\n1 WE in najaar – 1 WE in voorjaar TLO Moeskroen – Kortrijk\r\n1 week nachten in maart, mei, september en november. \n ",40685]
["Infrabel","40707","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2022,2022,11,12,"2022-03-12",44568.25,"2022-03-13",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z3. 51  P4+\r\nUPM 297206 \nHKM à adapter",40707]
["Infrabel","40722","Erquelinnes - Montzen","< >","FROIDMONT","VISE",2022,2022,27,27,"2022-06-27",44568.916666666664,"2022-07-02",44568.25,"5d","Periodical",null,"T","","Travaux d'entretien mécanisé et manuel des AS du grill côté Bressoux - Carte 9\r\n294739 \n ",40722]
["Infrabel","40747","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2022,2022,10,11,"2022-02-28",44568.25,"2022-03-06",44568.708333333336,"6d","Continuous",null,"T","","Maintenance massifiée (en complément demande 29933 L139)\r\n308104 \nHKM à adapter\r\nInfo Racc 47 : 1.N.112/3 (Inovyn 2)",40747]
["Infrabel","40752","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2022,2022,11,12,"2022-03-11",44568.979166666664,"2022-03-14",44568.208333333336,"3d","Continuous",null,"T","","Maintenance massifiée (en complément demande 30891 L139)\r\nUPM: 279867 \nHKM à adapter\r\nInfo Racc 47 : 1.N.112/3 (Inovyn 2)",40752]
["Infrabel","40757","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2022,2022,13,14,"2022-03-25",44568.979166666664,"2022-03-28",44568.208333333336,"3d","Continuous",null,"T","","Maintenance massifiée (en complément demande 30892 L139)\r\nUPM: 293408 \nHKM à adapter\r\nInfo Racc 47 : 1.N.112/3 (Inovyn 2)",40757]
["Infrabel","40773","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2022,2022,43,43,"2022-10-16",44568.25,"2022-10-16",44568.625,"0d","Periodical",null,"T","","maintenance infrastructure \n ",40773]
["Infrabel","40957","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2022,2022,8,9,"2022-02-19",44568.25,"2022-02-20",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z4. 51  P4+\r\nUPM 297224 \nNéant",40957]
["Infrabel","41023","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2022,2022,23,24,"2022-06-03",44568.96875,"2022-06-05",44568.708333333336,"2d","Continuous",null,"T","","Maintenance Z4. 51  P4+\r\nUPM 297227 \nHKM à adapter",41023]
["Infrabel","41226","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","Y.RENORY",2022,2022,18,19,"2022-04-30",44568.333333333336,"2022-05-01",44568.708333333336,"1d","Periodical",null,"T","","Z.21.41 P4+ - Maintenance AI41\r\nUPM: 303962\r\n+ UPM 275402/colt 38742 \nInfo Racc 54 : 1.L.103/3 (Renory 2)",41226]
["Infrabel","41227","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","FLEMALLE-HAUTE",2022,2022,18,18,"2022-04-26",44568.083333333336,"2022-04-30",44568.125,"4d","Periodical",null,"T","","Z.19.41 P3 - Maintenance AI41\r\n+ Travaux PLP sur L125A_Flémalle-Annexe. TR384304 \ndesserte Renory impossible",41227]
["Infrabel","41238","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","Y.LEMAN",2022,2022,17,17,"2022-04-19",44568.965277777781,"2022-04-23",44568.1875,"4d","Periodical",null,"T","","Z.09.41 - P3 Maintenance AI41\r\nUPM: 282539 \nNéant\r\nInfo Racc 72 : 1.L.L125/2 (Prayon)",41238]
["Infrabel","41301","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,18,19,"2022-04-30",44568.25,"2022-05-02",44568.208333333336,"2d","Continuous",null,"T","","P93 - renouvellement\r\n+ 385335 PLP\r\nUPM 298285 \nHKM à adapter",41301]
["Infrabel","41319","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,45,46,"2022-11-04",44568.958333333336,"2022-11-07",44568.208333333336,"3d","Continuous",null,"T","","P93 - renouvellement \n ",41319]
["Infrabel","41320","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2022,2022,46,47,"2022-11-12",44568.875,"2022-11-14",44568.208333333336,"2d","Continuous",null,"T","","P93 - renouvellement\r\n+ 385335 PLP \n ",41320]
["Infrabel","41340","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,37,38,"2022-09-09",44568.923611111109,"2022-09-12",44568.215277777781,"3d","Continuous",null,"T","","Renouvellement de traverses entre Ath et Lens P93 \n ",41340]
["Infrabel","41341","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,39,40,"2022-09-23",44568.923611111109,"2022-09-26",44568.215277777781,"3d","Continuous",null,"T","","Renouvellement de traverses entre Ath et Lens P93 \n ",41341]
["Infrabel","41342","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,40,41,"2022-09-30",44568.923611111109,"2022-10-03",44568.215277777781,"3d","Continuous",null,"T","","Renouvellement de traverses entre Ath et Lens P93 \n ",41342]
["Infrabel","41346","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,44,45,"2022-10-29",44568.25,"2022-10-31",44568.215277777781,"2d","Continuous",null,"T","","Renouvellement de traverses entre Ath et Lens P93\r\nFinitions \n ",41346]
["Infrabel","41383","Erquelinnes - Montzen","< >","LA SAMBRE","Y.NORD",2022,2022,7,7,"2022-02-07",44568.9375,"2022-02-12",44568.166666666664,"5d","Periodical",null,"T","","Maintenance Z5. 51:    P3 HKV\r\nUPM 287679 \nHKM à adapter\r\nInfo racc : Solvay (Les Petons)",41383]
["Infrabel","41385","Erquelinnes - Montzen","< >","LA SAMBRE","Y.NORD",2022,2022,43,43,"2022-10-17",44568.9375,"2022-10-22",44568.166666666664,"5d","Periodical",null,"T","","Maintenance Z5. 51:    P3 HKV \n ",41385]
["Infrabel","41434","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,47,48,"2022-11-19",44568.958333333336,"2022-11-20",44568.625,"1d","Continuous",null,"T","","Trapèze de Straimont : travaux Signalling (MES) \n ",41434]
["Infrabel","41465","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,26,26,"2022-06-20",44568.923611111109,"2022-06-25",44568.166666666664,"5d","Periodical",null,"T","","Pose seconds tabliers ponts 10 et 11\r\nTravaux préparatoires\r\nUPM 278786 \nHKM à adapter\r\nVia L117 - 124 - 96",41465]
["Infrabel","41576","Lille - Charleroi","< >","CHARLEROI-SUD","CHARLEROI-SUD",2022,2022,5,5,"2022-01-24",44568.9375,"2022-01-29",44568.208333333336,"5d","Periodical",null,"T","","Maintenance Z8. 51   P3 HKV\r\nUPM 286239 \n ",41576]
["Infrabel","41604","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,7,7,"2022-02-09",44568.979166666664,"2022-02-12",44568.1875,"3d","Periodical",null,"T","","Maintenance Z7. 51   P3\r\nUPM 299661 \nHKM à adpater",41604]
["Infrabel","41605","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2022,2022,37,37,"2022-09-07",44568.979166666664,"2022-09-10",44568.1875,"3d","Periodical",null,"T","","Maintenance Z7. 51   P3 \n ",41605]
["Infrabel","41618","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2022,2022,17,17,"2022-04-19",44568.979166666664,"2022-04-23",44568.208333333336,"4d","Periodical",null,"T","","Maintenance Z10. 51   P3 HKV          UPM 297279\r\nDétails car sur plusieurs lignes:\r\nL130\tVoie B\tCharleroi-Sud\tChâtelet\tD08-G. 20   &\t FX3_I. 20\r\n\t        Voie A\t\t\t                        D09-G. 20    &  F4_I. 20\r\n\t\t\t\tE10_H. 20   &\tF4_I. 20\r\n\t\t\t\tE11_H.  \nHKM à adapter",41618]
["Infrabel","41619","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2022,2022,35,35,"2022-08-22",44568.979166666664,"2022-08-27",44568.208333333336,"5d","Periodical",null,"T","","Maintenance Z10. 51   P3 \n ",41619]
["Infrabel","41706","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2022,2022,47,47,"2022-11-14",44568.972222222219,"2022-11-19",44568.229166666664,"5d","Periodical",null,"T","","Maintenance Z9.52\r\nMise HS P3 HKV - Zone 9 AI52\r\n+ Maintenance Z.3.53 \n ",41706]
["Infrabel","41707","Lille - Charleroi","< >","Y.ECAUSSINNES","MANAGE",2022,2022,29,30,"2022-07-16",44568.25,"2022-07-17",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z9.52\r\nMise HS P4  - Zone 9 AI52 \n ",41707]
["Infrabel","41717","Athus - Meuse","< >","LUSTIN","YVOIR",2022,2022,23,24,"2022-06-04",44568.25,"2022-06-07",44568.180555555555,"3d","Continuous",null,"T","","Criblage du ballast + rails/traverses dans tunnel Fidevoye\r\n278953 \nDétournement via L130A",41717]
["Infrabel","41718","Athus - Meuse",">","LUSTIN","YVOIR",2022,2022,23,24,"2022-06-03",44568.979166666664,"2022-06-07",44568.666666666664,"4d","Continuous",null,"","ST","Criblage du ballast + rails/traverses dans tunnel Fidevoye\r\n278952 \nHKM à adapter",41718]
["Infrabel","41730","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.SOIGNIES",2022,2022,12,12,"2022-03-15",44568.034722222219,"2022-03-19",44568.1875,"4d","Periodical",null,"T","","Maintenance Z2.53 \r\nMise HS P3 HKV zone 2 AI Mons\r\nUPM 290146 \nHKM à adapter",41730]
["Infrabel","41732","Lille - Antwerpen","< >","LOKEREN","SINT-NIKLAAS",2022,2022,8,9,"2022-02-19",44568.027777777781,"2022-02-21",44568.180555555555,"2d","Continuous",null,"T","","CoLT 41732 An Van Den Abeele - Indienstname SIW (I-Build - ETCS) St Niklaas - Lokeren \r\nCoLT 42180 Elise Vereecken - ETCS L2-IL_NW_P025_03_L59_Lokeren - Sint Niklaas_IL // indienstname // PL: Arne Jacob\r\nCoLT 37244 Dirk Van Hoorebeke P143 afschaffing OW \nINFO RACC\r\nHK om te leiden",41732]
["Infrabel","41733","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.SOIGNIES",2022,2022,39,39,"2022-09-20",44568.083333333336,"2022-09-24",44568.125,"4d","Periodical",null,"T","","Maintenance Z2.53 \r\nMise HS P3 HKM zone 2 AI Mons \n ",41733]
["Infrabel","41734","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2022,2022,14,14,"2022-03-29",44568.027777777781,"2022-04-01",44568.180555555555,"3d","Periodical",null,"T","","Maintenance Z4.53 \r\nMise HS P3 HKM zone 4 AI Mons\r\nUPM 290149 \nHKM à adapter",41734]
["Infrabel","41735","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2022,2022,22,22,"2022-05-24",44568.034722222219,"2022-05-26",44568.180555555555,"2d","Periodical",null,"T","","Maintenance Z4.53 + Z02.53\r\nMise HS P3 zone 4 AI Mons\r\nUPM 278201 \nHKM à adapter",41735]
["Infrabel","41736","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2022,2022,40,40,"2022-09-27",44568.083333333336,"2022-10-01",44568.125,"4d","Periodical",null,"T","","Maintenance Z4.53 \r\nMise HS P3 HKM zone 4 AI Mons \niti dispo L130A-124A/124-117 ou L130A-130-144-161-139",41736]
["Infrabel","41745","Lille - Charleroi","< >","JURBISE","BRUGELETTE",2022,2022,13,13,"2022-03-21",44568.9375,"2022-03-26",44568.229166666664,"5d","Periodical",null,"T","","Maintenance Z.7.53\r\nMise HS en P3 zone 7 AI Mons\r\nUPM 290661 \nHKM à adapter",41745]
["Infrabel","41746","Lille - Charleroi","< >","JURBISE","BRUGELETTE",2022,2022,18,18,"2022-04-25",44568.9375,"2022-04-30",44568.201388888891,"5d","Periodical",null,"T","","Maintenance Z.7.53\r\nMise HS en P3 zone 7 AI Mons\r\nUPM 290662 \nHKM à adapter",41746]
["Infrabel","41748","Lille - Charleroi","< >","JURBISE","BRUGELETTE",2022,2022,39,39,"2022-09-20",44568.083333333336,"2022-09-24",44568.125,"4d","Periodical",null,"T","","Maintenance Z.7.53\r\nMise HS en P3 zone 7 AI Mons \n ",41748]
["Infrabel","41848","Lille - Antwerpen","< >","Y.MELSELE","ANTWERPEN-BERCHEM",2022,2022,11,12,"2022-03-12",44568.25,"2022-03-14",44568.166666666664,"2d","Continuous",null,"T","","Massificatieprogramma lijn 59\r\n+ Kennedytunnel (Cornelis Bram)\r\nBouwen van een nieuwe brug over station Antwerpen-Zuid (Annick Locquet) + L52 DOES - Deraeve Sam\r\nTCR 280043 \nHKM om te leiden.",41848]
["Infrabel","41865","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2022,2022,23,24,"2022-06-04",44568.006944444445,"2022-06-07",44568.173611111109,"3d","Continuous",null,"T","","CoLT 41865 Dieter Opsomer- Onderhoud (Deinze-Kortrijk) *pinkstermaandag inbegrepen\r\nCoLT 42115 Testen ETCS L2-IL_NW_P014_04_L75_Deinze_IL\r\nCoLT 42623 IDS ETCS L2-IL_NW_P014a_L75_Waregem - Y Zandberg_ETCS - PL: Kenny Van Heuverswijn-IDS - buitendienstste \n ",41865]
["Infrabel","41868","Lille - Antwerpen","< >","DE PINTE","Y.ZANDBERG",2022,2022,43,44,"2022-10-22",44568.013888888891,"2022-10-24",44568.166666666664,"2d","Continuous",null,"T","","CoLT 41868 An Van Den Abeele - Indienstname SIW in Deinze(I-Build ETCS)  - Waregem\r\nCoLT 41459 SI indienstname SIW (Deinze-Lichtervelde)\r\nCoLT 42137 Eric Denolin - ETCS L2-IL_NW_P014_05_L75_Deinze - Waregem_IL\r\nCoLT 42130 Eric Denolin - ETCS L2-IL_NW_P0 \n ",41868]
["Infrabel","41869","Lille - Antwerpen","< >","DE PINTE","Y.ZANDBERG",2022,2022,45,46,"2022-11-05",44568.013888888891,"2022-11-07",44568.166666666664,"2d","Continuous",null,"T","","CoLT 41869 An Van Den Abeele - Indienstname SIW in Deinze(I-Build ETCS)  - Waregem \r\nCoLT 41461 An Van Den AbeeleSI indienstname SIW (Deinze-Lichtervelde)\r\nCoLT 42138 Eric Denolin - ETCS L2-IL_NW_P014_05_L75_Deinze - Waregem_IL\r\nCoLT 42131 Eric Denolin  \n ",41869]
["Infrabel","41870","Lille - Antwerpen","< >","DE PINTE","Y.ZANDBERG",2022,2022,44,45,"2022-10-29",44568.013888888891,"2022-10-31",44568.166666666664,"2d","Continuous",null,"T","","CoLT 41870 An Van Den Abeele - Indienstname SIW in Deinze(I-Build ETCS)  - Waregem \r\nCoLT 41460 An Van Den Abeele - SI indienstname SIW (Deinze-Lichtervelde)\r\nCoLT 42132 Eric Denolin ETCS L2-IL_NW_P014_04_L75_Deinze_IL\r\nCoLT 42127 Eric Denolin ETCS L2-I \n ",41870]
["Infrabel","41940","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2022,2022,16,17,"2022-04-16",44568.25,"2022-04-17",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z10. 51   P4+\r\nUPM 288724 \nHKM à adapter\r\nVia L130C",41940]
["Infrabel","41941","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2022,2022,43,44,"2022-10-22",44568.25,"2022-10-23",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z10. 51   P4+ \n ",41941]
["Infrabel","41942","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2022,2022,44,44,"2022-10-24",44568.979166666664,"2022-10-29",44568.208333333336,"5d","Periodical",null,"T","","Maintenance Z10. 51   P3 \n ",41942]
["Infrabel","41944","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2022,2022,46,47,"2022-11-12",44568.25,"2022-11-13",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z4. 51  P4+ \n ",41944]
["Infrabel","42022","Lille - Charleroi","< >","JURBISE","ATH",2022,2022,14,14,"2022-03-28",44568.9375,"2022-04-02",44568.229166666664,"5d","Periodical",null,"T","","Maintenance Z13.54/Z7.53\r\nUPM 280966 \nHKM à adapter",42022]
["Infrabel","42024","Lille - Charleroi","< >","ATH","TOURNAI",2022,2022,7,7,"2022-02-08",44568.027777777781,"2022-02-12",44568.1875,"4d","Periodical",null,"T","","Maintenance Z5.54 \nNéant\r\nInfo racc : CCB",42024]
["Infrabel","42027","Lille - Charleroi","< >","ATH","HAVINNES",2022,2022,24,24,"2022-06-07",44568.940972222219,"2022-06-11",44568.184027777781,"4d","Periodical",null,"T","","Maintenance Z5.54\r\nUPM 281042 \nNéant",42027]
["Infrabel","42028","Lille - Charleroi","< >","ATH","TOURNAI",2022,2022,41,41,"2022-10-04",44568.006944444445,"2022-10-08",44568.190972222219,"4d","Periodical",null,"T","","Maintenance Z5.54 \n ",42028]
["Infrabel","42030","Lille - Charleroi","< >","ATH","TOURNAI",2022,2022,44,44,"2022-10-24",44568.979166666664,"2022-10-29",44568.180555555555,"5d","Periodical",null,"T","","Maintenance Z5.54 \n ",42030]
["Infrabel","42033","Lille - Charleroi","< >","TOURNAI","FROYENNES",2022,2022,11,11,"2022-03-07",44568.944444444445,"2022-03-12",44568.166666666664,"5d","Periodical",null,"T","","Maintenance Z2.54\r\nUPM 291299 \nNéant",42033]
["Infrabel","42035","Lille - Charleroi","< >","TOURNAI","FROYENNES",2022,2022,23,23,"2022-05-30",44568.944444444445,"2022-06-04",44568.166666666664,"5d","Periodical",null,"T","","Maintenance Z2.54\r\nUPM 294463 \nNéant",42035]
["Infrabel","42036","Lille - Charleroi","< >","TOURNAI","FROYENNES",2022,2022,42,42,"2022-10-11",44568.083333333336,"2022-10-15",44568.125,"4d","Periodical",null,"T","","Maintenance Z2.54 \n ",42036]
["Infrabel","42037","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","BLANDAIN-FRONTIERE",2022,2022,11,11,"2022-03-07",44568.944444444445,"2022-03-12",44568.243055555555,"5d","Periodical",null,"T","","Maintenance Z7.54\r\nUPM 291319 \nNéant",42037]
["Infrabel","42041","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","BLANDAIN-FRONTIERE",2022,2022,23,23,"2022-05-30",44568.944444444445,"2022-06-04",44568.243055555555,"5d","Periodical",null,"T","","Maintenance Z7.54\r\nUPM 294473 \nNéant",42041]
["Infrabel","42051","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","KORTRIJK",2022,2022,10,10,"2022-02-28",44568.951388888891,"2022-03-05",44568.236111111109,"5d","Periodical",null,"T","","Maintenance Z3.54\r\nUPM 291409 \nHKM à adapter",42051]
["Infrabel","42064","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2022,2022,14,14,"2022-03-29",44568.083333333336,"2022-04-02",44568.125,"4d","Periodical",null,"T","","ETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_04_L75_Deinze_IL\r\nR-284120 \nNéant",42064]
["Infrabel","42068","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2022,2022,20,20,"2022-05-10",44568.083333333336,"2022-05-14",44568.125,"4d","Periodical",null,"T","","ETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_04_L75_Deinze_IL \n ",42068]
["Infrabel","42069","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2022,2022,21,21,"2022-05-17",44568.083333333336,"2022-05-21",44568.125,"4d","Periodical",null,"T","","ETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_04_L75_Deinze_IL \n ",42069]
["Infrabel","42139","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2022,2022,12,12,"2022-03-15",44568.083333333336,"2022-03-19",44568.125,"4d","Periodical",null,"T","","ETCS L2-IL_NW_P014_06_L75_Waregem_IL\r\nETCS L2-IL_NW_P014_07_L75_Waregem - Y Zandberg_IL\r\nETCS L2-IL_NW_P014_04_L75_Deinze_IL \n ",42139]
["Infrabel","42140","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2022,2022,13,13,"2022-03-22",44568.083333333336,"2022-03-26",44568.125,"4d","Periodical",null,"T","","ETCS L2-IL_NW_P014_06_L75_Waregem_IL\r\nETCS L2-IL_NW_P014_07_L75_Waregem - Y Zandberg_IL\r\nETCS L2-IL_NW_P014_04_L75_Deinze_IL \n ",42140]
["Infrabel","42143","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2022,2022,18,18,"2022-04-26",44568.083333333336,"2022-04-30",44568.125,"4d","Periodical",null,"T","","ETCS L2-IL_NW_P014_06_L75_Waregem_IL\r\nETCS L2-IL_NW_P014_07_L75_Waregem - Y Zandberg_IL\r\nETCS L2-IL_NW_P014_04_L75_Deinze_IL \n ",42143]
["Infrabel","42144","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2022,2022,19,19,"2022-05-03",44568.083333333336,"2022-05-07",44568.125,"4d","Periodical",null,"T","","ETCS L2-IL_NW_P014_06_L75_Waregem_IL\r\nETCS L2-IL_NW_P014_07_L75_Waregem - Y Zandberg_IL\r\nETCS L2-IL_NW_P014_04_L75_Deinze_IL \n ",42144]
["Infrabel","42179","Lille - Antwerpen","< >","BEERVELDE","LOKEREN",2022,2022,50,51,"2022-12-10",44568.083333333336,"2022-12-12",44568.125,"2d","Continuous",null,"T","","CoLT 43052 An Van Den Abeele - Indienstname SIW (I-Build - ETCS) Lokeren-Beervelde\r\nCoLT 42179 Elise Vereecken - ETCS L2-IL_NW_P025_02_L59_Beervelde - Lokeren_IL // indienstname // PL: Arne Jacob \n ",42179]
["Infrabel","42284","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","FLEMALLE-HAUTE",2022,2022,21,21,"2022-05-17",44568.083333333336,"2022-05-21",44568.125,"4d","Periodical",null,"T","","ETCS1-LS_SE_L125_A-B-C_Software_Kinkempois - Flémalle Haute\r\n+ Z.19.41 P3 - Maintenance AI41\r\nUPM: 300555 \ndesserte Renory impossible\r\nHKM à adapter",42284]
["Infrabel","42305","Lille - Charleroi","< >","LUTTRE","ROUX",2022,2022,36,36,"2022-08-30",44568.020833333336,"2022-09-03",44568.229166666664,"4d","Periodical",null,"T","","Maintenance Z5.52\r\nMise HS P3 HKM - Zone 5 AI52 (Gare de Luttre)\r\n+ travaux service caténaire \n ",42305]
["Infrabel","42331","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2022,2022,47,47,"2022-11-14",44568.972222222219,"2022-11-19",44568.208333333336,"5d","Periodical",null,"T","","Maintenance Z7.52\r\nMise HS P3' - Zone 7 AI52 \n ",42331]
["Infrabel","42333","Lille - Charleroi","< >","MANAGE","LUTTRE",2022,2022,5,5,"2022-01-24",44568.972222222219,"2022-01-29",44568.21875,"5d","Periodical",null,"T","","Maintenance Z8.52\r\nMise HS P3 - Zone 8 AI52\r\nUPM 295681 \n ",42333]
["Infrabel","42334","Lille - Charleroi","< >","MANAGE","LUTTRE",2022,2022,29,29,"2022-07-11",44568.916666666664,"2022-07-16",44568.236111111109,"5d","Periodical",null,"T","","Maintenance Z8.52\r\nMise HS P3 HKV  - Zone 8 AI52 \n ",42334]
["Infrabel","42358","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2022,2022,16,16,"2022-04-11",44568.979166666664,"2022-04-16",44568.180555555555,"5d","Periodical",null,"T","","Maintenance Z13.52\r\nMise HS P3  - Zone 13 AI52\r\nUPM 294964 \nHKM à adapter",42358]
["Infrabel","42359","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2022,2022,26,26,"2022-06-20",44568.979166666664,"2022-06-25",44568.1875,"5d","Periodical",null,"T","","Maintenance Z13.52\r\nMise HS P3 - Zone 13 AI52 \n ",42359]
["Infrabel","42360","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2022,2022,42,42,"2022-10-10",44568.979166666664,"2022-10-15",44568.1875,"5d","Periodical",null,"T","","Maintenance Z13.52\r\nMise HS P3 - Zone 13 AI52\r\n+ Renouvellement PS 54.263\r\nSciage tablier L124A\r\n+ Renouvellement Rails (L112 Piéton et Y.Martinet) \n ",42360]
["Infrabel","42363","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2022,2022,28,29,"2022-07-09",44568.020833333336,"2022-07-11",44568.180555555555,"2d","Continuous",null,"T","","Démolition PS BK 54,263 Marchienne-Est\r\nRéélectrification L124/124A\r\n+ Maintenance Z13.52 P4 \nA détourner",42363]
["Infrabel","42944","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2023,2023,23,24,"2023-06-10",44568.25,"2023-06-12",44568.1875,"2d","Continuous",null,"T","","Weekend 1/3\r\nSanering + Ziftwerf (C75) \n ",42944]
["Infrabel","42946","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2023,2023,24,25,"2023-06-16",44568.993055555555,"2023-06-19",44568.1875,"3d","Continuous",null,"T","","Sanering + C75 :Y-Bethune - Moeskroen\r\n2 weekends + 1 weekend afwerking \n ",42946]
["Infrabel","42947","Lille - Antwerpen","< >","MOUSCRON","Y.BETHUNE",2023,2023,25,26,"2023-06-24",44568.25,"2023-06-26",44568.1875,"2d","Continuous",null,"T","","Weekend 3/3\r\nSanering + Ziftwerf (C75) \n ",42947]
["Infrabel","43052","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2022,2022,51,52,"2022-12-17",44568.013888888891,"2022-12-19",44568.166666666664,"2d","Continuous",null,"T","","CoLT 43052 An Van Den Abeele - Indienstname SIW (I-Build - ETCS) Lokeren-Beervelde\r\nCoLT 42179 Elise Vereecken - ETCS L2-IL_NW_P025_02_L59_Beervelde - Lokeren_IL // indienstname // PL: Arne Jacob \n ",43052]
["Infrabel","43615","Lille - Charleroi","< >","LOT","HALLE",2022,2022,20,20,"2022-05-10",44568.027777777781,"2022-05-14",44568.197916666664,"4d","Periodical",null,"T","","Vernieuwen BVL L96 + aw's L96N sp B \n ",43615]
["Infrabel","43616","Lille - Charleroi","< >","LOT","HALLE",2022,2022,21,21,"2022-05-17",44568.027777777781,"2022-05-20",44568.197916666664,"3d","Periodical",null,"T","","Vernieuwen BVL L96 + aw's L96N sp B \n ",43616]
["Infrabel","43617","Lille - Charleroi","< >","LOT","HALLE",2022,2022,25,25,"2022-06-14",44568.027777777781,"2022-06-18",44568.194444444445,"4d","Periodical",null,"T","","Vernieuwen BVL L96 + aw's L96N sp B\r\nSp A L96 tss H-N1 en NX-D1 / BL96 tss GX-N1 en O-D1 en zonder 21888. \n ",43617]
["Infrabel","43618","Lille - Charleroi","< >","LOT","HALLE",2022,2022,26,26,"2022-06-21",44568.027777777781,"2022-06-24",44568.194444444445,"3d","Periodical",null,"T","","Vernieuwen BVL L96 + aw's L96N sp B\r\nSp A L96 tss H-N1 en NX-D1 / BL96 tss GX-N1 en O-D1 en zonder 21888. \n ",43618]
["Infrabel","44045","Athus - Meuse","< >","Y.NEFFE","GENDRON-CELLES",2023,2023,9,10,"2023-03-04",44568.000694444447,"2023-03-06",44568.166666666664,"2d","Continuous",null,"T","","Basculement 25 kV jusque Neffe. \n ",44045]
["Infrabel","44074","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2022,2022,22,23,"2022-05-27",44568.25,"2022-05-30",44568.1875,"3d","Continuous",null,"T","","CoLT 44074 Frank Matthys - Onderhoud  Beervelde - Dampoort\r\nCoLT 41423 Bruno Van Damme - km 44.393 -- Beerveldse Baan\r\nCoLT 42982 David Van Hoey Vernieuwen sporen Oostakker- FGDM\r\nCoLT 46189 TUC RAIL afschaffen OW 61 Lokeren\r\n\r\nbuitenwerken ETCS SIW Lok \n ",44074]
["Infrabel","44116","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,13,14,"2022-03-26",44568.958333333336,"2022-03-27",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Straimont\r\nUPM: 275963 \nNéant",44116]
["Infrabel","44117","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,14,15,"2022-04-02",44568.958333333336,"2022-04-03",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Straimont\r\nUPM: 275965 \nNéant",44117]
["Infrabel","44118","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,17,18,"2022-04-23",44568.958333333336,"2022-04-24",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Signeulx\r\nUPM: 275970 \nNéant",44118]
["Infrabel","44119","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,10,11,"2022-03-05",44568.958333333336,"2022-03-06",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Signeulx\r\nUPM: 275849 \nHKM à adapter",44119]
["Infrabel","44160","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2022,2022,47,48,"2022-11-19",44568.25,"2022-11-21",44568.166666666664,"2d","Continuous",null,"T","","Réserve maintenance\r\n(in combinatie met TLO Sittard - Maastricht, besproken op trilaterale) \n",44160]
["Infrabel","44162","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2022,2022,34,35,"2022-08-20",44568.25,"2022-08-22",44568.166666666664,"2d","Continuous",null,"T","","Réserve maintenance\r\n(in combinatie met TLO Sittard - Roermand, besproken op trilaterale) \n",44162]
["Infrabel","44163","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2022,2022,24,25,"2022-06-11",44568.25,"2022-06-13",44568.166666666664,"2d","Continuous",null,"T","","Réserve maintenance\r\n\r\nIDS ETCS1LS L40 Liège-Visé\r\n280599 \n",44163]
["Infrabel","44449","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","SERAING",2022,2022,39,40,"2022-09-23",44568.979166666664,"2022-09-25",44568.708333333336,"2d","Continuous",null,"T","","IL for ETCS_IL-SML_SE_L125A_Flémalle-Annexe \r\nBDS voor indienstname, samenwerken niet mogelijk \n ",44449]
["Infrabel","44520","Erquelinnes - Montzen","< >","FROIDMONT","VISE",2023,2023,16,17,"2023-04-22",44568.013888888891,"2023-04-24",44568.194444444445,"2d","Continuous",null,"T","","Préparation du transfert des PN 11, 12 et 18 \n ",44520]
["Infrabel","44704","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","ANTWERPEN-NOORD-INRIT C1",2022,2022,28,28,"2022-07-03",44568.291666666664,"2022-07-03",44568.666666666664,"0d","Periodical",null,"T","","TLO-zondag : \r\nBVL-massieven maken en plaatsen van BVL-constructies , ...\r\nuren ingekort wegens oml. \n ",44704]
["Infrabel","44705","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","ANTWERPEN-NOORD-INRIT C1",2022,2022,35,35,"2022-08-21",44568.25,"2022-08-21",44568.736111111109,"0d","Periodical",null,"T","","TLO-zondag : \r\nBVL-massieven maken en plaatsen van BVL-constructies , ... \n ",44705]
["Infrabel","44706","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","ANTWERPEN-NOORD-INRIT C1",2022,2022,36,36,"2022-08-28",44568.25,"2022-08-28",44568.736111111109,"0d","Periodical",null,"T","","TLO-zondag : \r\nBVL-massieven maken en plaatsen van BVL-constructies , ... \n ",44706]
["Infrabel","44707","Namur - Antwerpen","< >","ANTWERPEN-LUCHTBAL","ANTWERPEN-NOORD-INRIT C1",2022,2022,29,29,"2022-07-10",44568.291666666664,"2022-07-10",44568.666666666664,"0d","Periodical",null,"T","","TLO-zondag : \r\nBVL-massieven maken en plaatsen van BVL-constructies , ...\r\nuren ingekort wegens oml. \n ",44707]
["Infrabel","44802","Lille - Charleroi",">","ROUX","Y.NORD",2022,2022,5,7,"2022-01-24",44568.9375,"2022-02-12",44568.229166666664,"19d","Periodical",null,"","ST","Réélectrification L. 124+L. 124A\r\nUPM 279280 \n ",44802]
["Infrabel","45044","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2023,2023,42,42,"2023-10-16",44568.958333333336,"2023-10-20",44568.1875,"4d","Periodical",null,"T","","Renouvellement des traverses Y Soignies - Braine\r\nPréparations \n ",45044]
["Infrabel","45060","Erquelinnes - Montzen","< >","LOBBES","HOURPES",2022,2022,24,24,"2022-06-07",44568.923611111109,"2022-06-11",44568.166666666664,"4d","Periodical",null,"T","","Pose seconds tabliers ponts 10 et 11\r\nTravaux préparatoires\r\nUPM 278784 \nHKM à adapter\r\nVia L117 - 124 - 96",45060]
["Infrabel","45061","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2022,2022,41,41,"2022-10-04",44568.083333333336,"2022-10-08",44568.125,"4d","Periodical",null,"T","","Pose seconds tabliers ponts 10 et 11 - Travaux de finition\r\n+ Travaux de préparation pour le renouvellement des tabliers du pont BK 125.363\r\n+ Travaux de préparation pour renouvellement chape d'étanchéité PI km 106,769 \n ",45061]
["Infrabel","45105","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2023,2023,34,36,"2023-08-21",44568.25,"2023-09-06",44568.666666666664,"16d","Continuous",null,"T","","Criblage du ballast \n ",45105]
["Infrabel","45106","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL EST",2022,2022,21,21,"2022-05-16",44568.947916666664,"2022-05-21",44568.208333333336,"5d","Periodical",null,"T","","Aménagement Le Campinaire\r\nPhase 10 : Travaux Voie sur CTL de nuits semaine\r\nBourrage révision, contrainte, pose caniveaux pistes, finitions chantier….\r\n+ Maintenance Z15.51\r\n+ Buitenwerken ETCS (Mathilde Wallez)\r\nUPM 289180\r\nART 2' \nHKM à adapter\r\nVia 117 - 124 - 130 - 140 - 147 - 96",45106]
["Infrabel","45107","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,22,22,"2022-05-23",44568.9375,"2022-05-28",44568.215277777781,"5d","Periodical",null,"T","","Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nTravaux de renouvellement des chapes d'étanchéité des PI 61.597 et 64.126 + construction de passerelles en VA et VB au droit du PI 61.597.\r\nUPM 291741 \nHKM à adapter\r\nVia 117 - 124 - 130A - 90 - 94 - 96",45107]
["Infrabel","45118","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2022,2022,30,31,"2022-07-23",44568.944444444445,"2022-07-24",44568.666666666664,"1d","Continuous",null,"T","","Maintenance Z4.53 + Révision 05E + 08AF\r\nMini CTL \n ",45118]
["Infrabel","45122","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,37,38,"2022-09-05",44568.951388888891,"2022-09-12",44568.1875,"7d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n + dépose traverses \n ",45122]
["Infrabel","45125","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,38,39,"2022-09-12",44568.951388888891,"2022-09-19",44568.1875,"7d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45125]
["Infrabel","45128","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,39,40,"2022-09-19",44568.951388888891,"2022-09-26",44568.1875,"7d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45128]
["Infrabel","45130","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,40,40,"2022-09-26",44568.951388888891,"2022-10-01",44568.1875,"5d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45130]
["Infrabel","45132","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,41,42,"2022-10-03",44568.951388888891,"2022-10-10",44568.1875,"7d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45132]
["Infrabel","45136","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,42,43,"2022-10-10",44568.951388888891,"2022-10-17",44568.1875,"7d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45136]
["Infrabel","45139","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,43,44,"2022-10-17",44568.951388888891,"2022-10-24",44568.1875,"7d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45139]
["Infrabel","45140","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,45,46,"2022-10-31",44568.951388888891,"2022-11-07",44568.1875,"7d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45140]
["Infrabel","45141","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,44,45,"2022-10-24",44568.951388888891,"2022-10-31",44568.1875,"7d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45141]
["Infrabel","45146","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,46,47,"2022-11-12",44568.951388888891,"2022-11-14",44568.1875,"2d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45146]
["Infrabel","45385","Namur - Antwerpen","< >","TILLY","FLEURUS",2022,2022,47,48,"2022-11-19",44568.958333333336,"2022-11-21",44568.166666666664,"2d","Periodical",null,"T","","Nuits pour travaux de finitions Rnvlt du Tablier métallique situé Bk 47.290 \n ",45385]
["Infrabel","45386","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,49,50,"2022-12-03",44568.25,"2022-12-04",44568.708333333336,"1d","Continuous",null,"T","","Renouvellement de traverses entre Ath et Lens P93\r\nFinitions \n ",45386]
["Infrabel","45392","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,36,37,"2022-09-03",44568.958333333336,"2022-09-04",44568.625,"1d","Continuous",null,"T","","Travaux de finition des nouvelles liaisons de Straimont \n ",45392]
["Infrabel","45514","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,47,47,"2022-11-14",44568.951388888891,"2022-11-19",44568.1875,"5d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45514]
["Infrabel","45517","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,48,48,"2022-11-21",44568.951388888891,"2022-11-26",44568.1875,"5d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45517]
["Infrabel","45518","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,49,49,"2022-11-28",44568.951388888891,"2022-12-03",44568.1875,"5d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45518]
["Infrabel","45521","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,50,50,"2022-12-05",44568.951388888891,"2022-12-09",44568.1875,"4d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45521]
["Infrabel","45523","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2022,2022,52,52,"2022-12-19",44568.951388888891,"2022-12-24",44568.1875,"5d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes\r\n+ dépose traverses \n ",45523]
["Infrabel","45539","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,40,41,"2022-10-01",44568.958333333336,"2022-10-02",44568.625,"1d","Continuous",null,"T","","Travaux de finition des nouvelles liaisons de Straimont \n ",45539]
["Infrabel","45553","Athus - Meuse","< >","HOUYET","BEAURAING",2023,2023,15,16,"2023-04-15",44568.25,"2023-04-17",44568.1875,"2d","Continuous",null,"T","","Criblage du ballast \n ",45553]
["Infrabel","45554","Athus - Meuse",">","HOUYET","BEAURAING",2023,2023,17,17,"2023-04-24",44568.1875,"2023-04-24",44568.666666666664,"0d","Periodical",null,"","ST","Criblage du ballast \n ",45554]
["Infrabel","45579","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,33,34,"2022-08-13",44568.958333333336,"2022-08-14",44568.25,"1d","Periodical",null,"T","","traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",45579]
["Infrabel","45580","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,34,34,"2022-08-14",44568.958333333336,"2022-08-15",44568.25,"1d","Periodical",null,"T","","traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",45580]
["Infrabel","45581","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2022,2022,35,36,"2022-08-27",44568.958333333336,"2022-08-28",44568.25,"1d","Periodical",null,"T","","traitement de zone boueuse, voie B, entre Bk 101.220 et 101.320 \nAxe 3 fermé suite switch 25 kV",45581]
["Infrabel","45593","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2023,2023,24,25,"2023-06-16",44568.958333333336,"2023-06-19",44568.208333333336,"3d","Continuous",null,"T","","Renouvellement des Tabliers métalliques situés Bk 43.660 et Bk 48.720\r\n+ Renouvellement des tabliers métalliques à la BK29.453 à Ottignies \n ",45593]
["Infrabel","45594","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2023,2023,25,26,"2023-06-23",44568.958333333336,"2023-06-26",44568.208333333336,"3d","Continuous",null,"T","","Renouvellement des Tabliers métalliques situés Bk 43.660 et Bk 48.720\r\nRenouvellement des tabliers métalliques à la BK29.453 à Ottignies \n ",45594]
["Infrabel","45600","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,8,9,"2022-02-19",44568.958333333336,"2022-02-20",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Signeulx\r\nUPM: 275845 \nNéant",45600]
["Infrabel","45601","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,6,7,"2022-02-05",44568.958333333336,"2022-02-06",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Straimont\r\nUPM: 275841 \nNéant",45601]
["Infrabel","45606","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2023,2023,18,19,"2023-05-06",44568.013888888891,"2023-05-08",44568.194444444445,"2d","Continuous",null,"T","","Préparation du transfert des PN 11, 12 et 18 \n ",45606]
["Infrabel","45607","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2023,2023,23,24,"2023-06-10",44568.013888888891,"2023-06-12",44568.194444444445,"2d","Continuous",null,"T","","Préparation du transfert des PN 11, 12 et 18\r\n+ Travaux sur les PN 11, 12 et 18 de L40 \n ",45607]
["Infrabel","45609","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2023,2023,24,25,"2023-06-17",44568.013888888891,"2023-06-19",44568.194444444445,"2d","Continuous",null,"T","","Préparation du transfert des PN 11, 12 et 18 \n ",45609]
["Infrabel","45610","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2023,2023,26,27,"2023-07-01",44568.013888888891,"2023-07-03",44568.194444444445,"2d","Continuous",null,"T","","Préparation du transfert des PN 11, 12 et 18 \n ",45610]
["Infrabel","45626","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2023,2023,42,43,"2023-10-20",44568.958333333336,"2023-10-23",44568.1875,"3d","Continuous",null,"T","","Renouvellement des traverses Y Soignies - Braine\r\nWE 1/3 \n ",45626]
["Infrabel","45627","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.SOIGNIES",2023,2023,43,43,"2023-10-23",44568.958333333336,"2023-10-27",44568.1875,"4d","Periodical",null,"T","","Renouvellement des traverses Y Soignies - Braine\r\nPréparation \n ",45627]
["Infrabel","45628","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.SOIGNIES",2023,2023,43,44,"2023-10-27",44568.958333333336,"2023-10-30",44568.1875,"3d","Continuous",null,"T","","Renouvellement des traverses Y Soignies - Braine\r\nWE 2/3 \n ",45628]
["Infrabel","45629","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2023,2023,44,45,"2023-11-03",44568.958333333336,"2023-11-06",44568.1875,"3d","Continuous",null,"T","","Renouvellement des traverses Y Soignies - Braine\r\nWE 3/3 \n ",45629]
["Infrabel","45630","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.SOIGNIES",2023,2023,44,44,"2023-10-30",44568.958333333336,"2023-11-03",44568.1875,"4d","Periodical",null,"T","","Renouvellement des traverses Y Soignies - Braine\r\nPréparation \n ",45630]
["Infrabel","45645","Athus - Meuse",">","HOUYET","BEAURAING",2023,2023,16,16,"2023-04-17",44568.1875,"2023-04-17",44568.666666666664,"0d","Periodical",null,"","ST","Criblage du ballast \n ",45645]
["Infrabel","45646","Athus - Meuse","< >","ANSEREMME","BEAURAING",2023,2023,16,17,"2023-04-22",44568.25,"2023-04-24",44568.166666666664,"2d","Continuous",null,"T","","Criblage du ballast\r\nRemplacement de deux tabliers métalliques à pose directe VA à la bk 7,591 - Préparations\r\nInterventions diverses AS et PN Houyet + traitement zone boueuse (La voie 2 en gare de Houyet fait partie de la demande de mise H.S.) \n ",45646]
["Infrabel","45664","Athus - Meuse",">","VIRTON","HALANZY",2022,2022,27,28,"2022-07-02",44568.958333333336,"2022-07-03",44568.625,"1d","Continuous",null,"","ST","Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",45664]
["Infrabel","45666","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,27,28,"2022-07-02",44568.958333333336,"2022-07-03",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",45666]
["Infrabel","45667","Athus - Meuse","< >","VIRTON","HALANZY",2022,2022,28,29,"2022-07-09",44568.958333333336,"2022-07-10",44568.625,"1d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",45667]
["Infrabel","45668","Athus - Meuse",">","VIRTON","HALANZY",2022,2022,28,29,"2022-07-09",44568.958333333336,"2022-07-11",44568.625,"2d","Continuous",null,"","ST","Travaux préparatoires pose des nouvelles liaisons de Signeulx \n ",45668]
["Infrabel","45685","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,49,50,"2022-12-03",44568.958333333336,"2022-12-05",44568.208333333336,"2d","Continuous",null,"T","","Travaux de finition des nouvelles liaisons de Straimont\r\nCTL du sam. 23h00 au dim. 15h00 et du dim. 23h00 au lun. 5h00 \n ",45685]
["Infrabel","45686","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2022,2022,11,12,"2022-03-12",44568.958333333336,"2022-03-14",44568.208333333336,"2d","Continuous",null,"T","","Travaux préparatoires pose des nouvelles liaisons de Straimont\r\nUPM: 275850 \nNéant",45686]
["Infrabel","45688","Lille - Charleroi","< >","MANAGE","LUTTRE",2022,2022,3,3,"2022-01-10",44568.972222222219,"2022-01-15",44568.21875,"5d","Periodical",null,"T","","Maintenance Z8.52\r\nMise HS P3 HKV - Zone 8 AI52\r\nUPM 293564 \n ",45688]
["Infrabel","45689","Lille - Charleroi","< >","MANAGE","LUTTRE",2022,2022,50,50,"2022-12-05",44568.972222222219,"2022-12-10",44568.21875,"5d","Periodical",null,"T","","Maintenance Z8.52\r\nMise HS P3 HKV - Zone 8 AI52\r\n+ travaux service caténaire \n ",45689]
["Infrabel","45706","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2023,2023,37,38,"2023-09-16",44568.041666666664,"2023-09-18",44568.1875,"2d","Continuous",null,"T","","OVERWEGVERNIEUWING\r\n\r\nOude Landen \n ",45706]
["Infrabel","45707","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2023,2023,38,39,"2023-09-23",44568.041666666664,"2023-09-25",44568.1875,"2d","Continuous",null,"T","","OVERWEGVERNIEUWING\r\n\r\nOude Landen \n ",45707]
["Infrabel","45722","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE-MARCHANDISE","TAMINES",2022,2022,33,34,"2022-08-12",44568.979166666664,"2022-08-16",44568.1875,"4d","Continuous",null,"T","","CTL 3 jours pour renouvellement de la chape d'étanchéité du PI 78.887 - compatible avec la demande 30893 au niveau des travaux à réaliser\r\n+ Zone 19.51 - Laurent Benoit \n ",45722]
["Infrabel","45723","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE-MARCHANDISE","TAMINES",2022,2022,32,33,"2022-08-05",44568.979166666664,"2022-08-08",44568.1875,"3d","Continuous",null,"T","","CTL préparation - renouvellement de la chape d'étanchéité du PI 78.887 - compatible avec 29749 au niveau travaux \n ",45723]
["Infrabel","45916","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2024,2024,10,11,"2024-03-09","2022-01-07T01:00:00","2024-03-11","2022-01-07T04:30:00","2d","Continuous",null,"T","","VERNIEUWING WISSELS ESSEN\r\n3 weekends gevraagd, dienen nog trilateraal afgestemd.\r\nWij voorzien voorjaar 2024 om niet in het vaarwater te zitten van de grote werken op het Duitse net (najaar 2024 tot voorjaar 2026). \n ",45916]
["Infrabel","45917","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN-GRENS",2024,2024,11,12,"2024-03-16","2022-01-07T01:00:00","2024-03-18","2022-01-07T04:30:00","2d","Continuous",null,"T","","VERNIEUWING WISSELS ESSEN\r\n3 weekends gevraagd, dienen nog trilateraal afgestemd.\r\nWij voorzien voorjaar 2024 om niet in het vaarwater te zitten van de grote werken op het Duitse net (najaar 2024 tot voorjaar 2026). \n ",45917]
["Infrabel","45918","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2024,2024,12,13,"2024-03-23","2022-01-07T01:00:00","2024-03-25","2022-01-07T04:30:00","2d","Continuous",null,"T","","VERNIEUWING WISSELS ESSEN\r\n3 weekends gevraagd, dienen nog trilateraal afgestemd.\r\nWij voorzien voorjaar 2024 om niet in het vaarwater te zitten van de grote werken op het Duitse net (najaar 2024 tot voorjaar 2026). \n ",45918]
["Infrabel","46033","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2022,2022,17,18,"2022-04-22",44568.958333333336,"2022-04-25",44568.208333333336,"3d","Continuous",null,"T","","CoLT 46033 Dieter Opsomer - Onderhoud\r\nGekoppeld aan werken op het Franse net \n ",46033]
["Infrabel","46034","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2022,2022,47,48,"2022-11-19",44568.25,"2022-11-21",44568.208333333336,"2d","Continuous",null,"T","","CoLT 46034 Dieter Opsomer - Onderhoud\r\nGekoppeld aan werken op het Franse net\r\n(nacht R5/R6 niet inbegrepen wegens geen CBP van toepassing) \n ",46034]
["Infrabel","46045","Athus - Meuse","< >","BERTRIX","SAINT-VINCENT-BELLEFONTAINE",2022,2022,21,22,"2022-05-21",44568.951388888891,"2022-05-23",44568.243055555555,"2d","Periodical",null,"T","","Kirow pour nouveau trapèze de Straimont\r\nUPM: 291721 \nNéant",46045]
["Infrabel","46061","Lille - Charleroi","< >","LOT","HALLE",2022,2022,18,18,"2022-04-26",44568.027777777781,"2022-04-30",44568.197916666664,"4d","Periodical",null,"T","","Vernieuwen BVL L96 + aw's L96N sp B.\r\nSp AL96 tss H-N1 en NX-D1 / BL96 tss GX-N1 en aw 43BE en zonder 21888. \n ",46061]
["Infrabel","46062","Lille - Charleroi","< >","LOT","HALLE",2022,2022,23,23,"2022-05-31",44568.027777777781,"2022-06-04",44568.194444444445,"4d","Periodical",null,"T","","Vernieuwen BVL L96 + aw's L96N sp B\r\nSp A L96 tss H-N1 en NX-D1 / BL96 tss GX-N1 en O-D1 en zonder 21888. \n ",46062]
["Infrabel","46254","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2022,2022,19,19,"2022-05-01",44568.027777777781,"2022-05-02",44568.180555555555,"1d","Periodical",null,"T","","Modernisation Gare d'Athus Phase 2=> Remplacement consoles caténaire voie 702\r\nUPM N° 306619 \nInfo Racc 3 : 1.N.7/2 (TCA Wissel 5BU)\r\nInfo Racc 361 : 1.N.7/1 (TCA Wissel 10BU)",46254]
["Infrabel","46255","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2022,2022,20,20,"2022-05-08",44568.027777777781,"2022-05-09",44568.180555555555,"1d","Periodical",null,"T","","Modernisation Gare d'Athus Phase 2=> Remplacement consoles caténaire voie 702\r\nUPM N° 306639 \nInfo Racc 3 : 1.N.7/2 (TCA Wissel 5BU)\r\nInfo Racc 361 : 1.N.7/1 (TCA Wissel 10BU)",46255]
["Infrabel","46256","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2022,2022,21,21,"2022-05-15",44568.027777777781,"2022-05-16",44568.180555555555,"1d","Periodical",null,"T","","Modernisation Gare d'Athus Phase 2=> Remplacement consoles caténaire voie 702\r\nUPM N° 306640 \nInfo Racc 3 : 1.N.7/2 (TCA Wissel 5BU)\r\nInfo Racc 361 : 1.N.7/1 (TCA Wissel 10BU)",46256]
["Infrabel","46257","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2022,2022,22,22,"2022-05-22",44568.027777777781,"2022-05-23",44568.180555555555,"1d","Periodical",null,"T","","Modernisation Gare d'Athus Phase 2=> Remplacement consoles caténaire voie 702\r\nUPM N° 306641 \nInfo Racc 3 : 1.N.7/2 (TCA Wissel 5BU)\r\nInfo Racc 361 : 1.N.7/1 (TCA Wissel 10BU)",46257]
["Infrabel","46272","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2022,2022,14,14,"2022-03-28",44568.975694444445,"2022-04-02",44568.177083333336,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nKortrijk rooster kant Y.Zandberg inbegrepen\r\nDeinze sporen 1+2 inbegrepen\r\n+\r\nL89 onderhoud\r\n+\r\nETCS L2-IL_NW_P014_06_L75_Waregem_IL\r\nETCS L2-IL_NW_P014_07_L75_Waregem - Y Zandberg_IL\r\nETCS L2-IL_NW_P014_04_L75_Deinze_IL\r\nR-284385 \n66 - frontverandering Brugge - 50A\r\nHKM à adapter",46272]
["Infrabel","46273","Lille - Antwerpen","< >","DEINZE","GENT-SINT-PIETERS",2022,2022,12,12,"2022-03-14",44568.979166666664,"2022-03-19",44568.1875,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nSP III-IV-V in Deinze inbegrepen tot inritseinen L73\r\n+\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_04_L75_De \n66 - frontverandering Brugge - 50A",46273]
["Infrabel","46352","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2024,2024,2,51,"2024-01-08",44568.951388888891,"2024-12-15",44568.1875,"342d","Periodical",null,"T","","Modernisation de la ligne 161 entre Gembloux et Rhisnes \n ",46352]
["Infrabel","46441","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.SOIGNIES",2022,2022,6,6,"2022-01-31",44568.979166666664,"2022-02-05",44568.190972222219,"5d","Periodical",null,"T","","Maintenance Z2 Braine-le-Compte - Y.Soignies\r\nP3 HKV\r\nVoie V et VI à FBC HT\r\nUPM 290121 \n ",46441]
["Infrabel","46535","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2023,2023,33,34,"2023-08-19",44568.25,"2023-08-20",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z9.52 - Mise HS P4  \r\n+ Maintenance Z.3.53 en P4 \n ",46535]
["Infrabel","46607","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2024,2024,13,15,"2024-03-29","2022-01-07T23:50:00","2024-04-08","2022-01-07T04:40:00","10d","Continuous",null,"T","","RER\r\nTravaux plateformes, voies, signalisation et caténaires à Watermael et sur le tronçon Bakenbos-Ottignies \n ",46607]
["Infrabel","46690","Lille - Antwerpen","< >","DEINZE","GENT-SINT-PIETERS",2022,2022,13,13,"2022-03-21",44568.979166666664,"2022-03-26",44568.1875,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nSP III-IV-V in Deinze inbegrepen tot inritseinen L73\r\n+\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_04_L75_De \nINFO RACC\r\nHK om te leiden\r\n66 - frontverandering Brugge - 50A",46690]
["Infrabel","46691","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2022,2022,20,20,"2022-05-09",44568.975694444445,"2022-05-14",44568.177083333336,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nKortrijk rooster kant Y.Zandberg inbegrepen\r\nDeinze sporen 1+2 inbegrepen\r\n+\r\nETCS L2-IL_NW_P014_06_L75_Waregem_IL\r\nETCS L2-IL_NW_P014_07_L75_Waregem - Y Zandberg_IL\r\nETCS L2-IL_NW_P014_04_L75_Deinze_IL \n66 - frontverandering Brugge - 50A",46691]
["Infrabel","46692","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2022,2022,21,21,"2022-05-16",44568.975694444445,"2022-05-21",44568.177083333336,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nKortrijk rooster kant Y.Zandberg inbegrepen\r\nDeinze sporen 1+2 inbegrepen\r\n+\r\nETCS L2-IL_NW_P014_06_L75_Waregem_IL\r\nETCS L2-IL_NW_P014_07_L75_Waregem - Y Zandberg_IL\r\nETCS L2-IL_NW_P014_04_L75_Deinze_IL \n66 - frontverandering Brugge - 50A",46692]
["Infrabel","46693","Lille - Antwerpen","< >","DEINZE","GENT-SINT-PIETERS",2022,2022,18,18,"2022-04-25",44568.979166666664,"2022-04-30",44568.1875,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nSP III-IV-V in Deinze inbegrepen tot inritseinen L73\r\n+\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_04_L75_De \n66 - frontverandering Brugge - 50A",46693]
["Infrabel","46694","Lille - Antwerpen","< >","DEINZE","GENT-SINT-PIETERS",2022,2022,19,19,"2022-05-02",44568.979166666664,"2022-05-07",44568.1875,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nSP III-IV-V in Deinze inbegrepen tot inritseinen L73\r\n+\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_04_L75_De \n66 - frontverandering Brugge - 50A",46694]
["Infrabel","46695","Lille - Antwerpen","< >","DEINZE","GENT-SINT-PIETERS",2022,2022,22,22,"2022-05-23",44568.979166666664,"2022-05-26",44568.1875,"3d","Periodical",null,"T","","Reservatie onderhoud\r\nSP III-IV-V in Deinze inbegrepen tot inritseinen L73\r\n\r\n+\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_04_L75_ \n66 - frontverandering Brugge - 50A",46695]
["Infrabel","46696","Lille - Antwerpen","< >","DEINZE","GENT-SINT-PIETERS",2022,2022,37,37,"2022-09-05",44568.979166666664,"2022-09-10",44568.1875,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nSP III-IV-V in Deinze inbegrepen tot inritseinen L73\r\n\r\n+\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL \n66 - frontverandering Brugge - 50A",46696]
["Infrabel","46697","Lille - Antwerpen","< >","DEINZE","GENT-SINT-PIETERS",2022,2022,39,39,"2022-09-19",44568.979166666664,"2022-09-24",44568.1875,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nSP III-IV-V in Deinze inbegrepen tot inritseinen L73\r\n+\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL \n66 - frontverandering Brugge - 50A",46697]
["Infrabel","46698","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2022,2022,38,38,"2022-09-12",44568.975694444445,"2022-09-17",44568.177083333336,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nKortrijk rooster kant Y.Zandberg inbegrepen\r\nDeinze sporen 1+2 inbegrepen\r\n+\r\nETCS L2-IL_NW_P014_05_L75_Deinze - Waregem_IL \n66 - frontverandering Brugge - 50A",46698]
["Infrabel","46699","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2022,2022,40,40,"2022-09-26",44568.975694444445,"2022-10-01",44568.177083333336,"5d","Periodical",null,"T","","Reservatie onderhoud\r\nKortrijk rooster kant Y.Zandberg inbegrepen\r\nDeinze sporen 1+2 inbegrepen\r\n+ L89 Reservering werken SI\r\n+ L89 ETCS1-LS_NW_L89_L86_Software_Kortrijk - Oudenaarde - Ronse\r\n+ ETCS L2-IL_NW_P014_05_L75_Deinze - Waregem_IL \n66 - frontverandering Brugge - 50A",46699]
["Infrabel","46745","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,13,13,"2022-03-21",44568.979166666664,"2022-03-25",44568.177083333336,"4d","Periodical",null,"T","","Renouvellement des traverses Bi-blocs P93\r\nPréparations/finitions\r\n+ Maintenance Z.5.53\r\nMise HS en P3 HKV zone 5 AI Mons\r\nUPM 278678 \nHKM à adpater\r\nVia L116 - 117 - 118 - 130A",46745]
["Infrabel","46746","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,14,14,"2022-03-28",44568.979166666664,"2022-04-01",44568.177083333336,"4d","Periodical",null,"T","","Renouvellement des traverses Bi-blocs P93\r\nPréparations/finitions\r\nUPM 278593 \nHKM à adapter\r\nVia L116 - 117 - 118 - 130A",46746]
["Infrabel","46747","Lille - Charleroi","< >","JURBISE","MONS",2022,2022,15,15,"2022-04-04",44568.979166666664,"2022-04-08",44568.177083333336,"4d","Periodical",null,"T","","Renouvellement des traverses Bi-blocs P93\r\nPréparations/finitions\r\nUPM 278674 \nHKM à adapter\r\nVia L116 - 117 - 118 - 130A",46747]
["Infrabel","46805","Athus - Meuse","< >","BEAURAING","BERTRIX",2024,2024,26,27,"2024-06-28","2022-01-07T23:00:00","2024-07-01","2022-01-07T04:30:00","3d","Continuous",null,"T","","Renouvellement traverses (P93)\r\nBourrage révision \n ",46805]
["Infrabel","46809","Athus - Meuse","< >","BEAURAING","BERTRIX",2024,2024,27,28,"2024-07-05","2022-01-07T23:00:00","2024-07-08","2022-01-07T04:30:00","3d","Continuous",null,"T","","Renouvellement traverses (P93) \n ",46809]
["Infrabel","46810","Athus - Meuse","< >","BEAURAING","BERTRIX",2024,2024,28,29,"2024-07-12","2022-01-07T23:00:00","2024-07-15","2022-01-07T04:30:00","3d","Continuous",null,"T","","Renouvellement traverses (P93)\r\nBourrage de révision \n ",46810]
["Infrabel","46811","Athus - Meuse","< >","BEAURAING","BERTRIX",2024,2024,33,34,"2024-08-16","2022-01-07T23:00:00","2024-08-19","2022-01-07T04:30:00","3d","Continuous",null,"T","","Renouvellement traverses (P93)\r\nRq 333 : conflit travaux Artère NE les we 25 – 26 – 27 - 33 et  34  - demande de déplacement de la part de la SNCF\r\n+ conflit L130A \n ",46811]
["Infrabel","46904","Namur - Antwerpen",">","TAMINES","CHATELET-GRIL EST",2022,2022,17,17,"2022-04-18",44568.9375,"2022-04-23",44568.229166666664,"5d","Periodical",null,"","ST","Aménagement Le Campinaire Phase 9\r\nUPM 288891 \nHKM à adapter",46904]
["Infrabel","46911","Lille - Charleroi","< >","MONS","QUEVY",2024,2024,8,9,"2024-02-23",44568.9375,"2024-02-26",44568.194444444445,"3d","Continuous",null,"T","","Renouvellement des appareils de Quévy (04I-03I-06I) \n ",46911]
["Infrabel","46912","Lille - Charleroi","< >","MONS","QUEVY",2024,2024,7,8,"2024-02-16",44568.9375,"2024-02-19",44568.194444444445,"3d","Continuous",null,"T","","Renouvellement des appareils de Quévy (04I-03I-06I) \n ",46912]
["Infrabel","46977","Erquelinnes - Montzen","< >","HUY","FLEMALLE-HAUTE",2023,2023,20,21,"2023-05-20",44568.020833333336,"2023-05-21",44568.708333333336,"1d","Continuous",null,"T","","Renouvellement des appareils de voies d'Engis\r\nPhase 2 - WE 2/3 - AW 02AT / 02BT / 03BT (+  assainissement)\r\n+ Renouvellement des traverses entre AS 02AT et 05BT\r\n+ Raccordement sur les nouveaux AS 05AT/05BT\r\n+ Renouvellement AS 14AS à Hermalle sous-Huy \n ",46977]
["Infrabel","46978","Erquelinnes - Montzen","< >","HUY","FLEMALLE-HAUTE",2023,2023,21,22,"2023-05-27",44568.020833333336,"2023-05-28",44568.708333333336,"1d","Continuous",null,"T","","Renouvellement des appareils de voies d'Engis\r\nPhase 2 - WE 3/3 - AW 02AT / 02BT / 03BT (+  assainissement)\r\n+ Renouvellement des traverses entre AS 02AT et 05BT\r\n+ Raccordement sur les nouveaux AS 05AT/05BT\r\n+ Renouvellement AS 14AS à Hermalle sous-Huy \n ",46978]
["Infrabel","47028","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2022,2022,9,9,"2022-02-21",44568.986111111109,"2022-02-26",44568.1875,"5d","Periodical",null,"T","","reservering onderhoud\r\nR-286583-01\r\naanvangsuur werken aangepast naar 23u50 voor doorrit E744 te Lokeren. \nINFO RACC\r\nHK om te leiden",47028]
["Infrabel","47105","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2023,2023,31,31,"2023-07-30",44568.625,"2023-07-31",44568.583333333336,"1d","Continuous",null,"","ST","Renouvellement traverses St-Vincent : P93 W-E n°8.\r\nRéglage des contraintes \nPas de trafic possible durant le SAVU du lundi 6h-9h",47105]
["Infrabel","47106","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,29,30,"2023-07-22",44568.25,"2023-07-23",44568.625,"1d","Continuous",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°7.\r\nRéglage des contraintes \n ",47106]
["Infrabel","47107","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2023,2023,30,30,"2023-07-23",44568.625,"2023-07-24",44568.583333333336,"1d","Continuous",null,"","ST","Renouvellement traverses St-Vincent : P93 W-E n°7.\r\nRéglage des contraintes \nPas de trafic possible durant le SAVU du lundi 6h-9h",47107]
["Infrabel","47108","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,28,29,"2023-07-15",44568.25,"2023-07-16",44568.625,"1d","Continuous",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°6.\r\nRéglage des contraintes \n ",47108]
["Infrabel","47109","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2023,2023,29,29,"2023-07-16",44568.625,"2023-07-17",44568.583333333336,"1d","Continuous",null,"","ST","Renouvellement traverses St-Vincent : P93 W-E n°6.\r\nRéglage des contraintes \nPas de trafic possible durant le SAVU du lundi 6h-9h",47109]
["Infrabel","47110","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,27,28,"2023-07-08",44568.25,"2023-07-09",44568.625,"1d","Continuous",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°5.\r\nRéglage des contraintes \n ",47110]
["Infrabel","47111","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,28,28,"2023-07-10",44568.375,"2023-07-10",44568.666666666664,"0d","Periodical",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°5.\r\nRéglage des contraintes \n ",47111]
["Infrabel","47112","Athus - Meuse",">","FLORENVILLE","VIRTON",2023,2023,27,28,"2023-07-08",44568.25,"2023-07-10",44568.666666666664,"2d","Continuous",null,"","ST","Renouvellement traverses St-Vincent : P93 W-E n°5.\r\nRéglage des contraintes \nPas de trafic possible durant le SAVU",47112]
["Infrabel","47113","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,27,27,"2023-07-03",44568.375,"2023-07-03",44568.666666666664,"0d","Periodical",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°4.\r\nP93 \n ",47113]
["Infrabel","47114","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,26,27,"2023-06-30",44568.916666666664,"2023-07-03",44568.25,"3d","Continuous",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°4.\r\nP93\r\nRenouvellement PI 116615 - Saint-Vincent - Virton \n ",47114]
["Infrabel","47115","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2023,2023,26,27,"2023-06-30",44568.916666666664,"2023-07-03",44568.666666666664,"3d","Continuous",null,"","ST","Renouvellement traverses St-Vincent : P93 W-E n°4.\r\nP93 \n ",47115]
["Infrabel","47116","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,25,26,"2023-06-23",44568.916666666664,"2023-06-26",44568.25,"3d","Continuous",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°3.\r\nP93 \n ",47116]
["Infrabel","47117","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2023,2023,25,26,"2023-06-23",44568.916666666664,"2023-06-26",44568.666666666664,"3d","Continuous",null,"","ST","Renouvellement traverses St-Vincent : P93 W-E n°3.\r\nP93 \nPas de trafic possible durant le SAVU",47117]
["Infrabel","47118","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,26,26,"2023-06-26",44568.375,"2023-06-26",44568.666666666664,"0d","Periodical",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°3.\r\nP93 \n ",47118]
["Infrabel","47119","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,24,25,"2023-06-16",44568.916666666664,"2023-06-19",44568.25,"3d","Continuous",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°2.\r\nP93 \n ",47119]
["Infrabel","47120","Athus - Meuse",">","FLORENVILLE","VIRTON",2023,2023,24,25,"2023-06-16",44568.916666666664,"2023-06-19",44568.666666666664,"3d","Continuous",null,"","ST","Renouvellement traverses St-Vincent : P93 W-E n°2.\r\nP93 \nPas de trafic possible durant le SAVU",47120]
["Infrabel","47121","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,25,25,"2023-06-19",44568.375,"2023-06-19",44568.666666666664,"0d","Periodical",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°2.\r\nP93 \n ",47121]
["Infrabel","47122","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,24,24,"2023-06-12",44568.375,"2023-06-12",44568.666666666664,"0d","Periodical",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°1.\r\nP93 \n ",47122]
["Infrabel","47123","Athus - Meuse","< >","BERTRIX","VIRTON",2023,2023,23,24,"2023-06-09",44568.916666666664,"2023-06-12",44568.25,"3d","Continuous",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°1.\r\nP93 \n ",47123]
["Infrabel","47124","Athus - Meuse",">","FLORENVILLE","VIRTON",2023,2023,23,24,"2023-06-09",44568.916666666664,"2023-06-12",44568.666666666664,"3d","Continuous",null,"","ST","Renouvellement traverses St-Vincent : P93 W-E n°1.\r\nP93 \nPas de trafic possible durant le SAVU",47124]
["Infrabel","47168","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,2,3,"2024-01-13",44568.958333333336,"2024-01-15",44568.208333333336,"2d","Continuous",null,"T","","Electrification 2 x 25 kV \n ",47168]
["Infrabel","47169","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,3,4,"2024-01-20",44568.958333333336,"2024-01-22",44568.208333333336,"2d","Continuous",null,"T","","Electrification 2 x 25 kV \n ",47169]
["Infrabel","47170","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,4,5,"2024-01-27",44568.958333333336,"2024-01-29",44568.208333333336,"2d","Continuous",null,"T","","Electrification 2 x 25 kV \n ",47170]
["Infrabel","47171","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,5,6,"2024-02-03",44568.958333333336,"2024-02-05",44568.208333333336,"2d","Continuous",null,"T","","Electrification 2 x 25 kV \n ",47171]
["Infrabel","47172","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,6,7,"2024-02-10",44568.958333333336,"2024-02-12",44568.208333333336,"2d","Continuous",null,"T","","Electrification 2 x 25 kV \n ",47172]
["Infrabel","47173","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,7,8,"2024-02-17",44568.958333333336,"2024-02-19",44568.208333333336,"2d","Continuous",null,"T","","Electrification 2 x 25 kV \n ",47173]
["Infrabel","47174","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,8,9,"2024-02-24","2022-01-07T23:00:00","2024-02-26","2022-01-07T05:00:00","2d","Continuous",null,"T","","Electrification 2 x 25 kV \n ",47174]
["Infrabel","47206","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,39,40,"2024-09-28","2022-01-07T23:00:00","2024-09-30","2022-01-07T05:00:00","2d","Continuous",null,"T","","Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix \n ",47206]
["Infrabel","47207","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,40,41,"2024-10-05","2022-01-07T23:00:00","2024-10-07","2022-01-07T05:00:00","2d","Continuous",null,"T","","Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix \n ",47207]
["Infrabel","47210","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,41,42,"2024-10-12","2022-01-07T23:00:00","2024-10-14","2022-01-07T05:00:00","2d","Continuous",null,"T","","Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix \n ",47210]
["Infrabel","47211","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,42,43,"2024-10-19","2022-01-07T23:00:00","2024-10-21","2022-01-07T05:00:00","2d","Continuous",null,"T","","Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix \n ",47211]
["Infrabel","47214","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,43,44,"2024-10-26","2022-01-07T23:00:00","2024-10-28","2022-01-07T05:00:00","2d","Continuous",null,"T","","Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix \n ",47214]
["Infrabel","47280","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,21,21,"2024-05-20","2022-01-07T09:00:00","2024-05-24","2022-01-07T15:30:00","4d","Periodical",null,"T","","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nPréparations \nInfo Racc : raccordement inaccessible",47280]
["Infrabel","47299","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,9,10,"2024-03-01","2022-01-07T23:10:00","2024-03-04","2022-01-07T04:00:00","3d","Continuous",null,"T","","TLO-Weekend voor onderhouds werken\r\nminimum van 2 weekends per jaar, 1 weekend maart/april + 1 weekend oktober/november\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken mogelijk \n ",47299]
["Infrabel","47300","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,41,42,"2024-10-11","2022-01-07T23:10:00","2024-10-14","2022-01-07T04:00:00","3d","Continuous",null,"T","","TLO-Weekend voor onderhouds werken\r\nminimum van 2 weekends per jaar, 1 weekend maart/april + 1 weekend oktober/november\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken mogelijk \n ",47300]
["Infrabel","47301","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,4,4,"2024-01-22",44568.965277777781,"2024-01-27",44568.166666666664,"5d","Periodical",null,"T","","TLO-nachten voor TESTEN ETCS\r\n1 week aansluitend nachten in januari\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk \n ",47301]
["Infrabel","47302","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,20,20,"2024-05-13","2022-01-07T23:10:00","2024-05-18","2022-01-07T04:00:00","5d","Periodical",null,"T","","TLO-nachten voor TESTEN ETCS\r\n2 weken aansluitend nachten in mei 2024\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk \n ",47302]
["Infrabel","47303","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,37,38,"2024-09-13","2022-01-07T23:10:00","2024-09-16","2022-01-07T04:00:00","3d","Continuous",null,"T","","TLO-weekend voor in dienst stellen ETCS\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk \n ",47303]
["Infrabel","47304","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,21,21,"2024-05-20","2022-01-07T23:10:00","2024-05-25","2022-01-07T04:00:00","5d","Periodical",null,"T","","TLO-nachten voor TESTEN ETCS\r\n2 weken aansluitend nachten in mei 2024\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk \n ",47304]
["Infrabel","47313","Lille - Antwerpen","< >","LAUWE","MOUSCRON",2023,2023,41,41,"2023-10-09",44568.965277777781,"2023-10-14",44568.166666666664,"5d","Periodical",null,"T","","TLO-nachten voor TESTEN ETCS\r\n2 weken aansluitend nachten tussen 06/06/23 en 31/03/24  +/- 4 maanden later 1X TLO-weekend (3 dagen) voor IDS \r\nTLO-weekend voorzien 30-31maart+1 april\r\nbuiten dienst stelling station Moeskroen inbegrepen tot Lauwe\r\nsamenw \n ",47313]
["Infrabel","47314","Lille - Antwerpen","< >","LAUWE","MOUSCRON",2023,2023,42,42,"2023-10-16",44568.965277777781,"2023-10-21",44568.166666666664,"5d","Periodical",null,"T","","TLO-nachten voor TESTEN ETCS\r\n2 weken aansluitend nachten tussen 06/06/23 en 31/03/24  +/- 4 maanden later 1X TLO-weekend (3 dagen) voor IDS \r\nTLO-weekend voorzien 30-31maart+1 april\r\nbuiten dienst stelling station Moeskroen inbegrepen tot Lauwe\r\nsamenw \n ",47314]
["Infrabel","47327","Lille - Antwerpen","< >","LAUWE","MOUSCRON-FRONTIERE",2024,2024,13,14,"2024-03-29","2022-01-07T23:10:00","2024-04-02","2022-01-07T04:00:00","4d","Continuous",null,"T","","TLO-nachten voor TESTEN ETCS\r\n2 weken aansluitend nachten tussen 06/06/23 en 31/03/24  +/- 4 maanden later 1X TLO-weekend (3 dagen) voor IDS \r\nTLO-weekend voorzien 30-31maart+1 april\r\nbuiten dienst stelling station Moeskroen inbegrepen tot Lauwe\r\nsamenw \n ",47327]
["Infrabel","47338","Athus - Meuse","< >","ANSEREMME","GENDRON-CELLES",2024,2024,23,24,"2024-06-07","2022-01-07T23:00:00","2024-06-09","2022-01-07T16:00:00","2d","Continuous",null,"T","","Mise en service CV Jade Anseremme-Gendron. \n ",47338]
["Infrabel","47366","Athus - Meuse","< >","VIRTON","Y.AUBANGE",2023,2023,41,42,"2023-10-14",44568.25,"2023-10-15",44568.625,"1d","Continuous",null,"T","","Renouvellement ballast Halanzy : C75 (Musson) --- Phase 1.1. WE 3\r\nRéglage des contraintes\r\n+ traitement de zone boueuse VB Bk 135 800 à 135 900 \n ",47366]
["Infrabel","47368","Athus - Meuse","< >","Y.AUBANGE","VIRTON",2023,2023,44,45,"2023-11-04",44568.25,"2023-11-05",44568.625,"1d","Continuous",null,"T","","Renouvellement ballast Halanzy : C75 (Aix-sur-Cloie) --- Phase 2.1. WE 6\r\nRéglage des contraintes\r\n+ traitement de zone boueuse VA Bk 133 900 \n ",47368]
["Infrabel","47393","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2024,2024,38,39,"2024-09-21","2022-01-07T01:00:00","2024-09-23","2022-01-07T04:30:00","2d","Continuous",null,"T","","OVERWEGVERNIEUWING \n ",47393]
["Infrabel","47394","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2024,2024,39,40,"2024-09-28","2022-01-07T01:00:00","2024-09-30","2022-01-07T04:30:00","2d","Continuous",null,"T","","Vernieuwen van overwegen \n ",47394]
["Infrabel","47406","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,13,14,"2024-03-29","2022-01-07T23:30:00","2024-04-01","2022-01-07T05:30:00","3d","Continuous",null,"T","","Aménagement gare de Floreffe\r\nC75 pour rectification tracé BK 68.300 à 69.500\r\nWE 1/6\r\nDossier de concertation validé le 26 octobre 2021 \n ",47406]
["Infrabel","47407","Namur - Antwerpen",">","FRANIERE","Y.FLAWINNE",2024,2024,14,14,"2024-04-01","2022-01-07T05:30:00","2024-04-05","2022-01-07T23:30:00","4d","Continuous",null,"","ST","Aménagement gare de Floreffe \r\nSAVU voie B. Voie A HS\r\nDossier de concertation validé le 28 octobre 2021 \n ",47407]
["Infrabel","47408","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,14,15,"2024-04-05","2022-01-07T23:30:00","2024-04-08","2022-01-07T05:30:00","3d","Continuous",null,"T","","Aménagement gare de Floreffe\r\nWE 2/6\r\nDossier de concertation validé le 26 octobre 2021 \n ",47408]
["Infrabel","47411","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,15,16,"2024-04-12","2022-01-07T23:30:00","2024-04-15","2022-01-07T05:30:00","3d","Continuous",null,"T","","Aménagement gare de Floreffe\r\nWE 3/6\r\nDossier de concertation validé le 26 octobre 2021 \n ",47411]
["Infrabel","47438","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2024,2024,6,8,"2024-02-09",44568.96875,"2024-02-19",44568.229166666664,"10d","Continuous",null,"T","","Renouvellement Traverses et Ballast \r\nC75 + P93 entre 12.100 et 19.285 \n ",47438]
["Infrabel","47480","Erquelinnes - Montzen","< >","MARCHE-LES-DAMES-MARCHANDISES","BEEZ",2022,2022,40,41,"2022-09-30",44568.979166666664,"2022-10-03",44568.208333333336,"3d","Continuous",null,"T","","Marche-les-Dames Phase 5: Pose bordures de quai voie A\r\nVoir SIRU \n ",47480]
["Infrabel","47496","Athus - Meuse","< >","NAMUR","LUSTIN",2024,2024,19,20,"2024-05-09","2022-01-07T00:10:00","2024-05-12","2022-01-07T18:00:00","3d","Continuous",null,"T","","Suppression PN 99 et 101 Jambes : pose de deux couloir sous-voies + extension quais gare de Jambes\r\nRemise en état pistes PI BK 63.100 \n ",47496]
["Infrabel","47497","Athus - Meuse","< >","NAMUR","LUSTIN",2024,2024,21,22,"2024-05-25","2022-01-07T06:00:00","2024-05-26","2022-01-07T18:00:00","1d","Continuous",null,"T","","Suppression PN 99 et 101 Jambes : finitions aux deux couloir sous-voies + extension quais gare de Jambes\r\nRemise en état pistes PI BK 63.100 \n ",47497]
["Infrabel","47498","Athus - Meuse",">","DINANT","Y.NEFFE",2024,2024,3,11,"2024-01-15",44568.25,"2024-03-15",44568.916666666664,"60d","Continuous",null,"","ST","Suppression PN 115 bis et PN 116\r\nConstruction de deux couloirs sous-voies \n ",47498]
["Infrabel","47500","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2024,2024,13,27,"2024-03-25","2022-01-07T06:00:00","2024-07-05","2022-01-07T22:00:00","102d","Continuous",null,"","ST","Massification travaux\r\nRenouvellement tablier métallique PPI 13.808\r\nMise au gabarit pistes PI + sécurisation parois rocheuses + stabilisation talus \n ",47500]
["Infrabel","47501","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2024,2024,33,45,"2024-08-12","2022-01-07T06:00:00","2024-11-03","2022-01-07T22:00:00","83d","Continuous",null,"","ST","Massification travaux\r\nRenouvellement tablier métallique PI 13.808\r\nMise au gabarit pistes PI + sécurisation parois rocheuses + stabilisation talus \n ",47501]
["Infrabel","47504","Athus - Meuse","< >","ANSEREMME","HOUYET",2024,2024,15,16,"2024-04-13","2022-01-07T23:00:00","2024-04-14","2022-01-07T15:00:00","1d","Continuous",null,"T","","Massification travaux OA tronçons Anseremme - Gendron et Gendron - Houyet (entretien tunnels, parois,...) \n ",47504]
["Infrabel","47505","Athus - Meuse","< >","ANSEREMME","HOUYET",2024,2024,21,22,"2024-05-25","2022-01-07T23:00:00","2024-05-26","2022-01-07T15:00:00","1d","Continuous",null,"T","","Massification travaux OA tronçons Anseremme - Gendron et Gendron - Houyet (entretien tunnels, parois,...) \n ",47505]
["Infrabel","47506","Athus - Meuse","< >","ANSEREMME","HOUYET",2024,2024,34,35,"2024-08-24","2022-01-07T23:00:00","2024-08-25","2022-01-07T15:00:00","1d","Continuous",null,"T","","Massification travaux OA tronçons Anseremme - Gendron et Gendron - Houyet (entretien tunnels, parois,...) \n ",47506]
["Infrabel","47507","Athus - Meuse","< >","ANSEREMME","HOUYET",2024,2024,40,41,"2024-10-05","2022-01-07T23:00:00","2024-10-06","2022-01-07T15:00:00","1d","Continuous",null,"T","","Massification travaux OA tronçons Anseremme - Gendron et Gendron - Houyet (entretien tunnels, parois,...) \n ",47507]
["Infrabel","47567","Lille - Charleroi",">","MONS","JURBISE",2024,2024,6,16,"2024-02-05",44568.25,"2024-04-14",44568.958333333336,"69d","Continuous",null,"","ST","Réélectrification - Phases 1 et 2 - 2024 \nInséré dans le saisonnier",47567]
["Infrabel","47568","Lille - Charleroi","< >","MONS","JURBISE",2024,2024,16,18,"2024-04-15","2022-01-07T23:20:00","2024-05-03","2022-01-07T04:10:00","18d","Periodical",null,"T","","Réélectrification - Phase 3 - 2024\r\nDépose anciennes traverses \n",47568]
["Infrabel","47569","Lille - Charleroi",">","JURBISE","MONS",2024,2024,19,24,"2024-05-06","2022-01-07T22:50:00","2024-06-14","2022-01-07T05:10:00","39d","Periodical",null,"","ST","Réélectrification - Phase 4 - 2024\r\nDépose anciens poteaux \n",47569]
["Infrabel","47570","Lille - Charleroi",">","MONS","JURBISE",2024,2024,32,37,"2024-08-05","2022-01-07T22:50:00","2024-09-14","2022-01-07T05:10:00","40d","Periodical",null,"","ST","Réélectrification - Phase 5 - 2024\r\nDépose anciens poteaux \n",47570]
["Infrabel","47666","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,10,10,"2024-03-04","2022-01-07T23:10:00","2024-03-09","2022-01-07T04:00:00","5d","Periodical",null,"T","","Afwerkingsnachten na TLO-Weekend voor onderhouds werken\r\nminimum van 2 weekends per jaar, 1 weekend maart/april + 1 weekend oktober/november\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken mogelijk \n ",47666]
["Infrabel","47667","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,42,42,"2024-10-14","2022-01-07T23:10:00","2024-10-19","2022-01-07T04:00:00","5d","Periodical",null,"T","","Afwerkingsnachten na TLO-Weekend voor onderhouds werken\r\nminimum van 2 weekends per jaar, 1 weekend maart/april + 1 weekend oktober/november\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken mogelijk \n ",47667]
["Infrabel","47723","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2023,2023,17,17,"2023-04-24",44568.947916666664,"2023-04-29",44568.173611111109,"5d","Periodical",null,"T","","Renouvellement des AS Y. Froyennes\r\nUPM : 317287 \n ",47723]
["Infrabel","47740","Athus - Meuse","< >","BEAURAING","BERTRIX",2024,2024,25,26,"2024-06-21","2022-01-07T23:00:00","2024-06-24","2022-01-07T04:30:00","3d","Continuous",null,"T","","Renouvellement traverses (P93) \n ",47740]
["Infrabel","47743","Athus - Meuse","< >","BEAURAING","BERTRIX",2024,2024,34,35,"2024-08-23","2022-01-07T23:00:00","2024-08-26","2022-01-07T04:30:00","3d","Continuous",null,"T","","Renouvellement traverses(P93)\r\nRq 333 : conflit travaux Artère NE les we 25 – 26 – 27 - 33 et  34  - demande de déplacement de la part de la SNCF\r\n+ conflit L130A \n ",47743]
["Infrabel","47758","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,41,44,"2024-10-07","2022-01-07T07:30:00","2024-10-28","2022-01-07T06:00:00","21d","Continuous",null,"","ST","Renouvellement ballast par train C75 à Aix-sur-Cloie VB.\r\n+ ART 7' du 7/10 au 21/10/24 \nrestriction capacité importante -> Partie HKM dévies via ANE",47758]
["Infrabel","47761","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,44,47,"2024-10-28","2022-01-07T07:30:00","2024-11-18","2022-01-07T06:00:00","21d","Continuous",null,"","ST","Révision suite renouvellement ballast par train C75 à Aix-sur-Cloie VB. \nrestriction capacité importante -> Partie HKM dévies via ANE",47761]
["Infrabel","47763","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,47,48,"2024-11-18","2022-01-07T07:30:00","2024-11-29","2022-01-07T16:00:00","11d","Periodical",null,"","ST","Sécurisation des pistes suite renouvellement ballast par train C75 à Aix-sur-Cloie VB. \nrestriction capacité importante -> Partie HKM dévies via ANE",47763]
["Infrabel","47790","Athus - Meuse","< >","BEAURAING","BERTRIX",2024,2024,35,36,"2024-08-30","2022-01-07T23:00:00","2024-09-02","2022-01-07T04:30:00","3d","Continuous",null,"T","","Renouvellement traverses (P93)\r\nBourrage de révision \n ",47790]
["Infrabel","47812","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,45,47,"2024-11-08","2022-01-07T23:00:00","2024-11-18","2022-01-07T05:00:00","10d","Continuous",null,"","ST","Renouvellement ballast par train C75 (phase 1 : VB). \nrestriction capacité importante -> Partie HKM dévies via ANE",47812]
["Infrabel","47813","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,47,48,"2024-11-22","2022-01-07T23:00:00","2024-11-25","2022-01-07T05:00:00","3d","Continuous",null,"","ST","Renouvellement ballast par train C75 (phase 2 : VA). \nrestriction capacité importante -> Partie HKM dévies via ANE",47813]
["Infrabel","47814","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,48,49,"2024-11-29","2022-01-07T23:00:00","2024-12-02","2022-01-07T05:00:00","3d","Continuous",null,"","ST","Renouvellement ballast par train C75 (phase 3 : révision VB). \nrestriction capacité importante -> Partie HKM dévies via ANE",47814]
["Infrabel","47815","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,49,50,"2024-12-06","2022-01-07T23:00:00","2024-12-09","2022-01-07T05:00:00","3d","Continuous",null,"","ST","Renouvellement ballast par train C75 (phase 4 : révision VA). \nrestriction capacité importante -> Partie HKM dévies via ANE",47815]
["Infrabel","47850","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2023,2023,26,26,"2023-06-26",44568.25,"2023-06-30",44568.916666666664,"4d","Continuous",null,"T","","Renouvellement traverses St-Vincent : P93 W-E n°3.\r\nART \n ",47850]
["Infrabel","47865","Erquelinnes - Montzen",">","HERMALLE-SOUS-HUY","FLEMALLE-HAUTE",2023,2023,20,20,"2023-05-14",44568.708333333336,"2023-05-15",44568.222222222219,"1d","Continuous",null,"","ST","Renouvellement des appareils de voies d'Engis\r\nWE 1/3 - Renouvellement AS 05AT / 05BT(+  plateforme) \n ",47865]
["Infrabel","47866","Erquelinnes - Montzen",">","HERMALLE-SOUS-HUY","FLEMALLE-HAUTE",2023,2023,21,21,"2023-05-21",44568.708333333336,"2023-05-22",44568.222222222219,"1d","Continuous",null,"","ST","Renouvellement des appareils de voies d'Engis\r\nPhase 2 - WE 2/3 - AW 02AT / 02BT / 03BT (+  assainissement)\r\n+ Renouvellement des traverses entre AS 02AT et 05BT\r\n+ Raccordement sur les nouveaux AS 05AT/05BT\r\n+ Renouvellement AS 14AS à Hermalle sous-Huy \n ",47866]
["Infrabel","47867","Erquelinnes - Montzen",">","HERMALLE-SOUS-HUY","FLEMALLE-HAUTE",2023,2023,22,22,"2023-05-28",44568.708333333336,"2023-05-29",44568.222222222219,"1d","Continuous",null,"","ST","Renouvellement des appareils de voies d'Engis\r\nPhase 2 - WE 3/3 - AW 02AT / 02BT / 03BT (+  assainissement)\r\n+ Renouvellement des traverses entre AS 02AT et 05BT\r\n+ Raccordement sur les nouveaux AS 05AT/05BT\r\n+ Renouvellement AS 14AS à Hermalle sous-Huy \n ",47867]
["Infrabel","48023","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,19,19,"2022-05-02",44568.9375,"2022-05-07",44568.215277777781,"5d","Periodical",null,"T","","Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nDémontage Signalisation suite au passage en PLP\r\nTravaux de préparation pour la construction de passerelles au droit du PI 61.597\r\nUPM 291698 \nHKM à adapter\r\nVia 117 - 124 - 130A - 90 - 94 - 96",48023]
["Infrabel","48024","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,20,20,"2022-05-09",44568.9375,"2022-05-14",44568.215277777781,"5d","Periodical",null,"T","","Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nDémontage Signalisation suite au passage en PLP\r\nTravaux de préparation pour la construction de passerelles au droit du PI 61.597\r\nUPM 291702 \nHKM à adapter\r\nVia 117 - 124 - 130A - 90 - 94 - 96",48024]
["Infrabel","48025","Lille - Charleroi","< >","Y.LENS","ATH",2022,2022,21,21,"2022-05-16",44568.9375,"2022-05-21",44568.215277777781,"5d","Periodical",null,"T","","Renouvellement des AS 31AF/31BF + 32AF/32BF\r\nDémontage Signalisation suite au passage en PLP\r\nTravaux de préparation pour la construction de passerelles au droit du PI 61.597\r\nUPM 291739 \nHKM à adapter\r\nVia 117 - 124 - 130A - 90 - 94 - 96",48025]
["Infrabel","48112","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2023,2023,43,44,"2023-10-28",44568.041666666664,"2023-10-30",44568.1875,"2d","Continuous",null,"T","","Oude Landen \n ",48112]
["Infrabel","48113","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2023,2023,45,46,"2023-11-11",44568.041666666664,"2023-11-13",44568.1875,"2d","Continuous",null,"T","","Oude Landen \n ",48113]
["Infrabel","48145","Erquelinnes - Montzen","< >","STATTE","NAMUR",2023,2023,37,38,"2023-09-16",44568.006944444445,"2023-09-18",44568.166666666664,"2d","Continuous",null,"T","","Massification travaux :\r\n- 2 liaisons de Andenne\r\n- Poste de sectionnement Andenne + adaptation CAT\r\n- Passage supérieur Andenne\r\n- Quais de Sclaigneaux\r\n- Couloir sous-voies en vue de la suppression des PN 75-76-77-78 \n ",48145]
["Infrabel","48146","Erquelinnes - Montzen","< >","STATTE","NAMUR",2023,2023,38,39,"2023-09-23",44568.006944444445,"2023-09-25",44568.166666666664,"2d","Continuous",null,"T","","Massification travaux :\r\n- 2 liaisons de Andenne\r\n- Poste de sectionnement Andenne + adaptation CAT\r\n- Passage supérieur Andenne\r\n- Quais de Sclaigneaux\r\n- Couloir sous-voies en vue de la suppression des PN 75-76-77-78 \n ",48146]
["Infrabel","48147","Erquelinnes - Montzen","< >","STATTE","NAMUR",2023,2023,39,40,"2023-09-30",44568.006944444445,"2023-10-02",44568.166666666664,"2d","Continuous",null,"T","","Massification travaux :\r\n- 2 liaisons de Andenne\r\n- Poste de sectionnement Andenne + adaptation CAT\r\n- Passage supérieur Andenne\r\n- Quais de Sclaigneaux\r\n- Couloir sous-voies en vue de la suppression des PN 75-76-77-78 \n ",48147]
["Infrabel","48148","Erquelinnes - Montzen","< >","STATTE","NAMUR",2023,2023,40,41,"2023-10-07",44568.006944444445,"2023-10-09",44568.166666666664,"2d","Continuous",null,"T","","Massification travaux :\r\n- 2 liaisons de Andenne\r\n- Poste de sectionnement Andenne + adaptation CAT\r\n- Passage supérieur Andenne\r\n- Quais de Sclaigneaux\r\n- Couloir sous-voies en vue de la suppression des PN 75-76-77-78 \n ",48148]
["Infrabel","48201","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,16,17,"2024-04-19","2022-01-07T23:30:00","2024-04-22","2022-01-07T05:30:00","3d","Continuous",null,"T","","Aménagement gare de Floreffe\r\nWE 4/6\r\nDossier de concertation validé le 26 octobre 2021 \n ",48201]
["Infrabel","48235","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,32,35,"2024-08-09","2022-01-07T23:00:00","2024-08-26","2022-01-07T04:10:00","17d","Continuous",null,"T","","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nCTL 17 jours continu \nA déterminer",48235]
["Infrabel","48241","Erquelinnes - Montzen","< >","CHARLEROI-SUD","ERQUELINNES-FRONTIERE",2024,2024,35,36,"2024-08-30","2022-01-07T23:00:00","2024-09-02","2022-01-07T04:10:00","3d","Continuous",null,"T","","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+132 Finitions\r\n+ Renouvellement des as Y La Sambre \r\nDossier de concertation validé le 28 octobre 2021 \nHKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",48241]
["Infrabel","48242","Erquelinnes - Montzen","< >","CHARLEROI-SUD","ERQUELINNES-FRONTIERE",2024,2024,36,37,"2024-09-06","2022-01-07T23:00:00","2024-09-09","2022-01-07T04:10:00","3d","Continuous",null,"T","","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+132  Finitions\r\n+ Renouvellement des as Y La Sambre \r\nDossier de concertation validé le 28 octobre 2021 \nHKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",48242]
["Infrabel","48243","Erquelinnes - Montzen","< >","CHARLEROI-SUD","LA SAMBRE",2024,2024,34,35,"2024-08-23","2022-01-07T23:00:00","2024-08-26","2022-01-07T04:10:00","3d","Continuous",null,"T","","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+L132\r\n+ Renouvellement des as Y La Sambre \r\nDossier de concertation validé le 28 octobre 2021 \nHKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",48243]
["Infrabel","48244","Erquelinnes - Montzen","< >","CHARLEROI-SUD","LA SAMBRE",2024,2024,33,34,"2024-08-16","2022-01-07T23:00:00","2024-08-19","2022-01-07T04:10:00","3d","Continuous",null,"T","","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+L132 \nHKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",48244]
["Infrabel","48245","Erquelinnes - Montzen","< >","CHARLEROI-SUD","LA SAMBRE",2024,2024,32,33,"2024-08-09","2022-01-07T23:00:00","2024-08-12","2022-01-07T04:10:00","3d","Continuous",null,"T","","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+L132 \nA déterminer",48245]
["Infrabel","48246","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,5,6,"2024-02-03",44568.291666666664,"2024-02-04",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z2. 51  P4+ \n ",48246]
["Infrabel","48247","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,19,20,"2024-05-11","2022-01-07T07:00:00","2024-05-12","2022-01-07T17:00:00","1d","Continuous",null,"T","","Maintenance Z2. 51  P4+ \n ",48247]
["Infrabel","48249","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,47,48,"2024-11-23","2022-01-07T07:00:00","2024-11-24","2022-01-07T17:00:00","1d","Continuous",null,"T","","Maintenance Z2. 51  P4+ \n ",48249]
["Infrabel","48250","Lille - Charleroi","< >","Y.LENS","ATH",2024,2024,12,13,"2024-03-22","2022-01-07T22:10:00","2024-03-25","2022-01-07T05:10:00","3d","Continuous",null,"T","","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette \n ",48250]
["Infrabel","48251","Lille - Charleroi","< >","Y.LENS","ATH",2024,2024,11,12,"2024-03-15","2022-01-07T22:10:00","2024-03-18","2022-01-07T05:10:00","3d","Continuous",null,"T","","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette \n ",48251]
["Infrabel","48252","Lille - Charleroi","< >","ATH","Y.LENS",2024,2024,10,11,"2024-03-08","2022-01-07T22:10:00","2024-03-11","2022-01-07T05:10:00","3d","Continuous",null,"T","","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette \n ",48252]
["Infrabel","48253","Lille - Charleroi","< >","Y.LENS","ATH",2024,2024,9,10,"2024-03-01","2022-01-07T22:10:00","2024-03-04","2022-01-07T05:10:00","3d","Continuous",null,"T","","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette \n ",48253]
["Infrabel","48254","Lille - Charleroi","< >","BRUGELETTE","ATH",2024,2024,10,12,"2024-03-04","2022-01-07T22:10:00","2024-03-22","2022-01-07T05:10:00","18d","Periodical",null,"T","","Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette \n ",48254]
["Infrabel","48255","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,14,16,"2024-04-05","2022-01-07T23:00:00","2024-04-15","2022-01-07T05:00:00","10d","Continuous",null,"T","","Renouvellement des Tabliers métalliques  + 5chapes \r\nTravaux RER Ottignies (CSV)\r\nCTL 9 jours continu \n ",48255]
["Infrabel","48256","Namur - Antwerpen",">","LA ROCHE(BRABANT)","TILLY",2024,2024,14,24,"2024-04-01","2022-01-07T06:00:00","2024-06-09","2022-01-07T17:00:00","69d","Continuous",null,"","ST","Sécurisation paroi rocheuse (400m) \n ",48256]
["Infrabel","48257","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,16,17,"2024-04-19","2022-01-07T23:00:00","2024-04-22","2022-01-07T05:00:00","3d","Continuous",null,"T","","Renouvellement des Tabliers métalliques  + 5chapes \r\nWE Finitions \n ",48257]
["Infrabel","48258","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,17,18,"2024-04-26","2022-01-07T23:00:00","2024-04-29","2022-01-07T05:00:00","3d","Continuous",null,"T","","Renouvellement des Tabliers métalliques  + 5chapes \r\nWE Finitions \n ",48258]
["Infrabel","48507","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2023,2023,6,7,"2023-02-11",44568.25,"2023-02-12",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z15. 51\r\nP4+ \n ",48507]
["Infrabel","48508","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2024,2024,3,4,"2024-01-20",44568.25,"2024-01-21",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z15. 51\r\nP4+\r\nReport 2023 \n ",48508]
["Infrabel","48509","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2023,2023,32,33,"2023-08-12",44568.25,"2023-08-13",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z15. 51\r\nP4+ \n ",48509]
["Infrabel","48510","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2023,2023,29,30,"2023-07-20",44568.972222222219,"2023-07-24",44568.166666666664,"4d","Continuous",null,"T","","Renouvellement PS 85.708\r\n+ Maintenance Z15. 51\r\nP4+ \n ",48510]
["Infrabel","48545","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2023,2023,25,25,"2023-06-19",44568.923611111109,"2023-06-24",44568.173611111109,"5d","Periodical",null,"T","","CTL toutes les nuits de semaine pour travaux préparatoires - Pose 2nd tablier des ponts 7&8 \n ",48545]
["Infrabel","48547","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2023,2023,20,20,"2023-05-15",44568.923611111109,"2023-05-18",44568.173611111109,"3d","Periodical",null,"T","","CTL toutes les nuits de semaine pour travaux préparatoires - Pose 2nd tablier des ponts 7&8 \n ",48547]
["Infrabel","48549","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2023,2023,40,40,"2023-10-02",44568.923611111109,"2023-10-06",44568.173611111109,"4d","Periodical",null,"T","","CTL toutes les nuits de semaine pour travaux de finition - Pose 2nd tablier des ponts 7&8\r\n+ Maintenance P3 Z2.51 \n ",48549]
["Infrabel","48553","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2023,2023,38,39,"2023-09-23",44568.291666666664,"2023-09-24",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z2. 51  P4+ \n ",48553]
["Infrabel","48555","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2023,2023,14,15,"2023-04-07",44568.958333333336,"2023-04-11",44568.208333333336,"4d","Continuous",null,"T","","CTL pour la démolition des PS km 104.903 et 118.788\r\n+ Maintenance Z2. 51  P4+ \n ",48555]
["Infrabel","48556","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2023,2023,39,39,"2023-09-25",44568.881944444445,"2023-09-29",44568.173611111109,"4d","Periodical",null,"T","","Maintenance Z2. 51  P3HKV \n ",48556]
["Infrabel","48595","Lille - Charleroi","< >","BRUXELLES-MIDI","HALLE",2023,2023,23,23,"2023-06-04",44568.000694444447,"2023-06-04",44568.5,"0d","Continuous",null,"T","","MES ETCS \nInfo Racc.",48595]
["Infrabel","48645","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2023,2023,4,4,"2023-01-24",44568.027777777781,"2023-01-28",44568.180555555555,"4d","Periodical",null,"T","","Maintenance Z4.53 en P3 HKM \n ",48645]
["Infrabel","48652","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,14,14,"2024-04-01","2022-01-07T23:00:00","2024-04-05","2022-01-07T05:00:00","4d","Periodical",null,"T","","Renouvellement des Tabliers métalliques  + 5chapes \r\nNuits préparation \n ",48652]
["Infrabel","48653","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,13,13,"2024-03-25","2022-01-07T23:00:00","2024-03-30","2022-01-07T05:00:00","5d","Periodical",null,"T","","Renouvellement des Tabliers métalliques  + 5chapes \r\nNuits préparation \n ",48653]
["Infrabel","48654","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,16,16,"2024-04-15","2022-01-07T23:00:00","2024-04-19","2022-01-07T05:00:00","4d","Periodical",null,"T","","Renouvellement des Tabliers métalliques  + 5chapes \r\nNuits préparation \n ",48654]
["Infrabel","48655","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,17,17,"2024-04-22","2022-01-07T23:00:00","2024-04-26","2022-01-07T05:00:00","4d","Periodical",null,"T","","Renouvellement des Tabliers métalliques  + 5chapes \r\nNuits préparation \n ",48655]
["Infrabel","48656","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,18,18,"2024-04-29","2022-01-07T23:00:00","2024-05-04","2022-01-07T05:00:00","5d","Periodical",null,"T","","Renouvellement des Tabliers métalliques  + 5chapes \r\nNuits préparation \n ",48656]
["Infrabel","48657","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,19,19,"2024-05-06","2022-01-07T23:00:00","2024-05-11","2022-01-07T05:00:00","5d","Periodical",null,"T","","Renouvellement des Tabliers métalliques  + 5chapes \r\nNuits préparation \n ",48657]
["Infrabel","48658","Lille - Charleroi","< >","JURBISE","MONS",2023,2023,7,8,"2023-02-18",44568.25,"2023-02-19",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z.5.53\r\nP4 \n ",48658]
["Infrabel","48772","Lille - Charleroi","< >","LEUZE","TOURNAI",2024,2024,36,36,"2024-09-02","2022-01-07T23:20:00","2024-09-06","2022-01-07T04:40:00","4d","Periodical",null,"T","","Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH\r\nTravaux de préparation \nInfo Racc : désertes Havinnes impossible",48772]
["Infrabel","48773","Lille - Charleroi","< >","LEUZE","TOURNAI",2024,2024,36,37,"2024-09-06","2022-01-07T23:20:00","2024-09-09","2022-01-07T04:40:00","3d","Continuous",null,"T","","Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH \nInfo Racc : Havinnes inaccessible",48773]
["Infrabel","48783","Namur - Antwerpen",">","LA ROCHE(BRABANT)","TILLY",2023,2023,38,39,"2023-09-18",44568.25,"2023-09-30",44568.708333333336,"12d","Continuous",null,"","ST","Sécurisation paroi rocheuse bk 38.690 (220m) \n ",48783]
["Infrabel","48786","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2023,2023,19,20,"2023-05-13",44568.25,"2023-05-14",44568.666666666664,"1d","Continuous",null,"T","","Maintenance Z4.53 en P4 \n ",48786]
["Infrabel","48802","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2023,2023,44,45,"2023-11-04",44568.25,"2023-11-05",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z3. 51  P4+ \n ",48802]
["Infrabel","48803","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2023,2023,4,5,"2023-01-28",44568.25,"2023-01-29",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z3. 51  P4+ \n ",48803]
["Infrabel","48804","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2023,2023,40,41,"2023-10-07",44568.25,"2023-10-08",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z4. 51  P4+ \n ",48804]
["Infrabel","48805","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2023,2023,45,46,"2023-11-11",44568.25,"2023-11-12",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z4. 51  P4+ \n ",48805]
["Infrabel","48806","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2023,2023,9,10,"2023-03-04",44568.25,"2023-03-05",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z4. 51  P4+ \n ",48806]
["Infrabel","48824","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2023,2023,36,37,"2023-09-09",44568.25,"2023-09-10",44568.666666666664,"1d","Continuous",null,"T","","Maintenance Z4.53 en P4 \n ",48824]
["Infrabel","48828","Namur - Antwerpen","< >","TAMINES","LE CAMPINAIRE",2024,2024,38,39,"2024-09-20","2022-01-07T23:40:00","2024-09-23","2022-01-07T05:00:00","3d","Continuous",null,"T","","PS 87,100 - travaux en-dessous du tablier \n ",48828]
["Infrabel","48845","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2023,2023,30,31,"2023-07-29",44568.25,"2023-07-30",44568.666666666664,"1d","Continuous",null,"T","","Maintenance Z4.53 en P4\r\n+ révisions ES \n ",48845]
["Infrabel","48846","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2023,2023,1,2,"2023-01-07",44568.25,"2023-01-08",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z.3.53 +  Z9.52 en P4 \n ",48846]
["Infrabel","48847","Athus - Meuse",">","Y.NEFFE","GENDRON-CELLES",2022,2022,9,16,"2022-02-21",44568.333333333336,"2022-04-15",44568.708333333336,"53d","Continuous",null,"","ST","Réalisation d'une dalle en béton armé pour l'étanchéité de la culée-voûte à la bk 8,509 - côté voie B\r\nSécurisation parois rocheuses du 10.01 8:00 au 1.04 18:00 (Javaux)\r\nUPM: 308199 \nPas de croisements prévus au saisonnier pour la période Pert de février\r\nHKM à adapter du 04 au 15/04",48847]
["Infrabel","48931","Lille - Charleroi","< >","JURBISE","ATH",2023,2023,45,46,"2023-11-11",44568.25,"2023-11-12",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z7.53 +  Z13.54 en P4 \n ",48931]
["Infrabel","49033","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2023,2023,24,25,"2023-06-17",44568.25,"2023-06-18",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z10. 51   P4+ \n ",49033]
["Infrabel","49034","Namur - Antwerpen","< >","CHARLEROI-SUD","COUILLET",2023,2023,39,40,"2023-09-30",44568.25,"2023-10-01",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z10. 51   P4+ \n ",49034]
["Infrabel","49071","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2023,2023,2,3,"2023-01-14",44568.986111111109,"2023-01-15",44568.618055555555,"1d","Continuous",null,"T","","Maintenance Z19. 51\r\nMini CTL\r\n+  Travaux OA - Chape 78.887\r\nUPM : 335295 \nINFO RACC",49071]
["Infrabel","49072","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2023,2023,16,17,"2023-04-22",44568.986111111109,"2023-04-23",44568.618055555555,"1d","Continuous",null,"T","","Maintenance Z19. 51\r\nMini CTL \n ",49072]
["Infrabel","49073","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2023,2023,31,32,"2023-08-05",44568.986111111109,"2023-08-06",44568.618055555555,"1d","Continuous",null,"T","","Maintenance Z19. 51\r\nMini CTL \n ",49073]
["Infrabel","49075","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2023,2023,46,47,"2023-11-18",44568.986111111109,"2023-11-19",44568.618055555555,"1d","Continuous",null,"T","","Maintenance Z19. 51\r\nMini CTL \n ",49075]
["Infrabel","49110","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET",2024,2024,36,39,"2024-09-02","2022-01-07T23:00:00","2024-09-28","2022-01-07T05:00:00","26d","Periodical",null,"","ST","Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.a\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 octobre 2021 \n ",49110]
["Infrabel","49111","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET",2024,2024,39,43,"2024-09-28","2022-01-07T05:00:00","2024-10-20","2022-01-07T05:00:00","22d","Continuous",null,"","ST","Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.b\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 octobre 2021 \n ",49111]
["Infrabel","49120","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,19,20,"2024-05-10","2022-01-07T23:00:00","2024-05-12","2022-01-07T17:00:00","2d","Continuous",null,"T","","Travaux de remise en état du PS km 104,903 \n ",49120]
["Infrabel","49121","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,18,19,"2024-05-03","2022-01-07T23:00:00","2024-05-06","2022-01-07T05:00:00","3d","Continuous",null,"T","","Renouvellement des 5chapes +P93\r\nWE Finitions \n ",49121]
["Infrabel","49122","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,19,20,"2024-05-10","2022-01-07T23:00:00","2024-05-13","2022-01-07T05:00:00","3d","Continuous",null,"T","","Renouvellement des 5chapes +P93\r\nWE Finitions \n ",49122]
["Infrabel","49150","Lille - Charleroi","< >","LEUZE","TOURNAI",2024,2024,19,19,"2024-05-06","2022-01-07T23:20:00","2024-05-10","2022-01-07T04:40:00","4d","Periodical",null,"T","","Renouvellement PN 70 et 80 \nInfo Racc : desserte d'Havinnes impossible",49150]
["Infrabel","49237","Erquelinnes - Montzen","< >","CHARLEROI-SUD","ERQUELINNES-FRONTIERE",2024,2024,35,36,"2024-08-26","2022-01-07T23:00:00","2024-09-07","2022-01-07T04:10:00","12d","Periodical",null,"T","","Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nRenouvellement des AS de Y.La Sambre\r\n2 x Sem. nuits CTL L130A+132  Finitions \nHKM à adapter\r\nInfo racc - CARRIERES LES PETONS (SOLVAY) inacessible",49237]
["Infrabel","49238","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,20,21,"2024-05-13","2022-01-07T22:30:00","2024-05-25","2022-01-07T04:10:00","12d","Periodical",null,"T","","Renouvellement AS Y. La Sambre\r\nTravaux préparatoires caténaire \n ",49238]
["Infrabel","49243","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2023,2023,46,47,"2023-11-18",44568.25,"2023-11-19",44568.666666666664,"1d","Continuous",null,"T","","Maintenance Z4.53 en P4 \n ",49243]
["Infrabel","49265","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2024,2024,15,16,"2024-04-12","2022-01-07T23:30:00","2024-04-15","2022-01-07T04:50:00","3d","Continuous",null,"T","","RER Watermael - Ottignies\r\nFinitions après semaine CTL de Pâques \n ",49265]
["Infrabel","49289","Lille - Charleroi","< >","ATH","LEUZE",2023,2023,41,41,"2023-10-09",44568.961805555555,"2023-10-14",44568.1875,"5d","Periodical",null,"T","","Criblage de ballast - C75 nuits finitions \n ",49289]
["Infrabel","49290","Lille - Charleroi","< >","ATH","LEUZE",2023,2023,42,42,"2023-10-16",44568.961805555555,"2023-10-21",44568.1875,"5d","Periodical",null,"T","","Criblage de ballast - C75 nuits finitions \n ",49290]
["Infrabel","49295","Lille - Charleroi","< >","Y.LENS","ATH",2023,2023,15,15,"2023-04-11",44568.958333333336,"2023-04-14",44568.208333333336,"3d","Periodical",null,"T","","Construction d'un pont-cadre en vue de la suppression du PN5(km 51.775)\r\nRenouvellement de la chape d'étanchéité du PI L90C (km 61.597)\r\nPréparations \n ",49295]
["Infrabel","49298","Lille - Charleroi","< >","JURBISE","ATH",2023,2023,15,16,"2023-04-14",44568.958333333336,"2023-04-17",44568.208333333336,"3d","Continuous",null,"T","","Construction d'un pont-cadre en vue de la suppression du PN5(km 51.775)\r\nRenouvellement de la chape d'étanchéité du PI L90C (km 61.597)\r\n+ Maintenance AI53 \n ",49298]
["Infrabel","49319","Lille - Charleroi","< >","PONT-A-CELLES","LUTTRE",2022,2022,45,46,"2022-11-05",44568.013888888891,"2022-11-07",44568.1875,"2d","Periodical",null,"T","","Transfert caténaire transversale nord de Luttre \n ",49319]
["Infrabel","49320","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET",2024,2024,44,45,"2024-11-02","2022-01-07T22:00:00","2024-11-03","2022-01-07T22:00:00","1d","Continuous",null,"","ST","Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.c\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 octobre 2021 \n ",49320]
["Infrabel","49321","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET",2024,2024,45,46,"2024-11-09","2022-01-07T22:00:00","2024-11-10","2022-01-07T22:00:00","1d","Continuous",null,"","ST","Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.c\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 octobre 2021 \n ",49321]
["Infrabel","49341","Lille - Charleroi","< >","ATH","TOURNAI",2023,2023,16,17,"2023-04-22",44568.25,"2023-04-23",44568.708333333336,"1d","Continuous",null,"T","","Maintenance Z5.54 \n ",49341]
["Infrabel","49378","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2023,2023,38,39,"2023-09-22",44568.958333333336,"2023-09-25",44568.208333333336,"3d","Continuous",null,"T","","WE CTL - Chape OA 32.898\r\n+ Massification des travaux de maintenance AI 44 \n ",49378]
["Infrabel","49379","Namur - Antwerpen","< >","TAMINES","LE CAMPINAIRE",2023,2023,41,41,"2023-10-09",44568.972222222219,"2023-10-14",44568.208333333336,"5d","Periodical",null,"T","","Renouvellement PS 85.708\r\nNuits de préparation \n ",49379]
["Infrabel","49387","Namur - Antwerpen","< >","LE CAMPINAIRE","TAMINES",2023,2023,42,43,"2023-10-21",44568.965277777781,"2023-10-22",44568.638888888891,"1d","Continuous",null,"T","","Renouvellement PS 85.708\r\nMini CTL R6 23h10 - R7 15h20 \n ",49387]
["Infrabel","49394","Lille - Charleroi","< >","LEUZE","HAVINNES",2023,2023,32,33,"2023-08-11",44568.972222222219,"2023-08-14",44568.194444444445,"3d","Continuous",null,"T","","Renouvellement du PS L94 (BK 67.995)\r\nConstruction du PS - pose du tablier \n ",49394]
["Infrabel","49412","Lille - Charleroi","< >","LEUZE","TOURNAI",2024,2024,37,37,"2024-09-09","2022-01-07T23:20:00","2024-09-14","2022-01-07T04:40:00","5d","Periodical",null,"T","","Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH\r\nTravaux de finition \nInfo Racc : désertes Havinnes impossible",49412]
["Infrabel","49413","Lille - Charleroi","< >","LEUZE","TOURNAI",2024,2024,21,21,"2024-05-20","2022-01-07T23:20:00","2024-05-25","2022-01-07T04:40:00","5d","Periodical",null,"T","","Renouvellement PN 70 et 80 \nInfo Racc : desserte d'Havinnes impossible",49413]
["Infrabel","49462","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,6,7,"2024-02-09",44568.75,"2024-02-12",44568.194444444445,"3d","Continuous",null,"T","","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 2/6\r\nDossier de concertation validé le 28 octobre 2021\r\nRq 333 : demande EF's de déplacer au WE du 27/01 \n ",49462]
["Infrabel","49479","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,17,18,"2022-04-23",44568,"2022-04-25",44568.166666666664,"2d","Continuous",null,"T","","Werken wissels Y Antwerpen Schijnpoort\r\nCR 187\r\nTer vervanging van uitgestelde aanvragen 38790 + 34344\r\n3 aaneensluitende weekends: verplaatsbaar in de tijd, niet in vakantieperiode, na levering wissels in februari 2022.\r\nOPGEPAST: ook L27A  op zondag ( \nHKM om te leiden",49479]
["Infrabel","49480","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,18,19,"2022-04-30",44568,"2022-05-02",44568.166666666664,"2d","Continuous",null,"T","","Werken wissels Y Antwerpen Schijnpoort\r\nCR 189\r\nTer vervanging van uitgestelde aanvragen 38790 + 34344\r\n3 aaneensluitende weekends: verplaatsbaar in de tijd, niet in vakantieperiode, na levering wissels in februari 2022.\r\nOPGEPAST: ook L27A  op zondag ( \nHKM om te leiden",49480]
["Infrabel","49481","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2022,2022,19,20,"2022-05-07",44568,"2022-05-09",44568.166666666664,"2d","Continuous",null,"T","","Werken wissels Y Antwerpen Schijnpoort\r\nCR 191\r\nTer vervanging van uitgestelde aanvragen 38790 + 34344\r\n3 aaneensluitende weekends: verplaatsbaar in de tijd, niet in vakantieperiode, na levering wissels in februari 2022.\r\nOPGEPAST: ook L27A  op zondag ( \nHKM om te leiden",49481]
["Infrabel","49495","Erquelinnes - Montzen","< >","CHARLEROI-SUD","MARCHIENNE-ZONE",2024,2024,25,25,"2024-06-17","2022-01-07T22:30:00","2024-06-21","2022-01-07T04:00:00","4d","Periodical",null,"T","","Livraison des AS Y LLS, à l'aide du train Kirow \n ",49495]
["Infrabel","49498","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2023,2023,24,24,"2023-06-12",44568.958333333336,"2023-06-16",44568.208333333336,"4d","Periodical",null,"T","","Renouvellement des Tabliers métalliques situés Bk 43.660 et Bk 48.720\r\nPréparations\r\n+ Maintenance Z3. 51  P3 HKM \n ",49498]
["Infrabel","49544","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,41,42,"2024-10-11","2022-01-07T23:00:00","2024-10-14","2022-01-07T05:00:00","3d","Continuous",null,"T","","Renouvellement des traverses P93\r\nPhase 2 - WE 1/2\r\nDossier de concertation validé le 28 octobre 2021 \n ",49544]
["Infrabel","49545","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,38,39,"2024-09-20","2022-01-07T23:00:00","2024-09-23","2022-01-07T05:00:00","3d","Continuous",null,"T","","Renouvellement des traverses P93\r\nPhase 1 WE 1/3\r\nDossier de concertation validé le 28 octobre 2021 \n ",49545]
["Infrabel","49546","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,39,40,"2024-09-27","2022-01-07T23:00:00","2024-09-30","2022-01-07T05:00:00","3d","Continuous",null,"T","","Renouvellement des traverses P93\r\nPhase 1 WE 2/3\r\nDossier de concertation validé le 28 octobre 2021 \n ",49546]
["Infrabel","49547","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,40,41,"2024-10-04","2022-01-07T23:00:00","2024-10-07","2022-01-07T05:00:00","3d","Continuous",null,"T","","Renouvellement des traverses P93\r\nPhase 1 WE 1/3\r\nDossier de concertation validé le 28 octobre 2021 \n ",49547]
["Infrabel","49548","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,42,43,"2024-10-18","2022-01-07T23:00:00","2024-10-21","2022-01-07T05:00:00","3d","Continuous",null,"T","","Renouvellement des traverses P93\r\nPhase 2 - WE 2/2\r\nDossier de concertation validé le 28 octobre 2021 \n ",49548]
["Infrabel","49550","Lille - Charleroi","< >","Y.LENS","ATH",2023,2023,4,4,"2023-01-23",44568.958333333336,"2023-01-28",44568.208333333336,"5d","Periodical",null,"T","","Construction d'un pont-cadre en vue de la suppression du PN5(km 51.775)\r\nRenouvellement de la chape d'étanchéité du PI L90C (km 61.597)\r\nPréparations \n ",49550]
["Infrabel","49551","Lille - Charleroi","< >","JURBISE","ATH",2023,2023,16,18,"2023-04-17",44568.965277777781,"2023-05-01",44568.208333333336,"14d","Periodical",null,"T","","Construction d'un pont-cadre en vue de la suppression du PN5(km 51.775)\r\nRenouvellement de la chape d'étanchéité du PI L90C (km 61.597)\r\nFinitions\r\n+ Maintenance Z13.54/Z7.53 \n ",49551]
["Infrabel","49552","Lille - Charleroi","< >","LEUZE","HAVINNES",2023,2023,41,42,"2023-10-13",44568.972222222219,"2023-10-16",44568.1875,"3d","Continuous",null,"T","","Renouvellement du PS L94 (BK 67.995)\r\nDémolition du PS \n ",49552]
["Infrabel","49553","Lille - Charleroi","< >","LEUZE","HAVINNES",2023,2023,8,8,"2023-02-20",44568.993055555555,"2023-02-25",44568.194444444445,"5d","Periodical",null,"T","","Renouvellement du PS L94 (BK 67.995)\r\nConstruction du PS - Terrassements \n ",49553]
["Infrabel","49554","Lille - Charleroi","< >","ATH","TOURNAI",2023,2023,9,9,"2023-02-27",44568.993055555555,"2023-03-04",44568.194444444445,"5d","Periodical",null,"T","","Renouvellement du PS L94 (BK 67.995)\r\nConstruction du PS - Fondations\r\n+ Maintenance Z5.54 \nInfoRacc",49554]
["Infrabel","49555","Lille - Charleroi","< >","ATH","TOURNAI",2023,2023,23,23,"2023-06-05",44568.972222222219,"2023-06-10",44568.1875,"5d","Periodical",null,"T","","Renouvellement du PS L94 (BK 67.995)\r\nConstruction du PS - Fondations\r\n+ Maintenance Z5.54 \nInfoRacc",49555]
["Infrabel","49556","Lille - Charleroi","< >","ATH","TOURNAI",2023,2023,32,32,"2023-08-07",44568.972222222219,"2023-08-11",44568.1875,"4d","Periodical",null,"T","","Renouvellement du PS L94 (BK 67.995)\r\nConstruction du PS - Préparations\r\n+ Maintenance Z5.54 \n ",49556]
["Infrabel","49557","Lille - Charleroi","< >","LEUZE","HAVINNES",2023,2023,34,34,"2023-08-21",44568.972222222219,"2023-08-26",44568.1875,"5d","Periodical",null,"T","","Renouvellement du PS L94 (BK 67.995)\r\nDémolition du PS - préparation \n ",49557]
["Infrabel","49558","Lille - Charleroi","< >","LEUZE","HAVINNES",2023,2023,41,41,"2023-10-09",44568.972222222219,"2023-10-13",44568.1875,"4d","Periodical",null,"T","","Renouvellement du PS L94 (BK 67.995)\r\nDémolition du PS - Finitions \n ",49558]
["Infrabel","49559","Lille - Charleroi","< >","LEUZE","HAVINNES",2023,2023,42,42,"2023-10-16",44568.972222222219,"2023-10-21",44568.1875,"5d","Periodical",null,"T","","Renouvellement du PS L94 (BK 67.995)\r\nDémolition du PS - Finitions \n ",49559]
["Infrabel","49565","Athus - Meuse","< >","DINANT","Y.NEFFE",2023,2023,39,40,"2023-09-29",44568.000694444447,"2023-10-02",44568.166666666664,"3d","Continuous",null,"T","","Suppression PN 115 bis et PN 116 par la construction de deux couloirs sous-voies\r\nPose CSV \n ",49565]
["Infrabel","49567","Athus - Meuse","< >","Y.NEFFE","GENDRON-CELLES",2023,2023,10,11,"2023-03-11",44568.000694444447,"2023-03-13",44568.166666666664,"2d","Continuous",null,"T","","Basculement 25 kV jusque Neffe. \n ",49567]
["Infrabel","49568","Athus - Meuse","< >","Y.NEFFE","GENDRON-CELLES",2023,2023,11,12,"2023-03-18",44568.000694444447,"2023-03-20",44568.166666666664,"2d","Continuous",null,"T","","Basculement 25 kV jusque Neffe. \n ",49568]
["Infrabel","49569","Athus - Meuse","< >","Y.NEFFE","GENDRON-CELLES",2023,2023,12,13,"2023-03-25",44568.000694444447,"2023-03-27",44568.166666666664,"2d","Continuous",null,"T","","Basculement 25 kV jusque Neffe.\r\nRemplacement de deux tabliers métalliques à pose directe VA à la bk 7,591 - Préparations \n ",49569]
["Infrabel","49570","Athus - Meuse","< >","BERTRIX","VONECHE",2023,2023,3,4,"2023-01-21",44568.25,"2023-01-23",44568.166666666664,"2d","Continuous",null,"T","","Renouvellement PN1 Gedinne \n ",49570]
["Infrabel","49571","Athus - Meuse","< >","BERTRIX","VONECHE",2023,2023,4,5,"2023-01-28",44568.25,"2023-01-30",44568.166666666664,"2d","Continuous",null,"T","","Renouvellement PN1 Gedinne \n ",49571]
["Infrabel","49584","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,4,5,"2024-01-26",44568.972222222219,"2024-01-29",44568.194444444445,"3d","Continuous",null,"T","","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 1/6\r\nDépose transversale caténaire\r\nDossier de concertation validé le 28 octobre 2021\r\nRq 333 : demande EF's de déplacer au WE du 20/01 \n ",49584]
["Infrabel","49585","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,15,16,"2024-04-08","2022-01-07T08:00:00","2024-04-19","2022-01-07T15:00:00","11d","Periodical",null,"T","","Aménagement Gare de Luttre : Phase 4-2024\r\nDossier de concertation validé le 28 octobre 2021 \n ",49585]
["Infrabel","49592","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2023,2023,10,11,"2023-03-11",44568.25,"2023-03-13",44568.166666666664,"2d","Continuous",null,"T","","Maintenance \n",49592]
["Infrabel","49593","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2023,2023,36,37,"2023-09-09",44568.25,"2023-09-11",44568.166666666664,"2d","Continuous",null,"T","","Maintenance \n",49593]
["Infrabel","49597","Athus - Meuse","< >","PALISEUL","BERTRIX",2024,2024,44,45,"2024-11-01","2022-01-07T08:00:00","2024-11-03","2022-01-07T16:00:00","2d","Continuous",null,"T","","Mise en service PLP et modifications ETCS gare de Bertrix et bloc automatique Libramont - Bertrix. \n ",49597]
["Infrabel","49776","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,7,8,"2024-02-16",44568.972222222219,"2024-02-19",44568.194444444445,"3d","Continuous",null,"T","","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 3/6\r\nDossier de concertation validé le 28 octobre 2021\r\nRq 333 : demande EF's de déplacer au WE du 02/02 \n ",49776]
["Infrabel","49777","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,8,9,"2024-02-23",44568.972222222219,"2024-02-26",44568.194444444445,"3d","Continuous",null,"T","","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 4/6\r\nDossier de concertation validé le 28 octobre 2021 \n ",49777]
["Infrabel","49778","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,9,10,"2024-03-01","2022-01-07T23:20:00","2024-03-04","2022-01-07T04:40:00","3d","Continuous",null,"T","","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 5/6\r\nDossier de concertation validé le 28 octobre 2021 \n ",49778]
["Infrabel","49779","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,10,11,"2024-03-08","2022-01-07T23:20:00","2024-03-11","2022-01-07T04:40:00","3d","Continuous",null,"T","","Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 6/6\r\nDossier de concertation validé le 28 octobre 2021 \n ",49779]
["Infrabel","49859","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","ANTWERPEN-NOORD-INRIT C1",2024,2024,19,24,"2024-05-10","2022-01-07T23:00:00","2024-06-10","2022-01-07T05:00:00","31d","Continuous",null,"T","","LANGE TLO 4 weken: Vernieuwing wissels bundelkop C1 + verbinding tussen C1-C2 --> Fase 2 \nINFO RACC",49859]
["Infrabel","49862","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2024,2024,9,10,"2024-03-02","2022-01-07T01:00:00","2024-03-04","2022-01-07T04:30:00","2d","Continuous",null,"T","","VERNIEUWING WISSELS ESSEN\r\n3 weekends gevraagd, dienen nog trilateraal afgestemd.\r\nWij voorzien voorjaar 2024 om niet in het vaarwater te zitten van de grote werken op het Duitse net (najaar 2024 tot voorjaar 2026). \n ",49862]
["Infrabel","49889","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2024,2024,6,8,"2024-02-10",44568.041666666664,"2024-02-19",44568.208333333336,"9d","Continuous",null,"T","","Vernieuwing sporen. \n",49889]
["Infrabel","49891","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2023,2023,24,36,"2023-06-12",44568.1875,"2023-09-04",44568.1875,"84d","Continuous",null,"T","","L12 Engelselei – waterdichte rokken vervangen \n ",49891]
["Infrabel","49893","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,21,22,"2024-05-24","2022-01-07T23:30:00","2024-05-27","2022-01-07T06:00:00","3d","Continuous",null,"T","","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 1/4 (AS 21Q, 22Q) \nInfo Racc : raccordement inaccessible",49893]
["Infrabel","49894","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,22,23,"2024-05-31","2022-01-07T23:30:00","2024-06-03","2022-01-07T06:00:00","3d","Continuous",null,"T","","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 2/4 (AS 19BQ, 18Q) \nInfo Racc : raccordement inaccessible",49894]
["Infrabel","49895","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,23,24,"2024-06-07","2022-01-07T23:30:00","2024-06-10","2022-01-07T06:00:00","3d","Continuous",null,"T","","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 3/4 (AS 19AQ) \nInfo Racc : raccordement inaccessible",49895]
["Infrabel","49896","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,25,26,"2024-06-21","2022-01-07T23:30:00","2024-06-24","2022-01-07T06:00:00","3d","Continuous",null,"T","","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 4/4 - Bourrage de révision et réglage des contraintes \nInfo Racc : raccordement inaccessible",49896]
["Infrabel","49897","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,26,26,"2024-06-24","2022-01-07T09:00:00","2024-06-28","2022-01-07T15:30:00","4d","Periodical",null,"T","","Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nFinitions \nInfo Racc : raccordement inaccessible",49897]
["Infrabel","49928","Athus - Meuse",">","YVOIR","DINANT",2024,2024,14,15,"2024-04-01","2022-01-07T08:30:00","2024-04-10","2022-01-07T05:00:00","9d","Continuous",null,"","ST","Renouvellement de Ballast (C75) \n ",49928]
["Infrabel","49929","Athus - Meuse",">","YVOIR","DINANT",2024,2024,15,17,"2024-04-10","2022-01-07T09:00:00","2024-04-22","2022-01-07T15:00:00","12d","Continuous",null,"","ST","Renouvellement de Ballast (C75) \n ",49929]
["Infrabel","49930","Athus - Meuse","< >","YVOIR","DINANT",2024,2024,14,15,"2024-04-05","2022-01-07T23:50:00","2024-04-08","2022-01-07T04:20:00","3d","Continuous",null,"T","","Renouvellement de Ballast (C75)\r\nWE 1/6 \n ",49930]
["Infrabel","49931","Athus - Meuse","< >","YVOIR","DINANT",2024,2024,15,15,"2024-04-08","2022-01-07T09:00:00","2024-04-08","2022-01-07T15:00:00","0d","Continuous",null,"T","","Renouvellement de Ballast (C75)\r\nWE 1/3 \n ",49931]
["Infrabel","49932","Athus - Meuse","< >","YVOIR","DINANT",2024,2024,15,16,"2024-04-12","2022-01-07T23:50:00","2024-04-15","2022-01-07T04:20:00","3d","Continuous",null,"T","","Renouvellement de Ballast (C75)\r\nWE 2/6 \n ",49932]
["Infrabel","49933","Athus - Meuse","< >","YVOIR","DINANT",2024,2024,16,17,"2024-04-19","2022-01-07T23:50:00","2024-04-22","2022-01-07T04:20:00","3d","Continuous",null,"T","","Renouvellement de Ballast (C75)\r\nWE 3/6 \n ",49933]
["Infrabel","49934","Athus - Meuse","< >","YVOIR","DINANT",2024,2024,17,18,"2024-04-26","2022-01-07T23:50:00","2024-04-29","2022-01-07T04:20:00","3d","Continuous",null,"T","","Renouvellement de Ballast (C75)\r\nWE 4/6 \n ",49934]
["Infrabel","49935","Athus - Meuse","< >","YVOIR","DINANT",2024,2024,18,19,"2024-05-03","2022-01-07T23:50:00","2024-05-06","2022-01-07T04:20:00","3d","Continuous",null,"T","","Renouvellement de Ballast (C75)\r\nWE 5/6 \n ",49935]
["Infrabel","49936","Athus - Meuse","< >","YVOIR","DINANT",2024,2024,19,20,"2024-05-10","2022-01-07T23:50:00","2024-05-13","2022-01-07T04:20:00","3d","Continuous",null,"T","","Renouvellement de Ballast (C75)\r\nWE 6/6 \n ",49936]
["Infrabel","49937","Athus - Meuse","< >","YVOIR","DINANT",2024,2024,16,16,"2024-04-15","2022-01-07T09:00:00","2024-04-15","2022-01-07T15:00:00","0d","Continuous",null,"T","","Renouvellement de Ballast (C75)\r\nWE 2/3 \n ",49937]
["Infrabel","49938","Athus - Meuse","< >","YVOIR","DINANT",2024,2024,17,17,"2024-04-22","2022-01-07T09:00:00","2024-04-22","2022-01-07T15:00:00","0d","Continuous",null,"T","","Renouvellement de Ballast (C75)\r\nWE 3/3 \n ",49938]
["Infrabel","49945","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2023,2023,50,51,"2023-12-16",44568.006944444445,"2023-12-18",44568.173611111109,"2d","Continuous",null,"T","","IDS SIW Waregem - Deinze\r\ntestritten op zondag in overleg met regelaar\r\nuitwijk testloco in bundel Deinze\r\n+\r\nIDS\r\nETCS L2-IL_NW_P014_05_L75_Deinze - Waregem_IL \n ",49945]
["Infrabel","49948","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2023,2023,13,14,"2023-04-01",44568.25,"2023-04-03",44568.180555555555,"2d","Continuous",null,"T","","IDS SIW  Beervelde-Y. Sint Bernadettestraat\r\ntestritten op zondag in overleg met regelaar\r\ntestloco uitwijken naar bundel D/E FGZH\r\n+\r\nIDS ETCS L2-IL_NW_P025_01_L59_Y-St Bernadettestraat - Beervelde_IL \n ",49948]
["Infrabel","49950","Lille - Antwerpen","< >","DE PINTE","Y.ZANDBERG",2023,2023,4,5,"2023-01-28",44568.013888888891,"2023-01-30",44568.166666666664,"2d","Continuous",null,"T","","IDS SIW in Deinze\r\ntestritten op zondag in overleg met regelaar\r\ntestloco uitwijken in bundel Deinze \n ",49950]
["Infrabel","49951","Lille - Antwerpen","< >","DE PINTE","Y.ZANDBERG",2023,2023,5,6,"2023-02-04",44568.013888888891,"2023-02-06",44568.166666666664,"2d","Continuous",null,"T","","IDS SIW in Deinze\r\ntestritten op zondag in overleg met regelaar\r\ntestloco uitwijken in bundel Deinze \n ",49951]
["Infrabel","49952","Lille - Antwerpen","< >","DE PINTE","Y.ZANDBERG",2023,2023,3,4,"2023-01-21",44568.013888888891,"2023-01-23",44568.166666666664,"2d","Continuous",null,"T","","IDS SIW in Deinze\r\ntestritten op zondag in overleg met regelaar\r\ntestloco uitwijken in bundel Deinze\r\n\r\nIDS ETCS2 Y.Zandberg - Waregem op zondagmorgen \n ",49952]
["Infrabel","49980","Lille - Charleroi",">","BRUXELLES-MIDI","Y.NOORD HALLE",2024,2024,21,22,"2024-05-24","2022-01-07T23:40:00","2024-06-01","2022-01-07T04:30:00","8d","Continuous",null,"","ST","Vernieuwen sp A L96 met P+C-trein. Fase 2 WE1-W1 \n ",49980]
["Infrabel","49981","Lille - Charleroi",">","BRUXELLES-MIDI","Y.NOORD HALLE",2024,2024,22,24,"2024-05-31","2022-01-07T23:40:00","2024-06-15","2022-01-07T04:30:00","15d","Continuous",null,"","ST","Vernieuwen sp A L96 met P+C-trein. Fase 2 WE2-W2-WE3-W3 \n ",49981]
["Infrabel","49982","Lille - Charleroi","< >","Y.RUISBROEK","Y.NOORD HALLE",2024,2024,20,21,"2024-05-18","2022-01-07T00:40:00","2024-05-21","2022-01-07T04:40:00","3d","Continuous",null,"T","","Vernieuwing met P+C-trein Fase 3 WE4 \n ",49982]
["Infrabel","50039","Lille - Charleroi","< >","Y.RUISBROEK","Y.NOORD HALLE",2024,2024,26,27,"2024-06-29","2022-01-07T00:40:00","2024-07-01","2022-01-07T04:40:00","2d","Continuous",null,"T","","Vernieuwing TB perron Buizingen met kraan. Fase 1 WE 3/3. \n ",50039]
["Infrabel","50040","Lille - Charleroi","< >","BRUXELLES-MIDI","Y.NOORD HALLE",2024,2024,19,20,"2024-05-11","2022-01-07T00:40:00","2024-05-13","2022-01-07T04:40:00","2d","Continuous",null,"T","","Vernieuwing TB perron Lot met kraan. Fase 1 WE 2/3 + voorbereidingsWE Fase 2 \n ",50040]
["Infrabel","50041","Lille - Charleroi","< >","BRUXELLES-MIDI","Y.NOORD HALLE",2024,2024,18,18,"2024-04-30","2022-01-07T00:40:00","2024-05-04","2022-01-07T04:40:00","4d","Periodical",null,"T","","Vernieuwen sp A L96: voorbereidende nachten Fase 2 \n ",50041]
["Infrabel","50042","Lille - Charleroi","< >","BRUXELLES-MIDI","Y.NOORD HALLE",2024,2024,19,19,"2024-05-07","2022-01-07T00:40:00","2024-05-10","2022-01-07T04:40:00","3d","Periodical",null,"T","","Vernieuwen sp A L96: voorbereidende nachten Fase 2 \n ",50042]
["Infrabel","50043","Lille - Charleroi","< >","BRUXELLES-MIDI","Y.NOORD HALLE",2024,2024,20,20,"2024-05-14","2022-01-07T00:40:00","2024-05-17","2022-01-07T04:40:00","3d","Periodical",null,"T","","Vernieuwen sp A L96: voorbereidende nachten Fase 2 \n ",50043]
["Infrabel","50044","Lille - Charleroi",">","BRUXELLES-MIDI","Y.NOORD HALLE",2024,2024,25,26,"2024-06-21","2022-01-07T23:40:00","2024-06-24","2022-01-07T04:30:00","3d","Continuous",null,"","ST","Vernieuwen sp A L96: afwerkingsWE 1/2 Fase 2 \n ",50044]
["Infrabel","50045","Lille - Charleroi",">","BRUXELLES-MIDI","Y.NOORD HALLE",2024,2024,27,28,"2024-07-05","2022-01-07T23:40:00","2024-07-08","2022-01-07T04:30:00","3d","Continuous",null,"","ST","Vernieuwen sp A L96: afwerkingsWE 2/2 Fase 2 \n ",50045]
["Infrabel","50046","Lille - Charleroi","< >","Y.RUISBROEK","Y.NOORD HALLE",2024,2024,28,29,"2024-07-13","2022-01-07T00:40:00","2024-07-15","2022-01-07T04:40:00","2d","Continuous",null,"T","","Vernieuwen sp A L96: afwerkingsWE Fase 3 \n ",50046]
["Infrabel","50074","Namur - Antwerpen","< >","TAMINES","LE CAMPINAIRE",2023,2023,42,42,"2023-10-16",44568.972222222219,"2023-10-20",44568.208333333336,"4d","Periodical",null,"T","","Renouvellement PS 85.708\r\nNuits de préparation \n ",50074]
["Infrabel","50075","Namur - Antwerpen","< >","TAMINES","LE CAMPINAIRE",2023,2023,43,43,"2023-10-23",44568.965277777781,"2023-10-28",44568.208333333336,"5d","Periodical",null,"T","","Renouvellement PS 85.708\r\nNuits \n ",50075]
["Infrabel","50076","Namur - Antwerpen","< >","TAMINES","LE CAMPINAIRE",2023,2023,44,44,"2023-10-30",44568.972222222219,"2023-11-04",44568.208333333336,"5d","Periodical",null,"T","","Renouvellement PS 85.708\r\nNuits \n ",50076]
["Infrabel","50189","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2023,2023,15,15,"2023-04-10",44568.930555555555,"2023-04-11",44568.180555555555,"1d","Periodical",null,"T","","Travaux SNCF CHA23_0025211 \r\nRecquignies Maintenance – Bourrage appareils de voie \n ",50189]
["Infrabel","50289","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","ANTWERPEN-BERCHEM",2022,2022,9,10,"2022-02-26",44568.041666666664,"2022-02-28",44568.1875,"2d","Continuous",null,"T","","Y West Berchem\r\nUPM R-312983 \nHKM om te leiden.",50289]
["Infrabel","50290","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","ANTWERPEN-BERCHEM",2022,2022,10,11,"2022-03-05",44568.041666666664,"2022-03-07",44568.1875,"2d","Continuous",null,"T","","Y West Berchem\r\nUPM R-312984 \nHKM om te leiden.",50290]
["Infrabel","50291","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","ANTWERPEN-BERCHEM",2022,2022,11,12,"2022-03-12",44568.041666666664,"2022-03-14",44568.1875,"2d","Continuous",null,"T","","Y West Berchem\r\nUPM R-312985 \nHKM om te leiden.",50291]
["Infrabel","50294","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2023,2023,17,18,"2023-04-29",44568.25,"2023-05-02",44568.166666666664,"3d","Continuous",null,"T","","AWV Asbest sanering - brug E40\r\n+\r\nOnderhoud Arrondisement \n",50294]
["Infrabel","50295","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2023,2023,18,19,"2023-05-06",44568.25,"2023-05-08",44568.166666666664,"2d","Continuous",null,"T","","AWV Asbest sanering - brug E40 \n",50295]
["Infrabel","50482","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2023,2023,9,10,"2023-03-04",44568.013888888891,"2023-03-06",44568.166666666664,"2d","Continuous",null,"T","","Testen \r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL \n ",50482]
["Infrabel","51730","Lille - Charleroi","< >","BRAINE-LE-COMTE","SOIGNIES",2023,2023,41,41,"2023-10-09",44568.958333333336,"2023-10-13",44568.1875,"4d","Periodical",null,"T","","Renouvellement des traverses Y Soignies - Braine\r\nPréparations \n ",51730]
["Infrabel","51739","Lille - Charleroi","< >","ATH","LEUZE",2023,2023,35,35,"2023-08-28",44568.961805555555,"2023-09-02",44568.1875,"5d","Periodical",null,"T","","Criblage de ballast - C75 nuits prépa \n ",51739]
["Infrabel","51740","Lille - Charleroi","< >","ATH","LEUZE",2023,2023,36,36,"2023-09-04",44568.961805555555,"2023-09-09",44568.1875,"5d","Periodical",null,"T","","Criblage de ballast - C75 nuits prépa \n ",51740]
["Infrabel","51868","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,19,22,"2024-05-06","2022-01-07T06:00:00","2024-05-27","2022-01-07T04:30:00","21d","Continuous",null,"","ST","Chantier peignage paroi\r\nProjet pâturage chèvre \n ",51868]
["Infrabel","52086","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2023,2023,9,9,"2023-02-27",44568.979166666664,"2023-03-03",44568.1875,"4d","Periodical",null,"T","","Testen \r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nR5/R6 in weekend TLO \n ",52086]
["Infrabel","52099","Athus - Meuse",">","Y.NEFFE","GENDRON-CELLES",2022,2022,15,16,"2022-04-04",44568.25,"2022-04-15",44568.708333333336,"11d","Continuous",null,"","ST","Réalisation d'une dalle en béton armé pour l'étanchéité de la culée-voûte à la bk 8,509 - côté voie B\r\nSécurisation parois rocheuses du 10.01 8:00 au 1.04 18:00 (Javaux)\r\nUPM: 308199\r\n\r\n=> Englobée par la demande 48847 qui se déroule du 21/02/21 au 15/0 \nPas de croisements prévus au saisonnier pour la période Pert de février\r\nHKM à adapter du 04 au 15/04",52099]
["Infrabel","52192","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2023,2023,1,2,"2023-01-07",44568.013888888891,"2023-01-09",44568.166666666664,"2d","Continuous",null,"T","","ETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\n+ stukje L86 tot Gavere-Asper\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL \n ",52192]
["Infrabel","52194","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2023,2023,2,3,"2023-01-14",44568.013888888891,"2023-01-16",44568.166666666664,"2d","Continuous",null,"T","","ETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\n+ stukje L86 tot Gavere-Asper\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL \n ",52194]
["Infrabel","52344","Lille - Antwerpen","< >","LOKEREN","Y.BERNADETTESTRAAT",2022,2022,8,9,"2022-02-19",44568.027777777781,"2022-02-21",44568.180555555555,"2d","Continuous",null,"T","","buitenwerken ETCS L59-Y.Bernadettestraat - Beervelde\r\nbuitenwerken ETCS L59-Beervelde - Lokeren \nINFO RACC\r\nHK om te leiden",52344]
["Infrabel","52731","Namur - Antwerpen","< >","TAMINES","LE CAMPINAIRE",2023,2023,29,29,"2023-07-17",44568.972222222219,"2023-07-20",44568.208333333336,"3d","Periodical",null,"T","","Renouvellement PS 85.708\r\nNuits de préparation \n ",52731]
["Infrabel","52732","Namur - Antwerpen","< >","TAMINES","LE CAMPINAIRE",2023,2023,30,30,"2023-07-24",44568.972222222219,"2023-07-29",44568.208333333336,"5d","Periodical",null,"T","","Renouvellement PS 85.708\r\nNuits \n ",52732]
["Infrabel","52734","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,17,18,"2024-04-27","2022-01-07T23:40:00","2024-04-29","2022-01-07T05:00:00","2d","Periodical",null,"T","","Aménagement gare de Floreffe\r\nWE 5/6\r\nDossier de concertation validé le 26 octobre 2021 \n ",52734]
["Infrabel","52735","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,18,19,"2024-05-04","2022-01-07T23:40:00","2024-05-06","2022-01-07T05:00:00","2d","Periodical",null,"T","","Aménagement gare de Floreffe\r\nWE 6/6\r\nDossier de concertation validé le 26 octobre 2021 \n ",52735]
["Infrabel","52824","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","ANTWERPEN-CENTRAAL",2023,2023,11,12,"2023-03-18",44568.041666666664,"2023-03-20",44568.166666666664,"2d","Continuous",null,"T","","Onderhoud wissels Antwerpen-Centraal +1\r\nAntwerpen Centraal Niveau +1 gaat gefaseerd buiten dienst  (fasering nog te bepalen)\r\nUren zullen worden bepaald na bekendmaking fasering \n ",52824]
["Infrabel","52825","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","ANTWERPEN-CENTRAAL",2023,2023,34,35,"2023-08-26",44568.041666666664,"2023-08-28",44568.166666666664,"2d","Continuous",null,"T","","Onderhoud wissels Antwerpen-Centraal +1\r\n\r\nAntwerpen Centraal niveau +1 gaat gefaseerd buiten dienst voor onderhoud wissels (fasering nog uit te werken)\r\n\r\nuren nog te bepalen bij uitwerking fasering \n ",52825]
["Infrabel","52947","Lille - Charleroi","< >","Y.RUISBROEK","Y.NOORD HALLE",2024,2024,18,19,"2024-05-04","2022-01-07T00:40:00","2024-05-06","2022-01-07T04:40:00","2d","Continuous",null,"T","","Vernieuwing TB perron Lot met kraan. Fase 1 WE 1/3. \n ",52947]
["Infrabel","52980","Lille - Antwerpen","< >","GENT-SINT-PIETERS","WAREGEM",2024,2024,1,2,"2024-01-03",44568.916666666664,"2024-01-08",44568.166666666664,"5d","Continuous",null,"T","","Backup IDS weekend\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\n\r\nFGSP NIET IN\r\nFVG bereikbaar kant Kortrijk \n ",52980]
["Infrabel","53212","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2023,2023,13,14,"2023-03-31",44568.979166666664,"2023-04-03",44568.208333333336,"3d","Continuous",null,"T","","CR -  CSV Froyennes \n",53212]
["Infrabel","53304","Lille - Antwerpen","< >","DEINZE","GENT-SINT-PIETERS",2024,2024,19,20,"2024-05-09","2022-01-07T00:30:00","2024-05-13","2022-01-07T04:00:00","4d","Continuous",null,"T","","IDS SIW L75-De Pinte - De Pinte - Gent-Sint-Pieters\r\nGEEN ANDERE WERKEN MOGELIJK \n ",53304]
["Infrabel","Continuous","Namur - Antwerpen","","A+B","FLEURUS",2022,2022,44,45,"2022-10-28",44568.979166666664,"2022-10-31",44568.208333333336,"3d","periodical","CHARLEROI-OUEST","",""," ","Continuous"]
["Infrabel","Continuous","Lille - Charleroi","","A+B","MONS",2022,2022,7,8,"2022-02-12",44568.003472222219,"2022-02-13",44568.996527777781,"1d","periodical","QUEVY","","","V01 --> 30/11/2021\r\nP01 --> 19/10/2021\r\nSW_2022_L96_06_Mons_Quevy-Finition chantier P93-du 12 au 13 février","Continuous"]
["Infrabel","Continuous","Athus - Meuse","","A+B","SAINT-VINCENT-BELLEFONTAINE",2022,2022,43,44,"2022-10-22",44568.958333333336,"2022-10-23",44568.666666666664,"1d","periodical","VIRTON","",""," ","Continuous"]
["Infrabel","Day","Athus - Meuse","","A","BERTRIX",2022,2022,50,51,"2022-12-05",44568.333333333336,"2022-12-16",44568.666666666664,"11d","periodical","FLORENVILLE","",""," ","Day"]
["Infrabel","Night","Lille - Antwerpen","","A+B","DEINZE",2023,2023,14,14,"2023-04-03",44568.979166666664,"2023-04-08",44568.1875,"5d","periodical","GENT-SINT-PIETERS","","",0,"Night"]
["Infrabel","Night","Namur - Antwerpen","","A+B","FLEURUS",2022,2022,41,41,"2022-10-03",44568.958333333336,"2022-10-07",44568.208333333336,"4d","periodical","CHARLEROI-OUEST","",""," ","Night"]

{"sheet":"Data","index":4,"n_rows":24,"n_cols":7,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction"]
["SNCF R",87,"Boulogne-Calais",1,"All day",10868,"Signal work"]
[null,null,"Calais-Dunkerque-Hazebrouck",2,"Day",null,"Switch work"]
[null,null,"Calais-Lille-Aulnoye",3,"Night",null,"Catenary work"]
[null,null,"Hazebrouck-Lens-Aulnoye",4,null,null,"Track work"]
[null,null,"Amiens-Douai",5,null,null,"Rail work"]
[null,null,"Paris-Amiens",6,null,null,"Tunnel work"]
[null,null,"Paris-Busigny",7,null,null,"Bridge work"]
[null,null,"Aulnoye-Longuyon",8,null,null,"Misc. Work"]
[null,null,"Longuyon-Metz-Sarrebourg",9,null,null,"Maintanance"]
[null,null,"Longuyon-Nancy-Sarrebourg",10]
[null,null,"Lerouville-Metz",11]
[null,null,"Lerouville-Nancy",12]
[null,null,"Sarrebourg-Basel",13]
[null,null,"Dijon-Toul",14]
[null,null,"Dijon-Lyon",15]
[null,null,"Dijon-Amberieu-Lyon",16]
[null,null,"Lyon-Valence",17]
[null,null,"Valence - Avignon",18]
[null,null,"Avignon-Miramasparouest",19]
[null,null,"Avignon-Miramasparest",20]
[null,null,"Miramas-Marseille",21]
[null,null,"Miramas-Fos-Marseille",22]
[null,null,"Aulnoye-Feignies-Jeumont",23]

{"sheet":"SNCFR","index":5,"n_rows":108,"n_cols":36,"rows_kept":108,"cut":false,"hidden":false,"merged":[[1,23,1,27],[3,0,104,0],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]]}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","Last update","Classification","Weekdays","Status","Automatic process","Bitmap Days","Variant"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","No catenary","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,87,"3C_HAU_008","LilleBifJustice","< >","Lille-Flandres - Bât Voyageurs","Lille-St-Sauveur - E/S Faisceaux",2023,2023,14,15,"2023-04-09","14:00:00","2023-04-10","10:00:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 0,1,AM,DM,N,SA,V1,V2, 20:00, Passe-minuit, DI/LU","2022-01-07","unclassified","1, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_HAU_019","LilleBifJustice","< >","Lille-Flandres - Bât Voyageurs","Lille-St-Sauveur - E/S Faisceaux",2023,2023,36,38,"2023-09-09","20:00:00","2023-09-24","11:00:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 0,1,AM,DM,N,SA,V1,V2, 15:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LE_002","LilleFlandres","< >","Lille-Flandres - Bif Verte-Rue","Lille-Flandres - Bif Verte-Rue",2023,2023,9,9,"2023-03-04","15:20:00","2023-03-05","15:21:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, RB1,RB2,V1,V2, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000011000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LE_003","LilleFlandres","< >","Lille-Flandres - Bif Verte-Rue","Lille-Flandres - Bif Verte-Rue",2023,2023,28,29,"2023-07-14","05:00:00","2023-07-17","05:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, RB1,RB2,V1,V2, 72:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LE_004","LilleFlandres","< >","Lille-Flandres - Bif Verte-Rue","Lille-Flandres - Bif Verte-Rue",2023,2023,32,33,"2023-08-12","14:20:00","2023-08-15","14:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, RB1,RB2,V1,V2, 72:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LE_013","LilleFlandres","< >","Lille-Flandres - Ent/Sort VA TGV","Lille-Flandres - Jonct V2/V1",2023,2023,14,15,"2023-04-09","14:00:00","2023-04-10","10:00:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 2,V1,V1,V2,V2, 20:00, Passe-minuit, DI/LU","2022-01-07","unclassified","1, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LE_032","LilleFlandres","< >","Lille-Flandres - Ent/Sort VA TGV","Lille-Flandres - Bât Voyageurs",2023,2023,36,38,"2023-09-09","20:00:00","2023-09-24","11:00:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 2,V1,V2, 15:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_ORM-LWP_2","Ormoy-Longueil","< >","Verberie - Bif d'Ageux","Longueil-Ste-Marie - Bif Rivecourt",2023,2023,12,27,"2023-03-24","23:35:00","2023-07-03","04:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, VR1,VR2,VU, 52:55, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100011110001111000111100011110001111000111100000000000000000000000000000000000000000000000000001111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_ORM-LWP_2","Ormoy-Longueil","< >","Ormoy-Villiers","Estrées-St-Denis - Bât Voyageurs",2023,2023,12,27,"2023-03-24","23:35:00","2023-07-03","04:30:00",null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 52:55, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100011110001111000111100011110001111000111100000000000000000000000000000000000000000000000000001111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LWP-TGR_1","Longueil Ste Marie-Tergnier",">","Compiègne - ITE Nourylande","Compiègne - Garage Impair",2023,2023,12,45,"2023-03-24","23:39:00","2023-11-06","23:39:00",null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Cap, 3,5,7,9, 53:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100000000000000000000000000000000000000000000011110001111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100011110001111000000000000000001111000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LWP-TGR_2","Longueil Ste Marie-Tergnier",">","Compiègne - ITE Nourylande","Compiègne - Garage Impair",2023,2023,13,15,"2023-03-31","23:39:00","2023-04-10","23:39:00",null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Cap, 5,7,9, 53:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011110001111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LWP-TGR_3","Longueil Ste Marie-Tergnier",">","Compiègne - ITE Nourylande","Compiègne - Garage Impair",2023,2023,15,28,"2023-04-14","23:39:00","2023-07-10","23:39:00",null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Cap, 3,9, 53:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100000000000000000000000000000000000000000000000000000000000000000000000001111000111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_LWP-TGR_2","Longueil Ste Marie-Tergnier","< >","Compiègne - ITE Nourylande","Compiègne - Garage Impair",2023,2023,15,28,"2023-04-14","23:39:00","2023-07-10","23:39:00",null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 53:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100000000000000000000000000000000000000000000000000000000000000000000000001111000111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_TGR1_002","Tergnier(242000)","<","Tergnier - Bât Voyageurs","Ternier - Triage",2023,2023,12,"12","2023-03-25","21:00:00","2023-03-26","14:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 4,6, 17:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_TGR1_003","Tergnier(242000)","<","Tergnier - Bât Voyageurs","Ternier - Triage",2023,2023,14,15,"2023-04-08","01:00:00","2023-04-10","01:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 4,6, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_TGR1_004","Tergnier(242000)","<","Tergnier - Bât Voyageurs","Ternier - Triage",2023,2023,15,19,"2023-04-15","15:00:00","2023-05-14","15:01:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 4,6, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011000000000000000000000000001100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_TGR1_005","Tergnier(242000)","<","Tergnier - Bât Voyageurs","Ternier - Triage",2023,2023,16,16,"2023-04-22","00:40:00","2023-04-23","16:40:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 4,6, 40:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_TGR1_006","Tergnier(242000)","<","Tergnier - Bât Voyageurs","Ternier - Triage",2023,2023,17,17,"2023-04-29","10:50:00","2023-04-30","16:50:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 4,6, 30:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_TGR2_003","Tergnier(261000)","<","Tergnier - Accès Nord","Fargniers-Garage - ITE ALB",2023,2023,14,15,"2023-04-08","01:00:00","2023-04-10","01:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 12,V1,V2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_TGR-LAO_2","Ternier-Laon","< >","Tergnier - Bât Voyageurs","Laon - Bât Voyageurs",2023,2023,12,12,"2023-03-25","21:00:00","2023-03-26","14:00:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 17:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_TGR-LAO_3","Ternier-Laon","< >","Tergnier - Bât Voyageurs","Laon - Bât Voyageurs",2023,2023,14,15,"2023-04-08","01:00:00","2023-04-10","01:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_TGR-LAO_4","Ternier-Laon","< >","Tergnier - Bât Voyageurs","Laon - Bât Voyageurs",2023,2023,15,19,"2023-04-15","15:00:00","2023-05-14","15:01:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011000000000000000000000000001100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_TGR-LAO_5","Ternier-Laon","< >","Tergnier - Bât Voyageurs","Laon - Bât Voyageurs",2023,2023,16,16,"2023-04-22","00:40:00","2023-04-23","16:40:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 40:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_TGR-LAO_6","Ternier-Laon","< >","Tergnier - Bât Voyageurs","Laon - Bât Voyageurs",2023,2023,17,17,"2023-04-29","10:50:00","2023-04-30","16:50:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 30:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_TGR-LAO_10","Ternier-Laon","< >","Fargniers-Garage - ITE ALB","Laon - Bât Voyageurs",2023,2023,28,29,"2023-07-13","22:45:00","2023-07-17","04:45:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 78:00, Continu, LU,JE,VE,SA,DI","2022-01-07","unclassified","1, 4, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_TGR-LAO_11","Ternier-Laon","< >","Fargniers-Garage - ITE ALB","Laon - Bât Voyageurs",2023,2023,32,33,"2023-08-11","22:20:00","2023-08-15","12:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 86:00, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_AYE1_002","Aulnoye(242000)","< >","Aulnoye-Aymeries - Poste 1","Aulnoye-Aymeries - Poste 3",2023,2023,32,33,"2023-08-12","23:30:00","2023-08-14","03:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 10,4,6,8,B,C,D1,D3,DM,E,F,K,L2,L4,O,P,R,V1,V2, 28:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_RNG-BE_3","Rang-Boulogne","< >","Conchil-le-Temple","Boulogne-Ville - Bif d'Outreau",2023,2023,39,39,"2023-09-29","22:00:00","2023-10-01","18:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, 3,4,V1,V2, 2V/2, 44:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_BE-MRX_3","Boulogne-Marquise","< >","Boulogne-Tintelleries","Marquise-Rinxent",2023,2023,8,9,"2023-02-24","23:00:00","2023-02-27","03:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 52:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000001111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_MRX-CS_3","Marquise-Calais","<","Wimille-Wimereux","Le Haut-Banc",2023,2023,8,9,"2023-02-24","23:00:00","2023-02-27","03:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 4, 52:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000001111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_MRX-CS_4","Marquise-Calais","<","Wimille-Wimereux","Le Haut-Banc",2023,2023,9,13,"2023-03-04","17:55:00","2023-04-02","15:55:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 4, 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000001000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_MRX-CS_5","Marquise-Calais","<","Wimille-Wimereux","Le Haut-Banc",2023,2023,11,11,"2023-03-18","20:20:00","2023-03-19","10:20:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 4, 14:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_MRX-CS_7","Marquise-Calais","<","Wimille-Wimereux","Le Haut-Banc",2023,2023,14,15,"2023-04-08","17:55:00","2023-04-16","15:55:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 4, 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000100000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_MRX-CS_4","Marquise-Calais","< >","Wimille-Wimereux","Calais-Fréthun - C102/204",2023,2023,9,13,"2023-03-04","17:55:00","2023-04-02","15:55:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000001000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_MRX-CS_5","Marquise-Calais","< >","Wimille-Wimereux","Calais-Fréthun - C102/205",2023,2023,11,11,"2023-03-18","20:20:00","2023-03-19","10:20:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 14:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_MRX-CS_7","Marquise-Calais","< >","Wimille-Wimereux","Caffiers - Bât Voyageurs",2023,2023,14,15,"2023-04-08","17:55:00","2023-04-16","15:55:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000100000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_CS_019","Calais","< >","Calais-Ville - Bât Voyageurs","Calais-Ville - Bât Voyageurs",2023,2023,43,44,"2023-10-28","04:00:00","2023-10-31","22:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, A,B,C,D,V1,V2, 90:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001111000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SRO-ABB_2","StRoch-Abbeville","< >","St-Roch (Somme) - Bif et Poste 1","Abbeville",2023,2023,19,19,"2023-05-12","23:00:00","2023-05-14","23:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 48:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_ABB-RDF_3","Abbeville-Rang","< >","Abbeville","Rang-du-Fliers-Verton",2023,2023,20,20,"2023-05-17","23:30:00","2023-05-21","23:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 96:00, Continu, ME,JE,VE,SA,DI","2022-01-07","unclassified","3, 4, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_AS_007","Amiens","< >","Amiens - Poste 1","Longueau - E/S Tergnier",2023,2023,21,21,"2023-05-27","23:00:00","2023-05-28","11:00:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, CIC,V1,V2, 12:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_LUA-AS_9","Longueau-Amiens","< >","Longueau - Bât Voyageurs","Amiens - Poste 1",2023,2023,21,21,"2023-05-27","23:00:00","2023-05-28","11:00:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 12:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_LUA-BFY_5","Longueau-BifAgnyExclue",">","Albert","Achiet",2023,2023,21,22,"2023-05-26","23:50:00","2023-05-30","03:50:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1, 1V/2, 76:00, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_LUA-BFR_5","Longueau-Bif de l'arbre Robert exclue","<","Albert","Achiet",2023,2023,21,22,"2023-05-26","23:50:00","2023-05-30","03:50:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V2, 1V/2, 76:00, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_BE_004","Boulogne   ",">","Boulogne-Ville - Bât Voyageurs","Boulogne-Tintelleries",2023,2023,9,13,"2023-03-04","17:55:00","2023-04-02","17:55:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1, 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000001000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_BE_005","Boulogne   ",">","Boulogne-Ville - Bât Voyageurs","Boulogne-Tintelleries",2023,2023,11,11,"2023-03-18","20:20:00","2023-03-19","10:20:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1, 14:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_BE_007","Boulogne   ",">","Boulogne-Ville - Bât Voyageurs","Boulogne-Tintelleries",2023,2023,14,15,"2023-04-08","17:55:00","2023-04-16","15:55:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1, 22:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000100000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LNS_001","Lens",">","Lens - Poste 3","Lens - Poste 4",2023,2023,29,29,"2023-07-17","08:00:00","2023-07-23","17:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 5, 153:00, Continu, LU,MA,ME,JE,VE,SA,DI","2022-01-07","unclassified","1, 2, 3, 4, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011111110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LNS-HZK_2","Lens-Hazebrouck",">","Béthune - E/S Béthune","Béthune - Poste 2",2023,2023,17,19,"2023-04-29","13:10:00","2023-05-08","17:10:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 3,5, 52:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LNS-HZK_3","Lens-Hazebrouck",">","Béthune - E/S Béthune","Béthune - Poste 2",2023,2023,19,19,"2023-05-13","10:30:00","2023-05-14","16:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 3,5, 30:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_LNS-HZK_2","Lens-Hazebrouck","< >","Noeudx-les-Mines","Fouquereuil - Bât Voyageurs",2023,2023,17,19,"2023-04-29","13:10:00","2023-05-08","17:10:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 52:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_LNS-HZK_3","Lens-Hazebrouck","< >","Noeudx-les-Mines","Fouquereuil - Bât Voyageurs",2023,2023,19,19,"2023-05-13","10:30:00","2023-05-14","16:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 30:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_HZK_002","Hazebrouck","< >","Hazebrouck - Bif Haute Loge","Ebblighem",2023,2023,16,17,"2023-04-22","06:30:00","2023-04-30","12:30:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1,V2, 30:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001100000110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_HZK_004","Hazebrouck",">","Hazebrouck - Bif Haute Loge","Ebblighem",2023,2023,22,22,"2023-06-03","00:30:00","2023-06-04","12:30:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1, 36:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_HZK_005","Hazebrouck","< >","Hazebrouck - Bif Haute Loge","Ebblighem",2023,2023,18,18,"2023-05-06","00:30:00","2023-05-07","12:30:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1,V2, 36:00, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_DO-OIC_6","Douai-Ostricourt","< >","Douai - Aig Km 218,5","Triangle d'Ostricourt - Bif Harponlieu",2023,2023,16,31,"2023-04-21","22:30:00","2023-08-06","22:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 48:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_DO_018","Douai   ","< >","Douai - Acc Marchandise","Pont-de-la-Deule",2023,2023,16,31,"2023-04-21","22:30:00","2023-08-06","22:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 3,4,5,6,7,9,A,B,K,V1,V1,V2,V2, 48:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_SOM1_004","Somain(262000)","<","Somain - Aig Km 230,5","Somain - ITE EDF",2022,2022,50,51,"2022-12-17","05:20:00","2022-12-19","05:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000001110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_SOM1_005","Somain(262000)","<","Somain - Aig Km 230,5","Somain - ITE EDF",2023,2023,32,33,"2023-08-12","01:20:00","2023-08-16","05:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V2, 100:00, Continu, LU,MA,ME,SA,DI","2022-01-07","unclassified","1, 2, 3, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SOM-VS_2","Somain-Valenciennes","< >","Somain - Aig Km 230,5","Beuvrages",2023,2023,50,51,"2022-12-17","05:20:00","2022-12-19","05:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000001110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SOM-VS_3","Somain-Valenciennes","< >","Somain - Aig Km 230,5","Beuvrages",2023,2023,32,33,"2023-08-12","01:20:00","2023-08-16","05:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 100:00, Continu, LU,MA,ME,SA,DI","2022-01-07","unclassified","1, 2, 3, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_VS_002","Valenciennes","< >","Raismes (Nord)","Valenciennes - Poste 1",2022,2022,50,51,"2022-12-17","05:20:00","2022-12-19","05:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, UNIQUE,V1,V2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000001110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_VS_003","Valenciennes","< >","Raismes (Nord)","Valenciennes - Poste 1",2023,2023,32,33,"2023-08-12","01:20:00","2023-08-16","05:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, UNIQUE,V1,V2, 100:00, Continu, LU,MA,ME,SA,DI","2022-01-07","unclassified","1, 2, 3, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_LZP_002","Lille-Lambersart","< >","Lille-Flandres - Jonct Lion d'Or","Lambersart - Bif 4 Maisons",2023,2023,9,9,"2023-03-04","15:20:00","2023-03-05","15:21:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000011000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_LZP_003","Lille-Lambersart","< >","Lille-Flandres - Jonct Lion d'Or","Lambersart - Bif 4 Maisons",2023,2023,28,29,"2023-07-14","05:00:00","2023-07-17","05:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 72:00, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_LZP_004","Lille-Lambersart","< >","Lille-Flandres - Jonct Lion d'Or","Lambersart - Bif 4 Maisons",2023,2023,32,33,"2023-08-12","14:20:00","2023-08-15","14:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 72:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_AYE_002","Aulnoye(267000)","< >","Aulnoye-Aymeries - Poste 1","Aulnoye-Aymeries - Bif de Leval",2023,2023,32,33,"2023-08-12","23:30:00","2023-08-14","03:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1,V1,V2,V2, 28:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_AYE-HI_2","Aulnoye-Hirson","< >","Leval","Fourmies",2023,2023,13,14,"2023-04-01","06:30:00","2023-04-03","06:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_AYE-HI_3","Aulnoye-Hirson","< >","Leval","Hirson-Écoles",2023,2023,14,15,"2023-04-08","06:30:00","2023-04-11","12:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 78:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_AYE-HI_4","Aulnoye-Hirson","< >","Leval","Hirson-Écoles",2023,2023,17,22,"2023-04-29","06:30:00","2023-05-30","06:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 72:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100011110000000000000000011110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_AYE-HI_6","Aulnoye-Hirson","< >","Leval","Fourmies",2023,2023,32,33,"2023-08-12","06:30:00","2023-08-18","06:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 150:00, Continu, LU,MA,ME,JE,VE,SA,DI","2022-01-07","unclassified","1, 2, 3, 4, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_AYE-HI_7","Aulnoye-Hirson","< >","Leval","Fourmies",2023,2023,32,33,"2023-08-12","19:00:00","2023-08-14","19:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SED-LGN_2","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,31,31,"2023-08-04","20:25:00","2023-08-06","18:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 45:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SED-LGN_3","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,32,33,"2023-08-11","20:25:00","2023-08-15","18:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 93:55, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SED-LGN_5","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,31,31,"2023-08-04","20:25:00","2023-08-06","18:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 45:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SED-LGN_6","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,32,33,"2023-08-11","20:25:00","2023-08-15","18:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 93:55, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SED-LGN_8","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,31,31,"2023-08-04","20:25:00","2023-08-06","18:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 45:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SED-LGN_9","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,32,33,"2023-08-11","20:25:00","2023-08-15","18:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 93:55, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SED-LGN_11","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,31,31,"2023-08-04","20:25:00","2023-08-06","18:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 45:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_SED-LGN_12","Sedan-Longuyon","< >","Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2023,2023,32,33,"2023-08-11","20:25:00","2023-08-15","18:20:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, , 93:55, Continu, LU,MA,VE,SA,DI","2022-01-07","unclassified","1, 2, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_EPR_010","Epernay","< >","Épernay - Bât Voyageurs","Épernay - Bif L1/22 5",2023,2023,10,15,"2023-03-10","23:30:00","2023-04-16","11:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 1B-2B,V1, 36:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_CM-BIM_008","Chalons-Blesme Haussignemont","< >","Vitry-le-François - Bât Voyageurs","Blesme-Haussignemont - Bât Voyageurs",2023,2023,15,15,"2023-04-14","23:35:00","2023-04-16","11:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 35:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_BIM1_005","Blesme Haussignemont(070000)","< >","Vitry-le-François - Aig Est-V Bis","Pargny-sur-Saulx",2023,2023,15,15,"2023-04-14","23:35:00","2023-04-16","11:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1,V2, 35:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_BIM1_007","Blesme Haussignemont(070000)","< >","Vitry-le-François - Aig Est-V Bis","Pargny-sur-Saulx",2023,2023,15,15,"2023-04-14","23:35:00","2023-04-16","11:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, V1,V2, 35:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_BIM-BLD_2","Blesme Haussignemont-Bar le Duc","< >","Revigny - Aig Km 235,8","Revigny - Aig Km 239,3",2023,2023,18,19,"2023-05-07","09:00:00","2023-05-08","10:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, 2BIS,V1, 2V/4, 25:30, Continu, LU,DI","2022-01-07","unclassified","1, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_BIM-BLD_018","Blesme Haussignemont-Bar le Duc","<","Vitry-le-François - Aig Est-V Bis","Blesme-Haussignemont - Aiguille L1/L10",2023,2023,15,15,"2023-04-14","23:35:00","2023-04-16","11:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V2, 1V/2, 35:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_BIM-BLD_020","Blesme Haussignemont-Bar le Duc","<","Vitry-le-François - Aig Est-V Bis","Blesme-Haussignemont - Aiguille L1/L10",2023,2023,15,15,"2023-04-14","23:35:00","2023-04-16","11:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V2, 1V/2, 35:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_BLD_004","Bar le Duc",">","Bar-le-Duc - Bât Voyageurs","Nançois-Tronville - Aig Km 263,4",2023,2023,7,7,"2023-02-18","16:00:00","2023-02-19","16:01:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 1BIS,V1, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000001100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_BLD-LER_4","Bar le Duc-Lerouville",">","Bar-le-Duc - Bât Voyageurs","Nançois-Tronville - Aig Km 263,4",2023,2023,7,7,"2023-02-18","16:00:00","2023-02-19","16:01:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1, 2V/4, 24:01, Continu, SA,DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000001100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_EPR-RE_1","Epernay-Reims","< >","Germaine - Sortie Paire","Germaine - Sortie Impaire",2023,2023,23,24,"2023-06-05","09:25:00","2023-06-14","15:59:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, UNIQUE, 1V/1, 54:34, Continu, LU,MA,ME","2022-01-07","unclassified","1, 2, 3","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100001110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_EPR-RE_15","Epernay-Reims","< >","Germaine - Sortie Paire","Germaine - Sortie Impaire",2023,2023,22,22,"2023-05-30","09:25:00","2023-05-31","15:59:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, UNIQUE, 1V/1, 30:34, Continu, MA,ME","2022-01-07","unclassified","2, 3","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_LEW-FFT_5","LilleEurope-Calais","< >","Lille-Europe - Poste 41","Lambersart - Rac de Lille",2023,2023,28,28,"2023-07-14","23:30:00","2023-07-15","05:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 43,44,45,46, 05:30, Passe-minuit, VE/SA","2022-01-07","unclassified","5, 6","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_CHM-CY_003","Chaumont-Culmont","< >","Grandpuits - Poste 4","Vesoul - Poste C",2023,2023,16,16,"2023-04-21","23:30:00","2023-04-23","05:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 30:00, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_CHM-CY_004","Chaumont-Culmont","< >","Grandpuits - Poste 4","Vesoul - Poste C",2023,2023,17,18,"2023-04-28","21:40:00","2023-05-01","17:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 67:20, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_CHM-CY_005","Chaumont-Culmont","< >","Grandpuits - Poste 4","Vesoul - Poste C",2023,2023,20,20,"2023-05-18","11:40:00","2023-05-21","07:28:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 67:48, Continu, JE,VE,SA,DI","2022-01-07","unclassified","4, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000011110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_SDZ_001","StDizier","< >","Villiers-en-Lieu","St-Dizier - ITE Tréfilunion",2023,2023,15,16,"2023-04-14","22:00:00","2023-04-23","20:55:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 1B-2B,1T-2T,V1,V2, 46:55, Continu, VE,SA,DI","2022-01-07","unclassified","5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000011100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_SDZ_009","StDizier","< >","Villiers-en-Lieu","St-Dizier - ITE Tréfilunion",2023,2023,17,18,"2023-04-28","22:00:00","2023-05-01","20:55:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 1B-2B,1T-2T,V1,V2, 70:55, Continu, LU,VE,SA,DI","2022-01-07","unclassified","1, 5, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001111000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_RDG-SNE20","Reding-Saverne","<","Arzviller - IPCS","Lutzelbourg - IPCS",2022,2022,50,50,"2022-12-11","00:01:00","2022-12-12","05:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V2, 1V/2, 29:29, Continu, LU,DI","2022-01-07","unclassified","1, 7","publication","Y","1100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_VHM-HN_7","Vendenheim-Hausbergen","< >","Hausbergen-Triage - Aiguille 496,9","Hausbergen-Triage - Relais Pairs",2023,2023,9,9,"2023-03-04","13:00:00","2023-03-05","09:00:00",null,"periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, 1M,2M, 20:00, Passe-minuit, SA/DI","2022-01-07","unclassified","6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000010000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3C_PMO_002","Pagny sur Moselle","< >","Raccordement Pagny-Vandières - RAC côté Paris","Pagny-sur-Moselle - Bât Voyageurs",2023,2023,32,33,"2023-08-12","12:30:00","2023-08-15","12:30:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Cap, R2,V1,V2, 72:00, Continu, LU,MA,SA,DI","2022-01-07","unclassified","1, 2, 6, 7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111100000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_THL-AP_008","Thionville-Apach","< >","Thionville - Poste 3","Apach (Moselle) - Frontière Fr-Al",2023,2023,47,48,"2023-11-25","04:00:00","2023-11-27","05:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 49:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000"]
[null,87,"3D_THL-ZOU17","Thionville-Zoufftgen","< >","Thionville - Poste 2","Zoufftgen (IE) - Frontière Fr-Lu",2023,2023,47,48,"2023-11-25","04:00:00","2023-11-27","05:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V2, 2V/2, 49:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000"]
[null,87,"3D_HGD-UCK_8","Hagondange-Uckange","< >","Hagondange - Bât Voyageurs","Uckange - Ano Km 181,3",2023,2023,47,48,"2023-11-25","04:00:00","2023-11-27","05:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V1BIS,V2,V2BIS, 4V/4, 49:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000"]
[null,87,"3D_UCK-THL14","Uckange-Thionville","< >","Uckange - Poste 2","Ébange - Jonction Nord",2023,2023,47,48,"2023-11-25","04:00:00","2023-11-27","05:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V1,V1BIS,V2,V2BIS, 4V/4, 49:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000111000000000000000000000000000000000000000000000000"]
[null,87,"3D_CY-NCH_007","Culmont-NeufChateau","< >","Bourmont","Neufchâteau - CV 254",2023,2023,16,17,"2023-04-22","06:00:00","2023-04-24","06:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, 1BIS,2BIS,V2, 3V/4, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]
[null,87,"3D_NCH-TL_005","NeufChateau-Toul","<","Neufchâteau - Bât Voyageurs","Soulosse",2023,2023,16,17,"2023-04-22","06:00:00","2023-04-24","06:00:00",null,"continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Def, V2, 1V/2, 48:00, Continu, LU,SA,DI","2022-01-07","unclassified","1, 6 ,7","publication","Y","0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001110000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000"]

{"sheet":"SBB","index":6,"n_rows":19,"n_cols":23,"rows_kept":19,"cut":false,"hidden":false,"merged":[[0,18,0,21],[0,3,0,4],[0,5,0,6],[0,7,0,8],[0,9,0,10],[0,11,0,12],[0,16,0,17]]}
["IM","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,"Traffic measures",null,null,null,"Description"]
[null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Cancellation","Re-routing","Train replacement","Delays"]
["SBB Infra","Basel GB - Basel RB EMU","< >","BSGB","BSRB",2022,2022,1,8,"2022-01-08",null,"2022-02-28",null,"Weekend","continuous","track works ","x",null,"x","x",null,"x","Saturday 14:00 - Monday 02:00 (Sperrmuster 1)"]
["SBB Infra","Basel GB - Basel RB EMU","< >","BSGB","BSRB",2022,2022,20,26,"2022-05-22",null,"2022-07-04",null,"Weekend","continuous","track works ","x",null,"x","x",null,"x","Sunday 02:00 - Monday 02:00 (Sperrmuster 1)"]
["SBB Infra","Basel GB - Basel RB EMU","< >","BSGB","BSRB",2022,2022,22,22,"2022-06-05",null,"2022-06-07",null,"Weekend","continuous","track works ","x",null,"x",null,null,"x","Sunday 02:00 - Tuesday 02:00 (Sperrmuster 1)"]
["SBB Infra","Basel RB - Basel GB EMU",">","BSRB","BSGB",2022,2022,22,null,"2022-07-03",null,"2022-07-07",null,"Weekend","continuous","track works ",null,"x","x",null,null,"x","Sperrmuster 7"]
["SBB Infra","Basel RB - Basel GB EMU",">","BSRB","BSGB",2022,2022,29,null,"2022-07-22",null,"2022-07-25",null,"Weekend","continuous","track works ",null,"x","x",null,null,"x","Sperrmuster 7"]
["SBB Infra","Basel GB - Basel RB EMU","< >","BSGB","BSRB",2022,2022,32,null,"2022-08-14",null,"2022-08-15",null,"Weekend","continuous","track works ","x",null,"x","x",null,"x","Sunday 02:00 - Monday 02:00 (Sperrmuster 1)"]
["SBB Infra","Basel GB - Basel RB EMU","< >","BSGB","BSRB",2022,2022,37,null,"2022-09-18",null,"2022-09-19",null,"Weekend","continuous","track works ","x",null,"x","x",null,"x","Sunday 02:00 - Monday 02:00 (Sperrmuster 1)"]
["SBB Infra","Basel GB - Basel RB EMU","< >","BSGB","BSRB",2022,2022,39,null,"2022-10-02",null,"2022-10-03",null,"Weekend","continuous","track works ","x",null,"x","x",null,"x","Sunday 02:00 - Monday 02:00 (Sperrmuster 1)"]
["SBB Infra","Basel GB - Basel RB EMU","< >","BSGB","BSRB",2022,2022,49,50,"2022-12-11",null,"2022-12-19",null,"Weekend","continuous","track works ","x",null,"x","x",null,"x","Sunday 02:00 - Monday 02:00 (Sperrmuster 1)"]
["SBB Infra","Bellegarde-La Plaine-Genève La Praille","< >","LPFR","GEPR",2022,2023,50,49,"2022-12-12",null,"2023-12-09",null,"12 months","continuous","Platform and track works ",null,"x","x",null,"x","x","Total closures may be possible"]
["SBB Infra","Bellegarde-La Plaine-Genève La Praille","<>","LPFR","GEPR/GE",2023,2024,50,49,"2023-12-10",null,"2024-12-14",null,"12 months","continuous","Platform and track works ",null,"x","x",null,"x","x","Total closures may be possible"]
["SBB Infra",null,"<>","LPFR","GEPR/GE",2024,2024,33,34,"2024-08-12",null,"2024-08-25",null,"2 weeks","continuous","track works ","x",null,"x",null,null,null,"Total closure "]
["SBB Infra","Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,9,9,"2023-03-03","22:45:00","2023-03-06","05:00:00","Weekend","continuous","track works ","x",null,null,"x",null,null,"Total closure "]
["SBB Infra","Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,10,10,"2023-03-10","22:45:00","2023-03-12","22:00:00","Weekend","continuous","track works ","x",null,null,"x",null,null,"Total closure "]
["SBB Infra","Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,39,39,"2023-09-29","22:45:00","2023-10-02","05:00:00","Weekend","continuous","track works ","x",null,null,"x",null,null,"Total closure "]
["SBB Infra","Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,40,40,"2023-10-06","22:45:00","2023-10-09","05:00:00","Weekend","continuous","track works ","x",null,null,"x",null,null,"Total closure "]
["SBB Infra","Basel RB","<","BSRB",null,2023,2023,31,33,"2023-08-05","09:00:00","2023-08-21","06:00:00","Weekend Sa-Mo","continuous","track works ",null,"x","x","x","x","x","Trains S-N re-routing, no buffering possibilities BSRB"]

{"sheet":"ACF CFL","index":7,"n_rows":93,"n_cols":29,"rows_kept":93,"cut":false,"hidden":false,"merged":[]}
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["ACF/CFL","ACF78","Rodange-Bettembourg","< >","Belval-Lycée","Esch/Alzette",2022,2022,1,26,"2022-01-03","00:10:00","2022-06-30","04:45:00","172 days","Night","catenary renewal","x",null,null,null,null,"x","x",null,null,null,"from Monday to Friday","no"]
["ACF/CFL","ACF94","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,4,5,"2022-01-29","01:00:00","2022-01-31","04:00:00","2 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction","no"]
["ACF/CFL","ACF79","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,5,8,"2022-01-31","01:20:00","2022-02-25","04:10:00","26 days","Night","station renewal","x",null,null,null,null,"x",null,null,null,null,"from Monday to Friday","no"]
["ACF/CFL","ACF95","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,5,6,"2022-02-05","01:00:00","2022-02-07","04:00:00","2 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction","no"]
["ACF/CFL","ACF96","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,6,7,"2022-02-12","01:00:00","2022-02-14","04:00:00","2 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction","no"]
["ACF/CFL","ACF48","Rodange-Bettembourg","< >","Noertzange","Esch/Alzette",2022,2022,7,8,"2022-02-19","01:00:00","2022-02-21","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF97","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,7,8,"2022-02-19","01:00:00","2022-02-21","04:00:00","2 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction","no"]
["ACF/CFL","ACF49","Rodange-Bettembourg","< >","Noertzange","Esch/Alzette",2022,2022,9,10,"2022-03-05","01:00:00","2022-03-07","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF98","Rodange - Bettembourg","< >","Pétange","Luxembourg",2022,2022,10,11,"2022-03-12","01:00:00","2022-03-14","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF99","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2022,2022,13,15,"2022-04-02","01:00:00","2022-04-11","04:00:00","9 days","Night/Day","catenary & track maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF126","Rodange - Bettembourg","< >","Rodange","Pétange",2022,2022,13,14,"2022-04-02","01:00:00","2022-04-04","09:00:00","2 days","Night/Day","train station renewal"]
["ACF/CFL","ACF127","Rodange - Bettembourg","< >","Rodange","Pétange",2022,2022,14,14,"2022-04-04","17:00:00","2022-04-08","09:00:00","4 days","Night","train station renewal"]
["ACF/CFL","ACF128","Rodange - Bettembourg","< >","Rodange","Pétange",2022,2022,14,15,"2022-04-08","17:00:00","2022-04-10","04:00:00","2 days","Night/Day","train station renewal"]
["ACF/CFL","ACF100","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2022,2022,15,16,"2022-04-11","01:00:00","2022-04-18","04:00:00","7 days","Night/Day","catenary & track maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF82","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,16,17,"2022-04-23","01:00:00","2022-04-25","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF83","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,17,18,"2022-04-30","01:00:00","2022-05-02","04:00:00","3 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF50","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2022,2022,18,19,"2022-05-07","00:30:00","2022-05-10","04:00:00","3 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF84","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2022,2022,19,20,"2022-05-14","00:30:00","2022-05-16","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF51","Rodange-Bettembourg","< >","Belvaux-Soleuvre","Esch/Alzette",2022,2022,20,22,"2022-05-21","00:30:00","2022-05-30","04:00:00","9 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF52","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2022,2022,22,23,"2022-06-04","00:30:00","2022-06-07","04:00:00","3 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF53","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,23,24,"2022-06-11","01:20:00","2022-06-13","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF54","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,24,25,"2022-06-18","01:20:00","2022-06-20","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF55","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,25,26,"2022-06-25","01:20:00","2022-06-27","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF56","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,26,27,"2022-07-02","01:00:00","2022-07-04","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF85","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2022,2022,27,28,"2022-07-09","01:00:00","2022-07-11","04:00:00","3 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF101","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2022,2022,29,31,"2022-07-16","01:20:00","2022-08-01","04:00:00","16 days","Night/Day","new line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF58","Rodange-Bettembourg","< >","Rodange","Lamadelaine",2022,2022,34,37,"2022-08-20","01:00:00","2022-09-05","04:00:00","16 days","Night/Day","train station renewal","x",null,null,null,null,"x",null,null,null,null,"continious restriction","no"]
["ACF/CFL","ACF60","Luxembourg-Bettembourg",">","Luxembourg","Bettembourg",2022,2022,37,38,"2022-09-16","23:30:00","2022-09-19","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF87","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,37,38,"2022-09-17","01:00:00","2022-09-19","04:00:00","2 days","Night/Day","renewal station","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF61","Rodange-Bettembourg","< >","Belval-Usines","Pétange",2022,2022,38,39,"2022-09-24","00:30:00","2022-09-26","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF62","Rodange-Bettembourg","< >","Belval-Usines","Pétange",2022,2022,39,40,"2022-10-01","00:30:00","2022-10-03","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF66","Rodange-Bettembourg","< >","Belval-Usines","Pétange",2022,2022,42,43,"2022-10-22","00:30:00","2022-10-24","04:00:00","2 days","Night/Day","maintenance of a bridge","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF69","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,46,47,"2022-11-19","01:00:00","2022-11-21","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF72","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,47,48,"2022-11-21","07:00:00","2022-12-04","22:00:00","14 days","Night/Day","Construction new hangar","x",null,null,null,null,"x",null,null,null,null,"continious restriction","no"]
["ACF/CFL","ACF73","Rodange-Bettembourg","< >","Rodange","Pétange",2022,2022,49,50,"2022-12-10","04:00:00","2022-12-12","01:00:00","2 days","Night/Day","Construction new hangar","x",null,null,null,null,"x",null,null,null,null,"continious restriction","no"]
["ACF/CFL","ACF74","Luxembourg-Bettembourg","< >","Luxembourg","Bettembourg",2022,2022,50,51,"2022-12-17","01:30:00","2022-12-19","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF102","Luxembourg-Bettembourg",">","Luxembourg","Berchem",2023,2023,1,2,"2023-01-08","01:00:00","2023-01-09","04:00:00","1 day","Night/Day","renewal of the line","x","x",null,null,null,null,"x",null,null,"x","continious restriction","no"]
["ACF/CFL","ACF103","Luxembourg-Bettembourg",">","Luxembourg","Berchem",2023,2023,2,3,"2023-01-15","01:00:00","2023-01-16","04:00:00","1 day","Night/Day","renewal of the line","x","x",null,null,null,null,"x",null,null,"x","continious restriction","no"]
["ACF/CFL","ACF104","Luxembourg-Bettembourg","< >","Luxembourg","Fentange",2023,2023,7,8,"2023-02-18","01:00:00","2023-02-20","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF105","Luxembourg-Bettembourg","< >","Luxembourg","Fentange",2023,2023,8,9,"2023-02-25","01:00:00","2023-02-27","04:00:00","2 days","Night/Day","renewal of the line","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF107","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2023,13,15,"2023-04-01","01:00:00","2023-04-17","04:00:00","16 days","Night/Day","Track maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF109","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,16,17,"2023-04-22","01:00:00","2023-04-24","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF110","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2023,2023,17,18,"2023-04-29","01:00:00","2023-05-02","04:00:00","3 days","Night/Day","plattform renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF113","Rodange - Bettembourg","< >","Bettembourg","Esch/Alzette",2023,2023,18,19,"2023-05-06","01:00:00","2023-05-08","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF129","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2023,2023,19,20,"2023-05-13","01:00:00","2023-05-15","04:00:00","2 days","Night/Day","plattform renewal"]
["ACF/CFL","ACF111","Luxembourg-Bettembourg","< >","Berchem","Bettembourg",2023,2023,21,22,"2023-05-27","01:00:00","2023-05-30","04:00:00","3 days","Night/Day","plattform renewal","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF112","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2023,2023,21,23,"2023-05-27","01:00:00","2023-06-05","04:00:00","9 days","Night/Day","Track and plattform maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF114","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2023,24,25,"2023-06-17","01:00:00","2023-06-19","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF117","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,24,25,"2023-06-17","01:00:00","2023-06-19","04:00:00","2 days","Night/Day","renewal aqueducs","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF115","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2022,25,26,"2023-06-24","01:00:00","2023-06-26","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF118","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,25,26,"2023-06-24","01:00:00","2023-06-26","04:00:00","2 days","Night/Day","renewal aqueducs","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF116","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2023,2023,26,27,"2023-07-01","01:00:00","2023-07-03","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF119","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,26,27,"2023-07-01","01:00:00","2023-07-03","04:00:00","2 days","Night/Day","renewal aqueducs","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF130","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,26,26,"2023-07-01","06:00:00","2023-07-02","21:00:00","2 days","Night/Day","plattform renewal"]
["ACF/CFL","ACF120","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,27,28,"2023-07-08","01:00:00","2023-07-10","04:00:00","2 days","Night/Day","renewal aqueducs","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF131","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,27,28,"2023-07-08","06:00:00","2023-07-10","04:00:00","2 days","Night/Day","plattform renewal"]
["ACF/CFL","ACF121","Luxembourg-Bettembourg",">","Luxembourg","Berchem",2023,2023,29,35,"2023-07-14","22:00:00","2023-08-28","04:00:00","45 days","Night/Day","renewal of the line",null,"x","x",null,null,"x","x",null,null,"x","continious restriction","no"]
["ACF/CFL","ACF132","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,28,29,"2023-07-15","06:00:00","2023-07-17","04:00:00","2 days","Night/Day","plattform renewal"]
["ACF/CFL","ACF133","Rodange - Bettembourg","< >","Rodange","Pétange",2023,2023,29,30,"2023-07-22","06:00:00","2023-07-24","04:00:00","2 days","Night/Day","plattform renewal"]
["ACF/CFL","ACF134","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,37,38,"2023-09-16","01:00:00","2023-09-18","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF135","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,38,39,"2023-09-23","01:00:00","2023-09-25","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF136","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,39,40,"2023-09-30","01:00:00","2023-10-02","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF137","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,40,41,"2023-10-07","01:00:00","2023-10-09","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF138","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,41,42,"2023-10-14","01:00:00","2023-10-16","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF139","Rodange - Bettembourg","< >","Pétange","Belval-Usines",2023,2023,42,43,"2023-10-21","01:00:00","2023-10-23","04:00:00","2 days","Night/Day","renewal aqueducs"]
["ACF/CFL","ACF122","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2023,2023,43,45,"2023-10-28","01:00:00","2023-11-06","04:00:00","9 days","Night/Day","Track and plattform maintenance","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF140","Rodange - Bettembourg","< >","Luxembourg","Bettembourg",2023,2023,43,51,"2023-10-28","06:00:00","2023-12-18","14:00:00","51 days","Mo-Fr"]
["ACF/CFL","ACF141","Rodange - Bettembourg","< >","Luxembourg","Bettembourg",2023,2023,45,46,"2023-11-11","01:00:00","2023-11-13","04:00:00","2 days","Night/Day","new line"]
["ACF/CFL","ACF147","Rodange - Bettembourg","< >","Luxembourg","Dippach/Reckange",2023,2023,45,46,"2023-11-11","01:00:00","2023-11-13","04:00:00","2 days","Night/Day","elimination railway crossing"]
["ACF/CFL","ACF142","Rodange - Bettembourg","< >","Luxembourg","Bettembourg",2023,2023,46,47,"2023-11-18","01:00:00","2023-11-20","04:00:00","2 days","Night/Day","new line"]
["ACF/CFL","ACF125","Rodange - Bettembourg","< >","Pétange","Luxembourg",2023,2023,47,48,"2023-11-25","01:00:00","2023-11-27","04:00:00","2 days","Night/Day","general maintenance IM","x",null,null,null,null,"x","x",null,null,null,"continious restriction","no"]
["ACF/CFL","ACF143","Rodange - Bettembourg","< >","Luxembourg","Bettembourg",2023,2023,47,48,"2023-11-25","01:00:00","2023-11-27","04:00:00","2 days","Night/Day","new line"]
["ACF/CFL","ACF148","Rodange - Bettembourg","< >","Luxembourg","Pétange",2023,2023,47,48,"2023-11-25","01:00:00","2023-11-27","04:00:00","2 days","Night/Day","catenary & track maintenance"]
["ACF/CFL","ACF144","Rodange - Bettembourg","< >","Luxembourg","Bettembourg",2023,2023,48,49,"2023-12-02","01:00:00","2023-12-04","04:00:00","2 days","Night/Day","new line"]
["ACF/CFL","ACF145","Rodange - Bettembourg","< >","Luxembourg","Bettembourg",2023,2023,49,50,"2023-12-09","01:00:00","2023-12-11","04:00:00","2 days","Night/Day","new line"]
["ACF/CFL","ACF146","Rodange - Bettembourg","< >","Luxembourg","Bettembourg",2023,2023,50,51,"2023-12-16","01:00:00","2023-12-18","04:00:00","2 days","Night/Day","new line"]
["ACF/CFL","ACF149","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2024,2024,13,16,"2024-03-30","01:00:00","2024-04-15","04:00:00","2 weeks","Night/Day","Infrastructure maintenance"]
["ACF/CFL","ACF150","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2024,2024,16,17,"2024-04-20","01:00:00","2024-04-22","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF151","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2024,2024,17,18,"2024-04-27","01:00:00","2024-04-29","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF152","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2024,2024,18,19,"2024-05-04","01:00:00","2024-05-06","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF153","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2024,2024,19,20,"2024-05-11","01:00:00","2024-05-13","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF154","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2024,2024,20,21,"2024-05-18","01:00:00","2024-05-20","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF155","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2024,2024,21,23,"2024-05-25","01:00:00","2024-06-03","04:00:00","1 week","Night/Day","Infrastructure maintenance"]
["ACF/CFL","ACF156","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2024,2024,26,27,"2024-06-29","01:00:00","2024-07-01","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF157","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2024,2024,27,28,"2024-07-06","01:00:00","2024-07-08","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF158","Rodange-Bettembourg","< >","Luxembourg","Berchem",2024,2024,29,33,"2024-07-16","01:00:00","2024-08-12","04:00:00","4 weeks","Night/Day","new line"]
["ACF/CFL","ACF159","Rodange-Bettembourg","< >","Berchem","Bettembourg",2024,2024,33,38,"2024-08-12","04:00:00","2024-09-16","04:00:00","5 weeks","Night/Day","new line"]
["ACF/CFL","ACF160","Rodange-Athus","< >","Rodange","Athus",2024,2024,34,38,"2024-08-24","01:00:00","2024-09-16","04:00:00","4 weeks","Night/Day","Maintenance"]
["ACF/CFL","ACF161","Rodange-Bettembourg","< >","Berchem","Bettembourg",2024,2024,38,39,"2024-09-21","01:00:00","2024-09-23","04:00:00","2 days","Night/Day","Maintenance"]
["ACF/CFL","ACF162","Rodange-Bettembourg","< >","Luxembourg","Berchem",2024,2024,40,41,"2024-10-06","01:00:00","2024-10-07","04:00:00","1 day","Night/Day","Maintenance"]
["ACF/CFL","ACF163","Rodange-Bettembourg","< >","Luxembourg","Berchem",2024,2024,41,42,"2024-10-13","01:00:00","2024-10-14","04:00:00","1 day","Night/Day","Maintenance"]
["ACF/CFL","ACF164","Rodange-Bettembourg","< >","Luxembourg","Berchem",2024,2024,42,43,"2024-10-20","01:00:00","2024-10-21","04:00:00","1 day","Night/Day","Maintenance"]