{"text_format":"1","workbook":"xlsx","n_sheets":8,"sheets":["Home","Main Impact Map","ACF CFL-I","Infrabel","ProRail","SBB-I TVS","SNCF-R","Data"],"not_rendered":{"charts":0,"images":11,"macros":1,"external_links":7,"defined_names":58,"comments":4,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Home","index":0,"n_rows":5,"n_cols":15,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"! click icon to follow !"]

{"sheet":"Main Impact Map","index":1,"n_rows":15,"n_cols":14,"rows_kept":15,"cut":false,"hidden":false,"merged":[[45,5,46,7]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Main TCR for TT 2024 to TT 2026"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"24/01/2024 version 1"]
[null,null,null,null,null,null,null,null,null,null,null,null,"click on the comments for a direct link to TCR details"]

{"sheet":"ACF CFL-I","index":2,"n_rows":112,"n_cols":45,"rows_kept":112,"cut":false,"hidden":false,"merged":[[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]]}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)","Last update","Classification","Weekdays","Interval","Affected estimated travel volume","Affected border","Deviation location","Deviation border","Status","Additional information","Automatic process","BitmapDays","Variant value"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","No catenary","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"ACF / CFL-I","ACF402","Rodange-Bettembourg","< >","Lux.-Sud","Hollerich",2024,2024,1,37,"2024-01-02","00:00:00","2024-09-15","23:59:00","8 1/2 month","Night/Day","New platform / New line",null,"x",null,null,null,null,"x",null,"x"]
[null,"ACF / CFL-I","ACF456","Rodange-Bettembourg","< >","Fentange","Hollerich",2024,2024,1,1,"2024-01-05","22:00:00","2024-01-08","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF462","Rodange-Bettembourg","< >","Fentange","Hollerich",2024,2024,2,2,"2024-01-12","22:00:00","2024-01-15","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF569","Rodange-Bettembourg","< >","Fentange","Hollerich",2024,2024,3,3,"2024-01-19","22:00:00","2024-01-22","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF400","Rodange-Bettembourg","< >","Bettembourg","Bettembourg",2024,2024,3,3,"2024-01-20","01:00:00","2024-01-22","04:00:00","2 days","Night/Day","Steetbridge maintenance",null,"x",null,null,null,null,"x",null,"x"]
[null,"ACF / CFL-I","ACF401","Rodange-Bettembourg","< >","Bettembourg","Bettembourg",2024,2024,4,4,"2024-01-27","01:00:00","2024-01-29","04:00:00","2 days","Night/Day","Steetbridge maintenance",null,"x",null,null,null,null,"x",null,"x"]
[null,"ACF / CFL-I","ACF457","Rodange-Bettembourg","< >","Fentange","Hollerich",2024,2024,6,6,"2024-02-09","22:00:00","2024-02-12","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF226","Rodange-Bettembourg","< >","Bettembourg","Bettembourg",2024,2024,6,6,"2024-02-10","01:00:00","2024-02-12","04:00:00","2 days","Night/Day","Steetbridge maintenance",null,"x",null,null,null,null,"x",null,"x"]
[null,"ACF / CFL-I","ACF458","Rodange-Bettembourg","< >","Fentange","Hollerich",2024,2024,7,7,"2024-02-16","22:00:00","2024-02-19","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF439","Rodange-Bettembourg","< >","Bettembourg","Berchem",2024,2024,7,7,"2024-02-17","01:00:00","2024-02-19","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF459","Rodange-Bettembourg","< >","Fentange","Hollerich",2024,2024,8,8,"2024-02-23","22:00:00","2024-02-26","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF440","Rodange-Bettembourg","< >","Bettembourg","Berchem",2024,2024,9,9,"2024-03-02","01:00:00","2024-03-04","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF453","Thionville-Bettembourg","< >","Acces Terminal Bettembourg",null,2024,2024,14,15,"2024-03-29","00:00:00","2024-04-01","23:59:00","3 days","Night/Day","New platform / New line","x","x"]
[null,"ACF / CFL-I","ACF170","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2024,2024,13,15,"2024-03-30","01:00:00","2024-04-15","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF205","Rodange-Bettembourg","< >","Bettembourg","Berchem",2024,2024,16,16,"2024-04-20","01:00:00","2024-04-22","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF206","Rodange-Bettembourg","< >","Bettembourg","Berchem",2024,2024,17,17,"2024-04-27","01:00:00","2024-04-29","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF321","Rodange-Bettembourg","< >","Bettembourg","Bettembourg",2024,2024,18,18,"2024-05-04","01:00:00","2024-05-06","04:00:00","2 days","Night/Day","Steetbridge maintenance",null,"x",null,null,null,null,"x",null,"x"]
[null,"ACF / CFL-I","ACF441","Rodange-Athus/Aubange","< >","Rodange","Athus/Aubange",2024,2024,19,19,"2024-05-11","01:00:00","2024-05-13","04:00:00","2 days","Night/Day","Track renewal","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF522","Rodange-Bettembourg","< >","Bettembourg","Berchem",2024,2024,23,23,"2024-06-08","01:00:00","2024-06-10","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF454","Rodange-Bettembourg","< >","Dippach/Reckange","Leudelange",2024,2024,24,24,"2024-06-15","01:00:00","2024-06-17","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF460","Rodange-Bettembourg","< >","Fentange","Hollerich",2024,2024,26,26,"2024-06-28","22:00:00","2024-07-01","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF461","Rodange-Bettembourg","< >","Fentange","Hollerich",2024,2024,27,27,"2024-07-05","22:00:00","2024-07-08","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF172","Rodange-Bettembourg","< >","Bettembourg","Berchem",2024,2024,28,32,"2024-07-13","01:00:00","2024-08-12","04:00:00","4 weeks","Night/Day","New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF435","Thionville-Bettembourg","< >","Thionville","Bettembourg",2024,2024,30,31,"2024-07-16","08:00:00","2024-07-27","17:00:00","2 weeks","Daily","Infrastructure renewal","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF436","Thionville-Bettembourg","< >","Thionville","Bettembourg",2024,2024,30,31,"2024-07-16","08:00:00","2024-07-27","17:00:00","2 weeks","Night/Day","Infrastructure renewal",null,"x",null,null,null,null,"x",null,"x"]
[null,"ACF / CFL-I","ACF173","Rodange-Bettembourg","< >","Bettembourg","Berchem",2024,2024,33,37,"2024-08-12","04:00:00","2024-09-16","04:00:00","4 weeks","Night/Day","Station renewal",null,"x",null,null,null,null,"x",null,"x"]
[null,"ACF / CFL-I","ACF202","Rodange-Bettembourg","< >","Berchem","Luxembourg",2024,2024,33,37,"2024-08-12","04:00:00","2024-09-16","04:00:00","4 weeks","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF176","Rodange-Athus","< >","Rodange","Athus",2024,2024,34,37,"2024-08-24","01:00:00","2024-09-16","04:00:00","3 weeks","Night/Day","Track renewal","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF405","Rodange-Bettembourg","< >","Fentange","Hollerich",2024,2024,37,52,"2024-09-15","00:00:00","2024-12-31","23:59:00","3 1/2 month","Night/Day","New station",null,"x",null,null,null,null,"x",null,"x"]
[null,"ACF / CFL-I","ACF463","Rodange-Bettembourg","< >","Fentange","Hollerich",2024,2024,37,38,"2024-09-16","04:00:00","2024-09-23","04:00:00","1 week","Night/Day","New station","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF517","Rodange-Bettembourg","< >","Dippach/Reckange","Leudelange",2024,2024,38,40,"2024-09-17","00:45:00","2024-10-06","04:15:00","3 weeks","Night","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF221","Rodange-Bettembourg","< >","Berchem","Bettembourg",2024,2024,38,38,"2024-09-21","01:00:00","2024-09-23","04:00:00","2 days","Night/Day","Station renewal","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF271","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2024,2024,39,39,"2024-09-28","01:00:00","2024-09-30","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF272","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2024,2024,40,40,"2024-10-05","01:00:00","2024-10-07","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF444","Rodange-Bettembourg","< >","Pétange","Dippach/Reckange",2024,2024,40,40,"2024-10-05","01:00:00","2024-10-07","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF467","Rodange-Bettembourg","< >","Esch/Alzette","Belval-Usines",2024,2024,42,42,"2024-10-19","06:00:00","2024-10-20","22:00:00","2 days","Night/Day","Infrastructure maintenance",null,"x",null,null,null,null,"x",null,"x"]
[null,"ACF / CFL-I","ACF171","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2024,2024,43,44,"2024-10-26","01:00:00","2024-11-04","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF421","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2024,2024,43,44,"2024-10-26","01:00:00","2024-10-31","23:59:00","6 days","Night/Day","Track renewal","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF445","Rodange-Bettembourg","< >","Pétange","Dippach/Reckange",2024,2024,44,44,"2024-11-01","01:00:00","2024-11-04","04:00:00","3 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF273","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2024,2024,45,45,"2024-11-09","01:00:00","2024-11-11","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF442","Rodange-Athus/Aubange","< >","Rodange","Athus/Aubange",2024,2024,46,46,"2024-11-16","01:00:00","2024-11-18","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF212","Rodange-Bettembourg","< >","Berchem","Bettembourg",2024,2024,50,50,"2024-12-14","01:00:00","2024-12-16","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF212","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,50,50,"2024-12-14","01:00:00","2024-12-16","04:00:00","2 days","Night/Day","New platform / New line / Infra. Main.","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF213","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,2,2,"2025-01-11","01:00:00","2025-01-13","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF490","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,4,4,"2025-01-25","01:00:00","2025-01-27","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF529","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,6,6,"2025-02-08","01:00:00","2025-02-10","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF345","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,7,8,"2025-02-15","01:00:00","2025-02-24","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF530","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,7,7,"2025-02-15","01:00:00","2025-02-17","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF473","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,8,8,"2025-02-17","01:00:00","2025-02-21","23:00:00","5 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF485","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,9,9,"2025-03-01","01:00:00","2025-03-03","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF329","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,10,10,"2025-03-08","01:00:00","2025-03-10","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF474","Rodange-Bettembourg","< >","Pétange","Hollerich",2025,2025,11,11,"2025-03-15","01:00:00","2025-03-17","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF531","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,11,11,"2025-03-15","01:00:00","2025-03-17","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF532","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,12,12,"2025-03-22","01:00:00","2024-03-24","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF533","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,13,13,"2025-03-29","01:00:00","2025-03-31","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF534","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,14,14,"2025-04-05","01:00:00","2025-04-07","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF236","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2025,2025,14,16,"2025-04-05","00:00:00","2025-04-22","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF275","Rodange-Bettembourg","< >","Berchem","Bettembourg",2025,2025,14,16,"2025-04-05","00:00:00","2025-04-22","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF535","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,15,15,"2025-04-12","01:00:00","2025-04-14","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF549","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,17,17,"2025-04-26","01:00:00","2025-04-28","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF477","Athus/Aubange-Bettembourg","< >","Athus/Aubange","Pétange",2025,2025,18,18,"2025-05-03","01:00:00","2025-05-05","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF486","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,19,19,"2025-05-10","01:00:00","2025-05-12","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF550","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,20,20,"2025-05-17","01:00:00","2025-05-19","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF279","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2025,2025,21,22,"2025-05-24","00:00:00","2025-06-02","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF487","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,21,22,"2025-05-24","00:00:00","2025-06-02","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF551","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,23,23,"2025-06-07","01:00:00","2025-06-09","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF478","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,24,24,"2025-06-14","01:00:00","2025-06-16","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF284","Rodange-Bettembourg","< >","Berchem","Bettembourg",2025,2025,26,26,"2025-06-28","01:00:00","2025-06-30","04:00:00","2 days","Night/Day","New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF285","Rodange-Bettembourg","< >","Berchem","Bettembourg",2025,2025,27,27,"2025-07-05","01:00:00","2025-07-07","04:00:00","2 days","Night/Day","New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF488","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,28,28,"2025-07-12","01:00:00","2025-07-14","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF234","Rodange-Bettembourg","< >","Berchem","Bettembourg",2025,2025,29,37,"2025-07-16","01:00:00","2025-09-15","04:00:00","2 months","Night/Day","New line","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF526","Rodange-Bettembourg","< >","Fentange","Hollerich",2025,2025,38,52,"2025-09-15","04:00:00","2025-12-31","23:59:00","3 1/2 month","Night/Day","New platform / New line",null,"x",null,null,null,null,"x",null,"x"]
[null,"ACF / CFL-I","ACF475","Rodange-Bettembourg","< >","Pétange","Hollerich",2025,2025,38,38,"2025-09-20","01:00:00","2025-09-22","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF512","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,38,38,"2025-09-20","01:00:00","2025-09-22","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF513","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,39,39,"2025-09-27","01:00:00","2025-09-29","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF471","Rodange-Bettembourg","< >","Fentange","Hollerich",2025,2025,40,40,"2025-10-04","01:00:00","2025-10-06","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF483","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,41,41,"2025-10-11","01:00:00","2025-10-13","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF489","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2025,2025,42,42,"2025-10-18","01:00:00","2025-10-20","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF484","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,43,43,"2025-10-25","01:00:00","2025-10-27","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF281","Rodange-Bettembourg","< >","Pétange","Luxembourg",2025,2025,44,45,"2025-11-01","01:00:00","2025-11-10","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF510","Rodange-Bettembourg","< >","Differdange","Belvaux-Soleuvre",2025,2025,46,46,"2025-11-15","01:00:00","2025-11-17","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF514","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,46,46,"2025-11-15","01:00:00","2025-11-17","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF232","Rodange-Bettembourg","< >","Dippach/Reckange","Hollerich",2025,2025,47,47,"2025-11-22","01:00:00","2025-11-24","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF472","Rodange-Bettembourg","< >","Fentange","Hollerich",2025,2025,50,50,"2025-12-13","01:00:00","2025-12-15","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF500","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2026,2026,3,3,"2026-01-17","01:00:00","2025-01-19","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF554","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,7,8,"2026-02-14","01:00:00","2026-02-23","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF491","Rodange-Bettembourg","< >","Fentange","Hollerich",2026,2026,9,9,"2026-02-28","01:00:00","2026-03-02","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF556","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,10,10,"2026-03-07","01:00:00","2026-03-09","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF557","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,11,11,"2026-03-14","01:00:00","2026-03-16","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF497","Rodange-Bettembourg","< >","Pétange","Luxembourg",2026,2026,12,12,"2026-03-21","01:00:00","2026-03-23","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF280","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2026,2026,13,15,"2026-03-28","00:00:00","2026-04-13","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF495","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2026,2026,13,15,"2026-03-28","00:00:00","2026-04-13","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF558","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,16,16,"2026-04-18","01:00:00","2026-04-20","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF498","Athus/Aubange-Bettembourg","< >","Athus/Aubange","Pétange",2026,2026,17,17,"2026-04-25","01:00:00","2026-04-27","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF559","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,18,18,"2026-05-01","01:00:00","2026-05-04","04:00:00","3 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF560","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,19,19,"2026-05-09","01:00:00","2026-05-11","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF502","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2026,2026,20,20,"2026-05-16","01:00:00","2026-05-18","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF496","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2026,2026,21,22,"2026-05-23","01:00:00","2026-06-01","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF555","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,21,22,"2026-05-23","01:00:00","2026-06-01","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF561","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,23,23,"2026-06-06","01:00:00","2026-06-08","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF492","Rodange-Bettembourg","< >","Fentange","Hollerich",2026,2026,24,24,"2026-06-13","01:00:00","2026-06-15","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF509","Rodange-Bettembourg","< >","Fentange","Hollerich",2026,2026,25,25,"2026-06-20","01:00:00","2026-06-22","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF562","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,26,26,"2026-06-27","01:00:00","2026-06-29","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF563","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,27,27,"2026-07-04","01:00:00","2026-07-06","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF564","Rodange-Bettembourg","< >","Differdange","Esch/Alzette",2026,2026,26,26,"2026-07-11","01:00:00","2026-07-13","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF397","Rodange-Bettembourg","< >","Berchem","Bettembourg",2026,2026,29,38,"2026-07-16","01:00:00","2026-09-15","04:00:00","2 months","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF511","Rodange-Bettembourg","< >","Differdange","Belvaux-Soleuvre",2026,2026,38,38,"2026-09-19","01:00:00","2026-09-21","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF499","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2026,2026,40,40,"2026-10-03","01:00:00","2026-10-05","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
[null,"ACF / CFL-I","ACF503","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2026,2026,47,47,"2026-11-21","01:00:00","2026-11-23","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]

{"sheet":"Infrabel","index":3,"n_rows":3900,"n_cols":43,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)","Last updated","Classification","Weekdays","Interval","Affected Estimated Travel Volume","Affected Border","Deviation Location","Deviation Border","Status","Additional Information","Automatic process"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"Infrabel","40219","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","ANTWERPEN-NOORD-INRIT C1",2023,2023,36,51,"2023-09-04",45280.25,"2023-12-22",45280.75,"110d, 12:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"LANGE TLO 3weken: Vernieuwing wissels bundelkop C1 + verbinding tussen C1-C2.\r\nbuiten diensstelling tussen Antwerpen-noord uitrit C1 en  Antwerpen-noord Blok 9 rooster J\r\nWerkgroep wordt opgestart; zie dossier 20210203_2023 - L27A Antwerpen-Noord-C2-N_v",null,null,40219,"2023-03-06","Major","1,2,3,4,5,6,7"]
[null,"Infrabel","48580","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2023,2023,49,50,"2023-12-09",45280.993055555555,"2023-12-11",45280.222222222219,"2d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN\r\n+\r\nLossing rails perrons SJW\r\n\r\nUPM 412573",null,null,48580,"2023-10-04","Minor","5,6"]
[null,"Infrabel","67113","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2023,2023,50,50,"2023-12-11",45280.958333333336,"2023-12-13",45280.177083333336,"2d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2023-331\r\nCriblage du ballast (C75) suite panne machine du mois de mars 23\r\nBourrage de révision\r\n\r\n\r\nUPM: 460670",null,null,67113,"2023-08-03","Minor","1,2,3,4,5"]
[null,"Infrabel","49693","Namur - Antwerpen",">","NAMUR","GEMBLOUX",2023,2023,50,50,"2023-12-11",45280.958333333336,"2023-12-16",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"poteaux",null,null,49693,"2023-08-17","Minor","1,2,3,4,5"]
[null,"Infrabel","53571","Namur - Antwerpen",">","OTTIGNIES","MONT-SAINT-GUIBERT",2023,2023,50,50,"2023-12-11",45280.958333333336,"2023-12-16",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER OTTIGNIES SAVU VOIE B L161\r\nUPM 469390",null,null,53571,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","37888","Namur - Antwerpen",">","NAMUR","FLAWINNE",2023,2023,50,50,"2023-12-11",45280.333333333336,"2023-12-11",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nUPM 470206",null,null,37888,"2023-07-05","Minor","5,6"]
[null,"Infrabel","38694","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2023,2023,50,50,"2023-12-11",45280.333333333336,"2023-12-11",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 116 à 121 + faisceau manage\r\nUPM 474841",null,null,38694,"2023-08-17","Minor","1,2,3,4,5"]
[null,"Infrabel","49235","Lille - Charleroi","< >","LUTTRE","ROUX",2023,2023,50,50,"2023-12-11",45280.979166666664,"2023-12-16",45280.208333333336,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement de la transversale Sud de Luttre\r\nDépose des traverses et consoles\r\nDémolition des poteaux\r\nUPM : 414149",null,null,49235,"2023-06-19","Minor","1,2,3,4,5"]
[null,"Infrabel","69944","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2023,2023,50,50,"2023-12-11",45280.979166666664,"2023-12-16",45280.229166666664,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR2023 - xxx L40 et autres\r\nFinitions P93\r\nUPM 472306",null,null,69944,"2023-08-08","Minor","1,2,3,4,5"]
[null,"Infrabel","50996","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2023,2023,50,50,"2023-12-11",45280.388888888891,"2023-12-11",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Semaine verte , visite et interventions diverses",null,null,50996,"2023-06-30","Minor","1,2,3,4,5"]
[null,"Infrabel","52895","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2023,2023,50,50,"2023-12-12",45280.013888888891,"2023-12-15",45280.173611111109,"4d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-405114\r\nMasterplan Gent\r\nStap 31: afbraak perronspoor 4 + 5\r\nL50E Y West Driehoek Ledeberg Niet inbegrepen, SP I tot VIII wel inbegrepen\r\nB/L50 FGSP - Y West Driehoek Ledeberg vrij\r\nA/L50 tot AW 18BH vrij\r\nA+B/L50A6 FGSP - Y Snepbrug vrij\r\nA+B/L75 FGS",null,null,52895,"2023-05-25","Minor","1,2,3,4,5"]
[null,"Infrabel","55204","Namur - Antwerpen","< >","SCHAERBEEK","Y.JOSAPHAT",2023,2023,50,50,"2023-12-12",45280.013888888891,"2023-12-16",45280.215277777781,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P137304: Upgrade SI zone H\r\nB L161 : sein D4-L.8  -> sein LX-J.8\r\nA L161 : sein D3-L.8 -> sein L-J.8\r\nB L25  : J12-E.8  -> sein DX5-L.8",null,null,55204,"2023-07-18","Minor","1,2,3,4,5"]
[null,"Infrabel","53371","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2023,2023,50,50,"2023-12-12",45280.388888888891,"2023-12-12",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Semaine verte , visite et interventions diverses",null,null,53371,"2023-06-30","Minor","1,2,3,4,5"]
[null,"Infrabel","57405","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-DIJKSTRAAT",2023,2023,50,50,"2023-12-12",45280.038194444445,"2023-12-15",45280.208333333336,"4d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan station Mechelen\r\nWeeknachten TUC\r\nRooster N+M\r\n+ sporen 5 en 6 te FM (R-416500)",null,null,57405,"2023-06-29","Minor","1,2,3,4,5"]
[null,"Infrabel","50994","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2023,2023,50,50,"2023-12-14",45280.34375,"2023-12-14",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Semaine verte , visite et interventions diverses\r\nUPM 413418",null,null,50994,"2023-06-30","Minor","1,2,3,4,5"]
[null,"Infrabel","57298","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-DIJKSTRAAT",2023,2023,50,51,"2023-12-15",45280.996527777781,"2023-12-18",45280.166666666664,"3d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS\r\n\r\nR-416502",null,null,57298,"2023-06-30","Minor","5,6"]
[null,"Infrabel","60341","Namur - Antwerpen","< >","MUIZEN-ROOSTER T","Y.HEIKE",2023,2023,50,51,"2023-12-15",45280.996527777781,"2023-12-18",45280.166666666664,"2d, 04:05h","Continuous",null,"T","","",null,null,null,null,null,null,null,"masterplan mechelen \r\ndeels met L27\r\n\r\nR-418714",null,null,60341,"2023-07-04","Medium","5,6"]
[null,"Infrabel","49945","Lille - Antwerpen","< >","DE PINTE","WAREGEM",2023,2023,50,51,"2023-12-15",45280.875,"2023-12-18",45280.208333333336,"2d, 08:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-404871\r\nIDS SIW  Deinze\r\ntestritten op zondag in overleg met regelaar\r\nuitwijk testloco in bundel Deinze",null,null,49945,"2023-05-25","Medium","5,6"]
[null,"Infrabel","53372","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2023,2023,50,50,"2023-12-15",45280.34375,"2023-12-15",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Semaine verte , visite et interventions diverses\r\nUPM 413420",null,null,53372,"2023-06-30","Minor","1,2,3,4,5"]
[null,"Infrabel","50357","Athus - Meuse","< >","PALISEUL","BERTRIX",2023,2023,50,51,"2023-12-16",45280.958333333336,"2023-12-18",45280.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"forages, consoles",null,null,50357,"2023-08-17","Minor","5,6"]
[null,"Infrabel","46001","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2023,2023,50,50,"2023-12-16",45280.333333333336,"2023-12-17",45280.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique + maintenance infrastructure + contrôles\r\nUPM 468482 ; 468486",null,null,46001,"2023-07-06","Minor","5,6"]
[null,"Infrabel","65746","Namur - Antwerpen",">","MARCINELLE","CHARLEROI-OUEST",2023,2023,50,50,"2023-12-16",45280.979166666664,"2023-12-17",45280.208333333336,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2023-313 : Rechargement armoires AZSMR.\r\nCR 2023-313 en cours d'analyse (21/02/2023)\r\nRS le 13/03/2023\r\nUPM 456317\r\nCR 2023-313 Version 02 le 02/08/2023 - validée le 02/08/2023.",null,null,65746,"2023-08-22","Minor","1,2,3,4,5"]
[null,"Infrabel","37915","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2023,2023,50,50,"2023-12-17",45280.333333333336,"2023-12-17",45280.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144 + 130/1 + maintenance infrastructure + contrôles",null,null,37915,"2023-08-17","Minor","5,6"]
[null,"Infrabel","60340","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2023,2023,50,50,"2023-12-17",45280.25,"2023-12-17",45280.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TOS 2222: Onderhoud wissels Y Liersesteenweg , Y-Krijgsbaan en Y-Zuid Groenenhoek.\r\n\r\nperiodiciteit: 1 zondag per maand, \r\nverlenging op werkvenster van L27A, \r\nuren 6:00u tot 17:40u\r\n\r\nTE HERHALEN 1  zondag per maand\r\n\r\nR-418711",null,null,60340,"2023-08-08","Minor","5,6"]
[null,"Infrabel","57297","Namur - Antwerpen","< >","Y.HEIKE","MUIZEN",2023,2023,50,51,"2023-12-17",45280.993055555555,"2023-12-18",45280.208333333336,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS\r\n\r\nR-416505",null,null,57297,"2023-06-30","Minor","5,6"]
[null,"Infrabel","54640","Athus - Meuse",">","GEDINNE","PALISEUL",2023,2023,51,51,"2023-12-18",45280.333333333336,"2023-12-18",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie\r\nUPM 412206",null,null,54640,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","53798","Erquelinnes - Montzen",">","BRESSOUX","FROIDMONT",2023,2023,51,51,"2023-12-18",45280.333333333336,"2023-12-18",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie",null,null,53798,"2023-08-16","Minor","1,2,3,4,5"]
[null,"Infrabel","55205","Namur - Antwerpen","< >","SCHAERBEEK","Y.JOSAPHAT",2023,2023,51,51,"2023-12-18",45280.979166666664,"2023-12-23",45280.1875,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P137304: Upgrade SI zone H\r\nB L161 : sein D4-L.8  -> sein LX-J.8\r\nA L161 : sein D3-L.8 -> sein L-J.8\r\nB L25  : J12-E.8  -> sein DX5-L.8",null,null,55205,"2023-07-18","Minor","1,2,3,4,5"]
[null,"Infrabel","55105","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2023,2023,51,51,"2023-12-18",45280.003472222219,"2023-12-23",45280.201388888891,"6d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FBMZ_16 en FBMZ_17 volgens onderhoudskalender Area CE\r\n\r\nL96 Spoor A tussen perron FBMZ en Y Ruisbroek + naastliggend spoor (Bypass)",null,null,55105,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","51228","Namur - Antwerpen",">","LA ROCHE(BRABANT)","TILLY",2023,2023,51,51,"2023-12-18",45280.354166666664,"2023-12-18",45280.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2023: L140 Partie 3\r\nUPM 469280",null,null,51228,"2023-07-05","Minor","1,2,3,4,5"]
[null,"Infrabel","50878","Athus - Meuse",">","NAMUR","JAMBES",2023,2023,51,51,"2023-12-18",45280.395833333336,"2023-12-18",45280.645833333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 413276",null,null,50878,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","53807","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2023,2023,51,51,"2023-12-18",45280.527777777781,"2023-12-18",45280.680555555555,"1d, 03:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie avec contrôle PN",null,null,53807,"2023-07-14","Minor","1,2,3,4,5"]
[null,"Infrabel","54641","Athus - Meuse",">","PALISEUL","GEDINNE",2023,2023,51,51,"2023-12-19",45280.333333333336,"2023-12-19",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,54641,"2023-07-03","Minor","1,2,3,4,5"]
[null,"Infrabel","55225","Lille - Charleroi",">","NEUFVILLES","SOIGNIES",2023,2023,51,51,"2023-12-19",45280.333333333336,"2023-12-19",45280.427083333336,"1d, 02:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VB (entre AS 08BE-01AE)\r\n+ S460 voie A\r\nUPM 469338",null,null,55225,"2023-06-22","Minor","1,2,3,4,5"]
[null,"Infrabel","55233","Lille - Charleroi",">","SOIGNIES","NEUFVILLES",2023,2023,51,51,"2023-12-19",45280.447916666664,"2023-12-19",45280.541666666664,"1d, 02:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA (entre AS 07AE et 13BE)\r\n+ S460 voie B\r\nUPM 469342",null,null,55233,"2023-06-22","Minor","1,2,3,4,5"]
[null,"Infrabel","53374","Athus - Meuse",">","LUSTIN","YVOIR",2023,2023,51,51,"2023-12-19",45280.375,"2023-12-19",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 413277",null,null,53374,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","61171","Athus - Meuse",">","STOCKEM-NORD","ARLON",2023,2023,51,51,"2023-12-19",45280.361111111109,"2023-12-19",45280.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,61171,"2023-08-08","Minor","1,2,3,4,5"]
[null,"Infrabel","51239","Namur - Antwerpen",">","TILLY","FLEURUS",2023,2023,51,51,"2023-12-19",45280.354166666664,"2023-12-19",45280.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2023: L140 Partie 4\r\nUPM 469284",null,null,51239,"2023-07-05","Minor","1,2,3,4,5"]
[null,"Infrabel","53772","Erquelinnes - Montzen",">","VISE","BRESSOUX",2023,2023,51,51,"2023-12-19",45280.395833333336,"2023-12-19",45280.611111111109,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie",null,null,53772,"2023-07-14","Minor","1,2,3,4,5"]
[null,"Infrabel","51269","Namur - Antwerpen",">","JEMEPPE-SUR-SAMBRE-MARCHANDISE","TAMINES",2023,2023,51,51,"2023-12-20",45280.993055555555,"2023-12-21",45280.1875,"1d, 04:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2023: L130 Partie 1\r\nUPM 414247",null,null,51269,"2023-07-05","Minor","1,2,3,4,5"]
[null,"Infrabel","61993","Athus - Meuse",">","HALANZY","Y.AUBANGE",2023,2023,51,51,"2023-12-20",45280.375,"2023-12-20",45280.645833333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / Maintenance voie A L 165\r\nVisite voie A",null,null,61993,"2023-07-03","Minor","1,2,3,4,5"]
[null,"Infrabel","53375","Athus - Meuse",">","YVOIR","LUSTIN",2023,2023,51,51,"2023-12-20",45280.375,"2023-12-20",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 413279",null,null,53375,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","61169","Athus - Meuse",">","HABAY","STOCKEM-NORD",2023,2023,51,51,"2023-12-20",45280.375,"2023-12-20",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,61169,"2023-08-08","Minor","1,2,3,4,5"]
[null,"Infrabel","51049","Erquelinnes - Montzen",">","JAVA","STATTE",2023,2023,51,51,"2023-12-20",45280.354166666664,"2023-12-20",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 414453",null,null,51049,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","54672","Athus - Meuse",">","PALISEUL","BERTRIX",2023,2023,51,51,"2023-12-21",45280.333333333336,"2023-12-21",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,54672,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","51278","Namur - Antwerpen",">","TAMINES","LE CAMPINAIRE",2023,2023,51,51,"2023-12-21",45280.993055555555,"2023-12-22",45280.1875,"1d, 04:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2023: L130 Partie 2\r\nUPM 469272",null,null,51278,"2023-07-05","Minor","1,2,3,4,5"]
[null,"Infrabel","51067","Erquelinnes - Montzen",">","ANDENNE","JAVA",2023,2023,51,51,"2023-12-21",45280.5625,"2023-12-21",45280.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 414454",null,null,51067,"2023-07-07","Minor","1,2,3,4,5"]
[null,"Infrabel","51058","Erquelinnes - Montzen",">","PLOMCOT","BEEZ",2023,2023,51,51,"2023-12-21",45280.375,"2023-12-21",45280.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 414455",null,null,51058,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","53376","Athus - Meuse",">","YVOIR","DINANT",2023,2023,51,51,"2023-12-21",45280.34375,"2023-12-21",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 413288",null,null,53376,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","54450","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2023,2023,51,51,"2023-12-21",45280.336805555555,"2023-12-21",45280.413194444445,"1d, 01:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite Ligne ETCS",null,null,54450,"2023-07-03","Minor","1,2,3,4,5"]
[null,"Infrabel","51260","Erquelinnes - Montzen",">","CHARLEROI-CENTRAL","LA SAMBRE",2023,2023,51,51,"2023-12-22",45280.958333333336,"2023-12-23",45280.0625,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2023: L130A Partie 3.a\r\nUPM 469276",null,null,51260,"2023-07-05","Minor","1,2,3,4,5"]
[null,"Infrabel","54673","Athus - Meuse",">","BERTRIX","PALISEUL",2023,2023,51,51,"2023-12-22",45280.333333333336,"2023-12-22",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,54673,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","53377","Athus - Meuse",">","DINANT","YVOIR",2023,2023,51,51,"2023-12-22",45280.385416666664,"2023-12-22",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 413289",null,null,53377,"2023-07-07","Minor","1,2,3,4,5"]
[null,"Infrabel","51295","Namur - Antwerpen",">","CHARLEROI-CENTRAL","CHATELET",2023,2023,51,51,"2023-12-23",45280.041666666664,"2023-12-23",45280.229166666664,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2023: L130 Partie 3.b\r\nUPM 469274",null,null,51295,"2023-07-05","Minor","5,6"]
[null,"Infrabel","50881","Athus - Meuse",">","JAMBES","LUSTIN",2023,2023,51,51,"2023-12-23",45280.385416666664,"2023-12-23",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 413291",null,null,50881,"2023-07-07","Minor","5,6"]
[null,"Infrabel","51076","Erquelinnes - Montzen",">","BEEZ","SCLAIGNEAUX",2023,2023,51,51,"2023-12-23",45280.354166666664,"2023-12-23",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 414456",null,null,51076,"2023-07-07","Minor","5,6"]
[null,"Infrabel","51082","Erquelinnes - Montzen",">","MARCHE-LES-DAMES","ANDENNE",2023,2023,51,51,"2023-12-24",45280.354166666664,"2023-12-24",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 414457",null,null,51082,"2023-07-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61938","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2023,2023,52,52,"2023-12-26",45280.375,"2023-12-26",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie A\r\nVisite voie A",null,null,61938,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","51000","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2023,2023,52,52,"2023-12-26",45280.388888888891,"2023-12-26",45280.65625,"1d, 06:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,51000,"2023-08-08","Minor","1,2,3,4,5"]
[null,"Infrabel","50883","Athus - Meuse",">","LUSTIN","JAMBES",2023,2023,52,52,"2023-12-27",45280.385416666664,"2023-12-27",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 413294",null,null,50883,"2023-07-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61944","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2023,2023,52,52,"2023-12-27",45280.375,"2023-12-27",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie B\r\nVisite voie B",null,null,61944,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","54330","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-FRANCE",2023,2023,52,52,"2023-12-27",45280.375,"2023-12-27",45280.5,"1d, 03:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie ETCS",null,null,54330,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","61934","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2023,2023,52,52,"2023-12-28",45280.378472222219,"2023-12-28",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance et/ou visite voie A",null,null,61934,"2023-08-08","Minor","1,2,3,4,5"]
[null,"Infrabel","51001","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2023,2023,52,52,"2023-12-28",45280.34375,"2023-12-28",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA\r\nUPM 413427",null,null,51001,"2023-07-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61935","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2023,2023,52,52,"2023-12-29",45280.378472222219,"2023-12-29",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,61935,"2023-08-08","Minor","1,2,3,4,5"]
[null,"Infrabel","51002","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2023,2023,52,52,"2023-12-29",45280.34375,"2023-12-29",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB\r\nUPM 413428",null,null,51002,"2023-07-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61995","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,1,1,"2024-01-02",45280.375,"2024-01-02",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / Maintenance voie B L 165\r\n\r\nVisite voie B",null,null,61995,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","53379","Athus - Meuse",">","BEAURAING","HOUYET",2024,2024,1,1,"2024-01-02",45280.388888888891,"2024-01-02",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,53379,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","61471","Athus - Meuse",">","BERTRIX","STRAIMONT",2024,2024,1,1,"2024-01-03",45280.333333333336,"2024-01-03",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,61471,"2023-09-14","Minor","1,2,3,4,5"]
[null,"Infrabel","67810","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2024,2024,1,1,"2024-01-03",45280.333333333336,"2024-01-03",45280.4375,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11\r\nTCR 467939",null,null,67810,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","61163","Athus - Meuse",">","LAVAUX","MARBEHAN",2024,2024,1,1,"2024-01-03",45280.361111111109,"2024-01-03",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,61163,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","60086","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,1,1,"2024-01-03",45280.395833333336,"2024-01-03",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn\r\n\r\nR-444817",null,null,60086,"2023-07-04","Minor","1,2,3,4,5"]
[null,"Infrabel","53378","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,1,1,"2024-01-03",45280.388888888891,"2024-01-03",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,53378,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","61492","Athus - Meuse",">","VONECHE","GEDINNE",2024,2024,1,1,"2024-01-04",45280.333333333336,"2024-01-04",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,61492,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","61164","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2024,2024,1,1,"2024-01-04",45280.368055555555,"2024-01-04",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,61164,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","65535","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2024,2024,1,1,"2024-01-04",45280.375,"2024-01-04",45280.645833333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Schouwen lopend spoor\r\nR-464080",null,null,65535,"2023-07-19","Minor","1,2,3,4,5"]
[null,"Infrabel","61470","Athus - Meuse",">","STRAIMONT","BERTRIX",2024,2024,1,1,"2024-01-04",45280.375,"2024-01-04",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,61470,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","67788","Lille - Charleroi",">","LUTTRE","MARCHIENNE-AU-PONT",2024,2024,1,1,"2024-01-04",45280.326388888891,"2024-01-04",45280.645833333336,"1d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J10",null,null,67788,"2023-06-20","Minor","1,2,3,4,5"]
[null,"Infrabel","61491","Athus - Meuse",">","GEDINNE","VONECHE",2024,2024,1,1,"2024-01-05",45280.333333333336,"2024-01-05",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,61491,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","59035","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,1,2,"2024-01-05",45280.979166666664,"2024-01-08",45280.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"migratie tunnelveiligheidstechnieken antw NZ\r\n\r\nR-459879",null,null,59035,"2023-07-05","Medium","5,6"]
[null,"Infrabel","61165","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2024,2024,1,1,"2024-01-05",45280.368055555555,"2024-01-05",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,61165,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","61994","Athus - Meuse",">","HALANZY","Y.AUBANGE",2024,2024,1,1,"2024-01-05",45280.375,"2024-01-05",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / Maintenance voie A L 165\r\nVisite voie A",null,null,61994,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","61493","Athus - Meuse",">","VONECHE","BEAURAING",2024,2024,1,1,"2024-01-06",45280.333333333336,"2024-01-06",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,61493,"2023-08-24","Minor","5,6"]
[null,"Infrabel","49188","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2024,2024,1,1,"2024-01-06",45280.333333333336,"2024-01-07",45280.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles\r\nUPM 466916\r\nUPM 466918",null,null,49188,"2023-11-17","Minor","5,6"]
[null,"Infrabel","63153","Namur - Antwerpen","< >","LEUVEN","WAVRE",2024,2024,1,1,"2024-01-06",45280.993055555555,"2024-01-07",45280.256944444445,"1d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"lossen rails\r\nN za/zo: min 5 uur nodig voor lossen rails robel\r\n\r\nR-446501",null,null,63153,"2023-07-04","Minor","5,6"]
[null,"Infrabel","61963","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,1,1,"2024-01-06",45280.375,"2024-01-06",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie A\r\nVisite voie A",null,null,61963,"2023-08-24","Minor","5,6"]
[null,"Infrabel","61167","Athus - Meuse",">","ARLON","Y.AUTELBAS",2024,2024,1,1,"2024-01-06",45280.361111111109,"2024-01-06",45280.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,61167,"2023-08-24","Minor","5,6"]
[null,"Infrabel","37868","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2024,2024,1,1,"2024-01-06",45280.326388888891,"2024-01-06",45280.659722222219,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A + maintenance infrastructure + contrôles\r\nUPM:  461973",null,null,37868,"2023-11-17","Minor","5,6"]
[null,"Infrabel","37876","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2024,2024,1,1,"2024-01-07",45280.333333333336,"2024-01-07",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie B + maintenance infrastructure + contrôles\r\nUPM : 461982",null,null,37876,"2023-08-07","Minor","5,6"]
[null,"Infrabel","61494","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,1,1,"2024-01-07",45280.333333333336,"2024-01-07",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,61494,"2023-08-24","Minor","5,6"]
[null,"Infrabel","61966","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2024,2024,1,1,"2024-01-07",45280.375,"2024-01-07",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie B\r\nVisite voie B",null,null,61966,"2023-08-24","Minor","5,6"]
[null,"Infrabel","61166","Athus - Meuse",">","MARBEHAN","HABAY",2024,2024,1,1,"2024-01-07",45280.375,"2024-01-07",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,61166,"2023-08-24","Minor","5,6"]
[null,"Infrabel","62334","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","FLEMALLE-HAUTE",2024,2024,2,2,"2024-01-08",45280.958333333336,"2024-01-13",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Z.19.41 - Maintenance P3\r\n+ Entretien et interventions diverses sur caténaire",null,null,62334,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","61490","Athus - Meuse",">","GEDINNE","PALISEUL",2024,2024,2,2,"2024-01-08",45280.333333333336,"2024-01-08",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,61490,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","47135","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,2,2,"2024-01-08",45280.979166666664,"2024-01-13",45280.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nmassifs caténaires\r\nUPM : 468207",null,null,47135,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","55934","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2024,2024,2,2,"2024-01-08",45280.951388888891,"2024-01-13",45280.180555555555,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 en P3 HKV\r\nUPM 462897",null,null,55934,"2023-07-27","Minor","1,2,3,4,5"]
[null,"Infrabel","64179","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,2,2,"2024-01-08",45280.972222222219,"2024-01-12",45280.208333333336,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-461483\r\n\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VIII (geen continue buiten dienst stellingen meer op de sporen IX tem XII)\r\n\r\n(alternatief stappenplan)",null,null,64179,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","64002","Lille - Antwerpen","< >","DEINZE","KORTRIJK",2024,2024,2,2,"2024-01-08",45280.972222222219,"2024-01-13",45280.173611111109,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud \r\nL75 Y Zandberg IN\r\nL75 \r\nFD SP I+II+III inbegrepen\r\nLK SP I-II-III-IV inbegrepen\r\nL89 \r\nFDN SP I-II inbegrepen\r\nL86\r\nFDN-FRN inbegrepen",null,null,64002,"2023-03-13","Minor","1,2,3,4,5"]
[null,"Infrabel","61240","Erquelinnes - Montzen","< >","HUY","NAMUR",2024,2024,2,2,"2024-01-08",45280.96875,"2024-01-12",45280.211805555555,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.43\r\nUPM : 459681",null,null,61240,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","61929","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","BAKENBOS",2024,2024,2,2,"2024-01-08",45280.986111111109,"2024-01-13",45280.201388888891,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_05 Area CE volgens onderhoudskalender 2024.\r\nBuitendienststelling L161 tussen Bru Luxemburg en Bakenbos voor onderhoudswerken + L161A.",null,null,61929,"2023-08-17","Minor","1,2,3,4,5"]
[null,"Infrabel","60133","Athus - Meuse","< >","HAVERSIN","ROCHEFORT-JEMELLE",2024,2024,2,51,"2024-01-08",45280.986111111109,"2024-12-20",45280.180555555555,"347d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaire Axe 3 en gare de Marloie Phase 24\r\n+ Travaux PLP BA Marloie-Jemelle\r\nUPM 474856",null,null,60133,"2023-10-25","Minor","1,2,3,4,5"]
[null,"Infrabel","61196","Lille - Charleroi","< >","JURBISE","ATH",2024,2024,2,2,"2024-01-08",45280.944444444445,"2024-01-12",45280.222222222219,"4d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53\r\nUPM 464313",null,null,61196,"2023-07-27","Minor","1,2,3,4,5"]
[null,"Infrabel","61041","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,2,2,"2024-01-08",45280.989583333336,"2024-01-12",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service\r\nUPM 465740",null,null,61041,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","62067","Namur - Antwerpen","< >","MECHELEN","Y.DRABSTRAAT",2024,2024,2,2,"2024-01-08",45280.996527777781,"2024-01-13",45280.201388888891,"5d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\nR-446502",null,null,62067,"2023-07-10","Minor","1,2,3,4,5"]
[null,"Infrabel","62632","Namur - Antwerpen","< >","Y.HEIKE","MUIZEN",2024,2024,2,2,"2024-01-08",45280.996527777781,"2024-01-13",45280.201388888891,"5d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rooster M+N. Werken ikv MP Mechelen.\r\nR-444821",null,null,62632,"2023-07-10","Minor","1,2,3,4,5"]
[null,"Infrabel","49595","Lille - Charleroi","< >","MONS","JURBISE",2024,2024,2,2,"2024-01-08",45280.947916666664,"2024-01-13",45280.173611111109,"5d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification - Phase 9 - 2024 (suite planning 2023)\r\nPose des traverses entre 49/9B et 53/17B\r\n+ ETCS L2-IL_SO_P036_L96_L97_Jurbise - Mons - Saint Ghislain_ETCS\r\nETCS : Travaux extérieurs + chargements\r\nmeewerken mogelijk\r\nUPM 459865",null,null,49595,"2023-07-27","Minor","1,2,3,4,5"]
[null,"Infrabel","61168","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2024,2024,2,2,"2024-01-08",45280.409722222219,"2024-01-08",45280.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,61168,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","54073","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2024,2024,2,2,"2024-01-08",45280.381944444445,"2024-01-08",45280.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41 (à répéter toutes les 6 semaines, le lundi)",null,null,54073,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","61489","Athus - Meuse",">","PALISEUL","GEDINNE",2024,2024,2,2,"2024-01-09",45280.333333333336,"2024-01-09",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,61489,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","65854","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2024,2024,2,2,"2024-01-09",45280.013888888891,"2024-01-13",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-460387\r\n\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\n\r\nTesten, meewerken niet mogelijk",null,null,65854,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","61472","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2024,2024,2,2,"2024-01-09",45280.378472222219,"2024-01-09",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,61472,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","61468","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2024,2024,2,2,"2024-01-10",45280.378472222219,"2024-01-10",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,61468,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","61120","Athus - Meuse",">","DINANT","Y.NEFFE",2024,2024,2,2,"2024-01-10",45280.34375,"2024-01-10",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites\r\nSemaine verte\r\nUPM 462594",null,null,61120,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61487","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,2,2,"2024-01-11",45280.333333333336,"2024-01-11",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,61487,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","61941","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2024,2024,2,2,"2024-01-11",45280.375,"2024-01-11",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A\r\nEntretien / maintenance voie A",null,null,61941,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","60102","Namur - Antwerpen",">","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL",2024,2024,2,2,"2024-01-11",45280.34375,"2024-01-11",45280.510416666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12 buiten dienst\r\n\r\nR-444860",null,null,60102,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","61488","Athus - Meuse",">","BERTRIX","PALISEUL",2024,2024,2,2,"2024-01-12",45280.333333333336,"2024-01-12",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,61488,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","58839","Lille - Charleroi","< >","JURBISE","ATH",2024,2024,2,2,"2024-01-12",45280.944444444445,"2024-01-14",45280.708333333336,"2d, 18:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z7.53 + Z13.54\r\nUPM 442409",null,null,58839,"2023-07-27","Medium","5,6"]
[null,"Infrabel","48508","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2024,2024,2,3,"2024-01-12",45280.947916666664,"2024-01-15",45280.208333333336,"2d, 06:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.51  P4+\r\nUPM : 457206\r\nReport 2023",null,null,48508,"2023-08-02","Medium","5,6"]
[null,"Infrabel","69845","Namur - Antwerpen","< >","CHATELET","CHATELET",2024,2024,2,3,"2024-01-12",45280.947916666664,"2024-01-15",45280.208333333336,"2d, 06:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Ajout Voie Car Wash à la Colt 48508, pour entrée machines, entre Signal D2-I. 20 et LYJ 20 + Cas elec  27314 + 316\r\nCR 2024-116 envoyé le 20/07/2023 - CR 2024-116 V03 envoyé le 13/09/2023 - CR validé le 02/10/2023 - CR 2024-116 V 04 validé le 23/10/23\r\n",null,null,69845,"2023-10-24","Medium","5,6"]
[null,"Infrabel","61947","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2024,2024,2,2,"2024-01-12",45280.375,"2024-01-12",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B\r\nEntretien / maintenance voie B",null,null,61947,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","33781","Namur - Antwerpen","< >","Y.BERCHEM-STADION","Y.LIERSESTEENWEG",2024,2024,2,3,"2024-01-12",45280.982638888891,"2024-01-15",45280.190972222219,"3d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing van de wissels Y-Drabstraat\r\n\r\nR-444349",null,null,33781,"2023-07-06","Minor","5,6"]
[null,"Infrabel","61226","Erquelinnes - Montzen",">","ENGIS","AMAY",2024,2024,2,2,"2024-01-13",45280.333333333336,"2024-01-13",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,61226,"2023-09-21","Minor","5,6"]
[null,"Infrabel","58745","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,2,3,"2024-01-13",45280.020833333336,"2024-01-15",45280.1875,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-457862\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP\r\nPerron I tem II en IV tot en met IV  (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\nSpoor III vrijgemaakt Z verkeer\r\n\r\n(alternatief s",null,null,58745,"2023-09-28","Medium","5,6"]
[null,"Infrabel","49435","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","MERELBEKE-ROOSTER S",2024,2024,2,3,"2024-01-13",45280.25,"2024-01-15",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-432063\r\n\r\nVernieuwen Y. Oost Driehoek Ledeberg \r\nFase 2 + 3\r\nWE1/3\r\n* aangepast naar 06.00u R6 >> geen CBP tijdens nacht R5/R6",null,null,49435,"2023-09-28","Medium","5,6"]
[null,"Infrabel","71547","Namur - Antwerpen","< >","CHATELET","CHATELET-GRIL EST",2024,2024,2,2,"2024-01-13",45280.000694444447,"2024-01-14",45280.1875,"2d, 04:29h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose et dépose de l'ART\r\nPose de l'ART Nuit 13^14/01/24 de 00.01 à 04.30\r\nDépose de l'ART nuit 20^21/01/24 de 00.01 à 04.30\r\nTCR 476538\r\nEn corrélation nuit 13^14/01/24 avec Colt 48508 - TCR 457206 / Nuit 20^21/01/24 Colt 69847 - TCR 471584",null,null,71547,"2023-10-24","Minor","5,6"]
[null,"Infrabel","50618","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,2,3,"2024-01-13",45280.996527777781,"2024-01-15",45280.222222222219,"2d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris\r\nUPM 474854",null,null,50618,"2023-08-30","Minor","5,6"]
[null,"Infrabel","61591","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2024,2024,2,2,"2024-01-14",45280.25,"2024-01-14",45280.625,"1d, 09:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...\r\n\r\nR-454081",null,null,61591,"2023-08-24","Minor","5,6"]
[null,"Infrabel","61227","Erquelinnes - Montzen",">","TILLEUR","ENGIS",2024,2024,2,2,"2024-01-14",45280.354166666664,"2024-01-14",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,61227,"2023-09-21","Minor","5,6"]
[null,"Infrabel","71482","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","ESSEN-GRENS",2024,2024,2,2,"2024-01-14",45280.072916666664,"2024-01-14",45280.180555555555,"1d, 02:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-189\r\nBuitendienst van de EBP seinpost Berchem (FN) - Computer Room gedurende minimaal 4 uur te bepalen tussen 22.00 uur en 06.00 uur voor werken : \"Renewal of Network Device\".\r\nHet volledig stilleggen van het treinverkeer vereist is.\r\nR-478357",null,null,71482,"2023-11-09","Minor","5,6"]
[null,"Infrabel","49045","Namur - Antwerpen",">","NAMUR","FLAWINNE",2024,2024,3,3,"2024-01-15",45280.333333333336,"2024-01-15",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nUPM : 465512",null,null,49045,"2023-11-17","Minor","1,2,3,4,5"]
[null,"Infrabel","49461","Lille - Charleroi",">","LUTTRE","ROUX",2024,2024,3,11,"2024-01-15",45280.333333333336,"2024-03-11",45280.25,"56d, 22:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre : Phase 1-2024\r\nDossier de concertation validé le 28 octobre 2021\r\nUPM 456865\r\nART\r\nCR 2024-224 envoyé le 07/11/23 (Concerne WE 3-4/02/24) - CR refusé le 21/11/23 - CR 2024-224 version 02 le 28/11/23 - Validé le 07/12/23",null,null,49461,"2023-12-13","High","1,2,3,4,5,6,7"]
[null,"Infrabel","47136","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,3,3,"2024-01-15",45280.979166666664,"2024-01-20",45280.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nmassifs caténaires\r\nUPM : 468211",null,null,47136,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","64212","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,3,3,"2024-01-15",45280.972222222219,"2024-01-19",45280.208333333336,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-461639\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VIII (geen continue buiten dienst stellingen meer op de sporen IX tem XII)\r\n\r\n(alternatief stappenplan)",null,null,64212,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","60280","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2024,2024,3,3,"2024-01-15",45280.972222222219,"2024-01-19",45280.208333333336,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"herelectrificatie (bijkomend)\r\n+\r\nOnderhoud\r\nZ04.25 : studie nog uit te voeren door I-CBE  COLT 62975\r\n\r\nR-445680",null,null,60280,"2023-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","64632","Lille - Antwerpen","< >","SINT-NIKLAAS","Y.MELSELE",2024,2024,3,3,"2024-01-15",45280.972222222219,"2024-01-20",45280.184027777781,"5d, 05:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nR-465636\r\n\r\n*perron II-V inbegrepen. \r\n*SP I + SP A  niet inbegrepen om doorrit naar L54 toe te laten",null,null,64632,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","72268","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,3,11,"2024-01-15",45280.354166666664,"2024-03-11",45280.645833333336,"57d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre : Phase 1-2024\r\nDossier de concertation validé le 28 octobre 2021\r\nUPM 456865\r\nART",null,null,72268,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","61109","Erquelinnes - Montzen","< >","Y.NORD","ERQUELINNES-FRONTIERE",2024,2024,3,3,"2024-01-15",45280.930555555555,"2024-01-19",45280.166666666664,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires caténaire (Beton+poteaux)\r\n+ Maintenance Z2. 51  P3 HKV\r\n+ Travaux voie A signalisation\r\nTCR 466703",null,null,61109,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","58698","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,3,3,"2024-01-16",45280.006944444445,"2024-01-20",45280.1875,"5d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\nR-431052",null,null,58698,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","65829","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","GENT-DAMPOORT",2024,2024,3,3,"2024-01-16",45280.027777777781,"2024-01-20",45280.184027777781,"5d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS L2-IL_NW_P025_P026_L59_Y Sint Bernadettestraat - Berchem_ETCS\r\nDownload, meewerken mogelijk\r\nR-469296",null,null,65829,"2023-08-08","Minor","1,2,3,4,5"]
[null,"Infrabel","64695","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2024,2024,3,3,"2024-01-16",45280.020833333336,"2024-01-20",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nR-465641",null,null,64695,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","64653","Lille - Antwerpen","< >","LOKEREN","SINT-NIKLAAS",2024,2024,3,3,"2024-01-16",45280.013888888891,"2024-01-20",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\n* doorrit ultrasoon N13/14\r\nR-465153",null,null,64653,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","63369","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2024,2024,3,3,"2024-01-16",45280.375,"2024-01-16",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-446591",null,null,63369,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","54413","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,3,3,"2024-01-17",45280.375,"2024-01-17",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,54413,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","63392","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,3,3,"2024-01-17",45280.375,"2024-01-17",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-446598",null,null,63392,"2023-07-13","Minor","1,2,3,4,5"]
[null,"Infrabel","62010","Athus - Meuse",">","VIRTON","SIGNEULX",2024,2024,3,3,"2024-01-18",45280.375,"2024-01-18",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,62010,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","63415","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,3,3,"2024-01-18",45280.375,"2024-01-18",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-446600",null,null,63415,"2023-07-13","Minor","1,2,3,4,5"]
[null,"Infrabel","60281","Namur - Antwerpen","< >","MUIZEN-ROOSTER T","LEUVEN",2024,2024,3,4,"2024-01-19",45280.972222222219,"2024-01-22",45280.208333333336,"2d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"herelectrificatie (bijkomend)\r\n\r\nR-429651",null,null,60281,"2023-07-13","Medium","5,6"]
[null,"Infrabel","49584","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,3,4,"2024-01-19",45280.972222222219,"2024-01-22",45280.194444444445,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 1/6\r\nDépose transversale caténaire\r\n+ Maintenance Z8.52\r\nMise HS P4+ - Zone 8 AI52\r\nUPM 444880\r\nEn corrélation avec Colt 49461 + UPM 456865\r\nART",null,null,49584,"2023-09-20","Medium","5,6"]
[null,"Infrabel","61989","Athus - Meuse",">","SIGNEULX","VIRTON",2024,2024,3,3,"2024-01-19",45280.375,"2024-01-19",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,61989,"2023-08-28","Minor","1,2,3,4,5"]
[null,"Infrabel","63433","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,3,3,"2024-01-19",45280.375,"2024-01-19",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-446602",null,null,63433,"2023-07-13","Minor","1,2,3,4,5"]
[null,"Infrabel","66751","Lille - Charleroi",">","BRAINE-LE-COMTE","Y.FELUY",2024,2024,3,3,"2024-01-20",45280.333333333336,"2024-01-20",45280.635416666664,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique AI52 + AI53\r\nUPM 468109 - 468110",null,null,66751,"2023-09-11","Minor","5,6"]
[null,"Infrabel","49205","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2024,2024,3,3,"2024-01-20",45280.333333333336,"2024-01-21",45280.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique + maintenance infrastructure + contrôles\r\nUPM 466894\r\nUPM 466895",null,null,49205,"2023-11-17","Minor","5,6"]
[null,"Infrabel","63678","Erquelinnes - Montzen","< >","MARCHIENNE-ZONE","ERQUELINNES-FRONTIERE",2024,2024,3,4,"2024-01-20",45280.979166666664,"2024-01-22",45280.166666666664,"2d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-LS_SO_L130A_Software_Marchienne-Zone - Erquelinnes\r\nTesten\r\nMee werken niet mogelijk\r\nUPM 466274",null,null,63678,"2023-08-02","Minor","5,6"]
[null,"Infrabel","59036","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,3,4,"2024-01-20",45280.027777777781,"2024-01-22",45280.166666666664,"2d, 03:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"migratie tunnelveiligheidstechnieken antw NZ\r\n\r\nR-446060",null,null,59036,"2023-07-14","Medium","5,6"]
[null,"Infrabel","58757","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,3,4,"2024-01-20",45280.020833333336,"2024-01-22",45280.1875,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-457878\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg. AW 12BH vrij.\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)",null,null,58757,"2023-07-26","Medium","5,6"]
[null,"Infrabel","48644","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2024,2024,3,3,"2024-01-20",45280.25,"2024-01-21",45280.666666666664,"1d, 10:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 - Mise HS P4 + Diagno Zones 2 et 4\r\nUPM 459785",null,null,48644,"2023-07-27","Medium","5,6"]
[null,"Infrabel","62626","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2024,2024,3,3,"2024-01-20",45280.3125,"2024-01-20",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY (à répéter toutes les 4 semaines le samedi)",null,null,62626,"2023-08-29","Minor","5,6"]
[null,"Infrabel","50619","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,3,4,"2024-01-20",45280.996527777781,"2024-01-22",45280.222222222219,"2d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris\r\nUPM 474858",null,null,50619,"2023-08-30","Minor","5,6"]
[null,"Infrabel","69847","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2024,2024,3,4,"2024-01-20",45280.961805555555,"2024-01-22",45280.201388888891,"2d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-116 Maintenance Z15. 51 -> Bourrage de révision De Witt Voie B + lever ART + Ballastage complémentaire & toilette Voie B.\r\nP3 HKV\r\nTronçon Allongé\r\nCR 2024-116 envoyé le 20/07/2023 - CR 2024-116 V03 envoyé le 13/09/2023 - CR 2024-116 Version 04 ",null,null,69847,"2023-11-14","Minor","5,6"]
[null,"Infrabel","48974","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,3,3,"2024-01-21",45280.333333333336,"2024-01-21",45280.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144 + 130/1 + maintenance infrastructure + contrôles\r\nUPM 467554",null,null,48974,"2023-08-07","Minor","5,6"]
[null,"Infrabel","48896","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2024,2024,3,3,"2024-01-21",45280.333333333336,"2024-01-21",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nOttignies gare  voie 1 à 5 en alternance\r\nUPM : 467713",null,null,48896,"2023-08-30","Minor","5,6"]
[null,"Infrabel","69788","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2024,2024,3,3,"2024-01-21",45280.006944444445,"2024-01-21",45280.229166666664,"1d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Trapkooien Vilvoorde\r\nDemontage nieuwe luifel perron 3-4 voorbereiding\r\n\r\nR-471020",null,null,69788,"2023-07-14","Minor","5,6"]
[null,"Infrabel","62588","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2024,2024,3,3,"2024-01-21",45280.25,"2024-01-21",45280.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TOS 2222: Onderhoud wissels Y Liersesteenweg , Y-Krijgsbaan en Y-Zuid Groenenhoek.\r\n\r\nR-446674",null,null,62588,"2023-07-14","Minor","5,6"]
[null,"Infrabel","52761","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ANTWERPEN-NOORD-INRIT C1",2024,2024,3,3,"2024-01-21",45280.25,"2024-01-21",45280.729166666664,"1d, 11:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Oude Landen\r\nproject 304\r\n\r\nwerkvenster kan ingekort worden ,afhankelijk werken L59\r\n\r\nR-444403",null,null,52761,"2023-07-14","Minor","5,6"]
[null,"Infrabel","62640","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2024,2024,3,3,"2024-01-21",45280.3125,"2024-01-21",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY (à répéter toutes les 4 semaines le dimanche)",null,null,62640,"2023-08-29","Minor","5,6"]
[null,"Infrabel","64588","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2024,2024,4,4,"2024-01-22",45280.958333333336,"2024-01-27",45280.180555555555,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken\r\nFGDM niet IN.",null,null,64588,"2023-01-23","Minor","1,2,3,4,5"]
[null,"Infrabel","50577","Namur - Antwerpen",">","Y.FLAWINNE","MOUSTIER-GARAGE",2024,2024,4,4,"2024-01-22",45280.979166666664,"2024-01-23",45280.208333333336,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie\r\nUPM : 467246",null,null,50577,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","55037","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2024,2024,4,4,"2024-01-22",45280.979166666664,"2024-01-27",45280.208333333336,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10. 51   P3\r\nUPM : 460156",null,null,55037,"2023-08-02","Minor","1,2,3,4,5"]
[null,"Infrabel","64213","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,4,4,"2024-01-22",45280.972222222219,"2024-01-26",45280.208333333336,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VIII (geen continue buiten dienst stellingen meer op de sporen IX tem XII)\r\n\r\n(alternatief stappenplan)\r\n\r\nR-461841",null,null,64213,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","62976","Namur - Antwerpen","< >","Y.HEVER","Y.LEUVEN-BUNDEL M",2024,2024,4,4,"2024-01-22",45280.972222222219,"2024-01-26",45280.208333333336,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nZ04.25 : studie nog uit te voeren door I-CBE\r\n\r\nR-446683",null,null,62976,"2023-07-17","Minor","1,2,3,4,5"]
[null,"Infrabel","64642","Lille - Antwerpen","< >","LOKEREN","SINT-NIKLAAS",2024,2024,4,4,"2024-01-22",45280.972222222219,"2024-01-27",45280.194444444445,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"reservatie onderhoud\r\nLokeren\r\nSP II-III-IV inbegrepen, \r\nSP I na laatste trein\r\nSint Niklaas\r\nSPII-III-IV-V inbegrepen\r\nSP I na laatste trein\r\nR-465181",null,null,64642,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","61382","Erquelinnes - Montzen","< >","Y.NORD","ERQUELINNES-FRONTIERE",2024,2024,4,4,"2024-01-22",45280.9375,"2024-01-26",45280.173611111109,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires caténaire (Beton+poteaux)\r\n+ Maintenance Z2. 51  P3 HKV\r\n+ Travaux voie A signalisation\r\n+ MHS entre EXL20 Lobbes  et KK20 - Kxk20 Marchienne zone\r\nVisite  de la voie unique + entretien liaisons Ho",null,null,61382,"2023-08-02","Minor","1,2,3,4,5"]
[null,"Infrabel","57908","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2024,2024,4,4,"2024-01-22",45280.916666666664,"2024-01-27",45280.21875,"5d, 07:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF CHA24_0026001 \r\nLille Racc RougeBarre – Bif St André : REGE – RVB, RB/RT et RR\r\n+ Tirage de cable\r\nUPM 460042",null,null,57908,"2023-07-27","Minor","1,2,3,4,5"]
[null,"Infrabel","57794","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,4,4,"2024-01-22",45280.965277777781,"2024-01-26",45280.1875,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-431058\r\nVernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\n\r\nR5/56 in weekend TLO",null,null,57794,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","47301","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,4,4,"2024-01-22",45280.965277777781,"2024-01-27",45280.166666666664,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TLO-nachten voor TESTEN ETCS\r\n1 week aansluitend nachten in januari\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk\r\nR-431059",null,null,47301,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","61044","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,4,4,"2024-01-22",45280.989583333336,"2024-01-26",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service\r\nUPM 465743",null,null,61044,"2023-08-30","Minor","1,2,3,4,5"]
[null,"Infrabel","60126","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2024,2024,4,4,"2024-01-22",45280.996527777781,"2024-01-26",45280.190972222219,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud SIG +onderhoud wissels en overwegen\r\n\r\nR-445823",null,null,60126,"2023-07-17","Minor","1,2,3,4,5"]
[null,"Infrabel","62019","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2024,2024,4,4,"2024-01-22",45280.385416666664,"2024-01-22",45280.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,62019,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","62018","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-FRANCE",2024,2024,4,4,"2024-01-22",45280.375,"2024-01-22",45280.583333333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite voie unique L 165/2 \r\nVisite voie unique L 165/3\r\nVisite voie unique L 165/1\r\nMaintenance",null,null,62018,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","61113","Athus - Meuse",">","NAMUR","JAMBES",2024,2024,4,4,"2024-01-22",45280.388888888891,"2024-01-22",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 462599",null,null,61113,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","48957","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2024,2024,4,4,"2024-01-22",45280.319444444445,"2024-01-22",45280.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance\r\nUPM 467728",null,null,48957,"2023-08-30","Minor","1,2,3,4,5"]
[null,"Infrabel","66707","Lille - Charleroi",">","SOIGNIES","NEUFVILLES",2024,2024,4,4,"2024-01-23",45280.333333333336,"2024-01-23",45280.541666666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B\r\nUPM 464786 - 464794",null,null,66707,"2023-07-27","Minor","1,2,3,4,5"]
[null,"Infrabel","47137","Namur - Antwerpen",">","MOUSTIER-GARAGE","AUVELAIS",2024,2024,4,4,"2024-01-23",45280.979166666664,"2024-01-27",45280.208333333336,"4d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nmassifs caténaires\r\n+ Savu Entretien de voie\r\nUPM 467250",null,null,47137,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","65830","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","GENT-DAMPOORT",2024,2024,4,4,"2024-01-23",45280.027777777781,"2024-01-27",45280.184027777781,"5d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS L2-IL_NW_P025_P026_L59_Y Sint Bernadettestraat - Berchem_ETCS\r\nDownload, meewerken mogelijk\r\nR-469298",null,null,65830,"2023-08-08","Minor","1,2,3,4,5"]
[null,"Infrabel","64696","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2024,2024,4,4,"2024-01-23",45280.020833333336,"2024-01-27",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nR-465642",null,null,64696,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","65855","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2024,2024,4,4,"2024-01-23",45280.013888888891,"2024-01-27",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\n\r\nTesten, meewerken niet mogelijk\r\n\r\nR-460393",null,null,65855,"2023-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","64652","Lille - Antwerpen","< >","SINT-NIKLAAS","Y.MELSELE",2024,2024,4,4,"2024-01-23",45280.013888888891,"2024-01-27",45280.184027777781,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud\r\nR-465665\r\n\r\n*perron II-V inbegrepen. \r\n*SP I + SP A  niet inbegrepen om doorrit naar L54 toe te laten",null,null,64652,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61116","Athus - Meuse",">","LUSTIN","YVOIR",2024,2024,4,4,"2024-01-23",45280.375,"2024-01-23",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 462600",null,null,61116,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","62870","Lille - Antwerpen","< >","Y.OOST BERCHEM","SINT-NIKLAAS-OOST",2024,2024,4,4,"2024-01-24",45280.003472222219,"2024-01-24",45280.184027777781,"1d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen\r\nZ23.22 : studie nog uit te voeren door I-CBE\r\n\r\nR-445823",null,null,62870,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61117","Athus - Meuse",">","YVOIR","LUSTIN",2024,2024,4,4,"2024-01-24",45280.375,"2024-01-24",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 462601",null,null,61117,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61230","Erquelinnes - Montzen",">","JAVA","STATTE",2024,2024,4,4,"2024-01-24",45280.354166666664,"2024-01-24",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463086",null,null,61230,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","60675","Namur - Antwerpen",">","CHARLEROI-OUEST","Y.NORD",2024,2024,4,4,"2024-01-24",45280.541666666664,"2024-01-24",45280.625,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2024: L140 Partie 7\r\nUPM 465954",null,null,60675,"2023-08-02","Minor","1,2,3,4,5"]
[null,"Infrabel","60087","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,4,4,"2024-01-24",45280.395833333336,"2024-01-24",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn\r\n\r\nR-445851",null,null,60087,"2023-09-01","Minor","1,2,3,4,5"]
[null,"Infrabel","67078","Lille - Charleroi",">","ATH","BRUGELETTE",2024,2024,4,4,"2024-01-25",45280.333333333336,"2024-01-25",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno\r\nUPM 464319",null,null,67078,"2023-07-27","Minor","1,2,3,4,5"]
[null,"Infrabel","61075","Namur - Antwerpen","< >","NAMUR","RONET",2024,2024,4,4,"2024-01-25",45280.951388888891,"2024-01-26",45280.208333333336,"1d, 06:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 9\r\nPériodicité toutes les 4 semaines en alternance avec la zone 4\r\nzone 9 : 9 fois sur l'année\r\nzone 4 : 3 fois sur l'année\r\nUPM 459498",null,null,61075,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61118","Athus - Meuse",">","YVOIR","DINANT",2024,2024,4,4,"2024-01-25",45280.385416666664,"2024-01-25",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 462602",null,null,61118,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61231","Erquelinnes - Montzen",">","ANDENNE","JAVA",2024,2024,4,4,"2024-01-25",45280.5625,"2024-01-25",45280.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463087",null,null,61231,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61232","Erquelinnes - Montzen",">","PLOMCOT","BEEZ",2024,2024,4,4,"2024-01-25",45280.375,"2024-01-25",45280.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463084",null,null,61232,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","55941","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,4,4,"2024-01-25",45280.395833333336,"2024-01-25",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nMise HS en P2\r\nUPM 459744",null,null,55941,"2023-07-27","Minor","1,2,3,4,5"]
[null,"Infrabel","60103","Namur - Antwerpen",">","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL",2024,2024,4,4,"2024-01-25",45280.34375,"2024-01-25",45280.510416666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 13 - 14 buiten dienst\r\n\r\nR-445866",null,null,60103,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","61071","Namur - Antwerpen",">","NAMUR","RHISNES",2024,2024,4,4,"2024-01-26",45280.958333333336,"2024-01-27",45280.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nUPM 459439",null,null,61071,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","67087","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2024,2024,4,4,"2024-01-26",45280.333333333336,"2024-01-26",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno\r\nUPM 464332",null,null,67087,"2023-07-27","Minor","1,2,3,4,5"]
[null,"Infrabel","49462","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,4,5,"2024-01-26",45280.972222222219,"2024-01-29",45280.194444444445,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 2/6\r\nDossier de concertation validé le 28 octobre 2021\r\nUPM 444980\r\nEn corrélation avec Colt 49461 - UPM 456865",null,null,49462,"2023-12-04","Medium","5,6"]
[null,"Infrabel","61119","Athus - Meuse",">","DINANT","YVOIR",2024,2024,4,4,"2024-01-26",45280.385416666664,"2024-01-26",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 462604",null,null,61119,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","47170","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,4,5,"2024-01-27",45280.958333333336,"2024-01-29",45280.1875,"1d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Electrification 2 x 25 kV\r\nUPM : 466017",null,null,47170,"2023-10-11","Medium","5,6"]
[null,"Infrabel","48866","Namur - Antwerpen",">","WAVRE","OTTIGNIES",2024,2024,4,4,"2024-01-27",45280.333333333336,"2024-01-27",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes+ maintenances infrastructure et contrôles\r\nUPM: 465078",null,null,48866,"2023-08-30","Minor","5,6"]
[null,"Infrabel","57789","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,4,5,"2024-01-27",45280.006944444445,"2024-01-29",45280.1875,"2d, 04:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\nR-431060",null,null,57789,"2023-07-20","Medium","5,6"]
[null,"Infrabel","63677","Erquelinnes - Montzen","< >","MARCHIENNE-ZONE","ERQUELINNES-FRONTIERE",2024,2024,4,5,"2024-01-27",45280.979166666664,"2024-01-29",45280.166666666664,"2d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-LS_SO_L130A_Software_Marchienne-Zone - Erquelinnes\r\nTesten\r\nMee werken niet mogelijk\r\nUPM 466273",null,null,63677,"2023-08-02","Minor","5,6"]
[null,"Infrabel","61503","Namur - Antwerpen","< >","MECHELEN","HAACHT",2024,2024,4,4,"2024-01-27",45280.020833333336,"2024-01-28",45280.25,"2d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossing wissels Muizen Rooster T - L53\r\n\r\nR-444410",null,null,61503,"2023-07-18","Minor","5,6"]
[null,"Infrabel","58758","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,4,5,"2024-01-27",45280.020833333336,"2024-01-29",45280.1875,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-457880\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)",null,null,58758,"2023-07-20","Medium","5,6"]
[null,"Infrabel","68225","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,4,5,"2024-01-27",45280.020833333336,"2024-01-29",45280.180555555555,"3d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"migratie tunnelveiligheidstechnieken antwerpen NZ\r\nR-445910",null,null,68225,"2023-07-18","Minor","5,6"]
[null,"Infrabel","49164","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2024,2024,4,4,"2024-01-27",45280.986111111109,"2024-01-28",45280.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nMini CTL\r\nUPM 457221\r\nCR 2024-219 envoyé le 11/09/2023 - CR validé par AI.51 le 13/09/23 - CR validé par AI. SE le 15/09/23",null,null,49164,"2023-10-10","Medium","5,6"]
[null,"Infrabel","50430","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2024,2024,4,4,"2024-01-27",45280.986111111109,"2024-01-28",45280.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+Visite de la voie B Moustier/Auvelais + maintenance infrastructure + contrôles\r\nUPM: 461990\r\nCR 2024-219 envoyé le 11/09/2023 - Cr validé le 15/09/2023",null,null,50430,"2023-11-17","Medium","5,6"]
[null,"Infrabel","58157","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","MERELBEKE-ROOSTER S",2024,2024,4,5,"2024-01-27",45280.041666666664,"2024-01-29",45280.166666666664,"2d, 03:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y. Oost Driehoek Ledeberg \r\nWE3/3",null,null,58157,"2023-03-03","Medium","5,6"]
[null,"Infrabel","61114","Athus - Meuse",">","JAMBES","LUSTIN",2024,2024,4,4,"2024-01-27",45280.385416666664,"2024-01-27",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 462596",null,null,61114,"2023-08-07","Minor","5,6"]
[null,"Infrabel","61233","Erquelinnes - Montzen",">","BEEZ","SCLAIGNEAUX",2024,2024,4,4,"2024-01-27",45280.354166666664,"2024-01-27",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463093",null,null,61233,"2023-08-07","Minor","5,6"]
[null,"Infrabel","48948","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2024,2024,4,4,"2024-01-27",45280.340277777781,"2024-01-28",45280.659722222219,"2d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles \r\nUPM 466926",null,null,48948,"2023-08-30","Minor","5,6"]
[null,"Infrabel","61074","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2024,2024,4,5,"2024-01-28",45280.958333333336,"2024-01-29",45280.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 3) 6 fois sur l'année\r\nUPM 459459",null,null,61074,"2023-08-09","Minor","1,2,3,4,5"]
[null,"Infrabel","48876","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2024,2024,4,4,"2024-01-28",45280.333333333336,"2024-01-28",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes - maintenances diverses et révisions\r\nUPM : 465094",null,null,48876,"2023-08-30","Minor","5,6"]
[null,"Infrabel","69789","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2024,2024,4,4,"2024-01-28",45280.006944444445,"2024-01-28",45280.229166666664,"1d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Trapkooien Vilvoorde\r\nDemontage nieuwe luifel perron 3-4 voorbereiding\r\n\r\nR-471022",null,null,69789,"2023-07-18","Minor","5,6"]
[null,"Infrabel","50698","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,4,5,"2024-01-28",45280.027777777781,"2024-01-29",45280.1875,"2d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44\r\nUPM 467766\r\nART",null,null,50698,"2023-09-20","Minor","5,6"]
[null,"Infrabel","61115","Athus - Meuse",">","LUSTIN","JAMBES",2024,2024,4,4,"2024-01-28",45280.385416666664,"2024-01-28",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 462297",null,null,61115,"2023-08-09","Minor","5,6"]
[null,"Infrabel","61234","Erquelinnes - Montzen",">","MARCHE-LES-DAMES","ANDENNE",2024,2024,4,4,"2024-01-28",45280.354166666664,"2024-01-28",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM : 463094",null,null,61234,"2023-08-09","Minor","5,6"]
[null,"Infrabel","62813","Athus - Meuse",">","YVOIR","DINANT",2024,2024,5,5,"2024-01-29",45280.958333333336,"2024-02-03",45280.204861111109,"5d, 05:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble\r\nUPM 462733",null,null,62813,"2023-10-05","Minor","1,2,3,4,5"]
[null,"Infrabel","49216","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2024,2024,5,5,"2024-01-29",45280.333333333336,"2024-01-29",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 116 à 121 + faisceau manage\r\nUPM 474846",null,null,49216,"2023-08-30","Minor","1,2,3,4,5"]
[null,"Infrabel","63731","Athus - Meuse",">","BERTRIX","STRAIMONT",2024,2024,5,5,"2024-01-29",45280.333333333336,"2024-01-29",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,63731,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","56610","Erquelinnes - Montzen",">","BRESSOUX","FROIDMONT",2024,2024,5,5,"2024-01-29",45280.333333333336,"2024-01-29",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Cette visite se fait le même lundi que la visite entre Visé-Bas et Frontière NS prévue l'après-midi\r\n- Visite de voie, tunnel et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56610,"2023-08-03","Minor","1,2,3,4,5"]
[null,"Infrabel","47138","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,5,5,"2024-01-29",45280.979166666664,"2024-02-03",45280.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nmassifs caténaires\r\nUPM 468222",null,null,47138,"2023-08-09","Minor","1,2,3,4,5"]
[null,"Infrabel","64214","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,5,5,"2024-01-29",45280.972222222219,"2024-02-03",45280.208333333336,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VIII (geen continue buiten dienst stellingen meer op de sporen IX tem XII)\r\n\r\n(alternatief stappenplan)\r\nR-461857",null,null,64214,"2023-07-24","Minor","1,2,3,4,5"]
[null,"Infrabel","57932","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2024,2024,5,5,"2024-01-29",45280.916666666664,"2024-02-03",45280.21875,"5d, 07:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF CHA24_0026001 \r\nLille Racc RougeBarre – Bif St André : REGE – RVB, RB/RT et RR\r\nUPM 460048",null,null,57932,"2023-07-27","Minor","1,2,3,4,5"]
[null,"Infrabel","57795","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,5,5,"2024-01-29",45280.965277777781,"2024-02-02",45280.1875,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-431061\r\nVernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\n\r\n* R5/R6 in weekend-TLO",null,null,57795,"2023-07-24","Minor","1,2,3,4,5"]
[null,"Infrabel","62958","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2024,2024,5,5,"2024-01-29",45280.965277777781,"2024-02-03",45280.1875,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nZ28.25 : studie nog uit te voeren door I-CBE \r\n+ \r\nFreeswerken\r\n\r\nR-446743",null,null,62958,"2023-07-18","Minor","1,2,3,4,5"]
[null,"Infrabel","61959","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2024,2024,5,5,"2024-01-29",45280.986111111109,"2024-02-03",45280.229166666664,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudswerken volgens onderhoudskalender area CE\r\nOnderhoudszone FBMZ_13/14 in rooster FBMZ tijdens de nachten\r\n\r\nBeschermingsspoor en BVL later te verkrijgen BUV.",null,null,61959,"2023-08-21","Minor","1,2,3,4,5"]
[null,"Infrabel","49368","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2024,2024,5,5,"2024-01-29",45280.993055555555,"2024-02-02",45280.201388888891,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP3 HKM\r\nUPM 465148",null,null,49368,"2023-08-02","Minor","1,2,3,4,5"]
[null,"Infrabel","60127","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2024,2024,5,5,"2024-01-29",45280.993055555555,"2024-02-02",45280.190972222219,"4d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud SIG +onderhoud wissels en overwegen\r\n\r\nR-446106",null,null,60127,"2023-07-18","Minor","1,2,3,4,5"]
[null,"Infrabel","61679","Erquelinnes - Montzen",">","AMAY","RACC.DUMONT-WAUTHIER",2024,2024,5,5,"2024-01-29",45280.375,"2024-02-02",45280.625,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement pièces caténaire",null,null,61679,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","56611","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2024,2024,5,5,"2024-01-29",45280.5,"2024-01-29",45280.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Cette visite se fait le même lundi que la visite entre Froidmont et Bressoux prévue l'avant-midi\r\n- Visite de voie, PN et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56611,"2023-08-03","Minor","1,2,3,4,5"]
[null,"Infrabel","65337","Namur - Antwerpen",">","Y.MELLE-WEST","MERELBEKE-ROOSTER S",2024,2024,5,5,"2024-01-29",45280.395833333336,"2024-01-30",45280.645833333336,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"reservatie onderhoud\r\ndagdienst zone 1\r\nL50E SP B Y Melle West AW02BT niet inbegrepen tot inrit Merelbeke rooster S AW01AS niet inbegrepen\r\nBVL: 29164\r\nR-464521",null,null,65337,"2023-07-24","Minor","1,2,3,4,5"]
[null,"Infrabel","61122","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2024,2024,5,5,"2024-01-29",45280.34375,"2024-01-29",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA\r\nUPM 463241",null,null,61122,"2023-08-09","Minor","1,2,3,4,5"]
[null,"Infrabel","65831","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","GENT-DAMPOORT",2024,2024,5,5,"2024-01-30",45280.027777777781,"2024-02-03",45280.184027777781,"5d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS L2-IL_NW_P025_P026_L59_Y Sint Bernadettestraat - Berchem_ETCS\r\nDownload, meewerken mogelijk\r\nR-469299",null,null,65831,"2023-08-08","Minor","1,2,3,4,5"]
[null,"Infrabel","64637","Lille - Antwerpen","< >","GENT-DAMPOORT","LOKEREN",2024,2024,5,5,"2024-01-30",45280.020833333336,"2024-02-03",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nR-465646",null,null,64637,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","64633","Lille - Antwerpen","< >","SINT-NIKLAAS","Y.MELSELE",2024,2024,5,5,"2024-01-30",45280.013888888891,"2024-02-03",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud\r\nR-465666\r\n\r\n*perron II-V inbegrepen. \r\n*SP I + SP A  niet inbegrepen om doorrit naar L54 toe te laten",null,null,64633,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","64654","Lille - Antwerpen","< >","LOKEREN","SINT-NIKLAAS",2024,2024,5,5,"2024-01-30",45280.013888888891,"2024-02-03",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\n* doorrit ultrasoon N13/14\r\nR-465158",null,null,64654,"2023-07-24","Minor","1,2,3,4,5"]
[null,"Infrabel","63732","Athus - Meuse",">","STRAIMONT","BERTRIX",2024,2024,5,5,"2024-01-30",45280.375,"2024-01-30",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,63732,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","69259","Athus - Meuse",">","STOCKEM-NORD","ARLON",2024,2024,5,5,"2024-01-30",45280.361111111109,"2024-01-30",45280.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69259,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","56614","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,5,5,"2024-01-30",45280.395833333336,"2024-01-30",45280.611111111109,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Visite de voie, PN et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56614,"2023-08-03","Minor","1,2,3,4,5"]
[null,"Infrabel","61123","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2024,2024,5,5,"2024-01-30",45280.34375,"2024-01-30",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB\r\nUPM 463243",null,null,61123,"2023-08-09","Minor","1,2,3,4,5"]
[null,"Infrabel","54392","Athus - Meuse",">","SIGNEULX","HALANZY",2024,2024,5,5,"2024-01-31",45280.375,"2024-01-31",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,54392,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","69258","Athus - Meuse",">","HABAY","STOCKEM-NORD",2024,2024,5,5,"2024-01-31",45280.375,"2024-01-31",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69258,"2023-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","65338","Namur - Antwerpen","< >","MERELBEKE-ROOSTER S","Y.OOST DRIEHOEK LEDEBERG",2024,2024,5,5,"2024-01-31",45280.395833333336,"2024-02-02",45280.645833333336,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"reservatie onderhoud\r\ndagdienst zone 2\r\nL50E SP A Merelbeke rooster S sein EX-S.6 tot Y Oost Driehoek Ledeberg 10AR niet inbegrepen\r\nL50E SP B Merelbeke rooster S sein F-S.6 tot Y Oost Driehoek Ledeberg 03XR niet inbegrepen\r\nBVL: niet mogelijk overdag\r\n",null,null,65338,"2023-07-24","Minor","1,2,3,4,5"]
[null,"Infrabel","65976","Athus - Meuse",">","DINANT","Y.NEFFE",2024,2024,5,5,"2024-01-31",45280.34375,"2024-01-31",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites\r\nUPM 463240",null,null,65976,"2023-08-09","Minor","1,2,3,4,5"]
[null,"Infrabel","62001","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,5,5,"2024-02-01",45280.375,"2024-02-01",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,62001,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","61124","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2024,2024,5,5,"2024-02-01",45280.388888888891,"2024-02-01",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,61124,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","59191","Namur - Antwerpen","< >","WONDELGEM","EEKLO",2024,2024,5,5,"2024-02-02",45280.958333333336,"2024-02-04",45280.180555555555,"1d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen houtstukken brug Schoonstraat Kp 15 078\r\nR-433327",null,null,59191,"2023-07-24","Medium","5,6"]
[null,"Infrabel","49260","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,5,6,"2024-02-02",45280.979166666664,"2024-02-05",45280.1875,"2d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR2024-208 V2\r\n\r\nWE CTL RER Ottignies-Y.LLN\r\nUPM 464550\r\nEn accord avec I-B et SNCB : Suppression de la CTL pour un SAVU.\r\n\r\nDu ve 02/02/2024 23h30 au lu 05/02/2024 04h30 (we S05/2024 en continu)  :\r\nSAVU VA HS continu L161 Ottignies compris – Y.LLN\r\net",null,null,49260,"2023-12-06","Minor","5,6"]
[null,"Infrabel","47357","Athus - Meuse","< >","LEIGNON","HAVERSIN-GARAGE",2024,2024,5,6,"2024-02-02",45280.96875,"2024-02-05",45280.180555555555,"2d, 05:05h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3:\r\nTravaux de traversée de voie + Massification OA\r\nUPM 462259",null,null,47357,"2023-08-31","Medium","5,6"]
[null,"Infrabel","63671","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2024,2024,5,6,"2024-02-02",45280.996527777781,"2024-02-05",45280.180555555555,"2d, 04:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"werken antwerpen-zuid\r\n\r\nR-446107",null,null,63671,"2023-07-25","Medium","5,6"]
[null,"Infrabel","61997","Athus - Meuse",">","HALANZY","Y.AUBANGE",2024,2024,5,5,"2024-02-02",45280.375,"2024-02-02",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,61997,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","61125","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2024,2024,5,5,"2024-02-02",45280.388888888891,"2024-02-02",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,61125,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","47171","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,5,6,"2024-02-03",45280.958333333336,"2024-02-05",45280.1875,"1d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Electrification 2 x 25 kV\r\nUPM : 466018",null,null,47171,"2023-10-11","Medium","5,6"]
[null,"Infrabel","57788","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,5,6,"2024-02-03",45280.006944444445,"2024-02-05",45280.1875,"2d, 04:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\nR-431062",null,null,57788,"2023-07-24","Medium","5,6"]
[null,"Infrabel","58191","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2024,2024,5,6,"2024-02-03",45280.020833333336,"2024-02-05",45280.166666666664,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Trapkooien Vilvoorde\r\nDemontage nieuwe luifel perron 3-4\r\n\r\nR-446133",null,null,58191,"2023-07-19","Medium","5,6"]
[null,"Infrabel","68240","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,5,6,"2024-02-03",45280.020833333336,"2024-02-05",45280.180555555555,"3d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"migratie tunnelveiligheidstechnieken antwerpen NZ\r\n\r\nR-446137",null,null,68240,"2023-07-19","Minor","5,6"]
[null,"Infrabel","56910","Lille - Charleroi","< >","GHLIN","MONS",2024,2024,5,5,"2024-02-03",45280.993055555555,"2024-02-04",45280.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim\r\nUPM 463485",null,null,56910,"2023-07-27","Minor","5,6"]
[null,"Infrabel","63733","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,5,5,"2024-02-03",45280.375,"2024-02-03",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie A\r\nVisite voie A",null,null,63733,"2023-08-29","Minor","5,6"]
[null,"Infrabel","60790","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2024,2024,5,5,"2024-02-03",45280.263888888891,"2024-02-04",45280.708333333336,"1d, 10:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z07.52\r\nUPM 456915\r\nEn corrélation avec Colt 49776 - 49461 / UPM 445060 - 456865",null,null,60790,"2023-07-05","Medium","5,6"]
[null,"Infrabel","63734","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2024,2024,5,5,"2024-02-04",45280.375,"2024-02-04",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie B\r\nVisite voie B",null,null,63734,"2023-08-29","Minor","5,6"]
[null,"Infrabel","62814","Athus - Meuse",">","YVOIR","DINANT",2024,2024,6,6,"2024-02-05",45280.958333333336,"2024-02-10",45280.204861111109,"5d, 05:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble\r\nUPM 462797",null,null,62814,"2023-10-05","Minor","1,2,3,4,5"]
[null,"Infrabel","60807","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2024,2024,6,6,"2024-02-05",45280.333333333336,"2024-02-09",45280.583333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z07.52\r\nJOUR",null,null,60807,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","58898","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2024,2024,6,6,"2024-02-05",45280.951388888891,"2024-02-09",45280.21875,"4d, 06:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing sporen.\r\nvoorbereidende werken massificatie met werken Waver-Ottignies\r\n+\r\nonderhoud\r\n\r\nR-444422",null,null,58898,"2023-08-16","Minor","1,2,3,4,5"]
[null,"Infrabel","64215","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,6,6,"2024-02-05",45280.972222222219,"2024-02-10",45280.208333333336,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)",null,null,64215,"2023-01-10","Minor","1,2,3,4,5"]
[null,"Infrabel","62977","Namur - Antwerpen","< >","MECHELEN","Y.LEUVEN-BUNDEL M",2024,2024,6,6,"2024-02-05",45280.972222222219,"2024-02-10",45280.208333333336,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nZ04.25 : studie nog uit te voeren door I-CBE\r\n\r\nR-447421",null,null,62977,"2023-08-16","Minor","1,2,3,4,5"]
[null,"Infrabel","49495","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","MARCHIENNE-ZONE",2024,2024,6,6,"2024-02-05",45280.9375,"2024-02-10",45280.173611111109,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Livraison des AS Y LLS, à l'aide du train Kirow\r\n+ Travaux voie A signalisation\r\nUPM 442502",null,null,49495,"2023-09-12","Minor","1,2,3,4,5"]
[null,"Infrabel","57933","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2024,2024,6,6,"2024-02-05",45280.916666666664,"2024-02-10",45280.21875,"5d, 07:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF CHA24_0026001 \r\nLille Racc RougeBarre – Bif St André : REGE – RVB, RB/RT et RR\r\nUPM 460050",null,null,57933,"2023-09-01","Minor","1,2,3,4,5"]
[null,"Infrabel","59403","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2024,2024,6,6,"2024-02-05",45280.965277777781,"2024-02-09",45280.215277777781,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Traverses et Ballast \r\nC75 entre 12.100 et 19.285\r\nPréparations\r\nUPM: 465182",null,null,59403,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","47567","Lille - Charleroi",">","MONS","JURBISE",2024,2024,6,15,"2024-02-05",45280.25,"2024-04-14",45280.958333333336,"70d, 17:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification - Phases 1 et 2 - 2024\r\nUPM 459969",null,null,47567,"2023-09-01","High","1,2,3,4,5,6,7"]
[null,"Infrabel","61046","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,6,6,"2024-02-05",45280.989583333336,"2024-02-10",45280.197916666664,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service\r\nUPM 465745",null,null,61046,"2023-09-28","Minor","1,2,3,4,5"]
[null,"Infrabel","60215","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,6,6,"2024-02-05",45280.947916666664,"2024-02-10",45280.204861111109,"5d, 06:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud wissels en sporen te ANtwerpen Schijnpoort inrit bundel F inclusief bundelkoppen F, D\r\n\r\nR-446466",null,null,60215,"2023-08-16","Minor","1,2,3,4,5"]
[null,"Infrabel","66428","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2024,2024,6,6,"2024-02-05",45280.378472222219,"2024-02-05",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,66428,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","66228","Athus - Meuse",">","BEAURAING","HOUYET",2024,2024,6,6,"2024-02-05",45280.388888888891,"2024-02-05",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,66228,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","57796","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,6,6,"2024-02-06",45280.006944444445,"2024-02-09",45280.1875,"4d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-431063\r\nVernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\n\r\n*R5/R6 in weekend TLO",null,null,57796,"2023-09-13","Minor","1,2,3,4,5"]
[null,"Infrabel","63370","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2024,2024,6,6,"2024-02-06",45280.375,"2024-02-06",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-447423",null,null,63370,"2023-08-21","Minor","1,2,3,4,5"]
[null,"Infrabel","66425","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2024,2024,6,6,"2024-02-06",45280.378472222219,"2024-02-06",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,66425,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","66229","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,6,6,"2024-02-06",45280.388888888891,"2024-02-06",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,66229,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","66432","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2024,2024,6,6,"2024-02-07",45280.375,"2024-02-07",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A\r\nEntretien / maintenance voie A",null,null,66432,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","63393","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,6,6,"2024-02-07",45280.375,"2024-02-07",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-447466",null,null,63393,"2023-08-21","Minor","1,2,3,4,5"]
[null,"Infrabel","63739","Athus - Meuse",">","VONECHE","GEDINNE",2024,2024,6,6,"2024-02-08",45280.333333333336,"2024-02-08",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,63739,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","63737","Athus - Meuse",">","VIRTON","SIGNEULX",2024,2024,6,6,"2024-02-08",45280.375,"2024-02-08",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,63737,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","63416","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,6,6,"2024-02-08",45280.375,"2024-02-08",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-447468",null,null,63416,"2023-08-21","Minor","1,2,3,4,5"]
[null,"Infrabel","48246","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,6,7,"2024-02-09",45280.958333333336,"2024-02-12",45280.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2. 51  P4+\r\n+ Travaux Signalisation PN 107 108 109 114\r\nUPM 442547",null,null,48246,"2023-09-12","Medium","5,6"]
[null,"Infrabel","63740","Athus - Meuse",">","GEDINNE","VONECHE",2024,2024,6,6,"2024-02-09",45280.333333333336,"2024-02-09",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,63740,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","47438","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2024,2024,6,8,"2024-02-09",45280.96875,"2024-02-19",45280.229166666664,"9d, 06:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Traverses et Ballast \r\nC75 entre 12.100 et 19.285\r\n+ PNs 16, 31 et 32\r\nUPM : 465184",null,null,47438,"2023-10-02","High","1,2,3,4,5,6,7"]
[null,"Infrabel","57931","Namur - Antwerpen","< >","FLEURUS","AUVELAIS",2024,2024,6,8,"2024-02-09",45280.96875,"2024-02-19",45280.229166666664,"9d, 06:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance L147\r\nUPM 444802",null,null,57931,"2023-09-12","High","1,2,3,4,5,6,7"]
[null,"Infrabel","63738","Athus - Meuse",">","SIGNEULX","VIRTON",2024,2024,6,6,"2024-02-09",45280.375,"2024-02-09",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,63738,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","63434","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,6,6,"2024-02-09",45280.375,"2024-02-09",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-447475",null,null,63434,"2023-08-21","Minor","1,2,3,4,5"]
[null,"Infrabel","66245","Athus - Meuse",">","VONECHE","BEAURAING",2024,2024,6,6,"2024-02-10",45280.333333333336,"2024-02-10",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66245,"2023-09-19","Minor","5,6"]
[null,"Infrabel","63161","Namur - Antwerpen","< >","MOUSTIER-GARAGE","AUVELAIS",2024,2024,6,7,"2024-02-10",45280.986111111109,"2024-02-12",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nmassifs caténaires\r\n+ Savu Entretien de voie\r\nUPM 467258\r\nCR 2024-219 envoyé le 11/09/2023 - CR validé le 15/09/2023",null,null,63161,"2023-09-28","Minor","5,6"]
[null,"Infrabel","59048","Namur - Antwerpen","< >","Y.HOLLAND","ANTWERPEN-NOORDERDOKKEN",2024,2024,6,6,"2024-02-10",45280.25,"2024-02-11",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"oosterweelverbinding R0\r\n\r\nR-447640",null,null,59048,"2023-08-23","Medium","5,6"]
[null,"Infrabel","58208","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-NEKKERSPOEL",2024,2024,6,7,"2024-02-10",45280.25,"2024-02-12",45280.201388888891,"2d, 22:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"masterplan Mechelen\r\n\r\nR-447666",null,null,58208,"2023-08-21","Medium","5,6"]
[null,"Infrabel","59012","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ANTWERPEN-NOORD-INRIT C1",2024,2024,6,7,"2024-02-10",45280.25,"2024-02-12",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Oude Landen\r\nproject 304\r\n\r\nR-444431",null,null,59012,"2023-10-25","Medium","5,6"]
[null,"Infrabel","53185","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2024,2024,6,8,"2024-02-10",45280.25,"2024-02-19",45280.166666666664,"9d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-433626\r\nbuitenwerken  ETCS - Mechelen-Londerzeel\r\n9 dagen TLO\r\nETCS L2-IL_NO_P033_L53_Dendermonde - Mechelen_ETCS (Londerzeel - Dendermonde= meewerken op 58438)\r\n\r\n+\r\nonderhoud EDW\r\n+\r\nMP FM\r\n\r\nMeewerken mogelijk zie mail Evelyn\r\n\r\n* Starten op zaterd",null,null,53185,"2023-09-13","High","1,2,3,4,5,6,7"]
[null,"Infrabel","49889","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2024,2024,6,8,"2024-02-10",45280.000694444447,"2024-02-19",45280.208333333336,"9d, 04:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing sporen.\r\n\r\nBTS op deze werken ==> zie Colt ID 49890 (+4')\r\n+\r\nOnderhoud\r\nZ01.25 : studie nog uit te voeren door I-CBE  colt 62898\r\n\r\nR-444569",null,null,49889,"2023-08-23","High","1,2,3,4,5,6,7"]
[null,"Infrabel","49170","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2024,2024,6,6,"2024-02-10",45280.326388888891,"2024-02-10",45280.666666666664,"1d, 08:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A + maintenance infrastructure + contrôles\r\nUPM : 461987",null,null,49170,"2023-12-13","Minor","5,6"]
[null,"Infrabel","66246","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,6,6,"2024-02-11",45280.333333333336,"2024-02-11",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,66246,"2023-09-19","Minor","5,6"]
[null,"Infrabel","71030","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2024,2024,6,6,"2024-02-11",45280.333333333336,"2024-02-11",45280.652777777781,"1d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie B + maintenance infrastructure + contrôles\r\nTCR 486510",null,null,71030,"2023-12-18","Minor","5,6"]
[null,"Infrabel","64855","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2024,2024,6,6,"2024-02-11",45280.027777777781,"2024-02-11",45280.229166666664,"1d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465966\r\nreservatie onderhoud",null,null,64855,"2023-09-13","Minor","5,6"]
[null,"Infrabel","64859","Lille - Antwerpen","< >","Y.MELSELE","LOKEREN",2024,2024,6,6,"2024-02-11",45280.027777777781,"2024-02-11",45280.215277777781,"1d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465985\r\nreservatie onderhoud",null,null,64859,"2023-09-13","Minor","5,6"]
[null,"Infrabel","66434","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2024,2024,6,6,"2024-02-11",45280.375,"2024-02-11",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B\r\nEntretien / maintenance voie B",null,null,66434,"2023-09-19","Minor","5,6"]
[null,"Infrabel","62815","Athus - Meuse",">","YVOIR","DINANT",2024,2024,7,7,"2024-02-12",45280.958333333336,"2024-02-17",45280.204861111109,"5d, 05:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble\r\nUPM 462798",null,null,62815,"2023-10-05","Minor","1,2,3,4,5"]
[null,"Infrabel","66247","Athus - Meuse",">","GEDINNE","PALISEUL",2024,2024,7,7,"2024-02-12",45280.333333333336,"2024-02-12",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66247,"2023-09-20","Minor","1,2,3,4,5"]
[null,"Infrabel","47140","Namur - Antwerpen",">","JEMEPPE-SUR-SAMBRE-MARCHANDISE","AUVELAIS",2024,2024,7,7,"2024-02-12",45280.979166666664,"2024-02-17",45280.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nmassifs caténaires\r\nUPM 468227",null,null,47140,"2023-09-18","Minor","1,2,3,4,5"]
[null,"Infrabel","50633","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,7,7,"2024-02-12",45280.979166666664,"2024-02-17",45280.1875,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris R1 à R5\r\nId 54602 13/02/2024 - 27/02/2024\r\nTravaux Possible Map Extra - New 2004\r\nCAPACITY BASED PLANNING\r\nUPM 474868",null,null,50633,"2023-09-28","Minor","1,2,3,4,5"]
[null,"Infrabel","57057","Namur - Antwerpen","< >","OTTIGNIES","LODELINSART",2024,2024,7,7,"2024-02-12",45280.972222222219,"2024-02-16",45280.197916666664,"4d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement complet des Passages à niveau\r\nUPM : 460355",null,null,57057,"2023-09-12","Minor","1,2,3,4,5"]
[null,"Infrabel","64216","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,7,7,"2024-02-12",45280.972222222219,"2024-02-17",45280.208333333336,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-461874\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)",null,null,64216,"2023-09-13","Minor","1,2,3,4,5"]
[null,"Infrabel","57934","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2024,2024,7,7,"2024-02-12",45280.916666666664,"2024-02-17",45280.21875,"5d, 07:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF CHA24_0026001 \r\nLille Racc RougeBarre – Bif St André : REGE – RVB, RB/RT et RR\r\n+ Tirage de cable\r\nUPM 460059",null,null,57934,"2023-09-01","Minor","1,2,3,4,5"]
[null,"Infrabel","56283","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2024,2024,7,7,"2024-02-12",45280.965277777781,"2024-02-17",45280.229166666664,"5d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.3.53 en P3 HKV\r\n+ Maintenance Z9.52\r\nUPM 462934",null,null,56283,"2023-09-01","Minor","1,2,3,4,5"]
[null,"Infrabel","50715","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,7,7,"2024-02-12",45280.986111111109,"2024-02-17",45280.1875,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44\r\nUPM 467770",null,null,50715,"2023-09-28","Minor","1,2,3,4,5"]
[null,"Infrabel","55960","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2024,2024,7,7,"2024-02-12",45280.996527777781,"2024-02-16",45280.208333333336,"4d, 05:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien manuel et mécanisés des AW Bressoux / Visé-Bas / Longchamps + Grill et PN / \r\nEntretien manuel et mécanisés de la voie courante\r\n+ Entretien des liaisons + ligne + composants",null,null,55960,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","66058","Athus - Meuse",">","NAMUR","JAMBES",2024,2024,7,7,"2024-02-12",45280.388888888891,"2024-02-12",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463250",null,null,66058,"2023-09-18","Minor","1,2,3,4,5"]
[null,"Infrabel","65943","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2024,2024,7,7,"2024-02-12",45280.409722222219,"2024-02-12",45280.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65943,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","65406","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2024,2024,7,7,"2024-02-12",45280.381944444445,"2024-02-12",45280.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41 (à répéter toutes les 6 semaines, le lundi)",null,null,65406,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","66248","Athus - Meuse",">","PALISEUL","GEDINNE",2024,2024,7,7,"2024-02-13",45280.333333333336,"2024-02-13",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66248,"2023-09-20","Minor","1,2,3,4,5"]
[null,"Infrabel","58251","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,7,7,"2024-02-13",45280.006944444445,"2024-02-17",45280.1875,"5d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-431065\r\nVernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497",null,null,58251,"2023-09-13","Minor","1,2,3,4,5"]
[null,"Infrabel","65825","Namur - Antwerpen","< >","Y.NOORD DRIEHOEK LEDEBERG","WONDELGEM",2024,2024,7,7,"2024-02-13",45280.027777777781,"2024-02-17",45280.180555555555,"5d, 03:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-466565\r\nETCS L2-IL_NW_P024_L58_Merelbeke - Y Sint Bernadettestraat_ETCS\r\nBuitenwerken, meewerken mogelijk\r\nFGDM IN\r\nL58 tot Y Oost Drieheok Ledeberg vrij\r\nL58/1 tot Y West driehoek Ledeberg vrij\r\nL59 SP A tot Y Sint Bernadette vrij\r\nL59 SP B tot roost",null,null,65825,"2023-09-13","Minor","1,2,3,4,5"]
[null,"Infrabel","60119","Namur - Antwerpen","< >","ANTWERPEN-NOORDERDOKKEN","Y.HOLLAND",2024,2024,7,7,"2024-02-13",45280.020833333336,"2024-02-17",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderheid SIG Y luchtbal en onderhoud wissel Y Antwerpen-luchtbal\r\n\r\nR-447730",null,null,60119,"2023-08-30","Minor","1,2,3,4,5"]
[null,"Infrabel","65863","Lille - Antwerpen","< >","DEINZE","WAREGEM",2024,2024,7,7,"2024-02-13",45280.013888888891,"2024-02-17",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-65863\r\nETCS L2-IL_NW_P014_05_L75_Deinze - Waregem_IL\r\nOpkuis, meewerken mogelijk",null,null,65863,"2023-09-13","Minor","1,2,3,4,5"]
[null,"Infrabel","65992","Athus - Meuse",">","LUSTIN","YVOIR",2024,2024,7,7,"2024-02-13",45280.375,"2024-02-13",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463251",null,null,65992,"2023-09-18","Minor","1,2,3,4,5"]
[null,"Infrabel","63735","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,7,7,"2024-02-14",45280.375,"2024-02-14",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,63735,"2023-09-20","Minor","1,2,3,4,5"]
[null,"Infrabel","66007","Athus - Meuse",">","YVOIR","LUSTIN",2024,2024,7,7,"2024-02-14",45280.375,"2024-02-14",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463252",null,null,66007,"2023-09-18","Minor","1,2,3,4,5"]
[null,"Infrabel","65919","Athus - Meuse",">","LAVAUX","MARBEHAN",2024,2024,7,7,"2024-02-14",45280.361111111109,"2024-02-14",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65919,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","60088","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,7,7,"2024-02-14",45280.395833333336,"2024-02-14",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn\r\n\r\nR-448600",null,null,60088,"2023-09-01","Minor","1,2,3,4,5"]
[null,"Infrabel","66249","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,7,7,"2024-02-15",45280.333333333336,"2024-02-15",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66249,"2023-09-20","Minor","1,2,3,4,5"]
[null,"Infrabel","66085","Athus - Meuse",">","YVOIR","DINANT",2024,2024,7,7,"2024-02-15",45280.385416666664,"2024-02-15",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463253",null,null,66085,"2023-09-18","Minor","1,2,3,4,5"]
[null,"Infrabel","65911","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2024,2024,7,7,"2024-02-15",45280.368055555555,"2024-02-15",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65911,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","63736","Athus - Meuse",">","HALANZY","Y.AUBANGE",2024,2024,7,7,"2024-02-15",45280.375,"2024-02-15",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,63736,"2023-09-20","Minor","1,2,3,4,5"]
[null,"Infrabel","60104","Namur - Antwerpen","< >","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL",2024,2024,7,7,"2024-02-15",45280.34375,"2024-02-15",45280.510416666664,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal (schouwen-metingen-smeren-kleine herstellingen)\r\n\r\nperronsporen 11-12 buiten dienst\r\n\r\nR-448602",null,null,60104,"2023-11-14","Minor","1,2,3,4,5"]
[null,"Infrabel","49708","Namur - Antwerpen",">","RHISNES","GEMBLOUX",2024,2024,7,8,"2024-02-16",45280.958333333336,"2024-02-19",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"réélectrification\r\n + Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles\r\nUPM 466823",null,null,49708,"2023-09-18","Minor","5,6"]
[null,"Infrabel","66250","Athus - Meuse",">","BERTRIX","PALISEUL",2024,2024,7,7,"2024-02-16",45280.333333333336,"2024-02-16",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66250,"2023-09-20","Minor","1,2,3,4,5"]
[null,"Infrabel","60085","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,7,8,"2024-02-16",45280.979166666664,"2024-02-19",45280.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"onderhoud wissels Antwerpen-centraal\r\n\r\nvolledig verdiep +1 (perronsporen 1-6)\r\n\r\nsamen met werkaanvraag L12\r\n\r\nR-448620",null,null,60085,"2023-09-28","Medium","5,6"]
[null,"Infrabel","47358","Athus - Meuse","< >","LEIGNON","HAVERSIN-GARAGE",2024,2024,7,8,"2024-02-16",45280.96875,"2024-02-19",45280.180555555555,"2d, 05:05h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3:\r\nTravaux de traversée de voie + Massification OA\r\nUPM 462266",null,null,47358,"2023-09-18","Medium","5,6"]
[null,"Infrabel","66100","Athus - Meuse",">","DINANT","YVOIR",2024,2024,7,7,"2024-02-16",45280.385416666664,"2024-02-16",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM  463254",null,null,66100,"2023-09-18","Minor","1,2,3,4,5"]
[null,"Infrabel","65903","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2024,2024,7,7,"2024-02-16",45280.368055555555,"2024-02-16",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65903,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","66873","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,7,7,"2024-02-16",45280.375,"2024-02-16",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,66873,"2023-09-20","Minor","1,2,3,4,5"]
[null,"Infrabel","47173","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,7,8,"2024-02-17",45280.958333333336,"2024-02-19",45280.1875,"1d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Electrification 2 x 25 kV\r\nUPM : 466021",null,null,47173,"2023-09-20","Medium","5,6"]
[null,"Infrabel","70994","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-DIJKSTRAAT",2024,2024,7,8,"2024-02-17",45280.006944444445,"2024-02-19",45280.166666666664,"2d, 03:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"MP Mechelen\r\nTer vervanging van WE37 2023\r\nCR-2024-169\r\n\r\nUPM 476998",null,null,70994,"2023-11-07","Medium","5,6"]
[null,"Infrabel","57542","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2024,2024,7,8,"2024-02-17",45280.013888888891,"2024-02-19",45280.166666666664,"2d, 03:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-460406\r\nBuitenwerken\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL",null,null,57542,"2023-09-13","Medium","5,6"]
[null,"Infrabel","50620","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,7,8,"2024-02-17",45280.996527777781,"2024-02-19",45280.222222222219,"2d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN\r\nUPM 474865",null,null,50620,"2023-09-28","Minor","5,6"]
[null,"Infrabel","66024","Athus - Meuse",">","JAMBES","LUSTIN",2024,2024,7,7,"2024-02-17",45280.385416666664,"2024-02-17",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463255",null,null,66024,"2023-09-18","Minor","5,6"]
[null,"Infrabel","65935","Athus - Meuse",">","ARLON","Y.AUTELBAS",2024,2024,7,7,"2024-02-17",45280.361111111109,"2024-02-17",45280.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65935,"2023-09-19","Minor","5,6"]
[null,"Infrabel","48897","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2024,2024,7,7,"2024-02-18",45280.333333333336,"2024-02-18",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR2024-209 \r\nVisite de voie + maintenance infrastructure + contrôles\r\nOttignies gare  voie 1 à 5 en alternance\r\nUPM 467716",null,null,48897,"2023-11-08","Minor","5,6"]
[null,"Infrabel","64856","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2024,2024,7,7,"2024-02-18",45280.027777777781,"2024-02-18",45280.229166666664,"1d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465979\r\nreservatie onderhoud",null,null,64856,"2023-09-13","Minor","5,6"]
[null,"Infrabel","64860","Lille - Antwerpen","< >","Y.MELSELE","LOKEREN",2024,2024,7,7,"2024-02-18",45280.027777777781,"2024-02-18",45280.215277777781,"1d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465986\r\nreservatie onderhoud",null,null,64860,"2023-09-13","Minor","5,6"]
[null,"Infrabel","62589","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2024,2024,7,7,"2024-02-18",45280.25,"2024-02-18",45280.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TOS 2222: Onderhoud wissels Y Liersesteenweg , Y-Krijgsbaan en Y-Zuid Groenenhoek.\r\n\r\nR-449001",null,null,62589,"2023-09-01","Minor","5,6"]
[null,"Infrabel","66040","Athus - Meuse",">","LUSTIN","JAMBES",2024,2024,7,7,"2024-02-18",45280.385416666664,"2024-02-18",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463256",null,null,66040,"2023-09-18","Minor","5,6"]
[null,"Infrabel","65927","Athus - Meuse",">","MARBEHAN","HABAY",2024,2024,7,7,"2024-02-18",45280.375,"2024-02-18",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65927,"2023-09-19","Minor","5,6"]
[null,"Infrabel","63994","Lille - ZeeBrugge","< >","BRUGGE","LICHTERVELDE",2024,2024,8,8,"2024-02-19",45280.958333333336,"2024-02-24",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-450641\r\nOnderhoud\r\nFR SP VII+VIII inbegrepen\r\nFLC SP III-IV-V inbegrepen\r\nL73 FLC tot Diksmuide inbegrepen",null,null,63994,"2023-09-13","Minor","1,2,3,4,5"]
[null,"Infrabel","64589","Namur - Antwerpen","< >","EEKLO","GENT-DAMPOORT",2024,2024,8,8,"2024-02-19",45280.958333333336,"2024-02-24",45280.1875,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-464096\r\nOnderhoud\r\nFGDM niet IN.",null,null,64589,"2023-09-13","Minor","1,2,3,4,5"]
[null,"Infrabel","66413","Athus - Meuse",">","BERTRIX","STRAIMONT",2024,2024,8,8,"2024-02-19",45280.333333333336,"2024-02-19",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,66413,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","50578","Namur - Antwerpen",">","Y.FLAWINNE","MOUSTIER-GARAGE",2024,2024,8,8,"2024-02-19",45280.979166666664,"2024-02-23",45280.208333333336,"4d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie\r\n+ Réélectrification\r\nUPM 467327",null,null,50578,"2023-11-17","Minor","1,2,3,4,5"]
[null,"Infrabel","59974","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2024,2024,8,8,"2024-02-19",45280.951388888891,"2024-02-23",45280.21875,"4d, 06:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing sporen.\r\n\r\nvoorbereidende werken massificatie met werken Waver-Ottignies\r\n\r\n+\r\nonderhoud\r\n\r\nR-444571",null,null,59974,"2023-08-30","Minor","1,2,3,4,5"]
[null,"Infrabel","63262","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2024,2024,8,8,"2024-02-19",45280.951388888891,"2024-02-24",45280.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-468406\r\nBuitenwerken, meewerken mogelijk, CTL spoor A+B\r\nIL for ETCS_IL-SML_NO_L53_Mechelen - Londerzeel",null,null,63262,"2023-09-13","Minor","1,2,3,4,5"]
[null,"Infrabel","59404","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2024,2024,8,8,"2024-02-19",45280.965277777781,"2024-02-24",45280.215277777781,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Traverses et Ballast \r\nC75  entre 12.100 et 19.285\r\nFinitions\r\nUPM : 465188",null,null,59404,"2023-09-28","Minor","1,2,3,4,5"]
[null,"Infrabel","61047","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,8,8,"2024-02-19",45280.989583333336,"2024-02-24",45280.197916666664,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service\r\nUPM 465748",null,null,61047,"2023-09-28","Minor","1,2,3,4,5"]
[null,"Infrabel","60808","Lille - Charleroi","< >","MANAGE","LUTTRE",2024,2024,8,8,"2024-02-19",45280.375,"2024-02-23",45280.625,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre : Phase 1-2024\r\nCTL L117 de jour en semaine\r\nDossier de concertation validé le 28 octobre 2021\r\n+ Maintenance Z8.52",null,null,60808,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","66206","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2024,2024,8,8,"2024-02-19",45280.34375,"2024-02-19",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA\r\nUPM 463258",null,null,66206,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","52990","Erquelinnes - Montzen","< >","Y.NORD","ERQUELINNES-FRONTIERE",2024,2024,8,8,"2024-02-19",45280.923611111109,"2024-02-23",45280.173611111109,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires caténaire (Beton+poteaux)\r\n+ Maintenance Z2. 51  P3 HKV\r\n+ Travaux voie A signalisation\r\nTCR 466731",null,null,52990,"2023-09-12","Minor","1,2,3,4,5"]
[null,"Infrabel","64345","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,8,8,"2024-02-19",45280.923611111109,"2024-02-24",45280.208333333336,"5d, 06:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails , ballast...",null,null,64345,"2023-02-27","Minor","1,2,3,4,5"]
[null,"Infrabel","66417","Athus - Meuse",">","STRAIMONT","BERTRIX",2024,2024,8,8,"2024-02-20",45280.375,"2024-02-20",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,66417,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","66207","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2024,2024,8,8,"2024-02-20",45280.34375,"2024-02-20",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,66207,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","65977","Athus - Meuse",">","DINANT","Y.NEFFE",2024,2024,8,8,"2024-02-21",45280.34375,"2024-02-21",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites\r\nUPM 463257",null,null,65977,"2023-09-25","Minor","1,2,3,4,5"]
[null,"Infrabel","66208","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2024,2024,8,8,"2024-02-22",45280.388888888891,"2024-02-22",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,66208,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","64372","Namur - Antwerpen",">","NAMUR","RHISNES",2024,2024,8,8,"2024-02-23",45280.958333333336,"2024-02-24",45280.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nUPM 459440",null,null,64372,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","49777","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,8,9,"2024-02-23",45280.972222222219,"2024-02-26",45280.194444444445,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 4/6\r\nDossier de concertation validé le 28 octobre 2021\r\nUPM 445082\r\nEn corrélation avec colt 49461 - UPM 456865\r\nART",null,null,49777,"2023-10-10","Medium","5,6"]
[null,"Infrabel","66209","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2024,2024,8,8,"2024-02-23",45280.388888888891,"2024-02-23",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,66209,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","47174","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,8,9,"2024-02-24",45280.958333333336,"2024-02-26",45280.1875,"1d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Electrification 2 x 25 kV\r\nUPM : 466023",null,null,47174,"2023-09-21","Medium","5,6"]
[null,"Infrabel","61228","Erquelinnes - Montzen",">","AMAY","ENGIS",2024,2024,8,8,"2024-02-24",45280.333333333336,"2024-02-24",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,61228,"2023-09-20","Minor","1,2,3,4,5"]
[null,"Infrabel","69251","Lille - Charleroi","< >","ROUX","Y.NORD",2024,2024,8,8,"2024-02-24",45280.979166666664,"2024-02-25",45280.1875,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Train Fraiseur\r\nL124A voie A du Bk 52.450 au bk 53.150\r\nUPM 468442",null,null,69251,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","46911","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,8,8,"2024-02-24",45280.979166666664,"2024-02-25",45280.708333333336,"1d, 17:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z6.53 en P4\r\n+ Z.11.53\r\nUPM 459749",null,null,46911,"2023-09-01","Medium","5,6"]
[null,"Infrabel","59728","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,8,9,"2024-02-24",45280.027777777781,"2024-02-26",45280.180555555555,"3d, 03:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud SIG + wissels Y arendstraat\r\nhangt samen met colt 59707 ===beveiliging werken L25\r\n\r\nR-451040",null,null,59728,"2023-08-30","Minor","5,6"]
[null,"Infrabel","67230","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,8,9,"2024-02-24",45280,"2024-02-26",45280.222222222219,"3d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage du ballast entre Sint-Joris-Weert et Wavre et le renouvellement du PN12 (Pécrot)\r\nUPM 467454",null,null,67230,"2023-09-28","Minor","5,6"]
[null,"Infrabel","55053","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET-GRIL OUEST",2024,2024,8,8,"2024-02-24",45280.9375,"2024-02-25",45280.916666666664,"1d, 23:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance Z17. 51\r\nFaisceau de Chatelet\r\nUPM 457223",null,null,55053,"2023-09-12","Minor","5,6"]
[null,"Infrabel","55122","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2024,2024,8,9,"2024-02-24",45280.013888888891,"2024-02-26",45280.194444444445,"2d, 04:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Entretien manuel et mécanisés des AW Bressoux / Visé-Bas\r\nEntretien manuel et mécanisés de la voie courante\r\nUPM : 464555",null,null,55122,"2023-10-05","Medium","5,6"]
[null,"Infrabel","68817","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2024,2024,8,8,"2024-02-24",45280.3125,"2024-02-24",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY (à répéter toutes les 4 semaines le samedi)",null,null,68817,"2023-10-06","Minor","5,6"]
[null,"Infrabel","49530","Lille - ZeeBrugge","< >","BRUGGE","Y.BLAUWE TOREN",2024,2024,8,8,"2024-02-24",45280.993055555555,"2024-02-25",45280.263888888891,"0d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"plaatsen + overnemen seinkeet",null,null,49530,"2023-11-16","Medium","5,6"]
[null,"Infrabel","60164","Lille - ZeeBrugge","< >","Y.DUDZELE","KNOKKE",2024,2024,8,8,"2024-02-24",45280.993055555555,"2024-02-25",45280.263888888891,"0d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-440257\r\nR-440262\r\nonderhoudsweekend\r\n(als gevolg van Renovatie brugdekken)\r\n+\r\nR7 14.00-22.00\r\n- Bundel Voorhaven West zone nr. 129: er worden max 3 sporen vrij gevraagd, overige sporen mogen bezet blijven\r\n- Zeebrugge strand blijft bereikbaar",null,null,60164,"2023-11-16","Medium","5,6"]
[null,"Infrabel","64868","Lille - Antwerpen",">","Y.MELSELE","SINT-NIKLAAS",2024,2024,8,8,"2024-02-24",45280.010416666664,"2024-02-24",45280.21875,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-465213\r\nReservatie onderhoud",null,null,64868,"2023-09-13","Minor","1,2,3,4,5"]
[null,"Infrabel","66447","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,8,8,"2024-02-24",45280.375,"2024-02-24",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie A\r\nVisite voie A",null,null,66447,"2023-09-21","Minor","5,6"]
[null,"Infrabel","48949","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2024,2024,8,8,"2024-02-24",45280.340277777781,"2024-02-25",45280.659722222219,"2d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles \r\nUPM 466933",null,null,48949,"2023-09-28","Minor","5,6"]
[null,"Infrabel","59011","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ANTWERPEN-NOORD-INRIT C1",2024,2024,8,8,"2024-02-25",45280.25,"2024-02-25",45280.729166666664,"1d, 11:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Oude Landen\r\nproject 304\r\n\r\nR-444666",null,null,59011,"2023-10-04","Minor","5,6"]
[null,"Infrabel","68818","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2024,2024,8,8,"2024-02-25",45280.3125,"2024-02-25",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY (à répéter toutes les 4 semaines le dimanche)",null,null,68818,"2023-10-06","Minor","5,6"]
[null,"Infrabel","61072","Namur - Antwerpen","< >","NAMUR","RONET",2024,2024,8,8,"2024-02-25",45280.003472222219,"2024-02-25",45280.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur (ZONE 6)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année\r\nUPM 459452",null,null,61072,"2023-09-26","Minor","5,6"]
[null,"Infrabel","66448","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2024,2024,8,8,"2024-02-25",45280.375,"2024-02-25",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie B\r\nVisite voie B",null,null,66448,"2023-09-21","Minor","5,6"]
[null,"Infrabel","61229","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2024,2024,8,8,"2024-02-25",45280.354166666664,"2024-02-25",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,61229,"2023-09-20","Minor","5,6"]
[null,"Infrabel","61743","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,9,9,"2024-02-26",45280.958333333336,"2024-03-02",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement pièces caténaire",null,null,61743,"2023-10-05","Minor","1,2,3,4,5"]
[null,"Infrabel","62818","Athus - Meuse",">","YVOIR","DINANT",2024,2024,9,9,"2024-02-26",45280.958333333336,"2024-03-02",45280.204861111109,"5d, 05:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble\r\nUPM 462810",null,null,62818,"2023-10-05","Minor","1,2,3,4,5"]
[null,"Infrabel","49046","Namur - Antwerpen",">","NAMUR","FLAWINNE",2024,2024,9,9,"2024-02-26",45280.333333333336,"2024-02-26",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nUPM 467232",null,null,49046,"2023-11-17","Minor","1,2,3,4,5"]
[null,"Infrabel","47142","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,9,9,"2024-02-26",45280.979166666664,"2024-03-02",45280.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nmassifs caténaires\r\nUPM 468233",null,null,47142,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","58910","Namur - Antwerpen","< >","SINT-JORIS-WEERT","LEUVEN",2024,2024,9,9,"2024-02-26",45280.951388888891,"2024-03-01",45280.21875,"4d, 06:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing sporen.\r\n\r\nafwerking  werken massificatie met werken Waver-Ottignies\r\n\r\n+\r\nonderhoud\r\n\r\nR-444669",null,null,58910,"2023-09-05","Minor","1,2,3,4,5"]
[null,"Infrabel","59405","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2024,2024,9,9,"2024-02-26",45280.965277777781,"2024-03-02",45280.215277777781,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Traverses et Ballast \r\nC75  entre 12.100 et 19.285\r\nFinitions\r\nUPM : 465200",null,null,59405,"2023-09-28","Minor","1,2,3,4,5"]
[null,"Infrabel","62156","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2024,2024,9,9,"2024-02-26",45280.986111111109,"2024-03-02",45280.229166666664,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FH_03 Area CE volgens onderhoudskalender 2024.\r\nBuitendienststelling L96 spoor A tussen FBMZ en Y Ruisbroek aw10R (Ni).",null,null,62156,"2023-09-25","Minor","1,2,3,4,5"]
[null,"Infrabel","61048","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,9,9,"2024-02-26",45280.989583333336,"2024-03-01",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service\r\nUPM 465750",null,null,61048,"2023-09-28","Minor","1,2,3,4,5"]
[null,"Infrabel","66205","Athus - Meuse",">","BEAURAING","HOUYET",2024,2024,9,9,"2024-02-26",45280.388888888891,"2024-02-26",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,66205,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","63371","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2024,2024,9,9,"2024-02-27",45280.375,"2024-02-27",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-451486",null,null,63371,"2023-09-18","Minor","1,2,3,4,5"]
[null,"Infrabel","66204","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,9,9,"2024-02-27",45280.388888888891,"2024-02-27",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,66204,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","67811","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2024,2024,9,9,"2024-02-28",45280.333333333336,"2024-02-28",45280.4375,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11",null,null,67811,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","65536","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2024,2024,9,9,"2024-02-28",45280.375,"2024-02-28",45280.645833333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-464326\r\nSchouwen lopend spoor",null,null,65536,"2023-09-13","Minor","1,2,3,4,5"]
[null,"Infrabel","66909","Athus - Meuse",">","SIGNEULX","HALANZY",2024,2024,9,9,"2024-02-28",45280.375,"2024-02-28",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,66909,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","63394","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,9,9,"2024-02-28",45280.375,"2024-02-28",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-451540",null,null,63394,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","66455","Athus - Meuse",">","VIRTON","SIGNEULX",2024,2024,9,9,"2024-02-29",45280.375,"2024-02-29",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,66455,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","55942","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,9,9,"2024-02-29",45280.395833333336,"2024-02-29",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53 + Visite Diagno\r\nMise HS en P2\r\nUPM 459752\r\nLe Je 29/02/2024 de 09:30 à 15:30   (total: 06h00) --> UPM",null,null,55942,"2023-11-28","Minor","1,2,3,4,5"]
[null,"Infrabel","67789","Lille - Charleroi",">","LUTTRE","MARCHIENNE-AU-PONT",2024,2024,9,9,"2024-02-29",45280.326388888891,"2024-02-29",45280.590277777781,"1d, 06:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J10\r\nEn corrélation avec aménagement de FLU Colt 49461",null,null,67789,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","49116","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2024,2024,9,9,"2024-03-01",45280.958333333336,"2024-03-03",45280.708333333336,"2d, 18:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4. 51  P4+\r\nUPM 444542",null,null,49116,"2023-12-04","Medium","5,6"]
[null,"Infrabel","60551","Athus - Meuse","< >","HOUYET","BEAURAING",2024,2024,9,10,"2024-03-01",45280.958333333336,"2024-03-04",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux pour adaptation du tracé pour augmenter la vitesse\r\nEntretien AS , traitement zone boueuse\r\nUPM : 466111\r\nART",null,null,60551,"2023-10-23","Medium","5,6"]
[null,"Infrabel","60440","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,9,10,"2024-03-01",45280.208333333336,"2024-03-05",45280.208333333336,"4d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Massification travaux pour adaptation du tracé pour augmenter la vitesse\r\nUPM : 466117",null,null,60440,"2023-11-27","Minor","1,2,3,4,5"]
[null,"Infrabel","49778","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,9,10,"2024-03-01",45280.972222222219,"2024-03-04",45280.194444444445,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 5/6\r\nDossier de concertation validé le 28 octobre 2021\r\nUPM 445120\r\nEn corrélation avec Colt 49461 - UPM 456865\r\nART",null,null,49778,"2023-10-23","Medium","5,6"]
[null,"Infrabel","47299","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,9,10,"2024-03-01",45280.965277777781,"2024-03-04",45280.166666666664,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-431069\r\nTLO-Weekend voor onderhouds werken",null,null,47299,"2023-09-13","Medium","5,6"]
[null,"Infrabel","66458","Athus - Meuse",">","SIGNEULX","VIRTON",2024,2024,9,9,"2024-03-01",45280.375,"2024-03-01",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,66458,"2023-09-21","Minor","1,2,3,4,5"]
[null,"Infrabel","46685","Athus - Meuse","< >","BERTRIX","FLORENVILLE",2024,2024,9,9,"2024-03-02",45280.958333333336,"2024-03-03",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Interventions Programmées\r\nUPM : 466414",null,null,46685,"2023-09-21","Medium","5,6"]
[null,"Infrabel","49862","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2024,2024,9,10,"2024-03-02",45280.052083333336,"2024-03-04",45280.1875,"2d, 03:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoud/vernieuwing spoor 3 Essen\r\nOnderhoud wissels station Essen\r\nWerken zone 1\r\n+\r\nHerelektrificatie voor TUC\r\n\r\nR-451761",null,null,49862,"2023-09-25","Medium","5,6"]
[null,"Infrabel","49531","Lille - ZeeBrugge","< >","BRUGGE","Y.BLAUWE TOREN",2024,2024,9,9,"2024-03-02",45280.993055555555,"2024-03-03",45280.263888888891,"0d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-417944\r\nplaatsen + overnemen seinkeet",null,null,49531,"2023-11-16","Medium","5,6"]
[null,"Infrabel","60165","Lille - ZeeBrugge","< >","Y.DUDZELE","KNOKKE",2024,2024,9,9,"2024-03-02",45280.993055555555,"2024-03-03",45280.263888888891,"0d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-417944\r\nonderhoudsweekend\r\n(als gevolg van Renovatie brugdekken)",null,null,60165,"2023-11-16","Medium","5,6"]
[null,"Infrabel","66660","Lille - Charleroi",">","BRAINE-LE-COMTE","SOIGNIES",2024,2024,9,9,"2024-03-02",45280.541666666664,"2024-03-02",45280.59375,"1d, 01:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA - Zone 2\r\nUPM 464814\r\n13h00-14h15 suite réunion Yvan/A-L/Damien/Emilien du 11/10/2023",null,null,66660,"2023-12-18","Minor","5,6"]
[null,"Infrabel","66752","Lille - Charleroi",">","BRAINE-LE-COMTE","Y.FELUY",2024,2024,9,9,"2024-03-02",45280.34375,"2024-03-02",45280.635416666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique AI52 + AI53\r\nUPM 468164 - 468165",null,null,66752,"2023-10-11","Minor","5,6"]
[null,"Infrabel","67231","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,9,10,"2024-03-02",45280.017361111109,"2024-03-04",45280.222222222219,"3d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage du ballast entre Sint-Joris-Weert et Wavre et le renouvellement du PN12 (Pécrot)\r\nUPM 467455",null,null,67231,"2023-11-27","Minor","5,6"]
[null,"Infrabel","66672","Lille - Charleroi",">","Y.SOIGNIES","SOIGNIES",2024,2024,9,9,"2024-03-03",45280.520833333336,"2024-03-03",45280.645833333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B\r\nUPM 464817 - 464815",null,null,66672,"2023-09-01","Minor","5,6"]
[null,"Infrabel","67107","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2024,2024,10,10,"2024-03-04",45280.958333333336,"2024-03-09",45280.177083333336,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage ballast finitios contraintes suite CR 2023\r\nUPM 468250",null,null,67107,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","62816","Athus - Meuse",">","YVOIR","DINANT",2024,2024,10,10,"2024-03-04",45280.958333333336,"2024-03-09",45280.204861111109,"5d, 05:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble\r\nUPM 462821",null,null,62816,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","49217","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2024,2024,10,10,"2024-03-04",45280.333333333336,"2024-03-04",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 116 à 121 + faisceau manage\r\nUPM 474851",null,null,49217,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","47139","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,10,10,"2024-03-04",45280.979166666664,"2024-03-09",45280.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nmassifs caténaires\r\nUPM 468235",null,null,47139,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","64003","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2024,2024,10,10,"2024-03-04",45280.979166666664,"2024-03-09",45280.1875,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-450680\r\nR-467582\r\nOnderhoud FGSP Nacht: Werkveld 4.1 + werkveld 4.2\r\n\r\nbijkomend mogelijk:\r\nFD SP Iv-V inbegrepen\r\nL73\r\nFLC SP I-II inbegrepen\r\nL86\r\ntot FRN",null,null,64003,"2023-09-25","Minor","1,2,3,4,5"]
[null,"Infrabel","49523","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2024,2024,10,10,"2024-03-04",45280.965277777781,"2024-03-08",45280.208333333336,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4. 51  P3  HKV\r\nUPM : 466852",null,null,49523,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","47666","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,10,10,"2024-03-04",45280.965277777781,"2024-03-09",45280.166666666664,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-431066\r\nAfwerkingsnachten na TLO-Weekend voor onderhouds werken\r\nminimum van 2 weekends per jaar, 1 weekend maart/april + 1 weekend oktober/november\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken mogelijk",null,null,47666,"2023-09-25","Minor","1,2,3,4,5"]
[null,"Infrabel","61049","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,10,10,"2024-03-04",45280.989583333336,"2024-03-08",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service\r\nUPM 465752",null,null,61049,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","58930","Namur - Antwerpen","< >","Y.BERCHEM-STADION","Y.LIERSESTEENWEG",2024,2024,10,10,"2024-03-04",45280.993055555555,"2024-03-08",45280.194444444445,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing van  Y-Drabstraat\r\n\r\nR-451822",null,null,58930,"2023-09-25","Minor","1,2,3,4,5"]
[null,"Infrabel","64351","Erquelinnes - Montzen",">","VISE","BRESSOUX",2024,2024,10,10,"2024-03-04",45280.947916666664,"2024-03-09",45280.215277777781,"5d, 06:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails , ballast...",null,null,64351,"2023-10-04","Minor","1,2,3,4,5"]
[null,"Infrabel","66886","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,10,10,"2024-03-04",45280.375,"2024-03-04",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,66886,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","60931","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2024,2024,10,10,"2024-03-04",45280.395833333336,"2024-03-08",45280.583333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z07.52\r\nJOUR",null,null,60931,"2023-10-04","Minor","1,2,3,4,5"]
[null,"Infrabel","61110","Erquelinnes - Montzen","< >","Y.NORD","ERQUELINNES-FRONTIERE",2024,2024,10,10,"2024-03-04",45280.923611111109,"2024-03-08",45280.173611111109,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires caténaire (Traverses)\r\n+ Maintenance Z2. 51  P3 HKV\r\n+ Travaux voie A signalisation\r\nTCR 466732",null,null,61110,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","48958","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2024,2024,10,10,"2024-03-04",45280.319444444445,"2024-03-04",45280.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance\r\nUPM 467730",null,null,48958,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","66715","Lille - Charleroi",">","SOIGNIES","NEUFVILLES",2024,2024,10,10,"2024-03-05",45280.333333333336,"2024-03-05",45280.541666666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B\r\nUPM 464823 - 464824",null,null,66715,"2023-10-04","Minor","1,2,3,4,5"]
[null,"Infrabel","65864","Lille - Antwerpen","< >","DEINZE","WAREGEM",2024,2024,10,10,"2024-03-05",45280.013888888891,"2024-03-09",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-460422\r\nETCS L2-IL_NW_P014_05_L75_Deinze - Waregem_IL\r\nOpkuis, meewerken mogelijk",null,null,65864,"2023-09-25","Minor","1,2,3,4,5"]
[null,"Infrabel","62871","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2024,2024,10,10,"2024-03-05",45280.996527777781,"2024-03-06",45280.190972222219,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen\r\nZ23.22 : studie nog uit te voeren door I-CBE\r\n\r\nR-451840",null,null,62871,"2023-09-25","Minor","1,2,3,4,5"]
[null,"Infrabel","66887","Athus - Meuse",">","HALANZY","Y.AUBANGE",2024,2024,10,10,"2024-03-05",45280.375,"2024-03-05",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,66887,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","61235","Erquelinnes - Montzen",">","STATTE","JAVA",2024,2024,10,10,"2024-03-06",45280.354166666664,"2024-03-06",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463074",null,null,61235,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","60089","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,10,10,"2024-03-06",45280.395833333336,"2024-03-06",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn\r\n\r\nR-451922",null,null,60089,"2023-09-25","Minor","1,2,3,4,5"]
[null,"Infrabel","60105","Namur - Antwerpen","< >","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL",2024,2024,10,10,"2024-03-07",45280.986111111109,"2024-03-08",45280.236111111109,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z11.22\r\n\r\nR-483531",null,null,60105,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","61236","Erquelinnes - Montzen",">","JAVA","ANDENNE",2024,2024,10,10,"2024-03-07",45280.5625,"2024-03-07",45280.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463107",null,null,61236,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","66900","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2024,2024,10,10,"2024-03-07",45280.375,"2024-03-07",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A\r\nEntretien / maintenance voie A",null,null,66900,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","61237","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2024,2024,10,10,"2024-03-07",45280.375,"2024-03-07",45280.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463078",null,null,61237,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","65962","Athus - Meuse",">","Y.NEFFE","DINANT",2024,2024,10,10,"2024-03-08",45280.333333333336,"2024-03-08",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB\r\nUPM 463268",null,null,65962,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","49779","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,10,11,"2024-03-08",45280.972222222219,"2024-03-11",45280.194444444445,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre : Phase 1-2024\r\nWeek-end 6/6\r\nDossier de concertation validé le 28 octobre 2021\r\nUPM 445142\r\nEn corrélation avec Colt 49461 - UPM 456865\r\nART",null,null,49779,"2023-10-24","Medium","5,6"]
[null,"Infrabel","60441","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,10,11,"2024-03-08",45280.25,"2024-03-12",45280.1875,"4d, 22:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Adaptation du tracé entre 17200 et 19700 pour augmentation de vitesse\r\nUPM : 466121",null,null,60441,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","33774","Namur - Antwerpen","< >","Y.BERCHEM-STADION","Y.LIERSESTEENWEG",2024,2024,10,11,"2024-03-08",45280.996527777781,"2024-03-11",45280.190972222219,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing van de wissels Y-Drabstraat\r\n\r\nR-452704",null,null,33774,"2023-09-25","Medium","5,6"]
[null,"Infrabel","57581","Lille - ZeeBrugge","< >","Y.KORTRIJK-WEST","LICHTERVELDE",2024,2024,10,11,"2024-03-08",45280.993055555555,"2024-03-11",45280.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-431067\r\nIndienstname PLP \r\nLichtervelde - Roeselare\r\nStations niet inbegrepen\r\n\r\nTestritten op zondag tot op de perrons van Lichtervelde en Roeselare in overleg met regelaar\r\n\r\n+ Roeselare-Y West Kortrijk voor onderhoud",null,null,57581,"2023-09-25","Medium","5,6"]
[null,"Infrabel","66901","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2024,2024,10,10,"2024-03-08",45280.375,"2024-03-08",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B\r\nEntretien / maintenance voie B",null,null,66901,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","48867","Namur - Antwerpen",">","WAVRE","OTTIGNIES",2024,2024,10,10,"2024-03-09",45280.333333333336,"2024-03-09",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes+ maintenances infrastructure et contrôles\r\nUPM : 465225",null,null,48867,"2023-10-18","Minor","5,6"]
[null,"Infrabel","69569","Namur - Antwerpen",">","CHATELET-GRIL OUEST","CHATELET",2024,2024,10,10,"2024-03-09",45280.333333333336,"2024-03-09",45280.5625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2024-089 (Envoyé le 10/07/23) Refusé par SNCB le 04/08/23 - CR 2024-089 validé le 16-08-23 par I-AM (Chgt dates)\r\nGéo 22J + 21AJ  (Date Max: 22J = 27/06/24 & 21AJ = 14/08/24)\r\nS627 en L130 VB entre 38AI/37BI ne & DX-J.20\r\nTCR 474827",null,null,69569,"2023-10-10","Minor","5,6"]
[null,"Infrabel","49207","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2024,2024,10,10,"2024-03-09",45280.333333333336,"2024-03-10",45280.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique + maintenance infrastructure + contrôles\r\nUPM 466897\r\nUPM 466898",null,null,49207,"2023-11-17","Minor","5,6"]
[null,"Infrabel","60451","Athus - Meuse","< >","HOUYET","VONECHE",2024,2024,10,11,"2024-03-09",45280.25,"2024-03-11",45280.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Adaptation du tracé entre 17200 et 19700 pour augmentation de vitesse\r\nRipages caténaires suite adaptation du tracé 17200 -19700\r\nUPM : 466116",null,null,60451,"2023-10-20","Medium","5,6"]
[null,"Infrabel","45916","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2024,2024,10,11,"2024-03-09",45280.052083333336,"2024-03-11",45280.1875,"2d, 03:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoud/vernieuwing spoor 3 Essen\r\nOnderhoud wissels station Essen\r\nWerken zone 1\r\n+\r\nHerelektrificatie voor TUC",null,null,45916,"2023-10-03","Medium","5,6"]
[null,"Infrabel","69576","Namur - Antwerpen",">","CHATELET-GRIL OUEST","CHATELET",2024,2024,10,10,"2024-03-09",45280.5625,"2024-03-09",45280.666666666664,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2024-089 (Envoyé le 10/07/2023) Refusé par SNCB le 04/08/24 - CR 2024-089 validé par I-AM le 16/08/23. (Chgt dates)\r\nGéo 21BJ (Date Max: 21BJ = 14/08/24)\r\nS627 en L130 VA entre 37AI/36BI ne & D-J.20\r\nTCR 469088",null,null,69576,"2023-10-10","Minor","5,6"]
[null,"Infrabel","61238","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2024,2024,10,10,"2024-03-09",45280.354166666664,"2024-03-09",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463109",null,null,61238,"2023-10-10","Minor","5,6"]
[null,"Infrabel","48877","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2024,2024,10,10,"2024-03-10",45280.333333333336,"2024-03-10",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes - maintenances diverses et révisions\r\nUPM : 465263",null,null,48877,"2023-10-18","Minor","5,6"]
[null,"Infrabel","48976","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,10,10,"2024-03-10",45280.333333333336,"2024-03-10",45280.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144 + 130/1 + maintenance infrastructure + contrôles\r\nUPM 467555",null,null,48976,"2023-10-10","Minor","5,6"]
[null,"Infrabel","69578","Namur - Antwerpen",">","CHATELET-GRIL OUEST","CHATELET",2024,2024,10,10,"2024-03-10",45280.333333333336,"2024-03-10",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2024-089 (Envoyé le 10/07/2023) refusé par SNCB le 04/08/23 - CR 2024-089 validé par I-AM le  16/08/23. (Chgt dates)\r\nGéo 38AI + 37BI (Date Max: 38AI & 37BI = 26/06/24)\r\nS627 en L130 VB entre F4-I.20 & 21AJ/22J ne\r\nTCR 469089",null,null,69578,"2023-10-10","Minor","5,6"]
[null,"Infrabel","61594","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2024,2024,10,10,"2024-03-10",45280.25,"2024-03-10",45280.729166666664,"1d, 11:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...\r\n\r\nR-454100",null,null,61594,"2023-11-02","Minor","5,6"]
[null,"Infrabel","66041","Athus - Meuse",">","LUSTIN","JAMBES",2024,2024,10,10,"2024-03-10",45280.385416666664,"2024-03-10",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463436",null,null,66041,"2023-10-10","Minor","5,6"]
[null,"Infrabel","61239","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2024,2024,10,10,"2024-03-10",45280.354166666664,"2024-03-10",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463111",null,null,61239,"2023-10-10","Minor","5,6"]
[null,"Infrabel","69579","Namur - Antwerpen",">","CHATELET-GRIL OUEST","CHATELET",2024,2024,10,10,"2024-03-10",45280.5,"2024-03-10",45280.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2024-089 (Envoyé le 10/07/2023)refusé le 04/08/23 - CR 2024-089 validé par I-AM le 16/08/2023. (Cght dates)\r\nGéo 36BI + 37AI (Date Max: 36BI & 37AI =  18/07/24)\r\nS627 en L130 VA entre FX3-I.20 & 23AJ/21BJ ne\r\nTCR 469091",null,null,69579,"2023-10-10","Minor","5,6"]
[null,"Infrabel","62817","Athus - Meuse",">","YVOIR","DINANT",2024,2024,11,11,"2024-03-11",45280.958333333336,"2024-03-15",45280.204861111109,"4d, 05:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble\r\nUPM 462824",null,null,62817,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","66878","Athus - Meuse",">","BERTRIX","STRAIMONT",2024,2024,11,11,"2024-03-11",45280.333333333336,"2024-03-11",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,66878,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","50592","Namur - Antwerpen",">","AUVELAIS","MOUSTIER-GARAGE",2024,2024,11,11,"2024-03-11",45280.979166666664,"2024-03-15",45280.208333333336,"4d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie\r\nUPM 467330",null,null,50592,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","61681","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2024,2024,11,11,"2024-03-11",45280.951388888891,"2024-03-15",45280.201388888891,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.43 + Z9.41\r\n+ Entretien et interventions diverses sur caténaire",null,null,61681,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","64643","Lille - Antwerpen","< >","SINT-NIKLAAS","Y.MELSELE",2024,2024,11,11,"2024-03-11",45280.972222222219,"2024-03-16",45280.184027777781,"5d, 05:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465695\r\nOnderhoud\r\n\r\n\r\n*perron II-V inbegrepen. \r\n*SP I + SP A  niet inbegrepen om doorrit naar L54 toe te laten",null,null,64643,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","61045","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,11,11,"2024-03-11",45280.989583333336,"2024-03-15",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service\r\nUPM 465755",null,null,61045,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","64139","Namur - Antwerpen","< >","Y.NAZARETH","Y.OOST DRIEHOEK AARSCHOT",2024,2024,11,11,"2024-03-11",45280.993055555555,"2024-03-12",45280.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"LEVEREN rails voor vernieuwing wissels Y Noord Dr. Aarschot\r\n\r\nR-453441",null,null,64139,"2023-09-27","Minor","1,2,3,4,5"]
[null,"Infrabel","58931","Namur - Antwerpen","< >","Y.BERCHEM-STADION","Y.LIERSESTEENWEG",2024,2024,11,11,"2024-03-11",45280.993055555555,"2024-03-15",45280.194444444445,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing van  Y-Drabstraat\r\n\r\nR-453500",null,null,58931,"2023-09-27","Minor","1,2,3,4,5"]
[null,"Infrabel","61922","Namur - Antwerpen","< >","ROGIER","WATERMAEL",2024,2024,11,11,"2024-03-11",45280.982638888891,"2024-03-16",45280.208333333336,"5d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_01 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling L161 voor onderhoudswerken.\r\nBijkomend L161A tussen Y Jubelpark en Y Watermaal, L26/4 tussen Etterbeek en Y Boondaal en L26/2 MTB-Y MTB",null,null,61922,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","69818","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.DRABSTRAAT",2024,2024,11,11,"2024-03-11",45280.190972222219,"2024-03-15",45280.982638888891,"5d, 19:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing van de wissels Y-Drabstraat\r\nwissels 21J, 22J en 23J kunnen een week niet gedraaid worden. rijrichting van L27 naar L15.\r\n\r\nR-470898\r\nCR 2024-108",null,null,69818,"2023-12-05","Medium","1,2,3,4,5"]
[null,"Infrabel","58214","Namur - Antwerpen","< >","MECHELEN","MECHELEN-NEKKERSPOEL",2024,2024,11,11,"2024-03-12",45280,"2024-03-15",45280.194444444445,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"masterplan Mechelen \r\ndeels met L53 sp 5\r\n+\r\nReservatie onderhoud\r\nZ02.23.02 : studie nog uit te voeren door I-CBE COLT 62087\r\n\r\nR-453560",null,null,58214,"2023-09-27","Minor","1,2,3,4,5"]
[null,"Infrabel","64638","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2024,2024,11,11,"2024-03-12",45280.020833333336,"2024-03-16",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465651\r\nOnderhoud",null,null,64638,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","64655","Lille - Antwerpen","< >","LOKEREN","SINT-NIKLAAS",2024,2024,11,11,"2024-03-12",45280.013888888891,"2024-03-16",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465162\r\nOnderhoud\r\n* doorrit ultrasoon N13/14",null,null,64655,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","60442","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,11,11,"2024-03-12",45280.25,"2024-03-17",45280.25,"5d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Adaptation du tracé entre 17200 et 19700 pour augmentation de vitesse\r\nBourrage de révision, contraintes,...\r\nUPM : 466127",null,null,60442,"2023-11-15","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","66880","Athus - Meuse",">","STRAIMONT","BERTRIX",2024,2024,11,11,"2024-03-12",45280.375,"2024-03-12",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,66880,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","69260","Athus - Meuse",">","STOCKEM-NORD","ARLON",2024,2024,11,11,"2024-03-12",45280.361111111109,"2024-03-12",45280.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69260,"2023-09-22","Minor","1,2,3,4,5"]
[null,"Infrabel","68653","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2024,2024,11,11,"2024-03-13",45280.034722222219,"2024-03-14",45280.166666666664,"2d, 03:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-057\r\nR-466005\r\n\r\nReservatie Onderhoud nachtdienst Schets 3\r\nBuiten dienst \r\nFGSP Perronspoor I tem IV tot L50E SP A  tot 02BO niet inbegrepen + L50E SP B tot 05O niet inbegrepen \r\n+ verlengde van de perrons I+II kant kust L50A6 inbegrepen, L75 v",null,null,68653,"2023-11-07","Minor","1,2,3,4,5"]
[null,"Infrabel","66881","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,11,11,"2024-03-13",45280.375,"2024-03-13",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,66881,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","69267","Athus - Meuse",">","HABAY","STOCKEM-NORD",2024,2024,11,11,"2024-03-13",45280.375,"2024-03-13",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69267,"2023-09-22","Minor","1,2,3,4,5"]
[null,"Infrabel","66059","Athus - Meuse",">","NAMUR","JAMBES",2024,2024,11,11,"2024-03-13",45280.388888888891,"2024-03-13",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463270",null,null,66059,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","66086","Athus - Meuse",">","YVOIR","DINANT",2024,2024,11,11,"2024-03-14",45280.385416666664,"2024-03-14",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463275",null,null,66086,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","66882","Athus - Meuse",">","VIRTON","SIGNEULX",2024,2024,11,11,"2024-03-14",45280.375,"2024-03-14",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,66882,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","53439","Athus - Meuse","< >","LIBRAMONT","HATRIVAL",2024,2024,11,12,"2024-03-15",45280.958333333336,"2024-03-18",45280.201388888891,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Réalisation de lame d'air et déplacement séparation de phase Rocogne L165(1) - L162\r\nUPM : 466598",null,null,53439,"2023-12-15","Medium","5,6"]
[null,"Infrabel","71424","Athus - Meuse","< >","GRUPONT","HATRIVAL",2024,2024,11,12,"2024-03-15",45280.958333333336,"2024-03-18",45280.201388888891,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 114 Poix.\r\nMassification sur Colt 53439.",null,null,71424,"2023-11-21","Medium","5,6"]
[null,"Infrabel","49928","Athus - Meuse",">","YVOIR","DINANT",2024,2024,11,14,"2024-03-15",45280.916666666664,"2024-04-03",45280.270833333336,"18d, 08:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de Ballast (C75)\r\nUPM : 462138",null,null,49928,"2023-11-07","High","1,2,3,4,5,6,7"]
[null,"Infrabel","33778","Namur - Antwerpen","< >","Y.BERCHEM-STADION","Y.LIERSESTEENWEG",2024,2024,11,12,"2024-03-15",45280.996527777781,"2024-03-18",45280.190972222219,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing van de wissels Y-Drabstraat\r\n\r\nvernieuwing waterdichte rok van de kruisingsbrug BX15/L27A te Mortsel\r\nmeewerken met DVE Y Drabstraat\r\n\r\nR-454100",null,null,33778,"2023-10-02","Medium","5,6"]
[null,"Infrabel","58775","Namur - Antwerpen","< >","SCHAERBEEK","VILVOORDE",2024,2024,11,12,"2024-03-15",45280.993055555555,"2024-03-18",45280.166666666664,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Werken Viaduct Vilvoorde (L27 = moot 18)\r\n\r\nR-455458",null,null,58775,"2023-10-02","Medium","5,6"]
[null,"Infrabel","66101","Athus - Meuse",">","DINANT","YVOIR",2024,2024,11,11,"2024-03-15",45280.385416666664,"2024-03-15",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463276",null,null,66101,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","48833","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2024,2024,11,12,"2024-03-15",45280.947916666664,"2024-03-18",45280.208333333336,"2d, 06:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.51\r\nP4+\r\nUPM 457229\r\nCR 2024-117 (+ART colt 69907) envoyé le 20/07/2023 CR 2024-117 V02 envoyé le 13/09/2023 - V03 envoyé le 23/09/23 -  Validé le 23/10/23",null,null,48833,"2023-10-24","Medium","5,6"]
[null,"Infrabel","69849","Namur - Antwerpen","< >","CHATELET","CHATELET",2024,2024,11,12,"2024-03-15",45280.947916666664,"2024-03-18",45280.208333333336,"2d, 06:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Ajout Voie Car Wash à la Colt 48833, pour entrée machines, entre Signal D2-I. 20 et LYJ 20 + Cas elec  27314 + 316\r\nCR 2024-117 en corrélation avec COLT 48833 envoyé le 20/07/2023 - CR 2024-117 V02 le 13/09/2023 - CR 2024-117 V03 validé le 23/10/23\r\nVoi",null,null,69849,"2023-11-14","Medium","5,6"]
[null,"Infrabel","66884","Athus - Meuse",">","SIGNEULX","VIRTON",2024,2024,11,11,"2024-03-15",45280.375,"2024-03-15",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,66884,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","69850","Namur - Antwerpen","< >","CHATELET","CHATELET",2024,2024,11,11,"2024-03-16",45280.958333333336,"2024-03-17",45280.041666666664,"1d, 02:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Ajout Voie Car Wash à la Colt 48833, pour sortie machines, entre Signal D2-I. 20 et LYJ 20 + Cas elec  27314 + 316\r\nCR 2024-117 (En corrélation avec Colt 48833) envoyé le 20/07/2023\r\nVoie 335 du Car-Wash de Chatelet déjà HS en continu jusqu'au 20/04/202",null,null,69850,"2023-11-14","Minor","5,6"]
[null,"Infrabel","59732","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,11,12,"2024-03-16",45280.027777777781,"2024-03-18",45280.180555555555,"3d, 03:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud SIG + wissels Y arendstraat+onderhous wissel antwerpen centraal -1\r\n\r\nperronsporen 11-12-13-14\r\n\r\nR-455511",null,null,59732,"2023-10-02","Minor","5,6"]
[null,"Infrabel","71348","Namur - Antwerpen","< >","GENT-DAMPOORT","WONDELGEM",2024,2024,11,11,"2024-03-16",45280.972222222219,"2024-03-17",45280.270833333336,"1d, 07:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereiding overname(s) L204 in PLP.\r\nCR 2024-184\r\nTCR R-477979 (L58 tot 17/3 07:00) + R-477981 (L58/2 tot 17/3 14:00)",null,null,71348,"2023-11-17","Minor","5,6"]
[null,"Infrabel","58196","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2024,2024,11,12,"2024-03-16",45280.020833333336,"2024-03-18",45280.166666666664,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"afbraak trapkooien perrons Vilvoorde\r\nDemontage nieuwe luifel perron 3-4-5-6\r\n\r\nR-447665",null,null,58196,"2023-10-02","Medium","5,6"]
[null,"Infrabel","58326","Namur - Antwerpen",">","MECHELEN","Y.HEIKE",2024,2024,11,12,"2024-03-16",45280.25,"2024-03-18",45280.166666666664,"2d, 22:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"masterplan mechelen \r\ndeels met L27,L53A en spoor 5 in station Mechelen\r\n\r\nR-455527",null,null,58326,"2023-10-02","Minor","5,6"]
[null,"Infrabel","68820","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2024,2024,11,11,"2024-03-16",45280.3125,"2024-03-16",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY (à répéter toutes les 4 semaines le samedi)",null,null,68820,"2023-10-25","Minor","5,6"]
[null,"Infrabel","45917","Namur - Antwerpen","< >","Y.LUCHTBAL","KAPELLEN",2024,2024,11,12,"2024-03-16",45280.041666666664,"2024-03-18",45280.1875,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoud lopend spoor en spoortoestellen\r\n\r\n+\r\n\r\nherelectrificatie\r\n\r\nR-455507",null,null,45917,"2023-10-02","Medium","5,6"]
[null,"Infrabel","63679","Erquelinnes - Montzen","< >","MARCHIENNE-ZONE","ERQUELINNES-FRONTIERE",2024,2024,11,11,"2024-03-16",45280.993055555555,"2024-03-17",45280.166666666664,"1d, 04:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-LS_SO_L130A_Software_Marchienne-Zone - Erquelinnes\r\nTesten\r\nMee werken niet mogelijk\r\nUPM 466272",null,null,63679,"2023-10-10","Minor","5,6"]
[null,"Infrabel","66888","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,11,11,"2024-03-16",45280.375,"2024-03-16",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie A\r\nVisite voie A",null,null,66888,"2023-11-15","Minor","5,6"]
[null,"Infrabel","66843","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,11,12,"2024-03-17",45280.979166666664,"2024-03-18",45280.1875,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-461899\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nTLO L50A6\r\nBUNDEL NIET BEREIKBAAR\r\nPerron I tem V (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)",null,null,66843,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","68673","Namur - Antwerpen","< >","GENT-SINT-PIETERS","MERELBEKE-ROOSTER S",2024,2024,11,11,"2024-03-17",45280.027777777781,"2024-03-17",45280.243055555555,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-063\r\nR-466049\r\nReservatie onderhoud schets za^zo.",null,null,68673,"2023-10-16","Minor","5,6"]
[null,"Infrabel","60443","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,11,12,"2024-03-17",45280.25,"2024-03-22",45280.25,"5d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Massification travaux pour adaptation du tracé\r\nAdaptation du tracé entre 17200 et 19700 pour augmentation de vitesse\r\nBourrage de révision, contraintes,...\r\nUPM: 466129",null,null,60443,"2023-11-16","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","68819","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2024,2024,11,11,"2024-03-17",45280.3125,"2024-03-17",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY (à répéter toutes les 4 semaines le dimanche)",null,null,68819,"2023-10-25","Minor","5,6"]
[null,"Infrabel","50622","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,11,12,"2024-03-17",45280.034722222219,"2024-03-18",45280.222222222219,"2d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris\r\nUPM 467459",null,null,50622,"2023-12-08","Minor","5,6"]
[null,"Infrabel","66890","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2024,2024,11,11,"2024-03-17",45280.375,"2024-03-17",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie B\r\nVisite voie B",null,null,66890,"2023-11-16","Minor","5,6"]
[null,"Infrabel","50699","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,11,12,"2024-03-17",45280.038194444445,"2024-03-18",45280.1875,"2d, 03:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44\r\nUPM 474875",null,null,50699,"2023-10-18","Minor","5,6"]
[null,"Infrabel","64590","Namur - Antwerpen","< >","EEKLO","GENT-DAMPOORT",2024,2024,12,12,"2024-03-18",45280.958333333336,"2024-03-23",45280.1875,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-464097\r\nOnderhoud\r\nFGDM niet IN",null,null,64590,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","59242","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,12,12,"2024-03-18",45280.979166666664,"2024-03-22",45280.1875,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"UPM R-438494\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)",null,null,59242,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","49361","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2024,2024,12,12,"2024-03-18",45280.9375,"2024-03-23",45280.208333333336,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z8. 51   P3 HKV\r\nUPM 467138",null,null,49361,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","50717","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,12,12,"2024-03-18",45280.965277777781,"2024-03-22",45280.1875,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44.\r\n+ travaux caténaires / traverses\r\nUPM 467775",null,null,50717,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","60112","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,12,12,"2024-03-18",45280.986111111109,"2024-03-22",45280.236111111109,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z11.22",null,null,60112,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","58776","Namur - Antwerpen","< >","SCHAERBEEK","VILVOORDE",2024,2024,12,12,"2024-03-18",45280.993055555555,"2024-03-22",45280.166666666664,"4d, 04:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Werken Viaduct Vilvoorde (L27 = moot 18)\r\n\r\nR-455626",null,null,58776,"2023-10-02","Minor","1,2,3,4,5"]
[null,"Infrabel","61678","Erquelinnes - Montzen",">","HERMALLE-SOUS-HUY","AMAY",2024,2024,12,12,"2024-03-18",45280.375,"2024-03-22",45280.625,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement pièces caténaire",null,null,61678,"2023-10-06","Minor","1,2,3,4,5"]
[null,"Infrabel","66893","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2024,2024,12,12,"2024-03-18",45280.378472222219,"2024-03-18",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,66893,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","61920","Namur - Antwerpen","< >","SCHAERBEEK","Y.HAREN-NORD",2024,2024,12,12,"2024-03-18",45280.395833333336,"2024-03-22",45280.625,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone FSR_10  Area CE volgens onderhoudskalender 2024\r\nBuitendienststelling L27 Y Groep G overdag buiten de spitsuren voor onderhoudswerken.",null,null,61920,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","61923","Namur - Antwerpen","< >","ROGIER","WATERMAEL",2024,2024,12,12,"2024-03-18",45280.982638888891,"2024-03-23",45280.208333333336,"5d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_01 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling L161 voor onderhoudswerken.\r\nBijkomend L161A tussen Y Jubelpark en Y Watermaal, L26/4 tussen Etterbeek en Y Boondaal en L26/2 MTB-Y MTB",null,null,61923,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","62089","Namur - Antwerpen","< >","VILVOORDE","MECHELEN",2024,2024,12,12,"2024-03-19",45280,"2024-03-23",45280.194444444445,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\n\r\nZ02.23.02 : studie nog uit te voeren door I-CBE\r\n\r\nR-455637",null,null,62089,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","58138","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2024,2024,12,12,"2024-03-19",45280.010416666664,"2024-03-22",45280.201388888891,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"afbraak trapkooien perrons Vilvoorde\r\n\r\nR-455620",null,null,58138,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","63372","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2024,2024,12,12,"2024-03-19",45280.375,"2024-03-19",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-455635",null,null,63372,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","66894","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2024,2024,12,12,"2024-03-19",45280.378472222219,"2024-03-19",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,66894,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","66897","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,12,12,"2024-03-20",45280.375,"2024-03-20",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,66897,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","63395","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,12,12,"2024-03-20",45280.375,"2024-03-20",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-455642",null,null,63395,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","67079","Lille - Charleroi",">","ATH","BRUGELETTE",2024,2024,12,12,"2024-03-21",45280.333333333336,"2024-03-21",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno\r\nUPM 464337",null,null,67079,"2023-10-04","Minor","1,2,3,4,5"]
[null,"Infrabel","66266","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,12,12,"2024-03-21",45280.333333333336,"2024-03-21",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66266,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","61070","Namur - Antwerpen",">","NAMUR","RHISNES",2024,2024,12,12,"2024-03-21",45280.9375,"2024-03-22",45280.229166666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 4\r\nPériodicité toutes les 4 semaines en alternance avec la zone 9\r\nzone 4 : 3 fois sur l'année\r\nzone 9 : 9 fois sur l'année\r\nUPM 459436",null,null,61070,"2023-10-17","Minor","1,2,3,4,5"]
[null,"Infrabel","66687","Namur - Antwerpen","< >","Y.PRINSENHOEK","Y.MUIZEN",2024,2024,12,12,"2024-03-21",45280.989583333336,"2024-03-22",45280.208333333336,"1d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Raillossing ter voorbereiding van vernieuwing Muizen Rooster T\r\nPlanning rails-Schaarbeek moeilijk verplaatsbaar.\r\nBuitendienststelling Y Prinsenhoek - Y Muizen noodzakelijk (Muizen niet bereikbaar via kant Muizen Rooster T)\r\n\r\nR-469013",null,null,66687,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","63418","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,12,12,"2024-03-21",45280.375,"2024-03-21",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-455648",null,null,63418,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","60726","Namur - Antwerpen",">","Y.NORD","MARCINELLE",2024,2024,12,12,"2024-03-21",45280.354166666664,"2024-03-21",45280.666666666664,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rév 25Q & Rév 28Q\r\nUPM : 466214",null,null,60726,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","64373","Namur - Antwerpen",">","NAMUR","RHISNES",2024,2024,12,12,"2024-03-22",45280.958333333336,"2024-03-23",45280.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nUPM 459441",null,null,64373,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","49113","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,12,13,"2024-03-22",45280.958333333336,"2024-03-25",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z3. 51  P4+\r\n+ Renouvellement complet des PN\r\nUPM 444601",null,null,49113,"2023-10-10","Medium","5,6"]
[null,"Infrabel","66267","Athus - Meuse",">","BERTRIX","PALISEUL",2024,2024,12,12,"2024-03-22",45280.333333333336,"2024-03-22",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66267,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","67089","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2024,2024,12,12,"2024-03-22",45280.333333333336,"2024-03-22",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno\r\nUPM 464339",null,null,67089,"2023-10-04","Minor","1,2,3,4,5"]
[null,"Infrabel","33780","Namur - Antwerpen","< >","Y.NOORD GROENENHOEK","Y.LIERSESTEENWEG",2024,2024,12,13,"2024-03-22",45280.996527777781,"2024-03-25",45280.190972222219,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing van de wissels Y-Drabstraat \r\n+\r\nOnderhoud wissels Y.Stadion\r\n\r\nZIE COLT 58222",null,null,33780,"2023-10-19","Medium","5,6"]
[null,"Infrabel","49930","Athus - Meuse","< >","YVOIR","Y.NEFFE",2024,2024,12,13,"2024-03-22",45280.993055555555,"2024-03-25",45280.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de Ballast (C75)\r\nWE 1/6\r\nUPM: 462141\r\nART",null,null,49930,"2023-11-15","Medium","5,6"]
[null,"Infrabel","63436","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,12,12,"2024-03-22",45280.375,"2024-03-22",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-455649",null,null,63436,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","66252","Athus - Meuse",">","VONECHE","BEAURAING",2024,2024,12,12,"2024-03-23",45280.333333333336,"2024-03-23",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66252,"2023-11-16","Minor","5,6"]
[null,"Infrabel","69848","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2024,2024,12,13,"2024-03-23",45280.951388888891,"2024-03-25",45280.201388888891,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-117 Maintenance Z15. 51 -> Bourrage de révision De Witt Voie B + lever ART + Ballastage complémentaire & toilette Voie B.\r\nP3 HKV\r\nTronçon Allongé\r\nCR 2024-117 envoyé le 20/07/2023 - CR 2024-117V02 le 13/09/2023 - CR 2024-117 Version 03 validé l",null,null,69848,"2023-11-15","Minor","5,6"]
[null,"Infrabel","59088","Lille - Antwerpen",">","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM",2024,2024,12,13,"2024-03-23",45280,"2024-03-25",45280.1875,"2d, 04:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)\r\n\r\nR-455891",null,null,59088,"2023-10-19","Minor","5,6"]
[null,"Infrabel","64843","Lille - Antwerpen",">","LOKEREN","OOSTAKKER",2024,2024,12,12,"2024-03-23",45280.020833333336,"2024-03-23",45280.229166666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-465192\r\nReservatie onderhoud",null,null,64843,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","45918","Namur - Antwerpen","< >","KAPELLEN","Y.LUCHTBAL",2024,2024,12,13,"2024-03-23",45280.041666666664,"2024-03-25",45280.1875,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoud lopend spoor en spoortoestellen\r\n+\r\nherelectrificatie kapellen - luchtbal Colt 58059\r\n\r\nR-455897",null,null,45918,"2023-10-19","Medium","5,6"]
[null,"Infrabel","63680","Erquelinnes - Montzen","< >","MARCHIENNE-ZONE","ERQUELINNES-FRONTIERE",2024,2024,12,12,"2024-03-23",45280.993055555555,"2024-03-24",45280.166666666664,"1d, 04:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-LS_SO_L130A_Software_Marchienne-Zone - Erquelinnes\r\nTesten\r\nMee werken niet mogelijk\r\nUPM 466271",null,null,63680,"2023-10-10","Minor","5,6"]
[null,"Infrabel","65936","Athus - Meuse",">","ARLON","Y.AUTELBAS",2024,2024,12,12,"2024-03-23",45280.361111111109,"2024-03-23",45280.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65936,"2023-10-10","Minor","5,6"]
[null,"Infrabel","65329","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2024,2024,12,13,"2024-03-24",45280.958333333336,"2024-03-25",45280.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 3) 6 fois sur l'année\r\nUPM 459460",null,null,65329,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","66253","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,12,12,"2024-03-24",45280.333333333336,"2024-03-24",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,66253,"2023-11-16","Minor","5,6"]
[null,"Infrabel","71400","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2024,2024,12,12,"2024-03-24",45280.052083333336,"2024-03-24",45280.211805555555,"1d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-478237\r\nIDS ETCS L2-IL_NW_P014a_L75_Waregem - Y Zandberg_ETCS\r\nmeewerken niet mogelijk\r\nzonder impact, buiten het treinverkeer",null,null,71400,"2023-09-28","Minor","5,6"]
[null,"Infrabel","65928","Athus - Meuse",">","MARBEHAN","HABAY",2024,2024,12,12,"2024-03-24",45280.375,"2024-03-24",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65928,"2023-10-10","Minor","5,6"]
[null,"Infrabel","71324","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2024,2024,12,12,"2024-03-24",45280.072916666664,"2024-03-24",45280.201388888891,"1d, 03:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-181\r\nBuitendienst van de EBP seinpost - Leuven - Computer Room \"FLV\" voor 4u00 voor\r\nwerken \"Renewal of Network Device\". Uurregelingen zijn aanpasbaar tussen 22u00 en 06u00 voor dewelke het volledig stilleggen van het treinverkeer vereist is.\r\nR",null,null,71324,"2023-11-24","Minor","5,6"]
[null,"Infrabel","66264","Athus - Meuse",">","GEDINNE","PALISEUL",2024,2024,13,13,"2024-03-25",45280.333333333336,"2024-03-25",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66264,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","56666","Erquelinnes - Montzen",">","BRESSOUX","FROIDMONT",2024,2024,13,13,"2024-03-25",45280.333333333336,"2024-03-25",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Cette visite se fait le même lundi que la visite entre Visé-Bas et Frontière NS prévue l'après-midi\r\n- Visite de voie, tunnel et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56666,"2023-10-05","Minor","1,2,3,4,5"]
[null,"Infrabel","50579","Namur - Antwerpen",">","Y.FLAWINNE","MOUSTIER-GARAGE",2024,2024,13,13,"2024-03-25",45280.979166666664,"2024-03-29",45280.208333333336,"4d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie\r\nUPM 467331",null,null,50579,"2023-11-17","Minor","1,2,3,4,5"]
[null,"Infrabel","62331","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2024,2024,13,13,"2024-03-25",45280.951388888891,"2024-03-29",45280.201388888891,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.43 + Z9.41\r\n+ Entretien et interventions diverses sur caténaire",null,null,62331,"2023-10-05","Minor","1,2,3,4,5"]
[null,"Infrabel","62090","Namur - Antwerpen","< >","Y.NAZARETH","Y.OOST DRIEHOEK AARSCHOT",2024,2024,13,13,"2024-03-25",45280.96875,"2024-03-30",45280.1875,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\n'ZCC.23 : studie nog uit te voeren door I-CBE & Z28.25 : studie nog uit te voeren door I-CBE\r\n+\r\nLEVEREN WISSEL (X3) ==> colt 59694-59695-59698\r\n\r\nR-455999",null,null,62090,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","52663","Namur - Antwerpen","< >","MONT-SAINT-GUIBERT","GEMBLOUX",2024,2024,13,13,"2024-03-25",45280.986111111109,"2024-03-29",45280.180555555555,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires \r\nDépose traverses\r\nUPM 468251",null,null,52663,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","58933","Namur - Antwerpen","< >","ANTWERPEN-BERCHEM","Y.LIERSESTEENWEG",2024,2024,13,13,"2024-03-25",45280.986111111109,"2024-03-29",45280.190972222219,"4d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing van  Y-Drabstraat\r\n+\r\nonderhoud SIG Y stadion +Y noord Groenenhoek 4 nachten (colt 59717)\r\n\r\nR-455955",null,null,58933,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","62091","Namur - Antwerpen","< >","SCHAERBEEK","Y.WEERDE",2024,2024,13,13,"2024-03-25",45280.989583333336,"2024-03-29",45280.1875,"4d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\nZ02.23.01 : studie nog uit te voeren door I-CBE",null,null,62091,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","49931","Athus - Meuse",">","YVOIR","DINANT",2024,2024,13,13,"2024-03-25",45280.375,"2024-03-25",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de Ballast (C75)\r\nWE 1/3 - CTL R1\r\nUPM: 462203\r\nART",null,null,49931,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","56671","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2024,2024,13,13,"2024-03-25",45280.5,"2024-03-25",45280.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Cette visite se fait le même lundi que la visite entre Froidmont et Bressoux prévue l'avant-midi\r\n- Visite de voie, PN et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56671,"2023-10-24","Minor","1,2,3,4,5"]
[null,"Infrabel","65944","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2024,2024,13,13,"2024-03-25",45280.409722222219,"2024-03-25",45280.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65944,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","65407","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2024,2024,13,13,"2024-03-25",45280.381944444445,"2024-03-25",45280.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41 (à répéter toutes les 6 semaines, le lundi)",null,null,65407,"2023-10-05","Minor","1,2,3,4,5"]
[null,"Infrabel","66265","Athus - Meuse",">","PALISEUL","GEDINNE",2024,2024,13,13,"2024-03-26",45280.333333333336,"2024-03-26",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66265,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","60727","Namur - Antwerpen",">","Y.NORD","MARCINELLE",2024,2024,13,13,"2024-03-26",45280.354166666664,"2024-03-26",45280.666666666664,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rév 53Q & Rév 62Q\r\nUPM : 466216",null,null,60727,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","56613","Erquelinnes - Montzen",">","VISE","BRESSOUX",2024,2024,13,13,"2024-03-26",45280.395833333336,"2024-03-26",45280.611111111109,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Visite de voie, PN et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56613,"2023-10-24","Minor","1,2,3,4,5"]
[null,"Infrabel","66910","Athus - Meuse",">","SIGNEULX","HALANZY",2024,2024,13,13,"2024-03-27",45280.375,"2024-03-27",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,66910,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","65920","Athus - Meuse",">","LAVAUX","MARBEHAN",2024,2024,13,13,"2024-03-27",45280.361111111109,"2024-03-27",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65920,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","60090","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,13,13,"2024-03-27",45280.395833333336,"2024-03-27",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn\r\n\r\nR-456019",null,null,60090,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","66262","Athus - Meuse",">","VONECHE","GEDINNE",2024,2024,13,13,"2024-03-28",45280.333333333336,"2024-03-28",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,66262,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","65912","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2024,2024,13,13,"2024-03-28",45280.368055555555,"2024-03-28",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65912,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","55943","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,13,13,"2024-03-28",45280.395833333336,"2024-03-28",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53 + Visite Diagno\r\nMise HS en P2\r\nUPM 459753",null,null,55943,"2023-10-04","Minor","1,2,3,4,5"]
[null,"Infrabel","66263","Athus - Meuse",">","GEDINNE","VONECHE",2024,2024,13,13,"2024-03-29",45280.333333333336,"2024-03-29",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66263,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","47406","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","Y.FLAWINNE",2024,2024,13,14,"2024-03-29",45280.979166666664,"2024-04-02",45280.208333333336,"3d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement gare de Floreffe\r\nC75 pour rectification tracé BK 68.300 à 69.500\r\nWE 1/6\r\nDossier de concertation validé le 26 octobre 2021\r\n+ Renouvellement PS BK 0.796\r\n+ Visite de voies A et B + maintenance infrastructure + contrôles\r\n+CR2024 028-123\r\nU",null,null,47406,"2023-12-06","Medium","5,6"]
[null,"Infrabel","64356","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,13,13,"2024-03-29",45280.951388888891,"2024-03-30",45280.208333333336,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des AW d'entrée de gare de Visé",null,null,64356,"2023-10-24","Minor","1,2,3,4,5"]
[null,"Infrabel","55492","Lille - Antwerpen","< >","KORTRIJK-RINGLAAN","MOUSCRON-FRONTIERE",2024,2024,13,14,"2024-03-29",45280.965277777781,"2024-04-02",45280.166666666664,"3d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-431483\r\nMise en service ETCS\r\nWE 3jours\r\nUPM 460062\r\nSuite aux réunions de préparation de chantier entre I-AM et I-CBE, la TCR suivante a été modifiée :\r\n- R460062 - Semaine 13+14 - L.75/L75A - Avec impact HKV/HKM.\r\nUne réduction de zone est planifiée",null,null,55492,"2023-12-14","Medium","5,6"]
[null,"Infrabel","58934","Namur - Antwerpen","< >","Y.NOORD GROENENHOEK","Y.LIERSESTEENWEG",2024,2024,13,14,"2024-03-29",45280.996527777781,"2024-04-01",45280.190972222219,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing van de wissels Y-Drabstraat\r\n+\r\nonderhoud SIG Y stadion +Y noord Groenenhoek (59718)\r\n\r\nR-456024",null,null,58934,"2023-11-24","Medium","5,6"]
[null,"Infrabel","49932","Athus - Meuse","< >","YVOIR","Y.NEFFE",2024,2024,13,14,"2024-03-29",45280.993055555555,"2024-04-01",45280.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de Ballast (C75)\r\nWE 2/6\r\n+ Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble\r\nUPM : 462357\r\nART",null,null,49932,"2023-11-16","Medium","5,6"]
[null,"Infrabel","65904","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2024,2024,13,13,"2024-03-29",45280.368055555555,"2024-03-29",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65904,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","59090","Lille - Antwerpen",">","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM",2024,2024,13,14,"2024-03-30",45280,"2024-04-01",45280.1875,"2d, 04:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)\r\n\r\nR-456123",null,null,59090,"2023-10-23","Minor","5,6"]
[null,"Infrabel","38672","Athus - Meuse","< >","BOIS D'AUSSE","BRAIBANT",2024,2024,13,14,"2024-03-30",45280.020833333336,"2024-04-02",45280.180555555555,"3d, 03:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"chape d'étanchéité au Pont 79.965 à Assesse\r\nBesoin d'une CTL de 3 jours complets\r\nUPM 462271\r\nART colt 59608",null,null,38672,"2023-12-06","Medium","5,6"]
[null,"Infrabel","64864","Lille - Antwerpen",">","SINT-NIKLAAS","LOKEREN",2024,2024,13,13,"2024-03-30",45280.013888888891,"2024-03-30",45280.222222222219,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-465259\r\nReservatie onderhoud",null,null,64864,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","48660","Lille - Charleroi","< >","Y.JURBISE","MONS",2024,2024,13,13,"2024-03-30",45280.260416666664,"2024-03-31",45280.708333333336,"1d, 10:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.5.53\r\nMise HS en P4\r\nUPM 459888",null,null,48660,"2023-10-04","Medium","5,6"]
[null,"Infrabel","69066","Namur - Antwerpen",">","MOUSTIER","AUVELAIS",2024,2024,13,13,"2024-03-30",45280.326388888891,"2024-03-30",45280.659722222219,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A + maintenance infrastructure + contrôles\r\nUPM 467581",null,null,69066,"2023-11-15","Minor","5,6"]
[null,"Infrabel","73872","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2024,2024,13,13,"2024-03-30",45280.388888888891,"2024-03-30",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,73872,"2023-12-06","Minor","5,6"]
[null,"Infrabel","49180","Namur - Antwerpen",">","MOUSTIER","AUVELAIS",2024,2024,13,13,"2024-03-31",45280.333333333336,"2024-03-31",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies B + maintenance infrastructure + contrôles\r\nUPM : 462036",null,null,49180,"2023-10-18","Minor","5,6"]
[null,"Infrabel","60729","Erquelinnes - Montzen",">","Y.NORD","CHARLEROI-CENTRAL",2024,2024,13,13,"2024-03-31",45280.25,"2024-03-31",45280.479166666664,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rév 27AG\r\nUPM 466234",null,null,60729,"2023-10-10","Minor","5,6"]
[null,"Infrabel","73873","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2024,2024,13,13,"2024-03-31",45280.388888888891,"2024-03-31",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,73873,"2023-12-06","Minor","5,6"]
[null,"Infrabel","60731","Erquelinnes - Montzen",">","Y.NORD","HOURPES",2024,2024,13,13,"2024-03-31",45280.479166666664,"2024-03-31",45280.583333333336,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Géo critique 05K + 07K\r\nUPM 466236",null,null,60731,"2023-10-10","Minor","5,6"]
[null,"Infrabel","66905","Athus - Meuse",">","BERTRIX","STRAIMONT",2024,2024,14,14,"2024-04-01",45280.333333333336,"2024-04-01",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,66905,"2023-11-21","Minor","1,2,3,4,5"]
[null,"Infrabel","60927","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2024,2024,14,14,"2024-04-01",45280.979166666664,"2024-04-06",45280.1875,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.52\r\nTCR 467833\r\nEn corrélation avec Aménagement de Luttre Colt 49467 - TCR 456289",null,null,60927,"2023-11-07","Minor","1,2,3,4,5"]
[null,"Infrabel","47407","Namur - Antwerpen",">","FRANIERE","Y.FLAWINNE",2024,2024,14,14,"2024-04-01",45280.208333333336,"2024-04-05",45280.979166666664,"5d, 18:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement gare de Floreffe \r\nSAVU voie B. Voie A HS\r\nDossier de concertation validé le 28 octobre 2021\r\n+CR2024 028-123\r\nUPM: 459374",null,null,47407,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","62158","Lille - Charleroi",">","BRUXELLES-MIDI","LOT",2024,2024,14,14,"2024-04-01",45280.986111111109,"2024-04-06",45280.229166666664,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FH_04 Area CE volgens onderhoudskalender 2024\r\nBuitendienststelling L96 spoor B tussen FBMZ en Lot.",null,null,62158,"2023-11-27","Minor","1,2,3,4,5"]
[null,"Infrabel","49937","Athus - Meuse",">","YVOIR","DINANT",2024,2024,14,14,"2024-04-01",45280.180555555555,"2024-04-01",45280.625,"0d, 10:40h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de Ballast (C75)\r\nWE 2/3 CTL R1\r\nUPM: 462363",null,null,49937,"2023-11-21","Minor","1,2,3,4,5"]
[null,"Infrabel","48256","Namur - Antwerpen",">","LA ROCHE(BRABANT)","TILLY",2024,2024,14,23,"2024-04-01",45280.25,"2024-06-09",45280.708333333336,"69d, 11:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Sécurisation paroi rocheuse (400m)\r\nUPM 460231",null,null,48256,"2023-11-07","High","1,2,3,4,5,6,7"]
[null,"Infrabel","58225","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.BERCHEM-STADION",2024,2024,14,14,"2024-04-01",45280.993055555555,"2024-04-05",45280.194444444445,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"vernieuwing waterdichte rok van de kruisingsbrug BX15/L27A te Mortsel\r\nmeewerken met DVE Y Drabstraat\r\n+\r\nVernieuwing van  Y-Drabstraat (colt 58935)\r\n\r\nR-456212",null,null,58225,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","64363","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2024,2024,14,14,"2024-04-02",45280.333333333336,"2024-04-05",45280.625,"4d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"HKC ballast, osv, rails, tunnel avec protection par S460",null,null,64363,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","66906","Athus - Meuse",">","STRAIMONT","BERTRIX",2024,2024,14,14,"2024-04-02",45280.375,"2024-04-02",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,66906,"2023-11-21","Minor","1,2,3,4,5"]
[null,"Infrabel","49929","Athus - Meuse",">","YVOIR","DINANT",2024,2024,14,15,"2024-04-03",45280.270833333336,"2024-04-08",45280.625,"5d, 08:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de Ballast (C75)\r\nUPM: 462207",null,null,49929,"2023-11-07","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","66904","Athus - Meuse",">","HALANZY","Y.AUBANGE",2024,2024,14,14,"2024-04-03",45280.375,"2024-04-03",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,66904,"2023-11-22","Minor","1,2,3,4,5"]
[null,"Infrabel","66907","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2024,2024,14,14,"2024-04-04",45280.375,"2024-04-04",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A\r\nEntretien / maintenance voie A",null,null,66907,"2023-11-22","Minor","1,2,3,4,5"]
[null,"Infrabel","47408","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,14,15,"2024-04-05",45280.979166666664,"2024-04-08",45280.229166666664,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement gare de Floreffe\r\nWE 2/6\r\nDossier de concertation validé le 26 octobre 2021\r\n+CR2024 028-123\r\nUPM: 459376",null,null,47408,"2023-12-06","Medium","5,6"]
[null,"Infrabel","49933","Athus - Meuse","< >","YVOIR","Y.NEFFE",2024,2024,14,15,"2024-04-05",45280.916666666664,"2024-04-08",45280.229166666664,"2d, 07:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de Ballast (C75)\r\nWE 3/6\r\nUPM: 462366\r\nSuite CR SNCB 2024-203: libérer la voie 3 à  Dinant le dimanche 7 avril entre 7h et 9h30 dans le cadre du marathon de Namur.",null,null,49933,"2023-11-21","Medium","5,6"]
[null,"Infrabel","73270","Lille - Antwerpen","< >","Y.MELSELE","Y.WEST BERCHEM",2024,2024,14,15,"2024-04-05",45280.989583333336,"2024-04-08",45280.197916666664,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR2024-201\r\nbijkomende DOES spoor 59",null,null,73270,"2023-11-14","Medium","5,6"]
[null,"Infrabel","66908","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2024,2024,14,14,"2024-04-05",45280.375,"2024-04-05",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B\r\nEntretien / maintenance voie B",null,null,66908,"2023-11-22","Minor","1,2,3,4,5"]
[null,"Infrabel","59333","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","HALANZY",2024,2024,14,14,"2024-04-06",45280.958333333336,"2024-04-07",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS entrée de Virton : phase VB.\r\nUPM: 464341",null,null,59333,"2023-11-22","Medium","5,6"]
[null,"Infrabel","65545","Erquelinnes - Montzen",">","AMAY","ENGIS",2024,2024,14,14,"2024-04-06",45280.333333333336,"2024-04-06",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,65545,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","64845","Lille - Antwerpen",">","LOKEREN","OOSTAKKER",2024,2024,14,14,"2024-04-06",45280.020833333336,"2024-04-06",45280.229166666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-465204\r\nReservatie onderhoud",null,null,64845,"2023-11-17","Minor","5,6"]
[null,"Infrabel","49165","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2024,2024,14,14,"2024-04-06",45280.986111111109,"2024-04-07",45280.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nMini CTL\r\nUPM 457319",null,null,49165,"2023-11-07","Medium","5,6"]
[null,"Infrabel","50426","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2024,2024,14,14,"2024-04-06",45280.986111111109,"2024-04-07",45280.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\nUPM: 460273",null,null,50426,"2023-11-21","Medium","5,6"]
[null,"Infrabel","55977","Lille - Charleroi","< >","JURBISE","BRUGELETTE",2024,2024,14,14,"2024-04-06",45280.25,"2024-04-07",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z7.53\r\nUPM 442442",null,null,55977,"2023-11-08","Medium","5,6"]
[null,"Infrabel","60169","Lille - Antwerpen","< >","LOKEREN","SINT-NIKLAAS",2024,2024,14,15,"2024-04-06",45280.25,"2024-04-08",45280.180555555555,"2d, 22:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-436032\r\nOnderhoud\r\n\r\n* Lokeren:\r\n- Rooster kant Antwerpen inbegrepen + SP IV\r\n- gevallen BVL perronsporen enkel tijdens de nacht\r\n* Sint Niklaas \r\n- Rooster kant Gent inbegrepen + SP IV en V\r\n- gevallen BVL perronsporen enkel tijdens de nacht",null,null,60169,"2023-10-11","Medium","5,6"]
[null,"Infrabel","68949","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,14,15,"2024-04-06",45280.041666666664,"2024-04-08",45280.1875,"3d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"migratie tunnelveiligheidstechnieken antwerpen NZ\r\n\r\nR-456285",null,null,68949,"2023-10-31","Minor","5,6"]
[null,"Infrabel","63279","Namur - Antwerpen","< >","Y.NAZARETH","Y.OOST DRIEHOEK AARSCHOT",2024,2024,14,14,"2024-04-06",45280.993055555555,"2024-04-07",45280.208333333336,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Weekendnacht 8h 06^07/04/2024\r\n\r\nIDS, meewerken niet mogelijk, CTL spoor A+B\r\nETCS L2-IL_NO_P010_P011_L16_L35_Lier-Leuven_ETCS\r\n\r\nR-456279\r\nuitgebreid zonder impact met \r\nL15 Lier - De Bist\r\nL35 driehoek Aarschot - Testelt\r\nL35 Driehoek Aarschot - Leuve",null,null,63279,"2023-11-20","Minor","5,6"]
[null,"Infrabel","65544","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2024,2024,14,14,"2024-04-07",45280.354166666664,"2024-04-07",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,65544,"2023-12-13","Minor","5,6"]
[null,"Infrabel","49047","Namur - Antwerpen",">","NAMUR","FLAWINNE",2024,2024,15,15,"2024-04-08",45280.333333333336,"2024-04-08",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nUPM 467235",null,null,49047,"2023-11-21","Minor","5,6"]
[null,"Infrabel","49585","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,15,16,"2024-04-08",45280.333333333336,"2024-04-19",45280.625,"12d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre : Phase 4-2024\r\nDossier de concertation validé le 28 octobre 2021\r\nUPM 456988",null,null,49585,"2023-11-07","Minor","1,2,3,4,5"]
[null,"Infrabel","47144","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,15,15,"2024-04-08",45280.979166666664,"2024-04-13",45280.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\npose poteaux\r\nUPM 468237",null,null,47144,"2023-11-22","Minor","1,2,3,4,5"]
[null,"Infrabel","62959","Namur - Antwerpen","< >","Y.NAZARETH","Y.OOST DRIEHOEK AARSCHOT",2024,2024,15,15,"2024-04-08",45280.96875,"2024-04-13",45280.1875,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nZ28.25 : studie nog uit te voeren door I-CBE\r\n\r\nR-456346",null,null,62959,"2023-10-31","Minor","1,2,3,4,5"]
[null,"Infrabel","61132","Athus - Meuse",">","YVOIR","DINANT",2024,2024,15,15,"2024-04-08",45280.927083333336,"2024-04-12",45280.236111111109,"4d, 07:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast (C75)\r\nFinitions, contraintes,...\r\nUPM 466523",null,null,61132,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","58215","Namur - Antwerpen","< >","MECHELEN","MECHELEN-NEKKERSPOEL",2024,2024,15,15,"2024-04-08",45280.996527777781,"2024-04-13",45280.194444444445,"5d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"masterplan Mechelen \r\nL27+L53DOES+spoor V in Mechelen buiten dienst",null,null,58215,"2023-03-09","Minor","1,2,3,4,5"]
[null,"Infrabel","59720","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.ARENDSTRAAT",2024,2024,15,15,"2024-04-08",45280.993055555555,"2024-04-13",45280.190972222219,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"L 27 spoor A onderhoud SIG schets \r\nY noord Berchem inbegrepen\r\n\r\nR-456353",null,null,59720,"2023-11-27","Minor","1,2,3,4,5"]
[null,"Infrabel","67726","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2024,2024,15,15,"2024-04-08",45280.385416666664,"2024-04-08",45280.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,67726,"2023-11-22","Minor","1,2,3,4,5"]
[null,"Infrabel","67718","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-FRANCE",2024,2024,15,15,"2024-04-08",45280.375,"2024-04-08",45280.583333333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite voie unique L 165/2 \r\nVisite voie unique L 165/3\r\nVisite voie unique L 165/1\r\nMaintenance",null,null,67718,"2023-11-22","Minor","1,2,3,4,5"]
[null,"Infrabel","61927","Namur - Antwerpen","< >","SCHAERBEEK","Y.JOSAPHAT",2024,2024,15,15,"2024-04-08",45280.395833333336,"2024-04-12",45280.645833333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken Area CE volgens kalender.\r\nZone MTB 03, L161 perronsporen 3+4 te FSR + bundel M",null,null,61927,"2023-11-22","Minor","1,2,3,4,5"]
[null,"Infrabel","61127","Athus - Meuse",">","BEAURAING","HOUYET",2024,2024,15,15,"2024-04-08",45280.388888888891,"2024-04-08",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"visite et interventions diverses\r\nCR 2024-159",null,null,61127,"2023-11-27","Minor","5,6"]
[null,"Infrabel","62243","Namur - Antwerpen","< >","SCHAERBEEK","Y.JOSAPHAT",2024,2024,15,15,"2024-04-09",45280.013888888891,"2024-04-13",45280.215277777781,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P137304: Upgrade SI zone H\r\nB L161 : sein D4-L.8  -> sein LX-J.8\r\nA L161 : sein D3-L.8 -> sein L-J.8\r\nB L25  : J12-E.8  -> sein DX5-L.8",null,null,62243,"2023-11-22","Minor","1,2,3,4,5"]
[null,"Infrabel","63373","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2024,2024,15,15,"2024-04-09",45280.375,"2024-04-09",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-456363",null,null,63373,"2023-11-27","Minor","1,2,3,4,5"]
[null,"Infrabel","61126","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,15,15,"2024-04-09",45280.388888888891,"2024-04-09",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"visite et interventions diverses\r\nCR 2024-159",null,null,61126,"2023-11-27","Minor","5,6"]
[null,"Infrabel","66915","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,15,15,"2024-04-10",45280.375,"2024-04-10",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,66915,"2023-11-27","Minor","1,2,3,4,5"]
[null,"Infrabel","63397","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,15,15,"2024-04-10",45280.375,"2024-04-10",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-456382",null,null,63397,"2023-11-27","Minor","1,2,3,4,5"]
[null,"Infrabel","73345","Lille - Charleroi",">","MONS","MONS",2024,2024,15,15,"2024-04-11",45280.958333333336,"2024-04-12",45280.208333333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Démontage ancienne caténaire en gare de Mons : Dé, nettoyage et toilette pt 75N, 56Bis, 62N\r\n\r\nListe des sections de voie PTDES:\r\n\tMONS: la voie IV à Mons\r\nentre les délimitations\r\nMONS signal CX-K.27 (CUM 59.142 - L.96) du tronçon de voie MONS -> GHLIN",null,null,73345,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","66369","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,15,15,"2024-04-11",45280.333333333336,"2024-04-11",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66369,"2023-11-27","Minor","1,2,3,4,5"]
[null,"Infrabel","65993","Athus - Meuse",">","LUSTIN","YVOIR",2024,2024,15,15,"2024-04-11",45280.375,"2024-04-11",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463272",null,null,65993,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","63419","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,15,15,"2024-04-11",45280.375,"2024-04-11",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-456583",null,null,63419,"2023-11-02","Minor","1,2,3,4,5"]
[null,"Infrabel","38734","Athus - Meuse","< >","MARLOIE","MARLOIE",2024,2024,15,16,"2024-04-12",45280.958333333336,"2024-04-15",45280.180555555555,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaire\r\nPhase 16 \r\nUPM 462277",null,null,38734,"2023-11-17","Medium","5,6"]
[null,"Infrabel","66370","Athus - Meuse",">","BERTRIX","PALISEUL",2024,2024,15,15,"2024-04-12",45280.333333333336,"2024-04-12",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66370,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","47411","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,15,16,"2024-04-12",45280.979166666664,"2024-04-15",45280.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement gare de Floreffe\r\nWE 3/6\r\n+ Renouvellement PS BK 0.796\r\n+CR2024 028-123\r\nUPM : 462042",null,null,47411,"2023-12-06","Medium","5,6"]
[null,"Infrabel","49934","Athus - Meuse","< >","YVOIR","Y.NEFFE",2024,2024,15,16,"2024-04-12",45280.993055555555,"2024-04-15",45280.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de Ballast (C75)\r\nWE 4/6\r\nUPM: 462627",null,null,49934,"2023-11-22","Medium","5,6"]
[null,"Infrabel","66008","Athus - Meuse",">","YVOIR","LUSTIN",2024,2024,15,15,"2024-04-12",45280.375,"2024-04-12",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463273",null,null,66008,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","63437","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,15,15,"2024-04-12",45280.375,"2024-04-12",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-456584",null,null,63437,"2023-11-02","Minor","1,2,3,4,5"]
[null,"Infrabel","59334","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,15,15,"2024-04-13",45280.958333333336,"2024-04-14",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS entrée de Virton : phase VA.\r\nUPM : 466354\r\nCR 2024-039: Aménagement de la gare de Virton",null,null,59334,"2023-11-29","Medium","5,6"]
[null,"Infrabel","64839","Lille - Antwerpen",">","OOSTAKKER","GENT-DAMPOORT",2024,2024,15,15,"2024-04-13",45280.020833333336,"2024-04-13",45280.229166666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-465239\r\nReservatie onderhoud",null,null,64839,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","62378","Namur - Antwerpen","< >","NAMUR","RONET",2024,2024,15,15,"2024-04-13",45280.986111111109,"2024-04-14",45280.208333333336,"1d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Transfert des alimentations des loges en gare de Namur en vue du renouvellement de celle-ci\r\nLoge H1 remise en service\r\nUPM 462718",null,null,62378,"2023-11-22","Minor","5,6"]
[null,"Infrabel","58838","Lille - Charleroi","< >","ATH","BRUGELETTE",2024,2024,15,15,"2024-04-13",45280.25,"2024-04-14",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.54\r\nUPM 442445",null,null,58838,"2023-11-08","Medium","5,6"]
[null,"Infrabel","60719","Namur - Antwerpen","< >","Y.NOORD DRIEHOEK LEDEBERG","GENT-DAMPOORT",2024,2024,15,16,"2024-04-13",45280.25,"2024-04-15",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-433351\r\nInstandhouding Y Noord Driehoek Ledeberg\r\nGent Dampoort perron vrij\r\nL50E vrij",null,null,60719,"2023-11-06","Medium","5,6"]
[null,"Infrabel","57552","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2024,2024,15,16,"2024-04-13",45280.25,"2024-04-15",45280.173611111109,"2d, 22:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Oude landen project 308+304\r\n\r\nherlading ROCS op 14/04 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk",null,null,57552,"2023-11-28","Medium","5,6"]
[null,"Infrabel","68822","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2024,2024,15,15,"2024-04-13",45280.3125,"2024-04-13",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY (à répéter toutes les 4 semaines le samedi)",null,null,68822,"2023-11-22","Minor","5,6"]
[null,"Infrabel","60408","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2024,2024,15,15,"2024-04-13",45280.996527777781,"2024-04-14",45280.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B\r\nTCR 464403",null,null,60408,"2023-04-26","Minor","5,6"]
[null,"Infrabel","56911","Lille - Charleroi","< >","GHLIN","MONS",2024,2024,15,15,"2024-04-13",45280.993055555555,"2024-04-14",45280.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim\r\nUPM 463585",null,null,56911,"2023-11-08","Minor","5,6"]
[null,"Infrabel","66753","Lille - Charleroi",">","BRAINE-LE-COMTE","Y.FELUY",2024,2024,15,15,"2024-04-13",45280.34375,"2024-04-13",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique AI52 + AI53\r\nTCR 468166 - 468167",null,null,66753,"2023-11-08","Minor","5,6"]
[null,"Infrabel","62016","Athus - Meuse","< >","JAMBES-EST","MARLOIE",2024,2024,15,15,"2024-04-13",45280.982638888891,"2024-04-14",45280.263888888891,"1d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-FS_SE_L162_MNN-AYE",null,null,62016,"2023-11-17","Minor","5,6"]
[null,"Infrabel","48836","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2024,2024,15,15,"2024-04-13",45280.263888888891,"2024-04-14",45280.708333333336,"1d, 10:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10. 51   P4+\r\nUPM 457320",null,null,48836,"2023-11-07","Medium","5,6"]
[null,"Infrabel","48977","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,15,15,"2024-04-14",45280.333333333336,"2024-04-14",45280.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144 + 130/1 + maintenance infrastructure + contrôles\r\nUPM 467556",null,null,48977,"2023-11-22","Minor","5,6"]
[null,"Infrabel","48898","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2024,2024,15,15,"2024-04-14",45280.333333333336,"2024-04-14",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nOttignies gare  voie 1 à 5 en alternance\r\nUPM 467717",null,null,48898,"2023-12-03","Minor","5,6"]
[null,"Infrabel","70089","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2024,2024,15,15,"2024-04-14",45280.006944444445,"2024-04-14",45280.25,"1d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Project trapkooien: Weekendnacht spoor 3 en 4 in Vilvoorde BD\r\n\r\nR-456602",null,null,70089,"2023-11-02","Minor","5,6"]
[null,"Infrabel","62006","Namur - Antwerpen","< >","Y.NAZARETH","Y.OOST DRIEHOEK AARSCHOT",2024,2024,15,15,"2024-04-14",45280.013888888891,"2024-04-14",45280.25,"1d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"IDS ETCS L2-IL_NO_P010_P011_L16_L35_Lier-Leuven_ETCS\r\n\r\nL15 tot Lier maar tot 05u15\r\n\r\nR-457443",null,null,62006,"2023-11-29","Minor","5,6"]
[null,"Infrabel","58226","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","LUCHTBAL-ROOSTER S",2024,2024,15,15,"2024-04-14",45280.25,"2024-04-14",45280.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"304 statiestraat , tussen Y laarsebeek en Y driehoekstraat\r\n\r\ngekoppeld aan colt 57552",null,null,58226,"2023-08-30","Minor","5,6"]
[null,"Infrabel","61811","Namur - Antwerpen",">","Y.SCHIJN","ANTWERPEN-D.S.-RHODESIE",2024,2024,15,15,"2024-04-14",45280.25,"2024-04-14",45280.729166666664,"0d, 11:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Slijpwerken met SPENO op spoor A \r\n(planning per mail gekregen op 4/11/2022 van De Kempeneer David)",null,null,61811,"2023-11-03","Minor","5,6"]
[null,"Infrabel","57560","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","Y.SCHIJN",2024,2024,15,15,"2024-04-14",45280.25,"2024-04-14",45280.729166666664,"1d, 11:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Oude Landen\r\nproject 304",null,null,57560,"2023-08-18","Minor","5,6"]
[null,"Infrabel","61595","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2024,2024,15,15,"2024-04-14",45280.25,"2024-04-14",45280.729166666664,"1d, 11:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,61595,"2023-08-18","Minor","5,6"]
[null,"Infrabel","68821","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2024,2024,15,15,"2024-04-14",45280.3125,"2024-04-14",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY (à répéter toutes les 4 semaines le dimanche)",null,null,68821,"2023-11-22","Minor","5,6"]
[null,"Infrabel","50623","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,15,16,"2024-04-14",45280.038194444445,"2024-04-15",45280.21875,"2d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris\r\nUPM 467460",null,null,50623,"2023-12-03","Minor","5,6"]
[null,"Infrabel","73266","Namur - Antwerpen","< >","SCHELLEBELLE","Y.HEIKE",2024,2024,15,15,"2024-04-14",45280.017361111109,"2024-04-14",45280.184027777781,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-235\r\nR-479099\r\n\r\nBuitendienst van de EBP seinpost Dendermonde - (FDR) - Computer Room  tijdens 04u00\r\n voor werken \"Renewal of Network Device\". Uurregelingen zijn aanpasbaar tussen 00u0\r\n0 en 04u00. Het volledig stilleggen van het treinverkeer v",null,null,73266,"2023-11-27","Minor","5,6"]
[null,"Infrabel","66371","Athus - Meuse",">","GEDINNE","PALISEUL",2024,2024,16,16,"2024-04-15",45280.333333333336,"2024-04-15",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66371,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","50593","Namur - Antwerpen",">","AUVELAIS","MOUSTIER-GARAGE",2024,2024,16,16,"2024-04-15",45280.979166666664,"2024-04-19",45280.208333333336,"4d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie\r\n+électrification gare Jemeppe-sur-Sambre \r\npose poteaux\r\n-Voie à coordonner",null,null,50593,"2023-12-13","Minor","1,2,3,4,5"]
[null,"Infrabel","64797","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2024,2024,16,16,"2024-04-15",45280.979166666664,"2024-04-19",45280.229166666664,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2024-028\r\nAménagement gare de Floreffe \r\nSAVU voie A. Voie B HS\r\n\r\nUPM: 484913",null,null,64797,"2023-12-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61133","Athus - Meuse",">","YVOIR","DINANT",2024,2024,16,16,"2024-04-15",45280.927083333336,"2024-04-19",45280.236111111109,"4d, 07:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast (C75)\r\nFinitions, contraintes,...\r\nUPM 462960",null,null,61133,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","58216","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-NEKKERSPOEL",2024,2024,16,16,"2024-04-15",45280.993055555555,"2024-04-19",45280.194444444445,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"masterplan Mechelen \r\nL27+L53 spoor A + Spoor V in Mechelen station",null,null,58216,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","66374","Athus - Meuse",">","PALISEUL","GEDINNE",2024,2024,16,16,"2024-04-16",45280.333333333336,"2024-04-16",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66374,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","49358","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2024,2024,16,16,"2024-04-16",45280.979166666664,"2024-04-19",45280.1875,"3d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z7. 51   P3\r\nUPM 467212",null,null,49358,"2023-11-07","Minor","1,2,3,4,5"]
[null,"Infrabel","67034","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2024,2024,16,16,"2024-04-16",45280.027777777781,"2024-04-20",45280.1875,"5d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-462742\r\nOnderhoud TLN WERKVELD 1\r\nBuiten dienst \r\nFGSP Perronspoor I tem IV tot L50E SP A  tot 02XO niet inbegrepen + L50E SP B tot 01BO niet inbegrepen \r\n+ verlengde van de perrons I+II kant kust L50A6 inbegrepen, Bundel vrij L75 vrij",null,null,67034,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","65834","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","GENT-DAMPOORT",2024,2024,16,16,"2024-04-16",45280.027777777781,"2024-04-20",45280.184027777781,"5d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-469300\r\nETCS L2-IL_NW_P025_P026_L59_Y Sint Bernadettestraat - Berchem_ETCS\r\nDownload, meewerken mogelijk",null,null,65834,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","64641","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2024,2024,16,16,"2024-04-16",45280.020833333336,"2024-04-20",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465653\r\nOnderhoud",null,null,64641,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","64765","Lille - Antwerpen","< >","SINT-NIKLAAS","Y.MELSELE",2024,2024,16,16,"2024-04-16",45280.013888888891,"2024-04-19",45280.184027777781,"4d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465668\r\nonderhoud\r\n\r\n*perron II-V inbegrepen. \r\n*SP I + SP A  niet inbegrepen om doorrit naar L54 toe te laten\r\n*R5/R6 in WE TLO",null,null,64765,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","64761","Lille - Antwerpen","< >","LOKEREN","SINT-NIKLAAS",2024,2024,16,16,"2024-04-16",45280.013888888891,"2024-04-20",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465163\r\nOnderhoud\r\n* doorrit ultrasoon N13/14",null,null,64761,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","62242","Namur - Antwerpen","< >","SCHAERBEEK","Y.JOSAPHAT",2024,2024,16,16,"2024-04-16",45280.013888888891,"2024-04-20",45280.215277777781,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P137304: Upgrade SI zone H\r\nB L161 : sein D4-L.8  -> sein LX-J.8\r\nA L161 : sein D3-L.8 -> sein L-J.8\r\nB L25  : J12-E.8  -> sein DX5-L.8",null,null,62242,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","60106","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,16,16,"2024-04-16",45280.986111111109,"2024-04-17",45280.236111111109,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z11.22\r\n\r\nR-456020",null,null,60106,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","62872","Lille - Antwerpen","< >","Y.OOST BERCHEM","SINT-NIKLAAS-OOST",2024,2024,16,16,"2024-04-17",45280,"2024-04-17",45280.184027777781,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen\r\nZ23.22 : studie nog uit te voeren door I-CBE\r\n\r\nR-456725",null,null,62872,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","66911","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,16,16,"2024-04-17",45280.375,"2024-04-17",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,66911,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","63566","Erquelinnes - Montzen",">","JAVA","STATTE",2024,2024,16,16,"2024-04-17",45280.354166666664,"2024-04-17",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,63566,"2023-11-24","Minor","1,2,3,4,5"]
[null,"Infrabel","60091","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,16,16,"2024-04-17",45280.395833333336,"2024-04-17",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn\r\n\r\nR-456745",null,null,60091,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","66919","Athus - Meuse",">","BERTRIX","STRAIMONT",2024,2024,16,16,"2024-04-18",45280.333333333336,"2024-04-18",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,66919,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","66373","Athus - Meuse",">","VONECHE","GEDINNE",2024,2024,16,16,"2024-04-18",45280.333333333336,"2024-04-18",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,66373,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","60211","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2024,2024,16,16,"2024-04-18",45280.996527777781,"2024-04-19",45280.190972222219,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud SIG,wissels en overwegen\r\n\r\n+\r\n\r\nonderhoud TRA+SIG+OW L52\r\n\r\nsporen 1+4 antwerpen- zuid buiten dienst\r\n\r\nR-485775",null,null,60211,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","63567","Erquelinnes - Montzen",">","JAVA","ANDENNE",2024,2024,16,16,"2024-04-18",45280.5625,"2024-04-18",45280.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463123",null,null,63567,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","63568","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2024,2024,16,16,"2024-04-18",45280.375,"2024-04-18",45280.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463120",null,null,63568,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","64374","Namur - Antwerpen",">","NAMUR","RHISNES",2024,2024,16,16,"2024-04-19",45280.958333333336,"2024-04-20",45280.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nUPM 459442",null,null,64374,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","66377","Athus - Meuse",">","GEDINNE","VONECHE",2024,2024,16,16,"2024-04-19",45280.333333333336,"2024-04-19",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66377,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","48201","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,16,17,"2024-04-19",45280.979166666664,"2024-04-22",45280.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement gare de Floreffe\r\nWE 4/6\r\nDossier de concertation validé le 26 octobre 2021\r\n+CR2024 028-123\r\nUPM: 462048",null,null,48201,"2023-12-06","Medium","5,6"]
[null,"Infrabel","47359","Athus - Meuse","< >","LEIGNON","MARLOIE",2024,2024,16,17,"2024-04-19",45280.972222222219,"2024-04-22",45280.180555555555,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3: Phase 18 + Tir caténaire N°12\r\nTravaux de traversée de voie + Massification OA\r\nUPM 462270",null,null,47359,"2023-12-15","Medium","5,6"]
[null,"Infrabel","49935","Athus - Meuse","< >","YVOIR","Y.NEFFE",2024,2024,16,17,"2024-04-19",45280.993055555555,"2024-04-22",45280.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de Ballast (C75)\r\nWE 5/6\r\nUPM: 462629",null,null,49935,"2023-11-30","Medium","5,6"]
[null,"Infrabel","66920","Athus - Meuse",">","STRAIMONT","BERTRIX",2024,2024,16,16,"2024-04-19",45280.375,"2024-04-19",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,66920,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","59335","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","HALANZY",2024,2024,16,16,"2024-04-20",45280.958333333336,"2024-04-21",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS entrée de Virton : révision (1)\r\nUPM : 466363",null,null,59335,"2023-11-30","Medium","5,6"]
[null,"Infrabel","66375","Athus - Meuse",">","VONECHE","BEAURAING",2024,2024,16,16,"2024-04-20",45280.333333333336,"2024-04-20",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66375,"2023-11-30","Minor","5,6"]
[null,"Infrabel","48950","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2024,2024,16,16,"2024-04-20",45280.333333333336,"2024-04-21",45280.659722222219,"2d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles \r\nUPM 466937",null,null,48950,"2023-12-03","Minor","5,6"]
[null,"Infrabel","58246","Namur - Antwerpen",">","ANTWERPEN-OOST","Y.HOLLAND",2024,2024,16,17,"2024-04-20",45280,"2024-04-22",45280.166666666664,"2d, 04:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Engelse leien vervolg vernieuwen wissels \r\nlange weekends incl vrijdag nacht\r\n\r\nTLO L12+27A SPa +bundelkop C\r\n\r\nBundel C en Bundel E mee buiten spanning gaat tijdens de werken.\r\n\r\nR-457481",null,null,58246,"2023-12-07","Minor","5,6"]
[null,"Infrabel","55055","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET-GRIL OUEST",2024,2024,16,16,"2024-04-20",45280.9375,"2024-04-21",45280.916666666664,"1d, 23:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance Z17. 51 \r\nFaisceau de Chatelet\r\nUPM 457323",null,null,55055,"2023-11-07","Minor","5,6"]
[null,"Infrabel","58415","Lille - Antwerpen","< >","Y.MELSELE","SINT-NIKLAAS",2024,2024,16,17,"2024-04-20",45280.020833333336,"2024-04-22",45280.184027777781,"2d, 03:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-436035\r\nP143: afschaffen overwegen NW afschaffen overweg 17 L59 - Haasdonkbaan, Beveren fietstunnel - BTS gedurende 1 week na inschuiven fietstunnel lente 2024 \r\n+\r\nOnderhoud Wissels Sint Niklaas \r\nperron IV-V inbegrepen + AW13L-11AL-15L-05L-03AL+ gev",null,null,58415,"2023-10-11","Medium","5,6"]
[null,"Infrabel","60738","Erquelinnes - Montzen",">","CHARLEROI-CENTRAL","Y.NORD",2024,2024,16,16,"2024-04-20",45280.25,"2024-04-20",45280.583333333336,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rév 27BG + 28AG\r\nUPM 466318",null,null,60738,"2023-11-07","Minor","5,6"]
[null,"Infrabel","61308","Lille - Charleroi","< >","ECAUSSINNES","LUTTRE",2024,2024,16,16,"2024-04-20",45280.927083333336,"2024-04-21",45280.243055555555,"1d, 07:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-FS_SO_L117_Feluy_Pont-à-Celles\r\nMES avril 2024",null,null,61308,"2023-11-08","Minor","5,6"]
[null,"Infrabel","59740","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2024,2024,16,17,"2024-04-20",45280.041666666664,"2024-04-22",45280.190972222219,"2d, 03:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Oosterweel (sloop brug, herpenduleren BVL,..) + duiker Sleedoornstraat\r\n\r\n+\r\n\r\nonderhoud SIG,wissels en overwegen\r\n\r\nR-456866",null,null,59740,"2023-11-17","Medium","5,6"]
[null,"Infrabel","63570","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2024,2024,16,16,"2024-04-20",45280.354166666664,"2024-04-20",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463124",null,null,63570,"2023-12-01","Minor","5,6"]
[null,"Infrabel","66376","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,16,16,"2024-04-21",45280.333333333336,"2024-04-21",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,66376,"2023-11-30","Minor","5,6"]
[null,"Infrabel","68263","Lille - Charleroi",">","BRAINE-LE-COMTE","HENNUYERES-GARAGE",2024,2024,16,16,"2024-04-21",45280.333333333336,"2024-04-21",45280.5625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique + S460\r\nUPM 464893 - 464894 - 464895",null,null,68263,"2023-11-08","Minor","5,6"]
[null,"Infrabel","61501","Namur - Antwerpen","< >","Y.WEERDE","Y.MUIZEN",2024,2024,16,16,"2024-04-21",45280.020833333336,"2024-04-21",45280.25,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossing wissels Muizen Rooster T - L27B\r\ndoodspoor 430 gaat mee BD + BS\r\n\r\nR-456872",null,null,61501,"2023-11-20","Minor","5,6"]
[null,"Infrabel","61812","Namur - Antwerpen","< >","Y.SCHIJN","ANTWERPEN-D.S.-RHODESIE",2024,2024,16,16,"2024-04-21",45280.25,"2024-04-21",45280.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Slijpwerken met SPENO op spoor B \r\n(planning per mail gekregen op 4/11/2022 van De Kempeneer David)\r\n\r\nR-431975",null,null,61812,"2023-11-20","Medium","5,6"]
[null,"Infrabel","64892","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2024,2024,16,16,"2024-04-21",45280.3125,"2024-04-21",45280.520833333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Noord\r\nBuitendienststellen van de van de volledige overeenkomstige EBP-zone gedurende minimaal 4 uur te bepalen tussen 06.00 uur en 14.00 uur\r\nUpdate EBP release to last version\r\nR-447025",null,null,64892,"2023-11-20","Minor","5,6"]
[null,"Infrabel","65379","Namur - Antwerpen","< >","NAMUR","RONET",2024,2024,16,16,"2024-04-21",45280.003472222219,"2024-04-21",45280.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur (ZONE 6)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année\r\nUPM 459453",null,null,65379,"2023-12-01","Minor","5,6"]
[null,"Infrabel","63571","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2024,2024,16,16,"2024-04-21",45280.354166666664,"2024-04-21",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463125",null,null,63571,"2023-12-01","Minor","5,6"]
[null,"Infrabel","49711","Namur - Antwerpen",">","RHISNES","GEMBLOUX",2024,2024,17,17,"2024-04-22",45280.958333333336,"2024-04-26",45280.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"poteaux\r\nUPM 474879",null,null,49711,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","65657","Erquelinnes - Montzen",">","NAMUR-HERBATTE","TILLEUR",2024,2024,17,17,"2024-04-22",45280.958333333336,"2024-04-27",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance et entretien\r\nSAVU double-cas à définir au moyen terme de nuit en semaine\r\nEn semaine 12 - 17 - 24 -\r\nUPM 459676",null,null,65657,"2023-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","64346","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,17,17,"2024-04-22",45280.958333333336,"2024-04-27",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails , ballast...",null,null,64346,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","64596","Namur - Antwerpen","< >","EEKLO","GENT-DAMPOORT",2024,2024,17,17,"2024-04-22",45280.958333333336,"2024-04-27",45280.1875,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-464103\r\nOnderhoud\r\nFGDM niet IN",null,null,64596,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","60935","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,17,17,"2024-04-22",45280.979166666664,"2024-04-26",45280.229166666664,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.52\r\nMise HS Zone 5 AI52 (Gare de Luttre)",null,null,60935,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","55038","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2024,2024,17,17,"2024-04-22",45280.979166666664,"2024-04-27",45280.208333333336,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10. 51   P3\r\nUPM : 460235",null,null,55038,"2023-11-07","Minor","1,2,3,4,5"]
[null,"Infrabel","73901","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2024,2024,17,17,"2024-04-22",45280.979166666664,"2024-04-27",45280.229166666664,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2024-028\r\nAménagement gare de Floreffe \r\nSAVU voie A. Voie B HS\r\n\r\nUPM: 484920",null,null,73901,"2023-12-07","Minor","1,2,3,4,5"]
[null,"Infrabel","64217","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,17,17,"2024-04-22",45280.972222222219,"2024-04-26",45280.208333333336,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-461875\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nTLO L50A6 - Bundel L/M vrij\r\nPerron I tot IV buiten dienst\r\n\r\n(alternatief stappenplan)",null,null,64217,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","64634","Lille - Antwerpen","< >","LOKEREN","SINT-NIKLAAS",2024,2024,17,17,"2024-04-22",45280.972222222219,"2024-04-27",45280.194444444445,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465189\r\nreservatie onderhoud\r\nLokeren\r\nSP II-III-IV inbegrepen, \r\nSP I na laatste trein\r\nSint Niklaas\r\nSPII-III-IV-V inbegrepen\r\nSP I na laatste trein",null,null,64634,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","61134","Athus - Meuse",">","YVOIR","DINANT",2024,2024,17,17,"2024-04-22",45280.916666666664,"2024-04-26",45280.25,"4d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast (C75)\r\nFinitions, contraintes,...\r\nUPM 462961",null,null,61134,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","60212","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2024,2024,17,17,"2024-04-22",45280.996527777781,"2024-04-26",45280.190972222219,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud SIG,wissels en overwegen\r\n\r\nR-456890",null,null,60212,"2023-11-21","Minor","1,2,3,4,5"]
[null,"Infrabel","59721","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.BERCHEM-STADION",2024,2024,17,17,"2024-04-22",45280.993055555555,"2024-04-26",45280.201388888891,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"L 27 spoor B onderhoud SIG \r\nY noord Berchem inbegrepen\r\n+\r\nL59/1 spoor A onderhoud SIG\r\n\r\nR-456877",null,null,59721,"2023-11-21","Minor","1,2,3,4,5"]
[null,"Infrabel","66913","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2024,2024,17,17,"2024-04-22",45280.378472222219,"2024-04-22",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,66913,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","61911","Namur - Antwerpen",">","SCHAERBEEK","Y.SCHAERBEEK-GROUPE G",2024,2024,17,17,"2024-04-22",45280.427083333336,"2024-04-26",45280.625,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FSR_03 volgens onderhoudskalender Area CE\r\nLokale wissels te FSR thv sporen A L27 en B L36,\r\nFSR sp IX,X en XI",null,null,61911,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","48959","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2024,2024,17,17,"2024-04-22",45280.319444444445,"2024-04-22",45280.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance\r\nUPM 467733",null,null,48959,"2023-12-03","Minor","1,2,3,4,5"]
[null,"Infrabel","65835","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","GENT-DAMPOORT",2024,2024,17,17,"2024-04-23",45280.027777777781,"2024-04-27",45280.184027777781,"5d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-469302\r\nETCS L2-IL_NW_P025_P026_L59_Y Sint Bernadettestraat - Berchem_ETCS\r\nTesten, meewerken niet mogelijk",null,null,65835,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","64697","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2024,2024,17,17,"2024-04-23",45280.020833333336,"2024-04-27",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465654\r\nOnderhoud",null,null,64697,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","66912","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2024,2024,17,17,"2024-04-23",45280.378472222219,"2024-04-23",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,66912,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","69261","Athus - Meuse",">","STOCKEM-NORD","ARLON",2024,2024,17,17,"2024-04-23",45280.361111111109,"2024-04-23",45280.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69261,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","67812","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2024,2024,17,17,"2024-04-24",45280.333333333336,"2024-04-24",45280.4375,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11",null,null,67812,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","65537","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2024,2024,17,17,"2024-04-24",45280.375,"2024-04-24",45280.645833333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-464327\r\nSchouwen lopend spoor",null,null,65537,"2023-10-11","Minor","1,2,3,4,5"]
[null,"Infrabel","69268","Athus - Meuse",">","HABAY","STOCKEM-NORD",2024,2024,17,17,"2024-04-24",45280.375,"2024-04-24",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69268,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","66089","Athus - Meuse",">","YVOIR","DINANT",2024,2024,17,17,"2024-04-25",45280.385416666664,"2024-04-25",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 468226",null,null,66089,"2023-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","67199","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2024,2024,17,17,"2024-04-25",45280.375,"2024-04-25",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A\r\nEntretien / maintenance voie A",null,null,67199,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","55944","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,17,17,"2024-04-25",45280.395833333336,"2024-04-25",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53 + Visite Diagno\r\nMise HS en P2\r\nUPM 459754",null,null,55944,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","67796","Lille - Charleroi",">","LUTTRE","MARCHIENNE-AU-PONT",2024,2024,17,17,"2024-04-25",45280.326388888891,"2024-04-25",45280.590277777781,"1d, 06:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J10",null,null,67796,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","60740","Namur - Antwerpen",">","COUILLET","CHATELET",2024,2024,17,17,"2024-04-25",45280.520833333336,"2024-04-25",45280.666666666664,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rév 01AI\r\nUPM 466320",null,null,60740,"2023-11-07","Minor","1,2,3,4,5"]
[null,"Infrabel","49710","Namur - Antwerpen",">","NAMUR","GEMBLOUX",2024,2024,17,18,"2024-04-26",45280.958333333336,"2024-04-29",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"réélectrification\r\n+ Visite périodique + maintenance infrastructure + contrôles\r\nUPM 466872",null,null,49710,"2023-12-02","Minor","5,6"]
[null,"Infrabel","47352","Athus - Meuse","< >","CINEY","MARLOIE",2024,2024,17,20,"2024-04-26",45280.979166666664,"2024-05-13",45280.180555555555,"16d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux en gare de d'Haversin : Phase 19\r\npour renouvellement caténaire R3 mixte\r\n+  renouvellement du PS d’Haversin bK 102.161\r\n+ Pose TDJ 02AC/01BC\r\n+ Pose TDJ 03AC/02BC\r\nUPM 462257",null,null,47352,"2023-12-02","High","1,2,3,4,5,6,7"]
[null,"Infrabel","49936","Athus - Meuse","< >","YVOIR","Y.NEFFE",2024,2024,17,18,"2024-04-26",45280.993055555555,"2024-04-29",45280.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de Ballast (C75)\r\nWE 6/6\r\nUPM : 462641",null,null,49936,"2023-12-01","Medium","5,6"]
[null,"Infrabel","66103","Athus - Meuse",">","DINANT","YVOIR",2024,2024,17,17,"2024-04-26",45280.385416666664,"2024-04-26",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463447",null,null,66103,"2023-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","67198","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2024,2024,17,17,"2024-04-26",45280.375,"2024-04-26",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B\r\nEntretien / maintenance voie B",null,null,67198,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","59336","Athus - Meuse","< >","BERTRIX","VIRTON",2024,2024,17,17,"2024-04-27",45280.958333333336,"2024-04-28",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS entrée de Virton : révision (2)\r\n+ Interventions Programmées\r\nUPM : 466367\r\nCR 2024-039: Aménagement de la gare de Virton",null,null,59336,"2023-11-29","Medium","5,6"]
[null,"Infrabel","69843","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2024,2024,17,18,"2024-04-27",45280.958333333336,"2024-04-29",45280.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-118 Maintenance Z10. 51   P3 (Bourrage de révision Infrabel Voie A + lever ART + Ballastage complémentaire & toilette Voie A)\r\nCR 2024-118 envoyé le 10/07/2023 - CR 2024-118 validé par AI.51 le  16/08/23\r\nTCR 471577",null,null,69843,"2023-11-07","Minor","5,6"]
[null,"Infrabel","48868","Namur - Antwerpen",">","WAVRE","OTTIGNIES",2024,2024,17,17,"2024-04-27",45280.333333333336,"2024-04-27",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes+ maintenances infrastructure et contrôles\r\nUPM : 465242",null,null,48868,"2023-12-03","Minor","5,6"]
[null,"Infrabel","58047","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,17,18,"2024-04-27",45280,"2024-04-29",45280.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Engelse Leien vervolg vernieuwen wissels \r\nTLO L12+27A SPa +bundelkop C\r\n\r\nBundel C en Bundel E mee buiten spanning gaat tijdens de werken.\r\n\r\nR-456961",null,null,58047,"2023-12-04","Medium","5,6"]
[null,"Infrabel","58199","Namur - Antwerpen","< >","Y.MACHELEN","Y.WEERDE",2024,2024,17,18,"2024-04-27",45280,"2024-04-29",45280.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"afbraak trapkooien perrons 3+4 te Vilvoorde\r\nDemontage trapkooi perron 3-4 + kraan parking (reserve)\r\nVilvoorde sporen 3+4+5+6+7+8+9\r\n\r\nR-457486",null,null,58199,"2023-11-21","Medium","5,6"]
[null,"Infrabel","59050","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,17,18,"2024-04-27",45280.013888888891,"2024-04-29",45280.180555555555,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"UPM R-438500\r\nGent Sint Pieters - Onderhoud \r\nY West vrij - FGSP SP I tem IV BD + verlengde op L50A6 - Bundel blijft bereikbaar",null,null,59050,"2023-10-11","Medium","5,6"]
[null,"Infrabel","52734","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,17,18,"2024-04-27",45280.986111111109,"2024-04-29",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement gare de Floreffe\r\nWE 5/6 - Nuits\r\nDossier de concertation validé le 26 octobre 2021\r\n+CR2024 028-123\r\nextension de la mise hors service MHS :\r\n• Des voies accessoires voie A côté Flawinne.\r\nUPM: 462049",null,null,52734,"2023-12-04","Minor","5,6"]
[null,"Infrabel","55957","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,17,17,"2024-04-27",45280.25,"2024-04-28",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z6.53 en P4\r\nUPM 459757",null,null,55957,"2023-11-08","Medium","5,6"]
[null,"Infrabel","66028","Athus - Meuse",">","JAMBES","LUSTIN",2024,2024,17,17,"2024-04-27",45280.385416666664,"2024-04-27",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463449",null,null,66028,"2023-12-02","Minor","5,6"]
[null,"Infrabel","58064","Namur - Antwerpen","< >","Y.SINT-MARIABURG","LUCHTBAL-ROOSTER S",2024,2024,17,18,"2024-04-27",45280.003472222219,"2024-04-29",45280.166666666664,"2d, 03:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"304(statiestraat)+308 (herelectrificatie)\r\n\r\nAan deze werken is een R7 (van 06h00 tot 17h30) gekoppeld op L27A voor het spoorgedeelte Y.Laarsebeek - Y.Schijn!! (58227) => afgeschaft!\r\n\r\nR-456945",null,null,58064,"2023-11-28","Medium","5,6"]
[null,"Infrabel","66642","Lille - Charleroi",">","BRAINE-LE-COMTE","SOIGNIES",2024,2024,17,17,"2024-04-27",45280.604166666664,"2024-04-27",45280.645833333336,"1d, 01:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA",null,null,66642,"2023-11-08","Minor","5,6"]
[null,"Infrabel","48878","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2024,2024,17,17,"2024-04-28",45280.333333333336,"2024-04-28",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes - maintenances diverses et révisions\r\nUPM : 465272",null,null,48878,"2023-12-03","Minor","5,6"]
[null,"Infrabel","66936","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2024,2024,17,17,"2024-04-28",45280.027777777781,"2024-04-28",45280.229166666664,"1d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465982\r\nreservatie onderhoud",null,null,66936,"2023-10-11","Minor","5,6"]
[null,"Infrabel","66937","Lille - Antwerpen","< >","Y.MELSELE","LOKEREN",2024,2024,17,17,"2024-04-28",45280.027777777781,"2024-04-28",45280.215277777781,"1d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465988\r\nreservatie onderhoud",null,null,66937,"2023-10-11","Minor","5,6"]
[null,"Infrabel","50701","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,17,18,"2024-04-28",45280.027777777781,"2024-04-29",45280.1875,"2d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44\r\nUPM 474886",null,null,50701,"2023-12-03","Minor","5,6"]
[null,"Infrabel","66044","Athus - Meuse",">","LUSTIN","JAMBES",2024,2024,17,17,"2024-04-28",45280.385416666664,"2024-04-28",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463450",null,null,66044,"2023-12-02","Minor","5,6"]
[null,"Infrabel","66673","Lille - Charleroi",">","Y.SOIGNIES","SOIGNIES",2024,2024,17,17,"2024-04-28",45280.520833333336,"2024-04-28",45280.645833333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B\r\nUPM 464901 - 464902",null,null,66673,"2023-11-08","Minor","5,6"]
[null,"Infrabel","66768","Lille - Charleroi",">","Y.JURBISE","NEUFVILLES-GARAGE",2024,2024,17,17,"2024-04-28",45280.322916666664,"2024-04-28",45280.479166666664,"1d, 03:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VB\r\nUPM 464899",null,null,66768,"2023-11-08","Minor","5,6"]
[null,"Infrabel","49712","Namur - Antwerpen",">","RHISNES","GEMBLOUX",2024,2024,18,18,"2024-04-29",45280.958333333336,"2024-05-03",45280.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"poteaux\r\nUPM 474880",null,null,49712,"2023-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","66313","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,18,18,"2024-04-29",45280.958333333336,"2024-05-03",45280.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux de nettoyage EBP PLP",null,null,66313,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","61135","Athus - Meuse",">","YVOIR","DINANT",2024,2024,18,18,"2024-04-29",45280.958333333336,"2024-05-03",45280.204861111109,"4d, 05:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast (C75)\r\nFinitions, contraintes,...\r\nUPM 462962",null,null,61135,"2023-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","60938","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,18,18,"2024-04-29",45280.979166666664,"2024-05-03",45280.229166666664,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.52\r\nMise HS Zone 5 AI52 (Gare de Luttre)",null,null,60938,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","50580","Namur - Antwerpen",">","Y.FLAWINNE","MOUSTIER-GARAGE",2024,2024,18,18,"2024-04-29",45280.979166666664,"2024-05-04",45280.229166666664,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie\r\nUPM 467380\r\n+ aménagement gare de Floreffe\r\nCR2024 028-123",null,null,50580,"2023-12-07","Minor","1,2,3,4,5"]
[null,"Infrabel","64238","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,18,18,"2024-04-29",45280.972222222219,"2024-05-03",45280.208333333336,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-461883\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nTLO L50A6 - Bundel L/M vrij\r\nPerron I tot IV buiten dienst\r\n\r\n(alternatief stappenplan)",null,null,64238,"2023-10-12","Minor","1,2,3,4,5"]
[null,"Infrabel","62126","Namur - Antwerpen","< >","SCHAERBEEK","MECHELEN",2024,2024,18,18,"2024-04-29",45280.989583333336,"2024-05-04",45280.1875,"5d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\nZ02.23.01 : studie nog uit te voeren door I-CBE\r\n\r\nR-457500",null,null,62126,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","59722","Namur - Antwerpen",">","Y.BERCHEM-STADION","ANTWERPEN-CENTRAAL",2024,2024,18,18,"2024-04-29",45280.993055555555,"2024-05-03",45280.201388888891,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"L 27 spoor B onderhoud SIG \r\nY noord Berchem inbegrepen\r\n\r\n+\r\nL59/1 spoor A\r\n\r\nR-457494",null,null,59722,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","58963","Namur - Antwerpen","< >","Y.OOST DRIEHOEK AARSCHOT","Y.NAZARETH",2024,2024,18,18,"2024-04-29",45280.993055555555,"2024-05-03",45280.1875,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers\r\n+\r\nReservatie onderhoud\r\n'ZCC.23 : studie nog uit te voeren door I-CBE & Z28.25 : studie nog uit te voeren door I-CBE  COLT 62125\r\n\r\nR-457495",null,null,58963,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","66914","Athus - Meuse",">","HALANZY","Y.AUBANGE",2024,2024,18,18,"2024-04-29",45280.375,"2024-04-29",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,66914,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","63398","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,18,18,"2024-04-29",45280.375,"2024-04-29",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-457489",null,null,63398,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","66062","Athus - Meuse",">","NAMUR","JAMBES",2024,2024,18,18,"2024-04-29",45280.388888888891,"2024-04-29",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463280",null,null,66062,"2023-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","66716","Lille - Charleroi",">","SOIGNIES","NEUFVILLES",2024,2024,18,18,"2024-04-30",45280.333333333336,"2024-04-30",45280.541666666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B\r\nUPM 464910 - 464908",null,null,66716,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","65836","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","GENT-DAMPOORT",2024,2024,18,18,"2024-04-30",45280.027777777781,"2024-05-04",45280.184027777781,"5d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-469303\r\nETCS L2-IL_NW_P025_P026_L59_Y Sint Bernadettestraat - Berchem_ETCS\r\nTesten, meewerken niet mogelijk",null,null,65836,"2023-10-12","Minor","1,2,3,4,5"]
[null,"Infrabel","60233","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2024,2024,18,18,"2024-04-30",45280,"2024-05-03",45280.1875,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"oosterweel LO(sloop brug 5236, herpendueren BVL, renovatie brug 5237)\r\n\r\nalternatief is week 31 (augustus)\r\n\r\nR-457490",null,null,60233,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","64698","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2024,2024,18,18,"2024-04-30",45280.020833333336,"2024-05-04",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465655\r\nOnderhoud",null,null,64698,"2023-10-12","Minor","1,2,3,4,5"]
[null,"Infrabel","64762","Lille - Antwerpen","< >","LOKEREN","SINT-NIKLAAS",2024,2024,18,18,"2024-04-30",45280.013888888891,"2024-05-04",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465166\r\nOnderhoud\r\n* doorrit ultrasoon N13/14",null,null,64762,"2023-10-12","Minor","1,2,3,4,5"]
[null,"Infrabel","64635","Lille - Antwerpen","< >","SINT-NIKLAAS","Y.MELSELE",2024,2024,18,18,"2024-04-30",45280.013888888891,"2024-05-04",45280.184027777781,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-465670\r\nonderhoud Sint Niklaas \r\n\r\n*perron II-V inbegrepen. \r\n*SP I + SP A  niet inbegrepen om doorrit naar L54 toe te laten",null,null,64635,"2023-10-12","Minor","1,2,3,4,5"]
[null,"Infrabel","66927","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,18,18,"2024-04-30",45280.375,"2024-04-30",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,66927,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","63374","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2024,2024,18,18,"2024-04-30",45280.375,"2024-04-30",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-457505",null,null,63374,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","65996","Athus - Meuse",">","LUSTIN","YVOIR",2024,2024,18,18,"2024-04-30",45280.375,"2024-04-30",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463457",null,null,65996,"2023-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","66922","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,18,18,"2024-05-01",45280.375,"2024-05-01",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,66922,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","66011","Athus - Meuse",">","YVOIR","LUSTIN",2024,2024,18,18,"2024-05-01",45280.375,"2024-05-01",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463459",null,null,66011,"2023-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","66433","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,18,18,"2024-05-02",45280.333333333336,"2024-05-02",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66433,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","57815","Athus - Meuse","< >","ARLON","STERPENICH-FRONTIERE",2024,2024,18,19,"2024-05-03",45280.958333333336,"2024-05-06",45280.166666666664,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux aux appareils d'Autelbas (traverses, rails)\r\nUPM 462923",null,null,57815,"2023-12-04","Medium","5,6"]
[null,"Infrabel","48247","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,18,19,"2024-05-03",45280.958333333336,"2024-05-06",45280.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2. 51  P4+\r\n+ Remplacement Loge PLP K6\r\n+ Travaux de remise en état du PS km 104,903\r\n + Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires caténaire (int. 99/4)\r\nUPM 442701",null,null,48247,"2023-11-07","Medium","5,6"]
[null,"Infrabel","65965","Athus - Meuse",">","Y.NEFFE","DINANT",2024,2024,18,18,"2024-05-03",45280.333333333336,"2024-05-03",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB\r\nUPM 463463",null,null,65965,"2023-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","66436","Athus - Meuse",">","BERTRIX","PALISEUL",2024,2024,18,18,"2024-05-03",45280.333333333336,"2024-05-03",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66436,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","60236","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2024,2024,18,19,"2024-05-03",45280.993055555555,"2024-05-06",45280.1875,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"oosterweel LO(sloop brug 5236, herpendueren BVL, renovatie brug 5237)\r\n\r\nalternatief weekend 31 (augustus)\r\n\r\nR-457514",null,null,60236,"2023-12-04","Medium","5,6"]
[null,"Infrabel","52880","Namur - Antwerpen","< >","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG",2024,2024,18,19,"2024-05-03",45280.993055555555,"2024-05-06",45280.166666666664,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Voorbereidingsweekend  1/2 Vernieuwing Y.Noord-Driehoek-Aarschot + vernieuwen duikers\r\nPlaatsen nieuwe BVL-palen en voorbereidingswerken sporen\r\n\r\n\r\nOverlegdossier: 2024 - L16 Y.Oost Driehoek Aarschot-Heist od Berg - 211109\r\n\r\nR-457569",null,null,52880,"2023-12-04","Medium","5,6"]
[null,"Infrabel","63438","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,18,18,"2024-05-03",45280.375,"2024-05-03",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-457510",null,null,63438,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","49171","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2024,2024,18,18,"2024-05-04",45280.333333333336,"2024-05-04",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie A  + maintenance infrastructure + contrôles\r\nUPM: 462054",null,null,49171,"2023-12-02","Minor","5,6"]
[null,"Infrabel","58048","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,18,19,"2024-05-04",45280,"2024-05-06",45280.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Engelse Leien vervolg vernieuwen wissels \r\nTLO L12+27A SPa +bundelkop C\r\n\r\nBundel C en Bundel E mee buiten spanning gaat tijdens de werken.\r\n\r\nR-457559",null,null,58048,"2023-12-04","Medium","5,6"]
[null,"Infrabel","58200","Namur - Antwerpen","< >","Y.MACHELEN","Y.WEERDE",2024,2024,18,19,"2024-05-04",45280,"2024-05-06",45280.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"afbraak trapkooien perrons 3+4 te Vilvoorde\r\nAfscherming dakstructuur op wanden\r\nVilvoorde sporen 3+4+5+6+7+8+9\r\n\r\nR-457574",null,null,58200,"2023-12-04","Medium","5,6"]
[null,"Infrabel","47148","Namur - Antwerpen","< >","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,18,19,"2024-05-04",45280.986111111109,"2024-05-06",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\npose portiques\r\nUPM 468238",null,null,47148,"2023-12-02","Minor","5,6"]
[null,"Infrabel","52735","Namur - Antwerpen","< >","MOUSTIER","Y.FLAWINNE",2024,2024,18,19,"2024-05-04",45280.986111111109,"2024-05-06",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement gare de Floreffe\r\nWE 6/6 Nuits\r\nDossier de concertation validé le 26 octobre 2021\r\n+CR2024 028-123\r\nextension de la mise hors service MHS :\r\n• Des voies accessoires voie A côté Flawinne.\r\nUPM: 462057",null,null,52735,"2023-12-04","Minor","5,6"]
[null,"Infrabel","60276","Namur - Antwerpen","< >","LEUVEN","SINT-JORIS-WEERT",2024,2024,18,19,"2024-05-04",45280.25,"2024-05-06",45280.222222222219,"2d, 23:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"vernieuwing rails Harmelen OW2 L139 + rails steken 139/1 +DL\r\n\r\nR-457515",null,null,60276,"2023-12-04","Medium","5,6"]
[null,"Infrabel","68243","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2024,2024,18,19,"2024-05-04",45280.25,"2024-05-06",45280.222222222219,"2d, 23:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2024-050: Renouvellement des PN31 et 32 - WE n°1\r\nUPM 465505",null,null,68243,"2023-12-13","Medium","5,6"]
[null,"Infrabel","49181","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2024,2024,18,18,"2024-05-05",45280.333333333336,"2024-05-05",45280.652777777781,"1d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie B + maintenance infrastructure + contrôles\r\nUPM : 462058",null,null,49181,"2023-12-02","Minor","5,6"]
[null,"Infrabel","61502","Namur - Antwerpen","< >","Y.WEERDE","Y.MUIZEN",2024,2024,18,18,"2024-05-05",45280.020833333336,"2024-05-05",45280.25,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossing wissels Muizen Rooster T - L27B\r\ndoodspoor 430 gaat mee BD + BS\r\n\r\nR-457576",null,null,61502,"2023-12-04","Minor","5,6"]
[null,"Infrabel","48402","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,19,19,"2024-05-06",45280.958333333336,"2024-05-10",45280.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement pièces caténaire \r\n+ Entretien",null,null,48402,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","66426","Athus - Meuse",">","GEDINNE","PALISEUL",2024,2024,19,19,"2024-05-06",45280.333333333336,"2024-05-06",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66426,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","47147","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,19,19,"2024-05-06",45280.979166666664,"2024-05-11",45280.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\npose poteaux",null,null,47147,"2023-12-08","Minor","1,2,3,4,5"]
[null,"Infrabel","64239","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,19,19,"2024-05-06",45280.972222222219,"2024-05-10",45280.208333333336,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-461909\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nTLO L50A6 - Bundel L/M vrij\r\nPerron I tot IV buiten dienst\r\n\r\n(alternatief stappenplan)",null,null,64239,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","49150","Lille - Charleroi","< >","ATH","TOURNAI",2024,2024,19,19,"2024-05-06",45280.972222222219,"2024-05-10",45280.1875,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 70 et 80\r\n+ Renforcement de 7 PI entre les km 54.992 et 63.375 sur la L94\r\nPhase 1.1 : PI 1+2\r\nUPM 446355\r\n04h30 ALD 04h40 pour RE3204",null,null,49150,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","55563","Namur - Antwerpen","< >","OTTIGNIES","LODELINSART",2024,2024,19,19,"2024-05-06",45280.965277777781,"2024-05-10",45280.215277777781,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Pi métalliques 52.015 et 52.215\r\nPréparations\r\nUPM 460977",null,null,55563,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","61198","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2024,2024,19,19,"2024-05-06",45280.944444444445,"2024-05-11",45280.173611111109,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.54\r\n+ Maintenance Z7.54 P3HKM\r\nUPM 464444",null,null,61198,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","47500","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2024,2024,19,22,"2024-05-06",45280.25,"2024-05-27",45280.208333333336,"21d, 23:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement quais de Gendron-Celles (suite ripage voies) et stabilisation talus et parois rocheuses + rectification de tracé Gendron - Houyet\r\nUPM : 462737",null,null,47500,"2023-12-06","High","1,2,3,4,5,6,7"]
[null,"Infrabel","61051","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,19,19,"2024-05-06",45280.989583333336,"2024-05-10",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service\r\nUPM 465575",null,null,61051,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","62127","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2024,2024,19,19,"2024-05-06",45280.993055555555,"2024-05-09",45280.215277777781,"3d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\nZGG.23 : studie nog uit te voeren door I-CBE & ZFF.23 : studie nog uit te voeren door I-CBE\r\n\r\nR-457723",null,null,62127,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","58970","Namur - Antwerpen","< >","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG",2024,2024,19,19,"2024-05-06",45280.993055555555,"2024-05-10",45280.1875,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers\r\n\r\n+ 2 WE voorbereiding en 2 WE afwerking\r\n\r\nR-457728",null,null,58970,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","49714","Namur - Antwerpen","< >","RHISNES","GEMBLOUX",2024,2024,19,19,"2024-05-06",45280.993055555555,"2024-05-11",45280.180555555555,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"traverses\r\nUPM 474881",null,null,49714,"2023-12-08","Minor","1,2,3,4,5"]
[null,"Infrabel","65341","Namur - Antwerpen",">","Y.MELLE-WEST","MERELBEKE-ROOSTER S",2024,2024,19,19,"2024-05-06",45280.395833333336,"2024-05-08",45280.645833333336,"3d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-464522\r\nreservatie onderhoud\r\ndagdienst zone 1\r\nL50E SP B Y Melle West AW02BT niet inbegrepen tot inrit Merelbeke rooster S AW01AS niet inbegrepen\r\nBVL: 29164",null,null,65341,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","55938","Erquelinnes - Montzen","< >","Y.NORD","ERQUELINNES-FRONTIERE",2024,2024,19,19,"2024-05-06",45280.940972222219,"2024-05-08",45280.173611111109,"2d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Y.La Sambre\r\nTravaux préparatoires caténaire (traverses)\r\n+ Travaux voie A signalisation\r\nUPM 442729",null,null,55938,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","65416","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2024,2024,19,19,"2024-05-06",45280.381944444445,"2024-05-06",45280.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41 (à répéter toutes les 6 semaines, le lundi)",null,null,65416,"2023-11-28","Minor","1,2,3,4,5"]
[null,"Infrabel","66430","Athus - Meuse",">","PALISEUL","GEDINNE",2024,2024,19,19,"2024-05-07",45280.333333333336,"2024-05-07",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66430,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","65837","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","GENT-DAMPOORT",2024,2024,19,19,"2024-05-07",45280.027777777781,"2024-05-09",45280.184027777781,"3d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-469305\r\nETCS L2-IL_NW_P025_P026_L59_Y Sint Bernadettestraat - Berchem_ETCS\r\nTesten, meewerken niet mogelijk\r\n\r\n\r\n*OLH Hemelvaart niet inbegrepen",null,null,65837,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","60234","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2024,2024,19,19,"2024-05-07",45280,"2024-05-10",45280.1875,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"oosterweel LO(sloop brug 5236, herpendueren BVL, renovatie brug 5237)\r\n\r\nalternatief week 32 (augustus)\r\n\r\nR-457729",null,null,60234,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","65856","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2024,2024,19,19,"2024-05-07",45280.013888888891,"2024-05-09",45280.180555555555,"3d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-460425\r\nETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\n\r\nTesten, meewerken niet mogelijk",null,null,65856,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","67203","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,19,19,"2024-05-08",45280.375,"2024-05-08",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,67203,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","60092","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,19,19,"2024-05-08",45280.395833333336,"2024-05-08",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn\r\n\r\nR-457743",null,null,60092,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","65981","Athus - Meuse",">","DINANT","Y.NEFFE",2024,2024,19,19,"2024-05-08",45280.34375,"2024-05-08",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites\r\nUPM 463467",null,null,65981,"2023-12-08","Minor","1,2,3,4,5"]
[null,"Infrabel","66421","Athus - Meuse",">","VONECHE","GEDINNE",2024,2024,19,19,"2024-05-09",45280.333333333336,"2024-05-09",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,66421,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","61620","Athus - Meuse","< >","BERTRIX","VIRTON",2024,2024,19,19,"2024-05-09",45280.006944444445,"2024-05-12",45280.75,"4d, 17:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"AI46 : Assainissement VA BK de 91.000 à 91.100 + Remplacement ballast et traverses VA de 94.975 à 95.218 (Th Marechal et M Minet)\r\nAI45 : Remplacement de rail entre Bertrix et Straimont sur voie A (G Depierreux)\r\n+visites Bertrix - Straimont\r\nUPM : 4663",null,null,61620,"2023-12-06","Medium","1,2,3,4,5,6,7"]
[null,"Infrabel","47496","Athus - Meuse","< >","ANSEREMME","HOUYET",2024,2024,19,19,"2024-05-09",45280.006944444445,"2024-05-12",45280.770833333336,"4d, 18:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement tabliers métalliques du PI 10.176 en gare de Gendron-Celles (tabliers voies 1, 2 et 3) – ripage voies et caténaires au droit des tabliers\r\nUPM: 462646",null,null,47496,"2023-12-06","Medium","1,2,3,4,5,6,7"]
[null,"Infrabel","53304","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2024,2024,19,20,"2024-05-09",45280.020833333336,"2024-05-13",45280.166666666664,"4d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-439482\r\nIDS SIW L75-FGSP - De Pinte\r\nGEEN ANDERE WERKEN MOGELIJK",null,null,53304,"2023-10-18","Medium","5,6"]
[null,"Infrabel","60766","Lille - Charleroi",">","CHARLEROI-CENTRAL","Y.NORD",2024,2024,19,19,"2024-05-09",45280.375,"2024-05-09",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rév 25G + 24BG\r\nUPM 466364\r\n09h00 - 15h00 après heure de pointe",null,null,60766,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","65342","Namur - Antwerpen","< >","MERELBEKE-ROOSTER S","Y.OOST DRIEHOEK LEDEBERG",2024,2024,19,19,"2024-05-09",45280.395833333336,"2024-05-10",45280.645833333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-464525\r\nreservatie onderhoud\r\ndagdienst zone 2\r\nL50E SP A Merelbeke rooster S sein EX-S.6 tot Y Oost Driehoek Ledeberg 10AR niet inbegrepen\r\nL50E SP B Merelbeke rooster S sein F-S.6 tot Y Oost Driehoek Ledeberg 03XR niet inbegrepen\r\nBVL: niet mogelijk",null,null,65342,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","60278","Namur - Antwerpen","< >","LEUVEN","SINT-JORIS-WEERT",2024,2024,19,20,"2024-05-10",45280.958333333336,"2024-05-13",45280.222222222219,"2d, 06:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"vernieuwing rails Harmelen OW2 L139 + rails steken 139/1 +DL\r\n\r\nof werken doorgaan dit weekend hangt af van massificatie onderhoud arr 44 (colt 50702)\r\n\r\nR-469330",null,null,60278,"2023-12-05","Medium","5,6"]
[null,"Infrabel","66423","Athus - Meuse",">","GEDINNE","VONECHE",2024,2024,19,19,"2024-05-10",45280.333333333336,"2024-05-10",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66423,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","49114","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,19,20,"2024-05-10",45280.979166666664,"2024-05-13",45280.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z3. 51  P4+\r\n+ Renouvellement Pi métalliques 52.015 et 52.215\r\nUPM 460185",null,null,49114,"2023-12-05","Medium","5,6"]
[null,"Infrabel","49414","Lille - Charleroi","< >","ATH","TOURNAI",2024,2024,19,20,"2024-05-10",45280.972222222219,"2024-05-13",45280.1875,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 70 et 80\r\n+ Renforcement de 7 PI entre les km 54.992 et 63.375 sur la L94\r\nPhase 1.2 : PI 1+2\r\nConstruction d'un PI dans le cadre de la suppression du PN30\r\nPhase 1.1 : Mise en œuvre de palplanches\r\nUPM 446361\r\n04h30 ALD 04h40 pour RE3",null,null,49414,"2023-12-06","Medium","5,6"]
[null,"Infrabel","60237","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2024,2024,19,20,"2024-05-10",45280.993055555555,"2024-05-13",45280.1875,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"oosterweel LO(sloop brug 5236, herpendueren BVL, renovatie brug 5237)\r\n\r\n\r\nalternatief weekend 32 (augustus)",null,null,60237,"2023-10-20","Medium","5,6"]
[null,"Infrabel","68244","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2024,2024,19,20,"2024-05-10",45280.993055555555,"2024-05-13",45280.222222222219,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2024-050: Renouvellement des PN31 et 32 - WE n°2 - bourrage de révision, contraintes,...\r\nUPM 465506",null,null,68244,"2023-12-14","Medium","5,6"]
[null,"Infrabel","66414","Athus - Meuse",">","VONECHE","BEAURAING",2024,2024,19,19,"2024-05-11",45280.333333333336,"2024-05-11",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66414,"2023-12-06","Minor","5,6"]
[null,"Infrabel","58049","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,19,20,"2024-05-11",45280,"2024-05-13",45280.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Engelse Leien vervolg vernieuwen wissels \r\nTLO L12+27A SPa +bundelkop C\r\n\r\nBundel C en Bundel E mee buiten spanning gaat tijdens de werken.\r\n\r\nR-457882",null,null,58049,"2023-12-05","Medium","5,6"]
[null,"Infrabel","64866","Lille - Antwerpen",">","SINT-NIKLAAS","LOKEREN",2024,2024,19,19,"2024-05-11",45280.013888888891,"2024-05-11",45280.222222222219,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-465276\r\nReservatie onderhoud",null,null,64866,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","62381","Athus - Meuse","< >","NAMUR","JAMBES-EST",2024,2024,19,19,"2024-05-11",45280.986111111109,"2024-05-12",45280.208333333336,"1d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Transfert des alimentations des loges en gare de Namur en vue du renouvellement de celle-ci\r\nLoges H3 et H4 mise hors service",null,null,62381,"2023-12-08","Minor","5,6"]
[null,"Infrabel","68824","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2024,2024,19,19,"2024-05-11",45280.3125,"2024-05-11",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY (à répéter toutes les 4 semaines le samedi)",null,null,68824,"2023-12-11","Minor","5,6"]
[null,"Infrabel","52879","Namur - Antwerpen","< >","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG",2024,2024,19,20,"2024-05-11",45280.041666666664,"2024-05-13",45280.166666666664,"2d, 03:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Voorbereidingsweekend  2/2 Vernieuwing Y.Noord-Driehoek-Aarschot\r\nPlaatsen nieuwe BVL-palen en voorbereidingswerken sporen\r\nDossier: 2024 - L16 Y.Oost Driehoek Aarschot-Heist od Berg - 211109\r\n\r\nR-457885",null,null,52879,"2023-12-05","Medium","5,6"]
[null,"Infrabel","67589","Athus - Meuse",">","VIRTON","SIGNEULX",2024,2024,19,19,"2024-05-11",45280.375,"2024-05-11",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,67589,"2023-12-06","Minor","5,6"]
[null,"Infrabel","57907","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2024,2024,19,19,"2024-05-11",45280.5,"2024-05-12",45280.500694444447,"1d, 00:01h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF CHA24_0027268 \r\nLille Tourcoing : REGE - Remplacement du joint entre les deux tabliers TPE Pra km 5.921\r\nUPM 460066",null,null,57907,"2023-12-06","Medium","5,6"]
[null,"Infrabel","66419","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,19,19,"2024-05-12",45280.333333333336,"2024-05-12",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,66419,"2023-12-06","Minor","5,6"]
[null,"Infrabel","50702","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,19,20,"2024-05-12",45280.027777777781,"2024-05-13",45280.1875,"2d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44\r\nUPM 474888",null,null,50702,"2023-12-14","Minor","5,6"]
[null,"Infrabel","61596","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2024,2024,19,19,"2024-05-12",45280.25,"2024-05-12",45280.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,61596,"2023-01-02","Medium","5,6"]
[null,"Infrabel","68823","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2024,2024,19,19,"2024-05-12",45280.3125,"2024-05-12",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY (à répéter toutes les 4 semaines le dimanche)",null,null,68823,"2023-12-11","Minor","5,6"]
[null,"Infrabel","50624","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,19,20,"2024-05-12",45280.034722222219,"2024-05-13",45280.222222222219,"2d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris\r\nUPM 467461",null,null,50624,"2023-12-14","Minor","5,6"]
[null,"Infrabel","67590","Athus - Meuse",">","SIGNEULX","VIRTON",2024,2024,19,19,"2024-05-12",45280.375,"2024-05-12",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,67590,"2023-12-06","Minor","5,6"]
[null,"Infrabel","64614","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2024,2024,20,20,"2024-05-13",45280.958333333336,"2024-05-18",45280.180555555555,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-464114\r\nOnderhoudswerken\r\nFGDM niet IN.",null,null,64614,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","56667","Erquelinnes - Montzen",">","BRESSOUX","FROIDMONT",2024,2024,20,20,"2024-05-13",45280.333333333336,"2024-05-13",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Cette visite se fait le même lundi que la visite entre Visé-Bas et Frontière NS prévue l'après-midi\r\n- Visite de voie, tunnel et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56667,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","57991","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2024,2024,20,20,"2024-05-13",45280.333333333336,"2024-05-18",45280.1875,"5d, 20:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveaux - pistes à l'aide de grues ferroviaires 10T entre bK 1.320 et 1.900.\r\nPas de S460 nécessaire.",null,null,57991,"2023-11-29","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","50591","Namur - Antwerpen",">","AUVELAIS","MOUSTIER-GARAGE",2024,2024,20,20,"2024-05-13",45280.979166666664,"2024-05-18",45280.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie",null,null,50591,"2023-12-08","Minor","1,2,3,4,5"]
[null,"Infrabel","63268","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2024,2024,20,20,"2024-05-13",45280.951388888891,"2024-05-18",45280.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-468407\r\nBuitenwerken, meewerken mogelijk, CTL spoor A+B\r\nIL for ETCS_IL-SML_NO_L53_Mechelen - Londerzeel\r\n+\r\nReservatie onderhoud",null,null,63268,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","57127","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,20,20,"2024-05-13",45280.965277777781,"2024-05-18",45280.166666666664,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-431071\r\nTLO-nachten voor TESTEN ETCS\r\n2 weken aansluitend nachten in mei 2024\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk",null,null,57127,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","55565","Namur - Antwerpen","< >","OTTIGNIES","LODELINSART",2024,2024,20,20,"2024-05-13",45280.965277777781,"2024-05-18",45280.215277777781,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Pi métalliques 52.015 et 52.215\r\nNuit pour soudures\r\nUPM 461158",null,null,55565,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","61052","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,20,20,"2024-05-13",45280.989583333336,"2024-05-17",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service\r\nUPM 465759",null,null,61052,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","58979","Namur - Antwerpen","< >","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG",2024,2024,20,20,"2024-05-13",45280.993055555555,"2024-05-17",45280.1875,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers\r\n\r\nR-457914",null,null,58979,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","49715","Namur - Antwerpen","< >","RHISNES","GEMBLOUX",2024,2024,20,20,"2024-05-13",45280.993055555555,"2024-05-17",45280.180555555555,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"traverses",null,null,49715,"2023-12-08","Minor","1,2,3,4,5"]
[null,"Infrabel","67727","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2024,2024,20,20,"2024-05-13",45280.385416666664,"2024-05-13",45280.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,67727,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","67719","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-FRANCE",2024,2024,20,20,"2024-05-13",45280.375,"2024-05-13",45280.583333333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite voie unique L 165/2 \r\nVisite voie unique L 165/3\r\nVisite voie unique L 165/1\r\nMaintenance",null,null,67719,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","61680","Erquelinnes - Montzen",">","AMAY","RACC.DUMONT-WAUTHIER",2024,2024,20,20,"2024-05-13",45280.375,"2024-05-17",45280.625,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement pièces caténaire",null,null,61680,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","66934","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2024,2024,20,20,"2024-05-13",45280.378472222219,"2024-05-13",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,66934,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","56672","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2024,2024,20,20,"2024-05-13",45280.5,"2024-05-13",45280.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Cette visite se fait le même lundi que la visite entre Froidmont et Bressoux prévue l'avant-midi\r\n- Visite de voie, PN et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56672,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","49238","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,20,20,"2024-05-13",45280.923611111109,"2024-05-17",45280.173611111109,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS Y. La Sambre\r\nTravaux préparatoires caténaire\r\n+ Maintenance Z2. 51  P3 HKV\r\n+ Travaux voie A signalisation\r\nUPM 442746\r\nEn corrélation avec CTL L132 Colt 49239 - UPM 441727 (Nuits du 13^14/05 à 24^25/05/24)",null,null,49238,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","65945","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2024,2024,20,20,"2024-05-13",45280.409722222219,"2024-05-13",45280.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance\r\nRq333: +1 sem suite CTL L165",null,null,65945,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","60235","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","Y.MELSELE",2024,2024,20,20,"2024-05-14",45280,"2024-05-17",45280.1875,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"oosterweel LO(sloop brug 5236, herpendueren BVL, renovatie brug 5237)\r\n\r\n\r\nalternatief week 33 (augustus)\r\n\r\nR-457922",null,null,60235,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","71153","Namur - Antwerpen","< >","LONDERZEEL","SCHELLEBELLE",2024,2024,20,20,"2024-05-14",45280.010416666664,"2024-05-17",45280.190972222219,"4d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP Dendermonde\r\nWeeknachten\r\nR-478519",null,null,71153,"2023-11-27","Minor","1,2,3,4,5"]
[null,"Infrabel","65357","Namur - Antwerpen","< >","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2024,2024,20,20,"2024-05-14",45280.003472222219,"2024-05-18",45280.194444444445,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-463062\r\nreservatie onderhoud\r\nnacht schets  6 + TLO L50E (kan volgens CBP)\r\nL50 SP B Schellebelle AW23W niet inbegrepen tot Y Melle West 01AT niet inbegrepen\r\nL50E SP A+B Y Melle West inbegrepen, inrit Merelbeke kant Gent niet inbegrepen",null,null,65357,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","66935","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2024,2024,20,20,"2024-05-14",45280.378472222219,"2024-05-14",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,66935,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","56676","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,20,20,"2024-05-14",45280.395833333336,"2024-05-14",45280.611111111109,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Visite de voie, PN et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56676,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","66929","Athus - Meuse",">","HALANZY","Y.AUBANGE",2024,2024,20,20,"2024-05-15",45280.375,"2024-05-15",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,66929,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","65921","Athus - Meuse",">","LAVAUX","MARBEHAN",2024,2024,20,20,"2024-05-15",45280.361111111109,"2024-05-15",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65921,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","65913","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2024,2024,20,20,"2024-05-16",45280.368055555555,"2024-05-16",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65913,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","67201","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2024,2024,20,20,"2024-05-16",45280.375,"2024-05-16",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A\r\nEntretien / maintenance voie A",null,null,67201,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","64375","Namur - Antwerpen",">","NAMUR","RHISNES",2024,2024,20,20,"2024-05-17",45280.958333333336,"2024-05-18",45280.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nUPM 459443",null,null,64375,"2023-12-13","Minor","1,2,3,4,5"]
[null,"Infrabel","49709","Namur - Antwerpen",">","RHISNES","GEMBLOUX",2024,2024,20,21,"2024-05-17",45280.958333333336,"2024-05-20",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"réélectrification\r\n+ Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles\r\nUPM 466864",null,null,49709,"2023-12-13","Minor","5,6"]
[null,"Infrabel","47855","Namur - Antwerpen","< >","LONDERZEEL","SCHELLEBELLE",2024,2024,20,21,"2024-05-17",45280.979166666664,"2024-05-21",45280.1875,"3d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-432312\r\nL53 + Dendermonde:  indienstname PLP (masterplan ETCS)\r\nWE1/3\r\ntussen de weekends zijn er beperkingen  in de versporingen (meerdere wissels blijven geklauwd na WE1)",null,null,47855,"2023-10-18","Medium","5,6"]
[null,"Infrabel","65905","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2024,2024,20,20,"2024-05-17",45280.368055555555,"2024-05-17",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65905,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","67202","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2024,2024,20,20,"2024-05-17",45280.375,"2024-05-17",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B\r\nEntretien / maintenance voie B",null,null,67202,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","67080","Lille - Charleroi",">","ATH","BRUGELETTE",2024,2024,20,20,"2024-05-17",45280.34375,"2024-05-17",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno\r\nUPM 464345",null,null,67080,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","46687","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,20,20,"2024-05-18",45280.958333333336,"2024-05-19",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance \r\nInterventions Programmées\r\nUPM : 466428",null,null,46687,"2023-12-06","Medium","5,6"]
[null,"Infrabel","47172","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,20,21,"2024-05-18",45280.958333333336,"2024-05-20",45280.1875,"1d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Electrification 2 x 25 kV\r\nUPM : 466024",null,null,47172,"2023-12-06","Medium","5,6"]
[null,"Infrabel","67493","Erquelinnes - Montzen",">","AMAY","ENGIS",2024,2024,20,20,"2024-05-18",45280.333333333336,"2024-05-18",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67493,"2023-03-29","Minor","1,2,3,4,5"]
[null,"Infrabel","58050","Namur - Antwerpen","< >","ANTWERPEN-OOST","Y.HOLLAND",2024,2024,20,21,"2024-05-18",45280,"2024-05-20",45280.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Engelse leien vervolg vernieuwen wissels \r\nTLO L12  + bundelkop bundel C\r\n\r\nBundel C en Bundel E mee buiten spanning gaat tijdens de werken.\r\n\r\nR-457993",null,null,58050,"2023-12-07","Medium","5,6"]
[null,"Infrabel","59714","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","ANTWERPEN-BERCHEM",2024,2024,20,21,"2024-05-18",45280.020833333336,"2024-05-20",45280.166666666664,"3d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud wissels Y Stadion , beveiliging L27\r\n\r\nhangt samen met colt 59710 L25\r\n\r\nR-458057",null,null,59714,"2023-12-07","Minor","5,6"]
[null,"Infrabel","61402","Namur - Antwerpen","< >","COUILLET","AUVELAIS",2024,2024,20,20,"2024-05-18",45280.965277777781,"2024-05-19",45280.25,"1d, 06:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-FS_SO_L130_FTM-FCL\r\nMES mai 2024\r\nPas de sous coupure possible (meewerken niet mogelijk)\r\nUPM 466281",null,null,61402,"2023-12-05","Minor","5,6"]
[null,"Infrabel","47149","Namur - Antwerpen","< >","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,20,21,"2024-05-18",45280.986111111109,"2024-05-20",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\npose portiques\r\nUPM 474884",null,null,47149,"2023-12-13","Minor","5,6"]
[null,"Infrabel","49873","Namur - Antwerpen","< >","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG",2024,2024,20,22,"2024-05-18",45280.041666666664,"2024-05-27",45280.1875,"9d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers\r\n\r\n+ 2 WE voorbereiding en 2 WE afwerking\r\n\r\nR-458067",null,null,49873,"2023-12-07","High","1,2,3,4,5,6,7"]
[null,"Infrabel","60444","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2024,2024,20,20,"2024-05-18",45280.996527777781,"2024-05-19",45280.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-464405\r\nOnderhoud L51 -51A-51B",null,null,60444,"2023-10-18","Minor","5,6"]
[null,"Infrabel","65937","Athus - Meuse",">","ARLON","Y.AUTELBAS",2024,2024,20,20,"2024-05-18",45280.361111111109,"2024-05-18",45280.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65937,"2023-12-04","Minor","5,6"]
[null,"Infrabel","73532","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2024,2024,20,20,"2024-05-18",45280.5,"2024-05-19",45280.500694444447,"1d, 00:01h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF CHA24_0027269\r\nTourcoing : REGE - Remplacement murs de soutènement Km 14,027 et 14,099\r\nUPM 483979",null,null,73532,"2023-12-06","Medium","5,6"]
[null,"Infrabel","67581","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,20,20,"2024-05-18",45280.388888888891,"2024-05-18",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses",null,null,67581,"2023-12-06","Minor","5,6"]
[null,"Infrabel","65330","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2024,2024,20,21,"2024-05-19",45280.958333333336,"2024-05-20",45280.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 3) 6 fois sur l'année\r\nUPM 459461",null,null,65330,"2023-12-13","Minor","1,2,3,4,5"]
[null,"Infrabel","58228","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","Y.HOLLAND",2024,2024,20,20,"2024-05-19",45280.25,"2024-05-19",45280.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"304 statiestraat , tussen Y laarsebeek en Y driehoekstraat\r\n\r\nR-458086",null,null,58228,"2023-12-07","Minor","5,6"]
[null,"Infrabel","57562","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","Y.SCHIJN",2024,2024,20,20,"2024-05-19",45280.25,"2024-05-19",45280.729166666664,"1d, 11:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Oude Landen\r\nproject 304",null,null,57562,"2023-08-18","Minor","5,6"]
[null,"Infrabel","65929","Athus - Meuse",">","MARBEHAN","HABAY",2024,2024,20,20,"2024-05-19",45280.375,"2024-05-19",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65929,"2023-12-04","Minor","5,6"]
[null,"Infrabel","66867","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2024,2024,20,20,"2024-05-19",45280.354166666664,"2024-05-19",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,66867,"2023-12-01","Minor","5,6"]
[null,"Infrabel","67583","Athus - Meuse",">","BEAURAING","HOUYET",2024,2024,20,20,"2024-05-19",45280.388888888891,"2024-05-19",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"visite et interventions diverses\r\nCR 2024-159 : VA ald VB",null,null,67583,"2023-12-06","Minor","5,6"]
[null,"Infrabel","61694","Erquelinnes - Montzen",">","LEMAN","TILLEUR",2024,2024,21,21,"2024-05-20",45280.958333333336,"2024-05-25",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement pièces caténaire",null,null,61694,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","50594","Namur - Antwerpen",">","AUVELAIS","MOUSTIER-GARAGE",2024,2024,21,21,"2024-05-20",45280.979166666664,"2024-05-24",45280.208333333336,"4d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie\r\nUPM 467342",null,null,50594,"2023-12-13","Minor","1,2,3,4,5"]
[null,"Infrabel","49413","Lille - Charleroi","< >","ATH","TOURNAI",2024,2024,21,21,"2024-05-20",45280.972222222219,"2024-05-25",45280.1875,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 70 et 80\r\nUPM 446359\r\n04h30 ALD 04h40 pour RE3204",null,null,49413,"2023-12-06","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","60120","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","Y.HOLLAND",2024,2024,21,21,"2024-05-20",45280.986111111109,"2024-05-24",45280.166666666664,"4d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderheid SIG Y luchtbal en onderhoud wissel Y Antwerpen-luchtbal\r\n\r\nR-458107",null,null,60120,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","51868","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,21,24,"2024-05-20",45280.25,"2024-06-10",45280.1875,"21d, 22:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Chantier peignage paroi\r\nProjet pâturage chèvre\r\nUPM : 466374",null,null,51868,"2023-12-06","High","1,2,3,4,5,6,7"]
[null,"Infrabel","49716","Namur - Antwerpen",">","RHISNES","GEMBLOUX",2024,2024,21,21,"2024-05-20",45280.996527777781,"2024-05-24",45280.180555555555,"4d, 04:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"poteaux\r\nUPM 474887",null,null,49716,"2023-12-13","Minor","1,2,3,4,5"]
[null,"Infrabel","47280","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,21,21,"2024-05-20",45280.375,"2024-05-24",45280.645833333336,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nPréparations\r\nUPM : 466560",null,null,47280,"2023-12-13","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","60764","Lille - Charleroi",">","CHARLEROI-CENTRAL","Y.NORD",2024,2024,21,21,"2024-05-20",45280.263888888891,"2024-05-20",45280.583333333336,"1d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rév 23G + 24AG\r\nUPM 466369",null,null,60764,"2023-12-05","Minor","5,6"]
[null,"Infrabel","60243","Namur - Antwerpen","< >","LEUVEN","WAVRE",2024,2024,21,21,"2024-05-21",45280.958333333336,"2024-05-25",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud\r\n\r\nR-458108",null,null,60243,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","49512","Namur - Antwerpen","< >","FLEURUS","OTTIGNIES",2024,2024,21,21,"2024-05-21",45280.958333333336,"2024-05-25",45280.197916666664,"4d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z3. 51  P3  HKV\r\n+ Renouvellement complet des Passages à niveau \r\n+ Renouvellement Pi métalliques 52.015 et 52.215\r\nUPM 466803",null,null,49512,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","50634","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,21,21,"2024-05-21",45280.979166666664,"2024-05-25",45280.222222222219,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nP3 HKM\r\nUPM 467462",null,null,50634,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","63269","Namur - Antwerpen","< >","LONDERZEEL","Y.HEIKE",2024,2024,21,21,"2024-05-21",45280.951388888891,"2024-05-25",45280.201388888891,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Buitenwerken, meewerken mogelijk, CTL spoor A+B\r\nIL for ETCS_IL-SML_NO_L53_Mechelen - Londerzeel\r\n\r\n(beperkt tot Heike wegens masterplan FM)",null,null,63269,"2022-12-13","Minor","1,2,3,4,5"]
[null,"Infrabel","61204","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","LAUWE",2024,2024,21,21,"2024-05-21",45280.951388888891,"2024-05-25",45280.236111111109,"4d, 06:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z3.54\r\n+ Maintenance Z8.54\r\nUPM 464331",null,null,61204,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","57137","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2024,2024,21,21,"2024-05-21",45280.965277777781,"2024-05-25",45280.166666666664,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-431073\r\nTLO-nachten voor TESTEN ETCS\r\n2 weken aansluitend nachten in mei 2024\r\nbuiten dienst van inritseinen Moeskroen tot inritseinen Kortrijk\r\nsamenwerken NIET mogelijk\r\n\r\n*Pinkstermaandag niet in",null,null,57137,"2023-10-24","Minor","1,2,3,4,5"]
[null,"Infrabel","50723","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,21,21,"2024-05-21",45280.986111111109,"2024-05-25",45280.1875,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44\r\nUPM 467784",null,null,50723,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","63375","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2024,2024,21,21,"2024-05-21",45280.375,"2024-05-21",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-458113",null,null,63375,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","67090","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2024,2024,21,21,"2024-05-21",45280.354166666664,"2024-05-21",45280.666666666664,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno\r\nUPM 464348",null,null,67090,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","65826","Namur - Antwerpen","< >","Y.NOORD DRIEHOEK LEDEBERG","WONDELGEM",2024,2024,21,21,"2024-05-22",45280.027777777781,"2024-05-25",45280.180555555555,"4d, 03:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS L2-IL_NW_P024_L58_Merelbeke - Y Sint Bernadettestraat_ETCS\r\nBuitenwerken, meewerken mogelijk\r\nFGDM IN\r\nL58 tot Y Oost Drieheok Ledeberg vrij\r\nL58/1 tot Y West driehoek Ledeberg vrij\r\nL59 SP A tot Y Sint Bernadette vrij\r\nL59 SP B tot rooster Oostakk",null,null,65826,"2023-03-13","Minor","1,2,3,4,5"]
[null,"Infrabel","63399","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,21,21,"2024-05-22",45280.375,"2024-05-22",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-458156",null,null,63399,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","66435","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,21,21,"2024-05-23",45280.333333333336,"2024-05-23",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66435,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","63421","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,21,21,"2024-05-23",45280.375,"2024-05-23",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-458160",null,null,63421,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","55945","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,21,21,"2024-05-23",45280.395833333336,"2024-05-23",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53 + Visite Diagno\r\nMise HS en P2\r\nUPM 459759",null,null,55945,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","66437","Athus - Meuse",">","BERTRIX","PALISEUL",2024,2024,21,21,"2024-05-24",45280.333333333336,"2024-05-24",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66437,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","47859","Namur - Antwerpen","< >","LONDERZEEL","SCHELLEBELLE",2024,2024,21,22,"2024-05-24",45280.979166666664,"2024-05-27",45280.1875,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-432315\r\nL53/60 Dendermonde:  indienstname PLP (masterplan ETCS)\r\nWE2/3\r\ntussen de weekends zijn er beperkingen  in de versporingen (meerdere wissels blijven geklauwd na WE1)",null,null,47859,"2023-10-24","Medium","5,6"]
[null,"Infrabel","49893","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,21,22,"2024-05-24",45280.979166666664,"2024-05-27",45280.25,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 1/4 (AS 21Q, 22Q)\r\nUPM : 466564",null,null,49893,"2023-12-13","Medium","5,6"]
[null,"Infrabel","63439","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,21,21,"2024-05-24",45280.375,"2024-05-24",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen\r\n\r\nR-458161",null,null,63439,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","58051","Namur - Antwerpen","< >","ANTWERPEN-OOST","Y.HOLLAND",2024,2024,21,22,"2024-05-25",45280,"2024-05-27",45280.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Engelse leien vervolg vernieuwen wissels \r\nTLO L12 + bundelkop bundel C\r\n\r\nBundel C en Bundel E mee buiten spanning gaat tijdens de werken.\r\n\r\nR-458229",null,null,58051,"2023-12-12","Medium","5,6"]
[null,"Infrabel","62384","Athus - Meuse","< >","NAMUR","JAMBES-EST",2024,2024,21,21,"2024-05-25",45280.986111111109,"2024-05-26",45280.208333333336,"1d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Transfert des alimentations des loges en gare de Namur en vue du renouvellement de celle-ci\r\nLoges H3 et H4 remise en service\r\nUPM 462866",null,null,62384,"2023-12-13","Minor","5,6"]
[null,"Infrabel","47150","Namur - Antwerpen","< >","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,21,22,"2024-05-25",45280.986111111109,"2024-05-27",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\npose portiques\r\nUPM 468242",null,null,47150,"2023-12-13","Minor","5,6"]
[null,"Infrabel","47497","Athus - Meuse","< >","NAMUR","LUSTIN",2024,2024,21,21,"2024-05-25",45280.25,"2024-05-26",45280.75,"2d, 12:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mise au gabarit des pistes dans le tronçon Namur - Lustin. \r\nUPM : 462657",null,null,47497,"2023-12-13","Medium","5,6"]
[null,"Infrabel","60553","Athus - Meuse","< >","ANSEREMME","HOUYET",2024,2024,21,22,"2024-05-25",45280.25,"2024-05-27",45280.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse\r\nUPM : 462878",null,null,60553,"2023-12-06","Medium","5,6"]
[null,"Infrabel","66688","Namur - Antwerpen","< >","MECHELEN","HAACHT",2024,2024,21,21,"2024-05-25",45280.996527777781,"2024-05-26",45280.239583333336,"1d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Raillossing ter voorbereiding van vernieuwing Muizen Rooster T\r\nPlanning rails-Schaarbeek moeilijk verplaatsbaar.\r\n\r\nR-469014",null,null,66688,"2023-12-12","Minor","5,6"]
[null,"Infrabel","48899","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2024,2024,21,21,"2024-05-26",45280.333333333336,"2024-05-26",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nOttignies gare  voie 1 à 5 en alternance\r\nUPM 467718",null,null,48899,"2023-12-15","Minor","5,6"]
[null,"Infrabel","50625","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,21,22,"2024-05-26",45280.034722222219,"2024-05-27",45280.222222222219,"2d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris\r\nUPM 467528",null,null,50625,"2023-12-15","Minor","5,6"]
[null,"Infrabel","63270","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2024,2024,22,22,"2024-05-27",45280.958333333336,"2024-06-01",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-468412\r\nBuitenwerken, meewerken mogelijk, CTL spoor A+B\r\nIL for ETCS_IL-SML_NO_L53_Mechelen - Londerzeel",null,null,63270,"2023-10-24","Minor","1,2,3,4,5"]
[null,"Infrabel","49048","Namur - Antwerpen",">","NAMUR","FLAWINNE",2024,2024,22,22,"2024-05-27",45280.333333333336,"2024-05-27",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nUPM 467236",null,null,49048,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","66427","Athus - Meuse",">","GEDINNE","PALISEUL",2024,2024,22,22,"2024-05-27",45280.333333333336,"2024-05-27",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66427,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","47151","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,22,22,"2024-05-27",45280.979166666664,"2024-06-01",45280.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nmassifs\r\nUPM 468243",null,null,47151,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","50718","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,22,22,"2024-05-27",45280.965277777781,"2024-05-31",45280.1875,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44\r\nUPM 467787",null,null,50718,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","49718","Namur - Antwerpen",">","RHISNES","GEMBLOUX",2024,2024,22,22,"2024-05-27",45280.993055555555,"2024-05-31",45280.208333333336,"4d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"poteaux\r\nUPM 474891",null,null,49718,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","58981","Namur - Antwerpen","< >","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG",2024,2024,22,22,"2024-05-27",45280.993055555555,"2024-05-31",45280.1875,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers\r\n\r\nR-458268",null,null,58981,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","69970","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,22,22,"2024-05-27",45280.361111111109,"2024-05-31",45280.631944444445,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-122\r\nRenouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont",null,null,69970,"2023-10-09","Minor","1,2,3,4,5"]
[null,"Infrabel","48960","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2024,2024,22,22,"2024-05-27",45280.319444444445,"2024-05-27",45280.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance\r\nUPM 467734",null,null,48960,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","66431","Athus - Meuse",">","PALISEUL","GEDINNE",2024,2024,22,22,"2024-05-28",45280.333333333336,"2024-05-28",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66431,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","62873","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2024,2024,22,22,"2024-05-29",45280.013888888891,"2024-05-29",45280.190972222219,"1d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen\r\nZ23.22 : studie nog uit te voeren door I-CBE\r\n\r\nR-458157",null,null,62873,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","68656","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2024,2024,22,22,"2024-05-29",45280.034722222219,"2024-05-30",45280.180555555555,"2d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-058\r\nR-466011\r\n\r\nReservatie Onderhoud nachtdienst Schets 3\r\nBuiten dienst \r\nFGSP Perronspoor I tem IV tot L50E SP A  tot 02BO niet inbegrepen + L50E SP B tot 05O niet inbegrepen \r\n+ verlengde van de perrons I+II kant kust L50A6 inbegrepen, L75 v",null,null,68656,"2023-12-18","Minor","1,2,3,4,5"]
[null,"Infrabel","63573","Erquelinnes - Montzen",">","JAVA","STATTE",2024,2024,22,22,"2024-05-29",45280.354166666664,"2024-05-29",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463081",null,null,63573,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","60093","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,22,22,"2024-05-29",45280.395833333336,"2024-05-29",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn\r\n\r\nR-458295",null,null,60093,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","66422","Athus - Meuse",">","VONECHE","GEDINNE",2024,2024,22,22,"2024-05-30",45280.333333333336,"2024-05-30",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,66422,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","60107","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,22,22,"2024-05-30",45280.986111111109,"2024-05-31",45280.236111111109,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z11.22\r\n\r\nR-457462",null,null,60107,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","63575","Erquelinnes - Montzen",">","JAVA","ANDENNE",2024,2024,22,22,"2024-05-30",45280.5625,"2024-05-30",45280.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463140",null,null,63575,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","67535","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2024,2024,22,22,"2024-05-30",45280.375,"2024-05-30",45280.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nUPM 463101",null,null,67535,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","66424","Athus - Meuse",">","GEDINNE","VONECHE",2024,2024,22,22,"2024-05-31",45280.333333333336,"2024-05-31",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66424,"2023-12-06","Minor","1,2,3,4,5"]
[null,"Infrabel","62631","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.NOORD BERCHEM",2024,2024,22,23,"2024-05-31",45280.979166666664,"2024-06-03",45280.1875,"2d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"TOS 2222: Onderhoud wissels Y Noord Groenenhoek\r\n\r\nR-458307",null,null,62631,"2023-12-15","Minor","5,6"]
[null,"Infrabel","57597","Namur - Antwerpen","< >","SCHELLEBELLE","LONDERZEEL",2024,2024,22,23,"2024-05-31",45280.979166666664,"2024-06-03",45280.1875,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-432318\r\nL53/60 Dendermonde:  indienstname PLP (masterplan ETCS)\r\nWE3/3\r\ntussen de weekends zijn er beperkingen  in de versporingen (meerdere wissels blijven geklauwd na WE1)\r\n+\r\nIDS - ETCS \r\nETCS_IL-SMI_NW_L53 FDR-B9\r\n\r\nGat voorzien op 1/6 tussen 17:0",null,null,57597,"2023-12-06","Medium","5,6"]
[null,"Infrabel","49894","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,22,23,"2024-05-31",45280.979166666664,"2024-06-03",45280.25,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 2/4 (AS 19BQ, 18Q)\r\n+ Visite de voie L144 + 130/1 + maintenance infrastructure + contrôles\r\nUPM : 466570",null,null,49894,"2023-12-14","Medium","5,6"]
[null,"Infrabel","53699","Namur - Antwerpen","< >","Y.OOST DRIEHOEK AARSCHOT","Y.NAZARETH",2024,2024,22,23,"2024-05-31",45280.993055555555,"2024-06-03",45280.1875,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Afwerkingsweekend 1/3 Vernieuwing Y.Noord-Driehoek-Aarschot+vernieuwen duikers\r\n\r\n\r\nDossier: 2024 - L16 Y.Oost Driehoek Aarschot-Heist od Berg - 211109\r\n\r\n+\r\n\r\nvernieuwen overwegen strail\r\n\r\nR-458300",null,null,53699,"2023-12-15","Medium","5,6"]
[null,"Infrabel","66415","Athus - Meuse",">","VONECHE","BEAURAING",2024,2024,22,22,"2024-06-01",45280.333333333336,"2024-06-01",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66415,"2023-12-06","Minor","5,6"]
[null,"Infrabel","58203","Namur - Antwerpen",">","Y.WEERDE","Y.MACHELEN",2024,2024,22,23,"2024-06-01",45280.020833333336,"2024-06-03",45280.166666666664,"2d, 03:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"afbraak trapkooien perrons Vilvoorde\r\nAfscherming dakstructuur op wanden\r\n\r\nVilvoorde sporen 4+5+6+7+8+9\r\n\r\nR-458390",null,null,58203,"2023-12-18","Minor","5,6"]
[null,"Infrabel","62385","Erquelinnes - Montzen","< >","NAMUR","MARCHE-LES-DAMES",2024,2024,22,22,"2024-06-01",45280.986111111109,"2024-06-02",45280.208333333336,"1d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Transfert des alimentations des loges en gare de Namur en vue du renouvellement de celle-ci\r\nVoies 3 - 4 - 11 en gare de Namur\r\nloge H5 et H6 mise hors service\r\nUPM 462687",null,null,62385,"2023-12-14","Minor","5,6"]
[null,"Infrabel","49166","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2024,2024,22,22,"2024-06-01",45280.986111111109,"2024-06-02",45280.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nMini CTL\r\nUPM 457338 voir avec SE",null,null,49166,"2023-12-05","Medium","5,6"]
[null,"Infrabel","50427","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2024,2024,22,22,"2024-06-01",45280.986111111109,"2024-06-02",45280.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\nUPM: 462061",null,null,50427,"2023-12-14","Medium","5,6"]
[null,"Infrabel","47152","Namur - Antwerpen","< >","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,22,23,"2024-06-01",45280.986111111109,"2024-06-03",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nportiques\r\nUPM 474885",null,null,47152,"2023-12-14","Minor","5,6"]
[null,"Infrabel","49499","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2024,2024,22,22,"2024-06-01",45280.25,"2024-06-02",45280.666666666664,"1d, 10:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 - Mise HS P4 + Diagno Zones 2 + 4\r\nUPM 459788",null,null,49499,"2023-12-06","Medium","5,6"]
[null,"Infrabel","66029","Athus - Meuse",">","JAMBES","LUSTIN",2024,2024,22,22,"2024-06-01",45280.385416666664,"2024-06-01",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463479",null,null,66029,"2023-12-14","Minor","5,6"]
[null,"Infrabel","58067","Namur - Antwerpen","< >","Y.SINT-MARIABURG","Y.LUCHTBAL",2024,2024,22,23,"2024-06-01",45280.003472222219,"2024-06-03",45280.166666666664,"2d, 03:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"304(statiestraat)+308 (herelectrificatie) oude landen\r\n\r\nR-458350\r\n\r\nSamen met CoLT 73595 (CR 2024-230) BLWB + spoor A L27A",null,null,58067,"2023-12-18","Medium","5,6"]
[null,"Infrabel","73595","Namur - Antwerpen",">","Y.HOLLAND","Y.DRIEHOEKSTRAAT",2024,2024,22,23,"2024-06-01",45280.003472222219,"2024-06-03",45280.166666666664,"2d, 03:55h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR2024-320\r\nuitbreiding op BDS L12 TLO\r\n308 (herelectrificatie) oude landen --> dringende vernieuwing inrit Bundel Luchtbal\r\ngevallen 22243+22224+22226 noodzakelijk (bijkomend aan L12)\r\n\r\nR-458350 (samen met CoLT 58067)",null,null,73595,"2023-12-18","Minor","5,6"]
[null,"Infrabel","66754","Lille - Charleroi",">","BRAINE-LE-COMTE","Y.FELUY",2024,2024,22,22,"2024-06-01",45280.34375,"2024-06-01",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique AI52 + AI53\r\nUPM 468168 - 468169",null,null,66754,"2023-12-06","Minor","5,6"]
[null,"Infrabel","48951","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2024,2024,22,22,"2024-06-01",45280.340277777781,"2024-06-02",45280.659722222219,"2d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles\r\nUPM 466940",null,null,48951,"2023-12-15","Minor","5,6"]
[null,"Infrabel","66420","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,22,22,"2024-06-02",45280.333333333336,"2024-06-02",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,66420,"2023-12-06","Minor","5,6"]
[null,"Infrabel","57563","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","Y.SCHIJN",2024,2024,22,22,"2024-06-02",45280.25,"2024-06-02",45280.729166666664,"1d, 11:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Oude Landen\r\nproject 304\r\n\r\nR-475419",null,null,57563,"2023-12-18","Minor","5,6"]
[null,"Infrabel","58229","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","Y.HOLLAND",2024,2024,22,22,"2024-06-02",45280.3125,"2024-06-02",45280.729166666664,"1d, 10:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"304 statiestraat , tussen Y laarsebeek en Y driehoekstraat\r\n\r\nR-458391",null,null,58229,"2023-12-18","Minor","5,6"]
[null,"Infrabel","66046","Athus - Meuse",">","LUSTIN","JAMBES",2024,2024,22,22,"2024-06-02",45280.385416666664,"2024-06-02",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463480",null,null,66046,"2023-12-14","Minor","5,6"]
[null,"Infrabel","64241","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,23,23,"2024-06-03",45280.979166666664,"2024-06-07",45280.1875,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-461914\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem VIII)\r\n\r\n(alternatief stappenplan)",null,null,64241,"2023-11-21","Minor","1,2,3,4,5"]
[null,"Infrabel","60936","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,23,23,"2024-06-03",45280.979166666664,"2024-06-08",45280.229166666664,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.52\r\nMise HS Zone 5 AI52 (Gare de Luttre)",null,null,60936,"2022-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","49362","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2024,2024,23,23,"2024-06-03",45280.9375,"2024-06-08",45280.208333333336,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z8. 51   P3 HKV",null,null,49362,"2022-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","50720","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,23,23,"2024-06-03",45280.965277777781,"2024-06-07",45280.1875,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44",null,null,50720,"2023-04-08","Minor","1,2,3,4,5"]
[null,"Infrabel","70138","Namur - Antwerpen","< >","MUIZEN-ROOSTER T","MUIZEN",2024,2024,23,23,"2024-06-03",45280.25,"2024-06-07",45280.645833333336,"4d, 09:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie werken bundel Muizen van zone 17 + 18 (T-wissels bundel Muizen)\r\nOnderstoppen wissels\r\n\r\nBuitendienststelling van wissels 10AT en 10BT tot voorbij de t-seinen van de bundelsporen.\r\nDe bundelsporen zouden telkens een 100m-150m ingekort moete",null,null,70138,"2023-10-16","Medium","1,2,3,4,5"]
[null,"Infrabel","71258","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2024,2024,23,24,"2024-06-03",45280.25,"2024-06-14",45280.666666666664,"11d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2024-159: Bourrage de révision et contraintes\r\nUPM 482647",null,null,71258,"2023-11-10","High","1,2,3,4,5,6,7"]
[null,"Infrabel","49719","Namur - Antwerpen",">","RHISNES","GEMBLOUX",2024,2024,23,23,"2024-06-03",45280.993055555555,"2024-06-07",45280.208333333336,"4d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"poteaux\r\nUPM 474895",null,null,49719,"2023-12-20","Minor","1,2,3,4,5"]
[null,"Infrabel","58983","Namur - Antwerpen","< >","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG",2024,2024,23,23,"2024-06-03",45280.993055555555,"2024-06-07",45280.1875,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Y.Noord-Driehoek-Aarschot\r\nVernieuwing duikers",null,null,58983,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","66741","Lille - Charleroi",">","SOIGNIES","NEUFVILLES",2024,2024,23,23,"2024-06-04",45280.333333333336,"2024-06-04",45280.541666666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B",null,null,66741,"2023-05-12","Minor","1,2,3,4,5"]
[null,"Infrabel","61964","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2024,2024,23,23,"2024-06-04",45280.003472222219,"2024-06-08",45280.201388888891,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FBMZ_16 en FBMZ_17 volgens onderhoudskalender Area CE\r\n\r\nL96 Spoor A tussen perron FBMZ en Y Ruisbroek\r\nnaastliggend spoor (Bypass)",null,null,61964,"2023-02-21","Minor","1,2,3,4,5"]
[null,"Infrabel","69262","Athus - Meuse",">","STOCKEM-NORD","ARLON",2024,2024,23,23,"2024-06-04",45280.361111111109,"2024-06-04",45280.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69262,"2023-05-22","Minor","1,2,3,4,5"]
[null,"Infrabel","69269","Athus - Meuse",">","HABAY","STOCKEM-NORD",2024,2024,23,23,"2024-06-05",45280.375,"2024-06-05",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69269,"2023-05-22","Minor","1,2,3,4,5"]
[null,"Infrabel","65982","Athus - Meuse",">","DINANT","Y.NEFFE",2024,2024,23,23,"2024-06-05",45280.34375,"2024-06-05",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites\r\nUPM 463487",null,null,65982,"2023-12-20","Minor","1,2,3,4,5"]
[null,"Infrabel","49311","Lille - Charleroi",">","LUTTRE","ROUX",2024,2024,23,23,"2024-06-06",45280.25,"2024-06-08",45280.25,"2d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Ré-électrification de la Gare de Luttre\r\nTravaux de pose caténaires L117 - L124A voie B\r\nentre R41/4 et R42/4\r\nUPM 457107",null,null,49311,"2023-03-22","Minor","1,2,3,4,5"]
[null,"Infrabel","66090","Athus - Meuse",">","YVOIR","DINANT",2024,2024,23,23,"2024-06-06",45280.385416666664,"2024-06-06",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES\r\nUPM 463490",null,null,66090,"2023-12-20","Minor","1,2,3,4,5"]
[null,"Infrabel","59724","Namur - Antwerpen",">","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,23,23,"2024-06-06",45280.416666666664,"2024-06-06",45280.625,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud SIG DOES",null,null,59724,"2022-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","49895","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,23,24,"2024-06-07",45280.979166666664,"2024-06-10",45280.25,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nWE 3/4 (AS 19AQ)\r\nUPM : 466573",null,null,49895,"2023-05-08","Medium","5,6"]
[null,"Infrabel","49119","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2024,2024,23,24,"2024-06-07",45280.986111111109,"2024-06-10",45280.208333333336,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4. 51  P4+\r\n+ Renouvellement complet des PN\r\nUPM 444780",null,null,49119,"2023-01-18","Medium","5,6"]
[null,"Infrabel","58984","Namur - Antwerpen","< >","Y.OOST DRIEHOEK AARSCHOT","HEIST-OP-DEN-BERG",2024,2024,23,24,"2024-06-07",45280.993055555555,"2024-06-10",45280.1875,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Afwerkingsweekend 2/3 Vernieuwing Y.Noord-Driehoek-Aarschot +vernieuwen duikers\r\n\r\n\r\nDossier: 2024 - L16 Y.Oost Driehoek Aarschot-Heist od Berg - 211109",null,null,58984,"2023-05-12","Medium","5,6"]
[null,"Infrabel","48870","Namur - Antwerpen",">","WAVRE","OTTIGNIES",2024,2024,23,23,"2024-06-08",45280.333333333336,"2024-06-08",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes+ maintenances infrastructure et contrôles\r\nUPM : 465246",null,null,48870,"2023-04-27","Minor","5,6"]
[null,"Infrabel","59006","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,23,24,"2024-06-08",45280.020833333336,"2024-06-10",45280.1875,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-438580\r\nMasterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)",null,null,59006,"2023-11-22","Medium","5,6"]
[null,"Infrabel","47154","Namur - Antwerpen","< >","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,23,24,"2024-06-08",45280.986111111109,"2024-06-10",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nportiques",null,null,47154,"2022-12-16","Minor","5,6"]
[null,"Infrabel","58641","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2024,2024,23,24,"2024-06-08",45280.25,"2024-06-10",45280.173611111109,"2d, 22:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Oude landen project 308+304",null,null,58641,"2023-02-17","Medium","5,6"]
[null,"Infrabel","67523","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2024,2024,23,23,"2024-06-08",45280.354166666664,"2024-06-08",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67523,"2023-04-06","Minor","5,6"]
[null,"Infrabel","48879","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2024,2024,23,23,"2024-06-09",45280.333333333336,"2024-06-09",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes - maintenances diverses et révisions\r\nUPM : 465275",null,null,48879,"2023-04-27","Minor","5,6"]
[null,"Infrabel","61597","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2024,2024,23,23,"2024-06-09",45280.25,"2024-06-09",45280.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,61597,"2022-10-26","Medium","5,6"]
[null,"Infrabel","49720","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2024,2024,24,24,"2024-06-10",45280.958333333336,"2024-06-14",45280.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"poteaux",null,null,49720,"2023-01-18","Minor","1,2,3,4,5"]
[null,"Infrabel","66932","Athus - Meuse",">","BERTRIX","STRAIMONT",2024,2024,24,24,"2024-06-10",45280.333333333336,"2024-06-10",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,66932,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","62486","Namur - Antwerpen","< >","SCHAERBEEK","MECHELEN",2024,2024,24,24,"2024-06-10",45280.979166666664,"2024-06-14",45280.1875,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\nZ02.23.01 : studie nog uit te voeren door I-CBE",null,null,62486,"2023-06-07","Minor","1,2,3,4,5"]
[null,"Infrabel","60925","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2024,2024,24,24,"2024-06-10",45280.951388888891,"2024-06-15",45280.194444444445,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.52",null,null,60925,"2022-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","49524","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2024,2024,24,24,"2024-06-10",45280.965277777781,"2024-06-15",45280.208333333336,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4. 51  P3  HKV",null,null,49524,"2022-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","63376","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2024,2024,24,24,"2024-06-11",45280.375,"2024-06-11",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63376,"2023-01-05","Minor","1,2,3,4,5"]
[null,"Infrabel","59725","Namur - Antwerpen",">","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,24,24,"2024-06-12",45280.416666666664,"2024-06-12",45280.625,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud SIG DOES",null,null,59725,"2022-07-06","Minor","1,2,3,4,5"]
[null,"Infrabel","66931","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,24,24,"2024-06-13",45280.375,"2024-06-13",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,66931,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","63422","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,24,24,"2024-06-13",45280.375,"2024-06-13",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63422,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","67204","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,24,24,"2024-06-14",45280.375,"2024-06-14",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,67204,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","57838","Athus - Meuse","< >","VIRTON","AUBANGE",2024,2024,24,24,"2024-06-15",45280.333333333336,"2024-06-16",45280.666666666664,"1d, 08:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Pose de caniveaux drainant (boueux)\r\nUPM : 466433",null,null,57838,"2023-05-05","Medium","5,6"]
[null,"Infrabel","62387","Erquelinnes - Montzen","< >","NAMUR","MARCHE-LES-DAMES",2024,2024,24,24,"2024-06-15",45280.986111111109,"2024-06-16",45280.208333333336,"1d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Transfert des alimentations des loges en gare de Namur en vue du renouvellement de celle-ci\r\nVoies A et B L125\r\nLoge N1 et N2 mise hors service",null,null,62387,"2023-04-08","Minor","5,6"]
[null,"Infrabel","65930","Athus - Meuse",">","MARBEHAN","HABAY",2024,2024,24,24,"2024-06-15",45280.375,"2024-06-15",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65930,"2023-02-28","Minor","5,6"]
[null,"Infrabel","68826","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2024,2024,24,24,"2024-06-16",45280.3125,"2024-06-16",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY (à répéter toutes les 4 semaines le dimanche)",null,null,68826,"2023-05-08","Minor","5,6"]
[null,"Infrabel","65380","Namur - Antwerpen","< >","NAMUR","RONET",2024,2024,24,24,"2024-06-16",45280.003472222219,"2024-06-16",45280.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur (ZONE 6)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,65380,"2023-02-08","Minor","5,6"]
[null,"Infrabel","66441","Athus - Meuse",">","GEDINNE","PALISEUL",2024,2024,25,25,"2024-06-17",45280.333333333336,"2024-06-17",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66441,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","57837","Athus - Meuse",">","HALANZY","AUBANGE",2024,2024,25,25,"2024-06-17",45280.333333333336,"2024-06-23",45280.666666666664,"6d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveaux drainant (boueux)\r\nUPM : 466407",null,null,57837,"2023-05-05","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","60937","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,25,25,"2024-06-17",45280.979166666664,"2024-06-22",45280.229166666664,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.52\r\nMise HS Zone 5 AI52 (Gare de Luttre)\r\n+ Ré-électrification de la gare de Luttre",null,null,60937,"2023-01-17","Minor","1,2,3,4,5"]
[null,"Infrabel","50721","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,25,25,"2024-06-17",45280.965277777781,"2024-06-22",45280.1875,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44",null,null,50721,"2022-12-16","Minor","1,2,3,4,5"]
[null,"Infrabel","66440","Athus - Meuse",">","PALISEUL","GEDINNE",2024,2024,25,25,"2024-06-18",45280.333333333336,"2024-06-18",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66440,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","65538","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2024,2024,25,25,"2024-06-19",45280.375,"2024-06-19",45280.645833333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Schouwen lopend spoor\r\nR-464328",null,null,65538,"2023-11-22","Minor","1,2,3,4,5"]
[null,"Infrabel","65922","Athus - Meuse",">","LAVAUX","MARBEHAN",2024,2024,25,25,"2024-06-19",45280.361111111109,"2024-06-19",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65922,"2023-02-21","Minor","1,2,3,4,5"]
[null,"Infrabel","60094","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,25,25,"2024-06-19",45280.395833333336,"2024-06-19",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn",null,null,60094,"2022-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","56276","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,25,25,"2024-06-20",45280.395833333336,"2024-06-20",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53 + Visite Diagno\r\nMise HS en P2\r\nUPM 459763",null,null,56276,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","58335","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2024,2024,25,26,"2024-06-21",45280.979166666664,"2024-06-24",45280.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"vernieuwen Muizen rooster T \r\n(samen met L27B)\r\n\r\nsecundair fietstunnel Willendries en ONB Willendriesbeek\r\n\r\nHerelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nVoorbereidingsweekend 2/3\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINA",null,null,58335,"2023-10-12","Medium","5,6"]
[null,"Infrabel","67494","Erquelinnes - Montzen",">","AMAY","ENGIS",2024,2024,25,25,"2024-06-22",45280.333333333336,"2024-06-22",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67494,"2023-03-29","Minor","1,2,3,4,5"]
[null,"Infrabel","56289","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2024,2024,25,25,"2024-06-22",45280.25,"2024-06-23",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z3.53 en P4\r\n+ Maintenance Zone Z09.52\r\nUPM 445247",null,null,56289,"2023-01-19","Medium","5,6"]
[null,"Infrabel","49182","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2024,2024,25,25,"2024-06-23",45280.333333333336,"2024-06-23",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie B + maintenance infrastructure + contrôles\r\nUPM : 462064",null,null,49182,"2023-11-17","Minor","5,6"]
[null,"Infrabel","50626","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,25,26,"2024-06-23",45280.034722222219,"2024-06-24",45280.222222222219,"2d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris",null,null,50626,"2023-01-16","Minor","5,6"]
[null,"Infrabel","49563","Lille - Charleroi",">","BRUGELETTE","BRUGELETTE",2024,2024,26,26,"2024-06-24",45280.333333333336,"2024-06-28",45280.9375,"5d, 14:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\nUPM 445802",null,null,49563,"2023-09-05","Minor","1,2,3,4,5"]
[null,"Infrabel","64004","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2024,2024,26,26,"2024-06-24",45280.979166666664,"2024-06-29",45280.1875,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud FGSP Nacht: Werkveld 4.1 + werkveld 4.2\r\nbijkomend mogelijk:\r\nFD SP Iv-V inbegrepen\r\nL73\r\nFLC SP I-II inbegrepen\r\nL86 tot FDN NIET nacht R5/R6 (zit reeds in een weekend TLO)\r\nR-450720\r\nR-467583",null,null,64004,"2023-11-22","Minor","1,2,3,4,5"]
[null,"Infrabel","48254","Lille - Charleroi","< >","JURBISE","ATH",2024,2024,26,28,"2024-06-24",45280.9375,"2024-07-12",45280.229166666664,"18d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\n+ Maintenance Z7.53 +  Z13.54 en P3\r\nUPM 445751",null,null,48254,"2023-09-05","Minor","1,2,3,4,5"]
[null,"Infrabel","61053","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,26,26,"2024-06-24",45280.989583333336,"2024-06-28",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service",null,null,61053,"2023-03-20","Minor","1,2,3,4,5"]
[null,"Infrabel","49897","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,26,26,"2024-06-24",45280.375,"2024-06-28",45280.645833333336,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des appareils 18Q, 19BQ, 19AQ, 21Q, 22Q à Y. Jemeppe-Froidmont\r\nFinitions\r\nUPM : 466580",null,null,49897,"2023-05-08","Minor","1,2,3,4,5"]
[null,"Infrabel","67214","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2024,2024,26,26,"2024-06-24",45280.378472222219,"2024-06-24",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,67214,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","67210","Athus - Meuse",">","HALANZY","Y.AUBANGE",2024,2024,26,26,"2024-06-26",45280.375,"2024-06-26",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,67210,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","67208","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2024,2024,26,26,"2024-06-27",45280.375,"2024-06-27",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A\r\nEntretien / maintenance voie A",null,null,67208,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","53693","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2024,2024,26,27,"2024-06-28",45280.979166666664,"2024-07-01",45280.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nVoorbereidingsweekend 3/3\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINAL\r\n+\r\nherelectrificatie (bijkomend) colt 60283\r\n+\r\nvernieuwen Muizen rooster T \r\n(samen met L27B)\r\nsecundair f",null,null,53693,"2023-10-12","Medium","5,6"]
[null,"Infrabel","62633","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.NOORD BERCHEM",2024,2024,26,27,"2024-06-28",45280.979166666664,"2024-07-01",45280.1875,"2d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"TOS 2222: Onderhoud wissels Y Noord Groenenhoek\r\nperiodiciteit: 3 keer/jaar buitendienststelling zoals colt 57506 - 57507 van 2023. Lijn 27 sp. B. (Antwerpen Berchem perronspoor 5) + deel L27/2 sporen A + B",null,null,62633,"2023-06-07","Minor","5,6"]
[null,"Infrabel","69323","Namur - Antwerpen","< >","ROGIER","BRUXELLES-LUXEMBOURG",2024,2024,26,28,"2024-06-28",45280.993055555555,"2024-07-08",45280.194444444445,"9d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing tunnelverlichting tunnel Dechainnel en Berlaymont\r\n\r\nUPM 468798",null,null,69323,"2023-07-19","High","1,2,3,4,5,6,7"]
[null,"Infrabel","63675","Erquelinnes - Montzen","< >","MARCHIENNE-ZONE","ERQUELINNES-FRONTIERE",2024,2024,26,26,"2024-06-29",45280.958333333336,"2024-06-30",45280.173611111109,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-LS_SO_L130A_Software_Marchienne-Zone - Erquelinnes\r\nMES fase 2 du projet\r\nMeewerken niet mogelijk\r\nTCR 466270",null,null,63675,"2023-08-24","Minor","5,6"]
[null,"Infrabel","49372","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2024,2024,26,26,"2024-06-29",45280.25,"2024-06-30",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10. 51   P4+\r\nUPM 457545",null,null,49372,"2023-03-24","Medium","5,6"]
[null,"Infrabel","58642","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2024,2024,26,27,"2024-06-29",45280.25,"2024-07-01",45280.173611111109,"2d, 22:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Oude landen project 308+304",null,null,58642,"2022-11-08","Medium","5,6"]
[null,"Infrabel","58663","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","Y.HOLLAND",2024,2024,26,26,"2024-06-30",45280.25,"2024-06-30",45280.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"304 statiestraat , tussen Y laarsebeek en Y driehoekstraat",null,null,58663,"2023-08-30","Minor","5,6"]
[null,"Infrabel","65401","Lille - Charleroi","< >","HALLE","QUEVY-FRONTIERE",2024,2024,26,26,"2024-06-30",45280.083333333336,"2024-06-30",45280.208333333336,"1d, 03:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Mise hors service de l’ensemble de la zone EBP FMS pendant un minimum de 2h30 (4h est parfait pour avoir un peu de marge) à définir entre 22h et 6h (selon les disponibilités de la zone) Christine Deschrijver; Christine Payen",null,null,65401,"2023-03-27","Minor","5,6"]
[null,"Infrabel","61241","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2024,2024,27,27,"2024-07-01",45280.958333333336,"2024-07-05",45280.194444444445,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z14.43\r\nPilote 6h",null,null,61241,"2023-03-09","Minor","1,2,3,4,5"]
[null,"Infrabel","67212","Athus - Meuse",">","BERTRIX","STRAIMONT",2024,2024,27,27,"2024-07-01",45280.333333333336,"2024-07-01",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,67212,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","61930","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","BAKENBOS",2024,2024,27,27,"2024-07-01",45280.986111111109,"2024-07-06",45280.201388888891,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_05 Area CE volgens onderhoudskalender 2024.\r\nBuitendienststelling L161 tussen Bru Luxemburg en Bakenbos voor onderhoudswerken + L161A.",null,null,61930,"2023-03-01","Minor","1,2,3,4,5"]
[null,"Infrabel","64168","Namur - Antwerpen","< >","MECHELEN","MECHELEN-NEKKERSPOEL",2024,2024,27,27,"2024-07-01",45280.993055555555,"2024-07-06",45280.194444444445,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"masterplan Mechelen \r\nL27+L53 spoor A + Spoor V in Mechelen station",null,null,64168,"2023-01-06","Minor","1,2,3,4,5"]
[null,"Infrabel","67213","Athus - Meuse",">","STRAIMONT","BERTRIX",2024,2024,27,27,"2024-07-02",45280.375,"2024-07-02",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,67213,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","50596","Namur - Antwerpen",">","AUVELAIS","MOUSTIER-GARAGE",2024,2024,27,27,"2024-07-03",45280.979166666664,"2024-07-04",45280.208333333336,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie",null,null,50596,"2022-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","66925","Athus - Meuse",">","VIRTON","SIGNEULX",2024,2024,27,27,"2024-07-04",45280.375,"2024-07-04",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,66925,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","46809","Athus - Meuse","< >","BEAURAING","BERTRIX",2024,2024,27,28,"2024-07-05",45280.958333333336,"2024-07-08",45280.1875,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses (P93)\r\n+ Visites\r\nUPM : 462894",null,null,46809,"2023-04-13","Medium","5,6"]
[null,"Infrabel","67211","Athus - Meuse",">","SIGNEULX","VIRTON",2024,2024,27,27,"2024-07-05",45280.375,"2024-07-05",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,67211,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","63441","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,27,27,"2024-07-05",45280.375,"2024-07-05",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63441,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","68829","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2024,2024,27,27,"2024-07-06",45280.3125,"2024-07-06",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY (à répéter toutes les 4 semaines le samedi)",null,null,68829,"2023-05-08","Minor","5,6"]
[null,"Infrabel","48979","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,27,27,"2024-07-07",45280.333333333336,"2024-07-07",45280.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144 + 130/1 + maintenance infrastructure + contrôles",null,null,48979,"2023-02-07","Minor","5,6"]
[null,"Infrabel","50627","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,27,28,"2024-07-07",45280.034722222219,"2024-07-08",45280.222222222219,"2d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris",null,null,50627,"2023-01-16","Minor","5,6"]
[null,"Infrabel","66314","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,28,28,"2024-07-08",45280.958333333336,"2024-07-13",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux de nettoyage EBP PLP",null,null,66314,"2023-02-27","Minor","1,2,3,4,5"]
[null,"Infrabel","56838","Lille - Charleroi",">","BRUGELETTE","BRUGELETTE",2024,2024,28,28,"2024-07-08",45280.333333333336,"2024-07-12",45280.923611111109,"5d, 14:10h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\nUPM 445834",null,null,56838,"2023-08-29","Minor","1,2,3,4,5"]
[null,"Infrabel","66852","Erquelinnes - Montzen","< >","HUY","NAMUR",2024,2024,28,28,"2024-07-08",45280.96875,"2024-07-13",45280.215277777781,"5d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.43\r\nP3 Pilote 6h",null,null,66852,"2023-03-09","Minor","1,2,3,4,5"]
[null,"Infrabel","62562","Namur - Antwerpen","< >","MECHELEN","KONTICH-LINT",2024,2024,28,28,"2024-07-08",45280.993055555555,"2024-07-12",45280.201388888891,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\nZ31.23 : studie nog uit te voeren door I-CBE & Z30.23 : studie nog uit te voeren door I-CBE",null,null,62562,"2023-06-07","Minor","1,2,3,4,5"]
[null,"Infrabel","64157","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-NEKKERSPOEL",2024,2024,28,28,"2024-07-08",45280.993055555555,"2024-07-13",45280.194444444445,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"masterplan Mechelen \r\nTLO L27+L53 + Spoor V en VI in Mechelen station",null,null,64157,"2023-05-12","Minor","1,2,3,4,5"]
[null,"Infrabel","62874","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2024,2024,28,28,"2024-07-10",45280.013888888891,"2024-07-10",45280.190972222219,"1d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen\r\nZ23.22 : studie nog uit te voeren door I-CBE",null,null,62874,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","60095","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,28,28,"2024-07-10",45280.395833333336,"2024-07-10",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn",null,null,60095,"2022-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","60108","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,28,28,"2024-07-11",45280.986111111109,"2024-07-12",45280.236111111109,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z11.22",null,null,60108,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","67536","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2024,2024,28,28,"2024-07-11",45280.375,"2024-07-11",45280.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67536,"2023-04-20","Minor","1,2,3,4,5"]
[null,"Infrabel","67091","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2024,2024,28,28,"2024-07-12",45280.333333333336,"2024-07-12",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno",null,null,67091,"2023-03-17","Minor","1,2,3,4,5"]
[null,"Infrabel","49500","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2024,2024,28,28,"2024-07-13",45280.25,"2024-07-14",45280.666666666664,"1d, 10:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 Mise HS P4 +Diagno Zones 2 + 4 (FBC - FSG - FJR)\r\nUPM 459789",null,null,49500,"2023-03-20","Medium","5,6"]
[null,"Infrabel","60649","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2024,2024,28,28,"2024-07-13",45280.354166666664,"2024-07-13",45280.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2024: L140 Partie 1",null,null,60649,"2023-02-06","Minor","5,6"]
[null,"Infrabel","48952","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2024,2024,28,28,"2024-07-13",45280.340277777781,"2024-07-14",45280.659722222219,"2d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles \r\nUPM 466945",null,null,48952,"2023-06-27","Minor","5,6"]
[null,"Infrabel","50704","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,28,29,"2024-07-14",45280.027777777781,"2024-07-15",45280.1875,"2d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44",null,null,50704,"2022-12-16","Minor","5,6"]
[null,"Infrabel","60656","Namur - Antwerpen",">","FLEURUS","CHARLEROI-OUEST",2024,2024,28,28,"2024-07-14",45280.354166666664,"2024-07-14",45280.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2024: L140 Partie 2",null,null,60656,"2023-02-06","Minor","5,6"]
[null,"Infrabel","66854","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2024,2024,29,29,"2024-07-15",45280.958333333336,"2024-07-20",45280.194444444445,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z14.43",null,null,66854,"2023-03-09","Minor","1,2,3,4,5"]
[null,"Infrabel","64160","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-NEKKERSPOEL",2024,2024,29,29,"2024-07-15",45280.993055555555,"2024-07-20",45280.194444444445,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"masterplan Mechelen \r\nTLO L27+L53 + Spoor V en VI in Mechelen station",null,null,64160,"2023-05-12","Minor","1,2,3,4,5"]
[null,"Infrabel","60663","Namur - Antwerpen",">","LA ROCHE(BRABANT)","TILLY",2024,2024,29,29,"2024-07-15",45280.354166666664,"2024-07-15",45280.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2024: L140 Partie 3",null,null,60663,"2023-02-06","Minor","1,2,3,4,5"]
[null,"Infrabel","67215","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2024,2024,29,29,"2024-07-16",45280.378472222219,"2024-07-16",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,67215,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","69263","Athus - Meuse",">","STOCKEM-NORD","ARLON",2024,2024,29,29,"2024-07-16",45280.361111111109,"2024-07-16",45280.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69263,"2023-05-22","Minor","1,2,3,4,5"]
[null,"Infrabel","69270","Athus - Meuse",">","HABAY","STOCKEM-NORD",2024,2024,29,29,"2024-07-17",45280.375,"2024-07-17",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69270,"2023-05-22","Minor","1,2,3,4,5"]
[null,"Infrabel","67216","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2024,2024,29,29,"2024-07-18",45280.375,"2024-07-18",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A\r\nEntretien / maintenance voie A",null,null,67216,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","48871","Namur - Antwerpen",">","WAVRE","OTTIGNIES",2024,2024,29,29,"2024-07-20",45280.333333333336,"2024-07-20",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes+ maintenances infrastructure et contrôles\r\nUPM : 465251",null,null,48871,"2023-04-27","Minor","5,6"]
[null,"Infrabel","67525","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2024,2024,29,29,"2024-07-20",45280.354166666664,"2024-07-20",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67525,"2023-03-31","Minor","5,6"]
[null,"Infrabel","67223","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2024,2024,29,29,"2024-07-21",45280.375,"2024-07-21",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie B\r\nVisite voie B",null,null,67223,"2023-03-21","Minor","5,6"]
[null,"Infrabel","64161","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-NEKKERSPOEL",2024,2024,30,30,"2024-07-22",45280.993055555555,"2024-07-27",45280.194444444445,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"masterplan Mechelen \r\nTLO L27+L53 + Spoor V en VI in Mechelen station",null,null,64161,"2023-05-12","Minor","1,2,3,4,5"]
[null,"Infrabel","67729","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2024,2024,30,30,"2024-07-22",45280.385416666664,"2024-07-22",45280.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,67729,"2023-04-08","Minor","1,2,3,4,5"]
[null,"Infrabel","56673","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2024,2024,30,30,"2024-07-22",45280.5,"2024-07-22",45280.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Cette visite se fait le même lundi que la visite entre Froidmont et Bressoux prévue l'avant-midi\r\n- Visite de voie, PN et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56673,"2023-02-27","Minor","1,2,3,4,5"]
[null,"Infrabel","67219","Athus - Meuse",">","STRAIMONT","BERTRIX",2024,2024,30,30,"2024-07-23",45280.375,"2024-07-23",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,67219,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","66449","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,30,30,"2024-07-25",45280.333333333336,"2024-07-25",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66449,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","63424","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,30,30,"2024-07-25",45280.375,"2024-07-25",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63424,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","66451","Athus - Meuse",">","BERTRIX","PALISEUL",2024,2024,30,30,"2024-07-26",45280.333333333336,"2024-07-26",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66451,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","63442","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,30,30,"2024-07-26",45280.375,"2024-07-26",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63442,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","56798","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,30,30,"2024-07-27",45280.291666666664,"2024-07-28",45280.677083333336,"1d, 09:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance  Z.11.53\r\nMise HS P4\r\nUPM 459765",null,null,56798,"2023-04-17","Medium","5,6"]
[null,"Infrabel","66453","Athus - Meuse",">","GEDINNE","PALISEUL",2024,2024,31,31,"2024-07-29",45280.333333333336,"2024-07-29",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66453,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","55959","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,31,31,"2024-07-29",45280.923611111109,"2024-08-03",45280.194444444445,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53 en P3\r\n+ ETCS L2-IL_SO_P036_L96_L97_Jurbise - Mons - Saint Ghislain_ETCS \r\nTests",null,null,55959,"2023-10-24","Minor","1,2,3,4,5"]
[null,"Infrabel","65947","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2024,2024,31,31,"2024-07-29",45280.409722222219,"2024-07-29",45280.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65947,"2023-02-21","Minor","1,2,3,4,5"]
[null,"Infrabel","67367","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,31,31,"2024-07-31",45280.375,"2024-07-31",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,67367,"2023-04-06","Minor","1,2,3,4,5"]
[null,"Infrabel","65923","Athus - Meuse",">","LAVAUX","MARBEHAN",2024,2024,31,31,"2024-07-31",45280.361111111109,"2024-07-31",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65923,"2023-02-21","Minor","1,2,3,4,5"]
[null,"Infrabel","65915","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2024,2024,31,31,"2024-08-01",45280.368055555555,"2024-08-01",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65915,"2023-02-21","Minor","1,2,3,4,5"]
[null,"Infrabel","52664","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2024,2024,31,32,"2024-08-02",45280.958333333336,"2024-08-05",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"réélectrification\r\n+ Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles\r\nUPM 466854",null,null,52664,"2023-11-17","Minor","5,6"]
[null,"Infrabel","57383","Athus - Meuse","< >","ROCHEFORT-JEMELLE","HATRIVAL",2024,2024,31,31,"2024-08-02",45280.965277777781,"2024-08-04",45280.673611111109,"2d, 17:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Rénovation Pont sur la Masblette (P.I.) bK 124.781\r\n+ Renouvellement des rails à Poix-Saint-Hubert (sans ART supplémentaire).\r\nUPM 462876",null,null,57383,"2023-10-05","Medium","5,6"]
[null,"Infrabel","67357","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,31,31,"2024-08-02",45280.375,"2024-08-02",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,67357,"2023-04-06","Minor","1,2,3,4,5"]
[null,"Infrabel","66464","Athus - Meuse",">","VONECHE","BEAURAING",2024,2024,31,31,"2024-08-03",45280.333333333336,"2024-08-03",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66464,"2023-03-10","Minor","5,6"]
[null,"Infrabel","62390","Athus - Meuse","< >","NAMUR","NAMUR-HERBATTE",2024,2024,31,31,"2024-08-03",45280.986111111109,"2024-08-04",45280.208333333336,"1d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Transfert des alimentations des loges en gare de Namur en vue du renouvellement de celle-ci\r\nLoges H8 et H10 mise hors service",null,null,62390,"2023-04-08","Minor","5,6"]
[null,"Infrabel","65939","Athus - Meuse",">","ARLON","Y.AUTELBAS",2024,2024,31,31,"2024-08-03",45280.361111111109,"2024-08-03",45280.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65939,"2023-02-21","Minor","5,6"]
[null,"Infrabel","66466","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,31,31,"2024-08-04",45280.333333333336,"2024-08-04",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,66466,"2023-03-10","Minor","5,6"]
[null,"Infrabel","68830","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2024,2024,31,31,"2024-08-04",45280.3125,"2024-08-04",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY (à répéter toutes les 4 semaines le dimanche)",null,null,68830,"2023-05-08","Minor","5,6"]
[null,"Infrabel","66675","Lille - Charleroi",">","Y.SOIGNIES","SOIGNIES",2024,2024,31,31,"2024-08-04",45280.520833333336,"2024-08-04",45280.645833333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B\r\nTCR 465072 - 465073\r\nCR HKI 2024-1 validé le 11/09/2023\r\nMassifié avec Colt 48650",null,null,66675,"2023-09-11","Minor","5,6"]
[null,"Infrabel","64348","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,32,32,"2024-08-05",45280.958333333336,"2024-08-10",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails , ballast...",null,null,64348,"2023-02-27","Minor","1,2,3,4,5"]
[null,"Infrabel","47570","Lille - Charleroi",">","MONS","JURBISE",2024,2024,32,36,"2024-08-05",45280.951388888891,"2024-09-07",45280.215277777781,"33d, 06:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification - Phase 5 - 2024\r\nDépose anciens poteaux\r\nUPM 459869",null,null,47570,"2023-08-23","Minor","1,2,3,4,5"]
[null,"Infrabel","60286","Namur - Antwerpen","< >","MUIZEN-ROOSTER T","LEUVEN",2024,2024,32,32,"2024-08-05",45280.972222222219,"2024-08-09",45280.208333333336,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"herelectrificatie (bijkomend)",null,null,60286,"2022-07-18","Minor","1,2,3,4,5"]
[null,"Infrabel","62157","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2024,2024,32,32,"2024-08-05",45280.986111111109,"2024-08-10",45280.229166666664,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FH_03 Area CE volgens onderhoudskalender 2024.\r\nBuitendienststelling L96 spoor A tussen FBMZ en FH.\r\nZone beperken tot aw 10R (NI) .",null,null,62157,"2023-03-02","Minor","1,2,3,4,5"]
[null,"Infrabel","67362","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2024,2024,32,32,"2024-08-05",45280.378472222219,"2024-08-05",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,67362,"2023-04-06","Minor","1,2,3,4,5"]
[null,"Infrabel","65412","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2024,2024,32,32,"2024-08-05",45280.381944444445,"2024-08-05",45280.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41 (à répéter toutes les 6 semaines, le lundi)",null,null,65412,"2023-02-23","Minor","1,2,3,4,5"]
[null,"Infrabel","59212","Lille - Antwerpen","< >","Y.BERNADETTESTRAAT","GENT-DAMPOORT",2024,2024,32,32,"2024-08-06",45280.020833333336,"2024-08-10",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I",null,null,59212,"2022-05-19","Minor","1,2,3,4,5"]
[null,"Infrabel","67363","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2024,2024,32,32,"2024-08-06",45280.378472222219,"2024-08-06",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,67363,"2023-04-06","Minor","1,2,3,4,5"]
[null,"Infrabel","67814","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2024,2024,32,32,"2024-08-07",45280.333333333336,"2024-08-07",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11\r\nTCR 467943",null,null,67814,"2023-10-31","Minor","1,2,3,4,5"]
[null,"Infrabel","66093","Athus - Meuse",">","YVOIR","DINANT",2024,2024,32,32,"2024-08-08",45280.385416666664,"2024-08-08",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,66093,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","67360","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2024,2024,32,32,"2024-08-08",45280.375,"2024-08-08",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A\r\nEntretien / maintenance voie A",null,null,67360,"2023-04-06","Minor","1,2,3,4,5"]
[null,"Infrabel","52665","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2024,2024,32,33,"2024-08-09",45280.958333333336,"2024-08-12",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"réélectrification\r\nUPM 466857",null,null,52665,"2023-05-10","Minor","5,6"]
[null,"Infrabel","67361","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2024,2024,32,32,"2024-08-09",45280.375,"2024-08-09",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B\r\nEntretien / maintenance voie B",null,null,67361,"2023-04-06","Minor","1,2,3,4,5"]
[null,"Infrabel","67358","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,32,32,"2024-08-10",45280.375,"2024-08-10",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie A\r\nVisite voie A",null,null,67358,"2023-04-06","Minor","5,6"]
[null,"Infrabel","61599","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2024,2024,32,32,"2024-08-11",45280.25,"2024-08-11",45280.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,61599,"2023-01-02","Medium","5,6"]
[null,"Infrabel","52666","Namur - Antwerpen",">","RHISNES","GEMBLOUX",2024,2024,33,33,"2024-08-12",45280.958333333336,"2024-08-17",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"finitions",null,null,52666,"2022-12-16","Minor","1,2,3,4,5"]
[null,"Infrabel","61056","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,33,33,"2024-08-12",45280.989583333336,"2024-08-16",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service",null,null,61056,"2023-03-20","Minor","1,2,3,4,5"]
[null,"Infrabel","49370","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2024,2024,33,33,"2024-08-12",45280.993055555555,"2024-08-17",45280.194444444445,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP3 HKM",null,null,49370,"2022-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","59215","Lille - Antwerpen","< >","Y.BERNADETTESTRAAT","GENT-DAMPOORT",2024,2024,33,33,"2024-08-13",45280.020833333336,"2024-08-16",45280.1875,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I\r\n- R5/R6 in weekend TLO",null,null,59215,"2023-04-21","Minor","1,2,3,4,5"]
[null,"Infrabel","64766","Lille - Antwerpen","< >","SINT-NIKLAAS","Y.MELSELE",2024,2024,33,33,"2024-08-13",45280.013888888891,"2024-08-17",45280.184027777781,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud Sint Niklaas \r\n\r\n*perron II-V inbegrepen. \r\n*SP I + SP A  niet inbegrepen om doorrit naar L54 toe te laten",null,null,64766,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","65539","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2024,2024,33,33,"2024-08-14",45280.375,"2024-08-14",45280.645833333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Schouwen lopend spoor",null,null,65539,"2023-02-10","Minor","1,2,3,4,5"]
[null,"Infrabel","63404","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,33,33,"2024-08-14",45280.375,"2024-08-14",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63404,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","47156","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,33,34,"2024-08-16",45280.958333333336,"2024-08-19",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu\r\nUPM: 460261",null,null,47156,"2023-04-05","Minor","5,6"]
[null,"Infrabel","69835","Namur - Antwerpen","< >","MECHELEN","Y.LEUVEN-BUNDEL M",2024,2024,33,34,"2024-08-16",45280.979166666664,"2024-08-19",45280.1875,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nR-471073\r\nCR 2024-109",null,null,69835,"2023-10-16","Medium","5,6"]
[null,"Infrabel","66471","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2024,2024,33,33,"2024-08-16",45280.388888888891,"2024-08-16",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,66471,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","63959","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,33,33,"2024-08-17",45280.979166666664,"2024-08-18",45280.229166666664,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossen Rails met Robeltrein",null,null,63959,"2022-12-20","Minor","5,6"]
[null,"Infrabel","48901","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2024,2024,33,33,"2024-08-18",45280.333333333336,"2024-08-18",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nOttignies gare  voie 1 à 5 en alternance",null,null,48901,"2023-03-10","Minor","5,6"]
[null,"Infrabel","50706","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,33,34,"2024-08-18",45280.027777777781,"2024-08-19",45280.1875,"2d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44",null,null,50706,"2022-12-16","Minor","5,6"]
[null,"Infrabel","62823","Athus - Meuse",">","YVOIR","DINANT",2024,2024,34,34,"2024-08-19",45280.958333333336,"2024-08-24",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,62823,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","49315","Lille - Charleroi",">","PONT-A-CELLES","LUTTRE",2024,2024,34,34,"2024-08-19",45280.958333333336,"2024-08-24",45280.25,"5d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Ré-électrification de la Gare de Luttre\r\nFinitions",null,null,49315,"2023-01-17","Minor","1,2,3,4,5"]
[null,"Infrabel","66454","Athus - Meuse",">","GEDINNE","PALISEUL",2024,2024,34,34,"2024-08-19",45280.333333333336,"2024-08-19",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66454,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","55039","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2024,2024,34,34,"2024-08-19",45280.979166666664,"2024-08-24",45280.208333333336,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10. 51   P3\r\nUPM : 460236",null,null,55039,"2023-03-22","Minor","1,2,3,4,5"]
[null,"Infrabel","49888","Namur - Antwerpen","< >","MECHELEN","HAACHT",2024,2024,34,36,"2024-08-19",45280.1875,"2024-09-02",45280.1875,"14d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nTijdens de weekends uitbreiding tot Leuven\r\n\r\nvernieuwen Muizen rooster T ( ==> colt 58337)\r\n(samen met L27B)(",null,null,49888,"2023-12-14","High","1,2,3,4,5,6,7"]
[null,"Infrabel","61057","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,34,34,"2024-08-19",45280.989583333336,"2024-08-24",45280.197916666664,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service",null,null,61057,"2023-03-20","Minor","1,2,3,4,5"]
[null,"Infrabel","65898","Lille - ZeeBrugge","< >","BRUGGE-ROOSTER E","ROESELARE",2024,2024,34,34,"2024-08-20",45280.006944444445,"2024-08-23",45280.194444444445,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-LS_NW_L66_Software_Lichtervelde - Brugge\r\nTesten, meewerken niet mogelijk",null,null,65898,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","59216","Lille - Antwerpen","< >","Y.BERNADETTESTRAAT","GENT-DAMPOORT",2024,2024,34,34,"2024-08-20",45280.020833333336,"2024-08-24",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen spoor tussen BT 15C en BT 20D\r\n\r\n- FGDM SP II en 5 inbegrepen\r\n- Toegang Gent Zeehaven via SP I",null,null,59216,"2022-05-19","Minor","1,2,3,4,5"]
[null,"Infrabel","66469","Athus - Meuse",">","BEAURAING","HOUYET",2024,2024,34,34,"2024-08-20",45280.388888888891,"2024-08-20",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses",null,null,66469,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","66017","Athus - Meuse",">","YVOIR","LUSTIN",2024,2024,34,34,"2024-08-21",45280.375,"2024-08-21",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,66017,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","63834","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2024,2024,34,34,"2024-08-22",45280.993055555555,"2024-08-23",45280.194444444445,"1d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen\r\nZ23.22 : studie nog uit te voeren door I-CBE",null,null,63834,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","67537","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2024,2024,34,34,"2024-08-22",45280.375,"2024-08-22",45280.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67537,"2023-04-20","Minor","1,2,3,4,5"]
[null,"Infrabel","47157","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,34,35,"2024-08-23",45280.958333333336,"2024-08-26",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu\r\nUPM : 460263",null,null,47157,"2023-03-22","Minor","5,6"]
[null,"Infrabel","71481","Athus - Meuse","< >","HATRIVAL","GRUPONT",2024,2024,34,35,"2024-08-23",45280.958333333336,"2024-08-26",45280.201388888891,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de rails à Poix.\r\nMassification sur Colt n°52541",null,null,71481,"2023-10-04","Medium","5,6"]
[null,"Infrabel","66463","Athus - Meuse",">","GEDINNE","VONECHE",2024,2024,34,34,"2024-08-23",45280.333333333336,"2024-08-23",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66463,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","59715","Namur - Antwerpen","< >","Y.ARENDSTRAAT","Y.BERCHEM-STADION",2024,2024,34,35,"2024-08-23",45280.996527777781,"2024-08-26",45280.166666666664,"2d, 04:05h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Lijn 27 sp. B samen met Lijn 59/1 sp. A, met een correcte beveiliging Indringing type II op L59/1 spoor B.\r\nL59/1 sp A: Y West Berchem J-F.12 tot Y West Berchem J-F.12\r\nL27 sp B: Y Noord Groenenhoek M-F.12 tot Y Arenstraat JX-G.12",null,null,59715,"2022-12-27","Medium","5,6"]
[null,"Infrabel","70038","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2024,2024,34,34,"2024-08-24",45280.979166666664,"2024-08-25",45280.1875,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"vernieuwing perronsporen A-Centraal: lossen rails\r\nsp 4 + spoor 5(L12 sp A) en 6 Antwerpen-Centraal buitendienst\r\nmin 5 uur BD nodig\r\nCR 2024-173",null,null,70038,"2023-10-16","Minor","5,6"]
[null,"Infrabel","58643","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.SINT-MARIABURG",2024,2024,34,35,"2024-08-24",45280.25,"2024-08-26",45280.173611111109,"2d, 22:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Oude landen project 308+304",null,null,58643,"2022-11-08","Medium","5,6"]
[null,"Infrabel","60650","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2024,2024,34,34,"2024-08-24",45280.354166666664,"2024-08-24",45280.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2024: L140 Partie 1",null,null,60650,"2023-02-06","Minor","5,6"]
[null,"Infrabel","64872","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","ESSEN-GRENS",2024,2024,34,34,"2024-08-25",45280,"2024-08-25",45280.166666666664,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Buitendienststellen van de van de volledige overeenkomstige EBP-zone gedurende minimaal 2,5 uur te bepalen tussen 22.00 uur en 06.00 uur\r\nUpdate EBP release to last version\r\nR-446960",null,null,64872,"2023-01-27","Minor","5,6"]
[null,"Infrabel","66052","Athus - Meuse",">","LUSTIN","JAMBES",2024,2024,34,34,"2024-08-25",45280.385416666664,"2024-08-25",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,66052,"2023-03-14","Minor","5,6"]
[null,"Infrabel","67528","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2024,2024,34,34,"2024-08-25",45280.354166666664,"2024-08-25",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67528,"2023-04-20","Minor","5,6"]
[null,"Infrabel","49237","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","ERQUELINNES-FRONTIERE",2024,2024,35,35,"2024-08-26",45280.958333333336,"2024-08-30",45280.173611111109,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nRenouvellement des AS de Y.La Sambre\r\nSem. nuits CTL L130A+132  Finitions\r\nUPM : 444840",null,null,49237,"2023-07-31","Minor","1,2,3,4,5"]
[null,"Infrabel","50583","Namur - Antwerpen",">","Y.FLAWINNE","MOUSTIER-GARAGE",2024,2024,35,35,"2024-08-26",45280.979166666664,"2024-08-27",45280.208333333336,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie",null,null,50583,"2023-11-17","Minor","1,2,3,4,5"]
[null,"Infrabel","57799","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,35,35,"2024-08-26",45280.965277777781,"2024-08-30",45280.1875,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-57799(uren nog aanpassen in UPM)\r\nVernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\n\r\nR5/56 in weekend TLO",null,null,57799,"2022-12-22","Minor","1,2,3,4,5"]
[null,"Infrabel","67370","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2024,2024,35,35,"2024-08-26",45280.378472222219,"2024-08-26",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,67370,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","60121","Namur - Antwerpen","< >","ANTWERPEN-NOORDERDOKKEN","Y.HOLLAND",2024,2024,35,35,"2024-08-26",45280.975694444445,"2024-08-31",45280.166666666664,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderheid SIG Y luchtbal en onderhoud wissel Y Antwerpen-luchtbal",null,null,60121,"2022-08-24","Minor","1,2,3,4,5"]
[null,"Infrabel","64768","Lille - Antwerpen","< >","SINT-NIKLAAS","Y.MELSELE",2024,2024,35,35,"2024-08-27",45280.013888888891,"2024-08-31",45280.184027777781,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud Sint Niklaas \r\n\r\n*perron II-V inbegrepen. \r\n*SP I + SP A  niet inbegrepen om doorrit naar L54 toe te laten",null,null,64768,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","60672","Namur - Antwerpen",">","TILLY","FLEURUS",2024,2024,35,35,"2024-08-27",45280.354166666664,"2024-08-27",45280.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2024: L140 Partie 4",null,null,60672,"2023-02-06","Minor","1,2,3,4,5"]
[null,"Infrabel","50597","Namur - Antwerpen",">","AUVELAIS","MOUSTIER-GARAGE",2024,2024,35,35,"2024-08-28",45280.979166666664,"2024-08-29",45280.208333333336,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie",null,null,50597,"2022-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","69271","Athus - Meuse",">","HABAY","STOCKEM-NORD",2024,2024,35,35,"2024-08-28",45280.375,"2024-08-28",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69271,"2023-05-22","Minor","1,2,3,4,5"]
[null,"Infrabel","67372","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2024,2024,35,35,"2024-08-29",45280.375,"2024-08-29",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A\r\nEntretien / maintenance voie A",null,null,67372,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","48241","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","ERQUELINNES-FRONTIERE",2024,2024,35,36,"2024-08-30",45280.958333333336,"2024-09-02",45280.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+132 Finitions  \r\n+ Renouvellement des as Y La Sambre \r\nDossier de concertation validé le 28 octobre 2021\r\nUPM 443072",null,null,48241,"2023-01-12","Medium","5,6"]
[null,"Infrabel","47501","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2024,2024,35,36,"2024-08-30",45280.208333333336,"2024-09-03",45280.208333333336,"4d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Massification travaux\r\nRenouvellement tablier métallique PI 13.808\r\nMise au gabarit pistes PI + sécurisation parois rocheuses + stabilisation talus\r\nMassification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse\r\nUPM : 462",null,null,47501,"2023-04-13","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","48872","Namur - Antwerpen",">","WAVRE","OTTIGNIES",2024,2024,35,35,"2024-08-31",45280.333333333336,"2024-08-31",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes+ maintenances infrastructure et contrôles\r\nUPM : 465252",null,null,48872,"2023-04-27","Minor","5,6"]
[null,"Infrabel","49211","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2024,2024,35,35,"2024-08-31",45280.333333333336,"2024-09-01",45280.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique + maintenance infrastructure + contrôles\r\nUPM 466902\r\nUPM 466904",null,null,49211,"2023-11-17","Minor","5,6"]
[null,"Infrabel","47506","Athus - Meuse","< >","ANSEREMME","HOUYET",2024,2024,35,36,"2024-08-31",45280.25,"2024-09-02",45280.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux OA tronçons Anseremme - Gendron et Gendron - Houyet (entretien tunnels, parois,...)\r\nMassification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse\r\n+ Visites\r\nUPM: 462920",null,null,47506,"2023-12-15","Medium","5,6"]
[null,"Infrabel","68832","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2024,2024,35,35,"2024-08-31",45280.3125,"2024-08-31",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY (à répéter toutes les 4 semaines le samedi)",null,null,68832,"2023-05-08","Minor","5,6"]
[null,"Infrabel","49184","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2024,2024,35,35,"2024-09-01",45280.333333333336,"2024-09-01",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie B + maintenance infrastructure + contrôles\r\nUPM : 461853",null,null,49184,"2023-11-17","Minor","5,6"]
[null,"Infrabel","69700","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,35,35,"2024-09-01",45280.25,"2024-09-01",45280.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwingen bundel Q\r\nvoorbereiding BVL \r\nR-469623\r\nCR 2024-100",null,null,69700,"2023-12-14","Minor","5,6"]
[null,"Infrabel","58458","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","ANTWERPEN-CENTRAAL",2024,2024,35,50,"2024-09-01",45280.993055555555,"2024-12-15",45280.003472222219,"104d, 00:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"spoor 5(L12 sp A) en 6 Antwerpen-Centraal in continue buiten dienst\r\nPert sept",null,null,58458,"2023-03-28","Major","1,2,3,4,5,6,7"]
[null,"Infrabel","60242","Namur - Antwerpen","< >","LEUVEN","SINT-JORIS-WEERT",2024,2024,36,36,"2024-09-02",45280.958333333336,"2024-09-06",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,60242,"2022-07-20","Minor","1,2,3,4,5"]
[null,"Infrabel","69701","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,36,37,"2024-09-02",45280.333333333336,"2024-09-13",45280.666666666664,"12d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwingen bundel Q\r\nvoorbereiding BVL \r\nR-469625\r\nCR 2024-101",null,null,69701,"2023-10-16","Minor","1,2,3,4,5"]
[null,"Infrabel","50635","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,36,36,"2024-09-02",45280.979166666664,"2024-09-06",45280.222222222219,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nP3 HKM",null,null,50635,"2022-11-10","Minor","1,2,3,4,5"]
[null,"Infrabel","71149","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2024,2024,36,36,"2024-09-02",45280.979166666664,"2024-09-07",45280.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1 buiten uren verkeer.\r\nzaterdag tot 4u55 \r\nR-477477\r\nCR 2024-174",null,null,71149,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","48772","Lille - Charleroi","< >","LEUZE","TOURNAI",2024,2024,36,36,"2024-09-02",45280.972222222219,"2024-09-06",45280.194444444445,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH\r\nTravaux de préparation\r\nUPM 459555",null,null,48772,"2023-03-17","Minor","1,2,3,4,5"]
[null,"Infrabel","47470","Erquelinnes - Montzen",">","HUY","STATTE",2024,2024,36,36,"2024-09-02",45280.229166666664,"2024-09-06",45280.979166666664,"5d, 18:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement voie 717 et 718 + Quais centraux 6/7 et 8/9",null,null,47470,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","67722","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-FRANCE",2024,2024,36,36,"2024-09-02",45280.375,"2024-09-02",45280.583333333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite voie unique L 165/2 \r\nVisite voie unique L 165/3\r\nVisite voie unique L 165/1\r\nMaintenance",null,null,67722,"2023-04-08","Minor","1,2,3,4,5"]
[null,"Infrabel","61924","Namur - Antwerpen","< >","ROGIER","WATERMAEL",2024,2024,36,36,"2024-09-02",45280.982638888891,"2024-09-07",45280.166666666664,"5d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_01 Area CE volgens onderhoudskalender 2024.\r\n\r\nBuitendienststelling L161 voor onderhoudswerken.\r\nBijkomend L161A tussen Y Jubelpark en Y Watermaal, L26/4 tussen Etterbeek en Y Boondaal en L26/2 MTB-Y MTB\r\nR5/R6 stoppen om 04u00 voor M",null,null,61924,"2023-03-03","Minor","1,2,3,4,5"]
[null,"Infrabel","65859","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2024,2024,36,36,"2024-09-03",45280.013888888891,"2024-09-07",45280.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS L2-IL_NW_P014_01_L75_Gent-Sint-Pieters - De Pinte_IL\r\nETCS L2-IL_NW_P014_02_L75_De Pinte_IL\r\nETCS L2-IL_NW_P014_03_L75_De Pinte - Deinze_IL\r\n\r\nOpkuis, meewerken mogelijk,",null,null,65859,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","63406","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,36,36,"2024-09-04",45280.375,"2024-09-04",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63406,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","64379","Namur - Antwerpen",">","NAMUR","RHISNES",2024,2024,36,36,"2024-09-06",45280.958333333336,"2024-09-07",45280.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,64379,"2023-01-18","Minor","1,2,3,4,5"]
[null,"Infrabel","48242","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","ERQUELINNES-FRONTIERE",2024,2024,36,37,"2024-09-06",45280.958333333336,"2024-09-09",45280.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Second tabliers ponts 10 et 11 + chape+passerelles du pont 14\r\nWE L130A+132  Finitions\r\n+ Renouvellement des as Y La Sambre \r\nDossier de concertation validé le 28 octobre 2021\r\nUPM 443081\r\n+ Diagno 2024: L130 Partie 3.b nuit 6^7/09\r\nEn corrélation avec ",null,null,48242,"2023-05-31","Medium","5,6"]
[null,"Infrabel","67093","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2024,2024,36,36,"2024-09-06",45280.333333333336,"2024-09-06",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno",null,null,67093,"2023-03-17","Minor","1,2,3,4,5"]
[null,"Infrabel","58338","Namur - Antwerpen","< >","MECHELEN","HAACHT",2024,2024,36,37,"2024-09-06",45280.993055555555,"2024-09-09",45280.166666666664,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"vernieuwen Muizen rooster T \r\n(samen met L27B)\r\nCOLT 58357 TOEGEVOEGD",null,null,58338,"2023-03-23","Medium","5,6"]
[null,"Infrabel","57792","Lille - ZeeBrugge","< >","LICHTERVELDE","ROESELARE",2024,2024,36,37,"2024-09-07",45280.006944444445,"2024-09-09",45280.1875,"2d, 04:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497\r\n\r\n\r\nRMS THV DR-O.7+DRX-O.7\r\ngevallen 29352+29347 niet mogelijk!",null,null,57792,"2022-09-01","Medium","5,6"]
[null,"Infrabel","65838","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","GENT-DAMPOORT",2024,2024,36,36,"2024-09-07",45280.020833333336,"2024-09-08",45280.215277777781,"2d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS L2-IL_NW_P025_P026_L59_Y Sint Bernadettestraat - Berchem_ETCS\r\nIDS, meewerken niet mogelijk",null,null,65838,"2023-08-29","Minor","5,6"]
[null,"Infrabel","65332","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2024,2024,36,37,"2024-09-08",45280.958333333336,"2024-09-09",45280.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 3) 6 fois sur l'année",null,null,65332,"2023-02-27","Minor","1,2,3,4,5"]
[null,"Infrabel","64888","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2024,2024,36,36,"2024-09-08",45280,"2024-09-08",45280.166666666664,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Buitendienststellen van de van de volledige overeenkomstige EBP-zone gedurende minimaal 2,5 uur te bepalen tussen\r\n22.00 uur en 06.00 uur\r\nUpdate EBP release to last version\r\nR-446984",null,null,64888,"2023-01-27","Minor","5,6"]
[null,"Infrabel","62820","Athus - Meuse",">","YVOIR","Y.NEFFE",2024,2024,37,37,"2024-09-09",45280.958333333336,"2024-09-14",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble\r\nDéroulage nouveaux câbles alimentations 3KV, interrupteurs T, retour courant de traction de sous-station de Neffe\r\nRemplacement des caniveaux",null,null,62820,"2022-12-08","Minor","1,2,3,4,5"]
[null,"Infrabel","56669","Erquelinnes - Montzen",">","BRESSOUX","FROIDMONT",2024,2024,37,37,"2024-09-09",45280.333333333336,"2024-09-09",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Cette visite se fait le même lundi que la visite entre Visé-Bas et Frontière NS prévue l'après-midi\r\n- Visite de voie, tunnel et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56669,"2023-02-27","Minor","1,2,3,4,5"]
[null,"Infrabel","56839","Lille - Charleroi",">","BRUGELETTE","BRUGELETTE",2024,2024,37,37,"2024-09-09",45280.333333333336,"2024-09-13",45280.9375,"5d, 14:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\nUPM 445838",null,null,56839,"2023-09-05","Minor","1,2,3,4,5"]
[null,"Infrabel","56236","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2024,2024,37,37,"2024-09-09",45280.951388888891,"2024-09-13",45280.180555555555,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 en P3 HKV\r\n+ ETCS L2-IL_SO_P036_L96_L97_Jurbise - Mons - Saint Ghislain_ETCS",null,null,56236,"2023-01-16","Minor","1,2,3,4,5"]
[null,"Infrabel","49412","Lille - Charleroi","< >","LEUZE","TOURNAI",2024,2024,37,37,"2024-09-09",45280.972222222219,"2024-09-14",45280.194444444445,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Tournai : Renouvellement TJD 04H/05BH - 05AH/06BH\r\nTravaux de finition\r\nUPM 459562",null,null,49412,"2023-03-17","Minor","1,2,3,4,5"]
[null,"Infrabel","70140","Namur - Antwerpen","< >","MUIZEN","Y.MUIZEN",2024,2024,37,37,"2024-09-09",45280.291666666664,"2024-09-13",45280.645833333336,"4d, 08:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificiatiewerken zone 20 Muizen\r\nVervangen puntstuk en tongenstellen bundelwissels => kranen en buitenspanning bundel Muizen nodig\r\n\r\nCR 2024-140",null,null,70140,"2023-10-16","Medium","1,2,3,4,5"]
[null,"Infrabel","64352","Erquelinnes - Montzen",">","VISE","FRONT. WALLONIE-FLANDRE L40",2024,2024,37,37,"2024-09-09",45280.947916666664,"2024-09-14",45280.215277777781,"5d, 06:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails , ballast...",null,null,64352,"2023-02-27","Minor","1,2,3,4,5"]
[null,"Infrabel","57905","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2024,2024,37,37,"2024-09-09",45280.395833333336,"2024-09-13",45280.645833333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF CHA24_0027238 \r\nLille Bif Wasquehal Tourcoing : REGE - Réfection et création de regard\r\nUPM 460053",null,null,57905,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","57801","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,37,37,"2024-09-10",45280.006944444445,"2024-09-13",45280.1875,"4d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497",null,null,57801,"2022-06-02","Minor","1,2,3,4,5"]
[null,"Infrabel","61683","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","JAVA",2024,2024,37,37,"2024-09-10",45280.020833333336,"2024-09-13",45280.194444444445,"4d, 04:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien et interventions diverses sur caténaire",null,null,61683,"2023-05-16","Minor","1,2,3,4,5"]
[null,"Infrabel","67661","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,37,37,"2024-09-12",45280.375,"2024-09-12",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,67661,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","62398","Erquelinnes - Montzen",">","Y.VAL-BENOIT","FLEMALLE-ANNEXE",2024,2024,37,37,"2024-09-13",45280.958333333336,"2024-09-14",45280.208333333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Train meuleur",null,null,62398,"2023-03-09","Minor","1,2,3,4,5"]
[null,"Infrabel","47464","Erquelinnes - Montzen","< >","HUY","STATTE",2024,2024,37,38,"2024-09-13",45280.979166666664,"2024-09-16",45280.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement voie 717 et 718 + Quais centraux 6/7 et 8/9\r\nUPM : 461862",null,null,47464,"2023-05-16","Medium","5,6"]
[null,"Infrabel","58339","Namur - Antwerpen","< >","MECHELEN","HAACHT",2024,2024,37,38,"2024-09-13",45280.986111111109,"2024-09-16",45280.166666666664,"2d, 04:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"vernieuwen Muizen rooster T \r\n(samen met L27B)\r\n+\r\nCOLT 58358",null,null,58339,"2023-06-07","Medium","5,6"]
[null,"Infrabel","58052","Namur - Antwerpen","< >","Y.SINT-MARIABURG","Y.LUCHTBAL",2024,2024,37,38,"2024-09-14",45280,"2024-09-16",45280.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"oude landen 301",null,null,58052,"2022-11-08","Medium","5,6"]
[null,"Infrabel","65899","Lille - ZeeBrugge","< >","BRUGGE-ROOSTER E","LICHTERVELDE",2024,2024,37,37,"2024-09-14",45280.965277777781,"2024-09-15",45280.284722222219,"1d, 07:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-LS_NW_L66_Software_Lichtervelde - Brugge\r\nIDS, meewerken niet mogelijk",null,null,65899,"2023-08-29","Minor","5,6"]
[null,"Infrabel","61429","Athus - Meuse",">","DINANT","Y.NEFFE",2024,2024,37,37,"2024-09-14",45280.291666666664,"2024-09-15",45280.666666666664,"2d, 09:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux caténaires\r\nDéroulage nouveaux câbles alimentations 3KV, interrupteurs T, retour courant de traction de sous-station de Neffe\r\nRemplacement des caniveaux\r\nUPM : 465795",null,null,61429,"2023-05-25","Minor","5,6"]
[null,"Infrabel","58792","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2024,2024,37,38,"2024-09-14",45280.000694444447,"2024-09-16",45280.208333333336,"3d, 04:59h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing OW\r\nOnderhoud lopend spoor en spoortoestellen",null,null,58792,"2023-03-01","Minor","5,6"]
[null,"Infrabel","66651","Lille - Charleroi",">","BRAINE-LE-COMTE","SOIGNIES",2024,2024,37,37,"2024-09-14",45280.604166666664,"2024-09-14",45280.645833333336,"1d, 01:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA (\r\nRemarq 33: Avancée suite TX L96 - 90 - 130A en S39",null,null,66651,"2023-05-15","Minor","5,6"]
[null,"Infrabel","61600","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2024,2024,37,37,"2024-09-15",45280.25,"2024-09-15",45280.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,61600,"2023-01-02","Medium","5,6"]
[null,"Infrabel","66676","Lille - Charleroi",">","Y.SOIGNIES","SOIGNIES",2024,2024,37,37,"2024-09-15",45280.520833333336,"2024-09-15",45280.645833333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B",null,null,66676,"2023-03-07","Minor","5,6"]
[null,"Infrabel","66871","Athus - Meuse",">","GEDINNE","PALISEUL",2024,2024,38,38,"2024-09-16",45280.333333333336,"2024-09-16",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66871,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","64005","Lille - Antwerpen","< >","DEINZE","KORTRIJK",2024,2024,38,38,"2024-09-16",45280.972222222219,"2024-09-20",45280.173611111109,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L75 Y Zandberg IN\r\nL75 \r\nFD SP I+II+III inbegrepen\r\nLK SP I-II-III-IV inbegrepen\r\nL89 \r\nFDN SP I-II inbegrepen\r\nL86\r\nFDN-FRN inbegrepenR5/R6 niet in wegens weekendTLO L86+89",null,null,64005,"2023-03-13","Minor","1,2,3,4,5"]
[null,"Infrabel","64992","Erquelinnes - Montzen","< >","HUY","NAMUR",2024,2024,38,38,"2024-09-16",45280.96875,"2024-09-20",45280.208333333336,"4d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.43",null,null,64992,"2023-05-16","Minor","1,2,3,4,5"]
[null,"Infrabel","47473","Erquelinnes - Montzen",">","HUY","STATTE",2024,2024,38,38,"2024-09-16",45280.229166666664,"2024-09-20",45280.979166666664,"5d, 18:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement voie 717 et 718 + Quais centraux 6/7 et 8/9",null,null,47473,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","57906","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2024,2024,38,38,"2024-09-16",45280.395833333336,"2024-09-20",45280.645833333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF CHA24_0027238 \r\nLille Bif Wasquehal Tourcoing : REGE - Réfection et création de regard\r\nUPM 460055",null,null,57906,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","66872","Athus - Meuse",">","PALISEUL","GEDINNE",2024,2024,38,38,"2024-09-17",45280.333333333336,"2024-09-17",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66872,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","65924","Athus - Meuse",">","LAVAUX","MARBEHAN",2024,2024,38,38,"2024-09-18",45280.361111111109,"2024-09-18",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65924,"2023-02-28","Minor","1,2,3,4,5"]
[null,"Infrabel","66869","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,38,38,"2024-09-19",45280.333333333336,"2024-09-19",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66869,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","63052","Erquelinnes - Montzen",">","Y.VAL-BENOIT","FLEMALLE-ANNEXE",2024,2024,38,38,"2024-09-20",45280.958333333336,"2024-09-20",45280.208333333336,{"$error":"#VALUE!"},"Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Train meuleur",null,null,63052,"2023-03-02","Minor","1,2,3,4,5"]
[null,"Infrabel","52671","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2024,2024,38,39,"2024-09-20",45280.958333333336,"2024-09-23",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"réélectrification\r\n+ Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles\r\nUPM 466859",null,null,52671,"2023-11-17","Minor","5,6"]
[null,"Infrabel","58340","Namur - Antwerpen","< >","MECHELEN","HAACHT",2024,2024,38,39,"2024-09-20",45280.993055555555,"2024-09-23",45280.166666666664,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"vernieuwen Muizen rooster T \r\n(samen met L27B)\r\n+\r\nCOLT 58359",null,null,58340,"2023-06-07","Medium","5,6"]
[null,"Infrabel","70761","Lille - Charleroi","< >","LUTTRE","LUTTRE",2024,2024,38,38,"2024-09-20",45280.322916666664,"2024-09-20",45280.4375,"1d, 02:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Extension voie III et IV Gare de Luttre dans les intervalles libres de circulation de 07h30 à 10h30 ; de 10h50 à 13h20  et de 13h45 à 15h15\r\nTCR 475534\r\nCR 2024-158 envoyé le 31/08/2023 - Validé le 02/10/23",null,null,70761,"2023-10-02","Minor","1,2,3,4,5"]
[null,"Infrabel","47493","Erquelinnes - Montzen","< >","STATTE","NAMUR",2024,2024,38,38,"2024-09-21",45280.006944444445,"2024-09-22",45280.75,"2d, 17:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux OA \r\nrenouvellement quais - renouvellement passerelles - parois rocheuses\r\nUPM : 461912",null,null,47493,"2023-05-16","Medium","5,6"]
[null,"Infrabel","53696","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2024,2024,38,39,"2024-09-21",45280.006944444445,"2024-09-23",45280.166666666664,"2d, 03:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nAfwerkingsweekend 3/4\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINAL",null,null,53696,"2022-05-04","Medium","5,6"]
[null,"Infrabel","64869","Lille - Antwerpen",">","Y.MELSELE","SINT-NIKLAAS",2024,2024,38,38,"2024-09-21",45280.010416666664,"2024-09-21",45280.21875,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Reservatie onderhoud",null,null,64869,"2023-03-16","Minor","1,2,3,4,5"]
[null,"Infrabel","50629","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,38,39,"2024-09-22",45280.034722222219,"2024-09-23",45280.222222222219,"2d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris",null,null,50629,"2023-01-16","Minor","5,6"]
[null,"Infrabel","66855","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2024,2024,39,39,"2024-09-23",45280.958333333336,"2024-09-27",45280.194444444445,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z14.43\r\nPilote 6h",null,null,66855,"2023-05-16","Minor","1,2,3,4,5"]
[null,"Infrabel","61262","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","ERQUELINNES-FRONTIERE",2024,2024,39,39,"2024-09-23",45280.958333333336,"2024-09-28",45280.173611111109,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Chape+passerelles du pont 14\r\nRenouvellement des AS de Y.La Sambre\r\nSem. nuits CTL L130A+132  Finitions\r\n+ Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux préparatoires caténaire (poteaux + traverses)\r\nUPM 443084",null,null,61262,"2023-09-04","Minor","1,2,3,4,5"]
[null,"Infrabel","56840","Lille - Charleroi",">","BRUGELETTE","BRUGELETTE",2024,2024,39,39,"2024-09-23",45280.333333333336,"2024-09-27",45280.9375,"5d, 14:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\nUPM 445839",null,null,56840,"2023-09-05","Minor","1,2,3,4,5"]
[null,"Infrabel","57901","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2024,2024,39,39,"2024-09-23",45280.916666666664,"2024-09-28",45280.197916666664,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nGare de Jeumont fermée\r\nUPM 466949",null,null,57901,"2023-05-10","Minor","1,2,3,4,5"]
[null,"Infrabel","65343","Namur - Antwerpen",">","Y.MELLE-WEST","MERELBEKE-ROOSTER S",2024,2024,39,39,"2024-09-23",45280.395833333336,"2024-09-24",45280.645833333336,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"reservatie onderhoud\r\ndagdienst zone 1\r\nL50E SP B Y Melle West AW02BT niet inbegrepen tot inrit Merelbeke rooster S AW01AS niet inbegrepen\r\nBVL: 29164",null,null,65343,"2023-02-08","Minor","1,2,3,4,5"]
[null,"Infrabel","67129","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2024,2024,39,39,"2024-09-23",45280.388888888891,"2024-09-23",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses \r\nVA",null,null,67129,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","67130","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2024,2024,39,39,"2024-09-24",45280.34375,"2024-09-24",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,67130,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","63408","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,39,39,"2024-09-25",45280.375,"2024-09-25",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63408,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","63427","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,39,39,"2024-09-26",45280.375,"2024-09-26",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63427,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","56843","Lille - Charleroi","< >","JURBISE","ATH",2024,2024,39,40,"2024-09-27",45280.9375,"2024-09-30",45280.229166666664,"2d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS 01BR-01AR, 02R, 06R et 07AR - 07 BR\r\nPN 14 + 15 / Quais de Brugelette\r\nentretien PS BK 50.033\r\nUPM 445787",null,null,56843,"2023-10-23","Medium","5,6"]
[null,"Infrabel","63445","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,39,39,"2024-09-27",45280.375,"2024-09-27",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63445,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","47206","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,39,40,"2024-09-28",45280.958333333336,"2024-09-30",45280.1875,"1d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix\r\nUPM : 466030",null,null,47206,"2023-05-04","Medium","5,6"]
[null,"Infrabel","53697","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2024,2024,39,40,"2024-09-28",45280.006944444445,"2024-09-30",45280.166666666664,"2d, 03:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie, perronvernieuwing, vernieuwing Muizen Rooster T\r\nAfwerkingsweekend 4/4\r\nZie dossier 2024 - L53 Muizen-Haacht Leuven FINAL",null,null,53697,"2022-05-04","Medium","5,6"]
[null,"Infrabel","57251","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,39,39,"2024-09-28",45280.25,"2024-09-29",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Transfert CV jade et mise en service PN\r\nUPM 443123",null,null,57251,"2023-07-07","Medium","5,6"]
[null,"Infrabel","60448","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2024,2024,39,39,"2024-09-28",45280.996527777781,"2024-09-29",45280.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B\r\nTCR 464409",null,null,60448,"2023-04-26","Minor","5,6"]
[null,"Infrabel","50707","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,39,40,"2024-09-29",45280.027777777781,"2024-09-30",45280.1875,"2d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44",null,null,50707,"2022-12-16","Minor","5,6"]
[null,"Infrabel","68835","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2024,2024,39,39,"2024-09-29",45280.3125,"2024-09-29",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY (à répéter toutes les 4 semaines le dimanche)",null,null,68835,"2023-05-08","Minor","5,6"]
[null,"Infrabel","66857","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2024,2024,40,40,"2024-09-30",45280.958333333336,"2024-10-04",45280.194444444445,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z14.43\r\nPilote 6h",null,null,66857,"2023-05-16","Minor","1,2,3,4,5"]
[null,"Infrabel","59245","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2024,2024,40,40,"2024-09-30",45280.916666666664,"2024-10-05",45280.197916666664,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nGare de Jeumont fermée\r\nUPM 443160",null,null,59245,"2023-01-12","Minor","1,2,3,4,5"]
[null,"Infrabel","61062","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,40,40,"2024-09-30",45280.989583333336,"2024-10-04",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service",null,null,61062,"2023-03-20","Minor","1,2,3,4,5"]
[null,"Infrabel","62570","Namur - Antwerpen","< >","MECHELEN","KONTICH-LINT",2024,2024,40,40,"2024-09-30",45280.993055555555,"2024-10-05",45280.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\nZ31.23 : studie nog uit te voeren door I-CBE & Z30.23 : studie nog uit te voeren door I-CBE",null,null,62570,"2023-06-07","Minor","1,2,3,4,5"]
[null,"Infrabel","55567","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,40,40,"2024-09-30",45280.947916666664,"2024-10-04",45280.197916666664,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"4 Chapes L140 - 38.279 39.681 39.749 40.133\r\nPréparations\r\nTCR 445347\r\nTX en corrélation avec Colt 49375 - TCR 445347",null,null,55567,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","66891","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,40,40,"2024-09-30",45280.388888888891,"2024-09-30",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses",null,null,66891,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","68957","Lille - Charleroi",">","SOIGNIES","NEUFVILLES",2024,2024,40,40,"2024-10-01",45280.333333333336,"2024-10-01",45280.541666666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B",null,null,68957,"2023-05-12","Minor","1,2,3,4,5"]
[null,"Infrabel","66892","Athus - Meuse",">","BEAURAING","HOUYET",2024,2024,40,40,"2024-10-01",45280.388888888891,"2024-10-01",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses",null,null,66892,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","66020","Athus - Meuse",">","YVOIR","LUSTIN",2024,2024,40,40,"2024-10-02",45280.375,"2024-10-02",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,66020,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","67664","Athus - Meuse",">","VIRTON","SIGNEULX",2024,2024,40,40,"2024-10-03",45280.375,"2024-10-03",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,67664,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","66003","Athus - Meuse",">","LUSTIN","YVOIR",2024,2024,40,40,"2024-10-03",45280.375,"2024-10-03",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,66003,"2023-03-29","Minor","1,2,3,4,5"]
[null,"Infrabel","57016","Erquelinnes - Montzen","< >","SERAING","FLEMALLE-ANNEXE",2024,2024,40,41,"2024-10-04",45280.958333333336,"2024-10-07",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de l'appareil de voie  21AC + liaison\r\nUPM : 462845",null,null,57016,"2023-04-12","Medium","5,6"]
[null,"Infrabel","66895","Athus - Meuse",">","GEDINNE","VONECHE",2024,2024,40,40,"2024-10-04",45280.333333333336,"2024-10-04",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,66895,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","55608","Erquelinnes - Montzen","< >","STATTE","NAMUR",2024,2024,40,40,"2024-10-05",45280.006944444445,"2024-10-06",45280.75,"2d, 17:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux OA \r\nRenouvellement quais - renouvellement passerelles - parois rocheuses\r\nUPM : 461924\r\n+ visites Andenne - MLD + Beez-Scaligneaux",null,null,55608,"2023-05-16","Medium","5,6"]
[null,"Infrabel","57521","Lille - Antwerpen","< >","Y.ZANDBERG","MOUSCRON-FRONTIERE",2024,2024,40,41,"2024-10-05",45280.027777777781,"2024-10-07",45280.166666666664,"2d, 03:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"ETCS1-FS-NW-Kortrijk\r\nMeewerken niet mogelijk op grote zone van Kortrijk\r\nUitbreiding van de aanvraag voor dienst onderhoud I-AM;\r\nMeewerken wel mogelijk op baanvakken L89 FND - Y Zandberg + L69 Y West Kortrijk - Menen + L75 Y Zandberg - FVG + L66 Y Kor",null,null,57521,"2023-03-14","Medium","5,6"]
[null,"Infrabel","48661","Lille - Charleroi","< >","Y.JURBISE","MONS",2024,2024,40,40,"2024-10-05",45280.25,"2024-10-06",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.5.53\r\nMise HS en P4\r\nUPM 459883",null,null,48661,"2023-03-20","Medium","5,6"]
[null,"Infrabel","47507","Athus - Meuse","< >","Y.NEFFE","HOUYET",2024,2024,40,41,"2024-10-05",45280.25,"2024-10-07",45280.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux OA tronçons Anseremme - Gendron et Gendron - Houyet (entretien tunnels, parois,...)\r\n+ Massification travaux pour adaptation du tracé entre 10600 et 13300 pour augmenter la vitesse\r\n+ Visites\r\nUPM : 462993",null,null,47507,"2023-12-15","Medium","5,6"]
[null,"Infrabel","67392","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,40,40,"2024-10-05",45280.375,"2024-10-05",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie A\r\nVisite voie A",null,null,67392,"2023-04-07","Minor","5,6"]
[null,"Infrabel","48954","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2024,2024,40,40,"2024-10-05",45280.340277777781,"2024-10-06",45280.659722222219,"2d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A/B Ottignies / Gembloux + maintenance infrastructure + contrôles \r\nUPM 466952",null,null,48954,"2023-06-27","Minor","5,6"]
[null,"Infrabel","62572","Namur - Antwerpen","< >","Y.NAZARETH","Y.OOST DRIEHOEK AARSCHOT",2024,2024,41,41,"2024-10-07",45280.958333333336,"2024-10-12",45280.1875,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\n'ZCC.23 : studie nog uit te voeren door I-CBE & Z28.25 : studie nog uit te voeren door I-CBE\r\n+\r\nOnderhoud\r\nZ28.25 : studie nog uit te voeren door I-CBE   COLT 62961",null,null,62572,"2022-12-29","Minor","1,2,3,4,5"]
[null,"Infrabel","69774","Lille - Charleroi","< >","LUTTRE","ROUX",2024,2024,41,41,"2024-10-07",45280.333333333336,"2024-10-11",45280.666666666664,"5d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de ballast avec un train de renouvellement C75 \r\nL124 A voie A entre BK 41.700 et 45.350\r\nTCR 470541\r\nCR 2024-158 envoyé le 31/08/2023- validé le  15/09/23",null,null,69774,"2023-10-31","Minor","1,2,3,4,5"]
[null,"Infrabel","47569","Lille - Charleroi",">","JURBISE","MONS",2024,2024,41,46,"2024-10-07",45280.951388888891,"2024-11-16",45280.215277777781,"40d, 06:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification - Phase 4 - 2024\r\nDépose anciens poteaux\r\nUPM 459875",null,null,47569,"2023-03-20","Minor","1,2,3,4,5"]
[null,"Infrabel","60114","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2024,2024,41,41,"2024-10-07",45280.986111111109,"2024-10-11",45280.236111111109,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z11.22",null,null,60114,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","62208","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,41,41,"2024-10-07",45280.923611111109,"2024-10-12",45280.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux préparatoires caténaire (poteaux + traverses)\r\n+ Maintenance Z2. 51  P3 HKV\r\nTCR 466842",null,null,62208,"2023-07-31","Minor","1,2,3,4,5"]
[null,"Infrabel","66899","Athus - Meuse",">","PALISEUL","GEDINNE",2024,2024,41,41,"2024-10-08",45280.333333333336,"2024-10-08",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66899,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","67815","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2024,2024,41,41,"2024-10-09",45280.333333333336,"2024-10-09",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11\r\nTCR 467944",null,null,67815,"2023-10-31","Minor","1,2,3,4,5"]
[null,"Infrabel","60802","Namur - Antwerpen","< >","ANTWERPEN-D.S.-RHODESIE","ANTWERPEN-D.S.-RHODESIE",2024,2024,41,41,"2024-10-09",45280.25,"2024-10-09",45280.75,"1d, 12:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"massificatiewerken",null,null,60802,"2022-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","66902","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,41,41,"2024-10-10",45280.333333333336,"2024-10-10",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66902,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","55951","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,41,41,"2024-10-10",45280.395833333336,"2024-10-10",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nMise HS en P2\r\nUPM 459769",null,null,55951,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","66903","Athus - Meuse",">","BERTRIX","PALISEUL",2024,2024,41,41,"2024-10-11",45280.333333333336,"2024-10-11",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,66903,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","47462","Erquelinnes - Montzen",">","HUY","ANDENNE",2024,2024,41,42,"2024-10-11",45280.979166666664,"2024-10-14",45280.229166666664,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement voie 717 et 718 + Quais centraux 6/7 et 8/9\r\nUPM 461928",null,null,47462,"2023-05-16","Minor","5,6"]
[null,"Infrabel","47210","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,41,42,"2024-10-12",45280.958333333336,"2024-10-14",45280.1875,"1d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix\r\n+ Visites Bertrix-Straimont\r\nUPM : 466032",null,null,47210,"2023-05-04","Medium","5,6"]
[null,"Infrabel","54832","Athus - Meuse",">","DINANT","Y.NEFFE",2024,2024,41,41,"2024-10-12",45280.291666666664,"2024-10-13",45280.666666666664,"2d, 09:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux caténaires\r\nDéroulage nouveaux câbles alimentations 3KV, interrupteurs T, retour courant de traction de sous-station de Neffe\r\nRemplacement des caniveaux\r\nUPM : 465807",null,null,54832,"2023-05-02","Minor","5,6"]
[null,"Infrabel","60784","Lille - Charleroi",">","LUTTRE","ROUX",2024,2024,41,41,"2024-10-12",45280.25,"2024-10-13",45280.708333333336,"1d, 11:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance Z05.52\r\nUPM 445282",null,null,60784,"2023-02-23","Minor","5,6"]
[null,"Infrabel","58794","Namur - Antwerpen","< >","ESSEN","Y.LUCHTBAL",2024,2024,41,42,"2024-10-12",45280.000694444447,"2024-10-14",45280.166666666664,"3d, 03:59h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing OW\r\nOnderhoud lopend spoor en spoortoestellen",null,null,58794,"2023-03-01","Minor","5,6"]
[null,"Infrabel","64164","Namur - Antwerpen","< >","MECHELEN","Y.HEIKE",2024,2024,41,42,"2024-10-12",45280.003472222219,"2024-10-14",45280.194444444445,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"masterplan mechelen \r\ndeels met L27,L53A en spoor V in station Mechelen\r\n+\r\nvernieuwen spoor L54,OW2 en AW01H\r\nWE met vertakking Heike inbegrepen\r\nBTS (L54?) tussen de weekends te voorzien",null,null,64164,"2023-05-24","Medium","5,6"]
[null,"Infrabel","61498","Namur - Antwerpen","< >","HAACHT-WIJKSPOOR","Y.DIJLEBRUG",2024,2024,41,41,"2024-10-13",45280.006944444445,"2024-10-13",45280.25,"1d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossing rails L53 2024",null,null,61498,"2022-12-15","Minor","5,6"]
[null,"Infrabel","50630","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,41,42,"2024-10-13",45280.034722222219,"2024-10-14",45280.222222222219,"2d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nNuit Ctl Ottignies/Saint Joris",null,null,50630,"2023-01-16","Minor","5,6"]
[null,"Infrabel","63275","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2024,2024,42,42,"2024-10-14",45280.951388888891,"2024-10-19",45280.208333333336,"5d, 06:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Buitenwerken, meewerken mogelijk, CTL spoor A+B\r\nIL for ETCS_IL-SML_NO_L53_Mechelen - Londerzeel",null,null,63275,"2022-12-13","Minor","1,2,3,4,5"]
[null,"Infrabel","60210","Lille - Antwerpen","< >","ANTWERPEN-ZUID","Y.MELSELE",2024,2024,42,42,"2024-10-14",45280.993055555555,"2024-10-19",45280.190972222219,"5d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoudsweek Kennedytunnel",null,null,60210,"2022-07-19","Minor","1,2,3,4,5"]
[null,"Infrabel","67723","Athus - Meuse","< >","Y.AUBANGE","AUBANGE-FRONTIERE-FRANCE",2024,2024,42,42,"2024-10-14",45280.375,"2024-10-14",45280.583333333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite voie unique L 165/2 \r\nVisite voie unique L 165/3\r\nVisite voie unique L 165/1\r\nMaintenance",null,null,67723,"2023-04-08","Minor","1,2,3,4,5"]
[null,"Infrabel","49510","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2024,2024,42,42,"2024-10-14",45280.923611111109,"2024-10-19",45280.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2. 51  P3 HKV\r\n+ Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux préparatoires caténaire (poteaux + traverses)\r\nTCR 466844",null,null,49510,"2023-07-31","Minor","1,2,3,4,5"]
[null,"Infrabel","63384","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2024,2024,42,42,"2024-10-15",45280.375,"2024-10-15",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63384,"2023-01-05","Minor","1,2,3,4,5"]
[null,"Infrabel","67131","Athus - Meuse",">","DINANT","Y.NEFFE",2024,2024,42,42,"2024-10-16",45280.34375,"2024-10-16",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,67131,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","63446","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,42,42,"2024-10-18",45280.375,"2024-10-18",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63446,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","67137","Athus - Meuse",">","VONECHE","BEAURAING",2024,2024,42,42,"2024-10-19",45280.333333333336,"2024-10-19",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,67137,"2023-04-07","Minor","5,6"]
[null,"Infrabel","64842","Lille - Antwerpen",">","OOSTAKKER","GENT-DAMPOORT",2024,2024,42,42,"2024-10-19",45280.020833333336,"2024-10-19",45280.229166666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Reservatie onderhoud",null,null,64842,"2023-03-16","Minor","1,2,3,4,5"]
[null,"Infrabel","49167","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2024,2024,42,42,"2024-10-19",45280.986111111109,"2024-10-20",45280.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nMini CTL\r\nUPM: 459893",null,null,49167,"2023-03-20","Medium","5,6"]
[null,"Infrabel","67138","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,42,42,"2024-10-20",45280.333333333336,"2024-10-20",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,67138,"2023-04-07","Minor","5,6"]
[null,"Infrabel","61499","Namur - Antwerpen","< >","HAACHT-WIJKSPOOR","Y.DIJLEBRUG",2024,2024,42,42,"2024-10-20",45280.006944444445,"2024-10-20",45280.25,"1d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossing rails L53 2024",null,null,61499,"2022-12-15","Minor","5,6"]
[null,"Infrabel","50708","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,42,43,"2024-10-20",45280.027777777781,"2024-10-21",45280.1875,"2d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44",null,null,50708,"2022-12-16","Minor","5,6"]
[null,"Infrabel","61745","Erquelinnes - Montzen",">","TILLEUR","LEMAN",2024,2024,43,43,"2024-10-21",45280.958333333336,"2024-10-26",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement pièces caténaire",null,null,61745,"2023-03-01","Minor","1,2,3,4,5"]
[null,"Infrabel","64248","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,43,43,"2024-10-21",45280.979166666664,"2024-10-25",45280.1875,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)",null,null,64248,"2023-01-12","Minor","1,2,3,4,5"]
[null,"Infrabel","61060","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,43,43,"2024-10-21",45280.989583333336,"2024-10-25",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service",null,null,61060,"2023-03-20","Minor","1,2,3,4,5"]
[null,"Infrabel","65414","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2024,2024,43,43,"2024-10-21",45280.381944444445,"2024-10-21",45280.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41",null,null,65414,"2023-02-23","Minor","1,2,3,4,5"]
[null,"Infrabel","58550","Lille - ZeeBrugge","< >","Y.PELIKAAN","KNOKKE",2024,2024,43,43,"2024-10-22",45280.020833333336,"2024-10-26",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Fietstunnel sportcentra Heist KP 112.000-112.100\r\nR6 tot 06u00.",null,null,58550,"2023-05-16","Minor","1,2,3,4,5"]
[null,"Infrabel","67134","Athus - Meuse",">","BEAURAING","HOUYET",2024,2024,43,43,"2024-10-22",45280.388888888891,"2024-10-22",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses",null,null,67134,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","65925","Athus - Meuse",">","LAVAUX","MARBEHAN",2024,2024,43,43,"2024-10-23",45280.361111111109,"2024-10-23",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65925,"2023-02-21","Minor","1,2,3,4,5"]
[null,"Infrabel","66004","Athus - Meuse",">","LUSTIN","YVOIR",2024,2024,43,43,"2024-10-24",45280.375,"2024-10-24",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,66004,"2023-04-04","Minor","1,2,3,4,5"]
[null,"Infrabel","69122","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2024,2024,43,43,"2024-10-26",45280.958333333336,"2024-10-27",45280.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2024-073\r\nMES ETCS1FS Tamines – Chatelet.",null,null,69122,"2023-12-20","Minor","5,6"]
[null,"Infrabel","67497","Erquelinnes - Montzen",">","AMAY","ENGIS",2024,2024,43,43,"2024-10-26",45280.333333333336,"2024-10-26",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67497,"2023-04-06","Minor","5,6"]
[null,"Infrabel","53177","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2024,2024,43,45,"2024-10-26",45280.020833333336,"2024-11-04",45280.166666666664,"9d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"IDS ETCS - Mechelen-Londerzeel\r\n9 dagen TLO\r\n\r\nherlading ROCS op 27/10 van 00:30 tot 04:30 ===>geen bewerkingen door seinhuis mogelijk",null,null,53177,"2023-05-16","High","1,2,3,4,5,6,7"]
[null,"Infrabel","68837","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2024,2024,43,43,"2024-10-26",45280.3125,"2024-10-26",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY (à répéter toutes les 4 semaines le samedi)",null,null,68837,"2023-05-08","Minor","5,6"]
[null,"Infrabel","65426","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","ESSEN-GRENS",2024,2024,43,43,"2024-10-27",45280.020833333336,"2024-10-27",45280.1875,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR2024-026\r\nVerhuis Computerzaal SI Blok 12 naar nieuw gebouw (ganse actiezone Blok 12 buiten dienst)\r\nNacht za ^zo, min 4 uur aaneensluitend ganse actiezone Blok 12 buiten dienst. \r\nWeekend te kiezen tussen 14/09/2024 en 29/09/2024\r\nR-453704",null,null,65426,"2023-12-05","Minor","5,6"]
[null,"Infrabel","67412","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2024,2024,43,43,"2024-10-27",45280.375,"2024-10-27",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B\r\nEntretien / maintenance voie B",null,null,67412,"2023-04-08","Minor","1,2,3,4,5"]
[null,"Infrabel","67488","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2024,2024,43,43,"2024-10-27",45280.354166666664,"2024-10-27",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,67488,"2023-04-06","Minor","5,6"]
[null,"Infrabel","56086","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,44,44,"2024-10-28",45280.958333333336,"2024-10-31",45280.208333333336,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des Tabliers métalliques  + 5chapes \r\nTravaux RER Ottignies (CSV)\r\n+ Maintenance Z3. 51  P3  HKV\r\nUPM 460238",null,null,56086,"2023-03-22","Minor","1,2,3,4,5"]
[null,"Infrabel","60926","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2024,2024,44,44,"2024-10-28",45280.979166666664,"2024-10-31",45280.194444444445,"3d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.52",null,null,60926,"2022-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","59249","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2024,2024,44,44,"2024-10-28",45280.916666666664,"2024-11-02",45280.197916666664,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nGare de Jeumont fermée\r\nUPM 443418",null,null,59249,"2023-09-11","Minor","1,2,3,4,5"]
[null,"Infrabel","47761","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,44,47,"2024-10-28",45280.3125,"2024-11-18",45280.25,"21d, 22:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Révision suite renouvellement ballast par train C75 à Aix-sur-Cloie VB.\r\nUPM : 466380",null,null,47761,"2023-05-05","High","1,2,3,4,5,6,7"]
[null,"Infrabel","64167","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-NEKKERSPOEL",2024,2024,44,44,"2024-10-28",45280.166666666664,"2024-11-02",45280.003472222219,"5d, 20:05h","Continuous",null,"T","","",null,null,null,null,null,null,null,"masterplan mechelen: \r\nL53 BD voor 9 dagen tijdens lange TLO.\r\nNO werkt mee voor masterplan Mechelen.\r\nBijkomend hebben zij TLO L27 nodig tussen Y.Weerde en Nekkerspoel.\r\n\r\nR-461414",null,null,64167,"2023-09-28","Medium","1,2,3,4,5"]
[null,"Infrabel","67140","Athus - Meuse",">","PALISEUL","GEDINNE",2024,2024,44,44,"2024-10-29",45280.333333333336,"2024-10-29",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,67140,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","67141","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,44,44,"2024-10-31",45280.333333333336,"2024-10-31",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,67141,"2023-03-21","Minor","1,2,3,4,5"]
[null,"Infrabel","60313","Lille - Charleroi","< >","QUEVY-FRONTIERE","TUBIZE",2024,2024,44,44,"2024-10-31",45280.083333333336,"2024-11-01",45280.145833333336,"2d, 01:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rechargement EBP/PLP pour MES SIW L118 Mons-Obourg\r\nLié à la demande COLT 45837\r\nNécessité d'un interval de 3h\r\nCR 2024-172 envoyé le 4/10/2024 - TCR 461027 (Modif date + heure Nuit 31/10^01/11/24 de 02.00 à 3.30) Validé le 16/10/23\r\nUPM 461027",null,null,60313,"2023-11-08","Minor","5,6"]
[null,"Infrabel","66097","Athus - Meuse",">","YVOIR","DINANT",2024,2024,44,44,"2024-10-31",45280.385416666664,"2024-10-31",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,66097,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","73353","Lille - Charleroi",">","MONS","MONS",2024,2024,44,44,"2024-11-01",45280.260416666664,"2024-11-03",45280.90625,"3d, 15:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Démontage ancienne caténaire en gare de Mons : Prévoir 08h00 pour déposer cs2 6 du pt 96 au 133N 304m et Cs2 6bis du 80N au 106 408m. Prévoir 08h00 pour dérouler CC 6 su 80N au 133N. Prévoir 08h00 pour régler et penduler Prévoir 08h00 pour IC 124, IC 13",null,null,73353,"2023-11-20","Minor","5,6"]
[null,"Infrabel","49320","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET",2024,2024,44,44,"2024-11-02",45280.916666666664,"2024-11-03",45280.916666666664,"1d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 46Ai - 46BI - 48I - 47I - 01J - 02AJ - \r\nPhase 2.c\r\nMSH faisceau A + Trapèze de Châtelet du Cas elec 27331\r\nDossier de concertation validé le 28 octobre 2021\r\nUPM: 459905",null,null,49320,"2023-11-27","Minor","5,6"]
[null,"Infrabel","67531","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2024,2024,44,44,"2024-11-02",45280.354166666664,"2024-11-02",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67531,"2023-04-06","Minor","5,6"]
[null,"Infrabel","49601","Athus - Meuse",">","LIBRAMONT","HATRIVAL",2024,2024,44,44,"2024-11-03",45280.020833333336,"2024-11-03",45280.625,"1d, 14:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Mise en service PLP et modifications ETCS gare de Bertrix et bloc automatique Libramont - Bertrix et nouvelle ligne L162/1.\r\nMassifié avec MES Bertrix\r\nUPM 462919",null,null,49601,"2023-04-13","Minor","5,6"]
[null,"Infrabel","67532","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2024,2024,44,44,"2024-11-03",45280.354166666664,"2024-11-03",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67532,"2023-04-20","Minor","5,6"]
[null,"Infrabel","67083","Lille - Charleroi",">","ATH","BRUGELETTE",2024,2024,45,45,"2024-11-04",45280.333333333336,"2024-11-04",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno",null,null,67083,"2023-05-09","Minor","1,2,3,4,5"]
[null,"Infrabel","56670","Erquelinnes - Montzen",">","BRESSOUX","FROIDMONT",2024,2024,45,45,"2024-11-04",45280.333333333336,"2024-11-04",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Cette visite se fait le même lundi que la visite entre Visé-Bas et Frontière NS prévue l'après-midi\r\n- Visite de voie, tunnel et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56670,"2023-02-06","Minor","1,2,3,4,5"]
[null,"Infrabel","59250","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2024,2024,45,45,"2024-11-04",45280.916666666664,"2024-11-09",45280.197916666664,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nGare de Jeumont fermée\r\nUPM 443421",null,null,59250,"2023-01-13","Minor","1,2,3,4,5"]
[null,"Infrabel","62159","Lille - Charleroi",">","BRUXELLES-MIDI","LOT",2024,2024,45,45,"2024-11-04",45280.986111111109,"2024-11-09",45280.229166666664,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FH_04 Area CE volgens onderhoudskalender 2024\r\nBuitendienststelling L96 spoor B tussen FBMZ en Lot.",null,null,62159,"2023-03-07","Minor","1,2,3,4,5"]
[null,"Infrabel","65850","Lille - ZeeBrugge","< >","LICHTERVELDE","KORTRIJK",2024,2024,45,45,"2024-11-04",45280.993055555555,"2024-11-09",45280.1875,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1-LS_NW_L66_Software_Kortrijk - Lichtervelde\r\nTesten, meewerken niet mogelijk\r\n\r\nKortrijk en Lichtervelde vrij",null,null,65850,"2023-02-20","Minor","1,2,3,4,5"]
[null,"Infrabel","61912","Namur - Antwerpen",">","SCHAERBEEK","Y.SCHAERBEEK-GROUPE G",2024,2024,45,45,"2024-11-04",45280.427083333336,"2024-11-08",45280.625,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FSR_03 volgens onderhoudskalender Area CE\r\nLokale wissels te FSR thv sporen A L27 en B L36,\r\nFSR sp IX,X en XI",null,null,61912,"2023-03-07","Minor","1,2,3,4,5"]
[null,"Infrabel","64772","Lille - Antwerpen","< >","SINT-NIKLAAS","Y.MELSELE",2024,2024,45,45,"2024-11-05",45280.013888888891,"2024-11-09",45280.184027777781,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud Sint Niklaas \r\n\r\n*perron II-V inbegrepen. \r\n*SP I + SP A  niet inbegrepen om doorrit naar L54 toe te laten",null,null,64772,"2023-08-07","Minor","1,2,3,4,5"]
[null,"Infrabel","56679","Erquelinnes - Montzen",">","VISE","BRESSOUX",2024,2024,45,45,"2024-11-05",45280.395833333336,"2024-11-05",45280.611111111109,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"- Visite de voie, PN et intervention avec S460 sur la voie contiguë\r\n- Visite de voie jusqu'aux AW (NE)",null,null,56679,"2023-02-06","Minor","1,2,3,4,5"]
[null,"Infrabel","67144","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2024,2024,45,45,"2024-11-05",45280.34375,"2024-11-05",45280.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,67144,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","67501","Erquelinnes - Montzen",">","JAVA","STATTE",2024,2024,45,45,"2024-11-06",45280.354166666664,"2024-11-06",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67501,"2023-03-29","Minor","1,2,3,4,5"]
[null,"Infrabel","67521","Erquelinnes - Montzen",">","JAVA","ANDENNE",2024,2024,45,45,"2024-11-07",45280.5625,"2024-11-07",45280.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67521,"2023-04-20","Minor","1,2,3,4,5"]
[null,"Infrabel","55952","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2024,2024,45,45,"2024-11-07",45280.395833333336,"2024-11-07",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nMise HS en P2\r\nUPM 459770",null,null,55952,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","47812","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,45,47,"2024-11-08",45280.958333333336,"2024-11-18",45280.208333333336,"9d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement ballast par train C75 (phase 1 : VB).\r\nUPM : 463033",null,null,47812,"2023-04-13","High","1,2,3,4,5,6,7"]
[null,"Infrabel","60138","Athus - Meuse","< >","HAVERSIN","ROCHEFORT-JEMELLE",2024,2024,45,46,"2024-11-08",45280.986111111109,"2024-11-12",45280.180555555555,"3d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaire \r\nPhase 26 Marloie : Tir caténaire 7-8-9-11\r\nmassifs / poteaux/ CDPA / feeder / R3 mixte / démontage caténaire existante\r\nUPM 462872",null,null,60138,"2023-10-06","Medium","5,6"]
[null,"Infrabel","58343","Namur - Antwerpen","< >","MUIZEN-ROOSTER T","LEUVEN",2024,2024,45,46,"2024-11-09",45280,"2024-11-12",45280.166666666664,"3d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"railvernieuwing nodig wegens veel railfouten)",null,null,58343,"2023-04-26","Medium","5,6"]
[null,"Infrabel","60449","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2024,2024,45,45,"2024-11-09",45280.996527777781,"2024-11-10",45280.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B\r\nTCR 464410",null,null,60449,"2023-04-26","Minor","5,6"]
[null,"Infrabel","69698","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,45,45,"2024-11-10",45280,"2024-11-10",45280.736111111109,"2d, 17:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwingen bundel Q\r\nafwerking BVL\r\nR-469628\r\nCR 2024-102",null,null,69698,"2023-10-16","Minor","5,6"]
[null,"Infrabel","64921","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2024,2024,45,45,"2024-11-10",45280.3125,"2024-11-10",45280.520833333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Noord\r\nBuitendienststellen van de van de volledige overeenkomstige EBP-zone gedurende minimaal 4 uur te bepalen tussen 06.00 uur en 14.00 uur\r\nUpdate EBP release to last version\r\nR-447105",null,null,64921,"2023-01-27","Minor","5,6"]
[null,"Infrabel","50636","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2024,2024,46,46,"2024-11-11",45280.979166666664,"2024-11-15",45280.222222222219,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de voie + PN \r\nP3 HKM",null,null,50636,"2022-11-10","Minor","1,2,3,4,5"]
[null,"Infrabel","52456","Erquelinnes - Montzen","< >","Y.NORD","ERQUELINNES-FRONTIERE",2024,2024,46,46,"2024-11-11",45280.923611111109,"2024-11-16",45280.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5. 51  P3\r\n+ travaux signalisation renouvellement CV en L132\r\nTCR 467259",null,null,52456,"2023-09-04","Minor","1,2,3,4,5"]
[null,"Infrabel","51113","Namur - Antwerpen","< >","OTTIGNIES","OTTIGNIES",2024,2024,46,46,"2024-11-12",45280.333333333336,"2024-11-15",45280.666666666664,"3d, 08:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance voies 9 et 10 en gare d'Ottignies\r\nMHS zone voies 120,119,140,996 (Voie B L140): points de limites entre les OR- talon 12R / Talon 16AR-Talon 19BR\r\nUPM : 466498",null,null,51113,"2023-05-08","Medium","1,2,3,4,5"]
[null,"Infrabel","57802","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2024,2024,46,46,"2024-11-13",45280.006944444445,"2024-11-15",45280.1875,"3d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen rails Lichtervelde kp 29 145 - Roeselare Kp 36 497",null,null,57802,"2022-06-02","Minor","1,2,3,4,5"]
[null,"Infrabel","57188","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2024,2024,46,47,"2024-11-15",45280.958333333336,"2024-11-18",45280.236111111109,"2d, 06:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nUPM 460074",null,null,57188,"2023-03-21","Medium","5,6"]
[null,"Infrabel","60137","Athus - Meuse","< >","HAVERSIN","ROCHEFORT-JEMELLE",2024,2024,46,47,"2024-11-15",45280.986111111109,"2024-11-18",45280.180555555555,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaire .\r\nPhase 27 Marloie : Tir caténaire 7-8-9-11\r\nmassifs / poteaux/ CDPA / feeder / R3 mixte / démontage caténaire existante\r\nUPM 462875",null,null,60137,"2023-10-06","Medium","5,6"]
[null,"Infrabel","57582","Lille - ZeeBrugge","< >","Y.KORTRIJK-WEST","LICHTERVELDE",2024,2024,46,47,"2024-11-15",45280.993055555555,"2024-11-18",45280.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Indienstname PLP \r\nLichtervelde - Roeselare\r\nStations niet inbegrepen\r\n\r\nTestritten op zondag tot op de perrons van Lichtervelde en Roeselare in overleg met regelaar",null,null,57582,"2022-04-27","Medium","5,6"]
[null,"Infrabel","50709","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,46,47,"2024-11-17",45280.027777777781,"2024-11-18",45280.1875,"2d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44",null,null,50709,"2022-12-16","Minor","5,6"]
[null,"Infrabel","69699","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2024,2024,46,46,"2024-11-17",45280,"2024-11-17",45280.736111111109,"1d, 17:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwingen bundel Q\r\nafwerking BVL\r\nR-469630\r\nCR 2024-103",null,null,69699,"2023-10-16","Medium","5,6"]
[null,"Infrabel","55570","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,47,47,"2024-11-18",45280.958333333336,"2024-11-22",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des Tabliers métalliques  + 5chapes \r\nCTL finition + levé ART\r\nUPM 444745",null,null,55570,"2023-01-18","Minor","1,2,3,4,5"]
[null,"Infrabel","64350","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,47,47,"2024-11-18",45280.958333333336,"2024-11-23",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails , ballast...",null,null,64350,"2023-02-27","Minor","1,2,3,4,5"]
[null,"Infrabel","58552","Lille - ZeeBrugge","< >","Y.PELIKAAN","KNOKKE",2024,2024,47,47,"2024-11-18",45280.979166666664,"2024-11-22",45280.1875,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Fietstunnel sportcentra Heist KP 112.000-112.100\r\n\r\n\r\n*R5/R6 in weekend TLO",null,null,58552,"2023-05-17","Minor","1,2,3,4,5"]
[null,"Infrabel","64006","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2024,2024,47,47,"2024-11-18",45280.979166666664,"2024-11-22",45280.1875,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud FGSP Nacht: Werkveld 4.1\r\nBijkomend mogelijk:\r\nFD SP Iv-V inbegrepen\r\nL73\r\nFLC SP I-II inbegrepen\r\nL86 tot FRN \r\n\r\nR5/R6 niet inbegrepen wegens weekend TLO L50A",null,null,64006,"2023-03-15","Minor","1,2,3,4,5"]
[null,"Infrabel","61064","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,47,47,"2024-11-18",45280.989583333336,"2024-11-22",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service",null,null,61064,"2023-03-20","Minor","1,2,3,4,5"]
[null,"Infrabel","47763","Athus - Meuse",">","Y.AUBANGE","HALANZY",2024,2024,47,48,"2024-11-18",45280.3125,"2024-11-29",45280.666666666664,"12d, 08:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Sécurisation des pistes suite renouvellement ballast par train C75 à Aix-sur-Cloie VB.\r\nUPM : 466382",null,null,47763,"2023-12-18","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","61203","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2024,2024,47,47,"2024-11-18",45280.930555555555,"2024-11-23",45280.180555555555,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.54",null,null,61203,"2023-02-09","Minor","1,2,3,4,5"]
[null,"Infrabel","60122","Namur - Antwerpen","< >","ANTWERPEN-NOORDERDOKKEN","Y.HOLLAND",2024,2024,47,47,"2024-11-18",45280.975694444445,"2024-11-22",45280.166666666664,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderheid SIG Y luchtbal en onderhoud wissel Y Antwerpen-luchtbal",null,null,60122,"2022-09-05","Minor","1,2,3,4,5"]
[null,"Infrabel","64773","Lille - Antwerpen","< >","SINT-NIKLAAS","Y.MELSELE",2024,2024,47,47,"2024-11-19",45280.013888888891,"2024-11-22",45280.184027777781,"4d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud Sint Niklaas \r\n\r\n*perron II-V inbegrepen. \r\n*SP I + SP A  niet inbegrepen om doorrit naar L54 toe te laten\r\n*R5/R6 niet inbegrepen wegens TLO L53",null,null,64773,"2023-08-09","Minor","1,2,3,4,5"]
[null,"Infrabel","69266","Athus - Meuse",">","STOCKEM-NORD","ARLON",2024,2024,47,47,"2024-11-19",45280.361111111109,"2024-11-19",45280.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,69266,"2023-05-22","Minor","1,2,3,4,5"]
[null,"Infrabel","60098","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2024,2024,47,47,"2024-11-20",45280.395833333336,"2024-11-20",45280.625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud wissels antwerpen centraal +1 \r\n\r\nTe bekijken op middellange -korte termijn",null,null,60098,"2022-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","47159","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,47,48,"2024-11-22",45280.958333333336,"2024-11-25",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nélectrification en continu\r\nUPM: 460264",null,null,47159,"2023-03-22","Minor","5,6"]
[null,"Infrabel","47813","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,47,48,"2024-11-22",45280.958333333336,"2024-11-25",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement ballast par train C75 (phase 2 : VA).\r\nUPM : 463036",null,null,47813,"2023-04-13","Minor","5,6"]
[null,"Infrabel","67156","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,47,47,"2024-11-22",45280.333333333336,"2024-11-22",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,67156,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","48874","Namur - Antwerpen",">","WAVRE","OTTIGNIES",2024,2024,47,47,"2024-11-23",45280.333333333336,"2024-11-23",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes+ maintenances infrastructure et contrôles\r\nUPM : 465260",null,null,48874,"2023-04-27","Minor","5,6"]
[null,"Infrabel","59105","Lille - Antwerpen",">","ZWIJNDRECHT-ROOSTER D","Y.WEST BERCHEM",2024,2024,47,48,"2024-11-23",45280.020833333336,"2024-11-25",45280.1875,"2d, 04:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"werken NMBS/brug antwerpen zuid (zonder plaatsing van extra isolatoren)",null,null,59105,"2023-07-28","Minor","5,6"]
[null,"Infrabel","67414","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,47,47,"2024-11-23",45280.375,"2024-11-23",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie A\r\nVisite voie A",null,null,67414,"2023-04-08","Minor","5,6"]
[null,"Infrabel","48984","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2024,2024,47,47,"2024-11-24",45280.333333333336,"2024-11-24",45280.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144 + 130/1 + maintenance infrastructure + contrôles",null,null,48984,"2023-01-18","Minor","5,6"]
[null,"Infrabel","66303","Lille - Charleroi","< >","MANAGE","LUTTRE",2024,2024,47,47,"2024-11-24",45280.013888888891,"2024-11-24",45280.222222222219,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Déchargement train Robel : chantier de Luttre 2025",null,null,66303,"2023-03-13","Minor","5,6"]
[null,"Infrabel","66697","Lille - Charleroi",">","Y.SOIGNIES","SOIGNIES",2024,2024,47,47,"2024-11-24",45280.520833333336,"2024-11-24",45280.645833333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B",null,null,66697,"2023-03-07","Minor","5,6"]
[null,"Infrabel","72386","Lille - ZeeBrugge","< >","ZEDELGEM-ROOSTER E/G","ROESELARE",2024,2024,47,47,"2024-11-24",45280.069444444445,"2024-11-24",45280.1875,"1d, 02:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"IDS ETCS1-LS L66 Brugge - Roeselare - moet op zelfde datum als IDS L50A\r\nZONDER IMPACT\r\nstart om 01:40 door omlieiding treinen van L50A",null,null,72386,"2023-10-26","Minor",{"$error":"#N/A"}]
[null,"Infrabel","55571","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,48,48,"2024-11-25",45280.958333333336,"2024-11-30",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des Tabliers métalliques  + 5chapes \r\nFinitions\r\nUPM 444751",null,null,55571,"2023-01-18","Minor","1,2,3,4,5"]
[null,"Infrabel","50599","Namur - Antwerpen",">","AUVELAIS","MOUSTIER-GARAGE",2024,2024,48,48,"2024-11-25",45280.979166666664,"2024-11-29",45280.208333333336,"4d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie",null,null,50599,"2022-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","58348","Namur - Antwerpen","< >","MUIZEN-ROOSTER T","LEUVEN",2024,2024,48,48,"2024-11-25",45280.972222222219,"2024-11-29",45280.166666666664,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"railvernieuwing (nodig wegens veel railfouten)\r\n+\r\nherelectrificatie colt 60291",null,null,58348,"2023-04-26","Minor","1,2,3,4,5"]
[null,"Infrabel","61065","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,48,48,"2024-11-25",45280.989583333336,"2024-11-29",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service",null,null,61065,"2023-03-20","Minor","1,2,3,4,5"]
[null,"Infrabel","60666","Namur - Antwerpen",">","LA ROCHE(BRABANT)","TILLY",2024,2024,48,48,"2024-11-25",45280.354166666664,"2024-11-25",45280.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2024: L140 Partie 3",null,null,60666,"2023-02-06","Minor","1,2,3,4,5"]
[null,"Infrabel","64707","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2024,2024,48,48,"2024-11-26",45280.020833333336,"2024-11-30",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,64707,"2023-01-25","Minor","1,2,3,4,5"]
[null,"Infrabel","60674","Namur - Antwerpen",">","TILLY","FLEURUS",2024,2024,48,48,"2024-11-26",45280.354166666664,"2024-11-26",45280.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2024: L140 Partie 4",null,null,60674,"2023-02-06","Minor","1,2,3,4,5"]
[null,"Infrabel","60682","Namur - Antwerpen",">","CHARLEROI-OUEST","Y.NORD",2024,2024,48,48,"2024-11-27",45280.541666666664,"2024-11-27",45280.625,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2024: L140 Partie 7",null,null,60682,"2023-02-06","Minor","1,2,3,4,5"]
[null,"Infrabel","67162","Athus - Meuse",">","BEAURAING","HOUYET",2024,2024,48,48,"2024-11-27",45280.388888888891,"2024-11-27",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,67162,"2023-04-08","Minor","1,2,3,4,5"]
[null,"Infrabel","65393","Namur - Antwerpen",">","NAMUR","RHISNES",2024,2024,48,48,"2024-11-28",45280.9375,"2024-11-29",45280.229166666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 4\r\nPériodicité toutes les 4 semaines en alternance avec la zone 9\r\nzone 4 : 3 fois sur l'année\r\nzone 9 : 9 fois sur l'année",null,null,65393,"2023-02-08","Minor","1,2,3,4,5"]
[null,"Infrabel","47814","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,48,49,"2024-11-29",45280.958333333336,"2024-12-02",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement ballast par train C75 (phase 3 : révision VB).\r\nUPM: 463038",null,null,47814,"2023-04-13","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","63448","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2024,2024,48,48,"2024-11-29",45280.375,"2024-11-29",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63448,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","58789","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,48,49,"2024-11-30",45280.020833333336,"2024-12-02",45280.1875,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)",null,null,58789,"2022-09-02","Medium","5,6"]
[null,"Infrabel","68838","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2024,2024,48,48,"2024-11-30",45280.3125,"2024-11-30",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY (à répéter toutes les 4 semaines le samedi)",null,null,68838,"2023-05-08","Minor","5,6"]
[null,"Infrabel","67703","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,48,48,"2024-11-30",45280.375,"2024-11-30",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B",null,null,67703,"2023-04-08","Minor","5,6"]
[null,"Infrabel","58668","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-LUCHTBAL",2024,2024,48,48,"2024-12-01",45280.25,"2024-12-01",45280.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"304 statiestraat , tussen Y laarsebeek en Y driehoekstraat",null,null,58668,"2023-11-08","Minor","5,6"]
[null,"Infrabel","67704","Athus - Meuse",">","HALANZY","SIGNEULX",2024,2024,48,48,"2024-12-01",45280.375,"2024-12-01",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie A",null,null,67704,"2023-04-08","Minor","5,6"]
[null,"Infrabel","61965","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2024,2024,49,49,"2024-12-02",45280.986111111109,"2024-12-07",45280.222222222219,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FBMZ_16 en FBMZ_17 volgens onderhoudskalender Area CE\r\n\r\nL96 Spoor A tussen perron FBMZ en Y Ruisbroek\r\nnaastliggend spoor (Bypass)",null,null,61965,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","61066","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,49,49,"2024-12-02",45280.989583333336,"2024-12-06",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service",null,null,61066,"2023-03-20","Minor","1,2,3,4,5"]
[null,"Infrabel","55973","Lille - Charleroi","< >","Y.JURBISE","MONS",2024,2024,49,49,"2024-12-02",45280.947916666664,"2024-12-07",45280.173611111109,"5d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.5.53 en P3",null,null,55973,"2023-04-17","Minor","1,2,3,4,5"]
[null,"Infrabel","65950","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2024,2024,49,49,"2024-12-02",45280.409722222219,"2024-12-02",45280.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie ETCS / maintenance",null,null,65950,"2023-02-21","Minor","1,2,3,4,5"]
[null,"Infrabel","67816","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2024,2024,49,49,"2024-12-04",45280.333333333336,"2024-12-04",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11",null,null,67816,"2023-04-17","Minor","1,2,3,4,5"]
[null,"Infrabel","65541","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2024,2024,49,49,"2024-12-04",45280.375,"2024-12-04",45280.645833333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Schouwen lopend spoor",null,null,65541,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","66023","Athus - Meuse",">","YVOIR","LUSTIN",2024,2024,49,49,"2024-12-04",45280.375,"2024-12-04",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,66023,"2023-12-18","Minor","1,2,3,4,5"]
[null,"Infrabel","67805","Lille - Charleroi",">","LUTTRE","MARCHIENNE-AU-PONT",2024,2024,49,49,"2024-12-05",45280.333333333336,"2024-12-05",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J10",null,null,67805,"2023-04-13","Minor","1,2,3,4,5"]
[null,"Infrabel","47815","Athus - Meuse",">","BEAURAING","VONECHE",2024,2024,49,50,"2024-12-06",45280.958333333336,"2024-12-09",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement ballast par train C75 (phase 4 : révision VA).\r\nUPM: 463041",null,null,47815,"2023-04-13","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","65975","Athus - Meuse",">","Y.NEFFE","DINANT",2024,2024,49,49,"2024-12-06",45280.333333333336,"2024-12-06",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,65975,"2023-02-23","Minor","1,2,3,4,5"]
[null,"Infrabel","67422","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2024,2024,49,49,"2024-12-06",45280.375,"2024-12-06",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite voie B\r\nEntretien / maintenance voie B",null,null,67422,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","49177","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2024,2024,49,49,"2024-12-07",45280.333333333336,"2024-12-07",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie A + maintenance infrastructure + contrôles\r\nUPM: 461956",null,null,49177,"2023-11-17","Minor","5,6"]
[null,"Infrabel","68946","Namur - Antwerpen","< >","Y.HEIKE","MUIZEN-ROOSTER T",2024,2024,49,50,"2024-12-07",45280.041666666664,"2024-12-09",45280.1875,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Masterplan Mechelen\r\n\r\nConfiguratie Rooster M+N\r\nCR 2024-072 \r\n\r\nHerzieningsweekend na werken lange TLO tijdens herfstvakantie 2024\r\n\r\nUPM 468161",null,null,68946,"2023-09-28","Medium","5,6"]
[null,"Infrabel","67424","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2024,2024,49,49,"2024-12-07",45280.375,"2024-12-07",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien / maintenance voie A\r\nVisite voie A",null,null,67424,"2023-04-07","Minor","5,6"]
[null,"Infrabel","50711","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2024,2024,49,50,"2024-12-08",45280.027777777781,"2024-12-09",45280.1875,"2d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien voie Massification Arr 44",null,null,50711,"2022-12-16","Minor","5,6"]
[null,"Infrabel","73470","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","NAMUR",2024,2024,49,49,"2024-12-08",45280.020833333336,"2024-12-08",45280.229166666664,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"IDS ETCS L2-IL_SE_P018_P019_L125_Namur-Liège_ETCS_RW_LFA\r\nmeewerken niet mogelijk",null,null,73470,"2023-12-14","Minor","5,6"]
[null,"Infrabel","66057","Athus - Meuse",">","LUSTIN","JAMBES",2024,2024,49,49,"2024-12-08",45280.385416666664,"2024-12-08",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,66057,"2023-03-14","Minor","5,6"]
[null,"Infrabel","67489","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2024,2024,49,49,"2024-12-08",45280.354166666664,"2024-12-08",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,67489,"2023-03-29","Minor","5,6"]
[null,"Infrabel","62600","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.ARENDSTRAAT",2024,2024,50,50,"2024-12-09",45280.979166666664,"2024-12-13",45280.1875,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"TOS 2222: Gekoppelde DOES: L27 sp A / L59/1 sp B Onderhoud wissels Y Noord Berchem",null,null,62600,"2023-06-07","Minor","1,2,3,4,5"]
[null,"Infrabel","61067","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,50,50,"2024-12-09",45280.989583333336,"2024-12-13",45280.197916666664,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service",null,null,61067,"2023-03-20","Minor","1,2,3,4,5"]
[null,"Infrabel","66072","Athus - Meuse",">","NAMUR","JAMBES",2024,2024,50,50,"2024-12-09",45280.388888888891,"2024-12-09",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,66072,"2023-03-14","Minor","1,2,3,4,5"]
[null,"Infrabel","50587","Namur - Antwerpen",">","Y.FLAWINNE","MOUSTIER-GARAGE",2024,2024,50,50,"2024-12-10",45280.979166666664,"2024-12-11",45280.208333333336,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Savu Entretien de voie",null,null,50587,"2022-12-02","Minor","1,2,3,4,5"]
[null,"Infrabel","67709","Athus - Meuse",">","STRAIMONT","BERTRIX",2024,2024,50,50,"2024-12-10",45280.375,"2024-12-10",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,67709,"2023-04-08","Minor","1,2,3,4,5"]
[null,"Infrabel","66864","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","Y.VAL-SAINT-LAMBERT",2024,2024,50,50,"2024-12-11",45280.958333333336,"2024-12-12",45280.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Z19.41 - Maintenance P3",null,null,66864,"2023-03-10","Minor","1,2,3,4,5"]
[null,"Infrabel","67167","Athus - Meuse",">","PALISEUL","BERTRIX",2024,2024,50,50,"2024-12-12",45280.333333333336,"2024-12-12",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie\r\nVA",null,null,67167,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","71325","Athus - Meuse",">","SIGNEULX","VIRTON",2024,2024,50,50,"2024-12-13",45280.333333333336,"2024-12-13",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,71325,"2023-12-19","Minor","1,2,3,4,5"]
[null,"Infrabel","61380","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2024,2024,50,50,"2024-12-14",45280.958333333336,"2024-12-15",45280.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Z3 pour implantation ART pour mauvais état de la L140 VA entre GLR-MCM",null,null,61380,"2023-02-02","Minor","5,6"]
[null,"Infrabel","47143","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2024,2024,51,51,"2024-12-16",45280.958333333336,"2024-12-20",45280.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\npose poteaux",null,null,47143,"2023-02-24","Minor","1,2,3,4,5"]
[null,"Infrabel","64619","Namur - Antwerpen","< >","EEKLO","GENT-DAMPOORT",2024,2024,51,51,"2024-12-16",45280.958333333336,"2024-12-21",45280.1875,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nFGDM niet IN.",null,null,64619,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","64254","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2024,2024,51,51,"2024-12-16",45280.979166666664,"2024-12-20",45280.1875,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters\r\nTLO L50E FGSP-Y West Driehoek Ledeberg\r\nDOES L50 FGSP-Y West Driehoek Ledeberg\r\nPerron I tem VI (geen continue buiten dienst stellingen meer op de sporen VII tem XII)\r\n\r\n(alternatief stappenplan)",null,null,64254,"2023-03-15","Minor","1,2,3,4,5"]
[null,"Infrabel","61068","Namur - Antwerpen",">","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2024,2024,51,51,"2024-12-16",45280.989583333336,"2024-12-21",45280.197916666664,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"RER\r\nmise hors service de 3 voies sur les 4 en service",null,null,61068,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","63387","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2024,2024,51,51,"2024-12-17",45280.375,"2024-12-17",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63387,"2023-01-05","Minor","1,2,3,4,5"]
[null,"Infrabel","63412","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2024,2024,51,51,"2024-12-18",45280.375,"2024-12-18",45280.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Schouwen, smeren van spoortoestellen en onderhoudswerken lopend spoor en spoortoestellen",null,null,63412,"2023-01-02","Minor","1,2,3,4,5"]
[null,"Infrabel","70812","Erquelinnes - Montzen",">","JAVA","ANDENNE",2024,2024,51,51,"2024-12-19",45280.5625,"2024-12-19",45280.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70812,"2023-11-03","Minor","1,2,3,4,5"]
[null,"Infrabel","67159","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2024,2024,51,51,"2024-12-19",45280.388888888891,"2024-12-19",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,67159,"2023-04-07","Minor","1,2,3,4,5"]
[null,"Infrabel","71327","Athus - Meuse",">","SIGNEULX","HALANZY",2024,2024,51,51,"2024-12-20",45280.333333333336,"2024-12-20",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A ou B",null,null,71327,"2023-11-03","Minor","1,2,3,4,5"]
[null,"Infrabel","47207","Athus - Meuse","< >","GEDINNE","BERTRIX",2024,2024,51,52,"2024-12-21",45280.958333333336,"2024-12-23",45280.1875,"1d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Electrification 2 x 25 kV : Florenville - Gedinne (L165 + L166) : passage feeder négatif dans la gare de Bertrix\r\nUPM : 466041",null,null,47207,"2023-05-04","Medium","5,6"]
[null,"Infrabel","48875","Namur - Antwerpen",">","WAVRE","OTTIGNIES",2024,2024,51,51,"2024-12-21",45280.333333333336,"2024-12-21",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes+ maintenances infrastructure et contrôles\r\nUPM : 465261",null,null,48875,"2023-04-27","Minor","5,6"]
[null,"Infrabel","68839","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2024,2024,51,51,"2024-12-21",45280.3125,"2024-12-21",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY (à répéter toutes les 4 semaines le samedi)",null,null,68839,"2023-11-03","Minor","5,6"]
[null,"Infrabel","48884","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2024,2024,51,51,"2024-12-22",45280.333333333336,"2024-12-22",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites des postes - maintenances diverses et révisions\r\nUPM : 465398",null,null,48884,"2023-04-27","Minor","5,6"]
[null,"Infrabel","67148","Athus - Meuse",">","HOUYET","BEAURAING",2024,2024,52,52,"2024-12-23",45280.388888888891,"2024-12-23",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,67148,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","67163","Athus - Meuse",">","VONECHE","GEDINNE",2024,2024,52,52,"2024-12-26",45280.333333333336,"2024-12-26",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien",null,null,67163,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","69276","Erquelinnes - Montzen",">","BRESSOUX","FROIDMONT",2024,2024,1,1,"2024-12-30",45280.333333333336,"2024-12-30",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,69276,"2023-11-07","Minor","1,2,3,4,5"]
[null,"Infrabel","70418","Erquelinnes - Montzen",">","BRESSOUX","VISE",2024,2024,1,1,"2024-12-31",45280.333333333336,"2024-12-31",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie et intervention avec S460 sur la voie contiguë + ATW",null,null,70418,"2023-11-07","Minor","1,2,3,4,5"]
[null,"Infrabel","71326","Athus - Meuse",">","SIGNEULX","VIRTON",2025,2025,1,1,"2025-01-03",45280.333333333336,"2025-01-03",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,71326,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","67780","Lille - Charleroi",">","BRAINE-LE-COMTE","ECAUSSINNES",2025,2025,1,1,"2025-01-04",45280.333333333336,"2025-01-04",45280.583333333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique AI52 + AI53",null,null,67780,"2023-04-12","Minor","5,6"]
[null,"Infrabel","70005","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2025,2025,1,1,"2025-01-05",45280.333333333336,"2025-01-05",45280.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144-130/1",null,null,70005,"2023-10-12","Minor","5,6"]
[null,"Infrabel","69592","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","ANTWERPEN-NOORD-INRIT C1",2025,2025,2,10,"2025-01-06",45280,"2025-03-03",45280.166666666664,"56d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Bundel C1-C2-N vernieuwen van spoortoestellen\r\nFasering: zie extra document op Teams (projecten)\r\nFase 3: Bundel C2-N",null,null,69592,"2023-12-19","Major","1,2,3,4,5,6,7"]
[null,"Infrabel","73960","Namur - Antwerpen",">","Y.OOST DRIEHOEK LEDEBERG","Y.WEST DRIEHOEK LEDEBERG",2025,2025,2,2,"2025-01-07",45280.027777777781,"2025-01-11",45280.194444444445,"5d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"reservatie onderhoud \r\nSchets DOES 4\r\nL50E SP B 01XR inbegrepen tot 05O inbegrepen\r\nL58/1 SP B 05O inbegrepen tot 10XO inbegrepen\r\nL58(1) SP A 10XO inbegrepen tot 01XR inbegrepen",null,null,73960,"2023-12-07","Minor","1,2,3,4,5"]
[null,"Infrabel","71432","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,2,2,"2025-01-07",45280.375,"2025-01-07",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,71432,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","71433","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,2,2,"2025-01-08",45280.375,"2025-01-08",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,71433,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","71434","Athus - Meuse",">","YVOIR","DINANT",2025,2025,2,2,"2025-01-09",45280.385416666664,"2025-01-09",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,71434,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","71318","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2025,2025,2,2,"2025-01-11",45280.333333333336,"2025-01-11",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71318,"2023-11-13","Minor","5,6"]
[null,"Infrabel","70023","Namur - Antwerpen",">","OTTIGNIES","BAKENBOS",2025,2025,2,2,"2025-01-11",45280.333333333336,"2025-01-12",45280.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie",null,null,70023,"2023-09-25","Minor","5,6"]
[null,"Infrabel","67117","Namur - Antwerpen",">","AUVELAIS","FLAWINNE",2025,2025,2,2,"2025-01-12",45280.333333333336,"2025-01-12",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130",null,null,67117,"2023-11-29","Minor","5,6"]
[null,"Infrabel","71320","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2025,2025,2,2,"2025-01-12",45280.333333333336,"2025-01-12",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,71320,"2023-11-13","Minor","5,6"]
[null,"Infrabel","59308","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,3,3,"2025-01-13",45280.979166666664,"2025-01-18",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe",null,null,59308,"2023-03-28","Minor","1,2,3,4,5"]
[null,"Infrabel","72701","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","BAKENBOS",2025,2025,3,3,"2025-01-13",45280.986111111109,"2025-01-18",45280.201388888891,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_05 Area CE volgens onderhoudskalender 2025.\r\nBuitendienststelling L161 tussen Bru Luxemburg en Bakenbos voor onderhoudswerken + L161A.",null,null,72701,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","65817","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,3,3,"2025-01-13",45280.923611111109,"2025-01-18",45280.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.51 P3 HKV",null,null,65817,"2023-10-17","Minor","1,2,3,4,5"]
[null,"Infrabel","71339","Athus - Meuse",">","LAVAUX","MARBEHAN",2025,2025,3,3,"2025-01-15",45280.361111111109,"2025-01-15",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,71339,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","71314","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,3,3,"2025-01-16",45280.333333333336,"2025-01-16",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71314,"2023-11-10","Minor","1,2,3,4,5"]
[null,"Infrabel","71331","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,3,3,"2025-01-16",45280.333333333336,"2025-01-16",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71331,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","73097","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,3,3,"2025-01-17",45280.333333333336,"2025-01-17",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73097,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","66509","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,3,4,"2025-01-17",45280.993055555555,"2025-01-20",45280.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification OA + AI44 \r\nAI44: Intervention PN + Entretien divers\r\nOA; Mise au gabarit des pistes Namur Rhisnes parois rocheuses\r\n+ Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles",null,null,66509,"2023-11-29","Medium","5,6"]
[null,"Infrabel","66197","Lille - Charleroi",">","LUTTRE","ROUX",2025,2025,3,3,"2025-01-18",45280.25,"2025-01-19",45280.708333333336,"1d, 11:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance Z05.52 P4",null,null,66197,"2023-05-15","Minor","5,6"]
[null,"Infrabel","71430","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,3,3,"2025-01-18",45280.385416666664,"2025-01-18",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,71430,"2023-11-13","Minor","5,6"]
[null,"Infrabel","59312","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,3,3,"2025-01-19",45280.034722222219,"2025-01-19",45280.21875,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nTLO L 50 tussen Gent Sint Pieters en Y. West Driehoek Le",null,null,59312,"2023-06-28","Minor","5,6"]
[null,"Infrabel","70071","Erquelinnes - Montzen","< >","Y.VAL-BENOIT","Y.RENORY",2025,2025,4,4,"2025-01-20",45280.958333333336,"2025-01-24",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Z21.41 - P3 maintenance AI41",null,null,70071,"2023-11-03","Minor","1,2,3,4,5"]
[null,"Infrabel","59309","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,4,4,"2025-01-20",45280.979166666664,"2025-01-25",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe",null,null,59309,"2023-02-15","Minor","1,2,3,4,5"]
[null,"Infrabel","55902","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2025,2025,4,4,"2025-01-20",45280.965277777781,"2025-01-24",45280.208333333336,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Semaines de nuits de préparations - démolition 85.708\r\n+ Réélectrification L130\r\n+ Maintenance Z15. 51\r\nP3 HKV \r\nTronçon Allongé 6h",null,null,55902,"2023-10-16","Minor","1,2,3,4,5"]
[null,"Infrabel","68036","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,4,4,"2025-01-20",45280.034722222219,"2025-01-20",45280.201388888891,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68036,"2023-04-25","Minor","5,6"]
[null,"Infrabel","71704","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,4,4,"2025-01-20",45280.319444444445,"2025-01-20",45280.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance",null,null,71704,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","71143","Athus - Meuse",">","STRAIMONT","BERTRIX",2025,2025,4,4,"2025-01-21",45280.375,"2025-01-21",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,71143,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","66628","Athus - Meuse","< >","STOCKEM-SUD","ARLON",2025,2025,4,5,"2025-01-24",45280.979166666664,"2025-01-27",45280.1875,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Entretien en profondeur de l'ouvrage et remplacement des gardes-corps",null,null,66628,"2023-08-25","Medium","5,6"]
[null,"Infrabel","66512","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2025,2025,4,5,"2025-01-25",45280.25,"2025-01-27",45280.25,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Intervention PN + Entretien divers\r\n+ Remplacement CV(50Hz) par CV Jade entre Jemeppe-Sur-Sambre Sg G-Q.30 et L130/1 Sg NY-Q.30",null,null,66512,"2023-06-15","Medium","5,6"]
[null,"Infrabel","68894","Namur - Antwerpen","< >","Y.SCHIJN","ANTWERPEN-D.S.-RHODESIE",2025,2025,4,4,"2025-01-26",45280.25,"2025-01-26",45280.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Slijpwerken met SPENO op spoor A \r\n(planning per mail gekregen op 28/04/2023 van De Kempeneer David)",null,null,68894,"2023-05-26","Medium","5,6"]
[null,"Infrabel","63156","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,5,5,"2025-01-27",45280.958333333336,"2025-02-01",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,63156,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","71753","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,5,5,"2025-01-27",45280.333333333336,"2025-01-27",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles",null,null,71753,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","55905","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2025,2025,5,5,"2025-01-27",45280.951388888891,"2025-01-31",45280.201388888891,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Semaines de nuits de préparations - démolition 85.708\r\n+ Réélectrification L130\r\n+ Maintenance Z15. 51\r\nP3 HKV \r\nTronçon Allongé 6h",null,null,55905,"2023-08-31","Minor","1,2,3,4,5"]
[null,"Infrabel","68710","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2025,2025,5,5,"2025-01-27",45280.965277777781,"2025-01-31",45280.197916666664,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons\r\nZ9.41 + L.125/1\r\n+ voies 834 et 835 de Flémalle-Haute",null,null,68710,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","67817","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2025,2025,5,5,"2025-01-29",45280.333333333336,"2025-01-29",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11",null,null,67817,"2023-04-12","Minor","1,2,3,4,5"]
[null,"Infrabel","71187","Erquelinnes - Montzen",">","JAVA","STATTE",2025,2025,5,5,"2025-01-29",45280.354166666664,"2025-01-29",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71187,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","65049","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2025,2025,5,6,"2025-01-31",45280.958333333336,"2025-02-03",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Démolition PS km 85.708\r\n+ Maintenance Z15. 51 P4+",null,null,65049,"2023-08-31","Medium","5,6"]
[null,"Infrabel","70820","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2025,2025,5,5,"2025-01-31",45280.375,"2025-01-31",45280.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70820,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","69500","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.OOST BERCHEM",2025,2025,5,6,"2025-02-01",45280.979166666664,"2025-02-03",45280.166666666664,"2d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug",null,null,69500,"2023-08-29","Minor","5,6"]
[null,"Infrabel","72252","Namur - Antwerpen",">","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,5,5,"2025-02-01",45280.25,"2025-02-01",45280.979166666664,"2d, 17:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug  L15 km 6.027 BX L15 en L27A\r\n\r\nL27A Y Liersesteenweg - Y Oost Berchem: Zaterdag DOES + zondagTLO\r\n\r\nalternatief voor geweigerde L15+L27A",null,null,72252,"2023-10-19","Minor","5,6"]
[null,"Infrabel","70821","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2025,2025,5,5,"2025-02-01",45280.354166666664,"2025-02-01",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70821,"2023-10-26","Minor","5,6"]
[null,"Infrabel","66483","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,5,5,"2025-02-02",45280.333333333336,"2025-02-02",45280.659722222219,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie B Ottignies - Gembloux (extension Rhisnes SAS)",null,null,66483,"2023-06-27","Minor","5,6"]
[null,"Infrabel","59314","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,5,5,"2025-02-02",45280.034722222219,"2025-02-02",45280.21875,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nTLO L 50 tussen Gent Sint Pieters en Y. West Driehoek Le",null,null,59314,"2023-06-28","Minor","5,6"]
[null,"Infrabel","70822","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2025,2025,5,5,"2025-02-02",45280.354166666664,"2025-02-02",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70822,"2023-10-26","Minor","5,6"]
[null,"Infrabel","54905","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2025,2025,6,6,"2025-02-03",45280.958333333336,"2025-02-08",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10.51   P3 HKV\r\nSans voie de protection",null,null,54905,"2023-10-16","Minor","1,2,3,4,5"]
[null,"Infrabel","70416","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2025,2025,6,6,"2025-02-03",45280.333333333336,"2025-02-03",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,70416,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","71909","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2025,2025,6,6,"2025-02-03",45280.989583333336,"2025-02-08",45280.194444444445,"5d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nimpact HKV",null,null,71909,"2023-11-30","Minor","1,2,3,4,5"]
[null,"Infrabel","68038","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,6,6,"2025-02-03",45280.034722222219,"2025-02-03",45280.201388888891,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68038,"2023-04-25","Minor","5,6"]
[null,"Infrabel","70419","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,6,6,"2025-02-04",45280.395833333336,"2025-02-04",45280.611111111109,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie et intervention avec S460 sur la voie contiguë + ATW",null,null,70419,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","73378","Athus - Meuse",">","YVOIR","DINANT",2025,2025,6,6,"2025-02-06",45280.385416666664,"2025-02-06",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73378,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","56487","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,6,7,"2025-02-07",45280.958333333336,"2025-02-10",45280.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation\r\n+ Maintenance Z2. 51  P4+",null,null,56487,"2023-12-19","Medium","5,6"]
[null,"Infrabel","64982","Namur - Antwerpen","< >","TILLY-GARAGE","CHARLEROI-OUEST",2025,2025,6,7,"2025-02-07",45280.979166666664,"2025-02-10",45280.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement CV en gare de Fleurus",null,null,64982,"2023-09-25","Medium","5,6"]
[null,"Infrabel","69346","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,6,6,"2025-02-09",45280.020833333336,"2025-02-09",45280.25,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossen rails vernieuwingswerken april/mei 2025",null,null,69346,"2023-07-14","Minor","5,6"]
[null,"Infrabel","59219","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,7,7,"2025-02-10",45280.979166666664,"2025-02-15",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nDoes Spoor A L 50 tussen Gent Sint Pieters en Y. West Dr",null,null,59219,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","55903","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2025,2025,7,7,"2025-02-10",45280.951388888891,"2025-02-15",45280.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Démolition 85.708 - Préparations\r\n+ Réélectrification L130\r\n+ Maintenance Z15. 51 P3 HKV \r\n+Placement Jic pour D. Pecceu",null,null,55903,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","65792","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2025,2025,7,7,"2025-02-10",45280.9375,"2025-02-15",45280.208333333336,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z8.51   P3",null,null,65792,"2023-09-26","Minor","1,2,3,4,5"]
[null,"Infrabel","73391","Athus - Meuse",">","DINANT","Y.NEFFE",2025,2025,7,7,"2025-02-10",45280.34375,"2025-02-10",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites VA",null,null,73391,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","73058","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,7,7,"2025-02-13",45280.333333333336,"2025-02-13",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73058,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","59516","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,7,8,"2025-02-14",45280.958333333336,"2025-02-17",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des traverses P93",null,null,59516,"2023-10-17","Medium","5,6"]
[null,"Infrabel","73059","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,7,7,"2025-02-14",45280.333333333336,"2025-02-14",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73059,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","72543","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,7,7,"2025-02-15",45280.3125,"2025-02-15",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72543,"2023-11-03","Minor","5,6"]
[null,"Infrabel","67465","Lille - Charleroi","< >","GHLIN","MONS",2025,2025,7,7,"2025-02-15",45280.993055555555,"2025-02-16",45280.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim",null,null,67465,"2023-10-23","Minor","5,6"]
[null,"Infrabel","68925","Lille - Antwerpen","< >","BEERVELDE","GENT-DAMPOORT",2025,2025,7,7,"2025-02-16",45280.03125,"2025-02-16",45280.215277777781,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"In dienst stelling ETCS\r\nMeewerken niet mogelijk\r\nL59 Gent Dampoort - Lokeren (v) 00.45 - 05.30\r\nL58 - Eeklo Niet in tot Y Oost Driehoek Ledeberg IN - 00.45 tot 05.50\r\nL58/1 - Y Noord Driehoek ledeberg IN tot Y West Driehoek Ledeberg IN - 00.45 tot 05.3",null,null,68925,"2023-07-03","Minor","5,6"]
[null,"Infrabel","72556","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,7,7,"2025-02-16",45280.3125,"2025-02-16",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72556,"2023-11-03","Minor","5,6"]
[null,"Infrabel","71754","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,8,8,"2025-02-17",45280.333333333336,"2025-02-17",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles",null,null,71754,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","66574","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2025,2025,8,8,"2025-02-17",45280.951388888891,"2025-02-22",45280.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.51 \r\nP3 HKV",null,null,66574,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","46317","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2025,2025,8,20,"2025-02-17",45280.25,"2025-05-18",45280.666666666664,"90d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Mise au gabarit des pistes de circulation\r\nSécurisation des parois rocheuses \r\nRenouvellement PI BK 13808",null,null,46317,"2023-12-19","High","1,2,3,4,5,6,7"]
[null,"Infrabel","68708","Erquelinnes - Montzen","< >","SERAING","FLEMALLE-HAUTE",2025,2025,8,8,"2025-02-18",45280.958333333336,"2025-02-22",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons",null,null,68708,"2023-11-03","Minor","1,2,3,4,5"]
[null,"Infrabel","73360","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,8,8,"2025-02-18",45280.375,"2025-02-18",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)\r\nRQ333:@Elise ok avec SAVU Gendron- Houyet (< 30km!)?",null,null,73360,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","73361","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,8,8,"2025-02-19",45280.375,"2025-02-19",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)\r\nRQ333:@Elise ok avec SAVU Gendron- Houyet (< 30km!)?",null,null,73361,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","72746","Athus - Meuse",">","HABAY","STOCKEM-NORD",2025,2025,8,8,"2025-02-19",45280.375,"2025-02-19",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72746,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","70024","Namur - Antwerpen",">","OTTIGNIES","BAKENBOS",2025,2025,8,8,"2025-02-22",45280.333333333336,"2025-02-23",45280.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie",null,null,70024,"2023-10-05","Minor","5,6"]
[null,"Infrabel","68396","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,8,9,"2025-02-22",45280.000694444447,"2025-02-24",45280.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing BVL.\r\nWeekend 7+8 ter  vervanging van geannuleerde lange TLO (COLT 57997)",null,null,68396,"2023-08-29","Medium","5,6"]
[null,"Infrabel","71450","Athus - Meuse",">","LUSTIN","JAMBES",2025,2025,8,8,"2025-02-23",45280.385416666664,"2025-02-23",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,71450,"2023-11-13","Minor","5,6"]
[null,"Infrabel","68051","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET",2025,2025,9,9,"2025-02-24",45280.965277777781,"2025-03-01",45280.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130",null,null,68051,"2023-04-15","Minor","1,2,3,4,5"]
[null,"Infrabel","71661","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2025,2025,9,9,"2025-02-24",45280.947916666664,"2025-03-01",45280.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 05.32\r\nL58 Eeklo inbegrepen tot Gent Dampoort NIET inbegrepen",null,null,71661,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","67022","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,9,9,"2025-02-24",45280.923611111109,"2025-02-28",45280.194444444445,"4d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de rails \r\n+ Travaux OA \r\n+ Chantier SPW PS 65.090",null,null,67022,"2023-08-31","Minor","1,2,3,4,5"]
[null,"Infrabel","72928","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2025,2025,9,9,"2025-02-25",45280.333333333336,"2025-02-25",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,72928,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","71311","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,9,9,"2025-02-26",45280.333333333336,"2025-02-26",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71311,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","55769","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2025,2025,9,9,"2025-02-27",45280.333333333336,"2025-02-28",45280.958333333336,"2d, 15:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre - travaux préparatoires",null,null,55769,"2023-03-17","Minor","1,2,3,4,5"]
[null,"Infrabel","67454","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,9,9,"2025-02-27",45280.395833333336,"2025-02-27",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nVisite diagnostique\r\nMise HS en P2",null,null,67454,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","67553","Lille - Antwerpen",">","KORTRIJK","KORTRIJK-RINGLAAN",2025,2025,9,10,"2025-02-28",45280.979166666664,"2025-03-03",45280.166666666664,"2d, 04:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwen lopend spoor van Bundel C naar Y Bethune - \r\nbundel C Buiten dienst\r\n+\r\nOnderhoud\r\n\r\nBundels Kortrijk bereikbaar kant Moeskroen\r\nBundel C niet toegankelijk",null,null,67553,"2023-12-15","Minor","5,6"]
[null,"Infrabel","69067","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2025,2025,9,9,"2025-03-01",45280.333333333336,"2025-03-01",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130 Flawinne - Moustier VA/VB",null,null,69067,"2023-11-29","Minor","5,6"]
[null,"Infrabel","66624","Athus - Meuse","< >","BOIS D'AUSSE","BRAIBANT",2025,2025,9,10,"2025-03-01",45280.020833333336,"2025-03-03",45280.180555555555,"2d, 03:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"PI 82.155, 84.933, 81.040, \r\nPS 81.795, \r\nPI 79,508\r\nPS 88,293\r\nTravaux profonds sur différents ouvrages  + chapes pour pont 79,965 et 81,040",null,null,66624,"2023-09-21","Medium","5,6"]
[null,"Infrabel","54889","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2025,2025,9,9,"2025-03-01",45280.986111111109,"2025-03-02",45280.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+ Visites voie B Flawine/Auvelais",null,null,54889,"2023-11-29","Medium","5,6"]
[null,"Infrabel","72258","Namur - Antwerpen",">","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,9,9,"2025-03-01",45280.25,"2025-03-01",45280.979166666664,"2d, 17:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug  L15 km 6.027 BX L15 en L27A\r\n\r\nL27A Y Liersesteenweg - Y Oost Berchem: Zaterdag DOES + zondagTLO\r\n\r\nalternatief voor geweigerde L15+L27A",null,null,72258,"2023-10-19","Minor","5,6"]
[null,"Infrabel","74099","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2025,2025,9,9,"2025-03-01",45280.996527777781,"2025-03-02",45280.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B",null,null,74099,"2023-12-13","Minor","5,6"]
[null,"Infrabel","68754","Namur - Antwerpen","< >","FRONT. FLANDRE-WALLONIE L139","LEUVEN",2025,2025,9,10,"2025-03-01",45280.003472222219,"2025-03-03",45280.208333333336,"2d, 04:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Buitenwerken, BDS, meewerken mogelijk\r\nETCS Baanvak Heverlee – St-Joris-Weert (doorsteken e.d.) + grid St-Joris-Weert\r\nverspreid over jaar (niet in januari)",null,null,68754,"2023-08-30","Medium","5,6"]
[null,"Infrabel","71351","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,10,10,"2025-03-03",45280.979166666664,"2025-03-08",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe",null,null,71351,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","66535","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","LAUWE",2025,2025,10,10,"2025-03-03",45280.951388888891,"2025-03-08",45280.236111111109,"5d, 06:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z3.54\r\n+ Maintenance Z8.54",null,null,66535,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","67036","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,10,10,"2025-03-03",45280.965277777781,"2025-03-08",45280.243055555555,"5d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose poteaux caténaire sur L144. (entre L130 et PN10)",null,null,67036,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","73123","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2025,2025,10,10,"2025-03-03",45280.385416666664,"2025-03-03",45280.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,73123,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","71705","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,10,10,"2025-03-03",45280.319444444445,"2025-03-03",45280.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance",null,null,71705,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","72904","Athus - Meuse",">","STRAIMONT","BERTRIX",2025,2025,10,10,"2025-03-04",45280.375,"2025-03-04",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,72904,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","71317","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2025,2025,10,10,"2025-03-07",45280.333333333336,"2025-03-07",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,71317,"2023-11-24","Minor","1,2,3,4,5"]
[null,"Infrabel","68305","Lille - Antwerpen",">","KORTRIJK","KORTRIJK-RINGLAAN",2025,2025,10,11,"2025-03-07",45280.979166666664,"2025-03-10",45280.166666666664,"2d, 04:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwen lopend spoor van Bundel C naar Y Bethune - \r\nbundel C Buiten dienst\r\n+\r\nOnderhoud\r\n\r\nBundels Kortrijk bereikbaar kant Moeskroen\r\nBundel C niet toegankelijk",null,null,68305,"2023-12-15","Minor","5,6"]
[null,"Infrabel","64218","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,10,11,"2025-03-08",45280.965277777781,"2025-03-10",45280.215277777781,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses",null,null,64218,"2023-06-15","Minor","5,6"]
[null,"Infrabel","68755","Namur - Antwerpen","< >","FRONT. FLANDRE-WALLONIE L139","LEUVEN",2025,2025,10,11,"2025-03-08",45280.003472222219,"2025-03-10",45280.208333333336,"2d, 04:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Buitenwerken, BDS, meewerken mogelijk\r\nETCS Baanvak Heverlee – St-Joris-Weert (doorsteken e.d.) + grid St-Joris-Weert",null,null,68755,"2023-08-30","Medium","5,6"]
[null,"Infrabel","68796","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,10,10,"2025-03-09",45280.333333333336,"2025-03-09",45280.659722222219,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie B Ottignies - Gembloux (extension Rhisnes SAS)",null,null,68796,"2023-06-27","Minor","5,6"]
[null,"Infrabel","67038","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,11,11,"2025-03-10",45280.958333333336,"2025-03-15",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose de console L144-L130",null,null,67038,"2023-10-12","Minor","1,2,3,4,5"]
[null,"Infrabel","72360","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2025,2025,11,11,"2025-03-10",45280.965277777781,"2025-03-15",45280.215277777781,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien massification\r\nMaintenance Z2.44",null,null,72360,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","56117","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,11,11,"2025-03-10",45280.375,"2025-03-14",45280.645833333336,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement de Luttre - phase 2025\r\nPréparations caténaires, IX-E.20 > quai IV\r\n+ révision à mi-vie caténaire L117, IX-E.20 > T-H.11",null,null,56117,"2023-04-06","Minor","1,2,3,4,5"]
[null,"Infrabel","53511","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.ECAUSSINNES",2025,2025,11,11,"2025-03-11",45280.020833333336,"2025-03-15",45280.229166666664,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.3 courte.53 en P3 HKM",null,null,53511,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","70813","Erquelinnes - Montzen",">","JAVA","STATTE",2025,2025,11,11,"2025-03-12",45280.354166666664,"2025-03-12",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70813,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","53988","Athus - Meuse","< >","HAVERSIN","CINEY",2025,2025,11,12,"2025-03-14",45280.927083333336,"2025-03-17",45280.208333333336,"2d, 06:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3:\r\npose super structure PS de Leignon",null,null,53988,"2023-05-17","Medium","5,6"]
[null,"Infrabel","64984","Namur - Antwerpen","< >","TILLY-GARAGE","CHARLEROI-OUEST",2025,2025,11,12,"2025-03-15",45280.208333333336,"2025-03-17",45280.166666666664,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement CV en gare de Fleurus",null,null,64984,"2023-11-22","Medium","5,6"]
[null,"Infrabel","72546","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,11,11,"2025-03-15",45280.3125,"2025-03-15",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72546,"2023-11-03","Minor","5,6"]
[null,"Infrabel","72557","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,11,11,"2025-03-16",45280.3125,"2025-03-16",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72557,"2023-11-03","Minor","5,6"]
[null,"Infrabel","71112","Namur - Antwerpen","< >","NAMUR","RONET",2025,2025,11,11,"2025-03-16",45280.003472222219,"2025-03-16",45280.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur (ZONE 6)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,71112,"2023-11-06","Minor","5,6"]
[null,"Infrabel","70190","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,12,12,"2025-03-17",45280.958333333336,"2025-03-22",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails, attaches...",null,null,70190,"2023-09-19","Minor","1,2,3,4,5"]
[null,"Infrabel","72798","Lille - Charleroi",">","BRUXELLES-MIDI","BRUXELLES-MIDI",2025,2025,12,12,"2025-03-17",45280.979166666664,"2025-03-22",45280.229166666664,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoudswerken volgens onderhoudskalender Area Ce\r\nOnderhoudszone FBMZ_05, perronsporen 16+17 FBMZ",null,null,72798,"2023-11-27","Minor","1,2,3,4,5"]
[null,"Infrabel","68039","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,12,12,"2025-03-17",45280.034722222219,"2025-03-17",45280.201388888891,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68039,"2023-04-14","Minor","5,6"]
[null,"Infrabel","67025","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,12,13,"2025-03-21",45280.958333333336,"2025-03-24",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des traverses P93\r\nWE Bourrage et finitions\r\n+ Renouvellement CV",null,null,67025,"2023-10-17","Medium","5,6"]
[null,"Infrabel","64220","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,12,13,"2025-03-22",45280.965277777781,"2025-03-24",45280.215277777781,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses",null,null,64220,"2023-06-15","Minor","5,6"]
[null,"Infrabel","64934","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2025,2025,12,12,"2025-03-23",45280.3125,"2025-03-23",45280.520833333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Noord\r\nBuitendienststellen van de van de volledige overeenkomstige EBP-zone gedurende minimaal 4 uur te bepalen tussen 06.00 uur en 14.00 uur\r\nUpdate EBP release to last version\r\nR-447116",null,null,64934,"2023-01-27","Minor","5,6"]
[null,"Infrabel","68055","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET",2025,2025,13,13,"2025-03-24",45280.965277777781,"2025-03-29",45280.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130",null,null,68055,"2023-04-15","Minor","1,2,3,4,5"]
[null,"Infrabel","67461","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,13,13,"2025-03-27",45280.395833333336,"2025-03-27",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nMise HS en P2",null,null,67461,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","69379","Athus - Meuse","< >","DINANT","Y.NEFFE",2025,2025,13,13,"2025-03-29",45280.958333333336,"2025-03-30",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mise au gabarit des pistes de circulation\r\nSécurisation des parois rocheuses \r\nRenouvellement PI BK 13808\r\nCR 2024-195 (en cours)",null,null,69379,"2023-12-19","Medium","5,6"]
[null,"Infrabel","64221","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,13,14,"2025-03-29",45280.965277777781,"2025-03-31",45280.215277777781,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses",null,null,64221,"2023-06-15","Minor","5,6"]
[null,"Infrabel","60156","Namur - Antwerpen","< >","Y.NOORD DRIEHOEK LEDEBERG","GENT-DAMPOORT",2025,2025,13,14,"2025-03-29",45280.25,"2025-03-31",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Instandhouding vertakking Noord-Driehoek Ledeberg\r\nCf Escalade Head Of nov/dec 2023",null,null,60156,"2023-12-04","Medium","5,6"]
[null,"Infrabel","73063","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,13,13,"2025-03-30",45280.333333333336,"2025-03-30",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite",null,null,73063,"2023-11-24","Minor","1,2,3,4,5"]
[null,"Infrabel","73580","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,14,17,"2025-03-31",45280.333333333336,"2025-04-26",45280.666666666664,"26d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Stabilisation paroi rocheuse VA entre 89.200 et 90.000\r\n+Visites VA et VB",null,null,73580,"2023-12-15","High","1,2,3,4,5,6,7"]
[null,"Infrabel","72357","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2025,2025,14,14,"2025-03-31",45280.965277777781,"2025-04-05",45280.243055555555,"5d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien massification L144 + 130/1\r\nZone Z09.44 \r\n+ Dépose poteaux caténaire sur L144. (entre L130 et PN10)",null,null,72357,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","53238","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,14,14,"2025-03-31",45280.923611111109,"2025-04-05",45280.194444444445,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de rails \r\n+ Travaux OA \r\n+ Chantier SPW PS 65.090",null,null,53238,"2023-04-12","Minor","1,2,3,4,5"]
[null,"Infrabel","67026","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,14,15,"2025-04-04",45280.958333333336,"2025-04-07",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des traverses P93\r\nWE Bourrage et finitions",null,null,67026,"2023-10-17","Medium","5,6"]
[null,"Infrabel","64661","Athus - Meuse",">","ARLON","ARLON",2025,2025,14,14,"2025-04-04",45280.979166666664,"2025-04-06",45280.708333333336,"2d, 17:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de la TJD 29L/28BL",null,null,64661,"2023-11-15","Minor","5,6"]
[null,"Infrabel","55773","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2025,2025,14,15,"2025-04-05",45280.958333333336,"2025-04-07",45280.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre \r\ncontraintes, finitions (4)",null,null,55773,"2023-03-17","Minor","5,6"]
[null,"Infrabel","64222","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,14,15,"2025-04-05",45280.965277777781,"2025-04-07",45280.215277777781,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses",null,null,64222,"2023-06-15","Minor","5,6"]
[null,"Infrabel","60195","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2025,2025,14,15,"2025-04-05",45280.041666666664,"2025-04-07",45280.1875,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Stationsproject Antwerpen-Zuid B-Stations:\r\nTrapconstructie op perron\r\nCf Escalade Head Of nov/dec 2023",null,null,60195,"2023-12-04","Medium","5,6"]
[null,"Infrabel","74100","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2025,2025,14,14,"2025-04-05",45280.996527777781,"2025-04-06",45280.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B",null,null,74100,"2023-12-13","Minor","5,6"]
[null,"Infrabel","70930","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2025,2025,14,15,"2025-04-06",45280.951388888891,"2025-04-07",45280.194444444445,"1d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.52 P3 HKV\r\nNuit dim/lun",null,null,70930,"2023-09-11","Minor","5,6"]
[null,"Infrabel","56490","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,15,15,"2025-04-07",45280.958333333336,"2025-04-11",45280.173611111109,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Second tabliers ponts 7,8 et 9 + Renouvellement AS de Lobbes-Garage & Hourpes\r\nNuits de préparation",null,null,56490,"2023-05-17","Minor","1,2,3,4,5"]
[null,"Infrabel","72569","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2025,2025,15,15,"2025-04-07",45280.333333333336,"2025-04-07",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,72569,"2023-11-03","Minor","1,2,3,4,5"]
[null,"Infrabel","68928","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,15,15,"2025-04-07",45280.979166666664,"2025-04-11",45280.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L53",null,null,68928,"2023-09-05","Minor","1,2,3,4,5"]
[null,"Infrabel","68057","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET",2025,2025,15,15,"2025-04-07",45280.965277777781,"2025-04-12",45280.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130",null,null,68057,"2023-04-15","Minor","1,2,3,4,5"]
[null,"Infrabel","72813","Lille - Charleroi",">","BRUXELLES-MIDI","BRUXELLES-MIDI",2025,2025,15,15,"2025-04-07",45280.986111111109,"2025-04-12",45280.222222222219,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoudswerken volgens onderhoudskalender Area CE\r\nOnderhoudszone FBMZ_04, perronspoor 18+19 FBMZ.\r\n\r\nBVL later te verkrijgen.",null,null,72813,"2023-12-01","Minor","1,2,3,4,5"]
[null,"Infrabel","72570","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2025,2025,15,15,"2025-04-07",45280.5,"2025-04-07",45280.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,72570,"2023-11-03","Minor","1,2,3,4,5"]
[null,"Infrabel","71706","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,15,15,"2025-04-07",45280.319444444445,"2025-04-07",45280.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance",null,null,71706,"2023-11-24","Minor","1,2,3,4,5"]
[null,"Infrabel","73393","Athus - Meuse",">","DINANT","Y.NEFFE",2025,2025,15,15,"2025-04-08",45280.34375,"2025-04-08",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,73393,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","70276","Namur - Antwerpen",">","AISEAU","LE CAMPINAIRE",2025,2025,15,15,"2025-04-08",45280.34375,"2025-04-08",45280.510416666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rév 64BJ",null,null,70276,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","73108","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,15,15,"2025-04-10",45280.333333333336,"2025-04-10",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73108,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","71119","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,15,15,"2025-04-10",45280.9375,"2025-04-11",45280.229166666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 4\r\nPériodicité toutes les 4 semaines en alternance avec la zone 9\r\nzone 4 : 3 fois sur l'année\r\nzone 9 : 9 fois sur l'année",null,null,71119,"2023-11-06","Minor","1,2,3,4,5"]
[null,"Infrabel","64662","Athus - Meuse",">","ARLON","ARLON",2025,2025,15,16,"2025-04-11",45280.979166666664,"2025-04-14",45280.708333333336,"3d, 17:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de la TJD 29L/28BL\r\n\r\nBourrage de révision, finitions,...",null,null,64662,"2023-04-27","Minor","5,6"]
[null,"Infrabel","55542","Lille - Charleroi","< >","ATH","LEUZE",2025,2025,15,16,"2025-04-11",45280.9375,"2025-04-14",45280.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renforcement des 7 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.",null,null,55542,"2023-04-17","Medium","5,6"]
[null,"Infrabel","69381","Athus - Meuse","< >","DINANT","Y.NEFFE",2025,2025,15,15,"2025-04-12",45280.958333333336,"2025-04-13",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mise au gabarit des pistes de circulation\r\nSécurisation des parois rocheuses \r\nRenouvellement PI BK 13808\r\nCR 2024-195 (en cours)",null,null,69381,"2023-12-19","Medium","5,6"]
[null,"Infrabel","64223","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,15,16,"2025-04-12",45280.965277777781,"2025-04-14",45280.215277777781,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses",null,null,64223,"2023-06-15","Minor","5,6"]
[null,"Infrabel","67466","Lille - Charleroi","< >","GHLIN","MONS",2025,2025,15,15,"2025-04-12",45280.993055555555,"2025-04-13",45280.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim",null,null,67466,"2023-10-23","Minor","5,6"]
[null,"Infrabel","72558","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,15,15,"2025-04-13",45280.3125,"2025-04-13",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72558,"2023-11-03","Minor","5,6"]
[null,"Infrabel","55512","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,16,16,"2025-04-14",45280.958333333336,"2025-04-18",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 1-  39.681 39.749 40.133\r\nPréparations",null,null,55512,"2023-10-17","Minor","1,2,3,4,5"]
[null,"Infrabel","68929","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,16,16,"2025-04-14",45280.979166666664,"2025-04-18",45280.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L53",null,null,68929,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","55547","Lille - Charleroi","< >","ATH","LEUZE",2025,2025,16,16,"2025-04-14",45280.9375,"2025-04-19",45280.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux de construction d'un PI au droit du km 53.560 en vue de la suppression du PN30 + renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\nNuits de finitions",null,null,55547,"2023-04-17","Minor","1,2,3,4,5"]
[null,"Infrabel","55589","Namur - Antwerpen",">","LA ROCHE(BRABANT)","TILLY",2025,2025,16,21,"2025-04-14",45280.25,"2025-05-23",45280.666666666664,"39d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Sécurisation des Parois Rocheuses entre La Roche et Tilly (2 parois)",null,null,55589,"2023-12-19","High","1,2,3,4,5,6,7"]
[null,"Infrabel","66514","Lille - Charleroi","< >","ATH","TOURNAI",2025,2025,16,16,"2025-04-14",45280.940972222219,"2025-04-19",45280.1875,"5d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.54 P3HKV",null,null,66514,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","69459","Erquelinnes - Montzen",">","FLEMALLE-HAUTE","ENGIS",2025,2025,16,16,"2025-04-15",45280.381944444445,"2025-04-18",45280.618055555555,"4d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien caténaire",null,null,69459,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","55514","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,16,17,"2025-04-18",45280.958333333336,"2025-04-22",45280.208333333336,"3d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 1 - 39.681 39.749 40.133",null,null,55514,"2023-10-17","Medium","5,6"]
[null,"Infrabel","56181","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,16,17,"2025-04-19",45280.979166666664,"2025-04-21",45280.208333333336,"2d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement de Luttre - phase 2025\r\nPréparations caténaires, \r\ndémolitions poteaux entre IX-E.20 > quai IV\r\n+ révision à mi-vie caténaire L117, IX-E.20 > T-H.11",null,null,56181,"2023-04-17","Minor","5,6"]
[null,"Infrabel","64233","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,16,17,"2025-04-19",45280.986111111109,"2025-04-21",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais",null,null,64233,"2023-10-12","Minor","5,6"]
[null,"Infrabel","69427","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,16,17,"2025-04-19",45280.000694444447,"2025-04-21",45280.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Migratie tunnelveiligheidstechnieken Antw. NZ -1\r\nAntwerpen-Berchem - Antwerpen-Centraal\r\nCf Escalade Head Of nov/dec 2023",null,null,69427,"2023-12-04","Medium","5,6"]
[null,"Infrabel","72758","Athus - Meuse",">","MARBEHAN","HABAY",2025,2025,16,16,"2025-04-20",45280.375,"2025-04-20",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72758,"2023-11-08","Minor","5,6"]
[null,"Infrabel","53455","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,17,17,"2025-04-22",45280.958333333336,"2025-04-25",45280.173611111109,"3d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Second tabliers ponts 7,8 et 9 + Renouvellement AS de Lobbes-Garage & Hourpes\r\nNuits de préparation",null,null,53455,"2023-05-17","Minor","1,2,3,4,5"]
[null,"Infrabel","67849","Namur - Antwerpen","< >","ESSEN","ESSEN",2025,2025,17,17,"2025-04-22",45280.333333333336,"2025-04-25",45280.666666666664,"4d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels en sporen bundel Essen.  Periodiciteit: 2 keer / jaar (voorjaar/najaar),",null,null,67849,"2023-09-05","Minor","1,2,3,4,5"]
[null,"Infrabel","55548","Lille - Charleroi","< >","ATH","TOURNAI",2025,2025,17,17,"2025-04-22",45280.9375,"2025-04-26",45280.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux de construction d'un PI au droit du km 53.560 en vue de la suppression du PN30 + renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\nNuits de finitions + enlèvement de l'ART\r\n+ Maintenance Z5.54",null,null,55548,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","65794","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2025,2025,17,17,"2025-04-24",45280.979166666664,"2025-04-26",45280.1875,"2d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z7.51 P3",null,null,65794,"2023-10-16","Minor","1,2,3,4,5"]
[null,"Infrabel","67455","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,17,17,"2025-04-24",45280.395833333336,"2025-04-24",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nVisite diagnostique\r\nMise HS en P2",null,null,67455,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","54820","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET",2025,2025,17,18,"2025-04-25",45280.965277777781,"2025-04-28",45280.215277777781,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTir caténaires",null,null,54820,"2023-04-17","Minor","5,6"]
[null,"Infrabel","56524","Athus - Meuse",">","VONECHE","PALISEUL",2025,2025,17,17,"2025-04-25",45280.25,"2025-04-26",45280.25,"2d, 00:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 1 - WE 1\r\nDossier de concertation octobre 2022",null,null,56524,"2022-11-12","Minor","1,2,3,4,5"]
[null,"Infrabel","69933","Lille - Charleroi","< >","Y.JURBISE","QUEVY",2025,2025,17,17,"2025-04-26",45280.03125,"2025-04-27",45280.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Mise en service ETCS\r\nETCS L2-IL_SO_P036_L96_L97_Jurbise –  Mons – Saint Ghislain_ETCS\r\n\r\n En même temps que la colt 71854",null,null,69933,"2023-11-27","Minor","5,6"]
[null,"Infrabel","57974","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,17,18,"2025-04-26",45280.000694444447,"2025-04-28",45280.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwarsliggers",null,null,57974,"2023-06-27","Medium","5,6"]
[null,"Infrabel","68977","Lille - Antwerpen","< >","GENT-SINT-PIETERS","Y.ZANDBERG",2025,2025,17,17,"2025-04-27",45280.055555555555,"2025-04-27",45280.222222222219,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"In dienst stelling ETCS\r\nMeewerken niet mogelijk\r\n\r\nL75 Gent Sint Pieters (v) tot Y.Zandberg (v) - 01.20 tot 05.20\r\nL86 De Pinte - Gavere (v) - 23.25 tot 7.35\r\nL73 Deinze - Lichtervelde (v) - 22.40 tot 07.00",null,null,68977,"2023-06-29","Minor","5,6"]
[null,"Infrabel","54906","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2025,2025,18,18,"2025-04-28",45280.979166666664,"2025-05-03",45280.208333333336,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10.51   P3 HKV",null,null,54906,"2023-10-16","Minor","1,2,3,4,5"]
[null,"Infrabel","72909","Athus - Meuse",">","BERTRIX","STRAIMONT",2025,2025,18,18,"2025-04-29",45280.333333333336,"2025-04-29",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nRQ333: + 2 semaines et en R2 suite SAVU colt 57823 + 61879",null,null,72909,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","72910","Athus - Meuse",">","STRAIMONT","BERTRIX",2025,2025,18,18,"2025-04-30",45280.375,"2025-04-30",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nRQ333: + 2 semaines et en R3 suite SAVU colt 57823",null,null,72910,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","73006","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,18,18,"2025-05-01",45280.333333333336,"2025-05-01",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73006,"2023-11-24","Minor","1,2,3,4,5"]
[null,"Infrabel","56523","Athus - Meuse",">","VONECHE","PALISEUL",2025,2025,18,18,"2025-05-02",45280.25,"2025-05-03",45280.25,"2d, 00:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 1 - WE 2\r\nDossier de concertation octobre 2022",null,null,56523,"2022-11-12","Minor","1,2,3,4,5"]
[null,"Infrabel","64235","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,18,19,"2025-05-03",45280.986111111109,"2025-05-05",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais",null,null,64235,"2023-10-12","Minor","5,6"]
[null,"Infrabel","69756","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,18,19,"2025-05-03",45280.25,"2025-05-05",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"sporen 3+4+5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde",null,null,69756,"2023-10-12","Medium","5,6"]
[null,"Infrabel","71191","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2025,2025,18,18,"2025-05-03",45280.354166666664,"2025-05-03",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nRq 333 : propo +1 we",null,null,71191,"2023-10-26","Minor","5,6"]
[null,"Infrabel","71192","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2025,2025,18,18,"2025-05-04",45280.354166666664,"2025-05-04",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43\r\nRq 333 : propo +1 we",null,null,71192,"2023-10-26","Minor","5,6"]
[null,"Infrabel","69457","Erquelinnes - Montzen",">","HUY","AMPSIN",2025,2025,19,19,"2025-05-05",45280.388888888891,"2025-05-09",45280.625,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien caténaire\r\nRq 333 : incompatible visites + L130\r\nPropo : semaine 19\r\nHuy doit être totalement accessible",null,null,69457,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","73065","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,19,19,"2025-05-08",45280.333333333336,"2025-05-08",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73065,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","73066","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,19,19,"2025-05-09",45280.333333333336,"2025-05-09",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73066,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","70015","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2025,2025,19,19,"2025-05-10",45280.333333333336,"2025-05-11",45280.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie",null,null,70015,"2023-11-29","Minor","5,6"]
[null,"Infrabel","69403","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,19,20,"2025-05-10",45280.25,"2025-05-12",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing wisselonderdelen en sporen te Anwerpen Schijnpoort inrit bundel F.  \r\nMet inbegrip van bundelkop van bundel D - F (K-Q.12 - T-O.12) + L27A sp A zo 0:00u tot ma 5:00u, L27A Sp B zo 6:00u tot 17:40u",null,null,69403,"2023-05-25","Medium","5,6"]
[null,"Infrabel","69757","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,19,20,"2025-05-10",45280.25,"2025-05-12",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"sporen 5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde",null,null,69757,"2023-08-30","Medium","5,6"]
[null,"Infrabel","70008","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2025,2025,19,19,"2025-05-11",45280.333333333336,"2025-05-11",45280.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144-130/1",null,null,70008,"2023-10-12","Minor","5,6"]
[null,"Infrabel","72559","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,19,19,"2025-05-11",45280.3125,"2025-05-11",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72559,"2023-11-03","Minor","5,6"]
[null,"Infrabel","56537","Athus - Meuse",">","VONECHE","PALISEUL",2025,2025,20,20,"2025-05-12",45280.1875,"2025-05-12",45280.6875,"1d, 12:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 1 - WE 3\r\nDossier de concertation octobre 2022",null,null,56537,"2022-11-12","Minor","1,2,3,4,5"]
[null,"Infrabel","73083","Athus - Meuse",">","SIGNEULX","HALANZY",2025,2025,20,20,"2025-05-13",45280.333333333336,"2025-05-13",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73083,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","74478","Lille - ZeeBrugge",">","BRUGGE","Y.BLAUWE TOREN",2025,2025,20,20,"2025-05-13",45280.354166666664,"2025-05-13",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudswerken SK  Brugge St. Pieters. Does via sp B L51 tss Brugge en Y. Blauwe Toren.",null,null,74478,"2023-12-20","Minor","1,2,3,4,5"]
[null,"Infrabel","74479","Lille - ZeeBrugge",">","BRUGGE","BRUGGE-SINT-PIETERS",2025,2025,20,20,"2025-05-13",45280.354166666664,"2025-05-13",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudswerken SK  Brugge St. Pieters.\r\nDoes via sp B L51 tss Brugge en Brugge St. Pieters.\r\nWisselcomplex 12AU/BU en 13AU/BU dient vrij te blijven.",null,null,74479,"2023-12-20","Minor","1,2,3,4,5"]
[null,"Infrabel","72931","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2025,2025,20,20,"2025-05-14",45280.378472222219,"2025-05-14",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,72931,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","53228","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,20,21,"2025-05-16",45280.916666666664,"2025-05-19",45280.229166666664,"2d, 07:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - Phase 2025\r\nWE 2",null,null,53228,"2023-03-08","Medium","5,6"]
[null,"Infrabel","64237","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,20,21,"2025-05-17",45280.986111111109,"2025-05-19",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais",null,null,64237,"2023-06-15","Minor","5,6"]
[null,"Infrabel","68385","Lille - Antwerpen",">","Y.OOST BERCHEM","Y.MELSELE",2025,2025,20,21,"2025-05-17",45280.041666666664,"2025-05-19",45280.1875,"2d, 03:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Stationsproject Antwerpen-Zuid B-Stations:\r\n\r\nTrapconstructie op perron\r\n\r\nIndien weekend 11+12  in orde deze niet nodig!",null,null,68385,"2023-08-31","Minor","5,6"]
[null,"Infrabel","68798","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,20,20,"2025-05-17",45280.340277777781,"2025-05-17",45280.659722222219,"1d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie A Ottignies - Gembloux (extension Rhisnes SAS)",null,null,68798,"2023-06-27","Minor","5,6"]
[null,"Infrabel","69570","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,21,21,"2025-05-19",45280.958333333336,"2025-05-23",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!\r\n\r\nnog geen coordinatie",null,null,69570,"2023-05-28","Minor","1,2,3,4,5"]
[null,"Infrabel","68067","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,21,21,"2025-05-19",45280.958333333336,"2025-05-24",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Dépose poteaux caténaire sur L144. (entre L130 et PN10)",null,null,68067,"2023-10-12","Minor","1,2,3,4,5"]
[null,"Infrabel","71756","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,21,21,"2025-05-19",45280.333333333336,"2025-05-19",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles",null,null,71756,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","56538","Athus - Meuse",">","VONECHE","PALISEUL",2025,2025,21,21,"2025-05-19",45280.1875,"2025-05-19",45280.6875,"1d, 12:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 1 - WE 4\r\nDossier de concertation octobre 2022",null,null,56538,"2022-11-12","Minor","1,2,3,4,5"]
[null,"Infrabel","73380","Athus - Meuse",">","YVOIR","DINANT",2025,2025,21,21,"2025-05-19",45280.385416666664,"2025-05-19",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73380,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","69708","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,21,21,"2025-05-20",45280.979166666664,"2025-05-24",45280.197916666664,"4d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Omvorming 50Hz naar TFSK (L27+L27B+L27B1): \r\n- 2 weken WN van ma-> za in april/mei 2025 (samenwerken ok)",null,null,69708,"2023-12-12","Minor","1,2,3,4,5"]
[null,"Infrabel","73365","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,21,21,"2025-05-21",45280.375,"2025-05-21",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73365,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","73110","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,21,21,"2025-05-22",45280.333333333336,"2025-05-22",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73110,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","66507","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2025,2025,21,22,"2025-05-23",45280.958333333336,"2025-05-26",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Intervention PN + Entretien divers",null,null,66507,"2023-09-25","Medium","5,6"]
[null,"Infrabel","73111","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,21,21,"2025-05-23",45280.333333333336,"2025-05-23",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73111,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","69441","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2025,2025,21,22,"2025-05-24",45280.958333333336,"2025-05-26",45280.201388888891,"2d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing spoorstaven tussen Y Liersesteenweg en Y Krijgsbaan. \r\nBuitendienststelling van L27 Kontich tot L27A Y Zuid Groenenhoek \r\n2 TLO Weekenden van +48u nodig --> L27 enkel tijdens nachten ingevoerd\r\nvoorkeur 17-18/05/2025 en 24-25/05/202\r\n--> hor",null,null,69441,"2023-08-31","Minor","5,6"]
[null,"Infrabel","68176","Namur - Antwerpen",">","OTTIGNIES","WAVRE",2025,2025,21,21,"2025-05-24",45280.333333333336,"2025-05-24",45280.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Ottignies - Wavre VA/VB",null,null,68176,"2023-04-19","Minor","5,6"]
[null,"Infrabel","53520","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2025,2025,21,21,"2025-05-24",45280.25,"2025-05-25",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10. 51   P4+",null,null,53520,"2023-08-31","Medium","5,6"]
[null,"Infrabel","57978","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,21,22,"2025-05-24",45280.25,"2025-05-26",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwaarsliggers",null,null,57978,"2023-08-23","Medium","5,6"]
[null,"Infrabel","71179","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2025,2025,21,21,"2025-05-25",45280.354166666664,"2025-05-25",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,71179,"2023-10-26","Minor","5,6"]
[null,"Infrabel","55523","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,22,22,"2025-05-26",45280.958333333336,"2025-05-31",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes - 36.363 38.279\r\nPréparations\r\n+ Maintenance Z3.51 P3",null,null,55523,"2023-10-17","Minor","1,2,3,4,5"]
[null,"Infrabel","73394","Athus - Meuse",">","Y.NEFFE","DINANT",2025,2025,22,22,"2025-05-26",45280.333333333336,"2025-05-26",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,73394,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","71286","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2025,2025,22,22,"2025-05-26",45280.951388888891,"2025-05-30",45280.201388888891,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.43 HKV",null,null,71286,"2023-09-25","Minor","1,2,3,4,5"]
[null,"Infrabel","54153","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,22,23,"2025-05-26",45280.25,"2025-06-02",45280.208333333336,"7d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - Phase 2025\r\nCTL 1 semaine",null,null,54153,"2023-04-06","Medium","1,2,3,4,5,6,7"]
[null,"Infrabel","67792","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,22,22,"2025-05-27",45280.020833333336,"2025-05-31",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud \r\nFLC SP III-IV inbegrepen",null,null,67792,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","72769","Athus - Meuse",">","LAVAUX","MARBEHAN",2025,2025,22,22,"2025-05-28",45280.361111111109,"2025-05-28",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72769,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","59623","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,22,23,"2025-05-30",45280.993055555555,"2025-06-02",45280.1875,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification OA\r\nSuppression des PN 56 et 58 - Poussage PI\r\nPS Maréchal Juin BK45.631 - Démolition\r\nChapes d'étanchéité\r\n+ Mise au gabarit des pistes Namur Rhisnes parois rocheuses.\r\n+ Travaux caténaires\r\n10 - Déroulage liaisons Namur- Gembloux",null,null,59623,"2023-06-22","Medium","5,6"]
[null,"Infrabel","69760","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,22,23,"2025-05-31",45280.25,"2025-06-02",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"sporen 5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde",null,null,69760,"2023-08-31","Medium","5,6"]
[null,"Infrabel","73167","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,22,22,"2025-05-31",45280.385416666664,"2025-05-31",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73167,"2023-11-13","Minor","5,6"]
[null,"Infrabel","72774","Athus - Meuse",">","ARLON","Y.AUTELBAS",2025,2025,22,22,"2025-05-31",45280.361111111109,"2025-05-31",45280.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72774,"2023-11-08","Minor","5,6"]
[null,"Infrabel","73171","Athus - Meuse",">","LUSTIN","JAMBES",2025,2025,22,22,"2025-06-01",45280.385416666664,"2025-06-01",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73171,"2023-11-13","Minor","5,6"]
[null,"Infrabel","69572","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,23,23,"2025-06-02",45280.958333333336,"2025-06-06",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!\r\n\r\nnog geen coordinatie",null,null,69572,"2023-05-28","Minor","1,2,3,4,5"]
[null,"Infrabel","46309","Athus - Meuse",">","DINANT","YVOIR",2025,2025,23,28,"2025-06-02",45280.333333333336,"2025-07-07",45280.666666666664,"35d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Remise en peinture viaduc de Houx\r\nMise au gabarit pistes de circulation\r\nPhase 1\r\n+ Remplacement des pdb du viaduc de Houx",null,null,46309,"2023-12-15","High","1,2,3,4,5,6,7"]
[null,"Infrabel","73125","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2025,2025,23,23,"2025-06-02",45280.385416666664,"2025-06-02",45280.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie\r\nRQ333:+1 semaine ok?",null,null,73125,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","67793","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,23,23,"2025-06-03",45280.020833333336,"2025-06-07",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud \r\nFLC SP III-IV inbegrepen",null,null,67793,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","71211","Erquelinnes - Montzen",">","JAVA","STATTE",2025,2025,23,23,"2025-06-04",45280.354166666664,"2025-06-04",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71211,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","71077","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,23,23,"2025-06-06",45280.958333333336,"2025-06-07",45280.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,71077,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","55529","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,23,24,"2025-06-06",45280.958333333336,"2025-06-10",45280.208333333336,"3d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 2- 36.363 38.279\r\n+ Maintenance Z3.51 P4",null,null,55529,"2023-10-17","Medium","5,6"]
[null,"Infrabel","69360","Namur - Antwerpen","< >","Y.HOLLAND","LUCHTBAL-ROOSTER S",2025,2025,23,23,"2025-06-07",45280.25,"2025-06-08",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Lantis Oosterweelverbinding RO",null,null,69360,"2023-09-06","Medium","5,6"]
[null,"Infrabel","55215","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2025,2025,23,24,"2025-06-07",45280.25,"2025-06-09",45280.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Entretien mécanisé et manuel des AS du grill Nord de Visé-Bas\r\nEntretien mécanisé du PN 28",null,null,55215,"2023-09-26","Medium","5,6"]
[null,"Infrabel","72549","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,23,23,"2025-06-07",45280.3125,"2025-06-07",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72549,"2023-11-03","Minor","5,6"]
[null,"Infrabel","72560","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,23,23,"2025-06-08",45280.3125,"2025-06-08",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72560,"2023-11-03","Minor","5,6"]
[null,"Infrabel","66582","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2025,2025,24,24,"2025-06-09",45280.364583333336,"2025-06-13",45280.635416666664,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Peignage parois rocheuses",null,null,66582,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","65800","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2025,2025,24,24,"2025-06-10",45280.996527777781,"2025-06-14",45280.208333333336,"4d, 05:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.51 P3",null,null,65800,"2023-10-16","Minor","1,2,3,4,5"]
[null,"Infrabel","72932","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2025,2025,24,24,"2025-06-13",45280.378472222219,"2025-06-13",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,72932,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","73044","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2025,2025,24,24,"2025-06-14",45280.333333333336,"2025-06-14",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A\r\nRQ333:@Elise quid compatibilité avec ART ST-Vincent/Florenville ?",null,null,73044,"2023-11-22","Minor","5,6"]
[null,"Infrabel","65803","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2025,2025,24,24,"2025-06-14",45280.25,"2025-06-15",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.51 P4",null,null,65803,"2023-04-24","Medium","5,6"]
[null,"Infrabel","74101","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2025,2025,24,24,"2025-06-14",45280.996527777781,"2025-06-15",45280.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B",null,null,74101,"2023-12-11","Minor","5,6"]
[null,"Infrabel","69574","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,25,25,"2025-06-16",45280.958333333336,"2025-06-20",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!\r\n\r\nnog geen coordinatie",null,null,69574,"2023-05-28","Minor","1,2,3,4,5"]
[null,"Infrabel","68128","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,25,25,"2025-06-16",45280.958333333336,"2025-06-21",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022",null,null,68128,"2023-04-18","Minor","1,2,3,4,5"]
[null,"Infrabel","71235","Erquelinnes - Montzen","< >","HUY","NAMUR",2025,2025,25,25,"2025-06-16",45280.993055555555,"2025-06-20",45280.215277777781,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.43 HKV \r\nChoix restrictif\r\nRQ333: amplitude 23h50-5h10 suite CTL 112",null,null,71235,"2023-11-16","Minor","1,2,3,4,5"]
[null,"Infrabel","71905","Namur - Antwerpen","< >","MECHELEN","KONTICH-LINT",2025,2025,25,25,"2025-06-16",45280.993055555555,"2025-06-21",45280.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKV",null,null,71905,"2023-12-12","Minor","1,2,3,4,5"]
[null,"Infrabel","71665","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2025,2025,25,25,"2025-06-16",45280.947916666664,"2025-06-21",45280.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 05.32\r\nL58 Eeklo inbegrepen tot Gent Dampoort NIET inbegrepen",null,null,71665,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","69042","Erquelinnes - Montzen",">","TILLEUR","Y.LEMAN",2025,2025,25,25,"2025-06-16",45280.375,"2025-06-20",45280.625,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien caténaire\r\nPrestation de 05h minimum\r\nRQ333: proposition S25 car dorsale moins chargée\r\nrép ok",null,null,69042,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","72912","Athus - Meuse",">","BERTRIX","STRAIMONT",2025,2025,25,25,"2025-06-18",45280.333333333336,"2025-06-18",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nRQ333: +1 semaine et en R3",null,null,72912,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","72911","Athus - Meuse",">","STRAIMONT","BERTRIX",2025,2025,25,25,"2025-06-19",45280.375,"2025-06-19",45280.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nRQ333: +1 sem et en R4",null,null,72911,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","39541","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2025,2025,25,26,"2025-06-20",45280.9375,"2025-06-23",45280.173611111109,"2d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nCTL en continu pour ripage du CSV",null,null,39541,"2023-06-22","Medium","5,6"]
[null,"Infrabel","69566","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,25,26,"2025-06-21",45280,"2025-06-23",45280.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!\r\n\r\nnog geen coordinatie",null,null,69566,"2023-05-28","Medium","5,6"]
[null,"Infrabel","54891","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2025,2025,25,25,"2025-06-21",45280.986111111109,"2025-06-22",45280.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mini CTL pour maintenance globale  L130  + L130/1 + L144",null,null,54891,"2023-11-29","Medium","5,6"]
[null,"Infrabel","59607","Namur - Antwerpen","< >","ESSEN-GRENS","Y.LUCHTBAL",2025,2025,25,26,"2025-06-21",45280.041666666664,"2025-06-23",45280.166666666664,"2d, 03:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie",null,null,59607,"2023-12-15","Medium","5,6"]
[null,"Infrabel","64935","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2025,2025,25,25,"2025-06-22",45280.3125,"2025-06-22",45280.520833333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Noord\r\nBuitendienststellen van de van de volledige overeenkomstige EBP-zone gedurende minimaal 4 uur te bepalen tussen 06.00 uur en 14.00 uur\r\nUpdate EBP release to last version\r\nR-447118",null,null,64935,"2023-01-27","Minor","5,6"]
[null,"Infrabel","69575","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,26,26,"2025-06-23",45280.958333333336,"2025-06-27",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!\r\n\r\nnog geen coordinatie",null,null,69575,"2023-05-28","Minor","1,2,3,4,5"]
[null,"Infrabel","55531","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,26,26,"2025-06-23",45280.958333333336,"2025-06-28",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 2 - 36.363 38.279\r\nfinitions",null,null,55531,"2023-10-17","Minor","1,2,3,4,5"]
[null,"Infrabel","69705","Namur - Antwerpen","< >","MECHELEN-DIJKSTRAAT","KONTICH-LINT",2025,2025,26,26,"2025-06-23",45280.993055555555,"2025-06-28",45280.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK (samen met L27B): \r\n- min. 2 weken WN voor indienststelling (in maand ervoor)",null,null,69705,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","72040","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2025,2025,26,26,"2025-06-24",45280.003472222219,"2025-06-28",45280.184027777781,"5d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z07.31 HKM\r\nL75 FGSP-FD \r\nFGSP SP VIII-IX + Bundel CD niet bereikbaar\r\nFD blijft vrij\r\nL86 FPT-FDN\r\nFDN SP III-IV in",null,null,72040,"2023-11-10","Minor","1,2,3,4,5"]
[null,"Infrabel","72789","Athus - Meuse",">","HABAY","STOCKEM-NORD",2025,2025,26,26,"2025-06-25",45280.375,"2025-06-25",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72789,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","62944","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2025,2025,26,27,"2025-06-27",45280.993055555555,"2025-06-30",45280.166666666664,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nPMR Maubeuge 48h00",null,null,62944,"2022-12-02","Medium","5,6"]
[null,"Infrabel","65315","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2025,2025,26,27,"2025-06-28",45280.013888888891,"2025-06-30",45280.194444444445,"2d, 04:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Z-12.42\r\nEntretien manuel et mécanisés des AW de Visé-Bas \r\nEntretien manuel et mécanisés de la voie courante\r\n+ + Renouvellement de rails",null,null,65315,"2023-10-18","Medium","5,6"]
[null,"Infrabel","55172","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,26,27,"2025-06-29",45280.958333333336,"2025-06-30",45280.208333333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022",null,null,55172,"2023-05-22","Minor","5,6"]
[null,"Infrabel","71758","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,27,27,"2025-06-30",45280.333333333336,"2025-06-30",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles",null,null,71758,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","59225","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,27,27,"2025-06-30",45280.979166666664,"2025-07-05",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels\r\nSP A L58/1 Y West Driehoek ",null,null,59225,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","69706","Namur - Antwerpen","< >","MECHELEN-DIJKSTRAAT","KONTICH-LINT",2025,2025,27,27,"2025-06-30",45280.993055555555,"2025-07-05",45280.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK (samen met L27B): \r\n- min. 1 week WN na indienststelling",null,null,69706,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","66515","Lille - Charleroi","< >","ATH","TOURNAI",2025,2025,27,27,"2025-06-30",45280.940972222219,"2025-07-05",45280.1875,"5d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.54",null,null,66515,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","73112","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,27,27,"2025-07-01",45280.333333333336,"2025-07-01",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73112,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","72787","Athus - Meuse",">","LAVAUX","MARBEHAN",2025,2025,27,27,"2025-07-02",45280.361111111109,"2025-07-02",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72787,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","72786","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2025,2025,27,27,"2025-07-03",45280.368055555555,"2025-07-03",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72786,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","56531","Athus - Meuse",">","GEDINNE","PALISEUL",2025,2025,27,27,"2025-07-04",45280.25,"2025-07-05",45280.25,"2d, 00:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 2 - WE 3\r\nDossier de concertation octobre 2022",null,null,56531,"2022-11-12","Minor","1,2,3,4,5"]
[null,"Infrabel","72785","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2025,2025,27,27,"2025-07-04",45280.368055555555,"2025-07-04",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72785,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","73028","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,27,27,"2025-07-05",45280.333333333336,"2025-07-05",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A\r\nRQ333: - 1 semaine et en R6 ok ?",null,null,73028,"2023-11-10","Minor","1,2,3,4,5"]
[null,"Infrabel","66571","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2025,2025,27,28,"2025-07-05",45280.013888888891,"2025-07-07",45280.166666666664,"2d, 03:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen perron De Pinte - weekend 2/3\r\n+  Massificatie tss De Pinte en Gent\r\n+ Onderhoud Rooster De PInte\r\n+ Onderhoud rooster Gent \r\n * Gent Sint Pieters SP III-IV-V inbegrepen\r\nCf Escalade Head Of nov/dec 2023",null,null,66571,"2023-12-04","Medium","5,6"]
[null,"Infrabel","74102","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2025,2025,27,27,"2025-07-05",45280.996527777781,"2025-07-06",45280.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B",null,null,74102,"2023-12-11","Minor","5,6"]
[null,"Infrabel","73193","Athus - Meuse",">","LIBRAMONT","HATRIVAL",2025,2025,27,27,"2025-07-05",45280.385416666664,"2025-07-05",45280.611111111109,"1d, 05:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73193,"2023-11-15","Minor","5,6"]
[null,"Infrabel","68802","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,27,27,"2025-07-06",45280.333333333336,"2025-07-06",45280.375,"1d, 01:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie B Ottignies - Gembloux (extension Rhisnes SAS)",null,null,68802,"2023-12-05","Minor","5,6"]
[null,"Infrabel","72561","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,27,27,"2025-07-06",45280.3125,"2025-07-06",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72561,"2023-11-03","Minor","5,6"]
[null,"Infrabel","71114","Namur - Antwerpen","< >","NAMUR","RONET",2025,2025,27,27,"2025-07-06",45280.003472222219,"2025-07-06",45280.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur (ZONE 6)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,71114,"2023-11-06","Minor","5,6"]
[null,"Infrabel","73876","Namur - Antwerpen",">","MONT-SAINT-GUIBERT","GEMBLOUX",2025,2025,27,27,"2025-07-06",45280.375,"2025-07-06",45280.583333333336,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie B Ottignies - Gembloux (extension Rhisnes SAS)",null,null,73876,"2023-12-05","Minor","5,6"]
[null,"Infrabel","65783","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2025,2025,28,28,"2025-07-07",45280.951388888891,"2025-07-12",45280.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.51 \r\nP3 HKV",null,null,65783,"2023-10-05","Minor","1,2,3,4,5"]
[null,"Infrabel","56541","Athus - Meuse",">","GEDINNE","PALISEUL",2025,2025,28,28,"2025-07-07",45280.1875,"2025-07-07",45280.6875,"1d, 12:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 2 - WE 3\r\nDossier de concertation octobre 2022",null,null,56541,"2022-11-12","Minor","1,2,3,4,5"]
[null,"Infrabel","66525","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2025,2025,28,28,"2025-07-07",45280.930555555555,"2025-07-12",45280.180555555555,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.54",null,null,66525,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","71708","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,28,28,"2025-07-07",45280.319444444445,"2025-07-07",45280.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance",null,null,71708,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","73141","Athus - Meuse",">","NAMUR","JAMBES",2025,2025,28,28,"2025-07-08",45280.388888888891,"2025-07-08",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73141,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","73191","Athus - Meuse",">","LUSTIN","JAMBES",2025,2025,28,28,"2025-07-10",45280.385416666664,"2025-07-10",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73191,"2023-12-15","Minor","5,6"]
[null,"Infrabel","73367","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,28,28,"2025-07-11",45280.375,"2025-07-11",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73367,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","68177","Namur - Antwerpen",">","OTTIGNIES","WAVRE",2025,2025,28,28,"2025-07-12",45280.333333333336,"2025-07-12",45280.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Ottignies - Wavre VA/VB",null,null,68177,"2023-04-19","Minor","5,6"]
[null,"Infrabel","68179","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2025,2025,28,28,"2025-07-13",45280.333333333336,"2025-07-13",45280.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Ottignies - Wavre VA/VB",null,null,68179,"2023-04-19","Minor","5,6"]
[null,"Infrabel","68711","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2025,2025,29,29,"2025-07-14",45280.951388888891,"2025-07-18",45280.201388888891,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons\r\nZ9.41 + L.125/1\r\n+ voies 834 et 835 de Flémalle-Haute\r\nPrestation de 05h00 minimum\r\nRQ333:@Elise, détournement des derniers trains \"Les Ardentes\" via SAVU L125A, ok ?",null,null,68711,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","56542","Athus - Meuse",">","GEDINNE","PALISEUL",2025,2025,29,29,"2025-07-14",45280.1875,"2025-07-14",45280.6875,"1d, 12:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 2 - WE 4\r\nDossier de concertation octobre 2022",null,null,56542,"2022-11-12","Minor","1,2,3,4,5"]
[null,"Infrabel","72575","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2025,2025,29,29,"2025-07-14",45280.5,"2025-07-14",45280.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,72575,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","72576","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,29,29,"2025-07-15",45280.395833333336,"2025-07-15",45280.611111111109,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie et intervention avec S460 sur la voie contiguë + ATW",null,null,72576,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","71196","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2025,2025,29,29,"2025-07-17",45280.375,"2025-07-17",45280.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71196,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","53512","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2025,2025,29,30,"2025-07-19",45280.25,"2025-07-21",45280.708333333336,"2d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.3.53 +  Z9.52 en P4",null,null,53512,"2023-08-31","Medium","5,6"]
[null,"Infrabel","71198","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2025,2025,29,29,"2025-07-20",45280.354166666664,"2025-07-20",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71198,"2023-10-26","Minor","5,6"]
[null,"Infrabel","73961","Namur - Antwerpen",">","Y.OOST DRIEHOEK LEDEBERG","Y.WEST DRIEHOEK LEDEBERG",2025,2025,30,30,"2025-07-22",45280.027777777781,"2025-07-26",45280.194444444445,"5d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"reservatie onderhoud \r\nSchets DOES 4\r\nL50E SP B 01XR inbegrepen tot 05O inbegrepen\r\nL58/1 SP B 05O inbegrepen tot 10XO inbegrepen\r\nL58(1) SP A 10XO inbegrepen tot 01XR inbegrepen",null,null,73961,"2023-12-07","Minor","1,2,3,4,5"]
[null,"Infrabel","73046","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2025,2025,30,30,"2025-07-26",45280.333333333336,"2025-07-26",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73046,"2023-11-13","Minor","5,6"]
[null,"Infrabel","71109","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2025,2025,30,31,"2025-07-27",45280.958333333336,"2025-07-28",45280.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 3) 6 fois sur l'année",null,null,71109,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","66147","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2025,2025,31,31,"2025-07-28",45280.951388888891,"2025-08-02",45280.194444444445,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.52 P3 HKV",null,null,66147,"2023-09-11","Minor","1,2,3,4,5"]
[null,"Infrabel","72933","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,31,31,"2025-07-30",45280.378472222219,"2025-07-30",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,72933,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","71079","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,31,31,"2025-08-01",45280.958333333336,"2025-08-02",45280.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,71079,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","67283","Athus - Meuse","< >","GEDINNE","BERTRIX",2025,2025,31,31,"2025-08-02",45280.958333333336,"2025-08-03",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires",null,null,67283,"2023-06-08","Medium","5,6"]
[null,"Infrabel","72398","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","Y.NORD",2025,2025,31,32,"2025-08-03",45280.9375,"2025-08-04",45280.229166666664,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Centrale\r\nLivraison LRS par le biais du train T-Portique\r\nCoupure type selon le plan \"SIRU Aménagement Charleroi 2025_ Zone déchargement LRS n°2 (T-Portique)\"",null,null,72398,"2023-11-27","Minor","5,6"]
[null,"Infrabel","67044","Namur - Antwerpen",">","AUVELAIS","HAM-SUR-SAMBRE",2025,2025,32,32,"2025-08-04",45280.958333333336,"2025-08-09",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre",null,null,67044,"2023-04-18","Minor","1,2,3,4,5"]
[null,"Infrabel","74340","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,32,32,"2025-08-04",45280.965277777781,"2025-08-08",45280.243055555555,"4d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose poteaux caténaire sur L144. (entre L130 et PN10)",null,null,74340,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","73069","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,32,32,"2025-08-07",45280.333333333336,"2025-08-07",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A\r\nRQ333:+1 semaine ok ?",null,null,73069,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","68133","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2025,2025,32,32,"2025-08-09",45280.333333333336,"2025-08-09",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130",null,null,68133,"2023-11-29","Minor","5,6"]
[null,"Infrabel","53489","Lille - Charleroi","< >","Y.JURBISE","MONS",2025,2025,32,32,"2025-08-09",45280.25,"2025-08-10",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.5.53 P4+",null,null,53489,"2023-09-08","Medium","5,6"]
[null,"Infrabel","68134","Namur - Antwerpen",">","AUVELAIS","MOUSTIER",2025,2025,33,33,"2025-08-11",45280.958333333336,"2025-08-16",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre",null,null,68134,"2023-04-19","Minor","1,2,3,4,5"]
[null,"Infrabel","71759","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,33,33,"2025-08-11",45280.333333333336,"2025-08-11",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles",null,null,71759,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","66385","Lille - Charleroi","< >","Y.FELUY","Y.FAMILLEUREUX",2025,2025,33,33,"2025-08-11",45280.916666666664,"2025-08-14",45280.208333333336,"3d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de l'étanchéité et renforcement du PS 41.010\r\nPhase de préparation\r\nRq 333 : NOK CBP - lié quel chantier??\r\nPropo du 11/08 au 14/08",null,null,66385,"2023-11-08","Minor","1,2,3,4,5"]
[null,"Infrabel","73092","Lille - ZeeBrugge","< >","LICHTERVELDE","KORTRIJK",2025,2025,33,33,"2025-08-11",45280.961805555555,"2025-08-15",45280.166666666664,"4d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud zone 04.35 HKV\r\nL66/1 volledig inbegrepen \r\nL75 SP B van LK tot Y Bethune AW20E/19AE vrij\r\nL66 LK tot FLC SP II-IV-V + DSP 736 inbegrepen \r\nL69 TLO Y LK West tot FME SP II inbegrepen\r\nL69 DOES SP B FME SP II inbegrepen tot FOI AW 31N vrij\r\nR5/",null,null,73092,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","72782","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2025,2025,33,33,"2025-08-11",45280.409722222219,"2025-08-11",45280.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72782,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","67744","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2025,2025,33,33,"2025-08-12",45280.010416666664,"2025-08-14",45280.177083333336,"3d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken en kleine vernieuwingswerken\r\nDeinze SP I-II inbegrepen\r\nY Zandberg niet inbegrepen\r\n\r\nGevallen; \r\n29289-29288-29290-29291-29293-29292-29295-29294-29296-29297-29298",null,null,67744,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","67784","Athus - Meuse","< >","HATRIVAL","MARBEHAN",2025,2025,33,34,"2025-08-13",45280.979166666664,"2025-08-18",45280.208333333336,"4d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renforcement mur de soutènement VB 166.693 + renouvellement P.I. 166.698\r\n+ Réalisation de lame d'air et déplacement séparation de phase Rocogne L165(1) - L162 avec Cas caténaire: 26814, 815, 818, 820, 821, 822, 824,828, 830, 832,444, 445\r\n+ Pose supers",null,null,67784,"2023-11-15","Medium","1,2,3,4,5,6,7"]
[null,"Infrabel","67457","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,33,33,"2025-08-14",45280.395833333336,"2025-08-14",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nVisite diagnostique\r\nMise HS en P2",null,null,67457,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","67743","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2025,2025,33,34,"2025-08-15",45280.979166666664,"2025-08-18",45280.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken en kleine vernieuwingswerken\r\nDeinze SP I-II inbegrepen\r\nY Zandberg niet inbegrepen\r\n\r\nGevallen; \r\n29289-29288-29290-29291-29293-29292-29295-29294-29296-29297-29298",null,null,67743,"2023-10-09","Medium","5,6"]
[null,"Infrabel","71181","Erquelinnes - Montzen",">","AMAY","ENGIS",2025,2025,33,33,"2025-08-16",45280.333333333336,"2025-08-16",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71181,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","68162","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,33,34,"2025-08-16",45280.986111111109,"2025-08-18",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre",null,null,68162,"2023-10-12","Minor","5,6"]
[null,"Infrabel","68310","Erquelinnes - Montzen",">","LOBBES","ERQUELINNES-VILLAGE",2025,2025,34,34,"2025-08-18",45280.958333333336,"2025-08-23",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement AS Lobbes-Garage : préparation caténaire",null,null,68310,"2023-04-26","Minor","1,2,3,4,5"]
[null,"Infrabel","70069","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","Y.LEMAN",2025,2025,34,34,"2025-08-18",45280.951388888891,"2025-08-23",45280.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Z9.41 - P3 maintenance AI41",null,null,70069,"2023-09-25","Minor","1,2,3,4,5"]
[null,"Infrabel","67777","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,34,34,"2025-08-18",45280.375,"2025-08-19",45280.625,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nTransfert L130/1 du cas 26690",null,null,67777,"2023-04-12","Minor","1,2,3,4,5"]
[null,"Infrabel","73142","Athus - Meuse",">","NAMUR","JAMBES",2025,2025,34,34,"2025-08-18",45280.388888888891,"2025-08-18",45280.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73142,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","73197","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,34,34,"2025-08-19",45280.385416666664,"2025-08-19",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73197,"2023-11-20","Minor","5,6"]
[null,"Infrabel","73370","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,34,34,"2025-08-21",45280.375,"2025-08-21",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73370,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","73031","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2025,2025,34,34,"2025-08-22",45280.333333333336,"2025-08-22",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73031,"2023-11-24","Minor","1,2,3,4,5"]
[null,"Infrabel","73371","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,34,34,"2025-08-22",45280.375,"2025-08-22",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73371,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","66196","Lille - Charleroi",">","LUTTRE","ROUX",2025,2025,34,34,"2025-08-23",45280.25,"2025-08-24",45280.708333333336,"1d, 11:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance Z05.52 P4",null,null,66196,"2023-05-15","Minor","5,6"]
[null,"Infrabel","65640","Lille - Antwerpen","< >","Y.MELSELE","SINT-NIKLAAS",2025,2025,34,35,"2025-08-23",45280.25,"2025-08-25",45280.194444444445,"2d, 22:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"P143: afschaffen overweg 17 L59 - Haasdonkbaan, Beveren fietstunnel\r\ngevallen van toepassing; 22847, 22848, 22846\r\n+  Onderhoud Wissels Sint Niklaas \r\nperron II-III inbegrepen AW12AL-11BL-14BL-10XL-16BL-14AL-12BL-18AL-03BL-15L\r\ngeval 29671+29672\r\nCf Esc",null,null,65640,"2023-12-15","Medium","5,6"]
[null,"Infrabel","70011","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2025,2025,34,34,"2025-08-24",45280.333333333336,"2025-08-24",45280.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144-130/1",null,null,70011,"2023-11-22","Minor","5,6"]
[null,"Infrabel","68312","Erquelinnes - Montzen",">","LOBBES","ERQUELINNES-VILLAGE",2025,2025,35,35,"2025-08-25",45280.958333333336,"2025-08-30",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement AS Lobbes-Garage : préparation caténaire",null,null,68312,"2023-04-26","Minor","1,2,3,4,5"]
[null,"Infrabel","69770","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,35,35,"2025-08-25",45280.979166666664,"2025-08-30",45280.208333333336,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"sporen 5+6\r\nRestauratie trapkooien Vilvoorde",null,null,69770,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","59228","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,35,35,"2025-08-25",45280.979166666664,"2025-08-30",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels\r\nSP A L58/1 Y West Driehoek ",null,null,59228,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","73127","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2025,2025,35,35,"2025-08-25",45280.385416666664,"2025-08-25",45280.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,73127,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","71219","Erquelinnes - Montzen",">","JAVA","STATTE",2025,2025,35,35,"2025-08-27",45280.354166666664,"2025-08-27",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71219,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","73399","Athus - Meuse",">","DINANT","Y.NEFFE",2025,2025,35,35,"2025-08-28",45280.34375,"2025-08-28",45280.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites VA",null,null,73399,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","50216","Erquelinnes - Montzen",">","HUY","ANDENNE",2025,2025,35,36,"2025-08-29",45280.979166666664,"2025-09-01",45280.229166666664,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA\r\n+ suppression des passages à niveau n°75 à 78 (construction des couloir sous-voies)",null,null,50216,"2023-09-01","Minor","5,6"]
[null,"Infrabel","61439","Erquelinnes - Montzen","< >","STATTE","NAMUR",2025,2025,35,36,"2025-08-30",45280.25,"2025-09-01",45280.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux OA \r\nrenouvellement quais  - parois rocheuses - suppression PN Seilles\r\n+ Visite périodique de voie AI43 : Andenne-MLD + Slaigneaux-Beez\r\n+ Démentellement gare de Namèche",null,null,61439,"2023-11-13","Medium","5,6"]
[null,"Infrabel","69118","Namur - Antwerpen","< >","ANTWERPEN-OOST","Y.HOLLAND",2025,2025,35,36,"2025-08-30",45280.041666666664,"2025-09-01",45280.15625,"2d, 02:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels en sporen te Anwerpen Schijnpoort inrit bundel E.  \r\nPeriodiciteit: 1 keer / jaar, \r\nTLO van 48u; \r\n\r\nmet inbegrip van bundelkop van bundel C (G-N.12 - F-N.12) en bundel E (H-H.12 - E-N.12) \r\n+ L27A sp A zo 0:00u tot ma 5:00u, L27A Sp ",null,null,69118,"2023-08-31","Medium","5,6"]
[null,"Infrabel","69120","Namur - Antwerpen","< >","ANTWERPEN-OOST","Y.HOLLAND",2025,2025,35,35,"2025-08-31",45280.25,"2025-08-31",45280.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels en sporen te Anwerpen Schijnpoort inrit bundel E.  \r\nPeriodiciteit: 1 keer / jaar, \r\nTLO van 48u; \r\n\r\nmet inbegrip van bundelkop van bundel C (G-N.12 - F-N.12) en bundel E (H-H.12 - E-N.12) \r\n+ L27A sp A zo 0:00u tot ma 5:00u, L27A Sp ",null,null,69120,"2023-05-26","Minor","5,6"]
[null,"Infrabel","71115","Namur - Antwerpen","< >","NAMUR","RONET",2025,2025,35,35,"2025-08-31",45280.003472222219,"2025-08-31",45280.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur (ZONE 6)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,71115,"2023-11-06","Minor","5,6"]
[null,"Infrabel","55532","Namur - Antwerpen","< >","OTTIGNIES","LODELINSART",2025,2025,36,36,"2025-09-01",45280.958333333336,"2025-09-06",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Pi métalliques 52.015 et 52.215\r\nPréparations",null,null,55532,"2023-10-17","Minor","1,2,3,4,5"]
[null,"Infrabel","68930","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,36,36,"2025-09-01",45280.979166666664,"2025-09-05",45280.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L53",null,null,68930,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","64174","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","FROYENNES",2025,2025,36,36,"2025-09-01",45280.944444444445,"2025-09-06",45280.222222222219,"5d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction d’un PS pour supprimer les PN 8 et 10 - Réalisation des pieux",null,null,64174,"2023-04-19","Minor","1,2,3,4,5"]
[null,"Infrabel","62219","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,36,36,"2025-09-01",45280.923611111109,"2025-09-06",45280.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux préparatoires caténaire (poteaux + équiments)",null,null,62219,"2023-04-26","Minor","1,2,3,4,5"]
[null,"Infrabel","54840","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,36,38,"2025-09-04",45280.958333333336,"2025-09-16",45280.208333333336,"12d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022",null,null,54840,"2022-11-09","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","67281","Athus - Meuse","< >","GEDINNE","BERTRIX",2025,2025,36,36,"2025-09-06",45280.958333333336,"2025-09-07",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires",null,null,67281,"2023-06-08","Medium","5,6"]
[null,"Infrabel","53513","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2025,2025,36,36,"2025-09-06",45280.25,"2025-09-07",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.3.53 +  Z9.52 en P4",null,null,53513,"2023-08-31","Medium","5,6"]
[null,"Infrabel","61438","Erquelinnes - Montzen","< >","STATTE","NAMUR",2025,2025,36,37,"2025-09-06",45280.25,"2025-09-08",45280.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux OA \r\nrenouvellement quais  - parois rocheuses - suppression PN Seilles\r\n+ Démentellement gare de Namèche",null,null,61438,"2023-11-13","Medium","5,6"]
[null,"Infrabel","72552","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,36,36,"2025-09-06",45280.3125,"2025-09-06",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72552,"2023-11-03","Minor","5,6"]
[null,"Infrabel","73049","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2025,2025,36,36,"2025-09-07",45280.333333333336,"2025-09-07",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73049,"2023-11-13","Minor","5,6"]
[null,"Infrabel","69496","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.ANTWERPEN-OOST",2025,2025,36,36,"2025-09-07",45280.25,"2025-09-07",45280.666666666664,"1d, 10:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug",null,null,69496,"2023-09-01","Minor","5,6"]
[null,"Infrabel","74035","Namur - Antwerpen","< >","GENT-SINT-PIETERS","MERELBEKE-ROOSTER S",2025,2025,36,36,"2025-09-07",45280.034722222219,"2025-09-07",45280.243055555555,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud schets za^zo\r\n\r\nL50E TLO Rooster S tot FGSP\r\nL58 + L58/1 TLO tot FGDM",null,null,74035,"2023-12-11","Minor","5,6"]
[null,"Infrabel","68931","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,37,37,"2025-09-08",45280.979166666664,"2025-09-12",45280.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L53",null,null,68931,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","69772","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,37,37,"2025-09-08",45280.979166666664,"2025-09-13",45280.25,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"sporen 3+4+5+6\r\nRestauratie trapkooien Vilvoorde",null,null,69772,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","68204","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","FROYENNES",2025,2025,37,37,"2025-09-08",45280.944444444445,"2025-09-12",45280.222222222219,"4d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction d’un PS pour supprimer les PN 8 et 10 - Réalisation des pieux",null,null,68204,"2023-04-19","Minor","1,2,3,4,5"]
[null,"Infrabel","72961","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,37,37,"2025-09-08",45280.996527777781,"2025-09-12",45280.1875,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 04.35.01 HKM\r\n\r\nL66 FLC-Y Kortrijk West niet inbegrepen\r\nFLC SP III-IV-V inbegrepen\r\nR5/R6 niet inbegrepen wegens WE TLO L73",null,null,72961,"2023-11-10","Minor","1,2,3,4,5"]
[null,"Infrabel","72935","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2025,2025,37,37,"2025-09-11",45280.378472222219,"2025-09-11",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,72935,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","67464","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,37,37,"2025-09-11",45280.395833333336,"2025-09-11",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nMise HS en P2",null,null,67464,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","50212","Erquelinnes - Montzen",">","HUY","ANDENNE",2025,2025,37,38,"2025-09-12",45280.979166666664,"2025-09-15",45280.229166666664,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA\r\n+ suppression des passages à niveau n°75 à 78 (construction des couloir sous-voies)",null,null,50212,"2023-09-01","Minor","5,6"]
[null,"Infrabel","66198","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2025,2025,37,37,"2025-09-13",45280.25,"2025-09-14",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z07.52 P4",null,null,66198,"2023-05-04","Medium","5,6"]
[null,"Infrabel","61864","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2025,2025,38,38,"2025-09-15",45280.958333333336,"2025-09-18",45280.208333333336,"3d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022",null,null,61864,"2022-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","55535","Namur - Antwerpen","< >","OTTIGNIES","LODELINSART",2025,2025,38,38,"2025-09-15",45280.958333333336,"2025-09-19",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Pi métalliques 52.015 et 52.215\r\nNuit pour soudures\r\n+ Maintenance Z3.51 P3",null,null,55535,"2023-10-17","Minor","1,2,3,4,5"]
[null,"Infrabel","55572","Athus - Meuse",">","HOUYET","BEAURAING",2025,2025,38,48,"2025-09-15",45280.333333333336,"2025-11-24",45280.25,"70d, 22:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Assainissement bk 16.200.\r\nDossier concertation octobre 2022",null,null,55572,"2023-03-22","High","1,2,3,4,5,6,7"]
[null,"Infrabel","68932","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,38,38,"2025-09-15",45280.979166666664,"2025-09-19",45280.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L53",null,null,68932,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","58108","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.NOORD DRIEHOEK AARSCHOT",2025,2025,38,38,"2025-09-15",45280.993055555555,"2025-09-19",45280.1875,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"vernieuwing OW 38 + 39 +43",null,null,58108,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","72579","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2025,2025,38,38,"2025-09-15",45280.5,"2025-09-15",45280.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,72579,"2023-11-03","Minor","1,2,3,4,5"]
[null,"Infrabel","54839","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,38,38,"2025-09-16",45280.958333333336,"2025-09-19",45280.208333333336,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022",null,null,54839,"2022-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","72577","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,38,38,"2025-09-16",45280.395833333336,"2025-09-16",45280.611111111109,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie et intervention avec S460 sur la voie contiguë + ATW",null,null,72577,"2023-11-03","Minor","1,2,3,4,5"]
[null,"Infrabel","56354","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2025,2025,38,39,"2025-09-19",45280.958333333336,"2025-09-22",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022",null,null,56354,"2023-06-27","Medium","5,6"]
[null,"Infrabel","56481","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2025,2025,38,39,"2025-09-19",45280.958333333336,"2025-09-22",45280.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Chape PI km 121,703",null,null,56481,"2023-12-19","Medium","5,6"]
[null,"Infrabel","50218","Erquelinnes - Montzen",">","HUY","JAVA",2025,2025,38,39,"2025-09-19",45280.979166666664,"2025-09-22",45280.229166666664,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Massification travaux OA - finitions\r\n+ Travaux caténaires Renouvellement chaine de suspension caténaires\r\n+ Maintenance",null,null,50218,"2023-05-16","Minor","5,6"]
[null,"Infrabel","65683","Erquelinnes - Montzen","< >","FROIDMONT","BRESSOUX",2025,2025,38,39,"2025-09-19",45280.9375,"2025-09-22",45280.229166666664,"2d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Z8.42\r\nEntretien mécanisé et manuel des AS du grill de Bressoux côté Froitmond\r\nEntretien tunnel\r\nCf Escalade Head Of nov/dec 2023",null,null,65683,"2023-12-04","Medium","5,6"]
[null,"Infrabel","69111","Lille - Antwerpen","< >","Y.ZWIJNDRECHT-FORT","SINT-NIKLAAS",2025,2025,38,39,"2025-09-20",45280.020833333336,"2025-09-22",45280.194444444445,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Verlenging buitendienststelling NW\r\nVernieuwing wisselonderdelen en sporen te Melsele.",null,null,69111,"2023-09-04","Medium","5,6"]
[null,"Infrabel","57970","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,38,40,"2025-09-21",45280.996527777781,"2025-09-29",45280.1875,"7d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek\r\n+ BVL Y Weerde - Y Prinsenhoek \r\n+ RTB L27B/1\r\nCf Escalade Head Of nov/dec 2023",null,null,57970,"2023-12-04","Medium","1,2,3,4,5,6,7"]
[null,"Infrabel","39577","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2025,2025,39,40,"2025-09-22",45280.9375,"2025-10-03",45280.173611111109,"11d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nCTL de nuit pour préparation et finition des travaux de ripage du PI.",null,null,39577,"2023-03-17","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","71667","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2025,2025,39,39,"2025-09-22",45280.947916666664,"2025-09-27",45280.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 05.32\r\nL58 Eeklo inbegrepen tot Gent Dampoort NIET inbegrepen",null,null,71667,"2023-11-28","Minor","1,2,3,4,5"]
[null,"Infrabel","66552","Lille - Antwerpen","< >","Y.MELSELE","SINT-NIKLAAS",2025,2025,39,39,"2025-09-23",45280.020833333336,"2025-09-27",45280.194444444445,"5d, 04:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"vernieuwing wissels 02BM en 03AM\r\n+\r\nP143: afschaffen overweg 17 L59 - Haasdonkbaan, Beveren fietstunnel\r\ngevallen van toepassing; 22847, 22848, 22846",null,null,66552,"2023-03-06","Minor","1,2,3,4,5"]
[null,"Infrabel","73091","Athus - Meuse",">","HALANZY","SIGNEULX",2025,2025,39,39,"2025-09-24",45280.333333333336,"2025-09-24",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie  B",null,null,73091,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","56349","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2025,2025,39,39,"2025-09-25",45280.958333333336,"2025-09-26",45280.958333333336,"1d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022",null,null,56349,"2023-06-29","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","73116","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,39,39,"2025-09-25",45280.333333333336,"2025-09-25",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73116,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","56355","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2025,2025,39,40,"2025-09-26",45280.958333333336,"2025-09-29",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022\r\n+ Visite de Voie L 130 Flawinne - Moustier VA/VB",null,null,56355,"2023-11-29","Medium","5,6"]
[null,"Infrabel","73117","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,39,39,"2025-09-26",45280.333333333336,"2025-09-26",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73117,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","69065","Namur - Antwerpen",">","AUVELAIS","MOUSTIER",2025,2025,39,39,"2025-09-27",45280.333333333336,"2025-09-27",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130",null,null,69065,"2023-10-12","Minor","5,6"]
[null,"Infrabel","68166","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,39,40,"2025-09-27",45280.986111111109,"2025-09-29",45280.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre",null,null,68166,"2023-10-12","Minor","5,6"]
[null,"Infrabel","68137","Namur - Antwerpen",">","AUVELAIS","MOUSTIER",2025,2025,39,39,"2025-09-28",45280.333333333336,"2025-09-28",45280.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130 Auvelais - Moustier VA/VB",null,null,68137,"2023-04-19","Minor","5,6"]
[null,"Infrabel","69515","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.OOST BERCHEM",2025,2025,39,39,"2025-09-28",45280.083333333336,"2025-09-28",45280.666666666664,"2d, 14:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug",null,null,69515,"2023-09-06","Minor","5,6"]
[null,"Infrabel","61861","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,40,40,"2025-09-29",45280.958333333336,"2025-10-04",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 5\r\nDossier de concertation validé en octobre 2022",null,null,61861,"2022-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","69113","Lille - Antwerpen","< >","Y.ZWIJNDRECHT-FORT","SINT-NIKLAAS",2025,2025,40,40,"2025-09-29",45280.020833333336,"2025-10-04",45280.194444444445,"6d, 04:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Verlenging buitendienststelling NW\r\nVernieuwing wisselonderdelen en sporen te Melsele. \r\nPeriodiciteit: 1 keer / jaar, TLO van 48u. \r\n+ weekend voor en na nachtprestaties voorzien.\r\nVoorkeur TLO week 40 (za 4 en zo 5/10) en nachtprestaties week 39 (ma/d",null,null,69113,"2023-09-04","Minor","1,2,3,4,5"]
[null,"Infrabel","58109","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.NOORD DRIEHOEK AARSCHOT",2025,2025,40,40,"2025-09-29",45280.993055555555,"2025-10-04",45280.1875,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"vernieuwing OW39 + 38 + 43",null,null,58109,"2023-12-04","Minor","1,2,3,4,5"]
[null,"Infrabel","71710","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,40,40,"2025-09-29",45280.319444444445,"2025-09-29",45280.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance",null,null,71710,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","73202","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,40,40,"2025-10-01",45280.385416666664,"2025-10-01",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73202,"2023-12-15","Minor","5,6"]
[null,"Infrabel","73032","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,40,40,"2025-10-02",45280.333333333336,"2025-10-02",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73032,"2023-11-10","Minor","1,2,3,4,5"]
[null,"Infrabel","56357","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2025,2025,40,41,"2025-10-03",45280.958333333336,"2025-10-06",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022",null,null,56357,"2023-06-21","Medium","5,6"]
[null,"Infrabel","56479","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2025,2025,40,41,"2025-10-03",45280.958333333336,"2025-10-06",45280.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Chape PI km 122.927",null,null,56479,"2023-12-19","Medium","5,6"]
[null,"Infrabel","66492","Namur - Antwerpen","< >","OTTIGNIES","WATERMAEL",2025,2025,40,41,"2025-10-03",45280.979166666664,"2025-10-06",45280.201388888891,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux de maintenance importante  Ottignies -Bakenpos + Maintenance ECFM  1000V + Boueux\r\n+ Travaux RER\r\nRER Livraison Kirow à Bakenbos",null,null,66492,"2023-05-25","Medium","5,6"]
[null,"Infrabel","73241","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2025,2025,40,40,"2025-10-03",45280.368055555555,"2025-10-03",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73241,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","72553","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,40,40,"2025-10-04",45280.3125,"2025-10-04",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72553,"2023-11-03","Minor","5,6"]
[null,"Infrabel","73237","Athus - Meuse",">","ARLON","Y.AUTELBAS",2025,2025,40,40,"2025-10-04",45280.361111111109,"2025-10-04",45280.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73237,"2023-11-15","Minor","5,6"]
[null,"Infrabel","71177","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2025,2025,40,40,"2025-10-05",45280.354166666664,"2025-10-05",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41\r\nRq 333 : propo +1 we",null,null,71177,"2023-10-26","Minor","5,6"]
[null,"Infrabel","61870","Namur - Antwerpen",">","FLAWINNE","MOUSTIER",2025,2025,41,42,"2025-10-06",45280.958333333336,"2025-10-18",45280.208333333336,"12d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage Flawinne - Moustier\r\nDossier de concertation validé en octobre 2022",null,null,61870,"2022-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","59281","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,41,41,"2025-10-06",45280.972222222219,"2025-10-11",45280.1875,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg\r\nTLO L50A/6 Gent Sint Pieters-",null,null,59281,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","67039","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2025,2025,41,43,"2025-10-06",45280.9375,"2025-10-24",45280.173611111109,"18d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction passage inférieur + couloir-sous-voie pour la suppression du PN4. \r\nCTL de nuit pour préparation et finition des travaux de ripage du PI.\r\n+ Maintenance Z2.54\r\n+ Maintenance Z7.54 P3HKM",null,null,67039,"2023-10-23","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","66523","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2025,2025,41,41,"2025-10-06",45280.944444444445,"2025-10-11",45280.173611111109,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.54\r\n+ Maintenance Z7.54 P3HKM",null,null,66523,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","62218","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,41,41,"2025-10-06",45280.923611111109,"2025-10-11",45280.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux préparatoires caténaire (poteaux + équiments)\r\n+ Chape PI km 122,927 - Finitions",null,null,62218,"2023-04-26","Minor","1,2,3,4,5"]
[null,"Infrabel","73373","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,41,41,"2025-10-08",45280.375,"2025-10-08",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73373,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","73384","Athus - Meuse",">","YVOIR","DINANT",2025,2025,41,41,"2025-10-09",45280.385416666664,"2025-10-09",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)\r\nRQ333: @Elise, quid concomitance SAVU Houyet - Beauraing ?",null,null,73384,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","67458","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,41,41,"2025-10-09",45280.395833333336,"2025-10-09",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nVisite diagnostique\r\nMise HS en P2",null,null,67458,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","73385","Athus - Meuse",">","DINANT","YVOIR",2025,2025,41,41,"2025-10-10",45280.385416666664,"2025-10-10",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)\r\nRQ333: @Elise, quid concomitance SAVU Houyet - Beauraing ?",null,null,73385,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","72453","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,41,42,"2025-10-11",45280.25,"2025-10-13",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"sporen 3+4+5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde\r\n\r\nChange Request nog op te maken/aan te vullen zoals besproken tijdens meeting met B-ST en B-PT.4\r\nCR 2025-",null,null,72453,"2023-10-31","Medium","5,6"]
[null,"Infrabel","58707","Namur - Antwerpen","< >","Y.HAREN-NORD","VILVOORDE",2025,2025,41,42,"2025-10-11",45280.000694444447,"2025-10-13",45280.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Werken Viaduct Vilvoorde (AWV)",null,null,58707,"2023-08-28","Medium","5,6"]
[null,"Infrabel","68043","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN-GRENS",2025,2025,41,41,"2025-10-12",45280.034722222219,"2025-10-12",45280.243055555555,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68043,"2023-04-14","Minor","5,6"]
[null,"Infrabel","71208","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2025,2025,41,41,"2025-10-12",45280.354166666664,"2025-10-12",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71208,"2023-10-26","Minor","5,6"]
[null,"Infrabel","69704","Namur - Antwerpen","< >","MECHELEN-DIJKSTRAAT","KONTICH-LINT",2025,2025,42,42,"2025-10-13",45280.958333333336,"2025-10-18",45280.201388888891,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK (samen met L27B): \r\n- min. 2 weken WN voor indienststelling (in maand ervoor)\r\n\r\n\r\n\r\nniet gecoordineerd",null,null,69704,"2023-09-06","Minor","1,2,3,4,5"]
[null,"Infrabel","59236","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,42,42,"2025-10-13",45280.979166666664,"2025-10-18",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels\r\nSP A L58/1 Y West Driehoek ",null,null,59236,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","65686","Lille - Antwerpen","< >","KORTRIJK","WAREGEM",2025,2025,42,42,"2025-10-14",45280.010416666664,"2025-10-17",45280.177083333336,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vervangen metalen spoordekken door betonnen bakbruggen",null,null,65686,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","67255","Athus - Meuse","< >","GEDINNE","BERTRIX",2025,2025,42,42,"2025-10-18",45280.958333333336,"2025-10-19",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires",null,null,67255,"2023-06-08","Medium","5,6"]
[null,"Infrabel","56480","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2025,2025,42,43,"2025-10-18",45280.958333333336,"2025-10-20",45280.173611111109,"2d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Chape PI km 122.927\r\nNuits finition + levée ART",null,null,56480,"2023-04-26","Minor","5,6"]
[null,"Infrabel","66393","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2025,2025,42,43,"2025-10-18",45280.027777777781,"2025-10-20",45280.166666666664,"2d, 03:20h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Bundel centraal Merelbeke\r\naansluiting nieuwe sporen 5-6-7-8 van bundel centraal + aansluiten aan L50E \r\n+ Dienst onderhoud werkt mee waar mogelijk\r\nCf Escalade Head Of nov/dec 2023",null,null,66393,"2023-12-11","Minor","5,6"]
[null,"Infrabel","64317","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,42,42,"2025-10-18",45280.986111111109,"2025-10-19",45280.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nMini CTL",null,null,64317,"2023-08-31","Medium","5,6"]
[null,"Infrabel","59355","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2025,2025,42,43,"2025-10-18",45280.25,"2025-10-20",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\n+\r\nInstandhouding Y Bethune",null,null,59355,"2023-12-15","Medium","5,6"]
[null,"Infrabel","68183","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2025,2025,42,42,"2025-10-19",45280.333333333336,"2025-10-19",45280.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Ottignies - Wavre VA/VB",null,null,68183,"2023-11-24","Minor","5,6"]
[null,"Infrabel","55541","Lille - Charleroi","< >","JURBISE","ATH",2025,2025,43,43,"2025-10-20",45280.958333333336,"2025-10-25",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux de construction d'un PI au droit du km 51.775 en vue de la suppression du PN5 \r\nNuits de finitions et enlèvement ART",null,null,55541,"2023-06-27","Minor","1,2,3,4,5"]
[null,"Infrabel","69936","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","ERQUELINNES",2025,2025,43,43,"2025-10-20",45280.875,"2025-10-25",45280.208333333336,"5d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nCHA25_0027989 - PMR Maubeuge",null,null,69936,"2023-09-11","Minor","1,2,3,4,5"]
[null,"Infrabel","65687","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2025,2025,43,43,"2025-10-21",45280.972222222219,"2025-10-24",45280.166666666664,"3d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vervangen metalen spoordekken door betonnen bakbruggen\r\n+\r\nOnderhoudswerken en kleine vernieuwingswerken\r\nDeinze SP I-II inbegrepen\r\n\r\nR5/R6 in WE TLO",null,null,65687,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","72936","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,43,43,"2025-10-21",45280.378472222219,"2025-10-21",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,72936,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","71082","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,43,43,"2025-10-24",45280.958333333336,"2025-10-25",45280.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,71082,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","73074","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,43,43,"2025-10-24",45280.333333333336,"2025-10-24",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73074,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","67276","Athus - Meuse","< >","GEDINNE","BERTRIX",2025,2025,43,43,"2025-10-25",45280.958333333336,"2025-10-26",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires",null,null,67276,"2023-06-08","Medium","5,6"]
[null,"Infrabel","53521","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2025,2025,43,43,"2025-10-25",45280.25,"2025-10-26",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10. 51   P4+",null,null,53521,"2023-08-31","Medium","5,6"]
[null,"Infrabel","72554","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,43,43,"2025-10-25",45280.3125,"2025-10-25",45280.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72554,"2023-11-03","Minor","5,6"]
[null,"Infrabel","68890","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,43,44,"2025-10-25",45280.000694444447,"2025-10-27",45280.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing BVL. (alternatief voor weekends februari)\r\nWeekends 7+8 ter vervanging van geannuleerde lange TLO (COLT 57997).",null,null,68890,"2023-09-13","Medium","5,6"]
[null,"Infrabel","71116","Namur - Antwerpen","< >","NAMUR","RONET",2025,2025,43,43,"2025-10-26",45280.003472222219,"2025-10-26",45280.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur (ZONE 6)\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,71116,"2023-11-06","Minor","5,6"]
[null,"Infrabel","53484","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2025,2025,44,44,"2025-10-27",45280.951388888891,"2025-10-31",45280.180555555555,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 en P3 HKV",null,null,53484,"2023-09-08","Minor","1,2,3,4,5"]
[null,"Infrabel","59305","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,44,44,"2025-10-27",45280.972222222219,"2025-11-01",45280.1875,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n+\r\nDienst onderhoud werkt mee\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg",null,null,59305,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","69937","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","ERQUELINNES",2025,2025,44,44,"2025-10-27",45280.875,"2025-11-01",45280.208333333336,"5d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nCHA25_0027989 - PMR Maubeuge",null,null,69937,"2023-09-11","Minor","1,2,3,4,5"]
[null,"Infrabel","66527","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2025,2025,44,44,"2025-10-27",45280.930555555555,"2025-11-01",45280.180555555555,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.54",null,null,66527,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","54953","Lille - Charleroi","< >","SOIGNIES","JURBISE",2025,2025,44,45,"2025-10-31",45280.993055555555,"2025-11-03",45280.1875,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de LRS entre Neufville et Jurbise  + Travaux OA Chape 39.680\r\nWE2/2",null,null,54953,"2023-10-12","Medium","5,6"]
[null,"Infrabel","67277","Athus - Meuse","< >","GEDINNE","BERTRIX",2025,2025,44,44,"2025-11-01",45280.958333333336,"2025-11-02",45280.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires",null,null,67277,"2023-06-08","Medium","5,6"]
[null,"Infrabel","69703","Namur - Antwerpen","< >","MECHELEN-DIJKSTRAAT","KONTICH-LINT",2025,2025,44,45,"2025-11-01",45280.25,"2025-11-03",45280.201388888891,"2d, 22:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK (samen met L27B): \r\n\r\n- 1x WE indienststelling: 25/10/2023 (samenwerkingen NIET mogelijk)\r\n\r\nvan L27 sein W-Q.5, VX-Q.5 tot L27 VX-N.5, V-N.5 en  L27B GX-J.5, F-J.5",null,null,69703,"2023-10-04","Medium","5,6"]
[null,"Infrabel","67470","Lille - Charleroi","< >","GHLIN","MONS",2025,2025,44,44,"2025-11-01",45280.993055555555,"2025-11-02",45280.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim",null,null,67470,"2023-10-23","Minor","5,6"]
[null,"Infrabel","70073","Erquelinnes - Montzen","< >","Y.VAL-BENOIT","FLEMALLE-HAUTE",2025,2025,45,45,"2025-11-03",45280.958333333336,"2025-11-08",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Z.19.41 - Maintenance P3\r\n+ Entretien et interventions diverses sur caténaire",null,null,70073,"2023-11-03","Minor","1,2,3,4,5"]
[null,"Infrabel","53495","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2025,2025,45,45,"2025-11-03",45280.951388888891,"2025-11-07",45280.180555555555,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 en P3 HKV",null,null,53495,"2023-09-11","Minor","1,2,3,4,5"]
[null,"Infrabel","66397","Lille - Charleroi","< >","JURBISE","ATH",2025,2025,45,45,"2025-11-03",45280.9375,"2025-11-07",45280.222222222219,"4d, 06:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 P3 HKM",null,null,66397,"2023-09-11","Minor","1,2,3,4,5"]
[null,"Infrabel","55796","Erquelinnes - Montzen",">","FLEMALLE-ANNEXE","SERAING",2025,2025,45,46,"2025-11-03",45280.25,"2025-11-14",45280.916666666664,"12d, 16:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"renouvellement de traverses",null,null,55796,"2023-10-26","High","1,2,3,4,5,6,7"]
[null,"Infrabel","72381","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2025,2025,45,45,"2025-11-03",45280.381944444445,"2025-11-03",45280.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41",null,null,72381,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","73244","Athus - Meuse",">","STOCKEM-NORD","ARLON",2025,2025,45,45,"2025-11-04",45280.361111111109,"2025-11-04",45280.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73244,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","73245","Athus - Meuse",">","HABAY","STOCKEM-NORD",2025,2025,45,45,"2025-11-05",45280.375,"2025-11-05",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73245,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","68781","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","WATERMAEL",2025,2025,45,46,"2025-11-07",45280.993055555555,"2025-11-10",45280.1875,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Plaatsen passerelle in station Etterbeek",null,null,68781,"2023-10-19","Medium","5,6"]
[null,"Infrabel","55797","Erquelinnes - Montzen","< >","FLEMALLE-ANNEXE","SERAING",2025,2025,45,46,"2025-11-08",45280.25,"2025-11-12",45280.208333333336,"4d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"renouvellement de traverses",null,null,55797,"2023-10-13","Medium","1,2,3,4,5,6,7"]
[null,"Infrabel","69465","Namur - Antwerpen","< >","Y.OTTERBEEK","Y.MUIZEN",2025,2025,45,46,"2025-11-08",45280.000694444447,"2025-11-10",45280.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK (samen met L27)\r\n\r\nnog geen coordinatie",null,null,69465,"2023-05-28","Medium","5,6"]
[null,"Infrabel","66506","Namur - Antwerpen","< >","OTTIGNIES","WAVRE",2025,2025,46,46,"2025-11-10",45280.965277777781,"2025-11-14",45280.215277777781,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien Maintenance",null,null,66506,"2023-11-06","Minor","1,2,3,4,5"]
[null,"Infrabel","67560","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2025,2025,46,46,"2025-11-10",45280.965277777781,"2025-11-15",45280.166666666664,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\n+\r\nInstandhouding Y Bethune",null,null,67560,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","59303","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,46,46,"2025-11-12",45280.972222222219,"2025-11-15",45280.1875,"3d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg\r\nTLO L50A/6 Gent Sint Pieters-",null,null,59303,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","67803","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,46,46,"2025-11-12",45280.020833333336,"2025-11-14",45280.1875,"3d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud \r\nFLC SP III-IV inbegrepen",null,null,67803,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","73249","Athus - Meuse",">","LAVAUX","MARBEHAN",2025,2025,46,46,"2025-11-12",45280.361111111109,"2025-11-12",45280.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73249,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","73208","Athus - Meuse",">","LUSTIN","JAMBES",2025,2025,46,46,"2025-11-13",45280.385416666664,"2025-11-13",45280.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73208,"2023-12-15","Minor","5,6"]
[null,"Infrabel","66611","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2025,2025,46,47,"2025-11-14",45280.958333333336,"2025-11-17",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellment du PS de Gqemblox bk 0,776",null,null,66611,"2023-10-13","Medium","5,6"]
[null,"Infrabel","73035","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2025,2025,46,46,"2025-11-14",45280.333333333336,"2025-11-14",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73035,"2023-11-10","Minor","1,2,3,4,5"]
[null,"Infrabel","73251","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2025,2025,46,46,"2025-11-14",45280.368055555555,"2025-11-14",45280.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73251,"2023-11-15","Minor","1,2,3,4,5"]
[null,"Infrabel","71184","Erquelinnes - Montzen",">","AMAY","ENGIS",2025,2025,46,46,"2025-11-15",45280.333333333336,"2025-11-15",45280.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71184,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","56516","Athus - Meuse",">","VIRTON","HALANZY",2025,2025,46,46,"2025-11-15",45280.25,"2025-11-15",45280.916666666664,"2d, 16:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage - Phase 2\r\nDossier de concertation validé en octobre 2022",null,null,56516,"2023-11-07","Minor","5,6"]
[null,"Infrabel","60159","Namur - Antwerpen","< >","Y.NOORD DRIEHOEK LEDEBERG","GENT-DAMPOORT",2025,2025,46,47,"2025-11-15",45280.25,"2025-11-17",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Instandhouding vertakking Noord-Driehoek Ledeberg",null,null,60159,"2023-09-01","Medium","5,6"]
[null,"Infrabel","73247","Athus - Meuse",">","ARLON","Y.AUTELBAS",2025,2025,46,46,"2025-11-15",45280.361111111109,"2025-11-15",45280.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73247,"2023-11-15","Minor","5,6"]
[null,"Infrabel","68808","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,46,46,"2025-11-16",45280.333333333336,"2025-11-16",45280.659722222219,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie B Ottignies - Gembloux (extension Rhisnes SAS)",null,null,68808,"2023-06-27","Minor","5,6"]
[null,"Infrabel","71185","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2025,2025,46,46,"2025-11-16",45280.354166666664,"2025-11-16",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,71185,"2023-12-15","Minor","5,6"]
[null,"Infrabel","72581","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2025,2025,47,47,"2025-11-17",45280.333333333336,"2025-11-17",45280.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,72581,"2023-11-03","Minor","1,2,3,4,5"]
[null,"Infrabel","65784","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2025,2025,47,47,"2025-11-17",45280.951388888891,"2025-11-22",45280.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.51\r\nP3 HKV",null,null,65784,"2023-10-10","Minor","1,2,3,4,5"]
[null,"Infrabel","66517","Lille - Charleroi","< >","ATH","TOURNAI",2025,2025,47,47,"2025-11-17",45280.940972222219,"2025-11-21",45280.1875,"4d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.54",null,null,66517,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","73374","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,47,47,"2025-11-18",45280.375,"2025-11-18",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73374,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","73375","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,47,47,"2025-11-19",45280.375,"2025-11-19",45280.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73375,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","56505","Athus - Meuse",">","Y.AUBANGE","HALANZY",2025,2025,47,48,"2025-11-20",45280.25,"2025-11-26",45280.25,"6d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage - Phase 3\r\nDossier de concertation validé en octobre 2022",null,null,56505,"2022-11-12","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","71083","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,47,47,"2025-11-21",45280.958333333336,"2025-11-22",45280.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,71083,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","66396","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2025,2025,47,48,"2025-11-22",45280.027777777781,"2025-11-24",45280.166666666664,"2d, 03:20h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Bundel centraal Merelbeke\r\naansluiting nieuwe sporen 5-6-7-8 van bundel centraal + aansluiten aan L50E\r\n+ Dienst onderhoud werkt mee waar mogelijk\r\nCf Escalade Head Of nov/dec 2023",null,null,66396,"2023-12-11","Minor","5,6"]
[null,"Infrabel","66572","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2025,2025,47,48,"2025-11-22",45280.013888888891,"2025-11-24",45280.166666666664,"2d, 03:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen perron De Pinte - weekend 3/3\r\n+\r\nMassificatie tss De Pinte en Gent\r\n+\r\nOnderhoud Rooster De PInte\r\n+\r\nOnderhoud rooster Gent \r\n\r\n* Gent Sint Pieters SP III-IV-V inbegrepen",null,null,66572,"2023-10-16","Medium","5,6"]
[null,"Infrabel","69480","Namur - Antwerpen","< >","Y.HOLLAND","LUCHTBAL-ROOSTER S",2025,2025,47,47,"2025-11-22",45280.25,"2025-11-23",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Lantis Oosterweelverbinding RO",null,null,69480,"2023-09-06","Medium","5,6"]
[null,"Infrabel","71228","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2025,2025,47,47,"2025-11-22",45280.354166666664,"2025-11-22",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71228,"2023-10-26","Minor","5,6"]
[null,"Infrabel","72566","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,47,47,"2025-11-23",45280.3125,"2025-11-23",45280.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72566,"2023-11-03","Minor","5,6"]
[null,"Infrabel","71229","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2025,2025,47,47,"2025-11-23",45280.354166666664,"2025-11-23",45280.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71229,"2023-10-26","Minor","5,6"]
[null,"Infrabel","72924","Athus - Meuse",">","BERTRIX","STRAIMONT",2025,2025,48,48,"2025-11-24",45280.333333333336,"2025-11-24",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,72924,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","65801","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2025,2025,48,48,"2025-11-24",45280.965277777781,"2025-11-29",45280.208333333336,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.51 P3 HKV",null,null,65801,"2023-10-16","Minor","1,2,3,4,5"]
[null,"Infrabel","68049","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,48,48,"2025-11-24",45280.034722222219,"2025-11-24",45280.201388888891,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68049,"2023-04-25","Minor","5,6"]
[null,"Infrabel","53517","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,48,48,"2025-11-24",45280.909722222219,"2025-11-29",45280.229166666664,"5d, 07:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z8.52 P3 HKV",null,null,53517,"2023-10-30","Minor","1,2,3,4,5"]
[null,"Infrabel","67808","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,48,48,"2025-11-25",45280.020833333336,"2025-11-29",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud \r\nFLC SP III-IV inbegrepen",null,null,67808,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","53232","Lille - Charleroi",">","Y.NORD","CHARLEROI-CENTRAL",2025,2025,48,49,"2025-11-28",45280.979166666664,"2025-12-01",45280.1875,"2d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Grill Charleroi-Sud - Phase 1.3",null,null,53232,"2023-12-13","Minor","5,6"]
[null,"Infrabel","73387","Athus - Meuse",">","DINANT","YVOIR",2025,2025,48,48,"2025-11-28",45280.385416666664,"2025-11-28",45280.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73387,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","59241","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2025,2025,48,49,"2025-11-29",45280.020833333336,"2025-12-01",45280.1875,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters stap 33 : Indienststelling perronsporen IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. West Driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters -Y West Driehoek Ledeberg\r\nSP A L58/1 Y West Driehoek Le",null,null,59241,"2023-12-15","Medium","5,6"]
[null,"Infrabel","52451","Athus - Meuse",">","HAVERSIN","MARLOIE",2025,2025,48,48,"2025-11-30",45280.333333333336,"2025-11-30",45280.958333333336,"2d, 15:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Mise en service CV Jade Haversin - Marloie.\r\nRq333: à intégrer lors de la CTL WE 11, 48 ou 49 Ciney/Haversin",null,null,52451,"2023-12-15","Minor","5,6"]
[null,"Infrabel","68169","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,49,49,"2025-12-01",45280.958333333336,"2025-12-05",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\nFinitions",null,null,68169,"2023-10-12","Minor","1,2,3,4,5"]
[null,"Infrabel","67459","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,49,49,"2025-12-04",45280.395833333336,"2025-12-04",45280.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nVisite diagnostique\r\nMise HS en P2",null,null,67459,"2023-11-20","Minor","1,2,3,4,5"]
[null,"Infrabel","59459","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,49,50,"2025-12-05",45280.979166666664,"2025-12-08",45280.201388888891,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER – suppression CV50 Ottignies suite suppression PN45 et poussage du CSV",null,null,59459,"2023-04-24","Medium","5,6"]
[null,"Infrabel","69357","Namur - Antwerpen","< >","KONTICH-LINT","MECHELEN-NEKKERSPOEL",2025,2025,49,50,"2025-12-06",45280.25,"2025-12-08",45280.201388888891,"2d, 22:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel\r\n+\r\nVernieuwing spoorstaven tussen Y Liersesteenweg en Y Krijgsbaan.",null,null,69357,"2023-09-26","Medium","5,6"]
[null,"Infrabel","74105","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2025,2025,49,49,"2025-12-06",45280.996527777781,"2025-12-07",45280.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B",null,null,74105,"2023-12-11","Minor","5,6"]
[null,"Infrabel","71762","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,50,50,"2025-12-08",45280.333333333336,"2025-12-08",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles",null,null,71762,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","65802","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2025,2025,50,50,"2025-12-08",45280.965277777781,"2025-12-13",45280.208333333336,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.51 P3",null,null,65802,"2023-10-05","Minor","1,2,3,4,5"]
[null,"Infrabel","72938","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,50,50,"2025-12-09",45280.378472222219,"2025-12-09",45280.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,72938,"2023-11-09","Minor","1,2,3,4,5"]
[null,"Infrabel","73076","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,50,50,"2025-12-12",45280.333333333336,"2025-12-12",45280.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B\r\nRQ333: +1 semaine ok ?",null,null,73076,"2023-11-13","Minor","1,2,3,4,5"]
[null,"Infrabel","47375","Athus - Meuse",">","HAVERSIN","MARLOIE",2025,2026,51,50,"2025-12-15",45280.208333333336,"2026-12-11",45280.927083333336,"362d, 17:15h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3:\r\nTronçon Haversin Marloie\r\nDossier de concertation validé en ocotbre 2023\r\nSAVU de jour en continu et CTL de nuit en semaine\r\nSIRU à réaliser",null,null,47375,"2023-12-15","High","1,2,3,4,5,6,7"]
[null,"Infrabel","59260","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,51,51,"2025-12-15",45280.972222222219,"2025-12-19",45280.1875,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg\r\nTLO L50A/6 Gent Sint Pieters-",null,null,59260,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","62055","Namur - Antwerpen",">","GEMBLOUX","OTTIGNIES",2026,2026,2,51,"2026-01-05",45280.958333333336,"2026-12-18",45280.166666666664,"347d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Modernisation AXE 3 - travaux préparatoires portiques caténaires",null,null,62055,"2023-09-12","Minor","1,2,3,4,5"]
[null,"Infrabel","68404","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,3,3,"2026-01-12",45280.979166666664,"2026-01-17",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-486668\r\nMasterplan Gent Sint Pieters: Stap 34+35\r\nAfbraak sporen I+II+III\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters en Y. West Driehoek Led",null,null,68404,"2023-12-18","Minor","1,2,3,4,5"]
[null,"Infrabel","66278","Lille - Antwerpen","< >","KORTRIJK","KORTRIJK-RINGLAAN",2026,2026,3,3,"2026-01-12",45280.996527777781,"2026-01-17",45280.197916666664,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"KIROW - Vernieuwing Y.Bethune\r\n\r\nBD\r\nL75C SP A+B\r\nL75 SP A+B\r\nL66/1\r\n\r\nGevallen\r\n29950+29936+29935+29938+29928+29929+29947+29932+29948+29934+29958",null,null,66278,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","70251","Lille - Charleroi","< >","CHARLEROI-CENTRAL","Y.NORD",2026,2026,3,3,"2026-01-17",45280.9375,"2026-01-18",45280.229166666664,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Grill Charleroi-Sud - Phase 1.0.1\r\nAcheminement matériel (préalable à la phase 1.0.2 à 1.0.6\r\nDossier de concertation validé en octobre 2023",null,null,70251,"2023-10-23","Minor","5,6"]
[null,"Infrabel","67506","Lille - Antwerpen","< >","KORTRIJK","KORTRIJK-RINGLAAN",2026,2026,4,4,"2026-01-19",45280.996527777781,"2026-01-24",45280.197916666664,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereiding - Vernieuwing Y.Bethune\r\n\r\nBD\r\nL75C SP A+B\r\nL75 SP A+B\r\nL66/1\r\n\r\nGevallen\r\n29950+29936+29935+29938+29928+29929+29947+29932+29948+29934+29958",null,null,67506,"2023-11-29","Minor","1,2,3,4,5"]
[null,"Infrabel","74395","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN",2026,2026,4,5,"2026-01-24",45280.25,"2026-01-26",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Masterplan Mechelen\r\nVervangen oplegtoestellen",null,null,74395,"2023-12-19","Medium","5,6"]
[null,"Infrabel","68406","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,5,5,"2026-01-26",45280.979166666664,"2026-01-31",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 34+35\r\nAfbraak sporen I+II+III\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg niet",null,null,68406,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","70922","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,5,5,"2026-01-26",45280.923611111109,"2026-01-31",45280.1875,"5d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage de ballast - C75",null,null,70922,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","68443","Lille - ZeeBrugge","< >","BRUGGE","Y.BLAUWE TOREN",2026,2026,5,6,"2026-01-31",45280.041666666664,"2026-02-02",45280.166666666664,"2d, 03:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"ONB gistelsesteenweg AP 93.863 (L50A+L51) +/- thv Brugge Sint Pieters\r\nNieuw dienstpad-Betonherstellingen-Vernieuwing waterdichte rok\r\n+\r\nVervangen naakte feeders in geïsoleerde feeders op L50A (Ts 107+108) \r\n+\r\nMassificatie onderhoud op betrokken lijne",null,null,68443,"2023-12-15","Medium","5,6"]
[null,"Infrabel","68407","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,6,6,"2026-02-02",45280.979166666664,"2026-02-07",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 34+35\r\nAfbraak sporen I+II+III\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg niet",null,null,68407,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","64191","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,6,6,"2026-02-02",45280.923611111109,"2026-02-07",45280.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux SI + Voie + Caténaire",null,null,64191,"2023-12-18","Minor","1,2,3,4,5"]
[null,"Infrabel","66708","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,6,7,"2026-02-07",45280.166666666664,"2026-02-09",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC)",null,null,66708,"2023-12-13","Medium","5,6"]
[null,"Infrabel","55843","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,7,7,"2026-02-09",45280.958333333336,"2026-02-14",45280.239583333336,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\nPhase 1 - Nuits de préparation à la démolition\r\nPhase 1.1 - travaux au niveau de la 1ère travée située au-dessus des L75 VA+L75 VB et",null,null,55843,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","66700","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,7,7,"2026-02-09",45280.986111111109,"2026-02-14",45280.1875,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"\"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC):",null,null,66700,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","70913","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,7,7,"2026-02-09",45280.923611111109,"2026-02-14",45280.1875,"5d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage de ballast - C75\r\nDossier de concertation",null,null,70913,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","63086","Athus - Meuse","< >","CINEY","MARLOIE",2026,2026,7,8,"2026-02-13",45280.927083333336,"2026-02-16",45280.208333333336,"2d, 06:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS de Haversin - BK 102.161",null,null,63086,"2023-10-20","Medium","5,6"]
[null,"Infrabel","66709","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,7,8,"2026-02-14",45280.166666666664,"2026-02-16",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC)",null,null,66709,"2023-12-13","Medium","5,6"]
[null,"Infrabel","68409","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,8,8,"2026-02-16",45280.979166666664,"2026-02-21",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 34+35\r\nAfbraak sporen I+II+III\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg niet",null,null,68409,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","63898","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","Y.NORD",2026,2026,8,8,"2026-02-18",45280.958333333336,"2026-02-21",45280.208333333336,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi-Central- Phase 2.1\r\nCoupure Type 9\r\nDossier de concertation validé en octobre 2023\r\nAvec id 65581 nuit 18^19/02 et id 65582 nuit 19^20/02",null,null,63898,"2023-12-18","Minor","1,2,3,4,5"]
[null,"Infrabel","65766","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,8,11,"2026-02-20",45280.9375,"2026-03-09",45280.1875,"16d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes\r\nDossier de concertation validé en octobre 2023",null,null,65766,"2023-10-18","High","1,2,3,4,5,6,7"]
[null,"Infrabel","66340","Namur - Antwerpen","< >","Y.SINT-MARIABURG","ESSEN",2026,2026,8,9,"2026-02-21",45280.25,"2026-02-23",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Kleine vernieuwingen",null,null,66340,"2023-10-19","Medium","5,6"]
[null,"Infrabel","68410","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,9,9,"2026-02-23",45280.979166666664,"2026-02-28",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 34+35\r\nAfbraak sporen I+II+III\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg niet",null,null,68410,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","55846","Lille - Charleroi","< >","MOUSCRON","HERSEAUX",2026,2026,9,10,"2026-02-24",45280.9375,"2026-03-02",45280.173611111109,"5d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\nPhase 2 - CTL en continu pour la démolition des tabliers et de la pile centrale\r\nPhase 2.2 - travaux au niveau de la 2è travée",null,null,55846,"2023-10-03","Medium","1,2,3,4,5,6,7"]
[null,"Infrabel","63918","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,9,10,"2026-02-27",45280.923611111109,"2026-03-02",45280.1875,"2d, 06:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Criblage de ballast - C75\r\nDossier de concertation",null,null,63918,"2023-10-03","Medium","5,6"]
[null,"Infrabel","63868","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2026,2026,10,10,"2026-03-02",45280.958333333336,"2026-03-07",45280.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses entre Fleurus et Tilly\r\n7h amplitude",null,null,63868,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","55866","Lille - Antwerpen",">","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,10,10,"2026-03-02",45280.25,"2026-03-06",45280.666666666664,"5d, 10:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nDossier de concertation\r\n\r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pou",null,null,55866,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","68422","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,10,10,"2026-03-02",45280.993055555555,"2026-03-07",45280.180555555555,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y Kortrijk West\r\nLossen Kirow",null,null,68422,"2023-07-14","Minor","1,2,3,4,5"]
[null,"Infrabel","63924","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,10,11,"2026-03-06",45280.923611111109,"2026-03-09",45280.1875,"2d, 06:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Criblage de ballast - C75\r\nDossier de concertation",null,null,63924,"2023-10-03","Medium","5,6"]
[null,"Infrabel","66335","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.HOLLAND",2026,2026,10,11,"2026-03-07",45280.166666666664,"2026-03-09",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Oosterweel\r\noverpakken bruggen en impact bemaling",null,null,66335,"2023-10-19","Medium","5,6"]
[null,"Infrabel","66341","Namur - Antwerpen","< >","Y.SINT-MARIABURG","ESSEN",2026,2026,10,11,"2026-03-08",45280.003472222219,"2026-03-09",45280.166666666664,"2d, 03:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Kleine vernieuwingen",null,null,66341,"2023-11-28","Minor","5,6"]
[null,"Infrabel","72264","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2026,2026,11,11,"2026-03-09",45280.958333333336,"2026-03-14",45280.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses entre Fleurus et Tilly",null,null,72264,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","63093","Athus - Meuse","< >","GENDRON-CELLES","BEAURAING",2026,2026,11,13,"2026-03-13",45280.958333333336,"2026-03-23",45280.208333333336,"9d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification :\r\nO.A. : Pistes, sécurisation de parois rocheuses et de talus + étanchéïté de chape de pont \r\nService Tracks: Assainissement VA BK 17000 à 17500 et 19900 à 20300. Par camion. \r\nECFM: Modernisation de l'éclairage du tunnel d'Ardenne (Houye",null,null,63093,"2023-10-09","High","1,2,3,4,5,6,7"]
[null,"Infrabel","72265","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2026,2026,12,12,"2026-03-16",45280.958333333336,"2026-03-21",45280.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses entre Fleurus et Tilly",null,null,72265,"2023-12-14","Minor","1,2,3,4,5"]
[null,"Infrabel","61878","Athus - Meuse",">","Y.AUBANGE","HALANZY",2026,2026,12,13,"2026-03-16",45280.25,"2026-03-29",45280.666666666664,"14d, 10:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage - Phase 5\r\nVoir Dossier de concertation 2025",null,null,61878,"2023-10-19","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","64295","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,12,13,"2026-03-20",45280.958333333336,"2026-03-23",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre \r\nRenouvellement des voies III - IV  - V en gare de Luttre\r\nAménagement Aw L117\r\nDossier de concertation validé en octobre 2023",null,null,64295,"2023-10-19","Medium","5,6"]
[null,"Infrabel","63919","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,12,13,"2026-03-20",45280.923611111109,"2026-03-23",45280.1875,"2d, 06:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Criblage de ballast - C75\r\nDossier de concertation",null,null,63919,"2023-10-03","Medium","5,6"]
[null,"Infrabel","67515","Lille - Antwerpen","< >","KORTRIJK","KORTRIJK-RINGLAAN",2026,2026,13,13,"2026-03-23",45280.996527777781,"2026-03-28",45280.197916666664,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Afwerking - Vernieuwing Y.Bethune\r\n\r\nBD\r\nL75C SP A+B\r\nL75 SP A+B\r\nL66/1\r\n\r\nGevallen\r\n29950+29936+29935+29938+29928+29929+29947+29932+29948+29934+29958",null,null,67515,"2023-04-03","Minor","1,2,3,4,5"]
[null,"Infrabel","64296","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,13,14,"2026-03-27",45280.958333333336,"2026-03-30",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre \r\nRenouvellement des voies III - IV  - V en gare de Luttre\r\nAménagement Aw L117\r\nDossier de concertation validé en octobre 2023",null,null,64296,"2023-10-19","Medium","5,6"]
[null,"Infrabel","63095","Athus - Meuse","< >","GENDRON-CELLES","BEAURAING",2026,2026,13,14,"2026-03-27",45280.958333333336,"2026-03-30",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification :\r\nO.A. : Pistes, sécurisation de parois rocheuses et de talus + étanchéïté de chape de pont \r\nService Tracks: Assainissement VA BK 17000 à 17500 et 19900 à 20300: Bourrage de révision et contraintes\r\nECFM: Modernisation de l'éclairage du ",null,null,63095,"2023-10-09","Medium","5,6"]
[null,"Infrabel","67689","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,13,14,"2026-03-27",45280.993055555555,"2026-03-30",45280.194444444445,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,67689,"2023-12-19","Medium","5,6"]
[null,"Infrabel","61842","Lille - Antwerpen",">","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,14,14,"2026-03-30",45280.25,"2026-04-03",45280.666666666664,"5d, 10:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nDossier de concertation\r\n\r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pou",null,null,61842,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","67701","Erquelinnes - Montzen",">","HUY","STATTE",2026,2026,14,19,"2026-03-30",45280.194444444445,"2026-05-04",45280.194444444445,"35d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,67701,"2023-12-19","High","1,2,3,4,5,6,7"]
[null,"Infrabel","63962","Lille - Charleroi","< >","JURBISE","Y.LENS",2026,2026,14,17,"2026-04-03",45280.9375,"2026-04-20",45280.208333333336,"16d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Chantier gare de Jurbise  - Renouvellement traverses-ballast des voies 3, 4 et 5\r\nPhase 1\r\nDossier de concertation validé en octobre 2023",null,null,63962,"2023-12-19","High","1,2,3,4,5,6,7"]
[null,"Infrabel","63085","Athus - Meuse","< >","CINEY","MARLOIE",2026,2026,14,15,"2026-04-03",45280.927083333336,"2026-04-07",45280.208333333336,"3d, 06:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3:\r\nsuppression des PN de Chapois et Leignon + PS d'Haversin\r\nDossier de concertation validé en octobre 2023",null,null,63085,"2023-10-18","Medium","5,6"]
[null,"Infrabel","64298","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,15,16,"2026-04-10",45280.958333333336,"2026-04-13",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre \r\nRenouvellement des voies III - IV  - V en gare de Luttre\r\nAménagement Aw L117\r\nDossier de concertation validé en ocotbre 2023",null,null,64298,"2023-10-19","Medium","5,6"]
[null,"Infrabel","65758","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,15,16,"2026-04-10",45280.9375,"2026-04-13",45280.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes",null,null,65758,"2023-12-19","Medium","5,6"]
[null,"Infrabel","65243","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","FROYENNES",2026,2026,16,16,"2026-04-13",45280.944444444445,"2026-04-17",45280.215277777781,"4d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction d’un PS pour supprimer les PN 8 et 10 - Décoffrage + pose garde-corps",null,null,65243,"2023-12-19","Minor","1,2,3,4,5"]
[null,"Infrabel","72214","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,16,16,"2026-04-13",45280.354166666664,"2026-04-17",45280.645833333336,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre \r\nRenouvellement des voies III - IV  - V en gare de Luttre\r\nAménagement Aw L117\r\nDossier de concertation validé en octobre 2023",null,null,72214,"2023-10-19","Minor","1,2,3,4,5"]
[null,"Infrabel","63306","Athus - Meuse","< >","BOIS D'AUSSE","NAMUR",2026,2026,16,16,"2026-04-18",45280.25,"2026-04-19",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE1\r\nDossier de concertation validé en octobre 2023",null,null,63306,"2023-10-16","Medium","5,6"]
[null,"Infrabel","72232","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,17,17,"2026-04-20",45280.958333333336,"2026-04-24",45280.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre \r\nRenouvellement des voies III - IV  - V en gare de Luttre\r\nAménagement Aw L117\r\nDossier de concertation validé en octobre 2023",null,null,72232,"2023-10-19","Minor","1,2,3,4,5"]
[null,"Infrabel","72215","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,17,17,"2026-04-20",45280.354166666664,"2026-04-24",45280.645833333336,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre \r\nRenouvellement des voies III - IV  - V en gare de Luttre\r\nAménagement Aw L117\r\nDossier de concertation validé en octobre 2023",null,null,72215,"2023-10-19","Minor","1,2,3,4,5"]
[null,"Infrabel","70255","Lille - Charleroi",">","Y.LA SAMBRE","CHARLEROI-CENTRAL",2026,2026,17,18,"2026-04-24",45280.958333333336,"2026-04-27",45280.166666666664,"2d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Grill Charleroi-Sud - Phase 1.0.2\r\nDossier de concertation validé en octobre 2023",null,null,70255,"2023-12-18","Minor","5,6"]
[null,"Infrabel","63964","Lille - Charleroi","< >","JURBISE","Y.LENS",2026,2026,17,18,"2026-04-24",45280.9375,"2026-04-27",45280.208333333336,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Chantier gare de Jurbise  - Renouvellement traverses-ballast des voies 3, 4 et 5\r\nPhase 2\r\nDossier de concertation validé en octobre 2023",null,null,63964,"2023-12-19","Medium","5,6"]
[null,"Infrabel","71535","Lille - Charleroi",">","MONS","NEUFVILLES",2026,2026,17,18,"2026-04-24",45280.9375,"2026-04-27",45280.208333333336,"3d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Chantier gare de Jurbise  - Renouvellement traverses-ballast des voies 3, 4 et 5\r\nPhase 2\r\nDossier de concertation validé en octobre 2023",null,null,71535,"2023-12-19","Minor","5,6"]
[null,"Infrabel","66379","Namur - Antwerpen","< >","Y.HOLLAND","ANTWERPEN-NOORDERDOKKEN",2026,2026,18,18,"2026-04-27",45280.958333333336,"2026-05-02",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"\"Werken SIG (schets A22-SIG 1): \r\nOnderdelen vernieuwen wissels Y Antw. Luchtbal: uitbreiding op CBP van L25Y \r\nPeriodiciteit: minium 4 keer 1 week/jaar; voorkeur  week 8 (van ma/di 17/18-02 t.e.m. vr/za 21/22-02) en week 18 (van ma/di 28/29-04 t.e.m. v",null,null,66379,"2023-05-26","Minor","1,2,3,4,5"]
[null,"Infrabel","63081","Namur - Antwerpen","< >","MOUSTIER","JEMEPPE-SUR-SAMBRE",2026,2026,18,19,"2026-04-30",45280.958333333336,"2026-05-04",45280.208333333336,"3d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Démolition du PS 76.318",null,null,63081,"2023-05-17","Medium","5,6"]
[null,"Infrabel","64302","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,18,18,"2026-05-01",45280.875,"2026-05-02",45280.25,"1d, 09:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre - Phase 6\r\nRenouvellement des Aw L124\r\nExtension nuit pour dépose CAT 40/9\r\nDossier de concertation validé en octobre 2023",null,null,64302,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","61844","Lille - Antwerpen",">","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,19,19,"2026-05-04",45280.25,"2026-05-08",45280.666666666664,"5d, 10:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nDossier de concertation\r\n\r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pou",null,null,61844,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","64192","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,19,22,"2026-05-04",45280.923611111109,"2026-05-30",45280.173611111109,"26d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux Caténaire",null,null,64192,"2023-04-11","Minor","1,2,3,4,5"]
[null,"Infrabel","67699","Erquelinnes - Montzen",">","HUY","STATTE",2026,2026,19,21,"2026-05-04",45280.201388888891,"2026-05-18",45280.194444444445,"14d, 23:50h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,67699,"2023-12-19","High","1,2,3,4,5,6,7"]
[null,"Infrabel","64303","Lille - Charleroi",">","MANAGE","LUTTRE",2026,2026,19,20,"2026-05-08",45280.958333333336,"2026-05-11",45280.208333333336,"3d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre - Phase 6\r\nRenouvellement des Aw L124\r\nExtension nuit pour V et Caténaire\r\nDossier de concertation validé en octobre 2023",null,null,64303,"2023-10-20","Minor","5,6"]
[null,"Infrabel","63942","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2026,2026,19,20,"2026-05-08",45280.965277777781,"2026-05-11",45280.208333333336,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement LRS\r\nCourtrai - Mouscron",null,null,63942,"2023-12-05","Medium","5,6"]
[null,"Infrabel","66277","Lille - Antwerpen","< >","KORTRIJK","FRONT. FLANDRE-WALLONIE L75",2026,2026,19,20,"2026-05-08",45280.996527777781,"2026-05-11",45280.197916666664,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud",null,null,66277,"2023-05-22","Medium","5,6"]
[null,"Infrabel","72388","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,19,20,"2026-05-08",45280.993055555555,"2026-05-11",45280.194444444445,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,72388,"2023-10-26","Medium","5,6"]
[null,"Infrabel","66961","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2026,2026,19,21,"2026-05-09",45280.166666666664,"2026-05-18",45280.166666666664,"9d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vervolg werken 2023: vervangen houtstukken op Jan Bogaertsbrug (ander spoor) + vernieuwen spoor op brug over Zenne + sanering en vernieuwing spoor in een zone aan Jan Bogaertsbrug\r\n\r\nOverlegdossier gevalideerd in oktober 2023",null,null,66961,"2023-10-13","High","1,2,3,4,5,6,7"]
[null,"Infrabel","61830","Lille - Charleroi","< >","CHARLEROI-CENTRAL","MARCHIENNE-AU-PONT",2026,2026,20,20,"2026-05-11",45280.9375,"2026-05-12",45280.229166666664,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Livraison AS Charleroi via grue KIROW\r\nLivraison 35G + 44G le long de la VB L124A\r\nDossier de concertation validé en octobre 2023",null,null,61830,"2023-12-19","Minor","1,2,3,4,5"]
[null,"Infrabel","63940","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2026,2026,20,20,"2026-05-11",45280.965277777781,"2026-05-16",45280.208333333336,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Courtrai - Mouscron LRS",null,null,63940,"2023-12-05","Minor","1,2,3,4,5"]
[null,"Infrabel","68423","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,20,20,"2026-05-11",45280.993055555555,"2026-05-16",45280.180555555555,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y Kortrijk West\r\nvoorbereidende werken + Kirow",null,null,68423,"2023-07-14","Minor","1,2,3,4,5"]
[null,"Infrabel","64304","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,20,20,"2026-05-11",45280.354166666664,"2026-05-15",45280.645833333336,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre - Phase 7\r\nDossier de concertation validé en octobre 2023",null,null,64304,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","53995","Athus - Meuse","< >","CINEY","MARLOIE",2026,2026,20,21,"2026-05-13",45280.927083333336,"2026-05-18",45280.208333333336,"4d, 06:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3:\r\nPI de Chapois\r\ndéplacement de la coupure initiale du 22 au 26-5-26 suite travaux voies ce we-là sur Namur Bois d'Ausse\r\nBesoin absolu d'un we de minimum 60 heures.\r\nRq 333 : possible fin R7 17h?",null,null,53995,"2023-10-25","Medium","5,6"]
[null,"Infrabel","63070","Athus - Meuse","< >","YVOIR","Y.NEFFE",2026,2026,20,21,"2026-05-13",45280.993055555555,"2026-05-18",45280.180555555555,"4d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Poussage du P.I. de Neffe , d'un couloir sous voie à Dinant, renouvellement de chapes d'étanchéité et suppression du PN 116",null,null,63070,"2023-10-20","Medium","1,2,3,4,5,6,7"]
[null,"Infrabel","64171","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2026,2026,20,21,"2026-05-15",45280.979166666664,"2026-05-18",45280.180555555555,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA\r\nTravaux de réfection en face inférieur du PS km 87.100\r\nRq 333 : Propo WE 20",null,null,64171,"2023-10-20","Medium","5,6"]
[null,"Infrabel","63340","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2026,2026,20,21,"2026-05-15",45280.25,"2026-05-18",45280.916666666664,"4d, 16:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement  P93\r\nWE1",null,null,63340,"2023-10-19","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","64305","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,20,20,"2026-05-16",45280.958333333336,"2026-05-17",45280.583333333336,"1d, 15:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement gare de Luttre",null,null,64305,"2023-05-10","Medium","5,6"]
[null,"Infrabel","63343","Athus - Meuse","< >","STRAIMONT","FLORENVILLE",2026,2026,20,20,"2026-05-16",45280.25,"2026-05-17",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement P93 \r\nWE 1",null,null,63343,"2023-10-19","Medium","5,6"]
[null,"Infrabel","66956","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2026,2026,21,21,"2026-05-18",45280.958333333336,"2026-05-23",45280.166666666664,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vervolg werken 2023: vervangen houtstukken op Jan Bogaertsbrug (ander spoor) + vernieuwen spoor op brug over Zenne + sanering en vernieuwing spoor in een zone aan Jan Bogaertbrug\r\n\r\nOverlegdossier gevalideerd in oktober 2023",null,null,66956,"2023-10-09","Minor","1,2,3,4,5"]
[null,"Infrabel","68960","Namur - Antwerpen",">","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,21,21,"2026-05-18",45280.979166666664,"2026-05-23",45280.194444444445,"5d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel:",null,null,68960,"2023-12-18","Minor","1,2,3,4,5"]
[null,"Infrabel","63309","Athus - Meuse","< >","BOIS D'AUSSE","NAMUR",2026,2026,21,21,"2026-05-18",45280.951388888891,"2026-05-23",45280.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nCTL nuits finitions\r\nDossier de concertation validé en octobre 2023",null,null,63309,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","61845","Lille - Antwerpen",">","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,21,21,"2026-05-18",45280.25,"2026-05-22",45280.666666666664,"5d, 10:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nDossier de concertation\r\n\r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pou",null,null,61845,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","68424","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,21,21,"2026-05-18",45280.993055555555,"2026-05-22",45280.180555555555,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y Kortrijk West\r\nvoorbereidende werken + Kirow\r\n\r\n\r\n*R5/R6 in WE TLO",null,null,68424,"2023-07-14","Minor","1,2,3,4,5"]
[null,"Infrabel","72263","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,21,21,"2026-05-18",45280.354166666664,"2026-05-22",45280.645833333336,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre - Phase 7\r\nDossier de concertation validé en octobre 2023",null,null,72263,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","64691","Namur - Antwerpen","< >","OTTIGNIES","OTTIGNIES",2026,2026,21,22,"2026-05-22",45280.979166666664,"2026-05-26",45280.201388888891,"3d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER Ottignies: renouvellement du Coeur de la gare + quais N7 et N8\r\ncoupure de 3 jours",null,null,64691,"2023-10-19","Medium","5,6"]
[null,"Infrabel","63345","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2026,2026,21,22,"2026-05-22",45280.25,"2026-05-25",45280.916666666664,"4d, 16:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement P93\r\nWE 2\r\n P93 + bourage, contraintes zone WE 1",null,null,63345,"2023-10-19","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","63071","Athus - Meuse","< >","YVOIR","Y.NEFFE",2026,2026,21,22,"2026-05-22",45280.993055555555,"2026-05-26",45280.180555555555,"3d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Poussage du P.I. de Neffe , d'un couloir sous voie à Dinant, renouvellement de chapes d'étanchéité et suppression du PN 116",null,null,63071,"2023-10-20","Medium","5,6"]
[null,"Infrabel","68430","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,21,22,"2026-05-22",45280.993055555555,"2026-05-26",45280.180555555555,"3d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y Kortrijk West\r\nvoorbereidende werken + Kirow\r\n\r\n\r\n*Pinkstermaandag inbegrepen\r\n* Roeselare niet in",null,null,68430,"2023-07-14","Medium","5,6"]
[null,"Infrabel","63350","Athus - Meuse","< >","STRAIMONT","FLORENVILLE",2026,2026,21,21,"2026-05-23",45280.25,"2026-05-24",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement P93 WE 2",null,null,63350,"2023-10-19","Medium","5,6"]
[null,"Infrabel","66959","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2026,2026,21,22,"2026-05-23",45280.166666666664,"2026-05-25",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vervolg werken 2023: vervangen houtstukken op Jan Bogaertsbrug (ander spoor) + vernieuwen spoor op brug over Zenne + sanering en vernieuwing spoor in een zone aan Jan Bogaertsbrug\r\n\r\nOverlegdossier gevalideerd in oktober 2023",null,null,66959,"2023-10-15","Medium","5,6"]
[null,"Infrabel","66648","Namur - Antwerpen",">","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,22,22,"2026-05-25",45280.979166666664,"2026-05-30",45280.194444444445,"5d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel:               \r\nL27 spA + L25 spB  BD",null,null,66648,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","66957","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2026,2026,22,22,"2026-05-25",45280.993055555555,"2026-05-30",45280.208333333336,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vervolg werken 2023: vervangen houtstukken op Jan Bogaertsbrug (ander spoor) + vernieuwen spoor op brug over Zenne + sanering en vernieuwing spoor in een zone aan Jan Bogaertsbrug\r\n\r\nOverlegdossier gevalideerd in oktober 2023",null,null,66957,"2023-12-18","Minor","1,2,3,4,5"]
[null,"Infrabel","63311","Athus - Meuse","< >","BOIS D'AUSSE","NAMUR",2026,2026,22,22,"2026-05-26",45280.951388888891,"2026-05-30",45280.201388888891,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nCTL nuits finitions\r\nDossier de concertation validé en octobre 2023",null,null,63311,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","68425","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,22,22,"2026-05-26",45280.993055555555,"2026-05-29",45280.180555555555,"3d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y Kortrijk West\r\n\r\nvoorbereidende werken \r\n\r\n\r\n*R1/R2 in WE TLO (Pinkstermaandag)\r\n*R5/R6 in WE TLO",null,null,68425,"2023-07-14","Minor","1,2,3,4,5"]
[null,"Infrabel","64704","Namur - Antwerpen","< >","OTTIGNIES","OTTIGNIES",2026,2026,22,23,"2026-05-29",45280.979166666664,"2026-06-01",45280.201388888891,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER Ottignies: renouvellement du coeur de la gare + quais N7 et N8",null,null,64704,"2023-10-23","Medium","5,6"]
[null,"Infrabel","65759","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,22,23,"2026-05-29",45280.9375,"2026-06-01",45280.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes\r\nRq 333 : Propo +2 WE, WE 22",null,null,65759,"2023-10-18","Medium","5,6"]
[null,"Infrabel","63073","Athus - Meuse","< >","YVOIR","Y.NEFFE",2026,2026,22,23,"2026-05-29",45280.916666666664,"2026-06-01",45280.208333333336,"2d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Poussage du P.I. de Neffe , d'un couloir sous voie à Dinant, renouvellement de chapes d'étanchéité et suppression du PN 116",null,null,63073,"2023-10-20","Medium","5,6"]
[null,"Infrabel","63353","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,22,23,"2026-05-29",45280.25,"2026-06-01",45280.916666666664,"4d, 16:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement P93\r\nWE 3\r\nP93 + bourrage, contraintes zone WE2",null,null,63353,"2023-10-19","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","68431","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,22,23,"2026-05-29",45280.993055555555,"2026-06-01",45280.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y Kortrijk West\r\n\r\n\r\n\r\n\r\n* Roeselare niet in",null,null,68431,"2023-07-14","Medium","5,6"]
[null,"Infrabel","63802","Athus - Meuse","< >","STRAIMONT","SAINT-VINCENT-BELLEFONTAINE",2026,2026,22,22,"2026-05-30",45280.25,"2026-05-31",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CTL P93 WE 3",null,null,63802,"2023-10-19","Medium","5,6"]
[null,"Infrabel","63701","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,22,22,"2026-05-30",45280.25,"2026-05-31",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Préparation transfert PN11, 12 et 18 + TRV\r\n+ Maintenance\r\nOK I-AM - A proposer trilatérale",null,null,63701,"2023-11-17","Medium","5,6"]
[null,"Infrabel","63810","Erquelinnes - Montzen","< >","FROIDMONT","BRESSOUX",2026,2026,22,22,"2026-05-30",45280.25,"2026-05-31",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z8.42\r\nEntretien mécanisé et manuel des AS du grill de Bressoux côté froitmond\r\nEntretien tunnel\r\nOK I-AM - OK pour proposer trilatérale",null,null,63810,"2023-10-27","Medium","5,6"]
[null,"Infrabel","67122","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2026,2026,22,22,"2026-05-30",45280.166666666664,"2026-05-31",45280.166666666664,"1d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"werken aan wissels Antwerpen Centraal , samen met L59/1, \r\n +1 (perronsporen van 1 t.e.m. 6),",null,null,67122,"2023-10-19","Medium","5,6"]
[null,"Infrabel","66960","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2026,2026,22,23,"2026-05-30",45280.166666666664,"2026-06-01",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vervolg werken 2023: vervangen houtstukken op Jan Bogaertsbrug (ander spoor) + vernieuwen spoor op brug over Zenne + sanering en vernieuwing spoor in een zone aan Jan Bogaertsbrug\r\nOverlegdossier gevalideerd in oktober 2023",null,null,66960,"2023-10-15","Medium","5,6"]
[null,"Infrabel","63901","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2026,2026,23,23,"2026-06-01",45280.958333333336,"2026-06-05",45280.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 7\r\nCoupure Type 5",null,null,63901,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","66649","Namur - Antwerpen",">","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,23,23,"2026-06-01",45280.979166666664,"2026-06-06",45280.194444444445,"5d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel:               \r\nL27 spA + L25 spB  BD",null,null,66649,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","71536","Athus - Meuse","< >","BOIS D'AUSSE","NAMUR",2026,2026,23,23,"2026-06-01",45280.951388888891,"2026-06-06",45280.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nCTL nuits finitions\r\nDossier de concertation validé en octobre 2023",null,null,71536,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","65349","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,23,23,"2026-06-01",45280.9375,"2026-06-06",45280.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS 63.687 en L94\r\nPhase 5 - Finitions au niveau du nouveau PS\r\n[Phases 1+2+3 en 2025]",null,null,65349,"2023-12-20","Minor","1,2,3,4,5"]
[null,"Infrabel","68426","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,23,23,"2026-06-01",45280.993055555555,"2026-06-06",45280.180555555555,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y Kortrijk West\r\nafwerking",null,null,68426,"2023-07-14","Minor","1,2,3,4,5"]
[null,"Infrabel","63914","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,23,27,"2026-06-01",45280.923611111109,"2026-07-04",45280.173611111109,"33d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux SI + Voie",null,null,63914,"2023-04-11","Minor","1,2,3,4,5"]
[null,"Infrabel","63902","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2026,2026,23,24,"2026-06-05",45280.958333333336,"2026-06-08",45280.208333333336,"3d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 7\r\nCoupure Type 4",null,null,63902,"2023-10-20","Minor","5,6"]
[null,"Infrabel","63331","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2026,2026,23,24,"2026-06-05",45280.979166666664,"2026-06-08",45280.1875,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Dépose des AS de Mont St Guibert \r\n+ Assainissement de la plateforme \r\nWE1\r\nrq 333 : Dépose As bien reportée?",null,null,63331,"2023-10-18","Medium","5,6"]
[null,"Infrabel","63074","Athus - Meuse","< >","YVOIR","Y.NEFFE",2026,2026,23,24,"2026-06-05",45280.916666666664,"2026-06-08",45280.208333333336,"2d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Poussage du P.I. de Neffe , d'un couloir sous voie à Dinant, renouvellement de chapes d'étanchéité et suppression du PN 116",null,null,63074,"2023-10-20","Medium","5,6"]
[null,"Infrabel","63355","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,23,24,"2026-06-05",45280.25,"2026-06-08",45280.916666666664,"4d, 16:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement P93\r\nWE 4 \r\nP93 + bourrage, contraintes zone WE3",null,null,63355,"2023-10-19","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","66591","Erquelinnes - Montzen","< >","HUY","NAMUR",2026,2026,23,24,"2026-06-05",45280.993055555555,"2026-06-08",45280.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification renforcement de talus  (L, enrochement,...), parois rocheuses. Suppression PN 75, 76, 77 78",null,null,66591,"2023-10-27","Medium","5,6"]
[null,"Infrabel","63358","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,23,23,"2026-06-06",45280.25,"2026-06-07",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement P93 \r\nWE 4",null,null,63358,"2023-10-19","Medium","5,6"]
[null,"Infrabel","66305","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,23,23,"2026-06-06",45280.25,"2026-06-07",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 11 + 12 - Préparation transfert PN11, 12 et 18 + TRV\r\n+ Maintenance\r\nOK I-AM - A proposer trilatérale",null,null,66305,"2023-11-17","Medium","5,6"]
[null,"Infrabel","63903","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2026,2026,24,28,"2026-06-08",45280.25,"2026-07-06",45280.208333333336,"29d, 23:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 8\r\nCoupure type 1 continu\r\nCoupure type 2 de nuit semaine\r\nVoie B L130 HS de nuits entre CJ.20 et DXJ.20 en semaine",null,null,63903,"2023-10-20","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","68427","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,24,24,"2026-06-08",45280.993055555555,"2026-06-13",45280.180555555555,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y Kortrijk West\r\nafwerking",null,null,68427,"2023-07-14","Minor","1,2,3,4,5"]
[null,"Infrabel","64308","Lille - Charleroi",">","LUTTRE","LUTTRE",2026,2026,24,25,"2026-06-12",45280.958333333336,"2026-06-15",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre\r\nExtension mise HS : Voie III en gare de Luttre",null,null,64308,"2023-05-09","Minor","5,6"]
[null,"Infrabel","63333","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2026,2026,24,25,"2026-06-12",45280.979166666664,"2026-06-15",45280.1875,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Dépose des AS de Mont St Guibert \r\n+ Assainissement de la plateforme \r\nWE2",null,null,63333,"2023-10-18","Medium","5,6"]
[null,"Infrabel","63361","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,24,25,"2026-06-12",45280.25,"2026-06-15",45280.916666666664,"4d, 16:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement P93 \r\nWE 5 \r\nP93 + bourrage, contraintes zone WE4",null,null,63361,"2023-10-19","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","63295","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,24,24,"2026-06-13",45280.25,"2026-06-14",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement P93 \r\nWE 5",null,null,63295,"2023-10-19","Medium","5,6"]
[null,"Infrabel","63710","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,24,24,"2026-06-13",45280.25,"2026-06-14",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Préparation transfert PN11, 12 et 18 + TRV\r\n+ Massification Z9.42\r\nEntretien mécanisé et manuel des AS de Bressoux côté Visé et AS des d'entrée de Visé et/ou entretien de PN",null,null,63710,"2023-10-27","Medium","5,6"]
[null,"Infrabel","64311","Lille - Charleroi",">","LUTTRE","LUTTRE",2026,2026,25,26,"2026-06-15",45280.958333333336,"2026-06-26",45280.208333333336,"11d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre\r\nExtension mise HS : Voie III en gare de Luttre",null,null,64311,"2023-05-09","Minor","1,2,3,4,5"]
[null,"Infrabel","65418","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,25,25,"2026-06-15",45280.9375,"2026-06-19",45280.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.",null,null,65418,"2023-05-10","Minor","1,2,3,4,5"]
[null,"Infrabel","65244","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","FROYENNES",2026,2026,25,25,"2026-06-15",45280.944444444445,"2026-06-19",45280.243055555555,"4d, 07:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction d’un PS pour supprimer les PN 8 et 10 - Décoffrage + pose garde-corps (réserve)",null,null,65244,"2023-04-11","Minor","1,2,3,4,5"]
[null,"Infrabel","69254","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,25,26,"2026-06-16",45280.027777777781,"2026-06-22",45280.208333333336,"7d, 04:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Bundel centraal Merelbeke\r\nlossen KIROW \r\nBuiten dienst;\r\nBundel Centraal volledig\r\nL50E SP B\r\nL58 SP B\r\nBuiten spanning;\r\n29170 - 29168 - 29166 - 29154 - 29184 - 29182 - 29187 - 29185 - 29186\r\nWerkplaats Melle bundel GC/GD buiten spanning!",null,null,69254,"2023-05-22","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","64309","Lille - Charleroi",">","LUTTRE","LUTTRE",2026,2026,25,26,"2026-06-19",45280.958333333336,"2026-06-22",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre\r\nExtension mise HS : Voie III en gare de Luttre",null,null,64309,"2023-05-09","Minor","5,6"]
[null,"Infrabel","63904","Namur - Antwerpen",">","LE CAMPINAIRE","COUILLET",2026,2026,25,26,"2026-06-19",45280.958333333336,"2026-06-22",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 9\r\nCoupure type 3",null,null,63904,"2023-10-20","Minor","5,6"]
[null,"Infrabel","65760","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,25,26,"2026-06-19",45280.9375,"2026-06-22",45280.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes\r\nCTL de WE mensuel",null,null,65760,"2023-10-18","Medium","5,6"]
[null,"Infrabel","65420","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,25,26,"2026-06-19",45280.9375,"2026-06-22",45280.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.",null,null,65420,"2023-05-10","Medium","5,6"]
[null,"Infrabel","63296","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,25,26,"2026-06-19",45280.25,"2026-06-22",45280.916666666664,"4d, 16:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement P93\r\nWE 6\r\nBourrage -contraintes zone WE 5",null,null,63296,"2023-10-19","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","63707","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,25,25,"2026-06-20",45280.25,"2026-06-21",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Préparation transfert PN11, 12 et 18 + TRV\r\n+ Maintenance\r\nOK I-AM - A proposer trilatérale",null,null,63707,"2023-11-17","Medium","5,6"]
[null,"Infrabel","63335","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2026,2026,26,26,"2026-06-22",45280.979166666664,"2026-06-27",45280.229166666664,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Dépose des AS de Mont St Guibert \r\n+ Assainissement de la plateforme\r\nBourrage de révision, contraintes,…",null,null,63335,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","65419","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,26,26,"2026-06-22",45280.9375,"2026-06-26",45280.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.",null,null,65419,"2023-05-10","Minor","1,2,3,4,5"]
[null,"Infrabel","63514","Athus - Meuse",">","VIRTON","SIGNEULX",2026,2026,26,28,"2026-06-25",45280.375,"2026-07-07",45280.625,"13d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Traitement zone boueuse (Golf Virton) L 165 voie A Bk 119.220 (120m)",null,null,63514,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","64310","Lille - Charleroi",">","LUTTRE","LUTTRE",2026,2026,26,27,"2026-06-26",45280.958333333336,"2026-06-29",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre\r\nExtension mise HS : Voie III en gare de Luttre",null,null,64310,"2023-05-09","Minor","5,6"]
[null,"Infrabel","63082","Namur - Antwerpen","< >","MOUSTIER","JEMEPPE-SUR-SAMBRE",2026,2026,26,27,"2026-06-26",45280.958333333336,"2026-06-29",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS bK 76.318",null,null,63082,"2023-05-17","Medium","5,6"]
[null,"Infrabel","63905","Namur - Antwerpen",">","LE CAMPINAIRE","COUILLET",2026,2026,26,27,"2026-06-26",45280.958333333336,"2026-06-29",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 9\r\nCoupure type 3",null,null,63905,"2023-10-20","Minor","5,6"]
[null,"Infrabel","65630","Athus - Meuse","< >","BEAURAING","GEDINNE",2026,2026,26,27,"2026-06-26",45280.979166666664,"2026-06-29",45280.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification de travaux OA\r\nRemplacement de chapes d'étanchéité PI BK 25.267 (PI rue de Rochefort à Beauraing)\r\nrq 333 : conflit L162 P93 Arlon-Sterpenich",null,null,65630,"2023-10-20","Medium","5,6"]
[null,"Infrabel","65421","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,26,27,"2026-06-26",45280.9375,"2026-06-29",45280.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.",null,null,65421,"2023-05-10","Medium","5,6"]
[null,"Infrabel","63515","Athus - Meuse","< >","VIRTON","SIGNEULX",2026,2026,26,27,"2026-06-27",45280.25,"2026-06-29",45280.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Traitement zone boueuse (Golf Virton) L 165 voie A Bk 119.220 (120m)",null,null,63515,"2023-10-20","Medium","5,6"]
[null,"Infrabel","64963","Erquelinnes - Montzen","< >","VISE","VISE",2026,2026,26,27,"2026-06-27",45280.25,"2026-06-29",45280.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Z13.42\r\nEntretien mécanisé et manuel des AS des faisceaux 56 et 57 de Visé-Bas\r\nEntretien de voie courante de la VB de L24/1 et L24/2\r\nA proposer trilatérale",null,null,64963,"2023-11-17","Medium","5,6"]
[null,"Infrabel","63297","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,26,27,"2026-06-27",45280.003472222219,"2026-06-29",45280.229166666664,"2d, 05:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 11 + 12\r\nMassification avec I-AM A4 Signalling (Ing. Julie Laforgia)\r\n+ Maintenance\r\nOK I-AM - A proposer trilatérale",null,null,63297,"2023-11-17","Medium","5,6"]
[null,"Infrabel","72101","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2026,2026,27,27,"2026-06-29",45280.979166666664,"2026-07-04",45280.229166666664,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Dépose des AS de Mont St Guibert \r\n+ Assainissement de la plateforme\r\nBourrage de révision, contraintes,…\r\nRq 333 : nuits we incompatibles - Propo 2 semaines CTL nuits",null,null,72101,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","63336","Athus - Meuse","< >","Y.AUTELBAS","ARLON",2026,2026,27,29,"2026-07-03",45280.916666666664,"2026-07-13",45280.25,"9d, 08:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement C75\r\nCf Escalade Head Of nov/dec 2023",null,null,63336,"2023-12-04","High","1,2,3,4,5,6,7"]
[null,"Infrabel","63298","Erquelinnes - Montzen",">","BRESSOUX","VISE",2026,2026,28,28,"2026-07-06",45280.958333333336,"2026-07-11",45280.229166666664,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement PN 11 + 12\r\nBourrage de révision",null,null,63298,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","63906","Namur - Antwerpen",">","LE CAMPINAIRE","COUILLET",2026,2026,28,28,"2026-07-11",45280.916666666664,"2026-07-12",45280.916666666664,"1d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 10\r\nCoupure type 3",null,null,63906,"2023-10-20","Minor","5,6"]
[null,"Infrabel","66337","Namur - Antwerpen","< >","KAPELLEN-WIJKSPOOR","ESSEN-GRENS",2026,2026,31,32,"2026-08-01",45280.166666666664,"2026-08-03",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Kleine vernieuwingen + onderhoud\r\nBundel Essen inbegrepen",null,null,66337,"2023-05-23","Medium","5,6"]
[null,"Infrabel","55877","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,32,32,"2026-08-03",45280.9375,"2026-08-07",45280.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 4  - Pose du nouveau tablier \r\nPhase 4.1 – CTL L75+75A+Faisceau de nuit",null,null,55877,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","65768","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,32,34,"2026-08-03",45280.9375,"2026-08-21",45280.9375,"18d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes\r\nDossier de concertation validé en octobre 2023",null,null,65768,"2023-10-18","High","1,2,3,4,5,6,7"]
[null,"Infrabel","55879","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2026,2026,32,33,"2026-08-07",45280.958333333336,"2026-08-10",45280.1875,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 4  - Pose du nouveau tablier \r\nPhase 4.2 – CTL L75+75A+Faisceau en continu",null,null,55879,"2023-10-17","Medium","5,6"]
[null,"Infrabel","40297","Namur - Antwerpen",">","BRUXELLES-NORD","BRUXELLES-NORD-GRIL F",2026,2026,32,34,"2026-08-07",45280.9375,"2026-08-17",45280.229166666664,"9d, 07:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing perrronboorden en perronverharding perron 6 FBN",null,null,40297,"2023-12-15","High","1,2,3,4,5,6,7"]
[null,"Infrabel","63907","Namur - Antwerpen",">","LE CAMPINAIRE","COUILLET",2026,2026,32,32,"2026-08-08",45280.916666666664,"2026-08-09",45280.916666666664,"1d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 10\r\nCoupure type 3",null,null,63907,"2023-10-20","Minor","5,6"]
[null,"Infrabel","55882","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,33,33,"2026-08-10",45280.958333333336,"2026-08-15",45280.239583333336,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 5 -Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architectoni",null,null,55882,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","63076","Athus - Meuse",">","DINANT","Y.NEFFE",2026,2026,33,39,"2026-08-10",45280.208333333336,"2026-09-21",45280.208333333336,"42d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement des rampes d'accès au CSV de Neffe et suppression des PN 115bis et 116",null,null,63076,"2023-10-20","High","1,2,3,4,5,6,7"]
[null,"Infrabel","63909","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2026,2026,33,34,"2026-08-14",45280.958333333336,"2026-08-17",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 11\r\nCoupure type 1 week-end continu",null,null,63909,"2023-10-20","Minor","5,6"]
[null,"Infrabel","63716","Namur - Antwerpen","< >","OTTIGNIES","TILLY",2026,2026,33,35,"2026-08-14",45280.979166666664,"2026-08-24",45280.201388888891,"9d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER : Suppression du PN 45 à Ottignies et remplacement par un CSV\r\nDossier de concertation validé en octobre 2023",null,null,63716,"2023-10-16","High","1,2,3,4,5,6,7"]
[null,"Infrabel","63334","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2026,2026,33,34,"2026-08-14",45280.25,"2026-08-17",45280.666666666664,"3d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE 1 P93\r\nDossier de concertation validé en octobre 2023",null,null,63334,"2023-10-16","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","63088","Athus - Meuse","< >","CINEY","MARLOIE",2026,2026,33,34,"2026-08-14",45280.927083333336,"2026-08-17",45280.208333333336,"2d, 06:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS de Haversin\r\nbK 102.161\r\nDossier de concertation validé en octobre 2023\r\nPropo déplacer tout bloc",null,null,63088,"2023-10-18","Medium","5,6"]
[null,"Infrabel","63337","Athus - Meuse","< >","GENDRON-CELLES","HOUYET",2026,2026,33,34,"2026-08-15",45280.25,"2026-08-17",45280.229166666664,"2d, 23:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE 1 P93\r\nDossier de concertation validé en octobre 2023",null,null,63337,"2023-10-20","Medium","5,6"]
[null,"Infrabel","66356","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2026,2026,33,34,"2026-08-16",45280.003472222219,"2026-08-17",45280.166666666664,"2d, 03:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"WEEKENDNACHTEN: werkvenster",null,null,66356,"2023-11-28","Minor","5,6"]
[null,"Infrabel","61850","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,34,34,"2026-08-17",45280.958333333336,"2026-08-22",45280.239583333336,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 5 -Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architectoni",null,null,61850,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","64326","Lille - Charleroi",">","MANAGE","LUTTRE",2026,2026,34,36,"2026-08-17",45280.208333333336,"2026-08-31",45280.208333333336,"14d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre - Phase 12\r\nTravaux Caténaire\r\nDossier de concertation validé en octobre 2023",null,null,64326,"2023-10-19","High","1,2,3,4,5,6,7"]
[null,"Infrabel","63089","Athus - Meuse",">","CINEY","MARLOIE",2026,2026,34,34,"2026-08-17",45280.927083333336,"2026-08-21",45280.208333333336,"4d, 06:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du PS de Haversin\r\nbK 102.161\r\nDossier de concertation validé en ocotbre 2023\r\ndéplacer tout bloc 1sem",null,null,63089,"2023-10-18","Minor","1,2,3,4,5"]
[null,"Infrabel","63910","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2026,2026,34,35,"2026-08-21",45280.958333333336,"2026-08-24",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 11\r\nCoupure type 1 week-end continu",null,null,63910,"2023-10-20","Minor","5,6"]
[null,"Infrabel","63341","Athus - Meuse",">","GENDRON-CELLES","BEAURAING",2026,2026,34,35,"2026-08-21",45280.25,"2026-08-24",45280.666666666664,"3d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE 2 P93 + bourrage...\r\nDossier de concertation validé en octobre 2023",null,null,63341,"2023-10-16","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","63091","Athus - Meuse","< >","CINEY","MARLOIE",2026,2026,34,35,"2026-08-21",45280.927083333336,"2026-08-24",45280.208333333336,"2d, 06:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS de Haversin\r\nbK 102.161\r\nRq 333 : incompatible L43 + AThus-Meuse A déplacer\r\nPropo : déplacer tout bloc 1sem",null,null,63091,"2023-10-18","Medium","5,6"]
[null,"Infrabel","72389","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,34,35,"2026-08-21",45280.993055555555,"2026-08-24",45280.194444444445,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,72389,"2023-10-26","Medium","5,6"]
[null,"Infrabel","63339","Athus - Meuse","< >","GENDRON-CELLES","BEAURAING",2026,2026,34,35,"2026-08-22",45280.25,"2026-08-24",45280.229166666664,"2d, 23:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE 2 P93\r\nDossier de concertation validé en octobre 2023",null,null,63339,"2023-10-16","Medium","5,6"]
[null,"Infrabel","66357","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2026,2026,34,35,"2026-08-23",45280.003472222219,"2026-08-24",45280.166666666664,"2d, 03:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"WEEKENDNACHTEN: werkvenster\r\nOverwegen + vernieuwing wisselonderdelen",null,null,66357,"2023-11-28","Minor","5,6"]
[null,"Infrabel","72391","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,35,35,"2026-08-24",45280.958333333336,"2026-08-28",45280.194444444445,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,72391,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","39558","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2026,2026,35,35,"2026-08-24",45280.9375,"2026-08-29",45280.173611111109,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 5 - Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architecton",null,null,39558,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","63911","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2026,2026,35,36,"2026-08-28",45280.958333333336,"2026-08-31",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 11\r\nCoupure type 1 week-end continu",null,null,63911,"2023-10-20","Minor","5,6"]
[null,"Infrabel","64134","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2026,2026,35,36,"2026-08-28",45280.958333333336,"2026-08-31",45280.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PI km 122.927\r\nEntretien face inférieur du PS km 120.098",null,null,64134,"2023-12-18","Medium","5,6"]
[null,"Infrabel","63718","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2026,2026,35,36,"2026-08-28",45280.979166666664,"2026-08-31",45280.201388888891,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER : Suppression du PN 45 à Ottignies et remplacement par un CSV - regulation contraintes  + bourrage de révision",null,null,63718,"2023-10-18","Medium","5,6"]
[null,"Infrabel","63342","Athus - Meuse",">","HOUYET","BEAURAING",2026,2026,35,36,"2026-08-28",45280.25,"2026-08-31",45280.666666666664,"3d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE3 P93 Bourrage\r\nDossier de concertation validé en octobre 2023",null,null,63342,"2023-10-16","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","72390","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,35,36,"2026-08-28",45280.993055555555,"2026-08-31",45280.194444444445,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,72390,"2023-10-26","Medium","5,6"]
[null,"Infrabel","66674","Namur - Antwerpen",">","ANTWERPEN-BERCHEM","Y.ARENDSTRAAT",2026,2026,35,36,"2026-08-29",45280.958333333336,"2026-08-31",45280.166666666664,"2d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken aan wissels Y Noord Berchem. Periodiciteit: 1 keer / jaar, TLO van 48u, Voorkeur week 35 (za 29 en zo 30-08),  beveiliging L59/1 27 spA: s'nachts door buitendienststelling, overdag correcte beveiliging voor indringing II\r\n\r\n\r\nniet gecoordineerd",null,null,66674,"2023-10-17","Minor","5,6"]
[null,"Infrabel","63344","Athus - Meuse","< >","HOUYET","BEAURAING",2026,2026,35,36,"2026-08-29",45280.25,"2026-08-31",45280.229166666664,"2d, 23:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE3 P93 Bourrage\r\nDossier de concertation validé en octobre 2023",null,null,63344,"2023-10-16","Medium","5,6"]
[null,"Infrabel","66354","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2026,2026,35,36,"2026-08-29",45280.166666666664,"2026-08-31",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Overwegen + kleine vernieuwingswerken",null,null,66354,"2023-07-11","Medium","5,6"]
[null,"Infrabel","66711","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,35,36,"2026-08-29",45280.166666666664,"2026-08-31",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"\"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC):               \r\n8 TLO weekends + 8 weken ruime weeknachten\r\ndata’s flexibel \r\nSamenwerking met andere diensten is mogelijk maar is afhankelijk van het type werk en dient vooraf goed afg",null,null,66711,"2023-10-17","Medium","5,6"]
[null,"Infrabel","69405","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2026,2026,36,36,"2026-08-31",45280.979166666664,"2026-09-04",45280.1875,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing aw's 18AR/18BR op Y Ruisbroek voorbereidende werken",null,null,69405,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","64327","Lille - Charleroi",">","MANAGE","LUTTRE",2026,2026,36,38,"2026-08-31",45280.208333333336,"2026-09-14",45280.208333333336,"14d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre - Phase 13\r\nTravaux Caténaire\r\nDossier de concertation validé en octobre 2023",null,null,64327,"2023-10-19","High","1,2,3,4,5,6,7"]
[null,"Infrabel","61851","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2026,2026,36,36,"2026-08-31",45280.9375,"2026-09-05",45280.173611111109,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 5 - Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architecton",null,null,61851,"2023-10-17","Minor","1,2,3,4,5"]
[null,"Infrabel","66702","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,36,36,"2026-08-31",45280.986111111109,"2026-09-05",45280.1875,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC)",null,null,66702,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","68649","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2026,2026,36,37,"2026-09-04",45280.979166666664,"2026-09-07",45280.1875,"2d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing aw's 18AR/18BR op Y Ruisbroek",null,null,68649,"2023-05-26","Minor","5,6"]
[null,"Infrabel","65761","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,36,37,"2026-09-04",45280.9375,"2026-09-07",45280.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes\r\nRq 333 : Propo +2 we,WE 5-6/09, ok?",null,null,65761,"2023-10-18","Medium","5,6"]
[null,"Infrabel","63346","Athus - Meuse",">","HOUYET","BEAURAING",2026,2026,36,37,"2026-09-04",45280.25,"2026-09-07",45280.666666666664,"3d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE4 P93 Bourrage\r\nDossier de concertation validé en octobre 2023",null,null,63346,"2023-10-16","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","63347","Athus - Meuse","< >","HOUYET","BEAURAING",2026,2026,36,37,"2026-09-05",45280.25,"2026-09-07",45280.229166666664,"2d, 23:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE4 P93 Bourrage\r\nDossier de concertation validé en octobre 2023",null,null,63347,"2023-10-16","Medium","5,6"]
[null,"Infrabel","67121","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","ANTWERPEN-CENTRAAL",2026,2026,36,37,"2026-09-05",45280.166666666664,"2026-09-07",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"werken wissels en sporen te Anwerpen Oost.",null,null,67121,"2023-10-17","Medium","5,6"]
[null,"Infrabel","66712","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,36,37,"2026-09-05",45280.166666666664,"2026-09-07",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC):",null,null,66712,"2023-10-17","Medium","5,6"]
[null,"Infrabel","66380","Namur - Antwerpen","< >","Y.HOLLAND","ANTWERPEN-NOORDERDOKKEN",2026,2026,37,37,"2026-09-07",45280.958333333336,"2026-09-12",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"\"Werken SIG (schets A22-SIG 1): \r\nWerken wissels Y Antw. Luchtbal: uitbreiding op CBP van L25Y \r\nPeriodiciteit: minium 4 keer 1 week/jaar; voorkeur  week 8 (van ma/di 17/18-02 t.e.m. vr/za 21/22-02) en week 18 (van ma/di 28/29-04 t.e.m. vr/za 2/3-05) en",null,null,66380,"2023-05-26","Minor","1,2,3,4,5"]
[null,"Infrabel","69406","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2026,2026,37,37,"2026-09-07",45280.979166666664,"2026-09-11",45280.1875,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing aw's 18AR/18BR op Y Ruisbroek voorbereidende werken",null,null,69406,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","69179","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,37,37,"2026-09-07",45280.965277777781,"2026-09-11",45280.166666666664,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Saneren met kranen thv Y Ringlaan\r\n+ \r\nOnderhoud\r\n\r\n* Y Bethune vrij\r\n* gevallen 29962 + 29959\r\n* R5/R6 in WE TLO",null,null,69179,"2023-07-24","Minor","1,2,3,4,5"]
[null,"Infrabel","66703","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,37,37,"2026-09-07",45280.986111111109,"2026-09-12",45280.1875,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC):",null,null,66703,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","68682","Lille - ZeeBrugge","< >","BRUGGE","ZEDELGEM-ROOSTER E/G",2026,2026,37,37,"2026-09-07",45280.993055555555,"2026-09-12",45280.208333333336,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing wissels Brugge fase 5\r\nLossen KIROW\r\n\r\nTLO L66 Brugge SP VII + VIII tot Rooster Zedelgem\r\nDOES SP A L50D(1) Brugge SP VI tot Rooster E vrij\r\nDOES SP B L50A Brugge SP IX tot Y Stuyvenberg vrij",null,null,68682,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","64899","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2026,2026,37,38,"2026-09-11",45280.958333333336,"2026-09-14",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Entretien OA 87.100",null,null,64899,"2023-05-22","Medium","5,6"]
[null,"Infrabel","68651","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2026,2026,37,38,"2026-09-11",45280.979166666664,"2026-09-14",45280.1875,"2d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing aw's 18AR/18BR op Y Ruisbroek",null,null,68651,"2023-10-16","Minor","5,6"]
[null,"Infrabel","69180","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,37,38,"2026-09-11",45280.965277777781,"2026-09-14",45280.166666666664,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Saneren met kranen thv Y Ringlaan\r\n+ \r\nOnderhoud\r\n\r\n* Y Bethune vrij\r\n* gevallen 29962 + 29959",null,null,69180,"2023-07-14","Medium","5,6"]
[null,"Infrabel","63779","Athus - Meuse","< >","JAMBES","YVOIR",2026,2026,37,38,"2026-09-11",45280.993055555555,"2026-09-14",45280.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement rails PN112 à Yvoir\r\n+ Massification travaux divers O.A. : Pistes, sécurisation de parois rocheuses et de talus",null,null,63779,"2023-10-20","Medium","5,6"]
[null,"Infrabel","66355","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2026,2026,37,38,"2026-09-12",45280.166666666664,"2026-09-14",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Overwegen + kleine vernieuwingswerken",null,null,66355,"2023-10-16","Medium","5,6"]
[null,"Infrabel","66713","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,37,38,"2026-09-12",45280.166666666664,"2026-09-14",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Te verplaatsen (L96)\r\nHerelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC):",null,null,66713,"2023-10-18","Medium","5,6"]
[null,"Infrabel","72395","Erquelinnes - Montzen",">","HUY","STATTE",2026,2026,38,38,"2026-09-14",45280.958333333336,"2026-09-19",45280.194444444445,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,72395,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","63348","Athus - Meuse",">","HOUYET","BEAURAING",2026,2026,38,38,"2026-09-14",45280.333333333336,"2026-09-18",45280.666666666664,"5d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nFinitions P93 Bourrage révision, pistes, contraintes \r\nDossier de concertation validé en octobre 2023",null,null,63348,"2023-10-16","Minor","1,2,3,4,5"]
[null,"Infrabel","69407","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2026,2026,38,38,"2026-09-14",45280.979166666664,"2026-09-19",45280.1875,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing aw's 18AR/18BR op Y Ruisbroek: afwerkingsnachten",null,null,69407,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","66647","Namur - Antwerpen",">","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,38,38,"2026-09-14",45280.979166666664,"2026-09-19",45280.194444444445,"5d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel:               \r\nL27 spA + L25 spB  BD",null,null,66647,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","65033","Lille - Charleroi",">","MANAGE","LUTTRE",2026,2026,38,39,"2026-09-14",45280.208333333336,"2026-09-21",45280.208333333336,"7d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre - Phase 14\r\nTravaux Caténaire\r\nDossier de concertation validé en octobre 2023",null,null,65033,"2023-10-19","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","69181","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,38,38,"2026-09-14",45280.965277777781,"2026-09-18",45280.166666666664,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Saneren met kranen thv Y Ringlaan\r\n+ \r\nOnderhoud\r\n\r\n* Y Bethune vrij\r\n* gevallen 29962 + 29959\r\n* R5/R6 in WE TLO",null,null,69181,"2023-07-24","Minor","1,2,3,4,5"]
[null,"Infrabel","66704","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,38,38,"2026-09-14",45280.986111111109,"2026-09-19",45280.1875,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC):",null,null,66704,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","63915","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,38,40,"2026-09-14",45280.923611111109,"2026-10-03",45280.173611111109,"19d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux SI + Voie",null,null,63915,"2023-04-11","Minor","1,2,3,4,5"]
[null,"Infrabel","69182","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,38,39,"2026-09-18",45280.965277777781,"2026-09-21",45280.166666666664,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Saneren met kranen thv Y Ringlaan\r\n+ \r\nOnderhoud\r\n\r\n* Y Bethune vrij\r\n* gevallen 29962 + 29959",null,null,69182,"2023-07-24","Medium","5,6"]
[null,"Infrabel","66714","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,38,39,"2026-09-19",45280.166666666664,"2026-09-21",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC):",null,null,66714,"2023-05-26","Medium","5,6"]
[null,"Infrabel","63056","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2026,2026,38,43,"2026-09-20",45280.916666666664,"2026-10-24",45280.25,"33d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du MDS VA",null,null,63056,"2023-07-13","High","1,2,3,4,5,6,7"]
[null,"Infrabel","72392","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,39,39,"2026-09-21",45280.958333333336,"2026-09-26",45280.194444444445,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,72392,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","71925","Athus - Meuse",">","HOUYET","BEAURAING",2026,2026,39,39,"2026-09-21",45280.333333333336,"2026-09-25",45280.666666666664,"5d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nFinitions P93 Bourrage révision, pistes, contraintes \r\nDossier de concertation validé en octobre 2023",null,null,71925,"2023-10-16","Minor","1,2,3,4,5"]
[null,"Infrabel","69408","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2026,2026,39,39,"2026-09-21",45280.979166666664,"2026-09-26",45280.1875,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing aw's 18AR/18BR op Y Ruisbroek: afwerkingsnachten",null,null,69408,"2023-11-23","Minor","1,2,3,4,5"]
[null,"Infrabel","69183","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,39,39,"2026-09-21",45280.965277777781,"2026-09-25",45280.166666666664,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Saneren met kranen thv Y Ringlaan\r\n+ \r\nOnderhoud\r\n\r\n* Y Bethune vrij\r\n* gevallen 29962 + 29959\r\n* R5/R6 in WE TLO",null,null,69183,"2023-07-14","Minor","1,2,3,4,5"]
[null,"Infrabel","66705","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,39,39,"2026-09-21",45280.986111111109,"2026-09-26",45280.1875,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC):",null,null,66705,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","64901","Namur - Antwerpen","< >","CHATELET-GRIL EST","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2026,2026,39,40,"2026-09-25",45280.979166666664,"2026-09-28",45280.180555555555,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA\r\nEn face inférieure des PS 79.750 (+ désiamantage) et 81.981 - WE CTL",null,null,64901,"2023-10-20","Medium","5,6"]
[null,"Infrabel","69184","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,39,40,"2026-09-25",45280.965277777781,"2026-09-28",45280.166666666664,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Saneren met kranen thv Y Ringlaan\r\n+ \r\nOnderhoud\r\n\r\n* Y Bethune vrij\r\n* gevallen 29962 + 29959",null,null,69184,"2023-07-24","Medium","5,6"]
[null,"Infrabel","63054","Erquelinnes - Montzen","< >","FROIDMONT","BRESSOUX",2026,2026,39,39,"2026-09-26",45280.25,"2026-09-27",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du MDS VA",null,null,63054,"2023-05-23","Medium","5,6"]
[null,"Infrabel","67123","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.ANTWERPEN-OOST",2026,2026,39,40,"2026-09-26",45280.166666666664,"2026-09-28",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Werken aan wissels Antwerpen Centraal \r\n+1 buiten dienst",null,null,67123,"2023-10-18","Medium","5,6"]
[null,"Infrabel","66359","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2026,2026,39,40,"2026-09-27",45280.003472222219,"2026-09-28",45280.166666666664,"2d, 03:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"WEEKENDNACHTEN: werkvenster\r\nOverwegen + kleine vernieuwingswerken",null,null,66359,"2023-11-28","Minor","5,6"]
[null,"Infrabel","72393","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,40,40,"2026-09-28",45280.958333333336,"2026-10-03",45280.194444444445,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,72393,"2023-10-26","Minor","1,2,3,4,5"]
[null,"Infrabel","69185","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,40,40,"2026-09-28",45280.965277777781,"2026-10-03",45280.166666666664,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Saneren met kranen thv Y Ringlaan\r\n+ \r\nOnderhoud\r\n\r\n* Y Bethune vrij\r\n* gevallen 29962 + 29959",null,null,69185,"2023-07-24","Minor","1,2,3,4,5"]
[null,"Infrabel","65762","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,40,41,"2026-10-02",45280.9375,"2026-10-05",45280.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes\r\n Rq 333 : propo WE 40 -> Lever CTL Ottignies-Bakenbos en + ce we là \r\n-> Choix entre Gembloux-Rhisnes et Ottignies Bakenbos pour WE sept/octobre vu contraintes C75 L161\r\nA déplacer",null,null,65762,"2023-12-18","Medium","5,6"]
[null,"Infrabel","63055","Erquelinnes - Montzen","< >","FROIDMONT","BRESSOUX",2026,2026,40,40,"2026-10-03",45280.25,"2026-10-04",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du MDS VA",null,null,63055,"2023-05-23","Medium","5,6"]
[null,"Infrabel","63754","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,40,40,"2026-10-03",45280.25,"2026-10-04",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 11 + 12\r\nPlacement loges PLP +  loges PNs\r\nRq 333 : Propo WE 40 en prolongement CTL MDS",null,null,63754,"2023-10-23","Medium","5,6"]
[null,"Infrabel","66349","Namur - Antwerpen","< >","KAPELLEN-WIJKSPOOR","ESSEN",2026,2026,40,41,"2026-10-04",45280.003472222219,"2026-10-05",45280.166666666664,"2d, 03:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Overwegen + kleine vernieuwingswerken\r\n weekendnachten werkvenster",null,null,66349,"2023-11-28","Minor","5,6"]
[null,"Infrabel","68413","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,41,41,"2026-10-05",45280.979166666664,"2026-10-10",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters e",null,null,68413,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","63077","Athus - Meuse",">","DINANT","Y.NEFFE",2026,2026,41,46,"2026-10-05",45280.208333333336,"2026-11-15",45280.666666666664,"41d, 11:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement des rampes d'accès au CSV de Neffe et suppression des PN 115bis et 116",null,null,63077,"2023-10-20","High","1,2,3,4,5,6,7"]
[null,"Infrabel","40058","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2026,2026,41,43,"2026-10-05",45280.965277777781,"2026-10-24",45280.229166666664,"19d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PI 37.804 pour élargissement du passage sous l'ouvrage et construction d'un CSV en gare pour la suppression du PN 65\r\n+ Remplacement des appuis du PS 117 et renouvellement de la chape d'étanchéité\r\nRq333 : devra être déplacé quand CBP ",null,null,40058,"2023-08-09","Minor","1,2,3,4,5"]
[null,"Infrabel","63083","Namur - Antwerpen","< >","MOUSTIER","JEMEPPE-SUR-SAMBRE",2026,2026,41,42,"2026-10-09",45280.958333333336,"2026-10-12",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS bK 76.318",null,null,63083,"2023-05-23","Medium","5,6"]
[null,"Infrabel","64902","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE",2026,2026,41,42,"2026-10-09",45280.958333333336,"2026-10-12",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux en face inférieure des OA 79.750 et 81.981 - WE CTL",null,null,64902,"2023-05-23","Medium","5,6"]
[null,"Infrabel","40034","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2026,2026,41,42,"2026-10-09",45280.986111111109,"2026-10-12",45280.194444444445,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PI 37.804 pour élargissement du passage sous l'ouvrage et construction d'un CSV en gare pour la suppression du PN 65\r\n+ Remplacement des appuis du PS 117 et renouvellement de la chape d'étanchéité",null,null,40034,"2023-07-13","Medium","5,6"]
[null,"Infrabel","63057","Erquelinnes - Montzen","< >","FROIDMONT","BRESSOUX",2026,2026,41,41,"2026-10-10",45280.25,"2026-10-11",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du MDS VA",null,null,63057,"2023-05-23","Medium","5,6"]
[null,"Infrabel","63833","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,41,41,"2026-10-10",45280.25,"2026-10-11",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 11 + 12\r\n+ Massification Z9.42\r\nEntretien mécanisé et manuel des AS de Bressoux côté Visé et AS des d'entrée de Visé et/ou entretien de PN\r\nOK I-AM - A proposer trilatérale",null,null,63833,"2023-10-27","Medium","5,6"]
[null,"Infrabel","63517","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,41,42,"2026-10-10",45280.25,"2026-10-12",45280.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Traitement zone boueuse voie A L 165 BK 91.000 (90m).",null,null,63517,"2023-10-20","Medium","5,6"]
[null,"Infrabel","55883","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,42,42,"2026-10-12",45280.958333333336,"2026-10-17",45280.239583333336,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 6 - finitions\r\nPhase 6.1 – CTL L75 de nuit de semaine",null,null,55883,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","68414","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,42,42,"2026-10-12",45280.979166666664,"2026-10-17",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters e",null,null,68414,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","63518","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,42,42,"2026-10-14",45280.375,"2026-10-16",45280.625,"3d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Traitement zone boueuse voie A L 165 BK 91.000 (90m).",null,null,63518,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","64257","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,42,44,"2026-10-16",45280.958333333336,"2026-10-26",45280.173611111109,"9d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Pose 2nd tablier Ponts 8 et 10",null,null,64257,"2023-10-19","High","1,2,3,4,5,6,7"]
[null,"Infrabel","66304","Erquelinnes - Montzen","< >","FROIDMONT","BRESSOUX",2026,2026,42,43,"2026-10-16",45280.9375,"2026-10-19",45280.208333333336,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du MDS VA \r\n+ Massification\r\n+ Maintenance Z8.42 AI 42\r\nEntretien mécanisé et manuel des AS du grill de Bressoux côté froitmond\r\nEntretien tunnel",null,null,66304,"2023-05-23","Medium","5,6"]
[null,"Infrabel","65769","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,42,45,"2026-10-16",45280.9375,"2026-11-02",45280.1875,"16d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes\r\nDossier de concertation validé en octobre 2023",null,null,65769,"2023-10-18","High","1,2,3,4,5,6,7"]
[null,"Infrabel","66543","Namur - Antwerpen",">","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2026,2026,42,43,"2026-10-17",45280.958333333336,"2026-10-19",45280.166666666664,"2d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Beveiliging voor onderstaande werken:\r\nwerken SIG (schets 2), Werken aan wissels Y Arendstraat en Antwerpen Centraal -2.",null,null,66543,"2023-05-22","Minor","5,6"]
[null,"Infrabel","70735","Namur - Antwerpen","< >","OTTIGNIES","Y.LOUVAIN-LA-NEUVE",2026,2026,42,42,"2026-10-17",45280.25,"2026-10-18",45280.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement C75\r\nDossier de concertation validé en octobre 2023\r\nCTL pour bourrage révision et contraintes suite C75",null,null,70735,"2023-10-16","Medium","5,6"]
[null,"Infrabel","68415","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,43,43,"2026-10-19",45280.979166666664,"2026-10-24",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters e",null,null,68415,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","55887","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2026,2026,43,43,"2026-10-19",45280.9375,"2026-10-24",45280.173611111109,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 6 - finitions\r\nPhase 6.2 – CTL L75A+Faisceau de nuit de semaine​",null,null,55887,"2023-10-17","Minor","1,2,3,4,5"]
[null,"Infrabel","72271","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,43,43,"2026-10-19",45280.375,"2026-10-20",45280.625,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Traitement zone boueuse voie A L 165 BK 91.000 (90m).",null,null,72271,"2023-10-20","Minor","1,2,3,4,5"]
[null,"Infrabel","63367","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","LEMAN",2026,2026,43,44,"2026-10-23",45280.25,"2026-10-27",45280.208333333336,"4d, 23:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"P93 WE1",null,null,63367,"2023-07-13","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","63377","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2026,2026,43,44,"2026-10-24",45280.958333333336,"2026-10-26",45280.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement P93 \r\nWE1",null,null,63377,"2023-04-11","Minor","5,6"]
[null,"Infrabel","63059","Erquelinnes - Montzen","< >","FROIDMONT","BRESSOUX",2026,2026,43,43,"2026-10-24",45280.25,"2026-10-25",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du MDS VA",null,null,63059,"2023-05-23","Medium","5,6"]
[null,"Infrabel","66336","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.HOLLAND",2026,2026,43,44,"2026-10-24",45280.166666666664,"2026-10-26",45280.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Oosterweel: \r\noverpakken bruggen en impact bemaling",null,null,66336,"2023-10-19","Medium","5,6"]
[null,"Infrabel","66639","Namur - Antwerpen","< >","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,44,44,"2026-10-26",45280.979166666664,"2026-10-31",45280.194444444445,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel:",null,null,66639,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","68416","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,44,44,"2026-10-26",45280.979166666664,"2026-10-31",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters e",null,null,68416,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","68676","Lille - ZeeBrugge","< >","BRUGGE","ZEDELGEM-ROOSTER E/G",2026,2026,44,44,"2026-10-26",45280.993055555555,"2026-10-30",45280.208333333336,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing wissels Brugge fase 5\r\n\r\nTLO L66 Brugge SP VII + VIII tot Rooster Zedelgem\r\nDOES SP A L50D(1) Brugge SP VI tot Rooster E vrij\r\nDOES SP B L50A Brugge SP IX tot Y Stuyvenberg vrij\r\n\r\nR5/R6 in WE TLO",null,null,68676,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","63890","Lille - Charleroi",">","CHARLEROI-CENTRAL","Y.NORD",2026,2026,44,44,"2026-10-26",45280.354166666664,"2026-10-30",45280.958333333336,"5d, 14:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Charleroi-Central- Phase 2.16.1\r\nCoupure Type 7 en continu + Type 8 de nuit\r\nDossier de concertation",null,null,63890,"2023-10-24","Minor","1,2,3,4,5"]
[null,"Infrabel","63893","Lille - Charleroi","< >","Y.LA SAMBRE","Y.NORD",2026,2026,44,44,"2026-10-30",45280.958333333336,"2026-11-01",45280.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi-Central- Phase 2.17\r\nCoupure Type 4\r\nExtension Nuit L124A\r\nDossier de concertation",null,null,63893,"2023-10-24","Minor","5,6"]
[null,"Infrabel","68254","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,44,45,"2026-10-30",45280.958333333336,"2026-11-02",45280.173611111109,"3d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose 2nd tablier Ponts 8 et 10\r\nBourrage et libération de contraintes",null,null,68254,"2023-05-10","Minor","5,6"]
[null,"Infrabel","65959","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","LEMAN",2026,2026,44,45,"2026-10-30",45280.25,"2026-11-03",45280.208333333336,"4d, 23:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"P93 WE2",null,null,65959,"2023-07-13","Minor","1,2,3,4,5,6,7"]
[null,"Infrabel","68677","Lille - ZeeBrugge","< >","BRUGGE","ZEDELGEM-ROOSTER E/G",2026,2026,44,45,"2026-10-30",45280.993055555555,"2026-11-03",45280.208333333336,"3d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing wissels Brugge fase 5\r\nTLO L66 Brugge SP VII + VIII tot Rooster Zedelgem\r\nDOES SP A L50D(1) Brugge SP VI tot Rooster E vrij\r\nDOES SP B L50A Brugge SP IX tot Y Stuyvenberg vrij\r\nPerron VI-VII-VIII buiten spanning\r\n\r\nOPGELET; aansluitend 2 dag",null,null,68677,"2023-12-15","Medium","1,2,3,4,5,6,7"]
[null,"Infrabel","63381","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2026,2026,44,45,"2026-10-31",45280.958333333336,"2026-11-02",45280.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement P93 WE2",null,null,63381,"2023-04-11","Minor","5,6"]
[null,"Infrabel","69242","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,44,45,"2026-10-31",45280.027777777781,"2026-11-02",45280.166666666664,"2d, 03:20h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Bundel centraal Merelbeke\r\naansluiting nieuwe sporen 5-6-7-8 van bundel centraal + aansluiten aan L50E\r\nBuiten dienst;\r\nBundel Centraal volledig\r\nL50E SP B\r\nL58 SP B\r\nBuiten spanning;\r\n29170 - 29168 - 29166 - 29154 - 29184 - 29182 - 29187 - 29185 - 2918",null,null,69242,"2023-05-22","Minor","5,6"]
[null,"Infrabel","66643","Namur - Antwerpen","< >","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,44,46,"2026-10-31",45280.166666666664,"2026-11-09",45280.166666666664,"9d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel:  Herfstvakantie",null,null,66643,"2023-10-18","High","1,2,3,4,5,6,7"]
[null,"Infrabel","61852","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,45,45,"2026-11-02",45280.958333333336,"2026-11-07",45280.239583333336,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation \r\n\r\nPhase 6 - finitions\r\nPhase 6.1 – CTL L75 de nuit de semaine",null,null,61852,"2023-10-03","Minor","1,2,3,4,5"]
[null,"Infrabel","68417","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,45,45,"2026-11-02",45280.979166666664,"2026-11-07",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters e",null,null,68417,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","68678","Lille - ZeeBrugge","< >","BRUGGE","BRUGGE-ROOSTER E",2026,2026,45,45,"2026-11-03",45280.208333333336,"2026-11-05",45280.208333333336,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing wissels Brugge fase 5\r\nTLO L66 Brugge SP VII + VIII tot Brugge Rooster E vrij\r\nDOES SP A L50D(1) Brugge SP VI tot Rooster E vrij\r\nDOES SP B L50A Brugge SP IX tot Y Stuyvenberg vrij\r\nPerron VI-VII-VIII buiten spanning",null,null,68678,"2023-12-15","Medium","1,2,3,4,5"]
[null,"Infrabel","68255","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,45,46,"2026-11-06",45280.958333333336,"2026-11-09",45280.173611111109,"3d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose 2nd tablier Ponts 8 et 10\r\nLever ART + finitions",null,null,68255,"2023-05-10","Minor","5,6"]
[null,"Infrabel","63388","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","LEMAN",2026,2026,45,46,"2026-11-07",45280.958333333336,"2026-11-09",45280.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"bourrage de révision, contraintes",null,null,63388,"2023-04-11","Minor","5,6"]
[null,"Infrabel","69243","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,45,46,"2026-11-07",45280.027777777781,"2026-11-09",45280.166666666664,"2d, 03:20h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Bundel centraal Merelbeke\r\naansluiting nieuwe sporen 5-6-7-8 van bundel centraal + aansluiten aan L50E\r\nBuiten dienst;\r\nBundel Centraal volledig\r\nL50E SP B\r\nL58 SP B\r\nBuiten spanning;\r\n29170 - 29168 - 29166 - 29154 - 29184 - 29182 - 29187 - 29185 - 2918",null,null,69243,"2023-05-22","Minor","5,6"]
[null,"Infrabel","66381","Namur - Antwerpen","< >","Y.HOLLAND","ANTWERPEN-NOORDERDOKKEN",2026,2026,46,46,"2026-11-09",45280.958333333336,"2026-11-14",45280.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"\"Werken SIG (schets A22-SIG 1): \r\nWerken wissels Y Antw. Luchtbal: uitbreiding op CBP van L25Y \r\nPeriodiciteit: minium 4 keer 1 week/jaar; voorkeur  week 8 (van ma/di 17/18-02 t.e.m. vr/za 21/22-02) en week 18 (van ma/di 28/29-04 t.e.m. vr/za 2/3-05) en",null,null,66381,"2023-05-26","Minor","1,2,3,4,5"]
[null,"Infrabel","63389","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","LEMAN",2026,2026,46,46,"2026-11-09",45280.958333333336,"2026-11-14",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"bourrage de révision, contraintes",null,null,63389,"2023-04-11","Minor","1,2,3,4,5"]
[null,"Infrabel","66641","Namur - Antwerpen","< >","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,46,46,"2026-11-09",45280.979166666664,"2026-11-14",45280.194444444445,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel:",null,null,66641,"2023-12-11","Minor","1,2,3,4,5"]
[null,"Infrabel","68418","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,46,46,"2026-11-09",45280.979166666664,"2026-11-14",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters e",null,null,68418,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","61853","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2026,2026,46,46,"2026-11-09",45280.9375,"2026-11-14",45280.173611111109,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 6 - finitions\r\nPhase 6.2 – CTL L75A+Faisceau de nuit de semaine​",null,null,61853,"2023-10-17","Minor","1,2,3,4,5"]
[null,"Infrabel","63954","Lille - Charleroi","< >","JURBISE","ATH",2026,2026,46,46,"2026-11-09",45280.923611111109,"2026-11-13",45280.215277777781,"4d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93",null,null,63954,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","64714","Namur - Antwerpen","< >","OTTIGNIES","OTTIGNIES",2026,2026,46,47,"2026-11-13",45280.979166666664,"2026-11-16",45280.201388888891,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER Ottignies: renouvellement du coeur de la gare + quais N7 et N8",null,null,64714,"2023-10-20","Medium","5,6"]
[null,"Infrabel","68680","Lille - ZeeBrugge","< >","BRUGGE","BRUGGE-ROOSTER E",2026,2026,46,47,"2026-11-13",45280.993055555555,"2026-11-16",45280.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing wissels Brugge fase 5\r\n\r\nTLO L66 Brugge SP VII + VIII tot Rooster E vrij\r\nDOES SP A L50D(1) Brugge SP VI tot Rooster E vrij\r\nDOES SP B L50A Brugge SP IX tot Y Stuyvenberg vrij\r\n\r\nperron VI-VII-VIII buiten spanning.",null,null,68680,"2023-12-15","Medium","5,6"]
[null,"Infrabel","63079","Athus - Meuse","< >","JAMBES","YVOIR",2026,2026,46,47,"2026-11-13",45280.993055555555,"2026-11-16",45280.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux divers O.A. : Pistes, sécurisation de parois rocheuses et de talus",null,null,63079,"2023-04-14","Medium","5,6"]
[null,"Infrabel","63945","Lille - Charleroi","< >","JURBISE","ATH",2026,2026,46,47,"2026-11-13",45280.923611111109,"2026-11-16",45280.215277777781,"2d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93",null,null,63945,"2023-10-23","Medium","5,6"]
[null,"Infrabel","63391","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","LEMAN",2026,2026,46,47,"2026-11-14",45280.958333333336,"2026-11-16",45280.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"bourrage de révision, contraintes",null,null,63391,"2023-04-11","Minor","5,6"]
[null,"Infrabel","69244","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,46,47,"2026-11-14",45280.027777777781,"2026-11-16",45280.166666666664,"2d, 03:20h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Bundel centraal Merelbeke\r\naansluiting nieuwe sporen 5-6-7-8 van bundel centraal + aansluiten aan L50E\r\nBuiten dienst;\r\nBundel Centraal volledig\r\nL50E SP B\r\nL58 SP B\r\nBuiten spanning;\r\n29170 - 29168 - 29166 - 29154 - 29184 - 29182 - 29187 - 29185 - 2918",null,null,69244,"2023-05-22","Minor","5,6"]
[null,"Infrabel","63390","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","LEMAN",2026,2026,47,47,"2026-11-16",45280.958333333336,"2026-11-21",45280.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"bourrage de révision, contraintes",null,null,63390,"2023-04-11","Minor","1,2,3,4,5"]
[null,"Infrabel","68419","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,47,47,"2026-11-16",45280.979166666664,"2026-11-21",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters e",null,null,68419,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","68681","Lille - ZeeBrugge","< >","BRUGGE","ZEDELGEM-ROOSTER E/G",2026,2026,47,47,"2026-11-16",45280.993055555555,"2026-11-21",45280.208333333336,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing wissels Brugge fase 5\r\nTLO L66 Brugge SP VII + VIII tot Rooster Zedelgem\r\nDOES SP A L50D(1) Brugge SP VI tot Rooster E vrij\r\nDOES SP B L50A Brugge SP IX tot Y Stuyvenberg vrij",null,null,68681,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","65063","Namur - Antwerpen","< >","CHATELET","CHATELET-GRIL OUEST",2026,2026,47,48,"2026-11-20",45280.958333333336,"2026-11-23",45280.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 4",null,null,65063,"2023-03-08","Medium","5,6"]
[null,"Infrabel","64721","Namur - Antwerpen","< >","OTTIGNIES","OTTIGNIES",2026,2026,47,48,"2026-11-20",45280.979166666664,"2026-11-23",45280.201388888891,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER Ottignies: renouvellement du coeur de la gare + quais N7 et N8",null,null,64721,"2023-10-19","Medium","5,6"]
[null,"Infrabel","63080","Athus - Meuse","< >","JAMBES","YVOIR",2026,2026,47,48,"2026-11-20",45280.993055555555,"2026-11-23",45280.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux divers O.A. : Pistes, sécurisation de parois rocheuses et de talus",null,null,63080,"2023-04-14","Medium","5,6"]
[null,"Infrabel","63946","Lille - Charleroi","< >","JURBISE","ATH",2026,2026,47,48,"2026-11-20",45280.923611111109,"2026-11-23",45280.215277777781,"2d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93",null,null,63946,"2023-10-23","Medium","5,6"]
[null,"Infrabel","68420","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,48,48,"2026-11-23",45280.979166666664,"2026-11-28",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters e",null,null,68420,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","69188","Namur - Antwerpen","< >","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,48,48,"2026-11-24",45280.020833333336,"2026-11-28",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels 1AS & 1BS L50E (kirow)\r\n\r\n*R5/R6 in WE TLO\r\n* inrit Merelbeke enkel kant Gent",null,null,69188,"2023-05-17","Minor","1,2,3,4,5"]
[null,"Infrabel","65070","Namur - Antwerpen",">","CHATELET","CHATELET-GRIL OUEST",2026,2026,48,49,"2026-11-27",45280.958333333336,"2026-11-30",45280.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 5",null,null,65070,"2023-01-30","Minor","5,6"]
[null,"Infrabel","65764","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,48,49,"2026-11-27",45280.979166666664,"2026-11-30",45280.1875,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes",null,null,65764,"2023-12-19","Medium","5,6"]
[null,"Infrabel","63947","Lille - Charleroi","< >","JURBISE","ATH",2026,2026,48,49,"2026-11-27",45280.923611111109,"2026-11-30",45280.215277777781,"2d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93",null,null,63947,"2023-10-23","Medium","5,6"]
[null,"Infrabel","74436","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN",2026,2026,48,49,"2026-11-28",45280.020833333336,"2026-11-30",45280.208333333336,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Masterplan Mechelen\r\nSpoor 9&10\r\nBijkomend bij 71420 tijdens nacht",null,null,74436,"2023-12-19","Medium","5,6"]
[null,"Infrabel","69187","Namur - Antwerpen","< >","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,48,49,"2026-11-28",45280.020833333336,"2026-11-30",45280.1875,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels 1AS & 1BS L50E (kirow)",null,null,69187,"2023-05-17","Medium","5,6"]
[null,"Infrabel","66315","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,48,48,"2026-11-28",45280.25,"2026-11-29",45280.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 11 + 12 \r\n+ Massification Z9.42\r\nEntretien mécanisé et manuel des AS de Bressoux côté Visé et AS des d'entrée de Visé et/ou entretien de PN\r\nOK I-AM - A proposer trilatérale",null,null,66315,"2023-10-27","Medium","5,6"]
[null,"Infrabel","65064","Namur - Antwerpen",">","CHATELET","CHATELET-GRIL OUEST",2026,2026,49,49,"2026-11-30",45280.958333333336,"2026-12-01",45280.208333333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 6",null,null,65064,"2023-01-30","Minor","1,2,3,4,5"]
[null,"Infrabel","68421","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,49,49,"2026-11-30",45280.979166666664,"2026-12-05",45280.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters e",null,null,68421,"2023-12-15","Minor","1,2,3,4,5"]
[null,"Infrabel","65071","Namur - Antwerpen",">","CHATELET","CHATELET-GRIL OUEST",2026,2026,49,49,"2026-12-01",45280.958333333336,"2026-12-02",45280.208333333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 6",null,null,65071,"2023-01-30","Minor","1,2,3,4,5"]
[null,"Infrabel","69189","Namur - Antwerpen","< >","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,49,49,"2026-12-01",45280.020833333336,"2026-12-05",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels 1AS & 1BS L50E (kirow)\r\n\r\n* inrit Merelbeke enkel kant Gent",null,null,69189,"2023-05-17","Minor","1,2,3,4,5"]
[null,"Infrabel","65065","Namur - Antwerpen",">","CHATELET","CHATELET-GRIL OUEST",2026,2026,49,49,"2026-12-02",45280.958333333336,"2026-12-04",45280.208333333336,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 6",null,null,65065,"2023-01-30","Minor","1,2,3,4,5"]
[null,"Infrabel","65074","Namur - Antwerpen",">","CHATELET","CHATELET-GRIL OUEST",2026,2026,49,49,"2026-12-04",45280.958333333336,"2026-12-06",45280.208333333336,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 6",null,null,65074,"2023-01-30","Minor","5,6"]
[null,"Infrabel","65765","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,49,50,"2026-12-04",45280.9375,"2026-12-07",45280.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes",null,null,65765,"2023-10-18","Medium","5,6"]
[null,"Infrabel","63952","Lille - Charleroi","< >","JURBISE","ATH",2026,2026,49,50,"2026-12-04",45280.923611111109,"2026-12-07",45280.215277777781,"2d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93",null,null,63952,"2023-10-23","Medium","5,6"]
[null,"Infrabel","74457","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN",2026,2026,49,50,"2026-12-05",45280.020833333336,"2026-12-07",45280.208333333336,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Masterplan Mechelen\r\nSpoor 9&10\r\nBijkomend bij 74444 tijdens nacht",null,null,74457,"2023-12-19","Medium","5,6"]
[null,"Infrabel","63953","Lille - Charleroi","< >","JURBISE","ATH",2026,2026,50,50,"2026-12-07",45280.923611111109,"2026-12-12",45280.215277777781,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93",null,null,63953,"2023-10-23","Minor","1,2,3,4,5"]
[null,"Infrabel","69190","Namur - Antwerpen","< >","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,50,50,"2026-12-08",45280.020833333336,"2026-12-12",45280.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels 1AS & 1BS L50E (kirow)\r\n\r\n* inrit Merelbeke enkel kant Gent",null,null,69190,"2023-05-17","Minor","1,2,3,4,5"]
[null,"Infrabel","74460","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN",2026,2026,50,51,"2026-12-12",45280.020833333336,"2026-12-14",45280.208333333336,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Masterplan Mechelen\r\nSpoor 9&10\r\nBijkomend bij 71381 tijdens nacht",null,null,74460,"2023-12-19","Medium","5,6"]

{"sheet":"ProRail","index":4,"n_rows":331,"n_cols":45,"rows_kept":331,"cut":false,"hidden":false,"merged":[[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]]}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Type of TCR","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)","Last update","Classification","Weekdays","Interval","Affected estimated travel volume","Affected border","Deviation location","Deviation border","Status","Additional information","Automatic process","Selected days","Variant value"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null," "," "]
[null,"ProRail","R3AE041-2404",null,">","Amsterdam Centraal","Amsterdam Centraal",2023,2024,49,26,"2023-12-10","08:00:00","2024-06-29","09:00:00","202d 01:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Betreft werkzaamheden aan de Westknoop thv spoor 1 en 2a. Deze sporen zijn al op BVS buitendienst genomen. * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE041-2404-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE041","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006146-2403",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,2,3,"2024-01-13","01:00:00","2024-01-16","01:00:00","2d 00:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"Groot Onderhoud TTI * More details: https://btd-planner.prorail.nl?taak=IO-K-006146-2403-00-5&doc=FOT (Register with ProRail)",null,null,"K-006146","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006146-2404",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,2,2,"2024-01-09","01:00:00","2024-01-12","01:00:00","2d 00:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"Groot Onderhoud TTI * More details: https://btd-planner.prorail.nl?taak=IO-K-006146-2404-00-5&doc=FOT (Register with ProRail)",null,null,"K-006146","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z907175-2401",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,3,4,"2024-01-20","01:00:00","2024-01-22","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren hem boog spoor 9, 10 * More details: https://btd-planner.prorail.nl?taak=IO-Z-907175-2401-00-3&doc=FOT (Register with ProRail)",null,null,"Z-907175","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005445-2402",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,3,4,"2024-01-20","01:16:00","2024-01-22","05:16:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2402-00-2&doc=FOT (Register with ProRail)",null,null,"L-005445","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005300-2403",null,">","Amsterdam Riekerpolder aansl.","Amsterdam Riekerpolder aansl.",2024,2024,3,3,"2024-01-20","01:16:00","2024-01-20","17:16:00","0d 16:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"PVE-8 Vervangen zijwaartse bevestigingen * More details: https://btd-planner.prorail.nl?taak=IO-L-005300-2403-00-3&doc=FOT (Register with ProRail)",null,null,"L-005300","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006902-ST01",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,3,3,"2024-01-17","12:00:00","2024-01-19","19:00:00","2d 07:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"Onderhoud/herstel mootvoegen/lekkages Sophia Tunnel * More details: https://btd-planner.prorail.nl?taak=IO-K-006902-ST01-00-5&doc=FOT (Register with ProRail)",null,null,"K-006902","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KB17018-2403",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,3,3,"2024-01-15","08:00:00","2024-01-17","12:00:00","2d 04:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"Sophia & Giessen tunnel,  jaarlijkse controle Tunnel Technische Installaties * More details: https://btd-planner.prorail.nl?taak=IO-K-B17018-2403-00-3&doc=FOT (Register with ProRail)",null,null,"K-B17018","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R564000-24B1",null,">","Lage Zwaluwe","Roosendaal",2024,2024,4,4,"2024-01-27","00:00:00","2024-01-28","11:00:00","1d 11:00","continuous","Signal","","LT+ST",null,null,null,null,null,null,null,null,"Saneren Wido Breda en opheffen Seinvertraging * More details: https://btd-planner.prorail.nl?taak=IO-R-564000-24B1-00-5&doc=FOT (Register with ProRail)",null,null,"R-564000","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006108-2401",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2024,2024,4,5,"2024-01-27","00:14:00","2024-01-29","05:44:00","2d 05:30","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Schuilingervliet-Stabiliteit baan terugbrengen-Herstelwerkzaamheden-Spoorstaafschades-Randelementen * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2401-00-6&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007202-04",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,4,10,"2024-01-22","06:00:00","2024-03-04","06:00:00","42d 00:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"SAT2 bundels 6-4. testwerkzaamheden. * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-04-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z907175-2402",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,5,6,"2024-02-03","01:00:00","2024-02-05","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren hem boog spoor 9, 10 * More details: https://btd-planner.prorail.nl?taak=IO-Z-907175-2402-00-3&doc=FOT (Register with ProRail)",null,null,"Z-907175","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007806-2423",null,">","Willemstunnel Zuid","Willemstunnel Noord",2024,2024,5,5,"2024-02-03","01:00:00","2024-02-04","17:00:00","1d 16:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen van LO's (20 sts)  nabij Rotterdam Lombardijen en Rotterdam Stadion * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2423-00-4&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007806-2460",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,5,6,"2024-02-03","23:00:00","2024-02-05","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging diverse LO's  op en nabij emplacement Kijfhoek. * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2460-00-5&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-24B1",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2024,2024,5,6,"2024-02-03","23:00:00","2024-02-05","07:00:00","1d 08:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-24B1-00-3&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005300-2404",null,">","Amsterdam Zaanstraat","Amsterdam Zaanstraat",2024,2024,5,6,"2024-02-04","01:00:00","2024-02-05","05:00:00","1d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"PVE-9 Vervangen zijwaartse bevestigingen * More details: https://btd-planner.prorail.nl?taak=IO-L-005300-2404-00-5&doc=FOT (Register with ProRail)",null,null,"L-005300","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007202-03",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,5,7,"2024-01-29","07:00:00","2024-02-12","07:00:00","13d 00:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"Ombouw zwitserskruis, wissel 3577 * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-03-00-8&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005442-2406",null,">","Amersfoort Centraal","Amersfoort Centraal",2024,2024,5,6,"2024-02-03","01:00:00","2024-02-05","01:00:00","1d 00:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Vernieuwen spoortak * More details: https://btd-planner.prorail.nl?taak=IO-L-005442-2406-00-5&doc=FOT (Register with ProRail)",null,null,"L-005442","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005445-2404",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,5,6,"2024-02-03","01:00:00","2024-02-05","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2404-00-2&doc=FOT (Register with ProRail)",null,null,"L-005445","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R480400-05xl",null,">","Waalhaven Zuid","Waalhaven Zuid",2024,2024,5,6,"2024-02-03","23:00:00","2024-02-05","07:00:00","1d 08:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden Waalhaven Blusleiding: * More details: https://btd-planner.prorail.nl?taak=IO-R-480400-05xl-00-2&doc=FOT (Register with ProRail)",null,null,"R-480400","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007202-wk05",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,5,7,"2024-01-29","07:00:00","2024-02-12","07:00:00","13d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Zwitsers kruis * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-wk05-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2450",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2024,2024,5,6,"2024-02-03","23:00:00","2024-02-05","07:00:00","1d 08:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2450-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00006-TS05",null,">","Waalhaven Zuid","Waalhaven Zuid",2024,2024,5,6,"2024-02-03","23:00:00","2024-02-05","07:00:00","1d 08:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Vernieuwen overweg * More details: https://btd-planner.prorail.nl?taak=IO-K-X00006-TS05-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00006","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","Z907175-2403",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,6,7,"2024-02-10","01:00:00","2024-02-12","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren hem boog spoor 9, 10 * More details: https://btd-planner.prorail.nl?taak=IO-Z-907175-2403-00-3&doc=FOT (Register with ProRail)",null,null,"Z-907175","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","Z907175-MA01",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,6,7,"2024-02-10","01:15:00","2024-02-12","05:15:00","2d 04:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Conserveren perronkappen Asd Sloterdijk. (t.b.v. in-/uitzet groot materieel voor WBI 78059A SRNL) * More details: https://btd-planner.prorail.nl?taak=IO-Z-907175-MA01-00-2&doc=FOT (Register with ProRail)",null,null,"Z-907175","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005363-2403",null,">","Venserpolder aansl.","Venserpolder aansl.",2024,2024,6,7,"2024-02-10","01:00:00","2024-02-12","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Plaatsen hekwerk locatie Diemen Zuid. * More details: https://btd-planner.prorail.nl?taak=IO-L-005363-2403-00-3&doc=FOT (Register with ProRail)",null,null,"L-005363","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005445-2403",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,6,7,"2024-02-10","01:30:00","2024-02-12","05:30:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2403-00-2&doc=FOT (Register with ProRail)",null,null,"L-005445","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005100-Bru",null,">","Singelgracht aansl.","Singelgracht aansl.",2024,2024,6,6,"2024-02-09","01:27:00","2024-02-10","05:27:00","1d 04:00","continuous","Maintenance","","LT+ST",null,null,null,null,null,null,null,null,"Brugovergangen vervangen spoor B5-B6 , SA-SB (4 stuks) * More details: https://btd-planner.prorail.nl?taak=IO-L-005100-Bru-00-7&doc=FOT (Register with ProRail)",null,null,"L-005100","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE041-2402",null,">","Amsterdam Centraal","Amsterdam Centraal",2024,2024,7,8,"2024-02-17","01:00:00","2024-02-19","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden Westknoop * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE041-2402-00-4&doc=FOT (Register with ProRail)",null,null,"R-3AE041","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007806-2422",null,">","Willemstunnel Zuid","Willemstunnel Noord",2024,2024,8,9,"2024-02-24","01:12:00","2024-02-26","05:12:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen van LO's * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2422-00-10&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006108-2402",null,">","Zevenbergschenhoek aansl.","HSL Breda grens",2024,2024,8,9,"2024-02-24","00:15:00","2024-02-26","05:45:00","2d 05:30","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Schuilingervliet-Stabiliteit baan terugbrengen-Herstelwerkzaamheden-Spoorstaafschades-Randelementen * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2402-00-7&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2408",null,">","Rotterdam Stadion","Rotterdam Stadion",2024,2024,8,8,"2024-02-24","01:12:00","2024-02-24","13:12:00","0d 12:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI steller 879 door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2408-00-5&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007202-W8",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,8,8,"2024-02-19","06:30:00","2024-02-25","17:30:00","6d 11:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Testen Bundel 6-4 - Week 8 * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-W8-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","Z907175-2404",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,9,10,"2024-03-02","01:30:00","2024-03-04","05:30:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren hem boog spoor 9, 10 * More details: https://btd-planner.prorail.nl?taak=IO-Z-907175-2404-00-2&doc=FOT (Register with ProRail)",null,null,"Z-907175","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","Z907175-MA02",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,9,10,"2024-03-02","01:30:00","2024-03-04","05:30:00","2d 04:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Conserveren perronkappen Asd Sloterdijk. (t.b.v. in-/uitzet groot materieel voor WBI SRNL) * More details: https://btd-planner.prorail.nl?taak=IO-Z-907175-MA02-00-2&doc=FOT (Register with ProRail)",null,null,"Z-907175","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005445-2405",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,9,10,"2024-03-02","01:30:00","2024-03-04","05:30:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2405-00-3&doc=FOT (Register with ProRail)",null,null,"L-005445","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007202-W9",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,9,9,"2024-02-26","06:30:00","2024-03-03","17:30:00","6d 11:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Testen Bundel 6-4 - Week 9 * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-W9-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","Z907175-2405",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,10,11,"2024-03-09","01:00:00","2024-03-11","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren hem boog spoor 9, 10 * More details: https://btd-planner.prorail.nl?taak=IO-Z-907175-2405-00-3&doc=FOT (Register with ProRail)",null,null,"Z-907175","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007806-2413",null,">","Zwijndrecht","Zwijndrecht",2024,2024,10,11,"2024-03-09","01:00:00","2024-03-11","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging diverse LO's (ca. 14 sts) regio RZ ter hoogte van de perronsporen 1, 2, 15, 16, 20 en 21 op station Dordrecht * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2413-00-5&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008103-2403",null,">","Zwijndrecht","Zwijndrecht",2024,2024,10,10,"2024-03-09","01:00:00","2024-03-10","01:00:00","0d 00:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen van diverse rijdraden op het baanvak Ddr-Brd * More details: https://btd-planner.prorail.nl?taak=IO-K-008103-2403-00-3&doc=FOT (Register with ProRail)",null,null,"K-008103","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2401",null,">","Wantijbrug - bij Dordrecht","Wantijbrug - bij Dordrecht",2024,2024,10,11,"2024-03-08","21:00:00","2024-03-11","05:00:00","2d 08:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 13, 33, 45, 53, 65, 73 en 85 door de NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2401-00-3&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005445-2406",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,10,11,"2024-03-09","01:30:00","2024-03-11","05:30:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2406-00-3&doc=FOT (Register with ProRail)",null,null,"L-005445","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007202-W10",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,10,10,"2024-03-04","06:30:00","2024-03-10","17:30:00","6d 11:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Testen Bundel 6-4 - Week 10 * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-W10-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005429-2402",null,">","Venserpolder aansl.","Venserpolder aansl.",2024,2024,11,12,"2024-03-16","01:24:00","2024-03-18","05:24:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV met spoorstaafvervanging, dwarsliggers, bevestigingsmiddelen en ballastbed te A'dam Dijksgracht-Amstel. * More details: https://btd-planner.prorail.nl?taak=IO-L-005429-2402-00-3&doc=FOT (Register with ProRail)",null,null,"L-005429","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007209-11RT",null,">","Rotterdam Centraal","Rotterdam Centraal",2024,2024,11,12,"2024-03-16","01:00:00","2024-03-18","01:00:00","1d 00:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Voorbereidende werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-007209-11RT-00-3&doc=FOT (Register with ProRail)",null,null,"K-007209","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004902-2413",null,">","Zevenbergen inhaalsp.","Roosendaal",2024,2024,11,12,"2024-03-16","01:10:00","2024-03-18","05:10:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2413-00-5&doc=FOT (Register with ProRail)",null,null,"M-004902","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007202-W11",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,11,11,"2024-03-11","06:30:00","2024-03-17","17:30:00","6d 11:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Testen Bundel 6-4 - Week 11 * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-W11-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z907175-2406",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,12,13,"2024-03-23","01:15:00","2024-03-25","05:15:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren hem boog spoor 9, 10 * More details: https://btd-planner.prorail.nl?taak=IO-Z-907175-2406-00-3&doc=FOT (Register with ProRail)",null,null,"Z-907175","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005445-2407",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,12,13,"2024-03-23","01:15:00","2024-03-25","05:15:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2407-00-3&doc=FOT (Register with ProRail)",null,null,"L-005445","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004902-2411",null,">","Roosendaal","Roosendaal",2024,2024,12,13,"2024-03-23","05:00:00","2024-03-30","05:00:00","7d 00:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"vernieuwen van wissels en sporen * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2411-00-5&doc=FOT (Register with ProRail)",null,null,"M-004902","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007202-W12",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,12,12,"2024-03-18","06:30:00","2024-03-24","17:30:00","6d 11:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Testen Bundel 6-4 - Week 12 * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-W12-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K005837-4120",null,">","Zwijndrecht","Zwijndrecht",2024,2024,12,13,"2024-03-23","13:40:00","2024-03-25","05:40:00","1d 16:00","continuous","Maintenance","","LT+ST",null,null,null,null,null,null,null,null,"IO-KT. Werkzaamheden BROM-brugovergang. * More details: https://btd-planner.prorail.nl?taak=IO-K-005837-4120-00-5&doc=FOT (Register with ProRail)",null,null,"K-005837","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007806-2461",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,13,14,"2024-03-30","19:00:00","2024-04-02","00:00:00","2d 05:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Vervanging diverse LO's * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2461-00-5&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-24B2",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2024,2024,13,14,"2024-03-30","19:00:00","2024-04-02","00:00:00","2d 05:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-24B2-00-3&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007202-W13",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,13,13,"2024-03-25","06:30:00","2024-03-29","17:30:00","4d 11:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Testen Bundel 6-4 - Week 13 * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-W13-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007202-05",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,13,14,"2024-03-30","19:00:00","2024-04-02","00:00:00","2d 05:00","continuous","Signal","","LT+ST",null,null,null,null,null,null,null,null,"Omklap bundels 6-4 -> 3-1 + ebs wijziging * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-05-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006613-2451",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2024,2024,13,13,"2024-03-29","01:25:00","2024-03-29","15:25:00","0d 14:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"TTI vervanging SCADA (verwerken restpunten, integraal testen) * More details: https://btd-planner.prorail.nl?taak=IO-K-006613-2451-00-4&doc=FOT (Register with ProRail)",null,null,"K-006613","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R3HRB01-TVP4",null,">","Westelijke splitsing Blijdorp aansl","Westelijke splitsing Blijdorp aansl",2024,2024,13,14,"2024-03-30","00:50:00","2024-04-01","05:50:00","2d 05:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Voorbereidende werkzaamheden Sdm * More details: https://btd-planner.prorail.nl?taak=IO-R-3HRB01-TVP4-00-7&doc=FOT (Register with ProRail)",null,null,"R-3HRB01","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2451",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2024,2024,13,14,"2024-03-30","19:00:00","2024-04-02","00:00:00","2d 05:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2451-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007202-06",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,14,51,"2024-04-01","00:00:00","2024-12-22","23:00:00","265d 23:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Ombouw bundels 3-1 * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-06-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004902-2405",null,">","Roosendaal","Vlakebrug o/h Kanaal door Zuid-Beveland",2024,2024,14,15,"2024-04-06","01:00:00","2024-04-08","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2405-00-8&doc=FOT (Register with ProRail)",null,null,"M-004902","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004902-2455",null,">","Arnemuiden","Vlissingen Souburg",2024,2024,14,15,"2024-04-06","01:00:00","2024-04-08","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2455-00-4&doc=FOT (Register with ProRail)",null,null,"M-004902","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2408",null,">","Amsterdam Westhaven West","Amsterdam Westhaven West",2024,2024,14,15,"2024-04-06","01:00:00","2024-04-11","01:00:00","4d 00:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"BBV, vernieuwen sporen en wissels. * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2408-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2409",null,">","Amsterdam Westhaven","Amsterdam Westhaven",2024,2024,15,16,"2024-04-14","01:00:00","2024-04-17","01:00:00","2d 00:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"BBV, vernieuwen sporen en wissels. ingieten Harmelen ovw * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2409-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z907175-2407",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,16,17,"2024-04-20","01:15:00","2024-04-22","05:15:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren hem boog spoor 9, 10 * More details: https://btd-planner.prorail.nl?taak=IO-Z-907175-2407-00-3&doc=FOT (Register with ProRail)",null,null,"Z-907175","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007806-2450",null,">","Zwijndrecht","Zwijndrecht",2024,2024,16,17,"2024-04-20","01:30:00","2024-04-22","05:30:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging diverse LO's op geo 116 tussen ca. km 31.600 en ca. km 33.100 * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2450-00-8&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006108-2403",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2024,2024,16,17,"2024-04-20","00:15:00","2024-04-22","05:45:00","2d 05:30","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Schuilingervliet-Stabiliteit baan terugbrengen-Herstelwerkzaamheden-Spoorstaafschades-Randelementen * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2403-00-5&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004902-2408",null,">","Lage Zwaluwe","Lage Zwaluwe",2024,2024,16,17,"2024-04-20","01:00:00","2024-04-22","05:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden, vernieuwen wisselstellers en vervangen rijdraad * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2408-00-5&doc=FOT (Register with ProRail)",null,null,"M-004902","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2405",null,">","Amsterdam Westhaven","Amsterdam Westhaven",2024,2024,16,17,"2024-04-20","01:00:00","2024-04-22","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"BBV * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2405-00-4&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z9ASA01-2406",null,">","Duivendrecht","Duivendrecht",2024,2024,18,18,"2024-04-30","01:00:00","2024-05-02","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Keerwandvernieuwing sp 1+4 en vervangen hemelwaterafvoeren * More details: https://btd-planner.prorail.nl?taak=IO-Z-9ASA01-2406-00-2&doc=FOT (Register with ProRail)",null,null,"Z-9ASA01","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z9ASA01-2405",null,">","Duivendrecht","Duivendrecht",2024,2024,18,18,"2024-04-29","01:00:00","2024-05-01","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Keerwandvernieuwing sp 1+4 en vervangen hemelwaterafvoeren * More details: https://btd-planner.prorail.nl?taak=IO-Z-9ASA01-2405-00-2&doc=FOT (Register with ProRail)",null,null,"Z-9ASA01","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z9ASA01-2408",null,">","Duivendrecht","Duivendrecht",2024,2024,18,18,"2024-05-03","01:00:00","2024-05-05","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Keerwandvernieuwing sp 1+4 en vervangen hemelwaterafvoeren * More details: https://btd-planner.prorail.nl?taak=IO-Z-9ASA01-2408-00-2&doc=FOT (Register with ProRail)",null,null,"Z-9ASA01","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z9ASA01-2407",null,">","Duivendrecht","Duivendrecht",2024,2024,18,18,"2024-05-01","01:00:00","2024-05-03","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Keerwandvernieuwing sp 1+4 en vervangen hemelwaterafvoeren * More details: https://btd-planner.prorail.nl?taak=IO-Z-9ASA01-2407-00-2&doc=FOT (Register with ProRail)",null,null,"Z-9ASA01","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007806-2414",null,">","Zwijndrecht","Zwijndrecht",2024,2024,18,19,"2024-05-04","01:00:00","2024-05-06","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging diverse LO's (ca. 11 sts) regio RZ ter hoogte van de perronsporen 3, 4, 5 en 6 op station Dordrecht geo 542 * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2414-00-12&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005222-2412",null,">","Venserpolder aansl.","Venserpolder aansl.",2024,2024,18,18,"2024-05-04","01:00:00","2024-05-04","21:00:00","0d 20:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 3201-1 en 3201-2 * More details: https://btd-planner.prorail.nl?taak=IO-L-005222-2412-00-3&doc=FOT (Register with ProRail)",null,null,"L-005222","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005222-2405",null,">","Singelgrachtbrug","Singelgrachtbrug",2024,2024,18,18,"2024-04-29","01:00:00","2024-05-01","05:00:00","2d 04:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"Vervangen EBI-switches voor NSE-stellers van 9 wissels, te weten: 67A, 67B, 159A, 157B, 155A, 161B, 147A, 151A en 149B. * More details: https://btd-planner.prorail.nl?taak=IO-L-005222-2405-00-2&doc=FOT (Register with ProRail)",null,null,"L-005222","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005360-24IB",null,">","Duivendrecht","Duivendrecht",2024,2024,18,18,"2024-05-03","01:00:00","2024-05-05","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren kunstwerken * More details: https://btd-planner.prorail.nl?taak=IO-L-005360-24IB-00-3&doc=FOT (Register with ProRail)",null,null,"L-005360","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005360-24BB",null,">","Duivendrecht","Duivendrecht",2024,2024,18,18,"2024-05-01","01:00:00","2024-05-03","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren kunstwerken * More details: https://btd-planner.prorail.nl?taak=IO-L-005360-24BB-00-3&doc=FOT (Register with ProRail)",null,null,"L-005360","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2403",null,">","Amsterdam Westhaven","Amsterdam Westhaven",2024,2024,19,20,"2024-05-12","01:00:00","2024-05-13","07:00:00","1d 06:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Vernieuwen ingietmassa harmelen overweg * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2403-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R3HRB01-TP5",null,">","Westelijke splitsing Blijdorp aansl","Westelijke splitsing Blijdorp aansl",2024,2024,19,20,"2024-05-07","01:15:00","2024-05-13","05:15:00","6d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"werkzaamheden aan ter voorbereiding op de 4-sporig gebruik Schiedam Rotterdam op de corridor Rotterdam Delft * More details: https://btd-planner.prorail.nl?taak=IO-R-3HRB01-TP5-00-4&doc=FOT (Register with ProRail)",null,null,"R-3HRB01","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-24B3",null,">","Rotterdam Lombardijen","Waalhaven Zuid aansl Zuid",2024,2024,20,21,"2024-05-18","19:00:00","2024-05-20","23:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-24B3-00-3&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R3AE041-2403",null,">","Amsterdam Centraal","Amsterdam Centraal",2024,2024,20,21,"2024-05-18","01:00:00","2024-05-20","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden Westknoop * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE041-2403-00-3&doc=FOT (Register with ProRail)",null,null,"R-3AE041","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007208-2407",null,">","IJsselmonde aansl.","Waalhaven Zuid aansl. Noord",2024,2024,20,21,"2024-05-18","19:00:00","2024-05-20","03:00:00","1d 08:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2407-00-3&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007202-08",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,20,21,"2024-05-18","19:00:00","2024-05-20","23:00:00","2d 04:00","continuous","Catenary","","ST",null,null,null,null,null,null,null,null,"- aanpassen bovenleiding - inbouwen strail - asfalteren - inbouwen compensatielassen * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-08-00-1&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004942-2410",null,">","Moerdijk","Moerdijk",2024,2024,20,21,"2024-05-18","01:00:00","2024-05-20","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004942-2410-00-3&doc=FOT (Register with ProRail)",null,null,"M-004942","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2402",null,">","Amsterdam Westhaven","Amsterdam Westhaven",2024,2024,20,21,"2024-05-19","01:00:00","2024-05-20","00:55:00","0d 23:55","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"BBV * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2402-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R3HRB01-BS3c",null,">","Rotterdam Centraal","Rotterdam Centraal",2024,2024,20,22,"2024-05-13","04:00:00","2024-05-27","04:00:00","13d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"werkzaamheden aan ter voorbereiding op de 4-sporig gebruik Schiedam Rotterdam op de corridor Rotterdam Delft * More details: https://btd-planner.prorail.nl?taak=IO-R-3HRB01-BS3c-00-3&doc=FOT (Register with ProRail)",null,null,"R-3HRB01","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-24D3",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2024,2024,20,21,"2024-05-18","19:00:00","2024-05-20","23:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Spoorvernieuwing Dintelhavenbrug * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-24D3-00-3&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2452",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2024,2024,20,21,"2024-05-18","19:00:00","2024-05-20","23:00:00","2d 04:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2452-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z907175-2408",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,21,22,"2024-05-25","01:30:00","2024-05-27","05:30:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren hem boog spoor 9, 10 * More details: https://btd-planner.prorail.nl?taak=IO-Z-907175-2408-00-3&doc=FOT (Register with ProRail)",null,null,"Z-907175","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2401",null,">","Amsterdam Westhaven","Amsterdam Westhaven",2024,2024,21,22,"2024-05-26","01:00:00","2024-05-27","00:55:00","0d 23:55","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"BBV * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2401-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005445-2401",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,21,22,"2024-05-25","01:30:00","2024-05-27","05:30:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2401-00-3&doc=FOT (Register with ProRail)",null,null,"L-005445","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K008110-2451",null,">","Rotterdam Noord goed. West","Rotterdam Noord goed. West",2024,2024,21,22,"2024-05-25","01:00:00","2024-05-27","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-008110-2451-00-4&doc=FOT (Register with ProRail)",null,null,"K-008110","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005417-2411",null,">","Amsterdam Centraal","Amsterdam Centraal",2024,2024,21,22,"2024-05-25","01:00:00","2024-05-27","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Voorbereidende werkzaamheden IJ-viaduct * More details: https://btd-planner.prorail.nl?taak=IO-L-005417-2411-00-7&doc=FOT (Register with ProRail)",null,null,"L-005417","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007808-2411",null,">","Rotterdam Westelijke Splitsing","Rotterdam Westelijke Splitsing",2024,2024,21,21,"2024-05-25","01:24:00","2024-05-26","21:24:00","1d 20:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 407 A/B, 409 en 411 A/B door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2411-00-2&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007208-2410",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,22,23,"2024-06-01","01:00:00","2024-06-03","05:00:00","2d 04:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 2309, 2301 A/B, 2303 A en 2305 A/B door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2410-00-2&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2406",null,">","Amsterdam Westhaven","Amsterdam Westhaven",2024,2024,22,22,"2024-06-02","01:00:00","2024-06-02","17:00:00","0d 16:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"BBV * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2406-00-2&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005429-2406",null,">","Duivendrecht","Duivendrecht",2024,2024,22,23,"2024-06-01","01:00:00","2024-06-03","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV met spoorstaafvervanging, dwarsliggers, bevestigingsmiddelen en ballastbed * More details: https://btd-planner.prorail.nl?taak=IO-L-005429-2406-00-2&doc=FOT (Register with ProRail)",null,null,"L-005429","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2407",null,">","Amsterdam Westhaven","Amsterdam Westhaven",2024,2024,23,23,"2024-06-09","01:00:00","2024-06-09","17:00:00","0d 16:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"BBV * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2407-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007827-2450",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,24,24,"2024-06-12","17:00:00","2024-06-13","09:00:00","0d 16:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen luik van de beweegbare waterkering (Sophiatunnel) * More details: https://btd-planner.prorail.nl?taak=IO-K-007827-2450-00-2&doc=FOT (Register with ProRail)",null,null,"K-007827","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007501-TP4b",null,">","Willemstunnel Zuid","Willemstunnel Noord",2024,2024,24,25,"2024-06-15","01:00:00","2024-06-17","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV vernieuwing KM 43,326 tot 44,300 * More details: https://btd-planner.prorail.nl?taak=IO-K-007501-TP4b-00-3&doc=FOT (Register with ProRail)",null,null,"K-007501","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006108-2404",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2024,2024,24,25,"2024-06-15","01:00:00","2024-06-17","06:30:00","2d 05:30","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Schuilingervliet-Stabiliteit baan terugbrengen-Herstelwerkzaamheden-Spoorstaafschades-Randelementen * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2404-00-2&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006136-4BWS",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,24,24,"2024-06-13","09:00:00","2024-06-14","17:00:00","1d 08:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"BWK testen 2024  Sophiatunnel  LET OP: Niet tegelijk met BWK Pankantunnel en niet tegelijk met  TTI plannen * More details: https://btd-planner.prorail.nl?taak=IO-K-006136-4BWS-00-1&doc=FOT (Register with ProRail)",null,null,"K-006136","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005429-2403",null,">","Venserpolder aansl.","Venserpolder aansl.",2024,2024,25,26,"2024-06-22","01:00:00","2024-06-24","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV met bevestigingsmiddelen te A'dam Bijlmer - Utrecht Boog * More details: https://btd-planner.prorail.nl?taak=IO-L-005429-2403-00-1&doc=FOT (Register with ProRail)",null,null,"L-005429","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007107-HY02",null,">","Europoort","Europoort",2024,2024,26,27,"2024-06-29","23:00:00","2024-07-01","07:00:00","1d 08:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Spoorkruising met open ontgraving HY transport * More details: https://btd-planner.prorail.nl?taak=IO-K-007107-HY02-00-1&doc=FOT (Register with ProRail)",null,null,"K-007107","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-24B4",null,">","Rotterdam Lombardijen","Waalhaven Zuid aansl Zuid",2024,2024,26,27,"2024-06-29","23:00:00","2024-07-01","07:00:00","1d 08:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-24B4-00-3&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R552900-2401",null,">","Amsterdam Centraal","Amsterdam Centraal",2024,2024,26,28,"2024-06-29","01:00:00","2024-07-08","05:00:00","9d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden Stalling onder de sporen. Aanbrengen damwanden in perron 5. * More details: https://btd-planner.prorail.nl?taak=IO-R-552900-2401-00-2&doc=FOT (Register with ProRail)",null,null,"R-552900","2024-01-04","High",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z906096-2303",null,">","Amersfoort Centraal","Amersfoort Centraal",2024,2024,26,27,"2024-06-29","01:00:00","2024-07-01","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Conserveren staalconstructie perronkappen * More details: https://btd-planner.prorail.nl?taak=IO-Z-906096-2303-00-3&doc=FOT (Register with ProRail)",null,null,"Z-906096","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K008109-TVP7",null,">","Waalhaven Zuid aansl. Noord","Waalhaven Zuid aansl. Noord",2024,2024,26,27,"2024-06-29","23:00:00","2024-07-01","07:00:00","1d 08:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-TVP7-00-2&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R577000-2401",null,">","Amsterdam Centraal","Amsterdam Centraal",2024,2025,26,13,"2024-06-29","01:00:00","2025-03-28","00:00:00","271d 23:00","continuous","Bridge","","ST",null,null,null,null,null,null,null,null,"Betreft werkzaamheden 5de brug in het verlengde van spoor 14 + 15. Deze sporen zijn al op BVS buitendienst genomen. * More details: https://btd-planner.prorail.nl?taak=IO-R-577000-2401-00-1&doc=FOT (Register with ProRail)",null,null,"R-577000","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R3AE032-2401",null,">","Singelgracht aansl.","Singelgracht aansl.",2024,2024,26,27,"2024-06-29","01:00:00","2024-07-02","05:00:00","3d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Stap 1i, buiten exploitatie nemen spoor 14+15 en indienststellen spoor 1 en 2a. * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE032-2401-00-9&doc=FOT (Register with ProRail)",null,null,"R-3AE032","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2453",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2024,2024,26,27,"2024-06-29","23:00:00","2024-07-01","07:00:00","1d 08:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2453-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005417-2401",null,">","Amsterdam Centraal","Amsterdam Centraal",2024,2025,27,10,"2024-07-02","01:00:00","2025-03-08","00:00:00","248d 23:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Betreft werkzaamheden aan het IJ-viaduct onder spoor 14 + 15. Deze sporen zijn al op BVS buitendienst genomen. * More details: https://btd-planner.prorail.nl?taak=IO-L-005417-2401-00-2&doc=FOT (Register with ProRail)",null,null,"L-005417","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z180023-2450",null,">","Amersfoort Centraal","Amersfoort Centraal",2024,2024,27,27,"2024-07-04","01:00:00","2024-07-06","01:00:00","1d 00:00","continuous","Signal","","ST",null,null,null,null,null,null,null,null,"FOT stap A * More details: https://btd-planner.prorail.nl?taak=IO-Z-180023-2450-00-10&doc=FOT (Register with ProRail)",null,null,"Z-180023","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004917-2402",null,">","Zevenbergen inhaalsp.","Roosendaal",2024,2024,27,28,"2024-07-06","01:00:00","2024-07-08","05:00:00","2d 04:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2402-00-3&doc=FOT (Register with ProRail)",null,null,"M-004917","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R3HRB01-TP6",null,">","Willemstunnel Zuid","Rotterdam Westelijke Splitsing",2024,2024,28,30,"2024-07-13","00:00:00","2024-07-25","04:00:00","12d 04:00","continuous","Signal","","LT+ST",null,null,null,null,null,null,null,null,"Bouwen zettingsvrije plaat en seinverdichting Dt-Sdm. werkzaamheden aan ter voorbereiding op de 4-sporig gebruik Sdm Rtd * More details: https://btd-planner.prorail.nl?taak=IO-R-3HRB01-TP6-00-4&doc=FOT (Register with ProRail)",null,null,"R-3HRB01","2024-01-04","High",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K008130-2401",null,">","Zwijndrecht","Zwijndrecht",2024,2024,29,30,"2024-07-15","05:00:00","2024-07-26","05:00:00","11d 00:00","continuous","Bridge","","LT+ST",null,null,null,null,null,null,null,null,"vervangen ingegoten spoorstaven op de brug incl compensatielassen. * More details: https://btd-planner.prorail.nl?taak=IO-K-008130-2401-00-6&doc=FOT (Register with ProRail)",null,null,"K-008130","2024-01-04","High",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z907123-2402",null,">","Dordrecht","Dordrecht",2024,2024,32,34,"2024-08-10","01:00:00","2024-08-19","05:00:00","9d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"werkzaamheden aan scheefstand kolommen, perron 2 spant 8 * More details: https://btd-planner.prorail.nl?taak=IO-Z-907123-2402-00-5&doc=FOT (Register with ProRail)",null,null,"Z-907123","2024-01-04","High",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004942-2407",null,">","Lage Zwaluwe","Lage Zwaluwe",2024,2024,32,32,"2024-08-10","01:00:00","2024-08-11","05:00:00","1d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004942-2407-00-2&doc=FOT (Register with ProRail)",null,null,"M-004942","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004902-2402",null,">","Lage Zwaluwe","Lage Zwaluwe",2024,2024,32,34,"2024-08-10","01:00:00","2024-08-19","05:00:00","9d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2402-00-5&doc=FOT (Register with ProRail)",null,null,"M-004902","2024-01-04","High",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2402",null,">","Waalhaven Zuid","Waalhaven Zuid",2024,2024,33,34,"2024-08-17","01:00:00","2024-08-19","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster WR-20 + WR-21 (2x3275m sps) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2402-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-24B5",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2024,2024,34,35,"2024-08-24","23:00:00","2024-08-26","07:00:00","1d 08:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-24B5-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007806-2420",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2024,2024,34,34,"2024-08-24","23:00:00","2024-08-25","19:00:00","0d 20:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen van LO's (5 sts)  nabij Barendrecht Vork * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2420-00-3&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K008109-TVP8",null,">","Waalhaven Zuid","Waalhaven Zuid",2024,2024,34,35,"2024-08-24","23:00:00","2024-08-26","07:00:00","1d 08:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-TVP8-00-2&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2454",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2024,2024,34,35,"2024-08-24","23:00:00","2024-08-26","07:00:00","1d 08:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2454-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007501-TVP4",null,">","Willemstunnel Zuid","Willemstunnel Noord",2024,2024,36,37,"2024-09-07","01:00:00","2024-09-09","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV vernieuwing * More details: https://btd-planner.prorail.nl?taak=IO-K-007501-TVP4-00-6&doc=FOT (Register with ProRail)",null,null,"K-007501","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006108-2405",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2024,2024,36,37,"2024-09-07","01:00:00","2024-09-09","06:30:00","2d 05:30","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Schuilingervliet-Stabiliteit baan terugbrengen-Herstelwerkzaamheden-Spoorstaafschades-Randelementen * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2405-00-2&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007501-TVP2",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2024,2024,37,38,"2024-09-14","01:00:00","2024-09-16","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV vernieuwing * More details: https://btd-planner.prorail.nl?taak=IO-K-007501-TVP2-00-4&doc=FOT (Register with ProRail)",null,null,"K-007501","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007808-2410",null,">","Rotterdam Noord goed. Oost","Rotterdam Noord goed. Oost",2024,2024,37,37,"2024-09-14","01:00:00","2024-09-15","17:00:00","1d 16:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 293 A/B en  295A/B door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2410-00-1&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R488000-2401",null,">","Rotterdam Noord goed. West","Rotterdam Noord",2024,2024,37,38,"2024-09-14","01:00:00","2024-09-16","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Groene boog plaatsen ligger over spoor * More details: https://btd-planner.prorail.nl?taak=IO-R-488000-2401-00-1&doc=FOT (Register with ProRail)",null,null,"R-488000","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K008103-2402",null,">","Willemsdorp","Willemsdorp",2024,2024,38,38,"2024-09-21","00:00:00","2024-09-22","08:00:00","1d 08:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen van diverse rijdraden op het baanvak Zlw - Ddr * More details: https://btd-planner.prorail.nl?taak=IO-K-008103-2402-00-5&doc=FOT (Register with ProRail)",null,null,"K-008103","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007806-2427",null,">","Zwijndrecht","Zwijndrecht",2024,2024,38,39,"2024-09-21","01:00:00","2024-09-23","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging diverse LO's (ca. 19 sts) regio RZ ter hoogte van de perronsporen 2, 3 en 4 op station Dordrecht geo 542 * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2427-00-8&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004902-2412",null,">","Zevenbergen inhaalsp.","Roosendaal",2024,2024,38,39,"2024-09-21","01:00:00","2024-09-23","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2412-00-2&doc=FOT (Register with ProRail)",null,null,"M-004902","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004917-2404",null,">","Zevenbergen inhaalsp.","Roosendaal",2024,2024,38,40,"2024-09-21","05:00:00","2024-09-30","05:00:00","9d 00:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2404-00-4&doc=FOT (Register with ProRail)",null,null,"M-004917","2024-01-04","High",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z907452-2402",null,">","Amersfoort Centraal","Amersfoort Centraal",2024,2024,38,39,"2024-09-21","01:00:00","2024-09-23","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Vervangen roltrap op perronspoor 6-7 (AMF-ROL-001) * More details: https://btd-planner.prorail.nl?taak=IO-Z-907452-2402-00-1&doc=FOT (Register with ProRail)",null,null,"Z-907452","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004849-2401",null,">","Zevenbergen inhaalsp.","Roosendaal",2024,2024,38,40,"2024-09-16","05:00:00","2024-09-30","05:00:00","14d 00:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwing baanlichaam, ballast, dwarsliggers, spoorstaven, overwegen en perrons. * More details: https://btd-planner.prorail.nl?taak=IO-M-004849-2401-00-2&doc=FOT (Register with ProRail)",null,null,"M-004849","2024-01-04","High",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005445-2408",null,">","Radarweg aansl.","Radarweg aansl.",2024,2024,39,40,"2024-09-28","01:15:00","2024-09-30","05:15:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen regelbare bevestiging * More details: https://btd-planner.prorail.nl?taak=IO-L-005445-2408-00-6&doc=FOT (Register with ProRail)",null,null,"L-005445","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z906096-2302",null,">","Amersfoort Centraal","Amersfoort Centraal",2024,2024,39,40,"2024-09-28","01:00:00","2024-09-30","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Conserveren staalconstructie perronkappen * More details: https://btd-planner.prorail.nl?taak=IO-Z-906096-2302-00-2&doc=FOT (Register with ProRail)",null,null,"Z-906096","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007808-2412",null,">","Rotterdam Westelijke Splitsing","Rotterdam Westelijke Splitsing",2024,2024,39,39,"2024-09-29","01:00:00","2024-09-29","19:00:00","0d 18:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI steller 391 & 401 door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2412-00-2&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006108-2406",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2024,2024,41,42,"2024-10-12","01:00:00","2024-10-14","06:30:00","2d 05:30","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Schuilingervliet-Stabiliteit baan terugbrengen-Herstelwerkzaamheden-Spoorstaafschades-Randelementen * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2406-00-2&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005424-2406",null,">","Amsterdam Zaanstraat","Amsterdam Zaanstraat",2024,2024,41,41,"2024-10-13","01:00:00","2024-10-13","13:00:00","0d 12:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"lichtmasten thv spoor 21 22 23 * More details: https://btd-planner.prorail.nl?taak=IO-L-005424-2406-00-4&doc=FOT (Register with ProRail)",null,null,"L-005424","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004902-2409",null,">","Lage Zwaluwe","Lage Zwaluwe",2024,2024,41,42,"2024-10-12","01:00:00","2024-10-14","05:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden, vernieuwen wisselstellers en vervangen rijdraad * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2409-00-3&doc=FOT (Register with ProRail)",null,null,"M-004902","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007806-2405",null,">","Zwijndrecht","Zwijndrecht",2024,2024,42,43,"2024-10-19","01:00:00","2024-10-21","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging diverse LO's op geo 116 tussen ca. km 31.600 en ca. km 33.100 * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2405-00-9&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004902-2407",null,">","Lage Zwaluwe","Roosendaal",2024,2024,42,43,"2024-10-19","01:00:00","2024-10-21","05:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden, vernieuwen wisselstellers en vervangen rijdraad * More details: https://btd-planner.prorail.nl?taak=IO-M-004902-2407-00-5&doc=FOT (Register with ProRail)",null,null,"M-004902","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R3HRB01-BS3d",null,">","Rotterdam Centraal","Rotterdam Centraal",2024,2024,42,44,"2024-10-19","07:00:00","2024-10-29","18:00:00","10d 11:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"werkzaamheden aan ter voorbereiding op de 4-sporig gebruik Schiedam Rotterdam op de corridor Rotterdam Delft * More details: https://btd-planner.prorail.nl?taak=IO-R-3HRB01-BS3d-00-2&doc=FOT (Register with ProRail)",null,null,"R-3HRB01","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z907452-2401",null,">","Amersfoort Centraal","Amersfoort Centraal",2024,2024,43,44,"2024-10-26","01:00:00","2024-10-28","04:00:00","2d 03:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Vervangen roltrap op perronspoor 4-5 (AMF-ROL-002) * More details: https://btd-planner.prorail.nl?taak=IO-Z-907452-2401-00-1&doc=FOT (Register with ProRail)",null,null,"Z-907452","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007202-09",null,">","Kijfhoek zuid","Kijfhoek zuid",2024,2024,43,49,"2024-10-21","06:00:00","2024-12-02","05:00:00","41d 23:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"SAT2 bundels 3-1. testwerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-007202-09-00-2&doc=FOT (Register with ProRail)",null,null,"K-007202","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R472600-2401",null,">","Venserpolder aansl.","Venserpolder aansl.",2024,2024,43,44,"2024-10-26","01:00:00","2024-10-28","04:00:00","2d 03:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Plaatsen liftschacht * More details: https://btd-planner.prorail.nl?taak=IO-R-472600-2401-00-2&doc=FOT (Register with ProRail)",null,null,"R-472600","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005424-2404",null,">","Singelgrachtbrug","Singelgrachtbrug",2024,2024,44,44,"2024-11-02","01:00:00","2024-11-02","13:00:00","0d 12:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"spoor SA lichtmasten * More details: https://btd-planner.prorail.nl?taak=IO-L-005424-2404-00-1&doc=FOT (Register with ProRail)",null,null,"L-005424","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R3HRB01-TVP7",null,">","Willemstunnel Zuid","Rotterdam Westelijke Splitsing",2024,2024,44,45,"2024-10-29","18:00:00","2024-11-04","04:00:00","5d 10:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"werkzaamheden t.b.v. het indienststellen van 4-sporen ( Sdm Rtd ) * More details: https://btd-planner.prorail.nl?taak=IO-R-3HRB01-TVP7-00-2&doc=FOT (Register with ProRail)",null,null,"R-3HRB01","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2405",null,">","Maasvlakte aansl.","Maasvlakte aansl.",2024,2024,46,47,"2024-11-16","12:00:00","2024-11-18","12:00:00","2d 00:00","continuous","Track & Rail","","LT",null,null,null,null,null,null,null,null,"Cluster ME-08 (2x 1:9 GW en ca. 327m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2405-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007808-2407",null,">","Gouda","Gouda",2024,2024,47,47,"2024-11-24","01:00:00","2024-11-24","21:00:00","0d 20:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vervangen wisselstellers 167A en 167B EBI door NSE-4 / NSE-S * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2407-00-1&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2401",null,">","IJsselmonde aansl.","IJsselmonde aansl.",2024,2024,48,49,"2024-11-30","01:00:00","2024-12-02","05:00:00","2d 04:00","continuous","Track & Rail","","LT",null,null,null,null,null,null,null,null,"Cluster IE-05 + IE-08 (1x 1:9 GW en ca. 204m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2401-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007808-2409",null,">","Rotterdam Centraal","Rotterdam Centraal",2024,2024,49,49,"2024-12-07","01:00:00","2024-12-07","19:00:00","0d 18:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"Vervangen EBI steller 393 A/B * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2409-00-1&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2412",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2024,2024,50,50,"2024-12-13","23:00:00","2024-12-15","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2412-00-2&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007022-2401",null,">","Maasvlakte aansl.","Maasvlakte aansl.",2024,2024,50,51,"2024-12-14","23:00:00","2024-12-16","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2401-00-4&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2404",null,">","Botlek","Botlek",2024,2024,50,51,"2024-12-14","23:00:00","2024-12-16","07:00:00","1d 08:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster BR-10 (1x 4,8m OVW en ca. 25m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2404-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007806-2421",null,">","Kijfhoek aansluiting noord","Kijfhoek aansluiting noord",2024,2024,50,50,"2024-12-14","23:00:00","2024-12-15","19:00:00","0d 20:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen van LO's (5 sts)  nabij Barendrecht Vork * More details: https://btd-planner.prorail.nl?taak=IO-K-007806-2421-00-3&doc=FOT (Register with ProRail)",null,null,"K-007806","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2455",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2024,2024,50,51,"2024-12-14","23:00:00","2024-12-16","07:00:00","1d 08:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2455-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K008421-2501",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,1,2,"2025-01-04","01:00:00","2025-01-06","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Diverse BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-008421-2501-00-4&doc=FOT (Register with ProRail)",null,null,"K-008421","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2504",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,1,2,"2025-01-04","01:00:00","2025-01-06","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2504-00-4&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2502",null,">","Amsterdam Coenhaven","Amsterdam Coenhaven",2025,2025,2,3,"2025-01-11","01:00:00","2025-01-13","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoortak, dwarsligger, spoorstaven, overweg, wegaansluiting. conserveren kunstwerk Koelwaterkanaal * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2502-00-2&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2501",null,">","IJsselmonde","IJsselmonde",2025,2025,4,5,"2025-01-25","01:00:00","2025-01-27","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster IE-14 + IE-17 + IE-20 (saneren 2x GW en 3x EW, incl. vernieuwen ca. 1515m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2501-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004917-2501",null,">","Zevenbergen inhaalsp.","Roosendaal",2025,2025,4,5,"2025-01-25","01:00:00","2025-01-27","05:00:00","2d 04:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2501-00-5&doc=FOT (Register with ProRail)",null,null,"M-004917","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2506",null,">","Zevenbergen inhaalsp.","Roosendaal",2025,2025,4,5,"2025-01-25","01:00:00","2025-01-27","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2506-00-3&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007808-2511",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,4,5,"2025-01-25","17:00:00","2025-01-27","05:00:00","1d 12:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 279 A/B en 283 A/B door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2511-00-2&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2510",null,">","Amsterdam Westhaven Goederen","Amsterdam Westhaven Goederen",2025,2025,5,6,"2025-02-01","01:00:00","2025-02-03","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoortak, spoorstaven en overweg.  saneren harmelen * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2510-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-25B1",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B1-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2503",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Signal","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2503-00-2&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2501",null,">","Maasvlakte aansl.","Maasvlakte aansl.",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2501-00-2&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2511",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2511-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006108-2502",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2025,2025,5,6,"2025-02-01","01:00:00","2025-02-03","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2502-00-7&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2507",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,5,5,"2025-02-01","23:00:00","2025-02-02","23:00:00","1d 00:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 2371 A/B, 2375, 2395 A/B, 2397 A/B en 2399 A/B door de NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2507-00-1&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2501",null,">","Waalhaven Zuid aansl. Noord","Waalhaven Zuid aansl. Noord",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2501-00-2&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2550",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2550-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2517",null,">","Europoort","Europoort",2025,2025,6,6,"2025-02-03","20:00:00","2025-02-05","00:00:00","1d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster ER-14 (ca. 409m sps) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2517-00-3&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2505",null,">","Waalhaven Zuid","Waalhaven Zuid",2025,2025,6,6,"2025-02-08","01:00:00","2025-02-09","09:00:00","1d 08:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster WR-07 + WR-08 (1x 1:9 GW en ca. 202m spoor + OVW) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2505-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K008401-RT18",null,">","Gouda","Gouda",2025,2025,6,6,"2025-02-08","01:00:00","2025-02-09","17:00:00","1d 16:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vernieuwen spoorstaven, spoortak, overwegbevloering, wissel. * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT18-00-2&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007808-2512",null,">","Rotterdam Westelijke Splitsing","Rotterdam Westelijke Splitsing",2025,2025,6,7,"2025-02-09","01:00:00","2025-02-10","01:00:00","0d 00:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 173 A/B, 199, 211 A/B, 251 A/B en 293A * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2512-00-3&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2511",null,">","Roosendaal","Bergen op Zoom",2025,2025,6,7,"2025-02-08","01:00:00","2025-02-10","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2511-00-5&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2504",null,">","Amsterdam Coenhaven","Amsterdam Coenhaven",2025,2025,7,7,"2025-02-15","01:00:00","2025-02-16","09:00:00","1d 08:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoorstaven, dwarsliggers en wegaansluiting * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2504-00-2&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE032-2506",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,7,8,"2025-02-15","01:00:00","2025-02-17","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"TVP tbv inbrengen van kabels in kabelkoker derde perron. * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE032-2506-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE032","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2502",null,">","Rotterdam Stadion","Rotterdam Stadion",2025,2025,8,9,"2025-02-22","01:00:00","2025-02-24","05:00:00","2d 04:00","continuous","Track & Rail","","LT",null,null,null,null,null,null,null,null,"Cluster IE-20 + IE-23 (ca. 826m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2502-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004966-2501",null,">","Roosendaal","Bergen op Zoom",2025,2025,10,10,"2025-03-08","01:00:00","2025-03-09","01:00:00","0d 00:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen rijdraden tussen Roosendaal (Rsd) en Bergen op Zoom (Bgn) * More details: https://btd-planner.prorail.nl?taak=IO-M-004966-2501-00-5&doc=FOT (Register with ProRail)",null,null,"M-004966","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2512",null,">","Roosendaal","Roosendaal grens",2025,2025,10,11,"2025-03-08","01:00:00","2025-03-10","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2512-00-3&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004897-FL02",null,">","Roosendaal","Roosendaal grens",2025,2025,10,11,"2025-03-08","01:00:00","2025-03-10","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren van spoorviaduct in 3 perioden van 52u * More details: https://btd-planner.prorail.nl?taak=IO-M-004897-FL02-00-4&doc=FOT (Register with ProRail)",null,null,"M-004897","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004987-2501",null,">","Roosendaal","Roosendaal grens",2025,2025,10,10,"2025-03-08","01:00:00","2025-03-09","05:00:00","1d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen sps (L+R) bij overweg Willem Dreesweg en vernieuwen spoortak kopspoor bij grens België * More details: https://btd-planner.prorail.nl?taak=IO-M-004987-2501-00-3&doc=FOT (Register with ProRail)",null,null,"M-004987","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2505",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,11,12,"2025-03-14","01:00:00","2025-03-17","05:00:00","3d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"vernieuwen wissel, spoortak en paden * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2505-00-2&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2507",null,">","Waalhaven Zuid","Waalhaven Zuid",2025,2025,11,12,"2025-03-15","08:00:00","2025-03-17","12:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster WR-18 (OVW 21m en ca. 31m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2507-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006108-2507",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2025,2025,11,12,"2025-03-15","01:00:00","2025-03-17","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2507-00-2&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005346-2530",null,">","Amersfoort Centraal","Amersfoort Centraal",2025,2025,11,11,"2025-03-10","01:00:00","2025-03-14","09:00:00","4d 08:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-L-005346-2530-00-6&doc=FOT (Register with ProRail)",null,null,"L-005346","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2503",null,">","Waalhaven Zuid","Waalhaven Zuid",2025,2025,12,13,"2025-03-22","01:00:00","2025-03-24","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster WE-19 (1x 1:9 EW, 2x 1:9 GW en ca. 60m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2503-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE032-2501",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,12,13,"2025-03-22","01:00:00","2025-03-29","01:00:00","6d 00:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Inbouwen nieuw wissel voor TVP stap 1J. Betreft wissel 2555 * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE032-2501-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE032","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2508",null,">","Waalhaven Zuid","Waalhaven Zuid",2025,2025,13,14,"2025-03-29","01:00:00","2025-03-31","06:00:00","2d 05:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster WR-19 + WR-22 (3x 1:9 GW en ca. 442m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2508-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007808-2509",null,">","Rotterdam Westelijke Splitsing","Rotterdam Westelijke Splitsing",2025,2025,13,14,"2025-03-29","01:00:00","2025-03-31","06:00:00","2d 05:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 255A, 259A, 271, 273B en 277A/B * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2509-00-1&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT04",null,">","Rotterdam Noord goed. West","Rotterdam Westelijke Splitsing",2025,2025,13,14,"2025-03-29","01:00:00","2025-03-31","06:00:00","2d 05:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen spoortak, overwegbevloering, inspectiepad, regelbare bevestiging, blokkenspoor, overgangsconstructie * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT04-00-3&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005346-2531",null,">","Amersfoort Centraal","Amersfoort Centraal",2025,2025,13,13,"2025-03-24","01:00:00","2025-03-26","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-L-005346-2531-00-2&doc=FOT (Register with ProRail)",null,null,"L-005346","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005346-2522",null,">","Amersfoort Centraal","Amersfoort Centraal",2025,2025,13,13,"2025-03-30","01:00:00","2025-03-30","18:00:00","0d 17:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Vernieuwen bevestigingsmiddelen * More details: https://btd-planner.prorail.nl?taak=IO-L-005346-2522-00-2&doc=FOT (Register with ProRail)",null,null,"L-005346","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R552900-2501",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,13,17,"2025-03-29","01:00:00","2025-04-21","06:00:00","23d 05:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden aan Fietsenstalling onder de sporen. Vrijdragend maken van het 4de perron. * More details: https://btd-planner.prorail.nl?taak=IO-R-552900-2501-00-1&doc=FOT (Register with ProRail)",null,null,"R-552900","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008421-2502",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,14,15,"2025-04-05","01:00:00","2025-04-07","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Diverse BBV werkzaamheden. * More details: https://btd-planner.prorail.nl?taak=IO-K-008421-2502-00-6&doc=FOT (Register with ProRail)",null,null,"K-008421","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2507",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,14,15,"2025-04-05","01:00:00","2025-04-07","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"vernieuwen spoorstaven incl. raildraagplaat. * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2507-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2510",null,">","Botlek","Botlek",2025,2025,14,15,"2025-04-06","08:00:00","2025-04-07","12:00:00","1d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster BR-02 (1x 1:9 GW) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2510-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2514",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,14,15,"2025-04-05","01:00:00","2025-04-07","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2514-00-5&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005346-2521",null,">","Amersfoort Centraal","Amersfoort Centraal",2025,2025,14,14,"2025-04-05","01:00:00","2025-04-06","05:00:00","1d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Vernieuwen bevestigingsmiddelen * More details: https://btd-planner.prorail.nl?taak=IO-L-005346-2521-00-1&doc=FOT (Register with ProRail)",null,null,"L-005346","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008718-TP01",null,">","Maasvlakte West","Maasvlakte West",2025,2025,15,16,"2025-04-07","08:00:00","2025-04-17","08:00:00","10d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Herstellen/in dienst stellen van tankplaat spoor 870 * More details: https://btd-planner.prorail.nl?taak=IO-K-008718-TP01-00-4&doc=FOT (Register with ProRail)",null,null,"K-008718","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2510",null,">","Roosendaal","Bergen op Zoom",2025,2025,15,16,"2025-04-12","01:00:00","2025-04-14","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2510-00-4&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-25B2",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2025,2025,16,17,"2025-04-19","07:00:00","2025-04-21","11:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B2-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2512",null,">","Botlek","Botlek",2025,2025,16,17,"2025-04-19","08:00:00","2025-04-21","08:00:00","2d 00:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster BR-20 (2x OVW 9,6m en ca. 55m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2512-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2502",null,">","Maasvlakte aansl.","Maasvlakte aansl.",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2502-00-3&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2520",null,">","Maasvlakte Europahaven zuid","Maasvlakte Europahaven zuid",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Track & Rail","","LT",null,null,null,null,null,null,null,null,"Cluster MR-04 (ca. 438 spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2520-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2501",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Signal","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2501-00-3&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2519",null,">","Maasvlakte Europahaven zuid","Maasvlakte Europahaven zuid",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-25","19:00:00","5d 00:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Cluster ME-13 (1x 1:9 EW, 6x 1:9 GW en ca. 153m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2519-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2512",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,16,17,"2025-04-19","23:00:00","2025-04-22","03:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2512-00-2&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R577400-2502",null,">","Europoort","Europoort",2025,2025,16,16,"2025-04-19","19:00:00","2025-04-20","07:00:00","0d 12:00","continuous","Catenary","","ST",null,null,null,null,null,null,null,null,"electrificering (aanpassen bovenleiding) * More details: https://btd-planner.prorail.nl?taak=IO-R-577400-2502-00-1&doc=FOT (Register with ProRail)",null,null,"R-577400","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2504",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 3569, 3623, 3633, 3635 en 3769 door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2504-00-1&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2502",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2502-00-3&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004987-2509",null,">","Moerdijk","Moerdijk",2025,2025,16,17,"2025-04-19","01:00:00","2025-04-22","05:00:00","3d 04:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vernieuwen spoortakken en 3 wissels * More details: https://btd-planner.prorail.nl?taak=IO-M-004987-2509-00-2&doc=FOT (Register with ProRail)",null,null,"M-004987","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2551",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2551-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004863-2502",null,">","Roosendaal","Roosendaal",2025,2025,17,39,"2025-04-24","07:00:00","2025-09-23","07:00:00","151d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Tankplaat verplaatsen. * More details: https://btd-planner.prorail.nl?taak=IO-M-004863-2502-00-2&doc=FOT (Register with ProRail)",null,null,"M-004863","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005509-2516",null,">","Singelgracht aansl.","Singelgracht aansl.",2025,2025,18,18,"2025-05-03","01:00:00","2025-05-04","01:00:00","0d 00:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen dwarsliggers en bevestigingsmiddelen. * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2516-00-1&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE032-2507",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,19,20,"2025-05-10","01:00:00","2025-05-12","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"TVP tbv inbrengen van kabels in kabelkoker derde perron. * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE032-2507-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE032","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2513",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,19,20,"2025-05-10","01:00:00","2025-05-12","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen dwarsligger, spoorstaven, bevestigingsmiddelen en spoorstaven * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2513-00-3&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005467-2507",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,19,20,"2025-05-11","21:00:00","2025-05-12","09:00:00","0d 12:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Werkzaamheden aan KW Noordzeeweg in lang nachtgat * More details: https://btd-planner.prorail.nl?taak=IO-L-005467-2507-00-3&doc=FOT (Register with ProRail)",null,null,"L-005467","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008421-2503",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,20,21,"2025-05-17","01:00:00","2025-05-19","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Diverse BBV werkzaamheden. * More details: https://btd-planner.prorail.nl?taak=IO-K-008421-2503-00-3&doc=FOT (Register with ProRail)",null,null,"K-008421","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004987-2512",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,20,21,"2025-05-17","01:00:00","2025-05-19","05:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen wisselstellers * More details: https://btd-planner.prorail.nl?taak=IO-M-004987-2512-00-3&doc=FOT (Register with ProRail)",null,null,"M-004987","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2515",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,20,21,"2025-05-17","01:00:00","2025-05-19","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2515-00-3&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006108-2509",null,">","Zevenbergschenhoek aansl.","HSL breda grens overloop",2025,2025,21,22,"2025-05-24","01:00:00","2025-05-26","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2509-00-1&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT12",null,">","Rotterdam Westelijke Splitsing","Rotterdam Westelijke Splitsing",2025,2025,21,22,"2025-05-24","01:00:00","2025-05-26","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen ballast, regelbare bevestiging, broekbalken * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT12-00-2&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005417-2510",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,21,22,"2025-05-24","01:00:00","2025-05-26","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Afwerken Ij-viaduct * More details: https://btd-planner.prorail.nl?taak=IO-L-005417-2510-00-3&doc=FOT (Register with ProRail)",null,null,"L-005417","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007206-25AA",null,">","Willemstunnel Zuid","Rotterdam Westelijke Splitsing",2025,2025,21,22,"2025-05-24","01:00:00","2025-05-26","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Indienstellen nieuwe IXL Rotterdam * More details: https://btd-planner.prorail.nl?taak=IO-K-007206-25AA-00-3&doc=FOT (Register with ProRail)",null,null,"K-007206","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE042-2501",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,21,22,"2025-05-25","01:00:00","2025-05-26","00:50:00","0d 23:50","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden stijgpunten perrons * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE042-2501-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE042","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2517",null,">","Amsterdam Zaanstraat","Amsterdam Zaanstraat",2025,2025,22,23,"2025-05-30","01:00:00","2025-06-02","05:00:00","3d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen sporen en wissels * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2517-00-1&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-25B3",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2025,2025,23,24,"2025-06-07","07:00:00","2025-06-09","11:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B3-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2514",null,">","Botlek Theemsweg aansl.","Botlek Theemsweg aansl.",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-10","11:00:00","2d 16:00","continuous","Track & Rail","","LT",null,null,null,null,null,null,null,null,"Cluster ER-05 + ER-06 (2x OVW 21m en ca. 235m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2514-00-3&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2521",null,">","Maasvlakte West","Maasvlakte West",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Track & Rail","","LT",null,null,null,null,null,null,null,null,"Cluster MR-06 + MR-07 + MR-08 (2x 1:9 GW en ca. 256 spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2521-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2502",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Signal","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2502-00-1&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R577400-2501",null,">","Europoort","Europoort",2025,2025,23,24,"2025-06-07","23:00:00","2025-06-10","03:00:00","2d 04:00","continuous","Catenary","","ST",null,null,null,null,null,null,null,null,"electrificering (aanpassen bovenleiding) * More details: https://btd-planner.prorail.nl?taak=IO-R-577400-2501-00-2&doc=FOT (Register with ProRail)",null,null,"R-577400","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2510",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 2371 A/B, 2375, 2395 A/B, 2397 A/B en 2399 A/B door de NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2510-00-1&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT19",null,">","Rotterdam Noord goed. West","Rotterdam Westelijke Splitsing",2025,2025,23,24,"2025-06-07","01:00:00","2025-06-09","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen spoortak, overwegbevloering, inspectiepad, regelbare bevestiging, blokkenspoor, overgangsconstructie * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT19-00-3&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2511",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,23,24,"2025-06-07","01:00:00","2025-06-10","05:00:00","3d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen dwarsligger, spoorstaven, bevestigingsmiddelen en spoorstaven en bouwen RIP * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2511-00-3&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2503",null,">","Waalhaven Zuid aansl. Noord","Waalhaven Zuid aansl. Noord",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2503-00-3&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2503",null,">","Maasvlakte aansl.","Maasvlakte aansl.",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2503-00-3&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2513",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2513-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2552",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2552-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT17",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,24,25,"2025-06-14","01:00:00","2025-06-16","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Vernieuwen spoortak, overwegbevloering, dwarsliggers, ballast, * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT17-00-2&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004966-2502",null,">","Roosendaal","Bergen op Zoom",2025,2025,25,26,"2025-06-21","01:00:00","2025-06-23","05:00:00","2d 04:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen rijdraden tussen Roosendaal (Rsd) en Bergen op Zoom (Bgn) * More details: https://btd-planner.prorail.nl?taak=IO-M-004966-2502-00-4&doc=FOT (Register with ProRail)",null,null,"M-004966","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004987-2502",null,">","Roosendaal","Vlakebrug o/h Kanaal door Zuid-Beveland",2025,2025,25,26,"2025-06-21","01:00:00","2025-06-23","05:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwingen (spoortakken, overwegbevloeringen, dwarsliggers + ballast, wissels, wisselverwarm.) en aanleggen drainage * More details: https://btd-planner.prorail.nl?taak=IO-M-004987-2502-00-6&doc=FOT (Register with ProRail)",null,null,"M-004987","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004897-FL03",null,">","Roosendaal","Roosendaal grens",2025,2025,25,26,"2025-06-21","01:00:00","2025-06-23","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren van spoorviaduct in 3 perioden van 52u * More details: https://btd-planner.prorail.nl?taak=IO-M-004897-FL03-00-3&doc=FOT (Register with ProRail)",null,null,"M-004897","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2509",null,">","Roosendaal","Roosendaal grens",2025,2025,25,26,"2025-06-21","01:00:00","2025-06-23","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2509-00-6&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005417-2511",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,26,27,"2025-06-28","01:00:00","2025-06-30","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Afwerken Ij-viaduct * More details: https://btd-planner.prorail.nl?taak=IO-L-005417-2511-00-4&doc=FOT (Register with ProRail)",null,null,"L-005417","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006146-2508",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,27,27,"2025-06-30","08:00:00","2025-07-05","08:00:00","5d 00:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"vervangen TTI * More details: https://btd-planner.prorail.nl?taak=IO-K-006146-2508-00-1&doc=FOT (Register with ProRail)",null,null,"K-006146","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007808-2510",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,27,28,"2025-07-06","02:00:00","2025-07-07","05:00:00","1d 03:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 221 A/B en 243 A door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2510-00-2&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006146-2507",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,28,28,"2025-07-07","08:00:00","2025-07-12","08:00:00","5d 00:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"vervangen TTI (A15 West) * More details: https://btd-planner.prorail.nl?taak=IO-K-006146-2507-00-2&doc=FOT (Register with ProRail)",null,null,"K-006146","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006146-2509",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,29,29,"2025-07-14","08:00:00","2025-07-19","08:00:00","5d 00:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"vervangen TTI (A15 West) * More details: https://btd-planner.prorail.nl?taak=IO-K-006146-2509-00-2&doc=FOT (Register with ProRail)",null,null,"K-006146","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT13",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,31,32,"2025-07-28","01:00:00","2025-08-04","05:00:00","7d 04:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vernieuwen wissels, bevestigingsmiddelen, spoortak, overwegbvloering Saneren wissels * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT13-00-4&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2515",null,">","Europoort","Europoort",2025,2025,31,32,"2025-08-02","08:00:00","2025-08-04","00:00:00","1d 16:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster ER-09 + ER-10 (OVW 26,4m en ca. 150m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2515-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-25B4",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B4-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2404",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Signal","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2404-00-1&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006108-2506",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2025,2025,31,32,"2025-08-02","01:00:00","2025-08-04","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2506-00-2&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE032-2508",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,31,32,"2025-08-02","01:00:00","2025-08-04","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"TVP tbv inbrengen van kabels in kabelkoker derde perron. * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE032-2508-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE032","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2514",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,31,31,"2025-08-02","23:00:00","2025-08-03","23:00:00","1d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 3311, 3313, 3315, 3317, 3319, 3321 en 3237A door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2514-00-4&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2519",null,">","Kijfhoek aansluiting noord","Waalhaven Zuid aansl. Noord",2025,2025,31,31,"2025-08-02","23:00:00","2025-08-03","23:00:00","1d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2519-00-1&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2504",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2504-00-2&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006136-5BWS",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"BWK testen 2025  Sophiatunnel  LET OP: Niet tegelijk met BWK Pankan tunnel en niet tegelijk met  TTI plannen * More details: https://btd-planner.prorail.nl?taak=IO-K-006136-5BWS-00-2&doc=FOT (Register with ProRail)",null,null,"K-006136","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008410-2502",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2025,2025,31,31,"2025-08-02","23:00:00","2025-08-03","15:00:00","0d 16:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen pompen * More details: https://btd-planner.prorail.nl?taak=IO-K-008410-2502-00-1&doc=FOT (Register with ProRail)",null,null,"K-008410","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2504",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2504-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2514",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2514-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2553",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2553-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2508",null,">","Amsterdam Westhaven Goederen","Amsterdam Westhaven Goederen",2025,2025,33,33,"2025-08-16","01:00:00","2025-08-17","09:00:00","1d 08:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"vernieuwen dwarsliggers en ballast * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2508-00-2&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2516",null,">","Europoort","Europoort",2025,2025,34,34,"2025-08-18","20:00:00","2025-08-20","00:00:00","1d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Cluster ER-14 (ca. 409m sps) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2516-00-4&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004917-2503",null,">","Zevenbergen inhaalsp.","Roosendaal",2025,2025,35,36,"2025-08-30","01:00:00","2025-09-01","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2503-00-2&doc=FOT (Register with ProRail)",null,null,"M-004917","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006108-2508",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2025,2025,36,37,"2025-09-06","01:00:00","2025-09-08","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2508-00-3&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008410-2503",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2025,2025,36,36,"2025-09-06","23:00:00","2025-09-07","15:00:00","0d 16:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen pompen * More details: https://btd-planner.prorail.nl?taak=IO-K-008410-2503-00-2&doc=FOT (Register with ProRail)",null,null,"K-008410","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE042-2502",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,36,36,"2025-09-04","01:00:00","2025-09-05","00:50:00","0d 23:50","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden stijgpunten perrons * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE042-2502-00-3&doc=FOT (Register with ProRail)",null,null,"R-3AE042","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2506",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,37,38,"2025-09-12","01:00:00","2025-09-15","05:00:00","3d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"verniewen, wissel, ballast, spoortak en paden. * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2506-00-4&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","Z906301-2501",null,">","Zwijndrecht","Zwijndrecht",2025,2025,37,38,"2025-09-13","01:00:00","2025-09-15","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren/ dakdekken * More details: https://btd-planner.prorail.nl?taak=IO-Z-906301-2501-00-2&doc=FOT (Register with ProRail)",null,null,"Z-906301","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT15",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,37,38,"2025-09-13","01:00:00","2025-09-15","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Vernieuwen sporen 21m, 22m, 23m, 25m, 26m * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT15-00-2&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2512",null,">","Singelgracht aansl.","Singelgracht aansl.",2025,2025,37,38,"2025-09-13","17:00:00","2025-09-15","05:00:00","1d 12:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen dwarsligger, spoorstaven, bevestigingsmiddelen en spoorstaven * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2512-00-4&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2502",null,">","Zwijndrecht","Zwijndrecht",2025,2025,37,38,"2025-09-13","01:00:00","2025-09-15","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2502-00-5&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008410-2501",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,37,38,"2025-09-13","01:00:00","2025-09-15","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen pompen * More details: https://btd-planner.prorail.nl?taak=IO-K-008410-2501-00-2&doc=FOT (Register with ProRail)",null,null,"K-008410","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008410-2505",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2025,2025,37,37,"2025-09-13","23:00:00","2025-09-14","11:00:00","0d 12:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen ventilatoren. * More details: https://btd-planner.prorail.nl?taak=IO-K-008410-2505-00-1&doc=FOT (Register with ProRail)",null,null,"K-008410","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005467-2508",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,37,37,"2025-09-13","21:00:00","2025-09-14","09:00:00","0d 12:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Werkzaamheden aan KW Noordzeeweg in lang nachtgat * More details: https://btd-planner.prorail.nl?taak=IO-L-005467-2508-00-3&doc=FOT (Register with ProRail)",null,null,"L-005467","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R551400-2501",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,37,38,"2025-09-13","01:00:00","2025-09-15","05:00:00","2d 04:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Aansluiten nieuwe opstelsporen en vernieuwen sporen * More details: https://btd-planner.prorail.nl?taak=IO-R-551400-2501-00-2&doc=FOT (Register with ProRail)",null,null,"R-551400","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-25B5",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-22","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B5-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2505",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-22","07:00:00","1d 08:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2505-00-1&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007808-2507",null,">","Rotterdam Westelijke Splitsing","Rotterdam Westelijke Splitsing",2025,2025,38,39,"2025-09-20","01:00:00","2025-09-22","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 173 A/B, 199, 211 A/B, 251 A/B en 293A * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2507-00-3&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2511",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,38,39,"2025-09-21","04:00:00","2025-09-22","04:00:00","0d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 2327, 3531, 2325 A/B, 2329 A/B en 2331A/B door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2511-00-3&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2515",null,">","Singelgracht aansl.","Singelgracht aansl.",2025,2025,38,38,"2025-09-20","01:00:00","2025-09-21","01:00:00","0d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Aanpassen talud, vervangen bevestigingsmiddelen * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2515-00-5&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2505",null,">","Waalhaven Zuid aansl. Noord","Waalhaven Zuid aansl. Noord",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-22","07:00:00","1d 08:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2505-00-2&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008423-2501",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-25","23:00:00","5d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Ombouw VPI naar nieuwe interlocking * More details: https://btd-planner.prorail.nl?taak=IO-K-008423-2501-00-5&doc=FOT (Register with ProRail)",null,null,"K-008423","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2505",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-23","03:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2505-00-5&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2515",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-22","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2515-00-2&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2554",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-22","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2554-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT14",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,39,40,"2025-09-27","01:00:00","2025-09-29","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Vernieuwen wissels 295A, 295B en 297, vernieuwen overwegbevloering, vernieuwen sporen * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT14-00-2&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2509",null,">","Amsterdam Westhaven Goederen","Amsterdam Westhaven Goederen",2025,2025,39,40,"2025-09-27","01:00:00","2025-09-29","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoortak, spoorstaven, overweg, en wegaansluiting * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2509-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2503",null,">","Amsterdam Coenhaven","Amsterdam Coenhaven",2025,2025,40,41,"2025-10-04","01:00:00","2025-10-06","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoortak, overweg en wegaansluiting * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2503-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007808-2508",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,41,42,"2025-10-12","09:00:00","2025-10-13","05:00:00","0d 20:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers van 237 en 291 B door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2508-00-3&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004987-2517",null,">","Roosendaal","Roosendaal grens",2025,2025,41,42,"2025-10-10","01:00:00","2025-10-19","05:00:00","9d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Spoorvernieuwingen en aanbrengen wisselverwarming * More details: https://btd-planner.prorail.nl?taak=IO-M-004987-2517-00-8&doc=FOT (Register with ProRail)",null,null,"M-004987","2024-01-04","High",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004897-FL04",null,">","Roosendaal","Roosendaal grens",2025,2025,41,42,"2025-10-11","01:00:00","2025-10-13","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren van spoorviaduct in 3 perioden van 52u * More details: https://btd-planner.prorail.nl?taak=IO-M-004897-FL04-00-3&doc=FOT (Register with ProRail)",null,null,"M-004897","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2513",null,">","Roosendaal","Bergen op Zoom",2025,2025,41,42,"2025-10-11","01:00:00","2025-10-13","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2513-00-5&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2508",null,">","Roosendaal","Roosendaal",2025,2025,42,42,"2025-10-14","13:00:00","2025-10-16","17:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2508-00-4&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004917-2502",null,">","Zevenbergen inhaalsp.","Roosendaal",2025,2025,43,44,"2025-10-25","01:00:00","2025-10-27","04:00:00","2d 03:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2502-00-2&doc=FOT (Register with ProRail)",null,null,"M-004917","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006146-2511",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,44,44,"2025-10-30","08:00:00","2025-11-02","16:00:00","3d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen TTI (A15 West) * More details: https://btd-planner.prorail.nl?taak=IO-K-006146-2511-00-2&doc=FOT (Register with ProRail)",null,null,"K-006146","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2514",null,">","Singelgracht aansl.","Singelgracht aansl.",2025,2025,44,45,"2025-11-01","01:00:00","2025-11-03","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen bevestigingsmiddelen * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2514-00-1&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005467-2506",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,44,45,"2025-11-01","01:00:00","2025-11-03","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Herstel kabelkokers op KW Hemboog. Periode nodig om materiaal via RIP aan te voeren. * More details: https://btd-planner.prorail.nl?taak=IO-L-005467-2506-00-5&doc=FOT (Register with ProRail)",null,null,"L-005467","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2505",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,44,45,"2025-11-01","01:00:00","2025-11-03","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2505-00-3&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R551400-2502",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,44,45,"2025-11-01","01:00:00","2025-11-03","05:00:00","2d 04:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Aansluiten nieuwe opstelsporen en vernieuwen sporen * More details: https://btd-planner.prorail.nl?taak=IO-R-551400-2502-00-3&doc=FOT (Register with ProRail)",null,null,"R-551400","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R3AE042-2503",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,44,45,"2025-11-02","01:00:00","2025-11-03","00:50:00","0d 23:50","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden stijgpunten perrons * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE042-2503-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE042","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007206-25BB",null,">","Willemstunnel Zuid","Rotterdam Westelijke Splitsing",2025,2025,45,46,"2025-11-08","01:00:00","2025-11-10","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Indienstellen nieuwe IXL Rotterdam * More details: https://btd-planner.prorail.nl?taak=IO-K-007206-25BB-00-2&doc=FOT (Register with ProRail)",null,null,"K-007206","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2501",null,">","Amsterdam Coenhaven","Amsterdam Coenhaven",2025,2025,47,48,"2025-11-22","01:00:00","2025-11-24","01:00:00","1d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoortak, overwegen, wegaansluiting, dwarliggers * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2501-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2511",null,">","Botlek","Botlek",2025,2025,47,47,"2025-11-22","01:00:00","2025-11-22","17:00:00","0d 16:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Cluster BR-13 (ca. 12m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2511-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","Z906301-2502",null,">","Zwijndrecht","Zwijndrecht",2025,2025,47,48,"2025-11-22","01:00:00","2025-11-24","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren/ dakdekken * More details: https://btd-planner.prorail.nl?taak=IO-Z-906301-2502-00-2&doc=FOT (Register with ProRail)",null,null,"Z-906301","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2501",null,">","Zwijndrecht","Zwijndrecht",2025,2025,47,48,"2025-11-22","01:00:00","2025-11-24","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2501-00-5&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008410-2504",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2025,2025,47,47,"2025-11-23","01:00:00","2025-11-23","13:00:00","0d 12:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen ventilatoren. * More details: https://btd-planner.prorail.nl?taak=IO-K-008410-2504-00-3&doc=FOT (Register with ProRail)",null,null,"K-008410","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006108-2510",null,">","Zevenbergschenhoek aansl.","HSL breda grens overloop",2025,2025,48,49,"2025-11-29","01:00:00","2025-12-01","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2510-00-4&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-25B6",null,">","Europoort","Europoort",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B6-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2506",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2506-00-1&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2518",null,">","Europoort West","Europoort West",2025,2025,49,50,"2025-12-07","08:00:00","2025-12-08","12:00:00","1d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Cluster ER-16 (1x 1:9 GW en ca. 20m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2518-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004966-2506",null,">","Arnemuiden","Vlissingen Souburg",2025,2025,49,50,"2025-12-05","21:00:00","2025-12-08","01:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen rijdraden Tussen Goes (Gs) en Vlissingen (Vs) * More details: https://btd-planner.prorail.nl?taak=IO-M-004966-2506-00-7&doc=FOT (Register with ProRail)",null,null,"M-004966","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007208-2518",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,49,49,"2025-12-06","23:00:00","2025-12-07","23:00:00","1d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 3331, 3333, 3335, 3337, 3339 en 3341 door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2518-00-1&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2506",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2506-00-2&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R569600-2501",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"aanpassen Sophiatunnel ivm capaciteitsvergroting * More details: https://btd-planner.prorail.nl?taak=IO-R-569600-2501-00-1&doc=FOT (Register with ProRail)",null,null,"R-569600","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R584600-2501",null,">","Arnemuiden","Vlissingen Souburg",2025,2025,49,50,"2025-12-04","01:00:00","2025-12-08","01:00:00","3d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Verbeteren van de verlichting voor de gebruiker (NS) van het emplacement. * More details: https://btd-planner.prorail.nl?taak=IO-R-584600-2501-00-4&doc=FOT (Register with ProRail)",null,null,"R-584600","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z907116-2502",null,">","Arnemuiden","Vlissingen Souburg",2025,2025,49,50,"2025-12-04","01:00:00","2025-12-08","01:00:00","3d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Integraal project station Middelburg, o.a. P76, perronkaprenovatie en aanpassen stationstunnel * More details: https://btd-planner.prorail.nl?taak=IO-Z-907116-2502-00-6&doc=FOT (Register with ProRail)",null,null,"Z-907116","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004864-2501",null,">","Arnemuiden","Vlissingen Souburg",2025,2025,49,50,"2025-12-04","01:00:00","2025-12-08","01:00:00","3d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen waterleidingen * More details: https://btd-planner.prorail.nl?taak=IO-M-004864-2501-00-4&doc=FOT (Register with ProRail)",null,null,"M-004864","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007022-2506",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2506-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2516",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2516-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2555",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2555-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]

{"sheet":"SBB-I TVS","index":5,"n_rows":30,"n_cols":31,"rows_kept":30,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["SBB Infra",null,"Basel GB - Basel RB EMU","< >","BSGB","BSRB",2022,2022,39,null,"2022-10-02",null,"2022-10-03",null,"Weekend","continuous","track works ","x",null,null,null,null,"x","x",null,"x",null,"Sunday 02:00 - Monday 02:00 (Sperrmuster 1)"]
["SBB Infra",null,"Basel GB - Basel RB EMU","< >","BSGB","BSRB",2022,2022,49,50,"2022-12-11",null,"2022-12-19",null,"Weekend","continuous","track works ","x",null,null,null,null,"x","x",null,"x",null,"Sunday 02:00 - Monday 02:00 (Sperrmuster 1)"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<> ","LPFR","GEPR/GE",2023,2023,8,49,"2023-02-19","22:00:00","2023-12-08","05:00:00","Week","night","track works ",null,"x",null,null,null,"x",null,"x","x",null,"Pose diagonales Satigny / nuit "]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<> ","LPFR","GEPR/GE",2023,2023,25,30,"2023-06-16",null,"2023-07-24",null,"6 weeks","continuous","track works ",null,"x",null,null,null,"x",null,"x","x",null,"Permanentes 680/580 pose diagonales Satigny"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<>","LPFR","GEPR/GE",2023,2023,41,42,"2023-10-13",null,"2023-10-23",null,"2 weekends","continuous","track works ","x","x",null,null,null,"x",null,"x",null,null,"Total closure 2 weekends / Friday 22:00-Monday 05:00"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","< >","LPFR","GEPR/GE",2024,2024,1,46,"2024-01-01",null,"2024-11-15",null,"10 months","continuous","Platform and track works ",null,"x",null,null,null,"x",null,"x","x",null,"Total closures may be possible"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<>","LPFR","GEPR/GE",2026,2026,1,49,"2026-01-01",null,"2026-12-10",null,"12 months","continuous","Platform and track works ",null,"x",null,null,null,"x",null,"x","x",null,"Total closures may be possible / only one track available (postponed form 2025 to 2026)"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<>","LPFR","GEPR/GE",2026,2026,31,33,"2026-07-27",null,"2026-08-16",null,"2 weeks","continuous","track works ","x",null,null,null,null,"x",null,"x",null,null,"Total closure (postponed form 2025 to 2026)"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<>","SY","LP",2027,2027,1,13,"2027-01-01",null,"2027-04-04",null,"13 weeks","continuous","track works ",null,"x",null,null,null,"x",null,"x",null,null,"only one track available (postponed form 2026 to 2027)"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<>","SY","VMC",2027,2027,27,33,"2027-07-05",null,"2027-08-22",null,"7 weeks","continuous","track works ",null,"x",null,null,null,"x",null,"x",null,null,"only one track available (postponed form 2026 to 2027)"]
["SBB Infra",null,"Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,9,9,"2023-03-03","22:45:00","2023-03-06","05:00:00","Weekend","continuous","track works ","x",null,null,null,null,null,"x",null,null,null,"Total closure "]
["SBB Infra",null,"Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,10,10,"2023-03-10","22:45:00","2023-03-12","22:00:00","Weekend","continuous","track works ","x",null,null,null,null,null,"x",null,null,null,"Total closure "]
["SBB Infra",null,"Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,39,39,"2023-09-29","22:45:00","2023-10-02","05:00:00","Weekend","continuous","track works ","x",null,null,null,null,null,"x",null,null,null,"Total closure "]
["SBB Infra",null,"Basel St.Johann - Basel SBB","< >","BSSJ","BS",2023,2023,40,40,"2023-10-06","22:45:00","2023-10-09","05:00:00","Weekend","continuous","track works ","x",null,null,null,null,null,"x",null,null,null,"Total closure "]
["SBB Infra",null,"Basel RB","<","BSRB",null,2023,2023,31,33,"2023-08-05","09:00:00","2023-08-21","06:00:00","Weekend Sa-Mo","continuous","track works ",null,"x",null,null,null,"x","x","x","x",null,"Trains S-N re-routing, no buffering possibilities BSRB"]
["SBB Infra",null,"Basel RB","< >","BSGB","BSRB",2024,2024,26,37,"2024-06-29","14:00:00","2024-09-09","02:00:00","Weekend Sa-Mo","continuous","track works ",null,"x",null,null,null,null,null,null,"x",null,"only one track available"]
["SBB Infra",null,"Basel St.Johann","< >","BSSJ",null,2024,2024,49,50,"2024-12-02",null,"2024-12-13",null,"Monday-Sunday","shifts","track works ","x","x",null,null,null,null,null,null,null,null,"Only garage installation affected"]
["SBB Infra",null,"Basel St.Johann","< >","BSSJ",null,2024,2024,41,null,"2024-10-13","23:00:00","2024-10-14","05:00:00","Sunday-Monday","continuous","signal box replacement","x",null,null,null,null,null,null,null,null,null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BS",null,2024,2024,48,null,"2024-11-30","19:00:00","2024-12-02","05:00:00","Saturday-Monday","2x 10h shift","track works ",null,"x",null,null,null,"x",null,null,"x",null,"Reduced Track Availability "]
["SBB Infra",null,"Basel SBB","< >","BS",null,2024,2024,39,null,"2024-09-28","19:00:00","2024-09-30","05:00:00","Saturday-Monday","2x 10h shift","track works ",null,"x",null,null,null,"x",null,null,"x",null,"Reduced Track Availability "]
["SBB Infra",null,"Basel SBB","< >","BSRB",null,2025,2025,null,null,"2025-01-06",null,"2025-01-11",null,"Monday-Sunday","continuous","track works ",null,null,null,null,null,null,"x",null,"x",null,"Reduced Availability, many diffrent TCR's"]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,null,null,"2026-01-31",null,"2026-02-02",null,null,"continuous","track works ","x",null,null,null,null,null,null,null,null,null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,null,null,"2026-03-07",null,"2026-03-09",null,null,"continuous","track works ","x",null,null,null,null,null,null,null,null,null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,null,null,"2026-05-09",null,"2026-05-11",null,null,"continuous","track works ","x",null,null,null,null,null,null,null,null,null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,null,null,"2026-06-06",null,"2026-06-08",null,null,"continuous","track works ","x",null,null,null,null,null,null,null,null,null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,null,null,"2026-11-14",null,"2026-11-16",null,null,"continuous","track works ","x",null,null,null,null,null,null,null,null,null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,null,null,"2026-01-03","23:30:00","2026-12-23","04:30:00","Saturday-Sunday","continuous","track works ","x",null,null,null,null,null,null,null,null,null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,null,null,"2026-01-03","23:30:00","2026-12-23","04:30:00","Sunday-Monday","continuous","track works ","x",null,null,null,null,null,null,null,null,null,"Total closure "]

{"sheet":"SNCF-R","index":6,"n_rows":2059,"n_cols":45,"rows_kept":2059,"cut":false,"hidden":false,"merged":[[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]]}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)","Last update","Classification","Weekdays","Interval","Affected estimated travel volume","Affected border","Deviation location","Deviation border","Status","Additional information","Automatic process","BitmapDays","Variant value"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","No catenary","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"SNCF-R","R22718c",null,"< >","Reding-Remilly","Reding-Remilly",2025,2025,39,50,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"30 Sarraltroff - Berthelming: HS: V1 : 3,855 km de RR et V2 : 5,11 km de RRN_1F",null,null,null,"2022-10-06","High",12,null,null,null,null,null,"Planned"]
[null,"SNCF-R","14011720261",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,15,16,"2024-04-13","23:30:00","2024-04-21","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prépa MES LGV+",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14011357761",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,15,16,"2024-04-13","00:05:00","2024-04-20","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prépa MES LGV+",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689838461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,50,50,"2024-04-04","10:15:00","2024-04-12","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aiguille d'accès LGV Aisy GV libre Accord en CODAB le 26/09/2016 pour 35 semaines     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689838461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:15:00","2024-12-13","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aiguille d'accès LGV Aisy GV libre Accord en CODAB le 26/09/2016 pour 35 semaines     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689839461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,51,34,"2023-12-18","11:42:00","2024-08-23","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401060",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689836861",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,31,34,"2024-07-29","00:34:00","2024-08-19","03:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401135",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689838461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,50,50,"2024-12-09","10:15:00","2024-12-13","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aiguille d'accès LGV Aisy GV libre Accord en CODAB le 26/09/2016 pour 35 semaines     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14472116761",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,43,43,"2024-10-21","10:10:00","2024-10-24","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9264     TF: 17762",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14504405361",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,43,43,"2024-10-25","10:10:00","2024-10-25","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9264     TF: 6743",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15109488761",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,40,41,"2024-09-30","10:00:00","2024-10-11","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15109430361",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,13,13,"2024-03-25","10:45:00","2024-03-28","12:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9206   TF: 6705",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15169710861",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,44,44,"2024-11-02","20:20:00","2024-11-02","12:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1 + 2",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446457961",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,9,11,"2024-02-26","10:45:00","2024-02-29","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446660561",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,16,17,"2024-04-15","10:45:00","2024-04-25","13:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15169740761",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,48,48,"2024-11-25","10:25:00","2024-11-29","16:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1 + 2",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689844061",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,11,11,"2024-03-16","11:30:00","2024-03-16","11:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9211 du Samedi   TF: 9211 du Dimanche",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689845061",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage modifiée le 01/12/2022  suite report de la MES.  ",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689842061",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance IHM   ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641083161",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641811661",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446385761",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,7,11,"2024-02-12","10:45:00","2024-03-14","16:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Circulation des trains par la voie 1 de Les Laumes à Aisy.",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446457961",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,9,11,"2024-02-26","10:45:00","2024-03-14","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446660561",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,16,17,"2024-04-15","10:45:00","2024-04-25","13:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689838461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,50,50,"2024-01-26","10:15:00","2024-07-05","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aiguille d'accès LGV Aisy GV libre Accord en CODAB le 26/09/2016 pour 35 semaines     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689844061",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,11,11,"2024-03-16","11:30:00","2024-03-16","11:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9211 du Samedi   TF: 9211 du Dimanche",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14366427461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MES LGV+",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689838461",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Bât Voyageurs",2024,2024,50,50,"2024-01-15","10:15:00","2024-02-02","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aiguille d'accès LGV Aisy GV libre Accord en CODAB le 26/09/2016 pour 35 semaines     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14333518961",null,"< >","Aisy - évitement Pair","Montbard - Bât Voyageurs",2024,2024,13,13,"2024-03-25","09:05:00","2024-03-27","11:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261    TF: 9211",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14325172061",null,"< >","Aisy - évitement Pair","Montbard - Bât Voyageurs",2024,2024,33,33,"2024-08-12","09:25:00","2024-08-15","16:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En Complément de la 4D_RAI_005",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14768809361",null,"< >","Aisy - évitement Pair","Montbard - Bât Voyageurs",2024,2024,27,27,"2024-07-01","09:50:00","2024-07-05","16:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En Complément de la 4D_RAI_013",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14365081161",null,"< >","Aisy - évitement Pair","Les Laumes-Alésia - Côté NO",2024,2024,4,17,"2024-01-22","10:10:00","2024-04-25","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1 OU Voie 2  Complété par la 4C_AIY-LLA_007 (Evit. Nogent)",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14333732961",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Bât Voyageurs",2024,2024,13,14,"2024-03-29","10:10:00","2024-04-03","14:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14333562061",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Côté NO",2024,2024,13,13,"2024-03-25","09:05:00","2024-03-28","14:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261   TF: 5763",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689840261",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Côté NO",2024,2024,51,34,"2023-12-18","10:20:00","2024-08-23","11:27:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401031",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689837661",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Côté NO",2024,2024,51,30,"2023-12-18","01:36:00","2024-07-22","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401136",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446602061",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Côté NO",2024,2024,9,10,"2024-02-26","10:40:00","2024-03-05","16:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Circulation des trains par la voie 2 de Aisy à Les Laumes",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446336661",null,"< >","Aisy - Rac LGV","Les Laumes-Alésia - Côté NO",2024,2024,6,6,"2024-02-05","09:10:00","2024-02-08","15:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Passage des trains en Bana par la voie 2 depuis Aisy à LLA.  TO: 9261     TF: 9215",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14858632261",null,"< >","AISY ENTREE SORTIE LGV","Montbard - Point Changement de Voie",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance IHM",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13851162261",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,3,47,"2024-01-16","09:45:00","2024-01-16","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"NUR Voie 1Bis OU Voie A de NUR  En SIM avec la 4D_TNE-AIY_014 (= Voie 1 OU Voie 2)  Si Tx sont : - Voie 1 alors se sera V1Bis                   - Voie 2 alors se sera Voie A                                Accès Faisceau Impair IMPOSSIBLE lorsqu'il s'agit ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14640886061",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   Les zones doivent etre au blanc",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641049261",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   Les zones doivent etre au blanc",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641658861",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   Les zones doivent etre au blanc",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689906661",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance IHM1 Les zones doivent etre au blanc ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13793246461",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage Modifiée le 01/12/2022 suite report de la MES",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13851162261",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,3,47,"2024-02-19","09:45:00","2024-11-22","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"NUR Voie 1Bis OU Voie A de NUR  En SIM avec la 4D_TNE-AIY_014 (= Voie 1 OU Voie 2)  Si Tx sont : - Voie 1 alors se sera V1Bis                   - Voie 2 alors se sera Voie A                                Accès Faisceau Impair IMPOSSIBLE lorsqu'il s'agit ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689907861",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"   ",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13851162261",null,"< >","Ancy-le-Franc","Aisy - Bât Voyageurs",2024,2024,3,47,"2024-01-15","09:45:00","2024-04-26","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"NUR Voie 1Bis OU Voie A de NUR  En SIM avec la 4D_TNE-AIY_014 (= Voie 1 OU Voie 2)  Si Tx sont : - Voie 1 alors se sera V1Bis                   - Voie 2 alors se sera Voie A                                Accès Faisceau Impair IMPOSSIBLE lorsqu'il s'agit ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13971963961",null,"< >","Ancy-sur-Moselle","Metz-Sablon - Montigny AT",2024,2024,46,47,"2024-11-12","23:30:00","2024-11-22","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec 4D_MZS-WPY_002 et 4C_MZ_003 qui reprend les conséquences circulations.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13972521061",null,"< >","Ancy-sur-Moselle","Metz-Sablon - Montigny AT",2024,2024,45,46,"2024-11-09","08:00:00","2024-11-12","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec 4D_MZS-WPY_003 et 4C_MZ_004 qui reprend les conséquences circulations.",null,null,null,null,"Medium","1,2,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13972581861",null,"< >","Ancy-sur-Moselle","Metz-Sablon - Montigny AT",2024,2024,46,46,"2024-11-16","08:00:00","2024-11-16","20:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec 4D_MZS-WPY_004 et 4C_MZ_005 qui reprend les conséquences circulations.",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14705658161",null,"< >","Ancy-sur-Moselle","Metz-Sablon - Montigny AT",2024,2024,44,45,"2024-10-28","23:30:00","2024-11-07","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec 4D_MZS-WPY_006 et 4C_MZ_018 qui reprend les conséquences circulations.",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689385561",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2024-09-16","23:30:00","2024-10-31","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification de la fenêtre pour le passage du TGV 6129 (avec marge pour anticiper le décalage du sillon lié à des LTV) en sillon ouvrant et TER 8810402 en sillon fermant (avec marge pour anticiper le décalage du sillon lié à des LTV). La forme en trapèze ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13886949661",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,41,41,"2024-10-12","00:01:00","2024-10-13","04:01:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Réfection aqueduc Km 26,242 OCP 28h We S41 :  Domaine S9 : V1 DFV L AUB-CIS + ZEPG CIS 21 / V2 ZEP G CIS 22 + DFV L CIS-AUB  Domaine S11 : Sél ou Ssr correspondant  Nota : VS impaires prises ZEP 23  ",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689388961",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2023-12-11","11:10:00","2024-12-13","11:26:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MC19-0070 pour augmentation de l'amplitude horaire à 1h00 2021_SE_81 + 2021_SE_82 + 2021_SE_83 : décalage de quelques minutes pour avoir 881426 en SO",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689384761",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2023-12-11","08:48:00","2024-12-13","10:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"decalage MC18-0281 pour Thello 145  2021_SE_87 + 2021_SE_88 + 2021_SE_89 : décalage pour avoir 881611 en SF",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689385561",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-13","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification de la fenêtre pour le passage du TGV 6129 (avec marge pour anticiper le décalage du sillon lié à des LTV) en sillon ouvrant et TER 8810402 en sillon fermant (avec marge pour anticiper le décalage du sillon lié à des LTV). La forme en trapèze ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689385561",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2024-09-30","23:30:00","2024-12-06","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification de la fenêtre pour le passage du TGV 6129 (avec marge pour anticiper le décalage du sillon lié à des LTV) en sillon ouvrant et TER 8810402 en sillon fermant (avec marge pour anticiper le décalage du sillon lié à des LTV). La forme en trapèze ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689385561",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2024-12-02","23:30:00","2024-12-13","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification de la fenêtre pour le passage du TGV 6129 (avec marge pour anticiper le décalage du sillon lié à des LTV) en sillon ouvrant et TER 8810402 en sillon fermant (avec marge pour anticiper le décalage du sillon lié à des LTV). La forme en trapèze ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689385561",null,"< >","Aubagne","Toulon - Bât Voyageurs",2024,2024,50,50,"2024-09-30","23:30:00","2024-11-15","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification de la fenêtre pour le passage du TGV 6129 (avec marge pour anticiper le décalage du sillon lié à des LTV) en sillon ouvrant et TER 8810402 en sillon fermant (avec marge pour anticiper le décalage du sillon lié à des LTV). La forme en trapèze ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14340811761",null,"< >","Aubagne - Jonction 3","ITE Camp-Militaire-Carpiagne",2024,2024,3,37,"2024-01-20","23:59:00","2024-09-14","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA20_0018098 \"\"Augmentation débit LGV\"\" : OCP 4h41,  1 nuit du Sa/Di de S3 (20-21/01/24) + 1 nuit du Sa/Di de S25 ( 22-23/06/24 de 23h59 à 04h40 opérations sur l´IHM1 Mistral au P1 de Marseille) et 1 nuit du Sa/Di de S37 pour essai complet de montée en c",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14845641261",null,"< >","Aubagne - Jonction 3","ITE Camp-Militaire-Carpiagne",2024,2024,43,45,"2024-10-21","23:30:00","2024-11-08","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Meuleur SA2024, S43, AUB V1+V2+Générique AUB-TLN",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14340560461",null,"< >","Aubagne - Jonction 3","ITE Camp-Militaire-Carpiagne",2024,2024,45,45,"2024-11-10","22:35:00","2024-11-10","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0026458, OCP 7h00, 1 nuit du Di/Lu 10-11/11/24 (de 22h35 à 05h35), mise en service \"\"LGV +\"\" sur l'interface de la zone télécommandée de l'IHM1 de Mistral P1 de Marseille)  Conditions de réalisation : toute la zone d'action du poste de l'IHM1 de Mar",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15224291261",null,"< >","Aubagne - Jonction 3","ITE Camp-Militaire-Carpiagne",2024,2024,35,50,"2024-09-01","22:50:00","2024-12-12","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Portiques souples Aubagne, reprise travaux sur SA2024 :   Domaine S9 :  V.D : zep 3617+3619+3621  V.1/VC : zep 3601+3603+3605+3607+3609+3611+3613+3615  MV2/VB : zep 3600+3602+3604+3606+3608+3610+3612+3614  MV3/VA : zep 3616+3618+3620+3622+3624+3626  VE : ",null,null,null,null,"Major","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15446184461",null,"< >","Aubagne - Jonction 3","ITE Camp-Militaire-Carpiagne",2024,2024,41,41,"2024-10-12","00:01:00","2024-10-12","12:01:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"OCP 12h, sur S41 (sur le même We que le CHA24_0026522 Aqueducs Km 26,242) :  Portiques souples Aubagne, reprise travaux sur SA2024 à l'ombre de l'OCP 28h du CHA24_0026522) :   Domaine S9 :  V.D : zep 3617+3619+3621  V.1/VC : zep 3601+3603+3605+3607+3609+3",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14560456661",null,"< >","Avignon - Bât Voyageurs","Avignon-Champfleury - FSC Réception",2024,2024,13,14,"2024-03-25","22:05:00","2024-04-05","01:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA 2024, VG, Avi Lot 4  :  Etendue S9 : V2 du Cv148 Km 741,773 au C164 Km 741,910   Domaine S9 : 576+594  Etendue S11 : V2 du Km 741,663 au Km 742,550  Domaine S11 : Sel 2098 Sr Foncouverte Champfleury V2",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14553510361",null,"< >","Avignon - Bât Voyageurs","Avignon-Champfleury - Aig Km 744,4",2024,2024,13,13,"2024-03-25","23:15:00","2024-03-29","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"AVI Voie 1+1 Gare,VTE+RFC, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870, équivalent Gén, à prendre avec 4D_AF-TCN_016 et 4C_TCN_013 :  Etendue S9 : V1 Côté TCN, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870  Domaine S9 : ZEP G 705+703+701 Ete",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14545600461",null,"< >","Avignon - Bât Voyageurs","Avignon-Champfleury - Cv 2A",2024,2024,13,13,"2024-03-25","22:35:00","2024-03-27","03:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP voie Avignon, à prendre avec 4C_AV_074 :  Etendue S9 : V1 du C162 Km 741,862 vers V à quais au Km 741,604  Domaine S9 : ZEP 595+599+621",null,null,null,null,"Medium","1,2,3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14545565861",null,"< >","Avignon - Bât Voyageurs","Avignon-Champfleury - Cv 2A",2024,2024,13,13,"2024-03-25","22:35:00","2024-03-29","03:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avignon :  Etendue : depuis V A/B/C/D/E des C163 à 151 Km 741,604 vers Cv162 V1 Km 741,862 et Cv148 V2 Km 741,773  Domaine S9 : ZEP (V2 : 572+574=>4C_AV_076)+582+584+586+588+590+592 (+V1 : ZEP 595+599+621 =>4C_AV_075)",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14545613861",null,"< >","Avignon - Bât Voyageurs","Avignon-Champfleury - Cv 2A",2024,2024,13,13,"2024-03-25","22:35:00","2024-03-29","01:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avignon :  Etendue : depuis V 2 du C 151 Km 741,604 vers Cv148 V2 Km 741,773  Domaine S9 : ZEP 572+574+(582+584+586+588+590+592=> 4C_AV_074) (+ ZEP 595+599+621 =>4C_AV_075)",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14737169161",null,"< >","Avignon - Bif Cavaillon","Miramas - Bât Voyageurs",2024,2024,39,40,"2024-09-25","08:37:00","2024-10-02","17:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx Principaux 08h40 -Miramas inclus à Cavaillon exclu - Ppx : S39 ME+JE+VE et S40 LU+MA+ME- :  Etendue S9 : V1 de la PATC Km 38,695 au C507 au Km 66,880 => JI Z 605/617 km 67.837 de Mas / V2 Du Cv 607 km 67,860 => à la PATC Km 65,976 au C24 Km 34,100    ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14545251861",null,"< >","Avignon - Bif Cavaillon","Avignon - Bât Voyageurs",2024,2024,14,14,"2024-04-02","22:35:00","2024-04-05","03:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA 2024, UP SEs Avignon :  Etendue S9 : L830 V1 du Cv115 Km 740,895 (GF Aig 108) au+V2 du Cv 113 Km 740,895 au (C110 Km 741,130)=>VA/B/C C118 à 112 Km 741,107 -559 non prise cause It Alternatif-   Domaine S9 : ZEP 521+522+523+524+525+529+531+533+535+539 -",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14544875661",null,"< >","Avignon - Bif Cavaillon","Avignon - Bât Voyageurs",2024,2024,15,15,"2024-04-10","09:10:00","2024-04-11","13:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP Voie Avignon :  Etendue S9 : L925, V2 AMS du C 68 Km 0,860 au JI Z117/401 Km0,547 + L830, V1Bis du Km 740,800 au Km 741,102  Domaine S9 : ZEP 509+554+556+560+562+563",null,null,null,null,"Medium","3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14473742261",null,"< >","Avignon - Bif Cavaillon","Avignon - Bât Voyageurs",2024,2024,2,2,"2024-01-08","21:50:00","2024-01-12","03:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA 2024, Famille B de 05h20 :    étendue du domaine : L925 V1 du Km 0,547 à la Pte de l'Aig 5  Km 2+244/ V2 du Km 0,547 au Cv48 Km 2,227 et V1Bis+V2Bis du 740,598/7 jusqu'au Km 741,180 et V2Bis Km 741,093.  Domaine S9 :  V1bis/V1 L925, 563+556+509  /  V2B",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13836845561",null,"< >","Avignon - Bif Cavaillon","Avignon-Fontcouverte - Fais Réc Impair",2024,2024,48,50,"2024-11-25","08:25:00","2024-12-13","16:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx PPx V1+V2 (de S48+49+50 du SA2024 et S51 de 2024 sur SA2025) -Avignon Fontcouverte inclus à Miramas exclu-, à prendre avec 4D_AFT-CVN_029  :  Etendue S9 : V1 du Km 0+730 (Cv105 d'AFT) au Km 66+880 (C507 de Mas) et V2 au Km 65+976 (PATC de Mas) au Km 0",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14559555261",null,"< >","Avignon - Bif Cavaillon","Avignon-Champfleury - Aig Km 743,5",2024,2024,38,39,"2024-09-16","22:17:00","2024-09-29","01:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Lot G C SUD, AVI, VTE+RFC :   Etendue S9 : V1 du C163 Km 741,604 au C255 m 743,417  + vers tête des voies VA , VB, VC   Domaine S9 Depuis A/B/C vers V1: ZEP G AVI 597(VA)+573(VB)+575(VC)+586+584+582+588+590+594+596+598   Etendue S11 Depuis A/B/C/D/E vers ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14544446561",null,"< >","Avignon - Bif Cavaillon","Avignon - Ent Dépôt",2024,2024,15,15,"2024-04-08","09:10:00","2024-04-09","13:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Voie Avignon :  Etendue S9 : Avi V2 AMS du C61 Km 1,490 au C68 Km 0,860 et V1 AMS du  du C66 Km 0,841 au C35 Km 1,902  Domaine S9 : 528+530+532+534+538+540 + 569+571",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14558703661",null,"< >","Avignon - Bif Cavaillon","Avignon-Champfleury - Cv 2A",2024,2024,38,39,"2024-09-16","22:17:00","2024-09-29","01:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Lot G C SUD, AVI, VTE+RFC à prendre avec 4C_AV_085 :   Etendue S9 : V2 du C176 Km 742,286 au Km 741,604 tête des voies VA , VB, VC   Domaine S9 Depuis A/B/C vers V2: ZEP G AVI 597(VA)+573(VB)+575(VC)+586+584+582+588+590+594+596+598   Etendue S11 Depuis A/",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14545016661",null,"< >","Avignon - Bif Rac","L'Ardoise - Voie 2Bis",2024,2024,15,15,"2024-04-12","22:35:00","2024-04-12","03:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avignon :   Etendue S9 : V1 du C103 Km 740,569 au Ji Z106/112 Km 740,700 +V2 du C102 Km 740,790 au C101 Km 740,597 L830 Avi Nord    Domaine S9 : ZEP 507+510+511+512",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15036281461",null,"< >","Avignon - Bif Rac","Avignon - Bât Voyageurs",2024,2024,14,15,"2024-04-02","21:50:00","2024-04-12","03:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA 2024, Famille B de 05h20 :    étendue du domaine : V1 du JI Z4/5 Km 739,850 au GF Aig. 113 Km 740,950 /V2 du C2 Km 739, 768 au C113 Km 740,895  Domaine S9 : ZEP V1  505+507+511+513+521+523 / V2  508+510+512+514+520 d'Avignon  Domaine S11 : Sel 2093 SR ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14557402061",null,"< >","Avignon - Bif Rac","Avignon-Champfleury - FSC Réception",2024,2024,38,39,"2024-09-16","22:17:00","2024-09-27","01:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Lot G C SUD, AVI, VTE+RFC à prendre avec 4C_AV_086 :   Etendue S9 : V2 du GF Aig 101 Km 740,655 du C176 Km 742,286    Domaine S9 V2 : ZEP G AVI V2 512+514+520+522+524+570+572+574+576+594+596+598  Etendue S11 V2 : du Km 740,719 au Km 741,604    Domaine S11",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14553194261",null,"< >","Avignon - Bif Rac","Avignon-Champfleury - Cv 2A",2024,2024,19,20,"2024-05-06","22:05:00","2024-05-17","03:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"AVI Voie 1+1 Gare,VTE+RFC, du C1 Km 739,706 au C163 Km 741,604, à prendre avec 4D_SCP-AVI_012 : Etendue S9 : PLM du C1 Km 739,706 au C 163 Km 741,604 Domaine S9 : ZEP G AVI 501+505+507+511+513+521+523+525+527 Etendue S11 : du Km 740,038 au Km 741,643 Doma",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14560316161",null,"< >","Avignon - Bif Rac","Avignon-Champfleury - Cv 2A",2024,2024,13,14,"2024-03-25","22:05:00","2024-04-05","01:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA 2024, VG, Avi Lot 4 à prendre avec 4D_SCP-AV_013 :  Etendue S9 : de la PATC Km 737,920 au Cv148 Km 741,773  Domaine S9 : 502+504+508+510+512+514+520+522+524+570+572+574  Etendue S11 : du Km 739,702 au Km 741,663  Domaine S11 : Sel 2092+2094+2096 Sr Fon",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687153661",null,"< >","AVIGNON - ENT DEPOT","Avignon-Fontcouverte - Fais Réc Impair",2024,2024,16,39,"2024-04-15","09:10:00","2024-09-27","14:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"RPU Maintenance, épuration, Voie AVI (ESV méca) S16+17 et S38+39 (SR Voie sur zone de l'ITE SMEA de S38 à S43) :  Etendue S9 : AMS V2 du C88 Km 3,645 au Cv48 Km 2,227 / AMS V1 du ZI z127/129 Km 2,244 à la PATC Km 4,283   Domaine S9 : AMS V2 (ZEP G 927+918",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14548126061",null,"< >","Avignon-Champfleury - Aig Km 743,9","Barbentane-Rognonas",2024,2024,18,18,"2024-04-29","23:15:00","2024-04-30","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avignon :   Etendue S9 : V2 du C306 km 744,730 au C260 Km 744,165   Domaine S9 : 702+712",null,null,null,null,"Medium","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14548162161",null,"< >","Avignon-Champfleury - Aig Km 743,9","Barbentane-Rognonas",2024,2024,18,18,"2024-05-02","23:15:00","2024-05-03","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avignon :   Etendue S9 : V1 du C304 km 744,730 au C307 Km 744,405   Domaine S9 : 705",null,null,null,null,"Medium","4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687480061",null,"< >","Avignon-Champfleury - Aig Km 743,9","Tarascon - Poste Km 759,1",2024,2024,50,50,"2023-12-11","14:00:00","2024-12-13","15:01:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_59 : décalage et réduction pour avoir TER 886569 en SO et TER 17709 en SF  2021_SE_47 : décalage de -10mn avec 879531 en SO et 879535 en SF, aligné V1 d'Avignon à St Louis, le 19/11/2019  Main courante MC20-0317 pour le passage du FBCE22, le 06/11",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687476661",null,"< >","Avignon-Champfleury - Aig Km 743,9","Tarascon - Poste Km 759,1",2024,2024,8,11,"2024-02-19","23:10:00","2024-03-15","05:04:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Gen, V1, 1V/2, 5h54 Nuit en sim partielle, LU/MA->VE/SA (sim 2V/2 avec 1F_AF-TCN_002 / FEN21_Avignon-Tarascon_002) 2h en sim 5N/7 Modification le 11/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687478261",null,"< >","Avignon-Champfleury - Aig Km 743,9","Tarascon - Poste Km 759,1",2024,2024,8,11,"2024-02-20","00:00:00","2024-03-16","02:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14553555461",null,"< >","Avignon-Champfleury - Aig Km 743,9","Tarascon - Poste Km 759,1",2024,2024,13,13,"2024-03-25","23:15:00","2024-03-29","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"AVI Voie 1+1 Gare,VTE+RFC, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870, équivalent Gén, à prendre avec 4D_AV_082 et 2C_TCN_013 :  Etendue S9 : V1 Côté TCN, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870  Domaine S9 : ZEP G 705+703+701 Etendue",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14550034061",null,"< >","Avignon-Champfleury - Aig Km 743,9","Tarascon - Poste Km 759,1",2024,2024,17,17,"2024-04-22","23:15:00","2024-04-24","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tir 744/15A, SA2024, à prendre avec 4C_AV_080  :  Domaine S9 : V1 ZEP 701+703+705 / V2 ZEP 706+704+702 +DFL Avi/TCN V1+V2 (jusqu'au V1 C601/V2 603 Km 759,095)   Etendue S11 : V1 du Km 742,441 au Km 759,179 / V2 du Km 758,757 au Km 742,573  Domaine S11 : V",null,null,null,null,"Medium","1,2,3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687479261",null,"< >","Avignon-Champfleury - Aig Km 744,5","Tarascon - Poste Km 759,1",2024,2024,50,50,"2023-12-11","10:23:00","2024-12-13","11:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_20 : vibration de +5mn pour avoir Fret PNBP07 en SO  2021_SE_125 : gros décalage pour TER 876416 tout en conservant l'alignement avec les surveillances V2 Avignon-Pierrelatte pour minimiser l'impact sur les flux fret (report de la contrainte sur T",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14586018461",null,"< >","Avignon-Champfleury - Aig Km 744,5","Tarascon - Poste Km 759,1",2024,2024,14,15,"2024-04-03","00:00:00","2024-04-13","02:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"VI Voie C Circ+V2Courtine+V1Courtine+HCourtine+A/B Courtine, VTE+RFC, du C154 Km 741,629 au C306 Km 744,730, à prendre avec 4C_AV_083+4C_AV_084 :  Etendue S9 : depuis V1Bis/2bis vers VC Circ. + VCirc du C154 Km 741,629 au C305 Km 743,974 (et du C305 Km 74",null,null,null,null,"High","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14551529261",null,"< >","Avignon-Champfleury - Aig Km 744,5","Tarascon - Poste Km 759,1",2024,2024,15,15,"2024-04-08","23:15:00","2024-04-12","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, Tir 714/16 + 752/11 (à prendre avec 4C_TCN_012+4D_TCN-MAS_037)  :  Etendue S9 : V1 du C 304 Km 744,730 (Avignon) à la PATC Km 767+009 (Tarascon) / V2 du C 306  Km 744,730 (Avignon) au C22 Km 766,134 (Tarascon)   Domaine S9 : V1 ZEP L Avi-TCN + ZEP",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14549525861",null,"< >","Avignon-Champfleury - Aig Km 744,5","Tarascon - Poste Km 759,1",2024,2024,16,16,"2024-04-17","23:15:00","2024-04-18","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tir 742/3077 (V2 à prendre avec 4C_AV_079+078) :  Domaine S9 : ZEP600+620+624+706+704+702+DFV L Avi/TCN V2 (Jusqu'au C603 Km 759,095)   Etendue S11 : du Km 758,757 au Km 742,573  Domaine S11 :  Sel 2112+2114 SR Champfleury/les Olivettes voie2",null,null,null,null,"Medium","3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14550052061",null,"< >","Avignon-Champfleury - Chant Multitech","Avignon-Champfleury - Aig Km 744,4",2024,2024,17,17,"2024-04-22","23:15:00","2024-04-24","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tir 744/15A, SA2024 (à prendre avec 4D_AF-TCN_014)  :  Domaine S9 : V1 ZEP 701+703+705 / V2 ZEP 706+704+702 +DFL Avi/TCN V1+V2 (jusqu'au V1 C601/V2 603 Km 759,095)    Etendue S11 : V1 du Km 742,441 au Km 759,179 / V2 du Km 758,757 au Km 742,573  Domaine S",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14553757061",null,"< >","Avignon-Champfleury - Chant Multitech","Barbentane-Rognonas",2024,2024,14,15,"2024-04-03","00:00:00","2024-04-13","02:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"AVI Voie C Circ+V2Courtine+V1Courtine+HCourtine+A/B Courtine, VTE+RFC, du C154 Km 741,629 au C306 Km 744,730, à prendre avec 4C_AF-TCN_017 + 4C_AV_083 :  Etendue S9 : depuis V1Bis/2bis vers VC Circ. + VCirc du C154 Km 741,629 au C305 Km 743,974 (et du C30",null,null,null,null,"High","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14549427561",null,"< >","Avignon-Champfleury - Chant Multitech","Barbentane-Rognonas",2024,2024,16,16,"2024-04-18","23:15:00","2024-04-19","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null," Tir 742/3077 (V2 à prendre avec 4C_AV_078+4D_AF-TCN_013) :  Domaine S9 : ZEP600+620+624+706+704+702+ +DFV L Avi/TCN V2 (Jusqu'au C603 Km 759,095)    Etendue S11 : du Km 758,757 au Km 742,573  Domaine S11 :  Sel 2112+2114 SR Champfleury/les Olivettes voie",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13836816961",null,"< >","Avignon-Fontcouverte - Aig Km 3,383","Cavaillon - Bât Voyageurs",2024,2024,44,47,"2024-10-28","08:25:00","2024-11-22","16:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx PPx V1+V2 (de S44 à S47), -Avignon Fontcouverte exclu à Miramas exclu- et à prendre avec 4D_AFT-CVN_028  :  Etendue S9 : V1 de la PATC Km 4,283 au C507 au Km 66,880 de Mas / V2 De la PATC Km 65,976 au C88 Km 3,645   Domaine S9 : DFV L CAV-MAS V1/ V2+ ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14644066861",null,"< >","Avignon-Fontcouverte - Aig Km 3,383","Cavaillon - Bât Voyageurs",2024,2024,26,37,"2024-06-24","08:35:00","2024-09-15","16:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SR Voie AMS, de S26 à S36,Tvx connexes et hors suite  et S37 Tvx Préparatoires -Avignon Fontcouverte exclu Cavaillon exclu- DEF de 08h00 :  Etendue S9 : V1 de la PATC Km 4,283 (AFT) au C1 Km 32,188 / V2 de la PATC km 32,167 (CAV) au C88 Km 3,645  Domaine ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687038861",null,"< >","Avignon-Fontcouverte - Chantier TAC","Avignon-Fontcouverte - Fais Récep Pair",2024,2024,42,50,"2024-10-14","09:10:00","2024-12-13","13:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PRO RD907 PK 2,247 (mise en peinture)-bout de S11 V1AMS- :   Etendue S9 : du JI z121/123 Km 2,092 au Cv64 V5à11 Km 2,341 + Cv65 V15à27 Km 2,341 / de la butte Km 1,846 au Cv47 Km 2,255 /V1 AMS du C35 Km 1,902 au Cv62 Km 2,427 / V2 AMS du Cv37 Km 2,048 au C",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687038061",null,"< >","Avignon-Fontcouverte - Chantier TAC","Avignon-Fontcouverte - Fais Récep Pair",2024,2024,37,41,"2024-09-09","09:10:00","2024-10-11","15:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PRO RD907 PK 2,247 (mise en peinture)-bout de S11 V1AMS- :   Etendue S9 : du JI z121/123 Km 2,092 au Cv64 V5à11 Km 2,341 + Cv65 V15à27 Km 2,341 / de la butte Km 1,846 au Cv47 Km 2,255 /V1 AMS du C35 Km 1,902 au Cv62 Km 2,427 / V2 AMS du Cv37 Km 2,048 au C",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687026661",null,"< >","Avignon-Fontcouverte - Chantier TAC","Cavaillon - Bât Voyageurs",2024,2024,50,50,"2023-12-11","13:03:00","2024-12-13","14:33:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_15 : vibration de +13mn pour avoir TER 879632 en SO  2021_SE_113 : décalage de quelques minutes pour avoir 879636 en SO et 879671 en SF et FEN21_Avignon-Cavaillon_002 à avancer pour avoir 879636 en SO pour aligner les surveillances sur l'axe  Déca",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687036061",null,"< >","Avignon-Fontcouverte - Fais Réc Impair","Cavaillon - Bât Voyageurs",2024,2024,9,11,"2024-02-26","09:17:00","2024-03-15","14:47:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"RPU Maintenance Voie BML VC avec B1N+Régaleuse : Format Générique + 1h30= 09h10 /14h40 soit 05h30  Domaine S9 : DFV L CAV-AFT V1+ V2 Domaine S11 : néant TO : 50541/879650 TF :",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687027461",null,"< >","Avignon-Fontcouverte - Fais Réc Impair","Cavaillon - Bât Voyageurs",2024,2024,50,50,"2023-12-11","11:00:00","2024-12-13","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2023/Main Courante PCO_SE/demande n°75 : vibration <10mn pour passage 879688 (SO 879622/SF 879688)  Décalage mineure MC17-0060 pour 879608 ouvrant et 879610  Main courante MAJ 224 pour train 879660 le 14/10/15  2021_SE_56 : décalage de +01h pour avoir 8",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13836831161",null,"< >","Avignon-Fontcouverte - Fais Récep Pair","Cavaillon - Bât Voyageurs",2024,2024,48,50,"2024-11-25","08:25:00","2024-12-13","16:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx PPx V1+V2 (de S48+49+50 SA2024 et 51 de 2024 sur SA2025) -Avignon Fontcouverte inclus à Miramas exclu-, à prendre avec 4C_AV_068+4C_CVN_010 :    Etendue S9 : V1 du Km 0+730 (Cv105 d'AFT) au Km 66+880 (C507 de Mas) et V2 au Km 65+976 (PATC de Mas) au K",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687363461",null,"< >","Berre","Vitrolles-Aéroport-Marseille-P",2024,2024,50,40,"2023-12-12","22:35:00","2024-10-04","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CCR OUEST P. -Etape1- : CAP V2EVIT Berre + V4G RGC (06h55 du Ma/Me au Ve/Sa)  Domaine S9, V2 EVIT Berre : ZEP G 862  Domaine S9, V4G RGC : ZEP G 28+34  Nota : Les autres voies côté Pair de Berre et de Rognac ne peuvent pas être réservées dans TCAP, elles ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687359061",null,"< >","Berre","Rognac - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:46:00","2024-12-13","11:49:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_28 : vibration de -10' pour avoir TER 17701 en SO et TER 886565 en SF  MC19-0032 le 19/09/17 pour alignement sur 9F_MAS-RGC_002 MC19-0147 le 10/11/17 calage entre 879653 et 879655 Modif main courante 2020 Maj-548-871     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687359861",null,"< >","Berre","Rognac - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:08:00","2024-12-13","11:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Annulation Décalage MC17-0228 pour 879610 2021_SE_66 : décalage de +40mn pour avoir 879518 en SO et 879522 en SF, aligné V2 de St Louis à Tarascon, le 19/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689881261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure de 06h00 IHM1 pendant la Mise En Service",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2024-01-15","10:35:00","2024-02-02","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14127821161",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,38,45,"2024-09-16","09:30:00","2024-11-07","17:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261     TF: 17764",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14382904161",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,33,50,"2024-08-13","09:50:00","2024-12-13","15:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 17756   TF: Sans",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14382883761",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,35,49,"2024-08-26","09:50:00","2024-12-06","16:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 17756    TF: Sans",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14997595861",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,38,45,"2024-09-20","09:30:00","2024-11-08","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261     TF: 6706",null,null,null,null,"High","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2024-08-12","10:35:00","2024-08-12","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2024-10-23","10:35:00","2024-10-24","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2024-06-17","10:35:00","2024-06-21","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13861527461",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,14,14,"2024-04-02","10:35:00","2024-04-05","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Utilisation des 4 Pas au lieu des 2 autorisés par la 4F_BSB-DN_001  Circulation des trains en bana sur la voie non utilisée par les travaux.  Croisement possible à Malain et Plombières",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14127821161",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,38,45,"2024-09-30","09:30:00","2024-10-10","17:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261     TF: 17764",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14382883761",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,35,49,"2024-11-25","09:50:00","2024-11-29","16:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 17756    TF: Sans",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15111243161",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,9,9,"2024-02-26","13:25:00","2024-02-29","14:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 891907    TF: 9268",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689877261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,11,11,"2024-03-16","12:00:00","2024-03-16","11:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"   T0: 9211 du Sa        TF: 9211 du Di  (Amplitude initiale Coupure de 24h00  Abaisser à 23h40 pour le SA2023   )",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15111256061",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,9,17,"2024-02-26","11:10:00","2024-04-25","12:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 6703     TF: 891904",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15111252961",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,13,13,"2024-03-25","10:20:00","2024-03-28","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9206   TF: 9210",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15138737861",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,15,16,"2024-04-13","23:50:00","2024-04-21","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14928112061",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,44,44,"2024-11-02","19:50:00","2024-11-02","13:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1 + 2  TO: 17766    TF: 891375/6704",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14997595861",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,38,45,"2024-10-04","09:30:00","2024-10-11","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261     TF: 6706",null,null,null,null,"High","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15138724361",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,15,16,"2024-04-13","00:45:00","2024-04-20","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14642076061",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689879261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance IHM 1 ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2024-04-08","10:35:00","2024-04-26","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14366709061",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MES LGV+",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689870261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,50,"2023-12-11","10:35:00","2024-12-13","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Accord en CODAB le 26/09/2016 pour 37 semaines  Ajout du 12/08 par DECC24_00025 rattaché au CHA24_0026195 « RVB HSI Baulme la Roche - Dijon ».",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689868661",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,50,33,"2023-12-17","00:05:00","2024-08-18","02:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401110 Corrective activable en même temps que sur la V1, a condition que la simultanée n'impacte pas de sillon                  ",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689871261",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,52,34,"2023-12-27","11:17:00","2024-08-23","12:01:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401058 Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689869461",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,52,34,"2023-12-26","10:41:00","2024-08-23","11:53:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401030 Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689872061",null,"< >","Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2024,2024,51,34,"2023-12-18","02:07:00","2024-08-19","05:21:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401109 Corrective activable en même temps que sur la V2, a condition que la simultanée n'impacte pas de sillon                             ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14928571161",null,"< >","Blaisy-Bas","Mâlain - Bât Voyageurs",2024,2024,15,15,"2024-04-08","10:50:00","2024-04-08","12:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 6703   TF: 6705",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13854459661",null,"< >","Blaisy-Bas","Mâlain - Bât Voyageurs",2024,2024,43,43,"2024-10-21","10:15:00","2024-10-22","12:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 17753   TF: 6705",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15002468261",null,"< >","Bondy - Bât Voyageurs","Bondy - Bât Voyageurs",2024,2024,10,12,"2024-03-08","23:30:00","2024-03-18","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Zone 2               ",null,null,null,null,"High","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14998835161",null,"< >","Bondy - Bât Voyageurs","Bondy - Bât Voyageurs",2024,2024,8,13,"2024-02-20","23:00:00","2024-03-28","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Zone 2              ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13997810061",null,"< >","Bondy - Bât Voyageurs","Bondy - Bât Voyageurs",2024,2024,8,13,"2024-02-20","23:00:00","2024-03-28","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Zone 1  ZEP 610+776+774+772+770+782+780+736  ZEP 620+784+788+786  ZEP 810+812                  ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15002437261",null,"< >","Bondy - Bât Voyageurs","Bondy - Bât Voyageurs",2024,2024,10,12,"2024-03-08","23:30:00","2024-03-18","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Zone 1                   ",null,null,null,null,"High","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673326261",null,"< >","Bondy - Bât Voyageurs","Le Raincy-Villemomble-Montferm",2024,2024,40,40,"2024-09-30","12:50:00","2024-10-02","14:48:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2L1 : ZEP 742,744 CHL (aig. 2660a,2664b,2745a)   ",null,null,null,null,"Medium","1,2,3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673325461",null,"< >","Bondy - Bât Voyageurs","Le Raincy-Villemomble-Montferm",2024,2024,40,40,"2024-10-03","11:09:00","2024-10-04","12:57:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1L1 : ZEP 761 CHL (aig. 2743b,2745b) ",null,null,null,null,"Medium","4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2024-04-15","23:30:00","2024-04-19","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2024-03-04","23:30:00","2024-03-08","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2024-02-12","23:30:00","2024-10-10","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15304959061",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,40,40,"2024-09-30","22:30:00","2024-10-02","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP                       ",null,null,null,null,"Medium","1,3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-12","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2024-03-11","23:30:00","2024-05-03","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14000040161",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,16,16,"2024-04-19","23:30:00","2024-04-21","16:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TOUT VAIRES P5   Restitution 16h40 pour TER 839165 acté en Conciliation N°3 Désaccords RP0 2024",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673329461",null,"< >","Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-13","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15222684661",null,"< >","Brienon","St-Florentin-Vergigny - Bât Voyageurs",2024,2024,36,36,"2024-09-02","10:00:00","2024-09-03","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14552398361",null,"< >","Brienon","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,35,35,"2024-08-26","08:15:00","2024-08-30","16:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14390397161",null,"< >","Brienon","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,49,37,"2023-12-10","23:10:00","2024-09-14","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14606420461",null,"< >","Brienon","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,45,45,"2024-11-10","22:10:00","2024-11-10","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14390276661",null,"< >","Brienon","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,49,49,"2023-12-10","00:00:00","2023-12-10","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14606711861",null,"< >","Brienon","St-Florentin-Vergigny - Voie 4 Garage",2024,2024,11,12,"2024-03-12","08:51:00","2024-03-20","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15222787761",null,"< >","Brienon","St-Florentin-Vergigny - Voie 4 Garage",2024,2024,36,36,"2024-09-02","10:00:00","2024-09-03","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15202420661",null,"< >","Brienon","Flogny",2024,2024,39,39,"2024-09-28","08:00:00","2024-09-29","18:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687195461",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,50,50,"2023-12-11","10:22:00","2024-12-13","10:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MC19-0027 pour calage entre 879606 et 879654 Modif par la main courante 2020 Maj-570-871 2021_SE_58 : décalage de -40mn pour avoir 879662 en SO(train rapide) et 879622 en SF (train lent), aligné V2 de Miramas à Avignon, le 19/11/2019 2022_SE_15 : vibratio",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687198661",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,9,11,"2024-02-26","09:17:00","2024-03-15","14:47:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_74 : vibration de +7' pour avoir FRET LDMC17 en SO (vibration imposée aussi sur 4D_AFT-CVN_009 pour maintenir l'alignement)   RPU Maintenance Voie BML VC avec B1N+Régaleuse :  Format Générique + 1h30= 09h10 /14h40 soit 05h30   Domaine S9 : DFV L C",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14696392861",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,17,48,"2024-04-27","22:10:00","2024-11-30","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, Maint, DEF 08h00, L925 V1+V2+V1S+V2S+1Racct+2Racct, du Sa 22h10 au Di 06h10 (du 30/03 au 31/03 + 23/11 au 24/11 + 30/11 au 01/12 ) :  Etendue S9 : V1 de la PATC de CAV Km 38,695 au C507 Km 66,880 jusqu'au JI Z605/617 Km 68,130 (V1S) / V2 du C24 de",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687209461",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,44,47,"2024-10-28","08:25:00","2024-11-22","16:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx Ppx 08h30 -de S44 à 47 - Avignon Fontcouverte exclu à Miramas exclu -  :  Tvx PPx V1+V2 (de S44 à S47), -Avignon Fontcouverte exclu à Miramas exclu- et à prendre avec 4D_AFT-CVN_028  :  Etendue S9 : V1 de la PATC Km 4,283 au C507 au Km 66,880 de Mas /",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13836688561",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,48,50,"2024-11-25","08:25:00","2024-12-13","16:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx PPx V1+V2 (de S48+49+50 SA2024 et 51 de 2024 sur SA2025) -Avignon Fontcouverte inclus à Miramas exclu-, à prendre avec 4C_AV_068+4C_CVN_010+4C_AFT-CVN_002+4D_AFT-CVN_029 :    Etendue S9 : V1 du Km 0+730 (Cv105 d'AFT) au Km 66+880 (C507 de Mas) et V2 a",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14737175761",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,37,43,"2024-09-09","08:35:00","2024-10-25","17:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx Préparatoires, Principaux, ou Finitions 08h40 -Miramas inclus à Cavaillon exclu - S37+38+S39 LU, MA+S40 JE, VE+S41 ET S39 ME, JE, VE+S40 LU, MA, ME ET S42+43 :  Etendue S9 : V1 de la PATC Km 38,695 au C507 au Km 66,880 => JI Z 605/617 km 67.837 de Mas",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14644009261",null,"< >","Cavaillon - Bât Voyageurs","Miramas ITE SMEA",2024,2024,26,36,"2024-06-24","08:35:00","2024-09-06","16:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SR Voie AMS, de S26 à S36,Tvx connexes et hors suite et S37 Tvx Préparatoires , -Cavaillon exclu à Miramas exclu- DEF de 08h00 :  Etendue S9 : V1 de la PATC Km 38,695 au C507 au Km 66,880 / V2 de la PATC Km 65,976 au C24 Km 34,100  Domaine S9 : DFV L CAV-",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687197061",null,"< >","Cavaillon - Bif ChevalBlanc","Miramas ITE SMEA",2024,2024,50,50,"2023-12-11","13:42:00","2024-12-13","15:07:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_16 : vibration de +7' pour avoir TER 879632 en SO  2021_SE_113 : décalage de quelques minutes pour avoir 879636 en SO et 879671 en SF et FEN21_Avignon-Cavaillon_002 à avancer pour avoir 879636 en SO pour aligner les surveillances sur l'axe  Décala",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703654261",null,"< >","Champ-de-Courses-d'Enghien","Ermont-Eaubonne - Garage Pair",2024,2024,50,50,"2023-12-12","01:30:00","2024-12-14","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703656461",null,"< >","Champ-de-Courses-d'Enghien","Ermont-Eaubonne - Garage Pair",2024,2024,1,50,"2024-09-30","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC industrielles     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703656461",null,"< >","Champ-de-Courses-d'Enghien","Ermont-Eaubonne - Garage Pair",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC industrielles     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673354461",null,"< >","Chézy-sur-Marne","Mézy - Poste U",2024,2024,42,43,"2024-10-18","23:00:00","2024-10-25","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP de type G 201 + 202 + 203 + 204 + 205 + 207 + 209 + 210 + 211 + 212 + 213 + 214 + 216 + 222 + 224 + 226 + 301 + 309 + 311 + 313 + 315 + 317 Château Thierry   ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14561746161",null,"< >","Choisy-le-Roi - Bât Voyageurs","Villeneuve-le-Roi",2024,2024,50,50,"2023-12-12","08:44:00","2024-12-10","09:44:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PAZ(CLR) C727  à  PAZ(CLR) S10,7",null,null,null,null,"Major","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14376091661",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","23:20:00","2024-12-13","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"JUVISY C102  à  CHOISY LE ROI C528",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14376033161",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","22:45:00","2024-12-13","05:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"JUVISY C104 15.905 21:10 05:50 à  PAZ(CLR) C728 10,320 21:10 05:50",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14719463761",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,3,42,"2024-01-19","23:20:00","2024-10-14","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575986361",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,21,41,"2024-05-26","23:30:00","2024-10-13","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"JY C104 A PAZ C728     ",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14719475461",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,21,41,"2024-05-25","10:15:00","2024-10-13","15:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15133556461",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,18,44,"2024-04-30","23:20:00","2024-10-31","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"JUVISY C102  à  CHOISY LE ROI C528",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14376091661",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2024-11-13","23:20:00","2024-11-14","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"JUVISY C102  à  CHOISY LE ROI C528",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575966361",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","00:10:00","2024-12-09","03:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575964761",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","00:25:00","2024-12-09","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14700315261",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,36,42,"2024-09-08","23:45:00","2024-10-20","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575967961",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2024-09-27","23:13:00","2024-09-27","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h par voie sur V1 et V2 dont min 3h10 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy) 3690 ouvrant 142144 (ou 141142) et 143844 (ou 141844) circulent V2bis                    ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575986361",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,21,41,"2024-09-28","23:30:00","2024-09-29","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"JY C104 A PAZ C728     ",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14717993961",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,39,39,"2024-09-29","00:05:00","2024-09-29","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14651501661",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2024-09-27","23:20:00","2024-09-27","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14651501661",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","23:20:00","2024-12-13","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575967961",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2023-12-11","23:13:00","2024-12-13","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h par voie sur V1 et V2 dont min 3h10 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy) 3690 ouvrant 142144 (ou 141142) et 143844 (ou 141844) circulent V2bis                    ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575968761",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,51,36,"2023-12-19","00:10:00","2024-09-07","04:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h 2V/4 dont 4h de sim. et Incompatible avec fenêtre longue voies dir sur Choisy<->Juvisy(Choisy-Juvisy)                                               ",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14651501661",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2024-04-24","23:20:00","2024-04-29","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575967961",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Ent/Sort VDTA",2024,2024,50,50,"2024-04-24","23:13:00","2024-04-30","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h par voie sur V1 et V2 dont min 3h10 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy) 3690 ouvrant 142144 (ou 141142) et 143844 (ou 141844) circulent V2bis                    ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14376128961",null,"< >","Choisy-le-Roi - Déviation Sud","Juvisy - Poste B",2024,2024,50,28,"2023-12-11","22:45:00","2024-07-12","05:47:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PAZ(CLR) Jiz 273/285  à  JUVISY C203",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14376274561",null,"< >","Choisy-le-Roi - E/S V1V","Villeneuve-le-Roi",2024,2024,50,50,"2023-12-11","23:18:00","2024-12-13","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHOISY LE ROI JIZ 241/245  à  PANCARTE ARRET 10.728",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14375806461",null,"< >","Choisy-le-Roi - E/S V1V","Villeneuve-le-Roi",2024,2024,50,50,"2023-12-11","22:45:00","2024-12-13","05:47:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PAZ(CLR) C725 à  PANCARTE ARRET 10.728",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14761032761",null,"< >","Choisy-le-Roi - E/S V1V","Villeneuve-le-Roi",2024,2024,10,11,"2024-03-08","23:20:00","2024-03-11","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHOISY LE ROI JIZ 241/245 à  PAZ (CLR) PATC",null,null,null,null,"Medium","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15133515261",null,"< >","Choisy-le-Roi - E/S V1V","Villeneuve-le-Roi",2024,2024,18,44,"2024-04-30","23:15:00","2024-10-31","05:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHOISY LE ROI JIZ 241/245  à  PANCARTE ARRET 10.728",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14725523361",null,"< >","Choisy-le-Roi - E/S V1V","Choisy-le-Roi - Déviation Sud",2024,2024,22,47,"2024-06-01","00:00:00","2024-11-18","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PAZ(CLR) C725 à  PAZ(CLR) C727",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14375958861",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,28,"2023-12-11","23:18:00","2024-07-12","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHOISY LE ROI JIZ 241/245  à  JUVISY C205 16,590",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14719451261",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,3,42,"2024-01-19","23:18:00","2024-10-14","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14719469761",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,21,41,"2024-05-25","09:50:00","2024-10-13","14:52:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14719484861",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,21,41,"2024-05-26","23:20:00","2024-10-13","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15133680161",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,18,44,"2024-04-30","23:20:00","2024-10-31","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHOISY LE ROI JIZ 241/245  à  JUVISY C205 16,590",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15535469261",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,9,11,"2024-03-02","00:00:00","2024-03-11","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PAZ(CLR) C725 à  JUVISY C203",null,null,null,null,"Medium","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","16273658561",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,3,7,"2024-01-19","23:25:00","2024-02-18","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","5,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","16273788261",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,3,7,"2024-01-21","00:40:00","2024-02-18","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PAZ(CLR) C725 à  JUVISY C203",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575965561",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2023-12-11","01:05:00","2024-12-09","05:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575967161",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2023-12-11","00:25:00","2024-12-09","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575971961",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2023-12-11","23:23:00","2024-12-13","05:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h par voie V1 et V2 avec min 3h10 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy)               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14651543761",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2023-12-11","23:15:00","2024-12-13","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575970361",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,51,37,"2023-12-19","01:00:00","2024-09-11","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h par voie V1 et V2 dont min 3h10 de sim 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy)                   ",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13575971961",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2024-04-22","23:23:00","2024-04-30","05:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h par voie V1 et V2 avec min 3h10 4V/4. Incompatible avec fenêtre longue voies bis sur Choisy<->Juvisy(Choisy-Juvisy)               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14651543761",null,"< >","Choisy-le-Roi - E/S V1V","Juvisy - Poste B",2024,2024,50,50,"2024-04-25","23:15:00","2024-04-30","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14867464261",null,"< >","Claveyson-Bren","Poste 52 Upie",2024,2024,6,37,"2024-02-10","23:10:00","2024-09-14","05:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage créée pour le CHA20_0018098, essai de poste à poste avec l'infrapôle Alpes le SA/DI  Toute la zone du poste 51 d'Alixan TGV est concernée  Plage sans impact pour les circulations.",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14867374861",null,"< >","Claveyson-Bren","Poste 52 Upie",2024,2024,6,7,"2024-02-09","23:55:00","2024-02-16","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage créée pour le CHA20_0018098, essai de poste à poste avec l'infrapôle Alpes le VE/SA  Toute la zone du poste 51 d'Alixan TGV est concernée  Plage sans impact pour les circulations.",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14867534561",null,"< >","Claveyson-Bren","Poste 52 Upie",2024,2024,6,7,"2024-02-11","23:55:00","2024-02-18","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage créée pour le CHA20_0018098, essai de poste à poste avec l'infrapôle Alpes le DI/LU  Toute la zone du poste 51 d'Alixan TGV est concernée  Plage sans impact pour les circulations.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14714567061",null,"< >","Condrieu","Sarras",2024,2024,12,21,"2024-03-18","07:45:00","2024-05-24","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créé pour CHA24_0025937 RVB PEY  Toutes ZEP de Peyraud P1 - + Zep 426  438  442 de St Rambert - + ZEP type L Entre PEY et LVO V1 et V2  Sr Limony - Peyraud V1   Sr Limony - Peyraud V2  Sr. Peyraud - Ozon V1  Sr. Peyraud - Ozon V2   S.El 18P S.El 20P du Se",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14481961961",null,"< >","Corbeil-Essonnes - Bif Km 33","Essonnes-Robinson",2024,2024,50,27,"2023-12-11","23:10:00","2024-07-05","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14482116961",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,2,18,"2024-01-08","21:15:00","2024-05-03","05:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14483016661",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,4,10,"2024-01-22","08:42:00","2024-03-08","17:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14482973261",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,19,25,"2024-05-06","08:42:00","2024-06-21","17:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14482340961",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,28,31,"2024-07-08","23:10:00","2024-08-02","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14482271061",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,26,27,"2024-06-24","22:00:00","2024-07-05","05:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14481897861",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,50,51,"2023-12-11","21:45:00","2023-12-22","05:41:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14552785561",null,"< >","Corbeil-Essonnes - Bif Km 33","Villabé",2024,2024,37,38,"2024-09-13","23:00:00","2024-09-20","05:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15183724661",null,"< >","Croix-Sainte","Martigues - Bât Voyageurs",2024,2024,10,48,"2024-03-04","22:30:00","2024-11-29","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SM+Télécommande Pont de Caronte, sans aménagement d'ouverture de Pont : PORT DE BOUC - MARTIGUES (MIRAMAS - MARSEILLE-ST CH (PORT DE BOUC) MARSEILLE-MARITIME SUD DE MIRAMAS)        Ouvertures et fermetures liées à la manoeuvre du viaduc de Caronte  Etendu",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14537508361",null,"< >","Croix-Sainte","Martigues - CV 878",2024,2024,8,38,"2024-02-19","22:30:00","2024-09-22","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avi :  Domaine S9 : ZEP 33+40+46(V4)+75(Sortie VS 3 à 11) ou ZEP 35+38 ou ZEP 42(V4G)+74 ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14753954761",null,"< >","Dijon-Ville - C4104","Dijon-Ville - Aiguilles Nord",2024,2024,26,26,"2024-06-24","10:40:00","2024-06-28","15:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4C_DN_194",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14753882061",null,"< >","Dijon-Ville - C4104","Dijon-Ville - Aiguilles Nord",2024,2024,10,10,"2024-03-10","22:15:00","2024-03-10","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4C_DN_183",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14458077361",null,"< >","Ebange - Accès Nord","Thionville - Dépôt",2024,2024,22,22,"2024-05-30","10:00:00","2024-05-31","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 815+846, Voie B+1B / Accès VA interdit",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457558961",null,"< >","Ebange - Accès Nord","Thionville - Dépôt",2024,2024,16,16,"2024-04-15","10:00:00","2024-04-16","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 817, Voie 1+2L7",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457539261",null,"< >","Ebange - Accès Nord","Thionville - Dépôt",2024,2024,15,15,"2024-04-12","10:00:00","2024-04-13","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 2h30 jour, zep 818, Voie 2Bis",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462167361",null,"< >","Ebange - Accès Nord","Thionville - Jonctions Nord",2024,2024,32,32,"2024-08-08","10:00:00","2024-08-09","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h30 jour, zep 843+817, Voie D+1 - Accès L204 interdit (vers 2L7)",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457838361",null,"< >","Ebange - Accès Sud","Ebange - Aig VL90",2024,2024,16,16,"2024-04-17","10:00:00","2024-04-18","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Déf 1h30 jour, zep 156 d'Uckange, V2B",null,null,null,null,"Medium","3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14000079461",null,"< >","Ebange - Accès Sud","Ebange - Jonction Nord",2024,2024,6,6,"2024-02-07","11:30:00","2024-02-08","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf V1B+V2B entre Thionville et Uckange. Avec 4C_THL_098.",null,null,null,null,"Medium","3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14458025261",null,"< >","Ebange - Aig VL90","Ebange - Accès Nord",2024,2024,22,22,"2024-05-27","10:00:00","2024-05-28","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 802, Voie 2",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13675990061",null,"< >","Ebange - Faisceau","Thionville - FSC Luxembourg",2024,2024,44,44,"2024-11-02","08:00:00","2024-11-03","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 7h SA, V1B+V2B. Accès Ebange AN interdit. Report des circulations sur V1/V2 entre THL et UCK. Voies A+B+C interdites.",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14549694761",null,"< >","Ebange - Faisceau","Thionville - Bif L3/L7",2024,2024,8,8,"2024-02-20","11:30:00","2024-02-23","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 4h jour, V1+V2 à Thionville, MA à VE. Avec 4F_UCK-THL_001, 4F_UCK-THL_002 et 4D_UCK_034 qui reprend les conséquences circulations. (zep 811,803,801,802)",null,null,null,null,"Medium","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14549526361",null,"< >","Ebange - Faisceau","Thionville - Bif L3/L7",2024,2024,8,8,"2024-02-19","09:30:00","2024-02-20","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 6h jour, V1+V2 à Thionville, LU. Avec 4F_UCK-THL_005, 4F_UCK-THL_006 et 4D_UCK_033 qui reprend les conséquences circulations. (zep 811,803,801,802)",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14000156161",null,"< >","Ebange - Faisceau","Ebange - Accès Nord",2024,2024,6,6,"2024-02-07","11:30:00","2024-02-08","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap V1B+V2B Thionville. Avec 4D_UCK-THL_005.       ",null,null,null,null,"Medium","3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14000107561",null,"< >","Ebange - Faisceau","Ebange - Accès Nord",2024,2024,6,6,"2024-02-05","11:30:00","2024-02-06","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap V1+V2 Thionville. Avec 4D_UCK-THL_005.       ",null,null,null,null,"Medium","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14458010161",null,"< >","Ebange - Faisceau","Ebange - Jonction Nord",2024,2024,17,17,"2024-04-26","10:00:00","2024-04-27","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 2h30 jour, zep 804, Voie 2Bis",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676084061",null,"< >","Ebange - Faisceau","Thionville - Jonctions Nord",2024,2024,44,44,"2024-11-03","08:00:00","2024-11-04","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 7h DI, V1+V2B+VD+VC. Report des circulations V1B/V2 entre THL et UCK. Accès 204000 sens THL-->LGN(2L7) interdit. Voies C+D interdites. ",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15120169561",null,"< >","Ebange - Faisceau","Thionville - Jonctions Nord",2024,2024,14,16,"2024-04-01","23:55:00","2024-04-19","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 4h30 nuit, V1B+V2B+A+B+C, Thionville côté Sud.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457677361",null,"< >","Ebange - Jonction Nord","Thionville - Bif L3/L7",2024,2024,16,16,"2024-04-16","10:00:00","2024-04-17","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 2h jour, zep 811+814, Voies 1+2B",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703631461",null,"< >","Enghien-les-Bains","Ermont-Eaubonne - Poste 1",2024,2024,50,36,"2024-07-09","01:05:00","2024-08-04","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703631461",null,"< >","Enghien-les-Bains","Ermont-Eaubonne - Poste 1",2024,2024,50,36,"2023-12-11","01:05:00","2024-09-08","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14352010261",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-09","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703635061",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703635061",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,1,50,"2024-03-04","23:35:00","2024-07-07","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703634261",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,50,50,"2024-07-09","00:55:00","2024-08-04","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703630661",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,50,50,"2024-07-09","00:30:00","2024-08-04","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14630464561",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,23,24,"2024-06-07","23:35:00","2024-06-10","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703635061",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,1,50,"2024-09-30","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703630661",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,50,50,"2023-12-11","00:30:00","2024-12-14","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703634261",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2024,2024,50,50,"2023-12-11","00:55:00","2024-12-14","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14329314461",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Poste 1",2024,2024,38,39,"2024-09-20","23:35:00","2024-09-27","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14869528861",null,"< >","Epinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Poste 1",2024,2024,38,40,"2024-09-22","01:30:00","2024-09-30","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14137283861",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Ermont-Eaubonne - Garage Pair",2024,2024,1,50,"2024-09-30","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC INDUS",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14352976161",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Ermont-Eaubonne - Garage Pair",2024,2024,46,48,"2024-11-15","23:35:00","2024-11-25","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14137283861",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Ermont-Eaubonne - Garage Pair",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC INDUS",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703604261",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703603461",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2024,2024,50,50,"2023-12-12","01:30:00","2024-12-14","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703601861",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2024,2024,50,36,"2023-12-12","00:30:00","2024-09-08","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703604261",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2024,2024,1,50,"2024-09-30","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14352999361",null,"< >","Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2024,2024,46,48,"2024-11-15","23:35:00","2024-11-25","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703651861",null,"< >","Ermont-Eaubonne - Garages Impairs","Cernay (Val-d'Oise)",2024,2024,1,50,"2024-09-30","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14352987061",null,"< >","Ermont-Eaubonne - Garages Impairs","Cernay (Val-d'Oise)",2024,2024,46,48,"2024-11-15","23:35:00","2024-11-25","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703651861",null,"< >","Ermont-Eaubonne - Garages Impairs","Cernay (Val-d'Oise)",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703650861",null,"< >","Ermont-Eaubonne - Garages Impairs","Cernay (Val-d'Oise)",2024,2024,50,50,"2023-12-12","01:30:00","2024-12-14","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14352949461",null,"< >","Ermont-Eaubonne - Poste 1","Ermont-Eaubonne - Bât Voyageurs",2024,2024,46,48,"2024-11-15","23:35:00","2024-11-25","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14352960361",null,"< >","Ermont-Eaubonne - Poste 1","Ermont-Eaubonne - Garage Pair",2024,2024,46,48,"2024-11-15","23:35:00","2024-11-25","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673407261",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,40,50,"2024-09-30","23:10:00","2024-12-13","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673408861",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,46,48,"2024-11-15","23:10:00","2024-11-25","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13884886761",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,48,48,"2024-11-29","23:10:00","2024-12-01","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13872234161",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,45,46,"2024-11-08","23:10:00","2024-11-11","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15733405461",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,43,43,"2024-10-27","21:30:00","2024-10-27","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15614938461",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,44,45,"2024-10-31","23:10:00","2024-11-04","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,4,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15733367261",null,"< >","Esbly","Meaux - ITE ZI",2024,2024,43,43,"2024-10-25","23:10:00","2024-10-27","18:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672978261",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Troyes - Aig OE-Preize",2024,2024,5,41,"2024-01-30","00:15:00","2024-04-20","05:13:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Fenêtre Courte                                                                     ",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672978261",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Troyes - Aig OE-Preize",2024,2024,5,41,"2024-03-12","00:15:00","2024-10-12","05:13:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Fenêtre Courte                                                                     ",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672979261",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Troyes - Aig OE-Preize",2024,2024,15,24,"2024-04-08","00:00:00","2024-06-10","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672978261",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Troyes - Aig OE-Preize",2024,2024,5,41,"2024-02-13","00:15:00","2024-02-24","05:13:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Fenêtre Courte                                                                     ",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672976661",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Troyes - FSC St-Luc",2024,2024,15,24,"2024-04-08","01:30:00","2024-06-10","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672975861",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Romilly-sur-Seine - Bât Voyageurs",2024,2024,50,49,"2023-12-11","12:57:00","2024-12-06","13:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672980061",null,"< >","Flamboin-Gouaix - Bât Voyageurs","Romilly-sur-Seine - Bât Voyageurs",2024,2024,50,49,"2023-12-11","10:54:00","2024-12-06","12:12:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14472067061",null,"< >","Fos-Coussoul - Poste 1","Fos-Viguerat - Poste 1",2024,2024,10,49,"2024-04-29","22:40:00","2024-05-05","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, Epurations, UP Voie Avignon :  Domaine S9 : ZEP L FOS-VIG V1 (étendue V1 PATC de FOC Km 6,015 au C303 Viguerat au Km 11,215) + ZEP L VIG-FOC V2 (étendue Du C8 Km 4,945 à la PATC de VIG Km 10,379) Domaine S11 : sans  ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14472067061",null,"< >","Fos-Coussoul - Poste 1","Fos-Viguerat - Poste 1",2024,2024,10,49,"2024-03-04","22:40:00","2024-12-06","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, Epurations, UP Voie Avignon :  Domaine S9 : ZEP L FOS-VIG V1 (étendue V1 PATC de FOC Km 6,015 au C303 Viguerat au Km 11,215) + ZEP L VIG-FOC V2 (étendue Du C8 Km 4,945 à la PATC de VIG Km 10,379) Domaine S11 : sans  ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703602661",null,"< >","Franconville-Plessis-Bouchard","Montigny-Beauchamp - Tiroir",2024,2024,7,50,"2024-02-13","01:30:00","2024-12-14","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14513391661",null,"< >","Gagny Raccordement - Bif Nord","Gagny Raccordement - Bif Est",2024,2024,2,47,"2024-01-08","08:30:00","2024-11-24","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14513391661",null,"< >","Gagny Raccordement - Bif Nord","Gagny Raccordement - Bif Est",2024,2024,2,47,"2024-01-08","08:30:00","2024-11-24","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14513947061",null,"< >","Gagny Raccordement - Bif Nord","Gagny Raccordement - Bif Est",2024,2024,50,47,"2023-12-16","08:30:00","2024-11-18","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703595461",null,"< >","Gennevilliers - Ent/Sort Sud","Gennevilliers - Ent/Sort Sud",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC industrielle",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703592861",null,"< >","Gennevilliers - Garages","Ermont-Eaubonne - Bât Voyageurs",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-14","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14484261261",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,19,33,"2024-05-10","23:25:00","2024-08-16","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14483605961",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,25,25,"2024-06-21","21:30:00","2024-06-23","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14713557161",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,49,49,"2024-12-04","00:35:00","2024-12-04","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14713837161",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,13,13,"2024-03-29","23:20:00","2024-03-29","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP38117+38124",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14119230261",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,44,49,"2024-10-28","22:55:00","2024-12-06","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP38117+38124",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14119239461",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,46,48,"2024-11-11","21:30:00","2024-11-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP38117+38124",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14471018661",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,38,38,"2024-09-16","23:35:00","2024-09-20","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP425+443",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14471328561",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,39,41,"2024-09-23","22:00:00","2024-10-11","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP423+425+427+443",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14471413861",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,39,41,"2024-09-23","23:35:00","2024-10-12","04:35:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP443",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","14509562861",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,8,8,"2024-02-19","23:35:00","2024-02-19","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP443+449",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15102547461",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,12,12,"2024-03-21","21:15:00","2024-03-21","23:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP441",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14657724161",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,11,11,"2024-03-13","21:15:00","2024-03-13","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP441",null,null,null,null,"Medium","3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15102549761",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,12,12,"2024-03-21","23:40:00","2024-03-21","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP441",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15102552261",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,12,12,"2024-03-22","23:50:00","2024-03-22","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP441",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15102556261",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,12,12,"2024-03-22","21:00:00","2024-03-22","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP443",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14657832461",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,11,11,"2024-03-14","21:00:00","2024-03-14","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP443",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14713724861",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,49,49,"2024-12-05","00:35:00","2024-12-06","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2024-07-16","22:15:00","2024-07-25","05:09:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2023-12-11","22:15:00","2023-12-15","05:09:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2023-12-11","22:15:00","2024-06-14","05:09:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15088750061",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,22,22,"2024-05-31","23:42:00","2024-06-02","16:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14766708361",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,4,4,"2024-01-26","21:25:00","2024-01-28","10:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14762533061",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,4,4,"2024-01-26","23:42:00","2024-01-28","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15295774761",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,23,23,"2024-06-06","12:25:00","2024-06-07","14:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour enrobés V2 entre 839410 et 839508",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15088752461",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,22,22,"2024-05-31","21:25:00","2024-06-02","15:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15295736661",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,23,23,"2024-06-06","10:45:00","2024-06-07","12:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour enrobés V1 entre 839403 et 839584/5",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14670005261",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,14,38,"2024-04-02","22:15:00","2024-09-20","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aménagement aires de mise en voie / Pose auvents Marnay, Pont sur Seine, Romilly, Barberey  La ZEP 603 est inclue dans le domaine intercepté",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14670147761",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,14,38,"2024-04-02","21:30:00","2024-09-20","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aménagement aires de mise en voie / Pose de auvents Marnay, Pont sur Seine, Romilly, Troyes Barberey  ZEP 606 inclue dans le domaine intercepté",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2024-02-19","22:15:00","2024-11-15","05:09:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2023-12-18","22:15:00","2024-01-12","05:09:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672989861",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,50,46,"2024-08-19","22:15:00","2024-10-18","05:09:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15298773061",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,37,41,"2024-09-13","23:45:00","2024-10-13","16:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15298807361",null,"< >","Grandpuits - Poste 4","Vesoul - Poste C",2024,2024,37,41,"2024-09-13","21:25:00","2024-10-13","15:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14553592661",null,"< >","Graveson-Maillane","Tarascon - Bif Rac Nord",2024,2024,13,13,"2024-03-25","23:15:00","2024-03-29","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"AVI Voie 1+1 Gare,VTE+RFC, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870, équivalent Gén, à prendre avec 4D_AF-TCN_0016 et 4C_AV_082 :  Etendue S9 : V1 Côté TCN, du C304 Km 744,730 au Cv 162 de type Bas Km 741,870  Domaine S9 : ZEP G 705+703+701 Ete",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14551601361",null,"< >","Graveson-Maillane","Tarascon - Voies 6 Ã  10",2024,2024,15,15,"2024-04-08","23:15:00","2024-04-12","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, Tir 714/16 + 752/11 (àprendre avec 4D_AF-TCN_015+4D_TCN-MAS_037)  :  Etendue S9 : V1 du C 304 Km 744,730 (Avignon) à la PATC Km 767+009 (Tarascon) / V2 du C 306  Km 744,730 (Avignon) au C22 Km 766,134 (Tarascon)   Domaine S9 : V1 ZEP L Avi-TCN + Z",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15088121161",null,"< >","Hagondange - Aig ITE","Uckange - Ano Km 181,3",2024,2024,37,40,"2024-09-09","08:30:00","2024-10-04","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 27678, 8h30 jour, V1B+V2B entre Hagondange et Uckange P2. Avec 4D_UCK_039 et 4D_UCK-THL_031.   Report circulations sur V1+V2 entre Hagondange et Thionville.  Rac Mondelange interdit (Thionville, Ebange <-->Rac<-->Conflans interdit).   Accès Ebange via",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14550971561",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,9,9,"2024-03-03","08:00:00","2024-03-03","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 les DI sur voies Bis entre Hagondange et Thionville. Simultanément: 4D_WPY-MMZ_012 + 4D_MMZ-HGD_018 + 4D_HGD2_014 + 4D_HGD-UCK_021 + 4D_UCK_035.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676476761",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,7,35,"2024-02-18","23:55:00","2024-09-01","01:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15126490961",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,9,36,"2024-03-03","23:00:00","2024-09-08","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676460961",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676458561",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676457761",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676456961",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676463561",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,50,50,"2023-12-11","11:30:00","2024-12-13","12:34:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676465961",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,50,50,"2023-12-11","14:20:00","2024-12-13","15:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14131583461",null,"< >","Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2024,2024,10,16,"2024-03-10","23:50:00","2024-04-21","03:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec 4C_THL_100 qui reprend les conséquences circulations.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14550923461",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,9,9,"2024-03-03","08:00:00","2024-03-04","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 sur voies Bis entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_012 + 4D_MMZ-HGD_018 + 4D_HGD2_014 + 4D_HGD-UCK_021 + 4D_UCK_035.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676496461",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,46,46,"2024-11-16","08:00:00","2024-11-17","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 sur les voies rapides entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_001 + 4D_MMZ-HGD_001 + 4D_HGD2_002. Report circulation sur voies BIS entre UCK ou THL et WPY BV. Entrée WPY par voie 1M interdite => report via FO",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676497261",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,46,46,"2024-11-17","08:00:00","2024-11-18","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 les DI sur voies 1+2Bis entre Woippy et Hagondange. Simultanément 4D_WPY-MMZ_004 + 4D_MMZ-HGD_003 + 4D_HGD2_003. Report circulation sur voie 1Bis d'UCK ou THL à WPY AS, report sur voie 2 de WPY BV à UCK ou THL. Départ WPY côté Nord interdit => s",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676498261",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,10,16,"2024-03-10","23:50:00","2024-04-21","03:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec 4C_THL_100 qui reprend les conséquences circulations.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676491461",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                     ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676490361",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV       ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676492261",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                       ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676494661",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,50,50,"2023-12-11","11:28:00","2024-12-13","12:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676493061",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,50,50,"2023-12-11","14:11:00","2024-12-13","15:09:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modifiée suite main courante pour le SA2023",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676493861",null,"< >","Hagondange - Faisceau","Hagondange - ITE Richemont",2024,2024,50,34,"2023-12-11","09:17:00","2024-08-23","10:14:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676460161",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy B)",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676459361",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676461761",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676462561",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676465161",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,50,46,"2023-12-11","13:45:00","2024-11-15","14:49:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676464361",null,"< >","Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2024,2024,50,34,"2023-12-11","09:15:00","2024-08-23","10:11:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462859561",null,"< >","Hagondange - ITE Richemont","Uckange - Ano Km 181,3",2024,2024,13,49,"2024-03-30","04:00:00","2024-12-02","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en service CCR secteur Thionville    Les objets travaux placés sur les WE S13+21+40+48 ne seront pas tous utilisés (WE de secours selon avancement du projet CCR), il est demandé à la DAC de tracer les sillons dans les objets travaux au lot 1 avec la ",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15087968861",null,"< >","Hagondange - ITE Richemont","Uckange - Ano Km 181,3",2024,2024,32,32,"2024-08-11","21:30:00","2024-08-12","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 27678, 8h nuit, V1+V1B+V2B entre Hagondange et Uckange P2. Avec 4D_UCK_038 et 4D_UCK-THL_030.   Trafic Impair Thionville-->Uckange-->Hagondange INTERDIT.   Report circulations paires sur V2. Rac Mondelange interdit (Thionville, Ebange <-->Rac<-->Confl",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687541061",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,50,"2023-12-11","10:56:00","2024-12-13","12:02:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_43 :vibration de -3' pour avoir TER 86985 en SF  le 15/19/17 MC19-0007 pour passage entre 4761 et 86985  MC19-0073 pour calage entre 4761 et 86985 (50minutes)  Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687539261",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,50,"2023-12-11","10:03:00","2024-12-13","10:48:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MC19-0074 calage entre 9708 et 4654 Main courante 2020 Maj-565-871              ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687538461",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,49,"2023-12-11","00:35:00","2024-12-02","03:31:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687540061",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,50,"2023-12-12","00:15:00","2024-12-14","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687537661",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,49,"2023-12-11","01:33:00","2024-12-02","04:43:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687540061",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,50,"2024-12-03","00:15:00","2024-12-07","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687540061",null,"< >","Jonquières - Rac Jonquières","Nîmes - Poste 1",2024,2024,50,50,"2024-04-03","00:15:00","2024-04-27","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14392325361",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,49,49,"2024-12-02","22:00:00","2024-12-08","03:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14392347461",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,49,49,"2024-12-02","23:00:00","2024-12-08","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690608761",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,50,49,"2024-07-08","23:45:00","2024-08-23","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification horaire du 1er train au départ de COE 129600 (04h25)",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690608761",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,50,49,"2024-09-20","23:45:00","2024-12-06","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification horaire du 1er train au départ de COE 129600 (04h25)",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15242625161",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,42,43,"2024-10-18","23:45:00","2024-10-21","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690608761",null,"< >","Juvisy - FSC March Local","Villabé",2024,2024,50,49,"2023-12-11","23:45:00","2024-12-08","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification horaire du 1er train au départ de COE 129600 (04h25)",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15224237461",null,"< >","La Barasse","Aubagne",2024,2024,35,50,"2024-09-01","22:50:00","2024-12-12","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Portiques souples Aubagne, reprise travaux sur SA2024 :   Domaine S9 :  V.D : zep 3617+3619+3621  V.1/VC : zep 3601+3603+3605+3607+3609+3611+3613+3615  MV2/VB : zep 3600+3602+3604+3606+3608+3610+3612+3614  MV3/VA : zep 3616+3618+3620+3622+3624+3626  VE : ",null,null,null,null,"Major","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15446138061",null,"< >","La Barasse","Aubagne",2024,2024,41,41,"2024-10-12","00:01:00","2024-10-12","12:01:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"OCP 12h, sur S41 (sur le même We que le CHA24_0026522 Aqueducs Km 26,242) :  Portiques souples Aubagne, reprise travaux sur SA2024 à l'ombre de l'OCP 28h du CHA24_0026522) :   Domaine S9 :  V.D : zep 3617+3619+3621  V.1/VC : zep 3601+3603+3605+3607+3609+3",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13875665461",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,1,49,"2024-01-02","10:10:00","2024-12-06","12:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"maintenance de jour DV/RV",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703610261",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2024-07-09","00:30:00","2024-08-04","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703612861",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,1,50,"2024-03-04","23:35:00","2024-07-07","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703611061",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2024-07-09","01:05:00","2024-08-04","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703611861",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703612861",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703609461",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","01:05:00","2024-12-14","05:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703608661",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","00:25:00","2024-12-14","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703611061",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","01:05:00","2024-12-14","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703610261",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","00:30:00","2024-12-14","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14351779361",null,"< >","La Barre-Ormesson","La Barre-Ormesson",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-09","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13886964061",null,"< >","La Ciotat","La Seyne-Tamaris-sur-Mer - Aig Km 59,9 PA",2024,2024,50,13,"2023-12-11","22:25:00","2024-03-28","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tranchée Rocheuse du PRo Reynaud, DEF 07h00, de S50 à S13 de 2024 :  Etendue S9 : V1 du C201 SNA Km 39,820 au C73 Km 59,771 LSM et V2 du C 203 Km 39,820 SNA au C 59 Km 59,690  Domaine S9 : ZEP G 41+42 + DFV L SNA-LSM V1/V2  Etendue S11 : V1 Si Sél du Km 4",null,null,null,null,"Major","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13576578461",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:05:00","2024-12-13","11:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en qualité Refonte 2022",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13576579261",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:15:00","2024-12-13","11:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en qualité Refonte 2022",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13576580861",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,49,45,"2023-12-10","22:30:00","2024-11-07","03:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en qualité Refonte 2022",null,null,null,null,"Major","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13576576861",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,49,45,"2023-12-10","23:50:00","2024-11-07","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en qualité Refonte 2022",null,null,null,null,"Major","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14394943861",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,5,8,"2024-02-04","22:25:00","2024-02-22","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"capacités de nuit SIM V1+ V2 entre La Touche et Lusignan  Demande 2022 UTM Partie Ouest IPPC  ",null,null,null,null,"High","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14394548061",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,2,50,"2024-01-08","09:50:00","2024-12-12","14:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"capacités de jour monovoie Voie 1 entre La Touche et Lusignan  Demande 2022 UTM Partie Ouest IPPC",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14394701561",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,9,40,"2024-02-26","10:05:00","2024-10-03","14:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"capacités de jour monovoie Voie 2 entre La Touche et Lusignan  Demande 2022 UTM Partie Ouest IPPC",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14689751061",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,40,42,"2024-10-05","23:00:00","2024-10-19","06:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Nuit de sa/di besoin de maintenance",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15125792461",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,5,8,"2024-02-04","21:40:00","2024-02-22","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"capacités de nuit monovoie V1 ou V2 entre La Touche et Lusignan  Demande 2022 UTM Ouest IPPC  ",null,null,null,null,"High","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13576579261",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,50,50,"2024-03-07","10:15:00","2024-03-13","11:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en qualité Refonte 2022",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13576578461",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,50,50,"2024-03-07","10:05:00","2024-03-13","11:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en qualité Refonte 2022",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15310152661",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,15,24,"2024-04-08","22:20:00","2024-06-13","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"RR + relevage  SIM V1+V2  Zep 8383 V1 et 702 V2 + Sr Mezeau Lusignan V1 + V2",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13886927061",null,"< >","La Touche - Bif La Touche","Rouillé - Bât Voyageurs",2024,2024,14,24,"2024-04-07","22:25:00","2024-06-16","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"RR + relevage  SIM V1+V2  Zep 8383 V1 et 702 V2 + Sr Mezeau Lusignan V1 + V2",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673368261",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-10-22","23:55:00","2024-10-25","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre générique Lagny Meaux ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673369061",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-10-22","23:35:00","2024-10-25","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre fenêtrre generique Lagny Meaux ZEP 1106+1104 Vaires 5VP SEL 24 SSr Pomponne Dampmart V2",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673368261",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-02-26","23:55:00","2024-10-10","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre générique Lagny Meaux ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673369061",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-02-26","23:35:00","2024-10-10","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre fenêtrre generique Lagny Meaux ZEP 1106+1104 Vaires 5VP SEL 24 SSr Pomponne Dampmart V2",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673371061",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,5,27,"2024-01-29","09:30:00","2024-07-02","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1B1 : ZEP 1209 (1103 + 1141 + 1143) LGY (aig. 3915b,3923a)     ",null,null,null,null,"Medium","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673369061",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-05-20","23:35:00","2024-10-20","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre fenêtrre generique Lagny Meaux ZEP 1106+1104 Vaires 5VP SEL 24 SSr Pomponne Dampmart V2",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673368261",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-05-20","23:55:00","2024-10-20","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre générique Lagny Meaux ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673368261",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-03-19","23:55:00","2024-03-22","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre générique Lagny Meaux ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673369061",null,"< >","Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2024,2024,9,43,"2024-03-19","23:35:00","2024-03-22","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre fenêtrre generique Lagny Meaux ZEP 1106+1104 Vaires 5VP SEL 24 SSr Pomponne Dampmart V2",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673370061",null,"< >","Lagny-Thorigny","Esbly",2024,2024,5,5,"2024-01-29","14:00:00","2024-01-29","15:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"3+T3 : ZEP 1205 (1143 + 1145 + 1147) LGY (aig. 3944b)     ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14724329261",null,"< >","Lagny-Thorigny","Esbly",2024,2024,41,41,"2024-10-10","22:35:00","2024-10-11","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15050524861",null,"< >","Lagny-Thorigny","Esbly",2024,2024,43,43,"2024-10-25","23:30:00","2024-10-27","18:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"WE de Maintenance type CASTOR  Aligné sur CHA19_0026052 RAV Meaux    ",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673371861",null,"< >","Lagny-Thorigny","Esbly",2024,2024,48,48,"2024-11-25","23:30:00","2024-11-29","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre Mega ZEP ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1 ZEP 1106+1104 Vaires 5VP SEL 24 SSr Pomponne Dampmart V2     ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14610328761",null,"< >","Lagny-Thorigny","Esbly",2024,2024,16,16,"2024-04-19","23:30:00","2024-04-21","16:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TOUT VAIRES P5  Restitution 16h40 pour TER 839165 acté en Conciliation N°3 Désaccords RP0 2024",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15202283661",null,"< >","Laroche-Migennes - BÃ¢t Voyageurs","Laroche-Migennes - Poste 4",2024,2024,37,42,"2024-09-09","10:00:00","2024-10-18","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689848861",null,"< >","Laroche-Migennes - CarrÃ© Violet 12","Laroche-Migennes - Poste 4",2024,2024,17,17,"2024-04-22","09:30:00","2024-04-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Besoins Caténaires : - Secteur Laroche Voie de service Pair - Secteur Laroche Cezy voie 2bis - Sel 2320 bis du Secteur Laroche St Florentin Voie 2bis (Voie 2 Racco) - Sel 2321bis +131 du Secteur  Laroche St Florentin Voie 1bis (Voie 1 Racco + Voie A Racco",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689922261",null,"< >","Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,1,30,"2024-03-25","08:51:00","2024-03-26","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens Prise de voie V2                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689933061",null,"< >","Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,50,48,"2023-12-11","00:19:00","2024-12-01","03:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 => 1 voie dans chaque sens               ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689922261",null,"< >","Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,1,30,"2024-01-02","08:51:00","2024-07-28","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens Prise de voie V2                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689924661",null,"< >","Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,1,7,"2024-01-02","09:53:00","2024-02-18","13:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"V2 + V2BIS dans l'ombre de la fenêtre générique St Florenton tonnerre => Décision N2 du 02/10/2015 TO 891352 / TF 891354 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14552276461",null,"< >","Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,34,34,"2024-08-19","08:15:00","2024-08-23","16:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15652718461",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-16","10:00:00","2024-11-08","18:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15652473261",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,37,42,"2024-09-09","08:45:00","2024-10-18","14:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15202029761",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-21","07:00:00","2024-11-04","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15201913561",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-16","10:00:00","2024-11-08","18:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15201830661",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,37,42,"2024-09-09","09:45:00","2024-10-18","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15654108661",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,34,50,"2024-08-19","00:50:00","2024-12-09","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15202297561",null,"< >","Laroche-Migennes - FSC Bercy","Laroche-Migennes - Poste 4",2024,2024,33,46,"2024-08-12","00:50:00","2024-11-11","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15652558361",null,"< >","Laroche-Migennes - Poste 1","Laroche-Migennes - Poste 2",2024,2024,40,42,"2024-10-03","10:00:00","2024-10-14","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,4,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15645809461",null,"< >","Laroche-Migennes - Poste 1","Laroche-Migennes - Poste 4",2024,2024,37,42,"2024-09-09","08:45:00","2024-10-18","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689931461",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 165,9",2024,2024,50,32,"2024-03-27","08:51:00","2024-04-19","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens Prise de voie V1bis       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689925661",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 165,9",2024,2024,51,49,"2023-12-18","02:47:00","2024-12-02","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 => 1 voie dans chaque sens               ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689931461",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 165,9",2024,2024,50,32,"2023-12-11","08:51:00","2024-08-11","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens Prise de voie V1bis       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689923061",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 165,9",2024,2024,46,46,"2024-11-14","12:55:00","2024-11-15","14:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401052 Incompatible avec Fenêtre générique V1 pour eviter la sim de 1h                             ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689935461",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 165,9",2024,2024,20,43,"2024-05-19","23:00:00","2024-10-26","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689928061",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,50,32,"2024-03-27","08:51:00","2024-04-19","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens Prise de voie V2bis                                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14552356561",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,35,35,"2024-08-26","08:15:00","2024-08-30","16:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689926461",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,51,49,"2023-12-18","00:19:00","2024-12-02","03:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 => 1 voie dans chaque sens             ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689928061",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,50,32,"2023-12-11","08:51:00","2024-08-11","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens Prise de voie V2bis                                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689936261",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,20,43,"2024-05-19","22:00:00","2024-10-26","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689934661",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,19,41,"2024-05-12","22:00:00","2024-10-10","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689927261",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,46,46,"2024-11-14","12:20:00","2024-11-17","13:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401082  Incompatible avec Fenêtre générique V2 pour eviter la sim de 1h                           ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689928861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bât Voyageurs",2024,2024,46,46,"2024-11-12","12:55:00","2024-11-13","14:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401026 Incompatible avec Fenêtre générique V1BIS pour eviter la sim de 1h                                     ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195439161",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,19,45,"2024-09-30","10:00:00","2024-10-31","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195341161",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,17,50,"2024-04-22","10:00:00","2024-12-06","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689923861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,1,30,"2024-03-25","08:51:00","2024-03-26","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens Prise de voie V1   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689923861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,1,30,"2024-03-11","08:51:00","2024-03-18","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens Prise de voie V1   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15202374061",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,39,39,"2024-09-28","08:00:00","2024-09-29","18:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689932261",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,50,48,"2023-12-11","02:47:00","2024-12-01","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 => 1 voie dans chaque sens             ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689923861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,1,30,"2024-01-02","08:51:00","2024-07-28","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens Prise de voie V1   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689930461",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,1,7,"2024-01-02","09:16:00","2024-02-18","13:26:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"V1 + V1BIS  dans l'ombre de la fenêtre générique St Florenton tonnerre => Décision N2 du 02/10/2015 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195341161",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,17,50,"2024-04-22","10:00:00","2024-12-13","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195439161",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,19,45,"2024-05-06","10:00:00","2024-11-07","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689941861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,18,37,"2024-05-05","23:05:00","2024-09-15","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Entre 5789 et 5790 ",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689933861",null,"< >","Laroche-Migennes - Poste 4","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,19,41,"2024-05-12","23:00:00","2024-10-10","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Accord derrière 5789",null,null,null,null,"High","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689805061",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 1",2024,2024,12,42,"2024-09-09","10:00:00","2024-10-18","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689805061",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 1",2024,2024,12,42,"2024-03-18","10:00:00","2024-03-22","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689851461",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 2",2024,2024,5,42,"2024-03-18","10:00:00","2024-03-22","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689851461",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 2",2024,2024,5,42,"2024-01-29","10:00:00","2024-03-31","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689851461",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 2",2024,2024,5,42,"2024-09-09","10:00:00","2024-10-18","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689849661",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,16,16,"2024-04-15","09:30:00","2024-04-21","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Besoins Caténaires : - Secteur Laroche Voie de service Impair - Secteur Cezy Laroche voie 1bis Besoins ZEP : - Toutes les ZEP du faisceau Bourgogne Impair et Accès  - Toutes les ZEP du faisceau de Préblin + ZEP 481 et Accès par bourgogne faisceau impair  ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15202016261",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-21","07:00:00","2024-11-04","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15201727861",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,33,49,"2024-08-12","10:00:00","2024-12-08","16:31:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15652676761",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-16","10:00:00","2024-11-08","16:31:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15654038861",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,34,50,"2024-08-19","00:50:00","2024-12-09","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15201987861",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,38,45,"2024-09-21","01:00:00","2024-11-04","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15201892561",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,33,49,"2024-08-12","10:00:00","2024-12-08","11:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15652892461",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,33,49,"2024-08-18","22:00:00","2024-12-08","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15652809261",null,"< >","Laroche-Migennes - Voie 10 Tiroir","Laroche-Migennes - Poste 4",2024,2024,46,46,"2024-11-11","00:50:00","2024-11-11","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689929661",null,"< >","Laroche-Migennes - Voies 4 Ã  10","St-Florentin-Vergigny - Aig Km 168,3",2024,2024,46,46,"2024-11-12","12:20:00","2024-11-13","13:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401054 Incompatible avec Fenêtre générique V2BIS pour eviter la sim de 1h                               ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15358183661",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Aig V2Bis/V2Ter",2024,2024,40,40,"2024-10-03","22:30:00","2024-10-03","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h                       ",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673398061",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Aig V2Bis/V2Ter",2024,2024,8,8,"2024-02-19","13:40:00","2024-02-19","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2TER : ZEP 1732,1736 GN (aig. 2905b,2913a)           ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15358105961",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2024,2024,40,40,"2024-10-01","22:35:00","2024-10-01","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14119814861",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2024,2024,15,16,"2024-04-08","08:00:00","2024-04-21","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673398861",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2024,2024,11,40,"2024-03-11","22:55:00","2024-05-03","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673398861",null,"< >","Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2024,2024,11,40,"2024-04-22","22:55:00","2024-10-06","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13836835461",null,"< >","Le Thor","L'Isle-Fontaine-de-Vaucluse",2024,2024,48,50,"2024-11-25","08:25:00","2024-12-13","16:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx PPx V1+V2 (de S48 à S50 du SA2024 et S51 2024 sur SA2025) - VA L'Isle-Fontaine - (de Avignon Fontcouverte inclus à Miramas exclu), à prendre avec  :    Etendue S9 : V1 du Km 0+730 (Cv105 d'AFT) au Km 66+880 (C507 de Mas) et V2 au Km 65+976 (PATC de Ma",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13809744261",null,"< >","Le Thor","L'Isle-Fontaine-de-Vaucluse",2024,2024,26,37,"2024-06-24","08:35:00","2024-09-15","16:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SR Voie AMS, de S26 à S36,Tvx connexes et hors suite et S37 Tvx Préparatoires - VA L'Isle-Fontaine - Avignon  Fontcouverte exclu à Cavaillon exclu - DEF de 08h00 :  Etendue S9 : V1 de la PATC Km 4,283 (AFT) au C1 Km 32,188 / V2 de la PATC km 32,167 (CAV) ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690515961",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - Panneau 19",2024,2024,1,49,"2024-01-02","10:35:00","2024-12-04","11:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Gpt: 9928 ",null,null,null,null,"High","2,3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15231590661",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - Bif Km 8,9/9,1",2024,2024,12,12,"2024-03-18","21:55:00","2024-03-18","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690517761",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - Carré 55",2024,2024,5,45,"2024-02-01","10:35:00","2024-11-07","11:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Gpt: 9933   ",null,null,null,null,"Medium","2,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690513361",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - FSC Départ Nord",2024,2024,52,36,"2024-07-08","23:30:00","2024-09-06","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"s30:ve26/sa27 juillet + s31: lu29/ma30 à ve02/sa03 août + s32: lu05/ma06 à ve09/sa10 août + s35:lu26/ma27 à ve30/sa31 août + s36: lu02/ma03 à ve06/sa07 septembre  En cas de nécessité pour TN ou impératif pour assurer la sécurité technique des installation",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690513361",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - FSC Départ Nord",2024,2024,52,36,"2023-12-26","23:30:00","2024-01-05","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"s30:ve26/sa27 juillet + s31: lu29/ma30 à ve02/sa03 août + s32: lu05/ma06 à ve09/sa10 août + s35:lu26/ma27 à ve30/sa31 août + s36: lu02/ma03 à ve06/sa07 septembre  En cas de nécessité pour TN ou impératif pour assurer la sécurité technique des installation",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14861863261",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,3,46,"2024-01-20","23:20:00","2024-11-16","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14862348261",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,11,16,"2024-03-15","23:15:00","2024-04-21","13:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14862449961",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,21,24,"2024-05-25","23:20:00","2024-06-15","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15237953161",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Toucy-Ville - Bât Voyageurs",2024,2024,19,19,"2024-05-06","23:20:00","2024-05-10","05:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15231606061",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Toucy-Ville - Bât Voyageurs",2024,2024,12,12,"2024-03-19","23:20:00","2024-03-21","05:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690516761",null,"< >","Le Vert-de-Maisons - Aiguille 8 Rebt","Villeneuve-St-Georges-Triage - Remisage Nord",2024,2024,1,49,"2024-01-02","13:50:00","2024-12-04","15:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Gpt: 9933 891022 & 151954 circulent 2/2bis à LIU  ",null,null,null,null,"High","2,3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689487961",null,"< >","Les Arcs-Draguignan","Boulouris-sur-Mer",2024,2024,50,50,"2023-12-11","10:02:00","2024-12-13","11:16:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"decalage MC18-0284 pour Thello 145 2021_SE_90 : décalage pour avoir 881267 en SF",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13908516961",null,"< >","Les Arcs-Draguignan - V 3 de Garage","St-Raphaël-Valescure - Bât Voyageurs",2024,2024,45,50,"2024-11-10","22:44:00","2024-12-12","05:12:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"HS Fréjus-Nice - zone Fréjus- :  Etendue S9 : V1 du C30 Km 136,335 au C17 Km 160,238 et V2 du C22 Km 136,335 au C14 Km 160,694  Domaine S9 : V1 Groupement de ZEP type L Les Arcs Saint Raphaël V1 et ZEP 101+103+105+107+109 de SRV et V2 ZEP de SRV ZEP 118+1",null,null,null,null,"High","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13910981761",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,47,48,"2024-11-24","21:35:00","2024-11-28","05:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"HS Fréjus-Nice - zone Fréjus +TTes Zones- :  ",null,null,null,null,"Medium","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689488761",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,50,50,"2024-10-05","00:03:00","2024-11-16","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"31/07/2019:décalage de la fenêtre pour avoir le TGV 6187 sillon ouvrant le soir positionnement horaire pour ne pas créer d'autres trains dans l'espace libéré, cet espace est prévu pour le décalage du 6187 impacté par des LTV",null,null,null,null,"Major","3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689486961",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,50,50,"2024-09-30","22:44:00","2024-11-14","05:12:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"modif 2020: Maj-461-690              ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689486161",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,50,50,"2023-12-11","13:33:00","2024-12-13","14:16:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modif horaire via MC 429 MC19-0068 calage pour 17478 2021_SE_76 + 2021_SE_77 + 2021_SE_78 : décalage de quelques minutes pour avoir 17484 en SF (ISO 2020) ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689488761",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,50,50,"2023-12-16","00:03:00","2024-12-14","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"31/07/2019:décalage de la fenêtre pour avoir le TGV 6187 sillon ouvrant le soir positionnement horaire pour ne pas créer d'autres trains dans l'espace libéré, cet espace est prévu pour le décalage du 6187 impacté par des LTV",null,null,null,null,"Major","3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689486961",null,"< >","Les Arcs-Draguignan - V 3 de Garage","Boulouris-sur-Mer",2024,2024,50,50,"2023-12-11","22:44:00","2024-12-12","05:12:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"modif 2020: Maj-461-690              ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13854283861",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,43,43,"2024-10-21","10:00:00","2024-10-22","12:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En Simultanée avec la 4F_LLA-BSB_001  TO: 17753   TF: 6705",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689818461",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-03-04","09:00:00","2024-04-05","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689818461",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-01-22","09:00:00","2024-02-02","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689818461",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-04-04","09:00:00","2024-04-26","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689819261",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,2,34,"2024-01-08","12:32:00","2024-08-23","13:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401061 Incompatible avec les Fenêtre générique et surveillance V2, pour eviter la sim de 1h                                             ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689818461",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-01-22","09:00:00","2024-12-06","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689824861",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,2,34,"2024-01-08","00:20:00","2024-08-19","03:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401123",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689818461",null,"< >","Les Laumes-Alésia - Bif Km 258,7","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-09-02","09:00:00","2024-10-04","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689820861",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,50,50,"2024-03-25","09:10:00","2024-03-29","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689831461",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,8,14,"2024-02-19","09:10:00","2024-04-05","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1 OU 1 Bis  La voie sera déterminée par le plateau commun lors des \"\"réunions des Pas\"\"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689830061",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,11,11,"2024-03-16","11:45:00","2024-03-16","11:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689820861",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,50,50,"2024-01-15","09:10:00","2024-01-19","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689820861",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,50,50,"2024-03-27","09:10:00","2024-03-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689820861",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,50,50,"2023-12-11","09:10:00","2024-12-13","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689823261",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,51,31,"2023-12-18","10:27:00","2024-08-02","11:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401032  Incompatible avec les Fenêtre générique et surveillance V1BIS, pour eviter la sim de 1h                                                     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689824061",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,51,31,"2023-12-18","01:51:00","2024-07-29","05:07:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401118",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14615040761",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,35,39,"2024-08-26","10:15:00","2024-09-27","16:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4D_AIY-LLA_020 et de la 4C_LLA_004",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689820861",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,50,50,"2024-10-07","09:10:00","2024-10-22","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14366467161",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641237561",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689828061",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance IHM ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641889261",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13793938961",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage modifiée le 01/12/2022 suite report de la MES",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15169803561",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,48,48,"2024-11-25","10:25:00","2024-11-29","16:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15138662161",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,15,16,"2024-04-13","00:25:00","2024-04-20","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15138700361",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,15,16,"2024-04-13","23:30:00","2024-04-21","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15110090561",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,9,17,"2024-02-26","10:50:00","2024-04-25","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 6703   TF 891907",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15110333561",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,40,41,"2024-09-30","10:00:00","2024-10-11","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689829061",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,9,9,"2024-02-26","13:10:00","2024-02-29","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 891904   TF: 9268",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689830061",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,11,11,"2024-03-16","11:45:00","2024-03-16","11:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15169834761",null,"< >","Les Laumes-Alésia - Côté NO","Mâlain - Bât Voyageurs",2024,2024,44,44,"2024-11-02","20:10:00","2024-11-02","12:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14334121761",null,"< >","Les Laumes-Alésia - Côté NO","Les Laumes-Alésia - Bif Km 259",2024,2024,15,15,"2024-04-10","09:00:00","2024-04-11","13:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Entrée et Sortie coté Pair du Fx Escale est Impossible",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689832461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,10,11,"2024-03-04","10:55:00","2024-03-14","14:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 6703   TF: 891377",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14466406361",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,12,13,"2024-03-18","09:25:00","2024-03-28","12:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261     TF:6705",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14466406361",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,12,13,"2024-03-25","09:25:00","2024-03-28","12:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261     TF:6705",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689826461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-01-22","09:10:00","2024-02-02","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 10 semaines suite à revue de cloture d'ordonnancement PCAST                                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689826461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-04-02","09:10:00","2024-04-26","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 10 semaines suite à revue de cloture d'ordonnancement PCAST                                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689826461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-01-22","09:10:00","2024-12-06","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 10 semaines suite à revue de cloture d'ordonnancement PCAST                                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689821661",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,2,34,"2024-01-08","13:29:00","2024-08-23","14:42:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Incompatible avec les Fenêtre générique et surveillance V1, pour eviter la sim de 1h                                                                   ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689827261",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,2,34,"2024-01-08","01:51:00","2024-08-19","05:07:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401119",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689826461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,4,49,"2024-09-02","09:10:00","2024-10-04","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 10 semaines suite à revue de cloture d'ordonnancement PCAST                                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15109773161",null,"< >","Les Laumes-Alésia - Faisceau Escale","Mâlain - Bât Voyageurs",2024,2024,13,13,"2024-03-25","10:35:00","2024-03-28","12:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9206  TF: 9210",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689820061",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,50,50,"2024-02-19","09:00:00","2024-04-03","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens.                                                                                   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689820061",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,50,50,"2024-01-15","09:00:00","2024-01-19","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens.                                                                                   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689820061",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,50,50,"2024-03-29","09:00:00","2024-04-03","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens.                                                                                   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689820061",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,50,50,"2023-12-11","09:00:00","2024-12-13","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens.                                                                                   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689825661",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,51,31,"2023-12-18","00:20:00","2024-07-29","03:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401122",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689822461",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,51,31,"2023-12-18","11:23:00","2024-08-02","12:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401061 Incompatible avec les Fenêtre générique et surveillance V2BIS, pour eviter la sim de 1h                               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689820061",null,"< >","Les Laumes-Alésia - Faisceau Escale","Blaisy-Bas",2024,2024,50,50,"2024-10-23","09:00:00","2024-11-08","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens.                                                                                   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13686989661",null,"< >","L'Estaque - BÃ¢t Voyageurs","Marseille-Maritime-Arenc - Bif Rac Canet",2024,2024,17,24,"2024-04-22","21:20:00","2024-06-14","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Le Canet - Fermeture du chantier puis cession de terrain à partir de S17 jusqu´à S24, DEF 07h35 - (Rac Canet et Rac Arenc reliant de part et d'autre le chantier du Canet avec neutralisation aiguilles 313ac/314bd sur Bif Rac. Arenc et VA Circulation P1 Are",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14340433861",null,"< >","L'Estaque - Bif Mourepiane","L'Estaque - Bif Mourepiane",2024,2024,45,45,"2024-11-10","22:35:00","2024-11-10","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0026458, OCP 7h00, 1 nuit du Di/Lu 10-11/11/24 (de 22h35 à 05h35), mise en service \"\"LGV +\"\" sur l'interface de la zone télécommandée de l'IHM1 de Mistral P1 de Marseille)  Conditions de réalisation : toute la zone d'action du poste de l'IHM1 de Mar",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14340932761",null,"< >","L'Estaque - Bif Mourepiane","L'Estaque - Bif Mourepiane",2024,2024,3,37,"2024-01-20","23:59:00","2024-09-14","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA20_0018098 \"\"Augmentation débit LGV\"\" : OCP 4h41,  1 nuit du Sa/Di de S3 (20-21/01/24) + 1 nuit du Sa/Di de S25 ( 22-23/06/24 de 23h59 à 04h40 opérations sur l´IHM1 Mistral au P1 de Marseille) et 1 nuit du Sa/Di de S37 pour essai complet de montée en c",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15445947261",null,"< >","L'Estaque - Point Km","Marseille-Maritime-Arenc - Bif Rac Canet",2024,2024,20,21,"2024-05-18","19:00:00","2024-05-20","07:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Fermeture du Canet -Fermeture du chantier, cession du terrain- , OCP 36h  => We S20/21, du Sa 18/05 à 19h00 au Lu 20/05 à 07h00 : remplacement des ADV 203aV et 205aV par de la voie courante, dépose de l´ADV 203b et remplacement de la TJD 313ac/314bd par B",null,null,null,null,"Medium","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13686977861",null,"< >","L'Estaque - Point Km","Marseille-Maritime-Arenc - Bif Rac Canet",2024,2024,41,50,"2024-10-07","21:20:00","2024-12-13","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Raccordement Mourepiane, pose de la nouvelle Com Tg 0.085 (Voie et caténaire) et modification platelage PN2 :  Etendue S9 MM1 / MM2 : MM1 du C944 à revers Km 853,154 au C946 à revers Km 854,559 / MM2 du C201 à revers Km 856,051 au C942 km 853,154  Domaine",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13686979861",null,"< >","L'Estaque - Point Km","Marseille-Maritime-Arenc - Bif Rac Canet",2024,2024,41,50,"2024-10-07","21:20:00","2024-12-13","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Raccordement Mourepiane, Entrées/ Sorties de trains travaux vers le S9A3 => depuis MM1 vers le tunnel de Soulat (via Aig 947 neut.D) :  1 Nuit de 7h30 sur MM1 LU/MA et puis une sur VE/SA toutes les semaines de octobre (S41) à déc. 2024 (S49).  Etendue S9 ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13851215761",null,"< >","Lézinnes","Aisy - Bât Voyageurs",2024,2024,8,47,"2024-02-19","09:30:00","2024-11-22","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie A de Pacy ET Voie 4 Garage  de NUR  En SIM avec la 4D_TNE-AIY_014  ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13835715861",null,"< >","Lézinnes","Aisy - Bât Voyageurs",2024,2024,17,44,"2024-04-22","09:00:00","2024-10-31","16:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Correspond aux voies 1Bis + 4G + A de Nuits sous Ravières et Voie A de Pacy  Pour TTX caténaire.",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689910061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,17,44,"2024-10-21","09:45:00","2024-10-25","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13850875061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,3,47,"2024-01-16","09:45:00","2024-01-16","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Il s'agit des pas 2 + 3 + 4 Voie 1 OU voie 2  - Passage possible en bana du 207 au 241  - Croisement possible en gare de NUR (Voie 1Bis ou Voie A) .",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13850875061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,3,47,"2024-03-25","09:45:00","2024-03-29","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Il s'agit des pas 2 + 3 + 4 Voie 1 OU voie 2  - Passage possible en bana du 207 au 241  - Croisement possible en gare de NUR (Voie 1Bis ou Voie A) .",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689910061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,17,44,"2024-04-22","09:45:00","2024-10-31","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13850875061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,3,47,"2024-02-19","09:45:00","2024-11-22","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Il s'agit des pas 2 + 3 + 4 Voie 1 OU voie 2  - Passage possible en bana du 207 au 241  - Croisement possible en gare de NUR (Voie 1Bis ou Voie A) .",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13971950761",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,33,41,"2024-08-12","09:25:00","2024-10-11","16:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 891352   TF: 891379",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14768769161",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,19,27,"2024-05-06","09:50:00","2024-07-05","16:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 17753   TF: Sans",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14768769161",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,19,27,"2024-06-03","09:50:00","2024-06-28","16:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 17753   TF: Sans",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13971950761",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,33,41,"2024-09-30","09:25:00","2024-10-11","16:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 891352   TF: 891379",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13850875061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,3,47,"2024-01-15","09:45:00","2024-04-26","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Il s'agit des pas 2 + 3 + 4 Voie 1 OU voie 2  - Passage possible en bana du 207 au 241  - Croisement possible en gare de NUR (Voie 1Bis ou Voie A) .",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689910061",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,17,44,"2024-04-29","09:45:00","2024-05-03","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14768769161",null,"< >","Lézinnes","Aisy - Rac LGV",2024,2024,19,27,"2024-05-06","09:50:00","2024-07-05","16:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 17753   TF: Sans",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15108831461",null,"< >","LEZINNES POINT DE CHANGEMENT DE VOIE","Aisy - Rac LGV",2024,2024,16,48,"2024-04-15","10:40:00","2024-11-29","13:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1 + 2",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15169707761",null,"< >","LEZINNES POINT DE CHANGEMENT DE VOIE","Aisy - Rac LGV",2024,2024,44,44,"2024-11-02","20:40:00","2024-11-02","12:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1 + 2",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690650761",null,"< >","Lieusaint-Moissy - ITE EPAMS","Melun - Poste 1",2024,2024,14,49,"2024-05-06","23:35:00","2024-05-10","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13836777961",null,"< >","L'Isle-Fontaine-de-Vaucluse","Orgon",2024,2024,44,47,"2024-10-28","08:25:00","2024-11-22","16:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx PPx V1+V2 (de S44 à S47), -Avignon Fontcouverte exclu à Miramas exclu- et à prendre avec 4D_AFT-CVN_028  :  Etendue S9 : V1 de la PATC Km 4,283 au C507 au Km 66,880 de Mas / V2 De la PATC Km 65,976 au C88 Km 3,645   Domaine S9 : DFV L CAV-MAS V1/ V2+ ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13836727061",null,"< >","L'Isle-Fontaine-de-Vaucluse","Orgon",2024,2024,48,50,"2024-11-25","08:25:00","2024-12-13","16:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx PPx V1+V2 (de S48+49+50 SA2024 et 51 de 2024 sur SA2025) -Avignon Fontcouverte inclus à Miramas exclu-, à prendre avec 4C_AV_068 +4C_AFT-CVN_002+4D_AFT-CVN_029+4D_CVN-MAS_014 :    Etendue S9 : V1 du Km 0+730 (Cv105 d'AFT) au Km 66+880 (C507 de Mas) et",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14628965661",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,3,5,"2024-01-20","00:15:00","2024-02-03","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage créée pour le CHA20_0018098, essai de poste à poste avec l'infrapôle Rhodanien  Toute la zone du poste 44 est concernée  Plage sans impact pour les circulations.",null,null,null,null,"Medium","5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14418916661",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-09-02","22:45:00","2024-10-21","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand lu/ma et jours en lu/ma  (en raison du 6131 circulant dans sa variante du lundi) Pour le CHA24_0026280 Cas V2 sim lu/ma lorsque DEF24_MXO-GNA_006 est prise sur V1 Cas V1 sim lu/ma lorsque DEF24_MXO-GNA_007 est prise sur V2  Pour l",null,null,null,null,"Major","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14419102261",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-09-03","22:35:00","2024-10-24","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand ma/me à me/je:  Pour le CHA24_0026280 Cas V2 sim ma/me à me/je lorsque DEF24_MXO-GNA_006 est prise sur V1 Cas V1 sim ma/me à me/je lorsque DEF24_MXO-GNA_007 est prise sur V2  Pour le CHA24_0026378 Cas V2 sim ma/me à me/je lorsque ",null,null,null,null,"Major","2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14975846361",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,36,43,"2024-09-02","21:20:00","2024-10-24","06:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_MXO-GNA_008 lu/ma ou DEF24_MXO-GNA_009 du ma/me à je/ve  sur V2  V1 derrière 6225 jusqu'au 999603 + 25 minutes Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571 + 745 + 4771 + 747",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14418774961",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-09-02","21:05:00","2024-10-24","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V2 en grand lu/ma à je/ve, la prise de cette DEF rend applicable DEF24_MXO-GNA_008 lu/ma ou DEF24_MXO-GNA_009 ma/me à je/ve sur V1 V2 derrière 6260 jusqu'au 999600 + 10 Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 + ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14418916661",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-01-08","22:45:00","2024-06-24","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand lu/ma et jours en lu/ma  (en raison du 6131 circulant dans sa variante du lundi) Pour le CHA24_0026280 Cas V2 sim lu/ma lorsque DEF24_MXO-GNA_006 est prise sur V1 Cas V1 sim lu/ma lorsque DEF24_MXO-GNA_007 est prise sur V2  Pour l",null,null,null,null,"Major","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14419143661",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,26,"2024-01-12","21:50:00","2024-06-28","06:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_MXO-GNA_012 le ve/sa sur V2  V1 derrière 6129 et 6953  jusqu'au 999603 + 25 minutes  Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571 + 745 + 4771 + 747  Consignation C: Sr Grena",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14419182161",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,26,"2024-01-12","22:05:00","2024-06-28","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V2 en grand rend applicable DEF24_MXO-GNA_012 le ve/sa sur V1 V2 derrière 6206 jusqu'au 999600 + 10  Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 + 4472 + 4474 + 843   Consignation C: Sr Grenay DV2 + SEL 1002 Sr Cham",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14419210161",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,26,"2024-01-12","23:50:00","2024-06-28","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand le ve/sa  Cas V2 sim ve/sa lorsque DEF24_MXO-GNA_010 est prise sur V1 Cas V1 sim ve/sa lorsque DEF24_MXO-GNA_011 est prise sur V2   Derrière 6137  jusqu'au 999603 + 25 minutes ou 999600 + 10   Zeps V1:  743 + 4471 + 4473 + 4475 + ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14419334061",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,14,21,"2024-04-01","22:45:00","2024-05-20","06:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V1 en grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05 rend applicable en sim DEF24_MXO-GNA_015  sur V2  V1 derrière 6131  jusqu'au 999603 + 25 minutes  Zeps V1 : 743 + 4471 + 4473 ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14419483361",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,14,21,"2024-04-01","23:50:00","2024-05-20","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05 Cas V2 sim ve/sa lorsque DEF24_MXO-GNA_013 est prise sur V1 Cas V1 sim ve/sa lorsque DEF24_MXO-GNA_014 est prise sur V2   Derrière 6137  jusqu'",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14413142561",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,26,"2024-01-08","20:55:00","2024-06-27","06:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_MXO-GNA_008 lu/ma ou DEF24_MXO-GNA_009 du ma/me à je/ve  sur V2  V1 derrière 6225 moins 25 minutes jusqu'au 999603 + 25 minutes Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571 +",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14419414161",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,14,21,"2024-04-01","22:50:00","2024-05-20","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V2 en grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05, rend applicable DEF24_MXO-GNA_015 sur V1 V2 derrière 6186 jusqu'au 999600 + 10 Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 457",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14418774961",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-01-08","21:05:00","2024-06-27","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V2 en grand lu/ma à je/ve, la prise de cette DEF rend applicable DEF24_MXO-GNA_008 lu/ma ou DEF24_MXO-GNA_009 ma/me à je/ve sur V1 V2 derrière 6260 jusqu'au 999600 + 10 Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 + ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14419102261",null,"< >","Lyon-St-Exupéry-TGV","Grenay-PRG - Rep4431-Pk419,4",2024,2024,2,43,"2024-01-09","22:35:00","2024-06-27","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand ma/me à me/je:  Pour le CHA24_0026280 Cas V2 sim ma/me à me/je lorsque DEF24_MXO-GNA_006 est prise sur V1 Cas V1 sim ma/me à me/je lorsque DEF24_MXO-GNA_007 est prise sur V2  Pour le CHA24_0026378 Cas V2 sim ma/me à me/je lorsque ",null,null,null,null,"Major","2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14643893861",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Culoz - Bif de Genève",2024,2024,33,50,"2024-08-18","22:20:00","2024-12-12","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Interception Gare de Culoz:  Voie CG+ VU(raccordement)  Domaine S9 :  Zep 432 (V CG)  Zep 436(VRacco)     ",null,null,null,null,"Major","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14926727161",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Vions-Chanaz",2024,2024,16,16,"2024-04-16","22:20:00","2024-04-18","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Interception Gare de Culoz: BML Appareil  Voies 1M et 2M et Racco  Domaine S9:(CCTT)   ZEP 436+437+438+439+440  ",null,null,null,null,"Medium","2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688229461",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Montanay-Bif",2024,2024,50,50,"2023-12-11","12:21:00","2024-12-13","13:11:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10700733",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688230261",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Montanay-Bif",2024,2024,50,50,"2023-12-11","14:33:00","2024-12-13","15:44:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10700732 2021_SE_106 + 2021_SE_107 + 2021_SE_108 + 2021_SE_109 + 2021_SE_110 + 2021_SE_111 : décalage de quelques minutes pour avoir 6615 en SO et 6617 en SF",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688228661",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,50,50,"2023-12-11","22:50:00","2024-12-12","05:28:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"derrière le 6672 le VE/SA",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688233661",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,52,46,"2023-12-25","23:25:00","2024-11-11","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022 ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688231861",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,50,50,"2023-12-11","23:05:00","2024-12-12","05:28:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"derrière 9847 SA2018 => SF  ME 9/05 + ME 31/10       ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14886193561",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00           ",null,null,null,null,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688228661",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,50,50,"2023-12-15","22:50:00","2024-12-13","05:28:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"derrière le 6672 le VE/SA",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688231061",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,50,50,"2023-12-15","23:35:00","2024-12-13","05:42:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Derrière le 6635 SA2018 => + ME 9/05 + ME 31/10",null,null,null,null,"Major","3,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688237261",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,49,49,"2023-12-10","23:45:00","2024-12-08","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable di/lu train ouvrant 6635, train fermant 999614     ",null,null,null,null,"Major","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14995596061",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,6,25,"2024-02-09","23:55:00","2024-06-21","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage pour le CHA20-0018098, essais avec l'infrapôle Rhodanien  Toutes les ZEP des postes 27 et 40  TO 6635, TF 999614            ",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688236261",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Miribel-LGV",2024,2024,50,49,"2023-12-16","23:30:00","2024-12-07","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable sa/di train ouvrant 9847 , train fermant 999614     ",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688288661",null,"< >","Mâcon-Loché-TGV - Rac Nord Mâcon","Poste 27 Cesseins",2024,2024,2,2,"2024-01-08","23:40:00","2024-01-09","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais limitrophes avec infrapôle Alpes la Semaine2, nuit du lu/ma à ma/me avec plage 4C_RPV_004   ZEP 257, 250, 260 et 261 du Poste 25 (MLH) en protection du rac de Pont de Veyle, TO 6635 TF 999614",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13794550361",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure de 06h00 IHM1 pendant la Mise En Service",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14382966161",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,33,50,"2024-08-13","08:00:00","2024-12-13","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14389425161",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,35,49,"2024-08-26","08:00:00","2024-12-06","18:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689873861",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenace IHM 04h00   ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14642192761",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14366977261",null,"< >","Mâlain - Bât Voyageurs","Dijon-Ville - Aiguilles Nord",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MES LGV+",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14437994361",null,"< >","Marquixanes","St-Antoine (M) Poste 1",2024,2024,38,50,"2024-09-22","23:20:00","2024-12-12","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Confortement mur +OT des Cuettes :   Etendue S9 : V1 du C104 (Cassis) Km 26,744 au C201(SNA) Km 39,820 / V2 du C102 Km 26,787 au C203 (SNA) Km 39,820  Domaine S9 : ZEP 31 / ZEP 32  Etendue S11 : V1 du Km 28,849 au Km 40,110 /V2 du Km au Km 40,110  Domaine",null,null,null,null,"Major","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14340744061",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,3,37,"2024-01-20","23:59:00","2024-09-14","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA20_0018098 \"\"Augmentation débit LGV\"\" : OCP 4h41,  1 nuit du Sa/Di de S3 (20-21/01/24) + 1 nuit du Sa/Di de S25 ( 22-23/06/24 de 23h59 à 04h40 opérations sur l´IHM1 Mistral au P1 de Marseille) et 1 nuit du Sa/Di de S37 pour essai complet de montée en c",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689508961",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,50,50,"2024-10-28","23:19:00","2024-12-06","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689508961",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,50,50,"2024-09-30","23:19:00","2024-11-15","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689508961",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,50,50,"2023-12-11","23:19:00","2024-12-13","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689508161",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,50,50,"2023-12-11","08:38:00","2024-12-13","09:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MC19-0062 entre 6805 et 17475 2021_SE_87 + 2021_SE_88 + 2021_SE_89 : décalage pour avoir 881611 en SF   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14340542561",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,45,45,"2024-11-10","22:35:00","2024-11-10","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0026458, OCP 7h00, 1 nuit du Di/Lu 10-11/11/24 (de 22h35 à 05h35), mise en service \"\"LGV +\"\" sur l'interface de la zone télécommandée de l'IHM1 de Mistral P1 de Marseille)  Conditions de réalisation : toute la zone d'action du poste de l'IHM1 de Mar",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689508961",null,"< >","Marseille-Blancarde - Bât Voyageurs","Aubagne",2024,2024,50,50,"2024-03-18","23:19:00","2024-03-29","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14978218061",null,"< >","Marseille-Blancarde - Bif Km 2,0 V B","Marseille-Blancarde - Technicentre",2024,2024,18,26,"2024-04-29","22:50:00","2024-06-28","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PMR Blancarde, rallongement du quai de MV1 sur 100 mètres :  Domaine S9 : MV1, ZEP G 5813+5811 (Du JI Z429/423 Km 2,550 au C 407 + du C407 Km 2,767 au C500 Km 3,333)  Domaine S11 Sél 2759 (du Km 2,550 au Km 3,335)  ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689510161",null,"< >","Marseille-Blancarde - Jonction 1","Aubagne",2024,2024,50,50,"2023-12-11","11:20:00","2024-12-13","12:12:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MC19-0071 avoir une heure de surveillance pleine de 1h00 2021_SE_81 + 2021_SE_82 + 2021_SE_83 : décalage de quelques minutes pour avoir 881426 en SO   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689510961",null,"< >","Marseille-Blancarde - Jonction 1","Aubagne",2024,2024,50,50,"2023-12-11","11:10:00","2024-12-13","12:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Décalage MC18-0207 passage entre 881034 et 881036 2021_SE_79 : décalage de quelques minutes pour avoir 881037 et 881036 en SO",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14952641261",null,"< >","Marseille-Blancarde - Technicentre","Marseille-Blancarde - Technicentre",2024,2024,36,50,"2024-09-02","00:00:00","2024-12-14","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"LNPCA -Remisage TC Blancarde- Dépose d'installations et Fermeture en continue de 4 VS grill Electrique (de VS37 à 43). La capacité réservée dans l'outil TCAP ne nous permet pas cette précision apportée ci-après :  déposes d'installations sur le site du TC",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14958334961",null,"< >","Marseille-Maritime-Arenc - Fsc Sud","Marseille-St-Charles - Marchandises",2024,2024,2,3,"2024-01-08","23:20:00","2024-01-19","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"LNPCA, Bloc Ouest Voie N :  Domaine S9 : ZEP G 5430+5432+5433 (du Cv304 Km 861,539 au Cv349 Km 861,689)   Domaine S11 : Sél 316 (du Km 861,539 au Km 861,810)",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14411818061",null,"< >","Marseille-Maritime-Arenc - Fsc Sud","Marseille-Maritime-Arenc - Fsc Sud",2024,2024,17,24,"2024-04-22","21:20:00","2024-06-14","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Le Canet - Fermeture du chantier puis cession de terrain à partir de S17 jusqu´à S24, DEF 07h35 - (Rac Canet et Rac Arenc reliant de part et d'autre le chantier du Canet avec neutralisation aiguilles 313ac/314bd sur Bif Rac. Arenc et VA Circulation P1 Are",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15445950461",null,"< >","Marseille-Maritime-Arenc - Fsc Sud","Marseille-Maritime-Arenc - Fsc Sud",2024,2024,20,21,"2024-05-18","19:00:00","2024-05-20","07:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Fermeture du Canet -Fermeture du chantier, cession du terrain- , OCP 36h  => We S20/21, du Sa 18/05 à 19h00 au Lu 20/05 à 07h00 : remplacement des ADV 203aV et 205aV par de la voie courante, dépose de l´ADV 203b et remplacement de la TJD 313ac/314bd par B",null,null,null,null,"Medium","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14609810461",null,"< >","Marseille-St-Charles - E/S Gare","Marseille-St-Charles - Remisage TER",2024,2024,6,6,"2024-02-05","21:00:00","2024-02-06","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx RAV MSC de 2024, zone E Circ de S06, L930, Traversée depuis Abeille vers zone E Circ. : MV1+MV2+MV3+MV4+GCirc du P3 0,820 => jusqu'au Sr2 Km 1,060 , Sur L830 depuis P3 Km 861,305 (C et D Circ.) => jusqu'au Km 857,206(C723)/859,625 (Aig 102bV) (MV1/MV2",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14976487661",null,"< >","Marseille-St-Charles - Marchandises","Marseille-St-Charles - Marchandises",2024,2024,36,50,"2024-09-02","00:00:00","2024-12-14","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"LNPCA : Libération Abeilles : travaux VS, prise des voies 19 à 23 uniquement, SA 2024 de septembre (S36) à décembre 2024 (S50) - démolition bâtiments le long de la voie A.",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14975654261",null,"< >","Marseille-St-Charles - Marchandises","Marseille-St-Charles - Marchandises",2024,2024,20,24,"2024-05-18","06:00:00","2024-06-16","22:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024 : Déménagement CSS Marseille, gare des Pierres uniquement sf voies 87 :  1 OCP WE S20 40h (MES : du Sa 18/05 à 06h00 au Di 19/05 22h00) + 1 OCP 40h secours S24 40h (MES : du Sa 15/06 06h00 au Di 16/06 22h00)  Nota : les travaux sur l'intégralité du",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14845750361",null,"< >","Marseille-St-Charles - Remisage TER","La Pomme",2024,2024,43,45,"2024-10-21","23:19:00","2024-11-08","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Meuleur SA2024, S43, V1+V2",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14346157561",null,"< >","Marseille-St-Charles - Remisage TER","Marseille-St-Charles - Remisage TER",2024,2024,1,15,"2024-01-02","23:20:00","2024-04-11","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx préparatoires et finitions du RAV MSC de 2024 de S01 à S03 et de S14 à S15, de 23h20 à 05h00 (du Lu/Ma à Je/Ve) : L930 VA, VB/MV4 à VC/MV3, MV1+MV2 => Sr2 Km 1,060 , sur L830 D à J en passant pas C/D/E/F Circ. => jusqu'au Km 860,187 (M1) et Km 860,113",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14621277961",null,"< >","Marseille-St-Charles - Remisage TER","Marseille-St-Charles - Remisage TER",2024,2024,4,4,"2024-01-22","23:00:00","2024-01-26","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx préparatoires et finitions du RAV MSC de 2024 de S04, (06h00 du Lu/Ma à Ve/Sa) : L930 VA, VB/MV4 à VC/MV3, MV1+MV2 +VG Circ.=> Sr2 Km 1,060 , sur L830 D à J en passant pas C/D/E/F Circ. => jusqu'au Km 860,113 (MV1+MV2) et jusqu'au  Km 860,257  (VE Cir",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14894397161",null,"< >","Marseille-St-Charles - Remisage TER","Marseille-St-Charles - Remisage TER",2024,2024,1,15,"2024-01-05","23:35:00","2024-04-12","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx préparatoires et finitions du RAV MSC de 2024 de S01 à S03 et 14 à 15, de 23h35 à 05h15 (nuit Ve/Sa) : L930 VA, VB/MV4 à VC/MV3, MV1+MV2 => Sr2 Km 1,060 , sur L830 D à J en passant pas C/D/E/F Circ. => jusqu'au Km 860,187 (M1) et Km 860,113 (M2) et ju",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13686953261",null,"< >","Martigues - Aig Rac La Mède","L'Estaque - Bât Voyageurs",2024,2024,11,41,"2024-03-11","09:20:00","2024-10-11","13:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MC19-0025 le 19/09/17 pour décalage pour passage du 879728.",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14537771861",null,"< >","Martigues - Aig Rac La Mède","L'Estaque - Bât Voyageurs",2024,2024,8,38,"2024-02-19","22:30:00","2024-09-20","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avi :  Domaine S9 : ZEP 33+40+46(V4)+75(Sortie VS 3 à 11) ou ZEP 35+38 ou ZEP 42(V4G)+74",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13686954261",null,"< >","Martigues - Aig Rac La Mède","L'Estaque - Panneau 901",2024,2024,50,50,"2023-12-11","15:26:00","2024-12-13","16:54:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13686955061",null,"< >","Martigues - CV 878","L'Estaque - Bât Voyageurs",2024,2024,50,50,"2023-12-11","09:38:00","2024-12-13","10:06:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_10 : vibration de +5' pour avoir TER 879716 en SO  2021_SE_52 : décalage de +35mn pour avoir 879716 en SO, aligné V2 de l'Estaque à Miramas, le 19/11/2019  MC19-0020 pour caler la plage entre 879716 et 879720  Modification le 05/02/2019 : inversio",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14484681361",null,"< >","Meaux - Aig Km 41,7-Ã‰v","Meaux - Bât Voyageurs",2024,2024,42,50,"2024-10-14","08:00:00","2024-12-14","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673363061",null,"< >","Meaux - Bât Voyageurs","Trilport - Bât Voyageurs",2024,2024,4,44,"2024-01-22","13:24:00","2024-11-03","14:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tournée M02 - Courbe Saint Faron ZEP MT01",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673363861",null,"< >","Meaux - Bât Voyageurs","Trilport - Bât Voyageurs",2024,2024,4,44,"2024-01-22","13:45:00","2024-11-03","14:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tournée M02 - Courbe Saint Faron ZEP TM 04  Train fermant 117278 Passage Trilport 14h30  ",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15029512061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,2,9,"2024-01-08","23:40:00","2024-03-01","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14754152461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,1,"2023-12-11","22:40:00","2024-01-05","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15700763161",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,1,1,"2024-01-01","23:30:00","2024-01-01","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Variante réduite JF pour TER",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-03-25","23:10:00","2024-09-06","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-03-25","23:10:00","2024-09-06","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-07-01","23:10:00","2024-11-10","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-07-01","23:10:00","2024-11-10","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-05-27","23:10:00","2024-05-31","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-05-27","23:10:00","2024-05-31","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-02-27","23:10:00","2024-03-08","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-02-27","23:10:00","2024-03-08","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13872239561",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,45,46,"2024-11-08","23:10:00","2024-11-11","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14484765361",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,40,50,"2024-09-30","23:10:00","2024-12-13","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673366261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,46,48,"2024-11-15","23:10:00","2024-11-25","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13884889461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,48,48,"2024-11-29","23:10:00","2024-12-01","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15614946061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,44,45,"2024-10-31","23:10:00","2024-11-04","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,4,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15733370361",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,43,43,"2024-10-25","23:10:00","2024-10-27","18:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15733412561",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,43,43,"2024-10-27","21:30:00","2024-10-27","04:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673359661",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,50,"2023-12-11","13:43:00","2024-12-13","14:27:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Train ouvrant: 117144  Train fermant: 117278",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673358861",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,50,"2023-12-11","09:23:00","2024-12-13","10:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Train ouvrant: 117267  Trin fermant: 117117",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-03-04","23:10:00","2024-10-20","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673360461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,50,"2023-12-11","00:40:00","2024-12-09","03:32:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673361261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,50,"2023-12-11","00:31:00","2024-12-09","03:39:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"03/02/2023 : DECC24_00077 pour circulation sillon JO.",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-03-04","23:10:00","2024-10-20","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14716575461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,37,42,"2024-10-14","23:10:00","2024-10-15","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO 795631",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14716575461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,37,42,"2024-09-09","23:10:00","2024-09-18","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO 795631",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673357261",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-04-22","23:10:00","2024-04-26","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673358061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,9,45,"2024-04-22","23:10:00","2024-04-26","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15029512061",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,2,9,"2024-01-08","23:40:00","2024-01-26","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14754152461",null,"< >","Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2024,2024,50,1,"2024-01-01","22:40:00","2024-01-05","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14467346161",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,24,27,"2024-06-10","01:00:00","2024-07-01","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690526361",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,39,47,"2024-11-04","10:26:00","2024-11-22","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Du 151427 au 151554. ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14517858761",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,48,50,"2024-11-25","21:30:00","2024-12-13","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14482200561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,2,3,"2024-01-08","22:30:00","2024-01-19","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14482256661",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,11,16,"2024-03-11","21:15:00","2024-04-18","05:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14481956861",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,18,"2023-12-11","23:15:00","2024-05-03","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14552666061",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,37,37,"2024-09-11","22:25:00","2024-09-12","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690524561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,50,"2024-01-17","23:30:00","2024-11-01","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690526361",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,39,47,"2024-09-23","10:26:00","2024-09-27","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Du 151427 au 151554. ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690523761",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,49,"2023-12-11","13:05:00","2024-12-06","13:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401806 fenêtre intercaler entre 151536 et 151538                   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690525561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,49,"2023-12-11","11:50:00","2024-12-06","13:26:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401805 MC18-255 pour sillon cadre PNSO05 le 18/11/16                     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690527361",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,49,21,"2023-12-10","23:45:00","2024-05-26","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage corrective en nuit de di/lu ",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690524561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-13","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690526361",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,39,47,"2024-09-23","10:26:00","2024-11-24","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Du 151427 au 151554. ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690524561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-13","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690524561",null,"< >","Melun - Bif Km 58,4","Montereau - Voie 5 - PVD",2024,2024,50,50,"2024-07-08","23:30:00","2024-07-23","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676236861",null,"< >","Metz-Nord - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,46,46,"2024-11-16","08:00:00","2024-11-16","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 sur les voies rapides entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_001 + 4D_MMZ-HGD_001 + 4D_HGD2_002. Report circulation sur voies BIS entre UCK ou THL et WPY BV. Entrée WPY par voie 1M interdite => report via FO",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676229661",null,"< >","Metz-Nord - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                         ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676224061",null,"< >","Metz-Nord - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                           ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676154261",null,"< >","Metz-Nord - Bât Voyageurs","Woippy - AccÃ¨s Sud",2024,2024,11,41,"2024-03-11","23:30:00","2024-10-11","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CAP 6h00 de nuit voies 1 + 2 au niveau de Woippy BV. Simultanément avec 4F_MZ-WPY_001. Report circulation sur voies BIS entre MZS AO et WPY AN. Entrée WPY par voie 1M libre. Permet de travailler sur la jonction Bis/Rapides au BV. Prévoir un renfort au fai",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676628961",null,"< >","Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2024,2024,3,42,"2024-01-21","23:25:00","2024-10-20","03:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"04h05 simultanées nuit de DI/LU durant 2 WE. Re-paramétrage Mistral CCR Lorraine. Interdiction de circulation dans la zone d´action des PAI de Pagny et Metz. Décalage horaire. Fenêtres déformées simultanément sur lignes 89000 + 95000 + 140000 + 180000 + 1",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676631961",null,"< >","Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2024,2024,21,27,"2024-05-21","23:35:00","2024-07-05","05:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec 4C_MZ_014 qui reprend les conséquences circulations.",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676629961",null,"< >","Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2024,2024,43,44,"2024-10-27","23:40:00","2024-11-03","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Fenêtre déformée 5h10 nuit DI/LU sur voies V1+V2+1M+2M, simultanément lignes 180000+191300. Maintenance annuelle ADV au nord de MZV. Accès Metz-Ville côté Woippy interdit. Détournements via MZ DLP avec rebroussement à Metz Sablon pour les trains de/vers N",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676624761",null,"< >","Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2024,2024,11,41,"2024-03-11","23:30:00","2024-10-11","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2019 Modif des horaires suite à la demande de la MC 144  SA2023 Modification des horaires par main courante (passage de 23h26 - 05h26 à 23h30 - 05h30)",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676627361",null,"< >","Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2024,2024,50,50,"2023-12-11","13:35:00","2024-12-13","14:38:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676628161",null,"< >","Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2024,2024,50,50,"2023-12-11","09:25:00","2024-12-13","10:22:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676626561",null,"< >","Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2024,2024,49,43,"2023-12-10","23:56:00","2024-11-02","02:56:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676625761",null,"< >","Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2024,2024,49,43,"2023-12-10","23:56:00","2024-11-02","02:56:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676310561",null,"< >","Metz-Ville - Quai Est","Metz-Ville - Poste 66 CTN1",2024,2024,11,49,"2024-03-11","23:35:00","2024-12-06","05:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 5h30 simultanées voies 1 + 2 lignes 3 + 11 de nuit entre Metz Ville et MZ-AM + MZS-AO + MZS-AE avec voies 1T + 2T. Accès Metz Ville et dépôt côté BV interdits. Suppression TER. Détournement FRET via Metz Marchandises ou Metz-Devant-les-Ponts. Attentio",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687303261",null,"< >","Miramas - Aig Km 805,1","Miramas - FSC réception",2024,2024,50,39,"2023-12-11","22:07:00","2024-09-27","05:01:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CCR OUEST P. -Etape1- : DEF V1+V2 de St Martin de Crau à Mas (exclus) de 06h57, à prendre avec 3D_TCN-MAS_011 :  Etendue S9 : V1 du C 1 Km 791,183 de SMA au C 603 Km 808,585 de MAS / V2 du GF Aig 301 (V2/V2Bis) Km 805,980 de MAS à la PATC du Km 791,250 de",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14110119961",null,"< >","Miramas - Aig Km 805,1","St-Chamas",2024,2024,13,13,"2024-03-30","00:00:00","2024-03-31","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CCR OP1, OCP2 36h We S13/14, V2+V2Bis+VBCirc/VB+Tête de voies F. Départ :  Etendue S9 : V2 du Cv647 Km 809,384 au C204 Km 805,240 et V2Bis TTes Zeps / VBCirc=>VB du C601 Km 808,650 au C639 Km 809,349 / F.Départ du des GF Km 808,750 au Km 808,887   Domaine",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14535645861",null,"< >","Miramas - Aig Km 808,5","Miramas - Dépôt",2024,2024,10,10,"2024-03-04","23:59:00","2024-03-08","03:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avi :  Etendue S9 : L925 V1+V3G (du V1 Cv517 Km 67,251 au C627 Km 68,512+ V3G+ VS E/S dépôt)/L925 V2 du C619 Km 68,100 au C612 Km 68,220 / V1 L830 du C603 Km 808,585 au Cv610 Km 808,947    Domaine S9 :  L925 V1 173+175+177+190+179+137(VS)+1",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14012586261",null,"< >","Miramas - Aig Km 808,5","Miramas - Dépôt",2024,2024,4,4,"2024-01-27","00:15:00","2024-01-28","12:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"OCP1 36h, WE S04/05, sur VC, VD, V1MRS (passage par A circ+1Ter+B Circ+AM) :  Etendue S9 : 1S=>VD du JI Z605/617 Km 68,120 au C 627 Km 68,512 + 2S=>VC du Cv 615 Km 68,000 au C 625 Km 68,564 / V1Mrs du C 603 Km 808,585 au C 623 Km 68,564/809,312  Domaine S",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687360661",null,"< >","Miramas - Aig Km 818,2","Vitrolles-Aéroport-Marseille-P",2024,2024,50,40,"2023-12-11","22:35:00","2024-10-04","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CCR OUEST P. -Etape1- : CAP V1Bis Berre +1 Bis de RGC + Voie circ. Aix à RGC de 06h55  Domaine S9, V1Bis Berre : ZEP G 861+863+867   Domaine S9, V1 Bis RGC : ZEPG 29+31+49+27  Domaine S9, VU Aix-Rgc 33+29+89  Nota : les ZEPs de Berre 865 (V3+V5) ne peuven",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687355661",null,"< >","Miramas - Bât Voyageurs","Vitrolles-Aéroport-Marseille-P",2024,2024,8,24,"2024-05-28","00:00:00","2024-06-15","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687355661",null,"< >","Miramas - Bât Voyageurs","Vitrolles-Aéroport-Marseille-P",2024,2024,8,24,"2024-02-20","00:00:00","2024-03-16","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687372061",null,"< >","Miramas - Bât Voyageurs","Vitrolles-Aéroport-Marseille-P",2024,2024,50,40,"2023-12-11","22:35:00","2024-10-04","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CCR OUEST P. : DEF V1 de MAS à RGC (inclus jusqu'au C3 de RGC Km 835,940) de 06h55  Etendue S9 : V1 du C653 Km 810,004 de Mas au C3 Km 835,940 de Rognac (+ du C3 Km 835,940 à la PATC Km 837,500 de Rognac = ZEP 27+85)  Domaine S9 : ZEP G Mas 99 + Les Roque",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687377261",null,"< >","Miramas - Bât Voyageurs","Vitrolles-Aéroport-Marseille-P",2024,2024,50,40,"2023-12-12","22:35:00","2024-10-03","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CCR OUEST P. -Etape1- : DEF V2 de RGC à MAS (depuis le JI Z14/16B de RGC Km 835,940 jusqu'au C 651 de MAS Km 810,004) de 06h55 (depuis le C4 de RGC Km 836,421 au Km 835,940 JI z14/z6B)  Etendue S9 : V2 depuis le JI Z14/16B de RGC Km 835,940 au C 653 Km 81",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687374261",null,"< >","Miramas - Bât Voyageurs","Vitrolles-Aéroport-Marseille-P",2024,2024,50,40,"2023-12-11","23:45:00","2024-10-04","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CCR OUEST P. -Etape1- : DEF V2 de RGC à MAS (depuis le JI Z14/16B de RGC Km 835,940 jusqu'au C 651 de MAS Km 810,004) de 05h45 (depuis le C4 de RGC Km 836,421 au Km 835,940 JI z14/z6B)  Etendue S9 : V2 depuis le JI Z14/16B de RGC Km 835,940 au C 653 Km 81",null,null,null,null,"Major","1,3,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14552158561",null,"< >","Miramas - Bât Voyageurs","St-Chamas",2024,2024,12,12,"2024-03-20","00:10:00","2024-03-23","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, Tir823/08  : DEF V1+V2 de MAS à RGC de 05h00  Etendue S9 : V1 du C653 Km 810,004 de Mas au C1 Km 834,933 de Rognac+ V2 depuis PATC de RGC Km 834,175 au C 651 Km 810,004 de Mas  Domaine S9 : V1 ZEP G Mas 99 + Les Roques ZEP G 801+821+841 + Berre ZE",null,null,null,null,"Medium","3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687356661",null,"< >","Miramas - Bât Voyageurs","Berre",2024,2024,50,50,"2023-12-11","10:35:00","2024-12-13","11:46:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_27 : vibration de -5' pour avoir TER 17701 en SO et TER 886565 en SF  MC19-0146 Passage entre 879653 et 87655 Modif suite main courante 2020 Min-547-871    ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687357461",null,"< >","Miramas - Bât Voyageurs","Berre",2024,2024,50,50,"2023-12-11","10:20:00","2024-12-13","11:08:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Annulation Décalage MC17-0229 pour 879610 le 21/10/15 2021_SE_65 décalage de + 40mn pour avoir 879518 en SO et 879522 en SF, aligné V2 de St Louis à Tarascon, le 19/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13686995261",null,"< >","Miramas - Bât Voyageurs","Fos-sur-Mer - ITE Lafarge",2024,2024,10,50,"2024-04-08","22:30:00","2024-04-19","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Demande EF d'avancer les fenêtres génériques Miramas - Lavalduc, Lavalduc - Fos et Lavalduc - Martigues d'une heure. Validation lors de la Concertation SE-NEN du 25/11/2014.   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14113365161",null,"< >","Miramas - Bât Voyageurs","Fos-sur-Mer - ITE Lafarge",2024,2024,21,40,"2024-05-21","22:00:00","2024-10-04","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CCR OP1, DEF 07h30 MAS<=>LVU",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13686995261",null,"< >","Miramas - Bât Voyageurs","Fos-sur-Mer - ITE Lafarge",2024,2024,10,50,"2024-03-04","22:30:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Demande EF d'avancer les fenêtres génériques Miramas - Lavalduc, Lavalduc - Fos et Lavalduc - Martigues d'une heure. Validation lors de la Concertation SE-NEN du 25/11/2014.   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14551847761",null,"< >","Miramas - Bât Voyageurs","Rognac - Poste A",2024,2024,12,12,"2024-03-20","00:10:00","2024-03-23","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, Tir823/08  : DEF V1+V2 de MAS à RGC de 05h00  Etendue S9 : V1 du C653 Km 810,004 de Mas au C1 Km 834,933 de Rognac+ V2 depuis PATC de RGC Km 834,175 au C 651 Km 810,004 de Mas  Domaine S9 : V1 ZEP G Mas 99 + Les Roques ZEP G 801+821+841 + Berre ZE",null,null,null,null,"Medium","3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687299461",null,"< >","Miramas - Bif Km 67","Miramas - Panneau 601",2024,2024,8,48,"2024-02-19","09:55:00","2024-11-29","15:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA 2024, Famille B, Maintenance massifiée sur ADV AMS, raccord et entrée sortie Dépot :   ZEP : 154+156+161+163+117+145+147+149+183+185+174+176+178+180+182+184+168  Nota : étapes de réunion avec la DT  ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13686993661",null,"< >","Miramas - Bif Km 811,8","Fos-sur-Mer - ITE Lafarge",2024,2024,50,50,"2023-12-11","14:51:00","2024-12-13","16:06:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13686996261",null,"< >","Miramas - Bif Km 811,8","Lavalduc - Bif Km823,3 V2B",2024,2024,50,50,"2023-12-11","10:13:00","2024-12-13","11:03:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_12 : vibration de +8' pour avoir TER 879716 en SO  2021_SE_54 : décalage de +35mn pour avoir 879716 en SO, aligné V2 de l'Estaque à Miramas, le 19/11/2019  MC19-0022 pour caler la plage entre 879716 et 879720  Modification le 05/02/2019 : inversio",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14463937161",null,"< >","Miramas - FSC réception","Miramas - Triage PC",2024,2024,42,48,"2024-10-15","05:05:00","2024-11-30","05:05:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"RAV Mas, F. Triage, réservation des voies 27+28+29 pour Base arrière du Ma 15/10 à 05h05 de S42 au Sa 30/11 à 05h05 de S48 :  Domaine S9 : 527+526+529  Domaine S11 : néant",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14596796961",null,"< >","Miramas - Relais La Crau","Miramas - Bât Voyageurs",2024,2024,50,25,"2023-12-11","14:00:00","2024-06-21","22:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"La réservation capacitaire de l'outil TCAP sur les VS de Miramas ne nous permet pas de réservation voie par voie (à voir les nouvelles données prévues pour fin juin, fin de campagne RP0, si elles nous permettront ou pas une réservation plus précise : ici ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14535706861",null,"< >","Miramas - Relais La Crau","Miramas - Bât Voyageurs",2024,2024,10,10,"2024-03-04","23:59:00","2024-03-08","03:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avi (V3G) :  Etendue S9 : L925 V1+V3G (du V1 Cv517 Km 67,251 au C627 Km 68,512+ V3G+ VS E/S dépôt)/L925 V2 du C619 Km 68,100 au C612 Km 68,220 / V1 L830 du C603 Km 808,585 au Cv610 Km 808,947    Domaine S9 :  L925 V1 173+175+177+190+179+137",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14573175261",null,"< >","Miramas - Relais La Crau","Miramas - Panneau 601",2024,2024,19,19,"2024-05-08","12:10:00","2024-05-10","00:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CCR OP1, OCP3 36h, We S19, de Me 08/05 à 12h10 au  VE 10/05 à 00h10 :  Etendue S9 : Racc 1 jusqu'au Cv510 Km 67,270 + Racc 2 Jusqu'au C508 Km 67,391 + V1TER C403 Km 807,317 au Pte Ag 410 Km 808,109 + V2TER/VB Circ du C401 Km 807,317 au C601 Km 808,650 + V",null,null,null,null,"Medium","3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14012551761",null,"< >","Miramas - Relais La Crau","St-Chamas",2024,2024,4,4,"2024-01-27","00:15:00","2024-01-28","12:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"OCP1 36h, WE S04/05, sur VC, VD, V1MRS (passage par A circ+1Ter+B Circ+AM) :  Etendue S9 : 1S=>VD du JI Z605/617 Km 68,120 au C 627 Km 68,512 + 2S=>VC du Cv 615 Km 68,000 au C 625 Km 68,564 / V1Mrs du C 603 Km 808,585 au C 623 Km 68,564/809,312  Domaine S",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14114692761",null,"< >","Miramas - Relais La Crau","Miramas - Dépôt",2024,2024,40,49,"2024-09-30","23:05:00","2024-12-07","05:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"RAV MAS, CAP 06h00, Domaine de base :  Etendue S9 : V1TER C306 Km 806,814 au Pte Ag 410 Km 808,109 + V2TER/VB Circ du C308 Km 806,814 au GF Aig 603v Km 808,764 + VRacc. Triage du Pte Aig 421 Km 808,197 au C416 Km 808,369 +Racc V1 (du Cv 510 Km 67,270 à la",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14115493161",null,"< >","Miramas - Relais La Crau","Miramas - Dépôt",2024,2024,44,46,"2024-11-01","05:01:00","2024-11-12","05:01:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"RAV MAS, OCP 72h00, WE(s) S44/45 + S45/46, Domaine de base :  Etendue S9 : V1TER C306 Km 806,814 au Pte Ag 410 Km 808,109 + V2TER/VB Circ du C308 Km 806,814 au GF 603v Km 808,764 + VRacc. Triage du Pte Aig 421 Km 808,197 au C416 Km 808,369 +Racc V1 (du Cv",null,null,null,null,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14535551661",null,"< >","Miramas - Relais La Crau","Miramas - Dépôt",2024,2024,10,10,"2024-03-04","23:59:00","2024-03-08","03:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avi :  Etendue S9 : L925 V1+V3G (du V1 Cv517 Km 67,251 au C627 Km 68,512+ V3G+ VS E/S dépôt)/L925 V2 du C619 Km 68,100 au C612 Km 68,220 / V1 L830 du C603 Km 808,585 au Cv610 Km 808,947    Domaine S9 :  L925 V1 173+175+177+190+179+137(VS)+1",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14114692761",null,"< >","Miramas - Relais La Crau","Miramas - Dépôt",2024,2024,40,49,"2024-09-30","23:05:00","2024-12-06","05:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"RAV MAS, CAP 06h00, Domaine de base :  Etendue S9 : V1TER C306 Km 806,814 au Pte Ag 410 Km 808,109 + V2TER/VB Circ du C308 Km 806,814 au GF Aig 603v Km 808,764 + VRacc. Triage du Pte Aig 421 Km 808,197 au C416 Km 808,369 +Racc V1 (du Cv 510 Km 67,270 à la",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14535482661",null,"< >","Miramas - Triage PC","Miramas - Faisceau Départ",2024,2024,23,36,"2024-06-03","23:59:00","2024-09-06","03:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA 2024, UP SES Avi :  Etendue S9 : sortie F.Tri V51 à V74 (du Km 807,680 au C1 Km 807,736)  Domaine S9 : uniquement ZEPG 660+661+662+664 (Poste C)     Nota : révision SIPH/VS TCAP faites au 23-07-22",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14535505361",null,"< >","Miramas - Triage PC","Miramas - Faisceau Départ",2024,2024,24,37,"2024-06-10","23:59:00","2024-09-13","03:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA 2024, UP SES Avi :  Etendue S9 : sortie F.Tri V31 à V50 (du Km 807,614 au Km 807,875)  Domaine S9 : uniquement ZEPG 304+647+658+659+663    Nota : révision SIPH/VS TCAP faites au 23-07-22",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14535532461",null,"< >","Miramas - Triage PC","Miramas - Faisceau Départ",2024,2024,25,25,"2024-06-17","23:59:00","2024-06-19","03:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Avi :  Etendue S9 : du 29C Km 807,568 (F. Relais)  au C9C Km 807,746 (Voie SAS Mach.)   Domaine S9 : ZEPG 313+315+300    Nota : révision SIPH/VS TCAP faites au 23-07-22  ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462347061",null,"< >","Miramas - Triage PC","Miramas - Triage PC",2024,2024,42,48,"2024-10-14","23:05:00","2024-11-29","05:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Extension du domaine fermée, depuis le domaine de base vers le faisceau Relais, de S42 à S48 :  Etendue S9 : du Km 806,688 au Km 807,566 pour les V153 et 154 et limitée au Km 807,509 pour les V150 à 152    Domaine S9 : 184+313+315+753+754+757+758  Etendue",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462594961",null,"< >","Miramas - Triage PC","Miramas - Triage PC",2024,2024,44,46,"2024-11-01","05:01:00","2024-11-12","05:01:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Extension du domaine fermée, depuis le domaine de base vers le faisceau Relais, pdt tte l'OCP 72h,  WE(s) S44/45 + S45/46 :  Etendue S9 : du Km 806,766 au Km 807,509 pour les V153 et 154 et limitée au Km 807,509 pour les V150 à 152  Domaine S9 : 184+313+3",null,null,null,null,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462981961",null,"< >","Miramas - Triage PC","Miramas - Triage PC",2024,2024,40,49,"2024-10-01","05:05:00","2024-12-07","05:05:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fermeture continue de la V154 sur le F. Relais, aire de montage des APvs, du Ma 01/10 à 05h05 de S40 à Sa 07/12 à 05h05 de S49 :   Etendue S9 : du Km 806,766 au Km 807,509   Domaine S9 : ZEPG 754 (V154)   Etendue S11 : du Km 806,766 au Km 807,509, CBT S11",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14463434861",null,"< >","Miramas - Triage PC","Miramas - Triage PC",2024,2024,40,49,"2024-09-30","23:05:00","2024-12-06","05:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en application de la CBT S11 sur 154 ( mise en place et retrait) , besoin de consigner la Sél 134, F. relais inexploitable sur 2 jours (Lu/Ma et Ma/Me) de la S40 et 2 jrs sur la S49 :  Etendue S9 : du Km 806,670 au Km 807,509 pour les V153 et 154 et ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688383661",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-15","22:10:00","2024-12-13","05:18:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"7h18 de sim. partielle déduite. SA2018 => + ME 9/05 + ME 31/10                            ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688385261",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-15","23:21:00","2024-12-13","05:52:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h21 de sim. partielle déduite SA2018 => + ME 9/05 + ME 31/10            ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688388061",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,49,"2023-12-16","23:20:00","2024-12-07","07:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable sa/di  train ouvrant  9098 quand il circule, train fermant 6136",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688389061",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,49,49,"2023-12-10","23:30:00","2024-12-08","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable di/lu train ouvrant 6137, train fermant 6900",null,null,null,null,"Major","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688382861",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-11","12:11:00","2024-12-13","13:03:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10701424",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688384461",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-11","14:44:00","2024-12-13","15:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10701421",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688381261",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-11","22:23:00","2024-12-09","05:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h50 de sim. partielle déduite. Pour SA2018 => LU/MA + jours typés LU : MA/ME 26-27/12, MA/ME 02-03/01, MA/ME 03-04/04, ME/JE 02-03/05, MA/ME 22-23/05         ",null,null,null,null,"Major","1,2,3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688380461",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-12","22:10:00","2024-12-12","05:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"7h15 de sim. partielle déduite. Sauf jours particulier TGV typé LU ou VE  SA2018 => SF ME 9/05 + ME 31/10      ",null,null,null,null,"Major","2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688386061",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,52,46,"2023-12-25","23:40:00","2024-11-11","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022       ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688382061",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,50,50,"2023-12-11","21:48:00","2024-12-12","05:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"7h18 de sim. partielle déduite. Sauf jours typés VE  sur le calendrier TGV SA2018 => SF ME 9/05 + ME 31/10                       ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688387061",null,"< >","Montanay-Bif","Poste 44 Grenay - Bif de Lyon",2024,2024,52,46,"2023-12-25","23:00:00","2024-11-11","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14886304761",null,"< >","Montanay-Bif","Grenay-PRG - Rep4431-Pk419,4",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00",null,null,null,null,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14011400361",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,15,16,"2024-04-13","00:05:00","2024-04-20","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prépa MES LGV+ Les zones doivent être au blanc.  ",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14011804961",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,10,21,"2024-04-13","23:10:00","2024-04-21","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prépa MES LGV+ Les zones doivent être au blanc.  ",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14333548561",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,13,13,"2024-03-25","09:00:00","2024-03-28","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14333698361",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,13,14,"2024-03-29","10:00:00","2024-04-03","14:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13793479061",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null," Plage modifiée le 01/12/2022 suite report de la MES",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689841061",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance IHM 1 Les zones doivent etre au blanc.   ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641848161",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   Les zones doivent etre au blanc.",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14011804961",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,10,21,"2024-03-09","23:10:00","2024-05-25","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prépa MES LGV+ Les zones doivent être au blanc.  ",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14640970761",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard   Les zones doivent etre au blanc.",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14365016761",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,4,17,"2024-01-22","10:10:00","2024-04-25","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie A OU Voie B (Evitement de Nogent)  Complément de la 4D_AIY-LLA_012 (Voie 1 OU Voie 2).  Si Voie 1 alors Voie A  Si Voie 2 alors Voie B",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14365140761",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,4,27,"2024-01-26","10:15:00","2024-07-05","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie A OU Voie B  (Evit. Nogent)  En complément de la 4F_AIY-LLA_001 (Voie 1 OU Voie 2)  Si Voie 1 alors Voie A  Si voie 2 alors Voie B",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446758361",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,9,11,"2024-02-26","10:40:00","2024-03-14","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4D_AIY-LLA_016   Voie 1 + 2",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446852061",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,16,17,"2024-04-15","10:45:00","2024-04-25","13:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4D_AIY-LLA_018   Voie 1 + 2",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446684161",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,6,6,"2024-02-05","09:10:00","2024-02-08","15:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4D_AIY-LLA_014 (Voie 1)",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446706161",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,7,11,"2024-02-12","10:45:00","2024-03-14","16:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4D_AIY-LLA_015   Voie 2",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14446812161",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,9,10,"2024-02-26","14:40:00","2024-03-05","16:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14447001961",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,11,11,"2024-03-16","11:30:00","2024-03-16","11:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4D_AIY-LLA_003  OCP de 24h Voie 1 + 2",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14366366361",null,"< >","Montbard - Bât Voyageurs","Montbard - C 2211 Ã  2214",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MES LGV+ Les zones doivent être au blanc.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13793849461",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage modifiée le 01/12/2022 suite report de la MES.",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14366445261",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MES LGV+",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641192261",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard  les zones devront être au blanc.",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641865161",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard  les zones devront être au blanc.",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689834461",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance IHM, les zones devront être au blanc.",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14333663161",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bif Km 259",2024,2024,35,39,"2024-08-26","10:15:00","2024-09-27","16:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complement de la 4D_AIY-LLA_021",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14333883161",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bât Voyageurs",2024,2024,14,15,"2024-04-04","10:36:00","2024-04-08","12:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 6703    TF: 6705  Accès Entrée Nord (par Voie 1) du Fx Impaire Impossible",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14334347461",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bât Voyageurs",2024,2024,15,15,"2024-04-10","10:35:00","2024-04-11","12:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9206    TF: 9210",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14615000261",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Bât Voyageurs",2024,2024,35,39,"2024-08-26","10:15:00","2024-09-27","16:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9264   TF: 891379",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14333627861",null,"< >","MONTBARD - C 2211 A 2214","Les Laumes-Alésia - Faisceau Impair",2024,2024,13,13,"2024-03-27","09:10:00","2024-03-28","14:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261  TF: 5763  Accès Fx Impaire Impossible  ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673317561",null,"< >","Noisy-le-Sec - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,28,36,"2024-07-08","01:20:00","2024-09-08","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673322561",null,"< >","Noisy-le-Sec - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,8,50,"2024-02-19","01:14:00","2024-12-09","04:23:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673320961",null,"< >","Noisy-le-Sec - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2024,2024,8,50,"2024-02-19","01:10:00","2024-12-09","04:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673380261",null,"< >","Noisy-le-Sec - Bif Impaire O","Noisy-le-Sec - Bât Voyageurs",2024,2024,14,37,"2024-04-01","12:00:00","2024-09-13","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"De ZEP 770 à ZEP 776 2B4/2EO + ZEP 782 2B1 Reconduction DETC20_02242   ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673378661",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,24,24,"2024-06-10","10:00:00","2024-06-14","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Schéma 18 ZEP 627+751+753   ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-02-12","23:30:00","2024-05-16","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673379461",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,15,15,"2024-04-08","10:00:00","2024-04-12","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Schéma 19 De ZEP 633 à ZEP 775 1B1   ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15070155261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,18,18,"2024-04-29","22:30:00","2024-05-02","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-03-25","23:30:00","2024-03-28","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2023-12-11","23:30:00","2024-12-12","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13797360761",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,30,36,"2024-07-22","01:30:00","2024-09-06","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"High","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673388861",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,3,17,"2024-01-15","23:00:00","2024-04-25","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14998706761",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,6,13,"2024-02-05","23:00:00","2024-03-28","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1B4+1L1+1B1 zone 2   Zone 2535a sur ZEP 633 libre pour circulation sur aig 2535a vers 2535b       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15002413361",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,7,9,"2024-02-16","23:30:00","2024-02-26","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1B4+1L1+1B1 zone 2   Zone 2535a sur ZEP 633 libre pour circulation sur aig 2535a vers 2535b       ",null,null,null,null,"High","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-01-01","23:30:00","2024-10-11","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-01-01","23:30:00","2024-11-21","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-05-13","23:30:00","2024-12-06","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13836398261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,48,"2023-12-17","23:50:00","2024-12-01","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"Major","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13836363461",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2023-12-16","23:15:00","2024-12-14","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673383261",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,50,50,"2024-01-05","23:30:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673386061",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,38,38,"2024-09-21","12:16:00","2024-09-21","12:16:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"DFV sur ZEP type G ensemble des ZEP du poste CHL et les ZEP encadrantes de chaque poste Ligne 1 jusqu´avant les quais de Gagny Ligne 4 jusqu´avant les quais de Nogent         ",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673387461",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,17,17,"2024-04-27","20:00:00","2024-04-27","08:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"DFV sur ZEP type G ensemble des ZEP du poste CHL et les ZEP encadrantes de chaque poste Ligne 1 jusqu´avant les quais de Gagny Ligne 4 jusqu´avant les quais de Nogent         ",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673341061",null,"< >","Noisy-le-Sec - Bif Impaire O","Bondy - Bât Voyageurs",2024,2024,15,15,"2024-04-08","13:30:00","2024-04-12","15:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1TER : ZEP 789 CHL  Sans impact",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673318361",null,"< >","Noisy-le-Sec - Bif Impaire O","Gagny - Aig V2Bis/V2Ter",2024,2024,28,36,"2024-07-08","01:30:00","2024-09-08","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673319361",null,"< >","Noisy-le-Sec - Bif Impaire O","Gagny - Bât Voyageurs",2024,2024,28,36,"2024-07-08","01:00:00","2024-09-08","03:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673320161",null,"< >","Noisy-le-Sec - Bif Impaire O","Gagny - Bât Voyageurs",2024,2024,8,50,"2024-02-19","01:07:00","2024-12-09","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673321761",null,"< >","Noisy-le-Sec - Bif Impaire O","Gagny - Bât Voyageurs",2024,2024,8,50,"2024-02-19","01:10:00","2024-12-09","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676665261",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2024,2024,50,50,"2023-12-11","10:48:00","2024-12-13","11:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676666861",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2024,2024,50,50,"2023-12-11","14:11:00","2024-12-13","15:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676664461",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2024,2024,50,50,"2023-12-11","09:20:00","2024-12-13","10:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676668461",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2024,2024,5,50,"2024-01-29","00:00:00","2024-12-09","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676663661",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Montigny AT",2024,2024,50,50,"2023-12-11","14:09:00","2024-12-13","15:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676662861",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Montigny AT",2024,2024,50,40,"2023-12-11","00:00:00","2024-10-06","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14528331061",null,"< >","Novéant - Bât Voyageurs","Metz-Sablon - Montigny AT",2024,2024,47,48,"2024-11-18","23:00:00","2024-11-29","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf V1B entre Novéant et Metz-Sablon. Report des trafics V1. Accès faisceau Montigny en venant de Novéant interdit.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676660861",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,11,50,"2024-03-11","23:00:00","2024-12-13","05:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : X voies sur Y passé de \"\"2V/2\"\" à \"\"2V/4\"\", et Typologie schématisée passée de \"\"Simultanée\"\" à \"\"Autre\"\"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676661861",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,8,48,"2024-02-19","23:00:00","2024-11-29","05:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676666061",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,50,40,"2023-12-11","00:00:00","2024-10-06","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676667661",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,5,50,"2024-01-29","00:00:00","2024-12-09","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676661861",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,8,48,"2024-04-22","23:00:00","2024-11-22","05:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676695161",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,11,46,"2024-03-16","23:45:00","2024-11-17","04:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Def 4 voies entre Novéant et Metz",null,null,null,null,"High","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676660861",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,11,50,"2024-08-12","23:00:00","2024-12-13","05:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : X voies sur Y passé de \"\"2V/2\"\" à \"\"2V/4\"\", et Typologie schématisée passée de \"\"Simultanée\"\" à \"\"Autre\"\"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676693761",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,42,45,"2024-10-14","23:00:00","2024-11-08","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf V2B entre Metz-Sablon et Novéant.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13910915161",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,45,47,"2024-11-09","23:30:00","2024-11-24","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf V1+V2+V1B+V2B entre Novéant et Metz-Sablon.",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14548405761",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,39,41,"2024-09-28","21:30:00","2024-10-13","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf V2B entre Metz-Sablon et Novéant.",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676670261",null,"< >","Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2024,2024,3,42,"2024-01-21","23:25:00","2024-10-20","03:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"04h05 simultanées nuit de DI/LU durant 2 WE. Re-paramétrage Mistral CCR Lorraine. Interdiction de circulation dans la zone d´action des PAI de Pagny et Metz. Décalage horaire. Fenêtres déformées simultanément sur lignes 89000 + 95000 + 140000 + 180000 + 1",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14011430261",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,15,16,"2024-04-13","23:30:00","2024-04-21","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prépa MES LGV +",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14011302061",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,15,16,"2024-04-13","00:05:00","2024-04-20","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13836175461",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,17,44,"2024-04-22","09:45:00","2024-10-31","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En SIM avec la 4D_TNE-AIY_002  L'aig 1722 est dégagée. La sortie des TGV est possible.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13851395361",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,8,47,"2024-02-19","09:45:00","2024-11-22","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En SIM avec la 4D_TNE-AIY_014",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13972261361",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,33,41,"2024-08-12","09:25:00","2024-10-11","16:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En SIM avec la 4D_TNE-AIY_016  L'aig 1722 est dégagée. La sortie des TGV est possible.",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14768798861",null,"< >","Nuits-sous-Ravières","Aisy - Rac LGV",2024,2024,19,27,"2024-05-06","09:50:00","2024-07-05","16:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En SIM avec la 4D_TNE-AIY_021  L'aig 1722 est dégagée. La sortie des TGV est possible.",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703670661",null,"< >","Paris-La Chapelle - Jonct Km 3,4","St-Ouen-les-Docks - Garage Centraux",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-14","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703671661",null,"< >","Paris-La Chapelle - Poste E","St-Ouen-les-Docks - Garage Centraux",2024,2024,1,49,"2024-01-02","23:35:00","2024-12-06","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLE (fermeture gare sout) ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14894106361",null,"< >","Paris-La Chapelle - Poste E","Paris-La Chapelle - Jonct Km 3,4",2024,2024,28,34,"2024-07-12","23:30:00","2024-08-19","04:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703619661",null,"< >","Paris-Landy - Pleyel","St-Denis - Garages Pairs",2024,2024,1,50,"2024-01-08","23:35:00","2024-01-28","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703619661",null,"< >","Paris-Landy - Pleyel","St-Denis - Garages Pairs",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13875530761",null,"< >","Paris-Landy - Pleyel","St-Denis - Garages Pairs",2024,2024,1,49,"2024-01-02","10:10:00","2024-12-06","12:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"maintenance de jour DV/RV",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14351655161",null,"< >","Paris-Landy - Pleyel","St-Denis - Garages Pairs",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-09","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13541700461",null,"< >","Parthenay - Bât Voyageurs","Niort - Bif de Thouars",2024,2024,50,50,"2023-12-11","12:45:00","2024-12-13","13:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13541701261",null,"< >","Parthenay - Bât Voyageurs","Niort - Bif de Thouars",2024,2024,20,38,"2024-05-13","07:00:00","2024-09-20","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687217861",null,"< >","Pas-des-Lanciers - Bât Voyageurs","L'Estaque - Bât Voyageurs",2024,2024,50,50,"2023-12-11","10:56:00","2024-12-13","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_30 : vibration de -10' pour avoir TER 17701 en SO et TER 886565 en SF  MC19-0149 Calage entre 879653 et 879655 Modif main courante 2020 Maj-550_871   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687217061",null,"< >","Pas-des-Lanciers - Bât Voyageurs","L'Estaque - Bât Voyageurs",2024,2024,50,50,"2023-12-11","09:56:00","2024-12-13","10:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Annulation Décalage MC17-0226 pour 879610 le 21/10/15 2021_SE_68 : décalage de +30mn pour avoir 879518 en SO et 879522 en SF, aligné V2 de St Louis à Tarascon, le 19/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14340462561",null,"< >","Pas-des-Lanciers - V 4 Garage","Séon-St-Henry",2024,2024,45,45,"2024-11-10","22:35:00","2024-11-10","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0026458, OCP 7h00, 1 nuit du Di/Lu 10-11/11/24 (de 22h35 à 05h35), mise en service \"\"LGV +\"\" sur l'interface de la zone télécommandée de l'IHM1 de Mistral P1 de Marseille)  Conditions de réalisation : toute la zone d'action du poste de l'IHM1 de Mar",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688243461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2024-09-23","22:24:00","2024-09-26","06:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h26 de sim. partielle déduite. derrière 9847 SA2018 => SF ME 9/05, ME 31/10 2022_SE_09: vibration <10mn pour avoir 9846/7 en SO     ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688240261",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2024-09-23","23:17:00","2024-09-26","05:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h30 de sim. partielle déduite. sauf jours typé VE SA2018 => SF ME 9/05, ME 31/10 Modification le 05/02/2019 : inversion Heure Début PK Début et Heure Début PK Fin, et Heure Fin PK Début et Heure Fin PK Fin ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14886083461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00  ",null,null,null,null,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688242661",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-11","13:01:00","2024-12-13","13:19:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10700733",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688244261",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-11","13:46:00","2024-12-13","15:26:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10700732 2021_SE_106 + 2021_SE_107 + 2021_SE_108 + 2021_SE_109 + 2021_SE_110 + 2021_SE_111 : décalage de quelques minutes pour avoir 6615 en SO et 6617 en SF                                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688243461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-11","22:24:00","2024-12-12","06:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h26 de sim. partielle déduite. derrière 9847 SA2018 => SF ME 9/05, ME 31/10 2022_SE_09: vibration <10mn pour avoir 9846/7 en SO     ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688240261",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-11","23:17:00","2024-12-12","05:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h30 de sim. partielle déduite. sauf jours typé VE SA2018 => SF ME 9/05, ME 31/10 Modification le 05/02/2019 : inversion Heure Début PK Début et Heure Début PK Fin, et Heure Fin PK Début et Heure Fin PK Fin ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688246061",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,52,46,"2023-12-25","23:35:00","2024-11-11","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022   ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688247061",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,52,46,"2023-12-26","00:05:00","2024-11-12","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022 ",null,null,null,null,"High","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688241061",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-15","23:25:00","2024-12-13","05:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TGV ouvrant 6672 TGV fermant 999614 VE/SA + jours typé VE SA2018 => + ME 9/05 + ME 31/10       ",null,null,null,null,"Major","3,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688241861",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,50,"2023-12-15","22:55:00","2024-12-13","06:37:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TGV ouvrant 6635, TGV fermant 999611 VE/SA + jours typé VE SA2018 => + ME 9/05 + ME 31/10       ",null,null,null,null,"Major","3,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688250461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,15,49,"2024-04-13","23:05:00","2024-12-07","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable sa/di lorsque ne circule pas 9098 train ouvrant 9847 et 6442, train fermant 999614 ",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688252461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,49,49,"2023-12-10","23:55:00","2024-12-08","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable di/lu train ouvrant 6208, train fermant 999614 ",null,null,null,null,"Major","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688249461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,50,14,"2023-12-17","00:10:00","2024-04-07","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable sa/di lorsque circule 9098 avancé  train ouvrant 9098, train fermant 999614  ",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688250461",null,"< >","Pasilly - Poste 17","Mâcon-Loché-TGV - Bât Voyageurs",2024,2024,15,49,"2024-09-28","23:05:00","2024-09-28","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable sa/di lorsque ne circule pas 9098 train ouvrant 9847 et 6442, train fermant 999614 ",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688264261",null,"< >","Pasilly - Poste 17","Poste 19 Lacour-d'Arcenay",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard   Train ouvrant: 6676    train fermant: 999611   ",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688245061",null,"< >","Pasilly - Poste 17","Poste 19 Lacour-d'Arcenay",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard  Train ouvrant  6144, train fermant  999611",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688265261",null,"< >","Pasilly - Poste 17","Poste 19 Lacour-d'Arcenay",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14637203161",null,"< >","Pasilly - Poste 17","Poste 19 Lacour-d'Arcenay",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14600494561",null,"< >","Picon-Busserine","Picon-Busserine",2024,2024,4,9,"2024-01-22","23:00:00","2024-03-01","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx préparatoires et finitions du RAV MSC de 2024 de S04 DEF de 06h00 (yc S4 pose de LTV et S9 dépose de LTV) : L930 VA, VB/MV4 à VC/MV3, MV1+MV2 => Sr2 Km 1,060 , sur L830 D à J en passant pas C/D/E/F Circ. => jusqu'au Km 857,206(C723)/859,625 (Aig 102bV",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14863521761",null,"< >","Plombières - Evit Plombières","Dijon-Ville - Aiguilles Nord",2024,2024,11,11,"2024-03-17","05:00:00","2024-03-17","11:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ombre de la coupure de 24h     En simultanée avec 4C_DN_240",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14863542061",null,"< >","Plombières - Evit Plombières","Dijon-Ville - Aiguilles Nord",2024,2024,12,12,"2024-03-18","00:00:00","2024-03-18","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En simultanée avec 4C_DN_241",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14754012061",null,"< >","Plombières - Pt Changt Voie","Dijon-Ville - Aiguilles Nord",2024,2024,44,44,"2024-11-02","19:40:00","2024-11-02","13:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4C_DN_196  ",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14753922261",null,"< >","Plombières - Pt Changt Voie","Dijon-Ville - Aiguilles Nord",2024,2024,11,11,"2024-03-16","17:00:00","2024-03-16","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4C_DN_190",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338885561",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,28,35,"2024-07-08","22:25:00","2024-08-30","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338907561",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,28,35,"2024-07-08","22:25:00","2024-08-30","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338334161",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338321361",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338430561",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338423761",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338413761",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338888761",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,28,35,"2024-07-08","22:25:00","2024-08-30","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338846061",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,28,35,"2024-07-08","22:25:00","2024-08-30","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338195361",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703586861",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,2,50,"2024-01-08","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14345221361",null,"< >","Pontoise - Bât Voyageurs","Pontoise - Bât Voyageurs",2024,2024,51,36,"2023-12-19","01:45:00","2024-09-07","04:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703648061",null,"< >","Pontoise - Bif de Liesse","Pontoise - Bif de Liesse",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703646061",null,"< >","Pontoise - Bif de Liesse","Pontoise - Bif de Liesse",2024,2024,50,50,"2023-12-12","01:30:00","2024-12-14","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703644061",null,"< >","Pontoise - Bif de Liesse","Pontoise - Bât Voyageurs",2024,2024,50,50,"2023-12-12","00:00:00","2024-12-14","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689917461",null,"< >","Port-Sec-de-Pacy","Aisy - Rac LGV",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance IHM 1 ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689920461",null,"< >","Port-Sec-de-Pacy","Aisy - Rac LGV",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689918461",null,"< >","Port-Sec-de-Pacy","Aisy - Rac LGV",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage modifiée le 01/12/2022 suite report de la MES",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13884171661",null,"< >","Port-Sec-de-Pacy","Aisy - Rac LGV",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MES LGV+",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14657670361",null,"< >","Poste 14 Vaumort","Pasilly - Km 160,2",2024,2024,14,15,"2024-04-07","23:55:00","2024-04-14","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA23_0024712, zone st florentin vergigny, postes 15 et 16   Train ouvrant 6442  ",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688331461",null,"< >","Poste 14 Vaumort","Pasilly - Km 160,2",2024,2024,14,37,"2024-04-06","23:30:00","2024-09-14","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA23_0024712, zone st florentin vergigny, postes 15 et 16   Train ouvrant 9784   ",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688437261",null,"< >","Poste 14 Vaumort","Poste 15 Vergigny",2024,2024,14,37,"2024-04-06","23:30:00","2024-09-14","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA23_0024712, zone st florentin vergigny, postes 15 à 16    Train ouvrant le 9784",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14657634061",null,"< >","Poste 14 Vaumort","Poste 15 Vergigny",2024,2024,14,15,"2024-04-07","23:55:00","2024-04-14","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA23_0024712, zone st florentin vergigny, postes 15 à 16    Train ouvrant le 6442",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688297861",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-11","13:11:00","2024-12-13","14:01:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10700733",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688296261",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-11","13:35:00","2024-12-13","14:44:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10700732 2021_SE_106 + 2021_SE_107 + 2021_SE_108 + 2021_SE_109 + 2021_SE_110 + 2021_SE_111 : décalage de quelques minutes pour avoir 6615 en SO et 6617 en SF                                           ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688307461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,52,46,"2023-12-26","00:15:00","2024-11-12","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022                   ",null,null,null,null,"High","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688295461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-11","22:50:00","2024-12-12","06:07:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"5h52 de sim. partielle déduite. derrière 6635 les VE/SA SA2018 => VE/SA non activé du début du service au 30/03 pour circulation de l'Eurostar 9097                     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688306461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,52,46,"2023-12-25","22:50:00","2024-11-11","05:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022                   ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688299461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-11","23:10:00","2024-12-12","05:57:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"sauf jours typé VE SA2018 => SF ME 9/05, ME 31/10 Modification le 05/02/2019 : inversion Heure Début PK Début et Heure Début PK Fin",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688295461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2024-04-12","22:50:00","2024-12-13","06:07:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"5h52 de sim. partielle déduite. derrière 6635 les VE/SA SA2018 => VE/SA non activé du début du service au 30/03 pour circulation de l'Eurostar 9097                     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688298661",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-15","23:30:00","2024-12-13","05:57:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TGV ouvrant 6672 VE/SA + jours typé VE SA2018 => + ME 9/05 + ME 31/10                       ",null,null,null,null,"Major","3,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688308461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,14,"2023-12-17","00:20:00","2024-04-07","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TGV ouvrant 9098 avancé train fermant 999611 retardé +15'                   ",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688311461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,50,"2023-12-11","00:10:00","2024-12-09","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable di/lu train ouvrant 6208 train fermant 999611 retardé +15                   ",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688297061",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,50,14,"2023-12-15","23:57:00","2024-04-05","06:07:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"sim. partielle déduite. SA2018 => VE/SA activé du début du service au 30/03 pour circulation de l'Eurostar 9097/6                     ",null,null,null,null,"High","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688309461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,15,49,"2024-04-13","23:10:00","2024-12-07","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable sa/di lorsque circule ne circule ni 6442 ni 9098. train ouvrant 9784 jusqu'au 999611 + 15                               ",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688305461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00                             ",null,null,null,null,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688320661",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard   Train ouvrant: 6676    train fermant: 999611  ",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688321661",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14636816861",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard.",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688304461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard  Train ouvrant  6144, train fermant  999611",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688309461",null,"< >","Poste 14 Vaumort","Poste 18 Toutry",2024,2024,15,49,"2024-09-28","23:10:00","2024-09-28","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable sa/di lorsque circule ne circule ni 6442 ni 9098. train ouvrant 9784 jusqu'au 999611 + 15                               ",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14995298761",null,"< >","Poste 27 Cesseins","Miribel-LGV",2024,2024,3,13,"2024-01-19","23:55:00","2024-03-29","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage pour le CHA20-0018098, essais avec l'infrapôle Rhodanien  Toutes les ZEP du poste 40  TO 6635, TF 999614            ",null,null,null,null,"High","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14995157061",null,"< >","Poste 27 Cesseins","Miribel-LGV",2024,2024,3,13,"2024-01-15","23:30:00","2024-03-28","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage pour le CHA20-0018098, essais avec l'infrapôle Rhodanien  Toutes les ZEP du poste 40  TO 9847, TF 999614            ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14640921261",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard  Maintenance IHM1",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641724661",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard  Maintenance IHM1",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14641059261",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard  Maintenance IHM1",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13884217661",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,45,45,"2024-11-10","23:10:00","2024-11-10","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MES LGV+",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14472142061",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,43,43,"2024-10-21","09:45:00","2024-10-25","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689955461",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage modifiée le 01/12/2022 suite report de la MES.",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14011324961",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,15,16,"2024-04-13","00:05:00","2024-04-20","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prépa MES LGV+",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14011795461",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,15,16,"2024-04-13","23:30:00","2024-04-21","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prépa MES LGV+",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14448448461",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,6,6,"2024-02-05","09:10:00","2024-02-08","15:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4D_AIY-LLA_014   Voie 1",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14448496861",null,"< >","Poste 30 Étivey - Km 8,3","Montbard - Bât Voyageurs",2024,2024,9,10,"2024-02-26","10:40:00","2024-03-05","16:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"En complément de la 4D_AIY-LLA_017  Voie 1",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14629096761",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 44 Grenay - Transition TVM",2024,2024,3,5,"2024-01-20","00:15:00","2024-02-03","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage créée pour le CHA20_0018098, essai de poste à poste avec l'infrapôle Rhodanien  Toute la zone du poste 44 de Grenay est concernée  Plage sans impact pour les circulations.",null,null,null,null,"Medium","5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688214061",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,50,"2023-12-15","23:47:00","2024-12-13","06:18:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"5h20 de sim. partielle déduite. Pour SA2018 => VE/SA + jours typés VE : + ME 9/05 + ME 31/10  derrière le 5137 en DI     ",null,null,null,null,"Major","3,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688212461",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,50,"2023-12-15","23:12:00","2024-12-13","04:48:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification main courante majeure MC565 SA2018 => + ME 9/05 + ME 31/10              ",null,null,null,null,"Major","3,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688218061",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,49,"2023-12-16","23:00:00","2024-12-07","05:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ouvrant 6131, fermant 999603 ",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688219061",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,49,49,"2023-12-10","23:50:00","2024-12-08","05:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ouvrant 6137, fermant 999600  ",null,null,null,null,"Major","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14886336461",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00",null,null,null,null,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688215661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,50,"2023-12-11","22:36:00","2024-12-09","06:19:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h25 de sim. partielle déduite. Pour SA2018 => LU/MA + jours typés LU : MA/ME 26-27/12, MA/ME 02-03/01, MA/ME 03-04/04, ME/JE 02-03/05, MA/ME 22-23/05     ",null,null,null,null,"Major","1,2,3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688211661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,50,"2023-12-12","22:24:00","2024-12-12","06:18:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h36 de sim. partielle déduite. Sauf jours particulier TGV typé LU VE SA2018 => SF ME 9/05, ME 31/10 MA/ME 26-27/12, MA/ME 02-03/01, MA/ME 03-04/04, ME/JE 02-03/05, MA/ME 22-23/05   ",null,null,null,null,"Major","2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688216461",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,52,46,"2023-12-25","23:50:00","2024-11-11","05:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Variante Gen pour VF,F et LDF         ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688210861",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,50,50,"2023-12-11","22:00:00","2024-12-12","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"6h32 de sim. partielle déduite. Sauf jours typés VE sur le calendrier TGV SA2018 => SF ME 9/05 + ME 31/10         ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688217261",null,"< >","Poste 44 Grenay - Bif de Grenoble","Poste 52 Upie",2024,2024,52,46,"2023-12-25","23:05:00","2024-11-11","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Variante Gen pour VF,F et LDF         ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688220861",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-09-02","21:05:00","2024-10-24","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V2 en grand lu/ma à je/ve, la prise de cette DEF rend applicable DEF24_GNA-VXN_007 lu/ma ou DEF24_GNA-VXN_008 ma/me à je/ve sur V1  V2 derrière 6260 jusqu'au 999600 +10   Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688221661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-09-02","22:45:00","2024-10-21","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand lu/ma et jours en lu/ma  (en raison du 6131 circulant dans sa variante du lundi)  CHA24_0026280:   Cas V2 sim lu/ma lorsque DEF24_GNA-VXN_005 est prise sur V1  Cas V1 sim lu/ma lorsque DEF24_GNA-VXN_006 est prise sur V2  CHA24_002",null,null,null,null,"Major","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688222661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-09-03","22:35:00","2024-10-24","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand ma/me à je/ve  CHA24_0026280:   Cas V2 sim ma/me à je/ve lorsque DEF24_GNA-VXN_005 est prise sur V1  Cas V1 sim ma/me à je/ve lorsque DEF24_GNA-VXN_006 est prise sur V2  CHA24_0026378:   Cas V2 sim ma/me à je/ve lorsque DEF24_GNA-",null,null,null,null,"Major","2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14976483561",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,36,43,"2024-09-02","21:20:00","2024-10-24","06:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_GNA-VXN_007 lu/ma ou DEF24_GNA_VXN_008 du ma/me à je/ve  sur V2   V1 derrière 6225  jusqu'au 999603 + 25 minutes  Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571 + 745 + 4771 + ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688223661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,26,"2024-01-12","21:50:00","2024-06-28","06:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_GNA-VXN_011 le ve/sa  sur V2   V1 derrière 6129 et 6953  jusqu'au 999603 + 25 minutes  Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571 + 745 + 4771 + 747    Consignation C: Sr G",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688224461",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,26,"2024-01-12","22:05:00","2024-06-28","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V2 en grand rend applicable DEF24_GNA-VXN_011 le ve/sa sur V1   V2 derrière 6206 jusqu'au 999600 + 10     Zeps V2: 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 + 4472 + 4474 + 843   Consignation C: Sr Grenay DV2 + SEL 1002 Sr ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688225261",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,26,"2024-01-12","23:50:00","2024-06-28","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand le ve/sa   Cas V2 sim ve/sa lorsque DEF24_GNA-VXN_009 est prise sur V1   Cas V1 sim ve/sa lorsque DEF24_GNA-VXN_010 est prise sur V2  Derrière 6137  jusqu'au  999603 + 25 minutes ou 999600 + 10   Zeps V1:  743 + 4471 + 4473 + 4475",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688226261",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,14,21,"2024-04-01","22:45:00","2024-05-20","06:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas voie 1 en Grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05, rend applicable en sim DEF24_GNA-VXN_014    V1 derrière 6131  jusqu'au 999603 + 25  Zeps V1 : 743 + 4471 + 4473 + 4475 + ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14409893561",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,14,21,"2024-04-01","23:50:00","2024-05-20","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05   Cas V2 sim ve/sa lorsque DEF24_GNA-VXN_012 est prise sur V1   Cas V1 sim ve/sa lorsque DEF24_GNA-VXN_013 est prise sur V2  Derrière 6137  jus",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688221661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-01-08","22:45:00","2024-06-24","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand lu/ma et jours en lu/ma  (en raison du 6131 circulant dans sa variante du lundi)  CHA24_0026280:   Cas V2 sim lu/ma lorsque DEF24_GNA-VXN_005 est prise sur V1  Cas V1 sim lu/ma lorsque DEF24_GNA-VXN_006 est prise sur V2  CHA24_002",null,null,null,null,"Major","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688220861",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-01-08","21:05:00","2024-06-27","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V2 en grand lu/ma à je/ve, la prise de cette DEF rend applicable DEF24_GNA-VXN_007 lu/ma ou DEF24_GNA-VXN_008 ma/me à je/ve sur V1  V2 derrière 6260 jusqu'au 999600 +10   Zeps V2 : 847 + 4772 + 4774 + 845 + 4572 + 4574 + 844 ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688220061",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,26,"2024-01-08","20:55:00","2024-06-27","06:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas V1 en grand rend applicable en sim DEF24_GNA-VXN_007 lu/ma ou DEF24_GNA_VXN_008 du ma/me à je/ve  sur V2   V1 derrière 6225 moins 25 minutes jusqu'au 999603 + 25 minutes  Zeps V1 : 743 + 4471 + 4473 + 4475 + 4477 + 744 + 4571",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688227061",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,14,21,"2024-04-01","22:50:00","2024-05-20","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand, cas voie 2 en Grand le LU/MA 01-02/04, ME/JE 08-09/05, JE/VE 09-10/05, VE/SA 10-11/05 et le LU/MA 20-21/05, rend applicable en sim DEF24_GNA-VXN_014   V2 derrière 6206 jusqu'au 999600 + 10    Zeps V2: 847 + 4772 + 4774 + 845 + 45",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688222661",null,"< >","Poste 44 Grenay - Bif de Grenoble","Claveyson-Bren",2024,2024,2,43,"2024-01-09","22:35:00","2024-06-27","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Notion V1 ou V2 en grand ma/me à je/ve  CHA24_0026280:   Cas V2 sim ma/me à je/ve lorsque DEF24_GNA-VXN_005 est prise sur V1  Cas V1 sim ma/me à je/ve lorsque DEF24_GNA-VXN_006 est prise sur V2  CHA24_0026378:   Cas V2 sim ma/me à je/ve lorsque DEF24_GNA-",null,null,null,null,"Major","2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688213261",null,"< >","Poste 44 Grenay - Bif de Lyon","Valence-TGV - Bif de Valence",2024,2024,50,50,"2023-12-11","14:50:00","2024-12-13","16:09:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10701426",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688214861",null,"< >","Poste 44 Grenay - Bif de Lyon","Valence-TGV - Bif de Valence",2024,2024,50,50,"2023-12-11","12:07:00","2024-12-13","12:46:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10701429",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688339061",null,"< >","Poste 56 Lapalud - Rac d'Avignon","Poste 61 Roquemaure",2024,2024,50,50,"2023-12-11","15:33:00","2024-12-13","16:42:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10701436",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688338261",null,"< >","Poste 56 Lapalud - Rac d'Avignon","Poste 61 Roquemaure",2024,2024,50,50,"2023-12-11","11:23:00","2024-12-13","12:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10701439 2021_SE_48 : décalage de -5mn pour avoir 9710 en SF, le 19/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14705167261",null,"< >","Poste 66 Crisenoy","Poste 11 Le ChÃ¢telet",2024,2024,16,40,"2024-04-15","00:00:00","2024-09-30","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour  le CHA23-0024712 (PSE)   Zone du Poste 66 Crisenoy, TO 6928                             ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14704969461",null,"< >","Poste 66 Crisenoy","Poste 11 Le ChÃ¢telet",2024,2024,15,39,"2024-04-12","23:55:00","2024-09-27","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour  le CHA23-0024712 (PSE)   Zone du Poste 66 Crisenoy, TO 6676                             ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14705160661",null,"< >","Poste 66 Crisenoy","Poste 11 Le ChÃ¢telet",2024,2024,15,39,"2024-04-13","23:45:00","2024-09-28","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour  le CHA23-0024712 (PSE)   Zone du Poste 66 Crisenoy, TO 6442                             ",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688403261",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2024-09-16","22:30:00","2024-09-19","05:33:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"5h10 de sim. partielle déduite. SA2018 => VE/SA non activé du début du service au 30/03 pour circulation de l'Eurostar 9097 => Variante plus courte FEN17 Crisnoy-Vergigny 005 s'applique       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688406461",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2024-09-16","23:37:00","2024-09-19","05:37:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"5h20 de sim. partielle déduite. SA2018 => SF ME 9/05, ME 31/10 Modification le 05/02/2019 : inversion Heure Début PK Début et Heure Début PK Fin, et Heure Fin PK Début et Heure Fin PK Fin   ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688424061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard  Train ouvrant  6144, train fermant  999611",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688423061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,10,21,"2024-03-08","23:55:00","2024-05-24","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard  Train ouvrant le 6676 et  train fermant le 999611",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688420061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,10,21,"2024-03-09","23:30:00","2024-05-25","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0027102, préparation mise en service du PAI Nuits Aisy Montbard  Train ouvrant  6144, train fermant  999611",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688421061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,27,27,"2024-07-01","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"                                 ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688416061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,2,49,"2024-09-28","23:30:00","2024-09-28","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour le CHA20-0018098 LGV + et le CHA23-0024712 (PSE)  après 9784 jusqu'au 999611 +  15                             ",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688403261",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2024-04-12","22:30:00","2024-12-13","05:33:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"5h10 de sim. partielle déduite. SA2018 => VE/SA non activé du début du service au 30/03 pour circulation de l'Eurostar 9097 => Variante plus courte FEN17 Crisnoy-Vergigny 005 s'applique       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688407261",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,14,"2023-12-15","23:36:00","2024-04-05","05:54:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"5h10 de sim. partielle déduite. sim. partielle déduite. SA2018 => VE/SA activé du début du service au 30/03 pour circulation de l'Eurostar 9097/6                     ",null,null,null,null,"High","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688404061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2023-12-15","23:50:00","2024-12-13","05:37:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TGV ouvrant 6672 ",null,null,null,null,"Major","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688416061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,2,49,"2024-04-13","23:30:00","2024-12-07","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour le CHA20-0018098 LGV + et le CHA23-0024712 (PSE)  après 9784 jusqu'au 999611 +  15                             ",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688418061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2023-12-11","00:10:00","2024-12-09","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour le CHA20-0018098 LGV + et le CHA23-0024712 (PSE) après 6144 jusqu'au 999611 retardé +15'                             ",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688415061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,14,"2023-12-17","00:45:00","2024-04-07","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"applicable lorsque circule 9098  9098 avancé ouvrant, 999611 retardé + 15 fermant                          ",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688406461",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2023-12-11","23:37:00","2024-12-12","05:37:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"5h20 de sim. partielle déduite. SA2018 => SF ME 9/05, ME 31/10 Modification le 05/02/2019 : inversion Heure Début PK Début et Heure Début PK Fin, et Heure Fin PK Début et Heure Fin PK Fin   ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688413461",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,52,46,"2023-12-25","22:40:00","2024-11-11","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022                     ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688414261",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,52,46,"2023-12-26","00:35:00","2024-11-12","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"fenêtre applicable les VF, F et LDF selon calendrier Voyages 2022                     ",null,null,null,null,"High","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688403261",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2023-12-11","22:30:00","2024-12-12","05:33:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"5h10 de sim. partielle déduite. SA2018 => VE/SA non activé du début du service au 30/03 pour circulation de l'Eurostar 9097 => Variante plus courte FEN17 Crisnoy-Vergigny 005 s'applique       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688418061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,50,50,"2024-01-15","00:10:00","2024-01-22","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour le CHA20-0018098 LGV + et le CHA23-0024712 (PSE) après 6144 jusqu'au 999611 retardé +15'                             ",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688416061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,2,49,"2024-01-13","23:30:00","2024-01-20","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour le CHA20-0018098 LGV + et le CHA23-0024712 (PSE)  après 9784 jusqu'au 999611 +  15                             ",null,null,null,null,"Major","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688422061",null,"< >","Poste 66 Crisenoy","Poste 15 Vergigny",2024,2024,45,46,"2024-11-08","23:00:00","2024-11-13","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Plage pour le CHA24-0026458 pour la mise en service de projet LGV+  Fermeture en continue du Vendredi 08/11 à 23h jusqu'au Mercredi 13/11/24 à 4h00",null,null,null,null,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688436261",null,"< >","Poste 66 Crisenoy - Bif","Poste 14 Vaumort",2024,2024,2,3,"2024-01-12","23:50:00","2024-01-19","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pour  le CHA23-0024712 (PSE)   après 6672 jusqu'au 999611                              ",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688404861",null,"< >","Poste 66 Crisenoy - Bif","Poste 15 Vergigny",2024,2024,50,50,"2023-12-11","13:13:00","2024-12-13","14:32:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10700732 2021_SE_106 + 2021_SE_107 + 2021_SE_108 + 2021_SE_109 + 2021_SE_110 + 2021_SE_111 : décalage de quelques minutes pour avoir 6615 en SO et 6617 en SF                                                             ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688405661",null,"< >","Poste 66 Crisenoy - Bif","Poste 15 Vergigny",2024,2024,50,50,"2023-12-11","13:34:00","2024-12-13","14:11:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10700733",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687470661",null,"< >","Rassuen","Fos-sur-Mer - ITE Lafarge",2024,2024,15,17,"2024-04-08","22:30:00","2024-04-28","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES Voie Avignon, CAP 6H V2 LVU PRA LAVALDUC coté PdB, à prendre avec 4F_MAS-LVU_001 et 4C_LVU_005   Domaine S9 : ZEP 2+4+6+8+10          ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14535938661",null,"< >","Rassuen","Lavalduc - Bif RN Poste",2024,2024,15,16,"2024-04-08","22:30:00","2024-04-21","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP SES AVI :  V2Bis avec Générique de nuit   Doamine S9 : ZEPG à LVU sur les deux semaines soit : ZEP 1+10+30 ou ZEP 6+7+8+9+13+24+26 ou ZEP 2+4+11",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672977461",null,"< >","Romilly-sur-Seine - Bât Voyageurs","Troyes - Aig Ouest-V C",2024,2024,50,50,"2023-12-11","12:40:00","2024-12-13","13:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13672975061",null,"< >","Romilly-sur-Seine - Bât Voyageurs","Troyes - Aig Ouest-V C",2024,2024,50,50,"2023-12-11","11:12:00","2024-12-13","12:28:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14696449561",null,"< >","Salon","Miramas - Bât Voyageurs",2024,2024,9,11,"2024-02-26","11:35:00","2024-03-15","13:44:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, Maint, de 11h35 à 13h44, V1S+V2S+1Racct+2Racct, entre les circulaztions de l'ITE SMEA :  Etendue S9 : V1S du C507 Km 66,880 au JI Z605/617 Km 68,130 / V2 de la PATC Km 65,976 au C607 Km 67,860 /Racct 1 de l'Aig 505 Km au C420 Km ,595  /Racct 2 de ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14696432461",null,"< >","Salon","Miramas - Bât Voyageurs",2024,2024,17,48,"2024-04-27","22:10:00","2024-11-30","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, Maint, DEF 08h00, L925 V1+V2+V1S+V2S+1Racct+2Racct, du Sa 22h10 au Di 06h10 (du 30/03 au 31/03 + 23/11 au 24/11 + 30/11 au 01/12 ) :  Etendue S9 : V1 de la PATC de CAV Km 38,695 au C507 Km 66,880 jusqu'au JI Z605/617 Km 68,130 (V1S) / V2 du C24 de",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","16633986861",null,"< >","Salon","Miramas - Bât Voyageurs",2024,2024,38,41,"2024-09-16","09:55:00","2024-10-11","17:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx Prépa/Confortatifs ou Principaux 07h20 -Miramas inclus à Cavaillon exclu - S37+S38(Prépa/Conf.) et S39 LU+MA (Ppx)+S40 JE+VE (Ppx)+S41(Ppx)+S42(finitions)+43 (finitions)- :  Etendue S9 : V1 de la PATC Km 38,695 au C507 au Km 66,880 => JI Z 605/617 km ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14646586861",null,"< >","Salon","Miramas - Bât Voyageurs",2024,2024,37,43,"2024-09-09","09:55:00","2024-10-25","17:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tvx Prépa/Confortatifs ou Principaux 07h20 -Miramas inclus à Cavaillon exclu - S37+S38(Prépa/Conf.) et S39 LU+MA (Ppx)+S40 JE+VE (Ppx)+S41(Ppx)+S42(finitions)+43 (finitions)- :  Etendue S9 : V1 de la PATC Km 38,695 au C507 au Km 66,880 => JI Z 605/617 km ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14570436061",null,"< >","Salon","Miramas - Bât Voyageurs",2024,2024,24,24,"2024-06-15","17:00:00","2024-06-15","11:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, CCR OP1, OCP 4 V1S+V2S+1Racct+2Racct, OCP4 18h du Sa 17h00 au Di 11h00 (du 15/06 au 16/06), pendant la fermeture ITE SMEA :  Etendue S9 : V1S du C507 Km 66,880 au JI Z605/617 Km 68,130 / V2 de la PATC Km 65,976 au C607 Km 67,860 /Racct 1 de l'Aig ",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14542959461",null,"< >","Salon","Miramas - V 3 garage",2024,2024,21,40,"2024-05-25","23:00:00","2024-10-05","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, UP Voie SES Avi, OCP 7h00 We SA/DI cause Ite SMEA :   Etendue S9 : L925 : V1S du C507 Km 66,880 au Cv 514 Km 67,231 / V2S de la PATC km 65,976 au JI Z506/512 Km 67,200 / V3G de la Butte Km 67,174 au Cv 504 Km 67,259  Domaine S9 : ZEPG 96+158+160+1",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14571039661",null,"< >","Salon","Miramas - ITE ZRA ETAMAT",2024,2024,24,24,"2024-06-15","17:00:00","2024-06-15","11:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2024, CCR OP1, OCP 4 V1S+V2S+1Racct+2Racct, OCP4 18h du Sa 17h00 au Di 11h00 (du 01/06 au 02/06) :  Etendue S9 : V1S du C507 Km 66,880 au JI Z605/617 Km 68,130 / V2 de la PATC Km 65,976 au C607 Km 67,860 /Racct 1 de l'Aig 505 Km au C420 Km ,595  /Racct ",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689816861",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-03-11","09:45:00","2024-10-18","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15196873161",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,10,13,"2024-03-04","08:00:00","2024-03-22","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15196897061",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,10,13,"2024-03-04","10:00:00","2024-03-22","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec le 1610",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689815261",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-03-11","08:45:00","2024-10-18","14:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15867245361",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,38,38,"2024-09-16","22:00:00","2024-09-19","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689816061",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-10-14","08:45:00","2024-10-18","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689814461",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-10-14","10:00:00","2024-10-18","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15867293561",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,38,42,"2024-09-22","22:00:00","2024-10-20","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689816861",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-01-29","09:45:00","2024-10-20","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15196873161",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,10,13,"2024-03-04","08:00:00","2024-03-31","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689815261",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-20","14:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15196897061",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,10,13,"2024-03-04","10:00:00","2024-03-31","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec le 1610",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689816061",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-20","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689814461",null,"< >","Sens - Poste 1","Sens - ITE ZI",2024,2024,5,42,"2024-01-29","10:00:00","2024-10-20","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15236674761",null,"< >","Sens - Poste 2","Sens - ITE ZI",2024,2024,38,38,"2024-09-16","23:00:00","2024-09-19","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14687105161",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","10:00:00","2024-03-29","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14687095061",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","08:00:00","2024-03-29","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15200936961",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,11,11,"2024-03-16","08:55:00","2024-03-17","16:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14687118361",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,11,12,"2024-03-16","08:55:00","2024-03-18","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15200952361",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,11,11,"2024-03-17","19:10:00","2024-03-17","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689801861",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,50,44,"2023-12-11","02:32:00","2024-11-03","05:47:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 => 1 voie dans chaque sens Modification le 05/02/2019 : Typologie passée de Jour à Nuit non passe-minuit",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689797861",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,51,45,"2023-12-18","02:32:00","2024-11-10","05:47:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 => 1 voie dans chaque sens Modification le 05/02/2019 : Typologie passée de Jour à Nuit non passe-minuit",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689800261",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,52,50,"2023-12-26","08:51:00","2024-12-13","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prise de voie V1   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689798661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,50,49,"2023-12-11","08:51:00","2024-12-08","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prise de voie V1bis ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689803461",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-20","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689809261",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,20,43,"2024-05-19","23:00:00","2024-10-26","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14687105161",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","10:00:00","2024-03-31","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689807661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,19,48,"2024-05-12","23:00:00","2024-11-29","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689802661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-01-29","10:00:00","2024-10-20","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14687095061",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","08:00:00","2024-03-31","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689806861",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,16,16,"2024-04-15","09:30:00","2024-04-21","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Besoins Caténaires : - Secteur Laroche Voie de service Impair - Secteur Cezy Laroche voie 1bis   Besoins ZEP : - Toutes les ZEP du faisceau Bourgogne Impair et Accès  - Toutes les ZEP du faisceau de Préblin + ZEP 481 et Accès par bourgogne faisceau impair",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15202273861",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,33,49,"2024-08-12","10:00:00","2024-12-06","16:31:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689803461",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-09-09","08:45:00","2024-10-18","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15645800061",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,38,45,"2024-09-16","10:00:00","2024-11-08","16:31:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689802661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-09-09","10:00:00","2024-10-18","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689806861",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,16,16,"2024-04-15","09:30:00","2024-04-19","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Besoins Caténaires : - Secteur Laroche Voie de service Impair - Secteur Cezy Laroche voie 1bis   Besoins ZEP : - Toutes les ZEP du faisceau Bourgogne Impair et Accès  - Toutes les ZEP du faisceau de Préblin + ZEP 481 et Accès par bourgogne faisceau impair",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689798661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,50,49,"2024-04-22","08:51:00","2024-04-26","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prise de voie V1bis ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14687095061",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","08:00:00","2024-03-22","16:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14687105161",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,10,13,"2024-03-04","10:00:00","2024-03-22","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689800261",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,52,50,"2024-01-22","08:51:00","2024-02-23","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prise de voie V1   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689803461",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-18","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689802661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,5,42,"2024-01-29","10:00:00","2024-10-18","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689807661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,19,48,"2024-09-16","23:00:00","2024-09-19","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689798661",null,"< >","Sens - Poste 2","Laroche-Migennes - Carré Violet 12",2024,2024,50,49,"2024-05-06","08:51:00","2024-07-14","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prise de voie V1bis ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689799461",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,51,45,"2023-12-18","00:37:00","2024-11-10","03:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 => 1 voie dans chaque sens Modification le 05/02/2019 : Typologie passée de Jour à Nuit non passe-minuit",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689797061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,50,50,"2023-12-11","08:51:00","2024-12-13","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prise de voie V2bis ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689804261",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-20","14:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689810061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,20,43,"2024-05-19","22:00:00","2024-10-26","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689806061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,17,17,"2024-04-22","09:30:00","2024-04-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Besoins Caténaires : - Secteur Laroche Voie de service Pair - Secteur Laroche Cezy voie 2bis - Sel 2320 bis du Secteur Laroche St Florentin Voie 2bis (Voie 2 Racco) - Sel 2321bis +131 du Secteur  Laroche St Florentin Voie 1bis (Voie 1 Racco + Voie A Racco",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15201970961",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,38,45,"2024-09-21","01:00:00","2024-11-04","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689804261",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,5,42,"2024-09-09","08:45:00","2024-10-18","14:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15652881061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,33,49,"2024-08-18","22:00:00","2024-12-08","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689804261",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,5,42,"2024-01-29","08:45:00","2024-10-18","14:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689806061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,17,17,"2024-04-22","09:30:00","2024-04-26","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Besoins Caténaires : - Secteur Laroche Voie de service Pair - Secteur Laroche Cezy voie 2bis - Sel 2320 bis du Secteur Laroche St Florentin Voie 2bis (Voie 2 Racco) - Sel 2321bis +131 du Secteur  Laroche St Florentin Voie 1bis (Voie 1 Racco + Voie A Racco",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15238035061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,4,8,"2024-01-22","10:45:00","2024-02-23","11:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15238038761",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,4,8,"2024-01-22","12:45:00","2024-02-23","13:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15201970961",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,38,45,"2024-09-21","01:00:00","2024-10-21","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689797061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,50,50,"2024-04-15","08:51:00","2024-04-19","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prise de voie V2bis ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689797061",null,"< >","Sens - Poste 2","Laroche-Migennes - FSC Bercy",2024,2024,50,50,"2024-05-06","08:51:00","2024-07-14","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prise de voie V2bis ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689801061",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,50,44,"2023-12-11","00:37:00","2024-11-03","03:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 => 1 voie dans chaque sens Modification le 05/02/2019 : Typologie passée de Jour à Nuit non passe-minuit ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689810861",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,5,42,"2024-01-29","09:45:00","2024-10-20","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689796261",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,52,30,"2023-12-26","08:51:00","2024-07-28","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prise de voie V2   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689808461",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,19,48,"2024-05-12","22:00:00","2024-11-29","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15202008861",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,38,45,"2024-09-21","07:00:00","2024-11-04","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15652915361",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,34,50,"2024-08-19","00:50:00","2024-12-09","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689810861",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,5,42,"2024-09-09","09:45:00","2024-10-18","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15652335461",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,46,46,"2024-11-11","00:50:00","2024-11-11","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689810861",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,5,42,"2024-01-29","09:45:00","2024-10-18","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689796261",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,52,30,"2024-01-22","08:51:00","2024-02-23","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Prise de voie V2   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689808461",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,19,48,"2024-09-16","22:00:00","2024-09-19","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15202008861",null,"< >","Sens - Poste 2","Laroche-Migennes - Poste 1",2024,2024,38,45,"2024-09-21","07:00:00","2024-10-21","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14958206361",null,"< >","Séon-St-Henry","St-Louis-les-Aygalades - Km 857,206",2024,2024,8,11,"2024-02-24","01:00:00","2024-03-16","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"LNPCA - Marseille Nord (St Louis les Aygualades) L830 tunnel Delorme, nuit courte VE/SA (SA) :  Domaine S9 : M1 ZEP 5111 (du C716 Km 855,709 au C723 Km 856,633) et M2 ZEP 5110 (du C714 Km 855,709 au C721 Km 856,633)  Domaine S11 : M1 Sél 2915 (du Km 854,4",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14958157661",null,"< >","Séon-St-Henry","St-Louis-les-Aygalades - Km 857,206",2024,2024,8,11,"2024-02-20","00:05:00","2024-03-15","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"LNPCA - Marseille Nord (St Louis les Aygualades) L830 tunnel Delorme :  Domaine S9 : M1 ZEP 5111 (du C716 Km 855,709 au C723 Km 856,633) et M2 ZEP 5110 (du C714 Km 855,709 au C721 Km 856,633)  Domaine S11 : M1 Sél 2915 (du Km 854,422 au Km 856,868) et M2 ",null,null,null,null,"High","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13665563561",null,"< >","Serqueux - CV9105","Serqueux - C9144",2024,2024,3,50,"2024-03-04","13:11:00","2024-11-29","17:11:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13665563561",null,"< >","Serqueux - CV9105","Serqueux - C9144",2024,2024,3,50,"2024-01-15","13:11:00","2024-12-10","17:11:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13665563561",null,"< >","Serqueux - CV9105","Serqueux - C9144",2024,2024,3,50,"2024-02-05","13:11:00","2024-11-24","17:11:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703676461",null,"< >","Stade-de-France-St-Denis","St-Denis - Pk 6,8",2024,2024,50,50,"2023-12-11","00:30:00","2024-12-14","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703678061",null,"< >","Stade-de-France-St-Denis","St-Denis - Pk 6,8",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703678061",null,"< >","Stade-de-France-St-Denis","St-Denis - Pk 6,8",2024,2024,1,50,"2024-01-08","23:35:00","2024-01-28","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13576554061",null,"< >","St-Benoît (Vienne) - Bât Voyageurs","Coulombiers - Bif Coulombiers",2024,2024,50,50,"2023-12-11","12:40:00","2024-12-13","13:47:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en qualité Refonte 2022                                ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13576553261",null,"< >","St-Benoît (Vienne) - Bât Voyageurs","Coulombiers - Bif Coulombiers",2024,2024,50,50,"2023-12-11","10:30:00","2024-12-13","11:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en qualité Refonte 2022                          ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13576555661",null,"< >","St-Benoît (Vienne) - Bât Voyageurs","Coulombiers - Bif Coulombiers",2024,2024,50,45,"2023-12-11","23:50:00","2024-11-07","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en qualité Refonte 2022                                                              ",null,null,null,null,"Major","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13576554861",null,"< >","St-Benoît (Vienne) - Bât Voyageurs","Coulombiers - Bif Coulombiers",2024,2024,50,45,"2023-12-11","23:00:00","2024-11-07","04:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"                                             ",null,null,null,null,"Major","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703673861",null,"< >","St-Denis - Garages Impairs","St-Denis - Pk 6,8",2024,2024,50,50,"2023-12-11","00:35:00","2024-12-14","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703675661",null,"< >","St-Denis - Garages Impairs","St-Denis - Pk 6,8",2024,2024,50,50,"2023-12-11","01:00:00","2024-12-14","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703679061",null,"< >","St-Denis - Garages Impairs","St-Denis - Pk 6,8",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13875734061",null,"< >","St-Denis - Garages Impairs","St-Denis - Pk 6,8",2024,2024,1,49,"2024-01-02","10:10:00","2024-12-06","12:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"maintenance de jour DV/RV",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14329448361",null,"< >","St-Denis - Pk 6,8","La Barre-Ormesson",2024,2024,38,39,"2024-09-20","23:35:00","2024-09-27","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14869513161",null,"< >","St-Denis - Pk 6,8","La Barre-Ormesson",2024,2024,38,40,"2024-09-22","01:30:00","2024-09-30","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14630498761",null,"< >","St-Denis - Pk 6,8","La Barre-Ormesson",2024,2024,23,24,"2024-06-07","23:35:00","2024-06-10","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14552340761",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","St-Florentin-Vergigny - Bif Km 173,8",2024,2024,34,34,"2024-08-19","08:15:00","2024-08-23","16:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14390402661",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","St-Florentin-Vergigny - Voie 3 Garage",2024,2024,49,37,"2023-12-10","23:10:00","2024-09-14","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14606741261",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","St-Florentin-Vergigny - Voie 3 Garage",2024,2024,11,12,"2024-03-14","08:51:00","2024-03-21","14:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14390257261",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","St-Florentin-Vergigny - Voie 3 Garage",2024,2024,49,49,"2023-12-10","00:00:00","2023-12-10","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14606406461",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","St-Florentin-Vergigny - Voie 3 Garage",2024,2024,45,45,"2024-11-10","22:10:00","2024-11-10","04:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195746261",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,38,45,"2024-09-30","09:45:00","2024-10-31","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195715761",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,17,50,"2024-04-22","09:45:00","2024-12-06","16:13:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689890661",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,50,16,"2024-03-25","10:50:00","2024-04-19","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Derrière 17756 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15202406561",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,39,39,"2024-09-28","08:00:00","2024-09-29","18:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689883861",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,50,49,"2023-12-11","00:10:00","2024-12-02","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689890661",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,50,16,"2023-12-11","10:50:00","2024-04-19","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Derrière 17756 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195746261",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,38,45,"2024-09-16","09:45:00","2024-11-07","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689888861",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,12,37,"2024-03-24","23:15:00","2024-09-15","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Entre 5789 et 5790 ",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689884661",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,1,32,"2024-01-02","09:46:00","2024-08-11","13:26:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"3h45 à 3h54 en sim 5J/7 MC17-0131 pour 891352 (ouvrant) et le 891354 (fermant)                                                                                     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195715761",null,"< >","St-Florentin-Vergigny - Aig Km 165,9","Tanlay",2024,2024,17,50,"2024-04-22","09:45:00","2024-12-13","16:13:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689889861",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tanlay",2024,2024,50,16,"2024-03-25","11:25:00","2024-04-19","13:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Derrière 17757 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689885461",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tanlay",2024,2024,50,49,"2023-12-11","03:00:00","2024-12-02","06:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689889861",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tanlay",2024,2024,50,16,"2023-12-11","11:25:00","2024-04-19","13:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Derrière 17757 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689883061",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tanlay",2024,2024,1,32,"2024-01-02","09:26:00","2024-08-11","13:37:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"3h45 à 3h54 en sim 5J/7                                                               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689887061",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tonnerre - Bât Voyageurs",2024,2024,46,46,"2024-11-12","12:25:00","2024-11-17","13:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401034",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689886261",null,"< >","St-Florentin-Vergigny - Bât Voyageurs","Tonnerre - Bât Voyageurs",2024,2024,46,46,"2024-11-12","12:05:00","2024-11-17","12:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401062",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703682061",null,"< >","St-Ouen - Bât Voyageurs","Épinay-sur-Seine",2024,2024,50,50,"2023-12-11","01:30:00","2024-12-14","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703683061",null,"< >","St-Ouen - Bât Voyageurs","Épinay-sur-Seine",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC industrielles",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15338387961",null,"< >","St-Ouen-l'Aumône","St-Ouen-l'Aumône",2024,2024,30,33,"2024-07-26","22:25:00","2024-08-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13703587861",null,"< >","St-Ouen-l'Aumône","St-Ouen-l'Aumône",2024,2024,1,50,"2024-01-02","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ITC industrielles ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14339216561",null,"< >","St-Ouen-l'Aumône","St-Ouen-l'Aumône",2024,2024,2,50,"2024-01-08","23:35:00","2024-12-13","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14345094961",null,"< >","St-Ouen-l'Aumône","St-Ouen-l'Aumône",2024,2024,50,50,"2023-12-12","01:45:00","2024-12-14","04:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14345153161",null,"< >","St-Ouen-l'Aumône","St-Ouen-l'Aumône",2024,2024,51,36,"2023-12-19","01:45:00","2024-09-07","04:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688630261",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","Valence - Bif Cagnard",2024,2024,51,33,"2023-12-18","12:57:00","2024-08-14","13:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401066 FEN22_StRambert-BifduCagnard(RG)_004(2F_SRA-VCE_004) :  o Heure Fin PK Fin : 13h29 au lieu de 13h32 ,  o TRAIN FERMANT 886184.                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688625461",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","Valence - Bât Voyageurs",2024,2024,23,34,"2024-06-03","10:01:00","2024-08-23","14:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h06 à 4h59 en sim 5J SA2017 => TO 17706 / TF 886118 Décalage MC18-0157 MC18-0160 réduction pour 886118                       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14671255261",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","Andancette - Bât Voyageurs",2024,2024,22,30,"2024-05-27","22:35:00","2024-07-28","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créé pour CHA 24_0026405 RAG De St-Rambert-D'Albons  Sél 8+10 Sr Champ Rolland St Rambert V1",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14568462161",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","La Roche-de-Glun - Bât Voyageurs",2024,2024,12,46,"2024-03-18","22:25:00","2024-11-14","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée pour CCR 5 -  Tx SeG Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58  ZEP L St-Rambert Vallier Voie 1 - ZEP L St Vallier St Rambert V2 - ZEP 201+203+205 ZEP 202+204+206+208 -  ZEP L St Vallier Tain Voie 1 - ZEP L Tain S",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14562487861",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","La Roche-de-Glun - Bât Voyageurs",2024,2024,6,8,"2024-02-05","21:35:00","2024-02-23","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée pour CCR 5 - Travaux Voie SAINT VALLIER KM 583 au KM 585+200 + Tx SeG ravaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58  ZEP L St-Rambert Vallier Voie 1 - ZEP L St Vallier St Rambert V2 - ZEP 201+203+205 ZEP 202+204+206+20",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14985061761",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","La Roche-de-Glun - Bât Voyageurs",2024,2024,4,11,"2024-01-22","22:10:00","2024-03-17","05:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée pour CCR 5 - Travaux Voie SAINT VALLIER KM 583 au KM 585+200 + Tx SeG ravaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58  ZEP L St-Rambert Vallier Voie 1 - ZEP L St Vallier St Rambert V2 - ZEP 201+203+205 ZEP 202+204+206+20",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14985100761",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","La Roche-de-Glun - Bât Voyageurs",2024,2024,12,46,"2024-03-18","23:30:00","2024-11-17","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée pour CCR 5 -  Tx SeG Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58  ZEP L St-Rambert Vallier Voie 1 - ZEP L St Vallier St Rambert V2 - ZEP 201+203+205 ZEP 202+204+206+208 -  ZEP L St Vallier Tain Voie 1 - ZEP L Tain S",null,null,null,null,"High","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14699475061",null,"< >","St-Rambert-d'Albon - Bif Km 572,3","Valence - ITE Km 611,695",2024,2024,20,30,"2024-05-13","21:40:00","2024-07-26","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créé pour CHA 24_0026011 - Eradication de Zones Bois RVB Andancette Portes  ZEP St Rambert Tain V1 - ZEP Tain St Rambert V2 - Sr. Saint Rambert-St Vallier V1 et Sr. Saint Rambert-St Vallier V2 - Sr. St Valliers - Serves V1 -  Sr. St Valliers - Serves V2 -",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14629399561",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,27,43,"2024-07-01","22:35:00","2024-10-24","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créé pour CHA 24_006301 RR double File entre SRA et VCE BOA 34100 ml - Travaux Préparatoires et Finitions  ZEP L St Rambert Valence V1 + ZEP 413+415+417 de St Rambert d´Albon - ZEP L Valence - St Rambert V2 + ZEP 402+404 et 420+422+424 ZEP 418+PP de St Ra",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14633816961",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,33,41,"2024-08-12","21:35:00","2024-10-11","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créé pour CHA 24_006301 RR double File entre SRA et VCE BOA 34100 ml - Travaux Principaux  ZEP L St Rambert Valence V1 + ZEP 413+415+417 de St Rambert d´Albon - ZEP L Valence - St Rambert V2 + ZEP 402+404 et 420+422+424 ZEP 418+PP de St Rambert d´Albon  S",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","16030874661",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,27,43,"2024-07-05","23:30:00","2024-10-25","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créé pour CHA 24_006301 RR double File entre SRA et VCE BOA 34100 ml - Travaux Préparatoires et Finitions  ZEP L St Rambert Valence V1 + ZEP 413+415+417 de St Rambert d´Albon - ZEP L Valence - St Rambert V2 + ZEP 402+404 et 420+422+424 ZEP 418+PP de St Ra",null,null,null,null,"High","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688626261",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,23,34,"2024-06-03","10:05:00","2024-08-23","15:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h06 à 4h59 en sim 5J/7 SA2017 => TO 17709 / TF 886127 FEN22_StRambert-BifduCagnard(RG)_001(2F_SRA-VCE_001) :  o Heure Début PK Début : 10h05 au lieu de 09h59 ,  o Heure Fin PK Début : 14h56 au lieu de 14h59,  o Heure Début PK Fin : 10h32 au lieu de 10h24",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688628661",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,35,48,"2024-08-26","12:02:00","2024-11-29","13:28:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401037 A vigiler passage du 886185 (demande TER en RP0 RAA du 14/06/2017 sur CHA17_0016613) à h+29 à VCE BG dans la trame 2h SA2019 (passage à 13h26 dans le préconstruit 2018). Sinon réduire fin de plage PKfin à 13h25.                    ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688627061",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bif Cagnard",2024,2024,21,47,"2024-05-26","23:12:00","2024-11-24","02:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10800589",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688631861",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bât Voyageurs",2024,2024,4,41,"2024-01-22","22:40:00","2024-10-11","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée initialement  pour chantier de Maintenance (Engins,... )  Toutes ZEP et S.él de SRA à VCE (Bif du Cagnard)",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15036019061",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bât Voyageurs",2024,2024,45,45,"2024-11-10","22:15:00","2024-11-10","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée initialement pour CHA26_0026458 - HPGV SE MeS  ------------------ ATTENTION -----------------  Coupure IHM3 CCSL  --------------------------------------------------",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14970478761",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Valence - Bât Voyageurs",2024,2024,15,37,"2024-04-13","22:35:00","2024-09-14","05:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créé Pour CHA20_0018098 HPGV SE   Essais Poste à poste et essais en long IHM : Poste 51 Alixan / P10 Chateauneuf sur Isère / P60 St Marcel les Valences +  PCD Moirans / SAE LGV SE / IHM3 CCSL (A globaliser avec demande sur IFP ALPES  Toutes ZEP et Sel ent",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14569321061",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Andancette - Bât Voyageurs",2024,2024,6,49,"2024-02-05","22:10:00","2024-12-05","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée pour CHA 24_0026620 - CCR Tx SeG : Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles VT + Essais Poste 58  CCTT Toutes  ZEP de SRA - Sr Champ Rolland St Rambert voie - Sr Peyraud Champ Rolland St Rambert V2",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14984882661",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Andancette - Bât Voyageurs",2024,2024,6,49,"2024-02-05","23:05:00","2024-12-08","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée pour CHA 24_0026620 - CCR Tx SeG : Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles VT + Essais Poste 58  CCTT Toutes  ZEP de SRA - Sr Champ Rolland St Rambert voie - Sr Peyraud Champ Rolland St Rambert V2",null,null,null,null,"Major","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14669234461",null,"< >","St-Rambert-d'Albon - Voie 12 Garage","Andancette - Bât Voyageurs",2024,2024,19,33,"2024-05-06","22:35:00","2024-08-18","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée pour CHA 24_0026405- RAG de SRA :   Sél  9 drSr Champ Rolland St Rambert voie 1 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14568473161",null,"< >","St-Vallier-sur-Rhône - Voie 4 Garage","St-Vallier-sur-Rhône - Voie 5 Garage",2024,2024,12,46,"2024-03-18","22:25:00","2024-11-14","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée pour CHA 24_0026620 -  CCR 5 - Travaux SeG SAINT VALLIER :  Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58   ZEP L St-Rambert St-Vallier  V1 - ZEP 201+203+205 de St Vallier  - ZEP L St-Vallier Tain Voie 1 - Secteurs St",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14558253561",null,"< >","St-Vallier-sur-Rhône - Voie 4 Garage","St-Vallier-sur-Rhône - Voie 5 Garage",2024,2024,4,11,"2024-01-22","21:35:00","2024-03-15","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée pour CHA 24_0026620 -  CCR 5 - Travaux Voie SAINT VALLIER KM 583 au KM 585+200 + Tx SeG :  Travaux Signalisation - Panneaux - KVB-CDV - Aiguilles - VT + Essais Poste 58   ZEP L St-Rambert St-Vallier  V1 - ZEP 201+203+205 de St Vallier  - ZEP L St-Va",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15036569261",null,"< >","St-Vallier-sur-Rhône - Voie 4 Garage","St-Vallier-sur-Rhône - Voie 5 Garage",2024,2024,45,45,"2024-11-10","22:15:00","2024-11-10","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée initialement pour CHA26_0026458 - HPGV SE MeS  Report des mesures de protections sur les postes encadrants.  ------------------ ATTENTION -----------------  Coupure IHM3 CCSL  --------------------------------------------------",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14970519361",null,"< >","St-Vallier-sur-Rhône - Voie 4 Garage","St-Vallier-sur-Rhône - Voie 5 Garage",2024,2024,15,37,"2024-04-13","22:35:00","2024-09-14","05:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée pour CHA20_0018098 HPGVSE  Essais Poste à poste et essais en long IHM : Poste 51 Alixan / P10 Chateauneuf sur Isère / P60 St Marcel les Valence +  PCD Moirans / SAE LGV SE / IHM3 CCSL (A globaliser avec demande sur IFP ALPES)  Toutes ZEP et Sel de S",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462011761",null,"< >","Thionville - Ac Nord FSC Lux","Hettange-Grande",2024,2024,31,31,"2024-07-29","10:15:00","2024-07-30","11:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h35 jour, zep 934",null,null,null,null,"Medium","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14461983661",null,"< >","Thionville - Ac Nord FSC Lux","Hettange-Grande",2024,2024,30,30,"2024-07-26","10:15:00","2024-07-26","12:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h55 jour, zep 934",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14000425461",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,7,7,"2024-02-14","10:25:00","2024-02-15","14:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 3h45 jour, V1+V2 entre Thionville et Bettembourg.",null,null,null,null,"Medium","3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15126429461",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,9,36,"2024-03-03","23:00:00","2024-09-08","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15121690461",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,35,36,"2024-08-27","00:10:00","2024-09-07","03:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 3h30, V1+V2 entre Thionville et Zoufftgen. Avec 4D_THL-HGT_019, 4D_THL-AP_025 et 4C_THL_153.",null,null,null,null,"High","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462092361",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,13,49,"2024-03-30","04:00:00","2024-12-02","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en service CCR secteur Thionville    Les objets travaux placés sur les WE S13+21+40+48 ne seront pas tous utilisés (WE de secours selon avancement du projet CCR), il est demandé à la DAC de tracer les sillons dans les objets travaux au lot 1 avec la ",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14132534061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,30,30,"2024-07-25","11:30:00","2024-07-25","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 2h45 jour, DFV-L BTG-THL V1",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14000728161",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,7,35,"2024-02-18","23:55:00","2024-09-01","01:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676094461",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,50,50,"2023-12-11","09:03:00","2024-12-13","09:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676093661",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,50,50,"2023-12-11","14:00:00","2024-12-13","15:07:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14128639961",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,10,16,"2024-03-10","23:50:00","2024-04-21","03:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec 4C_THL_100 qui reprend les conséquences circulations.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676092061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-01-08","23:27:00","2024-06-14","05:27:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676092061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-06-03","23:27:00","2024-06-07","05:27:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676092061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-10-28","23:27:00","2024-11-08","05:27:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676092061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-01-22","23:27:00","2024-12-06","05:27:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676092061",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-06-24","23:27:00","2024-06-28","05:27:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676092861",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-01-08","23:43:00","2024-06-14","05:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676092861",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-06-03","23:43:00","2024-06-07","05:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676092861",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-10-28","23:43:00","2024-11-08","05:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676092861",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-01-22","23:43:00","2024-12-06","05:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676092861",null,"< >","Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,2,49,"2024-06-24","23:43:00","2024-06-28","05:29:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15120760061",null,"< >","Thionville - Bât Voyageurs","Thionville - ITE EDF/Catteno",2024,2024,23,24,"2024-06-03","23:45:00","2024-06-14","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null," Cap 5h40, 1L3+2L3 coté Nord, Accès FLUX interdit, Avec 4F_THL-ZOU_001 et _002.     ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457938661",null,"< >","Thionville - Bât Voyageurs","Thionville - FSC Luxembourg",2024,2024,17,17,"2024-04-22","10:00:00","2024-04-23","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 895, Voie C",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457794361",null,"< >","Thionville - Bât Voyageurs","Thionville - FSC Luxembourg",2024,2024,16,16,"2024-04-19","10:00:00","2024-04-20","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 896, Voie B",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457962261",null,"< >","Thionville - Bât Voyageurs","Thionville - FSC Luxembourg",2024,2024,17,17,"2024-04-23","10:00:00","2024-04-24","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 893, Voie D",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14461812861",null,"< >","Thionville - Bât Voyageurs","Thionville - FSC Luxembourg",2024,2024,29,29,"2024-07-15","10:00:00","2024-07-16","11:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h20 jour, zep 895+897, Voie 1L3+2L3/C",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676085461",null,"< >","Thionville - Bât Voyageurs","Thionville - Ac Nord FSC Lux",2024,2024,32,35,"2024-08-05","08:00:00","2024-08-30","14:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 6h, Faisceau Luxembourg Thionville (V15 à 29). DP S9C: zep 913,915,917,919,921,923,925,927,929,905,902. DP S11: Sél 340,315,317,319,321,323,325,327,329,330 du SSr Thionville Faisceau Luxembourg.   ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457991961",null,"< >","Thionville - Bât Voyageurs","Thionville - Jonctions Nord",2024,2024,17,17,"2024-04-24","10:00:00","2024-04-25","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 891, Voie E",null,null,null,null,"Medium","3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462280261",null,"< >","Thionville - Bif L3/L7","Thionville - Bât Voyageurs",2024,2024,35,35,"2024-08-27","10:00:00","2024-08-28","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h30 jour, zep 854, Voie 2M",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14132577061",null,"< >","Thionville - Bif L3/L7","Thionville - Ac Nord FSC Lux",2024,2024,23,24,"2024-06-03","23:40:00","2024-06-14","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Sél 44+46+47+145+147 du SSr Thionville côté BV. B+C interdites. Accès L180N de/vers Bettembourg interdit. FLUX inacessible.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457507261",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,15,15,"2024-04-10","10:00:00","2024-04-11","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 862, Voie C",null,null,null,null,"Medium","3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457335561",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,14,14,"2024-04-03","10:00:00","2024-04-04","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 2h30 jour, zep 863, Voie B",null,null,null,null,"Medium","3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14458001961",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,17,17,"2024-04-25","10:00:00","2024-04-26","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 856, Voie F",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457362761",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,14,14,"2024-04-05","10:00:00","2024-04-06","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 2h jour, zep 861, Voie D",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457726661",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,16,16,"2024-04-18","10:00:00","2024-04-19","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 853, Voie 1M",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457380761",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,15,15,"2024-04-08","10:00:00","2024-04-09","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 859, Voie E",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14461835561",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,29,29,"2024-07-18","10:00:00","2024-07-19","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 2h30 jour, zep 861, Voie D",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457525761",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,15,15,"2024-04-11","10:00:00","2024-04-12","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 861, Voie D",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462275061",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,35,35,"2024-08-26","10:00:00","2024-08-27","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h30 jour, zep 856, Voie F",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14461831961",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,29,29,"2024-07-16","10:00:00","2024-07-17","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 2h30 jour, zep 863, Voie B",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457478061",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,15,15,"2024-04-09","10:00:00","2024-04-10","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 2h jour, zep 861, Voie D",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14458059461",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,22,22,"2024-05-29","10:00:00","2024-05-30","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 1h30 jour, zep 843, Voie D+1",null,null,null,null,"Medium","3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14457353561",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,14,14,"2024-04-04","10:00:00","2024-04-05","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Cap 2h30 jour, zep 862, Voie C",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14461833761",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,29,29,"2024-07-17","10:00:00","2024-07-18","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 2h30 jour, zep 862, Voie C",null,null,null,null,"Medium","3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462225261",null,"< >","Thionville - Bif L3/L7","Thionville - Jonctions Nord",2024,2024,32,32,"2024-08-09","10:00:00","2024-08-10","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h30 jour, zep 859, Voie E",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462099361",null,"< >","Thionville - FSC Luxembourg","Thionville - ITE EDF/Catteno",2024,2024,31,31,"2024-08-02","10:15:00","2024-08-03","11:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h30 jour, zep 932, Voie 2L3",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14132586861",null,"< >","Thionville - FSC Luxembourg","Thionville - FSC Luxembourg",2024,2024,25,25,"2024-06-17","23:40:00","2024-06-21","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Sél 44+46+48+56+58 du SSr Thionville côté BV. Voie C+D interdites. Accès L180N restreint.",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15120971561",null,"< >","Thionville - FSC Luxembourg","Thionville - FSC Luxembourg",2024,2024,25,28,"2024-06-17","10:30:00","2024-07-12","14:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 4h jour, 1Bis+2Bis+M+FAE+DP accès Nord + D,E,F,1M,2M coté Nord.Avec 4D_THL-HGT_018 et 4D_THL-AP_024.       ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14461678761",null,"< >","Thionville - FSC Luxembourg","Thionville - FSC Luxembourg",2024,2024,28,28,"2024-07-10","10:00:00","2024-07-12","11:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h55 jour, zep 942, Voie 2L3",null,null,null,null,"Medium","3,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14461796661",null,"< >","Thionville - FSC Luxembourg","Thionville - Ac Nord FSC Lux",2024,2024,28,28,"2024-07-11","09:30:00","2024-07-12","11:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h50 jour, zep 941, Voie 1L3",null,null,null,null,"Medium","4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15050429661",null,"< >","Thionville - ITE EDF/Catteno","Thionville - ITE EDF/Catteno",2024,2024,27,27,"2024-07-07","00:10:00","2024-07-08","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PTE Thionville Nord - TT Domaine revendiqué: Ssr Thionville-Yutz + Feeder R du Ssr Thionville côté P1 + Ssr Thionville côté BV (simultanée)  V1B+V2B+A+B+C+D+1Bis+2bis+M interdites. Accès L177,178,180N interdit. FLUX interdit.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14132220461",null,"< >","Thionville - ITE EDF/Catteno","Thionville - ITE EDF/Catteno",2024,2024,27,27,"2024-07-07","23:45:00","2024-07-08","04:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"PTE Thionville Nord - TT Domaine revendiqué: Ssr Thionville-Yutz + Feeder R du Ssr Thionville côté P1 + Ssr Thionville côté BV (simultanée)  V1B+V2B+A+B+C+D+1Bis+2bis+M interdites. Accès L177,178,180N interdit. FLUX interdit.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15121565761",null,"< >","Thionville - ITE EDF/Catteno","Thionville - ITE EDF/Catteno",2024,2024,35,36,"2024-08-27","00:10:00","2024-09-07","03:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 3h30 nuit, 1L3+2L3+1L7.3+2L7.3+1L37.7+2L37.7+1Bis+2Bis+M+FAE+FLUX+DP accès Nord + B,C,D,E,F,1M,2M coté Nord. Avec 4D_THL-ZOU_010 , 4D_THL-HGT_019 et 4D_THL-AP_025.       ",null,null,null,null,"High","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462084061",null,"< >","Thionville - ITE EDF/Catteno","Zoufftgen (IE) - Frontière Fr-Lu",2024,2024,31,31,"2024-07-31","10:15:00","2024-08-01","11:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 1h35 jour, zep 936",null,null,null,null,"Medium","3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14132538861",null,"< >","Thionville - Jonctions Nord","Thionville - ITE EDF/Catteno",2024,2024,20,22,"2024-05-13","23:55:00","2024-05-31","05:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Sél 47+48+49+50+51+52 du SSr Thionville côté BV. Accès L180N de/vers Bettembourg interdit. FLUX inacessible.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14135869261",null,"< >","Thionville - Jonctions Nord","Thionville - ITE EDF/Catteno",2024,2024,10,10,"2024-03-04","23:45:00","2024-03-08","05:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 6h nuit, 1L3+2L3+1L37,7+2L37,7+1L7,3+2L7,3+1Bis+2Bis+M+Accès FAE Nord+Accès FLUX Nord. Accès L177,178,180N interdit.",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462305561",null,"< >","Thionville - Jonctions Nord","Thionville - Ac Nord FSC Lux",2024,2024,35,35,"2024-08-29","10:00:00","2024-08-30","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C1 - Cap 2h jour, zep 905+913, FLUX",null,null,null,null,"Medium","4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14132606061",null,"< >","Thionville - Jonctions Nord","Thionville - Jonctions Nord",2024,2024,26,26,"2024-06-24","23:40:00","2024-06-28","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Sél 56+58 du SSr Thionville côté BV, sél 29+31 du SSr Thionville côté P1, sél 60+63 du SSr Thionville Yutz. D+E+F+1Bis+2Bis interdites. Accès L177,178 restreint.",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195840061",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,8,16,"2024-02-19","09:45:00","2024-04-21","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1 OU voie 2  - Passage possible en bana du 199 au 212, en dehors du domaine de  la SR Cat",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195882861",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,17,18,"2024-04-22","09:45:00","2024-05-05","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195891061",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,19,27,"2024-05-06","09:45:00","2024-07-07","16:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195910761",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,33,47,"2024-08-12","09:36:00","2024-11-24","16:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195918761",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,38,45,"2024-09-16","09:36:00","2024-11-07","17:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195882861",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,17,18,"2024-04-22","09:45:00","2024-05-03","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195918761",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,38,45,"2024-09-30","09:36:00","2024-10-31","17:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195840061",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,8,16,"2024-04-15","09:45:00","2024-04-19","15:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1 OU voie 2  - Passage possible en bana du 199 au 212, en dehors du domaine de  la SR Cat",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195910761",null,"< >","Tonnerre - Bât Voyageurs","Port-Sec-de-Pacy",2024,2024,33,47,"2024-10-04","09:36:00","2024-11-01","16:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689902261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,50,"2023-12-11","10:15:00","2024-12-13","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aiguille d'accès LGV Aisy GV libre       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689903261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,46,"2023-12-18","10:10:00","2024-08-23","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401033",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689905861",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,46,"2023-12-18","11:55:00","2024-08-23","12:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401059",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689905061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,49,"2023-12-18","01:11:00","2024-08-12","04:36:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11300364",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689904061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,1,20,"2024-02-26","10:10:00","2024-05-17","13:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Fenêtre activable lorsque FEN19_StFlorentin-Tonnerre_001 et FEN19_StFlorentin-Tonnerre_003 sont activées. Sans impact sillons           ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689901461",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,48,"2024-01-08","00:50:00","2024-08-19","03:31:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401132",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689902261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,50,"2024-01-15","10:15:00","2024-02-02","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aiguille d'accès LGV Aisy GV libre       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689901461",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,48,"2023-12-11","00:50:00","2024-12-01","03:31:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401132",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689905061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,49,"2023-12-18","01:11:00","2024-12-02","04:36:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11300364",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689911061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,18,37,"2024-05-05","23:30:00","2024-09-15","04:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Entre 5789 et 5790 ",null,null,null,null,"High","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689904061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,1,20,"2024-01-02","10:10:00","2024-02-18","13:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Fenêtre activable lorsque FEN19_StFlorentin-Tonnerre_001 et FEN19_StFlorentin-Tonnerre_003 sont activées. Sans impact sillons           ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689902261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,50,"2023-12-11","10:15:00","2024-08-11","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aiguille d'accès LGV Aisy GV libre       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689903261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,46,"2024-11-12","10:10:00","2024-11-17","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401033",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689905861",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,51,46,"2024-11-12","11:55:00","2024-11-17","12:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401059",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689902261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,50,"2023-12-11","10:15:00","2023-12-15","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aiguille d'accès LGV Aisy GV libre       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689909061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,11,11,"2024-03-16","11:20:00","2024-03-16","11:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: SANS    TF: 17757    ",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689902261",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,50,50,"2024-01-19","10:15:00","2024-04-12","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Aiguille d'accès LGV Aisy GV libre       ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14439111461",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,9,15,"2024-02-26","10:00:00","2024-04-11","13:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Voie 1 + 2",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689909061",null,"< >","Tonnerre - Bât Voyageurs","Aisy - Rac LGV",2024,2024,11,11,"2024-03-16","11:20:00","2024-03-16","11:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: SANS    TF: 17757    ",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15195958761",null,"< >","Tonnerre - Bât Voyageurs","Nuits-sous-Ravières",2024,2024,48,50,"2024-11-25","09:36:00","2024-12-13","16:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673365461",null,"< >","Trilport - Bât Voyageurs","Trilport - Bif de Germigny",2024,2024,5,45,"2024-01-29","13:31:00","2024-11-10","14:16:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tournée M03 - Courbe de Trilport ZEP 205 V1 TO 117275 / TF 117133 ZEP 205 V1 ",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14754070361",null,"< >","Trilport - ITE CCI de Meau","Trilport - Aig Év Germigny",2024,2024,6,6,"2024-02-05","21:40:00","2024-02-09","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673364661",null,"< >","Trilport - ITE CCI de Meau","Trilport - Aig Év Germigny",2024,2024,5,45,"2024-01-29","13:40:00","2024-11-10","14:24:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tournée M03 - Courbe de Trilport ZEP 33002 (202+204+206+208+210+212+214+216) V2 TO 117144 / TF 117278   ",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14131497161",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,10,15,"2024-03-10","23:50:00","2024-04-14","03:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec 4C_THL_100 qui reprend les conséquences circulations.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676573761",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,8,45,"2024-02-19","09:30:00","2024-11-04","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                             ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676577761",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,50,50,"2023-12-11","09:10:00","2024-12-13","10:08:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676579361",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,50,50,"2023-12-11","13:50:00","2024-12-13","14:52:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676580161",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,6,50,"2024-02-05","00:00:00","2024-12-09","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676576161",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,50,50,"2023-12-11","11:35:00","2024-12-13","12:38:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676575361",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,8,45,"2024-02-19","09:30:00","2024-11-04","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)         ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14925047961",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,4,42,"2024-01-23","11:30:00","2024-10-18","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"V1B+V2B à Uckange, MA ME JE VE. Avec 4F_UCK-THL_003 et 4F_UCK-THL_004.  Ne pas activer la Déf quand générique activée sur la L204000 (LGN-THL)                       ",null,null,null,null,"High","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14924978961",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,8,46,"2024-02-20","11:30:00","2024-11-15","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"V1+V2 à Uckange, MA ME JE VE. Accès Faisceau Uckange et Rac d'Uckange interdit. Avec 4F_UCK-THL_001 et 4F_UCK-THL_002.  Déf à activer quand générique activée sur la L204000 (LGN-THL)",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676574561",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,4,42,"2024-01-22","09:30:00","2024-10-14","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                           ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676576961",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,50,45,"2023-12-11","00:00:00","2024-11-04","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676578561",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,6,50,"2024-02-05","00:00:00","2024-12-09","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14000730661",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,7,35,"2024-02-18","23:55:00","2024-09-01","01:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15126004861",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,13,49,"2024-03-30","04:00:00","2024-12-02","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en service CCR secteur Thionville    Les objets travaux placés sur les WE S13+21+40+48 ne seront pas tous utilisés (WE de secours selon avancement du projet CCR), il est demandé à la DAC de tracer les sillons dans les objets travaux au lot 1 avec la ",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15126494561",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,9,36,"2024-03-03","23:00:00","2024-09-08","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15088062761",null,"< >","Uckange - Ano Km 181,3","Ebange - Accès Sud",2024,2024,32,32,"2024-08-11","21:30:00","2024-08-12","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 27678, 8h nuit, V1+V1B+V2 à Uckange P2. Avec 4D_UCK-THL_030 et 4D_HGD-UCK_022 qui reprend les conséquences circulations.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676572961",null,"< >","Uckange - Ano Km 181,3","Uckange - Faisceau",2024,2024,4,42,"2024-01-22","09:30:00","2024-10-14","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                           ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15088080861",null,"< >","Uckange - Ano Km 181,3","Uckange - Faisceau",2024,2024,37,40,"2024-09-09","08:30:00","2024-10-04","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 27678, 8h30 jour, V1B+V2B à Uckange P2. Avec 4D_UCK-THL_031 et 4D_HGD-UCK_023 qui reprend les conséquences circulations.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14550983561",null,"< >","Uckange - Ano Km 181,3","Uckange - Faisceau",2024,2024,9,9,"2024-03-03","08:00:00","2024-03-03","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 les DI sur voies Bis entre Hagondange et Uckange. Simultanément: 4D_WPY-MMZ_012 + 4D_MMZ-HGD_018 + 4D_HGD2_014 + 4D_HGD-UCK_021 + 4D_UCK_035.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676550061",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,4,42,"2024-01-22","09:30:00","2024-10-14","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                       ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676553561",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,50,50,"2023-12-11","09:09:00","2024-12-13","10:07:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676546061",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,4,42,"2024-01-23","11:30:00","2024-10-18","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                             ",null,null,null,null,"High","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676554361",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,50,50,"2023-12-11","11:37:00","2024-12-13","12:44:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676546861",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,8,46,"2024-02-20","11:30:00","2024-11-15","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)         ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676546861",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,8,46,"2024-02-20","11:30:00","2024-02-23","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)         ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676547661",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,8,45,"2024-02-19","09:30:00","2024-11-04","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                               ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676547661",null,"< >","Uckange - Poste 1","Ebange - Aig VL90",2024,2024,8,45,"2024-02-19","09:30:00","2024-02-19","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                               ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13999992261",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,6,6,"2024-02-05","11:30:00","2024-02-06","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf V1+V2 entre Thionville et Uckange. Avec 4C_THL_097.",null,null,null,null,"Medium","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14458115561",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,22,22,"2024-05-31","10:00:00","2024-06-01","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Essais ETCS_C2 - Déf 1h30 jour, zep 162 d'Uckange, V2",null,null,null,null,"Medium","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676552461",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,50,50,"2023-12-11","13:51:00","2024-12-13","14:53:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676544461",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,8,46,"2024-02-20","11:30:00","2024-11-15","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                               ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676544461",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,8,46,"2024-02-20","11:30:00","2024-02-23","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                               ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676548461",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,8,45,"2024-02-19","09:30:00","2024-11-04","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                     ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676548461",null,"< >","Uckange - Poste 1","Ebange - Jonction Nord",2024,2024,8,45,"2024-02-19","09:30:00","2024-02-19","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                     ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15088333061",null,"< >","Uckange - Poste 2","Ebange - Accès Sud",2024,2024,37,40,"2024-09-09","08:30:00","2024-10-04","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 27678, 8h30 jour, V1B (correspond à la zep 157) à Uckange. Avec 4D_UCK_039 et 4D_HGD-UCK_023 qui reprend les conséquences circulations.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15088083761",null,"< >","Uckange - Poste 2","Ebange - Accès Sud",2024,2024,32,32,"2024-08-11","21:30:00","2024-08-12","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 27678, 8h nuit, V1B (correspond à la zep 157) à Uckange. Avec 4D_UCK_038 et 4D_HGD-UCK_022 qui reprend les conséquences circulations.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14000754761",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,7,35,"2024-02-18","23:55:00","2024-09-01","01:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462777561",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,13,49,"2024-03-30","04:00:00","2024-12-02","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Mise en service CCR secteur Thionville    Les objets travaux placés sur les WE S13+21+40+48 ne seront pas tous utilisés (WE de secours selon avancement du projet CCR), il est demandé à la DAC de tracer les sillons dans les objets travaux au lot 1 avec la ",null,null,null,null,"High","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15126500861",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,9,36,"2024-03-03","23:00:00","2024-09-08","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676551661",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,50,50,"2023-12-11","14:15:00","2024-12-13","15:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676549261",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,4,42,"2024-01-23","11:30:00","2024-10-18","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                       ",null,null,null,null,"High","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676545261",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,4,42,"2024-01-22","09:30:00","2024-10-14","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                             ",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676550861",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,50,45,"2023-12-11","00:00:00","2024-11-04","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14131541961",null,"< >","Uckange - Poste 2","Ebange - Jonction Nord",2024,2024,10,16,"2024-03-10","23:50:00","2024-04-21","03:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Avec 4C_THL_100 qui reprend les conséquences circulations.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673432661",null,"< >","Vaires-Torcy - Aig Km 21,0","Vaires-Torcy - Bât Voyageurs",2024,2024,5,27,"2024-02-01","12:40:00","2024-07-05","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2B1/2A2 : ZEP 1336 VAI (aig. 3314a,3314b)     ",null,null,null,null,"Medium","4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673422261",null,"< >","Vaires-Torcy - Aig Km 21,0","Lagny-Thorigny - Tiroir 3",2024,2024,35,35,"2024-08-27","00:45:00","2024-08-31","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673435361",null,"< >","Vaires-Torcy - Bât Voyageurs","Vaires-Torcy - ITE EDF",2024,2024,5,5,"2024-01-30","11:00:00","2024-01-30","12:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1B1 : ZEP 1333 EDF (aig. 3365a)           ",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673436161",null,"< >","Vaires-Torcy - Bât Voyageurs","Lagny-Thorigny",2024,2024,27,27,"2024-07-04","13:37:00","2024-07-05","15:02:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2B1 : ZEP 1330 VAI (aig. 4E2)       ",null,null,null,null,"Medium","4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673438361",null,"< >","Vaires-Torcy - Bât Voyageurs","Lagny-Thorigny",2024,2024,27,27,"2024-07-03","09:30:00","2024-07-03","11:51:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1B1 : ZEP 1333 EDF (aig. 3365a+3365b)       ",null,null,null,null,"Medium","3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673436961",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,50,50,"2024-02-19","23:30:00","2024-02-23","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673423061",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,35,35,"2024-08-26","22:50:00","2024-08-30","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673423861",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,35,35,"2024-08-27","01:18:00","2024-08-31","05:48:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673421461",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,35,35,"2024-08-26","22:45:00","2024-08-30","04:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673436961",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,50,50,"2024-10-22","23:30:00","2024-10-31","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673436961",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,50,50,"2024-02-12","23:30:00","2024-10-10","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673436961",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,50,50,"2024-03-19","23:30:00","2024-09-13","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673436961",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,50,50,"2024-03-11","23:30:00","2024-05-03","04:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14000076761",null,"< >","Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2024,2024,16,16,"2024-04-19","23:30:00","2024-04-21","16:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TOUT VAIRES P5   Restitution 16h40 pour TER 839165 acté en Conciliation N°3 Désaccords RP0 2024",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673434561",null,"< >","Vaires-Torcy - ITE EDF","Lagny-Thorigny",2024,2024,5,27,"2024-01-30","09:10:00","2024-07-04","10:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1L1 : ZEP 1111 LGY (aig. 3915a)         ",null,null,null,null,"Medium","2,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673431061",null,"< >","Vaires-Torcy - ITE EDF","Lagny-Thorigny - Tiroir 3",2024,2024,5,27,"2024-01-29","09:30:00","2024-07-02","12:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1B1 : ZEP 1209 (1103 + 1141 + 1143) LGY (aig. 3915b,3923a)   ",null,null,null,null,"Medium","1,2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673431861",null,"< >","Vaires-Torcy - Poste 4","Vaires-Torcy - Bât Voyageurs",2024,2024,5,5,"2024-01-30","14:00:00","2024-01-30","15:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2B1/2A4 : ZEP 1334 VAI (aig. 3320)   ",null,null,null,null,"Medium","2",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13673433761",null,"< >","Vaires-Torcy - Poste 4","Lagny-Thorigny",2024,2024,5,5,"2024-01-31","13:00:00","2024-01-31","15:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2B1 : ZEP 1330+1332+1350 EDF (aig. 2E1,4E2)         ",null,null,null,null,"Medium","3",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688631061",null,"< >","Valence - ITE Km 611,695","Valence - Bât Voyageurs",2024,2024,51,48,"2023-12-18","12:17:00","2024-11-29","13:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_21 : vibration de +3mn pour avoir Fret PNBP07 en SO   2021_SE_26 : décalage de -25mn alignement avec 1F_POR-LIV_004 pour croisement entre 96634 et 17576 en fin de fenêtre + 17574 en IPCS de Valence à Bif du Cagnard, le 14/11/2019  11401077  MC18-0",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688627861",null,"< >","Valence - ITE Km 611,695","Valence - Bât Voyageurs",2024,2024,22,48,"2024-05-27","02:10:00","2024-11-25","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401131",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13794225461",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,39,39,"2024-09-28","23:05:00","2024-09-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure de 06h00 IHM1 pendant la Mise En Service",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13689967861",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,11,22,"2024-03-11","00:05:00","2024-05-27","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14858721861",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,4,27,"2024-01-22","00:30:00","2024-07-01","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Coupure Pré + Post MES PAI Nuits Aisy Montbard",null,null,null,null,"Medium","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13855620061",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,15,43,"2024-04-09","10:20:00","2024-04-10","12:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9206  TF: 9210  Correspond aux Zeps 304 + 308 + 308 + 310 Voie 2 et 2Bis de BSB",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14408975661",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,33,50,"2024-08-13","09:50:00","2024-12-13","15:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 17756  TF: Sans  En complément de la 4D_BSB-DN_011",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14409036161",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,35,49,"2024-08-26","09:50:00","2024-12-06","16:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 17756 TF: Sans  En complément de la 4D_BSB-DN_010",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14409052361",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,38,45,"2024-09-16","09:30:00","2024-11-07","17:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261  TF:17764   En complément de la 4D_BSB-DN_008",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14997524361",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,38,45,"2024-09-20","09:30:00","2024-11-08","17:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9261  TF: 6706   En complément de la 4D_BSB-DN_029",null,null,null,null,"High","5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13855620061",null,"< >","Verrey","Mâlain - Bât Voyageurs",2024,2024,15,43,"2024-10-23","10:20:00","2024-10-24","12:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO: 9206  TF: 9210  Correspond aux Zeps 304 + 308 + 308 + 310 Voie 2 et 2Bis de BSB",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688591261",null,"< >","Vienne - Bât Voyageurs","St-Rambert-d'Albon - Voie 12 Garage",2024,2024,23,27,"2024-06-03","09:43:00","2024-07-05","14:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h22 à 4h59 en sim 5J/7 SA2017 => TO 17709 / TF 886127 A vigiler passage du TO 17709 (demande TER en RP0 RAA du 14/06/2017 sur CHA17_0016613) à h+42 à VIE dans la trame 2h SA2019 (passage à 9h41 dans le préconstruit 2018). Plage décalée à 9h43/14h43 PK dé",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13688592061",null,"< >","Vienne - Bât Voyageurs","St-Rambert-d'Albon - Bif Km 570,2",2024,2024,23,27,"2024-06-03","10:21:00","2024-07-05","14:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h22 à 4h59 en sim 5J/7 SA2017 => TO 17706 / TF 886118 Décalage MC18-0158 MC18-0160 : Réduction 886118                                 ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15092851861",null,"< >","Vienne - Bât Voyageurs","St-Rambert-d'Albon - Bât Voyageurs",2024,2024,7,45,"2024-02-12","22:40:00","2024-11-10","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée Pour Maintenance spécialisée avec Engins lourds (Entreprises...)  ZEP et Sel de Vienne à Sra  ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15179391861",null,"< >","Vienne - Poste","Vaugris",2024,2024,40,40,"2024-09-30","23:00:00","2024-10-04","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créée Pour  - Maintenance voie ou SeG avec engins spéciaux  ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14623761961",null,"< >","Vienne - Voie 2Bis","Salaise",2024,2024,7,48,"2024-02-12","22:30:00","2024-11-29","06:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Créé pour CHA24_0026549 ADAP PEAGE ROUSSILLON  Travaux de préparations  - Travaux Génie civil - Grutage ascenseur  DFV Type L VIENNE - St RAMBERT voie 1 de la gare de VIENNE   DFV Type L PSt RAMBERT - VIENNE voie 2 de la gare de St RAMBERT - Secteur CLONA",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687134661",null,"< >","Villeneuve-lès-Avignon - Bif de Nîmes","Avignon - Bât Voyageurs",2024,2024,10,11,"2024-03-04","09:57:00","2024-03-17","14:49:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"RPU Fam B, AVIGNON  :   Etendue S9 : Voie 1+2 VAV + V102 ZEP (V1/V2 VAV V2 de la pointe de l'aig 405 Km 2,135 (C401) à la pointe AIG 189 Km 4,087+ V1 de la pointe de AIG 190 Km 3,690 à la pointe de l'aig 407 Km 2,125 et voie 102 de la pointe de l'AIG 190 ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687017861",null,"< >","Villeneuve-lès-Avignon - Bif de Nîmes","Villeneuve-lès-Avignon - Rac Nord",2024,2024,18,18,"2024-04-29","09:57:00","2024-05-03","14:49:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Lot AVI RVLA+VLA, VTE+RFC AVI, à prendre avec 4C_AV_003 :  Etendue S9 : VLA 1 => Rac Sud V2 du Ji Z350/414 km 2,845 à la Pte Aig 407 Km 2,125 + Racc VLA1 du Ji 412/410b Km 2,850 au C406 Km 0,203 (V2 RAC)/0,0028(Rac Sud V2) jusqu'au Rac sud V2 C 406 Km 0,2",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687110261",null,"< >","Villeneuve-lès-Avignon - Rac Nord","Villeneuve-lès-Avignon - Rac Nord",2024,2024,18,18,"2024-04-29","09:57:00","2024-05-03","14:49:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Lot Avi RVLA/VLA, Fenêtre capacitaire voie 1 et 2 de Villeneuve les Avignon à Avignon pour Révision Périodique (VTE+RFC) de 4h52 V2, (Semaine 18, à rendre avec 4C_VAV_001).  Etendue de la plage: du C412 et PATC 748+886 (coté Nimes) vers C171 ( voie1 et 2 ",null,null,null,null,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687343061",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,5,46,"2024-04-15","10:00:00","2024-05-10","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_010 suite disparition après le redécoupage des sections CNM pour le SA 2020 2021_SE_45 : décalage de +50mn pour Corridor PNMD05, le 14/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687343061",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,5,46,"2024-01-29","10:00:00","2024-11-15","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_010 suite disparition après le redécoupage des sections CNM pour le SA 2020 2021_SE_45 : décalage de +50mn pour Corridor PNMD05, le 14/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687343861",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,50,50,"2023-12-11","10:33:00","2024-12-13","11:06:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_012 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687343061",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,5,46,"2024-01-29","10:00:00","2024-02-09","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_010 suite disparition après le redécoupage des sections CNM pour le SA 2020 2021_SE_45 : décalage de +50mn pour Corridor PNMD05, le 14/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687343061",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,5,46,"2024-03-04","10:00:00","2024-11-15","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_010 suite disparition après le redécoupage des sections CNM pour le SA 2020 2021_SE_45 : décalage de +50mn pour Corridor PNMD05, le 14/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687343061",null,"< >","Villeneuve-lès-Avignon - Rac Nord","St-Gervasy-Bezouce - Virgule Ouest",2024,2024,5,46,"2024-08-26","10:00:00","2024-10-04","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_010 suite disparition après le redécoupage des sections CNM pour le SA 2020 2021_SE_45 : décalage de +50mn pour Corridor PNMD05, le 14/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-04-15","09:53:00","2024-05-10","15:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687342261",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,50,50,"2023-12-11","11:52:00","2024-12-13","13:08:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_011 suite disparition après le redécoupage des sections CNM pour le SA 2020  2021_SE_100 + 2021_SE_101 + 2021_SE_102 + 2021_SE_103 : décalage de -02h dans un créneau offrant 01h d'amplitude pour la surveillance et permettre le tra",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-01-29","09:53:00","2024-11-15","15:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-01-29","09:53:00","2024-02-09","15:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-03-11","09:53:00","2024-09-20","15:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-03-04","09:53:00","2024-11-15","15:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13687344661",null,"< >","Villeneuve-lès-Avignon - Rac Sud","St-Gervasy-Bezouce - Rac St-Gervasy",2024,2024,5,46,"2024-08-26","09:53:00","2024-10-04","15:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"recréation de 0F_VAV-SIZ_009 suite disparition après le redécoupage des sections CNM pour le SA 2020",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14517655461",null,"< >","Villeneuve-St-Georges - Bât Voyageurs","Montgeron-Crosne",2024,2024,43,45,"2024-10-21","21:50:00","2024-11-08","05:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15230590561",null,"< >","Villeneuve-St-Georges - Bât Voyageurs","Villeneuve-St-Georges - Point X",2024,2024,7,7,"2024-02-17","21:55:00","2024-02-17","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15281827561",null,"< >","Villeneuve-St-Georges-Triage - Atelier Mat","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,16,17,"2024-04-15","09:35:00","2024-04-26","15:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP 156+158",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14680188361",null,"< >","Villeneuve-St-Georges-Triage - Bif Km 8,9/9,1","Villeneuve-St-Georges-Triage - Carré 55",2024,2024,2,5,"2024-01-08","23:15:00","2024-02-02","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14778744361",null,"< >","Villeneuve-St-Georges-Triage - Bif Km 8,9/9,1","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,41,43,"2024-10-12","22:00:00","2024-10-21","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14778631061",null,"< >","Villeneuve-St-Georges-Triage - FSC Débranche","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,39,43,"2024-09-23","23:15:00","2024-10-25","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14778707861",null,"< >","Villeneuve-St-Georges-Triage - FSC Débranche","Villeneuve-St-Georges-Triage - FSC Rebrousse",2024,2024,40,41,"2024-10-04","23:15:00","2024-10-07","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15289086361",null,"< >","Villeneuve-St-Georges-Triage - FSC Débranche","Villeneuve-St-Georges-Triage - Poste 2",2024,2024,20,21,"2024-05-13","10:00:00","2024-05-24","14:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP 459+462 de VTRP2",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15243804161",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 15,9",2024,2024,10,11,"2024-03-08","23:15:00","2024-03-11","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690593961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,4,50,"2024-09-23","23:15:00","2024-10-11","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690593961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,4,50,"2024-01-22","23:15:00","2024-12-13","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690593961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,4,50,"2024-01-22","23:15:00","2024-12-13","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14862365361",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,11,16,"2024-03-15","23:15:00","2024-04-21","13:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14861910061",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,3,46,"2024-01-20","23:20:00","2024-11-16","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14862454961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Villeneuve-St-Georges - Bif Km 17,090",2024,2024,21,24,"2024-05-25","23:20:00","2024-06-15","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690597761",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,1,34,"2024-07-08","23:15:00","2024-08-23","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"S1/2023",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15702660161",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,39,39,"2024-09-27","23:15:00","2024-09-27","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","3,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690590761",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,50,49,"2023-12-11","23:15:00","2024-12-08","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690591961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,3,38,"2024-01-15","23:15:00","2024-09-22","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP 665 libre",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690597761",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,1,34,"2024-01-02","23:15:00","2024-01-05","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"S1/2023",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690590761",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,50,49,"2023-12-11","23:15:00","2024-12-06","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13690591961",null,"< >","Villeneuve-St-Georges-Triage - FSC Rebrousse","Montgeron-Crosne",2024,2024,3,38,"2024-01-15","23:15:00","2024-09-20","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP 665 libre",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","15289056861",null,"< >","Villeneuve-St-Georges-Triage - FSC Réception","Villeneuve-St-Georges-Triage - Atelier Mat",2024,2024,22,23,"2024-05-27","10:00:00","2024-06-07","14:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"ZEP 176 de VTRP3",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14868014661",null,"< >","Villeneuve-St-Georges-Triage - Poste 3","Villeneuve-St-Georges-Triage - Carré 11",2024,2024,22,23,"2024-05-31","23:15:00","2024-06-03","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Medium","1,5,6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14340826861",null,"< >","Vitrolles-Aéroport-Marseille-P","L'Estaque - Bât Voyageurs",2024,2024,3,37,"2024-01-20","23:59:00","2024-09-14","04:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA20_0018098 \"\"Augmentation débit LGV\"\" : OCP 4h41,  1 nuit du Sa/Di de S3 (20-21/01/24) + 1 nuit du Sa/Di de S25 ( 22-23/06/24 de 23h59 à 04h41 opérations sur l´IHM1 Mistral au P1 de Marseille) et 1 nuit du Sa/Di de S37 pour essai complet de montée en c",null,null,null,null,"Medium","6",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14340241361",null,"< >","Vitrolles-Aéroport-Marseille-P","L'Estaque - Bât Voyageurs",2024,2024,45,45,"2024-11-10","22:35:00","2024-11-10","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"CHA24_0026458, OCP 7h00, 1 nuit du Di/Lu 10-11/11/24 (de 22h35 à 05h35), mise en service \"\"LGV +\"\" sur l'interface de la zone télécommandée de l'IHM1 de Mistral P1 de Marseille)  Conditions de réalisation : toute la zone d'action du poste de l'IHM1 de Mar",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14550504661",null,"< >","Walibi-Lorraine","Hagondange - Faisceau",2024,2024,9,9,"2024-02-26","09:30:00","2024-02-29","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 11822, 6h jour, LU MA ME JE, V1B+V2B entre Woippy AN et Hagondange  (zep type L entre WPY et HGD). Avec 4D_WPY-MMZ_011 qui reprend les conséquences circulations.",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676387261",null,"< >","Woippy - Accès Nord","Hagondange - ITE Richemont",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                           ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676389661",null,"< >","Woippy - Accès Nord","Hagondange - ITE Richemont",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                   ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676393661",null,"< >","Woippy - Accès Nord","Hagondange - ITE Richemont",2024,2024,50,46,"2023-12-11","13:41:00","2024-11-15","14:44:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676396061",null,"< >","Woippy - Accès Nord","Hagondange - ITE Richemont",2024,2024,46,46,"2024-11-16","08:00:00","2024-11-16","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 sur les voies rapides entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_001 + 4D_MMZ-HGD_001 + 4D_HGD2_002. Report circulation sur voies BIS entre UCK ou THL et WPY BV. Entrée WPY par voie 1M interdite => report via FO",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676390461",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                     ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676392061",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                             ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676388861",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                               ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676391261",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)         ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676386461",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                             ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676388061",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                     ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676395261",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,50,50,"2023-12-11","11:27:00","2024-12-13","12:28:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676392861",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,50,50,"2023-12-11","14:25:00","2024-12-13","15:21:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676394461",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,50,34,"2023-12-11","09:19:00","2024-08-23","10:17:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676398061",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,46,46,"2024-11-17","08:00:00","2024-11-17","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 les DI sur voies 1+2Bis entre Woippy et Hagondange. Simultanément 4D_WPY-MMZ_004 + 4D_MMZ-HGD_003 + 4D_HGD2_003. Report circulation sur voie 1Bis d'UCK ou THL à WPY AS, report sur voie 2 de WPY BV à UCK ou THL. Départ WPY côté Nord interdit => s",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14550857361",null,"< >","Woippy - Accès Nord","Hagondange - Faisceau",2024,2024,9,9,"2024-03-03","08:00:00","2024-03-03","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 sur voies Bis entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_012 + 4D_MMZ-HGD_018 + 4D_HGD2_014 + 4D_HGD-UCK_021 + 4D_UCK_035.",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14550032461",null,"< >","Woippy - Accès Nord","Hagondange - Poste 3",2024,2024,8,8,"2024-02-24","22:30:00","2024-02-25","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 11822, 7h nuits SaDi+DiLu, V1+V2 entre Woippy AN et Hagondange  (zep type L entre WPY et HGD). Avec 4D_WPY-MMZ_007 qui reprend les conséquences circulations.",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676232861",null,"< >","Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2024,2024,6,50,"2024-01-30","00:00:00","2024-12-09","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676232061",null,"< >","Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,46,"2023-12-11","13:38:00","2024-11-15","14:41:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676231261",null,"< >","Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,34,"2023-12-11","09:21:00","2024-08-23","10:19:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676233661",null,"< >","Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2024,2024,6,50,"2024-01-30","00:00:00","2024-12-09","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676242461",null,"< >","Woippy - Aig ITE","Maizières-lès-Metz - Bât Voyageurs",2024,2024,8,8,"2024-02-24","22:30:00","2024-02-25","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 11822, 7h nuits SaDi+DiLu, V1+V2 à Woippy AN (zep 45,41,39,26,30). Avec 4D_MMZ-HGD_016. Report des circulations V1B/V2B entre Hagondange et Woippy BV.",null,null,null,null,"Medium","6,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14550724661",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,9,9,"2024-03-03","08:00:00","2024-03-03","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 DI sur voies Bis entre Woippy et Hagondange. Simultanément: 4D_WPY-MMZ_012 + 4D_MMZ-HGD_018 + 4D_HGD2_014 + 4D_HGD-UCK_021 + 4D_UCK_035. Report circulation sur voies rapides entre UCK ou THL et WPY BV. Faisceau départ WPY côté Nord + Faisceau et",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676228061",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                     ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676227261",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,12,44,"2024-03-19","11:30:00","2024-10-31","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                               ",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676226461",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                   ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676225661",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,6,50,"2024-02-05","09:30:00","2024-12-09","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                           ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676234461",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,45,"2023-12-11","00:00:00","2024-11-04","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676236061",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,45,"2023-12-11","00:00:00","2024-11-04","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676230461",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,50,"2023-12-11","11:23:00","2024-12-13","12:27:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676235261",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,50,50,"2023-12-11","14:30:00","2024-12-13","15:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676224861",null,"< >","Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2024,2024,12,44,"2024-03-18","09:30:00","2024-10-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                   ",null,null,null,null,"High","1",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676238861",null,"< >","Woippy - Bât Voyageurs","Woippy - Aig V1M",2024,2024,6,50,"2024-02-06","11:30:00","2024-12-13","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Se substitue à la FEN20_Woippy-Maizières_009 pour adaptation au PK 164+650 (au lieu du PK 167+169 interdisant la sortie AFPL du RE de Woippy). Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uc",null,null,null,null,"Major","2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676239661",null,"< >","Woippy - CV 188","Maizières-lès-Metz - Bât Voyageurs",2024,2024,46,46,"2024-11-17","08:00:00","2024-11-17","15:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf. 7h00 les DI sur voies 1+2Bis entre Woippy et Hagondange. Simultanément 4D_WPY-MMZ_004 + 4D_MMZ-HGD_003 + 4D_HGD2_003. Report circulation sur voie 1Bis d'UCK ou THL à WPY AS, report sur voie 2 de WPY BV à UCK ou THL. Départ WPY côté Nord interdit => s",null,null,null,null,"Medium","7",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676157261",null,"< >","Woippy - Faisceau Début","Woippy - Aig Km 165,3",2024,2024,20,39,"2024-05-13","08:00:00","2024-09-27","14:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 6h30, voie FO Woippy. DP S9C: Zep 291. DP S11: Sél 156 du SSr Woippy Triage Départ à concerter car impact sur la liaison FRE<-->Faisceau Départ.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676162061",null,"< >","Woippy - FSC Arrivée","Woippy - Aig V1M",2024,2024,20,39,"2024-05-13","08:00:00","2024-09-27","14:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 6h30, FRE Woippy. DP S9C: zep 672, 673, 676, 757 à 764, 956, 955, 953. DP S11: sel 157,161,170 du SSr Woippy Triage Départ.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","13676158061",null,"< >","Woippy - FSC Arrivée","Woippy - Faisceau Relais",2024,2024,20,40,"2024-05-13","08:00:00","2024-10-04","14:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Cap 6h30, voie DO Woippy. DP S9C: Zep 282. DP S11: Sél 256 du SSr Woippy Triage Reception.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14550411661",null,"< >","Woippy - FSC Départ","Maizières-lès-Metz - Bât Voyageurs",2024,2024,9,9,"2024-02-26","09:30:00","2024-02-29","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Déf 11822, 6h jour, LU MA ME JE, V1B+V2B à Woippy AN (zep 91,89,84,86,90,92,96). Avec 4D_MMZ-HGD_017. Report des circulations V1/V2 entre Hagondange et Woippy BV. Sortie FD et FRE Woippy vers V2B interdit. Accès ITE Euromoselle interdit. Accès HGD Faiscea",null,null,null,null,"Medium","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24692c",null,"< >","Arras-Bif d'Agny\nArras-Bif de l'arbre Robert","Arras-Bif d'Agny\nArras-Bif de l'arbre Robert",2025,2025,26,33,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"232.2 Gare d'Arras: RAV Brt 40 et 41 + RVB Voie K du 190,270 au 190,292 et du 190,320 au 190,340 - RAV Brt 208 + RVB Voie 9 du 191,820 au 192,360 (avec mise en LRS) + RAV Brt 126 + Simplif des Brt 131 et TO 2 +Voie SN/SL + 400 ml de RVB",null,null,null,"2022-10-06","Major",8,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24692c",null,"< >","Arras-Douai","Arras-Douai",2025,2025,26,33,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"232.1 Gare d'Arras: RAV Brt 40 et 41 + RVB Voie K du 190,270 au 190,292 et du 190,320 au 190,340 - RAV Brt 208 + RVB Voie 9 du 191,820 au 192,360 (avec mise en LRS) + RAV Brt 126 + Simplif des Brt 131 et TO 2 +Voie SN/SL + 400 ml de RVB",null,null,null,"2022-10-06","Major",8,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R21846n",null,"< >","Arras-Lens","Arras-Lens",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"230 Régénération Poste EALE Bailleul Sir Berthoult",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R06869w\n",null,"< >","Arras-Lens ","Arras-Lens ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"72 Déblai de FARBUS au km 202,100 côté V1 et V2: Travaux de reconnaissance et injection",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R16036p",null,"< >","Aulnoye","Aulnoye",2025,2025,2,50,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"78 Aulnoye PMR",null,null,null,"2022-10-06","Major",49,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R00148e",null,"< >","Aulnoye","Aulnoye",2025,2025,39,48,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"298 - RVB Vois RM Aulnoye",null,null,null,"2022-10-06","High",10,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24927g",null,"< >","Aulnoye-Hirson\n\n**","Aulnoye-Hirson\n\n**",2025,2025,22,31,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"235 SR CAT Fives Hirson phase 2/6",null,null,null,"2022-10-06","Major",10,null,null,null,null,null,"Planned"]
[null,"SNCF-R",null,null,"< >","Aulnoye-Hirson\n\n**","Aulnoye-Hirson\n\n**",2025,2025,24,30,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"317- suppression du PN95 à Avesnelles",null,null,null,"2022-10-06","High",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R01584g",null,"< >","Creil-Longueau","Creil-Longueau",2025,2025,14,48,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"124.1 SR ZD Ailly Sur Noye Miraumont \nHSI V80 HP\n\n",null,null,null,"2022-10-06","Major",23,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R30473m",null,"< >","Creil-Longueau","Creil-Longueau",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"259.1 Remplacement FC 2025 IHP",null,null,null,"2022-10-06",null,null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R27364e",null,"< >","Creil-Longueau ","Creil-Longueau ",2025,2025,39,49,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"4 RAV  + du RVB Clermont de l'Oise\n1718a & 1718ac/bd & 1728a et 1728b\nen même temps que St Just",null,null,null,"2022-10-06","High",11,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R03838y",null,"< >","Creil-Longueau ","Creil-Longueau ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"VIGIRAIL 2025 - St Just en Chaussée: \nRAV 1803 & 1805 & 1819b et Simplif du Waa+ Simplif du Brt Za de Gannes\nEn même temps que Clermont et attention à l'accès base de St Just pour Roissy Picardie",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R27356w",null,"< >","Creil-LongueilSteMarie ","Creil-LongueilSteMarie ",2025,2025,38,47,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Simplification en gare de Pont Sainte Maxence (8 AdV)\nVérifier compatibilités axes alternatifs FRET",null,null,null,"2022-10-06","High",10,null,null,null,null,null,"Planned"]
[null,"SNCF-R",null,null,"< >","Frouard-Pagny","Frouard-Pagny",2025,2025,26,34,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"140 Dieulouard - Pont-à-Mousson RR ",null,null,null,"2022-10-06","High",9,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R30494m",null,"< >","Goussainville-Orry ","Goussainville-Orry ",2025,2025,26,30,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Déblai de Marly la Ville & Remblai de Louvres-Marlot - amélioration du drainage - Ligne 272 000 km 24+900 à 27+160",null,null,null,"2022-10-06","High",5,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R28647u",null,"< >","Goussainville-Orry ","Goussainville-Orry ",2025,2025,2,50,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Roissy Picardie : Block Survilliers (dont Goussainville) : saut de mouton + création 2 voies et quais + impacts sig + Ecopont de Chantilly",null,null,null,"2022-10-06","Major",49,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R13458r",null,"< >","Goussainville-Orry ","Goussainville-Orry ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Renouvellement des 10 interrupteurs 25 kV du poste de traction électrique de Marly-la-Ville",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R20537q",null,"< >","Hagondange","Hagondange",2025,2025,2,9,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"25 Création SST Richemont",null,null,null,"2022-10-06","High",9,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R19153h",null,"< >","Hazebrouck-Dunkerque\n\n*","Hazebrouck-Dunkerque\n\n*",2025,2025,4,44,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"226 Gare de Dunkerque : RVB Voie 1 à quai (304ml), Voie 2 à quai (304ml), Voie 3 à quai (298ml), Voie 4 à quai (273ml) - RB+RT du 302,350 au 304,497 - RVB sur 1299m - RB+RT sur 3826m - B sur 23m + Reliquat RVB HS 301000 2016 (F50005)",null,null,null,"2022-10-06","Major",25,null,null,null,null,null,"Planned"]
[null,"SNCF-R",null,null,"< >","Hazebrouck-Dunkerque\n\n*","Hazebrouck-Dunkerque\n\n*",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"270 Meulage 2024 sur SA 2025",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24718y",null,"< >","Hazebrouck-Dunkerque\n\n*","Hazebrouck-Dunkerque\n\n*",2025,2025,33,47,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"286 Dunkerque RAV TJ10/11, RAV brt46b (incorpo?), RVB 115ml talon brt 31",null,null,null,"2022-10-06","High",6,null,null,null,null,null,"Planned"]
[null,"SNCF-R",null,null,"< >","Hazebrouck-Dunkerque\n\n*","Hazebrouck-Dunkerque\n\n*",2025,2025,15,48,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"293 - Maintenance Hazebrouck Dunkerque ",null,null,null,"2022-10-06","High",8,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R21349s",null,"< >","Lens-Hazebrouck","Lens-Hazebrouck",2025,2025,23,30,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"227 RVB Voie D Bully",null,null,null,"2022-10-06","High",8,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24721y",null,"< >","Lens-Hazebrouck","Lens-Hazebrouck",2025,2025,24,31,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"233 Gare de Béthune: RVB V5 du Pk 229+700 au 229+800 et du Pk 230+200 au 230+250 - RB/RR V5 du Pk 229+800 au 230+200 avec Rt partiel de 189 Tba - RVB Voie 3 du Pk 229+720 au 230+210 - RR Voie 3 du Pk 230+210 au 230+300",null,null,null,"2022-10-06","High",8,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R20536y",null,"< >","Lerouville-Noveant","Lerouville-Noveant",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"145.2 Création d'un atelier TER en I-LOR",null,null,null,"2022-10-06",null,null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24727y",null,"< >","Lerouville-Noveant","Lerouville-Noveant",2025,2025,11,15,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"158.2 RAV Lérouville ",null,null,null,"2022-10-06","Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R30274v",null,"< >","LilleEurope-Calais","LilleEurope-Calais",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"258 Régénération des DBC (4 => 4 bis) PRCI 45 et 46",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R25761a",null,"< >","Lille-Hazebrouck","Lille-Hazebrouck",2025,2025,17,31,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"245.2 Fives Mouscron - Reliquats: RVB Voie 1 du 2,580 au 2,985 - RVB Voie M1/P1 du 0,000 au 0,500 (Becquerel) - RVB Voie M1/P1 du 1,300 au 2,100 - RVB Voies 1+2 suite RAV Bif Lion d'Op 2018 (2x100m)",null,null,null,"2022-10-06","Major",15,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R25715j",null,"< >","Lille-Hazebrouck","Lille-Hazebrouck",2025,2025,7,16,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"281 RRI  Nieppe Hazebrouck",null,null,null,"2022-10-06","High",10,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R25761a",null,"< >","Lille-Tourcoing","Lille-Tourcoing",2025,2025,17,31,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"245.1 Fives Mouscron - Reliquats: RVB Voie 1 du 2,580 au 2,985 - RVB Voie M1/P1 du 0,000 au 0,500 (Becquerel) - RVB Voie M1/P1 du 1,300 au 2,100 - RVB Voies 1+2 suite RAV Bif Lion d'Op 2018 (2x100m)",null,null,null,"2022-10-06","Major",15,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R05089l",null,"< >","Lille-Valenciennes","Lille-Valenciennes",2025,2025,7,10,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"306 - PRO CNV contournement Nord Valenciennes PK 42,673 ",null,null,null,"2022-10-06","High",4,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R01584g",null,"< >","Longueau-Bif d'Agny exclue","Longueau-Bif d'Agny exclue",2025,2025,14,48,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"124.2 SR ZD Ailly Sur Noye Miraumont  \nHSI V80 HP\nLIGNE PARIS/LILLE - RB/RT SR 2018 (Lot 4) DU PK 115.287 AU PK 165.930 VOIE 1 ET 2",null,null,null,"2022-10-06","Major",23,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R00157e",null,"< >","Longueau-Bif d'Agny exclue","Longueau-Bif d'Agny exclue",2025,2025,19,46,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"210 .1 ACHIET-Renouvel. Partie 25 kV",null,null,null,"2022-10-06","High",8,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R30473m",null,"< >","Longueau-Bif d'Agny exclue","Longueau-Bif d'Agny exclue",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"259.2 Remplacement FC 2025 IHP",null,null,null,"2022-10-06",null,null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R25632n",null,"< >","Longueau-Bif d'Agny exclue ","Longueau-Bif d'Agny exclue ",2025,2025,6,9,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"105 LONGUEAU - RAV Brt 2700",null,null,null,"2022-10-06","High",4,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R01584g",null,"< >","Longueau-Bif de l'arbre Robert exclue ","Longueau-Bif de l'arbre Robert exclue ",2025,2025,14,48,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"124.3 SR ZD Ailly Sur Noye Miraumont\nHSI V80 HP\n LIGNE PARIS/LILLE - RB/RT SR 2018 (Lot 4) DU PK 115.287 AU PK 165.930 VOIE 1 ET 2",null,null,null,"2022-10-06","Major",23,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R00157e",null,"< >","Longueau-Bif de l'arbre Robert exclue ","Longueau-Bif de l'arbre Robert exclue ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"210.2 ACHIET-Renouvel. Partie 25 kV",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R30473m",null,"< >","Longueau-Bif de l'arbre Robert exclue ","Longueau-Bif de l'arbre Robert exclue ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"259.3 Remplacement FC 2025 IHP",null,null,null,"2022-10-06",null,null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","?",null,"< >","Longueau-Bif de l'arbre Robert exclue ","Longueau-Bif de l'arbre Robert exclue ",2025,2025,15,18,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"336 - OGE Etanchéité PRA",null,null,null,"2022-10-06","High",4,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R23175n",null,"< >","Longueil Ste Marie-Tergnier ","Longueil Ste Marie-Tergnier ",2025,2025,2,50,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"Travaux du BV de Compiègne",null,null,null,"2022-10-06","High",22,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R01709q",null,"< >","Longueil Ste Marie-Tergnier ","Longueil Ste Marie-Tergnier ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"PRa Margny les compiègne (Elargissement ? Création ? Réhaussement ?)",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R22914u",null,"< >","Longuyon-Thionville","Longuyon-Thionville",2025,2025,15,18,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"156 Remplacement de deux TM du PRA sur RD 653, Terville, ligne 204 000, de Thionville à Mohon.",null,null,null,"2022-10-06","Major",4,null,null,null,null,null,"Planned"]
[null,"SNCF-R",null,null,"< >","Longuyon-Thionville","Longuyon-Thionville",2025,2025,8,39,null,null,null,null,null,"periodical","Development",null,null,null,null,null,null,null,null,null,null,"339.1 CCR Thionville ",null,null,null,"2022-10-06","High",5,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R11993z",null,"< >","Maubeuge","Maubeuge",2025,2025,2,50,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"73 PMR Maubeuge",null,null,null,"2022-10-06","Major",49,null,null,null,null,null,"Planned"]
[null,"SNCF-R","??",null,"< >","Mohon-Mohon\n\n***","Mohon-Mohon\n\n***",2025,2025,36,42,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"344.1 OGE RR File Haute ",null,null,null,"2022-10-06","High",4,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R26291q",null,"< >","Mohon-Sedan","Mohon-Sedan",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"174.2 UP SES Charleville : Éradication de CDV de type monorail/ancien",null,null,null,"2022-10-06",null,null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R20516q",null,"< >","Mohon-Sedan\n\n***","Mohon-Sedan\n\n***",2025,2025,21,30,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"144 Gare de Lumes  :  4 RAV (530, 531A, 531B, 523/522) et Gare de Margut-Fromy  :  3 SUPPR (Aig C- Aig G - TO XB",null,null,null,"2022-10-06","Major",10,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24725q",null,"< >","Noveant-Metz ","Noveant-Metz ",2025,2025,11,15,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"151.2 RAV Metz Sablon",null,null,null,"2022-10-06","High",5,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R14111f",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"CPER P 2015 2020 - Creil - aménagement du pôle Gare",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R18200t",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,2,50,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Modernisation du noeud ferroviaire de Creil - Phase 2 (lié Roissy Picardie)",null,null,null,"2022-10-06","Major",49,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R03930u",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,2,50,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"G&C : PMR Chantilly : phase 2 (notamment PaSo)\nMise en œuvre de Tabliers Auxiliaires\nVersion initiale",null,null,null,"2022-10-06","Major",49,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R03930u",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"G&C : PMR Chantilly : phase 2 (notamment PaSo)\nMise en œuvre d'un cadre préfabriqué sur une OCP de 100h\nVersion initiale",null,null,null,"2022-10-06","Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R03930u",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"G&C : PMR Chantilly : phase 2 (notamment PaSo)\nMise en œuvre de Tabliers Auxiliaires\nVersion validée",null,null,null,"2022-10-06","Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R03930u",null,"< >","Orry-Creil ","Orry-Creil ",2025,2025,39,49,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"G&C : PMR Chantilly : phase 2 (notamment PaSo)\nMise en œuvre d'un cadre préfabriqué sur une OCP de 100h\nVersion validée",null,null,null,"2022-10-06","Major",11,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R18462k",null,"< >","Ostricourt-Lille","Ostricourt-Lille",2025,2025,13,21,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"223.1 RR 16 585m - V1 233,180 à 235,765 - V2 233,220 à 238,470 - V2 238,590 à 239,470 - V2 239,630 à 247,500 + Voie 2 du 171,950 au 173,450",null,null,null,"2022-10-06","High",9,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R20536y",null,"< >","Pagny-Noveant ","Pagny-Noveant ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"145.1 Création d'un atelier TER en I-LOR",null,null,null,"2022-10-06",null,null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",0,null,"< >","ParisNord-Bif de Pierrefitte ","ParisNord-Bif de Pierrefitte ",2025,2025,4,45,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Réfection des quais de la gare du Nord de surface",null,null,null,"2022-10-06","High",41,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R19150h",null,"< >","ParisNord-Bif de Pierrefitte ","ParisNord-Bif de Pierrefitte ",2025,2025,22,50,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"Franchissement urbain Pleyel (FUP) : phase 2\nVoir pour déverinage en semaine au lieu des WE",null,null,null,"2022-10-06","Major",17,null,null,null,null,null,"Planned"]
[null,"SNCF-R",0,null,"< >","Paris-Stade de France ","Paris-Stade de France ",2025,2025,13,23,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"NExTEO BD - Nord : Phase 2a : Prédisposition des installations  de sécurité (P30+P31+P44+P47+P6)\nCréation du STD NExTEO et du réseau radio\nGare du Nord Sout à Stade de France St Denis sur voies RO et DO",null,null,null,"2022-10-06","High",11,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R28557g",null,"< >","Paris-Stade de France ","Paris-Stade de France ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Déplacement de la section de séparation de Paris Gare du Nord souterraine (uniquement RER B pour adaptation MR MING ?)",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R27716w",null,"< >","Paris-Stade de France ","Paris-Stade de France ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Fontis Gare du Nord",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R27333n",null,"< >","Paris-Stade de France ","Paris-Stade de France ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"RR industrialisé BOA entre Paris et Epinay\nVoies DM et RM du pk 1 au pk 6\nA faire en 2025",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",0,null,"< >","Paris-Stade de France ","Paris-Stade de France ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Suppression des zones neutres des portiques souples des quais de la Gare du Nord",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R21788j",null,"< >","Reding-Remilly","Reding-Remilly",2025,2025,5,9,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"152.1  Bénestroff - Metz : RVB HS voies 1 et 2 de 9 zones courtes (TB éxo) pour une longueur total de 1697m.",null,null,null,"2022-10-06","High",5,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R22699y",null,"< >","Reding-Remilly","Reding-Remilly",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"153.1 Bénestroff - Metz-Ville: HS: V2 : 11,507 km de RR et 3,342 km de RRN_1F et V1 : 6,731 km de RR et 0,98 km de RRN_1F",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24793y",null,"< >","Remilly-Bening","Remilly-Bening",2025,2025,16,20,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"167.2 RVB HS, ligne 140 et 172, Rémilly Faulquemont.",null,null,null,"2022-10-06","High",5,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R21788j",null,"< >","Remilly-Metz","Remilly-Metz",2025,2025,10,13,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"152.2  Bénestroff - Metz : RVB HS voies 1 et 2 de 9 zones courtes (TB éxo) pour une longueur total de 1697m.",null,null,null,"2022-10-06","High",4,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R22699y",null,"< >","Remilly-Metz","Remilly-Metz",2025,2025,46,51,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"153.2 Bénestroff - Metz-Ville: HS: V2 : 11,507 km de RR et 3,342 km de RRN_1F et V1 : 6,731 km de RR et 0,98 km de RRN_1F",null,null,null,"2022-10-06","High",6,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24793y",null,"< >","Remilly-Metz","Remilly-Metz",2025,2025,11,15,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"167.1 RVB HS, ligne 140 et 172, Rémilly Faulquemont.",null,null,null,"2022-10-06",null,5,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R10318p",null,"< >","Remilly-Metz ","Remilly-Metz ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"264.7 Corridors européens ETCS niveau1, Corridor 2 - Axe Longuyon - Bettembourg Bâle. PHASE 1 à 5",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R27367e",null,"< >","SaintDenis-VilliersLeBel ","SaintDenis-VilliersLeBel ",2025,2025,8,13,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"RVB HS à Joncherolles (RJ)\nVoir pour décaler d'une semaine cause TX SDM Combs Melun (WE 09/10 et 10/11)",null,null,null,"2022-10-06","Major",6,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R19252v",null,"< >","SaintDenis-VilliersLeBel ","SaintDenis-VilliersLeBel ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"SMGL Grand Joncherolles: Pivos + Syprai",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R23785e",null,"< >","SaintDenis-VilliersLeBel ","SaintDenis-VilliersLeBel ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"SMGL Grand Joncherolles adaptation au RER NG",null,null,null,"2022-10-06","Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R25348s",null,"< >","SaintDenis-VilliersLeBel ","SaintDenis-VilliersLeBel ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"Régé 2 tabliers à poutres jumelles PRA de Pierrefitte (petit ouvrage accolé au PRa 4 voies GL+RER)\nITC côté 272000",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R04320n",null,"< >","SaintDenis-VilliersLeBel ","SaintDenis-VilliersLeBel ",2025,2025,47,49,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"SDA PMR de niveau 4 de la gare de Villiers le Bel (notamment passerelle traversante ville-ville)",null,null,null,"2022-10-06","Major",3,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R26739u",null,"< >","Sedan-Longuyon","Sedan-Longuyon",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"178 Confortement Remblai Villecloye   L204000 km 210+762,",null,null,null,"2022-10-06",null,null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R20516q",null,"< >","Sedan-Longuyon\n\n***","Sedan-Longuyon\n\n***",2025,2025,26,32,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"144 Gare de Lumes  :  4 RAV (530, 531A, 531B, 523/522) et Gare de Margut-Fromy  :  3 SUPPR (Aig C- Aig G - TO XB",null,null,null,"2022-10-06","Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R18871b",null,"< >","St clair-Ambérieu ","St clair-Ambérieu ",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"101 Création Sous Station de Miribel dans le cadre de la convention robustesse",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R07181c",null,"< >","StQuentin-Busigny","StQuentin-Busigny",2025,2025,2,15,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"213.2 PMR Saint Quentin",null,null,null,"2022-10-06","Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R12336k",null,"< >","StQuentin-Busigny","StQuentin-Busigny",2025,2025,21,25,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"218 Régé Potences signaux C106 et C110/112 Busigny",null,null,null,"2022-10-06","High",5,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R16040f",null,"< >","StQuentin-Busigny","StQuentin-Busigny",2025,2025,35,41,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"221.1 Gare de Busigny :  3 RAV (3 BS) et 2 RB (2 BS) + FEM 13974 RVB voie 3 et 5 en gare de Busigny",null,null,null,"2022-10-06","Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R25608n",null,"< >","StQuentin-Busigny","StQuentin-Busigny",2025,2025,35,41,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"241.1 RVB Gare de Busigny voie 3 et voie 5\njumelée avec le F49036 dossier FIC commun",null,null,null,"2022-10-06","Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R","?",null,"< >","Tergnier","Tergnier",2025,2025,2,39,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"331.1 - Passerelle de Tergnier - Démolition",null,null,null,"2022-10-06","Major",19,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R07181c",null,"< >","Tergnier-StQuentin","Tergnier-StQuentin",2025,2025,2,15,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"213.1 PMR Saint Quentin",null,null,null,"2022-10-06","Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R","?",null,"< >","Tergnier-StQuentin","Tergnier-StQuentin",2025,2025,21,25,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"335.1 - OGE Etancheite PRA",null,null,null,"2022-10-06","High",5,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R25610w",null,"< >","Tergnier-StQuentin ","Tergnier-StQuentin ",2025,2025,39,41,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"284 Simplification du Brt 2 de MONTESCOURT",null,null,null,"2022-10-06","High",3,null,null,null,null,null,"Planned"]
[null,"SNCF-R",null,null,"< >","Tergnier-StQuentin ","Tergnier-StQuentin ",2025,2025,3,25,null,null,null,null,null,"periodical","Maintenance",null,null,null,null,null,null,null,null,null,null,"314 - Travaux d'artère câble et passage câble St Quentin Tergnier",null,null,null,"2022-10-06","High",9,null,null,null,null,null,"Planned"]
[null,"SNCF-R",null,null,"< >","Thionville-Apach","Thionville-Apach",2025,2025,4,39,null,null,null,null,null,"periodical","Development",null,null,null,null,null,null,null,null,null,null,"339.3 CCR Thionville ",null,null,null,"2022-10-06","High",6,null,null,null,null,null,"Planned"]
[null,"SNCF-R",null,null,"< >","Thionville-Zoufftgen","Thionville-Zoufftgen",2025,2025,7,39,null,null,null,null,null,"periodical","Development",null,null,null,null,null,null,null,null,null,null,"339.5 CCR Thionville ",null,null,null,"2022-10-06","High",4,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R14872b",null,"< >","Uckange","Uckange",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"134.1 Uckange - poste 1 : 11;12; 13/14; 15/16; 17/18; 18; 19; 20; 21; 22/23 - Aiguilles équipées de réchauffeurs gaz . A équiper avec des réchauffeurs électriques.",null,null,null,"2022-10-06",null,null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R14873t",null,"< >","Uckange","Uckange",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"134.2 Uckange - poste 2 : 15/16; 17/18; 19/20; 21/22; 23/116; 114; 118; 115; 117 - Aiguilles équipées de réchauffeurs gaz . A équiper avec des réchauffeurs électriques.",null,null,null,"2022-10-06",null,null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",null,null,"< >","Uckange-Thionville","Uckange-Thionville",2025,2025,6,39,null,null,null,null,null,"periodical","Development",null,null,null,null,null,null,null,null,null,null,"339.2 CCR Thionville ",null,null,null,"2022-10-06","High",4,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R29722s",null,"< >","Valenciennes-Aulnoye","Valenciennes-Aulnoye",2025,2025,null,null,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"257 Redécoupage de la zone Z562 - ligne 267000",null,null,null,"2022-10-06","High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24970y",null,"< >","Vemars-Sainghin","Vemars-Sainghin",2025,2025,3,27,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"237 Réfection des collecteurs drainant de la gare Haute I-HP",null,null,null,"2022-10-06","Major",26,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R31151t",null,"< >","Vemars-Sainghin","Vemars-Sainghin",2025,2025,32,50,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"313 - RAV PRCI 26 IZEL Pk 165+000 -169+500  - (4 AdV 1/46)",null,null,null,"2022-10-06","Major",19,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R18929f",null,"< >","Vemars-Sainghin\n","Vemars-Sainghin\n",2025,2025,2,50,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"224.2 Liaison ferroviaire Roissy-I-HP - Partie Infrapôle Nord Européen",null,null,null,"2022-10-06","Major",49,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R31061f",null,"< >","Villiers le Bel-Goussainville ","Villiers le Bel-Goussainville ",2025,2025,38,51,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"RVB SR Villiers Orry Chantilly Creil à la place d'Epinay Meru\nV1D du 15+085 au 19+120 soit 4135 ml\nV1D du 33+250 au 41+300 soit 7400 ml\nV1D du 45+950 au 48+000 soit 2050 ml\nV1D du 49+400 au 49+830 soit 430 ml\nV2D du 14+090 au 19+231 soit 5141 ml\nV2D du 45+950 au 48+000 soit 2050 ml\nVM du 36+000 au 41+190 soit 5190 ml",null,null,null,"2022-10-06","High",14,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R18929f",null,"< >","VilliersLeBel-Vemars\n","VilliersLeBel-Vemars\n",2025,2025,2,50,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"224.1 Liaison ferroviaire Roissy-I-HP - Partie Infrapôle Nord Européen",null,null,null,"2022-10-06","Major",49,null,null,null,null,null,"Planned"]
[null,"SNCF-R","R24971q",null,"< >","VilliersLeBel-Vemars\n","VilliersLeBel-Vemars\n",2025,2025,2,8,null,null,null,null,null,"continuous","Maintenance",null,null,null,null,null,null,null,null,null,null,"238.2 LN3 2025 - Remplacement de 5 AD (2 AD Interco LN3 à Ourcq – 2 AD Interco LN1 et 1 AD au Km 4 (226 000) )",null,null,null,"2022-10-06","Major",8,null,null,null,null,null,"Planned"]
[null,"SNCF-R","F41151",null,"< >",62,81,2026,2026,{"$f":"WEEKNUM(L1469)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1469)+[7]dates!$L$3-[7]dates!$H$3","v":38},"2026-01-19","00:00:00","2026-09-13",0.99998842592592585,{"$f":"TEXT(N1469-L1469+ROUNDDOWN(O1469-M1469,0),\"0\")&\" days\"& IF(MOD((O1469-M1469)*24,24)>0,\" + \" & ROUNDDOWN((O1469-M1469)*24,0) & \" h \" & ROUNDDOWN(MOD((O1469-M1469)*1440,60),0) & \" min\",\"\")","v":"237 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65015",null,"< >",73,81,2026,2026,{"$f":"WEEKNUM(L1470)+[7]dates!$L$3-[7]dates!$H$3","v":22},{"$f":"WEEKNUM(N1470)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-05-25","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1470-L1470+ROUNDDOWN(O1470-M1470,0),\"0\")&\" days\"& IF(MOD((O1470-M1470)*24,24)>0,\" + \" & ROUNDDOWN((O1470-M1470)*24,0) & \" h \" & ROUNDDOWN(MOD((O1470-M1470)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64256",null,"< >",80,70,2026,2026,{"$f":"WEEKNUM(L1471)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1471)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-03-09","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1471-L1471+ROUNDDOWN(O1471-M1471,0),\"0\")&\" days\"& IF(MOD((O1471-M1471)*24,24)>0,\" + \" & ROUNDDOWN((O1471-M1471)*24,0) & \" h \" & ROUNDDOWN(MOD((O1471-M1471)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F50429",null,"< >",84,94,2026,2026,{"$f":"WEEKNUM(L1472)+[7]dates!$L$3-[7]dates!$H$3","v":43},{"$f":"WEEKNUM(N1472)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-10-19","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1472-L1472+ROUNDDOWN(O1472-M1472,0),\"0\")&\" days\"& IF(MOD((O1472-M1472)*24,24)>0,\" + \" & ROUNDDOWN((O1472-M1472)*24,0) & \" h \" & ROUNDDOWN(MOD((O1472-M1472)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62585",null,"< >",102,108,2026,2026,{"$f":"WEEKNUM(L1473)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1473)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-09-28","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1473-L1473+ROUNDDOWN(O1473-M1473,0),\"0\")&\" days\"& IF(MOD((O1473-M1473)*24,24)>0,\" + \" & ROUNDDOWN((O1473-M1473)*24,0) & \" h \" & ROUNDDOWN(MOD((O1473-M1473)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65017",null,"< >",136,138,2026,2026,{"$f":"WEEKNUM(L1474)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1474)+[7]dates!$L$3-[7]dates!$H$3","v":46},"2026-08-31","00:00:00","2026-11-08",0.99998842592592585,{"$f":"TEXT(N1474-L1474+ROUNDDOWN(O1474-M1474,0),\"0\")&\" days\"& IF(MOD((O1474-M1474)*24,24)>0,\" + \" & ROUNDDOWN((O1474-M1474)*24,0) & \" h \" & ROUNDDOWN(MOD((O1474-M1474)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","E20214",null,"< >",147,143,2026,2026,{"$f":"WEEKNUM(L1475)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N1475)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-02-02","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1475-L1475+ROUNDDOWN(O1475-M1475,0),\"0\")&\" days\"& IF(MOD((O1475-M1475)*24,24)>0,\" + \" & ROUNDDOWN((O1475-M1475)*24,0) & \" h \" & ROUNDDOWN(MOD((O1475-M1475)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65293",null,"< >",148,178,2026,2026,{"$f":"WEEKNUM(L1476)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1476)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-03-09","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1476-L1476+ROUNDDOWN(O1476-M1476,0),\"0\")&\" days\"& IF(MOD((O1476-M1476)*24,24)>0,\" + \" & ROUNDDOWN((O1476-M1476)*24,0) & \" h \" & ROUNDDOWN(MOD((O1476-M1476)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64636",null,"< >",152,153,2026,2026,{"$f":"WEEKNUM(L1477)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N1477)+[7]dates!$L$3-[7]dates!$H$3","v":37},"2026-07-20","00:00:00","2026-09-06",0.99998842592592585,{"$f":"TEXT(N1477-L1477+ROUNDDOWN(O1477-M1477,0),\"0\")&\" days\"& IF(MOD((O1477-M1477)*24,24)>0,\" + \" & ROUNDDOWN((O1477-M1477)*24,0) & \" h \" & ROUNDDOWN(MOD((O1477-M1477)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58185",null,"< >",153,233,2026,2026,{"$f":"WEEKNUM(L1478)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1478)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-01-05","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1478-L1478+ROUNDDOWN(O1478-M1478,0),\"0\")&\" days\"& IF(MOD((O1478-M1478)*24,24)>0,\" + \" & ROUNDDOWN((O1478-M1478)*24,0) & \" h \" & ROUNDDOWN(MOD((O1478-M1478)*1440,60),0) & \" min\",\"\")","v":"188 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58185",null,"< >",153,233,2026,2026,{"$f":"WEEKNUM(L1479)+[7]dates!$L$3-[7]dates!$H$3","v":15},{"$f":"WEEKNUM(N1479)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-04-06","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1479-L1479+ROUNDDOWN(O1479-M1479,0),\"0\")&\" days\"& IF(MOD((O1479-M1479)*24,24)>0,\" + \" & ROUNDDOWN((O1479-M1479)*24,0) & \" h \" & ROUNDDOWN(MOD((O1479-M1479)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","E22591",null,"< >",173,180,2026,2026,{"$f":"WEEKNUM(L1480)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1480)+[7]dates!$L$3-[7]dates!$H$3","v":12},"2026-01-26","00:00:00","2026-03-15",0.99998842592592585,{"$f":"TEXT(N1480-L1480+ROUNDDOWN(O1480-M1480,0),\"0\")&\" days\"& IF(MOD((O1480-M1480)*24,24)>0,\" + \" & ROUNDDOWN((O1480-M1480)*24,0) & \" h \" & ROUNDDOWN(MOD((O1480-M1480)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F50625",null,"< >",178,188,2026,2026,{"$f":"WEEKNUM(L1481)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1481)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-04-20","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1481-L1481+ROUNDDOWN(O1481-M1481,0),\"0\")&\" days\"& IF(MOD((O1481-M1481)*24,24)>0,\" + \" & ROUNDDOWN((O1481-M1481)*24,0) & \" h \" & ROUNDDOWN(MOD((O1481-M1481)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65199",null,"< >",186,143,2026,2026,{"$f":"WEEKNUM(L1482)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1482)+[7]dates!$L$3-[7]dates!$H$3","v":16},"2026-02-16","00:00:00","2026-04-12",0.99998842592592585,{"$f":"TEXT(N1482-L1482+ROUNDDOWN(O1482-M1482,0),\"0\")&\" days\"& IF(MOD((O1482-M1482)*24,24)>0,\" + \" & ROUNDDOWN((O1482-M1482)*24,0) & \" h \" & ROUNDDOWN(MOD((O1482-M1482)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F66016",null,"< >",187,188,2026,2026,{"$f":"WEEKNUM(L1483)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1483)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-04-27","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1483-L1483+ROUNDDOWN(O1483-M1483,0),\"0\")&\" days\"& IF(MOD((O1483-M1483)*24,24)>0,\" + \" & ROUNDDOWN((O1483-M1483)*24,0) & \" h \" & ROUNDDOWN(MOD((O1483-M1483)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F53227",null,"< >",207,207,2026,2026,{"$f":"WEEKNUM(L1484)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1484)+[7]dates!$L$3-[7]dates!$H$3","v":26},"2026-01-05","00:00:00","2026-06-21",0.99998842592592585,{"$f":"TEXT(N1484-L1484+ROUNDDOWN(O1484-M1484,0),\"0\")&\" days\"& IF(MOD((O1484-M1484)*24,24)>0,\" + \" & ROUNDDOWN((O1484-M1484)*24,0) & \" h \" & ROUNDDOWN(MOD((O1484-M1484)*1440,60),0) & \" min\",\"\")","v":"167 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F47690",null,"< >",208,615,2026,2026,{"$f":"WEEKNUM(L1485)+[7]dates!$L$3-[7]dates!$H$3","v":44},{"$f":"WEEKNUM(N1485)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-10-26","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1485-L1485+ROUNDDOWN(O1485-M1485,0),\"0\")&\" days\"& IF(MOD((O1485-M1485)*24,24)>0,\" + \" & ROUNDDOWN((O1485-M1485)*24,0) & \" h \" & ROUNDDOWN(MOD((O1485-M1485)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52803",null,"< >",236,297,2026,2026,{"$f":"WEEKNUM(L1486)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1486)+[7]dates!$L$3-[7]dates!$H$3","v":26},"2026-03-02","00:00:00","2026-06-21",0.99998842592592585,{"$f":"TEXT(N1486-L1486+ROUNDDOWN(O1486-M1486,0),\"0\")&\" days\"& IF(MOD((O1486-M1486)*24,24)>0,\" + \" & ROUNDDOWN((O1486-M1486)*24,0) & \" h \" & ROUNDDOWN(MOD((O1486-M1486)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A52803",null,"< >",236,297,2026,2026,{"$f":"WEEKNUM(L1487)+[7]dates!$L$3-[7]dates!$H$3","v":15},{"$f":"WEEKNUM(N1487)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-04-06","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1487-L1487+ROUNDDOWN(O1487-M1487,0),\"0\")&\" days\"& IF(MOD((O1487-M1487)*24,24)>0,\" + \" & ROUNDDOWN((O1487-M1487)*24,0) & \" h \" & ROUNDDOWN(MOD((O1487-M1487)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65868",null,"< >",237,67,2026,2026,{"$f":"WEEKNUM(L1488)+[7]dates!$L$3-[7]dates!$H$3","v":34},{"$f":"WEEKNUM(N1488)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-08-17","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1488-L1488+ROUNDDOWN(O1488-M1488,0),\"0\")&\" days\"& IF(MOD((O1488-M1488)*24,24)>0,\" + \" & ROUNDDOWN((O1488-M1488)*24,0) & \" h \" & ROUNDDOWN(MOD((O1488-M1488)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65224",null,"< >",238,238,2026,2026,{"$f":"WEEKNUM(L1489)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1489)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-01-05","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N1489-L1489+ROUNDDOWN(O1489-M1489,0),\"0\")&\" days\"& IF(MOD((O1489-M1489)*24,24)>0,\" + \" & ROUNDDOWN((O1489-M1489)*24,0) & \" h \" & ROUNDDOWN(MOD((O1489-M1489)*1440,60),0) & \" min\",\"\")","v":"104 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58534",null,"< >",279,281,2026,2026,{"$f":"WEEKNUM(L1490)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1490)+[7]dates!$L$3-[7]dates!$H$3","v":18},"2026-03-02","00:00:00","2026-04-26",0.99998842592592585,{"$f":"TEXT(N1490-L1490+ROUNDDOWN(O1490-M1490,0),\"0\")&\" days\"& IF(MOD((O1490-M1490)*24,24)>0,\" + \" & ROUNDDOWN((O1490-M1490)*24,0) & \" h \" & ROUNDDOWN(MOD((O1490-M1490)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58534",null,"< >",279,281,2026,2026,{"$f":"WEEKNUM(L1491)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1491)+[7]dates!$L$3-[7]dates!$H$3","v":18},"2026-03-16","00:00:00","2026-04-26",0.99998842592592585,{"$f":"TEXT(N1491-L1491+ROUNDDOWN(O1491-M1491,0),\"0\")&\" days\"& IF(MOD((O1491-M1491)*24,24)>0,\" + \" & ROUNDDOWN((O1491-M1491)*24,0) & \" h \" & ROUNDDOWN(MOD((O1491-M1491)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F61845",null,"< >",296,297,2026,2026,{"$f":"WEEKNUM(L1492)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1492)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-02-16","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1492-L1492+ROUNDDOWN(O1492-M1492,0),\"0\")&\" days\"& IF(MOD((O1492-M1492)*24,24)>0,\" + \" & ROUNDDOWN((O1492-M1492)*24,0) & \" h \" & ROUNDDOWN(MOD((O1492-M1492)*1440,60),0) & \" min\",\"\")","v":"279 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A61845",null,"< >",296,297,2026,2026,{"$f":"WEEKNUM(L1493)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1493)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-03-16","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1493-L1493+ROUNDDOWN(O1493-M1493,0),\"0\")&\" days\"& IF(MOD((O1493-M1493)*24,24)>0,\" + \" & ROUNDDOWN((O1493-M1493)*24,0) & \" h \" & ROUNDDOWN(MOD((O1493-M1493)*1440,60),0) & \" min\",\"\")","v":"251 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B61845",null,"< >",296,297,2026,2026,{"$f":"WEEKNUM(L1494)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1494)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-03-16","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1494-L1494+ROUNDDOWN(O1494-M1494,0),\"0\")&\" days\"& IF(MOD((O1494-M1494)*24,24)>0,\" + \" & ROUNDDOWN((O1494-M1494)*24,0) & \" h \" & ROUNDDOWN(MOD((O1494-M1494)*1440,60),0) & \" min\",\"\")","v":"251 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65262",null,"< >",297,294,2026,2026,{"$f":"WEEKNUM(L1495)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N1495)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-08","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1495-L1495+ROUNDDOWN(O1495-M1495,0),\"0\")&\" days\"& IF(MOD((O1495-M1495)*24,24)>0,\" + \" & ROUNDDOWN((O1495-M1495)*24,0) & \" h \" & ROUNDDOWN(MOD((O1495-M1495)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A65262",null,"< >",297,294,2026,2026,{"$f":"WEEKNUM(L1496)+[7]dates!$L$3-[7]dates!$H$3","v":37},{"$f":"WEEKNUM(N1496)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-09-07","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1496-L1496+ROUNDDOWN(O1496-M1496,0),\"0\")&\" days\"& IF(MOD((O1496-M1496)*24,24)>0,\" + \" & ROUNDDOWN((O1496-M1496)*24,0) & \" h \" & ROUNDDOWN(MOD((O1496-M1496)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH9166",null,"< >",338,339,2026,2026,{"$f":"WEEKNUM(L1497)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N1497)+[7]dates!$L$3-[7]dates!$H$3","v":34},"2026-06-01","00:00:00","2026-08-16",0.99998842592592585,{"$f":"TEXT(N1497-L1497+ROUNDDOWN(O1497-M1497,0),\"0\")&\" days\"& IF(MOD((O1497-M1497)*24,24)>0,\" + \" & ROUNDDOWN((O1497-M1497)*24,0) & \" h \" & ROUNDDOWN(MOD((O1497-M1497)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F56869",null,"< >",352,847,2026,2026,{"$f":"WEEKNUM(L1498)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1498)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-11","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1498-L1498+ROUNDDOWN(O1498-M1498,0),\"0\")&\" days\"& IF(MOD((O1498-M1498)*24,24)>0,\" + \" & ROUNDDOWN((O1498-M1498)*24,0) & \" h \" & ROUNDDOWN(MOD((O1498-M1498)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58127",null,"< >",364,344,2026,2026,{"$f":"WEEKNUM(L1499)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1499)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-03-02","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1499-L1499+ROUNDDOWN(O1499-M1499,0),\"0\")&\" days\"& IF(MOD((O1499-M1499)*24,24)>0,\" + \" & ROUNDDOWN((O1499-M1499)*24,0) & \" h \" & ROUNDDOWN(MOD((O1499-M1499)*1440,60),0) & \" min\",\"\")","v":"118 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58127",null,"< >",364,344,2026,2026,{"$f":"WEEKNUM(L1500)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1500)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-05","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1500-L1500+ROUNDDOWN(O1500-M1500,0),\"0\")&\" days\"& IF(MOD((O1500-M1500)*24,24)>0,\" + \" & ROUNDDOWN((O1500-M1500)*24,0) & \" h \" & ROUNDDOWN(MOD((O1500-M1500)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B58127",null,"< >",364,344,2026,2026,{"$f":"WEEKNUM(L1501)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1501)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-05-04","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1501-L1501+ROUNDDOWN(O1501-M1501,0),\"0\")&\" days\"& IF(MOD((O1501-M1501)*24,24)>0,\" + \" & ROUNDDOWN((O1501-M1501)*24,0) & \" h \" & ROUNDDOWN(MOD((O1501-M1501)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C58127",null,"< >",364,344,2026,2026,{"$f":"WEEKNUM(L1502)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1502)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-26","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1502-L1502+ROUNDDOWN(O1502-M1502,0),\"0\")&\" days\"& IF(MOD((O1502-M1502)*24,24)>0,\" + \" & ROUNDDOWN((O1502-M1502)*24,0) & \" h \" & ROUNDDOWN(MOD((O1502-M1502)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH3697\nG09164",null,"< >",371,371,2026,2026,{"$f":"WEEKNUM(L1503)+[7]dates!$L$3-[7]dates!$H$3","v":3},{"$f":"WEEKNUM(N1503)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-12","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1503-L1503+ROUNDDOWN(O1503-M1503,0),\"0\")&\" days\"& IF(MOD((O1503-M1503)*24,24)>0,\" + \" & ROUNDDOWN((O1503-M1503)*24,0) & \" h \" & ROUNDDOWN(MOD((O1503-M1503)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH3697\nA09164",null,"< >",371,371,2026,2026,{"$f":"WEEKNUM(L1504)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1504)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-04-20","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1504-L1504+ROUNDDOWN(O1504-M1504,0),\"0\")&\" days\"& IF(MOD((O1504-M1504)*24,24)>0,\" + \" & ROUNDDOWN((O1504-M1504)*24,0) & \" h \" & ROUNDDOWN(MOD((O1504-M1504)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","BH3697\nB09164",null,"< >",371,371,2026,2026,{"$f":"WEEKNUM(L1505)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1505)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-08-31","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1505-L1505+ROUNDDOWN(O1505-M1505,0),\"0\")&\" days\"& IF(MOD((O1505-M1505)*24,24)>0,\" + \" & ROUNDDOWN((O1505-M1505)*24,0) & \" h \" & ROUNDDOWN(MOD((O1505-M1505)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","CH3697\nC09164",null,"< >",371,371,2026,2026,{"$f":"WEEKNUM(L1506)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1506)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-08-31","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1506-L1506+ROUNDDOWN(O1506-M1506,0),\"0\")&\" days\"& IF(MOD((O1506-M1506)*24,24)>0,\" + \" & ROUNDDOWN((O1506-M1506)*24,0) & \" h \" & ROUNDDOWN(MOD((O1506-M1506)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","DH3697\nD09164",null,"< >",371,371,2026,2026,{"$f":"WEEKNUM(L1507)+[7]dates!$L$3-[7]dates!$H$3","v":42},{"$f":"WEEKNUM(N1507)+[7]dates!$L$3-[7]dates!$H$3","v":47},"2026-10-12","00:00:00","2026-11-15",0.99998842592592585,{"$f":"TEXT(N1507-L1507+ROUNDDOWN(O1507-M1507,0),\"0\")&\" days\"& IF(MOD((O1507-M1507)*24,24)>0,\" + \" & ROUNDDOWN((O1507-M1507)*24,0) & \" h \" & ROUNDDOWN(MOD((O1507-M1507)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64561",null,"< >",372,371,2026,2026,{"$f":"WEEKNUM(L1508)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1508)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-08-31","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1508-L1508+ROUNDDOWN(O1508-M1508,0),\"0\")&\" days\"& IF(MOD((O1508-M1508)*24,24)>0,\" + \" & ROUNDDOWN((O1508-M1508)*24,0) & \" h \" & ROUNDDOWN(MOD((O1508-M1508)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F45487",null,"< >",377,1448,2026,2026,{"$f":"WEEKNUM(L1509)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1509)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-02-09","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1509-L1509+ROUNDDOWN(O1509-M1509,0),\"0\")&\" days\"& IF(MOD((O1509-M1509)*24,24)>0,\" + \" & ROUNDDOWN((O1509-M1509)*24,0) & \" h \" & ROUNDDOWN(MOD((O1509-M1509)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A45487",null,"< >",377,1448,2026,2026,{"$f":"WEEKNUM(L1510)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1510)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-04-20","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1510-L1510+ROUNDDOWN(O1510-M1510,0),\"0\")&\" days\"& IF(MOD((O1510-M1510)*24,24)>0,\" + \" & ROUNDDOWN((O1510-M1510)*24,0) & \" h \" & ROUNDDOWN(MOD((O1510-M1510)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B45487",null,"< >",377,1448,2026,2026,{"$f":"WEEKNUM(L1511)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1511)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-08-31","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1511-L1511+ROUNDDOWN(O1511-M1511,0),\"0\")&\" days\"& IF(MOD((O1511-M1511)*24,24)>0,\" + \" & ROUNDDOWN((O1511-M1511)*24,0) & \" h \" & ROUNDDOWN(MOD((O1511-M1511)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C45487",null,"< >",377,1448,2026,2026,{"$f":"WEEKNUM(L1512)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1512)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-22","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1512-L1512+ROUNDDOWN(O1512-M1512,0),\"0\")&\" days\"& IF(MOD((O1512-M1512)*24,24)>0,\" + \" & ROUNDDOWN((O1512-M1512)*24,0) & \" h \" & ROUNDDOWN(MOD((O1512-M1512)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D45487",null,"< >",377,1448,2026,2026,{"$f":"WEEKNUM(L1513)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1513)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-04-20","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1513-L1513+ROUNDDOWN(O1513-M1513,0),\"0\")&\" days\"& IF(MOD((O1513-M1513)*24,24)>0,\" + \" & ROUNDDOWN((O1513-M1513)*24,0) & \" h \" & ROUNDDOWN(MOD((O1513-M1513)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58932",null,"< >",385,392,2026,2026,{"$f":"WEEKNUM(L1514)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1514)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-02-09","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1514-L1514+ROUNDDOWN(O1514-M1514,0),\"0\")&\" days\"& IF(MOD((O1514-M1514)*24,24)>0,\" + \" & ROUNDDOWN((O1514-M1514)*24,0) & \" h \" & ROUNDDOWN(MOD((O1514-M1514)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58932",null,"< >",385,392,2026,2026,{"$f":"WEEKNUM(L1515)+[7]dates!$L$3-[7]dates!$H$3","v":37},{"$f":"WEEKNUM(N1515)+[7]dates!$L$3-[7]dates!$H$3","v":39},"2026-09-07","00:00:00","2026-09-20",0.99998842592592585,{"$f":"TEXT(N1515-L1515+ROUNDDOWN(O1515-M1515,0),\"0\")&\" days\"& IF(MOD((O1515-M1515)*24,24)>0,\" + \" & ROUNDDOWN((O1515-M1515)*24,0) & \" h \" & ROUNDDOWN(MOD((O1515-M1515)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B58932",null,"< >",385,392,2026,2026,{"$f":"WEEKNUM(L1516)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1516)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-10-05","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N1516-L1516+ROUNDDOWN(O1516-M1516,0),\"0\")&\" days\"& IF(MOD((O1516-M1516)*24,24)>0,\" + \" & ROUNDDOWN((O1516-M1516)*24,0) & \" h \" & ROUNDDOWN(MOD((O1516-M1516)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C58932",null,"< >",385,392,2026,2026,{"$f":"WEEKNUM(L1517)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1517)+[7]dates!$L$3-[7]dates!$H$3","v":10},"2026-02-09","00:00:00","2026-03-01",0.99998842592592585,{"$f":"TEXT(N1517-L1517+ROUNDDOWN(O1517-M1517,0),\"0\")&\" days\"& IF(MOD((O1517-M1517)*24,24)>0,\" + \" & ROUNDDOWN((O1517-M1517)*24,0) & \" h \" & ROUNDDOWN(MOD((O1517-M1517)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D58932",null,"< >",385,392,2026,2026,{"$f":"WEEKNUM(L1518)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1518)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-10-05","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N1518-L1518+ROUNDDOWN(O1518-M1518,0),\"0\")&\" days\"& IF(MOD((O1518-M1518)*24,24)>0,\" + \" & ROUNDDOWN((O1518-M1518)*24,0) & \" h \" & ROUNDDOWN(MOD((O1518-M1518)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F55615",null,"< >",441,441,2026,2026,{"$f":"WEEKNUM(L1519)+[7]dates!$L$3-[7]dates!$H$3","v":34},{"$f":"WEEKNUM(N1519)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-08-17","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N1519-L1519+ROUNDDOWN(O1519-M1519,0),\"0\")&\" days\"& IF(MOD((O1519-M1519)*24,24)>0,\" + \" & ROUNDDOWN((O1519-M1519)*24,0) & \" h \" & ROUNDDOWN(MOD((O1519-M1519)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AF55615",null,"< >",441,441,2026,2026,{"$f":"WEEKNUM(L1520)+[7]dates!$L$3-[7]dates!$H$3","v":35},{"$f":"WEEKNUM(N1520)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-08-24","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N1520-L1520+ROUNDDOWN(O1520-M1520,0),\"0\")&\" days\"& IF(MOD((O1520-M1520)*24,24)>0,\" + \" & ROUNDDOWN((O1520-M1520)*24,0) & \" h \" & ROUNDDOWN(MOD((O1520-M1520)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58532",null,"< >",449,446,2026,2026,{"$f":"WEEKNUM(L1521)+[7]dates!$L$3-[7]dates!$H$3","v":38},{"$f":"WEEKNUM(N1521)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-09-14","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1521-L1521+ROUNDDOWN(O1521-M1521,0),\"0\")&\" days\"& IF(MOD((O1521-M1521)*24,24)>0,\" + \" & ROUNDDOWN((O1521-M1521)*24,0) & \" h \" & ROUNDDOWN(MOD((O1521-M1521)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58532",null,"< >",449,446,2026,2026,{"$f":"WEEKNUM(L1522)+[7]dates!$L$3-[7]dates!$H$3","v":39},{"$f":"WEEKNUM(N1522)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-21","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1522-L1522+ROUNDDOWN(O1522-M1522,0),\"0\")&\" days\"& IF(MOD((O1522-M1522)*24,24)>0,\" + \" & ROUNDDOWN((O1522-M1522)*24,0) & \" h \" & ROUNDDOWN(MOD((O1522-M1522)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64032",null,"< >",461,460,2026,2026,{"$f":"WEEKNUM(L1523)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1523)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-02","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1523-L1523+ROUNDDOWN(O1523-M1523,0),\"0\")&\" days\"& IF(MOD((O1523-M1523)*24,24)>0,\" + \" & ROUNDDOWN((O1523-M1523)*24,0) & \" h \" & ROUNDDOWN(MOD((O1523-M1523)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A64032",null,"< >",461,460,2026,2026,{"$f":"WEEKNUM(L1524)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1524)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-02","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1524-L1524+ROUNDDOWN(O1524-M1524,0),\"0\")&\" days\"& IF(MOD((O1524-M1524)*24,24)>0,\" + \" & ROUNDDOWN((O1524-M1524)*24,0) & \" h \" & ROUNDDOWN(MOD((O1524-M1524)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64897 remplacé par F58050",null,"< >",469,469,2026,2026,{"$f":"WEEKNUM(L1525)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1525)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-02-23","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1525-L1525+ROUNDDOWN(O1525-M1525,0),\"0\")&\" days\"& IF(MOD((O1525-M1525)*24,24)>0,\" + \" & ROUNDDOWN((O1525-M1525)*24,0) & \" h \" & ROUNDDOWN(MOD((O1525-M1525)*1440,60),0) & \" min\",\"\")","v":"132 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A64897 remplacé par A58050",null,"< >",469,469,2026,2026,{"$f":"WEEKNUM(L1526)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1526)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-03-16","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1526-L1526+ROUNDDOWN(O1526-M1526,0),\"0\")&\" days\"& IF(MOD((O1526-M1526)*24,24)>0,\" + \" & ROUNDDOWN((O1526-M1526)*24,0) & \" h \" & ROUNDDOWN(MOD((O1526-M1526)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57052",null,"< >",494,496,2026,2026,{"$f":"WEEKNUM(L1527)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1527)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-30","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1527-L1527+ROUNDDOWN(O1527-M1527,0),\"0\")&\" days\"& IF(MOD((O1527-M1527)*24,24)>0,\" + \" & ROUNDDOWN((O1527-M1527)*24,0) & \" h \" & ROUNDDOWN(MOD((O1527-M1527)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","G08113",null,"< >",576,576,2026,2026,{"$f":"WEEKNUM(L1528)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1528)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-01-05","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N1528-L1528+ROUNDDOWN(O1528-M1528,0),\"0\")&\" days\"& IF(MOD((O1528-M1528)*24,24)>0,\" + \" & ROUNDDOWN((O1528-M1528)*24,0) & \" h \" & ROUNDDOWN(MOD((O1528-M1528)*1440,60),0) & \" min\",\"\")","v":"104 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A08113",null,"< >",576,576,2026,2026,{"$f":"WEEKNUM(L1529)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1529)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-05-18","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1529-L1529+ROUNDDOWN(O1529-M1529,0),\"0\")&\" days\"& IF(MOD((O1529-M1529)*24,24)>0,\" + \" & ROUNDDOWN((O1529-M1529)*24,0) & \" h \" & ROUNDDOWN(MOD((O1529-M1529)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58974",null,"< >",577,1568,2026,2026,{"$f":"WEEKNUM(L1530)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1530)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-05-04","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1530-L1530+ROUNDDOWN(O1530-M1530,0),\"0\")&\" days\"& IF(MOD((O1530-M1530)*24,24)>0,\" + \" & ROUNDDOWN((O1530-M1530)*24,0) & \" h \" & ROUNDDOWN(MOD((O1530-M1530)*1440,60),0) & \" min\",\"\")","v":"181 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH3690\nJJ7728",null,"< >",667,668,2026,2026,{"$f":"WEEKNUM(L1531)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N1531)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-02-02","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1531-L1531+ROUNDDOWN(O1531-M1531,0),\"0\")&\" days\"& IF(MOD((O1531-M1531)*24,24)>0,\" + \" & ROUNDDOWN((O1531-M1531)*24,0) & \" h \" & ROUNDDOWN(MOD((O1531-M1531)*1440,60),0) & \" min\",\"\")","v":"300 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F54745",null,"< >",686,684,2026,2026,{"$f":"WEEKNUM(L1532)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1532)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-11","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1532-L1532+ROUNDDOWN(O1532-M1532,0),\"0\")&\" days\"& IF(MOD((O1532-M1532)*24,24)>0,\" + \" & ROUNDDOWN((O1532-M1532)*24,0) & \" h \" & ROUNDDOWN(MOD((O1532-M1532)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A54745",null,"< >",686,684,2026,2026,{"$f":"WEEKNUM(L1533)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1533)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-18","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1533-L1533+ROUNDDOWN(O1533-M1533,0),\"0\")&\" days\"& IF(MOD((O1533-M1533)*24,24)>0,\" + \" & ROUNDDOWN((O1533-M1533)*24,0) & \" h \" & ROUNDDOWN(MOD((O1533-M1533)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","E17683",null,"< >",700,701,2026,2026,{"$f":"WEEKNUM(L1534)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1534)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-19","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1534-L1534+ROUNDDOWN(O1534-M1534,0),\"0\")&\" days\"& IF(MOD((O1534-M1534)*24,24)>0,\" + \" & ROUNDDOWN((O1534-M1534)*24,0) & \" h \" & ROUNDDOWN(MOD((O1534-M1534)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A17683",null,"< >",700,701,2026,2026,{"$f":"WEEKNUM(L1535)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1535)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-30","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1535-L1535+ROUNDDOWN(O1535-M1535,0),\"0\")&\" days\"& IF(MOD((O1535-M1535)*24,24)>0,\" + \" & ROUNDDOWN((O1535-M1535)*24,0) & \" h \" & ROUNDDOWN(MOD((O1535-M1535)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B17683",null,"< >",700,701,2026,2026,{"$f":"WEEKNUM(L1536)+[7]dates!$L$3-[7]dates!$H$3","v":43},{"$f":"WEEKNUM(N1536)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-10-19","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1536-L1536+ROUNDDOWN(O1536-M1536,0),\"0\")&\" days\"& IF(MOD((O1536-M1536)*24,24)>0,\" + \" & ROUNDDOWN((O1536-M1536)*24,0) & \" h \" & ROUNDDOWN(MOD((O1536-M1536)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","M65265",null,"< >",703,1241,2026,2026,{"$f":"WEEKNUM(L1537)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1537)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-19","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1537-L1537+ROUNDDOWN(O1537-M1537,0),\"0\")&\" days\"& IF(MOD((O1537-M1537)*24,24)>0,\" + \" & ROUNDDOWN((O1537-M1537)*24,0) & \" h \" & ROUNDDOWN(MOD((O1537-M1537)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59382",null,"< >",705,706,2026,2026,{"$f":"WEEKNUM(L1538)+[7]dates!$L$3-[7]dates!$H$3","v":32},{"$f":"WEEKNUM(N1538)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-08-03","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1538-L1538+ROUNDDOWN(O1538-M1538,0),\"0\")&\" days\"& IF(MOD((O1538-M1538)*24,24)>0,\" + \" & ROUNDDOWN((O1538-M1538)*24,0) & \" h \" & ROUNDDOWN(MOD((O1538-M1538)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A59382",null,"< >",705,706,2026,2026,{"$f":"WEEKNUM(L1539)+[7]dates!$L$3-[7]dates!$H$3","v":35},{"$f":"WEEKNUM(N1539)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-08-24","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1539-L1539+ROUNDDOWN(O1539-M1539,0),\"0\")&\" days\"& IF(MOD((O1539-M1539)*24,24)>0,\" + \" & ROUNDDOWN((O1539-M1539)*24,0) & \" h \" & ROUNDDOWN(MOD((O1539-M1539)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B59382",null,"< >",705,706,2026,2026,{"$f":"WEEKNUM(L1540)+[7]dates!$L$3-[7]dates!$H$3","v":35},{"$f":"WEEKNUM(N1540)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-08-24","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N1540-L1540+ROUNDDOWN(O1540-M1540,0),\"0\")&\" days\"& IF(MOD((O1540-M1540)*24,24)>0,\" + \" & ROUNDDOWN((O1540-M1540)*24,0) & \" h \" & ROUNDDOWN(MOD((O1540-M1540)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F53280",null,"< >",705,706,2026,2026,{"$f":"WEEKNUM(L1541)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1541)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-05-04","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1541-L1541+ROUNDDOWN(O1541-M1541,0),\"0\")&\" days\"& IF(MOD((O1541-M1541)*24,24)>0,\" + \" & ROUNDDOWN((O1541-M1541)*24,0) & \" h \" & ROUNDDOWN(MOD((O1541-M1541)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A53280",null,"< >",705,706,2026,2026,{"$f":"WEEKNUM(L1542)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1542)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-05-11","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1542-L1542+ROUNDDOWN(O1542-M1542,0),\"0\")&\" days\"& IF(MOD((O1542-M1542)*24,24)>0,\" + \" & ROUNDDOWN((O1542-M1542)*24,0) & \" h \" & ROUNDDOWN(MOD((O1542-M1542)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65743",null,"< >",706,697,2026,2026,{"$f":"WEEKNUM(L1543)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1543)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-06-22","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1543-L1543+ROUNDDOWN(O1543-M1543,0),\"0\")&\" days\"& IF(MOD((O1543-M1543)*24,24)>0,\" + \" & ROUNDDOWN((O1543-M1543)*24,0) & \" h \" & ROUNDDOWN(MOD((O1543-M1543)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","H65265",null,"< >",709,703,2026,2026,{"$f":"WEEKNUM(L1544)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1544)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-16","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1544-L1544+ROUNDDOWN(O1544-M1544,0),\"0\")&\" days\"& IF(MOD((O1544-M1544)*24,24)>0,\" + \" & ROUNDDOWN((O1544-M1544)*24,0) & \" h \" & ROUNDDOWN(MOD((O1544-M1544)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","K65265",null,"< >",709,703,2026,2026,{"$f":"WEEKNUM(L1545)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1545)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-05-11","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1545-L1545+ROUNDDOWN(O1545-M1545,0),\"0\")&\" days\"& IF(MOD((O1545-M1545)*24,24)>0,\" + \" & ROUNDDOWN((O1545-M1545)*24,0) & \" h \" & ROUNDDOWN(MOD((O1545-M1545)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","L65265",null,"< >",709,703,2026,2026,{"$f":"WEEKNUM(L1546)+[7]dates!$L$3-[7]dates!$H$3","v":22},{"$f":"WEEKNUM(N1546)+[7]dates!$L$3-[7]dates!$H$3","v":39},"2026-05-25","00:00:00","2026-09-20",0.99998842592592585,{"$f":"TEXT(N1546-L1546+ROUNDDOWN(O1546-M1546,0),\"0\")&\" days\"& IF(MOD((O1546-M1546)*24,24)>0,\" + \" & ROUNDDOWN((O1546-M1546)*24,0) & \" h \" & ROUNDDOWN(MOD((O1546-M1546)*1440,60),0) & \" min\",\"\")","v":"118 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F40466",null,"< >",710,713,2026,2026,{"$f":"WEEKNUM(L1547)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1547)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-19","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1547-L1547+ROUNDDOWN(O1547-M1547,0),\"0\")&\" days\"& IF(MOD((O1547-M1547)*24,24)>0,\" + \" & ROUNDDOWN((O1547-M1547)*24,0) & \" h \" & ROUNDDOWN(MOD((O1547-M1547)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A40466",null,"< >",710,713,2026,2026,{"$f":"WEEKNUM(L1548)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1548)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-16","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1548-L1548+ROUNDDOWN(O1548-M1548,0),\"0\")&\" days\"& IF(MOD((O1548-M1548)*24,24)>0,\" + \" & ROUNDDOWN((O1548-M1548)*24,0) & \" h \" & ROUNDDOWN(MOD((O1548-M1548)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B40466",null,"< >",710,713,2026,2026,{"$f":"WEEKNUM(L1549)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1549)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-05-11","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1549-L1549+ROUNDDOWN(O1549-M1549,0),\"0\")&\" days\"& IF(MOD((O1549-M1549)*24,24)>0,\" + \" & ROUNDDOWN((O1549-M1549)*24,0) & \" h \" & ROUNDDOWN(MOD((O1549-M1549)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C40466",null,"< >",710,713,2026,2026,{"$f":"WEEKNUM(L1550)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1550)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-28","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1550-L1550+ROUNDDOWN(O1550-M1550,0),\"0\")&\" days\"& IF(MOD((O1550-M1550)*24,24)>0,\" + \" & ROUNDDOWN((O1550-M1550)*24,0) & \" h \" & ROUNDDOWN(MOD((O1550-M1550)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D40466",null,"< >",710,713,2026,2026,{"$f":"WEEKNUM(L1551)+[7]dates!$L$3-[7]dates!$H$3","v":22},{"$f":"WEEKNUM(N1551)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-05-25","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1551-L1551+ROUNDDOWN(O1551-M1551,0),\"0\")&\" days\"& IF(MOD((O1551-M1551)*24,24)>0,\" + \" & ROUNDDOWN((O1551-M1551)*24,0) & \" h \" & ROUNDDOWN(MOD((O1551-M1551)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65186",null,"< >",715,1242,2026,2026,{"$f":"WEEKNUM(L1552)+[7]dates!$L$3-[7]dates!$H$3","v":45},{"$f":"WEEKNUM(N1552)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-11-02","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1552-L1552+ROUNDDOWN(O1552-M1552,0),\"0\")&\" days\"& IF(MOD((O1552-M1552)*24,24)>0,\" + \" & ROUNDDOWN((O1552-M1552)*24,0) & \" h \" & ROUNDDOWN(MOD((O1552-M1552)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59560",null,"< >",720,720,2026,2026,{"$f":"WEEKNUM(L1553)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1553)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-19","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1553-L1553+ROUNDDOWN(O1553-M1553,0),\"0\")&\" days\"& IF(MOD((O1553-M1553)*24,24)>0,\" + \" & ROUNDDOWN((O1553-M1553)*24,0) & \" h \" & ROUNDDOWN(MOD((O1553-M1553)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A59560",null,"< >",720,720,2026,2026,{"$f":"WEEKNUM(L1554)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1554)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-03-16","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1554-L1554+ROUNDDOWN(O1554-M1554,0),\"0\")&\" days\"& IF(MOD((O1554-M1554)*24,24)>0,\" + \" & ROUNDDOWN((O1554-M1554)*24,0) & \" h \" & ROUNDDOWN(MOD((O1554-M1554)*1440,60),0) & \" min\",\"\")","v":"83 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","BF59560",null,"< >",720,720,2026,2026,{"$f":"WEEKNUM(L1555)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1555)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-28","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1555-L1555+ROUNDDOWN(O1555-M1555,0),\"0\")&\" days\"& IF(MOD((O1555-M1555)*24,24)>0,\" + \" & ROUNDDOWN((O1555-M1555)*24,0) & \" h \" & ROUNDDOWN(MOD((O1555-M1555)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C59560",null,"< >",720,720,2026,2026,{"$f":"WEEKNUM(L1556)+[7]dates!$L$3-[7]dates!$H$3","v":16},{"$f":"WEEKNUM(N1556)+[7]dates!$L$3-[7]dates!$H$3","v":21},"2026-04-13","00:00:00","2026-05-17",0.99998842592592585,{"$f":"TEXT(N1556-L1556+ROUNDDOWN(O1556-M1556,0),\"0\")&\" days\"& IF(MOD((O1556-M1556)*24,24)>0,\" + \" & ROUNDDOWN((O1556-M1556)*24,0) & \" h \" & ROUNDDOWN(MOD((O1556-M1556)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59235",null,"< >",733,752,2026,2026,{"$f":"WEEKNUM(L1557)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1557)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-05","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1557-L1557+ROUNDDOWN(O1557-M1557,0),\"0\")&\" days\"& IF(MOD((O1557-M1557)*24,24)>0,\" + \" & ROUNDDOWN((O1557-M1557)*24,0) & \" h \" & ROUNDDOWN(MOD((O1557-M1557)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B49235",null,"< >",733,752,2026,2026,{"$f":"WEEKNUM(L1558)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1558)+[7]dates!$L$3-[7]dates!$H$3","v":38},"2026-08-31","00:00:00","2026-09-13",0.99998842592592585,{"$f":"TEXT(N1558-L1558+ROUNDDOWN(O1558-M1558,0),\"0\")&\" days\"& IF(MOD((O1558-M1558)*24,24)>0,\" + \" & ROUNDDOWN((O1558-M1558)*24,0) & \" h \" & ROUNDDOWN(MOD((O1558-M1558)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A59235",null,"< >",733,752,2026,2026,{"$f":"WEEKNUM(L1559)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1559)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-05","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1559-L1559+ROUNDDOWN(O1559-M1559,0),\"0\")&\" days\"& IF(MOD((O1559-M1559)*24,24)>0,\" + \" & ROUNDDOWN((O1559-M1559)*24,0) & \" h \" & ROUNDDOWN(MOD((O1559-M1559)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59228\nou\nF49228",null,"< >",751,755,2026,2026,{"$f":"WEEKNUM(L1560)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1560)+[7]dates!$L$3-[7]dates!$H$3","v":21},"2026-02-23","00:00:00","2026-05-17",0.99998842592592585,{"$f":"TEXT(N1560-L1560+ROUNDDOWN(O1560-M1560,0),\"0\")&\" days\"& IF(MOD((O1560-M1560)*24,24)>0,\" + \" & ROUNDDOWN((O1560-M1560)*24,0) & \" h \" & ROUNDDOWN(MOD((O1560-M1560)*1440,60),0) & \" min\",\"\")","v":"83 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AF59228\nou\nA49228",null,"< >",751,755,2026,2026,{"$f":"WEEKNUM(L1561)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1561)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-03-09","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1561-L1561+ROUNDDOWN(O1561-M1561,0),\"0\")&\" days\"& IF(MOD((O1561-M1561)*24,24)>0,\" + \" & ROUNDDOWN((O1561-M1561)*24,0) & \" h \" & ROUNDDOWN(MOD((O1561-M1561)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B59228\nou\nB49228",null,"< >",751,755,2026,2026,{"$f":"WEEKNUM(L1562)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N1562)+[7]dates!$L$3-[7]dates!$H$3","v":16},"2026-03-23","00:00:00","2026-04-12",0.99998842592592585,{"$f":"TEXT(N1562-L1562+ROUNDDOWN(O1562-M1562,0),\"0\")&\" days\"& IF(MOD((O1562-M1562)*24,24)>0,\" + \" & ROUNDDOWN((O1562-M1562)*24,0) & \" h \" & ROUNDDOWN(MOD((O1562-M1562)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58132",null,"< >",818,356,2026,2026,{"$f":"WEEKNUM(L1563)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1563)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-04-20","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1563-L1563+ROUNDDOWN(O1563-M1563,0),\"0\")&\" days\"& IF(MOD((O1563-M1563)*24,24)>0,\" + \" & ROUNDDOWN((O1563-M1563)*24,0) & \" h \" & ROUNDDOWN(MOD((O1563-M1563)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58132",null,"< >",818,356,2026,2026,{"$f":"WEEKNUM(L1564)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1564)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-04-20","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1564-L1564+ROUNDDOWN(O1564-M1564,0),\"0\")&\" days\"& IF(MOD((O1564-M1564)*24,24)>0,\" + \" & ROUNDDOWN((O1564-M1564)*24,0) & \" h \" & ROUNDDOWN(MOD((O1564-M1564)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F46804",null,"< >",892,903,2026,2026,{"$f":"WEEKNUM(L1565)+[7]dates!$L$3-[7]dates!$H$3","v":43},{"$f":"WEEKNUM(N1565)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-10-19","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1565-L1565+ROUNDDOWN(O1565-M1565,0),\"0\")&\" days\"& IF(MOD((O1565-M1565)*24,24)>0,\" + \" & ROUNDDOWN((O1565-M1565)*24,0) & \" h \" & ROUNDDOWN(MOD((O1565-M1565)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57868",null,"< >",910,1395,2026,2026,{"$f":"WEEKNUM(L1566)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1566)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-03-30","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1566-L1566+ROUNDDOWN(O1566-M1566,0),\"0\")&\" days\"& IF(MOD((O1566-M1566)*24,24)>0,\" + \" & ROUNDDOWN((O1566-M1566)*24,0) & \" h \" & ROUNDDOWN(MOD((O1566-M1566)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A57868",null,"< >",910,1395,2026,2026,{"$f":"WEEKNUM(L1567)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1567)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-04-20","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1567-L1567+ROUNDDOWN(O1567-M1567,0),\"0\")&\" days\"& IF(MOD((O1567-M1567)*24,24)>0,\" + \" & ROUNDDOWN((O1567-M1567)*24,0) & \" h \" & ROUNDDOWN(MOD((O1567-M1567)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F49244\nF52599?",null,"< >",950,946,2026,2026,{"$f":"WEEKNUM(L1568)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1568)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-05-18","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1568-L1568+ROUNDDOWN(O1568-M1568,0),\"0\")&\" days\"& IF(MOD((O1568-M1568)*24,24)>0,\" + \" & ROUNDDOWN((O1568-M1568)*24,0) & \" h \" & ROUNDDOWN(MOD((O1568-M1568)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A49244\nA52599?",null,"< >",950,946,2026,2026,{"$f":"WEEKNUM(L1569)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N1569)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-01","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1569-L1569+ROUNDDOWN(O1569-M1569,0),\"0\")&\" days\"& IF(MOD((O1569-M1569)*24,24)>0,\" + \" & ROUNDDOWN((O1569-M1569)*24,0) & \" h \" & ROUNDDOWN(MOD((O1569-M1569)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52664",null,"< >",983,887,2026,2026,{"$f":"WEEKNUM(L1570)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1570)+[7]dates!$L$3-[7]dates!$H$3","v":41},"2026-05-18","00:00:00","2026-10-04",0.99998842592592585,{"$f":"TEXT(N1570-L1570+ROUNDDOWN(O1570-M1570,0),\"0\")&\" days\"& IF(MOD((O1570-M1570)*24,24)>0,\" + \" & ROUNDDOWN((O1570-M1570)*24,0) & \" h \" & ROUNDDOWN(MOD((O1570-M1570)*1440,60),0) & \" min\",\"\")","v":"139 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A52664",null,"< >",983,887,2026,2026,{"$f":"WEEKNUM(L1571)+[7]dates!$L$3-[7]dates!$H$3","v":32},{"$f":"WEEKNUM(N1571)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-03","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1571-L1571+ROUNDDOWN(O1571-M1571,0),\"0\")&\" days\"& IF(MOD((O1571-M1571)*24,24)>0,\" + \" & ROUNDDOWN((O1571-M1571)*24,0) & \" h \" & ROUNDDOWN(MOD((O1571-M1571)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B52664",null,"< >",983,887,2026,2026,{"$f":"WEEKNUM(L1572)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1572)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-08-31","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1572-L1572+ROUNDDOWN(O1572-M1572,0),\"0\")&\" days\"& IF(MOD((O1572-M1572)*24,24)>0,\" + \" & ROUNDDOWN((O1572-M1572)*24,0) & \" h \" & ROUNDDOWN(MOD((O1572-M1572)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C52664",null,"< >",983,887,2026,2026,{"$f":"WEEKNUM(L1573)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1573)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-06-15","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1573-L1573+ROUNDDOWN(O1573-M1573,0),\"0\")&\" days\"& IF(MOD((O1573-M1573)*24,24)>0,\" + \" & ROUNDDOWN((O1573-M1573)*24,0) & \" h \" & ROUNDDOWN(MOD((O1573-M1573)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65012",null,"< >",1026,1027,2026,2026,{"$f":"WEEKNUM(L1574)+[7]dates!$L$3-[7]dates!$H$3","v":34},{"$f":"WEEKNUM(N1574)+[7]dates!$L$3-[7]dates!$H$3","v":38},"2026-08-17","00:00:00","2026-09-13",0.99998842592592585,{"$f":"TEXT(N1574-L1574+ROUNDDOWN(O1574-M1574,0),\"0\")&\" days\"& IF(MOD((O1574-M1574)*24,24)>0,\" + \" & ROUNDDOWN((O1574-M1574)*24,0) & \" h \" & ROUNDDOWN(MOD((O1574-M1574)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A65012",null,"< >",1026,1027,2026,2026,{"$f":"WEEKNUM(L1575)+[7]dates!$L$3-[7]dates!$H$3","v":39},{"$f":"WEEKNUM(N1575)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-09-21","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1575-L1575+ROUNDDOWN(O1575-M1575,0),\"0\")&\" days\"& IF(MOD((O1575-M1575)*24,24)>0,\" + \" & ROUNDDOWN((O1575-M1575)*24,0) & \" h \" & ROUNDDOWN(MOD((O1575-M1575)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B65012",null,"< >",1026,1027,2026,2026,{"$f":"WEEKNUM(L1576)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1576)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-28","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1576-L1576+ROUNDDOWN(O1576-M1576,0),\"0\")&\" days\"& IF(MOD((O1576-M1576)*24,24)>0,\" + \" & ROUNDDOWN((O1576-M1576)*24,0) & \" h \" & ROUNDDOWN(MOD((O1576-M1576)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C65012",null,"< >",1026,1027,2026,2026,{"$f":"WEEKNUM(L1577)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1577)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-09-28","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1577-L1577+ROUNDDOWN(O1577-M1577,0),\"0\")&\" days\"& IF(MOD((O1577-M1577)*24,24)>0,\" + \" & ROUNDDOWN((O1577-M1577)*24,0) & \" h \" & ROUNDDOWN(MOD((O1577-M1577)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57046",null,"< >",1051,1049,2026,2026,{"$f":"WEEKNUM(L1578)+[7]dates!$L$3-[7]dates!$H$3","v":16},{"$f":"WEEKNUM(N1578)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-04-13","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1578-L1578+ROUNDDOWN(O1578-M1578,0),\"0\")&\" days\"& IF(MOD((O1578-M1578)*24,24)>0,\" + \" & ROUNDDOWN((O1578-M1578)*24,0) & \" h \" & ROUNDDOWN(MOD((O1578-M1578)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B57050",null,"< >",1071,1069,2026,2026,{"$f":"WEEKNUM(L1579)+[7]dates!$L$3-[7]dates!$H$3","v":43},{"$f":"WEEKNUM(N1579)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-10-19","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1579-L1579+ROUNDDOWN(O1579-M1579,0),\"0\")&\" days\"& IF(MOD((O1579-M1579)*24,24)>0,\" + \" & ROUNDDOWN((O1579-M1579)*24,0) & \" h \" & ROUNDDOWN(MOD((O1579-M1579)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C57050",null,"< >",1071,1069,2026,2026,{"$f":"WEEKNUM(L1580)+[7]dates!$L$3-[7]dates!$H$3","v":45},{"$f":"WEEKNUM(N1580)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-11-02","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1580-L1580+ROUNDDOWN(O1580-M1580,0),\"0\")&\" days\"& IF(MOD((O1580-M1580)*24,24)>0,\" + \" & ROUNDDOWN((O1580-M1580)*24,0) & \" h \" & ROUNDDOWN(MOD((O1580-M1580)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F49924",null,"< >",1089,1091,2026,2026,{"$f":"WEEKNUM(L1581)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1581)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-03-30","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N1581-L1581+ROUNDDOWN(O1581-M1581,0),\"0\")&\" days\"& IF(MOD((O1581-M1581)*24,24)>0,\" + \" & ROUNDDOWN((O1581-M1581)*24,0) & \" h \" & ROUNDDOWN(MOD((O1581-M1581)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A49924",null,"< >",1089,1091,2026,2026,{"$f":"WEEKNUM(L1582)+[7]dates!$L$3-[7]dates!$H$3","v":22},{"$f":"WEEKNUM(N1582)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-25","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1582-L1582+ROUNDDOWN(O1582-M1582,0),\"0\")&\" days\"& IF(MOD((O1582-M1582)*24,24)>0,\" + \" & ROUNDDOWN((O1582-M1582)*24,0) & \" h \" & ROUNDDOWN(MOD((O1582-M1582)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58425",null,"< >",1089,1090,2026,2026,{"$f":"WEEKNUM(L1583)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1583)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-03-30","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N1583-L1583+ROUNDDOWN(O1583-M1583,0),\"0\")&\" days\"& IF(MOD((O1583-M1583)*24,24)>0,\" + \" & ROUNDDOWN((O1583-M1583)*24,0) & \" h \" & ROUNDDOWN(MOD((O1583-M1583)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62488",null,"< >",1107,1114,2026,2026,{"$f":"WEEKNUM(L1584)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1584)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-05-11","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1584-L1584+ROUNDDOWN(O1584-M1584,0),\"0\")&\" days\"& IF(MOD((O1584-M1584)*24,24)>0,\" + \" & ROUNDDOWN((O1584-M1584)*24,0) & \" h \" & ROUNDDOWN(MOD((O1584-M1584)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B62488",null,"< >",1107,1114,2026,2026,{"$f":"WEEKNUM(L1585)+[7]dates!$L$3-[7]dates!$H$3","v":35},{"$f":"WEEKNUM(N1585)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-08-24","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1585-L1585+ROUNDDOWN(O1585-M1585,0),\"0\")&\" days\"& IF(MOD((O1585-M1585)*24,24)>0,\" + \" & ROUNDDOWN((O1585-M1585)*24,0) & \" h \" & ROUNDDOWN(MOD((O1585-M1585)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A62488",null,"< >",1110,1110,2026,2026,{"$f":"WEEKNUM(L1586)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1586)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-05-11","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1586-L1586+ROUNDDOWN(O1586-M1586,0),\"0\")&\" days\"& IF(MOD((O1586-M1586)*24,24)>0,\" + \" & ROUNDDOWN((O1586-M1586)*24,0) & \" h \" & ROUNDDOWN(MOD((O1586-M1586)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C62488",null,"< >",1110,1110,2026,2026,{"$f":"WEEKNUM(L1587)+[7]dates!$L$3-[7]dates!$H$3","v":35},{"$f":"WEEKNUM(N1587)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-08-24","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1587-L1587+ROUNDDOWN(O1587-M1587,0),\"0\")&\" days\"& IF(MOD((O1587-M1587)*24,24)>0,\" + \" & ROUNDDOWN((O1587-M1587)*24,0) & \" h \" & ROUNDDOWN(MOD((O1587-M1587)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57050",null,"< >",1117,1128,2026,2026,{"$f":"WEEKNUM(L1588)+[7]dates!$L$3-[7]dates!$H$3","v":39},{"$f":"WEEKNUM(N1588)+[7]dates!$L$3-[7]dates!$H$3","v":46},"2026-09-21","00:00:00","2026-11-08",0.99998842592592585,{"$f":"TEXT(N1588-L1588+ROUNDDOWN(O1588-M1588,0),\"0\")&\" days\"& IF(MOD((O1588-M1588)*24,24)>0,\" + \" & ROUNDDOWN((O1588-M1588)*24,0) & \" h \" & ROUNDDOWN(MOD((O1588-M1588)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A57050",null,"< >",1117,1128,2026,2026,{"$f":"WEEKNUM(L1589)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1589)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-10-05","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1589-L1589+ROUNDDOWN(O1589-M1589,0),\"0\")&\" days\"& IF(MOD((O1589-M1589)*24,24)>0,\" + \" & ROUNDDOWN((O1589-M1589)*24,0) & \" h \" & ROUNDDOWN(MOD((O1589-M1589)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57762",null,"< >",1123,1135,2026,2026,{"$f":"WEEKNUM(L1590)+[7]dates!$L$3-[7]dates!$H$3","v":32},{"$f":"WEEKNUM(N1590)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-08-03","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1590-L1590+ROUNDDOWN(O1590-M1590,0),\"0\")&\" days\"& IF(MOD((O1590-M1590)*24,24)>0,\" + \" & ROUNDDOWN((O1590-M1590)*24,0) & \" h \" & ROUNDDOWN(MOD((O1590-M1590)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F49920",null,"< >",1155,1114,2026,2026,{"$f":"WEEKNUM(L1591)+[7]dates!$L$3-[7]dates!$H$3","v":27},{"$f":"WEEKNUM(N1591)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-06-29","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N1591-L1591+ROUNDDOWN(O1591-M1591,0),\"0\")&\" days\"& IF(MOD((O1591-M1591)*24,24)>0,\" + \" & ROUNDDOWN((O1591-M1591)*24,0) & \" h \" & ROUNDDOWN(MOD((O1591-M1591)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58349",null,"< >",1160,1114,2026,2026,{"$f":"WEEKNUM(L1592)+[7]dates!$L$3-[7]dates!$H$3","v":27},{"$f":"WEEKNUM(N1592)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-06-29","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N1592-L1592+ROUNDDOWN(O1592-M1592,0),\"0\")&\" days\"& IF(MOD((O1592-M1592)*24,24)>0,\" + \" & ROUNDDOWN((O1592-M1592)*24,0) & \" h \" & ROUNDDOWN(MOD((O1592-M1592)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58350",null,"< >",1160,1160,2026,2026,{"$f":"WEEKNUM(L1593)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1593)+[7]dates!$L$3-[7]dates!$H$3","v":18},"2026-03-02","00:00:00","2026-04-26",0.99998842592592585,{"$f":"TEXT(N1593-L1593+ROUNDDOWN(O1593-M1593,0),\"0\")&\" days\"& IF(MOD((O1593-M1593)*24,24)>0,\" + \" & ROUNDDOWN((O1593-M1593)*24,0) & \" h \" & ROUNDDOWN(MOD((O1593-M1593)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58350",null,"< >",1160,1160,2026,2026,{"$f":"WEEKNUM(L1594)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1594)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-03-02","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1594-L1594+ROUNDDOWN(O1594-M1594,0),\"0\")&\" days\"& IF(MOD((O1594-M1594)*24,24)>0,\" + \" & ROUNDDOWN((O1594-M1594)*24,0) & \" h \" & ROUNDDOWN(MOD((O1594-M1594)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B58350",null,"< >",1160,1160,2026,2026,{"$f":"WEEKNUM(L1595)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1595)+[7]dates!$L$3-[7]dates!$H$3","v":18},"2026-03-30","00:00:00","2026-04-26",0.99998842592592585,{"$f":"TEXT(N1595-L1595+ROUNDDOWN(O1595-M1595,0),\"0\")&\" days\"& IF(MOD((O1595-M1595)*24,24)>0,\" + \" & ROUNDDOWN((O1595-M1595)*24,0) & \" h \" & ROUNDDOWN(MOD((O1595-M1595)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C58350",null,"< >",1161,8044,2026,2026,{"$f":"WEEKNUM(L1596)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1596)+[7]dates!$L$3-[7]dates!$H$3","v":18},"2026-03-02","00:00:00","2026-04-26",0.99998842592592585,{"$f":"TEXT(N1596-L1596+ROUNDDOWN(O1596-M1596,0),\"0\")&\" days\"& IF(MOD((O1596-M1596)*24,24)>0,\" + \" & ROUNDDOWN((O1596-M1596)*24,0) & \" h \" & ROUNDDOWN(MOD((O1596-M1596)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D58350",null,"< >",1161,8044,2026,2026,{"$f":"WEEKNUM(L1597)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1597)+[7]dates!$L$3-[7]dates!$H$3","v":16},"2026-03-16","00:00:00","2026-04-12",0.99998842592592585,{"$f":"TEXT(N1597-L1597+ROUNDDOWN(O1597-M1597,0),\"0\")&\" days\"& IF(MOD((O1597-M1597)*24,24)>0,\" + \" & ROUNDDOWN((O1597-M1597)*24,0) & \" h \" & ROUNDDOWN(MOD((O1597-M1597)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","H58350",null,"< >",1161,8044,2026,2026,{"$f":"WEEKNUM(L1598)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1598)+[7]dates!$L$3-[7]dates!$H$3","v":16},"2026-03-16","00:00:00","2026-04-12",0.99998842592592585,{"$f":"TEXT(N1598-L1598+ROUNDDOWN(O1598-M1598,0),\"0\")&\" days\"& IF(MOD((O1598-M1598)*24,24)>0,\" + \" & ROUNDDOWN((O1598-M1598)*24,0) & \" h \" & ROUNDDOWN(MOD((O1598-M1598)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62430",null,"< >",1165,1167,2026,2026,{"$f":"WEEKNUM(L1599)+[7]dates!$L$3-[7]dates!$H$3","v":43},{"$f":"WEEKNUM(N1599)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-10-19","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1599-L1599+ROUNDDOWN(O1599-M1599,0),\"0\")&\" days\"& IF(MOD((O1599-M1599)*24,24)>0,\" + \" & ROUNDDOWN((O1599-M1599)*24,0) & \" h \" & ROUNDDOWN(MOD((O1599-M1599)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R"," JJ7620 et JJ7622",null,"< >",1176,1176,2026,2026,{"$f":"WEEKNUM(L1600)+[7]dates!$L$3-[7]dates!$H$3","v":28},{"$f":"WEEKNUM(N1600)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-07-06","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1600-L1600+ROUNDDOWN(O1600-M1600,0),\"0\")&\" days\"& IF(MOD((O1600-M1600)*24,24)>0,\" + \" & ROUNDDOWN((O1600-M1600)*24,0) & \" h \" & ROUNDDOWN(MOD((O1600-M1600)*1440,60),0) & \" min\",\"\")","v":"146 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F50761",null,"< >",1177,1177,2026,2026,{"$f":"WEEKNUM(L1601)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1601)+[7]dates!$L$3-[7]dates!$H$3","v":10},"2026-01-05","00:00:00","2026-03-01",0.99998842592592585,{"$f":"TEXT(N1601-L1601+ROUNDDOWN(O1601-M1601,0),\"0\")&\" days\"& IF(MOD((O1601-M1601)*24,24)>0,\" + \" & ROUNDDOWN((O1601-M1601)*24,0) & \" h \" & ROUNDDOWN(MOD((O1601-M1601)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH3682",null,"< >",1240,1253,2026,2026,{"$f":"WEEKNUM(L1602)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1602)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-16","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1602-L1602+ROUNDDOWN(O1602-M1602,0),\"0\")&\" days\"& IF(MOD((O1602-M1602)*24,24)>0,\" + \" & ROUNDDOWN((O1602-M1602)*24,0) & \" h \" & ROUNDDOWN(MOD((O1602-M1602)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH3682",null,"< >",1240,1253,2026,2026,{"$f":"WEEKNUM(L1603)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1603)+[7]dates!$L$3-[7]dates!$H$3","v":38},"2026-05-18","00:00:00","2026-09-13",0.99998842592592585,{"$f":"TEXT(N1603-L1603+ROUNDDOWN(O1603-M1603,0),\"0\")&\" days\"& IF(MOD((O1603-M1603)*24,24)>0,\" + \" & ROUNDDOWN((O1603-M1603)*24,0) & \" h \" & ROUNDDOWN(MOD((O1603-M1603)*1440,60),0) & \" min\",\"\")","v":"118 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58415",null,"< >",1245,1051,2026,2026,{"$f":"WEEKNUM(L1604)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1604)+[7]dates!$L$3-[7]dates!$H$3","v":41},"2026-03-30","00:00:00","2026-10-04",0.99998842592592585,{"$f":"TEXT(N1604-L1604+ROUNDDOWN(O1604-M1604,0),\"0\")&\" days\"& IF(MOD((O1604-M1604)*24,24)>0,\" + \" & ROUNDDOWN((O1604-M1604)*24,0) & \" h \" & ROUNDDOWN(MOD((O1604-M1604)*1440,60),0) & \" min\",\"\")","v":"188 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F51102",null,"< >",1252,1074,2026,2026,{"$f":"WEEKNUM(L1605)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1605)+[7]dates!$L$3-[7]dates!$H$3","v":41},"2026-03-30","00:00:00","2026-10-04",0.99998842592592585,{"$f":"TEXT(N1605-L1605+ROUNDDOWN(O1605-M1605,0),\"0\")&\" days\"& IF(MOD((O1605-M1605)*24,24)>0,\" + \" & ROUNDDOWN((O1605-M1605)*24,0) & \" h \" & ROUNDDOWN(MOD((O1605-M1605)*1440,60),0) & \" min\",\"\")","v":"188 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58986",null,"< >",1281,1283,2026,2026,{"$f":"WEEKNUM(L1606)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1606)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-03-30","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N1606-L1606+ROUNDDOWN(O1606-M1606,0),\"0\")&\" days\"& IF(MOD((O1606-M1606)*24,24)>0,\" + \" & ROUNDDOWN((O1606-M1606)*24,0) & \" h \" & ROUNDDOWN(MOD((O1606-M1606)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F48453",null,"< >",1293,1297,2026,2026,{"$f":"WEEKNUM(L1607)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1607)+[7]dates!$L$3-[7]dates!$H$3","v":6},"2026-01-19","00:00:00","2026-02-01",0.99998842592592585,{"$f":"TEXT(N1607-L1607+ROUNDDOWN(O1607-M1607,0),\"0\")&\" days\"& IF(MOD((O1607-M1607)*24,24)>0,\" + \" & ROUNDDOWN((O1607-M1607)*24,0) & \" h \" & ROUNDDOWN(MOD((O1607-M1607)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A48453",null,"< >",1293,1297,2026,2026,{"$f":"WEEKNUM(L1608)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1608)+[7]dates!$L$3-[7]dates!$H$3","v":9},"2026-02-09","00:00:00","2026-02-22",0.99998842592592585,{"$f":"TEXT(N1608-L1608+ROUNDDOWN(O1608-M1608,0),\"0\")&\" days\"& IF(MOD((O1608-M1608)*24,24)>0,\" + \" & ROUNDDOWN((O1608-M1608)*24,0) & \" h \" & ROUNDDOWN(MOD((O1608-M1608)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B48453",null,"< >",1293,1297,2026,2026,{"$f":"WEEKNUM(L1609)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1609)+[7]dates!$L$3-[7]dates!$H$3","v":21},"2026-02-23","00:00:00","2026-05-17",0.99998842592592585,{"$f":"TEXT(N1609-L1609+ROUNDDOWN(O1609-M1609,0),\"0\")&\" days\"& IF(MOD((O1609-M1609)*24,24)>0,\" + \" & ROUNDDOWN((O1609-M1609)*24,0) & \" h \" & ROUNDDOWN(MOD((O1609-M1609)*1440,60),0) & \" min\",\"\")","v":"83 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F61976",null,"< >",1308,1310,2026,2026,{"$f":"WEEKNUM(L1610)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1610)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-05","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1610-L1610+ROUNDDOWN(O1610-M1610,0),\"0\")&\" days\"& IF(MOD((O1610-M1610)*24,24)>0,\" + \" & ROUNDDOWN((O1610-M1610)*24,0) & \" h \" & ROUNDDOWN(MOD((O1610-M1610)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A61976",null,"< >",1308,1310,2026,2026,{"$f":"WEEKNUM(L1611)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1611)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-02-23","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1611-L1611+ROUNDDOWN(O1611-M1611,0),\"0\")&\" days\"& IF(MOD((O1611-M1611)*24,24)>0,\" + \" & ROUNDDOWN((O1611-M1611)*24,0) & \" h \" & ROUNDDOWN(MOD((O1611-M1611)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B61976",null,"< >",1308,1310,2026,2026,{"$f":"WEEKNUM(L1612)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N1612)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-23","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1612-L1612+ROUNDDOWN(O1612-M1612,0),\"0\")&\" days\"& IF(MOD((O1612-M1612)*24,24)>0,\" + \" & ROUNDDOWN((O1612-M1612)*24,0) & \" h \" & ROUNDDOWN(MOD((O1612-M1612)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C61976",null,"< >",1308,1310,2026,2026,{"$f":"WEEKNUM(L1613)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N1613)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-06-01","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1613-L1613+ROUNDDOWN(O1613-M1613,0),\"0\")&\" days\"& IF(MOD((O1613-M1613)*24,24)>0,\" + \" & ROUNDDOWN((O1613-M1613)*24,0) & \" h \" & ROUNDDOWN(MOD((O1613-M1613)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F54990",null,"< >",1395,882,2026,2026,{"$f":"WEEKNUM(L1614)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N1614)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-02-02","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1614-L1614+ROUNDDOWN(O1614-M1614,0),\"0\")&\" days\"& IF(MOD((O1614-M1614)*24,24)>0,\" + \" & ROUNDDOWN((O1614-M1614)*24,0) & \" h \" & ROUNDDOWN(MOD((O1614-M1614)*1440,60),0) & \" min\",\"\")","v":"146 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F66043",null,"< >",1532,1535,2026,2026,{"$f":"WEEKNUM(L1615)+[7]dates!$L$3-[7]dates!$H$3","v":32},{"$f":"WEEKNUM(N1615)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-08-03","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1615-L1615+ROUNDDOWN(O1615-M1615,0),\"0\")&\" days\"& IF(MOD((O1615-M1615)*24,24)>0,\" + \" & ROUNDDOWN((O1615-M1615)*24,0) & \" h \" & ROUNDDOWN(MOD((O1615-M1615)*1440,60),0) & \" min\",\"\")","v":"125 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R"," \tF66042 ",null,"< >",1554,1711,2026,2026,{"$f":"WEEKNUM(L1616)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1616)+[7]dates!$L$3-[7]dates!$H$3","v":16},"2026-02-16","00:00:00","2026-04-12",0.99998842592592585,{"$f":"TEXT(N1616-L1616+ROUNDDOWN(O1616-M1616,0),\"0\")&\" days\"& IF(MOD((O1616-M1616)*24,24)>0,\" + \" & ROUNDDOWN((O1616-M1616)*24,0) & \" h \" & ROUNDDOWN(MOD((O1616-M1616)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52841",null,"< >",1584,8691,2026,2026,{"$f":"WEEKNUM(L1617)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1617)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-02-09","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1617-L1617+ROUNDDOWN(O1617-M1617,0),\"0\")&\" days\"& IF(MOD((O1617-M1617)*24,24)>0,\" + \" & ROUNDDOWN((O1617-M1617)*24,0) & \" h \" & ROUNDDOWN(MOD((O1617-M1617)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A52841",null,"< >",1584,8691,2026,2026,{"$f":"WEEKNUM(L1618)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1618)+[7]dates!$L$3-[7]dates!$H$3","v":21},"2026-04-20","00:00:00","2026-05-17",0.99998842592592585,{"$f":"TEXT(N1618-L1618+ROUNDDOWN(O1618-M1618,0),\"0\")&\" days\"& IF(MOD((O1618-M1618)*24,24)>0,\" + \" & ROUNDDOWN((O1618-M1618)*24,0) & \" h \" & ROUNDDOWN(MOD((O1618-M1618)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","W54402",null,"< >",1613,1629,2026,2026,{"$f":"WEEKNUM(L1619)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1619)+[7]dates!$L$3-[7]dates!$H$3","v":37},"2026-01-26","00:00:00","2026-09-06",0.99998842592592585,{"$f":"TEXT(N1619-L1619+ROUNDDOWN(O1619-M1619,0),\"0\")&\" days\"& IF(MOD((O1619-M1619)*24,24)>0,\" + \" & ROUNDDOWN((O1619-M1619)*24,0) & \" h \" & ROUNDDOWN(MOD((O1619-M1619)*1440,60),0) & \" min\",\"\")","v":"223 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64707",null,"< >",1630,1640,2026,2026,{"$f":"WEEKNUM(L1620)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1620)+[7]dates!$L$3-[7]dates!$H$3","v":13},"2026-02-16","00:00:00","2026-03-22",0.99998842592592585,{"$f":"TEXT(N1620-L1620+ROUNDDOWN(O1620-M1620,0),\"0\")&\" days\"& IF(MOD((O1620-M1620)*24,24)>0,\" + \" & ROUNDDOWN((O1620-M1620)*24,0) & \" h \" & ROUNDDOWN(MOD((O1620-M1620)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F43590",null,"< >",1632,1633,2026,2026,{"$f":"WEEKNUM(L1621)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1621)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-05-04","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1621-L1621+ROUNDDOWN(O1621-M1621,0),\"0\")&\" days\"& IF(MOD((O1621-M1621)*24,24)>0,\" + \" & ROUNDDOWN((O1621-M1621)*24,0) & \" h \" & ROUNDDOWN(MOD((O1621-M1621)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F61019",null,"< >",1632,1633,2026,2026,{"$f":"WEEKNUM(L1622)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1622)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-01-26","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1622-L1622+ROUNDDOWN(O1622-M1622,0),\"0\")&\" days\"& IF(MOD((O1622-M1622)*24,24)>0,\" + \" & ROUNDDOWN((O1622-M1622)*24,0) & \" h \" & ROUNDDOWN(MOD((O1622-M1622)*1440,60),0) & \" min\",\"\")","v":"153 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F50331",null,"< >",1633,1632,2026,2026,{"$f":"WEEKNUM(L1623)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1623)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-01-26","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1623-L1623+ROUNDDOWN(O1623-M1623,0),\"0\")&\" days\"& IF(MOD((O1623-M1623)*24,24)>0,\" + \" & ROUNDDOWN((O1623-M1623)*24,0) & \" h \" & ROUNDDOWN(MOD((O1623-M1623)*1440,60),0) & \" min\",\"\")","v":"153 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F49858",null,"< >",1686,1714,2026,2026,{"$f":"WEEKNUM(L1624)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1624)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-01-05","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1624-L1624+ROUNDDOWN(O1624-M1624,0),\"0\")&\" days\"& IF(MOD((O1624-M1624)*24,24)>0,\" + \" & ROUNDDOWN((O1624-M1624)*24,0) & \" h \" & ROUNDDOWN(MOD((O1624-M1624)*1440,60),0) & \" min\",\"\")","v":"300 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58237",null,"< >",1690,1691,2026,2026,{"$f":"WEEKNUM(L1625)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1625)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-26","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1625-L1625+ROUNDDOWN(O1625-M1625,0),\"0\")&\" days\"& IF(MOD((O1625-M1625)*24,24)>0,\" + \" & ROUNDDOWN((O1625-M1625)*24,0) & \" h \" & ROUNDDOWN(MOD((O1625-M1625)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58237",null,"< >",1690,1691,2026,2026,{"$f":"WEEKNUM(L1626)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1626)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-05-11","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N1626-L1626+ROUNDDOWN(O1626-M1626,0),\"0\")&\" days\"& IF(MOD((O1626-M1626)*24,24)>0,\" + \" & ROUNDDOWN((O1626-M1626)*24,0) & \" h \" & ROUNDDOWN(MOD((O1626-M1626)*1440,60),0) & \" min\",\"\")","v":"104 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58693",null,"< >",1699,2429,2026,2026,{"$f":"WEEKNUM(L1627)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1627)+[7]dates!$L$3-[7]dates!$H$3","v":41},"2026-08-31","00:00:00","2026-10-04",0.99998842592592585,{"$f":"TEXT(N1627-L1627+ROUNDDOWN(O1627-M1627,0),\"0\")&\" days\"& IF(MOD((O1627-M1627)*24,24)>0,\" + \" & ROUNDDOWN((O1627-M1627)*24,0) & \" h \" & ROUNDDOWN(MOD((O1627-M1627)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52538",null,"< >",1703,1703,2026,2026,{"$f":"WEEKNUM(L1628)+[7]dates!$L$3-[7]dates!$H$3","v":39},{"$f":"WEEKNUM(N1628)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-09-21","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1628-L1628+ROUNDDOWN(O1628-M1628,0),\"0\")&\" days\"& IF(MOD((O1628-M1628)*24,24)>0,\" + \" & ROUNDDOWN((O1628-M1628)*24,0) & \" h \" & ROUNDDOWN(MOD((O1628-M1628)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63063",null,"< >",1718,1716,2026,2026,{"$f":"WEEKNUM(L1629)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1629)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-10-05","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1629-L1629+ROUNDDOWN(O1629-M1629,0),\"0\")&\" days\"& IF(MOD((O1629-M1629)*24,24)>0,\" + \" & ROUNDDOWN((O1629-M1629)*24,0) & \" h \" & ROUNDDOWN(MOD((O1629-M1629)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH3499",null,"< >",1719,1719,2026,2026,{"$f":"WEEKNUM(L1630)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N1630)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-02-02","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1630-L1630+ROUNDDOWN(O1630-M1630,0),\"0\")&\" days\"& IF(MOD((O1630-M1630)*24,24)>0,\" + \" & ROUNDDOWN((O1630-M1630)*24,0) & \" h \" & ROUNDDOWN(MOD((O1630-M1630)*1440,60),0) & \" min\",\"\")","v":"146 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F42906",null,"< >",1744,1743,2026,2026,{"$f":"WEEKNUM(L1631)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1631)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-02-16","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1631-L1631+ROUNDDOWN(O1631-M1631,0),\"0\")&\" days\"& IF(MOD((O1631-M1631)*24,24)>0,\" + \" & ROUNDDOWN((O1631-M1631)*24,0) & \" h \" & ROUNDDOWN(MOD((O1631-M1631)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JJ3255",null,"< >",1787,1787,2026,2026,{"$f":"WEEKNUM(L1632)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1632)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-02-16","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1632-L1632+ROUNDDOWN(O1632-M1632,0),\"0\")&\" days\"& IF(MOD((O1632-M1632)*24,24)>0,\" + \" & ROUNDDOWN((O1632-M1632)*24,0) & \" h \" & ROUNDDOWN(MOD((O1632-M1632)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AJ3255",null,"< >",1787,1787,2026,2026,{"$f":"WEEKNUM(L1633)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1633)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1633-L1633+ROUNDDOWN(O1633-M1633,0),\"0\")&\" days\"& IF(MOD((O1633-M1633)*24,24)>0,\" + \" & ROUNDDOWN((O1633-M1633)*24,0) & \" h \" & ROUNDDOWN(MOD((O1633-M1633)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65265",null,"< >",1816,709,2026,2026,{"$f":"WEEKNUM(L1634)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1634)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-19","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1634-L1634+ROUNDDOWN(O1634-M1634,0),\"0\")&\" days\"& IF(MOD((O1634-M1634)*24,24)>0,\" + \" & ROUNDDOWN((O1634-M1634)*24,0) & \" h \" & ROUNDDOWN(MOD((O1634-M1634)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A65265",null,"< >",1816,709,2026,2026,{"$f":"WEEKNUM(L1635)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1635)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-16","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1635-L1635+ROUNDDOWN(O1635-M1635,0),\"0\")&\" days\"& IF(MOD((O1635-M1635)*24,24)>0,\" + \" & ROUNDDOWN((O1635-M1635)*24,0) & \" h \" & ROUNDDOWN(MOD((O1635-M1635)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B65265",null,"< >",1816,709,2026,2026,{"$f":"WEEKNUM(L1636)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1636)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-05-11","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1636-L1636+ROUNDDOWN(O1636-M1636,0),\"0\")&\" days\"& IF(MOD((O1636-M1636)*24,24)>0,\" + \" & ROUNDDOWN((O1636-M1636)*24,0) & \" h \" & ROUNDDOWN(MOD((O1636-M1636)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C65265",null,"< >",1816,709,2026,2026,{"$f":"WEEKNUM(L1637)+[7]dates!$L$3-[7]dates!$H$3","v":22},{"$f":"WEEKNUM(N1637)+[7]dates!$L$3-[7]dates!$H$3","v":39},"2026-05-25","00:00:00","2026-09-20",0.99998842592592585,{"$f":"TEXT(N1637-L1637+ROUNDDOWN(O1637-M1637,0),\"0\")&\" days\"& IF(MOD((O1637-M1637)*24,24)>0,\" + \" & ROUNDDOWN((O1637-M1637)*24,0) & \" h \" & ROUNDDOWN(MOD((O1637-M1637)*1440,60),0) & \" min\",\"\")","v":"118 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D65265",null,"< >",1816,709,2026,2026,{"$f":"WEEKNUM(L1638)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1638)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-28","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1638-L1638+ROUNDDOWN(O1638-M1638,0),\"0\")&\" days\"& IF(MOD((O1638-M1638)*24,24)>0,\" + \" & ROUNDDOWN((O1638-M1638)*24,0) & \" h \" & ROUNDDOWN(MOD((O1638-M1638)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","N65265",null,"< >",1816,709,2026,2026,{"$f":"WEEKNUM(L1639)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N1639)+[7]dates!$L$3-[7]dates!$H$3","v":39},"2026-06-01","00:00:00","2026-09-20",0.99998842592592585,{"$f":"TEXT(N1639-L1639+ROUNDDOWN(O1639-M1639,0),\"0\")&\" days\"& IF(MOD((O1639-M1639)*24,24)>0,\" + \" & ROUNDDOWN((O1639-M1639)*24,0) & \" h \" & ROUNDDOWN(MOD((O1639-M1639)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58107",null,"< >",1843,1840,2026,2026,{"$f":"WEEKNUM(L1640)+[7]dates!$L$3-[7]dates!$H$3","v":16},{"$f":"WEEKNUM(N1640)+[7]dates!$L$3-[7]dates!$H$3","v":21},"2026-04-13","00:00:00","2026-05-17",0.99998842592592585,{"$f":"TEXT(N1640-L1640+ROUNDDOWN(O1640-M1640,0),\"0\")&\" days\"& IF(MOD((O1640-M1640)*24,24)>0,\" + \" & ROUNDDOWN((O1640-M1640)*24,0) & \" h \" & ROUNDDOWN(MOD((O1640-M1640)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B50175",null,"< >",1934,2012,2026,2026,{"$f":"WEEKNUM(L1641)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1641)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-05-11","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1641-L1641+ROUNDDOWN(O1641-M1641,0),\"0\")&\" days\"& IF(MOD((O1641-M1641)*24,24)>0,\" + \" & ROUNDDOWN((O1641-M1641)*24,0) & \" h \" & ROUNDDOWN(MOD((O1641-M1641)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C50175",null,"< >",1934,2012,2026,2026,{"$f":"WEEKNUM(L1642)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1642)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-15","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1642-L1642+ROUNDDOWN(O1642-M1642,0),\"0\")&\" days\"& IF(MOD((O1642-M1642)*24,24)>0,\" + \" & ROUNDDOWN((O1642-M1642)*24,0) & \" h \" & ROUNDDOWN(MOD((O1642-M1642)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58057",null,"< >",1937,1942,2026,2026,{"$f":"WEEKNUM(L1643)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1643)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-11","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1643-L1643+ROUNDDOWN(O1643-M1643,0),\"0\")&\" days\"& IF(MOD((O1643-M1643)*24,24)>0,\" + \" & ROUNDDOWN((O1643-M1643)*24,0) & \" h \" & ROUNDDOWN(MOD((O1643-M1643)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58057",null,"< >",1945,1914,2026,2026,{"$f":"WEEKNUM(L1644)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1644)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-11","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1644-L1644+ROUNDDOWN(O1644-M1644,0),\"0\")&\" days\"& IF(MOD((O1644-M1644)*24,24)>0,\" + \" & ROUNDDOWN((O1644-M1644)*24,0) & \" h \" & ROUNDDOWN(MOD((O1644-M1644)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F54524",null,"< >",1953,1950,2026,2026,{"$f":"WEEKNUM(L1645)+[7]dates!$L$3-[7]dates!$H$3","v":16},{"$f":"WEEKNUM(N1645)+[7]dates!$L$3-[7]dates!$H$3","v":18},"2026-04-13","00:00:00","2026-04-26",0.99998842592592585,{"$f":"TEXT(N1645-L1645+ROUNDDOWN(O1645-M1645,0),\"0\")&\" days\"& IF(MOD((O1645-M1645)*24,24)>0,\" + \" & ROUNDDOWN((O1645-M1645)*24,0) & \" h \" & ROUNDDOWN(MOD((O1645-M1645)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","H54524",null,"< >",1953,1950,2026,2026,{"$f":"WEEKNUM(L1646)+[7]dates!$L$3-[7]dates!$H$3","v":27},{"$f":"WEEKNUM(N1646)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-06-29","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1646-L1646+ROUNDDOWN(O1646-M1646,0),\"0\")&\" days\"& IF(MOD((O1646-M1646)*24,24)>0,\" + \" & ROUNDDOWN((O1646-M1646)*24,0) & \" h \" & ROUNDDOWN(MOD((O1646-M1646)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","K54524",null,"< >",1953,1950,2026,2026,{"$f":"WEEKNUM(L1647)+[7]dates!$L$3-[7]dates!$H$3","v":38},{"$f":"WEEKNUM(N1647)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-09-14","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N1647-L1647+ROUNDDOWN(O1647-M1647,0),\"0\")&\" days\"& IF(MOD((O1647-M1647)*24,24)>0,\" + \" & ROUNDDOWN((O1647-M1647)*24,0) & \" h \" & ROUNDDOWN(MOD((O1647-M1647)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A54524",null,"< >",1953,1950,2026,2026,{"$f":"WEEKNUM(L1648)+[7]dates!$L$3-[7]dates!$H$3","v":38},{"$f":"WEEKNUM(N1648)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-09-14","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1648-L1648+ROUNDDOWN(O1648-M1648,0),\"0\")&\" days\"& IF(MOD((O1648-M1648)*24,24)>0,\" + \" & ROUNDDOWN((O1648-M1648)*24,0) & \" h \" & ROUNDDOWN(MOD((O1648-M1648)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","FB54524",null,"< >",1953,1950,2026,2026,{"$f":"WEEKNUM(L1649)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1649)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-09-28","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N1649-L1649+ROUNDDOWN(O1649-M1649,0),\"0\")&\" days\"& IF(MOD((O1649-M1649)*24,24)>0,\" + \" & ROUNDDOWN((O1649-M1649)*24,0) & \" h \" & ROUNDDOWN(MOD((O1649-M1649)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C54524",null,"< >",1953,1950,2026,2026,{"$f":"WEEKNUM(L1650)+[7]dates!$L$3-[7]dates!$H$3","v":38},{"$f":"WEEKNUM(N1650)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-09-14","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1650-L1650+ROUNDDOWN(O1650-M1650,0),\"0\")&\" days\"& IF(MOD((O1650-M1650)*24,24)>0,\" + \" & ROUNDDOWN((O1650-M1650)*24,0) & \" h \" & ROUNDDOWN(MOD((O1650-M1650)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D54524",null,"< >",1953,1950,2026,2026,{"$f":"WEEKNUM(L1651)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1651)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-09-28","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N1651-L1651+ROUNDDOWN(O1651-M1651,0),\"0\")&\" days\"& IF(MOD((O1651-M1651)*24,24)>0,\" + \" & ROUNDDOWN((O1651-M1651)*24,0) & \" h \" & ROUNDDOWN(MOD((O1651-M1651)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F61386",null,"< >",2013,2013,2026,2026,{"$f":"WEEKNUM(L1652)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1652)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-19","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1652-L1652+ROUNDDOWN(O1652-M1652,0),\"0\")&\" days\"& IF(MOD((O1652-M1652)*24,24)>0,\" + \" & ROUNDDOWN((O1652-M1652)*24,0) & \" h \" & ROUNDDOWN(MOD((O1652-M1652)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A61386",null,"< >",2013,2013,2026,2026,{"$f":"WEEKNUM(L1653)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1653)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-16","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1653-L1653+ROUNDDOWN(O1653-M1653,0),\"0\")&\" days\"& IF(MOD((O1653-M1653)*24,24)>0,\" + \" & ROUNDDOWN((O1653-M1653)*24,0) & \" h \" & ROUNDDOWN(MOD((O1653-M1653)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B61386",null,"< >",2013,2013,2026,2026,{"$f":"WEEKNUM(L1654)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1654)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-28","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1654-L1654+ROUNDDOWN(O1654-M1654,0),\"0\")&\" days\"& IF(MOD((O1654-M1654)*24,24)>0,\" + \" & ROUNDDOWN((O1654-M1654)*24,0) & \" h \" & ROUNDDOWN(MOD((O1654-M1654)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58088",null,"< >",2025,8133,2026,2026,{"$f":"WEEKNUM(L1655)+[7]dates!$L$3-[7]dates!$H$3","v":31},{"$f":"WEEKNUM(N1655)+[7]dates!$L$3-[7]dates!$H$3","v":41},"2026-07-27","00:00:00","2026-10-04",0.99998842592592585,{"$f":"TEXT(N1655-L1655+ROUNDDOWN(O1655-M1655,0),\"0\")&\" days\"& IF(MOD((O1655-M1655)*24,24)>0,\" + \" & ROUNDDOWN((O1655-M1655)*24,0) & \" h \" & ROUNDDOWN(MOD((O1655-M1655)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F53229",null,"< >",2046,2046,2026,2026,{"$f":"WEEKNUM(L1656)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1656)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-06-22","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1656-L1656+ROUNDDOWN(O1656-M1656,0),\"0\")&\" days\"& IF(MOD((O1656-M1656)*24,24)>0,\" + \" & ROUNDDOWN((O1656-M1656)*24,0) & \" h \" & ROUNDDOWN(MOD((O1656-M1656)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F46802",null,"< >",2068,2056,2026,2026,{"$f":"WEEKNUM(L1657)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1657)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-01-19","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1657-L1657+ROUNDDOWN(O1657-M1657,0),\"0\")&\" days\"& IF(MOD((O1657-M1657)*24,24)>0,\" + \" & ROUNDDOWN((O1657-M1657)*24,0) & \" h \" & ROUNDDOWN(MOD((O1657-M1657)*1440,60),0) & \" min\",\"\")","v":"195 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A46802",null,"< >",2068,2056,2026,2026,{"$f":"WEEKNUM(L1658)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1658)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-28","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1658-L1658+ROUNDDOWN(O1658-M1658,0),\"0\")&\" days\"& IF(MOD((O1658-M1658)*24,24)>0,\" + \" & ROUNDDOWN((O1658-M1658)*24,0) & \" h \" & ROUNDDOWN(MOD((O1658-M1658)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B46802",null,"< >",2068,2056,2026,2026,{"$f":"WEEKNUM(L1659)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N1659)+[7]dates!$L$3-[7]dates!$H$3","v":9},"2026-02-02","00:00:00","2026-02-22",0.99998842592592585,{"$f":"TEXT(N1659-L1659+ROUNDDOWN(O1659-M1659,0),\"0\")&\" days\"& IF(MOD((O1659-M1659)*24,24)>0,\" + \" & ROUNDDOWN((O1659-M1659)*24,0) & \" h \" & ROUNDDOWN(MOD((O1659-M1659)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C46802",null,"< >",2068,2056,2026,2026,{"$f":"WEEKNUM(L1660)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1660)+[7]dates!$L$3-[7]dates!$H$3","v":13},"2026-02-23","00:00:00","2026-03-22",0.99998842592592585,{"$f":"TEXT(N1660-L1660+ROUNDDOWN(O1660-M1660,0),\"0\")&\" days\"& IF(MOD((O1660-M1660)*24,24)>0,\" + \" & ROUNDDOWN((O1660-M1660)*24,0) & \" h \" & ROUNDDOWN(MOD((O1660-M1660)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D46802",null,"< >",2068,2056,2026,2026,{"$f":"WEEKNUM(L1661)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1661)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-03-30","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1661-L1661+ROUNDDOWN(O1661-M1661,0),\"0\")&\" days\"& IF(MOD((O1661-M1661)*24,24)>0,\" + \" & ROUNDDOWN((O1661-M1661)*24,0) & \" h \" & ROUNDDOWN(MOD((O1661-M1661)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","H46802",null,"< >",2068,2056,2026,2026,{"$f":"WEEKNUM(L1662)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1662)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-06-15","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1662-L1662+ROUNDDOWN(O1662-M1662,0),\"0\")&\" days\"& IF(MOD((O1662-M1662)*24,24)>0,\" + \" & ROUNDDOWN((O1662-M1662)*24,0) & \" h \" & ROUNDDOWN(MOD((O1662-M1662)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","K46802",null,"< >",2068,2056,2026,2026,{"$f":"WEEKNUM(L1663)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N1663)+[7]dates!$L$3-[7]dates!$H$3","v":9},"2026-02-02","00:00:00","2026-02-22",0.99998842592592585,{"$f":"TEXT(N1663-L1663+ROUNDDOWN(O1663-M1663,0),\"0\")&\" days\"& IF(MOD((O1663-M1663)*24,24)>0,\" + \" & ROUNDDOWN((O1663-M1663)*24,0) & \" h \" & ROUNDDOWN(MOD((O1663-M1663)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","L46802",null,"< >",2068,2056,2026,2026,{"$f":"WEEKNUM(L1664)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1664)+[7]dates!$L$3-[7]dates!$H$3","v":13},"2026-02-23","00:00:00","2026-03-22",0.99998842592592585,{"$f":"TEXT(N1664-L1664+ROUNDDOWN(O1664-M1664,0),\"0\")&\" days\"& IF(MOD((O1664-M1664)*24,24)>0,\" + \" & ROUNDDOWN((O1664-M1664)*24,0) & \" h \" & ROUNDDOWN(MOD((O1664-M1664)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","M46802",null,"< >",2068,2056,2026,2026,{"$f":"WEEKNUM(L1665)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1665)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-03-30","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1665-L1665+ROUNDDOWN(O1665-M1665,0),\"0\")&\" days\"& IF(MOD((O1665-M1665)*24,24)>0,\" + \" & ROUNDDOWN((O1665-M1665)*24,0) & \" h \" & ROUNDDOWN(MOD((O1665-M1665)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","N46802",null,"< >",2068,2056,2026,2026,{"$f":"WEEKNUM(L1666)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1666)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-06-15","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1666-L1666+ROUNDDOWN(O1666-M1666,0),\"0\")&\" days\"& IF(MOD((O1666-M1666)*24,24)>0,\" + \" & ROUNDDOWN((O1666-M1666)*24,0) & \" h \" & ROUNDDOWN(MOD((O1666-M1666)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64769",null,"< >",2083,8140,2026,2026,{"$f":"WEEKNUM(L1667)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1667)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-19","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1667-L1667+ROUNDDOWN(O1667-M1667,0),\"0\")&\" days\"& IF(MOD((O1667-M1667)*24,24)>0,\" + \" & ROUNDDOWN((O1667-M1667)*24,0) & \" h \" & ROUNDDOWN(MOD((O1667-M1667)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A64769",null,"< >",2083,8140,2026,2026,{"$f":"WEEKNUM(L1668)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1668)+[7]dates!$L$3-[7]dates!$H$3","v":23},"2026-03-16","00:00:00","2026-05-31",0.99998842592592585,{"$f":"TEXT(N1668-L1668+ROUNDDOWN(O1668-M1668,0),\"0\")&\" days\"& IF(MOD((O1668-M1668)*24,24)>0,\" + \" & ROUNDDOWN((O1668-M1668)*24,0) & \" h \" & ROUNDDOWN(MOD((O1668-M1668)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B64769",null,"< >",2083,8140,2026,2026,{"$f":"WEEKNUM(L1669)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N1669)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-06-01","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1669-L1669+ROUNDDOWN(O1669-M1669,0),\"0\")&\" days\"& IF(MOD((O1669-M1669)*24,24)>0,\" + \" & ROUNDDOWN((O1669-M1669)*24,0) & \" h \" & ROUNDDOWN(MOD((O1669-M1669)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C64769",null,"< >",2083,8140,2026,2026,{"$f":"WEEKNUM(L1670)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1670)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-28","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1670-L1670+ROUNDDOWN(O1670-M1670,0),\"0\")&\" days\"& IF(MOD((O1670-M1670)*24,24)>0,\" + \" & ROUNDDOWN((O1670-M1670)*24,0) & \" h \" & ROUNDDOWN(MOD((O1670-M1670)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F39756",null,"< >",2106,2057,2026,2026,{"$f":"WEEKNUM(L1671)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1671)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-02-16","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1671-L1671+ROUNDDOWN(O1671-M1671,0),\"0\")&\" days\"& IF(MOD((O1671-M1671)*24,24)>0,\" + \" & ROUNDDOWN((O1671-M1671)*24,0) & \" h \" & ROUNDDOWN(MOD((O1671-M1671)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A65625",null,"< >",2115,8142,2026,2026,{"$f":"WEEKNUM(L1672)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1672)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-06-15","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1672-L1672+ROUNDDOWN(O1672-M1672,0),\"0\")&\" days\"& IF(MOD((O1672-M1672)*24,24)>0,\" + \" & ROUNDDOWN((O1672-M1672)*24,0) & \" h \" & ROUNDDOWN(MOD((O1672-M1672)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F47156",null,"< >",2120,2141,2026,2026,{"$f":"WEEKNUM(L1673)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1673)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-02-16","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1673-L1673+ROUNDDOWN(O1673-M1673,0),\"0\")&\" days\"& IF(MOD((O1673-M1673)*24,24)>0,\" + \" & ROUNDDOWN((O1673-M1673)*24,0) & \" h \" & ROUNDDOWN(MOD((O1673-M1673)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A47156",null,"< >",2120,2141,2026,2026,{"$f":"WEEKNUM(L1674)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1674)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1674-L1674+ROUNDDOWN(O1674-M1674,0),\"0\")&\" days\"& IF(MOD((O1674-M1674)*24,24)>0,\" + \" & ROUNDDOWN((O1674-M1674)*24,0) & \" h \" & ROUNDDOWN(MOD((O1674-M1674)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B47156",null,"< >",2120,2141,2026,2026,{"$f":"WEEKNUM(L1675)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N1675)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-07-20","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1675-L1675+ROUNDDOWN(O1675-M1675,0),\"0\")&\" days\"& IF(MOD((O1675-M1675)*24,24)>0,\" + \" & ROUNDDOWN((O1675-M1675)*24,0) & \" h \" & ROUNDDOWN(MOD((O1675-M1675)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C47156",null,"< >",2120,2141,2026,2026,{"$f":"WEEKNUM(L1676)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1676)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-02-16","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1676-L1676+ROUNDDOWN(O1676-M1676,0),\"0\")&\" days\"& IF(MOD((O1676-M1676)*24,24)>0,\" + \" & ROUNDDOWN((O1676-M1676)*24,0) & \" h \" & ROUNDDOWN(MOD((O1676-M1676)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D47156",null,"< >",2120,2141,2026,2026,{"$f":"WEEKNUM(L1677)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1677)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1677-L1677+ROUNDDOWN(O1677-M1677,0),\"0\")&\" days\"& IF(MOD((O1677-M1677)*24,24)>0,\" + \" & ROUNDDOWN((O1677-M1677)*24,0) & \" h \" & ROUNDDOWN(MOD((O1677-M1677)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","H47156",null,"< >",2120,2141,2026,2026,{"$f":"WEEKNUM(L1678)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N1678)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-07-20","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1678-L1678+ROUNDDOWN(O1678-M1678,0),\"0\")&\" days\"& IF(MOD((O1678-M1678)*24,24)>0,\" + \" & ROUNDDOWN((O1678-M1678)*24,0) & \" h \" & ROUNDDOWN(MOD((O1678-M1678)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","K47156",null,"< >",2120,2141,2026,2026,{"$f":"WEEKNUM(L1679)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1679)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-02-16","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1679-L1679+ROUNDDOWN(O1679-M1679,0),\"0\")&\" days\"& IF(MOD((O1679-M1679)*24,24)>0,\" + \" & ROUNDDOWN((O1679-M1679)*24,0) & \" h \" & ROUNDDOWN(MOD((O1679-M1679)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","L47156",null,"< >",2120,2141,2026,2026,{"$f":"WEEKNUM(L1680)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1680)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1680-L1680+ROUNDDOWN(O1680-M1680,0),\"0\")&\" days\"& IF(MOD((O1680-M1680)*24,24)>0,\" + \" & ROUNDDOWN((O1680-M1680)*24,0) & \" h \" & ROUNDDOWN(MOD((O1680-M1680)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","M47156",null,"< >",2120,2141,2026,2026,{"$f":"WEEKNUM(L1681)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N1681)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-07-20","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1681-L1681+ROUNDDOWN(O1681-M1681,0),\"0\")&\" days\"& IF(MOD((O1681-M1681)*24,24)>0,\" + \" & ROUNDDOWN((O1681-M1681)*24,0) & \" h \" & ROUNDDOWN(MOD((O1681-M1681)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F48779",null,"< >",2126,2127,2026,2026,{"$f":"WEEKNUM(L1682)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1682)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-03-09","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1682-L1682+ROUNDDOWN(O1682-M1682,0),\"0\")&\" days\"& IF(MOD((O1682-M1682)*24,24)>0,\" + \" & ROUNDDOWN((O1682-M1682)*24,0) & \" h \" & ROUNDDOWN(MOD((O1682-M1682)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A48779",null,"< >",2126,2127,2026,2026,{"$f":"WEEKNUM(L1683)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1683)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1683-L1683+ROUNDDOWN(O1683-M1683,0),\"0\")&\" days\"& IF(MOD((O1683-M1683)*24,24)>0,\" + \" & ROUNDDOWN((O1683-M1683)*24,0) & \" h \" & ROUNDDOWN(MOD((O1683-M1683)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B48779",null,"< >",2126,2127,2026,2026,{"$f":"WEEKNUM(L1684)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N1684)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-07-20","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1684-L1684+ROUNDDOWN(O1684-M1684,0),\"0\")&\" days\"& IF(MOD((O1684-M1684)*24,24)>0,\" + \" & ROUNDDOWN((O1684-M1684)*24,0) & \" h \" & ROUNDDOWN(MOD((O1684-M1684)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C48779",null,"< >",2126,2127,2026,2026,{"$f":"WEEKNUM(L1685)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1685)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1685-L1685+ROUNDDOWN(O1685-M1685,0),\"0\")&\" days\"& IF(MOD((O1685-M1685)*24,24)>0,\" + \" & ROUNDDOWN((O1685-M1685)*24,0) & \" h \" & ROUNDDOWN(MOD((O1685-M1685)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D48779",null,"< >",2126,2127,2026,2026,{"$f":"WEEKNUM(L1686)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1686)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1686-L1686+ROUNDDOWN(O1686-M1686,0),\"0\")&\" days\"& IF(MOD((O1686-M1686)*24,24)>0,\" + \" & ROUNDDOWN((O1686-M1686)*24,0) & \" h \" & ROUNDDOWN(MOD((O1686-M1686)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58996",null,"< >",2141,2130,2026,2026,{"$f":"WEEKNUM(L1687)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1687)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-02-16","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1687-L1687+ROUNDDOWN(O1687-M1687,0),\"0\")&\" days\"& IF(MOD((O1687-M1687)*24,24)>0,\" + \" & ROUNDDOWN((O1687-M1687)*24,0) & \" h \" & ROUNDDOWN(MOD((O1687-M1687)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58996",null,"< >",2141,2130,2026,2026,{"$f":"WEEKNUM(L1688)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1688)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1688-L1688+ROUNDDOWN(O1688-M1688,0),\"0\")&\" days\"& IF(MOD((O1688-M1688)*24,24)>0,\" + \" & ROUNDDOWN((O1688-M1688)*24,0) & \" h \" & ROUNDDOWN(MOD((O1688-M1688)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B58996",null,"< >",2141,2130,2026,2026,{"$f":"WEEKNUM(L1689)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N1689)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-07-20","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1689-L1689+ROUNDDOWN(O1689-M1689,0),\"0\")&\" days\"& IF(MOD((O1689-M1689)*24,24)>0,\" + \" & ROUNDDOWN((O1689-M1689)*24,0) & \" h \" & ROUNDDOWN(MOD((O1689-M1689)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C58996",null,"< >",2141,2130,2026,2026,{"$f":"WEEKNUM(L1690)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1690)+[7]dates!$L$3-[7]dates!$H$3","v":12},"2026-02-23","00:00:00","2026-03-15",0.99998842592592585,{"$f":"TEXT(N1690-L1690+ROUNDDOWN(O1690-M1690,0),\"0\")&\" days\"& IF(MOD((O1690-M1690)*24,24)>0,\" + \" & ROUNDDOWN((O1690-M1690)*24,0) & \" h \" & ROUNDDOWN(MOD((O1690-M1690)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","K54744",null,"< >",2141,2122,2026,2026,{"$f":"WEEKNUM(L1691)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1691)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-02-16","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1691-L1691+ROUNDDOWN(O1691-M1691,0),\"0\")&\" days\"& IF(MOD((O1691-M1691)*24,24)>0,\" + \" & ROUNDDOWN((O1691-M1691)*24,0) & \" h \" & ROUNDDOWN(MOD((O1691-M1691)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B44271",null,"< >",2200,2348,2026,2026,{"$f":"WEEKNUM(L1692)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1692)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-03-30","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1692-L1692+ROUNDDOWN(O1692-M1692,0),\"0\")&\" days\"& IF(MOD((O1692-M1692)*24,24)>0,\" + \" & ROUNDDOWN((O1692-M1692)*24,0) & \" h \" & ROUNDDOWN(MOD((O1692-M1692)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C44271",null,"< >",2200,2348,2026,2026,{"$f":"WEEKNUM(L1693)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1693)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-09-28","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1693-L1693+ROUNDDOWN(O1693-M1693,0),\"0\")&\" days\"& IF(MOD((O1693-M1693)*24,24)>0,\" + \" & ROUNDDOWN((O1693-M1693)*24,0) & \" h \" & ROUNDDOWN(MOD((O1693-M1693)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D44271",null,"< >",2200,2348,2026,2026,{"$f":"WEEKNUM(L1694)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1694)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-04-20","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1694-L1694+ROUNDDOWN(O1694-M1694,0),\"0\")&\" days\"& IF(MOD((O1694-M1694)*24,24)>0,\" + \" & ROUNDDOWN((O1694-M1694)*24,0) & \" h \" & ROUNDDOWN(MOD((O1694-M1694)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65625",null,"< >",2208,2447,2026,2026,{"$f":"WEEKNUM(L1695)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1695)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-06-22","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1695-L1695+ROUNDDOWN(O1695-M1695,0),\"0\")&\" days\"& IF(MOD((O1695-M1695)*24,24)>0,\" + \" & ROUNDDOWN((O1695-M1695)*24,0) & \" h \" & ROUNDDOWN(MOD((O1695-M1695)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F54916",null,"< >",2298,2299,2026,2026,{"$f":"WEEKNUM(L1696)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N1696)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-03-23","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1696-L1696+ROUNDDOWN(O1696-M1696,0),\"0\")&\" days\"& IF(MOD((O1696-M1696)*24,24)>0,\" + \" & ROUNDDOWN((O1696-M1696)*24,0) & \" h \" & ROUNDDOWN(MOD((O1696-M1696)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A54916",null,"< >",2298,2299,2026,2026,{"$f":"WEEKNUM(L1697)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1697)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-06-22","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1697-L1697+ROUNDDOWN(O1697-M1697,0),\"0\")&\" days\"& IF(MOD((O1697-M1697)*24,24)>0,\" + \" & ROUNDDOWN((O1697-M1697)*24,0) & \" h \" & ROUNDDOWN(MOD((O1697-M1697)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B54916",null,"< >",2298,2299,2026,2026,{"$f":"WEEKNUM(L1698)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1698)+[7]dates!$L$3-[7]dates!$H$3","v":9},"2026-01-05","00:00:00","2026-02-22",0.99998842592592585,{"$f":"TEXT(N1698-L1698+ROUNDDOWN(O1698-M1698,0),\"0\")&\" days\"& IF(MOD((O1698-M1698)*24,24)>0,\" + \" & ROUNDDOWN((O1698-M1698)*24,0) & \" h \" & ROUNDDOWN(MOD((O1698-M1698)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C54916",null,"< >",2298,2299,2026,2026,{"$f":"WEEKNUM(L1699)+[7]dates!$L$3-[7]dates!$H$3","v":27},{"$f":"WEEKNUM(N1699)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-06-29","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N1699-L1699+ROUNDDOWN(O1699-M1699,0),\"0\")&\" days\"& IF(MOD((O1699-M1699)*24,24)>0,\" + \" & ROUNDDOWN((O1699-M1699)*24,0) & \" h \" & ROUNDDOWN(MOD((O1699-M1699)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D54916",null,"< >",2298,2299,2026,2026,{"$f":"WEEKNUM(L1700)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1700)+[7]dates!$L$3-[7]dates!$H$3","v":9},"2026-01-05","00:00:00","2026-02-22",0.99998842592592585,{"$f":"TEXT(N1700-L1700+ROUNDDOWN(O1700-M1700,0),\"0\")&\" days\"& IF(MOD((O1700-M1700)*24,24)>0,\" + \" & ROUNDDOWN((O1700-M1700)*24,0) & \" h \" & ROUNDDOWN(MOD((O1700-M1700)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","H54916",null,"< >",2298,2299,2026,2026,{"$f":"WEEKNUM(L1701)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N1701)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-03-23","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1701-L1701+ROUNDDOWN(O1701-M1701,0),\"0\")&\" days\"& IF(MOD((O1701-M1701)*24,24)>0,\" + \" & ROUNDDOWN((O1701-M1701)*24,0) & \" h \" & ROUNDDOWN(MOD((O1701-M1701)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JJ8892",null,"< >",2349,2351,2026,2026,{"$f":"WEEKNUM(L1702)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1702)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-03-09","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N1702-L1702+ROUNDDOWN(O1702-M1702,0),\"0\")&\" days\"& IF(MOD((O1702-M1702)*24,24)>0,\" + \" & ROUNDDOWN((O1702-M1702)*24,0) & \" h \" & ROUNDDOWN(MOD((O1702-M1702)*1440,60),0) & \" min\",\"\")","v":"167 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F44271",null,"< >",2380,2348,2026,2026,{"$f":"WEEKNUM(L1703)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1703)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-03-30","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1703-L1703+ROUNDDOWN(O1703-M1703,0),\"0\")&\" days\"& IF(MOD((O1703-M1703)*24,24)>0,\" + \" & ROUNDDOWN((O1703-M1703)*24,0) & \" h \" & ROUNDDOWN(MOD((O1703-M1703)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A44271",null,"< >",2380,2348,2026,2026,{"$f":"WEEKNUM(L1704)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1704)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-09-28","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1704-L1704+ROUNDDOWN(O1704-M1704,0),\"0\")&\" days\"& IF(MOD((O1704-M1704)*24,24)>0,\" + \" & ROUNDDOWN((O1704-M1704)*24,0) & \" h \" & ROUNDDOWN(MOD((O1704-M1704)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F61902",null,"< >",2438,2436,2026,2026,{"$f":"WEEKNUM(L1705)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1705)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-06-22","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N1705-L1705+ROUNDDOWN(O1705-M1705,0),\"0\")&\" days\"& IF(MOD((O1705-M1705)*24,24)>0,\" + \" & ROUNDDOWN((O1705-M1705)*24,0) & \" h \" & ROUNDDOWN(MOD((O1705-M1705)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH4065",null,"< >",2451,2451,2026,2026,{"$f":"WEEKNUM(L1706)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1706)+[7]dates!$L$3-[7]dates!$H$3","v":9},"2026-01-05","00:00:00","2026-02-22",0.99998842592592585,{"$f":"TEXT(N1706-L1706+ROUNDDOWN(O1706-M1706,0),\"0\")&\" days\"& IF(MOD((O1706-M1706)*24,24)>0,\" + \" & ROUNDDOWN((O1706-M1706)*24,0) & \" h \" & ROUNDDOWN(MOD((O1706-M1706)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH4065",null,"< >",2451,2451,2026,2026,{"$f":"WEEKNUM(L1707)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N1707)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-03-23","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1707-L1707+ROUNDDOWN(O1707-M1707,0),\"0\")&\" days\"& IF(MOD((O1707-M1707)*24,24)>0,\" + \" & ROUNDDOWN((O1707-M1707)*24,0) & \" h \" & ROUNDDOWN(MOD((O1707-M1707)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A41199?\nA66136",null,"< >",2493,8164,2026,2026,{"$f":"WEEKNUM(L1708)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1708)+[7]dates!$L$3-[7]dates!$H$3","v":23},"2026-05-18","00:00:00","2026-05-31",0.99998842592592585,{"$f":"TEXT(N1708-L1708+ROUNDDOWN(O1708-M1708,0),\"0\")&\" days\"& IF(MOD((O1708-M1708)*24,24)>0,\" + \" & ROUNDDOWN((O1708-M1708)*24,0) & \" h \" & ROUNDDOWN(MOD((O1708-M1708)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F48976",null,"< >",2496,2498,2026,2026,{"$f":"WEEKNUM(L1709)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1709)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-19","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1709-L1709+ROUNDDOWN(O1709-M1709,0),\"0\")&\" days\"& IF(MOD((O1709-M1709)*24,24)>0,\" + \" & ROUNDDOWN((O1709-M1709)*24,0) & \" h \" & ROUNDDOWN(MOD((O1709-M1709)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A48976",null,"< >",2496,2498,2026,2026,{"$f":"WEEKNUM(L1710)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1710)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-16","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1710-L1710+ROUNDDOWN(O1710-M1710,0),\"0\")&\" days\"& IF(MOD((O1710-M1710)*24,24)>0,\" + \" & ROUNDDOWN((O1710-M1710)*24,0) & \" h \" & ROUNDDOWN(MOD((O1710-M1710)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B48976",null,"< >",2496,2498,2026,2026,{"$f":"WEEKNUM(L1711)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1711)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-28","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1711-L1711+ROUNDDOWN(O1711-M1711,0),\"0\")&\" days\"& IF(MOD((O1711-M1711)*24,24)>0,\" + \" & ROUNDDOWN((O1711-M1711)*24,0) & \" h \" & ROUNDDOWN(MOD((O1711-M1711)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F41199?\nF66136",null,"< >",2497,2493,2026,2026,{"$f":"WEEKNUM(L1712)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1712)+[7]dates!$L$3-[7]dates!$H$3","v":23},"2026-05-18","00:00:00","2026-05-31",0.99998842592592585,{"$f":"TEXT(N1712-L1712+ROUNDDOWN(O1712-M1712,0),\"0\")&\" days\"& IF(MOD((O1712-M1712)*24,24)>0,\" + \" & ROUNDDOWN((O1712-M1712)*24,0) & \" h \" & ROUNDDOWN(MOD((O1712-M1712)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63770",null,"< >",2498,2083,2026,2026,{"$f":"WEEKNUM(L1713)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1713)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-19","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1713-L1713+ROUNDDOWN(O1713-M1713,0),\"0\")&\" days\"& IF(MOD((O1713-M1713)*24,24)>0,\" + \" & ROUNDDOWN((O1713-M1713)*24,0) & \" h \" & ROUNDDOWN(MOD((O1713-M1713)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A63770",null,"< >",2498,2083,2026,2026,{"$f":"WEEKNUM(L1714)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1714)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-16","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1714-L1714+ROUNDDOWN(O1714-M1714,0),\"0\")&\" days\"& IF(MOD((O1714-M1714)*24,24)>0,\" + \" & ROUNDDOWN((O1714-M1714)*24,0) & \" h \" & ROUNDDOWN(MOD((O1714-M1714)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B63770",null,"< >",2498,2083,2026,2026,{"$f":"WEEKNUM(L1715)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1715)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-28","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1715-L1715+ROUNDDOWN(O1715-M1715,0),\"0\")&\" days\"& IF(MOD((O1715-M1715)*24,24)>0,\" + \" & ROUNDDOWN((O1715-M1715)*24,0) & \" h \" & ROUNDDOWN(MOD((O1715-M1715)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F47942",null,"< >",2557,2555,2026,2026,{"$f":"WEEKNUM(L1716)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1716)+[7]dates!$L$3-[7]dates!$H$3","v":12},"2026-02-16","00:00:00","2026-03-15",0.99998842592592585,{"$f":"TEXT(N1716-L1716+ROUNDDOWN(O1716-M1716,0),\"0\")&\" days\"& IF(MOD((O1716-M1716)*24,24)>0,\" + \" & ROUNDDOWN((O1716-M1716)*24,0) & \" h \" & ROUNDDOWN(MOD((O1716-M1716)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A47942",null,"< >",2557,2555,2026,2026,{"$f":"WEEKNUM(L1717)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1717)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-02-23","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1717-L1717+ROUNDDOWN(O1717-M1717,0),\"0\")&\" days\"& IF(MOD((O1717-M1717)*24,24)>0,\" + \" & ROUNDDOWN((O1717-M1717)*24,0) & \" h \" & ROUNDDOWN(MOD((O1717-M1717)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B47942",null,"< >",2557,2555,2026,2026,{"$f":"WEEKNUM(L1718)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1718)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-02-23","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1718-L1718+ROUNDDOWN(O1718-M1718,0),\"0\")&\" days\"& IF(MOD((O1718-M1718)*24,24)>0,\" + \" & ROUNDDOWN((O1718-M1718)*24,0) & \" h \" & ROUNDDOWN(MOD((O1718-M1718)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58509",null,"< >",2606,2603,2026,2026,{"$f":"WEEKNUM(L1719)+[7]dates!$L$3-[7]dates!$H$3","v":16},{"$f":"WEEKNUM(N1719)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-04-13","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1719-L1719+ROUNDDOWN(O1719-M1719,0),\"0\")&\" days\"& IF(MOD((O1719-M1719)*24,24)>0,\" + \" & ROUNDDOWN((O1719-M1719)*24,0) & \" h \" & ROUNDDOWN(MOD((O1719-M1719)*1440,60),0) & \" min\",\"\")","v":"83 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65160",null,"< >",2618,2626,2026,2026,{"$f":"WEEKNUM(L1720)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N1720)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-06-01","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1720-L1720+ROUNDDOWN(O1720-M1720,0),\"0\")&\" days\"& IF(MOD((O1720-M1720)*24,24)>0,\" + \" & ROUNDDOWN((O1720-M1720)*24,0) & \" h \" & ROUNDDOWN(MOD((O1720-M1720)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A65160",null,"< >",2618,2626,2026,2026,{"$f":"WEEKNUM(L1721)+[7]dates!$L$3-[7]dates!$H$3","v":44},{"$f":"WEEKNUM(N1721)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-10-26","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1721-L1721+ROUNDDOWN(O1721-M1721,0),\"0\")&\" days\"& IF(MOD((O1721-M1721)*24,24)>0,\" + \" & ROUNDDOWN((O1721-M1721)*24,0) & \" h \" & ROUNDDOWN(MOD((O1721-M1721)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F40100",null,"< >",2661,2661,2026,2026,{"$f":"WEEKNUM(L1722)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1722)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-01-05","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N1722-L1722+ROUNDDOWN(O1722-M1722,0),\"0\")&\" days\"& IF(MOD((O1722-M1722)*24,24)>0,\" + \" & ROUNDDOWN((O1722-M1722)*24,0) & \" h \" & ROUNDDOWN(MOD((O1722-M1722)*1440,60),0) & \" min\",\"\")","v":"195 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65162",null,"< >",2679,2681,2026,2026,{"$f":"WEEKNUM(L1723)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1723)+[7]dates!$L$3-[7]dates!$H$3","v":26},"2026-04-20","00:00:00","2026-06-21",0.99998842592592585,{"$f":"TEXT(N1723-L1723+ROUNDDOWN(O1723-M1723,0),\"0\")&\" days\"& IF(MOD((O1723-M1723)*24,24)>0,\" + \" & ROUNDDOWN((O1723-M1723)*24,0) & \" h \" & ROUNDDOWN(MOD((O1723-M1723)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A65162",null,"< >",2679,2681,2026,2026,{"$f":"WEEKNUM(L1724)+[7]dates!$L$3-[7]dates!$H$3","v":32},{"$f":"WEEKNUM(N1724)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-08-03","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1724-L1724+ROUNDDOWN(O1724-M1724,0),\"0\")&\" days\"& IF(MOD((O1724-M1724)*24,24)>0,\" + \" & ROUNDDOWN((O1724-M1724)*24,0) & \" h \" & ROUNDDOWN(MOD((O1724-M1724)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65166",null,"< >",2697,2634,2026,2026,{"$f":"WEEKNUM(L1725)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1725)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1725-L1725+ROUNDDOWN(O1725-M1725,0),\"0\")&\" days\"& IF(MOD((O1725-M1725)*24,24)>0,\" + \" & ROUNDDOWN((O1725-M1725)*24,0) & \" h \" & ROUNDDOWN(MOD((O1725-M1725)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A64248 ",null,"< >",2748,3156,2026,2026,{"$f":"WEEKNUM(L1726)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1726)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-05","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1726-L1726+ROUNDDOWN(O1726-M1726,0),\"0\")&\" days\"& IF(MOD((O1726-M1726)*24,24)>0,\" + \" & ROUNDDOWN((O1726-M1726)*24,0) & \" h \" & ROUNDDOWN(MOD((O1726-M1726)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65700",null,"< >",2752,8190,2026,2026,{"$f":"WEEKNUM(L1727)+[7]dates!$L$3-[7]dates!$H$3","v":37},{"$f":"WEEKNUM(N1727)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-09-07","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1727-L1727+ROUNDDOWN(O1727-M1727,0),\"0\")&\" days\"& IF(MOD((O1727-M1727)*24,24)>0,\" + \" & ROUNDDOWN((O1727-M1727)*24,0) & \" h \" & ROUNDDOWN(MOD((O1727-M1727)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F42024",null,"< >",2761,2754,2026,2026,{"$f":"WEEKNUM(L1728)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N1728)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-02-02","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1728-L1728+ROUNDDOWN(O1728-M1728,0),\"0\")&\" days\"& IF(MOD((O1728-M1728)*24,24)>0,\" + \" & ROUNDDOWN((O1728-M1728)*24,0) & \" h \" & ROUNDDOWN(MOD((O1728-M1728)*1440,60),0) & \" min\",\"\")","v":"237 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F46584",null,"< >",2766,2814,2026,2026,{"$f":"WEEKNUM(L1729)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1729)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-09","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1729-L1729+ROUNDDOWN(O1729-M1729,0),\"0\")&\" days\"& IF(MOD((O1729-M1729)*24,24)>0,\" + \" & ROUNDDOWN((O1729-M1729)*24,0) & \" h \" & ROUNDDOWN(MOD((O1729-M1729)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A46584",null,"< >",2766,2814,2026,2026,{"$f":"WEEKNUM(L1730)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N1730)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-06-01","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1730-L1730+ROUNDDOWN(O1730-M1730,0),\"0\")&\" days\"& IF(MOD((O1730-M1730)*24,24)>0,\" + \" & ROUNDDOWN((O1730-M1730)*24,0) & \" h \" & ROUNDDOWN(MOD((O1730-M1730)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B46584",null,"< >",2766,2814,2026,2026,{"$f":"WEEKNUM(L1731)+[7]dates!$L$3-[7]dates!$H$3","v":27},{"$f":"WEEKNUM(N1731)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-06-29","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N1731-L1731+ROUNDDOWN(O1731-M1731,0),\"0\")&\" days\"& IF(MOD((O1731-M1731)*24,24)>0,\" + \" & ROUNDDOWN((O1731-M1731)*24,0) & \" h \" & ROUNDDOWN(MOD((O1731-M1731)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C46584",null,"< >",2766,2814,2026,2026,{"$f":"WEEKNUM(L1732)+[7]dates!$L$3-[7]dates!$H$3","v":31},{"$f":"WEEKNUM(N1732)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-07-27","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N1732-L1732+ROUNDDOWN(O1732-M1732,0),\"0\")&\" days\"& IF(MOD((O1732-M1732)*24,24)>0,\" + \" & ROUNDDOWN((O1732-M1732)*24,0) & \" h \" & ROUNDDOWN(MOD((O1732-M1732)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F47725",null,"< >",2778,2780,2026,2026,{"$f":"WEEKNUM(L1733)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1733)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-01-05","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1733-L1733+ROUNDDOWN(O1733-M1733,0),\"0\")&\" days\"& IF(MOD((O1733-M1733)*24,24)>0,\" + \" & ROUNDDOWN((O1733-M1733)*24,0) & \" h \" & ROUNDDOWN(MOD((O1733-M1733)*1440,60),0) & \" min\",\"\")","v":"174 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A47725",null,"< >",2778,2780,2026,2026,{"$f":"WEEKNUM(L1734)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N1734)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-07-20","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1734-L1734+ROUNDDOWN(O1734-M1734,0),\"0\")&\" days\"& IF(MOD((O1734-M1734)*24,24)>0,\" + \" & ROUNDDOWN((O1734-M1734)*24,0) & \" h \" & ROUNDDOWN(MOD((O1734-M1734)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B47725",null,"< >",2778,2780,2026,2026,{"$f":"WEEKNUM(L1735)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1735)+[7]dates!$L$3-[7]dates!$H$3","v":39},"2026-08-31","00:00:00","2026-09-20",0.99998842592592585,{"$f":"TEXT(N1735-L1735+ROUNDDOWN(O1735-M1735,0),\"0\")&\" days\"& IF(MOD((O1735-M1735)*24,24)>0,\" + \" & ROUNDDOWN((O1735-M1735)*24,0) & \" h \" & ROUNDDOWN(MOD((O1735-M1735)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C47725",null,"< >",2778,2780,2026,2026,{"$f":"WEEKNUM(L1736)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1736)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-09-28","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N1736-L1736+ROUNDDOWN(O1736-M1736,0),\"0\")&\" days\"& IF(MOD((O1736-M1736)*24,24)>0,\" + \" & ROUNDDOWN((O1736-M1736)*24,0) & \" h \" & ROUNDDOWN(MOD((O1736-M1736)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D47725",null,"< >",2778,2780,2026,2026,{"$f":"WEEKNUM(L1737)+[7]dates!$L$3-[7]dates!$H$3","v":46},{"$f":"WEEKNUM(N1737)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-11-09","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1737-L1737+ROUNDDOWN(O1737-M1737,0),\"0\")&\" days\"& IF(MOD((O1737-M1737)*24,24)>0,\" + \" & ROUNDDOWN((O1737-M1737)*24,0) & \" h \" & ROUNDDOWN(MOD((O1737-M1737)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65161",null,"< >",2782,2793,2026,2026,{"$f":"WEEKNUM(L1738)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1738)+[7]dates!$L$3-[7]dates!$H$3","v":13},"2026-01-05","00:00:00","2026-03-22",0.99998842592592585,{"$f":"TEXT(N1738-L1738+ROUNDDOWN(O1738-M1738,0),\"0\")&\" days\"& IF(MOD((O1738-M1738)*24,24)>0,\" + \" & ROUNDDOWN((O1738-M1738)*24,0) & \" h \" & ROUNDDOWN(MOD((O1738-M1738)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A65161",null,"< >",2782,2793,2026,2026,{"$f":"WEEKNUM(L1739)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1739)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-05-18","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1739-L1739+ROUNDDOWN(O1739-M1739,0),\"0\")&\" days\"& IF(MOD((O1739-M1739)*24,24)>0,\" + \" & ROUNDDOWN((O1739-M1739)*24,0) & \" h \" & ROUNDDOWN(MOD((O1739-M1739)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F40064",null,"< >",2826,2826,2026,2026,{"$f":"WEEKNUM(L1740)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1740)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-01-05","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N1740-L1740+ROUNDDOWN(O1740-M1740,0),\"0\")&\" days\"& IF(MOD((O1740-M1740)*24,24)>0,\" + \" & ROUNDDOWN((O1740-M1740)*24,0) & \" h \" & ROUNDDOWN(MOD((O1740-M1740)*1440,60),0) & \" min\",\"\")","v":"195 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A40064",null,"< >",2836,2836,2026,2026,{"$f":"WEEKNUM(L1741)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1741)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-01-05","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N1741-L1741+ROUNDDOWN(O1741-M1741,0),\"0\")&\" days\"& IF(MOD((O1741-M1741)*24,24)>0,\" + \" & ROUNDDOWN((O1741-M1741)*24,0) & \" h \" & ROUNDDOWN(MOD((O1741-M1741)*1440,60),0) & \" min\",\"\")","v":"195 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58940",null,"< >",2838,2836,2026,2026,{"$f":"WEEKNUM(L1742)+[7]dates!$L$3-[7]dates!$H$3","v":37},{"$f":"WEEKNUM(N1742)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-09-07","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1742-L1742+ROUNDDOWN(O1742-M1742,0),\"0\")&\" days\"& IF(MOD((O1742-M1742)*24,24)>0,\" + \" & ROUNDDOWN((O1742-M1742)*24,0) & \" h \" & ROUNDDOWN(MOD((O1742-M1742)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F48503",null,"< >",3155,2750,2026,2026,{"$f":"WEEKNUM(L1743)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1743)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-03-02","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1743-L1743+ROUNDDOWN(O1743-M1743,0),\"0\")&\" days\"& IF(MOD((O1743-M1743)*24,24)>0,\" + \" & ROUNDDOWN((O1743-M1743)*24,0) & \" h \" & ROUNDDOWN(MOD((O1743-M1743)*1440,60),0) & \" min\",\"\")","v":"153 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58256",null,"< >",3175,3175,2026,2026,{"$f":"WEEKNUM(L1744)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1744)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-03-02","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1744-L1744+ROUNDDOWN(O1744-M1744,0),\"0\")&\" days\"& IF(MOD((O1744-M1744)*24,24)>0,\" + \" & ROUNDDOWN((O1744-M1744)*24,0) & \" h \" & ROUNDDOWN(MOD((O1744-M1744)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58256",null,"< >",3175,3175,2026,2026,{"$f":"WEEKNUM(L1745)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1745)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-10-05","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1745-L1745+ROUNDDOWN(O1745-M1745,0),\"0\")&\" days\"& IF(MOD((O1745-M1745)*24,24)>0,\" + \" & ROUNDDOWN((O1745-M1745)*24,0) & \" h \" & ROUNDDOWN(MOD((O1745-M1745)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R"," F64248 ",null,"< >",3181,2750,2026,2026,{"$f":"WEEKNUM(L1746)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1746)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-05","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1746-L1746+ROUNDDOWN(O1746-M1746,0),\"0\")&\" days\"& IF(MOD((O1746-M1746)*24,24)>0,\" + \" & ROUNDDOWN((O1746-M1746)*24,0) & \" h \" & ROUNDDOWN(MOD((O1746-M1746)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58768",null,"< >",3181,2750,2026,2026,{"$f":"WEEKNUM(L1747)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1747)+[7]dates!$L$3-[7]dates!$H$3","v":10},"2026-02-16","00:00:00","2026-03-01",0.99998842592592585,{"$f":"TEXT(N1747-L1747+ROUNDDOWN(O1747-M1747,0),\"0\")&\" days\"& IF(MOD((O1747-M1747)*24,24)>0,\" + \" & ROUNDDOWN((O1747-M1747)*24,0) & \" h \" & ROUNDDOWN(MOD((O1747-M1747)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58768",null,"< >",3181,2750,2026,2026,{"$f":"WEEKNUM(L1748)+[7]dates!$L$3-[7]dates!$H$3","v":29},{"$f":"WEEKNUM(N1748)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-07-13","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N1748-L1748+ROUNDDOWN(O1748-M1748,0),\"0\")&\" days\"& IF(MOD((O1748-M1748)*24,24)>0,\" + \" & ROUNDDOWN((O1748-M1748)*24,0) & \" h \" & ROUNDDOWN(MOD((O1748-M1748)*1440,60),0) & \" min\",\"\")","v":"104 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B58768",null,"< >",3181,2750,2026,2026,{"$f":"WEEKNUM(L1749)+[7]dates!$L$3-[7]dates!$H$3","v":32},{"$f":"WEEKNUM(N1749)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-08-03","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N1749-L1749+ROUNDDOWN(O1749-M1749,0),\"0\")&\" days\"& IF(MOD((O1749-M1749)*24,24)>0,\" + \" & ROUNDDOWN((O1749-M1749)*24,0) & \" h \" & ROUNDDOWN(MOD((O1749-M1749)*1440,60),0) & \" min\",\"\")","v":"83 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65200",null,"< >",3181,3205,2026,2026,{"$f":"WEEKNUM(L1750)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1750)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-03-30","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1750-L1750+ROUNDDOWN(O1750-M1750,0),\"0\")&\" days\"& IF(MOD((O1750-M1750)*24,24)>0,\" + \" & ROUNDDOWN((O1750-M1750)*24,0) & \" h \" & ROUNDDOWN(MOD((O1750-M1750)*1440,60),0) & \" min\",\"\")","v":"97 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B64248 ",null,"< >",3201,3201,2026,2026,{"$f":"WEEKNUM(L1751)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1751)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-05","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1751-L1751+ROUNDDOWN(O1751-M1751,0),\"0\")&\" days\"& IF(MOD((O1751-M1751)*24,24)>0,\" + \" & ROUNDDOWN((O1751-M1751)*24,0) & \" h \" & ROUNDDOWN(MOD((O1751-M1751)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C64248 ",null,"< >",3201,3201,2026,2026,{"$f":"WEEKNUM(L1752)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1752)+[7]dates!$L$3-[7]dates!$H$3","v":10},"2026-01-26","00:00:00","2026-03-01",0.99998842592592585,{"$f":"TEXT(N1752-L1752+ROUNDDOWN(O1752-M1752,0),\"0\")&\" days\"& IF(MOD((O1752-M1752)*24,24)>0,\" + \" & ROUNDDOWN((O1752-M1752)*24,0) & \" h \" & ROUNDDOWN(MOD((O1752-M1752)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57476",null,"< >",3226,3219,2026,2026,{"$f":"WEEKNUM(L1753)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1753)+[7]dates!$L$3-[7]dates!$H$3","v":46},"2026-06-22","00:00:00","2026-11-08",0.99998842592592585,{"$f":"TEXT(N1753-L1753+ROUNDDOWN(O1753-M1753,0),\"0\")&\" days\"& IF(MOD((O1753-M1753)*24,24)>0,\" + \" & ROUNDDOWN((O1753-M1753)*24,0) & \" h \" & ROUNDDOWN(MOD((O1753-M1753)*1440,60),0) & \" min\",\"\")","v":"139 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A57476",null,"< >",3226,3219,2026,2026,{"$f":"WEEKNUM(L1754)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1754)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-06-22","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1754-L1754+ROUNDDOWN(O1754-M1754,0),\"0\")&\" days\"& IF(MOD((O1754-M1754)*24,24)>0,\" + \" & ROUNDDOWN((O1754-M1754)*24,0) & \" h \" & ROUNDDOWN(MOD((O1754-M1754)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B57476",null,"< >",3226,3219,2026,2026,{"$f":"WEEKNUM(L1755)+[7]dates!$L$3-[7]dates!$H$3","v":34},{"$f":"WEEKNUM(N1755)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-08-17","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N1755-L1755+ROUNDDOWN(O1755-M1755,0),\"0\")&\" days\"& IF(MOD((O1755-M1755)*24,24)>0,\" + \" & ROUNDDOWN((O1755-M1755)*24,0) & \" h \" & ROUNDDOWN(MOD((O1755-M1755)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C57476",null,"< >",3226,3219,2026,2026,{"$f":"WEEKNUM(L1756)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1756)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-06-22","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1756-L1756+ROUNDDOWN(O1756-M1756,0),\"0\")&\" days\"& IF(MOD((O1756-M1756)*24,24)>0,\" + \" & ROUNDDOWN((O1756-M1756)*24,0) & \" h \" & ROUNDDOWN(MOD((O1756-M1756)*1440,60),0) & \" min\",\"\")","v":"132 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57896",null,"< >",3326,3174,2026,2026,{"$f":"WEEKNUM(L1757)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1757)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-01-05","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1757-L1757+ROUNDDOWN(O1757-M1757,0),\"0\")&\" days\"& IF(MOD((O1757-M1757)*24,24)>0,\" + \" & ROUNDDOWN((O1757-M1757)*24,0) & \" h \" & ROUNDDOWN(MOD((O1757-M1757)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A57896",null,"< >",3326,3174,2026,2026,{"$f":"WEEKNUM(L1758)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1758)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-01-05","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1758-L1758+ROUNDDOWN(O1758-M1758,0),\"0\")&\" days\"& IF(MOD((O1758-M1758)*24,24)>0,\" + \" & ROUNDDOWN((O1758-M1758)*24,0) & \" h \" & ROUNDDOWN(MOD((O1758-M1758)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F43904",null,"< >",3345,7108,2026,2026,{"$f":"WEEKNUM(L1759)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1759)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1759-L1759+ROUNDDOWN(O1759-M1759,0),\"0\")&\" days\"& IF(MOD((O1759-M1759)*24,24)>0,\" + \" & ROUNDDOWN((O1759-M1759)*24,0) & \" h \" & ROUNDDOWN(MOD((O1759-M1759)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A43904",null,"< >",3345,7108,2026,2026,{"$f":"WEEKNUM(L1760)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1760)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1760-L1760+ROUNDDOWN(O1760-M1760,0),\"0\")&\" days\"& IF(MOD((O1760-M1760)*24,24)>0,\" + \" & ROUNDDOWN((O1760-M1760)*24,0) & \" h \" & ROUNDDOWN(MOD((O1760-M1760)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63461",null,"< >",3351,4161,2026,2026,{"$f":"WEEKNUM(L1761)+[7]dates!$L$3-[7]dates!$H$3","v":31},{"$f":"WEEKNUM(N1761)+[7]dates!$L$3-[7]dates!$H$3","v":47},"2026-07-27","00:00:00","2026-11-15",0.99998842592592585,{"$f":"TEXT(N1761-L1761+ROUNDDOWN(O1761-M1761,0),\"0\")&\" days\"& IF(MOD((O1761-M1761)*24,24)>0,\" + \" & ROUNDDOWN((O1761-M1761)*24,0) & \" h \" & ROUNDDOWN(MOD((O1761-M1761)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52628",null,"< >",3827,3829,2026,2026,{"$f":"WEEKNUM(L1762)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1762)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-05-18","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N1762-L1762+ROUNDDOWN(O1762-M1762,0),\"0\")&\" days\"& IF(MOD((O1762-M1762)*24,24)>0,\" + \" & ROUNDDOWN((O1762-M1762)*24,0) & \" h \" & ROUNDDOWN(MOD((O1762-M1762)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A52628",null,"< >",3827,3829,2026,2026,{"$f":"WEEKNUM(L1763)+[7]dates!$L$3-[7]dates!$H$3","v":42},{"$f":"WEEKNUM(N1763)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-10-12","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1763-L1763+ROUNDDOWN(O1763-M1763,0),\"0\")&\" days\"& IF(MOD((O1763-M1763)*24,24)>0,\" + \" & ROUNDDOWN((O1763-M1763)*24,0) & \" h \" & ROUNDDOWN(MOD((O1763-M1763)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63788",null,"< >",3836,3858,2026,2026,{"$f":"WEEKNUM(L1764)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1764)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1764-L1764+ROUNDDOWN(O1764-M1764,0),\"0\")&\" days\"& IF(MOD((O1764-M1764)*24,24)>0,\" + \" & ROUNDDOWN((O1764-M1764)*24,0) & \" h \" & ROUNDDOWN(MOD((O1764-M1764)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A63788",null,"< >",3836,3858,2026,2026,{"$f":"WEEKNUM(L1765)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1765)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-10-05","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1765-L1765+ROUNDDOWN(O1765-M1765,0),\"0\")&\" days\"& IF(MOD((O1765-M1765)*24,24)>0,\" + \" & ROUNDDOWN((O1765-M1765)*24,0) & \" h \" & ROUNDDOWN(MOD((O1765-M1765)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B63788",null,"< >",3836,3858,2026,2026,{"$f":"WEEKNUM(L1766)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1766)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-05-04","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1766-L1766+ROUNDDOWN(O1766-M1766,0),\"0\")&\" days\"& IF(MOD((O1766-M1766)*24,24)>0,\" + \" & ROUNDDOWN((O1766-M1766)*24,0) & \" h \" & ROUNDDOWN(MOD((O1766-M1766)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F49371",null,"< >",3837,3767,2026,2026,{"$f":"WEEKNUM(L1767)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N1767)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-03-23","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1767-L1767+ROUNDDOWN(O1767-M1767,0),\"0\")&\" days\"& IF(MOD((O1767-M1767)*24,24)>0,\" + \" & ROUNDDOWN((O1767-M1767)*24,0) & \" h \" & ROUNDDOWN(MOD((O1767-M1767)*1440,60),0) & \" min\",\"\")","v":"97 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A49371",null,"< >",3837,3767,2026,2026,{"$f":"WEEKNUM(L1768)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1768)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-05-04","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1768-L1768+ROUNDDOWN(O1768-M1768,0),\"0\")&\" days\"& IF(MOD((O1768-M1768)*24,24)>0,\" + \" & ROUNDDOWN((O1768-M1768)*24,0) & \" h \" & ROUNDDOWN(MOD((O1768-M1768)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B49371",null,"< >",3837,3767,2026,2026,{"$f":"WEEKNUM(L1769)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N1769)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-03-23","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1769-L1769+ROUNDDOWN(O1769-M1769,0),\"0\")&\" days\"& IF(MOD((O1769-M1769)*24,24)>0,\" + \" & ROUNDDOWN((O1769-M1769)*24,0) & \" h \" & ROUNDDOWN(MOD((O1769-M1769)*1440,60),0) & \" min\",\"\")","v":"83 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","E25514",null,"< >",3889,3893,2026,2026,{"$f":"WEEKNUM(L1770)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1770)+[7]dates!$L$3-[7]dates!$H$3","v":16},"2026-03-02","00:00:00","2026-04-12",0.99998842592592585,{"$f":"TEXT(N1770-L1770+ROUNDDOWN(O1770-M1770,0),\"0\")&\" days\"& IF(MOD((O1770-M1770)*24,24)>0,\" + \" & ROUNDDOWN((O1770-M1770)*24,0) & \" h \" & ROUNDDOWN(MOD((O1770-M1770)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A25514",null,"< >",3889,3893,2026,2026,{"$f":"WEEKNUM(L1771)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1771)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1771-L1771+ROUNDDOWN(O1771-M1771,0),\"0\")&\" days\"& IF(MOD((O1771-M1771)*24,24)>0,\" + \" & ROUNDDOWN((O1771-M1771)*24,0) & \" h \" & ROUNDDOWN(MOD((O1771-M1771)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH4113",null,"< >",3905,4016,2026,2026,{"$f":"WEEKNUM(L1772)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1772)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-01-05","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1772-L1772+ROUNDDOWN(O1772-M1772,0),\"0\")&\" days\"& IF(MOD((O1772-M1772)*24,24)>0,\" + \" & ROUNDDOWN((O1772-M1772)*24,0) & \" h \" & ROUNDDOWN(MOD((O1772-M1772)*1440,60),0) & \" min\",\"\")","v":"125 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH4113",null,"< >",3905,4016,2026,2026,{"$f":"WEEKNUM(L1773)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1773)+[7]dates!$L$3-[7]dates!$H$3","v":47},"2026-05-18","00:00:00","2026-11-15",0.99998842592592585,{"$f":"TEXT(N1773-L1773+ROUNDDOWN(O1773-M1773,0),\"0\")&\" days\"& IF(MOD((O1773-M1773)*24,24)>0,\" + \" & ROUNDDOWN((O1773-M1773)*24,0) & \" h \" & ROUNDDOWN(MOD((O1773-M1773)*1440,60),0) & \" min\",\"\")","v":"181 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57063",null,"< >",4001,3978,2026,2026,{"$f":"WEEKNUM(L1774)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1774)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-01-05","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1774-L1774+ROUNDDOWN(O1774-M1774,0),\"0\")&\" days\"& IF(MOD((O1774-M1774)*24,24)>0,\" + \" & ROUNDDOWN((O1774-M1774)*24,0) & \" h \" & ROUNDDOWN(MOD((O1774-M1774)*1440,60),0) & \" min\",\"\")","v":"174 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","E24606",null,"< >",4009,4011,2026,2026,{"$f":"WEEKNUM(L1775)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N1775)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-03-23","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1775-L1775+ROUNDDOWN(O1775-M1775,0),\"0\")&\" days\"& IF(MOD((O1775-M1775)*24,24)>0,\" + \" & ROUNDDOWN((O1775-M1775)*24,0) & \" h \" & ROUNDDOWN(MOD((O1775-M1775)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A24606",null,"< >",4009,4011,2026,2026,{"$f":"WEEKNUM(L1776)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1776)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-10-05","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1776-L1776+ROUNDDOWN(O1776-M1776,0),\"0\")&\" days\"& IF(MOD((O1776-M1776)*24,24)>0,\" + \" & ROUNDDOWN((O1776-M1776)*24,0) & \" h \" & ROUNDDOWN(MOD((O1776-M1776)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B24606",null,"< >",4009,4011,2026,2026,{"$f":"WEEKNUM(L1777)+[7]dates!$L$3-[7]dates!$H$3","v":15},{"$f":"WEEKNUM(N1777)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-04-06","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1777-L1777+ROUNDDOWN(O1777-M1777,0),\"0\")&\" days\"& IF(MOD((O1777-M1777)*24,24)>0,\" + \" & ROUNDDOWN((O1777-M1777)*24,0) & \" h \" & ROUNDDOWN(MOD((O1777-M1777)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65044",null,"< >",4037,4046,2026,2026,{"$f":"WEEKNUM(L1778)+[7]dates!$L$3-[7]dates!$H$3","v":27},{"$f":"WEEKNUM(N1778)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-06-29","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1778-L1778+ROUNDDOWN(O1778-M1778,0),\"0\")&\" days\"& IF(MOD((O1778-M1778)*24,24)>0,\" + \" & ROUNDDOWN((O1778-M1778)*24,0) & \" h \" & ROUNDDOWN(MOD((O1778-M1778)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59445",null,"< >",4117,8303,2026,2026,{"$f":"WEEKNUM(L1779)+[7]dates!$L$3-[7]dates!$H$3","v":45},{"$f":"WEEKNUM(N1779)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-11-02","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1779-L1779+ROUNDDOWN(O1779-M1779,0),\"0\")&\" days\"& IF(MOD((O1779-M1779)*24,24)>0,\" + \" & ROUNDDOWN((O1779-M1779)*24,0) & \" h \" & ROUNDDOWN(MOD((O1779-M1779)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63813",null,"< >",4130,4128,2026,2026,{"$f":"WEEKNUM(L1780)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1780)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-03-09","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1780-L1780+ROUNDDOWN(O1780-M1780,0),\"0\")&\" days\"& IF(MOD((O1780-M1780)*24,24)>0,\" + \" & ROUNDDOWN((O1780-M1780)*24,0) & \" h \" & ROUNDDOWN(MOD((O1780-M1780)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59444",null,"< >",4144,4123,2026,2026,{"$f":"WEEKNUM(L1781)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1781)+[7]dates!$L$3-[7]dates!$H$3","v":26},"2026-05-11","00:00:00","2026-06-21",0.99998842592592585,{"$f":"TEXT(N1781-L1781+ROUNDDOWN(O1781-M1781,0),\"0\")&\" days\"& IF(MOD((O1781-M1781)*24,24)>0,\" + \" & ROUNDDOWN((O1781-M1781)*24,0) & \" h \" & ROUNDDOWN(MOD((O1781-M1781)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F49603",null,"< >",4350,4446,2026,2026,{"$f":"WEEKNUM(L1782)+[7]dates!$L$3-[7]dates!$H$3","v":3},{"$f":"WEEKNUM(N1782)+[7]dates!$L$3-[7]dates!$H$3","v":34},"2026-01-12","00:00:00","2026-08-16",0.99998842592592585,{"$f":"TEXT(N1782-L1782+ROUNDDOWN(O1782-M1782,0),\"0\")&\" days\"& IF(MOD((O1782-M1782)*24,24)>0,\" + \" & ROUNDDOWN((O1782-M1782)*24,0) & \" h \" & ROUNDDOWN(MOD((O1782-M1782)*1440,60),0) & \" min\",\"\")","v":"216 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A49603",null,"< >",4350,4446,2026,2026,{"$f":"WEEKNUM(L1783)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1783)+[7]dates!$L$3-[7]dates!$H$3","v":47},"2026-08-31","00:00:00","2026-11-15",0.99998842592592585,{"$f":"TEXT(N1783-L1783+ROUNDDOWN(O1783-M1783,0),\"0\")&\" days\"& IF(MOD((O1783-M1783)*24,24)>0,\" + \" & ROUNDDOWN((O1783-M1783)*24,0) & \" h \" & ROUNDDOWN(MOD((O1783-M1783)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65225",null,"< >",4425,4430,2026,2026,{"$f":"WEEKNUM(L1784)+[7]dates!$L$3-[7]dates!$H$3","v":45},{"$f":"WEEKNUM(N1784)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-11-02","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1784-L1784+ROUNDDOWN(O1784-M1784,0),\"0\")&\" days\"& IF(MOD((O1784-M1784)*24,24)>0,\" + \" & ROUNDDOWN((O1784-M1784)*24,0) & \" h \" & ROUNDDOWN(MOD((O1784-M1784)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63255",null,"< >",4438,4446,2026,2026,{"$f":"WEEKNUM(L1785)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1785)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-06-15","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1785-L1785+ROUNDDOWN(O1785-M1785,0),\"0\")&\" days\"& IF(MOD((O1785-M1785)*24,24)>0,\" + \" & ROUNDDOWN((O1785-M1785)*24,0) & \" h \" & ROUNDDOWN(MOD((O1785-M1785)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A63255",null,"< >",4438,4446,2026,2026,{"$f":"WEEKNUM(L1786)+[7]dates!$L$3-[7]dates!$H$3","v":34},{"$f":"WEEKNUM(N1786)+[7]dates!$L$3-[7]dates!$H$3","v":47},"2026-08-17","00:00:00","2026-11-15",0.99998842592592585,{"$f":"TEXT(N1786-L1786+ROUNDDOWN(O1786-M1786,0),\"0\")&\" days\"& IF(MOD((O1786-M1786)*24,24)>0,\" + \" & ROUNDDOWN((O1786-M1786)*24,0) & \" h \" & ROUNDDOWN(MOD((O1786-M1786)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B63255",null,"< >",4438,4446,2026,2026,{"$f":"WEEKNUM(L1787)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1787)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-06-15","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1787-L1787+ROUNDDOWN(O1787-M1787,0),\"0\")&\" days\"& IF(MOD((O1787-M1787)*24,24)>0,\" + \" & ROUNDDOWN((O1787-M1787)*24,0) & \" h \" & ROUNDDOWN(MOD((O1787-M1787)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C63255",null,"< >",4438,4446,2026,2026,{"$f":"WEEKNUM(L1788)+[7]dates!$L$3-[7]dates!$H$3","v":34},{"$f":"WEEKNUM(N1788)+[7]dates!$L$3-[7]dates!$H$3","v":47},"2026-08-17","00:00:00","2026-11-15",0.99998842592592585,{"$f":"TEXT(N1788-L1788+ROUNDDOWN(O1788-M1788,0),\"0\")&\" days\"& IF(MOD((O1788-M1788)*24,24)>0,\" + \" & ROUNDDOWN((O1788-M1788)*24,0) & \" h \" & ROUNDDOWN(MOD((O1788-M1788)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60911",null,"< >",4496,4495,2026,2026,{"$f":"WEEKNUM(L1789)+[7]dates!$L$3-[7]dates!$H$3","v":35},{"$f":"WEEKNUM(N1789)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-08-24","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1789-L1789+ROUNDDOWN(O1789-M1789,0),\"0\")&\" days\"& IF(MOD((O1789-M1789)*24,24)>0,\" + \" & ROUNDDOWN((O1789-M1789)*24,0) & \" h \" & ROUNDDOWN(MOD((O1789-M1789)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH4616",null,"< >",4501,4500,2026,2026,{"$f":"WEEKNUM(L1790)+[7]dates!$L$3-[7]dates!$H$3","v":38},{"$f":"WEEKNUM(N1790)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-09-14","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1790-L1790+ROUNDDOWN(O1790-M1790,0),\"0\")&\" days\"& IF(MOD((O1790-M1790)*24,24)>0,\" + \" & ROUNDDOWN((O1790-M1790)*24,0) & \" h \" & ROUNDDOWN(MOD((O1790-M1790)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F61010",null,"< >",4503,4520,2026,2026,{"$f":"WEEKNUM(L1791)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1791)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-06-15","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1791-L1791+ROUNDDOWN(O1791-M1791,0),\"0\")&\" days\"& IF(MOD((O1791-M1791)*24,24)>0,\" + \" & ROUNDDOWN((O1791-M1791)*24,0) & \" h \" & ROUNDDOWN(MOD((O1791-M1791)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JJ8152",null,"< >",4529,4529,2026,2026,{"$f":"WEEKNUM(L1792)+[7]dates!$L$3-[7]dates!$H$3","v":35},{"$f":"WEEKNUM(N1792)+[7]dates!$L$3-[7]dates!$H$3","v":38},"2026-08-24","00:00:00","2026-09-13",0.99998842592592585,{"$f":"TEXT(N1792-L1792+ROUNDDOWN(O1792-M1792,0),\"0\")&\" days\"& IF(MOD((O1792-M1792)*24,24)>0,\" + \" & ROUNDDOWN((O1792-M1792)*24,0) & \" h \" & ROUNDDOWN(MOD((O1792-M1792)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AJ8152",null,"< >",4531,4533,2026,2026,{"$f":"WEEKNUM(L1793)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1793)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-02-16","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N1793-L1793+ROUNDDOWN(O1793-M1793,0),\"0\")&\" days\"& IF(MOD((O1793-M1793)*24,24)>0,\" + \" & ROUNDDOWN((O1793-M1793)*24,0) & \" h \" & ROUNDDOWN(MOD((O1793-M1793)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","BJ8152",null,"< >",4531,4533,2026,2026,{"$f":"WEEKNUM(L1794)+[7]dates!$L$3-[7]dates!$H$3","v":37},{"$f":"WEEKNUM(N1794)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-07","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1794-L1794+ROUNDDOWN(O1794-M1794,0),\"0\")&\" days\"& IF(MOD((O1794-M1794)*24,24)>0,\" + \" & ROUNDDOWN((O1794-M1794)*24,0) & \" h \" & ROUNDDOWN(MOD((O1794-M1794)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59894",null,"< >",4655,4540,2026,2026,{"$f":"WEEKNUM(L1795)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1795)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-05-04","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1795-L1795+ROUNDDOWN(O1795-M1795,0),\"0\")&\" days\"& IF(MOD((O1795-M1795)*24,24)>0,\" + \" & ROUNDDOWN((O1795-M1795)*24,0) & \" h \" & ROUNDDOWN(MOD((O1795-M1795)*1440,60),0) & \" min\",\"\")","v":"216 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52470",null,"< >",4684,8309,2026,2026,{"$f":"WEEKNUM(L1796)+[7]dates!$L$3-[7]dates!$H$3","v":3},{"$f":"WEEKNUM(N1796)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-01-12","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1796-L1796+ROUNDDOWN(O1796-M1796,0),\"0\")&\" days\"& IF(MOD((O1796-M1796)*24,24)>0,\" + \" & ROUNDDOWN((O1796-M1796)*24,0) & \" h \" & ROUNDDOWN(MOD((O1796-M1796)*1440,60),0) & \" min\",\"\")","v":"202 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A52470",null,"< >",4684,8309,2026,2026,{"$f":"WEEKNUM(L1797)+[7]dates!$L$3-[7]dates!$H$3","v":34},{"$f":"WEEKNUM(N1797)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-08-17","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1797-L1797+ROUNDDOWN(O1797-M1797,0),\"0\")&\" days\"& IF(MOD((O1797-M1797)*24,24)>0,\" + \" & ROUNDDOWN((O1797-M1797)*24,0) & \" h \" & ROUNDDOWN(MOD((O1797-M1797)*1440,60),0) & \" min\",\"\")","v":"97 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH4107",null,"< >",4724,4724,2026,2026,{"$f":"WEEKNUM(L1798)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1798)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-01-05","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1798-L1798+ROUNDDOWN(O1798-M1798,0),\"0\")&\" days\"& IF(MOD((O1798-M1798)*24,24)>0,\" + \" & ROUNDDOWN((O1798-M1798)*24,0) & \" h \" & ROUNDDOWN(MOD((O1798-M1798)*1440,60),0) & \" min\",\"\")","v":"181 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH4107",null,"< >",4724,4724,2026,2026,{"$f":"WEEKNUM(L1799)+[7]dates!$L$3-[7]dates!$H$3","v":3},{"$f":"WEEKNUM(N1799)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-01-12","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1799-L1799+ROUNDDOWN(O1799-M1799,0),\"0\")&\" days\"& IF(MOD((O1799-M1799)*24,24)>0,\" + \" & ROUNDDOWN((O1799-M1799)*24,0) & \" h \" & ROUNDDOWN(MOD((O1799-M1799)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57483",null,"< >",4729,5726,2026,2026,{"$f":"WEEKNUM(L1800)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1800)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-03-30","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1800-L1800+ROUNDDOWN(O1800-M1800,0),\"0\")&\" days\"& IF(MOD((O1800-M1800)*24,24)>0,\" + \" & ROUNDDOWN((O1800-M1800)*24,0) & \" h \" & ROUNDDOWN(MOD((O1800-M1800)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63943",null,"< >",4738,4859,2026,2026,{"$f":"WEEKNUM(L1801)+[7]dates!$L$3-[7]dates!$H$3","v":38},{"$f":"WEEKNUM(N1801)+[7]dates!$L$3-[7]dates!$H$3","v":41},"2026-09-14","00:00:00","2026-10-04",0.99998842592592585,{"$f":"TEXT(N1801-L1801+ROUNDDOWN(O1801-M1801,0),\"0\")&\" days\"& IF(MOD((O1801-M1801)*24,24)>0,\" + \" & ROUNDDOWN((O1801-M1801)*24,0) & \" h \" & ROUNDDOWN(MOD((O1801-M1801)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","W63943",null,"< >",4738,4859,2026,2026,{"$f":"WEEKNUM(L1802)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1802)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-09-28","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N1802-L1802+ROUNDDOWN(O1802-M1802,0),\"0\")&\" days\"& IF(MOD((O1802-M1802)*24,24)>0,\" + \" & ROUNDDOWN((O1802-M1802)*24,0) & \" h \" & ROUNDDOWN(MOD((O1802-M1802)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F66174",null,"< >",4746,4855,2026,2026,{"$f":"WEEKNUM(L1803)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1803)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-01-26","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1803-L1803+ROUNDDOWN(O1803-M1803,0),\"0\")&\" days\"& IF(MOD((O1803-M1803)*24,24)>0,\" + \" & ROUNDDOWN((O1803-M1803)*24,0) & \" h \" & ROUNDDOWN(MOD((O1803-M1803)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65919",null,"< >",4758,4761,2026,2026,{"$f":"WEEKNUM(L1804)+[7]dates!$L$3-[7]dates!$H$3","v":43},{"$f":"WEEKNUM(N1804)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-10-19","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1804-L1804+ROUNDDOWN(O1804-M1804,0),\"0\")&\" days\"& IF(MOD((O1804-M1804)*24,24)>0,\" + \" & ROUNDDOWN((O1804-M1804)*24,0) & \" h \" & ROUNDDOWN(MOD((O1804-M1804)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B61010",null,"< >",4774,4778,2026,2026,{"$f":"WEEKNUM(L1805)+[7]dates!$L$3-[7]dates!$H$3","v":27},{"$f":"WEEKNUM(N1805)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-06-29","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1805-L1805+ROUNDDOWN(O1805-M1805,0),\"0\")&\" days\"& IF(MOD((O1805-M1805)*24,24)>0,\" + \" & ROUNDDOWN((O1805-M1805)*24,0) & \" h \" & ROUNDDOWN(MOD((O1805-M1805)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59951",null,"< >",4776,4778,2026,2026,{"$f":"WEEKNUM(L1806)+[7]dates!$L$3-[7]dates!$H$3","v":44},{"$f":"WEEKNUM(N1806)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-10-26","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1806-L1806+ROUNDDOWN(O1806-M1806,0),\"0\")&\" days\"& IF(MOD((O1806-M1806)*24,24)>0,\" + \" & ROUNDDOWN((O1806-M1806)*24,0) & \" h \" & ROUNDDOWN(MOD((O1806-M1806)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62168",null,"< >",4776,4778,2026,2026,{"$f":"WEEKNUM(L1807)+[7]dates!$L$3-[7]dates!$H$3","v":44},{"$f":"WEEKNUM(N1807)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-10-26","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1807-L1807+ROUNDDOWN(O1807-M1807,0),\"0\")&\" days\"& IF(MOD((O1807-M1807)*24,24)>0,\" + \" & ROUNDDOWN((O1807-M1807)*24,0) & \" h \" & ROUNDDOWN(MOD((O1807-M1807)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A61010",null,"< >",4788,8563,2026,2026,{"$f":"WEEKNUM(L1808)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1808)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-22","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1808-L1808+ROUNDDOWN(O1808-M1808,0),\"0\")&\" days\"& IF(MOD((O1808-M1808)*24,24)>0,\" + \" & ROUNDDOWN((O1808-M1808)*24,0) & \" h \" & ROUNDDOWN(MOD((O1808-M1808)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F56927",null,"< >",4788,4778,2026,2026,{"$f":"WEEKNUM(L1809)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1809)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-01-05","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1809-L1809+ROUNDDOWN(O1809-M1809,0),\"0\")&\" days\"& IF(MOD((O1809-M1809)*24,24)>0,\" + \" & ROUNDDOWN((O1809-M1809)*24,0) & \" h \" & ROUNDDOWN(MOD((O1809-M1809)*1440,60),0) & \" min\",\"\")","v":"125 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A56927",null,"< >",4788,4778,2026,2026,{"$f":"WEEKNUM(L1810)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1810)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-02-16","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N1810-L1810+ROUNDDOWN(O1810-M1810,0),\"0\")&\" days\"& IF(MOD((O1810-M1810)*24,24)>0,\" + \" & ROUNDDOWN((O1810-M1810)*24,0) & \" h \" & ROUNDDOWN(MOD((O1810-M1810)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60678",null,"< >",4817,4824,2026,2026,{"$f":"WEEKNUM(L1811)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1811)+[7]dates!$L$3-[7]dates!$H$3","v":16},"2026-02-23","00:00:00","2026-04-12",0.99998842592592585,{"$f":"TEXT(N1811-L1811+ROUNDDOWN(O1811-M1811,0),\"0\")&\" days\"& IF(MOD((O1811-M1811)*24,24)>0,\" + \" & ROUNDDOWN((O1811-M1811)*24,0) & \" h \" & ROUNDDOWN(MOD((O1811-M1811)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A60678",null,"< >",4817,4824,2026,2026,{"$f":"WEEKNUM(L1812)+[7]dates!$L$3-[7]dates!$H$3","v":28},{"$f":"WEEKNUM(N1812)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-07-06","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1812-L1812+ROUNDDOWN(O1812-M1812,0),\"0\")&\" days\"& IF(MOD((O1812-M1812)*24,24)>0,\" + \" & ROUNDDOWN((O1812-M1812)*24,0) & \" h \" & ROUNDDOWN(MOD((O1812-M1812)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64907",null,"< >",4817,4837,2026,2026,{"$f":"WEEKNUM(L1813)+[7]dates!$L$3-[7]dates!$H$3","v":38},{"$f":"WEEKNUM(N1813)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-09-14","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1813-L1813+ROUNDDOWN(O1813-M1813,0),\"0\")&\" days\"& IF(MOD((O1813-M1813)*24,24)>0,\" + \" & ROUNDDOWN((O1813-M1813)*24,0) & \" h \" & ROUNDDOWN(MOD((O1813-M1813)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C61010",null,"< >",4824,4791,2026,2026,{"$f":"WEEKNUM(L1814)+[7]dates!$L$3-[7]dates!$H$3","v":28},{"$f":"WEEKNUM(N1814)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-07-06","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1814-L1814+ROUNDDOWN(O1814-M1814,0),\"0\")&\" days\"& IF(MOD((O1814-M1814)*24,24)>0,\" + \" & ROUNDDOWN((O1814-M1814)*24,0) & \" h \" & ROUNDDOWN(MOD((O1814-M1814)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F67176",null,"< >",4833,4835,2026,2026,{"$f":"WEEKNUM(L1815)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1815)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-10","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1815-L1815+ROUNDDOWN(O1815-M1815,0),\"0\")&\" days\"& IF(MOD((O1815-M1815)*24,24)>0,\" + \" & ROUNDDOWN((O1815-M1815)*24,0) & \" h \" & ROUNDDOWN(MOD((O1815-M1815)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A67176",null,"< >",4833,4835,2026,2026,{"$f":"WEEKNUM(L1816)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1816)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-09-28","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N1816-L1816+ROUNDDOWN(O1816-M1816,0),\"0\")&\" days\"& IF(MOD((O1816-M1816)*24,24)>0,\" + \" & ROUNDDOWN((O1816-M1816)*24,0) & \" h \" & ROUNDDOWN(MOD((O1816-M1816)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59989",null,"< >",4889,4903,2026,2026,{"$f":"WEEKNUM(L1817)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1817)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-03-09","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N1817-L1817+ROUNDDOWN(O1817-M1817,0),\"0\")&\" days\"& IF(MOD((O1817-M1817)*24,24)>0,\" + \" & ROUNDDOWN((O1817-M1817)*24,0) & \" h \" & ROUNDDOWN(MOD((O1817-M1817)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60369",null,"< >",4889,4903,2026,2026,{"$f":"WEEKNUM(L1818)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1818)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-04-20","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1818-L1818+ROUNDDOWN(O1818-M1818,0),\"0\")&\" days\"& IF(MOD((O1818-M1818)*24,24)>0,\" + \" & ROUNDDOWN((O1818-M1818)*24,0) & \" h \" & ROUNDDOWN(MOD((O1818-M1818)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A60369",null,"< >",4889,4903,2026,2026,{"$f":"WEEKNUM(L1819)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1819)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-03-09","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N1819-L1819+ROUNDDOWN(O1819-M1819,0),\"0\")&\" days\"& IF(MOD((O1819-M1819)*24,24)>0,\" + \" & ROUNDDOWN((O1819-M1819)*24,0) & \" h \" & ROUNDDOWN(MOD((O1819-M1819)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59187",null,"< >",4897,4900,2026,2026,{"$f":"WEEKNUM(L1820)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N1820)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-06-08","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1820-L1820+ROUNDDOWN(O1820-M1820,0),\"0\")&\" days\"& IF(MOD((O1820-M1820)*24,24)>0,\" + \" & ROUNDDOWN((O1820-M1820)*24,0) & \" h \" & ROUNDDOWN(MOD((O1820-M1820)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A59187",null,"< >",4897,4900,2026,2026,{"$f":"WEEKNUM(L1821)+[7]dates!$L$3-[7]dates!$H$3","v":29},{"$f":"WEEKNUM(N1821)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-07-13","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1821-L1821+ROUNDDOWN(O1821-M1821,0),\"0\")&\" days\"& IF(MOD((O1821-M1821)*24,24)>0,\" + \" & ROUNDDOWN((O1821-M1821)*24,0) & \" h \" & ROUNDDOWN(MOD((O1821-M1821)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B59187",null,"< >",4897,4900,2026,2026,{"$f":"WEEKNUM(L1822)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1822)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-08-31","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1822-L1822+ROUNDDOWN(O1822-M1822,0),\"0\")&\" days\"& IF(MOD((O1822-M1822)*24,24)>0,\" + \" & ROUNDDOWN((O1822-M1822)*24,0) & \" h \" & ROUNDDOWN(MOD((O1822-M1822)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F47693",null,"< >",4940,4942,2026,2026,{"$f":"WEEKNUM(L1823)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1823)+[7]dates!$L$3-[7]dates!$H$3","v":21},"2026-01-05","00:00:00","2026-05-17",0.99998842592592585,{"$f":"TEXT(N1823-L1823+ROUNDDOWN(O1823-M1823,0),\"0\")&\" days\"& IF(MOD((O1823-M1823)*24,24)>0,\" + \" & ROUNDDOWN((O1823-M1823)*24,0) & \" h \" & ROUNDDOWN(MOD((O1823-M1823)*1440,60),0) & \" min\",\"\")","v":"132 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A47693",null,"< >",4940,4942,2026,2026,{"$f":"WEEKNUM(L1824)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1824)+[7]dates!$L$3-[7]dates!$H$3","v":9},"2026-01-05","00:00:00","2026-02-22",0.99998842592592585,{"$f":"TEXT(N1824-L1824+ROUNDDOWN(O1824-M1824,0),\"0\")&\" days\"& IF(MOD((O1824-M1824)*24,24)>0,\" + \" & ROUNDDOWN((O1824-M1824)*24,0) & \" h \" & ROUNDDOWN(MOD((O1824-M1824)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59447",null,"< >",4940,5011,2026,2026,{"$f":"WEEKNUM(L1825)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1825)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-04-20","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1825-L1825+ROUNDDOWN(O1825-M1825,0),\"0\")&\" days\"& IF(MOD((O1825-M1825)*24,24)>0,\" + \" & ROUNDDOWN((O1825-M1825)*24,0) & \" h \" & ROUNDDOWN(MOD((O1825-M1825)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59448",null,"< >",5011,5041,2026,2026,{"$f":"WEEKNUM(L1826)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1826)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-04-20","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1826-L1826+ROUNDDOWN(O1826-M1826,0),\"0\")&\" days\"& IF(MOD((O1826-M1826)*24,24)>0,\" + \" & ROUNDDOWN((O1826-M1826)*24,0) & \" h \" & ROUNDDOWN(MOD((O1826-M1826)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F66695",null,"< >",5029,5043,2026,2026,{"$f":"WEEKNUM(L1827)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1827)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-05-18","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1827-L1827+ROUNDDOWN(O1827-M1827,0),\"0\")&\" days\"& IF(MOD((O1827-M1827)*24,24)>0,\" + \" & ROUNDDOWN((O1827-M1827)*24,0) & \" h \" & ROUNDDOWN(MOD((O1827-M1827)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58890",null,"< >",5041,5042,2026,2026,{"$f":"WEEKNUM(L1828)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1828)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-01-05","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1828-L1828+ROUNDDOWN(O1828-M1828,0),\"0\")&\" days\"& IF(MOD((O1828-M1828)*24,24)>0,\" + \" & ROUNDDOWN((O1828-M1828)*24,0) & \" h \" & ROUNDDOWN(MOD((O1828-M1828)*1440,60),0) & \" min\",\"\")","v":"125 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","G&C",null,"< >",5041,5042,2026,2026,{"$f":"WEEKNUM(L1829)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1829)+[7]dates!$L$3-[7]dates!$H$3","v":34},"2026-01-05","00:00:00","2026-08-16",0.99998842592592585,{"$f":"TEXT(N1829-L1829+ROUNDDOWN(O1829-M1829,0),\"0\")&\" days\"& IF(MOD((O1829-M1829)*24,24)>0,\" + \" & ROUNDDOWN((O1829-M1829)*24,0) & \" h \" & ROUNDDOWN(MOD((O1829-M1829)*1440,60),0) & \" min\",\"\")","v":"223 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","1G&C",null,"< >",5041,5042,2026,2026,{"$f":"WEEKNUM(L1830)+[7]dates!$L$3-[7]dates!$H$3","v":16},{"$f":"WEEKNUM(N1830)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-04-13","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1830-L1830+ROUNDDOWN(O1830-M1830,0),\"0\")&\" days\"& IF(MOD((O1830-M1830)*24,24)>0,\" + \" & ROUNDDOWN((O1830-M1830)*24,0) & \" h \" & ROUNDDOWN(MOD((O1830-M1830)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59446",null,"< >",5136,5156,2026,2026,{"$f":"WEEKNUM(L1831)+[7]dates!$L$3-[7]dates!$H$3","v":15},{"$f":"WEEKNUM(N1831)+[7]dates!$L$3-[7]dates!$H$3","v":18},"2026-04-06","00:00:00","2026-04-26",0.99998842592592585,{"$f":"TEXT(N1831-L1831+ROUNDDOWN(O1831-M1831,0),\"0\")&\" days\"& IF(MOD((O1831-M1831)*24,24)>0,\" + \" & ROUNDDOWN((O1831-M1831)*24,0) & \" h \" & ROUNDDOWN(MOD((O1831-M1831)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60772",null,"< >",5151,4973,2026,2026,{"$f":"WEEKNUM(L1832)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1832)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-01-05","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N1832-L1832+ROUNDDOWN(O1832-M1832,0),\"0\")&\" days\"& IF(MOD((O1832-M1832)*24,24)>0,\" + \" & ROUNDDOWN((O1832-M1832)*24,0) & \" h \" & ROUNDDOWN(MOD((O1832-M1832)*1440,60),0) & \" min\",\"\")","v":"195 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A60772",null,"< >",5151,4973,2026,2026,{"$f":"WEEKNUM(L1833)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1833)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-01-05","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1833-L1833+ROUNDDOWN(O1833-M1833,0),\"0\")&\" days\"& IF(MOD((O1833-M1833)*24,24)>0,\" + \" & ROUNDDOWN((O1833-M1833)*24,0) & \" h \" & ROUNDDOWN(MOD((O1833-M1833)*1440,60),0) & \" min\",\"\")","v":"139 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64691",null,"< >",5153,4975,2026,2026,{"$f":"WEEKNUM(L1834)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1834)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-04-20","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1834-L1834+ROUNDDOWN(O1834-M1834,0),\"0\")&\" days\"& IF(MOD((O1834-M1834)*24,24)>0,\" + \" & ROUNDDOWN((O1834-M1834)*24,0) & \" h \" & ROUNDDOWN(MOD((O1834-M1834)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65558",null,"< >",5191,5191,2026,2026,{"$f":"WEEKNUM(L1835)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1835)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-15","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1835-L1835+ROUNDDOWN(O1835-M1835,0),\"0\")&\" days\"& IF(MOD((O1835-M1835)*24,24)>0,\" + \" & ROUNDDOWN((O1835-M1835)*24,0) & \" h \" & ROUNDDOWN(MOD((O1835-M1835)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F55991",null,"< >",5191,5191,2026,2026,{"$f":"WEEKNUM(L1836)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1836)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-10","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1836-L1836+ROUNDDOWN(O1836-M1836,0),\"0\")&\" days\"& IF(MOD((O1836-M1836)*24,24)>0,\" + \" & ROUNDDOWN((O1836-M1836)*24,0) & \" h \" & ROUNDDOWN(MOD((O1836-M1836)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A55991",null,"< >",5191,5191,2026,2026,{"$f":"WEEKNUM(L1837)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1837)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-10-05","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1837-L1837+ROUNDDOWN(O1837-M1837,0),\"0\")&\" days\"& IF(MOD((O1837-M1837)*24,24)>0,\" + \" & ROUNDDOWN((O1837-M1837)*24,0) & \" h \" & ROUNDDOWN(MOD((O1837-M1837)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62758",null,"< >",5198,5226,2026,2026,{"$f":"WEEKNUM(L1838)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1838)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-10","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1838-L1838+ROUNDDOWN(O1838-M1838,0),\"0\")&\" days\"& IF(MOD((O1838-M1838)*24,24)>0,\" + \" & ROUNDDOWN((O1838-M1838)*24,0) & \" h \" & ROUNDDOWN(MOD((O1838-M1838)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A62758",null,"< >",5198,5226,2026,2026,{"$f":"WEEKNUM(L1839)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1839)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-10-05","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1839-L1839+ROUNDDOWN(O1839-M1839,0),\"0\")&\" days\"& IF(MOD((O1839-M1839)*24,24)>0,\" + \" & ROUNDDOWN((O1839-M1839)*24,0) & \" h \" & ROUNDDOWN(MOD((O1839-M1839)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F46808",null,"< >",5202,8516,2026,2026,{"$f":"WEEKNUM(L1840)+[7]dates!$L$3-[7]dates!$H$3","v":15},{"$f":"WEEKNUM(N1840)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-04-06","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1840-L1840+ROUNDDOWN(O1840-M1840,0),\"0\")&\" days\"& IF(MOD((O1840-M1840)*24,24)>0,\" + \" & ROUNDDOWN((O1840-M1840)*24,0) & \" h \" & ROUNDDOWN(MOD((O1840-M1840)*1440,60),0) & \" min\",\"\")","v":"118 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A46808",null,"< >",5202,8516,2026,2026,{"$f":"WEEKNUM(L1841)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1841)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-10","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1841-L1841+ROUNDDOWN(O1841-M1841,0),\"0\")&\" days\"& IF(MOD((O1841-M1841)*24,24)>0,\" + \" & ROUNDDOWN((O1841-M1841)*24,0) & \" h \" & ROUNDDOWN(MOD((O1841-M1841)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B46808",null,"< >",5202,8516,2026,2026,{"$f":"WEEKNUM(L1842)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1842)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-10-05","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1842-L1842+ROUNDDOWN(O1842-M1842,0),\"0\")&\" days\"& IF(MOD((O1842-M1842)*24,24)>0,\" + \" & ROUNDDOWN((O1842-M1842)*24,0) & \" h \" & ROUNDDOWN(MOD((O1842-M1842)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C46808",null,"< >",5202,8516,2026,2026,{"$f":"WEEKNUM(L1843)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1843)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-20","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1843-L1843+ROUNDDOWN(O1843-M1843,0),\"0\")&\" days\"& IF(MOD((O1843-M1843)*24,24)>0,\" + \" & ROUNDDOWN((O1843-M1843)*24,0) & \" h \" & ROUNDDOWN(MOD((O1843-M1843)*1440,60),0) & \" min\",\"\")","v":"97 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57907",null,"< >",5202,8516,2026,2026,{"$f":"WEEKNUM(L1844)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1844)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-01-05","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1844-L1844+ROUNDDOWN(O1844-M1844,0),\"0\")&\" days\"& IF(MOD((O1844-M1844)*24,24)>0,\" + \" & ROUNDDOWN((O1844-M1844)*24,0) & \" h \" & ROUNDDOWN(MOD((O1844-M1844)*1440,60),0) & \" min\",\"\")","v":"139 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A57907",null,"< >",5202,8516,2026,2026,{"$f":"WEEKNUM(L1845)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N1845)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-06-01","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1845-L1845+ROUNDDOWN(O1845-M1845,0),\"0\")&\" days\"& IF(MOD((O1845-M1845)*24,24)>0,\" + \" & ROUNDDOWN((O1845-M1845)*24,0) & \" h \" & ROUNDDOWN(MOD((O1845-M1845)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B57907",null,"< >",5202,8516,2026,2026,{"$f":"WEEKNUM(L1846)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1846)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-08-10","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1846-L1846+ROUNDDOWN(O1846-M1846,0),\"0\")&\" days\"& IF(MOD((O1846-M1846)*24,24)>0,\" + \" & ROUNDDOWN((O1846-M1846)*24,0) & \" h \" & ROUNDDOWN(MOD((O1846-M1846)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52922\nJH 4246",null,"< >",5320,5320,2026,2026,{"$f":"WEEKNUM(L1847)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1847)+[7]dates!$L$3-[7]dates!$H$3","v":12},"2026-02-09","00:00:00","2026-03-15",0.99998842592592585,{"$f":"TEXT(N1847-L1847+ROUNDDOWN(O1847-M1847,0),\"0\")&\" days\"& IF(MOD((O1847-M1847)*24,24)>0,\" + \" & ROUNDDOWN((O1847-M1847)*24,0) & \" h \" & ROUNDDOWN(MOD((O1847-M1847)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A52922\nAH 4246",null,"< >",5320,5320,2026,2026,{"$f":"WEEKNUM(L1848)+[7]dates!$L$3-[7]dates!$H$3","v":15},{"$f":"WEEKNUM(N1848)+[7]dates!$L$3-[7]dates!$H$3","v":18},"2026-04-06","00:00:00","2026-04-26",0.99998842592592585,{"$f":"TEXT(N1848-L1848+ROUNDDOWN(O1848-M1848,0),\"0\")&\" days\"& IF(MOD((O1848-M1848)*24,24)>0,\" + \" & ROUNDDOWN((O1848-M1848)*24,0) & \" h \" & ROUNDDOWN(MOD((O1848-M1848)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F46288",null,"< >",5358,5360,2026,2026,{"$f":"WEEKNUM(L1849)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1849)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-04-20","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1849-L1849+ROUNDDOWN(O1849-M1849,0),\"0\")&\" days\"& IF(MOD((O1849-M1849)*24,24)>0,\" + \" & ROUNDDOWN((O1849-M1849)*24,0) & \" h \" & ROUNDDOWN(MOD((O1849-M1849)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A46288",null,"< >",5358,5360,2026,2026,{"$f":"WEEKNUM(L1850)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1850)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-05-04","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1850-L1850+ROUNDDOWN(O1850-M1850,0),\"0\")&\" days\"& IF(MOD((O1850-M1850)*24,24)>0,\" + \" & ROUNDDOWN((O1850-M1850)*24,0) & \" h \" & ROUNDDOWN(MOD((O1850-M1850)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F39730",null,"< >",5360,5364,2026,2026,{"$f":"WEEKNUM(L1851)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1851)+[7]dates!$L$3-[7]dates!$H$3","v":18},"2026-01-05","00:00:00","2026-04-26",0.99998842592592585,{"$f":"TEXT(N1851-L1851+ROUNDDOWN(O1851-M1851,0),\"0\")&\" days\"& IF(MOD((O1851-M1851)*24,24)>0,\" + \" & ROUNDDOWN((O1851-M1851)*24,0) & \" h \" & ROUNDDOWN(MOD((O1851-M1851)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59194",null,"< >",5472,5472,2026,2026,{"$f":"WEEKNUM(L1852)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1852)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-04-27","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1852-L1852+ROUNDDOWN(O1852-M1852,0),\"0\")&\" days\"& IF(MOD((O1852-M1852)*24,24)>0,\" + \" & ROUNDDOWN((O1852-M1852)*24,0) & \" h \" & ROUNDDOWN(MOD((O1852-M1852)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A59194",null,"< >",5472,5472,2026,2026,{"$f":"WEEKNUM(L1853)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1853)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-10","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1853-L1853+ROUNDDOWN(O1853-M1853,0),\"0\")&\" days\"& IF(MOD((O1853-M1853)*24,24)>0,\" + \" & ROUNDDOWN((O1853-M1853)*24,0) & \" h \" & ROUNDDOWN(MOD((O1853-M1853)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B59194",null,"< >",5472,5472,2026,2026,{"$f":"WEEKNUM(L1854)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1854)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-10-05","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1854-L1854+ROUNDDOWN(O1854-M1854,0),\"0\")&\" days\"& IF(MOD((O1854-M1854)*24,24)>0,\" + \" & ROUNDDOWN((O1854-M1854)*24,0) & \" h \" & ROUNDDOWN(MOD((O1854-M1854)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C59194",null,"< >",5472,5472,2026,2026,{"$f":"WEEKNUM(L1855)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1855)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-05-04","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1855-L1855+ROUNDDOWN(O1855-M1855,0),\"0\")&\" days\"& IF(MOD((O1855-M1855)*24,24)>0,\" + \" & ROUNDDOWN((O1855-M1855)*24,0) & \" h \" & ROUNDDOWN(MOD((O1855-M1855)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F47844",null,"< >",5600,5602,2026,2026,{"$f":"WEEKNUM(L1856)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1856)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-10","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1856-L1856+ROUNDDOWN(O1856-M1856,0),\"0\")&\" days\"& IF(MOD((O1856-M1856)*24,24)>0,\" + \" & ROUNDDOWN((O1856-M1856)*24,0) & \" h \" & ROUNDDOWN(MOD((O1856-M1856)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52872",null,"< >",5634,5634,2026,2026,{"$f":"WEEKNUM(L1857)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N1857)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-08","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1857-L1857+ROUNDDOWN(O1857-M1857,0),\"0\")&\" days\"& IF(MOD((O1857-M1857)*24,24)>0,\" + \" & ROUNDDOWN((O1857-M1857)*24,0) & \" h \" & ROUNDDOWN(MOD((O1857-M1857)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A52872",null,"< >",5634,5634,2026,2026,{"$f":"WEEKNUM(L1858)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1858)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-10","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1858-L1858+ROUNDDOWN(O1858-M1858,0),\"0\")&\" days\"& IF(MOD((O1858-M1858)*24,24)>0,\" + \" & ROUNDDOWN((O1858-M1858)*24,0) & \" h \" & ROUNDDOWN(MOD((O1858-M1858)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63511",null,"< >",5636,5663,2026,2026,{"$f":"WEEKNUM(L1859)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1859)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-02-23","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1859-L1859+ROUNDDOWN(O1859-M1859,0),\"0\")&\" days\"& IF(MOD((O1859-M1859)*24,24)>0,\" + \" & ROUNDDOWN((O1859-M1859)*24,0) & \" h \" & ROUNDDOWN(MOD((O1859-M1859)*1440,60),0) & \" min\",\"\")","v":"132 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A63511",null,"< >",5636,5663,2026,2026,{"$f":"WEEKNUM(L1860)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1860)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-10","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1860-L1860+ROUNDDOWN(O1860-M1860,0),\"0\")&\" days\"& IF(MOD((O1860-M1860)*24,24)>0,\" + \" & ROUNDDOWN((O1860-M1860)*24,0) & \" h \" & ROUNDDOWN(MOD((O1860-M1860)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B63511",null,"< >",5636,5663,2026,2026,{"$f":"WEEKNUM(L1861)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1861)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-10-05","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1861-L1861+ROUNDDOWN(O1861-M1861,0),\"0\")&\" days\"& IF(MOD((O1861-M1861)*24,24)>0,\" + \" & ROUNDDOWN((O1861-M1861)*24,0) & \" h \" & ROUNDDOWN(MOD((O1861-M1861)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F66487",null,"< >",5667,5675,2026,2026,{"$f":"WEEKNUM(L1862)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1862)+[7]dates!$L$3-[7]dates!$H$3","v":16},"2026-03-09","00:00:00","2026-04-12",0.99998842592592585,{"$f":"TEXT(N1862-L1862+ROUNDDOWN(O1862-M1862,0),\"0\")&\" days\"& IF(MOD((O1862-M1862)*24,24)>0,\" + \" & ROUNDDOWN((O1862-M1862)*24,0) & \" h \" & ROUNDDOWN(MOD((O1862-M1862)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A66487",null,"< >",5667,5675,2026,2026,{"$f":"WEEKNUM(L1863)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N1863)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-08","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1863-L1863+ROUNDDOWN(O1863-M1863,0),\"0\")&\" days\"& IF(MOD((O1863-M1863)*24,24)>0,\" + \" & ROUNDDOWN((O1863-M1863)*24,0) & \" h \" & ROUNDDOWN(MOD((O1863-M1863)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B66487",null,"< >",5667,5675,2026,2026,{"$f":"WEEKNUM(L1864)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1864)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-10","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N1864-L1864+ROUNDDOWN(O1864-M1864,0),\"0\")&\" days\"& IF(MOD((O1864-M1864)*24,24)>0,\" + \" & ROUNDDOWN((O1864-M1864)*24,0) & \" h \" & ROUNDDOWN(MOD((O1864-M1864)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C66487",null,"< >",5667,5675,2026,2026,{"$f":"WEEKNUM(L1865)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1865)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-10-05","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1865-L1865+ROUNDDOWN(O1865-M1865,0),\"0\")&\" days\"& IF(MOD((O1865-M1865)*24,24)>0,\" + \" & ROUNDDOWN((O1865-M1865)*24,0) & \" h \" & ROUNDDOWN(MOD((O1865-M1865)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60999",null,"< >",5734,5725,2026,2026,{"$f":"WEEKNUM(L1866)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1866)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-01-05","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1866-L1866+ROUNDDOWN(O1866-M1866,0),\"0\")&\" days\"& IF(MOD((O1866-M1866)*24,24)>0,\" + \" & ROUNDDOWN((O1866-M1866)*24,0) & \" h \" & ROUNDDOWN(MOD((O1866-M1866)*1440,60),0) & \" min\",\"\")","v":"216 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A60999",null,"< >",5734,5725,2026,2026,{"$f":"WEEKNUM(L1867)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1867)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-01-19","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1867-L1867+ROUNDDOWN(O1867-M1867,0),\"0\")&\" days\"& IF(MOD((O1867-M1867)*24,24)>0,\" + \" & ROUNDDOWN((O1867-M1867)*24,0) & \" h \" & ROUNDDOWN(MOD((O1867-M1867)*1440,60),0) & \" min\",\"\")","v":"104 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64909",null,"< >",5737,5746,2026,2026,{"$f":"WEEKNUM(L1868)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1868)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-16","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1868-L1868+ROUNDDOWN(O1868-M1868,0),\"0\")&\" days\"& IF(MOD((O1868-M1868)*24,24)>0,\" + \" & ROUNDDOWN((O1868-M1868)*24,0) & \" h \" & ROUNDDOWN(MOD((O1868-M1868)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A64909",null,"< >",5737,5746,2026,2026,{"$f":"WEEKNUM(L1869)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1869)+[7]dates!$L$3-[7]dates!$H$3","v":10},"2026-02-16","00:00:00","2026-03-01",0.99998842592592585,{"$f":"TEXT(N1869-L1869+ROUNDDOWN(O1869-M1869,0),\"0\")&\" days\"& IF(MOD((O1869-M1869)*24,24)>0,\" + \" & ROUNDDOWN((O1869-M1869)*24,0) & \" h \" & ROUNDDOWN(MOD((O1869-M1869)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62001",null,"< >",5739,5737,2026,2026,{"$f":"WEEKNUM(L1870)+[7]dates!$L$3-[7]dates!$H$3","v":37},{"$f":"WEEKNUM(N1870)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-09-07","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N1870-L1870+ROUNDDOWN(O1870-M1870,0),\"0\")&\" days\"& IF(MOD((O1870-M1870)*24,24)>0,\" + \" & ROUNDDOWN((O1870-M1870)*24,0) & \" h \" & ROUNDDOWN(MOD((O1870-M1870)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A62001",null,"< >",5739,5737,2026,2026,{"$f":"WEEKNUM(L1871)+[7]dates!$L$3-[7]dates!$H$3","v":39},{"$f":"WEEKNUM(N1871)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-09-21","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N1871-L1871+ROUNDDOWN(O1871-M1871,0),\"0\")&\" days\"& IF(MOD((O1871-M1871)*24,24)>0,\" + \" & ROUNDDOWN((O1871-M1871)*24,0) & \" h \" & ROUNDDOWN(MOD((O1871-M1871)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64908",null,"< >",5746,5766,2026,2026,{"$f":"WEEKNUM(L1872)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1872)+[7]dates!$L$3-[7]dates!$H$3","v":12},"2026-01-26","00:00:00","2026-03-15",0.99998842592592585,{"$f":"TEXT(N1872-L1872+ROUNDDOWN(O1872-M1872,0),\"0\")&\" days\"& IF(MOD((O1872-M1872)*24,24)>0,\" + \" & ROUNDDOWN((O1872-M1872)*24,0) & \" h \" & ROUNDDOWN(MOD((O1872-M1872)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62563",null,"< >",5747,8507,2026,2026,{"$f":"WEEKNUM(L1873)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1873)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-02-09","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1873-L1873+ROUNDDOWN(O1873-M1873,0),\"0\")&\" days\"& IF(MOD((O1873-M1873)*24,24)>0,\" + \" & ROUNDDOWN((O1873-M1873)*24,0) & \" h \" & ROUNDDOWN(MOD((O1873-M1873)*1440,60),0) & \" min\",\"\")","v":"125 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B62758",null,"< >",5760,5722,2026,2026,{"$f":"WEEKNUM(L1874)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1874)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-15","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1874-L1874+ROUNDDOWN(O1874-M1874,0),\"0\")&\" days\"& IF(MOD((O1874-M1874)*24,24)>0,\" + \" & ROUNDDOWN((O1874-M1874)*24,0) & \" h \" & ROUNDDOWN(MOD((O1874-M1874)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C62758",null,"< >",5760,5722,2026,2026,{"$f":"WEEKNUM(L1875)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N1875)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-07-20","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1875-L1875+ROUNDDOWN(O1875-M1875,0),\"0\")&\" days\"& IF(MOD((O1875-M1875)*24,24)>0,\" + \" & ROUNDDOWN((O1875-M1875)*24,0) & \" h \" & ROUNDDOWN(MOD((O1875-M1875)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1876)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1876)+[7]dates!$L$3-[7]dates!$H$3","v":16},"2026-01-26","00:00:00","2026-04-12",0.99998842592592585,{"$f":"TEXT(N1876-L1876+ROUNDDOWN(O1876-M1876,0),\"0\")&\" days\"& IF(MOD((O1876-M1876)*24,24)>0,\" + \" & ROUNDDOWN((O1876-M1876)*24,0) & \" h \" & ROUNDDOWN(MOD((O1876-M1876)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1877)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N1877)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-06-08","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1877-L1877+ROUNDDOWN(O1877-M1877,0),\"0\")&\" days\"& IF(MOD((O1877-M1877)*24,24)>0,\" + \" & ROUNDDOWN((O1877-M1877)*24,0) & \" h \" & ROUNDDOWN(MOD((O1877-M1877)*1440,60),0) & \" min\",\"\")","v":"181 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1878)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1878)+[7]dates!$L$3-[7]dates!$H$3","v":13},"2026-03-09","00:00:00","2026-03-22",0.99998842592592585,{"$f":"TEXT(N1878-L1878+ROUNDDOWN(O1878-M1878,0),\"0\")&\" days\"& IF(MOD((O1878-M1878)*24,24)>0,\" + \" & ROUNDDOWN((O1878-M1878)*24,0) & \" h \" & ROUNDDOWN(MOD((O1878-M1878)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1879)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N1879)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-03-23","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1879-L1879+ROUNDDOWN(O1879-M1879,0),\"0\")&\" days\"& IF(MOD((O1879-M1879)*24,24)>0,\" + \" & ROUNDDOWN((O1879-M1879)*24,0) & \" h \" & ROUNDDOWN(MOD((O1879-M1879)*1440,60),0) & \" min\",\"\")","v":"258 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1880)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1880)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-05-18","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1880-L1880+ROUNDDOWN(O1880-M1880,0),\"0\")&\" days\"& IF(MOD((O1880-M1880)*24,24)>0,\" + \" & ROUNDDOWN((O1880-M1880)*24,0) & \" h \" & ROUNDDOWN(MOD((O1880-M1880)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","H57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1881)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N1881)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-06-08","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1881-L1881+ROUNDDOWN(O1881-M1881,0),\"0\")&\" days\"& IF(MOD((O1881-M1881)*24,24)>0,\" + \" & ROUNDDOWN((O1881-M1881)*24,0) & \" h \" & ROUNDDOWN(MOD((O1881-M1881)*1440,60),0) & \" min\",\"\")","v":"181 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","K57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1882)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1882)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-04-20","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1882-L1882+ROUNDDOWN(O1882-M1882,0),\"0\")&\" days\"& IF(MOD((O1882-M1882)*24,24)>0,\" + \" & ROUNDDOWN((O1882-M1882)*24,0) & \" h \" & ROUNDDOWN(MOD((O1882-M1882)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","L57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1883)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N1883)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-06-08","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1883-L1883+ROUNDDOWN(O1883-M1883,0),\"0\")&\" days\"& IF(MOD((O1883-M1883)*24,24)>0,\" + \" & ROUNDDOWN((O1883-M1883)*24,0) & \" h \" & ROUNDDOWN(MOD((O1883-M1883)*1440,60),0) & \" min\",\"\")","v":"181 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","M57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1884)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1884)+[7]dates!$L$3-[7]dates!$H$3","v":8},"2026-01-26","00:00:00","2026-02-15",0.99998842592592585,{"$f":"TEXT(N1884-L1884+ROUNDDOWN(O1884-M1884,0),\"0\")&\" days\"& IF(MOD((O1884-M1884)*24,24)>0,\" + \" & ROUNDDOWN((O1884-M1884)*24,0) & \" h \" & ROUNDDOWN(MOD((O1884-M1884)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","N57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1885)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1885)+[7]dates!$L$3-[7]dates!$H$3","v":21},"2026-02-16","00:00:00","2026-05-17",0.99998842592592585,{"$f":"TEXT(N1885-L1885+ROUNDDOWN(O1885-M1885,0),\"0\")&\" days\"& IF(MOD((O1885-M1885)*24,24)>0,\" + \" & ROUNDDOWN((O1885-M1885)*24,0) & \" h \" & ROUNDDOWN(MOD((O1885-M1885)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","P57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1886)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1886)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-05-18","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1886-L1886+ROUNDDOWN(O1886-M1886,0),\"0\")&\" days\"& IF(MOD((O1886-M1886)*24,24)>0,\" + \" & ROUNDDOWN((O1886-M1886)*24,0) & \" h \" & ROUNDDOWN(MOD((O1886-M1886)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","R57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1887)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N1887)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-06-08","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1887-L1887+ROUNDDOWN(O1887-M1887,0),\"0\")&\" days\"& IF(MOD((O1887-M1887)*24,24)>0,\" + \" & ROUNDDOWN((O1887-M1887)*24,0) & \" h \" & ROUNDDOWN(MOD((O1887-M1887)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","S57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1888)+[7]dates!$L$3-[7]dates!$H$3","v":35},{"$f":"WEEKNUM(N1888)+[7]dates!$L$3-[7]dates!$H$3","v":37},"2026-08-24","00:00:00","2026-09-06",0.99998842592592585,{"$f":"TEXT(N1888-L1888+ROUNDDOWN(O1888-M1888,0),\"0\")&\" days\"& IF(MOD((O1888-M1888)*24,24)>0,\" + \" & ROUNDDOWN((O1888-M1888)*24,0) & \" h \" & ROUNDDOWN(MOD((O1888-M1888)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","V57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1889)+[7]dates!$L$3-[7]dates!$H$3","v":37},{"$f":"WEEKNUM(N1889)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-09-07","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1889-L1889+ROUNDDOWN(O1889-M1889,0),\"0\")&\" days\"& IF(MOD((O1889-M1889)*24,24)>0,\" + \" & ROUNDDOWN((O1889-M1889)*24,0) & \" h \" & ROUNDDOWN(MOD((O1889-M1889)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","W57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1890)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1890)+[7]dates!$L$3-[7]dates!$H$3","v":8},"2026-01-26","00:00:00","2026-02-15",0.99998842592592585,{"$f":"TEXT(N1890-L1890+ROUNDDOWN(O1890-M1890,0),\"0\")&\" days\"& IF(MOD((O1890-M1890)*24,24)>0,\" + \" & ROUNDDOWN((O1890-M1890)*24,0) & \" h \" & ROUNDDOWN(MOD((O1890-M1890)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","Y57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1891)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N1891)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-06-22","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1891-L1891+ROUNDDOWN(O1891-M1891,0),\"0\")&\" days\"& IF(MOD((O1891-M1891)*24,24)>0,\" + \" & ROUNDDOWN((O1891-M1891)*24,0) & \" h \" & ROUNDDOWN(MOD((O1891-M1891)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","Z57811",null,"< >",5936,6673,2026,2026,{"$f":"WEEKNUM(L1892)+[7]dates!$L$3-[7]dates!$H$3","v":37},{"$f":"WEEKNUM(N1892)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-09-07","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1892-L1892+ROUNDDOWN(O1892-M1892,0),\"0\")&\" days\"& IF(MOD((O1892-M1892)*24,24)>0,\" + \" & ROUNDDOWN((O1892-M1892)*24,0) & \" h \" & ROUNDDOWN(MOD((O1892-M1892)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60430",null,"< >",5978,5985,2026,2026,{"$f":"WEEKNUM(L1893)+[7]dates!$L$3-[7]dates!$H$3","v":32},{"$f":"WEEKNUM(N1893)+[7]dates!$L$3-[7]dates!$H$3","v":38},"2026-08-03","00:00:00","2026-09-13",0.99998842592592585,{"$f":"TEXT(N1893-L1893+ROUNDDOWN(O1893-M1893,0),\"0\")&\" days\"& IF(MOD((O1893-M1893)*24,24)>0,\" + \" & ROUNDDOWN((O1893-M1893)*24,0) & \" h \" & ROUNDDOWN(MOD((O1893-M1893)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH4143\nF51277",null,"< >",6065,6063,2026,2026,{"$f":"WEEKNUM(L1894)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1894)+[7]dates!$L$3-[7]dates!$H$3","v":47},"2026-01-05","00:00:00","2026-11-15",0.99998842592592585,{"$f":"TEXT(N1894-L1894+ROUNDDOWN(O1894-M1894,0),\"0\")&\" days\"& IF(MOD((O1894-M1894)*24,24)>0,\" + \" & ROUNDDOWN((O1894-M1894)*24,0) & \" h \" & ROUNDDOWN(MOD((O1894-M1894)*1440,60),0) & \" min\",\"\")","v":"314 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F39664",null,"< >",6092,8363,2026,2026,{"$f":"WEEKNUM(L1895)+[7]dates!$L$3-[7]dates!$H$3","v":37},{"$f":"WEEKNUM(N1895)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-09-07","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1895-L1895+ROUNDDOWN(O1895-M1895,0),\"0\")&\" days\"& IF(MOD((O1895-M1895)*24,24)>0,\" + \" & ROUNDDOWN((O1895-M1895)*24,0) & \" h \" & ROUNDDOWN(MOD((O1895-M1895)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62385",null,"< >",6149,6150,2026,2026,{"$f":"WEEKNUM(L1896)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1896)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-06-15","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N1896-L1896+ROUNDDOWN(O1896-M1896,0),\"0\")&\" days\"& IF(MOD((O1896-M1896)*24,24)>0,\" + \" & ROUNDDOWN((O1896-M1896)*24,0) & \" h \" & ROUNDDOWN(MOD((O1896-M1896)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59304",null,"< >",6152,6172,2026,2026,{"$f":"WEEKNUM(L1897)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N1897)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-01","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1897-L1897+ROUNDDOWN(O1897-M1897,0),\"0\")&\" days\"& IF(MOD((O1897-M1897)*24,24)>0,\" + \" & ROUNDDOWN((O1897-M1897)*24,0) & \" h \" & ROUNDDOWN(MOD((O1897-M1897)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A59304",null,"< >",6152,6172,2026,2026,{"$f":"WEEKNUM(L1898)+[7]dates!$L$3-[7]dates!$H$3","v":31},{"$f":"WEEKNUM(N1898)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-07-27","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1898-L1898+ROUNDDOWN(O1898-M1898,0),\"0\")&\" days\"& IF(MOD((O1898-M1898)*24,24)>0,\" + \" & ROUNDDOWN((O1898-M1898)*24,0) & \" h \" & ROUNDDOWN(MOD((O1898-M1898)*1440,60),0) & \" min\",\"\")","v":"125 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B59304",null,"< >",6154,8372,2026,2026,{"$f":"WEEKNUM(L1899)+[7]dates!$L$3-[7]dates!$H$3","v":34},{"$f":"WEEKNUM(N1899)+[7]dates!$L$3-[7]dates!$H$3","v":46},"2026-08-17","00:00:00","2026-11-08",0.99998842592592585,{"$f":"TEXT(N1899-L1899+ROUNDDOWN(O1899-M1899,0),\"0\")&\" days\"& IF(MOD((O1899-M1899)*24,24)>0,\" + \" & ROUNDDOWN((O1899-M1899)*24,0) & \" h \" & ROUNDDOWN(MOD((O1899-M1899)*1440,60),0) & \" min\",\"\")","v":"83 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62274",null,"< >",6172,8372,2026,2026,{"$f":"WEEKNUM(L1900)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1900)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-03-09","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N1900-L1900+ROUNDDOWN(O1900-M1900,0),\"0\")&\" days\"& IF(MOD((O1900-M1900)*24,24)>0,\" + \" & ROUNDDOWN((O1900-M1900)*24,0) & \" h \" & ROUNDDOWN(MOD((O1900-M1900)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A62274",null,"< >",6172,8372,2026,2026,{"$f":"WEEKNUM(L1901)+[7]dates!$L$3-[7]dates!$H$3","v":35},{"$f":"WEEKNUM(N1901)+[7]dates!$L$3-[7]dates!$H$3","v":37},"2026-08-24","00:00:00","2026-09-06",0.99998842592592585,{"$f":"TEXT(N1901-L1901+ROUNDDOWN(O1901-M1901,0),\"0\")&\" days\"& IF(MOD((O1901-M1901)*24,24)>0,\" + \" & ROUNDDOWN((O1901-M1901)*24,0) & \" h \" & ROUNDDOWN(MOD((O1901-M1901)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B62274",null,"< >",6172,8372,2026,2026,{"$f":"WEEKNUM(L1902)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1902)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-10-05","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1902-L1902+ROUNDDOWN(O1902-M1902,0),\"0\")&\" days\"& IF(MOD((O1902-M1902)*24,24)>0,\" + \" & ROUNDDOWN((O1902-M1902)*24,0) & \" h \" & ROUNDDOWN(MOD((O1902-M1902)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60955",null,"< >",6173,6263,2026,2026,{"$f":"WEEKNUM(L1903)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1903)+[7]dates!$L$3-[7]dates!$H$3","v":26},"2026-04-27","00:00:00","2026-06-21",0.99998842592592585,{"$f":"TEXT(N1903-L1903+ROUNDDOWN(O1903-M1903,0),\"0\")&\" days\"& IF(MOD((O1903-M1903)*24,24)>0,\" + \" & ROUNDDOWN((O1903-M1903)*24,0) & \" h \" & ROUNDDOWN(MOD((O1903-M1903)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F39972",null,"< >",6175,6154,2026,2026,{"$f":"WEEKNUM(L1904)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1904)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-16","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1904-L1904+ROUNDDOWN(O1904-M1904,0),\"0\")&\" days\"& IF(MOD((O1904-M1904)*24,24)>0,\" + \" & ROUNDDOWN((O1904-M1904)*24,0) & \" h \" & ROUNDDOWN(MOD((O1904-M1904)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62377",null,"< >",6176,6153,2026,2026,{"$f":"WEEKNUM(L1905)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N1905)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-01","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1905-L1905+ROUNDDOWN(O1905-M1905,0),\"0\")&\" days\"& IF(MOD((O1905-M1905)*24,24)>0,\" + \" & ROUNDDOWN((O1905-M1905)*24,0) & \" h \" & ROUNDDOWN(MOD((O1905-M1905)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A62377",null,"< >",6176,6153,2026,2026,{"$f":"WEEKNUM(L1906)+[7]dates!$L$3-[7]dates!$H$3","v":31},{"$f":"WEEKNUM(N1906)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-07-27","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1906-L1906+ROUNDDOWN(O1906-M1906,0),\"0\")&\" days\"& IF(MOD((O1906-M1906)*24,24)>0,\" + \" & ROUNDDOWN((O1906-M1906)*24,0) & \" h \" & ROUNDDOWN(MOD((O1906-M1906)*1440,60),0) & \" min\",\"\")","v":"125 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63616",null,"< >",6194,6178,2026,2026,{"$f":"WEEKNUM(L1907)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1907)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-01-19","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1907-L1907+ROUNDDOWN(O1907-M1907,0),\"0\")&\" days\"& IF(MOD((O1907-M1907)*24,24)>0,\" + \" & ROUNDDOWN((O1907-M1907)*24,0) & \" h \" & ROUNDDOWN(MOD((O1907-M1907)*1440,60),0) & \" min\",\"\")","v":"104 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A63616",null,"< >",6194,6192,2026,2026,{"$f":"WEEKNUM(L1908)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1908)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-01-19","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1908-L1908+ROUNDDOWN(O1908-M1908,0),\"0\")&\" days\"& IF(MOD((O1908-M1908)*24,24)>0,\" + \" & ROUNDDOWN((O1908-M1908)*24,0) & \" h \" & ROUNDDOWN(MOD((O1908-M1908)*1440,60),0) & \" min\",\"\")","v":"104 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F43230",null,"< >",6198,6193,2026,2026,{"$f":"WEEKNUM(L1909)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1909)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-10-05","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N1909-L1909+ROUNDDOWN(O1909-M1909,0),\"0\")&\" days\"& IF(MOD((O1909-M1909)*24,24)>0,\" + \" & ROUNDDOWN((O1909-M1909)*24,0) & \" h \" & ROUNDDOWN(MOD((O1909-M1909)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64490",null,"< >",6221,6228,2026,2026,{"$f":"WEEKNUM(L1910)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1910)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-04-27","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1910-L1910+ROUNDDOWN(O1910-M1910,0),\"0\")&\" days\"& IF(MOD((O1910-M1910)*24,24)>0,\" + \" & ROUNDDOWN((O1910-M1910)*24,0) & \" h \" & ROUNDDOWN(MOD((O1910-M1910)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A64490",null,"< >",6221,6223,2026,2026,{"$f":"WEEKNUM(L1911)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1911)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-05-04","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1911-L1911+ROUNDDOWN(O1911-M1911,0),\"0\")&\" days\"& IF(MOD((O1911-M1911)*24,24)>0,\" + \" & ROUNDDOWN((O1911-M1911)*24,0) & \" h \" & ROUNDDOWN(MOD((O1911-M1911)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60279",null,"< >",6262,6273,2026,2026,{"$f":"WEEKNUM(L1912)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1912)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-26","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1912-L1912+ROUNDDOWN(O1912-M1912,0),\"0\")&\" days\"& IF(MOD((O1912-M1912)*24,24)>0,\" + \" & ROUNDDOWN((O1912-M1912)*24,0) & \" h \" & ROUNDDOWN(MOD((O1912-M1912)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A60279",null,"< >",6262,6273,2026,2026,{"$f":"WEEKNUM(L1913)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1913)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-26","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N1913-L1913+ROUNDDOWN(O1913-M1913,0),\"0\")&\" days\"& IF(MOD((O1913-M1913)*24,24)>0,\" + \" & ROUNDDOWN((O1913-M1913)*24,0) & \" h \" & ROUNDDOWN(MOD((O1913-M1913)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F44059",null,"< >",6366,1103,2026,2026,{"$f":"WEEKNUM(L1914)+[7]dates!$L$3-[7]dates!$H$3","v":28},{"$f":"WEEKNUM(N1914)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-07-06","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N1914-L1914+ROUNDDOWN(O1914-M1914,0),\"0\")&\" days\"& IF(MOD((O1914-M1914)*24,24)>0,\" + \" & ROUNDDOWN((O1914-M1914)*24,0) & \" h \" & ROUNDDOWN(MOD((O1914-M1914)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52358",null,"< >",6368,6371,2026,2026,{"$f":"WEEKNUM(L1915)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1915)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-01-26","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1915-L1915+ROUNDDOWN(O1915-M1915,0),\"0\")&\" days\"& IF(MOD((O1915-M1915)*24,24)>0,\" + \" & ROUNDDOWN((O1915-M1915)*24,0) & \" h \" & ROUNDDOWN(MOD((O1915-M1915)*1440,60),0) & \" min\",\"\")","v":"167 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52762",null,"< >",6368,6371,2026,2026,{"$f":"WEEKNUM(L1916)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1916)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-01-26","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1916-L1916+ROUNDDOWN(O1916-M1916,0),\"0\")&\" days\"& IF(MOD((O1916-M1916)*24,24)>0,\" + \" & ROUNDDOWN((O1916-M1916)*24,0) & \" h \" & ROUNDDOWN(MOD((O1916-M1916)*1440,60),0) & \" min\",\"\")","v":"167 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A52358",null,"< >",6368,6371,2026,2026,{"$f":"WEEKNUM(L1917)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1917)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-02-23","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N1917-L1917+ROUNDDOWN(O1917-M1917,0),\"0\")&\" days\"& IF(MOD((O1917-M1917)*24,24)>0,\" + \" & ROUNDDOWN((O1917-M1917)*24,0) & \" h \" & ROUNDDOWN(MOD((O1917-M1917)*1440,60),0) & \" min\",\"\")","v":"132 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F52766",null,"< >",6372,6283,2026,2026,{"$f":"WEEKNUM(L1918)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1918)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-03-16","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1918-L1918+ROUNDDOWN(O1918-M1918,0),\"0\")&\" days\"& IF(MOD((O1918-M1918)*24,24)>0,\" + \" & ROUNDDOWN((O1918-M1918)*24,0) & \" h \" & ROUNDDOWN(MOD((O1918-M1918)*1440,60),0) & \" min\",\"\")","v":"118 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH3907",null,"< >",6374,6375,2026,2026,{"$f":"WEEKNUM(L1919)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1919)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1919-L1919+ROUNDDOWN(O1919-M1919,0),\"0\")&\" days\"& IF(MOD((O1919-M1919)*24,24)>0,\" + \" & ROUNDDOWN((O1919-M1919)*24,0) & \" h \" & ROUNDDOWN(MOD((O1919-M1919)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH3907",null,"< >",6374,6375,2026,2026,{"$f":"WEEKNUM(L1920)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1920)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1920-L1920+ROUNDDOWN(O1920-M1920,0),\"0\")&\" days\"& IF(MOD((O1920-M1920)*24,24)>0,\" + \" & ROUNDDOWN((O1920-M1920)*24,0) & \" h \" & ROUNDDOWN(MOD((O1920-M1920)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57938",null,"< >",6390,6373,2026,2026,{"$f":"WEEKNUM(L1921)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1921)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1921-L1921+ROUNDDOWN(O1921-M1921,0),\"0\")&\" days\"& IF(MOD((O1921-M1921)*24,24)>0,\" + \" & ROUNDDOWN((O1921-M1921)*24,0) & \" h \" & ROUNDDOWN(MOD((O1921-M1921)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A57938",null,"< >",6390,6373,2026,2026,{"$f":"WEEKNUM(L1922)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1922)+[7]dates!$L$3-[7]dates!$H$3","v":46},"2026-10-05","00:00:00","2026-11-08",0.99998842592592585,{"$f":"TEXT(N1922-L1922+ROUNDDOWN(O1922-M1922,0),\"0\")&\" days\"& IF(MOD((O1922-M1922)*24,24)>0,\" + \" & ROUNDDOWN((O1922-M1922)*24,0) & \" h \" & ROUNDDOWN(MOD((O1922-M1922)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60476",null,"< >",6473,7451,2026,2026,{"$f":"WEEKNUM(L1923)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N1923)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-02-02","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1923-L1923+ROUNDDOWN(O1923-M1923,0),\"0\")&\" days\"& IF(MOD((O1923-M1923)*24,24)>0,\" + \" & ROUNDDOWN((O1923-M1923)*24,0) & \" h \" & ROUNDDOWN(MOD((O1923-M1923)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A60476",null,"< >",6473,7451,2026,2026,{"$f":"WEEKNUM(L1924)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N1924)+[7]dates!$L$3-[7]dates!$H$3","v":18},"2026-02-23","00:00:00","2026-04-26",0.99998842592592585,{"$f":"TEXT(N1924-L1924+ROUNDDOWN(O1924-M1924,0),\"0\")&\" days\"& IF(MOD((O1924-M1924)*24,24)>0,\" + \" & ROUNDDOWN((O1924-M1924)*24,0) & \" h \" & ROUNDDOWN(MOD((O1924-M1924)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F48977",null,"< >",6482,6475,2026,2026,{"$f":"WEEKNUM(L1925)+[7]dates!$L$3-[7]dates!$H$3","v":10},{"$f":"WEEKNUM(N1925)+[7]dates!$L$3-[7]dates!$H$3","v":26},"2026-03-02","00:00:00","2026-06-21",0.99998842592592585,{"$f":"TEXT(N1925-L1925+ROUNDDOWN(O1925-M1925,0),\"0\")&\" days\"& IF(MOD((O1925-M1925)*24,24)>0,\" + \" & ROUNDDOWN((O1925-M1925)*24,0) & \" h \" & ROUNDDOWN(MOD((O1925-M1925)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64849",null,"< >",6494,6497,2026,2026,{"$f":"WEEKNUM(L1926)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N1926)+[7]dates!$L$3-[7]dates!$H$3","v":39},"2026-07-20","00:00:00","2026-09-20",0.99998842592592585,{"$f":"TEXT(N1926-L1926+ROUNDDOWN(O1926-M1926,0),\"0\")&\" days\"& IF(MOD((O1926-M1926)*24,24)>0,\" + \" & ROUNDDOWN((O1926-M1926)*24,0) & \" h \" & ROUNDDOWN(MOD((O1926-M1926)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","ABFF DH 136",null,"< >",6509,6510,2026,2026,{"$f":"WEEKNUM(L1927)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N1927)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-06-15","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1927-L1927+ROUNDDOWN(O1927-M1927,0),\"0\")&\" days\"& IF(MOD((O1927-M1927)*24,24)>0,\" + \" & ROUNDDOWN((O1927-M1927)*24,0) & \" h \" & ROUNDDOWN(MOD((O1927-M1927)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","1BFF DH 136",null,"< >",6509,6510,2026,2026,{"$f":"WEEKNUM(L1928)+[7]dates!$L$3-[7]dates!$H$3","v":28},{"$f":"WEEKNUM(N1928)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-07-06","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N1928-L1928+ROUNDDOWN(O1928-M1928,0),\"0\")&\" days\"& IF(MOD((O1928-M1928)*24,24)>0,\" + \" & ROUNDDOWN((O1928-M1928)*24,0) & \" h \" & ROUNDDOWN(MOD((O1928-M1928)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F51171",null,"< >",6533,6538,2026,2026,{"$f":"WEEKNUM(L1929)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1929)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1929-L1929+ROUNDDOWN(O1929-M1929,0),\"0\")&\" days\"& IF(MOD((O1929-M1929)*24,24)>0,\" + \" & ROUNDDOWN((O1929-M1929)*24,0) & \" h \" & ROUNDDOWN(MOD((O1929-M1929)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A51171",null,"< >",6533,6538,2026,2026,{"$f":"WEEKNUM(L1930)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1930)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1930-L1930+ROUNDDOWN(O1930-M1930,0),\"0\")&\" days\"& IF(MOD((O1930-M1930)*24,24)>0,\" + \" & ROUNDDOWN((O1930-M1930)*24,0) & \" h \" & ROUNDDOWN(MOD((O1930-M1930)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B51171",null,"< >",6533,6538,2026,2026,{"$f":"WEEKNUM(L1931)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1931)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-10-05","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1931-L1931+ROUNDDOWN(O1931-M1931,0),\"0\")&\" days\"& IF(MOD((O1931-M1931)*24,24)>0,\" + \" & ROUNDDOWN((O1931-M1931)*24,0) & \" h \" & ROUNDDOWN(MOD((O1931-M1931)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH4252",null,"< >",6545,7434,2026,2026,{"$f":"WEEKNUM(L1932)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1932)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1932-L1932+ROUNDDOWN(O1932-M1932,0),\"0\")&\" days\"& IF(MOD((O1932-M1932)*24,24)>0,\" + \" & ROUNDDOWN((O1932-M1932)*24,0) & \" h \" & ROUNDDOWN(MOD((O1932-M1932)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH4252",null,"< >",6545,7434,2026,2026,{"$f":"WEEKNUM(L1933)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1933)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1933-L1933+ROUNDDOWN(O1933-M1933,0),\"0\")&\" days\"& IF(MOD((O1933-M1933)*24,24)>0,\" + \" & ROUNDDOWN((O1933-M1933)*24,0) & \" h \" & ROUNDDOWN(MOD((O1933-M1933)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","BH4252",null,"< >",6545,7434,2026,2026,{"$f":"WEEKNUM(L1934)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1934)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-10-05","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1934-L1934+ROUNDDOWN(O1934-M1934,0),\"0\")&\" days\"& IF(MOD((O1934-M1934)*24,24)>0,\" + \" & ROUNDDOWN((O1934-M1934)*24,0) & \" h \" & ROUNDDOWN(MOD((O1934-M1934)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","CH4252",null,"< >",6545,6546,2026,2026,{"$f":"WEEKNUM(L1935)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1935)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1935-L1935+ROUNDDOWN(O1935-M1935,0),\"0\")&\" days\"& IF(MOD((O1935-M1935)*24,24)>0,\" + \" & ROUNDDOWN((O1935-M1935)*24,0) & \" h \" & ROUNDDOWN(MOD((O1935-M1935)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","DH4252",null,"< >",6545,6546,2026,2026,{"$f":"WEEKNUM(L1936)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1936)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-04-27","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1936-L1936+ROUNDDOWN(O1936-M1936,0),\"0\")&\" days\"& IF(MOD((O1936-M1936)*24,24)>0,\" + \" & ROUNDDOWN((O1936-M1936)*24,0) & \" h \" & ROUNDDOWN(MOD((O1936-M1936)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62695",null,"< >",6549,6548,2026,2026,{"$f":"WEEKNUM(L1937)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1937)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1937-L1937+ROUNDDOWN(O1937-M1937,0),\"0\")&\" days\"& IF(MOD((O1937-M1937)*24,24)>0,\" + \" & ROUNDDOWN((O1937-M1937)*24,0) & \" h \" & ROUNDDOWN(MOD((O1937-M1937)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F51169",null,"< >",6554,6556,2026,2026,{"$f":"WEEKNUM(L1938)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1938)+[7]dates!$L$3-[7]dates!$H$3","v":8},"2026-01-05","00:00:00","2026-02-15",0.99998842592592585,{"$f":"TEXT(N1938-L1938+ROUNDDOWN(O1938-M1938,0),\"0\")&\" days\"& IF(MOD((O1938-M1938)*24,24)>0,\" + \" & ROUNDDOWN((O1938-M1938)*24,0) & \" h \" & ROUNDDOWN(MOD((O1938-M1938)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A51169",null,"< >",6554,6556,2026,2026,{"$f":"WEEKNUM(L1939)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1939)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-30","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1939-L1939+ROUNDDOWN(O1939-M1939,0),\"0\")&\" days\"& IF(MOD((O1939-M1939)*24,24)>0,\" + \" & ROUNDDOWN((O1939-M1939)*24,0) & \" h \" & ROUNDDOWN(MOD((O1939-M1939)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B51169",null,"< >",6554,6556,2026,2026,{"$f":"WEEKNUM(L1940)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N1940)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-07-20","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N1940-L1940+ROUNDDOWN(O1940-M1940,0),\"0\")&\" days\"& IF(MOD((O1940-M1940)*24,24)>0,\" + \" & ROUNDDOWN((O1940-M1940)*24,0) & \" h \" & ROUNDDOWN(MOD((O1940-M1940)*1440,60),0) & \" min\",\"\")","v":"83 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH4144\n",null,"< >",6581,6581,2026,2026,{"$f":"WEEKNUM(L1941)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1941)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-01-05","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1941-L1941+ROUNDDOWN(O1941-M1941,0),\"0\")&\" days\"& IF(MOD((O1941-M1941)*24,24)>0,\" + \" & ROUNDDOWN((O1941-M1941)*24,0) & \" h \" & ROUNDDOWN(MOD((O1941-M1941)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH4144\n",null,"< >",6581,6581,2026,2026,{"$f":"WEEKNUM(L1942)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1942)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1942-L1942+ROUNDDOWN(O1942-M1942,0),\"0\")&\" days\"& IF(MOD((O1942-M1942)*24,24)>0,\" + \" & ROUNDDOWN((O1942-M1942)*24,0) & \" h \" & ROUNDDOWN(MOD((O1942-M1942)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65629",null,"< >",6605,6605,2026,2026,{"$f":"WEEKNUM(L1943)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1943)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1943-L1943+ROUNDDOWN(O1943-M1943,0),\"0\")&\" days\"& IF(MOD((O1943-M1943)*24,24)>0,\" + \" & ROUNDDOWN((O1943-M1943)*24,0) & \" h \" & ROUNDDOWN(MOD((O1943-M1943)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH3624",null,"< >",6606,6604,2026,2026,{"$f":"WEEKNUM(L1944)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1944)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-01-05","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1944-L1944+ROUNDDOWN(O1944-M1944,0),\"0\")&\" days\"& IF(MOD((O1944-M1944)*24,24)>0,\" + \" & ROUNDDOWN((O1944-M1944)*24,0) & \" h \" & ROUNDDOWN(MOD((O1944-M1944)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH3624",null,"< >",6606,6604,2026,2026,{"$f":"WEEKNUM(L1945)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1945)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1945-L1945+ROUNDDOWN(O1945-M1945,0),\"0\")&\" days\"& IF(MOD((O1945-M1945)*24,24)>0,\" + \" & ROUNDDOWN((O1945-M1945)*24,0) & \" h \" & ROUNDDOWN(MOD((O1945-M1945)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","BH3624",null,"< >",6611,6604,2026,2026,{"$f":"WEEKNUM(L1946)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1946)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-04-27","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1946-L1946+ROUNDDOWN(O1946-M1946,0),\"0\")&\" days\"& IF(MOD((O1946-M1946)*24,24)>0,\" + \" & ROUNDDOWN((O1946-M1946)*24,0) & \" h \" & ROUNDDOWN(MOD((O1946-M1946)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A64154",null,"< >",6615,7548,2026,2026,{"$f":"WEEKNUM(L1947)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1947)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-01-05","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N1947-L1947+ROUNDDOWN(O1947-M1947,0),\"0\")&\" days\"& IF(MOD((O1947-M1947)*24,24)>0,\" + \" & ROUNDDOWN((O1947-M1947)*24,0) & \" h \" & ROUNDDOWN(MOD((O1947-M1947)*1440,60),0) & \" min\",\"\")","v":"125 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F51774/44553",null,"< >",6622,6373,2026,2026,{"$f":"WEEKNUM(L1948)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1948)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1948-L1948+ROUNDDOWN(O1948-M1948,0),\"0\")&\" days\"& IF(MOD((O1948-M1948)*24,24)>0,\" + \" & ROUNDDOWN((O1948-M1948)*24,0) & \" h \" & ROUNDDOWN(MOD((O1948-M1948)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A51774/44553",null,"< >",6622,6373,2026,2026,{"$f":"WEEKNUM(L1949)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1949)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1949-L1949+ROUNDDOWN(O1949-M1949,0),\"0\")&\" days\"& IF(MOD((O1949-M1949)*24,24)>0,\" + \" & ROUNDDOWN((O1949-M1949)*24,0) & \" h \" & ROUNDDOWN(MOD((O1949-M1949)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B51774/44553",null,"< >",6622,6402,2026,2026,{"$f":"WEEKNUM(L1950)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1950)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1950-L1950+ROUNDDOWN(O1950-M1950,0),\"0\")&\" days\"& IF(MOD((O1950-M1950)*24,24)>0,\" + \" & ROUNDDOWN((O1950-M1950)*24,0) & \" h \" & ROUNDDOWN(MOD((O1950-M1950)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C51774/44553",null,"< >",6622,6402,2026,2026,{"$f":"WEEKNUM(L1951)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1951)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1951-L1951+ROUNDDOWN(O1951-M1951,0),\"0\")&\" days\"& IF(MOD((O1951-M1951)*24,24)>0,\" + \" & ROUNDDOWN((O1951-M1951)*24,0) & \" h \" & ROUNDDOWN(MOD((O1951-M1951)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F46605",null,"< >",6625,6627,2026,2026,{"$f":"WEEKNUM(L1952)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1952)+[7]dates!$L$3-[7]dates!$H$3","v":21},"2026-03-09","00:00:00","2026-05-17",0.99998842592592585,{"$f":"TEXT(N1952-L1952+ROUNDDOWN(O1952-M1952,0),\"0\")&\" days\"& IF(MOD((O1952-M1952)*24,24)>0,\" + \" & ROUNDDOWN((O1952-M1952)*24,0) & \" h \" & ROUNDDOWN(MOD((O1952-M1952)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A46605",null,"< >",6625,6627,2026,2026,{"$f":"WEEKNUM(L1953)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1953)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-30","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1953-L1953+ROUNDDOWN(O1953-M1953,0),\"0\")&\" days\"& IF(MOD((O1953-M1953)*24,24)>0,\" + \" & ROUNDDOWN((O1953-M1953)*24,0) & \" h \" & ROUNDDOWN(MOD((O1953-M1953)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63929",null,"< >",6650,6482,2026,2026,{"$f":"WEEKNUM(L1954)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N1954)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-08-31","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1954-L1954+ROUNDDOWN(O1954-M1954,0),\"0\")&\" days\"& IF(MOD((O1954-M1954)*24,24)>0,\" + \" & ROUNDDOWN((O1954-M1954)*24,0) & \" h \" & ROUNDDOWN(MOD((O1954-M1954)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62306",null,"< >",6731,6733,2026,2026,{"$f":"WEEKNUM(L1955)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1955)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-01-26","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1955-L1955+ROUNDDOWN(O1955-M1955,0),\"0\")&\" days\"& IF(MOD((O1955-M1955)*24,24)>0,\" + \" & ROUNDDOWN((O1955-M1955)*24,0) & \" h \" & ROUNDDOWN(MOD((O1955-M1955)*1440,60),0) & \" min\",\"\")","v":"181 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A62306",null,"< >",6731,6733,2026,2026,{"$f":"WEEKNUM(L1956)+[7]dates!$L$3-[7]dates!$H$3","v":32},{"$f":"WEEKNUM(N1956)+[7]dates!$L$3-[7]dates!$H$3","v":39},"2026-08-03","00:00:00","2026-09-20",0.99998842592592585,{"$f":"TEXT(N1956-L1956+ROUNDDOWN(O1956-M1956,0),\"0\")&\" days\"& IF(MOD((O1956-M1956)*24,24)>0,\" + \" & ROUNDDOWN((O1956-M1956)*24,0) & \" h \" & ROUNDDOWN(MOD((O1956-M1956)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B62306",null,"< >",6732,6733,2026,2026,{"$f":"WEEKNUM(L1957)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1957)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-05-18","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N1957-L1957+ROUNDDOWN(O1957-M1957,0),\"0\")&\" days\"& IF(MOD((O1957-M1957)*24,24)>0,\" + \" & ROUNDDOWN((O1957-M1957)*24,0) & \" h \" & ROUNDDOWN(MOD((O1957-M1957)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62295",null,"< >",6733,565,2026,2026,{"$f":"WEEKNUM(L1958)+[7]dates!$L$3-[7]dates!$H$3","v":40},{"$f":"WEEKNUM(N1958)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-28","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N1958-L1958+ROUNDDOWN(O1958-M1958,0),\"0\")&\" days\"& IF(MOD((O1958-M1958)*24,24)>0,\" + \" & ROUNDDOWN((O1958-M1958)*24,0) & \" h \" & ROUNDDOWN(MOD((O1958-M1958)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A62659",null,"< >",6827,6830,2026,2026,{"$f":"WEEKNUM(L1959)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1959)+[7]dates!$L$3-[7]dates!$H$3","v":13},"2026-02-09","00:00:00","2026-03-22",0.99998842592592585,{"$f":"TEXT(N1959-L1959+ROUNDDOWN(O1959-M1959,0),\"0\")&\" days\"& IF(MOD((O1959-M1959)*24,24)>0,\" + \" & ROUNDDOWN((O1959-M1959)*24,0) & \" h \" & ROUNDDOWN(MOD((O1959-M1959)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B62659",null,"< >",6827,6830,2026,2026,{"$f":"WEEKNUM(L1960)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1960)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-30","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1960-L1960+ROUNDDOWN(O1960-M1960,0),\"0\")&\" days\"& IF(MOD((O1960-M1960)*24,24)>0,\" + \" & ROUNDDOWN((O1960-M1960)*24,0) & \" h \" & ROUNDDOWN(MOD((O1960-M1960)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64470",null,"< >",6833,6833,2026,2026,{"$f":"WEEKNUM(L1961)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N1961)+[7]dates!$L$3-[7]dates!$H$3","v":48},"2026-10-05","00:00:00","2026-11-22",0.99998842592592585,{"$f":"TEXT(N1961-L1961+ROUNDDOWN(O1961-M1961,0),\"0\")&\" days\"& IF(MOD((O1961-M1961)*24,24)>0,\" + \" & ROUNDDOWN((O1961-M1961)*24,0) & \" h \" & ROUNDDOWN(MOD((O1961-M1961)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A64470",null,"< >",6833,6833,2026,2026,{"$f":"WEEKNUM(L1962)+[7]dates!$L$3-[7]dates!$H$3","v":43},{"$f":"WEEKNUM(N1962)+[7]dates!$L$3-[7]dates!$H$3","v":45},"2026-10-19","00:00:00","2026-11-01",0.99998842592592585,{"$f":"TEXT(N1962-L1962+ROUNDDOWN(O1962-M1962,0),\"0\")&\" days\"& IF(MOD((O1962-M1962)*24,24)>0,\" + \" & ROUNDDOWN((O1962-M1962)*24,0) & \" h \" & ROUNDDOWN(MOD((O1962-M1962)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60164",null,"< >",6834,6839,2026,2026,{"$f":"WEEKNUM(L1963)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1963)+[7]dates!$L$3-[7]dates!$H$3","v":37},"2026-04-27","00:00:00","2026-09-06",0.99998842592592585,{"$f":"TEXT(N1963-L1963+ROUNDDOWN(O1963-M1963,0),\"0\")&\" days\"& IF(MOD((O1963-M1963)*24,24)>0,\" + \" & ROUNDDOWN((O1963-M1963)*24,0) & \" h \" & ROUNDDOWN(MOD((O1963-M1963)*1440,60),0) & \" min\",\"\")","v":"132 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A60164",null,"< >",6834,53,2026,2026,{"$f":"WEEKNUM(L1964)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1964)+[7]dates!$L$3-[7]dates!$H$3","v":34},"2026-04-27","00:00:00","2026-08-16",0.99998842592592585,{"$f":"TEXT(N1964-L1964+ROUNDDOWN(O1964-M1964,0),\"0\")&\" days\"& IF(MOD((O1964-M1964)*24,24)>0,\" + \" & ROUNDDOWN((O1964-M1964)*24,0) & \" h \" & ROUNDDOWN(MOD((O1964-M1964)*1440,60),0) & \" min\",\"\")","v":"111 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64903",null,"< >",6843,6849,2026,2026,{"$f":"WEEKNUM(L1965)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N1965)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-02-02","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1965-L1965+ROUNDDOWN(O1965-M1965,0),\"0\")&\" days\"& IF(MOD((O1965-M1965)*24,24)>0,\" + \" & ROUNDDOWN((O1965-M1965)*24,0) & \" h \" & ROUNDDOWN(MOD((O1965-M1965)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A64903",null,"< >",6843,6849,2026,2026,{"$f":"WEEKNUM(L1966)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N1966)+[7]dates!$L$3-[7]dates!$H$3","v":16},"2026-02-16","00:00:00","2026-04-12",0.99998842592592585,{"$f":"TEXT(N1966-L1966+ROUNDDOWN(O1966-M1966,0),\"0\")&\" days\"& IF(MOD((O1966-M1966)*24,24)>0,\" + \" & ROUNDDOWN((O1966-M1966)*24,0) & \" h \" & ROUNDDOWN(MOD((O1966-M1966)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62897",null,"< >",6848,6897,2026,2026,{"$f":"WEEKNUM(L1967)+[7]dates!$L$3-[7]dates!$H$3","v":27},{"$f":"WEEKNUM(N1967)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-06-29","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N1967-L1967+ROUNDDOWN(O1967-M1967,0),\"0\")&\" days\"& IF(MOD((O1967-M1967)*24,24)>0,\" + \" & ROUNDDOWN((O1967-M1967)*24,0) & \" h \" & ROUNDDOWN(MOD((O1967-M1967)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A62897",null,"< >",6848,6897,2026,2026,{"$f":"WEEKNUM(L1968)+[7]dates!$L$3-[7]dates!$H$3","v":31},{"$f":"WEEKNUM(N1968)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-07-27","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N1968-L1968+ROUNDDOWN(O1968-M1968,0),\"0\")&\" days\"& IF(MOD((O1968-M1968)*24,24)>0,\" + \" & ROUNDDOWN((O1968-M1968)*24,0) & \" h \" & ROUNDDOWN(MOD((O1968-M1968)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F46690",null,"< >",6897,6900,2026,2026,{"$f":"WEEKNUM(L1969)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1969)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-05-11","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N1969-L1969+ROUNDDOWN(O1969-M1969,0),\"0\")&\" days\"& IF(MOD((O1969-M1969)*24,24)>0,\" + \" & ROUNDDOWN((O1969-M1969)*24,0) & \" h \" & ROUNDDOWN(MOD((O1969-M1969)*1440,60),0) & \" min\",\"\")","v":"83 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A46690",null,"< >",6897,6900,2026,2026,{"$f":"WEEKNUM(L1970)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N1970)+[7]dates!$L$3-[7]dates!$H$3","v":37},"2026-08-10","00:00:00","2026-09-06",0.99998842592592585,{"$f":"TEXT(N1970-L1970+ROUNDDOWN(O1970-M1970,0),\"0\")&\" days\"& IF(MOD((O1970-M1970)*24,24)>0,\" + \" & ROUNDDOWN((O1970-M1970)*24,0) & \" h \" & ROUNDDOWN(MOD((O1970-M1970)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F47327",null,"< >",6897,6896,2026,2026,{"$f":"WEEKNUM(L1971)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1971)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-04-20","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1971-L1971+ROUNDDOWN(O1971-M1971,0),\"0\")&\" days\"& IF(MOD((O1971-M1971)*24,24)>0,\" + \" & ROUNDDOWN((O1971-M1971)*24,0) & \" h \" & ROUNDDOWN(MOD((O1971-M1971)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F56553",null,"< >",6914,8416,2026,2026,{"$f":"WEEKNUM(L1972)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N1972)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-30","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1972-L1972+ROUNDDOWN(O1972-M1972,0),\"0\")&\" days\"& IF(MOD((O1972-M1972)*24,24)>0,\" + \" & ROUNDDOWN((O1972-M1972)*24,0) & \" h \" & ROUNDDOWN(MOD((O1972-M1972)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A56553",null,"< >",6914,8416,2026,2026,{"$f":"WEEKNUM(L1973)+[7]dates!$L$3-[7]dates!$H$3","v":16},{"$f":"WEEKNUM(N1973)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-04-13","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N1973-L1973+ROUNDDOWN(O1973-M1973,0),\"0\")&\" days\"& IF(MOD((O1973-M1973)*24,24)>0,\" + \" & ROUNDDOWN((O1973-M1973)*24,0) & \" h \" & ROUNDDOWN(MOD((O1973-M1973)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH4006",null,"< >",6962,8421,2026,2026,{"$f":"WEEKNUM(L1974)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N1974)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-19","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N1974-L1974+ROUNDDOWN(O1974-M1974,0),\"0\")&\" days\"& IF(MOD((O1974-M1974)*24,24)>0,\" + \" & ROUNDDOWN((O1974-M1974)*24,0) & \" h \" & ROUNDDOWN(MOD((O1974-M1974)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH4006",null,"< >",6962,8421,2026,2026,{"$f":"WEEKNUM(L1975)+[7]dates!$L$3-[7]dates!$H$3","v":11},{"$f":"WEEKNUM(N1975)+[7]dates!$L$3-[7]dates!$H$3","v":14},"2026-03-09","00:00:00","2026-03-29",0.99998842592592585,{"$f":"TEXT(N1975-L1975+ROUNDDOWN(O1975-M1975,0),\"0\")&\" days\"& IF(MOD((O1975-M1975)*24,24)>0,\" + \" & ROUNDDOWN((O1975-M1975)*24,0) & \" h \" & ROUNDDOWN(MOD((O1975-M1975)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","BH4006",null,"< >",6962,8421,2026,2026,{"$f":"WEEKNUM(L1976)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N1976)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-05-04","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N1976-L1976+ROUNDDOWN(O1976-M1976,0),\"0\")&\" days\"& IF(MOD((O1976-M1976)*24,24)>0,\" + \" & ROUNDDOWN((O1976-M1976)*24,0) & \" h \" & ROUNDDOWN(MOD((O1976-M1976)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","CH4006",null,"< >",6962,8421,2026,2026,{"$f":"WEEKNUM(L1977)+[7]dates!$L$3-[7]dates!$H$3","v":27},{"$f":"WEEKNUM(N1977)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-06-29","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N1977-L1977+ROUNDDOWN(O1977-M1977,0),\"0\")&\" days\"& IF(MOD((O1977-M1977)*24,24)>0,\" + \" & ROUNDDOWN((O1977-M1977)*24,0) & \" h \" & ROUNDDOWN(MOD((O1977-M1977)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62659",null,"< >",6990,6827,2026,2026,{"$f":"WEEKNUM(L1978)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1978)+[7]dates!$L$3-[7]dates!$H$3","v":23},"2026-01-05","00:00:00","2026-05-31",0.99998842592592585,{"$f":"TEXT(N1978-L1978+ROUNDDOWN(O1978-M1978,0),\"0\")&\" days\"& IF(MOD((O1978-M1978)*24,24)>0,\" + \" & ROUNDDOWN((O1978-M1978)*24,0) & \" h \" & ROUNDDOWN(MOD((O1978-M1978)*1440,60),0) & \" min\",\"\")","v":"146 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","AH3775",null,"< >",7096,7098,2026,2026,{"$f":"WEEKNUM(L1979)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1979)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1979-L1979+ROUNDDOWN(O1979-M1979,0),\"0\")&\" days\"& IF(MOD((O1979-M1979)*24,24)>0,\" + \" & ROUNDDOWN((O1979-M1979)*24,0) & \" h \" & ROUNDDOWN(MOD((O1979-M1979)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH3775",null,"< >",7097,7097,2026,2026,{"$f":"WEEKNUM(L1980)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N1980)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N1980-L1980+ROUNDDOWN(O1980-M1980,0),\"0\")&\" days\"& IF(MOD((O1980-M1980)*24,24)>0,\" + \" & ROUNDDOWN((O1980-M1980)*24,0) & \" h \" & ROUNDDOWN(MOD((O1980-M1980)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","BH3775",null,"< >",7097,7097,2026,2026,{"$f":"WEEKNUM(L1981)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N1981)+[7]dates!$L$3-[7]dates!$H$3","v":31},"2026-04-27","00:00:00","2026-07-26",0.99998842592592585,{"$f":"TEXT(N1981-L1981+ROUNDDOWN(O1981-M1981,0),\"0\")&\" days\"& IF(MOD((O1981-M1981)*24,24)>0,\" + \" & ROUNDDOWN((O1981-M1981)*24,0) & \" h \" & ROUNDDOWN(MOD((O1981-M1981)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F42032",null,"< >",7169,7170,2026,2026,{"$f":"WEEKNUM(L1982)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1982)+[7]dates!$L$3-[7]dates!$H$3","v":26},"2026-01-05","00:00:00","2026-06-21",0.99998842592592585,{"$f":"TEXT(N1982-L1982+ROUNDDOWN(O1982-M1982,0),\"0\")&\" days\"& IF(MOD((O1982-M1982)*24,24)>0,\" + \" & ROUNDDOWN((O1982-M1982)*24,0) & \" h \" & ROUNDDOWN(MOD((O1982-M1982)*1440,60),0) & \" min\",\"\")","v":"167 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH4332",null,"< >",7174,7171,2026,2026,{"$f":"WEEKNUM(L1983)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1983)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-01-05","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N1983-L1983+ROUNDDOWN(O1983-M1983,0),\"0\")&\" days\"& IF(MOD((O1983-M1983)*24,24)>0,\" + \" & ROUNDDOWN((O1983-M1983)*24,0) & \" h \" & ROUNDDOWN(MOD((O1983-M1983)*1440,60),0) & \" min\",\"\")","v":"335 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F56066",null,"< >",7349,7349,2026,2026,{"$f":"WEEKNUM(L1984)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1984)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-03-16","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1984-L1984+ROUNDDOWN(O1984-M1984,0),\"0\")&\" days\"& IF(MOD((O1984-M1984)*24,24)>0,\" + \" & ROUNDDOWN((O1984-M1984)*24,0) & \" h \" & ROUNDDOWN(MOD((O1984-M1984)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60254",null,"< >",7351,7355,2026,2026,{"$f":"WEEKNUM(L1985)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1985)+[7]dates!$L$3-[7]dates!$H$3","v":23},"2026-01-05","00:00:00","2026-05-31",0.99998842592592585,{"$f":"TEXT(N1985-L1985+ROUNDDOWN(O1985-M1985,0),\"0\")&\" days\"& IF(MOD((O1985-M1985)*24,24)>0,\" + \" & ROUNDDOWN((O1985-M1985)*24,0) & \" h \" & ROUNDDOWN(MOD((O1985-M1985)*1440,60),0) & \" min\",\"\")","v":"146 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62665",null,"< >",7381,7389,2026,2026,{"$f":"WEEKNUM(L1986)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1986)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-01-05","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N1986-L1986+ROUNDDOWN(O1986-M1986,0),\"0\")&\" days\"& IF(MOD((O1986-M1986)*24,24)>0,\" + \" & ROUNDDOWN((O1986-M1986)*24,0) & \" h \" & ROUNDDOWN(MOD((O1986-M1986)*1440,60),0) & \" min\",\"\")","v":"174 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64245",null,"< >",7410,8923,2026,2026,{"$f":"WEEKNUM(L1987)+[7]dates!$L$3-[7]dates!$H$3","v":44},{"$f":"WEEKNUM(N1987)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-10-26","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1987-L1987+ROUNDDOWN(O1987-M1987,0),\"0\")&\" days\"& IF(MOD((O1987-M1987)*24,24)>0,\" + \" & ROUNDDOWN((O1987-M1987)*24,0) & \" h \" & ROUNDDOWN(MOD((O1987-M1987)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64244",null,"< >",7429,7442,2026,2026,{"$f":"WEEKNUM(L1988)+[7]dates!$L$3-[7]dates!$H$3","v":44},{"$f":"WEEKNUM(N1988)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-10-26","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N1988-L1988+ROUNDDOWN(O1988-M1988,0),\"0\")&\" days\"& IF(MOD((O1988-M1988)*24,24)>0,\" + \" & ROUNDDOWN((O1988-M1988)*24,0) & \" h \" & ROUNDDOWN(MOD((O1988-M1988)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63127",null,"< >",7445,7581,2026,2026,{"$f":"WEEKNUM(L1989)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N1989)+[7]dates!$L$3-[7]dates!$H$3","v":34},"2026-06-08","00:00:00","2026-08-16",0.99998842592592585,{"$f":"TEXT(N1989-L1989+ROUNDDOWN(O1989-M1989,0),\"0\")&\" days\"& IF(MOD((O1989-M1989)*24,24)>0,\" + \" & ROUNDDOWN((O1989-M1989)*24,0) & \" h \" & ROUNDDOWN(MOD((O1989-M1989)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A63127",null,"< >",7445,7581,2026,2026,{"$f":"WEEKNUM(L1990)+[7]dates!$L$3-[7]dates!$H$3","v":29},{"$f":"WEEKNUM(N1990)+[7]dates!$L$3-[7]dates!$H$3","v":34},"2026-07-13","00:00:00","2026-08-16",0.99998842592592585,{"$f":"TEXT(N1990-L1990+ROUNDDOWN(O1990-M1990,0),\"0\")&\" days\"& IF(MOD((O1990-M1990)*24,24)>0,\" + \" & ROUNDDOWN((O1990-M1990)*24,0) & \" h \" & ROUNDDOWN(MOD((O1990-M1990)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F60425",null,"< >",7445,7582,2026,2026,{"$f":"WEEKNUM(L1991)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N1991)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-04-20","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1991-L1991+ROUNDDOWN(O1991-M1991,0),\"0\")&\" days\"& IF(MOD((O1991-M1991)*24,24)>0,\" + \" & ROUNDDOWN((O1991-M1991)*24,0) & \" h \" & ROUNDDOWN(MOD((O1991-M1991)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A60425",null,"< >",7445,7582,2026,2026,{"$f":"WEEKNUM(L1992)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1992)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-05-11","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1992-L1992+ROUNDDOWN(O1992-M1992,0),\"0\")&\" days\"& IF(MOD((O1992-M1992)*24,24)>0,\" + \" & ROUNDDOWN((O1992-M1992)*24,0) & \" h \" & ROUNDDOWN(MOD((O1992-M1992)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B60425",null,"< >",7445,7582,2026,2026,{"$f":"WEEKNUM(L1993)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N1993)+[7]dates!$L$3-[7]dates!$H$3","v":23},"2026-05-11","00:00:00","2026-05-31",0.99998842592592585,{"$f":"TEXT(N1993-L1993+ROUNDDOWN(O1993-M1993,0),\"0\")&\" days\"& IF(MOD((O1993-M1993)*24,24)>0,\" + \" & ROUNDDOWN((O1993-M1993)*24,0) & \" h \" & ROUNDDOWN(MOD((O1993-M1993)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64883",null,"< >",7450,7594,2026,2026,{"$f":"WEEKNUM(L1994)+[7]dates!$L$3-[7]dates!$H$3","v":5},{"$f":"WEEKNUM(N1994)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-01-26","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N1994-L1994+ROUNDDOWN(O1994-M1994,0),\"0\")&\" days\"& IF(MOD((O1994-M1994)*24,24)>0,\" + \" & ROUNDDOWN((O1994-M1994)*24,0) & \" h \" & ROUNDDOWN(MOD((O1994-M1994)*1440,60),0) & \" min\",\"\")","v":"132 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F47283",null,"< >",7456,7457,2026,2026,{"$f":"WEEKNUM(L1995)+[7]dates!$L$3-[7]dates!$H$3","v":15},{"$f":"WEEKNUM(N1995)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-04-06","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1995-L1995+ROUNDDOWN(O1995-M1995,0),\"0\")&\" days\"& IF(MOD((O1995-M1995)*24,24)>0,\" + \" & ROUNDDOWN((O1995-M1995)*24,0) & \" h \" & ROUNDDOWN(MOD((O1995-M1995)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A47283",null,"< >",7456,7457,2026,2026,{"$f":"WEEKNUM(L1996)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N1996)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-05-18","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N1996-L1996+ROUNDDOWN(O1996-M1996,0),\"0\")&\" days\"& IF(MOD((O1996-M1996)*24,24)>0,\" + \" & ROUNDDOWN((O1996-M1996)*24,0) & \" h \" & ROUNDDOWN(MOD((O1996-M1996)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JJ3475",null,"< >",7461,7682,2026,2026,{"$f":"WEEKNUM(L1997)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1997)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-03-16","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N1997-L1997+ROUNDDOWN(O1997-M1997,0),\"0\")&\" days\"& IF(MOD((O1997-M1997)*24,24)>0,\" + \" & ROUNDDOWN((O1997-M1997)*24,0) & \" h \" & ROUNDDOWN(MOD((O1997-M1997)*1440,60),0) & \" min\",\"\")","v":"160 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62136",null,"< >",7461,7682,2026,2026,{"$f":"WEEKNUM(L1998)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N1998)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-03-16","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N1998-L1998+ROUNDDOWN(O1998-M1998,0),\"0\")&\" days\"& IF(MOD((O1998-M1998)*24,24)>0,\" + \" & ROUNDDOWN((O1998-M1998)*24,0) & \" h \" & ROUNDDOWN(MOD((O1998-M1998)*1440,60),0) & \" min\",\"\")","v":"160 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F50753",null,"< >",7469,7130,2026,2026,{"$f":"WEEKNUM(L1999)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N1999)+[7]dates!$L$3-[7]dates!$H$3","v":12},"2026-01-05","00:00:00","2026-03-15",0.99998842592592585,{"$f":"TEXT(N1999-L1999+ROUNDDOWN(O1999-M1999,0),\"0\")&\" days\"& IF(MOD((O1999-M1999)*24,24)>0,\" + \" & ROUNDDOWN((O1999-M1999)*24,0) & \" h \" & ROUNDDOWN(MOD((O1999-M1999)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F61954",null,"< >",7554,7560,2026,2026,{"$f":"WEEKNUM(L2000)+[7]dates!$L$3-[7]dates!$H$3","v":19},{"$f":"WEEKNUM(N2000)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-05-04","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N2000-L2000+ROUNDDOWN(O2000-M2000,0),\"0\")&\" days\"& IF(MOD((O2000-M2000)*24,24)>0,\" + \" & ROUNDDOWN((O2000-M2000)*24,0) & \" h \" & ROUNDDOWN(MOD((O2000-M2000)*1440,60),0) & \" min\",\"\")","v":"69 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64521",null,"< >",7593,7594,2026,2026,{"$f":"WEEKNUM(L2001)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N2001)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-02-02","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N2001-L2001+ROUNDDOWN(O2001-M2001,0),\"0\")&\" days\"& IF(MOD((O2001-M2001)*24,24)>0,\" + \" & ROUNDDOWN((O2001-M2001)*24,0) & \" h \" & ROUNDDOWN(MOD((O2001-M2001)*1440,60),0) & \" min\",\"\")","v":"97 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A64521",null,"< >",7595,328,2026,2026,{"$f":"WEEKNUM(L2002)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N2002)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-03-23","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N2002-L2002+ROUNDDOWN(O2002-M2002,0),\"0\")&\" days\"& IF(MOD((O2002-M2002)*24,24)>0,\" + \" & ROUNDDOWN((O2002-M2002)*24,0) & \" h \" & ROUNDDOWN(MOD((O2002-M2002)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F56067",null,"< >",7599,7682,2026,2026,{"$f":"WEEKNUM(L2003)+[7]dates!$L$3-[7]dates!$H$3","v":21},{"$f":"WEEKNUM(N2003)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-05-18","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N2003-L2003+ROUNDDOWN(O2003-M2003,0),\"0\")&\" days\"& IF(MOD((O2003-M2003)*24,24)>0,\" + \" & ROUNDDOWN((O2003-M2003)*24,0) & \" h \" & ROUNDDOWN(MOD((O2003-M2003)*1440,60),0) & \" min\",\"\")","v":"97 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65278",null,"< >",7632,7610,2026,2026,{"$f":"WEEKNUM(L2004)+[7]dates!$L$3-[7]dates!$H$3","v":17},{"$f":"WEEKNUM(N2004)+[7]dates!$L$3-[7]dates!$H$3","v":25},"2026-04-20","00:00:00","2026-06-14",0.99998842592592585,{"$f":"TEXT(N2004-L2004+ROUNDDOWN(O2004-M2004,0),\"0\")&\" days\"& IF(MOD((O2004-M2004)*24,24)>0,\" + \" & ROUNDDOWN((O2004-M2004)*24,0) & \" h \" & ROUNDDOWN(MOD((O2004-M2004)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58305",null,"< >",7682,7682,2026,2026,{"$f":"WEEKNUM(L2005)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N2005)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-03-16","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N2005-L2005+ROUNDDOWN(O2005-M2005,0),\"0\")&\" days\"& IF(MOD((O2005-M2005)*24,24)>0,\" + \" & ROUNDDOWN((O2005-M2005)*24,0) & \" h \" & ROUNDDOWN(MOD((O2005-M2005)*1440,60),0) & \" min\",\"\")","v":"160 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B30944",null,"< >",7809,7824,2026,2026,{"$f":"WEEKNUM(L2006)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N2006)+[7]dates!$L$3-[7]dates!$H$3","v":23},"2026-01-19","00:00:00","2026-05-31",0.99998842592592585,{"$f":"TEXT(N2006-L2006+ROUNDDOWN(O2006-M2006,0),\"0\")&\" days\"& IF(MOD((O2006-M2006)*24,24)>0,\" + \" & ROUNDDOWN((O2006-M2006)*24,0) & \" h \" & ROUNDDOWN(MOD((O2006-M2006)*1440,60),0) & \" min\",\"\")","v":"132 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C30944",null,"< >",7809,7824,2026,2026,{"$f":"WEEKNUM(L2007)+[7]dates!$L$3-[7]dates!$H$3","v":22},{"$f":"WEEKNUM(N2007)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-05-25","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N2007-L2007+ROUNDDOWN(O2007-M2007,0),\"0\")&\" days\"& IF(MOD((O2007-M2007)*24,24)>0,\" + \" & ROUNDDOWN((O2007-M2007)*24,0) & \" h \" & ROUNDDOWN(MOD((O2007-M2007)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F30944",null,"< >",7817,7821,2026,2026,{"$f":"WEEKNUM(L2008)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N2008)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-01-19","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N2008-L2008+ROUNDDOWN(O2008-M2008,0),\"0\")&\" days\"& IF(MOD((O2008-M2008)*24,24)>0,\" + \" & ROUNDDOWN((O2008-M2008)*24,0) & \" h \" & ROUNDDOWN(MOD((O2008-M2008)*1440,60),0) & \" min\",\"\")","v":"139 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A30944",null,"< >",7817,7821,2026,2026,{"$f":"WEEKNUM(L2009)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N2009)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-08","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N2009-L2009+ROUNDDOWN(O2009-M2009,0),\"0\")&\" days\"& IF(MOD((O2009-M2009)*24,24)>0,\" + \" & ROUNDDOWN((O2009-M2009)*24,0) & \" h \" & ROUNDDOWN(MOD((O2009-M2009)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A47730",null,"< >",7820,7824,2026,2026,{"$f":"WEEKNUM(L2010)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N2010)+[7]dates!$L$3-[7]dates!$H$3","v":38},"2026-08-31","00:00:00","2026-09-13",0.99998842592592585,{"$f":"TEXT(N2010-L2010+ROUNDDOWN(O2010-M2010,0),\"0\")&\" days\"& IF(MOD((O2010-M2010)*24,24)>0,\" + \" & ROUNDDOWN((O2010-M2010)*24,0) & \" h \" & ROUNDDOWN(MOD((O2010-M2010)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F47730",null,"< >",7821,7824,2026,2026,{"$f":"WEEKNUM(L2011)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N2011)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-01","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N2011-L2011+ROUNDDOWN(O2011-M2011,0),\"0\")&\" days\"& IF(MOD((O2011-M2011)*24,24)>0,\" + \" & ROUNDDOWN((O2011-M2011)*24,0) & \" h \" & ROUNDDOWN(MOD((O2011-M2011)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F40041",null,"< >",7829,7807,2026,2026,{"$f":"WEEKNUM(L2012)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N2012)+[7]dates!$L$3-[7]dates!$H$3","v":20},"2026-02-09","00:00:00","2026-05-10",0.99998842592592585,{"$f":"TEXT(N2012-L2012+ROUNDDOWN(O2012-M2012,0),\"0\")&\" days\"& IF(MOD((O2012-M2012)*24,24)>0,\" + \" & ROUNDDOWN((O2012-M2012)*24,0) & \" h \" & ROUNDDOWN(MOD((O2012-M2012)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A40041",null,"< >",7829,7807,2026,2026,{"$f":"WEEKNUM(L2013)+[7]dates!$L$3-[7]dates!$H$3","v":35},{"$f":"WEEKNUM(N2013)+[7]dates!$L$3-[7]dates!$H$3","v":49},"2026-08-24","00:00:00","2026-11-29",0.99998842592592585,{"$f":"TEXT(N2013-L2013+ROUNDDOWN(O2013-M2013,0),\"0\")&\" days\"& IF(MOD((O2013-M2013)*24,24)>0,\" + \" & ROUNDDOWN((O2013-M2013)*24,0) & \" h \" & ROUNDDOWN(MOD((O2013-M2013)*1440,60),0) & \" min\",\"\")","v":"97 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","JH4121",null,"< >",7831,7832,2026,2026,{"$f":"WEEKNUM(L2014)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N2014)+[7]dates!$L$3-[7]dates!$H$3","v":33},"2026-01-05","00:00:00","2026-08-09",0.99998842592592585,{"$f":"TEXT(N2014-L2014+ROUNDDOWN(O2014-M2014,0),\"0\")&\" days\"& IF(MOD((O2014-M2014)*24,24)>0,\" + \" & ROUNDDOWN((O2014-M2014)*24,0) & \" h \" & ROUNDDOWN(MOD((O2014-M2014)*1440,60),0) & \" min\",\"\")","v":"216 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F49227",null,"< >",7997,140,2026,2026,{"$f":"WEEKNUM(L2015)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N2015)+[7]dates!$L$3-[7]dates!$H$3","v":26},"2026-02-16","00:00:00","2026-06-21",0.99998842592592585,{"$f":"TEXT(N2015-L2015+ROUNDDOWN(O2015-M2015,0),\"0\")&\" days\"& IF(MOD((O2015-M2015)*24,24)>0,\" + \" & ROUNDDOWN((O2015-M2015)*24,0) & \" h \" & ROUNDDOWN(MOD((O2015-M2015)*1440,60),0) & \" min\",\"\")","v":"125 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A49227",null,"< >",7997,140,2026,2026,{"$f":"WEEKNUM(L2016)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N2016)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-06-22","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N2016-L2016+ROUNDDOWN(O2016-M2016,0),\"0\")&\" days\"& IF(MOD((O2016-M2016)*24,24)>0,\" + \" & ROUNDDOWN((O2016-M2016)*24,0) & \" h \" & ROUNDDOWN(MOD((O2016-M2016)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B49227",null,"< >",7997,140,2026,2026,{"$f":"WEEKNUM(L2017)+[7]dates!$L$3-[7]dates!$H$3","v":32},{"$f":"WEEKNUM(N2017)+[7]dates!$L$3-[7]dates!$H$3","v":38},"2026-08-03","00:00:00","2026-09-13",0.99998842592592585,{"$f":"TEXT(N2017-L2017+ROUNDDOWN(O2017-M2017,0),\"0\")&\" days\"& IF(MOD((O2017-M2017)*24,24)>0,\" + \" & ROUNDDOWN((O2017-M2017)*24,0) & \" h \" & ROUNDDOWN(MOD((O2017-M2017)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F59105",null,"< >",8002,207,2026,2026,{"$f":"WEEKNUM(L2018)+[7]dates!$L$3-[7]dates!$H$3","v":24},{"$f":"WEEKNUM(N2018)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-06-08","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N2018-L2018+ROUNDDOWN(O2018-M2018,0),\"0\")&\" days\"& IF(MOD((O2018-M2018)*24,24)>0,\" + \" & ROUNDDOWN((O2018-M2018)*24,0) & \" h \" & ROUNDDOWN(MOD((O2018-M2018)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A59105",null,"< >",8002,207,2026,2026,{"$f":"WEEKNUM(L2019)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N2019)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-15","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N2019-L2019+ROUNDDOWN(O2019-M2019,0),\"0\")&\" days\"& IF(MOD((O2019-M2019)*24,24)>0,\" + \" & ROUNDDOWN((O2019-M2019)*24,0) & \" h \" & ROUNDDOWN(MOD((O2019-M2019)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F48763",null,"< >",8088,8690,2026,2026,{"$f":"WEEKNUM(L2020)+[7]dates!$L$3-[7]dates!$H$3","v":29},{"$f":"WEEKNUM(N2020)+[7]dates!$L$3-[7]dates!$H$3","v":35},"2026-07-13","00:00:00","2026-08-23",0.99998842592592585,{"$f":"TEXT(N2020-L2020+ROUNDDOWN(O2020-M2020,0),\"0\")&\" days\"& IF(MOD((O2020-M2020)*24,24)>0,\" + \" & ROUNDDOWN((O2020-M2020)*24,0) & \" h \" & ROUNDDOWN(MOD((O2020-M2020)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F47800",null,"< >",8091,83,2026,2026,{"$f":"WEEKNUM(L2021)+[7]dates!$L$3-[7]dates!$H$3","v":16},{"$f":"WEEKNUM(N2021)+[7]dates!$L$3-[7]dates!$H$3","v":34},"2026-04-13","00:00:00","2026-08-16",0.99998842592592585,{"$f":"TEXT(N2021-L2021+ROUNDDOWN(O2021-M2021,0),\"0\")&\" days\"& IF(MOD((O2021-M2021)*24,24)>0,\" + \" & ROUNDDOWN((O2021-M2021)*24,0) & \" h \" & ROUNDDOWN(MOD((O2021-M2021)*1440,60),0) & \" min\",\"\")","v":"125 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58959",null,"< >",8093,1498,2026,2026,{"$f":"WEEKNUM(L2022)+[7]dates!$L$3-[7]dates!$H$3","v":39},{"$f":"WEEKNUM(N2022)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-09-21","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N2022-L2022+ROUNDDOWN(O2022-M2022,0),\"0\")&\" days\"& IF(MOD((O2022-M2022)*24,24)>0,\" + \" & ROUNDDOWN((O2022-M2022)*24,0) & \" h \" & ROUNDDOWN(MOD((O2022-M2022)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F66373",null,"< >",8117,8119,2026,2026,{"$f":"WEEKNUM(L2023)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N2023)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-06-22","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N2023-L2023+ROUNDDOWN(O2023-M2023,0),\"0\")&\" days\"& IF(MOD((O2023-M2023)*24,24)>0,\" + \" & ROUNDDOWN((O2023-M2023)*24,0) & \" h \" & ROUNDDOWN(MOD((O2023-M2023)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A66373",null,"< >",8117,8119,2026,2026,{"$f":"WEEKNUM(L2024)+[7]dates!$L$3-[7]dates!$H$3","v":26},{"$f":"WEEKNUM(N2024)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-06-22","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N2024-L2024+ROUNDDOWN(O2024-M2024,0),\"0\")&\" days\"& IF(MOD((O2024-M2024)*24,24)>0,\" + \" & ROUNDDOWN((O2024-M2024)*24,0) & \" h \" & ROUNDDOWN(MOD((O2024-M2024)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F42006",null,"< >",8123,8123,2026,2026,{"$f":"WEEKNUM(L2025)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N2025)+[7]dates!$L$3-[7]dates!$H$3","v":27},"2026-03-16","00:00:00","2026-06-28",0.99998842592592585,{"$f":"TEXT(N2025-L2025+ROUNDDOWN(O2025-M2025,0),\"0\")&\" days\"& IF(MOD((O2025-M2025)*24,24)>0,\" + \" & ROUNDDOWN((O2025-M2025)*24,0) & \" h \" & ROUNDDOWN(MOD((O2025-M2025)*1440,60),0) & \" min\",\"\")","v":"104 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F50662?",null,"< >",8140,2066,2026,2026,{"$f":"WEEKNUM(L2026)+[7]dates!$L$3-[7]dates!$H$3","v":20},{"$f":"WEEKNUM(N2026)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-05-11","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N2026-L2026+ROUNDDOWN(O2026-M2026,0),\"0\")&\" days\"& IF(MOD((O2026-M2026)*24,24)>0,\" + \" & ROUNDDOWN((O2026-M2026)*24,0) & \" h \" & ROUNDDOWN(MOD((O2026-M2026)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A50662?",null,"< >",8140,2066,2026,2026,{"$f":"WEEKNUM(L2027)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N2027)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-07-20","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N2027-L2027+ROUNDDOWN(O2027-M2027,0),\"0\")&\" days\"& IF(MOD((O2027-M2027)*24,24)>0,\" + \" & ROUNDDOWN((O2027-M2027)*24,0) & \" h \" & ROUNDDOWN(MOD((O2027-M2027)*1440,60),0) & \" min\",\"\")","v":"83 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F50662",null,"< >",8140,2066,2026,2026,{"$f":"WEEKNUM(L2028)+[7]dates!$L$3-[7]dates!$H$3","v":39},{"$f":"WEEKNUM(N2028)+[7]dates!$L$3-[7]dates!$H$3","v":42},"2026-09-21","00:00:00","2026-10-11",0.99998842592592585,{"$f":"TEXT(N2028-L2028+ROUNDDOWN(O2028-M2028,0),\"0\")&\" days\"& IF(MOD((O2028-M2028)*24,24)>0,\" + \" & ROUNDDOWN((O2028-M2028)*24,0) & \" h \" & ROUNDDOWN(MOD((O2028-M2028)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F64267",null,"< >",8179,8118,2026,2026,{"$f":"WEEKNUM(L2029)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N2029)+[7]dates!$L$3-[7]dates!$H$3","v":7},"2026-01-05","00:00:00","2026-02-08",0.99998842592592585,{"$f":"TEXT(N2029-L2029+ROUNDDOWN(O2029-M2029,0),\"0\")&\" days\"& IF(MOD((O2029-M2029)*24,24)>0,\" + \" & ROUNDDOWN((O2029-M2029)*24,0) & \" h \" & ROUNDDOWN(MOD((O2029-M2029)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F39537",null,"< >",8190,8183,2026,2026,{"$f":"WEEKNUM(L2030)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N2030)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-01-05","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N2030-L2030+ROUNDDOWN(O2030-M2030,0),\"0\")&\" days\"& IF(MOD((O2030-M2030)*24,24)>0,\" + \" & ROUNDDOWN((O2030-M2030)*24,0) & \" h \" & ROUNDDOWN(MOD((O2030-M2030)*1440,60),0) & \" min\",\"\")","v":"90 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F50666",null,"< >",8212,8212,2026,2026,{"$f":"WEEKNUM(L2031)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N2031)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-02-23","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N2031-L2031+ROUNDDOWN(O2031-M2031,0),\"0\")&\" days\"& IF(MOD((O2031-M2031)*24,24)>0,\" + \" & ROUNDDOWN((O2031-M2031)*24,0) & \" h \" & ROUNDDOWN(MOD((O2031-M2031)*1440,60),0) & \" min\",\"\")","v":"188 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63462",null,"< >",8285,4406,2026,2026,{"$f":"WEEKNUM(L2032)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N2032)+[7]dates!$L$3-[7]dates!$H$3","v":23},"2026-03-16","00:00:00","2026-05-31",0.99998842592592585,{"$f":"TEXT(N2032-L2032+ROUNDDOWN(O2032-M2032,0),\"0\")&\" days\"& IF(MOD((O2032-M2032)*24,24)>0,\" + \" & ROUNDDOWN((O2032-M2032)*24,0) & \" h \" & ROUNDDOWN(MOD((O2032-M2032)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A63462",null,"< >",8285,4406,2026,2026,{"$f":"WEEKNUM(L2033)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N2033)+[7]dates!$L$3-[7]dates!$H$3","v":43},"2026-10-05","00:00:00","2026-10-18",0.99998842592592585,{"$f":"TEXT(N2033-L2033+ROUNDDOWN(O2033-M2033,0),\"0\")&\" days\"& IF(MOD((O2033-M2033)*24,24)>0,\" + \" & ROUNDDOWN((O2033-M2033)*24,0) & \" h \" & ROUNDDOWN(MOD((O2033-M2033)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B63462",null,"< >",8285,4406,2026,2026,{"$f":"WEEKNUM(L2034)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N2034)+[7]dates!$L$3-[7]dates!$H$3","v":22},"2026-03-30","00:00:00","2026-05-24",0.99998842592592585,{"$f":"TEXT(N2034-L2034+ROUNDDOWN(O2034-M2034,0),\"0\")&\" days\"& IF(MOD((O2034-M2034)*24,24)>0,\" + \" & ROUNDDOWN((O2034-M2034)*24,0) & \" h \" & ROUNDDOWN(MOD((O2034-M2034)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A59445",null,"< >",8302,5139,2026,2026,{"$f":"WEEKNUM(L2035)+[7]dates!$L$3-[7]dates!$H$3","v":15},{"$f":"WEEKNUM(N2035)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-04-06","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N2035-L2035+ROUNDDOWN(O2035-M2035,0),\"0\")&\" days\"& IF(MOD((O2035-M2035)*24,24)>0,\" + \" & ROUNDDOWN((O2035-M2035)*24,0) & \" h \" & ROUNDDOWN(MOD((O2035-M2035)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B52470",null,"< >",8309,8309,2026,2026,{"$f":"WEEKNUM(L2036)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N2036)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-23","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N2036-L2036+ROUNDDOWN(O2036-M2036,0),\"0\")&\" days\"& IF(MOD((O2036-M2036)*24,24)>0,\" + \" & ROUNDDOWN((O2036-M2036)*24,0) & \" h \" & ROUNDDOWN(MOD((O2036-M2036)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F58607",null,"< >",8309,4728,2026,2026,{"$f":"WEEKNUM(L2037)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N2037)+[7]dates!$L$3-[7]dates!$H$3","v":32},"2026-01-05","00:00:00","2026-08-02",0.99998842592592585,{"$f":"TEXT(N2037-L2037+ROUNDDOWN(O2037-M2037,0),\"0\")&\" days\"& IF(MOD((O2037-M2037)*24,24)>0,\" + \" & ROUNDDOWN((O2037-M2037)*24,0) & \" h \" & ROUNDDOWN(MOD((O2037-M2037)*1440,60),0) & \" min\",\"\")","v":"209 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A58607",null,"< >",8309,4728,2026,2026,{"$f":"WEEKNUM(L2038)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N2038)+[7]dates!$L$3-[7]dates!$H$3","v":36},"2026-08-10","00:00:00","2026-08-30",0.99998842592592585,{"$f":"TEXT(N2038-L2038+ROUNDDOWN(O2038-M2038,0),\"0\")&\" days\"& IF(MOD((O2038-M2038)*24,24)>0,\" + \" & ROUNDDOWN((O2038-M2038)*24,0) & \" h \" & ROUNDDOWN(MOD((O2038-M2038)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B58607",null,"< >",8309,4728,2026,2026,{"$f":"WEEKNUM(L2039)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N2039)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-01-05","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N2039-L2039+ROUNDDOWN(O2039-M2039,0),\"0\")&\" days\"& IF(MOD((O2039-M2039)*24,24)>0,\" + \" & ROUNDDOWN((O2039-M2039)*24,0) & \" h \" & ROUNDDOWN(MOD((O2039-M2039)*1440,60),0) & \" min\",\"\")","v":"104 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F63450",null,"< >",8387,6451,2026,2026,{"$f":"WEEKNUM(L2040)+[7]dates!$L$3-[7]dates!$H$3","v":7},{"$f":"WEEKNUM(N2040)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-09","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N2040-L2040+ROUNDDOWN(O2040-M2040,0),\"0\")&\" days\"& IF(MOD((O2040-M2040)*24,24)>0,\" + \" & ROUNDDOWN((O2040-M2040)*24,0) & \" h \" & ROUNDDOWN(MOD((O2040-M2040)*1440,60),0) & \" min\",\"\")","v":"55 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A63450",null,"< >",8387,6451,2026,2026,{"$f":"WEEKNUM(L2041)+[7]dates!$L$3-[7]dates!$H$3","v":12},{"$f":"WEEKNUM(N2041)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-03-16","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N2041-L2041+ROUNDDOWN(O2041-M2041,0),\"0\")&\" days\"& IF(MOD((O2041-M2041)*24,24)>0,\" + \" & ROUNDDOWN((O2041-M2041)*24,0) & \" h \" & ROUNDDOWN(MOD((O2041-M2041)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F43639",null,"< >",8407,7426,2026,2026,{"$f":"WEEKNUM(L2042)+[7]dates!$L$3-[7]dates!$H$3","v":6},{"$f":"WEEKNUM(N2042)+[7]dates!$L$3-[7]dates!$H$3","v":8},"2026-02-02","00:00:00","2026-02-15",0.99998842592592585,{"$f":"TEXT(N2042-L2042+ROUNDDOWN(O2042-M2042,0),\"0\")&\" days\"& IF(MOD((O2042-M2042)*24,24)>0,\" + \" & ROUNDDOWN((O2042-M2042)*24,0) & \" h \" & ROUNDDOWN(MOD((O2042-M2042)*1440,60),0) & \" min\",\"\")","v":"13 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A43639",null,"< >",8407,7426,2026,2026,{"$f":"WEEKNUM(L2043)+[7]dates!$L$3-[7]dates!$H$3","v":14},{"$f":"WEEKNUM(N2043)+[7]dates!$L$3-[7]dates!$H$3","v":19},"2026-03-30","00:00:00","2026-05-03",0.99998842592592585,{"$f":"TEXT(N2043-L2043+ROUNDDOWN(O2043-M2043,0),\"0\")&\" days\"& IF(MOD((O2043-M2043)*24,24)>0,\" + \" & ROUNDDOWN((O2043-M2043)*24,0) & \" h \" & ROUNDDOWN(MOD((O2043-M2043)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","B43639",null,"< >",8407,7426,2026,2026,{"$f":"WEEKNUM(L2044)+[7]dates!$L$3-[7]dates!$H$3","v":9},{"$f":"WEEKNUM(N2044)+[7]dates!$L$3-[7]dates!$H$3","v":15},"2026-02-23","00:00:00","2026-04-05",0.99998842592592585,{"$f":"TEXT(N2044-L2044+ROUNDDOWN(O2044-M2044,0),\"0\")&\" days\"& IF(MOD((O2044-M2044)*24,24)>0,\" + \" & ROUNDDOWN((O2044-M2044)*24,0) & \" h \" & ROUNDDOWN(MOD((O2044-M2044)*1440,60),0) & \" min\",\"\")","v":"41 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","C43639",null,"< >",8407,7426,2026,2026,{"$f":"WEEKNUM(L2045)+[7]dates!$L$3-[7]dates!$H$3","v":23},{"$f":"WEEKNUM(N2045)+[7]dates!$L$3-[7]dates!$H$3","v":30},"2026-06-01","00:00:00","2026-07-19",0.99998842592592585,{"$f":"TEXT(N2045-L2045+ROUNDDOWN(O2045-M2045,0),\"0\")&\" days\"& IF(MOD((O2045-M2045)*24,24)>0,\" + \" & ROUNDDOWN((O2045-M2045)*24,0) & \" h \" & ROUNDDOWN(MOD((O2045-M2045)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","D43639",null,"< >",8407,7426,2026,2026,{"$f":"WEEKNUM(L2046)+[7]dates!$L$3-[7]dates!$H$3","v":33},{"$f":"WEEKNUM(N2046)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-08-10","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N2046-L2046+ROUNDDOWN(O2046-M2046,0),\"0\")&\" days\"& IF(MOD((O2046-M2046)*24,24)>0,\" + \" & ROUNDDOWN((O2046-M2046)*24,0) & \" h \" & ROUNDDOWN(MOD((O2046-M2046)*1440,60),0) & \" min\",\"\")","v":"48 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","H43639",null,"< >",8407,7426,2026,2026,{"$f":"WEEKNUM(L2047)+[7]dates!$L$3-[7]dates!$H$3","v":41},{"$f":"WEEKNUM(N2047)+[7]dates!$L$3-[7]dates!$H$3","v":50},"2026-10-05","00:00:00","2026-12-06",0.99998842592592585,{"$f":"TEXT(N2047-L2047+ROUNDDOWN(O2047-M2047,0),\"0\")&\" days\"& IF(MOD((O2047-M2047)*24,24)>0,\" + \" & ROUNDDOWN((O2047-M2047)*24,0) & \" h \" & ROUNDDOWN(MOD((O2047-M2047)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","K43639",null,"< >",8407,7426,2026,2026,{"$f":"WEEKNUM(L2048)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N2048)+[7]dates!$L$3-[7]dates!$H$3","v":21},"2026-04-27","00:00:00","2026-05-17",0.99998842592592585,{"$f":"TEXT(N2048-L2048+ROUNDDOWN(O2048-M2048,0),\"0\")&\" days\"& IF(MOD((O2048-M2048)*24,24)>0,\" + \" & ROUNDDOWN((O2048-M2048)*24,0) & \" h \" & ROUNDDOWN(MOD((O2048-M2048)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","L43639",null,"< >",8407,7426,2026,2026,{"$f":"WEEKNUM(L2049)+[7]dates!$L$3-[7]dates!$H$3","v":30},{"$f":"WEEKNUM(N2049)+[7]dates!$L$3-[7]dates!$H$3","v":34},"2026-07-20","00:00:00","2026-08-16",0.99998842592592585,{"$f":"TEXT(N2049-L2049+ROUNDDOWN(O2049-M2049,0),\"0\")&\" days\"& IF(MOD((O2049-M2049)*24,24)>0,\" + \" & ROUNDDOWN((O2049-M2049)*24,0) & \" h \" & ROUNDDOWN(MOD((O2049-M2049)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","M43639",null,"< >",8407,7426,2026,2026,{"$f":"WEEKNUM(L2050)+[7]dates!$L$3-[7]dates!$H$3","v":39},{"$f":"WEEKNUM(N2050)+[7]dates!$L$3-[7]dates!$H$3","v":44},"2026-09-21","00:00:00","2026-10-25",0.99998842592592585,{"$f":"TEXT(N2050-L2050+ROUNDDOWN(O2050-M2050,0),\"0\")&\" days\"& IF(MOD((O2050-M2050)*24,24)>0,\" + \" & ROUNDDOWN((O2050-M2050)*24,0) & \" h \" & ROUNDDOWN(MOD((O2050-M2050)*1440,60),0) & \" min\",\"\")","v":"34 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F56064",null,"< >",8464,7454,2026,2026,{"$f":"WEEKNUM(L2051)+[7]dates!$L$3-[7]dates!$H$3","v":13},{"$f":"WEEKNUM(N2051)+[7]dates!$L$3-[7]dates!$H$3","v":24},"2026-03-23","00:00:00","2026-06-07",0.99998842592592585,{"$f":"TEXT(N2051-L2051+ROUNDDOWN(O2051-M2051,0),\"0\")&\" days\"& IF(MOD((O2051-M2051)*24,24)>0,\" + \" & ROUNDDOWN((O2051-M2051)*24,0) & \" h \" & ROUNDDOWN(MOD((O2051-M2051)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F65623",null,"< >",8464,7454,2026,2026,{"$f":"WEEKNUM(L2052)+[7]dates!$L$3-[7]dates!$H$3","v":8},{"$f":"WEEKNUM(N2052)+[7]dates!$L$3-[7]dates!$H$3","v":39},"2026-02-16","00:00:00","2026-09-20",0.99998842592592585,{"$f":"TEXT(N2052-L2052+ROUNDDOWN(O2052-M2052,0),\"0\")&\" days\"& IF(MOD((O2052-M2052)*24,24)>0,\" + \" & ROUNDDOWN((O2052-M2052)*24,0) & \" h \" & ROUNDDOWN(MOD((O2052-M2052)*1440,60),0) & \" min\",\"\")","v":"216 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F46748",null,"< >",8511,2565,2026,2026,{"$f":"WEEKNUM(L2053)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N2053)+[7]dates!$L$3-[7]dates!$H$3","v":17},"2026-01-05","00:00:00","2026-04-19",0.99998842592592585,{"$f":"TEXT(N2053-L2053+ROUNDDOWN(O2053-M2053,0),\"0\")&\" days\"& IF(MOD((O2053-M2053)*24,24)>0,\" + \" & ROUNDDOWN((O2053-M2053)*24,0) & \" h \" & ROUNDDOWN(MOD((O2053-M2053)*1440,60),0) & \" min\",\"\")","v":"104 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A46748",null,"< >",8511,2565,2026,2026,{"$f":"WEEKNUM(L2054)+[7]dates!$L$3-[7]dates!$H$3","v":2},{"$f":"WEEKNUM(N2054)+[7]dates!$L$3-[7]dates!$H$3","v":11},"2026-01-05","00:00:00","2026-03-08",0.99998842592592585,{"$f":"TEXT(N2054-L2054+ROUNDDOWN(O2054-M2054,0),\"0\")&\" days\"& IF(MOD((O2054-M2054)*24,24)>0,\" + \" & ROUNDDOWN((O2054-M2054)*24,0) & \" h \" & ROUNDDOWN(MOD((O2054-M2054)*1440,60),0) & \" min\",\"\")","v":"62 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A62969",null,"< >",8654,8656,2026,2026,{"$f":"WEEKNUM(L2055)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N2055)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-04-27","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N2055-L2055+ROUNDDOWN(O2055-M2055,0),\"0\")&\" days\"& IF(MOD((O2055-M2055)*24,24)>0,\" + \" & ROUNDDOWN((O2055-M2055)*24,0) & \" h \" & ROUNDDOWN(MOD((O2055-M2055)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F57796",null,"< >",8655,8405,2026,2026,{"$f":"WEEKNUM(L2056)+[7]dates!$L$3-[7]dates!$H$3","v":25},{"$f":"WEEKNUM(N2056)+[7]dates!$L$3-[7]dates!$H$3","v":28},"2026-06-15","00:00:00","2026-07-05",0.99998842592592585,{"$f":"TEXT(N2056-L2056+ROUNDDOWN(O2056-M2056,0),\"0\")&\" days\"& IF(MOD((O2056-M2056)*24,24)>0,\" + \" & ROUNDDOWN((O2056-M2056)*24,0) & \" h \" & ROUNDDOWN(MOD((O2056-M2056)*1440,60),0) & \" min\",\"\")","v":"20 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","A57796",null,"< >",8655,8405,2026,2026,{"$f":"WEEKNUM(L2057)+[7]dates!$L$3-[7]dates!$H$3","v":36},{"$f":"WEEKNUM(N2057)+[7]dates!$L$3-[7]dates!$H$3","v":40},"2026-08-31","00:00:00","2026-09-27",0.99998842592592585,{"$f":"TEXT(N2057-L2057+ROUNDDOWN(O2057-M2057,0),\"0\")&\" days\"& IF(MOD((O2057-M2057)*24,24)>0,\" + \" & ROUNDDOWN((O2057-M2057)*24,0) & \" h \" & ROUNDDOWN(MOD((O2057-M2057)*1440,60),0) & \" min\",\"\")","v":"27 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R","F62969",null,"< >",8655,6452,2026,2026,{"$f":"WEEKNUM(L2058)+[7]dates!$L$3-[7]dates!$H$3","v":18},{"$f":"WEEKNUM(N2058)+[7]dates!$L$3-[7]dates!$H$3","v":29},"2026-04-27","00:00:00","2026-07-12",0.99998842592592585,{"$f":"TEXT(N2058-L2058+ROUNDDOWN(O2058-M2058,0),\"0\")&\" days\"& IF(MOD((O2058-M2058)*24,24)>0,\" + \" & ROUNDDOWN((O2058-M2058)*24,0) & \" h \" & ROUNDDOWN(MOD((O2058-M2058)*1440,60),0) & \" min\",\"\")","v":"76 days + 23 h 59 min"},"continuous"]
[null,"SNCF-R"," F59602",null,"< >",8688,1611,2026,2026,{"$f":"WEEKNUM(L2059)+[7]dates!$L$3-[7]dates!$H$3","v":4},{"$f":"WEEKNUM(N2059)+[7]dates!$L$3-[7]dates!$H$3","v":39},"2026-01-19","00:00:00","2026-09-20",0.99998842592592585,{"$f":"TEXT(N2059-L2059+ROUNDDOWN(O2059-M2059,0),\"0\")&\" days\"& IF(MOD((O2059-M2059)*24,24)>0,\" + \" & ROUNDDOWN((O2059-M2059)*24,0) & \" h \" & ROUNDDOWN(MOD((O2059-M2059)*1440,60),0) & \" min\",\"\")","v":"244 days + 23 h 59 min"},"continuous"]

{"sheet":"Data","index":7,"n_rows":24,"n_cols":7,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction"]
["SNCF R",87,"Boulogne-Calais",1,"All day",10868,"Signal work"]
[null,null,"Calais-Dunkerque-Hazebrouck",2,"Day",null,"Switch work"]
[null,null,"Calais-Lille-Aulnoye",3,"Night",null,"Catenary work"]
[null,null,"Hazebrouck-Lens-Aulnoye",4,null,null,"Track work"]
[null,null,"Amiens-Douai",5,null,null,"Rail work"]
[null,null,"Paris-Amiens",6,null,null,"Tunnel work"]
[null,null,"Paris-Busigny",7,null,null,"Bridge work"]
[null,null,"Aulnoye-Longuyon",8,null,null,"Misc. Work"]
[null,null,"Longuyon-Metz-Sarrebourg",9,null,null,"Maintanance"]
[null,null,"Longuyon-Nancy-Sarrebourg",10]
[null,null,"Lerouville-Metz",11]
[null,null,"Lerouville-Nancy",12]
[null,null,"Sarrebourg-Basel",13]
[null,null,"Dijon-Toul",14]
[null,null,"Dijon-Lyon",15]
[null,null,"Dijon-Amberieu-Lyon",16]
[null,null,"Lyon-Valence",17]
[null,null,"Valence - Avignon",18]
[null,null,"Avignon-Miramasparouest",19]
[null,null,"Avignon-Miramasparest",20]
[null,null,"Miramas-Marseille",21]
[null,null,"Miramas-Fos-Marseille",22]
[null,null,"Aulnoye-Feignies-Jeumont",23]