{"text_format":"1","workbook":"xlsx","n_sheets":8,"sheets":["Home","Main Impact Map","ACF CFL-I","Infrabel","ProRail","SBB-I TVS","SNCF-R","Data"],"not_rendered":{"charts":0,"images":12,"macros":1,"external_links":6,"defined_names":60,"comments":3,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Home","index":0,"n_rows":5,"n_cols":15,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"! click icon to follow !"]

{"sheet":"Main Impact Map","index":1,"n_rows":15,"n_cols":14,"rows_kept":15,"cut":false,"hidden":false,"merged":[[45,5,46,7]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"Main TCR for TT 2025 to TT 2027"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,"23/01/2025 version 1"]
[null,null,null,null,null,null,null,null,null,null,null,null,"click on the comments for a direct link to TCR details"]

{"sheet":"ACF CFL-I","index":2,"n_rows":89,"n_cols":31,"rows_kept":89,"cut":false,"hidden":false,"merged":[[0,17,0,21],[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13]]}
["IM",null,"Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,"New ID",null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["CFL-Infra / ACF","ACF213","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,2,2,"2025-01-11","01:00:00","2025-01-13","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF490","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,4,4,"2025-01-25","01:00:00","2025-01-27","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF528","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,5,5,"2025-02-01","01:00:00","2025-02-03","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF529","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,6,6,"2025-02-08","01:00:00","2025-02-10","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF651","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,7,7,"2025-02-15","01:00:00","2025-02-17","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF345","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,7,8,"2025-02-15","01:00:00","2025-02-24","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF530","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,7,7,"2025-02-15","01:00:00","2025-02-17","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF473","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,8,8,"2025-02-17","01:00:00","2024-02-24","04:00:00","7 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF485","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,9,9,"2025-03-01","01:00:00","2025-03-03","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF329","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,10,10,"2025-03-08","01:00:00","2025-03-10","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF474","Rodange-Bettembourg","< >","Pétange","Hollerich",2025,2025,11,11,"2025-03-15","01:00:00","2025-03-17","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF531","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,11,11,"2025-03-15","01:00:00","2025-03-17","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF532","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,12,12,"2025-03-22","01:00:00","2024-03-24","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF533","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,13,13,"2025-03-29","01:00:00","2025-03-31","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF534","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,14,14,"2025-04-05","01:00:00","2025-04-07","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF236","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2025,2025,14,16,"2025-04-05","00:00:00","2025-04-22","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF275","Rodange-Bettembourg","< >","Berchem","Bettembourg",2025,2025,14,16,"2025-04-05","00:00:00","2025-04-22","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF535","Rodange-Bettembourg","< >","Luxembourg","Berchem",2025,2025,15,15,"2025-04-12","01:00:00","2025-04-14","04:00:00","2 days","Night/Day","New platform / New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF549","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,17,17,"2025-04-26","01:00:00","2025-04-28","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF477","Athus/Aubange-Bettembourg","< >","Athus/Aubange","Pétange",2025,2025,18,18,"2025-05-03","01:00:00","2025-05-05","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF486","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,19,19,"2025-05-10","01:00:00","2025-05-12","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF550","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,20,20,"2025-05-17","01:00:00","2025-05-19","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF279","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2025,2025,21,22,"2025-05-24","00:00:00","2025-06-02","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF487","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,21,22,"2025-05-24","00:00:00","2025-06-02","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF551","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,23,23,"2025-06-07","01:00:00","2025-06-09","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF478","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,24,24,"2025-06-14","01:00:00","2025-06-16","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF284","Rodange-Bettembourg","< >","Berchem","Bettembourg",2025,2025,26,26,"2025-06-28","01:00:00","2025-06-30","04:00:00","2 days","Night/Day","New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF285","Rodange-Bettembourg","< >","Berchem","Bettembourg",2025,2025,27,27,"2025-07-05","01:00:00","2025-07-07","04:00:00","2 days","Night/Day","New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF488","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,28,28,"2025-07-12","01:00:00","2025-07-14","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF234","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2025,2025,29,37,"2025-07-12","01:00:00","2025-09-15","04:00:00","2 months","Night/Day","New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF526","Rodange-Bettembourg","< >","Fentange","Hollerich",2025,2025,38,52,"2025-09-15","04:00:00","2025-12-31","23:59:00","3 1/2 month","Night/Day","New platform / New line",null,"x",null,null,null,null,"x",null,"x"]
["CFL-Infra / ACF","ACF475","Rodange-Bettembourg","< >","Pétange","Hollerich",2025,2025,38,38,"2025-09-20","01:00:00","2025-09-22","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF512","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,38,38,"2025-09-20","01:00:00","2025-09-22","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF513","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,39,39,"2025-09-27","01:00:00","2025-09-29","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF471","Rodange-Bettembourg","< >","Fentange","Hollerich",2025,2025,40,40,"2025-10-04","01:00:00","2025-10-06","04:00:00","2 days","Night/Day","Public road works & Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF483","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,41,41,"2025-10-11","01:00:00","2025-10-13","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF489","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2025,2025,42,42,"2025-10-18","01:00:00","2025-10-20","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF484","Rodange-Bettembourg","< >","Differdange","Belval-Usines",2025,2025,43,43,"2025-10-25","01:00:00","2025-10-27","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF281","Rodange-Bettembourg","< >","Pétange","Luxembourg",2025,2025,44,45,"2025-11-01","01:00:00","2025-11-10","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF514","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2025,2025,46,46,"2025-11-15","01:00:00","2025-11-17","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF232","Rodange-Bettembourg","< >","Dippach/Reckange","Hollerich",2025,2025,47,47,"2025-11-22","01:00:00","2025-11-24","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF491","Rodange-Bettembourg","< >","Fentange","Hollerich",2026,2026,9,9,"2026-02-28","01:00:00","2026-03-02","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF589","Rodange-Bettembourg","< >","Fentange","Luxembourg",2026,2026,7,8,"2026-02-14","01:00:00","2024-02-23","04:00:00","1 week","Night/Day","New line",null,"x",null,null,null,"x","x"]
["CFL-Infra / ACF","ACF677","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2026,2026,7,8,"2026-02-14","01:00:00","2024-02-23","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF640","Rodange-Bettembourg","< >","Rodange","Pétange",2026,2026,10,10,"2026-03-07","01:00:00","2026-03-09","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF641","Rodange-Bettembourg","< >","Rodange","Pétange",2026,2026,11,11,"2026-03-14","01:00:00","2026-03-16","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF497","Rodange-Bettembourg","< >","Pétange","Luxembourg",2026,2026,12,12,"2026-03-21","01:00:00","2026-03-23","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF280","Rodange-Bettembourg","< >","Esch/Alzette","Bettembourg",2026,2026,13,15,"2026-03-28","00:00:00","2026-04-13","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF495","Luxembourg-Kleinbettingen","< >","Bertrange/Str.","Kleinbettingen",2026,2026,13,15,"2026-03-28","00:00:00","2026-04-13","04:00:00","2 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF558","Rodange-Bettembourg","< >","Rodange","Pétange",2026,2026,16,16,"2026-04-18","01:00:00","2026-04-20","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF498","Rodange-Bettembourg","< >","Rodange","Pétange",2026,2026,17,17,"2026-04-25","01:00:00","2026-04-27","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF643","Rodange-Bettembourg","< >","Rodange","Pétange",2026,2026,18,18,"2026-05-01","01:00:00","2026-05-04","04:00:00","3 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF496","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2026,2026,21,22,"2026-05-23","01:00:00","2026-06-01","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF590","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2026,2026,21,22,"2026-05-23","01:00:00","2026-06-01","04:00:00","1 week","Night/Day","New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF694","Rodange-Bettembourg","< >","Fentange","Hollerich",2026,2026,24,24,"2026-06-13","01:00:00","2026-06-15","04:00:00","2 days","Night/Day","Public road works","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF397","Rodange-Bettembourg","< >","Berchem","Bettembourg",2026,2026,29,35,"2026-07-16","01:00:00","2026-08-24","04:00:00","6 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF685","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2026,2026,39,39,"2026-09-26","01:00:00","2026-09-28","04:00:00","2 days","Night/Day","Public works",null,"x",null,null,null,"x","x"]
["CFL-Infra / ACF","ACF686","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2026,2026,41,41,"2026-10-10","01:00:00","2026-10-12","04:00:00","2 days","Night/Day","Public works",null,"x",null,null,null,"x","x"]
["CFL-Infra / ACF","ACF687","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2026,2026,42,42,"2026-10-17","01:00:00","2026-10-19","04:00:00","2 days","Night/Day","Public works",null,"x",null,null,null,"x","x"]
["CFL-Infra / ACF","ACF695","Rodange-Bettembourg","< >","Fentange","Hollerich",2026,2026,43,43,"2026-10-24","01:00:00","2026-10-26","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF499","Rodange-Bettembourg","< >","Pétange","Belval-Usines",2026,2026,40,40,"2026-10-03","01:00:00","2026-10-05","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF678","Rodange-Bettembourg","< >","Pétange","Luxembourg",2026,2026,44,45,"2026-10-31","01:00:00","2026-11-09","04:00:00","1 week","Night/Day","New train station","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF678","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2026,2026,44,45,"2026-10-31","01:00:00","2026-11-09","04:00:00","1 week","Night/Day","New train station","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF688","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2026,2026,48,48,"2026-11-28","01:00:00","2026-11-30","04:00:00","2 days","Night/Day","Public works",null,"x",null,null,null,"x","x"]
["CFL-Infra / ACF","ACF749","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2027,2027,3,3,"2027-01-23","01:00:00","2027-01-25","04:00:00","2 days","Night/Day","Public works",null,"x",null,null,null,"x","x"]
["CFL-Infra / ACF","ACF767","Rodange-Bettembourg","< >","Fentange","Hollerich",2027,2027,8,8,"2027-02-27","01:00:00","2027-03-01","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF769","Rodange-Bettembourg","< >","Pétange","Luxembourg",2027,2027,9,9,"2027-03-06","01:00:00","2027-03-08","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF753","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2027,2027,10,10,"2027-03-13","01:00:00","2027-03-15","04:00:00","2 days","Night/Day","Public works",null,"x",null,null,null,"x","x"]
["CFL-Infra / ACF","ACF752","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2027,2027,11,11,"2027-03-20","01:00:00","2027-03-22","04:00:00","2 days","Night/Day","Public works",null,"x",null,null,null,"x","x"]
["CFL-Infra / ACF","ACF734","Luxembourg-Kleinbettingen","< >","Luxembourg","Bertrange/Str.",2027,2027,12,14,"2027-03-27","01:00:00","2027-04-12","04:00:00","2 weeks","Night/Day","New train station","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF734","Rodange-Bettembourg","< >","Pétange","Luxembourg",2027,2027,12,14,"2027-03-27","01:00:00","2027-04-12","04:00:00","2 weeks","Night/Day","New train station","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF732","Luxembourg-Kleinbettingen","< >","Luxembourg","Bertrange/Str.",2027,2027,15,22,"2027-04-12","01:00:00","2027-06-07","04:00:00","8 weeks","Night/Day","New train station",null,"x",null,null,null,"x","x"]
["CFL-Infra / ACF","ACF732","Rodange-Bettembourg","< >","Pétange","Luxembourg",2027,2027,15,22,"2027-04-12","01:00:00","2027-06-07","04:00:00","8 weeks","Night/Day","New train station",null,"x",null,null,null,"x","x"]
["CFL-Infra / ACF","ACF754","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2027,2027,16,16,"2027-04-24","01:00:00","2027-04-26","04:00:00","2 days","Night/Day","Public works","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF539","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2027,2027,21,22,"2027-05-29","01:00:00","2027-06-07","04:00:00","1 week","Night/Day","New train station","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF544","Rodange-Bettembourg","< >","Pétange","Luxembourg",2027,2027,21,22,"2027-05-29","01:00:00","2027-06-07","04:00:00","1 week","Night/Day","New train station","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF711","Rodange-Bettembourg","< >","Rodange","Pétange",2027,2027,23,23,"2027-06-12","01:00:00","2027-06-14","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF755","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2027,2027,26,26,"2027-07-03","01:00:00","2027-07-05","04:00:00","2 days","Night/Day","Public works","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF727","Rodange-Bettembourg","< >","Berchem","Bettembourg",2027,2027,28,33,"2027-07-16","01:00:00","2027-08-23","04:00:00","6 weeks","Night/Day","New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF728","Rodange-Bettembourg","< >","Berchem","Bettembourg",2027,2027,33,37,"2027-08-23","01:00:00","2027-09-15","04:00:00","3 weeks","Night/Day","New line","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF540","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2027,2027,33,37,"2027-08-23","01:00:00","2027-09-13","04:00:00","3 weeks","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF705","Bettembourg-Thionville","< >","Bettembourg","Thionville",2027,2027,35,36,"2027-09-01","01:00:00","2027-09-10","04:00:00","10 days","Night/Day","track renewal","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF781","Rodange-Bettembourg","< >","Pétange","Differdange",2027,2027,39,39,"2027-10-02","01:00:00","2027-10-04","04:00:00","2 days","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF546","Rodange-Bettembourg","< >","Pétange","Luxembourg",2027,2027,43,45,"2027-10-30","01:00:00","2027-11-08","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF568","Luxembourg-Kleinbettingen","< >","Luxembourg","Kleinbettingen",2027,2027,43,45,"2027-10-30","01:00:00","2027-11-08","04:00:00","1 week","Night/Day","Infrastructure maintenance","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF756","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2027,2027,46,46,"2027-11-13","01:00:00","2027-11-15","04:00:00","2 days","Night/Day","Public works","x",null,null,null,null,"x","x"]
["CFL-Infra / ACF","ACF757","Rodange-Bettembourg","< >","Luxembourg","Bettembourg",2027,2027,47,47,"2027-11-20","01:00:00","2027-11-22","04:00:00","2 days","Night/Day","Public works","x",null,null,null,null,"x","x"]

{"sheet":"Infrabel","index":3,"n_rows":4339,"n_cols":43,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)","Last updated","Classification","Weekdays","Interval","Affected Estimated Travel Volume","Affected Border","Deviation Location","Deviation Border","Status","Additional Information","Automatic process"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"Infrabel","77567","Namur - Antwerpen","< >","BAKENBOS","OTTIGNIES",2024,2026,17,45,"2024-04-22",45644.003472222219,"2026-11-02",45644.201388888891,"924d, 04:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mise à 4 voies entre Ottignies et Baekenbos\r\nPassage via L161A(1)\r\nDossier de concertation validé en octobre 2023",null,null,77567,"2024-07-12",3,"1,2,3,4,5,6,7"]
[null,"Infrabel","58458","Namur - Antwerpen",">","ANTWERPEN-CENTRAAL","ANTWERPEN-CENTRAAL",2024,2025,35,15,"2024-09-01",45644.993055555555,"2025-04-07",45644.003472222219,"217d, 00:15h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2024-409\r\nspoor 5(L12 sp A) en 6 Antwerpen-Centraal in continue buiten dienst\r\nPert sept\r\n\r\nR-457120",null,null,58458,"2024-11-13",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","74026","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,1,1,"2025-01-01",45644.923611111109,"2025-01-04",45644.173611111109,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de ligne",null,null,74026,"2024-09-23",0,"1,2,3,4,5"]
[null,"Infrabel","71128","Athus - Meuse",">","VONECHE","GEDINNE",2025,2025,1,1,"2025-01-02",45644.354166666664,"2025-01-02",45644.65625,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,71128,"2024-08-06",0,"1,2,3,4,5"]
[null,"Infrabel","71130","Athus - Meuse",">","GEDINNE","VONECHE",2025,2025,1,1,"2025-01-03",45644.354166666664,"2025-01-03",45644.65625,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,71130,"2024-08-06",0,"1,2,3,4,5"]
[null,"Infrabel","68701","Erquelinnes - Montzen","< >","Y.VAL-BENOIT","Y.RENORY",2025,2025,1,1,"2025-01-04",45644.979166666664,"2025-01-05",45644.208333333336,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien caténaire",null,null,68701,"2024-08-27",0,"5,6"]
[null,"Infrabel","75213","Lille - Antwerpen",">","Y.MELSELE","SINT-NIKLAAS",2025,2025,1,1,"2025-01-04",45644.013888888891,"2025-01-04",45644.215277777781,"1d, 04:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\nTCR500299",null,null,75213,"2024-07-17",0,"1,2,3,4,5"]
[null,"Infrabel","75029","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,1,2,"2025-01-04",45644.010416666664,"2025-01-06",45644.1875,"3d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Migratie tunnelveiligheidstechnieken Antw. NZ -2\r\nAntwerpen-Centraal - Antwerpen-Luchtbal",null,null,75029,"2024-01-31",0,"5,6"]
[null,"Infrabel","70005","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2025,2025,1,1,"2025-01-05",45644.333333333336,"2025-01-05",45644.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144-130/1\r\nUPM 507094",null,null,70005,"2024-08-27",0,"5,6"]
[null,"Infrabel","75214","Lille - Antwerpen","< >","OOSTAKKER","Y.MELSELE",2025,2025,1,1,"2025-01-05",45644.020833333336,"2025-01-05",45644.21875,"1d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud\r\nTCR500327",null,null,75214,"2024-05-31",0,"5,6"]
[null,"Infrabel","71132","Athus - Meuse",">","GEDINNE","PALISEUL",2025,2025,2,2,"2025-01-06",45644.333333333336,"2025-01-06",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,71132,"2024-08-30",0,"1,2,3,4,5"]
[null,"Infrabel","72704","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,2,2,"2025-01-06",45644.979166666664,"2025-01-11",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72704,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","56440","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,2,2,"2025-01-06",45644.993055555555,"2025-01-11",45644.215277777781,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n1- Réalisation de massifs et pose de poteaux\r\n+ Modernisation Axe 3\r\nUPM 487844",null,null,56440,"2024-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","71335","Athus - Meuse","< >","AUBANGE-FRONTIERE-FRANCE","Y.AUBANGE",2025,2025,2,2,"2025-01-06",45644.354166666664,"2025-01-06",45644.5,"1d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite voie unique L 165/2 \r\nVisite voie unique L 165/3\r\nVisite voie unique L 165/1",null,null,71335,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","71429","Athus - Meuse",">","NAMUR","JAMBES",2025,2025,2,2,"2025-01-06",45644.388888888891,"2025-01-06",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,71429,"2024-09-03",0,"1,2,3,4,5"]
[null,"Infrabel","73122","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2025,2025,2,2,"2025-01-06",45644.423611111109,"2025-01-06",45644.493055555555,"1d, 01:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,73122,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","72187","Namur - Antwerpen","< >","MECHELEN","Y.LEUVEN-BUNDEL M",2025,2025,2,2,"2025-01-06",45644.975694444445,"2025-01-11",45644.208333333336,"5d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,72187,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","71328","Athus - Meuse",">","SIGNEULX","HALANZY",2025,2025,2,2,"2025-01-07",45644.333333333336,"2025-01-07",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71328,"2024-08-30",0,"1,2,3,4,5"]
[null,"Infrabel","71134","Athus - Meuse",">","PALISEUL","GEDINNE",2025,2025,2,2,"2025-01-07",45644.333333333336,"2025-01-07",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,71134,"2024-08-30",0,"1,2,3,4,5"]
[null,"Infrabel","73960","Namur - Antwerpen",">","Y.OOST DRIEHOEK LEDEBERG","Y.WEST DRIEHOEK LEDEBERG",2025,2025,2,2,"2025-01-07",45644.027777777781,"2025-01-11",45644.194444444445,"5d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"reservatie onderhoud \r\nSchets DOES 4\r\nL50E SP B 01XR inbegrepen tot 05O inbegrepen\r\nL58/1 SP B 05O inbegrepen tot 10XO inbegrepen\r\nL58(1) SP A 10XO inbegrepen tot 01XR inbegrepen\r\nTCR501982",null,null,73960,"2024-07-17",0,"1,2,3,4,5"]
[null,"Infrabel","69916","Lille - Charleroi","< >","Y.JURBISE","MONS",2025,2025,2,2,"2025-01-07",45644.034722222219,"2025-01-11",45644.177083333336,"5d, 03:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Balises installation and/or download, meewerken IS mogelijk\r\nETCS L2-IL_SO_P036_L96_L97_Jurbise –  Mons – Saint Ghislain_ETCS",null,null,69916,"2024-08-13",0,"1,2,3,4,5"]
[null,"Infrabel","71432","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,2,2,"2025-01-07",45644.375,"2025-01-07",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,71432,"2024-09-03",0,"1,2,3,4,5"]
[null,"Infrabel","71343","Athus - Meuse",">","STOCKEM-NORD","ARLON",2025,2025,2,2,"2025-01-07",45644.361111111109,"2025-01-07",45644.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,71343,"2024-08-30",0,"1,2,3,4,5"]
[null,"Infrabel","71329","Athus - Meuse",">","HALANZY","SIGNEULX",2025,2025,2,2,"2025-01-08",45644.333333333336,"2025-01-08",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie  B",null,null,71329,"2024-08-30",0,"1,2,3,4,5"]
[null,"Infrabel","71433","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,2,2,"2025-01-08",45644.375,"2025-01-08",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,71433,"2024-09-03",0,"1,2,3,4,5"]
[null,"Infrabel","71342","Athus - Meuse",">","HABAY","STOCKEM-NORD",2025,2025,2,2,"2025-01-08",45644.375,"2025-01-08",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,71342,"2024-08-30",0,"1,2,3,4,5"]
[null,"Infrabel","71136","Athus - Meuse",">","PALISEUL","BERTRIX",2025,2025,2,2,"2025-01-09",45644.333333333336,"2025-01-09",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,71136,"2024-08-30",0,"1,2,3,4,5"]
[null,"Infrabel","71434","Athus - Meuse",">","YVOIR","DINANT",2025,2025,2,2,"2025-01-09",45644.385416666664,"2025-01-09",45644.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,71434,"2024-09-03",0,"1,2,3,4,5"]
[null,"Infrabel","67453","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,2,2,"2025-01-09",45644.395833333336,"2025-01-09",45644.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nVisite diagnostique\r\nMise HS en P2\r\nTCR 488827",null,null,67453,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","71138","Athus - Meuse",">","BERTRIX","PALISEUL",2025,2025,2,2,"2025-01-10",45644.333333333336,"2025-01-10",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,71138,"2024-08-30",0,"1,2,3,4,5"]
[null,"Infrabel","71435","Athus - Meuse",">","DINANT","YVOIR",2025,2025,2,2,"2025-01-10",45644.385416666664,"2025-01-10",45644.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,71435,"2024-09-03",0,"1,2,3,4,5"]
[null,"Infrabel","73598","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,2,3,"2025-01-10",45644.923611111109,"2025-01-13",45644.194444444445,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-015 validé\r\nMise en service PLP de la loge 96-643 nécessaire pour la transition ETCS 2FS\r\nInclus les travaux TUC et cellule ETCS\r\nUPM: 485822",null,null,73598,"2024-08-13",1,"5,6"]
[null,"Infrabel","71318","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2025,2025,2,2,"2025-01-11",45644.333333333336,"2025-01-11",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71318,"2024-08-30",0,"5,6"]
[null,"Infrabel","66493","Namur - Antwerpen",">","Y.FLAWINNE","AUVELAIS",2025,2025,2,2,"2025-01-11",45644.333333333336,"2025-01-11",45644.6875,"1d, 08:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130 Y-Flawinne - Moustier VA\r\nUPM: 488983",null,null,66493,"2024-09-16",0,"5,6"]
[null,"Infrabel","75215","Lille - Antwerpen",">","LOKEREN","OOSTAKKER",2025,2025,2,2,"2025-01-11",45644.020833333336,"2025-01-11",45644.229166666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\nTCR500284",null,null,75215,"2024-07-17",0,"1,2,3,4,5"]
[null,"Infrabel","75030","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,2,3,"2025-01-11",45644.020833333336,"2025-01-13",45644.1875,"3d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Migratie tunnelveiligheidstechnieken Antw. NZ -2\r\nAntwerpen-Centraal - Antwerpen-Luchtbal",null,null,75030,"2024-01-31",0,"5,6"]
[null,"Infrabel","65513","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2025,2025,2,2,"2025-01-11",45644.986111111109,"2025-01-12",45644.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\nUPM: 489069",null,null,65513,"2024-10-08",1,"5,6"]
[null,"Infrabel","59468","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,2,3,"2025-01-11",45644.986111111109,"2025-01-13",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nPose portiques Moustier- Auvelais\r\nUPM: 489224",null,null,59468,"2024-09-03",0,"5,6"]
[null,"Infrabel","68841","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,2,2,"2025-01-11",45644.3125,"2025-01-11",45644.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,68841,"2024-08-28",0,"5,6"]
[null,"Infrabel","67117","Namur - Antwerpen",">","AUVELAIS","Y.FLAWINNE",2025,2025,2,2,"2025-01-12",45644.333333333336,"2025-01-12",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130 Auvelais-Y.Flawinne VB\r\nUPM: 489081",null,null,67117,"2024-09-03",0,"5,6"]
[null,"Infrabel","71320","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2025,2025,2,2,"2025-01-12",45644.333333333336,"2025-01-12",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,71320,"2024-08-30",0,"5,6"]
[null,"Infrabel","75216","Lille - Antwerpen","< >","SINT-NIKLAAS","OOSTAKKER",2025,2025,2,2,"2025-01-12",45644.020833333336,"2025-01-12",45644.225694444445,"1d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud\r\nTCR500338",null,null,75216,"2024-07-17",0,"5,6"]
[null,"Infrabel","67314","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ANTWERPEN-D.S.-RHODESIE",2025,2025,2,2,"2025-01-12",45644.25,"2025-01-12",45644.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,67314,"2024-03-27",1,"5,6"]
[null,"Infrabel","70130","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,2,2,"2025-01-12",45644.3125,"2025-01-12",45644.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,70130,"2024-08-29",0,"5,6"]
[null,"Infrabel","79453","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2025,2025,2,2,"2025-01-12",45644.083333333336,"2025-01-12",45644.125,"1d, 01:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-020\r\nEBP herlading zone Leuven\r\nIndienstname PLP Keet H3\r\nR-510963",null,null,79453,"2024-08-30",0,"5,6"]
[null,"Infrabel","72038","Lille - Charleroi","< >","QUEVY-FRONTIERE","TUBIZE",2025,2025,2,2,"2025-01-12",45644.083333333336,"2025-01-12",45644.145833333336,"1d, 01:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rechargement EBP/PLP pour MES SIW L96 Mons-Quévy",null,null,72038,"2024-08-13",0,"5,6"]
[null,"Infrabel","70834","Namur - Antwerpen","< >","NAMUR","RONET",2025,2025,2,2,"2025-01-12",45644.003472222219,"2025-01-12",45644.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur ZONE 6\r\nZ6.43\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,70834,"2024-09-04",0,"5,6"]
[null,"Infrabel","47153","Namur - Antwerpen",">","HAM-SUR-SAMBRE","AUVELAIS",2025,2025,3,3,"2025-01-13",45644.979166666664,"2025-01-18",45644.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"électrification gare Jemeppe-sur-Sambre \r\nmassifs",null,null,47153,"2024-09-09",0,"1,2,3,4,5"]
[null,"Infrabel","59308","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,3,3,"2025-01-13",45644.979166666664,"2025-01-18",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe",null,null,59308,"2023-03-28",0,"1,2,3,4,5"]
[null,"Infrabel","78889","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,3,3,"2025-01-13",45644.972222222219,"2025-01-17",45644.201388888891,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-078\r\nR-507751-xx\r\nSaneren vormlaag",null,null,78889,"2024-09-16",0,"1,2,3,4,5"]
[null,"Infrabel","67866","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET",2025,2025,3,3,"2025-01-13",45644.965277777781,"2025-01-18",45644.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nCR2025_046: faisceau C_voie 352 inaccessible (les aiguillages du faisceau C côté Charleroi sont disponibles via la voie II de Châtelet)\r\nTCR: 490372",null,null,67866,"2024-09-11",0,"1,2,3,4,5"]
[null,"Infrabel","66520","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2025,2025,3,3,"2025-01-13",45644.944444444445,"2025-01-17",45644.173611111109,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.54\r\n+ Maintenance Z7.54 P3 HKM",null,null,66520,"2024-08-13",0,"1,2,3,4,5"]
[null,"Infrabel","72701","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","BAKENBOS",2025,2025,3,3,"2025-01-13",45644.996527777781,"2025-01-18",45644.201388888891,"5d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_05 Area CE volgens onderhoudskalender 2025.\r\nBuitendienststelling L161 tussen Bru Luxemburg en Bakenbos voor onderhoudswerken + L161A.",null,null,72701,"2024-08-28",0,"1,2,3,4,5"]
[null,"Infrabel","68789","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,3,3,"2025-01-13",45644.993055555555,"2025-01-17",45644.177083333336,"4d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n1- Réalisation de massifs et pose de poteaux\r\nUPM: 487885",null,null,68789,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","71860","Namur - Antwerpen","< >","LONDERZEEL","Y.HEIKE",2025,2025,3,3,"2025-01-13",45644.993055555555,"2025-01-18",45644.211805555555,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71860,"2024-04-11",0,"1,2,3,4,5"]
[null,"Infrabel","71874","Namur - Antwerpen","< >","Y.HEIKE","MECHELEN",2025,2025,3,3,"2025-01-13",45644.993055555555,"2025-01-18",45644.211805555555,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71874,"2024-04-11",0,"1,2,3,4,5"]
[null,"Infrabel","73086","Lille - ZeeBrugge","< >","LICHTERVELDE","KORTRIJK",2025,2025,3,3,"2025-01-13",45644.961805555555,"2025-01-18",45644.166666666664,"5d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud zone 04.35 HKV\r\nL66/1 volledig inbegrepen \r\nL75 C SP B van LK tot Y Bethune AW20E/19AE vrij\r\nL66 LK tot FLC SP III-IV-V + DSP 736 inbegrepen \r\nL69 TLO Y LK West tot FME SP II inbegrepen\r\nL69 DOES SP B FME SP II inbegrepen tot FOI AW 31N vrij\r\n",null,null,73086,"2024-08-05",0,"1,2,3,4,5"]
[null,"Infrabel","65817","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,3,3,"2025-01-13",45644.923611111109,"2025-01-18",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.51 P3 HKV",null,null,65817,"2024-08-14",0,"1,2,3,4,5"]
[null,"Infrabel","71436","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2025,2025,3,3,"2025-01-13",45644.388888888891,"2025-01-13",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA (périodicité 3 semaines)",null,null,71436,"2024-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","71345","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2025,2025,3,3,"2025-01-13",45644.409722222219,"2025-01-13",45644.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,71345,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","71312","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2025,2025,3,3,"2025-01-14",45644.333333333336,"2025-01-14",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,71312,"2024-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","68062","Namur - Antwerpen","< >","DENDERMONDE","Y.HEIKE",2025,2025,3,3,"2025-01-14",45644.006944444445,"2025-01-17",45644.201388888891,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P208 Waterhuishouding\r\n+\r\nP221 goederencorridors\r\n+\r\nOnderhoud\r\n\r\nFDR SP III-IV in\r\nY Heike niet in\r\n\r\nR5/R6 in WE TLO\r\n\r\nTCR499279",null,null,68062,"2024-06-06",0,"1,2,3,4,5"]
[null,"Infrabel","72705","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,3,3,"2025-01-14",45644.003472222219,"2025-01-18",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72705,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","71437","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2025,2025,3,3,"2025-01-14",45644.34375,"2025-01-14",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,71437,"2024-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","70486","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,3,3,"2025-01-15",45644.375,"2025-01-15",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y-Holland",null,null,70486,"2024-02-14",0,"1,2,3,4,5"]
[null,"Infrabel","71146","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2025,2025,3,3,"2025-01-15",45644.378472222219,"2025-01-15",45644.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,71146,"2024-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","71339","Athus - Meuse",">","LAVAUX","MARBEHAN",2025,2025,3,3,"2025-01-15",45644.361111111109,"2025-01-15",45644.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,71339,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","71441","Athus - Meuse",">","DINANT","Y.NEFFE",2025,2025,3,3,"2025-01-15",45644.34375,"2025-01-15",45644.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites VA",null,null,71441,"2024-09-09",0,"1,2,3,4,5"]
[null,"Infrabel","71314","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,3,3,"2025-01-16",45644.333333333336,"2025-01-16",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71314,"2024-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","71340","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2025,2025,3,3,"2025-01-16",45644.368055555555,"2025-01-16",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,71340,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","70613","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2025,2025,3,3,"2025-01-16",45644.375,"2025-01-16",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen - Schijnpoort + inrit bundel Q",null,null,70613,"2024-03-13",0,"1,2,3,4,5"]
[null,"Infrabel","71438","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2025,2025,3,3,"2025-01-16",45644.388888888891,"2025-01-16",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA (périodicité 3 semaines)",null,null,71438,"2024-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","70833","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,3,3,"2025-01-17",45644.958333333336,"2025-01-18",45644.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nZ5.43",null,null,70833,"2024-09-23",0,"1,2,3,4,5"]
[null,"Infrabel","71316","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2025,2025,3,3,"2025-01-17",45644.333333333336,"2025-01-17",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,71316,"2024-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","78892","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,3,4,"2025-01-17",45644.972222222219,"2025-01-20",45644.201388888891,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-078\r\nR-507998-xx\r\nSaneren vormlaag",null,null,78892,"2024-09-16",1,"5,6"]
[null,"Infrabel","78199","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2025,2025,3,4,"2025-01-17",45644.989583333336,"2025-01-20",45644.229166666664,"2d, 05:45h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-075 : Travaux RER\r\n\r\nUPM: 505514",null,null,78199,"2024-09-09",0,"5,6"]
[null,"Infrabel","66509","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,3,4,"2025-01-17",45644.993055555555,"2025-01-20",45644.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification OA + AI44 \r\nAI44: Intervention PN + Entretien divers\r\nOA; Mise au gabarit des pistes Namur Rhisnes parois rocheuses\r\n+ Visite de voies Gembloux / Rhisnes + maintenance infrastructure + contrôles\r\n+ Déroulage caténaires en voie B \r\nUPM: 487",null,null,66509,"2024-12-03",1,"5,6"]
[null,"Infrabel","71338","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2025,2025,3,3,"2025-01-17",45644.368055555555,"2025-01-17",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,71338,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","70626","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,3,3,"2025-01-17",45644.375,"2025-01-17",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y Holland + inrit bundel Q",null,null,70626,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","71439","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2025,2025,3,3,"2025-01-17",45644.388888888891,"2025-01-17",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,71439,"2024-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","75031","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,3,4,"2025-01-18",45644.020833333336,"2025-01-20",45644.1875,"3d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Migratie tunnelveiligheidstechnieken Antw. NZ -2\r\nAntwerpen-Centraal - Antwerpen-Luchtbal",null,null,75031,"2024-01-31",0,"5,6"]
[null,"Infrabel","66545","Namur - Antwerpen","< >","DENDERMONDE","Y.HEIKE",2025,2025,3,4,"2025-01-18",45644.013888888891,"2025-01-20",45644.1875,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"P208 waterhuishouding\r\n+\r\nP221 goederencorridors\r\n+\r\nOnderhoud\r\nTCR 492725",null,null,66545,"2024-05-31",1,"5,6"]
[null,"Infrabel","69985","Namur - Antwerpen","< >","MECHELEN","Y.HEIKE",2025,2025,3,4,"2025-01-18",45644.013888888891,"2025-01-20",45644.1875,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Kleine vernieuwingswerken + onderhoud",null,null,69985,"2024-10-18",1,"5,6"]
[null,"Infrabel","59470","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER-GARAGE",2025,2025,3,4,"2025-01-18",45644.986111111109,"2025-01-20",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nPose portiques Moustier Garage- Auvelais\r\nUPM: 489227",null,null,59470,"2024-09-09",0,"5,6"]
[null,"Infrabel","65775","Lille - Charleroi","< >","LEMBEEK","BRAINE-LE-COMTE",2025,2025,3,3,"2025-01-18",45644.260416666664,"2025-01-19",45644.666666666664,"1d, 09:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.53 en P4\r\nTCR 488833",null,null,65775,"2024-09-10",1,"5,6"]
[null,"Infrabel","71430","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,3,3,"2025-01-18",45644.385416666664,"2025-01-18",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,71430,"2024-09-09",0,"5,6"]
[null,"Infrabel","71344","Athus - Meuse",">","ARLON","Y.AUTELBAS",2025,2025,3,3,"2025-01-18",45644.361111111109,"2025-01-18",45644.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,71344,"2024-09-05",0,"5,6"]
[null,"Infrabel","66197","Lille - Charleroi",">","LUTTRE","ROUX",2025,2025,3,3,"2025-01-18",45644.263888888891,"2025-01-19",45644.708333333336,"1d, 10:40h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance Z05.52 P4\r\nTCR 487862",null,null,66197,"2024-08-12",0,"5,6"]
[null,"Infrabel","59312","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,3,3,"2025-01-19",45644.034722222219,"2025-01-19",45644.21875,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nTLO L 50 tussen Gent Sint Pieters en Y. West Driehoek Le",null,null,59312,"2023-06-28",0,"5,6"]
[null,"Infrabel","68035","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,3,3,"2025-01-19",45644.034722222219,"2025-01-19",45644.243055555555,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68035,"2024-02-23",0,"5,6"]
[null,"Infrabel","71431","Athus - Meuse",">","LUSTIN","JAMBES",2025,2025,3,3,"2025-01-19",45644.385416666664,"2025-01-19",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,71431,"2024-09-09",0,"5,6"]
[null,"Infrabel","71341","Athus - Meuse",">","MARBEHAN","HABAY",2025,2025,3,3,"2025-01-19",45644.375,"2025-01-19",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,71341,"2024-09-05",0,"5,6"]
[null,"Infrabel","79275","Athus - Meuse",">","HAVERSIN","MARLOIE",2025,2025,3,3,"2025-01-19",45644.364583333336,"2025-01-19",45644.666666666664,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-085 \r\nVisite périodique de jour le dimanche pour AI45. (suite mise en service ETCS)\r\nVA: Le dimanche entre 08h45 et 16h00\r\nVB: Le dimanche entre 08h00 et 15h15\r\nA dupliquer toutes les 8 semaines.\r\nTCR 510716",null,null,79275,"2024-10-14",0,"5,6"]
[null,"Infrabel","70071","Erquelinnes - Montzen","< >","Y.VAL-BENOIT","Y.RENORY",2025,2025,4,4,"2025-01-20",45644.958333333336,"2025-01-24",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Z21.41 - P3 maintenance AI41",null,null,70071,"2024-09-04",0,"1,2,3,4,5"]
[null,"Infrabel","71141","Athus - Meuse",">","BERTRIX","STRAIMONT",2025,2025,4,4,"2025-01-20",45644.333333333336,"2025-01-20",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,71141,"2024-09-11",0,"1,2,3,4,5"]
[null,"Infrabel","59309","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,4,4,"2025-01-20",45644.979166666664,"2025-01-25",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe",null,null,59309,"2023-02-15",0,"1,2,3,4,5"]
[null,"Infrabel","78890","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,4,4,"2025-01-20",45644.972222222219,"2025-01-24",45644.201388888891,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-078\r\nR-507996-xx\r\nSaneren vormlaag",null,null,78890,"2024-09-16",0,"1,2,3,4,5"]
[null,"Infrabel","55902","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2025,2025,4,4,"2025-01-20",45644.965277777781,"2025-01-24",45644.208333333336,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Semaines de nuits de préparations - démolition 85.708\r\n+ Réélectrification L130\r\n+ Maintenance Z15. 51\r\nP3 HKV \r\nTronçon Allongé 6h\r\nTCR: 491334",null,null,55902,"2024-08-14",0,"1,2,3,4,5"]
[null,"Infrabel","53504","Lille - Charleroi","< >","JURBISE","ATH",2025,2025,4,4,"2025-01-20",45644.944444444445,"2025-01-24",45644.222222222219,"4d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.54 + Z7.53 P3 HKM",null,null,53504,"2024-08-13",0,"1,2,3,4,5"]
[null,"Infrabel","71233","Erquelinnes - Montzen","< >","HUY","NAMUR",2025,2025,4,4,"2025-01-20",45644.993055555555,"2025-01-24",45644.190972222219,"4d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.43 HKV\r\n",null,null,71233,"2024-09-12",0,"1,2,3,4,5"]
[null,"Infrabel","68790","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,4,4,"2025-01-20",45644.993055555555,"2025-01-25",45644.215277777781,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n1- Réalisation de massifs et pose de poteaux\r\nUPM: 487888",null,null,68790,"2024-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","71866","Namur - Antwerpen","< >","LONDERZEEL","Y.HEIKE",2025,2025,4,4,"2025-01-20",45644.993055555555,"2025-01-25",45644.211805555555,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71866,"2024-04-11",0,"1,2,3,4,5"]
[null,"Infrabel","71875","Namur - Antwerpen","< >","Y.HEIKE","MECHELEN",2025,2025,4,4,"2025-01-20",45644.993055555555,"2025-01-25",45644.211805555555,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71875,"2024-04-11",0,"1,2,3,4,5"]
[null,"Infrabel","68036","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,4,4,"2025-01-20",45644.034722222219,"2025-01-20",45644.201388888891,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68036,"2024-02-23",0,"5,6"]
[null,"Infrabel","53496","Lille - Charleroi","< >","Y.JURBISE","MONS",2025,2025,4,4,"2025-01-20",45644.947916666664,"2025-01-24",45644.173611111109,"4d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.53 P3 HKV\r\n+ ETCS L2-IL_SO_P036_L96_L97_Jurbise –  Mons – Saint Ghislain_ETCS\r\n Balises installation and/or download, meewerken IS mogelijk",null,null,53496,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","71704","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,4,4,"2025-01-20",45644.361111111109,"2025-01-20",45644.645833333336,"1d, 06:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance\r\nTCR 507124",null,null,71704,"2024-09-12",0,"1,2,3,4,5"]
[null,"Infrabel","74218","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,4,4,"2025-01-20",45644.354166666664,"2025-01-21",45644.645833333336,"2d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud + schouwen - TCR 498781\r\n\r\nSP A BD + perronspoor I\r\n",null,null,74218,"2024-07-24",0,"1,2,3,4,5"]
[null,"Infrabel","71443","Athus - Meuse",">","HOUYET","BEAURAING",2025,2025,4,4,"2025-01-20",45644.388888888891,"2025-01-20",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA (périodicité 3 semaines)",null,null,71443,"2024-09-11",0,"1,2,3,4,5"]
[null,"Infrabel","67486","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2025,2025,4,4,"2025-01-20",45644.381944444445,"2025-01-20",45644.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41",null,null,67486,"2024-09-09",0,"1,2,3,4,5"]
[null,"Infrabel","68063","Namur - Antwerpen","< >","DENDERMONDE","Y.HEIKE",2025,2025,4,4,"2025-01-21",45644.006944444445,"2025-01-25",45644.201388888891,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P208 Waterhuishouding\r\n+\r\nP221 goederencorridors\r\n+\r\nOnderhoud\r\n\r\nFDR SP III-IV in\r\nY Heike niet in\r\nTCR499280",null,null,68063,"2024-06-06",0,"1,2,3,4,5"]
[null,"Infrabel","67885","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,4,4,"2025-01-21",45644.020833333336,"2025-01-25",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67885,"2024-08-13",0,"1,2,3,4,5"]
[null,"Infrabel","68223","Lille - Antwerpen","< >","DEINZE","KORTRIJK",2025,2025,4,4,"2025-01-21",45644.013888888891,"2025-01-24",45644.173611111109,"4d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken en kleine vernieuwingswerken\r\n\r\nFD SP I-II inbegrepen\r\nLK rooster kant Gent inbegrepen\r\n\r\naangepast na overleg met I-O zie mail Edwin op 06/06/2024\r\n\r\nTCR503253",null,null,68223,"2024-06-06",0,"1,2,3,4,5"]
[null,"Infrabel","70565","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,4,4,"2025-01-21",45644.986111111109,"2025-01-23",45644.236111111109,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen van Y Arendstraat",null,null,70565,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","69917","Lille - Charleroi","< >","MONS","QUEVY",2025,2025,4,4,"2025-01-21",45644.041666666664,"2025-01-24",45644.180555555555,"4d, 03:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Balises installation and/or download, meewerken IS mogelijk\r\nETCS L2-IL_SO_P036_L96_L97_Jurbise –  Mons – Saint Ghislain_ETCS",null,null,69917,"2024-09-02",0,"1,2,3,4,5"]
[null,"Infrabel","70575","Namur - Antwerpen","< >","Y.BERCHEM-STADION","Y.ARENDSTRAAT",2025,2025,4,4,"2025-01-21",45644.083333333336,"2025-01-23",45644.125,"3d, 01:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen van Y Noord Berchem",null,null,70575,"2024-06-26",0,"1,2,3,4,5"]
[null,"Infrabel","72706","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,4,4,"2025-01-21",45644.003472222219,"2025-01-25",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72706,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","71143","Athus - Meuse",">","STRAIMONT","BERTRIX",2025,2025,4,4,"2025-01-21",45644.375,"2025-01-21",45644.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,71143,"2024-09-11",0,"1,2,3,4,5"]
[null,"Infrabel","71444","Athus - Meuse",">","BEAURAING","HOUYET",2025,2025,4,4,"2025-01-21",45644.388888888891,"2025-01-21",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,71444,"2024-09-11",0,"1,2,3,4,5"]
[null,"Infrabel","71331","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,4,4,"2025-01-22",45644.333333333336,"2025-01-22",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71331,"2024-09-11",0,"1,2,3,4,5"]
[null,"Infrabel","74219","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,4,4,"2025-01-22",45644.354166666664,"2025-01-23",45644.645833333336,"2d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud + schouwen\r\n\r\nSP B BD + perronspoor II\r\n\r\nPerronspoor III tot VII + bundel M ontoegankelijk\r\nTCR499717",null,null,74219,"2024-06-06",0,"1,2,3,4,5"]
[null,"Infrabel","72272","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,4,4,"2025-01-23",45644.958333333336,"2025-01-25",45644.208333333336,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Déchargement de rails avec train Robel \r\nAvec quai de la voie II de Visé compris dans la coupure la seconde nuit",null,null,72272,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","73097","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,4,4,"2025-01-23",45644.333333333336,"2025-01-23",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73097,"2024-09-11",0,"1,2,3,4,5"]
[null,"Infrabel","56545","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,4,5,"2025-01-24",45644.958333333336,"2025-01-27",45644.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation\r\nTCR 487610",null,null,56545,"2024-08-14",1,"5,6"]
[null,"Infrabel","78893","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,4,5,"2025-01-24",45644.972222222219,"2025-01-27",45644.201388888891,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-078\r\nR-508001-xx\r\nSaneren vormlaag",null,null,78893,"2024-09-16",1,"5,6"]
[null,"Infrabel","70698","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2025,2025,4,4,"2025-01-24",45644.013888888891,"2025-01-25",45644.194444444445,"2d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen\r\nHKM\r\nZ23.22.01",null,null,70698,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","66512","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2025,2025,4,5,"2025-01-25",45644.25,"2025-01-27",45644.25,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Intervention PN + Entretien divers\r\n+ Remplacement CV(50Hz) par CV Jade entre Jemeppe-Sur-Sambre Sg G-Q.30 et L130/1 Sg NY-Q.30\r\nUPM: 488636",null,null,66512,"2024-09-12",1,"5,6"]
[null,"Infrabel","74098","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2025,2025,4,4,"2025-01-25",45644.996527777781,"2025-01-26",45644.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B - TCR 495735",null,null,74098,"2024-06-10",0,"5,6"]
[null,"Infrabel","70473","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2025,2025,4,4,"2025-01-25",45644.326388888891,"2025-01-25",45644.722222222219,"1d, 09:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen Oost - Antwerpen - Schijnpoort",null,null,70473,"2024-02-14",0,"5,6"]
[null,"Infrabel","67499","Erquelinnes - Montzen",">","AMAY","ENGIS",2025,2025,4,4,"2025-01-25",45644.340277777781,"2025-01-25",45644.652777777781,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,67499,"2024-09-09",0,"1,2,3,4,5"]
[null,"Infrabel","68894","Namur - Antwerpen","< >","Y.SCHIJN","ANTWERPEN-D.S.-RHODESIE",2025,2025,4,4,"2025-01-26",45644.25,"2025-01-26",45644.729166666664,"1d, 11:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Slijpwerken met SPENO op spoor A \r\n(planning per mail gekregen op 28/04/2023 van De Kempeneer David)",null,null,68894,"2024-06-26",0,"5,6"]
[null,"Infrabel","79722","Lille - Antwerpen","< >","MELSELE-ROOSTER O/Q","GENT-DAMPOORT",2025,2025,4,4,"2025-01-26",45644.041666666664,"2025-01-26",45644.145833333336,"1d, 02:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-106\r\nR-512890\r\n\r\nEBP - Hardware Equipment Maintenance : \"Renewal Network Devices\". Buitendienst van seinpost (Computer Room) en de EBP gekoppelde zone tijdens 02u30 voor werken \"Renewal of Network Device\". Uurregelingen zijn aanpasbaar tussen 00",null,null,79722,"2024-09-12",0,"5,6"]
[null,"Infrabel","59313","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,4,4,"2025-01-26",45644.034722222219,"2025-01-26",45644.21875,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nTLO L 50 tussen Gent Sint Pieters en Y. West Driehoek Le",null,null,59313,"2023-06-28",0,"5,6"]
[null,"Infrabel","67492","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2025,2025,4,4,"2025-01-26",45644.354166666664,"2025-01-26",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,67492,"2024-09-12",0,"5,6"]
[null,"Infrabel","70880","Namur - Antwerpen","< >","Y.HEIKE","DENDERMONDE",2025,2025,5,5,"2025-01-27",45644.958333333336,"2025-01-31",45644.204861111109,"4d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z79.33 - TCR 499289\r\nFDR SPIII-IV tot FM SP III inbegrepen\r\nR5/R6 niet inbegrepen, voorkeur voor P- Werf",null,null,70880,"2024-08-19",0,"1,2,3,4,5"]
[null,"Infrabel","63156","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,5,5,"2025-01-27",45644.958333333336,"2025-02-01",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,63156,"2024-09-16",0,"1,2,3,4,5"]
[null,"Infrabel","71753","Namur - Antwerpen",">","NAMUR","Y.FLAWINNE",2025,2025,5,5,"2025-01-27",45644.333333333336,"2025-01-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nUPM 507449",null,null,71753,"2024-09-16",0,"1,2,3,4,5"]
[null,"Infrabel","81786","Lille - Charleroi","< >","BRUGELETTE","JURBISE",2025,2025,5,5,"2025-01-27",45644.979166666664,"2025-01-31",45644.166666666664,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS - TEST L96 - 90C ",null,null,81786,"2024-11-04",0,"1,2,3,4,5"]
[null,"Infrabel","70546","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.ARENDSTRAAT",2025,2025,5,5,"2025-01-27",45644.979166666664,"2025-02-01",45644.1875,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud wissels Y Noord Berchem\r\nHKV",null,null,70546,"2024-01-29",0,"1,2,3,4,5"]
[null,"Infrabel","74921","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE-WIJKSPOREN",2025,2025,5,5,"2025-01-27",45644.979166666664,"2025-02-01",45644.1875,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud FGSP Nacht: Werkveld 4.1 + werkveld 4.2 - TCR 503301\r\n\r\nL86 tot uitritseinen De Pinte (kant FGSP)\r\n\r\nPerronsporen III tem IX buitendienst.",null,null,74921,"2024-06-10",0,"1,2,3,4,5"]
[null,"Infrabel","59310","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,5,5,"2025-01-27",45644.979166666664,"2025-02-01",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\n Spoor B L 50 tussen Gent Sint Pieters en Y. West Drieho",null,null,59310,"2023-01-30",0,"1,2,3,4,5"]
[null,"Infrabel","78891","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,5,5,"2025-01-27",45644.972222222219,"2025-02-01",45644.201388888891,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-078\r\nR-507997-xx\r\nSaneren vormlaag",null,null,78891,"2024-09-16",0,"1,2,3,4,5"]
[null,"Infrabel","67746","Lille - Antwerpen","< >","DEINZE","KORTRIJK",2025,2025,5,5,"2025-01-27",45644.972222222219,"2025-02-01",45644.173611111109,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken en kleine vernieuwingswerken - TCR 503257\r\n\r\nFD SP I-II inbegrepen\r\nLK rooster kant Gent inbegrepen",null,null,67746,"2024-06-10",0,"1,2,3,4,5"]
[null,"Infrabel","55905","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2025,2025,5,5,"2025-01-27",45644.965277777781,"2025-01-31",45644.208333333336,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Semaines de nuits de préparations - démolition 85.708\r\n+ Réélectrification L130\r\n+ Maintenance Z15. 51\r\nP3 HKV \r\nTronçon Allongé 6h\r\nTCR: 492065",null,null,55905,"2024-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","68710","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2025,2025,5,5,"2025-01-27",45644.965277777781,"2025-01-31",45644.197916666664,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons\r\nZ9.41 + L.125/1\r\n+ voies 834 et 835 de Flémalle-Haute",null,null,68710,"2024-09-11",0,"1,2,3,4,5"]
[null,"Infrabel","59699","Lille - Charleroi","< >","BRUXELLES-MIDI","Y.RUISBROEK",2025,2025,5,5,"2025-01-27",45644.986111111109,"2025-01-31",45644.1875,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen aw 37AJ/46BJ: voorbereidende werken\r\nFBMZ sp 17-18 tot Y Ruisbroek\r\nTijdens de nachten uitbreiding naar L124 en bundel Charleroi",null,null,59699,"2023-12-22",0,"1,2,3,4,5"]
[null,"Infrabel","68791","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,5,5,"2025-01-27",45644.993055555555,"2025-02-01",45644.215277777781,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n1- Réalisation de massifs et pose de poteaux\r\nUPM: 487889",null,null,68791,"2024-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","53492","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2025,2025,5,5,"2025-01-27",45644.954861111109,"2025-02-01",45644.180555555555,"5d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 + Z2.53 en P3 HKV",null,null,53492,"2024-08-13",0,"1,2,3,4,5"]
[null,"Infrabel","71743","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2025,2025,5,5,"2025-01-27",45644.368055555555,"2025-01-27",45644.638888888891,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 116 à 119 \r\nNe fonctionne plus en Phase 5\r\nTCR 507077",null,null,71743,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","71660","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2025,2025,5,5,"2025-01-27",45644.947916666664,"2025-02-01",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 05.32 - TCR 500403\r\nL58 Eeklo inbegrepen tot Gent Dampoort NIET inbegrepen",null,null,71660,"2024-08-05",0,"1,2,3,4,5"]
[null,"Infrabel","75385","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,5,5,"2025-01-27",45644.395833333336,"2025-01-27",45644.645833333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"DOES Schouwen sporen overdag. - TCR 510838",null,null,75385,"2024-06-10",0,"1,2,3,4,5"]
[null,"Infrabel","53239","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,5,5,"2025-01-27",45644.923611111109,"2025-02-01",45644.194444444445,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Quévy\r\nTravaux préparatoires - déchargement LRS\r\n+ ETCS L2-IL_SO_P036_L96_L97_Jurbise –  Mons – Saint Ghislain_ETCS\r\nBalises installation and/or download, meewerken IS mogelijk\r\nTCR 488640",null,null,53239,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","67886","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,5,5,"2025-01-28",45644.020833333336,"2025-02-01",45644.180555555555,"5d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67886,"2024-08-13",0,"1,2,3,4,5"]
[null,"Infrabel","72707","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,5,5,"2025-01-28",45644.003472222219,"2025-02-01",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72707,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","71187","Erquelinnes - Montzen",">","JAVA","STATTE",2025,2025,5,5,"2025-01-29",45644.354166666664,"2025-01-29",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71187,"2024-09-12",0,"1,2,3,4,5"]
[null,"Infrabel","70819","Erquelinnes - Montzen",">","JAVA","ANDENNE",2025,2025,5,5,"2025-01-30",45644.5625,"2025-01-30",45644.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70819,"2024-09-16",0,"1,2,3,4,5"]
[null,"Infrabel","70820","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2025,2025,5,5,"2025-01-30",45644.375,"2025-01-30",45644.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70820,"2024-09-16",0,"1,2,3,4,5"]
[null,"Infrabel","59697","Lille - Charleroi","< >","BRUXELLES-MIDI","Y.RUISBROEK",2025,2025,5,6,"2025-01-31",45644.993055555555,"2025-02-03",45644.1875,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen aw 37AJ/46BJ\r\nFBMZ sp 17-18 tot Y Ruisbroek\r\nTijdens de nachten uitbreiding naar L124 en bundel Charleroi",null,null,59697,"2024-10-17",1,"5,6"]
[null,"Infrabel","72253","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,5,6,"2025-02-01",45644.979166666664,"2025-02-03",45644.166666666664,"1d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug  L15 km 6.027 BX L15 en L27A\r\n\r\nalternatief voor geweigerde L15+L27A",null,null,72253,"2024-03-11",1,"5,6"]
[null,"Infrabel","70821","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2025,2025,5,5,"2025-02-01",45644.354166666664,"2025-02-01",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70821,"2024-09-16",0,"5,6"]
[null,"Infrabel","66477","Namur - Antwerpen",">","Y.LOUVAIN-LA-NEUVE","GEMBLOUX",2025,2025,5,5,"2025-02-01",45644.354166666664,"2025-02-01",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie A : Y-Louvain La Neuve - Gembloux\r\nUPM: 488024",null,null,66477,"2024-09-17",0,"5,6"]
[null,"Infrabel","75329","Lille - Charleroi",">","BRAINE-LE-COMTE","SOIGNIES",2025,2025,5,5,"2025-02-01",45644.541666666664,"2025-02-01",45644.59375,"1d, 01:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA",null,null,75329,"2024-08-13",0,"5,6"]
[null,"Infrabel","66494","Namur - Antwerpen",">","OTTIGNIES","WAVRE",2025,2025,5,5,"2025-02-01",45644.326388888891,"2025-02-01",45644.652777777781,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Ottignies - Wavre \r\nUPM: 488493",null,null,66494,"2024-09-17",0,"5,6"]
[null,"Infrabel","75989","Lille - Charleroi",">","BRAINE-LE-COMTE","Y.FELUY",2025,2025,5,5,"2025-02-01",45644.34375,"2025-02-01",45644.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique AI52 + AI53\r\n",null,null,75989,"2024-08-13",0,"5,6"]
[null,"Infrabel","66483","Namur - Antwerpen",">","Y.LOUVAIN-LA-NEUVE","GEMBLOUX",2025,2025,5,5,"2025-02-02",45644.333333333336,"2025-02-02",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie B Y Louvain La neuve - Gembloux \r\nUPM: 488043",null,null,66483,"2024-09-17",0,"5,6"]
[null,"Infrabel","66603","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2025,2025,5,5,"2025-02-02",45644.333333333336,"2025-02-02",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Sint-Joris-Weert - Wavre VA/VB\r\nUPM: 488508",null,null,66603,"2024-09-17",0,"5,6"]
[null,"Infrabel","70006","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2025,2025,5,5,"2025-02-02",45644.333333333336,"2025-02-02",45644.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144-130/1\r\nTCR 507096",null,null,70006,"2024-09-16",0,"5,6"]
[null,"Infrabel","70537","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2025,2025,5,5,"2025-02-02",45644.25,"2025-02-02",45644.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Kleine vernieuwingen lopend spoor en wissels",null,null,70537,"2024-02-01",0,"5,6"]
[null,"Infrabel","68895","Namur - Antwerpen","< >","Y.SCHIJN","ANTWERPEN-D.S.-RHODESIE",2025,2025,5,5,"2025-02-02",45644.25,"2025-02-02",45644.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Slijpwerken met SPENO op spoor B \r\n(planning per mail gekregen op 28/04/2023 van De Kempeneer David)",null,null,68895,"2024-06-26",1,"5,6"]
[null,"Infrabel","68494","Namur - Antwerpen",">","ANTWERPEN-D.S.-RHODESIE","Y.HOLLAND",2025,2025,5,5,"2025-02-02",45644.3125,"2025-02-02",45644.666666666664,"1d, 08:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Curatief slijpen met slijptrein op L27A spoor B buiten dienst.\r\n\r\n",null,null,68494,"2024-06-26",0,"5,6"]
[null,"Infrabel","68493","Namur - Antwerpen",">","Y.LIERSESTEENWEG","Y.HOLLAND",2025,2025,5,5,"2025-02-02",45644.041666666664,"2025-02-02",45644.291666666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Curatief slijpen met slijptrein op L27A spoor B buiten dienst.",null,null,68493,"2023-09-01",0,"5,6"]
[null,"Infrabel","59314","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,5,5,"2025-02-02",45644.034722222219,"2025-02-02",45644.21875,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot IX BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nTLO L 50 tussen Gent Sint Pieters en Y. West Driehoek Le",null,null,59314,"2023-06-28",0,"5,6"]
[null,"Infrabel","68037","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,5,5,"2025-02-02",45644.034722222219,"2025-02-02",45644.243055555555,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68037,"2024-06-27",0,"5,6"]
[null,"Infrabel","70822","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2025,2025,5,5,"2025-02-02",45644.354166666664,"2025-02-02",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70822,"2024-12-06",0,"5,6"]
[null,"Infrabel","75984","Lille - Charleroi",">","Y.SOIGNIES","SOIGNIES",2025,2025,5,5,"2025-02-02",45644.520833333336,"2025-02-02",45644.645833333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B\r\n",null,null,75984,"2024-08-13",0,"5,6"]
[null,"Infrabel","75985","Lille - Charleroi",">","Y.JURBISE","NEUFVILLES-GARAGE",2025,2025,5,5,"2025-02-02",45644.319444444445,"2025-02-02",45644.479166666664,"1d, 03:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VB\r\n",null,null,75985,"2024-08-13",0,"5,6"]
[null,"Infrabel","71695","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2025,2025,5,5,"2025-02-02",45644.329861111109,"2025-02-02",45644.545138888891,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nOttignies gare  voie A à 5 en alternance\r\nTCR 507141",null,null,71695,"2024-09-17",0,"5,6"]
[null,"Infrabel","63157","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,6,6,"2025-02-03",45644.958333333336,"2025-02-07",45644.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,63157,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","71242","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2025,2025,6,6,"2025-02-03",45644.958333333336,"2025-02-07",45644.194444444445,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z14.43 P3 HKV",null,null,71242,"2024-09-16",0,"1,2,3,4,5"]
[null,"Infrabel","54905","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","CHATELET-GRIL OUEST",2025,2025,6,6,"2025-02-03",45644.958333333336,"2025-02-08",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10.51   P3 HKV\r\nSans voie de protection",null,null,54905,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","71703","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2025,2025,6,6,"2025-02-03",45644.958333333336,"2025-02-08",45644.194444444445,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z73.33.02 - TCR 499310\r\nL53 FCB-FDR\r\nFDR SP I tem IV inbegrepen\r\nY FCB vrij",null,null,71703,"2024-08-05",0,"1,2,3,4,5"]
[null,"Infrabel","70416","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2025,2025,6,6,"2025-02-03",45644.333333333336,"2025-02-03",45644.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,70416,"2024-09-13",0,"1,2,3,4,5"]
[null,"Infrabel","56485","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,6,6,"2025-02-03",45644.979166666664,"2025-02-07",45644.173611111109,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation\r\nTCR 487613",null,null,56485,"2024-10-01",0,"1,2,3,4,5"]
[null,"Infrabel","59218","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,6,6,"2025-02-03",45644.979166666664,"2025-02-08",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe",null,null,59218,"2023-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","67818","Lille - ZeeBrugge","< >","LICHTERVELDE","KORTRIJK",2025,2025,6,6,"2025-02-03",45644.96875,"2025-02-08",45644.1875,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud - TCR 493191\r\nFLC SP III-IV inbegrepen",null,null,67818,"2024-06-21",0,"1,2,3,4,5"]
[null,"Infrabel","67868","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET",2025,2025,6,6,"2025-02-03",45644.965277777781,"2025-02-08",45644.201388888891,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTCR: 490387\r\n",null,null,67868,"2024-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","53251","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2025,2025,6,7,"2025-02-03",45644.965277777781,"2025-02-15",45644.208333333336,"12d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des CV\r\nDeux semaines de nuits (N67)\r\nTCR: 487935",null,null,53251,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","66479","Lille - Charleroi","< >","HALLE","ATH",2025,2025,6,6,"2025-02-03",45644.944444444445,"2025-02-08",45644.180555555555,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z9.54 + Z10.54\r\n+ PLP",null,null,66479,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","71909","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2025,2025,6,6,"2025-02-03",45644.989583333336,"2025-02-08",45644.194444444445,"5d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nimpact HKV\r\nZ14.23.01",null,null,71909,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","71630","Namur - Antwerpen","< >","MUIZEN-ROOSTER T","Y.OTTERBEEK",2025,2025,6,6,"2025-02-03",45644.993055555555,"2025-02-08",45644.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71630,"2024-04-09",0,"1,2,3,4,5"]
[null,"Infrabel","68792","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,6,6,"2025-02-03",45644.993055555555,"2025-02-08",45644.215277777781,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n1- Réalisation de massifs et pose de poteaux\r\nUPM: 487890",null,null,68792,"2024-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","68038","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,6,6,"2025-02-03",45644.034722222219,"2025-02-03",45644.201388888891,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68038,"2024-02-23",0,"5,6"]
[null,"Infrabel","76024","Lille - Charleroi",">","Y.SOIGNIES","BRAINE-LE-COMTE",2025,2025,6,6,"2025-02-03",45644.354166666664,"2025-02-03",45644.4375,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VB - Zone 2",null,null,76024,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","66183","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2025,2025,6,6,"2025-02-03",45644.354166666664,"2025-02-07",45644.645833333336,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z07.52 \r\nJOUR",null,null,66183,"2024-09-19",0,"1,2,3,4,5"]
[null,"Infrabel","70417","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2025,2025,6,6,"2025-02-03",45644.5,"2025-02-03",45644.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,70417,"2024-09-13",0,"1,2,3,4,5"]
[null,"Infrabel","74616","Lille - Charleroi","< >","BRUXELLES-MIDI","Y.RUISBROEK",2025,2025,6,6,"2025-02-04",45644.027777777781,"2025-02-08",45644.1875,"5d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen aw 37AJ/46BJ: afwerking\r\nFBMZ sp 17-18 tot Y Ruisbroek\r\nTijdens de nachten uitbreiding naar L124 en bundel Charleroi",null,null,74616,"2023-12-22",0,"1,2,3,4,5"]
[null,"Infrabel","71903","Namur - Antwerpen","< >","MECHELEN","KONTICH-LINT",2025,2025,6,6,"2025-02-04",45644.034722222219,"2025-02-08",45644.201388888891,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKM\r\nZ30.23",null,null,71903,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","72708","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,6,6,"2025-02-04",45644.003472222219,"2025-02-08",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72708,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","70419","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,6,6,"2025-02-04",45644.395833333336,"2025-02-04",45644.604166666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie et intervention avec S460 sur la voie contiguë + ATW",null,null,70419,"2024-09-13",0,"1,2,3,4,5"]
[null,"Infrabel","71442","Athus - Meuse",">","Y.NEFFE","DINANT",2025,2025,6,6,"2025-02-05",45644.333333333336,"2025-02-05",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,71442,"2024-09-23",0,"1,2,3,4,5"]
[null,"Infrabel","67460","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,6,6,"2025-02-06",45644.395833333336,"2025-02-06",45644.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nMise HS en P2\r\nTCR 488838",null,null,67460,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","74564","Lille - Charleroi",">","ATH","BRUGELETTE",2025,2025,6,6,"2025-02-06",45644.34375,"2025-02-06",45644.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno",null,null,74564,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","65681","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2025,2025,6,7,"2025-02-07",45644.958333333336,"2025-02-10",45644.201388888891,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Z9.42\r\nEntretien mécanisé et manuel des AS de Bressoux côté Visé\r\nEntretien mécanisé et manuel des AS du grill de Visé\r\n+ renouvellemnt des rails entre Bressoux et Visé sur la voie B en 2025\r\n\r\nUPM 488110",null,null,65681,"2024-09-16",1,"5,6"]
[null,"Infrabel","74563","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2025,2025,6,6,"2025-02-07",45644.333333333336,"2025-02-07",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno",null,null,74563,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","64982","Namur - Antwerpen","< >","TILLY-GARAGE","CHARLEROI-OUEST",2025,2025,6,7,"2025-02-07",45644.979166666664,"2025-02-10",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement CV en gare de Fleurus\r\nTCR: 488045",null,null,64982,"2024-09-17",1,"5,6"]
[null,"Infrabel","56487","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,6,7,"2025-02-07",45644.979166666664,"2025-02-10",45644.173611111109,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation\r\n+ Maintenance Z2. 51  P4+\r\nTCR 487617",null,null,56487,"2024-10-01",1,"5,6"]
[null,"Infrabel","68187","Lille - Charleroi",">","TUBIZE","BRAINE-LE-COMTE",2025,2025,6,7,"2025-02-07",45644.96875,"2025-02-10",45644.1875,"2d, 05:15h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification entre Lembeek et Braine-le-Comte\r\nWE SAVU\r\nTCR 491281\r\nCR NMBS2025-376 -L96 envoyé le 27/11/24/Validé le 28/11/24",null,null,68187,"2024-11-28",0,"5,6"]
[null,"Infrabel","75341","Lille - Antwerpen",">","Y.MELSELE","SINT-NIKLAAS",2025,2025,6,6,"2025-02-08",45644.013888888891,"2025-02-08",45644.215277777781,"1d, 04:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Reservatie onderhoud - TCR 500308",null,null,75341,"2024-06-21",0,"1,2,3,4,5"]
[null,"Infrabel","71645","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,6,7,"2025-02-08",45644.25,"2025-02-10",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"sporen 5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde",null,null,71645,"2024-06-28",1,"5,6"]
[null,"Infrabel","74107","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2025,2025,6,6,"2025-02-08",45644.996527777781,"2025-02-09",45644.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B - TCR495736",null,null,74107,"2024-06-21",0,"5,6"]
[null,"Infrabel","75032","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,6,7,"2025-02-08",45644.010416666664,"2025-02-10",45644.1875,"3d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Migratie tunnelveiligheidstechnieken Antw. NZ -2\r\nAntwerpen-Centraal - Antwerpen-Luchtbal",null,null,75032,"2024-01-31",0,"5,6"]
[null,"Infrabel","79276","Athus - Meuse",">","NAMUR","BOIS D'AUSSE",2025,2025,6,6,"2025-02-08",45644.375,"2025-02-08",45644.677083333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-085 \r\nVisite périodique de jour le samedi pour AI43. (suite mise en service ETCS)\r\nVA: Le samedi entre 9h et 16h15\r\nVB: Le Samedi entre 8h45 et 16h\r\nA dupliquer toutes les 8 semaines.\r\nTCR 510700",null,null,79276,"2024-10-14",0,"5,6"]
[null,"Infrabel","79730","Athus - Meuse","< >","ANSEREMME","BERTRIX",2025,2025,6,6,"2025-02-09",45644.03125,"2025-02-09",45644.197916666664,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-104: EBP - Hardware Equipment Maintenance : \"Renewal Network Devices\" pour I-AM251 (Ch Payen)\r\nTCR 514419",null,null,79730,"2024-10-08",0,"5,6"]
[null,"Infrabel","69346","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,6,6,"2025-02-09",45644.020833333336,"2025-02-09",45644.25,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossen rails vernieuwingswerken april/mei 2025",null,null,69346,"2024-11-12",0,"5,6"]
[null,"Infrabel","67315","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ANTWERPEN-D.S.-RHODESIE",2025,2025,6,6,"2025-02-09",45644.25,"2025-02-09",45644.729166666664,"1d, 11:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,67315,"2024-04-08",0,"5,6"]
[null,"Infrabel","63158","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,7,7,"2025-02-10",45644.958333333336,"2025-02-15",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,63158,"2024-09-27",0,"1,2,3,4,5"]
[null,"Infrabel","68397","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,7,7,"2025-02-10",45644.979166666664,"2025-02-14",45644.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing BVL.\r\nWeeknachten ter vervanging van geannuleerde lange TLO (COLT 57997)",null,null,68397,"2023-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","72709","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,7,7,"2025-02-10",45644.979166666664,"2025-02-15",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72709,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","59219","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,7,7,"2025-02-10",45644.979166666664,"2025-02-15",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nDoes Spoor A L 50 tussen Gent Sint Pieters en Y. West Dr",null,null,59219,"2023-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","53494","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2025,2025,7,7,"2025-02-10",45644.951388888891,"2025-02-14",45644.180555555555,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 en P3 HKV\r\n+ Z2.53",null,null,53494,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","65557","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,7,7,"2025-02-10",45644.972222222219,"2025-02-14",45644.201388888891,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Blankenberge vernieuwen wissels - TCR 494968\r\n\r\n*gevallen 29534-29542-29543-29544\r\n*R5/R6 in weekend TLO",null,null,65557,"2024-07-17",0,"1,2,3,4,5"]
[null,"Infrabel","65792","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2025,2025,7,7,"2025-02-10",45644.9375,"2025-02-15",45644.208333333336,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z8.51   P3",null,null,65792,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","79396","Namur - Antwerpen",">","HEVERLEE-ROOSTER K/L","SINT-JORIS-WEERT",2025,2025,7,7,"2025-02-10",45644.916666666664,"2025-02-11",45644.25,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-091\r\nFREESCAMPAGNE 2025\r\nDe te behandelen zones worden bepaald door de meetresultaten van de laatste meetcampagne.\r\nDeze baanvakken moeten dringend door de freestrein behandeld worden om verdere beschadigingen te voorkomen (US fouten en railbreu",null,null,79396,"2024-06-27",0,"5,6"]
[null,"Infrabel","55903","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2025,2025,7,7,"2025-02-10",45644.965277777781,"2025-02-15",45644.208333333336,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Démolition 85.708 - Préparations\r\n+ Réélectrification L130\r\n+ Maintenance Z15. 51 P3 HKV \r\n+Placement Jic pour D. Pecceu\r\nTCR: 490393",null,null,55903,"2024-10-17",0,"1,2,3,4,5"]
[null,"Infrabel","67981","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2025,2025,7,7,"2025-02-10",45644.965277777781,"2025-02-15",45644.166666666664,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\n+\r\nInstandhouding Y Bethune\r\n\r\nTCR 492779",null,null,67981,"2024-07-17",0,"1,2,3,4,5"]
[null,"Infrabel","72760","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2025,2025,7,7,"2025-02-10",45644.986111111109,"2025-02-15",45644.222222222219,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudswerken volgens onderhoudskalender area CE\r\nOnderhoudszone FBMZ_13/14 in rooster FBMZ tijdens de nachten\r\n\r\nBeschermingsspoor en BVL later te verkrijgen BUV: L96D, FBMZ sp 15-16-17",null,null,72760,"2024-02-02",0,"1,2,3,4,5"]
[null,"Infrabel","71234","Erquelinnes - Montzen","< >","HUY","NAMUR",2025,2025,7,7,"2025-02-10",45644.993055555555,"2025-02-14",45644.208333333336,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.43 HKV \r\nPropo amplitude 23h50- 5h - conflit L130 chantier",null,null,71234,"2024-09-27",0,"1,2,3,4,5"]
[null,"Infrabel","71631","Namur - Antwerpen","< >","MUIZEN-ROOSTER T","Y.OTTERBEEK",2025,2025,7,7,"2025-02-10",45644.993055555555,"2025-02-15",45644.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71631,"2024-04-16",0,"1,2,3,4,5"]
[null,"Infrabel","68793","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,7,7,"2025-02-10",45644.993055555555,"2025-02-15",45644.215277777781,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n1- Réalisation de massifs et pose de poteaux\r\nUPM: 487892",null,null,68793,"2024-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","73474","Namur - Antwerpen",">","Y.MELLE-WEST","MERELBEKE-ROOSTER S",2025,2025,7,7,"2025-02-10",45644.395833333336,"2025-02-12",45644.645833333336,"3d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"reservatie onderhoud - TCR 501996\r\ndagdienst zone 1\r\nL50E SP B Y Melle West AW02BT niet inbegrepen tot inrit Merelbeke rooster S AW01AS niet inbegrepen\r\nBVL: 29164\r\nR-464521",null,null,73474,"2024-07-17",0,"1,2,3,4,5"]
[null,"Infrabel","79402","Namur - Antwerpen",">","HEVERLEE-ROOSTER K/L","SINT-JORIS-WEERT",2025,2025,7,7,"2025-02-11",45644.916666666664,"2025-02-13",45644.25,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-091\r\nFREESCAMPAGNE 2025\r\nDe te behandelen zones worden bepaald door de meetresultaten van de laatste meetcampagne.\r\nDeze baanvakken moeten dringend door de freestrein behandeld worden om verdere beschadigingen te voorkomen (US fouten en railbreu",null,null,79402,"2024-06-27",0,"1,2,3,4,5"]
[null,"Infrabel","67888","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,7,7,"2025-02-11",45644.020833333336,"2025-02-14",45644.180555555555,"4d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67888,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","72034","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2025,2025,7,7,"2025-02-11",45644.003472222219,"2025-02-14",45644.184027777781,"4d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z07.31 HKM - TCR 502520\r\nL75 FGSP-FD \r\nFGSP SP VIII-IX + Bundel CD niet bereikbaar\r\nFD blijft vrij\r\nL86 FPT-FDN\r\nFDN SP III-IV in\r\nR5/R6 niet inbegrepen, conflict FGSP ea",null,null,72034,"2024-08-05",0,"1,2,3,4,5"]
[null,"Infrabel","70487","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,7,7,"2025-02-12",45644.375,"2025-02-12",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y-Holland",null,null,70487,"2024-02-14",0,"1,2,3,4,5"]
[null,"Infrabel","73058","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,7,7,"2025-02-13",45644.333333333336,"2025-02-13",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73058,"2024-09-26",0,"1,2,3,4,5"]
[null,"Infrabel","70553","Namur - Antwerpen","< >","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL",2025,2025,7,7,"2025-02-13",45644.986111111109,"2025-02-14",45644.236111111109,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen Centraal -1",null,null,70553,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","73378","Athus - Meuse",">","YVOIR","DINANT",2025,2025,7,7,"2025-02-13",45644.385416666664,"2025-02-13",45644.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73378,"2024-09-27",0,"1,2,3,4,5"]
[null,"Infrabel","70614","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2025,2025,7,7,"2025-02-13",45644.375,"2025-02-13",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen - Schijnpoort + inrit bundel Q",null,null,70614,"2024-03-13",0,"1,2,3,4,5"]
[null,"Infrabel","73475","Namur - Antwerpen","< >","MERELBEKE-ROOSTER S","Y.OOST DRIEHOEK LEDEBERG",2025,2025,7,7,"2025-02-13",45644.395833333336,"2025-02-14",45644.645833333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"reservatie onderhoud -  TCR 502159\r\ndagdienst zone 2\r\nL50E SP A Merelbeke rooster S sein EX-S.6 tot Y Oost Driehoek Ledeberg 10AR niet inbegrepen\r\nL50E SP B Merelbeke rooster S sein F-S.6 tot Y Oost Driehoek Ledeberg 03XR niet inbegrepen\r\nBVL: niet moge",null,null,73475,"2024-07-17",0,"1,2,3,4,5"]
[null,"Infrabel","71073","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,7,7,"2025-02-14",45644.958333333336,"2025-02-15",45644.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nZ5.43",null,null,71073,"2024-09-27",0,"1,2,3,4,5"]
[null,"Infrabel","56488","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,7,8,"2025-02-14",45644.958333333336,"2025-02-17",45644.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation\r\n+ Maintenance Z2. 51  P4+\r\nTCR 487621",null,null,56488,"2024-09-17",1,"5,6"]
[null,"Infrabel","73059","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,7,7,"2025-02-14",45644.333333333336,"2025-02-14",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73059,"2024-09-26",0,"1,2,3,4,5"]
[null,"Infrabel","59516","Namur - Antwerpen","< >","CHARLEROI-OUEST","FLEURUS",2025,2025,7,8,"2025-02-14",45644.965277777781,"2025-02-17",45644.208333333336,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de CV\r\nTCR: 488065",null,null,59516,"2024-09-17",1,"5,6"]
[null,"Infrabel","65564","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,7,8,"2025-02-14",45644.965277777781,"2025-02-17",45644.201388888891,"2d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Blankenberge vernieuwen wissels - TCR 494972\r\nTLO tss Y Bl Toren en Blankenberge\r\nSPI+II+ III+IV+V+VI+VII buiten dienst\r\nBundel M niet bereikbaar",null,null,65564,"2024-07-17",1,"5,6"]
[null,"Infrabel","78204","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2025,2025,7,8,"2025-02-14",45644.989583333336,"2025-02-17",45644.229166666664,"2d, 05:45h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-075 : Travaux RER\r\nremplace COLT 59177 et UPM 488181\r\n\r\nNew UPM: 505516",null,null,78204,"2024-09-30",0,"5,6"]
[null,"Infrabel","73379","Athus - Meuse",">","DINANT","YVOIR",2025,2025,7,7,"2025-02-14",45644.385416666664,"2025-02-14",45644.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73379,"2024-09-27",0,"1,2,3,4,5"]
[null,"Infrabel","70627","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,7,7,"2025-02-14",45644.375,"2025-02-14",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y Holland + inrit bundel Q",null,null,70627,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","72255","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,7,8,"2025-02-15",45644.979166666664,"2025-02-17",45644.166666666664,"1d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug  L15 km 6.027 BX L15 en L27A\r\n\r\nalternatief voor geweigerde L15+L27A",null,null,72255,"2024-03-12",1,"5,6"]
[null,"Infrabel","55057","Namur - Antwerpen",">","CHATELET-GRIL OUEST","CHATELET-GRIL EST",2025,2025,7,7,"2025-02-15",45644.9375,"2025-02-16",45644.916666666664,"1d, 23:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance Z17. 51 \r\nFaisceau de Chatelet\r\nTCR: 491690",null,null,55057,"2024-09-17",0,"5,6"]
[null,"Infrabel","75345","Lille - Antwerpen",">","LOKEREN","OOSTAKKER",2025,2025,7,7,"2025-02-15",45644.020833333336,"2025-02-15",45644.229166666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Reservatie onderhoud - TCR 500289",null,null,75345,"2024-07-18",0,"1,2,3,4,5"]
[null,"Infrabel","67980","Lille - Charleroi","< >","ATH","ENGHIEN",2025,2025,7,8,"2025-02-15",45644.020833333336,"2025-02-17",45644.1875,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"PLP\r\nUPM 487887",null,null,67980,"2024-09-17",1,"5,6"]
[null,"Infrabel","66717","Namur - Antwerpen","< >","DENDERMONDE","LONDERZEEL",2025,2025,7,8,"2025-02-15",45644.013888888891,"2025-02-17",45644.1875,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"P208 waterhuishouding +P221 Goederen coriddors Dendermonde - TCR 492740",null,null,66717,"2024-07-18",1,"5,6"]
[null,"Infrabel","72543","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,7,7,"2025-02-15",45644.3125,"2025-02-15",45644.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72543,"2024-09-20",0,"5,6"]
[null,"Infrabel","60194","Lille - Antwerpen",">","Y.WEST BERCHEM","ZWIJNDRECHT-ROOSTER D",2025,2025,7,8,"2025-02-15",45644.041666666664,"2025-02-17",45644.1875,"2d, 03:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Stationsproject Antwerpen-Zuid B-Stations:\r\nTrapconstructie op perron\r\nCf Escalade Head Of nov/dec 2023",null,null,60194,"2024-05-17",0,"5,6"]
[null,"Infrabel","68395","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,7,8,"2025-02-15",45644.000694444447,"2025-02-17",45644.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing BVL.\r\nWeekends 7+8 ter vervanging van geannuleerde lange TLO (COLT 57997).",null,null,68395,"2023-07-14",1,"5,6"]
[null,"Infrabel","67465","Lille - Charleroi","< >","GHLIN","MONS",2025,2025,7,7,"2025-02-15",45644.993055555555,"2025-02-16",45644.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim",null,null,67465,"2024-09-17",0,"5,6"]
[null,"Infrabel","73360","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,7,7,"2025-02-15",45644.375,"2025-02-15",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73360,"2024-09-27",0,"5,6"]
[null,"Infrabel","71106","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2025,2025,7,8,"2025-02-16",45644.958333333336,"2025-02-17",45644.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nZ7.43",null,null,71106,"2024-09-27",0,"1,2,3,4,5"]
[null,"Infrabel","68925","Lille - Antwerpen","< >","BEERVELDE","GENT-DAMPOORT",2025,2025,7,7,"2025-02-16",45644.03125,"2025-02-16",45644.215277777781,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"In dienst stelling ETCS - TCR 493368\r\nMeewerken niet mogelijk\r\nL59 Gent Dampoort - Lokeren (v) 00.45 - 05.30\r\nL58 - Eeklo Niet in tot Y Oost Driehoek Ledeberg IN - 00.45 tot 05.50\r\nL58/1 - Y Noord Driehoek ledeberg IN tot Y West Driehoek Ledeberg IN - 0",null,null,68925,"2024-07-18",0,"5,6"]
[null,"Infrabel","75346","Lille - Antwerpen","< >","Y.MELSELE","LOKEREN",2025,2025,7,7,"2025-02-16",45644.03125,"2025-02-16",45644.215277777781,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud - TCR 500396",null,null,75346,"2024-07-18",0,"5,6"]
[null,"Infrabel","72556","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,7,7,"2025-02-16",45644.3125,"2025-02-16",45644.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72556,"2024-09-20",0,"5,6"]
[null,"Infrabel","82127","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","GENT-DAMPOORT",2025,2025,7,7,"2025-02-16",45644.041666666664,"2025-02-16",45644.166666666664,"1d, 03:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-191\r\nIDS P025/26 _RW_P024 - IDS Gent - Denderleeuw-Merelbeke-Bernadettestraat RW L59 Antwerpen-Zuid - Gent-Zeehaven\r\nR-521493",null,null,82127,"2024-11-05",0,"5,6"]
[null,"Infrabel","79710","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2025,2025,7,7,"2025-02-16",45644.0625,"2025-02-16",45644.166666666664,"1d, 02:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-101\r\nEBP - Hardware Equipment Maintenance : \"Renewal Network Devices\" + FORTINET. Buitendienst van seinpost FLV-CR (Computer Room) en de EBP gekoppelde zone voor minimaal 2,5u voor werken \"Renewal of Network Device\". Uurregelingen zijn aanpasbaa",null,null,79710,"2024-06-26",0,"5,6"]
[null,"Infrabel","73361","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,7,7,"2025-02-16",45644.375,"2025-02-16",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73361,"2024-09-27",0,"5,6"]
[null,"Infrabel","56486","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,8,8,"2025-02-17",45644.958333333336,"2025-02-21",45644.173611111109,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage & Hourpes : blindage pour construction MDS + préparation caténaire\r\nSecond tabliers ponts 7,8 et 9 \r\nTravaux de préparation\r\n+Maintenance Z2.51.\r\nTCR 487622",null,null,56486,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","65316","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,8,8,"2025-02-17",45644.958333333336,"2025-02-22",45644.229166666664,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails , ballast...",null,null,65316,"2024-09-24",0,"1,2,3,4,5"]
[null,"Infrabel","71754","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,8,8,"2025-02-17",45644.333333333336,"2025-02-17",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nTCR 507451",null,null,71754,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","71133","Athus - Meuse",">","GEDINNE","PALISEUL",2025,2025,8,8,"2025-02-17",45644.333333333336,"2025-02-17",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,71133,"2024-10-02",0,"1,2,3,4,5"]
[null,"Infrabel","68398","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,8,8,"2025-02-17",45644.979166666664,"2025-02-21",45644.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing BVL.\r\nWeeknachten ter vervanging van geannuleerde lange TLO (COLT 57997)",null,null,68398,"2023-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","71349","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,8,8,"2025-02-17",45644.979166666664,"2025-02-22",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe",null,null,71349,"2024-01-19",0,"1,2,3,4,5"]
[null,"Infrabel","66574","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2025,2025,8,8,"2025-02-17",45644.951388888891,"2025-02-22",45644.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.51 \r\nP3 HKV",null,null,66574,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","71904","Namur - Antwerpen","< >","MECHELEN","KONTICH-LINT",2025,2025,8,8,"2025-02-17",45644.972222222219,"2025-02-22",45644.204861111109,"5d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKV\r\nZ30.23\r\n",null,null,71904,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","65558","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,8,8,"2025-02-17",45644.965277777781,"2025-02-21",45644.201388888891,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Blankenberge vernieuwen wissels - TCR 494975\r\n\r\n*gevallen 29534-29542-29543-29544\r\n*R5/R6 in weekend TLO",null,null,65558,"2024-07-18",0,"1,2,3,4,5"]
[null,"Infrabel","68218","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2025,2025,8,8,"2025-02-17",45644.965277777781,"2025-02-22",45644.166666666664,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\n+\r\nInstandhouding Y Bethune\r\n\r\nTCR 492785",null,null,68218,"2024-07-18",0,"1,2,3,4,5"]
[null,"Infrabel","67871","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET",2025,2025,8,8,"2025-02-17",45644.965277777781,"2025-02-22",45644.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTCR: 490408",null,null,67871,"2024-10-17",0,"1,2,3,4,5"]
[null,"Infrabel","60134","Athus - Meuse","< >","HAVERSIN","ROCHEFORT-JEMELLE",2025,2025,8,51,"2025-02-17",45644.986111111109,"2025-12-19",45644.180555555555,"305d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaire Axe 3 en gare de Marloie:\r\nUPM 490244",null,null,60134,"2024-09-23",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","75880","Athus - Meuse",">","DINANT","Y.NEFFE",2025,2025,8,13,"2025-02-17",45644.25,"2025-03-29",45644.958333333336,"41d, 17:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"suppression du PN 115bis avant reprise en PLP\r\nCR2025-054 \r\nUPM:508161",null,null,75880,"2024-12-13",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","74024","Namur - Antwerpen","< >","FLEURUS","Y.NORD",2025,2025,8,8,"2025-02-17",45644.996527777781,"2025-02-22",45644.201388888891,"5d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien Caténaires\r\nTCR 499753",null,null,74024,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","71898","Namur - Antwerpen","< >","MECHELEN","Y.SINT-KATELIJNE-WAVER",2025,2025,8,8,"2025-02-17",45644.993055555555,"2025-02-22",45644.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nenkel L27 mogelijk in combinatie met Z30.23\r\nenkel L25 sp B zit in zone Z30.23\r\nHKV",null,null,71898,"2024-01-18",0,"1,2,3,4,5"]
[null,"Infrabel","71633","Namur - Antwerpen","< >","Y.MUIZEN","Y.OTTERBEEK",2025,2025,8,8,"2025-02-17",45644.993055555555,"2025-02-22",45644.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71633,"2024-04-09",0,"1,2,3,4,5"]
[null,"Infrabel","70452","Namur - Antwerpen","< >","Y.HOLLAND","LUCHTBAL-ROOSTER S",2025,2025,8,8,"2025-02-17",45644.993055555555,"2025-02-22",45644.1875,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissel Y Antwerpen-Luchtbal\r\nHKV",null,null,70452,"2024-02-06",0,"1,2,3,4,5"]
[null,"Infrabel","68794","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,8,8,"2025-02-17",45644.993055555555,"2025-02-22",45644.215277777781,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n1- Réalisation de massifs et pose de poteaux\r\n+ Entretien tronçon allongé Z1.44\r\nUPM: 487898",null,null,68794,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","77623","Athus - Meuse","< >","AUBANGE-FRONTIERE-FRANCE","Y.AUBANGE",2025,2025,8,8,"2025-02-17",45644.354166666664,"2025-02-17",45644.5,"1d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite voie unique L 165/2 \r\nVisite voie unique L 165/3\r\nVisite voie unique L 165/1",null,null,77623,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","73391","Athus - Meuse",">","DINANT","Y.NEFFE",2025,2025,8,8,"2025-02-17",45644.34375,"2025-02-17",45644.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites VA",null,null,73391,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","73123","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2025,2025,8,8,"2025-02-17",45644.423611111109,"2025-02-17",45644.493055555555,"1d, 01:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,73123,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","68708","Erquelinnes - Montzen","< >","SERAING","FLEMALLE-HAUTE",2025,2025,8,8,"2025-02-18",45644.958333333336,"2025-02-22",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons",null,null,68708,"2024-09-24",0,"1,2,3,4,5"]
[null,"Infrabel","73079","Athus - Meuse",">","SIGNEULX","HALANZY",2025,2025,8,8,"2025-02-18",45644.333333333336,"2025-02-18",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73079,"2024-10-02",0,"1,2,3,4,5"]
[null,"Infrabel","71135","Athus - Meuse",">","PALISEUL","GEDINNE",2025,2025,8,8,"2025-02-18",45644.333333333336,"2025-02-18",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,71135,"2024-10-02",0,"1,2,3,4,5"]
[null,"Infrabel","71245","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2025,2025,8,8,"2025-02-18",45644,"2025-02-21",45644.201388888891,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z14.43\r\nconflit L130 maintenance",null,null,71245,"2024-09-26",0,"1,2,3,4,5"]
[null,"Infrabel","67889","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,8,8,"2025-02-18",45644.020833333336,"2025-02-21",45644.208333333336,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67889,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","72035","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2025,2025,8,8,"2025-02-18",45644.003472222219,"2025-02-21",45644.184027777781,"4d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z07.31 HKM + werkveld 4.2 - TCR 503287\r\nL75 FGSP-FD \r\nFGSP SP III -IX + Bundel CD niet bereikbaar\r\nFD blijft vrij\r\nL86 FPT-FDN\r\nFDN SP III-IV in\r\nR5/R6 niet inbegrepen, conflict FGSP ea",null,null,72035,"2024-08-05",0,"1,2,3,4,5"]
[null,"Infrabel","72710","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,8,8,"2025-02-18",45644.003472222219,"2025-02-22",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72710,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","72745","Athus - Meuse",">","STOCKEM-NORD","ARLON",2025,2025,8,8,"2025-02-18",45644.361111111109,"2025-02-18",45644.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72745,"2024-10-01",0,"1,2,3,4,5"]
[null,"Infrabel","73080","Athus - Meuse",">","HALANZY","SIGNEULX",2025,2025,8,8,"2025-02-19",45644.333333333336,"2025-02-19",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie  B",null,null,73080,"2024-10-02",0,"1,2,3,4,5"]
[null,"Infrabel","72746","Athus - Meuse",">","HABAY","STOCKEM-NORD",2025,2025,8,8,"2025-02-19",45644.375,"2025-02-19",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72746,"2024-10-01",0,"1,2,3,4,5"]
[null,"Infrabel","71129","Athus - Meuse",">","VONECHE","GEDINNE",2025,2025,8,8,"2025-02-20",45644.333333333336,"2025-02-20",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,71129,"2024-10-02",0,"1,2,3,4,5"]
[null,"Infrabel","71131","Athus - Meuse",">","GEDINNE","VONECHE",2025,2025,8,8,"2025-02-21",45644.333333333336,"2025-02-21",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,71131,"2024-10-02",0,"1,2,3,4,5"]
[null,"Infrabel","59517","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,8,9,"2025-02-21",45644.965277777781,"2025-02-24",45644.208333333336,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance P4  Z3;51 \r\nTCR: 488067",null,null,59517,"2024-09-17",1,"5,6"]
[null,"Infrabel","77833","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,8,9,"2025-02-21",45644.965277777781,"2025-02-24",45644.201388888891,"2d, 05:40h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-067\r\nR-501738-xx\r\n\r\nBlankenberge vernieuwen wissels \r\nDOES tss Y Bl Toren en Blankenberge\r\nSP B BD van sein O-U.7 tot SP II Blankenberge inbegrepen\r\nSP III+IV+V+VI+VII buiten dienst\r\nBundel M niet bereikbaar\r\n\r\n*gevallen 29534-29542-29543-29544-",null,null,77833,"2024-07-22",0,"5,6"]
[null,"Infrabel","65565","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,8,9,"2025-02-21",45644.965277777781,"2025-02-24",45644.201388888891,"3d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Blankenberge vernieuwen wissels  - TCR 494977\r\nDOES tss Y Bl Toren en Blankenberge\r\nSP B BD van sein O-U.7 tot SP II Blankenberge inbegrepen\r\nSP III+IV+V+VI+VII buiten dienst\r\nBundel M niet bereikbaar\r\n\r\n*gevallen 29534-29542-29543-29544-29532-29541",null,null,65565,"2024-07-18",0,"5,6"]
[null,"Infrabel","71319","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2025,2025,8,8,"2025-02-22",45644.333333333336,"2025-02-22",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71319,"2024-10-02",0,"5,6"]
[null,"Infrabel","71125","Athus - Meuse",">","BEAURAING","VONECHE",2025,2025,8,8,"2025-02-22",45644.333333333336,"2025-02-22",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,71125,"2024-10-02",0,"5,6"]
[null,"Infrabel","77566","Lille - Charleroi",">","SOIGNIES","NEUFVILLES",2025,2025,8,8,"2025-02-22",45644.333333333336,"2025-02-22",45644.458333333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagno Zone 4",null,null,77566,"2024-09-17",0,"5,6"]
[null,"Infrabel","66995","Lille - Charleroi","< >","HALLE","ENGHIEN",2025,2025,8,8,"2025-02-22",45644.333333333336,"2025-02-23",45644.666666666664,"2d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.54\r\nUPM 487937",null,null,66995,"2024-11-13",0,"5,6"]
[null,"Infrabel","66718","Namur - Antwerpen","< >","DENDERMONDE","LONDERZEEL",2025,2025,8,9,"2025-02-22",45644.013888888891,"2025-02-24",45644.1875,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"P208 waterhuishouding+P221 Goederencorridors Dendermmonde - TCR 492744",null,null,66718,"2024-07-18",1,"5,6"]
[null,"Infrabel","75277","Lille - Charleroi",">","HENNUYERES-GARAGE","TUBIZE",2025,2025,8,8,"2025-02-22",45644.524305555555,"2025-02-22",45644.645833333336,"1d, 02:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique + S460\r\n",null,null,75277,"2024-09-17",0,"5,6"]
[null,"Infrabel","68396","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,8,9,"2025-02-22",45644.000694444447,"2025-02-24",45644.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing BVL.\r\nWeekend 7+8 ter  vervanging van geannuleerde lange TLO (COLT 57997)",null,null,68396,"2023-08-29",1,"5,6"]
[null,"Infrabel","69347","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,8,8,"2025-02-22",45644.993055555555,"2025-02-23",45644.208333333336,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossen rails vernieuwingswerken april/mei 2025",null,null,69347,"2024-11-12",0,"5,6"]
[null,"Infrabel","75033","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,8,9,"2025-02-22",45644.010416666664,"2025-02-24",45644.1875,"3d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Migratie tunnelveiligheidstechnieken Antw. NZ -2\r\nAntwerpen-Centraal - Antwerpen-Luchtbal",null,null,75033,"2024-01-31",0,"5,6"]
[null,"Infrabel","71447","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,8,8,"2025-02-22",45644.385416666664,"2025-02-22",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,71447,"2024-10-08",0,"5,6"]
[null,"Infrabel","71321","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2025,2025,8,8,"2025-02-23",45644.333333333336,"2025-02-23",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,71321,"2024-10-02",0,"5,6"]
[null,"Infrabel","71127","Athus - Meuse",">","VONECHE","BEAURAING",2025,2025,8,8,"2025-02-23",45644.333333333336,"2025-02-23",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,71127,"2024-10-02",0,"5,6"]
[null,"Infrabel","75272","Lille - Charleroi",">","BRAINE-LE-COMTE","HENNUYERES-GARAGE",2025,2025,8,8,"2025-02-23",45644.333333333336,"2025-02-23",45644.5625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique +S460\r\n",null,null,75272,"2024-09-17",0,"5,6"]
[null,"Infrabel","71450","Athus - Meuse",">","LUSTIN","JAMBES",2025,2025,8,8,"2025-02-23",45644.385416666664,"2025-02-23",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,71450,"2024-10-08",0,"5,6"]
[null,"Infrabel","75271","Lille - Charleroi",">","TUBIZE","LEMBEEK",2025,2025,8,8,"2025-02-23",45644.597222222219,"2025-02-23",45644.645833333336,"1d, 01:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique Voie B  +S460 voie A\r\n",null,null,75271,"2024-09-17",0,"5,6"]
[null,"Infrabel","71350","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,9,9,"2025-02-24",45644.979166666664,"2025-02-28",45644.180555555555,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe",null,null,71350,"2023-09-27",0,"1,2,3,4,5"]
[null,"Infrabel","68399","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,9,9,"2025-02-24",45644.979166666664,"2025-03-01",45644.208333333336,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing BVL.\r\nWeeknachten ter vervanging van geannuleerde lange TLO (COLT 57997)",null,null,68399,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","72711","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,9,9,"2025-02-24",45644.979166666664,"2025-03-01",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72711,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","72082","Lille - ZeeBrugge","< >","BRUGGE","LICHTERVELDE",2025,2025,9,9,"2025-02-24",45644.972222222219,"2025-02-28",45644.208333333336,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 07.34 HKM - TCR 500298\r\nFR SP VI+VII+VIII inbegrepen\r\nL73 FLC tot Diksmuide perronspoor II inbegrepen\r\nR5/R6 niet inbegrepen >> TLO WE L73",null,null,72082,"2024-08-05",0,"1,2,3,4,5"]
[null,"Infrabel","65559","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,9,9,"2025-02-24",45644.965277777781,"2025-03-01",45644.201388888891,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Blankenberge vernieuwen wissels - TCR 494981\r\n\r\n*gevallen 29534-29542-29543-29544\r\n*R5/R6 in weekend TLO",null,null,65559,"2024-07-19",0,"1,2,3,4,5"]
[null,"Infrabel","68051","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET",2025,2025,9,9,"2025-02-24",45644.965277777781,"2025-03-01",45644.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTCR: 490426\r\nCR2025_046_V02",null,null,68051,"2024-10-18",0,"1,2,3,4,5"]
[null,"Infrabel","66990","Lille - Charleroi","< >","HALLE","ATH",2025,2025,9,9,"2025-02-24",45644.944444444445,"2025-03-01",45644.180555555555,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z9.54+Z10.54 P3 HKV\r\n+ PLP",null,null,66990,"2024-09-23",0,"1,2,3,4,5"]
[null,"Infrabel","56183","Namur - Antwerpen",">","MOUSTIER","FRANIERE",2025,2025,9,14,"2025-02-24",45644.291666666664,"2025-04-06",45644.666666666664,"41d, 09:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du système de drainage (caniveaux) dans le bois de Soye\r\nDossier de concertation validé en octobre 2022\r\nUPM: 489457",null,null,56183,"2024-10-10",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","74025","Namur - Antwerpen","< >","FLEURUS","Y.NORD",2025,2025,9,9,"2025-02-24",45644.996527777781,"2025-03-01",45644.201388888891,"5d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de ligne",null,null,74025,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","71661","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2025,2025,9,9,"2025-02-24",45644.947916666664,"2025-03-01",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 05.32 - TCR 500585\r\nL58 Eeklo inbegrepen tot Gent Dampoort NIET inbegrepen",null,null,71661,"2024-08-05",0,"1,2,3,4,5"]
[null,"Infrabel","56182","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,9,9,"2025-02-24",45644.375,"2025-02-28",45644.645833333336,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement de Luttre - phase 2025\r\nentre  IX-E.20 > quai IV\r\nTravaux ES + Préparations caténaires, \r\n(réalisation de massifs en tête de faisceau)\r\n+ révision à mi-vie caténaire L117, entre IX-E.20 > T-H.11\r\nTCR: 488550",null,null,56182,"2024-09-23",0,"1,2,3,4,5"]
[null,"Infrabel","67022","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,9,9,"2025-02-24",45644.923611111109,"2025-02-28",45644.194444444445,"4d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de rails \r\n+ Travaux OA \r\n+ Chantier SPW PS 65.090\r\nTCR 488644",null,null,67022,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","73138","Athus - Meuse",">","NAMUR","JAMBES",2025,2025,9,9,"2025-02-24",45644.388888888891,"2025-02-24",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73138,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","72747","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2025,2025,9,9,"2025-02-24",45644.409722222219,"2025-02-24",45644.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72747,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","72928","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2025,2025,9,9,"2025-02-25",45644.333333333336,"2025-02-25",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,72928,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","78637","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,9,9,"2025-02-25",45644.010416666664,"2025-03-01",45644.208333333336,"5d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien de CV\r\nUPM: 507247",null,null,78637,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","77161","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2025,2025,9,9,"2025-02-25",45644.34375,"2025-02-25",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,77161,"2024-10-10",0,"1,2,3,4,5"]
[null,"Infrabel","71311","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,9,9,"2025-02-26",45644.333333333336,"2025-02-26",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71311,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","72749","Athus - Meuse",">","LAVAUX","MARBEHAN",2025,2025,9,9,"2025-02-26",45644.361111111109,"2025-02-26",45644.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72749,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","77160","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2025,2025,9,9,"2025-02-26",45644.388888888891,"2025-02-26",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA (périodicité 3 semaines)",null,null,77160,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","73098","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,9,9,"2025-02-27",45644.333333333336,"2025-02-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73098,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","71137","Athus - Meuse",">","PALISEUL","BERTRIX",2025,2025,9,9,"2025-02-27",45644.333333333336,"2025-02-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,71137,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","55769","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2025,2025,9,9,"2025-02-27",45644.333333333336,"2025-02-28",45644.958333333336,"2d, 15:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre - travaux préparatoires\r\nUPM: 488523",null,null,55769,"2024-10-09",0,"1,2,3,4,5"]
[null,"Infrabel","70699","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2025,2025,9,9,"2025-02-27",45644.951388888891,"2025-03-01",45644.1875,"2d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen\r\nHKV\r\nZ23.22.01",null,null,70699,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","72752","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2025,2025,9,9,"2025-02-27",45644.368055555555,"2025-02-27",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72752,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","67454","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,9,9,"2025-02-27",45644.395833333336,"2025-02-27",45644.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nVisite diagnostique\r\nMise HS en P2\r\nTCR 488840",null,null,67454,"2024-09-17",0,"1,2,3,4,5"]
[null,"Infrabel","55770","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2025,2025,9,11,"2025-02-28",45644.958333333336,"2025-03-10",45644.208333333336,"9d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre\r\nRenouvellement de rails entre SJW et Y Ottignies Relais\r\n+ visites\r\n+ Entretien massification\r\nUPM: 488527",null,null,55770,"2024-10-09",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","73099","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,9,9,"2025-02-28",45644.333333333336,"2025-02-28",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73099,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","71139","Athus - Meuse",">","BERTRIX","PALISEUL",2025,2025,9,9,"2025-02-28",45644.333333333336,"2025-02-28",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,71139,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","67553","Lille - Antwerpen",">","KORTRIJK","KORTRIJK-RINGLAAN",2025,2025,9,10,"2025-02-28",45644.979166666664,"2025-03-03",45644.166666666664,"2d, 04:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwen lopend spoor van Bundel C naar Y Bethune - \r\nbundel C Buiten dienst\r\n+\r\nOnderhoud\r\n\r\nBundels Kortrijk bereikbaar kant Moeskroen\r\nBundel C niet toegankelijk",null,null,67553,"2023-12-15",0,"5,6"]
[null,"Infrabel","78205","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2025,2025,9,10,"2025-02-28",45644.989583333336,"2025-03-03",45644.229166666664,"2d, 05:45h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-075 : Travaux RER\r\nremplace COLT 59176 et UPM 488055\r\n\r\nNew UPM: 505517",null,null,78205,"2024-10-09",0,"5,6"]
[null,"Infrabel","72753","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2025,2025,9,9,"2025-02-28",45644.368055555555,"2025-02-28",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72753,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","53237","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,9,10,"2025-02-28",45644.923611111109,"2025-03-03",45644.194444444445,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de rails \r\n+ Travaux OA \r\n+ Chantier SPW PS 65.090\r\nTCR 488719",null,null,53237,"2024-09-17",1,"5,6"]
[null,"Infrabel","70013","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2025,2025,9,9,"2025-03-01",45644.333333333336,"2025-03-02",45644.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nTCR 507472",null,null,70013,"2024-10-09",0,"5,6"]
[null,"Infrabel","84225","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,9,9,"2025-03-01",45644.979166666664,"2025-03-02",45644.229166666664,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Déchargement de longs rails soudés dans le tronçon Manage-Luttre pour chantier Luttre 2025. ",null,null,84225,"2024-12-16",0,"5,6"]
[null,"Infrabel","74857","Namur - Antwerpen","< >","DENDERMONDE","LONDERZEEL",2025,2025,9,9,"2025-03-01",45644.979166666664,"2025-03-02",45644.222222222219,"1d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P208 waterhuishouding - TCR 492756",null,null,74857,"2024-07-19",0,"5,6"]
[null,"Infrabel","72257","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,9,10,"2025-03-01",45644.979166666664,"2025-03-03",45644.166666666664,"1d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug  L15 km 6.027 BX L15 en L27A\r\n\r\n\r\nalternatief voor geweigerde L15+L27A",null,null,72257,"2024-02-29",1,"5,6"]
[null,"Infrabel","84177","Lille - ZeeBrugge",">","Y.KORTRIJK-WEST","Y.LEIEBRUG",2025,2025,9,9,"2025-03-01",45644.916666666664,"2025-03-02",45644.25,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-239\r\nR-529897\r\nuitbreiding op R-493378\r\nlossen ballast\r\n",null,null,84177,"2024-11-25",0,"5,6"]
[null,"Infrabel","54819","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,9,10,"2025-03-01",45644.965277777781,"2025-03-03",45644.208333333336,"2d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses\r\nTCR: 490613",null,null,54819,"2024-10-03",0,"5,6"]
[null,"Infrabel","53526","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,9,9,"2025-03-01",45644.986111111109,"2025-03-02",45644.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nMini CTL\r\nTCR: 491719",null,null,53526,"2024-09-17",1,"5,6"]
[null,"Infrabel","54889","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2025,2025,9,9,"2025-03-01",45644.986111111109,"2025-03-02",45644.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+ Visites voie B Flawine/Auvelais\r\nUPM: 489075",null,null,54889,"2024-10-10",1,"5,6"]
[null,"Infrabel","60187","Lille - Antwerpen","< >","Y.MELSELE","Y.OOST BERCHEM",2025,2025,9,10,"2025-03-01",45644.041666666664,"2025-03-03",45644.1875,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Stationsproject Antwerpen-Zuid B-Stations:\r\n\r\nBrugdek boven L59",null,null,60187,"2024-10-23",1,"5,6"]
[null,"Infrabel","74099","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2025,2025,9,9,"2025-03-01",45644.996527777781,"2025-03-02",45644.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B - TCR 495737",null,null,74099,"2024-07-19",0,"5,6"]
[null,"Infrabel","69348","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,9,9,"2025-03-01",45644.993055555555,"2025-03-02",45644.208333333336,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossen rails vernieuwingswerken april/mei 2025",null,null,69348,"2024-11-12",0,"5,6"]
[null,"Infrabel","68754","Namur - Antwerpen","< >","FRONT. FLANDRE-WALLONIE L139","LEUVEN",2025,2025,9,10,"2025-03-01",45644.003472222219,"2025-03-03",45644.208333333336,"2d, 04:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Buitenwerken, BDS, meewerken mogelijk\r\nETCS Baanvak Heverlee – St-Joris-Weert (doorsteken e.d.) + grid St-Joris-Weert\r\nverspreid over jaar (niet in januari)",null,null,68754,"2023-08-30",1,"5,6"]
[null,"Infrabel","72748","Athus - Meuse",">","ARLON","Y.AUTELBAS",2025,2025,9,9,"2025-03-01",45644.361111111109,"2025-03-01",45644.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72748,"2024-10-11",0,"5,6"]
[null,"Infrabel","70474","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2025,2025,9,9,"2025-03-01",45644.326388888891,"2025-03-01",45644.722222222219,"1d, 09:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen Oost - Antwerpen - Schijnpoort",null,null,70474,"2024-10-09",0,"5,6"]
[null,"Infrabel","69067","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2025,2025,9,9,"2025-03-02",45644.333333333336,"2025-03-02",45644.618055555555,"1d, 06:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130 Flawinne - Moustier VA/VB\r\nUPM: 489009",null,null,69067,"2024-10-10",0,"5,6"]
[null,"Infrabel","72751","Athus - Meuse",">","MARBEHAN","HABAY",2025,2025,9,9,"2025-03-02",45644.375,"2025-03-02",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72751,"2024-10-11",0,"5,6"]
[null,"Infrabel","75041","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2025,2025,10,10,"2025-03-03",45644.958333333336,"2025-03-07",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux d'entretien en P3 HKV",null,null,75041,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","63169","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2025,2025,10,10,"2025-03-03",45644.958333333336,"2025-03-08",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,63169,"2024-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","72144","Namur - Antwerpen","< >","LEUVEN","WAVRE",2025,2025,10,10,"2025-03-03",45644.958333333336,"2025-03-08",45644.215277777781,"5d, 06:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKV",null,null,72144,"2024-04-11",0,"1,2,3,4,5"]
[null,"Infrabel","72088","Namur - Antwerpen","< >","Y.HEIKE","DENDERMONDE",2025,2025,10,10,"2025-03-03",45644.958333333336,"2025-03-08",45644.204861111109,"5d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z79.33 - TCR 499295\r\nFDR SPIII-IV tot FM SP III inbegrepen",null,null,72088,"2024-08-19",0,"1,2,3,4,5"]
[null,"Infrabel","72903","Athus - Meuse",">","BERTRIX","STRAIMONT",2025,2025,10,10,"2025-03-03",45644.333333333336,"2025-03-03",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,72903,"2024-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","71351","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,10,10,"2025-03-03",45644.979166666664,"2025-03-08",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters: Stap 32 bis aanleg bovenleiding wisselverbinding 19AH-19BH +20AH/20BH\r\n\r\nPerronsporen I tot VI BDS \r\nTLO L 50E tussen Gent Sint Pieters en Y. West Driehoek Ledeberg \r\nSpoor B L 50 tussen Gent Sint Pieters en Y. West Driehoe",null,null,71351,"2023-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","70068","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","Y.LEMAN",2025,2025,10,10,"2025-03-03",45644.951388888891,"2025-03-07",45644.201388888891,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Z9.41 - P3 maintenance AI41",null,null,70068,"2024-10-09",0,"1,2,3,4,5"]
[null,"Infrabel","66535","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","LAUWE",2025,2025,10,10,"2025-03-03",45644.951388888891,"2025-03-08",45644.236111111109,"5d, 06:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z3.54\r\n+ Maintenance Z8.54",null,null,66535,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","65560","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,10,10,"2025-03-03",45644.965277777781,"2025-03-07",45644.201388888891,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Blankenberge vernieuwen wissels - TCR 494990\r\n\r\n*gevallen 29534-29542-29543-29544\r\n*R5/R6 in weekend TLO",null,null,65560,"2024-07-22",0,"1,2,3,4,5"]
[null,"Infrabel","70960","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,10,10,"2025-03-03",45644.965277777781,"2025-03-07",45644.1875,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 04.35.01 HKV - TCR 500377\r\n\r\nL66 FLC-Y Kortrijk West niet inbegrepen\r\nFLC SP III-IV-V inbegrepen\r\nR5/R6 niet inbegrepen wegens WE TLO L50/53/122",null,null,70960,"2024-08-05",0,"1,2,3,4,5"]
[null,"Infrabel","78631","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2025,2025,10,10,"2025-03-03",45644.965277777781,"2025-03-08",45644.208333333336,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des CV\r\nUPM: 507240",null,null,78631,"2024-10-14",0,"1,2,3,4,5"]
[null,"Infrabel","68052","Namur - Antwerpen",">","FARCIENNES","CHATELET",2025,2025,10,10,"2025-03-03",45644.965277777781,"2025-03-08",45644.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTCR: 490615\r\nCR2025_046_V02: extension de la coupure jusqu'au Campinaire inclus",null,null,68052,"2024-10-14",0,"1,2,3,4,5"]
[null,"Infrabel","67036","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,10,10,"2025-03-03",45644.965277777781,"2025-03-08",45644.243055555555,"5d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose poteaux caténaire sur L144. (entre L130 et PN10)",null,null,67036,"2024-10-17",0,"1,2,3,4,5"]
[null,"Infrabel","56116","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,10,10,"2025-03-03",45644.375,"2025-03-07",45644.645833333336,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement de Luttre - phase 2025\r\nPréparations caténaires, I-E.20 > quai III\r\n+ révision à mi-vie caténaire L117, I-E.20 > TX-H.11\r\nTCR: 488777",null,null,56116,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","71705","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,10,10,"2025-03-03",45644.361111111109,"2025-03-03",45644.645833333336,"1d, 06:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance\r\nTCR 507125",null,null,71705,"2024-10-17",0,"1,2,3,4,5"]
[null,"Infrabel","67023","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,10,10,"2025-03-03",45644.923611111109,"2025-03-07",45644.194444444445,"4d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de rails \r\n+ Travaux OA \r\n+ Chantier SPW PS 65.090\r\nTCR 488721",null,null,67023,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","77254","Athus - Meuse",">","HOUYET","BEAURAING",2025,2025,10,10,"2025-03-03",45644.388888888891,"2025-03-03",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,77254,"2024-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","72375","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2025,2025,10,10,"2025-03-03",45644.381944444445,"2025-03-03",45644.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41",null,null,72375,"2024-10-10",0,"1,2,3,4,5"]
[null,"Infrabel","67891","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,10,10,"2025-03-04",45644.020833333336,"2025-03-08",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67891,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","70566","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,10,10,"2025-03-04",45644.986111111109,"2025-03-06",45644.236111111109,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen van Y Arendstraat",null,null,70566,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","68657","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2025,2025,10,10,"2025-03-04",45644.989583333336,"2025-03-07",45644.208333333336,"3d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons\r\nVA L.24/1 entre Visé et Y.Longchamp compris\r\nVoies à quai 551 et 552 de visé comprises",null,null,68657,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","70576","Namur - Antwerpen","< >","Y.BERCHEM-STADION","Y.ARENDSTRAAT",2025,2025,10,10,"2025-03-04",45644.083333333336,"2025-03-06",45644.125,"3d, 01:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen van Y Noord Berchem",null,null,70576,"2024-06-26",0,"1,2,3,4,5"]
[null,"Infrabel","72712","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,10,10,"2025-03-04",45644.003472222219,"2025-03-08",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72712,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","72904","Athus - Meuse",">","STRAIMONT","BERTRIX",2025,2025,10,10,"2025-03-04",45644.375,"2025-03-04",45644.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,72904,"2024-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","77255","Athus - Meuse",">","BEAURAING","HOUYET",2025,2025,10,10,"2025-03-04",45644.388888888891,"2025-03-04",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,77255,"2024-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","67817","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2025,2025,10,10,"2025-03-05",45644.333333333336,"2025-03-05",45644.4375,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11",null,null,67817,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","71315","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,10,10,"2025-03-06",45644.333333333336,"2025-03-06",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,71315,"2024-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","71317","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2025,2025,10,10,"2025-03-07",45644.333333333336,"2025-03-07",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,71317,"2024-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","68305","Lille - Antwerpen",">","KORTRIJK","KORTRIJK-RINGLAAN",2025,2025,10,11,"2025-03-07",45644.979166666664,"2025-03-10",45644.166666666664,"2d, 04:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwen lopend spoor van Bundel C naar Y Bethune - bundel C Buiten dienst+Onderhoud TCR 493889\r\n\r\nBundels Kortrijk bereikbaar kant Moeskroen\r\nBundel C niet toegankelijk",null,null,68305,"2024-07-22",0,"5,6"]
[null,"Infrabel","65566","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,10,11,"2025-03-07",45644.965277777781,"2025-03-10",45644.201388888891,"2d, 05:40h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Blankenberge vernieuwen wissels TCR 494992\r\nDOES tss Y Bl Toren en Blankenberge\r\nSP B BD van sein O-U.7 tot SP II Blankenberge inbegrepen\r\nSP III+IV+V+VI+VII buiten dienst\r\nBundel M niet bereikbaar\r\n\r\n*gevallen 29534-29542-29543-29544-29532-29541",null,null,65566,"2024-07-22",0,"5,6"]
[null,"Infrabel","67021","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,10,11,"2025-03-07",45644.923611111109,"2025-03-10",45644.194444444445,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de rails \r\n+ Travaux OA \r\n+ Chantier SPW PS 65.090\r\nTCR 488723",null,null,67021,"2024-10-07",1,"5,6"]
[null,"Infrabel","70823","Erquelinnes - Montzen",">","AMAY","ENGIS",2025,2025,10,10,"2025-03-08",45644.333333333336,"2025-03-08",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70823,"2024-10-09",0,"1,2,3,4,5"]
[null,"Infrabel","72335","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,10,11,"2025-03-08",45644.979166666664,"2025-03-10",45644.166666666664,"1d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug  L15 km 6.027 BX L15 en L27A\r\n\r\n\r\nalternatief voor geweigerde L15+L27A",null,null,72335,"2024-03-12",1,"5,6"]
[null,"Infrabel","66625","Athus - Meuse","< >","BOIS D'AUSSE","BRAIBANT",2025,2025,10,11,"2025-03-08",45644.020833333336,"2025-03-10",45644.180555555555,"2d, 03:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Réalisation d’une chape sur le PI bk 86.264. \r\nUPM 490272",null,null,66625,"2024-10-21",1,"5,6"]
[null,"Infrabel","64218","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,10,11,"2025-03-08",45644.965277777781,"2025-03-10",45644.208333333336,"2d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses\r\nTCR: 490661\r\nCR2025_046_V02",null,null,64218,"2024-10-14",0,"5,6"]
[null,"Infrabel","56123","Namur - Antwerpen","< >","ESSEN-GRENS","KAPELLEN",2025,2025,10,11,"2025-03-08",45644.25,"2025-03-10",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie\r\nCf Escalade Head Of nov/dec 2023",null,null,56123,"2024-10-11",1,"5,6"]
[null,"Infrabel","69426","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,10,11,"2025-03-08",45644.000694444447,"2025-03-10",45644.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Migratie tunnelveiligheidstechnieken Antw. NZ -1\r\nAntwerpen-Berchem - Antwerpen-Centraal\r\nCf Escalade Head Of nov/dec 2023",null,null,69426,"2023-12-04",1,"5,6"]
[null,"Infrabel","68755","Namur - Antwerpen","< >","FRONT. FLANDRE-WALLONIE L139","LEUVEN",2025,2025,10,11,"2025-03-08",45644.003472222219,"2025-03-10",45644.208333333336,"2d, 04:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Buitenwerken, BDS, meewerken mogelijk\r\nETCS Baanvak Heverlee – St-Joris-Weert (doorsteken e.d.) + grid St-Joris-Weert",null,null,68755,"2023-08-30",1,"5,6"]
[null,"Infrabel","68795","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,10,10,"2025-03-08",45644.354166666664,"2025-03-08",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie A Ottignies - Gembloux (extension Rhisnes SAS)\r\nUPM: 488028",null,null,68795,"2024-10-17",0,"5,6"]
[null,"Infrabel","68796","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,10,10,"2025-03-09",45644.333333333336,"2025-03-09",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie B Ottignies - Gembloux (extension Rhisnes SAS)\r\nUPM: 488044",null,null,68796,"2024-10-17",0,"5,6"]
[null,"Infrabel","67316","Namur - Antwerpen","< >","Y.SCHIJN","ANTWERPEN-D.S.-RHODESIE",2025,2025,10,10,"2025-03-09",45644.25,"2025-03-09",45644.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,67316,"2024-03-27",1,"5,6"]
[null,"Infrabel","70824","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2025,2025,10,10,"2025-03-09",45644.354166666664,"2025-03-09",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,70824,"2024-10-10",0,"5,6"]
[null,"Infrabel","67038","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,11,11,"2025-03-10",45644.958333333336,"2025-03-15",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose de console L144-L130\r\nUPM: 488638",null,null,67038,"2024-10-22",0,"1,2,3,4,5"]
[null,"Infrabel","63170","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2025,2025,11,11,"2025-03-10",45644.958333333336,"2025-03-15",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,63170,"2024-10-21",0,"1,2,3,4,5"]
[null,"Infrabel","80739","Lille - ZeeBrugge","< >","BRUGGE","BRUGGE-ROOSTER E",2025,2025,11,11,"2025-03-10",45644.333333333336,"2025-03-11",45644.645833333336,"2d, 07:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-156\r\nR-518963-xx\r\nwerkveld 3411-21\r\nmassificatie onderhoud Tracks&Signaling",null,null,80739,"2024-10-02",0,"1,2,3,4,5"]
[null,"Infrabel","55768","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2025,2025,11,11,"2025-03-10",45644.333333333336,"2025-03-11",45644.958333333336,"2d, 15:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre - travaux pour remise en service\r\nUPM: 488525",null,null,55768,"2024-10-28",0,"1,2,3,4,5"]
[null,"Infrabel","57823","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,11,13,"2025-03-10",45644.333333333336,"2025-03-29",45644.333333333336,"19d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Stabilisation paroi rocheuse VA entre 89.200 et 90.000\r\n+ Visites VA\r\nUPM:488478",null,null,57823,"2024-10-21",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","72713","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,11,11,"2025-03-10",45644.979166666664,"2025-03-15",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72713,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","65561","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,11,11,"2025-03-10",45644.965277777781,"2025-03-15",45644.201388888891,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Blankenberge vernieuwen wissels  - TCR 494993\r\n\r\n*gevallen 29534-29542-29543-29544\r\n*R5/R6 in weekend TLO",null,null,65561,"2024-07-22",0,"1,2,3,4,5"]
[null,"Infrabel","72360","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2025,2025,11,11,"2025-03-10",45644.965277777781,"2025-03-15",45644.1875,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massification\r\nMaintenance Z2.44\r\nTCR 507154",null,null,72360,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","68053","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET-GRIL OUEST",2025,2025,11,11,"2025-03-10",45644.965277777781,"2025-03-15",45644.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTCR: 490664\r\nCR2025_046_V02: L130 Voie B HS CHATELET-GRIL Est et CHATELET-GRIL OUEST",null,null,68053,"2024-10-14",0,"1,2,3,4,5"]
[null,"Infrabel","68723","Lille - Charleroi","< >","Y.NOORD HALLE","SAINTES",2025,2025,11,11,"2025-03-10",45644.986111111109,"2025-03-14",45644.180555555555,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone FH_10 Area CE volgens onderhoudskalender 2025\r\nOnderhoudswerken L94 tussen perrons Halle en Grens Vlaanderen-Wallonië.",null,null,68723,"2024-02-05",0,"1,2,3,4,5"]
[null,"Infrabel","59617","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,11,11,"2025-03-10",45644.993055555555,"2025-03-14",45644.177083333336,"4d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n3 - Réalisation de massifs et pose de poteaux\r\nUPM: 487901",null,null,59617,"2024-10-22",0,"1,2,3,4,5"]
[null,"Infrabel","71876","Namur - Antwerpen","< >","Y.HEIKE","MECHELEN",2025,2025,11,11,"2025-03-10",45644.993055555555,"2025-03-14",45644.211805555555,"4d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71876,"2024-04-11",0,"1,2,3,4,5"]
[null,"Infrabel","71620","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,11,11,"2025-03-10",45644.993055555555,"2025-03-15",45644.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK",null,null,71620,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","53518","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,11,11,"2025-03-10",45644.909722222219,"2025-03-14",45644.229166666664,"4d, 07:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z8.52 P3 HKV",null,null,53518,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","53497","Lille - Charleroi","< >","Y.JURBISE","MONS",2025,2025,11,11,"2025-03-10",45644.947916666664,"2025-03-15",45644.173611111109,"5d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.5.53 P3 HKV",null,null,53497,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","56117","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,11,11,"2025-03-10",45644.375,"2025-03-14",45644.645833333336,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement de Luttre - phase 2025\r\nPréparations caténaires, IX-E.20 > quai IV\r\n+ révision à mi-vie caténaire L117, IX-E.20 > T-H.11\r\nTCR: 488932",null,null,56117,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","71882","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,11,11,"2025-03-10",45644.975694444445,"2025-03-14",45644.208333333336,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71882,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","72795","Namur - Antwerpen","< >","ROGIER","WATERMAEL",2025,2025,11,11,"2025-03-10",45644.982638888891,"2025-03-15",45644.166666666664,"5d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_01 Area CE volgens onderhoudskalender 2025.\r\n\r\nBuitendienststelling L161 voor onderhoudswerken.\r\nBijkomend L161A tussen Y Jubelpark en Y Watermaal, L26/4 tussen Etterbeek en Y Boondaal en L26/2 MTB-Y MTB\r\nR5/R6 stoppen om 04u00 voor M",null,null,72795,"2024-10-21",0,"1,2,3,4,5"]
[null,"Infrabel","53511","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.ECAUSSINNES",2025,2025,11,11,"2025-03-11",45644.020833333336,"2025-03-14",45644.229166666664,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.3 courte.53 en P3 HKM",null,null,53511,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","67893","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,11,11,"2025-03-11",45644.020833333336,"2025-03-15",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67893,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","70488","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,11,11,"2025-03-12",45644.375,"2025-03-12",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y-Holland",null,null,70488,"2024-02-14",0,"1,2,3,4,5"]
[null,"Infrabel","70813","Erquelinnes - Montzen",">","JAVA","STATTE",2025,2025,11,11,"2025-03-12",45644.354166666664,"2025-03-12",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70813,"2024-10-22",0,"1,2,3,4,5"]
[null,"Infrabel","70815","Erquelinnes - Montzen",">","JAVA","ANDENNE",2025,2025,11,11,"2025-03-13",45644.5625,"2025-03-13",45644.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70815,"2024-10-22",0,"1,2,3,4,5"]
[null,"Infrabel","70615","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2025,2025,11,11,"2025-03-13",45644.375,"2025-03-13",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen - Schijnpoort + inrit bundel Q",null,null,70615,"2024-03-13",0,"1,2,3,4,5"]
[null,"Infrabel","70814","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2025,2025,11,11,"2025-03-13",45644.375,"2025-03-13",45644.517361111109,"1d, 03:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70814,"2024-10-22",0,"1,2,3,4,5"]
[null,"Infrabel","71074","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,11,11,"2025-03-14",45644.958333333336,"2025-03-15",45644.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nZ5.43",null,null,71074,"2024-10-22",0,"1,2,3,4,5"]
[null,"Infrabel","78895","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,11,12,"2025-03-14",45644.972222222219,"2025-03-17",45644.201388888891,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-078\r\nR-508004-xx\r\nSaneren vormlaag",null,null,78895,"2024-09-16",1,"5,6"]
[null,"Infrabel","68722","Lille - Charleroi","< >","Y.NOORD HALLE","SAINTES",2025,2025,11,12,"2025-03-14",45644.993055555555,"2025-03-17",45644.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken zone FH_10 volgens onderhoudskalender",null,null,68722,"2024-11-12",1,"5,6"]
[null,"Infrabel","70628","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,11,11,"2025-03-14",45644.375,"2025-03-14",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y Holland + inrit bundel Q",null,null,70628,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","55767","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2025,2025,11,12,"2025-03-15",45644.979166666664,"2025-03-17",45644.229166666664,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre - contraintes, finitions (1)\r\nUPM: 488535",null,null,55767,"2024-11-04",0,"5,6"]
[null,"Infrabel","82414","Athus - Meuse","< >","BOIS D'AUSSE","BRAIBANT",2025,2025,11,12,"2025-03-15",45644.020833333336,"2025-03-17",45644.180555555555,"2d, 03:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Réalisation d’une chape sur le PI bk 86.264. \r\nUPM 522036\r\n",null,null,82414,"2024-10-22",1,"5,6"]
[null,"Infrabel","64219","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,11,12,"2025-03-15",45644.965277777781,"2025-03-17",45644.208333333336,"2d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses\r\nTCR: 490691",null,null,64219,"2024-10-14",0,"5,6"]
[null,"Infrabel","64984","Namur - Antwerpen","< >","TILLY-GARAGE","CHARLEROI-OUEST",2025,2025,11,12,"2025-03-15",45644.25,"2025-03-17",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement CV en gare de Fleurus\r\nTCR: 488068",null,null,64984,"2024-10-14",1,"5,6"]
[null,"Infrabel","69754","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,11,12,"2025-03-15",45644.25,"2025-03-17",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"sporen 5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde",null,null,69754,"2023-08-30",1,"5,6"]
[null,"Infrabel","72546","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,11,11,"2025-03-15",45644.3125,"2025-03-15",45644.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72546,"2024-10-11",0,"5,6"]
[null,"Infrabel","68378","Lille - Antwerpen",">","Y.WEST BERCHEM","ZWIJNDRECHT-ROOSTER D",2025,2025,11,12,"2025-03-15",45644.041666666664,"2025-03-17",45644.1875,"2d, 03:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Stationsproject Antwerpen-Zuid B-Stations:\r\nTrapconstructie op perron\r\nCf Escalade Head Of nov/dec 2023",null,null,68378,"2024-10-11",0,"5,6"]
[null,"Infrabel","53491","Lille - Charleroi","< >","Y.JURBISE","MONS",2025,2025,11,11,"2025-03-15",45644.173611111109,"2025-03-16",45644.708333333336,"2d, 12:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.5.53 P4+ + Visite Diagno Z5V\r\nTCR 488843",null,null,53491,"2024-10-07",1,"5,6"]
[null,"Infrabel","70816","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2025,2025,11,11,"2025-03-15",45644.354166666664,"2025-03-15",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70816,"2024-10-22",0,"5,6"]
[null,"Infrabel","75340","Lille - Antwerpen",">","SINT-NIKLAAS","LOKEREN",2025,2025,11,11,"2025-03-15",45644.017361111109,"2025-03-15",45644.21875,"1d, 04:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Reservatie onderhoud - TCR 500398",null,null,75340,"2024-07-23",0,"1,2,3,4,5"]
[null,"Infrabel","70538","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2025,2025,11,11,"2025-03-16",45644.291666666664,"2025-03-16",45644.666666666664,"1d, 09:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Kleine vernieuwingen lopend spoor en wissels\r\n+\r\ninstandhouding kunstwerken (CIV)",null,null,70538,"2024-03-08",0,"5,6"]
[null,"Infrabel","72557","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,11,11,"2025-03-16",45644.3125,"2025-03-16",45644.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72557,"2024-10-11",0,"5,6"]
[null,"Infrabel","68041","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,11,11,"2025-03-16",45644.034722222219,"2025-03-16",45644.243055555555,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68041,"2024-02-23",0,"5,6"]
[null,"Infrabel","71112","Namur - Antwerpen","< >","NAMUR","RONET",2025,2025,11,11,"2025-03-16",45644.003472222219,"2025-03-16",45644.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur ZONE 6\r\nZ6.43\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,71112,"2024-10-22",0,"5,6"]
[null,"Infrabel","70817","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2025,2025,11,11,"2025-03-16",45644.354166666664,"2025-03-16",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70817,"2024-10-22",0,"5,6"]
[null,"Infrabel","80267","Athus - Meuse",">","HAVERSIN","MARLOIE",2025,2025,11,11,"2025-03-16",45644.364583333336,"2025-03-16",45644.666666666664,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-085 \r\nVisite périodique de jour le dimanche pour AI45. (suite mise en service ETCS)\r\nVA: Le dimanche entre 08h45 et 16h00\r\nVB: Le dimanche entre 08h00 et 15h15\r\nA dupliquer toutes les 8 semaines.",null,null,80267,"2024-10-21",0,"5,6"]
[null,"Infrabel","71696","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2025,2025,11,11,"2025-03-16",45644.329861111109,"2025-03-16",45644.545138888891,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nOttignies gare  voie 1 à 5 en alternance\r\nTCR 507142",null,null,71696,"2024-10-28",0,"5,6"]
[null,"Infrabel","68066","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,12,12,"2025-03-17",45644.958333333336,"2025-03-21",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose de console L144-L130\r\nUPM: 488649",null,null,68066,"2024-10-30",0,"1,2,3,4,5"]
[null,"Infrabel","63171","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2025,2025,12,12,"2025-03-17",45644.958333333336,"2025-03-22",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,63171,"2024-10-29",0,"1,2,3,4,5"]
[null,"Infrabel","70190","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,12,12,"2025-03-17",45644.958333333336,"2025-03-22",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails, attaches...",null,null,70190,"2024-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","71744","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2025,2025,12,12,"2025-03-17",45644.333333333336,"2025-03-17",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 116 à 121 + faisceau manage\r\nNe fonctionne plus en Phase 5\r\nTCR 507080",null,null,71744,"2024-10-31",0,"1,2,3,4,5"]
[null,"Infrabel","72714","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,12,12,"2025-03-17",45644.979166666664,"2025-03-22",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72714,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","68950","Lille - Charleroi","< >","Y.NOORD HALLE","TUBIZE",2025,2025,12,12,"2025-03-17",45644.972222222219,"2025-03-22",45644.194444444445,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone FH_11 volgens onderhoudskalender Area CE\r\nTLO op L96",null,null,68950,"2024-02-05",0,"1,2,3,4,5"]
[null,"Infrabel","69454","Erquelinnes - Montzen",">","HERMALLE-SOUS-HUY","AMAY",2025,2025,12,12,"2025-03-17",45644.9375,"2025-03-21",45644.208333333336,"4d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien caténaire\r\n",null,null,69454,"2024-10-17",0,"1,2,3,4,5"]
[null,"Infrabel","65562","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,12,12,"2025-03-17",45644.965277777781,"2025-03-22",45644.201388888891,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Blankenberge vernieuwen wissels - TCR 494994\r\n\r\n*gevallen 29534-29542-29543-29544\r\n",null,null,65562,"2024-07-23",0,"1,2,3,4,5"]
[null,"Infrabel","66399","Lille - Charleroi","< >","LEMBEEK","BRAINE-LE-COMTE",2025,2025,12,12,"2025-03-17",45644.965277777781,"2025-03-22",45644.194444444445,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.53 P3 HKV",null,null,66399,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","68054","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET",2025,2025,12,12,"2025-03-17",45644.965277777781,"2025-03-22",45644.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTCR: 490693\r\nCR2025_046_V02",null,null,68054,"2024-10-14",0,"1,2,3,4,5"]
[null,"Infrabel","72798","Lille - Charleroi",">","BRUXELLES-MIDI","BRUXELLES-MIDI",2025,2025,12,12,"2025-03-17",45644.986111111109,"2025-03-22",45644.201388888891,"5d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoudswerken volgens onderhoudskalender Area Ce\r\nOnderhoudszone FBMZ_05, perronsporen 16+17 FBMZ",null,null,72798,"2024-10-21",0,"1,2,3,4,5"]
[null,"Infrabel","72178","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2025,2025,12,12,"2025-03-17",45644.996527777781,"2025-03-21",45644.1875,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKM",null,null,72178,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","71239","Namur - Antwerpen","< >","Y.NAZARETH","HEIST-OP-DEN-BERG",2025,2025,12,12,"2025-03-17",45644.996527777781,"2025-03-22",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKM ZBB.23",null,null,71239,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","71621","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,12,12,"2025-03-17",45644.993055555555,"2025-03-22",45644.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK",null,null,71621,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","68039","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,12,12,"2025-03-17",45644.034722222219,"2025-03-17",45644.201388888891,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68039,"2024-02-23",0,"5,6"]
[null,"Infrabel","67894","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,12,12,"2025-03-18",45644.020833333336,"2025-03-22",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67894,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","72797","Namur - Antwerpen","< >","ROGIER","WATERMAEL",2025,2025,12,12,"2025-03-18",45644.982638888891,"2025-03-22",45644.166666666664,"4d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_01 Area CE volgens onderhoudskalender 2025.\r\n\r\nBuitendienststelling L161 voor onderhoudswerken.\r\nBijkomend L161A tussen Y Jubelpark en Y Watermaal, L26/4 tussen Etterbeek en Y Boondaal en L26/2 MTB-Y MTB\r\nR5/R6 stoppen om 04u00 voor M",null,null,72797,"2024-10-21",0,"1,2,3,4,5"]
[null,"Infrabel","78896","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,12,13,"2025-03-21",45644.972222222219,"2025-03-24",45644.201388888891,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-078\r\nR-508005-xx\r\nSaneren vormlaag",null,null,78896,"2024-09-16",1,"5,6"]
[null,"Infrabel","67025","Namur - Antwerpen","< >","CHARLEROI-OUEST","FLEURUS",2025,2025,12,13,"2025-03-21",45644.965277777781,"2025-03-24",45644.215277777781,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement CV\r\nTCR: 488069",null,null,67025,"2024-10-14",1,"5,6"]
[null,"Infrabel","78206","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2025,2025,12,13,"2025-03-21",45644.989583333336,"2025-03-24",45644.229166666664,"2d, 05:45h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-075 : Travaux RER\r\n\r\nUPM: 505518",null,null,78206,"2024-10-31",0,"5,6"]
[null,"Infrabel","69377","Athus - Meuse","< >","DINANT","Y.NEFFE",2025,2025,12,12,"2025-03-22",45644.958333333336,"2025-03-23",45644.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mise au gabarit des pistes de circulation\r\nSécurisation des parois rocheuses \r\nRenouvellement PI BK 13808\r\nCR 2025-054\r\nVisite VB\r\nUPM:508166",null,null,69377,"2024-10-29",1,"5,6"]
[null,"Infrabel","55771","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2025,2025,12,13,"2025-03-22",45644.979166666664,"2025-03-24",45644.229166666664,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre \r\ncontraintes, finitions (2) suppression ART\r\nUPM: 488540",null,null,55771,"2024-11-04",0,"5,6"]
[null,"Infrabel","64220","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,12,12,"2025-03-22",45644.965277777781,"2025-03-23",45644.208333333336,"1d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL la nuit de Sa^Di uniquement\r\nPose traverses\r\nTCR: 491042",null,null,64220,"2024-10-14",0,"5,6"]
[null,"Infrabel","70458","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,12,12,"2025-03-22",45644.291666666664,"2025-03-23",45644.708333333336,"2d, 10:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels en sporen te Antwerpen Schijnpoort inrit bundel F",null,null,70458,"2024-04-30",0,"5,6"]
[null,"Infrabel","65804","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2025,2025,12,12,"2025-03-22",45644.25,"2025-03-23",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.51 P4\r\nTCR: 488082\r\nCR_EF's HKM-2025-001: déplacer au WE12 et deux voies disponible à Fleurus",null,null,65804,"2024-10-14",1,"5,6"]
[null,"Infrabel","68383","Lille - Antwerpen",">","Y.WEST BERCHEM","ZWIJNDRECHT-ROOSTER D",2025,2025,12,13,"2025-03-22",45644.041666666664,"2025-03-24",45644.1875,"2d, 03:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Stationsproject Antwerpen-Zuid B-Stations:\r\nTrapconstructie op perron\r\nCf Escalade Head Of nov/dec 2023",null,null,68383,"2024-05-17",0,"5,6"]
[null,"Infrabel","53463","Lille - Charleroi",">","TUBIZE","BRAINE-LE-COMTE",2025,2025,12,13,"2025-03-22",45644.194444444445,"2025-03-24",45644.1875,"2d, 23:50h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification entre Lembeek et Braine-le-Comte\r\nWE SAVU\r\nTCR 491279",null,null,53463,"2024-10-07",0,"5,6"]
[null,"Infrabel","70007","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2025,2025,12,12,"2025-03-23",45644.333333333336,"2025-03-23",45644.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144-130/1\r\nTCR 507098",null,null,70007,"2024-11-04",0,"5,6"]
[null,"Infrabel","84384","Lille - Antwerpen","< >","BEERVELDE","GENT-DAMPOORT",2025,2025,12,12,"2025-03-23",45644.03125,"2025-03-23",45644.215277777781,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"In dienst stelling ETCS - TCR 531519\r\nMeewerken niet mogelijk\r\nL59 Gent Dampoort - Lokeren (v) 00.45 - 05.30\r\nL58 - Eeklo Niet in tot Y Oost Driehoek Ledeberg IN - 00.45 tot 05.50\r\nL58/1 - Y Noord Driehoek ledeberg IN tot Y West Driehoek Ledeberg IN - 0",null,null,84384,"2024-12-05",0,"5,6"]
[null,"Infrabel","79756","Lille - Charleroi","< >","HALLE","QUEVY-FRONTIERE",2025,2025,12,12,"2025-03-23",45644.020833333336,"2025-03-23",45644.1875,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Mise hors service de l’ensemble de la zone EBP FMS \r\nEBP - Hardware Equipment Maintenance : \"Renewal Network Devices\".\r\nMise hors service du poste de signalisation - (Computer Room)  et de la zone EBP correspondante pendant 04h00 pour laquelle l'arrêt c",null,null,79756,"2024-10-30",0,"5,6"]
[null,"Infrabel","64934","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2025,2025,12,12,"2025-03-23",45644.3125,"2025-03-23",45644.520833333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Noord\r\nBuitendienststellen van de van de volledige overeenkomstige EBP-zone gedurende minimaal 4 uur te bepalen tussen 06.00 uur en 14.00 uur\r\nUpdate EBP release to last version\r\nR-447116",null,null,64934,"2023-01-27",0,"5,6"]
[null,"Infrabel","84385","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","GENT-DAMPOORT",2025,2025,12,12,"2025-03-23",45644.041666666664,"2025-03-23",45644.166666666664,"1d, 03:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"\r\nIDS P025/26 _RW_P024 - IDS Gent - Denderleeuw-Merelbeke-Bernadettestraat RW L59 Antwerpen-Zuid - Gent-Zeehaven\r\nR-531535",null,null,84385,"2024-12-05",0,"5,6"]
[null,"Infrabel","71842","Namur - Antwerpen","< >","Y.SCHAERBEEK-GROUPE G","VILVOORDE",2025,2025,13,13,"2025-03-24",45644.958333333336,"2025-03-29",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKV",null,null,71842,"2024-01-18",0,"1,2,3,4,5"]
[null,"Infrabel","66186","Lille - Charleroi","< >","LUTTRE","ROUX",2025,2025,13,13,"2025-03-24",45644.979166666664,"2025-03-29",45644.229166666664,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.52 P3\r\nMise HS Zone 5 AI52 (Gare de Luttre)\r\nMassification 53223",null,null,66186,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","65563","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,13,13,"2025-03-24",45644.965277777781,"2025-03-29",45644.201388888891,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Blankenberge vernieuwen wissels TCR 494995\r\n\r\n*gevallen 29534-29542-29543-29544\r\n",null,null,65563,"2024-07-24",0,"1,2,3,4,5"]
[null,"Infrabel","66199","Lille - Charleroi","< >","LEMBEEK","BRAINE-LE-COMTE",2025,2025,13,13,"2025-03-24",45644.965277777781,"2025-03-29",45644.194444444445,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.53 P3",null,null,66199,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","68055","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL EST",2025,2025,13,13,"2025-03-24",45644.965277777781,"2025-03-29",45644.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTCR: 491046\r\nCR046_2025_V02",null,null,68055,"2024-10-14",0,"1,2,3,4,5"]
[null,"Infrabel","59691","Lille - Charleroi","< >","Y.RUISBROEK","Y.NOORD HALLE",2025,2025,13,13,"2025-03-24",45644.986111111109,"2025-03-28",45644.1875,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen BVL L96+L96E zone A4-B4-A5-B5: voorbereiding",null,null,59691,"2023-12-15",0,"1,2,3,4,5"]
[null,"Infrabel","71867","Namur - Antwerpen","< >","LONDERZEEL","Y.HEIKE",2025,2025,13,13,"2025-03-24",45644.993055555555,"2025-03-28",45644.201388888891,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71867,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","71877","Namur - Antwerpen","< >","Y.HEIKE","MECHELEN",2025,2025,13,13,"2025-03-24",45644.993055555555,"2025-03-28",45644.201388888891,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71877,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","59620","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,13,13,"2025-03-24",45644.993055555555,"2025-03-28",45644.177083333336,"4d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n5 - Réalisation de massifs et pose de poteaux\r\nUPM: 487907",null,null,59620,"2024-11-04",0,"1,2,3,4,5"]
[null,"Infrabel","71662","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2025,2025,13,13,"2025-03-24",45644.947916666664,"2025-03-29",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 05.32 - TCR 500417\r\nL58 Eeklo inbegrepen tot Gent Dampoort NIET inbegrepen",null,null,71662,"2024-07-24",0,"1,2,3,4,5"]
[null,"Infrabel","75386","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,13,13,"2025-03-24",45644.395833333336,"2025-03-24",45644.645833333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"DOES Schouwen sporen overdag. - TCR 510882",null,null,75386,"2024-07-24",0,"1,2,3,4,5"]
[null,"Infrabel","67895","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,13,13,"2025-03-25",45644.020833333336,"2025-03-29",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67895,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","72715","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,13,13,"2025-03-25",45644.003472222219,"2025-03-29",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72715,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","70554","Namur - Antwerpen","< >","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL",2025,2025,13,13,"2025-03-27",45644.986111111109,"2025-03-28",45644.236111111109,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen Centraal -1",null,null,70554,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","67461","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,13,13,"2025-03-27",45644.395833333336,"2025-03-27",45644.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nMise HS en P2\r\nTCR 488846",null,null,67461,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","59690","Lille - Charleroi","< >","Y.RUISBROEK","Y.NOORD HALLE",2025,2025,13,14,"2025-03-28",45644.986111111109,"2025-03-31",45644.1875,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen BVL L96+L96E zone A4-B4-A5-B5",null,null,59690,"2024-05-23",1,"5,6"]
[null,"Infrabel","76408","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2025,2025,13,13,"2025-03-28",45644.326388888891,"2025-03-28",45644.645833333336,"1d, 07:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visites J10",null,null,76408,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","69379","Athus - Meuse","< >","DINANT","Y.NEFFE",2025,2025,13,13,"2025-03-29",45644.958333333336,"2025-03-30",45644.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mise au gabarit des pistes de circulation\r\nSécurisation des parois rocheuses \r\nRenouvellement PI BK 13808\r\nCR 2025-054\r\n+ Visite VA\r\nUPM: 508167",null,null,69379,"2024-10-31",1,"5,6"]
[null,"Infrabel","73042","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2025,2025,13,13,"2025-03-29",45644.333333333336,"2025-03-29",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73042,"2024-10-31",0,"5,6"]
[null,"Infrabel","70159","Namur - Antwerpen",">","RHISNES-SAS","GEMBLOUX",2025,2025,13,13,"2025-03-29",45644.333333333336,"2025-03-30",45644.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nTCR 507476",null,null,70159,"2024-11-04",0,"5,6"]
[null,"Infrabel","69707","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,13,14,"2025-03-29",45644,"2025-03-31",45644.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Omvorming 50Hz naar TFSK (L27+L27B+L27B1): \r\n- 1x TLO WE voorbereidende werken maart 2025  (samenwerken ok)\r\n\r\n+\r\nonderhoud",null,null,69707,"2024-10-11",1,"5,6"]
[null,"Infrabel","64221","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,13,14,"2025-03-29",45644.965277777781,"2025-03-31",45644.208333333336,"2d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses\r\nTCR: 493488",null,null,64221,"2024-10-14",0,"5,6"]
[null,"Infrabel","69749","Namur - Antwerpen","< >","Y.SCHAERBEEK-GROUPE G","VILVOORDE",2025,2025,13,14,"2025-03-29",45644.25,"2025-03-31",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"sporen 3+4+5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde",null,null,69749,"2024-01-25",1,"5,6"]
[null,"Infrabel","60156","Namur - Antwerpen","< >","Y.NOORD DRIEHOEK LEDEBERG","GENT-DAMPOORT",2025,2025,13,14,"2025-03-29",45644.25,"2025-03-31",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Instandhouding vertakking Noord-Driehoek Ledeberg - TCR 492277\r\nCf Escalade Head Of nov/dec 2023",null,null,60156,"2024-07-25",1,"5,6"]
[null,"Infrabel","68379","Lille - Antwerpen",">","Y.WEST BERCHEM","ZWIJNDRECHT-ROOSTER D",2025,2025,13,14,"2025-03-29",45644.041666666664,"2025-03-31",45644.1875,"2d, 03:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Stationsproject Antwerpen-Zuid B-Stations:\r\n\r\nTrapconstructie op perron\r\n\r\nIndien weekend 14 DOES L59 niet mogelijk --> lange nachten?",null,null,68379,"2024-05-17",0,"5,6"]
[null,"Infrabel","70475","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2025,2025,13,13,"2025-03-29",45644.326388888891,"2025-03-29",45644.722222222219,"1d, 09:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen Oost - Antwerpen - Schijnpoort",null,null,70475,"2024-02-14",0,"5,6"]
[null,"Infrabel","53464","Lille - Charleroi","< >","LEMBEEK","BRAINE-LE-COMTE",2025,2025,13,14,"2025-03-29",45644.194444444445,"2025-03-31",45644.1875,"2d, 23:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Réélectrification entre Lembeek et Braine-le-Comte\r\nCTL WE\r\n+ Maintenance Z1.53 en P4\r\nTCR 488849",null,null,53464,"2024-10-09",1,"5,6"]
[null,"Infrabel","73063","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,13,13,"2025-03-30",45644.333333333336,"2025-03-30",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite",null,null,73063,"2024-10-31",0,"1,2,3,4,5"]
[null,"Infrabel","68042","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,13,13,"2025-03-30",45644.034722222219,"2025-03-30",45644.243055555555,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68042,"2024-06-27",0,"5,6"]
[null,"Infrabel","71713","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2025,2025,14,14,"2025-03-31",45644.958333333336,"2025-04-04",45644.194444444445,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z73.33.02 - TCR 499313\r\nL53 FCB-FDR - FDR SP I tem IV inbegrepen - Y FCB vrij\r\nR5/R6 niet inbegrepen, conflict CBP (L53 blauw voor werken FBND)",null,null,71713,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","70196","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2025,2025,14,14,"2025-03-31",45644.333333333336,"2025-04-03",45644.625,"4d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"HKC ballast, osv, rails, tunnel avec protection par S460",null,null,70196,"2024-10-24",0,"1,2,3,4,5"]
[null,"Infrabel","73580","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,14,17,"2025-03-31",45644.333333333336,"2025-04-24",45644.666666666664,"24d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Stabilisation paroi rocheuse VA entre 89.200 et 90.000\r\n+Visites VB\r\nUPM:488481",null,null,73580,"2024-11-06",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","74912","Namur - Antwerpen","< >","DENDERMONDE","LONDERZEEL",2025,2025,14,14,"2025-03-31",45644.006944444445,"2025-04-05",45644.201388888891,"6d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P221 Goederencorridors - TCR 492914",null,null,74912,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","72716","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,14,14,"2025-03-31",45644.979166666664,"2025-04-05",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72716,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","56172","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,14,14,"2025-03-31",45644.9375,"2025-04-05",45644.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - phase 2025\r\npréparations caténaires \r\nentre I-E.20/IX-E.20 et K-E.20/KX.E.20\r\n+ révision à mi-vie de la caténaire\r\nentre I-E.20/IX-E.20 et TX-H.11 et T-H.11\r\nTCR: 489099",null,null,56172,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","71624","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,14,14,"2025-03-31",45644.965277777781,"2025-04-04",45644.225694444445,"4d, 06:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud Z02.23.03",null,null,71624,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","68056","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL EST",2025,2025,14,14,"2025-03-31",45644.965277777781,"2025-04-05",45644.208333333336,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTCR: 491059\r\nCR2025_046_V02",null,null,68056,"2024-10-14",0,"1,2,3,4,5"]
[null,"Infrabel","68299","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,14,14,"2025-03-31",45644.965277777781,"2025-04-05",45644.208333333336,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Démontage couverture quai voie I",null,null,68299,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","72357","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2025,2025,14,14,"2025-03-31",45644.965277777781,"2025-04-05",45644.243055555555,"5d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien massification L144 + 130/1\r\nZone Z09.44 \r\n+ Dépose poteaux caténaire sur L144. (entre L130 et PN10)\r\nTCR 507172",null,null,72357,"2024-11-07",0,"1,2,3,4,5"]
[null,"Infrabel","72802","Lille - Charleroi",">","BRUXELLES-MIDI","Y.NOORD HALLE",2025,2025,14,14,"2025-03-31",45644.986111111109,"2025-04-05",45644.229166666664,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FH_03 Area CE volgens onderhoudskalender 2025.\r\nBuitendienststelling L96 spoor A tussen FBMZ en FH.",null,null,72802,"2024-02-05",0,"1,2,3,4,5"]
[null,"Infrabel","71878","Namur - Antwerpen","< >","Y.HEIKE","MECHELEN",2025,2025,14,14,"2025-03-31",45644.993055555555,"2025-04-04",45644.211805555555,"4d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71878,"2024-04-11",0,"1,2,3,4,5"]
[null,"Infrabel","68040","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2025,2025,14,14,"2025-03-31",45644.034722222219,"2025-03-31",45644.201388888891,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68040,"2024-06-27",0,"5,6"]
[null,"Infrabel","72801","Namur - Antwerpen","< >","SCHAERBEEK","Y.HAREN-NORD",2025,2025,14,14,"2025-03-31",45644.395833333336,"2025-04-04",45644.625,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone FSR_10  Area CE volgens onderhoudskalender 2025\r\nBuitendienststelling L27 Y Groep G overdag buiten de spitsuren voor onderhoudswerken.\r\nR2 : 09.50 - 13.50",null,null,72801,"2024-10-21",0,"1,2,3,4,5"]
[null,"Infrabel","73081","Athus - Meuse",">","SIGNEULX","HALANZY",2025,2025,14,14,"2025-04-01",45644.333333333336,"2025-04-01",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73081,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","77280","Athus - Meuse",">","VONECHE","GEDINNE-MARCHANDISES",2025,2025,14,14,"2025-04-01",45644.333333333336,"2025-04-01",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,77280,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","76375","Lille - Charleroi",">","Y.FELUY","MANAGE",2025,2025,14,14,"2025-04-01",45644.333333333336,"2025-04-01",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagno J6",null,null,76375,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","67896","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,14,14,"2025-04-01",45644.020833333336,"2025-04-05",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67896,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","73363","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,14,14,"2025-04-01",45644.375,"2025-04-01",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73363,"2024-11-07",0,"1,2,3,4,5"]
[null,"Infrabel","53238","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,14,14,"2025-04-01",45644.923611111109,"2025-04-04",45644.194444444445,"3d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de rails \r\n+ Travaux OA \r\n+ Chantier SPW PS 65.090\r\nTCR 488725",null,null,53238,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","73082","Athus - Meuse",">","HALANZY","SIGNEULX",2025,2025,14,14,"2025-04-02",45644.333333333336,"2025-04-02",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie  B",null,null,73082,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","77281","Athus - Meuse",">","GEDINNE","VONECHE",2025,2025,14,14,"2025-04-02",45644.333333333336,"2025-04-02",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,77281,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","76469","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,14,14,"2025-04-02",45644.333333333336,"2025-04-02",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite Diagno J27",null,null,76469,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","73364","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,14,14,"2025-04-02",45644.375,"2025-04-02",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73364,"2024-11-07",0,"1,2,3,4,5"]
[null,"Infrabel","77473","Athus - Meuse",">","GEDINNE","PALISEUL",2025,2025,14,14,"2025-04-03",45644.333333333336,"2025-04-03",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,77473,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","76427","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,14,14,"2025-04-03",45644.333333333336,"2025-04-03",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagno J12",null,null,76427,"2024-10-08",0,"1,2,3,4,5"]
[null,"Infrabel","77118","Athus - Meuse",">","YVOIR","DINANT",2025,2025,14,14,"2025-04-03",45644.385416666664,"2025-04-03",45644.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,77118,"2024-11-07",0,"1,2,3,4,5"]
[null,"Infrabel","74575","Lille - Charleroi",">","ATH","BRUGELETTE",2025,2025,14,14,"2025-04-03",45644.34375,"2025-04-03",45644.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno",null,null,74575,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","67026","Namur - Antwerpen","< >","CHARLEROI-OUEST","FLEURUS",2025,2025,14,15,"2025-04-04",45644.958333333336,"2025-04-07",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement CV\r\nTCR: 488131",null,null,67026,"2024-10-14",1,"5,6"]
[null,"Infrabel","77474","Athus - Meuse",">","PALISEUL","GEDINNE",2025,2025,14,14,"2025-04-04",45644.333333333336,"2025-04-04",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,77474,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","78208","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2025,2025,14,15,"2025-04-04",45644.989583333336,"2025-04-07",45644.229166666664,"2d, 05:45h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-075 : Travaux RER\r\n\r\nUPM: 505519",null,null,78208,"2024-11-08",0,"5,6"]
[null,"Infrabel","77119","Athus - Meuse",">","DINANT","YVOIR",2025,2025,14,14,"2025-04-04",45644.385416666664,"2025-04-04",45644.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,77119,"2024-11-07",0,"1,2,3,4,5"]
[null,"Infrabel","74574","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2025,2025,14,14,"2025-04-04",45644.354166666664,"2025-04-04",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno",null,null,74574,"2024-10-07",0,"1,2,3,4,5"]
[null,"Infrabel","77156","Athus - Meuse",">","BEAURAING","VONECHE",2025,2025,14,14,"2025-04-05",45644.333333333336,"2025-04-05",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,77156,"2024-11-06",0,"5,6"]
[null,"Infrabel","70014","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2025,2025,14,14,"2025-04-05",45644.333333333336,"2025-04-06",45644.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nTCR 507473",null,null,70014,"2024-11-07",0,"5,6"]
[null,"Infrabel","55773","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2025,2025,14,15,"2025-04-05",45644.979166666664,"2025-04-07",45644.229166666664,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 de la voie A entre SJW et Wavre \r\ncontraintes, finitions (4)\r\nUPM: 488544",null,null,55773,"2024-11-08",0,"5,6"]
[null,"Infrabel","64222","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,14,15,"2025-04-05",45644.965277777781,"2025-04-07",45644.208333333336,"2d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses\r\nTCR: 493486",null,null,64222,"2024-10-14",0,"5,6"]
[null,"Infrabel","53487","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2025,2025,14,14,"2025-04-05",45644.25,"2025-04-06",45644.666666666664,"1d, 10:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 + Z2.53 en P4\r\nTCR 488963",null,null,53487,"2024-10-07",1,"5,6"]
[null,"Infrabel","69750","Namur - Antwerpen","< >","Y.SCHAERBEEK-GROUPE G","MECHELEN",2025,2025,14,15,"2025-04-05",45644.25,"2025-04-07",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"sporen 3+4+5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde\r\n+\r\nWerken Viaduct Vilvoorde (in samenwerking met AWV)",null,null,69750,"2024-11-08",1,"5,6"]
[null,"Infrabel","72116","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","ANTWERPEN-CENTRAAL",2025,2025,14,15,"2025-04-05",45644.041666666664,"2025-04-07",45644.1875,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing wisselonderdelen Antwerpen Centraal , \r\nperronsporen 3 tem 6 BD (perrons 1+ 2 blijevn in dienst)\r\n\r\nHerziening perronsporen 5+6",null,null,72116,"2024-01-26",1,"5,6"]
[null,"Infrabel","60195","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2025,2025,14,15,"2025-04-05",45644.041666666664,"2025-04-07",45644.1875,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Stationsproject Antwerpen-Zuid B-Stations:\r\nTrapconstructie op perron\r\nCf Escalade Head Of nov/dec 2023",null,null,60195,"2024-10-23",1,"5,6"]
[null,"Infrabel","69469","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,14,15,"2025-04-05",45644.000694444447,"2025-04-07",45644.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK",null,null,69469,"2024-11-12",1,"5,6"]
[null,"Infrabel","74100","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2025,2025,14,14,"2025-04-05",45644.996527777781,"2025-04-06",45644.25,"1d, 06:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud L51 -51A-51B - TCR 495738\r\nMassificatie onderhoud wissels sp B L51A tss Lissewege en Zwankendamme",null,null,74100,"2024-08-06",0,"5,6"]
[null,"Infrabel","80255","Athus - Meuse",">","NAMUR","BOIS D'AUSSE",2025,2025,14,14,"2025-04-05",45644.375,"2025-04-05",45644.677083333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-085 \r\nVisite périodique de jour le samedi pour AI43. (suite mise en service ETCS)\r\nVA: Le samedi entre 9h et 16h15\r\nVB: Le Samedi entre 8h45 et 16h\r\nA dupliquer toutes les 8 semaines.\r\n",null,null,80255,"2024-11-07",0,"5,6"]
[null,"Infrabel","77157","Athus - Meuse",">","VONECHE","BEAURAING",2025,2025,14,14,"2025-04-06",45644.333333333336,"2025-04-06",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,77157,"2024-11-06",0,"5,6"]
[null,"Infrabel","70930","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2025,2025,14,15,"2025-04-06",45644.951388888891,"2025-04-07",45644.194444444445,"1d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.52 P3 HKV\r\nNuit dim/lun",null,null,70930,"2024-11-20",0,"5,6"]
[null,"Infrabel","56490","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,15,15,"2025-04-07",45644.958333333336,"2025-04-11",45644.173611111109,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Second tabliers ponts 7,8 et 9 + Renouvellement AS de Lobbes-Garage & Hourpes\r\nNuits de préparation\r\nTCR 487625",null,null,56490,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","63191","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2025,2025,15,15,"2025-04-07",45644.958333333336,"2025-04-12",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,63191,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","71755","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,15,15,"2025-04-07",45644.333333333336,"2025-04-07",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nTCR 507452",null,null,71755,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","72569","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2025,2025,15,15,"2025-04-07",45644.333333333336,"2025-04-07",45644.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,72569,"2024-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","68928","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,15,15,"2025-04-07",45644.979166666664,"2025-04-11",45644.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L53",null,null,68928,"2023-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","72717","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,15,15,"2025-04-07",45644.979166666664,"2025-04-12",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72717,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","66150","Lille - Charleroi","< >","MONCEAU-GRIL F","Y.NORD",2025,2025,15,15,"2025-04-07",45644.951388888891,"2025-04-11",45644.194444444445,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.52 P3 HKV",null,null,66150,"2024-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","68300","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,15,15,"2025-04-07",45644.972222222219,"2025-04-12",45644.197916666664,"5d, 05:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Démontage structure quai voie I",null,null,68300,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","55546","Lille - Charleroi","< >","ATH","LEUZE",2025,2025,15,15,"2025-04-07",45644.9375,"2025-04-11",45644.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux OA supprimés, TCR reprise par service caténaire (mail de Bertrand Huon le 28/11/2024).\r\nUPM 487977",null,null,55546,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","65790","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2025,2025,15,15,"2025-04-07",45644.9375,"2025-04-12",45644.208333333336,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z8.51   P3",null,null,65790,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","72815","Lille - Charleroi","< >","HALLE","Y.NOORD HALLE",2025,2025,15,15,"2025-04-07",45644.9375,"2025-04-12",45644.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone FH_08 volgens onderhoudskalender Area CE\r\n\r\nsp A L94 met ATW/TX",null,null,72815,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","79366","Namur - Antwerpen",">","Y.EKERSEDIJK","Y.NOORDERLAAN",2025,2025,15,15,"2025-04-07",45644.916666666664,"2025-04-08",45644.25,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Lossen van rails met T-portiek voor vernieuwing Y-Ekersedijk\r\nR-510298\r\nA-510062",null,null,79366,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","53252","Namur - Antwerpen","< >","CHARLEROI-OUEST","FLEURUS",2025,2025,15,15,"2025-04-07",45644.965277777781,"2025-04-12",45644.201388888891,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de CV\r\nTCR: 488071\r\nMassifiée dans la 488132 colt 55511",null,null,53252,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","55511","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,15,15,"2025-04-07",45644.965277777781,"2025-04-12",45644.201388888891,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 1 - 39.681 39.749 40.133\r\nPréparations\r\n+ Maintenance Z3.51 (voies I et II de Fleurus comprises)\r\nTCR: 488132",null,null,55511,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","68057","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL EST",2025,2025,15,15,"2025-04-07",45644.965277777781,"2025-04-12",45644.215277777781,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTCR: 491105\r\nCR2025_046_V02",null,null,68057,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","72813","Lille - Charleroi",">","BRUXELLES-MIDI","BRUXELLES-MIDI",2025,2025,15,15,"2025-04-07",45644.986111111109,"2025-04-12",45644.222222222219,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoudswerken volgens onderhoudskalender Area CE\r\nOnderhoudszone FBMZ_04, perronspoor 18+19 FBMZ.\r\n\r\nBVL later te verkrijgen.",null,null,72813,"2024-02-19",0,"1,2,3,4,5"]
[null,"Infrabel","66521","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2025,2025,15,15,"2025-04-07",45644.944444444445,"2025-04-12",45644.173611111109,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.54\r\n+ Maintenance Z7.54 P3HKM",null,null,66521,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","69458","Erquelinnes - Montzen",">","AMPSIN","HUY",2025,2025,15,15,"2025-04-07",45644.375,"2025-04-11",45644.625,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien caténaire",null,null,69458,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","71706","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,15,15,"2025-04-07",45644.361111111109,"2025-04-07",45644.645833333336,"1d, 06:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance\r\nTCR 507126",null,null,71706,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","77624","Athus - Meuse","< >","AUBANGE-FRONTIERE-FRANCE","Y.AUBANGE",2025,2025,15,15,"2025-04-07",45644.354166666664,"2025-04-07",45644.5,"1d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite voie unique L 165/2 \r\nVisite voie unique L 165/3\r\nVisite voie unique L 165/1",null,null,77624,"2024-12-16",0,"1,2,3,4,5"]
[null,"Infrabel","56175","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,15,15,"2025-04-07",45644.354166666664,"2025-04-11",45644.645833333336,"5d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement de Luttre - phase 2025\r\nPréparations caténaires, T-H.11 > quai IV\r\npose de consoles en tête de faisceau + transfert de la caténaire\r\n+ révision à mi-vie\r\nTCR: 488970",null,null,56175,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","72570","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2025,2025,15,15,"2025-04-07",45644.5,"2025-04-07",45644.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,72570,"2024-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","72812","Namur - Antwerpen","< >","SCHAERBEEK","Y.JOSAPHAT",2025,2025,15,15,"2025-04-07",45644.395833333336,"2025-04-11",45644.645833333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken Area CE volgens kalender.\r\nZone MTB 03, L161 perronsporen 3+4 te FSR + bundel M",null,null,72812,"2024-02-05",0,"1,2,3,4,5"]
[null,"Infrabel","77162","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2025,2025,15,15,"2025-04-07",45644.388888888891,"2025-04-07",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA (périodicité 3 semaines)",null,null,77162,"2024-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","73124","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2025,2025,15,15,"2025-04-07",45644.423611111109,"2025-04-07",45644.493055555555,"1d, 01:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,73124,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","72188","Namur - Antwerpen","< >","MECHELEN","Y.LEUVEN-BUNDEL M",2025,2025,15,15,"2025-04-07",45644.975694444445,"2025-04-12",45644.208333333336,"5d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,72188,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","67897","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,15,15,"2025-04-08",45644.020833333336,"2025-04-12",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67897,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","75067","Lille - Antwerpen","< >","SINT-NIKLAAS","LOKEREN",2025,2025,15,15,"2025-04-08",45644.013888888891,"2025-04-12",45644.184027777781,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P221 goederencorridors Lokeren +R56 - TCR 501080\r\n\r\n+ Onderhoud sp A of B L59 tijdens N56 tss Sint-Niklaas en Lokeren",null,null,75067,"2024-08-06",0,"1,2,3,4,5"]
[null,"Infrabel","73594","Athus - Meuse",">","DINANT","Y.NEFFE",2025,2025,15,20,"2025-04-08",45644.25,"2025-05-16",45644.666666666664,"38d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025 - 054\r\nRenouvellement du PN115 bis\r\nAménagement des rampes et escaliers d'Accès au CSV côté VB suite suppression PN115bis.\r\nUPM:508163",null,null,73594,"2024-11-14",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","73827","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,15,15,"2025-04-08",45644.034722222219,"2025-04-10",45644.180555555555,"3d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie Onderhoud nachtdienst Schets 3 - TCR 502186\r\nFGSP Perronspoor I tem IV tot L50E SP A  tot 02BO niet inbegrepen + L50E SP B tot 05O niet inbegrepen \r\n+ verlengde van de perrons I+II kant kust L50A6 inbegrepen, L75 vrij te houden voor verkeer\r\n",null,null,73827,"2024-08-06",0,"1,2,3,4,5"]
[null,"Infrabel","72754","Athus - Meuse",">","STOCKEM-NORD","ARLON",2025,2025,15,15,"2025-04-08",45644.361111111109,"2025-04-08",45644.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72754,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","72568","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,15,15,"2025-04-08",45644.395833333336,"2025-04-08",45644.611111111109,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie et intervention avec S460 sur la voie contiguë + ATW",null,null,72568,"2024-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","73393","Athus - Meuse",">","DINANT","Y.NEFFE",2025,2025,15,15,"2025-04-08",45644.34375,"2025-04-08",45644.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,73393,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","70276","Namur - Antwerpen",">","AISEAU","LE CAMPINAIRE",2025,2025,15,15,"2025-04-08",45644.34375,"2025-04-08",45644.510416666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rév 64BJ",null,null,70276,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","73139","Athus - Meuse",">","NAMUR","JAMBES",2025,2025,15,15,"2025-04-08",45644.388888888891,"2025-04-08",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73139,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","70489","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,15,15,"2025-04-09",45644.375,"2025-04-09",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y-Holland",null,null,70489,"2024-02-14",0,"1,2,3,4,5"]
[null,"Infrabel","72755","Athus - Meuse",">","HABAY","STOCKEM-NORD",2025,2025,15,15,"2025-04-09",45644.375,"2025-04-09",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72755,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","73108","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,15,15,"2025-04-10",45644.333333333336,"2025-04-10",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73108,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","77500","Athus - Meuse",">","PALISEUL","BERTRIX",2025,2025,15,15,"2025-04-10",45644.333333333336,"2025-04-10",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,77500,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","71119","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,15,15,"2025-04-10",45644.9375,"2025-04-11",45644.225694444445,"1d, 06:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 4\r\nZ4.43\r\nPériodicité toutes les 4 semaines en alternance avec la zone 9\r\nzone 4 : 3 fois sur l'année\r\nzone 9 : 9 fois sur l'année",null,null,71119,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","70616","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2025,2025,15,15,"2025-04-10",45644.375,"2025-04-10",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen - Schijnpoort + inrit bundel Q",null,null,70616,"2024-03-13",0,"1,2,3,4,5"]
[null,"Infrabel","71075","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,15,15,"2025-04-11",45644.958333333336,"2025-04-12",45644.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nZ5.43",null,null,71075,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","73109","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,15,15,"2025-04-11",45644.333333333336,"2025-04-11",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73109,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","77502","Athus - Meuse",">","BERTRIX","PALISEUL",2025,2025,15,15,"2025-04-11",45644.333333333336,"2025-04-11",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,77502,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","66484","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2025,2025,15,16,"2025-04-11",45644.986111111109,"2025-04-14",45644.1875,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux de maintenance importante  + intervention PN + Maintenance ECFM 1000V\r\n+ Visite L161 Ottignies - Gembloux (extension Rhisnes SAS)\r\nUPM: 488248",null,null,66484,"2024-11-19",1,"5,6"]
[null,"Infrabel","70629","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,15,15,"2025-04-11",45644.375,"2025-04-11",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y Holland + inrit bundel Q",null,null,70629,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","53222","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,15,16,"2025-04-11",45644.930555555555,"2025-04-14",45644.229166666664,"2d, 07:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - Phase 2025\r\nWE 1\r\nTCR: 488971",null,null,53222,"2024-11-12",1,"5,6"]
[null,"Infrabel","77163","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2025,2025,15,15,"2025-04-11",45644.34375,"2025-04-11",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,77163,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","69381","Athus - Meuse","< >","DINANT","Y.NEFFE",2025,2025,15,15,"2025-04-12",45644.958333333336,"2025-04-13",45644.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mise au gabarit des pistes de circulation\r\nSécurisation des parois rocheuses \r\nRenouvellement PI BK 13808\r\nCR 2025-054\r\nUPM:508168",null,null,69381,"2024-11-12",1,"5,6"]
[null,"Infrabel","68173","Namur - Antwerpen",">","OTTIGNIES","WAVRE",2025,2025,15,15,"2025-04-12",45644.333333333336,"2025-04-12",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Ottignies - Wavre VA/VB\r\nUPM: 488495",null,null,68173,"2024-11-15",0,"5,6"]
[null,"Infrabel","68702","Erquelinnes - Montzen","< >","Y.VAL-BENOIT","Y.RENORY",2025,2025,15,15,"2025-04-12",45644.979166666664,"2025-04-13",45644.208333333336,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons",null,null,68702,"2024-11-13",0,"5,6"]
[null,"Infrabel","64960","Erquelinnes - Montzen","< >","FROIDMONT","BRESSOUX",2025,2025,15,16,"2025-04-12",45644.208333333336,"2025-04-14",45644.208333333336,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Z8.42\r\nEntretien mécanisé et manuel des AS du grill de Bressoux côté Froidmond\r\nEntretien tunnel\r\nUPM 488115",null,null,64960,"2024-11-13",1,"5,6"]
[null,"Infrabel","64223","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,15,16,"2025-04-12",45644.965277777781,"2025-04-14",45644.208333333336,"2d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses\r\nTCR: 491107",null,null,64223,"2024-11-14",0,"5,6"]
[null,"Infrabel","59471","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,15,16,"2025-04-12",45644.986111111109,"2025-04-14",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais\r\nUPM: 489229",null,null,59471,"2024-12-06",0,"5,6"]
[null,"Infrabel","70456","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2025,2025,15,15,"2025-04-12",45644.291666666664,"2025-04-13",45644.708333333336,"2d, 10:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels en sporen te Antwerpen Schijnpoort inrit bundel E\r\nHKV",null,null,70456,"2024-04-30",0,"5,6"]
[null,"Infrabel","70273","Namur - Antwerpen",">","CHATELET-GRIL EST","CHATELET",2025,2025,15,15,"2025-04-12",45644.260416666664,"2025-04-12",45644.385416666664,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Géo critique 21AJ/22J",null,null,70273,"2024-10-23",0,"5,6"]
[null,"Infrabel","72547","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,15,15,"2025-04-12",45644.3125,"2025-04-12",45644.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72547,"2024-11-13",0,"5,6"]
[null,"Infrabel","68381","Lille - Antwerpen",">","Y.WEST BERCHEM","ZWIJNDRECHT-ROOSTER D",2025,2025,15,16,"2025-04-12",45644.041666666664,"2025-04-14",45644.1875,"2d, 03:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Stationsproject Antwerpen-Zuid B-Stations:\r\nTrapconstructie op perron\r\nCf Escalade Head Of nov/dec 2023",null,null,68381,"2024-05-17",0,"5,6"]
[null,"Infrabel","67466","Lille - Charleroi","< >","GHLIN","MONS",2025,2025,15,15,"2025-04-12",45644.993055555555,"2025-04-13",45644.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim",null,null,67466,"2024-11-18",0,"5,6"]
[null,"Infrabel","70274","Namur - Antwerpen",">","CHATELET","CHATELET-GRIL OUEST",2025,2025,15,15,"2025-04-12",45644.385416666664,"2025-04-12",45644.510416666664,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Géo critique 21BJ/23AJ",null,null,70274,"2024-10-23",0,"5,6"]
[null,"Infrabel","70275","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL EST",2025,2025,15,15,"2025-04-12",45644.510416666664,"2025-04-12",45644.583333333336,"1d, 01:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Géo critique 43BJ",null,null,70275,"2024-10-23",0,"5,6"]
[null,"Infrabel","71107","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2025,2025,15,16,"2025-04-13",45644.958333333336,"2025-04-14",45644.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nZ7.43",null,null,71107,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","68174","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2025,2025,15,15,"2025-04-13",45644.333333333336,"2025-04-13",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Sint-Joris-Weert - Wavre VA/VB\r\nUPM: 488510",null,null,68174,"2024-12-06",0,"5,6"]
[null,"Infrabel","75217","Lille - Antwerpen","< >","Y.MELSELE","OOSTAKKER",2025,2025,15,15,"2025-04-13",45644.020833333336,"2025-04-13",45644.21875,"1d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud - TCR 500386",null,null,75217,"2024-08-06",0,"5,6"]
[null,"Infrabel","75440","Namur - Antwerpen",">","CHATELET","CHATELET-GRIL OUEST",2025,2025,15,15,"2025-04-13",45644.25,"2025-04-13",45644.458333333336,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rév 58BJ",null,null,75440,"2024-11-14",0,"5,6"]
[null,"Infrabel","67317","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ANTWERPEN-D.S.-RHODESIE",2025,2025,15,15,"2025-04-13",45644.25,"2025-04-13",45644.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,67317,"2024-03-27",1,"5,6"]
[null,"Infrabel","72558","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,15,15,"2025-04-13",45644.3125,"2025-04-13",45644.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72558,"2024-11-13",0,"5,6"]
[null,"Infrabel","73829","Namur - Antwerpen","< >","GENT-SINT-PIETERS","MERELBEKE-ROOSTER S",2025,2025,15,15,"2025-04-13",45644.034722222219,"2025-04-13",45644.243055555555,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud schets za^zo - TCR 502208\r\n\r\nL50E TLO Rooster S tot FGSP\r\nL58 + L58/1 TLO tot FGDM",null,null,73829,"2024-08-06",0,"5,6"]
[null,"Infrabel","75496","Athus - Meuse",">","BERTRIX","STRAIMONT",2025,2025,15,15,"2025-04-13",45644.347222222219,"2025-04-13",45644.65625,"1d, 07:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,75496,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","75441","Namur - Antwerpen",">","AISEAU","CHATELET-GRIL EST",2025,2025,15,15,"2025-04-13",45644.458333333336,"2025-04-13",45644.583333333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Géo 59BJ + 61AJ",null,null,75441,"2024-11-14",0,"5,6"]
[null,"Infrabel","63192","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2025,2025,16,16,"2025-04-14",45644.958333333336,"2025-04-19",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,63192,"2024-11-19",0,"1,2,3,4,5"]
[null,"Infrabel","68929","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,16,16,"2025-04-14",45644.979166666664,"2025-04-18",45644.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L53",null,null,68929,"2023-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","68301","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,16,16,"2025-04-14",45644.972222222219,"2025-04-19",45644.197916666664,"5d, 05:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Démontage fondations quai voie I",null,null,68301,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","56179","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,16,16,"2025-04-14",45644.9375,"2025-04-19",45644.229166666664,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - phase 2025\r\npréparations caténaires \r\ndépose des grandes traverses VP + tête de faisceau\r\nentre I-E.20/IX-E.20 et K-E.20/KX.E.20\r\n+ révision à mi-vie de la caténaire\r\nentre I-E.20/IX-E.20 et TX-H.11 et T-H.11\r\nTCR: 489111",null,null,56179,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","53503","Lille - Charleroi","< >","JURBISE","ATH",2025,2025,16,16,"2025-04-14",45644.9375,"2025-04-19",45644.222222222219,"5d, 06:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 P3 HKM\r\n\r\nJH le 30/10 : Incompatible avec R505073 (capacité Ath).\r\nTCR limitée à DF/DXF en accord avec David Parent -> priorité à R505073 pour le gril de Ath.",null,null,53503,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","55512","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,16,16,"2025-04-14",45644.96875,"2025-04-18",45644.201388888891,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 1-  39.681 39.749 40.133\r\nPréparations\r\nTCR: 488133",null,null,55512,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","54818","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL EST",2025,2025,16,16,"2025-04-14",45644.965277777781,"2025-04-18",45644.215277777781,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTCR: 491110\r\nCR2025_046_V02",null,null,54818,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","55547","Lille - Charleroi","< >","ATH","LEUZE",2025,2025,16,16,"2025-04-14",45644.944444444445,"2025-04-19",45644.1875,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux de construction d'un PI au droit du km 53.560 en vue de la suppression du PN30 + renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\nNuits de finitions\r\nUPM 505073",null,null,55547,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","66514","Lille - Charleroi","< >","ATH","TOURNAI",2025,2025,16,16,"2025-04-14",45644.944444444445,"2025-04-19",45644.1875,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.54 P3HKV",null,null,66514,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","82616","Athus - Meuse","< >","ARLON","Y.AUTELBAS",2025,2025,16,17,"2025-04-14",45644.25,"2025-04-22",45644.166666666664,"8d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-095 \r\nAssainissement Voie B : CTL suite barrage CFL\r\nTCR 523936",null,null,82616,"2024-12-06",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","55589","Namur - Antwerpen",">","LA ROCHE(BRABANT)","TILLY",2025,2025,16,21,"2025-04-14",45644.25,"2025-05-23",45644.666666666664,"39d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Sécurisation des Parois Rocheuses entre La Roche et Tilly (2 parois)\r\nTCR: 487763",null,null,55589,"2024-11-14",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","59619","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,16,16,"2025-04-14",45644.993055555555,"2025-04-18",45644.177083333336,"4d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n6- Déroulage Liaisons Namur- Gembloux\r\nUPM: 488280",null,null,59619,"2024-11-21",0,"1,2,3,4,5"]
[null,"Infrabel","74221","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,16,16,"2025-04-14",45644.354166666664,"2025-04-15",45644.645833333336,"2d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud + schouwen spoor - TCR 499575\r\nSP A BD + perronspoor I\r\nMassificatie met onderhoudswerken wissels (R2)",null,null,74221,"2024-08-06",0,"1,2,3,4,5"]
[null,"Infrabel","77256","Athus - Meuse",">","HOUYET","BEAURAING",2025,2025,16,16,"2025-04-14",45644.388888888891,"2025-04-14",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,77256,"2024-11-19",0,"1,2,3,4,5"]
[null,"Infrabel","72189","Namur - Antwerpen","< >","MECHELEN","Y.LEUVEN-BUNDEL M",2025,2025,16,16,"2025-04-14",45644.975694444445,"2025-04-18",45644.208333333336,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,72189,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","72756","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2025,2025,16,16,"2025-04-14",45644.409722222219,"2025-04-14",45644.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72756,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","72376","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2025,2025,16,16,"2025-04-14",45644.381944444445,"2025-04-14",45644.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41",null,null,72376,"2024-11-19",0,"1,2,3,4,5"]
[null,"Infrabel","67898","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,16,16,"2025-04-15",45644.020833333336,"2025-04-19",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67898,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","70567","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,16,16,"2025-04-15",45644.986111111109,"2025-04-17",45644.236111111109,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen van Y Arendstraat",null,null,70567,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","72718","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,16,16,"2025-04-15",45644.003472222219,"2025-04-19",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72718,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","70499","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.HOLLAND",2025,2025,16,16,"2025-04-15",45644.354166666664,"2025-04-17",45644.645833333336,"3d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud bundelkop bundel C te Antwerpen schijnpoort thv sein S-N.12\r\nwissels  37N, 38N, 39N, 40N 41N",null,null,70499,"2024-04-30",0,"1,2,3,4,5"]
[null,"Infrabel","77257","Athus - Meuse",">","BEAURAING","HOUYET",2025,2025,16,16,"2025-04-15",45644.388888888891,"2025-04-15",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,77257,"2024-11-19",0,"1,2,3,4,5"]
[null,"Infrabel","69459","Erquelinnes - Montzen",">","FLEMALLE-HAUTE","ENGIS",2025,2025,16,16,"2025-04-15",45644.381944444445,"2025-04-18",45644.618055555555,"4d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien caténaire",null,null,69459,"2024-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","72750","Athus - Meuse",">","LAVAUX","MARBEHAN",2025,2025,16,16,"2025-04-16",45644.361111111109,"2025-04-16",45644.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72750,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","74222","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,16,16,"2025-04-16",45644.354166666664,"2025-04-17",45644.645833333336,"2d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud + schouwen  + SP B BD + perronspoor II + Perronspoor III tot VII + bundel M ontoegankelijk\r\nMassificatie met onderhoudswerken wissels (R3 - R4)\r\nTCR 499750",null,null,74222,"2024-08-06",0,"1,2,3,4,5"]
[null,"Infrabel","77696","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2025,2025,16,16,"2025-04-16",45644.388888888891,"2025-04-16",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,77696,"2024-11-19",0,"1,2,3,4,5"]
[null,"Infrabel","72761","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2025,2025,16,16,"2025-04-17",45644.368055555555,"2025-04-17",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72761,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","77697","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2025,2025,16,16,"2025-04-17",45644.388888888891,"2025-04-17",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB \r\n",null,null,77697,"2024-11-19",0,"1,2,3,4,5"]
[null,"Infrabel","70700","Lille - Antwerpen","< >","Y.OOST BERCHEM","SINT-NIKLAAS-OOST",2025,2025,16,16,"2025-04-18",45644.020833333336,"2025-04-19",45644.1875,"2d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen\r\nHKM\r\nZ23.22",null,null,70700,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","55514","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,16,17,"2025-04-18",45644.965277777781,"2025-04-22",45644.201388888891,"3d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 1 - 39.681 39.749 40.133\r\nTCR: 488124",null,null,55514,"2024-11-14",1,"5,6"]
[null,"Infrabel","72762","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2025,2025,16,16,"2025-04-18",45644.378472222219,"2025-04-18",45644.618055555555,"1d, 05:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72762,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","56181","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,16,17,"2025-04-19",45644.979166666664,"2025-04-21",45644.208333333336,"2d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement de Luttre - phase 2025\r\nPréparations caténaires, \r\ndémolitions poteaux entre IX-E.20 > quai IV\r\n+ révision à mi-vie caténaire L117, IX-E.20 > T-H.11\r\nTCR: 489201",null,null,56181,"2024-11-12",0,"5,6"]
[null,"Infrabel","64224","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET",2025,2025,16,17,"2025-04-19",45644.965277777781,"2025-04-21",45644.208333333336,"2d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Réélectrification L130\r\nDu Campinaire à Châtelet\r\nCTL de WE nuit uniquement\r\nPose traverses\r\nTCR: 491115",null,null,64224,"2024-11-14",0,"5,6"]
[null,"Infrabel","64233","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,16,17,"2025-04-19",45644.986111111109,"2025-04-21",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais\r\nUPM: 489230",null,null,64233,"2024-12-06",0,"5,6"]
[null,"Infrabel","53490","Lille - Charleroi","< >","Y.JURBISE","MONS",2025,2025,16,17,"2025-04-19",45644.25,"2025-04-21",45644.708333333336,"2d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR NMBS 307+316 accepté ce 27/08/2024\r\nMaintenance Z.5.53 P4+\r\nTCR 488835",null,null,53490,"2024-11-18",1,"5,6"]
[null,"Infrabel","53493","Lille - Charleroi","< >","Y.SOIGNIES","JURBISE",2025,2025,16,17,"2025-04-19",45644.25,"2025-04-21",45644.708333333336,"2d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR NMBS 307+316 accepté ce 27/08/2024\r\nMaintenance Z4.53 en P4\r\nTCR 489205",null,null,53493,"2024-11-18",1,"5,6"]
[null,"Infrabel","69427","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,16,17,"2025-04-19",45644.000694444447,"2025-04-21",45644.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Migratie tunnelveiligheidstechnieken Antw. NZ -1\r\nAntwerpen-Berchem - Antwerpen-Centraal\r\nCf Escalade Head Of nov/dec 2023",null,null,69427,"2023-12-04",1,"5,6"]
[null,"Infrabel","73181","Athus - Meuse",">","LIBRAMONT","HATRIVAL",2025,2025,16,16,"2025-04-19",45644.385416666664,"2025-04-19",45644.611111111109,"1d, 05:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73181,"2023-11-15",0,"5,6"]
[null,"Infrabel","72757","Athus - Meuse",">","ARLON","Y.AUTELBAS",2025,2025,16,16,"2025-04-19",45644.361111111109,"2025-04-19",45644.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72757,"2024-11-18",0,"5,6"]
[null,"Infrabel","74544","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2025,2025,16,16,"2025-04-19",45644.354166666664,"2025-04-19",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudswerken Wissels sp A L51B tss sein HX-R.7 en merksein sp 831. - TCR 507558",null,null,74544,"2024-08-07",0,"5,6"]
[null,"Infrabel","71170","Erquelinnes - Montzen",">","AMAY","ENGIS",2025,2025,16,16,"2025-04-19",45644.340277777781,"2025-04-19",45644.652777777781,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71170,"2024-11-20",0,"5,6"]
[null,"Infrabel","71589","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.BERNADETTESTRAAT",2025,2025,16,16,"2025-04-20",45644.020833333336,"2025-04-20",45644.204861111109,"1d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"NW_P025_P026_L59_Y Sint Bernadettestraat - Berchem_ETCS - TCR 506900\r\n\"IDS Backup, meewerken NIET mogelijk",null,null,71589,"2024-08-07",0,"5,6"]
[null,"Infrabel","72758","Athus - Meuse",">","MARBEHAN","HABAY",2025,2025,16,16,"2025-04-20",45644.375,"2025-04-20",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72758,"2024-11-18",0,"5,6"]
[null,"Infrabel","71171","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2025,2025,16,16,"2025-04-20",45644.354166666664,"2025-04-20",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,71171,"2024-11-22",0,"5,6"]
[null,"Infrabel","74545","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2025,2025,16,16,"2025-04-20",45644.354166666664,"2025-04-20",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudswerken Wissels sp B L51B tss sein H-R.7 en 03BV (vrijwaring MWB). - TCR 507563",null,null,74545,"2024-08-07",0,"5,6"]
[null,"Infrabel","71697","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2025,2025,16,16,"2025-04-20",45644.329861111109,"2025-04-20",45644.545138888891,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nOttignies gare  voie 1 à 5 en alternance\r\nTCR 507143",null,null,71697,"2024-12-04",0,"5,6"]
[null,"Infrabel","71745","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2025,2025,17,17,"2025-04-21",45644.333333333336,"2025-04-21",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 116 à 121 + faisceau manage\r\nNe fonctionne plus en Phase 5\r\nTCR 507081",null,null,71745,"2024-11-26",0,"5,6"]
[null,"Infrabel","71663","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2025,2025,17,17,"2025-04-21",45644.947916666664,"2025-04-26",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 05.32 - TCR 500419\r\nL58 Eeklo inbegrepen tot Gent Dampoort NIET inbegrepen",null,null,71663,"2024-08-07",0,"1,2,3,4,5"]
[null,"Infrabel","69457","Erquelinnes - Montzen",">","HUY","AMPSIN",2025,2025,17,17,"2025-04-21",45644.388888888891,"2025-04-25",45644.625,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien caténaire",null,null,69457,"2024-11-22",0,"1,2,3,4,5"]
[null,"Infrabel","53455","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,17,17,"2025-04-22",45644.958333333336,"2025-04-25",45644.173611111109,"3d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Second tabliers ponts 7,8 et 9 + Renouvellement AS de Lobbes-Garage & Hourpes\r\nNuits de préparation\r\nTCR 487626",null,null,53455,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","63193","Athus - Meuse",">","ANSEREMME","GENDRON-CELLES",2025,2025,17,17,"2025-04-22",45644.958333333336,"2025-04-26",45644.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Pose de caniveau ES, pose de nouvelle armoire ES et tirage de câble",null,null,63193,"2024-11-22",0,"1,2,3,4,5"]
[null,"Infrabel","70755","Lille - Antwerpen","< >","Y.OOST BERCHEM","SINT-NIKLAAS",2025,2025,17,17,"2025-04-22",45644.958333333336,"2025-04-26",45644.1875,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud lopend spoor en spoortoestellen\r\nHKV\r\nZ23.22",null,null,70755,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","67849","Namur - Antwerpen","< >","ESSEN","ESSEN",2025,2025,17,17,"2025-04-22",45644.333333333336,"2025-04-25",45644.666666666664,"4d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels en sporen bundel Essen.  Periodiciteit: 2 keer / jaar (voorjaar/najaar),",null,null,67849,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","68400","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,17,17,"2025-04-22",45644.979166666664,"2025-04-25",45644.208333333336,"3d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwarsliggers.\r\nWEEKNACHTEN",null,null,68400,"2023-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","72080","Lille - ZeeBrugge","< >","BRUGGE","LICHTERVELDE",2025,2025,17,17,"2025-04-22",45644.979166666664,"2025-04-25",45644.208333333336,"3d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 07.34 HKM - TCR 72080\r\nFR SP VI+VII+VIII inbegrepen\r\nL73 FLC tot Diksmuide inbegrepen\r\npaasmaandag niet inbegrepen\r\nR5/R6 niet inbegrepen, conflict WE FDD",null,null,72080,"2024-08-07",0,"1,2,3,4,5"]
[null,"Infrabel","68302","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,17,17,"2025-04-22",45644.972222222219,"2025-04-26",45644.197916666664,"4d, 05:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Nouvelles fondations + égouttage/gaine quai voie I",null,null,68302,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","55548","Lille - Charleroi","< >","ATH","TOURNAI",2025,2025,17,17,"2025-04-22",45644.9375,"2025-04-26",45644.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux de construction d'un PI au droit du km 53.560 en vue de la suppression du PN30 + renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\nNuits de finitions + enlèvement de l'ART\r\n+ Maintenance Z5.54\r\nUPM 487981",null,null,55548,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","75068","Lille - Antwerpen","< >","SINT-NIKLAAS","LOKEREN",2025,2025,17,17,"2025-04-22",45644.013888888891,"2025-04-25",45644.184027777781,"4d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P221 goederencorridors Lokeren - TCR 501100",null,null,75068,"2024-08-07",0,"1,2,3,4,5"]
[null,"Infrabel","55515","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,17,17,"2025-04-22",45644.965277777781,"2025-04-26",45644.201388888891,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 1 - 39.681 39.749 40.133\r\nCTL nuit soudures\r\nTCR: 488135",null,null,55515,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","72355","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2025,2025,17,17,"2025-04-22",45644.965277777781,"2025-04-26",45644.201388888891,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien massification\r\nMassifié travaux SW : Renouvellement de chapes id 55515",null,null,72355,"2024-11-26",0,"1,2,3,4,5"]
[null,"Infrabel","59622","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,17,17,"2025-04-22",45644.993055555555,"2025-04-26",45644.215277777781,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n8 - Réalisation de massifs et pose de poteaux\r\n9 - Pose de traverses Namur -Gembloux\r\nUPM: 487915",null,null,59622,"2024-11-22",0,"1,2,3,4,5"]
[null,"Infrabel","70500","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.HOLLAND",2025,2025,17,17,"2025-04-22",45644.354166666664,"2025-04-24",45644.645833333336,"3d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud bundelkop bundel C te Antwerpen schijnpoort thv sein R-N.12 en Q-N.12 en P-N.12\r\nwissels  35N, 34BN, 36N, 34AN",null,null,70500,"2024-04-30",0,"1,2,3,4,5"]
[null,"Infrabel","66524","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2025,2025,17,17,"2025-04-22",45644.930555555555,"2025-04-26",45644.180555555555,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.54",null,null,66524,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","71883","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,17,17,"2025-04-22",45644.975694444445,"2025-04-25",45644.208333333336,"3d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71883,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","65794","Lille - Charleroi","< >","Y.NORD","MARCHIENNE-AU-PONT",2025,2025,17,17,"2025-04-23",45644.979166666664,"2025-04-25",45644.1875,"2d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z7.51 P3\r\nUPM 500920",null,null,65794,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","67899","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,17,17,"2025-04-23",45644.020833333336,"2025-04-26",45644.208333333336,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP\r\n\r\nJH le 31/10 : TCR demandée à partir du 22^23/04 (après férié).",null,null,67899,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","67455","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,17,17,"2025-04-24",45644.395833333336,"2025-04-24",45644.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nVisite diagnostique\r\nMise HS en P2\r\nTCR 488965",null,null,67455,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","53234","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,17,20,"2025-04-25",45644.958333333336,"2025-05-12",45644.173611111109,"16d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Construction MDS + élargissement plateforme\r\nSecond tabliers ponts 7,8 et 9\r\nCTL 17 jours continu\r\nTCR 487629",null,null,53234,"2024-11-14",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","54820","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL EST",2025,2025,17,18,"2025-04-25",45644.965277777781,"2025-04-28",45644.215277777781,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTir caténaires\r\nTCR: 491119\r\nCR2025_046_V02",null,null,54820,"2024-11-14",0,"5,6"]
[null,"Infrabel","67872","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2025,2025,17,17,"2025-04-26",45644.333333333336,"2025-04-26",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130\r\nUPM: 489010",null,null,67872,"2024-12-06",0,"5,6"]
[null,"Infrabel","77505","Athus - Meuse",">","PALISEUL","BERTRIX",2025,2025,17,17,"2025-04-26",45644.333333333336,"2025-04-26",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,77505,"2024-11-22",0,"5,6"]
[null,"Infrabel","75562","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.NOORD BERCHEM",2025,2025,17,18,"2025-04-26",45644.979166666664,"2025-04-28",45644.1875,"1d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud wissels Y Noord Groenenhoek",null,null,75562,"2024-02-05",0,"5,6"]
[null,"Infrabel","64961","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2025,2025,17,18,"2025-04-26",45644.208333333336,"2025-04-28",45644.201388888891,"2d, 23:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Z9.42\r\nEntretien mécanisé et manuel des AS de Bressoux côté Visé\r\nEntretien mécanisé et manuel des AS du grill de Visé\r\n+ renouvellement des rails entre Bressoux et Visé sur la voie B en 2025\r\n\r\nUPM 469442 (Massifié avec R-488112)",null,null,64961,"2024-11-29",1,"5,6"]
[null,"Infrabel","73770","Namur - Antwerpen","< >","Y.DIJLEBRUG","LEUVEN",2025,2025,17,18,"2025-04-26",45644,"2025-04-28",45644.1875,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-21 5TLO indienstname PLP keet H3)\r\nL53: TLO indienstname PLP keet H3\r\n\r\n",null,null,73770,"2024-08-30",1,"5,6"]
[null,"Infrabel","64234","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,17,18,"2025-04-26",45644.986111111109,"2025-04-28",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais\r\nUPM: 489231",null,null,64234,"2024-11-25",0,"5,6"]
[null,"Infrabel","83872","Lille - Charleroi","< >","MONCEAU-GRIL F","MONCEAU-GRIL F",2025,2025,17,17,"2025-04-26",45644.25,"2025-04-27",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Traverses et Rail voie 812",null,null,83872,"2024-12-16",1,"5,6"]
[null,"Infrabel","56520","Athus - Meuse","< >","BEAURAING","BERTRIX",2025,2025,17,18,"2025-04-26",45644.25,"2025-04-28",45644.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux de maintenance voies et caténaire + travaux OA \r\nUPM:491566",null,null,56520,"2024-11-22",1,"5,6"]
[null,"Infrabel","79902","Lille - Charleroi","< >","MONS","NEUFVILLES-GARAGE",2025,2025,17,17,"2025-04-26",45644.989583333336,"2025-04-27",45644.21875,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ETCS1 FS L90-L90C - MES",null,null,79902,"2024-11-18",0,"5,6"]
[null,"Infrabel","57974","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,17,18,"2025-04-26",45644.000694444447,"2025-04-28",45644.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwarsliggers",null,null,57974,"2024-11-12",1,"5,6"]
[null,"Infrabel","75991","Lille - Charleroi",">","BRAINE-LE-COMTE","SOIGNIES",2025,2025,17,17,"2025-04-26",45644.541666666664,"2025-04-26",45644.59375,"1d, 01:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA",null,null,75991,"2024-11-18",0,"5,6"]
[null,"Infrabel","70476","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2025,2025,17,17,"2025-04-26",45644.326388888891,"2025-04-26",45644.722222222219,"1d, 09:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen Oost - Antwerpen - Schijnpoort",null,null,70476,"2024-02-14",0,"5,6"]
[null,"Infrabel","75996","Lille - Charleroi",">","BRAINE-LE-COMTE","Y.FELUY",2025,2025,17,17,"2025-04-26",45644.34375,"2025-04-26",45644.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique AI52 + AI53\r\n",null,null,75996,"2024-11-18",0,"5,6"]
[null,"Infrabel","67873","Namur - Antwerpen",">","AUVELAIS","FLAWINNE",2025,2025,17,17,"2025-04-27",45644.333333333336,"2025-04-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130 Auvelais-Flawinne\r\nUPM: 489086",null,null,67873,"2024-12-06",0,"5,6"]
[null,"Infrabel","73007","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2025,2025,17,17,"2025-04-27",45644.333333333336,"2025-04-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73007,"2024-11-22",0,"1,2,3,4,5"]
[null,"Infrabel","77837","Athus - Meuse",">","BERTRIX","PALISEUL",2025,2025,17,17,"2025-04-27",45644.333333333336,"2025-04-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,77837,"2024-11-22",0,"5,6"]
[null,"Infrabel","68977","Lille - Antwerpen","< >","GENT-SINT-PIETERS","Y.ZANDBERG",2025,2025,17,17,"2025-04-27",45644.055555555555,"2025-04-27",45644.222222222219,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"In dienst stelling ETCS - TCR 493001\r\nMeewerken niet mogelijk\r\n\r\nL75 Gent Sint Pieters (v) tot Y.Zandberg (v) - 01.20 tot 05.20\r\nL86 De Pinte - Gavere (v) - 23.25 tot 7.35\r\nL73 Deinze - Lichtervelde (v) - 22.40 tot 07.00",null,null,68977,"2024-08-07",0,"5,6"]
[null,"Infrabel","79454","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2025,2025,17,17,"2025-04-27",45644.055555555555,"2025-04-27",45644.159722222219,"1d, 02:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-021\r\nEBP herlading zone Leuven\r\nIndienstname PLP Keet H3\r\nR-510966",null,null,79454,"2024-11-20",0,"5,6"]
[null,"Infrabel","75994","Lille - Charleroi",">","Y.SOIGNIES","SOIGNIES",2025,2025,17,17,"2025-04-27",45644.520833333336,"2025-04-27",45644.645833333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B\r\n",null,null,75994,"2024-11-18",0,"5,6"]
[null,"Infrabel","80221","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","ESSEN-GRENS",2025,2025,17,17,"2025-04-27",45644.048611111109,"2025-04-27",45644.194444444445,"1d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-132\r\nEBP - Hardware Equipment Maintenance : \"Renewal Network Devices\" + FORTINET. Buitendienst van seinpost FN-CR (Computer Room) en de EBP gekoppelde zone tijdens 04u00 voor werken \"Renewal of Network Device\". Uurregelingen zijn aanpasbaar tuss",null,null,80221,"2024-11-27",0,"5,6"]
[null,"Infrabel","75995","Lille - Charleroi",">","Y.JURBISE","NEUFVILLES-GARAGE",2025,2025,17,17,"2025-04-27",45644.319444444445,"2025-04-27",45644.479166666664,"1d, 03:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VB\r\n",null,null,75995,"2024-11-18",0,"5,6"]
[null,"Infrabel","54906","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2025,2025,18,18,"2025-04-28",45644.958333333336,"2025-05-03",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10.51   P3 HKV",null,null,54906,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","79175","Athus - Meuse",">","ARLON","Y.AUTELBAS",2025,2025,18,18,"2025-04-28",45644.958333333336,"2025-05-03",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-095 \r\nAssainissement Voie B - bourrage de révision, contraintes et finitions\r\nUPM: 512490",null,null,79175,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","68401","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,18,18,"2025-04-28",45644.979166666664,"2025-05-02",45644.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwarsliggers.\r\nWEEKNACHTEN",null,null,68401,"2023-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","68303","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,18,18,"2025-04-28",45644.972222222219,"2025-05-03",45644.197916666664,"5d, 05:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Nouvelles fondations - coffrage ferraillage + cage d'ascenseur - coffrage ferraillage + Egouttage / Gaine",null,null,68303,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","72879","Lille - Charleroi",">","BRUXELLES-MIDI","LOT",2025,2025,18,18,"2025-04-28",45644.986111111109,"2025-05-03",45644.229166666664,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FH_04 Area CE volgens onderhoudskalender 2025\r\nBuitendienststelling L96 spoor B tussen FBMZ en Lot.",null,null,72879,"2024-02-29",0,"1,2,3,4,5"]
[null,"Infrabel","66480","Lille - Charleroi","< >","HALLE","ATH",2025,2025,18,18,"2025-04-28",45644.944444444445,"2025-05-03",45644.180555555555,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z9.54+Z10.54 P3 HKV\r\n+ PLP",null,null,66480,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","70453","Namur - Antwerpen","< >","Y.HOLLAND","LUCHTBAL-ROOSTER S",2025,2025,18,18,"2025-04-28",45644.993055555555,"2025-05-03",45644.1875,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissel Y Antwerpen-Luchtbal\r\nHKV",null,null,70453,"2024-02-06",0,"1,2,3,4,5"]
[null,"Infrabel","67290","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,18,18,"2025-04-28",45644.993055555555,"2025-05-03",45644.215277777781,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n8 - Réalisation de massifs et pose de poteaux\r\n9 - Pose de traverses Namur -Gembloux\r\nUPM: 487917",null,null,67290,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","78638","Lille - Charleroi",">","Y.SOIGNIES","BRAINE-LE-COMTE",2025,2025,18,18,"2025-04-28",45644.354166666664,"2025-04-28",45644.4375,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VB - Zone 2",null,null,78638,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","73476","Namur - Antwerpen",">","Y.MELLE-WEST","MERELBEKE-ROOSTER S",2025,2025,18,18,"2025-04-28",45644.395833333336,"2025-04-29",45644.645833333336,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"reservatie onderhoud - TCR 502221\r\ndagdienst zone 1\r\nL50E SP B Y Melle West AW02BT niet inbegrepen tot inrit Merelbeke rooster S AW01AS niet inbegrepen\r\nBVL: 29164\r\n",null,null,73476,"2024-08-07",0,"1,2,3,4,5"]
[null,"Infrabel","72909","Athus - Meuse",">","BERTRIX","STRAIMONT",2025,2025,18,18,"2025-04-29",45644.333333333336,"2025-04-29",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\n",null,null,72909,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","75069","Lille - Antwerpen","< >","SINT-NIKLAAS","LOKEREN",2025,2025,18,18,"2025-04-29",45644.013888888891,"2025-05-01",45644.184027777781,"3d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P221 goederencorridors Lokeren - TCR 501102",null,null,75069,"2024-08-07",0,"1,2,3,4,5"]
[null,"Infrabel","72720","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,18,18,"2025-04-29",45644.003472222219,"2025-05-03",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72720,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","74473","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,18,18,"2025-04-29",45644.354166666664,"2025-04-29",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudswerken SK sp A L51 tss Y. Blauwe Toren en inritsein Blankenberge. TCR 507559\r\nAlle perronsporen te Blankenberge zijn bereikbaar",null,null,74473,"2024-08-07",0,"1,2,3,4,5"]
[null,"Infrabel","76409","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2025,2025,18,18,"2025-04-30",45644.333333333336,"2025-04-30",45644.4375,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11",null,null,76409,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","72910","Athus - Meuse",">","STRAIMONT","BERTRIX",2025,2025,18,18,"2025-04-30",45644.375,"2025-04-30",45644.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\n",null,null,72910,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","70818","Erquelinnes - Montzen",">","JAVA","STATTE",2025,2025,18,18,"2025-04-30",45644.354166666664,"2025-04-30",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,70818,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","73477","Namur - Antwerpen","< >","MERELBEKE-ROOSTER S","Y.OOST DRIEHOEK LEDEBERG",2025,2025,18,18,"2025-04-30",45644.395833333336,"2025-05-02",45644.645833333336,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"reservatie onderhoud - TCR 502319\r\ndagdienst zone 2\r\nL50E SP A Merelbeke rooster S sein EX-S.6 tot Y Oost Driehoek Ledeberg 10AR niet inbegrepen\r\nL50E SP B Merelbeke rooster S sein F-S.6 tot Y Oost Driehoek Ledeberg 03XR niet inbegrepen\r\nBVL: niet mogel",null,null,73477,"2024-08-07",0,"1,2,3,4,5"]
[null,"Infrabel","73006","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,18,18,"2025-05-01",45644.333333333336,"2025-05-01",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73006,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","71189","Erquelinnes - Montzen",">","JAVA","ANDENNE",2025,2025,18,18,"2025-05-01",45644.5625,"2025-05-01",45644.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71189,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","71190","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2025,2025,18,18,"2025-05-01",45644.375,"2025-05-01",45644.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71190,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","79420","Athus - Meuse",">","HAVERSIN","ROCHEFORT-JEMELLE",2025,2025,18,19,"2025-05-02",45644.979166666664,"2025-05-05",45644.177083333336,"2d, 04:45h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-105\r\nModernisation gare de Marloie - tirs VA\r\nEn remplacement du CR 2025-074 qui est refusé\r\nTCR 512792\r\n\r\n",null,null,79420,"2024-12-04",0,"5,6"]
[null,"Infrabel","54821","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL EST",2025,2025,18,19,"2025-05-02",45644.965277777781,"2025-05-05",45644.215277777781,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTir caténaires\r\nTCR: 491123\r\nCR2025_046_V02",null,null,54821,"2024-11-14",0,"5,6"]
[null,"Infrabel","80144","Athus - Meuse","< >","HAVERSIN","ROCHEFORT-JEMELLE",2025,2025,18,19,"2025-05-02",45644.986111111109,"2025-05-05",45644.180555555555,"3d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-105\r\nModernisation gare de Marloie - tirs VA\r\nEn remplacement du CR 2025-074 qui est refusé\r\nTCR 512792\r\nAvec colt 79420\r\n",null,null,80144,"2024-07-31",0,"5,6"]
[null,"Infrabel","73040","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2025,2025,18,18,"2025-05-03",45644.333333333336,"2025-05-03",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73040,"2024-12-02",0,"5,6"]
[null,"Infrabel","77568","Lille - Charleroi",">","SOIGNIES","NEUFVILLES",2025,2025,18,18,"2025-05-03",45644.333333333336,"2025-05-03",45644.447916666664,"1d, 02:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagno Zone 4",null,null,77568,"2024-11-18",0,"5,6"]
[null,"Infrabel","70021","Namur - Antwerpen",">","RHISNES-SAS","GEMBLOUX",2025,2025,18,18,"2025-05-03",45644.333333333336,"2025-05-04",45644.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nTCR 507480",null,null,70021,"2024-12-03",0,"5,6"]
[null,"Infrabel","72337","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,18,19,"2025-05-03",45644.979166666664,"2025-05-05",45644.166666666664,"1d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug  L15 km 6.027 BX L15 en L27A\r\n\r\n\r\nalternatief voor geweigerde L15+L27A",null,null,72337,"2024-03-12",1,"5,6"]
[null,"Infrabel","75249","Lille - Antwerpen",">","LOKEREN","OOSTAKKER",2025,2025,18,18,"2025-05-03",45644.020833333336,"2025-05-03",45644.229166666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Reservatie onderhoud - TCR 500290",null,null,75249,"2024-07-22",0,"1,2,3,4,5"]
[null,"Infrabel","64235","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,18,19,"2025-05-03",45644.986111111109,"2025-05-05",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais\r\nUPM: 489235",null,null,64235,"2024-12-03",0,"5,6"]
[null,"Infrabel","75857","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,18,18,"2025-05-03",45644.25,"2025-05-04",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-059\r\nVernieuwingswerken BVL t.h.v. Y.Ekerse Dijk\r\nBuitenspanning tem Bundel Rhodesië (gevolggevallen)",null,null,75857,"2024-12-05",1,"5,6"]
[null,"Infrabel","56521","Athus - Meuse","< >","BEAURAING","BERTRIX",2025,2025,18,19,"2025-05-03",45644.25,"2025-05-05",45644.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux de maintenance voies et caténaire + travaux OA \r\nRenouvellement de traverses par P93 - Phase 1 - WE 2\r\nUPM:491554",null,null,56521,"2024-12-02",1,"5,6"]
[null,"Infrabel","69756","Namur - Antwerpen","< >","Y.SCHAERBEEK-GROUPE G","MECHELEN",2025,2025,18,19,"2025-05-03",45644.25,"2025-05-05",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"sporen 3+4+5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde",null,null,69756,"2024-11-08",1,"5,6"]
[null,"Infrabel","69428","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,18,19,"2025-05-03",45644.000694444447,"2025-05-05",45644.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Migratie tunnelveiligheidstechnieken Antw. NZ -1\r\nAntwerpen-Berchem - Antwerpen-Centraal\r\nCf Escalade Head Of nov/dec 2023",null,null,69428,"2023-12-04",1,"5,6"]
[null,"Infrabel","57975","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,18,19,"2025-05-03",45644.000694444447,"2025-05-05",45644.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwarsliggers",null,null,57975,"2024-11-12",1,"5,6"]
[null,"Infrabel","60275","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2025,2025,18,19,"2025-05-03",45644.003472222219,"2025-05-05",45644.208333333336,"2d, 04:55h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Remplacement de traverses L125B VB (liée avec 60274, 60307 et 60308)\r\nUPM 469443",null,null,60275,"2024-12-05",0,"5,6"]
[null,"Infrabel","71191","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2025,2025,18,18,"2025-05-03",45644.354166666664,"2025-05-03",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71191,"2024-12-03",0,"5,6"]
[null,"Infrabel","75322","Lille - Charleroi",">","HENNUYERES-GARAGE","TUBIZE",2025,2025,18,18,"2025-05-03",45644.520833333336,"2025-05-03",45644.645833333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique + S460\r\n",null,null,75322,"2024-11-18",0,"5,6"]
[null,"Infrabel","73041","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2025,2025,18,18,"2025-05-04",45644.333333333336,"2025-05-04",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73041,"2024-12-02",0,"5,6"]
[null,"Infrabel","75321","Lille - Charleroi",">","BRAINE-LE-COMTE","HENNUYERES-GARAGE",2025,2025,18,18,"2025-05-04",45644.333333333336,"2025-05-04",45644.5625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique +S460\r\n",null,null,75321,"2024-11-18",0,"5,6"]
[null,"Infrabel","80604","Lille - Antwerpen","< >","BEERVELDE","LOKEREN-OOST",2025,2025,18,18,"2025-05-04",45644.013888888891,"2025-05-04",45644.229166666664,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-0143\r\nR-518737\r\n\r\nWisselslijptrein.",null,null,80604,"2024-11-25",0,"5,6"]
[null,"Infrabel","71192","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2025,2025,18,18,"2025-05-04",45644.354166666664,"2025-05-04",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71192,"2024-12-03",0,"5,6"]
[null,"Infrabel","80268","Athus - Meuse",">","HAVERSIN","MARLOIE",2025,2025,18,18,"2025-05-04",45644.364583333336,"2025-05-04",45644.666666666664,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-085 - massifié dans SAVU voie A HS colt 79420\r\nVisite périodique de jour le dimanche pour AI45. (suite mise en service ETCS)\r\nVA: Le dimanche entre 08h45 et 16h00\r\nVB: Le dimanche entre 08h00 et 15h15\r\nA dupliquer toutes les 8 semaines.",null,null,80268,"2024-11-29",0,"5,6"]
[null,"Infrabel","75320","Lille - Charleroi",">","TUBIZE","LEMBEEK",2025,2025,18,18,"2025-05-04",45644.597222222219,"2025-05-04",45644.645833333336,"1d, 01:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique Voie B  +S460 voie A\r\n",null,null,75320,"2024-11-18",0,"5,6"]
[null,"Infrabel","68402","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,19,19,"2025-05-05",45644.979166666664,"2025-05-09",45644.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwarsliggers.\r\nWEEKNACHTEN",null,null,68402,"2023-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","70549","Namur - Antwerpen",">","Y.BERCHEM-STADION","ANTWERPEN-CENTRAAL",2025,2025,19,19,"2025-05-05",45644.979166666664,"2025-05-10",45644.1875,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud wissels Y Noord Berchem\r\nHKV",null,null,70549,"2024-01-29",0,"1,2,3,4,5"]
[null,"Infrabel","68304","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,19,19,"2025-05-05",45644.972222222219,"2025-05-10",45644.201388888891,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Nouvelles fondations - béton + cage d'ascenseur - béton",null,null,68304,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","80605","Lille - Antwerpen",">","LOKEREN-OOST","LOKEREN",2025,2025,19,19,"2025-05-05",45644.013888888891,"2025-05-05",45644.208333333336,"1d, 04:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-143\r\nR-518738\r\n\r\nWisselslijptrein Lokeren",null,null,80605,"2024-11-25",0,"5,6"]
[null,"Infrabel","55521","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,19,19,"2025-05-05",45644.965277777781,"2025-05-10",45644.204861111109,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 1 - 39.681 39.749 40.133\r\nfinitions\r\nTCR: 488136",null,null,55521,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","72944","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2025,2025,19,19,"2025-05-05",45644.993055555555,"2025-05-10",45644.21875,"5d, 05:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FBMZ_16 en FBMZ_17 volgens onderhoudskalender Area CE\r\n\r\nL96 Spoor A tussen perron FBMZ en Y Ruisbroek\r\nnaastliggend spoor (Bypass)",null,null,72944,"2024-03-01",0,"1,2,3,4,5"]
[null,"Infrabel","72190","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,19,19,"2025-05-05",45644.975694444445,"2025-05-09",45644.208333333336,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,72190,"2024-10-15",0,"1,2,3,4,5"]
[null,"Infrabel","72943","Namur - Antwerpen",">","SCHAERBEEK","Y.SCHAERBEEK-GROUPE G",2025,2025,19,19,"2025-05-05",45644.427083333336,"2025-05-09",45644.625,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FSR_03 volgens onderhoudskalender Area CE\r\nLokale wissels te FSR thv sporen A L27 en B L36,\r\nFSR sp IX,X en XI",null,null,72943,"2024-03-01",0,"1,2,3,4,5"]
[null,"Infrabel","67932","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,19,19,"2025-05-06",45644.020833333336,"2025-05-10",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67932,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","75070","Lille - Antwerpen","< >","SINT-NIKLAAS","LOKEREN",2025,2025,19,19,"2025-05-06",45644.013888888891,"2025-05-09",45644.184027777781,"4d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P221 goederencorridors Lokeren - TCR 501104",null,null,75070,"2024-08-08",0,"1,2,3,4,5"]
[null,"Infrabel","72721","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,19,19,"2025-05-06",45644.003472222219,"2025-05-10",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72721,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","70490","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,19,19,"2025-05-07",45644.375,"2025-05-07",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y-Holland",null,null,70490,"2024-02-14",0,"1,2,3,4,5"]
[null,"Infrabel","73065","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,19,19,"2025-05-08",45644.333333333336,"2025-05-08",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73065,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","76428","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,19,19,"2025-05-08",45644.333333333336,"2025-05-08",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagno J12",null,null,76428,"2024-12-03",0,"1,2,3,4,5"]
[null,"Infrabel","70617","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2025,2025,19,19,"2025-05-08",45644.375,"2025-05-08",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen - Schijnpoort + inrit bundel Q",null,null,70617,"2024-03-13",0,"1,2,3,4,5"]
[null,"Infrabel","74474","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,19,19,"2025-05-08",45644.354166666664,"2025-05-08",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudswerken SK sp B L51 tss Y. Blauwe Toren en inritsein Blankenberge. - TCR 507564\r\nAlle perronsporen te Blankenberge zijn bereikbaar",null,null,74474,"2024-08-09",0,"1,2,3,4,5"]
[null,"Infrabel","71076","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,19,19,"2025-05-09",45644.958333333336,"2025-05-10",45644.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nZ5.43",null,null,71076,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","73066","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,19,19,"2025-05-09",45644.333333333336,"2025-05-09",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73066,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","54822","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET",2025,2025,19,20,"2025-05-09",45644.965277777781,"2025-05-12",45644.215277777781,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Réélectrification L130\r\nTir caténaires\r\nTCR: 493513",null,null,54822,"2024-12-10",0,"5,6"]
[null,"Infrabel","70630","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,19,19,"2025-05-09",45644.375,"2025-05-09",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y Holland + inrit bundel Q",null,null,70630,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","57976","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,19,20,"2025-05-09",45644.975694444445,"2025-05-12",45644.166666666664,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwaarsliggers",null,null,57976,"2024-11-12",1,"5,6"]
[null,"Infrabel","78576","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2025,2025,19,19,"2025-05-10",45644.958333333336,"2025-05-11",45644.229166666664,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Essais ETCS L75 Frontière Lens Bavo\r\nPas de sous coupure",null,null,78576,"2024-12-10",0,"5,6"]
[null,"Infrabel","70015","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2025,2025,19,19,"2025-05-10",45644.333333333336,"2025-05-11",45644.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nTCR 507474",null,null,70015,"2024-12-06",0,"5,6"]
[null,"Infrabel","74914","Namur - Antwerpen","< >","DENDERMONDE","LONDERZEEL",2025,2025,19,19,"2025-05-10",45644.979166666664,"2025-05-11",45644.222222222219,"1d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P221 goederencorridor - afbreken BTS - TCR 499320",null,null,74914,"2024-08-09",0,"5,6"]
[null,"Infrabel","68706","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","OUGREE-GRIL F/K",2025,2025,19,20,"2025-05-10",45644.979166666664,"2025-05-12",45644.208333333336,"2d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons\r\n+ Z28.41 + voies 213 et 205 de Kinkempois",null,null,68706,"2024-12-09",0,"5,6"]
[null,"Infrabel","72339","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,19,20,"2025-05-10",45644.979166666664,"2025-05-12",45644.166666666664,"1d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug  L15 km 6.027 BX L15 en L27A\r\n\r\n\r\nalternatief voor geweigerde L15+L27A",null,null,72339,"2024-03-12",1,"5,6"]
[null,"Infrabel","64236","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,19,20,"2025-05-10",45644.986111111109,"2025-05-12",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais\r\nUPM: 489236",null,null,64236,"2024-12-06",0,"5,6"]
[null,"Infrabel","66518","Lille - Charleroi","< >","ENGHIEN","ATH",2025,2025,19,19,"2025-05-10",45644.25,"2025-05-11",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z16.54\r\nUPM 487939",null,null,66518,"2024-12-10",1,"5,6"]
[null,"Infrabel","75858","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,19,19,"2025-05-10",45644.25,"2025-05-11",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-059\r\nVernieuwingswerken BVL t.h.v. Y.Ekerse Dijk\r\nBuitenspanning tem Bundel Rhodesië (gevolggevallen)",null,null,75858,"2024-12-05",1,"5,6"]
[null,"Infrabel","56525","Athus - Meuse","< >","BEAURAING","BERTRIX",2025,2025,19,20,"2025-05-10",45644.25,"2025-05-12",45644.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 1 - WE 3\r\nDossier de concertation octobre 2022 - CR 2025-037\r\n+ Travaux de maintenance\r\nUPM:491548\r\nRQ333: intégration des visites VA + VB Gedinne - Paliseul, ",null,null,56525,"2024-10-15",1,"5,6"]
[null,"Infrabel","69464","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,19,20,"2025-05-10",45644.25,"2025-05-12",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing wisselonderdelen en sporen te Antwerpen Schijnpoort inrit bundel F\r\n\r\nmet inbegrip van bundelkop bundel D-F (K-Q.12-T-O.12) +L27A spA zo 00:00 tot 17:40",null,null,69464,"2023-08-30",1,"5,6"]
[null,"Infrabel","72548","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,19,19,"2025-05-10",45644.3125,"2025-05-10",45644.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72548,"2024-12-03",0,"5,6"]
[null,"Infrabel","77923","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","ESSEN-GRENS",2025,2025,19,19,"2025-05-10",45644.125,"2025-05-10",45644.145833333336,"1d, 00:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-069\r\nEBP herlading zone Berchem\r\nL29 omvormen treindetectiesysteem van 50Hz naar TFSK + uitrol ZAX-DUO\r\nR-502412",null,null,77923,"2024-08-07",0,"5,6"]
[null,"Infrabel","70008","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2025,2025,19,19,"2025-05-11",45644.333333333336,"2025-05-11",45644.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144-130/1\r\nTCR 507099",null,null,70008,"2024-12-06",0,"5,6"]
[null,"Infrabel","75782","Namur - Antwerpen",">","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,19,19,"2025-05-11",45644,"2025-05-11",45644.736111111109,"2d, 17:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing wisselonderdelen en sporen te Antwerpen Schijnpoort inrit bundel F\r\n\r\nmet inbegrip van bundelkop bundel D-F (K-Q.12-T-O.12) +L27A spA zo 00:00 tot 17:40\r\nsamen met colt 69464",null,null,75782,"2024-03-27",0,"5,6"]
[null,"Infrabel","79794","Namur - Antwerpen",">","Y.ZUID GROENENHOEK","Y.ANTWERPEN-SCHIJNPOORT",2025,2025,19,19,"2025-05-11",45644.020833333336,"2025-05-11",45644.708333333336,"1d, 16:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-115\r\nRVN tgv zijdelingse sleet en degradatie GIV's \r\nstaat GIV's is dermate snel achteruit gegaan dat  de aanvraag niet tijdig ingepland is\r\nR-513606",null,null,79794,"2024-10-03",0,"5,6"]
[null,"Infrabel","69512","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.OOST BERCHEM",2025,2025,19,19,"2025-05-11",45644.020833333336,"2025-05-11",45644.708333333336,"2d, 16:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug",null,null,69512,"2024-03-12",0,"5,6"]
[null,"Infrabel","79793","Namur - Antwerpen",">","Y.ZUID GROENENHOEK","Y.ANTWERPEN-SCHIJNPOORT",2025,2025,19,20,"2025-05-11",45644.020833333336,"2025-05-12",45644.166666666664,"1d, 03:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-115\r\nRVN tgv zijdelingse sleet en degradatie GIV's \r\nstaat GIV's is dermate snel achteruit gegaan dat  de aanvraag niet tijdig ingepland is\r\nR-513606",null,null,79793,"2024-10-03",0,"5,6"]
[null,"Infrabel","69403","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,19,19,"2025-05-11",45644.25,"2025-05-11",45644.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing wisselonderdelen en sporen te Anwerpen Schijnpoort inrit bundel F.  \r\nMet inbegrip van bundelkop van bundel D - F (K-Q.12 - T-O.12) + L27A sp A zo 0:00u tot ma 5:00u, L27A Sp B zo 6:00u tot 17:40u",null,null,69403,"2024-11-20",0,"5,6"]
[null,"Infrabel","72559","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,19,19,"2025-05-11",45644.3125,"2025-05-11",45644.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72559,"2024-12-05",0,"5,6"]
[null,"Infrabel","71113","Namur - Antwerpen","< >","NAMUR","RONET",2025,2025,19,19,"2025-05-11",45644.003472222219,"2025-05-11",45644.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur ZONE 6\r\nZ6.43\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,71113,"2024-12-06",0,"5,6"]
[null,"Infrabel","67040","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,20,20,"2025-05-12",45644.958333333336,"2025-05-16",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Dépose console sur L144. (entre L130 et PN10)\r\nUPM: 488650",null,null,67040,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","72722","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,20,20,"2025-05-12",45644.979166666664,"2025-05-17",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72722,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","69568","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,20,20,"2025-05-12",45644,"2025-05-16",45644.541666666664,"6d, 13:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossen wissels.\r\nVernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!\r\n\r\n",null,null,69568,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","72949","Lille - Charleroi",">","HALLE","LOT",2025,2025,20,20,"2025-05-12",45644.9375,"2025-05-17",45644.197916666664,"5d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FH_09 volgens onderhoudskalender Area CE\r\nL96 spoor B + L94 spoor A + L26 sp A\r\nBescherming L94 sp B en L96 sp A BUV \r\n\r\nR5/R6: sp A L96 met ATW/TX",null,null,72949,"2024-03-01",0,"1,2,3,4,5"]
[null,"Infrabel","68332","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,20,20,"2025-05-12",45644.965277777781,"2025-05-17",45644.229166666664,"5d, 06:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Pose structure quai voie I - cage d'ascenseur\tcoffrage / ferraillage / décoffrage.",null,null,68332,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","75208","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2025,2025,20,20,"2025-05-12",45644.989583333336,"2025-05-17",45644.21875,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3\r\n",null,null,75208,"2024-12-13",0,"1,2,3,4,5"]
[null,"Infrabel","66400","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.SOIGNIES",2025,2025,20,20,"2025-05-12",45644.954861111109,"2025-05-16",45644.1875,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.53 en P3 HKV",null,null,66400,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","53225","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,20,20,"2025-05-12",45644.909722222219,"2025-05-16",45644.229166666664,"4d, 07:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - Phase 2025\r\nNuits préparatoires\r\n+ Maintenance Z5.52 P3\r\nTCR: 489092",null,null,53225,"2024-12-03",0,"1,2,3,4,5"]
[null,"Infrabel","77625","Athus - Meuse","< >","AUBANGE-FRONTIERE-FRANCE","Y.AUBANGE",2025,2025,20,20,"2025-05-12",45644.375,"2025-05-12",45644.5,"1d, 03:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite voie unique L 165/2 \r\nVisite voie unique L 165/3\r\nVisite voie unique L 165/1",null,null,77625,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","72931","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2025,2025,20,20,"2025-05-12",45644.378472222219,"2025-05-12",45644.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,72931,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","73125","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2025,2025,20,20,"2025-05-12",45644.423611111109,"2025-05-12",45644.493055555555,"1d, 01:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,73125,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","76376","Lille - Charleroi",">","Y.FELUY","MANAGE",2025,2025,20,20,"2025-05-13",45644.333333333336,"2025-05-13",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagno J6",null,null,76376,"2024-12-03",0,"1,2,3,4,5"]
[null,"Infrabel","67901","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,20,20,"2025-05-13",45644.020833333336,"2025-05-16",45644.208333333336,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67901,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","74479","Lille - ZeeBrugge",">","BRUGGE","Y.BLAUWE TOREN",2025,2025,20,20,"2025-05-13",45644.354166666664,"2025-05-13",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudswerken SK  Brugge St. Pieters. - TCR 507570\r\nDoes via sp B L51 tss Brugge en Y. Bl. Toren.\r\nWisselcomplex  13AU/BU dient vrij te blijven.",null,null,74479,"2024-08-09",0,"1,2,3,4,5"]
[null,"Infrabel","70501","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.HOLLAND",2025,2025,20,20,"2025-05-13",45644.354166666664,"2025-05-15",45644.645833333336,"3d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud bundelkop bundel E te Antwerpen schijnpoort thv sein O-N.12 en N-N.12 en M-N.12 en T-Q.12\r\nwissels  33AN, 33BN, 31AN/32N, 31BN, 01Q, 02Q, 03Q",null,null,70501,"2024-04-30",0,"1,2,3,4,5"]
[null,"Infrabel","71145","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,20,20,"2025-05-13",45644.350694444445,"2025-05-13",45644.625,"1d, 06:35h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,71145,"2024-12-11",0,"1,2,3,4,5"]
[null,"Infrabel","77258","Athus - Meuse",">","HOUYET","BEAURAING",2025,2025,20,20,"2025-05-13",45644.388888888891,"2025-05-13",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,77258,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","73083","Athus - Meuse",">","SIGNEULX","HALANZY",2025,2025,20,20,"2025-05-14",45644.333333333336,"2025-05-14",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73083,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","77259","Athus - Meuse",">","BEAURAING","HOUYET",2025,2025,20,20,"2025-05-14",45644.388888888891,"2025-05-14",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,77259,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","73702","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,20,20,"2025-05-15",45644.034722222219,"2025-05-17",45644.180555555555,"3d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie Onderhoud nachtdienst Schets 3 - TCR 502325\r\nFGSP Perronspoor I tem IV tot L50E SP A  tot 02BO niet inbegrepen + L50E SP B tot 05O niet inbegrepen \r\n+ verlengde van de perrons I+II kant kust L50A6 inbegrepen, L75 vrij te houden voor verkeer\r\n",null,null,73702,"2024-08-09",0,"1,2,3,4,5"]
[null,"Infrabel","74485","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BRUGGE",2025,2025,20,20,"2025-05-15",45644.354166666664,"2025-05-15",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudswerken SK  Brugge St. Pieters. - TCR 507560\r\nDoes via sp A L51 tss Brugge en Brugge St. Pieters.\r\nWisselcomplex 12AU/BU en 13AU/BU dient vrij te blijven.\r\nBVL 29522",null,null,74485,"2024-08-09",0,"1,2,3,4,5"]
[null,"Infrabel","73084","Athus - Meuse",">","HALANZY","SIGNEULX",2025,2025,20,20,"2025-05-15",45644.347222222219,"2025-05-15",45644.645833333336,"1d, 07:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie  B",null,null,73084,"2024-12-11",0,"1,2,3,4,5"]
[null,"Infrabel","56528","Athus - Meuse",">","GEDINNE","PALISEUL",2025,2025,20,20,"2025-05-16",45644.270833333336,"2025-05-17",45644.25,"1d, 23:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 1 - WE 4\r\nDossier de concertation octobre 2022 - CR 2025-037\r\nUPM:491544",null,null,56528,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","53228","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,20,21,"2025-05-16",45644.930555555555,"2025-05-19",45644.229166666664,"2d, 07:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - Phase 2025\r\nWE 2\r\nTCR: 488973",null,null,53228,"2024-12-03",1,"5,6"]
[null,"Infrabel","64237","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,20,21,"2025-05-17",45644.986111111109,"2025-05-19",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais\r\nUPM: 489237",null,null,64237,"2024-12-12",0,"5,6"]
[null,"Infrabel","53524","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2025,2025,20,21,"2025-05-17",45644.25,"2025-05-19",45644.201388888891,"2d, 22:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15. 51 P4+\r\n+Réélectrification L130 (travaux voie A entre R88/5 et R89/3)\r\nTir caténaires\r\nTCR: 492787",null,null,53524,"2024-12-10",1,"5,6"]
[null,"Infrabel","56526","Athus - Meuse","< >","BEAURAING","BERTRIX",2025,2025,20,21,"2025-05-17",45644.25,"2025-05-19",45644.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 1 - WE 4\r\nDossier de concertation octobre 2022 - CR 2025-037\r\nUPM:491539\r\n intégrer visites VA + VB Vonêche - Gedinne",null,null,56526,"2024-12-10",1,"5,6"]
[null,"Infrabel","68385","Lille - Antwerpen",">","Y.WEST BERCHEM","ZWIJNDRECHT-ROOSTER D",2025,2025,20,21,"2025-05-17",45644.041666666664,"2025-05-19",45644.1875,"2d, 03:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Stationsproject Antwerpen-Zuid B-Stations:\r\n\r\nTrapconstructie op perron\r\n\r\nIndien weekend 11+12  in orde deze niet nodig!",null,null,68385,"2024-05-17",0,"5,6"]
[null,"Infrabel","69561","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,20,21,"2025-05-17",45644.041666666664,"2025-05-19",45644.125,"2d, 02:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!",null,null,69561,"2024-12-05",1,"5,6"]
[null,"Infrabel","57977","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,20,21,"2025-05-17",45644.000694444447,"2025-05-19",45644.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwarsliggers",null,null,57977,"2024-11-12",1,"5,6"]
[null,"Infrabel","68798","Namur - Antwerpen",">","Y.LOUVAIN-LA-NEUVE","GEMBLOUX",2025,2025,20,20,"2025-05-17",45644.354166666664,"2025-05-17",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie A Ottignies - Gembloux\r\nUPM: 488035",null,null,68798,"2024-12-13",0,"5,6"]
[null,"Infrabel","70478","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2025,2025,20,20,"2025-05-17",45644.326388888891,"2025-05-17",45644.722222222219,"1d, 09:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen Oost - Antwerpen - Schijnpoort",null,null,70478,"2024-07-25",0,"5,6"]
[null,"Infrabel","68800","Namur - Antwerpen",">","Y.LOUVAIN-LA-NEUVE","GEMBLOUX",2025,2025,20,20,"2025-05-18",45644.333333333336,"2025-05-18",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie B Ottignies - Gembloux (extension Rhisnes SAS)\r\nUPM: 488046",null,null,68800,"2024-12-13",0,"5,6"]
[null,"Infrabel","67318","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ANTWERPEN-D.S.-RHODESIE",2025,2025,20,20,"2025-05-18",45644.25,"2025-05-18",45644.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,67318,"2024-03-28",1,"5,6"]
[null,"Infrabel","73703","Namur - Antwerpen","< >","GENT-SINT-PIETERS","MERELBEKE-ROOSTER S",2025,2025,20,20,"2025-05-18",45644.034722222219,"2025-05-18",45644.243055555555,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud schets za^zo - TCR 502327\r\n\r\nL50E TLO Rooster S tot FGSP\r\nL58 + L58/1 TLO tot FGDM",null,null,73703,"2024-08-09",0,"5,6"]
[null,"Infrabel","59472","Namur - Antwerpen",">","AUVELAIS","MOUSTIER",2025,2025,21,21,"2025-05-19",45644.958333333336,"2025-05-24",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nDépose portiques Moustier- Auvelais\r\nUPM: 489591",null,null,59472,"2024-01-17",0,"1,2,3,4,5"]
[null,"Infrabel","68067","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,21,21,"2025-05-19",45644.958333333336,"2025-05-24",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Dépose poteaux caténaire sur L144. (entre L130 et PN10)\r\nUPM: 488652",null,null,68067,"2024-01-10",0,"1,2,3,4,5"]
[null,"Infrabel","71756","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,21,21,"2025-05-19",45644.333333333336,"2025-05-19",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nTCR 507453",null,null,71756,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","71894","Namur - Antwerpen","< >","VILVOORDE","MECHELEN",2025,2025,21,21,"2025-05-19",45644.979166666664,"2025-05-24",45644.197916666664,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKV\r\nZ02.23.02",null,null,71894,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","69708","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,21,21,"2025-05-19",45644.979166666664,"2025-05-24",45644.197916666664,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Omvorming 50Hz naar TFSK (L27+L27B+L27B1): \r\n- 2 weken WN van ma-> za in april/mei 2025 (samenwerken ok)\r\n\r\nCR-2025-238",null,null,69708,"2024-12-11",0,"1,2,3,4,5"]
[null,"Infrabel","72952","Lille - Charleroi","< >","Y.RUISBROEK","Y.NOORD HALLE",2025,2025,21,21,"2025-05-19",45644.979166666664,"2025-05-24",45644.197916666664,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone FH_07 Area CE volgens onderhoudskalender 2025.\r\n\r\nBuitendienststelling L96 sporen A en B tussen Y Ruisbroek en Y Noord Halle + L96E.",null,null,72952,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","72182","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2025,2025,21,21,"2025-05-19",45644.96875,"2025-05-24",45644.1875,"5d, 05:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKV",null,null,72182,"2024-12-09",0,"1,2,3,4,5"]
[null,"Infrabel","72361","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2025,2025,21,21,"2025-05-19",45644.965277777781,"2025-05-24",45644.1875,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien massification\r\nMaintenance Z2.44\r\nTCR 507162",null,null,72361,"2024-10-24",0,"1,2,3,4,5"]
[null,"Infrabel","68333","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,21,21,"2025-05-19",45644.965277777781,"2025-05-24",45644.229166666664,"5d, 06:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Pose bardage/faux plafond quai voie I - cage d'ascenseur : béton.",null,null,68333,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","56538","Athus - Meuse",">","GEDINNE","PALISEUL",2025,2025,21,21,"2025-05-19",45644.1875,"2025-05-19",45644.6875,"1d, 12:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 1 - WE 4\r\nDossier de concertation octobre 2022 - CR 2025-037\r\nUPM:491536",null,null,56538,"2024-12-16",0,"1,2,3,4,5"]
[null,"Infrabel","69570","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,21,21,"2025-05-19",45644.291666666664,"2025-05-23",45644.541666666664,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!",null,null,69570,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","71843","Namur - Antwerpen","< >","Y.SCHAERBEEK-GROUPE G","VILVOORDE",2025,2025,21,21,"2025-05-19",45644.041666666664,"2025-05-24",45644.166666666664,"6d, 03:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71843,"2023-12-15",0,"1,2,3,4,5"]
[null,"Infrabel","71240","Namur - Antwerpen","< >","Y.NAZARETH","HEIST-OP-DEN-BERG",2025,2025,21,21,"2025-05-19",45644.996527777781,"2025-05-24",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKM ZBB.23",null,null,71240,"2024-12-09",0,"1,2,3,4,5"]
[null,"Infrabel","75209","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2025,2025,21,21,"2025-05-19",45644.993055555555,"2025-05-23",45644.180555555555,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3\r\n",null,null,75209,"2024-03-18",0,"1,2,3,4,5"]
[null,"Infrabel","53226","Lille - Charleroi","< >","Y.FAMILLEUREUX","LUTTRE",2025,2025,21,21,"2025-05-19",45644.909722222219,"2025-05-24",45644.229166666664,"5d, 07:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - Phase 2025\r\nNuits préparatoires\r\n+ Maintenance Z8.52 P3 HKV\r\nTCR: 489093",null,null,53226,"2024-12-03",0,"1,2,3,4,5"]
[null,"Infrabel","71664","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2025,2025,21,21,"2025-05-19",45644.947916666664,"2025-05-24",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud zone 05.32 - TCR 500421\r\nL58 Eeklo inbegrepen tot Gent Dampoort NIET inbegrepen",null,null,71664,"2024-08-12",0,"1,2,3,4,5"]
[null,"Infrabel","75387","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,21,21,"2025-05-19",45644.395833333336,"2025-05-19",45644.645833333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"DOES Schouwen sporen overdag.TCR 510883",null,null,75387,"2024-08-09",0,"1,2,3,4,5"]
[null,"Infrabel","73140","Athus - Meuse",">","NAMUR","JAMBES",2025,2025,21,21,"2025-05-19",45644.388888888891,"2025-05-19",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73140,"2024-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","56038","Athus - Meuse",">","GEDINNE","RACC.JEHONVILLE-M.D.N.",2025,2025,21,21,"2025-05-20",45644.958333333336,"2025-05-24",45644.229166666664,"4d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 1 - Finitions\r\nDossier de concertation octobre 2022 - CR 2025-037\r\nUPM:491521",null,null,56038,"2024-12-16",0,"1,2,3,4,5"]
[null,"Infrabel","59689","Lille - Charleroi","< >","Y.NOORD HALLE","TUBIZE",2025,2025,21,21,"2025-05-20",45644.03125,"2025-05-23",45644.177083333336,"4d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's 96/94 kant Lembeek zone A12-A13",null,null,59689,"2024-03-04",0,"1,2,3,4,5"]
[null,"Infrabel","67791","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,21,21,"2025-05-20",45644.020833333336,"2025-05-23",45644.1875,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud - TCR 493200\r\nFLC SP III-IV inbegrepen\r\n\r\nR5/R6 in weekendTLO",null,null,67791,"2024-08-12",0,"1,2,3,4,5"]
[null,"Infrabel","67902","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,21,21,"2025-05-20",45644.020833333336,"2025-05-24",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67902,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","66200","Lille - Charleroi","< >","LEMBEEK","BRAINE-LE-COMTE",2025,2025,21,21,"2025-05-20",45644.013888888891,"2025-05-24",45644.1875,"5d, 04:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.53 P3 HKM",null,null,66200,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","72723","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,21,21,"2025-05-20",45644.003472222219,"2025-05-24",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72723,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","72773","Athus - Meuse",">","STOCKEM-NORD","ARLON",2025,2025,21,21,"2025-05-20",45644.361111111109,"2025-05-20",45644.541666666664,"1d, 04:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie ",null,null,72773,"2024-12-16",0,"1,2,3,4,5"]
[null,"Infrabel","70502","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.HOLLAND",2025,2025,21,21,"2025-05-20",45644.354166666664,"2025-05-22",45644.645833333336,"3d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud bundelkop bundel F te Antwerpen schijnpoort thv sein C-Q.12\r\nwissels  04Q/05Q, 06Q, 07Q, 08Q, 09Q, 10Q",null,null,70502,"2024-04-30",0,"1,2,3,4,5"]
[null,"Infrabel","72772","Athus - Meuse",">","HABAY","STOCKEM-NORD",2025,2025,21,21,"2025-05-21",45644.368055555555,"2025-05-21",45644.628472222219,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72772,"2024-12-16",0,"1,2,3,4,5"]
[null,"Infrabel","73365","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,21,21,"2025-05-21",45644.375,"2025-05-21",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73365,"2024-03-29",0,"1,2,3,4,5"]
[null,"Infrabel","73110","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,21,21,"2025-05-22",45644.333333333336,"2025-05-22",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73110,"2024-12-16",0,"1,2,3,4,5"]
[null,"Infrabel","73366","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,21,21,"2025-05-22",45644.375,"2025-05-22",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73366,"2024-03-29",0,"1,2,3,4,5"]
[null,"Infrabel","67462","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2025,2025,21,21,"2025-05-22",45644.395833333336,"2025-05-22",45644.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53\r\nMise HS en P2\r\nTCR 489203",null,null,67462,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","80370","Athus - Meuse","< >","CINEY","MARLOIE",2025,2025,21,22,"2025-05-23",45644.986111111109,"2025-05-26",45644.180555555555,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-142 accepté\r\nTravaux Axe 3:\r\nMassification travaux OA:\r\n- pose super structure PS de Leignon (dans le cadre de la supression PN de Leignon)\r\n- Pose  cadre du futur CSV au droit du nouveau PANG de Chapois \r\n+ massification Travaux préparatoires p",null,null,80370,"2024-12-16",1,"5,6"]
[null,"Infrabel","76422","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2025,2025,21,21,"2025-05-23",45644.326388888891,"2025-05-23",45644.645833333336,"1d, 07:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visites J10",null,null,76422,"2024-12-03",0,"1,2,3,4,5"]
[null,"Infrabel","73111","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,21,21,"2025-05-23",45644.34375,"2025-05-23",45644.652777777781,"1d, 07:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73111,"2024-12-16",0,"1,2,3,4,5"]
[null,"Infrabel","69441","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2025,2025,21,22,"2025-05-24",45644.958333333336,"2025-05-26",45644.201388888891,"2d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing spoorstaven tussen Y Liersesteenweg en Y Krijgsbaan. \r\nBuitendienststelling van L27 Kontich tot L27A Y Zuid Groenenhoek \r\n2 TLO Weekenden van +48u nodig --> L27 enkel tijdens nachten ingevoerd\r\nvoorkeur 17-18/05/2025 en 24-25/05/202\r\n--> hor",null,null,69441,"2024-06-28",0,"5,6"]
[null,"Infrabel","71178","Erquelinnes - Montzen",">","AMAY","ENGIS",2025,2025,21,21,"2025-05-24",45644.333333333336,"2025-05-24",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71178,"2024-12-13",0,"1,2,3,4,5"]
[null,"Infrabel","68058","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2025,2025,21,21,"2025-05-24",45644.333333333336,"2025-05-24",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130\r\nUPM: 489011",null,null,68058,"2024-01-12",0,"5,6"]
[null,"Infrabel","77158","Athus - Meuse",">","BEAURAING","VONECHE",2025,2025,21,21,"2025-05-24",45644.333333333336,"2025-05-24",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,77158,"2024-12-16",0,"5,6"]
[null,"Infrabel","68176","Namur - Antwerpen",">","OTTIGNIES","WAVRE",2025,2025,21,21,"2025-05-24",45644.333333333336,"2025-05-24",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Ottignies - Wavre VA/VB\r\nUPM: 488497",null,null,68176,"2024-01-09",0,"5,6"]
[null,"Infrabel","74913","Namur - Antwerpen","< >","DENDERMONDE","LONDERZEEL",2025,2025,21,21,"2025-05-24",45644.979166666664,"2025-05-25",45644.222222222219,"1d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Lossen LGS Röbeltrein  - TCR 499324",null,null,74913,"2024-08-12",0,"5,6"]
[null,"Infrabel","75565","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.NOORD BERCHEM",2025,2025,21,22,"2025-05-24",45644.979166666664,"2025-05-26",45644.1875,"1d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud wissels Y Noord Groenenhoek",null,null,75565,"2024-02-05",0,"5,6"]
[null,"Infrabel","59680","Lille - Charleroi","< >","Y.NOORD HALLE","TUBIZE",2025,2025,21,22,"2025-05-24",45644.03125,"2025-05-26",45644.177083333336,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen BVL L96 + aw's 96/94 kant Lembeek zone A12-A13\r\nCf Escalade Head Of nov/dec 2023",null,null,59680,"2023-12-15",1,"5,6"]
[null,"Infrabel","68827","Lille - Charleroi","< >","Y.NOORD HALLE","TUBIZE",2025,2025,21,22,"2025-05-24",45644.03125,"2025-05-26",45644.177083333336,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone FH_11 volgens onderhoudskalender Area CE\r\n\r\nTLO op L96",null,null,68827,"2024-08-19",1,"5,6"]
[null,"Infrabel","67770","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,21,22,"2025-05-24",45644.020833333336,"2025-05-26",45644.1875,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud - TCR 493222",null,null,67770,"2024-08-12",1,"5,6"]
[null,"Infrabel","53465","Lille - Charleroi","< >","LEMBEEK","BRAINE-LE-COMTE",2025,2025,21,22,"2025-05-24",45644.1875,"2025-05-26",45644.1875,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Réélectrification entre Lembeek et Braine-le-Comte\r\nCTL WE\r\n+ Maintenance Z1.53 en P4\r\nTCR 489204",null,null,53465,"2024-12-10",1,"5,6"]
[null,"Infrabel","53520","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","CHATELET-GRIL EST",2025,2025,21,21,"2025-05-24",45644.25,"2025-05-25",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10. 51   P4+\r\nTCR: 491787",null,null,53520,"2024-12-10",1,"5,6"]
[null,"Infrabel","83873","Lille - Charleroi","< >","MONCEAU-GRIL F","MONCEAU-GRIL F",2025,2025,21,21,"2025-05-24",45644.25,"2025-05-25",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Traverses et Rail voie 812",null,null,83873,"2024-12-16",1,"5,6"]
[null,"Infrabel","66507","Namur - Antwerpen","< >","SINT-JORIS-WEERT","WAVRE",2025,2025,21,22,"2025-05-24",45644.25,"2025-05-26",45644.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Intervention PN + Entretien divers\r\nUPM: 488547",null,null,66507,"2024-06-20",1,"5,6"]
[null,"Infrabel","69440","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.OOST BERCHEM",2025,2025,21,22,"2025-05-24",45644.25,"2025-05-26",45644.201388888891,"2d, 22:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing spoorstaven tussen Y Liersesteenweg en Y Krijgsbaan. \r\nBuitendienststelling van L27 Kontich tot L27A Y Zuid Groenenhoek.",null,null,69440,"2024-03-12",1,"5,6"]
[null,"Infrabel","57978","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,21,22,"2025-05-24",45644.25,"2025-05-26",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwaarsliggers",null,null,57978,"2024-11-12",1,"5,6"]
[null,"Infrabel","69562","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,21,22,"2025-05-24",45644.041666666664,"2025-05-26",45644.125,"2d, 02:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!",null,null,69562,"2024-12-05",1,"5,6"]
[null,"Infrabel","75469","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2025,2025,21,21,"2025-05-24",45644.354166666664,"2025-05-24",45644.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2025: L140 Partie 1",null,null,75469,"2024-12-10",0,"5,6"]
[null,"Infrabel","68059","Namur - Antwerpen",">","AUVELAIS","FLAWINNE",2025,2025,21,21,"2025-05-25",45644.333333333336,"2025-05-25",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130\r\nUPM: 489220",null,null,68059,"2024-01-15",0,"5,6"]
[null,"Infrabel","68175","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2025,2025,21,21,"2025-05-25",45644.333333333336,"2025-05-25",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Sint-Joris-Weert - Wavre VA/VB\r\nUPM: 488512",null,null,68175,"2024-01-09",0,"5,6"]
[null,"Infrabel","71179","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2025,2025,21,21,"2025-05-25",45644.354166666664,"2025-05-25",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,71179,"2024-12-13",0,"5,6"]
[null,"Infrabel","75473","Namur - Antwerpen",">","FLEURUS","CHARLEROI-OUEST",2025,2025,21,21,"2025-05-25",45644.354166666664,"2025-05-25",45644.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2025: L140 Partie 2",null,null,75473,"2024-12-10",0,"5,6"]
[null,"Infrabel","77159","Athus - Meuse",">","VONECHE","BEAURAING",2025,2025,21,21,"2025-05-25",45644.34375,"2025-05-25",45644.659722222219,"1d, 07:35h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,77159,"2024-12-16",0,"5,6"]
[null,"Infrabel","72145","Namur - Antwerpen","< >","LEUVEN","WAVRE",2025,2025,22,22,"2025-05-26",45644.958333333336,"2025-05-29",45644.215277777781,"3d, 06:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKV",null,null,72145,"2024-04-11",0,"1,2,3,4,5"]
[null,"Infrabel","55166","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,22,22,"2025-05-26",45644.958333333336,"2025-05-31",45644.201388888891,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022\r\nTCR: 492788",null,null,55166,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","73394","Athus - Meuse",">","Y.NEFFE","DINANT",2025,2025,22,22,"2025-05-26",45644.333333333336,"2025-05-26",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,73394,"2023-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","53508","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2025,2025,22,22,"2025-05-26",45644.979166666664,"2025-05-31",45644.229166666664,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z9.52 + Maintenance Z.3.53 en P3 HKV",null,null,53508,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","71286","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","FLEMALLE-HAUTE",2025,2025,22,22,"2025-05-26",45644.951388888891,"2025-05-30",45644.201388888891,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.43 HKV + Z9.41 P3",null,null,71286,"2024-12-16",0,"1,2,3,4,5"]
[null,"Infrabel","68334","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,22,22,"2025-05-26",45644.972222222219,"2025-05-31",45644.201388888891,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : finitions + cage d'ascenseur - décoffrage",null,null,68334,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","74338","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,22,22,"2025-05-26",45644.965277777781,"2025-05-29",45644.243055555555,"3d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose poteaux caténaire sur L144. (entre L130 et PN10)",null,null,74338,"2023-12-15",0,"1,2,3,4,5"]
[null,"Infrabel","55581","Lille - Charleroi","< >","HALLE","ENGHIEN",2025,2025,22,22,"2025-05-26",45644.965277777781,"2025-05-31",45644.194444444445,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Nuits de préparation - Construction d'un PI - PN16\r\nUPM 487945",null,null,55581,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","55523","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,22,22,"2025-05-26",45644.965277777781,"2025-05-31",45644.204861111109,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes - 36.363 38.279\r\nPréparations\r\n+ Maintenance Z3.51 P3 (voies I et II de Fleurus comprises)\r\nTCR: 488137",null,null,55523,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","66504","Namur - Antwerpen","< >","OTTIGNIES","WAVRE",2025,2025,22,22,"2025-05-26",45644.986111111109,"2025-05-30",45644.215277777781,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien Maintenance\r\nTCR 507195",null,null,66504,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","69571","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,22,22,"2025-05-26",45644.291666666664,"2025-05-28",45644.541666666664,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!",null,null,69571,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","71707","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,22,22,"2025-05-26",45644.361111111109,"2025-05-26",45644.645833333336,"1d, 06:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance\r\nTCR 507128",null,null,71707,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","54153","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,22,23,"2025-05-26",45644.263888888891,"2025-06-02",45644.208333333336,"7d, 22:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - Phase 2025\r\nCTL 1 semaine\r\nTCR: 489097\r\nDiagno J27 massifiée le 26/05/25 de 08.00 à 15.00",null,null,54153,"2024-12-04",1,"1,2,3,4,5,6,7"]
[null,"Infrabel","72775","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2025,2025,22,22,"2025-05-26",45644.409722222219,"2025-05-26",45644.625,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72775,"2023-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","72377","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2025,2025,22,22,"2025-05-26",45644.381944444445,"2025-05-26",45644.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41",null,null,72377,"2023-10-26",0,"1,2,3,4,5"]
[null,"Infrabel","67933","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,22,22,"2025-05-27",45644.020833333336,"2025-05-31",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67933,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","67792","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,22,22,"2025-05-27",45644.020833333336,"2025-05-31",45644.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud  - TCR 493226\r\nFLC SP III-IV inbegrepen",null,null,67792,"2024-08-12",0,"1,2,3,4,5"]
[null,"Infrabel","70568","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,22,22,"2025-05-27",45644.986111111109,"2025-05-29",45644.236111111109,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen van Y Arendstraat",null,null,70568,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","70578","Namur - Antwerpen","< >","Y.BERCHEM-STADION","Y.ARENDSTRAAT",2025,2025,22,22,"2025-05-27",45644.083333333336,"2025-05-29",45644.125,"3d, 01:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen van Y Noord Berchem",null,null,70578,"2024-06-26",0,"1,2,3,4,5"]
[null,"Infrabel","72724","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,22,22,"2025-05-27",45644.003472222219,"2025-05-31",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72724,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","73395","Athus - Meuse",">","DINANT","Y.NEFFE",2025,2025,22,22,"2025-05-27",45644.34375,"2025-05-27",45644.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites VA",null,null,73395,"2023-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","72769","Athus - Meuse",">","LAVAUX","MARBEHAN",2025,2025,22,22,"2025-05-28",45644.361111111109,"2025-05-28",45644.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72769,"2023-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","73019","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,22,22,"2025-05-29",45644.333333333336,"2025-05-29",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73019,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","64661","Athus - Meuse",">","ARLON","ARLON",2025,2025,22,22,"2025-05-29",45644.333333333336,"2025-06-01",45644.25,"3d, 22:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de la TJD 29L/28BL\r\nUPM 490361",null,null,64661,"2024-11-26",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","84375","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,22,22,"2025-05-29",45644.291666666664,"2025-05-29",45644.916666666664,"2d, 15:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!",null,null,84375,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","72768","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2025,2025,22,22,"2025-05-29",45644.368055555555,"2025-05-29",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72768,"2023-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","77165","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2025,2025,22,22,"2025-05-29",45644.388888888891,"2025-05-29",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA (périodicité 3 semaines)",null,null,77165,"2024-03-14",0,"1,2,3,4,5"]
[null,"Infrabel","79181","Athus - Meuse","< >","ARLON","ARLON",2025,2025,22,22,"2025-05-30",45644.916666666664,"2025-06-01",45644.166666666664,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-098: Renouvellement de la TJD 29L/28BL \r\nacheminement TJD et pose + rectification dévers voie 363\r\n intervention caténaire\r\nTCR 512492",null,null,79181,"2024-11-26",0,"5,6"]
[null,"Infrabel","70701","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2025,2025,22,22,"2025-05-30",45644.013888888891,"2025-05-31",45644.194444444445,"2d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen\r\nHKM",null,null,70701,"2024-01-26",0,"1,2,3,4,5"]
[null,"Infrabel","84376","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,22,22,"2025-05-30",45644.291666666664,"2025-05-30",45644.541666666664,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!",null,null,84376,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","59623","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,22,23,"2025-05-30",45644.993055555555,"2025-06-02",45644.1875,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification OA\r\nSuppression des PN 56 et 58 - Poussage PI\r\nPS Maréchal Juin BK45.631 - Démolition\r\nChapes d'étanchéité\r\n+ Mise au gabarit des pistes Namur Rhisnes parois rocheuses.\r\n+ Travaux caténaires\r\n10 - Déroulage liaisons Namur- Gembloux\r\nUPM: 4",null,null,59623,"2024-07-15",1,"5,6"]
[null,"Infrabel","72767","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2025,2025,22,22,"2025-05-30",45644.368055555555,"2025-05-30",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72767,"2023-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","77166","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2025,2025,22,22,"2025-05-30",45644.34375,"2025-05-30",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,77166,"2024-03-14",0,"1,2,3,4,5"]
[null,"Infrabel","72341","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,22,23,"2025-05-31",45644.979166666664,"2025-06-02",45644.166666666664,"1d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing spoorstaven tussen Y Liersesteenweg en Y Krijgsbaan.",null,null,72341,"2024-03-12",1,"5,6"]
[null,"Infrabel","67929","Lille - Charleroi","< >","ATH","ENGHIEN",2025,2025,22,23,"2025-05-31",45644.25,"2025-06-02",45644.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux PLP\r\nUPM 487893",null,null,67929,"2024-12-10",1,"5,6"]
[null,"Infrabel","69760","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,22,23,"2025-05-31",45644.25,"2025-06-02",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"sporen 5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde",null,null,69760,"2023-08-31",1,"5,6"]
[null,"Infrabel","69563","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,22,23,"2025-05-31",45644.041666666664,"2025-06-02",45644.125,"2d, 02:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!",null,null,69563,"2024-12-05",1,"5,6"]
[null,"Infrabel","57979","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,22,23,"2025-05-31",45644.000694444447,"2025-06-02",45644.166666666664,"2d, 03:59h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwaarsliggers",null,null,57979,"2024-11-12",1,"5,6"]
[null,"Infrabel","73185","Athus - Meuse",">","LIBRAMONT","HATRIVAL",2025,2025,22,22,"2025-05-31",45644.385416666664,"2025-05-31",45644.611111111109,"1d, 05:25h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73185,"2023-11-15",0,"5,6"]
[null,"Infrabel","73167","Athus - Meuse",">","JAMBES","LUSTIN",2025,2025,22,22,"2025-05-31",45644.385416666664,"2025-05-31",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73167,"2023-11-13",0,"5,6"]
[null,"Infrabel","80256","Athus - Meuse",">","NAMUR","BOIS D'AUSSE",2025,2025,22,22,"2025-05-31",45644.375,"2025-05-31",45644.677083333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-085 \r\nVisite périodique de jour le samedi pour AI43. (suite mise en service ETCS)\r\nVA: Le samedi entre 9h et 16h15\r\nVB: Le Samedi entre 8h45 et 16h\r\nA dupliquer toutes les 8 semaines.\r\n",null,null,80256,"2024-08-02",0,"5,6"]
[null,"Infrabel","72774","Athus - Meuse",">","ARLON","Y.AUTELBAS",2025,2025,22,22,"2025-05-31",45644.361111111109,"2025-05-31",45644.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72774,"2023-11-08",0,"5,6"]
[null,"Infrabel","71108","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2025,2025,22,23,"2025-06-01",45644.958333333336,"2025-06-02",45644.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nZ7.43",null,null,71108,"2024-02-07",0,"1,2,3,4,5"]
[null,"Infrabel","78090","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2025,2025,22,23,"2025-06-01",45644.958333333336,"2025-06-02",45644.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Préparation au Criblage 102500-98200",null,null,78090,"2024-04-12",0,"5,6"]
[null,"Infrabel","67319","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ANTWERPEN-D.S.-RHODESIE",2025,2025,22,22,"2025-06-01",45644.25,"2025-06-01",45644.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,67319,"2024-03-28",1,"5,6"]
[null,"Infrabel","73171","Athus - Meuse",">","LUSTIN","JAMBES",2025,2025,22,22,"2025-06-01",45644.385416666664,"2025-06-01",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES",null,null,73171,"2023-11-13",0,"5,6"]
[null,"Infrabel","72770","Athus - Meuse",">","MARBEHAN","HABAY",2025,2025,22,22,"2025-06-01",45644.375,"2025-06-01",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72770,"2023-11-08",0,"5,6"]
[null,"Infrabel","53457","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2025,2025,23,23,"2025-06-02",45644.958333333336,"2025-06-06",45644.173611111109,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Second tabliers ponts 7,8 et 9 + Renouvellement AS de Lobbes-Garage & Hourpes\r\nNuits de finition\r\nTCR 487631",null,null,53457,"2024-01-03",0,"1,2,3,4,5"]
[null,"Infrabel","68124","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,23,23,"2025-06-02",45644.958333333336,"2025-06-07",45644.201388888891,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022\r\nTCR: 493756",null,null,68124,"2024-06-26",0,"1,2,3,4,5"]
[null,"Infrabel","74595","Lille - Charleroi",">","ATH","BRUGELETTE",2025,2025,23,23,"2025-06-02",45644.333333333336,"2025-06-02",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno",null,null,74595,"2023-12-22",0,"1,2,3,4,5"]
[null,"Infrabel","71746","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2025,2025,23,23,"2025-06-02",45644.333333333336,"2025-06-02",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 116 à 121 + faisceau manage\r\nNe fonctionne plus en Phase 5\r\nTCR 507085",null,null,71746,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","72572","Erquelinnes - Montzen",">","FROIDMONT","BRESSOUX",2025,2025,23,23,"2025-06-02",45644.333333333336,"2025-06-02",45644.5,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,72572,"2023-11-03",0,"1,2,3,4,5"]
[null,"Infrabel","46309","Athus - Meuse",">","DINANT","YVOIR",2025,2025,23,28,"2025-06-02",45644.333333333336,"2025-07-07",45644.666666666664,"35d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Remise en peinture viaduc de Houx\r\nMise au gabarit pistes de circulation\r\nPhase 1\r\n+ Remplacement des pdb du viaduc de Houx\r\nCR 2024-195 en cours",null,null,46309,"2024-05-13",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","70547","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.ARENDSTRAAT",2025,2025,23,23,"2025-06-02",45644.979166666664,"2025-06-07",45644.1875,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud wissels Y Noord Berchem\r\nHKV",null,null,70547,"2024-01-29",0,"1,2,3,4,5"]
[null,"Infrabel","55799","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,23,24,"2025-06-02",45644.208333333336,"2025-06-13",45644.25,"11d, 01:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage 102500-98200\r\nDossier de concertation validé en octobre 2022\r\n+ Visite VB\r\nUPM:488485",null,null,55799,"2024-04-12",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","68335","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,23,23,"2025-06-02",45644.972222222219,"2025-06-07",45644.208333333336,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Démontage couverture.",null,null,68335,"2023-11-10",0,"1,2,3,4,5"]
[null,"Infrabel","71241","Namur - Antwerpen","< >","Y.NAZARETH","Y.OOST DRIEHOEK AARSCHOT",2025,2025,23,23,"2025-06-02",45644.972222222219,"2025-06-07",45644.1875,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKV",null,null,71241,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","55580","Lille - Charleroi","< >","HALLE","ENGHIEN",2025,2025,23,23,"2025-06-02",45644.965277777781,"2025-06-06",45644.194444444445,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Nuits de préparation - Construction d'un PI - PN16\r\nUPM 487948",null,null,55580,"2024-01-04",0,"1,2,3,4,5"]
[null,"Infrabel","55525","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,23,23,"2025-06-02",45644.965277777781,"2025-06-06",45644.204861111109,"4d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 2- 36.363 38.279\r\nPréparations\r\nTCR: 488138",null,null,55525,"2024-12-17",0,"1,2,3,4,5"]
[null,"Infrabel","71625","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,23,23,"2025-06-02",45644.965277777781,"2025-06-07",45644.225694444445,"5d, 06:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud Z02.23.03",null,null,71625,"2024-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","75404","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2025,2025,23,23,"2025-06-02",45644.291666666664,"2025-06-02",45644.625,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage 102500-98200\r\nExtension pour criblage zone début\r\nUPM:510626",null,null,75404,"2024-05-30",0,"1,2,3,4,5"]
[null,"Infrabel","69572","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,23,23,"2025-06-02",45644.291666666664,"2025-06-06",45644.541666666664,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!",null,null,69572,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","72571","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2025,2025,23,23,"2025-06-02",45644.5,"2025-06-02",45644.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,72571,"2023-11-03",0,"1,2,3,4,5"]
[null,"Infrabel","74599","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2025,2025,23,23,"2025-06-03",45644.333333333336,"2025-06-03",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno",null,null,74599,"2023-12-22",0,"1,2,3,4,5"]
[null,"Infrabel","67793","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,23,23,"2025-06-03",45644.020833333336,"2025-06-07",45644.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud  TCR 493230\r\nFLC SP III-IV inbegrepen",null,null,67793,"2024-08-13",0,"1,2,3,4,5"]
[null,"Infrabel","67903","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,23,23,"2025-06-03",45644.020833333336,"2025-06-07",45644.180555555555,"5d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67903,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","72725","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,23,23,"2025-06-03",45644.003472222219,"2025-06-07",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72725,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","72573","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,23,23,"2025-06-03",45644.395833333336,"2025-06-03",45644.611111111109,"1d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie et intervention avec S460 sur la voie contiguë + ATW",null,null,72573,"2023-11-03",0,"1,2,3,4,5"]
[null,"Infrabel","70491","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,23,23,"2025-06-04",45644.375,"2025-06-04",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y-Holland",null,null,70491,"2024-02-14",0,"1,2,3,4,5"]
[null,"Infrabel","70618","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2025,2025,23,23,"2025-06-05",45644.375,"2025-06-05",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen - Schijnpoort + inrit bundel Q",null,null,70618,"2024-03-13",0,"1,2,3,4,5"]
[null,"Infrabel","77698","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2025,2025,23,23,"2025-06-05",45644.388888888891,"2025-06-05",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,77698,"2024-03-26",0,"1,2,3,4,5"]
[null,"Infrabel","71077","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,23,23,"2025-06-06",45644.958333333336,"2025-06-07",45644.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nZ5.43",null,null,71077,"2024-01-25",0,"1,2,3,4,5"]
[null,"Infrabel","55582","Lille - Charleroi","< >","HALLE","ENGHIEN",2025,2025,23,24,"2025-06-06",45644.965277777781,"2025-06-10",45644.194444444445,"3d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Construction d'un PI - PN16\r\nUPM 487951",null,null,55582,"2024-01-04",1,"5,6"]
[null,"Infrabel","55529","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,23,24,"2025-06-06",45644.965277777781,"2025-06-10",45644.204861111109,"3d, 05:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 2- 36.363 38.279\r\n+ Maintenance Z3.51 P4\r\nTCR: 488139",null,null,55529,"2024-12-17",1,"5,6"]
[null,"Infrabel","56494","Athus - Meuse","< >","YVOIR","DINANT",2025,2025,23,24,"2025-06-06",45644.993055555555,"2025-06-09",45644.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Remplacement de rails dans le PN114 à Dinant\r\nUPM:491845",null,null,56494,"2024-12-09",1,"5,6"]
[null,"Infrabel","70631","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,23,23,"2025-06-06",45644.375,"2025-06-06",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y Holland + inrit bundel Q",null,null,70631,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","77699","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2025,2025,23,23,"2025-06-06",45644.388888888891,"2025-06-06",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,77699,"2024-03-26",0,"1,2,3,4,5"]
[null,"Infrabel","55168","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,23,24,"2025-06-07",45644.958333333336,"2025-06-09",45644.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022\r\nTCR: 493769",null,null,55168,"2024-07-19",0,"5,6"]
[null,"Infrabel","72343","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,23,24,"2025-06-07",45644.979166666664,"2025-06-09",45644.166666666664,"1d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing spoorstaven tussen Y Liersesteenweg en Y Krijgsbaan.",null,null,72343,"2024-03-12",1,"5,6"]
[null,"Infrabel","66368","Athus - Meuse",">","GEDINNE-MARCHANDISES","VONECHE",2025,2025,23,23,"2025-06-07",45644.25,"2025-06-08",45644.916666666664,"2d, 16:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux de maintenance.",null,null,66368,"2024-05-27",0,"5,6"]
[null,"Infrabel","69360","Namur - Antwerpen","< >","Y.HOLLAND","LUCHTBAL-ROOSTER S",2025,2025,23,23,"2025-06-07",45644.25,"2025-06-08",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Lantis Oosterweelverbinding RO",null,null,69360,"2023-09-06",1,"5,6"]
[null,"Infrabel","55215","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2025,2025,23,24,"2025-06-07",45644.25,"2025-06-09",45644.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Entretien mécanisé et manuel des AS du grill Nord de Visé-Bas\r\nEntretien mécanisé du PN 28\r\nUPM 488122",null,null,55215,"2024-12-09",1,"5,6"]
[null,"Infrabel","64519","Namur - Antwerpen","< >","Y.SCHIJN","Y.EKERSEDIJK",2025,2025,23,24,"2025-06-07",45644.25,"2025-06-09",45644.916666666664,"3d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"vernieuwen wissel 201B/202",null,null,64519,"2023-05-26",1,"1,2,3,4,5,6,7"]
[null,"Infrabel","53229","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,23,24,"2025-06-07",45644.25,"2025-06-10",45644.1875,"3d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - Phase 2025\r\nWE 3 (3jrs)\r\nTCR: 488974",null,null,53229,"2024-01-19",1,"5,6"]
[null,"Infrabel","57980","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,23,24,"2025-06-07",45644.25,"2025-06-10",45644.166666666664,"3d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing Ballast & Dwaarsliggers",null,null,57980,"2024-11-12",1,"5,6"]
[null,"Infrabel","72549","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,23,23,"2025-06-07",45644.3125,"2025-06-07",45644.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72549,"2023-11-03",0,"5,6"]
[null,"Infrabel","69564","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,23,24,"2025-06-07",45644.041666666664,"2025-06-10",45644.145833333336,"3d, 02:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!",null,null,69564,"2024-12-05",1,"5,6"]
[null,"Infrabel","70009","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2025,2025,23,23,"2025-06-08",45644.333333333336,"2025-06-08",45644.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144-130/1\r\nTCR 507100",null,null,70009,"2024-07-26",0,"5,6"]
[null,"Infrabel","71698","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2025,2025,23,23,"2025-06-08",45644.333333333336,"2025-06-08",45644.65625,"1d, 07:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nOttignies gare  voie 1 à 5 en alternance\r\nTCR 507144",null,null,71698,"2024-07-26",0,"5,6"]
[null,"Infrabel","72560","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,23,23,"2025-06-08",45644.3125,"2025-06-08",45644.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72560,"2023-11-03",0,"5,6"]
[null,"Infrabel","82233","Lille - Antwerpen","< >","GENT-DAMPOORT","BEERVELDE",2025,2025,23,23,"2025-06-08",45644.0625,"2025-06-08",45644.1875,"1d, 03:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-195\r\nIDS P023_RW_P008 - Gent st pieters-  RW Gent-Denderl_RW",null,null,82233,"2024-11-05",0,"5,6"]
[null,"Infrabel","82212","Lille - Antwerpen","< >","GENT-SINT-PIETERS","KORTRIJK",2025,2025,23,23,"2025-06-08",45644.0625,"2025-06-08",45644.1875,"1d, 03:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-194\r\nIDS P014b_RW_P008 - Gent st pieters-  RW L75 FGSP - Kortrijk\r\nR-521576",null,null,82212,"2024-11-05",0,"5,6"]
[null,"Infrabel","55171","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,24,24,"2025-06-09",45644.958333333336,"2025-06-14",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022\r\nTCR: 494074",null,null,55171,"2024-07-19",0,"1,2,3,4,5"]
[null,"Infrabel","68336","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,24,24,"2025-06-09",45644.972222222219,"2025-06-14",45644.208333333336,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Démontage structure.",null,null,68336,"2023-11-10",0,"1,2,3,4,5"]
[null,"Infrabel","65317","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,24,24,"2025-06-09",45644.9375,"2025-06-14",45644.229166666664,"5d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails , ballast",null,null,65317,"2024-01-22",0,"1,2,3,4,5"]
[null,"Infrabel","70757","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2025,2025,24,24,"2025-06-09",45644.020833333336,"2025-06-14",45644.1875,"6d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud lopend spoor en spoortoestellen\r\nHKM\r\nZ23.22.01",null,null,70757,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","70542","Namur - Antwerpen","< >","Y.NOORD GROENENHOEK","ANTWERPEN-BERCHEM",2025,2025,24,24,"2025-06-09",45644.375,"2025-06-13",45644.666666666664,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels en sporen bundel Groenenhoek",null,null,70542,"2024-02-01",0,"1,2,3,4,5"]
[null,"Infrabel","59220","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,24,24,"2025-06-10",45644.979166666664,"2025-06-14",45644.180555555555,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Stap 33: inkorten bovenleiding spoor III\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. West Driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters -Y. West Driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels\r\nSP B L 75 Gent Sin",null,null,59220,"2023-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","53227","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,24,24,"2025-06-10",45644.9375,"2025-06-14",45644.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement de Luttre - Phase 2025\r\nNuits de finition\r\nTCR: 488975",null,null,53227,"2024-02-29",0,"1,2,3,4,5"]
[null,"Infrabel","55583","Lille - Charleroi","< >","HALLE","ENGHIEN",2025,2025,24,24,"2025-06-10",45644.965277777781,"2025-06-14",45644.194444444445,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Nuits de finition - Construction d'un PI - PN16\r\nUPM 487952",null,null,55583,"2024-01-04",0,"1,2,3,4,5"]
[null,"Infrabel","55530","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,24,24,"2025-06-10",45644.965277777781,"2025-06-14",45644.204861111109,"4d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 2 - 36.363 38.279\r\nNuit pour soudures\r\nTCR: 488309",null,null,55530,"2024-12-17",0,"1,2,3,4,5"]
[null,"Infrabel","69573","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,24,24,"2025-06-10",45644.291666666664,"2025-06-13",45644.541666666664,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!",null,null,69573,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","65800","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2025,2025,24,24,"2025-06-10",45644.996527777781,"2025-06-14",45644.208333333336,"4d, 05:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.51 P3",null,null,65800,"2023-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","71212","Erquelinnes - Montzen",">","JAVA","ANDENNE",2025,2025,24,24,"2025-06-12",45644.5625,"2025-06-12",45644.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71212,"2024-01-26",0,"1,2,3,4,5"]
[null,"Infrabel","59625","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,24,25,"2025-06-13",45644.979166666664,"2025-06-16",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification OA\r\nSuppression des PN 56 et 58 - Poussage PI\r\nPS Maréchal Juin BK45.631 - Démolition\r\nChapes d'étanchéité\r\n+ Mise au gabarit des pistes Namur Rhisnes parois rocheuses.\r\n+ Travaux caténaires\r\n12 - Déroulage liaisons Namur- Gembloux\r\n+ Visi",null,null,59625,"2024-07-15",1,"5,6"]
[null,"Infrabel","77094","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.KRIJGSBAAN",2025,2025,24,25,"2025-06-14",45644.979166666664,"2025-06-16",45644.166666666664,"1d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Betonherstellingen aan de kruisingsbrug  L15 km 6.027 BX L15 en L27A\r\n\r\n\r\nalternatief voor geweigerde L15+L27A",null,null,77094,"2024-03-13",1,"5,6"]
[null,"Infrabel","65803","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2025,2025,24,24,"2025-06-14",45644.25,"2025-06-15",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.51 P4\r\nTCR: 488096",null,null,65803,"2024-01-05",1,"5,6"]
[null,"Infrabel","71215","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2025,2025,24,24,"2025-06-14",45644.354166666664,"2025-06-14",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71215,"2024-01-26",0,"5,6"]
[null,"Infrabel","73045","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2025,2025,24,24,"2025-06-15",45644.333333333336,"2025-06-15",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73045,"2024-05-28",0,"5,6"]
[null,"Infrabel","68128","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,25,25,"2025-06-16",45644.958333333336,"2025-06-21",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022\r\nTCR: 494092",null,null,68128,"2024-07-19",0,"1,2,3,4,5"]
[null,"Infrabel","68337","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,25,25,"2025-06-16",45644.972222222219,"2025-06-21",45644.208333333336,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Démontage fondations",null,null,68337,"2024-01-15",0,"1,2,3,4,5"]
[null,"Infrabel","57064","Lille - Charleroi","< >","HALLE","ATH",2025,2025,25,25,"2025-06-16",45644.944444444445,"2025-06-20",45644.180555555555,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Nuits de finition - Construction d'un PI - PN16\r\n+ Maintenance Z9.54+Z10.54 P3 HKV\r\n+ PLP\r\nUPM 487956",null,null,57064,"2024-01-04",0,"1,2,3,4,5"]
[null,"Infrabel","68713","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","STATTE",2025,2025,25,25,"2025-06-16",45644.993055555555,"2025-06-20",45644.194444444445,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons\r\nZ14.43\r\n+ voies 831, 832 et 833 de Flémalle-Haute",null,null,68713,"2024-01-22",0,"1,2,3,4,5"]
[null,"Infrabel","69712","Namur - Antwerpen","< >","MECHELEN-DIJKSTRAAT","KONTICH-LINT",2025,2025,25,25,"2025-06-16",45644.993055555555,"2025-06-21",45644.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK (samen met L27B): \r\n- min. 2 weken WN voor indienststelling (in maand ervoor)",null,null,69712,"2023-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","71884","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,25,25,"2025-06-16",45644.975694444445,"2025-06-21",45644.208333333336,"5d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71884,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","72912","Athus - Meuse",">","BERTRIX","STRAIMONT",2025,2025,25,25,"2025-06-18",45644.333333333336,"2025-06-18",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\n",null,null,72912,"2024-05-29",0,"1,2,3,4,5"]
[null,"Infrabel","73067","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,25,25,"2025-06-18",45644.333333333336,"2025-06-18",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73067,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","72911","Athus - Meuse",">","STRAIMONT","BERTRIX",2025,2025,25,25,"2025-06-19",45644.375,"2025-06-19",45644.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\n",null,null,72911,"2024-05-29",0,"1,2,3,4,5"]
[null,"Infrabel","56497","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,25,26,"2025-06-20",45644.25,"2025-06-28",45644.25,"8d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage 98200-95100\r\nDossier de concertation validé en octobre 2022\r\nUPM:488488",null,null,56497,"2024-01-09",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","66569","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2025,2025,25,26,"2025-06-21",45644.013888888891,"2025-06-23",45644.166666666664,"2d, 03:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen perron De Pinte - weekend 1/3 - TCR 492319\r\n+ Massificatie tss De Pinte en Gent\r\n+ Onderhoud Rooster De PInte\r\n+ Onderhoud rooster Gent \r\n* Gent Sint Pieters SP III-IV-V inbegrepen\r\nCf Escalade Head Of nov/dec 2023",null,null,66569,"2024-08-20",1,"5,6"]
[null,"Infrabel","53516","Lille - Charleroi","< >","MANAGE","LUTTRE",2025,2025,25,25,"2025-06-21",45644.25,"2025-06-22",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z8.52 P4\r\nLuttre prolongation Z8.52 : MHS jusqu'à K-E.20 KX-E.20\r\nTranservale Nord Luttre non accessible  - Transervale Roux accessible\r\nVoies I-II Luttre libres \r\nVoies 3-4-5 en CDS\r\nTCR: 488790",null,null,53516,"2024-03-13",1,"5,6"]
[null,"Infrabel","67467","Lille - Charleroi","< >","GHLIN","MONS",2025,2025,25,25,"2025-06-21",45644.993055555555,"2025-06-22",45644.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53 + Z.11.53\r\nTCR 489845",null,null,67467,"2024-12-17",0,"5,6"]
[null,"Infrabel","70072","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","FLEMALLE-HAUTE",2025,2025,26,26,"2025-06-23",45644.958333333336,"2025-06-27",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Z.19.41 - Maintenance P3\r\n+ Entretien et interventions diverses sur caténaire",null,null,70072,"2024-01-22",0,"1,2,3,4,5"]
[null,"Infrabel","77626","Athus - Meuse","< >","AUBANGE-FRONTIERE-FRANCE","Y.AUBANGE",2025,2025,26,26,"2025-06-23",45644.333333333336,"2025-06-23",45644.541666666664,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite voie unique L 165/2 \r\nVisite voie unique L 165/3\r\nVisite voie unique L 165/1",null,null,77626,"2024-04-04",0,"1,2,3,4,5"]
[null,"Infrabel","55531","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,26,26,"2025-06-23",45644.965277777781,"2025-06-28",45644.204861111109,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – Phase 2 - 36.363 38.279\r\nfinitions\r\nTCR: 488311",null,null,55531,"2024-12-17",0,"1,2,3,4,5"]
[null,"Infrabel","56539","Athus - Meuse",">","PALISEUL","BERTRIX",2025,2025,26,26,"2025-06-23",45644.1875,"2025-06-23",45644.6875,"1d, 12:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 2 - WE 1\r\nDossier de concertation octobre 2022 - CR 2025-037\r\nUPM:491507",null,null,56539,"2024-07-30",0,"1,2,3,4,5"]
[null,"Infrabel","73126","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2025,2025,26,26,"2025-06-23",45644.385416666664,"2025-06-23",45644.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,73126,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","71886","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,26,26,"2025-06-23",45644.975694444445,"2025-06-28",45644.208333333336,"5d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71886,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","72040","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2025,2025,26,26,"2025-06-24",45644.003472222219,"2025-06-28",45644.184027777781,"5d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 505626: Maintenance Z07.31 HKM\r\nL75 FGSP-FD \r\nFGSP SP VIII-IX + Bundel CD  bereikbaar\r\nFD blijft vrij\r\nL86 FPT-FDN\r\nFDN SP III-IV in",null,null,72040,"2024-08-20",0,"1,2,3,4,5"]
[null,"Infrabel","68060","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2025,2025,26,26,"2025-06-25",45644.333333333336,"2025-06-25",45644.4375,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11",null,null,68060,"2024-02-26",0,"1,2,3,4,5"]
[null,"Infrabel","74224","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,26,26,"2025-06-25",45644.354166666664,"2025-06-26",45644.645833333336,"2d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud + schouwen TCR 499751\r\n\r\nSP B BD + perronspoor II\r\n\r\nPerronspoor III tot VII + bundel M ontoegankelijk",null,null,74224,"2024-08-20",0,"1,2,3,4,5"]
[null,"Infrabel","74030","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.WEST BERCHEM",2025,2025,26,26,"2025-06-25",45644.416666666664,"2025-06-27",45644.583333333336,"3d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Opleiding opgeleide bediende.",null,null,74030,"2024-01-26",0,"1,2,3,4,5"]
[null,"Infrabel","71678","Namur - Antwerpen",">","MECHELEN","MECHELEN",2025,2025,26,26,"2025-06-27",45644.979166666664,"2025-06-28",45644.3125,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Om te bovenleiding te verwijderen op L25 voor start renovatie vaartbrug tijdens weekend coupure 59456 heeft men voor een periode van 8 uren het nevenliggend spoor B op L27 ook BD nodig.",null,null,71678,"2023-11-28",0,"5,6"]
[null,"Infrabel","55170","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,26,26,"2025-06-28",45644.958333333336,"2025-06-29",45644.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022\r\nTCR: 494345",null,null,55170,"2024-07-19",0,"5,6"]
[null,"Infrabel","69567","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,26,27,"2025-06-28",45644.041666666664,"2025-06-30",45644.125,"2d, 02:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen Y-Ekerse Dijk en overweg 430\r\nL27A+L27C\r\ngeval BVL inclusief Y Leopold!\r\n\r\n",null,null,69567,"2024-12-05",1,"5,6"]
[null,"Infrabel","80269","Athus - Meuse",">","HAVERSIN","MARLOIE",2025,2025,26,26,"2025-06-29",45644.364583333336,"2025-06-29",45644.666666666664,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-085 \r\nVisite périodique de jour le dimanche pour AI45. (suite mise en service ETCS)\r\nVA: Le dimanche entre 08h45 et 16h00\r\nVB: Le dimanche entre 08h00 et 15h15\r\nA dupliquer toutes les 8 semaines.\r\nTCR 510716",null,null,80269,"2024-08-05",0,"5,6"]
[null,"Infrabel","68339","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,27,27,"2025-06-30",45644.979166666664,"2025-07-05",45644.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Nouvelles fondations - coffrage ferraillage + Egouttage / Gaine",null,null,68339,"2023-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","72959","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","BAKENBOS",2025,2025,27,27,"2025-06-30",45644.986111111109,"2025-07-05",45644.201388888891,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_05 Area CE volgens onderhoudskalender 2025.\r\nBuitendienststelling L161 tussen Bru Luxemburg en Bakenbos voor onderhoudswerken + L161A.",null,null,72959,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","69706","Namur - Antwerpen","< >","MECHELEN-DIJKSTRAAT","KONTICH-LINT",2025,2025,27,27,"2025-06-30",45644.993055555555,"2025-07-05",45644.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK (samen met L27B): \r\n- min. 1 week WN na indienststelling",null,null,69706,"2024-07-10",0,"1,2,3,4,5"]
[null,"Infrabel","71901","Namur - Antwerpen","< >","MECHELEN","Y.SINT-KATELIJNE-WAVER",2025,2025,27,27,"2025-06-30",45644.993055555555,"2025-07-05",45644.201388888891,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKV",null,null,71901,"2024-07-10",0,"1,2,3,4,5"]
[null,"Infrabel","73112","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,27,27,"2025-07-01",45644.333333333336,"2025-07-01",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73112,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","67907","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,27,27,"2025-07-01",45644.020833333336,"2025-07-05",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67907,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","70492","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,27,27,"2025-07-02",45644.375,"2025-07-02",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y-Holland",null,null,70492,"2024-02-14",0,"1,2,3,4,5"]
[null,"Infrabel","77269","Athus - Meuse",">","VONECHE","BEAURAING",2025,2025,27,27,"2025-07-03",45644.333333333336,"2025-07-03",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,77269,"2024-05-27",0,"1,2,3,4,5"]
[null,"Infrabel","71078","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,27,27,"2025-07-04",45644.958333333336,"2025-07-05",45644.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nZ5.43",null,null,71078,"2024-01-25",0,"1,2,3,4,5"]
[null,"Infrabel","72785","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2025,2025,27,27,"2025-07-04",45644.368055555555,"2025-07-04",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72785,"2023-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","55173","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,27,28,"2025-07-05",45644.958333333336,"2025-07-07",45644.208333333336,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3\r\nDossier de concertation validé en octobre 2022\r\nTCR: 494348",null,null,55173,"2024-07-19",0,"5,6"]
[null,"Infrabel","68126","Namur - Antwerpen",">","FLAWINNE","AUVELAIS",2025,2025,27,27,"2025-07-05",45644.333333333336,"2025-07-05",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130\r\nUPM: 489015",null,null,68126,"2024-01-12",0,"5,6"]
[null,"Infrabel","68703","Erquelinnes - Montzen","< >","Y.VAL-BENOIT","Y.RENORY",2025,2025,27,27,"2025-07-05",45644.979166666664,"2025-07-06",45644.208333333336,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons",null,null,68703,"2023-11-03",0,"5,6"]
[null,"Infrabel","56535","Athus - Meuse","< >","BEAURAING","BERTRIX",2025,2025,27,28,"2025-07-05",45644.25,"2025-07-07",45644.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 2 - WE 3\r\nDossier de concertation octobre 2022 - CR 2025-037\r\nUPM:491265",null,null,56535,"2024-07-30",1,"5,6"]
[null,"Infrabel","67469","Lille - Charleroi","< >","GHLIN","MONS",2025,2025,27,27,"2025-07-05",45644.993055555555,"2025-07-06",45644.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim",null,null,67469,"2024-05-30",0,"5,6"]
[null,"Infrabel","68801","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,27,27,"2025-07-05",45644.340277777781,"2025-07-05",45644.659722222219,"1d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie A Ottignies - Gembloux (extension Rhisnes SAS)\r\nUPM: 488037",null,null,68801,"2024-01-05",0,"5,6"]
[null,"Infrabel","65695","Lille - Charleroi","< >","HALLE","QUEVY-FRONTIERE",2025,2025,27,27,"2025-07-06",45644.020833333336,"2025-07-06",45644.1875,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Mise hors service de l’ensemble de la zone EBP FMS pendant un minimum de 2h30 (4h est parfait pour avoir un peu de marge) à définir entre 22h et 6h (selon les disponibilités de la zone) Christine Deschrijver; Christine Payen",null,null,65695,"2023-11-08",0,"5,6"]
[null,"Infrabel","72788","Athus - Meuse",">","MARBEHAN","HABAY",2025,2025,27,27,"2025-07-06",45644.375,"2025-07-06",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,72788,"2023-11-08",0,"5,6"]
[null,"Infrabel","75042","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2025,2025,28,28,"2025-07-07",45644.958333333336,"2025-07-11",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux d'entretien en P3 HKV \r\nCTL de nuit allongé de 06h00",null,null,75042,"2024-04-12",0,"1,2,3,4,5"]
[null,"Infrabel","59226","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,28,28,"2025-07-07",45644.979166666664,"2025-07-12",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels\r\nSP A L58/1 Y West Driehoek ",null,null,59226,"2023-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","56499","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,28,28,"2025-07-07",45644.916666666664,"2025-07-11",45644.583333333336,"5d, 16:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage: bourrage et finitions\r\nDossier de concertation validé en octobre 2022\r\nUPM:488500",null,null,56499,"2024-04-12",0,"1,2,3,4,5"]
[null,"Infrabel","76239","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,28,28,"2025-07-07",45644.291666666664,"2025-07-11",45644.541666666664,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-059\r\nVernieuwingswerken BVL t.h.v. Y.Ekerse Dijk\r\nBuitenspanning tem Bundel Rhodesië (gevolggeval)",null,null,76239,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","66525","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2025,2025,28,28,"2025-07-07",45644.930555555555,"2025-07-12",45644.180555555555,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.54",null,null,66525,"2024-05-31",0,"1,2,3,4,5"]
[null,"Infrabel","68716","Erquelinnes - Montzen","< >","AMAY","JAVA",2025,2025,28,28,"2025-07-08",45644.993055555555,"2025-07-12",45644.194444444445,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons",null,null,68716,"2024-01-22",0,"1,2,3,4,5"]
[null,"Infrabel","77167","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2025,2025,28,28,"2025-07-10",45644.388888888891,"2025-07-10",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,77167,"2024-03-14",0,"1,2,3,4,5"]
[null,"Infrabel","73367","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,28,28,"2025-07-11",45644.375,"2025-07-11",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73367,"2023-12-15",0,"1,2,3,4,5"]
[null,"Infrabel","56536","Athus - Meuse","< >","BEAURAING","BERTRIX",2025,2025,28,29,"2025-07-12",45644.25,"2025-07-14",45644.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 2 - WE 4\r\nDossier de concertation octobre 2022 - CR 2025-037\r\nUPM:491250",null,null,56536,"2024-07-30",1,"5,6"]
[null,"Infrabel","76241","Namur - Antwerpen","< >","ANTWERPEN-NOORD-INRIT C1","Y.NOORDERLAAN",2025,2025,28,29,"2025-07-12",45644.041666666664,"2025-07-14",45644.125,"2d, 02:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-059\r\nVernieuwingswerken BVL t.h.v. Y.Ekerse Dijk\r\nBuitenspanning tot  Bundel Rhodesië (gevolggevallen)",null,null,76241,"2024-12-06",1,"5,6"]
[null,"Infrabel","67320","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ANTWERPEN-D.S.-RHODESIE",2025,2025,28,28,"2025-07-13",45644.25,"2025-07-13",45644.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,67320,"2024-03-28",1,"5,6"]
[null,"Infrabel","70903","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2025,2025,29,29,"2025-07-14",45644.958333333336,"2025-07-19",45644.194444444445,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z73.33.02\r\nL53 FCB-FDR\r\nFDR SP I tem III inbegrepen (Spoor IV toebedeeld aan MP FDD vanaf 00u45 colt 65576 - 495434)\r\nY FCB vrij",null,null,70903,"2024-06-12",0,"1,2,3,4,5"]
[null,"Infrabel","46303","Athus - Meuse",">","DINANT","YVOIR",2025,2025,29,33,"2025-07-14",45644.333333333336,"2025-08-14",45644.666666666664,"31d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Remise en peinture viaduc de Houx\r\nMise au gabarit pistes de circulation \r\nPhase 2\r\n+ Remplacement des pdb du viaduc de Houx\r\n+Visite VB,\r\n\r\nCR2025-054",null,null,46303,"2024-06-26",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","55538","Lille - Charleroi","< >","JURBISE","ATH",2025,2025,29,29,"2025-07-14",45644.9375,"2025-07-19",45644.222222222219,"5d, 06:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.54/Z7.53 P3 HKV\r\nUPM 488177",null,null,55538,"2024-06-12",0,"1,2,3,4,5"]
[null,"Infrabel","75388","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,29,29,"2025-07-14",45644.395833333336,"2025-07-14",45644.645833333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"DOES Schouwen sporen overdag. TCR 510885",null,null,75388,"2024-08-20",0,"1,2,3,4,5"]
[null,"Infrabel","56056","Athus - Meuse",">","PALISEUL","BERTRIX",2025,2025,29,31,"2025-07-15",45644.958333333336,"2025-07-28",45644.229166666664,"13d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - Phase 2 - Finitions\r\nDossier de concertation octobre 2022 - CR 2025-037\r\nUPM:491234",null,null,56056,"2024-07-30",0,"1,2,3,4,5"]
[null,"Infrabel","77261","Athus - Meuse",">","BEAURAING","HOUYET",2025,2025,29,29,"2025-07-16",45644.388888888891,"2025-07-16",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,77261,"2024-03-28",0,"1,2,3,4,5"]
[null,"Infrabel","71195","Erquelinnes - Montzen",">","JAVA","ANDENNE",2025,2025,29,29,"2025-07-17",45644.5625,"2025-07-17",45644.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71195,"2023-10-26",0,"1,2,3,4,5"]
[null,"Infrabel","76423","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2025,2025,29,29,"2025-07-18",45644.326388888891,"2025-07-18",45644.645833333336,"1d, 07:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visites J10",null,null,76423,"2024-02-27",0,"1,2,3,4,5"]
[null,"Infrabel","71197","Erquelinnes - Montzen",">","SCLAIGNEAUX","BEEZ",2025,2025,29,29,"2025-07-19",45644.354166666664,"2025-07-19",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71197,"2023-10-26",0,"5,6"]
[null,"Infrabel","70010","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE","GEMBLOUX",2025,2025,29,29,"2025-07-20",45644.333333333336,"2025-07-20",45644.666666666664,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visite de voie L144-130/1\r\nTCR 507101",null,null,70010,"2024-07-26",0,"5,6"]
[null,"Infrabel","76006","Lille - Charleroi",">","Y.SOIGNIES","SOIGNIES",2025,2025,29,29,"2025-07-20",45644.520833333336,"2025-07-20",45644.645833333336,"1d, 03:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique VA/B\r\n",null,null,76006,"2024-05-30",0,"5,6"]
[null,"Infrabel","74339","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,30,30,"2025-07-22",45644.965277777781,"2025-07-25",45644.243055555555,"3d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Pose poteaux caténaire sur L144. (entre L130 et PN10)",null,null,74339,"2023-12-15",0,"1,2,3,4,5"]
[null,"Infrabel","67910","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,30,30,"2025-07-23",45644.020833333336,"2025-07-26",45644.180555555555,"4d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67910,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","73029","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2025,2025,30,30,"2025-07-24",45644.333333333336,"2025-07-24",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73029,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","65776","Lille - Charleroi","< >","LEMBEEK","BRAINE-LE-COMTE",2025,2025,30,31,"2025-07-26",45644.03125,"2025-07-28",45644.1875,"2d, 03:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.53 en P4\r\nVisite Diagno Zone 1 Lembeek-Braine-Le-Comte\r\nTCR 489208",null,null,65776,"2024-09-10",1,"5,6"]
[null,"Infrabel","73047","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2025,2025,30,30,"2025-07-27",45644.333333333336,"2025-07-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73047,"2024-05-28",0,"5,6"]
[null,"Infrabel","74596","Lille - Charleroi",">","ATH","BRUGELETTE",2025,2025,31,31,"2025-07-28",45644.333333333336,"2025-07-28",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno",null,null,74596,"2023-12-22",0,"1,2,3,4,5"]
[null,"Infrabel","68340","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,31,31,"2025-07-28",45644.965277777781,"2025-08-02",45644.229166666664,"5d, 06:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Nouvelles fondations - béton quai voie I",null,null,68340,"2023-11-10",0,"1,2,3,4,5"]
[null,"Infrabel","59693","Lille - Charleroi","< >","Y.RUISBROEK","Y.NOORD HALLE",2025,2025,31,31,"2025-07-29",45644.03125,"2025-08-01",45644.197916666664,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen BVL L96+L96E zone A4-B4-A5-B5: voorbereiding",null,null,59693,"2024-03-05",0,"1,2,3,4,5"]
[null,"Infrabel","72933","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,31,31,"2025-07-30",45644.378472222219,"2025-07-30",45644.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,72933,"2023-12-15",0,"1,2,3,4,5"]
[null,"Infrabel","71120","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,31,31,"2025-07-31",45644.9375,"2025-08-01",45644.225694444445,"1d, 06:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 4\r\nZ4.43\r\nPériodicité toutes les 4 semaines en alternance avec la zone 9\r\nzone 4 : 3 fois sur l'année\r\nzone 9 : 9 fois sur l'année",null,null,71120,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","70559","Namur - Antwerpen","< >","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL",2025,2025,31,31,"2025-07-31",45644.986111111109,"2025-08-01",45644.236111111109,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen Centraal -1",null,null,70559,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","71079","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,31,31,"2025-08-01",45644.958333333336,"2025-08-02",45644.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\nZ5.43",null,null,71079,"2024-01-25",0,"1,2,3,4,5"]
[null,"Infrabel","67283","Athus - Meuse","< >","GEDINNE","BERTRIX",2025,2025,31,31,"2025-08-02",45644.958333333336,"2025-08-03",45644.625,"1d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\nUPM:490200",null,null,67283,"2024-01-22",1,"5,6"]
[null,"Infrabel","59692","Lille - Charleroi","< >","Y.RUISBROEK","Y.NOORD HALLE",2025,2025,31,32,"2025-08-02",45644.03125,"2025-08-04",45644.1875,"2d, 03:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen BVL L96+L96E zone A4-B4-A5-B5",null,null,59692,"2023-12-29",1,"5,6"]
[null,"Infrabel","53525","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2025,2025,31,31,"2025-08-02",45644.25,"2025-08-03",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15. 51 P4+\r\nTCR: 492010\r\nCR_SNCB_2025_08_SO_365_validé le 04/12/2024",null,null,53525,"2024-12-04",1,"5,6"]
[null,"Infrabel","72398","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","Y.NORD",2025,2025,31,32,"2025-08-03",45644.9375,"2025-08-04",45644.229166666664,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Centrale\r\nLivraison LRS par le biais du train T-Portique\r\nCoupure type selon le plan \"SIRU Aménagement Charleroi 2025_ Zone déchargement LRS n°2 (T-Portique)\"",null,null,72398,"2023-11-27",0,"5,6"]
[null,"Infrabel","56336","Erquelinnes - Montzen",">","HOURPES","ERQUELINNES-VILLAGE",2025,2025,32,32,"2025-08-04",45644.958333333336,"2025-08-09",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement AS Lobbes-Garage : préparation caténaire\r\nTCR 487645",null,null,56336,"2024-01-03",0,"1,2,3,4,5"]
[null,"Infrabel","69769","Namur - Antwerpen",">","VILVOORDE","VILVOORDE",2025,2025,32,32,"2025-08-04",45644.979166666664,"2025-08-09",45644.25,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"sporen 4+5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde",null,null,69769,"2023-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","67068","Athus - Meuse","< >","HATRIVAL","LIBRAMONT",2025,2025,32,34,"2025-08-04",45644.979166666664,"2025-08-18",45644.201388888891,"14d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification nouvelle liaison L162/1\r\n\r\nPour Libramont sur L162: Prendre mise HS jusqu'au signaux L1-G.74 et LX2-G.74.\r\nPour Libramont sur L165: Prendre mise HS jusqu'au signaux L4-G.74 et L3-G.74.",null,null,67068,"2024-07-31",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","71243","Namur - Antwerpen","< >","Y.NAZARETH","Y.OOST DRIEHOEK AARSCHOT",2025,2025,32,32,"2025-08-04",45644.996527777781,"2025-08-08",45644.1875,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKM\r\nZBB.23.02",null,null,71243,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","77478","Athus - Meuse",">","PALISEUL","GEDINNE",2025,2025,32,32,"2025-08-05",45644.333333333336,"2025-08-05",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,77478,"2024-05-27",0,"1,2,3,4,5"]
[null,"Infrabel","76474","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,32,32,"2025-08-06",45644.333333333336,"2025-08-06",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite Diagno J27",null,null,76474,"2024-02-27",0,"1,2,3,4,5"]
[null,"Infrabel","76794","Namur - Antwerpen",">","VILVOORDE","Y.WEERDE",2025,2025,32,36,"2025-08-08",45644.958333333336,"2025-09-01",45644.208333333336,"24d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-061\r\nVernieuwen spoorstaven en dwarsliggers perronspoor II",null,null,76794,"2024-12-09",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","77285","Athus - Meuse",">","GEDINNE","VONECHE",2025,2025,32,32,"2025-08-09",45644.333333333336,"2025-08-09",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,77285,"2024-05-27",0,"1,2,3,4,5"]
[null,"Infrabel","53489","Lille - Charleroi","< >","Y.JURBISE","MONS",2025,2025,32,32,"2025-08-09",45644.25,"2025-08-10",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.5.53 P4+\r\nTCR 489729",null,null,53489,"2024-09-10",1,"5,6"]
[null,"Infrabel","82467","Athus - Meuse","< >","GEDINNE","BERTRIX",2025,2025,32,33,"2025-08-10",45644.958333333336,"2025-08-11",45644.1875,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\nUPM:490198",null,null,82467,"2024-10-07",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","75349","Lille - Antwerpen","< >","Y.MELSELE","OOSTAKKER",2025,2025,32,32,"2025-08-10",45644.020833333336,"2025-08-10",45644.21875,"1d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud - TCR 500388",null,null,75349,"2024-08-21",0,"5,6"]
[null,"Infrabel","68308","Erquelinnes - Montzen",">","HOURPES","ERQUELINNES-VILLAGE",2025,2025,33,33,"2025-08-11",45644.958333333336,"2025-08-16",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement AS Lobbes-Garage : préparation caténaire\r\nTCR 487652",null,null,68308,"2024-01-03",0,"1,2,3,4,5"]
[null,"Infrabel","65795","Lille - Charleroi","< >","Y.NORD","Y.LA SAMBRE",2025,2025,33,33,"2025-08-11",45644.979166666664,"2025-08-14",45644.1875,"3d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z7.51 P3",null,null,65795,"2023-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","53509","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2025,2025,33,33,"2025-08-11",45644.965277777781,"2025-08-14",45644.229166666664,"3d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z9.52 + Maintenance Z.3.53 en P3 HKV\r\nTCR 490498",null,null,53509,"2024-05-07",0,"1,2,3,4,5"]
[null,"Infrabel","59473","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,33,33,"2025-08-11",45644.375,"2025-08-12",45644.625,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nTransfert L130/1 du cas 26690\r\nUPM: 488740",null,null,59473,"2024-01-10",0,"1,2,3,4,5"]
[null,"Infrabel","73088","Athus - Meuse",">","SIGNEULX","HALANZY",2025,2025,33,33,"2025-08-12",45644.333333333336,"2025-08-12",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73088,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","67913","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,33,33,"2025-08-12",45644.020833333336,"2025-08-15",45644.180555555555,"4d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67913,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","73089","Athus - Meuse",">","HALANZY","SIGNEULX",2025,2025,33,33,"2025-08-13",45644.333333333336,"2025-08-13",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie  B",null,null,73089,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","67784","Athus - Meuse","< >","HATRIVAL","MARBEHAN",2025,2025,33,34,"2025-08-13",45644.979166666664,"2025-08-18",45644.201388888891,"4d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renforcement mur de soutènement VB 166.693 + renouvellement P.I. 166.698\r\n+ Réalisation de lame d'air et déplacement séparation de phase Rocogne L165(1) - L162 avec Cas caténaire: 26814, 815, 818, 820, 821, 822, 824,828, 830, 832,444, 445\r\n+ Pose supers",null,null,67784,"2024-07-31",1,"1,2,3,4,5,6,7"]
[null,"Infrabel","67776","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,33,33,"2025-08-14",45644.375,"2025-08-14",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nTransfert L130/1 du cas 26690\r\nUPM: 488741",null,null,67776,"2024-01-10",0,"1,2,3,4,5"]
[null,"Infrabel","73115","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,33,33,"2025-08-15",45644.333333333336,"2025-08-15",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73115,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","71181","Erquelinnes - Montzen",">","AMAY","ENGIS",2025,2025,33,33,"2025-08-16",45644.333333333336,"2025-08-16",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71181,"2024-02-29",0,"5,6"]
[null,"Infrabel","68162","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,33,34,"2025-08-16",45644.986111111109,"2025-08-18",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nUPM: 489239",null,null,68162,"2024-01-15",0,"5,6"]
[null,"Infrabel","71183","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2025,2025,33,33,"2025-08-17",45644.354166666664,"2025-08-17",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,71183,"2023-10-26",0,"5,6"]
[null,"Infrabel","59227","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,34,34,"2025-08-18",45644.979166666664,"2025-08-23",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels\r\nSP A L58/1 Y West Driehoek ",null,null,59227,"2023-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","72972","Lille - Charleroi","< >","HALLE","Y.NOORD HALLE",2025,2025,34,34,"2025-08-18",45644.993055555555,"2025-08-23",45644.1875,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone FH_08 volgens onderhoudskalender Area CE\r\n\r\nsp A L94 met ATW/TX",null,null,72972,"2024-03-06",0,"1,2,3,4,5"]
[null,"Infrabel","71666","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2025,2025,34,34,"2025-08-18",45644.947916666664,"2025-08-23",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 500423: Onderhoud zone 05.32\r\nL58 Eeklo inbegrepen tot Gent Dampoort NIET inbegrepen",null,null,71666,"2024-08-22",0,"1,2,3,4,5"]
[null,"Infrabel","77169","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2025,2025,34,34,"2025-08-18",45644.34375,"2025-08-18",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,77169,"2024-03-14",0,"1,2,3,4,5"]
[null,"Infrabel","67745","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2025,2025,34,34,"2025-08-19",45644.010416666664,"2025-08-23",45644.177083333336,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 499879: Onderhoudswerken en kleine vernieuwingswerken\r\nDeinze SP I-II inbegrepen\r\nY Zandberg niet inbegrepen\r\n\r\nGevallen; \r\n29289-29288-29290-29291-29293-29292-29295-29294-29296-29297-29298",null,null,67745,"2024-08-22",0,"1,2,3,4,5"]
[null,"Infrabel","76410","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2025,2025,34,34,"2025-08-20",45644.333333333336,"2025-08-20",45644.4375,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11",null,null,76410,"2024-02-26",0,"1,2,3,4,5"]
[null,"Infrabel","73370","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,34,34,"2025-08-21",45644.375,"2025-08-21",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73370,"2023-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","73371","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,34,34,"2025-08-22",45644.375,"2025-08-22",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73371,"2023-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","68163","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,34,35,"2025-08-23",45644.986111111109,"2025-08-25",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nUPM: 489241",null,null,68163,"2024-01-15",0,"5,6"]
[null,"Infrabel","66196","Lille - Charleroi",">","LUTTRE","ROUX",2025,2025,34,34,"2025-08-23",45644.25,"2025-08-24",45644.708333333336,"1d, 11:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance Z05.52 P4\r\nTCR 487866",null,null,66196,"2024-01-14",0,"5,6"]
[null,"Infrabel","68804","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,34,34,"2025-08-23",45644.340277777781,"2025-08-23",45644.659722222219,"1d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie A Ottignies - Gembloux (extension Rhisnes SAS)\r\nUPM: 488038",null,null,68804,"2024-01-05",0,"5,6"]
[null,"Infrabel","68180","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2025,2025,34,34,"2025-08-24",45644.333333333336,"2025-08-24",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Sint-Joris-Weert - Wavre VA/VB\r\nUPM: 488519",null,null,68180,"2024-01-09",0,"5,6"]
[null,"Infrabel","64924","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","ESSEN-GRENS",2025,2025,34,34,"2025-08-24",45644.003472222219,"2025-08-24",45644.166666666664,"1d, 03:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Buitendienststellen van de van de volledige overeenkomstige EBP-zone gedurende minimaal 2,5 uur te bepalen tussen 22.00 uur en 06.00 uur\r\nUpdate EBP release to last version\r\nR-447107",null,null,64924,"2023-11-28",0,"5,6"]
[null,"Infrabel","71748","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2025,2025,35,35,"2025-08-25",45644.333333333336,"2025-08-25",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 116 à 121 + faisceau manage\r\nNe fonctionne plus en Phase 5\r\nTCR 507090",null,null,71748,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","73382","Athus - Meuse",">","YVOIR","DINANT",2025,2025,35,35,"2025-08-25",45644.385416666664,"2025-08-25",45644.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73382,"2024-04-04",0,"1,2,3,4,5"]
[null,"Infrabel","73398","Athus - Meuse",">","Y.NEFFE","DINANT",2025,2025,35,35,"2025-08-27",45644.333333333336,"2025-08-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,73398,"2023-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","71219","Erquelinnes - Montzen",">","JAVA","STATTE",2025,2025,35,35,"2025-08-27",45644.354166666664,"2025-08-27",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71219,"2023-10-26",0,"1,2,3,4,5"]
[null,"Infrabel","71221","Erquelinnes - Montzen",">","JAVA","ANDENNE",2025,2025,35,35,"2025-08-28",45644.5625,"2025-08-28",45644.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71221,"2023-10-26",0,"1,2,3,4,5"]
[null,"Infrabel","77702","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2025,2025,35,35,"2025-08-28",45644.388888888891,"2025-08-28",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,77702,"2024-03-26",0,"1,2,3,4,5"]
[null,"Infrabel","70634","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,35,35,"2025-08-29",45644.375,"2025-08-29",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y Holland + inrit bundel Q",null,null,70634,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","65685","Lille - Antwerpen","< >","KORTRIJK","WAREGEM",2025,2025,35,36,"2025-08-30",45644.25,"2025-09-01",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"TCR 492558: Vervangen metalen spoordekken door betonnen bakbruggen (Marijn Libbrecht)\r\n+\r\nVernieuwen tunnel Hulstweg (kp 50.010) (Ilse Vancoilli)\r\n+\r\nOverweg 82 Harmelen toevoegen (LA David Van Hoey)",null,null,65685,"2024-08-23",1,"5,6"]
[null,"Infrabel","69118","Namur - Antwerpen","< >","ANTWERPEN-OOST","Y.HOLLAND",2025,2025,35,36,"2025-08-30",45644.041666666664,"2025-09-01",45644.15625,"2d, 02:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels en sporen te Anwerpen Schijnpoort inrit bundel E.  \r\nPeriodiciteit: 1 keer / jaar, \r\nTLO van 48u; \r\n\r\nmet inbegrip van bundelkop van bundel C (G-N.12 - F-N.12) en bundel E (H-H.12 - E-N.12) \r\n+ L27A sp A zo 0:00u tot ma 5:00u, L27A Sp ",null,null,69118,"2023-08-31",1,"5,6"]
[null,"Infrabel","71115","Namur - Antwerpen","< >","NAMUR","RONET",2025,2025,35,35,"2025-08-31",45644.003472222219,"2025-08-31",45644.21875,"1d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur ZONE 6\r\nZ6.43\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,71115,"2024-01-25",0,"5,6"]
[null,"Infrabel","55532","Namur - Antwerpen","< >","OTTIGNIES","LODELINSART",2025,2025,36,36,"2025-09-01",45644.958333333336,"2025-09-06",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Pi métalliques 52.015 et 52.215\r\nPréparations\r\nTCR: 488317",null,null,55532,"2024-04-26",0,"1,2,3,4,5"]
[null,"Infrabel","68930","Namur - Antwerpen","< >","MECHELEN","LEUVEN",2025,2025,36,36,"2025-09-01",45644.979166666664,"2025-09-05",45644.208333333336,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L53",null,null,68930,"2023-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","70550","Namur - Antwerpen",">","Y.BERCHEM-STADION","ANTWERPEN-CENTRAAL",2025,2025,36,36,"2025-09-01",45644.979166666664,"2025-09-06",45644.1875,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud wissels Y Noord Berchem\r\nHKV",null,null,70550,"2024-01-29",0,"1,2,3,4,5"]
[null,"Infrabel","69143","Lille - Charleroi","< >","Y.NOORD HALLE","SAINTES",2025,2025,36,36,"2025-09-01",45644.986111111109,"2025-09-05",45644.180555555555,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone FH_10 Area CE volgens onderhoudskalender 2025\r\nOnderhoudswerken L94 tussen perrons Halle en Grens Vlaanderen-Wallonië.\r\n\r\nSp 3 in Halle vanaf 00u20.\r\nReisweg van L96 -> L26 moet steeds open blijven.",null,null,69143,"2024-03-06",0,"1,2,3,4,5"]
[null,"Infrabel","66522","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2025,2025,36,36,"2025-09-01",45644.944444444445,"2025-09-06",45644.173611111109,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.54\r\n+ Maintenance Z7.54 P3HKM",null,null,66522,"2024-05-31",0,"1,2,3,4,5"]
[null,"Infrabel","72191","Namur - Antwerpen","< >","MECHELEN","Y.LEUVEN-BUNDEL M",2025,2025,36,36,"2025-09-01",45644.975694444445,"2025-09-05",45644.208333333336,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,72191,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","75071","Lille - Antwerpen","< >","SINT-NIKLAAS","LOKEREN",2025,2025,36,36,"2025-09-02",45644.013888888891,"2025-09-06",45644.184027777781,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 501106:  P221 goederencorridors Lokeren +R56 tot 05u20",null,null,75071,"2024-08-23",0,"1,2,3,4,5"]
[null,"Infrabel","69142","Lille - Charleroi","< >","Y.NOORD HALLE","SAINTES",2025,2025,36,37,"2025-09-05",45644.986111111109,"2025-09-08",45644.180555555555,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken zone FH_10 volgens onderhoudskalender",null,null,69142,"2024-02-05",1,"5,6"]
[null,"Infrabel","73048","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2025,2025,36,36,"2025-09-06",45644.333333333336,"2025-09-06",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73048,"2024-05-28",0,"5,6"]
[null,"Infrabel","72452","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,36,37,"2025-09-06",45644.25,"2025-09-08",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-\r\nChange Request nog op te maken/aan te vullen zoals besproken tijdens meeting met B-ST en B-PT.4\r\n\r\n\r\nsporen 3+4+5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde\r\n\r\n",null,null,72452,"2024-06-26",1,"5,6"]
[null,"Infrabel","72552","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,36,36,"2025-09-06",45644.3125,"2025-09-06",45644.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72552,"2023-11-03",0,"5,6"]
[null,"Infrabel","82469","Athus - Meuse","< >","GEDINNE","BERTRIX",2025,2025,36,37,"2025-09-07",45644.958333333336,"2025-09-08",45644.1875,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\nUPM: 490190",null,null,82469,"2024-10-07",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","64928","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2025,2025,36,36,"2025-09-07",45644,"2025-09-07",45644.166666666664,"1d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Buitendienststellen van de van de volledige overeenkomstige EBP-zone gedurende minimaal 2,5 uur te bepalen tussen\r\n22.00 uur en 06.00 uur\r\nUpdate EBP release to last version\r\nR-447110",null,null,64928,"2023-04-19",0,"5,6"]
[null,"Infrabel","72563","Erquelinnes - Montzen",">","Y.RENORY","Y.VAL-BENOIT",2025,2025,36,36,"2025-09-07",45644.3125,"2025-09-07",45644.583333333336,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A  YVB - YRENORY",null,null,72563,"2023-11-03",0,"5,6"]
[null,"Infrabel","74035","Namur - Antwerpen","< >","GENT-SINT-PIETERS","MERELBEKE-ROOSTER S",2025,2025,36,36,"2025-09-07",45644.034722222219,"2025-09-07",45644.243055555555,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 503225: Reservatie onderhoud schets za^zo\r\n\r\nL50E TLO Rooster S tot FGSP\r\nL58 + L58/1 TLO tot FGDM",null,null,74035,"2024-08-26",0,"5,6"]
[null,"Infrabel","69112","Lille - Antwerpen","< >","Y.ZWIJNDRECHT-FORT","SINT-NIKLAAS",2025,2025,37,37,"2025-09-08",45644.958333333336,"2025-09-13",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Verlenging buitendienststelling NW",null,null,69112,"2023-09-06",0,"1,2,3,4,5"]
[null,"Infrabel","59232","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,37,37,"2025-09-08",45644.979166666664,"2025-09-13",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Stap 33: Aanleg perronspoor IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters- Y. West driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters- Y. West driehoek Ledeberg \r\nTLO L 50A/6 Gent Sint Pieters-Y. Assels\r\nSP A L58/1 Y West Driehoek ",null,null,59232,"2023-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","77944","Namur - Antwerpen","< >","WONDELGEM","SLEIDINGE",2025,2025,37,37,"2025-09-08",45644.9375,"2025-09-13",45644.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Project R4WO\r\n\r\nCR 2025-068\r\nR-502478-xx",null,null,77944,"2024-12-11",0,"1,2,3,4,5"]
[null,"Infrabel","72980","Lille - Charleroi",">","BRUXELLES-MIDI","LOT",2025,2025,37,37,"2025-09-08",45644.986111111109,"2025-09-13",45644.201388888891,"5d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FH_04 Area CE volgens onderhoudskalender 2025\r\nBuitendienststelling L96 spoor B tussen FBMZ en Lot.",null,null,72980,"2024-03-08",0,"1,2,3,4,5"]
[null,"Infrabel","70454","Namur - Antwerpen","< >","Y.HOLLAND","LUCHTBAL-ROOSTER S",2025,2025,37,37,"2025-09-08",45644.993055555555,"2025-09-13",45644.1875,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissel Y Antwerpen-Luchtbal\r\nHKV",null,null,70454,"2024-02-06",0,"1,2,3,4,5"]
[null,"Infrabel","77517","Athus - Meuse",">","PALISEUL","BERTRIX",2025,2025,37,37,"2025-09-09",45644.333333333336,"2025-09-09",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,77517,"2024-05-27",0,"1,2,3,4,5"]
[null,"Infrabel","67917","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,37,37,"2025-09-09",45644.020833333336,"2025-09-13",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67917,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","75072","Lille - Antwerpen","< >","SINT-NIKLAAS","LOKEREN",2025,2025,37,37,"2025-09-09",45644.013888888891,"2025-09-13",45644.184027777781,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 501107: P221 goederencorridors Lokeren +R56 tot 05u20\r\n\r\n+ Onderhoud Sp A/B L59 tss Lokeren en Sint-Niklaas op R56",null,null,75072,"2024-08-26",0,"1,2,3,4,5"]
[null,"Infrabel","77286","Athus - Meuse",">","VONECHE","GEDINNE",2025,2025,37,37,"2025-09-11",45644.333333333336,"2025-09-11",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,77286,"2024-05-27",0,"1,2,3,4,5"]
[null,"Infrabel","56543","Athus - Meuse","< >","HOUYET","BEAURAING",2025,2025,37,38,"2025-09-12",45644.958333333336,"2025-09-15",45644.1875,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Assainissement bk 16.200\r\nDossier concertation octobre 2022\r\nUPM:489502",null,null,56543,"2024-01-16",1,"5,6"]
[null,"Infrabel","55534","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,37,38,"2025-09-12",45644.965277777781,"2025-09-15",45644.204861111109,"2d, 05:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Pi métalliques 52.015 et 52.215\r\nCTL WE\r\nTCR: 488328",null,null,55534,"2024-12-17",1,"5,6"]
[null,"Infrabel","76424","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2025,2025,37,37,"2025-09-12",45644.326388888891,"2025-09-12",45644.645833333336,"1d, 07:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visites J10",null,null,76424,"2024-02-27",0,"1,2,3,4,5"]
[null,"Infrabel","74516","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN",2025,2025,37,38,"2025-09-13",45644,"2025-09-15",45644.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-016\r\nRenovatie BX L27/L25.\r\nR-512794",null,null,74516,"2024-11-14",1,"5,6"]
[null,"Infrabel","77273","Athus - Meuse",">","VONECHE","BEAURAING",2025,2025,37,37,"2025-09-14",45644.333333333336,"2025-09-14",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,77273,"2024-05-27",0,"5,6"]
[null,"Infrabel","70540","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2025,2025,37,37,"2025-09-14",45644.25,"2025-09-14",45644.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Kleine vernieuwingen lopend spoor en wissels\r\n+\r\ninstandhouding kunstwerken (CIV)",null,null,70540,"2024-03-08",0,"5,6"]
[null,"Infrabel","61864","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2025,2025,38,38,"2025-09-15",45644.958333333336,"2025-09-18",45644.208333333336,"3d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage Flawinne - Moustier\r\nUPM: 489377",null,null,61864,"2024-08-21",0,"1,2,3,4,5"]
[null,"Infrabel","70430","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","LA SAMBRE",2025,2025,38,38,"2025-09-15",45644.958333333336,"2025-09-21",45644.173611111109,"6d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Grill Charleroi-Sud - Phase 1.2\r\nTCR 497648",null,null,70430,"2024-03-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","55572","Athus - Meuse",">","HOUYET","BEAURAING",2025,2025,38,48,"2025-09-15",45644.333333333336,"2025-11-24",45644.25,"70d, 22:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Assainissement bk 16.200.\r\nDossier concertation octobre 2022\r\nUPM:490168\r\nintégrer visites",null,null,55572,"2024-04-04",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","68348","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,38,38,"2025-09-15",45644.972222222219,"2025-09-19",45644.208333333336,"4d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Nouvelles fondations - terrassement quai voie II / III",null,null,68348,"2023-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","70961","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,38,38,"2025-09-15",45644.9375,"2025-09-19",45644.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 500379: Onderhoud zone 04.35.01 HKV\r\n\r\nL66 FLC-Y Kortrijk West niet inbegrepen\r\nFLC SP III-IV-V inbegrepen\r\nR5/R6 niet inbegrepen wegens WE TLO L73",null,null,70961,"2024-08-27",0,"1,2,3,4,5"]
[null,"Infrabel","58108","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.NOORD DRIEHOEK AARSCHOT",2025,2025,38,38,"2025-09-15",45644.993055555555,"2025-09-19",45644.1875,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"vernieuwing OW 38 + 39 +43",null,null,58108,"2023-12-04",0,"1,2,3,4,5"]
[null,"Infrabel","56482","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2025,2025,38,38,"2025-09-15",45644.923611111109,"2025-09-19",45644.173611111109,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Chape PI km 121,703\r\nNuits de préparation\r\nTCR 487671",null,null,56482,"2024-01-03",0,"1,2,3,4,5"]
[null,"Infrabel","76379","Lille - Charleroi",">","Y.FELUY","MANAGE",2025,2025,38,38,"2025-09-16",45644.333333333336,"2025-09-16",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagno J6",null,null,76379,"2024-02-26",0,"1,2,3,4,5"]
[null,"Infrabel","75073","Lille - Antwerpen","< >","SINT-NIKLAAS","LOKEREN",2025,2025,38,38,"2025-09-16",45644.013888888891,"2025-09-19",45644.184027777781,"4d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 501110: P221 goederencorridors Lokeren",null,null,75073,"2024-08-27",0,"1,2,3,4,5"]
[null,"Infrabel","55833","Namur - Antwerpen",">","FRANIERE","MOUSTIER",2025,2025,38,39,"2025-09-18",45644.958333333336,"2025-09-23",45644.208333333336,"4d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage Flawinne - Moustier\r\nUPM: 489381",null,null,55833,"2024-01-16",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","76432","Lille - Charleroi",">","MANAGE","LUTTRE",2025,2025,38,38,"2025-09-18",45644.333333333336,"2025-09-18",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagno J12",null,null,76432,"2024-02-27",0,"1,2,3,4,5"]
[null,"Infrabel","67047","Namur - Antwerpen","< >","AUVELAIS","MOUSTIER",2025,2025,38,39,"2025-09-19",45644.958333333336,"2025-09-22",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Electrification Gare de Jemeppe Sur Sambre\r\nUPM: 489247",null,null,67047,"2024-01-15",1,"5,6"]
[null,"Infrabel","66613","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2025,2025,38,39,"2025-09-19",45644.958333333336,"2025-09-22",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS de Gqemblox bk 0,776\r\nUPM: 488782",null,null,66613,"2024-01-10",1,"5,6"]
[null,"Infrabel","73072","Athus - Meuse",">","VIRTON","SIGNEULX",2025,2025,38,38,"2025-09-19",45644.333333333336,"2025-09-19",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73072,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","74517","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN",2025,2025,38,39,"2025-09-20",45644,"2025-09-22",45644.166666666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-017\r\nRenovatie BX L27/L25.\r\nR-512795",null,null,74517,"2024-11-14",1,"5,6"]
[null,"Infrabel","69111","Lille - Antwerpen","< >","Y.ZWIJNDRECHT-FORT","SINT-NIKLAAS",2025,2025,38,39,"2025-09-20",45644.020833333336,"2025-09-22",45644.194444444445,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Verlenging buitendienststelling NW\r\nVernieuwing wisselonderdelen en sporen te Melsele.",null,null,69111,"2023-09-04",1,"5,6"]
[null,"Infrabel","80258","Athus - Meuse",">","NAMUR","BOIS D'AUSSE",2025,2025,38,38,"2025-09-20",45644.375,"2025-09-20",45644.677083333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-085 \r\nVisite périodique de jour le samedi pour AI43. (suite mise en service ETCS)\r\nVA: Le samedi entre 9h et 16h15\r\nVB: Le Samedi entre 8h45 et 16h\r\nA dupliquer toutes les 8 semaines.\r\n",null,null,80258,"2024-08-02",0,"5,6"]
[null,"Infrabel","57970","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,38,40,"2025-09-21",45644.996527777781,"2025-09-29",45644.1875,"7d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek\r\n+ BVL Y Weerde - Y Prinsenhoek \r\n+ RTB L27B/1\r\n+Onderhoud\r\nCf Escalade Head Of nov/dec 2023",null,null,57970,"2024-04-09",1,"1,2,3,4,5,6,7"]
[null,"Infrabel","54842","Namur - Antwerpen","< >","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,39,39,"2025-09-22",45644.958333333336,"2025-09-27",45644.201388888891,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 4\r\nDossier de concertation validé en octobre 2022\r\nTCR: 494686",null,null,54842,"2024-07-19",0,"1,2,3,4,5"]
[null,"Infrabel","72729","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,39,39,"2025-09-22",45644.979166666664,"2025-09-27",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72729,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","70252","Erquelinnes - Montzen","< >","LA SAMBRE","CHARLEROI-CENTRAL",2025,2025,39,39,"2025-09-22",45644.944444444445,"2025-09-25",45644.173611111109,"3d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Grill Charleroi-Sud - Phase 1.3\r\nAs 01AG pose 2 Jic + pose 2 Jic entre 01AG & 01BG/02G + 01BG/02G remplacer fer par epoxy + pose 2 Jic entre 03G/04AG & 01BG/02G\r\nSelon plan \"Aménagement Charleroi 2025 _ Coupure type 8\"\r\nTCR 497663",null,null,70252,"2024-03-05",0,"1,2,3,4,5"]
[null,"Infrabel","71667","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2025,2025,39,39,"2025-09-22",45644.947916666664,"2025-09-27",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 500427: Onderhoud zone 05.32\r\nL204 en uren aanpassen UPM",null,null,71667,"2024-08-28",0,"1,2,3,4,5"]
[null,"Infrabel","67919","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,39,39,"2025-09-23",45644.020833333336,"2025-09-27",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67919,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","73234","Athus - Meuse",">","STOCKEM-NORD","ARLON",2025,2025,39,39,"2025-09-23",45644.361111111109,"2025-09-23",45644.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73234,"2023-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","73091","Athus - Meuse",">","HALANZY","SIGNEULX",2025,2025,39,39,"2025-09-24",45644.333333333336,"2025-09-24",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie  B",null,null,73091,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","70622","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2025,2025,39,39,"2025-09-25",45644.375,"2025-09-25",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen - Schijnpoort + inrit bundel Q",null,null,70622,"2024-03-13",0,"1,2,3,4,5"]
[null,"Infrabel","47338","Athus - Meuse","< >","ANSEREMME","GENDRON-CELLES",2025,2025,39,40,"2025-09-26",45644.958333333336,"2025-09-29",45644.1875,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mise en service CV Jade\r\nUPM:489466",null,null,47338,"2024-01-16",1,"5,6"]
[null,"Infrabel","56544","Athus - Meuse","< >","Y.NEFFE","GENDRON-CELLES",2025,2025,39,40,"2025-09-26",45644.958333333336,"2025-09-29",45644.1875,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance, renouvellement de traverses au niveau du viaduc d’Anseremme.\r\nUPM:489460\r\nRQ333: Visites Dinant-Anseremme et Anseremme - Gendron intégrables ?",null,null,56544,"2024-03-14",1,"5,6"]
[null,"Infrabel","50219","Erquelinnes - Montzen",">","HUY","ANDENNE",2025,2025,39,40,"2025-09-26",45644.979166666664,"2025-09-29",45644.229166666664,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA\r\n+ suppression des passages à niveau n°75 à 78 (construction des couloir sous-voies)\r\nUPM: 489609\r\nSIRU 2025_08 à 09_SE_L125_Massification travaux OA + quais Statte",null,null,50219,"2024-05-31",0,"5,6"]
[null,"Infrabel","70635","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,39,39,"2025-09-26",45644.375,"2025-09-26",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y Holland + inrit bundel Q",null,null,70635,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","75336","Lille - Antwerpen",">","LOKEREN","OOSTAKKER",2025,2025,39,39,"2025-09-27",45644.020833333336,"2025-09-27",45644.229166666664,"1d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"TCR 500292: Reservatie onderhoud",null,null,75336,"2024-08-28",0,"1,2,3,4,5"]
[null,"Infrabel","68805","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,39,39,"2025-09-27",45644.340277777781,"2025-09-27",45644.659722222219,"1d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie A Ottignies - Gembloux (extension Rhisnes SAS)\r\nUPM: 488041",null,null,68805,"2024-01-05",0,"5,6"]
[null,"Infrabel","75335","Lille - Antwerpen","< >","SINT-NIKLAAS","OOSTAKKER",2025,2025,39,39,"2025-09-28",45644.020833333336,"2025-09-28",45644.225694444445,"1d, 04:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 500345: Reservatie onderhoud",null,null,75335,"2024-08-28",0,"5,6"]
[null,"Infrabel","82277","Lille - Antwerpen","< >","GENT-SINT-PIETERS","KORTRIJK",2025,2025,39,39,"2025-09-28",45644.0625,"2025-09-28",45644.1875,"1d, 03:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-199\r\nIDS P014b_RW_LK_L1FS\r\nR-521703",null,null,82277,"2024-11-05",0,"5,6"]
[null,"Infrabel","61866","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2025,2025,40,40,"2025-09-29",45644.208333333336,"2025-09-30",45644.208333333336,"1d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage Flawinne - Moustier\r\nUPM: 489522",null,null,61866,"2024-01-16",0,"1,2,3,4,5"]
[null,"Infrabel","58109","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.NOORD DRIEHOEK AARSCHOT",2025,2025,40,40,"2025-09-29",45644.993055555555,"2025-10-04",45644.1875,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"vernieuwing OW39 + 38 + 43",null,null,58109,"2024-07-01",0,"1,2,3,4,5"]
[null,"Infrabel","73152","Lille - Charleroi","< >","HALLE","ENGHIEN",2025,2025,40,40,"2025-09-29",45644.947916666664,"2025-10-03",45644.180555555555,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Assainissement\r\nUPM 487965",null,null,73152,"2024-01-04",0,"1,2,3,4,5"]
[null,"Infrabel","73144","Athus - Meuse",">","NAMUR","JAMBES",2025,2025,40,40,"2025-09-29",45644.388888888891,"2025-09-29",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73144,"2023-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","69113","Lille - Antwerpen","< >","Y.ZWIJNDRECHT-FORT","SINT-NIKLAAS",2025,2025,40,40,"2025-09-30",45644.020833333336,"2025-10-04",45644.194444444445,"5d, 04:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Verlenging buitendienststelling NW\r\nVernieuwing wisselonderdelen en sporen te Melsele. \r\nPeriodiciteit: 1 keer / jaar, TLO van 48u. \r\n+ weekend voor en na nachtprestaties voorzien.\r\nVoorkeur TLO week 40 (za 4 en zo 5/10) en nachtprestaties week 39 (ma/d",null,null,69113,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","61869","Namur - Antwerpen",">","FRANIERE","FLAWINNE",2025,2025,40,40,"2025-10-01",45644.958333333336,"2025-10-02",45644.208333333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage Flawinne - Moustier\r\nUPM: 489530",null,null,61869,"2024-01-16",0,"1,2,3,4,5"]
[null,"Infrabel","73032","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,40,40,"2025-10-02",45644.333333333336,"2025-10-02",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73032,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","73240","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2025,2025,40,40,"2025-10-02",45644.368055555555,"2025-10-02",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie:",null,null,73240,"2023-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","73033","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2025,2025,40,40,"2025-10-03",45644.333333333336,"2025-10-03",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73033,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","59442","Lille - Charleroi","< >","HALLE","ENGHIEN",2025,2025,40,41,"2025-10-03",45644.9375,"2025-10-06",45644.194444444445,"2d, 06:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Assainissement\r\nUPM 487967",null,null,59442,"2024-01-04",1,"5,6"]
[null,"Infrabel","73241","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2025,2025,40,40,"2025-10-03",45644.368055555555,"2025-10-03",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73241,"2023-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","71176","Erquelinnes - Montzen",">","AMAY","ENGIS",2025,2025,40,40,"2025-10-04",45644.333333333336,"2025-10-04",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71176,"2024-01-19",0,"1,2,3,4,5"]
[null,"Infrabel","73237","Athus - Meuse",">","ARLON","Y.AUTELBAS",2025,2025,40,40,"2025-10-04",45644.361111111109,"2025-10-04",45644.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73237,"2023-11-15",0,"5,6"]
[null,"Infrabel","73238","Athus - Meuse",">","MARBEHAN","HABAY",2025,2025,40,40,"2025-10-05",45644.375,"2025-10-05",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73238,"2023-11-15",0,"5,6"]
[null,"Infrabel","72356","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2025,2025,41,41,"2025-10-06",45644.958333333336,"2025-10-11",45644.201388888891,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien massification\r\nTCR 507204",null,null,72356,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","71749","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2025,2025,41,41,"2025-10-06",45644.333333333336,"2025-10-06",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 116 à 121 + faisceau manage\r\nNe fonctionne plus en Phase 5\r\nTCR 507092",null,null,71749,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","70070","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","Y.LEMAN",2025,2025,41,41,"2025-10-06",45644.951388888891,"2025-10-11",45644.201388888891,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Z9.41 - P3 maintenance AI41\r\n",null,null,70070,"2024-02-16",0,"1,2,3,4,5"]
[null,"Infrabel","70759","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2025,2025,41,41,"2025-10-06",45644.951388888891,"2025-10-11",45644.1875,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud lopend spoor en spoortoestellen\r\nHKV\r\nZ23.22.01\r\n+\r\nAfbraak tijdelijke passerelle te Antwerpen Zuid\r\n+\r\nOnderhoudsweek Kennedytunnel.",null,null,70759,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","65234","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","FROYENNES",2025,2025,41,41,"2025-10-06",45644.944444444445,"2025-10-11",45644.222222222219,"5d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction d’un PS pour supprimer les PN 8 et 10 - Pose des coffrages des culées\r\nUPM 487999",null,null,65234,"2024-01-04",0,"1,2,3,4,5"]
[null,"Infrabel","79706","Athus - Meuse",">","MARBEHAN","LAVAUX",2025,2025,41,41,"2025-10-06",45644.364583333336,"2025-10-10",45644.635416666664,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-119: Peignage parois rocheuses\r\nTCR 512567",null,null,79706,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","71888","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2025,2025,41,41,"2025-10-06",45644.975694444445,"2025-10-11",45644.208333333336,"5d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71888,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","72994","Namur - Antwerpen","< >","ROGIER","WATERMAEL",2025,2025,41,41,"2025-10-06",45644.982638888891,"2025-10-11",45644.166666666664,"5d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone MTB_01 Area CE volgens onderhoudskalender 2025.\r\n\r\nBuitendienststelling L161 voor onderhoudswerken.\r\nBijkomend L161A tussen Y Jubelpark en Y Watermaal, L26/4 tussen Etterbeek en Y Boondaal en L26/2 MTB-Y MTB\r\nR5/R6 stoppen om 04u00 voor M",null,null,72994,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","67921","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,41,41,"2025-10-07",45644.020833333336,"2025-10-10",45644.208333333336,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67921,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","72731","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,41,41,"2025-10-07",45644.003472222219,"2025-10-11",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72731,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","71204","Erquelinnes - Montzen",">","JAVA","ANDENNE",2025,2025,41,41,"2025-10-09",45644.5625,"2025-10-09",45644.645833333336,"1d, 02:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71204,"2023-10-26",0,"1,2,3,4,5"]
[null,"Infrabel","71206","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2025,2025,41,41,"2025-10-09",45644.375,"2025-10-09",45644.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71206,"2023-10-26",0,"1,2,3,4,5"]
[null,"Infrabel","75667","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","WATERMAEL",2025,2025,41,42,"2025-10-10",45644.979166666664,"2025-10-13",45644.1875,"3d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing station Etterbeek B-ST: Sporen 1-2-3-4",null,null,75667,"2024-05-23",0,"5,6"]
[null,"Infrabel","68307","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2025,2025,41,42,"2025-10-11",45644.958333333336,"2025-10-13",45644.173611111109,"2d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Chape PI km 122.927\r\nNuits finition + bourrage de révision + réglage contrainte\r\nTCR 487780",null,null,68307,"2024-01-03",0,"5,6"]
[null,"Infrabel","57971","Namur - Antwerpen","< >","Y.WEERDE","MUIZEN-ROOSTER T",2025,2025,41,42,"2025-10-11",45644.25,"2025-10-13",45644.1875,"2d, 22:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen houtstukken Leuvensevaart, ONB Baarbeek",null,null,57971,"2024-11-12",1,"5,6"]
[null,"Infrabel","59606","Namur - Antwerpen","< >","ESSEN-GRENS","KAPELLEN",2025,2025,41,42,"2025-10-11",45644.041666666664,"2025-10-13",45644.166666666664,"2d, 03:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vervangen wisselonderdelen\r\n+\r\nOude Landen project 301",null,null,59606,"2024-02-08",1,"5,6"]
[null,"Infrabel","76019","Lille - Charleroi",">","BRAINE-LE-COMTE","Y.FELUY",2025,2025,41,41,"2025-10-11",45644.34375,"2025-10-11",45644.645833333336,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique AI52 + AI53\r\n",null,null,76019,"2024-05-30",0,"5,6"]
[null,"Infrabel","75338","Lille - Antwerpen","< >","Y.MELSELE","OOSTAKKER",2025,2025,41,41,"2025-10-12",45644.020833333336,"2025-10-12",45644.21875,"1d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Reservatie onderhoud",null,null,75338,"2024-01-26",0,"5,6"]
[null,"Infrabel","68043","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN-GRENS",2025,2025,41,41,"2025-10-12",45644.034722222219,"2025-10-12",45644.243055555555,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud + overwegen",null,null,68043,"2024-06-26",0,"5,6"]
[null,"Infrabel","71208","Erquelinnes - Montzen",">","ANDENNE","MARCHE-LES-DAMES",2025,2025,41,41,"2025-10-12",45644.354166666664,"2025-10-12",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71208,"2023-10-26",0,"5,6"]
[null,"Infrabel","83907","Lille - Charleroi","< >","ATH","JURBISE",2025,2025,42,42,"2025-10-13",45644.958333333336,"2025-10-17",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux de finitions SNCB - Finition quai voie II de FBG.",null,null,83907,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","69704","Namur - Antwerpen","< >","MECHELEN","KONTICH-LINT",2025,2025,42,42,"2025-10-13",45644.958333333336,"2025-10-18",45644.201388888891,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende buitenwerken omvorming 50Hz naar TFSK (samen met L27B): \r\n- min. 2 weken WN voor indienststelling (in maand ervoor)\r\n\r\n+\r\n\r\nHerelektrificatie L27\r\n+\r\nOnderhoud",null,null,69704,"2024-01-12",0,"1,2,3,4,5"]
[null,"Infrabel","72732","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,42,42,"2025-10-13",45644.979166666664,"2025-10-18",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72732,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","68352","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,42,42,"2025-10-13",45644.972222222219,"2025-10-18",45644.208333333336,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Démontage couverture + pose structure quai voie II / III",null,null,68352,"2023-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","79707","Athus - Meuse",">","LAVAUX","MARBEHAN",2025,2025,42,42,"2025-10-13",45644.364583333336,"2025-10-17",45644.635416666664,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-119: Peignage parois rocheuses\r\nTCR 512563",null,null,79707,"2024-10-11",0,"1,2,3,4,5"]
[null,"Infrabel","67922","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,42,42,"2025-10-14",45644.020833333336,"2025-10-18",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67922,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","53255","Lille - Charleroi","< >","HALLE","ENGHIEN",2025,2025,42,42,"2025-10-14",45644.013888888891,"2025-10-18",45644.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Assainissement\r\nTravaux de finition\r\nUPM 487971",null,null,53255,"2024-01-04",0,"1,2,3,4,5"]
[null,"Infrabel","71912","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2025,2025,42,42,"2025-10-14",45644.083333333336,"2025-10-18",45644.125,"5d, 01:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,71912,"2024-06-26",0,"1,2,3,4,5"]
[null,"Infrabel","76411","Lille - Charleroi",">","Y.NORD","MARCHIENNE-AU-PONT",2025,2025,42,42,"2025-10-15",45644.333333333336,"2025-10-15",45644.4375,"1d, 02:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites J11",null,null,76411,"2024-02-26",0,"1,2,3,4,5"]
[null,"Infrabel","56361","Namur - Antwerpen","< >","FLAWINNE","MOUSTIER",2025,2025,42,43,"2025-10-18",45644.958333333336,"2025-10-20",45644.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage voie B Flawinne - Moustier\r\nUPM: 489400\r\n",null,null,56361,"2024-01-16",0,"5,6"]
[null,"Infrabel","77288","Athus - Meuse",">","VONECHE","GEDINNE",2025,2025,42,42,"2025-10-18",45644.333333333336,"2025-10-18",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,77288,"2024-05-27",0,"1,2,3,4,5"]
[null,"Infrabel","66393","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2025,2025,42,43,"2025-10-18",45644.027777777781,"2025-10-20",45644.166666666664,"2d, 03:20h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Bundel centraal Merelbeke\r\naansluiting nieuwe sporen 5-6-7-8 van bundel centraal + aansluiten aan L50E \r\n+ Dienst onderhoud werkt mee waar mogelijk\r\nCf Escalade Head Of nov/dec 2023\r\n\r\nTCR496629",null,null,66393,"2024-03-06",0,"5,6"]
[null,"Infrabel","64317","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,42,42,"2025-10-18",45644.986111111109,"2025-10-19",45644.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z19. 51\r\nMini CTL\r\nTCR: 491779",null,null,64317,"2024-01-31",1,"5,6"]
[null,"Infrabel","73051","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2025,2025,42,42,"2025-10-19",45644.333333333336,"2025-10-19",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73051,"2024-05-28",0,"5,6"]
[null,"Infrabel","68183","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2025,2025,42,42,"2025-10-19",45644.333333333336,"2025-10-19",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Sint-Joris-Weert - Wavre VA/VB\r\nUPM: 488520",null,null,68183,"2024-01-09",0,"5,6"]
[null,"Infrabel","80271","Athus - Meuse",">","HAVERSIN","MARLOIE",2025,2025,42,42,"2025-10-19",45644.364583333336,"2025-10-19",45644.666666666664,"1d, 07:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"CR 2025-085 \r\nVisite périodique de jour le dimanche pour AI45. (suite mise en service ETCS)\r\nVA: Le dimanche entre 08h45 et 16h00\r\nVB: Le dimanche entre 08h00 et 15h15\r\nA dupliquer toutes les 8 semaines.\r\nTCR 510716",null,null,80271,"2024-08-05",0,"5,6"]
[null,"Infrabel","70195","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2025,2025,43,43,"2025-10-20",45644.958333333336,"2025-10-25",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails, attaches...",null,null,70195,"2024-01-22",0,"1,2,3,4,5"]
[null,"Infrabel","70548","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.ARENDSTRAAT",2025,2025,43,43,"2025-10-20",45644.979166666664,"2025-10-25",45644.1875,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud wissels Y Noord Berchem\r\nHKV",null,null,70548,"2024-01-29",0,"1,2,3,4,5"]
[null,"Infrabel","77946","Namur - Antwerpen","< >","WONDELGEM","SLEIDINGE",2025,2025,43,43,"2025-10-20",45644.9375,"2025-10-25",45644.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Project R4WO\r\n\r\nCR 2025-068\r\nR-502480-xx",null,null,77946,"2024-12-11",0,"1,2,3,4,5"]
[null,"Infrabel","69936","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","ERQUELINNES",2025,2025,43,43,"2025-10-20",45644.875,"2025-10-25",45644.208333333336,"5d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nCHA25_0027989 - PMR Maubeuge\r\nTCR 487676",null,null,69936,"2024-01-03",0,"1,2,3,4,5"]
[null,"Infrabel","73129","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2025,2025,43,43,"2025-10-20",45644.385416666664,"2025-10-20",45644.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,73129,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","73001","Namur - Antwerpen","< >","SCHAERBEEK","Y.HAREN-NORD",2025,2025,43,43,"2025-10-20",45644.395833333336,"2025-10-24",45644.625,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone FSR_10  Area CE volgens onderhoudskalender 2025\r\nBuitendienststelling L27 Y Groep G overdag buiten de spitsuren voor onderhoudswerken.",null,null,73001,"2024-05-22",0,"1,2,3,4,5"]
[null,"Infrabel","72092","Namur - Antwerpen","< >","Y.HEIKE","DENDERMONDE",2025,2025,43,43,"2025-10-21",45644.006944444445,"2025-10-24",45644.201388888891,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z79.33 HKM\r\nZone (geografisch) volgens UPM 398599 (COLT 61753) \r\nR5/R6 niet inbegrepen, conflict Merelbeke",null,null,72092,"2024-08-19",0,"1,2,3,4,5"]
[null,"Infrabel","72733","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,43,43,"2025-10-21",45644.003472222219,"2025-10-25",45644.173611111109,"5d, 04:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72733,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","72936","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,43,43,"2025-10-21",45644.378472222219,"2025-10-21",45644.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,72936,"2023-11-09",0,"1,2,3,4,5"]
[null,"Infrabel","77519","Athus - Meuse",">","PALISEUL","BERTRIX",2025,2025,43,43,"2025-10-23",45644.333333333336,"2025-10-23",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,77519,"2024-05-27",0,"1,2,3,4,5"]
[null,"Infrabel","70623","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2025,2025,43,43,"2025-10-23",45644.375,"2025-10-23",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen - Schijnpoort + inrit bundel Q",null,null,70623,"2024-03-13",0,"1,2,3,4,5"]
[null,"Infrabel","58628","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2025,2025,43,44,"2025-10-24",45644.979166666664,"2025-10-27",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Station Kortrijk buiten dienst voor het leveren en inbouwen van wissels rooster kant Gent.\r\n+\r\nVervangen metalen spoordekken door betonnen bakbruggen (Goedendaglaan KP 40.330 + OW 44 Meyleghemstraat)\r\n+\r\nOnderhoudswerken en kleine vernieuwingswerken\r\nDe",null,null,58628,"2024-07-01",1,"5,6"]
[null,"Infrabel","53241","Lille - Charleroi","< >","SOIGNIES","JURBISE",2025,2025,43,44,"2025-10-24",45644.993055555555,"2025-10-27",45644.1875,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de LRS entre Neufville et Jurbise + Travaux OA Chape 39.680 préparations\r\nWE1/2\r\nTCR 489815",null,null,53241,"2024-05-30",1,"5,6"]
[null,"Infrabel","77289","Athus - Meuse",">","GEDINNE","VONECHE",2025,2025,43,43,"2025-10-25",45644.333333333336,"2025-10-25",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,77289,"2024-05-27",0,"5,6"]
[null,"Infrabel","66394","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2025,2025,43,44,"2025-10-25",45644.027777777781,"2025-10-27",45644.166666666664,"2d, 03:20h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Bundel centraal Merelbeke\r\naansluiting nieuwe sporen 5-6-7-8 van bundel centraal + aansluiten aan L50E\r\n+ Dienst onderhoud werkt mee waar mogelijk\r\nCf Escalade Head Of nov/dec 2023\r\n\r\nTCR496650",null,null,66394,"2024-03-06",0,"5,6"]
[null,"Infrabel","72454","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,43,44,"2025-10-25",45644.25,"2025-10-27",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-\r\nChange Request nog op te maken/aan te vullen zoals besproken tijdens meeting met B-ST en B-PT.4\r\n\r\n\r\nsporen 3+4+5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde\r\n\r\n",null,null,72454,"2024-06-26",1,"5,6"]
[null,"Infrabel","69108","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2025,2025,43,44,"2025-10-25",45644.041666666664,"2025-10-27",45644.1875,"2d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing spoorstaven en dwarsliggers op L59/1 van tegen wissels Y West Berchem tot perron 6-7 station Antwerpen Berchem (perrons inclusief).\r\n+\r\nTUC RAIL P315363 Kennedy tunnel\r\n\r\nDeze werken dienen ASAP uitgevoerd te worden in het kader van Safety F",null,null,69108,"2024-12-09",1,"5,6"]
[null,"Infrabel","82477","Athus - Meuse","< >","GEDINNE","BERTRIX",2025,2025,43,44,"2025-10-26",45644.958333333336,"2025-10-27",45644.1875,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\nUPM: 489455",null,null,82477,"2024-10-08",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","84857","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2025,2025,44,44,"2025-10-27",45644.958333333336,"2025-10-31",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"RER Ott + MDS OA à Faulx \r\nUPM: 532440",null,null,84857,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","71761","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,44,44,"2025-10-27",45644.333333333336,"2025-10-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nTCR 507458",null,null,71761,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","72734","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,44,44,"2025-10-27",45644.979166666664,"2025-11-01",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72734,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","77948","Namur - Antwerpen","< >","WONDELGEM","SLEIDINGE",2025,2025,44,44,"2025-10-27",45644.9375,"2025-11-01",45644.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Project R4WO\r\n\r\nCR 2025-068\r\nR-502483-xx",null,null,77948,"2024-12-11",0,"1,2,3,4,5"]
[null,"Infrabel","68354","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,44,44,"2025-10-27",45644.986111111109,"2025-11-01",45644.208333333336,"5d, 05:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Démontage fondations + pose bardage quai voie II / III",null,null,68354,"2024-01-15",0,"1,2,3,4,5"]
[null,"Infrabel","84856","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2025,2025,44,44,"2025-10-27",45644.173611111109,"2025-10-31",45644.958333333336,"5d, 18:50h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"RER Ott + MDS OA à Faulx \r\nUPM: 532440",null,null,84856,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","73005","Namur - Antwerpen","< >","SCHAERBEEK","Y.JOSAPHAT",2025,2025,44,44,"2025-10-27",45644.395833333336,"2025-10-31",45644.645833333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken Area CE volgens kalender.\r\nZone MTB 03, L161 perronsporen 3+4 te FSR + bundel M",null,null,73005,"2024-05-22",0,"1,2,3,4,5"]
[null,"Infrabel","72093","Namur - Antwerpen","< >","Y.HEIKE","DENDERMONDE",2025,2025,44,44,"2025-10-28",45644.006944444445,"2025-10-31",45644.201388888891,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z79.33 HKM\r\nFDR SPIII-IV\r\nZone volgens UPM 398599 (COLT 61753) \r\nR5/R6 niet inbegrepen, conflict Y Schellebelle",null,null,72093,"2024-08-19",0,"1,2,3,4,5"]
[null,"Infrabel","56511","Athus - Meuse",">","Y.AUBANGE","VIRTON",2025,2025,44,44,"2025-10-28",45644.25,"2025-10-28",45644.916666666664,"2d, 16:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage - Phase 1\r\nDossier de concertation validé en octobre 2022\r\nUPM:488515",null,null,56511,"2024-01-09",0,"1,2,3,4,5"]
[null,"Infrabel","74226","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,44,44,"2025-10-29",45644.354166666664,"2025-10-30",45644.645833333336,"2d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud + schouwen\r\n\r\nSP B BD + perronspoor II\r\n\r\nPerronspoor III tot VII + bundel M ontoegankelijk\r\nR-499752\r\n",null,null,74226,"2024-08-14",0,"1,2,3,4,5"]
[null,"Infrabel","66510","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2025,2025,44,45,"2025-10-31",45644.993055555555,"2025-11-03",45644.166666666664,"2d, 04:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Intervention PN + Entretien divers\r\n+ Massification ; Mise au gabarit des pistes Namur Rhisnes parois rocheuses.\r\n+ Travaux caténaires\r\n24 - Déroulage Namur- Gembloux\r\nUPM: 488329",null,null,66510,"2024-07-15",1,"5,6"]
[null,"Infrabel","54848","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,44,44,"2025-11-01",45644.916666666664,"2025-11-02",45644.916666666664,"1d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 7\r\nDossier de concertation validé en octobre 2022\r\nTCR: 494782",null,null,54848,"2024-07-19",0,"5,6"]
[null,"Infrabel","72455","Namur - Antwerpen","< >","VILVOORDE","VILVOORDE",2025,2025,44,45,"2025-11-01",45644.25,"2025-11-03",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CR 2025-\r\nChange Request nog op te maken/aan te vullen zoals besproken tijdens meeting met B-ST en B-PT.4\r\n\r\nsporen 3+4+5+6+7+8+9\r\nRestauratie trapkooien Vilvoorde\r\n\r\n",null,null,72455,"2024-06-26",1,"5,6"]
[null,"Infrabel","65742","Erquelinnes - Montzen","< >","KINKEMPOIS-BLOCK 2","Y.RENORY",2025,2025,44,44,"2025-11-01",45644.416666666664,"2025-11-02",45644.708333333336,"1d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Z28.41 Maintenance AI41",null,null,65742,"2023-04-20",1,"5,6"]
[null,"Infrabel","75475","Namur - Antwerpen",">","FLEURUS","CHARLEROI-OUEST",2025,2025,44,44,"2025-11-02",45644.354166666664,"2025-11-02",45644.625,"1d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno 2025: L140 Partie 2",null,null,75475,"2024-03-22",0,"5,6"]
[null,"Infrabel","70194","Erquelinnes - Montzen",">","BRESSOUX","VISE",2025,2025,45,45,"2025-11-03",45644.958333333336,"2025-11-08",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien des PN, rails, attaches...",null,null,70194,"2024-01-22",0,"1,2,3,4,5"]
[null,"Infrabel","68355","Lille - Charleroi",">","TUBIZE","FRONT. FLANDRE-WALLONIE L96",2025,2025,45,45,"2025-11-03",45644.972222222219,"2025-11-08",45644.208333333336,"5d, 05:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Tubize SNCB Auvents : Nouvelles fondations - terrassement quai voie II / III",null,null,68355,"2023-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","71238","Erquelinnes - Montzen","< >","HUY","NAMUR",2025,2025,45,45,"2025-11-03",45644.96875,"2025-11-07",45644.215277777781,"4d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z13.43 HKV \r\n\r\n",null,null,71238,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","69110","Lille - Antwerpen","< >","Y.OOST BERCHEM","ANTWERPEN-ZUID",2025,2025,45,45,"2025-11-03",45644.993055555555,"2025-11-08",45644.1875,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Weeknachten voor herziening:\r\nVernieuwing spoorstaven en dwarsliggers op L59/1 van tegen wissels Y West Berchem tot perron 6-7 station Antwerpen Berchem (perrons inclusief). \r\nBuitendienststelling van L59 Antwerpen Zuid tot L59/1 Y Noord Berchem. \r\nOok ",null,null,69110,"2024-03-08",0,"1,2,3,4,5"]
[null,"Infrabel","75390","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2025,2025,45,45,"2025-11-03",45644.395833333336,"2025-11-03",45644.645833333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"DOES Schouwen sporen overdag.\r\nR-510887\r\n",null,null,75390,"2024-08-14",0,"1,2,3,4,5"]
[null,"Infrabel","73008","Namur - Antwerpen",">","SCHAERBEEK","Y.SCHAERBEEK-GROUPE G",2025,2025,45,45,"2025-11-03",45644.427083333336,"2025-11-07",45644.625,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FSR_03 volgens onderhoudskalender Area CE\r\nLokale wissels te FSR thv sporen A L27 en B L36,\r\nFSR sp IX,X en XI",null,null,73008,"2024-05-22",0,"1,2,3,4,5"]
[null,"Infrabel","68064","Namur - Antwerpen","< >","DENDERMONDE","Y.HEIKE",2025,2025,45,45,"2025-11-04",45644.006944444445,"2025-11-07",45644.201388888891,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P208 Waterhuishouding\r\n+\r\nP221 goederencorridors\r\n+\r\nOnderhoud\r\n\r\nFDR SP III-IV in\r\nY Heike niet in\r\n\r\nR5/R6 in WE TLO",null,null,68064,"2023-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","73244","Athus - Meuse",">","STOCKEM-NORD","ARLON",2025,2025,45,45,"2025-11-04",45644.361111111109,"2025-11-04",45644.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73244,"2023-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","73245","Athus - Meuse",">","HABAY","STOCKEM-NORD",2025,2025,45,45,"2025-11-05",45644.375,"2025-11-05",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73245,"2023-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","54849","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2025,2025,45,45,"2025-11-08",45644.916666666664,"2025-11-09",45644.916666666664,"1d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 7\r\nDossier de concertation validé en octobre 2022\r\nTCR: 494783",null,null,54849,"2024-07-19",0,"5,6"]
[null,"Infrabel","55797","Erquelinnes - Montzen","< >","FLEMALLE-ANNEXE","SERAING",2025,2025,45,46,"2025-11-08",45644.25,"2025-11-12",45644.208333333336,"4d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses\r\nUPM: 489655",null,null,55797,"2024-01-17",1,"1,2,3,4,5,6,7"]
[null,"Infrabel","75668","Namur - Antwerpen",">","BRUXELLES-LUXEMBOURG","WATERMAEL",2025,2025,45,46,"2025-11-09",45644.027777777781,"2025-11-10",45644.1875,"2d, 03:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing station Etterbeek B-ST: Sporen 2-3",null,null,75668,"2024-05-23",0,"5,6"]
[null,"Infrabel","70541","Namur - Antwerpen","< >","KONTICH-LINT","Y.DRABSTRAAT",2025,2025,45,45,"2025-11-09",45644.25,"2025-11-09",45644.736111111109,"1d, 11:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Kleine vernieuwingen lopend spoor en wissels",null,null,70541,"2024-02-01",0,"5,6"]
[null,"Infrabel","80740","Lille - ZeeBrugge","< >","BRUGGE","BRUGGE-ROOSTER E",2025,2025,46,46,"2025-11-10",45644.333333333336,"2025-11-11",45644.645833333336,"2d, 07:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-156\r\nR-518965-xx\r\nwerkveld 3411-21\r\nmassificatie onderhoud Tracks&Signaling",null,null,80740,"2024-10-02",0,"1,2,3,4,5"]
[null,"Infrabel","72369","Namur - Antwerpen","< >","SINT-JORIS-WEERT","OTTIGNIES",2025,2025,46,46,"2025-11-10",45644.972222222219,"2025-11-15",45644.222222222219,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien massification\r\nZ5.44\r\nTCR 72369",null,null,72369,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","71711","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2025,2025,46,46,"2025-11-10",45644.361111111109,"2025-11-10",45644.645833333336,"1d, 06:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nGembloux gare en alternance\r\nTCR 507134",null,null,71711,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","68660","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2025,2025,46,46,"2025-11-11",45644.958333333336,"2025-11-14",45644.208333333336,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance et interventions sur liaisons",null,null,68660,"2024-01-22",0,"1,2,3,4,5"]
[null,"Infrabel","70572","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,46,46,"2025-11-11",45644.986111111109,"2025-11-13",45644.236111111109,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen van Y Arendstraat",null,null,70572,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","67803","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2025,2025,46,46,"2025-11-12",45644.020833333336,"2025-11-14",45644.1875,"3d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud \r\nFLC SP III-IV inbegrepen",null,null,67803,"2023-12-15",0,"1,2,3,4,5"]
[null,"Infrabel","53510","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2025,2025,46,46,"2025-11-12",45644.965277777781,"2025-11-15",45644.229166666664,"3d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z9.52 + Maintenance Z.3.53 en P3 HKV\r\n+ Renouvellement de l'étanchéité et renforcement du PS 41.010",null,null,53510,"2024-03-11",0,"1,2,3,4,5"]
[null,"Infrabel","73034","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2025,2025,46,46,"2025-11-13",45644.333333333336,"2025-11-13",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,73034,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","73250","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2025,2025,46,46,"2025-11-13",45644.368055555555,"2025-11-13",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie:",null,null,73250,"2023-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","73119","Athus - Meuse",">","HALANZY","Y.AUBANGE",2025,2025,46,46,"2025-11-14",45644.333333333336,"2025-11-14",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,73119,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","73251","Athus - Meuse",">","LIBRAMONT","NEUFCHATEAU",2025,2025,46,46,"2025-11-14",45644.368055555555,"2025-11-14",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73251,"2023-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","66395","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2025,2025,46,47,"2025-11-15",45644.027777777781,"2025-11-17",45644.166666666664,"2d, 03:20h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Bundel centraal Merelbeke\r\naansluiting nieuwe sporen 5-6-7-8 van bundel centraal + aansluiten aan L50E\r\n+ Dienst onderhoud werkt mee waar mogelijk\r\nCf Escalade Head Of nov/dec 2023\r\n\r\nTCR496654",null,null,66395,"2024-03-06",0,"5,6"]
[null,"Infrabel","60159","Namur - Antwerpen","< >","Y.NOORD DRIEHOEK LEDEBERG","GENT-DAMPOORT",2025,2025,46,47,"2025-11-15",45644.25,"2025-11-17",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Instandhouding vertakking Noord-Driehoek Ledeberg",null,null,60159,"2024-02-26",1,"5,6"]
[null,"Infrabel","68760","Namur - Antwerpen","< >","FRONT. FLANDRE-WALLONIE L139","LEUVEN",2025,2025,46,47,"2025-11-15",45644.003472222219,"2025-11-17",45644.208333333336,"2d, 04:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Buitenwerken, BDS, meewerken mogelijk\r\nETCS Baanvak Heverlee – St-Joris-Weert (doorsteken e.d.) + grid St-Joris-Weert",null,null,68760,"2023-09-06",1,"5,6"]
[null,"Infrabel","68167","Namur - Antwerpen",">","AUVELAIS","FLAWINNE",2025,2025,46,46,"2025-11-16",45644.333333333336,"2025-11-16",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L 130\r\nUPM: 489223",null,null,68167,"2024-01-15",0,"5,6"]
[null,"Infrabel","68808","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,46,46,"2025-11-16",45644.333333333336,"2025-11-16",45644.659722222219,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie B Ottignies - Gembloux (extension Rhisnes SAS)\r\nUPM: 488051",null,null,68808,"2024-01-05",0,"5,6"]
[null,"Infrabel","71185","Erquelinnes - Montzen",">","ENGIS","TILLEUR",2025,2025,46,46,"2025-11-16",45644.354166666664,"2025-11-16",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43 + AI41",null,null,71185,"2023-12-15",0,"5,6"]
[null,"Infrabel","72737","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,47,47,"2025-11-17",45644.979166666664,"2025-11-22",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72737,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","65784","Namur - Antwerpen","< >","AUVELAIS","CHATELET-GRIL OUEST",2025,2025,47,47,"2025-11-17",45644.965277777781,"2025-11-22",45644.208333333336,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.51\r\nP3 HKV",null,null,65784,"2024-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","72580","Erquelinnes - Montzen",">","VISE","VISE-FRONTIERE",2025,2025,47,47,"2025-11-17",45644.5,"2025-11-17",45644.666666666664,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie, PN et intervention avec S460 sur la voie contiguë + ATW",null,null,72580,"2023-11-03",0,"1,2,3,4,5"]
[null,"Infrabel","72094","Namur - Antwerpen","< >","Y.HEIKE","DENDERMONDE",2025,2025,47,47,"2025-11-18",45644.006944444445,"2025-11-21",45644.201388888891,"4d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z79.33 HKM\r\nFDR SPIII-IV \r\nZone volgens UPM 398599 (COLT 61753) \r\nR5/R6 niet inbegrepen, conflict Merelbeke",null,null,72094,"2024-08-19",0,"1,2,3,4,5"]
[null,"Infrabel","73374","Athus - Meuse",">","LUSTIN","YVOIR",2025,2025,47,47,"2025-11-18",45644.375,"2025-11-18",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73374,"2023-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","70497","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,47,47,"2025-11-19",45644.375,"2025-11-19",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y-Holland",null,null,70497,"2024-02-14",0,"1,2,3,4,5"]
[null,"Infrabel","73375","Athus - Meuse",">","YVOIR","LUSTIN",2025,2025,47,47,"2025-11-19",45644.375,"2025-11-19",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,73375,"2023-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","71121","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,47,47,"2025-11-20",45644.9375,"2025-11-21",45644.225694444445,"1d, 06:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 4\r\nZ4.43\r\nPériodicité toutes les 4 semaines en alternance avec la zone 9\r\nzone 4 : 3 fois sur l'année\r\nzone 9 : 9 fois sur l'année",null,null,71121,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","71227","Erquelinnes - Montzen",">","BEEZ","PLOMCOT",2025,2025,47,47,"2025-11-20",45644.375,"2025-11-20",45644.520833333336,"1d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite périodique de voie AI43",null,null,71227,"2023-10-26",0,"1,2,3,4,5"]
[null,"Infrabel","56510","Athus - Meuse",">","Y.AUBANGE","VIRTON",2025,2025,47,47,"2025-11-21",45644.25,"2025-11-21",45644.916666666664,"2d, 16:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage - Phase 3\r\nDossier de concertation validé en octobre 2022\r\nUPM:488549",null,null,56510,"2024-01-09",0,"1,2,3,4,5"]
[null,"Infrabel","70019","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2025,2025,47,47,"2025-11-22",45644.333333333336,"2025-11-23",45644.666666666664,"2d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nTCR 507475",null,null,70019,"2024-07-26",0,"5,6"]
[null,"Infrabel","65805","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2025,2025,47,47,"2025-11-22",45644.25,"2025-11-23",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.51 P4\r\n+ Renouvellement CV\r\nTCR: 488097",null,null,65805,"2024-01-05",1,"5,6"]
[null,"Infrabel","72555","Erquelinnes - Montzen",">","Y.VAL-SAINT-LAMBERT","Y.RENORY",2025,2025,47,47,"2025-11-22",45644.3125,"2025-11-22",45644.5,"1d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de la voie L125A YVSL - YRENORY",null,null,72555,"2023-11-03",0,"5,6"]
[null,"Infrabel","71111","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2025,2025,47,48,"2025-11-23",45644.958333333336,"2025-11-24",45644.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nZ7.43",null,null,71111,"2024-02-07",0,"1,2,3,4,5"]
[null,"Infrabel","79592","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.DRIEHOEKSTRAAT",2025,2025,47,47,"2025-11-23",45644.25,"2025-11-23",45644.583333333336,"1d, 08:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-093\r\nLossen/laden Rails - uitgestelde levering ",null,null,79592,"2024-06-26",0,"5,6"]
[null,"Infrabel","80988","Lille - ZeeBrugge","< >","LICHTERVELDE","KORTRIJK",2025,2025,47,47,"2025-11-23",45644.0625,"2025-11-23",45644.208333333336,"1d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-161\r\nR-519534\r\n\r\n\"Buitengebruikstelling van de gevraagde seinhuizen (zie hieronder) - (Computerzaal (CR)) en de bijbehorende EBP-zone waarvoor de volledige stopzetting van het treinverkeer vereist is. \r\nHet schema is aanpasbaar tussen 0.00 uur e",null,null,80988,"2024-09-17",0,"5,6"]
[null,"Infrabel","67048","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2025,2025,48,48,"2025-11-24",45644.958333333336,"2025-11-29",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\nFinitions\r\nUPM: 488789",null,null,67048,"2024-01-10",0,"1,2,3,4,5"]
[null,"Infrabel","70551","Namur - Antwerpen",">","Y.BERCHEM-STADION","ANTWERPEN-CENTRAAL",2025,2025,48,48,"2025-11-24",45644.979166666664,"2025-11-29",45644.1875,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud wissels Y Noord Berchem\r\nHKV",null,null,70551,"2024-01-29",0,"1,2,3,4,5"]
[null,"Infrabel","72184","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2025,2025,48,48,"2025-11-24",45644.96875,"2025-11-29",45644.180555555555,"5d, 05:05h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone 28.25",null,null,72184,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","71244","Namur - Antwerpen","< >","Y.NAZARETH","HEIST-OP-DEN-BERG",2025,2025,48,48,"2025-11-24",45644.996527777781,"2025-11-29",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKM\r\nZBB.23.02",null,null,71244,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","69043","Erquelinnes - Montzen",">","TILLEUR","LIEGE-GUILLEMINS",2025,2025,48,48,"2025-11-24",45644.375,"2025-11-28",45644.625,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien caténaire\r\nPrestation de 05h minimum",null,null,69043,"2023-12-15",0,"1,2,3,4,5"]
[null,"Infrabel","67928","Lille - Charleroi","< >","SILLY","ENGHIEN",2025,2025,48,48,"2025-11-25",45644.020833333336,"2025-11-29",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67928,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","70758","Lille - Antwerpen","< >","Y.OOST BERCHEM","Y.MELSELE",2025,2025,48,48,"2025-11-25",45644.020833333336,"2025-11-29",45644.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud lopend spoor en spoortoestellen\r\nHKM\r\nZ23.22.01",null,null,70758,"2024-11-06",0,"1,2,3,4,5"]
[null,"Infrabel","63898","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","Y.NORD",2025,2025,48,48,"2025-11-26",45644.958333333336,"2025-11-29",45644.208333333336,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi-Central- Phase 1.12\r\nCoupure Type 9 2026\r\nDossier de concertation validé en octobre 2023\r\nTCR 487681",null,null,63898,"2024-03-06",0,"1,2,3,4,5"]
[null,"Infrabel","56509","Athus - Meuse",">","Y.AUBANGE","HALANZY",2025,2025,48,48,"2025-11-28",45644.25,"2025-11-28",45644.916666666664,"2d, 16:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage - Phase 3\r\nDossier de concertation validé en octobre 2022\r\nUPM:488554",null,null,56509,"2024-01-09",0,"1,2,3,4,5"]
[null,"Infrabel","59241","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","GENT-SINT-PIETERS",2025,2025,48,49,"2025-11-29",45644.020833333336,"2025-12-01",45644.1875,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters stap 33 : Indienststelling perronsporen IV+V\r\nPerronsporen I tot VI buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y. West Driehoek Ledeberg\r\nSP B L 50 Gent Sint Pieters -Y West Driehoek Ledeberg\r\nSP A L58/1 Y West Driehoek Le",null,null,59241,"2024-08-14",1,"5,6"]
[null,"Infrabel","70484","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2025,2025,48,48,"2025-11-29",45644.326388888891,"2025-11-29",45644.722222222219,"1d, 09:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen Oost - Antwerpen - Schijnpoort",null,null,70484,"2024-02-14",0,"5,6"]
[null,"Infrabel","80126","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","NAMUR",2025,2025,48,48,"2025-11-30",45644.020833333336,"2025-11-30",45644.229166666664,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"IDS ETCS L2-IL_SE_P018_P019_L125_Namur-Liège_ETCS_RW_LFA\r\nmeewerken niet mogelijk",null,null,80126,"2024-07-26",0,"5,6"]
[null,"Infrabel","71845","Namur - Antwerpen","< >","Y.SCHAERBEEK-GROUPE G","VILVOORDE",2025,2025,49,49,"2025-12-01",45644.958333333336,"2025-12-06",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nHKV",null,null,71845,"2024-01-18",0,"1,2,3,4,5"]
[null,"Infrabel","54817","Lille - Charleroi",">","Y.NORD","CHARLEROI-CENTRAL",2025,2025,49,49,"2025-12-01",45644.979166666664,"2025-12-05",45644.1875,"4d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Grill Charleroi-Sud - Phase 1.13\r\n1.13.1_Nuits 1^2 – 2^3/12/2025\r\n1.13.2_Nuits 3^4 – 4^5/12/2025\r\nTCR 487842",null,null,54817,"2024-02-28",0,"1,2,3,4,5"]
[null,"Infrabel","72739","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","ANTWERPEN-CENTRAAL",2025,2025,49,49,"2025-12-01",45644.979166666664,"2025-12-06",45644.173611111109,"5d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Centraal\r\nuitbreiding van de +1",null,null,72739,"2024-04-22",0,"1,2,3,4,5"]
[null,"Infrabel","73024","Lille - Charleroi",">","HALLE","LOT",2025,2025,49,49,"2025-12-01",45644.9375,"2025-12-06",45644.197916666664,"5d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FH_09 volgens onderhoudskalender Area CE\r\nL96 spoor B + L94 spoor A + L26 sp A\r\nBeschermingssporen BUV: L94 sp B  en L96 Sp A",null,null,73024,"2024-05-23",0,"1,2,3,4,5"]
[null,"Infrabel","77291","Athus - Meuse",">","VONECHE","GEDINNE",2025,2025,49,49,"2025-12-04",45644.333333333336,"2025-12-04",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,77291,"2024-05-27",0,"1,2,3,4,5"]
[null,"Infrabel","70564","Namur - Antwerpen","< >","Y.ARENDSTRAAT","ANTWERPEN-CENTRAAL",2025,2025,49,49,"2025-12-04",45644.986111111109,"2025-12-05",45644.236111111109,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Antwerpen Centraal -1",null,null,70564,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","77522","Athus - Meuse",">","BERTRIX","PALISEUL",2025,2025,49,49,"2025-12-05",45644.333333333336,"2025-12-05",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie\r\nEntretien voie",null,null,77522,"2024-05-27",0,"1,2,3,4,5"]
[null,"Infrabel","70545","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.NOORD BERCHEM",2025,2025,49,50,"2025-12-06",45644.979166666664,"2025-12-08",45644.1875,"1d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud wissels Y Noord Groenenhoek",null,null,70545,"2024-02-01",0,"5,6"]
[null,"Infrabel","53514","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2025,2025,49,49,"2025-12-06",45644.25,"2025-12-07",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.3.53 +  Z9.52 en P4\r\nTCR: 488816",null,null,53514,"2024-01-10",1,"5,6"]
[null,"Infrabel","69357","Namur - Antwerpen","< >","KONTICH-LINT","MECHELEN-NEKKERSPOEL",2025,2025,49,50,"2025-12-06",45644.25,"2025-12-08",45644.201388888891,"2d, 22:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel\r\n+\r\nOnderhoud",null,null,69357,"2024-11-14",1,"5,6"]
[null,"Infrabel","80128","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","NAMUR",2025,2025,49,49,"2025-12-07",45644.020833333336,"2025-12-07",45644.229166666664,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"BACKUP IDS ETCS L2-IL_SE_P018_P019_L125_Namur-Liège_ETCS_RW_LFA\r\nmeewerken niet mogelijk",null,null,80128,"2024-07-26",0,"5,6"]
[null,"Infrabel","79790","Namur - Antwerpen","< >","HEIST-OP-DEN-BERG","Y.OOST DRIEHOEK AARSCHOT",2025,2025,49,49,"2025-12-07",45644.0625,"2025-12-07",45644.104166666664,"1d, 01:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"CR 2025-040\r\nEBP herlading Leuven\r\nindienstname PLP keet M1 \r\nR-513549",null,null,79790,"2024-06-27",0,"5,6"]
[null,"Infrabel","71762","Namur - Antwerpen",">","NAMUR","FLAWINNE",2025,2025,50,50,"2025-12-08",45644.333333333336,"2025-12-08",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voies A et B + maintenance infrastructure + contrôles\r\nTCR 507464",null,null,71762,"2024-07-26",0,"1,2,3,4,5"]
[null,"Infrabel","59301","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,50,50,"2025-12-08",45644.972222222219,"2025-12-12",45644.1875,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n+\r\nDienst onderhoud werkt mee\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters rooster lokaal AW12BH vrij",null,null,59301,"2024-08-14",0,"1,2,3,4,5"]
[null,"Infrabel","65802","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2025,2025,50,50,"2025-12-08",45644.965277777781,"2025-12-13",45644.208333333336,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.51 P3",null,null,65802,"2023-10-05",0,"1,2,3,4,5"]
[null,"Infrabel","73130","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2025,2025,50,50,"2025-12-08",45644.385416666664,"2025-12-08",45644.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,73130,"2024-05-28",0,"1,2,3,4,5"]
[null,"Infrabel","72938","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2025,2025,50,50,"2025-12-09",45644.378472222219,"2025-12-09",45644.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,72938,"2023-11-09",0,"1,2,3,4,5"]
[null,"Infrabel","73254","Athus - Meuse",">","STOCKEM-NORD","ARLON",2025,2025,50,50,"2025-12-09",45644.361111111109,"2025-12-09",45644.527777777781,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie\r\nRq333 : -1sem (fêtes de fin d'année)",null,null,73254,"2024-09-12",0,"1,2,3,4,5"]
[null,"Infrabel","73255","Athus - Meuse",">","HABAY","STOCKEM-NORD",2025,2025,50,50,"2025-12-10",45644.375,"2025-12-10",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie\r\nRq333: -1sem (fêtes de fin d'année)",null,null,73255,"2024-09-12",0,"1,2,3,4,5"]
[null,"Infrabel","77278","Athus - Meuse",">","VONECHE","BEAURAING",2025,2025,50,50,"2025-12-11",45644.333333333336,"2025-12-11",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,77278,"2024-05-27",0,"5,6"]
[null,"Infrabel","67325","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ANTWERPEN-D.S.-RHODESIE",2025,2025,50,50,"2025-12-14",45644.25,"2025-12-14",45644.729166666664,"0d, 11:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhouden sporen, wissels, seinen, sk's,...",null,null,67325,"2024-04-08",1,"5,6"]
[null,"Infrabel","59260","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2025,2025,51,51,"2025-12-15",45644.972222222219,"2025-12-19",45644.1875,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Gent Sint Pieters  Stap 33: Aanleg perronspoor IV+V\r\n\r\nPerronsporen I tot en met VII buiten dienst \r\nTLO L 50E Gent Sint Pieters -Y.West driehoek Ledeberg \r\nSP B L 50 Gent Sint Pieters - Y.West driehoek Ledeberg\r\nTLO L50A/6 Gent Sint Pieters-",null,null,59260,"2024-08-14",0,"1,2,3,4,5"]
[null,"Infrabel","72382","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","TILLEUR",2025,2025,51,51,"2025-12-15",45644.381944444445,"2025-12-15",45644.642361111109,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie L125 AI41",null,null,72382,"2023-10-26",0,"1,2,3,4,5"]
[null,"Infrabel","70573","Namur - Antwerpen","< >","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2025,2025,51,51,"2025-12-16",45644.986111111109,"2025-12-18",45644.236111111109,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Periodiek schouwen van lopend spoor en spoortoestellen van Y Arendstraat",null,null,70573,"2024-01-31",0,"1,2,3,4,5"]
[null,"Infrabel","70498","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","Y.LUCHTBAL",2025,2025,51,51,"2025-12-17",45644.375,"2025-12-17",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y-Holland",null,null,70498,"2024-02-14",0,"1,2,3,4,5"]
[null,"Infrabel","84037","Athus - Meuse",">","LAVAUX","MARBEHAN",2025,2025,51,51,"2025-12-17",45644.361111111109,"2025-12-17",45644.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie\r\nRq333: -1sem (fêtes de fin d'année)",null,null,84037,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","84038","Athus - Meuse",">","NEUFCHATEAU","LAVAUX",2025,2025,51,51,"2025-12-18",45644.368055555555,"2025-12-18",45644.618055555555,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie:\r\nRq333: -1sem (fêtes de fin d'année)",null,null,84038,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","71084","Namur - Antwerpen",">","NAMUR","RHISNES",2025,2025,51,51,"2025-12-19",45644.958333333336,"2025-12-20",45644.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,71084,"2024-12-04",0,"1,2,3,4,5"]
[null,"Infrabel","70638","Namur - Antwerpen","< >","Y.ANTWERPEN-SCHIJNPOORT","LUCHTBAL-ROOSTER S",2025,2025,51,51,"2025-12-19",45644.375,"2025-12-19",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud wissels Y Holland + inrit bundel Q",null,null,70638,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","67285","Athus - Meuse","< >","PALISEUL","BERTRIX",2025,2025,51,52,"2025-12-20",45644.958333333336,"2025-12-22",45644.197916666664,"2d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\nUPM:489394",null,null,67285,"2024-06-21",0,"5,6"]
[null,"Infrabel","84042","Athus - Meuse",">","ARLON","Y.AUTELBAS",2025,2025,51,51,"2025-12-20",45644.361111111109,"2025-12-20",45644.638888888891,"1d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie\r\nRq333: -1sem (fêtes de fin d'année)",null,null,84042,"2024-11-15",0,"5,6"]
[null,"Infrabel","76124","Namur - Antwerpen",">","OTTIGNIES","WAVRE",2025,2025,51,51,"2025-12-20",45644.326388888891,"2025-12-20",45644.652777777781,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Ottignies - Wavre Gare comprise VA/VB\r\nUPM: 528373",null,null,76124,"2024-11-12",0,"5,6"]
[null,"Infrabel","79870","Namur - Antwerpen","< >","RHISNES","MONT-SAINT-GUIBERT",2025,2025,51,52,"2025-12-21",45644.034722222219,"2025-12-22",45644.180555555555,"2d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\n26 - Déroulage Rhisnes- Mont ST Guibert",null,null,79870,"2024-07-05",0,"5,6"]
[null,"Infrabel","73212","Athus - Meuse",">","LUSTIN","JAMBES",2025,2025,51,51,"2025-12-21",45644.385416666664,"2025-12-21",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,73212,"2024-11-14",0,"5,6"]
[null,"Infrabel","76097","Namur - Antwerpen",">","OTTIGNIES","GEMBLOUX",2025,2025,52,52,"2025-12-27",45644.340277777781,"2025-12-27",45644.659722222219,"1d, 07:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite L161 voie A Ottignies - Gembloux",null,null,76097,"2024-04-05",0,"5,6"]
[null,"Infrabel","76426","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2026,2026,1,1,"2026-01-02",45644.326388888891,"2026-01-02",45644.645833333336,"1d, 07:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Visites J10",null,null,76426,"2024-02-27",0,"1,2,3,4,5"]
[null,"Infrabel","82296","Namur - Antwerpen","< >","VILVOORDE","MECHELEN",2026,2026,2,2,"2026-01-05",45644.958333333336,"2026-01-10",45644.204861111109,"5d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud bovenleiding",null,null,82296,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","75683","Lille - Charleroi","< >","Y.JURBISE","MONS",2026,2026,2,2,"2026-01-05",45644.947916666664,"2026-01-10",45644.173611111109,"5d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.5.53 P3 HKV\r\nRQ333: en concomitance L78 Z13.53\r\nPropo : en sem 2",null,null,75683,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","82065","Athus - Meuse",">","PALISEUL","GEDINNE",2026,2026,2,2,"2026-01-06",45644.333333333336,"2026-01-06",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VB\r\nEntretien voie",null,null,82065,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","73259","Athus - Meuse",">","LAVAUX","MARBEHAN",2026,2026,2,2,"2026-01-07",45644.361111111109,"2026-01-07",45644.611111111109,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73259,"2024-09-12",0,"1,2,3,4,5"]
[null,"Infrabel","73018","Namur - Antwerpen",">","MOUSTIER","AUVELAIS",2026,2026,2,3,"2026-01-09",45644.958333333336,"2026-01-12",45644.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"déroulage voie 533 CS2 4\r\n\r\nSAVU avec CTL de nuit - Liée à la CoLT 80085\r\nUPM: 532997",null,null,73018,"2024-12-17",0,"5,6"]
[null,"Infrabel","83837","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2026,2026,2,2,"2026-01-09",45644.333333333336,"2026-01-09",45644.645833333336,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno Z7V\r\n",null,null,83837,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","77709","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2026,2026,2,2,"2026-01-09",45644.388888888891,"2026-01-09",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,77709,"2024-09-30",0,"1,2,3,4,5"]
[null,"Infrabel","73731","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2026,2026,2,3,"2026-01-10",45644.25,"2026-01-12",45644.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement CV entre Fleurus et Lodelinsart",null,null,73731,"2024-04-22",1,"5,6"]
[null,"Infrabel","73262","Athus - Meuse",">","LIBRAMONT","HATRIVAL",2026,2026,2,2,"2026-01-10",45644.375,"2026-01-10",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie",null,null,73262,"2024-09-12",0,"1,2,3,4,5"]
[null,"Infrabel","75327","Lille - Charleroi",">","BRAINE-LE-COMTE","HENNUYERES-GARAGE",2026,2026,2,2,"2026-01-11",45644.333333333336,"2026-01-11",45644.5625,"1d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite diagnostique +S460\r\n",null,null,75327,"2024-03-15",0,"5,6"]
[null,"Infrabel","73388","Athus - Meuse",">","DINANT","YVOIR",2026,2026,2,2,"2026-01-11",45644.385416666664,"2026-01-11",45644.638888888891,"1d, 06:05h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VB (périodicité 6 semaines)",null,null,73388,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","78385","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,3,3,"2026-01-12",45644.958333333336,"2026-01-16",45644.180555555555,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78385,"2024-06-17",0,"1,2,3,4,5"]
[null,"Infrabel","68404","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,3,3,"2026-01-12",45644.979166666664,"2026-01-17",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-486668\r\nMasterplan Gent Sint Pieters: Stap 34+35\r\nAfbraak sporen I+II+III\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters en Y. West Driehoek Led",null,null,68404,"2024-07-09",0,"1,2,3,4,5"]
[null,"Infrabel","70439","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","Y.NORD",2026,2026,3,3,"2026-01-12",45644.9375,"2026-01-17",45644.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Grill Charleroi-Sud - Phase 2.1\r\nCoupure préparatoire ES. Semaine 3 : 12^13 au 17^18/01 de 23h00 à 4h30 (terrassier + élecs)\r\nDossier de concertation validé en octobre 2023\r\nTCR 498074",null,null,70439,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","65238","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","FROYENNES",2026,2026,3,3,"2026-01-12",45644.944444444445,"2026-01-16",45644.243055555555,"4d, 07:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction d’un PS pour supprimer les PN 8 et 10 - Pose des poutres\r\nUPM 530604",null,null,65238,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","73404","Athus - Meuse",">","Y.NEFFE","DINANT",2026,2026,3,3,"2026-01-13",45644.333333333336,"2026-01-13",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,73404,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","81972","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2026,2026,3,3,"2026-01-13",45644.378472222219,"2026-01-13",45644.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,81972,"2024-09-27",0,"1,2,3,4,5"]
[null,"Infrabel","77294","Athus - Meuse",">","VONECHE","GEDINNE",2026,2026,3,3,"2026-01-15",45644.333333333336,"2026-01-15",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,77294,"2024-03-19",0,"1,2,3,4,5"]
[null,"Infrabel","79962","Namur - Antwerpen",">","NAMUR","RHISNES",2026,2026,3,3,"2026-01-16",45644.958333333336,"2026-01-17",45644.21875,"1d, 06:15h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,79962,"2024-12-04",0,"1,2,3,4,5"]
[null,"Infrabel","77975","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2026,2026,3,4,"2026-01-16",45644.979166666664,"2026-01-19",45644.1875,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-511038\r\nVoorbereiding BVL, voor wisselvernieuwing.",null,null,77975,"2024-06-03",1,"5,6"]
[null,"Infrabel","65755","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2026,2026,3,4,"2026-01-16",45644.993055555555,"2026-01-19",45644.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Namur\r\nDossier de concertation validé en octobre 2023\r\nMassification travaux O.A. : Parois rocheuses et stabilisation de talus\r\n+ visites de voies",null,null,65755,"2024-07-15",1,"5,6"]
[null,"Infrabel","82599","Athus - Meuse","< >","Y.NEFFE","BEAURAING",2026,2026,3,4,"2026-01-17",45644.916666666664,"2026-01-19",45644.215277777781,"2d, 07:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance L166.\r\nCTL NSa^Di 22h/05h30 + NDi^Lu 22h10/05h10.\r\nA dupliquer toutes les 2 semaines.\r\nRQ333: la demande n'est pas réaliste en phase 4 (P5)",null,null,82599,"2024-12-02",0,"5,6"]
[null,"Infrabel","77869","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2026,2026,3,4,"2026-01-17",45644.003472222219,"2026-01-19",45644.1875,"2d, 04:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-511691\r\n\r\nP783 perronverhogingen - De Pinte 1/3\r\n",null,null,77869,"2024-06-10",1,"5,6"]
[null,"Infrabel","78387","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,4,4,"2026-01-19",45644.958333333336,"2026-01-24",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78387,"2024-06-07",0,"1,2,3,4,5"]
[null,"Infrabel","77637","Namur - Antwerpen","< >","DENDERMONDE","Y.HEIKE",2026,2026,4,4,"2026-01-19",45644.979166666664,"2026-01-23",45644.1875,"4d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie:\r\nP208 waterhuishouding\r\n+\r\n221331 Goederencorridors tss FDR en FLZ\r\n\r\nR-511495 ",null,null,77637,"2024-06-06",0,"1,2,3,4,5"]
[null,"Infrabel","63672","Lille - Charleroi","< >","HALLE","SAINTES",2026,2026,4,4,"2026-01-19",45644.972222222219,"2026-01-24",45644.180555555555,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende werken afschaffen OW",null,null,63672,"2024-09-24",0,"1,2,3,4,5"]
[null,"Infrabel","67506","Lille - Antwerpen","< >","KORTRIJK","KORTRIJK-RINGLAAN",2026,2026,4,4,"2026-01-19",45644.996527777781,"2026-01-24",45644.184027777781,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-488516 \r\nVoorbereiding - Vernieuwing Y.Bethune\r\nKIROW - Vernieuwing Y.Bethune\r\nOverlegdossier 2026\r\n\r\nBD\r\nL75C SP A+B\r\nL75 SP A+B\r\nL66/1\r\n\r\nGevallen\r\n29950+29936+29935+29938+29928+29929+29947+29932+29948+29934+29958",null,null,67506,"2024-11-04",0,"1,2,3,4,5"]
[null,"Infrabel","83537","Namur - Antwerpen","< >","DENDERMONDE","Y.HEIKE",2026,2026,4,4,"2026-01-20",45644.013888888891,"2026-01-24",45644.194444444445,"5d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,83537,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","75719","Lille - Charleroi","< >","Y.JURBISE","MONS",2026,2026,4,4,"2026-01-20",45644.034722222219,"2026-01-24",45644.177083333336,"5d, 03:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.5.53 P3 HKV \r\nRQ333: incompatible CBP + Tx L94+90C\r\nPropo: sem 4 sans amplitude allongée ou déplacé en 2027",null,null,75719,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","77277","Athus - Meuse",">","BEAURAING","VONECHE",2026,2026,4,4,"2026-01-21",45644.333333333336,"2026-01-21",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,77277,"2024-03-18",0,"5,6"]
[null,"Infrabel","77279","Athus - Meuse",">","VONECHE","BEAURAING",2026,2026,4,4,"2026-01-22",45644.333333333336,"2026-01-22",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,77279,"2024-03-18",0,"5,6"]
[null,"Infrabel","77641","Namur - Antwerpen","< >","DENDERMONDE","LONDERZEEL",2026,2026,4,5,"2026-01-23",45644.979166666664,"2026-01-26",45644.1875,"2d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie:\r\nP208 waterhuishouding\r\n+\r\n221331 Goederencorridors tss FDR en FLZ\r\n\r\nR-511507 ",null,null,77641,"2024-09-20",1,"5,6"]
[null,"Infrabel","78612","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","Y.RENORY",2026,2026,4,5,"2026-01-24",45644.208333333336,"2026-01-26",45644.208333333336,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement RTB courbe Val St Lambert avec adaptation du tracé\r\nUPM 530143",null,null,78612,"2024-11-25",1,"5,6"]
[null,"Infrabel","79504","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2026,2026,4,5,"2026-01-24",45644.25,"2026-01-26",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-521580\r\n\r\nVernieuwen spoorstaven A'Oost Berchem en Y A'schijnpoort",null,null,79504,"2024-10-01",1,"5,6"]
[null,"Infrabel","78388","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,5,5,"2026-01-26",45644.958333333336,"2026-01-31",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78388,"2024-06-07",0,"1,2,3,4,5"]
[null,"Infrabel","82542","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2026,2026,5,5,"2026-01-26",45644.958333333336,"2026-01-31",45644.194444444445,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z73.33.02",null,null,82542,"2024-11-13",0,"1,2,3,4,5"]
[null,"Infrabel","79294","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","Y.RENORY",2026,2026,5,6,"2026-01-26",45644.958333333336,"2026-02-06",45644.208333333336,"11d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage du ballast C75 VA + Contraintes, finitions suite travaux Renouvellement RTB courbe Val St Lambert avec adaptation du tracé\r\nUPM 530154",null,null,79294,"2024-11-25",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","75664","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2026,2026,5,5,"2026-01-26",45644.951388888891,"2026-01-31",45644.180555555555,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 en P3 HKV",null,null,75664,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","83539","Namur - Antwerpen","< >","DENDERMONDE","Y.HEIKE",2026,2026,5,5,"2026-01-26",45644.013888888891,"2026-01-31",45644.194444444445,"6d, 04:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,83539,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","80970","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2026,2026,5,5,"2026-01-26",45644.930555555555,"2026-01-31",45644.177083333336,"5d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.54",null,null,80970,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","76045","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2026,2026,5,5,"2026-01-26",45644.319444444445,"2026-01-26",45644.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie Gembloux gare + maintenance infrastructure + contrôles",null,null,76045,"2024-03-26",0,"1,2,3,4,5"]
[null,"Infrabel","84502","Athus - Meuse",">","HALANZY","SIGNEULX",2026,2026,5,5,"2026-01-28",45644.333333333336,"2026-01-28",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie  B",null,null,84502,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","81833","Athus - Meuse",">","LUSTIN","YVOIR",2026,2026,5,5,"2026-01-29",45644.375,"2026-01-29",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VA (périodicité 6 semaines)",null,null,81833,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","81834","Athus - Meuse",">","YVOIR","LUSTIN",2026,2026,5,5,"2026-01-30",45644.375,"2026-01-30",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VB (périodicité 6 semaines)",null,null,81834,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","74377","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","Y.NORD",2026,2026,5,5,"2026-01-31",45644.958333333336,"2026-02-01",45644.1875,"1d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Grill Charleroi-Sud - Phase 2.6.2\r\nCoupure préparatoire ES. Semaine 5 : 26^27/01 au 31^01/02 de 23h00 à 4h30 (élecs + brigade)\r\nDossier de concertation validé en octobre 2023\r\nTCR 498081",null,null,74377,"2024-11-18",0,"5,6"]
[null,"Infrabel","77989","Namur - Antwerpen","< >","DENDERMONDE","Y.HEIKE",2026,2026,5,5,"2026-01-31",45644.965277777781,"2026-02-01",45644.239583333336,"1d, 06:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"221331 Goederencorridors tss FDR en FLZ\r\nVerwijderen BTS\r\n\r\nR-511512 \r\n",null,null,77989,"2024-09-16",0,"5,6"]
[null,"Infrabel","81822","Athus - Meuse",">","JAMBES","LUSTIN",2026,2026,5,5,"2026-01-31",45644.385416666664,"2026-01-31",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VA",null,null,81822,"2024-11-14",0,"5,6"]
[null,"Infrabel","78390","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,6,6,"2026-02-02",45644.958333333336,"2026-02-06",45644.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78390,"2024-06-07",0,"1,2,3,4,5"]
[null,"Infrabel","63917","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,6,6,"2026-02-02",45644.9375,"2026-02-07",45644.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage de ballast - C75\r\nDossier de concertation\r\nUPM 530611",null,null,63917,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","66699","Namur - Antwerpen","< >","MECHELEN","Y.SCHAERBEEK-GROUPE G",2026,2026,6,6,"2026-02-02",45644.986111111109,"2026-02-06",45644.1875,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517819\r\nSamen met Colt 82287 (fase 4)\r\n\r\n\"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC):               \r\n\r\n+ Vervangen bi-blocs Y.Machelen - Vilvoorde\r\n+\r\nvoorbereiding omvorming SK's 50Hz naar TFSK",null,null,66699,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","64191","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,6,6,"2026-02-02",45644.923611111109,"2026-02-07",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux SI + Voie + Caténaire\r\n+ Maintenance Z02.51 P3\r\nTCR 529110\r\nColt 74054 massifié (Entretien Cat Lobbes - Erquelinnes Fr)",null,null,64191,"2024-12-17",0,"1,2,3,4,5"]
[null,"Infrabel","84552","Athus - Meuse",">","HALANZY","Y.AUBANGE",2026,2026,6,6,"2026-02-05",45644.333333333336,"2026-02-05",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,84552,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","66203","Namur - Antwerpen","< >","FLEURUS","CHARLEROI-OUEST",2026,2026,6,7,"2026-02-06",45644.958333333336,"2026-02-09",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.51 limitée + Travaux signalisation\r\nEn gare de Fleurus: voie III HS",null,null,66203,"2024-08-27",1,"5,6"]
[null,"Infrabel","65756","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2026,2026,6,7,"2026-02-06",45644.993055555555,"2026-02-09",45644.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Namur\r\nCTL de WE mensuel\r\n+ Massification travaux O.A. : Parois rocheuses et stabilisation de talus\r\n+ Déroulage\r\n+ Visite de voie Rhisnes - Namur",null,null,65756,"2024-06-19",1,"5,6"]
[null,"Infrabel","82223","Namur - Antwerpen","< >","Y.DRIEHOEKSTRAAT","ANTWERPEN-D.S.-RHODESIE",2026,2026,6,6,"2026-02-08",45644.3125,"2026-02-08",45644.520833333336,"1d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Antwerpen Noord\r\nUpdate EBP release to last version\r\nBuitendienststellen van de van de volledige overeenkomstige EBP-zone gedurende minimaal 4 uur te bepalen tussen 06.00 uur en 14.00 uur\r\n",null,null,82223,"2024-12-16",0,"5,6"]
[null,"Infrabel","82928","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,7,7,"2026-02-09",45644.958333333336,"2026-02-14",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF",null,null,82928,"2024-10-18",0,"1,2,3,4,5"]
[null,"Infrabel","76134","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2026,2026,7,7,"2026-02-09",45644.333333333336,"2026-02-09",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 117 à 121 + faisceau manage\r\n dans les intervalles le lundi\r\nUPM: 531483",null,null,76134,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","66638","Namur - Antwerpen","< >","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,7,7,"2026-02-09",45644.979166666664,"2026-02-14",45644.194444444445,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517924\r\n\r\nHerelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel",null,null,66638,"2024-08-20",0,"1,2,3,4,5"]
[null,"Infrabel","75818","Lille - Charleroi","< >","JURBISE","ATH",2026,2026,7,7,"2026-02-09",45644.9375,"2026-02-13",45644.229166666664,"4d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massification Maintenance Z7..53+Z13.54 P3\r\nUPM 526888",null,null,75818,"2024-10-29",0,"1,2,3,4,5"]
[null,"Infrabel","66700","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,7,7,"2026-02-09",45644.986111111109,"2026-02-13",45644.1875,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517850\r\n\r\n\"Herelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC):",null,null,66700,"2024-10-24",0,"1,2,3,4,5"]
[null,"Infrabel","70908","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,7,7,"2026-02-09",45644.923611111109,"2026-02-14",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux SI + Voie + Caténaire\r\nTCR 529153",null,null,70908,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","82053","Athus - Meuse",">","STRAIMONT","BERTRIX",2026,2026,7,7,"2026-02-10",45644.333333333336,"2026-02-10",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,82053,"2024-09-27",0,"1,2,3,4,5"]
[null,"Infrabel","83814","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2026,2026,7,7,"2026-02-10",45644.375,"2026-02-12",45644.645833333336,"3d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud bovenleiding spoor A of B",null,null,83814,"2024-12-13",0,"1,2,3,4,5"]
[null,"Infrabel","74003","Namur - Antwerpen",">","MOUSTIER","AUVELAIS",2026,2026,7,8,"2026-02-13",45644.958333333336,"2026-02-16",45644.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Déroulage transversal L130 VA + CTL de nuit dans BT par protection\r\n\r\nSAVU avec CTL de nuit - Liée à la CoLT 80086\r\nUPM: 532990",null,null,74003,"2024-12-17",0,"5,6"]
[null,"Infrabel","63086","Athus - Meuse","< >","CINEY","MARLOIE",2026,2026,7,8,"2026-02-13",45644.986111111109,"2026-02-16",45644.180555555555,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS de Haversin - BK 102.161\r\nUPM 530610",null,null,63086,"2024-11-28",1,"5,6"]
[null,"Infrabel","78590","Lille - Antwerpen",">","GENT-SINT-PIETERS","DEINZE",2026,2026,7,7,"2026-02-14",45644.940972222219,"2026-02-15",45644.003472222219,"1d, 01:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-513230\r\nI-AM.A3.CAM vervangen rijdraad Spoor B Gent - Deinze\r\n Nacht R67:\r\nSp B buitendienst van R6 22u35 tot R7 06u05\r\nSp A buitendienst R7 van 00u05 tot 05u30\r\n\r\n24/09/2024: Instructie I-CBE 33:  TLO nacht en DOES  dienen gesplitst te worden.\r\nDOES ",null,null,78590,"2024-09-25",0,"5,6"]
[null,"Infrabel","81914","Lille - Antwerpen",">","GENT-SINT-PIETERS","DEINZE",2026,2026,7,7,"2026-02-15",45644.229166666664,"2026-02-15",45644.253472222219,"1d, 00:35h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-513230\r\nI-AM.A3.CAM vervangen rijdraad Spoor B Gent - Deinze\r\n Nacht R67:\r\nSp B buitendienst van R6 22u35 tot R7 06u05\r\nSp A buitendienst R7 van 00u05 tot 05u30\r\n\r\n24/09/2024: Instructie I-CBE 33:  TLO nacht en DOES  dienen gesplitst te worden.\r\nDOES ",null,null,81914,"2024-09-25",0,"5,6"]
[null,"Infrabel","64193","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,8,8,"2026-02-16",45644.958333333336,"2026-02-20",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre\r\nPréparation Travaux caténaire\r\nDossier de concertation validé en octobre 2023\r\n+ Luttre SNCB Ascenceurs - Pose des drains et remblayage\r\nFerraillage et coffrage murs de gaine sur quai\r\nBétonnage murs gaines sur niveau quai et",null,null,64193,"2024-10-10",0,"1,2,3,4,5"]
[null,"Infrabel","79295","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","Y.RENORY",2026,2026,8,8,"2026-02-16",45644.958333333336,"2026-02-20",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Bourrage de révision, contraintes, finitions,...\r\nUPM 530156",null,null,79295,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","82934","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,8,8,"2026-02-16",45644.958333333336,"2026-02-21",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF",null,null,82934,"2024-10-18",0,"1,2,3,4,5"]
[null,"Infrabel","68409","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,8,8,"2026-02-16",45644.979166666664,"2026-02-21",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-512326\r\n\r\nMasterplan Gent Sint Pieters: Stap 34+35\r\nAfbraak sporen I+II+III\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters en Y. West Driehoek L",null,null,68409,"2024-06-13",0,"1,2,3,4,5"]
[null,"Infrabel","75931","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2026,2026,8,8,"2026-02-16",45644.965277777781,"2026-02-21",45644.208333333336,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15. 51\r\nP3 HKV\r\nTronçon Allongé",null,null,75931,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","82114","Athus - Meuse",">","CINEY","MARLOIE",2026,2026,8,8,"2026-02-16",45644.180555555555,"2026-02-16",45644.215277777781,"1d, 00:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du PS de Haversin - BK 102.161\r\nUPM 530610",null,null,82114,"2024-11-28",0,"5,6"]
[null,"Infrabel","83763","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2026,2026,8,8,"2026-02-16",45644.947916666664,"2026-02-21",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z05.32\r\nInclusief Eeklo alle perronsporen (I, II en III) \r\n",null,null,83763,"2024-12-04",0,"1,2,3,4,5"]
[null,"Infrabel","67939","Lille - Charleroi","< >","SILLY","ENGHIEN",2026,2026,8,8,"2026-02-17",45644.020833333336,"2026-02-20",45644.208333333336,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67939,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","84057","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2026,2026,8,8,"2026-02-17",45644.34375,"2026-02-17",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,84057,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","83354","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2026,2026,8,8,"2026-02-18",45644.354166666664,"2026-02-18",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Schouwen lopend spoor A/B",null,null,83354,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","83626","Lille - ZeeBrugge",">","BRUGGE-ROOSTER E","ZEDELGEM-ROOSTER E/G",2026,2026,8,8,"2026-02-19",45644.354166666664,"2026-02-19",45644.520833333336,"1d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Schouwing Lopend spoor A/B G-J.7/GX-J.7 tot DX-E.7/D-E.7",null,null,83626,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","78546","Namur - Antwerpen","< >","LEUVEN","SINT-JORIS-WEERT",2026,2026,8,9,"2026-02-20",45644.958333333336,"2026-02-23",45644.215277777781,"2d, 06:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Railvernieuwingen (slechtere toestand rails) + groot onderhoud: ",null,null,78546,"2024-09-17",1,"5,6"]
[null,"Infrabel","71534","Lille - Charleroi",">","Y.JURBISE","MONS",2026,2026,8,11,"2026-02-20",45644.958333333336,"2026-03-09",45644.208333333336,"17d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Chantier gare de Jurbise  - Renouvellement traverses-ballast des voies 3, 4 et 5\r\nPhase 1\r\nDossier de concertation validé en octobre 2023",null,null,71534,"2024-01-30",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","63962","Lille - Charleroi","< >","JURBISE","Y.LENS",2026,2026,8,11,"2026-02-20",45644.9375,"2026-03-09",45644.208333333336,"16d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Chantier gare de Jurbise  - Renouvellement traverses-ballast des voies 3, 4 et 5\r\nPhase 1\r\nDossier de concertation validé en octobre 2023\r\nUPM 526810",null,null,63962,"2024-10-29",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","76039","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2026,2026,8,8,"2026-02-21",45644.986111111109,"2026-02-22",45644.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\nUPM: 527917",null,null,76039,"2024-11-06",1,"5,6"]
[null,"Infrabel","66340","Namur - Antwerpen","< >","Y.SINT-MARIABURG","ESSEN",2026,2026,8,9,"2026-02-21",45644.25,"2026-02-23",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517225\r\n\r\nVervangen wisselonderdelen\r\n+ overwegen",null,null,66340,"2024-08-12",1,"5,6"]
[null,"Infrabel","84078","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2026,2026,8,8,"2026-02-22",45644.388888888891,"2026-02-22",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB",null,null,84078,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","84029","Athus - Meuse",">","DINANT","Y.NEFFE",2026,2026,9,9,"2026-02-23",45644.333333333336,"2026-02-23",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites VA",null,null,84029,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","68410","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,9,9,"2026-02-23",45644.979166666664,"2026-02-28",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-512332\r\n\r\nMasterplan Gent Sint Pieters: Stap 34+35\r\nAfbraak sporen I+II+III\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Sint Pieters en Y. West Driehoek L",null,null,68410,"2024-06-13",0,"1,2,3,4,5"]
[null,"Infrabel","84030","Athus - Meuse",">","Y.NEFFE","DINANT",2026,2026,9,9,"2026-02-24",45644.333333333336,"2026-02-24",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,84030,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","55846","Lille - Charleroi","< >","MOUSCRON","HERSEAUX",2026,2026,9,10,"2026-02-24",45644.9375,"2026-03-02",45644.173611111109,"5d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\nPhase 2 - CTL en continu pour la démolition des tabliers et de la pile centrale\r\nPhase 2.2 - travaux au niveau de la 2è travée",null,null,55846,"2023-10-03",1,"1,2,3,4,5,6,7"]
[null,"Infrabel","83509","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2026,2026,9,9,"2026-02-24",45644.003472222219,"2026-02-28",45644.190972222219,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud",null,null,83509,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","82075","Athus - Meuse",">","BEAURAING","VONECHE",2026,2026,9,9,"2026-02-25",45644.333333333336,"2026-02-25",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,82075,"2024-11-19",0,"5,6"]
[null,"Infrabel","67510","Lille - Antwerpen",">","KORTRIJK-RINGLAAN","KORTRIJK",2026,2026,9,10,"2026-02-27",45644.958333333336,"2026-03-02",45644.197916666664,"2d, 05:45h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"R-488528\r\nAfwerking Vernieuwen Y Bethune\r\nOverlegdossier 2026\r\n\r\nBD\r\nL75 SP B\r\n\r\nGevallen\r\n29928+29958",null,null,67510,"2024-11-04",0,"5,6"]
[null,"Infrabel","63235","Namur - Antwerpen",">","OTTIGNIES","OTTIGNIES",2026,2026,9,9,"2026-02-27",45644.333333333336,"2026-02-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement P93 - extension côté Ottignies\r\nUPM: 530252",null,null,63235,"2024-11-26",0,"1,2,3,4,5"]
[null,"Infrabel","78545","Namur - Antwerpen","< >","LEUVEN","SINT-JORIS-WEERT",2026,2026,9,10,"2026-02-27",45644.996527777781,"2026-03-02",45644.215277777781,"2d, 05:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517982\r\n\r\nRailvernieuwingen (slechtere toestand rails) + groot onderhoud: ",null,null,78545,"2024-08-20",1,"5,6"]
[null,"Infrabel","79363","Erquelinnes - Montzen",">","HUY","STATTE",2026,2026,9,10,"2026-02-28",45644.25,"2026-03-02",45644.208333333336,"2d, 23:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA au CSV Huy. \r\n",null,null,79363,"2024-08-07",0,"5,6"]
[null,"Infrabel","63868","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2026,2026,10,10,"2026-03-02",45644.958333333336,"2026-03-06",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z3.51 + Travaux signalisation\r\nRQ333 : demande 4 nuits ald 5 cf conflit CBP",null,null,63868,"2024-08-28",0,"1,2,3,4,5"]
[null,"Infrabel","68437","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2026,2026,10,10,"2026-03-02",45644.965277777781,"2026-03-06",45644.201388888891,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"TCR 511142\r\n\r\nBlankenberge wissels - opbreken oude wissels plaatsen wisselverbinding\r\ngevallen 29533-2535-29536-29534\r\n\r\n*R5/R6 in weekend TLO",null,null,68437,"2024-06-04",0,"1,2,3,4,5"]
[null,"Infrabel","55866","Lille - Antwerpen",">","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,10,10,"2026-03-02",45644.25,"2026-03-06",45644.666666666664,"5d, 10:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nDossier de concertation\r\n\r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pou",null,null,55866,"2023-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","67512","Lille - Antwerpen","< >","KORTRIJK","KORTRIJK-RINGLAAN",2026,2026,10,10,"2026-03-02",45644.996527777781,"2026-03-07",45644.184027777781,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-488542\r\nAfwerking - Vernieuwing Y.Bethune\r\nOverlegdossier 2026\r\n\r\nBD\r\nL75C SP A+B\r\nL75 SP A+B\r\nL66/1\r\n\r\nGevallen\r\n29950+29936+29935+29938+29928+29929+29947+29932+29948+29934+29958",null,null,67512,"2024-11-04",0,"1,2,3,4,5"]
[null,"Infrabel","81736","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2026,2026,10,10,"2026-03-02",45644.947916666664,"2026-03-07",45644.197916666664,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z04.35.01 HKV\r\n\r\ninclusief FLC perronsporen III tot V ",null,null,81736,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","65818","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,10,10,"2026-03-02",45644.923611111109,"2026-03-07",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z02.51 P3",null,null,65818,"2024-11-26",0,"1,2,3,4,5"]
[null,"Infrabel","82131","Lille - Antwerpen","< >","LOKEREN","GENT-DAMPOORT",2026,2026,10,10,"2026-03-03",45644.020833333336,"2026-03-07",45644.184027777781,"5d, 03:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nRooster Lokeren kant Gent NIET Inbegrepen (reeds gedeeltelijk buiten dienst in zone) \r\nRooster Gent Dampoort Kant Antwerpen inbegrepen",null,null,82131,"2024-12-03",0,"1,2,3,4,5"]
[null,"Infrabel","75049","Athus - Meuse","< >","FLORENVILLE","VIRTON",2026,2026,10,11,"2026-03-06",45644.958333333336,"2026-03-09",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Nouvelle voie d'évitement de 750m - St-Vincent.\r\n- Déroulage nouvelle caténaire et modificaiton de sectionnement\r\nUPM: 528411\r\nRQ333: intégrer les visites VA+VB Florenville - St-V. ok ? ",null,null,75049,"2024-11-12",1,"5,6"]
[null,"Infrabel","63924","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,10,11,"2026-03-06",45644.9375,"2026-03-09",45644.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Criblage de ballast - C75\r\nDossier de concertation\r\nUPM 530652",null,null,63924,"2024-11-28",1,"5,6"]
[null,"Infrabel","79354","Erquelinnes - Montzen",">","HUY","STATTE",2026,2026,10,11,"2026-03-07",45644.25,"2026-03-09",45644.208333333336,"2d, 23:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA au CSV Huy",null,null,79354,"2024-08-07",0,"5,6"]
[null,"Infrabel","66341","Namur - Antwerpen","< >","Y.SINT-MARIABURG","ESSEN",2026,2026,10,11,"2026-03-08",45644.034722222219,"2026-03-09",45644.201388888891,"2d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517239\r\n\r\nkleine vernieuwingen",null,null,66341,"2024-08-12",0,"5,6"]
[null,"Infrabel","78395","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,11,11,"2026-03-09",45644.958333333336,"2026-03-14",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78395,"2024-06-07",0,"1,2,3,4,5"]
[null,"Infrabel","81716","Lille - ZeeBrugge","< >","LICHTERVELDE","KORTRIJK",2026,2026,11,11,"2026-03-09",45644.965277777781,"2026-03-14",45644.1875,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z04.35 HKV\r\n\r\nInclusief perronspoor II te Menen, exclusief perronspoor I te Menen \r\nNavette tussen Poperinge en Menen moet mogelijk zijn via L69 Enk. baanvak FPP - Komen + Spoor A L69 \r\nInclusief perronspoor I tot IV te LK \r\nInclusief per",null,null,81716,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","79567","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,11,11,"2026-03-09",45644.993055555555,"2026-03-14",45644.177083333336,"5d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,79567,"2024-06-07",0,"1,2,3,4,5"]
[null,"Infrabel","76046","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2026,2026,11,11,"2026-03-09",45644.319444444445,"2026-03-09",45644.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie Gembloux gare + maintenance infrastructure + contrôles",null,null,76046,"2024-03-26",0,"1,2,3,4,5"]
[null,"Infrabel","67442","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2026,2026,11,11,"2026-03-10",45644.375,"2026-03-10",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517240\r\n\r\nTOS 2221 + TOS 2222 + TOS SI: Werken wissels Antwerpen Oost - Antwerpen - Schijnpoort (schouwen - metingen - smeren - kleine herstellingen), periodiciteit: 1 weekdag per 4 weken, buitendienststelling van 9:00u tot 15:00u. Te voorziene datums",null,null,67442,"2024-08-12",0,"1,2,3,4,5"]
[null,"Infrabel","82736","Namur - Antwerpen","< >","MERELBEKE-ROOSTER S","Y.OOST DRIEHOEK LEDEBERG",2026,2026,11,11,"2026-03-12",45644.395833333336,"2026-03-13",45644.625,"2d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"reservatie onderhoud \r\ndagdienst zone 2\r\nL50E SP A Merelbeke rooster S sein EX-S.6 tot Y Oost Driehoek Ledeberg 10AR niet inbegrepen\r\nL50E SP B Merelbeke rooster S sein F-S.6 tot Y Oost Driehoek Ledeberg 03XR niet inbegrepen\r\nBVL: niet mogelijk overdag",null,null,82736,"2024-12-04",0,"1,2,3,4,5"]
[null,"Infrabel","63964","Lille - Charleroi","< >","JURBISE","Y.LENS",2026,2026,11,12,"2026-03-13",45644.9375,"2026-03-16",45644.208333333336,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Chantier gare de Jurbise  - Renouvellement traverses-ballast des voies 3, 4 et 5\r\nPhase 2\r\nDossier de concertation validé en octobre 2023\r\nUPM 526815",null,null,63964,"2024-10-29",1,"5,6"]
[null,"Infrabel","83957","Athus - Meuse",">","LUSTIN","JAMBES",2026,2026,11,11,"2026-03-13",45644.385416666664,"2026-03-13",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VB\r\nRQ333: en R5 (ald R7) ok ? ",null,null,83957,"2024-11-14",0,"5,6"]
[null,"Infrabel","82938","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,11,11,"2026-03-14",45644.208333333336,"2026-03-15",45644.958333333336,"2d, 18:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF",null,null,82938,"2024-10-18",1,"5,6"]
[null,"Infrabel","76040","Namur - Antwerpen","< >","NAMUR","AUVELAIS",2026,2026,11,11,"2026-03-14",45644.986111111109,"2026-03-15",45644.618055555555,"1d, 15:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mini CTL pour maintenance globale  L130  + L130/1 + L144\r\n+ Visite de Voie Auvelais - Flawinne VB L 130 en R7\r\nUPM: 527919",null,null,76040,"2024-11-06",1,"5,6"]
[null,"Infrabel","79355","Erquelinnes - Montzen",">","HUY","STATTE",2026,2026,11,12,"2026-03-14",45644.25,"2026-03-16",45644.208333333336,"2d, 23:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA au CSV Huy. \r\n",null,null,79355,"2024-08-07",0,"5,6"]
[null,"Infrabel","78396","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,12,12,"2026-03-16",45644.958333333336,"2026-03-20",45644.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78396,"2024-06-07",0,"1,2,3,4,5"]
[null,"Infrabel","69124","Namur - Antwerpen","< >","OTTIGNIES","WAVRE",2026,2026,12,12,"2026-03-16",45644.958333333336,"2026-03-20",45644.222222222219,"4d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"chantier RER - dépose liaison L139 + raccordement chantier\r\nUPM: 530622",null,null,69124,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","82126","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","SINT-NIKLAAS",2026,2026,12,12,"2026-03-16",45644.958333333336,"2026-03-21",45644.1875,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z23.22.02",null,null,82126,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","72265","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2026,2026,12,12,"2026-03-16",45644.965277777781,"2026-03-20",45644.208333333336,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z03.51\r\nRQ333 : nuit ven/sa nok",null,null,72265,"2024-06-20",0,"1,2,3,4,5"]
[null,"Infrabel","69362","Lille - Charleroi","< >","HALLE","Y.NOORD HALLE",2026,2026,12,12,"2026-03-16",45644.993055555555,"2026-03-21",45644.180555555555,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels rooster N kant FBMZ: Fase 1.1 Aw's 52AN+53BN voorbereiding",null,null,69362,"2024-09-27",0,"1,2,3,4,5"]
[null,"Infrabel","80971","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2026,2026,12,12,"2026-03-16",45644.930555555555,"2026-03-21",45644.180555555555,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z1.54\r\nRq333: incompatible CBP",null,null,80971,"2024-09-09",0,"1,2,3,4,5"]
[null,"Infrabel","82139","Lille - Antwerpen","< >","SINT-NIKLAAS","LOKEREN",2026,2026,12,12,"2026-03-17",45644.020833333336,"2026-03-21",45644.184027777781,"5d, 03:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud\r\nRooster Sint Niklaas kant Gent Inbegrepen\r\nRooster Lokeren Kant Antwerpen inbegrepen",null,null,82139,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","83989","Athus - Meuse",">","LUSTIN","YVOIR",2026,2026,12,12,"2026-03-19",45644.375,"2026-03-19",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VA (périodicité 6 semaines)",null,null,83989,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","64295","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,12,13,"2026-03-20",45644.958333333336,"2026-03-23",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre \r\nRenouvellement des voies III - IV  - V en gare de Luttre\r\nAménagement Aw L117\r\nDossier de concertation validé en octobre 2023\r\nCorrélation ID 64292 + 79740\r\nTCR 527048\r\n",null,null,64295,"2024-10-30",1,"5,6"]
[null,"Infrabel","63919","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,12,13,"2026-03-20",45644.9375,"2026-03-23",45644.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Criblage de ballast - C75\r\nDossier de concertation\r\nUPM 530669",null,null,63919,"2024-11-28",1,"5,6"]
[null,"Infrabel","65057","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2026,2026,12,12,"2026-03-21",45644.958333333336,"2026-03-22",45644.208333333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 3.10.1\r\nCoupure Type 8 de 2026\r\nUPM: 529905",null,null,65057,"2024-11-22",0,"5,6"]
[null,"Infrabel","76126","Namur - Antwerpen",">","OTTIGNIES","WAVRE",2026,2026,12,12,"2026-03-21",45644.326388888891,"2026-03-21",45644.652777777781,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Ottignies - Wavre Gare comprise VA/VB\r\nUPM: 528360\r\n\r\n",null,null,76126,"2024-11-12",0,"5,6"]
[null,"Infrabel","82269","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2026,2026,12,13,"2026-03-22",45644.03125,"2026-03-23",45644.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud bovenleiding\r\nmin 14 prestaties, gespreid over het jaar,\r\nsp A of sp B\r\nHKV\r\nNacht R6^R7 van 00u45 tot 06u00",null,null,82269,"2024-11-14",0,"5,6"]
[null,"Infrabel","81915","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2026,2026,12,12,"2026-03-22",45644.003472222219,"2026-03-22",45644.229166666664,"1d, 05:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-513250\r\nI-AM.A3.CAM vervangen rijdraad Spoor B Gent - Deinze\r\n Nacht R67:\r\nSp B buitendienst van R6 22u35 tot R7 06u05\r\nSp A buitendienst R7 van 00u05 tot 05u30\r\n\r\n24/09/2024: Instructie I-CBE 33:  TLO nacht en DOES  dienen gesplitst te worden.\r\nDOES ",null,null,81915,"2024-09-25",0,"5,6"]
[null,"Infrabel","67270","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BRUGGE",2026,2026,12,13,"2026-03-22",45644.003472222219,"2026-03-23",45644.003472222219,"1d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-497914\r\nWeekend TLO 24u \r\ndoorsteek rijdraad vervangen+compacte I's plaatsen\r\n\r\nL66 SP A+B Brugge Rooster E tot Brugge SP VIII-VII inbegrepen\r\nL50D SP A Brugge Rooster E tot Brugge SP VI\r\nL51 SP A+B Brugge SP VIII-VII inbegrepen tot Y Blauwe Toren nie",null,null,67270,"2024-12-11",1,"5,6"]
[null,"Infrabel","82940","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,13,13,"2026-03-23",45644.958333333336,"2026-03-28",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF",null,null,82940,"2024-10-18",0,"1,2,3,4,5"]
[null,"Infrabel","70916","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,13,13,"2026-03-23",45644.9375,"2026-03-28",45644.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage de ballast - C75\r\nDossier de concertation\r\nUPM 530671",null,null,70916,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","80966","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2026,2026,13,13,"2026-03-23",45644.944444444445,"2026-03-28",45644.173611111109,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.54\r\n+ Maintenance Z7.54 P3 HKM",null,null,80966,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","72210","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,13,13,"2026-03-23",45644.354166666664,"2026-03-27",45644.645833333336,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre \r\nRenouvellement des voies III - IV  - V en gare de Luttre\r\nAménagement Aw L117\r\nDossier de concertation validé en octobre 2023\r\nTCR 523987",null,null,72210,"2024-10-15",0,"1,2,3,4,5"]
[null,"Infrabel","67944","Lille - Charleroi","< >","SILLY","ENGHIEN",2026,2026,13,13,"2026-03-24",45644.020833333336,"2026-03-28",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67944,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","63869","Lille - Charleroi","< >","CHARLEROI-CENTRAL","Y.NORD",2026,2026,13,14,"2026-03-27",45644.958333333336,"2026-03-30",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi-Central- Phase 2.11\r\nDossier de concertation validé en octobre 2023\r\nTCR498396",null,null,63869,"2024-11-25",1,"5,6"]
[null,"Infrabel","73021","Namur - Antwerpen",">","MOUSTIER-GARAGE","AUVELAIS",2026,2026,13,14,"2026-03-27",45644.993055555555,"2026-03-30",45644.208333333336,"2d, 05:10h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Déroulage L130 VA \r\nUPM: 533005",null,null,73021,"2024-12-17",0,"5,6"]
[null,"Infrabel","67689","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,13,14,"2026-03-28",45644.208333333336,"2026-03-30",45644.194444444445,"2d, 23:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,67689,"2024-06-19",1,"5,6"]
[null,"Infrabel","78879","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","WATERMAEL",2026,2026,13,14,"2026-03-28",45644.003472222219,"2026-03-30",45644.201388888891,"3d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing station Etterbeek B-ST: Sporen 1-2-3-4\r\nNacht vrijdag/zaterdag tussen 00u05 en 05u20\r\nNacht zaterdag/zondag tussen 00u40 en 05u20\r\nNacht zondag/maandag tussen 00u40 en 04u50",null,null,78879,"2024-09-27",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","78400","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,14,14,"2026-03-30",45644.958333333336,"2026-04-03",45644.180555555555,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78400,"2024-06-17",0,"1,2,3,4,5"]
[null,"Infrabel","61842","Lille - Antwerpen",">","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,14,14,"2026-03-30",45644.25,"2026-04-03",45644.666666666664,"5d, 10:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nDossier de concertation\r\n\r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pou",null,null,61842,"2023-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","84058","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2026,2026,14,14,"2026-03-30",45644.347222222219,"2026-03-30",45644.638888888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA (périodicité 3 semaines)",null,null,84058,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","84059","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2026,2026,14,14,"2026-03-31",45644.34375,"2026-03-31",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,84059,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","84373","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2026,2026,14,14,"2026-04-02",45644.333333333336,"2026-04-02",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,84373,"2024-12-04",0,"5,6"]
[null,"Infrabel","79757","Athus - Meuse",">","CINEY","MARLOIE",2026,2026,14,14,"2026-04-03",45644.916666666664,"2026-04-03",45644.986111111109,"1d, 01:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3:\r\nsuppression des PN de Chapois et Leignon + PS d'Haversin\r\nDossier de concertation validé en octobre 2023\r\n+ possibilité de travaux sur OA pour le tronçon Haversin Marloie\r\nUPM 530612",null,null,79757,"2024-11-28",0,"5,6"]
[null,"Infrabel","63939","Lille - Antwerpen","< >","MOUSCRON-FRONTIERE","MOUSCRON",2026,2026,14,15,"2026-04-03",45644.965277777781,"2026-04-07",45644.166666666664,"3d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mouscron - Tourcoing LRS",null,null,63939,"2023-10-19",1,"5,6"]
[null,"Infrabel","76740","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","CHATELET-GRIL EST",2026,2026,14,14,"2026-04-04",45644.25,"2026-04-05",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10.51   P4 + Visite du pont Champeau L130 VA (Colt 55496)\r\nUPM: 528627",null,null,76740,"2024-11-13",1,"5,6"]
[null,"Infrabel","67690","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,14,15,"2026-04-04",45644.003472222219,"2026-04-07",45644.194444444445,"3d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,67690,"2024-08-28",1,"5,6"]
[null,"Infrabel","84031","Athus - Meuse",">","DINANT","Y.NEFFE",2026,2026,15,15,"2026-04-06",45644.333333333336,"2026-04-06",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites VA",null,null,84031,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","79579","Athus - Meuse","< >","ROCHEFORT-JEMELLE","GRUPONT",2026,2026,15,50,"2026-04-06",45644.965277777781,"2026-12-13",45644.201388888891,"251d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3:\r\nTronçon Jemelle Grupont\r\nDossier de concertation validé en ocotbre 2023\r\nSAVU de jour en continu et CTL de nuit en semaine\r\nSIRU à réaliser\r\nTravaux préparatoires et MES de CV Jade entre Jemelle et Grupont avec des parcours machine seron",null,null,79579,"2024-12-11",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","84032","Athus - Meuse",">","Y.NEFFE","DINANT",2026,2026,15,15,"2026-04-07",45644.333333333336,"2026-04-07",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,84032,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","67946","Lille - Charleroi","< >","SILLY","ENGHIEN",2026,2026,15,15,"2026-04-07",45644.020833333336,"2026-04-11",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67946,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","79570","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,15,15,"2026-04-07",45644.993055555555,"2026-04-10",45644.177083333336,"3d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,79570,"2024-06-07",0,"1,2,3,4,5"]
[null,"Infrabel","67443","Namur - Antwerpen","< >","ANTWERPEN-CENTRAAL","Y.HOLLAND",2026,2026,15,15,"2026-04-07",45644.375,"2026-04-07",45644.625,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517242\r\n\r\nTOS 2221 + TOS 2222 + TOS SI: Werken wissels Antwerpen Oost - Antwerpen - Schijnpoort (schouwen - metingen - smeren - kleine herstellingen), periodiciteit: 1 weekdag per 4 weken, buitendienststelling van 9:00u tot 15:00u. Te voorziene datums",null,null,67443,"2024-08-12",0,"1,2,3,4,5"]
[null,"Infrabel","82074","Athus - Meuse",">","BEAURAING","VONECHE",2026,2026,15,15,"2026-04-08",45644.333333333336,"2026-04-08",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,82074,"2024-09-27",0,"5,6"]
[null,"Infrabel","79967","Namur - Antwerpen",">","NAMUR","RHISNES",2026,2026,15,15,"2026-04-09",45644.9375,"2026-04-10",45644.225694444445,"1d, 06:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 4\r\nZ4.43\r\nPériodicité toutes les 4 semaines en alternance avec la zone 9\r\nzone 4 : 3 fois sur l'année\r\nzone 9 : 9 fois sur l'année",null,null,79967,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","75569","Athus - Meuse",">","LUSTIN","DINANT",2026,2026,15,16,"2026-04-10",45644.958333333336,"2026-04-13",45644.180555555555,"2d, 05:20h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien AS, traitement zone boueuse\r\nSAVU + CTL nuits\r\nUPM : 527533",null,null,75569,"2024-11-04",0,"5,6"]
[null,"Infrabel","65758","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2026,2026,15,16,"2026-04-10",45644.993055555555,"2026-04-13",45644.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Namur",null,null,65758,"2024-08-28",1,"5,6"]
[null,"Infrabel","61825","Namur - Antwerpen",">","TAMINES","CHATELET-GRIL EST",2026,2026,15,16,"2026-04-11",45644.9375,"2026-04-13",45644.229166666664,"2d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Châtelet Livraison AS 14J à 16J + 38J à 42J via grue KIROW\r\nBesoin minimum 7h pendant 2 nuits\r\nPhase 5.0\r\nUPM: 529921",null,null,61825,"2024-11-22",0,"5,6"]
[null,"Infrabel","67691","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,15,16,"2026-04-11",45644.003472222219,"2026-04-13",45644.194444444445,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,67691,"2024-06-19",1,"5,6"]
[null,"Infrabel","78592","Lille - Antwerpen",">","GENT-SINT-PIETERS","DEINZE",2026,2026,15,15,"2026-04-11",45644.940972222219,"2026-04-12",45644.003472222219,"1d, 01:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-512362\r\n\r\nI-AM.A3.CAM vervangen rijdraad Spoor B Gent - Deinze\r\n Nacht R67:\r\nSp B buitendienst van R6 22u35 tot R7 06u05\r\nSp A buitendienst R7 van 00u05 tot 05u30\r\n\r\n24/09/2024: Instructie I-CBE 33:  TLO nacht en DOES  dienen gesplitst te worden.\r\nDOE",null,null,78592,"2024-09-25",0,"5,6"]
[null,"Infrabel","78595","Lille - Antwerpen",">","GENT-SINT-PIETERS","DEINZE",2026,2026,15,16,"2026-04-12",45644.982638888891,"2026-04-13",45644.184027777781,"1d, 04:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-512368\r\n\r\nI-AM.A3.CAM vervangen rijdraad\r\nSpoor B Gent - Deinze\r\n   SU55-65 (5/26-6/26)\r\n   SU65-67 (6/22-6-42\r\n   SU67-76 (6/38-7/22)",null,null,78595,"2024-06-13",0,"5,6"]
[null,"Infrabel","84398","Athus - Meuse",">","VIRTON","SIGNEULX",2026,2026,16,16,"2026-04-13",45644.333333333336,"2026-04-13",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,84398,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","79017","Namur - Antwerpen","< >","MECHELEN","VILVOORDE",2026,2026,16,16,"2026-04-13",45644.986111111109,"2026-04-18",45644.1875,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517821\r\n\r\nvoorbereiding omvorming SK's 50Hz naar TFSK",null,null,79017,"2024-08-19",0,"1,2,3,4,5"]
[null,"Infrabel","84604","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2026,2026,16,16,"2026-04-13",45644.385416666664,"2026-04-13",45644.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,84604,"2024-12-09",0,"1,2,3,4,5"]
[null,"Infrabel","72214","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,16,16,"2026-04-13",45644.354166666664,"2026-04-17",45644.645833333336,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre \r\nRenouvellement des voies III - IV  - V en gare de Luttre\r\nAménagement Aw L117\r\nDossier de concertation validé en octobre 2023\r\nTCR 524246",null,null,72214,"2024-10-15",0,"1,2,3,4,5"]
[null,"Infrabel","67947","Lille - Charleroi","< >","SILLY","ENGHIEN",2026,2026,16,16,"2026-04-14",45644.020833333336,"2026-04-18",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67947,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","83815","Lille - ZeeBrugge",">","Y.PELIKAAN","KNOKKE",2026,2026,16,16,"2026-04-14",45644.375,"2026-04-16",45644.645833333336,"3d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud bovenleiding spoor A of B",null,null,83815,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","84306","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,16,16,"2026-04-16",45644.333333333336,"2026-04-16",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,84306,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","82846","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2026,2026,16,16,"2026-04-16",45644.375,"2026-04-16",45644.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud + schouwen\r\nSP B BD + perronspoor II\r\n\r\nPerronspoor III tot VII + bundel M ontoegankelijk\r\n",null,null,82846,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","75566","Athus - Meuse",">","YVOIR","Y.NEFFE",2026,2026,16,17,"2026-04-17",45644.958333333336,"2026-04-20",45644.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Entretien AS, traitement zone boueuse\r\nSAVU + CTL de nuit (CoLT 80066)\r\nUPM: 527578\r\n",null,null,75566,"2024-11-04",0,"5,6"]
[null,"Infrabel","68497","Lille - Charleroi","< >","HALLE","LOT",2026,2026,16,17,"2026-04-18",45644.03125,"2026-04-20",45644.197916666664,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels rooster N kant FBMZ: Fase 1.4 Aw's 55AN",null,null,68497,"2024-10-02",1,"5,6"]
[null,"Infrabel","80066","Athus - Meuse","< >","YVOIR","Y.NEFFE",2026,2026,16,17,"2026-04-18",45644.986111111109,"2026-04-20",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien AS, traitement zone boueuse\r\nSAVU (CF. CoLT 75566) + CTL nuit dans les BT\r\nUPM: 527581\r\n",null,null,80066,"2024-11-04",0,"5,6"]
[null,"Infrabel","63320","Athus - Meuse","< >","ARLON","STERPENICH-FRONTIERE",2026,2026,16,17,"2026-04-18",45644.25,"2026-04-20",45644.229166666664,"2d, 23:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nDossier de concertation validé en octobre 2023\r\nUPM 531418",null,null,63320,"2024-12-04",1,"5,6"]
[null,"Infrabel","82270","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2026,2026,16,17,"2026-04-19",45644.03125,"2026-04-20",45644.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud bovenleiding\r\nmin 14 prestaties, gespreid over het jaar,\r\nsp A of sp B\r\nHKV\r\nNacht R6^R7 van 00u45 tot 06u00",null,null,82270,"2024-11-14",0,"5,6"]
[null,"Infrabel","78403","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,17,17,"2026-04-20",45644.958333333336,"2026-04-24",45644.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78403,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","75699","Lille - Charleroi",">","BRUXELLES-MIDI","LOT",2026,2026,17,17,"2026-04-20",45644.986111111109,"2026-04-25",45644.229166666664,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone FH_04 Area CE volgens onderhoudskalender 2026\r\nBuitendienststelling L96 spoor B tussen FBMZ en Lot.",null,null,75699,"2024-10-04",0,"1,2,3,4,5"]
[null,"Infrabel","61843","Lille - Antwerpen",">","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,17,17,"2026-04-20",45644.25,"2026-04-24",45644.666666666664,"5d, 10:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron \r\nDossier de concertation\r\n\r\nPhase 3 - Construction des nouvelles piles\r\nPhase 3.1 - Construction d'une nouvelle pile au niveau de la L75 VB : SAVU de jour pou",null,null,61843,"2023-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","72215","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,17,17,"2026-04-20",45644.354166666664,"2026-04-24",45644.645833333336,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre \r\nRenouvellement des voies III - IV  - V en gare de Luttre\r\nAménagement Aw L117\r\nDossier de concertation validé en octobre 2023\r\nTCR 525623",null,null,72215,"2024-10-22",0,"1,2,3,4,5"]
[null,"Infrabel","69448","Lille - Charleroi","< >","Y.NOORD HALLE","SAINTES",2026,2026,17,17,"2026-04-21",45644.013888888891,"2026-04-25",45644.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels rooster H kant Lembeek: Lossen wissels Fase 2.2 met Kirow",null,null,69448,"2024-10-04",0,"1,2,3,4,5"]
[null,"Infrabel","63308","Athus - Meuse","< >","BOIS D'AUSSE","NAMUR",2026,2026,17,17,"2026-04-24",45644.958333333336,"2026-04-26",45644.916666666664,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nCTL WE2 P93 + Bourrage\r\nDossier de concertation validé en octobre 2023\r\nUPM 530625",null,null,63308,"2024-11-28",1,"5,6"]
[null,"Infrabel","65767","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,17,20,"2026-04-24",45644.9375,"2026-05-11",45644.1875,"16d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Rhisnes\r\nDossier de concertation validé en octobre 2023\r\n+ visites de voies",null,null,65767,"2024-07-15",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","75287","Namur - Antwerpen","< >","MARCINELLE","FLEURUS",2026,2026,17,17,"2026-04-25",45644.25,"2026-04-26",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z04.51 P4\r\n+ L140 Travaux PLP Fleurus\r\n+ Renouvellement FDC  voie A (Et 38/39 + 39/40A)\r\nEntre signal TXN20 et CQ20",null,null,75287,"2024-08-29",1,"5,6"]
[null,"Infrabel","76164","Namur - Antwerpen",">","AUVELAIS","FLAWINNE",2026,2026,17,17,"2026-04-26",45644.333333333336,"2026-04-26",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie Auvelais - Flawinne VB L 130\r\nUPM: 532415",null,null,76164,"2024-12-12",0,"5,6"]
[null,"Infrabel","82822","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2026,2026,17,17,"2026-04-26",45644.006944444445,"2026-04-26",45644.229166666664,"1d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken station FR - L51 -L51A - L51B\r\n",null,null,82822,"2024-12-13",0,"5,6"]
[null,"Infrabel","69324","Lille - Charleroi","< >","HALLE","SAINTES",2026,2026,18,18,"2026-04-27",45644.979166666664,"2026-04-30",45644.180555555555,"3d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Voorbereidende werken afschaffen OW",null,null,69324,"2024-10-04",0,"1,2,3,4,5"]
[null,"Infrabel","64911","Lille - Charleroi","< >","HALLE","ENGHIEN",2026,2026,18,18,"2026-04-27",45644.965277777781,"2026-04-30",45644.194444444445,"3d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction d'un PI - PN16\r\nNuits de préparation\r\nUPM 530866",null,null,64911,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","73772","Lille - Charleroi","< >","Y.NOORD HALLE","TUBIZE",2026,2026,18,18,"2026-04-28",45644.013888888891,"2026-04-30",45644.180555555555,"3d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels rooster H kant Lembeek: voorbereidende werken",null,null,73772,"2024-10-15",0,"1,2,3,4,5"]
[null,"Infrabel","64910","Lille - Charleroi","< >","HALLE","ENGHIEN",2026,2026,18,19,"2026-04-30",45644.965277777781,"2026-05-04",45644.194444444445,"3d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Construction d'un PI - PN16\r\n+ Maintenance Z15.54 P4\r\nUPM 530871",null,null,64910,"2024-11-29",1,"5,6"]
[null,"Infrabel","58601","Lille - Charleroi","< >","HALLE","SAINTES",2026,2026,18,19,"2026-05-01",45644.013888888891,"2026-05-04",45644.180555555555,"3d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Afschaffen OW L94 area CE",null,null,58601,"2024-10-04",1,"5,6"]
[null,"Infrabel","79358","Erquelinnes - Montzen",">","HUY","STATTE",2026,2026,18,19,"2026-05-01",45644.25,"2026-05-04",45644.208333333336,"3d, 23:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA au CSV Huy\r\nWE 3jours - 1er mai \r\n",null,null,79358,"2024-08-07",0,"5,6"]
[null,"Infrabel","64302","Lille - Charleroi",">","MANAGE","LUTTRE",2026,2026,18,18,"2026-05-01",45644.875,"2026-05-02",45644.25,"1d, 09:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre - Phase 6\r\nRenouvellement des Aw L124\r\nExtension nuit pour dépose CAT 40/9\r\nDossier de concertation validé en octobre 2023\r\nCorrélation 63519\r\nTCR 525886\r\n",null,null,64302,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","83838","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2026,2026,18,18,"2026-05-01",45644.354166666664,"2026-05-01",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno Z7V\r\n",null,null,83838,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","80059","Namur - Antwerpen","< >","OTTIGNIES","LA ROCHE(BRABANT)",2026,2026,18,19,"2026-05-02",45644.010416666664,"2026-05-04",45644.197916666664,"3d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"RER : Suppression du PN 45 à Ottignies et remplacement par un CSV- travaux préparatoires\r\nliée à la colt 63592 pour le SAVU en continu \r\nUPM: 531553",null,null,80059,"2024-12-05",0,"5,6"]
[null,"Infrabel","64912","Lille - Charleroi","< >","HALLE","ENGHIEN",2026,2026,19,19,"2026-05-04",45644.965277777781,"2026-05-09",45644.173611111109,"5d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction d'un PI - PN16\r\nNuits de finitions\r\nUPM 530891",null,null,64912,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","84249","Athus - Meuse",">","BERTRIX","PALISEUL",2026,2026,19,19,"2026-05-05",45644.333333333336,"2026-05-05",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VB\r\nEntretien voie",null,null,84249,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","69385","Lille - Charleroi","< >","HALLE","SAINTES",2026,2026,19,19,"2026-05-05",45644.013888888891,"2026-05-09",45644.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels rooster H kant Lembeek: afwerkingsnachten",null,null,69385,"2024-10-04",0,"1,2,3,4,5"]
[null,"Infrabel","84079","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2026,2026,19,19,"2026-05-07",45644.388888888891,"2026-05-07",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,84079,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","63942","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2026,2026,19,20,"2026-05-08",45644.965277777781,"2026-05-11",45644.208333333336,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement LRS\r\nMassification NW : CTL Courtrai - Mouscron",null,null,63942,"2024-02-20",1,"5,6"]
[null,"Infrabel","75899","Athus - Meuse","< >","JAMBES","YVOIR",2026,2026,19,20,"2026-05-09",45644.208333333336,"2026-05-11",45644.180555555555,"2d, 23:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux préparatoires Block Automatique Jambes-Lustin + BA Lustin-Yvoir pour passage futur en EBP-PLP\r\nUPM: 526970\r\nRQ333: intégration des visites VA+VB Lustin - Yvoir ok ? ",null,null,75899,"2024-11-15",1,"5,6"]
[null,"Infrabel","71865","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","TILLEUR",2026,2026,19,20,"2026-05-09",45644.916666666664,"2026-05-11",45644.166666666664,"1d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement d'AS à Lg Guillemins\r\nPhase 5: bourrage de révision des phases 3 et 4\r\n5.2.\r\nUPM 532528\r\nSIRU en cours et en attente de présentation",null,null,71865,"2024-12-12",1,"5,6"]
[null,"Infrabel","72388","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,19,20,"2026-05-09",45644.003472222219,"2026-05-11",45644.194444444445,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,72388,"2023-12-20",1,"5,6"]
[null,"Infrabel","77540","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2026,2026,19,19,"2026-05-10",45644.333333333336,"2026-05-10",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Sint-Joris-weert - Wavre VA/VB\r\nUPM: 530240",null,null,77540,"2024-11-26",0,"5,6"]
[null,"Infrabel","78404","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,20,20,"2026-05-11",45644.958333333336,"2026-05-14",45644.180555555555,"3d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78404,"2024-06-17",0,"1,2,3,4,5"]
[null,"Infrabel","61830","Lille - Charleroi","< >","CHARLEROI-CENTRAL","MARCHIENNE-AU-PONT",2026,2026,20,20,"2026-05-11",45644.9375,"2026-05-12",45644.229166666664,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Grill Charleroi-Sud - Phase 2.16.2\r\nLivraison AS Charleroi via grue KIROW\r\nLivraison 35G + 44G le long de la VB L124A\r\nDossier de concertation validé en octobre 2023\r\nTCR 498439",null,null,61830,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","63940","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2026,2026,20,20,"2026-05-11",45644.965277777781,"2026-05-16",45644.208333333336,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie:\r\n1)Courtrai - Mouscron LRS\r\n+\r\n2) onderhoud massificatie Tracks/SI (Baanvak Y. Bethune - Moeskroen, beide niet in)\r\n",null,null,63940,"2024-05-02",0,"1,2,3,4,5"]
[null,"Infrabel","64304","Lille - Charleroi","< >","MANAGE","LUTTRE",2026,2026,20,20,"2026-05-11",45644.354166666664,"2026-05-15",45644.645833333336,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre - Phase 7\r\nDossier de concertation validé en octobre 2023\r\nTCR 525947",null,null,64304,"2024-10-23",0,"1,2,3,4,5"]
[null,"Infrabel","84233","Athus - Meuse",">","PALISEUL","GEDINNE",2026,2026,20,20,"2026-05-12",45644.333333333336,"2026-05-12",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VB\r\nEntretien voie",null,null,84233,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","82918","Namur - Antwerpen","< >","Y.HEIKE","DENDERMONDE",2026,2026,20,20,"2026-05-12",45644.006944444445,"2026-05-16",45644.204861111109,"5d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z79.33\r\nInclusief FDR sporen III en IV ",null,null,82918,"2024-11-22",0,"1,2,3,4,5"]
[null,"Infrabel","84061","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2026,2026,20,20,"2026-05-12",45644.34375,"2026-05-12",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,84061,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","72941","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2026,2026,20,20,"2026-05-13",45644.378472222219,"2026-05-13",45644.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA",null,null,72941,"2024-08-23",0,"1,2,3,4,5"]
[null,"Infrabel","84292","Athus - Meuse",">","FLORENVILLE","STRAIMONT",2026,2026,20,20,"2026-05-14",45644.378472222219,"2026-05-14",45644.670138888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,84292,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","78687","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON",2026,2026,20,21,"2026-05-15",45644.965277777781,"2026-05-18",45644.166666666664,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-512066\r\n\r\nonderhoud massificatie Tracks/SI\r\n\r\n* Y Bethune en Moeskroen vrij\r\n",null,null,78687,"2024-06-12",1,"5,6"]
[null,"Infrabel","76185","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2026,2026,20,20,"2026-05-16",45644.333333333336,"2026-05-16",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie Rhisnes - Namur \r\nPas de massification dans un SAVU en continu de w-e\r\nUne TCR pour le samedi et une autre pour le dimanche\r\n",null,null,76185,"2024-04-26",0,"5,6"]
[null,"Infrabel","68502","Lille - Charleroi","< >","Y.NOORD HALLE","ENGHIEN",2026,2026,20,21,"2026-05-16",45644.013888888891,"2026-05-18",45644.180555555555,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels rooster H kant Lembeek: Fase 2.2-1\r\nBeschermingsmaatregel op sp B L96",null,null,68502,"2024-10-04",1,"5,6"]
[null,"Infrabel","79057","Namur - Antwerpen","< >","Y.NAZARETH","Y.NOORD DRIEHOEK AARSCHOT",2026,2026,20,21,"2026-05-16",45644.25,"2026-05-18",45644.184027777781,"2d, 22:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517756\r\n\r\nVernieuwen overweg\r\n+\r\nVernieuwen overweg 31bis naar type Harmellen",null,null,79057,"2024-08-29",1,"5,6"]
[null,"Infrabel","77712","Namur - Antwerpen",">","NAMUR","RHISNES-SAS",2026,2026,20,20,"2026-05-17",45644.333333333336,"2026-05-17",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie Rhisnes - Namur \r\nPas de massification dans un SAVU en continu de w-e\r\nUne TCR pour le samedi et une autre pour le dimanche",null,null,77712,"2024-04-26",0,"5,6"]
[null,"Infrabel","76863","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2026,2026,21,21,"2026-05-18",45644.958333333336,"2026-05-23",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nGare de Jeumont fermée\r\nTCR 529196  - En corrélation avec ID 529198",null,null,76863,"2024-11-19",0,"1,2,3,4,5"]
[null,"Infrabel","68960","Namur - Antwerpen",">","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,21,21,"2026-05-18",45644.979166666664,"2026-05-23",45644.194444444445,"5d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-517902\r\n\r\nHerelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel:",null,null,68960,"2024-08-20",0,"1,2,3,4,5"]
[null,"Infrabel","68424","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,21,21,"2026-05-18",45644.993055555555,"2026-05-22",45644.180555555555,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-511653\r\n\r\nMassificatie: Vernieuwen Y Kortrijk West\r\n1)voorbereidende werken + Kirow\r\n+\r\n2)onderhoud massificatie Tracks/SI\r\n\r\n\r\n*R5/R6 in WE TLO",null,null,68424,"2024-06-07",0,"1,2,3,4,5"]
[null,"Infrabel","83766","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2026,2026,21,21,"2026-05-18",45644.947916666664,"2026-05-23",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z05.32\r\nInclusief Eeklo alle perronsporen (I, II en III) \r\n",null,null,83766,"2024-12-04",0,"1,2,3,4,5"]
[null,"Infrabel","84114","Athus - Meuse",">","VONECHE","BEAURAING",2026,2026,21,21,"2026-05-19",45644.333333333336,"2026-05-19",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,84114,"2024-11-19",0,"5,6"]
[null,"Infrabel","83796","Lille - ZeeBrugge",">","BLANKENBERGE","Y.BLAUWE TOREN",2026,2026,21,21,"2026-05-19",45644.375,"2026-05-21",45644.625,"3d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoud Bovenleiding DOES SP A OF B",null,null,83796,"2024-11-19",0,"1,2,3,4,5"]
[null,"Infrabel","84515","Athus - Meuse",">","SIGNEULX","HALANZY",2026,2026,21,21,"2026-05-21",45644.333333333336,"2026-05-21",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,84515,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","82072","Athus - Meuse",">","GEDINNE","VONECHE",2026,2026,21,21,"2026-05-21",45644.333333333336,"2026-05-21",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,82072,"2024-11-19",0,"1,2,3,4,5"]
[null,"Infrabel","64691","Namur - Antwerpen","< >","OTTIGNIES","OTTIGNIES",2026,2026,21,22,"2026-05-22",45644.979166666664,"2026-05-26",45644.201388888891,"3d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER Ottignies: renouvellement du Coeur de la gare + quais N7 et N8\r\ncoupure de 3 jours\r\nPas de passage L161-139\r\nUPM: 530601",null,null,64691,"2024-11-28",1,"5,6"]
[null,"Infrabel","63081","Namur - Antwerpen","< >","NAMUR","TAMINES",2026,2026,21,22,"2026-05-23",45644.208333333336,"2026-05-26",45644.208333333336,"3d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Démolition du PS 76.318\r\n+ maintenance globale  L130  + L130/1 + L144\r\n+ Intervention caténaire pour déroulage et iso 78/4.\r\nUPM: 527923",null,null,63081,"2024-11-06",1,"5,6"]
[null,"Infrabel","63350","Athus - Meuse","< >","BERTRIX","VIRTON",2026,2026,21,21,"2026-05-23",45644.25,"2026-05-24",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement P93 WE 2\r\nUPM: 528174",null,null,63350,"2024-11-08",1,"5,6"]
[null,"Infrabel","79364","Erquelinnes - Montzen",">","HUY","STATTE",2026,2026,21,22,"2026-05-23",45644.25,"2026-05-26",45644.208333333336,"3d, 23:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA au CSV Huy. \r\n",null,null,79364,"2024-08-07",0,"5,6"]
[null,"Infrabel","76864","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2026,2026,22,22,"2026-05-25",45644.958333333336,"2026-05-30",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nGare de Jeumont fermée\r\nEn corrélation avec ID68273 - 74680\r\nTCR529245",null,null,76864,"2024-11-19",0,"1,2,3,4,5"]
[null,"Infrabel","78601","Lille - Antwerpen","< >","DEINZE-WIJKSPOREN","DEINZE-WIJKSPOREN",2026,2026,22,25,"2026-05-25",45644.333333333336,"2026-06-19",45644.666666666664,"25d, 08:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-512068\r\n\r\nVernieuwen sporen Deinze Wijksporen: sporen 751-752-760 3 weken buitendienst",null,null,78601,"2024-12-09",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","74680","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,22,22,"2026-05-25",45644.923611111109,"2026-05-30",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux Caténaire",null,null,74680,"2024-04-10",0,"1,2,3,4,5"]
[null,"Infrabel","78406","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,22,22,"2026-05-26",45644.958333333336,"2026-05-29",45644.208333333336,"3d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78406,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","66648","Namur - Antwerpen",">","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,22,22,"2026-05-26",45644.979166666664,"2026-05-30",45644.194444444445,"4d, 05:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-517901\r\n\r\nHerelektrificatie L27 tussen Kontich en Mechelen-Nekkerspoel:               \r\nL27 spA + L25 spB  BD",null,null,66648,"2024-08-29",0,"1,2,3,4,5"]
[null,"Infrabel","81721","Lille - ZeeBrugge","< >","LICHTERVELDE","KORTRIJK",2026,2026,22,22,"2026-05-26",45644.993055555555,"2026-05-30",45644.180555555555,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z04.35 HKV\r\n\r\nInclusief perronspoor II te Menen, exclusief perronspoor I te Menen \r\nNavette tussen Poperinge en Menen moet mogelijk zijn via L69 Enk. baanvak FPP - Komen + Spoor A L69 \r\nInclusief perronspoor I tot IV te LK \r\nInclusief per",null,null,81721,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","69386","Lille - Charleroi","< >","Y.NOORD HALLE","TUBIZE",2026,2026,22,22,"2026-05-27",45644.027777777781,"2026-05-30",45644.194444444445,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels rooster H kant Lembeek: voorbereidende werken fase 2.3",null,null,69386,"2024-10-09",0,"1,2,3,4,5"]
[null,"Infrabel","84097","Athus - Meuse",">","BEAURAING","HOUYET",2026,2026,22,22,"2026-05-27",45644.388888888891,"2026-05-27",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"visite et interventions diverses VB ",null,null,84097,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","63353","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,22,23,"2026-05-29",45644.25,"2026-06-01",45644.916666666664,"4d, 16:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement P93\r\nWE 3\r\nP93 + bourrage, contraintes zone WE2\r\nUPM: 528176\r\nRQ333: intégrer la visite de la VA ok ? ",null,null,63353,"2024-11-08",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","68431","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,22,23,"2026-05-29",45644.993055555555,"2026-06-01",45644.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-511620\r\n\r\nVernieuwen Y Kortrijk West\r\n\r\n* Roeselare niet in",null,null,68431,"2024-07-11",1,"5,6"]
[null,"Infrabel","69125","Namur - Antwerpen","< >","OTTIGNIES","WAVRE",2026,2026,22,23,"2026-05-30",45644.208333333336,"2026-06-01",45644.229166666664,"2d, 00:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"chantier RER - dépose liaison L139 + raccordement chantier\r\nUPM: 530732\r\n",null,null,69125,"2024-11-28",1,"5,6"]
[null,"Infrabel","63802","Athus - Meuse","< >","BERTRIX","VIRTON",2026,2026,22,22,"2026-05-30",45644.25,"2026-05-31",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"CTL P93 WE 3\r\nUPM: 528177",null,null,63802,"2024-11-08",1,"5,6"]
[null,"Infrabel","63292","Erquelinnes - Montzen","< >","VISE","VISE-FRONTIERE",2026,2026,22,22,"2026-05-30",45644.25,"2026-05-31",45644.833333333336,"2d, 14:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Z:12.42 liée avec 66306 (Z.13.42 en phase 2)\r\n- Entretien mécanisé et manuel des AS du grill Nord de Visé-Bas avec MHS VA de L24/1\r\n- Entretien mécanisé du PN 28 \r\n- Quai de la voie I de Visé accessible vers Liège",null,null,63292,"2024-08-09",1,"5,6"]
[null,"Infrabel","79055","Namur - Antwerpen","< >","Y.NAZARETH","HEIST-OP-DEN-BERG",2026,2026,22,23,"2026-05-30",45644.25,"2026-06-01",45644.184027777781,"2d, 22:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-518127\r\n\r\nVernieuwen overweg\r\n+\r\nVernieuwen overweg 31bis naar type Harmellen",null,null,79055,"2024-08-29",1,"5,6"]
[null,"Infrabel","78407","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,23,23,"2026-06-01",45644.958333333336,"2026-06-05",45644.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78407,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","78671","Lille - ZeeBrugge","< >","LICHTERVELDE","BRUGGE",2026,2026,23,23,"2026-06-01",45644.979166666664,"2026-06-05",45644.215277777781,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-511500\r\n\r\nonderhoud massificatie Tracks/SI - Perronsporen Brugge - Lichtervelde - Diksmuide niet in.\r\nnacht 56 in WE-TLO",null,null,78671,"2024-06-06",0,"1,2,3,4,5"]
[null,"Infrabel","65349","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,23,23,"2026-06-01",45644.9375,"2026-06-06",45644.1875,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS 63.687 en L94\r\nPhase 5 - Finitions au niveau du nouveau PS\r\n[Phases 1+2+3 en 2025]\r\nUPM 530733",null,null,65349,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","68426","Lille - ZeeBrugge","< >","KORTRIJK","ROESELARE",2026,2026,23,23,"2026-06-01",45644.993055555555,"2026-06-05",45644.180555555555,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-511657\r\n\r\nVernieuwen Y Kortrijk West\r\nafwerking\r\n\r\nNacht R5/R6 opgenomen in COLT 77670",null,null,68426,"2024-06-07",0,"1,2,3,4,5"]
[null,"Infrabel","81073","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.SOIGNIES",2026,2026,23,23,"2026-06-01",45644.954861111109,"2026-06-05",45644.1875,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.53 en P3 HKV\r\nRQ333: en concomitance Z5\r\nPropo: sem 23",null,null,81073,"2024-11-26",0,"1,2,3,4,5"]
[null,"Infrabel","76048","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2026,2026,23,23,"2026-06-01",45644.319444444445,"2026-06-01",45644.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie Gembloux gare + maintenance infrastructure + contrôles",null,null,76048,"2024-03-26",0,"1,2,3,4,5"]
[null,"Infrabel","83961","Athus - Meuse",">","JAMBES","LUSTIN",2026,2026,23,23,"2026-06-04",45644.385416666664,"2026-06-04",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VA\r\nRQ333: en R4 (ald R6) OK ? ",null,null,83961,"2024-11-14",0,"5,6"]
[null,"Infrabel","78040","Lille - ZeeBrugge","< >","LICHTERVELDE","BRUGGE-ROOSTER E",2026,2026,23,24,"2026-06-05",45644.972222222219,"2026-06-08",45644.194444444445,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"TCR 511366\r\n\r\nMassificatie: Perronsporen FR en FLC niet in.\r\nBuitenwerken vernieuwing seininrichting naar SIW\r\n+\r\nonderhoud massificatie Tracks/SI",null,null,78040,"2024-07-11",1,"5,6"]
[null,"Infrabel","66591","Erquelinnes - Montzen","< >","HUY","NAMUR",2026,2026,23,24,"2026-06-05",45644.993055555555,"2026-06-08",45644.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification renforcement de talus  (L, enrochement,...), parois rocheuses. Suppression PN 75, 76, 77 78",null,null,66591,"2023-12-20",1,"5,6"]
[null,"Infrabel","80038","Namur - Antwerpen","< >","NAMUR","RONET",2026,2026,23,23,"2026-06-06",45644.958333333336,"2026-06-07",45644.21875,"1d, 06:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur ZONE 6\r\nZ6.43\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,80038,"2024-12-12",0,"5,6"]
[null,"Infrabel","68507","Lille - Charleroi","< >","Y.NOORD HALLE","TUBIZE",2026,2026,23,24,"2026-06-06",45644.027777777781,"2026-06-08",45644.194444444445,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels rooster H kant Lembeek: Fase 2.3-1\r\nBeschermingsmaatregel op sp A L94",null,null,68507,"2024-10-16",1,"5,6"]
[null,"Infrabel","79239","Namur - Antwerpen","< >","Y.HOLLAND","Y.DRIEHOEKSTRAAT",2026,2026,23,23,"2026-06-06",45644.25,"2026-06-07",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517318\r\n\r\nOnderhoud (voorjaar, voorkeur april), 2 TLO WE van 48u achter elkaar,",null,null,79239,"2024-09-03",1,"5,6"]
[null,"Infrabel","66305","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,23,23,"2026-06-06",45644.25,"2026-06-07",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 11 + 12 - Préparation transfert PN11, 12 et 18 + TRV\r\n+ Maintenance",null,null,66305,"2024-08-09",1,"5,6"]
[null,"Infrabel","82673","Lille - Charleroi","< >","GHLIN","MONS",2026,2026,23,23,"2026-06-06",45644.993055555555,"2026-06-07",45644.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim\r\nRQ333: déplacé au we 23",null,null,82673,"2024-12-12",0,"5,6"]
[null,"Infrabel","78408","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,24,24,"2026-06-08",45644.958333333336,"2026-06-13",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78408,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","81595","Lille - ZeeBrugge","< >","BRUGGE","LICHTERVELDE",2026,2026,24,24,"2026-06-08",45644.979166666664,"2026-06-13",45644.215277777781,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone 07.34  HKV\r\n\r\nInclusief Brugge perronsporen VI, VII en VIII \r\nInclusief Lichtervelde perronsporen IV en V + DSP 736/737 \r\nInclusief Diksmuide perronspoor II \r\n\r\n",null,null,81595,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","63903","Namur - Antwerpen",">","LE CAMPINAIRE","CHATELET-GRIL OUEST",2026,2026,24,28,"2026-06-08",45644.25,"2026-07-06",45644.208333333336,"29d, 23:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet 2026 - Phase 6.1\r\nCoupure type 1  - Phase 6.1.1 En continu du 08/06/26 au 06/07/26\r\nCoupure type 2 de nuit semaine - Phase 6.1.2 du 08^09/06/26 à 26^27/06/26 - du 29^30/06/26 à 03^04/07/26\r\nVoie B L130 HS de nuits entre CJ.20 et DXJ",null,null,63903,"2024-04-15",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","83948","Athus - Meuse",">","NAMUR","JAMBES",2026,2026,24,24,"2026-06-08",45644.388888888891,"2026-06-08",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES (périodicité 6 semaines)",null,null,83948,"2024-11-14",0,"1,2,3,4,5"]
[null,"Infrabel","73951","Lille - Charleroi","< >","Y.NOORD HALLE","TUBIZE",2026,2026,24,24,"2026-06-09",45644.027777777781,"2026-06-12",45644.194444444445,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels rooster H kant Lembeek: voorbereidende werken fase 2.3",null,null,73951,"2024-10-16",0,"1,2,3,4,5"]
[null,"Infrabel","80029","Namur - Antwerpen",">","NAMUR","RHISNES",2026,2026,24,24,"2026-06-12",45644.958333333336,"2026-06-13",45644.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5\r\n",null,null,80029,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","76315","Namur - Antwerpen","< >","GEMBLOUX","JEMEPPE-SUR-SAMBRE",2026,2026,24,25,"2026-06-12",45644.958333333336,"2026-06-15",45644.166666666664,"3d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Bourrage de révision suite chantier Chape d'étanchéité PI Victor Debecker - L144 bK 0.144\r\nvoir COLT 76303\r\nUPM: 527931",null,null,76315,"2024-11-06",0,"5,6"]
[null,"Infrabel","63333","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2026,2026,24,25,"2026-06-13",45644.208333333336,"2026-06-15",45644.1875,"2d, 23:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des AS de Mont St Guibert \r\n+ Assainissement de la plateforme \r\nWE2",null,null,63333,"2024-07-15",1,"5,6"]
[null,"Infrabel","77841","Lille - Antwerpen","< >","DEINZE","Y.ZANDBERG",2026,2026,24,25,"2026-06-13",45644.013888888891,"2026-06-15",45644.173611111109,"2d, 03:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-512071\r\n\r\nMassificatie: Perronsporen Deinze en Y. Zandberg vrij.\r\nfietstunnel OW 49B\r\n+\r\nonderhoud massificatie Tracks/SI\r\n+\r\nVervangen hoofd en hulpdrager ( KP29.500 en 33.00) Spoor B",null,null,77841,"2024-10-28",1,"5,6"]
[null,"Infrabel","63710","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,24,24,"2026-06-13",45644.25,"2026-06-14",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Préparation transfert PN11, 12 et 18 + TRV\r\n+ Massification Z9.42\r\nEntretien mécanisé et manuel des AS de Bressoux côté Visé et AS des d'entrée de Visé et/ou entretien de PN",null,null,63710,"2024-09-03",1,"5,6"]
[null,"Infrabel","78409","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,25,25,"2026-06-15",45644.958333333336,"2026-06-19",45644.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78409,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","65418","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,25,25,"2026-06-15",45644.9375,"2026-06-19",45644.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\nUPM 530721",null,null,65418,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","79882","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,25,25,"2026-06-15",45644.993055555555,"2026-06-19",45644.177083333336,"4d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,79882,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","81619","Lille - ZeeBrugge","< >","Y.BLAUWE TOREN","BLANKENBERGE",2026,2026,25,25,"2026-06-15",45644.940972222219,"2026-06-20",45644.208333333336,"5d, 06:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z06.34.01 HKV\r\n\r\nInclusief perronsporen FBK (spoor I, II, III, IV, V, VI en VII) \r\n\r\n",null,null,81619,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","84081","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2026,2026,25,25,"2026-06-15",45644.388888888891,"2026-06-15",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA",null,null,84081,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","69254","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,25,26,"2026-06-16",45644.027777777781,"2026-06-22",45644.208333333336,"7d, 04:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-513773\r\n\r\nBundel centraal Merelbeke\r\nlossen KIROW \r\nBuiten dienst;\r\nBundel Centraal volledig\r\nL50E SP B\r\nL58 SP B\r\nBuiten spanning;\r\n29170 - 29168 - 29166 - 29154 - 29184 - 29182 - 29187 - 29185 - 29186\r\nWerkplaats Melle bundel GC/GD buiten spanning!",null,null,69254,"2024-09-03",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","84250","Athus - Meuse",">","PALISEUL","BERTRIX",2026,2026,25,25,"2026-06-18",45644.333333333336,"2026-06-18",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VA\r\nEntretien voie",null,null,84250,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","68274","Erquelinnes - Montzen","< >","LA SAMBRE","CHARLEROI-CENTRAL",2026,2026,25,26,"2026-06-19",45644.958333333336,"2026-06-22",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Dossier de concertation validé en octobre 2023\r\nVoir croquis spécifique, \"SIRU Aménagement Charleroi 2026_ Coupure 19\"\r\nTCR",null,null,68274,"2024-12-11",1,"5,6"]
[null,"Infrabel","65420","Lille - Charleroi","< >","ATH","LEUZE",2026,2026,25,26,"2026-06-19",45644.9375,"2026-06-22",45644.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\nUPM 530737",null,null,65420,"2024-11-28",1,"5,6"]
[null,"Infrabel","83992","Athus - Meuse",">","YVOIR","LUSTIN",2026,2026,25,25,"2026-06-19",45644.375,"2026-06-19",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VB (périodicité 6 semaines)",null,null,83992,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","82674","Lille - Charleroi","< >","GHLIN","MONS",2026,2026,25,25,"2026-06-20",45644.993055555555,"2026-06-21",45644.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim\r\nRQ333: déplacé we25",null,null,82674,"2024-12-12",0,"5,6"]
[null,"Infrabel","77541","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2026,2026,25,25,"2026-06-21",45644.333333333336,"2026-06-21",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Sint-Joris-weert - Wavre VA/VB\r\nUPM: 530241",null,null,77541,"2024-11-26",0,"5,6"]
[null,"Infrabel","82272","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2026,2026,25,26,"2026-06-21",45644.03125,"2026-06-22",45644.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud bovenleiding\r\nmin 14 prestaties, gespreid over het jaar,\r\nsp A of sp B\r\nHKV\r\nNacht R6^R7 van 00u45 tot 06u00",null,null,82272,"2024-11-14",0,"5,6"]
[null,"Infrabel","63335","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2026,2026,26,26,"2026-06-22",45644.965277777781,"2026-06-27",45644.1875,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des AS de Mont St Guibert \r\n+ Assainissement de la plateforme\r\nBourrage de révision, contraintes,…",null,null,63335,"2024-04-05",0,"1,2,3,4,5"]
[null,"Infrabel","66955","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2026,2026,26,26,"2026-06-22",45644.993055555555,"2026-06-27",45644.208333333336,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517632\r\n\r\nVervolg werken 2023: vervangen houtstukken op Jan Bogaertsbrug (ander spoor) + vernieuwen spoor op brug over Zenne + sanering en vernieuwing spoor in een zone aan Jan Bogaertsbrug\r\n\r\nOverlegdossier gevalideerd in oktober 2023",null,null,66955,"2024-08-14",0,"1,2,3,4,5"]
[null,"Infrabel","82775","Namur - Antwerpen",">","Y.OOST DRIEHOEK LEDEBERG","Y.WEST DRIEHOEK LEDEBERG",2026,2026,26,26,"2026-06-23",45644.027777777781,"2026-06-27",45644.194444444445,"5d, 04:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"reservatie onderhoud/herzieningen/Schouwingen\r\nSchets DOES 4\r\nL50E SP B 01XR inbegrepen tot 05O inbegrepen\r\nL58/1 SP B 05O inbegrepen tot 10XO inbegrepen\r\nL58(1) SP A 10XO inbegrepen tot 01XR inbegrepen",null,null,82775,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","84174","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2026,2026,26,26,"2026-06-23",45644.34375,"2026-06-23",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,84174,"2024-11-22",0,"1,2,3,4,5"]
[null,"Infrabel","82836","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2026,2026,26,26,"2026-06-24",45644.333333333336,"2026-06-24",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud + schouwen spoor\r\nSP A BD + perronspoor I\r\n",null,null,82836,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","84235","Athus - Meuse",">","PALISEUL","GEDINNE",2026,2026,26,26,"2026-06-25",45644.333333333336,"2026-06-25",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VB\r\nEntretien voie",null,null,84235,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","82848","Lille - ZeeBrugge",">","Y.BLAUWE TOREN","BLANKENBERGE",2026,2026,26,26,"2026-06-25",45644.375,"2026-06-25",45644.666666666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"onderhoud + schouwen\r\nSP B BD + perronspoor II\r\n\r\nPerronspoor III tot VII + bundel M ontoegankelijk\r\n",null,null,82848,"2024-11-12",0,"1,2,3,4,5"]
[null,"Infrabel","84265","Athus - Meuse",">","STRAIMONT","BERTRIX",2026,2026,26,26,"2026-06-26",45644.333333333336,"2026-06-26",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,84265,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","65421","Lille - Charleroi","< >","ATH","TOURNAI",2026,2026,26,27,"2026-06-26",45644.9375,"2026-06-29",45644.1875,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"renforcement des 8 PI suivants : 54..992, 55.755, 58.487, 58.736, 60.362, 62.295, 63.375.\r\n+ Maintenance Z5.54\r\nUPM 530740",null,null,65421,"2024-11-28",1,"5,6"]
[null,"Infrabel","66961","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2026,2026,26,28,"2026-06-27",45644.166666666664,"2026-07-06",45644.166666666664,"9d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517633\r\n\r\nVervolg werken 2023: vervangen houtstukken op Jan Bogaertsbrug (ander spoor) + vernieuwen spoor op brug over Zenne + sanering en vernieuwing spoor in een zone aan Jan Bogaertsbrug\r\n\r\nOverlegdossier gevalideerd in oktober 2023",null,null,66961,"2024-08-14",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","78411","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,27,27,"2026-06-29",45644.958333333336,"2026-07-04",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78411,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","72101","Namur - Antwerpen","< >","OTTIGNIES","GEMBLOUX",2026,2026,27,27,"2026-06-29",45644.965277777781,"2026-07-04",45644.1875,"5d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement des AS de Mont St Guibert \r\n+ Assainissement de la plateforme\r\nBourrage de révision, contraintes,…",null,null,72101,"2024-04-05",0,"1,2,3,4,5"]
[null,"Infrabel","84044","Athus - Meuse",">","Y.NEFFE","DINANT",2026,2026,27,27,"2026-06-30",45644.333333333336,"2026-06-30",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,84044,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","84116","Athus - Meuse",">","VONECHE","BEAURAING",2026,2026,27,27,"2026-07-02",45644.333333333336,"2026-07-02",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,84116,"2024-11-19",0,"5,6"]
[null,"Infrabel","80030","Namur - Antwerpen",">","NAMUR","RHISNES",2026,2026,27,27,"2026-07-03",45644.958333333336,"2026-07-04",45644.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,80030,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","63285","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2026,2026,27,28,"2026-07-04",45644.25,"2026-07-06",45644.201388888891,"2d, 22:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93 Ottignies - La Roche\r\nUPM: 531622",null,null,63285,"2024-12-05",1,"5,6"]
[null,"Infrabel","84852","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2026,2026,27,28,"2026-07-05",45644.958333333336,"2026-07-06",45644.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nZ7.43\r\n",null,null,84852,"2024-12-12",0,"5,6"]
[null,"Infrabel","66956","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2026,2026,28,28,"2026-07-06",45644.993055555555,"2026-07-11",45644.208333333336,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517634\r\n\r\nVervolg werken 2023: vervangen houtstukken op Jan Bogaertsbrug (ander spoor) + vernieuwen spoor op brug over Zenne + sanering en vernieuwing spoor in een zone aan Jan Bogaertbrug\r\n\r\nOverlegdossier gevalideerd in oktober 2023",null,null,66956,"2024-08-14",0,"1,2,3,4,5"]
[null,"Infrabel","74684","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,28,28,"2026-07-06",45644.923611111109,"2026-07-11",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux SI + Voie\r\nTCR529380",null,null,74684,"2024-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","84099","Athus - Meuse",">","BEAURAING","HOUYET",2026,2026,28,28,"2026-07-07",45644.388888888891,"2026-07-07",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"visite et interventions diverses VB ",null,null,84099,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","62046","Namur - Antwerpen",">","GEMBLOUX","MONT-SAINT-GUIBERT",2026,2026,28,29,"2026-07-10",45644.958333333336,"2026-07-13",45644.166666666664,"2d, 05:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Déroulage\r\n+ visites",null,null,62046,"2024-07-05",0,"5,6"]
[null,"Infrabel","76634","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2026,2026,28,28,"2026-07-11",45644.25,"2026-07-12",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z02.54",null,null,76634,"2024-12-02",1,"5,6"]
[null,"Infrabel","63289","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2026,2026,28,29,"2026-07-11",45644.25,"2026-07-13",45644.197916666664,"2d, 22:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses entre Ottignies – La Roche P93\r\nbourrage de révision, contraintes, finitions,…\r\n+ Maintenance à massifier\r\nUPM: 531600",null,null,63289,"2024-12-05",1,"5,6"]
[null,"Infrabel","78413","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,29,29,"2026-07-13",45644.958333333336,"2026-07-18",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78413,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","80951","Lille - Charleroi","< >","HALLE","ATH",2026,2026,29,29,"2026-07-13",45644.944444444445,"2026-07-18",45644.180555555555,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z9.54 + Z10.54\r\n+massifié PLP",null,null,80951,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","76049","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2026,2026,29,29,"2026-07-13",45644.319444444445,"2026-07-13",45644.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie Gembloux gare + maintenance infrastructure + contrôles",null,null,76049,"2024-03-26",0,"1,2,3,4,5"]
[null,"Infrabel","83966","Athus - Meuse",">","JAMBES","LUSTIN",2026,2026,29,29,"2026-07-16",45644.385416666664,"2026-07-16",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VA\r\nRQ333: en R4 (ald R6) OK ? ",null,null,83966,"2024-11-14",0,"5,6"]
[null,"Infrabel","80069","Athus - Meuse","< >","ANSEREMME","HOUYET",2026,2026,29,30,"2026-07-18",45644.958333333336,"2026-07-20",45644.194444444445,"2d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien AS, traitement zone boueuse\r\nSAVU (CF. CoLT 75571) + CTL nuit\r\nUPM:527815",null,null,80069,"2024-11-06",0,"5,6"]
[null,"Infrabel","75884","Erquelinnes - Montzen","< >","STATTE","NAMUR",2026,2026,29,30,"2026-07-18",45644.25,"2026-07-20",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification travaux O.A. : Parois rocheuses, stabilisation de talus, étanchéité de P.I., suppression du PN de Seilles\r\nRQ333 : Propo WE 29 - Soit Arbitrage PMR Huy pour changement tronçon\r\nPhasage PMR huy en cours",null,null,75884,"2024-05-13",1,"5,6"]
[null,"Infrabel","76166","Namur - Antwerpen",">","AUVELAIS","FLAWINNE",2026,2026,29,29,"2026-07-19",45644.333333333336,"2026-07-19",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie Auvelais - Flawinne VB L 130\r\nUPM: 532397",null,null,76166,"2024-12-12",0,"5,6"]
[null,"Infrabel","63338","Athus - Meuse",">","Y.AUTELBAS","ARLON",2026,2026,30,33,"2026-07-20",45644.333333333336,"2026-08-10",45644.208333333336,"21d, 21:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement C75 \r\nbourrage de révision, contraintes, finitions,…\r\nAccord SNCB en réunion escalade du 22/01/2024\r\nUPM 531421",null,null,63338,"2024-12-04",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","78414","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,30,30,"2026-07-21",45644.958333333336,"2026-07-25",45644.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78414,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","84559","Athus - Meuse",">","HALANZY","Y.AUBANGE",2026,2026,30,30,"2026-07-22",45644.333333333336,"2026-07-22",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,84559,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","75415","Lille - Charleroi","< >","LEMBEEK","BRAINE-LE-COMTE",2026,2026,30,30,"2026-07-25",45644.25,"2026-07-26",45644.666666666664,"1d, 10:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z01.53 en P4",null,null,75415,"2024-09-10",1,"5,6"]
[null,"Infrabel","76129","Namur - Antwerpen",">","OTTIGNIES","WAVRE",2026,2026,30,30,"2026-07-25",45644.326388888891,"2026-07-25",45644.652777777781,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Ottignies - Wavre Gare comprise VA/VB\r\nUPM: 528362",null,null,76129,"2024-11-12",0,"5,6"]
[null,"Infrabel","81920","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2026,2026,31,31,"2026-07-27",45644.958333333336,"2026-08-01",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRVB Aulnoye\r\nTCR529620",null,null,81920,"2024-11-21",0,"1,2,3,4,5"]
[null,"Infrabel","75677","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2026,2026,31,31,"2026-07-27",45644.951388888891,"2026-08-01",45644.180555555555,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z4.53 en P3 HKV",null,null,75677,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","80961","Lille - Charleroi","< >","ATH","TOURNAI",2026,2026,31,31,"2026-07-27",45644.944444444445,"2026-08-01",45644.1875,"5d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z5.54",null,null,80961,"2024-12-13",0,"1,2,3,4,5"]
[null,"Infrabel","84383","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2026,2026,31,31,"2026-07-28",45644.333333333336,"2026-07-28",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,84383,"2024-12-05",0,"5,6"]
[null,"Infrabel","84252","Athus - Meuse",">","PALISEUL","BERTRIX",2026,2026,31,31,"2026-07-30",45644.333333333336,"2026-07-30",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VA\r\nEntretien voie",null,null,84252,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","80031","Namur - Antwerpen",">","NAMUR","RHISNES",2026,2026,31,31,"2026-07-31",45644.958333333336,"2026-08-01",45644.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,80031,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","80039","Namur - Antwerpen","< >","NAMUR","RONET",2026,2026,31,31,"2026-08-01",45644.958333333336,"2026-08-02",45644.21875,"1d, 06:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur ZONE 6\r\nZ6.43\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,80039,"2024-12-12",0,"5,6"]
[null,"Infrabel","75301","Lille - Charleroi","< >","LUTTRE","MARCHIENNE-AU-PONT",2026,2026,31,31,"2026-08-01",45644.25,"2026-08-02",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z07.52 P4\r\nTCR530061",null,null,75301,"2024-11-25",1,"5,6"]
[null,"Infrabel","77870","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2026,2026,31,32,"2026-08-01",45644.003472222219,"2026-08-03",45644.1875,"2d, 04:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-511776\r\n\r\nMassificatie:\r\n1)P783 perronverhogingen - De Pinte 2/3\r\n+\r\n2)Onderstoppen van P-Wissels op Absolute bassis met 2 Unimats Y. De Pinte en inrit FGSP + onderhoudswerken aan overwegn 18, 22 en 25 + vervangen spoorstaven + allerhande onderhoudsta",null,null,77870,"2024-07-11",1,"5,6"]
[null,"Infrabel","81919","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2026,2026,32,32,"2026-08-03",45644.958333333336,"2026-08-08",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRVB Aulnoye\r\nTCR529612",null,null,81919,"2024-11-21",0,"1,2,3,4,5"]
[null,"Infrabel","55877","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,32,32,"2026-08-03",45644.9375,"2026-08-07",45644.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 4  - Pose du nouveau tablier \r\nPhase 4.1 – CTL L75+75A+Faisceau de nuit",null,null,55877,"2023-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","65768","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,32,34,"2026-08-03",45644.9375,"2026-08-21",45644.9375,"18d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\nTronçon Gembloux - Rhisnes\r\nDossier de concertation validé en octobre 2023",null,null,65768,"2024-07-15",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","84404","Athus - Meuse",">","VIRTON","SIGNEULX",2026,2026,32,32,"2026-08-04",45644.333333333336,"2026-08-04",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,84404,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","77879","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2026,2026,32,32,"2026-08-04",45644.003472222219,"2026-08-08",45644.1875,"5d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-77879\r\n\r\nP783 perronverhogingen - De Pinte \r\n",null,null,77879,"2024-06-11",0,"1,2,3,4,5"]
[null,"Infrabel","84527","Athus - Meuse",">","SIGNEULX","HALANZY",2026,2026,32,32,"2026-08-06",45644.333333333336,"2026-08-06",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,84527,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","84010","Athus - Meuse",">","YVOIR","DINANT",2026,2026,32,32,"2026-08-06",45644.388888888891,"2026-08-06",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VA (périodicité 6 semaines)",null,null,84010,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","84011","Athus - Meuse",">","DINANT","YVOIR",2026,2026,32,32,"2026-08-07",45644.388888888891,"2026-08-07",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VB (périodicité 6 semaines)",null,null,84011,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","76723","Namur - Antwerpen","< >","CHARLEROI-CENTRAL","COUILLET",2026,2026,32,32,"2026-08-08",45644.25,"2026-08-09",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z10.51   P4\r\nUPM: 528640\r\n",null,null,76723,"2024-11-20",1,"5,6"]
[null,"Infrabel","79021","Namur - Antwerpen","< >","Y.LIERSESTEENWEG","Y.BERCHEM-STADION",2026,2026,32,33,"2026-08-08",45644.25,"2026-08-10",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517892\r\n\r\nvernieuwingen wisselonderdelen Y Drabstraat. \r\nAfbakeningen: Y Liersesteenweg (H-J.12 - HX-J.12) - Y Stadion (D-F.12 - DX.F.12) ",null,null,79021,"2024-10-17",1,"5,6"]
[null,"Infrabel","66960","Namur - Antwerpen","< >","LONDERZEEL","MECHELEN",2026,2026,32,33,"2026-08-08",45644.166666666664,"2026-08-10",45644.166666666664,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517640\r\n\r\nVervolg werken 2023: vervangen houtstukken op Jan Bogaertsbrug (ander spoor) + vernieuwen spoor op brug over Zenne + sanering en vernieuwing spoor in een zone aan Jan Bogaertsbrug\r\nOverlegdossier gevalideerd in oktober 2023",null,null,66960,"2024-08-14",1,"5,6"]
[null,"Infrabel","55882","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,33,33,"2026-08-10",45644.958333333336,"2026-08-15",45644.239583333336,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 5 -Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architectoni",null,null,55882,"2024-10-18",0,"1,2,3,4,5"]
[null,"Infrabel","63076","Athus - Meuse",">","DINANT","Y.NEFFE",2026,2026,33,39,"2026-08-10",45644.208333333336,"2026-09-21",45644.208333333336,"42d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement des rampes d'accès au CSV de Neffe et suppression des PN 115bis et 116\r\nUPM: 527093",null,null,63076,"2024-12-05",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","63349","Athus - Meuse",">","STOCKEM-NORD","HABAY",2026,2026,33,35,"2026-08-10",45644.25,"2026-08-24",45644.1875,"14d, 22:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de rails\r\nUPM 531398",null,null,63349,"2024-12-04",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","77886","Lille - Antwerpen","< >","GENT-SINT-PIETERS","DEINZE",2026,2026,33,33,"2026-08-11",45644.003472222219,"2026-08-14",45644.1875,"4d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-77886\r\n\r\nP783 perronverhogingen - De Pinte \r\n",null,null,77886,"2024-06-11",0,"1,2,3,4,5"]
[null,"Infrabel","63716","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2026,2026,33,35,"2026-08-14",45644.979166666664,"2026-08-24",45644.201388888891,"9d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER : Suppression du PN 45 à Ottignies et remplacement par un CSV\r\nDossier de concertation validé en octobre 2023\r\n+ Renouvellement Pi métalliques 52.015 et 52.215\r\nUPM: 531626",null,null,63716,"2024-12-05",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","79760","Athus - Meuse",">","CINEY","MARLOIE",2026,2026,33,33,"2026-08-14",45644.916666666664,"2026-08-14",45644.986111111109,"1d, 01:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du PS de Haversin\r\nbK 102.161\r\nDossier de concertation validé en octobre 2023\r\nUPM 530655",null,null,79760,"2024-11-28",0,"5,6"]
[null,"Infrabel","75295","Namur - Antwerpen","< >","TAMINES","JEMEPPE-SUR-SAMBRE-MARCHANDISE",2026,2026,33,34,"2026-08-15",45644.208333333336,"2026-08-17",45644.208333333336,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z19.51\r\nUPM: 528556",null,null,75295,"2024-11-20",1,"5,6"]
[null,"Infrabel","63337","Athus - Meuse","< >","GENDRON-CELLES","HOUYET",2026,2026,33,34,"2026-08-15",45644.25,"2026-08-17",45644.229166666664,"2d, 23:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE 1 P93\r\nDossier de concertation validé en octobre 2023\r\nUPM: 527730",null,null,63337,"2024-11-05",1,"5,6"]
[null,"Infrabel","61850","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,34,34,"2026-08-17",45644.958333333336,"2026-08-22",45644.239583333336,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 5 -Travaux de finition de la structure métallique, réalisation de la dalle du tablier et pose des rives en béton architectoni",null,null,61850,"2023-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","75656","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2026,2026,34,34,"2026-08-17",45644.965277777781,"2026-08-22",45644.229166666664,"5d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z9.52 + Maintenance Z.3.53 en P3 HKV",null,null,75656,"2024-12-13",0,"1,2,3,4,5"]
[null,"Infrabel","67964","Lille - Charleroi","< >","SILLY","ENGHIEN",2026,2026,34,34,"2026-08-18",45644.020833333336,"2026-08-22",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67964,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","84101","Athus - Meuse",">","BEAURAING","HOUYET",2026,2026,34,34,"2026-08-19",45644.388888888891,"2026-08-19",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"visite et interventions diverses VB ",null,null,84101,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","63341","Athus - Meuse",">","GENDRON-CELLES","BEAURAING",2026,2026,34,35,"2026-08-21",45644.25,"2026-08-24",45644.666666666664,"3d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE 2 P93 + bourrage...\r\nDossier de concertation validé en octobre 2023\r\nUPM:527733",null,null,63341,"2024-11-08",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","63066","Erquelinnes - Montzen","< >","Y.RENORY","SERAING",2026,2026,34,35,"2026-08-22",45644.208333333336,"2026-08-24",45644.208333333336,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Démantèlement des installation Arcelor\r\nUPM 530251",null,null,63066,"2024-11-26",1,"5,6"]
[null,"Infrabel","72389","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,34,35,"2026-08-22",45644.208333333336,"2026-08-24",45644.194444444445,"2d, 23:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,72389,"2024-06-26",1,"5,6"]
[null,"Infrabel","63339","Athus - Meuse","< >","GENDRON-CELLES","BEAURAING",2026,2026,34,35,"2026-08-22",45644.25,"2026-08-24",45644.229166666664,"2d, 23:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE 2 P93\r\nDossier de concertation validé en octobre 2023\r\nUPM: 527738",null,null,63339,"2024-11-05",1,"5,6"]
[null,"Infrabel","79187","Namur - Antwerpen","< >","VILVOORDE","Y.SCHAERBEEK-GROUPE G",2026,2026,35,35,"2026-08-24",45644.986111111109,"2026-08-28",45644.1875,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517853\r\n\r\nHerelektrificatie L27 tussen Vilvoorde en Areagrens (project TUC)",null,null,79187,"2024-10-24",0,"1,2,3,4,5"]
[null,"Infrabel","76339","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","FROYENNES",2026,2026,35,35,"2026-08-24",45644.944444444445,"2026-08-28",45644.215277777781,"4d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction d’un PS pour supprimer les PN 8 et 10 - Coffrages voiles côté rails \r\nUPM 531098",null,null,76339,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","81074","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.SOIGNIES",2026,2026,35,35,"2026-08-24",45644.954861111109,"2026-08-28",45644.1875,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.53 en P3 HKV\r\nRQ333: déplacée en sem 35 sans la nuit V^S pour permettre Z5 en sem 36",null,null,81074,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","75717","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2026,2026,35,35,"2026-08-24",45644.923611111109,"2026-08-28",45644.194444444445,"4d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53 P3",null,null,75717,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","84198","Athus - Meuse",">","GEDINNE","VONECHE",2026,2026,35,35,"2026-08-27",45644.333333333336,"2026-08-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,84198,"2024-11-26",0,"1,2,3,4,5"]
[null,"Infrabel","63718","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2026,2026,35,36,"2026-08-28",45644.979166666664,"2026-08-31",45644.201388888891,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER : Suppression du PN 45 à Ottignies et remplacement par un CSV - regulation contraintes  + bourrage de révision\r\n+Maintenance Z03.51\r\nUPM: 531625",null,null,63718,"2024-12-05",1,"5,6"]
[null,"Infrabel","63342","Athus - Meuse",">","HOUYET","BEAURAING",2026,2026,35,36,"2026-08-28",45644.25,"2026-08-31",45644.666666666664,"3d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE3 P93 Bourrage\r\nDossier de concertation validé en octobre 2023\r\nUPM:527740",null,null,63342,"2024-11-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","66354","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2026,2026,35,36,"2026-08-29",45644.25,"2026-08-31",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517253\r\n\r\nVervangen wisselonderdelen\r\n+ overwegen",null,null,66354,"2024-08-12",1,"5,6"]
[null,"Infrabel","82675","Lille - Charleroi","< >","GHLIN","MONS",2026,2026,35,35,"2026-08-29",45644.993055555555,"2026-08-30",45644.1875,"1d, 04:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.10.53\r\nMise HS nuit sam/dim\r\nRQ333: incompatible LGV\r\nPropo: WE 35",null,null,82675,"2024-12-12",0,"5,6"]
[null,"Infrabel","84854","Athus - Meuse","< >","NAMUR-HERBATTE","BOIS D'AUSSE",2026,2026,35,36,"2026-08-30",45644.958333333336,"2026-08-31",45644.208333333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur. (ZONE 7)\r\nZ7.43\r\n",null,null,84854,"2024-12-12",0,"5,6"]
[null,"Infrabel","64327","Lille - Charleroi",">","MANAGE","LUTTRE",2026,2026,36,38,"2026-08-31",45644.208333333336,"2026-09-14",45644.208333333336,"14d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Gare de Luttre - Phase 13\r\nTravaux Caténaire\r\nDossier de concertation validé en octobre 2023\r\nTCR 526917",null,null,64327,"2024-10-30",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","75819","Lille - Charleroi","< >","JURBISE","Y.LENS",2026,2026,36,36,"2026-08-31",45644.944444444445,"2026-09-04",45644.222222222219,"4d, 06:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z7..53 (mini) P3\r\nUPM 526907",null,null,75819,"2024-10-29",0,"1,2,3,4,5"]
[null,"Infrabel","79059","Namur - Antwerpen","< >","Y.NAZARETH","Y.NOORD DRIEHOEK AARSCHOT",2026,2026,36,36,"2026-09-01",45644.027777777781,"2026-09-04",45644.184027777781,"4d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-517758\r\n\r\nVernieuwen overweg\r\n+\r\nVernieuwen overweg 31bis naar type Harmellen",null,null,79059,"2024-08-19",0,"1,2,3,4,5"]
[null,"Infrabel","84561","Athus - Meuse",">","HALANZY","Y.AUBANGE",2026,2026,36,36,"2026-09-02",45644.333333333336,"2026-09-02",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,84561,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","84562","Athus - Meuse",">","HALANZY","Y.AUBANGE",2026,2026,36,36,"2026-09-03",45644.333333333336,"2026-09-03",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,84562,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","68649","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2026,2026,36,37,"2026-09-04",45644.979166666664,"2026-09-07",45644.197916666664,"2d, 05:15h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing aw's 18AR/18BR op Y Ruisbroek",null,null,68649,"2024-10-18",0,"5,6"]
[null,"Infrabel","63346","Athus - Meuse",">","HOUYET","BEAURAING",2026,2026,36,37,"2026-09-04",45644.25,"2026-09-07",45644.666666666664,"3d, 10:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE4 P93 Bourrage\r\nDossier de concertation validé en octobre 2023\r\nUPM:527745",null,null,63346,"2024-11-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","63347","Athus - Meuse","< >","HOUYET","BEAURAING",2026,2026,36,37,"2026-09-05",45644.25,"2026-09-07",45644.229166666664,"2d, 23:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nWE4 P93 Bourrage\r\nDossier de concertation validé en octobre 2023\r\nUPM: 527747",null,null,63347,"2024-11-05",1,"5,6"]
[null,"Infrabel","76139","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2026,2026,37,37,"2026-09-07",45644.333333333336,"2026-09-07",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 117 à 121 + faisceau manage\r\n dans les intervalles le lundi\r\nUPM: 531508",null,null,76139,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","69179","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,37,37,"2026-09-07",45644.965277777781,"2026-09-11",45644.166666666664,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-513224\r\nSaneren met kranen thv Y Ringlaan\r\n+ \r\nOnderhoud\r\n+\r\nonderhoud massificatie Tracks/SI\r\n\r\n* Y Bethune vrij\r\n* gevallen 29962 + 29959\r\n* R5/R6 in WE TLO",null,null,69179,"2024-06-24",0,"1,2,3,4,5"]
[null,"Infrabel","68682","Lille - ZeeBrugge","< >","BRUGGE","ZEDELGEM-ROOSTER E/G",2026,2026,37,37,"2026-09-07",45644.993055555555,"2026-09-11",45644.208333333336,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-512009\r\n\r\nVernieuwing wissels Brugge fase 5\r\nLossen KIROW\r\n\r\nTLO L66 Brugge SP VII + VIII tot Rooster Zedelgem\r\nDOES SP A L50D(1) Brugge SP VI tot Rooster E vrij\r\nDOES SP B L50A Brugge SP IX tot Y Stuyvenberg vrij\r\n\r\n+ Voorbereiding BVL voor wisselver",null,null,68682,"2024-06-11",0,"1,2,3,4,5"]
[null,"Infrabel","77892","Lille - Antwerpen","< >","GENT-SINT-PIETERS","Y.ZANDBERG",2026,2026,37,37,"2026-09-08",45644.013888888891,"2026-09-12",45644.173611111109,"5d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-511921\r\n\r\nMassificatie:  Y. Zandberg vrij.\r\n\r\nP783 perronverhogingen - De Pinte \r\n+\r\nonderhoud massificatie Tracks/SI\r\n",null,null,77892,"2024-06-11",0,"1,2,3,4,5"]
[null,"Infrabel","84239","Athus - Meuse",">","PALISEUL","GEDINNE",2026,2026,37,37,"2026-09-10",45644.333333333336,"2026-09-10",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VB\r\nEntretien voie",null,null,84239,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","76082","Lille - ZeeBrugge","< >","BRUGGE-ROOSTER E","BRUGGE",2026,2026,37,38,"2026-09-11",45644.993055555555,"2026-09-14",45644.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-511924\r\n\r\nVoorbereiding BVL voor wisselvernieuwing 14AI en 14BI.\r\n",null,null,76082,"2024-07-11",1,"5,6"]
[null,"Infrabel","66355","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2026,2026,37,38,"2026-09-12",45644.25,"2026-09-14",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517278\r\n\r\nOverwegen + kleine vernieuwingswerken",null,null,66355,"2024-08-12",1,"5,6"]
[null,"Infrabel","77462","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2026,2026,38,38,"2026-09-14",45644.958333333336,"2026-09-19",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRVB Aulnoye\r\nEn corrélation avec ID 63915\r\nTCR529385",null,null,77462,"2024-11-21",0,"1,2,3,4,5"]
[null,"Infrabel","63348","Athus - Meuse",">","HOUYET","BEAURAING",2026,2026,38,38,"2026-09-14",45644.333333333336,"2026-09-18",45644.666666666664,"5d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nFinitions P93 Bourrage révision, pistes, contraintes \r\nDossier de concertation validé en octobre 2023\r\nUPM: 527748",null,null,63348,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","69181","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,38,38,"2026-09-14",45644.965277777781,"2026-09-18",45644.166666666664,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-513223                                                                                                                                                                                                                                                     ",null,null,69181,"2024-06-24",0,"1,2,3,4,5"]
[null,"Infrabel","83769","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2026,2026,38,38,"2026-09-14",45644.947916666664,"2026-09-19",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z05.32\r\nInclusief Eeklo alle perronsporen (I, II en III) \r\n",null,null,83769,"2024-12-04",0,"1,2,3,4,5"]
[null,"Infrabel","84407","Athus - Meuse",">","VIRTON","SIGNEULX",2026,2026,38,38,"2026-09-15",45644.333333333336,"2026-09-15",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,84407,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","67968","Lille - Charleroi","< >","SILLY","ENGHIEN",2026,2026,38,38,"2026-09-15",45644.020833333336,"2026-09-19",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67968,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","80033","Namur - Antwerpen",">","NAMUR","RHISNES",2026,2026,38,38,"2026-09-18",45644.958333333336,"2026-09-19",45644.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,80033,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","80040","Namur - Antwerpen","< >","NAMUR","RONET",2026,2026,38,38,"2026-09-19",45644.958333333336,"2026-09-20",45644.21875,"1d, 06:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance AW et interventions diverses en gare de Namur ZONE 6\r\nZ6.43\r\nPériodicité toutes les 8 semaines (alternance avec la zone 10) 6 fois sur l'année",null,null,80040,"2024-12-12",0,"5,6"]
[null,"Infrabel","76724","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,38,38,"2026-09-19",45644.25,"2026-09-20",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z02.51 P4\r\nTCR529391\r\nEn corrélation ID 77467 // Tx SNCF",null,null,76724,"2024-12-11",1,"5,6"]
[null,"Infrabel","76336","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2026,2026,39,39,"2026-09-21",45644.958333333336,"2026-09-25",45644.173611111109,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Préparations pour renouvellement de la chape et pose de passerelle au PI 100.327\r\nTCR 529413",null,null,76336,"2024-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","79447","Erquelinnes - Montzen","< >","FLEMALLE-HAUTE","Y.RENORY",2026,2026,39,40,"2026-09-21",45644.958333333336,"2026-10-03",45644.208333333336,"12d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Bourrage de révision, contraintes, finitions,...\r\nUPM 530200",null,null,79447,"2024-11-26",0,"1,2,3,4,5"]
[null,"Infrabel","69408","Lille - Charleroi",">","BRUXELLES-MIDI","Y.RUISBROEK",2026,2026,39,39,"2026-09-21",45644.979166666664,"2026-09-26",45644.1875,"5d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing aw's 18AR/18BR op Y Ruisbroek: afwerkingsnachten",null,null,69408,"2024-10-24",0,"1,2,3,4,5"]
[null,"Infrabel","69183","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,39,39,"2026-09-21",45644.965277777781,"2026-09-25",45644.166666666664,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-513227\r\nSaneren met kranen thv Y Ringlaan\r\n+ \r\nOnderhoud\r\n\r\n* Y Bethune vrij\r\n* gevallen 29962 + 29959\r\n* R5/R6 in WE TLO",null,null,69183,"2024-06-24",0,"1,2,3,4,5"]
[null,"Infrabel","40058","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2026,2026,39,39,"2026-09-21",45644.965277777781,"2026-09-25",45644.229166666664,"4d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PI 37.804 pour élargissement du passage sous l'ouvrage et construction d'un CSV en gare pour la suppression du PN 65\r\n+ Remplacement des appuis du PS 117 et renouvellement de la chape d'étanchéité\r\nTCR 529964",null,null,40058,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","80952","Lille - Charleroi","< >","HALLE","ATH",2026,2026,39,39,"2026-09-21",45644.944444444445,"2026-09-26",45644.180555555555,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z9.54 + Z10.54\r\n+massifié PLP\r\nRQ333 : incompatible CBP L96\r\nPropos : sem 39\r\n",null,null,80952,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","75718","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2026,2026,39,39,"2026-09-21",45644.923611111109,"2026-09-26",45644.194444444445,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53 P3\r\nRQ333: incompatible CBP\r\nPropo: sem 39 (massifié avec chantier prép caténaire)",null,null,75718,"2024-11-25",0,"1,2,3,4,5"]
[null,"Infrabel","74985","Erquelinnes - Montzen","< >","FROIDMONT","VISE-FRONTIERE",2026,2026,39,39,"2026-09-22",45644.958333333336,"2026-09-25",45644.208333333336,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux d'entretien en P3 HKV avec MHT\r\nCTL de nuit allongé de 06h00\r\nTrilatéral en attente",null,null,74985,"2024-04-10",0,"1,2,3,4,5"]
[null,"Infrabel","84014","Athus - Meuse",">","DINANT","YVOIR",2026,2026,39,39,"2026-09-22",45644.388888888891,"2026-09-22",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VB (périodicité 6 semaines)",null,null,84014,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","64134","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","LA SAMBRE",2026,2026,39,40,"2026-09-25",45644.958333333336,"2026-09-28",45644.173611111109,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de la chape et pose de passerelle au PI 100.327\r\nTCR 529435\r\nEn corrélation TX SNCF ID 77466",null,null,64134,"2024-12-11",1,"5,6"]
[null,"Infrabel","69184","Lille - Antwerpen","< >","Y.BETHUNE","MOUSCRON-FRONTIERE",2026,2026,39,40,"2026-09-25",45644.965277777781,"2026-09-28",45644.166666666664,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-512089\r\n\r\nSaneren met kranen thv Y Ringlaan\r\n+ \r\nOnderhoud\r\n\r\n* Y Bethune vrij\r\n* gevallen 29962 + 29959",null,null,69184,"2024-06-12",1,"5,6"]
[null,"Infrabel","78809","Lille - Charleroi","< >","Y.NOORD HALLE","SAINTES",2026,2026,39,40,"2026-09-25",45644.986111111109,"2026-09-28",45644.177083333336,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken zone FH_10 volgens onderhoudskalender",null,null,78809,"2024-10-24",1,"5,6"]
[null,"Infrabel","74369","Lille - Charleroi","< >","ROUX","MARCHIENNE-AU-PONT",2026,2026,39,40,"2026-09-26",45644.208333333336,"2026-09-28",45644.208333333336,"2d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Pose nouvelles traverses, consoles, CT, FO, sur 124A\r\nTCR530048",null,null,74369,"2024-11-25",1,"5,6"]
[null,"Infrabel","80063","Athus - Meuse","< >","NAMUR","LUSTIN",2026,2026,39,40,"2026-09-26",45644.9375,"2026-09-28",45644.180555555555,"2d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Entretien AS, traitement zone boueuse.\r\nSAVU de jour (CoLT 75560) + CTL de nuit\r\nUPM: 527596",null,null,80063,"2024-11-04",0,"5,6"]
[null,"Infrabel","84065","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2026,2026,39,39,"2026-09-26",45644.347222222219,"2026-09-26",45644.638888888891,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VA (périodicité 3 semaines)",null,null,84065,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","84066","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2026,2026,39,39,"2026-09-27",45644.34375,"2026-09-27",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)",null,null,84066,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","72393","Erquelinnes - Montzen","< >","STATTE","FLEMALLE-HAUTE",2026,2026,40,40,"2026-09-28",45644.958333333336,"2026-10-03",45644.194444444445,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Projet du CSV PMR de Huy",null,null,72393,"2023-12-21",0,"1,2,3,4,5"]
[null,"Infrabel","82321","Lille - Antwerpen",">","OOSTAKKER","Y.BERNADETTESTRAAT",2026,2026,40,40,"2026-09-28",45644.965277777781,"2026-10-03",45644.1875,"5d, 05:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Onderhoudszone Z04.32\r\n",null,null,82321,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","79852","Lille - Charleroi","< >","BRAINE-LE-COMTE","MANAGE",2026,2026,40,40,"2026-09-28",45644.965277777781,"2026-10-03",45644.229166666664,"5d, 06:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z9.52 + Maintenance Z.3.53 en P3 HKV\r\nRQ333: incompatble CBP\r\nPropo: sem 40 massifié avec colt 74820 (CTL renouvellement PI, chape, construction CSV pour Xion PN65)",null,null,79852,"2024-12-13",0,"1,2,3,4,5"]
[null,"Infrabel","69088","Namur - Antwerpen","< >","OTTIGNIES","WAVRE",2026,2026,40,40,"2026-09-28",45644.986111111109,"2026-10-02",45644.215277777781,"4d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"chantier RER - dépose liaison L139 + raccordement chantier\r\nUPM: 530774",null,null,69088,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","84050","Athus - Meuse",">","Y.NEFFE","DINANT",2026,2026,40,40,"2026-09-29",45644.333333333336,"2026-09-29",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITES VB",null,null,84050,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","78073","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2026,2026,40,40,"2026-10-01",45644.395833333336,"2026-10-01",45644.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53.P2\r\n",null,null,78073,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","75427","Lille - Charleroi","< >","Y.JURBISE","MONS",2026,2026,40,40,"2026-10-03",45644.25,"2026-10-04",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z05.53 P4+",null,null,75427,"2024-09-10",1,"5,6"]
[null,"Infrabel","63754","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,40,40,"2026-10-03",45644.25,"2026-10-04",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 11 + 12\r\nPlacement loges PLP +  loges PNs",null,null,63754,"2024-03-05",1,"5,6"]
[null,"Infrabel","82826","Lille - ZeeBrugge","< >","BRUGGE","BLANKENBERGE",2026,2026,40,40,"2026-10-04",45644.006944444445,"2026-10-04",45644.229166666664,"1d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudswerken station FR - L51 -L51A - L51B\r\n",null,null,82826,"2024-12-13",0,"5,6"]
[null,"Infrabel","78579","Erquelinnes - Montzen",">","FLEMALLE-HAUTE","Y.RENORY",2026,2026,41,41,"2026-10-05",45644.958333333336,"2026-10-10",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rectification courbe Val-St-Lambert\r\nTravaux caténaires\r\nUPM 530373",null,null,78579,"2024-11-26",0,"1,2,3,4,5"]
[null,"Infrabel","78455","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2026,2026,41,41,"2026-10-05",45644.958333333336,"2026-10-10",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRB/RT Requignies\r\nGare de Jeumont fermée\r\nEn corrélation avec ID74674\r\nTCR 529473",null,null,78455,"2024-11-21",0,"1,2,3,4,5"]
[null,"Infrabel","68413","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,41,41,"2026-10-05",45644.979166666664,"2026-10-10",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-513597\r\n\r\nMasterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Si",null,null,68413,"2024-06-27",0,"1,2,3,4,5"]
[null,"Infrabel","76341","Lille - Charleroi","< >","BLANDAIN-FRONTIERE","FROYENNES",2026,2026,41,41,"2026-10-05",45644.944444444445,"2026-10-09",45644.215277777781,"4d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Construction d’un PS pour supprimer les PN 8 et 10 - Décoffrages voiles côté rails \r\nUPM 531076",null,null,76341,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","79895","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,41,41,"2026-10-05",45644.993055555555,"2026-10-10",45644.177083333336,"5d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,79895,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","76051","Namur - Antwerpen",">","GEMBLOUX","GEMBLOUX",2026,2026,41,41,"2026-10-05",45644.319444444445,"2026-10-05",45644.645833333336,"1d, 07:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie Gembloux gare + maintenance infrastructure + contrôles",null,null,76051,"2024-03-26",0,"1,2,3,4,5"]
[null,"Infrabel","84200","Athus - Meuse",">","GEDINNE","VONECHE",2026,2026,41,41,"2026-10-08",45644.333333333336,"2026-10-08",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB\r\nEntretien voie",null,null,84200,"2024-11-26",0,"1,2,3,4,5"]
[null,"Infrabel","83970","Athus - Meuse",">","LUSTIN","JAMBES",2026,2026,41,41,"2026-10-09",45644.385416666664,"2026-10-09",45644.635416666664,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VB\r\nRQ333: en R5 (ald R7) ok ? ",null,null,83970,"2024-11-14",0,"5,6"]
[null,"Infrabel","75298","Lille - Charleroi",">","LUTTRE","ROUX",2026,2026,41,41,"2026-10-10",45644.25,"2026-10-11",45644.708333333336,"1d, 11:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance Z05.52 P4\r\nTCR530074",null,null,75298,"2024-11-25",0,"5,6"]
[null,"Infrabel","64902","Namur - Antwerpen","< >","TAMINES","NAMUR",2026,2026,41,42,"2026-10-10",45644.25,"2026-10-12",45644.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux en face inférieure des OA 79.750 et 81.981 - WE CTL\r\n+ Maintenance Z19.51\r\n+ déroulage caténraire L130 VB BK 78760 à 75115\r\nUPM: 528560",null,null,64902,"2024-11-20",1,"5,6"]
[null,"Infrabel","63517","Athus - Meuse","< >","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,41,42,"2026-10-10",45644.25,"2026-10-12",45644.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Traitement zone boueuse voie A L 165 BK 91.000 (90m).\r\nUPM: 528524\r\nRQ333: intégrer visites VA+VB ok ? ",null,null,63517,"2024-11-08",1,"5,6"]
[null,"Infrabel","82274","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2026,2026,41,42,"2026-10-11",45644.03125,"2026-10-12",45644.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud bovenleiding\r\nmin 14 prestaties, gespreid over het jaar,\r\nsp A of sp B\r\nHKV\r\nNacht R6^R7 van 00u45 tot 06u00",null,null,82274,"2024-11-14",0,"5,6"]
[null,"Infrabel","78456","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2026,2026,42,42,"2026-10-12",45644.958333333336,"2026-10-17",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRB/RT Requignies\r\nGare de Jeumont fermée\r\nCorrélation ID 74675\r\nTCR529475",null,null,78456,"2024-11-21",0,"1,2,3,4,5"]
[null,"Infrabel","64684","Lille - Charleroi","< >","ENGHIEN","Y.LE COUCOU",2026,2026,42,42,"2026-10-12",45644.9375,"2026-10-16",45644.208333333336,"4d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage entre Enghien et Silly C75\r\nPréparations\r\n+massifié PLP\r\nUPM 530928",null,null,64684,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","79894","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,42,42,"2026-10-12",45644.993055555555,"2026-10-16",45644.176388888889,"4d, 04:24h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,79894,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","84566","Athus - Meuse",">","HALANZY","Y.AUBANGE",2026,2026,42,42,"2026-10-13",45644.333333333336,"2026-10-13",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,84566,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","64257","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2026,2026,42,44,"2026-10-16",45644.958333333336,"2026-10-26",45644.173611111109,"9d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Pose 2nd tablier Ponts 8 et 10\r\nTCR 529460",null,null,64257,"2024-12-05",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","63693","Erquelinnes - Montzen","< >","FROIDMONT","VISE",2026,2026,42,43,"2026-10-17",45644.958333333336,"2026-10-19",45644.208333333336,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Interventions sur liaisons \r\nFaisceau Bressoux compris (restera 3 voies disponibles selon besoins)\r\n",null,null,63693,"2024-09-06",0,"5,6"]
[null,"Infrabel","66543","Namur - Antwerpen",">","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2026,2026,42,43,"2026-10-17",45644.958333333336,"2026-10-19",45644.166666666664,"2d, 05:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Beveiliging voor onderstaande werken:\r\nwerken SIG (schets 2), Werken aan wissels Y Arendstraat en Antwerpen Centraal -2.",null,null,66543,"2024-10-21",0,"5,6"]
[null,"Infrabel","66304","Erquelinnes - Montzen","< >","FROIDMONT","BRESSOUX",2026,2026,42,43,"2026-10-17",45644.229166666664,"2026-10-19",45644.208333333336,"2d, 23:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du MDS VA \r\n+ Massification\r\n+ Maintenance Z8.42 AI 42\r\nEntretien mécanisé et manuel des AS du grill de Bressoux côté froitmond\r\nEntretien tunnel",null,null,66304,"2024-09-12",1,"5,6"]
[null,"Infrabel","76140","Namur - Antwerpen",">","OTTIGNIES","LA ROCHE(BRABANT)",2026,2026,43,43,"2026-10-19",45644.333333333336,"2026-10-19",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie + maintenance infrastructure + contrôles\r\nVisite de la L140 jusqu'à la BK 30.050+ visites des voies 117 à 121 + faisceau manage\r\n dans les intervalles le lundi\r\nUPM: 531518",null,null,76140,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","55887","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2026,2026,43,43,"2026-10-19",45644.9375,"2026-10-24",45644.173611111109,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 6 - finitions\r\nPhase 6.2 – CTL L75A+Faisceau de nuit de semaine​",null,null,55887,"2023-10-17",0,"1,2,3,4,5"]
[null,"Infrabel","84243","Athus - Meuse",">","PALISEUL","GEDINNE",2026,2026,43,43,"2026-10-20",45644.333333333336,"2026-10-20",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VB\r\nEntretien voie",null,null,84243,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","84387","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2026,2026,43,43,"2026-10-21",45644.333333333336,"2026-10-21",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,84387,"2024-12-05",0,"5,6"]
[null,"Infrabel","84256","Athus - Meuse",">","PALISEUL","BERTRIX",2026,2026,43,43,"2026-10-22",45644.333333333336,"2026-10-22",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VA\r\nEntretien voie",null,null,84256,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","80034","Namur - Antwerpen",">","NAMUR","RHISNES",2026,2026,43,43,"2026-10-23",45644.958333333336,"2026-10-24",45644.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,80034,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","84257","Athus - Meuse",">","BERTRIX","PALISEUL",2026,2026,43,43,"2026-10-23",45644.333333333336,"2026-10-23",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VB\r\nEntretien voie",null,null,84257,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","84019","Athus - Meuse",">","YVOIR","LUSTIN",2026,2026,43,43,"2026-10-23",45644.375,"2026-10-23",45644.625,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VB (périodicité 6 semaines)\r\n",null,null,84019,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","66336","Namur - Antwerpen","< >","Y.LUCHTBAL","Y.HOLLAND",2026,2026,43,44,"2026-10-24",45644.25,"2026-10-26",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517284\r\n\r\nOosterweel: \r\noverpakken bruggen en impact bemaling",null,null,66336,"2024-08-12",1,"5,6"]
[null,"Infrabel","84408","Athus - Meuse",">","VIRTON","SIGNEULX",2026,2026,44,44,"2026-10-26",45644.333333333336,"2026-10-26",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,84408,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","82962","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,44,44,"2026-10-26",45644.208333333336,"2026-10-30",45644.958333333336,"6d, 18:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF",null,null,82962,"2024-10-18",0,"1,2,3,4,5"]
[null,"Infrabel","84409","Athus - Meuse",">","VIRTON","SIGNEULX",2026,2026,44,44,"2026-10-27",45644.333333333336,"2026-10-27",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,84409,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","78074","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2026,2026,44,44,"2026-10-29",45644.395833333336,"2026-10-29",45644.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53.P2\r\n",null,null,78074,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","78583","Namur - Antwerpen","< >","Y.MELLE-WEST","Y.WEST DRIEHOEK LEDEBERG",2026,2026,44,45,"2026-10-30",45644.993055555555,"2026-11-03",45644.173611111109,"3d, 04:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-512694\r\n\r\nverlijmen van wissels ter hoogte van Y. Oost + vervangen van spoorstaven en gebroken isolatoren + onderstoppen op absolute basis van de wissels met 2 unimats",null,null,78583,"2024-09-18",1,"5,6"]
[null,"Infrabel","63893","Lille - Charleroi","< >","ROUX","Y.NORD",2026,2026,44,44,"2026-10-30",45644.961805555555,"2026-11-01",45644.208333333336,"2d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi-Central- Phase 2.35\r\nComplément du CoLT 63889 pour aller jusque Y.La Sambre compris\r\nExtension Nuit L124A\r\nDossier de concertation\r\nTCR 520164 + 520185",null,null,63893,"2024-11-25",0,"5,6"]
[null,"Infrabel","69216","Namur - Antwerpen","< >","DENDERMONDE","SCHELLEBELLE",2026,2026,44,45,"2026-10-31",45644.006944444445,"2026-11-02",45644.194444444445,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-513457\r\nVernieuwen 07D-10AD-12D-13D-10BD/11D \r\n\r\nBuiten dienst \r\nSP A+B Schellebelle - Dendermonde\r\nRooster Dendermonde kant Gent\r\nPerronspoor IV tem VII\r\nRooster bundel G kant Gent\r\nDoodspoor 108\r\nBuiten spanning\r\n29622-29628-29630-29664-29662-29660",null,null,69216,"2024-07-11",1,"5,6"]
[null,"Infrabel","66643","Namur - Antwerpen","< >","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2026,2026,44,46,"2026-10-31",45644.166666666664,"2026-11-09",45644.166666666664,"9d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-517887\r\n\r\nHerelektrificatie L27 :  Herfstvakantie \r\nOVK Klokkestraat",null,null,66643,"2024-08-20",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","61852","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,45,45,"2026-11-02",45644.958333333336,"2026-11-07",45644.239583333336,"5d, 06:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation \r\n\r\nPhase 6 - finitions\r\nPhase 6.1 – CTL L75 de nuit de semaine",null,null,61852,"2023-10-03",0,"1,2,3,4,5"]
[null,"Infrabel","82963","Lille - Antwerpen","< >","MOUSCRON","MOUSCRON-FRONTIERE",2026,2026,45,45,"2026-11-02",45644.208333333336,"2026-11-06",45644.958333333336,"6d, 18:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF",null,null,82963,"2024-10-18",0,"1,2,3,4,5"]
[null,"Infrabel","74370","Lille - Charleroi",">","ROUX","Y.NORD",2026,2026,45,45,"2026-11-02",45644.375,"2026-11-06",45644.666666666664,"4d, 07:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Réalisation dés, coupage poteaux… EL (Entreligne) \r\nEn corrélation avec Colt 80158 (Voie B L124 Nuits FCR FRX)\r\nTCR530614",null,null,74370,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","69217","Namur - Antwerpen","< >","DENDERMONDE","SCHELLEBELLE",2026,2026,45,45,"2026-11-03",45644.006944444445,"2026-11-06",45644.194444444445,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-513434\r\nVernieuwen wissels 08D en 09D - afwerking\r\nVernieuwen 07D-10AD-12D-13D-10BD/11D - voorbereiding\r\n\r\nBuiten dienst \r\nSP A+B Schellebelle - Dendermonde\r\nRooster Dendermonde kant Gent\r\nPerronspoor IV tem VII\r\nRooster bundel G kant Gent\r\nDoodspoor ",null,null,69217,"2024-06-26",0,"1,2,3,4,5"]
[null,"Infrabel","78673","Lille - ZeeBrugge","< >","LICHTERVELDE","BRUGGE",2026,2026,45,45,"2026-11-03",45644.979166666664,"2026-11-07",45644.215277777781,"4d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-512017\r\n\r\nonderhoud massificatie Tracks/SI - Perronsporen Brugge - Lichtervelde  niet in.\r\nnacht 56 tot 06u50",null,null,78673,"2024-06-17",0,"1,2,3,4,5"]
[null,"Infrabel","84069","Athus - Meuse",">","GENDRON-CELLES","ANSEREMME",2026,2026,45,45,"2026-11-03",45644.34375,"2026-11-03",45644.65625,"1d, 07:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB (périodicité 3 semaines)\r\nRQ333: SAVU Dinant - Y. Neffe (63077) en // --> croisement à adapter à Gendron",null,null,84069,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","72329","Lille - Charleroi","< >","ENGHIEN","Y.LE COUCOU",2026,2026,45,46,"2026-11-06",45644.9375,"2026-11-09",45644.208333333336,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Criblage entre Enghien et Silly C75\r\nUPM 530940",null,null,72329,"2024-11-29",1,"5,6"]
[null,"Infrabel","69218","Namur - Antwerpen","< >","DENDERMONDE","SCHELLEBELLE",2026,2026,45,46,"2026-11-07",45644.006944444445,"2026-11-09",45644.194444444445,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-513458\r\nVernieuwen 07D-10AD-12D-13D-10BD/11D \r\n\r\nBuiten dienst \r\nSP A+B Schellebelle - Dendermonde\r\nRooster Dendermonde kant Gent\r\nPerronspoor IV tem VII\r\nRooster bundel G kant Gent\r\nDoodspoor 108\r\nBuiten spanning\r\n29622-29628-29630-29664-29662-29660",null,null,69218,"2024-07-11",1,"5,6"]
[null,"Infrabel","84024","Athus - Meuse",">","YVOIR","DINANT",2026,2026,45,45,"2026-11-07",45644.388888888891,"2026-11-07",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"VISITE VA (périodicité 6 semaines)\r\n",null,null,84024,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","78417","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2026,2026,46,46,"2026-11-09",45644.958333333336,"2026-11-13",45644.208333333336,"4d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,78417,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","63389","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","LEMAN",2026,2026,46,46,"2026-11-09",45644.958333333336,"2026-11-14",45644.204861111109,"5d, 05:55h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement P93 \r\nBourrage de révision, contraintes",null,null,63389,"2024-06-12",0,"1,2,3,4,5"]
[null,"Infrabel","68418","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,46,46,"2026-11-09",45644.979166666664,"2026-11-14",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-513687\r\n\r\nMasterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Si",null,null,68418,"2024-06-27",0,"1,2,3,4,5"]
[null,"Infrabel","61853","Lille - Charleroi","< >","MOUSCRON","FROYENNES",2026,2026,46,46,"2026-11-09",45644.9375,"2026-11-14",45644.173611111109,"5d, 05:40h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du PS \"Pont du Phoenix\" situé au km 54.566 des L75&L75A + Faisceau de Mouscron\r\nDossier de concertation\r\n\r\nPhase 6 - finitions\r\nPhase 6.2 – CTL L75A+Faisceau de nuit de semaine​",null,null,61853,"2024-09-13",0,"1,2,3,4,5"]
[null,"Infrabel","79893","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2026,2026,46,46,"2026-11-09",45644.993055555555,"2026-11-13",45644.177083333336,"4d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3 \r\nTronçon Gembloux - Rhisnes \r\nTravaux de modernisation (petit GC)",null,null,79893,"2024-07-05",0,"1,2,3,4,5"]
[null,"Infrabel","72251","Lille - Charleroi","< >","ENGHIEN","Y.LE COUCOU",2026,2026,46,46,"2026-11-10",45644.020833333336,"2026-11-14",45644.180555555555,"5d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage entre Enghien et Silly C75\r\nFinitions + BNDR\r\n+massifié PLP\r\nUPM 530954",null,null,72251,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","68680","Lille - ZeeBrugge","< >","BRUGGE","BRUGGE-ROOSTER E",2026,2026,46,47,"2026-11-13",45644.993055555555,"2026-11-16",45644.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-506608\r\nVernieuwing wissels Brugge fase 5\r\n\r\nTLO L66 Brugge SP VII + VIII tot Rooster E vrij\r\nDOES SP A L50D(1) Brugge SP VI tot Rooster E vrij\r\nDOES SP B L50A Brugge SP IX tot Y Stuyvenberg vrij\r\n\r\nperron VI-VII-VIII buiten spanning.",null,null,68680,"2024-04-23",1,"5,6"]
[null,"Infrabel","69244","Namur - Antwerpen",">","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,46,47,"2026-11-14",45644.027777777781,"2026-11-16",45644.166666666664,"2d, 03:20h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"R-513795\r\n\r\nBundel centraal Merelbeke\r\naansluiting nieuwe sporen 5-6-7-8 van bundel centraal + aansluiten aan L50E\r\nBuiten dienst;\r\nBundel Centraal volledig\r\nL50E SP B\r\nL58 SP B\r\nBuiten spanning;\r\n29170 - 29168 - 29166 - 29154 - 29184 - 29182 - 29187 - ",null,null,69244,"2024-06-28",0,"5,6"]
[null,"Infrabel","74445","Namur - Antwerpen",">","BAKENBOS","OTTIGNIES",2026,2026,47,47,"2026-11-16",45644.958333333336,"2026-11-21",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement C75\r\nDossier de concertation validé en octobre 2023",null,null,74445,"2024-08-20",0,"1,2,3,4,5"]
[null,"Infrabel","68419","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,47,47,"2026-11-16",45644.979166666664,"2026-11-21",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-513689\r\n\r\nMasterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Si",null,null,68419,"2024-06-27",0,"1,2,3,4,5"]
[null,"Infrabel","84609","Athus - Meuse","< >","Y.AUBANGE","ATHUS",2026,2026,47,47,"2026-11-16",45644.385416666664,"2026-11-16",45644.65625,"1d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance\r\nVisite voie",null,null,84609,"2024-12-09",0,"1,2,3,4,5"]
[null,"Infrabel","79577","Lille - Charleroi","< >","JURBISE","ATH",2026,2026,47,48,"2026-11-16",45644.923611111109,"2026-11-27",45644.215277777781,"11d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nUPM 526846",null,null,79577,"2024-10-29",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","69221","Namur - Antwerpen","< >","DENDERMONDE","SCHELLEBELLE",2026,2026,47,47,"2026-11-17",45644.006944444445,"2026-11-21",45644.194444444445,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-513436\r\nVernieuwen wissels 08D en 09D - afwerking\r\nVernieuwen 07D-10AD-12D-13D-10BD/11D - voorbereiding\r\n\r\nBuiten dienst \r\nSP A+B Schellebelle - Dendermonde\r\nRooster Dendermonde kant Gent\r\nPerronspoor IV tem VII\r\nRooster bundel G kant Gent\r\nDoodspoor ",null,null,69221,"2024-06-26",0,"1,2,3,4,5"]
[null,"Infrabel","84105","Athus - Meuse",">","BEAURAING","HOUYET",2026,2026,47,47,"2026-11-18",45644.388888888891,"2026-11-18",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"visite et interventions diverses VB ",null,null,84105,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","80035","Namur - Antwerpen",">","NAMUR","RHISNES",2026,2026,47,47,"2026-11-20",45644.958333333336,"2026-11-21",45644.215277777781,"1d, 06:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance en gare de Namur ZONE 5",null,null,80035,"2024-12-12",0,"1,2,3,4,5"]
[null,"Infrabel","65762","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2026,2026,47,48,"2026-11-20",45644.958333333336,"2026-11-23",45644.1875,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Namur\r\n+ Visite de voie Rhisnes - Namur",null,null,65762,"2024-03-26",1,"5,6"]
[null,"Infrabel","84087","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2026,2026,47,47,"2026-11-20",45644.388888888891,"2026-11-20",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB\r\n",null,null,84087,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","65824","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2026,2026,47,47,"2026-11-21",45644.25,"2026-11-22",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.51 P4\r\n+Rnvlt PI km 85.708 Rvlt - Pieux (WE3)\r\nUPM: 528671",null,null,65824,"2024-11-14",1,"5,6"]
[null,"Infrabel","78884","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","WATERMAEL",2026,2026,47,48,"2026-11-21",45644.003472222219,"2026-11-23",45644.201388888891,"3d, 04:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing station Etterbeek B-ST: Sporen 1-2-3-4\r\nNacht vrijdag/zaterdag tussen 00u05 en 05u20\r\nNacht zaterdag/zondag tussen 00u40 en 05u20\r\nNacht zondag/maandag tussen 00u40 en 04u50",null,null,78884,"2024-10-25",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","77545","Namur - Antwerpen",">","SINT-JORIS-WEERT","WAVRE",2026,2026,47,47,"2026-11-22",45644.333333333336,"2026-11-22",45644.625,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de Voie L139 Sint-Joris-weert - Wavre VA/VB\r\nUPM: 530246",null,null,77545,"2024-11-26",0,"5,6"]
[null,"Infrabel","80068","Lille - Charleroi","< >","ROUX","MARCHIENNE-AU-PONT",2026,2026,48,48,"2026-11-23",45644.958333333336,"2026-11-27",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux caténaires\r\nRenouvellement 1 cat. 51C, voie A/124A, CT, FO, T EL…\r\nEn corrélation avec ID 74373 + 72149\r\nTCR530603\r\n",null,null,80068,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","78462","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2026,2026,48,48,"2026-11-23",45644.958333333336,"2026-11-28",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRB/RT Requignies\r\nGare de Jeumont fermée\r\nTCR529540",null,null,78462,"2024-11-21",0,"1,2,3,4,5"]
[null,"Infrabel","69828","Erquelinnes - Montzen",">","KINKEMPOIS-BLOCK 2","Y.RENORY",2026,2026,48,49,"2026-11-23",45644.208333333336,"2026-12-04",45644.916666666664,"12d, 17:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage du ballast C75\r\nUPM 530465\r\nPas de CTL nuit WE 48 cf travaux L43 (28^29/11) ok",null,null,69828,"2024-11-27",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","83772","Namur - Antwerpen","< >","GENT-DAMPOORT","EEKLO",2026,2026,48,48,"2026-11-23",45644.947916666664,"2026-11-28",45644.1875,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoudszone Z05.32\r\nInclusief Eeklo alle perronsporen (I, II en III) \r\n",null,null,83772,"2024-12-04",0,"1,2,3,4,5"]
[null,"Infrabel","84568","Athus - Meuse",">","HALANZY","Y.AUBANGE",2026,2026,48,48,"2026-11-24",45644.333333333336,"2026-11-24",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,84568,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","67977","Lille - Charleroi","< >","SILLY","ENGHIEN",2026,2026,48,48,"2026-11-24",45644.020833333336,"2026-11-28",45644.208333333336,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"PLP",null,null,67977,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","78075","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2026,2026,48,48,"2026-11-26",45644.395833333336,"2026-11-26",45644.645833333336,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z.6.53.P2\r\n",null,null,78075,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","74448","Lille - Charleroi",">","ROUX","MARCHIENNE-AU-PONT",2026,2026,48,49,"2026-11-27",45644.958333333336,"2026-11-30",45644.208333333336,"2d, 06:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Transfert 1 cat. 51D, voie B/124A, CT, FO, T…\r\nEn corrélation avec ID 80071\r\nTCR530632",null,null,74448,"2024-11-28",0,"5,6"]
[null,"Infrabel","77465","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2026,2026,48,49,"2026-11-27",45644.958333333336,"2026-11-30",45644.197916666664,"2d, 05:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRB/RT Requignies\r\nGare de Jeumont fermée\r\nTCR529602",null,null,77465,"2024-11-21",1,"5,6"]
[null,"Infrabel","65764","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2026,2026,48,49,"2026-11-27",45644.993055555555,"2026-11-30",45644.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Namur",null,null,65764,"2024-06-20",1,"5,6"]
[null,"Infrabel","74436","Namur - Antwerpen",">","Y.WEERDE","MECHELEN",2026,2026,48,49,"2026-11-28",45644.020833333336,"2026-11-30",45644.166666666664,"3d, 03:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"R-518121\r\n\r\nMasterplan Mechelen\r\nBijkomend bij 71420 tijdens nacht",null,null,74436,"2024-09-10",0,"5,6"]
[null,"Infrabel","66315","Erquelinnes - Montzen","< >","BRESSOUX","VISE",2026,2026,48,48,"2026-11-28",45644.25,"2026-11-29",45644.916666666664,"2d, 16:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement PN 11 + 12 \r\n+ Massification Z9.42\r\nEntretien mécanisé et manuel des AS de Bressoux côté Visé et AS des d'entrée de Visé et/ou entretien de PN\r\n\r\n",null,null,66315,"2024-08-09",1,"5,6"]
[null,"Infrabel","65064","Namur - Antwerpen",">","CHATELET","CHATELET-GRIL EST",2026,2026,49,49,"2026-11-30",45644.958333333336,"2026-12-01",45644.208333333336,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 4.3.1 - Coupure type 10\r\nUPM: 531772",null,null,65064,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","78463","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2026,2026,49,49,"2026-11-30",45644.958333333336,"2026-12-05",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRB/RT Requignies\r\nGare de Jeumont fermée\r\nTCR529605",null,null,78463,"2024-11-21",0,"1,2,3,4,5"]
[null,"Infrabel","84244","Athus - Meuse",">","GEDINNE","PALISEUL",2026,2026,49,49,"2026-11-30",45644.333333333336,"2026-11-30",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VA\r\nEntretien voie",null,null,84244,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","68421","Namur - Antwerpen","< >","GENT-SINT-PIETERS","Y.WEST DRIEHOEK LEDEBERG",2026,2026,49,49,"2026-11-30",45644.979166666664,"2026-12-05",45644.180555555555,"5d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"R-513691\r\n\r\nMasterplan Gent Sint Pieters Stap 36\r\nVoorbereiding bedding spoor I + plaatsen bovenleidingspalen\r\n\r\nBuiten dienst\r\nPerronsporen I tot en met VIII inbegrepen\r\nTLO L50A6 tussen Gent Sint Pieters tot Y Snepbrug niet in\r\nTLO L50E tussen Gent Si",null,null,68421,"2024-06-27",0,"1,2,3,4,5"]
[null,"Infrabel","80969","Lille - Charleroi","< >","TOURNAI","BLANDAIN-FRONTIERE",2026,2026,49,49,"2026-11-30",45644.944444444445,"2026-12-05",45644.173611111109,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z2.54\r\n+ Maintenance Z7.54 P3 HKM\r\nRQ333 : incompatible CBP\r\nPropos : sem 49",null,null,80969,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","84390","Athus - Meuse",">","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2026,2026,49,49,"2026-12-01",45644.333333333336,"2026-12-01",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,84390,"2024-12-05",0,"5,6"]
[null,"Infrabel","79205","Lille - Antwerpen","< >","Y.ANTWERPEN-ZUID","SINT-NIKLAAS-OOST",2026,2026,49,49,"2026-12-01",45644.020833333336,"2026-12-05",45644.194444444445,"5d, 04:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Appelstraat + onderhoud Y Melsele\r\nwerken Sint-Niklaas \r\n+\r\nwerken wisselonderdelen Melsele\r\n",null,null,79205,"2024-08-06",0,"1,2,3,4,5"]
[null,"Infrabel","65065","Namur - Antwerpen",">","CHATELET","CHATELET-GRIL OUEST",2026,2026,49,49,"2026-12-02",45644.958333333336,"2026-12-04",45644.208333333336,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - Phase 4.3.3 - Coupure type 10\r\nUPM: 531774",null,null,65065,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","84259","Athus - Meuse",">","BERTRIX","PALISEUL",2026,2026,49,49,"2026-12-04",45644.333333333336,"2026-12-04",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite VB\r\nEntretien voie",null,null,84259,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","65765","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2026,2026,49,50,"2026-12-04",45644.993055555555,"2026-12-07",45644.180555555555,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\ntronçon Gembloux - Namur",null,null,65765,"2024-06-20",1,"5,6"]
[null,"Infrabel","65821","Namur - Antwerpen","< >","TAMINES","CHATELET-GRIL OUEST",2026,2026,49,49,"2026-12-05",45644.25,"2026-12-06",45644.708333333336,"1d, 11:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Maintenance Z15.51 P4+\r\nUPM: 528676",null,null,65821,"2024-11-20",1,"5,6"]
[null,"Infrabel","82276","Namur - Antwerpen","< >","LUCHTBAL-ROOSTER S","ESSEN-GRENS",2026,2026,49,50,"2026-12-06",45644.03125,"2026-12-07",45644.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Onderhoud bovenleiding\r\nmin 14 prestaties, gespreid over het jaar,\r\nsp A of sp B\r\nHKV\r\nNacht R6^R7 van 00u45 tot 06u00",null,null,82276,"2024-11-14",0,"5,6"]
[null,"Infrabel","84123","Athus - Meuse",">","BEAURAING","VONECHE",2026,2026,50,50,"2026-12-07",45644.333333333336,"2026-12-07",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VA\r\nEntretien voie",null,null,84123,"2024-11-19",0,"5,6"]
[null,"Infrabel","63953","Lille - Charleroi","< >","JURBISE","ATH",2026,2026,50,50,"2026-12-07",45644.923611111109,"2026-12-12",45644.215277777781,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93\r\nUPM 526851",null,null,63953,"2024-10-29",0,"1,2,3,4,5"]
[null,"Infrabel","69190","Namur - Antwerpen","< >","Y.MELLE-WEST","Y.OOST DRIEHOEK LEDEBERG",2026,2026,50,50,"2026-12-08",45644.020833333336,"2026-12-12",45644.1875,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wissels 1AS & 1BS L50E (kirow)\r\n\r\n* inrit Merelbeke enkel kant Gent\r\n\r\nR-512247",null,null,69190,"2024-06-12",0,"1,2,3,4,5"]
[null,"Infrabel","83840","Lille - Charleroi",">","BRUGELETTE","Y.LENS",2026,2026,50,50,"2026-12-11",45644.354166666664,"2026-12-11",45644.645833333336,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Diagno Z7V\r\n",null,null,83840,"2024-11-08",0,"1,2,3,4,5"]
[null,"Infrabel","79511","Athus - Meuse","< >","ROCHEFORT-JEMELLE","GRUPONT",2026,2027,51,50,"2026-12-14",45644.951388888891,"2027-12-17",45644.201388888891,"368d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux Axe 3:\r\nTronçon Jemelle Grupont\r\nSAVU de jour en continu et CTL de nuit en semaine\r\nDossier de concertation validé en octobre 2024",null,null,79511,"2024-11-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","62776","Athus - Meuse",">","HAVERSIN","MARLOIE",2026,2027,51,50,"2026-12-14",45644.180555555555,"2027-12-13",45644.180555555555,"364d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux Axe 3\r\nDossier de concertation validé en octobre 2023",null,null,62776,"2024-11-05",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","74376","Lille - Charleroi",">","ROUX","MARCHIENNE-AU-PONT",2026,2026,51,51,"2026-12-14",45644.375,"2026-12-18",45644.666666666664,"4d, 07:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Réalisation dés, coupage poteaux… EL (entreligne)\r\nCorrélation ID 80072\r\nTCR530642",null,null,74376,"2024-11-28",0,"1,2,3,4,5"]
[null,"Infrabel","84273","Athus - Meuse",">","STRAIMONT","BERTRIX",2026,2026,51,51,"2026-12-15",45644.333333333336,"2026-12-15",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite de voie VB",null,null,84273,"2024-11-29",0,"1,2,3,4,5"]
[null,"Infrabel","84551","Athus - Meuse",">","HALANZY","SIGNEULX",2026,2026,51,51,"2026-12-17",45644.333333333336,"2026-12-17",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie  B",null,null,84551,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","81315","Namur - Antwerpen","< >","Y.LOUVAIN-LA-NEUVE","GEMBLOUX",2026,2027,51,49,"2026-12-18",45644.986111111109,"2027-12-10",45644.1875,"357d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3\r\nTronçon bifurcation LLN - Gembloux\r\nMassification travaux\r\nDossier de concertation\r\n",null,null,81315,"2024-09-12",0,"1,2,3,4,5"]
[null,"Infrabel","76349","Namur - Antwerpen","< >","Y.LOUVAIN-LA-NEUVE","GEMBLOUX",2026,2026,51,52,"2026-12-19",45644.25,"2026-12-21",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Entretien tronçon ",null,null,76349,"2024-08-29",1,"5,6"]
[null,"Infrabel","84054","Athus - Meuse",">","DINANT","Y.NEFFE",2026,2026,52,52,"2026-12-21",45644.333333333336,"2026-12-21",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visites VA",null,null,84054,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","84314","Athus - Meuse",">","FLORENVILLE","SAINT-VINCENT-BELLEFONTAINE",2026,2026,53,53,"2026-12-28",45644.333333333336,"2026-12-28",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie A",null,null,84314,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","84315","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","FLORENVILLE",2026,2026,53,53,"2026-12-29",45644.333333333336,"2026-12-29",45644.666666666664,"1d, 08:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Maintenance/visite voie B",null,null,84315,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","84091","Athus - Meuse",">","HOUYET","GENDRON-CELLES",2026,2026,53,53,"2026-12-29",45644.388888888891,"2026-12-29",45644.638888888891,"1d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Visite et interventions diverses VB\r\n",null,null,84091,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","75575","Athus - Meuse",">","NAMUR-HERBATTE","NAMUR",2027,2027,1,52,"2027-01-04",45644.333333333336,"2027-12-31",45644.666666666664,"361d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux SNCB: Renouvellement quai 2-3 en gare de Namur\r\nMise HS voie 2: Talon 18AG Libre - Signal L-H.30 (cas cat 26729 et 26727 HT)\r\nMise HS voie 3: Signaux K3-G.30 -  CX3-H.30 (Cas cat 26523 HT)\r\n\r\n28/03/24: NEW phasage à recevoir de SNCB pour minimis",null,null,75575,"2024-05-08",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","71293","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,1,1,"2027-01-08",45644.881944444445,"2027-01-09",45644.173611111109,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Livraison LRS via T-Portique, \r\nAménagement Hourpes & Lobbes Garage",null,null,71293,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","63944","Lille - Charleroi","< >","JURBISE","ATH",2027,2027,2,3,"2027-01-15",45644.9375,"2027-01-18",45644.215277777781,"2d, 06:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement traverses P93",null,null,63944,"2024-10-14",1,"5,6"]
[null,"Infrabel","79046","Lille - ZeeBrugge","< >","LICHTERVELDE","Y.KORTRIJK-WEST",2027,2027,3,3,"2027-01-18",45644.996527777781,"2027-01-23",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud regio 1 ",null,null,79046,"2024-08-21",0,"1,2,3,4,5"]
[null,"Infrabel","76807","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-NEKKERSPOEL",2027,2027,3,4,"2027-01-22",45644.993055555555,"2027-01-25",45644.194444444445,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Masterplan Mechelen \r\nConfiguratie M+N\r\nAfbraak bvl spoor 3&4 + terugplaatsen oplegtoestellen L53\r\n",null,null,76807,"2024-08-30",1,"5,6"]
[null,"Infrabel","79466","Namur - Antwerpen","< >","LONDERZEEL","Y.HEIKE",2027,2027,3,4,"2027-01-23",45644.010416666664,"2027-01-25",45644.166666666664,"2d, 03:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie Onderhoud Tracks + SI + schouwing sporen + kleine vernieuwingen\r\n\r\nsamen 78538 NO \r\n",null,null,79466,"2024-06-04",1,"5,6"]
[null,"Infrabel","71489","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2027,2027,4,4,"2027-01-25",45644.923611111109,"2027-01-30",45644.194444444445,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Quévy\r\nDéchargement des rails avec le Robel\r\nDossier de concertation",null,null,71489,"2024-10-14",0,"1,2,3,4,5"]
[null,"Infrabel","77102","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2027,2027,4,5,"2027-01-29",45644.989583333336,"2027-02-01",45644.180555555555,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\nMassification travaux\r\nDossier de concertation validé en octobre 2024",null,null,77102,"2024-10-30",1,"5,6"]
[null,"Infrabel","72806","Erquelinnes - Montzen",">","Y.RENORY","FLEMALLE-HAUTE",2027,2027,4,6,"2027-01-30",45644.333333333336,"2027-02-14",45644.666666666664,"15d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage\r\nSAVU continu\r\n+ CTL de nuit - CoLT 79532",null,null,72806,"2024-11-05",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","79036","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2027,2027,5,5,"2027-02-01",45644.958333333336,"2027-02-05",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud regio 1 ",null,null,79036,"2024-08-21",0,"1,2,3,4,5"]
[null,"Infrabel","76812","Namur - Antwerpen","< >","Y.WEERDE","MECHELEN-NEKKERSPOEL",2027,2027,5,5,"2027-02-01",45644.993055555555,"2027-02-05",45644.194444444445,"4d, 04:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Mechelen \r\nConfiguratie M+N\r\nUitbraak spoor 3&4\r\n",null,null,76812,"2024-09-10",0,"1,2,3,4,5"]
[null,"Infrabel","78043","Athus - Meuse","< >","ROCHEFORT-JEMELLE","GRUPONT",2027,2027,5,6,"2027-02-05",45644.979166666664,"2027-02-08",45644.197916666664,"2d, 05:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3 \r\nTronçon Rochefort-Jemelle - Grupont\r\nMassification travaux\r\n",null,null,78043,"2024-10-11",1,"5,6"]
[null,"Infrabel","78766","Namur - Antwerpen","< >","LONDERZEEL","Y.HEIKE",2027,2027,5,6,"2027-02-06",45644.010416666664,"2027-02-08",45644.166666666664,"2d, 03:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Afwerkingen en restwerken SIG/BVL/TRA\r\nMassificatie\r\n",null,null,78766,"2024-05-03",1,"5,6"]
[null,"Infrabel","79149","Namur - Antwerpen","< >","DENDERMONDE","DENDERMONDE",2027,2027,6,6,"2027-02-08",45644.996527777781,"2027-02-13",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Dendermonde fase 3 - sporen en bovenleiding\r\nDendermonde kant Schellebelle tussen E-D19 en 04AD en tussen G-D.19/ HD.19 en 14D + perronspoor VIII en IX buiten dienst \r\n+ Doodspoor 109 + bundel G \r\n",null,null,79149,"2024-05-14",0,"1,2,3,4,5"]
[null,"Infrabel","73608","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2027,2027,6,7,"2027-02-12",45644.979166666664,"2027-02-15",45644.1875,"3d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Central Phase 3.6\r\nCoupure type 8 - Extension Nuit\r\nRechargement AZSMR\r\n+rechargement EBP \r\nEn corrélation avec id 73607",null,null,73608,"2024-11-20",0,"5,6"]
[null,"Infrabel","9893","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2027,2027,6,10,"2027-02-12",45644.9375,"2027-03-08",45644.229166666664,"23d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Quévy\r\nRenouvellement rails Cuesmes-Quévy\r\nRenouvellement des appareils en gare\r\nRenouvellement des voies principales en gare\r\nDossier de concertation",null,null,9893,"2024-10-14",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","73611","Lille - Charleroi","< >","Y.NORD","Y.LA SAMBRE",2027,2027,7,7,"2027-02-19",45644.979166666664,"2027-02-21",45644.1875,"2d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Central Phase 3.6\r\nExtension coupure type 2\r\nEn corrélation avec id 73610\r\nTCR 520481",null,null,73611,"2024-09-18",0,"5,6"]
[null,"Infrabel","73610","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2027,2027,7,8,"2027-02-19",45644.9375,"2027-02-22",45644.229166666664,"2d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Central Phase 3.7\r\nCoupure type 2 2027\r\nEn corrélation avec id 73611 et 73645\r\nTCR 519232",null,null,73610,"2024-11-20",1,"5,6"]
[null,"Infrabel","72808","Erquelinnes - Montzen","< >","Y.RENORY","FLEMALLE-HAUTE",2027,2027,8,8,"2027-02-22",45644.958333333336,"2027-02-27",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage - bourrage de révision, contraintes, finitions,...",null,null,72808,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","73645","Lille - Charleroi",">","CHARLEROI-CENTRAL","CHARLEROI-CENTRAL",2027,2027,8,9,"2027-02-22",45644.166666666664,"2027-03-01",45644.166666666664,"7d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Charleroi Central conséquence 2.27\r\nEntre 48G non engagé - TJD 24BG/25G non engagé\r\nEn corrélation avec id 73610 -73613 - 73614\r\nTCR 520501",null,null,73645,"2024-11-20",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","73571","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","OTTIGNIES",2027,2027,8,9,"2027-02-26",45644.979166666664,"2027-03-01",45644.201388888891,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER : mise à 4 voies Watermael- Bakenbos",null,null,73571,"2024-12-02",1,"5,6"]
[null,"Infrabel","81089","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2027,2027,8,8,"2027-02-28",45644.333333333336,"2027-02-28",45644.625,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing\r\nUitbreiding op zondag bij 76760",null,null,81089,"2024-09-10",0,"5,6"]
[null,"Infrabel","79142","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2027,2027,9,9,"2027-03-01",45644.996527777781,"2027-03-06",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Dendermonde fase 3 - sporen en bovenleiding\r\nSchellebelle niet in, Dendermonde inclusief III, IV, VIII en IX\r\nInclusief bundel G, inclusief doodspoor 109 ",null,null,79142,"2024-05-14",0,"1,2,3,4,5"]
[null,"Infrabel","73646","Lille - Charleroi",">","CHARLEROI-CENTRAL","CHARLEROI-CENTRAL",2027,2027,9,16,"2027-03-01",45644.166666666664,"2027-04-23",45644.166666666664,"53d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Charleroi Central conséquence 3.2027\r\nEntre 30AG non engagé - E09H20 + 33AG non engagé - D08G20\r\nVoie 209 HS et voie 208 en CDS côté Bxl\r\nEn corrélation avec id 73618 - 73619 - 73620 - 73621 - 73623 à 73627",null,null,73646,"2024-11-20",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","72810","Erquelinnes - Montzen","< >","Y.RENORY","FLEMALLE-HAUTE",2027,2027,9,10,"2027-03-06",45644.958333333336,"2027-03-09",45644.208333333336,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage - bourrage de révision, contraintes, finitions,...",null,null,72810,"2024-11-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","71777","Lille - Charleroi",">","ROUX","Y.NORD",2027,2027,10,11,"2027-03-08",45644.9375,"2027-03-19",45644.666666666664,"11d, 17:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPhase 2\r\nPréparation caténaire\r\n2 - Massifs, poteaux, désamiantage des dés - 30 en A/124 A\r\nPréparation signalisation\r\nPrépa pose nouvelle loge en remplacement F21 F22\r\nPose de caniveau – Tirage de câble",null,null,71777,"2024-10-30",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","73875","Athus - Meuse","< >","VIRTON","SAINT-VINCENT-BELLEFONTAINE",2027,2027,10,11,"2027-03-12",45644.979166666664,"2027-03-15",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Traitement zone boueuse voie B L 165 BK 105.500 (zone à traiter = 25mètres)\r\n\r\n",null,null,73875,"2024-10-23",1,"5,6"]
[null,"Infrabel","74350","Namur - Antwerpen","< >","FRANIERE","JEMEPPE-SUR-SAMBRE",2027,2027,10,10,"2027-03-13",45644.25,"2027-03-14",45644.618055555555,"1d, 08:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification\r\nEntretien d'ouvrage sur le tronçon\r\n\r\n",null,null,74350,"2024-11-20",1,"5,6"]
[null,"Infrabel","71500","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.JURBISE",2027,2027,11,11,"2027-03-15",45644.965277777781,"2027-03-19",45644.180555555555,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de ballast (C 75) Soignies- Neufvilles\r\nPréparations-finitions\r\nDossier de concertation validé en octobre 2024",null,null,71500,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","76748","Namur - Antwerpen","< >","DENDERMONDE","SCHELLEBELLE",2027,2027,11,11,"2027-03-16",45644.006944444445,"2027-03-19",45644.194444444445,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P143 afschaffen overwegen\r\nPaalstraat OW 65, Dendermonde",null,null,76748,"2024-03-11",0,"1,2,3,4,5"]
[null,"Infrabel","74385","Athus - Meuse","< >","ANSEREMME","BEAURAING",2027,2027,11,12,"2027-03-19",45644.979166666664,"2027-03-22",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Talus, piste et étanchéité",null,null,74385,"2024-10-23",1,"5,6"]
[null,"Infrabel","73621","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2027,2027,11,12,"2027-03-19",45644.9375,"2027-03-22",45644.229166666664,"2d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Central Phase 3.13\r\nCoupure type 3 2027\r\nEn corrélation avec id 73622 et  73646",null,null,73621,"2024-11-20",1,"5,6"]
[null,"Infrabel","71495","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.JURBISE",2027,2027,11,12,"2027-03-19",45644.965277777781,"2027-03-22",45644.180555555555,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de ballast (C 75) Soignies- Neufvilles\r\nWE 1\r\nDossier de concertation validé en octobre 2024",null,null,71495,"2024-10-21",1,"5,6"]
[null,"Infrabel","73907","Lille - Charleroi","< >","TOURNAI","LEUZE",2027,2027,12,12,"2027-03-22",45644.9375,"2027-03-26",45644.1875,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Tournai Renouvellement des AS 24H-25H-26H-27H07AH/08H CDS 352\r\nPrépa renouvellement TJD 13H/14H-11AH/12H - 10AH/11BH\r\n",null,null,73907,"2024-12-13",0,"1,2,3,4,5"]
[null,"Infrabel","72834","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","Y.LEMAN",2027,2027,12,12,"2027-03-22",45644.965277777781,"2027-03-26",45644.197916666664,"4d, 05:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93",null,null,72834,"2024-10-30",0,"1,2,3,4,5"]
[null,"Infrabel","79144","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2027,2027,12,12,"2027-03-22",45644.996527777781,"2027-03-27",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Dendermonde fase 3 - sporen en bovenleiding\r\nSchellebelle niet in, Dendermonde inclusief III, IV, VIII en IX\r\nInclusief bundel G, inclusief doodspoor 109",null,null,79144,"2024-06-11",0,"1,2,3,4,5"]
[null,"Infrabel","73898","Athus - Meuse","< >","ROCHEFORT-JEMELLE","GRUPONT",2027,2027,12,13,"2027-03-26",45644.979166666664,"2027-03-30",45644.197916666664,"3d, 05:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3 \r\nTronçon Rochefort-Jemelle - Grupont\r\nMassification travaux\r\n",null,null,73898,"2024-12-13",1,"5,6"]
[null,"Infrabel","72831","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","Y.LEMAN",2027,2027,12,13,"2027-03-26",45644.965277777781,"2027-03-30",45644.197916666664,"3d, 05:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - WE3\r\nRenouvellement de rails",null,null,72831,"2024-10-30",1,"5,6"]
[null,"Infrabel","76885","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2027,2027,12,12,"2027-03-27",45644.979166666664,"2027-03-28",45644.229166666664,"1d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P143 afschaffen overwegen \r\nPaalstraat OW 65, Dendermonde \r\nNacht voor wegnemen BTS ( BTS Colt 76886)",null,null,76885,"2024-05-15",0,"5,6"]
[null,"Infrabel","73624","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2027,2027,13,13,"2027-03-30",45644.9375,"2027-04-03",45644.229166666664,"4d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Central Phase 3.14.2\r\nCoupure type 3 2027\r\nEn corrélation avec 73646",null,null,73624,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","83863","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.JURBISE",2027,2027,13,13,"2027-03-30",45644.965277777781,"2027-04-02",45644.180555555555,"3d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de ballast (C 75) Soignies- Neufvilles\r\nPréparations-finitions\r\nDossier de concertation validé en octobre 2024",null,null,83863,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","71497","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.JURBISE",2027,2027,13,14,"2027-04-02",45644.965277777781,"2027-04-05",45644.180555555555,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de ballast (C 75) Soignies- Neufvilles\r\nWE 3\r\nDossier de concertation validé en octobre 2024",null,null,71497,"2024-11-05",1,"5,6"]
[null,"Infrabel","77955","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,13,13,"2027-04-04",45644.041666666664,"2027-04-04",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,77955,"2024-10-10",0,"5,6"]
[null,"Infrabel","83864","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.JURBISE",2027,2027,14,14,"2027-04-05",45644.965277777781,"2027-04-09",45644.180555555555,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de ballast (C 75) Soignies- Neufvilles\r\nPréparations-finitions\r\nDossier de concertation validé en octobre 2024",null,null,83864,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","75260","Athus - Meuse","< >","Y.ATHUS-NORD","AUBANGE-FRONTIERE-FRANCE",2027,2027,14,15,"2027-04-09",45644.958333333336,"2027-04-12",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Pose du nouvel AS sur L165/3 et adaptation caténaire - WE2\r\n",null,null,75260,"2024-12-02",1,"5,6"]
[null,"Infrabel","72634","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE-MARCHANDISE","NAMUR",2027,2027,14,15,"2027-04-09",45644.965277777781,"2027-04-12",45644.208333333336,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification\r\nIntervention infrastructure",null,null,72634,"2024-10-23",1,"5,6"]
[null,"Infrabel","74146","Namur - Antwerpen","< >","JEMEPPE-SUR-SAMBRE-MARCHANDISE","TAMINES",2027,2027,14,15,"2027-04-09",45644.965277777781,"2027-04-12",45644.208333333336,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA : Chape CSV 79.580 ",null,null,74146,"2024-11-19",1,"5,6"]
[null,"Infrabel","76786","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2027,2027,14,15,"2027-04-11",45644.03125,"2027-04-12",45644.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud + overwegen\r\nWeekendnachten ter voorbereiding",null,null,76786,"2024-09-06",0,"5,6"]
[null,"Infrabel","72837","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","Y.LEMAN",2027,2027,15,15,"2027-04-12",45644.979166666664,"2027-04-17",45644.222222222219,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - bourrage de révision, contraintes, finitions,...",null,null,72837,"2024-10-30",0,"1,2,3,4,5"]
[null,"Infrabel","83865","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.JURBISE",2027,2027,15,15,"2027-04-12",45644.965277777781,"2027-04-16",45644.180555555555,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de ballast (C 75) Soignies- Neufvilles\r\nPréparations-finitions\r\nDossier de concertation validé en octobre 2024",null,null,83865,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","77634","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,15,16,"2027-04-16",45644.979166666664,"2027-04-19",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\nVoorbereiding en lossen materialen",null,null,77634,"2024-11-12",1,"5,6"]
[null,"Infrabel","75752","Lille - Antwerpen","< >","SINT-NIKLAAS-OOST","MELSELE",2027,2027,15,16,"2027-04-17",45644.010416666664,"2027-04-19",45644.194444444445,"2d, 04:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-527750\r\nP93 (A + B)  \r\nFSNO - Trapezium Melsele \r\nFSNO inbegrepen, FSNO bundel niet inbegrepen, station Melsele niet inbegrepen \r\n\r\n\r\n",null,null,75752,"2024-11-05",1,"5,6"]
[null,"Infrabel","72838","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","Y.LEMAN",2027,2027,16,16,"2027-04-19",45644.979166666664,"2027-04-24",45644.222222222219,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - bourrage de révision, contraintes, finitions,...",null,null,72838,"2024-10-30",0,"1,2,3,4,5"]
[null,"Infrabel","83866","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.JURBISE",2027,2027,16,16,"2027-04-19",45644.965277777781,"2027-04-23",45644.180555555555,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de ballast (C 75) Soignies- Neufvilles\r\nPréparations-finitions\r\nDossier de concertation validé en octobre 2024",null,null,83866,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","74124","Lille - Charleroi",">","MONS","QUEVY",2027,2027,16,16,"2027-04-19",45644.375,"2027-04-23",45644.625,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Rnlvt PS 61.216 Av. Wauters : Construction nouveau PS BK 61.400 : Réalisation des pieux côté L96\r\nDossier de concertation",null,null,74124,"2024-10-14",0,"1,2,3,4,5"]
[null,"Infrabel","73572","Namur - Antwerpen","< >","WATERMAEL","OTTIGNIES",2027,2027,16,18,"2027-04-23",45644.979166666664,"2027-05-03",45644.201388888891,"9d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"RER: mise à 4 voies Bakenbos Ottignies\r\nCTL continu vacances scolaires\r\nCTL Back Up de la CTL de mise en service de fin 2026\r\nNe pas massifier d'autres travaux au cas où cette TCR ne serait pas nécessaire! \r\nDossier de concertation validé en octobre 202",null,null,73572,"2024-12-02",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","73512","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2027,2027,16,17,"2027-04-23",45644.965277777781,"2027-04-26",45644.201388888891,"2d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"L140 Travaux PLP Fleurus + transfert PN 94",null,null,73512,"2024-10-30",1,"5,6"]
[null,"Infrabel","72843","Erquelinnes - Montzen","< >","LIEGE-GUILLEMINS","Y.LEMAN",2027,2027,16,17,"2027-04-24",45644.979166666664,"2027-04-26",45644.1875,"2d, 05:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - bourrage de révision, contraintes, finitions,...",null,null,72843,"2024-10-30",0,"5,6"]
[null,"Infrabel","77958","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,16,16,"2027-04-25",45644.041666666664,"2027-04-25",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,77958,"2024-10-10",0,"5,6"]
[null,"Infrabel","76393","Lille - Charleroi",">","MARCHIENNE-AU-PONT","Y.LA SAMBRE",2027,2027,17,17,"2027-04-26",45644.9375,"2027-05-01",45644.229166666664,"5d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPhase 5 : Préparation caténaire\r\n5 - Massifs, poteaux, désamiantage des dés - 30 en B/124 A -B/124A1-A/112, côté v.1 FMR",null,null,76393,"2024-10-14",0,"1,2,3,4,5"]
[null,"Infrabel","73390","Athus - Meuse","< >","GENDRON-CELLES","BEAURAING",2027,2027,17,19,"2027-04-30",45644.958333333336,"2027-05-10",45644.208333333336,"9d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massification: Tracks: Assainissement entre Houyet et Beauraing (VA de Bk 17.800 à 18.750) + Travaux OA: Démolition du pont (VB) de la Halte Royale (Bk 13.808) + préparations sommier.",null,null,73390,"2024-12-02",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","76188","Lille - ZeeBrugge","< >","BRUGGE","BRUGGE-ROOSTER E",2027,2027,17,18,"2027-04-30",45644.972222222219,"2027-05-03",45644.166666666664,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Brugge wissels 15BI, 17AI en 17BI \r\ninclusief perronsporen VI, VII en VIII en IX ",null,null,76188,"2024-12-04",1,"5,6"]
[null,"Infrabel","75542","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN",2027,2027,17,18,"2027-05-01",45644.25,"2027-05-03",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Fietstunnel Vloeiende\r\nMassificatie onderhoud + overwegen",null,null,75542,"2024-09-05",1,"5,6"]
[null,"Infrabel","72840","Erquelinnes - Montzen",">","LIEGE-GUILLEMINS","Y.LEMAN",2027,2027,18,18,"2027-05-03",45644.979166666664,"2027-05-08",45644.222222222219,"5d, 05:50h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93 - bourrage de révision, contraintes, finitions,...",null,null,72840,"2024-10-30",0,"1,2,3,4,5"]
[null,"Infrabel","70927","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,18,18,"2027-05-03",45644.923611111109,"2027-05-05",45644.173611111109,"2d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux préparatoires Signalisation\r\nDossier de concertation validé en octobre 2024\r\n",null,null,70927,"2024-12-13",0,"1,2,3,4,5"]
[null,"Infrabel","76195","Lille - ZeeBrugge","< >","BRUGGE","BRUGGE-ROOSTER E",2027,2027,18,19,"2027-05-07",45644.972222222219,"2027-05-10",45644.166666666664,"2d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Brugge wissels 15BI, 17AI en 17BI\r\n\r\ninclusief perronsporen VI, VII en VIII en IX ",null,null,76195,"2024-09-27",1,"5,6"]
[null,"Infrabel","75746","Lille - Antwerpen","< >","SINT-NIKLAAS-OOST","MELSELE",2027,2027,18,19,"2027-05-08",45644.010416666664,"2027-05-10",45644.194444444445,"2d, 04:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"P93 (A + B) \r\nFSNO - Trapezium Melsele \r\nFSNO inbegrepen, FSNO bundel niet inbegrepen, station Melsele niet inbegrepen \r\n\r\n\r\n",null,null,75746,"2024-09-27",1,"5,6"]
[null,"Infrabel","74391","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2027,2027,19,32,"2027-05-10",45644.208333333336,"2027-08-13",45644.979166666664,"96d, 18:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA: Pont Halte Royale Bk 13.808: Renouvellement complet tablier métallique VB (sommier, poutres, tablier et passerelle piétonne)",null,null,74391,"2024-12-02",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","78949","Lille - Antwerpen","< >","SINT-NIKLAAS-OOST","Y.ZWIJNDRECHT-FORT",2027,2027,19,19,"2027-05-11",45644.020833333336,"2027-05-14",45644.166666666664,"3d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wisselonderdelen en onderhoud te Melsele.\r\nWeeknachten\r\n\r\n\r\n",null,null,78949,"2024-05-09",1,"5,6"]
[null,"Infrabel","74649","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2027,2027,19,20,"2027-05-14",45644.989583333336,"2027-05-18",45644.180555555555,"3d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Parois rocheuses, PN 56 et 58 St Denis Bovesse et étanchéité PI de Rhisnes\r\nModernisation Axe 3 \r\nDossier de concertation validé en octobre 2024",null,null,74649,"2024-10-30",1,"1,2,3,4,5,6,7"]
[null,"Infrabel","73583","Namur - Antwerpen",">","CHATELET-GRIL EST","TAMINES",2027,2027,19,20,"2027-05-15",45644.9375,"2027-05-17",45644.229166666664,"2d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - 2027 Phase 8.1.6\r\nCoupure type 1 de 2027\r\n2 prest de nuits WE\r\nTCR: 525820",null,null,73583,"2024-11-20",0,"5,6"]
[null,"Infrabel","73633","Erquelinnes - Montzen",">","CHARLEROI-CENTRAL","Y.NORD",2027,2027,20,20,"2027-05-18",45644.333333333336,"2027-05-19",45644.666666666664,"1d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Charleroi Central Phase 3.17\r\nCoupure type 5 2027",null,null,73633,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","74664","Athus - Meuse","< >","BEAURAING","GRAIDE",2027,2027,20,21,"2027-05-21",45644.979166666664,"2027-05-24",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Renouvellement chape étanchéité PI 25.267 à Beauraing\r\n+ P247 - Prolongation de la 3ème voie\r\nPose caténaire\r\n\r\n",null,null,74664,"2024-12-02",1,"5,6"]
[null,"Infrabel","77646","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,20,21,"2027-05-21",45644.979166666664,"2027-05-24",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\nWespelaar-Tildonk en Wijgmaal",null,null,77646,"2024-11-12",1,"5,6"]
[null,"Infrabel","73750","Namur - Antwerpen","< >","OTTIGNIES","CHARLEROI-OUEST",2027,2027,20,21,"2027-05-22",45644.25,"2027-05-24",45644.208333333336,"2d, 23:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"L140 travaux PLP Fleurus - test des CV\r\n",null,null,73750,"2024-10-30",1,"5,6"]
[null,"Infrabel","73634","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2027,2027,21,21,"2027-05-24",45644.9375,"2027-05-29",45644.229166666664,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Central Phase 3.18\r\nCoupure type 3 2027",null,null,73634,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","78950","Lille - Antwerpen","< >","SINT-NIKLAAS-OOST","Y.ZWIJNDRECHT-FORT",2027,2027,21,21,"2027-05-25",45644.020833333336,"2027-05-28",45644.166666666664,"3d, 03:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wisselonderdelen en onderhoud te Melsele.\r\nWeeknachten\r\n\r\n\r\n",null,null,78950,"2024-05-09",1,"5,6"]
[null,"Infrabel","77620","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2027,2027,21,22,"2027-05-28",45644.979166666664,"2027-05-31",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Instandhoudingswerken brug Leuvensesteenweg\r\nMechelen vrij",null,null,77620,"2024-04-24",1,"5,6"]
[null,"Infrabel","77647","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,21,22,"2027-05-28",45644.979166666664,"2027-05-31",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\n",null,null,77647,"2024-11-12",1,"5,6"]
[null,"Infrabel","78955","Lille - Antwerpen","< >","MELSELE-ROOSTER O/Q","Y.ZWIJNDRECHT-FORT",2027,2027,21,22,"2027-05-29",45644.020833333336,"2027-05-31",45644.166666666664,"3d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wisselonderdelen en onderhoud te Melsele.\r\nWeekendnachten\r\n\r\n\r\n",null,null,78955,"2024-05-09",0,"5,6"]
[null,"Infrabel","78228","Namur - Antwerpen","< >","SCHAERBEEK","SCHAERBEEK",2027,2027,22,22,"2027-05-31",45644.958333333336,"2027-06-05",45644.1875,"5d, 05:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): verwijderen asbest\r\nFSR sp 10+11 BDS en BSS",null,null,78228,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","73635","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","Y.NORD",2027,2027,22,22,"2027-05-31",45644.9375,"2027-06-04",45644.229166666664,"4d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Central Phase 3.19\r\nCoupure type 4 2027",null,null,73635,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","78954","Lille - Antwerpen","< >","SINT-NIKLAAS-OOST","Y.ZWIJNDRECHT-FORT",2027,2027,22,22,"2027-06-01",45644.020833333336,"2027-06-05",45644.166666666664,"5d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen wisselonderdelen en onderhoud te Melsele.\r\nWeeknachten\r\n\r\n\r\n",null,null,78954,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","77621","Namur - Antwerpen","< >","MECHELEN","MUIZEN-ROOSTER T",2027,2027,22,23,"2027-06-04",45644.979166666664,"2027-06-07",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Instandhoudingswerken brug Leuvensesteenweg\r\nMechelen vrij",null,null,77621,"2024-04-24",1,"5,6"]
[null,"Infrabel","75749","Lille - Antwerpen","< >","SINT-NIKLAAS-OOST","MELSELE",2027,2027,22,23,"2027-06-05",45644.010416666664,"2027-06-07",45644.194444444445,"2d, 04:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"P93 (A + B) \r\nFSNO - Trapezium Melsele \r\nFSNO inbegrepen, FSNO bundel niet inbegrepen, station Melsele niet inbegrepen \r\n\r\n\r\n",null,null,75749,"2024-09-27",1,"5,6"]
[null,"Infrabel","77644","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,23,23,"2027-06-07",45644.979166666664,"2027-06-11",45644.166666666664,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\n weeknachten",null,null,77644,"2024-05-09",0,"1,2,3,4,5"]
[null,"Infrabel","73638","Erquelinnes - Montzen","< >","CHARLEROI-CENTRAL","Y.NORD",2027,2027,23,23,"2027-06-07",45644.9375,"2027-06-12",45644.229166666664,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Central Phase 3.21\r\nCoupure type 4 2027",null,null,73638,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","73658","Erquelinnes - Montzen","< >","HUY","NAMUR",2027,2027,23,23,"2027-06-10",45644.96875,"2027-06-11",45644.215277777781,"1d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage du ballast",null,null,73658,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","77649","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,23,24,"2027-06-11",45644.979166666664,"2027-06-14",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\n",null,null,77649,"2024-11-12",1,"5,6"]
[null,"Infrabel","73776","Lille - Charleroi","< >","ATH","ENGHIEN",2027,2027,24,24,"2027-06-14",45644.958333333336,"2027-06-18",45644.180555555555,"4d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS Y-Coucou",null,null,73776,"2024-10-14",0,"1,2,3,4,5"]
[null,"Infrabel","73639","Lille - Charleroi","< >","Y.NORD","CHARLEROI-CENTRAL",2027,2027,24,24,"2027-06-14",45644.9375,"2027-06-19",45644.229166666664,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Charleroi Central Phase 3.22\r\nCoupure type 11 2027",null,null,73639,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","75497","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,24,24,"2027-06-16",45644.923611111109,"2027-06-19",45644.173611111109,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + Hourpes\r\nLivraison 6AS à Lobbes Garage avec Grue Kirow\r\nDossier de concertation validé en octobre 2024",null,null,75497,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","73780","Lille - Charleroi","< >","ATH","ENGHIEN",2027,2027,24,25,"2027-06-18",45644.958333333336,"2027-06-21",45644.180555555555,"2d, 05:20h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS Y-Coucou",null,null,73780,"2024-10-14",1,"5,6"]
[null,"Infrabel","74623","Erquelinnes - Montzen","< >","STATTE","NAMUR",2027,2027,24,25,"2027-06-18",45644.979166666664,"2027-06-21",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Parois rocheuses - Talus - Etanchéité - PN Seilles (intervention de CJ à Sclaigneaux + Namêche pour des PR et pour les PN de Seilles entre Bk 38 et 40)\r\n+ Chantier de C75",null,null,74623,"2024-12-05",1,"5,6"]
[null,"Infrabel","73659","Erquelinnes - Montzen","< >","HUY","NAMUR",2027,2027,25,25,"2027-06-21",45644.96875,"2027-06-25",45644.215277777781,"4d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage du ballast",null,null,73659,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","73278","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2027,2027,25,25,"2027-06-25",45644.333333333336,"2027-06-25",45644.979166666664,"1d, 15:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Massification: Tracks: Renouvellement de traverses par train P93 - Tx préparatoires WE1 + Travaux OA: Pose de passerelle PI 87.356 VB\r\nSAVU R5",null,null,73278,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","75903","Athus - Meuse","< >","YVOIR","Y.NEFFE",2027,2027,25,26,"2027-06-25",45644.979166666664,"2027-06-28",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Block Automatique Yvoir-Dinant : Préparation MES passage en EBP-PLP",null,null,75903,"2024-12-10",1,"5,6"]
[null,"Infrabel","77101","Namur - Antwerpen",">","Y.DRABSTRAAT","Y.ARENDSTRAAT",2027,2027,25,26,"2027-06-26",45644.993055555555,"2027-06-28",45644.166666666664,"2d, 04:10h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Bijkomende beveiliging sp A L27 tijdens nacht bij\r\nKleine vernieuwingen wisselonderdelen Y Stadion",null,null,77101,"2024-03-13",0,"5,6"]
[null,"Infrabel","79588","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2027,2027,26,27,"2027-06-28",45644.979166666664,"2027-07-05",45644.194444444445,"6d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Rnlvt PS 61.216 Av. Wauters : Pose des dalles\r\nDossier de concertation validé en octobre 2024",null,null,79588,"2024-12-05",1,"1,2,3,4,5,6,7"]
[null,"Infrabel","75764","Lille - Antwerpen","< >","SINT-NIKLAAS-OOST","MELSELE",2027,2027,26,26,"2027-06-29",45644.010416666664,"2027-07-02",45644.194444444445,"4d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"P93 (A + B) \r\nFSNO - Trapezium Melsele \r\nFSNO inbegrepen, FSNO bundel niet inbegrepen, station Melsele niet inbegrepen \r\n\r\n\r\n",null,null,75764,"2024-09-03",0,"1,2,3,4,5"]
[null,"Infrabel","74620","Erquelinnes - Montzen","< >","STATTE","NAMUR",2027,2027,26,27,"2027-07-02",45644.979166666664,"2027-07-05",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Parois rocheuses - Talus - Etanchéité - PN Seilles (intervention de CJ à Sclaigneaux + Namêche pour des PR et pour les PN de Seilles entre Bk 38 et 40)\r\n+ Chantier de C75",null,null,74620,"2024-12-05",1,"5,6"]
[null,"Infrabel","73759","Athus - Meuse","< >","JAMBES","YVOIR",2027,2027,26,27,"2027-07-02",45644.979166666664,"2027-07-05",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA Etanchéité PI Yvoir 81.047 + Parois et Talus dans le tronçon Jambes - Yvoir\r\n+ Travaux préparatoires Block Automatique Lustin-Yvoir pour passage futur en EBP-PLP.\r\n",null,null,73759,"2024-11-19",1,"5,6"]
[null,"Infrabel","75791","Namur - Antwerpen","< >","LONDERZEEL","DENDERMONDE",2027,2027,26,27,"2027-07-03",45644.013888888891,"2027-07-05",45644.180555555555,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"221331 goederencorridors Dendermonde\r\n+\r\nDendermonde - bouw passerelle - deelfase A3\r\n\r\nDendermonde \r\nPerronsporen I-II-III-IV-VI buiten dienst \r\nBundel M\r\nDoodspoor 124 buiten dienst\r\nBundel G\r\nDoodspoor 105 buiten dienst \r\nSpoor 104 buiten dienst \r\n+\r",null,null,75791,"2024-06-10",1,"5,6"]
[null,"Infrabel","73667","Erquelinnes - Montzen","< >","HUY","NAMUR",2027,2027,27,27,"2027-07-05",45644.96875,"2027-07-10",45644.215277777781,"5d, 05:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage du ballast",null,null,73667,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","78233","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,27,27,"2027-07-05",45644.427083333336,"2027-07-09",45644.625,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78233,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","75796","Namur - Antwerpen","< >","DENDERMONDE","LONDERZEEL",2027,2027,27,27,"2027-07-06",45644.013888888891,"2027-07-10",45644.180555555555,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"221331 goederencorridors Dendermonde\r\n+\r\nDendermonde - bouw passerelle - deelfase A3\r\n+\r\nP208312: Waterhuishouding L53: Londerzeel- Malderen\r\n\r\nDendermonde \r\nPerronsporen I-II-III-IV-VI buiten dienst \r\nBundel M\r\nDoodspoor 124 buiten dienst\r\nBundel G\r\nDo",null,null,75796,"2024-06-11",0,"1,2,3,4,5"]
[null,"Infrabel","73666","Erquelinnes - Montzen","< >","ANDENNE","NAMUR-HERBATTE",2027,2027,27,28,"2027-07-10",45644.986111111109,"2027-07-12",45644.208333333336,"2d, 05:20h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Criblage du ballast - bourrage de révision",null,null,73666,"2024-12-05",0,"5,6"]
[null,"Infrabel","73668","Erquelinnes - Montzen",">","MARCHE-LES-DAMES","BEEZ",2027,2027,28,28,"2027-07-12",45644.958333333336,"2027-07-17",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage du ballast - bourrage de révision, contraintes,...",null,null,73668,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","73604","Athus - Meuse",">","STRAIMONT","FLORENVILLE",2027,2027,28,28,"2027-07-12",45644.958333333336,"2027-07-18",45644.208333333336,"6d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 nuits de min 06h\r\nBourrage de révision,...",null,null,73604,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","73305","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,28,28,"2027-07-12",45644.208333333336,"2027-07-12",45644.75,"2d, 13:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 - tx pour remise en service\r\nSAVU R1",null,null,73305,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","78257","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,28,28,"2027-07-12",45644.986111111109,"2027-07-17",45644.208333333336,"5d, 05:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78257,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","79589","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2027,2027,28,28,"2027-07-12",45644.923611111109,"2027-07-17",45644.194444444445,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnlvt PS 61.216 Av. Wauters : Révisions des voies suite à la pose des dalles\r\nDossier de concertation validé en octobre 2024",null,null,79589,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","78234","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,28,28,"2027-07-12",45644.427083333336,"2027-07-16",45644.625,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78234,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","74627","Athus - Meuse","< >","NAMUR","BOIS D'AUSSE",2027,2027,28,29,"2027-07-17",45644.003472222219,"2027-07-19",45644.208333333336,"2d, 04:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Parois - Talus \r\n",null,null,74627,"2024-11-18",1,"5,6"]
[null,"Infrabel","78258","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,29,29,"2027-07-19",45644.986111111109,"2027-07-24",45644.208333333336,"5d, 05:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78258,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","78235","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,29,29,"2027-07-19",45644.427083333336,"2027-07-23",45644.625,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78235,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","81896","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,30,30,"2027-07-26",45644.993055555555,"2027-07-30",45644.208333333336,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81896,"2024-09-24",0,"1,2,3,4,5"]
[null,"Infrabel","73505","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,30,30,"2027-07-26",45644.923611111109,"2027-07-31",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nDossier de concertation",null,null,73505,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","78035","Athus - Meuse","< >","ROCHEFORT-JEMELLE","GRUPONT",2027,2027,30,31,"2027-07-30",45644.979166666664,"2027-08-02",45644.197916666664,"2d, 05:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3 \r\nTronçon Rochefort-Jemelle - Grupont\r\nMassification travaux\r\n",null,null,78035,"2024-12-13",1,"5,6"]
[null,"Infrabel","74654","Namur - Antwerpen","< >","WAVRE","SINT-JORIS-WEERT",2027,2027,30,31,"2027-07-30",45644.979166666664,"2027-08-02",45644.222222222219,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Suppression PN 12 et 14: Démontage des PN\r\n",null,null,74654,"2024-10-30",1,"5,6"]
[null,"Infrabel","75534","Namur - Antwerpen","< >","KAPELLEN-WIJKSPOOR","ESSEN-GRENS",2027,2027,30,31,"2027-07-31",45644.25,"2027-08-02",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud + overwegen\r\nBundel Essen inbegrepen",null,null,75534,"2024-09-05",1,"5,6"]
[null,"Infrabel","73298","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,31,32,"2027-08-02",45644.958333333336,"2027-08-15",45644.208333333336,"13d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Finitions \r\nBourrage de révision, contraintes et finitions C75",null,null,73298,"2024-12-02",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","56335","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,31,35,"2027-08-02",45644.958333333336,"2027-08-30",45644.173611111109,"27d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux SI + Voie\r\n+ Renouvellement pont 7\r\nCTL 1 mois continu\r\nDossier de concertation validé en octobre 2024",null,null,56335,"2024-11-05",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","46277","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,31,39,"2027-08-02",45644.333333333336,"2027-10-01",45644.666666666664,"60d, 08:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Massification: Travaux OA: Stabilisation talus de Lahage (107.000 à 107.400). SAVU VB + Travaux Tracks: Fin des travaux de C75 + travaux P93\r\n",null,null,46277,"2024-12-13",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","73669","Erquelinnes - Montzen",">","MARCHE-LES-DAMES","BEEZ",2027,2027,31,31,"2027-08-02",45644.979166666664,"2027-08-07",45644.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage du ballast - bourrage de révision, contraintes,...",null,null,73669,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","71779","Lille - Charleroi","< >","ROUX","Y.NORD",2027,2027,31,31,"2027-08-02",45644.875,"2027-08-07",45644.229166666664,"5d, 08:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPhase 7 : Préparation caténaire\r\n7 - Pose nouvelles traverses 2 voies - 30 sur A + B/124A, BK 52 à 53,5",null,null,71779,"2024-12-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","81897","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,31,31,"2027-08-02",45644.993055555555,"2027-08-06",45644.208333333336,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81897,"2024-09-24",0,"1,2,3,4,5"]
[null,"Infrabel","74389","Athus - Meuse","< >","ANSEREMME","BEAURAING",2027,2027,31,32,"2027-08-06",45644.979166666664,"2027-08-09",45644.229166666664,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Pont Halte Royale Bk 13.808: Repose de la Voie B et pose de la passerelle piétonne",null,null,74389,"2024-11-26",1,"5,6"]
[null,"Infrabel","74653","Namur - Antwerpen","< >","WAVRE","SINT-JORIS-WEERT",2027,2027,31,32,"2027-08-06",45644.979166666664,"2027-08-09",45644.222222222219,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Suppression PN 12 et 14 avec poussage d'un PI.\r\n\r\n",null,null,74653,"2024-11-26",1,"5,6"]
[null,"Infrabel","81888","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,31,32,"2027-08-06",45644.993055555555,"2027-08-09",45644.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81888,"2024-10-23",1,"5,6"]
[null,"Infrabel","73671","Erquelinnes - Montzen",">","MARCHE-LES-DAMES","BEEZ",2027,2027,31,32,"2027-08-07",45644.958333333336,"2027-08-09",45644.208333333336,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage du ballast - bourrage de révision,...",null,null,73671,"2024-12-06",0,"5,6"]
[null,"Infrabel","74655","Namur - Antwerpen","< >","WAVRE","SINT-JORIS-WEERT",2027,2027,32,32,"2027-08-09",45644.979166666664,"2027-08-13",45644.222222222219,"4d, 05:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Suppression PN 12 et 14: Finitions suite WE de poussage\r\n",null,null,74655,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","73670","Erquelinnes - Montzen",">","MARCHE-LES-DAMES","BEEZ",2027,2027,32,32,"2027-08-09",45644.979166666664,"2027-08-14",45644.208333333336,"5d, 05:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage du ballast - bourrage de révision, contraintes,...",null,null,73670,"2024-12-05",0,"1,2,3,4,5"]
[null,"Infrabel","79042","Lille - ZeeBrugge","< >","Y.KORTRIJK-WEST","LICHTERVELDE",2027,2027,32,32,"2027-08-09",45644.996527777781,"2027-08-13",45644.184027777781,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud massificatie \r\n\r\n\r\n\r\n\r\n",null,null,79042,"2024-05-13",0,"1,2,3,4,5"]
[null,"Infrabel","81898","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,32,32,"2027-08-09",45644.993055555555,"2027-08-13",45644.208333333336,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81898,"2024-09-24",0,"1,2,3,4,5"]
[null,"Infrabel","74390","Athus - Meuse","< >","ANSEREMME","BEAURAING",2027,2027,32,33,"2027-08-13",45644.979166666664,"2027-08-16",45644.229166666664,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Pont Halte Royale Bk 13.808: Renouvellement du tablier d'approche",null,null,74390,"2024-11-26",1,"5,6"]
[null,"Infrabel","74657","Namur - Antwerpen","< >","WAVRE","SINT-JORIS-WEERT",2027,2027,32,33,"2027-08-13",45644.979166666664,"2027-08-16",45644.222222222219,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Suppression PN 12 et 14: Bourrage de révision\r\n",null,null,74657,"2024-10-30",1,"5,6"]
[null,"Infrabel","73515","Lille - Charleroi","< >","ENGHIEN","Y.SILLY",2027,2027,32,35,"2027-08-13",45644.944444444445,"2027-08-30",45644.180555555555,"16d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement AW Gare Enghien - Côté Ath\r\n+ renouvellement anticipé chape étanchéité PI L94…29.260\r\nDossier de concertation",null,null,73515,"2024-10-17",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","79041","Lille - ZeeBrugge","< >","Y.KORTRIJK-WEST","LICHTERVELDE",2027,2027,32,33,"2027-08-13",45644.996527777781,"2027-08-16",45644.184027777781,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-79041\r\nonderhoud massificatie \r\n\r\n\r\n\r\n\r\n",null,null,79041,"2024-10-22",1,"5,6"]
[null,"Infrabel","81889","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,32,33,"2027-08-13",45644.993055555555,"2027-08-16",45644.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81889,"2024-10-23",1,"5,6"]
[null,"Infrabel","73672","Erquelinnes - Montzen",">","MARCHE-LES-DAMES","BEEZ",2027,2027,32,33,"2027-08-14",45644.958333333336,"2027-08-16",45644.208333333336,"2d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Criblage du ballast - bourrage de révision,...",null,null,73672,"2024-12-06",0,"5,6"]
[null,"Infrabel","77248","Namur - Antwerpen","< >","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2027,2027,32,34,"2027-08-14",45644.25,"2027-08-28",45644.166666666664,"14d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Herelektrificatie L27 : schoolvakantie\r\n",null,null,77248,"2024-09-23",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","71788","Lille - Charleroi","< >","ROUX","Y.NORD",2027,2027,33,33,"2027-08-16",45644.9375,"2027-08-21",45644.229166666664,"5d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPhase 8 : Préparation caténaire\r\n8 - Equipement métallique T , ap t, haubans…) - 6 ap t, 4 T, haubans… dans entreligne\r\nPréparation signalisation\r\nPose nouveaux signaux en 124A",null,null,71788,"2024-08-29",0,"1,2,3,4,5"]
[null,"Infrabel","79543","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2027,2027,33,33,"2027-08-16",45644.944444444445,"2027-08-20",45644.222222222219,"4d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 \r\nPréparations\r\nSAVU Nuits + CTL nuits",null,null,79543,"2024-12-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","79258","Namur - Antwerpen","< >","DENDERMONDE","DENDERMONDE",2027,2027,33,33,"2027-08-16",45644.996527777781,"2027-08-21",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Dendermonde fase 3 - sporen en bovenleiding\r\nDendermonde kant Schellebelle tussen E-D19 en 04AD en tussen G-D.19/ HD.19 en 14D + perronspoor VIII en IX buiten dienst \r\n+ Doodspoor 109 + bundel G \r\n",null,null,79258,"2024-05-16",0,"1,2,3,4,5"]
[null,"Infrabel","79045","Lille - ZeeBrugge","< >","Y.KORTRIJK-WEST","LICHTERVELDE",2027,2027,33,33,"2027-08-16",45644.996527777781,"2027-08-21",45644.184027777781,"5d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"onderhoud massificatie \r\n\r\n\r\n\r\n\r\n",null,null,79045,"2024-05-13",0,"1,2,3,4,5"]
[null,"Infrabel","81899","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,33,33,"2027-08-16",45644.993055555555,"2027-08-20",45644.208333333336,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81899,"2024-09-24",0,"1,2,3,4,5"]
[null,"Infrabel","73955","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,33,34,"2027-08-16",45644.177083333336,"2027-08-27",45644.993055555555,"12d, 19:35h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Modernisation Axe 3\r\nTronçon Gembloux - Rhisnes\r\nMassification travaux (GC linéaire et ripage voies)\r\nDossier de concertation validé en octobre 2024",null,null,73955,"2024-11-18",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","73325","Athus - Meuse","< >","ARLON","STERPENICH-FRONTIERE",2027,2027,33,33,"2027-08-17",45644.020833333336,"2027-08-20",45644.180555555555,"4d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75\r\nPréparations\r\nSAVU Nuits + CTL nuits",null,null,73325,"2024-12-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","73323","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2027,2027,33,33,"2027-08-19",45644.333333333336,"2027-08-20",45644.958333333336,"2d, 15:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75\r\nSAVU\r\n2 jours hors barrage CFL nécessaires",null,null,73323,"2024-12-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","73326","Athus - Meuse","< >","Y.AUTELBAS","STERPENICH-FRONTIERE",2027,2027,33,36,"2027-08-20",45644.958333333336,"2027-09-06",45644.166666666664,"16d, 05:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75",null,null,73326,"2024-12-05",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","81890","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,33,34,"2027-08-20",45644.993055555555,"2027-08-23",45644.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81890,"2024-10-23",1,"5,6"]
[null,"Infrabel","74143","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2027,2027,34,34,"2027-08-23",45644.958333333336,"2027-08-27",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – 42.395 et 49.295 - Nuits prépa",null,null,74143,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","74486","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2027,2027,34,34,"2027-08-23",45644.958333333336,"2027-08-28",45644.229166666664,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA: Pont Halte Royale Bk 13.808: Travaux de finition, bourrage de révision et contraintes",null,null,74486,"2024-11-26",0,"1,2,3,4,5"]
[null,"Infrabel","71789","Lille - Charleroi",">","MARCHIENNE-AU-PONT","Y.NORD",2027,2027,34,34,"2027-08-23",45644.9375,"2027-08-28",45644.229166666664,"5d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPréparation caténaire\r\n9 - Equipement métallique T , ap t, haubans…) - 8 ap t, 6 T, haubans… en B/124A",null,null,71789,"2024-08-08",0,"1,2,3,4,5"]
[null,"Infrabel","79257","Namur - Antwerpen","< >","DENDERMONDE","DENDERMONDE",2027,2027,34,34,"2027-08-23",45644.996527777781,"2027-08-28",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Dendermonde fase 3 - sporen en bovenleiding\r\nDendermonde kant Schellebelle tussen E-D19 en 04AD en tussen G-D.19/ HD.19 en 14D + perronspoor VIII en IX buiten dienst \r\n+ Doodspoor 109 + bundel G \r\n",null,null,79257,"2024-05-16",0,"1,2,3,4,5"]
[null,"Infrabel","81900","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,34,34,"2027-08-23",45644.993055555555,"2027-08-28",45644.208333333336,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81900,"2024-09-24",0,"1,2,3,4,5"]
[null,"Infrabel","73895","Namur - Antwerpen","< >","OTTIGNIES","OTTIGNIES",2027,2027,34,40,"2027-08-23",45644.166666666664,"2027-10-08",45644.916666666664,"47d, 18:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"mise hors service de la liaison entre la L161 et la L140\r\nsauf sur demande ponctuelle ou S660",null,null,73895,"2024-12-09",3,"1,2,3,4,5,6,7"]
[null,"Infrabel","73447","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,34,34,"2027-08-27",45644.333333333336,"2027-08-27",45644.989583333336,"2d, 15:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie A - Tx préparatoires WE1\r\nSAVU R5",null,null,73447,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","73449","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2027,2027,34,35,"2027-08-27",45644.989583333336,"2027-08-30",45644.180555555555,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie A - WE1\r\n+ Modernisation Axe 3 \r\nDossier de concertation",null,null,73449,"2024-10-30",1,"5,6"]
[null,"Infrabel","81887","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,34,35,"2027-08-27",45644.993055555555,"2027-08-30",45644.208333333336,"2d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81887,"2024-10-23",1,"5,6"]
[null,"Infrabel","77100","Namur - Antwerpen",">","Y.BERCHEM-STADION","Y.ARENDSTRAAT",2027,2027,34,35,"2027-08-28",45644.979166666664,"2027-08-30",45644.166666666664,"2d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Kleine vernieuwingen wisselonderdelen Y Noord Berchem\r\nBijkomend tijdens nacht bij 77099",null,null,77100,"2024-03-13",0,"5,6"]
[null,"Infrabel","74144","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2027,2027,35,35,"2027-08-30",45644.958333333336,"2027-09-03",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – 42.395 et 49.295 - Nuits finitions",null,null,74144,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","74394","Athus - Meuse",">","GENDRON-CELLES","HOUYET",2027,2027,35,35,"2027-08-30",45644.958333333336,"2027-09-04",45644.229166666664,"5d, 06:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Travaux OA: Pont Halte Royale Bk 13.808: Travaux de finition, bourrage de révision et contraintes",null,null,74394,"2024-11-26",0,"1,2,3,4,5"]
[null,"Infrabel","73451","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,35,35,"2027-08-30",45644.180555555555,"2027-08-30",45644.916666666664,"2d, 17:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie A - Tx pour remise en service WE1\r\nSAVU R1",null,null,73451,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","79146","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2027,2027,35,35,"2027-08-30",45644.996527777781,"2027-09-03",45644.1875,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Dendermonde fase 3 - sporen en bovenleiding\r\nSchellebelle niet in, Dendermonde inclusief III, IV, VIII en IX\r\nInclusief bundel G,inclusief doodspoor 109 ",null,null,79146,"2024-05-14",0,"1,2,3,4,5"]
[null,"Infrabel","81901","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,35,35,"2027-08-30",45644.993055555555,"2027-09-04",45644.208333333336,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81901,"2024-09-24",0,"1,2,3,4,5"]
[null,"Infrabel","79085","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,35,35,"2027-08-30",45644.923611111109,"2027-09-04",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux Caténaire pour travaux sur médiane\r\nDossier de concertation validé en octobre 2024",null,null,79085,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","73284","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,35,35,"2027-09-03",45644.333333333336,"2027-09-03",45644.979166666664,"1d, 15:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 - Tx préparatoires\r\nSAVU R5",null,null,73284,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","73448","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,35,35,"2027-09-03",45644.333333333336,"2027-09-03",45644.989583333336,"2d, 15:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie A - Tx préparatoires WE2\r\nSAVU R5",null,null,73448,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","73288","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,35,36,"2027-09-03",45644.979166666664,"2027-09-06",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 - WE",null,null,73288,"2024-12-05",1,"5,6"]
[null,"Infrabel","77847","Lille - Charleroi",">","ROUX","Y.NORD",2027,2027,35,36,"2027-09-03",45644.9375,"2027-09-06",45644.229166666664,"3d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPréparation caténaire\r\n8A - Equipement métallique T , ap t, haubans…) – En A/124, 2 ap t, 4 T, haubans… \r\n9A - Equipement métallique T , ap t, haubans…) – En B/124, 2 ap t, 4 T, haubans… \r\n",null,null,77847,"2024-11-20",0,"5,6"]
[null,"Infrabel","73516","Lille - Charleroi","< >","ENGHIEN","Y.SILLY",2027,2027,35,36,"2027-09-03",45644.944444444445,"2027-09-06",45644.180555555555,"2d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement AW Gare Enghien - Côté Ath\r\nDossier de concertation",null,null,73516,"2024-10-17",1,"5,6"]
[null,"Infrabel","73450","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2027,2027,35,36,"2027-09-03",45644.989583333336,"2027-09-06",45644.180555555555,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie A - WE2\r\n+ Modernisation Axe 3 \r\nDossier de concertation validé en octobre 2024",null,null,73450,"2024-10-30",1,"5,6"]
[null,"Infrabel","79141","Namur - Antwerpen",">","DENDERMONDE","DENDERMONDE",2027,2027,35,38,"2027-09-04",45644.013888888891,"2027-09-20",45644.166666666664,"16d, 03:40h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Buitendienststelling Dendermonde Fase 3 \r\nBundelsporen 105-104-103-102-101-100 buiten dienst \r\nPerronsporen VIII en IX te Dendermonde  buiten dienst \r\nDoodspoor buiten dienst \r\nSpoor V-VI- VII doodspoor \r\nDoes op lijn 53 beperkt tussen sein E-D.19 tot A",null,null,79141,"2024-07-15",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","79148","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2027,2027,35,36,"2027-09-04",45644.041666666664,"2027-09-06",45644.166666666664,"2d, 03:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Buitendienststelling Dendermonde Fase 3 \r\nBundelsporen 105-104-103-102-101-100 buiten dienst \r\nPerronsporen VIII en IX te Dendermonde  buiten dienst \r\nDoodspoor buiten dienst \r\nSpoor V-VI- VIII doodspoor \r\nDoes op lijn 53 beperkt tussen sein E-D.19 tot ",null,null,79148,"2024-07-22",1,"5,6"]
[null,"Infrabel","81097","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2027,2027,35,35,"2027-09-05",45644.333333333336,"2027-09-05",45644.625,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing\r\nUitbreiding op zondag bij 76765",null,null,81097,"2024-09-10",0,"5,6"]
[null,"Infrabel","76795","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN-GRENS",2027,2027,35,36,"2027-09-05",45644.03125,"2027-09-06",45644.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud + overwegen\r\nWeekendnachten ter voorbereiding",null,null,76795,"2024-05-01",0,"5,6"]
[null,"Infrabel","76765","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,35,35,"2027-09-05",45644.041666666664,"2027-09-05",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76765,"2024-10-10",0,"5,6"]
[null,"Infrabel","74145","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2027,2027,36,36,"2027-09-06",45644.958333333336,"2027-09-10",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – 42.395 et 49.295 - Nuits finitions",null,null,74145,"2024-03-27",0,"1,2,3,4,5"]
[null,"Infrabel","73292","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,36,36,"2027-09-06",45644.208333333336,"2027-09-06",45644.75,"1d, 13:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 - Tx pour remise en service \r\nSAVU R1",null,null,73292,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","76529","Namur - Antwerpen","< >","SCHAERBEEK","SCHAERBEEK",2027,2028,36,15,"2027-09-06",45644.208333333336,"2028-04-10",45644.25,"217d, 01:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Bundel M in FSR continu buiten dienst voor de vernieuwing van de Albertbrug Fase 2.0: premontage brugdelen 5 en 6 (Reserve)\r\nBijkomend tijdens de nachten sp B L25 in W36 en W37.",null,null,76529,"2024-02-28",3,"1,2,3,4,5,6,7"]
[null,"Infrabel","80374","Athus - Meuse",">","Y.AUTELBAS","STERPENICH-FRONTIERE",2027,2027,36,37,"2027-09-06",45644.944444444445,"2027-09-13",45644.222222222219,"7d, 06:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 \r\nFinitions\r\nSAVU Nuits + CTL nuits",null,null,80374,"2024-12-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","73452","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,36,36,"2027-09-06",45644.180555555555,"2027-09-06",45644.916666666664,"2d, 17:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie A - Tx pour remise en service WE2\r\nSAVU R1",null,null,73452,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","81902","Namur - Antwerpen","< >","Y.PARKBRUG","SINT-JORIS-WEERT",2027,2027,36,36,"2027-09-06",45644.993055555555,"2027-09-11",45644.208333333336,"5d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van de bi-bloc dwarsliggers met externe P-trein\r\n",null,null,81902,"2024-10-23",0,"1,2,3,4,5"]
[null,"Infrabel","74121","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2027,2027,36,36,"2027-09-06",45644.923611111109,"2027-09-10",45644.194444444445,"4d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnlvt PS 61.216 Av. Wauters : Construction nouveau PS BK 61.400 : Dépose des coffrages des voiles extérieurs des culées + pose consoles protection pour travail sur les sommiers\r\nDossier de concertation validé en octobre 2024",null,null,74121,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","80375","Athus - Meuse","< >","ARLON","STERPENICH-FRONTIERE",2027,2027,36,37,"2027-09-07",45644.020833333336,"2027-09-13",45644.180555555555,"7d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75\r\nFinitions\r\nSAVU Nuits + CTL nuits\r\n",null,null,80375,"2024-12-05",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","73285","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,36,36,"2027-09-10",45644.333333333336,"2027-09-10",45644.979166666664,"1d, 15:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 - Tx préparatoires\r\nSAVU R5",null,null,73285,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","73289","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,36,37,"2027-09-10",45644.979166666664,"2027-09-13",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 ",null,null,73289,"2024-12-02",1,"5,6"]
[null,"Infrabel","75902","Athus - Meuse","< >","YVOIR","Y.NEFFE",2027,2027,36,37,"2027-09-10",45644.979166666664,"2027-09-13",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Block Automatique Yvoir-Dinant : MES passage en EBP-PLP.",null,null,75902,"2024-11-19",1,"5,6"]
[null,"Infrabel","73517","Lille - Charleroi","< >","ENGHIEN","Y.SILLY",2027,2027,36,37,"2027-09-10",45644.944444444445,"2027-09-13",45644.180555555555,"2d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement AW Gare Enghien - Côté Ath\r\nDossier de concertation",null,null,73517,"2024-10-14",1,"5,6"]
[null,"Infrabel","77355","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","WATERMAEL",2027,2027,36,37,"2027-09-10",45644.982638888891,"2027-09-13",45644.166666666664,"2d, 04:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Werken B-ST Station Etterbeek: Auvents - portiques + poutres",null,null,77355,"2024-11-19",1,"5,6"]
[null,"Infrabel","79150","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2027,2027,36,37,"2027-09-11",45644.041666666664,"2027-09-13",45644.166666666664,"2d, 03:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Buitendienststelling Dendermonde Fase 3 \r\nBundelsporen 105-104-103-102-101-100 buiten dienst \r\nPerronsporen VIII en IX te Dendermonde  buiten dienst \r\nDoodspoor buiten dienst 109\r\nSpoor V-VI- VIII doodspoor \r\nDoes op lijn 53 beperkt tussen sein E-D.19 t",null,null,79150,"2024-07-22",1,"5,6"]
[null,"Infrabel","81099","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2027,2027,36,36,"2027-09-12",45644.333333333336,"2027-09-12",45644.625,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing\r\nUitbreiding op zondag bij 76766",null,null,81099,"2024-09-10",0,"5,6"]
[null,"Infrabel","76796","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN-GRENS",2027,2027,36,37,"2027-09-12",45644.03125,"2027-09-13",45644.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Overwegen +massificatie onderhoud\r\nWeekendnachten ter voorbereiding",null,null,76796,"2024-05-01",0,"5,6"]
[null,"Infrabel","76766","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,36,36,"2027-09-12",45644.041666666664,"2027-09-12",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76766,"2024-10-10",0,"5,6"]
[null,"Infrabel","73453","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,37,37,"2027-09-13",45644.958333333336,"2027-09-18",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie A - \r\nBourrage de révision, contraintes et finitions",null,null,73453,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","73293","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,37,37,"2027-09-13",45644.208333333336,"2027-09-13",45644.75,"1d, 13:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 - Tx pour remise en service\r\nSAVU R1",null,null,73293,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","79554","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2027,2027,37,37,"2027-09-13",45644.993055555555,"2027-09-18",45644.177083333336,"5d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie A - \r\nBourrage de révision, contraintes et finitions",null,null,79554,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","78909","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,37,37,"2027-09-13",45644.993055555555,"2027-09-18",45644.159722222219,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW bereikbaar via omloopsspoor",null,null,78909,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","70934","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,37,37,"2027-09-13",45644.923611111109,"2027-09-18",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Bourrage\r\nDossier de concertation validé en octobre 2024",null,null,70934,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","78894","Lille - Antwerpen","< >","GENT-DAMPOORT","LOKEREN",2027,2027,37,37,"2027-09-14",45644.020833333336,"2027-09-17",45644.166666666664,"4d, 03:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"226332 afschaffen overwegen NW\r\nNieuwe Molenstraat (OW60), Lokeren\r\n+\r\nP143 afschaffen overwegen\r\nSchaessestraat OW 74, Destelbergen\r\n\r\nVoorbereidende weeknachten ",null,null,78894,"2024-06-13",0,"1,2,3,4,5"]
[null,"Infrabel","73286","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,37,37,"2027-09-17",45644.333333333336,"2027-09-17",45644.979166666664,"1d, 15:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 - Tx préparatoires \r\nSAVU R5",null,null,73286,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","73290","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,37,38,"2027-09-17",45644.979166666664,"2027-09-20",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93",null,null,73290,"2024-12-02",1,"5,6"]
[null,"Infrabel","74960","Namur - Antwerpen","< >","OTTIGNIES","LIMAL",2027,2027,37,38,"2027-09-17",45644.9375,"2027-09-20",45644.215277777781,"2d, 06:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"chantier RER : travaux coeur Ottignies + faisceau manage \r\nPas de passage L139-L140\r\nPas de passage L139-L161\r\n",null,null,74960,"2024-12-13",1,"5,6"]
[null,"Infrabel","75558","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN-GRENS",2027,2027,37,38,"2027-09-18",45644.25,"2027-09-20",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud +\r\nOverwegen",null,null,75558,"2024-09-05",1,"5,6"]
[null,"Infrabel","78888","Lille - Antwerpen","< >","GENT-DAMPOORT","LOKEREN",2027,2027,37,38,"2027-09-18",45644.041666666664,"2027-09-20",45644.166666666664,"2d, 03:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"R-527742\r\n226332 afschaffen overwegen NW\r\nNieuwe Molenstraat (OW60), Lokeren\r\n+\r\nP143 afschaffen overwegen\r\nSchaessestraat OW 74, Destelbergen+\r\n+\r\nOnderhoud\r\nWissels 11 BI en 13AI moeten vrijblijven ",null,null,78888,"2024-11-05",1,"5,6"]
[null,"Infrabel","76767","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,37,37,"2027-09-19",45644.041666666664,"2027-09-19",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76767,"2024-10-10",0,"5,6"]
[null,"Infrabel","73454","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,38,38,"2027-09-20",45644.958333333336,"2027-09-25",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie A - \r\nBourrage de révision, contraintes et finitions",null,null,73454,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","76004","Namur - Antwerpen",">","KONTICH-LINT","MECHELEN-NEKKERSPOEL",2027,2027,38,38,"2027-09-20",45644.958333333336,"2027-09-25",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Weeknachten L27 sp B\r\nOVB Rechtstraat: slopen brug, bouwen landhoofd, plaatsen liggers in kader van vernieuwing brug (Duffel) aan kp 30.250",null,null,76004,"2024-05-09",0,"1,2,3,4,5"]
[null,"Infrabel","77660","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,38,38,"2027-09-20",45644.979166666664,"2027-09-24",45644.166666666664,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\n weeknachten",null,null,77660,"2024-05-09",0,"1,2,3,4,5"]
[null,"Infrabel","73294","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,38,38,"2027-09-20",45644.208333333336,"2027-09-20",45644.75,"1d, 13:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 - Tx pour remise en service \r\nSAVU R1",null,null,73294,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","78897","Lille - Antwerpen","< >","GENT-DAMPOORT","LOKEREN",2027,2027,38,38,"2027-09-20",45644.020833333336,"2027-09-25",45644.180555555555,"6d, 03:50h","Periodical",null,"T","","",null,null,null,null,null,null,null,"226332 afschaffen overwegen NW\r\nNieuwe Molenstraat (OW60), Lokeren\r\n+\r\nP143 afschaffen overwegen\r\nSchaessestraat OW 74, Destelbergen\r\n\r\nVoorbereidende weeknachten ",null,null,78897,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","79154","Namur - Antwerpen",">","DENDERMONDE","DENDERMONDE",2027,2027,38,38,"2027-09-20",45644.996527777781,"2027-09-25",45644.1875,"5d, 04:35h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Masterplan Dendermonde fase 3 - sporen en bovenleiding\r\nDendermonde kant Schellebelle tussen E-D19 en 04AD en tussen G-D.19/ HD.19 en 14D + perronspoor VIII en IX buiten dienst \r\n+ Doodspoor 109 + bundel G \r\n",null,null,79154,"2024-12-06",0,"1,2,3,4,5"]
[null,"Infrabel","79553","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2027,2027,38,38,"2027-09-20",45644.993055555555,"2027-09-25",45644.177083333336,"5d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie A - \r\nBourrage de révision, contraintes et finitions\r\nSAVU voie A HS Gembloux - Rhisnes et CTL dans les blancs travaux",null,null,79553,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","78910","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,38,38,"2027-09-20",45644.993055555555,"2027-09-25",45644.159722222219,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW bereikbaar via omloopsspoor",null,null,78910,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","79591","Namur - Antwerpen","< >","DENDERMONDE","DENDERMONDE",2027,2028,38,26,"2027-09-20",45644.003472222219,"2028-07-01",45644.333333333336,"285d, 07:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"FDR stationsproject - Spoor II en III te FDR buiten dienst ",null,null,79591,"2024-07-29",3,"1,2,3,4,5,6,7"]
[null,"Infrabel","70935","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,38,38,"2027-09-20",45644.923611111109,"2027-09-25",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Contraintes - finitions\r\nDossier de concertation validé en octobre 2024",null,null,70935,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","73287","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,38,38,"2027-09-24",45644.333333333336,"2027-09-24",45644.979166666664,"1d, 15:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 - Tx préparatoires \r\nSAVU R5",null,null,73287,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","74353","Athus - Meuse","< >","JAMBES","YVOIR",2027,2027,38,39,"2027-09-24",45644.979166666664,"2027-09-27",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Parois et Talus dans le tronçon Jambes - Yvoir\r\n",null,null,74353,"2024-11-19",1,"5,6"]
[null,"Infrabel","73291","Athus - Meuse","< >","SAINT-VINCENT-BELLEFONTAINE","SIGNEULX",2027,2027,38,39,"2027-09-24",45644.979166666664,"2027-09-27",45644.208333333336,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93\r\n",null,null,73291,"2024-12-02",1,"5,6"]
[null,"Infrabel","77657","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,38,39,"2027-09-24",45644.979166666664,"2027-09-27",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\nHambos",null,null,77657,"2024-11-12",1,"5,6"]
[null,"Infrabel","74137","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2027,2027,38,39,"2027-09-24",45644.965277777781,"2027-09-27",45644.201388888891,"2d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"PIM peinture 43.660 44.528 48.720",null,null,74137,"2024-10-30",1,"5,6"]
[null,"Infrabel","75557","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN-GRENS",2027,2027,38,39,"2027-09-25",45644.25,"2027-09-27",45644.166666666664,"2d, 22:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud +\r\nOverwegen",null,null,75557,"2024-05-01",1,"5,6"]
[null,"Infrabel","78899","Lille - Antwerpen","< >","GENT-DAMPOORT","LOKEREN",2027,2027,38,38,"2027-09-26",45644.041666666664,"2027-09-26",45644.166666666664,"1d, 03:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"226332 afschaffen overwegen NW\r\nNieuwe Molenstraat (OW60), Lokeren\r\n+\r\nP143 afschaffen overwegen\r\nSchaessestraat OW 74, Destelbergen\r\n\r\nNacht voor wegnemen BTS ",null,null,78899,"2024-05-13",0,"5,6"]
[null,"Infrabel","76768","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,38,38,"2027-09-26",45644.041666666664,"2027-09-26",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76768,"2024-10-10",0,"5,6"]
[null,"Infrabel","77661","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,39,39,"2027-09-27",45644.979166666664,"2027-10-01",45644.166666666664,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\n weeknachten",null,null,77661,"2024-05-09",0,"1,2,3,4,5"]
[null,"Infrabel","73295","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,39,39,"2027-09-27",45644.208333333336,"2027-09-27",45644.75,"1d, 13:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par train P93 - Tx pour remise en service\r\nSAVU R1",null,null,73295,"2024-12-02",0,"1,2,3,4,5"]
[null,"Infrabel","79156","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2027,2027,39,39,"2027-09-27",45644.996527777781,"2027-10-02",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Dendermonde fase 3 - sporen en bovenleiding\r\nSchellebelle niet in, Dendermonde inclusief III, IV, VIII en IX\r\nInclusief bundel G ",null,null,79156,"2024-05-14",0,"1,2,3,4,5"]
[null,"Infrabel","78911","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,39,39,"2027-09-27",45644.993055555555,"2027-10-02",45644.159722222219,"5d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW bereikbaar via omloopsspoor\r\nY.Melle West  moet vrijblijven ",null,null,78911,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","71790","Lille - Charleroi",">","ROUX","Y.NORD",2027,2027,39,39,"2027-09-27",45644.229166666664,"2027-09-30",45644.229166666664,"3d, 00:00h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPréparation caténaire\r\n13 - Transfert caténaire, et créer RP prov. BK 53 - En A/124A, R 52/1 -BK 52 à 53,1, et  du 53/16 à 53/30",null,null,71790,"2024-08-18",0,"1,2,3,4,5"]
[null,"Infrabel","73502","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,39,39,"2027-09-27",45644.923611111109,"2027-10-02",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux finition des caniveaux signalisation\r\nDossier de concertation validé en octobre 2024",null,null,73502,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","71791","Lille - Charleroi",">","ROUX","Y.NORD",2027,2027,39,39,"2027-09-30",45644.333333333336,"2027-10-03",45644.229166666664,"3d, 21:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPréparation caténaire\r\n14 - Transfert caténaire, et créer RP prov. BK 53 - En B/124A, R 52/2,  I 52/10- BK 52 à 53,1, et  du 53/16 à 53/30",null,null,71791,"2024-10-29",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","75443","Lille - Charleroi","< >","ROUX","Y.NORD",2027,2027,39,39,"2027-09-30",45644.9375,"2027-10-03",45644.229166666664,"3d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPréparation caténaire\r\n14 - Transfert caténaire, et créer RP prov. BK 53 - En B/124A, R 52/2,  I 52/10- BK 52 à 53,1, et  du 53/16 à 53/30",null,null,75443,"2024-08-08",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","78038","Athus - Meuse","< >","ROCHEFORT-JEMELLE","GRUPONT",2027,2027,39,40,"2027-10-01",45644.979166666664,"2027-10-04",45644.197916666664,"2d, 05:15h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3 \r\nTronçon Rochefort-Jemelle - Grupont\r\nMassification travaux",null,null,78038,"2024-10-11",1,"5,6"]
[null,"Infrabel","77659","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,39,40,"2027-10-01",45644.979166666664,"2027-10-04",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\nHambos",null,null,77659,"2024-11-12",1,"5,6"]
[null,"Infrabel","74138","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2027,2027,39,40,"2027-10-01",45644.965277777781,"2027-10-04",45644.201388888891,"2d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"PIM peinture 43.660 44.528 48.720",null,null,74138,"2024-10-30",1,"5,6"]
[null,"Infrabel","72045","Lille - Charleroi","< >","ENGHIEN","ATH",2027,2027,39,40,"2027-10-01",45644.944444444445,"2027-10-04",45644.180555555555,"2d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Mise en service PLP du BA Enghien-Silly\r\nInclus les travaux TUC et cellule ETCS\r\nPAS D'AUTRE MASSIFICATION POSSIBLE",null,null,72045,"2024-10-14",1,"5,6"]
[null,"Infrabel","77356","Namur - Antwerpen","< >","BRUXELLES-LUXEMBOURG","WATERMAEL",2027,2027,39,40,"2027-10-01",45644.982638888891,"2027-10-04",45644.166666666664,"2d, 04:25h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Werken B-ST Station Etterbeek:  Auvents - portiques + poutres",null,null,77356,"2024-11-20",1,"5,6"]
[null,"Infrabel","77172","Namur - Antwerpen",">","Y.NOORD BERCHEM","ANTWERPEN-CENTRAAL",2027,2027,39,40,"2027-10-02",45644.979166666664,"2027-10-04",45644.166666666664,"2d, 04:30h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Nazicht wissels SIG Y Arendstraat en FNC-2\r\nBijkomend bij aanvraag 75983 ter beveiliging",null,null,77172,"2024-03-14",0,"5,6"]
[null,"Infrabel","72046","Lille - Charleroi","< >","SAINTES","BLANDAIN-FRONTIERE",2027,2027,39,39,"2027-10-02",45644.020833333336,"2027-10-02",45644.083333333336,"1d, 01:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rechargement EBP-PLP pour MES PLP L94 Silly - Enghien\r\nLié à la demande COLT 72045\r\nRq 333 : nuit ven/sa ou sa/dim??\r\nEncodage à corriger uniquement L94 d'encodée !!",null,null,72046,"2024-04-30",0,"5,6"]
[null,"Infrabel","76797","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN-GRENS",2027,2027,39,40,"2027-10-03",45644.03125,"2027-10-04",45644.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Overwegen + kleine vernieuwingen\r\nWeekendnachten voor afwerking",null,null,76797,"2024-05-01",0,"5,6"]
[null,"Infrabel","73300","Athus - Meuse",">","SAINT-VINCENT-BELLEFONTAINE","VIRTON",2027,2027,40,44,"2027-10-04",45644.958333333336,"2027-11-01",45644.208333333336,"28d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement de traverses par P93\r\nBourrage de révision, contraintes et finitions ",null,null,73300,"2024-12-02",0,"1,2,3,4,5,6,7"]
[null,"Infrabel","71810","Lille - Charleroi","< >","MARCHIENNE-AU-PONT","ROUX",2027,2027,40,43,"2027-10-04",45644.333333333336,"2027-10-25",45644.625,"21d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Ballast  - C75",null,null,71810,"2024-11-05",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","77662","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,40,40,"2027-10-04",45644.979166666664,"2027-10-08",45644.166666666664,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\n weeknachten",null,null,77662,"2024-05-09",0,"1,2,3,4,5"]
[null,"Infrabel","79157","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2027,2027,40,40,"2027-10-04",45644.996527777781,"2027-10-09",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Dendermonde fase 3 - sporen en bovenleiding\r\nSchellebelle niet in, Dendermonde inclusief III, IV, VIII en IX\r\nInclusief bundel G ",null,null,79157,"2024-05-14",0,"1,2,3,4,5"]
[null,"Infrabel","78916","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,40,40,"2027-10-04",45644.993055555555,"2027-10-08",45644.159722222219,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW bereikbaar via omloopsspoor\r\nY.Melle West  moet vrijblijven ",null,null,78916,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","73504","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,40,40,"2027-10-04",45644.923611111109,"2027-10-08",45644.173611111109,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux finition des caniveaux signalisation\r\nDossier de concertation validé en octobre 2024",null,null,73504,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","77658","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,40,41,"2027-10-08",45644.979166666664,"2027-10-11",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\nHambos",null,null,77658,"2024-11-12",1,"5,6"]
[null,"Infrabel","74661","Namur - Antwerpen","< >","MONT-SAINT-GUIBERT","GEMBLOUX",2027,2027,40,41,"2027-10-08",45644.986111111109,"2027-10-11",45644.1875,"2d, 04:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Renouvellement du PS 36.635: WE pour nettoyage et finition\r\n\r\n",null,null,74661,"2024-12-06",1,"5,6"]
[null,"Infrabel","78913","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,40,41,"2027-10-08",45644.993055555555,"2027-10-11",45644.159722222219,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW bereikbaar via omloopsspoor\r\nY.Melle West  moet vrijblijven ",null,null,78913,"2024-05-15",1,"5,6"]
[null,"Infrabel","74108","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2027,2027,40,41,"2027-10-08",45644.923611111109,"2027-10-11",45644.194444444445,"2d, 06:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Rnlvt PS 61.216 Av. Wauters : Construction nouveau PS BK 61.400 : Pose du bowstring\r\nDossier de concertation validé en octobre 2024",null,null,74108,"2024-11-05",1,"5,6"]
[null,"Infrabel","76798","Namur - Antwerpen","< >","Y.LUCHTBAL","ESSEN-GRENS",2027,2027,40,41,"2027-10-10",45644.03125,"2027-10-11",45644.208333333336,"2d, 04:15h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud + overwegen\r\nWeekendnachten voor afwerking",null,null,76798,"2024-05-01",0,"5,6"]
[null,"Infrabel","76770","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,40,40,"2027-10-10",45644.041666666664,"2027-10-10",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76770,"2024-10-10",0,"5,6"]
[null,"Infrabel","76867","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2027,2027,41,41,"2027-10-11",45644.958333333336,"2027-10-15",45644.197916666664,"4d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRVB Aulnoye",null,null,76867,"2024-09-23",0,"1,2,3,4,5"]
[null,"Infrabel","77663","Namur - Antwerpen","< >","HAACHT","Y.DIJLEBRUG",2027,2027,41,41,"2027-10-11",45644.979166666664,"2027-10-15",45644.166666666664,"4d, 04:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing RTB perronsporen Wijgmaal, Hambos en Wespelaar-Tildonk\r\n weeknachten",null,null,77663,"2024-05-09",0,"1,2,3,4,5"]
[null,"Infrabel","73522","Namur - Antwerpen",">","TAMINES","CHATELET",2027,2027,41,41,"2027-10-11",45644.9375,"2027-10-16",45644.229166666664,"5d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - 2027 Phase 8.2.2\r\nCoupure type 1 de 2027\r\n6 Nuits\r\nCorrélation avec id 73521\r\nTCR: 526319",null,null,73522,"2024-11-20",0,"1,2,3,4,5"]
[null,"Infrabel","77686","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","Y.MELSELE",2027,2027,41,41,"2027-10-11",45644.996527777781,"2027-10-15",45644.1875,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van rails, dwarsliggers en spoorstaven L59 en 59/1\r\nWeeknachten",null,null,77686,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","79158","Namur - Antwerpen","< >","SCHELLEBELLE","DENDERMONDE",2027,2027,41,41,"2027-10-11",45644.996527777781,"2027-10-16",45644.1875,"5d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Masterplan Dendermonde fase 3 - sporen en bovenleiding\r\nSchellebelle niet in, Dendermonde inclusief III, IV, VIII en IX\r\nInclusief bundel G ",null,null,79158,"2024-05-14",0,"1,2,3,4,5"]
[null,"Infrabel","78917","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,41,41,"2027-10-11",45644.993055555555,"2027-10-15",45644.159722222219,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW bereikbaar via omloopsspoor\r\nY.Melle West  moet vrijblijven ",null,null,78917,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","79113","Namur - Antwerpen",">","BRUXELLES-LUXEMBOURG","WATERMAEL",2027,2027,41,43,"2027-10-11",45644.166666666664,"2027-10-29",45644.993055555555,"19d, 19:50h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken B-ST Station Etterbeek: Auvents - panneaux sandwich + chéneaux",null,null,79113,"2024-11-20",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","70933","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,41,41,"2027-10-11",45644.923611111109,"2027-10-15",45644.173611111109,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnvlt AS Lobbes-Garage : Travaux Caténaire pour travaux sur médiane\r\nDossier de concertation validé en octobre 2024",null,null,70933,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","74110","Lille - Charleroi","< >","MONS","QUEVY-FRONTIERE",2027,2027,41,41,"2027-10-11",45644.923611111109,"2027-10-16",45644.194444444445,"5d, 06:30h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Rnlvt PS 61.216 Av. Wauters : Construction nouveau PS BK 61.400 : Pose des dalles précontraintes\r\nDossier de concertation validé en octobre 2024",null,null,74110,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","79786","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","ERQUELINNES",2027,2027,41,42,"2027-10-15",45644.958333333336,"2027-10-18",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF \r\nFermeture point frontière Jeumont",null,null,79786,"2024-10-14",1,"5,6"]
[null,"Infrabel","79787","Erquelinnes - Montzen","< >","ERQUELINNES-FRONTIERE","ERQUELINNES",2027,2027,41,42,"2027-10-15",45644.958333333336,"2027-10-18",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF \r\nFermeture point frontière Jeumont 48h",null,null,79787,"2024-10-14",1,"5,6"]
[null,"Infrabel","73537","Namur - Antwerpen",">","OTTIGNIES","LIMAL",2027,2027,41,42,"2027-10-15",45644.9375,"2027-10-18",45644.208333333336,"2d, 06:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"chantier RER : travaux coeur Ottignies + travaux faisceau manage\r\nvoie A HS entre  AW04AR et AW 16BR\r\nvoie  121 (quais 1) HS et pas de garage de train possible",null,null,73537,"2024-11-05",0,"5,6"]
[null,"Infrabel","71505","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2027,2027,41,42,"2027-10-15",45644.9375,"2027-10-18",45644.180555555555,"2d, 05:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de Rails Y Soignies- Neufvilles\r\nRenouvellement de chapes OA BK 35.500 - 35.300 - 13.030 \r\nDossier de concertation validé en octobre 2024",null,null,71505,"2024-11-05",1,"5,6"]
[null,"Infrabel","73956","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,41,43,"2027-10-15",45644.944444444445,"2027-10-29",45644.993055555555,"14d, 01:10h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Modernisation Axe 3 - Tronçon Gembloux - Rhisnes\r\nMassification travaux (GC linéaire et ripage voies)\r\nDossier de concertation validé en octobre 2024\r\nNe pas massifier d'autres travaux au cas où cette TCR serait annulée suite CTL back Up RER pas nécessa",null,null,73956,"2024-11-18",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","77146","Lille - ZeeBrugge","< >","BRUGGE","Y.BLAUWE TOREN",2027,2027,41,42,"2027-10-15",45644.041666666664,"2027-10-18",45644.166666666664,"3d, 03:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Railvernieuwing + Massificatie Onderhoud\r\nSpoor VII en VIII te Brugge buiten dienst\r\nSpoor I bis te Brugge buiten dienst \r\n\r\nOverlegdossier 2027",null,null,77146,"2024-12-04",1,"5,6"]
[null,"Infrabel","78914","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,41,42,"2027-10-15",45644.993055555555,"2027-10-18",45644.159722222219,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW bereikbaar via omloopsspoor\r\nY.Melle West  moet vrijblijven ",null,null,78914,"2024-05-15",1,"5,6"]
[null,"Infrabel","84159","Namur - Antwerpen",">","TAMINES","CHATELET",2027,2027,41,41,"2027-10-16",45644.9375,"2027-10-17",45644.229166666664,"1d, 07:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Aménagement Châtelet - 2027 Phase 8.2.2\r\nCoupure type 1 de 2027\r\n6 Nuits\r\nCorrélation avec id 73521\r\nTCR: 526319",null,null,84159,"2024-11-20",0,"5,6"]
[null,"Infrabel","81850","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2027,2027,41,41,"2027-10-16",45644.25,"2027-10-17",45644.996527777781,"2d, 17:55h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRVB Aulnoye 24h",null,null,81850,"2024-09-23",1,"5,6"]
[null,"Infrabel","81104","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2027,2027,41,41,"2027-10-17",45644.333333333336,"2027-10-17",45644.625,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing\r\nUitbreiding op zondag bij 76771",null,null,81104,"2024-09-10",0,"5,6"]
[null,"Infrabel","76771","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,41,41,"2027-10-17",45644.041666666664,"2027-10-17",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76771,"2024-10-10",0,"5,6"]
[null,"Infrabel","81849","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2027,2027,42,42,"2027-10-18",45644.958333333336,"2027-10-22",45644.197916666664,"4d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRVB Aulnoye",null,null,81849,"2024-09-23",0,"1,2,3,4,5"]
[null,"Infrabel","74131","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.JURBISE",2027,2027,42,42,"2027-10-18",45644.965277777781,"2027-10-22",45644.180555555555,"4d, 05:10h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes OA BK 35.500 - 35.300 - 13.030 : Nuits préparations\r\n(+ Renouvellement rails)\r\nDossier de concertation validé en octobre 2024",null,null,74131,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","77687","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","Y.MELSELE",2027,2027,42,42,"2027-10-18",45644.996527777781,"2027-10-22",45644.1875,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van rails, dwarsliggers en spoorstaven L59 en 59/1\r\nWeeknachten",null,null,77687,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","78918","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,42,42,"2027-10-18",45644.993055555555,"2027-10-22",45644.159722222219,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW bereikbaar via omloopsspoor\r\nY.Melle West  moet vrijblijven ",null,null,78918,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","77719","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2027,2027,42,43,"2027-10-22",45644.989583333336,"2027-10-25",45644.180555555555,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\nMassification travaux\r\nDossier de concertation\r\n",null,null,77719,"2024-12-10",1,"5,6"]
[null,"Infrabel","78915","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,42,43,"2027-10-22",45644.993055555555,"2027-10-25",45644.159722222219,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW bereikbaar via omloopsspoor\r\nY.Melle West  moet vrijblijven ",null,null,78915,"2024-05-15",1,"5,6"]
[null,"Infrabel","69984","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,42,43,"2027-10-22",45644.923611111109,"2027-10-29",45644.958333333336,"7d, 00:50h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Rnvlt Pont 7 + chape Pont 14\r\nCTL 7 jours\r\nDossier de concertation validé en octobre 2024",null,null,69984,"2024-11-05",1,"1,2,3,4,5,6,7"]
[null,"Infrabel","71798","Lille - Charleroi","< >","ROUX","Y.NORD",2027,2027,42,42,"2027-10-23",45644.958333333336,"2027-10-24",45644.583333333336,"1d, 15:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPréparation caténaire\r\n15 - Transfert caténaire - Liaisons vers L. 112 et vers R52/2\r\n+ Maintenance Z13.52\r\n",null,null,71798,"2024-12-13",1,"5,6"]
[null,"Infrabel","81105","Namur - Antwerpen","< >","Y.ANTWERPEN-OOST","Y.HOLLAND",2027,2027,42,42,"2027-10-24",45644.333333333336,"2027-10-24",45644.625,"1d, 07:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing\r\nUitbreiding op zondag bij 76772",null,null,81105,"2024-09-10",0,"5,6"]
[null,"Infrabel","76772","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,42,42,"2027-10-24",45644.041666666664,"2027-10-24",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76772,"2024-10-10",0,"5,6"]
[null,"Infrabel","81848","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2027,2027,43,43,"2027-10-25",45644.958333333336,"2027-10-29",45644.197916666664,"4d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nRVB Aulnoye",null,null,81848,"2024-12-09",0,"1,2,3,4,5"]
[null,"Infrabel","78253","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,43,43,"2027-10-25",45644.986111111109,"2027-10-29",45644.208333333336,"4d, 05:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78253,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","77688","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","Y.MELSELE",2027,2027,43,43,"2027-10-25",45644.996527777781,"2027-10-29",45644.1875,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van rails, dwarsliggers en spoorstaven L59 en 59/1\r\nWeeknachten",null,null,77688,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","78919","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,43,43,"2027-10-25",45644.993055555555,"2027-10-29",45644.159722222219,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW bereikbaar via omloopsspoor\r\nY.Melle West  moet vrijblijven ",null,null,78919,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","78250","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,43,43,"2027-10-25",45644.427083333336,"2027-10-29",45644.625,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78250,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","74058","Namur - Antwerpen","< >","OTTIGNIES","FLEURUS",2027,2027,43,44,"2027-10-29",45644.965277777781,"2027-11-02",45644.201388888891,"3d, 05:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de chapes – 42.395 et 49.295 - WE CTL\r\n",null,null,74058,"2024-12-13",1,"5,6"]
[null,"Infrabel","71503","Lille - Charleroi","< >","BRAINE-LE-COMTE","JURBISE",2027,2027,43,45,"2027-10-29",45644.965277777781,"2027-11-08",45644.180555555555,"9d, 05:10h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de Rails Y Soignies- Neufvilles\r\nRenouvellement de chapes OA BK 35.500 - 35.300 - 13.030\r\nDossier de concertation validé en octobre 2024",null,null,71503,"2024-11-05",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","73883","Athus - Meuse","< >","HAVERSIN","MARLOIE",2027,2027,43,44,"2027-10-29",45644.986111111109,"2027-11-02",45644.180555555555,"3d, 04:40h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\nTronçon Haversin-Marloie\r\nMassification travaux\r\nRmq: lundi 1/11 férié\r\nART de stabilisation à déterminer selon nature travaux",null,null,73883,"2024-10-11",1,"5,6"]
[null,"Infrabel","76773","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,43,43,"2027-10-31",45644.041666666664,"2027-10-31",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76773,"2024-10-10",0,"5,6"]
[null,"Infrabel","78254","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,44,44,"2027-11-01",45644.986111111109,"2027-11-06",45644.208333333336,"5d, 05:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78254,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","77683","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","Y.MELSELE",2027,2027,44,45,"2027-11-01",45644.166666666664,"2027-11-08",45644.166666666664,"7d, 00:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van rails, dwarsliggers en spoorstaven L59 en 59/1\r\nHerfstvakantie",null,null,77683,"2024-05-09",1,"1,2,3,4,5,6,7"]
[null,"Infrabel","79114","Namur - Antwerpen",">","BRUXELLES-LUXEMBOURG","WATERMAEL",2027,2027,44,49,"2027-11-02",45644.166666666664,"2027-12-10",45644.993055555555,"39d, 19:50h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken B-ST Station Etterbeek: Auvents - panneaux sandwich + chéneaux",null,null,79114,"2024-11-20",2,"1,2,3,4,5,6,7"]
[null,"Infrabel","78251","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,44,44,"2027-11-02",45644.427083333336,"2027-11-05",45644.625,"4d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78251,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","75901","Athus - Meuse","< >","JAMBES","YVOIR",2027,2027,44,45,"2027-11-05",45644.979166666664,"2027-11-08",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Block Automatique Lustin-Yvoir : MES passage en EBP-PLP.\r\n\r\n",null,null,75901,"2024-11-19",1,"5,6"]
[null,"Infrabel","76774","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,44,44,"2027-11-07",45644.041666666664,"2027-11-07",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76774,"2024-10-10",0,"5,6"]
[null,"Infrabel","78255","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,45,45,"2027-11-08",45644.986111111109,"2027-11-13",45644.208333333336,"5d, 05:20h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78255,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","77690","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","Y.MELSELE",2027,2027,45,45,"2027-11-08",45644.996527777781,"2027-11-11",45644.1875,"3d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van rails, dwarsliggers en spoorstaven L59 en 59/1\r\nWeeknachten",null,null,77690,"2024-10-21",0,"1,2,3,4,5"]
[null,"Infrabel","73506","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,45,45,"2027-11-08",45644.923611111109,"2027-11-11",45644.173611111109,"3d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux finition des caniveaux signalisation\r\nDossier de concertation validé en octobre 2024",null,null,73506,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","78252","Namur - Antwerpen",">","SCHAERBEEK","SCHAERBEEK",2027,2027,45,45,"2027-11-08",45644.427083333336,"2027-11-12",45644.625,"5d, 04:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Werken station Schaarbeek (Tuc + B-ST): plaatsen dak\r\nFSR sp 10+11 BDS",null,null,78252,"2024-04-17",0,"1,2,3,4,5"]
[null,"Infrabel","76285","Lille - Antwerpen","< >","KORTRIJK","Y.ZANDBERG",2027,2027,45,45,"2027-11-09",45644.013888888891,"2027-11-12",45644.170138888891,"4d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ONB Hugo Verriest \r\nVervangen metalen spoordekken door betonnen bakbruggen (KP 40.732)\r\n+\r\nMassificatie Onderhoud\r\n",null,null,76285,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","79030","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2027,2027,45,45,"2027-11-09",45644.010416666664,"2027-11-12",45644.173611111109,"4d, 03:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud regio 1",null,null,79030,"2024-07-15",0,"1,2,3,4,5"]
[null,"Infrabel","74692","Athus - Meuse","< >","NEUFCHATEAU","LAVAUX",2027,2027,45,45,"2027-11-12",45644.979166666664,"2027-11-14",45644.708333333336,"2d, 17:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Travaux OA: Renouvellement PI 161.212\r\n",null,null,74692,"2024-11-19",1,"5,6"]
[null,"Infrabel","71506","Lille - Charleroi","< >","BRAINE-LE-COMTE","Y.JURBISE",2027,2027,45,46,"2027-11-12",45644.951388888891,"2027-11-15",45644.180555555555,"2d, 05:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement de Rails Y Soignies- Neufvilles\r\nRenouvellement de chapes OA BK 35.500 - 35.300 - 13.030\r\nDossier de concertation validé en octobre 2024",null,null,71506,"2024-11-05",1,"5,6"]
[null,"Infrabel","74959","Namur - Antwerpen",">","OTTIGNIES","LIMAL",2027,2027,45,46,"2027-11-12",45644.9375,"2027-11-15",45644.25,"2d, 07:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"chantier RER : travaux coeur Ottignies + travaux faisceau manage\r\nvoie A HS entre  AW04AR et AW 16BR\r\nvoie  121 (quais 1) HS et pas de garage de train possible",null,null,74959,"2024-05-08",0,"5,6"]
[null,"Infrabel","76283","Lille - Antwerpen","< >","KORTRIJK","Y.ZANDBERG",2027,2027,45,46,"2027-11-13",45644.013888888891,"2027-11-15",45644.170138888891,"2d, 03:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"ONB Hugo Verriest  \r\nVervangen metalen spoordekken door betonnen bakbruggen (KP 40.732)\r\n+\r\nOW91 Harmelen \r\n+\r\nBuitenwerken voor vernieuwing seininrichting \r\n\r\n+ \r\nMassificatie onderhoud\r\n\r\n\r\n",null,null,76283,"2024-12-10",1,"5,6"]
[null,"Infrabel","76775","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,45,45,"2027-11-14",45644.041666666664,"2027-11-14",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76775,"2024-10-10",0,"5,6"]
[null,"Infrabel","71812","Lille - Charleroi","< >","MARCHIENNE-AU-PONT","ROUX",2027,2027,46,46,"2027-11-15",45644.333333333336,"2027-11-19",45644.625,"4d, 07:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement Ballast  - C75\r\nFinition",null,null,71812,"2024-11-05",1,"1,2,3,4,5"]
[null,"Infrabel","73507","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,46,46,"2027-11-15",45644.923611111109,"2027-11-20",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux Caténaire (suppression traverses, poteaux) - finition des caniveaux signalisation\r\nDossier de concertation validé en octobre 2024",null,null,73507,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","76286","Lille - Antwerpen","< >","KORTRIJK","Y.ZANDBERG",2027,2027,46,46,"2027-11-16",45644.013888888891,"2027-11-19",45644.170138888891,"4d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ONB Hugo Verriest - \r\nVervangen metalen spoordekken door betonnen bakbruggen (KP 40.732)\r\n+\r\nMassificatie Onderhoud\r\n\r\n\r\n",null,null,76286,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","79031","Lille - Antwerpen","< >","KORTRIJK","DEINZE",2027,2027,46,46,"2027-11-16",45644.010416666664,"2027-11-20",45644.173611111109,"5d, 03:55h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud regio 1",null,null,79031,"2024-07-15",0,"1,2,3,4,5"]
[null,"Infrabel","73456","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,46,46,"2027-11-19",45644.333333333336,"2027-11-19",45644.989583333336,"2d, 15:45h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie B - Tx préparatoires\r\nSAVU R5",null,null,73456,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","73415","Athus - Meuse","< >","BEAURAING","VONECHE",2027,2027,46,47,"2027-11-19",45644.979166666664,"2027-11-22",45644.229166666664,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement ballast C75",null,null,73415,"2024-11-15",1,"5,6"]
[null,"Infrabel","73411","Athus - Meuse",">","BEAURAING","VONECHE",2027,2027,46,46,"2027-11-19",45644.25,"2027-11-19",45644.979166666664,"1d, 17:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Chantier C75  - Tx préparatoires\r\nSAVU R5",null,null,73411,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","73457","Namur - Antwerpen","< >","GEMBLOUX","NAMUR",2027,2027,46,47,"2027-11-19",45644.989583333336,"2027-11-22",45644.180555555555,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie B\r\n+Modernisation Axe 3 \r\nDossier de concertation validé en octobre 2024",null,null,73457,"2024-11-22",1,"5,6"]
[null,"Infrabel","76776","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,46,46,"2027-11-21",45644.041666666664,"2027-11-21",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76776,"2024-10-10",0,"5,6"]
[null,"Infrabel","79035","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2027,2027,47,47,"2027-11-22",45644.958333333336,"2027-11-26",45644.208333333336,"4d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud regio 1 \r\n",null,null,79035,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","73460","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,47,47,"2027-11-22",45644.958333333336,"2027-11-27",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie B\r\nBourrage de révision, contraintes et finitions",null,null,73460,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","76801","Namur - Antwerpen",">","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2027,2027,47,47,"2027-11-22",45644.958333333336,"2027-11-27",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Lange Weeknachten L25 sp A\r\nOVB Rechtstraat:",null,null,76801,"2024-03-06",0,"1,2,3,4,5"]
[null,"Infrabel","73458","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,47,47,"2027-11-22",45644.180555555555,"2027-11-22",45644.916666666664,"2d, 17:40h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie B - Tx pour remise en service\r\nSAVU R1",null,null,73458,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","79555","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2027,2027,47,47,"2027-11-22",45644.993055555555,"2027-11-27",45644.177083333336,"5d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie B\r\nBourrage de révision, contraintes et finitions\r\nSAVU voie A HS Gembloux - Rhisnes et CTL dans les blancs travaux",null,null,79555,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","73419","Athus - Meuse",">","BEAURAING","VONECHE",2027,2027,47,47,"2027-11-22",45644.229166666664,"2027-11-22",45644.916666666664,"1d, 16:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement ballast C75 - Tx pour remise en service\r\nSAVU R1",null,null,73419,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","73508","Erquelinnes - Montzen","< >","LA SAMBRE","ERQUELINNES-FRONTIERE",2027,2027,47,47,"2027-11-22",45644.923611111109,"2027-11-27",45644.173611111109,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement AS de Lobbes-Garage + allongement de la voie d'évitement\r\nTravaux Caténaire (suppression traverses, poteaux) - finition des caniveaux signalisation\r\nDossier de concertation validé en octobre 2024",null,null,73508,"2024-11-05",0,"1,2,3,4,5"]
[null,"Infrabel","79033","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2027,2027,47,48,"2027-11-26",45644.958333333336,"2027-11-29",45644.208333333336,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud regio 1 \r\n ",null,null,79033,"2024-12-10",1,"5,6"]
[null,"Infrabel","73416","Athus - Meuse","< >","BEAURAING","VONECHE",2027,2027,47,48,"2027-11-26",45644.979166666664,"2027-11-29",45644.229166666664,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement ballast C 75",null,null,73416,"2024-11-15",1,"5,6"]
[null,"Infrabel","73412","Athus - Meuse",">","BEAURAING","VONECHE",2027,2027,47,47,"2027-11-26",45644.25,"2027-11-26",45644.979166666664,"1d, 17:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement ballast C75 - Tx préparatoires\r\nSAVU R5",null,null,73412,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","78927","Namur - Antwerpen","< >","Y.WEST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,47,48,"2027-11-26",45644.993055555555,"2027-11-29",45644.159722222219,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW enkel bereikbaar via Melle-West\r\nY.Melle West  moet vrijblijven ",null,null,78927,"2024-10-28",1,"5,6"]
[null,"Infrabel","76777","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,47,47,"2027-11-28",45644.041666666664,"2027-11-28",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76777,"2024-10-10",0,"5,6"]
[null,"Infrabel","73461","Namur - Antwerpen",">","GEMBLOUX","RHISNES",2027,2027,48,48,"2027-11-29",45644.958333333336,"2027-12-04",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie B\r\nBourrage de révision, contraintes et finitions",null,null,73461,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","76802","Namur - Antwerpen",">","MECHELEN-NEKKERSPOEL","KONTICH-LINT",2027,2027,48,48,"2027-11-29",45644.958333333336,"2027-12-04",45644.208333333336,"5d, 06:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Lange Weeknachten L25 sp A\r\nOVB Rechtstraat:",null,null,76802,"2024-03-06",0,"1,2,3,4,5"]
[null,"Infrabel","79034","Lille - Antwerpen","< >","KORTRIJK","MOUSCRON",2027,2027,48,48,"2027-11-29",45644.958333333336,"2027-12-04",45644.208333333336,"5d, 06:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Massificatie onderhoud regio 1 \r\n",null,null,79034,"2024-12-10",0,"1,2,3,4,5"]
[null,"Infrabel","82982","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2027,2027,48,48,"2027-11-29",45644.958333333336,"2027-12-04",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nPMR Maubeuge",null,null,82982,"2024-10-18",0,"1,2,3,4,5"]
[null,"Infrabel","78958","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","Y.MELSELE",2027,2027,48,48,"2027-11-29",45644.996527777781,"2027-12-03",45644.1875,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van rails, dwarsliggers en spoorstaven L59 en 59/1\r\nWeeknachten",null,null,78958,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","78939","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,48,48,"2027-11-29",45644.993055555555,"2027-12-03",45644.159722222219,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW enkel bereikbaar via Melle-West\r\nY.Melle West  moet vrijblijven ",null,null,78939,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","79556","Namur - Antwerpen","< >","GEMBLOUX","RHISNES",2027,2027,48,48,"2027-11-29",45644.993055555555,"2027-12-04",45644.177083333336,"5d, 04:25h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Renouvellement du ballast par C75 en voie B\r\nBourrage de révision, contraintes et finitions\r\nSAVU voie A HS Gembloux - Rhisnes et CTL dans les blancs travaux",null,null,79556,"2024-11-18",0,"1,2,3,4,5"]
[null,"Infrabel","73420","Athus - Meuse",">","BEAURAING","VONECHE",2027,2027,48,48,"2027-11-29",45644.229166666664,"2027-11-29",45644.916666666664,"1d, 16:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement ballast C75 - Tx pour remise en service\r\nSAVU R1",null,null,73420,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","76287","Lille - Antwerpen","< >","KORTRIJK","Y.ZANDBERG",2027,2027,48,48,"2027-11-30",45644.013888888891,"2027-12-03",45644.170138888891,"4d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ONB Hugo Verriest -\r\nVervangen metalen spoordekken door betonnen bakbruggen (KP 40.732)\r\n\r\n\r\n",null,null,76287,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","78959","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","Y.MELSELE",2027,2027,48,49,"2027-12-03",45644.979166666664,"2027-12-06",45644.166666666664,"2d, 04:30h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van rails, dwarsliggers en spoorstaven L59 en 59/1",null,null,78959,"2024-09-06",1,"5,6"]
[null,"Infrabel","73417","Athus - Meuse","< >","BEAURAING","VONECHE",2027,2027,48,49,"2027-12-03",45644.979166666664,"2027-12-06",45644.229166666664,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement ballast C75",null,null,73417,"2024-11-15",1,"5,6"]
[null,"Infrabel","73413","Athus - Meuse",">","BEAURAING","VONECHE",2027,2027,48,48,"2027-12-03",45644.25,"2027-12-03",45644.979166666664,"1d, 17:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement ballast C75 - Tx préparatoires\r\nSAVU R5",null,null,73413,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","77721","Namur - Antwerpen","< >","NAMUR","GEMBLOUX",2027,2027,48,49,"2027-12-03",45644.989583333336,"2027-12-06",45644.180555555555,"2d, 04:35h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Modernisation Axe 3:\r\nTronçon bifurcation LLN - Gembloux\r\nMassification travaux validé en octobre 2024",null,null,77721,"2024-10-30",1,"5,6"]
[null,"Infrabel","78928","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,48,49,"2027-12-03",45644.993055555555,"2027-12-06",45644.159722222219,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW enkel bereikbaar via Melle-West\r\nY.Melle West  moet vrijblijven ",null,null,78928,"2024-05-08",1,"5,6"]
[null,"Infrabel","76284","Lille - Antwerpen","< >","KORTRIJK","Y.ZANDBERG",2027,2027,48,49,"2027-12-04",45644.013888888891,"2027-12-06",45644.170138888891,"2d, 03:45h","Continuous",null,"T","","",null,null,null,null,null,null,null,"ONB Hugo Verriest  \r\nVervangen metalen spoordekken door betonnen bakbruggen (KP 40.732)\"\r\n\r\n",null,null,76284,"2024-05-15",1,"5,6"]
[null,"Infrabel","71782","Lille - Charleroi","< >","ROUX","Y.NORD",2027,2027,48,48,"2027-12-04",45644.25,"2027-12-05",45644.666666666664,"1d, 10:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Aménagement Marchienne au Pont\r\nPréparation caténaire\r\n16 - Enlèvement 8 vieilles traverses 4 voies, et 5 sur liaisons L. 112\r\nPréparation signalisation\r\nTransferts Loge F21 F22 + F16 F17\r\nRQ333 : +1 WE",null,null,71782,"2024-10-17",1,"5,6"]
[null,"Infrabel","76778","Namur - Antwerpen",">","Y.ANTWERPEN-OOST","Y.ANTWERPEN-SCHIJNPOORT",2027,2027,48,48,"2027-12-05",45644.041666666664,"2027-12-05",45644.75,"2d, 17:00h","Periodical",null,"","LT+ST","",null,null,null,null,null,null,null,"Vernieuwing viaduct Luitenant Naeyaertplein\r\nRenovatie kunstwerken\r\nSpoorvernieuwing",null,null,76778,"2024-10-10",0,"5,6"]
[null,"Infrabel","82983","Erquelinnes - Montzen","< >","ERQUELINNES","ERQUELINNES-FRONTIERE",2027,2027,49,49,"2027-12-06",45644.958333333336,"2027-12-11",45644.197916666664,"5d, 05:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Travaux SNCF\r\nPMR Maubeuge",null,null,82983,"2024-10-18",0,"1,2,3,4,5"]
[null,"Infrabel","78961","Lille - Antwerpen","< >","ANTWERPEN-BERCHEM","Y.MELSELE",2027,2027,49,49,"2027-12-06",45644.996527777781,"2027-12-10",45644.1875,"4d, 04:35h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Vernieuwen van rails, dwarsliggers en spoorstaven L59 en 59/1\r\nWeeknachten",null,null,78961,"2024-09-05",0,"1,2,3,4,5"]
[null,"Infrabel","78940","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,49,49,"2027-12-06",45644.993055555555,"2027-12-10",45644.159722222219,"4d, 04:00h","Periodical",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW enkel bereikbaar via Melle-West\r\nY.Melle West  moet vrijblijven ",null,null,78940,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","73421","Athus - Meuse",">","BEAURAING","VONECHE",2027,2027,49,49,"2027-12-06",45644.229166666664,"2027-12-06",45644.916666666664,"1d, 16:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement ballast C75 - Tx pour remise en service\r\nSAVU R1",null,null,73421,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","76288","Lille - Antwerpen","< >","KORTRIJK","Y.ZANDBERG",2027,2027,49,49,"2027-12-07",45644.013888888891,"2027-12-10",45644.170138888891,"4d, 03:45h","Periodical",null,"T","","",null,null,null,null,null,null,null,"ONB Hugo Verriest \r\nVervangen metalen spoordekken door betonnen bakbruggen (KP 40.732)\r\n\r\n\r\n",null,null,76288,"2024-05-15",0,"1,2,3,4,5"]
[null,"Infrabel","73418","Athus - Meuse","< >","BEAURAING","VONECHE",2027,2027,49,50,"2027-12-10",45644.979166666664,"2027-12-13",45644.229166666664,"2d, 06:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Renouvellement ballast C75",null,null,73418,"2024-11-15",1,"5,6"]
[null,"Infrabel","73414","Athus - Meuse",">","BEAURAING","VONECHE",2027,2027,49,49,"2027-12-10",45644.25,"2027-12-10",45644.979166666664,"1d, 17:30h","Continuous",null,"","LT+ST","",null,null,null,null,null,null,null,"Renouvellement ballast C75 - Tx préparatoires\r\nSAVU R5",null,null,73414,"2024-11-15",0,"1,2,3,4,5"]
[null,"Infrabel","78929","Namur - Antwerpen","< >","Y.OOST DRIEHOEK LEDEBERG","Y.MELLE-WEST",2027,2027,49,50,"2027-12-10",45644.993055555555,"2027-12-13",45644.159722222219,"2d, 04:00h","Continuous",null,"T","","",null,null,null,null,null,null,null,"Merelbeke Bundel Centraal \r\nBundel Merelbeke centraal buiten dienst \r\nTW enkel bereikbaar via Melle-West\r\nY.Melle West  moet vrijblijven ",null,null,78929,"2024-07-17",1,"5,6"]

{"sheet":"ProRail","index":4,"n_rows":172,"n_cols":45,"rows_kept":172,"cut":false,"hidden":false,"merged":[[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]]}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Type of TCR","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)","Last update","Classification","Weekdays","Interval","Affected estimated travel volume","Affected border","Deviation location","Deviation border","Status","Additional information","Automatic process","Selected days","Variant value"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null," "," "]
[null,"ProRail","K008421-2501",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,1,2,"2025-01-04","01:00:00","2025-01-06","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Diverse BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-008421-2501-00-4&doc=FOT (Register with ProRail)",null,null,"K-008421","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2504",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,1,2,"2025-01-04","01:00:00","2025-01-06","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2504-00-4&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2502",null,">","Amsterdam Coenhaven","Amsterdam Coenhaven",2025,2025,2,3,"2025-01-11","01:00:00","2025-01-13","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoortak, dwarsligger, spoorstaven, overweg, wegaansluiting. conserveren kunstwerk Koelwaterkanaal * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2502-00-2&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2501",null,">","IJsselmonde","IJsselmonde",2025,2025,4,5,"2025-01-25","01:00:00","2025-01-27","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster IE-14 + IE-17 + IE-20 (saneren 2x GW en 3x EW, incl. vernieuwen ca. 1515m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2501-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004917-2501",null,">","Zevenbergen inhaalsp.","Roosendaal",2025,2025,4,5,"2025-01-25","01:00:00","2025-01-27","05:00:00","2d 04:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2501-00-5&doc=FOT (Register with ProRail)",null,null,"M-004917","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2506",null,">","Zevenbergen inhaalsp.","Roosendaal",2025,2025,4,5,"2025-01-25","01:00:00","2025-01-27","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2506-00-3&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007808-2511",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,4,5,"2025-01-25","17:00:00","2025-01-27","05:00:00","1d 12:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 279 A/B en 283 A/B door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2511-00-2&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2510",null,">","Amsterdam Westhaven Goederen","Amsterdam Westhaven Goederen",2025,2025,5,6,"2025-02-01","01:00:00","2025-02-03","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoortak, spoorstaven en overweg.  saneren harmelen * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2510-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-25B1",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B1-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2503",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Signal","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2503-00-2&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2501",null,">","Maasvlakte aansl.","Maasvlakte aansl.",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2501-00-2&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2511",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2511-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006108-2502",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2025,2025,5,6,"2025-02-01","01:00:00","2025-02-03","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2502-00-7&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2507",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,5,5,"2025-02-01","23:00:00","2025-02-02","23:00:00","1d 00:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 2371 A/B, 2375, 2395 A/B, 2397 A/B en 2399 A/B door de NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2507-00-1&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2501",null,">","Waalhaven Zuid aansl. Noord","Waalhaven Zuid aansl. Noord",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2501-00-2&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2550",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,5,6,"2025-02-01","23:00:00","2025-02-03","07:00:00","1d 08:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2550-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2517",null,">","Europoort","Europoort",2025,2025,6,6,"2025-02-03","20:00:00","2025-02-05","00:00:00","1d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster ER-14 (ca. 409m sps) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2517-00-3&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2505",null,">","Waalhaven Zuid","Waalhaven Zuid",2025,2025,6,6,"2025-02-08","01:00:00","2025-02-09","09:00:00","1d 08:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster WR-07 + WR-08 (1x 1:9 GW en ca. 202m spoor + OVW) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2505-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K008401-RT18",null,">","Gouda","Gouda",2025,2025,6,6,"2025-02-08","01:00:00","2025-02-09","17:00:00","1d 16:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vernieuwen spoorstaven, spoortak, overwegbevloering, wissel. * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT18-00-2&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007808-2512",null,">","Rotterdam Westelijke Splitsing","Rotterdam Westelijke Splitsing",2025,2025,6,7,"2025-02-09","01:00:00","2025-02-10","01:00:00","0d 00:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 173 A/B, 199, 211 A/B, 251 A/B en 293A * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2512-00-3&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2511",null,">","Roosendaal","Bergen op Zoom",2025,2025,6,7,"2025-02-08","01:00:00","2025-02-10","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2511-00-5&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2504",null,">","Amsterdam Coenhaven","Amsterdam Coenhaven",2025,2025,7,7,"2025-02-15","01:00:00","2025-02-16","09:00:00","1d 08:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoorstaven, dwarsliggers en wegaansluiting * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2504-00-2&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE032-2506",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,7,8,"2025-02-15","01:00:00","2025-02-17","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"TVP tbv inbrengen van kabels in kabelkoker derde perron. * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE032-2506-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE032","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2502",null,">","Rotterdam Stadion","Rotterdam Stadion",2025,2025,8,9,"2025-02-22","01:00:00","2025-02-24","05:00:00","2d 04:00","continuous","Track & Rail","","LT",null,null,null,null,null,null,null,null,"Cluster IE-20 + IE-23 (ca. 826m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2502-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004966-2501",null,">","Roosendaal","Bergen op Zoom",2025,2025,10,10,"2025-03-08","01:00:00","2025-03-09","01:00:00","0d 00:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen rijdraden tussen Roosendaal (Rsd) en Bergen op Zoom (Bgn) * More details: https://btd-planner.prorail.nl?taak=IO-M-004966-2501-00-5&doc=FOT (Register with ProRail)",null,null,"M-004966","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2512",null,">","Roosendaal","Roosendaal grens",2025,2025,10,11,"2025-03-08","01:00:00","2025-03-10","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2512-00-3&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004897-FL02",null,">","Roosendaal","Roosendaal grens",2025,2025,10,11,"2025-03-08","01:00:00","2025-03-10","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren van spoorviaduct in 3 perioden van 52u * More details: https://btd-planner.prorail.nl?taak=IO-M-004897-FL02-00-4&doc=FOT (Register with ProRail)",null,null,"M-004897","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004987-2501",null,">","Roosendaal","Roosendaal grens",2025,2025,10,10,"2025-03-08","01:00:00","2025-03-09","05:00:00","1d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen sps (L+R) bij overweg Willem Dreesweg en vernieuwen spoortak kopspoor bij grens België * More details: https://btd-planner.prorail.nl?taak=IO-M-004987-2501-00-3&doc=FOT (Register with ProRail)",null,null,"M-004987","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2505",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,11,12,"2025-03-14","01:00:00","2025-03-17","05:00:00","3d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"vernieuwen wissel, spoortak en paden * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2505-00-2&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2507",null,">","Waalhaven Zuid","Waalhaven Zuid",2025,2025,11,12,"2025-03-15","08:00:00","2025-03-17","12:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster WR-18 (OVW 21m en ca. 31m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2507-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006108-2507",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2025,2025,11,12,"2025-03-15","01:00:00","2025-03-17","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2507-00-2&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005346-2530",null,">","Amersfoort Centraal","Amersfoort Centraal",2025,2025,11,11,"2025-03-10","01:00:00","2025-03-14","09:00:00","4d 08:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-L-005346-2530-00-6&doc=FOT (Register with ProRail)",null,null,"L-005346","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2503",null,">","Waalhaven Zuid","Waalhaven Zuid",2025,2025,12,13,"2025-03-22","01:00:00","2025-03-24","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster WE-19 (1x 1:9 EW, 2x 1:9 GW en ca. 60m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2503-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE032-2501",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,12,13,"2025-03-22","01:00:00","2025-03-29","01:00:00","6d 00:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Inbouwen nieuw wissel voor TVP stap 1J. Betreft wissel 2555 * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE032-2501-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE032","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2508",null,">","Waalhaven Zuid","Waalhaven Zuid",2025,2025,13,14,"2025-03-29","01:00:00","2025-03-31","06:00:00","2d 05:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster WR-19 + WR-22 (3x 1:9 GW en ca. 442m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2508-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007808-2509",null,">","Rotterdam Westelijke Splitsing","Rotterdam Westelijke Splitsing",2025,2025,13,14,"2025-03-29","01:00:00","2025-03-31","06:00:00","2d 05:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 255A, 259A, 271, 273B en 277A/B * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2509-00-1&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT04",null,">","Rotterdam Noord goed. West","Rotterdam Westelijke Splitsing",2025,2025,13,14,"2025-03-29","01:00:00","2025-03-31","06:00:00","2d 05:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen spoortak, overwegbevloering, inspectiepad, regelbare bevestiging, blokkenspoor, overgangsconstructie * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT04-00-3&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005346-2531",null,">","Amersfoort Centraal","Amersfoort Centraal",2025,2025,13,13,"2025-03-24","01:00:00","2025-03-26","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"BBV werkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-L-005346-2531-00-2&doc=FOT (Register with ProRail)",null,null,"L-005346","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005346-2522",null,">","Amersfoort Centraal","Amersfoort Centraal",2025,2025,13,13,"2025-03-30","01:00:00","2025-03-30","18:00:00","0d 17:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Vernieuwen bevestigingsmiddelen * More details: https://btd-planner.prorail.nl?taak=IO-L-005346-2522-00-2&doc=FOT (Register with ProRail)",null,null,"L-005346","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R552900-2501",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,13,17,"2025-03-29","01:00:00","2025-04-21","06:00:00","23d 05:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden aan Fietsenstalling onder de sporen. Vrijdragend maken van het 4de perron. * More details: https://btd-planner.prorail.nl?taak=IO-R-552900-2501-00-1&doc=FOT (Register with ProRail)",null,null,"R-552900","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008421-2502",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,14,15,"2025-04-05","01:00:00","2025-04-07","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Diverse BBV werkzaamheden. * More details: https://btd-planner.prorail.nl?taak=IO-K-008421-2502-00-6&doc=FOT (Register with ProRail)",null,null,"K-008421","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005430-2507",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,14,15,"2025-04-05","01:00:00","2025-04-07","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"vernieuwen spoorstaven incl. raildraagplaat. * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2507-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2510",null,">","Botlek","Botlek",2025,2025,14,15,"2025-04-06","08:00:00","2025-04-07","12:00:00","1d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster BR-02 (1x 1:9 GW) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2510-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2514",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,14,15,"2025-04-05","01:00:00","2025-04-07","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2514-00-5&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005346-2521",null,">","Amersfoort Centraal","Amersfoort Centraal",2025,2025,14,14,"2025-04-05","01:00:00","2025-04-06","05:00:00","1d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Vernieuwen bevestigingsmiddelen * More details: https://btd-planner.prorail.nl?taak=IO-L-005346-2521-00-1&doc=FOT (Register with ProRail)",null,null,"L-005346","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008718-TP01",null,">","Maasvlakte West","Maasvlakte West",2025,2025,15,16,"2025-04-07","08:00:00","2025-04-17","08:00:00","10d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Herstellen/in dienst stellen van tankplaat spoor 870 * More details: https://btd-planner.prorail.nl?taak=IO-K-008718-TP01-00-4&doc=FOT (Register with ProRail)",null,null,"K-008718","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2510",null,">","Roosendaal","Bergen op Zoom",2025,2025,15,16,"2025-04-12","01:00:00","2025-04-14","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2510-00-4&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-25B2",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2025,2025,16,17,"2025-04-19","07:00:00","2025-04-21","11:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B2-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2512",null,">","Botlek","Botlek",2025,2025,16,17,"2025-04-19","08:00:00","2025-04-21","08:00:00","2d 00:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster BR-20 (2x OVW 9,6m en ca. 55m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2512-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2502",null,">","Maasvlakte aansl.","Maasvlakte aansl.",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2502-00-3&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2520",null,">","Maasvlakte Europahaven zuid","Maasvlakte Europahaven zuid",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Track & Rail","","LT",null,null,null,null,null,null,null,null,"Cluster MR-04 (ca. 438 spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2520-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2501",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Signal","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2501-00-3&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2519",null,">","Maasvlakte Europahaven zuid","Maasvlakte Europahaven zuid",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-25","19:00:00","5d 00:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Cluster ME-13 (1x 1:9 EW, 6x 1:9 GW en ca. 153m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2519-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2512",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,16,17,"2025-04-19","23:00:00","2025-04-22","03:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2512-00-2&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R577400-2502",null,">","Europoort","Europoort",2025,2025,16,16,"2025-04-19","19:00:00","2025-04-20","07:00:00","0d 12:00","continuous","Catenary","","ST",null,null,null,null,null,null,null,null,"electrificering (aanpassen bovenleiding) * More details: https://btd-planner.prorail.nl?taak=IO-R-577400-2502-00-1&doc=FOT (Register with ProRail)",null,null,"R-577400","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2504",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 3569, 3623, 3633, 3635 en 3769 door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2504-00-1&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2502",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2502-00-3&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004987-2509",null,">","Moerdijk","Moerdijk",2025,2025,16,17,"2025-04-19","01:00:00","2025-04-22","05:00:00","3d 04:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vernieuwen spoortakken en 3 wissels * More details: https://btd-planner.prorail.nl?taak=IO-M-004987-2509-00-2&doc=FOT (Register with ProRail)",null,null,"M-004987","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-2551",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,16,17,"2025-04-19","19:00:00","2025-04-21","23:00:00","2d 04:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2551-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004863-2502",null,">","Roosendaal","Roosendaal",2025,2025,17,39,"2025-04-24","07:00:00","2025-09-23","07:00:00","151d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Tankplaat verplaatsen. * More details: https://btd-planner.prorail.nl?taak=IO-M-004863-2502-00-2&doc=FOT (Register with ProRail)",null,null,"M-004863","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005509-2516",null,">","Singelgracht aansl.","Singelgracht aansl.",2025,2025,18,18,"2025-05-03","01:00:00","2025-05-04","01:00:00","0d 00:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen dwarsliggers en bevestigingsmiddelen. * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2516-00-1&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE032-2507",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,19,20,"2025-05-10","01:00:00","2025-05-12","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"TVP tbv inbrengen van kabels in kabelkoker derde perron. * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE032-2507-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE032","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2513",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,19,20,"2025-05-10","01:00:00","2025-05-12","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen dwarsligger, spoorstaven, bevestigingsmiddelen en spoorstaven * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2513-00-3&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005467-2507",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,19,20,"2025-05-11","21:00:00","2025-05-12","09:00:00","0d 12:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Werkzaamheden aan KW Noordzeeweg in lang nachtgat * More details: https://btd-planner.prorail.nl?taak=IO-L-005467-2507-00-3&doc=FOT (Register with ProRail)",null,null,"L-005467","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008421-2503",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,20,21,"2025-05-17","01:00:00","2025-05-19","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Diverse BBV werkzaamheden. * More details: https://btd-planner.prorail.nl?taak=IO-K-008421-2503-00-3&doc=FOT (Register with ProRail)",null,null,"K-008421","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004987-2512",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,20,21,"2025-05-17","01:00:00","2025-05-19","05:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen wisselstellers * More details: https://btd-planner.prorail.nl?taak=IO-M-004987-2512-00-3&doc=FOT (Register with ProRail)",null,null,"M-004987","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2515",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,20,21,"2025-05-17","01:00:00","2025-05-19","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2515-00-3&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006108-2509",null,">","Zevenbergschenhoek aansl.","HSL breda grens overloop",2025,2025,21,22,"2025-05-24","01:00:00","2025-05-26","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2509-00-1&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT12",null,">","Rotterdam Westelijke Splitsing","Rotterdam Westelijke Splitsing",2025,2025,21,22,"2025-05-24","01:00:00","2025-05-26","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen ballast, regelbare bevestiging, broekbalken * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT12-00-2&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005417-2510",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,21,22,"2025-05-24","01:00:00","2025-05-26","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Afwerken Ij-viaduct * More details: https://btd-planner.prorail.nl?taak=IO-L-005417-2510-00-3&doc=FOT (Register with ProRail)",null,null,"L-005417","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007206-25AA",null,">","Willemstunnel Zuid","Rotterdam Westelijke Splitsing",2025,2025,21,22,"2025-05-24","01:00:00","2025-05-26","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Indienstellen nieuwe IXL Rotterdam * More details: https://btd-planner.prorail.nl?taak=IO-K-007206-25AA-00-3&doc=FOT (Register with ProRail)",null,null,"K-007206","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE042-2501",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,21,22,"2025-05-25","01:00:00","2025-05-26","00:50:00","0d 23:50","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden stijgpunten perrons * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE042-2501-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE042","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2517",null,">","Amsterdam Zaanstraat","Amsterdam Zaanstraat",2025,2025,22,23,"2025-05-30","01:00:00","2025-06-02","05:00:00","3d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen sporen en wissels * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2517-00-1&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-25B3",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2025,2025,23,24,"2025-06-07","07:00:00","2025-06-09","11:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B3-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2514",null,">","Botlek Theemsweg aansl.","Botlek Theemsweg aansl.",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-10","11:00:00","2d 16:00","continuous","Track & Rail","","LT",null,null,null,null,null,null,null,null,"Cluster ER-05 + ER-06 (2x OVW 21m en ca. 235m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2514-00-3&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2521",null,">","Maasvlakte West","Maasvlakte West",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Track & Rail","","LT",null,null,null,null,null,null,null,null,"Cluster MR-06 + MR-07 + MR-08 (2x 1:9 GW en ca. 256 spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2521-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2502",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Signal","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2502-00-1&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R577400-2501",null,">","Europoort","Europoort",2025,2025,23,24,"2025-06-07","23:00:00","2025-06-10","03:00:00","2d 04:00","continuous","Catenary","","ST",null,null,null,null,null,null,null,null,"electrificering (aanpassen bovenleiding) * More details: https://btd-planner.prorail.nl?taak=IO-R-577400-2501-00-2&doc=FOT (Register with ProRail)",null,null,"R-577400","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2510",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 2371 A/B, 2375, 2395 A/B, 2397 A/B en 2399 A/B door de NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2510-00-1&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT19",null,">","Rotterdam Noord goed. West","Rotterdam Westelijke Splitsing",2025,2025,23,24,"2025-06-07","01:00:00","2025-06-09","05:00:00","2d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen spoortak, overwegbevloering, inspectiepad, regelbare bevestiging, blokkenspoor, overgangsconstructie * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT19-00-3&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2511",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,23,24,"2025-06-07","01:00:00","2025-06-10","05:00:00","3d 04:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen dwarsligger, spoorstaven, bevestigingsmiddelen en spoorstaven en bouwen RIP * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2511-00-3&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2503",null,">","Waalhaven Zuid aansl. Noord","Waalhaven Zuid aansl. Noord",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Switch","","LT",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2503-00-3&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2503",null,">","Maasvlakte aansl.","Maasvlakte aansl.",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2503-00-3&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2513",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2513-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2552",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,23,24,"2025-06-07","19:00:00","2025-06-09","23:00:00","2d 04:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2552-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT17",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,24,25,"2025-06-14","01:00:00","2025-06-16","05:00:00","2d 04:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Vernieuwen spoortak, overwegbevloering, dwarsliggers, ballast, * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT17-00-2&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004966-2502",null,">","Roosendaal","Bergen op Zoom",2025,2025,25,26,"2025-06-21","01:00:00","2025-06-23","05:00:00","2d 04:00","continuous","Catenary","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen rijdraden tussen Roosendaal (Rsd) en Bergen op Zoom (Bgn) * More details: https://btd-planner.prorail.nl?taak=IO-M-004966-2502-00-4&doc=FOT (Register with ProRail)",null,null,"M-004966","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004987-2502",null,">","Roosendaal","Vlakebrug o/h Kanaal door Zuid-Beveland",2025,2025,25,26,"2025-06-21","01:00:00","2025-06-23","05:00:00","2d 04:00","continuous","Switch","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwingen (spoortakken, overwegbevloeringen, dwarsliggers + ballast, wissels, wisselverwarm.) en aanleggen drainage * More details: https://btd-planner.prorail.nl?taak=IO-M-004987-2502-00-6&doc=FOT (Register with ProRail)",null,null,"M-004987","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004897-FL03",null,">","Roosendaal","Roosendaal grens",2025,2025,25,26,"2025-06-21","01:00:00","2025-06-23","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren van spoorviaduct in 3 perioden van 52u * More details: https://btd-planner.prorail.nl?taak=IO-M-004897-FL03-00-3&doc=FOT (Register with ProRail)",null,null,"M-004897","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2509",null,">","Roosendaal","Roosendaal grens",2025,2025,25,26,"2025-06-21","01:00:00","2025-06-23","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2509-00-6&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","L005417-2511",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,26,27,"2025-06-28","01:00:00","2025-06-30","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Afwerken Ij-viaduct * More details: https://btd-planner.prorail.nl?taak=IO-L-005417-2511-00-4&doc=FOT (Register with ProRail)",null,null,"L-005417","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006146-2508",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,27,27,"2025-06-30","08:00:00","2025-07-05","08:00:00","5d 00:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"vervangen TTI * More details: https://btd-planner.prorail.nl?taak=IO-K-006146-2508-00-1&doc=FOT (Register with ProRail)",null,null,"K-006146","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007808-2510",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,27,28,"2025-07-06","02:00:00","2025-07-07","05:00:00","1d 03:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 221 A/B en 243 A door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2510-00-2&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006146-2507",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,28,28,"2025-07-07","08:00:00","2025-07-12","08:00:00","5d 00:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"vervangen TTI (A15 West) * More details: https://btd-planner.prorail.nl?taak=IO-K-006146-2507-00-2&doc=FOT (Register with ProRail)",null,null,"K-006146","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006146-2509",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,29,29,"2025-07-14","08:00:00","2025-07-19","08:00:00","5d 00:00","continuous","Tunnel","","LT+ST",null,null,null,null,null,null,null,null,"vervangen TTI (A15 West) * More details: https://btd-planner.prorail.nl?taak=IO-K-006146-2509-00-2&doc=FOT (Register with ProRail)",null,null,"K-006146","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT13",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,31,32,"2025-07-28","01:00:00","2025-08-04","05:00:00","7d 04:00","continuous","Switch","","ST",null,null,null,null,null,null,null,null,"Vernieuwen wissels, bevestigingsmiddelen, spoortak, overwegbvloering Saneren wissels * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT13-00-4&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2515",null,">","Europoort","Europoort",2025,2025,31,32,"2025-08-02","08:00:00","2025-08-04","00:00:00","1d 16:00","continuous","Track & Rail","","ST",null,null,null,null,null,null,null,null,"Cluster ER-09 + ER-10 (OVW 26,4m en ca. 150m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2515-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-25B4",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Track & Rail","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B4-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2404",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Signal","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2404-00-1&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006108-2506",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2025,2025,31,32,"2025-08-02","01:00:00","2025-08-04","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2506-00-2&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE032-2508",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,31,32,"2025-08-02","01:00:00","2025-08-04","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"TVP tbv inbrengen van kabels in kabelkoker derde perron. * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE032-2508-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE032","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2514",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,31,31,"2025-08-02","23:00:00","2025-08-03","23:00:00","1d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 3311, 3313, 3315, 3317, 3319, 3321 en 3237A door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2514-00-4&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2519",null,">","Kijfhoek aansluiting noord","Waalhaven Zuid aansl. Noord",2025,2025,31,31,"2025-08-02","23:00:00","2025-08-03","23:00:00","1d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2519-00-1&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2504",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2504-00-2&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006136-5BWS",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"BWK testen 2025  Sophiatunnel  LET OP: Niet tegelijk met BWK Pankan tunnel en niet tegelijk met  TTI plannen * More details: https://btd-planner.prorail.nl?taak=IO-K-006136-5BWS-00-2&doc=FOT (Register with ProRail)",null,null,"K-006136","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008410-2502",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2025,2025,31,31,"2025-08-02","23:00:00","2025-08-03","15:00:00","0d 16:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen pompen * More details: https://btd-planner.prorail.nl?taak=IO-K-008410-2502-00-1&doc=FOT (Register with ProRail)",null,null,"K-008410","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2504",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2504-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2514",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2514-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2553",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,31,32,"2025-08-02","23:00:00","2025-08-04","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2553-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2508",null,">","Amsterdam Westhaven Goederen","Amsterdam Westhaven Goederen",2025,2025,33,33,"2025-08-16","01:00:00","2025-08-17","09:00:00","1d 08:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"vernieuwen dwarsliggers en ballast * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2508-00-2&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2516",null,">","Europoort","Europoort",2025,2025,34,34,"2025-08-18","20:00:00","2025-08-20","00:00:00","1d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Cluster ER-14 (ca. 409m sps) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2516-00-4&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004917-2503",null,">","Zevenbergen inhaalsp.","Roosendaal",2025,2025,35,36,"2025-08-30","01:00:00","2025-09-01","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2503-00-2&doc=FOT (Register with ProRail)",null,null,"M-004917","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006108-2508",null,">","Zevenbergschenhoek aansl.","Zevenbergschenhoek aansl.",2025,2025,36,37,"2025-09-06","01:00:00","2025-09-08","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2508-00-3&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008410-2503",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2025,2025,36,36,"2025-09-06","23:00:00","2025-09-07","15:00:00","0d 16:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen pompen * More details: https://btd-planner.prorail.nl?taak=IO-K-008410-2503-00-2&doc=FOT (Register with ProRail)",null,null,"K-008410","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R3AE042-2502",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,36,36,"2025-09-04","01:00:00","2025-09-05","00:50:00","0d 23:50","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden stijgpunten perrons * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE042-2502-00-3&doc=FOT (Register with ProRail)",null,null,"R-3AE042","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2506",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,37,38,"2025-09-12","01:00:00","2025-09-15","05:00:00","3d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"verniewen, wissel, ballast, spoortak en paden. * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2506-00-4&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","Z906301-2501",null,">","Zwijndrecht","Zwijndrecht",2025,2025,37,38,"2025-09-13","01:00:00","2025-09-15","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren/ dakdekken * More details: https://btd-planner.prorail.nl?taak=IO-Z-906301-2501-00-2&doc=FOT (Register with ProRail)",null,null,"Z-906301","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT15",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,37,38,"2025-09-13","01:00:00","2025-09-15","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Vernieuwen sporen 21m, 22m, 23m, 25m, 26m * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT15-00-2&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2512",null,">","Singelgracht aansl.","Singelgracht aansl.",2025,2025,37,38,"2025-09-13","17:00:00","2025-09-15","05:00:00","1d 12:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen dwarsligger, spoorstaven, bevestigingsmiddelen en spoorstaven * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2512-00-4&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2502",null,">","Zwijndrecht","Zwijndrecht",2025,2025,37,38,"2025-09-13","01:00:00","2025-09-15","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2502-00-5&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008410-2501",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,37,38,"2025-09-13","01:00:00","2025-09-15","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen pompen * More details: https://btd-planner.prorail.nl?taak=IO-K-008410-2501-00-2&doc=FOT (Register with ProRail)",null,null,"K-008410","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008410-2505",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2025,2025,37,37,"2025-09-13","23:00:00","2025-09-14","11:00:00","0d 12:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen ventilatoren. * More details: https://btd-planner.prorail.nl?taak=IO-K-008410-2505-00-1&doc=FOT (Register with ProRail)",null,null,"K-008410","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005467-2508",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,37,37,"2025-09-13","21:00:00","2025-09-14","09:00:00","0d 12:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Werkzaamheden aan KW Noordzeeweg in lang nachtgat * More details: https://btd-planner.prorail.nl?taak=IO-L-005467-2508-00-3&doc=FOT (Register with ProRail)",null,null,"L-005467","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R551400-2501",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,37,38,"2025-09-13","01:00:00","2025-09-15","05:00:00","2d 04:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Aansluiten nieuwe opstelsporen en vernieuwen sporen * More details: https://btd-planner.prorail.nl?taak=IO-R-551400-2501-00-2&doc=FOT (Register with ProRail)",null,null,"R-551400","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","KX00010-25B5",null,">","Maasvlakte Yangtzehaven Zuid","Maasvlakte Yangtzehaven Zuid",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-22","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B5-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2505",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-22","07:00:00","1d 08:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2505-00-1&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007808-2507",null,">","Rotterdam Westelijke Splitsing","Rotterdam Westelijke Splitsing",2025,2025,38,39,"2025-09-20","01:00:00","2025-09-22","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 173 A/B, 199, 211 A/B, 251 A/B en 293A * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2507-00-3&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007208-2511",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,38,39,"2025-09-21","04:00:00","2025-09-22","04:00:00","0d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 2327, 3531, 2325 A/B, 2329 A/B en 2331A/B door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2511-00-3&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2515",null,">","Singelgracht aansl.","Singelgracht aansl.",2025,2025,38,38,"2025-09-20","01:00:00","2025-09-21","01:00:00","0d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Aanpassen talud, vervangen bevestigingsmiddelen * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2515-00-5&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2505",null,">","Waalhaven Zuid aansl. Noord","Waalhaven Zuid aansl. Noord",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-22","07:00:00","1d 08:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2505-00-2&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008423-2501",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-25","23:00:00","5d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Ombouw VPI naar nieuwe interlocking * More details: https://btd-planner.prorail.nl?taak=IO-K-008423-2501-00-5&doc=FOT (Register with ProRail)",null,null,"K-008423","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2505",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-23","03:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2505-00-5&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2515",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-22","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2515-00-2&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2554",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,38,39,"2025-09-20","23:00:00","2025-09-22","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2554-00-2&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008401-RT14",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,39,40,"2025-09-27","01:00:00","2025-09-29","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Vernieuwen wissels 295A, 295B en 297, vernieuwen overwegbevloering, vernieuwen sporen * More details: https://btd-planner.prorail.nl?taak=IO-K-008401-RT14-00-2&doc=FOT (Register with ProRail)",null,null,"K-008401","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2509",null,">","Amsterdam Westhaven Goederen","Amsterdam Westhaven Goederen",2025,2025,39,40,"2025-09-27","01:00:00","2025-09-29","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoortak, spoorstaven, overweg, en wegaansluiting * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2509-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2503",null,">","Amsterdam Coenhaven","Amsterdam Coenhaven",2025,2025,40,41,"2025-10-04","01:00:00","2025-10-06","05:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoortak, overweg en wegaansluiting * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2503-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007808-2508",null,">","Rotterdam Centraal","Rotterdam Centraal",2025,2025,41,42,"2025-10-12","09:00:00","2025-10-13","05:00:00","0d 20:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers van 237 en 291 B door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007808-2508-00-3&doc=FOT (Register with ProRail)",null,null,"K-007808","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004987-2517",null,">","Roosendaal","Roosendaal grens",2025,2025,41,42,"2025-10-10","01:00:00","2025-10-19","05:00:00","9d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Spoorvernieuwingen en aanbrengen wisselverwarming * More details: https://btd-planner.prorail.nl?taak=IO-M-004987-2517-00-8&doc=FOT (Register with ProRail)",null,null,"M-004987","2024-01-04","High",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004897-FL04",null,">","Roosendaal","Roosendaal grens",2025,2025,41,42,"2025-10-11","01:00:00","2025-10-13","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren van spoorviaduct in 3 perioden van 52u * More details: https://btd-planner.prorail.nl?taak=IO-M-004897-FL04-00-3&doc=FOT (Register with ProRail)",null,null,"M-004897","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2513",null,">","Roosendaal","Bergen op Zoom",2025,2025,41,42,"2025-10-11","01:00:00","2025-10-13","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2513-00-5&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","ER50008-2508",null,">","Roosendaal","Roosendaal",2025,2025,42,42,"2025-10-14","13:00:00","2025-10-16","17:00:00","2d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2508-00-4&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Minor",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004917-2502",null,">","Zevenbergen inhaalsp.","Roosendaal",2025,2025,43,44,"2025-10-25","01:00:00","2025-10-27","04:00:00","2d 03:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen betonnen bovenleiding portalen * More details: https://btd-planner.prorail.nl?taak=IO-M-004917-2502-00-2&doc=FOT (Register with ProRail)",null,null,"M-004917","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K006146-2511",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,44,44,"2025-10-30","08:00:00","2025-11-02","16:00:00","3d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen TTI (A15 West) * More details: https://btd-planner.prorail.nl?taak=IO-K-006146-2511-00-2&doc=FOT (Register with ProRail)",null,null,"K-006146","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005509-2514",null,">","Singelgracht aansl.","Singelgracht aansl.",2025,2025,44,45,"2025-11-01","01:00:00","2025-11-03","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen bevestigingsmiddelen * More details: https://btd-planner.prorail.nl?taak=IO-L-005509-2514-00-1&doc=FOT (Register with ProRail)",null,null,"L-005509","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005467-2506",null,">","Radarweg aansl.","Radarweg aansl.",2025,2025,44,45,"2025-11-01","01:00:00","2025-11-03","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Herstel kabelkokers op KW Hemboog. Periode nodig om materiaal via RIP aan te voeren. * More details: https://btd-planner.prorail.nl?taak=IO-L-005467-2506-00-5&doc=FOT (Register with ProRail)",null,null,"L-005467","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2505",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,44,45,"2025-11-01","01:00:00","2025-11-03","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS Parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2505-00-3&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R551400-2502",null,">","Lage Zwaluwe","Lage Zwaluwe",2025,2025,44,45,"2025-11-01","01:00:00","2025-11-03","05:00:00","2d 04:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"Aansluiten nieuwe opstelsporen en vernieuwen sporen * More details: https://btd-planner.prorail.nl?taak=IO-R-551400-2502-00-3&doc=FOT (Register with ProRail)",null,null,"R-551400","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","R3AE042-2503",null,">","Amsterdam Centraal","Amsterdam Centraal",2025,2025,44,45,"2025-11-02","01:00:00","2025-11-03","00:50:00","0d 23:50","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Werkzaamheden stijgpunten perrons * More details: https://btd-planner.prorail.nl?taak=IO-R-3AE042-2503-00-2&doc=FOT (Register with ProRail)",null,null,"R-3AE042","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007206-25BB",null,">","Willemstunnel Zuid","Rotterdam Westelijke Splitsing",2025,2025,45,46,"2025-11-08","01:00:00","2025-11-10","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Indienstellen nieuwe IXL Rotterdam * More details: https://btd-planner.prorail.nl?taak=IO-K-007206-25BB-00-2&doc=FOT (Register with ProRail)",null,null,"K-007206","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","L005430-2501",null,">","Amsterdam Coenhaven","Amsterdam Coenhaven",2025,2025,47,48,"2025-11-22","01:00:00","2025-11-24","01:00:00","1d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"vernieuwen spoortak, overwegen, wegaansluiting, dwarliggers * More details: https://btd-planner.prorail.nl?taak=IO-L-005430-2501-00-3&doc=FOT (Register with ProRail)",null,null,"L-005430","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2511",null,">","Botlek","Botlek",2025,2025,47,47,"2025-11-22","01:00:00","2025-11-22","17:00:00","0d 16:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Cluster BR-13 (ca. 12m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2511-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","Z906301-2502",null,">","Zwijndrecht","Zwijndrecht",2025,2025,47,48,"2025-11-22","01:00:00","2025-11-24","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Conserveren/ dakdekken * More details: https://btd-planner.prorail.nl?taak=IO-Z-906301-2502-00-2&doc=FOT (Register with ProRail)",null,null,"Z-906301","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","ER50008-2501",null,">","Zwijndrecht","Zwijndrecht",2025,2025,47,48,"2025-11-22","01:00:00","2025-11-24","05:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"ERTMS parallelbouw * More details: https://btd-planner.prorail.nl?taak=IO-E-R50008-2501-00-5&doc=FOT (Register with ProRail)",null,null,"E-R50008","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008410-2504",null,">","Rotterdam Lombardijen","Rotterdam Lombardijen",2025,2025,47,47,"2025-11-23","01:00:00","2025-11-23","13:00:00","0d 12:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"vervangen ventilatoren. * More details: https://btd-planner.prorail.nl?taak=IO-K-008410-2504-00-3&doc=FOT (Register with ProRail)",null,null,"K-008410","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K006108-2510",null,">","Zevenbergschenhoek aansl.","HSL breda grens overloop",2025,2025,48,49,"2025-11-29","01:00:00","2025-12-01","06:30:00","2d 05:30","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"integrale onderhoudswerkzaamheden * More details: https://btd-planner.prorail.nl?taak=IO-K-006108-2510-00-4&doc=FOT (Register with ProRail)",null,null,"K-006108","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-25B6",null,">","Europoort","Europoort",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"VB29-scope uitvoeren in blauwdrukweekend * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-25B6-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R594400-2506",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT",null,null,null,null,null,null,null,null,"bouw viaduct over de havenspoorlijn incl. seinverplaatsing. * More details: https://btd-planner.prorail.nl?taak=IO-R-594400-2506-00-1&doc=FOT (Register with ProRail)",null,null,"R-594400","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2518",null,">","Europoort West","Europoort West",2025,2025,49,50,"2025-12-07","08:00:00","2025-12-08","12:00:00","1d 04:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Cluster ER-16 (1x 1:9 GW en ca. 20m spoor) * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2518-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","M004966-2506",null,">","Arnemuiden","Vlissingen Souburg",2025,2025,49,50,"2025-12-05","21:00:00","2025-12-08","01:00:00","2d 04:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen rijdraden Tussen Goes (Gs) en Vlissingen (Vs) * More details: https://btd-planner.prorail.nl?taak=IO-M-004966-2506-00-7&doc=FOT (Register with ProRail)",null,null,"M-004966","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007208-2518",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,49,49,"2025-12-06","23:00:00","2025-12-07","23:00:00","1d 00:00","continuous","Miscellaneous","","ST",null,null,null,null,null,null,null,null,"Vervangen EBI stellers 3331, 3333, 3335, 3337, 3339 en 3341 door NSE - 4 / NSE - S * More details: https://btd-planner.prorail.nl?taak=IO-K-007208-2518-00-1&doc=FOT (Register with ProRail)",null,null,"K-007208","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K008109-2506",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen oude wisselverwarming (CB) naar nieuwe wisselverwarming (elektra). Werkzaamheden rondom en in de wissels. * More details: https://btd-planner.prorail.nl?taak=IO-K-008109-2506-00-2&doc=FOT (Register with ProRail)",null,null,"K-008109","2024-01-04","Minor",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R569600-2501",null,">","Kijfhoek zuid","Kijfhoek zuid",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"aanpassen Sophiatunnel ivm capaciteitsvergroting * More details: https://btd-planner.prorail.nl?taak=IO-R-569600-2501-00-1&doc=FOT (Register with ProRail)",null,null,"R-569600","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","R584600-2501",null,">","Arnemuiden","Vlissingen Souburg",2025,2025,49,50,"2025-12-04","01:00:00","2025-12-08","01:00:00","3d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Verbeteren van de verlichting voor de gebruiker (NS) van het emplacement. * More details: https://btd-planner.prorail.nl?taak=IO-R-584600-2501-00-4&doc=FOT (Register with ProRail)",null,null,"R-584600","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","Z907116-2502",null,">","Arnemuiden","Vlissingen Souburg",2025,2025,49,50,"2025-12-04","01:00:00","2025-12-08","01:00:00","3d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Integraal project station Middelburg, o.a. P76, perronkaprenovatie en aanpassen stationstunnel * More details: https://btd-planner.prorail.nl?taak=IO-Z-907116-2502-00-6&doc=FOT (Register with ProRail)",null,null,"Z-907116","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","M004864-2501",null,">","Arnemuiden","Vlissingen Souburg",2025,2025,49,50,"2025-12-04","01:00:00","2025-12-08","01:00:00","3d 00:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vernieuwen waterleidingen * More details: https://btd-planner.prorail.nl?taak=IO-M-004864-2501-00-4&doc=FOT (Register with ProRail)",null,null,"M-004864","2024-01-04","Medium",null,null,null,null,"","","Publication",null,"N",null,"00"]
[null,"ProRail","K007022-2506",null,">","Waalhaven Zuid aansl Zuid","Waalhaven Zuid aansl Zuid",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervangen treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2506-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","K007022-2516",null,">","Maasvlakte Yangtzehaven Noord","Maasvlakte Yangtzehaven Noord",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Vervanging treindetectie * More details: https://btd-planner.prorail.nl?taak=IO-K-007022-2516-00-1&doc=FOT (Register with ProRail)",null,null,"K-007022","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]
[null,"ProRail","KX00010-2555",null,">","Barendrecht Vork Aansl","Waalhaven Zuid aansl Zuid",2025,2025,49,50,"2025-12-06","23:00:00","2025-12-08","07:00:00","1d 08:00","continuous","Miscellaneous","","LT+ST",null,null,null,null,null,null,null,null,"Schakelen bovenleiding * More details: https://btd-planner.prorail.nl?taak=IO-K-X00010-2555-00-1&doc=FOT (Register with ProRail)",null,null,"K-X00010","2024-01-04","Medium",null,null,null,null,"","","Coordination",null,"N",null,"00"]

{"sheet":"SBB-I TVS","index":5,"n_rows":16,"n_cols":31,"rows_kept":16,"cut":false,"hidden":false,"merged":[[0,22,0,26],[0,4,0,5],[0,6,0,7],[0,8,0,9],[0,10,0,11],[0,12,0,13],[0,17,0,21]]}
["IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,"< >","From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<>","LPFR","GEPR/GE",2026,2026,1,49,"2026-01-01",null,"2026-12-10",null,"12 months","continuous","Platform and track works ",null,"x",null,null,null,"x",null,"x","x",null,"Total closures may be possible / only one track available (postponed form 2025 to 2026)"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<>","LPFR","GEPR/GE",2026,2026,31,33,"2026-02-27",null,"2026-08-16",null,"2 weeks","continuous","track works ","x",null,null,null,null,"x",null,"x",null,null,"Total closure (postponed form 2025 to 2026)"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<>","SY","LP",2027,2027,1,13,"2027-01-01",null,"2027-04-04",null,"13 weeks","continuous","track works ",null,"x",null,null,null,"x",null,"x",null,null,"only one track available (postponed form 2026 to 2027)"]
["SBB Infra",null,"Bellegarde-La Plaine-Genève La Praille","<>","SY","VMC",2027,2027,27,33,"2027-07-05",null,"2027-08-22",null,"7 weeks","continuous","track works ",null,"x",null,null,null,"x",null,"x",null,null,"only one track available (postponed form 2026 to 2027)"]
["SBB Infra",null,"Basel SBB","< >","BSRB",null,2025,2025,null,null,"2025-01-06",null,"2025-01-11",null,"Monday-Sunday","continuous","track works ",null,null,null,null,null,null,"x",null,"x",null,"Reduced Availability, many diffrent TCR's"]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,5,null,"2026-01-31",null,"2026-02-02",null,null,"continuous","track works ","x",null,null,null,null,"x","x",null,"x",null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,9,null,"2026-02-28",null,"2026-03-01",null,null,"continuous","track works ","x",null,null,null,null,"x","x",null,"x",null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,17,null,"2026-04-25",null,"2026-04-27",null,null,"continuous","track works ","x",null,null,null,null,"x","x",null,"x",null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,23,null,"2026-06-06",null,"2026-06-08",null,null,"continuous","track works ","x",null,null,null,null,"x","x",null,"x",null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,27,null,"2026-07-04",null,"2026-07-06",null,null,"continuous","track works ","x",null,null,null,null,"x","x",null,"x",null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2026,46,null,"2026-11-14",null,"2026-11-16",null,null,"continuous","track works ","x",null,null,null,null,"x","x",null,"x",null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2029,1,51,"2026-01-03",null,"2029-12-13",null,"Monday-Sunday","continuous","track works ",null,"x",null,null,null,null,null,null,null,null,"single track closure"]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2029,1,51,"2026-01-03","23:30:00","2029-12-13","04:30:00","Saturday-Sunday","continuous","track works ","x",null,null,null,null,null,null,null,"x",null,"Total closure "]
["SBB Infra",null,"Basel SBB","< >","BSSJ","BS",2026,2029,1,51,"2026-01-03","23:30:00","2029-12-13","04:30:00","Sunday-Monday","continuous","track works ","x",null,null,null,null,null,null,null,"x",null,"Total closure "]

{"sheet":"SNCF-R","index":6,"n_rows":5389,"n_cols":45,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)","Last update","Classification","Weekdays","Interval","Affected estimated travel volume","Affected border","Deviation location","Deviation border","Status","Additional information","Automatic process","BitmapDays","Variant value"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","No catenary","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"SNCF-R","14894106361",null,"< >","Paris-La Chapelle - Poste E","Paris-La Chapelle - Jonct Km 3,4",2024,2024,28,34,"2024-07-12","23:30:00","2024-08-19","04:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14471413861",null,"< >","Grandpuits - Poste 4","Grandpuits - Poste 4",2024,2024,39,41,"2024-09-23","23:35:00","2024-10-12","04:35:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP443",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R","14463937161",null,"< >","Miramas - FSC réception","Miramas - Triage PC",2024,2024,42,48,"2024-10-15","05:05:00","2024-11-30","05:05:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"RAV Mas, F. Triage, réservation des voies 27+28+29 pour Base arrière du Ma 15/10 à 05h05 de S42 au Sa 30/11 à 05h05 de S48 :  Domaine S9 : 527+526+529  Domaine S11 : néant",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14462981961",null,"< >","Miramas - Triage PC","Miramas - Triage PC",2024,2024,40,49,"2024-10-01","05:05:00","2024-12-07","05:05:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fermeture continue de la V154 sur le F. Relais, aire de montage des APvs, du Ma 01/10 à 05h05 de S40 à Sa 07/12 à 05h05 de S49 :   Etendue S9 : du Km 806,766 au Km 807,509   Domaine S9 : ZEPG 754 (V154)   Etendue S11 : du Km 806,766 au Km 807,509, CBT S11",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14952641261",null,"< >","Marseille-Blancarde - Technicentre","Marseille-Blancarde - Technicentre",2024,2024,36,50,"2024-09-02","00:00:00","2024-12-14","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"LNPCA -Remisage TC Blancarde- Dépose d'installations et Fermeture en continue de 4 VS grill Electrique (de VS37 à 43). La capacité réservée dans l'outil TCAP ne nous permet pas cette précision apportée ci-après :  déposes d'installations sur le site du TC",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14976487661",null,"< >","Marseille-St-Charles - Marchandises","Marseille-St-Charles - Marchandises",2024,2024,36,50,"2024-09-02","00:00:00","2024-12-14","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"LNPCA : Libération Abeilles : travaux VS, prise des voies 19 à 23 uniquement, SA 2024 de septembre (S36) à décembre 2024 (S50) - démolition bâtiments le long de la voie A.",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R","14484681361",null,"< >","Meaux - Aig Km 41,7-Ã‰v","Meaux - Bât Voyageurs",2024,2024,42,50,"2024-10-14","08:00:00","2024-12-14","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"",null,null,null,null,"Major","",null,null,null,null,null,"Planned"]
[null,"SNCF-R",16590764361,null,null,0,0,2025,2025,28,35,"2025-07-07","08:00:00","2025-08-31","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16828071661,null,null,0,0,2025,2025,43,50,"2025-10-20","22:35:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP 152 modifiée, du Pk 410,500 au 411.20, laisse l'usage des aiguilles permettant d'accéder au faisceau 3 à 11.  ",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16841209661,null,null,0,0,2025,2025,34,42,"2025-08-18","22:35:00","2025-10-18","06:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP 160, qui sera prise avec ZEP 1407 ( zep 158 + 160 + 162 +164), une CCCT S9 à établir, pour allonger et rétrécissement, avec 5C_LUR_004 & 005     Sera restituée si besoin d'entrée ou de sortie de TTX sur le faisceau pair de voies de services.",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18336943661,null,null,0,"St-Rambert-d'Albon - Bif Km 572,3",2025,2025,23,29,"2025-06-02","22:30:00","2025-07-19","15:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Créé pour CHA25_0028920 RAV RVB SRA SAS INTERDICTION RACC SUD et Voie A   Equivalent ZEP 422 +424+426+438  Immobilisation Aig 4b 43 ",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16786403861,null,null,0,0,2025,2025,50,50,"2024-12-15","00:00:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fenêtre localisée entre le C266 V1 au P5 et la TJD 331-332-333-334. afin d'empêcher les départs et arrivées de la V1 coté Sud.",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16787087361,null,null,0,0,2025,2025,50,50,"2024-12-15","00:00:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fenêtre localisée Zep 202.",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",22522214161,null,null,0,0,2025,2025,27,35,"2025-06-30","08:00:00","2025-08-29","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"MàJ du 05-12-2023 par PK DT GE en accord avec GM ILO  Fermeture en continu de la ligne 42000 Sud entre Epinal Bif SL et Aillevillers (exclu). TER O/T Aillevillers possible.",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18545600461,null,null,0,"Latour-de-Carol-Enveitg",2025,2025,40,44,"2025-09-29","06:00:00","2025-10-31","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18545589761,null,null,0,"Latour-de-Carol-Enveitg",2025,2025,8,17,"2025-02-17","06:00:00","2025-04-25","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",20520528661,null,null,"Charleville-Mézières - Bât Voyageurs","Nouzonville",2025,2025,15,16,"2025-04-07","08:45:00","2025-04-20","15:15:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"zep 544+545 en gare de Charleville",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16934907061,null,null,"Mulhouse-Ville - Aig Km 110","Mulhouse-Ville - Point D",2025,2025,26,45,"2025-06-28","07:00:00","2025-11-09","04:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Neutralisation Aig 326 à gauche",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16318004561,null,null,"Rouffach - Carré 576","Rouffach - Évit Voie 2Bis",2025,2025,13,14,"2025-03-24","20:00:00","2025-04-01","05:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP908",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16317749161,null,null,"Rouffach - Évit Voie 1Bis","Rouffach - Carré 573",2025,2025,12,13,"2025-03-17","20:00:00","2025-03-25","05:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP907",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16317484561,null,null,"Bollwiller - Bât Voyageurs","Staffelfelden",2025,2025,11,12,"2025-03-10","20:00:00","2025-03-18","05:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP931",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16316812461,null,null,"Raedersheim","Bollwiller - Évitement",2025,2025,10,11,"2025-03-03","20:00:00","2025-03-11","05:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP930",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16925814761,null,null,"Paris-Nord - Bât Voyageurs","Paris-Nord - Jonction Km 0,9",2025,2025,40,50,"2025-09-29","23:30:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"GEL 1/2 quai V10",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16925580261,null,null,"Paris-Nord-Souterraine","Paris-Nord - Jonction Km 0,9",2025,2025,3,16,"2025-01-13","23:30:00","2025-04-14","04:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"GEL 1/2 quai V7  uniquement S9 le S11 ne sera pas pris en continu",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16925778861,null,null,"Paris-Nord-Souterraine","Paris-Nord - Jonction Km 0,9",2025,2025,28,40,"2025-07-07","23:30:00","2025-09-29","04:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"GEL 1/2 quai V9",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16925652561,null,null,"Paris-Nord-Surface","Paris-Nord - Jonction Km 0,9",2025,2025,16,28,"2025-04-14","23:30:00","2025-07-07","04:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"GEL 1/2 quai V8",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16314023261,null,null,"Poste 12 Vémars - Bif Sud","Poste 12 Vémars - Bif Est",2025,2025,24,50,"2025-06-09","21:20:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Domaine K  en continu du 09/06/25 au 13/12/25",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16945411261,null,null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Poste Satellite",2025,2025,41,46,"2025-10-10","22:50:00","2025-11-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16945406861,null,null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Marchandises",2025,2025,41,46,"2025-10-10","22:50:00","2025-11-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16945395961,null,null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,41,46,"2025-10-10","22:50:00","2025-11-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16945403461,null,null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,41,46,"2025-10-10","22:50:00","2025-11-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16981248261,null,null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Poste Satellite",2025,2025,45,50,"2025-11-07","22:50:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16981244861,null,null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Poste Satellite",2025,2025,45,50,"2025-11-07","22:50:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16981232561,null,null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Poste Satellite",2025,2025,45,50,"2025-11-07","22:50:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16981241461,null,null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Jo IPCS Km 59,4",2025,2025,45,50,"2025-11-07","22:50:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16981237361,null,null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Jo IPCS Km 59,4",2025,2025,45,50,"2025-11-07","22:50:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16945415761,null,null,"Mantes-Station","Mantes-la-Jolie - Bât Voyageurs",2025,2025,41,46,"2025-10-10","22:50:00","2025-11-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16945175561,null,null,"Mantes-Station","Mantes-la-Jolie - Bât Voyageurs",2025,2025,41,46,"2025-10-10","22:50:00","2025-11-12","04:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16981187661,null,null,"Mantes-Station","Mantes-la-Jolie - Bât Voyageurs",2025,2025,45,50,"2025-11-07","22:50:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16981223361,null,null,"Mantes-Station","Mantes-la-Jolie - Bât Voyageurs",2025,2025,45,50,"2025-11-07","22:50:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16991955261,null,null,"Versailles-Chantiers - Bif Porchefont","Versailles-Rive-Gauche",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16993347061,null,null,"Invalides - Carré 92","Musée-d'Orsay - Carré 103",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16993330061,null,null,"Invalides - Carré 92","Musée-d'Orsay - Carré 103",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16992635261,null,null,"Invalides - Bât Voyageurs","Champ-de-Mars-Tour-Eiffel - Carré 405",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16992638061,null,null,"Invalides - Bât Voyageurs","Javel",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16902360661,null,null,"Champ-de-Mars-Tour-Eiffel - Carré 405","Versailles-Chantiers - Bif Porchefont",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16902352361,null,null,"Champ-de-Mars-Tour-Eiffel - Carré 405","Versailles-Chantiers - Bif Porchefont",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16902352361,null,null,"Champ-de-Mars-Tour-Eiffel - Carré 405","Versailles-Chantiers - Bif Porchefont",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16902360661,null,null,"Champ-de-Mars-Tour-Eiffel - Carré 405","Versailles-Chantiers - Bif Porchefont",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16902352361,null,null,"Champ-de-Mars-Tour-Eiffel - Carré 405","Versailles-Chantiers - Bif Porchefont",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16902360661,null,null,"Champ-de-Mars-Tour-Eiffel - Carré 405","Versailles-Chantiers - Bif Porchefont",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16992176661,null,null,"Champ-de-Mars-Tour-Eiffel - Carré 67","Avenue-Foch",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16992184761,null,null,"Champ-de-Mars-Tour-Eiffel - Carré 67","Boulainvilliers",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16992176661,null,null,"Champ-de-Mars-Tour-Eiffel - Carré 67","Avenue-Foch",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16992184761,null,null,"Champ-de-Mars-Tour-Eiffel - Carré 67","Boulainvilliers",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16975864561,null,null,"Caen - IPCS Km 238,1","Caen - IPCS Km 239,4",2025,2025,18,20,"2025-04-28","22:30:00","2025-05-16","22:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16975876861,null,null,"Caen - IPCS Km 238,1","Caen - IPCS Km 239,4",2025,2025,21,22,"2025-05-19","22:30:00","2025-05-28","22:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16975901661,null,null,"Caen - IPCS Km 238,1","Caen - IPCS Km 239,4",2025,2025,23,24,"2025-06-02","22:30:00","2025-06-13","22:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",20174090661,null,null,"Aiffres - Bât Voyageurs","Saintes - Signal 102",2025,2025,2,12,"2025-01-06","09:30:00","2025-03-21","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fermeture continue pour chantier PDIFER EP de Aiffres exclu (début du domaine fermé à la pancarte LM PK 421.419)",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16788731361,null,null,"Avenue-du-Président-Kennedy-Ra","St-Ouen - Bif de St-Ouen",2025,2025,31,34,"2025-07-31","23:35:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19904890961,null,null,"Gommiers - ITE Agralys","Les Aubrais-Orléans - Bif de Chartres",2025,2025,40,42,"2025-09-29","08:00:00","2025-10-17","18:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP Patay-Les Aubrais/Orléans en continue 3 semaines week compris  -Rempl traverses : S40 à S42 Fermeture en continue du Lu 29/09/25 08h00 au Ve 17/10/25 18h00 week compris",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16993417961,null,null,"Musée-d'Orsay - Bât Voyageurs","Paris-Austerlitz (Banlieue) - Bât Voyageurs",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16993401361,null,null,"Musée-d'Orsay - Bât Voyageurs","Paris-Austerlitz (Banlieue) - Bât Voyageurs",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16993417961,null,null,"Musée-d'Orsay - Bât Voyageurs","Paris-Austerlitz (Banlieue) - Bât Voyageurs",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16993401361,null,null,"Musée-d'Orsay - Bât Voyageurs","Paris-Austerlitz (Banlieue) - Bât Voyageurs",2025,2025,29,34,"2025-07-15","02:30:00","2025-08-23","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16701805061,null,null,"St-Pierre-des-Corps - Bif Joué-Tours","Monts (Indre-et-Loire) - Bât Voyageurs",2025,2025,11,14,"2025-03-10","10:00:00","2025-04-04","10:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"CAP virtuelle : Aig 2121a/b et 2122a/b immobilisée en position directe.",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16316100161,null,null,"St-Pierre-des-Corps - Rac Sud","ST-PIERRE-DES-CORPS - TIROIR 1 DÉP",2025,2025,42,45,"2025-10-13","08:00:00","2025-11-07","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fermeture continue ZEP 232-R9 (RO V159 et V160 entre Relais Nord et Poste 2)  RVB 160 : Fermerture continue S42 à S45 du Lu 13/10 08h00 au Ve 07/11 16h00",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16771180161,null,null,"Reignac","Fléré-la-Rivière - ITE Basque",2025,2025,35,50,"2025-08-31","22:00:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",20983984861,null,null,"Joué-lès-Tours - Bât Voyageurs","La Douzillère",2025,2025,35,50,"2025-08-31","22:00:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19414526661,null,null,"Selommes - Local",0,2025,2025,16,19,"2025-04-14","08:30:00","2025-05-07","18:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"VU Blois-Villefrancoeur Fermeture continue  -RR : S16 à S19 Fermeture continue du Lu 14/04/25 08h30 au Me 07/05/25 18h00",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",20951039961,null,null,"Montmorillon - Bât Voyageurs","Bessines - ITE Cogema N°1",2025,2025,38,50,"2025-09-19","08:00:00","2025-12-13","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Montmorillon exclu à Limoges exclu - suite SA2026  ZEP 725+727+705+695+2910+2299+2447+2930+2449+2557+2940",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16777728061,null,null,"Lussac-les-Châteaux","Le Dorat",2025,2025,50,13,"2024-12-15","00:01:00","2025-03-28","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Montmorillon inclus - Le Dorat exclu  ZEP 2940+2557",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16779670361,null,null,"Lussac-les-Châteaux","Le Dorat",2025,2025,13,31,"2025-03-28","08:00:00","2025-08-01","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Le Dorat exclu  ZEP 2940+2557",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",20950920161,null,null,"Lussac-les-Châteaux","Le Dorat",2025,2025,31,36,"2025-08-01","08:00:00","2025-09-02","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Le Dorat exclu  ZEP 2559+2940+2557",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16995793161,null,null,"Vayres - ITE BSN","St-Sulpice-Izon - Bât Voyageurs",2025,2025,11,13,"2025-03-16","00:01:00","2025-03-27","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"interdiction itinéraire sur 3261 a et 3261 b  :   position en voie directe , pas de passage IPCS",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16995825361,null,null,"Vayres - ITE BSN","St-Sulpice-Izon - Bât Voyageurs",2025,2025,11,13,"2025-03-16","00:01:00","2025-03-27","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"interdiction itinéraire sur 3262 a et 3262 b  :   position en voie directe , pas de passage IPCS",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",17950094961,null,null,"Jassonneix","Aix-la-Marsalouse",2025,2025,27,44,"2025-06-30","08:00:00","2025-10-31","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16925388961,null,null,"Colomiers - Bât Voyageurs","Colomiers-Lycée-International",2025,2025,27,29,"2025-07-06","22:00:00","2025-07-20","18:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP 369 interdite en continue - indissociable de la ZEP type L Colomiers -L'Isle Jourdain - associée à DEF25_COL-LIJ_003  Voies A, B , C de Colomiers considérées en buttoir côté Auch",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16777446061,null,null,"L'Isle-Jourdain (Gers)","Auch - Bât Voyageurs",2025,2025,27,29,"2025-07-06","22:00:00","2025-07-20","18:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"DFV en continue de Colomiers à Auch - associée à DEF25_COL-LIJ_003",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16777454561,null,null,"L'Isle-Jourdain (Gers)","Auch - Bât Voyageurs",2025,2025,29,33,"2025-07-20","18:00:00","2025-08-17","18:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"DFV type L en continue - L'Isle Jourdain Auch - L'Isle Jourdain exclu      ",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",20516728861,null,null,"Monteils","Laguépie",2025,2025,13,14,"2025-03-24","08:00:00","2025-04-05","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"voie E de Najac interdite  croisement impossible  Nature exacte des travaux   RVB de la Voie d´évitement de la gare de NAJAC      RVB de la voie d´évitement du talon de l´aiguille 2 au talon de l´aiguille 1         RT de la Voie d´évitement de la gare de ",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",17603547261,null,null,"St-Sulpice (Tarn)","St-Sulpice (Tarn) - Aig 7527/7528",2025,2025,42,48,"2025-10-13","00:00:00","2025-11-28","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Nature exacte des travauxravaux de voie en gare de St Sulpice et Tessonnières       Le chantier consiste aux opérations suivantes, localisées sur deux sites différents :      Site de St Sulpice   Voie Aenouvellement de ballast et traverses (RB+RT)",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18865185861,null,null,"Montluçon-Ville - Bif Eygurande","Commentry - Faisceaux",2025,2025,43,45,"2025-10-20","09:10:00","2025-11-07","16:40:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"SO 873008 du lu 20/10  SF 873014 du Ve 07/11",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16836478961,null,null,"Lannemezan","Sarrancolin - Bât Voyageurs",2025,2025,42,45,"2025-10-13","08:00:00","2025-11-07","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"DFV en continue Lannemezan - Labarthe - desserte EP interdite  SEL 4702 du secteur Lannemezan Arreau consignée",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",20912996161,null,null,"Lannemezan","Labarthe-Avezac - EP UGINE K",2025,2025,42,45,"2025-10-13","08:00:00","2025-11-07","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"SEL 4702 du secteur Lannemezan Arreau consignée en continue - desserte interdite  ZEP38 interdite aux circulations électriques",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18951267961,null,null,"Bayonne - Triage","Bayonne - Bif Mousserolle",2025,2025,12,14,"2025-03-17","08:00:00","2025-04-04","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16234197361,null,null,"Lyon-St-Paul","Le Méridien",2025,2025,28,35,"2025-07-07","10:00:00","2025-08-29","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"PRo ESPLETTE : Travaux Tiers - Remplacement OA, y compris travaux caténaires préparatoires et définitifs, y compris mesures SES pour la remise en exploitation  L782: Gr 8722 (35+36+37+40+45+47). L775 31+32+38+43+33+39+42+46 pour accès  Voie D: Ecully-Tass",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16234174261,null,null,"Les Flachères","Tassin - Sh FRANCHEVILLE",2025,2025,28,35,"2025-07-07","10:00:00","2025-08-29","16:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"PRo ESPLETTE : Travaux Tiers - Remplacement OA, y compris travaux caténaires préparatoires et définitifs, y compris mesures SES pour la remise en exploitation  L782: Gr 8722 (35+36+37+40+45+47). L775 31+32+38+43+33+39+42+46 pour accès  Voie D: Ecully-Tass",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16542236161,null,null,"Chalon-sur-Saône - Bif Nord","Chalon-sur-Saône - Faisceau Pair",2025,2025,11,13,"2025-03-16","09:10:00","2025-03-28","06:10:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP 2526 / sans S11",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16362935561,null,null,"Chalon-sur-Saône - Bif Nord","Chalon-sur-Saône - Faisceau Pair",2025,2025,2,17,"2025-01-06","23:10:00","2025-04-26","06:10:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16688731361,null,null,"Chalon-sur-Saône - Bif Nord","Chalon-sur-Saône - Poste PAI",2025,2025,26,29,"2025-06-23","23:10:00","2025-07-19","06:10:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fermeture en continue voie E.  ",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16731977161,null,null,"Chalon-sur-Saône - Bif Nord","Chalon-sur-Saône - Poste PAI",2025,2025,29,40,"2025-07-19","06:10:00","2025-10-04","06:10:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fermeture en continue voie E, prolongement de la 5C_CSS_013 pendant la période de priorité travaux Bresse.    ",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16690069961,null,null,"Mâcon-Ville - Bât Voyageurs","Mâcon-Ville - Bif Km 440,9",2025,2025,30,33,"2025-07-21","08:30:00","2025-08-14","16:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"V4 fermée en continu de S30à S33  APROPORT fermé de S31 à S33, travaux en simultané V5Mâcon",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16610593461,null,null,"Mâcon-Ville - Faisceau pair","Mâcon-Ville - Km 441,6",2025,2025,30,33,"2025-07-21","08:00:00","2025-08-14","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"APROPORT fermé de S30 à S33  Manoeuvre : sortie et entrée FI par V5T et V1G impossible.   Sortie et entrée FI  réalisable uniquement par V1 (CV1854)",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16633056061,null,null,"Mâcon-Ville - Changement V","Mâcon-Ville - Bât Voyageurs",2025,2025,7,13,"2025-02-10","22:25:00","2025-03-29","05:25:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fermeture V1Bis Mâcon du 10/02/2025 au 29/03/2025",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16649415461,null,null,"Mâcon-Ville - Changement V","Mâcon-Ville - Bif Km 440,9",2025,2025,18,29,"2025-04-28","22:25:00","2025-07-18","05:25:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fermeture V2Bis Mâcon du 28/04/2025 au 18/07/2025",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18545540861,null,null,"Langogne","La Bastide-St-Laurent-les-Bain",2025,2025,14,22,"2025-04-05","08:00:00","2025-06-01","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18545499861,null,null,"Luc (Lozère)","Génolhac",2025,2025,14,22,"2025-04-05","08:00:00","2025-06-01","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",17012523461,null,null,"Oyonnax","Brion-Montréal-la-Cluse - Bif 116,7/35,3",2025,2025,10,17,"2025-03-03","08:00:00","2025-04-25","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Interception en continu VU Brion-Oyonnax  Domaine S9 : ZEP 899",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16177471561,null,null,"Chamonix-Mont-Blanc","Vallorcine - Frontière Fr-Su",2025,2025,42,46,"2025-10-13","07:20:00","2025-11-14","15:15:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Inteception en continu VU métrique entre Chamonix et Vallorcine ",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16177471561,null,null,"Chamonix-Mont-Blanc","Vallorcine - Frontière Fr-Su",2025,2025,42,46,"2025-10-13","07:20:00","2025-11-14","15:15:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Inteception en continu VU métrique entre Chamonix et Vallorcine ",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16177475561,null,null,"Jarrie-Vizille - Bât Voyageurs","Vif - Bât Voyageurs",2025,2025,22,27,"2025-05-26","08:30:00","2025-07-04","16:10:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Interception en continu entre Jarrie et VIF",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16177475561,null,null,"Jarrie-Vizille - Bât Voyageurs","Vif - Bât Voyageurs",2025,2025,22,27,"2025-05-26","08:30:00","2025-07-04","16:10:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Interception en continu entre Jarrie et VIF",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16947141561,null,null,"Marseille-St-Charles - SAS","Marseille-St-Charles - Marchandises",2025,2025,11,17,"2025-03-15","04:45:00","2025-04-24","04:45:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"SA 2025 RAV MSC, Aire de montage des ADv de com. croisées -Fermeture en continue du SAS du Sa 15/03 à 04h45 (S11) au JE 24/04 à 04h45 (S17)-  :  Etendue S9 : du C300/302 Km 861,359 au C309/311 Km 861,414  Domaine S9/Etendue : 5411(VU) (du C+5412(VV)  Doma",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",15799985161,null,null,"Drap-Cantaron","Breil-sur-Roya - Bif",2025,2025,50,48,"2024-12-15","00:00:00","2025-11-25","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"SA2025 (continuité de 2024), CPER Nice-Breil, Fermeture S9A3 qui s'étend de fin de S35 de 2024 à S48 de SA2025 : pour le SA2025, la fermeture S9A3 représentée commence le DI 15/12/24 à 00h00 et s'arrête en S48 (Le Ma 25/11/25 à 12h00 de S48). La continuit",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18424436861,null,null,"St-Rambert-d'Albon - Voie 12 Garage","St-Rambert-d'Albon - Bât Voyageurs",2025,2025,17,48,"2025-04-21","23:00:00","2025-11-30","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Capacité pour matérialiser l'immobilisation / neutralisation des aiguilles 31,32,33,34,37a,37b et 39 et TJD 38ac de la S7/2025 jusqu´à la mise en service prévue en mars 2026",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18337576361,null,null,"St-Rambert-d'Albon - Voie 12 Garage","St-Rambert-d'Albon - Bât Voyageurs",2025,2025,23,29,"2025-06-02","22:30:00","2025-07-19","05:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Créé pour CHA25_0028920 RAV RVB SRA SAS interdiction V12G et V14G S23 à S29   Equivalent Zep 428+430+432 Immobilisation Aig 24 et TJD 68 Voie 14 Non Géolocalisée ",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23850694661,null,null,"St-Rambert-d'Albon - Voie 12 Garage","St-Rambert-d'Albon - Bât Voyageurs",2025,2025,17,21,"2025-04-21","23:00:00","2025-05-24","05:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Capacité pour matérialiser l'immobilisation / neutralisation des aiguilles 31,32.",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16712450561,null,null,"St-Rambert-d'Albon - Voie 12 Garage","St-Rambert-d'Albon - Bif Km 572,3",2025,2025,17,21,"2025-04-21","07:00:00","2025-05-24","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Créé pour RAV  RVB SRA SAS CHA25_0028920  INTERDICTION VOIE 1BIS SRA",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18545480061,null,null,"Génolhac","Malbosc",2025,2025,14,22,"2025-04-05","08:00:00","2025-06-01","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18545288561,null,null,"Grand'Combe-La Pise - Bât Voyageurs","Alès - Carré 104",2025,2025,14,22,"2025-04-05","08:00:00","2025-06-01","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19945172161,null,null,"Alès - Bât Voyageurs","Nîmes - Bif côté Alès",2025,2025,43,44,"2025-10-20","08:00:00","2025-11-02","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18861785961,null,null,"Béziers - Aig Km 433,030","Bédarieux",2025,2025,23,27,"2025-06-02","08:00:00","2025-07-04","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19945862361,null,null,"Ceilhes-Roqueredonde","Tournemire-Roquefort",2025,2025,40,44,"2025-09-29","08:00:00","2025-10-31","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18861806261,null,null,"Ceilhes-Roqueredonde","Tournemire-Roquefort",2025,2025,23,27,"2025-06-02","08:00:00","2025-07-04","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18861800161,null,null,"Bédarieux","Ceilhes-Roqueredonde",2025,2025,23,27,"2025-06-02","08:00:00","2025-07-04","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19945696061,null,null,"Bédarieux","Ceilhes-Roqueredonde",2025,2025,40,44,"2025-09-29","08:00:00","2025-10-31","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT Bédarieux Exclus",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19945918361,null,null,"Millau","Sévérac-le-Château - Bât Voyageurs",2025,2025,40,44,"2025-09-29","08:00:00","2025-10-31","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18861835561,null,null,"Millau","Sévérac-le-Château - Bât Voyageurs",2025,2025,23,27,"2025-06-02","08:00:00","2025-07-04","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19945933761,null,null,"Sévérac-le-Château - Bât Voyageurs","Le Monastier",2025,2025,40,44,"2025-09-29","08:00:00","2025-10-31","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT  Localisation bornée au C178 du Monastier KM 614+948 pour sortie circulations depuis ou vers L723000",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18861881261,null,null,"Sévérac-le-Château - Bât Voyageurs","Le Monastier",2025,2025,23,27,"2025-06-02","08:00:00","2025-07-04","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT  Localisation bornée au C178 du Monastier KM 614+948 pour sortie circulations depuis ou vers L723000",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18861812261,null,null,"Tournemire-Roquefort","Millau",2025,2025,23,27,"2025-06-02","08:00:00","2025-07-04","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19945913461,null,null,"Tournemire-Roquefort","Millau",2025,2025,40,44,"2025-09-29","08:00:00","2025-10-31","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Travaux LDFT",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18545557061,null,null,"Mende - Bât Voyageurs",0,2025,2025,14,22,"2025-04-05","08:00:00","2025-06-01","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",18545615361,null,null,"Perpignan - Ac Dépôt/Base T",0,2025,2025,40,44,"2025-09-29","06:00:00","2025-10-31","12:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Modif RP0 du 29/06/2023",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16590762361,null,null,"Grandpuits - Poste 4",0,2025,2025,28,35,"2025-07-07","08:00:00","2025-08-31","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16994889261,null,null,9182,9182,2025,2025,18,20,"2025-04-28","22:30:00","2025-05-16","22:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0468   Modification suite à MC22-0314",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16995031861,null,null,9182,9182,2025,2025,25,26,"2025-06-16","22:30:00","2025-06-27","22:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN Main courante n°25 : pour passage 3325",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16813398261,null,null,"Poste 12 Marcoussis","Poste 13 St-Arnoult",2025,2025,2,5,"2025-01-07","05:00:00","2025-01-28","05:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Interdictions d´itinéraires sur les liaisons 1201/1202 et 1203/1204 du 07 Janvier (S2) au 28 Janvier 2025 (S5) durant les travaux de RB Voie 2",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16813450661,null,null,"Poste 12 Marcoussis","Poste 13 St-Arnoult",2025,2025,6,11,"2025-02-04","05:00:00","2025-03-15","05:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Interdictions d´itinéraires sur les liaisons 1301/1302 et 1303/1304 du 04 Février (S6) au 15 Mars 2025 (S11) durant les travaux de RB Voie 2",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19959900961,null,null,"Tours - Poste O","St-Pierre-des-Corps - Bif de Grammont",2025,2025,10,31,"2025-03-03","08:00:00","2025-08-03","20:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"PO : Voies 41/43/29/31/33/35 (ZEP 075, 077, 081, 083, 087, 089) ZEP non géolocalisables dans TCAP - (création d'une CAP virtuelle sur ZEP 028 avec aig 778 immobilisée à gauche et aig 766 immobilisée à droite (gare de Tours accessible)  CPER Tours : Fermet",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19959974961,null,null,"Tours - Poste O","St-Pierre-des-Corps - Bif de Grammont",2025,2025,13,16,"2025-03-24","08:00:00","2025-04-20","20:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"PO : Accès Voie des travaux (ZEP 067) non géolocalisable dans TCAP - (création d'une CAP virtuelle sur ZEP 028 avec mise en place de SAM en bout des Voies 37 et 39 afin d'interdire l'accès à la Voie des travaux (gare de Tours accessible, seul l'accès à la",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",20577072361,null,null,"St-Étienne-Châteaucreux - Poste 1","St-Étienne-Châteaucreux - 13 Circulation",2025,2025,9,16,"2025-02-24","23:00:00","2025-04-18","05:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Créé pour SD TER St Etienne - Création alimentation futur TER  Extension du bâtiment Poste de Sectionnement - En continu de  09 à S16 - Voie 60 non géolocalisée  ZEP 121 Voie A ZEP 153 Voie 60  SEL 4062 Voie A SEL 358 Voie 60",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19419820461,null,null,"St-Martin-d'Étampes - Tiroir","Pithiviers - Local",2025,2025,13,15,"2025-03-24","08:00:00","2025-04-11","17:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fermeture continue ZEP Pithivier-Engenville week compris   -Rempl traverses + Renouv PN : S13 à S15 Fermeture continue du Lu 24/03/23 08h00 au Ve 11/04/23 17h00 week compris",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",19959564661,null,null,"ST-PIERRE-DES-CORPS - SAS R","Tours - Poste O",2025,2025,10,20,"2025-03-03","08:00:00","2025-05-18","20:00:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"PO : Voie 8 (ZEP 090 non géolocalisable dans TCAP - (création d'une CAP virtuelle sur ZEP 004 avec aig 650 immobilisée à gauche (gare de Tours accessible sauf la V8))  CPER Tours : Fermeture continue de S10 à S30 Voie 8",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16923218161,null,null,"Orléans - Garage des Rames","Orléans - Bât Voyageurs",2025,2025,2,15,"2025-01-06","00:00:00","2025-04-11","23:59:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"ZEP 204+217+205+216+206  Et interdiction d'itinéraire aig 572/574 et 594/595 en Sem 12 du lundi 17/03 au vendredi 21/03/25  Sem 2 à 15 en continue : PMR",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",15799984361,null,null,"Nice-St-Roch - Grill","Breil-sur-Roya - Bif",2025,2025,48,50,"2025-11-25","12:00:00","2025-12-12","15:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"SA2025, CPER Nice-Breil, Fermeture S9A1 longue durée de S48 à S50, du 25-11-2025 à 12h00 au 12-12-2025 à 15h30, soit 18 jrs, à S-2 la date de fin sera confirmée (21 jrs maxi =>pourrait allé au LU 15/12/2025 à 12h00, S51 du SA2026) :    Etendue S9 (Nice St",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",15806463161,null,null,"Nice-Ville - Tiroir 4","Nice-Ville - FSC Impair",2025,2025,14,15,"2025-03-31","05:30:00","2025-04-11","05:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"Fermeture en continue de la V4T+V4 depuis la butte jusqu'au C123 Km 223,663 sur S14+15  :   Domaine S9 : 102+30+28  Domaine S11 : Sél 104   Nota : la VA <=> VB Marseille par Aig 126/127 et sans restriction côté Vint.. La voie 4/4T non circulable sur S14+1",null,null,null,null,"High",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",16618057561,null,null,"Paris-La Chapelle - Voie VSE/153","Le Bourget-Triage - Poste 1",2025,2025,51,34,"2024-12-16","00:00:00","2025-08-18","04:30:00",null,"continuous",null,null,null,null,null,null,null,null,null,null,null,"fermeture voie DA",null,null,null,null,"Major",null,null,null,null,null,null,"Planned"]
[null,"SNCF-R",15805668561,"Paris - Strasbourg",null,"Noisy-le-Sec - Bif Impaire O",0,2025,2025,50,47,"2024-12-15","23:50:00","2025-11-24","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL y compris ZEP 789            ",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18423955561,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Faisceau V",2025,2025,50,42,"2024-12-15",1.0347222222222201,"2025-10-20","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL     ",null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18423990461,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2025,2025,50,42,"2024-12-15",1.0763888888888899,"2025-10-20","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16993048561,"Paris - Strasbourg",null,"Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2025,2025,50,42,"2024-12-15",1.11805555555556,"2025-10-20","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sf ZEP 789 + OMBRE           ",null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16972571661,"Paris - Hirson",null,0,0,2025,2025,50,50,"2024-12-15",1.1597222222222201,"2025-12-13","23:59:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Dans l'ombre de CHA25_0028695. KA.",null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813805261,"Calais - Dunkerque",null,"Dunkerque-Grande-Synthe - Bif Puyt-Houck","Calais-Fréthun - Accès Offerkerque",2025,2025,50,50,"2024-12-15",1.2013888888888899,"2025-12-13","10:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Interface forte avec le CG59 et VNF , ne pas modifier sans en aviser les parties.  Ordonnancer aussi les jours fériés.  ",null,"Y",null,45454,"Major",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17026297461,"Paris - Hirson",null,"Laon - Poste 2",0,2025,2025,50,50,"2024-12-15",1.24305555555556,"2025-12-13","23:59:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16656458061,"St Just en Chaussée - Douai",null,0,"Sin-le-Noble",2025,2025,50,18,"2024-12-15",1.2847222222222201,"2025-04-30","17:00:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812985761,"Don-Sainghin - Lens",null,"Lens - Bif l'Épinette","Don-Sainghin - Bât Voyageurs",2025,2025,50,48,"2024-12-15",1.3263888888888899,"2025-12-01","02:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812977961,"Longueau - Boulogne",null,"Conchil-le-Temple","Boulogne-Ville - Poste 5",2025,2025,50,48,"2024-12-15",1.36805555555556,"2025-12-01","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812984961,"Don-Sainghin - Lens",null,"Lens - Bif l'Épinette","Don-Sainghin - Bât Voyageurs",2025,2025,50,48,"2024-12-15",1.4097222222222201,"2025-12-01","02:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812959161,"Racc de Santes - Don-Sainghin",null,"Lille-St-Sauveur - Carre Violet 40","Haubourdin - Bif de Tortue",2025,2025,50,48,"2024-12-15",1.4513888888888899,"2025-12-01","02:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812959961,"Racc de Santes - Don-Sainghin",null,"Lille-St-Sauveur - Carre Violet 40","Haubourdin - Bif de Tortue",2025,2025,50,48,"2024-12-15",1.49305555555556,"2025-12-01","01:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812970361,"Longueau - Boulogne",null,"Abbeville","Rang-du-Fliers-Verton",2025,2025,50,48,"2024-12-15",1.5347222222222201,"2025-12-01","02:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812976961,"Longueau - Boulogne",null,"Conchil-le-Temple","Boulogne-Ville - Poste 5",2025,2025,50,48,"2024-12-15",1.5763888888888899,"2025-12-01","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812999361,"Calais - Lille",null,"Hazebrouck - Bif Haute Loge","Calais-Fréthun - Carré 321",2025,2025,50,49,"2024-12-15",1.61805555555556,"2025-12-08","23:57:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812996961,"Calais - Lille",null,"Hazebrouck - Bif Haute Loge","Calais-Fréthun - Carré 321",2025,2025,50,49,"2024-12-15",1.6597222222222201,"2025-12-08","01:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787679661,"Paris - Strasbourg",null,"Blesme-Haussignemont - Bât Voyageurs","Bar-le-Duc - Ent V1B/Sor V2B",2025,2025,50,49,"2024-12-15",1.7013888888888899,"2025-12-08","02:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787618961,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Vitry-le-François - Aig Ouest-VB",2025,2025,50,49,"2024-12-15",1.74305555555556,"2025-12-08","03:32:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787640661,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Mohon - Carré 302",2025,2025,50,49,"2024-12-15",1.7847222222222201,"2025-12-08","02:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  Modification le 12/11:2021 : Modification horaire suite à reunion evolution systeme capacitaire du 07/10/2021",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787652061,"Paris - Strasbourg",null,"Bar-le-Duc - Bât Voyageurs","Lérouville - Aig Km 290,4",2025,2025,50,49,"2024-12-15",1.8263888888888899,"2025-12-08","01:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787679661,"Paris - Strasbourg",null,"Blesme-Haussignemont - Bât Voyageurs","Bar-le-Duc - Ent V1B/Sor V2B",2025,2025,50,49,"2024-12-15",1.86805555555556,"2025-12-08","02:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787638261,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Mohon - Bif L2/Rac",2025,2025,50,49,"2024-12-15",1.9097222222222201,"2025-12-08","02:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  Modification le 12/11/2021: Suite à réunion evolution systeme capacitaire du 07/10/2021",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787616561,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Vitry-le-François - Aig Ouest-VB",2025,2025,50,49,"2024-12-15",1.9513888888888899,"2025-12-08","02:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799197561,"Longuyon - Onville",null,"Longuyon - Bif","Conflans-Jarny - Bif L5 VU/L12",2025,2025,50,48,"2024-12-15",1.99305555555556,"2025-12-01","02:53:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 176 : vibration de -100 minutes des horaires (passage du régime en Di/Lu au lieu de Lu)",null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799338961,"Toul - Culmont Chalindrey",null,"Merrey (Haute-Marne)","Neufchâteau - Bât Voyageurs",2025,2025,50,49,"2024-12-15",2.0347222222222201,"2025-12-08","02:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modif des horaires suite à la demande de MC 102",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799314961,"Toul - Culmont Chalindrey",null,"Neufchâteau - Bât Voyageurs","Toul - Poste 1",2025,2025,50,49,"2024-12-15",2.0763888888888902,"2025-12-08","01:34:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799163361,"Metz - Reding",null,"Rémilly - Bât Voyageurs","Metz-Sablon - Jonct V2/V2R",2025,2025,50,39,"2024-12-15",2.1180555555555598,"2025-09-29","02:26:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification des horaires par main courante (19/10/2021)",null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799196761,"Longuyon - Onville",null,"Longuyon - Bif","Conflans-Jarny - Bif L5 VU/L12",2025,2025,50,48,"2024-12-15",2.1597222222222201,"2025-12-01","02:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799359961,"Longuyon - Onville",null,"Conflans-Jarny - Bif L12/L5 D V","Onville - Bât Voyageurs",2025,2025,50,48,"2024-12-15",2.2013888888888902,"2025-12-01","02:23:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799306361,"Metz - Lérouville",null,"Lérouville - Bât Voyageurs","Novéant - Bif Km 338,9",2025,2025,50,49,"2024-12-15",2.2430555555555598,"2025-12-08","01:02:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modif des horaires suite à la MC 101",null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799332361,"Metz Ville - Zoufftgen",null,"Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2025,2025,50,49,"2024-12-15",2.2847222222222201,"2025-12-08","02:56:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799307961,"Metz - Lérouville",null,"Lérouville - Bât Voyageurs","Novéant - Bif Km 338,9",2025,2025,50,49,"2024-12-15",2.3263888888888902,"2025-12-08","02:32:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 154 : décalage des horaires de -27 minutes",null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799284761,"Remilly - Forbach",null,"Rémilly - Bât Voyageurs","Béning - Bât Voyageurs",2025,2025,50,49,"2024-12-15",2.3680555555555598,"2025-12-08","01:31:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16252188261,"Conflan-Jarny - Hagondange",null,"Gandrange-Amnéville","Hagondange - Bât Voyageurs",2025,2025,50,50,"2024-12-15",2.4097222222222201,"2024-12-15","08:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3 / simultanément HGD-UCK + HGD-CJ / 2 OT . Rac Mondelange interdit",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177661161,"Metz - Reding",null,"Courcelles-sur-Nied","Metz-Sablon - Jonct V2/V2R",2025,2025,50,50,"2024-12-15",2.4513888888888902,"2024-12-15","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3. Déf V1+V2 entre Metz et Rémilly. Détournement frets via ligne Thionville-Béning à ouvrir le SaDi de 21h à 05h00",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799186561,"Remilly - Forbach",null,"Béning - Acc E Faisceau","Forbach - Bât Voyageurs",2025,2025,50,49,"2024-12-15",2.4930555555555598,"2025-12-08","01:26:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799329761,"Metz Ville - Zoufftgen",null,"Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2025,2025,50,49,"2024-12-15",2.5347222222222201,"2025-12-08","02:56:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177978361,"Thionville - Mohon",null,"Charency-Vezin","Longuyon - Bât Voyageurs",2025,2025,50,50,"2024-12-15",2.5763888888888902,"2024-12-15","10:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3 / simultanément LGN-THL + SED-LGN + LGN-CJ / 4 OT",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177975161,"Longuyon - Mont St Martin (XB)",null,"Longuyon - Bât Voyageurs","Montigny-sur-Chiers",2025,2025,50,50,"2024-12-15",2.6180555555555598,"2024-12-15","06:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3 / simultanément LGN-MSM + THL-ZOU / 3 OT",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799325561,"Thionville - Mohon",null,"Longuyon - Bif","Pierrepont",2025,2025,50,50,"2024-12-15",2.6597222222222201,"2024-12-15","10:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3 / simultanément LGN-THL + SED-LGN + LGN-CJ / 4 OT",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177798361,"Longuyon - Onville",null,"Longuyon - Bif","Spincourt",2025,2025,50,50,"2024-12-15",2.7013888888888902,"2024-12-15","10:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3 / simultanément LGN-THL + SED-LGN + LGN-CJ / 4 OT     ",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16251460161,"Metz Ville - Zoufftgen",null,"Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2025,2025,50,50,"2024-12-15",2.7430555555555598,"2024-12-15","06:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3 / simultanément LGN-MSM + THL-ZOU / 3 OT",null,"Y",null,45454,"Medium",7,null,null,"Zoufftgen (IE) - Frontière Fr-Lu",null,null,"Planned",0]
[null,"SNCF-R",16177730361,"Metz Ville - Zoufftgen",null,"Hagondange - ITE Richemont","Hagondange - Aig ITE",2025,2025,50,50,"2024-12-15",2.7847222222222201,"2024-12-15","08:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3 / simultanément HGD-UCK + HGD-CJ / 2 OT . Rac Mondelange interdit",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177684561,"Metz - Lérouville",null,"Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2025,2025,50,50,"2024-12-15",2.8263888888888902,"2024-12-15","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3. Déf V1+V1B entre Novéant et MetzSablon - zep 2915,2921",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16251620861,"Longuyon - Mont St Martin (XB)",null,"Longuyon - Bât Voyageurs","Longwy - Poste 1",2025,2025,50,50,"2024-12-15",2.8680555555555598,"2024-12-15","06:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3 / simultanément LGN-MSM + THL-ZOU / 3 OT",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786374161,"Thionville - Mohon",null,"Sedan - Garages","Montmédy - Évitement",2025,2025,50,49,"2024-12-15",2.9097222222222201,"2025-12-08","02:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786412161,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - ITE BLAIRON","Tournes",2025,2025,50,49,"2024-12-15",2.9513888888888902,"2025-12-08","02:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786418161,"Liart - Tournes",null,"Rouvroy-l'Échelle","Tournes",2025,2025,50,49,"2024-12-15",2.9930555555555598,"2025-12-08","02:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786389761,"Thionville - Mohon",null,"Lumes","Lumes-Triage - Accès Km 144,5",2025,2025,50,49,"2024-12-15",3.0347222222222201,"2025-12-08","02:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786369161,"Lille - Hirson",null,"Lesquin - Bif de Lesquin","Beuvrages",2025,2025,50,46,"2024-12-15",3.0763888888888902,"2025-11-17","02:32:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786391361,"Thionville - Mohon",null,"Mohon - Bif L2","Lumes-Triage - Accès Km 144,5",2025,2025,50,49,"2024-12-15",3.1180555555555598,"2025-12-08","02:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786413761,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Hirson","Tournes",2025,2025,50,49,"2024-12-15",3.1597222222222201,"2025-12-08","02:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16251743761,"Thionville - Mohon",null,"Charency-Vezin","Longuyon - Bât Voyageurs",2025,2025,50,50,"2024-12-15",3.2013888888888902,"2024-12-15","10:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Mise en exploitation commerciale Z1 + Z2+ Z3 / simultanément LGN-THL + SED-LGN + LGN-CJ / 4 OT",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786422761,"Lille - Hirson",null,"Leval","Hirson - Ent Marchandise",2025,2025,50,49,"2024-12-15",3.2430555555555598,"2025-12-08","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786393761,"Thionville - Mohon",null,"Nouvion-sur-Meuse","Sedan - Accès Garage",2025,2025,50,49,"2024-12-15",3.2847222222222201,"2025-12-08","02:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  Modification le 12/11/2021 : Modification des horaires suite à Concertation Evolution du système capacitaire du 07/10/2021",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786417361,"Liart - Tournes",null,"Rouvroy-l'Échelle","Tournes",2025,2025,50,49,"2024-12-15",3.3263888888888902,"2025-12-08","02:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786388161,"Thionville - Mohon",null,"Lumes-Triage - FSC D","Sedan - Accès Garage",2025,2025,50,49,"2024-12-15",3.3680555555555598,"2025-12-08","02:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786378161,"Thionville - Mohon",null,"Sedan - Garages","Montmédy - Évitement",2025,2025,50,49,"2024-12-15",3.4097222222222201,"2025-12-08","02:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786435761,"Lille - Hirson",null,"Valenciennes - Bât Voyageurs","Berlaimont - Bât Voyageurs",2025,2025,50,49,"2024-12-15",3.4513888888888902,"2025-12-08","02:28:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805288561,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,50,47,"2024-12-15",3.4930555555555598,"2025-11-24","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL  24/01/2023 : Mise en qualité suite rejet SIPH / Suppression de la localisation voie 2BIS-R à PE, non décrite dans l'infra SIPH. ",null,"Y",null,45454,"Major",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805745561,"Paris - Strasbourg",null,"Chelles-Gournay - Aig côté Gagny","Vaires-Torcy - Aig Côté Chelle",2025,2025,51,50,"2024-12-16",3.5347222222222201,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV sur ZEP type G 1531 VAI P5. Sel 7151 SSr Chelles-Vaires voie 1R     ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805679161,"Paris - Strasbourg",null,"Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2025,2025,51,50,"2024-12-16",3.5763888888888902,"2025-12-12","10:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Train ouvrant: 117267 Trin fermant: 117117",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805590961,"Paris - Strasbourg",null,"Trilport - Bif de Germigny","Mézy - Poste U",2025,2025,51,50,"2024-12-16",3.6180555555555598,"2025-12-12","14:04:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"28/11/2022 (DAC) : Création de SURV suite au découpage de l'ancienne SEC_Trilport-ChateauThierry en deux sections au SA2025.  Train ouvrant : 117144. Train fermant : 117148.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805760161,"Paris - Strasbourg",null,"Gagny - Aig V2Bis/V2Ter","Vaires-Torcy - Faisceau V",2025,2025,51,50,"2024-12-16",3.6597222222222201,"2025-12-13","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL bif Gagny prise",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805746361,"Paris - Strasbourg",null,"Chelles-Gournay - Aig côté Gagny","Vaires-Torcy - Aig Côté Chelle",2025,2025,51,50,"2024-12-16",3.7013888888888902,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV sur ZEP type G 1538 VAI P5. Sel 7482 SSr Chelles-Vaires voie 2R           ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16247765761,"Paris - Strasbourg",null,"La Ferté-sous-Jouarre - ITE CA La-Brie","Mézy - Poste U",2025,2025,51,50,"2024-12-16",3.7430555555555598,"2025-12-12","10:56:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"28/11/2022 (DAC) : Création de SURV suite au découpage de l'ancienne SEC_Trilport-ChateauThierry en deux sections au SA2025. Train ouvrant : 117113. Train fermant : 117117.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805655961,"Paris - Strasbourg",null,"Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2025,2025,51,50,"2024-12-16",3.7847222222222201,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805737561,"Paris - Strasbourg",null,"Gagny - Bât Voyageurs","Vaires-Torcy - Aig Km 21,0",2025,2025,51,50,"2024-12-16",3.8263888888888902,"2025-12-08","04:21:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805657361,"Paris - Strasbourg",null,"Noisy-le-Sec - Bif Impaire O",0,2025,2025,51,50,"2024-12-16",3.8680555555555598,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sf ZEP 789                     ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805758161,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Aig Km 21,0",2025,2025,51,50,"2024-12-16",3.9097222222222201,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805666761,"Paris - Strasbourg",null,"Noisy-le-Sec - Bif Impaire O",0,2025,2025,51,49,"2024-12-16",3.9513888888888902,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL y compris ZEP 789          ",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805759161,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2025,2025,51,50,"2024-12-16",3.9930555555555598,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL bif Gagny degagé",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16247833161,"Paris - Strasbourg",null,"Changis-St-Jean - ITE Appel","Mézy - Poste U",2025,2025,51,50,"2024-12-16",4.0347222222222197,"2025-12-12","14:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"28/11/2022 (DAC) : Création de SURV suite au découpage de l'ancienne SEC_Trilport-ChateauThierry en deux sections au SA2025. Train ouvrant : 117144. Train fermant : 117148.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805655961,"Paris - Strasbourg",null,"Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2025,2025,51,50,"2024-12-16",4.0763888888888902,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP TOUT CHL               ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805758161,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Aig Km 21,0",2025,2025,51,50,"2024-12-16",4.1180555555555598,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805565961,"Paris - Strasbourg",null,"Vaires-Torcy - Aig Km 21,0","Lagny-Thorigny - Tiroir 3",2025,2025,51,50,"2024-12-16",4.1597222222222197,"2025-12-08","03:51:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805760161,"Paris - Strasbourg",null,"Gagny - Aig V2Bis/V2Ter","Vaires-Torcy - Faisceau V",2025,2025,51,50,"2024-12-16",4.2013888888888902,"2025-12-13","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL bif Gagny prise",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805680761,"Paris - Strasbourg",null,"Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2025,2025,51,50,"2024-12-16",4.2430555555555598,"2025-12-12","14:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Train ouvrant: 117144 Train fermant: 117278",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805657361,"Paris - Strasbourg",null,"Noisy-le-Sec - Bif Impaire O",0,2025,2025,51,50,"2024-12-16",4.2847222222222197,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sf ZEP 789                     ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805565161,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2025,2025,51,50,"2024-12-16",4.3263888888888902,"2025-12-08","04:14:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805738361,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Faisceau V",2025,2025,51,50,"2024-12-16",4.3680555555555598,"2025-12-08","03:51:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805736761,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Aig Km 21,0",2025,2025,51,50,"2024-12-16",4.4097222222222197,"2025-12-08","03:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805567561,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2025,2025,51,50,"2024-12-16",4.4513888888888902,"2025-12-08","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805589361,"Paris - Strasbourg",null,"Trilport - Bif de Germigny","Mézy - Poste U",2025,2025,51,50,"2024-12-16",4.4930555555555598,"2025-12-12","10:32:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"28/11/2022 (DAC) : Création de SURV suite au découpage de l'ancienne SEC_Trilport-ChateauThierry en deux sections au SA2025. Train ouvrant : 117113. Train fermant : 117117.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805577161,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2025,2025,51,50,"2024-12-16",4.5347222222222197,"2025-12-13","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805566761,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2025,2025,51,50,"2024-12-16",4.5763888888888902,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805735961,"Paris - Strasbourg",null,"Gagny - Bât Voyageurs","Vaires-Torcy - Aig Km 21,0",2025,2025,51,50,"2024-12-16",4.6180555555555598,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805577161,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2025,2025,51,50,"2024-12-16",4.6597222222222197,"2025-05-31","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813845061,"Paris - Hirson",null,"Crépy-en-Valois","Vierzy - Aig Km 94,1",2025,2025,51,50,"2024-12-16",4.7013888888888902,"2025-12-12","11:38:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813710861,"Paris - Hirson",null,"Vierzy - Aig Km 96,0","Vauxaillon - Km 115,970",2025,2025,51,50,"2024-12-16",4.7430555555555598,"2025-12-12","11:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813713061,"Paris - Hirson",null,"Vierzy - Aig Km 96,0","Vauxaillon - Km 115,970",2025,2025,51,50,"2024-12-16",4.7847222222222197,"2025-12-12","11:56:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813754061,"Mohon - Charleville-Mézière",null,"Braine - PN 15","Fismes",2025,2025,51,50,"2024-12-16",4.8263888888888902,"2025-12-12","12:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813765261,"Paris - Hirson",null,"Vierzy - Aig Km 94,1","Vierzy - Aig Km 96,0",2025,2025,51,50,"2024-12-16",4.8680555555555598,"2025-12-13","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813840261,"Paris - Hirson",null,"Ormoy-Villers","Vaumoise",2025,2025,51,50,"2024-12-16",4.9097222222222197,"2025-12-12","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Réduction des ITC de jour pour faire les tournées de surveillance du réseau : cela n´est possible qu´avec un décalage de cette surveillance en partie sur les ITC industrielles.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813807061,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",4.9513888888888902,"2025-12-12","11:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813808661,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",4.9930555555555598,"2025-12-13","05:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813766061,"Paris - Hirson",null,"Vierzy - Aig Km 94,1","Vierzy - Aig Km 96,0",2025,2025,51,50,"2024-12-16",5.0347222222222197,"2025-12-12","11:38:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813766861,"Paris - Hirson",null,"Vierzy - Aig Km 94,1","Vierzy - Aig Km 96,0",2025,2025,51,50,"2024-12-16",5.0763888888888902,"2025-12-13","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813807861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",5.1180555555555598,"2025-12-13","05:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16706382661,"Paris - Hirson",null,"Ormoy-Villers","Vaumoise",2025,2025,51,50,"2024-12-16",5.1597222222222197,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813838661,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",5.2013888888888902,"2025-12-13","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"caténaire voie 2 en gare de Crepy à rendre à 04h15 pour rendre l´alimentation des VS et permettre la préparation des rames voyageur. Du LUMA 11/12-01-16 au VESA 01/02-04-16 sauf les 26/27-02-16, 04/05-03-16.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813844261,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",5.2430555555555598,"2025-12-12","11:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813712061,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",5.2847222222222197,"2025-12-13","05:18:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813845861,"Paris - Hirson",null,"Crépy-en-Valois","Vierzy - Aig Km 94,1",2025,2025,51,50,"2024-12-16",5.3263888888888902,"2025-12-13","05:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16975165861,"Racc de Santes - Don-Sainghin",null,"Béthune - E/S Béthune","Béthune - Bât Voyageurs",2025,2025,51,50,"2024-12-16",5.3680555555555598,"2025-12-13","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813809461,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",5.4097222222222197,"2025-12-12","11:53:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813764461,"Paris - Hirson",null,"Vierzy - Aig Km 94,1","Vierzy - Aig Km 96,0",2025,2025,51,50,"2024-12-16",5.4513888888888902,"2025-12-12","11:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813843461,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",5.4930555555555598,"2025-12-13","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"caténaire voie 2 en gare de Crepy à rendre à 04h15 pour rendre l´alimentation des VS et permettre la préparation des rames voyageur. Du LUMA 11/12-01-16 au VESA 01/02-04-16 sauf les 26/27-02-16, 04/05-03-16. ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813710861,"Paris - Hirson",null,"Vierzy - Aig Km 96,0","Vauxaillon - Km 115,970",2025,2025,51,50,"2024-12-16",5.5347222222222197,"2025-12-12","11:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813844261,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",5.5763888888888902,"2025-12-12","11:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813762661,"Racc de Santes - Don-Sainghin",null,"Don-Sainghin - Bât Voyageurs","Béthune - E/S Béthune",2025,2025,51,50,"2024-12-16",5.6180555555555598,"2025-12-12","10:54:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813841861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",5.6597222222222197,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES  modif ( RP0)  23h45 pour permettre l'arrivée à Crépy du 121541",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813782661,"St Just en Chaussée - Douai",null,"Cantin","Douai - Bif de Sin",2025,2025,51,50,"2024-12-16",5.7013888888888902,"2025-12-12","15:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"11/06/2024 : Modification PK de fin de la fenêtre de surveillance 5F_SLN-002 en V1 : 221+321  au lieu de 221 + 466    Bif sin-ouest non engagée",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813761661,"Racc de Santes - Don-Sainghin",null,"Don-Sainghin - Bât Voyageurs","Béthune - E/S Béthune",2025,2025,51,50,"2024-12-16",5.7430555555555598,"2025-12-13","05:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813759261,"Racc de Santes - Don-Sainghin",null,"Fouquereuil - Bif Fouquereuil","St-Pol-sur-Ternoise - Bât Voyageurs",2025,2025,51,50,"2024-12-16",5.7847222222222197,"2025-12-12","16:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Suite main courante MC22-0336 ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813845061,"Paris - Hirson",null,"Crépy-en-Valois","Vierzy - Aig Km 94,1",2025,2025,51,50,"2024-12-16",5.8263888888888902,"2025-12-12","11:38:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813809461,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",5.8680555555555598,"2025-12-12","11:53:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813764461,"Paris - Hirson",null,"Vierzy - Aig Km 94,1","Vierzy - Aig Km 96,0",2025,2025,51,50,"2024-12-16",5.9097222222222197,"2025-12-12","11:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813713061,"Paris - Hirson",null,"Vierzy - Aig Km 96,0","Vauxaillon - Km 115,970",2025,2025,51,50,"2024-12-16",5.9513888888888902,"2025-12-12","11:56:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813766061,"Paris - Hirson",null,"Vierzy - Aig Km 94,1","Vierzy - Aig Km 96,0",2025,2025,51,50,"2024-12-16",5.9930555555555598,"2025-12-12","11:38:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813736461,"Lille - Baisieux",null,"Lezennes","Baisieux - Frontière Fr-Be",2025,2025,51,50,"2024-12-16",6.0347222222222197,"2025-12-12","11:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"12/04/2023 : report SA 2023 - vibration de la plage",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Baisieux - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",15813789461,"St Just en Chaussée - Douai",null,0,"Sin-le-Noble",2025,2025,51,50,"2024-12-16",6.0763888888888902,"2025-12-12","15:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813806061,"Calais - Dunkerque",null,"Dunkerque-Grande-Synthe - Bif Puyt-Houck","Calais-Fréthun - Accès Offerkerque",2025,2025,51,50,"2024-12-16",6.1180555555555598,"2025-12-12","10:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Interface forte avec le CG59 et VNF , ne pas modifier sans en aviser les parties.  Pour les jours fériés, il faut activer la FEN23_Puythouck-Fontinettes_004  ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813740261,"Paris - Hirson",null,"Vauxaillon - Km 117,291","La Neuville-sous-Laon",2025,2025,51,50,"2024-12-16",6.1597222222222197,"2025-12-12","11:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813763461,"Racc de Santes - Don-Sainghin",null,"Don-Sainghin - Bât Voyageurs","Béthune - E/S Béthune",2025,2025,51,50,"2024-12-16",6.2013888888888902,"2025-12-12","14:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813742661,"Paris - Hirson",null,"Vauxaillon - Km 117,291","Laon - Bif St-Marcel",2025,2025,51,50,"2024-12-16",6.2430555555555598,"2025-12-12","12:12:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813754861,"Mohon - Charleville-Mézière",null,"Braine - PN 15","Fismes",2025,2025,51,50,"2024-12-16",6.2847222222222197,"2025-12-12","11:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813781861,"St Just en Chaussée - Douai",null,"Cantin","Douai - Bif de Sin",2025,2025,51,50,"2024-12-16",6.3263888888888902,"2025-12-12","15:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"02/08/2022 - Modification PK Fin : 221+333 au lieu de 221+466",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813737261,"Lille - Baisieux",null,"Lezennes - Ateliers","Baisieux - Frontière Fr-Be",2025,2025,51,50,"2024-12-16",6.3680555555555598,"2025-12-12","14:49:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Baisieux - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",15813807061,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",6.4097222222222197,"2025-12-12","11:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812902761,"Creil - Jeumont",null,"Tergnier - Triage","St-Quentin - RA",2025,2025,51,50,"2024-12-16",6.4513888888888902,"2025-12-12","14:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire et pk faite le 28/09/2020 par LL suite main-courante MC22-0334.  Modification horaire faite le 27/01/2021 par LL, suite main-courante MC22-0452.  modification horaire des pk fin le 29/11/2021 par LL.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813043961,"Paris - Lille",null,"Creil - Bif Bonvilliers","St-Just-en-Chaussée - Voie 4",2025,2025,51,50,"2024-12-16",6.4930555555555598,"2025-12-12","13:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813041561,"Paris - Lille",null,"St-Just-en-Chaussée - Bât Voyageurs","Longueau - Poste 1",2025,2025,51,50,"2024-12-16",6.5347222222222197,"2025-12-12","13:51:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 20/10/2023 par LL, suite MC25-117.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813071561,"Calais - Boulogne",null,"non trouvé",0,2025,2025,51,49,"2024-12-16",6.5763888888888902,"2025-12-07","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813086761,"Paris - Lille",null,"Lamotte-Brebière","Achiet",2025,2025,51,50,"2024-12-16",6.6180555555555598,"2025-12-12","15:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0279 (Accord TP NEN mail du 24/08/2018) modification horaire faite le 5/10/20 par LL, suite main-courante MC22-0339   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813040761,"Paris - Lille",null,"St-Just-en-Chaussée - Bât Voyageurs","Longueau - Poste 1",2025,2025,51,50,"2024-12-16",6.6597222222222197,"2025-12-12","11:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813012761,"Creil - Jeumont",null,"Maubeuge - Poste 2","Jeumont - Bât Voyageurs",2025,2025,51,50,"2024-12-16",6.7013888888888902,"2025-12-12","14:24:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812957561,"Racc de Santes - Don-Sainghin",null,"Lille-St-Sauveur - Carre Violet 40","Haubourdin - Bif de Tortue",2025,2025,51,50,"2024-12-16",6.7430555555555598,"2025-12-12","11:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 05/11/2020 par LL, suite main-courante MC22-0388. ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16541574161,"Longueau - Boulogne",null,"Abbeville","Conchil-le-Temple - SBAPR9101",2025,2025,51,9,"2024-12-16",6.7847222222222197,"2025-03-01","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813039961,"Paris - Lille",null,"Creil - Bif Bonvilliers","St-Just-en-Chaussée - Bât Voyageurs",2025,2025,51,50,"2024-12-16",6.8263888888888902,"2025-12-12","11:51:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813018561,"Racc de Santes - Don-Sainghin",null,"Haubourdin - Bif Haubourdin","Don-Sainghin - Bât Voyageurs",2025,2025,51,49,"2024-12-16",6.8680555555555598,"2025-12-07","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812971961,"Longueau - Boulogne",null,"Abbeville","Rang-du-Fliers-Verton",2025,2025,51,50,"2024-12-16",6.9097222222222197,"2025-12-12","11:36:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0392 (Accord TP NEN mail du 05/12/2018)   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812978961,"Longueau - Boulogne",null,"Conchil-le-Temple","Étaples-Le Touquet - Accès Nord",2025,2025,51,50,"2024-12-16",6.9513888888888902,"2025-12-12","15:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0393 (Accord TP NEN mail du 05/12/2018) modification horaire faite le 05/11/2020 par LL, suite main-courante MC22-0362.   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813024361,"Somain - Busigny",null,0,"Somain - Aig Km 230,5",2025,2025,51,50,"2024-12-16",6.9930555555555598,"2025-12-12","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 11/09/2020 par LL, suite demande par main-courante MC22-0312. modification horaire faite le 05/11/2020 par LL, suite main-courante MC22-0378.   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812894761,"Creil - Jeumont",null,"Compiègne - Garage Pair","Tergnier - Bât Voyageurs",2025,2025,51,50,"2024-12-16",7.0347222222222197,"2025-12-12","11:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812982361,"Longueau - Boulogne",null,"Conchil-le-Temple","Étaples-Le Touquet - Bât Voyageurs",2025,2025,51,50,"2024-12-16",7.0763888888888902,"2025-12-12","11:16:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 05/11/2020 par LL, suite main-courante MC22-0359.  modification horaire faite le 09/08/2022 par LL, suite main-courante MC24-15.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16542990661,"Creil - Jeumont",null,"St-Quentin - RA","St-Quentin - ITE ZI",2025,2025,51,14,"2024-12-16",7.1180555555555598,"2025-04-05","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813016961,"Racc de Santes - Don-Sainghin",null,"Haubourdin - Bif Haubourdin","Don-Sainghin - Bât Voyageurs",2025,2025,51,50,"2024-12-16",7.1597222222222197,"2025-12-12","10:43:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813057361,"Calais - Boulogne",null,"Wimille-Wimereux","Calais-Fréthun - Carré 103",2025,2025,51,50,"2024-12-16",7.2013888888888902,"2025-12-12","15:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 28/09/21 par LL, suite main-courante MC-23-74.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16869055161,"Calais - Boulogne",null,"non trouvé",0,2025,2025,51,8,"2024-12-16",7.2430555555555598,"2025-02-22","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812942561,"Paris - Lille",null,"Arras - Bif Blangy-Est","Douai - Bif de St-Éloi",2025,2025,51,50,"2024-12-16",7.2847222222222197,"2025-12-12","15:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-334 (Accord TP NEN mail du 19/11/2018) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812986561,"Don-Sainghin - Lens",null,"Lens - Bif l'Épinette","Don-Sainghin - Bât Voyageurs",2025,2025,51,50,"2024-12-16",7.3263888888888902,"2025-12-12","15:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813025961,"Somain - Busigny",null,"Maurois","Cambrai Ville - Bif Sud",2025,2025,51,50,"2024-12-16",7.3680555555555598,"2025-12-12","15:54:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification des horaires suite à la demande MC23-92 faite le 28/09/21 par LL.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812901961,"Creil - Jeumont",null,"Tergnier - Triage","St-Quentin - Poste 1",2025,2025,51,50,"2024-12-16",7.4097222222222197,"2025-12-12","11:42:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite par LL le 20/01/2021, suite main-courante MC22-0423.  modification du pk fin faite par LL le 22/01/2021, suite main-courante MC22-0449.  Modification horaire faite le 11/08/23 par LL, suite MC25-042.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812956761,"Racc de Santes - Don-Sainghin",null,"Lille-St-Sauveur - Carre Violet 40","Haubourdin - Bif de Tortue",2025,2025,51,50,"2024-12-16",7.4513888888888902,"2025-12-12","15:21:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 8/11 par LL, suite main-courante MC25-150.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812953561,"Paris - Lille",null,"Longueau - Bif de Camon","Achiet",2025,2025,51,50,"2024-12-16",7.4930555555555598,"2025-12-12","10:22:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 16/10/20 par LL, suite main-courante MC22-0348 ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812936361,"Longueau - Boulogne",null,"St-Roch (Somme) - Bât Voyageurs","Abbeville - SBAPR303",2025,2025,51,50,"2024-12-16",7.5347222222222197,"2025-12-12","10:42:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 04/10/2023 par LL, suite main-courante MC25-90.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813000961,"Calais - Lille",null,"St-Omer (Pas-de-Calais) - Bât Voyageurs","Audruicq",2025,2025,51,50,"2024-12-16",7.5763888888888902,"2025-12-12","10:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0287 (Accord TP NEN mail du 29/08/2018) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812971161,"Longueau - Boulogne",null,"Abbeville","Rang-du-Fliers-Verton",2025,2025,51,49,"2024-12-16",7.6180555555555598,"2025-12-07","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812912361,"Creil - Jeumont",null,"St-Quentin - Bât Voyageurs","Busigny - Marchandises",2025,2025,51,50,"2024-12-16",7.6597222222222197,"2025-12-12","11:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 11/08/23 par LL, suite MC2025-043",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812915361,"Paris - Lille",null,"Boisleux","Arras - Poste 1",2025,2025,51,50,"2024-12-16",7.7013888888888902,"2025-12-12","15:34:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0277 (Accord TP NEN mail du 24/08/2018) modification horaire faite le 05/10/20 par LL, suite main-courante MC22-0337   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812941761,"Paris - Lille",null,"Arras - Bif Blangy-Est","Douai - Bif de St-Éloi",2025,2025,51,50,"2024-12-16",7.7430555555555598,"2025-12-12","10:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC19-0242 (Accord TP NEN Mail du 24/08/2018) modification horaire faite le 16/10/20 par LL suite main-courante MC22-0351   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812980761,"Longueau - Boulogne",null,"Étaples-Le Touquet - Bât Voyageurs","Hesdigneul",2025,2025,51,50,"2024-12-16",7.7847222222222197,"2025-12-12","11:02:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 05/11/2020 par LL, suite main-courante MC22-0360. ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812981561,"Longueau - Boulogne",null,"Hesdigneul","Boulogne-Ville - Poste 5",2025,2025,51,50,"2024-12-16",7.8263888888888902,"2025-12-12","10:58:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 05/11/2020 par LL, suite main-courante MC22-0361. ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813017761,"Racc de Santes - Don-Sainghin",null,"Haubourdin - Bif Haubourdin","Don-Sainghin - Bât Voyageurs",2025,2025,51,50,"2024-12-16",7.8680555555555598,"2025-12-12","15:09:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812997761,"Calais - Lille",null,"Audruicq","Calais-Fréthun - Carré 321",2025,2025,51,50,"2024-12-16",7.9097222222222197,"2025-12-12","09:46:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0286 (Accord mail du TP NEN du 29/08/2018) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813029361,"Somain - Busigny",null,"Maurois","Cambrai Ville - Bif Sud",2025,2025,51,50,"2024-12-16",7.9513888888888902,"2025-12-12","11:51:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 05/10/22 par LL, suite main-courante MC24-59.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813069161,"Calais - Boulogne",null,"non trouvé",0,2025,2025,51,50,"2024-12-16",7.9930555555555598,"2025-12-12","11:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0390 (Accord TP NEN mail du 05/12/2018)   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812951961,"Paris - Lille",null,"Achiet","Arras - Bif Sud",2025,2025,51,50,"2024-12-16",8.0347222222222197,"2025-12-12","10:26:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 16/10 par LL suite main-courante MC22-0349 ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813021961,"Somain - Busigny",null,"Lourches - Gros-Caillou","Somain - Aig Km 230,5",2025,2025,51,50,"2024-12-16",8.0763888888888893,"2025-12-12","15:29:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 28/09/21 par LL, suite main-courante MC23-90.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813055761,"Calais - Boulogne",null,"Wimille-Wimereux","Calais-Fréthun - Carré 103",2025,2025,51,49,"2024-12-16",8.1180555555555607,"2025-12-07","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812968161,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Aulnoye-Aymeries - Bif Sassegnies",2025,2025,51,50,"2024-12-16",8.1597222222222197,"2025-12-12","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 11/08/23 par LL, suite MC25-044.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813040761,"Paris - Lille",null,"St-Just-en-Chaussée - Bât Voyageurs","Longueau - Poste 1",2025,2025,51,50,"2024-12-16",8.2013888888888893,"2025-12-12","11:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813085961,"Paris - Lille",null,"Achiet","Arras - Bif Sud",2025,2025,51,50,"2024-12-16",8.2430555555555607,"2025-12-12","15:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0278 (Accord TP NEN mail du 24/08/2018) modification horaire faite le 5/10 par LL suite main-courante MC22-0338   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812972761,"Longueau - Boulogne",null,"Abbeville","Rang-du-Fliers-Verton",2025,2025,51,50,"2024-12-16",8.2847222222222197,"2025-12-12","10:14:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812968161,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Aulnoye-Aymeries - Bif Sassegnies",2025,2025,51,50,"2024-12-16",8.3263888888888893,"2025-12-12","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 11/08/23 par LL, suite MC25-044.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812979961,"Longueau - Boulogne",null,"Étaples-Le Touquet - Bât Voyageurs","Boulogne-Ville - Poste 5",2025,2025,51,50,"2024-12-16",8.3680555555555607,"2025-12-12","15:26:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812972761,"Longueau - Boulogne",null,"Abbeville","Rang-du-Fliers-Verton",2025,2025,51,50,"2024-12-16",8.4097222222222197,"2025-12-12","10:14:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813016161,"Racc de Santes - Don-Sainghin",null,"Haubourdin - Bif Haubourdin","Don-Sainghin - Bât Voyageurs",2025,2025,51,49,"2024-12-16",8.4513888888888893,"2025-12-07","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812996161,"Calais - Lille",null,"Audruicq","Calais-Fréthun - Carré 321",2025,2025,51,50,"2024-12-16",8.4930555555555607,"2025-12-12","12:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 01/03/2022 par LL, suite logique de la DECC23_00160.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813000161,"Calais - Lille",null,"St-Omer (Pas-de-Calais) - Bât Voyageurs","Audruicq",2025,2025,51,50,"2024-12-16",8.5347222222222197,"2025-12-12","12:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 01/03/2022 par LL, suite logique de la DECC23_00160.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813013561,"Creil - Jeumont",null,"Maubeuge - Poste 2","Jeumont - Bât Voyageurs",2025,2025,51,50,"2024-12-16",8.5763888888888893,"2025-12-12","13:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification faite le 04/09/2020 par LL, suite demande par main-courante MC22-310.  modification faite le 05/09/2022 par LL, suite demande par main-courante MC24-13.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813067561,"Calais - Boulogne",null,"non trouvé",0,2025,2025,51,49,"2024-12-16",8.6180555555555607,"2025-12-07","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813023561,"Somain - Busigny",null,0,"Lourches - Bât Voyageurs",2025,2025,51,50,"2024-12-16",8.6597222222222197,"2025-12-12","15:34:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 28/09/21 par LL, suite main-courante MC23-91.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813008961,"Creil - Jeumont",null,"Hautmont - Bif d'Hautmont","Louvroil",2025,2025,51,50,"2024-12-16",8.7013888888888893,"2025-12-12","12:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification faite le 04/09/2020 par LL suite demande par main-courante MC22-0309 ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812911561,"Creil - Jeumont",null,"St-Quentin - Bât Voyageurs","Busigny - Bât Voyageurs",2025,2025,51,50,"2024-12-16",8.7430555555555607,"2025-12-12","13:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire pour alignement de plages, fait le 3/12/2021 par LL.  Modification horaire faite le 24/11/22 par LL, suite main-courante MC24-103.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813056561,"Calais - Boulogne",null,"Wimille-Wimereux","Calais-Fréthun - C102/204",2025,2025,51,49,"2024-12-16",8.7847222222222197,"2025-12-07","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813001761,"Calais - Lille",null,"Hazebrouck - Bif Haute Loge","St-Omer (Pas-de-Calais) - Bât Voyageurs",2025,2025,51,50,"2024-12-16",8.8263888888888893,"2025-12-12","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 01/03/2022 par LL, suite DECC23_00160.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812889961,"Creil - Jeumont",null,"Compiègne - ITE Maille","Tergnier - Bât Voyageurs",2025,2025,51,50,"2024-12-16",8.8680555555555607,"2025-12-12","14:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"correction pour couverture de la gare de Noyon pour surv v1/v2 suite mail du 17/11/22, fait par LL.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813086761,"Paris - Lille",null,"Lamotte-Brebière","Achiet",2025,2025,51,50,"2024-12-16",8.9097222222222197,"2025-12-12","15:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0279 (Accord TP NEN mail du 24/08/2018) modification horaire faite le 5/10/20 par LL, suite main-courante MC22-0339   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813054961,"Calais - Boulogne",null,"Wimille-Wimereux","Calais-Fréthun - C102/204",2025,2025,51,50,"2024-12-16",8.9513888888888893,"2025-12-12","11:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0389 (Accord TP NEN mail du 05/12/2018)     ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813007161,"Creil - Jeumont",null,"Hautmont - Bif d'Hautmont","Louvroil",2025,2025,51,50,"2024-12-16",8.9930555555555607,"2025-12-12","14:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC19-0245 (Accord TP NEN mail du 17/08/2018) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812987361,"Don-Sainghin - Lens",null,"Lens - Bif l'Épinette","Don-Sainghin - Bât Voyageurs",2025,2025,51,50,"2024-12-16",9.0347222222222197,"2025-12-12","10:43:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812967361,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Aulnoye-Aymeries - Bif Sassegnies",2025,2025,51,50,"2024-12-16",9.0763888888888893,"2025-12-12","14:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 11/08/23 par LL, suite MC25-041.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812923561,"Lille - Mouscron",null,"La Madeleine (Nord) - ITE ZI Pilateri","Tourcoing - Frontière Fr-Be",2025,2025,51,50,"2024-12-16",9.1180555555555607,"2025-12-12","10:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Tourcoing - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",15812971961,"Longueau - Boulogne",null,"Abbeville","Rang-du-Fliers-Verton",2025,2025,51,50,"2024-12-16",9.1597222222222197,"2025-12-12","11:36:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0392 (Accord TP NEN mail du 05/12/2018)   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813029361,"Somain - Busigny",null,"Maurois","Cambrai Ville - Bif Sud",2025,2025,51,50,"2024-12-16",9.2013888888888893,"2025-12-12","11:51:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 05/10/22 par LL, suite main-courante MC24-59.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812953561,"Paris - Lille",null,"Longueau - Bif de Camon","Achiet",2025,2025,51,50,"2024-12-16",9.2430555555555607,"2025-12-12","10:22:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 16/10/20 par LL, suite main-courante MC22-0348 ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813041561,"Paris - Lille",null,"St-Just-en-Chaussée - Bât Voyageurs","Longueau - Poste 1",2025,2025,51,50,"2024-12-16",9.2847222222222197,"2025-12-12","13:51:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 20/10/2023 par LL, suite MC25-117.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812925161,"Lille - Mouscron",null,"La Madeleine (Nord) - ITE ZI Pilateri","Tourcoing - Frontière Fr-Be",2025,2025,51,50,"2024-12-16",9.3263888888888893,"2025-12-12","15:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Tourcoing - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",15812937561,"Longueau - Boulogne",null,"St-Roch (Somme) - Bât Voyageurs","Abbeville - SBAPR303",2025,2025,51,50,"2024-12-16",9.3680555555555607,"2025-12-12","11:11:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0391 (Accord TP NEN mail du 05/12/2018)   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813074961,"Paris - Lille",null,"Triangle d'Ostricourt - Bif de Évin","Lille-St-Sauveur - Bif Sourd-Muet",2025,2025,51,50,"2024-12-16",9.4097222222222197,"2025-12-12","14:58:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC19-0265 (Accord TP NEN mail du 24/08/2018).  Modification horaire faite le 9/11/23 par LL, suite main-courante MC25-155.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16541535261,"Longueau - Boulogne",null,"Pont-Remy","Abbeville - SBAPR303",2025,2025,51,9,"2024-12-16",9.4513888888888893,"2025-03-01","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812966561,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Aulnoye-Aymeries - Bif Sassegnies",2025,2025,51,50,"2024-12-16",9.4930555555555607,"2025-12-08","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812967361,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Aulnoye-Aymeries - Bif Sassegnies",2025,2025,51,50,"2024-12-16",9.5347222222222197,"2025-12-12","14:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 11/08/23 par LL, suite MC25-041.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813076561,"Paris - Lille",null,"Triangle d'Ostricourt - Bif de Évin","Lille-St-Sauveur - Bif Sourd-Muet",2025,2025,51,50,"2024-12-16",9.5763888888888893,"2025-12-12","11:09:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 07/09/2021 par LL, suite main-courante MC23-001.  modification horaire faite le 16/11/22 par LL, suite main-courante MC24-90. bif harponlieu engagée, vu infrapole.  modification horaire faite le 24/07/23 par LL, suite main-co",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813025961,"Somain - Busigny",null,"Maurois","Cambrai Ville - Bif Sud",2025,2025,51,50,"2024-12-16",9.6180555555555607,"2025-12-12","15:54:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification des horaires suite à la demande MC23-92 faite le 28/09/21 par LL.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812998561,"Calais - Lille",null,"Hazebrouck - Bif Haute Loge","St-Omer (Pas-de-Calais) - Bât Voyageurs",2025,2025,51,50,"2024-12-16",9.6597222222222197,"2025-12-12","10:17:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0288 (Accord TP NEN mail du 29/08/2018) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813068361,"Calais - Boulogne",null,"non trouvé",0,2025,2025,51,50,"2024-12-16",9.7013888888888893,"2025-12-12","15:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0394 (Accord TP NEN mail du 05/12/2018) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812968961,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Aulnoye-Aymeries - Bif Sassegnies",2025,2025,51,50,"2024-12-16",9.7430555555555607,"2025-12-08","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813048161,"Paris - Lille",null,"Boisleux","Arras - Poste 1",2025,2025,51,50,"2024-12-16",9.7847222222222197,"2025-12-12","10:26:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 16/10/20 par LL suite main-courante MC22-350 ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813011761,"Creil - Jeumont",null,"Maubeuge - Poste 2","Jeumont - Bât Voyageurs",2025,2025,51,50,"2024-12-16",9.8263888888888893,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813007961,"Creil - Jeumont",null,"Hautmont - Bif d'Hautmont","Louvroil",2025,2025,51,50,"2024-12-16",9.8680555555555607,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787681261,"Paris - Strasbourg",null,"Blesme-Haussignemont - Aiguille L1/L10","Bar-le-Duc - Ent V1B/Sor V2B",2025,2025,51,50,"2024-12-16",9.9097222222222197,"2025-12-12","14:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787639061,"Mohon - Charleville-Mézière",null,"Rethel - Bât Voyageurs","Mohon - Bif L2/Rac",2025,2025,51,50,"2024-12-16",9.9513888888888893,"2025-12-12","12:18:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"30/08/2023 (DAC) : Vibration suite main courante n° 67/2023.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787649661,"Paris - Strasbourg",null,"Bar-le-Duc - Bât Voyageurs","Lérouville - Aig Km 290,4",2025,2025,51,50,"2024-12-16",9.9930555555555607,"2025-12-12","13:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787647261,"Paris - Strasbourg",null,"Ernécourt-Loxéville - Aig Km 276,9","Lérouville - Bât Voyageurs",2025,2025,51,50,"2024-12-16",10.0347222222222,"2025-12-12","12:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787651261,"Paris - Strasbourg",null,"Bar-le-Duc - Bât Voyageurs","Lérouville - Bât Voyageurs",2025,2025,51,50,"2024-12-16",10.0763888888889,"2025-12-12","14:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  SA2025 - Main courante 52 : décalage de +5 minutes des horaires de début",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787639861,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Amagne-Lucquy - Bât Voyageurs",2025,2025,51,50,"2024-12-16",10.1180555555556,"2025-12-12","15:59:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"30/08/2023 (DAC) : Vibration suite main courante n° 63/2025.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787681261,"Paris - Strasbourg",null,"Blesme-Haussignemont - Aiguille L1/L10","Bar-le-Duc - Ent V1B/Sor V2B",2025,2025,51,50,"2024-12-16",10.1597222222222,"2025-12-12","14:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787650461,"Paris - Strasbourg",null,"Bar-le-Duc - Bât Voyageurs","Lérouville - Bât Voyageurs",2025,2025,51,50,"2024-12-16",10.2013888888889,"2025-12-08","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787641461,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Amagne-Lucquy - Bât Voyageurs",2025,2025,51,50,"2024-12-16",10.2430555555556,"2025-12-12","11:54:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"30/08/2023 (DAC) : Vibration suite main courante n° 66/2025.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787618161,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Vitry-le-François - Aig Ouest-VB",2025,2025,51,50,"2024-12-16",10.2847222222222,"2025-12-12","13:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\" Modification horaire le 12/06/2020 pour levée de désaccord",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787682061,"Paris - Strasbourg",null,"Blesme-Haussignemont - Aiguille L1/L10","Bar-le-Duc - Ent V1B/Sor V2B",2025,2025,51,50,"2024-12-16",10.3263888888889,"2025-12-12","13:23:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\" ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787626561,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Dormans - Bât Voyageurs",2025,2025,51,50,"2024-12-16",10.3680555555556,"2025-12-12","11:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787631961,"Paris - Strasbourg",null,"Épernay - Rac Côté Oiry","Châlons-en-Champagne - Accès Triage",2025,2025,51,50,"2024-12-16",10.4097222222222,"2025-12-12","11:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787623161,"Paris - Strasbourg",null,"Dormans - Bât Voyageurs","Épernay - Aiguille 139,3",2025,2025,51,50,"2024-12-16",10.4513888888889,"2025-12-12","11:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787629561,"Paris - Strasbourg",null,"Épernay - Rac Côté Oiry","Châlons-en-Champagne - Accès Triage",2025,2025,51,50,"2024-12-16",10.4930555555556,"2025-12-12","13:24:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787622361,"Paris - Strasbourg",null,"Dormans - A2-Évit Soilly","Épernay - Aiguille 139,3",2025,2025,51,50,"2024-12-16",10.5347222222222,"2025-12-12","13:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787625761,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Épernay - Aiguille 139,3",2025,2025,51,50,"2024-12-16",10.5763888888889,"2025-12-08","03:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787624761,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Dormans - Bât Voyageurs",2025,2025,51,50,"2024-12-16",10.6180555555556,"2025-12-12","13:53:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787642261,"Mohon - Charleville-Mézière",null,"Rethel - Bât Voyageurs","Mohon - Carré 302",2025,2025,51,50,"2024-12-16",10.6597222222222,"2025-12-12","10:38:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  Modification le 12/11/2021 : Modification des horaires suite à Reunion Evolution Systeme capacitaire du 07/10/2021  28/09/2022 (DAC) : suite contrôle qualité PQCP, les horaires étaien",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787632761,"Paris - Strasbourg",null,"Épernay - Rac Côté Oiry","Châlons-en-Champagne - Accès Triage",2025,2025,51,50,"2024-12-16",10.7013888888889,"2025-12-08","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787680461,"Paris - Strasbourg",null,"Blesme-Haussignemont - Aiguille L1/L10","Bar-le-Duc - Ent V1B/Sor V2B",2025,2025,51,50,"2024-12-16",10.7430555555556,"2025-12-08","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787682061,"Paris - Strasbourg",null,"Blesme-Haussignemont - Aiguille L1/L10","Bar-le-Duc - Ent V1B/Sor V2B",2025,2025,51,50,"2024-12-16",10.7847222222222,"2025-12-12","13:23:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\" ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787617361,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Vitry-le-François - Aig Ouest-VB",2025,2025,51,50,"2024-12-16",10.8263888888889,"2025-12-12","12:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modif des horaires suite à la demande de MC 87 Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787680461,"Paris - Strasbourg",null,"Blesme-Haussignemont - Aiguille L1/L10","Bar-le-Duc - Ent V1B/Sor V2B",2025,2025,51,50,"2024-12-16",10.8680555555556,"2025-12-08","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787631161,"Paris - Strasbourg",null,"Épernay - Rac Côté Oiry","Châlons-en-Champagne - Accès Triage",2025,2025,51,50,"2024-12-16",10.9097222222222,"2025-12-08","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787628161,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Épernay - Aiguille 139,3",2025,2025,51,50,"2024-12-16",10.9513888888889,"2025-12-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799198361,"Longuyon - Onville",null,"Longuyon - Bif","Conflans-Jarny - Bif L5 VU/L12",2025,2025,51,50,"2024-12-16",10.9930555555556,"2025-12-12","12:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799223361,"Metz Ville - Zoufftgen",null,"Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2025,2025,51,50,"2024-12-16",11.0347222222222,"2025-12-12","14:41:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16260058961,"Metz Ville - Zoufftgen",null,"Uckange - Poste 2","Ébange - Jonction Nord",2025,2025,51,45,"2024-12-16",11.0763888888889,"2025-11-09","15:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799373361,"Metz Ville - Zoufftgen",null,"Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2025,2025,51,35,"2024-12-16",11.1180555555556,"2025-08-29","10:11:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16259987461,"Metz Ville - Zoufftgen",null,"Uckange - Poste 1","Ébange - Aig VL90",2025,2025,51,45,"2024-12-16",11.1597222222222,"2025-11-09","12:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16255077861,"Metz Ville - Zoufftgen",null,"Hagondange - Faisceau","Hagondange - ITE Richemont",2025,2025,51,45,"2024-12-16",11.2013888888889,"2025-11-07","12:29:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799318361,"Thionville - Mohon",null,"Longuyon - Bif","Thionville - Bif L3/L7",2025,2025,51,50,"2024-12-16",11.2430555555556,"2025-12-12","13:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799287161,"Remilly - Forbach",null,"Herny - Bât Voyageurs","Béning - Bât Voyageurs",2025,2025,51,50,"2024-12-16",11.2847222222222,"2025-12-12","14:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 136 : Décalage des Heure Début PK Fin et Heure Fin PK Fin de +1 minute",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799370961,"Metz Ville - Zoufftgen",null,"Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2025,2025,51,50,"2024-12-16",11.3263888888889,"2025-12-12","14:49:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799337361,"Toul - Culmont Chalindrey",null,"Culmont-Chalindrey - Bif Chaudenay","Merrey (Haute-Marne)",2025,2025,51,50,"2024-12-16",11.3680555555556,"2025-12-12","11:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799285561,"Remilly - Forbach",null,"Herny - Bât Voyageurs","Béning - Bât Voyageurs",2025,2025,51,50,"2024-12-16",11.4097222222222,"2025-12-12","12:16:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 148 : décalage des Heure Fin PK Début et Heure Fin PK Fin de -4 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16255074061,"Metz Ville - Zoufftgen",null,"Hagondange - Faisceau","Hagondange - ITE Richemont",2025,2025,51,45,"2024-12-16",11.4513888888889,"2025-11-07","15:09:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799381361,"Metz - Reding",null,"Sarraltroff - Bif","Rémilly - Bif L3/L11",2025,2025,51,50,"2024-12-16",11.4930555555556,"2025-12-12","15:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 171 : Décalage des Heure Début PK Début et Heure Fin PK Début de +3 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799382161,"Metz - Reding",null,"Sarraltroff - Bif","Rémilly - Bif L3/L11",2025,2025,51,50,"2024-12-16",11.5347222222222,"2025-12-12","12:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799466161,"Metz - Lérouville",null,"Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2025,2025,51,50,"2024-12-16",11.5763888888889,"2025-12-12","11:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799308761,"Metz - Lérouville",null,"Lérouville - Rac Côté Metz","Onville - Accès Ouest",2025,2025,51,50,"2024-12-16",11.6180555555556,"2025-12-12","11:16:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799339761,"Toul - Culmont Chalindrey",null,"Merrey (Haute-Marne)","Neufchâteau - Bât Voyageurs",2025,2025,51,50,"2024-12-16",11.6597222222222,"2025-12-12","15:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799254761,"Metz Ville - Zoufftgen",null,"Woippy - Accès Nord","Hagondange - Faisceau",2025,2025,51,45,"2024-12-16",11.7013888888889,"2025-11-07","12:28:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799341361,"Toul - Culmont Chalindrey",null,"Merrey (Haute-Marne)","Neufchâteau - Bât Voyageurs",2025,2025,51,50,"2024-12-16",11.7430555555556,"2025-12-12","11:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16255062161,"Metz Ville - Zoufftgen",null,"Hagondange - Faisceau","Hagondange - ITE Richemont",2025,2025,51,35,"2024-12-16",11.7847222222222,"2025-08-29","10:14:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799220961,"Metz Ville - Zoufftgen",null,"Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2025,2025,51,45,"2024-12-16",11.8263888888889,"2025-11-07","12:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799321761,"Thionville - Mohon",null,"Longuyon - Bif","Thionville - Bif L3/L7",2025,2025,51,50,"2024-12-16",11.8680555555556,"2025-12-12","13:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799358361,"Longuyon - Onville",null,"Onville - Accès Ouest","Pagny-sur-Moselle - Poste 3",2025,2025,51,50,"2024-12-16",11.9097222222222,"2025-12-12","15:28:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799258761,"Metz Ville - Zoufftgen",null,"Woippy - Accès Nord","Hagondange - ITE Richemont",2025,2025,51,50,"2024-12-16",11.9513888888889,"2025-12-12","14:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799165761,"Metz - Reding",null,"Rémilly - Bât Voyageurs","Metz-Sablon - Jonct V2/V2R",2025,2025,51,50,"2024-12-16",11.9930555555556,"2025-12-12","15:17:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799382161,"Metz - Reding",null,"Sarraltroff - Bif","Rémilly - Bif L3/L11",2025,2025,51,50,"2024-12-16",12.0347222222222,"2025-12-12","12:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799458761,"Paris - Strasbourg",null,"Lunéville - Bât Voyageurs","Igney-Avricourt - Bât Voyageurs",2025,2025,51,50,"2024-12-16",12.0763888888889,"2025-12-12","15:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799465361,"Metz - Lérouville",null,"Novéant - Bât Voyageurs","Metz-Sablon - Montigny AT",2025,2025,51,45,"2024-12-16",12.1180555555556,"2025-11-03","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799257961,"Metz Ville - Zoufftgen",null,"Woippy - Accès Nord","Hagondange - Faisceau",2025,2025,51,45,"2024-12-16",12.1597222222222,"2025-11-07","15:21:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799221761,"Metz Ville - Zoufftgen",null,"Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2025,2025,51,45,"2024-12-16",12.2013888888889,"2025-11-07","15:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799183561,"Longuyon - Mont St Martin (XB)",null,"Longuyon - Bât Voyageurs","Mont-St-Martin - Frontière Fr-Be",2025,2025,51,50,"2024-12-16",12.2430555555556,"2025-12-12","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Mont-St-Martin - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",15799260361,"Metz Ville - Zoufftgen",null,"Woippy - Accès Nord","Hagondange - Faisceau",2025,2025,51,35,"2024-12-16",12.2847222222222,"2025-08-29","10:17:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799381361,"Metz - Reding",null,"Sarraltroff - Bif","Rémilly - Bif L3/L11",2025,2025,51,50,"2024-12-16",12.3263888888889,"2025-12-12","15:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 171 : Décalage des Heure Début PK Début et Heure Fin PK Début de +3 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799466961,"Metz - Lérouville",null,"Novéant - Bât Voyageurs","Metz-Sablon - Montigny AT",2025,2025,51,50,"2024-12-16",12.3680555555556,"2025-12-12","15:17:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799421561,"Remilly - Forbach",null,"Forbach - FSC Export","Stiring-Wendel - Frontière Fr-Al",2025,2025,51,50,"2024-12-16",12.4097222222222,"2025-12-12","14:21:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Stiring-Wendel - Frontière Fr-Al",null,null,"Planned",0]
[null,"SNCF-R",15799461961,"Paris - Strasbourg",null,"Igney-Avricourt - Bât Voyageurs","Réding - Bât Voyageurs",2025,2025,51,50,"2024-12-16",12.4513888888889,"2025-12-12","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799467761,"Metz - Lérouville",null,"Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2025,2025,51,50,"2024-12-16",12.4930555555556,"2025-12-12","15:04:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main courante 79 : décalage des horaires de -1 minute",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799457961,"Paris - Strasbourg",null,"Lunéville - Bât Voyageurs","Igney-Avricourt - Bât Voyageurs",2025,2025,51,50,"2024-12-16",12.5347222222222,"2025-12-12","10:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799372561,"Metz Ville - Zoufftgen",null,"Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2025,2025,51,45,"2024-12-16",12.5763888888889,"2025-11-07","15:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799342161,"Toul - Culmont Chalindrey",null,"Culmont-Chalindrey - Bif Chaudenay","Merrey (Haute-Marne)",2025,2025,51,50,"2024-12-16",12.6180555555556,"2025-12-12","14:48:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799408761,"Paris - Strasbourg",null,"Lérouville - Bât Voyageurs","Toul - Poste 1",2025,2025,51,50,"2024-12-16",12.6597222222222,"2025-12-12","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799369361,"Metz Ville - Zoufftgen",null,"Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2025,2025,51,45,"2024-12-16",12.7013888888889,"2025-11-07","12:34:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799469361,"Metz - Lérouville",null,"Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2025,2025,51,45,"2024-12-16",12.7430555555556,"2025-11-03","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799269561,"Novéant - Nancy",null,"Frouard - Bât Voyageurs","Pagny-sur-Moselle - Bât Voyageurs",2025,2025,51,50,"2024-12-16",12.7847222222222,"2025-12-12","15:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Mains courantes 81 et 145 : décalage des Heure Début PK Début et Heure Fin PK Début de +1 minute (Main Courante 145) et des Heure Début PK Fin et Heure Fin PK Fin de -1 minute (Main Courante 81)",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799409561,"Paris - Strasbourg",null,"Lérouville - Bât Voyageurs","Toul - Poste 1",2025,2025,51,50,"2024-12-16",12.8263888888889,"2025-12-12","11:56:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modif des horaires PK Fin suite à la MC 92                     ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799359161,"Longuyon - Onville",null,"Onville - Accès Ouest","Pagny-sur-Moselle - Poste 3",2025,2025,51,50,"2024-12-16",12.8680555555556,"2025-12-12","11:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799222561,"Metz Ville - Zoufftgen",null,"Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2025,2025,51,35,"2024-12-16",12.9097222222222,"2025-08-29","10:19:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799280161,"Ceinture de Metz",null,"Metz-Sablon - Bif L3/L11",0,2025,2025,51,50,"2024-12-16",12.9513888888889,"2025-12-12","12:23:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799399961,"Paris - Strasbourg",null,"Blainville-Damelevières - Bif L1/L16","Lunéville - Bât Voyageurs",2025,2025,51,50,"2024-12-16",12.9930555555556,"2025-12-12","10:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification des horaires suite à la demande MC20-0402",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799360761,"Longuyon - Onville",null,"Conflans-Jarny - Bif L12/L5 D V","Onville - Bât Voyageurs",2025,2025,51,50,"2024-12-16",13.0347222222222,"2025-12-12","11:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799314161,"Toul - Culmont Chalindrey",null,"Neufchâteau - Bât Voyageurs","Toul - Poste 1",2025,2025,51,50,"2024-12-16",13.0763888888889,"2025-12-12","10:34:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799396361,"Paris - Strasbourg",null,"Blainville-Damelevières - Aig Rosières","Blainville-Damelevières - Bât Voyageurs",2025,2025,51,50,"2024-12-16",13.1180555555556,"2025-12-12","15:26:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799304761,"Metz - Lérouville",null,"Onville - Rac Lérouville","Novéant - Bif Km 338,9",2025,2025,51,50,"2024-12-16",13.1597222222222,"2025-12-12","15:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799185761,"Remilly - Forbach",null,"Béning - Acc E Faisceau","Forbach - Bât Voyageurs",2025,2025,51,50,"2024-12-16",13.2013888888889,"2025-12-12","14:33:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799338161,"Toul - Culmont Chalindrey",null,"Merrey (Haute-Marne)","Neufchâteau - Bât Voyageurs",2025,2025,51,50,"2024-12-16",13.2430555555556,"2025-12-08","04:51:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799352961,"Conflan-Jarny - Hagondange",null,"Conflans-Jarny - Bif L12/L5 D V","Hagondange - Bât Voyageurs",2025,2025,51,50,"2024-12-16",13.2847222222222,"2025-12-12","15:32:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799389561,"Paris - Strasbourg",null,"Jarville-la-Malgrange - Bât Voyageurs","Blainville-Damelevières - Aig Rosières",2025,2025,51,50,"2024-12-16",13.3263888888889,"2025-12-12","15:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main courante 59 : décalage de -2 minutes des horaires début et de -1 minute des horaires fin",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799305561,"Metz - Lérouville",null,"Onville - Rac Lérouville","Novéant - Bif Km 338,9",2025,2025,51,50,"2024-12-16",13.3680555555556,"2025-12-12","11:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799501961,"Metz Ville - Zoufftgen",null,"Uckange - Ano Km 181,3","Ébange - Accès Sud",2025,2025,51,45,"2024-12-16",13.4097222222222,"2025-11-09","12:38:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16259841461,"Metz Ville - Zoufftgen",null,"Uckange - Poste 1","Ébange - Aig VL90",2025,2025,51,35,"2024-12-16",13.4513888888889,"2025-08-31","10:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799468561,"Metz - Lérouville",null,"Novéant - Bât Voyageurs","Metz-Sablon - Bif L3/L11",2025,2025,51,50,"2024-12-16",13.4930555555556,"2025-12-12","10:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 175 : Vibration des horaires de +5 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799307161,"Metz - Lérouville",null,"Lérouville - Rac Côté Metz","Onville - Accès Ouest",2025,2025,51,50,"2024-12-16",13.5347222222222,"2025-12-12","15:02:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main courante 51 : Décalage de +5 minutes des horaires de début",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799457161,"Paris - Strasbourg",null,"Igney-Avricourt - Bât Voyageurs","Réding - Bât Voyageurs",2025,2025,51,50,"2024-12-16",13.5763888888889,"2025-12-12","11:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16259961861,"Metz Ville - Zoufftgen",null,"Uckange - Poste 1","Ébange - Jonction Nord",2025,2025,51,50,"2024-12-16",13.6180555555556,"2025-12-12","14:53:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799181961,"Longuyon - Mont St Martin (XB)",null,"Longuyon - Bât Voyageurs","Mont-St-Martin - Frontière Fr-Be",2025,2025,51,50,"2024-12-16",13.6597222222222,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,"Mont-St-Martin - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",15799294761,"Metz Ville - Zoufftgen",null,"Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2025,2025,51,50,"2024-12-16",13.7013888888889,"2025-12-12","09:54:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main courante 76 : décalage des Heure Début PK Début et des Heure Fin PK Début de -3 minutes et des Heure Début PK Fin et Heure Fin PK Fin de -1 minute",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Zoufftgen (IE) - Frontière Fr-Lu",null,null,"Planned",0]
[null,"SNCF-R",15799164961,"Metz - Reding",null,"Rémilly - Bât Voyageurs","Metz-Sablon - Jonct V2/V2R",2025,2025,51,50,"2024-12-16",13.7430555555556,"2025-12-12","11:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 146 : vibration des horaires de -1 minute",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799188961,"Remilly - Forbach",null,"Béning - Acc E Faisceau","Forbach - Bât Voyageurs",2025,2025,51,50,"2024-12-16",13.7847222222222,"2025-12-12","12:24:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 149 : décalage des Heure Fin PK Début et Heure Fin PK Fin de -2 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799354161,"Longuyon - Onville",null,"Conflans-Jarny - Bif L12/L5 D V","Onville - Bât Voyageurs",2025,2025,51,50,"2024-12-16",13.8263888888889,"2025-12-12","15:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799330561,"Metz Ville - Zoufftgen",null,"Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2025,2025,51,50,"2024-12-16",13.8680555555556,"2025-12-12","10:22:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799272161,"Novéant - Nancy",null,"Frouard - Bât Voyageurs","Pagny-sur-Moselle - Rac côté Metz",2025,2025,51,50,"2024-12-16",13.9097222222222,"2025-12-12","11:42:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799345361,"Toul - Culmont Chalindrey",null,"Culmont-Chalindrey - Bif Chaudenay","Merrey (Haute-Marne)",2025,2025,51,50,"2024-12-16",13.9513888888889,"2025-12-08","03:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modif des horaires suite à la demande de la MC 103",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799238961,"Paris - Strasbourg",null,"Toul - Poste 1","Frouard - Bât Voyageurs",2025,2025,51,50,"2024-12-16",13.9930555555556,"2025-12-12","10:16:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799283961,"Remilly - Forbach",null,"Rémilly - Bif L3/L11","Herny - Rac côté Herny",2025,2025,51,50,"2024-12-16",14.0347222222222,"2025-12-12","11:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 147 : décalage des Heure Fin PK Début et Heure Fin PK Fin de -2 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799310961,"Toul - Culmont Chalindrey",null,"Neufchâteau - Bât Voyageurs","Toul - Rac Sud",2025,2025,51,50,"2024-12-16",14.0763888888889,"2025-12-08","05:12:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799399161,"Paris - Strasbourg",null,"Blainville-Damelevières - Aig V Bis/V L1","Lunéville - Bât Voyageurs",2025,2025,51,50,"2024-12-16",14.1180555555556,"2025-12-12","15:23:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799181161,"Longuyon - Mont St Martin (XB)",null,"Longuyon - Bât Voyageurs","Mont-St-Martin - Frontière Fr-Be",2025,2025,51,50,"2024-12-16",14.1597222222222,"2025-12-12","15:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Mont-St-Martin - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",15799352161,"Conflan-Jarny - Hagondange",null,"Conflans-Jarny - Bif L12/L5 D V","Hagondange - Bât Voyageurs",2025,2025,51,50,"2024-12-16",14.2013888888889,"2025-12-12","12:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 131 : décalage des Heure Début PK Début et Heure Fin PK Début de -17 minutes et des Heure Début PK Fin et Heure Fin PK Fin de -9 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799286361,"Remilly - Forbach",null,"Rémilly - Bât Voyageurs","Herny - Bât Voyageurs",2025,2025,51,50,"2024-12-16",14.2430555555556,"2025-12-12","15:01:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 135 : Décalage des Heure Début PK Début et Heure Début PK Fin de -1 minute",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799395561,"Paris - Strasbourg",null,"Rosières-aux-Salines - Bât Voyageurs","Blainville-Damelevières - Bât Voyageurs",2025,2025,51,50,"2024-12-16",14.2847222222222,"2025-12-12","10:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification des horaires suite à la demande MC20-0403",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799164161,"Metz - Reding",null,"Rémilly - Bât Voyageurs","Metz-Sablon - Jonct V2/V2R",2025,2025,51,40,"2024-12-16",14.3263888888889,"2025-10-05","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799279361,"Ceinture de Metz",null,"Metz-Sablon - Montigny Acc OE","Woippy - PN 1",2025,2025,51,50,"2024-12-16",14.3680555555556,"2025-12-12","15:31:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799237361,"Paris - Strasbourg",null,"Toul - Poste 1","Frouard - Bât Voyageurs",2025,2025,51,50,"2024-12-16",14.4097222222222,"2025-12-12","15:42:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799219361,"Metz Ville - Zoufftgen",null,"Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2025,2025,51,49,"2024-12-16",14.4513888888889,"2025-12-01","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799356761,"Longuyon - Onville",null,"Conflans-Jarny - Bif L12/L5 D V","Onville - Bât Voyageurs",2025,2025,51,49,"2024-12-16",14.4930555555556,"2025-12-01","03:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799502761,"Metz Ville - Zoufftgen",null,"Uckange - Ano Km 181,3","Ébange - Accès Sud",2025,2025,51,49,"2024-12-16",14.5347222222222,"2025-12-01","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799195161,"Longuyon - Onville",null,"Longuyon - Bif","Conflans-Jarny - Bif L5 VU/L12",2025,2025,51,50,"2024-12-16",14.5763888888889,"2025-12-12","15:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799288961,"Remilly - Forbach",null,"Rémilly - Bif L3/L11","Béning - Bât Voyageurs",2025,2025,51,50,"2024-12-16",14.6180555555556,"2025-12-08","03:43:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799293961,"Metz Ville - Zoufftgen",null,"Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2025,2025,51,50,"2024-12-16",14.6597222222222,"2025-12-12","15:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Zoufftgen (IE) - Frontière Fr-Lu",null,null,"Planned",0]
[null,"SNCF-R",15799311761,"Toul - Culmont Chalindrey",null,"Neufchâteau - Bât Voyageurs","Toul - Rac Sud",2025,2025,51,50,"2024-12-16",14.7013888888889,"2025-12-12","15:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799217761,"Metz Ville - Zoufftgen",null,"Woippy - Bât Voyageurs","Maizières-lès-Metz - Bât Voyageurs",2025,2025,51,49,"2024-12-16",14.7430555555556,"2025-12-01","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799420761,"Remilly - Forbach",null,"Forbach - FSC Export","Stiring-Wendel - Frontière Fr-Al",2025,2025,51,50,"2024-12-16",14.7847222222222,"2025-12-12","12:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Stiring-Wendel - Frontière Fr-Al",null,null,"Planned",0]
[null,"SNCF-R",15799354961,"Longuyon - Onville",null,"Onville - Accès Ouest","Pagny-sur-Moselle - Poste 3",2025,2025,51,49,"2024-12-16",14.8263888888889,"2025-12-01","03:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799172361,"Novéant - Nancy",null,"Pagny-sur-Moselle - Poste 3","Novéant - Bif Km 338,9",2025,2025,51,50,"2024-12-16",14.8680555555556,"2025-12-12","11:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799357561,"Longuyon - Onville",null,"Onville - Accès Ouest","Pagny-sur-Moselle - Poste 3",2025,2025,51,49,"2024-12-16",14.9097222222222,"2025-12-01","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799504361,"Metz Ville - Zoufftgen",null,"Uckange - Ano Km 181,3","Ébange - Accès Sud",2025,2025,51,50,"2024-12-16",14.9513888888889,"2025-12-12","14:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799182761,"Longuyon - Mont St Martin (XB)",null,"Longuyon - Bât Voyageurs","Mont-St-Martin - Frontière Fr-Be",2025,2025,51,50,"2024-12-16",14.9930555555556,"2025-12-08","03:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,"Mont-St-Martin - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",15799328961,"Metz Ville - Zoufftgen",null,"Metz-Ville - Carré 104","Woippy - Bât Voyageurs",2025,2025,51,50,"2024-12-16",15.0347222222222,"2025-12-12","14:38:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16260007861,"Metz Ville - Zoufftgen",null,"Uckange - Poste 2","Ébange - Jonction Nord",2025,2025,51,49,"2024-12-16",15.0763888888889,"2025-12-01","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799388761,"Paris - Strasbourg",null,"Jarville-la-Malgrange - Bât Voyageurs","Blainville-Damelevières - Aig Rosières",2025,2025,51,50,"2024-12-16",15.1180555555556,"2025-12-12","10:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification des horaires suite à la demande MC20-0404  SA2025 - Main Courante 110 : Décalage des Heure Début PK Début et et Heure Fin PK Début de -3 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799350561,"Conflan-Jarny - Hagondange",null,"Conflans-Jarny - Bif L12/L5 D V","Hagondange - Bât Voyageurs",2025,2025,51,49,"2024-12-16",15.1597222222222,"2025-12-01","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799176161,"Novéant - Nancy",null,"Pagny-sur-Moselle - Poste 3","Novéant - Bif Km 338,9",2025,2025,51,50,"2024-12-16",15.2013888888889,"2025-12-12","15:11:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main courante 80 : décalage des Heure Début PK Début et Heure Fin PK Début de -3 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799340561,"Toul - Culmont Chalindrey",null,"Culmont-Chalindrey - Bif Chaudenay","Merrey (Haute-Marne)",2025,2025,51,50,"2024-12-16",15.2430555555556,"2025-12-08","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799188161,"Remilly - Forbach",null,"Béning - Acc E Faisceau","Forbach - Bât Voyageurs",2025,2025,51,50,"2024-12-16",15.2847222222222,"2025-12-08","03:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799351361,"Conflan-Jarny - Hagondange",null,"Conflans-Jarny - Bif L12/L5 D V","Hagondange - Bât Voyageurs",2025,2025,51,49,"2024-12-16",15.3263888888889,"2025-12-07","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modifiée par main courante le 08/09/2021 (conservation des 03h00 d'amplitude, mais début à 00h00 et fin à 03h00, au lieu de 00h30 - 03h30)",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799503561,"Metz Ville - Zoufftgen",null,"Uckange - Ano Km 181,3","Ébange - Accès Sud",2025,2025,51,35,"2024-12-16",15.3680555555556,"2025-08-31","10:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main courante 77 : décalage des Heure Début PK Début et Heure Fin PK Début de +1 minute",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810396261,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - Bât Voyageurs",2025,2025,51,50,"2024-12-16",15.4097222222222,"2025-12-12","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  VAM RCST NEN : Main courante n°58 2023",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810470761,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bât Voyageurs","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,51,50,"2024-12-16",15.4513888888889,"2025-12-12","15:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Main courante n°53 2023",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810457861,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Mixte",2025,2025,51,50,"2024-12-16",15.4930555555556,"2025-12-12","11:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Main courante n°49 2023",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810517961,"Mantes - Le Havre",null,"Pavilly-Station","Le Havre - Bif d'Harfleur",2025,2025,51,50,"2024-12-16",15.5347222222222,"2025-12-12","11:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810450261,"Mantes - Le Havre",null,"Sotteville - Carré 354h","Rouen-Rive-Droite",2025,2025,51,50,"2024-12-16",15.5763888888889,"2025-12-12","11:13:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810406861,"Mantes - Le Havre",null,"Malaunay-Le Houlme - Bif de Malaunay","Motteville - Bif Auzouville",2025,2025,51,50,"2024-12-16",15.6180555555556,"2025-12-12","12:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810434661,"Mantes - Le Havre",null,"Sotteville - Triage Mixte","Sotteville - Carré 225,2",2025,2025,51,50,"2024-12-16",15.6597222222222,"2025-12-12","11:09:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Main courante n°47 2023",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810468761,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,51,50,"2024-12-16",15.7013888888889,"2025-12-12","04:41:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  VAM RCST NEN : 08/04/22 Vibration horaire suite RP0 CHA21_0021181 pour passage du 3132 (vérifier heure de passage PCO 2024)",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810399261,"Mantes - Le Havre",null,"Vernon (Eure) - Entrée Voie 4","Gaillon-Aubevoye - Poste 1",2025,2025,51,50,"2024-12-16",15.7430555555556,"2025-12-12","15:24:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  VAM RCST NEN : Main courante n°52 2023",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810398461,"Mantes - Le Havre",null,"Vernon (Eure) - Poste 1","Gaillon-Aubevoye - Poste 1",2025,2025,51,50,"2024-12-16",15.7847222222222,"2025-12-12","10:49:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810410261,"Mantes - Le Havre",null,"Gaillon-Aubevoye - ITE CFPI","Val-de-Reuil - ITE Herouard",2025,2025,51,50,"2024-12-16",15.8263888888889,"2025-12-12","15:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  VAM RCST NEN : Main courante n°46 2023",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810464961,"Mantes - Le Havre",null,"Rouen-Rive-Droite","Maromme - Sor Évit Impair",2025,2025,51,50,"2024-12-16",15.8680555555556,"2025-12-11","12:36:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification suite à MC21_0228",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810475561,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bât Voyageurs","Rosny-sur-Seine",2025,2025,51,50,"2024-12-16",15.9097222222222,"2025-12-13","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810403661,"Mantes - Le Havre",null,"Rouen-Rive-Droite - IPCS Km 142,9","Motteville - Bif Auzouville",2025,2025,51,50,"2024-12-16",15.9513888888889,"2025-12-12","11:43:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810425861,"Serqueux - Montériolier- Buchy",null,"Serqueux - C9164/9166","Motteville - Bif Auzouville",2025,2025,51,50,"2024-12-16",15.9930555555556,"2025-12-12","14:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810433861,"Mantes - Le Havre",null,"Sotteville - Quai 4 mares","Sotteville - Bif d'Eauplet",2025,2025,51,50,"2024-12-16",16.0347222222222,"2025-12-11","15:03:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante N°114 : pour train N° 852092 et 3120 trains encadrants. AAB RCST NEN 06/12/2023.  VAM RCST NEN : Main Courante n°43 2023",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810463961,"Mantes - Le Havre",null,"Bif de Darnétal - Rac 2","Maromme - Sor Évit Impair",2025,2025,51,50,"2024-12-16",16.0763888888889,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810411861,"Mantes - Le Havre",null,"Gaillon-Aubevoye - ITE CFPI","Val-de-Reuil - ITE Herouard",2025,2025,51,50,"2024-12-16",16.1180555555556,"2025-12-12","10:56:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810524361,"Mantes - Le Havre",null,"Pavilly-Station","Le Havre - Gare Locale",2025,2025,51,50,"2024-12-16",16.1597222222222,"2025-05-25","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Modification suite à évolution du système capacitaire 2025",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810518761,"Mantes - Le Havre",null,"Motteville - E/S VUT K 170,6","Foucart-Alvimare - Bât Voyageurs",2025,2025,51,50,"2024-12-16",16.2013888888889,"2025-12-12","11:49:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Main courante n°51 2023",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810448061,"Mantes - Le Havre",null,"Sotteville - Sortie TRI V4","Rouen-Rive-Droite",2025,2025,51,50,"2024-12-16",16.2430555555556,"2025-12-11","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante N°112 : pour train N° 852092 et 3120 trains encadrants. AAB RCST NEN 06/12/2023.     VAM RCST NEN : Main courante n°44 2023",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810521961,"Mantes - Le Havre",null,"Yvetot - Bât Voyageurs","Le Havre - Bif d'Harfleur",2025,2025,51,50,"2024-12-16",16.2847222222222,"2025-12-12","12:31:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810462361,"Mantes - Le Havre",null,"Bif de Darnétal - Rac 2","Rouen-Rive-Droite - IPCS Km 142,9",2025,2025,51,50,"2024-12-16",16.3263888888889,"2025-12-11","14:59:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main N° 112 : pour trains 852092 et 3120 trains encadrants. AAB RCST NEN 06/12/20023.        Modification suite à MC21_0212",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810404461,"Mantes - Le Havre",null,"Rouen-Rive-Droite - IPCS Km 142,9","Malaunay-Le Houlme - Bif de Malaunay",2025,2025,51,50,"2024-12-16",16.3680555555556,"2025-12-12","12:28:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810457061,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,51,50,"2024-12-16",16.4097222222222,"2025-12-11","15:03:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Main courante n°54 2023",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810432461,"Mantes - Le Havre",null,"Sotteville - Poste 1 + A","Sotteville - Bif d'Eauplet",2025,2025,51,50,"2024-12-16",16.4513888888889,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810525161,"Mantes - Le Havre",null,"Pavilly-Station","Le Havre - Gare Locale",2025,2025,51,50,"2024-12-16",16.4930555555556,"2025-05-26","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Modification suite à évolution du système capacitaire 2025",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810463161,"Mantes - Le Havre",null,"Bif de Darnétal - Rac 2","Rouen-Rive-Droite - IPCS Km 142,9",2025,2025,51,50,"2024-12-16",16.5347222222222,"2025-12-12","11:14:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Main Courante n°48",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810441061,"Mantes - Le Havre",null,"Val-de-Reuil - Bât Voyageurs","Oissel - Bif Tourville",2025,2025,51,50,"2024-12-16",16.5763888888889,"2025-12-12","11:03:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810468761,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,51,50,"2024-12-16",16.6180555555556,"2025-12-12","04:41:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  VAM RCST NEN : 08/04/22 Vibration horaire suite RP0 CHA21_0021181 pour passage du 3132 (vérifier heure de passage PCO 2024)",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810439461,"Mantes - Le Havre",null,"Val-de-Reuil - Bât Voyageurs","Oissel - Bif Tourville",2025,2025,51,50,"2024-12-16",16.6597222222222,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810440261,"Mantes - Le Havre",null,"Val-de-Reuil - Bât Voyageurs","Oissel - Bif Tourville",2025,2025,51,50,"2024-12-16",16.7013888888889,"2025-12-12","15:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Main courante n°45 2023",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810475561,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bât Voyageurs","Rosny-sur-Seine",2025,2025,51,50,"2024-12-16",16.7430555555556,"2025-12-13","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810458661,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Oissel - Bif Tourville",2025,2025,51,50,"2024-12-16",16.7847222222222,"2025-12-12","10:59:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810521161,"Mantes - Le Havre",null,"Motteville - Sortie Voie 2L","Le Havre - Gare Locale",2025,2025,51,50,"2024-12-16",16.8263888888889,"2025-12-08","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810441861,"Mantes - Le Havre",null,"Val-de-Reuil - Bât Voyageurs","Oissel - Bif Tourville",2025,2025,51,50,"2024-12-16",16.8680555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810471561,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bât Voyageurs","Vernon (Eure) - Pancarte Arrêt",2025,2025,51,50,"2024-12-16",16.9097222222222,"2025-12-12","10:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810520361,"Mantes - Le Havre",null,"Pavilly-Station","Yvetot - E/S VUT K 176,0",2025,2025,51,50,"2024-12-16",16.9513888888889,"2025-12-12","11:48:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Main courante n°50 2023",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810519561,"Mantes - Le Havre",null,"Pavilly-Station","Le Havre - Gare Locale",2025,2025,51,50,"2024-12-16",16.9930555555556,"2025-12-08","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810412661,"Mantes - Le Havre",null,"Gaillon-Aubevoye - ITE CFPI","Val-de-Reuil - ITE Herouard",2025,2025,51,50,"2024-12-16",17.0347222222222,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20880171861,"Mantes - Le Havre",null,"Rouen-Rive-Droite","Maromme - Sor Évit Impair",2025,2025,51,50,"2024-12-16",17.0763888888889,"2025-12-11","11:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Création Mai 2023 : suite échange avec ZP pour palier domaine voie entre rouen et Maromme. Pas de conséquences supplémentaires pour les circulations.",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810472361,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,51,50,"2024-12-16",17.1180555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810411061,"Mantes - Le Havre",null,"Gaillon-Aubevoye - ITE CFPI","Val-de-Reuil - ITE Herouard",2025,2025,51,50,"2024-12-16",17.1597222222222,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810522761,"Mantes - Le Havre",null,"Pavilly-Station","Le Havre - Gare Locale",2025,2025,51,50,"2024-12-16",17.2013888888889,"2025-05-25","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Modification suite à évolution du système capacitaire 2025",null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810400061,"Mantes - Le Havre",null,"Vernon (Eure) - Entrée Voie 4","Gaillon-Aubevoye - Poste 1",2025,2025,51,50,"2024-12-16",17.2430555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810523561,"Mantes - Le Havre",null,"Pavilly-Station","Le Havre - Gare Locale",2025,2025,51,50,"2024-12-16",17.2847222222222,"2025-05-25","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Modification suite à évolution du système capacitaire 2025",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810459461,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,51,50,"2024-12-16",17.3263888888889,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810446661,"Mantes - Le Havre",null,"Sotteville - Carré 354h","Rouen-Rive-Droite",2025,2025,51,50,"2024-12-16",17.3680555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810397661,"Mantes - Le Havre",null,"Vernon (Eure) - Poste 1","Gaillon-Aubevoye - Poste 1",2025,2025,51,50,"2024-12-16",17.4097222222222,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810406061,"Mantes - Le Havre",null,"Rouen-Rive-Droite - IPCS Km 142,9","Motteville - Bif Auzouville",2025,2025,51,50,"2024-12-16",17.4513888888889,"2025-12-08","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810405261,"Mantes - Le Havre",null,"Rouen-Rive-Droite - IPCS Km 142,9","Motteville - Bif Auzouville",2025,2025,51,50,"2024-12-16",17.4930555555556,"2025-12-08","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810473161,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Vernon (Eure) - Pancarte Arrêt",2025,2025,51,50,"2024-12-16",17.5347222222222,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810455661,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,51,50,"2024-12-16",17.5763888888889,"2025-02-24","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810454261,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,51,50,"2024-12-16",17.6180555555556,"2025-02-24","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806995961,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Voie Auxil",2025,2025,51,46,"2024-12-16",17.6597222222222,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806970961,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,51,46,"2024-12-16",17.7013888888889,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806979761,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,46,"2024-12-16",17.7430555555556,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24278367961,"Mantes - Le Havre",null,"Les Mureaux - Voie 4","Les Mureaux - ITE VBMDG",2025,2025,51,50,"2024-12-16",17.7847222222222,"2025-12-12","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16759202361,"Mantes - Le Havre",null,"Houilles-Carrières-sur-Seine - C148","Sartrouville - E/S Grps 3 et 5",2025,2025,51,51,"2024-12-16",17.8263888888889,"2024-12-21","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806705561,"Mantes - Le Havre",null,"La Garenne-Colombes - C Violet 123","Houilles-Carrières-sur-Seine - Bifurcation de Bezons",2025,2025,51,50,"2024-12-16",17.8680555555556,"2025-12-13","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806908761,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,51,45,"2024-12-16",17.9097222222222,"2025-11-08","04:34:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2019 : modification horaire suite modification offre J6 (modif 2018 via DECT18_01548) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806974961,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,46,"2024-12-16",17.9513888888889,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24277959261,"Mantes - Le Havre",null,"Houilles-Carrières-sur-Seine - C148","Sartrouville - E/S Grps 3 et 5",2025,2025,51,50,"2024-12-16",17.9930555555556,"2025-12-12","10:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806958961,"Argenteuil - Le Havre",null,"Asnières-sur-Seine - Poste 3","Argenteuil - Carré 643",2025,2025,51,50,"2024-12-16",18.0347222222222,"2025-12-11","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15807007161,"Argenteuil - Le Havre",null,"Paris-Batignolles - Remblai","Argenteuil - Carré 643",2025,2025,51,46,"2024-12-16",18.0763888888889,"2025-11-15","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806978961,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,46,"2024-12-16",18.1180555555556,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806959761,"Argenteuil - Le Havre",null,"Bois-Colombes - Bât Voyageurs","Argenteuil - Carré 643",2025,2025,51,50,"2024-12-16",18.1597222222222,"2025-12-11","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806976561,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,46,"2024-12-16",18.2013888888889,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806978161,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,46,"2024-12-16",18.2430555555556,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806980561,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,46,"2024-12-16",18.2847222222222,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806908761,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,51,45,"2024-12-16",18.3263888888889,"2025-11-08","04:34:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2019 : modification horaire suite modification offre J6 (modif 2018 via DECT18_01548) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806693561,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,51,47,"2024-12-16",18.3680555555556,"2025-11-20","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806982161,"Argenteuil - Le Havre",null,"ParisBatignolles - C791","Paris-Batignolles - FSC Formation",2025,2025,51,46,"2024-12-16",18.4097222222222,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806692761,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,51,47,"2024-12-16",18.4513888888889,"2025-11-20","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806977361,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,46,"2024-12-16",18.4930555555556,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24277977261,"Mantes - Le Havre",null,"Houilles-Carrières-sur-Seine - C148","Sartrouville - E/S Grps 3 et 5",2025,2025,51,50,"2024-12-16",18.5347222222222,"2025-12-12","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806970161,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,51,46,"2024-12-16",18.5763888888889,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806981361,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,46,"2024-12-16",18.6180555555556,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806982961,"Argenteuil - Le Havre",null,"ParisBatignolles - C791","Paris-Batignolles - FSC Formation",2025,2025,51,46,"2024-12-16",18.6597222222222,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806975761,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,46,"2024-12-16",18.7013888888889,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16759213161,"Mantes - Le Havre",null,"La Garenne-Colombes - Bif de Bezons","Houilles-Carrières-sur-Seine",2025,2025,51,51,"2024-12-16",18.7430555555556,"2024-12-21","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15807007961,"Argenteuil - Le Havre",null,"Paris-Batignolles - Remblai","Argenteuil - Carré 643",2025,2025,51,46,"2024-12-16",18.7847222222222,"2025-11-15","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16759192261,"Mantes - Le Havre",null,"La Garenne-Colombes - Sort Évit Pair","Houilles-Carrières-sur-Seine",2025,2025,51,51,"2024-12-16",18.8263888888889,"2024-12-21","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19919852061,"Pontoise - Serqueux",null,"Épinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2025,2025,51,50,"2024-12-16",18.8680555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19905854061,"Pontoise - Serqueux",null,"St-Ouen-l'Aumône",0,2025,2025,51,50,"2024-12-16",18.9097222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19919558561,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Garages Pairs",2025,2025,51,50,"2024-12-16",18.9513888888889,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19919692961,"Paris - Lille",null,"Paris-Nord - Portique Landy","St-Denis - Pk 6,8",2025,2025,51,50,"2024-12-16",18.9930555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19905788961,"Pontoise - Serqueux",null,"Pontoise - Bât Voyageurs",0,2025,2025,51,50,"2024-12-16",19.0347222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19919749461,"Pontoise - Serqueux",null,0,"La Barre-Ormesson",2025,2025,51,50,"2024-12-16",19.0763888888889,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809878961,"LGV Lille Europe - Tunnel de Fréthun",null,"Lille-Europe - Bât Voyageurs","Calais-Fréthun - Bât Voyageurs",2025,2025,51,50,"2024-12-16",19.1180555555556,"2025-12-12","12:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809901161,"LGV Lille Europe - Tunnel de Fréthun",null,"Poste 29 Sainghin - Bif de Sainghin","Lille-Europe - Bif Est",2025,2025,51,50,"2024-12-16",19.1597222222222,"2025-12-12","12:48:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809897961,"LGV Lille Europe - Tunnel de Fréthun",null,"Poste 29 Sainghin - Bif de Sainghin","Lille-Europe - Bât Voyageurs",2025,2025,51,50,"2024-12-16",19.2013888888889,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809896361,"LGV Lille Europe - Tunnel de Fréthun",null,"Poste 29 Sainghin - Bif de Sainghin","Lille-Europe - Bif Est",2025,2025,51,50,"2024-12-16",19.2430555555556,"2025-12-12","15:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 08/09/2020 par LL, suite demande par main-courante MC22-0324 ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809879761,"LGV Lille Europe - Tunnel de Fréthun",null,"Lille-Europe - Bât Voyageurs","Calais-Fréthun - Bât Voyageurs",2025,2025,51,50,"2024-12-16",19.2847222222222,"2025-12-12","15:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809881361,"LGV Lille Europe - Tunnel de Fréthun",null,"Lille-Europe - Bât Voyageurs","Calais-Fréthun - Bât Voyageurs",2025,2025,51,50,"2024-12-16",19.3263888888889,"2025-12-13","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809898761,"LGV Lille Europe - Tunnel de Fréthun",null,"Poste 29 Sainghin - Bif de Sainghin","Lille-Europe - Bât Voyageurs",2025,2025,51,50,"2024-12-16",19.3680555555556,"2025-12-13","05:16:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809880561,"LGV Lille Europe - Tunnel de Fréthun",null,"Lille-Europe - Poste 41","Calais-Fréthun - Bât Voyageurs",2025,2025,51,50,"2024-12-16",19.4097222222222,"2025-12-13","05:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809897161,"LGV Lille Europe - Tunnel de Fréthun",null,"Poste 29 Sainghin - Bif de Sainghin","Lille-Europe - Bif Est",2025,2025,51,50,"2024-12-16",19.4513888888889,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809880561,"LGV Lille Europe - Tunnel de Fréthun",null,"Lille-Europe - Poste 41","Calais-Fréthun - Bât Voyageurs",2025,2025,51,50,"2024-12-16",19.4930555555556,"2025-01-11","05:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809881361,"LGV Lille Europe - Tunnel de Fréthun",null,"Lille-Europe - Bât Voyageurs","Calais-Fréthun - Bât Voyageurs",2025,2025,51,50,"2024-12-16",19.5347222222222,"2025-01-11","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862288161,"Pontoise - Serqueux",null,"Gisors","Serqueux",2025,2025,51,50,"2024-12-16",19.5763888888889,"2025-12-12","11:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862288961,"Pontoise - Serqueux",null,"Gisors","Serqueux",2025,2025,51,50,"2024-12-16",19.6180555555556,"2025-12-12","11:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16868294661,"Pontoise - Serqueux",null,"Gisors - Garage","Serqueux - C9173",2025,2025,51,51,"2024-12-16",19.6597222222222,"2024-12-21","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16868288561,"Pontoise - Serqueux",null,"Gisors - Garage","non trouvé",2025,2025,51,51,"2024-12-16",19.7013888888889,"2024-12-21","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803748361,"Strasbourg - St Louis",null,"Colmar - Aiguille Sud","Lutterbach (Haut-Rhin) - Bât Voyageurs",2025,2025,51,50,"2024-12-16",19.7430555555556,"2025-12-12","10:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803720161,"Strasbourg - St Louis",null,"Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - Bât Voyageurs",2025,2025,51,50,"2024-12-16",19.7847222222222,"2025-12-12","10:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 141 : Décalage de l'Heure Fin PK Début de -2 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803732561,"Strasbourg - St Louis",null,"Graffenstaden - Bât Voyageurs","St-Hippolyte (Haut-Rhin)",2025,2025,51,50,"2024-12-16",19.8263888888889,"2025-12-12","11:19:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 140 : décalage des Heure Début PK Début et Heure Début PK Fin de +2 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803743161,"Paris - Strasbourg",null,"Saverne","Mommenheim - Accès Est",2025,2025,51,50,"2024-12-16",19.8680555555556,"2025-12-12","14:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"03/10/2023 XSE : Norme d'exploitation passée de Poreuse à Normale  SA2025 - Main Courante 169 : Vibration des horaires de +3 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803746361,"Paris - Strasbourg",null,"Réding - FSC Pair","Saverne - Aiguille Est",2025,2025,51,50,"2024-12-16",19.9097222222222,"2025-12-12","14:36:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main courante 88 : décalage des Heure Début PK Début et Heure Début PK Fin de -1 minute  03/10/2023 XSE : Norme d'exploitation passée de Poreuse à Normale",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803739761,"Paris - Strasbourg",null,"Saverne","Mommenheim - Accès Est",2025,2025,51,50,"2024-12-16",19.9513888888889,"2025-12-12","14:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"03/10/2023 XSE : Norme d'exploitation passée de Poreuse à Normale",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803718561,"Strasbourg - St Louis",null,"St-Louis (Haut-Rhin) - Bât Voyageurs","St-Louis (Haut-Rhin) - Frontière Fr-Su",2025,2025,51,50,"2024-12-16",19.9930555555556,"2025-12-12","10:26:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification faite suite à la demande de MC 193",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"St-Louis (Haut-Rhin) - Frontière Fr-Su",null,null,"Planned",0]
[null,"SNCF-R",15803733361,"Strasbourg - St Louis",null,"Graffenstaden - Raccordement","St-Hippolyte (Haut-Rhin)",2025,2025,51,50,"2024-12-16",20.0347222222222,"2025-12-12","15:09:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 139 : vibration des Heure Début PK Fin et Heure Fin PK Fin de +1 minute",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803758161,"Strasbourg - St Louis",null,"Sélestat","Colmar - Accès Nord",2025,2025,51,50,"2024-12-16",20.0763888888889,"2025-12-12","11:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 138 : Vibration des Heure Début PK Début et Heure Fin PK Début de -1 minute et des Heure Début PK Fin et Heure Fin PK Fin de -2 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803760761,"Strasbourg - St Louis",null,"Sélestat","Colmar - Accès Nord",2025,2025,51,50,"2024-12-16",20.1180555555556,"2025-12-12","15:21:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 142 : décalage des horaires de +2 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803759961,"Strasbourg - St Louis",null,"Colmar - ITE ZI","Colmar - Accès Nord",2025,2025,51,50,"2024-12-16",20.1597222222222,"2025-12-12","11:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"10/10/2022 : Modification des horaires de PK Fin (SA2024 - Main courante 62)  SA2025 - Main Courante 137 : Vibration des horaires de -1 minute",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803749161,"Strasbourg - St Louis",null,"Colmar - Aiguille Sud","Lutterbach (Haut-Rhin) - Bât Voyageurs",2025,2025,51,50,"2024-12-16",20.2013888888889,"2025-12-12","15:39:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803719361,"Strasbourg - St Louis",null,"St-Louis (Haut-Rhin) - Bât Voyageurs","St-Louis (Haut-Rhin) - Frontière Fr-Su",2025,2025,51,50,"2024-12-16",20.2430555555556,"2025-12-12","16:03:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification faite suite à la demande de MC 195  SA2025 - Main Courante 144 : décalage des Heure Début PK Fin et Heure Fin PK Fin de -1 minute",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"St-Louis (Haut-Rhin) - Frontière Fr-Su",null,null,"Planned",0]
[null,"SNCF-R",15803757361,"Strasbourg - St Louis",null,"Colmar - ITE ZI","Colmar - Accès Nord",2025,2025,51,50,"2024-12-16",20.2847222222222,"2025-12-12","15:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification faite suite à la demande de MC 194",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803741361,"Paris - Strasbourg",null,"Mommenheim - Accès Est","Vendenheim",2025,2025,51,50,"2024-12-16",20.3263888888889,"2025-12-12","14:57:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"03/10/2023 XSE : Norme d'exploitation passée de Poreuse à Normale",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803717761,"Strasbourg - St Louis",null,"Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - Bât Voyageurs",2025,2025,51,50,"2024-12-16",20.3680555555556,"2025-12-12","15:59:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Sa2025 - Main Courante 143 : Décalage des Heure Début PK Fin et Heure Fin PK Fin de -1 minute",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803740561,"Paris - Strasbourg",null,"Mommenheim - Accès Est","Vendenheim",2025,2025,51,50,"2024-12-16",20.4097222222222,"2025-12-12","14:29:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"03/10/2023 XSE : Norme d'exploitation passée de Poreuse à Normale  SA2025 - Main Courante 168 : Décalage des Heure Début PK Fin et Heure Fin PK Fin de +3 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803744561,"Paris - Strasbourg",null,"Réding - Accès Est","Saverne - Aiguille Est",2025,2025,51,50,"2024-12-16",20.4513888888889,"2025-12-12","14:48:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"03/10/2023 XSE : Norme d'exploitation passée de Poreuse à Normale  SA2025 - Main Courante 170 : Décalage des Heure Début PK Début et Heure Fin PK Début de +4 minutes et des Heures Début PK Fin et Heure Fin PK Fin de +3 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803908361,"Paris - Lille",null,"Goussainville - Tiroirs","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,51,50,"2024-12-16",20.4930555555556,"2025-12-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15898743861,"Creil - Jeumont",null,"Longueil-Ste-Marie - Rebroussement Cv24","Choisy-au-Bac",2025,2025,51,50,"2024-12-16",20.5347222222222,"2025-12-13","04:59:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC19-0250 (Accord TP NEN mail du 23/08/2018 et du TP IDF mail du 24/10/2018)",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803963961,"Paris - Lille",null,"St-Denis - Joncherolles","Goussainville - Garage",2025,2025,51,50,"2024-12-16",20.5763888888889,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",25075918361,"Creil - Jeumont",null,"Creil - JCT Nord","Longueil-Ste-Marie - Voie 4",2025,2025,51,50,"2024-12-16",20.6180555555556,"2025-12-13","04:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16541289561,"Paris - Lille",null,"Paris-Nord-Surface","Paris-Nord - Jonction Km 0,9",2025,2025,51,49,"2024-12-16",20.6597222222222,"2025-12-01","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maint de jour avant gare semaines impaires",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803907561,"Paris - Lille",null,"Goussainville - Bât Voyageurs","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,51,50,"2024-12-16",20.7013888888889,"2025-12-08","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803915961,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Joncherolles",2025,2025,51,50,"2024-12-16",20.7430555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812921561,"Creil - Jeumont",null,"Creil - JCT Nord","Longueil-Ste-Marie - Voie 4",2025,2025,51,50,"2024-12-16",20.7847222222222,"2025-12-08","03:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812918161,"Creil - Jeumont",null,"Creil - JCT Nord","Longueil-Ste-Marie - Voie 4",2025,2025,51,50,"2024-12-16",20.8263888888889,"2025-12-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19919464561,"Paris - Lille",null,"Paris-Nord - Jonction Km 0,9","St-Denis - Jonction Sud",2025,2025,51,50,"2024-12-16",20.8680555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20548652661,"Paris - Lille",null,"St-Denis - Garages Impairs","Pierrefitte-Stains - Bif Sud",2025,2025,51,50,"2024-12-16",20.9097222222222,"2025-12-12","14:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maintenance de jour",null,"Y",null,45454,"Major","1,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20548666761,"Paris - Lille",null,"St-Denis - Garages Impairs","St-Denis - Joncherolles",2025,2025,51,50,"2024-12-16",20.9513888888889,"2025-12-12","14:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maintenance de jour",null,"Y",null,45454,"Major","1,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803963161,"Paris - Lille",null,"St-Denis - Joncherolles","Goussainville - Garage",2025,2025,51,50,"2024-12-16",20.9930555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803914961,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Joncherolles",2025,2025,51,50,"2024-12-16",21.0347222222222,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803949961,"Paris - Lille",null,"Villiers-le-Bel-Gonesse - V 1M Côté Creil","Les Noues",2025,2025,51,50,"2024-12-16",21.0763888888889,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16706953361,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2024-12-16",21.1180555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16355414461,"Creil - Jeumont",null,"Longueil-Ste-Marie - Rebroussement Cv24","Compiègne - ITE Maille",2025,2025,51,50,"2024-12-16",21.1597222222222,"2025-12-08","03:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16618057561,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Le Bourget-Triage - Poste 1",2025,2025,51,34,"2024-12-16",21.2013888888889,"2025-08-18","04:30:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,"fermeture voie DA",null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803950761,"Paris - Lille",null,"Villiers-le-Bel-Gonesse - V 1M Côté Creil","Goussainville - CV 12",2025,2025,51,50,"2024-12-16",21.2430555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16355660761,"Creil - Jeumont",null,"Longueil-Ste-Marie - Rebroussement Cv24","Compiègne - Bât Voyageurs",2025,2025,51,50,"2024-12-16",21.2847222222222,"2025-12-08","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813977561,"Pontoise - Serqueux",null,"Liancourt-St-Pierre","Gisors - Tiroir Nord",2025,2025,51,50,"2024-12-16",21.3263888888889,"2025-12-13","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813975761,"Pontoise - Serqueux",null,0,"Gisors - Garage",2025,2025,51,50,"2024-12-16",21.3680555555556,"2025-12-13","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813976761,"Pontoise - Serqueux",null,"Osny","Montgeroult-Courcelles",2025,2025,51,50,"2024-12-16",21.4097222222222,"2025-12-13","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15814097361,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Chennevières","Conflans-Ste-Honorine - Bif Fin-d'Oise",2025,2025,51,45,"2024-12-16",21.4513888888889,"2025-11-08","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813977561,"Pontoise - Serqueux",null,"Liancourt-St-Pierre","Gisors - Tiroir Nord",2025,2025,51,50,"2024-12-16",21.4930555555556,"2024-12-21","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813975761,"Pontoise - Serqueux",null,0,"Gisors - Garage",2025,2025,51,50,"2024-12-16",21.5347222222222,"2024-12-21","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786431361,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,51,50,"2024-12-16",21.5763888888889,"2025-12-12","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786378961,"Thionville - Mohon",null,"Sedan - Garages","Montmédy - Bât Voyageurs",2025,2025,51,50,"2024-12-16",21.6180555555556,"2025-12-12","14:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786368361,"Lille - Hirson",null,"Lesquin - Bif de Lesquin","Beuvrages",2025,2025,51,50,"2024-12-16",21.6597222222222,"2025-12-12","14:09:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC19-0247 (Accord TP NEN mail du 17/08/2018) Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786377361,"Thionville - Mohon",null,"Montmédy - Bât Voyageurs","Longuyon - Bât Voyageurs",2025,2025,51,50,"2024-12-16",21.7013888888889,"2025-12-12","14:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2019 Modif des horaires suite à la demande de la MC120 Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786370761,"Lille - Hirson",null,"Lesquin - Bif de Lesquin","Beuvrages",2025,2025,51,47,"2024-12-16",21.7430555555556,"2025-11-23","04:13:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786409361,"Calais - Lille",null,"Lille-Flandres - Bif Verte-Rue","Lambersart - Bât Voyageurs",2025,2025,51,50,"2024-12-16",21.7847222222222,"2025-12-12","12:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786452161,"Calais - Lille",null,"Lambersart - Bif 4 Maisons","Hazebrouck - Poste 1",2025,2025,51,50,"2024-12-16",21.8263888888889,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786400761,"Douai - Valenciennes",null,"Somain - Aig Km 230,5","Beuvrages",2025,2025,51,50,"2024-12-16",21.8680555555556,"2025-12-12","14:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-342 (Accord TP NEN mail du 19/11/2018) Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786452961,"Calais - Lille",null,"Lambersart - Bif 4 Maisons","Hazebrouck - Poste 1",2025,2025,51,50,"2024-12-16",21.9097222222222,"2025-12-12","10:53:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0289 (Accord TP NEN mail du 29/08/2018) Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\" ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786424361,"Lille - Hirson",null,"Leval","Fourmies",2025,2025,51,50,"2024-12-16",21.9513888888889,"2025-12-12","12:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\" modification horaire faite le 05/11/2020 par LL, suite main-courante MC22-0376.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786441161,"Paris - Lille",null,"Douai - Aig Km 218,5","Triangle d'Ostricourt - Bif de Évin",2025,2025,51,45,"2024-12-16",21.9930555555556,"2025-11-09","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786418961,"Liart - Tournes",null,"Rouvroy-l'Échelle","Tournes",2025,2025,51,50,"2024-12-16",22.0347222222222,"2025-12-12","14:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786392961,"Thionville - Mohon",null,"Mohon - Bif L2","Lumes",2025,2025,51,50,"2024-12-16",22.0763888888889,"2025-12-12","14:23:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"30/08/2023 : Vibration suite main courante n° 64/2025.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786423561,"Lille - Hirson",null,"Fourmies","Hirson - Ent Marchandise",2025,2025,51,50,"2024-12-16",22.1180555555556,"2025-12-12","12:28:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\" modification horaire faite le 05/11/2020 par LL, suite main-courante MC22-0377.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786430561,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,51,50,"2024-12-16",22.1597222222222,"2025-12-12","13:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786434961,"Lille - Hirson",null,"Valenciennes - Bât Voyageurs","Berlaimont - Bât Voyageurs",2025,2025,51,50,"2024-12-16",22.2013888888889,"2025-12-12","14:18:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786390561,"Thionville - Mohon",null,"Lumes","Sedan - Accès Garage",2025,2025,51,50,"2024-12-16",22.2430555555556,"2025-12-12","14:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"30/08/2023 (DAC) : Vibration suite main courante n° 65/2023.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786380561,"Thionville - Mohon",null,"Montmédy - Bât Voyageurs","Longuyon - Bât Voyageurs",2025,2025,51,50,"2024-12-16",22.2847222222222,"2025-12-12","13:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  SA2025 - Main courante 60 : décalage de -5 minutes des horaires début",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786438761,"Paris - Lille",null,"Douai - Aig Km 218,5","Triangle d'Ostricourt - Bif de Évin",2025,2025,51,45,"2024-12-16",22.3263888888889,"2025-11-09","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786451361,"Calais - Lille",null,"Lambersart - Bif 4 Maisons","Hazebrouck - Poste 1",2025,2025,51,50,"2024-12-16",22.3680555555556,"2025-12-12","12:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  modification horaire faite par LL le 12/01/24 par DECC25-00015, suite MC25-174.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786414561,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Hirson","Tournes",2025,2025,51,50,"2024-12-16",22.4097222222222,"2025-12-12","13:21:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Attention aux horaires: la section est nommée Tournes Charleville mais la localisation réseau est de Charleville à Tournes: le PR début est donc Charleville et le PR fin Tournes. Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786385161,"Douai - Valenciennes",null,0,0,2025,2025,51,50,"2024-12-16",22.4513888888889,"2025-12-12","15:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786375761,"Thionville - Mohon",null,"Montmédy - PK 207 ,5","Longuyon - Bât Voyageurs",2025,2025,51,50,"2024-12-16",22.4930555555556,"2025-12-08","03:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786380561,"Thionville - Mohon",null,"Montmédy - Bât Voyageurs","Longuyon - Bât Voyageurs",2025,2025,51,50,"2024-12-16",22.5347222222222,"2025-12-12","13:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  SA2025 - Main courante 60 : décalage de -5 minutes des horaires début",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786440361,"Paris - Lille",null,"Douai - Aig Km 218,5","Triangle d'Ostricourt - Bif Harponlieu",2025,2025,51,50,"2024-12-16",22.5763888888889,"2025-12-12","10:54:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 16/10/20 par LL suite main-courante MC22-0352 ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786453761,"Calais - Lille",null,"Lambersart - Bif 4 Maisons","Hazebrouck - Poste 1",2025,2025,51,50,"2024-12-16",22.6180555555556,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786412961,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - ITE BLAIRON","Tournes",2025,2025,51,50,"2024-12-16",22.6597222222222,"2025-12-12","14:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Attention aux horaires: la section est nommée Tournes Charleville mais la localisation réseau va de Charleville à Tournes : le PR début est donc Charleville et le PR fin est Tournes. Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786436561,"Lille - Hirson",null,"Valenciennes - Bât Voyageurs","Berlaimont - Bât Voyageurs",2025,2025,51,50,"2024-12-16",22.7013888888889,"2025-12-12","12:23:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  modification horaire faite le 11/09/2020 par LL, suite à demande par main-courante MC22-0308.  modification horaire faite le 16/10/23 par LL, suite main-courante MC25-111.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786384361,"Douai - Valenciennes",null,0,0,2025,2025,51,50,"2024-12-16",22.7430555555556,"2025-12-12","14:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modificaition horaire suite demande de main courante MC19-0244 (Accord TP NEN mail du 03/08/2018) Modificaition horaire suite demande de main courante MC20-0341 (Accord TP NEN mail du 19/11/2018)       ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786430561,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,51,50,"2024-12-16",22.7847222222222,"2025-12-12","13:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786419761,"Liart - Tournes",null,"Rouvroy-l'Échelle","Tournes",2025,2025,51,50,"2024-12-16",22.8263888888889,"2025-12-12","13:21:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786429761,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,51,50,"2024-12-16",22.8680555555556,"2025-12-08","03:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786377361,"Thionville - Mohon",null,"Montmédy - Bât Voyageurs","Longuyon - Bât Voyageurs",2025,2025,51,50,"2024-12-16",22.9097222222222,"2025-12-12","14:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2019 Modif des horaires suite à la demande de la MC120 Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786369961,"Lille - Hirson",null,"Lesquin - Bif de Lesquin","Beuvrages",2025,2025,51,50,"2024-12-16",22.9513888888889,"2025-12-12","11:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC19-0246 (Accord TP NEN Mail du 24/08/2018) Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\" ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786431361,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,51,50,"2024-12-16",22.9930555555556,"2025-12-12","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786401561,"Douai - Valenciennes",null,"Somain - Aig Km 230,5","Beuvrages",2025,2025,51,50,"2024-12-16",23.0347222222222,"2025-12-12","15:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786439561,"Paris - Lille",null,"Douai - Aig Km 218,5","Triangle d'Ostricourt - Bif Harponlieu",2025,2025,51,50,"2024-12-16",23.0763888888889,"2025-12-12","15:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0276 (Accord TP NEN mail du 24/08/2018) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786388961,"Thionville - Mohon",null,"Lumes","Sedan - Accès Garage",2025,2025,51,50,"2024-12-16",23.1180555555556,"2025-12-12","14:11:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification des horaires suite à la demande MC20-0425 Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786421961,"Lille - Hirson",null,"Leval","Hirson - Ent Marchandise",2025,2025,51,50,"2024-12-16",23.1597222222222,"2025-12-12","13:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  Modification horaire faite le 13/10/20 par LL, suite main-courante MC22-0346.  modification horaire faite le 04/03/22 par LL, suite mail D VITRY du 25/02/22.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786428161,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,51,50,"2024-12-16",23.2013888888889,"2025-12-08","03:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786381361,"Thionville - Mohon",null,"Sedan - Garages","Montmédy - Bât Voyageurs",2025,2025,51,50,"2024-12-16",23.2430555555556,"2025-12-12","13:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification des horaires suite à la demande MC20-0396  Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  SA2025 - Main courante 61 : décalage de -5 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786408561,"Calais - Lille",null,"La Madeleine (Nord) - Garage Rougebar","Lambersart - Bif de St-André",2025,2025,51,50,"2024-12-16",23.2847222222222,"2025-12-12","11:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC20-0290 (Accord TP NEN mail du 29/08/2018)     ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786375761,"Thionville - Mohon",null,"Montmédy - PK 207 ,5","Longuyon - Bât Voyageurs",2025,2025,51,50,"2024-12-16",23.3263888888889,"2025-12-08","03:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786425161,"Lille - Hirson",null,"Leval","Hirson - Ent Marchandise",2025,2025,51,50,"2024-12-16",23.3680555555556,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786374961,"Thionville - Mohon",null,"Montmédy - PK 207 ,5","Longuyon - Bât Voyageurs",2025,2025,51,50,"2024-12-16",23.4097222222222,"2025-12-08","03:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786374961,"Thionville - Mohon",null,"Montmédy - PK 207 ,5","Longuyon - Bât Voyageurs",2025,2025,51,50,"2024-12-16",23.4513888888889,"2025-12-08","03:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786428161,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,51,50,"2024-12-16",23.4930555555556,"2025-12-08","03:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786429761,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,51,50,"2024-12-16",23.5347222222222,"2025-12-08","03:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786434161,"Lille - Hirson",null,"Valenciennes - Bât Voyageurs","Berlaimont - Bât Voyageurs",2025,2025,51,50,"2024-12-16",23.5763888888889,"2025-12-08","03:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805190161,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,51,50,"2024-12-16",23.6180555555556,"2025-12-12","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sauf ZEP 789 pour accès T4  + ZEP 252 Pantin G commandée par CHL pour aig 2547b        ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805190161,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,51,50,"2024-12-16",23.6597222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sauf ZEP 789 pour accès T4  + ZEP 252 Pantin G commandée par CHL pour aig 2547b        ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805190161,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,51,50,"2024-12-16",23.7013888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sauf ZEP 789 pour accès T4  + ZEP 252 Pantin G commandée par CHL pour aig 2547b        ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805258361,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,51,49,"2024-12-16",23.7430555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL 24/01/2023 : Mise en qualité suite rejet SIPH / Suppression de la localisation voie 2BIS-R à PE, non décrite dans l'infra SIPH.  ",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805190161,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,51,50,"2024-12-16",23.7847222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sauf ZEP 789 pour accès T4  + ZEP 252 Pantin G commandée par CHL pour aig 2547b        ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16677247761,"Mohon - Charleville-Mézière",null,"Charleville-Mézières - Bât Voyageurs","Fumay",2025,2025,51,50,"2024-12-16",23.8263888888889,"2025-12-12","10:48:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"MàJ par P KERGUIGNAS du 31-05-2023 suite à demande de l'ICA P Maslach et F Saint Maxen DLCA suite aux besoins du chantier CHA16_0010102 MàJ par P KERGUIGNAS du 13-01-2023 suite à demande de l'ICA P Maslach (Découpage de la surveillance) Charleville Revin ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862549561,"Mohon - Charleville-Mézière",null,"Revin","Givet - Poste 1",2025,2025,51,50,"2024-12-16",23.8680555555556,"2025-12-12","10:22:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"MàJ par P KERGUIGNAS du 31-05-2023 suite à demande de l'ICA P Maslach et F Saint Maxent DLCA suite aux besoins du chantier CHA16_0010102  MàJ du par P KERGUIGNAS du 13-01-2023 suite à demande de l'ICA P Maslach (Découpage de la surveillance) Revin Excl -G",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16677138461,"Mohon - Charleville-Mézière",null,"Revin","Givet - Poste 1",2025,2025,51,50,"2024-12-16",23.9097222222222,"2025-12-12","11:31:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"MàJ par P KERGUIGNAS du 31-05-2023 suite à demande de l'ICA P Maslach et F Saint Maxent DLCA suite aux besoins du chantier CHA16_0010102  MàJ du par P KERGUIGNAS du 13-01-2023 suite à demande de l'ICA P Maslach (Découpage de la surveillance) Revin Excl - ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862465161,"Conflan-Jarny - Hagondange",null,"Clermont-en-Argonne","Verdun - Bif L5/L19",2025,2025,51,50,"2024-12-16",23.9513888888889,"2025-12-12","10:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862413361,"Mohon - Charleville-Mézière",null,"Fismes","Reims - Bif L2/L22-5",2025,2025,51,50,"2024-12-16",23.9930555555556,"2025-12-12","12:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20997358661,"Conflan-Jarny - Hagondange",null,"Verdun - Bât Voyageurs","Conflans-Jarny - Bif L5 VU/L12",2025,2025,51,50,"2024-12-16",24.0347222222222,"2025-12-13","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déformée de nuit placée pendant la fermeture de ligne",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862550361,"Mohon - Charleville-Mézière",null,"Charleville-Mézières - Bât Voyageurs","Fumay",2025,2025,51,50,"2024-12-16",24.0763888888889,"2025-12-12","11:06:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"MàJ par P KERGUIGNAS du 27-09-2023 suite à demande de RCST F SATREAU MC N°84 MàJ par P KERGUIGNAS du 31-05-2023 suite à demande de l'ICA P Maslach et F Saint Maxent DLCA suite aux besoins du chantier CHA16_0010102  MàJ du par P KERGUIGNAS du 13-01-2023 su",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862412561,"Mohon - Charleville-Mézière",null,"Fismes","Reims - Bif L2/L22-5",2025,2025,51,50,"2024-12-16",24.1180555555556,"2025-12-12","11:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification suite main courante MC20-0489 du 29-11-2018 ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862546761,"Conflan-Jarny - Hagondange",null,"Verdun - Bât Voyageurs","Conflans-Jarny - Bif L5 VU/L12",2025,2025,51,50,"2024-12-16",24.1597222222222,"2025-12-12","09:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862474361,"Mulhouse - Chalampé",null,"Mulhouse-Ville - Aig Km 110","Bantzenheim - Bif L32-7/32-9",2025,2025,51,50,"2024-12-16",24.2013888888889,"2025-12-10","09:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1.3,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813839461,"Paris - Hirson",null,"Ormoy-Villers","Vaumoise",2025,2025,51,50,"2024-12-17",24.2430555555556,"2025-12-13","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812879961,"Creil - Jeumont",null,"Chevrières","Longueil-Ste-Marie - Bif Rivecourt",2025,2025,51,50,"2024-12-17",24.2847222222222,"2025-12-13","04:59:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19069820861,"Paris - Lille",null,"Creil - Bif Laversine","Creil - Bif Bonvilliers",2025,2025,51,9,"2024-12-17",24.3263888888889,"2025-03-01","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"semaine avec axe Fret ouvert",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806699161,"Mantes - Le Havre",null,"Asnières-sur-Seine - Bât Voyageurs","Sartrouville - Garage",2025,2025,51,45,"2024-12-17",24.3680555555556,"2025-11-08","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16800810561,"Mantes - Le Havre",null,"Poissy - C4147","Villennes-sur-Seine",2025,2025,51,45,"2024-12-17",24.4097222222222,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16800810561,"Mantes - Le Havre",null,"Poissy - C4147","Villennes-sur-Seine",2025,2025,51,45,"2024-12-17",24.4513888888889,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806964561,"Argenteuil - Le Havre",null,"Le Stade","Argenteuil-Triage - Dépôt du VND",2025,2025,51,50,"2024-12-17",24.4930555555556,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16780767261,"Mantes - Le Havre",null,"Maisons-Laffitte - Bât Voyageurs","Poissy - C4101",2025,2025,51,50,"2024-12-17",24.5347222222222,"2025-06-28","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788800561,"Mantes - Le Havre",null,"Achères-Triage - Les Ambassadeurs","Villennes-sur-Seine",2025,2025,51,44,"2024-12-17",24.5763888888889,"2025-06-28","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806633761,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Chennevières","Conflans-Ste-Honorine - Bif Fin-d'Oise",2025,2025,51,50,"2024-12-17",24.6180555555556,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806844361,"Mantes - Le Havre",null,"Poissy - ITE Talbot Ac O","Villennes-sur-Seine",2025,2025,51,50,"2024-12-17",24.6597222222222,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806660161,"Mantes - Le Havre",null,"Mantes-la-Jolie - ITE Aig Ouest","Mantes-la-Jolie - Bât Voyageurs",2025,2025,51,45,"2024-12-17",24.7013888888889,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788849761,"Mantes - Le Havre",null,"Achères-Triage - Jonct V1/V1Bis","Villennes-sur-Seine",2025,2025,51,44,"2024-12-17",24.7430555555556,"2025-08-22","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806844361,"Mantes - Le Havre",null,"Poissy - ITE Talbot Ac O","Villennes-sur-Seine",2025,2025,51,50,"2024-12-17",24.7847222222222,"2025-06-28","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806628161,"Argenteuil - Le Havre",null,"Le Val-d'Argenteuil","Conflans-Ste-Honorine - Bif Fin-d'Oise",2025,2025,51,50,"2024-12-17",24.8263888888889,"2025-12-13","04:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante itération I-PS et TN",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806839561,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Poissy - Bât Voyageurs",2025,2025,51,50,"2024-12-17",24.8680555555556,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806883361,"Mantes - Le Havre",null,"Les Mureaux - Voie 4","Les Mureaux - ITE VBMDG",2025,2025,51,45,"2024-12-17",24.9097222222222,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806701561,"Mantes - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,44,"2024-12-17",24.9513888888889,"2025-10-31","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806646961,"Mantes - Le Havre",null,"Sartrouville - E/S Grps 3 et 5","Maisons-Laffitte - E/S Côté Achère",2025,2025,51,50,"2024-12-17",24.9930555555556,"2025-12-13","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806892961,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage","Vernouillet-Verneuil - Triage Accès OE",2025,2025,51,45,"2024-12-17",25.0347222222222,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806884961,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,51,45,"2024-12-17",25.0763888888889,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806915961,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Jo IPCS Km 59,4",2025,2025,51,45,"2024-12-17",25.1180555555556,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806843561,"Mantes - Le Havre",null,"Poissy - ITE Talbot Ac O","Villennes-sur-Seine",2025,2025,51,50,"2024-12-17",25.1597222222222,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806700761,"Mantes - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,51,44,"2024-12-17",25.2013888888889,"2025-10-31","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16801086361,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,51,45,"2024-12-17",25.2430555555556,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806892961,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage","Vernouillet-Verneuil - Triage Accès OE",2025,2025,51,45,"2024-12-17",25.2847222222222,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788849761,"Mantes - Le Havre",null,"Achères-Triage - Jonct V1/V1Bis","Villennes-sur-Seine",2025,2025,51,44,"2024-12-17",25.3263888888889,"2025-06-28","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16801076861,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,51,45,"2024-12-17",25.3680555555556,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806657761,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - ITE Aig Est",2025,2025,51,45,"2024-12-17",25.4097222222222,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806839561,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Poissy - Bât Voyageurs",2025,2025,51,50,"2024-12-17",25.4513888888889,"2025-06-28","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806882561,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,51,45,"2024-12-17",25.4930555555556,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806839561,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Poissy - Bât Voyageurs",2025,2025,51,50,"2024-12-17",25.5347222222222,"2025-08-22","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788894861,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Villennes-sur-Seine",2025,2025,51,44,"2024-12-17",25.5763888888889,"2025-08-22","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806915961,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Jo IPCS Km 59,4",2025,2025,51,45,"2024-12-17",25.6180555555556,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806697561,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,51,44,"2024-12-17",25.6597222222222,"2025-10-31","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806660161,"Mantes - Le Havre",null,"Mantes-la-Jolie - ITE Aig Ouest","Mantes-la-Jolie - Bât Voyageurs",2025,2025,51,45,"2024-12-17",25.7013888888889,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16781042761,"Mantes - Le Havre",null,"Poissy - C4147","Poissy - Bât Voyageurs",2025,2025,51,45,"2024-12-17",25.7430555555556,"2025-11-08","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806884961,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,51,45,"2024-12-17",25.7847222222222,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16780767261,"Mantes - Le Havre",null,"Maisons-Laffitte - Bât Voyageurs","Poissy - C4101",2025,2025,51,50,"2024-12-17",25.8263888888889,"2025-08-22","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16801086361,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,51,45,"2024-12-17",25.8680555555556,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806967761,"Argenteuil - Le Havre",null,"Le Stade","Argenteuil-Triage - Poste 5",2025,2025,51,50,"2024-12-17",25.9097222222222,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16713216561,"Mantes - Le Havre",null,"Poissy - Bât Voyageurs","Épône-Mézières - Carré Violet167",2025,2025,51,45,"2024-12-17",25.9513888888889,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806756761,"Mantes - Le Havre",null,"Achères-Triage - Les Ambassadeurs","Poissy - ITE Talbot Ac O",2025,2025,51,50,"2024-12-17",25.9930555555556,"2025-08-22","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16713208961,"Mantes - Le Havre",null,"Poissy - Bât Voyageurs","Épône-Mézières - Carré Violet167",2025,2025,51,45,"2024-12-17",26.0347222222222,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806881761,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,51,45,"2024-12-17",26.0763888888889,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806756761,"Mantes - Le Havre",null,"Achères-Triage - Les Ambassadeurs","Poissy - ITE Talbot Ac O",2025,2025,51,50,"2024-12-17",26.1180555555556,"2025-06-28","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806885761,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,51,45,"2024-12-17",26.1597222222222,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16781042761,"Mantes - Le Havre",null,"Poissy - C4147","Poissy - Bât Voyageurs",2025,2025,51,45,"2024-12-17",26.2013888888889,"2025-06-28","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806704761,"Mantes - Le Havre",null,"Houilles-Carrières-sur-Seine - C148","Sartrouville - E/S Grps 3 et 5",2025,2025,51,45,"2024-12-17",26.2430555555556,"2025-11-08","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806626561,"Argenteuil - Le Havre",null,"Argenteuil-Triage - Voie Rebrousse","Conflans-Ste-Honorine - Bif Fin-d'Oise",2025,2025,51,50,"2024-12-17",26.2847222222222,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante pour passage du 136607 et 136700",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16801076861,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,51,45,"2024-12-17",26.3263888888889,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806885761,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,51,45,"2024-12-17",26.3680555555556,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806843561,"Mantes - Le Havre",null,"Poissy - ITE Talbot Ac O","Villennes-sur-Seine",2025,2025,51,50,"2024-12-17",26.4097222222222,"2025-06-28","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806882561,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,51,45,"2024-12-17",26.4513888888889,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806699961,"Mantes - Le Havre",null,"Asnières-sur-Seine - Bât Voyageurs","Sartrouville - E/S Grps 3 et 5",2025,2025,51,45,"2024-12-17",26.4930555555556,"2025-11-08","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806657761,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - ITE Aig Est",2025,2025,51,45,"2024-12-17",26.5347222222222,"2025-11-08","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788894861,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Villennes-sur-Seine",2025,2025,51,44,"2024-12-17",26.5763888888889,"2025-06-28","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806635561,"Mantes - Le Havre",null,"Maisons-Laffitte - Bât Voyageurs","Achères-Triage - FSC Réception",2025,2025,51,38,"2024-12-17",26.6180555555556,"2025-09-20","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16713208961,"Mantes - Le Havre",null,"Poissy - Bât Voyageurs","Épône-Mézières - Carré Violet167",2025,2025,51,45,"2024-12-17",26.6597222222222,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806696761,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,51,44,"2024-12-17",26.7013888888889,"2025-10-31","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806707161,"Mantes - Le Havre",null,"Houilles-Carrières-sur-Seine","Maisons-Laffitte - Bât Voyageurs",2025,2025,51,45,"2024-12-17",26.7430555555556,"2025-11-08","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"CPC : semaine 16 validée car la LTV passe de LTV40 à LTV60       ",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16713216561,"Mantes - Le Havre",null,"Poissy - Bât Voyageurs","Épône-Mézières - Carré Violet167",2025,2025,51,45,"2024-12-17",26.7847222222222,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806632161,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Chennevières","Conflans-Ste-Honorine - Bif Fin-d'Oise",2025,2025,51,50,"2024-12-17",26.8263888888889,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806881761,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,51,45,"2024-12-17",26.8680555555556,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806883361,"Mantes - Le Havre",null,"Les Mureaux - Voie 4","Les Mureaux - ITE VBMDG",2025,2025,51,45,"2024-12-17",26.9097222222222,"2025-11-08","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788800561,"Mantes - Le Havre",null,"Achères-Triage - Les Ambassadeurs","Villennes-sur-Seine",2025,2025,51,44,"2024-12-17",26.9513888888889,"2025-08-22","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802110861,"Pontoise - Serqueux",null,"Pontoise - Bif de Liesse",0,2025,2025,51,50,"2024-12-17",26.9930555555556,"2025-12-13","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19909942161,"Pontoise - Serqueux",null,"St-Ouen-l'Aumône-Liesse","St-Ouen-l'Aumône",2025,2025,51,50,"2024-12-17",27.0347222222222,"2025-12-13","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802177661,"Paris - Lille",null,"St-Denis - Garages Impairs","St-Denis - Pk 6,8",2025,2025,51,50,"2024-12-17",27.0763888888889,"2025-12-13","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802078061,"Pontoise - Serqueux",null,"Épinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2025,2025,51,50,"2024-12-17",27.1180555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802153261,"Pontoise - Serqueux",null,"Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2025,2025,51,50,"2024-12-17",27.1597222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19909770261,"Pontoise - Serqueux",null,"St-Ouen-l'Aumône",0,2025,2025,51,50,"2024-12-17",27.2013888888889,"2025-12-13","04:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802178461,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Pk 6,8",2025,2025,51,50,"2024-12-17",27.2430555555556,"2025-12-13","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802125661,"Pontoise - Serqueux",null,0,"La Barre-Ormesson",2025,2025,51,50,"2024-12-17",27.2847222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802067661,"Pontoise - Serqueux",null,"Ermont-Eaubonne - Garages Impairs","Cernay (Val-d'Oise)",2025,2025,51,50,"2024-12-17",27.3263888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802152461,"Pontoise - Serqueux",null,"Ermont-Eaubonne - Bât Voyageurs","Pontoise - Bif de Liesse",2025,2025,51,50,"2024-12-17",27.3680555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802179261,"Paris - Lille",null,"St-Denis - Garages Impairs","St-Denis - Pk 6,8",2025,2025,51,50,"2024-12-17",27.4097222222222,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802070061,"Pontoise - Serqueux",null,"Champ-de-Courses-d'Enghien","Ermont-Eaubonne - Garage Pair",2025,2025,51,50,"2024-12-17",27.4513888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802111861,"Pontoise - Serqueux",null,"Pontoise - Bif de Liesse","Pontoise - Bât Voyageurs",2025,2025,51,50,"2024-12-17",27.4930555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802128061,"Pontoise - Serqueux",null,0,"La Barre-Ormesson",2025,2025,51,50,"2024-12-17",27.5347222222222,"2025-12-13","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802126461,"Pontoise - Serqueux",null,0,"La Barre-Ormesson",2025,2025,51,50,"2024-12-17",27.5763888888889,"2025-12-13","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802151661,"Pontoise - Serqueux",null,"Franconville-Plessis-Bouchard","Montigny-Beauchamp - Tiroir",2025,2025,51,50,"2024-12-17",27.6180555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802077261,"Pontoise - Serqueux",null,"Épinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2025,2025,51,50,"2024-12-17",27.6597222222222,"2025-12-13","05:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802176861,"Paris - Lille",null,"Stade-de-France-St-Denis","St-Denis - Pk 6,8",2025,2025,51,50,"2024-12-17",27.7013888888889,"2025-12-13","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802078861,"Pontoise - Serqueux",null,"Enghien-les-Bains","Ermont-Eaubonne - Poste 1",2025,2025,51,50,"2024-12-17",27.7430555555556,"2025-12-13","05:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802127261,"Pontoise - Serqueux",null,0,"La Barre-Ormesson",2025,2025,51,50,"2024-12-17",27.7847222222222,"2025-12-13","05:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19917865261,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Garages Pairs",2025,2025,51,50,"2024-12-17",27.8263888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809899561,"LGV Lille Europe - Tunnel de Fréthun",null,"Poste 29 Sainghin - Bif de Sainghin","Lille-Europe - Bif Est",2025,2025,51,50,"2024-12-17",27.8680555555556,"2025-12-12","06:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19917453461,"Paris - Lille",null,"Paris-Nord-Surface","St-Denis - Jonction Sud",2025,2025,51,50,"2024-12-17",27.9097222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803959961,"Paris - Lille",null,"St-Denis - Joncherolles","Goussainville - Garage",2025,2025,51,50,"2024-12-17",27.9513888888889,"2025-12-13","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19069116461,"Paris - Lille",null,"Paris-Nord-Surface","St-Denis - Jonction Sud",2025,2025,51,50,"2024-12-17",27.9930555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18864678561,"Paris - Lille",null,"Goussainville - Garage","Goussainville - CV 12",2025,2025,51,50,"2024-12-17",28.0347222222222,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803948361,"Paris - Lille",null,"Villiers-le-Bel-Gonesse - V 1M Côté Creil","Goussainville - CV 12",2025,2025,51,50,"2024-12-17",28.0763888888889,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803961561,"Paris - Lille",null,"St-Denis - Joncherolles","Goussainville - Garage",2025,2025,51,50,"2024-12-17",28.1180555555556,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803911961,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Joncherolles",2025,2025,51,50,"2024-12-17",28.1597222222222,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803948361,"Paris - Lille",null,"Villiers-le-Bel-Gonesse - V 1M Côté Creil","Goussainville - CV 12",2025,2025,51,50,"2024-12-17",28.2013888888889,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803906761,"Paris - Lille",null,"Goussainville - Bât Voyageurs","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,51,50,"2024-12-17",28.2430555555556,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803949161,"Paris - Lille",null,"Villiers-le-Bel-Gonesse - V 1M Côté Creil","Les Noues",2025,2025,51,50,"2024-12-17",28.2847222222222,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803936961,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Mitry-Claye - Acc SAS/GAR",2025,2025,51,33,"2024-12-17",28.3263888888889,"2025-08-15","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20546634361,"Paris - Lille",null,"Villiers-le-Bel-Gonesse - Bif de Gonesse","Goussainville - Garage",2025,2025,51,50,"2024-12-17",28.3680555555556,"2025-12-09","15:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Maintenance de jour",null,"Y",null,45454,"Major",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803913961,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Joncherolles",2025,2025,51,50,"2024-12-17",28.4097222222222,"2025-12-13","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803905161,"Paris - Lille",null,"Goussainville - Tiroirs","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,51,50,"2024-12-17",28.4513888888889,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15804037361,"Paris - Lille",null,"Paris-Nord - Bât Voyageurs","St-Denis - Jonction Sud",2025,2025,51,26,"2024-12-17",28.4930555555556,"2025-06-28","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803906761,"Paris - Lille",null,"Goussainville - Bât Voyageurs","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,51,50,"2024-12-17",28.5347222222222,"2025-03-01","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20196204161,"Paris - Hirson",null,"Le Bourget-Triage - Poste 2","Laon - Poste 2",2025,2025,51,33,"2024-12-17",28.5763888888889,"2025-08-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803949161,"Paris - Lille",null,"Villiers-le-Bel-Gonesse - V 1M Côté Creil","Les Noues",2025,2025,51,50,"2024-12-17",28.6180555555556,"2025-03-01","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803940361,"Paris - Hirson",null,"Aulnay-sous-Bois - Aiguille Nord","Mitry-Claye",2025,2025,51,33,"2024-12-17",28.6597222222222,"2025-01-04","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19069372961,"Paris - Lille",null,"Paris-Nord - Portique Landy","Pierrefitte-Stains - Bif Sud",2025,2025,51,50,"2024-12-17",28.7013888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803998961,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,51,30,"2024-12-17",28.7430555555556,"2025-06-28","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20196189761,"Paris - Hirson",null,"Le Bourget-Triage - Poste 2","Laon - Poste 2",2025,2025,51,33,"2024-12-17",28.7847222222222,"2025-08-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803905161,"Paris - Lille",null,"Goussainville - Tiroirs","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,51,50,"2024-12-17",28.8263888888889,"2025-03-01","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803895561,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,14,"2024-12-17",28.8680555555556,"2025-01-04","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803997961,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,51,1,"2024-12-17",28.9097222222222,"2025-01-04","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16541312161,"Paris - Lille",null,"Paris-Nord - Bât Voyageurs","Paris-Nord - Jonction Km 0,9",2025,2025,51,49,"2024-12-17",28.9513888888889,"2025-12-02","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maint de jour avant gare semaines impaires",null,"Y",null,45454,"High",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803986361,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,1,"2024-12-17",28.9930555555556,"2025-01-04","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803998961,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,51,30,"2024-12-17",29.0347222222222,"2025-07-22","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20196259461,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","non trouvé",2025,2025,51,1,"2024-12-17",29.0763888888889,"2025-01-04","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803997961,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,51,1,"2024-12-17",29.1180555555556,"2024-12-17","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15814008161,"No encontrado",null,"Nanterre-Université - Ent/Sort SNCF","Sartrouville - Bât Voyageurs",2025,2025,51,50,"2024-12-17",29.1597222222222,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15814006161,"Mantes - Le Havre",null,"Houilles-Carrières-sur-Seine","Sartrouville - E/S Maison-Laff",2025,2025,51,50,"2024-12-17",29.2013888888889,"2025-12-13","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15814098161,"Conflan - Pontoise",null,"Conflans-Ste-Honorine - Bif du Gibet","Éragny-Neuville - Bif C-Ste-Honor",2025,2025,51,50,"2024-12-17",29.2430555555556,"2025-12-13","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862473561,"Mulhouse - Chalampé",null,"Mulhouse-Ville - Aig Km 110","Chalampé - Frontière Fr-Al",2025,2025,51,50,"2024-12-17",29.2847222222222,"2025-12-12","09:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,4,5",null,null,"Chalampé - Frontière Fr-Al",null,null,"Planned",0]
[null,"SNCF-R",16529806261,"Graffenstaden - Hausbergen",null,"Strasbourg-Koenigshoffen - Poste 1","Hausbergen-Triage - Accès 1B3 CS",2025,2025,51,51,"2024-12-18",29.3263888888889,"2024-12-21","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP125+131 avec SSr Hausbergen-Sud - Graffenstaden voie 1bis3 + SSr Hausbergen-Sud - Graffenstaden voie 2bis3",null,"Y",null,45454,"Medium","3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16541452261,"Paris - Lille",null,"Paris-Nord-Surface","Paris-Nord - Tech Landy",2025,2025,51,49,"2024-12-18",29.3680555555556,"2025-12-03","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maint de jour avant gare semaines impaires",null,"Y",null,45454,"High",3,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20548646661,"Paris - Lille",null,"Pierrefitte-Stains - Bif Sud","Villiers-le-Bel-Gonesse - Bif de Gonesse",2025,2025,51,50,"2024-12-18",29.4097222222222,"2025-12-10","16:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maintenance de jour",null,"Y",null,45454,"Major",3,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16541491061,"Paris - Lille",null,"Paris-Nord - Bât Voyageurs","Paris-Nord - Jonction Km 0,9",2025,2025,51,49,"2024-12-19",29.4513888888889,"2025-12-04","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maint de jour avant gare semaines impaires",null,"Y",null,45454,"High",4,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810469761,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,51,50,"2024-12-20",29.4930555555556,"2025-12-13","04:34:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810469761,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,51,50,"2024-12-20",29.5347222222222,"2025-12-13","04:34:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810400861,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - Bât Voyageurs",2025,2025,51,50,"2024-12-20",29.5763888888889,"2025-12-13","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806961361,"Argenteuil - Le Havre",null,"Bois-Colombes - Bât Voyageurs","Argenteuil - Carré 643",2025,2025,51,50,"2024-12-20",29.6180555555556,"2025-12-12","13:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806960561,"Argenteuil - Le Havre",null,"Asnières-sur-Seine - Poste 3","Argenteuil - Carré 643",2025,2025,51,50,"2024-12-20",29.6597222222222,"2025-12-12","13:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806695161,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,51,47,"2024-12-20",29.7013888888889,"2025-11-21","13:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806694361,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,51,47,"2024-12-20",29.7430555555556,"2025-11-21","13:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16541539061,"Paris - Lille",null,"Paris-Nord-Surface","Paris-Nord - Jonction Km 0,9",2025,2025,51,49,"2024-12-20",29.7847222222222,"2025-12-05","13:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maint de jour avant gare semaines impaires",null,"Y",null,45454,"High",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15809900361,"LGV Lille Europe - Tunnel de Fréthun",null,"Poste 29 Sainghin - Bif de Sainghin","Lille-Europe - Bif Est",2025,2025,51,50,"2024-12-21",29.8263888888889,"2025-12-13","06:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16529975561,"Graffenstaden - Hausbergen",null,"Strasbourg-Koenigshoffen - Poste 1","Hausbergen-Triage - Accès 1B3 CS",2025,2025,51,51,"2024-12-21",29.8680555555556,"2024-12-22","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP125+131 avec SSr Hausbergen-Sud - Graffenstaden voie 1bis3 + SSr Hausbergen-Sud - Graffenstaden voie 2bis3",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812970361,"Longueau - Boulogne",null,"Abbeville","Rang-du-Fliers-Verton",2025,2025,50,48,"2024-12-23",29.9097222222222,"2025-12-01","02:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812966561,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Aulnoye-Aymeries - Bif Sassegnies",2025,2025,51,50,"2024-12-23",29.9513888888889,"2025-12-08","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812968961,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Aulnoye-Aymeries - Bif Sassegnies",2025,2025,51,50,"2024-12-23",29.9930555555556,"2025-12-08","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805683961,"Paris - Strasbourg",null,"Meaux - Bât Voyageurs","Trilport - Bât Voyageurs",2025,2025,52,48,"2024-12-23",30.0347222222222,"2025-11-30","14:17:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Tournée M02 - Courbe Saint Faron ZEP MT01",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805569161,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Lagny-Thorigny",2025,2025,52,48,"2024-12-23",30.0763888888889,"2025-11-30","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Graissage ADV       ",null,"Y",null,45454,"High",2.2999999999999998,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805570561,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Lagny-Thorigny",2025,2025,52,48,"2024-12-23",30.1180555555556,"2025-11-30","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"surveillance     ",null,"Y",null,45454,"High",4.5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805730961,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Aig Km 21,0",2025,2025,52,48,"2024-12-23",30.1597222222222,"2025-11-28","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805699361,"Paris - Strasbourg",null,"Meaux - Voie 3","Meaux - ITE ZI",2025,2025,52,48,"2024-12-23",30.2013888888889,"2025-11-30","14:31:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Tournée M02 - Courbe Saint Faron ZEP TM04 Train fermant 117278 Passage Trilport 14h30",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805684761,"Paris - Strasbourg",null,"Meaux - Bât Voyageurs","Trilport - Bât Voyageurs",2025,2025,52,48,"2024-12-23",30.2430555555556,"2025-11-30","14:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Tournée M02 - Courbe Saint Faron ZEP TM 04 Train fermant 117278 Passage Trilport 14h30 ",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805742961,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau V","Vaires-Torcy - ITE EDF",2025,2025,52,48,"2024-12-23",30.2847222222222,"2025-11-30","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Graissage ADV + surveillance         ",null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805731961,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Faisceau V",2025,2025,52,48,"2024-12-23",30.3263888888889,"2025-11-26","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805735161,"Paris - Strasbourg",null,"Gagny - Bât Voyageurs","Vaires-Torcy - Aig Km 21,0",2025,2025,52,48,"2024-12-23",30.3680555555556,"2025-11-26","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805703361,"Paris - Strasbourg",null,"Meaux - Bât Voyageurs","Meaux - ITE ZI",2025,2025,52,48,"2024-12-23",30.4097222222222,"2025-11-30","14:12:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Tournée M02 - Courbe Saint Faron ZEP MT01  Train ouvrant : 117275 départ Meaux 13h22     ",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812903561,"Creil - Jeumont",null,"Tergnier - Triage","St-Quentin - ITE ZI",2025,2025,52,50,"2024-12-23",30.4513888888889,"2025-12-08","03:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812901161,"Creil - Jeumont",null,"Tergnier - Triage","St-Quentin - ITE ZI",2025,2025,52,50,"2024-12-23",30.4930555555556,"2025-12-08","03:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812913161,"Creil - Jeumont",null,"St-Quentin - Bât Voyageurs","Busigny - Bât Voyageurs",2025,2025,52,50,"2024-12-23",30.5347222222222,"2025-12-08","03:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813027561,"Somain - Busigny",null,"Lourches - Gros-Caillou","Somain - Aig Km 230,5",2025,2025,52,50,"2024-12-23",30.5763888888889,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812938361,"Longueau - Boulogne",null,"St-Roch (Somme) - Bât Voyageurs","Abbeville - SBAPR303",2025,2025,52,48,"2024-12-23",30.6180555555556,"2025-12-01","02:41:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813020361,"Somain - Busigny",null,"Maurois","Cambrai Ville - Bif Sud",2025,2025,52,50,"2024-12-23",30.6597222222222,"2025-12-08","03:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812943361,"Paris - Lille",null,"Arras - Bif Blangy-Est","Douai - Bif de St-Éloi",2025,2025,52,42,"2024-12-23",30.7013888888889,"2025-10-19","03:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813020361,"Somain - Busigny",null,"Maurois","Cambrai Ville - Bif Sud",2025,2025,52,50,"2024-12-23",30.7430555555556,"2025-12-08","03:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813022761,"Somain - Busigny",null,"Lourches - Gros-Caillou","Somain - Aig Km 230,5",2025,2025,52,50,"2024-12-23",30.7847222222222,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812910761,"Creil - Jeumont",null,"St-Quentin - Bât Voyageurs","Busigny - Marchandises",2025,2025,52,50,"2024-12-23",30.8263888888889,"2025-12-08","03:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813073161,"Paris - Lille",null,"Triangle d'Ostricourt - Bif de Évin","Lille-St-Sauveur - Bif Sourd-Muet",2025,2025,52,50,"2024-12-23",30.8680555555556,"2025-12-08","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813075761,"Paris - Lille",null,"Triangle d'Ostricourt - Bif de Évin","Lille-St-Sauveur - Bif Sourd-Muet",2025,2025,52,50,"2024-12-23",30.9097222222222,"2025-12-08","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812944161,"Paris - Lille",null,"Arras - Bif Blangy-Est","Douai - Bif de St-Éloi",2025,2025,52,42,"2024-12-23",30.9513888888889,"2025-10-19","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812897161,"Creil - Jeumont",null,"Compiègne - Garage Pair","Noyon",2025,2025,52,50,"2024-12-23",30.9930555555556,"2025-12-08","03:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813021161,"Somain - Busigny",null,"Maurois","Cambrai Ville - Bif Sud",2025,2025,52,50,"2024-12-23",31.0347222222222,"2025-12-08","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812893161,"Creil - Jeumont",null,"Noyon - Voie 3","Tergnier - Bât Voyageurs",2025,2025,52,50,"2024-12-23",31.0763888888889,"2025-12-08","03:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812891561,"Creil - Jeumont",null,"Compiègne - ITE Maille","Noyon",2025,2025,52,50,"2024-12-23",31.1180555555556,"2025-12-08","04:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813021161,"Somain - Busigny",null,"Maurois","Cambrai Ville - Bif Sud",2025,2025,52,50,"2024-12-23",31.1597222222222,"2025-12-08","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813025161,"Somain - Busigny",null,0,"Lourches - Bât Voyageurs",2025,2025,52,50,"2024-12-23",31.2013888888889,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813026761,"Somain - Busigny",null,0,"Lourches - Bât Voyageurs",2025,2025,52,50,"2024-12-23",31.2430555555556,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812893961,"Creil - Jeumont",null,"Noyon - Voie 3","Tergnier - Ent Marchandise",2025,2025,52,50,"2024-12-23",31.2847222222222,"2025-12-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806957361,"Argenteuil - Le Havre",null,"Paris-Batignolles - Remblai","Bois-Colombes - Bât Voyageurs",2025,2025,52,48,"2024-12-23",31.3263888888889,"2025-11-28","12:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806956561,"Argenteuil - Le Havre",null,"Paris-Batignolles - Remblai","Colombes",2025,2025,52,48,"2024-12-23",31.3680555555556,"2025-11-27","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806952561,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,52,48,"2024-12-23",31.4097222222222,"2025-11-27","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806953361,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,52,48,"2024-12-23",31.4513888888889,"2025-11-27","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806958161,"Argenteuil - Le Havre",null,"Paris-Batignolles - Remblai","Colombes",2025,2025,52,48,"2024-12-23",31.4930555555556,"2025-11-28","12:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806955761,"Argenteuil - Le Havre",null,"Paris-Batignolles - Remblai","Bois-Colombes - Bât Voyageurs",2025,2025,52,48,"2024-12-23",31.5347222222222,"2025-11-27","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812919761,"Creil - Jeumont",null,"Creil - JCT Nord","Longueil-Ste-Marie - Voie 4",2025,2025,52,50,"2024-12-23",31.5763888888889,"2025-12-12","10:57:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20546628461,"Paris - Lille",null,"Pierrefitte-Stains - Bât Voyageurs","Villiers-le-Bel-Gonesse - V 1M Côté Creil",2025,2025,52,50,"2024-12-23",31.6180555555556,"2025-12-09","15:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Maintenance de jour",null,"Y",null,45454,"Major",1.2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16357287861,"Creil - Jeumont",null,"Longueil-Ste-Marie - Rebroussement Cv24","Compiègne - Bât Voyageurs",2025,2025,52,50,"2024-12-23",31.6597222222222,"2025-12-12","11:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812918961,"Creil - Jeumont",null,"Creil - JCT Nord","Longueil-Ste-Marie - Voie 4",2025,2025,52,50,"2024-12-23",31.7013888888889,"2025-12-12","15:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC19-0253 (Accord TP NEN mail du 23/08/2018 et TP IDF mail du 18/10/2018) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803999961,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,52,49,"2024-12-23",31.7430555555556,"2025-12-07","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15804008561,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,52,49,"2024-12-23",31.7847222222222,"2025-12-07","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16357336261,"Creil - Jeumont",null,"Longueil-Ste-Marie - Rebroussement Cv24","Compiègne - Bât Voyageurs",2025,2025,52,50,"2024-12-23",31.8263888888889,"2025-12-12","15:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803942761,"Paris - Hirson",null,"Aulnay-sous-Bois - Aiguille Nord","Mitry-Claye",2025,2025,52,43,"2024-12-23",31.8680555555556,"2025-10-26","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20205935861,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153",0,2025,2025,52,47,"2024-12-23",31.9097222222222,"2025-11-21","12:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maintenance   non repris dans TCAp : tiroir H",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803996961,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,52,41,"2024-12-23",31.9513888888889,"2025-10-12","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803985361,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,52,50,"2024-12-23",31.9930555555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803937961,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Mitry-Claye - Acc SAS/GAR",2025,2025,52,42,"2024-12-23",32.0347222222222,"2025-10-19","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786402361,"Douai - Valenciennes",null,"Somain - Aig Km 230,5","Beuvrages",2025,2025,52,48,"2024-12-23",32.0763888888889,"2025-11-30","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786403161,"Douai - Valenciennes",null,"Somain - Aig Km 230,5","Beuvrages",2025,2025,52,48,"2024-12-23",32.1180555555556,"2025-11-30","03:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806954161,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,52,48,"2024-12-24",32.1597222222222,"2025-11-28","13:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806954961,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,52,48,"2024-12-24",32.2013888888889,"2025-11-28","13:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20548692961,"Paris - Lille",null,"Villiers-le-Bel-Gonesse - Bif de Gonesse","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,52,50,"2024-12-24",32.2430555555556,"2025-12-09","13:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maintenance de jour",null,"Y",null,45454,"Major",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20548674561,"Paris - Lille",null,"Goussainville - Garage","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,52,50,"2024-12-24",32.2847222222222,"2025-12-09","15:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Maintenance de jour",null,"Y",null,45454,"Major",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20546640261,"Paris - Lille",null,"Villiers-le-Bel-Gonesse - Bif de Gonesse","Goussainville - Garage",2025,2025,52,50,"2024-12-24",32.3263888888889,"2025-12-09","15:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Maintenance de jour",null,"Y",null,45454,"Major",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20546663261,"Paris - Lille",null,"Pierrefitte-Stains - Bât Voyageurs","Villiers-le-Bel-Gonesse - V 1M Côté Creil",2025,2025,52,50,"2024-12-26",32.3680555555556,"2025-12-12","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"maintenance de jour",null,"Y",null,45454,"Major",4.5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16161510161,"Paris - Strasbourg",null,"Trilport - Bif de Germigny","La Ferté-sous-Jouarre - Aig Km 63,6-Év",2025,2025,1,48,"2024-12-30",32.4097222222222,"2025-03-08","04:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"17/10/2023 (DAC) : Vibration suite main courante n° 104/2025. 23/11/2022 (DAC) : Création de fenêtre générique élargie pour maintenance suite concertation 2025. Trilport - LFJ (exclue) Train ouvrant : 56622 (voir Variante correspondante) Train fermant : 5",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805686361,"Paris - Strasbourg",null,"Trilport - Bât Voyageurs","Trilport - Bif de Germigny",2025,2025,1,49,"2024-12-30",32.4513888888889,"2025-12-07","14:16:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Tournée M03 - Courbe de Trilport ZEP 205 V1 TO 117275 / TF 117133 ZEP 205 V1 ",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16161555361,"Paris - Strasbourg",null,"Changis-St-Jean - ITE Appel","Mézy - Poste U",2025,2025,1,50,"2024-12-30",32.4930555555556,"2025-03-08","04:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"23/11/2022 (DAC) : Création de fenêtre générique élargie pour maintenance, suite concertation 2025. LFJ (inclue) - CTH (inclue) Voie 5 de CTH libre pour TN",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16161505561,"Paris - Strasbourg",null,"La Ferté-sous-Jouarre - ITE CA La-Brie","La Ferté-sous-Jouarre - Bât Voyageurs",2025,2025,1,10,"2024-12-30",32.5347222222222,"2025-03-08","04:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16161555361,"Paris - Strasbourg",null,"Changis-St-Jean - ITE Appel","Mézy - Poste U",2025,2025,1,50,"2024-12-30",32.5763888888889,"2025-03-08","04:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"23/11/2022 (DAC) : Création de fenêtre générique élargie pour maintenance, suite concertation 2025. LFJ (inclue) - CTH (inclue) Voie 5 de CTH libre pour TN",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805596161,"Paris - Strasbourg",null,"Trilport - Bif de Germigny","Trilport - Aig Év Germigny",2025,2025,1,49,"2024-12-30",32.6180555555556,"2025-12-07","14:24:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Tournée M03 - Courbe de Trilport ZEP 33002 (202+204+206+208+210+212+214+216) V2  TO 117144 / TF 117278",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16161555361,"Paris - Strasbourg",null,"Changis-St-Jean - ITE Appel","Mézy - Poste U",2025,2025,1,50,"2024-12-30",32.6597222222222,"2025-03-08","04:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"23/11/2022 (DAC) : Création de fenêtre générique élargie pour maintenance, suite concertation 2025. LFJ (inclue) - CTH (inclue) Voie 5 de CTH libre pour TN",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805603561,"Paris - Strasbourg",null,"Trilport - Bif de Germigny","La Ferté-sous-Jouarre - Aig Km 63,6-Év",2025,2025,1,49,"2024-12-30",32.7013888888889,"2025-12-07","14:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Tournée M03 - Tunnel Armentière ZEP de Type L LFJ TLP V1 TO 117129 / TF 117133",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805602761,"Paris - Strasbourg",null,"Trilport - Bif de Germigny","La Ferté-sous-Jouarre - ITE CA La-Brie",2025,2025,1,49,"2024-12-30",32.7430555555556,"2025-12-07","14:28:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Tournée M03 - Courbe de Trilport ZEP 33002 (202+204+206+208+210+212+214+216) + Tunnel Armentière ZEP de Type L LFJ TLP V2 TO 117144 / TF 117278",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805685561,"Paris - Strasbourg",null,"Trilport - ITE CCI de Meau","Trilport - Aig Év Germigny",2025,2025,1,49,"2024-12-30",32.7847222222222,"2025-12-07","14:24:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Tournée M03 - Courbe de Trilport ZEP 33002 (202+204+206+208+210+212+214+216) V2 TO 117144 / TF 117278   ",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18950210361,"Calais - Boulogne",null,0,0,2025,2025,1,20,"2024-12-30",32.8263888888889,"2025-05-17","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16880107261,"Calais - Boulogne",null,0,0,2025,2025,1,20,"2024-12-30",32.8680555555556,"2025-05-17","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812939161,"Longueau - Boulogne",null,"St-Roch (Somme) - Bif et Poste 1","Abbeville - SBAPR303",2025,2025,1,49,"2024-12-30",32.9097222222222,"2025-12-07","03:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810407661,"Mantes - Le Havre",null,"Rouen-Rive-Droite - IPCS Km 142,9","Motteville - Bif Auzouville",2025,2025,1,50,"2024-12-30",32.9513888888889,"2025-09-28","05:38:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810465761,"Mantes - Le Havre",null,"Bif de Darnétal - Rac 2","Maromme - Sor Évit Impair",2025,2025,1,50,"2024-12-30",32.9930555555556,"2025-05-08","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810466761,"Mantes - Le Havre",null,"Bif de Darnétal - Rac 2","Maromme - Sor Évit Impair",2025,2025,1,50,"2024-12-30",33.0347222222222,"2025-05-12","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810408661,"Mantes - Le Havre",null,"Rouen-Rive-Droite - IPCS Km 142,9","Motteville - Bif Auzouville",2025,2025,1,50,"2024-12-30",33.0763888888889,"2025-09-29","04:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante N°115: pour train N°3135. AAB RCST NEN. 06/12/2023.  Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810436661,"Mantes - Le Havre",null,"Sotteville - Triage Mixte","Sotteville - Carré 225,2",2025,2025,1,50,"2024-12-30",33.1180555555556,"2025-05-11","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810437461,"Mantes - Le Havre",null,"Sotteville - Poste 1 + A","Sotteville - Bif d'Eauplet",2025,2025,1,50,"2024-12-30",33.1597222222222,"2025-05-11","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée  électriquement",null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810451061,"Mantes - Le Havre",null,"Sotteville - Carré 354h","Rouen-Rive-Droite",2025,2025,1,49,"2024-12-30",33.2013888888889,"2025-05-11","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810452261,"Mantes - Le Havre",null,"Sotteville - Carré 354h","Rouen-Rive-Droite",2025,2025,1,49,"2024-12-30",33.2430555555556,"2025-05-11","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810448861,"Mantes - Le Havre",null,"Sotteville - Carré 354h","Rouen-Rive-Droite",2025,2025,1,49,"2024-12-30",33.2847222222222,"2025-05-11","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810435461,"Mantes - Le Havre",null,"Sotteville - Poste 1 + A","Sotteville - Bif d'Eauplet",2025,2025,1,50,"2024-12-30",33.3263888888889,"2025-05-11","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812971161,"Longueau - Boulogne",null,"Abbeville","Rang-du-Fliers-Verton",2025,2025,51,49,"2024-12-30",33.3680555555556,"2025-12-07","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810455661,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,51,50,"2024-12-30",33.4097222222222,"2025-05-12","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810454261,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,51,50,"2024-12-30",33.4513888888889,"2025-05-08","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805696961,"Paris - Strasbourg",null,"Lagny-Thorigny - Tiroir 3","Esbly",2025,2025,1,49,"2024-12-31",33.4930555555556,"2025-12-02","11:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"02/10/2023 (DAC) : Vibration suite main courante n° 91/2025. ZEP de type L Meaux Zone d'Esbly - Vaires Zone Lagny V2  Tournée 001 Tunnel de Chalifert  HOUAT 2021 : TO 113636 / TF 113638  Circulation du TN 113638 et TER 839136 en CS sur V1 IPCS  Suppressio",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805761161,"Paris - Strasbourg",null,"Gagny - Bât Voyageurs","Vaires-Torcy - Faisceau Pair",2025,2025,1,1,"2024-12-31",33.5347222222222,"2025-01-01","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV sur ZEP type G 1717+1519+1517 Vaires P5 Sel 7131 SSr Raincy-Lagny voie 1B1  DFV sur ZEP type G 1512 +1514+1516 Vaires P5 DFV sur ZEP type G 1505 Vaires P5. DFV sur ZEP type G 1705+1505+1503 Vaires P5.  Sel 7341 SSr Raincy-Pomponne voie 1L1  DFV sur ZE",null,"Y",null,45454,"Medium","1,2,3,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805740161,"Paris - Strasbourg",null,"Chelles-Gournay - Aig côté Gagny","Vaires-Torcy - Aig Côté Chelle",2025,2025,1,1,"2024-12-31",33.5763888888889,"2025-01-01","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV sur ZEP type G 1531 VAI P5. Sel 7151 SSr Chelles-Vaires voie 1R DFV sur ZEP type G 1538 VAI P5. Sel 7482 SSr Chelles-Vaires voie 2R",null,"Y",null,45454,"Medium","1,2,3,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806755961,"Mantes - Le Havre",null,"Sartrouville - E/S Grps 3 et 5","Villennes-sur-Seine",2025,2025,1,45,"2024-12-31",33.6180555555556,"2025-06-28","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19072847461,"Paris - Strasbourg",null,"Chelles-Gournay - Aig côté Gagny","Vaires-Torcy - Aig 40a",2025,2025,2,8,"2025-01-06",33.6597222222222,"2025-02-22","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805762561,"Paris - Strasbourg",null,"Vaires-Torcy - Dépôt","Vaires-Torcy - Aig Km 21,0",2025,2025,2,45,"2025-01-06",33.7013888888889,"2025-11-09","12:24:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP 2313 = 1301 + 1303 + 1305 + 1307 + 1341 + 1353 + 1505 ZEP 833(Pagny)+1320+1322 LGV2 Surveillance entrée LGV   ",null,"Y",null,45454,"High",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805568361,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Vaires-Torcy - ITE EDF",2025,2025,2,45,"2025-01-06",33.7430555555556,"2025-11-09","12:24:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP 2313 = 1301 + 1303 + 1305 + 1307 + 1341 + 1353 + 1505  ZEP 833(Pagny)+1320+1322 LGV2 Surveillance entrée LGV   ",null,"Y",null,45454,"High",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16555070461,"Paris - Hirson",null,"Le Bourget-Triage - Poste 2",0,2025,2025,2,50,"2025-01-06",33.7847222222222,"2025-12-13","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP G 403 Laon P2",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16555085361,"Paris - Hirson",null,0,0,2025,2025,2,50,"2025-01-06",33.8263888888889,"2025-12-13","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP G 404 Laon P2",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16733713461,"Calais - Dunkerque",null,"Dunkerque-Grande-Synthe - Bif Puyt-Houck","Gravelines - Accès Ouest",2025,2025,2,48,"2025-01-06",33.8680555555556,"2025-11-29","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16166281461,"Calais - Dunkerque",null,"Coudekerque-Branche","Dunkerque-Grande-Synthe - Groupe Attente A1",2025,2025,2,48,"2025-01-06",33.9097222222222,"2025-11-29","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16638478461,"Calais - Dunkerque",null,"Coudekerque-Branche","Loon-Plage",2025,2025,2,48,"2025-01-06",33.9513888888889,"2025-11-29","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"+ ZEP 117+118+119+120+121+122+123 Dunkerque P5 Voies de services (accès Dunkerque P5 côté P4)",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16902822261,"Paris - Lille",null,"Creil - Bif Laversine","Creil - Bif Bonvilliers",2025,2025,2,50,"2025-01-06",33.9930555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"semaine avec axe Fret ouvert",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812958361,"Racc de Santes - Don-Sainghin",null,"Lille-St-Sauveur - Carre Violet 40","Haubourdin - Bif de Tortue",2025,2025,2,46,"2025-01-06",34.0347222222222,"2025-11-15","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20876228761,"Calais - Boulogne",null,"non trouvé",0,2025,2025,2,50,"2025-01-06",34.0763888888889,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813070761,"Calais - Boulogne",null,"non trouvé",0,2025,2025,2,50,"2025-01-06",34.1180555555556,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire suite évol capa du sa2024, faite par LL le 16/11/2021.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812924361,"Lille - Mouscron",null,"La Madeleine (Nord) - ITE ZI Pilateri","Tourcoing - Frontière Fr-Be",2025,2025,2,44,"2025-01-06",34.1597222222222,"2025-11-02","13:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Tourcoing - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",16148538861,"Calais - Boulogne",null,0,0,2025,2025,2,47,"2025-01-06",34.2013888888889,"2025-11-22","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16940970461,"Paris - Lille",null,"Ronchin - Bât Voyageurs","Lille-Flandres - Jct V2B/DD-401a",2025,2025,2,48,"2025-01-06",34.2430555555556,"2025-11-29","04:58:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16703217161,"Racc de Santes - Don-Sainghin",null,"Haubourdin - Bif Haubourdin","Haubourdin - Bif de Tortue",2025,2025,2,46,"2025-01-06",34.2847222222222,"2025-11-15","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813069961,"Calais - Boulogne",null,"non trouvé",0,2025,2025,2,50,"2025-01-06",34.3263888888889,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire suite évol capa du sa2024, faite le 16/11/21 par LL.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813054161,"Calais - Boulogne",null,"Wimille-Wimereux","Calais-Fréthun - C102/204",2025,2025,2,50,"2025-01-06",34.3680555555556,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire suite évol capa du sa2024, faite le 16/11/21 par LL.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812955961,"Racc de Santes - Don-Sainghin",null,"Lille-St-Sauveur - Carre Violet 40","Haubourdin - Bif de Tortue",2025,2025,2,46,"2025-01-06",34.4097222222222,"2025-11-15","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16314076361,"Calais - Boulogne",null,0,0,2025,2025,2,50,"2025-01-06",34.4513888888889,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813073961,"Paris - Lille",null,"Triangle d'Ostricourt - Bif de Évin","Lille-St-Sauveur - Bif Sourd-Muet",2025,2025,2,48,"2025-01-06",34.4930555555556,"2025-11-29","04:58:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813053361,"Calais - Boulogne",null,"Wimille-Wimereux","Calais-Fréthun - Carré 103",2025,2025,2,50,"2025-01-06",34.5347222222222,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire suite évol capa du sa2024, faite le 16/11/21 par LL.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16702727761,"Racc de Santes - Don-Sainghin",null,"Lille-St-Sauveur - Poste CM","Lille-St-Sauveur - Bif de Justice",2025,2025,2,46,"2025-01-06",34.5763888888889,"2025-11-15","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812913961,"Creil - Jeumont",null,0,"Busigny - Marchandises",2025,2025,2,50,"2025-01-06",34.6180555555556,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire suite évol capa du sa2024 faite le 16/11/21 par LL.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16946447961,"Lille - Mouscron",null,"Roubaix - Annexe","Tourcoing - Poste 1",2025,2025,2,44,"2025-01-06",34.6597222222222,"2025-11-02","13:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812925961,"Lille - Mouscron",null,"La Madeleine (Nord) - ITE ZI Pilateri","Tourcoing - Frontière Fr-Be",2025,2025,2,44,"2025-01-06",34.7013888888889,"2025-11-02","13:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Tourcoing - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",16541599061,"Longueau - Boulogne",null,"Pont-Remy","Abbeville - SBAPR303",2025,2025,2,8,"2025-01-06",34.7430555555556,"2025-02-22","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812888961,"Creil - Jeumont",null,"Compiègne - Garage Pair","Tergnier - Bât Voyageurs",2025,2025,2,50,"2025-01-06",34.7847222222222,"2025-12-13","04:59:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17021287761,"Somain - Busigny",null,0,"Bertry",2025,2025,2,50,"2025-01-06",34.8263888888889,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17021260961,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Le Cateau",2025,2025,2,50,"2025-01-06",34.8680555555556,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16541629661,"Longueau - Boulogne",null,"Abbeville","Conchil-le-Temple - SBAPR9101",2025,2025,2,8,"2025-01-06",34.9097222222222,"2025-02-22","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16553063361,"Mohon - Charleville-Mézière",null,"non trouvé","Reims - Bif L2/L10 Sud",2025,2025,2,6,"2025-01-06",34.9513888888889,"2025-02-08","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP Poste1 Reims: 409+411+413+415+417 V1 et 412+416+418 V2  Consignation S11 Reims: SEL 6027+6031+6030+6034+104 SS Bétheny - Les Godets V1 + V2  ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17000884561,"Mohon - Charleville-Mézière",null,"Reims - Gril","Reims - Bât Voyageurs",2025,2025,2,22,"2025-01-06",34.9930555555556,"2025-01-25","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799393561,"Paris - Strasbourg",null,"Rosières-aux-Salines - Bât Voyageurs","Blainville-Damelevières - Aig V Bis/V L1",2025,2025,2,38,"2025-01-06",35.0347222222222,"2025-09-20","05:14:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799456361,"Paris - Strasbourg",null,"Lunéville - Bât Voyageurs","Réding - Bât Voyageurs",2025,2025,2,38,"2025-01-06",35.0763888888889,"2025-09-20","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799461161,"Paris - Strasbourg",null,"Lunéville - Bât Voyageurs","Réding - Bât Voyageurs",2025,2025,2,38,"2025-01-06",35.1180555555556,"2025-09-20","06:14:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.  Modification des horaires PK fin par main coura",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799387961,"Paris - Strasbourg",null,"Jarville-la-Malgrange - Bif L1/L14","Blainville-Damelevières - Aig Rosières",2025,2025,2,38,"2025-01-06",35.1597222222222,"2025-09-20","05:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799397561,"Paris - Strasbourg",null,"Blainville-Damelevières - Bif L1/L16","Marainviller",2025,2025,2,38,"2025-01-06",35.2013888888889,"2025-09-20","05:46:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799393561,"Paris - Strasbourg",null,"Rosières-aux-Salines - Bât Voyageurs","Blainville-Damelevières - Aig V Bis/V L1",2025,2025,2,38,"2025-01-06",35.2430555555556,"2025-09-20","05:14:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799387961,"Paris - Strasbourg",null,"Jarville-la-Malgrange - Bif L1/L14","Blainville-Damelevières - Aig Rosières",2025,2025,2,38,"2025-01-06",35.2847222222222,"2025-09-20","05:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799398361,"Paris - Strasbourg",null,"Blainville-Damelevières - Aig V Bis/V L1","Lunéville - Bât Voyageurs",2025,2025,2,38,"2025-01-06",35.3263888888889,"2025-09-20","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799248161,"Paris - Strasbourg",null,"Frouard - Bât Voyageurs","Nancy-Ville - Bât Voyageurs",2025,2025,2,38,"2025-01-06",35.3680555555556,"2025-09-20","05:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799398361,"Paris - Strasbourg",null,"Blainville-Damelevières - Aig V Bis/V L1","Lunéville - Bât Voyageurs",2025,2025,2,38,"2025-01-06",35.4097222222222,"2025-09-20","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799398361,"Paris - Strasbourg",null,"Blainville-Damelevières - Aig V Bis/V L1","Lunéville - Bât Voyageurs",2025,2025,2,38,"2025-01-06",35.4513888888889,"2025-09-20","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799397561,"Paris - Strasbourg",null,"Blainville-Damelevières - Bif L1/L16","Marainviller",2025,2025,2,38,"2025-01-06",35.4930555555556,"2025-09-20","05:46:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799248961,"Paris - Strasbourg",null,"Frouard - Accès Nord","Nancy-Ville - Bât Voyageurs",2025,2025,2,38,"2025-01-06",35.5347222222222,"2025-09-20","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément. Modif des horaires pour passage du TER 837586. ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799397561,"Paris - Strasbourg",null,"Blainville-Damelevières - Bif L1/L16","Marainviller",2025,2025,2,38,"2025-01-06",35.5763888888889,"2025-09-20","05:46:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799393561,"Paris - Strasbourg",null,"Rosières-aux-Salines - Bât Voyageurs","Blainville-Damelevières - Aig V Bis/V L1",2025,2025,2,38,"2025-01-06",35.6180555555556,"2025-09-20","05:14:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799391161,"Paris - Strasbourg",null,"Jarville-la-Malgrange - Bât Voyageurs","Blainville-Damelevières - Aig Rosières",2025,2025,2,38,"2025-01-06",35.6597222222222,"2025-09-20","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799391161,"Paris - Strasbourg",null,"Jarville-la-Malgrange - Bât Voyageurs","Blainville-Damelevières - Aig Rosières",2025,2025,2,38,"2025-01-06",35.7013888888889,"2025-09-20","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16749203061,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,2,4,"2025-01-06",35.7430555555556,"2025-01-26","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16881181561,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,2,2,"2025-01-06",35.7847222222222,"2025-01-13","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806752161,"Mantes - Le Havre",null,"Sartrouville - Bât Voyageurs","Villennes-sur-Seine",2025,2025,2,29,"2025-01-06",35.8263888888889,"2025-07-19","05:02:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806890561,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage","Vernouillet-Verneuil - Triage Accès OE",2025,2025,2,50,"2025-01-06",35.8680555555556,"2025-12-13","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806879361,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,2,50,"2025-01-06",35.9097222222222,"2025-12-13","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806754961,"Mantes - Le Havre",null,"Sartrouville - E/S Grps 3 et 5","Villennes-sur-Seine",2025,2025,2,50,"2025-01-06",35.9513888888889,"2025-12-13","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806695961,"Mantes - Le Havre",null,"Asnières-sur-Seine - Bât Voyageurs","Sartrouville - Garage",2025,2025,2,50,"2025-01-06",35.9930555555556,"2025-12-13","04:49:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante n°119 : Pour passage du 13164",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806878561,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,2,50,"2025-01-06",36.0347222222222,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806861561,"Mantes - Le Havre",null,"Poissy - ITE Talbot Ac O","Épône-Mézières - Carré Violet167",2025,2025,2,50,"2025-01-06",36.0763888888889,"2025-12-13","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante n°118 : Pour passage du 13164 VAM RCST NEN  V2Bis sur la zone de quai de Poissy   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16794931061,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Evo & Manœuvres","Limay - Bât Voyageurs",2025,2025,2,50,"2025-01-06",36.1180555555556,"2025-12-13","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806654561,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,2,50,"2025-01-06",36.1597222222222,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806754961,"Mantes - Le Havre",null,"Sartrouville - E/S Grps 3 et 5","Villennes-sur-Seine",2025,2025,2,50,"2025-01-06",36.2013888888889,"2025-12-13","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16795003061,"Argenteuil - Le Havre",null,"Issou-Porcheville","Mantes-la-Jolie - Bât Voyageurs",2025,2025,2,50,"2025-01-06",36.2430555555556,"2025-12-13","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806634761,"Mantes - Le Havre",null,"Maisons-Laffitte - Bât Voyageurs","Achères-Triage - FSC Réception",2025,2025,2,50,"2025-01-06",36.2847222222222,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante n°165 : reconduction des DETC SA 2023 et 2024",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806656161,"Mantes - Le Havre",null,"Mantes-la-Jolie - ITE Aig Ouest","Mantes-la-Jolie - Bât Voyageurs",2025,2025,2,50,"2025-01-06",36.3263888888889,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806880161,"Mantes - Le Havre",null,"Les Mureaux - Voie 4","Les Mureaux - ITE VBMDG",2025,2025,2,50,"2025-01-06",36.3680555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16780779061,"Mantes - Le Havre",null,"Achères-Triage - Les Ambassadeurs","Villennes-sur-Seine",2025,2025,2,50,"2025-01-06",36.4097222222222,"2025-06-21","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16780779061,"Mantes - Le Havre",null,"Achères-Triage - Les Ambassadeurs","Villennes-sur-Seine",2025,2025,2,50,"2025-01-06",36.4513888888889,"2025-08-08","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806757561,"Mantes - Le Havre",null,"Achères-Triage - Les Ambassadeurs","Poissy - ITE Talbot Ac O",2025,2025,2,29,"2025-01-06",36.4930555555556,"2025-07-19","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806911561,"Argenteuil - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Jo IPCS Km 59,4",2025,2025,2,50,"2025-01-06",36.5347222222222,"2025-12-13","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16794990061,"Argenteuil - Le Havre",null,"Issou-Porcheville","Mantes-la-Jolie - Bif Argenteuil",2025,2025,2,50,"2025-01-06",36.5763888888889,"2025-12-13","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806837161,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Poissy - Bât Voyageurs",2025,2025,2,29,"2025-01-06",36.6180555555556,"2025-07-19","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806703961,"Mantes - Le Havre",null,"Houilles-Carrières-sur-Seine - C148","Sartrouville - E/S Grps 3 et 5",2025,2025,2,50,"2025-01-06",36.6597222222222,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806862561,"Mantes - Le Havre",null,"Poissy - Bât Voyageurs","Épône-Mézières - Carré Violet167",2025,2025,2,50,"2025-01-06",36.7013888888889,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806655361,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - ITE Aig Est",2025,2025,2,50,"2025-01-06",36.7847222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806837161,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Poissy - Bât Voyageurs",2025,2025,2,29,"2025-01-06",36.9930555555556,"2025-01-18","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806754961,"Mantes - Le Havre",null,"Sartrouville - E/S Grps 3 et 5","Villennes-sur-Seine",2025,2025,2,50,"2025-01-06",37.2013888888889,"2025-08-08","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806841961,"Mantes - Le Havre",null,"Poissy - ITE Talbot Ac O","Villennes-sur-Seine",2025,2025,2,29,"2025-01-06",37.2430555555556,"2025-01-18","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16539177961,"Paris - Lille",null,"St-Denis - Garages Impairs","St-Denis - Pk 6,8",2025,2025,2,50,"2025-01-06",37.4513888888889,"2025-12-12","12:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"travaux de jour DV/RV uniquement semaines paires",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803916961,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Joncherolles",2025,2025,2,50,"2025-01-06",37.6597222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15804031961,"Paris - Lille",null,"Paris-Nord - P Sat Périp","St-Denis - Jonction Sud",2025,2025,2,50,"2025-01-06",37.8680555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES  ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803968961,"Paris - Hirson",null,"Paris-La Chapelle - Heurtoir","Le Bourget-Triage - Poste 1",2025,2025,2,50,"2025-01-06",38.0347222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES (Ligne B - DIR)   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803909161,"Paris - Lille",null,"Goussainville - Bât Voyageurs","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,2,50,"2025-01-06",38.1597222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15804035361,"Paris - Lille",null,"Paris-Nord - Bât Voyageurs","Paris-Nord - JCT DR/RT",2025,2025,2,50,"2025-01-06",38.3680555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES (Ligne B) Modification des PK début RR et DR pour libération des estacades.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803893761,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,2,50,"2025-01-06",38.5763888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19974136161,"Paris - Lille",null,"Paris-Nord - Bât Voyageurs","Paris-Nord - JCT DR/RT",2025,2025,2,50,"2025-01-06",38.6180555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES (Ligne B) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15804006161,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,2,50,"2025-01-06",38.8263888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES (Aulnay complet) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16708426361,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,2,50,"2025-01-06",39.0347222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18425477761,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,2,8,"2025-01-06",39.1597222222222,"2025-02-22","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16939950261,"St Just en Chaussée - Douai",null,"Douai - Bif de St-Éloi",0,2025,2025,2,49,"2025-01-06",39.3263888888889,"2025-12-06","04:33:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine B",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805190161,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,51,50,"2025-01-06",39.5347222222222,"2025-08-09","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sauf ZEP 789 pour accès T4  + ZEP 252 Pantin G commandée par CHL pour aig 2547b        ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15814006161,"Mantes - Le Havre",null,"Houilles-Carrières-sur-Seine","Sartrouville - E/S Maison-Laff",2025,2025,51,50,"2025-01-07",39.7430555555556,"2025-12-13","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16610680461,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,2,5,"2025-01-10",39.9513888888889,"2025-01-27","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null," POSE COM 9100 A ET B",null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16610878561,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,2,5,"2025-01-10",39.9930555555556,"2025-01-27","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"pose com 9100 a et b",null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799410361,"Paris - Strasbourg",null,"Lérouville - Bât Voyageurs","Toul - Poste 1",2025,2025,2,41,"2025-01-12",40.2013888888889,"2025-10-13","02:01:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modif des horaires suite à la demande de MC 100",null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810407661,"Mantes - Le Havre",null,"Rouen-Rive-Droite - IPCS Km 142,9","Motteville - Bif Auzouville",2025,2025,1,50,"2025-01-13",40.4930555555556,"2025-09-21","05:38:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810435461,"Mantes - Le Havre",null,"Sotteville - Poste 1 + A","Sotteville - Bif d'Eauplet",2025,2025,1,50,"2025-01-13",40.6597222222222,"2025-11-23","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810437461,"Mantes - Le Havre",null,"Sotteville - Poste 1 + A","Sotteville - Bif d'Eauplet",2025,2025,1,50,"2025-01-13",40.7013888888889,"2025-11-23","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée  électriquement",null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24242452061,"Mantes - Le Havre",null,"Poissy - C4147","Poissy - Bât Voyageurs",2025,2025,2,50,"2025-01-13",40.9097222222222,"2025-12-13","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16794990061,"Argenteuil - Le Havre",null,"Issou-Porcheville","Mantes-la-Jolie - Bif Argenteuil",2025,2025,2,50,"2025-01-13",41.1180555555556,"2025-12-13","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16795003061,"Argenteuil - Le Havre",null,"Issou-Porcheville","Mantes-la-Jolie - Bât Voyageurs",2025,2025,2,50,"2025-01-13",41.3263888888889,"2025-12-13","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806752161,"Mantes - Le Havre",null,"Sartrouville - Bât Voyageurs","Villennes-sur-Seine",2025,2025,2,29,"2025-01-13",41.3680555555556,"2025-07-19","05:02:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806864961,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,2,50,"2025-01-13",41.5763888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806879361,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,2,50,"2025-01-13",41.8263888888889,"2025-12-13","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803893761,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,2,50,"2025-01-13",42.0347222222222,"2025-10-11","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16708426361,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,2,50,"2025-01-13",42.0763888888889,"2025-11-25","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19915228561,"Paris - Hirson",null,"Le Bourget-Triage - Poste 2","Laon - Poste 2",2025,2025,3,50,"2025-01-13",42.2847222222222,"2025-12-13","05:33:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16543137461,"Creil - Jeumont",null,"St-Quentin - Poste 1","St-Quentin - ITE ZI",2025,2025,3,5,"2025-01-13",42.4930555555556,"2025-02-01","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812988161,"Don-Sainghin - Lens",null,"Lens - Bif l'Épinette","Don-Sainghin - Bât Voyageurs",2025,2025,3,50,"2025-01-13",42.7013888888889,"2025-12-13","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787637261,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Mohon - Bât Voyageurs",2025,2025,3,48,"2025-01-13",42.9097222222222,"2025-10-18","05:31:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16597704961,"Paris - Strasbourg",null,"Épernay - Poste 1","Épernay - Bât Voyageurs",2025,2025,3,29,"2025-01-13",42.9930555555556,"2025-07-19","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"voie 2 : zep 510 + SEL 36 du sous secteur Mardeuil Epernay Voie 2  ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799331361,"Metz Ville - Zoufftgen",null,"Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2025,2025,3,4,"2025-01-13",43.2013888888889,"2025-01-25","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2019 Modif des horaires suite à la demande de la MC 144  SA2023 Modification des horaires par main courante (passage de 23h26 - 05h26 à 23h30 - 05h30)",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810426661,"Serqueux - Montériolier- Buchy",null,"Serqueux - C9164/9166","Motteville - Bif Auzouville",2025,2025,3,50,"2025-01-13",43.4097222222222,"2025-09-21","16:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  VAM RCST NEN : Main courante n°108 2021",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177636961,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,3,6,"2025-01-13",43.4513888888889,"2025-02-10","05:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806706361,"Mantes - Le Havre",null,"Houilles-Carrières-sur-Seine","Maisons-Laffitte - Bât Voyageurs",2025,2025,3,50,"2025-01-13",43.6597222222222,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"CPC : semaine 16 validée car la LTV passe de LTV40 à LTV60 ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862287161,"Pontoise - Serqueux",null,"Gisors","Serqueux",2025,2025,3,49,"2025-01-13",43.8680555555556,"2025-12-07","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"04/10/13 SBE : adaptation de la générique suite aux commandes Sillons TER HN (perte de 30 min sur la générique) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16926014761,"Paris - Lille",null,"Paris-Nord-Surface","Paris-Nord - Jonction Km 0,9",2025,2025,3,27,"2025-01-13",44.0763888888889,"2025-07-04","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16882032961,"Douai - Valenciennes",null,0,0,2025,2025,3,50,"2025-01-13",44.2013888888889,"2025-12-13","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16881934061,"No encontrado",null,0,"Douai - Bât Voyageurs",2025,2025,3,50,"2025-01-13",44.3680555555556,"2025-12-13","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810400861,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - Bât Voyageurs",2025,2025,51,50,"2025-01-13",44.5763888888889,"2025-12-01","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810524361,"Mantes - Le Havre",null,"Pavilly-Station","Le Havre - Gare Locale",2025,2025,51,50,"2025-01-13",44.7847222222222,"2025-09-21","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Modification suite à évolution du système capacitaire 2025",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805190161,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,51,50,"2025-01-13",44.8263888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sauf ZEP 789 pour accès T4  + ZEP 252 Pantin G commandée par CHL pour aig 2547b        ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806988761,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,3,50,"2025-01-14",45.0347222222222,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806985961,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Voie Auxil",2025,2025,3,50,"2025-01-14",45.2430555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806989561,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-St-Lazare - Pont Legendre",2025,2025,3,50,"2025-01-14",45.3263888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23823715961,"Paris - Strasbourg",null,"Chelles-Gournay - Aig côté Gagny","Vaires-Torcy - Aig Côté Chelle",2025,2025,3,4,"2025-01-17",45.5347222222222,"2025-01-20","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV sur ZEP type G 1538 VAI P5. Sel 7482 SSr Chelles-Vaires voie 2R DFV sur ZEP type G 1531 VAI P5. Sel 7151 SSr Chelles-Vaires voie 1R                 ",null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16600615261,"Paris - Strasbourg",null,"Épernay - Cumières Triage","Épernay - Bif L1/22 5",2025,2025,3,10,"2025-01-18",45.7430555555556,"2025-03-09","07:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"voie quater zep 537 + SEL 231 du sous secteur Epernay GARE  voie M: zep 541 + SEL 241 du sous secteur Epernay GARE   ",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16876141461,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,3,40,"2025-01-18",45.9513888888889,"2025-10-05","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16879891361,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - ITE Aig Est",2025,2025,3,40,"2025-01-18",46.1597222222222,"2025-10-05","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16877258861,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,3,40,"2025-01-18",46.2013888888889,"2025-10-05","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16879876961,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,3,40,"2025-01-18",46.4097222222222,"2025-10-05","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16880352161,"Argenteuil - Le Havre",null,"Mantes-Station","Mantes-la-Jolie - Bât Voyageurs",2025,2025,3,40,"2025-01-18",46.6180555555556,"2025-10-05","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16876799061,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,3,26,"2025-01-19",46.8680555555556,"2025-06-30","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16876796761,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Vernon (Eure) - Pancarte Arrêt",2025,2025,3,26,"2025-01-19",46.9097222222222,"2025-06-30","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16877182361,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,3,40,"2025-01-19",47.1180555555556,"2025-10-06","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16877178161,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,3,40,"2025-01-19",47.3263888888889,"2025-10-06","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810435461,"Mantes - Le Havre",null,"Sotteville - Poste 1 + A","Sotteville - Bif d'Eauplet",2025,2025,1,50,"2025-01-20",47.5347222222222,"2025-10-19","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810451061,"Mantes - Le Havre",null,"Sotteville - Carré 354h","Rouen-Rive-Droite",2025,2025,1,49,"2025-01-20",47.5763888888889,"2025-09-28","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813053361,"Calais - Boulogne",null,"Wimille-Wimereux","Calais-Fréthun - Carré 103",2025,2025,2,50,"2025-01-20",47.7430555555556,"2025-11-29","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire suite évol capa du sa2024, faite le 16/11/21 par LL.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787637261,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Mohon - Bât Voyageurs",2025,2025,3,48,"2025-01-20",48.0347222222222,"2025-02-08","05:31:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862287161,"Pontoise - Serqueux",null,"Gisors","Serqueux",2025,2025,3,49,"2025-01-20",48.2430555555556,"2025-03-30","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"04/10/13 SBE : adaptation de la générique suite aux commandes Sillons TER HN (perte de 30 min sur la générique) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813741861,"Paris - Hirson",null,"Vauxaillon - Km 117,291","Laon - Bif St-Marcel",2025,2025,4,45,"2025-01-20",48.2847222222222,"2025-08-02","06:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16759070861,"Creil - Jeumont",null,"Busigny - Bif Sud","Le Cateau",2025,2025,4,11,"2025-01-20",48.4930555555556,"2025-03-15","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16736559861,"Calais - Lille",null,"Lille-Flandres - Bât Voyageurs","Lille-Flandres - Bif Wasquehal",2025,2025,4,46,"2025-01-20",48.7013888888889,"2025-11-15","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787623961,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Épernay - Bât Voyageurs",2025,2025,4,45,"2025-01-20",48.9097222222222,"2025-11-07","14:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"24/11/2022 (DAC) : Ajustement horaire suite concertation génériques 2025 (839136\\\\839154). Modification horaire le 12/06/2020 pour levée de désaccord.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787619761,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Blesme-Haussignemont - Bât Voyageurs",2025,2025,4,45,"2025-01-20",49.0763888888889,"2025-11-07","15:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"   Modification le 17/02/2020 : Modification d'horaires de la fenêtre générique suite à concertation 2019.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787678061,"Paris - Strasbourg",null,"Blesme-Haussignemont - Aiguille L1/L10","Bar-le-Duc - Ent V1B/Sor V2B",2025,2025,4,48,"2025-01-20",49.2013888888889,"2025-11-07","15:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17000945461,"No encontrado",null,"Reims - Bif L10S/Rac 3","Reims - Bif L2/L10 Sud",2025,2025,4,6,"2025-01-20",49.4097222222222,"2025-02-08","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799498761,"Metz Ville - Zoufftgen",null,"Uckange - Ano Km 181,3","Ébange - Accès Sud",2025,2025,4,47,"2025-01-20",49.6180555555556,"2025-11-17","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                             ",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799442361,"Metz Ville - Zoufftgen",null,0,"Metz-Ville - Poste 66 CTN1",2025,2025,4,4,"2025-01-20",49.6597222222222,"2025-01-25","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 5h30, LuMa>VeSa, toutes voies à quai MZV+1L3+2L3 MZ BV-MZ AM. Avec 4D_MZS-MZ1_002 et 4D_MZ-WPY_004. Détournement FRET via Metz DLP.          ",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799480961,"Metz Ville - Zoufftgen",null,"Metz-Nord - Bât Voyageurs","Woippy - Accès Sud",2025,2025,4,4,"2025-01-20",49.8680555555556,"2025-01-25","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"CAP 6h00 de nuit voies 1 + 2 au niveau de Woippy BV. Simultanément avec 5F_MZ-WPY_001. Report circulation sur voies BIS entre MZS AO et WPY AN. Entrée WPY par voie 1M libre. Permet de travailler sur la jonction Bis/Rapides au BV. Prévoir un renfort au fai",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16637008561,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Evo & Manœuvres","Mantes-la-Jolie - Bif Argenteuil",2025,2025,4,12,"2025-01-20",50.0763888888889,"2025-03-22","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786385961,"Douai - Valenciennes",null,0,0,2025,2025,4,42,"2025-01-20",50.2847222222222,"2025-10-19","03:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805758161,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Aig Km 21,0",2025,2025,51,50,"2025-01-20",50.3680555555556,"2025-03-10","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813807861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2025-01-20",50.5763888888889,"2025-08-02","05:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813765261,"Paris - Hirson",null,"Vierzy - Aig Km 94,1","Vierzy - Aig Km 96,0",2025,2025,51,50,"2025-01-20",50.7847222222222,"2025-08-02","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810400861,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - Bât Voyageurs",2025,2025,51,50,"2025-01-20",50.9930555555556,"2025-09-29","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810396261,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - Bât Voyageurs",2025,2025,51,50,"2025-01-20",51.0347222222222,"2025-09-29","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  VAM RCST NEN : Main courante n°58 2023",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21528341161,"Mantes - Le Havre",null,"Sartrouville - Bât Voyageurs","Maisons-Laffitte - E/S Côté Achère",2025,2025,4,50,"2025-01-21",51.2430555555556,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16880777761,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,4,24,"2025-01-24",51.4513888888889,"2025-06-15","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22794531661,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage","Vernouillet-Verneuil - Triage Accès OE",2025,2025,4,4,"2025-01-24",51.6597222222222,"2025-01-26","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16882119361,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Épône-Mézières - Carré Violet167",2025,2025,4,4,"2025-01-24",51.7430555555556,"2025-01-26","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16748633661,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153",0,2025,2025,4,7,"2025-01-25",51.9513888888889,"2025-02-10","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"non repris dans TCAP (VS):  Groupe S, Groupe T, Tiroir I, sas M, Groupe A voie 1 à 7 voie de la bosse de débranchement A, impasse C Le sas SE2 ne sera pas pris.",null,"Y",null,45454,"High","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22794777161,"Mantes - Le Havre",null,"Les Mureaux - Faisceau RNUR","Épône-Mézières - SG",2025,2025,4,26,"2025-01-26",52.1597222222222,"2025-06-30","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16880801661,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,4,26,"2025-01-26",52.3680555555556,"2025-06-30","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16882192461,"Mantes - Le Havre",null,"Les Mureaux - Voie 4","Les Mureaux - ITE VBMDG",2025,2025,4,22,"2025-01-26",52.4097222222222,"2025-06-02","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16882180861,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,4,22,"2025-01-26",52.6180555555556,"2025-06-02","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16662224461,"Calais - Lille",null,"Bailleul (Nord)","Hazebrouck - Poste 1",2025,2025,4,49,"2025-01-26",52.7847222222222,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810408661,"Mantes - Le Havre",null,"Rouen-Rive-Droite - IPCS Km 142,9","Motteville - Bif Auzouville",2025,2025,1,50,"2025-01-27",53.0763888888889,"2025-10-27","04:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante N°115: pour train N°3135. AAB RCST NEN. 06/12/2023.  Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810465761,"Mantes - Le Havre",null,"Bif de Darnétal - Rac 2","Maromme - Sor Évit Impair",2025,2025,1,50,"2025-01-27",53.1180555555556,"2025-09-01","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786399761,"Douai - Valenciennes",null,"Somain - Aig Km 230,5","Beuvrages",2025,2025,3,49,"2025-01-27",53.3263888888889,"2025-09-27","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805717361,"Paris - Strasbourg",null,"Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2025,2025,5,27,"2025-01-27",53.5347222222222,"2025-07-01","12:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"1B1 : ZEP 1209 (1103 + 1141 + 1143) LGY (aig. 3915b,3923a)     ",null,"Y",null,45454,"Medium",1.2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16733149461,"Lille - Baisieux",null,0,0,2025,2025,5,50,"2025-01-27",53.7430555555556,"2025-12-13","05:04:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16759435361,"Creil - Jeumont",null,"Viry-Noureuil","Tergnier - Voie F2",2025,2025,5,40,"2025-01-27",53.7847222222222,"2025-10-04","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799411161,"Paris - Strasbourg",null,"Lérouville - Bât Voyageurs","Toul - Poste 1",2025,2025,5,41,"2025-01-27",54.1180555555556,"2025-10-11","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799199161,"Longuyon - Onville",null,"Longuyon - Bif","Conflans-Jarny - Bif L5 VU/L12",2025,2025,5,45,"2025-01-27",54.2430555555556,"2025-11-07","16:23:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main courante 85 : décalage de +13 minutes des horaires",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16722076261,"Metz - Reding",null,0,"Sarraltroff - Bif",2025,2025,5,12,"2025-01-27",54.4513888888889,"2025-03-21","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16731938161,"Metz - Reding",null,0,0,2025,2025,5,12,"2025-01-27",54.4930555555556,"2025-03-21","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177638361,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,5,6,"2025-01-27",54.7013888888889,"2025-02-10","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16638849861,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Evo & Manœuvres","Mantes-la-Jolie - Bât Voyageurs",2025,2025,5,11,"2025-01-27",54.9097222222222,"2025-03-15","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805758161,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Aig Km 21,0",2025,2025,51,50,"2025-01-27",55.1180555555556,"2025-02-24","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805577161,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2025,2025,51,50,"2025-01-27",55.2013888888889,"2025-02-24","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810400861,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - Bât Voyageurs",2025,2025,51,50,"2025-01-27",55.4097222222222,"2025-12-08","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16262716861,"Paris - Strasbourg",null,"Vaires-Torcy - ITE EDF","Lagny-Thorigny",2025,2025,5,27,"2025-01-28",55.6180555555556,"2025-07-03","10:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"1L1 : ZEP 1111 LGY (aig. 3915a). 29/11/2022 (DAC) : transformation des DEF en FEN suite concertation génériques 2025.",null,"Y",null,45454,"Medium",2.4,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16259692561,"Metz Ville - Zoufftgen",null,"Uckange - Poste 2","Ébange - Jonction Nord",2025,2025,5,40,"2025-01-28",55.8263888888889,"2025-10-03","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis  Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                                           ",null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16262674161,"Paris - Strasbourg",null,"Vaires-Torcy - Poste 4","Lagny-Thorigny",2025,2025,5,5,"2025-01-29",55.8680555555556,"2025-01-29","15:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"2B1 : ZEP 1330+1332+1350 EDF (aig. 2E1,4E2). 29/11/2022 (DAC) : transformation des DEF en FEN suite concertation génériques 2025.",null,"Y",null,45454,"Medium",3,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788670261,"Paris - Strasbourg",null,"Chelles-Gournay - Aig côté Gagny","Vaires-Torcy - Dépôt",2025,2025,5,5,"2025-01-31",56.0763888888889,"2025-02-02","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV sur ZEP type G 1519+1512. Sel 7131 SSr Raincy-Lagny voie 1B1 Sel 7462 SSr Raincy-Lagny voie 2B1           ",null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24150804461,"Paris - Strasbourg",null,"Lérouville - Aig Km 287,6","Lérouville - Aig Km 290,4",2025,2025,5,11,"2025-01-31",56.2847222222222,"2025-03-15","02:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5C_LER_002.                                                                                                                 ",null,"Y",null,45454,"Medium",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16874320961,"Mantes - Le Havre",null,"Mantes-la-Jolie - Rem Banlieue","Rosny-sur-Seine",2025,2025,5,28,"2025-01-31",56.4930555555556,"2025-07-07","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16856798561,"Paris - Lille",null,"Boisleux","Arras - Poste 1",2025,2025,5,48,"2025-02-01",56.7013888888889,"2025-11-30","06:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16856792661,"Paris - Lille",null,"Boisleux","Arras - Poste 1",2025,2025,5,48,"2025-02-01",56.7847222222222,"2025-11-30","06:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16860430061,"Paris - Lille",null,"Miraumont","Courcelles-le-Comte",2025,2025,5,48,"2025-02-02",56.9930555555556,"2025-12-01","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16860436361,"Paris - Lille",null,"Boisleux","Arras - Poste 1",2025,2025,5,48,"2025-02-02",57.2013888888889,"2025-12-01","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799319161,"Thionville - Mohon",null,"Longuyon - Bif","Thionville - Bif L3/L7",2025,2025,5,49,"2025-02-02",57.2430555555556,"2025-12-08","02:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177726361,"Metz Ville - Zoufftgen",null,"Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2025,2025,5,8,"2025-02-02",57.4513888888889,"2025-02-24","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf V1+V2, 4h nuit entre Metz BV et Woippy.",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810426661,"Serqueux - Montériolier- Buchy",null,"Serqueux - C9164/9166","Motteville - Bif Auzouville",2025,2025,3,50,"2025-02-03",57.6597222222222,"2025-12-12","16:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  VAM RCST NEN : Main courante n°108 2021",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16833939861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 2","Laon - ITE Pirelli",2025,2025,6,6,"2025-02-03",57.8263888888889,"2025-02-08","06:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812975161,"Longueau - Boulogne",null,"Abbeville","Rang-du-Fliers-Verton",2025,2025,6,50,"2025-02-03",57.9513888888889,"2025-12-06","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cadrage de nuit alignés avec Calais Amiens ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813046361,"Paris - Lille",null,"Creil - Bât Voyageurs","Longueau - Poste 1",2025,2025,6,48,"2025-02-03",58.1597222222222,"2025-11-29","04:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification horaire suite demande de main courante MC19-0249 (Accord TP NEN mail du 23/08/2018 et TP IDF mail du 27/11/2018)   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16792199761,"Longueau - Boulogne",null,"Conchil-le-Temple","Étaples-Le Touquet - Accès Nord",2025,2025,6,49,"2025-02-03",58.3680555555556,"2025-12-06","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16712420961,"Calais - Boulogne",null,"non trouvé",0,2025,2025,6,9,"2025-02-03",58.5763888888889,"2025-03-01","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Travaux HS tunnel d'ordre PN 146 Domaine A S06 à S09",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812952761,"Paris - Lille",null,"Longueau - Bif de Camon","Arras - Bif Sud",2025,2025,6,49,"2025-02-03",58.6180555555556,"2025-12-07","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813085161,"Paris - Lille",null,"Lamotte-Brebière","Arras - Bif Sud",2025,2025,6,49,"2025-02-03",58.8263888888889,"2025-12-07","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813043161,"Paris - Lille",null,"St-Just-en-Chaussée - Bât Voyageurs","Longueau - Poste 1",2025,2025,6,49,"2025-02-03",58.9513888888889,"2025-12-07","04:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799216161,"Metz Ville - Zoufftgen",null,"Woippy - Accès Sud","Maizières-lès-Metz - Bât Voyageurs",2025,2025,6,50,"2025-02-03",59.2847222222222,"2025-12-08","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799505161,"Metz Ville - Zoufftgen",null,"Uckange - Ano Km 181,3","Ébange - Accès Sud",2025,2025,6,50,"2025-02-03",59.3263888888889,"2025-12-08","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177811161,"Thionville - Mohon",null,"Ébange - Faisceau","Thionville - Bif L3/L7",2025,2025,6,6,"2025-02-03",59.5347222222222,"2025-02-04","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap V1+V2 Thionville. Accès 1L7/2L7 interdit. Avec 5D_UCK-THL_004.",null,"Y",null,45454,"Medium",1.2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806631361,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Chennevières","Conflans-Ste-Honorine - Bif Fin-d'Oise",2025,2025,6,44,"2025-02-03",59.7430555555556,"2025-10-31","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20486026561,"Strasbourg - St Louis",null,"Rixheim - Bif","Habsheim - Bât Voyageurs",2025,2025,6,7,"2025-02-03",59.9513888888889,"2025-02-15","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP908+910",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20003987861,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Le Bourget-Triage - Poste 2",2025,2025,6,11,"2025-02-03",59.9930555555556,"2025-03-16","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786376561,"Thionville - Mohon",null,"Sedan - Garages","Longuyon - Bât Voyageurs",2025,2025,6,49,"2025-02-03",60.2430555555556,"2025-12-05","13:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  SA2025 - Main courante 62 : décalage de -5 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786411361,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Hirson","Tournes",2025,2025,6,49,"2025-02-03",60.4513888888889,"2025-10-17","14:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Attention aux horaires: la section est nommée Tournes Charleville mais la localisation réseau est dans le sens Charleville Tournes : le PR début est donc Charleville et le PR Fin Tournes. Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normal",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16702245861,"Calais - Lille",null,"Strazeele","Hazebrouck - Poste 1",2025,2025,6,46,"2025-02-03",60.6597222222222,"2025-11-15","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786428961,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,6,49,"2025-02-03",60.7013888888889,"2025-12-05","14:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786411361,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Hirson","Tournes",2025,2025,6,49,"2025-02-03",60.9097222222222,"2025-10-17","14:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Attention aux horaires: la section est nommée Tournes Charleville mais la localisation réseau est dans le sens Charleville Tournes : le PR début est donc Charleville et le PR Fin Tournes. Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normal",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786416561,"Liart - Tournes",null,"Rouvroy-l'Échelle","Tournes",2025,2025,6,49,"2025-02-03",61.1180555555556,"2025-10-17","14:54:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786428961,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,6,49,"2025-02-03",61.3263888888889,"2025-12-05","14:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786454561,"Calais - Lille",null,"Lambersart - Bif 4 Maisons","Hazebrouck - Poste 1",2025,2025,6,46,"2025-02-03",61.3680555555556,"2025-11-15","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810522761,"Mantes - Le Havre",null,"Pavilly-Station","Le Havre - Gare Locale",2025,2025,51,50,"2025-02-03",61.6180555555556,"2025-12-12","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Modification suite à évolution du système capacitaire 2025",null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806970961,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,51,46,"2025-02-03",61.8263888888889,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21276429361,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,6,15,"2025-02-04",62.0347222222222,"2025-04-11","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806756761,"Mantes - Le Havre",null,"Achères-Triage - Les Ambassadeurs","Poissy - ITE Talbot Ac O",2025,2025,51,50,"2025-02-04",62.0763888888889,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788849761,"Mantes - Le Havre",null,"Achères-Triage - Jonct V1/V1Bis","Villennes-sur-Seine",2025,2025,51,44,"2025-02-04",62.2847222222222,"2025-10-31","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24150964361,"Paris - Strasbourg",null,"Lérouville - Aig Km 287,6","Lérouville - Aig Km 290,4",2025,2025,6,12,"2025-02-05",62.4930555555556,"2025-03-20","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5C_LER_004.                                                                                                                 ",null,"Y",null,45454,"Medium",3.4,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799371761,"Metz Ville - Zoufftgen",null,"Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2025,2025,6,45,"2025-02-05",62.7013888888889,"2025-11-07","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24151127561,"Paris - Strasbourg",null,"Lérouville - Bât Voyageurs","Lérouville - Aig Km 290,4",2025,2025,6,12,"2025-02-05",62.8680555555556,"2025-03-20","02:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5C_LER_004.",null,"Y",null,45454,"Medium",3.4,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16157739261,"Paris - Strasbourg",null,"Changis-St-Jean - ITE Appel","Château-Thierry - Bât Voyageurs",2025,2025,6,7,"2025-02-07",62.9930555555556,"2025-02-16","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"LFJ (inclue) - CTH (inclue)",null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16875721161,"Paris - Lille",null,"Creil - Bât Voyageurs","Laigneville",2025,2025,6,9,"2025-02-07",63.2013888888889,"2025-02-24","04:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE configuration 1",null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805749761,"Paris - Strasbourg",null,"Chelles-Gournay - Aig côté Gagny","Vaires-Torcy - Aig Côté Chelle",2025,2025,6,6,"2025-02-08",63.4097222222222,"2025-02-09","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV sur ZEP type G 1538 VAI P5. Sel 7482 SSr Chelles-Vaires voie 2R DFV sur ZEP type G 1531 VAI P5. Sel 7151 SSr Chelles-Vaires voie 1R                 ",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16735586961,"Metz Ville - Zoufftgen",null,"Metz-Ville - Aiguille VM","Woippy - Bât Voyageurs",2025,2025,6,48,"2025-02-08",63.4513888888889,"2025-11-30","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 5h10, V1+V2 entre Metz-Ville et Woippy BV. Noveant<-->Woippy possible via MZ DLP avec rebroussement à Metz Sablon.",null,"Y",null,45454,"High",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16611219761,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,6,7,"2025-02-09",63.6597222222222,"2025-02-10","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"pose com 9100 a et b",null,"Y",null,45454,"Medium",1.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813044761,"Paris - Lille",null,"St-Just-en-Chaussée - Bât Voyageurs","Longueau - Poste 1",2025,2025,6,49,"2025-02-10",63.8680555555556,"2025-12-07","05:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16548157761,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,7,14,"2025-02-10",63.9930555555556,"2025-04-03","16:36:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16561068661,"Paris - Hirson",null,"Le Bourget-Triage - Poste 2",0,2025,2025,7,14,"2025-02-10",64.1597222222222,"2025-04-04","16:36:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP G 403 Laon P2",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16736333261,"Paris - Lille",null,0,"Lille-Flandres - Ent/Sort SM",2025,2025,7,48,"2025-02-10",64.3680555555556,"2025-11-29","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16972067461,"Creil - Jeumont",null,"Recquignies","Jeumont - Frontière Fr-Be",2025,2025,7,45,"2025-02-10",64.5763888888889,"2025-11-07","14:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,"Jeumont - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",16971872461,"Creil - Jeumont",null,"Hautmont - Bif des Usines","Les Bons-Pères",2025,2025,7,45,"2025-02-10",64.7847222222222,"2025-11-07","14:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813006361,"Creil - Jeumont",null,"Hautmont - Bif d'Hautmont","Louvroil",2025,2025,7,45,"2025-02-10",64.8263888888889,"2025-11-07","14:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Suite dedt24_00840, main-courante MC25-2 faite le 26/06/2023 par LL, pour passage train TCS.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16947520861,"Paris - Lille",null,"Gannes","Longueau - Poste 1",2025,2025,7,48,"2025-02-10",65.0347222222222,"2025-11-29","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799173961,"Novéant - Nancy",null,"Pagny-sur-Moselle - Poste 3","Novéant - Bif Km 338,9",2025,2025,7,50,"2025-02-10",65.3263888888889,"2025-12-08","03:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799272961,"Novéant - Nancy",null,"Frouard - Bât Voyageurs","Pagny-sur-Moselle - Bât Voyageurs",2025,2025,7,50,"2025-02-10",65.4930555555556,"2025-12-08","03:03:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799370161,"Metz Ville - Zoufftgen",null,"Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2025,2025,7,45,"2025-02-10",65.5347222222222,"2025-11-03","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799374161,"Metz Ville - Zoufftgen",null,"Hagondange - Bât Voyageurs","Hagondange - ITE Sacilor",2025,2025,7,45,"2025-02-10",65.7430555555556,"2025-11-03","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16923068361,"Calais - Lille",null,"Armentières","Hazebrouck - Poste 1",2025,2025,7,16,"2025-02-10",65.9513888888889,"2025-04-19","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786372361,"Lille - Hirson",null,"Lesquin - Bif de Lesquin","Beuvrages",2025,2025,7,47,"2025-02-10",66.1597222222222,"2025-03-08","05:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\" main courante \"\"MC21-0102\"\" acceptée le 10/09/2019 (L LAMBERT)",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16314234361,"Calais - Lille",null,"Hazebrouck - Bif Haute Loge","Ebblinghem",2025,2025,7,44,"2025-02-10",66.2013888888889,"2025-10-31","14:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16942669361,"Lille - Hirson",null,"St-Amand-les-Eaux","Valenciennes - Poste 1",2025,2025,7,10,"2025-02-10",66.4097222222222,"2025-03-08","04:22:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786392161,"Thionville - Mohon",null,"Mohon - Bif L2","Sedan - Accès Garage",2025,2025,7,9,"2025-02-10",66.6597222222222,"2025-02-14","14:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862547961,"Mohon - Charleville-Mézière",null,"Charleville-Mézières - Bât Voyageurs","Givet - Bât Voyageurs",2025,2025,7,44,"2025-02-10",66.8680555555556,"2025-10-31","16:53:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"MàJ du 08-07-2021 suite à demandes DL CA relatives au passage du 838814 nouvelle desserte et compatibilité RP0 CHA16_0009644 et CHA16_0010102  Travaux à réaliser pendant les vacances scolaires (ou hors période de vacances scolaires avec restitution le ME ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17270523361,"Mohon - Charleville-Mézière",null,"Bazoches","Magneux-Courlandon",2025,2025,7,7,"2025-02-10",66.9097222222222,"2025-02-13","16:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"MàJ du 16-08-2023 Par PK DT GE vu avec PM de l'ICA",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813838661,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2025-02-10",67.1180555555556,"2025-12-13","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"caténaire voie 2 en gare de Crepy à rendre à 04h15 pour rendre l´alimentation des VS et permettre la préparation des rames voyageur. Du LUMA 11/12-01-16 au VESA 01/02-04-16 sauf les 26/27-02-16, 04/05-03-16.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862545961,"Conflan-Jarny - Hagondange",null,"Verdun - Bât Voyageurs","Conflans-Jarny - Bif L5 VU/L12",2025,2025,7,44,"2025-02-11",67.3263888888889,"2025-10-31","16:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"mise à jour du 16/08/21 suite concertation ordo régional 2023, accord Infrapole du 08/06/21     Trafic: Fret (notamment vers les fours à Chaud de DUGNY) et TER (12)  Cadrage:  7h15 de jour Du Lundi au vendredi.  Travaux et maintenance a réaliser Pendant l",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16945991261,"Paris - Lille",null,"Longueau - E/S Dépôt","Daours - ITE Roquette",2025,2025,7,8,"2025-02-14",67.5347222222222,"2025-02-17","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16636423561,"Paris - Strasbourg",null,"Hausbergen-Triage - Aiguille 496,9","Hausbergen-Triage - Relais Pairs",2025,2025,7,7,"2025-02-15",67.7430555555556,"2025-02-15","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP439+440+441+366+379+563(voie H) +568(voie I) +569(voie F) +570 (voie G)",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177686361,"Metz - Lérouville",null,"Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2025,2025,7,47,"2025-02-16",67.8263888888889,"2025-11-24","04:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Def 4 voies entre Novéant et Metz",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810442661,"Mantes - Le Havre",null,"Val-de-Reuil - Bât Voyageurs","Oissel - Bif Tourville",2025,2025,4,50,"2025-02-17",68.0347222222222,"2025-05-12","05:17:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"High",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812916561,"Longueau - Boulogne",null,"Longueau - Poste 1","St-Roch (Somme) - Bif et Poste 1",2025,2025,6,46,"2025-02-17",68.2430555555556,"2025-02-22","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786379761,"Thionville - Mohon",null,"Sedan - Garages","Longuyon - Bât Voyageurs",2025,2025,6,49,"2025-02-17",68.2847222222222,"2025-10-31","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786416561,"Liart - Tournes",null,"Rouvroy-l'Échelle","Tournes",2025,2025,6,49,"2025-02-17",68.4930555555556,"2025-02-21","14:54:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805697761,"Paris - Strasbourg",null,"Meaux - Marchandises","Meaux - ITE ZI",2025,2025,8,47,"2025-02-17",68.7013888888889,"2025-10-20","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"CAP pour fenêtre générique classique zone de Meaux uniquement  DFV GPT de type G ZEP 32016 (216+218+222+226+230) Meaux",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16688841761,"St Just en Chaussée - Douai",null,"Épehy",0,2025,2025,8,45,"2025-02-17",68.9097222222222,"2025-11-08","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16754135361,"Racc de Santes - Don-Sainghin",null,"Lille-St-Sauveur - Jonction 24","Lille-St-Sauveur - Bif de Justice",2025,2025,8,40,"2025-02-17",69.0347222222222,"2025-10-03","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799166561,"Metz - Reding",null,"Rémilly - Bât Voyageurs","Metz-Ville - Quai Est",2025,2025,8,50,"2025-02-17",69.2013888888889,"2025-04-05","05:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177810161,"Metz Ville - Zoufftgen",null,"Ébange - Accès Nord","Thionville - Jonctions Nord",2025,2025,8,8,"2025-02-17",69.4097222222222,"2025-02-21","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 6h jour, V2+1L7+E+F+1M+2M+Technicentre accès Sud.",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799366961,"Metz Ville - Zoufftgen",null,"Hagondange - ITE Richemont","Hagondange - ITE Sacilor",2025,2025,8,50,"2025-02-17",69.6180555555556,"2025-12-08","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17000723061,"Paris - Strasbourg",null,"Toul - Poste 1","Toul - PosteA Fontenoy",2025,2025,8,8,"2025-02-17",69.6597222222222,"2025-02-21","15:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 5h05 jour - V1+V2 à Toul - Avec  5C_TL_011 qui reprend les conséquences circulations.",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16315596161,"Strasbourg - St Louis",null,"Rouffach - Évit Voie 1Bis","Merxheim",2025,2025,8,16,"2025-02-17",69.8680555555556,"2025-04-17","00:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP904+906+910",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16963264661,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Paris","Charleville-Mézières - ITE BLAIRON",2025,2025,8,41,"2025-02-17",70.0763888888889,"2025-10-10","15:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16995659861,"Thionville - Mohon",null,"Mohon - Bif L2","Sedan - Accès Garage",2025,2025,8,14,"2025-02-17",70.1597222222222,"2025-04-04","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16995659861,"Thionville - Mohon",null,"Mohon - Bif L2","Sedan - Accès Garage",2025,2025,8,14,"2025-02-17",70.3680555555556,"2025-02-21","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805552161,"Paris - Strasbourg",null,"Esbly","Meaux - Aig Km 41,7-Év",2025,2025,8,42,"2025-02-18",70.5763888888889,"2025-10-18","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Fenêtre générique sur 1BIS de Villenoy",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799251561,"Metz Ville - Zoufftgen",null,"Woippy - Accès Nord","Hagondange - ITE Richemont",2025,2025,8,50,"2025-02-18",70.7847222222222,"2025-12-12","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                           ",null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805743761,"Paris - Strasbourg",null,"Vaires-Torcy - Carré 129","Vaires-Torcy - Bât Voyageurs",2025,2025,8,8,"2025-02-19",70.9930555555556,"2025-02-21","11:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"1R : ZEP 1339,1343,1346 VAI (aig. 3317ac,3323,3329bd,3332) (aig. 3317b,3319)         ",null,"Y",null,45454,"Medium","3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805741161,"Paris - Strasbourg",null,"Vaires-Torcy - Aig Côté Chelle","Vaires-Torcy - Dépôt",2025,2025,8,8,"2025-02-19",71.0347222222222,"2025-02-19","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"1T2T : ZEP 1536 CSG (aig. 3140)       ",null,"Y",null,45454,"Medium",3,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16548251661,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,8,9,"2025-02-21",71.2430555555556,"2025-03-02","22:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16161510161,"Paris - Strasbourg",null,"Trilport - Bif de Germigny","La Ferté-sous-Jouarre - Aig Km 63,6-Év",2025,2025,1,48,"2025-02-24",71.4513888888889,"2025-12-01","04:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"17/10/2023 (DAC) : Vibration suite main courante n° 104/2025. 23/11/2022 (DAC) : Création de fenêtre générique élargie pour maintenance suite concertation 2025. Trilport - LFJ (exclue) Train ouvrant : 56622 (voir Variante correspondante) Train fermant : 5",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16829777661,"Paris - Lille",null,"Achiet","Arras - Bif Sud",2025,2025,9,14,"2025-02-24",71.7013888888889,"2025-04-01","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16947076961,"Paris - Lille",null,"Boves","Longueau - FSC Gp J / Arra",2025,2025,9,45,"2025-02-24",71.7430555555556,"2025-11-08","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787648061,"Paris - Strasbourg",null,"Bar-le-Duc - Bât Voyageurs","Lérouville - Aig Km 290,4",2025,2025,9,48,"2025-02-24",71.9513888888889,"2025-11-28","14:57:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799343761,"Toul - Culmont Chalindrey",null,"Culmont-Chalindrey - Bif Chaudenay","Neufchâteau - Bât Voyageurs",2025,2025,9,50,"2025-02-24",72.1597222222222,"2025-12-11","16:48:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 : modification des horaires suite à la concertation sur les évolutions du système capacitaire",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799189761,"Remilly - Forbach",null,"Béning - Acc E Faisceau","Forbach - Bât Voyageurs",2025,2025,9,47,"2025-02-24",72.3680555555556,"2025-11-21","14:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 : Main courante 38 (vibration de -1 min des horaires)",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799287961,"Remilly - Forbach",null,"Rémilly - Bât Voyageurs","Béning - Acc E Faisceau",2025,2025,9,50,"2025-02-24",72.4097222222222,"2025-12-13","05:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Typologie schématisée passée de \"\"Autre\"\" à \"\"Simultanée\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177809161,"Metz Ville - Zoufftgen",null,"Ébange - Accès Nord","Thionville - Jonctions Nord",2025,2025,9,9,"2025-02-24",72.5763888888889,"2025-02-28","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null," Cap 6h jour, V1+V2+D+E+F+1M+2M+Technicentre accès Sud.",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16593980461,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Hirson","Tournes",2025,2025,9,44,"2025-02-24",72.8680555555556,"2025-10-31","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP CHARLEVILLE - LIART voie 2 + Sel 14+16 SSR ROUVROY L'ECHELLE CHARLEVILLE  VOIE 2",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16593973461,"Liart - Tournes",null,0,"Tournes",2025,2025,9,44,"2025-02-24",73.0763888888889,"2025-10-31","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP CHARLEVILLE - LIART voie 2 + Sel 14+16 SSR ROUVROY L'ECHELLE CHARLEVILLE  VOIE 2     ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16923036261,"Calais - Lille",null,"Strazeele","Hazebrouck - Poste 1",2025,2025,9,14,"2025-02-24",73.1180555555556,"2025-04-05","05:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16593976061,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Hirson","Tournes",2025,2025,9,44,"2025-02-24",73.3263888888889,"2025-10-31","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP LIART - CHARLEVILLE voie 1 + Consignation des S.el 15+17+19 SSR ROUVROY L'ECHELLE - CHARLEVILLE V1  + Consignation longue durée Sel 105 du Ssr Rouvroy L'échelle - Charleville en gare de Tournes pour dépotage TTx",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16994169261,"Hirson - Liart",null,"Hirson - Bât Voyageurs","Aubenton",2025,2025,9,44,"2025-02-24",73.5347222222222,"2025-03-28","16:56:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16923082061,"Calais - Lille",null,"Armentières","Hazebrouck - Poste 1",2025,2025,9,14,"2025-02-24",73.7430555555556,"2025-04-05","05:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16992757861,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,9,44,"2025-02-24",73.9097222222222,"2025-10-31","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16593973461,"Liart - Tournes",null,0,"Tournes",2025,2025,9,44,"2025-02-24",74.0347222222222,"2025-03-07","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP CHARLEVILLE - LIART voie 2 + Sel 14+16 SSR ROUVROY L'ECHELLE CHARLEVILLE  VOIE 2     ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812884761,"Longueau - Boulogne",null,"Amiens - Bât Voyageurs","Dreuil-lès-Amiens",2025,2025,6,46,"2025-02-25",74.2430555555556,"2025-11-01","04:24:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16316144861,"Strasbourg - St Louis",null,"Raedersheim","Staffelfelden",2025,2025,9,16,"2025-02-26",74.4513888888889,"2025-04-19","05:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP923+925+927+929",null,"Y",null,45454,"Medium","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16316371861,"Strasbourg - St Louis",null,"Herrlisheim-près-Colmar","Rouffach - Évit Voie 2Bis",2025,2025,9,9,"2025-02-27",74.4930555555556,"2025-02-28","00:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP903+905+909",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16678863461,"Paris - Hirson",null,"Paris-La Chapelle - Heurtoir","Le Bourget-Triage - Poste 1",2025,2025,9,37,"2025-02-28",74.7013888888889,"2025-09-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177980361,"Longuyon - Onville",null,"Conflans-Jarny - Bif L12/L5 D V","Pagny-sur-Moselle - Poste 3",2025,2025,9,10,"2025-03-01",74.9097222222222,"2025-03-10","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf V1+V2 entre Conflans (exclu) et Pagny/Moselle. Avec 5D_LER-NEN_0?.",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16617341961,"Strasbourg - St Louis",null,"Mulhouse-Ville - Aig Km 110","Habsheim - Bât Voyageurs",2025,2025,9,19,"2025-03-01",75.1180555555556,"2025-05-11","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16617280861,"Strasbourg - St Louis",null,"Lutterbach (Haut-Rhin) - Bif","Rixheim - Bif",2025,2025,9,19,"2025-03-01",75.2013888888889,"2025-05-11","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Propagation du SRV 2076 de la ligne 115000",null,"Y",null,45454,"High",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16616997061,"Strasbourg - St Louis",null,"Wittelsheim - Bât Voyageurs","Lutterbach (Haut-Rhin) - Bât Voyageurs",2025,2025,9,17,"2025-03-02",75.4097222222222,"2025-04-28","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16617267661,"Lutterbach - Rixeim (Mulhouse)",null,"Lutterbach (Haut-Rhin) - Bif","Rixheim - Bif",2025,2025,9,17,"2025-03-02",75.6180555555556,"2025-04-28","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803944761,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,2,50,"2025-03-03",75.8263888888889,"2025-06-14","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862287161,"Pontoise - Serqueux",null,"Gisors","Serqueux",2025,2025,3,49,"2025-03-03",75.8680555555556,"2025-03-16","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"04/10/13 SBE : adaptation de la générique suite aux commandes Sillons TER HN (perte de 30 min sur la générique) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786432561,"Lille - Hirson",null,"Valenciennes - Bât Voyageurs","Berlaimont - Bât Voyageurs",2025,2025,9,44,"2025-03-03",76.0763888888889,"2025-11-02","15:14:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16753086161,"Lille - Baisieux",null,0,"Lille-St-Sauveur - Bif Ateliers E",2025,2025,10,41,"2025-03-03",76.2847222222222,"2025-10-11","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16753004561,"Paris - Lille",null,0,"Lille-Flandres - Ent/Sort SM",2025,2025,10,41,"2025-03-03",76.4930555555556,"2025-10-11","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16946910961,"Creil - Jeumont",null,"Compiègne - Garage Pair","Tergnier - Bât Voyageurs",2025,2025,10,10,"2025-03-03",76.5763888888889,"2025-03-08","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16504537261,"Longuyon - Mont St Martin (XB)",null,"Longuyon - Bât Voyageurs","Mont-St-Martin - Frontière Fr-Be",2025,2025,10,10,"2025-03-03",76.7847222222222,"2025-03-06","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 4h30 jour, V1+V2 entre Longuyon et Longwy.",null,"Y",null,45454,"Medium","1,2,3,4",null,null,"Mont-St-Martin - Frontière Fr-Be",null,null,"Planned",0]
[null,"SNCF-R",15799245161,"Toul - Culmont Chalindrey",null,"Culmont-Chalindrey - Bif Chaudenay",0,2025,2025,10,44,"2025-03-03",76.9930555555556,"2025-10-31","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 5h30. V1+V2+V1R+V2R entre Chalindrey-P2 et Chalindrey-BF. Suppression TER et décalage frets.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16148971761,"Paris - Strasbourg",null,"Stephansfeld","Mundolsheim",2025,2025,10,11,"2025-03-03",77.2013888888889,"2025-03-12","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP832+827+833+835+816+818+820+824+826+830",null,"Y",null,45454,"Medium",1.2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16721874961,"Strasbourg - St Louis",null,"Mulhouse-Ville - Aig Km 110","Rixheim - Bif",2025,2025,10,12,"2025-03-03",77.2430555555556,"2025-03-22","03:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19902999161,"Paris - Lille",null,"Goussainville - Bât Voyageurs","Les Noues",2025,2025,10,50,"2025-03-03",77.4513888888889,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES  S1_2_4",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19902847961,"Paris - Lille",null,"Goussainville - Bât Voyageurs","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,10,50,"2025-03-03",77.6180555555556,"2025-12-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES  S1-2-4",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806754161,"Mantes - Le Havre",null,"Sartrouville - Garage","Villennes-sur-Seine",2025,2025,10,45,"2025-03-04",77.9097222222222,"2025-11-08","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806753161,"Mantes - Le Havre",null,"Sartrouville - Bât Voyageurs","Villennes-sur-Seine",2025,2025,10,45,"2025-03-04",77.9513888888889,"2025-11-08","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16679084261,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Le Bourget-Triage - Poste 2",2025,2025,9,37,"2025-03-07",78.1597222222222,"2025-03-10","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16679795861,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,10,42,"2025-03-07",78.3680555555556,"2025-10-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16679795861,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,10,42,"2025-03-07",78.5763888888889,"2025-03-10","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16649315061,"Paris - Hirson",null,"Paris-La Chapelle - Heurtoir","Le Bourget-Triage - Poste 1",2025,2025,10,11,"2025-03-07",78.6180555555556,"2025-03-10","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE CDG reconstruction voie DA  + Régénération Cat.   ",null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21277752861,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,10,10,"2025-03-08",78.9513888888889,"2025-03-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16600708561,"Paris - Strasbourg",null,"Épernay - Cumières Triage","Épernay - Bif L1/22 5",2025,2025,10,10,"2025-03-09",79.0763888888889,"2025-03-10","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"voie quater zep 537 + SEL 231 du sous secteur Epernay GARE  voie M: zep 541 + SEL 241 du sous secteur Epernay GARE   ",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19418386261,"Argenteuil - Le Havre",null,"Paris-Batignolles - Dépôt-Grill","Paris-Batignolles - Poste 5",2025,2025,10,20,"2025-03-09",79.2847222222222,"2025-05-12","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19418359861,"Mantes - Le Havre",null,"Paris St Lazare - C374 à C774","Asnières-sur-Seine - Bât Voyageurs",2025,2025,10,10,"2025-03-09",79.3263888888889,"2025-03-09","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806708761,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,3,50,"2025-03-10",79.5347222222222,"2025-11-15","04:39:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante n°120 : pour passage du 13164",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805697761,"Paris - Strasbourg",null,"Meaux - Marchandises","Meaux - ITE ZI",2025,2025,8,47,"2025-03-10",79.7430555555556,"2025-05-05","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"CAP pour fenêtre générique classique zone de Meaux uniquement  DFV GPT de type G ZEP 32016 (216+218+222+226+230) Meaux",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23701673561,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,11,13,"2025-03-10",79.9513888888889,"2025-03-29","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"la caténaire doit être rendue à 04h45 pour la préparation du matériel ligne K",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23701715361,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,11,13,"2025-03-10",80.0347222222222,"2025-03-29","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"la caténaire doit être rendue à 04h45 pour la préparation du matériel ligne K",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16946934361,"Creil - Jeumont",null,"Viry-Noureuil","Tergnier - Voie F2",2025,2025,11,11,"2025-03-10",80.2430555555556,"2025-03-15","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16123484161,"Metz - Lérouville",null,"Lérouville - Bât Voyageurs","Onville - Rac Lérouville",2025,2025,11,15,"2025-03-10",80.4513888888889,"2025-04-12","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 7h30 nuit entre Lérouville et Onville. Détournements frets Nord-Sud via Pont-à-Mousson.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16801613461,"Metz Ville - Zoufftgen",null,"Uckange - Poste 2","Ébange - Faisceau",2025,2025,11,11,"2025-03-10",80.6597222222222,"2025-03-12","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 6h jour V1B au niveau d'Uckange P1. Accès Ebange Sud interdit.",null,"Y",null,45454,"Medium","1,2,3",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177983361,"Thionville - Mohon",null,"Longuyon - Bif","Pierrepont",2025,2025,11,11,"2025-03-10",80.7013888888889,"2025-03-13","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5C_LGN_001 qui reprend les conséquences circulations.  Alternatif rompu pendant 4h30",null,"Y",null,45454,"Medium","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19905488061,"Pontoise - Serqueux",null,"Ermont-Eaubonne - Bât Voyageurs","Ermont-Eaubonne - Garage Pair",2025,2025,11,39,"2025-03-10",80.9097222222222,"2025-09-27","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15802129861,"Pontoise - Serqueux",null,0,"La Barre-Ormesson",2025,2025,11,39,"2025-03-10",81.1180555555556,"2025-09-27","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19905545161,"Pontoise - Serqueux",null,"Champ-de-Courses-d'Enghien","Ermont-Eaubonne - Garage Pair",2025,2025,11,39,"2025-03-10",81.3680555555556,"2025-09-27","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19905813761,"Pontoise - Serqueux",null,"St-Ouen-l'Aumône",0,2025,2025,11,39,"2025-03-10",81.4097222222222,"2025-09-27","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23701661161,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,11,13,"2025-03-10",81.6180555555556,"2025-03-29","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"la caténaire doit être rendue à 04h45 pour la préparation du matériel ligne K",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805190161,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,51,50,"2025-03-10",81.8263888888889,"2025-11-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sauf ZEP 789 pour accès T4  + ZEP 252 Pantin G commandée par CHL pour aig 2547b        ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16123506861,"Metz - Lérouville",null,"Lérouville - Bât Voyageurs","Onville - Rac Lérouville",2025,2025,11,11,"2025-03-14",82.0347222222222,"2025-03-16","10:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"OCP 36h entre Lérouville et Onville. Détournements et décalage frets. Suppression TER.",null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810469761,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,51,50,"2025-03-14",82.0763888888889,"2025-04-26","04:34:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16317650261,"Strasbourg - St Louis",null,"Raedersheim","Staffelfelden",2025,2025,11,11,"2025-03-15",82.2847222222222,"2025-03-16","05:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP923+925+927+929",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16895991961,"Douai - Valenciennes",null,"Valenciennes - Poste 1","Valenciennes - Garage StSaulve",2025,2025,11,12,"2025-03-15",82.4930555555556,"2025-03-17","01:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"+ Voies G1, G2, MG à Beuvrages + voie AB (desserte ZI St Saulve au P2) + Têtes de faisceau VS 1 à 16 P2 St Saulve",null,"Y",null,45454,"Medium","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799512761,"Metz Ville - Zoufftgen",null,"Uckange - Ano Km 181,3","Ébange - Accès Sud",2025,2025,11,39,"2025-03-16",82.6597222222222,"2025-09-29","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799297361,"Metz Ville - Zoufftgen",null,"Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2025,2025,11,39,"2025-03-16",82.7847222222222,"2025-09-29","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action du secteur CCR de Thionville dans le noir. 177 000 de THL jusqu'à CREUTZWALD. 178 000 THL jusqu'à APACH. 180 000 côté Lux THL jusqu'à BETTEMBOURG. 180 000 côté Metz THL jusqu'à HAGONDANGE. 204 000 THL jusqu'à LONGUYON.",null,"Y",null,45454,"Medium",7,null,null,"Zoufftgen (IE) - Frontière Fr-Lu",null,null,"Planned",0]
[null,"SNCF-R",15813741061,"Paris - Hirson",null,"Vauxaillon - Km 117,291","La Neuville-sous-Laon",2025,2025,4,45,"2025-03-17",82.9930555555556,"2025-03-22","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786428961,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,6,49,"2025-03-17",83.2013888888889,"2025-10-31","14:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788931361,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Blesme-Haussignemont - Bât Voyageurs",2025,2025,11,44,"2025-03-17",83.4097222222222,"2025-04-04","14:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788931361,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Blesme-Haussignemont - Bât Voyageurs",2025,2025,11,44,"2025-03-17",83.4513888888889,"2025-10-31","14:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18424996361,"Paris - Strasbourg",null,"Changis-St-Jean - ITE Appel","Mézy - Poste U",2025,2025,12,42,"2025-03-17",83.6597222222222,"2025-10-20","04:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"LFJ (inclue) - CTH (inclue)  Voie 5 de CTH libre pour TN",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16752176761,"Lille - Baisieux",null,0,"Lille-Flandres - Ent/Sort SM",2025,2025,12,12,"2025-03-17",83.7847222222222,"2025-03-18","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16576391861,"Paris - Strasbourg",null,"Châlons-en-Champagne - Accès Triage","Châlons-en-Champagne - Poste 1",2025,2025,12,18,"2025-03-17",84.1180555555556,"2025-05-02","16:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP 1+3+5 V1 / ZEP 79 V1bis / ZEP 238 V2bis + Sous -Secteurs Matougues - Chalons V1 et SEL 321 et 322 su Sous Secteurs Chalons Voie B et dépôt",null,"Y",null,45454,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16576586761,"Paris - Strasbourg",null,"Épernay - Poste 1","Châlons-en-Champagne - Poste 1",2025,2025,12,21,"2025-03-17",84.1597222222222,"2025-04-25","16:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16344163361,"Paris - Strasbourg",null,"Commercy","Toul - Poste 1",2025,2025,12,12,"2025-03-17",84.3680555555556,"2025-03-21","15:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf V1+V2 entre Pagny/Meuse et Toul. Avec 5D_TL-FR_005, 5D_NCH-TL_002 et 5C_TL_008.",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16178014361,"Metz Ville - Zoufftgen",null,"Uckange - Poste 2","Ébange - Accès Sud",2025,2025,12,12,"2025-03-17",84.5763888888889,"2025-03-17","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5F_UCK-THL_007 + 5F_UCK-THL_008 ",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16157074561,"Paris - Strasbourg",null,"Vendenheim - Voies 3/5","Vendenheim - Voies 3/5",2025,2025,12,46,"2025-03-17",84.7847222222222,"2025-11-15","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP825",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803742161,"Paris - Strasbourg",null,"Saverne","Vendenheim",2025,2025,12,46,"2025-03-17",84.8263888888889,"2025-11-15","04:57:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 : modification des horaires suite à demande de TER Alsace lors de la concertation sur les évolutions du système capacitaire",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16956704361,"Hirson - Liart",null,"Hirson - Bât Voyageurs","Aubenton",2025,2025,12,44,"2025-03-17",85.0763888888889,"2025-10-31","14:07:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16972408761,"Lille - Hirson",null,"Féron-Glageon","Anor",2025,2025,12,44,"2025-03-17",85.2847222222222,"2025-10-31","15:18:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine A",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805758161,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Aig Km 21,0",2025,2025,51,50,"2025-03-17",85.4930555555556,"2025-03-29","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805760161,"Paris - Strasbourg",null,"Gagny - Aig V2Bis/V2Ter","Vaires-Torcy - Faisceau V",2025,2025,51,50,"2025-03-17",85.5347222222222,"2025-03-29","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL bif Gagny prise",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813843461,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2025-03-17",85.7430555555556,"2025-03-22","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"caténaire voie 2 en gare de Crepy à rendre à 04h15 pour rendre l´alimentation des VS et permettre la préparation des rames voyageur. Du LUMA 11/12-01-16 au VESA 01/02-04-16 sauf les 26/27-02-16, 04/05-03-16. ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813807861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2025-03-17",85.9513888888889,"2025-03-22","05:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16318181561,"Strasbourg - St Louis",null,"Raedersheim","Staffelfelden",2025,2025,12,12,"2025-03-18",86.1597222222222,"2025-03-18","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP923+925+927+929",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16791962561,"Strasbourg - St Louis",null,"St-Louis (Haut-Rhin) - Aiguille 12","St-Louis (Haut-Rhin) - Aiguille 23",2025,2025,12,19,"2025-03-19",86.2013888888889,"2025-05-07","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP967 depuis garage franc AdV14",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16272386861,"Ceinture de Metz",null,"Metz-Sablon - Bif L3/L11",0,2025,2025,12,12,"2025-03-22",86.4513888888889,"2025-03-23","20:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5C_MZ_020 qui reprend les conséquences circulations.",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16657283161,"Douai - Valenciennes",null,0,0,2025,2025,12,40,"2025-03-22",86.6597222222222,"2025-10-05","06:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Nuits Sa/Di",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16657450761,"Douai - Valenciennes",null,0,0,2025,2025,12,40,"2025-03-23",86.8680555555556,"2025-10-06","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Nuits Di/Lu",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16657461761,"No encontrado",null,"St-Amand-les-Eaux","Valenciennes - Garage StSaulve",2025,2025,12,40,"2025-03-23",86.9097222222222,"2025-10-06","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Nuits Di/Lu  + Caténaires accès voies 1 à 7 St Saulve PA et P2",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16259781961,"Metz Ville - Zoufftgen",null,"Uckange - Poste 1","Ébange - Aig VL90",2025,2025,4,47,"2025-03-24",87.1180555555556,"2025-06-16","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)   ",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812940361,"Longueau - Boulogne",null,"St-Roch (Somme) - Bif et Poste 1","Abbeville - SBAPR303",2025,2025,6,50,"2025-03-24",87.3263888888889,"2025-03-29","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16980544861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 2",0,2025,2025,13,45,"2025-03-24",87.5347222222222,"2025-11-08","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16712765161,"Calais - Boulogne",null,"non trouvé",0,2025,2025,13,16,"2025-03-24",87.6180555555556,"2025-04-19","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Travaux connexes SR Domaine B S S13 à 16",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16984704561,"Creil - Jeumont",null,"Tergnier - Bât Voyageurs","Tergnier - Triage",2025,2025,13,45,"2025-03-24",87.8263888888889,"2025-11-08","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16712708461,"Calais - Boulogne",null,0,0,2025,2025,13,16,"2025-03-24",88.0347222222222,"2025-04-19","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Travaux connexes SR Domaine B S S13 à 16",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17007325761,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Épernay - Aiguille 139,3",2025,2025,13,13,"2025-03-24",88.2430555555556,"2025-03-27","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16178017161,"Metz Ville - Zoufftgen",null,"Uckange - Ano Km 181,3","Ébange - Accès Sud",2025,2025,13,13,"2025-03-24",88.2847222222222,"2025-03-24","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5F_UCK-THL_005 + 5F_UCK-THL_006 + 5C_THL_003 ",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16157126361,"Paris - Strasbourg",null,"Vendenheim - Voies 3/5","Hausbergen-Triage - FSC Réception",2025,2025,13,13,"2025-03-24",88.4930555555556,"2025-03-28","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP830+834+836+825+829+831+839+841",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16995803961,"Thionville - Mohon",null,"Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2025,2025,13,13,"2025-03-24",88.7013888888889,"2025-03-28","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16995810961,"Thionville - Mohon",null,"Sedan - Bât Voyageurs","Longuyon - Bât Voyageurs",2025,2025,13,13,"2025-03-24",88.8263888888889,"2025-03-28","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813845861,"Paris - Hirson",null,"Crépy-en-Valois","Vierzy - Aig Km 94,1",2025,2025,51,50,"2025-03-24",88.9930555555556,"2025-11-08","05:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16259673861,"Metz Ville - Zoufftgen",null,"Uckange - Poste 1","Ébange - Jonction Nord",2025,2025,4,47,"2025-03-25",89.2013888888889,"2025-03-28","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis  Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                               ",null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16695802861,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Côté Rouen","Vernon (Eure) - Poste 1",2025,2025,13,15,"2025-03-28",89.4097222222222,"2025-04-07","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19949965661,"Paris - Strasbourg",null,"Vendenheim - Voies 3/5","Vendenheim - Jonct V1B/VD",2025,2025,13,15,"2025-03-28",89.6180555555556,"2025-04-12","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP824+826+830",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16617159961,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Le Bourget-Triage - Poste 1",2025,2025,13,14,"2025-03-28",89.6597222222222,"2025-03-31","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE PONT 1",null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16601169561,"Paris - Strasbourg",null,"Épernay - Poste 1","Épernay - Bif L1/22 5",2025,2025,13,17,"2025-03-29",89.8680555555556,"2025-04-27","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"voie 1: zep 511 + SEL 35 bis du sous secteur Mardeuil Epernay  Voie 1  ",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20906384761,"Paris - Lille",null,"Stade-de-France-St-Denis","St-Denis - Pk 6,8",2025,2025,13,29,"2025-03-29",90.1597222222222,"2025-07-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE PONT1",null,"Y",null,45454,"High","1,2,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16157374461,"Paris - Strasbourg",null,"Vendenheim - Jonct V1B/VD","Strasbourg-Ville - Voies 35/36",2025,2025,13,14,"2025-03-29",90.3263888888889,"2025-04-06","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP593+837",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16157447461,"Paris - Strasbourg",null,"Vendenheim - Voies 3/5","Mundolsheim",2025,2025,13,14,"2025-03-29",90.3680555555556,"2025-04-06","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP832+827+833+835",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799262161,"Metz Ville - Zoufftgen",null,"Woippy - Accès Nord","Hagondange - Faisceau",2025,2025,13,13,"2025-03-30",90.5763888888889,"2025-03-30","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf V1+V2B entre Woippy AN et Hagondange",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803909161,"Paris - Lille",null,"Goussainville - Bât Voyageurs","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,2,50,"2025-03-31",90.7847222222222,"2025-11-29","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805693761,"Paris - Strasbourg",null,"Lagny-Thorigny","Meaux - ITE ZI",2025,2025,8,47,"2025-03-31",90.9930555555556,"2025-04-05","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Ajout 2 semaines pour 17166 mise en cohérence domaines S9 S11",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805697761,"Paris - Strasbourg",null,"Meaux - Marchandises","Meaux - ITE ZI",2025,2025,8,47,"2025-03-31",91.0347222222222,"2025-04-05","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"CAP pour fenêtre générique classique zone de Meaux uniquement  DFV GPT de type G ZEP 32016 (216+218+222+226+230) Meaux",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799252361,"Metz Ville - Zoufftgen",null,"Woippy - Accès Nord","Hagondange - ITE Richemont",2025,2025,8,50,"2025-03-31",91.2430555555556,"2025-03-31","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)                                   ",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16677218561,"Paris - Lille",null,"Boves","Longueau - Direction Lille",2025,2025,14,48,"2025-03-31",91.4930555555556,"2025-11-29","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16677265161,"Paris - Lille",null,"Longueau - Bif de Camon","Achiet",2025,2025,14,48,"2025-03-31",91.7013888888889,"2025-11-29","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16901174561,"Paris - Lille",null,"Creil - JCT Sud","Creil - Acc/Sort Nord",2025,2025,14,48,"2025-03-31",91.7430555555556,"2025-11-29","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16985291761,"Paris - Lille",null,"Boves","Longueau - Bât Voyageurs",2025,2025,14,14,"2025-03-31",91.9513888888889,"2025-04-05","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16541882061,"Paris - Lille",null,"Longueau - Poste 1","Longueau - Tiroir",2025,2025,14,18,"2025-03-31",92.1597222222222,"2025-05-03","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16594016861,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Mohon - Bât Voyageurs",2025,2025,14,44,"2025-03-31",92.3680555555556,"2025-07-11","06:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787656461,"Paris - Strasbourg",null,"Bar-le-Duc - Bât Voyageurs","Lérouville - Aig Km 287,6",2025,2025,14,47,"2025-03-31",92.5763888888889,"2025-11-21","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf V1+V2 entre Bar-Le-Duc (inclus) et Ernecout-Loxeville (inclus). Avec 5D_BIM-BLD_002.                                                                                                                         ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799280961,"Ceinture de Metz",null,"Metz-Sablon - Bif L3/L11","Woippy - PN 1",2025,2025,14,38,"2025-03-31",92.6597222222222,"2025-09-20","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803930961,"Paris - Lille",null,"Pierrefitte-Stains - Bât Voyageurs","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,14,48,"2025-03-31",92.8680555555556,"2025-11-29","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806705561,"Mantes - Le Havre",null,"La Garenne-Colombes - C Violet 123","Houilles-Carrières-sur-Seine - Bifurcation de Bezons",2025,2025,51,50,"2025-03-31",93.0763888888889,"2025-05-24","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",25075918361,"Creil - Jeumont",null,"Creil - JCT Nord","Longueil-Ste-Marie - Voie 4",2025,2025,51,50,"2025-03-31",93.1180555555556,"2025-11-29","04:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805766161,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2025,2025,14,14,"2025-04-01",93.3263888888889,"2025-04-02","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"aig 2905a 2905b 2B1+2TER",null,"Y",null,45454,"Medium","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806699161,"Mantes - Le Havre",null,"Asnières-sur-Seine - Bât Voyageurs","Sartrouville - Garage",2025,2025,51,45,"2025-04-01",93.5347222222222,"2025-05-10","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16992757861,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,9,44,"2025-04-02",93.7013888888889,"2025-04-03","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16593980461,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Hirson","Tournes",2025,2025,9,44,"2025-04-02",93.8263888888889,"2025-04-03","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP CHARLEVILLE - LIART voie 2 + Sel 14+16 SSR ROUVROY L'ECHELLE CHARLEVILLE  VOIE 2",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16979420261,"Paris - Strasbourg",null,"Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2025,2025,14,17,"2025-04-04",94.0347222222222,"2025-04-21","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16576711561,"Paris - Strasbourg",null,"Châlons-en-Champagne - Accès Triage","Châlons-en-Champagne - Poste 1",2025,2025,14,15,"2025-04-04",94.2430555555556,"2025-04-07","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP 1+3+5 V1 / ZEP 79 V1bis / ZEP 238 V2bis + Sous -Secteurs Matougues - Chalons V1 et SEL 321 et 322 su Sous Secteurs Chalons Voie B et dépôt",null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16526658861,"Paris - Strasbourg",null,"Toul - Poste 1","Frouard - Accès Nord",2025,2025,14,45,"2025-04-05",94.4513888888889,"2025-11-10","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Fenêtre déformée 6h20 V1+V2 entre Toul et Frouard.",null,"Y",null,45454,"High",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799178961,"Novéant - Nancy",null,"Pagny-sur-Moselle - Poste 3","Novéant - Bif Km 338,9",2025,2025,14,46,"2025-04-05",94.4930555555556,"2025-11-16","06:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Fenêtre déformée 6h40 sur les 2 voies. Avec 5D_FR-PMO_006.",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177963161,"Ceinture de Metz",null,"Metz-Sablon - Jonct V2/V2R","Metz-Sablon - FSC Montigny",2025,2025,14,14,"2025-04-05",94.7013888888889,"2025-04-06","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 8h nuit, 1R+2R+FRE+FM, zone Metz-Sablon  1R/2R interdites coté Rémilly FRE+FM Metz interdits  Accès Metz-March interdit        ",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19419261561,"Argenteuil - Le Havre",null,"Paris-Batignolles - Dépôt-Grill","Paris-Batignolles - Poste 5",2025,2025,14,15,"2025-04-05",94.9097222222222,"2025-04-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799176961,"Novéant - Nancy",null,"Pagny-sur-Moselle - Poste 3","Novéant - Bif Km 338,9",2025,2025,14,46,"2025-04-06",94.9930555555556,"2025-11-17","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Fenêtre déformée 5h00 sur les 2 voies. Avec 5D_FR-PMO_001.",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16527208661,"Paris - Strasbourg",null,"Frouard - Bât Voyageurs","Nancy-Ville - Bât Voyageurs",2025,2025,14,43,"2025-04-06",95.2013888888889,"2025-10-27","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Fenêtre déformées entre Frouard BV et Réding pour la Maintenance. Détournements frets via RDG-RMI-MZS.",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810466761,"Mantes - Le Havre",null,"Bif de Darnétal - Rac 2","Maromme - Sor Évit Impair",2025,2025,1,50,"2025-04-07",95.4097222222222,"2025-04-28","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16576506961,"Paris - Strasbourg",null,"Épernay - Rac Côté Oiry","Châlons-en-Champagne - Accès Triage",2025,2025,12,21,"2025-04-07",95.6180555555556,"2025-04-30","16:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP 1+3+5 V1 / ZEP 79 V1bis / ZEP 238 V2bis + Sous -Secteurs Matougues - Chalons V1 et SEL 321 et 322 su Sous Secteurs Chalons Voie B et dépôt",null,"Y",null,45454,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805739161,"Paris - Strasbourg",null,"Vaires-Torcy - Aig Côté Chelle","Vaires-Torcy - Poste 4",2025,2025,15,43,"2025-04-07",95.8263888888889,"2025-10-26","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP 501 à 528 Poste 3 + 490 Poste F2 + 1344+1539 Poste 5 Sel 7155+7157+7159 SSr Chelles-Vaires voie 1R Sel 7484+7486+7488 SSr Chelles-Vaires voie 2R SSr Vaires Faisceau V Sel 122 SSr Vaires triage impair ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805739161,"Paris - Strasbourg",null,"Vaires-Torcy - Aig Côté Chelle","Vaires-Torcy - Poste 4",2025,2025,15,43,"2025-04-07",95.8680555555556,"2025-04-09","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP 501 à 528 Poste 3 + 490 Poste F2 + 1344+1539 Poste 5 Sel 7155+7157+7159 SSr Chelles-Vaires voie 1R Sel 7484+7486+7488 SSr Chelles-Vaires voie 2R SSr Vaires Faisceau V Sel 122 SSr Vaires triage impair ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16985305761,"Paris - Lille",null,"Longueau - E/S Tergnier/Do","Daours - ITE Roquette",2025,2025,15,15,"2025-04-07",96.0763888888889,"2025-04-12","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18951633361,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Blesme-Haussignemont - Bât Voyageurs",2025,2025,15,16,"2025-04-07",96.2847222222222,"2025-04-18","16:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16648281961,"Strasbourg - St Louis",null,"St-Louis (Haut-Rhin) - Aiguille 12","St-Louis (Haut-Rhin) - Aiguille 23",2025,2025,15,36,"2025-04-07",96.5347222222222,"2025-09-06","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16648182661,"Strasbourg - St Louis",null,"St-Louis (Haut-Rhin) - Aiguille 12","St-Louis (Haut-Rhin) - Aiguille 23",2025,2025,15,36,"2025-04-07",96.5763888888889,"2025-09-06","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803921561,"Paris - Lille",null,"Pierrefitte-Stains - Bif Sud","Villiers-le-Bel-Gonesse - V 1M Côté Creil",2025,2025,15,49,"2025-04-07",96.7847222222222,"2025-12-01","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803957761,"Paris - Lille",null,"Paris-Nord - Portique Landy","Pierrefitte-Stains - Bif Sud",2025,2025,15,49,"2025-04-07",96.9930555555556,"2025-12-01","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20520528661,"Mohon - Charleville-Mézière",null,"Charleville-Mézières - Bât Voyageurs","Nouzonville",2025,2025,15,16,"2025-04-07",97.2013888888889,"2025-04-20","15:15:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,"zep 544+545 en gare de Charleville",null,"Y",null,45454,"High",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20520583761,"Mohon - Charleville-Mézière",null,"Charleville-Mézières - Bât Voyageurs",0,2025,2025,15,16,"2025-04-07",97.2430555555556,"2025-04-20","15:15:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788800561,"Mantes - Le Havre",null,"Achères-Triage - Les Ambassadeurs","Villennes-sur-Seine",2025,2025,51,44,"2025-04-08",97.4097222222222,"2025-06-28","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16594021661,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Mohon - Bât Voyageurs",2025,2025,14,44,"2025-04-11",97.7013888888889,"2025-04-12","06:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16868177661,"Don-Sainghin - Lens",null,0,"Pont-à-Vendin - Poste 1",2025,2025,15,47,"2025-04-12",97.9097222222222,"2025-11-23","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16868201861,"No encontrado",null,"Lens - Bif l'Épinette","Pont-de-Sallaumines - Bât Voyageurs",2025,2025,15,47,"2025-04-12",97.9513888888889,"2025-11-23","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177918561,"Novéant - Nancy",null,"Pagny-sur-Moselle - Poste 3","Novéant - Bif Km 338,9",2025,2025,15,20,"2025-04-12",98.1597222222222,"2025-05-19","03:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toute la zone d'action de la CCR Onville-Novéant-Metz (IHM1)",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16891159661,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,15,15,"2025-04-12",98.3680555555556,"2025-04-13","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16891370361,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Mantes-la-Jolie - E/S VC PARIS",2025,2025,15,15,"2025-04-12",98.5763888888889,"2025-04-13","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803720961,"Strasbourg - St Louis",null,"Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - Frontière Fr-Su",2025,2025,4,44,"2025-04-14",98.7430555555556,"2025-10-18","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification des horaires suite à la MEQ des OT dans TCAP pour SIPH",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"St-Louis (Haut-Rhin) - Frontière Fr-Su",null,null,"Planned",0]
[null,"SNCF-R",16999991561,"Mohon - Charleville-Mézière",null,"Fismes","Reims - Bif L2/L22-5",2025,2025,7,44,"2025-04-14",98.8680555555556,"2025-04-18","16:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Demande de modification réalisée par PK DT GE le 14-02-2024 à la demande de TER DL CA F STMAXENT",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16594016861,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Mohon - Bât Voyageurs",2025,2025,14,44,"2025-04-14",99.0763888888889,"2025-04-16","06:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18424243361,"Paris - Strasbourg",null,"Lagny-Thorigny","Meaux - Marchandises",2025,2025,16,40,"2025-04-14",99.2847222222222,"2025-10-06","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18424209461,"Paris - Strasbourg",null,"Meaux - Marchandises","Meaux - ITE ZI",2025,2025,16,40,"2025-04-14",99.3263888888889,"2025-10-06","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"CAP pour fenêtre générique classique zone de Meaux uniquement  DFV GPT de type G ZEP 32016 (216+218+222+226+230) Meaux",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16947124461,"Paris - Lille",null,"Longueau - E/S Dépôt","Daours - ITE Roquette",2025,2025,16,46,"2025-04-14",99.5347222222222,"2025-11-15","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16178035961,"Remilly - Forbach",null,"Herny - Bât Voyageurs","St-Avold",2025,2025,16,19,"2025-04-14",99.7430555555556,"2025-05-10","05:41:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf V1+V2 entre Rémilly et Béning. Suppression TER, détournements frets vers Forbach via Thionville/Creutzwald. Accès Rac Herny interdit.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16293459761,"Paris - Strasbourg",null,"Champigneulles - Aig Km 345,7","Nancy-Ville - Tiroir Ouest",2025,2025,16,24,"2025-04-14",99.8263888888889,"2025-06-13","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Fenêtre déformée V1B+V1+V2+VE entre Champigneulles et Nancy exclu. Décalage ou détournement Frets, suppression TER. Avec 5C_FR_001.",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177792361,"Novéant - Nancy",null,"Pompey","Pont-à-Mousson - ITE Sigalnor",2025,2025,16,20,"2025-04-14",100.034722222222,"2025-05-17","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 7h20 V1 entre Pompey et Dieulouard. Détournement trafic fret via Lérouville-Onville.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16282918561,"Paris - Strasbourg",null,"Stephansfeld","Mundolsheim",2025,2025,16,16,"2025-04-14",100.243055555556,"2025-04-18","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP832+827+833+835+816+818+820+824+826",null,"Y",null,45454,"Medium","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16687426461,"Paris - Lille",null,"Corbehem - Garages Pairs","Douai - Triage",2025,2025,16,16,"2025-04-14",100.451388888889,"2025-04-16","05:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1.2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16814440061,"Strasbourg - St Louis",null,"Lutterbach (Haut-Rhin) - Bât Voyageurs","Mulhouse-Musées",2025,2025,16,16,"2025-04-15",100.659722222222,"2025-04-16","00:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP204+206+208+210+211+902",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16817840261,"Strasbourg - St Louis",null,"Mulhouse-Dornach - Jct Aig 723","Mulhouse-Ville - Bât Voyageurs",2025,2025,16,16,"2025-04-16",100.701388888889,"2025-04-17","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP405+415+422+408+417+420+419+423+424 Propagation du SRV 2076 de la ligne 115000",null,"Y",null,45454,"Medium",3,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16649575761,"Strasbourg - St Louis",null,"St-Louis (Haut-Rhin) - Faisceau","St-Louis (Haut-Rhin) - Aiguille 23",2025,2025,16,16,"2025-04-17",100.909722222222,"2025-04-20","00:01:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16946541761,"Paris - Lille",null,"Albert","Achiet",2025,2025,16,17,"2025-04-18",101.118055555556,"2025-04-21","23:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16752445461,"Pontoise - Serqueux",null,"Épinay-Villetaneuse - Bât Voyageurs","La Barre-Ormesson",2025,2025,16,17,"2025-04-18",101.326388888889,"2025-04-21","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16818233361,"Strasbourg - St Louis",null,"Rixheim - Bif","Habsheim - Bât Voyageurs",2025,2025,16,16,"2025-04-18",101.409722222222,"2025-04-18","01:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP908+910+912+911+913+915+917",null,"Y",null,45454,"Medium",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16549251661,"Paris - Strasbourg",null,"Sarrebourg","Réding - Bât Voyageurs",2025,2025,16,17,"2025-04-19",101.618055555556,"2025-04-21","09:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP1850+1913+1852+1851+1856",null,"Y",null,45454,"Medium","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16549380061,"Paris - Strasbourg",null,"Saverne","Steinbourg",2025,2025,16,17,"2025-04-19",101.826388888889,"2025-04-21","09:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16161555361,"Paris - Strasbourg",null,"Changis-St-Jean - ITE Appel","Mézy - Poste U",2025,2025,1,50,"2025-04-21",102.034722222222,"2025-05-03","04:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"23/11/2022 (DAC) : Création de fenêtre générique élargie pour maintenance, suite concertation 2025. LFJ (inclue) - CTH (inclue) Voie 5 de CTH libre pour TN",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810436661,"Mantes - Le Havre",null,"Sotteville - Triage Mixte","Sotteville - Carré 225,2",2025,2025,1,50,"2025-04-21",102.076388888889,"2025-12-13","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16576843561,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Blesme-Haussignemont - Bât Voyageurs",2025,2025,17,22,"2025-04-21",102.284722222222,"2025-05-30","17:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16842178961,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Vernon (Eure) - Pancarte Arrêt",2025,2025,17,33,"2025-04-21",102.451388888889,"2025-08-15","04:41:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18215778461,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Poissy - Bât Voyageurs",2025,2025,17,29,"2025-04-21",102.743055555556,"2025-05-09","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16752379261,"Mantes - Le Havre",null,"Sartrouville - E/S Grps 3 et 5","Villennes-sur-Seine",2025,2025,17,46,"2025-04-21",102.784722222222,"2025-11-12","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16793946661,"Mantes - Le Havre",null,"Poissy - C4147","Villennes-sur-Seine",2025,2025,17,46,"2025-04-21",102.993055555556,"2025-11-12","04:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16283285361,"Paris - Strasbourg",null,"Vendenheim - Voies 3/5","Strasbourg-Ville - Voies 35/36",2025,2025,17,17,"2025-04-21",103.201388888889,"2025-04-25","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP593+837+825+829+831+839+841+845",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20898414061,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,17,46,"2025-04-21",103.409722222222,"2025-11-12","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL  24/01/2023 : Mise en qualité suite rejet SIPH / Suppression de la localisation voie 2BIS-R à PE, non décrite dans l'infra SIPH. ",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20898414061,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,17,46,"2025-04-21",103.451388888889,"2025-04-22","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL  24/01/2023 : Mise en qualité suite rejet SIPH / Suppression de la localisation voie 2BIS-R à PE, non décrite dans l'infra SIPH. ",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16576506961,"Paris - Strasbourg",null,"Épernay - Rac Côté Oiry","Châlons-en-Champagne - Accès Triage",2025,2025,12,21,"2025-04-22",103.784722222222,"2025-04-25","16:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP 1+3+5 V1 / ZEP 79 V1bis / ZEP 238 V2bis + Sous -Secteurs Matougues - Chalons V1 et SEL 321 et 322 su Sous Secteurs Chalons Voie B et dépôt",null,"Y",null,45454,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16980617261,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,17,37,"2025-04-22",103.909722222222,"2025-09-12","12:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16712855161,"Calais - Boulogne",null,"non trouvé",0,2025,2025,17,31,"2025-04-22",104.118055555556,"2025-08-02","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Travaux Préparatoires et finitions SR Domaine B S S17 à S18, S31 et Domaine C S28 à S30",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16649751861,"Racc de Santes - Don-Sainghin",null,"Lille-Flandres - Carré 508","Lille-Flandres - Remisage Ter",2025,2025,17,28,"2025-04-22",104.159722222222,"2025-07-12","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine B 22h00/06h00",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16363552261,"Remilly - Forbach",null,"Béning - Acc E Faisceau","Forbach - Bât Voyageurs",2025,2025,17,17,"2025-04-22",104.368055555556,"2025-04-25","14:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf V1+V2, 3h10 jour entre BNG et FB.",null,"Y",null,45454,"Medium","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16734721461,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Poissy - Bât Voyageurs",2025,2025,17,33,"2025-04-22",104.576388888889,"2025-06-10","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16749172161,"Mantes - Le Havre",null,"Houilles-Carrières-sur-Seine","Sartrouville - E/S Maison-Laff",2025,2025,17,46,"2025-04-22",104.784722222222,"2025-11-12","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16649874461,"Calais - Lille",null,"Lille-Flandres - Jonct Lion d'Or","Lille-Flandres - Bif Verte-Rue",2025,2025,17,28,"2025-04-22",104.868055555556,"2025-07-12","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine B extension 22h30/05h10",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16814287861,"Strasbourg - St Louis",null,"Raedersheim","Staffelfelden",2025,2025,17,17,"2025-04-24",105.076388888889,"2025-04-24","02:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"RWL-BOW  + ZEP926+928+930+932+ ZEP925+927+931+929 + BOW-RWL",null,"Y",null,45454,"Medium",4,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16818827761,"Strasbourg - St Louis",null,"Fegersheim-Lipsheim - Sort Évit 2BIS","Erstein - Carré 211",2025,2025,17,17,"2025-04-25",105.284722222222,"2025-04-25","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP306+402+401+403+405",null,"Y",null,45454,"Medium",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16687672661,"Don-Sainghin - Lens",null,0,"Pont-à-Vendin - Poste 1",2025,2025,17,17,"2025-04-26",105.493055555556,"2025-04-27","06:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16687726861,"No encontrado",null,"Lens - Bif l'Épinette","Pont-de-Sallaumines - Bât Voyageurs",2025,2025,17,17,"2025-04-26",105.534722222222,"2025-04-27","06:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23856939961,"Argenteuil - Le Havre",null,"ParisBatignolles - C791","Paris-Batignolles - Voie Auxil",2025,2025,17,17,"2025-04-26",105.743055555556,"2025-04-27","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16673513561,"Creil - Jeumont",null,"Maubeuge - Garages Pairs","Les Bons-Pères",2025,2025,17,18,"2025-04-27",105.951388888889,"2025-04-30","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16891681161,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,17,17,"2025-04-27",106.201388888889,"2025-04-28","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16891687561,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,17,17,"2025-04-27",106.243055555556,"2025-04-28","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16745792461,"Paris - Lille",null,0,"Lille-Flandres - Bif Fives Nord",2025,2025,18,19,"2025-04-28",106.451388888889,"2025-05-10","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16724563461,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Épernay - Aiguille 139,3",2025,2025,18,40,"2025-04-28",106.659722222222,"2025-05-23","16:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV type G 215+217 V et Consignation sous secteur Château - Mézy V1",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16679796561,"Metz - Reding",null,"Metz-Sablon - Jonct V2/V2R","Metz-Ville - Bât Voyageurs",2025,2025,18,19,"2025-04-28",106.868055555556,"2025-05-10","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5C_Metz_028",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16802036461,"Metz Ville - Zoufftgen",null,"Uckange - Bât Voyageurs","Uckange - Faisceau",2025,2025,18,18,"2025-04-28",106.909722222222,"2025-04-30","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 6h30 nuit, V1+V2 au niveau d'Uckange P2. Accès Faisceau Uckange coté Hagondange interdit.       ",null,"Y",null,45454,"Medium",1.2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16819037161,"Strasbourg - St Louis",null,"Sélestat","St-Hippolyte (Haut-Rhin)",2025,2025,18,18,"2025-04-28",107.118055555556,"2025-04-29","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP626",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",25075918361,"Creil - Jeumont",null,"Creil - JCT Nord","Longueil-Ste-Marie - Voie 4",2025,2025,51,50,"2025-04-28",107.326388888889,"2025-08-09","04:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16819069561,"Strasbourg - St Louis",null,"Sélestat","St-Hippolyte (Haut-Rhin)",2025,2025,18,18,"2025-04-29",107.493055555556,"2025-04-29","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP628+627+629+631",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",27849875677,"Creil - Jeumont",null,"Creil - JCT Nord","Longueil-Ste-Marie - Voie 4",2025,2025,18,31,"2025-04-29",107.618055555556,"2025-07-30","04:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18425281761,"Mantes - Le Havre",null,"Achères-Triage - Poste A","non trouvé",2025,2025,18,18,"2025-04-30",107.826388888889,"2025-05-02","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19419700161,"Mantes - Le Havre",null,"Paris-St-Lazare - Pont Legendre","Asnières-sur-Seine - Bât Voyageurs",2025,2025,18,18,"2025-04-30",108.034722222222,"2025-05-04","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","3,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16947896861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,18,19,"2025-05-01",108.243055555556,"2025-05-05","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"non repris dans TCAP impasse K //SAS B//SASV//V10 des VS",null,"Y",null,45454,"Medium","1,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16576586761,"Paris - Strasbourg",null,"Épernay - Poste 1","Châlons-en-Champagne - Poste 1",2025,2025,12,21,"2025-05-02",108.284722222222,"2025-05-21","16:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18425346461,"Mantes - Le Havre",null,"Achères-Triage - Poste A","non trouvé",2025,2025,18,18,"2025-05-02",108.493055555556,"2025-05-04","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16829230061,"Paris - Lille",null,"Goussainville - Garage","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,18,49,"2025-05-02",108.618055555556,"2025-12-01","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806707961,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,3,50,"2025-05-05",108.951388888889,"2025-10-18","04:39:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante n°120 : pour passage du 13164",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799199161,"Longuyon - Onville",null,"Longuyon - Bif","Conflans-Jarny - Bif L5 VU/L12",2025,2025,5,45,"2025-05-05",108.993055555556,"2025-06-06","16:23:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main courante 85 : décalage de +13 minutes des horaires",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786411361,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Hirson","Tournes",2025,2025,6,49,"2025-05-05",109.201388888889,"2025-05-09","14:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Attention aux horaires: la section est nommée Tournes Charleville mais la localisation réseau est dans le sens Charleville Tournes : le PR début est donc Charleville et le PR Fin Tournes. Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normal",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20996871661,"Longueau - Boulogne",null,"Boulogne-Ville - Bif St-Léonard","Boulogne-Ville - Poste 5",2025,2025,19,27,"2025-05-05",109.409722222222,"2025-07-04","20:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Voie d'approche 02h00 avant ITC pour 2 TTx Principaux Suite Rapide depuis Longueau",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16713217861,"Calais - Boulogne",null,0,0,2025,2025,19,24,"2025-05-05",109.618055555556,"2025-06-14","05:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Travaux principaux SR Domaine B S19 à S24",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16542270061,"Paris - Lille",null,"Longueau - Poste 1","Longueau - Tiroir",2025,2025,19,19,"2025-05-05",109.659722222222,"2025-05-10","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18425359561,"Mantes - Le Havre",null,"Achères-Triage - Poste A","non trouvé",2025,2025,19,19,"2025-05-05",109.909722222222,"2025-05-05","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16567278661,"Thionville - Mohon",null,"Mohon - Bif L2","Lumes-Triage - ITE Citroën",2025,2025,19,28,"2025-05-05",110.118055555556,"2025-07-11","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Consignation du sous-secteur Mohon-Donchery voie 2  Consignation du sous secteur Lumes Faisceau A.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805190161,"Paris - Strasbourg",null,0,"Noisy-le-Sec - Bif GC/Ligne 4",2025,2025,51,50,"2025-05-05",110.326388888889,"2025-05-10","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sauf ZEP 789 pour accès T4  + ZEP 252 Pantin G commandée par CHL pour aig 2547b        ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16594016861,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Mohon - Bât Voyageurs",2025,2025,14,44,"2025-05-06",110.368055555556,"2025-05-08","06:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19419774361,"Mantes - Le Havre",null,"Paris St Lazare - C374 à C774","Asnières-sur-Seine - Bât Voyageurs",2025,2025,19,20,"2025-05-07",110.576388888889,"2025-05-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,3,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17000823861,"Paris - Strasbourg",null,"Toul - Rac Sud","Toul - PosteA Fontenoy",2025,2025,19,19,"2025-05-08",110.784722222222,"2025-05-09","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 9h30 - V1+V2+V1B+V2B à Toul BV interdites. Accès Faisceau Pair et Impair interdit. Rac Toul libre.",null,"Y",null,45454,"Medium",4,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16740271561,"Paris - Strasbourg",null,"Épernay - Poste 1","Épernay - Bif L1/22 5",2025,2025,19,19,"2025-05-09",110.993055555556,"2025-05-11","07:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP 506 + 510 + 512 V2  (Ajout des ZEP jusqu'au chantier \"\"V\"\" pour acheminement AdV sur lorry depuis l'aire de montage du chantier équipement)  SEL 34+36 Ss Mardeuil-Epernay V2  (Ajout des SEL jusqu'au chantier \"\"V\"\" pour acheminement AdV sur lorry depui",null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16175984661,"Paris - Strasbourg",null,"Toul - Rac Sud","Toul - PosteA Fontenoy",2025,2025,19,20,"2025-05-09",111.034722222222,"2025-05-12","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 56h25 - V1+V2+V1B+V2B à Toul BV interdites. Accès Faisceau Pair et Impair interdit. Rac Toul libre.",null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18542666661,"Mantes - Le Havre",null,"Achères-Triage - Jonct V1/V1Bis","non trouvé",2025,2025,19,28,"2025-05-09",111.284722222222,"2025-07-07","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16947742661,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,19,20,"2025-05-10",111.493055555556,"2025-05-12","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"non repris dans TCAP impasse K //SAS B//SASV//V10 des VS",null,"Y",null,45454,"Medium","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16892008061,"Mantes - Le Havre",null,"non trouvé","non trouvé",2025,2025,19,22,"2025-05-11",111.701388888889,"2025-06-02","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16892002961,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Mantes-la-Jolie - E/S VC PARIS",2025,2025,19,22,"2025-05-11",111.743055555556,"2025-06-02","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806698361,"Mantes - Le Havre",null,"Asnières-sur-Seine - Bât Voyageurs","Sartrouville - E/S Grps 3 et 5",2025,2025,2,50,"2025-05-12",111.951388888889,"2025-05-24","04:49:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante n°119 : Pour passage du 13164",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805763361,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Vaires-Torcy - Faisceau V",2025,2025,14,44,"2025-05-12",112.159722222222,"2025-05-17","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805580961,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau Impair","Lagny-Thorigny - Tiroir 3",2025,2025,20,50,"2025-05-12",112.368055555556,"2025-05-27","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805674961,"Paris - Strasbourg",null,"Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2025,2025,20,39,"2025-05-12",112.451388888889,"2025-05-17","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP                       ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16695026661,"Paris - Lille",null,"Achiet","Arras - Bif Sud",2025,2025,20,20,"2025-05-12",112.659722222222,"2025-05-16","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16248595961,"Paris - Strasbourg",null,"Lunéville - Bât Voyageurs","Sarrebourg",2025,2025,20,24,"2025-05-12",112.868055555556,"2025-06-14","06:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 9h10, V1+V2 entre Lunéville et Sarrebourg. Suppression TER, détournement frets via Réding-Rémilly-Metz. Desserte Heming interdite. ZEP LNE-SBG voie 1, ZEP SBG-LNE V2. Avec 5C_LNE_003.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16249306961,"Strasbourg - St Louis",null,"Graffenstaden - Bif","Graffenstaden - Bât Voyageurs",2025,2025,20,44,"2025-05-12",113.076388888889,"2025-11-01","00:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP203",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16688175361,"Paris - Lille",null,"Douai - Triage","Douai - Aig Km 218,5",2025,2025,20,20,"2025-05-12",113.118055555556,"2025-05-17","05:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806635561,"Mantes - Le Havre",null,"Maisons-Laffitte - Bât Voyageurs","Achères-Triage - FSC Réception",2025,2025,51,38,"2025-05-13",113.326388888889,"2025-06-28","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23351768561,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Chennevières","Conflans-Ste-Honorine - Evo & Manœuvres",2025,2025,20,39,"2025-05-18",113.534722222222,"2025-09-29","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23351775661,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Chennevières","Conflans-Ste-Honorine - Evo & Manœuvres",2025,2025,20,39,"2025-05-18",113.659722222222,"2025-09-29","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810408661,"Mantes - Le Havre",null,"Rouen-Rive-Droite - IPCS Km 142,9","Motteville - Bif Auzouville",2025,2025,1,50,"2025-05-19",113.826388888889,"2025-05-29","04:44:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante N°115: pour train N°3135. AAB RCST NEN. 06/12/2023.  Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810448861,"Mantes - Le Havre",null,"Sotteville - Carré 354h","Rouen-Rive-Droite",2025,2025,1,49,"2025-05-19",114.034722222222,"2025-06-01","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805714561,"Paris - Strasbourg",null,"Lagny-Thorigny","Lagny-Thorigny - Tiroir 3",2025,2025,11,42,"2025-05-19",114.243055555556,"2025-10-20","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Ombre générique Lagny Meaux ZEP 1115+1117+1141+1143+1145+1147 Vaires 5VP SEL 53 SSr Raincy Lagny V21B1   ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16724563461,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Épernay - Aiguille 139,3",2025,2025,18,40,"2025-05-19",114.451388888889,"2025-05-21","16:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV type G 215+217 V et Consignation sous secteur Château - Mézy V1",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16724617861,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Épernay - Bât Voyageurs",2025,2025,18,40,"2025-05-19",114.493055555556,"2025-05-21","16:28:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV type G 218 V2 de Château Thierry zone de Mézy et Consignation C sous secteur Château Mézy V2",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18426075261,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,21,25,"2025-05-19",114.701388888889,"2025-06-21","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16759108461,"Creil - Jeumont",null,"Montescourt","St-Quentin - ITE ZI",2025,2025,21,38,"2025-05-19",114.993055555556,"2025-09-20","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19903838161,"Pontoise - Serqueux",null,0,"La Barre-Ormesson",2025,2025,21,26,"2025-05-19",115.159722222222,"2025-06-28","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC Industrielles  S1 3 3",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18425845761,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,21,25,"2025-05-19",115.201388888889,"2025-06-21","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"la caténaire doit être rendue à 04h45 pour la préparation du matériel ligne K",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805759161,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2025,2025,51,50,"2025-05-19",115.409722222222,"2025-05-20","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL bif Gagny degagé",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806839561,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Poissy - Bât Voyageurs",2025,2025,51,50,"2025-05-20",115.618055555556,"2025-06-28","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16739699761,"Creil - Jeumont",null,"Viry-Noureuil","Tergnier - Triage",2025,2025,21,23,"2025-05-23",115.826388888889,"2025-06-02","04:00:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16900645161,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,21,24,"2025-05-23",115.868055555556,"2025-06-15","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21525918161,"Mantes - Le Havre",null,"Achères-Grand-Cormier","Poissy - C4134",2025,2025,21,21,"2025-05-23",116.076388888889,"2025-05-25","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16572465361,"Thionville - Mohon",null,"Mohon - Bif L2","Lumes-Triage - Accès Km 144,5",2025,2025,21,22,"2025-05-23",116.326388888889,"2025-06-01","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Consignation du sous-secteur Mohon-Donchery voie 1",null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16820276461,"Creil - Jeumont",null,"Chevrières","Longueil-Ste-Marie - Bât Voyageurs",2025,2025,21,30,"2025-05-24",116.534722222222,"2025-07-21","04:59:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16702077661,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Aulnoye-Aymeries - Bif Sassegnies",2025,2025,21,21,"2025-05-24",116.576388888889,"2025-05-26","04:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16702100261,"Lille - Hirson",null,"Aulnoye-Aymeries - Bif Berlaimont","Monceau-St-Waast",2025,2025,21,21,"2025-05-24",116.784722222222,"2025-05-26","04:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16364806861,"Metz Ville - Zoufftgen",null,"Hagondange - Faisceau","Hagondange - ITE Richemont",2025,2025,21,24,"2025-05-25",116.993055555556,"2025-06-16","03:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 4h nuit, V1 à Hagondange.",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16901783261,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,21,26,"2025-05-25",117.201388888889,"2025-06-30","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16899137661,"Mantes - Le Havre",null,"Poissy - C4147","Villennes-sur-Seine",2025,2025,21,21,"2025-05-25",117.409722222222,"2025-05-26","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22801625761,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,21,24,"2025-05-25",117.493055555556,"2025-06-16","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16899054361,"Mantes - Le Havre",null,"Achères-Triage - Bif de Dieppe","Poissy - Bât Voyageurs",2025,2025,21,21,"2025-05-25",117.701388888889,"2025-05-26","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16899404661,"Mantes - Le Havre",null,"Poissy - C4147","Poissy - Bât Voyageurs",2025,2025,21,21,"2025-05-25",117.909722222222,"2025-05-26","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16899575161,"Mantes - Le Havre",null,"Poissy - C4147","Villennes-sur-Seine",2025,2025,21,21,"2025-05-25",117.951388888889,"2025-05-26","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16638513961,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,21,33,"2025-05-25",118.159722222222,"2025-08-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"essais à blanc PCD",null,"Y",null,45454,"Medium","1,5,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16639346461,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Joncherolles",2025,2025,21,33,"2025-05-25",118.368055555556,"2025-08-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"essais à blanc PCD",null,"Y",null,45454,"Medium","1,5,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799293161,"Metz Ville - Zoufftgen",null,"Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2025,2025,10,48,"2025-05-26",118.534722222222,"2025-09-20","05:29:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"SA2025 - Main courante 56 : décalage de +2 minutes",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,"Zoufftgen (IE) - Frontière Fr-Lu",null,null,"Planned",0]
[null,"SNCF-R",16901405261,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Le Cateau",2025,2025,22,40,"2025-05-26",118.659722222222,"2025-10-04","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813804461,"Calais - Dunkerque",null,"Dunkerque-Grande-Synthe - Bif Puyt-Houck","Calais-Fréthun - Accès Offerkerque",2025,2025,7,46,"2025-05-27",118.868055555556,"2025-05-29","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16626533361,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,22,23,"2025-05-28",119.076388888889,"2025-06-02","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE TX Blanc Mesnil",null,"Y",null,45454,"Medium","1,3,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21285533161,"Calais - Boulogne",null,"Wimille-Wimereux","Calais-Fréthun - C102/204",2025,2025,22,22,"2025-05-29",119.284722222222,"2025-05-30","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",4,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16734609561,"Mantes - Le Havre",null,"Sartrouville - E/S Grps 3 et 5","Maisons-Laffitte - E/S Côté Achère",2025,2025,22,24,"2025-05-29",119.326388888889,"2025-06-10","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16818907961,"Pontoise - Serqueux",null,0,"Gisors - Garage",2025,2025,22,22,"2025-05-29",119.534722222222,"2025-05-30","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16798502761,"St Just en Chaussée - Douai",null,"Cantin","Douai - Bif de Sin",2025,2025,22,22,"2025-05-31",119.743055555556,"2025-06-01","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16798497761,"St Just en Chaussée - Douai",null,0,"Sin-le-Noble",2025,2025,22,22,"2025-05-31",119.826388888889,"2025-06-01","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16798588261,"Somain - Busigny",null,"Lourches - Gros-Caillou","Somain - Aig 80061b",2025,2025,22,22,"2025-05-31",120.034722222222,"2025-06-01","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16923110561,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Jonction Sud",2025,2025,22,23,"2025-05-31",120.243055555556,"2025-06-08","08:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE 22/23 et 23/24",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16798509061,"Douai - Valenciennes",null,"Corbehem - Garages Pairs",0,2025,2025,22,22,"2025-05-31",120.451388888889,"2025-06-01","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16798655761,"Paris - Lille",null,"Phalempin","Wattignies-Templemars",2025,2025,22,22,"2025-06-01",120.659722222222,"2025-06-02","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16798706061,"Paris - Lille",null,"Triangle d'Ostricourt - Bif de Évin","Lille-St-Sauveur - Bif Sourd-Muet",2025,2025,22,22,"2025-06-01",120.701388888889,"2025-06-02","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16798677661,"Douai - Valenciennes",null,"Corbehem - Garages Pairs",0,2025,2025,22,22,"2025-06-01",120.909722222222,"2025-06-02","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16161510161,"Paris - Strasbourg",null,"Trilport - Bif de Germigny","La Ferté-sous-Jouarre - Aig Km 63,6-Év",2025,2025,1,48,"2025-06-02",121.118055555556,"2025-06-05","04:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"17/10/2023 (DAC) : Vibration suite main courante n° 104/2025. 23/11/2022 (DAC) : Création de fenêtre générique élargie pour maintenance suite concertation 2025. Trilport - LFJ (exclue) Train ouvrant : 56622 (voir Variante correspondante) Train fermant : 5",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17000031361,"Paris - Strasbourg",null,"Meaux - Bât Voyageurs","Trilport - Aig Év Germigny",2025,2025,10,44,"2025-06-02",121.368055555556,"2025-06-05","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DEF Type générique, sans impact sillons.  Alignée sur la fenêtre TLP - LFJ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786425961,"Lille - Hirson",null,"Leval","Hirson - Ent Marchandise",2025,2025,12,44,"2025-06-02",121.409722222222,"2025-06-03","15:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16654278661,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Le Cateau",2025,2025,23,25,"2025-06-02",121.618055555556,"2025-06-21","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16175797161,"Paris - Strasbourg",null,"Toul - Bif L1/L15","Toul - Poste 1",2025,2025,23,33,"2025-06-02",121.826388888889,"2025-08-16","05:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Def 6h45 nuit - V1 à Toul - Avec 5D_TL-FR_002 et 5C_TL_002 qui reprend les conséquences circulations.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16249435561,"Strasbourg - St Louis",null,"Graffenstaden - Bif","Graffenstaden - Bât Voyageurs",2025,2025,23,42,"2025-06-02",122.034722222222,"2025-10-18","00:37:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP210",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803745361,"Paris - Strasbourg",null,"Réding - FSC Pair","Saverne - Aiguille Est",2025,2025,23,39,"2025-06-02",122.076388888889,"2025-06-14","04:57:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification des horaires suite à la MEQ des OT dans TCAP pour SIPH // Alignement des fenêtres génériques entre Reding et Vendenheim",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16676508461,"Douai - Valenciennes",null,0,0,2025,2025,23,23,"2025-06-02",122.243055555556,"2025-06-07","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine B (voir également Domaine de protection annexe 17 au CR RP0)",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16249440661,"Strasbourg - St Louis",null,"Graffenstaden - Bif","Graffenstaden - Bât Voyageurs",2025,2025,23,42,"2025-06-03",122.534722222222,"2025-10-18","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP210",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16909722461,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,23,29,"2025-06-06",122.743055555556,"2025-07-14","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16909318761,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,23,24,"2025-06-06",122.784722222222,"2025-06-09","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18542869661,"Mantes - Le Havre",null,"Achères-Grand-Cormier","Poissy - C4134",2025,2025,23,24,"2025-06-06",122.993055555556,"2025-06-09","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16909430261,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,23,24,"2025-06-06",123.201388888889,"2025-06-09","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16910352761,"Mantes - Le Havre",null,"Mantes-la-Jolie - Rem Banlieue","Rosny-sur-Seine",2025,2025,23,29,"2025-06-07",123.409722222222,"2025-07-14","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16910330661,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,23,29,"2025-06-07",123.576388888889,"2025-07-14","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16910430061,"Argenteuil - Le Havre",null,"Mantes-Station","Mantes-la-Jolie - Bât Voyageurs",2025,2025,23,29,"2025-06-07",123.701388888889,"2025-07-14","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16572483061,"Thionville - Mohon",null,"Lumes","Donchery",2025,2025,23,24,"2025-06-07",123.909722222222,"2025-06-15","11:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV Type G Voie 1 sur ZEP 655 et 657 de Lumes  ",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16734191461,"Mantes - Le Havre",null,"Maisons-Laffitte - Bât Voyageurs","Villennes-sur-Seine",2025,2025,17,29,"2025-06-09",124.118055555556,"2025-06-10","04:52:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16752228261,"Racc de Santes - Don-Sainghin",null,"Lille-Flandres - Impasse D","Lille-St-Sauveur - Bif de Justice",2025,2025,24,26,"2025-06-09",124.159722222222,"2025-06-28","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22805618661,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,24,29,"2025-06-09",124.368055555556,"2025-07-15","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16910388361,"Argenteuil - Le Havre",null,"Gargenville","Mantes-la-Jolie - Bât Voyageurs",2025,2025,24,29,"2025-06-09",124.576388888889,"2025-07-15","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22805532361,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,24,24,"2025-06-09",124.659722222222,"2025-06-10","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16528574461,"Paris - Strasbourg",null,"Lutzelbourg - IPCS","Saverne - Aiguille Est",2025,2025,24,24,"2025-06-09",124.868055555556,"2025-06-10","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16734012961,"Mantes - Le Havre",null,"Sartrouville - E/S Grps 3 et 5","Villennes-sur-Seine",2025,2025,24,24,"2025-06-10",125.076388888889,"2025-06-10","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16923415861,"Paris - Lille",null,"Paris-Nord - Portique Landy","St-Denis - Garages Pairs",2025,2025,24,40,"2025-06-14",125.284722222222,"2025-10-05","08:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE 24/25,  39/40 ET 40/41",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16923651261,"Paris - Lille",null,"Paris-Nord - Portique Landy","St-Denis - Jonction Sud",2025,2025,24,40,"2025-06-14",125.493055555556,"2025-10-05","08:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE 24/25,  39/40 ET 40/41",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799499561,"Metz Ville - Zoufftgen",null,"Uckange - Ano Km 181,3","Ébange - Accès Sud",2025,2025,4,47,"2025-06-16",125.534722222222,"2025-06-16","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Activation 2V/4 parmi V1,V2,V1Bis, V2Bis Incompatibilité entre Bloc 10 (Ebange - Uckange KM) et Block 10 Bis (Uckange KM - Woippy BV)         ",null,"Y",null,45454,"High",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16679871461,"Mantes - Le Havre",null,"Val-de-Reuil - Bât Voyageurs","Oissel - Bif Tourville",2025,2025,20,50,"2025-06-16",125.743055555556,"2025-10-10","05:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17021165161,"Mantes - Le Havre",null,"Pont-de-l'Arche - Bât Voyageurs","Sotteville - Triage Annexe",2025,2025,25,29,"2025-06-16",125.993055555556,"2025-07-21","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16139562461,"Strasbourg - St Louis",null,"Ribeauvillé - Carré 408","Colmar - Accès Nord",2025,2025,25,31,"2025-06-16",126.201388888889,"2025-08-02","00:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP716+718+720+722",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16139635361,"Strasbourg - St Louis",null,"Colmar - Aiguille Sud","Bollwiller - Bât Voyageurs",2025,2025,25,31,"2025-06-16",126.243055555556,"2025-08-02","00:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP732+902+904+904+906+908+910+922",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16140020561,"Strasbourg - St Louis",null,"Colmar - ITE ZI","Colmar - Ent/Sort Sud",2025,2025,25,31,"2025-06-17",126.451388888889,"2025-08-02","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP722+724+726+728+730+732",null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16139959661,"Strasbourg - St Louis",null,"Ribeauvillé - Carré 408","Colmar - Accès Nord",2025,2025,25,31,"2025-06-17",126.659722222222,"2025-08-02","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP716+718+720+722",null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16661247061,"Longueau - Boulogne",null,"Abbeville","Rang-du-Fliers-Verton",2025,2025,25,26,"2025-06-19",126.868055555556,"2025-06-27","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16572727861,"Thionville - Mohon",null,"Mohon - Bif L2","Sedan - Accès Garage",2025,2025,25,28,"2025-06-19",126.909722222222,"2025-07-11","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV Type G Voie 2 sur ZEP 656 et 658 de Lumes et entrée faisceau  ZEP 642 (voie 12) + 643 (voie 13)+ 644 (voie 14) + 672 + 668 + 670 + 674( pinceaux coté longuyon) de Lumes  Consignation du sous-secteur Mohon Donchery voie 2 et Donchery Sachy Voie 2 Consi",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16649946261,"Racc de Santes - Don-Sainghin",null,"Lille-Flandres - Carré 508","Lille-Flandres - Remisage Ter",2025,2025,25,27,"2025-06-21",127.118055555556,"2025-07-06","12:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine C 22h30/12h30",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799270361,"Novéant - Nancy",null,0,"Pagny-sur-Moselle - Bât Voyageurs",2025,2025,3,35,"2025-06-23",127.284722222222,"2025-08-30","05:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18426156461,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,26,32,"2025-06-23",127.576388888889,"2025-08-09","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18426240861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,26,32,"2025-06-23",127.618055555556,"2025-08-09","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16825599661,"Paris - Lille",null,"Arras - Bif Sud","Arras - Bif Blangy-Est",2025,2025,26,30,"2025-06-23",127.826388888889,"2025-07-25","06:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine A nuits de semaine + voie G2,G4,G6,SL,SN,RS,GY,triage 4 à 10",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16140145361,"Strasbourg - St Louis",null,"Ribeauvillé - Carré 408","Colmar - Accès Nord",2025,2025,26,27,"2025-06-23",128.034722222222,"2025-07-05","05:17:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP716+718+720+722+715+717",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21528341161,"Mantes - Le Havre",null,"Sartrouville - Bât Voyageurs","Maisons-Laffitte - E/S Côté Achère",2025,2025,4,50,"2025-06-24",128.243055555556,"2025-06-28","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21528386361,"Mantes - Le Havre",null,"Sartrouville - E/S Grps 3 et 5","Achères-Triage - FSC Réception",2025,2025,26,26,"2025-06-24",128.284722222222,"2025-06-28","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806892961,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage","Vernouillet-Verneuil - Triage Accès OE",2025,2025,51,45,"2025-06-24",128.618055555556,"2025-06-28","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16140237861,"Strasbourg - St Louis",null,"Colmar - ITE ZI","Colmar - Ent/Sort Sud",2025,2025,26,28,"2025-06-26",128.743055555556,"2025-07-09","05:17:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP722+724+726+728+730+732+719+721+723+725+727+729+731",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16827707361,"Paris - Lille",null,"Arras - Bif Sud","Arras - Bif Blangy-Est",2025,2025,26,26,"2025-06-28",128.951388888889,"2025-06-29","11:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine D nuit de Sa/Di + voie G2,G4,G6,SL,SN,RS,GY,triage 4 à 10",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16601248361,"Paris - Strasbourg",null,"Épernay - Poste 1","Épernay - Bif L1/22 5",2025,2025,26,27,"2025-06-28",128.993055555556,"2025-07-06","06:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"voie 1: zep 511 + SEL 35 bis du sous secteur Mardeuil Epernay  Voie 1  ",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177685561,"Metz - Lérouville",null,"Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2025,2025,26,27,"2025-06-28",129.201388888889,"2025-07-07","03:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf V1+V2+V1B+V2B entre Novéant et Metz.",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16914955561,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,26,26,"2025-06-28",129.409722222222,"2025-06-29","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16618374561,"Strasbourg - St Louis",null,"Mulhouse-Dornach - Jct Aig 291","Rixheim - Bif",2025,2025,26,26,"2025-06-28",129.618055555556,"2025-06-29","00:01:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Propagation du SRV 2076 de la ligne 115000",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16621072261,"Strasbourg - St Louis",null,"Mulhouse-Ville - Aig Km 110","Habsheim - Bât Voyageurs",2025,2025,26,26,"2025-06-28",129.701388888889,"2025-06-29","00:01:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16934907061,"Mulhouse - Chalampé",null,"Mulhouse-Ville - Aig Km 110","Mulhouse-Ville - Point D",2025,2025,26,45,"2025-06-28",129.909722222222,"2025-11-09","04:30:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Neutralisation Aig 326 à gauche",null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16622079561,"Strasbourg - St Louis",null,"Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - Frontière Fr-Su",2025,2025,26,26,"2025-06-29",130.118055555556,"2025-06-30","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,"St-Louis (Haut-Rhin) - Frontière Fr-Su",null,null,"Planned",0]
[null,"SNCF-R",16622052561,"Lutterbach - Rixeim (Mulhouse)",null,"Lutterbach (Haut-Rhin) - Bif","Rixheim - Bif",2025,2025,26,26,"2025-06-29",130.326388888889,"2025-06-30","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16621064461,"Strasbourg - St Louis",null,"Wittelsheim - Bât Voyageurs","Lutterbach (Haut-Rhin) - Bât Voyageurs",2025,2025,26,26,"2025-06-29",130.368055555556,"2025-06-29","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16621811461,"Mulhouse - Chalampé",null,"Brunstatt - Jct Aig 721/720",0,2025,2025,26,26,"2025-06-29",130.576388888889,"2025-06-30","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16794931061,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Evo & Manœuvres","Limay - Bât Voyageurs",2025,2025,2,50,"2025-06-30",130.784722222222,"2025-12-05","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805697761,"Paris - Strasbourg",null,"Meaux - Marchandises","Meaux - ITE ZI",2025,2025,8,47,"2025-06-30",131.034722222222,"2025-11-24","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"CAP pour fenêtre générique classique zone de Meaux uniquement  DFV GPT de type G ZEP 32016 (216+218+222+226+230) Meaux",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805695361,"Paris - Strasbourg",null,"Lagny-Thorigny","Meaux - Marchandises",2025,2025,8,47,"2025-06-30",131.076388888889,"2025-11-24","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Ajout 2 semaines pour 17 166 mise en cohérence domaines S9 S11",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16677756061,"Paris - Lille",null,"Longueau - Bif de Camon","Achiet",2025,2025,27,34,"2025-06-30",131.284722222222,"2025-08-23","05:33:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16677511461,"Paris - Lille",null,"Gannes","Longueau - Poste 1",2025,2025,27,30,"2025-06-30",131.493055555556,"2025-07-26","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16173493461,"Paris - Strasbourg",null,"Rosières-aux-Salines - Bât Voyageurs","Blainville-Damelevières - Aig V Bis/M",2025,2025,27,36,"2025-06-30",131.701388888889,"2025-09-06","05:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap V1+V2+V1B+V2B à Rosières. Avec 5D_ROI-BLV_001, 5C_LNE_001, 5D_BLV-LNE_004, 5D_LNE-RDG_001, 5D_LNE-STD_006 et 5C_BLV_001 qui reprend les conséquences circulations.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177821361,"Metz Ville - Zoufftgen",null,"Ébange - Faisceau","Thionville - Bif L3/L7",2025,2025,27,28,"2025-06-30",131.743055555556,"2025-07-12","05:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 6h15 nuit, V1+V2B entre Thionville et Uckange.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806868161,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,27,32,"2025-06-30",131.951388888889,"2025-08-09","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18543065361,"Paris - Lille",null,"Goussainville - Bât Voyageurs","Les Noues",2025,2025,27,31,"2025-06-30",132.159722222222,"2025-08-02","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862287161,"Pontoise - Serqueux",null,"Gisors","Serqueux",2025,2025,3,49,"2025-07-07",132.409722222222,"2025-07-13","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"04/10/13 SBE : adaptation de la générique suite aux commandes Sillons TER HN (perte de 30 min sur la générique) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813741861,"Paris - Hirson",null,"Vauxaillon - Km 117,291","Laon - Bif St-Marcel",2025,2025,4,45,"2025-07-07",132.451388888889,"2025-07-19","06:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16752731361,"Pontoise - Serqueux",null,"Épinay-Villetaneuse - Bât Voyageurs","La Barre-Ormesson",2025,2025,12,39,"2025-07-07",132.659722222222,"2025-09-27","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC  Industrielles",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16367091461,"Creil - Jeumont",null,"Hautmont - Bif d'Hautmont","Louvroil",2025,2025,28,29,"2025-07-07",132.868055555556,"2025-07-19","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine A travaux Quai 2 S28 et 29 Sf nuit Fériée 14/15-07-25",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23660458761,"Paris - Strasbourg",null,"Épernay - Poste 1","Épernay - Bif L1/22 5",2025,2025,28,28,"2025-07-07",133.076388888889,"2025-07-07","06:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"voie 1: zep 511 + SEL 35 bis du sous secteur Mardeuil Epernay  Voie 1  ",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16812236261,"Pontoise - Serqueux",null,0,"La Barre-Ormesson",2025,2025,28,39,"2025-07-07",133.118055555556,"2025-09-27","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC Industrielles ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16925778861,"Paris - Lille",null,"Paris-Nord-Souterraine","Paris-Nord - Jonction Km 0,9",2025,2025,28,40,"2025-07-07",133.326388888889,"2025-09-29","04:30:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,"GEL 1/2 quai V9",null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22828687061,"Paris - Lille",null,"Orry-la-Ville-Coye - Bât Voyageurs","Creil - Aig 32",2025,2025,28,31,"2025-07-07",133.451388888889,"2025-08-02","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813807861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2025-07-07",133.784722222222,"2025-07-19","05:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813808661,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,51,50,"2025-07-07",133.826388888889,"2025-07-19","05:08:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16193694161,"Paris - Strasbourg",null,"Toul - Bif L1/L15","Toul - Poste 1",2025,2025,28,29,"2025-07-11",134.034722222222,"2025-07-14","17:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Def 68h - V1+V2 à Toul - Avec 5D_TL-FR_004 et 5C_TL_007 qui reprend les conséquences circulations.",null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16713261761,"Mantes - Le Havre",null,"Poissy - Bât Voyageurs","Les Mureaux - Carré 4353",2025,2025,28,30,"2025-07-11",134.243055555556,"2025-07-21","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16713273661,"Mantes - Le Havre",null,"Poissy - Bât Voyageurs","Vernouillet-Verneuil - Triage Accès OE",2025,2025,28,30,"2025-07-11",134.451388888889,"2025-07-21","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16713300961,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Vernouillet-Verneuil - Triage Accès OE",2025,2025,28,30,"2025-07-11",134.493055555556,"2025-07-21","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20505082661,"Creil - Jeumont",null,"Hautmont - Bif des Usines","Les Bons-Pères",2025,2025,29,29,"2025-07-14",134.743055555556,"2025-07-15","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine A travaux Quai 2 S28 et 29 nuit Fériée 14/15-07-25   + Impasse M de Maubeuge",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22817622961,"Mantes - Le Havre",null,"non trouvé","Épône-Mézières - SG",2025,2025,29,29,"2025-07-14",134.951388888889,"2025-07-15","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806708761,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,3,50,"2025-07-15",135.159722222222,"2025-08-14","04:39:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante n°120 : pour passage du 13164",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806707961,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,3,50,"2025-07-15",135.201388888889,"2025-08-14","04:39:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante n°120 : pour passage du 13164",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16470407661,"Strasbourg - St Louis",null,"St-Louis (Haut-Rhin) - Faisceau","St-Louis (Haut-Rhin) - Frontière Fr-Su",2025,2025,29,29,"2025-07-15",135.409722222222,"2025-07-19","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP928+968+970 et Sel 12+14+102 SSr Rixheim-StLouis et SSr StLouis-Frontière",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,"St-Louis (Haut-Rhin) - Frontière Fr-Su",null,null,"Planned",0]
[null,"SNCF-R",24201387461,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,29,29,"2025-07-18",135.618055555556,"2025-07-20","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24201408161,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,29,29,"2025-07-18",135.826388888889,"2025-07-20","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16654378361,"Creil - Jeumont",null,"Aulnoye-Aymeries - ITE EDF","Sous-le-Bois",2025,2025,29,29,"2025-07-19",135.868055555556,"2025-07-20","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24202443861,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,29,34,"2025-07-19",136.118055555556,"2025-08-24","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24202032361,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,29,29,"2025-07-19",136.326388888889,"2025-07-20","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23346020861,"Pontoise - Serqueux",null,"Trie-Château","Gisors - Garage",2025,2025,29,39,"2025-07-20",136.534722222222,"2025-09-29","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23346013061,"Pontoise - Serqueux",null,"Trie-Château","Gisors - Tiroir Nord",2025,2025,29,39,"2025-07-20",136.576388888889,"2025-09-29","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16474818861,"Strasbourg - St Louis",null,"St-Louis-la-Chaussée","St-Louis (Haut-Rhin) - Frontière Fr-Su",2025,2025,30,30,"2025-07-21",136.784722222222,"2025-07-26","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Sel 7+9+101 et 8+10+12+14+102+104 SSr Rixheim-StLouis et SSr StLouis-Frontière",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,"St-Louis (Haut-Rhin) - Frontière Fr-Su",null,null,"Planned",0]
[null,"SNCF-R",15810522761,"Mantes - Le Havre",null,"Pavilly-Station","Le Havre - Gare Locale",2025,2025,51,50,"2025-07-21",136.993055555556,"2025-08-14","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Modification suite à évolution du système capacitaire 2025",null,"Y",null,45454,"Major","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16819930761,"Pontoise - Serqueux",null,"Épinay-Villetaneuse - Bât Voyageurs","Ermont-Eaubonne - Bât Voyageurs",2025,2025,30,36,"2025-07-25",137.201388888889,"2025-09-01","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16856243961,"Racc de Santes - Don-Sainghin",null,"Lille-Flandres - Impasse D","Lille-St-Sauveur - Jonction 24",2025,2025,30,30,"2025-07-26",137.284722222222,"2025-07-28","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20601762361,"Argenteuil - Le Havre",null,"Asnières-sur-Seine - Bât Voyageurs","Le Stade",2025,2025,30,32,"2025-07-26",137.493055555556,"2025-08-04","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19991149861,"Mantes - Le Havre",null,"Paris-Batignolles - Poste 5","Asnières-sur-Seine - Bât Voyageurs",2025,2025,30,32,"2025-07-27",137.701388888889,"2025-08-04","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16677654961,"Paris - Lille",null,"Boves","Longueau - Direction Lille",2025,2025,31,32,"2025-07-28",137.909722222222,"2025-08-09","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16677673461,"Paris - Lille",null,"Gannes","La Faloise",2025,2025,31,32,"2025-07-28",137.951388888889,"2025-08-09","07:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20595911361,"Strasbourg - St Louis",null,"Mulhouse-Ville - Bât Voyageurs","Mulhouse-Ville - Faisceau",2025,2025,31,32,"2025-07-28",138.159722222222,"2025-08-07","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP33452+33478 (ex 477+478)",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806965361,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,3,50,"2025-07-29",138.284722222222,"2025-09-06","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806962161,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,3,50,"2025-08-01",138.618055555556,"2025-08-09","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806962961,"Argenteuil - Le Havre",null,"Paris-Batignolles - Remblai","Argenteuil - Carré 643",2025,2025,3,50,"2025-08-01",138.659722222222,"2025-08-09","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21512892461,"Argenteuil - Le Havre",null,"Asnières-sur-Seine - Poste 3","Bois-Colombes - Bât Voyageurs",2025,2025,31,32,"2025-08-01",138.868055555556,"2025-08-08","13:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806697561,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,51,44,"2025-08-01",139.076388888889,"2025-08-09","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18214006161,"Paris - Lille",null,"St-Maximin-Marchandises","Creil - Acc/Sort Nord",2025,2025,32,34,"2025-08-04",139.284722222222,"2025-08-23","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177911361,"Metz Ville - Zoufftgen",null,"Thionville - Bât Voyageurs","Thionville - Ac Nord FSC Lux",2025,2025,32,35,"2025-08-04",139.326388888889,"2025-08-29","14:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 6h, Faisceau Luxembourg Thionville (V15 à 29). DP S9C: zep 913,915,917,919,921,923,925,927,929,905,902. DP S11: Sél 340,315,317,319,321,323,325,327,329,330 du SSr Thionville Faisceau Luxembourg.   ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18213812561,"Paris - Lille",null,"Goussainville - Garage","Orry-la-Ville-Coye - Aig Km 35,5",2025,2025,32,34,"2025-08-04",139.534722222222,"2025-08-23","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806708761,"Mantes - Le Havre",null,"Paris-St-Lazare","Asnières-sur-Seine - Poste 3",2025,2025,3,50,"2025-08-11",139.826388888889,"2025-08-30","04:39:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"[SA 2025] Main courante n°120 : pour passage du 13164",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806968561,"Argenteuil - Le Havre",null,"Paris-Batignolles - Poste 5","Argenteuil-Triage - Dépôt du VND",2025,2025,6,44,"2025-08-11",139.993055555556,"2025-08-14","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18542691661,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,33,48,"2025-08-11",140.034722222222,"2025-11-29","05:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16722668561,"Calais - Dunkerque",null,0,0,2025,2025,33,35,"2025-08-11",140.243055555556,"2025-08-30","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine A S33 à 35",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806970161,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,51,46,"2025-08-11",140.451388888889,"2025-08-30","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21569190661,"Novéant - Nancy",null,"Raccordement Pagny-Vandières - RAC côté Paris","Novéant - Bif Km 373,3",2025,2025,33,33,"2025-08-14",140.659722222222,"2025-08-17","18:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes voies à Pagny/Moselle + R1M+R2M.  Accès BM LGV interdit.  TER Nancy<--> Metz supprimés /  TGV Paris <--> Metz supprimés ou via Vieux-Lixheim, rebroussement vers Metz /  Frets Nord <-->Sud via LER-ONV /   TGV Paris <--> Nancy non impactés. Avec 5D_F",null,"Y",null,45454,"Medium","4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16926422161,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bif Côté Rouen",2025,2025,33,34,"2025-08-14",140.701388888889,"2025-08-18","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,4,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20505086961,"Creil - Jeumont",null,"Louvroil","Maubeuge - Poste 2",2025,2025,33,46,"2025-08-15",140.909722222222,"2025-11-12","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine B travaux Quai 2 S30 à 41 et 45 à 50 nuits Fériées 15/16-08-25 et 11/12-11-25  + Impasse M de Maubeuge",null,"Y",null,45454,"Medium",2.5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16925632461,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,33,33,"2025-08-15",141.159722222222,"2025-08-17","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19952048461,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Voie Auxil",2025,2025,33,33,"2025-08-15",141.368055555556,"2025-08-17","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16926366861,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,33,33,"2025-08-15",141.409722222222,"2025-08-17","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16926372861,"Mantes - Le Havre",null,"Mantes-Station","Mantes-la-Jolie - Bât Voyageurs",2025,2025,33,33,"2025-08-15",141.618055555556,"2025-08-17","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16925395661,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,33,33,"2025-08-15",141.826388888889,"2025-08-17","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16926400161,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,33,33,"2025-08-15",142.034722222222,"2025-08-17","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16926378561,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - ITE Aig Est",2025,2025,33,33,"2025-08-15",142.243055555556,"2025-08-17","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21535125861,"Argenteuil - Le Havre",null,"ParisBatignolles - C791","Paris-Batignolles - FSC Formation",2025,2025,33,33,"2025-08-15",142.326388888889,"2025-08-17","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16665137261,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,33,34,"2025-08-15",142.534722222222,"2025-08-18","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"We mise ne service PCD",null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16665176161,"Paris - Lille",null,"Paris-Nord-Souterraine","Paris-Landy - Pleyel",2025,2025,33,34,"2025-08-16",142.743055555556,"2025-08-18","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"We mise en service PCD",null,"Y",null,45454,"Medium","1,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16925653361,"Mantes - Le Havre",null,"Mantes-la-Jolie - Rem Banlieue","Vernon (Eure) - Pancarte Arrêt",2025,2025,33,40,"2025-08-17",142.784722222222,"2025-10-06","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19951614061,"Mantes - Le Havre",null,"Paris-St-Lazare","Paris-Batignolles - Poste 5",2025,2025,33,34,"2025-08-17",142.993055555556,"2025-08-18","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21535041661,"Mantes - Le Havre",null,"Paris-St-Lazare","Paris St Lazare - C374 à C774",2025,2025,33,34,"2025-08-17",143.201388888889,"2025-08-18","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24150014361,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris St Lazare - C374 à C774",2025,2025,33,33,"2025-08-17",143.368055555556,"2025-08-18","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24149990561,"Argenteuil - Le Havre",null,"Paris-St-Lazare","Paris St Lazare - C374 à C774",2025,2025,33,33,"2025-08-17",143.493055555556,"2025-08-18","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177624561,"Mantes - Le Havre",null,0,0,2025,2025,34,39,"2025-08-18",143.701388888889,"2025-09-29","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19954489761,"Argenteuil - Le Havre",null,"ParisBatignolles - C791","Paris-Batignolles - Voie Auxil",2025,2025,34,35,"2025-08-18",143.909722222222,"2025-08-29","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23345892461,"Pontoise - Serqueux",null,0,"Gisors - Garage",2025,2025,34,43,"2025-08-18",144.118055555556,"2025-10-24","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23345881561,"Pontoise - Serqueux",null,0,"Gisors - Garage",2025,2025,34,43,"2025-08-18",144.159722222222,"2025-10-24","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16942518561,"No encontrado",null,"Lens - Poste 3","Pont-de-Sallaumines - Bât Voyageurs",2025,2025,34,34,"2025-08-23",144.368055555556,"2025-08-24","10:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine B",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24203432661,"Argenteuil - Le Havre",null,"Mantes-Station","Mantes-la-Jolie - Bât Voyageurs",2025,2025,34,34,"2025-08-23",144.659722222222,"2025-08-24","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24203316761,"Argenteuil - Le Havre",null,"Gargenville","Mantes-la-Jolie - Bât Voyageurs",2025,2025,34,34,"2025-08-23",144.826388888889,"2025-08-24","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19954554761,"Argenteuil - Le Havre",null,"ParisBatignolles - C791","Paris-Batignolles - Voie Auxil",2025,2025,34,35,"2025-08-23",144.868055555556,"2025-08-30","15:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24202840761,"Mantes - Le Havre",null,"Les Mureaux - Faisceau RNUR","Épône-Mézières - Carré Violet167",2025,2025,34,34,"2025-08-23",145.076388888889,"2025-08-24","12:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22827097061,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Côté Rouen","Mantes-la-Jolie - Jo IPCS Km 59,4",2025,2025,34,36,"2025-08-24",145.284722222222,"2025-09-08","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799248961,"Paris - Strasbourg",null,"Frouard - Accès Nord","Nancy-Ville - Bât Voyageurs",2025,2025,2,38,"2025-08-25",145.493055555556,"2025-09-20","05:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"De Toul à Réding les gares intermédiaires (FR, CHG, NY, JA, VAR, BLV, LNE) seront privées d´alimentation électrique si des consignations caténaires des sous-secteurs encadrants sont accordées simultanément. Modif des horaires pour passage du TER 837586. ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16709151861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,2,50,"2025-08-25",145.534722222222,"2025-12-06","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23384631061,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,35,50,"2025-08-25",145.743055555556,"2025-12-13","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"la caténaire doit être rendue à 04h45 pour la préparation du matériel ligne K",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18542927461,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,35,50,"2025-08-25",145.951388888889,"2025-12-13","05:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23384631061,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,35,50,"2025-08-25",146.201388888889,"2025-09-27","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"la caténaire doit être rendue à 04h45 pour la préparation du matériel ligne K",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",18542929461,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,35,50,"2025-08-25",146.243055555556,"2025-09-27","05:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16759350761,"Creil - Jeumont",null,"Honnechy - Bif Honnechy","Le Cateau",2025,2025,35,40,"2025-08-25",146.451388888889,"2025-10-04","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16985386861,"Creil - Jeumont",null,"Montescourt","St-Quentin - Poste 1",2025,2025,35,35,"2025-08-25",146.659722222222,"2025-08-30","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16722526561,"Graffenstaden - Hausbergen",null,"Graffenstaden - Bif","Hausbergen-Triage - Point P",2025,2025,35,47,"2025-08-25",146.868055555556,"2025-11-21","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16630018661,"Strasbourg - St Louis",null,"Mulhouse-Dornach - Jct Aig 723","Mulhouse-Ville - Faisceau",2025,2025,35,36,"2025-08-25",146.909722222222,"2025-09-06","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP33420+33424+33441+33442 (ex 420+435+437+438)",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19951136661,"Paris - Strasbourg",null,"Vendenheim - Voies 3/5","Hausbergen-Triage - Aiguille 495,1",2025,2025,35,35,"2025-08-25",147.076388888889,"2025-08-30","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP825+829+831+839",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16626873161,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,35,42,"2025-08-29",147.368055555556,"2025-09-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"we suppression Dr 7721 et 7722",null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16923812561,"Racc de Santes - Don-Sainghin",null,"Haubourdin - Bif Haubourdin","Don-Sainghin - Bât Voyageurs",2025,2025,35,35,"2025-08-30",147.576388888889,"2025-08-31","14:36:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16923570661,"Don-Sainghin - Lens",null,"Loison","Don-Sainghin - Bât Voyageurs",2025,2025,35,35,"2025-08-30",147.618055555556,"2025-08-31","14:36:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806864961,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,2,50,"2025-09-01",147.826388888889,"2025-10-11","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Générique longue non activée. Refus PCAST de datation pour les S52 et S1.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16708426361,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,2,50,"2025-09-01",148.034722222222,"2025-10-11","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805693761,"Paris - Strasbourg",null,"Lagny-Thorigny","Meaux - ITE ZI",2025,2025,8,47,"2025-09-01",148.243055555556,"2025-09-05","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Ajout 2 semaines pour 17166 mise en cohérence domaines S9 S11",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16593976061,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Hirson","Tournes",2025,2025,9,44,"2025-09-01",148.409722222222,"2025-10-31","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP LIART - CHARLEVILLE voie 1 + Consignation des S.el 15+17+19 SSR ROUVROY L'ECHELLE - CHARLEVILLE V1  + Consignation longue durée Sel 105 du Ssr Rouvroy L'échelle - Charleville en gare de Tournes pour dépotage TTx",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16594016861,"Mohon - Charleville-Mézière",null,"Reims - Bif L2/Rac 3","Mohon - Bât Voyageurs",2025,2025,14,44,"2025-09-01",148.534722222222,"2025-09-05","06:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16759012161,"Creil - Jeumont",null,"Tergnier - Accès Nord","St-Quentin - ITE ZI",2025,2025,36,36,"2025-09-01",148.743055555556,"2025-09-06","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16986575361,"Longueau - Boulogne",null,"St-Roch (Somme) - Bif et Poste 1","Abbeville - SBAPR303",2025,2025,36,37,"2025-09-01",148.951388888889,"2025-09-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16759036761,"Creil - Jeumont",null,"Busigny - Bif Sud","Le Cateau",2025,2025,36,36,"2025-09-01",148.993055555556,"2025-09-06","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16167828561,"Paris - Strasbourg",null,"Vendenheim - Voies 3/5","Strasbourg-Ville - Voies 35/36",2025,2025,36,48,"2025-09-01",149.201388888889,"2025-11-29","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP830+834+836+825+829+831+839+841",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16688055761,"Paris - Lille",null,"Douai - Bif de St-Éloi","Douai - Bât Voyageurs",2025,2025,36,36,"2025-09-01",149.409722222222,"2025-09-06","05:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16857155461,"Strasbourg - St Louis",null,"Rixheim - Bif","Habsheim - Bât Voyageurs",2025,2025,36,36,"2025-09-02",149.493055555556,"2025-09-03","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",2.2999999999999998,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16857201461,"Strasbourg - St Louis",null,"Rixheim - Bif","Habsheim - Bât Voyageurs",2025,2025,36,36,"2025-09-04",149.701388888889,"2025-09-06","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19072856161,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,36,38,"2025-09-05",149.909722222222,"2025-09-15","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16560200561,"Metz - Reding",null,0,"Sarraltroff - Bif",2025,2025,36,45,"2025-09-06",150.118055555556,"2025-11-09","06:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22827090761,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Côté Rouen","Mantes-la-Jolie - Jo IPCS Km 59,4",2025,2025,36,36,"2025-09-06",150.326388888889,"2025-09-07","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16560180561,"Paris - Strasbourg",null,"Réding - FSC Pair","Saverne",2025,2025,36,45,"2025-09-06",150.368055555556,"2025-11-09","06:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799362561,"Longuyon - Onville",null,"Conflans-Jarny - Bif L12/L5 D V","Pagny-sur-Moselle - Poste 3",2025,2025,36,36,"2025-09-07",150.576388888889,"2025-09-08","03:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"04h05 simultanées nuit de DI/LU. Re-paramétrage Mistral CCR Lorraine. Interdiction de circulation dans la zone d´action des PAI de Pagny et Metz. Décalage horaire. Fenêtres déformées simultanément sur lignes 89000 + 95000 + 140000 + 180000 + 191300 + 1920",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16708572961,"Paris - Hirson",null,"Paris-La Chapelle - Voie VSE/153","Laon - Poste 2",2025,2025,2,50,"2025-09-08",150.826388888889,"2025-09-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16724599061,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Mézy - Poste U",2025,2025,36,40,"2025-09-08",151.034722222222,"2025-10-03","16:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV type G 218 V2 de Château Thierry zone de Mézy et Consignation C sous secteur Château Mézy V2",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16362684061,"St Just en Chaussée - Douai",null,0,"Sancourt",2025,2025,37,41,"2025-09-08",151.076388888889,"2025-10-10","16:00:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null," Domaine C en continu de S37 à S41 (Quai 3 fermé en continu également) + Toutes les VS des garages en continu du Lu 08h00 au Ve 16h00 (pendant ITC Domaine C en continu S37 à 41) = Domaine G",null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177734561,"Metz Ville - Zoufftgen",null,"Hagondange - Aig ITE","Uckange - Ano Km 181,3",2025,2025,37,40,"2025-09-08",151.284722222222,"2025-10-03","17:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 27678, 8h30 jour, V1B+V2B entre Hagondange et Uckange P2. Avec 5D_UCK_023 et 4D_UCK-THL_014.  Report circulations sur V1+V2 entre Hagondange et Thionville. Rac Mondelange interdit (Thionville, Ebange <-->Rac<-->Conflans interdit).   ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16824914861,"Paris - Strasbourg",null,"Sarrebourg","Réding - FSC Pair",2025,2025,37,37,"2025-09-08",151.493055555556,"2025-09-09","03:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP1857+1860+1862",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16168456061,"Paris - Strasbourg",null,"Vendenheim - Jonct V1B/VD","Strasbourg-Ville - Voies 35/36",2025,2025,37,37,"2025-09-08",151.701388888889,"2025-09-13","04:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP837",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16818649361,"Paris - Lille",null,"Paris-Nord-Surface","St-Denis - Jonction Sud",2025,2025,37,37,"2025-09-08",151.743055555556,"2025-09-13","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC IND",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805759161,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2025,2025,51,50,"2025-09-08",151.951388888889,"2025-09-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL bif Gagny degagé",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16819951061,"Paris - Strasbourg",null,"Vendenheim - Voies 3/5","Vendenheim - Jonct V1B/VD",2025,2025,37,37,"2025-09-11",152.118055555556,"2025-09-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP824+826+830",null,"Y",null,45454,"Medium",4,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16149378461,"Metz - Lérouville",null,"Novéant - Bif Km 338,9","Ars-sur-Moselle",2025,2025,37,44,"2025-09-13",152.409722222222,"2025-11-03","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Def 6h nuit, V1+V2+V1B+V2B entre ARS et NEN. Avec 5D_LER-NEN_004, 5C_PMO-NEN_004 et 5C_PMO_002. Noveant<-->Metz interdit pendant 6h. Trafic Nord<-->Sud possible par Conflans avec rebroussement.",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16149856761,"Novéant - Nancy",null,"Pagny-sur-Moselle - Rac côté Metz","Novéant - Bif Km 373,3",2025,2025,37,44,"2025-09-13",152.451388888889,"2025-11-03","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 6h nuit, V1+V2 à PMO. Avec 5D_LER-NEN_004, 5D_PMO-NEN_004 et 5D_NEN-MZS_004 qui reprend les conséquences circulations.",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15813054161,"Calais - Boulogne",null,"Wimille-Wimereux","Calais-Fréthun - C102/204",2025,2025,2,50,"2025-09-15",152.659722222222,"2025-09-20","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"modification horaire suite évol capa du sa2024, faite le 16/11/21 par LL.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16724617861,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Épernay - Bât Voyageurs",2025,2025,18,40,"2025-09-15",152.868055555556,"2025-09-26","16:28:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV type G 218 V2 de Château Thierry zone de Mézy et Consignation C sous secteur Château Mézy V2",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16601522661,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Vitry-la-Ville - Bât Voyageurs",2025,2025,38,44,"2025-09-15",153.076388888889,"2025-10-31","16:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"V1 L07000 DFV type G sur ZEP 25 + Type L Chalons -Vitry la Ville - Ss Chalons - Mairy V1   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16601544561,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Vitry-la-Ville - Songy Évit Pair",2025,2025,38,44,"2025-09-15",153.118055555556,"2025-10-31","16:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"V1 L07000 DFV type G sur ZEP 25 + Type L Chalons -Vitry la Ville - Ss Chalons - Mairy V1",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16819170561,"Strasbourg - St Louis",null,"Colmar - ITE ZI","Colmar - Faisceau",2025,2025,38,38,"2025-09-15",153.451388888889,"2025-09-16","00:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP722+724",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16819136561,"Strasbourg - St Louis",null,"Colmar - ITE ZI","Colmar - Accès Nord",2025,2025,38,38,"2025-09-15",153.576388888889,"2025-09-16","00:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP720+722",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20486285361,"Strasbourg - St Louis",null,"Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - Frontière Fr-Su",2025,2025,38,39,"2025-09-16",153.784722222222,"2025-09-27","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Pour essais dynamiques.",null,"Y",null,45454,"High","2,3,4,5,6",null,null,"St-Louis (Haut-Rhin) - Frontière Fr-Su",null,null,"Planned",0]
[null,"SNCF-R",16819199061,"Strasbourg - St Louis",null,"Colmar - Ent/Sort V3àV5","Colmar - Faisceau",2025,2025,38,38,"2025-09-16",153.826388888889,"2025-09-17","00:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP723+725+727",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805674961,"Paris - Strasbourg",null,"Bondy - Bât Voyageurs","Gagny - Aig V2Bis/V2Ter",2025,2025,20,39,"2025-09-18",154.034722222222,"2025-09-23","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Ombre de la DEF MEGA ZEP                       ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17997885761,"Paris - Strasbourg",null,0,"Bondy - Bât Voyageurs",2025,2025,38,38,"2025-09-18",154.243055555556,"2025-09-20","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",4.5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16724654361,"Paris - Strasbourg",null,"Château-Thierry - Bât Voyageurs","Épernay - Bât Voyageurs",2025,2025,38,38,"2025-09-19",154.451388888889,"2025-09-21","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV type G 218 V2 de Château Thierry zone de Mézy et Consignation C sous secteur Château Mézy V2",null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16722317461,"Mantes - Le Havre",null,"Rouen-Rive-Droite - IPCS Km 142,9","Motteville - Bif Auzouville",2025,2025,38,43,"2025-09-19",154.534722222222,"2025-10-25","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16923800961,"Paris - Lille",null,"Paris-Nord - Portique Landy","St-Denis - Garages Pairs",2025,2025,38,38,"2025-09-19",154.743055555556,"2025-09-20","08:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE 38/39",null,"Y",null,45454,"Medium",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16923798461,"Paris - Lille",null,"Paris-Landy - Pleyel","St-Denis - Garages Impairs",2025,2025,38,38,"2025-09-19",154.951388888889,"2025-09-20","08:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE 38/39",null,"Y",null,45454,"Medium",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177998561,"Thionville - Mohon",null,"Longuyon - Bif","Thionville - Bif L3/L7",2025,2025,38,40,"2025-09-20",155.159722222222,"2025-10-05","14:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 14396, V1+V2, 6h jour, SA et DI, Longuyon-Thionville. Détournement frets via CJ.",null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16834369461,"Longuyon - Onville",null,"Raccordement Pagny-Vandières - RAC côté Paris","Novéant - Bif Km 373,3",2025,2025,38,38,"2025-09-20",155.201388888889,"2025-09-21","06:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 7h nuit dans toute la gare de Pagny/Moselle. Avec 5D_FR-PMO_010 qui reprend les conséquences circulations.",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16249851261,"Paris - Strasbourg",null,"Lutzelbourg - IPCS","Saverne - Aiguille Est",2025,2025,38,38,"2025-09-20",155.409722222222,"2025-09-21","06:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP810+812+816",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16250202361,"Paris - Strasbourg",null,"Dettwiller - Bât Voyageurs","Mommenheim - Accès Est",2025,2025,38,43,"2025-09-21",155.618055555556,"2025-10-26","22:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP952+954 Sel 12+102+104 SSr Wilwisheim-Mommenheim voie 2  Pk en fonction du SSr",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16660492761,"Paris - Lille",null,"Paris-La Chapelle - Carré 423","Paris-Nord - JCT DR/RT",2025,2025,38,39,"2025-09-21",155.868055555556,"2025-09-22","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE CDG com 6031a/b et 6035 + WE Régé cat",null,"Y",null,45454,"Medium",1.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15799383761,"Metz - Reding",null,"Sarraltroff - Bif","Rémilly - Bif L3/L11",2025,2025,9,50,"2025-09-22",155.909722222222,"2025-09-23","05:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16144492461,"Longuyon - Onville",null,"Conflans-Jarny - Bif L12/L5 D V","Onville - Rac Confl-Jarny",2025,2025,39,44,"2025-09-22",156.118055555556,"2025-10-31","18:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5D_LGN-CJ_002 et 5C_CJ_002 qui reprend les conséquences circulations.",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21483394161,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,39,40,"2025-09-22",156.326388888889,"2025-10-03","16:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16819475561,"Strasbourg - St Louis",null,"Lutterbach (Haut-Rhin) - Bif","Mulhouse-Ville - Aiguille Voie M",2025,2025,39,39,"2025-09-22",156.534722222222,"2025-09-23","00:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP903+400+402+404+406+408",null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16250212161,"Paris - Strasbourg",null,"Lutzelbourg - IPCS","Saverne - Aiguille Est",2025,2025,39,39,"2025-09-22",156.576388888889,"2025-09-25","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP810+812+816",null,"Y",null,45454,"Medium","1,2,3",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16818625361,"Strasbourg - St Louis",null,"Rixheim - Bât Voyageurs","St-Louis (Haut-Rhin) - Faisceau",2025,2025,39,39,"2025-09-23",156.784722222222,"2025-09-24","00:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP923+921+917",null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21483390261,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Côté Rouen","Vernon (Eure) - Poste 1",2025,2025,39,39,"2025-09-27",156.993055555556,"2025-09-28","16:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17603469661,"Paris - Strasbourg",null,"Dettwiller - Bât Voyageurs","Mommenheim - Accès Est",2025,2025,39,39,"2025-09-28",157.243055555556,"2025-09-28","22:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP945+947+957 SSr Wilwisheim-Mommenheim voie 1  Pk en fonction du SSr",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16161510161,"Paris - Strasbourg",null,"Trilport - Bif de Germigny","La Ferté-sous-Jouarre - Aig Km 63,6-Év",2025,2025,1,48,"2025-09-29",157.284722222222,"2025-10-01","04:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"17/10/2023 (DAC) : Vibration suite main courante n° 104/2025. 23/11/2022 (DAC) : Création de fenêtre générique élargie pour maintenance suite concertation 2025. Trilport - LFJ (exclue) Train ouvrant : 56622 (voir Variante correspondante) Train fermant : 5",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788897561,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Blesme-Haussignemont - Bât Voyageurs",2025,2025,11,44,"2025-09-29",157.493055555556,"2025-10-17","14:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16263433461,"Paris - Strasbourg",null,"Bondy - Bât Voyageurs","Le Raincy-Villemomble-Montferm",2025,2025,40,40,"2025-09-29",157.701388888889,"2025-10-01","14:48:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"2L1 : ZEP 742,744 CHL (aig. 2660a, 2664b, 2745a).  29/11/2022 (DAC) : transformation des DEF en FEN suite concertation génériques 2025.",null,"Y",null,45454,"Medium","1,2,3",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16925814761,"Paris - Lille",null,"Paris-Nord - Bât Voyageurs","Paris-Nord - Jonction Km 0,9",2025,2025,40,50,"2025-09-29",157.909722222222,"2025-12-13","23:59:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,"GEL 1/2 quai V10",null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16926133961,"Paris - Lille",null,"Paris-Nord - Bât Voyageurs","Paris-Nord - Jonction Km 0,9",2025,2025,40,50,"2025-09-29",157.951388888889,"2025-12-12","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16992757861,"Hirson - Liart",null,"Hirson - Bif de Buire",0,2025,2025,9,44,"2025-10-01",158.159722222222,"2025-10-03","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16593980461,"Tournes - Charleville-Mézière",null,"Charleville-Mézières - Rac Côté Hirson","Tournes",2025,2025,9,44,"2025-10-01",158.284722222222,"2025-10-03","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP CHARLEVILLE - LIART voie 2 + Sel 14+16 SSR ROUVROY L'ECHELLE CHARLEVILLE  VOIE 2",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16735483161,"Mantes - Le Havre",null,0,0,2025,2025,40,40,"2025-10-03",158.618055555556,"2025-10-05","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16543430261,"Creil - Jeumont",null,"Fresnoy-le-Grand - Km 171,3","Busigny - Marchandises",2025,2025,40,40,"2025-10-04",158.659722222222,"2025-10-05","14:21:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16525696061,"Paris - Strasbourg",null,"Champigneulles - Aig Km 345,7","Champigneulles - Accès Est",2025,2025,40,40,"2025-10-04",158.868055555556,"2025-10-05","07:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5D_FR-NY_005",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16525850861,"Paris - Strasbourg",null,"Champigneulles - Aig Km 345,7","Champigneulles - Accès Est",2025,2025,40,40,"2025-10-05",159.076388888889,"2025-10-06","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Avec 5D_FR-NY_006",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",25058497261,"Thionville - Mohon",null,"Lumes","Donchery",2025,2025,40,41,"2025-10-06",159.284722222222,"2025-10-10","16:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV Type G Voie 1 sur ZEP 655 et 657 de Lumes  Consignation du sous-secteur Mohon-Donchery voie 1",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16688993761,"St Just en Chaussée - Douai",null,"Cantin","Douai - Bif de Sin",2025,2025,41,43,"2025-10-06",159.326388888889,"2025-10-25","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16250698461,"Paris - Strasbourg",null,"Dettwiller - Bât Voyageurs","Mommenheim - Accès Est",2025,2025,41,45,"2025-10-06",159.576388888889,"2025-11-05","23:42:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP952+954 Sel 12+102+104 SSr Wilwisheim-Mommenheim voie 2  Pk en fonction du SSr",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16629487661,"Strasbourg - St Louis",null,"Mulhouse-Ville - Bât Voyageurs","Rixheim - Bif",2025,2025,41,41,"2025-10-09",159.784722222222,"2025-10-10","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP33452+33478+33482+33494 (ex 477+478+488+542)",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16945471661,"Mantes - Le Havre",null,"Mantes-la-Jolie - Rem Banlieue","Rosny-sur-Seine",2025,2025,41,46,"2025-10-10",159.993055555556,"2025-11-12","04:00:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16949414061,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,41,42,"2025-10-10",160.034722222222,"2025-10-13","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16945403461,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,41,46,"2025-10-10",160.243055555556,"2025-11-12","04:00:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16945152161,"Argenteuil - Le Havre",null,"Limay - Port-de-Paris","Mantes-la-Jolie - Bif Argenteuil",2025,2025,41,46,"2025-10-10",160.451388888889,"2025-11-12","04:00:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22837674961,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Épône-Mézières - SG",2025,2025,41,42,"2025-10-10",160.659722222222,"2025-10-13","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16941687561,"Argenteuil - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,41,42,"2025-10-10",160.701388888889,"2025-10-13","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810452261,"Mantes - Le Havre",null,"Sotteville - Carré 354h","Rouen-Rive-Droite",2025,2025,1,49,"2025-10-11",160.951388888889,"2025-10-11","05:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Restitution caténaire à 4H00 pour réalimenter les Poste G et H lorsque la zone est totalement coupée électriquement",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16941136561,"Mantes - Le Havre",null,"Les Mureaux - Faisceau RNUR","Épône-Mézières - Bât Voyageurs",2025,2025,41,49,"2025-10-11",161.159722222222,"2025-12-07","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16924894061,"Paris - Lille",null,"Paris-Nord - Jonction Km 0,9","St-Denis - Jonction Sud",2025,2025,41,49,"2025-10-11",161.368055555556,"2025-12-07","08:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE 41/42 à 49/50",null,"Y",null,45454,"High",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16925187861,"Paris - Lille",null,"Paris-Nord - Portique Landy","St-Denis - Jonction Sud",2025,2025,41,49,"2025-10-11",161.409722222222,"2025-12-07","08:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"WE 41/42 à 49/50",null,"Y",null,45454,"High",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16942022961,"Mantes - Le Havre",null,"non trouvé","Épône-Mézières - SG",2025,2025,41,41,"2025-10-12",161.618055555556,"2025-10-13","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15786379761,"Thionville - Mohon",null,"Sedan - Garages","Longuyon - Bât Voyageurs",2025,2025,6,49,"2025-10-13",161.826388888889,"2025-10-24","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787633861,"Paris - Strasbourg",null,"Épernay - Rac Côté Oiry","Châlons-en-Champagne - Accès Triage",2025,2025,41,46,"2025-10-13",162.034722222222,"2025-11-07","14:13:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"06/06/2023 (DAC) : Ajustement horaire au PK fin (839133//839103).",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15787630361,"Paris - Strasbourg",null,"Épernay - Poste 1","Châlons-en-Champagne - Bât Voyageurs",2025,2025,41,46,"2025-10-13",162.118055555556,"2025-10-13","14:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"13/10/2023 (DAC) : Rectification des horaires de fin saisis à l'envers, suite retour PQCP. 24/11/2022 (DAC) : Ajustement horaire suite concertation génériques 2025 (839136\\\\839154).  Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  ",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16879736361,"Longueau - Boulogne",null,"Boulogne-Ville - Bif d'Outreau","non trouvé",2025,2025,42,50,"2025-10-13",162.326388888889,"2025-12-13","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16678066061,"Paris - Lille",null,"Boves","Longueau - Direction Lille",2025,2025,42,44,"2025-10-13",162.534722222222,"2025-11-01","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16525996761,"Paris - Strasbourg",null,"Ernécourt-Loxéville - Aig Km 276,9","Lérouville - Aig Km 290,4",2025,2025,42,42,"2025-10-13",162.743055555556,"2025-10-18","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Prolongement fen GEN 89000 pour B2N. Accès FAP Lérouville interdit.                                                                                                                          ",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16525938461,"Metz - Lérouville",null,"Lérouville - Bât Voyageurs","Lérouville - Rac Côté Metz",2025,2025,42,42,"2025-10-13",162.784722222222,"2025-10-18","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Prolongement fen GEN 89000 pour B2N. Accès FAP Lérouville interdit.",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16950241261,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bif Argenteuil",2025,2025,42,45,"2025-10-13",162.993055555556,"2025-11-08","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16950016761,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,42,45,"2025-10-13",163.118055555556,"2025-11-08","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20008606261,"Thionville - Mohon",null,"Lumes","Donchery",2025,2025,42,44,"2025-10-13",163.451388888889,"2025-10-31","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862410961,"Mohon - Charleville-Mézière",null,"Fismes","Reims - Bif L2/L22-5",2025,2025,42,42,"2025-10-13",163.493055555556,"2025-10-17","12:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"MàJ du par P KERGUIGNAS du 13-01-2023 suite à demande de l'ICA P Maslach (Découpage de la Générique) 10/07/2020 Mise à jour par PK DT GE suite confirmation par D LORIOT RCST de l'accord de ZP par mail du 10-07-2020  Régime pendant les vacances scolaires (",null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16789398361,"Thionville - Mohon",null,"Mohon - Bif L2","Lumes-Triage - ITE Citroën",2025,2025,42,44,"2025-10-15",163.701388888889,"2025-10-31","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP 265+267 MOHON + ZEP 652 LUMES  SEL 30+32",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16530504761,"Mantes - Le Havre",null,"Bif de Darnétal - Rac 2","Rouen-Rive-Droite",2025,2025,42,50,"2025-10-17",163.909722222222,"2025-12-13","06:05:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",5,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16971771361,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,42,43,"2025-10-17",164.118055555556,"2025-10-26","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16924567961,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Épône-Mézières - Carré Violet167",2025,2025,42,43,"2025-10-17",164.159722222222,"2025-10-26","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16879804461,"Calais - Boulogne",null,"non trouvé",0,2025,2025,42,43,"2025-10-18",164.368055555556,"2025-10-26","13:21:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16971584461,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,42,49,"2025-10-18",164.659722222222,"2025-12-07","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20864219061,"Mulhouse - Chalampé",null,"Mulhouse-Ville - Aig Km 110","Mulhouse-Ville - Point D",2025,2025,42,42,"2025-10-18",164.826388888889,"2025-10-19","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP33499",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177964161,"Ceinture de Metz",null,"Metz-Sablon - Faisceau","Metz-Ville - Dépôt",2025,2025,42,42,"2025-10-19",164.868055555556,"2025-10-20","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap 5h50 nuit DI/LU sur voies V1+V2+1Bis3-1Bis11+2Bis3+1R+2R Zone Metz-Sablon AO. Accès Metz-Ville côté Novéant interdit. Accès Faisceau Montigny possible, Accès FRE possible côté Rémilly.  Possibilité de venir de Novéant V1B, puis via faisceau Montigny-M",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16974748261,"Mantes - Le Havre",null,"Mantes-la-Jolie - Rem Banlieue","Vernon (Eure) - Pancarte Arrêt",2025,2025,42,43,"2025-10-19",165.076388888889,"2025-10-27","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16971810761,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,42,43,"2025-10-19",165.284722222222,"2025-10-27","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15812955961,"Racc de Santes - Don-Sainghin",null,"Lille-St-Sauveur - Carre Violet 40","Haubourdin - Bif de Tortue",2025,2025,2,46,"2025-10-20",165.493055555556,"2025-11-17","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15862548761,"Mohon - Charleville-Mézière",null,"Charleville-Mézières - Bât Voyageurs","Givet - Bât Voyageurs",2025,2025,7,44,"2025-10-20",165.534722222222,"2025-10-31","17:33:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"MàJ Par P KERGUIGNAS du 08-07-2021 suite demandes DL CA relatives au RP0 CHA16_009644 et CHA16_010102 pour passage du 838835  Travaux à réaliser pendant les vacances scolaires (ou hors période de vacances scolaires avec restitution le ME à 12h).     Train",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15806972561,"Argenteuil - Le Havre",null,"Paris-Batignolles - Poste 5","Argenteuil - Carré 643",2025,2025,43,45,"2025-10-20",165.743055555556,"2025-11-08","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16842963661,"Paris - Lille",null,"St-Just-en-Chaussée - Voie 4","Gannes",2025,2025,43,46,"2025-10-24",165.993055555556,"2025-11-10","04:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16518065061,"Metz Ville - Zoufftgen",null,"Thionville - Ac Nord FSC Lux","Zoufftgen (IE) - Frontière Fr-Lu",2025,2025,43,47,"2025-10-26",166.201388888889,"2025-11-24","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Exercice OMEGA Black Out",null,"Y",null,45454,"Medium",7,null,null,"Zoufftgen (IE) - Frontière Fr-Lu",null,null,"Planned",0]
[null,"SNCF-R",15804006161,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,2,50,"2025-10-27",166.243055555556,"2025-11-29","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES (Aulnay complet) ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16788897561,"Paris - Strasbourg",null,"Châlons-en-Champagne - Bif 1-26","Blesme-Haussignemont - Bât Voyageurs",2025,2025,11,44,"2025-10-27",166.451388888889,"2025-10-31","14:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20533255561,"Paris - Strasbourg",null,"Chelles-Gournay - Aig côté Gagny","Vaires-Torcy - Aig Côté Chelle",2025,2025,44,50,"2025-10-27",166.659722222222,"2025-12-13","04:55:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV sur ZEP type G 1531 VAI P5. DFV sur ZEP type G 1538 VAI P5",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16980119861,"Paris - Lille",null,"Boves","Longueau - Bât Voyageurs",2025,2025,44,44,"2025-10-27",166.868055555556,"2025-11-01","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17009804561,"No encontrado",null,"Châlons-en-Champagne - Accès Triage",0,2025,2025,44,44,"2025-10-27",167.076388888889,"2025-10-31","15:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16139936761,"Toul - Culmont Chalindrey",null,"Culmont-Chalindrey - Bif Chaudenay","Neufchâteau - CV 217",2025,2025,44,50,"2025-10-27",167.159722222222,"2025-12-12","16:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf 7h, V1+V2 entre Chalindrey (exclu) et Neuchateau (exclu).",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20931866861,"Paris - Hirson",null,"Le Bourget-Triage - Poste 2","Laon - Poste 2",2025,2025,44,49,"2025-10-31",167.368055555556,"2025-12-08","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"extension de nuit sur le WE",null,"Y",null,45454,"High","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22844464061,"Mantes - Le Havre",null,"Mantes-la-Jolie - Rem Banlieue","Vernon (Eure) - Pancarte Arrêt",2025,2025,44,44,"2025-11-01",167.576388888889,"2025-11-02","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22844470861,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,44,44,"2025-11-01",167.618055555556,"2025-11-02","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22844467061,"Mantes - Le Havre",null,"Mantes-la-Jolie - Rem Banlieue","Vernon (Eure) - Pancarte Arrêt",2025,2025,44,44,"2025-11-02",167.826388888889,"2025-11-03","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23097867961,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bif Argenteuil",2025,2025,44,44,"2025-11-02",168.034722222222,"2025-11-02","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23098497061,"Argenteuil - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,44,44,"2025-11-02",168.201388888889,"2025-11-02","04:20:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803944761,"Paris - Hirson",null,"Le Bourget-Triage - Poste 3","Laon - Poste 2",2025,2025,2,50,"2025-11-03",168.326388888889,"2025-11-29","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES   ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16722327361,"Calais - Dunkerque",null,"Dunkerque-Grande-Synthe - Poste 6","Loon-Plage",2025,2025,45,47,"2025-11-03",168.534722222222,"2025-11-22","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine B S45 à 47 + Voies 1 à 14 (GR1 et GR2) Faisceau Réception entre P7 et P8",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23097827761,"Mantes - Le Havre",null,"Mantes-la-Jolie - ITE Aig Ouest","Mantes-la-Jolie - Bât Voyageurs",2025,2025,45,45,"2025-11-03",168.743055555556,"2025-11-03","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23097860361,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,45,45,"2025-11-03",168.951388888889,"2025-11-03","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23096987961,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,45,45,"2025-11-03",168.993055555556,"2025-11-03","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805759161,"Paris - Strasbourg",null,"Le Raincy-Villemomble-Montferm","Gagny - Bif GC/Ligne 1",2025,2025,51,50,"2025-11-03",169.201388888889,"2025-11-15","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Aligné Mega ZEP TOUT CHL bif Gagny degagé",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16981059661,"Mantes - Le Havre",null,"Vernon (Eure) - Poste 1","Gaillon-Aubevoye - Poste 1",2025,2025,45,46,"2025-11-07",169.493055555556,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16530574361,"Mantes - Le Havre",null,"Bif de Darnétal - Rac 2","Rouen-Rive-Droite",2025,2025,45,47,"2025-11-07",169.659722222222,"2025-11-23","17:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16981023861,"Mantes - Le Havre",null,"Mantes-la-Jolie - Rem Banlieue","Rosny-sur-Seine",2025,2025,45,46,"2025-11-07",169.701388888889,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23104345561,"Argenteuil - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,45,50,"2025-11-07",169.909722222222,"2025-12-13","23:59:00",null,"continuous","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major",null,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16980431361,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,45,46,"2025-11-07",170.118055555556,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16980420761,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,45,46,"2025-11-07",170.326388888889,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16980403961,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,45,46,"2025-11-07",170.368055555556,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16939578661,"Racc de Santes - Don-Sainghin",null,"Haubourdin - Bif Haubourdin","Don-Sainghin - Bât Voyageurs",2025,2025,45,45,"2025-11-08",170.618055555556,"2025-11-09","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16646884961,"Mulhouse - Chalampé",null,"Mulhouse-Ville - Aig Km 110","Mulhouse-Ville - Point D",2025,2025,45,45,"2025-11-08",170.826388888889,"2025-11-09","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP33499",null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16980227461,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage","Vernouillet-Verneuil - Triage Accès OE",2025,2025,45,46,"2025-11-09",171.034722222222,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16980161061,"Mantes - Le Havre",null,"Poissy - Bât Voyageurs","Mantes-la-Jolie - E/S VC PARIS",2025,2025,45,46,"2025-11-09",171.076388888889,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15803964761,"Paris - Lille",null,"St-Denis - Joncherolles","Goussainville - Garage",2025,2025,2,50,"2025-11-10",171.284722222222,"2025-11-29","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC INDUSTRIELLES ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16722523161,"Calais - Dunkerque",null,"Dunkerque-Grande-Synthe - Poste 6","Loon-Plage",2025,2025,46,46,"2025-11-10",171.493055555556,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Domaine B ITC de 30h00 + Voies 1 à 14 (GR1 et GR2) Faisceau Réception entre P7 et P8",null,"Y",null,45454,"Medium","1,2,3",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177664161,"Metz - Reding",null,"Rémilly - Bât Voyageurs","Metz-Ville - Quai Est",2025,2025,46,50,"2025-11-10",171.701388888889,"2025-12-13","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf V1+V2 entre Metz Ville et Rémilly BV. Suppression TER, détournements TGV. Décalage ou Détournement des trafics frets internationaux de/vers Forbach via Thionville-Béning. Détournement des trafics frets de/vers Alsace via Nancy-Lunéville.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16333514861,"Metz - Reding",null,"Metz-Sablon - Jonct V2/V2R","Metz-Ville - Poste 66 CTS2",2025,2025,46,50,"2025-11-10",171.743055555556,"2025-12-13","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Déf V1+V2 entre Metz AE et Metz-Ville. Avec 5D_RMI-MZ_010 qui reprend les conséquences circulations.",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16979054361,"Mantes - Le Havre",null,"Poissy - C4147","Villennes-sur-Seine",2025,2025,46,46,"2025-11-10",171.909722222222,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16978889561,"Mantes - Le Havre",null,"Sartrouville - Bât Voyageurs","Maisons-Laffitte - Bât Voyageurs",2025,2025,46,46,"2025-11-10",172.201388888889,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16826950761,"Paris - Lille",null,"Garges","Villiers-le-Bel-Gonesse - Bif de Gonesse",2025,2025,46,48,"2025-11-10",172.409722222222,"2025-11-29","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ITC IND",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16978913161,"Mantes - Le Havre",null,"Sartrouville - Bât Voyageurs","Sartrouville - E/S Maison-Laff",2025,2025,46,46,"2025-11-10",172.451388888889,"2025-11-12","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21285733561,"Racc de Santes - Don-Sainghin",null,"Lille-St-Sauveur - Carre Violet 40","Haubourdin - Bif de Tortue",2025,2025,46,46,"2025-11-11",172.659722222222,"2025-11-12","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21284074461,"Paris - Lille",null,"Arras - Bif Blangy-Est","Douai - Bif de St-Éloi",2025,2025,46,46,"2025-11-11",172.868055555556,"2025-11-12","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",2,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",21283663161,"Calais - Lille",null,"Lambersart - Bif 4 Maisons","Hazebrouck - Poste 1",2025,2025,46,46,"2025-11-11",173.076388888889,"2025-11-12","04:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16984062061,"Mantes - Le Havre",null,"Mantes-Station","Mantes-la-Jolie - Bât Voyageurs",2025,2025,46,50,"2025-11-12",173.243055555556,"2025-12-13","04:45:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805705161,"Paris - Strasbourg",null,"Lagny-Thorigny - Tiroir 3","Meaux - Bât Voyageurs",2025,2025,46,48,"2025-11-14",173.368055555556,"2025-11-30","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16999907361,"Paris - Strasbourg",null,"Meaux - Marchandises","Meaux - Bât Voyageurs",2025,2025,46,48,"2025-11-14",173.576388888889,"2025-11-30","16:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"DFV GPT de type G 216+218 Meaux",null,"Y",null,45454,"High","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16842998061,"Paris - Lille",null,"Liancourt-Rantigny","Avrechy",2025,2025,46,48,"2025-11-14",173.784722222222,"2025-11-24","04:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16843050561,"Paris - Lille",null,"Creil - Acc/Sort Nord","St-Just-en-Chaussée - Voie 4",2025,2025,46,48,"2025-11-14",173.826388888889,"2025-11-24","04:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16984542061,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Rem Banlieue",2025,2025,46,46,"2025-11-15",174.034722222222,"2025-11-16","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16984459961,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,46,46,"2025-11-15",174.243055555556,"2025-11-16","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16941545961,"Argenteuil - Le Havre",null,"Conflans-Ste-Honorine - Evo & Manœuvres","Mantes-la-Jolie - Bif Argenteuil",2025,2025,46,46,"2025-11-15",174.326388888889,"2025-11-16","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23108548761,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - SG",2025,2025,46,46,"2025-11-15",174.534722222222,"2025-11-16","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",22796919161,"Paris - Strasbourg",null,"Vaires-Torcy - Faisceau V","Vaires-Torcy - Bât Voyageurs",2025,2025,46,47,"2025-11-16",174.743055555556,"2025-11-24","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null," ZEP 1324 VAI P5   ",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23108972861,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Rem Banlieue",2025,2025,46,46,"2025-11-16",174.951388888889,"2025-11-17","05:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16942144061,"Argenteuil - Le Havre",null,"Gargenville","Mantes-la-Jolie - Bât Voyageurs",2025,2025,46,46,"2025-11-16",175.159722222222,"2025-11-17","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23108960361,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,46,46,"2025-11-16",175.201388888889,"2025-11-17","05:40:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16161555361,"Paris - Strasbourg",null,"Changis-St-Jean - ITE Appel","Mézy - Poste U",2025,2025,1,50,"2025-11-17",175.409722222222,"2025-12-13","04:27:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"23/11/2022 (DAC) : Création de fenêtre générique élargie pour maintenance, suite concertation 2025. LFJ (inclue) - CTH (inclue) Voie 5 de CTH libre pour TN",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16947590461,"Paris - Lille",null,"Lamotte-Brebière","Achiet",2025,2025,47,48,"2025-11-17",175.659722222222,"2025-11-29","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16629906761,"Strasbourg - St Louis",null,"Mulhouse-Ville - Bât Voyageurs","Rixheim - Bif",2025,2025,47,48,"2025-11-17",175.868055555556,"2025-11-29","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"ZEP33452+33478+33482+33494+33489+33499 (ex 477+478+488+542+543+552)",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15805657361,"Paris - Strasbourg",null,"Noisy-le-Sec - Bif Impaire O",0,2025,2025,51,50,"2025-11-17",175.909722222222,"2025-12-06","04:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Toutes ZEP CHL sf ZEP 789                     ",null,"Y",null,45454,"Major","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20198508461,"Paris - Strasbourg",null,"Vaires-Torcy - Aig Km 21,0","Vaires-Torcy - ITE EDF",2025,2025,47,47,"2025-11-22",176.118055555556,"2025-11-24","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16987848561,"Mantes - Le Havre",null,"Vernon (Eure) - Bât Voyageurs","Gaillon-Aubevoye - ITE L'AVEBENE",2025,2025,47,47,"2025-11-22",176.326388888889,"2025-11-23","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16987435761,"Argenteuil - Le Havre",null,"Issou-Porcheville - Faisceau Pair","Mantes-la-Jolie - Bât Voyageurs",2025,2025,47,47,"2025-11-22",176.534722222222,"2025-11-23","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16986594861,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,47,47,"2025-11-22",176.576388888889,"2025-11-23","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16986570161,"Mantes - Le Havre",null,"Les Mureaux - RNUR Accès O","Épône-Mézières - Carré Violet167",2025,2025,47,47,"2025-11-22",176.784722222222,"2025-11-23","06:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16985563661,"Mantes - Le Havre",null,"Vernouillet-Verneuil - Triage Accès E","Les Mureaux - Bât Voyageurs",2025,2025,47,48,"2025-11-23",177.034722222222,"2025-11-24","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16985482761,"Mantes - Le Havre",null,"Achères-Triage - Les Ambassadeurs","Poissy - ITE Talbot Ac O",2025,2025,47,48,"2025-11-23",177.243055555556,"2025-11-24","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16942219961,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Mantes-la-Jolie - Bât Voyageurs",2025,2025,47,47,"2025-11-23",177.284722222222,"2025-11-24","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16985569661,"Mantes - Le Havre",null,"Les Mureaux - Voie 4","Les Mureaux - ITE VBMDG",2025,2025,47,48,"2025-11-23",177.493055555556,"2025-11-24","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,2,3,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16985554361,"Mantes - Le Havre",null,"Poissy - C4147","Villennes-sur-Seine",2025,2025,47,48,"2025-11-23",177.701388888889,"2025-11-24","04:35:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",1.7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810465761,"Mantes - Le Havre",null,"Bif de Darnétal - Rac 2","Maromme - Sor Évit Impair",2025,2025,1,50,"2025-11-24",177.909722222222,"2025-12-12","04:50:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810413461,"Mantes - Le Havre",null,"Gaillon-Aubevoye - ITE CFPI","Val-de-Reuil - ITE Herouard",2025,2025,3,49,"2025-11-24",177.951388888889,"2025-12-01","04:47:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  VAM RCST NEN : Main courante n°58 2023",null,"Y",null,45454,"Major","1,2,3,4",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",15810523561,"Mantes - Le Havre",null,"Pavilly-Station","Le Havre - Gare Locale",2025,2025,51,50,"2025-11-24",178.284722222222,"2025-12-13","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"VAM RCST NEN : Modification suite à évolution du système capacitaire 2025",null,"Y",null,45454,"Major",6,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16922838561,"Racc de Santes - Don-Sainghin",null,"Lille-Flandres - Ent/Sort Agnès","Lille-St-Sauveur - Jonction 24",2025,2025,48,49,"2025-11-27",178.409722222222,"2025-12-02","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","1,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",17000862561,"Paris - Strasbourg",null,"non trouvé","Frouard - Bât Voyageurs",2025,2025,48,49,"2025-11-28",178.618055555556,"2025-12-01","05:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Def 56h25 - V1+V2 à Toul - Avec 5D_LER-TL_0011 et 5C_TL_013 qui reprend les conséquences circulations.",null,"Y",null,45454,"Medium","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16995137861,"Mantes - Le Havre",null,"Mantes-la-Jolie - Bif Argenteuil","Rosny-sur-Seine",2025,2025,48,50,"2025-11-28",178.659722222222,"2025-12-08","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16995028161,"Mantes - Le Havre",null,"Épône-Mézières - Bât Voyageurs","Mantes-la-Jolie - Bât Voyageurs",2025,2025,48,50,"2025-11-28",178.868055555556,"2025-12-08","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16994910961,"Mantes - Le Havre",null,"Mantes-la-Jolie - ITE Aig Ouest","Mantes-la-Jolie - Bif Argenteuil",2025,2025,48,50,"2025-11-28",179.076388888889,"2025-12-08","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",23110149661,"Mantes - Le Havre",null,"Les Mureaux - Faisceau RNUR","Épône-Mézières - Bât Voyageurs",2025,2025,48,49,"2025-11-30",179.284722222222,"2025-12-08","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16994087261,"Mantes - Le Havre",null,"Épône-Mézières - Bif Graviers","Épône-Mézières - Carré Violet167",2025,2025,48,49,"2025-11-30",179.368055555556,"2025-12-08","04:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19974593761,"Ceinture de Metz",null,"Metz-Sablon - Jonct V2/V2R","Metz-Sablon - Bif L3/L11",2025,2025,49,50,"2025-12-01",179.576388888889,"2025-12-12","21:25:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap Voie 4 du FRE de Metz pour stationnement TTX",null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",20989480561,"Pontoise - Serqueux",null,0,0,2025,2025,49,50,"2025-12-01",179.784722222222,"2025-12-13","05:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"High","1,2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",19974604961,"Ceinture de Metz",null,"Metz-Sablon - Jonct V2/V2R","Metz-Sablon - Bif L3/L11",2025,2025,49,50,"2025-12-02",179.993055555556,"2025-12-13","06:30:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"Cap Voie 4 du FRE de Metz pour stationnement TTX",null,"Y",null,45454,"High","2,3,4,5,6",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16673337161,"Douai - Valenciennes",null,0,0,2025,2025,49,49,"2025-12-02",180.034722222222,"2025-12-06","05:15:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,45454,"Medium","2,3,4,5",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16362655961,"St Just en Chaussée - Douai",null,0,"Sancourt",2025,2025,49,49,"2025-12-05",180.243055555556,"2025-12-07","23:00:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null," Domaine B en continu 48h WE 49/50 ",null,"Y",null,45454,"Medium","5,6,7",null,null,null,null,null,"Planned",0]
[null,"SNCF-R",16177687161,"Metz - Lérouville",null,"Novéant - Bif Km 338,9","Metz-Sablon - Bif L3/L11",2025,2025,49,49,"2025-12-07",180.451388888889,"2025-12-08","05:10:00",null,"Periodical","Miscellanous",null,null,null,null,null,null,null,null,null,null,"6 OT pour chantier Migration en SML400T du Poste PAI de Metz-Sablon. Voir 5C_MZ_037 qui reprend les conséquences circulations.",null,"Y",null,45454,"Medium",7,null,null,null,null,null,"Planned",0]
[null,"SNCF-R",24100644461,null,null,"Gretz-Armainvilliers - Point D","Grandpuits - Poste 2",2026,2026,51,47,"2025-12-15","11:12:00","2026-11-22","11:42:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Tournée de surveillance périodique AdV G03Bis en gare de Gretz. 13 semaines par an.  Trains en provenance de Tournan et Coulommiers à dévoyer V3 au lieu de V2.",null,null,null,null,"High",2,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23681262961,null,null,"Gretz-Armainvilliers - Bât Voyageurs","Flamboin-Gouaix - Sémaphore 193",2026,2026,51,50,"2025-12-15","13:46:00","2026-12-11","13:58:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Train ouvrant : 117562    Train fermant : 117566",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23681264561,null,null,"Gretz-Armainvilliers - Bât Voyageurs","Flamboin-Gouaix - Sémaphore 98,8",2026,2026,35,49,"2026-11-25","23:05:00","2026-12-03","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Fin à 5h30 suite demande EF  18/11/2022 (DAC) : Suite concertation fenêtres génériques 2025, ajout du Ve/Sa à la 5F_GZ-LON_001 = abandon de la fenêtre courte 5F_GZ-LON_006.",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23680394361,null,null,"Petit-Croix - Raccordement","Mulhouse-Ville - Aiguille Voie M",2026,2026,51,50,"2025-12-15","11:03:00","2026-12-11","12:19:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"05/10/2017: modif horaire via main courante ref 81 08/09/2022 : vibration (- 2 min) suite main courante 05 (SE)",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23672107261,null,null,"Lérouville - Bât Voyageurs","Novéant - Bif Km 338,9",2026,2026,10,33,"2026-03-02","23:00:00","2026-08-15","05:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23682171661,null,null,"Sélestat","Colmar - Accès Nord",2026,2026,51,50,"2025-12-15","14:12:00","2026-12-11","15:21:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2025 - Main Courante 142 : décalage des horaires de +2 minutes",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23682150061,null,null,"St-Louis (Haut-Rhin) - Bât Voyageurs","St-Louis (Haut-Rhin) - Frontière Fr-Su",2026,2026,51,50,"2025-12-15","09:29:00","2026-12-11","10:26:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification faite suite à la demande de MC 193",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23682175461,null,null,"Colmar - Aiguille Sud","Lutterbach (Haut-Rhin) - Bât Voyageurs",2026,2026,51,50,"2025-12-15","10:03:00","2026-12-11","10:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23672000461,null,null,"Sarraltroff - Bif","Rémilly - Bif L3/L11",2026,2026,48,50,"2026-11-23","22:55:00","2026-12-12","05:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671998861,null,null,"Sarraltroff - Bif","Rémilly - Bif L3/L11",2026,2026,48,50,"2026-11-23","23:40:00","2026-12-12","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679157761,null,null,"Sedan - Garages","Montmédy - Bât Voyageurs",2026,2026,51,50,"2025-12-15","12:45:00","2026-12-11","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679157761,null,null,"Sedan - Garages","Montmédy - Bât Voyageurs",2026,2026,51,50,"2026-02-02","12:45:00","2026-02-06","14:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679182761,null,null,"Mohon - Bif L2","Sedan - Accès Garage",2026,2026,6,42,"2026-02-02","10:40:00","2026-10-16","14:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679183561,null,null,"Lumes","Sedan - Accès Garage",2026,2026,6,42,"2026-02-02","10:39:00","2026-10-16","14:47:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679332861,null,null,"Reims - Bif L2/Rac 3","Amagne-Lucquy - Bât Voyageurs",2026,2026,51,50,"2025-12-15","15:27:00","2026-12-11","15:59:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679331261,null,null,"Reims - Bif L2/Rac 3","Mohon - Bif L2/Rac",2026,2026,51,49,"2025-12-21","23:50:00","2026-12-07","02:50:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23683026661,null,null,"Revin","Givet - Poste 1",2026,2026,51,50,"2025-12-15","10:16:00","2026-12-11","11:31:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MàJ par P KERGUIGNAS du 31-05-2023 suite à demande de l'ICA P Maslach et F Saint Maxent DLCA suite aux besoins du chantier CHA16_0010102   MàJ du par P KERGUIGNAS du 13-01-2023 suite à demande de l'ICA P Maslach (Découpage de la surveillance) Revin Excl -",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23683025861,null,null,"Charleville-Mézières - Bât Voyageurs","Fumay",2026,2026,51,50,"2025-12-15","10:25:00","2026-12-11","10:48:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MàJ par P KERGUIGNAS du 31-05-2023 suite à demande de l'ICA P Maslach et F Saint Maxen DLCA suite aux besoins du chantier CHA16_0010102  MàJ par P KERGUIGNAS du 13-01-2023 suite à demande de l'ICA P Maslach (Découpage de la surveillance) Charleville Revin",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679100961,null,null,"Hirson - Bif de Buire",0,2026,2026,6,46,"2026-02-02","09:10:00","2026-11-13","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679100161,null,null,"Hirson - Bif de Buire",0,2026,2026,51,50,"2025-12-15","00:00:00","2026-12-07","03:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23680306961,null,null,"Poste 29 Sainghin - Bif de Sainghin","Lille-Europe - Bif Est",2026,2026,51,50,"2025-12-15","14:24:00","2026-12-11","15:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 08/09/2020 par LL, suite demande par main-courante MC22-0324 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23680306161,null,null,"Poste 29 Sainghin - Bif de Sainghin","Lille-Europe - Bif Est",2026,2026,51,50,"2025-12-15","11:58:00","2026-12-11","12:48:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23680289761,null,null,"Lille-Europe - Poste 41","Calais-Fréthun - Bât Voyageurs",2026,2026,51,50,"2025-12-15","23:10:00","2026-12-12","05:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679140161,null,null,"Rouvroy-l'Échelle","Tournes",2026,2026,51,49,"2025-12-21","23:00:00","2026-12-07","02:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679626161,null,null,"Maubeuge - Poste 2","Jeumont - Bât Voyageurs",2026,2026,51,50,"2025-12-15","00:30:00","2026-12-07","03:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679674561,null,null,"Compiègne - Garage Pair","Tergnier - Bât Voyageurs",2026,2026,23,25,"2026-06-01","23:20:00","2026-06-20","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"évol capa sa2026 fait par LL le 10/11/23.",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679113561,null,null,"Somain - Aig Km 230,5","Beuvrages",2026,2026,51,50,"2025-12-15","00:00:00","2026-12-07","03:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679143761,null,null,0,0,2026,2026,51,50,"2025-12-15","00:00:00","2026-12-07","03:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679107561,null,null,"Lesquin - Bif de Lesquin","Beuvrages",2026,2026,50,49,"2025-12-14","23:00:00","2026-12-07","02:32:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,null,null,null,"Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679108361,null,null,"Lesquin - Bif de Lesquin","Beuvrages",2026,2026,51,50,"2025-12-15","01:36:00","2026-12-07","04:13:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679117561,null,null,"Leval","Hirson - Ent Marchandise",2026,2026,51,50,"2025-12-15","13:10:00","2026-12-11","13:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  Modification horaire faite le 13/10/20 par LL, suite main-courante MC22-0346.  modification horaire faite le 04/03/22 par LL, suite mail D VITRY du 25/02/22.",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23694192961,null,null,"Lezennes - Ateliers","Baisieux - Frontière Fr-Be",2026,2026,51,50,"2025-12-15","13:48:00","2026-12-11","14:48:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679124761,null,null,"Douai - Aig Km 218,5","Triangle d'Ostricourt - Bif de Évin",2026,2026,51,50,"2025-12-15","01:00:00","2026-12-07","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679690361,null,null,"Achiet","Arras - Bif Sud",2026,2026,51,50,"2025-12-15","09:18:00","2026-12-11","10:22:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification horaire faite le 16/10 par LL suite main-courante MC22-0349 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679693961,null,null,"Arras - Bif Blangy-Est","Douai - Bif de St-Éloi",2026,2026,51,50,"2025-12-15","01:30:00","2026-12-07","04:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679577061,null,null,"Triangle d'Ostricourt - Bif de Évin","Lille-St-Sauveur - Bif Sourd-Muet",2026,2026,51,50,"2025-12-15","01:35:00","2026-12-07","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679727361,null,null,"Boisleux","Arras - Poste 1",2026,2026,51,50,"2025-12-15","09:24:00","2026-12-11","10:26:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 16/10/20 par LL suite main-courante MC22-350 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679761961,null,null,"La Madeleine (Nord) - ITE ZI Pilateri","Tourcoing - Frontière Fr-Be",2026,2026,51,50,"2025-12-15","14:34:00","2026-12-11","15:44:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679699961,null,null,"Lens - Bif l'Épinette","Don-Sainghin - Bât Voyageurs",2026,2026,51,50,"2025-12-15","09:55:00","2026-12-11","10:43:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23694085761,null,null,"Don-Sainghin - Bât Voyageurs","Béthune - E/S Béthune",2026,2026,51,50,"2025-12-15","13:45:00","2026-12-11","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679740361,null,null,"Haubourdin - Bif Haubourdin","Don-Sainghin - Bât Voyageurs",2026,2026,51,50,"2025-12-15","00:00:00","2026-12-07","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679711761,null,null,"Lille-St-Sauveur - Carre Violet 40","Haubourdin - Bif de Tortue",2026,2026,51,50,"2025-12-15","14:16:00","2026-12-11","15:21:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"modification horaire faite le 07/11/23 par LL, suite main-courante MC25-150.",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23694138961,null,null,"Haubourdin - Bif Haubourdin","Lille-Délivrance - Relais",2026,2026,51,50,"2025-12-15","13:50:00","2026-12-11","15:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Pk début/fin n'engagent pas les bifs Haubourdin, Tortue, St André et 4 Maisons",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679175161,null,null,"Lambersart - Bif 4 Maisons","Hazebrouck - Poste 1",2026,2026,51,50,"2025-12-15","11:05:00","2026-12-11","12:28:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679728961,null,null,"Hazebrouck - Bif Haute Loge","Calais-Fréthun - Carré 321",2026,2026,50,49,"2025-12-14","21:27:00","2026-12-07","23:57:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679734561,null,null,"Hazebrouck - Bif Haute Loge","Calais-Fréthun - Carré 321",2026,2026,50,49,"2025-12-14","21:28:00","2026-12-07","01:08:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679200161,null,null,"Lens - Poste 4","Béthune - E/S Béthune",2026,2026,51,50,"2025-12-15","10:11:00","2026-12-11","11:24:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Modification le 07/02/2019 : Norme d'exploitation passée à \"\"Normale\"\"  modification suite scission par création de la fen lns-hzk_010, fait par LL le 22/1121.",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679194561,null,null,"Béthune - E/S Béthune","Berguette-Isbergues",2026,2026,51,50,"2025-12-15","10:26:00","2026-12-11","11:42:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"création suite scission de la  fen lns-hzk_003, fait  par LL le 22/11/21.  Modification horaire faite le 01/03/2022 par LL, suite logique de la DECC23_00161.",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679705961,null,null,"Arras - Bif Blangy-Nord","Lens - Bif d'Avion",2026,2026,51,50,"2025-12-15","00:00:00","2026-12-07","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679706761,null,null,"Arras - Bif Blangy-Nord","Lens - Bif d'Avion",2026,2026,50,49,"2025-12-14","23:00:00","2026-12-07","02:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23679758361,null,null,"Wimille-Wimereux","Calais-Fréthun - C102/204",2026,2026,51,50,"2025-12-15","00:00:00","2026-12-07","03:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671076561,null,null,"Moulins-sur-Allier - Aig Km 314,3","La Ferté-Hauterive - Bât Voyageurs",2026,2026,51,50,"2025-12-15","09:32:00","2026-12-11","10:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10700095 Moulins - La Ferté                 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671063361,null,null,"Saincaize - Aig Km 265,3","Moulins-sur-Allier - Bât Voyageurs",2026,2026,51,50,"2025-12-15","10:17:00","2026-12-11","11:06:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10700093 Modification le 07/02/2019 : Norme d'exploitation passée de \"\"Poreuse\"\" à \"\"Normale\"\"",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671055361,null,null,0,"Sémaphore 107",2026,2026,51,49,"2026-01-20","00:05:00","2026-11-07","05:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Sillon 79507 fermant (accord fret) Modifié en RP0 du 02/04/19 pour sillon ouvrant TN 151885                                                                 ",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671053761,null,null,"Moret-Veneux-les-Sablons - Bât Voyageurs","Montargis - Bât Voyageurs",2026,2026,51,50,"2025-12-15","10:06:00","2026-12-11","11:53:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,11202238,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671049161,null,null,"Montargis - Bât Voyageurs","Cosne",2026,2026,50,49,"2025-12-14","23:00:00","2026-12-07","02:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671033361,null,null,"Cosne","Nevers - Aig Km 251,5",2026,2026,51,50,"2025-12-15","11:30:00","2026-12-11","11:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Vibration main courante 2021_SE_10 : Passage du 5968 en trame. Décalage de 02h23 alignée avec surveillance V2 Clermont-Nevers.             ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669778261,null,null,"St-Étienne-Pont-de-l'Âne - Poste 2","Givors-Ville - Bât Voyageurs",2026,2026,51,50,"2025-12-15","01:17:00","2026-12-07","04:02:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10800601 Faisceau Fret à St Etienne libre. 1V/2 libre pour circulation en IPCS     MC16-0372 Pour passage SICF0002               ",null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669780661,null,null,"St-Étienne-Pont-de-l'Âne - Poste 2","Givors-Canal - Bât Voyageurs",2026,2026,3,50,"2026-01-12","00:23:00","2026-12-12","05:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Simultanée entre le croisement des Génériques 4F_SEA-GIC_001 (V1) et 4F_SEA-GIC_002 (V2) pouvant amener à une amplitude minimum V1+V2 de 4h53 (coté St Etienne) et une amplitude maximum V1+V2 de 5h48 (coté Givors)  5 Nuits / 7  Faisceau Fret à St Etienne l",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23683362961,null,null,"Le Coteau","Montrond-les-Bains",2026,2026,12,41,"2026-03-16","10:05:00","2026-10-11","13:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance dans l´ombre des connexes de la SR ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23683595461,null,null,"ITE Km 463,2","St-Étienne-Châteaucreux - Poste 1",2026,2026,12,41,"2026-03-16","09:30:00","2026-10-11","13:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance dans l´ombre des connexes de la SR Alignement des semaines à rechercher avec St Just-Montbrison (ligne 784000)   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23683599461,null,null,"ITE Km 463,2","St-Étienne-Châteaucreux - Poste 1",2026,2026,12,41,"2026-03-16","09:15:00","2026-10-11","13:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Maintenance dans l´ombre des connexes de la SR Alignement des semaines à rechercher avec St Just-Montbrison (ligne 784000) ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23683371361,null,null,"St-Germain-des-Fossés - Bif de Clermont","Roanne - Carré 100",2026,2026,50,49,"2025-12-14","00:20:00","2026-12-07","02:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669662661,null,null,"Peyraud - Bât Voyageurs","La Voulte-sur-Rhône - Aig Km 634,9",2026,2026,51,46,"2025-12-15","11:49:00","2026-11-13","13:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11401010 Decalage main courante MC17-0050 Décalage main courante MC17-0204 Main courante MC18-305 pour FBPN,APCE,FBCE,BTLB le 18/11/16. 2021_SE_100 + 2021_SE_101 + 2021_SE_102 + 2021_SE_103 : décalage de quelques minutes pour avoir BTLB04 en SF           ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669713861,null,null,"Loire - Poste 1","Peyraud - Cv 1",2026,2026,50,45,"2025-12-14","21:50:00","2026-11-09","01:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"High",7,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669713061,null,null,"Loire - Poste 1","Peyraud - Bât Voyageurs",2026,2026,51,46,"2025-12-15","13:18:00","2026-11-13","13:49:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_47: vibration de -10mn pour avoir fret CETH06 en SF  11401011  Decalage main courante MC17-0057  Décalage main courante MC17-0313",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669687261,null,null,"La Voulte-sur-Rhône - Aig Km 634,9","Villeneuve-lès-Avignon - Rac Sud",2026,2026,5,50,"2026-01-26","09:47:00","2026-12-11","15:42:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668992761,null,null,"Mâcon-Ville - Bât Voyageurs","St-Germain-au-Mont-d'Or - Poste 1",2026,2026,51,49,"2025-12-15","01:45:00","2026-11-30","05:04:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,10800602,null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668994361,null,null,"Mâcon-Ville - Carré 117","St-Germain-au-Mont-d'Or - Faisceau Escale",2026,2026,51,50,"2026-10-09","23:25:00","2026-10-10","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO 50054 TF 30006/7 Modification validée au N2 du 19/02/2016",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668995161,null,null,"Mâcon-Ville - Bât Voyageurs","St-Germain-au-Mont-d'Or - Poste 1",2026,2026,51,50,"2025-12-15","23:40:00","2026-12-12","06:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_66 : décalage de -3min pour TER 887103, le 06/12/2022   2021_SE_37 : décalage de -2mn pour TER 887103, le 14/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668986161,null,null,"Chagny - Bif Sud","Chalon-sur-Saône - Bât Voyageurs",2026,2026,18,50,"2026-10-05","00:07:00","2026-12-12","05:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h52 à 5h12 en sim. TO 50054 / TF 891400. Modification validée au N2 du 19/02/2016",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668955361,null,null,"St-Germain-au-Mont-d'Or - Bât Voyageurs","Collonges-Fontaines",2026,2026,51,49,"2025-12-16","00:20:00","2026-12-06","06:24:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 1 dans chaque sens. La fenêtre sera activée en même temps sur les 4 voies mais en opérationnel, l'INFRA garantie une voie libre dans chaque sens Accord pour 19 semaines suite à revue de cloture d'ordonnancement PCAST",null,null,null,null,"Major","2,3,4,5,6",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668904761,null,null,"Chalon-sur-Saône - Bât Voyageurs","Mâcon-Ville - Faisceau pair",2026,2026,51,50,"2026-06-01","23:05:00","2026-12-12","05:57:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"5h08 à 5h11 en sim 5N/7",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668901561,null,null,"Chalon-sur-Saône - Bif Nord","Mâcon-Ville - Bât Voyageurs",2026,2026,51,50,"2026-10-09","23:58:00","2026-10-10","05:18:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"TO 50054 / TF 30006/7. Modification validée au N2 du 19/02/2016",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668920561,null,null,"Perrigny-Triage - Bif Km 316,2","Chagny - Bif Sud",2026,2026,18,41,"2026-04-27","22:29:00","2026-05-21","04:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"3h59 à 4h52 en sim 5N/7",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669600061,null,null,"Pierrelatte - Bât Voyageurs","Sorgues-Châteauneuf-du-Pape - Voie 2Bis",2026,2026,51,50,"2025-12-15","11:17:00","2026-12-11","11:43:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Vibration MC18-0171 Pour sillon corridor CECS05 ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669705661,null,null,"Chasse-sur-Rhône - Bât Voyageurs","Vienne - Poste",2026,2026,39,44,"2026-09-21","10:26:00","2026-10-30","15:16:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h06 à 4h20 en sim 5J/7 SA2017 => TO 17706 / TF 886118                   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669704861,null,null,"Ternay","Vienne - Poste",2026,2026,39,44,"2026-09-21","09:34:00","2026-10-30","14:36:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h06 à 4h20 en sim 5J/7 SA2017 => TO 17709 / TF 886127                   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23670827161,null,null,"Montereau - Bif Km 86,7","Sens - Voie 3 Garage",2026,2026,51,49,"2025-12-15","00:50:00","2026-12-06","03:40:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 => 1 voie dans chaque sens ",null,null,null,null,"High",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23670799361,null,null,"Laroche-Migennes - FSC Bercy","St-Florentin-Vergigny - Aig Km 168,3",2026,2026,52,50,"2025-12-22","00:19:00","2026-12-07","03:05:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2V/4 => 1 voie dans chaque sens               ",null,null,null,null,"High",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23670915361,null,null,"Les Laumes-Alésia - Bif Km 258,7","Mâlain - Pt Changt Voie",2026,2026,14,40,"2026-03-30","09:00:00","2026-04-24","14:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"1 voie par sens. Accord pour 12 semaines suite à revue de cloture d'ordonnancement PCAST                                                                                 ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23670920161,null,null,"Les Laumes-Alésia - Faisceau Impair","Mâlain - Pt Changt Voie",2026,2026,18,40,"2026-04-27","09:10:00","2026-05-22","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 10 semaines suite à revue de cloture d'ordonnancement PCAST                                       ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23670919361,null,null,"Les Laumes-Alésia - Côté NO","Mâlain - Pt Changt Voie",2026,2026,14,40,"2026-09-25","09:10:00","2026-09-28","15:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"voie par sens. Accord pour 29 semaines suite à revue de cloture d'ordonnancement PCAST                     ",null,null,null,null,"High","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671565761,null,null,"Moret-Veneux-les-Sablons - Voie 1Bis","Montereau - Bif Km 76,9",2026,2026,51,50,"2025-12-15","01:35:00","2026-12-07","04:45:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23670903561,null,null,"Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2026,2026,51,49,"2026-01-26","10:35:00","2026-03-20","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Accord en CODAB le 26/09/2016 pour 37 semaines ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23670903561,null,null,"Blaisy-Bas","Dijon-Ville - Aiguilles Nord",2026,2026,51,49,"2025-12-19","10:35:00","2025-12-19","14:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Accord en CODAB le 26/09/2016 pour 37 semaines ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671515761,null,null,"Melun - Voie 3 Garage","Moret-Veneux-les-Sablons - Bât Voyageurs",2026,2026,51,50,"2025-12-15","10:13:00","2026-12-11","10:54:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,11402232,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671516561,null,null,"Melun - Voie 3 Garage","Moret-Veneux-les-Sablons - Bât Voyageurs",2026,2026,51,50,"2026-01-19","23:45:00","2026-12-12","05:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"il y avait 23h40/05h10 , il faut 23h45/5h10 (pour circulation des transiliens 152881 et 152982 qui ont modifié définitivement leurs horaires de cadencement.) ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668318661,null,null,"Pas-des-Lanciers - Bât Voyageurs","L'Estaque - Bât Voyageurs",2026,2026,51,50,"2025-12-15","10:55:00","2026-12-11","12:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_30 : vibration de -10' pour avoir TER 17701 en SO et TER 886565 en SF  MC19-0149 Calage entre 879653 et 879655 Modif main courante 2020 Maj-550_871",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668320261,null,null,"Rognac - Triage","Pas-des-Lanciers - Bât Voyageurs",2026,2026,51,50,"2025-12-15","10:02:00","2026-12-11","10:56:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Annulation Décalage MC17-0227 pour 879610 21/10/2015 2021_SE_67 : décalage de +30mn pour avoir 879518 en SO et 879522 en SF, aligné V2 de St Louis à Tarascon, le 19/11/2019",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668284061,null,null,"Miramas - Bât Voyageurs","Berre",2026,2026,51,50,"2025-12-15","10:35:00","2026-12-11","11:46:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2024_SE_27 : vibration de -5' pour avoir TER 17701 en SO et TER 886565 en SF  MC19-0146 Passage entre 879653 et 87655 Modif suite main courante 2020 Min-547-871",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671789261,null,null,"Perrigny-Triage - Changement V","Auxonne",2026,2026,38,41,"2026-09-14","22:20:00","2026-10-09","05:26:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Ne pas activer en même temps que la FEN19 Longvic-VillersLesPots 007 (Incompatibilités fenêtres non opérationnel pour des jours isolés) ",null,null,null,null,"High","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668980561,null,null,"Pont-de-Veyle","Bourg-en-Bresse - Poste 1",2026,2026,51,50,"2025-12-15","14:31:00","2026-12-11","15:48:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"11402062 MC17-0288 Pour catalogue fret spécial ILAM08           ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668981361,null,null,"Pont-de-Veyle","Bourg-en-Bresse - Poste 1",2026,2026,51,50,"2025-12-15","15:05:00","2026-12-11","15:48:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,11402064,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668967561,null,null,"Bourg-en-Bresse - Poste 2","Ambérieu - Poste 5",2026,2026,1,40,"2025-12-29","10:15:00","2026-10-02","16:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Sur 1 pas d'IPCS dont 2h sur 2 pas en fin de plage (14h15-16h15) à ordonnacé en même temps que la fenêtre de 2h   ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23668929161,null,null,"Lyon-St-Clair","Ambérieu - Poste 1",2026,2026,51,50,"2025-12-15","00:24:00","2026-12-07","03:47:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,11401156,null,null,null,null,"Major",1,null,null,null,null,null,"Planned"]
[null,"SNCF-R",23667789761,null,null,"Longeray-Léaz - Bât Voyageurs","Pougny-Chancy - Frontière Fr-Su",2026,2026,51,50,"2025-12-15","15:07:00","2026-12-10","16:16:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,10701580,null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23667791361,null,null,"Longeray-Léaz - Bât Voyageurs","Pougny-Chancy - Frontière Fr-Su",2026,2026,51,50,"2025-12-15","10:52:00","2026-12-10","11:47:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10701581 MC17-0145 Pour circulation du TGV Lyria 9768 MC-655                  ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23667704861,null,null,"Ambérieu - Aig Km 53,6","Culoz - Aig Km 99,3",2026,2026,51,50,"2025-12-15","22:25:00","2026-12-11","04:25:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"MC18-0112 :  Vibration de 5' pour croisement 104 et NSMD16 ",null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23667748061,null,null,"Bellegarde (Ain) - Aig Km 135,1","Longeray-Léaz - Bât Voyageurs",2026,2026,11,48,"2026-03-09","00:00:00","2026-11-27","05:19:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Passé au DI/LU à JE/VE au N2 du 02/10/2015",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23667729061,null,null,"Culoz - Carré 318","Bellegarde (Ain) - Sémaphore 52",2026,2026,10,48,"2026-03-02","23:45:00","2026-11-28","05:53:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"4h37 à 5h15 en sim 5N/7(Culoz-Bellegarde) de MA à SA 2018 => amplitude augmentée. Validé au N2 du 02/10/15                               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669942961,null,null,"St-André-le-Gaz","Moirans",2026,2026,51,50,"2025-12-15","10:55:00","2026-12-10","12:28:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,10701591,null,null,null,null,"Major","1,2,3,4",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23670014961,null,null,"Vénissieux-Voyageurs - FSC Réception","St-Quentin-Fallavier - Bif LGV",2026,2026,51,50,"2025-12-15","00:00:00","2026-12-11","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"2018 => Basculé en DI/LU à JE/VE. Validé au N2 du 02/10/15     ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23669998361,null,null,"Bourgoin-Jallieu - Bât Voyageurs","St-André-le-Gaz",2026,2026,51,50,"2025-12-15","10:44:00","2026-12-11","11:58:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"10701327 2021_SE_14 : décalage +4mn alignée avec 1F_SAG-MOA_003 pour Passage du 17613, le 13/11/2019               ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23695028661,null,null,"Aspres-sur-Buëch","Veynes-Dévoluy - Bât Voyageurs",2026,2026,51,50,"2025-12-15","08:05:00","2026-12-11","09:10:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23694985661,null,null,"Château-Arnoux-St-Auban - Bât Voyageurs","Pertuis - BS",2026,2026,51,50,"2025-12-15","13:00:00","2026-12-11","13:55:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23694983661,null,null,"Veynes-Dévoluy - Bif 235,9/244,1","Laragne",2026,2026,51,50,"2025-12-15","11:40:00","2026-12-11","13:15:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23695004661,null,null,"Gardanne - Bât Voyageurs",0,2026,2026,51,50,"2025-12-15","23:35:00","2026-11-28","05:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"25/11/16 Vibration et réduction (20min) de la fenêtre suite à main courante (MC18-0327) pour TER 880196 et 88019  12/12/17: Suppression de cette fenetre générique de S27 à S44 pour garantir l'accès à Gardanne.  Suite RP0 du 18/06/21: Altéo perd 1 A/R, le ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23694999661,null,null,"Aix-en-Provence - Bât Voyageurs","Simiane",2026,2026,51,50,"2025-12-15","23:40:00","2026-12-12","05:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"Décalage de la fenêtre : main courante MC18-0213 du 19/10/16  Suite RP0 du 21/06/21:  Ter demande, un décalage de 5 minutes de la plage étant donné que le TER 880196 rentre à 23h38. Il y a 23h35 à 05h30, il faut 23h40 à 05h35 de manière à conserver l´ampl",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23683492961,null,null,"Vif - Bât Voyageurs","Clelles-Mens",2026,2026,51,50,"2025-12-15","09:21:00","2026-12-11","10:35:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"08/09/2017: suite à main courante, MC19-0046, décalage de 5 minutes (JTr) ->TER 885660 / 885605",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23683530361,null,null,"Grenoble - Bif de Veynes","St-Georges-de-Commiers",2026,2026,51,50,"2025-12-15","22:00:00","2026-12-11","04:00:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"04/05/2018: Passage à Di/Lu -> Je/Ve (JTr)",null,null,null,null,"Major","1,2,3,4,7",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23667943261,null,null,"Avignon-Fontcouverte - Fais Réc Impair","Cavaillon - Bât Voyageurs",2026,2026,51,50,"2025-12-15","11:00:00","2026-12-11","11:30:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2023/Main Courante PCO_SE/demande n°75 : vibration <10mn pour passage 879688 (SO 879622/SF 879688)  Décalage mineure MC17-0060 pour 879608 ouvrant et 879610  Main courante MAJ 224 pour train 879660 le 14/10/15  2021_SE_56 : décalage de +01h pour avoir 8",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23667967261,null,null,"Martigues - CV 878","L'Estaque - Bât Voyageurs",2026,2026,51,50,"2025-12-15","09:44:00","2026-12-11","10:13:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,"SA2025 : Main Courante SE n°22 : décalage (879716 SO)  2024_SE_10 : vibration de +5' pour avoir TER 879716 en SO  2021_SE_52 : décalage de +35mn pour avoir 879716 en SO, aligné V2 de l'Estaque à Miramas, le 19/11/2019  MC19-0020 pour caler la plage entre ",null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23667966461,null,null,"Martigues - Aig Rac La Mède","L'Estaque - Panneau 901",2026,2026,51,50,"2025-12-15","15:26:00","2026-12-11","16:54:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23682293961,null,null,"Noisy Raccordement","Valenton - Bif GC/GC Bis",2026,2026,51,50,"2025-12-15","10:00:00","2026-12-11","11:20:00",null,"Periodical",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Major","1,2,3,4,5",null,null,null,null,null,"Planned"]
[null,"SNCF-R",23671739461,null,null,"Valenton - Bif GC/GC Bis","Valenton - Dépôt",2026,2026,51,49,"2025-12-15","23:00:00","2026-12-07","05:00:00",null,"Periodical"]
[null,"SNCF-R","F35721",null,"< >",96,186,2027,2027,37,43,"2027-09-06","00:00:00","2027-10-17",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F39741",null,"< >",5662,5666,2027,2027,36,49,"2027-08-30","00:00:00","2027-11-28",0.99998842592592585,"90 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"DEF 5N LuMa à VeSa\nOCP 55H\nBA Pau et Artix",null,null,"650000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F41705",null,"< >",456,459,2027,2027,27,31,"2027-06-28","00:00:00","2027-07-25",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"8S DEF 7h00 sim V1V2 de nuit dans l'ombre ddes capacités d'EG3\n3S fermeture dans l'ombre de la fermeture de Boudelin\nDFV Type L Troyes - Chaumon V1 et Chaumont - Troyes V2",null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F44694",null,"< >",2056,2056,2027,2027,27,35,"2027-06-28","00:00:00","2027-08-22",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Avec Chantier 38 RR Hirson Hamagne\n\n2S DEF 5h00 de jour toute la gare Hirson (Domaine A)\n5S DEF 8h00 sim Toute la gare d'Hirson  (Domaine B)\n1WE de 40h00 toute la gare d'Hirson (Domaine B)\n2WE de 48h00 toute la gare d'Hirson (Domaine B)\nPour les ZEP et El voir les domaines au sein de l'EBC\nTTX - Base arrière Hirson\n\n\n\n\n\n",null,null,"267000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F45699",null,"< >",8305,4740,2027,2027,14,42,"2027-03-29","00:00:00","2027-10-10",0.99998842592592585,"195 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"640000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"4"]
[null,"SNCF-R","F45730",null,"< >",706,697,2027,2027,37,45,"2027-09-06","00:00:00","2027-10-31",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"7S DEF 7h00 sim de nuit \nZEP Type L Amagne - Mohon V1 + V2\nSsr Saulces - Poix V1 + V2",null,null,"205000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F46419",null,"< >",1669,1566,2027,2027,11,13,"2027-03-08","00:00:00","2027-03-21",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Coupure estivale + OCP + déformées \n\nRéseua régional",null,null,"962000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F46421",null,"< >",105,111,2027,2027,45,47,"2027-11-01","00:00:00","2027-11-14",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F46774",null,"< >",2752,8190,2027,2027,27,31,"2027-06-28","00:00:00","2027-07-25",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334900",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F46804",null,"< >",896,898,2027,2027,42,45,"2027-10-11","00:00:00","2027-10-31",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Voir le compte F avec Pascal Mariette\n\n8h00 sim de nuit les nuits de Sa/Di et Di/Lusur 1 WE\n1S 3h00 sim V1V2",null,null,"115000",45574,"High","1,2,3,4,5,6,7",null,null,"00903",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F47569",null,"< >",2281,1746,2027,2027,21,28,"2027-05-17","00:00:00","2027-07-04",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"325000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"4"]
[null,"SNCF-R","F47704",null,"< >",1452,1463,2027,2027,9,16,"2027-02-22","00:00:00","2027-04-11",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"6S DEF 6h00 dont 4h00 sim selon les voies\n5WE nuits de Sa/Di et Di/Lu en 8h00 dont 6h30 sim selon les voies\n\nVoir ZEP et SEL au sein de l'annexe 1C \n",null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,1]
[null,"SNCF-R","F48088",null,"< >",110,131,2027,2027,12,14,"2027-03-15","00:00:00","2027-03-28",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F48891",null,"< >",8165,2493,2027,2027,20,27,"2027-05-10","00:00:00","2027-06-27",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"10S DEF de 7h00 de nuit Sim VR VAB\n1 WE de 110h00 Sim VR VAB\nZEP 62, ZEP 304\nSous secteur Valenciennes Voie de service SEL201, 202, 205, 215 et 217",null,null,"263300",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"5"]
[null,"SNCF-R","F49858",null,"< >",1686,1714,2027,2027,36,39,"2027-08-30","00:00:00","2027-09-19",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F49920",null,"< >",1157,1102,2027,2027,38,46,"2027-09-13","00:00:00","2027-11-07",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"7S DEF 8h00 sim V1V2 V1BisV2Bis de nuit\n\nZep 3132+3130+2915+2921\nSs Sr Ars Montigny V1/V2\n\nTTX - Base arrière Blainville - Eventuellement voir pour des marches en début et/ou fin de période avec garage au faisceau VS de Lunéville ( A VERIFIER)\n\n\n",null,null,"89000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F50420",null,"< >",5042,5042,2027,2027,4,15,"2027-01-18","00:00:00","2027-04-04",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"06h00\n4 nuits Lu/Ma à Je/Ve",null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F50420",null,"< >",4858,5230,2027,2027,4,15,"2027-01-18","00:00:00","2027-04-04",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"6h SIM toute l'année à l'ombre AFSB/AFNT\n4 nuits Lu/Ma à Je/Ve",null,null,"640000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,1]
[null,"SNCF-R","F50724",null,"< >",1938,1930,2027,2027,5,9,"2027-01-25","00:00:00","2027-02-21",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Chantier à placer en période hivernale (du 1 janvier au 28 février ou du 7 octobre au 31 décembre). Si pas possible, une post-incorporation devra être réalisée pendant le week-end, donc passer de 14h00 à 16h00.\n\n3S DEF de 7h00 sim V1V2 de nuit\n1 We de 14h00 V1V2\n\nTTX - Base arrière GarotLille\nZEP et SEL voire shma domaine A sur EBC",null,null,"289000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F52951",null,"< >",848,903,2027,2027,37,39,"2027-09-06","00:00:00","2027-09-19",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 nuit Di/Lu 6h00 V2V2Bis\n2 nuits Di/Lu 6h00 V1V1Bis\n2 nuits Di/Lu 6h00 Sim V1V1BisV2V2Bis\n1S nuits Lu/Ma à Je/Ve V2V2Bis\n2S nuits Lu/Ma à Je/Ve V1V1Bis\n1nuit Lu/Ma 6h00 Sim V1V1BisV2V2Bis\nV2V2Bis: ZEP 928+968+970 et Sél 12+14+102 du SSr RIXHEIM-St LOUIS V2 et SSr St Louis Frontière V2\nV1V1Bis: ZEP 929+969+971 et Sél 7 + 9 +101 du SSr RIXHEIM-St LOUIS V1 et SSr St Louis Frontière V1 + Feeder( SEL 16) créer la semaine précédente\nV1V1BisV2V2Bis: ZEP 929+969+971 + ZEP 928+968+970 + sur VS:  ZEP 959+958+957 et Faisceau + Feeder Y + Sél 8+10+12+14+102+104 du SSr RIXHEIM-St LOUIS V2 + Feeder Z et SSr St Louis Frontière V2\nSél 7 + 9 +101 du SSr RIXHEIM-St LOUIS V1 et SSr St Louis Frontière V1",null,null,"115000",45574,"High","1,2,3,4,5,6,7",null,null,"00903",null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F53253",null,"< >",5746,5721,2027,2027,44,47,"2027-10-25","00:00:00","2027-11-14",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"655000",45574,"High","1,2,3,4,5,6,7",null,null,"05765",null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F53398",null,"< >",5874,5862,2027,2027,36,39,"2027-08-30","00:00:00","2027-09-19",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"746000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F54093 ",null,"< >",436,439,2027,2027,27,46,"2027-06-28","00:00:00","2027-11-07",0.99998842592592585,"132 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4S DEF 8h00 sim V1V2 de nuit pour principaux\n14S DEF 7h00 sim V1V2 pour prépa et finition et connexes\nV1: Du C303 Km 354,238 de Dieulouard au Km 362,850 de Pont à Mousson\nV2: Du C456 Km 362,955 de Pont à Mousson au C301Km 354,950 de Dieulouard\nSecteur Marbache Champ-Salmon (Km 347,507/347,512 au 367,500)\nSous-secteur Marbache-Dieulouard V1 (Km 347,507 au 356,185) \nSous-secteur Marbache-Dieulouard V2 (Km 347,512 au 355,424)\nSous-secteur Dieulouard- Champ Salmon V1 (Km 356,185 au 367,500) \nSous-secteur Belleville-Dieulouard V2bis (Km 351,522 au 355,424) \nSous-secteur Dieulouard- Champ Salmon V2 (Km 355,424 au 367,500) \nSous-secteur Blénod embranchement EDF",null,null,"90000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F54212",null,"< >",5834,5825,2027,2027,4,9,"2027-01-18","00:00:00","2027-02-21",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"4"]
[null,"SNCF-R","F54283",null,"< >",281,282,2027,2027,29,36,"2027-07-12","00:00:00","2027-08-29",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"3S DEF 7h00 sim V1V2 de nuit dans l'ombre des capacités d'EG3\n3S fermeture dans l'ombre de la fermeture de Boudelin\nDFV Type L Troyes - Chaumont V1 + V2",null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"9"]
[null,"SNCF-R","F54283",null,"< >",281,282,2027,2027,33,36,"2027-08-09","00:00:00","2027-08-29",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"3S DEF 7h00 sim V1V2 de nuit dans l'ombre des capacités d'EG3\n3S fermeture dans l'ombre de la fermeture de Boudelin\nDFV Type L Troyes - Chaumont V1 + V2",null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F54402",null,"< >",8843,1629,2027,2027,6,17,"2027-02-01","00:00:00","2027-04-18",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"229000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"5"]
[null,"SNCF-R","F54647",null,"< >",4422,4427,2027,2027,23,27,"2027-05-31","00:00:00","2027-06-27",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F54656",null,"< >",4790,4836,2027,2027,27,30,"2027-06-28","00:00:00","2027-07-18",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F54744",null,"< >",2141,2120,2027,2027,6,13,"2027-02-01","00:00:00","2027-03-21",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4S DEF 8h00 Sim V1 + V2 + Voie Mère + Impasse A\n2S DEF 7h00 Sim V1 + V2 + Voie Mère + Impasse A\nZEP type L Compiègne Tergnier V1\nZEP type L Tergnier Compiègne V2\nZEP type G Tergnier PRS : 18+1 +2+12+16+17\nSSr Tergnier-Appilly Voie 1\nSSr Tergnier-Appilly Voie 2\nSEL 1  du ss secteur Tergnier-Essigny le Grand V1\nSEL 2 du ss seceur Tergnier-Essigny le Grand V2\nSEL102 (voei Mere) et SEL 162 (Impasse A)",null,null,"242000",45574,"High","1,2,3,4,5,6,7",null,null,"02049",null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F54916",null,"< >",2298,2299,2027,2027,43,51,"2027-10-18","00:00:00","2027-12-12",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1S DEF de 7h00 de nuit  Sim V1 V2\n15S DEF de 8h00 de nuit Sim V1 V2\n1 WE de 120h Sim V1 V2",null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"7"]
[null,"SNCF-R","F55451",null,"< >",4341,4335,2027,2027,14,31,"2027-03-29","00:00:00","2027-07-25",0.99998842592592585,"118 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Chantier mutualisé avec CdV ITE\n5N DiLu à JeVe",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F56754",null,"< >",4333,4333,2027,2027,40,42,"2027-09-27","00:00:00","2027-10-10",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"561000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F56790",null,"< >",4052,4053,2027,2027,4,12,"2027-01-18","00:00:00","2027-03-14",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déformé SIM 7h (au lieu 6h)\n5 Nuits Di/Lu au Je/Ve",null,null,"500000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F57051",null,"< >",391,393,2027,2027,24,31,"2027-06-07","00:00:00","2027-07-25",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"10S DEF 8h00 sim V1 V2 de S4 à S13\nZEP LNE-412,5 V1 + ZEP 411,8- LNE V2 \nSs SR LUN Rohé V1  + Sel 34+36B+36A du Ssr LUN Rohé V2   \n\n6S DEF 8h00 sim VA VB VC VD VE de S23 à S28\nZEP : Grpt ZEP 604 Grpt ZEP 605 Grpt ZEP 607 Grpt ZEP 612\nSEL : Ss SR LUN Rohé V1 & V2 + Sel Secondaire Gare de LUN + Ss Sr Blainville Lunéville V1 & V2\n\nTTX - Base arrière Blainville \n\nEventuellement voir pour des marches en début et/ou fin de période avec garage au faisceau VS de Lunéville",null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F57122",null,"< >",5970,5979,2027,2027,14,30,"2027-03-29","00:00:00","2027-07-18",0.99998842592592585,"111 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F57890",null,"< >",4780,4764,2027,2027,10,24,"2027-03-01","00:00:00","2027-06-06",0.99998842592592585,"97 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"13 Sem DEF \n2 OCP 60H",null,null,"570000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F57890",null,"< >",4780,4764,2027,2027,13,24,"2027-03-22","00:00:00","2027-06-06",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F58002",null,"< >",4439,4443,2027,2027,39,47,"2027-09-20","00:00:00","2027-11-14",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"BA St Côme",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F58094",null,"< >",705,706,2027,2027,28,34,"2027-07-05","00:00:00","2027-08-15",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2S GEN de jour\n1S DEF 5h30 sim de nuit\n5S DEF 7h30 sim de nuit \nDFV Type L Amagne - Mohon V1 + V2\nSsr Saulces - Poix V1 + V2",null,null,"205000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F58130",null,"< >",8039,1063,2027,2027,18,42,"2027-04-26","00:00:00","2027-10-10",0.99998842592592585,"167 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"17S DEF 8h00 Sim de jour V1Bis V2Bis V3\n6S DEF 8h30 Sim de jour V1Bis V2Bis V3\nFermeture en continu de V1Bis V2Bis et V3 en gare d'Hagondange la S24 (Lu 8h30 au Ve 16h00) ZEP 110+323+321+311+313+813+811+807+805+428+426+424+422+430+810 d'Hagondange   \n\nGare d' UCKANGE  : Voie 1bis : ZEP type G 151+153+155+157+251 Voie 2Bis : 156+154+152+254+252 / ZEP type L Uckange Hagondange Voie 1bis et ZEP type L Hagondange Uckange Voie 2bis / Gare d' Hagondange Voie 1Bis ZEP type G 805+807+811+813+311+313+315+317+607        Voie 2bis : ZEP type G  810+430+428+426+424+424  Voie 3 : ZEP type G 315(commune 1bis)+ 323+321/ ZEP de type L+G H-W23 voie 1bis et ZEP type L+G W-H22 voie 2bis / Gare  de Woippy Voie 1 bis : ZEP de type G  81+79+75+73+71+59+57+55+53 Voie 2bis : ZEP de type G  82+78+74+72+70+68+62+58+56\nVoie 1 bis\nSous-secteur Montigny-Devant les Ponts V1bis (Km au 160,752)\nSous-secteur Devant les Ponts-Woippy V1 bis (Km 160,752 au 161,768)\nSous-secteur Woippy-Maizières V1 bis (Km 161,668 au 166,940)\nSous-secteur Maizières-Hagondange V1 bis (Km 166,940 au 172,435)\nSous-secteur Hagondange-Thionville V1 bis+ EP nord (Km 172,435 au 186,479)\nVoie 1\nSous-secteur Bellecroix-Woippy V1 (Km 156,125 au 161,557) simultanées pour Tx voie 2bis tiroir du TTx\nSous-secteur Maizières-Hagondange V1 (Km 166,675 au 172,435) simultanées pour Tx voie 2bis\nSous-secteur Hagondange-Thionville V1 (Km 172,435 au 176,356) simultanées pour Tx voie 2bis\nSel 4305+4307 du sous-secteur Thionville-Terville V1(Km 186,479 au 187,301) simultanées pour Tx voie 2bis\nVoie 2 bis\nSous-secteur Montigny-Devant les Ponts V2bis (Km au 160,955)\nSous-secteur Devant les Ponts-Woippy V2 bis (Km 160,955 au 161,672)\nSous-secteur Woippy-Maizières V2 bis (Km 161,672 au 167,279)\nSous-secteur Maizières-Hagondange V2 bis (Km 167,279 au 172,502)\nSous-secteur Hagondange-Thionville V2 bis (Km 172,502 au 186,228)\n\nWoippy travaux 1bis/2bis\nSel 203 du sous-secteur Woippy-Triage réception\nSel 610 du sous-secteur Woippy-Triage réception\nSel 256 du sous-secteur Woippy-Triage réception\nSel 258 du sous-secteur Woippy-Triage réception\nSel 101 du sous-secteur Woippy-Triage départ\nSel 100 du sous-secteur Woippy-Triage départ pas obligatoire\nSel 159 du sous-secteur Woippy-Triage départ pas obligatoire\nHagondange travaux 1bis/2bis\nSous-secteur Hagondange faisceau \n\nOU\n\nSel 305 du sous-secteur Hagondange faisceau\nSel 209 du sous-secteur Hagondange faisceau\nSel 213 du sous-secteur Hagondange faisceau\n\n",null,null,"180000",45574,"High","1,2,3,4,5,6,7",null,null,"01100",null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F58130",null,"< >",1064,1071,2027,2027,18,42,"2027-04-26","00:00:00","2027-10-10",0.99998842592592585,"167 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"17S DEF 8h00 Sim de jour V1Bis V2Bis V3\n6S DEF 8h30 Sim de jour V1Bis V2Bis V3\nFermeture en continu de V1Bis V2Bis et V3 en gare d'Hagondange la S24  (Lu 8h30 au Ve 16h00) ZEP 110+323+321+311+313+813+811+807+805+428+426+424+422+430+810 d'Hagondange   \n\nGare d' UCKANGE  : Voie 1bis : ZEP type G 151+153+155+157+251 Voie 2Bis : 156+154+152+254+252 / ZEP type L Uckange Hagondange Voie 1bis et ZEP type L Hagondange Uckange Voie 2bis / Gare d' Hagondange Voie 1Bis ZEP type G 805+807+811+813+311+313+315+317+607        Voie 2bis : ZEP type G  810+430+428+426+424+424  Voie 3 : ZEP type G 315(commune 1bis)+ 323+321/ ZEP de type L+G H-W23 voie 1bis et ZEP type L+G W-H22 voie 2bis / Gare  de Woippy Voie 1 bis : ZEP de type G  81+79+75+73+71+59+57+55+53 Voie 2bis : ZEP de type G  82+78+74+72+70+68+62+58+56\nVoie 1 bis\nSous-secteur Montigny-Devant les Ponts V1bis (Km au 160,752)\nSous-secteur Devant les Ponts-Woippy V1 bis (Km 160,752 au 161,768)\nSous-secteur Woippy-Maizières V1 bis (Km 161,668 au 166,940)\nSous-secteur Maizières-Hagondange V1 bis (Km 166,940 au 172,435)\nSous-secteur Hagondange-Thionville V1 bis+ EP nord (Km 172,435 au 186,479)\nVoie 1\nSous-secteur Bellecroix-Woippy V1 (Km 156,125 au 161,557) simultanées pour Tx voie 2bis tiroir du TTx\nSous-secteur Maizières-Hagondange V1 (Km 166,675 au 172,435) simultanées pour Tx voie 2bis\nSous-secteur Hagondange-Thionville V1 (Km 172,435 au 176,356) simultanées pour Tx voie 2bis\nSel 4305+4307 du sous-secteur Thionville-Terville V1(Km 186,479 au 187,301) simultanées pour Tx voie 2bis\nVoie 2 bis\nSous-secteur Montigny-Devant les Ponts V2bis (Km au 160,955)\nSous-secteur Devant les Ponts-Woippy V2 bis (Km 160,955 au 161,672)\nSous-secteur Woippy-Maizières V2 bis (Km 161,672 au 167,279)\nSous-secteur Maizières-Hagondange V2 bis (Km 167,279 au 172,502)\nSous-secteur Hagondange-Thionville V2 bis (Km 172,502 au 186,228)\n\nWoippy travaux 1bis/2bis\nSel 203 du sous-secteur Woippy-Triage réception\nSel 610 du sous-secteur Woippy-Triage réception\nSel 256 du sous-secteur Woippy-Triage réception\nSel 258 du sous-secteur Woippy-Triage réception\nSel 101 du sous-secteur Woippy-Triage départ\nSel 100 du sous-secteur Woippy-Triage départ pas obligatoire\nSel 159 du sous-secteur Woippy-Triage départ pas obligatoire\nHagondange travaux 1bis/2bis\nSous-secteur Hagondange faisceau \n\nOU\n\nSel 305 du sous-secteur Hagondange faisceau\nSel 209 du sous-secteur Hagondange faisceau\nSel 213 du sous-secteur Hagondange faisceau\n\n",null,null,"180000",45574,"High","1,2,3,4,5,6,7",null,null,"01100",null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F58580",null,"< >",2777,8956,2027,2027,17,21,"2027-04-19","00:00:00","2027-05-16",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"990000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,1]
[null,"SNCF-R","F58703",null,"< >",8754,8754,2027,2027,49,51,"2027-11-29","00:00:00","2027-12-12",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F58761",null,"< >",1098,1098,2027,2027,17,20,"2027-04-19","00:00:00","2027-05-09",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2S DEF 8h00 Sim V1 + V2 de nuit\nS9C HAGONDANGE\nZEP TYPE G 822 + GROUPEMENT ZEP (817+819+821+826)\nSOUS SECTEUR VOIE 1  et VOIE 2 VALLEROY HAGONDANGE\nSél 4294 du SSR HAG-THI V1BIS",null,null,"85000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F58793",null,"< >",2884,2885,2027,2027,12,18,"2027-03-15","00:00:00","2027-04-25",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"420000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F59236",null,"< >",450,450,2027,2027,41,48,"2027-10-04","00:00:00","2027-11-21",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"3S DEF 2h00 sim de jour pour les implentations\n8S DEF 8h00 sim V1V2V1BisV2Bis de nuit \n1 OCP de 34h00 + 1 OCP de 48h00\nZEP 301+303+305+313+206+208+210+212+214+216+400\n",null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F59909",null,"< >",1510,8066,2027,2027,13,20,"2027-03-22","00:00:00","2027-05-09",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"5000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F59938",null,"< >",188,141,2027,2027,46,51,"2027-11-08","00:00:00","2027-12-12",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F59989",null,"< >",4889,4903,2027,2027,20,30,"2027-05-10","00:00:00","2027-07-18",0.99998842592592585,"69 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"A l'ombre AFSB\n5 nuits Di/Lu a Je/Ve\nM.E.S par RESEAU S15à19",null,null,"640000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F60101",null,"< >",4251,4255,2027,2027,12,19,"2027-03-15","00:00:00","2027-05-02",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP PAJU",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F60101",null,"< >",4246,4234,2027,2027,16,24,"2027-04-12","00:00:00","2027-06-06",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP (WE POLT) + génériques",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F60388",null,"< >",8270,4145,2027,2027,3,5,"2027-01-11","00:00:00","2027-01-24",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Travaux de jour à l'ombre des travaux SR Voie Boisseaux CERCOTTES ",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F60388",null,"< >",8270,4145,2027,2027,6,8,"2027-02-01","00:00:00","2027-02-14",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Travaux de jour à l'ombre des travaux SR Voie Boisseaux CERCOTTES ",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F60388",null,"< >",8270,4145,2027,2027,24,26,"2027-06-07","00:00:00","2027-06-20",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Travaux de jour à l'ombre des travaux SR Voie Boisseaux CERCOTTES ",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,1]
[null,"SNCF-R","F60388",null,"< >",8270,4145,2027,2027,27,29,"2027-06-28","00:00:00","2027-07-11",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Travaux de jour à l'ombre des travaux SR Voie Boisseaux CERCOTTES ",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,2]
[null,"SNCF-R","F60581",null,"< >",5825,5842,2027,2027,10,12,"2027-03-01","00:00:00","2027-03-14",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Travaux en journée en semaine avec 16 OCP en gare de Melun (coupures partielles)",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F60698",null,"< >",5043,5343,2027,2027,4,24,"2027-01-18","00:00:00","2027-06-06",0.99998842592592585,"139 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F60706",null,"< >",5985,5983,2027,2027,15,20,"2027-04-05","00:00:00","2027-05-09",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP sur VS (V9RI)",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F60708",null,"< >",5823,5824,2027,2027,4,9,"2027-01-18","00:00:00","2027-02-21",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP de 54h de coupure Paris Clermont\n\nPerte de temps < 2min",null,null,"830000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F60999",null,"< >",5734,5725,2027,2027,3,33,"2027-01-11","00:00:00","2027-08-08",0.99998842592592585,"209 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"6h de SIM toute l'année\n5 nuits Di/Lu à Je/Ve\nJanv-Juin IPCS SVT/BYE\nJuil-Dec IPCS DAX/SVT",null,null,"655000",45574,"High","1,2,3,4,5,6,7",null,null,"05765",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F61012",null,"< >",1117,1128,2027,2027,35,41,"2027-08-23","00:00:00","2027-10-03",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"5S DEF 8h00 de jour Sim (5h / 13h)\n1 WE de 59h00\n2 WE de 15h30 (Dimanche)\nImpact RO-DO-RE-DEPART-DEPOT (phasage en cours), ",null,null,"180000",45574,"High","1,2,3,4,5,6,7",null,null,"01100",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F61019",null,"< >",1632,1633,2027,2027,31,33,"2027-07-26","00:00:00","2027-08-08",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"229000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F61019",null,"< >",1632,1633,2027,2027,39,44,"2027-09-20","00:00:00","2027-10-24",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"229000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F61245",null,"< >",4119,4128,2027,2027,15,25,"2027-04-05","00:00:00","2027-06-13",0.99998842592592585,"69 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F61245",null,"< >",4119,4128,2027,2027,24,27,"2027-06-07","00:00:00","2027-06-27",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F61352",null,"< >",4164,4591,2027,2027,5,20,"2027-01-25","00:00:00","2027-05-09",0.99998842592592585,"104 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"14 Sem 8H SIM de nuits",null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F61352",null,"< >",4164,4591,2027,2027,6,19,"2027-02-01","00:00:00","2027-05-02",0.99998842592592585,"90 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F61575",null,"< >",3836,3835,2027,2027,14,28,"2027-03-29","00:00:00","2027-07-04",0.99998842592592585,"97 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"515000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F61689",null,"< >",5858,8345,2027,2027,5,8,"2027-01-25","00:00:00","2027-02-14",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Génériques de jour",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F61689",null,"< >",5858,8345,2027,2027,12,16,"2027-03-15","00:00:00","2027-04-11",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Génériques de jour",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F61690",null,"< >",5858,8348,2027,2027,12,16,"2027-03-15","00:00:00","2027-04-11",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déformées de jour",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F61690",null,"< >",5858,8348,2027,2027,22,26,"2027-05-24","00:00:00","2027-06-20",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déformées de jour",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F61690",null,"< >",5858,8348,2027,2027,40,44,"2027-09-27","00:00:00","2027-10-24",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déformées de jour",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F61690",null,"< >",8348,6194,2027,2027,5,8,"2027-01-25","00:00:00","2027-02-14",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Plages de nuit alignées avec chantier BFC",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F61728",null,"< >",1178,1178,2027,2027,22,37,"2027-05-24","00:00:00","2027-09-05",0.99998842592592585,"104 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Prévu être réalisé pendant une fermeture de 3 mois de Juin à Août avec 2 RRI transformés en HS + RVB tunnel de Montois (chantier 205) + RAV Hagondange (chantier 190)",null,null,"85000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F61740",null,"< >",5033,5016,2027,2027,11,25,"2027-03-08","00:00:00","2027-06-13",0.99998842592592585,"97 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"12 sem Gen Nuits Longues",null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F61829",null,"< >",4251,4255,2027,2027,11,34,"2027-03-08","00:00:00","2027-08-15",0.99998842592592585,"160 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F61829",null,"< >",4251,4255,2027,2027,37,43,"2027-09-06","00:00:00","2027-10-17",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F61829",null,"< >",4251,4255,2027,2027,13,16,"2027-03-22","00:00:00","2027-04-11",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F61829",null,"< >",4251,4255,2027,2027,23,26,"2027-05-31","00:00:00","2027-06-20",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F61874",null,"< >",5681,5678,2027,2027,46,51,"2027-11-08","00:00:00","2027-12-12",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4 Sem génériques\nOCP18H",null,null,"650000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F61905",null,"< >",2054,721,2027,2027,29,35,"2027-07-12","00:00:00","2027-08-22",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Avec Chantier 4 RB Bt RAV : les consistances ayant changés le regroupement avec RAV Hirson n'est plus possible\n\n1S DEF 7h00 sim V1V2 de jour\n5S DEF 8h00 sim V1V2 de jour\n\nZEP Hirson - Liart voie 1 et V2",null,null,"212000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F62029",null,"< >",5767,5747,2027,2027,42,47,"2027-10-11","00:00:00","2027-11-14",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4 Sem de Générique\n1 OCP 24H",null,null,"655000",45574,"High","1,2,3,4,5,6,7",null,null,"05765",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F62037",null,"< >",5826,5850,2027,2027,5,7,"2027-01-25","00:00:00","2027-02-07",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F62232",null,"< >",6198,6195,2027,2027,36,51,"2027-08-30","00:00:00","2027-12-12",0.99998842592592585,"104 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déormées de jour alignées avec chantier BFC\n\nPertes de temps > 2min",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F62609",null,"< >",4786,4786,2027,2027,22,26,"2027-05-24","00:00:00","2027-06-20",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"8 sem FenGenJour",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F62652",null,"< >",4044,4054,2027,2027,41,49,"2027-10-04","00:00:00","2027-11-28",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"500000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63064",null,"< >",1725,1726,2027,2027,16,21,"2027-04-12","00:00:00","2027-05-16",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63065",null,"< >",4219,4220,2027,2027,18,23,"2027-04-26","00:00:00","2027-05-30",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63066",null,"< >",145,146,2027,2027,41,44,"2027-10-04","00:00:00","2027-10-24",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63115",null,"< >",1101,1128,2027,2027,20,26,"2027-05-10","00:00:00","2027-06-20",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"5S Def 5h sur V2 (ZEP 4620, SEL 4204 du sous secteur Bellecroix Woippy V2)\n3 WE Nuits Sa/Di et Di/Lu 6h V1 et V2 (ZEP 4620+4603+4601, SEL 2136 du sous secteur Metz Ville Bellecroix V2 + Sel 2135 et 2137 du sous secteur Metz Ville Bellecroix V1 + sous secteur Bellecroix Woippy V1 et V2",null,null,"180000",45574,"High","1,2,3,4,5,6,7",null,null,"01100",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63164",null,"< >",2752,2617,2027,2027,12,20,"2027-03-15","00:00:00","2027-05-09",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F63164",null,"< >",2752,2617,2027,2027,12,20,"2027-03-15","00:00:00","2027-05-09",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63181",null,"< >",6255,6255,2027,2027,4,27,"2027-01-18","00:00:00","2027-06-27",0.99998842592592585,"160 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"9S DEF 6h Sim V1 V2 de jour\n13S DEF 7h Sim V1 V2 de jour\n1WE 12h\n1WE de 24h\n1 WE de 34h\n2 WE de 48h\n1 et 2  \nInterdiction itinéraire  sur la com accès voies A et B interdites côté DIJON  de S10 à S14\nFermeture Faisceau Pair de S19 à S20\nFermeture fx 3/9 de S21 à S23",null,null,"849000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F63251",null,"< >",469,495,2027,2027,12,24,"2027-03-15","00:00:00","2027-06-06",0.99998842592592585,"83 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"9S DEF 7h00 sim V1V2 de Jour\n2S DEF 6h00 sim V1V2 de Jour P+F",null,null,"32000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63305",null,"< >",5830,5831,2027,2027,4,31,"2027-01-18","00:00:00","2027-07-25",0.99998842592592585,"188 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"5 OCP dont 3 OCP 4v/4 entre VSG et Combs",null,null,"830000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F63305",null,"< >",5829,5831,2027,2027,12,15,"2027-03-15","00:00:00","2027-04-04",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP de 15h de coupure de la plateforme alignée avec opérations SDMR\nPertes de temps<2min",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63389",null,"< >",4786,4786,2027,2027,5,18,"2027-01-25","00:00:00","2027-04-25",0.99998842592592585,"90 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"12 sem DEF 7h30 monovoie",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63394",null,"< >",1714,2214,2027,2027,32,40,"2027-08-02","00:00:00","2027-09-26",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63446",null,"< >",1602,1608,2027,2027,5,14,"2027-01-25","00:00:00","2027-03-28",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"990000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63581",null,"< >",1101,1128,2027,2027,5,11,"2027-01-25","00:00:00","2027-03-07",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"5S Def 6h sur VS (1S sur VS 15 (ZEL213) et 4S sur VS 56 et VS58 (ZEP 376, SEL 150) )\n3 WE Nuits Sa/Di et Di/Lu 6h V1, V2, V1M, V2M, VS56 ( sous secteur Metz Ville - Bellecroix V1 et V2, sous secteur Metz Ville  faisceau, sous secteur Metz Ville entretien, sous secteur Sablon Est Metz Ville V1M et V2M)",null,null,"180000",45574,"High","1,2,3,4,5,6,7",null,null,"01100",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63594",null,"< >",4320,6069,2027,2027,26,32,"2027-06-21","00:00:00","2027-08-01",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Génériques de nuit \n\nPertes de temps < 2min",null,null,"750000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63598",null,"< >",5846,5846,2027,2027,4,9,"2027-01-18","00:00:00","2027-02-21",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP de coupure de l'axe + génériques\n\nPertes de temps < 2min",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63598",null,"< >",5946,5945,2027,2027,8,15,"2027-02-15","00:00:00","2027-04-04",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP de coupure de l'axe + génériques\n\nPertes de temps < 2min",null,null,"750000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,1]
[null,"SNCF-R","F63599",null,"< >",5853,5854,2027,2027,4,6,"2027-01-18","00:00:00","2027-01-31",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP de coupure de l'axe + génériques\n\nPertes de temps < 2min",null,null,"750000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63600",null,"< >",6071,6070,2027,2027,28,31,"2027-07-05","00:00:00","2027-07-25",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"750000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F63600",null,"< >",6071,6070,2027,2027,30,33,"2027-07-19","00:00:00","2027-08-08",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"750000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63711",null,"< >",207,206,2027,2027,39,50,"2027-09-20","00:00:00","2027-12-05",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63716",null,"< >",5866,5823,2027,2027,34,39,"2027-08-16","00:00:00","2027-09-19",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"746000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F63716",null,"< >",5866,5823,2027,2027,36,39,"2027-08-30","00:00:00","2027-09-19",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"746000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63754",null,"< >",8834,56,2027,2027,4,11,"2027-01-18","00:00:00","2027-03-07",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63796",null,"< >",719,719,2027,2027,8,23,"2027-02-15","00:00:00","2027-05-30",0.99998842592592585,"104 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"12S DEF jour 7h30 sim V1V2\nDFV Charleville Liart V1 + V2 et ZEP 301+303+305+315 V1 et ZEP 300 + 304 + 306 + 308 + 310 V2 de Liart\nSous Secteur Rouvroy - L'Echelle V1 + V2 ET Sous Secteur Aouste - Rouvroy - l'Echelle V1 + V2",null,null,"222000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63891",null,"< >",5737,5740,2027,2027,37,42,"2027-09-06","00:00:00","2027-10-10",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4 Sem de Générique\n1 OCP 24H\n1Km de LTV40",null,null,"655000",45574,"High","1,2,3,4,5,6,7",null,null,"05765",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63946",null,"< >",8820,4547,2027,2027,5,14,"2027-01-25","00:00:00","2027-03-28",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Tx en Generiques et MES en Nuits WE",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F63946",null,"< >",4552,8812,2027,2027,21,32,"2027-05-17","00:00:00","2027-08-01",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Tx en Generiques et MES en Nuits WE",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63946",null,"< >",4552,8812,2027,2027,45,50,"2027-11-01","00:00:00","2027-12-05",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Tx en Generiques et MES en Nuits WE",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F63957",null,"< >",4786,4786,2027,2027,11,18,"2027-03-08","00:00:00","2027-04-25",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63957",null,"< >",4786,4786,2027,2027,11,18,"2027-03-08","00:00:00","2027-04-25",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F63962",null,"< >",4526,4528,2027,2027,46,51,"2027-11-08","00:00:00","2027-12-12",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déformée avec SIM partielle choix V1 / V2 à affiner.\nOCP48h S46",null,null,"570000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F63962",null,"< >",4526,4528,2027,2027,47,51,"2027-11-15","00:00:00","2027-12-12",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F63962",null,"< >",4526,4528,2027,2027,47,51,"2027-11-15","00:00:00","2027-12-12",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,1]
[null,"SNCF-R","F64030",null,"< >",2126,2116,2027,2027,12,18,"2027-03-15","00:00:00","2027-04-25",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4S DEF 7h30 V1 V2 V4 à V12\n4S DEF 8h00 V1 V2 V4 à V12\nZEP type G : 1333+65+61+55+60+56+62+64+66+57 + 8\nZEP 59 en continu \nSEL Groupe 4\n(mais besoin de SEL 108+110)\n1 WE de 24h et 1 WE de 64h\nZEP type G : 1333+65+61+55+60+56+62+64+66+57 + 8\nZEP 59 en continu \nSEL Groupe 4\n(mais besoin de SEL 108+110)",null,null,"261000",45574,"High","1,2,3,4,5,6,7",null,null,"02049",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64030",null,"< >",2126,2116,2027,2027,12,18,"2027-03-15","00:00:00","2027-04-25",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4S DEF 7h30 V1 V2 V4 à V12\n4S DEF 8h00 V1 V2 V4 à V12\nZEP type G : 1333+65+61+55+60+56+62+64+66+57 + 8\nZEP 59 en continu \nSEL Groupe 4\n(mais besoin de SEL 108+110)\n1 WE de 24h et 1 WE de 64h\nZEP type G : 1333+65+61+55+60+56+62+64+66+57 + 8\nZEP 59 en continu \nSEL Groupe 4\n(mais besoin de SEL 108+110)",null,null,"261000",45574,"High","1,2,3,4,5,6,7",null,null,"02049",null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F64030",null,"< >",2120,2120,2027,2027,10,17,"2027-03-01","00:00:00","2027-04-18",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"3S DEF 7h30 V1 V2 V4 à V12\n3S DEF 8h00 V1 V2 V4 à V12\nZEP type G : 1333+65+61+55+60+56+62+64+66+57 + 8\nZEP 59 en continu \nSEL Groupe 4\n(mais besoin de SEL 108+110)\n1 WE de 24h et 1 WE de 64h\nZEP type G : 1333+65+61+55+60+56+62+64+66+57 + 8\nZEP 59 en continu \nSEL Groupe 4\n(mais besoin de SEL 108+110)",null,null,"242000",45574,"High","1,2,3,4,5,6,7",null,null,"02049",null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F64038",null,"< >",3937,3936,2027,2027,3,14,"2027-01-11","00:00:00","2027-03-28",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"538000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F64038",null,"< >",3937,3936,2027,2027,37,46,"2027-09-06","00:00:00","2027-11-07",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"538000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"4"]
[null,"SNCF-R","F64038",null,"< >",3937,3936,2027,2027,3,14,"2027-01-11","00:00:00","2027-03-28",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"538000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64076",null,"< >",108,109,2027,2027,25,30,"2027-06-14","00:00:00","2027-07-18",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64153",null,"< >",8270,4145,2027,2027,4,6,"2027-01-18","00:00:00","2027-01-31",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déformées de jour alignées avec SR Voie Boisseaux Cercottes",null,null,"570000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F64153",null,"< >",8270,4145,2027,2027,7,9,"2027-02-08","00:00:00","2027-02-21",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déformées de jour alignées avec SR Voie Boisseaux Cercottes",null,null,"570000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64153",null,"< >",8270,4145,2027,2027,34,36,"2027-08-16","00:00:00","2027-08-29",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déformées de jour alignées avec SR Voie Boisseaux Cercottes",null,null,"570000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64234",null,"< >",4835,4837,2027,2027,13,26,"2027-03-22","00:00:00","2027-06-20",0.99998842592592585,"90 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"TX 5 nuits : (12sem & 5 OCP)\nDi/Lu en Générique\nLu/Ma -> Je/Ve en Déformé\nLTV aussi sur L570321 Racco V1S et V2S ",null,null,"570000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64256",null,"< >",80,70,2027,2027,4,7,"2027-01-18","00:00:00","2027-02-07",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64257",null,"< >",8834,56,2027,2027,4,11,"2027-01-18","00:00:00","2027-03-07",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64470",null,"< >",2991,8209,2027,2027,26,30,"2027-06-21","00:00:00","2027-07-18",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Fen GEN Nuits\nCampagne 1 : S25à27\nCampagne 2 : S45à49",null,null,"431000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64525",null,"< >",719,719,2027,2027,18,23,"2027-04-26","00:00:00","2027-05-30",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4S DEF jour 7h30 sim V1V2\nDFV Charleville Liart V1 + V2 et ZEP 301+303+305+315 V1 et ZEP 300 + 304 + 306 + 308 + 310 V2 de Liart\nSous Secteur Rouvroy - L'Echelle V1 + V2 ET Sous Secteur Aouste - Rouvroy - l'Echelle V1 + V2",null,null,"222000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64557",null,"< >",2355,2357,2027,2027,22,25,"2027-05-24","00:00:00","2027-06-13",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2S de Gen 6h00 Sim de nuit\n1 WE de 24h01\nDFV Type L \nZEP  ETAPLES - BOULOGNE voie 1\nV2: DFV Type G ZEP 124\nSous Secteur Pont de Briques - Etaples Voie 1\nSous Secteur Pont de Briques - Etaples Voie 2",null,null,"311000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64557",null,"< >",2355,2357,2027,2027,23,25,"2027-05-31","00:00:00","2027-06-13",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2S de Gen 6h00 Sim de nuit\n1 WE de 24h01\nDFV Type L \nZEP  ETAPLES - BOULOGNE voie 1\nV2: DFV Type G ZEP 124\nSous Secteur Pont de Briques - Etaples Voie 1\nSous Secteur Pont de Briques - Etaples Voie 2",null,null,"311000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F64561",null,"< >",372,371,2027,2027,22,37,"2027-05-24","00:00:00","2027-09-05",0.99998842592592585,"104 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"14S DEF 6h00 sim V1V2 (23h00 à 5h00)\nZEP : Voie 1 : DFV type L Nancy-Varangéville + ZEP 111 + ZEP 113\nVoie 2 : DFV type G ZEP 216 + 214\nSEL Voie 1 : Ss secteur Grise côte Rosières\nVoie 2 : Ss secteur Grise côte Rosières \n\n\n",null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64614",null,"< >",5136,4966,2027,2027,47,51,"2027-11-15","00:00:00","2027-12-12",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64614",null,"< >",4965,5031,2027,2027,8,12,"2027-02-15","00:00:00","2027-03-14",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F64711",null,"< >",5871,5870,2027,2027,38,46,"2027-09-13","00:00:00","2027-11-07",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP de coupure de l'axe + déformées de jour\n\nPertes de temps < 2min",null,null,"746000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64712",null,"< >",5846,5844,2027,2027,16,19,"2027-04-12","00:00:00","2027-05-02",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64712",null,"< >",5846,5844,2027,2027,20,23,"2027-05-10","00:00:00","2027-05-30",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F64714",null,"< >",5845,5842,2027,2027,6,9,"2027-02-01","00:00:00","2027-02-21",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP de coupure de l'axe + génériques\n\nPertes de temps < 2min",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F64717",null,"< >",5863,5864,2027,2027,28,35,"2027-07-05","00:00:00","2027-08-22",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 OCP de coupure de l'axe + génériques\n\nPertes de temps < 2min",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64768",null,"< >",2462,1976,2027,2027,12,14,"2027-03-15","00:00:00","2027-03-28",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"7S DEF 8h00 sim V1V2 de nuit\n7S de DEF de nuit de 7h30 sur V2 et 7h00 sur V1",null,null,"301000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64768",null,"< >",2462,1976,2027,2027,34,49,"2027-08-16","00:00:00","2027-11-28",0.99998842592592585,"104 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"7S DEF 8h00 sim V1V2 de nuit\n7S de DEF de nuit de 7h30 sur V2 et 7h00 sur V1",null,null,"301000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64856",null,"< >",8819,4489,2027,2027,43,51,"2027-10-18","00:00:00","2027-12-12",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64884",null,"< >",4525,4526,2027,2027,19,21,"2027-05-03","00:00:00","2027-05-16",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64905",null,"< >",5040,5040,2027,2027,15,21,"2027-04-05","00:00:00","2027-05-16",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"5 sem Gen Jour et OCP 72H",null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F64919",null,"< >",4503,4510,2027,2027,20,22,"2027-05-10","00:00:00","2027-05-23",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65103",null,"< >",5820,5820,2027,2027,6,9,"2027-02-01","00:00:00","2027-02-21",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65103",null,"< >",5820,5820,2027,2027,6,9,"2027-02-01","00:00:00","2027-02-21",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65108",null,"< >",5842,5828,2027,2027,40,43,"2027-09-27","00:00:00","2027-10-17",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F65140",null,"< >",2752,2608,2027,2027,3,7,"2027-01-11","00:00:00","2027-02-07",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334900",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65140",null,"< >",2752,8183,2027,2027,3,7,"2027-01-11","00:00:00","2027-02-07",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F65257",null,"< >",755,760,2027,2027,16,28,"2027-04-12","00:00:00","2027-07-04",0.99998842592592585,"83 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"interdit de S26 à S35\n3S de DEF 2h00 de jour Sim V1 + V2\n8S de DEF 7h30 de jour Sim V1 + V2\nZEP 1+2+3+4+6+ DFV type L v1 + V2 côté Paris\nSSr Loisy-Vitry V1 + V2 ET SEL 28 + 30 SSr Vitry Favresse V2 et  SEL 112 SSr Viry Voie bis et Faisceau\n1 WE de 34h00 et 1 WE de 48h00 Sim V1 V2 VU V2Bis\nZEP : 1+2+3+4+6+8+64+9+10+11+12+16 + type L V1+V2 côté Paris\nSSr Loisy-Vitry V1 + V2 ET SEL 28 + 30 SSr Vitry Favresse V2 et  SEL 112 SSr Viry Voie bis et Faisceau\n\nFERMETURE Faisceau Pair Voies 12 à 22\nZEP 18+85+86+87+88+89+90+91+77\nSEL 112 SSr Viry Voie bis et Faisceau",null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65262",null,"< >",297,294,2027,2027,33,38,"2027-08-09","00:00:00","2027-09-12",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"7S DEF 7h00 sim V1V2 de nuit dans l'ombre ddes capacités de Boudelin\n3S fermeture dans l'ombre de la fermeture d'EG3\nDFV Type L Bar sur Aube - Chaumont Voie 1 + Voie 2",null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65290",null,"< >",5970,5972,2027,2027,10,26,"2027-03-01","00:00:00","2027-06-20",0.99998842592592585,"111 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2 OCP de 72h et une période de fermeture de 15j affectant plusieurs voies à quai à Paris Gare de Lyon",null,null,"830000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65415",null,"< >",4722,4723,2027,2027,3,32,"2027-01-11","00:00:00","2027-08-01",0.99998842592592585,"202 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"DEF 6H30 en SIM toute l'année\n5N de DiLu à JeVe",null,null,"655000",45574,"High","1,2,3,4,5,6,7",null,null,"05765",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65491",null,"< >",4000,3978,2027,2027,3,20,"2027-01-11","00:00:00","2027-05-09",0.99998842592592585,"118 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2 ITC Longues : 11j et 5 j\n13sem DEF JOUR 8H",null,null,"500000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65592",null,"< >",577,1818,2027,2027,3,13,"2027-01-11","00:00:00","2027-03-21",0.99998842592592585,"69 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"229000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65627",null,"< >",3276,3278,2027,2027,14,16,"2027-03-29","00:00:00","2027-04-11",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"8S DEF 5h00 sim V1V2\n1 WE de 64h00\n\nV1 : ZEP type L Yvetot Bréauté Poste 2 Voie 1 + ZEP 201+203+205 + ZEP Type L Bréauté Poste 2 Le Havre Voie 1\nV2 : ZEP type L Bréauté Poste 2 Voie 2 + ZEP 202+204 + ZEP Type L Le Havre Bréauté Poste 2 Voie 2\n\nSous secteur Bolbec Etainhus V1 + Sous secteur Bolbec Etainhus V2\n\nTTX - Base arrière Bréauté",null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65637",null,"< >",4330,8930,2027,2027,3,17,"2027-01-11","00:00:00","2027-04-18",0.99998842592592585,"97 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"431000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65656",null,"< >",4060,4689,2027,2027,6,18,"2027-02-01","00:00:00","2027-04-25",0.99998842592592585,"83 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déformées 7H SIM 11sem\n5 Nuits du Di/Lu au Je/Ve\nLTV 60 9sem [+1,4]",null,null,"500000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65656",null,"< >",4060,4689,2027,2027,7,17,"2027-02-08","00:00:00","2027-04-18",0.99998842592592585,"69 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"500000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F65679",null,"< >",576,1528,2027,2027,15,28,"2027-04-05","00:00:00","2027-07-04",0.99998842592592585,"90 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65679",null,"< >",576,1528,2027,2027,21,26,"2027-05-17","00:00:00","2027-06-20",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F65684",null,"< >",5856,5857,2027,2027,3,7,"2027-01-11","00:00:00","2027-02-07",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65782",null,"< >",8510,2545,2027,2027,8,17,"2027-02-15","00:00:00","2027-04-18",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Avec chantier 24 (RR)\n8S DEF de 7h00 Sim V1 + V2\nV1: ZEP 83211\nV2: ZEP 80302",null,null,"250000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F65782",null,"< >",8510,2545,2027,2027,8,14,"2027-02-15","00:00:00","2027-03-28",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Avec chantier 24 (RR)\n8S DEF de 7h00 Sim V1 + V2\nV1: ZEP 83211\nV2: ZEP 80302",null,null,"250000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65790",null,"< >",1146,1141,2027,2027,15,21,"2027-04-05","00:00:00","2027-05-16",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1S DEF 7h30 sim V1V2 de nuit\n4S DEF 8h30 sim V1V2 de nuit \n1 WE de 45h00 du Sa 8h00 au Lu 5h00\n1WE de 31h00 du Sa 22h00 au Lun 5h00 V1V2\n1WE de 14h00 du Sa 22h00 au Dim 12h00 V1V2\nWE compatibles niveau alternatif avec PAM et Lunéville\n\nZEP : 703+704+705+706+707+708+709+710+717+720\n\nSEL V1 2303+2305+153 du SS Secteur Rémilly-Courcelles \nSEL V2  2310+2312 du SS Secteur Rémilly-Courcelles\n\nTTX - Base arrière non définie à date",null,null,"140000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65790",null,"< >",1143,1141,2027,2027,15,21,"2027-04-05","00:00:00","2027-05-16",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1S DEF 7h30 sim V1V2 de nuit\n4S DEF 8h30 sim V1V2 de nuit \n1 WE de 45h00 du Sa 8h00 au Lu 5h00\n1WE de 31h00 du Sa 22h00 au Lun 5h00 V1V2\n1WE de 14h00 du Sa 22h00 au Dim 12h00 V1V2\nWE compatibles niveau alternatif avec PAM et Lunéville\n\nZEP : 703+704+705+706+707+708+709+710+717+720\n\nSEL V1 2303+2305+153 du SS Secteur Rémilly-Courcelles \nSEL V2  2310+2312 du SS Secteur Rémilly-Courcelles\n\nTTX - Base arrière non définie à date",null,null,"140000",45574,"High","1,2,3,4,5,6,7",null,null,"01193",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65794",null,"< >",4234,4226,2027,2027,20,23,"2027-05-10","00:00:00","2027-05-30",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65794",null,"< >",4234,4226,2027,2027,20,23,"2027-05-10","00:00:00","2027-05-30",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65855",null,"< >",919,946,2027,2027,29,40,"2027-07-12","00:00:00","2027-09-26",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"7S DEF 6h00 de nuit sur V1 dont 4h30 de Sim V2\n3S DEF 6h00 de nuit sur V2 dont 4h30 de Sim V1",null,null,"115000",45574,"High","1,2,3,4,5,6,7",null,null,"00903",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65868",null,"< >",237,67,2027,2027,3,9,"2027-01-11","00:00:00","2027-02-21",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F65868",null,"< >",237,67,2027,2027,44,51,"2027-10-25","00:00:00","2027-12-12",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65895",null,"< >",1617,1618,2027,2027,38,50,"2027-09-13","00:00:00","2027-12-05",0.99998842592592585,"83 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"229000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F65895",null,"< >",1617,1618,2027,2027,41,48,"2027-10-04","00:00:00","2027-11-21",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"229000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F66133",null,"< >",8594,4788,2027,2027,48,50,"2027-11-22","00:00:00","2027-12-05",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F66133",null,"< >",8594,4788,2027,2027,48,50,"2027-11-22","00:00:00","2027-12-05",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F66358",null,"< >",1110,1110,2027,2027,47,50,"2027-11-15","00:00:00","2027-12-05",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2S DEF 8h30 de jour sur V1R V2R Entrée Sortie Dépôt de Metz\n1WE de 30h00 sur V1R V2R Entrée Sortie Dépôt de Metz\nZEP 3112+3114+3116+3118+3129+3131+3133+3236+3604\nSel 2140+2142 du SS Sablon Est-Montigny voies 2R-2Bis                                       Sel 2141 du SS Sablon Est-Montingy voies 1R-1Bis                                                 Sel 612 SS Sablon Dépôt",null,null,"192000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F66373",null,"< >",8118,8117,2027,2027,3,31,"2027-01-11","00:00:00","2027-07-25",0.99998842592592585,"195 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"8S GEN\n21S DEF 8h30 sur Voie Travaux dont 7h00 sur Voie Contigüe avec décalage de la Sim d'une heure maxi.\n3S DEF 9h00 sur Voie Travaux dont 7h00 sur Voie Contigüe avec décalage de la Sim d'une heure maxi.\nNeutralistion des AdV de S9 à S20.\nZEP:\nV1 : 726+2771 + 2773+ 2775+727 ET 2783\nV2 : 826+2776 + 2774 + 2772+827\nSEL:\nV1 : 447 et 449 + 451 + 453 et 455\nV2 : 444 et 446 + 448",null,null,"226000",45574,"High","1,2,3,4,5,6,7",null,null,"01856",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F66425",null,"< >",2677,2694,2027,2027,20,50,"2027-05-10","00:00:00","2027-12-05",0.99998842592592585,"209 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F66425",null,"< >",8183,2690,2027,2027,37,40,"2027-09-06","00:00:00","2027-09-26",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F66428",null,"< >",141,142,2027,2027,44,49,"2027-10-25","00:00:00","2027-11-28",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F66428",null,"< >",197,198,2027,2027,45,50,"2027-11-01","00:00:00","2027-12-05",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F66543",null,"< >",2752,8190,2027,2027,36,44,"2027-08-30","00:00:00","2027-10-24",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"973000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F66543",null,"< >",2752,8190,2027,2027,36,44,"2027-08-30","00:00:00","2027-10-24",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334900",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F66545",null,"< >",1558,1694,2027,2027,37,49,"2027-09-06","00:00:00","2027-11-28",0.99998842592592585,"83 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"330000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F66755",null,"< >",2814,2810,2027,2027,6,14,"2027-02-01","00:00:00","2027-03-28",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F66755",null,"< >",2814,2810,2027,2027,9,11,"2027-02-22","00:00:00","2027-03-07",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F66755",null,"< >",2814,2810,2027,2027,9,11,"2027-02-22","00:00:00","2027-03-07",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F66776",null,"< >",439,439,2027,2027,5,16,"2027-01-25","00:00:00","2027-04-11",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"17S DEF 8h00 sim V1V2 de nuit   La nuit du Jeudi 06/05 sera travaillée\n2 WE de 36h00\n1WE de 20h00\nWE compatibles niveau alternatif avec Lunéville\n\nZEP 1003 et 1002 de Pont-à-Mousson\n\nSEL Ss Sr Dieulouard Champs Salmon V1&V2\n\nTTX - Champigneulles, ouverture de nuit du poste C",null,null,"90000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F66776",null,"< >",439,439,2027,2027,22,30,"2027-05-24","00:00:00","2027-07-18",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"17S DEF 8h00 sim V1V2 de nuit   La nuit du Jeudi 06/05 sera travaillée\n2 WE de 36h00\n1WE de 20h00\nWE compatibles niveau alternatif avec Lunéville\n\nZEP 1003 et 1002 de Pont-à-Mousson\n\nSEL Ss Sr Dieulouard Champs Salmon V1&V2\n\nTTX - Champigneulles, ouverture de nuit du poste C",null,null,"90000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F66776",null,"< >",439,439,2027,2027,24,29,"2027-06-07","00:00:00","2027-07-11",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"10S DEF 8h00 sim V1V2 de nuit   La nuit du Jeudi 06/05 sera travaillée\n2 WE de 24h00\n1WE de 36h00\n\nZEP 1003 et 1002 de Pont-à-Mousson\n\nSEL Ss Sr Dieulouard Champs Salmon V1&V2\n\nTTX - Champigneulles, ouverture de nuit du poste C",null,null,"90000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F66827",null,"< >",5854,8353,2027,2027,26,43,"2027-06-21","00:00:00","2027-10-17",0.99998842592592585,"118 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"750000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F66905",null,"< >",2601,2600,2027,2027,40,47,"2027-09-27","00:00:00","2027-11-14",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"coupure estivale CASTOR",null,null,"962000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F67097",null,"< >",4233,4235,2027,2027,19,27,"2027-05-03","00:00:00","2027-06-27",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"745000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67098",null,"< >",4234,4226,2027,2027,15,26,"2027-04-05","00:00:00","2027-06-20",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"3 OCP (POLT) + génériques\n\nPertes de temps <  2min",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67188",null,"< >",92,92,2027,2027,8,19,"2027-02-15","00:00:00","2027-05-02",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"990311",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67204",null,"< >",56,8834,2027,2027,5,14,"2027-01-25","00:00:00","2027-03-28",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67258",null,"< >",4029,4036,2027,2027,14,21,"2027-03-29","00:00:00","2027-05-16",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Pas LTV car dejà LPV Patrimoine\n5N de DiLu à JeVe",null,null,"500000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67273",null,"< >",5734,5738,2027,2027,8,16,"2027-02-15","00:00:00","2027-04-11",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"7 Sem de Déformée SIM\n1500m de LTV100 glissante\nBA Laluque",null,null,"655000",45574,"High","1,2,3,4,5,6,7",null,null,"05765",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67399",null,"< >",3742,3742,2027,2027,14,31,"2027-03-29","00:00:00","2027-07-25",0.99998842592592585,"118 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Besoin ZEP et SEL sur faisceau Ouest Nates Blottereau toute l'année\nDEF 8H 4N luMa à JeVe",null,null,"515000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67435",null,"< >",8059,1337,2027,2027,20,27,"2027-05-10","00:00:00","2027-06-27",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"6S DEF 8h00 de nuit (21h00 - 5h00)\n1WE de 80h00 du Vendredi 21h00 au mardi 5h00\n1WE de 56h00 du Vendredi 21h00 au lundi 5h00\n2WE de 32h00 du samedi 21h00 au lundi 5h00\n",null,null,"145000",45574,"High","1,2,3,4,5,6,7",null,null,"01358",null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F67435",null,"< >",8059,1337,2027,2027,20,27,"2027-05-10","00:00:00","2027-06-27",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"6S DEF 8h00 de nuit (21h00 - 5h00)\n1WE de 80h00 du Vendredi 21h00 au mardi 5h00\n1WE de 56h00 du Vendredi 21h00 au lundi 5h00\n2WE de 32h00 du samedi 21h00 au lundi 5h00\n",null,null,"145000",45574,"High","1,2,3,4,5,6,7",null,null,"01358",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67435",null,"< >",8059,1337,2027,2027,21,24,"2027-05-17","00:00:00","2027-06-06",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"6S DEF 8h00 de nuit (21h00 - 5h00)\n1WE de 80h00 du Vendredi 21h00 au mardi 5h00\n1WE de 56h00 du Vendredi 21h00 au lundi 5h00\n2WE de 32h00 du samedi 21h00 au lundi 5h00\n",null,null,"145000",45574,"High","1,2,3,4,5,6,7",null,null,"01358",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67437",null,"< >",137,7994,2027,2027,30,37,"2027-07-19","00:00:00","2027-09-05",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F67437",null,"< >",137,7994,2027,2027,33,36,"2027-08-09","00:00:00","2027-08-29",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F67437",null,"< >",137,7994,2027,2027,33,36,"2027-08-09","00:00:00","2027-08-29",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67495",null,"< >",2438,2527,2027,2027,43,46,"2027-10-18","00:00:00","2027-11-07",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4S DEF 7h00 Sim V1 V2 de nuit\n7S DEF 7h30 Sim V1 V2 de nuit",null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67501",null,"< >",2496,2498,2027,2027,19,32,"2027-05-03","00:00:00","2027-08-01",0.99998842592592585,"90 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4S de GEN\n8S de DEF 7h30 Sim V1 V2 de nuit",null,null,"267000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67502",null,"< >",1916,1898,2027,2027,8,14,"2027-02-15","00:00:00","2027-03-28",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Avec chantiers 18 (RVB VM et P Lille Bif Justice) et 28 (RAV Lille Flandres)\n5S DEF 7h00 Domaine A: Nord Becquerel\n1 WE 42h00 Domaine B: Nord Becquerel + VS Dépôt\n3S DEF 7h00 Domaine C (Lion d'Or côté Mouscron) avec 4h00 Domaine D (Totale du Lion d'Or)\n1 WE 16h00 Domaine D: Totalité du Lion d'Or\n3S DEF 7h00 Domaine E (V6 à V17 Lille Flandres) avec 4h00 Domaine F (Totalité de la gare de Lille Flandres)\n1 WE 24h00 Domaine F: Totalité de la gare de Lille Flandres\n2 WE 36h00 Domaine F: Totalité de la gare de Lille Flandres\n2S DEF 7h00 Domaine G (V0 à V6) avec 4h00 (V7 à V17)",null,null,"289000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67505",null,"< >",92,85,2027,2027,44,51,"2027-10-25","00:00:00","2027-12-12",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"990000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67522",null,"< >",6196,6158,2027,2027,43,51,"2027-10-18","00:00:00","2027-12-12",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67524",null,"< >",2696,2660,2027,2027,11,38,"2027-03-08","00:00:00","2027-09-12",0.99998842592592585,"188 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67524",null,"< >",2696,2660,2027,2027,28,32,"2027-07-05","00:00:00","2027-08-01",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F67526",null,"< >",2617,2603,2027,2027,3,12,"2027-01-11","00:00:00","2027-03-14",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F67526",null,"< >",2617,2603,2027,2027,7,9,"2027-02-08","00:00:00","2027-02-21",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F67526",null,"< >",2617,2603,2027,2027,7,9,"2027-02-08","00:00:00","2027-02-21",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"334000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"4"]
[null,"SNCF-R","F67526",null,"< >",2617,2759,2027,2027,3,12,"2027-01-11","00:00:00","2027-03-14",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67526",null,"< >",2617,2759,2027,2027,5,9,"2027-01-25","00:00:00","2027-02-21",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F67526",null,"< >",2617,2759,2027,2027,5,9,"2027-01-25","00:00:00","2027-02-21",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F67528",null,"< >",106,108,2027,2027,31,44,"2027-07-26","00:00:00","2027-10-24",0.99998842592592585,"90 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F67528",null,"< >",106,108,2027,2027,37,42,"2027-09-06","00:00:00","2027-10-10",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"4"]
[null,"SNCF-R","F67528",null,"< >",106,108,2027,2027,41,44,"2027-10-04","00:00:00","2027-10-24",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67594",null,"< >",4402,4400,2027,2027,44,49,"2027-10-25","00:00:00","2027-11-28",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"4 sem DEF Nuits\nTx en 5 Nuits Di/LU à Je/Ve",null,null,"515000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67620",null,"< >",1556,1713,2027,2027,4,9,"2027-01-18","00:00:00","2027-02-21",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67620",null,"< >",1556,1713,2027,2027,6,8,"2027-02-01","00:00:00","2027-02-14",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F67665",null,"< >",1551,1701,2027,2027,8,12,"2027-02-15","00:00:00","2027-03-14",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"330000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F67665",null,"< >",1551,1701,2027,2027,15,20,"2027-04-05","00:00:00","2027-05-09",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"330000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F67665",null,"< >",1551,1701,2027,2027,21,26,"2027-05-17","00:00:00","2027-06-20",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"330000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"3"]
[null,"SNCF-R","F67665",null,"< >",1551,1701,2027,2027,31,35,"2027-07-26","00:00:00","2027-08-22",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"330000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67665",null,"< >",34,34,2027,2027,45,51,"2027-11-01","00:00:00","2027-12-12",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"962000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F67692",null,"< >",5879,5879,2027,2027,3,16,"2027-01-11","00:00:00","2027-04-11",0.99998842592592585,"90 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"SA2026 : 6 OCP de 45h de coupure de l'ensemble de la plateforme.\nEn semaine, travail de nuit 2v/4.",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67718",null,"< >",5859,5858,2027,2027,19,27,"2027-05-03","00:00:00","2027-06-27",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67846",null,"< >",5829,5825,2027,2027,8,21,"2027-02-15","00:00:00","2027-05-16",0.99998842592592585,"90 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Déformées 7h30 sim 1bis - 2bis",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F67910",null,"< >",5739,5737,2027,2027,37,43,"2027-09-06","00:00:00","2027-10-17",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"5 Sem de Générique\n1 OCP 24H",null,null,"655000",45574,"High","1,2,3,4,5,6,7",null,null,"05765",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F67910",null,"< >",5739,5737,2027,2027,37,43,"2027-09-06","00:00:00","2027-10-17",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"655000",45574,"High","1,2,3,4,5,6,7",null,null,"05765",null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F67951",null,"< >",8240,3749,2027,2027,25,27,"2027-06-14","00:00:00","2027-06-27",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"DEF 4 nuits",null,null,"530000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F67990",null,"< >",5191,5191,2027,2027,6,15,"2027-02-01","00:00:00","2027-04-04",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"10 sem de SIM 6H\n4 nuits LuMa-JeVe",null,null,"640000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F68074",null,"< >",1854,1852,2027,2027,3,7,"2027-01-11","00:00:00","2027-02-07",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"3S DEF Sim 7h00 de nuit\nDFV Type L \nZEP DUNKERQUE - HAZEBROUCK voie 2 (TTx)\nZEP HAZEBROUCK - DUNKERQUE voie 1 (TTx)\nSecteur Coudekerque DL\n",null,null,"301000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F68125",null,"< >",8342,5840,2027,2027,36,41,"2027-08-30","00:00:00","2027-10-03",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F68208",null,"< >",760,8031,2027,2027,10,22,"2027-03-01","00:00:00","2027-05-23",0.99998842592592585,"83 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"3S DEF 2h00 sim de jour\n8S DEF 7h00 sim de jour\n2 WE de 40h00 \n1 WE de 48h00\nZEP de St Dizier\n127+131 V1 / 104+106 V2\nSEL 141 Ssr St Dizier Gare V1",null,null,"20000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F68276",null,"< >",5832,5831,2027,2027,16,31,"2027-04-12","00:00:00","2027-07-25",0.99998842592592585,"104 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2 OCP de coupure entre VSG et Combs. Perte de temps >2min",null,null,"830000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F68276",null,"< >",5832,5831,2027,2027,16,20,"2027-04-12","00:00:00","2027-05-09",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F68350",null,"< >",82,106,2027,2027,10,27,"2027-03-01","00:00:00","2027-06-27",0.99998842592592585,"118 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"1000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F68793",null,"< >",706,697,2027,2027,34,45,"2027-08-16","00:00:00","2027-10-31",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"10S DEF 7h00 de nuit Sim V1 V2\nZEP Type L Amagne - Mohon V1 + V2\nSsr Saulces - Poix V1 + V2",null,null,"205000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F69006",null,"< >",5234,5379,2027,2027,45,48,"2027-11-01","00:00:00","2027-11-21",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2 sem DEF \n5Nuits LuMa à VeSa",null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F69022",null,"< >",5032,5040,2027,2027,5,11,"2027-01-25","00:00:00","2027-03-07",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F69171",null,"< >",5278,8316,2027,2027,3,6,"2027-01-11","00:00:00","2027-01-31",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"640000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F69171",null,"< >",5412,5413,2027,2027,3,5,"2027-01-11","00:00:00","2027-01-24",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"640000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F69171",null,"< >",5225,5226,2027,2027,4,6,"2027-01-18","00:00:00","2027-01-31",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"650000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F69276",null,"< >",4942,5000,2027,2027,38,44,"2027-09-13","00:00:00","2027-10-24",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2 x fermeture ligne 4jours : du Lu midi au Ve midi",null,null,"611000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F69319",null,"< >",5190,5807,2027,2027,20,31,"2027-05-10","00:00:00","2027-07-25",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F69319",null,"< >",5190,5807,2027,2027,22,27,"2027-05-24","00:00:00","2027-06-27",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F69319",null,"< >",5190,5807,2027,2027,22,27,"2027-05-24","00:00:00","2027-06-27",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"2"]
[null,"SNCF-R","F69646",null,"< >",3214,3283,2027,2027,5,9,"2027-01-25","00:00:00","2027-02-21",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"5S DEF 5h00 Sim V1 V2 de nuit\n4S DEF 6h00 Sim V1 V2 de nuit\nZEP V1 Moteville/Yvetot - ZEP V2 Yvetot/Motteville - ZEP 2+7+5 de Motteville\nSous secteur Motteville Foucart V1 et V2",null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","F69646",null,"< >",3214,3283,2027,2027,18,25,"2027-04-26","00:00:00","2027-06-13",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"5S DEF 5h00 Sim V1 V2 de nuit\n4S DEF 6h00 Sim V1 V2 de nuit\nZEP V1 Moteville/Yvetot - ZEP V2 Yvetot/Motteville - ZEP 2+7+5 de Motteville\nSous secteur Motteville Foucart V1 et V2",null,null,"340000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","F69928",null,"< >",4881,4889,2027,2027,38,46,"2027-09-13","00:00:00","2027-11-07",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"OCP seulement Voies impaires",null,null,"640000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","Fem 26776",null,"< >",2558,2558,2027,2027,28,31,"2027-07-05","00:00:00","2027-07-25",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2S DEF 8h00 de nuit Domaine A (V1 et V2 259000 + VZ + VS)\n2S DEF 8h00 de nuit Domaine B (VZ + VS)\nDomaine A:\nZEP 512+514+515+518+519+520+535+536+537+36611+36621+36618+36636+36634+36648+36652+36644\nSél 36507 - 36509 du SSr Sin Départ\nSél 36510 - 36512 du SSr Sin Arrivée\nSél 217+36564-219-213-207+209-211 du SSr Douai VS\nDomaine B:\nZEP 512+514+515+518+519+520+535+536+537\nSél 217+36564-219-213-207+209-211 du SSr Douai VS",null,null,"259000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","FEM 26931",null,"< >",2069,2069,2027,2027,42,46,"2027-10-11","00:00:00","2027-11-07",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"3S DEF 6h00 de nuit Sim Voies 4, 6, 8, 10, O et P\nZEP 20631+20632+20633+20635+20618+20630+20628+20636+20634+20642+20644+20646+20648+20649+20650+21610+21612+21614+21616+217+218+219+21626+21630+21634+263+21618+21620+21624\n1 WE de 24h00 Sim Voies 1, 2, 4, 6, 8, 10, O et P\nDomaine A + ZEP 20623+20625+20627+20620+20622+20624+20640+21601+21603+21605+21602+21604+21632+21634+263+255+256+259+260",null,null,"242000",45574,"High","1,2,3,4,5,6,7",null,null,"02049",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","FEM 32385",null,"< >",3859,3858,2027,2027,14,17,"2027-03-29","00:00:00","2027-04-18",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"2 sem DEF 8h SIM",null,null,"515000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","FEM 32956",null,"< >",1851,1852,2027,2027,6,8,"2027-02-01","00:00:00","2027-02-14",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1S DEF de 7h00 de nuit Sim V1 V2\nDFV Type L \nZEP DUNKERQUE - HAZEBROUCK voie 2 (TTx)\nZEP HAZEBROUCK - DUNKERQUE voie 1 (TTx)\nSecteur Coudekerque DL",null,null,"301000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","FEM 35417",null,"< >",4018,4016,2027,2027,40,44,"2027-09-27","00:00:00","2027-10-24",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"3 semaines Tx en gare",null,null,"500000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","G10571",null,"< >",2884,2884,2027,2027,3,6,"2027-01-11","00:00:00","2027-01-31",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"12 OCP de coupure partielle de plateforme\n\nPertes de temps < 2min",null,null,"420000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","G13345",null,"< >",5191,5191,2027,2027,3,18,"2027-01-11","00:00:00","2027-04-25",0.99998842592592585,"104 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"640000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","J82276",null,"< >",4660,4665,2027,2027,19,21,"2027-05-03","00:00:00","2027-05-16",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Capa à  l'ombre AFSB\n2 OCP 72H et 116 pour forages dirigés sous voies",null,null,"640000",45574,"Major","1,2,3,4,5,6,7",null,null,"05765",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","J82276",null,"< >",4660,4665,2027,2027,44,50,"2027-10-25","00:00:00","2027-12-05",0.99998842592592585,"41 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Capa à  l'ombre AFSB\n2 OCP 72H et 116 pour forages dirigés sous voies",null,null,"640000",45574,"Major","1,2,3,4,5,6,7",null,null,"05765",null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","JH3422",null,"< >",5692,5693,2027,2027,4,30,"2027-01-18","00:00:00","2027-07-18",0.99998842592592585,"181 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Gen Nuit Sim 7h20 Puyoo/Artix -> 8h en ZEP gare ",null,null,"650000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH3499",null,"< >",1719,1719,2027,2027,3,11,"2027-01-11","00:00:00","2027-03-07",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","JH3499",null,"< >",1719,1719,2027,2027,3,7,"2027-01-11","00:00:00","2027-02-07",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH3715",null,"< >",2531,2531,2027,2027,7,38,"2027-02-08","00:00:00","2027-09-12",0.99998842592592585,"216 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"48S DEF 7h00 Sim V1 V2 VS de jour\n5WE de 48h Sim V1 V2 + VS\nZEP 402 \"type L Ostricourt Lens V2\" + Type L Lens Ostricourt V1 + ZEP C (toutes les VS)\nSous-secteur Ostricourt - Billy V2  SEL 66 et SEL 1064 et Sous-secteur  Ostricourt Billy V1 SEL 65 et 67\nSEL voies de service 102, 104 et 106 ",null,null,"284000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH3715",null,"< >",2531,2531,2027,2027,7,38,"2027-02-08","00:00:00","2027-09-12",0.99998842592592585,"216 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"48S DEF 7h00 Sim V1 V2 VS de jour\n5WE de 48h Sim V1 V2 + VS\nZEP 402 \"type L Ostricourt Lens V2\" + Type L Lens Ostricourt V1 + ZEP C (toutes les VS)\nSous-secteur Ostricourt - Billy V2  SEL 66 et SEL 1064 et Sous-secteur  Ostricourt Billy V1 SEL 65 et 67\nSEL voies de service 102, 104 et 106 ",null,null,"284000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","JH3865",null,"< >",5936,5936,2027,2027,14,32,"2027-03-29","00:00:00","2027-08-01",0.99998842592592585,"125 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"Génériques longues",null,null,"750000",45574,"Major","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH4113",null,"< >",3919,3920,2027,2027,15,45,"2027-04-05","00:00:00","2027-10-31",0.99998842592592585,"209 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"538000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","JH4113",null,"< >",3919,3920,2027,2027,15,46,"2027-04-05","00:00:00","2027-11-07",0.99998842592592585,"216 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"538000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH4171",null,"< >",1703,1703,2027,2027,18,22,"2027-04-26","00:00:00","2027-05-23",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH4287",null,"< >",8754,8754,2027,2027,3,7,"2027-01-11","00:00:00","2027-02-07",0.99998842592592585,"27 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"1"]
[null,"SNCF-R","JH4287",null,"< >",8754,8754,2027,2027,16,26,"2027-04-12","00:00:00","2027-06-20",0.99998842592592585,"69 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH4292",null,"< >",2046,2046,2027,2027,8,13,"2027-02-15","00:00:00","2027-03-21",0.99998842592592585,"34 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"50 S DEF 8h00 Sim V1 V3\n1 WE de 72h Sim V1 V3 (S12/S13)\nZEP 23, 26\nSSr HAUMONT-JEUMONT voie 1 SEL 5 (découpage caténaire à réaliser en talon du brt 35a) et SEL 109 \n1 WE de 48h + nuit Lu/Ma Sim Voie 1, Voie 3, voie 5, voie 7, Voie 2 et voie 8 (S40/S41)\nZEP 23, 26, 22, 27, 28, 14, 42\nSSr HAUMONT-JEUMONT voie 1 SEL 5 (découpage caténaire à réaliser en talon du brt 35a) et SEL 109. Sel 111, SEL 113, SEL 6A, SEL122\nFermeture du quai 1 de 2026 jusqu'à S4 (2027)",null,null,"242000",45574,"High","1,2,3,4,5,6,7",null,null,"02049",null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH4314",null,"< >",4141,4140,2027,2027,3,6,"2027-01-11","00:00:00","2027-01-31",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"PASO : 6sem Def jours\nQUAI : 6 sem Def nuits.",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH4314",null,"< >",4141,4140,2027,2027,19,26,"2027-05-03","00:00:00","2027-06-20",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"PASO : 6sem Def jours\nQUAI : 6 sem Def nuits.",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH4315",null,"< >",4134,4134,2027,2027,37,44,"2027-09-06","00:00:00","2027-10-24",0.99998842592592585,"48 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"DEF Nuits 8H 1V \n4nuits LuMa à JeVe",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH4618",null,"< >",4440,4443,2027,2027,25,34,"2027-06-14","00:00:00","2027-08-15",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"8 Sem DEF nuiits en raison de Tx refection quais voyageurs",null,null,"570000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH4720",null,"< >",5879,5879,2027,2027,3,18,"2027-01-11","00:00:00","2027-04-25",0.99998842592592585,"104 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"SA2026 : 6 OCP de 45h de coupure de l'ensemble de la plateforme.\nEn semaine, travail de nuit 2v/4.",null,null,"830000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JH4856",null,"< >",700,701,2027,2027,21,44,"2027-05-17","00:00:00","2027-10-24",0.99998842592592585,"160 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"19S DEF 7h30 de sim V1V2 de Jour\n1 We de 70h00\n1 WE de 54h00\nAttention S21 interdite de travaux (Athus Meuse)\nDFV type L Lumes -Sedan V1 et V2\nSEL 11+13 V1 et 12 V2 Ssr Mohon Donchery / SEL 17 V1 et 16 V2 Ssr Donchery - Sachy",null,null,"204000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JJ8631",null,"< >",3742,3757,2027,2027,14,16,"2027-03-29","00:00:00","2027-04-11",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"1 semaine pour isolement en site propre : Immo Aig et Découpage CAT",null,null,"515000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JJ9082",null,"< >",5041,5043,2027,2027,6,15,"2027-02-01","00:00:00","2027-04-04",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JJ9083",null,"< >",5358,5359,2027,2027,6,17,"2027-02-01","00:00:00","2027-04-18",0.99998842592592585,"76 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JJ9084",null,"< >",5377,5377,2027,2027,14,23,"2027-03-29","00:00:00","2027-05-30",0.99998842592592585,"62 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"590000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JJ9346",null,"< >",1539,1532,2027,2027,31,51,"2027-07-26","00:00:00","2027-12-12",0.99998842592592585,"139 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"272000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JK3254",null,"< >",1175,1175,2027,2027,18,20,"2027-04-26","00:00:00","2027-05-09",0.99998842592592585,"13 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"3S DEF 7h00 sim de jour V1 V2 V2bis et faisceau V1V2\n4WE de 24h00 V1V2V2bis et faisceau V1V2\n\nZEP 14 + ZEP 33 + ZEP 37\n\nSEL: SSr Lopigneux Baroncourt V2 + SSr Lopigneux Baroncourt V1+VS + Sèl 60 + Feder B",null,null,"95000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JK4840",null,"< >",1852,1852,2027,2027,38,41,"2027-09-13","00:00:00","2027-10-03",0.99998842592592585,"20 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"12S DEF 7h00 de jour Sim V1 V2\n8S DEF 7h00 de nuit Sim V1 V2\n1 WE de 48h Sim V1 V2\nZEP DUNKERQUE-HAZEBROUCK VOIE 1 et ZEP HAZEBROUCK-DUNKERQUE VOIE 2\nSECTEUR COUDEKERQUE DL V1 / V2\n",null,null,"301000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","Jk6258",null,"< >",1322,1322,2027,2027,16,24,"2027-04-12","00:00:00","2027-06-06",0.99998842592592585,"55 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"7S DEF 4h30 Sim de nuit V1 V2\n1 WE de 48h00 Sim V1 V2\n1 WE de 65h00 Sim V1 V2\n1 WE de 60h00 Sim V1 V2\nZEP 817 et 932 de Wilwisheim\nSEL 8 et 9 du SSR Lupstein Wilwisheim\n",null,null,"70000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]
[null,"SNCF-R","JK8305",null,"< >",8088,8088,2027,2027,27,39,"2027-06-28","00:00:00","2027-09-19",0.99998842592592585,"83 days + 23 h 59 min","Continuous","Miscellaneous",null,null,null,null,null,null,null,null,null,null,null,null,null,"229000",45574,"High","1,2,3,4,5,6,7",null,null,null,null,null,"Publication",null,null,null,"0"]

{"sheet":"Data","index":7,"n_rows":24,"n_cols":7,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction"]
["SNCF R",87,"Boulogne-Calais",1,"All day",10868,"Signal work"]
[null,null,"Calais-Dunkerque-Hazebrouck",2,"Day",null,"Switch work"]
[null,null,"Calais-Lille-Aulnoye",3,"Night",null,"Catenary work"]
[null,null,"Hazebrouck-Lens-Aulnoye",4,null,null,"Track work"]
[null,null,"Amiens-Douai",5,null,null,"Rail work"]
[null,null,"Paris-Amiens",6,null,null,"Tunnel work"]
[null,null,"Paris-Busigny",7,null,null,"Bridge work"]
[null,null,"Aulnoye-Longuyon",8,null,null,"Misc. Work"]
[null,null,"Longuyon-Metz-Sarrebourg",9,null,null,"Maintanance"]
[null,null,"Longuyon-Nancy-Sarrebourg",10]
[null,null,"Lerouville-Metz",11]
[null,null,"Lerouville-Nancy",12]
[null,null,"Sarrebourg-Basel",13]
[null,null,"Dijon-Toul",14]
[null,null,"Dijon-Lyon",15]
[null,null,"Dijon-Amberieu-Lyon",16]
[null,null,"Lyon-Valence",17]
[null,null,"Valence - Avignon",18]
[null,null,"Avignon-Miramasparouest",19]
[null,null,"Avignon-Miramasparest",20]
[null,null,"Miramas-Marseille",21]
[null,null,"Miramas-Fos-Marseille",22]
[null,null,"Aulnoye-Feignies-Jeumont",23]